## Complete Project
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
| State funds not available for match. | Delay project | 1 | 5 | Medium | Funding Uncertainties
| Legislative approval not granted. | Have Dept. Legislative Liaison monitor status of budget and work with Legislature as needed. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties
| Unanticipated utility relocation required. | Project design >95% complete. Add construction funds and/or change order. | 1 | 3 | Low | Construction Risks
| Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties
| Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 1 | Low | Cost Uncertainties
| Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A. Project design >95% complete. | 1 | 1 | Low | Cost Uncertainties | Categories from the NOFO
| Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties | Procurement Delays
| Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties | Environmental Uncertainties
| Individual USACE permit or USCG permit required. | Permits already accounted for. | 1 | 1 | Low | Environmental Uncertainties | Cost Uncertainties
| Project environmental document not approved in time. | Dynamic regional resource management. | 1 | 3 | Low | Environmental Uncertainties | Funding Uncertainties
| Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Risk already assessed. Project design >95% complete. | 1 | 3 | Low | Environmental Uncertainties | Natural Hazard Risks
| Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 4 | Low | Funding Uncertainties | Construction Risks
| Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Dynamic regional resource management. | 1 | 2 | Low | Other Risks | Other Risks

## SRW #603
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
603 | Deck concrete deteriorates faster than anticipated during design and change order needed to address additional deck repairs | Add contingency to deck area or cost in engineer's estimate | 3 | 2 | Medium | Construction Risks
603 | State funds not available for match. | Delay project | 1 | 5 | Medium | Funding Uncertainties | Categories from the NOFO
603 | Legislative approval not granted. | Have Dept. Legislative Liaison monitor status of budget and work with Legislature as needed. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Procurement Delays
603 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Dynamic regional resource management. | 1 | 2 | Low | Other Risks | Environmental Uncertainties
603 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Cost Uncertainties
603 | Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 1 | Low | Cost Uncertainties | Funding Uncertainties
603 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A. Project design >95% complete. | 1 | 1 | Low | Cost Uncertainties | Natural Hazard Risks
603 | Individual USACE permit or USCG permit required. | Permits already accounted for. | 1 | 1 | Low | Environmental Uncertainties | Construction Risks
603 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties | Other Risks
603 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
603 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 4 | Low | Funding Uncertainties
603 | Project environmental document not approved in time. | Dynamic regional resource management. | 1 | 3 | Low | Environmental Uncertainties
603 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Risk already assessed. Project design >95% complete. | 1 | 3 | Low | Environmental Uncertainties
603 | Unanticipated utility relocation required. | Project design >95% complete. Add construction funds and/or change order. | 1 | 3 | Low | Construction Risks
603 | Bids for rehabilitation projects are often more unpredictable than new construction bids | Add contingency to costs to account for uncertainty | 3 | 1 | Low | Cost Uncertainties
603 | Polyester concrete is reportely being used more often in Oregon which could drive up prices in Alaska. | Add contingency to costs to account for uncertainty | 2 | 1 | Low | Cost Uncertainties

## SRC #605
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category
605 | State funds not available for match. | Delay project | 1 | 5 | Medium | Funding Uncertainties
605 | Deck concrete deteriorates faster than anticipated during design and change order needed to address additional deck repairs | Add contingency to deck area or cost in engineer's estimate | 2 | 3 | Medium | Construction Risks | Categories from the NOFO
605 | Legislative approval not granted. | Have Dept. Legislative Liaison monitor status of budget and work with Legislature as needed. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties | Procurement Delays
605 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Dynamic regional resource management. | 1 | 2 | Low | Other Risks | Environmental Uncertainties
605 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Cost Uncertainties
605 | Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 1 | Low | Cost Uncertainties | Funding Uncertainties
605 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A. Project design >95% complete. | 1 | 1 | Low | Cost Uncertainties | Natural Hazard Risks
605 | Individual USACE permit or USCG permit required. | Permits already accounted for. | 1 | 1 | Low | Environmental Uncertainties | Construction Risks
605 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties | Other Risks
605 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
605 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 4 | Low | Funding Uncertainties
605 | Project environmental document not approved in time. | Dynamic regional resource management. | 1 | 3 | Low | Environmental Uncertainties
605 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Risk already assessed. Project design >95% complete. | 1 | 3 | Low | Environmental Uncertainties
605 | Unanticipated utility relocation required. | Project design >95% complete. Add construction funds and/or change order. | 1 | 3 | Low | Construction Risks
605 | Bids for rehabilitation projects are often more unpredictable than new construction bids | Add contingency to costs to account for uncertainty | 3 | 1 | Low | Cost Uncertainties
605 | Polyester concrete is reportely being used more often in Oregon which could drive up prices in Alaska. | Add contingency to costs to account for uncertainty | 2 | 1 | Low | Cost Uncertainties

## Victor #607
Risk Register
Bridge No(s). | Risks | Mitigation Strategy | Probability (1 low/5 high) | Severity (1 low/5 high) | Risk Rating | Category | Comments
607 | State funds not available for match. | Delay project | 1 | 5 | Medium | Funding Uncertainties |  | Categories from the NOFO
607 | Existing bridge continues to deteriorate and requires load restrictions (similar to what occurred at the nearby Trail River Bridge) | Install temporary detour using the Department's trestle or modular truss bridge | 2 | 5 | Medium | Natural Hazard Risks | The existing bridge has NBI rating of 5 for deck, super and sub. The likelihood of deterioration seems high. The existing load rating is HS12 for inventory - this is low and further deterioration may require load posting. | Procurement Delays
607 | Design event earthquake or flood occurs damaging the existing bridge | Install temporary detour using the Department's trestle or modular truss bridge | 1 | 5 | Medium | Natural Hazard Risks | The exiting bridge is vulnerable to damage resulting from natural hazards such as earthquake and flood. | Environmental Uncertainties
607 | Second concrete precaster in Alaska retires and lack of competition drives up girder prices | Include contingency in estimate. | 3 | 2 | Medium | Cost Uncertainties | In general, the uncertainty that accompanies most bridge construction projects is applicable to this bridge. | Cost Uncertainties
607 | Legislative approval not granted. | Have Dept. Legislative Liaison monitor status of budget and work with Legislature as needed. As a last resort, delay project | 1 | 5 | Medium | Funding Uncertainties |  | Funding Uncertainties
607 | Unanticipated utility relocation required. | Project design >95% complete. Add construction funds and/or change order. | 1 | 3 | Low | Construction Risks |  | Natural Hazard Risks
607 | Cost inflation due to lack of information (e.g. no foundation drilling conducted yet or utility impacts not known). | Include contingency. | 1 | 2 | Low | Cost Uncertainties | Design and check are 99% complete. No significant design changes are anticipated. | Construction Risks
607 | Cost inflation due to real estate price increase. | Not necessary. Project has minor ROW costs. | 1 | 1 | Low | Cost Uncertainties |  | Other Risks
607 | Cost negotiations with design consultant delay NTP and subsequent advertise date. | N/A. Project design >95% complete. | 1 | 1 | Low | Cost Uncertainties | Bridge design is essentially complete
607 | Material escalation due to limited suppliers and competing work. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
607 | Material escalation due to tariffs or inflation. | Add funds or delay project. | 1 | 3 | Low | Cost Uncertainties
607 | Individual USACE permit or USCG permit required. | Permits already accounted for. | 1 | 1 | Low | Environmental Uncertainties
607 | Project environmental document not approved in time. | Dynamic regional resource management. | 1 | 3 | Low | Environmental Uncertainties
607 | Project located in area of high environmental scrutiny or with special environmental/regulatory area of concern (e.g. 4(f) resources, T&E species) | Risk already assessed. Project design >95% complete. | 1 | 3 | Low | Environmental Uncertainties
607 | Other (e.g. STIP or State) funds required for portions of work that do not meet grant program requirements (e.g. significant roadway realignment needed to meet geometric standards). | Other funds already identified. | 1 | 4 | Low | Funding Uncertainties
607 | Competing support group resources impact project schedule (e.g. can't get Statewide Foundations out in time) | Dynamic regional resource management. | 1 | 2 | Low | Other Risks | The subsurface investigation has been completed
607 | Overrun of piling during construction resulting in the need for deeper piles and more time for construction | Add funds and include in contingency. | 2 | 1 | Low | Procurement Delays | In general, the uncertainty that accompanies most bridge construction projects is applicable to this bridge.
607 | Polyester concrete is reportely being used more often in Oregon which could drive up prices in Alaska. | Add contingency to costs to account for uncertainty | 2 | 1 | Low | Cost Uncertainties | In general, the uncertainty that accompanies most bridge construction projects is applicable to this bridge.