## CY23_Polygons_Final_Dash_4_17_2
OBJECTID | IRIS Number | Project Name | Anticipated Completion Month | Anticipated Start Month | Construction Manager | Construction Manager Phone | Estimated Contract Dollar Amount | County Name | Design Manager | Design Manager Phone | Federal Poject Number | Funding Type | House District | Project Description | Project Impact | Project Lane miles | Project Type | Project Website | Route ID | Senate District | Why Construct?
1 | CFAPT00276 | Togiak Airport Resurfacing | 2023-08-01 | 2023-05-01 | Ericka Moore | 9072694550 | 6487530 | Dillingham Census Area | Paul Song, EMC | 9072694550 |  | FAA | State House District 37 | Rehabilitate the runway, taxiway, and apron. The project will also replace airport lighting. Application of a dust palliative anticipated in the summer of 2023. | Anticipate runway will be closed in 2023 for short durations to apply dust palliative. |  | Aviation |  |  | State Senate District S
2 | CFAPT00288 | Mekoryuk Airport Rehabilitation | 2023-09-24 | 2023-06-23 |  | 0 | 25000000 | Bethel Census Area | Phil Cheasebro, P.E. | 9072690606 | 3-02-0178-xxx-2023 | FAA | State House District 38 | The Mekoryuk Airport Rehabilitation project proposes to rehabilitate the runway, taxiway, apron, and access road; install aircraft tie-downs; replace lighting system and construct new Electrical Equipment Building (EEB); remove lighting equipment from existing SREB; construct new primary wind cone and segmented circle on a new pad adjacent to apron; remove rotating beacon from existing SREB and construct new rotating beacon on a tilt-down pole; construct new double bay SREB on new pad adjacent to the apron; replace existing culverts; drainage improvements. Corresponding SREB project: CFAPT00269 | There will be temporary impacts to the public approach procedures during construction, however there will be no permanent impacts. |  | Aviation |  | N/A | State Senate District S | The purpose of this project is to meet safety, operational and maintenance needs. The airport surfaces are in poor condition with surface material missing in some areas and the lighting system is beyond service life.
3 | CFAPT00292 | Ekwok & New Stuyahok Airport Resurfacing | 2023-08-01 | 2023-05-01 | Lorett Nabong | 9072690670 | 11497971 | Dillingham Census Area | Steve Reed, HDL | 9072690670 |  | FAA | State House District 37 |  | Runway and taxiway operations will be reduced to half‐width during construction. Apron repair activities will reduce the size of the usable apron during construction. |  | Aviation |  |  | State Senate District S
4 | CFAPT00293 | Sleetmute Airport Resurfacing | 2023-09-24 | 2023-05-23 | Ericka Moore | 9072694550 | 18914841.5 | Bethel Census Area | Aaron Hughes | 9072690523 | 3-02-0272-000-2022 | FAA | State House District 37 | The project proposes to resurface the gravel runway (including safety area), taxiway (including safety area), and apron. Improvements include a new double-bay snow removal equipment building, lighting, markings, DOT&PF owned visual aids, drainage, vegetation clearing, and a dust palliative. The runway safety areas will be extended to meet current standards. | Runway and taxiway operations will be reduced to half‐width during daytime construction with nighttime closures. Usable apron size will be reduced during daytime construction with nighttime closures. |  | Aviation |  |  | State Senate District S | The purpose of the project is to replace aging surface course and supporting infrastructure. A combination of poor drainage and aging surface material is causing soft conditions on the operational surface. Resurfacing the operational areas will improve s
5 | CFAPT00310 | Newtok Airport Relocation | 2023-08-01 | 2023-04-01 | Jacob Gondek, | 9072690445 | 22686977 | Bethel Census Area | Jake Goodell, EMC | 9072690445 |  | FAA | State House District 38 |  | Anticipate new runway will be closed in the summer of 2023 for short durations to apply dust palliative. |  | Aviation |  |  | State Senate District S
6 | CFAPT00403 | Cold Bay Airport Chemical/SRE Building | 2023-05-01 | 2023-01-01 |  |  | 6683000 | Aleutians East Borough | Mike Gillen | 9072690804 |  | FAA | State House District 37 | Construct an Airport SRE and chemical storage building. Demolish the abandoned fire hall building. | Flight operations should not be affected. |  | Aviation |  |  | State Senate District S
7 | CFAPT00426 | Atmautluak Airport Improvements | 2023-05-01 | 2023-01-01 | Ron Searcy, | 2690656 | 7485866 | Bethel Census Area | Dave Wood, R&M | 2690656 |  | FAA | State House District 38 | Resurface the runway, taxiway, safety areas, apron, and access road. The project will also replace airport lighting systems, remove brush obstructions within the Object Free Area, and construct a new heated single bay Snow Removal Equipment Building. | Night time runway closures during 2021 to rehabilitate runway, RSA, and replace lighting system. |  | Aviation |  |  | State Senate District S
8 | CFAPT00427 | Nunapitchuk Airport Improvements | 2023-08-01 | 2023-04-01 | Ron Searcy | 9072690656 | 6485127 | Bethel Census Area | Dave Wood, R&M | 9072690656 |  | FAA | State House District 38 | Resurface the runway, taxiway, and apron. The project will also replace airport lighting systems and apply dust palliative. | Night time runway closures during 2022 to rehabilitate runway and replace lighting system. |  | Aviation |  |  | State Senate District S
9 | CFAPT00433 | Kongiganak, Alaska Airport Improvements | 2023-10-24 | 2023-06-23 |  | 9072690606 | 55000000 | Bethel Census Area | Phil Cheasebro, P.E. | 9072690606 | 3-02-0380-004-2022 | FAA | State House District 38 | The Kongiganak Airport Improvement Project proposes to rehabilitate the existing runway, taxiway, apron, visual navigational aid pads; expand Runway Safety Area to accommodate ADG II aircraft; expand apron and construct SREB pad; relocate the existing SREB, electrical equipment building, fuel tanks, and associated electrical connections; relocate and extend primary electrical service to relocated SREB; install new single bay SREB; install aircraft tie-downs; install a new rotating beacon; replace airfield lighting system; improve drainage; replace airport signage; place dust palliative on all resurfaced and expanded areas. | During construction activities the runway may be reduced to half-width operations with the issuance of a NOTAM, airport closure is not anticipated. |  | Aviation |  |  | State Senate District S | The purpose of the proposed project is to improve safety, lower maintenance costs, and extend the service life of the airport. The communities dependence of the airports functions for MEDEVAC services, passenger transportation, cargo, and mail services i
10 | CFAPT00465 | ANC Taxiway Z West Improvements | 2023-09-25 | 2023-01-23 | Mahear Aboueid | 9072690446 | 45000000 | Anchorage Municipality | Phil Cheasebro | 9072690606 | 3-02-0016-2018-2023 | FAA | State House District 21 | This Federally Funded contract provides geometric upgrades as necessary to accommodate larger ADG VI, TDG 6 aircraft. The proposed geometric upgrades include widening Taxiway's Z & E, constructing a new entrance Taxiway R, and rehabilitating Taxilane's R & E. Additional work includes: • Rehabilitate or relocate existing private taxilane approaches as needed • Remove TW F entrance taxiway • Relocate existing service road • Drainage improvements • Replace taxiway lighting and sign and install new lights and signs as needed • Relocate/adjust utilities as needed • Relocate/adjust FAA NAVAIDS as needed | Temporary taxilane bypasses will be implemented to detour aircraft traffic around work zones. Runway 7R-25L will be temporarily closed as needed to tie taxiways into the runway. |  | Aviation |  | N/A | State Senate District K | The existing TW Z meets ADG III standards and must be reconstructed to ADG VI standards to accommodate future aircraft demand.
11 | CFAPT00491 | Homer Airport Improvements | 2023-10-24 | 2023-05-23 | Jacob Gondek, P.E. | 9072690445 | 35000000 | Kenai Peninsula Borough | Matthew Hansen, P.E. | 9072690602 | 3-02-0122-021-2023 | FAA | State House District 31 | This project proposes to rehabilitate the runway and runway safety area; remove terrain obstructing the runway object free area; rehabilitate Taxiways A, B, and a portion of D; remove a portion of Taxiway D and convert it to an airfield service road; construct a new turnaround taxiway (Taxiway G) near the Runway 22 threshold; rehabilitate and expand the General Aviation apron; construct drainage improvements including replacement of culverts crossing the runway and taxiways; remove existing VASIs and replace with PAPIs; replace runway and taxiway lighting and signage systems. | During 2023 construction, runway operations will be reduced to half‐width during the day with full closures at night and individual taxiways will be temporarily closed while under construction. During 2024 construction, portions of the General Aviation |  | Aviation | https://dot.alaska.gov/creg/homerairport/ |  | State Senate District P | This project is necessary to improve the condition of the airfield pavements, runway/taxiway lighting, and drainage structures at the Homer Airport. The runway and taxiway widths will be updated to current standards and a new taxiway will be added to all
12 | CFAPT00501 | Chefornak Airport Rehabilitation | 2023-10-24 | 2023-05-23 | Jake Gondek | 9072690445 | 26717608.85 | Bethel Census Area | Aaron Hughes | 9072690523 | 3-02-0442-003-2021 | FAA | State House District 38 | The project will resurface the gravel runway, taxiway, access road, and apron (including safety areas). Improvements include airfield lighting, markings, drainage, dust palliative, and visual NAVAIDS. | Runway and taxiway operations will be reduced to partial widths during daytime construction with nighttime closures. Usable apron size will be reduced during daytime construction with nighttime closures. |  | Aviation |  |  | State Senate District S | The airports operational surfaces currently have areas of subsidence, ponding, and dips. Resurfacing the operational areas will improve safety and reduce maintenance efforts necessary to keep the airport operational.
13 | CFAPT00505 | Kipnuk Airport Rehabilitation | 2023-10-15 | 2022-01-01 | Lorett Nabong | 9072690670 | 14085571.75 | Bethel Census Area | Aaron Hughes | 9072690523 | 3-02-0150-005-2021 | FAA | State House District 38 | This project resurfaces the gravel runway (RW 17-35), taxiway, and apron. The runway will be widened and RSA expanded. Improvements also include airport lighting, visual navigational aids, dust palliative, and aircraft tie-downs. | Runway and taxiway operations will be reduced to half‐width during daytime construction with nighttime closures. Usable apron size will be reduced during daytime construction with nighttime closures. |  | Aviation |  |  | State Senate District S | The operational surfaces need to be rehabilitated to correct undulations, dips, and cracking. Additionally, the runway needs to be expanded to meet the standards for the current design aircraft. The improvements will improve safety and reduce mainten
14 | CFAPT00718 | ANC GATES B4, B6, B7, B8, & B9 IMPROVEMENTS | 2023-10-23 | 2023-04-23 |  | 0 | 3000000 | Anchorage Municipality | Phil Cheasebro, P.E. | 9072690606 | 3-02-0016-214-2022 | FAA | State House District 21 | The ANC Gates B4, B6-B9 Reconstruction project proposes to reconstruct the concrete hardstands at ANC Gates B4, B6, B7, B8, and B9; remove lead in lights to Gates B4, B6, and B8; reconstruct / improve airport drainage system; replace the fuel hydrant system as required; reapply painted airport markings. | There are no impacts to FAA navigation aids associated with the project. There are no impacts to Public and Special Approach Procedures associated with the project. |  | Aviation |  |  | State Senate District K | Continued degradation of the pavement could result in potential damage to aircraft and surface transportation vehicles due to cracks, FOD, and other impediments if the project is not implemented.
15 | CFAPT00855 | ANC Taxiway K, G1, and J Improvements & FAA Taxilane Pavement Rehabilitation | 2023-05-01 | 2023-07-21 | Mahear Abou Eid | 2690446 | 16138894 | Anchorage Municipality | Mahear Abou Eid | 2690446 |  | FAA | State House District 21 | Rehabilitate the apron pavement north of Taxiway K and east of Taxilane E. | Temporary runway, taxiway, and parking closures along with aircraft traffic rerouting. |  | Aviation |  |  | State Senate District K
16 | CFAPT00855 | ANC TW K and TL E Apron Rehabilitation | 2023-05-01 | 2023-07-21 | Mahear Abou Eid | 2690446 | 16138894 | Anchorage Municipality | Mahear Abou Eid | 2690446 |  | FAA | State House District 21 | Rehabilitate the apron pavement north of Taxiway K and east of Taxilane E. | Temporary runway, taxiway, and parking closures along with aircraft traffic rerouting. |  | Aviation |  |  | State Senate District K
17 | CFAPT00880 | ANC TW K‐R Intersection Joint Repairs | 2023-10-01 | 2023-07-01 | Mahear Abou Eid | 2690446 | 750000 | Anchorage Municipality | TBD | 2690446 |  | FAA | State House District 21 | The project will rehabilitate the concrete joints and panels. Project includes concrete removal, hydro demolition, PCC pavement, elastomeric and epoxy repairs and joint sealant. | Temporary closures of the intersection along with aircraft rerouting. |  | Aviation |  |  | State Senate District K
18 | CFAPT00881 | ANC NT Baggage Handling System Improvements | 2023-04-01 | 2023-01-01 | Jesse Campbell | 2662723 | 254114 | Anchorage Municipality | Ken Banning | 2662196 |  | FAA | State House District 21 | Replace flooring and wainscot, and paint in North Terminal circulation areas at boarding level. | Coordinate with tenants and for work within the sterile area. |  | Aviation |  |  | State Senate District K
19 | CFAPT00881 | ANC NT Circulation Finishes | 2023-04-01 | 2023-01-01 | Jesse Campbell | 2662723 | 254114 | Anchorage Municipality | Ken Banning | 2662196 |  | FAA | State House District 21 | Replace flooring and wainscot, and paint in North Terminal circulation areas at boarding level. | Coordinate with tenants and for work within the sterile area. |  | Aviation |  |  | State Senate District K
20 | CFAPT00881 | ANC NT Ticket and Gate CUPPS | 2023-04-01 | 2023-01-01 | Jesse Campbell | 2662723 | 254114 | Anchorage Municipality | Ken Banning | 2662196 |  | FAA | State House District 21 | Replace flooring and wainscot, and paint in North Terminal circulation areas at boarding level. | Coordinate with tenants and for work within the sterile area. |  | Aviation |  |  | State Senate District K
21 | CFAPT00882 | LHD Aircraft and Lakeshore Drive Rehabilitate | [5 empty] | Anchorage Municipality |  |  |  |  | State House District 21 | [6 empty] | State Senate District K
22 | CFAPT00983 | ANC Security Fencing Improvements 2023 | 2023-09-23 | 2023-06-23 | Mahear Abou Eid | 2690446 | 400000 | Anchorage Municipality | TBD | 2690446 |  | FAA | State House District 21 | The project will remove and install approximately 1,000 feet new security fencing and one swing gate. Project includes grading, new culvert, subbase, topsoil and seeding. | No operational impacts. |  | Aviation |  |  | State Senate District K
23 | CFAPT00993 | ANC Terminal Water Main Improvments | 2023-07-25 | 2023-07-23 | Mahear Abou Eid, P.E. | 9072690446 | 10000000 | Anchorage Municipality | Matthew Hansen, P.E. | 9072690602 | 3-02-0016-###-2023 | FAA | State House District 21 | This project proposes to improve approximately 6,000 feet of existing underground water main pipes by trenchless techniques that serve the North Terminal, Concourse C, Concourse A, and the old Airfield Maintenance Building at Anchorage International Airport. All hydrants and water valves that are encountered will be replaced and additional valves will be installed where needed. A section of water main located under Concourse A with a valve that is currently closed and no longer in use will be abandoned. | Construction activities will occur under and around aircraft gates at Concourse A, Concourse C, and the North Terminal. Access to certain gates at Concourse C and North Terminal will be temporarily restricted during construction phases and operations div |  | Aviation |  |  | State Senate District K | The existing water mains provide water for firefighting protection for the Terminal and old Airfield Maintenance Building. The pipes are estimated to have between 5-15 years of remaining life and require lining to extend their useful life and prevent the
24 | CFAPT00996 | ANC B9 Passenger Boarding Bridge Replacement Design‐Build | 2023-12-01 | 2023-09-01 | Jesse Campbell | 2662723 | 1790000 | Anchorage Municipality | Jason Scheben | 2662668 |  | FAA | State House District 21 | Replace passenger boarding bridge at gate B9 | Gate B9 closure during removal and assembly of new PBB. Estimated closure is 60 days and will occur after September 2023 |  | Aviation |  |  | State Senate District K
25 | CFHWY00012 | Seward Highway: O'Malley Rd to Dimond Blvd Reconstruction | 2023-10-25 | 2023-07-23 | Jacob Gondek | 2690445 | 105000000 | Anchorage Municipality | Christina Huber | 2690572 | 537008 | STP | State House District 23 | Reconstruction of the Seward Highway from Dimond Blvd to O'Malley Road. Project will include widening the Highway to a full 3 lanes in each direction, adding a new underpass to connect Academy Drive on the east side of the Highway to Scooter Ave on the west side, frontage road improvements, and reconstruction of the O'Malley Road and Seward Highway Intersection. | There will likely be traffic detours throughout construction. | 17.2652 | Highway | http://www.sewardhighway.info/ |  | State Senate District L | The proposed improvements will improve safety throughout the corridor, improve east/west connectivity, add new bike and pedestrian routes and enhance existing connections, increase capacity of the O'Malley Road intersection, and increase the capacity of
26 | CFHWY00109 | Seward Hwy: MP 0-8 Pavement Preservation | 2023-10-01 | 2023-05-01 | Moore, Erika | 9072690450 | 15000000 | Kenai Peninsula Borough | Bentz, Christopher L | 9072690652 | 311034 | STP | State House District 29 | Resurface the Seward Highway from Mile points 0 - 8. The project will also include, as necessary, improvements to pedestrian curb ramps, guardrail, guardrail end treatments, dig-outs, drainage repair, sign replacement, replacement striping, and utility adjustments as needed. | Scheduled closures, detour routing, and lane closures | 17.5245 | Highway |  | 1020000X000 | State Senate District O | To extent the service life of the existing road facilities and enhance safety. Reduce maintenance cost and improve driver comfort.
27 | CFHWY00129 | TAKOTNA RIVER BRIDGE REPLACEMENT |  |  | Ron Searcy | 19072690656 |  | Yukon-Koyukuk Census Area | Steven Rzepka | 19072690592 | 1569 | STP | State House District 37 | This Project replaces the Takotna River Bridge (bridge #0463). Project includes bridge work, roadway resurfacing, roadside hardware, drainage improvements, and utilities. | Detour for the Takotna River Bridge is expected. | 0.61101 | Highway |  | 8241004X000 | State Senate District S | The purpose of the proposed project is to maintain connectivity along Sterling Landing/Takotna/Ophir Road. The purpose of the proposed project is to maintain connectivity along Sterling Landing/Takotna/Ophir Road.
28 | CFHWY00130 | STERLING SAFETY CORRIDOR IMPROVEMENTS MP 82.5 TO 94 DESIGN BUILD | 2025-09-01 | 2023-01-01 | TBD | 0 | 65000000 | Kenai Peninsula Borough | Kelly Summers | 9072690546 | 0A33026 | NHPP | State House District 30 | The Department issued an RFP for a federally funded Design-Build contract to provide the necessary engineering, labor, equipment, and materials to design, construct, and warranty a four lane divided highway from approximately Sterling Highway MP 82.5 to 94. The department’s solicitation is contingent on federal authority to proceed with construction. | This project will include delays, intermittent lane closures, and detours. Reasonable access will be maintained to public and private property in the area. | 26.1369 | Highway |  | 1000000X000 | State Senate District O | The proposed project will improve safety and reduce congestion within this existing safety corridor.
29 | CFHWY00132 | MINNESOTA DR: TUDOR TO 15TH AVE PAVEMENT PRESERVATION | 2023-09-23 | 2022-05-01 | Jason Lamoreaux | 19072690664 | 14036843.5 | Anchorage Municipality | Steven Rzepka | 19072690592 | 421099 | STP | State House District 18 | This federally funded contract is comprised of two projects. Project No. CFHWY00132 will resurface Minnesota Drive between Tudor Road to 15th Avenue. Project work includes guardrail, drainage, signalization, ADA curb ramp improvements, paving, signing and striping. | Expect lane closures and detours. | 15.47 | Highway |  | 2281216D00 | State Senate District I | The purpose of the project is to extend the service life of the roadway and reduce future maintenance costs.
30 | CFHWY00223/CFHWY00677 | A STREET, NORTHERN LIGHTS BOULEVARD to 40'" AVENUE PAVEMENT PRESERVATION & HSIP: A Street, Midtown Couplet Overhead Signal Indication U/G | 2023-09-01 | 2022-07-01 | Lorett Nabong | 9072690670 | 5048293.6 | Anchorage Municipality | Kevin Jackson | 9072690610 | 0527030/0001684 | STP | State House District 18 | This federally funded contract consists of two projects. Project CFHWY00223 will resurface A Street between Northern Lights Blvd and 40th Ave and project CFHWY00677 will make traffic signal indication upgrades. Project work includes utilities, pavement planing, temporary signal, paving, drainage, signing, and striping. | This project will include intermittent lane closures and potential delays. Reasonable access will be maintained to public and private property in the area. | 3.9792 | Highway |  | 2281101X000 | State Senate District I | The project will preserve the existing roadway structure with new pavement and minor associated repairs; in addition, the HSIP project will address identified issues to improve safety on this corridor.
31 | CFHWY00253 | Kenai Spur Highway Rehabilitation: Sport Lake Rd to Swires Rd - Phase II | 2023-10-25 | 2023-07-23 | Jacob Gondek | 9072690445 | 45000000 | Kenai Peninsula Borough | Alex Read, P.E. | 9072690641 | 221019 | NHPP | State House District 30 | Rehabilitate 5.7 miles of the Kenai Spur Highway between Soldotna and Kenai to increase capacity and improve safety from Sports Lake Road to Swires Road. Project will be constructed in two phases. This second phase will construct a 5-lane highway between Sports Lake Road and Eagle Rock Road, and install continuous lighting between Delta Avenue and Dolly Varden Street. | Normal construction impacts are anticipated. | 21.7943 | Highway | https://dot.alaska.gov/creg/kenaispur/ | 117600 | State Senate District O | The purpose of the project is to increase capacity and improve safety.
32 | CFHWY00281 | AMATS: Reeve Boulevard, 5" Avenue to Post Road Pavement Preservation | 2023-09-01 | 2022-05-01 | Lorett Nabong | 9072690670 | 2181636.65 | Anchorage Municipality | Galen Jones | 9072690550 | 535002 | AMATS | State House District 15 | This federally funded project will resurface Reeve Boulevard from 5th Avenue to Post Road. Project work includes drainage, paving, signal modification, curb ramps, signing, and striping. | This project will include intermittent lane closures and potential delays. Reasonable access will be maintained to public and private property in the area. | 4.1581 | Highway |  | 2281300X000 | State Senate District H | The project will preserve the existing roadway structure with new pavement and minor associated repairs.
33 | CFHWY00286 | DEARMOUN RD: E 140TH AVE - HILLSIDE DR PAVEMENT PRESERVATION | 2023-09-01 | 2023-05-01 | Lorett Nabong | 9072690670 | 3750000 | Anchorage Municipality | Jon Knowles | 9072690643 | 510007 | STP | State House District 28 | Pavement Preservation of DeArmoun Rd. from East 140th Avenue to Hillside Drive including improvements to drainage, intersections, ADA, roadside hardware, and utilities. High Friction Surface Treatment may be reapplied. | This project will include intermittent lane closures and potential delays. Reasonable access will be maintained to public and private property in the area. | 4.4745 | Highway |  | 2281077X000 | State Senate District N | The project will preserve the existing roadway structure with new pavement and minor associated repairs.
34 | CFHWY00359 | DOWLING ROAD and SEWARD HIGHWAY INTERCHANGE RECONSTRUCTION | 2023-09-01 | 2022-03-01 | Jake Gondek | 9072690445 | 33473036.53 | Anchorage Municipality | Kevin Jackson | 9072690610 | 0A31065 | NHPP | State House District 17 | This federally funded project will reconstruct the Dowling Road and Seward Highway interchange. Project work includes bridge replacement, grading, paving, drainage, retaining walls, signing, striping, and lighting. | This project will include delays, and intermittent lane closures, as well as long-term detours during bridge work. Reasonable access will be maintained to public and private property in the area. | 6.6088 | Highway |  | 1020000X000; 1020000D000; 2281323X000 | State Senate District I | The project will improve capacity at this interchange.
35 | CFHWY00366 | HSIP: Anchorage Pedestrian Lighting, Phase II | 2023-09-23 | 2022-05-01 | Jason Lamoreaux | 9072690664 | 1409958 | Anchorage Municipality | Chris Post | 9072697885 | 1607 | HSIP | State House District 18 | This HSIP funded project will increase visibility, reduce pedestrian/bicycle crashes, and ther traffic incidences by installing lighting. Work will include roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. This project will construct the second phase and includes work on Minnesota Drive. Project will be constructed in conjunction with the Minnesota Dr.: Tudor Rd to 15th Ave Pavement Preservation (CFHWY00132). | Project impacts may consist of lane closures to install new light poles and the removal of existing light poles. | 0.88299 | Highway |  | 2281216D000; 2281216I000 | State Senate District I | This project will increase the current lighting levels to make bicyclists and pedestrians more visible to drivers throughout the year.
36 | CFHWY00387 | AMATS: CHUGACH FOOTHILLS CONNECTOR, PHASE II | 2023-06-01 | 2022-05-01 | Ron Searcy | 9072690656 | 3548381 | Anchorage Municipality | Alex Read | 9072690641 | TA18004 | AMATS | State House District 27 | This federally funded project will construct a multi-use path along Tudor Road between Regal Mountain Drive and Campbell Airstrip Road. Project work includes grading, pathway, boardwalk and signing. | Limited impacts are expected for the travelling public. Pathway users may experience intermittent closures and detours. |  | Highway |  | N/A | State Senate District N | The project will improve pathway connectivity and pedestrian safety in the area.
37 | CFHWY00406 | MULDOON ROAD, DEBARR ROAD to EAST 36'" AVENUE, PAVEMENT PRESERVATION | 2023-09-01 | 2022-05-01 | Jason Lamoreaux | 9072690664 | 4821338 | Anchorage Municipality | Sean Baski | 9072690566 | 54402 | STP | State House District 15 | This is a preventative maintenance project for resurfacing Muldoon Road from Debarr Road to East 36th Avenue. This project includes resurfacing, roadside hardware, drainage improvements, intersection improvements, and ADA improvements as necessary. | This project will include intermittent lane closures and potential delays. Reasonable access will be maintained to public and private property in the area. | 8.0282 | Highway |  | 2281205X000 | State Senate District H | The project will preserve the existing roadway structure with new pavement and minor associated repairs.
38 | CFHWY00428 | MCHUGH RWIS TOWER UPGRADE | 2023-09-01 | 2023-05-01 | TBD | 0 | 375000 | Anchorage Municipality | John Turley | 9072662171 | 0106(094) | STP | State House District 28 | This project will demolish the existing McHugh RWIS Tower and its power supply which are located in ARCC ROW near Seward Highway MP 111.8, and install a new tower in DOT ROW near the existing tower location. Power will be routed from an existing CEA pole to the new tower. | Little to no impacts are anticipated for the traveling public. RWIS data from this location will be unavailable during construction. | 0.0093272 | Highway |  | 1020000X000 | State Senate District N | The project will relocate the RWIS tower and power source from ARRC ROW to DOT ROW.
39 | CFHWY00431, CFHWY00432 and CFHWY00006 | Glenn Hwy: Parks Hwy to S. Inner Springer Lp. (Phase II) | 2024-11-01 | 2023-06-01 | Ericka Moore | 9072694550 | 25000000 | Matanuska-Susitna Borough | Sean Baski | 9072690566 | 0A15037, 0A15038 and 0A15033 | NHPP | State House District 12 | This project will reconstruct the Glenn Highway from the Parks Highway to S. Inner Springer Loop as a four-lane divided highway. Project work will add lanes, widen shoulders, add turn lanes and frontage roads, signals, illumination, other traffic safety related improvements. It will also construct improvements to South Colleen Street intersection, and improve connectivity and access. It will also construct a pathway along the Glenn Highway and other roads. | This project will include intermittent closures and detours. Reasonable access will be maintained to public and private property in the area. | 39.7569 | Highway | http://www.brooks-alaska.com/glennhighway/ | 1060000I000 | State Senate District F | To address safety and capacity issues in the corridor.
40 | CFHWY00490 | COHOE LOOP ROAD MP 0-9.7 PAVEMENT PRESERVATION |  |  | Jacob Gondek | 19072690445 |  | Kenai Peninsula Borough | Steven Rzepka | 19072690592 | 1645 | STP | State House District 31 | Pavement preservation, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. | Lane closures expected. | 19.4556 | Highway |  | 2141017X000 | State Senate District P | The purpose of the project is to extend the service life of the roadway and reduce future maintenance costs.
41 | CFHWY00493 | FUNNY RIVER RD PAVEMENT PRESERVATION |  |  | Jacob Gondek | 19072690445 |  | Kenai Peninsula Borough | Steven Rzepka | 19072690592 | 485002 | STP | State House District 31 | Pavement preservation, bridge work, roadside hardware, drainage improvements, intersection improvements, ADA improvements and utilities. | Expect lane closures. | 17.5644 | Highway |  | 2161017X000 | State Senate District O | The purpose of the project is to extend the service life of the roadway and reduce future maintenance costs.
42 | CFHWY00551 | Anchorage Area Drainage Improvements FY2019 | 2023-10-01 | 2023-03-01 | Lorett Nabong, P.E. | 9072690670 | 2500000 | Anchorage Municipality | Galen Jones, P.E. | 9072690550 | 1651 | STP | State House District 28 | Project involves the design and construction of drainage infrastructure and erosion mitigation within the Anchorage area. Infrastructure including culverts, drainage basins, storm drain systems, ditches, swales, bridge embankments and abutments, side slopes, erosion protection features (such as dikes and rip rap), and other appertinent drainage and erosion protection infrastructure will be repaired, replaced, or improved as necessary. Roadways, pathways, sidewalks, and roadside appurtenances affected by drainage improvements are included. | Full road closures are not anticipated for this project. Temporary lane closures may occur. | 0.99051 | Highway |  | 1020000X000, 2281321X000 | State Senate District N | To eliminate threats to the State's transportation system within the Anchorage area.
43 | CFHWY00564 | HSIP: CR Guardrail Inventory and Upgrade | 2023-11-23 | 2023-05-23 | Jason Lamoreaux | 9072690664 | 7500000 | Anchorage Municipality | Chris Bentz | 9072690652 | 1665 | HSIP | State House District 28 | This project will replace guardrail and end terminals on 50mph and above roadways within the Anchorage area of Central Region as necessary to meet current standards. | Mo major impacts to traffic are anticipated. No full closures are anticipated. Impacts to traffic are possible, with major highways being limited for impacts to off peak hour times. |  | Highway | https://dot.alaska.gov/creg/guardrail/ | 1020000X000, 1021005X000, 2281235X000, 2361000X000, 1060000D000, 1060000I000, 2281321X000 | State Senate District N | To increase roadside safety by correcting deficiencies in guardrail throughout various routes by constructing improvements to bring them into conformance with current standards.
44 | CFHWY00568 | AMATS: Hiland RD MP 0-3.2 Pavement Preservation | 2023-10-01 | 2023-06-01 | Jason Lamoreaux | 9072690664 | 2500000 | Anchorage Municipality | Galen Jones, P.E. | 9072690550 | 1663 | AMATS | State House District 14 | Resurface Hiland Road, including milling, paving, minor subgrade rehabilitation, drainage improvements, updating guardrail and signposts to meet current safety standards, replacing striping and select signage, curb and gutter, lighting, and roadside signal and /or traffic data hardware. | Temporary lane closures are anticipated during construction operations. | 6.4389 | Highway |  | 2301050X000 | State Senate District G | To extend the useful life of the roadway.
45 | CFHWY00594 | Glenn/Parks Interchange Repairs - Nov 2018 EQ PR | 2023-10-23 | 2023-09-21 | Ericka Moore | 9072694550 | 2694800 | Anchorage Municipality | Julia Hanson | 9072690753 | 91011 | Emergency Relief | State House District 12 | Work includes permanent repairs at Glenn Hwy/Old Glenn Hwy interchange near MP 29.5, Glenn Hwy/Parks Hwy interchange flyover near MP 34.5, Glenn Hwy MP 36, and E Fireweed Rd along Loberg Lake. Work includes embankment and structural section reconstruction, grading, paving, guardrail, and striping. | Drivers should be alert to DETOUR signs and posted speed limits within the project area. | 3.8859 | Highway | www.ak2018earthquake.com | multiple | State Senate District F | This project will repair damage from the November 30, 2018 earthquake at several locations around the Glenn Hwy/Parks Hwy interchange.
46 | CFHWY00599 | KNIK GOOSE BAY ROAD, FAIRVIEW LOOP to PALMER-WASILLA HIGHWAY, PHASE I | 2024-09-01 | 2022-06-01 | Ericka Moore | 9072694550 | 54553989 | Matanuska-Susitna Borough | Tom Schmid | 9072690543 | 525019 | STP | State House District 8 | This federally funded project will reconstruct Knik Goose Bay Road to a divided 4 lane facility from to Fairview Loop to Centaur Ave. Project work includes drainage improvements, intersection improvements, ADA improvements, grading, paving, pathways, utilities, illumination, and signalization. | This project will include delays, intermittent lane closures, and potential detours. Reasonable access will be maintained to public and private property in the area. | 13.2682 | Highway | https://dot.alaska.gov/creg/kgb_cv/ | 2381037X000 | State Senate District F | This project will add capacity and correct problems created by uncontrolled access, thereby improving safety and reducing congestion for roadway users.
47 | CFHWY00603 | AMATS: POTTER MARCH IMPROVEMENTS | 2023-09-23 | 2023-05-23 | LORETT NABONG | 9072690670 | 375000 | Anchorage Municipality | SEAN BASKI | 9072690566 | TA18008 | AMATS | State House District 28 | This Project expands the parking area, improves drainage, and pedestrian facilities at the Potter Marsh South parking facility, located at the intersection of Potter Valley Road and Old Seward Highway. | Project Area will be closed for Construction. Mail boxes will be relocated during Construction for safe access. | 0.27683 | Highway |  | 2281318X000 & 2281051X000 | State Senate District N | Improve safety due to the existing parking area having insufficient capacity resulting in vehicle overflow and parking out onto Old Seward Highway and Potter Valley Road during peak use.
48 | CFHWY00610 | ANCHORAGE DISTRICT, GROUP B - NOV 2018 EQ PR | 2023-07-23 | 2022-05-01 | Lorett Nabong | 19072690670 | 2682469 | Anchorage Municipality | Steven Rzepka | 19072690592 | 91019 | Emergency Relief | State House District 28 | This project will design and construct repairs for the November 30, 2018 earthquake in the Central Region of Alaska. Repairs may include, but are not limited to, asphalt, embankment, roadside hardware, retaining walls, utilizes, and drainage. | Expect lane closures. | 17.8285 | Highway |  | Varies | State Senate District N | This project will make permanent repairs to locations damaged by the November 30, 2018 earthquake.
49 | CFHWY00648 | MAT-SU BOROUGH ROAD REPAIRS - NOV 2018 EQ PERM REPAIRS (MSB) |  |  | Ericka Moore | 19072694550 |  | Matanuska-Susitna Borough | Steven Rzepka | 19072690592 | 92010 | Emergency Relief | State House District 8 | This federally funded project will perform permanent repairs to damage from the November 30, 2018 earthquake in the Matanuska-Susitna Borough on Point MacKenzie Road, Vine Road, and South Settlers Bay Drive. Project work includes grading, drainage, paving, guardrail, and drainage. | Expect lane closures. A road closure and detour for the Vine Road location is likely. | 15.2752 | Highway |  | Varies | State Senate District D | This project will construct permanent repairs to locations damaged during the November 30, 2018 earthquake.
50 | CFHWY00833 | HSIP: Anchorage Pedestrian Lighting, Phase I | 2023-09-23 | 2022-05-01 | Ron Searcy | 9072690656 | 2590436 | Anchorage Municipality | Chris Post | 9072697885 | 1725 | HSIP | State House District 18 | This HSIP funded project will increase visibility, reduce pedestrian/bicycle crashes, and other traffic incidences by installing lighting. Work will include roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. This project will construct the first phase and includes work on Tudor Road, Seward Highway and Muldoon Road. | Project impacts include potential lane closures for the installation of new light poles and the removal of existing light poles. |  | Highway |  |  | State Senate District I | This project will increase the current lighting levels to make bicyclists and pedestrians more visible to drivers throughout the year along the three selected roadway segments.
51 | CFHWY00883 | HSIP: Church Rd and Spruce Ave Intersection Flashing Beacon | 2023-10-01 | 2023-08-01 | Ericka Moore, P.E. | 9072690450 | 2500000 | Matanuska-Susitna Borough | Cynthia Ferguson, P.E. | 9072690693 | 1727 | HSIP | State House District 10 | This project proposes to install an overhead flashing beacon at the intersection of Church Road and Spruce Avenue. The proposed work may include the following: • Installation of an overhead flashing beacon • Minor pavement work • Drainage improvements (ditches, culverts) • Upgrade signage and striping • Pedestrian facility improvements • Utility relocations | Road users may experience delays during project construction. However, traffic impacts would be mitigated by providing advance notice to the public and through implementation of a traffic control plan. Construction may also be scheduled at off-peak hours | 0.99986 | Highway |  | 2381032X000 and 2381013X00 | State Senate District D | The purpose of this proposed Highway Safety Improvement Program (HSIP) project is to increase drivers’ awareness of the intersection and the stop condition on Spruce Avenue. The proposed improvement aims to reduce the angle crashes from vehicles on Sp
52 | CFHWY00895 | Sterling Highway MP 45-60; Sunrise to Skliak Lake Rd Stages 3 & 4 Early Work Package - Grading (Temporary Profile), Drainage, and Structures | 2024-10-01 | 2023-03-01 | Jonathan Tymick | 9072690543 | 105000000 | Kenai Peninsula Borough |  |  |  | FHWA | State House District 29 |  | Stage 3&4 work: Minimal traffic impacts for project work. Large equipment will be accessing at Juneau Creek Rd (Sterling Hwy MP 53) and Bean Creek Rd (Sterling Hwy MP 47.5). Access to hiking trails will be maintained. | 0.31159 | Highway |  |  | State Senate District O
53 | CFHWY00895 | Sterling Hwy MP 45-60: Stage 1A (MP 56-58) | 2024-10-01 | 2023-03-01 | Jonathan Tymick | 9072690543 | 105000000 | Kenai Peninsula Borough |  |  |  | FHWA | State House District 29 |  | Stage 3&4 work: Minimal traffic impacts for project work. Large equipment will be accessing at Juneau Creek Rd (Sterling Hwy MP 53) and Bean Creek Rd (Sterling Hwy MP 47.5). Access to hiking trails will be maintained. | 0.31159 | Highway |  |  | State Senate District O
54 | CFHWY00938 | HSIP: CR Guardrail Inventory and Upgrade (South) | 2023-11-23 | 2023-05-23 | Jason Lamoreaux | 9072690664 | 15000000 | Kenai Peninsula Borough | Chris Bentz | 9072690652 | 1745 | HSIP | State House District 31 | This project will replace guardrail and end terminals on 50mph and above roadways within the Kenai Peninsula area of Central Region as necessary to meet current standards. | No major impacts to traffic are anticipated. No full closures are anticipated. Impacts to major roadways will be limited to off peak traffic hours. |  | Highway | https://dot.alaska.gov/creg/guardrail/ | 1000000X000, 1020000X000, 2121017X000, 2141077X000, 2141074X000, 2221006X000, 2181049X000, 2141069X000 | State Senate District O | To increase roadside safety by correcting deficiencies in guardrail throughout various routes on the Kenia Peninsula and constructing improvements to bring them into conformance with current standards.
55 | CFHWY00939 | HSIP: CR Guardrail Inventory and Upgrade (North) | 2023-11-23 | 2023-05-23 | Jason Lamoreaux | 9072690664 | 15000000 | Matanuska-Susitna Borough | Chris Bentz | 9072690652 | 1746 | HSIP | State House District 8 | This project will replace guardrail and end terminals on 50mph and above roadways within the Mat-Su area of Central Region as necessary to meet current standards. | No major impacts to traffic are anticipated. No full closures are anticipated. Impacts to major roadways will be limited to off peak traffic hours. |  | Highway | https://dot.alaska.gov/creg/guardrail/ | 2401007X000, 2361071X000, 2421008X000, 2381073X000, 1140000I000, 2381089X000, 2361053X000, 2381037X000, 1060000I000, 2381026X000, 2381095X000, 1060000D000 | State Senate District F | To increase roadside safety by correcting deficiencies in guardrail throughout various routes in the Mat-Su and constructing improvements to bring them into conformance with current standards.
56 | CFHWY00946 | KENAI PENINSULA BRIDGE DECK REHABILITATIONS FY2023 | 2024-06-01 | 2023-04-01 | TBD | 0 | 3750000 | Kenai Peninsula Borough | Galen Jones | 9072690550 | 0A33033 | NHPP | State House District 29 | This project includes bridge deck polyester concrete overlays, structural retrofits, miscellaneous structural repairs, expansion joints, bridge rail upgrades, guardrail and end terminals, paving, signing, and striping. | This project will include delays, intermittent lane closures, and potential detours. | 2.1309 | Highway |  | 1000000X000 | State Senate District O | This project proposes to make preservation-related improvements to bridges within Kenai Peninsula Borough to reduce future maintenance and extend their serviceable lifespan.
57 | CSAPT00754 | ANC RON 3 and 4 Rehabilitation | [5 empty] | Anchorage Municipality |  |  |  |  | State House District 21 | [6 empty] | State Senate District K
58 | NFAPT00254 | Kaltag Airport Improvements | 2023-08-01 | 2023-04-01 | Charlie Bohart | 9074515367 | 10686279 | Yukon-Koyukuk Census Area | R&M Consultant | 9074515367 |  | FAA | State House District 39 | Resurface the runway, taxiway, apron, and access road and apply dust palliative to operation surfaces. Remove airport obstructions and rehabilitate. Replace SREB, segmented circle, and airport lighting and electrical components. | Airport will experience regular night closures for the duration of project, likely late May – mid June for final shaping and installation of dust palliative. RW will be made ready for medevacs with 30‐ minute notice. |  | Aviation |  |  | State Senate District T
59 | NFAPT00370 | Shishmaref Airport Erosion Control | 2023-10-31 | 2023-06-01 | Michael Freytag | 9074433413 | 9000000 | Nome Census Area | Jonathan Hutchnson | 9074515479 |  | FAA | State House District 39 | • Installation, removal, and maintenance of hazard marking and signing on the landfill road. • Utilities – No utility work is anticipated. • Stake work limits • Delineate and improve haul route(s), access route(s), staging area(s), and stockpile area(s). • Sequenced removal, salvage and disposal of existing erosion control structures. • Sequential excavation, grading, and construction of new revetment structure and improvements to existing road • Seeding, restoration, and clean-up. | No major impacts and will have detour for the access road. |  | Aviation |  |  | State Senate District T | The primary objective of the Shishmaref Airport Erosion Control project is to reconstruct portions of the landfill access road and construct a new rock revetment.
60 | NFAPT00371 | Marshall Airport Improvements | 2023-10-24 | 2023-08-23 | Charles Bohart, P.E. | 9074515367 | 15000000 | Kusilvak Census Area | Chris Johnston, P.E. | 9074512322 | 3-02-0363-___-____ | FAA | State House District 38 | Rehabilitate the runway, taxiway, apron, airport access road, and the snow removal equipment building, replace airport lighting and segmented circle, and apply dust palliative. | Nightly runway closures and a few full-day closures during active construction. The airport will reopen for medevacs. |  | Aviation |  |  | State Senate District S | The Marshall Airport lighting system and snow removal equipment building are beyond their useful life and requiring increasing levels of maintenance. The airport embankments have minimal surfacing remaining and have significant shoulder cracking and sett
61 | NFAPT00500 | Brevig Mission Lighting and Resurfacing | 2023-10-31 | 2022-08-01 |  | 0 | 10000000 | Nome Census Area | Jonathan Hutchinson, P.E. | 9074515479 |  | FAA | State House District 39 | Resurface the runway, taxiway, and apron and replace airfield lighting. Stabilize runway shoulders and sideslopes. | Both runways will be subject to nighttime closures. One runway at a time will also be subject to temporary daytime closures while the other runway is under active construction. Half width taxiway operations will be required periodically. |  | Aviation |  |  | State Senate District T | The runway surface course and lighting are beyond their service life and are in need of rehabilitation. Runway shoulders are experiencing settlement and cracking and need to be stabilized.
62 | NFAPT00689 | FIA GA Apron & Taxiway Reconstruction | 2023-09-30 | 2023-06-01 | Brian Herning, P.E. | 9074513018 | 15000000 | Fairbanks North Star Borough | Richard Stumpf, P.E. | 9074742587 | 3-02-0096-XX-XXXX | FAA | State House District 5 | Reconstruct the general aviation apron and associated taxiways, replace taxiway lighting and other improvements. | Temporary relocation of aircraft tie downs. |  | Aviation |  |  | State Senate District C | Pavement and lighting has outlived it's useful life.
63 | NFHWY00097 | HSIP: Richardson Highway MP351 Interchange | 2023-09-25 | 2023-09-23 |  | 0 | 22500000 | Fairbanks North Star Borough | David Fischer, P.E. | 9074515357 | 0A424(034) | HSIP | State House District 5 | Reconstruct the Old Richardson Highway and Richardson Highway intersection at MP 351 of the Richardson Highway. Work will include intersection improvements, bridge work, roadside hardware, drainage improvements, and utilities. Additional work includes construction of new frontage roads and reconstruction of a portion of Keeney Road. | Partial closures, diversions and single lane traffic on the Richardson highway are all expected during construction. | 6.9698 | Highway |  | 1100000 | State Senate District C | This project will help create safer turning movements by constructing a 4 lane overpass at the 12 Mile Village intersection of the Old Rich and Richardson Highways.
64 | NFHWY00124 | Aurora Drive Noyes Slough Bridge #0209 Replacement | 2023-10-01 | 2023-02-01 | Guan Griffin, P.E. | 9074515087 | 5000000 | Fairbanks North Star Borough | Lauren Little, P.E. | 9073785911 | 629001 | STP | State House District 1 | Replace the Noyes Slough Bridge #209 on Aurora Drive in Fairbanks, AK. | Aurora Drive will be fully closed from approximately February 2023 - October 2023. | 0.65102 | Highway |  | 2581007X000 | State Senate District A | The existing bridge is structurally deficient and in need of replacement. In addition the project will add ADA compliant sidewalks to the bridge and within the project limits.
65 | NFHWY00133 | Richardson Highway MP 35-40 Resurfacing | 2023-10-23 | 2023-04-23 | Sarah Schlichting, P.E. | 9074512041 | 12500000 | Chugach Census Area | Russ Johnson, P.E. | 9074515059 | 711074 | STP | State House District 9 | This project will resurface the Richardson Highway between mileposts 35 and 40. Additional work includes repairing/replacing culverts, ditch and drainage improvements, stabilizing retaining walls, replacing signs, and bridge work. | Traffic delay during construction | 20.335 | Highway |  | 190000 | State Senate District E | This project is being constructed to extend the service life of the facility and improve safety. The pavement along the Richardson Highway in this section has reached the end of its useful life and preserving the pavement structure is needed to prevent f
66 | NFHWY00245 | Airport Way/Steese Expwy Intersection | 2023-08-23 | 2023-05-23 |  |  | 22500000 | Fairbanks North Star Borough | Carl Heim |  |  | FHWA | State House District 2 | Rebuild the intersection with a Continuous Flow Intersection/Median U-turn Intersection (CFI-MUT). | There will be delays up to 20 minutes at the intersection all summer. This project will be constructed with the Steese Expressway/Chena River Bridge Redeck project and the Steese Expressway Interconnect project. In 2022, a 60-day closure is being conside | 5.3036 | Highway |  |  | State Senate District A
67 | NFHWY00265 | Richardson Highway MP 128-138 Rehabilitation | 2023-10-23 | 2023-04-23 | Sarah Schlichting, P.E. | 9074512041 | 22500000 | Copper River Census Area | Russ Johnson, P.E. | 9074515059 | 173016 | STP | State House District 6 | Rehabilitate the Richardson Highway between MP 128-138. Improvements include re-paving the road, embankment slope flattening, ditching, replacing failing/undersized culverts, and continued work on a realignment at MP 134 where the highway is being shifted to the east, away from the eroding Gulkana River bluff. | Traffic delay during construction | 34.3057 | Highway |  | 190000 | State Senate District C | The project is being constructed to extend the service life of the facility and improve safety. The existing roadway has experienced uneven settling and heaving which has deteriorated the pavement structure and damaged culverts.
68 | NFHWY00269 | North Pole Street Lighting Standardization and Improvements | 2023-09-01 | 2023-05-01 | Kyungyun Chi | 9073743709 | 2500000 | Fairbanks North Star Borough | Ethan Graetz | 9074512281 | 2403 | FAST | State House District 5 | The Alaska Department of Transportation and Public Facilities (DOT&PF), in cooperation with the Alaska Division of the Federal Highway Administration, is proposing to install new street lighting in the Morning Star, Ford, and Highway Park subdivisions with additional lighting in the city core. The new streetlights are LED’s. Construction is anticipated to start summer 2022. | Traffic impacts around City of North Pole City Core subdivisions. Edge of road work, partial lane closures. |  | Highway | https://dot.alaska.gov/nreg/northpolelights/ |  | State Senate District C | The City of North Pole and DOT&PF’s purpose is to improve safety in these subdivisions. The subdivisions have areas of lighting that are not uniformly placed or non-existent. Many lights are unmetered with no service disconnects. The project will repla
69 | NFHWY00278 | Richardson Highway MP 233 Bear Creek Bridge #0593 Replacement | 2023-10-24 | 2023-05-23 | Sarah Schlichting, P.E. | 9074512041 | 25000000 | Southeast Fairbanks Census Area | Jennifer Wright, P.E. | 9073718949 | 714024 | Emergency Relief | State House District 9 | The project proposes to reconstruct the Richardson Highway between Milepost 232 - 234.5 and replace Bear Creek Bridge #0593. This will also include drainage improvements, roadside hardware, and utilities. | Construction of this project is expected to take 2 years. There will be a detour and temporary crossing at Bear Creek to facilitate the removal of the old bridge and construction of the new bridge. | 8.815 | Highway | https://rich-bear-creek-bridge-akdot.hub.arcgis.com/ | 1100000 | State Senate District E | The purpose of this project is to replace Bear Creek Bridge #0593, which has structural deficiencies; and to enhance safety an reduce maintenance costs by bringing the existing roadway geometry to current design standards.
70 | NFHWY00289 | Chena Hot Springs Road MP 0-6 | 2023-06-23 | 2023-05-23 |  |  | 22500000 | Fairbanks North Star Borough | Caroline Maniaci |  |  | FHWA | State House District 6 | Possible repair of temporary pavement, paving the last mile of the project, striping, and auger-boring one 36” culvert. | Expect flaggers and delays up to 20 minutes during paving and striping. | 21.42 | Highway |  |  | State Senate District C
71 | NFHWY00418 | Kotzebue to Cape Blossom Road - Stage I | 2023-10-22 | 2023-11-21 | Charles Bohart, P,E. | 90745135367 | 30000000 | Northwest Arctic Borough | Jonathan Hutchinson, P.E. | 907.4515479 | 2469 | CTP | State House District 40 | Construct the first stage of the Cape Blossom Road from Ted Steven's Way to Sadie Creek. Project work will include new road construction, drainage improvements, roadside hardware, and utilities. | No major impacts |  | Facilities | https://dot.alaska.gov/nreg/capeblossomroad/ | new road | State Senate District T | This is the first stage of a new road to a barge landing at Cape Blossom, which will help reduce barging costs to the community of Kotzebue.
72 | NFHWY00445 | Fairbanks 5th Avenue Reconstruction | 2023-10-23 | 2023-05-23 | David Arvey | 9074512621 | 3750000 | Fairbanks North Star Borough | Ivet Hall | 9074515386 | TA19(001) | FAST | State House District 1 | Reconstruct 5th Avenue between Barnette Street and Noble Street including ADA improvements, drainage improvements and utilities. | The 5th Avenue will be closed during construction (summer 2023), the intersections of the 5th Avenue with crossing streets will be impacted as needed. Pedestrians are anticipated to use detours as well. | 1.3824 | Highway | https://dot.alaska.gov/nreg/5th-ave/ | 2581155X000 | State Senate District A | The roadway surface is deteriorated and the pedestrian facilities do not meet ADA compliance.
73 | NFHWY00516 | NR Guardrail Upgrades (Tok Cutoff, Glenn Hwy, Richardson Hwy) | 2023-08-23 | 2023-05-23 |  |  | 7500000 | Southeast Fairbanks Census Area | Ivet Hall |  |  | FHWA | State House District 9 | Replace selected sections of guardrail along Tok Cutoff, Glenn Highway (NR section) and Richardson Highway (primarily between Delta and Paxson and potentially near Valdez) | Expect impacts to vehicular traffic, with shoulder work and possible delays up to 20 minutes. | 0 | Highway |  |  | State Senate District E
74 | NFHWY00580 | Healy Spur Road Rehabilitation | 2023-09-01 | 2023-04-01 | Sarah Schlichting | 9074512041 | 1500000 | Denali Borough | Jennifer Wright | 9073718949 | 638005 | CTP | State House District 6 | Rehabilitate Healy Spur Road in Healy. Project will include widening shoulders and drainage improvements. | There may be traffic impacts such as delays, flagging, pilot cars, etc | 2.6127 | Highway | https://healy-spur-road-rehabilitation-akdot.hub.arcgis.com/ | 173500 | State Senate District C | This project will provide improvements such as rehabilitation of the roadway, widening the roadway to add shoulder width, and improved drainage where necessary.
75 | NFHWY00587 | Edgerton Highway MP24-29 Resurfacing | 2023-09-01 | 2023-07-01 | Brian Herning | 9074513018 | 3500000 | Copper River Census Area | John Netardus | 9074515448 | 850030 | STP | State House District 6 | The Alaska Department of Transportation and Public Facilities (DOT&PF), in cooperation with the Federal Highway Administration (FHWA) is proposing to resurface the Edgerton Highway between MP 24 and MP 29. The purpose of this Preventive Maintenance project is to improve safety and extend the highway service life. This project is located on the Edgerton Highway between MP 24.4 and MP 28.8. The Edgerton Highway begins at MP 83 of the Richardson Highway and continues to MP 35 at Chitina, Alaska where the road becomes locally known as the McCarthy Road, then ending at MP 92 in McCarthy. The Edgerton Highway is classified as a major collector and is a sole access route connecting McCarthy and Chitina to the rest of Alaska. The Edgerton Highway was surfaced with an asphalt surface treatment (AST) in 1986, the AST remains between MP 24 and MP 29 and has reached the end of its useful life. | No major impacts expected. One lane road closures with flagger operations expected during resurfacing and culvert replacement. | 10.0341 | Highway |  | 198000 | State Senate District C | The existing pavement within the MP 24-29 has areas of localized settlement that requires a high frequency of patching by DOT&PF’s maintenance forces. This project will mill, regrade, and repave the roadway to alleviate DOT&PF’s maintenance. In addit
76 | NFHWY00589 | Alaska Hwy MP 1222-1227 Resurfacing | [5 empty] | Southeast Fairbanks Census Area | Ivet Hall |  |  | FHWA | State House District 6 | Resurface approximately 4.5 miles of Alaska Highway near the Canadian border. This project will be constructed with the Alaska Highway MP 1235-1251 Rehabilitation project. | Expect delays up to 20 minutes | 10.4174 | Highway |  |  | State Senate District C
77 | NFHWY00591 | Northern Region ADA Improvements - Fairbanks: College Road | 2023-09-23 | 2023-05-23 | David Arvey | 9074512621 | 1536063 | Fairbanks North Star Borough | Ivet Hall | 9074515386 | pending | STP | State House District 2 | DOT&PF, in cooperation with the Federal Highway Administration (FHWA), will replace/widen selected sidewalks on College Road between Margaret/Antoinette Avenues intersection and Steese Highway. This project includes regrading of driveways as needed and some associated curb and gutter work as well. Curb ramps within this section of College Road will be replaced under the East College Road Resurfacing project which will be constructed concurrent with this project. | Night and day work, vehicular lane restrictions, pedestrian detours. Most vehicular restrictions will be between 8PM to 7AM. | 4.5718 | Highway |  | 2581128 | State Senate District A | Following the Northern Region ADA Reconnaissance of all Department-maintained curb ramps, this was one of three locations that were nominated to address ADA deficiencies.
78 | NFHWY00624 | Alaska Hwy MP 1235-1251 Rehabilitation | [5 empty] | Southeast Fairbanks Census Area | Dave Fischer |  |  | FHWA | State House District 6 | Rehabilitate the Alaska Highway between milepost 1235-1252 and construct new passing lanes. | For the 2022 season anticipate deep pipe replacements and delays up to 20 minutes. | 31.5288 | Highway |  |  | State Senate District C
79 | NFHWY00627 | Fairbanks Area PM 2.5 Motor Vehicle Plug-Ins | 2023-09-01 | 2023-05-01 | Guan Griffin | 9074515087 | 2500000 | Fairbanks North Star Borough | Ethan Graetz | 9074512281 | 2480 | NHPP | State House District 5 | The Alaska Department of Transportation and Public Facilities (DOT&PF), in cooperation with the Alaska Division of the Federal Highway Administration, is installing electrical motor vehicle plug-in outlets at public parking lots located within the Fairbanks North Star Borough at Birch Hill Recreation Area, Tanana Lakes Recreation Area, Chena Lake Recreation Area, and UAF U-Park. Construction on this project is expected to begin in fall 2022 and be complete in 2023 | No roadway impacts. Local parking impacts at the Chena Lakes, Birch Hill, and UAF U-Park building facilities. |  | Highway | https://dot.alaska.gov/nreg/plug-ins/ | N/A | State Senate District C | The Fairbanks Metropolitan Area does not meet the National Ambient Air Quality Standards for particulate matter 2.5 microns and smaller (PM2.5) as required by the Clean Air Act, thus is designated as a non-attainment area. Congestion Mitigation and Air Q
80 | NFHWY00633 | FAST Area Surface Upgrades FFY2023 | 2023-09-01 | 2023-06-01 |  | 0 | 2200000 | Fairbanks North Star Borough | John Netardus | 9074515448 |  | FAST | State House District 5 | Repave 9 roads in the Aztec Road Service Area in North Pole. Pave 3 gravel roads in the Aztec Road Service Area. Install a crosswalk with flashing beacon on College Road at Caribou Way. Pave the entrance and parking pad at the 2nd Avenue Dog Park. Replace damaged bike/ped path at 2nd Ave Dog Park. | The dog park will be closed briefly. Roads being replaced will experience short-term closure. | 39.3653 | Highway |  | NA | State Senate District C | The condition of roads and dog park in the project areas is poor. There is no nearby crossing on College Road.
81 | NFHWY00643 | University Avenue Segment 2: Airport Way to Mithcell Expressway | 2023-10-01 | 2023-05-01 | Brian Herning, P.E. | 9074513018 | 10000000 | Fairbanks North Star Borough | Lauren Little, P.E. | 9073785911 | 617016 | NHPP | State House District 5 | Reconstruct and widen University Avenue from Holden Road to the Mitchell Expressway including continuous sidewalks, raised median, and drainage improvements. This project was substantially constructed in CY22. | Lane restrictions during landscaping activities. | 2.037 | Highway | https://dot.alaska.gov/nreg/university/ | 2581185X000, 2581021X000, 2582181X000 | State Senate District C | To improve safety, reduce maintenance and provide a continuous bicycle/pedestrian connection along University Avenue.
82 | NFHWY00645 | East College Road Resurfacing | 2023-10-23 | 2023-04-23 | Dave Arvey, P.E. | 9074512621 | 7500000 | Fairbanks North Star Borough | Russ Johnson, P.E. | 9074515059 | 640013 | STP | State House District 2 | Repave College Road between the Margaret/Antoinette and Old Steese Highway intersections and the College Rd/Johansen Expressway Interchange on and off ramps. Additional work includes replacing damaged curb and gutter, replacing non-compliant ADA ramps, drainage improvements, replacing signs, resurfacing, re-striping, and upgrading the railroad crossing. | Traffic delays during construction | 15.5561 | Highway |  | 2581128X000 | State Senate District A | The project is being constructed to improve safety, extend the useful life of the facility and upgrade existing curb ramps and sidewalks to meet current ADA standards. The paved driving surface is deteriorating and needs to be replaced.
83 | NFHWY00694 | Richardson Hwy MP 40-51 Resurfacing | 2023-08-23 | 2023-04-23 |  |  | 14000000 | Copper River Census Area | Colleen Ackiss |  |  | FHWA | State House District 9 | Resurface 11 miles of roadway, including replacement of multiple culverts, minor bridge work including new membranes and bridge railing, replacement of all guardrail, replacement of four retaining walls, and new signing and striping. | During much of the project work, traffic will be reduced to one lane. Expect delays of 20 minutes. Traffic speeds will be reduced to 10 mph across bridges when the new membranes are installed. | 22.1235 | Highway |  |  | State Senate District E
84 | NFHWY00707 | Northern Region Dynamic Messaging SIgns - Targeted Airshed Grant | 2023-09-01 | 2023-05-01 | Guan Griffin | 9074515057 | 2500000 | Fairbanks North Star Borough | Ethan Graetz | 9074512281 | 2518 | RSA | State House District 5 | Install and operate digital message signs on the Parks Highway MP 357 and Richardson Highway MP 359. | Shoulder and median construction. Potential for single lane closures. | 0 | Highway | https://dot.alaska.gov/nreg/tag-dms/ |  | State Senate District C | Install and operate highway signs to facilitate immediate communication of air quality alerts with the goal of increasing curtailment compliance. Fairbanks has been designated a Serious Nonattainment area for fine particulate matter (PM2.5) by the Enviro
85 | NRMBS00410 | Burma Pit Road Little Tonsina Bridge (Richardson Highway MP 74.2) | 2023-07-23 | 2023-07-22 |  |  | 1750000 | Copper River Census Area | Dave Arvey |  |  | FHWA | State House District 9 | Replace existing culverts with a bridge over the Little Tonsina River on the Burma Pit Road near MP 74.2 Richardson Highway. | Existing access to be maintained throughout construction. | 0.32912 | Highway |  |  | State Senate District E
86 | NSHWY00657 | Nenana-Totchaket Road, Phase 1 | 2023-09-01 | 2023-03-01 | Scott Woster, Brian Herning | 0 | 5750000 | Yukon-Koyukuk Census Area | Jonathan Hutchinson, P.E., | 9074515479 |  | GF | State House District 6 | Rehabilitate the existing 12 mile Totchaket Road and perform drainage improvements. Replace the West Middle, East Middle, and Little Nenana River Bridges. | Temporary closures of the Totchaket Road will be required, anticipated in Spring 2023. Access onto the project area will be authorized case by case. | 59.14 | Highway |  |  | State Senate District C | The existing Totchaket Road is in poor condition with no surface course and observed settlement in multiple locations. The West Middle, East Middle, and Little Nenana River Bridges have experienced settlement at the abutments and need to be rehabilitated
87 | SDRER00410 | SKG Dyea Road 00049 – DEC 20 SE PR | 2023-06-01 | 2023-04-01 | Keri Williamson | 9074651819 | 2000000 | Skagway Municipality | Joel Osburn | 9074654409 |  | Emergency Relief | State House District 33 | This project is a Permanent Repair (PR) due to flooding that occurred during the December, 2020 storm event in the Southcoast Region of Alaska. Repairs may include, but are not limited to, asphalt, embankment, roadside hardware, retaining walls, utilities, and drainage. May include mitigation to prevent future similar damage to facilities. | One-way road closures, with night work where possible to reduce traffic impacts. | 0.59783 | Highway |  |  | State Senate District Q | This project repairs sites on Dyea Road at FEMA Damage Inventory Numbers 461214, 461216, 461217, 461260, 461261, 461648, 784616, and 784619.
88 | SFAPT00144 | KDK AIRPORT PERIMETER FENCING UPGRADES | 2023-10-15 | 2023-04-01 | Keri Williamson | 9074651819 | 6000000 | Kodiak Island Borough | James Brown | 9074651796 | 3-02-0158-022-2021 | FAA | State House District 32 | Project will replace/upgrade access controls and gates to meet 49 CFR 1542 requirements. Replace existing fencing when needed | None |  | Aviation |  | N/A | State Senate District P | Upgrade existing facilities to latest standards and improve gate function.
89 | SFAPT00174 | [6 empty] | Yakutat City and Borough |  |  |  |  | State House District 32 | [6 empty] | State Senate District P
90 | SFAPT00212 | ST. Paul Airport Visual Aid Replacment | 2023-06-24 | 2023-09-23 | Garrett Paul | 9074651897 | 650000 | Aleutians West Census Area | Peter Jackson | 9074654439 |  | FAA | State House District 37 | Remove and replace secondary wind cone and install new conduit and wire. Remove and replace primary wind cone and install new conduit and wite. Remove ladder and platform on the Snow Removal Equipment Building. Remove the rotating Airport Beacon. Install a new tip down pole and airport beacon. | No major impacts anticipated. |  | Aviation |  |  | State Senate District S | Wind cones and airport beacon are at the end of their useful life.
91 | SFAPT00236 | [6 empty] | Hoonah-Angoon Census Area |  |  |  |  | State House District 35 | [6 empty] | State Senate District R
92 | SFHWY00069 | KTN - Water Street Trestle No.1 Improvement | 2023-11-23 | 2023-04-23 | Todd Boris | 9074654439 | 3447610 | Ketchikan Gateway Borough | Kirk Miller | 9074651215 | 3224 | CTP | State House District 36 | The Alaska Department of Transportation and Public Facilities (DOT&PF) is proposing to replace Water Street Trestle No. 1 within the 1700 block of Second Avenue in downtown Ketchikan, Alaska. Water Street Trestle No. 1, also known as the Second Avenue Trestle, is a 117-foot timber trestle built in 1922 that connects access along Second Avenue. The trestle is load restricted with damage to the structural timber elements caused by a failed uphill retaining wall, age, and weathering. The purpose of the project is to improve the trestle for continued transportation access to the residences and resolve these deficiencies. | Road Closure During Construction. Access to be accommodated from each end via detours. | 0.41443 | Highway | https://dot.alaska.gov/sereg/projects/second-ave-trestle/ | 291404 | State Senate District R | Replace Water Street Trestle No. 1 with retaining wall system and new bridge components.
93 | SFHWY00072 | Ketchikan Herring Cove Bridge Improvement | 2023-10-23 | 2022-05-01 | John Kajdan | 9074652392 | 15445815.77 | Ketchikan Gateway Borough | Bran Pollard | 9074654526 | 902043 | STP | State House District 36 | Replace Herring Cove Bridge (No. 253) to include pedestrian facilities, improve the intersections of S. Tongass and Powerhouse Road and S. Tongass and Wood Road, resurface between the intersections of Powerhouse Rd and Wood Rd on S. Tongass, replace existing guardrail, and provide drainage improvements. | project closed to pedestrians | 0.68768 | Highway | https://dot.alaska.gov/sereg/projects/herring-cove/index.shtml | 291400 | State Senate District R | replace the structurally deficient Herring Cove Bridge with a modern structure and rehabilitation of the road and pavement on South Tongass between Wood Road and Powerhouse Road intersections
94 | SFHWY00103 | Sit Halibut Point Road and Peterson Avenue Intersection Safety Improvements HSIP | 2023-07-23 | 2023-05-01 | Garrett Paul | 9074651897 | 1000000 | Sitka City and Borough | Nathan Purves | 9074654521 | 3214 | HSIP | State House District 35 | Provide additional illumination at the Halibut Point Road/Peterson Avenue Intersection to achieve a level of luminance that meets current DOT&PF standards. Modify adjacent roadway lighting as needed to maintain satisfactory continuous illumination. Replace existing S1-1 School signs with W11-2 advance pedestrian warning signs. | None | 14.601 | Highway |  | 295400/295435 | State Senate District R | To improve intersection and crosswalk lighting to make the intersection safer for pedestrians.
95 | SFHWY00152 | [6 empty] | Ketchikan Gateway Borough |  |  |  |  | State House District 36 | [6 empty] | State Senate District R
96 | SFHWY00163 | Juneau Douglas Highway Slope Stabilization | 2023-07-24 | 2023-05-23 | Keri Williamson | 9074651819 | 1750000 | Juneau City and Borough | David A Pyeatt | 9074654490 | 959021 | STP | State House District 33 | This project will repair/stabilize an unstable slope on Douglas Highway | Traffic will be two way two lane traffic but diverted to the land side | 0.035648 | Highway |  | 296110 | State Senate District Q | N/A
97 | SFHWY00171 | Hains Highway Reconstruction Milepost 12.2-23.0 | 2023-03-24 | 2022-05-01 | John Kajdan | 9074652392 | 38544591.5 | Haines Borough | Gregory Lockwood | 9074652393 | 956036 | STP | State House District 33 | Project consists of reconstruction of the Haines Highway from milepost 12 to milepost 20. Work includes realignment at some locations, widening of shoulders, grading, paving and drainage improvements. | Intermittent lane restrictions/reductions | 15.9234 | Highway | https://dot.alaska.gov/sereg/projects/haines_hwy/index.shtml | 298000 | State Senate District Q | Reconstruct Haines Highway
98 | SFHWY00186 | [6 empty] | Ketchikan Gateway Borough |  |  |  |  | State House District 36 | [6 empty] | State Senate District R
99 | SFHWY00261 | Juneau Mendenhall Loop RD Egan to Stephen Richards | 2023-06-23 | 2022-05-01 | Garrett Paul | 9074651897 | 4195926 | Juneau City and Borough | N/A | 0 | 966028 | STP | State House District 34 | Resurface JNU Mendenhall Loop Road and Egan to Stephen Richards. Associated preventative maintenance activies may include minor sturctural section improvements, signals and lighting, drainage repairs, striping, signs, and ADA improvements. Project Locations and Length: Along Mendenhall Loop Road from Egan Dr to the Stephen Richards roundabout improvements for a length of 0.972 miles. | Full Closure administered in 2022. Intermittent lane closures/reductions in 2023 are expected. | 4.8088 | Highway |  | 296400 | State Senate District Q | Resurface Pavement, Striping and Drainage Structures
100 | SFHWY00263 | Juneau Franklin & Thank Resurfacing - Tram Parking Lot to Mt. Roberts St. | 2023-06-23 | 2023-04-23 | Keri Williamson | 9074651819 | 1419781 | Juneau City and Borough | Brett Wells, P.E. | 9074651607 | 3250 | STP | State House District 33 | Resurface Franklin Street from the Tram parking lot to the intersection of Thane Road and Mt. Roberts Street. Associated preventive maintenance activities may include minor structural section improvements, drainage repairs, striping, signs, and ADA improvements. | Intermittent Lane Restrictions. | 1.3816 | Highway |  | 296014/296011 | State Senate District Q | Repair subgrade in select locations and resurface Franklin Street.
101 | SFHWY00278 | HNH Harbor Way Pedestrian Imp & Pitt Island Cemetery Walkway | 2024-10-01 | 2023-08-01 | David Lowell | 9074654812 | 6000000 | Hoonah-Angoon Census Area | Bran Pollard | 9074654526 | 3255 | CTP | State House District 35 | The Hoonah Harbor Way Pedestrian Improvements & Pitt Island Cemetery Walkway project is designed to address two major issues for the community: 1) Provide safe and reliable access to the community's cemetery on Pitt Island; and 2) Alleviate tourist-related pedestrian congestion in the harbor area. The City of Hoonah plans to construct a 6-foot wide sidewalk/walkway from the Hoonah city center out to Pitt Island and the community cemetery. This 0.8 mile project will start at the intersection of Front Street and Harbor Way and end on Pitt Island. Approximately 0.5 miles of the sidewalk/walkway will be built atop the US Army Corps of Engineers' breakwater and a 175-foot long gangway will be installed from the shore to the breakwater. | 5 minute maximum traffic lane restrictions, 24 hour limited parking restrictions, limited access to dock, boat launch ramp, and utility washout station. | 1.7152 | Highway | https://dot.alaska.gov/sereg/projects/hoonah-walkway/index.shtml | 295215 | State Senate District R | Provide safe and reliable access to community's cemetery on Pitt Island and alleviate tourist-related pedestrian congestion in the harbor area.
102 | SFHWY00306 | POW HOLLIS HWY GUARDRAIL SAFETY IMPROVEMENTS HSIP | 2023-09-01 | 2023-07-01 | Patty Shull | 0 | 750000 | Prince of Wales-Hyder Census Area | Nathan Purves | 9074654521 | 3260 | HSIP | State House District 35 | Determine which upstream guardrail end terminals need to be removed and replaced along the Hollis highway to bring guardrail systems up to MASH compliance. | None | 40.3817 | Highway |  | 292000 | State Senate District R | Upstream guardrail end terminals along Hollis Highway don't meet MASH compliance.
103 | SFHWY00307 | Juneau Egan Yandukin Intersection Improvements HSIP | 2023-09-01 | 2023-05-01 | David Lowell | 9074654812 | 750000 | Juneau City and Borough | Nathan Purves | 9074654521 | 3261 | HSIP | State House District 33 | Set seasonal speed limit reduction on Egan in the vicinity of the Egan Yandukin intersection. Improve delineation for both left turns on Egan to improve line of sight and reduce travel distance to clear opposing traffic. Improve delineation for the northbound right turn movement from Egan to make it easier for southbound left turn drivers to determine if opposing traffic is executing the right turn or continuing through the intersection. | Left Turn lane closures off peak hours. | 13.6222 | Highway | https://dot.alaska.gov/sereg/projects/egan-yandukin/index.shtml | 296000 | State Senate District Q | To improve safety at the Egan Yandukin intersection.
104 | SFHWY00308 | Wrangell Zimovia Hwy Rock Fall Mitigation HSIP | 2023-10-01 | 2023-08-01 | Keri Williamson | 9074651819 | 750000 | Wrangell City and Borough | Nathan Purves | 9074654521 | 3262 | HSIP | State House District 36 | Analyze and identify areas within the three targeted rockfall zones and apply the proscribed mitigation techniques to stabilize slopes to reduce hazards falling into the road. | None | 0.18484 | Highway |  | 293300 | State Senate District R | Reoccurring rock fall events along Zimovia Highway are a risk to the public.
105 | SFHWY00315 | JNU Douglas Hwy Stage 2 Construction | 2023-07-24 | 2023-05-23 | Keri Williamson | 9074651819 | 10865554 | Juneau City and Borough | David A Pyeatt | 9074654490 | 958032 | STP | State House District 36 | Resurface Douglas Highway and provide sidewalk repairs as needed for ADA compliance. Includes other preventative maintenance improvements to roadway related features. | It is anticipated that the project will continually have two way two lane traffic. | 9.8209 | Highway |  | 296110 | State Senate District R | N/A
106 | SFHWY00379 | PSG Mitkof Hwy MPt 10.8 Culvert Replacement - DEC 20 SE PR | 2023-06-01 | 2023-04-01 | Keri Williamson | 9074651819 | 1000000 | Petersburg Borough | Joel Osburn | 9074654409 | 93001 | Emergency Relief | State House District 35 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK 2020 01 PTG001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, and utilities. | One-way road closures. | 0.1365 | Highway |  |  | State Senate District R | Repairs to damages sustained to the Letti Creek culvert passing thru Mitkof Highway from the December 2020 storm.
107 | SFHWY00411 | JNU North Douglas Highway: Bonnie Brae - DEC 20 SE PR | 2023-06-01 | 2023-04-01 | Keri Williamson | 9074651819 | 500000 | Juneau City and Borough | Joel Osburn | 9074654409 |  | Emergency Relief | State House District 33 | This project will design and construct permanent repairs (PR) to assets damaged by the December 2020 Storm in the Southcoast Region of Alaska for DDIR AK 2020 01 JNU001. Repairs may include, but are not limited to, asphalt, embankment, geotextile, riprap, drainage, roadside hardware, retaining walls, and utilities. | Temporary single-lane closure, likely less than 30-days. Short waterline shutdown periods (8-hours or less). | 0.11202 | Highway |  |  | State Senate District Q | This project will repair a site on the North Douglas Highway near Bonnie Brae subdivision due to storm damages from December 2020.
108 | SFHWY00432 | Ketchikan Wolfe Point Slope Stability Improvements |  |  |  | 9074651819 |  | Ketchikan Gateway Borough | James Brown | 9074651796 | 920032 |  | State House District 36 | Repair unstable slope from MMP 3.0 to MP 3.9 on Tongass Highway |  | 2.3523 | Highway |  | 291500 | State Senate District R
109 | TBD-1 | ANC Fuel Tank Replacement |  |  | Brian Herning, | 9074513018 |  | Anchorage Municipality | Tyler Straub | 9074513018 |  | FAA | State House District 21 | Reconstruct the general aviation apron and associated taxiways. Replace taxiway lighting. | Coordinate with tie down holders for temporary parking during construction. |  | Aviation |  |  | State Senate District K
110 | TBD-10 | AWOS – Various Locations (Central Region) |  |  | Ericka Moore | 9072694550 |  | Bethel Census Area | PMC | 9072694550 |  | FAA | State House District 38 | Install Automated Weather Observation Systems at Crooked Creek, Akiachak, Tununak, and Perryville Airports. | Work should be completed outside operational surfaces and impact is expected to be minimal. |  | Aviation |  |  | State Senate District S
111 | TBD-11 | Chignik SRE Building Rehabilitation |  |  | TBD | 0 |  | Lake and Peninsula Borough | TBD | 0 |  | FAA | State House District 37 | Replace siding, doors, and electrical improvements at the SREB. | Flight operations should not be affected. |  | Aviation |  |  | State Senate District S
112 | TBD-12 | Elim Airport Segmented Circle |  |  | Daniel Phillips | 9074512926 |  | Nome Census Area | Artem Rupert | 9074515285 |  | FAA | State House District 39 | Install a segmented circle at the Elim Airport | None anticipated. All work will be performed outside the operational areas. |  | Aviation |  |  | State Senate District T
113 | TBD-13 | Noorvik Airport Rehabilitation | [5 empty] | Northwest Arctic Borough | Yusuf Rida |  |  | FAA | State House District 40 | Rehabilitate the runway, taxiway, apron and access road, and reconstruct the airport lighting system at Noorvik Airport. | Apron, taxiway, and access road work in 2022 or 2023 with night closures. Runway rehabilitation is anticipated to be in 2023 utilizing the half-width construction technique. During scheduled services, half of the runway width will be closed while the oth |  | Aviation |  |  | State Senate District T
114 | TBD-14 | Northern Region Surface Maintenance Preservation |  |  | Daniel Phillips | 9074512926 |  | Kusilvak Census Area | TBD | 9074512926 |  | FAA | State House District 39 | Apply dust palliative at the Emmonak, Pilot Station, Mountain Village, Alakanuk, Russian Mission, Holy Cross, and Nunam Iqua Airports. | None anticipated. All work will be performed around scheduled operations. |  | Aviation |  |  | State Senate District T
115 | TBD-15 | Sitka SRE Building Rehabilitation |  |  | TBD | 0 |  | Sitka City and Borough | TBD | 0 |  | FAA | State House District 35 | Replace siding, doors, and mechanical electrical improvements at the SREB. | Flight operations should not be affected. |  | Aviation |  |  | State Senate District R
116 | TBD-2 | ANC Miscellaneous Repairs 2022 |  |  | Mahear Abou Eid | 2690446 |  | Anchorage Municipality | TBD | 2690446 |  | FAA | State House District 21 | The project will install head bolt heaters on T/W A and Dehavilland snow dumps, improve drainage at TW A snow dump and upgrade Airfield Maintenance west access gate. | No operational impacts. |  | Aviation |  |  | State Senate District K
117 | TBD-3 | ANC Parking Garage Repair & Improvement |  |  | Jesse Campbell | 2662723 |  | Anchorage Municipality | Ken Banning | 2662196 |  | FAA | State House District 21 | Repair and improve the parking garage including spall repair, crack filling, repairing and applying waterproofing, replacing driving surface, lighting upgrades and special system installation. | Phased construction to include partial closure of each parking garage level as work is executed. |  | Aviation |  |  | State Senate District K
118 | TBD-4 | ANC Postmark Drive Repairs 2023 |  |  | Mahear Abou Eid | 2690446 |  | Anchorage Municipality | TBD | 2690446 |  | FAA | State House District 21 | The project will rehabilitate 3,000 feet of Postmark Drive from West Northern Lights Blvd. to approximately the Rockwell Avenue intersection. Project includes pavement planning, paving, and striping. | One lane closures on Postmark Drive to vehicular traffic. |  | Aviation |  |  | State Senate District K
119 | TBD-5 | ANC Supply Warehouse Roof Replacement |  |  | Jesse Campbell | 2662723 |  | Anchorage Municipality | Jason Scheben | 2552668 |  | FAA | State House District 21 | Replace the roof at Warehouse WH107 including possible asbestos abatement and upgrade to mechanical systems. | Coordinate with warehouse tenants. |  | Aviation |  |  | State Senate District K
120 | TBD-6 | ANC Taxilanes E1, E3, and E/G Intersection Reconstruction |  |  | Mahear Abou Eid | 2690446 |  | Anchorage Municipality | Chelsea Knight | 8305314 |  | FAA | State House District 21 | Rehabilitated Taxilanes E1 and E3, and a section of apron near the North Terminal, and reconstructed the intersection of Taxiways E and G. A Majority of the project is complete except for pipeliner installations. | Gates will be closed during 2022 and 2023. All 5 gates will not be closed at the same time. |  | Aviation |  |  | State Senate District K
121 | TBD-7 | ANC Terminal Loop Road Improvements |  |  | Mahear Abou Eid | 2690446 |  | Anchorage Municipality | Mahear Abou Eid | 2690446 |  | FAA | State House District 21 |  | Temporary lane closures. |  | Aviation |  |  | State Senate District K
122 | TBD-8 | ANC Vertical Infrastructure Earthquake Repairs |  |  | Jesse Campbell, | 2662723 |  | Anchorage Municipality | Ken Banning | 2662196 |  | FAA | State House District 21 | Perform repairs to the Field Maintenance Facility, North Terminal and South Terminal from the 2018 earthquake. | Phased project may impact passengers at the North and South Terminals. |  | Aviation |  |  | State Senate District K
123 | TBD-9 | Aniak Joe Parent Vocational Center Demolition and Remediation |  |  | Eric Hershey | 9072695572 |  | Bethel Census Area | TBD | 9072695572 |  | FAA | State House District 38 | Remediate and demolish the existing Joe Parent Vocational Center building and ancillary facilities. | Flight operations should not be affected. |  | Aviation |  |  | State Senate District S
124 | TBD (child project to CFHWY00395) | Elmore Rd Pavement Preservation: Abbott Rd to Providence Dr - Phase 1 | 2023-10-01 | 2023-05-01 | Ericka Moore, P.E. | 9072690450 | 7500000 | Anchorage Municipality | Cynthia Ferguson, P.E. | 9072690693 |  | NHPP | State House District 17 | The proposed work would include the following: • Structural section repairs • Bridge repair and resurfacing • Pedestrian facility improvements • Upgrade or rehabilitate signals, lighting, traffic recording equipment • Upgrade guardrail including end treatments • Drainage improvements • Utility relocations • Crack sealing • Vegetation clearing and grubbing • Upgrade signage and striping | Road users may experience delays during project construction. However, traffic impacts would be mitigated by providing advance notice to the public and through implementation of a traffic control plan. Construction may also be scheduled at off-peak hours | 6.2449 | Highway |  | 2281274X000 | State Senate District I | The purpose of the proposed project is to extend the service life of the facility, reduce maintenance costs, and improve safety. The roadway throughout the project corridor exhibits signs of deterioration including distressed pavement, faded pavement mar
125 | Z512210000 | Seward Meridian Parkway Road Improvements, Phase II Palmer-Wasilla Highway to Seldon Road | 2023-10-25 | 2023-02-23 | Ericka Moore, P.E. | 9072690450 | 55000000 | Matanuska-Susitna Borough | Chris Bentz, P.E. | 9072690652 | 1417 | STP | State House District 10 | Upgrade Seward Meridian to a four-lane roadway and a multi-use, separated pathway along the west side from the Palmer-Wasilla Highway to Bogard Road and extend SMP one mile from Bogard Road to Seldon Road. Intersection improvements include five new signals at the intersections of E. Country Field Circle, E. Birch View Drive, Bogard Road, E. Tambert Drive, and Seldon Road. A new bridge, Cottonwood Creek Bridge #1696, will replace the existing culvert crossing. | Anticipate potential nightly closure for final signal installations and for cross culvert installations. A detour and potential weekend closures maybe needed at Cottonwood Creek for culvert removal and Bridge installation. | 17.9477 | Highway | http://www.brooks-alaska.com/sewardmeridian/ | 2381005X000 | State Senate District D | The purpose of the proposed project is to increase the capacity of SMP between the Palmer-Wasilla Highway and Bogard Road and to extend SMP to Seldon Road, providing a key system linkage from Seldon Road to the Parks Highway.
126 | Z516210000 | TAKOTNA: GOLD CR BRIDGE & TATALINA BRIDGE REPLACEMENT |  |  | Ron Searcy | 19072690656 |  | Yukon-Koyukuk Census Area | Steven Rzepka | 19072690592 | 000S783 | STP | State House District 37 | The Alaska Department of Transportation and Public Facilities (DOT&PF) in cooperation with the Federal Highway Administration (FHWA) proposes to replace Gold Creek Bridge with a large diameter culvert, and replace the Tatalina River Bridge #462. | Detours are expected for Tatalina River bridge and Gold Creek culvert replacements. | 1.1593 | Highway |  | 8241001X000 | State Senate District S | The purpose of the proposed project is to construct structures with higher weight capacities and greater resistance to scour. The current infrastructure is deteriorating and the existing bridges do not conform to current design standards.
127 | Z530140000 | Sterling Highway MP 45-60; Sunrise to Skliak Lake Rd Stage 2 Juneau Creek Bridge |  |  | Jonathan Tymick | 9072690543 |  | Kenai Peninsula Borough |  |  |  | FHWA | State House District 29 |  | Stage 2 work: Minimal traffic impacts for bridge work. Large equipment will be accessing at Juneau Creek Rd (Sterling Hwy MP 53) and Bean Creek Rd (Sterling Hwy MP 47.5). Access to hiking trails will be maintained. | 0.41859 | Highway |  |  | State Senate District O
128 | Z536100000 | Seward Hwy: MP 17-22.5 Rehabilitation | 2023-10-24 | 2022-05-01 | Jacob Gondek | 19072690445 | 70672875 | Kenai Peninsula Borough | Clint Alder | 19072690544 | 311032 | STP | State House District 29 | The Alaska Department of Transportation, in cooperation with QAP, is working to improve the Seward Highway between MP 17 and 22.5. Project work includes replacing Victor Creek Bridge, rehabilitating Snow River Bridges, as well as installing grading, drainage, paving, signage and striping. | Ongoing lane and road closures expected. | 9.9356 | Highway |  | 1020000X000 | State Senate District O | Project will rehabilitate the Seward Highway, including realigning curves, replacing the Victor Creek bridge and rehabilitating the Snow River bridges, widening shoulders, and improving drainage.
129 | Z539350000 | AMATS: O'MALLEY ROAD RECONSTRUCTION, LIVINGSTON STREET to HILLSIDE DRIVE, PHASE II | 2023-09-01 | 2021-05-01 | Ron Searcy | 9072690656 | 22177021 | Anchorage Municipality | Chris Bentz | 9072690652 | 512005 | AMATS | State House District 26 | This project will reconstruct O’Malley Rd from Livingston Street to Hillside Drive. | This project will include delays, intermittent lane closures, and potential detours. Reasonable access will be maintained to public and private property in the area. | 15.592 | Highway |  | 2281016X000 | State Senate District M | This is the second phase in a two phase construction effort to reconstruct O’Malley Rd to improve safety and capacity at intersections and to accommodate pedestrians.
130 | Z543730000 | PARKS HIGHWAY MP 48.8 to 52.3 RECONSTRUCTION | 2023-06-01 | 2020-05-01 | Ericka Moore | 9072694550 | 39961801 | Matanuska-Susitna Borough | Sean Baski | 9072690566 | 0A4-1(29) | NHPP | State House District 8 | This federally funded project will upgrade the existing two-lane road to a four-lane divided highway with at-grade intersections spaced every half-mile. Work includes improving existing frontage roads, new frontage roads, reconstruct and/or relocate the existing pedestrian pathway, illumination, and replacement of existing culvert at Little Meadow Creek with a bridge. | This project will include delays, intermittent lane closures, and potential detours. Reasonable access will be maintained to public and private property in the area. | 25.2891 | Highway |  | 1140000I000 | State Senate District D | The project will improve safety and capacity on this major highway.
131 | Z559670000 | Glenn Highway Rehabilitation Kings River Bridge Section: MP 66.0 to MP 67.2 | 2023-10-24 | 2023-05-23 | Construction by Western Federal Lands | 0 | 18000000 | Matanuska-Susitna Borough | Chris Bentz | 9072690652 | AK DOT 135(6) | STP | State House District 9 | Replace the existing Kings River Bridge and realign the Glenn Highway to match new bridge location. | Traffic delays should be expected at times. Closures are not anticipated. | 5.2865 | Highway |  |  | State Senate District E | Existing bridge structure is nearing end of life and is in deteriorating condition. Project will construct new bridge.
132 | Z581060000 | STERLING HWY: MP 157-169 RECONSTRUCTION - ANCHOR PT TO BAYCREST HILL | 2024-02-01 | 2023-07-01 | TBD | 0 | 85000000 | Kenai Peninsula Borough | Kelly Summers | 9072690546 | 211052 | NHPP | State House District 31 | This project will reconstruct 12 miles of the Sterling Highway along the existing corridor. Project upgrades include widening, construction of passing lanes, resurfacing, scenic turnouts, drainage improvements, minor realignment, and configuration to current AASHTO geometric standards. Also, rehabilitation/replacement of the North Fork Anchor River and Anchor River Bridges. | This project will include delays, intermittent lane closures, and detours. Reasonable access will be maintained to public and private property in the area. | 26.4658 | Highway | http://www.sterlinghwymp157-169.com/ | 1000000X000 | State Senate District P | The project will improve safety and capacity on this major highway and replace multiple crossings nearing the end of their service life.
133 | Z585470000 | Quartz Creek Bridge Replacement | 2023-10-01 | 2023-04-01 | Jonathan Tymick | 9072690453 | 7500000 | Kenai Peninsula Borough | Galen Jones, P.E. | 902690550 | 1531 | STP | State House District 29 | Replace Bridge #1020 across Quartz Creek on Quartz Creek Road. | A temporary detour bridge will be constructed to maintain traffic through the project site. | 0.32452 | Highway |  | 1001006X000 | State Senate District O | The existing Quartz Creek Bridge (1020) is classified as functionally obsolete due to its narrow width and load limit. The 11-ton load limit indicates the bridge is structurally deficient for maintenance equipment to be driven across.
134 | Z589760000/CFHWY00217 | PARKS HIGHWAY BRIDGE REPLACEMENTS: MONTANA CREEK, SHEEP CREEK, and GOOSE CREEK | 2023-09-01 | 2022-05-01 | Ericka Moore | 9072694550 | 29947709 | Matanuska-Susitna Borough | Christina Huber | 9072690572 | 0A41034/0A41036 | NHPP | State House District 10 | This federally funded project will replace crossings at three Parks Highway Creeks. Montana Creek Bridge (#215) and Sheep Creek Bridge (#213) will be replaced. The Goose Creek crossing (#2343) will have three primary arch-pipes and two overflow pipes replaced. Project work includes detours, embankment, pathway, drainage, paving, guardrail, signing and striping. | Temporary detour bridges will be constructed to maintain traffic through the project sites, with potential for delays and intermittent road closures. | 13.5693 | Highway |  | 1140000I000 | State Senate District E | This project will replace multiple crossings that are nearing the end of their service life.
135 | Z605630000 | Saint Mary’s Airport Improvements | 2023-09-01 | 2023-06-01 | Charlie Bohart | 9074515367 | 53579007 | Kusilvak Census Area | Frank Jordano | 9074341200 |  | FAA | State House District 39 | Rehabilitate the resurface runways, taxiways, and apron. Project will include replacing airport lighting and runway safety area improvements. | Airport will experience regular night closures for the duration of project, likely June – Sept 2022. RW will be made ready for medevacs with 30‐minute notice. |  | Aviation |  |  | State Senate District T
136 | Z606320000 | Alaska Highway Passing Lanes (CONST 1330-1400) | 2023-10-01 | 2023-04-01 | Kyungyun Chi | 9073743709 | 13000000 | Southeast Fairbanks Census Area | Jennifer Wright | 9073718949 | 2332 | STP | State House District 9 | Construct lanes at various locations on the Alaska Highway between Delta Junction and the Canadian border | There may be impacts to the travelling public such as flaggers, pilot cars, etc. | 25.7577 | Highway | https://alaska-hwy-passing-lanes-akdot.hub.arcgis.com/ | 1150000X000 | State Senate District E | The Alaska Highway is the primary year round surface route connecting Alaska with Canada and the lower 48 states (a segment of Alaska Route 7 connects Haines to Haines Junction in Canada). There are no locations on the Alaska Highway where vehicles can p
137 | Z607150000 | Richardson Highway MP 266-341 Passing Lanes | 2023-10-25 | 2023-05-23 | Kyungyun Chi | 9073743709 | 40000000 | Fairbanks North Star Borough | Carl F. Heim | 9074515359 | 0A23021 | STP | State House District 9 | Construct passing lanes at multiple locations between Milepost 266 and 341 of the Richardson Highway. Work includes roadside hardware, drainage improvements, intersection improvements and utilities. | Up to 20-minuete delays should be expected during construction. No road closures are anticipated. | 20.8573 | Highway | https://dot.alaska.gov/nreg/richardsonpassinglanes/ |  | State Senate District E | Giving motorists more opportunities to pass withing the corridor will improve safety.
138 | Z607340000/Z615970000 | Richardson Hwy MP 359 Railroad Grade Separated Facility & Richardson Hwy MP 357-362 Bicycle/Pedestrian Path | 2023-10-24 | 2023-05-01 | Kyungyun Chi, P.E. | 9073743709 | 25000000 | Fairbanks North Star Borough | Lauren Little, P.E. | 9073785911 | 0A24033/0A24032 | NHPP | State House District 2 | Construct a grade separated railroad crossing for the Richardson Highway at MP 359 and construct a separated bicycle/pedestrian path from the GARS intersection to Badger Road. Rich 359 grade separation is NHPP, Rich 357-362 path is HSIP. | Overpass - Reduced speed (45 mph) through the project area during construction and nighttime lane closures. Path - None. | 35.4805 | Highway | https://dot.alaska.gov/nreg/rich359/ | 1100000D00/1100000I000 | State Senate District A | Eliminate the at-grade railroad crossing on the Richardson Highway near MP 359 and provide continuous separated bicycle/pedestrian facilities from the Steese Expressway/Airport Way to Badger Road.
139 | Z607350000 | Dalton Highway MP 18-37 Reconstruction | 2025-09-01 | 2023-03-01 | Guan Griffin, P.E. | 9074515087 | 83000000 | Yukon-Koyukuk Census Area | Carl F. Heim, P.E. | 9074515359 | 652017 | STP | State House District 6 | Reconstruct the Dalton Highway from Milepost 18 to 37. The project work includes grading, bridge replacement, roadside hardware and drainage improvements. | Three roadway closures of up to 12 hours each, with a minimum 48 hours between closures, may be allowed during the duration of the project. | 40.3619 | Highway | https://dot.alaska.gov/nreg/dalton18-37/ | 150000 | State Senate District C | The purpose of this project is to improve safety, reduce maintenance costs, and extend the life of the roadway.
140 | Z609130000 | Dalton Hwy MP 289-305 Rehabilitation | 2024-09-01 | 2021-08-01 |  |  | 40000000 | North Slope Borough | Sarah Schlichting |  |  | FHWA | State House District 40 |  | Expect one-lane traffic, 20-minute delays, and pilot car operations. | 32.7821 | Highway |  |  | State Senate District T
141 | Z612990000 | Parks Hwy MP 231 Enhancements | 2023-07-23 | 2023-06-23 |  |  | 22500000 | Denali Borough | Carl Heim |  |  | FHWA | State House District 6 | Rebuild the Parks Highway in front of Grizzly Bear and McKinley Village in Denali National Park and construction a park wayside. | Traffic impacts all season. This area is sensitive to tourists and business access will be paramount. | 2.3422 | Highway |  |  | State Senate District C
142 | Z618720000 | Airport Way (West) Improvements | [5 empty] | Fairbanks North Star Borough | Dave Fischer |  |  | FHWA | State House District 5 | Reconstruct Airport Way, Hoselton Road, Dale Road, Old Airport Way, and Wien Lake Road. Work includes roadside hardware, drainage improvements, intersection improvements utilities and ADA improvements such as curb ramps and sidewalks. | Expect traffic to be reduced to one lane in each direction to and from the airport and surrounding areas. | 13.7621 | Highway |  |  | State Senate District C
143 | Z621230000 | Nome Port Road Reconstruction | 2023-10-24 | 2023-09-23 | Charlie Bohart | 9074515367 | 7500000 | Nome Census Area | Lauren Little | 9073785911 | 2278 | STP | State House District 39 | Scope: Reconstruct Port Road and construct pedestrian facilities along Port Road in Nome. Work includes reconstruction, roadside hardware, drainage improvements, intersection improvements, ADA improvements, and utilities. Description: This project will rehabilitate Port Road in Nome (approximately 0.6 miles) including reconfiguring the intersection with Jetty Road at the southern end, the intersection with Jafet Road, and the intersection with Submarine Beach Road at the northern end. A separated pedestrian pathway will be built along the west side of Port Road from Jetty Road to Jafet Road. | The Nome Port Road Reconstruction project is expected to be under construction at the same time as the Port of Nome expansion, as well as projects on Seppala Drive and Center Creek Road. Detours and traffic delays are anticipated. | 1.7058 | Highway | https://dot.alaska.gov/nreg/port-road/ | 9141028X000 | State Senate District T | The intersections within the project area will be modified to improve sight distances and reduce confusion between the various vehicle traffic and pedestrian and improve traffic flow. A separated path will eliminate the need for pedestrians to share the
144 | Z621710000 | Shageluk Airport Access Road Improvements | 2023-09-23 | 2023-05-23 |  |  | 5556859.85 | Yukon-Koyukuk Census Area | Yusuf Rida |  |  | FAA | State House District 37 | Reconstruct approximately 2.6 miles of the Shageluk Airport Access Road from Hamilton Slough to the airport. | Minor traffic delays during daytime with night closures allowed from 6:00pm to 8:00am. |  | Aviation |  |  | State Senate District S
145 | Z631860000 | Richardson Highway MP 167-173 Reconstruction | 2023-10-24 | 2023-04-23 | Guan Griffin, P.E. | 9074515087 | 37500000 | Copper River Census Area | Russ Johnson, P.E. | 9074515059 | 713010 | STP | State House District 9 | Reconstruct the Richardson Highway between MP 167 and 173 with two 12-foot lanes and 6-foot wide paved shoulders. Additional work includes drainage improvements and replacement of roadside hardware. The scope includes a realignment of a segment of the highway to the east, around the Meiers Lake area (approx. MP 170). | Traffic delay during construction | 24.3025 | Highway |  | 190000 | State Senate District E | The project is being constructed to improve safety by bringing this section of the Richardson Highway up to current design standards. The pavement is in need of replacement, the embankment is steep, and the alignment has numerous sharp horizontal and ver
146 | Z632130000 | University Avenue Rehabilitation & Widening | 2023-10-01 | 2023-05-01 | Brian Herning, P.E. | 9074513018 | 12500000 | Fairbanks North Star Borough | Lauren Little, P.E. | 9073785911 | 617013 | NHPP | State House District 5 | Reconstruct University Avenue from Holden Road through Airport Way, including construction of a cul-de-sac on Marlin Street. Improvements include continuous sidewalks, intersection improvements at Rewak Drive, construction of a continuous raised median, shoulders, drainage improvements and utility relocations. | University Avenue will be closed between Rewak Drive and Airport Way for much of the season. | 3.3915 | Highway | https://dot.alaska.gov/nreg/university/ | 2581185X000 | State Senate District C | To improve safety through construction of access control along this busy corridor, as well as provide a continuous bicycle/pedestrian route.
147 | Z638420000 | Point Hope Runway Realignment | 2024-10-31 | 2023-06-01 |  | 0 | 31500000 | North Slope Borough | Jonathan Hutchinson | 9074515479 |  | FAA | State House District 40 | Reconstruct and re-align the runway and airfield lighting at Point Hope. Reconstruct the taxiway. Resurface the apron. | Runway will experience night closures, and a temporary three day closure during daytime. Runway will temporarily operate at half width during daytime operations. |  | Aviation |  |  | State Senate District T | The Point Hope runway is eroding on the north end and must be re-aligned away from the active coastal erosion.
148 | Z674660000 | Ketchikan Ferry Terminal Improvements - Phase II | 2023-11-01 | 2023-10-01 | Hrant Harutyunyan | 9074654812 | 2226002 | Ketchikan Gateway Borough | N/A | 0 | 000S855 | STP | State House District 36 | This project encompasses the replacement of an existing vessel berthing and turning dolphin structure at the west end of Berth 1; placement of a new turning dolphin between Berths 1 and 3, refurbishment of fendering and platform components at the Berth 3 float; construction of a new pedestrian cover structure over the existing sidewalk from the terminal building to the Berth 3 approach; and the placement of cathodic protection anodes on all existing offshore pile supported structures at Berths 1 and 3. | " A 40 day consecutive closure (Berth 3 only) will be permitted between October 1, 2023 and November 30, 2023. During the closure period the Department will provide alternative accommodations for ferry vessel operations." |  | AMHS |  | N/A | State Senate District R | "The project would replace the damaged ferry vessel fender system along the face of a 120’ long floating platform, install a new gangway and gangway landings, and make electrical and lighting improvements."
149 | Z676720000 | Sitka Katlian Bay RD | 2023-11-24 | 2022-05-01 | John Kajdan | 9074652392 | 31755278 | Sitka City and Borough | N/A | 0 |  | GF | State House District 35 | Construct approximately 9 miles of unpaved roadway and bridges from the current end of Halibut Point Road to the US Forest Service (USFS) trail system beyond the private lands in Katlian Bay. Approximately 3 miles of this roadway includes the reconstruction of an existing logging road system from the mouth of Katlian Bay to the USFS boundary. The USFS trail system provides recreational and subsistence opportunities for the public including fishing, hunting, hiking, berry picking, and ATV use. There is also the potential that the private lands in Katlian Bay could provide a material source for future development in Sitka. The community has expressed a need for a rock source in the Sitka area to support future development and construction projects. | No major traffic impacts to existing road system. | 13.9992 | Highway | https://dot.alaska.gov/sereg/projects/sitka_katlianbayroad/index.shtml |  | State Senate District R | The purpose of the Proposed Action is to provide: increased recreational and subsistence opportunities on Baranof Island within NFS lands of the Tongass National Forest, Sitka Ranger District, and  opportunity for development of new material sources o
150 | Z680910000 | Ketchikan Tongass Ave Improvements |  |  | Garrett Paul | 9074651897 | 12000000 | Ketchikan Gateway Borough | Peter Jackson | 9074654439 | 902042 | STP | State House District 36 | Refurbish Tongass Avenue, from MP 0.2000 to 1.2798 including rehabilitation of asphalt and concert pavement surfaces, curb and gutter, sidewalk, and correct ADA deficiencies, making improvements to the lane configurations and to the pedestrian and bike facilities to improve safety and level of service. | Mostly night construction. | 3.863 | Highway | https://dot.alaska.gov/sereg/projects/ktn_tongass_avenue/ | 291400 | State Senate District R | The corridor is in need of rehabilitation due to surface deterioration.
151 | Z681000000 | Sitka Sawmill Ceek RD. Resurface: Jeff Davis to Smith ST | 2023-12-23 | 2022-05-01 | Garrett Paul | 9074651897 | 7254223 | Sitka City and Borough | Bran Pollard | 9074654526 | 933042 | CTP | State House District 35 | Improve Sawmill Creek Road to make it more accessible to pedestrians, including those with disabilities, and improve mobility of bikers. This project will widen the sidewalks on the south side of Sawmill Creek Road from the roundabout to Jeff Davis Street and install bump-outs around the existing utility poles at the North edge sidewalk for ADA compliance. Remove parking from the South side of the road and install 5' bike lanes on each side of the vehicle lanes. Install concrete median to better delineate Sawmill creek Road and DeGroff Street. Resurface the entire project length. Replace the underground storm drain system. Replace school zone flashers and highway lighting system. Install added signage at the cross walk at Baranoff Street. | Intermittent lane restrictions/reductions. No major impacts anticipated in 2023. | 0.97233 | Highway | https://dot.alaska.gov/sereg/projects/sitka_sawmill_rd/index.shtml | 295500 | State Senate District R | Improve Sawmill Creek Road to make it more accessible to pedestrians, including those with disabilities, and improve mobility of bikers. Rehabilitate pavement structure.
152 | Z681240000 | Juneau Glacier Highway Improvements - Lemon Creek Area | 2023-07-22 | 2023-05-21 | Garrett Paul | 9074651897 | 17000000 | Juneau City and Borough | N/A | 123 | 955016 | CTP | State House District 33 | Resurface and improve Glacier Hwy from Glacier Highway Access Road to Twin Lakes. Improvements include: resurface entire length of roadway and address drainage needs, add pedestrian facilities on the water side of street, convert the Renninger Street intersection to a roundabout, add a traffic signal to the Davis Street intersection, adjust other driveways and intersections as needed, improve curb ramps to meet ADA standards as required according to the Alaska Preconstruction Manual, stripe bike lanes, determine crosswalk locations, install bus pullouts as needed, and address lighting needs. | Intermittent lane closures, detours, and limited and or delayed access to active business'. | 4.1892 | Highway |  | 4441045X000 | State Senate District Q | Improve existing facilities and ADA standards.
153 | Z768840000 | Kotzebue to Cape Blossom Road - Stage 1 | 2023-10-24 | 2023-07-23 | Charles Bohart, P.E. | 9074515367 | 45000000 | Northwest Arctic Borough | Jonathan Hutchinson, P.E. | 9074515479 |  | CTP | State House District 40 | Construct Stage II of the road from Kotzebue to Cape Blossom. Project includes extending road from Sadie Creek to Cape Blossom and constructing a new bridge over Sadie Creek (#1596). | new bridge over Sadie Creek | 28.0673 | Highway |  |  | State Senate District T
154 | Z768840000 | Kotzebue to Cape Blossom Road - Stage Ii | 2023-10-24 | 2023-07-23 | Charles Bohart, P.E. | 9074515367 | 45000000 | Northwest Arctic Borough | Jonathan Hutchinson, P.E. | 9074515479 | 2204 | CTP | State House District 40 | Construct Stage II of the road from Kotzebue to Cape Blossom. Project includes extending road from Sadie Creek to Cape Blossom and constructing a new bridge over Sadie Creek (#1596). | new bridge over Sadie Creek | 28.0673 | Highway | https://dot.alaska.gov/nreg/capeblossomroad/ | new road | State Senate District T | to construct a new road from Kotzebue to Cape Blossom and barge landing, to lower the costs of barging goods to Kotzebue.