Iliamna Airport

Paving and Fencing

Project No. 54739

AIP No. 3-02-0132-06

SAFETY PLAN

I.	INTRODUCTION

The following is the Safety Plan to be used during construction activity at Ilaimna Airport.

The purpose of the plan is to present information needed for operation of the airport and construction so that there is a minimum of disruption to operations of air and ground traffic and so the construction project can be completed in the shortest time possible.

Work to be accomplished on this project includes the following:

*	Paving of the existing runways, taxiways, aprons and access road

*	Construct new Taxiway C from Taxiway A to Runway 7-25

*	Construct new service road from ARFF/SRE Building to Runway 7-25

*	Install new emergency generator adjacent to ARFF/SRE Building

*	Install perimeter fencing including two power gates

II.	Contacts and Notification

A.	Chain of Notification

The DOT&PF Project Engineer will be the central point of contact between the Contractor, Iliamna Airport and the FAA.

Tony Barter, P.E.

Project Manager

Telephone (907)269-0659

FAX (907)269-0671

, Project Engineer

Telephone (907)

FAX (907)

The following person will be the point of contact with the FAA in matters relating to the FAA facilities at Iliamna Airport:

Verne Jensen, SA SMO, (907)269-1149

B.	Issuance of Notices to Airmen (NOTAM’s)

The Iliamna Airport Manager will issue NOTAM’s for the airport.  The following person, or his designated representative, has authority to issue NOTAM’s and shall be the point of contact for required issuance’s, updates and cancellations:

John Adcox, Airport Manager

Telephone (907) 571-1261

FAX  (907) 571-1298

C.	Radio Frequencies

Flight Service Station (FSS) - 123.6 MHz

(Part time - hours of operation vary)

(this is also the Common Traffic Advisory Frequency, CTAF)

Remote Communications Outlet (RCO)  - 123.6 MHz

(Remote to Kenai FAA)

III.	Construction Activities

A.	Scheduling of Work

Work is expected to begin in August of 2002 and be completed by October 31, 2003.

B.	Haul Routes

The borrow area for the project is located off of the north end of Runway 17-35.  Haul routes will generally be as follows:

Runway 17-35 - Haul direct to north end of runway.

Runway 7-25 - Haul on west access road to west end of runway or via the Iliamna-Nondalton Road to the new ARFF service road to the east end of the runway.

East Apron - Haul via Iliamna-Nondalton Road to service roads at north and south ends of apron.

West Apron - Haul via West Access Road to apron.

Other haul routes may be used if coordinated with the Engineer and Airport Manager.

C.	Location of Flaggers

Flaggers will be utilized as following:

1.	Where construction activity is being conducted within 200’ of an open runway.

2.	Where construction activity is being conducted in close proximity to operating aircraft and the Engineer determines that a flagger is needed.

Generally, flaggers will not be positioned at taxiway crossings and along haul routes unless safety concerns occur during construction.

Flaggers stationed within 200’ of an open runway will be equipped with radio communication on the CTAF frequency.

D.	Utility Line Location

The Contractor will request locates from all the utilities having facilities in the project area.  Their telephone numbers are as follows:

Locate Call Center			1-800-478-3121

Interior Telephone Co./TelAlaska	1-800-478-3121 (through Locate Call Center)

INN Electric Cooperative		(907)571-1259

FAA 					(907)269-1149

There is a taxiway/runway lighting system power cable running through the apron expansion area.  The FAA has various navigational aids and other equipment in operation at Iliamna Airport.  There may be FAA cables and equipment that are not shown on the construction drawings.  The Contractor will contact the FAA for locates prior to excavation and/or stockpiling as appropriate.

Where the Contractor's operations meet any of the following conditions, the Contractor will advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within three feet of an underground electrical line according to locates provided by the owning utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice will indicate the location and duration of the work to be performed.

The Contractor will provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line or the equipment is digging within 3 foot of a buried electrical line.

All existing utilities in service at the start of the project will remain in service.  The Contractor will be required to repair any damage caused to utilities by the Contractor's operations at no cost to the Department.

There may be various utility appurtenances located within the project limits.  The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around aboveground and underground utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

E.	Borrow Pit Location on Airport Property

The borrow pits are located to the north or west of Runway 17-35 on airport property.

F.	Marking and Lighting of Excavations, Open Trenches and Other Hazardous Areas

Open excavations, trenches and hazardous areas will be marked with barricades visible at night or other times of reduced visibility as determined by the Airport Manager.  Barricades will be placed along the Project Limits where aircraft are operating or around other portions of the work that may be deemed hazardous by the Engineer.  Barricades will be placed to protect portions of the project site left open for baggage-handling equipment or other aircraft service vehicles and personnel.  Taxiway lights removed along active movement areas shall be replaced temporarily with lighted barricades as shown in the plans and described below.

Barricades will be 12" x 12" by 8' timbers, spaced approximately 8' apart.  Each barricade will be painted for high visibility and marked with both a flag and flashing light.

IV.	Aircraft Operations Area

A.	Restriction of Aircraft Activity on Airport Operation Areas and Runway and Taxiway Closures

Construction activity will occur on all runways, taxiways and aprons.  This will require closure of each area at certain times during the course of the project.  The following criteria will be followed in construction activities.

*	One runway will remain open at all times for its entire length except during construction in the intersection.

*	Either Taxiway A or  C shall remain open to the East Apron at all times.

*	Lighting on one runway and either Taxiway A or C will remain operational during hours of darkness.

*	Access to the East Apron will be maintained at all times.

*

With the exception of work at the runway intersection, one runway will remain open at all times for its full length.  When work is being performed on a runway, that runway will be closed to operating aircraft.

During construction at the runway intersection, the north end of Runway 17-35 will be open.  The available runway length will be 3,400’.

B.	Runway and Taxiway Safety Areas

The safety area for runways at the airport is 300’ wide and 600’ beyond the end of each runway. The taxiway safety area width for Taxiway A is 118’ and the safety area width for Taxiway B is 79’.

C.	Setback Lines From Active Runways and Taxiways

The setback for work in the vicinity of an open runway is 200 feet

FAA AC 150/5370-2C allows work to occur to one-half of the wing span of the most demanding aircraft plus 25’ from the centerline of the taxiway.  For Iliamna, the most demanding aircraft is the Douglas DC-6 with a wingspan of 117.5’.  The setback for work on Taxiway A and C will be 84 feet.  For Taxiway B, the most demanding aircraft have wing spans of less than 40’ with a setback of 45 feet.  Operations may occur within this area, however, the Contractor will be required to give way to all taxing aircraft.

- Aircraft Operations in the Vicinity of Work Sites

The Contractor will coordinate project work with air carrier, air cargo and air taxi operations.  A work site subject to jet engine blast or propeller wash may have to be secured and personnel evacuated until subject aircraft have departed.  When aircraft using the East Apron make the turn to return to the runway, the apron worksite will be subject to jet or propeller blast.

The Contractor will be required to coordinate access to and from the businesses operating on the East Apron and assure that a suitable taxi route is provided to and from the runways.

V.  SECURITY PROGRAM

There is currently no security program at the Iliamna Airport.