## Engineers Estimate
ENGINEER'S ESTIMATE
Akiachak Airport Relocation
3-02-0461-001-2009 /59011
Last Modified: 5/18/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 135 | 402 | 54270
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 200 | 672 | 134400
F-162a | 8' Chain-Link Fence | Linear Foot | 150 | 106 | 15900
F-162d | 4' Single Cantilever Gate | Each | 2000 | 2 | 4000
F-170a | Steel Bollard | Each | 1000 | 16 | 16000
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 1475000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 350000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 40000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 30000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 7500 | 1 | 7500
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 25000 | 1 | 25000
G-131b | Engineering Transportation (ATV) | Each | 15000 | 1 | 15000
G-131c | Engineering Transportation (Snowmachine) | Each | 15000 | 1 | 15000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 100000
G-135b | Extra Three Person Survey Party | Hour | 250 | 50 | 12500
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 210 | 50 | 10500
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 25000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 12000 | 1 | 12000
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1100 | 48 | 52800
L-100e | Taxiway Edge Light, L-861T | Each | 1300 | 26 | 33800
L-100p | Handhole, L-867, Size B | Each | 800 | 8 | 6400
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 12000 | 1 | 12000
L-107a | 8-foot Lighted Wind Cone, in place | Each | 15000 | 1 | 15000
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 10000 | 1 | 10000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 23250
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 12900
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 3500
L-108g | Ground Rod | Each | 300 | 10 | 3000
L-109c | Electrical Enclosure and Foundation, In Place | Each | 30000 | 1 | 30000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 35000 | 1 | 35000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 147000
P-151a | Clearing | Acre | 1500 | 143 | 214500
P-152c | Muck Excavation | Cubic Yard | 10 | 10300 | 103000
P-152h(1) | Borrow Measured at Source | Cubic Yard | 17.5 | 466000 | 8155000
P-152af | Settlement Platform | Each | 3000 | 6 | 18000
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 10000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 25000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 40000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 135 | 23800 | 3213000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 135 | 100 | 13500
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 40000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 2000 | 3 | 6000
P-660b | Reflective Marker, Type II | Each | 120 | 28 | 3360
P-660c | Cone, 18 inch | Each | 100 | 74 | 7400
P-661a | Standard Sign | Square Foot | 250 | 43.25 | 10812.5
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 4000 | 2 | 8000
P-681b | Geotextile, Stabilization | Square Yard | 2.5 | 326600 | 816500
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 250000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 665000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 625000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 20000 | 1 | 20000
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 10000
S-143d | Electric Dispensing System | Each | 15000 | 1 | 15000
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 20000 | 1 | 20000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 5000
T-901a | Seeding | Acre | 3000 | 22 | 66000
T-901c | Water for Maintenance | M-Gal | 50 | 1650 | 82500
T-905b | Organic Material | Cubic Yard | 10 | 9600 | 96000
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1.5 | 178300 | 267450

## Bid Comparison
Bid Comparison
Akiachak Airport Relocation
3-02-0461-001-2009 /59011
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount | (+/-)%
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 135 | 402 | 54270
1 | PHILLIPS & JORDAN, INC. |  | 150 |  | 60300 | 11.11%
2 | KNIK CONSTRUCTION CO., INC. |  | 150 |  | 60300 | 11.11%
3 | BRICE INC. |  | 200 |  | 80400 | 48.15%
4 | QAP |  | 200 |  | 80400 | 48.15%
5 | KIEWIT PACIFIC CO. |  | 200 |  | 80400 | 48.15%
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 200 | 672 | 134400
1 | PHILLIPS & JORDAN, INC. |  | 200 |  | 134400 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  | 240 |  | 161280 | 20%
3 | BRICE INC. |  | 250 |  | 168000 | 25%
4 | QAP |  | 250 |  | 168000 | 25%
5 | KIEWIT PACIFIC CO. |  | 250 |  | 168000 | 25%
F-162a | 8' Chain-Link Fence | Linear Foot | 150 | 106 | 15900
1 | PHILLIPS & JORDAN, INC. |  | 90 |  | 9540 | -40%
2 | KNIK CONSTRUCTION CO., INC. |  | 165 |  | 17490 | 10%
3 | BRICE INC. |  | 150 |  | 15900 | 0%
4 | QAP |  | 200 |  | 21200 | 33.33%
5 | KIEWIT PACIFIC CO. |  | 350 |  | 37100 | 133.3%
F-162d | 4' Single Cantilever Gate | Each | 2000 | 2 | 4000
1 | PHILLIPS & JORDAN, INC. |  | 1800 |  | 3600 | -10%
2 | KNIK CONSTRUCTION CO., INC. |  | 2000 |  | 4000 | 0%
3 | BRICE INC. |  | 1500 |  | 3000 | -25%
4 | QAP |  | 2000 |  | 4000 | 0%
5 | KIEWIT PACIFIC CO. |  | 10000 |  | 20000 | 400%
F-170a | Steel Bollard | Each | 1000 | 16 | 16000
1 | PHILLIPS & JORDAN, INC. |  | 1100 |  | 17600 | 10%
2 | KNIK CONSTRUCTION CO., INC. |  | 1400 |  | 22400 | 40%
3 | BRICE INC. |  | 1250 |  | 20000 | 25%
4 | QAP |  | 1500 |  | 24000 | 50%
5 | KIEWIT PACIFIC CO. |  | 2000 |  | 32000 | 100%
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 1475000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 1400000 | -5.085%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 3222000 | 118.4%
3 | BRICE INC. |  |  |  | 1450000 | -1.695%
4 | QAP |  |  |  | 3020000 | 104.7%
5 | KIEWIT PACIFIC CO. |  |  |  | 1800000 | 22.03%
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 350000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 340000 | -2.857%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 455000 | 30%
3 | BRICE INC. |  |  |  | 1000000 | 185.7%
4 | QAP |  |  |  | 100000 | -71.43%
5 | KIEWIT PACIFIC CO. |  |  |  | 2000000 | 471.4%
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 40000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 40000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 105000 | 162.5%
3 | BRICE INC. |  |  |  | 50000 | 25%
4 | QAP |  |  |  | 95000 | 137.5%
5 | KIEWIT PACIFIC CO. |  |  |  | 40000 | 0%
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 30000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 20000 | -33.33%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 45000 | 50%
3 | BRICE INC. |  |  |  | 24000 | -20%
4 | QAP |  |  |  | 20000 | -33.33%
5 | KIEWIT PACIFIC CO. |  |  |  | 10000 | -66.67%
G-130g | Nuclear Testing Equipment Storage Shed | Each | 7500 | 1 | 7500
1 | PHILLIPS & JORDAN, INC. |  | 7000 |  | 7000 | -6.667%
2 | KNIK CONSTRUCTION CO., INC. |  | 15000 |  | 15000 | 100%
3 | BRICE INC. |  | 1500 |  | 1500 | -80%
4 | QAP |  | 3000 |  | 3000 | -60%
5 | KIEWIT PACIFIC CO. |  | 5000 |  | 5000 | -33.33%
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 5000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 5000 | 0%
3 | BRICE INC. |  |  |  | 5000 | 0%
4 | QAP |  |  |  | 5000 | 0%
5 | KIEWIT PACIFIC CO. |  |  |  | 5000 | 0%
G-131a | Engineering Transportation (Truck) | Each | 25000 | 1 | 25000
1 | PHILLIPS & JORDAN, INC. |  | 25000 |  | 25000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  | 85000 |  | 85000 | 240%
3 | BRICE INC. |  | 35000 |  | 35000 | 40%
4 | QAP |  | 30000 |  | 30000 | 20%
5 | KIEWIT PACIFIC CO. |  | 27500 |  | 27500 | 10%
G-131b | Engineering Transportation (ATV) | Each | 15000 | 1 | 15000
1 | PHILLIPS & JORDAN, INC. |  | 14000 |  | 14000 | -6.667%
2 | KNIK CONSTRUCTION CO., INC. |  | 18000 |  | 18000 | 20%
3 | BRICE INC. |  | 5000 |  | 5000 | -66.67%
4 | QAP |  | 15000 |  | 15000 | 0%
5 | KIEWIT PACIFIC CO. |  | 21000 |  | 21000 | 40%
G-131c | Engineering Transportation (Snowmachine) | Each | 15000 | 1 | 15000
1 | PHILLIPS & JORDAN, INC. |  | 14000 |  | 14000 | -6.667%
2 | KNIK CONSTRUCTION CO., INC. |  | 25000 |  | 25000 | 66.67%
3 | BRICE INC. |  | 10000 |  | 10000 | -33.33%
4 | QAP |  | 15000 |  | 15000 | 0%
5 | KIEWIT PACIFIC CO. |  | 21000 |  | 21000 | 40%
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 100000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 170000 | 70%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 95000 | -5%
3 | BRICE INC. |  |  |  | 65000 | -35%
4 | QAP |  |  |  | 115000 | 15%
5 | KIEWIT PACIFIC CO. |  |  |  | 225000 | 125%
G-135b | Extra Three Person Survey Party | Hour | 250 | 50 | 12500
1 | PHILLIPS & JORDAN, INC. |  | 320 |  | 16000 | 28%
2 | KNIK CONSTRUCTION CO., INC. |  | 275 |  | 13750 | 10%
3 | BRICE INC. |  | 300 |  | 15000 | 20%
4 | QAP |  | 300 |  | 15000 | 20%
5 | KIEWIT PACIFIC CO. |  | 270 |  | 13500 | 8%
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 210 | 50 | 10500
1 | PHILLIPS & JORDAN, INC. |  | 150 |  | 7500 | -28.57%
2 | KNIK CONSTRUCTION CO., INC. |  | 195 |  | 9750 | -7.143%
3 | BRICE INC. |  | 300 |  | 15000 | 42.86%
4 | QAP |  | 160 |  | 8000 | -23.81%
5 | KIEWIT PACIFIC CO. |  | 135 |  | 6750 | -35.71%
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 25000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 20000 | -20%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 80000 | 220%
3 | BRICE INC. |  |  |  | 25000 | 0%
4 | QAP |  |  |  | 65000 | 160%
5 | KIEWIT PACIFIC CO. |  |  |  | 29000 | 16%
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 40000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 40000 | 0%
3 | BRICE INC. |  |  |  | 40000 | 0%
4 | QAP |  |  |  | 40000 | 0%
5 | KIEWIT PACIFIC CO. |  |  |  | 40000 | 0%
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
1 | PHILLIPS & JORDAN, INC. |  |  |  | 0
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 0
3 | BRICE INC. |  |  |  | 0
4 | QAP |  |  |  | 0
5 | KIEWIT PACIFIC CO. |  |  |  | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 25000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 25000 | 0%
3 | BRICE INC. |  |  |  | 25000 | 0%
4 | QAP |  |  |  | 25000 | 0%
5 | KIEWIT PACIFIC CO. |  |  |  | 25000 | 0%
L-100b | Regulator, L-828 | Each | 12000 | 1 | 12000
1 | PHILLIPS & JORDAN, INC. |  | 19000 |  | 19000 | 58.33%
2 | KNIK CONSTRUCTION CO., INC. |  | 14000 |  | 14000 | 16.67%
3 | BRICE INC. |  | 16000 |  | 16000 | 33.33%
4 | QAP |  | 9000 |  | 9000 | -25%
5 | KIEWIT PACIFIC CO. |  | 8300 |  | 8300 | -30.83%
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1100 | 48 | 52800
1 | PHILLIPS & JORDAN, INC. |  | 1500 |  | 72000 | 36.36%
2 | KNIK CONSTRUCTION CO., INC. |  | 1650 |  | 79200 | 50%
3 | BRICE INC. |  | 1860 |  | 89280 | 69.09%
4 | QAP |  | 1400 |  | 67200 | 27.27%
5 | KIEWIT PACIFIC CO. |  | 1400 |  | 67200 | 27.27%
L-100e | Taxiway Edge Light, L-861T | Each | 1300 | 26 | 33800
1 | PHILLIPS & JORDAN, INC. |  | 1500 |  | 39000 | 15.38%
2 | KNIK CONSTRUCTION CO., INC. |  | 1650 |  | 42900 | 26.92%
3 | BRICE INC. |  | 1860 |  | 48360 | 43.08%
4 | QAP |  | 1300 |  | 33800 | 0%
5 | KIEWIT PACIFIC CO. |  | 1400 |  | 36400 | 7.692%
L-100p | Handhole, L-867, Size B | Each | 800 | 8 | 6400
1 | PHILLIPS & JORDAN, INC. |  | 1200 |  | 9600 | 50%
2 | KNIK CONSTRUCTION CO., INC. |  | 1100 |  | 8800 | 37.5%
3 | BRICE INC. |  | 1250 |  | 10000 | 56.25%
4 | QAP |  | 700 |  | 5600 | -12.5%
5 | KIEWIT PACIFIC CO. |  | 600 |  | 4800 | -25%
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 12000 | 1 | 12000
1 | PHILLIPS & JORDAN, INC. |  | 14000 |  | 14000 | 16.67%
2 | KNIK CONSTRUCTION CO., INC. |  | 13000 |  | 13000 | 8.333%
3 | BRICE INC. |  | 14650 |  | 14650 | 22.08%
4 | QAP |  | 9000 |  | 9000 | -25%
5 | KIEWIT PACIFIC CO. |  | 10000 |  | 10000 | -16.67%
L-107a | 8-foot Lighted Wind Cone, in place | Each | 15000 | 1 | 15000
1 | PHILLIPS & JORDAN, INC. |  | 14500 |  | 14500 | -3.333%
2 | KNIK CONSTRUCTION CO., INC. |  | 13000 |  | 13000 | -13.33%
3 | BRICE INC. |  | 14650 |  | 14650 | -2.333%
4 | QAP |  | 9000 |  | 9000 | -40%
5 | KIEWIT PACIFIC CO. |  | 15000 |  | 15000 | 0%
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 10000 | 1 | 10000
1 | PHILLIPS & JORDAN, INC. |  | 12000 |  | 12000 | 20%
2 | KNIK CONSTRUCTION CO., INC. |  | 8000 |  | 8000 | -20%
3 | BRICE INC. |  | 9000 |  | 9000 | -10%
4 | QAP |  | 5000 |  | 5000 | -50%
5 | KIEWIT PACIFIC CO. |  | 6000 |  | 6000 | -40%
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 23250
1 | PHILLIPS & JORDAN, INC. |  |  |  | 22000 | -5.376%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 36000 | 54.84%
3 | BRICE INC. |  |  |  | 41000 | 76.34%
4 | QAP |  |  |  | 30000 | 29.03%
5 | KIEWIT PACIFIC CO. |  |  |  | 18000 | -22.58%
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 12900
1 | PHILLIPS & JORDAN, INC. |  |  |  | 20000 | 55.04%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 22000 | 70.54%
3 | BRICE INC. |  |  |  | 25000 | 93.8%
4 | QAP |  |  |  | 18000 | 39.53%
5 | KIEWIT PACIFIC CO. |  |  |  | 12000 | -6.977%
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 3500
1 | PHILLIPS & JORDAN, INC. |  |  |  | 6000 | 71.43%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 8000 | 128.6%
3 | BRICE INC. |  |  |  | 9000 | 157.1%
4 | QAP |  |  |  | 1500 | -57.14%
5 | KIEWIT PACIFIC CO. |  |  |  | 10000 | 185.7%
L-108g | Ground Rod | Each | 300 | 10 | 3000
1 | PHILLIPS & JORDAN, INC. |  | 390 |  | 3900 | 30%
2 | KNIK CONSTRUCTION CO., INC. |  | 350 |  | 3500 | 16.67%
3 | BRICE INC. |  | 400 |  | 4000 | 33.33%
4 | QAP |  | 250 |  | 2500 | -16.67%
5 | KIEWIT PACIFIC CO. |  | 300 |  | 3000 | 0%
L-109c | Electrical Enclosure and Foundation, In Place | Each | 30000 | 1 | 30000
1 | PHILLIPS & JORDAN, INC. |  | 36000 |  | 36000 | 20%
2 | KNIK CONSTRUCTION CO., INC. |  | 33000 |  | 33000 | 10%
3 | BRICE INC. |  | 37000 |  | 37000 | 23.33%
4 | QAP |  | 21000 |  | 21000 | -30%
5 | KIEWIT PACIFIC CO. |  | 25000 |  | 25000 | -16.67%
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 35000 | 1 | 35000
1 | PHILLIPS & JORDAN, INC. |  | 34000 |  | 34000 | -2.857%
2 | KNIK CONSTRUCTION CO., INC. |  | 30000 |  | 30000 | -14.29%
3 | BRICE INC. |  | 35000 |  | 35000 | 0%
4 | QAP |  | 19000 |  | 19000 | -45.71%
5 | KIEWIT PACIFIC CO. |  | 20000 |  | 20000 | -42.86%
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 147000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 110000 | -25.17%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 95000 | -35.37%
3 | BRICE INC. |  |  |  | 104000 | -29.25%
4 | QAP |  |  |  | 76000 | -48.3%
5 | KIEWIT PACIFIC CO. |  |  |  | 150000 | 2.041%
P-151a | Clearing | Acre | 1500 | 143 | 214500
1 | PHILLIPS & JORDAN, INC. |  | 3800 |  | 543400 | 153.3%
2 | KNIK CONSTRUCTION CO., INC. |  | 4000 |  | 572000 | 166.7%
3 | BRICE INC. |  | 3000 |  | 429000 | 100%
4 | QAP |  | 2500 |  | 357500 | 66.67%
5 | KIEWIT PACIFIC CO. |  | 6000 |  | 858000 | 300%
P-152c | Muck Excavation | Cubic Yard | 10 | 10300 | 103000
1 | PHILLIPS & JORDAN, INC. |  | 13 |  | 133900 | 30%
2 | KNIK CONSTRUCTION CO., INC. |  | 15 |  | 154500 | 50%
3 | BRICE INC. |  | 18.75 |  | 193125 | 87.5%
4 | QAP |  | 10 |  | 103000 | 0%
5 | KIEWIT PACIFIC CO. |  | 25 |  | 257500 | 150%
P-152h(1) | Borrow Measured at Source | Cubic Yard | 17.5 | 466000 | 8155000
1 | PHILLIPS & JORDAN, INC. |  | 18 |  | 8388000 | 2.857%
2 | KNIK CONSTRUCTION CO., INC. |  | 20 |  | 9320000 | 14.29%
3 | BRICE INC. |  | 22.43 |  | 10452380 | 28.17%
4 | QAP |  | 21 |  | 9786000 | 20%
5 | KIEWIT PACIFIC CO. |  | 30 |  | 13980000 | 71.43%
P-152af | Settlement Platform | Each | 3000 | 6 | 18000
1 | PHILLIPS & JORDAN, INC. |  | 1800 |  | 10800 | -40%
2 | KNIK CONSTRUCTION CO., INC. |  | 3000 |  | 18000 | 0%
3 | BRICE INC. |  | 2300 |  | 13800 | -23.33%
4 | QAP |  | 4000 |  | 24000 | 33.33%
5 | KIEWIT PACIFIC CO. |  | 1500 |  | 9000 | -50%
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 10000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 25000 | 150%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 20000 | 100%
3 | BRICE INC. |  |  |  | 10000 | 0%
4 | QAP |  |  |  | 24000 | 140%
5 | KIEWIT PACIFIC CO. |  |  |  | 5000 | -50%
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 120000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 120000 | 0%
3 | BRICE INC. |  |  |  | 120000 | 0%
4 | QAP |  |  |  | 120000 | 0%
5 | KIEWIT PACIFIC CO. |  |  |  | 120000 | 0%
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
1 | PHILLIPS & JORDAN, INC. |  |  |  | 0
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 0
3 | BRICE INC. |  |  |  | 0
4 | QAP |  |  |  | 0
5 | KIEWIT PACIFIC CO. |  |  |  | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 25000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 15000 | -40%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 65000 | 160%
3 | BRICE INC. |  |  |  | 100000 | 300%
4 | QAP |  |  |  | 25000 | 0%
5 | KIEWIT PACIFIC CO. |  |  |  | 15000 | -40%
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 40000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 14000 | -65%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 40000 | 0%
3 | BRICE INC. |  |  |  | 5000 | -87.5%
4 | QAP |  |  |  | 25000 | -37.5%
5 | KIEWIT PACIFIC CO. |  |  |  | 10000 | -75%
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 135 | 23800 | 3213000
1 | PHILLIPS & JORDAN, INC. |  | 150 |  | 3570000 | 11.11%
2 | KNIK CONSTRUCTION CO., INC. |  | 90 |  | 2142000 | -33.33%
3 | BRICE INC. |  | 145 |  | 3451000 | 7.407%
4 | QAP |  | 150 |  | 3570000 | 11.11%
5 | KIEWIT PACIFIC CO. |  | 250 |  | 5950000 | 85.19%
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 135 | 100 | 13500
1 | PHILLIPS & JORDAN, INC. |  | 130 |  | 13000 | -3.704%
2 | KNIK CONSTRUCTION CO., INC. |  | 85 |  | 8500 | -37.04%
3 | BRICE INC. |  | 135 |  | 13500 | 0%
4 | QAP |  | 125 |  | 12500 | -7.407%
5 | KIEWIT PACIFIC CO. |  | 250 |  | 25000 | 85.19%
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 40000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 40000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 45000 | 12.5%
3 | BRICE INC. |  |  |  | 40000 | 0%
4 | QAP |  |  |  | 35000 | -12.5%
5 | KIEWIT PACIFIC CO. |  |  |  | 40000 | 0%
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 2000 | 3 | 6000
1 | PHILLIPS & JORDAN, INC. |  | 1600 |  | 4800 | -20%
2 | KNIK CONSTRUCTION CO., INC. |  | 1200 |  | 3600 | -40%
3 | BRICE INC. |  | 1000 |  | 3000 | -50%
4 | QAP |  | 1000 |  | 3000 | -50%
5 | KIEWIT PACIFIC CO. |  | 1000 |  | 3000 | -50%
P-660b | Reflective Marker, Type II | Each | 120 | 28 | 3360
1 | PHILLIPS & JORDAN, INC. |  | 110 |  | 3080 | -8.333%
2 | KNIK CONSTRUCTION CO., INC. |  | 145 |  | 4060 | 20.83%
3 | BRICE INC. |  | 125 |  | 3500 | 4.167%
4 | QAP |  | 100 |  | 2800 | -16.67%
5 | KIEWIT PACIFIC CO. |  | 125 |  | 3500 | 4.167%
P-660c | Cone, 18 inch | Each | 100 | 74 | 7400
1 | PHILLIPS & JORDAN, INC. |  | 50 |  | 3700 | -50%
2 | KNIK CONSTRUCTION CO., INC. |  | 60 |  | 4440 | -40%
3 | BRICE INC. |  | 50 |  | 3700 | -50%
4 | QAP |  | 50 |  | 3700 | -50%
5 | KIEWIT PACIFIC CO. |  | 60 |  | 4440 | -40%
P-661a | Standard Sign | Square Foot | 250 | 43.25 | 10812.5
1 | PHILLIPS & JORDAN, INC. |  | 156 |  | 6747 | -37.6%
2 | KNIK CONSTRUCTION CO., INC. |  | 200 |  | 8650 | -20%
3 | BRICE INC. |  | 200 |  | 8650 | -20%
4 | QAP |  | 200 |  | 8650 | -20%
5 | KIEWIT PACIFIC CO. |  | 75 |  | 3243.75 | -70%
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 4000 | 2 | 8000
1 | PHILLIPS & JORDAN, INC. |  | 2600 |  | 5200 | -35%
2 | KNIK CONSTRUCTION CO., INC. |  | 6000 |  | 12000 | 50%
3 | BRICE INC. |  | 5000 |  | 10000 | 25%
4 | QAP |  | 6500 |  | 13000 | 62.5%
5 | KIEWIT PACIFIC CO. |  | 3000 |  | 6000 | -25%
P-681b | Geotextile, Stabilization | Square Yard | 2.5 | 326600 | 816500
1 | PHILLIPS & JORDAN, INC. |  | 2.3 |  | 751180 | -8%
2 | KNIK CONSTRUCTION CO., INC. |  | 2.75 |  | 898150 | 10%
3 | BRICE INC. |  | 1.65 |  | 538890 | -34%
4 | QAP |  | 2 |  | 653200 | -20%
5 | KIEWIT PACIFIC CO. |  | 4 |  | 1306400 | 60%
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 250000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 200000 | -20%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 400000 | 60%
3 | BRICE INC. |  |  |  | 875000 | 250%
4 | QAP |  |  |  | 3100000 | 1140%
5 | KIEWIT PACIFIC CO. |  |  |  | 2000000 | 700%
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 665000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 860000 | 29.32%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 765000 | 15.04%
3 | BRICE INC. |  |  |  | 800000 | 20.3%
4 | QAP |  |  |  | 715000 | 7.519%
5 | KIEWIT PACIFIC CO. |  |  |  | 825000 | 24.06%
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 625000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 670000 | 7.2%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 725000 | 16%
3 | BRICE INC. |  |  |  | 750000 | 20%
4 | QAP |  |  |  | 655000 | 4.8%
5 | KIEWIT PACIFIC CO. |  |  |  | 750000 | 20%
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 20000 | 1 | 20000
1 | PHILLIPS & JORDAN, INC. |  | 20000 |  | 20000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  | 22000 |  | 22000 | 10%
3 | BRICE INC. |  | 22600 |  | 22600 | 13%
4 | QAP |  | 20000 |  | 20000 | 0%
5 | KIEWIT PACIFIC CO. |  | 15000 |  | 15000 | -25%
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 10000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 5500 | -45%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 11000 | 10%
3 | BRICE INC. |  |  |  | 5200 | -48%
4 | QAP |  |  |  | 5000 | -50%
5 | KIEWIT PACIFIC CO. |  |  |  | 12000 | 20%
S-143d | Electric Dispensing System | Each | 15000 | 1 | 15000
1 | PHILLIPS & JORDAN, INC. |  | 3500 |  | 3500 | -76.67%
2 | KNIK CONSTRUCTION CO., INC. |  | 9000 |  | 9000 | -40%
3 | BRICE INC. |  | 9300 |  | 9300 | -38%
4 | QAP |  | 8500 |  | 8500 | -43.33%
5 | KIEWIT PACIFIC CO. |  | 3500 |  | 3500 | -76.67%
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 20000 | 1 | 20000
1 | PHILLIPS & JORDAN, INC. |  | 20000 |  | 20000 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  | 25000 |  | 25000 | 25%
3 | BRICE INC. |  | 26000 |  | 26000 | 30%
4 | QAP |  | 23000 |  | 23000 | 15%
5 | KIEWIT PACIFIC CO. |  | 15000 |  | 15000 | -25%
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 5000
1 | PHILLIPS & JORDAN, INC. |  |  |  | 4000 | -20%
2 | KNIK CONSTRUCTION CO., INC. |  |  |  | 10000 | 100%
3 | BRICE INC. |  |  |  | 7500 | 50%
4 | QAP |  |  |  | 9000 | 80%
5 | KIEWIT PACIFIC CO. |  |  |  | 5000 | 0%
T-901a | Seeding | Acre | 3000 | 22 | 66000
1 | PHILLIPS & JORDAN, INC. |  | 1700 |  | 37400 | -43.33%
2 | KNIK CONSTRUCTION CO., INC. |  | 3000 |  | 66000 | 0%
3 | BRICE INC. |  | 3100 |  | 68200 | 3.333%
4 | QAP |  | 3000 |  | 66000 | 0%
5 | KIEWIT PACIFIC CO. |  | 3500 |  | 77000 | 16.67%
T-901c | Water for Maintenance | M-Gal | 50 | 1650 | 82500
1 | PHILLIPS & JORDAN, INC. |  | 22 |  | 36300 | -56%
2 | KNIK CONSTRUCTION CO., INC. |  | 45 |  | 74250 | -10%
3 | BRICE INC. |  | 55 |  | 90750 | 10%
4 | QAP |  | 30 |  | 49500 | -40%
5 | KIEWIT PACIFIC CO. |  | 150 |  | 247500 | 200%
T-905b | Organic Material | Cubic Yard | 10 | 9600 | 96000
1 | PHILLIPS & JORDAN, INC. |  | 20 |  | 192000 | 100%
2 | KNIK CONSTRUCTION CO., INC. |  | 15 |  | 144000 | 50%
3 | BRICE INC. |  | 8.5 |  | 81600 | -15%
4 | QAP |  | 7.5 |  | 72000 | -25%
5 | KIEWIT PACIFIC CO. |  | 35 |  | 336000 | 250%
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1.5 | 178300 | 267450
1 | PHILLIPS & JORDAN, INC. |  | 1.5 |  | 267450 | 0%
2 | KNIK CONSTRUCTION CO., INC. |  | 1 |  | 178300 | -33.33%
3 | BRICE INC. |  | 1.25 |  | 222875 | -16.67%
4 | QAP |  | 1.25 |  | 222875 | -16.67%
5 | KIEWIT PACIFIC CO. |  | 2.5 |  | 445750 | 66.67%

## PHILLIPS & JORDAN, INC.
Bid Rank: 1 |  | PHILLIPS & JORDAN, INC.
Akiachak Airport Relocation |  | 25809 BUSINESS CENTER DRIVE, SUITE A
3-02-0461-001-2009 /59011 |  | REDLANDS, CA 92374
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 150 | 402 | 60300
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 200 | 672 | 134400
F-162a | 8' Chain-Link Fence | Linear Foot | 90 | 106 | 9540
F-162d | 4' Single Cantilever Gate | Each | 1800 | 2 | 3600
F-170a | Steel Bollard | Each | 1100 | 16 | 17600
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 1400000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 340000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 40000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 20000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 7000 | 1 | 7000
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 25000 | 1 | 25000
G-131b | Engineering Transportation (ATV) | Each | 14000 | 1 | 14000
G-131c | Engineering Transportation (Snowmachine) | Each | 14000 | 1 | 14000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 170000
G-135b | Extra Three Person Survey Party | Hour | 320 | 50 | 16000
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 150 | 50 | 7500
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 20000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 19000 | 1 | 19000
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1500 | 48 | 72000
L-100e | Taxiway Edge Light, L-861T | Each | 1500 | 26 | 39000
L-100p | Handhole, L-867, Size B | Each | 1200 | 8 | 9600
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 14000 | 1 | 14000
L-107a | 8-foot Lighted Wind Cone, in place | Each | 14500 | 1 | 14500
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 12000 | 1 | 12000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 22000
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 20000
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 6000
L-108g | Ground Rod | Each | 390 | 10 | 3900
L-109c | Electrical Enclosure and Foundation, In Place | Each | 36000 | 1 | 36000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 34000 | 1 | 34000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 110000
P-151a | Clearing | Acre | 3800 | 143 | 543400
P-152c | Muck Excavation | Cubic Yard | 13 | 10300 | 133900
P-152h(1) | Borrow Measured at Source | Cubic Yard | 18 | 466000 | 8388000
P-152af | Settlement Platform | Each | 1800 | 6 | 10800
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 25000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 15000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 14000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 150 | 23800 | 3570000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 130 | 100 | 13000
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 40000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 1600 | 3 | 4800
P-660b | Reflective Marker, Type II | Each | 110 | 28 | 3080
P-660c | Cone, 18 inch | Each | 50 | 74 | 3700
P-661a | Standard Sign | Square Foot | 156 | 43.25 | 6747
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 2600 | 2 | 5200
P-681b | Geotextile, Stabilization | Square Yard | 2.3 | 326600 | 751180
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 200000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 860000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 670000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 20000 | 1 | 20000
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 5500
S-143d | Electric Dispensing System | Each | 3500 | 1 | 3500
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 20000 | 1 | 20000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 4000
T-901a | Seeding | Acre | 1700 | 22 | 37400
T-901c | Water for Maintenance | M-Gal | 22 | 1650 | 36300
T-905b | Organic Material | Cubic Yard | 20 | 9600 | 192000
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1.5 | 178300 | 267450

## KNIK CONSTRUCTION CO., INC.
Bid Rank: 2 |  | KNIK CONSTRUCTION CO., INC.
Akiachak Airport Relocation |  | 6441 SOUTH AIRPARK PLACE
3-02-0461-001-2009 /59011 |  | ANCHORAGE, AK 99502
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 150 | 402 | 60300
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 240 | 672 | 161280
F-162a | 8' Chain-Link Fence | Linear Foot | 165 | 106 | 17490
F-162d | 4' Single Cantilever Gate | Each | 2000 | 2 | 4000
F-170a | Steel Bollard | Each | 1400 | 16 | 22400
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 3222000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 455000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 105000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 45000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 15000 | 1 | 15000
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 85000 | 1 | 85000
G-131b | Engineering Transportation (ATV) | Each | 18000 | 1 | 18000
G-131c | Engineering Transportation (Snowmachine) | Each | 25000 | 1 | 25000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 95000
G-135b | Extra Three Person Survey Party | Hour | 275 | 50 | 13750
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 195 | 50 | 9750
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 80000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 14000 | 1 | 14000
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1650 | 48 | 79200
L-100e | Taxiway Edge Light, L-861T | Each | 1650 | 26 | 42900
L-100p | Handhole, L-867, Size B | Each | 1100 | 8 | 8800
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 13000 | 1 | 13000
L-107a | 8-foot Lighted Wind Cone, in place | Each | 13000 | 1 | 13000
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 8000 | 1 | 8000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 36000
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 22000
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 8000
L-108g | Ground Rod | Each | 350 | 10 | 3500
L-109c | Electrical Enclosure and Foundation, In Place | Each | 33000 | 1 | 33000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 30000 | 1 | 30000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 95000
P-151a | Clearing | Acre | 4000 | 143 | 572000
P-152c | Muck Excavation | Cubic Yard | 15 | 10300 | 154500
P-152h(1) | Borrow Measured at Source | Cubic Yard | 20 | 466000 | 9320000
P-152af | Settlement Platform | Each | 3000 | 6 | 18000
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 20000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 65000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 40000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 90 | 23800 | 2142000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 85 | 100 | 8500
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 45000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 1200 | 3 | 3600
P-660b | Reflective Marker, Type II | Each | 145 | 28 | 4060
P-660c | Cone, 18 inch | Each | 60 | 74 | 4440
P-661a | Standard Sign | Square Foot | 200 | 43.25 | 8650
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 6000 | 2 | 12000
P-681b | Geotextile, Stabilization | Square Yard | 2.75 | 326600 | 898150
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 400000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 765000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 725000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 22000 | 1 | 22000
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 11000
S-143d | Electric Dispensing System | Each | 9000 | 1 | 9000
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 25000 | 1 | 25000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 10000
T-901a | Seeding | Acre | 3000 | 22 | 66000
T-901c | Water for Maintenance | M-Gal | 45 | 1650 | 74250
T-905b | Organic Material | Cubic Yard | 15 | 9600 | 144000
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1 | 178300 | 178300

## BRICE INC.
Bid Rank: 3 |  | BRICE INC.
Akiachak Airport Relocation |  | P.O. BOX 70668
3-02-0461-001-2009 /59011 |  | FAIRBANKS, AK 99707
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 200 | 402 | 80400
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 250 | 672 | 168000
F-162a | 8' Chain-Link Fence | Linear Foot | 150 | 106 | 15900
F-162d | 4' Single Cantilever Gate | Each | 1500 | 2 | 3000
F-170a | Steel Bollard | Each | 1250 | 16 | 20000
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 1450000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 1000000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 50000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 24000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 1500 | 1 | 1500
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 35000 | 1 | 35000
G-131b | Engineering Transportation (ATV) | Each | 5000 | 1 | 5000
G-131c | Engineering Transportation (Snowmachine) | Each | 10000 | 1 | 10000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 65000
G-135b | Extra Three Person Survey Party | Hour | 300 | 50 | 15000
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 300 | 50 | 15000
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 25000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 16000 | 1 | 16000
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1860 | 48 | 89280
L-100e | Taxiway Edge Light, L-861T | Each | 1860 | 26 | 48360
L-100p | Handhole, L-867, Size B | Each | 1250 | 8 | 10000
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 14650 | 1 | 14650
L-107a | 8-foot Lighted Wind Cone, in place | Each | 14650 | 1 | 14650
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 9000 | 1 | 9000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 41000
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 25000
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 9000
L-108g | Ground Rod | Each | 400 | 10 | 4000
L-109c | Electrical Enclosure and Foundation, In Place | Each | 37000 | 1 | 37000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 35000 | 1 | 35000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 104000
P-151a | Clearing | Acre | 3000 | 143 | 429000
P-152c | Muck Excavation | Cubic Yard | 18.75 | 10300 | 193125
P-152h(1) | Borrow Measured at Source | Cubic Yard | 22.43 | 466000 | 10452380
P-152af | Settlement Platform | Each | 2300 | 6 | 13800
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 10000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 100000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 5000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 145 | 23800 | 3451000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 135 | 100 | 13500
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 40000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 1000 | 3 | 3000
P-660b | Reflective Marker, Type II | Each | 125 | 28 | 3500
P-660c | Cone, 18 inch | Each | 50 | 74 | 3700
P-661a | Standard Sign | Square Foot | 200 | 43.25 | 8650
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 5000 | 2 | 10000
P-681b | Geotextile, Stabilization | Square Yard | 1.65 | 326600 | 538890
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 875000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 800000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 750000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 22600 | 1 | 22600
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 5200
S-143d | Electric Dispensing System | Each | 9300 | 1 | 9300
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 26000 | 1 | 26000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 7500
T-901a | Seeding | Acre | 3100 | 22 | 68200
T-901c | Water for Maintenance | M-Gal | 55 | 1650 | 90750
T-905b | Organic Material | Cubic Yard | 8.5 | 9600 | 81600
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1.25 | 178300 | 222875

## QAP
Bid Rank: 4 |  | QAP
Akiachak Airport Relocation |  | 240 W. 68TH AVE.
3-02-0461-001-2009 /59011 |  | ANCHORAGE, AK 99518
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 200 | 402 | 80400
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 250 | 672 | 168000
F-162a | 8' Chain-Link Fence | Linear Foot | 200 | 106 | 21200
F-162d | 4' Single Cantilever Gate | Each | 2000 | 2 | 4000
F-170a | Steel Bollard | Each | 1500 | 16 | 24000
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 3020000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 100000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 95000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 20000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 3000 | 1 | 3000
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 30000 | 1 | 30000
G-131b | Engineering Transportation (ATV) | Each | 15000 | 1 | 15000
G-131c | Engineering Transportation (Snowmachine) | Each | 15000 | 1 | 15000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 115000
G-135b | Extra Three Person Survey Party | Hour | 300 | 50 | 15000
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 160 | 50 | 8000
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 65000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 9000 | 1 | 9000
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1400 | 48 | 67200
L-100e | Taxiway Edge Light, L-861T | Each | 1300 | 26 | 33800
L-100p | Handhole, L-867, Size B | Each | 700 | 8 | 5600
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 9000 | 1 | 9000
L-107a | 8-foot Lighted Wind Cone, in place | Each | 9000 | 1 | 9000
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 5000 | 1 | 5000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 30000
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 18000
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 1500
L-108g | Ground Rod | Each | 250 | 10 | 2500
L-109c | Electrical Enclosure and Foundation, In Place | Each | 21000 | 1 | 21000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 19000 | 1 | 19000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 76000
P-151a | Clearing | Acre | 2500 | 143 | 357500
P-152c | Muck Excavation | Cubic Yard | 10 | 10300 | 103000
P-152h(1) | Borrow Measured at Source | Cubic Yard | 21 | 466000 | 9786000
P-152af | Settlement Platform | Each | 4000 | 6 | 24000
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 24000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 25000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 25000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 150 | 23800 | 3570000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 125 | 100 | 12500
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 35000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 1000 | 3 | 3000
P-660b | Reflective Marker, Type II | Each | 100 | 28 | 2800
P-660c | Cone, 18 inch | Each | 50 | 74 | 3700
P-661a | Standard Sign | Square Foot | 200 | 43.25 | 8650
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 6500 | 2 | 13000
P-681b | Geotextile, Stabilization | Square Yard | 2 | 326600 | 653200
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 3100000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 715000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 655000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 20000 | 1 | 20000
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 5000
S-143d | Electric Dispensing System | Each | 8500 | 1 | 8500
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 23000 | 1 | 23000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 9000
T-901a | Seeding | Acre | 3000 | 22 | 66000
T-901c | Water for Maintenance | M-Gal | 30 | 1650 | 49500
T-905b | Organic Material | Cubic Yard | 7.5 | 9600 | 72000
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 1.25 | 178300 | 222875

## KIEWIT PACIFIC CO.
Bid Rank: 5 |  | KIEWIT PACIFIC CO.
Akiachak Airport Relocation |  | P.O. BOX 1769
3-02-0461-001-2009 /59011 |  | VANCOUVER, WA 98668
Bids Opened: 5/22/2009
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
D-701a(1) | CPE Pipe, 24 inch | Linear Foot | 200 | 402 | 80400
D-701a(2) | CPE Pipe, 36 inch | Linear Foot | 250 | 672 | 168000
F-162a | 8' Chain-Link Fence | Linear Foot | 350 | 106 | 37100
F-162d | 4' Single Cantilever Gate | Each | 10000 | 2 | 20000
F-170a | Steel Bollard | Each | 2000 | 16 | 32000
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 1800000
G-115a | Worker Meals and Lodging, or Per Diem | Lump Sum | All Req'd | All Req'd | 2000000
G-130a | Field Office | Lump Sum | All Req'd | All Req'd | 40000
G-130b | Field Laboratory | Lump Sum | All Req'd | All Req'd | 10000
G-130g | Nuclear Testing Equipment Storage Shed | Each | 5000 | 1 | 5000
G-130j | Engineering Communications | Contingent Sum | All Req'd | All Req'd | 5000
G-131a | Engineering Transportation (Truck) | Each | 27500 | 1 | 27500
G-131b | Engineering Transportation (ATV) | Each | 21000 | 1 | 21000
G-131c | Engineering Transportation (Snowmachine) | Each | 21000 | 1 | 21000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 225000
G-135b | Extra Three Person Survey Party | Hour | 270 | 50 | 13500
G-150a | Equipment Rental, Dozer (Minimum 70 HP) | Hour | 135 | 50 | 6750
G-710a | Highway Traffic Maintenance | Lump Sum | All Req'd | All Req'd | 29000
G-710b | Highway Flagger | Contingent Sum | All Req'd | All Req'd | 40000
G-710c | Highway Traffic Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
G-710d | Highway Traffic Control | Contingent Sum | All Req'd | All Req'd | 25000
L-100b | Regulator, L-828 | Each | 8300 | 1 | 8300
L-100d | Medium Intensity Runway Edge and Threshold Light, L-861 and L-861E | Each | 1400 | 48 | 67200
L-100e | Taxiway Edge Light, L-861T | Each | 1400 | 26 | 36400
L-100p | Handhole, L-867, Size B | Each | 600 | 8 | 4800
L-101b | Rotating Beacon, Medium Intensity, L-801A | Each | 10000 | 1 | 10000
L-107a | 8-foot Lighted Wind Cone, in place | Each | 15000 | 1 | 15000
L-107c | 8-foot Unlighted Wind Cone, in place | Each | 6000 | 1 | 6000
L-108b | Underground Cable #8 AWG, Copper, 5kV FAA Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 18000
L-108d | #6 Bare Copper Ground Conductor | Lump Sum | All Req'd | All Req'd | 12000
L-108f | Underground Cable #10 AWG, Copper, 600V, Type "C", L-824 | Lump Sum | All Req'd | All Req'd | 10000
L-108g | Ground Rod | Each | 300 | 10 | 3000
L-109c | Electrical Enclosure and Foundation, In Place | Each | 25000 | 1 | 25000
L-109d | Installation of Electrical Equipment in New or Existing Structure | Each | 20000 | 1 | 20000
L-110h | 2 Inch PE Conduit | Lump Sum | All Req'd | All Req'd | 150000
P-151a | Clearing | Acre | 6000 | 143 | 858000
P-152c | Muck Excavation | Cubic Yard | 25 | 10300 | 257500
P-152h(1) | Borrow Measured at Source | Cubic Yard | 30 | 466000 | 13980000
P-152af | Settlement Platform | Each | 1500 | 6 | 9000
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 5000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 120000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 15000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 10000
P-208a | Crushed Aggregate Surface Course | Cubic Yard | 250 | 23800 | 5950000
P-208e* | Crushed Aggregate Surface Course Stockpile | Cubic Yard | 250 | 100 | 25000
P-640b | Segmented Circle (Panel-Type) | Lump Sum | All Req'd | All Req'd | 40000
P-650a | Soil Anchor Tie-down, Buried Plate | Set | 1000 | 3 | 3000
P-660b | Reflective Marker, Type II | Each | 125 | 28 | 3500
P-660c | Cone, 18 inch | Each | 60 | 74 | 4440
P-661a | Standard Sign | Square Foot | 75 | 43.25 | 3243.75
P-671a | Runway Closure Marker, Vinyl Mesh Panel | Each | 3000 | 2 | 6000
P-681b | Geotextile, Stabilization | Square Yard | 4 | 326600 | 1306400
P-700a | Ice Road | Lump Sum | All Req'd | All Req'd | 2000000
S-142p(1) | Equipment Storage Building No. 1, Heated | Lump Sum | All Req'd | All Req'd | 825000
S-142p(2) | Equipment Storage Building No. 2, Unheated | Lump Sum | All Req'd | All Req'd | 750000
S-143a | Heating Fuel Tank (1,000 gallons) | Each | 15000 | 1 | 15000
S-143b | Fuel | Lump Sum | All Req'd | All Req'd | 12000
S-143d | Electric Dispensing System | Each | 3500 | 1 | 3500
S-143e | Motor Vehicle Fuel-dispensing Tank (1,000 gallons) | Each | 15000 | 1 | 15000
S-143f | Spill Prevention Control and Countermeasure Plan | Lump Sum | All Req'd | All Req'd | 5000
T-901a | Seeding | Acre | 3500 | 22 | 77000
T-901c | Water for Maintenance | M-Gal | 150 | 1650 | 247500
T-905b | Organic Material | Cubic Yard | 35 | 9600 | 336000
T-908i | Bonded Fiber Matrix (BFM) | Square Yard | 2.5 | 178300 | 445750