## Engineers Estimate
ENGINEER'S ESTIMATE
Lake Hood Seaplane Base Lake Hood Bank Stabilization
AIP 3-02-0013-014-2010 /50920
Last Modified: 9/14/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 12 | 37200 | 446400
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 120000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 100000
G-135b | Extra Three Person Survey Party | Hour | 300 | 60 | 18000
G-150a | Equipment Rental, Forklift | Hour | 300 | 400 | 120000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 8000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 40 | 700 | 28000
L-160c | Load Center, Type 2 | Each | 3000 | 17 | 51000
P-151e | Selective Tree Removal | Each | 300 | 21 | 6300
P-152a | Unclassified Excavation | Cubic Yard | 10 | 1500 | 15000
P-152i | Borrow | Ton | 7 | 18400 | 128800
P-152ae | Rock Lining | Ton | 35 | 680 | 23800
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 20000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 30000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 80000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 26 | 10300 | 267800
P-209b | Crushed Aggregate Base Course | Ton | 45 | 1200 | 54000
P-650a | Soil Anchor Tie-down, Screw | Set | 1000 | 59 | 59000
P-681a | Geotextile, Separation | Square Yard | 3 | 13400 | 40200
P-684a | Floating Silt Curtain | Linear Foot | 100 | 825 | 82500
P-685a | Geogrid, Type 1 | Square Yard | 4.5 | 1750 | 7875
P-685b | Geocell, 6-Inch | Square Yard | 40 | 1770 | 70800
T-901b | Seeding | Pound | 300 | 120 | 36000
T-901c | Water for Maintenance | M-gal | 40 | 700 | 28000
T-903b | Sprigging | Square Yard | 70 | 1850 | 129500
T-905a | Topsoiling | Square Yard | 3.5 | 11750 | 41125

## Bid Comparison
Bid Comparison
Lake Hood Seaplane Base Lake Hood Bank Stabilization
AIP 3-02-0013-014-2010 /50920
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount | (+/-)%
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 12 | 37200 | 446400
1 | GRANITE CONSTRUCTION COMPANY |  | 15 |  | 558000 | 25%
2 | RENEGADE EQUIPMENT, LLC. |  | 11.9 |  | 442680 | -0.8333%
3 | FRAWNER CORPORATION |  | 14 |  | 520800 | 16.67%
4 | ROGER HICKEL CONTRACTING, INC. |  | 10.6 |  | 394320 | -11.67%
5 | RIDGE CONTRACTING, INC. |  | 18 |  | 669600 | 50%
6 | SWALLING CONSTRUCTION CO., INC. |  | 20.85 |  | 775620 | 73.75%
7 | CONSTRUCTION UNLIMITED, INC. |  | 16 |  | 595200 | 33.33%
8 | QAP |  | 22 |  | 818400 | 83.33%
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 120000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 147000 | 22.5%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 90000 | -25%
3 | FRAWNER CORPORATION |  |  |  | 40000 | -66.67%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 515500 | 329.6%
5 | RIDGE CONTRACTING, INC. |  |  |  | 290000 | 141.7%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 115000 | -4.167%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 60000 | -50%
8 | QAP |  |  |  | 250000 | 108.3%
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 100000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 47000 | -53%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 66000 | -34%
3 | FRAWNER CORPORATION |  |  |  | 55000 | -45%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 46000 | -54%
5 | RIDGE CONTRACTING, INC. |  |  |  | 65000 | -35%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 60000 | -40%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 77000 | -23%
8 | QAP |  |  |  | 44175 | -55.83%
G-135b | Extra Three Person Survey Party | Hour | 300 | 60 | 18000
1 | GRANITE CONSTRUCTION COMPANY |  | 320 |  | 19200 | 6.667%
2 | RENEGADE EQUIPMENT, LLC. |  | 350 |  | 21000 | 16.67%
3 | FRAWNER CORPORATION |  | 325 |  | 19500 | 8.333%
4 | ROGER HICKEL CONTRACTING, INC. |  | 315 |  | 18900 | 5%
5 | RIDGE CONTRACTING, INC. |  | 330 |  | 19800 | 10%
6 | SWALLING CONSTRUCTION CO., INC. |  | 385 |  | 23100 | 28.33%
7 | CONSTRUCTION UNLIMITED, INC. |  | 330 |  | 19800 | 10%
8 | QAP |  | 300 |  | 18000 | 0%
G-150a | Equipment Rental, Forklift | Hour | 300 | 400 | 120000
1 | GRANITE CONSTRUCTION COMPANY |  | 128 |  | 51200 | -57.33%
2 | RENEGADE EQUIPMENT, LLC. |  | 110 |  | 44000 | -63.33%
3 | FRAWNER CORPORATION |  | 100 |  | 40000 | -66.67%
4 | ROGER HICKEL CONTRACTING, INC. |  | 20 |  | 8000 | -93.33%
5 | RIDGE CONTRACTING, INC. |  | 92 |  | 36800 | -69.33%
6 | SWALLING CONSTRUCTION CO., INC. |  | 115 |  | 46000 | -61.67%
7 | CONSTRUCTION UNLIMITED, INC. |  | 150 |  | 60000 | -50%
8 | QAP |  | 250 |  | 100000 | -16.67%
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 8000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 800 | -90%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 4000 | -50%
3 | FRAWNER CORPORATION |  |  |  | 25000 | 212.5%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 57000 | 612.5%
5 | RIDGE CONTRACTING, INC. |  |  |  | 4500 | -43.75%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 9000 | 12.5%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 10000 | 25%
8 | QAP |  |  |  | 5000 | -37.5%
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 35000 | 0%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 35000 | 0%
3 | FRAWNER CORPORATION |  |  |  | 35000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 35000 | 0%
5 | RIDGE CONTRACTING, INC. |  |  |  | 35000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 35000 | 0%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 35000 | 0%
8 | QAP |  |  |  | 35000 | 0%
G-705a | Watering for Dust Control | M-gal | 40 | 700 | 28000
1 | GRANITE CONSTRUCTION COMPANY |  | 24 |  | 16800 | -40%
2 | RENEGADE EQUIPMENT, LLC. |  | 95 |  | 66500 | 137.5%
3 | FRAWNER CORPORATION |  | 50 |  | 35000 | 25%
4 | ROGER HICKEL CONTRACTING, INC. |  | 55 |  | 38500 | 37.5%
5 | RIDGE CONTRACTING, INC. |  | 88 |  | 61600 | 120%
6 | SWALLING CONSTRUCTION CO., INC. |  | 96 |  | 67200 | 140%
7 | CONSTRUCTION UNLIMITED, INC. |  | 28 |  | 19600 | -30%
8 | QAP |  | 60 |  | 42000 | 50%
L-160c | Load Center, Type 2 | Each | 3000 | 17 | 51000
1 | GRANITE CONSTRUCTION COMPANY |  | 3200 |  | 54400 | 6.667%
2 | RENEGADE EQUIPMENT, LLC. |  | 7740 |  | 131580 | 158%
3 | FRAWNER CORPORATION |  | 4200 |  | 71400 | 40%
4 | ROGER HICKEL CONTRACTING, INC. |  | 3770 |  | 64090 | 25.67%
5 | RIDGE CONTRACTING, INC. |  | 3000 |  | 51000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  | 3800 |  | 64600 | 26.67%
7 | CONSTRUCTION UNLIMITED, INC. |  | 4000 |  | 68000 | 33.33%
8 | QAP |  | 3400 |  | 57800 | 13.33%
P-151e | Selective Tree Removal | Each | 300 | 21 | 6300
1 | GRANITE CONSTRUCTION COMPANY |  | 775 |  | 16275 | 158.3%
2 | RENEGADE EQUIPMENT, LLC. |  | 1200 |  | 25200 | 300%
3 | FRAWNER CORPORATION |  | 350 |  | 7350 | 16.67%
4 | ROGER HICKEL CONTRACTING, INC. |  | 580 |  | 12180 | 93.33%
5 | RIDGE CONTRACTING, INC. |  | 600 |  | 12600 | 100%
6 | SWALLING CONSTRUCTION CO., INC. |  | 1300 |  | 27300 | 333.3%
7 | CONSTRUCTION UNLIMITED, INC. |  | 1000 |  | 21000 | 233.3%
8 | QAP |  | 1000 |  | 21000 | 233.3%
P-152a | Unclassified Excavation | Cubic Yard | 10 | 1500 | 15000
1 | GRANITE CONSTRUCTION COMPANY |  | 45 |  | 67500 | 350%
2 | RENEGADE EQUIPMENT, LLC. |  | 18 |  | 27000 | 80%
3 | FRAWNER CORPORATION |  | 15 |  | 22500 | 50%
4 | ROGER HICKEL CONTRACTING, INC. |  | 30.69 |  | 46035 | 206.9%
5 | RIDGE CONTRACTING, INC. |  | 30 |  | 45000 | 200%
6 | SWALLING CONSTRUCTION CO., INC. |  | 19 |  | 28500 | 90%
7 | CONSTRUCTION UNLIMITED, INC. |  | 15 |  | 22500 | 50%
8 | QAP |  | 25 |  | 37500 | 150%
P-152i | Borrow | Ton | 7 | 18400 | 128800
1 | GRANITE CONSTRUCTION COMPANY |  | 14.5 |  | 266800 | 107.1%
2 | RENEGADE EQUIPMENT, LLC. |  | 16 |  | 294400 | 128.6%
3 | FRAWNER CORPORATION |  | 30 |  | 552000 | 328.6%
4 | ROGER HICKEL CONTRACTING, INC. |  | 18 |  | 331200 | 157.1%
5 | RIDGE CONTRACTING, INC. |  | 28 |  | 515200 | 300%
6 | SWALLING CONSTRUCTION CO., INC. |  | 16 |  | 294400 | 128.6%
7 | CONSTRUCTION UNLIMITED, INC. |  | 19.25 |  | 354200 | 175%
8 | QAP |  | 20 |  | 368000 | 185.7%
P-152ae | Rock Lining | Ton | 35 | 680 | 23800
1 | GRANITE CONSTRUCTION COMPANY |  | 28 |  | 19040 | -20%
2 | RENEGADE EQUIPMENT, LLC. |  | 90 |  | 61200 | 157.1%
3 | FRAWNER CORPORATION |  | 70 |  | 47600 | 100%
4 | ROGER HICKEL CONTRACTING, INC. |  | 35 |  | 23800 | 0%
5 | RIDGE CONTRACTING, INC. |  | 65 |  | 44200 | 85.71%
6 | SWALLING CONSTRUCTION CO., INC. |  | 195 |  | 132600 | 457.1%
7 | CONSTRUCTION UNLIMITED, INC. |  | 35 |  | 23800 | 0%
8 | QAP |  | 75 |  | 51000 | 114.3%
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 20000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 3000 | -85%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 14000 | -30%
3 | FRAWNER CORPORATION |  |  |  | 20000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 57000 | 185%
5 | RIDGE CONTRACTING, INC. |  |  |  | 7500 | -62.5%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 7000 | -65%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 11000 | -45%
8 | QAP |  |  |  | 10000 | -50%
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 40000 | 0%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 40000 | 0%
3 | FRAWNER CORPORATION |  |  |  | 40000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 40000 | 0%
5 | RIDGE CONTRACTING, INC. |  |  |  | 40000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 40000 | 0%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 40000 | 0%
8 | QAP |  |  |  | 40000 | 0%
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 0
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 0
3 | FRAWNER CORPORATION |  |  |  | 0
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 0
5 | RIDGE CONTRACTING, INC. |  |  |  | 0
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 0
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 0
8 | QAP |  |  |  | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 30000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 80000 | 166.7%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 12000 | -60%
3 | FRAWNER CORPORATION |  |  |  | 45000 | 50%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 5000 | -83.33%
5 | RIDGE CONTRACTING, INC. |  |  |  | 10500 | -65%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 45000 | 50%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 20000 | -33.33%
8 | QAP |  |  |  | 20000 | -33.33%
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 80000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 130000 | 62.5%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 165000 | 106.2%
3 | FRAWNER CORPORATION |  |  |  | 215000 | 168.8%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 274900 | 243.6%
5 | RIDGE CONTRACTING, INC. |  |  |  | 150000 | 87.5%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 150000 | 87.5%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 130000 | 62.5%
8 | QAP |  |  |  | 400000 | 400%
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 20000 | 0%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 20000 | 0%
3 | FRAWNER CORPORATION |  |  |  | 20000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 20000 | 0%
5 | RIDGE CONTRACTING, INC. |  |  |  | 20000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 20000 | 0%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 20000 | 0%
8 | QAP |  |  |  | 20000 | 0%
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 15000 | 0%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 15000 | 0%
3 | FRAWNER CORPORATION |  |  |  | 15000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 15000 | 0%
5 | RIDGE CONTRACTING, INC. |  |  |  | 15000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 15000 | 0%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 15000 | 0%
8 | QAP |  |  |  | 15000 | 0%
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
1 | GRANITE CONSTRUCTION COMPANY |  |  |  | 20000 | 0%
2 | RENEGADE EQUIPMENT, LLC. |  |  |  | 20000 | 0%
3 | FRAWNER CORPORATION |  |  |  | 20000 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  |  |  | 20000 | 0%
5 | RIDGE CONTRACTING, INC. |  |  |  | 20000 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  |  |  | 20000 | 0%
7 | CONSTRUCTION UNLIMITED, INC. |  |  |  | 20000 | 0%
8 | QAP |  |  |  | 20000 | 0%
P-186b | Sacked Slope Protection | Each | 26 | 10300 | 267800
1 | GRANITE CONSTRUCTION COMPANY |  | 19 |  | 195700 | -26.92%
2 | RENEGADE EQUIPMENT, LLC. |  | 31 |  | 319300 | 19.23%
3 | FRAWNER CORPORATION |  | 25 |  | 257500 | -3.846%
4 | ROGER HICKEL CONTRACTING, INC. |  | 23 |  | 236900 | -11.54%
5 | RIDGE CONTRACTING, INC. |  | 10 |  | 103000 | -61.54%
6 | SWALLING CONSTRUCTION CO., INC. |  | 21.5 |  | 221450 | -17.31%
7 | CONSTRUCTION UNLIMITED, INC. |  | 77 |  | 793100 | 196.2%
8 | QAP |  | 25 |  | 257500 | -3.846%
P-209b | Crushed Aggregate Base Course | Ton | 45 | 1200 | 54000
1 | GRANITE CONSTRUCTION COMPANY |  | 53 |  | 63600 | 17.78%
2 | RENEGADE EQUIPMENT, LLC. |  | 39 |  | 46800 | -13.33%
3 | FRAWNER CORPORATION |  | 50 |  | 60000 | 11.11%
4 | ROGER HICKEL CONTRACTING, INC. |  | 91.5 |  | 109800 | 103.3%
5 | RIDGE CONTRACTING, INC. |  | 65 |  | 78000 | 44.44%
6 | SWALLING CONSTRUCTION CO., INC. |  | 44 |  | 52800 | -2.222%
7 | CONSTRUCTION UNLIMITED, INC. |  | 35 |  | 42000 | -22.22%
8 | QAP |  | 50 |  | 60000 | 11.11%
P-650a | Soil Anchor Tie-down, Screw | Set | 1000 | 59 | 59000
1 | GRANITE CONSTRUCTION COMPANY |  | 152 |  | 8968 | -84.8%
2 | RENEGADE EQUIPMENT, LLC. |  | 1200 |  | 70800 | 20%
3 | FRAWNER CORPORATION |  | 550 |  | 32450 | -45%
4 | ROGER HICKEL CONTRACTING, INC. |  | 160 |  | 9440 | -84%
5 | RIDGE CONTRACTING, INC. |  | 550 |  | 32450 | -45%
6 | SWALLING CONSTRUCTION CO., INC. |  | 680 |  | 40120 | -32%
7 | CONSTRUCTION UNLIMITED, INC. |  | 175 |  | 10325 | -82.5%
8 | QAP |  | 1000 |  | 59000 | 0%
P-681a | Geotextile, Separation | Square Yard | 3 | 13400 | 40200
1 | GRANITE CONSTRUCTION COMPANY |  | 2.3 |  | 30820 | -23.33%
2 | RENEGADE EQUIPMENT, LLC. |  | 6.5 |  | 87100 | 116.7%
3 | FRAWNER CORPORATION |  | 3 |  | 40200 | 0%
4 | ROGER HICKEL CONTRACTING, INC. |  | 2.5 |  | 33500 | -16.67%
5 | RIDGE CONTRACTING, INC. |  | 3.5 |  | 46900 | 16.67%
6 | SWALLING CONSTRUCTION CO., INC. |  | 7 |  | 93800 | 133.3%
7 | CONSTRUCTION UNLIMITED, INC. |  | 6 |  | 80400 | 100%
8 | QAP |  | 5 |  | 67000 | 66.67%
P-684a | Floating Silt Curtain | Linear Foot | 100 | 825 | 82500
1 | GRANITE CONSTRUCTION COMPANY |  | 46.5 |  | 38362.5 | -53.5%
2 | RENEGADE EQUIPMENT, LLC. |  | 59 |  | 48675 | -41%
3 | FRAWNER CORPORATION |  | 180 |  | 148500 | 80%
4 | ROGER HICKEL CONTRACTING, INC. |  | 69 |  | 56925 | -31%
5 | RIDGE CONTRACTING, INC. |  | 150 |  | 123750 | 50%
6 | SWALLING CONSTRUCTION CO., INC. |  | 41 |  | 33825 | -59%
7 | CONSTRUCTION UNLIMITED, INC. |  | 120 |  | 99000 | 20%
8 | QAP |  | 30 |  | 24750 | -70%
P-685a | Geogrid, Type 1 | Square Yard | 4.5 | 1750 | 7875
1 | GRANITE CONSTRUCTION COMPANY |  | 2.4 |  | 4200 | -46.67%
2 | RENEGADE EQUIPMENT, LLC. |  | 10 |  | 17500 | 122.2%
3 | FRAWNER CORPORATION |  | 17.25 |  | 30187.5 | 283.3%
4 | ROGER HICKEL CONTRACTING, INC. |  | 2.5 |  | 4375 | -44.44%
5 | RIDGE CONTRACTING, INC. |  | 9 |  | 15750 | 100%
6 | SWALLING CONSTRUCTION CO., INC. |  | 10 |  | 17500 | 122.2%
7 | CONSTRUCTION UNLIMITED, INC. |  | 4 |  | 7000 | -11.11%
8 | QAP |  | 6 |  | 10500 | 33.33%
P-685b | Geocell, 6-Inch | Square Yard | 40 | 1770 | 70800
1 | GRANITE CONSTRUCTION COMPANY |  | 29 |  | 51330 | -27.5%
2 | RENEGADE EQUIPMENT, LLC. |  | 45 |  | 79650 | 12.5%
3 | FRAWNER CORPORATION |  | 49.75 |  | 88057.5 | 24.38%
4 | ROGER HICKEL CONTRACTING, INC. |  | 58 |  | 102660 | 45%
5 | RIDGE CONTRACTING, INC. |  | 40 |  | 70800 | 0%
6 | SWALLING CONSTRUCTION CO., INC. |  | 48 |  | 84960 | 20%
7 | CONSTRUCTION UNLIMITED, INC. |  | 25 |  | 44250 | -37.5%
8 | QAP |  | 25 |  | 44250 | -37.5%
T-901b | Seeding | Pound | 300 | 120 | 36000
1 | GRANITE CONSTRUCTION COMPANY |  | 77 |  | 9240 | -74.33%
2 | RENEGADE EQUIPMENT, LLC. |  | 62 |  | 7440 | -79.33%
3 | FRAWNER CORPORATION |  | 100 |  | 12000 | -66.67%
4 | ROGER HICKEL CONTRACTING, INC. |  | 53 |  | 6360 | -82.33%
5 | RIDGE CONTRACTING, INC. |  | 54 |  | 6480 | -82%
6 | SWALLING CONSTRUCTION CO., INC. |  | 450 |  | 54000 | 50%
7 | CONSTRUCTION UNLIMITED, INC. |  | 250 |  | 30000 | -16.67%
8 | QAP |  | 70 |  | 8400 | -76.67%
T-901c | Water for Maintenance | M-gal | 40 | 700 | 28000
1 | GRANITE CONSTRUCTION COMPANY |  | 35 |  | 24500 | -12.5%
2 | RENEGADE EQUIPMENT, LLC. |  | 90 |  | 63000 | 125%
3 | FRAWNER CORPORATION |  | 50 |  | 35000 | 25%
4 | ROGER HICKEL CONTRACTING, INC. |  | 82 |  | 57400 | 105%
5 | RIDGE CONTRACTING, INC. |  | 84 |  | 58800 | 110%
6 | SWALLING CONSTRUCTION CO., INC. |  | 32 |  | 22400 | -20%
7 | CONSTRUCTION UNLIMITED, INC. |  | 43 |  | 30100 | 7.5%
8 | QAP |  | 30 |  | 21000 | -25%
T-903b | Sprigging | Square Yard | 70 | 1850 | 129500
1 | GRANITE CONSTRUCTION COMPANY |  | 23 |  | 42550 | -67.14%
2 | RENEGADE EQUIPMENT, LLC. |  | 32 |  | 59200 | -54.29%
3 | FRAWNER CORPORATION |  | 28 |  | 51800 | -60%
4 | ROGER HICKEL CONTRACTING, INC. |  | 8 |  | 14800 | -88.57%
5 | RIDGE CONTRACTING, INC. |  | 8.5 |  | 15725 | -87.86%
6 | SWALLING CONSTRUCTION CO., INC. |  | 33 |  | 61050 | -52.86%
7 | CONSTRUCTION UNLIMITED, INC. |  | 86 |  | 159100 | 22.86%
8 | QAP |  | 20 |  | 37000 | -71.43%
T-905a | Topsoiling | Square Yard | 3.5 | 11750 | 41125
1 | GRANITE CONSTRUCTION COMPANY |  | 3 |  | 35250 | -14.29%
2 | RENEGADE EQUIPMENT, LLC. |  | 15 |  | 176250 | 328.6%
3 | FRAWNER CORPORATION |  | 5 |  | 58750 | 42.86%
4 | ROGER HICKEL CONTRACTING, INC. |  | 3 |  | 35250 | -14.29%
5 | RIDGE CONTRACTING, INC. |  | 3 |  | 35250 | -14.29%
6 | SWALLING CONSTRUCTION CO., INC. |  | 6 |  | 70500 | 71.43%
7 | CONSTRUCTION UNLIMITED, INC. |  | 6 |  | 70500 | 71.43%
8 | QAP |  | 3 |  | 35250 | -14.29%

## GRANITE CONSTRUCTION COMPANY
Bid Rank: 1 |  | GRANITE CONSTRUCTION COMPANY
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 11471 LANG STREET
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99515
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 15 | 37200 | 558000
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 147000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 47000
G-135b | Extra Three Person Survey Party | Hour | 320 | 60 | 19200
G-150a | Equipment Rental, Forklift | Hour | 128 | 400 | 51200
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 800
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 24 | 700 | 16800
L-160c | Load Center, Type 2 | Each | 3200 | 17 | 54400
P-151e | Selective Tree Removal | Each | 775 | 21 | 16275
P-152a | Unclassified Excavation | Cubic Yard | 45 | 1500 | 67500
P-152i | Borrow | Ton | 14.5 | 18400 | 266800
P-152ae | Rock Lining | Ton | 28 | 680 | 19040
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 3000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 80000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 130000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 19 | 10300 | 195700
P-209b | Crushed Aggregate Base Course | Ton | 53 | 1200 | 63600
P-650a | Soil Anchor Tie-down, Screw | Set | 152 | 59 | 8968
P-681a | Geotextile, Separation | Square Yard | 2.3 | 13400 | 30820
P-684a | Floating Silt Curtain | Linear Foot | 46.5 | 825 | 38362.5
P-685a | Geogrid, Type 1 | Square Yard | 2.4 | 1750 | 4200
P-685b | Geocell, 6-Inch | Square Yard | 29 | 1770 | 51330
T-901b | Seeding | Pound | 77 | 120 | 9240
T-901c | Water for Maintenance | M-gal | 35 | 700 | 24500
T-903b | Sprigging | Square Yard | 23 | 1850 | 42550
T-905a | Topsoiling | Square Yard | 3 | 11750 | 35250

## RENEGADE EQUIPMENT, LLC.
Bid Rank: 2 |  | RENEGADE EQUIPMENT, LLC.
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 4820 O'MALLEY RD
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99507
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 11.9 | 37200 | 442680
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 90000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 66000
G-135b | Extra Three Person Survey Party | Hour | 350 | 60 | 21000
G-150a | Equipment Rental, Forklift | Hour | 110 | 400 | 44000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 4000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 95 | 700 | 66500
L-160c | Load Center, Type 2 | Each | 7740 | 17 | 131580
P-151e | Selective Tree Removal | Each | 1200 | 21 | 25200
P-152a | Unclassified Excavation | Cubic Yard | 18 | 1500 | 27000
P-152i | Borrow | Ton | 16 | 18400 | 294400
P-152ae | Rock Lining | Ton | 90 | 680 | 61200
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 14000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 12000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 165000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 31 | 10300 | 319300
P-209b | Crushed Aggregate Base Course | Ton | 39 | 1200 | 46800
P-650a | Soil Anchor Tie-down, Screw | Set | 1200 | 59 | 70800
P-681a | Geotextile, Separation | Square Yard | 6.5 | 13400 | 87100
P-684a | Floating Silt Curtain | Linear Foot | 59 | 825 | 48675
P-685a | Geogrid, Type 1 | Square Yard | 10 | 1750 | 17500
P-685b | Geocell, 6-Inch | Square Yard | 45 | 1770 | 79650
T-901b | Seeding | Pound | 62 | 120 | 7440
T-901c | Water for Maintenance | M-gal | 90 | 700 | 63000
T-903b | Sprigging | Square Yard | 32 | 1850 | 59200
T-905a | Topsoiling | Square Yard | 15 | 11750 | 176250

## FRAWNER CORPORATION
Bid Rank: 3 |  | FRAWNER CORPORATION
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 1600 A STREET, SUITE 302
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99501
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 14 | 37200 | 520800
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 40000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 55000
G-135b | Extra Three Person Survey Party | Hour | 325 | 60 | 19500
G-150a | Equipment Rental, Forklift | Hour | 100 | 400 | 40000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 25000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 50 | 700 | 35000
L-160c | Load Center, Type 2 | Each | 4200 | 17 | 71400
P-151e | Selective Tree Removal | Each | 350 | 21 | 7350
P-152a | Unclassified Excavation | Cubic Yard | 15 | 1500 | 22500
P-152i | Borrow | Ton | 30 | 18400 | 552000
P-152ae | Rock Lining | Ton | 70 | 680 | 47600
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 20000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 45000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 215000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 25 | 10300 | 257500
P-209b | Crushed Aggregate Base Course | Ton | 50 | 1200 | 60000
P-650a | Soil Anchor Tie-down, Screw | Set | 550 | 59 | 32450
P-681a | Geotextile, Separation | Square Yard | 3 | 13400 | 40200
P-684a | Floating Silt Curtain | Linear Foot | 180 | 825 | 148500
P-685a | Geogrid, Type 1 | Square Yard | 17.25 | 1750 | 30187.5
P-685b | Geocell, 6-Inch | Square Yard | 49.75 | 1770 | 88057.5
T-901b | Seeding | Pound | 100 | 120 | 12000
T-901c | Water for Maintenance | M-gal | 50 | 700 | 35000
T-903b | Sprigging | Square Yard | 28 | 1850 | 51800
T-905a | Topsoiling | Square Yard | 5 | 11750 | 58750

## ROGER HICKEL CONTRACTING, INC.
Bid Rank: 4 |  | ROGER HICKEL CONTRACTING, INC.
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 11001 CALASKA CIRCLE
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99515-2933
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 10.6 | 37200 | 394320
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 515500
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 46000
G-135b | Extra Three Person Survey Party | Hour | 315 | 60 | 18900
G-150a | Equipment Rental, Forklift | Hour | 20 | 400 | 8000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 57000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 55 | 700 | 38500
L-160c | Load Center, Type 2 | Each | 3770 | 17 | 64090
P-151e | Selective Tree Removal | Each | 580 | 21 | 12180
P-152a | Unclassified Excavation | Cubic Yard | 30.69 | 1500 | 46035
P-152i | Borrow | Ton | 18 | 18400 | 331200
P-152ae | Rock Lining | Ton | 35 | 680 | 23800
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 57000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 5000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 274900
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 23 | 10300 | 236900
P-209b | Crushed Aggregate Base Course | Ton | 91.5 | 1200 | 109800
P-650a | Soil Anchor Tie-down, Screw | Set | 160 | 59 | 9440
P-681a | Geotextile, Separation | Square Yard | 2.5 | 13400 | 33500
P-684a | Floating Silt Curtain | Linear Foot | 69 | 825 | 56925
P-685a | Geogrid, Type 1 | Square Yard | 2.5 | 1750 | 4375
P-685b | Geocell, 6-Inch | Square Yard | 58 | 1770 | 102660
T-901b | Seeding | Pound | 53 | 120 | 6360
T-901c | Water for Maintenance | M-gal | 82 | 700 | 57400
T-903b | Sprigging | Square Yard | 8 | 1850 | 14800
T-905a | Topsoiling | Square Yard | 3 | 11750 | 35250

## RIDGE CONTRACTING, INC.
Bid Rank: 5 |  | RIDGE CONTRACTING, INC.
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | P.O. BOX 240121
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99524
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 18 | 37200 | 669600
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 290000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 65000
G-135b | Extra Three Person Survey Party | Hour | 330 | 60 | 19800
G-150a | Equipment Rental, Forklift | Hour | 92 | 400 | 36800
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 4500
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 88 | 700 | 61600
L-160c | Load Center, Type 2 | Each | 3000 | 17 | 51000
P-151e | Selective Tree Removal | Each | 600 | 21 | 12600
P-152a | Unclassified Excavation | Cubic Yard | 30 | 1500 | 45000
P-152i | Borrow | Ton | 28 | 18400 | 515200
P-152ae | Rock Lining | Ton | 65 | 680 | 44200
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 7500
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 10500
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 150000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 10 | 10300 | 103000
P-209b | Crushed Aggregate Base Course | Ton | 65 | 1200 | 78000
P-650a | Soil Anchor Tie-down, Screw | Set | 550 | 59 | 32450
P-681a | Geotextile, Separation | Square Yard | 3.5 | 13400 | 46900
P-684a | Floating Silt Curtain | Linear Foot | 150 | 825 | 123750
P-685a | Geogrid, Type 1 | Square Yard | 9 | 1750 | 15750
P-685b | Geocell, 6-Inch | Square Yard | 40 | 1770 | 70800
T-901b | Seeding | Pound | 54 | 120 | 6480
T-901c | Water for Maintenance | M-gal | 84 | 700 | 58800
T-903b | Sprigging | Square Yard | 8.5 | 1850 | 15725
T-905a | Topsoiling | Square Yard | 3 | 11750 | 35250

## SWALLING CONSTRUCTION CO., INC
Bid Rank: 6 |  | SWALLING CONSTRUCTION CO., INC.
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | P.O. BOX 101039
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99510
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 20.85 | 37200 | 775620
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 115000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 60000
G-135b | Extra Three Person Survey Party | Hour | 385 | 60 | 23100
G-150a | Equipment Rental, Forklift | Hour | 115 | 400 | 46000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 9000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 96 | 700 | 67200
L-160c | Load Center, Type 2 | Each | 3800 | 17 | 64600
P-151e | Selective Tree Removal | Each | 1300 | 21 | 27300
P-152a | Unclassified Excavation | Cubic Yard | 19 | 1500 | 28500
P-152i | Borrow | Ton | 16 | 18400 | 294400
P-152ae | Rock Lining | Ton | 195 | 680 | 132600
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 7000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 45000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 150000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 21.5 | 10300 | 221450
P-209b | Crushed Aggregate Base Course | Ton | 44 | 1200 | 52800
P-650a | Soil Anchor Tie-down, Screw | Set | 680 | 59 | 40120
P-681a | Geotextile, Separation | Square Yard | 7 | 13400 | 93800
P-684a | Floating Silt Curtain | Linear Foot | 41 | 825 | 33825
P-685a | Geogrid, Type 1 | Square Yard | 10 | 1750 | 17500
P-685b | Geocell, 6-Inch | Square Yard | 48 | 1770 | 84960
T-901b | Seeding | Pound | 450 | 120 | 54000
T-901c | Water for Maintenance | M-gal | 32 | 700 | 22400
T-903b | Sprigging | Square Yard | 33 | 1850 | 61050
T-905a | Topsoiling | Square Yard | 6 | 11750 | 70500

## CONSTRUCTION UNLIMITED, INC.
Bid Rank: 7 |  | CONSTRUCTION UNLIMITED, INC.
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 8821 EMERALD STREET
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99502
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 16 | 37200 | 595200
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 60000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 77000
G-135b | Extra Three Person Survey Party | Hour | 330 | 60 | 19800
G-150a | Equipment Rental, Forklift | Hour | 150 | 400 | 60000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 10000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 28 | 700 | 19600
L-160c | Load Center, Type 2 | Each | 4000 | 17 | 68000
P-151e | Selective Tree Removal | Each | 1000 | 21 | 21000
P-152a | Unclassified Excavation | Cubic Yard | 15 | 1500 | 22500
P-152i | Borrow | Ton | 19.25 | 18400 | 354200
P-152ae | Rock Lining | Ton | 35 | 680 | 23800
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 11000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 20000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 130000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 77 | 10300 | 793100
P-209b | Crushed Aggregate Base Course | Ton | 35 | 1200 | 42000
P-650a | Soil Anchor Tie-down, Screw | Set | 175 | 59 | 10325
P-681a | Geotextile, Separation | Square Yard | 6 | 13400 | 80400
P-684a | Floating Silt Curtain | Linear Foot | 120 | 825 | 99000
P-685a | Geogrid, Type 1 | Square Yard | 4 | 1750 | 7000
P-685b | Geocell, 6-Inch | Square Yard | 25 | 1770 | 44250
T-901b | Seeding | Pound | 250 | 120 | 30000
T-901c | Water for Maintenance | M-gal | 43 | 700 | 30100
T-903b | Sprigging | Square Yard | 86 | 1850 | 159100
T-905a | Topsoiling | Square Yard | 6 | 11750 | 70500

## QAP
Bid Rank: 8 |  | QAP
Lake Hood Seaplane Base Lake Hood Bank Stabilization |  | 240 W. 68TH AVE.
AIP 3-02-0013-014-2010 /50920 |  | ANCHORAGE, AK 99518
Bids Opened: 9/17/2010
Item Number | Pay Item | Pay Unit | Unit Price | Plan Quantity | Plan Amount
Basic Bid
S-160a | Sheet Pile, Vinyl | Square Foot | 22 | 37200 | 818400
G-100a | Mobilization and Demobilization | Lump Sum | All Req'd | All Req'd | 250000
G-135a | Construction Surveying by the Contractor | Lump Sum | All Req'd | All Req'd | 44175
G-135b | Extra Three Person Survey Party | Hour | 300 | 60 | 18000
G-150a | Equipment Rental, Forklift | Hour | 250 | 400 | 100000
G-300a | CPM Scheduling | Lump Sum | All Req'd | All Req'd | 5000
G-700a | Airport Flagger | Contingent Sum | All Req'd | All Req'd | 35000
G-705a | Watering for Dust Control | M-gal | 60 | 700 | 42000
L-160c | Load Center, Type 2 | Each | 3400 | 17 | 57800
P-151e | Selective Tree Removal | Each | 1000 | 21 | 21000
P-152a | Unclassified Excavation | Cubic Yard | 25 | 1500 | 37500
P-152i | Borrow | Ton | 20 | 18400 | 368000
P-152ae | Rock Lining | Ton | 75 | 680 | 51000
P-157a | Erosion, Sediment, and Pollution Control Administration | Lump Sum | All Req'd | All Req'd | 10000
P-157b | Temporary Erosion, Sediment, and Pollution Control | Contingent Sum | All Req'd | All Req'd | 40000
P-157e | Erosion, Sediment, and Pollution Control Price Adjustment | Contingent Sum | All Req'd | All Req'd | 0
P-157f | SWPPP Manager | Lump Sum | All Req'd | All Req'd | 20000
P-165a | Removal of Structures | Lump Sum | All Req'd | All Req'd | 400000
P-170e | Soil Testing Program | Contingent Sum | All Req'd | All Req'd | 20000
P-170g | Supplemental Laboratory Test | Contingent Sum | All Req'd | All Req'd | 15000
P-171b | Temporary Contaminated Soil Stockpile Area | Contingent Sum | All Req'd | All Req'd | 20000
P-186b | Sacked Slope Protection | Each | 25 | 10300 | 257500
P-209b | Crushed Aggregate Base Course | Ton | 50 | 1200 | 60000
P-650a | Soil Anchor Tie-down, Screw | Set | 1000 | 59 | 59000
P-681a | Geotextile, Separation | Square Yard | 5 | 13400 | 67000
P-684a | Floating Silt Curtain | Linear Foot | 30 | 825 | 24750
P-685a | Geogrid, Type 1 | Square Yard | 6 | 1750 | 10500
P-685b | Geocell, 6-Inch | Square Yard | 25 | 1770 | 44250
T-901b | Seeding | Pound | 70 | 120 | 8400
T-901c | Water for Maintenance | M-gal | 30 | 700 | 21000
T-903b | Sprigging | Square Yard | 20 | 1850 | 37000
T-905a | Topsoiling | Square Yard | 3 | 11750 | 35250