## Final
Project Name | [11 empty] | <= Fill in Project Name
Project Number | [11 empty] | <= Fill in Project number (both Federal/State)
Project Engineer Signature | [11 empty] | <= Leave Blank
Unshaded boxes indicate who approves the manufacturer's certificate of compliance or materials submittals. If two boxes aren't shaded, either approving authority may be used.
SECTION 660/661/669/740 MASTER MATERIALS CERTIFICATION LIST (Updated 3/28/2024) | [11 empty] | <= Delete 'MASTER' and date once you've made this project specific
Materials Item | Specification | Third Party Listing or Labeling Required? (Y/N) | Acceptance By: | [6 empty] | Manufacturer/ Remarks | Certificate Location e.g. Binder #
|  |  | Construction |  | Design |  |  | Statewide Materials
|  |  | Project Engineer | Regional Materials or QA Engineer | State Electrical Engineer | Regional Highway Data Manager | Regional Traffic Design Engineer | Qualified Products List (QPL) | State Materials or QA Engineer
660 SIGNALS AND LIGHTING
TRAFFIC SIGNAL SYSTEMS
PCC SIGNAL POLE FOUNDATIONS: Cast In Place
Concrete Mix Design | 660-3.02 | N
Reinforcing Steel Bars | Std. Plans 709-2.01 | N
Anchor Rods | Std. Plans 709-2.01 | N
Corrugated Metal Pipe | Std. Plans 660-3.02 | N
PCC TRAFFIC SIGNAL CONTROLLER CABINET FOUNDATION | See Detail in Plans | N
JUNCTION BOXES:
Type I / IA, II, III | See Detail in Plans 660-2.01 660-3.04 | N
Electronic Ball Marker | 660-3.04 | N
Concrete Mix Design | 660-2.01 501-2.02 | N
Curing Materials | 711-2.01 | N
Reinforcing Steel | 709-2.01 | N
Junction Box Cover | See Detail in Plans 660-3.04 | N
FIBER OPTIC VAULTS AND MANHOLES:
Vaults and Manholes | 662-2.06 | N
STEEL POLES AND POSTS:
Galvanizing | Std. Plans 740-2.02 | N
Shop Drawings | Std. Plans 660-3.01 740-2.02 | N
Calculations | Std. Plans 740-2.02 | N
Welding Plan | Std. Plans 660-3.01 740-2.02 | N
Mill Certifications | Std. Plans 740-2.02 | N
CONDUIT / LOOPS:
Galvanized Rigid Metal Conduit (RMC) | 740-2.06 | Y
High Density Polyethylene Conduit (HDPE) | 740-2.06 | Y
High Density Polyethylene Couplings | 660-3.03 740-2.06 | Y
Galvanized Couplings | 740-2.06 | Y
Galvanized Split Couplings | 740-2.06 | Y
Galvanized Elbows | 740-2.06 | Y
Bore Casing | 660-3.03 | N
Galvanized Nipples | 740-2.06 | Y
Underground Marker Tape | 660-3.03 | N
Pull Rope | 660-3.03 | N
Watertight Caps (for unused conduit) | See Detail in Plans | N
Watertight sealing bushing (for used conduits above ground) | See Detail in Plans | N
Duct Sealing Compound (for conduits below grade entry thru Controller Foundation Slab) | 660-3.03 | Y
Galvanized Myers Hub (for connection to enclosures) | 740-2.06 | Y
Schedule 80 PVC Conduit (for loops) | See Detail in Plans 740-2.06 | Y
PVC Fittings & Adapters (Loops) | See Detail in Plans 740-2.06 | Y
Type "X" Conduit Outlet Bodies with Covers, Gaskets & Plugs (Loops) | See Detail in Plans 740-2.06 | Y
BONDING & GROUNDING:
Copper Ground Rod | See Detail in Plans 660-3.06 | Y
Grounding Bushings | See Detail in Plans 740-2.06 | Y
Ground Rod Clamps | 660-3.01 660-3.06 | Y
Bare Copper Grounding Wire | See Detail in Plans 660-3.06 | N
Braided Copper J-Box Lid Bonding Wire | See Detail in Plans 740-2.06 660-3.06 | Y
Irreversible Compression Type Connectors | See Details in Plans 660-3.02 660-3.06 | Y
CONDUCTORS / CABLES:
Control Cables | 740-2.05 | Y
Power Cable | 740-2.05 | Y
Detector Loops | See Details in Plans 740-2.05 | Y
Loop Lead-in (Snyder) Cable | 740-2.05 | Y
a. Power & Control Tray Cable
b. Used on all new construction, and on rehabilitation work with sufficient conduit capacity.
Loop Lead-in (Shielded Data) Cable | 740-2.05 | Y
a. Polyethylene or polypro insulation
b. Used on Rehab jobs where Snyder Cable creates fill problems.
Interconnect Cable (Copper) | 740-2.05 | N
Interconnect Cable (Fiber) | 662-2.03 | N
Illumination Cable - PE Jacket | 740-2.05 | Y
Luminaire Tap Conductors | 740-2.05 | Y
Identification Tags | 660-3.05 | N
SPLICES and TERMINALS:
Terminal Blocks | 660-3.05 740-2.11 740-2.14 | Y
Spade type crimp-on terminals | 660-3.05 | Y
Loop Lead In Splice Kit (for Loops) | See Detail in Plans 660-3.05 | N
Heat Shrink Tubing | 660-3.05 | Y
Power Cable Splice Kit (Lighting) | See Details in Plans 660-3.05 | Y
Splice Connectors | See Details in Plans 660-3.05 | Y
Electrical Tape | See Details in Plans 660-3.05 | Y
Double Fuse Connector Kits (Lighting) | See Detail in Plans 740-2.07 | Y
Fuses for Double Fuse Connector Kit | See Detail in Plans 740-2.07 | Y
Interconnect Splice Kits (fiber) | 662-3.09 | N
Interconnect Closures and Splice Trays | 662-3.10 | N
CONTROLLER CABINET:
Size 6 Cabinet | See Detail in Plans. 740-2.11 | Y
Size 7 Cabinet | See Detail in Plans. 740-2.11 | Y
Flashing Beacon Control Cabinet | See Detail in Plans. 740-2.17 | N
TRAFFIC SIGNAL CONTROLLER:
Econolite Cobalt | 740-2.10 | N
Econolite ASC/3 | 740-2.10 | N
OTHER CABINET COMPONENTS:
NEMA TS2 Plug N Go | 740-2.11 | Y
Malfunction Management Unit (MMU) | 740-2.12 | N
Inductive Loop Detector Unit | 740-2.13 | N
Traffic Logging System | 740-2.13 | N
Solid State Flasher | 740-2.12 | N
Three-Circuit Solid State Load Switch | 740-2.12 | N
Flash Transfer Relay | 740-2.12 | N
Bus Interface Unit (BIU) | 740-2.13 | N
Time Switch | 740-2.17 | Y
Bypass Switch | 740-2.17 | N
Patch Panel (interconnect) | 662-2.04 | N
Ethernet Switch (interconnect) | See Detail in Plans 740-2.13 | N
Cabinet interface device (radar) | See Detail in Plans 740-2.13 | N
CABINET VENTILATION SYSTEM:
Heater | See Detail in Plans 740-2.11 | Y
Thermostat | See Detail in Plans 740-2.11 | Y
Fan | See Detail in Plans 740-2.11 | Y
COMMUNICATION SYSTEMS:
System Modem | 740-2.13 | N
Radio | 740-2.23 | Y
Antenna | See Detail in Plans 740-2.23 | N
Antenna Cable | See Detail in Plans | N
PAN TILT ZOOM CAMERA (PTZ) / RADAR:
Mounting Bracket Astro-Brac | See Detail in Plans | N
Pan Tilt Zoom Camera System | See Detail in Plans 740-2.13 | N
Wall Mount Adapter | See Detail in Plans | N
AXIS Wall and Pole Mount | See Detail in Plans | N
Radar Detection System | See Detail in Plans 740-2.13 | N
OPTICOM:
Astro-Brac | See Detail in Plans | N
Preemption Detector | See Detail in Plans 740-2.13 | N
Phase Selector | See Detail in Plans 740-2.13 | N
Opticom Lead in Cable | See Detail in Plans 740-2.13 | N
Auxillary Interface Panel | See Detail in Plans 740-2.13 | N
GPS/Radio Opticom Unit | See Detail in Plans 740-2.13 | N
GPS Installation Cable | See Detail in Plans 740-2.13 | N
Auxillary Harness | See Detail in Plans 740-2.13 | N
Emitter Kit | See Detail in Plans 740-2.13 | N
VEHICULAR SIGNAL HARDWARE:
LED Signal (Optical Units) | 740-2.14 | N
Housing | 740-2.14 | N
Backplate | 740-2.14 | N
Visor | 740-2.14 | N
Elevator Plumbizer | Std. Plans 740-2.14 | N
Astro-Brac | Std. Plans | N
One and two way side mounted signal frames | Std. Plans 660-3.08 740-2.14 | N
4.5" Slipfitter w/ or w/o Offset Opening | Std. Plans 740-2.14 | N
Terminal Compartments | Std. Plans 740-2.14 660-3.08 | N
Traffic Signal Shirt (pre-operational canvas signal head cover ) | 660-3.08 | N
Programmed Visibility Signal Heads | 740-2.14 | N
PEDESTRIAN SIGNAL HARDWARE:
LED Signal Module | 740-2.15 | N
Housing | 740-2.15 | N
Clamshell Mounting Bracket | 740-2.15 | N
Pedestrian Push Button | Std. Plans 740-2.16 | N
Push Button Housing | Std. Plans 740-2.16 | N
INTERSECTION LIGHTING AT TRAFFIC SIGNALS:
LED Luminaire (include all additional requirements) | See Detail in Plans 740-2.18 | Y
Luminaire, Lamp, Ballast | See Detail in Plans 740-2.18 740-2.21 | Y
HIGHWAY LIGHTING SYSTEMS
PCC STREET LIGHT POLE FOUNDATION: Cast in Place
Concrete Mix Design | 660-2.01 | N
Reinforcing Steel Bars | Std. Plans 709-2.01 | N
Anchor | Std. Plans | N
Corrugated Metal Pipe | Std. Plans 660-3.02 | N
Frangible Couplings | Std. Plans | N
PRECAST FOUNDATIONS | See Detail in Plans | N
PIPE PILE ELECTROLIER FOUNDATION:
Pipe Pile | See Detail in Plans 660-2.01 660-3.02 | N
Pile Adapter, Steel Plate | See Detail in Plans 740-2.02 | N
JUNCTION BOXES:
Type I / IA, II, III | See Detail in Plans 660-2.01 709-2.01 711-2.01 | N
Concrete Mix Design | 501-2.02 660-2.01 | N
Curing Materials | 711-2.01 | N
Reinforcing Steel | 709-2.01 | N
Electronic ball marker | See Detail in Plans 660-3.04 | N
Junction Box Cover | See Detail in Plans 660-3.04 | N
LIGHTING STRUCTURES:
Steel Poles | See Detail in Plans 740-2.02 | N
Galvanizing | 740-2.02 | N
Shop Drawings | 660-3.01 740-2.02 | N
Calculations | 740-2.02 | N
Welding Plan | 660-3.01 740-2.02 | N
Mill Certifications | 740-2.02 | N
CONDUIT:
Galvanized Rigid Metal Conduit (RMC) | 740-2.06 | Y
High Density Polyethylene Conduit (HDPE) | 740-2.06 | Y
High Density Polyethylene Couplings | 660-3.03 | Y
Galvanized Couplings | 740-2.06 | Y
Galvanized Split Couplings | 740-2.06 | Y
Galvanized Elbows | 740-2.06 | Y
Galvanized Nipples | 740-2.06 | Y
Bore Casing | 660-3.03 | N
Underground Marker Tape | 660-3.03 | N
Pull Rope | 660-3.03 | N
Type "C" and "LB" Conduit Outlet Bodies with Covers, Gaskets & Plugs | See Detail in Plans 740-2.06 | Y
BONDING & GROUNDING:
Grounding Bushings | See Detail in Plans 740-2.06 660-3.01 660-3.06 | Y
Bare Copper Ground Wire | See Detail in Plans 660-3.06 | N
Braided Copper J-Box Lid Bonding Wire | See Detail in Plans 740-2.06 660-3.06 | Y
Irreversible Compression Type Connectors | See Details in Plans 660-3.02 660-3.06 | Y
CONDUCTORS / CABLES:
Illumination Cable - PE Jacket | 740-2.05 | Y
Power Cable - PE Jacket | 740-2.05 | Y
Luminaire Tap Conductors | 740-2.05 | Y
Identification Labels | 660-3.05 | N
SPLICES:
Heat Shrink Tubing | See Detail in Plans 660-3.05 | Y
Electrical Tape | See Detail in Plans 660-3.05 | Y
Power Cable Splice Kit (Lighting) | See Detail in Plans 660-3.05 | Y
Double Fuse Connector Kits (Lighting) | See Detail in Plans 740-2.07 | Y
Fuses for Double Fuse Connector Kits | See Detail in Plans 740-2.07 | Y
LIGHTING FIXTURES:
LED Luminaire (include all additional requirements) | See Detail in Plans 740-2.18 | Y
HPS Luminaire, Lamp, Ballast | See Detail in Plans 740-2.18 740-2.21 | Y
Sign Lighting, Lamp, Ballast | See Detail in Plans 740-2.19 | Y
Underpass Luminaire, Lamp, Ballast | See Detail in Plans 740-2.23 | Y
ILLUMINATION CONTROL:
Node | See Detail in Plans 740-2.20 | N
Gateway | See Detail in Plans 740-2.20 | N
Modem | See Detail in Plans 740-2.20 | N
661 ELECTRICAL LOAD CENTERS
TYPE 1 & TYPE 1A FOUNDATIONS | Std. Plans 661-2.01 | N
Wood Posts (TYPE 2 & 3 FOUNDATIONS) | Std. Plans 661-2.01 | N
Treatment | Std. Plans 714-2.01 | N
BONDING & GROUNDING:
Copper Ground Rod | Std. Plans 661-2.01 | Y
Ground Rod Clamps | 661-2.01 | Y
Bare Copper Grounding Wire | Std. Plans 661-3.01 | N
COMPONENTS IN COMMON:
Photoelectric Control | Std. Plans 740-2.20 661-2.01 | Y
Photocell Cable | Std. Plans 740-2.05 | Y
Contactor | Std. Plans 661-2.01 | Y
Load Panel | Std. Plans 661-2.01 | Y
Neutral Bus Bar System | Std. Plans 661-2.01 | Y
Ground Bus Bar System | Std. Plans 661-2.01 | Y
Terminals | 661-2.01 | Y
Control Switch (selector switch) | Std. Plans 661-3.01 | Y
Uninterruptible Power Supply Cabinet | See Detail in Plans 661-2.01 | Y
Uninterruptible Power Supply Controller | See Detail in Plans 661-2.01 | Y
Uninterruptible Power Supply Batteries | See Detail in Plans 661-2.01 | Y
Power Transfer Switch | Std. Plans 661-2.01 | Y
Meter Socket | Std. Plans 661-2.01 | Y
Manual Circuit Closing Device | 661-2.01 | Y
Circuit Breakers | Std. Plans 661-2.01 | Y
Galvanized Rigid Metal Conduit | Std. Plans 661-2.01 | Y
LOAD CENTER ASSEMBLIES:
Type 1 | Std. Plans 661-2.01 | Y
Type 1A | Std. Plans 661-2.01 | Y
Type 1A with UPS | See Details in Plans 661-2.01 | Y
Type 2 | Std. Plans 661-2.01 | Y
Type 3 | Std. Plans 661-2.01 | Y
TRANSFORMERS | 661-2.01 | Y
669 AUTOMATED TRAFFIC RECORDERS
JUNCTION BOXES:
Type II | See Detail in Plans 660-2.01 709-2.01 711-2.01 | N
Concrete Mix Design | 660-2.01 | N
Curing Materials | 711-2.01 | N
Reinforcing Steel | 709-2.01 | N
Junction Box Cover | See Detail in Plans 660-3.04 | N
Ground Wire from Bushing to Cover | See Detail in Plans 660-3.04 | N
CONDUIT / LOOPS:
Galvanized Rigid Metal Conduit | 740-2.06 | Y
Galvanized Couplings | 740-2.06 | N
Galvanized Split Couplings | 740-2.06 | Y
Galvanized Elbows | 740-2.06 | Y
Galvanized Nipples | 740-2.06 | Y
Bore Casing | 660-3.03 | N
Underground Marker Tape | 660-3.03 | N
Pull Rope | 660-3.03 | N
Schedule 80 PVC Conduit (Loops) | 740-2.06 | Y
PVC Fittings & Adapters (Loops) | 740-2.06 | Y
Type "X" Conduit Bodies with Covers, Gaskets & Plugs (Loops) | See Detail in Plans | Y
BONDING & GROUNDING:
Copper Ground Rod | See Detail in Plans 660-3.06 | Y
Grounding Bushings | 660-3.06 | Y
Ground Rod Clamps | 660-3.06 | Y
#6 & 8 Bare Copper Ground Wire | 660-3.06 | N
Braided Copper J-Box Lid Bonding Wire | 660-3.06 | Y
CONDUCTORS / CABLES:
1C#14 Detector Loops | 669-2.01 | Y
6pr#18 Loop Lead-in Cable | 669-2.01 | Y
CONTROLLER CABINET:
Style CBA2 Cabinet | 740-2.11 669-2.01 | Y
Terminal Blocks: | 669-2.01 | Y
Circuit Breaker Panel | 669-2.01 | Y
Transient Voltage Surge Protection | 669-2.01 | Y
Interior Light | 669-2.01 | Y
Cooling Fan | 669-2.01 | Y
Thermostatically Controlled Outlet | 669-2.01 | Y
110-volt Recepticals | 669-2.01 | Y
Heater | 669-2.01 | Y
Thermostat | 669-2.01 | N
SPLICES:
Overlap Type Crimp Connector | 660-3.05 | Y
Heat Shrink Tubing | 660-3.05 | Y
Electrical Tape | 660-3.05 | Y
DATA LOGGERS AND TEMPERATURE SENSORS:
Data Logger | 669-2.01 | N
External Interface | 669-2.01 | N
Serial Interface | 669-2.01 | N
Termocouple Referance Termistor | 669-2.01 | N
Road Temperature Thermocouple | 669-2.01 | N
Air Temperature Thermocouple | 669-2.01 | N
Radiation Shield | 669-2.01 | N
Telemetry Software | 669-2.01 | N
Vertical Temperature probe | 669-2.01 | N
ADDITIONAL COMPONENTS:
Piezoelectric Sensor | 669-2.01 | N
AS475 methyl grout for sensor | 669-2.01 | N
PSTN Modem | 669-2.01 | N
Remotely Controllable Code Operated Switch | 669-2.01 | N
Automated Vehicle Classification (AVC) Counter | 669-2.01 | N
ADDITIONAL MATERIALS: