- CR PROJECT PROVISIONS - QUICK REFERENCE GUIDE

(Delete guide doc from final Project Provisions)

Use aides for the CR Provisions All-inclusive Master document (Master Doc).

Guide Documents

Additional information is available in the Project Provision and Style Guides.

	Network Drive "hyd" on 'Aviation Ave File Server (hyperion)',

..\..\USERS\Specification_Provision_Guides

	ADOT FTP site:

http://www.dot.state.ak.us/creg/design/highways/specs/Specification_Provision_Guides/

Current Provisions

Please review the update notifications and confirm the latest provisions are used.

	Network Drive "hyd" on 'Aviation Ave File Server (hyperion)':

..\..\USERS\Update_Notice_Past_To_Present

	ADOT FTP Site:

http://www.dot.state.ak.us/creg/design/highways/specs/Update_Notice_Past_To_Present/

Table of Contents and Navigation Pane

Please inform the Specification Engineer of problems using the automated table of contents.

Show/Hide: to see formatting symbols and fields, select - Home/Paragraph Group/¶ (show/hide symbol)

	Turn on the Show/Hide formatting and field aide to avoid deleting established fields

1.	Navigate the document using the Navigation Pane.

	Select: View/Show/Navigation Pane (brings up the Nav Pane)

	Select: Click the Section Number and Title to go to each Section

	Delete a Section Number and Title in the document to remove it from the Navigation Pane.

2.	Navigate the document using the Table of Contents.

	Place arrow over section number and title

	Press Control and Select:  Section Number and Title to go to each Section,

	Delete a Section Number and Title in the document to remove it from the Table of Content

	Update TOC (Follow link to update TOC)

3.	Restore the Table of Contents.

a.	If you delete a line of the table of contents - Update TOC and the line will come back.

b.	If you delete the table of Contents, you can put it back.

Option 1 (before you edit the Master Doc add a custom table of contents to the table of contents gallery)

	Highlight the complete TOC including the title (TABLE OF CONTENTS) and column headings (Section & Page) through the body of the TOC.  Do not highlight the Section Break.

	Select: Reference/Table of Contents/Down Arrow/Save Selection to Table of Contents Gallery

	Type in the Name "CR Table of Contents" or similar, click ok,

To verify you have created a new table of contents follow the steps above and after the down arrow, you should see under "General" the new table of contents.  Once established this table will be available in your future documents.

Replace the lost/deleted TOC.

	Position the cursor in the location of the lost/deleted TOC and then select - Reference/Table of Contents/Down Arrow/General CR Table of Contents

This will put the TOC back into the document.  If you had removed and or added sections from the document, and you had updated the TOC, the replacement TOC will include the deletions and or additions.

Option 2 (copy and paste the Table of Contents from the Master Doc to the project provisions)

	Save a new Master Doc from the DOT network or DOT ftp site

	Highlight the complete TOC including the title (TABLE OF CONTENTS) and column headings (Section & Page) through the body of the TOC.  Do not highlight the Section Break.

	Position the cursor in the location of the lost/deleted TOC and then Paste

Be sure to copy all of the TOC otherwise you will paste in formatted text without the fields.

Be sure you are placing the cursor where the TOC was before being deleted and that there is a section break (follow the link to add a Section) before the TOC and after the TOC.

Common Tasks (other than typical editing, copy/paste etc.)

Creating project specifications from the Master doc requires deleting text boxes, deleting Sections, adding sections, or otherwise modifying the provisions.

1.	Remove a Text Box. (Blue box including instructions and recommendations)

	Place the mouse arrow over the perimeter of the box (a four-way arrow appears)

	Left click the perimeter of the box (perimeter is highlighted by corner dots & squares between)

	Press the delete key

2.	Remove a Section

	Highlight all text beginning "SECTION XXX" through the Section Break at the end of the Section

	Press the delete key (no changes to the other Sections should be required)

	Update TOC. (Follow link to update TOC)

3.	Add a New Section

a.	Insert Section Break

	Place the cursor immediately before a preceding section break or before the title of the following Section

	Select Page Layout/Page Setup/Breaks down arrow/Section Breaks/Next Page

b.	Update Header & Footer

(1)	Header – One and Two Page Headers

	Select Insert/Header & Footer/Header down arrow/Edit Header

	Do not link the headers.  If the header is linked, "Link to Previous" will be highlighted.  If linked, click on "Link to Previous" to remove the link and highlight.

	Change the second page header to the new Section number

(2)	Footers

	Select Insert/Header & Footer/Footer down arrow/Edit Footer

	Link footers. If footer is not linked, "Link to Previous," is not highlighted. Click on "Link to Previous" to link and highlight.

c.	Insert Body Text

	Enter the new Section text (body text) above the new section break

d.	Insert Section Number and Title. (centered, bold, and uppercase)

	Enter "Section XXX;" Enter two soft returns (Shift + Enter); Enter "Title"

e.	Assign Style to Section Number and Title

	Place the cursor in the Section title and select: Home/Styles/CR TOC 1 (section number and title will be added to the Navigation Pane)

f.	Place the TC fields after the title similar to other sections

	Copy the TC field from a previous Section and paste after the new Section title.

	Place the cursor in the field and edit the title (use sentence case) to match the new section title keeping the quotes ("), and the switches (\f) as they were pasted in.

	Update TOC. (Follow link to update TOC)

If the division field has been removed or provisions in a new division have been added follow a similar processs to adding the Section TC fields for the Division fields.

4.	Footer Project Name and Project Number

Option 1

	Replace the "Name-Title" with the project Name (Master Doc the "-" is excluded)

	Add after "Project-#" the Federal and or State (AKSAS) numbers (Master Doc the "-" is excluded)

	Copy Project Name and Project-# XXX. Paste over "Name-Title" and insert "Project-#" (approximately five places)

Option 2

	Select Home/Editing/Find. (Opens the Navigation Pane)

	Select the search box down arrow/Advance Find

Name-Title, Project-#

	Select Replace and fill in. Find What: with "Name-Title" and Replace With: with "The Project Name." Select the options as provided at the bottom of the window. Project-# similar to Name-Title

5.	Update TOC (Update the TOC after any heading change, etc.)

	Left click in the TOC (turns gray)

	Right click and select: Update Field/Update entire table

Content

1.	Comment/Instruction Boxes (blue text box)

When the comment/instruction has not been resolved, please leave the box in place.  When you remove the box, without a resolution, the reviewer does not know if you believe the issue is resolved, or you intend to provide resolution in the future.  Leaving the box also works as a reminder of issues to be resolved.  If you removed the box without resolving the issue, it is difficult to identify the issue for future resolution.

2.	Blank Space Infill

Fill in the blank spaces with information specific to each project.  When the condition does not apply, fill the blank space with "NA"; do not leave the space blank.  A blank space appears to the reviewer, and ultimately to the Contractor, that information is missing and the spec is incomplete.

3.	Project Specific Edits – Identifying

Identify edits to provisions as indicated in the Project Provisions – Guide, APPENDIX_F– Project Specific Edits – Identifying, is a good quick reference.

Warranties

1.	Any Federal funding - Warranties require Federal Highway Administration (FHWA) Division Administrators' approval.

a.	Alaska Department of Transportation and Public Facilities (DOT&PF) Standard Specifications for Highway Construction (SSHC) are FHWA approved.

b.	Special Provisions incorporating the SSHC warranty content are FHWA approved.

c.	Central Region (CR) special provisions, including project specific special provisions, may include warranties that fulfill, Warranties 3. Central Region Warranty Provision Requirements

2.	State of Alaska (SOA) funding only – Warranty requirements are similar to Warranties 3. Central Region Warranty Provision Requirements, except the FHWA Division Administrators' approval is not required.

3.	Central Region Warranty Provision Requirements - CR special provision warranties, including project specific warranties, require approval by both:

a.	The CR DOT&PF Highway Department Design Group Chief

b.	The FHWA Division Administrator (not required for SOA only funding).

Requirements

a.	Specific construction product or feature under the Contractor's control

b.	Reasonable

	Period - Industry standard, except 1-2 years typical and 5 years' maximum

	Performance - Industry standard

c.	Enforceable

	Clear, specific requirements

	Maintenance and Operations does not follow up on design project warranties

	Construction enforces the project requirements through Final Acceptance, 105-1.16

	There is no enforcement after Final Acceptance unless arranged during design

d.	Defensible – Highway Design Group Chief must be able to defend the warranty

	Routine maintenance is not permitted, is therefore not defensible

	Industry standard is defensible

	Value to the Federal government is defensible

e.	Submit the warranty and subsequent revisions to the Design Group Chief and if approved,

f.	Submit the warranty and subsequent revisions to the FHWA Division Administrator.

4.	Federal Highway Administration Regulations and Guidance Documents – Warranty Excerpts

Specific information is available from the included web site.

Federal Highway Administration

Code of Federal Regulations

https://www.fhwa.dot.gov/construction/cqit/warranty.cfm

Title 23 – Highways

Laws

23 USC 116 Maintenance

Regulations

635.413	Guaranty and warranty clauses

The STD may include warranty provisions in National Highway System (NHS) construction contracts in accordance with the following:

(a)	Warranty provisions shall be for a specific construction product or feature. Items of maintenance not eligible for Federal participation shall not be covered.

(b)	All warranty requirements and subsequent revisions shall be submitted to the Division Administrator for advance approval.

(c)	No warranty requirement shall be approved which, in the judgment of the Division Administrator, may place an undue obligation on the contractor for items over which the contractor has no control.

See actual document for further information including design-build project warranty requirements.

Policy

Contract Administration Core Curriculum Manual

FHWA policy – Section III.B.8.c.iv.b)5) Warranty

The length of a warranty is dependent on the surety industry's willingness to underwrite the warranty. In general, warranties tend to be restricted to a maximum of five years due to bonding and/or surety limitations.

SPECIAL NOTICE TO BIDDERS

Sect:  CRSNtB_SSHC2017		Related Sect/Sp: MCL, 101, 2, 3, 9/HSM18-1, 103/ES11 & Escrow, 105/CR105, 107/CR107, 108/CR108, 120/SSP38, 408/CR408,

651/CR651, 652/CR652

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room or for download online:

a.	Standard Specifications for Highway Construction, 2017 Edition ($25.00).  Available online at:

www.dot.state.ak.us/stwddes/dcsspecs/assets/pdf/hwyspecs/sshc2017.pdf

b.	Alaska Test Methods Manual (Lab & Field), July 15, 2018 Edition ($25.00). Available online at:

www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, March 2017.

www.dot.state.ak.us/stwddes/desenviron/resources/stormwater.shtml

d.	Utility facility clearance requirements. Available online at:

1d.	Applies to all projects with utilities work. Edit to project utility companies.

	Municipal Light & Power (ML&P) Electrical Facility Clearance Requirements www.mlandp.com/Portals/0/pdf/2014_electrical_facility_clearance_requirements%20Policy.pdf

	Chugach Electric Association, Inc. (CEA) Electrical Facility Clearance Requirements www.chugachelectric.com/system/files/images/energy-efficiency/2014_electrical_facility_clearance_requirements.pdf

	ENSTAR Natural Gas Company (ENSTAR)

www.enstarnaturalgas.com/safety-education/natural-gas-safety/safety-for-excavators-contractors/

e.	Quantity Computations

f.	Cross Sections

1f.	Not typically in resurfacing projects.

1e.	Not typically in resurfacing projects.

g.	Geotechnical Report,

1g.  Project Name		, Project No. 	, Month 	, Year 	. By 		(Company/Agency/Dept. etc.).

1f.  Project Name		, Project No. 	, Month 	, Year 	. By 		(Company/Agency/Dept. etc.).

h.	Hazardous Building Materials Surveys.

1h.	Include as applicable to project.

1g.	Include as applicable to project.

I.	Erosion, Sediment Control Plan (ESCP).

1i.	Project Name			, Project No. 		, Month 		, Year 	.

1h.	Project Name			, Project No. 		, Month 		, Year 	.

j.	Traffic Control Plan (TCP).

1j.	Project Name			, Project No. 		, Month 		, Year 	.  Place TCPs, not Professionally sealed, in the plans room.  Seal TCPs per Preconstruction Manual 1400.3.5, Jan 30, 2012, coordinate with the PM.

1i.	Project Name			, Project No. 		, Month 		, Year 	.  Place TCPs, not professionally sealed, in the plans room.  Seal TCPs per Preconstruction Manual 1400.3.5, Jan 30, 2012, coordinate with the PM.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix 		.

2.	Applies to all projects. Identify the appropriate appendix.

2.	Identify the appropriate appendix.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

3. Applies to all projects.

4.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  The Department, in coordination with US DOT, has adopted a Race-Neutral DBE Program effective for Federal-aid projects advertised in Central Region after June 30, 2015.  In particular, all bidders shall be aware that Good Faith Effort Documentation is required from the successful bidder for all contracts, regardless of DBE goal or DBE utilization, in accordance with Section 120 Disadvantaged Business Enterprise (DBE) Program.

4.	Disadvantaged Business Enterprise (DBE) Program – Include if Any FED funds. Exclude if SOA Only funds.

5.	Disadvantaged Business Enterprise (DBE) Program - applies to projects with any federal funding.

The overall DBE Utilization Goal is revised to 8.83 percent.

Direct questions about this notice to the Manager of the Civil Rights Office, (907) 269-0848, http://www.dot.state.ak.us/cvlrts/index.shtml.

5.	Cargo Preference Act Requirements. The provisions of the Cargo Preference Act (CPA) must be physically incorporated into all Federal-aid Projects awarded after February 15, 2016, and must be physically incorporated in all agreements with subcontractors and lower tier subcontractors.

5.	Cargo Preference Act Requirements (CPA). – Include if Any FED funds. Exclude if SOA Only funds.

5.	Disadvantaged Business Enterprise (DBE) Program - applies to projects with any federal funding.

Form 25D-55 (2/16) is revised to include the CPA provisions to the Required Contract Provisions for Federal-Aid Construction Contracts.  See the last page of Form 25D-55 for the CPA requirements.

For additional details, please visit: https://www.fhwa.dot.gov/construction/cqit/cargo.cfm

6.	Buy America Act. On December 22, 2015, U.S. District Court for the District of Columbia issued a decision vacating the Federal Highway Administration (FHWA) 90 percent threshold exemption for manufactured steel and iron products and the miscellaneous steel or iron components, subcomponents and hardware waiver.  As a result of the federal court decision, FHWA withdrew their December 21, 2012 policy memorandum clarifying provisions of the Buy America Act requirements.

6.	Buy America Act.  – Include if Any FED funds. Exclude if SOA Only funds.

5.	Disadvantaged Business Enterprise (DBE) Program - applies to projects with any federal funding.

7.	Utilities.

7.	Confirm inclusion with DOT CR Utility engineers each project.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0644.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

8.	Applies to projects in Eagle River and Girdwood.

8.	AWWU Discharge Permits.  AWWU is not issuing Temporary Construction Water Discharge Permits for construction related water routed to AWWU collection systems in both Girdwood and Eagle River.  Contractors are required to utilize alternative means to dispose of water from construction related activities.

9.	Laborers Mechanics Minimum Rate of Pay.  The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

9.	Applies to projects more than 65 miles from the Anchorage International Airport. See WHPL #197(A3), September 1, 2009.

10.	Interim Completion Phase.  This project includes at least one interim completion phase.  Refer to Subsection 651-1.05 Interim Completion and Subsection 652-1.05 Failure to Complete on Time for further information.

10.	See SNtB Summary Table Comments.

13.	See SNtB Summary Table Comments.  Included is an example.

11.	Section 408 and 703 Hard Aggregate.  Hot Mix Asphalt, Type VH requires hard aggregate.  Refer to the table in 703-2.04 Coarse Aggregate for the specified Nordic Abrasion value.  Material suppliers are also included in 703-2.04.

11.	Include when the project includes Hot Mix Asphalt, Type VH.

13.	See SNtB Summary Table Comments.  Included is an example.

12.	Asphalt Material Price Adjustment.  The unit price adjustment for asphalt material will be combined and paid under one Pay Item. Refer to Sections in Division 300 and 400 that include an "Asphalt Material Price Adjustment" Pay Item.

12.	Include when the project includes Asphalt Material Price Adjustment Pay Item.

13.	Escrow of Bid Documentation Affidavit.  Refer to Subsection 103-1.11 Escrow of Bid Documentation. The form "Escrow of Bid Documentation Affidavit" is included at the end of Subsection 103-1.11 and is required as part of this Contract.

13.	Application where project has high risk and or high cost and is design-bid-build. Coord w/ ES11, 103-1.11 & CREscrowBidAffidavit.

14.	Escrow of Proposal Documentation Affidavit.  Refer to Subsection 103-1.11 Escrow of Proposal Documentation.  The form "Escrow of Proposal Documentation Affidavit" is included at the end of Subsection 103-1.11 and is required as part of this Contract.

14.	Application where project has high risk and or high cost and is design-build. Coord w/ ES11, 103-1.11 & CREscrowProposalAffidavit.

15.	See SNtB Summary Table comments.

8.	See SNtB Summary Table comments.

15.	Solicitation Cancellation.

16.	Cross-Reference for Pay Item Numbers.  Pay item numbers in the Bid Schedule are cross-referenced to the pay item numbers in all other contract documents.  The cross-reference for pay item numbers is included in the Estimate of Quantities table on the plans.

16. Relates to HSM18-1-070118. Include in all projects.

17.	Limitation of Operation. Limit disturbed unstabilized ground. Refer to Subsection 652-1.04 Limitation of Operation for further information.

17. Limits the Contractor's amount of disturbed ground. Applies to all projects.

sRelates to HSM18-1-070118. Include in all projects.

FED_SOA-CRSNtB-010120_SSHC2017

| SPECIAL NOTICE to BIDDERS SUMMARY TABLE |  |  |
| --- | --- | --- |
| Include SNtB items based on funding and project requirements. |  |  |
| Publications. | 1a, b, c, d, e: All | 1f, g, h, i, j: Project Specific |
|  | 1.i: Placing the ESCP in the plans room removes the ESCP from the Contract documents. |  |
|  | 1.j: Preconstruction Manual 1400.3.5 Traffic Control Plan. Place TCPs, not professionally sealed, in the Plans Room. |  |
| Materials Certification List (MCL). | All |  |
| Environmental Documents. | All |  |
| Disadvantaged Business Enterprise (DBE) Program. Latest 070115 | Include if Any FED funds. Exclude if SOA Only funds. |  |
| Cargo Preference Act Requirements. | Include if Any FED funds. Exclude if SOA Only funds. |  |
| Buy America Act. | Include if Any FED funds. Exclude if SOA Only funds. |  |
| Utilities. | Project Specific |  |
| AWWU discharge Permits. | Project Specific |  |
| Laborers Mechanics Minimum Rate of Pay. | Project Specific |  |
| Interim Completion Phase. | Project Specific b. |  |
| Section 408 and 703 Hard Aggregate | Project Specific |  |
| Asphalt Material Price Adjustment (– Unit Price). | Project Specific |  |
| Escrow of Bid Documentation Affidavit. | Project Specific |  |
| Escrow of Proposal Documentation Affidavit. | Project Specific |  |
| Solicitation Cancellation. | Include if SOA Only funds, project specific a. |  |
| Cross-Reference for Pay Item Numbers. | All |  |
| Limitation of Operation | All |  |

a.	Rare use, confirm inclusion each project with DOT Central Region Contracting. Text for item "Solicitation Cancellation" and "American Recovery and Reinvestment Act of 2009 (ARRA)" is available in the:

1)  Network folder:  hyd on 'Aviation Ave File Server (hyperion)' - "Alpha:\SPECS\ALLSPECIALS\002-SOA-Solicitation Cancellation-102611"

2)  ADOT FTP:  http://www.dot.state.ak.us/creg/design/highways/specs.  Address is case sensitive.

b.	Include with projects requiring interim completion date(s).  If project requires interim completion dates, include CR105.5, CR651 and

CR108.3, CR652.  This is an example only, adjust for actual project requirements.

PART 4

STANDARD MODIFICATIONS
AND
SPECIAL PROVISIONS

Alaska Seal on Title Sheet Only.

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2017

Professional Seal is not required on the highway specification Title sheet.

EDITION

KEEP THIS PAGE

Blank Page

TABLE OF CONTENTS

Section	Page

DIVISION 100 — GENERAL PROVISIONS

101	Definitions and Terms No Change	3

102	Bidding Requirements and Conditions No Change	4

103	Award and Execution of Contract No Change	8

105	Control of Work No Change	15

106	Control of Material Section Place Holder	16

107	Legal Relations and Responsibility to Public No Change	17

108	Prosecution and Progress No Change	20

109	Measurement and Payment No Change	21

120	Disadvantaged Business Enterprise (DBE) Program No Change	22

DIVISION 200 — earthwork

201	Clearing and Grubbing No Change	25

202	Removal of Structures and Obstructions No Change	26

203	Excavation and Embankment No Change	31

204	Structure Excavation for Conduits and Minor Structures No Change	33

205	Excavation and Fill for Major Structures Section Place Holder	36

DIVISION 300 — BASES

301	Aggregate Base and Surface Course No Change	39

304	Subbase No Change	41

306	Asphalt Treated Base Course Tech Mod	42

318	Foamed Asphalt Stabilized Base Course No Change	54

DIVISION 400 — ASPHALT PAVEMENTS AND SURFACE TREATMENTS

401	Hot Mix Asphalt Pavement Tech Mod	63

406	Rumble Strips No Change	86

408	Hot Mix Asphalt Pavement – Type V Tech Mod	90

411	Intelligent Compaction Section Place Holder	112

DIVISION 500 — STRUCTURES

501	Structural Concrete Section Place Holder	115

502	Prestressing Concrete Section Place Holder	116

503	Reinforcing Steel Section Place Holder	117

504	Steel Structures No Change	118

505	Piling Format Mod	120

507	Bridge Railing Section Place Holder	122

508	Waterproofing Membrane Tech Mod	123

511	Mechanically Stabilized Earth Wall No Change	124

514	Concrete Surface Finish and Treatment No Change	130

515	Drilled Shafts Section Place Holder	132

516	Expansion Joints and Bearings Section Place Holder	133

520	Temporary Crossings Section Place Holder	134

DIVISION 600 — MISCELLANEOUS CONSTRUCTION

602	Structural Plate Pipe Tech Mod	137

603	Culverts and Storm Drains Tech Mod	138

604	Manholes and Inlets No Change	144

605	Underdrains Tech Mod	146

606	Guardrail Tech Mod	147

608	Sidewalks No Change	156

609	Curbing No Change	157

610	Ditch Lining No Change	158

611	Riprap No Change	159

615	Standard Signs Tech Mod	160

617	Railroad Crossings No Change	166

618	Seeding No Change	167

619	Soil Stabilization No Change	172

621	Planting Trees and Shrubs No Change	177

623	Vegetative Cover No Change	180

627	Water System No Change	183

630	Geotextile for Embankment and Roadway Separation, Stabilization and Reinforcement No Change	185

631	Geotextile for Subsurface Drainage and Erosion Control No Change	188

632	Paving Fabric No Change	191

633	Silt Fence No Change	192

634	Geogrid Soil Reinforcement No Change	193

639	Driveways No Change	195

641	Erosion, Sediment, and Pollution Control Tech Mod	197

642	Construction Surveying and Monuments No Change	228

643	Traffic Maintenance Tech Mod	233

644	Services to be Furnished by the Contractor Tech Mod	261

644-2.03 CURING SHED.	262

645	Training Program No Change	273

646	CPM Scheduling No Change	276

647	Equipment Rental No Change	277

651	Control of Work – Supplemental Requirements No Change	279

652	Prosecution and Progress – Supplemental Requirements No Change	283

654	Monitor No Change	285

660	Signals and Lighting No Change	286

661	Electrical Load Centers Tech Mod	289

662	Signal Interconnect No Change	299

667	Traffic Signal Communication System No Change	301

668	High Tower Lighting Section Place Holder	307

669	Automated Traffic Recorders No Change	308

670	Traffic Markings Format Mod	309

682	Utility Potholing No Change	314

690	Waterway Section Place Holder	316

DIVISION 700 — MATERIALS

702	Asphalt Materials Format Mod	319

703	Aggregates Tech Mod	320

705	Joint Material No Change	322

706	Concrete and Plastic Pipe No Change	323

710	Fence and Guardrail Tech Mod	324

712	Miscellaneous Format Mod	326

726	Topsoil Tech Mod	327

727	Soil Stabilization Material Tech Mod	329

729	Geosynthetics No Change	334

730	Sign Materials No Change	336

740	Signals and Lighting Materials No Change	338

Appendix A	Construction Survey Requirements

Appendix B	Environmental Permits

Appendix C	Material Certification List

Appendix D	Sign Shop Drawings

Appendix E	Temporary Construction Easements

DIVISION 100 — GENERAL PROVISIONS

	Keep this page to keep the page number field functioning when you remove a section..

"Likely" all projects will have a Division 100 provision. Keeping the Division 100 page, and following "Blank Page" will keep continuity between page numbers.  If the pages, "Divisions 100" and "Blank Page," are removed you will likely need to adjust the page numbering.  If you need assistance with the numbering contact the CR Specification and Estimate Engineer.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 101
DEFINITIONS AND TERMS

Sect 101 of HSM18-1.101.4-020819

Related Sect/Sp:  102, 103, 109 & SNtB e-bid

Standard Modification

101-1.01 GENERAL.

Add the following paragraph after the sixth paragraph:

Delete "Standard Drawing" throughout the Alaska Standard Specifications for Highway Construction and throughout the Alaska Traffic Manual Supplement and replace in both documents with, "Alaska Standard Plan".

101-1.03 DEFINITIONS.

Add the following definition:

ALASKA STANDARD PLAN. Detail Drawing adopted by the Department for repetitive use, showing details to be used where appropriate.

Delete the following definition:

STANDARD DRAWING.

HSM18-4-020819

Delete the definition for BID and replace with the following:

BID (OR PROPOSAL). The bidder's offer, on the prescribed forms, to perform the specified work at the prices quoted.

Add the following five definitions:

BID FORMS. Department-furnished forms that a bidder must complete and submit when making a bid in response to an advertised project. Bid forms may include a bid schedule, certification forms, acknowledgment forms, and other documents.

DIGITAL SIGNATURE. An electronic signature that conforms to the Uniform Electronic Transactions Act, AS 09.80.010 et seq.

ELECTRONIC BID. A bid that a bidder (i) prepares on the Department’s bid forms accessed through the Department’s approved online bidding service and (ii) submits to the Department through use of that bidding service’s online submittal process.

ELECTRONIC MAIL (EMAIL). A system for sending messages from one person to another via telecommunications links between computers or terminals using dedicated software.

MANUAL BID. A bid that a bidder (i) prepares on the Department’s bid forms accessed either through the Department’s approved online bidding service or obtained from the Department’s Regional Contracts Office and (ii) submits to the Department in physical paper form by hand delivery, U.S. Mail, or courier service.

HSM18-1.101-070118

SECTION 102
BIDDING REQUIREMENTS AND CONDITIONS

Sect 102 of  HSM18-1-070118.

Related Sect/Sp:  101, 103, 109 & SNtB e-bid from Statewide HSM18-1-070118

Special Provisions

Include ESO8 where more than 50% of the primary construction items is made up of electrical items.  See below.

102-1.01 QUALIFICATION OF BIDDERS.  After the last paragraph, add the following paragraph:

You must be registered as an Electrical Administrator, or must employ a person whose Electrical Administrator's license is assigned to you, under AS 08.40 at the time designated for bid opening.

ES08-063004

Standard Modification

HSM18-1.102-070118 Section 102.

102-1.05 PREPARATION OF BID.  Delete the subsection in its entirety and replace with the following:

A bidder shall prepare its bid using either the Department approved bid preparation software or the Department provided bid forms or legible copies of the Department’s forms. All entries shall be legible and in ink or type.

Bidders shall:

1.	Enter all prices required on the Bid Schedule, in figures;

2.	Enter a unit price for each contract item for which a quantity is given;

3.	Enter the products of the respective unit prices and quantities in the column provided;

4.	Enter lump sum prices for lump sum contract items in the column(s) provided; and

5.	Enter the total amount of all contract items for the basic bid and, when specified, any alternates.

When a bid item contains a choice to be made by the bidder, the bidder shall indicate a choice according to the Specifications for that item. No further choice is permitted.

The bid must be signed in ink or by a digital signature by the person or persons authorized to sign the Contract for the bidder. If a bidder is a corporation, the bid must be signed by a corporate officer or agent with authority to bind the corporation. If a bidder is a partnership, a partner must sign. If the bidder is a joint venture, each principal member must sign. If a bidder is a sole proprietorship, the owner must sign. Each person signing the bid must initial any changes made to entries on the bid forms.

A bidder submitting an electronic bid agrees that its digital signature constitutes a binding signature.

The bidder shall make no claim against the Department in the event it is unable to submit its bid through approved online bidding service and/or approved online bidding service is unable to submit the bid(s) to the Department. The Department reserves the right to postpone the public bid opening in the event of technical problems.

For multiple-project bid openings, the bidder may limit the total dollar amount or number of projects to be accepted by completing and attaching the following statement with its bid for at least one of the projects.  The Department will then determine which of the low bids it will accept, up to the total indicated.

“We wish to disqualify all of our successful bids at this bid opening which exceed the total of $_____________ or ____ contracts and hereby authorize the Department to determine which bids to disqualify, based on this limit.”

102-1.06 NONRESPONSIVE BIDS.  Delete the subsection in its entirety and replace with the following:

1.	A bid shall be rejected as nonresponsive if it:

a.	Is not properly signed by an authorized representative of the bidder and in a legally binding manner;

b.	Contains unauthorized additions, conditional or alternative bids, or other irregularities that make the bid incomplete, indefinite, or ambiguous;

c.	Includes a reservation of the right to accept or reject any award, or to enter into a contract pursuant to an award, except for an award limitation under Subsection 102-1.05;

d.	Fails to include an acceptable bid guaranty with the bid;

e.	Is materially unbalanced; or

f.	Fails to meet any other material requirement of the Invitation To Bid.

2.	A bid may be rejected as nonresponsive, in the Department's discretion, if it:

a.	Is not typed or completed in ink;

b.	Fails to include an acknowledgement of receipt of each addendum by assigned number and date of issue; or

c.	Is missing a bid price for any pay item, except when alternate pay items are authorized.

102-1.07 BID GUARANTY. Delete the subsection in its entirety and replace with the following:

Bids shall be accompanied by a bid guaranty in the amount specified on the Invitation To Bid. The guaranty shall be unconditionally payable to the State of Alaska and shall be in the form of an acceptable paper Bid Bond (Form 25D-14), an electronic bid bond acceptable to the Department and verified through its online bidding service, a certified check, a cashier's check, or a money order.

The surety of a Bid Bond may be any corporation or partnership authorized to do business in Alaska as an insurer under AS 21.09. A legible power of attorney shall be included with each paper Bid Bond (Form 25D-14).

An individual surety will not be accepted as a bid guaranty.

102-1.08 DELIVERY OF BIDS.  Delete the subsection in its entirety and replace with the following:

Bids shall be submitted electronically through the online bidding service, or shall be submitted in a sealed envelope. When bids are submitted in a sealed envelope, the envelope shall clearly indicate its contents and the designated address, as specified on the Invitation to Bid. Bids for other work may not be included in the envelope. In the event of a bid delay, electronic bidders that have already submitted their bid prior to the bid delay must resubmit their bid utilizing all Bid Forms EBSX Files or their bid will not be received.

The Department will not accept a bid submitted by email or fax unless specifically called for in the Invitation to Bid.

102-1.09 WITHDRAWAL OR REVISION OF BIDS. Delete the subsection in its entirety and replace with the following:

Manual Bids may be withdrawn or revised in writing delivered by mail, fax, or email , provided that the designated office receives the withdrawal or revision before the deadline stated in the in the Invitation To Bid. Withdraw requests must be signed and submitted by the bidder’s duly appointed representative who is legally authorized to bind the bidder. Revisions shall include both the modification of the unit bid price and the total modification of each item modified but shall not reveal the amount of the total original or revised bids.

Electronic Bids may be withdrawn or resubmitted through the online bidding service. Revisions to electronic bids delivered by mail, fax, or email will not be permitted. If electronic bid withdrawal is unsuccessful, electronic bids may be withdrawn in writing delivered by mail, fax, or email provided that the designated office receives the withdrawal before the deadline stated in the Invitation To Bid. Written withdrawal requests must be signed and submitted by the bidder’s duly appointed representative who is legally authorized to bind the bidder.

102-1.11 ADDENDA REQUIREMENTS. Delete the subsection in its entirety and replace with the following:

The Department will issue addenda if it determines, in its discretion, that clarifications or changes to the Contract documents or bid opening date are needed. The Department may send addenda by any reasonable method such as fax, email, or may post the addenda on its website or online bidding service. Unless picked up in person or included with the bid documents, addenda or notice that an addendum has been issued will be addressed to the individual or company to whom bidding documents were issued and sent to the email address or fax number on the plan holders’ list. Notwithstanding the Department’s efforts to distribute addenda, bidders are responsible for ensuring that they have received all addenda affecting the Invitation To Bid. Bidders must acknowledge all addenda on the Bid Forms, by fax, or by email before the deadline stated in the Invitation to Bid.

102-1.12 RECEIPT AND OPENING OF BIDS. Delete the subsection in its entirety and replace with the following:

The Department will only consider bids, revisions, and withdrawals received before the deadline stated in the Invitation to Bid.

The Department will assemble, open, and publicly announce bids at the time and place indicated in the Invitation to Bid, or as soon thereafter as practicable. The Department is not responsible for prematurely opening or failing to open bids that are improperly addressed or identified.

Add the following subsection:

102-1.14 ELECTRONIC MAIL Within its submitted bid, a bidder must include a current electronic mail (email) address of bidder’s representative who possesses authority to receive, process, and respond to Department emails regarding the advertised project.

The Department may send notices and information to a bidder by using the furnished email address of the bidder’s authorized representative.

A bidder shall notify the Department if the bidder requests the Department to send email notices or information to an address different from the email address initially provided in its bid forms. The bidder shall notify the Department of such change by sending a request in writing to the Contract’s point of contact identified on the Invitation to Bid that is signed by a representative who is authorized and empowered to legally bind the bidder.

Delivery of an email sent by the Department is complete upon receipt in the addressee’s email account. An email sent after 4:30 pm shall be deemed to have occurred at the opening of business on the next working day.

If needed, the Department may demonstrate proof of email delivery by affidavit or certification that includes the following:

1.	The date and time that the Department sent the email message;

2.	The email address from which the Department sent the message;

3.	The name and email address to which the Department sent the message;

4.	A statement that the Department sent the email message and that the person signing the affidavit or certification believes the transmission to have been complete and without error; and

5.	An attached copy of the subject email.

HSM18-1.102-070118

For all highways projects advertised after December 20, 2010, include Statewide Special Provision ES 08 when more than fifty percent of the "primary construction items" in the engineer's estimate (for the construction contract) is made up of the sum of the load center, highway illumination system, traffic signal system, traffic data collection, and ITS items.  Construction Engineering and project development costs are not included in the engineer's estimate for the construction contract.

"Primary construction items" are ALL bid items EXCEPT:

Mob/Demob (640)

Erosion, Sediment & Pollution Control (641)

Construction Surveying & Monuments (642)

Traffic Maintenance (643)

Services to be Furnished by the Contractor (644)

Training (Apprentice) program (645)

CPM Scheduling (646)

Contractor Quality Control (When paid for as a separate bid item)

Example:

E (Sum of all "electrical" items) = Total Estimate amount for the sum of all the load center, highway illumination system, traffic signal system, traffic data collection, and ITS items that will be included in the Contract.

PCIh (primary Construction Itemshighways) = Total Contract Estimate minus 640, 641, 642, 643, 644, 645, 646, and Contractor QC items.

Include Statewide Special Provision ES 08 if:

(E)  is greater than 50%

(PCIh)

SECTION 103
AWARD AND EXECUTION OF CONTRACT

Sect 103, of HSM18-1-070118, ES11 and Escrow of Bid Affidavit and Escrow of Proposal affidavit

Related Sect/Sp:  101, 102, 109 & SNtB e-bid from Statewide HSM18-1-070118

Related Sect/Sp: ES11 FED & SOA funded Proj.  Escrow of Affidavit form is at end of ES11, 103-1.11. See instructions with Affidavit form.

Standard Modification

HSM18-1.103-070118 Section 103.

103-1.01 CONSIDERATION OF BIDS. Delete the subsection in its entirety and replace with the following:

After the bids are opened and read, the bids will be mathematically checked and compared on the basis of the sum of the products of the bid schedule quantities and the unit bid prices. The unit bid prices govern if there is an error in extending the unit bid prices, or in totaling the extensions, or if an extension is missing. The results of the bid comparisons will be made available to the public as soon as practicable.

Until the Award, the Department may reject any or all bids, waive minor informalities or advertise for new bids without liability to any bidder if the Department, in its discretion, determines that to do so is in the best interests of the State.

A bidder may request withdrawal of a bid after opening and before the Award only in accordance with AS 36.30.160(b) and State procurement regulations. Submit the request to the Contracting Officer.

An interested party, as defined in AS 36.30.699, may protest a proposed Award of contract as per AS 36.30.560 and AS 36.30.565. Submit the protest to the Contracting Officer.

WHOLLY STATE-FUNDED PROJECTS. On wholly state-funded projects, determination of the low bidder will include bidder preferences as required under AS 36.30.321, according to subsections 1-3 below. Alaska Bidder Preference, Alaska Veteran Preference, and Alaska Product Preference are not applicable on projects with federal funding.

1.	Alaska Bidder Preference: A bidder claiming this preference shall provide with their bid an Alaska Bidder Preference Certification, certifying they qualify as an Alaska bidder eligible for Alaska Bidder Preference according to AS 36.30.

If the bidder qualifies as an Alaska bidder, a five percent (5%) preference will be applied to the price of the bid. "Alaska bidder" means a person who:

a.	holds a current Alaska business license;

b.	submits a bid for goods, services, or construction under the name as appearing on the person's current Alaska business license;

c.	has maintained a place of business within the state staffed by the bidder or an employee of the bidder for a period of six months immediately preceding the date of the bid;

d.	is incorporated or qualified to do business under the laws of the state, is a sole proprietorship and the proprietor is a resident of the state, is a limited liability company organized under AS 10.50 and all members are residents of the state, or is a partnership under former AS 32.05, AS 32.06, or AS 32.11 and all partners are residents of the state; and

e.	If a joint venture, is composed entirely of ventures that qualify under (a) through (d), above.

2.	Alaska Veteran Preference: A bidder claiming this preference shall provide an Alaska Veteran Preference Certification, certifying they qualify as an Alaska bidder eligible for Alaska Veteran preference according to AS 36.30.

If a bidder qualifies as an Alaska bidder and is a qualifying entity, an Alaska Veteran Preference of 5 percent shall be applied to the bid price. The preference may not exceed $5,000 (AS 36.30.321). A “qualifying entity” means a:

a.	sole proprietorship owned by an Alaska veteran;

b.	partnership under AS 32.06 or AS 32.11 if a majority of the partners are Alaska veterans;

c. 	limited liability company organized under AS 10.50 if a majority of the members are Alaska veterans; or

d. 	corporation that is wholly owned by individuals, and a majority of the individuals are Alaska veterans.

A preference under this section is in addition to any other preference for which the bidder qualifies.

To qualify for this preference, the bidder must add value by the bidder itself actually performing, controlling, managing and supervising a significant part of the services provided or the bidder must have sold supplies of the general nature solicited to other state agencies, governments, or the general public.

An Alaska veteran is a resident of Alaska who:

(1)	served in the Armed forces of the United States, including a reserve unit of the United States armed forces; or the Alaska Territorial Guard, the Alaska Army National Guard, the Alaska Air National Guard, or the Alaska Naval Militia; and

(2)	was separated from service under a condition that was not dishonorable.

3.	Alaska Product Preference: A bidder claiming this preference shall complete and sign the Alaska Product Preference Worksheet, according to the worksheet instructions, and submit the completed worksheet with their bid.

Except for timber, lumber and manufactured lumber products used in the construction project under AS 36.30.322(b), an Alaska products preference will be given as required under AS 36.30.326 - 36.30.332 when the bidder designates the use of Alaska products.

If the successful bidder/contractor proposes to use an Alaska product and does not do so, a penalty will be assessed against the successful bidder/contractor according to AS 36.30.330(a).

Each Alaska product declared on the Alaska Product Preference Worksheet must have an “Approval” date on the Alaska Product Preference Program List, that is on or before the bid opening date for this contract, and that does not expire before the bid opening date for this contract.

103-1.03 AWARD OF CONTRACT. Delete the subsection in its entirety and replace with the following:

The Department will award the Contract to the lowest responsible and responsive bidder unless it rejects all bids. The Department will notify all bidders in writing via email, fax, or U.S. Mail of its intent to award.

The Department will notify the successful bidder in writing of its intent to award the Contract and request that certain required documents, including the Contract Form, bonds, and insurance be submitted within the time specified. The successful bidder's refusal to sign the Contract and provide the requested documents within the time specified may result in cancellation of the notice of intent to award and forfeiture of the bid security.

If an award is made, it will be made as soon as practicable and usually within 40 days after bid opening. Award may be delayed due to bid irregularities or a bid protest, or if the award date is extended by mutual consent. Bids shall be valid for 120 days after bid opening, and may be extended by mutual consent.

HSM18-1.103-070118

Special Provisions

Add the following Subsection 103-1.011 Related Sections:

Add the following subsection:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of the Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and information used to prepare the Bid for this project.

ES11 application is high risk and or high cost. Use w/"ESCROW" Affidavit form at end of ES11. See instructions with Escrow Affidavit form.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department designated document depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that

a.	the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

b.	the sealed container contains all bid documentation submitted,

c.	the escrow materials were relied on to prepare the bid, and

d.	should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least 5 days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of escrow documentation (whether hard copy, electronic, or otherwise); to use and review copies consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders the bid non-responsive.  Failure or refusal to provide subcontractor bid documentation will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are the Contractor’s property.  Except as otherwise provided herein, the escrow materials cannot be released without the Contractor’s approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to the Contractor once litigation is concluded, outstanding claims are resolved, the Contractor has completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11-010106

Blank Page

EscrowBid/Proposal Affidavit: When including the Escrow Affidavit form leave the page before and after blank.

ESCROW OF BID DOCUMENTATION AFFIDAVIT

Application where the project has high risk and or high cost.  Verify with the Regional Chief of Construction if "Escrow of Bid or Proposal Affidavit" is required.  If required the central region Contracts department will contact the Chief Contracts Officer for approval.  The form included here is for design-bid-build.  If the project is design-bid-build use this form with the consent of the regional Contracts Department.

For more information regarding high cost and high risk follow the link below to Specification Transmittal 02-1, February 22, 2002:

http://www.dot.state.ak.us/stwddes/dcspubs/assets/pdf/directives/022602_spec02_1.pdf

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF BID DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE BID AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE BID PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

CREscrowBidAffidavit-050509

ESCROW OF PROPOSAL DOCUMENTATION AFFIDAVIT

Sect: Escrow/103	When using escrow affidavit Keep on its' own Sheet, blank on one side

Related Sect/Sp:  ES11 FED & SOA funded projects and Special Notice to Bidders.

Application where the project has high risk and or high cost.  Verify with the Regional Chief of Construction if "Escrow of Bid or Proposal Affidavit" is required.  If required the central region Contracts department will contact the Chief Contracts Officer for approval.  If the project is design-build use this form with the consent of the regional Contracts department.

For more information regarding high cost and high risk follow the link below to Specification Transmittal 02-1, February 22, 2002:

http://www.dot.state.ak.us/stwddes/dcspubs/assets/pdf/directives/022602_spec02_1.pdf

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF PROPOSAL DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE PROPOSAL AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE BID PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

CREscrowProposalAffidavit-050509

Blank Page

EscrowBid/Proposal Affidavit: When including the Escrow Affidavit form leave the page before and after blank.

SECTION 105
CONTROL OF WORK

Sect 105. Section Specials: CR105.5, CR105.7. CR105.5 is the result of SSP9

Related Sect/Sp:  SNtB, 105, 108, 651, 652

Special Provisions

The following instructions are the same as occur in Section 651.

Section 105 Control of Work, and Section 651 Control of Work – Supplemental Requirements

	There are no Standard Modifications or Statewide Special Provisions for Sections 105 and 651.

	Provisions intended for Section 105, except CR105.5 and CR105.7, are placed in Section 651 as noted below.

Region and Project Provisions

You will always include the Central Region special provision CR105.7. This provision is outside the instruction that follows.

1.	If you do have region or project provisions for Section 105/Section 651, proceed to Step 2 (nearly always), otherwise you are now done with Section 105 and Section 651.

2.	If you do have project provisions for Section 105 that modify Section 105, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 105 proceed to Step 3 (nearly always), otherwise you are now done with Section 105 and 651.

3.	If you do have region provisions that modify or add to Section 105, or project provisions for Section 105 that add to Section 105, include CR105.5 and CR651 as follows:

a.	In Section 105 include CR105.5

b.	In Section 651, CR651:

(1)	Region provisions identified by subsection:

(a)	651-1.01 Description (always include)

(b)	651-1.02 Related Sections (always include)

(c)	651-1.03 Utilities (include when applicable)

(d)	651-1.04 Cooperation Between Contractors (include when applicable)

(e)	651-1.05 Interim Completion (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	651-1.01 – 1.05 add to or modifying region provisions

(b)	651-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.

Add the following Subsection 105-1.011 Related Sections:

105-1.011 RELATED SECTIONS.

Section 651, Control of Work – Supplemental Requirements

CR105.5-012816

105-1.15 PROJECT COMPLETION.

3rd paragraph 1st sentence, replace: "621-3.04" with "618-3.06 and 621-3.04"

CR105.7-042015

SECTION 106
CONTROL OF MATERIAL

Sect  106:  CR106.1

Related Sect/Sp:  101, 105, 200, 300, 400, 500, 600, 700

Use Provision CR106.1 Covered Loads, as is, when a specific project requires covered loads. The regional special is available as an individual file in the Allprovisions folder and in the Project_Specific_Specials folder. Covered loads are the exception.

SECTION 107
LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Sect  107:  CR107.1.2.3. (CR107.2 incorporates 1.02 from the SSHC2017 with minor edits and editions)

Related Sect/Sp:  SNtB,

Related Sect/Sp:

Special Provisions

Replace Subsection 107-1.02 Permits, Licenses, and Taxes with the following:

107-1.02 PERMITS, LICENSES, AND TAXES. The terms, conditions, and stipulations in permits obtained either by the Department or by the Contractor are made a part of this Contract. Permits obtained by the Department for this project are attached to these Specifications as appendices. Contact names and phone numbers for permits obtained by the Department are shown on the individual permits.

The Department will:

1.	Secure permits and licenses that the Department determines are required for the construction of the proposed project, and the use of mandatory sources, designated sources and designated material disposal areas for the proposed project; and

2.	Modify Department-acquired permits during the performance of the contract, if deemed necessary by the Engineer.

Where ARRC draft permit is required, include it in an appendix.  Add information below similar to other permits.  The ARRC permit includes their specification; do not include a DOT specification.

3.	The Department has received the following permits on the Contractor's behalf:

3. Fill in the permits as received by the Department.  If no permits remove "3.  The Department has" including a. and b.

a.

b.

The Contractor shall:

1.	Acquire any permits and licenses required to complete the project that are not acquired by the Department;

2.	Provide qualified professionals to collect data or perform studies necessary to acquire permits for the use of sites not previously permitted;

3.	Give all notices required for the prosecution of the work;

4.	Abide by all permits and licenses whether acquired by the Department or by the Contractor;

5.	Notify the Engineer promptly if any activity cannot be performed as specified in the permits, and cease conducting the activity until permit modifications or any required additional permits are obtained;

6.	Obtain modifications to permits acquired by the Contractor;

7.	Pay all charges, fees and taxes;

8.	Provide proof of payment of all taxes before the Department makes final payment; and

9.	Provide the information necessary to comply with the Alaska Department of Environmental Conservation, Alaska Pollutant Discharge Elimination System (APDES) to discharge storm water from the construction site.  Requirements for this permit are given under Section 641, Erosion, Sediment, and Pollution Control.

10.	Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

11.	A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

11. Add the Right-of-Way use permit when in and required by the Municipality of Anchorage.

The provisions of permits acquired by the Contractor, and of notices and information under this section does not shift or create responsibility for compliance with Federal or State law to the Department, or otherwise impose a duty for oversight or review.

In addition, before using an area on or off project site not previously permitted for use by the Contract, the Contractor shall:

1.	Contact all government agencies having possible or apparent permit authority over that area;

2.	Obtain all required permits, clearances, and licenses from those agencies;

3.	Obtain permission from any property owners or lessees with an interest in the property; and

4.	Provide all of the following to the Engineer:

a.	All permits or clearances necessary to use the site for its intended purpose(s);

b.	A written statement that all permits or clearances necessary have been obtained;

c.	Written evidence that the Contractor has contacted all of the relevant agencies and that no additional permits are required on the part of the Contractor, including at a minimum the name of the agency and staff person contacted, the date contacted, and result of coordination; and

d.	A plan that identifies how the site will be finally stabilized and protected.

The Engineer may reject a proposed site if the Contractor fails to provide any of the above information or to demonstrate that a proposed site can be finally stabilized to eliminate future adverse impacts on natural resources and the environment.

CR107.2-120117.SSHC2017

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Replace the 1st sentence including numbers 1, 2, and 3, with:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following:

Non-municipal Water Source. If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR107.3-051517

Add the following:

Eagles. Confirm applicable with project manager and environmental analyst.

E65 include in FED and SOA funded projects.

Eagles.  Eagles are protected under 16 U.S.C. 668-668c Protection of Bald and Golden Eagles, that prohibits “takes” of eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of minimum 330-feet as an undisturbed habitat buffer around nesting eagles.  If topography or vegetation does not provide an adequate screen or separation, extend the buffer to 1320-feet, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330-feet and 660-feet from a nest tree, no obtrusive facilities, or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, extend the buffer up to 2640-feet.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (February 1 – August 31) within the primary or secondary zones.

Do not disturb a nesting eagle.  Notify the Engineer when an active eagle nest is within the primary or secondary zones.

CR107.1-100118

SECTION 108
 PROSECUTION AND PROGRESS

Sect 108: CR108.3, SSP58.108.SSHC2017

Related Sect/Sp:  SNtB, 105, 651, 652

Related Sect/Sp:

Special Provisions

SSP58.108.SSHC2017-030117. 108-1.01.1h. and 2g, use when SOA only funded.

108-1.01 SUBCONTRACTING OF CONTRACT.

Replace Subsection 108-1.01 1h. with the following:

1h.	Other required items listed in Form 25D-042 are included in the subcontracts;

Replace Subsection 108-1.01 2g. with the following:

2g.	Other required items listed in Form 25D-042, are included in the lower tier subcontracts;

SSP-58.108.SSHC2017-030117

Add the following Subsection 108-1.011 Related Sections:

CR108.3. Reference to Section 652 from 108-1.011, see the text box below for instructions.

108-1.011 RELATED SECTIONS.

Section 652, Prosecution and Progress – Supplemental Requirements

CR108.3-012816R

The following instructions are the same as occur in Section 652.

Section 108 Prosecution and Progress, and Section 652 Prosecution and Progress – Supplemental Requirements

	There are no Standard Modifications for Sections 108 and 652.

	Provisions intended for Section 108, except CR108.3, are placed in Section 652 as noted below.

Region and Project Provisions

1.	If you do have region or project provisions for Section 108/Section 652, proceed to Step 2 (nearly always), otherwise you are now done with Section 108 and Section 652.

2.	If you do have project provisions for Section 108 that modify Section 108, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 108 proceed to Step 3 (nearly always), otherwise you are now done with Section 108 and 652.

3.	If you do have region provisions that modify or add to Section 108, or project provisions for Section 108 that add to Section 108, include CR108.3 and CR652 as follows:

a.	In Section 108 include CR108.3

b.	In Section 652, CR652:

(1)	Region provisions identified by subsection:

(a)	652-1.01 Description (always include)

(b)	652-1.02 Related Sections (always include)

(c)	652-1.03 Prosecution and Progress (include when applicable)

(d)	652-1.04 Limitations of Operations (always include)

(e)	652-1.05 Failure to Complete on Time (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	652-1.01 – 1.05 add to or modifying region provisions

(b)	652-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.

SECTION 109
MEASUREMENT AND PAYMENT

Sect  109: e-bid specials from Statewide. HSM18-1-070118.CR109.2.3

Related Sect/Sp:  101, 102, 103, & SNtB e-bid from Statewide HSM18-1-070118

Related Sect/Sp:

Standard Modification

HSM18-1.109-070118 Section 109.

109-1.01 GENERAL. Insert the following after the second paragraph:

Pay item numbers in the Bid Schedule are cross-referenced to the pay item numbers in all other contract documents.  The cross-reference for pay item numbers is included in the Estimate of Quantities table on the plans.

HSM18-1.109-070118

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Replace item, "14. Weighing Procedures" with "Weighing Procedures".  "Weighing Procedures" is a subtopic under item "13. Ton (2,000 pounds)."

CR109.3-042015

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

Provide a printed copy of the current EquipmentWatch rate sheet for each piece of equipment utilized on time and materials work.

CR109.2-110118

SECTION 120
DISADVANTAGED BUSINESS eNTERPRISE (DBE) PROGRAM

Sect 120.	CR120.1.SM3-122217.	CR120.1.-030117.SSHC2017 Replaced SSP-38.SSHC2017-030117)

Related Sect/Sp:

Related Sect/Sp:

Special Provisions

CR120.1-030117.SSHC2017. Include if SOA Only funds.

Delete Section 120 Disadvantaged Business Enterprise (DBE) Program.

CR120.1-030117.SSHC2017

Special Provisions

SM3. Include if Any FED funds.  Exclude if SOA Only funds.

.

120-1.01 DESCRIPTION.

Delete the second paragraph of Subsection 120-1.01 and replace with the following:

The Department, in coordination with the Federal Highway Administration (FHWA), adopted a Race-Neutral DBE Program with an overall DBE Utilization Goal of 8.83 percent for Alaska’s FHWA Federal-Aid program.  Although the Race-Neutral program does not establish or require individual project DBE Utilization Goals, 49 CFR establishes the Bidder is responsible to make a portion of the work available to DBEs and to select those portions of the work or material needs consistent with the available DBEs to facilitate DBE participation.

SM3-122217.SSHC2017

DIVISION 200 — EARTHWORK

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 201
CLEARING AND GRUBBING

Sect 201: CR201.1.2.3

Related Sect/Sp:

Related Sect/Sp:

If you have CR2012 you will include CR2013.  You may have CR2013 without CR2012.

Special Provisions

201-3.01 GENERAL.  Add the following:

CR2012.  Inclusion of this special is based on quantity of firewood available.  Discuss with the Engineer and include based on discussion.

Timber for Public Removal.  Cut timber, with a 5 inch diameter or larger at breast height, into 8 foot lengths, de-limbed, and stacked to a height no greater than 6 feet.  Place the stacks at locations shown in the Plans, included in Specifications or at other locations approved by the Engineer.  Make locations adjacent to the nearest turnout, side street, or other approved site that does not create a traffic hazard due to lack of adequate parking for the public.  Access to the site(s) shall be maintained and controlled by flaggers, in accordance with Subsection 643-3.04.  The Contractor shall provide and maintain a separate firewood telephone hotline that details when and where the wood is available to the public.  Special Construction signs, in accordance with Subsection 643-2.01, shall be used to advertise the firewood telephone hotline.  Provide two weeks for the public to access each area of the project where timber is made available. Dispose of the timber left by the public after the two week time period.

Mechanical loading by the public is not permitted.

CR201.2-010114

Add the following:

Perform the work necessary to preserve and/or restore land monuments and property corners from damage.  Restore land monuments and/or property corners that are disturbed according to Section 642.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

3.01 Above: Confirm ROW mapping is available.  If ROW mapping is not available remove the last sentence.  Discuss with the Const Engineer.

CR201.3-042313

CR201.1.  Verify the bird window dates with project location.

Add the following:

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws when approved by the Engineer.

CR201.1-010114

201-5.01 BASIS OF PAYMENT.  Add the following:

The work required to cut, de-limb, and stack timber for public removal is subsidiary to 201 Pay Items.

CR201.2-010114

Add the following:

The work required to preserve and restore land monuments and property corners is subsidiary to 201 Pay Items.

CR201.3-042313

SECTION 202
REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Sect 202: CR202.1.2.3.4.5.6.

Related Sect/Sp:  202, 306/CR306, 401/CR401, 408/CR408

Related Sect/Sp:

Special Provisions

202-1.01 DESCRIPTION.  Add the following:

Remove gas pipe, remove storage tanks (either fuel or septic) and abandon ground water wells.

Remove gas pipe, remove storage tanks (either fuel or septic) and decommission ground water wells.

Use paragraph below in place of the paragraph above when DEC requires decommissioning of Ground Water Wells in place of abandonment.

CR202.5R-010610

Add the following:

Pavement Planing.  Remove, and or reuse, or dispose of planed pavement materials as noted herein.

Include CR202.1 when using CR202.3.

CR202.3-071519

Add the following:

Fugitive Materials.  Remove and dispose of fugitive materials from under guardrails, around luminaire bases, and as specified in this section.  Conduct a pre-construction inspection of the project area with the Engineer to determine the limits of the fugitive material removal and disposal work.

Use CR202.4 for the removal of fugitive materials (debris, sand) around the guardrail posts.

202-2.01 MATERIALS. Add the following:

Fugitive Materials.  Including but not limited to organic matter (peat, roots, sticks, sod or other), muck, earth (where not part of surface material) rocks, gravel, sand, silts and debris (trash and similar) and as identified by the Engineer.

CR202.4R-092612

202-3.01 GENERAL.  Add the following:

Removal of buildings, foundations, and structures includes removal of utility lines, sidewalks, and other attached appurtenances.

Buildings may contain asbestos.  Take special handling measures when removing this material.

Cut the ends of retaining walls to remain after partial removal neat and true with no shatter outside the removal area.

Remove septic or fuel tanks according to the Department of Environmental Conservation (DEC) regulation.  Remove or abandon wells according to DEC regulations.

The building located on parcel No. ______ removed by others.  If advance removal of this building is required, remove and dispose of the building foundation, utility lines, and other attached appurtenances.  This work paid on a time and materials basis according to subsection 109-1.05 Compensation for Extra Work.

CR202.5R-010610

Add the following:

Carefully remove fences designated by the Engineer to the right-of-way limit, or to the end of the span beyond the right-of-way limit.  These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After the construction of noise barrier or fence is complete, use salvaged fencing to fill possible fencing gaps behind the property line.  Use salvaged fencing according to Section 607, for reconstructed fences.

CR202.6R-102402

202-3.04 REMOVAL OF PIPE.  Add the following:

During project construction, ENSTAR Natural Gas Company will abandon existing gas pipelines.  Follow the procedures given in Subsection 105-1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned.  Once the pipelines are abandoned, remove abandoned natural gas pipe within the right-of-way that are in conflict with the work and dispose of pipes off the project limits.

CR202.5R-010610

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:

Removed pavement material, including sidewalks and curbs, is the property of the Contractor.  Handle and transport materials according to the Alaska Department of Environmental Conservation (DEC) regulations.  Store materials at a Contractor DEC approved site.

Include CR202.1 when using CR202.2.

The use of pavement, sidewalk, and curb in the embankment requires written approval and direction for use from the Engineer. Maximum allowed dimension of broken material is 6 inches.  Bury the material below the finished surface.

Dispose of removed pavement, sidewalks, and curbs not wanted by the Contractor and not used in the project, according to Subsection 3.09.

CR202.2R-010610

Add the following Subsection 202-3.06:

202-3.06 PAVEMENT PLANING.

Remove existing asphalt pavement by cold planing. Adjust the planing machine to remove all ruts in the roadway surface and as directed. Plane a uniformly fine milled textured surface.

Remove planed material from the project immediately after planing according to Subsection 202-3.05 Removal of Pavement, Sidewalks, and Curbs, and dispose of planed material not accepted by the Maintenance Station, not used in the project, and not wanted by the Contractor according to Subsection 3.09 Disposal of Pavement, Sidewalks, and Curbs.

Designer, contact the Maintenance Dept. and local M&O Station and confirm they do (and how much) or do not want planed material.

Notify the Engineer of pavement areas that may be thin or unstable. When the planing equipment breaks through the existing pavement, repair the pavement as specified in Sections 401 and 408. Repair with Section 401 HMA; Type II, Class B, except use the HMA type specified for the immediate layer of HMA above the planed surface when Type II, Class B HMA is not included in the project.

The pavement material planed from the project roadway (X cubic yards) is the property of the Department. Planed material not claimed by the Department is the property of the Contractor.

If the M&O Station has a material limit note the limit inside the (), this includes "0", and if no limit remove the () and everything in the ().

If the M&O Station has a limit of "0" leave the "NA" in the blanks below, otherwise fill in each blank.

Stockpile the Department's planed material at the 	NA	 maintenance station located at 	NA	. Coordinate with 	NA	, Maintenance Foreman, telephone number 	NA	 for acceptance of material and desired location of stockpile.

Planed material may be used in the project with written approval. The material may be used:

	In the embankment construction, Section 203,

	As shoulder buttressing, Section 301,

	As recycled asphalt pavement, Section 306,

	As directed.

During planing operations, sweep the streets according to 643-3.04 Traffic Control Devices, No. 6. Street Sweeping and Power Brooming to control dust and remove loose material from the planed areas.  The removal operation shall follow within 50 feet of the planing machine.

Do not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 2 inches.  Place an asphalt pavement transition, 2 feet in width, adjacent to the edge and to gutters.

Where existing asphalt pavement overlays gutters adjacent to the area planed, remove the existing pavement.

Do not damage or disturb the existing curb, gutter, and edge of existing Portland cement pavement not designated for removal.  Remove and replace damage caused by the Contractor's planing operation at the Contractor’s expense.

Provide a capable planing machine:

1.	Self-propelled and capable of milling at speeds from 0 ft to 40+ ft per minute.

2.	Able to spray water inside the milling chamber to reduce dust.

3.	Able to mill adjacent to a gutter without damaging gutter.

4.	Automatic cross slope and depth control combined with automatic longitudinal grade control actuated by sonic or laser ski sensors.

5.	Produce a "fine milled" textured surface with a tool spacing of 5/16 inch.

6.	Able to uniformly maintain a planar surface across adjacent lanes (no elevation differential or ridges between adjacent passes).

Provide a small machine (producing a "fine milled" textured surface) to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.

The Engineer may reject any machine that does not comply with the above noted requirements.

CR202.3-071519

Add the following Subsection 202-3.07:

202-3.07 GROUND WATER WELL DECOMMISSIONING.  Decommission the water wells according to DEC requirements conforming to 18AAC 80.015 Well Protection Source Water Protection, and Well Decommissioning, or a DEC approved alternate method.  Develop and submit a detailed Ground Water Well Decommissioning Plan to the Engineer.  Contact the 		[City]	  DEC office at (907) ###-####, for plan review requirements of alternate methods.

CR202.5R-010610

Add the following Subsection 202-3.08:

202-3.08 REMOVAL OF FUGITIVE MATERIALS.  Remove fugitive materials from in front of, under, and for a width of 10 ft behind sections of guardrail, measured from the roadside face of guardrail, or as directed by the Engineer.  Provide positive drainage away from the roadway.  Slope edges of sand removal at 3:1 or flatter.

Clean around the base of a luminaire when the base falls within the 10 ft.  The 10 ft width is measured from the roadside face of the guardrail toward the shoulder to the closest point of the luminaire base plate, or as directed by the Engineer.  Remove fugitive materials from around the base to a level flush with surrounding ground - or as directed by the Engineer.

Remove disturbed materials in the same work shift the disturbance occurred.

Removed materials are the property of the Contractor.  Do not reuse these materials within the project limits without the written approval of the Engineer.

Dispose of removed materials at the Municipality of Anchorage Hazardous Materials Waste Disposal site or similar as required dependent on the type of materials and as required by the Federal, State, and Municipal environmental regulations.

CR202.4R-092612

Add the following Subsection 202-3.09:

202-3.09 DISPOSAL OF PAVEMENT, SIDEWALKS, AND CURBS.

Pavement, sidewalk, and curb materials not used in the project, stored at a Contractor DEC approved site, provided to the local DOT Maintenance and Operations Station, or disposed of at a previously approved DEC disposal site require a DEC Solid Waste Disposal Permit.

Use disposal sites outside the project limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Dispose of solid waste materials, pavement, sidewalk, and curb (including handling, transporting, storing and disposing) according to the Alaska Department of Environmental Conservation (DEC) Regulations.

A DEC Permitting Officer in Anchorage, contact at (907) 269-7590.

CR202.1R-010114

202-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 202(15).  Pavement planing measured by the square yard of the pavement planed.

CR202.3.-071519

Add the following:

Removing and disposing fugitive materials measured along the edge of the traveled way on the side of the road nearest the area of work by the linear foot.

CR202.4R-092612

202-5.01 BASIS OF PAYMENT.  Add the following:

Acquiring a solid waste disposal permit from DEC is subsidiary to 202 Pay Items.

CR202.1R-010114

Add the following:

Item 202(13).  At the Contract Unit price for the actual length of fence taken down, disposed, or delivered to the owner, regardless of the type or height.  Payment includes full compensation required to perform this work.

Pay Item No.	Pay Item	Pay Unit

202(13)	Removal of Fence	Linear Foot

CR202.6R-102402

Add the following:

Item 202(15).  At the Contract Unit Price - payment is full compensation for activities and equipment associated with pavement planing:

	removal of pavement from curbs, and gutters;

	mechanical sweepers, and power brooms used during the planing operation;

	stockpiling planed material when required.

Repair work and materials for thin and unstable pavement is subsidiary to HMA Pay Items.

Replace damaged loop detectors, piezoelectric sensors, RWIS, or other data sensors outside the specified planing depth according to the requirements of section 660 and 669 at no expense to the Department.

If the milling might remove loops, sensors or similar, from the pavement, include 660 and 669 in the specials, or parts of, for the repair.

Replace damaged loop detectors, piezoelectric sensors, RWIS, or other data sensors inside the specified planing depth according to the requirements of section 660 and 669. Payment is in Section 660.

Pay Item No.	Pay Item	Pay Unit

202(15)	Pavement Planing	Square Yard

CR202.3-071519

Add the following:

Item 202(16).  At the Contract Unit price for the length of pipe removed, regardless of size.  Payment includes full compensation to remove and dispose of the pipes as shown in the Plans.

Item 202(18).  At the Contract Lump Sum price for each tank removed and disposed of according to DEC regulations.  Payment includes full compensation for necessary excavation, purging, processing, or removing fuel-contaminated soils around the tanks, and backfilling the resultant hole.

Item 202(23).  At the Contract Unit price for each well capped according to DEC regulations.

Item 202(23A).  At the Contract Unit price for each well decommissioned according to DEC regulations.

Use paragraph below in place of the paragraph above when DEC requires decommissioning of Ground Water Wells in place of abandonment.

Pay Item No.	Pay Item	Pay Unit

202(16)	Removal of Gas Pipe	Linear Foot

202(18)	Removal of Storage Tanks	Each

202(23)	Ground Water Well Abandonment	Each

202(23A)	Ground Water Well Decommissioning	Each

Use Pay Item 202(23A) below when DEC requires decommissioning of Ground Water Wells in place of abandonment.

CR202.5R-010610

Add the following:

Pay Item No.	Pay Item	Pay Unit

202(40)	Remove Fugitive Materials	Linear Foot

CR202.4R-092612

SECTION 203
EXCAVATION AND EMBANKMENT

Sect 203: CR203.1.2.3.4

Related Sect/Sp:  703/CR703.1

Related Sect/Sp:

CR203.1 – piezometers and settlement platforms.  CR303.2 – ditch linear grading.  CR203.3 – compaction near large structure foundations.

Special Provisions

203-1.01 DESCRIPTION.  Add the following:

Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

CR203.2-010114

Add the following:

This work also includes fabrication, installation, maintenance, and removal of piezometers and settlement platforms as shown in the plans and directed by the Engineer.  The Department will monitor and record the data from the settlement platforms and piezometers.

CR203.1-010610

203-3.01 GENERAL.  Add No. 5 after the 11th paragraph:

CR203.4 – applies to glass in the embankment.

E65 include in FED and SOA funded projects.

5.	within 50 feet of detection loops.

CR203.4-022015

203-3.03 EMBANKMENT CONSTRUCTION.  Add the following after the last paragraph:

Furnish the materials, fabricate, install, and maintain the settlement platforms and piezometers as shown in the plans and as directed by the Engineer.  Remove the settlement platforms, and piezometers, and grout solid the remaining pipe and conduit as shown in the plans when directed by the Engineer.

CR203.1-010610

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Add the following:

Compact the embankment within 20 feet of a bridge abutment full width to not less than 100 percent of the maximum density.  Material used within this zone shall be graded to pass the 3 inch sieve.

CR203.3-110502

203-4.01 METHOD OF MEASUREMENT.  Add the following:

9.	Item 203(27).  Measurement of ditch linear grading, whether flat bottom or “V” ditch, will be measured for payment by the station along the center of the ditch for each ditch so designated, constructed, and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT.  Add the following:

Payment for ditch linear grading will be full compensation for furnishing equipment, labor, tools, and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

203(27)	Ditch Linear Grading	Station

CR203.2-010114

Add the following:

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly but will be subsidiary to Pay Item 203(6A) Borrow, Type A.

CR203.3-110502

Add the following:

The Contract unit price includes furnishing the materials, fabricating, installing, maintenance, removal of settlement platforms and piezometers, removal of conduit and steel pipe and grouting the remaining conduit and steel pipe solid.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

203(19A)	Settlement Platforms	Each

203(19B)	Piezometers	Each

CR203.1-010610

Special Provision

Replace Section 204 with the following:

SECTION 204
STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

Sect 204: CR204-010119

Related Sect/Sp:  203, 205, 602/CR602.1, 603/CR603, 604, 605/CR605.1, 626, 627, 660

204-1.01 DESCRIPTIONS. Excavate and backfill for conduits (pipe culverts, structural plate pipe, pipe arches, storm drains, underdrains, and electrical conduits), headwalls, manholes, inlet boxes, and other minor structures.

Perform all pumping, bailing, draining, sheeting, bracing, and incidentals required for proper execution of the work.

204-2.01 MATERIALS. Use materials that conform to the following:

Selected Material	Subsection 703-2.07

Porous Backfill Material	Subsection 703-2.10

1.	Structure Backfill and Bedding Material: Selected Material Type A.

Maximum Particle Size:

a.	Corrugated Steel and Aluminum Conduit: material passing the 3-inch sieve

b.	Precast Concrete Structures

(1)	Conduit: materials passing the 1-inch sieve, except 2-inch when bedding thickness is greater than 6 inches

(2)	Minor structures: material passing the 1-inch sieve

Be sure to address bedding of minor precast concrete structures, manholes, equipment pad, and utility items. Bedding/leveling is required.

c.	Plastic Conduit: material passing the 2-inch sieve, except 3/4-inch for conduit between 8 inches and 15 inches and for conduit less than 8 inches 10% of the conduit diameter

d.	Electrical Conduit: material passing the 1-inch sieve

Fine materials around an underdrain may clog the underdrain over time. Consider adding a geotextile around the pipe or bedding structure backfill material. See CR605.1 for further notes.

e.	Underdrain Conduit: uniform porous backfill material passing the 2-inch sieve and a minimum greater than the conduit perforations

2.	Backfill Material: Selected Material Type C

In the roadbed structure use backfill material meeting the requirements of the roadbed structure, except use the structure backfill material and bedding as specified herein.

Use all suitable material from the project excavation for bedding, structure backfill, and backfill material before using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Clear and grub prior to starting excavation according to the requirements of Section 201.

Remove and dispose, Subsection 203-3.01, of unsuitable foundation material, including rock or other unyielding material, below the designed elevation as directed, except no less than 6 inches, and replace with approved material.

Place bedding material to a minimum thickness of 4 inches, except 6-inch minimum thickness for conduit over rock or unyielding material, and below electrical conduit, unless shown otherwise in the plans.

Place the bedding material to provide uniform support for conduit with the material in the middle one-third loosely placed and not compacted. Do not shape the bedding to the curvature of the round conduits. Shape the bedding for pipe arches, horizontal ellipse, and underpass shapes with spans exceeding 12 feet. Provide a minimum shaped width one-half the span of the pipe arch and underpass shapes and one-third the span of horizontal ellipse shape. Shape the bedding to the relatively flat bottom arc or fine-grade the foundation to a slight "V" shape.

Place minor precast concrete structures, other than conduits, on the 4-inch bedding/leveling course, of uniform stiffness and thickness with even compaction throughout.

Place the structure backfill over the bedding each side of the structure to 12 inches above the structure or the ground surface if less than 12 inches, except 6 inches above electrical conduit.

Place the structure backfill and backfill material in uniform layers not more than 6 inches deep. Do not create unbalanced loading with the placement of the structure backfill materials. When placing material against concrete, place the material according to the requirements of Section 550.

Compact the materials, each layer, without ponding or jetting to meet Subsection 203-3.04. In the haunch area, each side of the conduit, compact the material by firmly tamping into place.

Outside the roadbed structure, the Engineer may visually inspect and approve the excavation, bedding, structure backfill, backfill material, and compaction.

Support and protect existing conduits or utilities, not scheduled for removal or abandonment, when encountered in the excavation.

Remove all sheeting and bracing used in structure excavation upon completion of the work.

204-4.01 METHOD OF MEASUREMENT. Section 109. Use neat line method as follows:

Structure Excavation:

1.	Masonry Structures (except conduit). Between vertical planes, 18 inches outside the base of the masonry sections for the depth required.

2.	Conduit. Between parallel vertical planes located 18 inches outside the horizontal projection of the outside diameter of the conduit and to the depth shown on the Plans.

Structure excavation only measured below the limits of other classes of excavation. Structure's in embankment section, the natural ground line as cross-sectioned is the uppermost level of computation.

204-5.01 BASIS OF PAYMENT. The Contract price includes the placing and compacting of all backfill and bedding when the materials used are obtained from excavation, any clearing and grubbing required and not paid for under some other item, formation of any embankments made with surplus material from structure excavation, and disposal of all surplus or unsuitable excavation.

Additional excavation to provide for shoring, sheet piles, excavation shields or flattening the excavation slopes, is subsidiary.

When item 204(1), structure Excavation, does not appear in the bid schedule, structure excavation required to complete other items of work is subsidiary, except that excavation and disposal of unsuitable material required from below a plane 12 inches below the invert elevation of conduits and 12 inches below the bottom of structures is paid as extra work.

Any backfill or bedding material required whose source is other than project excavation is paid at the contract unit price for the materials being used, or as extra work if no unit price has been established.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

204(1)	Structure Excavation	Cubic Yard

CR204-010119

SECTION 205
EXCAVATION and fill for Major structures

Sect 205: SSP13-010116. Section 205 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:

Temporary Waterway Diversion and Dewater Work Areas-Draft. This provision is available as an individual provision in the AllProvision folder for addition to Section 205, 602, 603 and other sections as applicable to a specific project. Includes notes for use.

205-CR205.1-060117CrkDiversionDewaterWithNotes

DIVISION 300 — BASES

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 301
AGGREGATE BASE AND SURFACE COURSE

CR301.1 – substituting Ram for aggregate base course.	CR301.2 – use of "Layton Box” in sidewalks and pathways.

CR301.3 – Adding glass to base course.

CR176 – substituting Ram for aggregate base course.	CR26 – use of "Layton Box” in sidewalks and pathways.

E93 – Adding glass to base course.

Sect 301:  CR301.1,2. (CR301.1 Rplcd CR176, CR301.2 Rplcd CR26).

Related Sect/Sp:  608/CR608.1.2, CR703/CR703.1

Special Provision

301-2.01 MATERIALS.  Add the following after the first sentence:

Recycled Asphalt Material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70 – 100 |
| 3/8 inch | 42 – 90 |
| No. 4 | 28 – 78 |
| No. 16 | 11 – 54 |
| No. 50 | 5 – 34 |
| No. 100 | 3 - 22 |
| No. 200 | 2 – 12 |

3.	The asphalt content shall be 2.5 – 5.0 percent by weight of the RAM.

CR301.1-012407

301-3.01 PLACING.  Add the following:

Place base course material, used for the sidewalk and pathway foundations, with equipment capable of providing a specified depth and uniform surface.

CR301.2-062116

Add No. 5 after the 5th paragraph:

5.	within 50 feet of detector loops.

CR301.3-022015

301-3.03 SHAPING AND COMPACTION. Add the following:

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi ( 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:

Recycled asphalt material substituted for aggregate base course will be paid for as Item 301(1) Aggregate Base Course, at the unit price shown in the bid schedule for that Item.

CR301.1-012407

SECTION 304
SUBBASE

Sect 304:  304.1

Related Sect/Sp:  203/CR203.1.2.3.4, 301/CR301.1.2, 306/CR306, 401/CR401, 408/CR408, 703/CR703.1

CR304.1 – Adding glass to subbase.

E94 – Adding glass to subbase.

Special Provision

304-3.01 CONSTRUCTION REQUIREMENTS.  Add No. 5 after the 4th paragraph:

5.	within 50 feet of detector loops.

CR304.1-022015

Special Provisions

CR306 Coordinate CR306 with other Asphalt provisions.

Replace Section 306 with the following:

SECTION 306
ASPHALT TREATED BASE COURSE

Sect 306: CR306

Related Sect/Sp:  301/CR301.1.2.3.4; 401/CR401, 408/CR408, 703/CR703.1

Related Sect/Sp:

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt binder in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Binder) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Binder |  |
| Percent Voids Filled with Asphalt Binder (VFA) | 65 - 78 |
| Asphalt Binder Content, Min. % | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |
| Recycled Asphalt Pavement (RAP) |  |
| RAP, Max. %. | 25 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt binder content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if WAQTC FOP for AASHTO T308 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt binder proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt binder source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306(8_) ATB, Asphalt Price Adjustment, Type ___; Class__.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04.  Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT BINDER.  Conform to 702-2.01.  If asphalt binder is not specified use PG 52-28.

The total asphalt binder content may be a combination of the asphalt binder specified and the residual asphalt binder in the RAP.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt binder is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt binder content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.05 and 3.06 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt binder content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.

Provide aggregate and asphalt binder sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self-propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt binder, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92.0 % MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a)	By weighing.  No deduction will be made for the weight of asphalt binder or anti stripping additive or cutting back joints.

2.	Asphalt Binder.  By the ton, as follows.

Method 1:

Percent of asphalt binder for each sublot multiplied by the total weight represented by that sublot.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  If no acceptance testing is required, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste ATB will be calculated using the target value for asphalt binder as specified in the JMD.

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt binder more than 0.4% above the optimal asphalt binder content specified in the JMD.

3.	ATB, Price Adjustment, Type   ; Class  .  Determined under Subsection 306-4.03 Evaluation of Materials for Acceptance.  Also included in the measurement are the fees specified in Subsections 306-2.01, 4.02, 4.03 and 5.01.

306-4.02 ACCEPTANCE SAMPLING AND TESTING.  The Engineer will evaluate ATB for conformance to specifications according to Subsection 306-4.03 Evaluation of Materials for Acceptance.

ASPHALT TREATED BASE

The quantity of ATB produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 10,000 tons.  The lot will be divided into sublots of 1000 tons; each randomly sampled and tested for asphalt binder content, density, and gradation according to this subsection.

If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and evaluation will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 3,000 tons and 10,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 1000 tons and randomly sampled for asphalt binder content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.  The lot will be evaluated according to Subsection 306-4.03 except as noted.

For Contract quantity of less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any ATB that does not conform to the approved JMD.

The Engineer will determine where samples are taken.

1.	Asphalt Binder Content.  Asphalt treated base mix samples taken for the determination of asphalt binder content will be taken randomly from behind the paver screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt binder content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308, except ATM 405 will not be used when RAP is included in the mixture.

2.	Aggregate Gradation. The gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt binder.

3.	Density.

The Engineer will determine and mark the location(s) where the Contractor will take each mat core sample.  The location(s) for taking mat core samples will be determined using a set of random numbers and the Engineer's judgment.

Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new ATB within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A fee will be assessed for each failure to take core samples, backfill core sample voids, backfill core samples within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.

A retest of any sample outside the limits specified in Table 306-2 may be requested provided the quality control requirements of 306-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used to evaluate the material regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, when gradation and asphalt binder content are determined from the same sample, retesting for gradation or asphalt binder from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt binder content will include retesting for MSG.

ASPHALT BINDER

The lot size for asphalt binder will normally be 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt binder is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt binder will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated in accordance with 306-4.03.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt binder after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  ATB, not meeting the specified limits noted in Table 306-2, is considered defective.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4-inch or largest sieve size | 99 | 100 |
| 1/2-inch sieve or first sieve retaining aggregate | TV - 6 | TV + 6 |
| 3/8 inch sieve | TV - 6 | TV + 6 |
| No. 4 sieve | TV - 6 | TV + 6 |
| No. 8 sieve | TV - 6 | TV + 6 |
| No. 16 sieve | TV - 5 | TV + 5 |
| No. 30 sieve | TV - 4 | TV + 4 |
| No. 50 sieve | TV - 4 | TV + 4 |
| No. 100 sieve | TV - 3 | TV + 3 |
| No. 200 sieve* | TV - 2.0 | TV + 2.0 |
| Asphalt Binder Content, % | TV - 0.4 | TV + 0.4 |
| Mat Density, % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits, Table 703-4.

ASPHALT BINDER

Asphalt binder will be randomly sampled and tested in accordance with Subsection 306-4.02.  Provide supplier process control test results with the delivery ticket for each load of asphalt binder to the Engineer before unloading asphalt binder at the project. No payment will be made without this documentation.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project during the pay period, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt binder, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306(8_) ATB, Price Adjustment, Type ___ ; Class __ : is the sum of the price adjustments for each material lot and for fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Item 306(15). Asphalt Material Price Adjustment.

For each Section as included in Subsection 306-4.04 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

306(1)	ATB	Ton

306(2)	Asphalt Binder, Grade PG ##-## X	Ton

306(8_)	ATB, Price Adjustment, Type ___; Class __	Contingent Sum

306(15)	Asphalt Material Price Adjustment	Contingent Sum

CR306-010120

Item 306(8_). Do not use Pay Item 306(8_) in the Engineers Estimate or Estimate of Quantities – Except as required by the Engineer.

E65 include in FED and SOA funded projects.

Item 306(15). For Sections 306, 307, 308, 318, 401 thru 405, 408 excluding Section 402 include the Pay Item "Asphalt Material Price Adjustment" for one Section only, the Section with the greatest asphalt material quantity.  Do not remove the pay item from the Pay Items in the special – theses specials are typically complete section replacements for the SSHC.

Item 306(2). Confirm the asphalt binder performance grade, each project. Verify the performance grade matches 702-2.01-1 as in 52-40 V, etc. Add the "V" or "E" to AASHTOWare (AWP) pay items as supplemental descriptions. The grade number in the AWP Pay Item will have a space between the number (description) and the letter (supplemental description, the "V" or "E") due to the format of AWP.

Estimating 306(1) and 306(2). Be sure to look closely at both items when researching historical bid results. The Contractors will vary how they estimate the items. If the price for the binder [306(2)] is very close to $0.00, or is $0.00 the Contractor has combined the total price of binder [306(2)] with the total price of ATB [306(1)] and divided by the quantity of the ATB [306(1)] for the unit price of ATB [306(1)]. You will need to look at a variety of like item cost and the different bidder prices.  Normally one or two bidders provide a price for both the Binder [306(2)] and the ATB [306(1)]. If you are unsure, discuss the cost with other design engineers and the construction engineers. You will significantly over estimate the cost of the ATB [306(1)] if you do not subtract the unit cost of the binder [306(2)].

|  |  |  | Contractor A |  |  | Contractor B |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Description | Quantity (Tons) | Unit Price $/Ton | Item Cost $ | Contractor's Combined Unit Price $/Ton [306(1) + 306(2)]/306(1QTY) | Unit Price $/Ton | Item cost $ | Contractor's Combined Unit Price $/Ton [306(1) + 306(2)]/306(1QTY) |
| 306(1) | ATB | 20,000 | 50 | 1,000,000 | 82.50 | 55 | 1,100,000 | 88.00 |
| 306(2) | Asphalt Binder, Grade PG 52-28 | 1100 | 550 | 605,000 | 0.00 | 600 | 660,000 | 0.0 |
| [306(1) + 306(2)] |  |  |  | 1,650,000 |  |  | 1,760,000 |  |
| 306(1) | ATB | 20,000 | 50 | 1,000,000 | 99.50 | 55 | 1,100,000 | 115.50 |
| 306(2) | Asphalt Binder, Grade PG 52-40 V | 1100 | 900 | 990,000 | 0.00 | 1100 | 1,210,000 | 0.00 |
| [306(1) + 306(2)] |  |  |  | 1,990,000 |  |  | 2,310,000 |  |

Special Provision

CR318 Coordinate CR318 with other Asphalt provisions, and the 2015 SSHC, and the 2017 SSHC to avoid conflicts.

Add the following Section:

SECTION 318
FOAMED ASPHALT STABILIZED BASE COURSE

Sect 318:  CR318

Related Sect/Sp:  306/CR306, 401/CR401, 408/CR408, 409/CR409, 703/CR703.1, 702/CR702.2.3

Related Sect/Sp:

CR318 include the SNtB item, "Asphalt Material Price Adjustment."

E65 include in FED and SOA funded projects.

318-1.01 DESCRIPTION.  The work consists of constructing a mixed in place foamed asphalt stabilized base.  Create foamed asphalt treated base course by simultaneously injecting and thoroughly mixing metered amounts of asphalt, Portland cement, and water into the pulverized asphalt and base course.  Spread, shape, and compact the mixed material according to these specifications and conforming to the dimensions shown on the Plans.

Provide an experienced foamed asphalt technician on site to supervise the foamed asphalt process and to supervise the related process control testing.

At the Preconstruction Meeting, provide information on the equipment proposed for use, the name, and resume of the foamed asphalt technician, and the location of the demonstration site.

MATERIALS

318-2.01 COMPOSITION OF MIXTURE – JOB MIX DESIGN (JMD).

1.	Sampling.  Before foamed asphalt stabilized base course production, laboratory tests of materials submitted by the Contractor shall be made to determine the quantity of asphalt binder and Portland cement required in the mix.  At least 15 days before the production of foamed asphalt stabilized base course, the Contractor shall furnish the following:

a.	500-pound representative sample of in-place aggregate

b.	200- pound representative sample of in-place asphalt concrete pavement

c.	10-gallons of asphalt binder

d.	One sack of Portland cement

2.	Job Mix Details.  The Engineer will determine the JMD using procedures contained in the Wirtgen Manual Foamed Bitumen Mix Design Procedure, using the Wirtgen WLB 10 to generate foamed asphalt.  The JMD will provide the following:

a.	The percent by weight of foamed asphalt binder to be added to the mix.

b.	The optimum percent by weight of water to be added to the asphalt binder for the foaming process.

c.	The minimum Foamed Asphalt Expansion Characteristics required.

d.	The temperature of asphalt binder at the time of injection.

e.	The percent by weight of Portland cement to be added to the mix.

f.	The gradation of the in place aggregate.

g.	The optimum compaction moisture content.

h.	Design dry indirect splitting tensile strength.

i.	The maximum dry density.

318-2.02 ASPHALT BINDER.  Conform to subsection 702-2.01 Asphalt Binders PG 52-28.  Each batch of asphalt binder shall be tested to conform to specifications before shipping.  Storage tanks used for the batch shall be noted on the test report.

Provide the following shipping documents:

1.	Manufacturer’s certification of compliance.

2.	Conformance test results of the batch

3.	Manufacturer shall also document:

a.	date and time of loading

b.	batch number and storage tank

c.	type, grade, and quantity of materials loaded.

The vendor’s certified test report for the asphalt binder can be used for acceptance or tested independently by the Engineer.

Excess asphalt binder shall remain the property of the Contractor.  Removal of excess asphalt binder from the project area shall be incidental to the Contract and no separate payment will be made.

318-2.03 PORTLAND CEMENT.  Conform to subsection 701-2.01, Type I or II meeting low alkali requirements.

318-2.04 WATER.  Water shall be clean and free from sewage, oil, acid, strong alkalis, or vegetable matter.  Water of questionable quality shall be tested according to the requirements of AASHTO T 26.

318-2.05 CONTRACTOR’S FOAMED ASPHALT TECHNICIAN.  The Contractor shall provide an onsite technician to supervise the foamed asphalt process and the related process control of the product on the control strip and for 10 days of production.  This technician shall have a minimum of 5 years supervising successful projects using foamed asphalt binder with similar base material and equipment.  The technician must also be qualified to develop a foamed asphalt stabilized base course mix design and supervise the process control.

Provide a submittal that includes the following information:

1.	Resume of Technician

2.	A list of successful projects; provide owners contact, address, and telephone number;  location of projects.

3.	Description of foamed asphalt binder equipment used on the project.

318-2.06 CONTRACTOR PROCESS CONTROL AND ACCEPTANCE SAMPLING AND TESTING.  The quantity of foamed asphalt stabilized base produced will be divided into lots and the lots evaluated individually.

A lot will normally be 24,000 square yards.  The lot will be divided into sublots of 4,000 square yards.  The Contractor shall randomly sample and test for density and Indirect Tensile Strength for each sublot.  The Engineer will validate this test data for each lot through independent random testing before accepting it.

The Contractor shall provide the following:

1.	Daily production records for each sublot, including the quantity of asphalt binder, Portland cement, and in place compaction moisture content.

2.	Measure and report expansion ratio and half life of foamed asphalt binder for every 4 hours of production.

3.	Monitor and report in place field density of the foamed asphalt stabilized base for each sublot.

4.	Provide a laboratory, test equipment and a qualified technician for ITS and density testing on the jobsite using ATM 412.  Sample and perform Indirect Tensile Strength testing for each sublot according to Wirtgen Foamed bitumen mix design procedure manual, using calibrated equipment and a qualified technician.  Make a minimum of 3 specimens to average for each sublot Indirect Tensile Strength test.

5.	Report process control and acceptance sampling and testing data to the Engineer within 24 hours.

318-2.07 PREPROCESS MEETING.  A minimum of 5 days before initiating operations, hold a meeting on the jobsite where the Contractor’s technician outlines a processing plan.  This plan must address the sequence of operation, equipment to be used, and process control.  Outline steps to assure product consistency, conformity to strength requirements, proposed quality control testing frequency, traffic control, and public notification.

CONSTRUCTION METHODS

318-3.01 WEATHER LIMITATIONS.  Foamed asphalt stabilized base course shall not be mixed while the air or surface temperature is below 40F, or when conditions indicate that the temperature may fall below 40F within 24 hours, or when the aggregate is above the optimum compactions moisture content, or when the aggregate or subgrade is frozen.  Follow the recommendations made by the Contractor’s technical representative as approved by the Engineer regarding the acceptability of the weather conditions for foaming operation.

318-3.02 CONTROL SECTION.  Before full production, the Contractor shall use the equipment specified for the foamed asphalt stabilized base course operation and construct a control section at a location approved by the Engineer.  Process material in the control section two passes wide, 150 feet long and to the depth shown on the Plans, and develop a density standard according to ATM 412.  The Contractor’s technical representative shall supervise this process.

318-3.03 RECLAIMER (RECYCLER).  The reclaimer shall have the following features and capabilities:

1.	A minimum power capability of 600 horsepower.

2.	The capability to pulverize to the size specified, mix, and recycle material to the depth shown on the Plans.

3.	Ability to increase the effective volume of the mixing chamber in relation to depth of cut.

4.	Two microprocessor controlled systems, complete with two independent pumping systems and spray bars, to regulate the application of foamed asphalt binder, separate from water that is used to increase the moisture content of the mixed material.  Both systems shall perform in relation to the forward speed of the reclaimer and the mass of the material being processed.

5.	Two spray bars, one for foamed asphalt binder and one for compaction moisture, shall each be fitted with self cleaning nozzles at a maximum spacing of one nozzle for each 6 inch width of the mixing chamber.  Provide a way to monitor the flow rate at each nozzle to verify that all nozzles are producing foamed asphalt at the same rate.

6.	The foamed asphalt binder shall be produced at the spray bar in individual expansion chambers into which hot asphalt binder, water, and air are injected under pressure through individual and small orifices that promote atomization.  The rate of addition of water into the hot asphalt binder shall be kept at a constant percentage by mass of asphalt binder by the same microprocessor.

7.	A system within the operator cabin to verify the foamed asphalt is being evenly distributed across the full width of the spray bar at the rate specified.  The system shall be demonstrated to the Engineer to verify even spraying.

8.	An inspection or test nozzle shall be fitted at one end of the spray bar that produces a representative sample of foamed asphalt binder.

9.	An electrical heating system capable of maintaining the temperature of asphalt binder flow components above 300 degrees F.

10.	A single asphalt binder feed pipe installed between the recycler and the supply tanker.  Do not use circulating systems that incorporate a return pipe to the supply tanker.

11.	The ability to print out asphalt binder quantities used during production.

12.	The teeth on the mandrel mixing head form a Chevron pattern.

The reclaimer model proposed for use shall have successfully been used by the Contractor/subcontractor on other projects.  Provide a submittal of the reclaimer specifications at the Preconstruction conference.

318-3.04 PORTLAND CEMENT DISTRIBUTOR.    Use a cement distributor designed to spread a uniform coverage of Portland cement at a specified rate.  The spread rate shall be integrated with the speed of travel to maintain a uniform coverage.

318-3.05 ROLLERS.  Provide the following types of rollers as required:

1.	Self-propelled vibratory pad foot roller having a minimum dynamic force of 60,000 lbs. for initial compaction.

2.	Pneumatic tired roller having a minimum operating weight of 50,000 lbs. for secondary compaction and finishing.

3.	Vibratory steel drum roller for secondary compaction and finishing.

318-3.06 GRADER.  Grader must have calibrated automatic cross slope blade controls.

318-3.07 PREPARATION.  The area to be stabilized with foamed asphalt binder may require pulverization, removal of material, grading, and shaping to conform to the grades and typical cross section shown on the Plans, then provide aggregate and pay for under a separate bid item.  Soft or yielding spots shall be removed and replaced with acceptable aggregate before being stabilized.

318-3.08 PULVERIZING.  Pulverize the existing asphalt pavement and base material so that at the completion of moist mixing, 100% passes a 2 inch sieve.  Multiple passes may be required to size the insitu material and to adjust moisture content before applying Portland cement and injecting foamed asphalt.

318-3.09 FOAMED ASPHALT BINDER AND PORTLAND CEMENT APPLICATION, MIXING, AND SPREADING.  Mix insitu material with foamed asphalt binder, Portland cement, and water in place with a reclaimer.

Measure the moisture content of insitu material before processing and adjust if necessary.  The percentage of moisture in the aggregate, at the time of Portland cement application, shall not exceed the quantity that will permit a uniform mixture during mixing operations, and it shall not exceed the specified optimum moisture content for the foamed asphalt stabilized base course mixture.

Spread the required quantity of Portland cement uniformly on the surface to be stabilized.  Pulverize to the depth required while simultaneously injecting foamed asphalt binder and compaction water.  Mixing shall continue until the foamed asphalt binder, Portland cement and compaction water have been sufficiently blended with the existing material.

318-3.10 COMPACTION.  Immediately upon completion of the mixing operations, the mixture shall be thoroughly compacted with the initial compaction done with the vibratory pad foot roller.  The intermediate compaction shall be done with the pneumatic tired roller and the finish compaction shall be done with the vibratory steel drum roller.

Acceptable field wet density of the compacted mixture shall not be less than 98 percent of the standard developed on the control strip according to ATM 412.  Determine the in place field density by direct transmission according to WAQTC FOP for AASHTO 310, Method A.   The moisture content of the mixture at the start of the compaction shall not be above the optimum moisture content as determined by the foamed asphalt mix design.

318-3.11 FINISHING.  The completed foamed asphalt stabilized base course shall conform to the required lines, grades and cross section.  If necessary, the surface shall be lightly scarified to eliminate any deep imprints made by the compacting or shaping equipment.  The surface shall then be recompacted to the required density.  Seal the surface with water and a pneumatic roller.  Control traffic on the finished surface for a cure period after sealing is completed, as directed by the Engineer.

318-3.12 CONSTRUCTION LIMITATIONS.  When the operation, after the application of cement, is interrupted for more than 30 minutes or when the uncompacted mixture is wetted by rain so that the optimum moisture content is exceeded by 2 percentage points, the decision to reconstruct the portion affected shall rest with the Engineer.  In the event the uncompacted, rain wetted mixture exceeds the specified moisture content tolerance, the Contractor shall reconstruct at the Contractor’s expense the portion affected.  Material along the longitudinal or transverse construction joints not properly compacted shall be reconstructed, at the Contractor’s expense, with properly moistened and mixed foamed asphalt stabilized base compacted to specified density.

318-3.13 SURFACE TESTS.   The finished surface shall not vary more than 3/8 inch when tested with a 10 foot straightedge applied parallel with, or at right angles to, the longitudinal axis of the pavement.  Variations in excess of this tolerance shall be corrected by the Contractor, at the Contractor’s expense, and in a manner satisfactory to the Engineer.

318-3.14 MAINTENANCE.  Maintain, at the Contractor’s expense, the entire base course within the limits of the Contract in a condition satisfactory to the Engineer from the time work starts until the work is completed.  Maintenance includes immediate repairs of defects that may occur either before or after the foamed asphalt stabilized base course has been constructed.  The work shall be done by the Contractor at the Contractor’s expense and repeated as often as necessary to keep the area intact.  Repairs shall be made in a manner that will ensure restoration of a uniform surface and the durability of the part repaired.  Faulty work must be reconstructed for the full depth of treatment.  Low areas shall be remedied by reconstructing the material for the full depth of treatment rather than by adding a thin layer of foamed asphalt stabilized base course to the completed work.

The Contractor is responsible for cost of road spray on vehicles and informing the public of potential hazards.

318-4.01 METHOD OF MEASUREMENT.    Section 109 and the following:

1.	Asphalt Binder.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

2.	Portland Cement.  By the weight recorded on delivery tickets minus waste, diversion, and remnant.

318-4.02 EVALUATION OF MATERIAL FOR ACCEPTANCE.  The Engineer must have Indirect Tensile Strength results and passing densities of the foamed asphalt stabilized base before allowing it to be covered by HMA pavement.  The Engineer will calculate the lot average of the Indirect Tensile Strength results from the acceptance testing for the project.  Payment shall be made at the Contract unit price per square yard for foamed asphalt stabilized base course when the lot average dry Indirect Tensile Strength is greater than 85% of the mix design.  This price shall be full compensation for furnishing materials, except asphalt binder or Portland cement, and for preparation, delivering, placing, and mixing of materials; and for labor, equipment, tools, and incidentals necessary to complete the item.

If the lot average dry Indirect Tensile Strength value is less than 85% of the JMD dry Indirect Tensile Strength value, the foamed asphalt stabilized base is deemed to not meet specifications.  The Contractor shall increase the thickness of the hot asphalt pavement for that lot and adjust the surface grade at the Contractor’s expense to compensate for reduced dry Indirect Tensile Strength.

T	=	(5.5-(6.25*(lot average dry ITS/JMD dry ITS)))

T	= 	increase in hot asphalt pavement thickness in inches

ITS	= 	Indirect Tensile Strength

318-4.03 ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project during the pay period, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

318-5.01 BASIS OF PAYMENT

Item 318(15). Asphalt Material Price Adjustment.

For each Section as included in Subsection 318-4.03 Asphalt Material Price Adjustment, item 1, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

318(1)	Foamed Asphalt Stabilized Base Course	Square Yard

318(2)	Asphalt Binder, Grade PG 52-28	Ton

318(3)	Portland Cement, Type I or II	Ton

318(4)	Foamed Asphalt Technician	Lump Sum

318(15)	Asphalt Material Price Adjustment	Contingent Sum

CR318-040119

Item 306(15). For Sections 306, 307, 308, 318, 401 through 409 excluding Section 402 include the Pay Item "Asphalt Material Price Adjustment" for one Section only, the Section with the greatest asphalt material quantity.  Do not remove the pay item from the Pay Items in the special – theses specials are typically complete section replacements for the SSHC.

DIVISION 400 — ASPHALT PAVEMENTS
AND
SURFACE TREATMENTS

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

Special Provision

Replace Section 401 with the following:

SECTION 401
HOT MIX ASPHALT PAVEMENT

Sect 401: CR401_SSHC2017	SSHC2015 combined with CR401.1-041017 for use in place of SSHC2017 Section 401.

Related Sect/Sp:  202, 301, 306, 408, 702, 703

401-1.01 DESCRIPTION. Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section, HMA refers to Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course: HMA, Type IV, Class B.

MATERIALS

401-2.01 ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 52-28.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

401-2.02  LIQUID ANTI-STRIP ADDITIVE.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design (JMD). At least 90% of the aggregate must remain coated when tested according to ATM 414. The following minimum dose (percent) of liquid anti-strip by weight of asphalt binder is required:

| Liquid Anti-strip Type | Minimum Dose by Weight of Asphalt Binder, % |
| --- | --- |
| Amines based | 0.30 |
| Phosphate Ester based | 0.30 |
| Organ-Silane based | 0.05 |

401-2.03  JOINT ADHESIVE.   Conform to Subsection 702-2.05.

401-2.04  JOINT SEALANT.   Conform to Subsection 702-2.06.

401-2.05  WARM MIX ASPHALT.   Conform to Subsection 702-2.07.

401-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

401-2.07 AGGREGATES.  Conform to Subsection 703-2.04.  Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

401-2.08  RECYCLED ASPHALT PAVEMENT.  Recycled asphalt pavement (RAP) may be used in the production of HMA.  The RAP may be from pavements removed under the Contract, or from an existing stockpile.  Conform to Subsection 703-2.16

401-2.09 JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements of Table 401-1, for the Type and Class of HMA specified.

TABLE 401-1

HMA MARSHALL Design Requirements

| DESIGN PARAMETER | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Binder) |  |  |
| Stability, Pounds | 1800 Min. | 1200 Min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix (VTM), % | 3.0 – 5.0 | 3.0 – 5.0 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Binder |  |  |
| Voids Filled with Asphalt (VFA), % | 65 - 75 | 65 - 78 |
| Asphalt Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |
| Liquid Anti-Strip Additive**,%, Min. | 0.30 | 0.30 |
| RAP, %, Max. | 15.0 | 25.0 |

*Dust-Asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt binder (calculated by weight).

** By Weight of Asphalt Binder

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant. The letter shall state whether or not WMA and/or RAP will be used. The letter shall include the proposed gradation for the JMD, gradations for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature- viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, minimum 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

6.	If applicable, a letter stating the WMA technology (Subsection 702-2.07) to be used, location where additive will be introduced and manufacturer’s recommended usage rate for each type of HMA.  Supply a minimum of 2-pint samples for each proposed additive.

7.	If applicable, representative samples of any RAP proposed for use.  Furnish a minimum of 200-pound sample of proposed RAP.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified, and establish the approved JMD which will become a part of the Contract.

Anti-strip evaluation (ATM 414) of HMA mix designs that include RAP will be completed without the inclusion of the RAP.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 401-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 401-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 401-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 401-5.01.

401-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting," Subsection 401-3.01, the JMD and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 401-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control:

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 401-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

401-3.01 PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, make adjustments to the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Summary of plant modifications (if applicable) for production of WMA

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

401-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

401-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F.

401-3.04 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of HMA and test strip HMA.

401-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

If WMA is approved by the Engineer, modify the mixing plant as required by the manufacturer and WMA additive manufacturer.

401-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

When directed by the Engineer, cover the HMA in the hauling vehicle(s).

Do not haul HMA on barges.

401-3.07 ASPHALT PAVERS.  Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.08  ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

401-3.09  RESERVED.

401-3.10  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 401-3.17. Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

401-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

401-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

401-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

401-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

401-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

401-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

Prevent indentation in the mat, do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 92.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

401-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.  Top lift longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG in a sublot, seal the surface of the longitudinal joints with joint sealant within that sublot or as directed.

Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

Top lift longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

401-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 401-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 0.25”, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to  inlaying new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 401-4.03.3.

Typically keep the 401-3.18 above and remove 401-3.18 below, Except remote, low volume, gravel to pave, small urban and ownership transfer projects – Replace Subsection 401-3.18 above with Subsection 401-3.18 included below.  Evaluation of Materials for Acceptance 401-4.03, 3 is similar.

401-3.18 SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the Contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks  The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16-inch from the straightedge, including joints, as defective work.  Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required.  Do not surface patch.  After the Contractor performs corrective work, the Engineer will retest the area.

Perform corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more the 1/4-inch grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer's recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the mill surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays. Place a minimum overlay thickness of 2.0-inches.

3.	Mill and Fill.  Mill the existing pavement to provide a vertical transverse joint face.  Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlaying new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0-inches.

401-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

401-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

401-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints. If the use of WMA is approved by the Engineer, WMA additives will not be measured and are considered subsidiary to the HMA pay item.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA class and type.

4.	Temporary Pavement.  By weight, without deduction for the weight of asphalt binder or anti-strip additive.

5.	Leveling Course.  By Lane-Station (12 foot width) or by weighing without deduction for the weight of asphalt binder or anti-strip additive.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 401-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 401-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 401-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 401-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 401-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 401-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 401-3.10(2), measured according to Section 109.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The bid quantity of each type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot

If the bid quantity is between 1,500 to 4,999 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 401-4.03.1.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

Sampling and testing include the following:

1.	Asphalt Binder Content.  HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting. Random sampling locations will be determined by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  Asphalt binder content will be determined according to ATM 405 or ATM 406, at the discretion of the Engineer.

2.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 401-2 applied.

a.	Drum Mix Plants.  Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

b.	Batch Plants.  Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for dry batch samples will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

3.	Density.  The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

a.	Mat Cores:  The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment.  Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

b.	Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples.  Backfill and compact voids left by coring with new HMA within 24 hours and according to ATM 413. The Engineer will determine density of samples according to ATM 410.

4.	Retest.  When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 401-3.02 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Retesting will be performed by the Department's regional laboratory.

5.	Asphalt Binder Grade.  The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 – 200 tons, the bid quantity is considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples.  Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702 requirements for asphalt binder quality.

6.	Asphalt Binder Grade Retest. Replace with the following:

Asphalt Binder Grade Retest. The assigned test value (ATV) will be determined using ASTM D3244. Testing will be by AASHTO accredited independent laboratories.  Each test will be completed by a different laboratory.

Retest.  Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract.  These methods describe how price adjustments are determined based on the quality of the HMA binder longitudinal joint density and pavement smoothness.

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.000 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.800 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 401-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| ¾” or largest sieve size | 99 | 100 |
| ½ inch sieve or first sieve retaining aggregate | TV-6 | TV+6 |
| 3/8 inch sieve | TV-6 | TV+6 |
| No. 4 sieve | TV-6 | TV+6 |
| No. 8 sieve | TV-6 | TV+6 |
| No. 16 sieve | TV-5 | TV+5 |
| No. 30 sieve | TV-4 | TV+4 |
| No. 50 sieve | TV-4 | TV+4 |
| No. 100 sieve | TV-3 | TV+3 |
| No. 200 sieve* | TV-2.0 | TV+2.0 |
| Asphalt Binder Content, % | TV-0.4 | TV+0.4 |
| Mat Density, % | 92.0 | 100.0 |

*LSL for the No. 200 sieve is restricted by the broadband limits Table 703-4.

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 401-3 gives the weight factor (f) for each test property considered.

TABLE 401-3

WEIGHT FACTORS

| Property | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| ¾ inch sieve | 4 | 4 | - |
| ½ inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve* | 20 | 20 | 20 |
| Asphalt Content, % | 40 | 40 | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = Price Adjustment Base = $110.00 per ton.

PAB: asphalt binder PG 52-28, Use PAB = $100. All other binders use PAB = $110.00.

Be sure of the binder at time of advertisement!

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401(8_).

2.	Longitudinal Joint Density Price Adjustment.  Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 401(9).

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 401-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade), or Method 2 (pavement placed over existing pavement). The SF is rounded to the nearest 0.001.

Method 1: SPA = PAB x PQ x SF,

where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PAB: asphalt binder PG 52-28, Use PAB = $100. All other binders use PAB = $110.00.

Be sure of the binder at time of advertisement!

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 401-4)

TABLE 401-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40 | 0.050 |
| 40 to 70 | 0.050 – (IRI - 40)/600 |
| 70 to 90 | 0.000 |
| 90 to 120 | (90 – IRI)/120 |
| Greater than 120* | - |

* Corrective Work required, see Subsection 401-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $110.00 per ton,

PAB: asphalt binder PG 52-28, Use PAB = $100. All other binders use PAB = $110.00.

Be sure of the binder at time of advertisement!

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.120 x RR – 0.020; SF not to exceed 0.050

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 401-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 401(10).

3.	Pavement Smoothness Price Adjustment. Not applicable to this project.

Typically keep the 401-4.03, 3 above and remove 401-4.03, 3 below, Except remote, low volume, gravel to pave, small urban and ownership transfer projects – Replace Subsection 401-4.03, 3 above with Subsection 401-4.03, 3 included below.  Surface requirements and Tolerance is similar.

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.0, is accepted or rejected per Table 401-3.01-1 Asphalt Binder Pay Factors.

TABLE 401-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52-40 V | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86 | 85–75 | 74–68 | 67–60 | 59–55 | < 55 |
|  | PG 58-34 E | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90 | 89–85 | 84–80 | 79–75 | 74–70 | < 70 |
|  | PG 64-40 E | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97 | 96–95 | 94–91 | 90–85 | 84 – 80 | < 80 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64-40 E & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52-40 V, PG 58-34 E | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR)

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 401(21).

401-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT. Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project during the pay period, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP = Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

401-5.01 BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 401 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Tack coat

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 401-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 401-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 401-3.06 Hauling Equipment

	Work and materials associated with Subsection 401-3.20 Roadway Maintenance

Test Strips:  Subsection 401-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 401(8_), 401(9), 401(10) and 401(21) do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Item 401(5) HMA, Temporary, Type     ; Class     . Removal and disposal of temporary HMA is subsidiary.

Typically 401(8), (9), (10), and (21) will be paid under 401(22). The exception is to include 401(8), (9), (10), and (21) individually. To include 401(8), (9), (10), and (21) requires coordination/approval with/by the Engineer. (21) is a deduct; EE = $0.0.

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are payed under  201(22) Combined Price Adjustment.

401(8_) HMA Price Adjustment, Type     ; Class     ,

401(9) Longitudinal Joint Density Price Adjustment,

401(10) Pavement Smoothness Price Adjustment, Method    .

401(21) Asphalt Binder Price Adjustment

Item 401(8_) HMA Price Adjustment, Type    ; Class    , is the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Item 401(8_) HMA Price Adjustment, Type    ; Class    , does not apply to the following:

	HMA contract quantity is less than 1500 tons.

	HMA leveling course and rut repair.

	Temporary HMA.

	Driveway and approach HMA.

Item 401(15) Asphalt Material Price Adjustment.

For each Section as included in Subsection 401-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Item 401(16) Crack Repair.  Cleaning loose material from cracks, asphalt binder, and HMA to fill cracks are subsidiary.

Item 401(17) Prelevel for Ruts, Delaminations, and Depressions.  Cleaning loose material, asphalt binder, and HMA are subsidiary.

Item 401(18) Repair Unstable Pavement. Removal of pavement and base course, asphalt binder, and HMA are subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1_)	HMA, Type     ; Class     	Ton

401(2)	HMA, Leveling Course, Type  IV ; Class  B 	Lane-Station

401(3)	HMA, Leveling Course, Type  IV ; Class  B 	Ton

401(4)	Asphalt Binder, Grade PG ##-## X	Ton

401(5)	HMA, Temporary, Type  II ; Class  B 	Ton

401(6)	HMA, Type     , Class     	Square Yard

401(7)	Liquid Anti-Strip Additives	Contingent Sum

401(8_)	HMA Price Adjustment, Type     ; Class     	Contingent Sum

401(9)	Longitudinal Joint Density Price Adjustment	Contingent Sum

401(10)	Pavement Smoothness Price Adjustment, Method     	Contingent Sum

401(13)	Job Mix Design	Each

401(14)	Joint Adhesive	Linear Foot

401(15)	Asphalt Material Price Adjustment	Contingent Sum

401(16)	Crack Repair	Linear Foot

401(17)	Prelevel for Ruts, Delaminations, and Depressions	Square Yard

401(18)	Repair Unstable Pavements	Square Yard

401(21)	Asphalt Binder Price Adjustment	Contingent Sum

401.(22)	Combined Price Adjustment	CS

CR401-010120

Item 401(4). Confirm the asphalt binder performance grade, each project. Verify the performance grade matches Table 401-4.03-1 and 702-2.01-1 as in 52-40 V, etc. Add the "V" or "E" to AASHTOWare (AWP) pay items as supplemental descriptions. The grade number in the AWP Pay Item will have a space between the number (description) and the letter (supplemental description, the "V" or "E") due to the format of AWP.

Item 401(15). For Sections 306, 307, 308, 318, 401 thru 405, 408 excluding Section 402 include the Pay Item "Asphalt Material Price Adjustment" for one Section only, the Section with the greatest asphalt material quantity. Do not remove the pay item from the Pay Items in the special.

401(8), in the Engineer's Estimate, is a contingent sum item, with a value equal to: 5.5% x [401(1) + 401(4)].

401(15), in the Engineer's Estimate, is a contingent sum item, with a value of $0.00.

Item 401(11) and (12) are removed. Typically, CR does not pay for driveways and approaches under Section 401. Driveways and approaches paid under Section 639 Approaches.

Estimating 401(1) and 401(4). Be sure to look closely at both items when researching historical bid results. The Contractors will vary how they estimate the items. If the price for the binder [401(4)] is very close to $0.00, or is $0.00 the Contractor has combined the total price of binder [401(4)] with the total price of HMA [401(1)] and divided by the quantity of the HMA [401(1)] for the unit price of HMA [401(1)]. You will need to look at a variety of like item cost and the different bidder prices.  Normally one or two bidders provide a price for both the Binder [401(4)] and the HMA [401(1)]. If you are unsure, discuss the cost with other design engineers and the construction engineers. You will significantly over estimate the cost of the HMA [401(1)] if you do not subtract the unit cost of the binder [401(4)].

|  |  |  | Contractor A |  |  | Contractor B |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Description | Quantity (Tons) | Unit Price $/Ton | Item Cost $ | Contractor's Combined Unit Price $/Ton [401(1) + 401(4)]/401(1QTY) | Unit Price $/Ton | Item cost $ | Contractor's Combined Unit Price $/Ton [401(1) + 401(4)]/401(1QTY) |
| 401(1) | HMA | 20,000 | 50 | 1,000,000 | 82.50 | 55 | 1,100,000 | 88.00 |
| 401(4) | Asphalt Binder, Grade PG 52-28 | 1100 | 550 | 605,000 | 0.00 | 600 | 660,000 | 0.0 |
| [401(1) + 401(4)] |  |  |  | 1,650,000 |  |  | 1,760,000 |  |
| 401(1) | HMA | 20,000 | 50 | 1,000,000 | 99.50 | 55 | 1,100,000 | 115.50 |
| 401(4) | Asphalt Binder, Grade PG 52-40 V | 1100 | 900 | 990,000 | 0.00 | 1100 | 1,210,000 | 0.00 |
| [401(1) + 401(4)] |  |  |  | 1,990,000 |  |  | 2,310,000 |  |

Special Provision

Replace Section 406 with the following:

1.01.  If rumble strips will not be in the shoulders and on the roadway centerline adjust the 2nd sentence for one or the other.

1.01.  If rumble strips will not be in the shoulders and on the roadway centerline adjust the 2nd sentence for one or the other.

SECTION 406
RUMBLE STRIPS

Sect 406: CR406

Related Sect/Sp:  643/CR643.1, 670/CR670.1, 712/CR712.1

406-1.01 DESCRIPTION.  Form a series of indentations (rumble strips) into the roadway pavement.  Place rumble strips in each shoulder and the roadway centerline to the width, depth and length as indicated in the Contract documents and/or as directed by the Engineer.

406-1.02 RUMBLE STRIP.  A single uniform circular concave (cross section) indentation/depression milled into the pavement surface having a length measured perpendicular to the direction of travel, a width measured in the direction of travel and a depth measured from the surface of the pavement to the bottom of the indentation.

406-2.01 MATERIALS.  None.

406-2.02 MILLING EQUIPMENT.  Use equipment designed specifically for milling rumble strips into asphalt pavement.  Equip milling machine with a rotary type cutting head with a maximum outside diameter of 24-inches and a minimum length of 16-inches capable of producing a depression both 12-inches and 16-inches in length by 7 1/2-inches in width to a depth shown in the Plans.  Arrange the cutting tips to provide a smooth cut (approximately 1/16-inch between peaks and valleys).

Furnish the milling equipment with a guidance system, including a guide, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the Plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

Equipment Manufacture: provide training for the operators and a representative onsite during installation of the rumble strip test section(s) (Subsection 406-3.03).  Representative: remain onsite until test specimen(s) satisfy the Plans and Specifications as determined by the Engineer.

CONSTRUCTION REQUIREMENTS

406-3.01 PAVEMENT SURFACE PREPARATION.  Inspect roadway to receive rumble strips for acceptable pavement condition and stake locations to receive rumble strips prior to installation.  Prepare the roadway for the milling operation by providing a smooth clean surface.  Sweep all loose material from the roadway surface in line with the planned rumble strips and to each side of the strips for the width of the milling machine plus an additional 12” minimum per side or edge of pavement whichever is smaller, and as directed by the Engineer.

Sweep and broom as noted and with the equipment indicated in Subsection 643-3.04, No. 6, Sweeping and Power Brooming.

406-3.02 TOLERANCES FOR RUMBLE STRIPS.

1.	Length:   1/2-inch.

2.	Width:  1/2-inch.

3.	Depth:  1/16-inch.

4.	Spacing:   1/2-inch.

5.	Alignment:  1-inch from the striping layout in the Plans; existing striping and re-established striping.

If it is determined that the rumble strips are not being placed to specification, make immediate adjustments to correct the problem.

Rumble strips are unacceptable if:

1.	The strips are not straight.

2.	The length or width does not meet tolerance.

3.	The depth of the depression does not meet tolerance.

4.	The depression/indentation concave surface is not smooth, does not meet tolerance.

5.	The edge of the indentation/depression is not straight, smooth, and free of spalling.

6.	Pavement surface is damaged as a result of improper rumble strip installation.

Unacceptable rumble strip installation, dimensional, alignment, surface irregularities, and surface damage shall be ground, resurfaced and the rumble strip reinstalled to the satisfaction of the Engineer and at the Contractor’s expense.  Perform repairs using equipment similar to the equipment initially used to mill the rumble strip.  Do not perform repairs in a “patch work” manner.  If more than one repair is required; in a group of rumble strips repair the entire group.  Where a repair is required in a continuous run, repair the unacceptable rumble strip(s) and repair or replace the rumble strip to each side of the unacceptable rumble strip as required to provide continuity between rumble strips as originally intended.  The Engineer will confirm the extent of the repair(s) required.

If during production the work becomes unacceptable the Engineer may require resumption of testing, Subsection 406-3.03.  Testing in addition to the initial test for each rumble strip type will be at the Contractor’s expense.

406-3.03 RUMBLE STRIP TEST SECTION.  Install an initial 1/4 mile test section for each of the following rumble strip type(s):

3.03.  Include one, both or another type to suit the project specific requirements.

3.03.  Include one, both or another type to suit the project specific requirements.

1.	Shoulder.

2.	Centerline.

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip, including the surface inside each depression, without damaging the surrounding asphalt pavement.  If any of the initial test sections do not meet tolerances, provide new equipment, new method, or make necessary adjustments and retest.  These additional test sections will be required before production runs will be allowed to begin.

Testing in addition to the initial test sections, one for the shoulder type and one for the centerline type, will be at the Contractor’s expense.

Additionally, demonstrate the means and methods, including the equipment, for containing dust and waste material.

406-3.04 TRAFFIC STRIPING RE-ESTABLISHMENT.  Traffic striping is required to provide guidance for the rumble strip installation operation.  Contractor, where shoulder and/or centerline striping is missing to the extent that rumble strip location cannot be determined by the Engineer, re-establish the striping location prior to the milling operation.  Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping.  Maintain the same lane widths that exist at each end of the missing striping.  Provide sufficient location marking or “rabbit tracks” to ensure an accurate milling operation.  Shoulder re-striping is not required.  Re-establishing roadway striping location will not be measured or paid for separately but will be subsidiary to the respective rumble strip pay items.

406-3.05  RUMBLE STRIP INSTALLATION.  Install the following types of rumble strip at the locations shown in the Plans:

3.05. Include one, both or another type to suit the project specific requirements.

3.05. Include one, both or another type to suit the project specific requirements.

1.	Shoulder.  Do not disturb existing shoulder striping.

2.	Centerline.  Place along the roadway centerline according to the patterns shown in the Plans.  Replace existing centerline stripe(s) after milling the pavement.  Payment for replacement striping is paid under Section 670, Traffic Markings.

In compacted pavement with a temperature below 80˚ F, mill each type of rumble strip to the dimensions shown in the Plans.  Locate the inside edge of the rumble strip as shown in the Plans.  The Engineer will randomly check the edge alignment of the milled pattern.

406-3.06 CLEAN UP OF MILLINGS.  Handle, transport, and store, or dispose of material according to the Alaska Department of Environmental Conservation (DEC) regulations.  Remove off the project, on a daily basis, waste material (millings) resulting from the operation.

Disposal:  Dispose waste material outside the project limits, unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Milled material not being spread on the roadway side slopes requires a Solid Waste Disposal Permit from the DEC.  Obtain a permit for disposal of milled material or dispose the material in a site previously approved.

Remove millings immediately following rumble strip installation.  Maintain the removal operation within 50 feet of the milling machine.  Dry power brooming and power brooming without direct immediate means of collection/pickup is not permitted.

During milling operations keep the travel lanes free of milling debris.  Do not berm the millings at the shoulder edge, do not allow milling debris to impede roadway drainage or enter waterways.  Use a sweeper, sweeper/vacuum, (Subsection 643-3.04 No. 6, Street Sweeping, and Power Brooming), continuously removing waste material, including dust from the operation.  Keep millings damp to help control airborne dust.  Millings shall not enter adjacent lanes open to traffic.

Remove the waste material from the roadway surface and any adjacent pathway beyond the shoulder.  Shoulder millings may be placed off of the road or pathway beyond the shoulder on the side slopes, except in areas where guardrail is present.  Uniformly spread shoulder millings on the roadway side slopes; alternatively, it may become property of the Contractor and disposed of off the project as indicated above.

Milled roadway segments shall be returned to debris-free state prior to re-opening for traffic.

406-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Measure pay units by station, foot, or mile parallel to the centerline of the highway.

Station.  A single lineal measurement for every measured station for each shoulder rumble strip and centerline rumble strip installed.

Linear Foot.  A single lineal measurement for every measured foot of rumble strip installed.

Mile.  A single lineal measurement for every measured mile for each shoulder rumble strip and centerline rumble strip installed.

Shoulder rumble strip measurement includes gaps (provided for bicycles or other as shown in the Plans) between groups of rumble strips.

406-5.01 BASIS OF PAYMENT.  Section 109.

Except where specified as individual Pay Items:

All work, including test strips and materials is subsidiary to 406 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

406(1)	Rumble Strips	Lump Sum

406(2)	Rumble Strips	Station

406(3)	Rumble Strips	Linear Foot

406(4)	Rumble Strips – Shoulders	Mile

406(5)	Rumble Strips – Centerline	Mile

406(6)	Sweeping and Disposal of Millings – Shoulders	Lump Sum

406(7)	Sweeping and Disposal of Millings – Centerline	Lump Sum

CR406-110812

Special Provision

HMA, Type ____. Type VH or V. If V remove the "H" from the title.

Add the following Section:

SECTION 408
HOT MIX ASPHALT PAVEMENT - TYPE VH

Sect 408: CR408

Related Sect/Sp:  306/CR306, 401/CR401, 702/CR702.1, 703/CR703.1

Related Sect/Sp:

(Superpave)

408-1.01  DESCRIPTION.  Construct one or more courses of plant-produced Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

HMA, Type ____. Type VH or V. If V remove the "H" from 1 below.

1.	In this Section HMA refers to Type V, except where noted otherwise.

Include CR401.1 if you have temporary pavement, prelevel/leveling course, driveways or side roads tie-ins.

408-1.02  REFERENCES.

1.	Section 401 Hot Mix Asphalt Pavement. (HMA Type I, II, III, and IV)

a.	Temporary Asphalt Pavement: HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

MATERIALS

408-2.01  ASPHALT BINDER.  Conform to Subsection 702-2.01. If binder performance grade is not specified, use PG 64-40E.

Provide test reports for each batch of asphalt binder showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt binder weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt binder loaded.

6.	Type and percent of liquid anti-strip added.

Asphalt binder may be conditionally accepted at the source if a manufacturer's certification of compliance is provided, according to Subsection 106-1.05, and the applicable requirements of Section 702 are met.

408-2.02  LIQUID ANTI-STRIP ADDITIVE. Use anti-strip agents in proportions determined by ATM 414 and included in the approved Job Mix Design (JMD).  At least  90% of the aggregate must remain coated when tested according to ATM 414.  The following minimum dose (percent) of liquid anti-strip by weight of asphalt binder is required:

| Liquid Anti-strip Type | Minimum Dose by Weight of Asphalt Binder, % |
| --- | --- |
| Amines based | 0.30 |
| Phosphate Ester based | 0.30 |
| Organ-Silane based | 0.05 |

408-2.03  JOINT ADHESIVE. Conform to Subsection 702-2.05.

408-2.04  JOINT SEALANT. Conform to Subsection 702-2.06.

408-2.05  WARM MIX ASPHALT. Conform to Subsection 702-2.07.

408-2.06  ASPHALT RELEASE AGENT.  Conform to Subsection 702-2.08.

408-2.07  AGGREGATES. Conform to Subsection 703.2.04. Use a minimum of three stockpiles of crushed aggregate (coarse, intermediate, and fine).  Place blend material, if any, in a fourth pile.

408-2.08  RECYCLED ASPHALT PAVEMENT. Not allowed in connection with HMA Type V.

HMA, Type ____. Type VH or V. If V remove the "H" from 2.08 and 2.09 below.

408-2.09  JOB MIX DESIGN.  Provide target values for gradation that satisfy both the broad band gradation limits shown in Table 703-4 and the requirements for Table 408-1 for Type V HMA.

TABLE 408-1

HMA Design Requirements

| DESIGN PARAMETERS |  |
| --- | --- |
| Design ESALs, Millions | 0.3 to < 3 |
| Rut Index, Max., ATM 419. mm | 3 |
| Asphalt Binder Content, Min. % | 5.0 |
| Liquid Anti-Strip Additive*, % Min. | 0.3 |

* By weight of asphalt binder.

The approved JMD will specify the Target Values (TV) for gradation, the TV for asphalt binder content, the Maximum Specific Gravity (MSG) of the HMA, the Additives, and the recommended mixing temperature range.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant.  The letter shall include the proposed gradation for the JMD, gradation for individual stockpiles, and the blend ratio of each aggregate stockpile.

2.	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) in the proposed mix design. Furnish a total of 500 pounds of material in the proportional amounts in the proposed JMD.

3.	Five separate 1-gallon samples of the asphalt binder proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt binder or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

5.	Testing results per Subsection 106-1.03.1 for each aggregate type proposed for use.

HMA, Type ____. Type VH or V. If V remove the "H" from the paragraph below.

The Engineer will evaluate the material and the proposed gradation using ATM 417 or AASHTO R35 and the requirements of Table 408-1 for Type V HMA, and establish the approved JMD which will become a part of the Contract.

Obtain an approved JMD prior to shipment of aggregates to an asphalt plant site or producing HMA for payment.

Contractor Mix Design.  If a bid item for JMD appears in the contract, or if the Engineer approves a request from the Contractor to perform the JMD at no cost to the Department, provide a JMD following the requirements specified in this section.  Submit the JMD to the Engineer at least 15 working days before HMA production.  Submit samples to the Engineer upon request for JMD verification testing.

All Contractor-furnished JMDs must be sealed by a professional Engineer registered in the State of Alaska.  The Professional Engineer shall certify that the JMD was performed according to the specified procedures, and meets all project specifications.

Changes. Submit a new JMD with changes noted and new samples in the same manner as the original JMD submittal when:

a.	The results of the JMD evaluation do not achieve the requirements specified in Table 408-1

b.	The asphalt binder source is changed

c.	The source of aggregate, aggregate quality or gradation is changed

d.	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD; the original, or a replacement JMD.

The Engineer has the option to require further verification of the JMD under 408-2.10 Process Quality Control.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, materials, and the JMD, Subsection 408-2.10.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.

Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design, per Subsection 408-5.01.

408-2.10 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer at the "Pre-Paving Meeting," Subsection 408-3.01, the JMD and a documentation plan that provides a complete, accurate, and clear record of the sampling and testing results.

Failure to perform quality control forfeits the Contractor's right to a retest under Subsection 408-4.02

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

Supplemental Process Quality Control.

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineer's approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train shall be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 408-3.04.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Failed Test Strip:  the Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

Refer to Subsection 408-5.01 for payment of test strips.

CONSTRUCTION REQUIREMENTS

408-3.01  PRE-PAVING MEETING. Meet with the Engineer for a pre-paving meeting in the presence of the project superintendent and paving foreman at least (5) working days before beginning paving operations.  Submit a paving plan and pavement inspection plan at the meeting.  When directed by the Engineer, make adjustments to the plan and resubmit.

1.	Paving Plan.  Include the following:

a.	Sequence of operations

b.	List of equipment that will be used for production, transport, pick-up (if applicable), laydown, and compaction

c.	Reserved

d.	Procedures to produce consistent HMA

e.	Procedures to minimize material and thermal segregation

f.	Procedures to minimize premature cooling

g.	Procedures to achieve HMA density

h.	Procedures for joint construction including corrective action for joints that do not meet surface tolerance requirements

i.	Quality control testing methods, frequencies and sample locations for gradation, asphalt binder content, and density, and

J.	Any other information or procedures necessary to provide completed HMA construction that meets the Contract Requirements

2.	Pavement Inspection Plan. Include the following:

a.	Process for daily inspections

b.	Means and methods to remove and dispose of project materials

408-3.02 CONTRACTOR QUALITY CONTROL. Perform quality control (QC) of HMA materials in accordance with Subsection 106-1.03.

408-3.03  WEATHER LIMITATIONS.  Place HMA on a stable/non-yielding roadbed. Do not place HMA when the base material is wet or frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA when the roadway surface temperature is colder than 40° F, or after September 15th without the Engineer's approval in writing.

408-3.04  EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production and test strip HMA.

408-3.05  ASPHALT MIXING PLANT.  Meet AASHTO M 156.  Use an HMA plant capable of producing at least 150 tons of HMA per hour noted on posted DEC air quality permit, designed to dry aggregates, maintain consistent and accurate temperature control, and accurately proportion asphalt binder and aggregates.  Calibrate the HMA plant and furnish copies of the calibration data to the Engineer at least 24 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt binder supply line just before it enters the plant (after the 3-way valve) for sampling asphalt binder.  Provide aggregate and asphalt binder-sampling locations meeting OSHA safety requirements.

You may use belt conveyor scales to proportion plant blends and mixtures if the scales meet the general requirements for weighing equipment and are calibrated according to the manufacturer’s instructions.

408-3.06  HAULING EQUIPMENT.  Haul HMA in trucks with tight, clean, smooth metal beds. Keep beds free of petroleum oils, solvents, or other materials that would adversely affect the mixture. Apply a thin coat of approved asphalt release agent to beds as necessary to prevent mixture adherence. Provide trucks with covers attached and available for use.

Do not haul HMA on barges.

When directed by the Engineer cover the HMA in the hauling vehicle(s).

408-3.07  ASPHALT PAVERS. Use self-propelled asphalt pavers with heated vibratory screed assemblies to spread and finish HMA to the specified section widths and thicknesses without introducing thermal or material segregation.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.  Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA. Heat and vibrate screed extensions. Place auger extensions within 20 inches of the screed extensions or per written manufacturer’s recommendations.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.

Equip the paver with automatic screed controls capable of operating from a reference line or a ski from either or both sides of the paver.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

408-3.08  ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Use rollers designed to compact HMA and capable of reversing without shoving or tearing the mixture. Select rollers that will not crush the aggregate or displace the HMA. Equip vibratory rollers with separate vibration and propulsion controls.

Equip the rollers with an infrared thermometer that measures and displays the surface temperature to the operator. Infrared thermometer may be hand-held or fixed to the roller.

Utilize a pneumatic roller in the complement of rollers to compact the leveling course.  Use fully skirted pneumatic-tire roller having a minimum operating weight of 3000 pounds per tire.

Equip rollers (breakdown and intermediate) with intelligent compaction (IC) equipment according to Section 411 Intelligent Compaction.

Confirm IC equip is required with PM/Materials/Construction. If IC is required, add Section 411 Intelligent Compaction, provided by the Materials Dept. If IC is not required delete paragraph Equip rollers (breakdown and intermediate) …

408-3.09  RESERVED.

408-3.10  PREPARATION OF EXISTING SURFACE. Prepare existing surfaces according to the Contract. Prior to placing HMA, clean existing surfaces of loose material and uniformly coat contact surfaces of curbing, gutters, manholes and other structures with tack coat material meeting Section 402.  Treat cold joint surfaces according to 408-3.17.  Allow tack coat to break before placement of HMA on these surfaces.  Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before applying tack coat to an existing paved surface, clean and patch the surface.  Remove irregularities to provide a reasonably smooth and uniform surface.  Remove and replace unstable areas with HMA.  Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.  Clean loose material from cracks.  Fill the cleaned cracks, wider than 1 inch, with HMA tamped in place.  Wash and/or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

1.	Prelevel remaining ruts, pavement delaminations, and depressions having a depth greater than 1/2 inch with an approved HMA.

2.	Notify the Engineer of pavement areas that appear thin or unstable.  Where milling operation creates thin or unstable pavement areas, or where it breaks through existing pavement, remove thin and unstable pavement, and 2 inches of existing base material, compact and replace with an approved HMA.

408-3.11  PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt binder to the asphalt mixing plant at a uniform temperature, within the recommended mixing temperature range.

408-3.12  PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt binder content, does not exceed 0.5% (by total weight of mix), as determined by ATM 407.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable per Subsection 105-1.11.

408-3.13  MIXING. Combine the aggregate, asphalt binder, and additives in the mixer in the amounts required by the JMD. Mix to obtain at least 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt binder.

Mix the HMA within the temperature range determined by the JMD.

Upon the Engineer’s request, provide daily burner charts showing start/stop times and temperatures.

408-3.14  TEMPORARY STORAGE OF HMA.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.

Signs of visible segregation, heat loss, changes from the JMD, change in the characteristics of asphalt binder, lumpiness, and stiffness of the mixture, are causes for rejection.

Do not store HMA on barges.

408-3.15  PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, are placed and accepted.

Do not place HMA abutting curb and gutter until curb and gutter are installed, except as approved by the Engineer. Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

When practicable, adjust elevation of metal fixtures before paving the final lift, so they will be between 1/4 and 1/2 inch below the top surface of the final lift.  Metal fixtures include, but are not limited to manholes, valve boxes, monument cases, hand holes, and drains.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

Place HMA over bridge deck membranes according to Section 508 and the membrane manufacturer's recommendations.

Do not mix HMA produced from different plants for testing or paving.

408-3.16  COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Prevent indentation in the mat; do not leave rollers or other equipment standing on HMA that has not sufficiently cooled.

The Lower Specification Limit for density is 93.0% of the Maximum Specific Gravity (MSG) as determined by ATM 409.  The MSG from the approved JMD is used for the first lot of each type of HMA.  The MSG for additional lots is determined from the first sublot of each lot.

408-3.17  JOINTS.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the pre-paving meeting.  Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints 15 to 25 degrees.

For all joints below the top lift, uniformly coat joint surfaces with tack coat material meeting Section 402.

Uniformly coat the joint face of all top lift joints with a joint adhesive. Follow joint adhesive manufacturer's recommendations for temperatures and application method.  Remove joint adhesive applied to the top of pavement surface.  If infrared joint heaters are used and passing joint densities are achieved in each of the first three joint densities taken, then joint adhesive is not required.

The Lower Specification Limit for top lift longitudinal joint density is 91.0% of the MSG of the panel completing the joint. MSG will be determined according to ATM 409.  Top lift longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

For top lift panels that have a longitudinal joint density less than 91.0% of the MSG in a sublot, seal the surface of the longitudinal joints with joint sealant within that sublot or as directed.   Apply joint sealant according to the manufacturer’s recommendations while the HMA is clean, free of moisture and prior to final traffic marking.  Place the sealant at a maximum application rate of 0.15 gallons per square yard, and at least 12 inches wide centered on the longitudinal joint.  After surface sealing, inlay by grinding pavement striping into the sealed HMA. Use grooving equipment that grinds a dry cut to groove the width, length, and thickness of the striping within the specified striping tolerances.

Correct improperly formed joints that result in surface irregularities according to a corrective action plan.

Complete all hot lapped joints while the mat temperature is over 230F as measured by the Engineer, within 3 inches of the joint. Tack coat and joint adhesive are not required for hot lapped joints. Hot lapped joints will receive the full Longitudinal Joint Density Price Adjustment incentive without testing for joint density.

Top lift longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

408-3.18  SURFACE REQUIREMENTS AND TOLERANCE.  The finished surface of all HMA paving must match dimensions shown in the contract for horizontal alignment and width, profile grade and elevation, crown slope, and pavement thickness. Water must drain across the pavement surface without ponding. The surface must have a uniform texture, without ridges, puddles, humps, depressions, and roller marks. The surface must not exhibit raveling, cracking, tearing, asphalt bleeding, or aggregate segregation. Leave no foreign material, uncoated aggregate, or oversize aggregate on the HMA surface.

The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  The Engineer will identify pavement areas that deviate more than 3/16 inch from the straightedge, including joints, as defective work. Perform corrective work by removing and replacing, grinding, cold milling or infrared heating such areas as required. Do not surface patch. After the Contractor performs corrective work, the Engineer will retest the area.

The Engineer will use an inertial profiler to measure the top lift HMA surface in the driving lanes for surface smoothness within 21 days after paving is complete and driving lanes are delineated.

Profiler measurements will not be taken in turn lanes, ramps, lane transitions, or within 25 feet of bridge abutments and transverse joints with pre-existing pavement.

The Engineer will measure the pavement smoothness in both wheel paths of each lane.  The smoothness is measured as International Roughness Index (IRI), reported as inches/mile, at 0.1-mile increments.  Pavement smoothness is the average of all IRI measurements for the project.

The Engineer will identify areas requiring corrective action in accordance with Table 408-4.  Perform full-width corrective action in those areas.  The Engineer may waive corrective work for localized roughness for deficiencies resulting from manholes or other similar appurtenances near the wheel path.

Perform Corrective Actions according to one of the following or by a method approved by the Engineer:

1.	Diamond Grinding.  If the required pavement thickness is not decreased by more than 1/4-inch, grind to the required surface tolerance and cross section.  Remove and dispose of all waste materials.  Apply joint sealant and sand to exposed aggregates per the manufacturer’s recommendations.

2.	Overlaying.  Mill or sawcut the existing pavement to provide a vertical transverse joint face to match the overlay to the existing pavement.  Apply tack coat on the milled surface and joint adhesive to all vertical joints and overlay the full width of the underlying pavement surface.  Use the same approved HMA for overlays.  Place a minimum overlay thickness of 2.0 inches.

3.	Mill and Fill. Mill the existing pavement to provide a vertical transverse joint face. Apply tack coat to the milled surface and joint adhesive to all vertical joints prior to inlaying new HMA to match the existing pavement.  Use the same approved HMA.  Place a minimum thickness of 2.0 inches.

After completion of corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.

Price adjustments for pavement smoothness will be calculated according to Subsection 408-4.03.3.

408-3.19  REPAIRING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt. Remove and dispose defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat according to Section 402.  Place and compact fresh HMA so that compaction, grade, and smoothness requirements are met.

408-3.20  ROADWAY MAINTENANCE.  Inspect daily according to pavement inspection plan. Remove, and dispose of project materials incorrectly deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The Contractor is responsible for damage caused by not removing these materials and any damage to the roadway from the removal method(s).

Repair damage to the existing roadway that results from fugitive materials or their removal.

408-4.01  METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a.	By weight.  No deduction is made for the weight of asphalt binder or anti stripping additive or cutting back joints.

b.	By the final HMA surface area.

2.	Asphalt Binder.  By weight, as follows:

Method 1 will be used for determining asphalt binder quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment is made for any asphalt binder more than 0.4% above the optimum asphalt binder content specified in the JMD.

Method 1: Percent of asphalt binder for each sublot multiplied by the total HMA weight represented by that sublot.  The Engineer will use either ATM 405 or ATM 406 to determine the percent of asphalt binder.  The same test method used for the acceptance testing of the sublot will be used for computation of the asphalt binder quantity.  In the absence of testing, the percent of asphalt binder is the target value for asphalt binder in the JMD.

Method 2: Supplier's invoices minus waste, diversion, and remnant.  This procedure is an Engineer’s option for projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers are weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment is based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt binder. The Engineer will determine the method. The weight of asphalt binder in waste HMA is calculated using the target value for asphalt binder as specified in the JMD.

3.	Job Mix Design. When specified, a Contractor furnished JMD is measured as one according to the HMA type.

4. If there is temporary pavement in the project include Section 401 for the mix and if not subsidiary for the Pay Item.

4.	Temporary Pavement.  Per Section 401.

5.	Leveling Course.  Per Section 401.

5. If there is a leveling course in the project include Section 401 for the mix and if not subsidiary for the Pay Item.

6.	HMA Price Adjustment.  Calculated by quality level analysis under Subsection 408-4.03.1.

7.	Longitudinal Joint Density Price Adjustment.  By the linear foot of top lift longitudinal joint under Subsection 408-4.03.2.

8.	Joint Adhesive.  By the linear foot of longitudinal and transverse joint.

9.	Pavement Smoothness Price Adjustment.  Calculated from inertial profiler data using FHWA’s ProVAL software under Subsection 408-4.03.3.

10.	Asphalt Material Price Adjustment.  Determined under Subsection 408-4.04.

11.	Liquid Anti-Strip Additive.  Based on the number of tons of asphalt binder containing required additive.

12.	Crack Repair.  From end to end of the crack repaired according to 408-3.10, measured horizontally along the centerline of the crack.

13.	Prelevel for Ruts, Delaminations, and Depressions.  By the surface area where prelevel is placed according to 408-3.10(1), measured according to Section 109.

14.	Repair Unstable Pavement.  By the surface area of pavement repaired according to 408-3.10(2), measured according to Section 109.

408-4.02 ACCEPTANCE SAMPLING AND TESTING.  The bid quantity of each type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot is normally 5,000 tons. The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 408-4.03.1. Seasonal startup or a new JMD requires starting a new lot.

If less than 8 sublots have been placed at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot. The price adjustment computed for the prior lot will include the samples from the shortened lot. Density test results from material in the shortened lot will be based on the MSG of the first sublot of the shortened lot. If there is no prior lot, and there are at least 3 sublots, the material in the shortened lot will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot. If there are less than 3 sublots, the HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

If 8 or 9 sublots have been placed at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results in the shortened lot

If the bid quantity is between 1,500 to 4,999 tons, the quantity is considered one lot.  The lot is divided into sublots of 500 tons, each randomly sampled and tested for asphalt binder content, density, and gradation according to this Subsection. The lot is evaluated for price adjustment according to Subsection 408-4.03.1.

For bid quantity less than 1,500 tons, HMA will be accepted for payment based on the Engineer’s approval of the JMD, and placement and compaction of the HMA to the specified depth, finished surface requirements, and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance.

Sampling and testing include the following:

1.	Asphalt Binder Content.  HMA samples shall be taken randomly by the Contractor in the presence of the Engineer from behind the paver screed before initial compaction, or will be taken randomly by the Engineer from the windrow, according to ATM 402 or ATM 403, at the discretion of the Engineer. The location (behind the paver screed or windrow) will be determined at the pre-paving meeting. Random sampling locations will be determined by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  Asphalt binder content will be determined according to ATM 405 or ATM 406, at the discretion of the Engineer.

2.	Aggregate Gradation. Aggregates tested for gradation acceptance will have the full tolerances from Table 408-2 applied.

a.	Drum Mix Plants.  Samples will be taken from the combined aggregate cold feed conveyor via a diverter device, from the stopped conveyor belt or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for samples from the conveyer system will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.

b.	Batch Plants.  Samples will be taken from dry batched aggregates according to ATM 301 or from the same location as samples for determination of asphalt binder content, at the discretion of the Engineer.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.  The aggregate gradation for dry batch samples will be determined according to ATM 304.  For HMA samples, the gradation will be determined according to ATM 408 from the aggregate remaining after the ignition oven (ATM 406) has burned off the asphalt binder.

3.	Density.  The Engineer will determine and mark the location(s) where the Contractor takes each core sample.

a.	Mat Cores:  The location(s) for taking core samples is determined using a set of random numbers (independent of asphalt binder and aggregate sampling set of random numbers) and the Engineer's judgment.  Take no mat cores within 1 foot of a joint or edge. Core samples are not taken on bridge decks.

b.	Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.

Take core samples according to ATM 413 in the presence of the Engineer. Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one 6-inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  The Engineer will immediately take possession of the samples.  Backfill and compact voids left by coring with new HMA within 24 hours according to ATM 413. The Engineer will determine density of samples according to ATM 410.

4.	Retest.  When test results have failed to meet specifications, retest of acceptance test results for asphalt binder content, gradation, and density may be requested provided the quality control requirements of Subsection 408-3.02 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2-foot radius of the original core.  The original test results are discarded and the retest result is used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  When gradation and asphalt binder content are determined from the same sample, a request for a retest of either gradation or asphalt binder content results in a retest of both. Both gradation and asphalt binder content retest results are used in the price adjustment calculation. Retesting will be performed by the region department laboratory.

5.	Asphalt Binder Grade.  The lot size for asphalt binder is 200 tons.  If a project has more than one lot and the remaining asphalt binder quantity is less than 150 tons, it is added to the previous lot and that total quantity will be evaluated as one lot.  If the remaining asphalt binder quantity is 150 tons or greater, it is sampled, tested and evaluated as a separate lot.

If the bid quantity of asphalt binder is between 85 – 200 tons, the bid quantity is considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt binder less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Sample asphalt binder at the plant from the supply line in the presence of the Engineer according to ATM 401.  The Engineer will take immediate possession of the samples.  Take three samples from each lot, one for acceptance testing, one for Contractor requested retesting, and one held in reserve for referee testing if requested.  Meet Subsection 702 requirements for asphalt binder quality.

6.	Asphalt Binder Grade Retest. The assigned test value (ATV) will be determined using ASTM D3244. Testing will be by AASHTO accredited independent laboratories.  Each test will be completed by a different laboratory.

Retest.  Submit a written request, for a retest, no more than 7 days from receiving notice of the failed acceptance test. In the request, identify the retest laboratory. The Engineer will send the second sample (retest sample) to the laboratory.  Provide the retest results to the Engineer. Contractor pays for the retest costs.

If the average of the combined test results ([acceptance + retest]/2) passes the specification requirement, the average value becomes the ATV. If this ATV fails the specification requirement, the Engineer or Contractor may request the third sample (referee sample) be tested.

Referee Test. The Engineer will send the third sample (referee sample) to an agreed upon laboratory. The average of the combined test results ([acceptance + retest + referee]/3) equals the ATV. If the ATV fails to meet specifications, the Contractor pays for the referee test.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

The Engineer may reject material which appears to be defective based on visual inspection.  If a test of rejected material is requested, a minimum of two samples are collected from the rejected material and tested.  If all test results are within specification limits, payment for the material is made.

The following methods are applied to each type of HMA with Price Adjustment Pay Items in the Contract.  These methods describe how price adjustments are determined based on the quality of the HMA, binder, longitudinal joint density, and pavement smoothness.

1.	HMA Price Adjustment.  Acceptance test results for HMA asphalt binder content, gradation and mat density are used in HMA price adjustment.  These test results for a lot are analyzed collectively and statistically by the Quality Level Analysis (QLA) method as specified in Subsection 106-1.03.3 to determine the total estimated percentage of the lot that is within specification limits. The values for percent passing the #200 sieve, asphalt binder content and density test results are reported to the nearest 0.1 percent.  All other sieves used in QLA are reported to the nearest whole number.

The HMA price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor (CPF) for HMA that includes gradation and asphalt binder content.  The second is the density pay factor (DPF).

A lot containing material with less than a 1.000 pay factor is accepted at an adjusted price, provided that pay factor is at least 0.800 and there are no isolated defects identified by the Engineer. A lot containing material that fails to obtain the minimum pay factor is considered unacceptable and rejected under Subsection 105-1.11.

HMA pay factors are computed as follows:

a.	All statistical Quality Level Analysis (QLA) is computed using the Engineer’s Price Adjustment programs.

b.	The USL and LSL are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2, or as shown below.  The TV is the specification value shown in the approved Job Mix Design.

TABLE 408-2

HMA LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICAITON LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| ¾” or largest sieve size | 99 | 100 |
| ½ inch sieve or first sieve retaining aggregate | TV-6 | TV+6 |
| 3/8 inch sieve | TV-6 | TV+6 |
| No. 4 sieve | TV-6 | TV+6 |
| No. 8 sieve | TV-6 | TV+6 |
| No. 16 sieve | TV-5 | TV+5 |
| No. 30 sieve | TV-4 | TV+4 |
| No. 50 sieve | TV-4 | TV+4 |
| No. 100 sieve | TV-3 | TV+3 |
| No. 200 sieve* | TV-2.0 | TV+2.0 |
| Asphalt Binder Content, % | TV-0.4 | TV+0.4 |
| Mat Density, % | 93.0 | 100.0 |

*LSL for the No. 200 Sieve is restricted by the broad band limits in Table 703-4.

c.	The percent within limits (PWL), Quality Levels and characteristic pay factors (PFs) are determined by the Engineer for each Lot in accordance with Subsection 106-1.03.3.  The Composite Pay Factor (CPF) for the lot is determined from gradation and asphalt binder content (ac) acceptance test results using the following example formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

Table 408-3 gives the weight factor (f) for each test property considered.

HMA, Type ____. Type VH or V. If V remove the "H" from Table 408-3 below.

TABLE 408-3

WEIGHT FACTORS

| Property | Type V Factor “f” |
| --- | --- |
| ¾ inch sieve | 4 |
| ½ inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt Content, % | 40 |

The Density Pay Factor (DPF) is computed using HMA mat core compaction acceptance test results.

The CPF and DPF are rounded to the nearest 0.001.  The price adjustment for each individual lot is calculated as follows:

HMA Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower

PAB = $140.

PAB = Price Adjustment Base = $140.00 per ton.

The HMA Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 408(8_).

2.	Longitudinal Joint Density Price Adjustment. Longitudinal joint density price adjustment will be based on the project average of all top lift cold joint densities and determined as follows:

a.	Disincentive. Project average top lift joint density less than 91.0% MSG:

Deduct $3.00 per lineal foot.

b.	Incentive. Project average top lift joint density greater than:

92.0% MSG.		Add $0.50 per lineal foot

93.0% MSG.		Add $1.00 per lineal foot

94.0% MSG.		Add $1.50 per lineal foot

The longitudinal Joint Density Price Adjustment is the total price adjustment paid for under Item 408(9).

3.	Pavement Smoothness Price Adjustment.  Pavement smoothness will be measured by the Engineer and reported as IRI (inches/mile), according to Subsection 408-3.18.  Incentive for pavement smoothness shall apply only if both the project average CPF and DPF are greater than or equal to 1.000.  Disincentive for pavement smoothness shall apply regardless of the project average CPF or DPF.

The Engineer will calculate the pavement smoothness price adjustment according to Method 1 (pavement placed over graded subgrade) or Method 2 (pavement placed over existing pavement). The SF is rounded to the nearest 0.001.

Method 1: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $140.

PAB = Price Adjustment Base = $140.00 per ton

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor (Table 408-4)

TABLE 408-4

SMOOTHNESS FACTOR (SF)

| IRI (in./mile) | SF |
| --- | --- |
| Less than 40 | 0.050 |
| 40 to 70 | 0.050 – (IRI - 40)/600 |
| 70 to 90 | 0.000 |
| 90 to 120 | (90 – IRI)/120 |
| Greater than 120* | - |

* Corrective Work required, see Subsection 408-3.18

Method 2: SPA = PAB x PQ x SF,

Where:

SPA = Pavement Smoothness Price Adjustment

PAB = $140.

PAB = Price Adjustment Base = $140.00 per ton

PQ = Top layer HMA quantity, tons

SF = Smoothness Factor = 0.120 x RR – 0.020; SF not to exceed 0.050

RR = Roughness Reduction = (Initial IRI – Final IRI) / Initial IRI

Initial IRI = 	Pre-project average IRI as measured and reported by the Engineer.  The Initial IRI will either be included in the bid documents or the timeline for when the Initial IRI will be measured will be identified in the bid documents.

Final IRI =	Top layer HMA average IRI as measured and reported by the Engineer according to Subsection 408-3.18.

The Pavement Smoothness Price Adjustment is the total price adjustment paid for under Item 408(10).

4.	Asphalt Binder Price Adjustment. A lot quantity of asphalt binder, with a pay factor less than 1.0, is accepted or rejected per Table 408-3.01-1 Asphalt Binder Pay Factors.

TABLE 408-4.03-1

ASPHALT BINDER PAY FACTORS

| Pay Factor |  |  | 1.01 | 1.00 | 0.95 | 0.90 | 0.75 | Reject |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RTFO (Rolling Thin Film Oven) |  |  |  |  |  |  |  |  |
| DSR(a.1) | All Grades | G*/Sinδ, kPa-1 | ≥ 2.69 | 2.68–2.20 | 2.19–1.96 | 1.95–1.43 | 1.42–1.10 | < 1.10 |
| MSCR(a.2) | PG 52-40 V | JNR 3.2 |  0.39 | 0.40–0.50 | 0.51–0.59 | 0.60–0.69 | 0.70–1.00 | > 1.00 |
|  |  | % Rec3.2 | ≥ 86 | 85–75 | 74–68 | 67–60 | 59–55 | < 55 |
|  | PG 58-34 E | JNR 3.2 |  0.19 | 0.20–0.25 | 0.26–0.29 | 0.30–0.39 | 0.40–0.50 | > 0.50 |
|  |  | % Rec3.2 | ≥ 90 | 89–85 | 84–80 | 79–75 | 74–70 | < 70 |
|  | PG 64-40 E | JNR 3.2 | < 0.05 | 0.05–0.10 | 0.11–0.15 | 0.16–0.20 | 0.21–0.25 | > 0.25 |
|  |  | % Rec3.2 | ≥ 97 | 96–95 | 94–91 | 90–85 | 84 – 80 | < 80 |
| PAV (Pressurized Aging Vessel) |  |  |  |  |  |  |  |  |
| DS(a.3) | PG 64-40 E & All Other Grades | G*Sinδ, kPa | < 4711 | 4712–5000 | 5001–5289 | 5290–5578 | 5579–5867 | > 5867 |
|  | PG 52-40 V, PG 58-34 E | G*Sinδ, kPa | < 5700 | 5701–6000 | 6001–6300 | 6301–6600 | 6601 – 7000 | > 7000 |
| CS(a.4 & 5) | All Grades(a.4) | BBR, S, MPa | < 247 | 248–300 | 301–338 | 339–388 | 389–449 | > 450 |
|  | All Grades(a.5) | BBR, m | > 0.320 | 0.319–0.300 | 0.299–0.294 | 0.293–0.278 | 0.277–0.261 | < 0.261 |

Creep Stiffness (CS)	Dynamic Shear (DS)	Multiple Stress Creep Recovery (MSCR

a.	Asphalt Binder Pay Adjustment = (Lowest Pay Factor – 1) x (tons in lot) x PAB x 5

Select the lowest pay factor from:

RTFO (test the binder residue at the performance grade temperature)

(1)	DS, All Grades, G*/Sinδ, kPa-1

(2)	MSCR: PG, Select the highest pay factor corresponding to, either JNR 3.2 or % Rec3.2 values

PAV

(3)	DS, PG, G*Sinδ, kPa

(4)	CS, All Grades, BBR, S MPa

(5)	CS, All Grades, BBR, m

b.	If three consecutive acceptance samples are out of specification, stop HMA production immediately and submit a corrective action plan to the Engineer for approval.

The Asphalt Binder Price Adjustment is the sum of the price adjustments for each lot and paid for under Item 408(21).

408-4.04  ASPHALT MATERIAL PRICE ADJUSTMENT.

Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

1.	This provision shall apply:

a.	To asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318, 401 thru 405, 408, 520, 608 and 609.

b.	To cost changes in asphalt material that occur between the date of bid opening and the date on the certified bill of lading from the asphalt material refiner/producer.

c.	When there is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, AAMPI, from the date of bid opening to the date on the certified bill of lading from the asphalt refiner/producer.

2.	Provide the certified bill of lading from the asphalt material refiner/producer.

3.	The AAMPI is calculated bimonthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bimonthly calculation. The AAMPI is posted on the Department’s Statewide Materials website at and calculated according to the formula posted there. http://www.dot.state.ak.us/stwddes/desmaterials/aprice_index.shtml

4.	Price adjustment will be cumulative and calculated with each progress payment. Use the AAMPI in effect on the date of the certified bill of lading from the asphalt material refiner/producer, to calculate the price adjustment for asphalt material   The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q = Quantity of Asphalt Material incorporated into project during the pay period, in tons as measured by the Engineer

IB = Index at Bid: the Bi-monthly AAMPI in effect on date of bid, in dollars per ton

IPP =	Index at Pay Period: The bi-monthly AAMPI in effect on the date shown on the certified bill of lading from the asphalt refiner/producer, in dollars per ton

5.	Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.  The quantity for emulsified asphalts will be based on the asphalt residue material only and will be calculated using the percent residue from testing, or if not tested, from the manufacturer’s certificate of compliance.

408-5.01 BASIS OF PAYMENT.

The following items, unless included as individual Pay Items, are subsidiary to the Section 408 Hot Mix Asphalt Pavement related Pay Items as included in the bid schedule:

	Asphalt binder

	Liquid anti-strip additives

	Tack coat

	Crack sealing

	Crack repair

	Joint adhesive

	Surface sealing of longitudinal joints

	Surface tolerance corrections

	Patching defective areas

	Prelevel for ruts, delaminations, and depressions

	Repair unstable pavement

	Job mix design

	Density profiles, Subsection 408-2.10 Process Quality Control

	Repair work and materials when planing equipment breaks through existing pavement – Subsection 408-3.10 Preparation of Existing Surface

	Work and materials associated with Subsection 408-3.06 Hauling Equipment

	Work and materials associated with Subsection 408-3.20 Roadway Maintenance

Test Strips:  Subsection 408-2.10 Process Quality Control.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices for HMA and asphalt binder as included in the Bid Schedule.  Price adjustments 408(8_), 408(9), 408(10) and 408(21) do not apply.

b.	Failed.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Typically 408(8), (9), (10), and (21) will be paid under 408(22). The exception is to include 408(8), (9), (10), and (21) individually. To include 408(8), (9), (10), and (21) requires coordination/approval with/by the Engineer.

The following price adjustment Pay Items, unless included as individual Pay Items in the bid schedule, are payed under 408(22)  Combined Price Adjustment:

408(8_) HMA Price Adjustment, Type     ,

408(9) Longitudinal Joint Density Price Adjustment,

408(10) Pavement Smoothness Price Adjustment, Method    .

408(21) Asphalt Binder Price Adjustment

Item 408(8_) HMA Price Adjustment, Type    , is the sum of the price adjustments for each material lot, and for deductions and fees assessed.  Deductions and fees assessed include:

	Each mix design subsequent to the approved JMD for each type and class of HMA specified will result in a fee of $6000.

	Failure to cut core samples within the specified period will result in a deduction of $100 per sample per day.

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day.

	If an asphalt binder referee test is requested and the ATV confirms the asphalt binder does not meet Contract requirements, a fee of $500 will be assessed.

Item 408(8_) HMA Price Adjustment, Type    , does not apply to the following:

	Driveway and approach HMA.

Item 408(15) Asphalt Material Price Adjustment.

For each Section as included in Subsection 408-4.04 Asphalt Material Price Adjustment, item 1.a, the "Asphalt Material Price Adjustment" is paid under the asphalt material Pay Item for the Section with the greatest quantity as determined by the estimate of quantities included in the Plans at the time of the bid opening.

	When more than one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule the asphalt material price adjustment, for each Section's asphalt material, is paid under the Pay Item with the greatest quantity.

	When more than one asphalt material is included in the project and only one "Asphalt Material Price Adjustment" Pay Item is included in the Plans or bid schedule, the asphalt material price adjustment, for each Section's asphalt material, is paid under the one Pay Item regardless of the quantity.

	When the Pay Item "Asphalt Material Price Adjustment," is not included, for any section, no payment will be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

408(1H)	HMA, Type VH or V	Ton

408(4)	Asphalt Binder, Grade PG ##-## X         	Ton

408(7)	Liquid Anti-Strip Additives	Contingent Sum

408(8H)	HMA Price Adjustment, Type VH or V	Contingent Sum

408(9)	Longitudinal Joint Density Price Adjustment	Contingent Sum

408(10)	Pavement Smoothness Price Adjustment, Method     	Contingent Sum

408(14)	Joint Adhesive	Linear Foot

408(15)	Asphalt Material Price Adjustment	Contingent Sum

408(20)	HMA, Fiber Reinforced, Type VF	Ton

408(21)	Asphalt Binder Price Adjustment	Contingent Sum

408(22)	Combined Price Adjustment	Contingent Sum

CR408-010120

Item 408(15). For Sections 306, 307, 308, 318, 401 thru 405, 408 excluding Section 402 include the Pay Item "Asphalt Material Price Adjustment" for one Section only, the Section with the greatest asphalt material quantity.  Do not remove the pay item from the Pay Items in the special.

408(8), in the Engineer's Estimate, is a contingent sum item, with a value equal to: 5.5% X [408(1)+408(4)].

408(15), in the Engineer's Estimate, is a contingent sum item, with a value equal to: $0.00.

HMA, Type VH or V. Item 408.(1). HMA, Type ___, and 408.(8) HMA Price Adjustment, Type ___. Fill in the Type in the description "VH" (Hardrock, Table 703-3 Nordic Abrasion = 8), or "V" (Not Hardrock, Table 703-3 Nordic abrasion is not included). For Type "V" you would revise Table 703-3 Type VH column to "Type V" and remove the Nordic Abrasion. Table 703-4 would also be altered making the heading "VH" into "V". Coordinate with Materials for other changes.

.

Item 408(4). Confirm the asphalt binder performance grade, each project. Verify the performance grade matches Table 408-4.03-1 and 702-2.01-1 as in 52-40 V, etc. Add the "V" or "E" to AASHTOWare (AWP) pay items as supplemental descriptions. The grade number in the AWP Pay Item will have a space between the number (description) and the letter (supplemental description, the "V" or "E") due to the format of AWP.

Estimating 408(1) and 408(4). Be sure to look closely at both items when researching historical bid results. The Contractors will vary how they estimate the items. If the price for the binder [408(4)] is very close to $0.00, or is $0.00 the Contractor has combined the total price of binder [408(4)] with the total price of HMA [408(1)] and divided by the quantity of the HMA [408(1)] for the unit price of HMA [408(1)]. You will need to look at a variety of like item cost and the different bidder prices.  Normally one or two bidders provide a price for both the Binder [408(4)] and the HMA [408(1)]. If you are unsure, discuss the cost with other design engineers and the construction engineers. You will significantly over estimate the cost of the HMA [408(1)] if you do not subtract the unit cost of the binder [408(4)].

|  |  |  | Contractor A |  |  | Contractor B |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item | Description | Quantity (Tons) | Unit Price $/Ton | Item Cost $ | Contractor's Combined Unit Price $/Ton [408(1) + 408(4)]/408(1QTY) | Unit Price $/Ton | Item cost $ | Contractor's Combined Unit Price $/Ton [408(1) + 408(4)]/408(1QTY) |
| 408(1) | HMA, Type VH | 20,000 | 70 | 1,400,000 | 100.25 | 82 | 1,640,000 | 115.00 |
| 408(4) | Asphalt Binder, Grade PG 52-28 | 1100 | 550 | 605,000 | 0.00 | 600 | 660,000 | 0.0 |
| [408(1) + 408(4)] |  |  |  | 2,005,000 |  |  | 2,300,000 |  |
| 408(1) | HMA | 20,000 | 70 | 1,400,000 | 119.50 | 82 | 1,640,000 | 142.50 |
| 408(4) | Asphalt Binder, Grade PG 52-40 V | 1100 | 900 | 990,000 | 0.00 | 1100 | 1,210,000 | 0.00 |
| [408(1) + 408(4)] |  |  |  | 2,390,000 |  |  | 2,850,000 |  |

Special Provision

Add the following Section:

SECTION 411
INTELLIGENT COMPACTION

Sect 408: CR411 	Section 411 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:  408/CR408

Related Sect/Sp:

Projects with Section 408 Hot Mix Asphalt Pavement – Type V (Superpave) may require 411(1) Intelligent Compaction. Designer, request a copy of the Intelligent Compaction specification from the Materials Department. Coordinate with Division 400, Asphalt Pavements and Surface Treatments, as included in the project.

DIVISION 500 — STRUCTURES

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 501
STRUCTURAL CONCRETE

Sect 501:  	Section 501 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:  	Consider Section 550 of the SSHC 2017 for Class B and W concrete. See the SSHC 2017

SECTION 502
PRESTRESSING CONCRETE

Sect 502: 	 Section 502 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:

SECTION 503
REINFORCING STEEL

Sect 503:  SSP16.  	 Section 503 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:

SECTION 504
STEEL STRUCTURES

Sect 504: (CR504.1 Rplcd CR224) (CR504.1 has been aligned with the SSHC2017 format. Carefully review the special and pare to the needs of the project, current codes etc.)

Example project: AMATS: Anchorage Areawide Trails Rehab – Fish Cr Trail Z584640000 & AMATS: Fish Cr trail Rehab – Turnagain Blvd to Kona Ln CFHWY00290 (SSHC2015)

Special Provisions

CR504.1. Use when the project includes a pedestrian prefabricated steel bridge structure.

504-1.01 DESCRIPTION.  Add the following after the first paragraph:

This work includes designing, furnishing, erecting, and finishing prefabricated steel bridge and concrete abutments.

Design the prefabricated steel bridge according to the latest edition of the "AASHTO Guide Specification for Design of Pedestrian Bridges" to meet the dimensions shown on the Plans.

Conform to the "AASHTO LRFD Bridge Design Specifications" for pedestrian railing geometry and load requirements.

Do not use a timber deck without the approval of the Engineer.

Modify manufacturer's standard drawings to reflect the exact requirements and conditions unique to this project.  Clearly specify relevant information such as member sizes, geometry, bearing reactions, design loads, material properties, and other design information on the drawings.  A licensed Professional Civil Engineer registered in the State of Alaska must stamp the drawings.

504-2.01 MATERIALS.  Add the following:

Use Class A Concrete for bridge abutments as defined in Section 501.

Construct prefabricated steel bridge from ASTM A500 Grade B square and rectangular tubing and/or AASHTO M270 plate and structural shapes.

504-3.01 FABRICATION.  Add the following:

8.	Prefabricated Steel Bridge.

Galvanize steel members.

Secure a nameplate to the structure indicating the bridge manufacturer's name, maximum load limits, and year of installation.

504-3.02 ERECTION.

2.	Handling and Storing Materials.  Add the following:

Propose a location for the storage of the prefabricated steel bridge for approval of the Engineer.  Notify the Engineer 48 hours in advance of bridge delivery.

4.	Assembling Steel.  Add the following:

Follow the recommended lifting and erection procedure of the prefabricated steel bridge manufacturer.  Provide a copy of the manufacturer's lifting and erection instructions to the Engineer prior to installation.  Notify the Engineer 48 hours in advance of the bridge erection.

Verify the abutment geometry for conformance to the specified tolerances prior to bridge installation.

504-4.01 METHOD OF MEASUREMENT.  Add the following:

7.	Prefabricated Steel Bridge.  By each unit completed in place and accepted.

504-5.01 BASIS OF PAYMENT.  Add the following:

Prefabricated Steel Bridge.  At the contract unit price shown on the bid schedule, for work, including design, fabrication, erection, and abutments.  Concrete for bridge abutments will be subsidiary to the respective bridge.  Excavation and backfill required for placement of the bridge abutment will be paid for separately under Items 203(3) Unclassified Excavation and 203(6) Borrow, respectively.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

504(3)	Prefabricated Steel Bridge (length)	Each

CR504.1-071519

SECTION 505
PILING

Sect 505: CR505.1.2

Related Sect/Sp: 504/CR504.1, 660/CR660.1, 668/CR668 (future high tower special)

Special Provisions

505-3.03 DRIVING PILES. Replace the 1st sentence in the 1st paragraph with the following:

CR505.2, use with highway lighting projects.

Drive all piles, except piles for lighting standards, to the driving resistance and minimum penetration specified in the Contract documents using the pile driving criteria provided by the Engineer.

Requirements for lighting standards are for typical conditions. Specifically address soil conditions where drawing required 15 ft. embedment is insufficient, peat etc.

Add No. 5:

5.	Piles for Lighting Standards. For lighting standards, install piles of sufficient length to cut the pile at the required cut-off elevation and to provide the minimum installed length shown on the Plans.

Sites for lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length, shown on the Plans, for a lighting standard foundation cannot be achieved, install the pile tip to an elevation established by the Engineer.

CR505.2-100118R

505-3.04 SPLICES, EXTENSIONS, AND BUILD-UPS. Add the following:

CR505.1, use with high tower lighting.

High Tower Piling.

Field splices shall be located a minimum of 10 ft. from either end of the pile and limited to one per 40 ft. of pile length. Make the splice with a complete-joint-penetration groove weld with backing ring.

1.	Joint Preparation.

Cut off pile perpendicular to the pile centerline, "freehand" cutting is prohibited. Before welding, prepare pile top establishing the proper groove angle with a pipe beveller.  Touch up and repair surfaces to be welded by grinding. Clean pile ends inside and out for a width of 4 inches perpendicular to the groove, for the length of the groove, each side of the groove removing all moisture, grease, rust, mill scale, and other material that might negatively influence the weld quality.

2.	Weld Inspection.

a.	Visual Inspection (VT)	100%

b.	Ultrasonic Testing (UT)	100%

Inspection and testing by a third party American Welding Society (AWS) Certified Weld Inspector (CWI) qualified to perform Nondestructive Examination (NDE) of welds.

505-5.01 BASIS OF PAYMENT. Add the following:

Pay Items 505(20) & (21) are new and separate pay items. This is to permit more than one pay item number for multiple pile types on the same project. Numbers will need to be coordinated and added to aashtoware.

Pay Item 505(20) Furnish and Install High Tower Lighting Piles includes the costs for both furnishing and installing piles for high tower lighting in Pay Item 668(1) High Tower Lighting System Complete.

CR505.1-100118

Pay Item 505(21) Furnish and Install Lighting Standard Piles includes the costs for both furnishing and installing piles for lighting standards for Pay Item 660(3) Highway Lighting System Complete.

CR505.2-100118R

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

505(20)	Furnish and Install High Tower Lighting Piles	Each

CR505.1-100118

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

505(21)	Furnish and Install Lighting Standard Piles	Each

CR505.2-100118R

SECTION 507
BRIDGE RAILING

Sect 507: 	Section 507 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:

SECTION 508
WATERPROOFING MEMBRANE

Sect 508: CR508.1 (Previous special used in CR for reference and is aligned with the SSHC2017. Attain 508 specification for projects in the Year 2019 from the Bridge Dept. Confirm the Project Manager and Construction Engineer concur with using the special from the Bridge Department, you may need to write a project specific special. Bridge Dept. has rewritten the specification with Northern Region. Uncertain if CR concerns are addressed in the Bridge Dept. special. Be sure to address the removal of the existing membrane. CR508.1 is available in the AllProvisions_2017SSHC folder.

Insert 508 from the SSHC 2020.

Special Provision

CR511.1 Replaces the SSHC Section 511. The provision allows for precast concrete facing panels and steel soil reinforcing. If a panel facing other than precast concrete or if a polymeric soil reinforcing is used (with approval from Construction) modify the provisions.

Replace Section 511 with the following:

SECTION 511
MECHANICALLY STABILIZED EARTH (MSE) WALL

Sect 511: CR511.1 (CR511.1 Rplcd CR90)

Related Sect/Sp:  203, 501, 504, 505.  Coordinate with Bridge Department project specials …

511-1.01 DESCRIPTION.  Furnish and install a mechanically stabilized earth wall system with precast concrete facing panels and metallic, strip or grid, soil reinforcement. Provide one system; multiple systems are not permitted.

511-1.02 SUBMITTAL. All manufacturers are required to submit documentation for the Engineer's review and approval.

Submit complete working drawings and calculations, in accordance with Subsection 105-1.02 and 511-2.01.4, sealed and signed by a Civil Engineer registered in the State of Alaska.  Allow 21 days for review.

511-2.01 MATERIALS. Furnish materials in accordance with Subsection 105-1.03 and Section 106. Substitutions require the Engineer's written approval, before the working drawings are approved.

Meet the following:

Class A Concrete 	Section 501

Precast Concrete Panels 	Section 501

Reinforcing Steel 	Section 503

Structural Steel 	AASHTO M 270

Pipe and Perforated Pipe 	Section 706

Geotextile for Drainage	Subsection 729-2.02

Geogrid	Subsection 729-2.05

Geocomposite Drainage System	As Specified

Porous Backfill Material 	Subsection 703-2.10

1.	Structure Backfill and Foundation Fill. Provide backfill materials used in the structure volume free from organic or otherwise deleterious materials (less than 1 percent as determined by ATM 203) and conform to the gradation requirements of Selected Material, Type A (Section 703-2.07) with a maximum size of 6-inches or less as determined by ATM 304.  Do not exceed a plasticity Index (P.I.) of 6 as determined by ATM 204 and ATM 205. Provide material with a sodium sulfate soundness loss of less than 10 percent after four cycles, determined in accordance with AASHTO T 104 and free of shale or other particles of low durability.

When using backfill material with 80 percent passing the 3/4-inch sieve, the minimum angle of internal friction, on the portion of the material finer than the No. 10 sieve, must be 34 degrees, as tested by AASHTO T 236.

Electrochemical Requirements. Steel soil reinforcement, use backfill material meeting the following:

ELECTROCHEMICAL REQUIREMENTS

| REQUIREMENTS | VALUE | TEST METHOD |
| --- | --- | --- |
| Resistivity | 1200 ohm inches min. | AASHTO T 288 |
| pH | 5 - 10 | AASHTO T 289 |
| Chlorides | 50 ppm max. | AASHTO T 291 |
| Sulfates | 100 ppm max. | AASHTO T 290 |

The state will perform corrosion tests. Notify the Engineer of the backfill source not less than 30 days before wall construction.

2.	Wall Members. Provide facing consisting of precast concrete panels.

Manufacture concrete panels with a minimum concrete compressive strength of 4,000 psi. Finish the exposed face with ordinary finish. Locate soil reinforcement connection hardware during concrete placement to avoid contact with the panel reinforcing steel.

a.	Concrete Face Panels.  Fabricate panels conforming to Section 501, with the following exceptions and additions.

(1)	Forms.  Do not strip the forms from the units until the concrete reaches a minimum compressive strength of 1000 psi.

(2)	Angle Points.  Changes in the wall alignment shall be accomplished using prefabricated angled corner panels or special columns of the same texture and size as the flat panels, such that a continuous panel is traversing the angle point without a break in the normal horizontal and vertical joint pattern, unless directed otherwise by the Engineer.  Bevel panels, or field outs that disrupt the normal joint pattern, and/or result in a single vertical line, are not permitted.

(3)	Marking.  Clearly scribe the date of manufacture, the production lot number, and the piece mark, in the unexposed face of each panel.

(4)	Handling, Storage, and Shipping.  Handle, store, and ship all panels in such a manner as to protect them from chipping, discoloration, cracks, and fractures.  Support panels in storage on firm blocking to protect the panel connection devices, and the exposed exterior finish.  Ship the units after reaching a minimum compressive strength of 3300 psi.

(5)	Tolerances.  Manufacture all panels within the following tolerances.

(a)	Panel Dimensions.  Position panel strap connection devices within 1-inch, all other dimensions within 3/16-inch.

(b)	Panel Squareness.  Squareness as determined by the difference between the two diagonals, not to exceed 1/2-inch.

(c)	Panel Exposed Surface Finish.  Surface defects on smooth formed surfaces measured on a length of 5-feet, not to exceed 1/8-inch.  Surface defects on the textured-finished surfaces measured over a length of 5-feet, not to exceed 3/16-inch.

(d)	Panel Hidden Surface Finish.  Provide a uniform surface finish free of open pockets of aggregate or surface distortions in excess of 1/4-inch.

(6)	Testing.

(a)	Compressive Strength.  Production lots shall determine the acceptance of concrete panels with respect to compressive strength.  A single compressive strength sample will represent a production lot of a group of panels.  A production lot will consist of either ten panels or a single day's production, whichever is less.

During the production of the concrete panels, the manufacturer will randomly sample the concrete in accordance with ATM 501.  A single compressive strength sample, consisting of a minimum of four cylinders, will be randomly selected for every production lot.

Perform compression tests on a standard 6-inch by 12-inch test specimen in accordance with ATM 506.  Conduct compressive strength testing in accordance with ATM 214.

For every compressive strength sample, cure a minimum of two cylinders in accordance with ATM 506 and test at twenty-eight days.  The average compressive strength, when tested in accordance with ATM 214, will provide a compressive strength test result that will determine the compressive strength of the production lot.

Compressive strength test result greater than or equal to 4000 psi will be accepted by the Engineer for the production lot.  If the compressive test result is less than 4000 psi, then the acceptance of the production lot will be based on the following acceptance criteria.

Meet each of the requirements:

I.	Ninety percent of the compressive strength test results for the overall production shall exceed 4060 psi.

II.	The average of any six consecutive compressive test results shall exceed 4200 psi.

III.	No individual compressive strength test result shall fall below 3600 psi.

(b)	Air Content.  Perform air content tests in accordance with ATM 505.  Take air content samples at the beginning of each day's production and take compressive samples at the same time to insure compliance.

(c)	Slump Test.  Perform the slump test in accordance with ATM 503.  Determine the slump at the beginning of each day's production and take the compressive samples at the same time.

(d)	Rejection.  Failure to meet any of the requirements (6)(a) thru (6)(c) will result in rejection of units.  In addition, the Engineer will reject the panel(s) if any of the following conditions exist.

I.	Faulty casting

II.	Honeycombed or open texture concrete

III.	Cracked, including hairline cracks, or severely chipped panels

IV.	Unreasonable color variation on front face of panels

b.	Joint Materials.  Bearing pads, joint filler, and joint cover materials according to the MSE wall supplier's recommendations.

c.	Concrete Leveling Pad.  Class A concrete.

3.	Soil Reinforcement.  Carefully inspect reinforcing and attachment devices to ensure that devices are true to size and free from defects that may impair strength and durability.  The metallic strip or grid shall meet the design requirements of AASHTO Standard Specifications for Highway Bridges, latest Edition, and the wall suppliers design recommendations.

Galvanize all steel soil reinforcement and any steel connection hardware to meet AASHTO M 111. Manufacture steel strip reinforcement by hot rolling to meet ASTM A572, Grade 450, or approved alternate.

4.	Working Drawings.  Prepare working drawings as noted in 105-1.02 and as noted here. Include:

a.	Earthwork requirements including specifications for material and compaction of backfill.

b.	Details of revisions or additions to drainage systems or other facilities required to accommodate the system.

c.	Existing ground elevations verified by the Contractor for each location, involving construction wholly or partially in original ground, before preparing the final working drawings.

d.	Complete design calculations substantiating that all proposed designs satisfy the design parameters in the Contract documents. Include all design assumptions. Demonstrate the internal and external stability of the wall system.  Include, in the external stability analysis, sliding, eccentricity, bearing capacity, and global stability analysis for static and seismic conditions. Comply with the design parameters shown on the Plans, the Specifications and the latest AASHTO LRFD Bridge Design Specifications including interims.

(1)	Use the minimum height and length for any system that will effectively retain the earth behind the structure for the loading conditions, contours, profile, slope lines, or other limiting parameters shown in the Plans or in the approved working drawings. The wall system dimensions may be slightly greater, not less, than shown on the Plans and approved working drawings.

(2)	Include design soils information:

Typically the Contractor should provide the following information: To provide the following information places liability on the Owner.

(a)	Foundation soil unit density and angle of internal friction

(b)	Retained soil unit density and soil angle of internal friction

(c)	Reinforced soil unit density and angle of internal friction

e.	Complete details of all elements required for the proper construction of the wall system, including complete material specifications.

Wall system work, requiring working drawings, is prohibited until the required working drawings are approved.

5.	Acceptance of Material.  Furnish the Engineer with a Certificate of Compliance certifying that all materials, excluding backfill, comply with the applicable contract specifications.  Furnish the Engineer with a copy of all test results performed by the Contractor necessary to assure Contract compliance.

Acceptance will be based on the Certificate of Compliance, accompanying test reports, and visual inspection by the Engineer.  The Engineer may require additional testing.

511-3.01 CONSTRUCTION REQUIREMENTS.

1.	Excavation and Backfill. Excavate and backfill earth retaining systems to meet Section 205. Replace excavated material with structure backfill material meeting Section 205. Compact the material as specified under Subsection 203-3.04 and herein.

a.	Foundation Preparation.  Grade the foundation for the structure level for a width equal to or exceeding the length of reinforcement elements plus 1-foot or as shown in the Plans.  Before wall construction, compact the foundation with two passes of a vibratory drum compactor, except where constructed on rock.  Remove foundation soils found to be unsuitable and replace with backfill according to Section 205.

2.	Drainage. Provide outlet works at sags in the profile and at the low ends of the gutter.

a.	Weep Holes. Place a minimum of 2-cubic feet of porous backfill material encapsulated with geotextile at each weep hole. Cover joints between retaining wall panels, which function as weep holes, with geotextile. Dry and thoroughly clean the face panels that are to receive the geotextile.

b.	Drainage Blankets. Construct drainage blankets consisting of porous backfill material encapsulated in geotextile, collector pipes, outlet pipes, and cleanout pipes. Construct and compact the subgrade to receive the geotextile so it is free of loose or extraneous material and sharp objects that may damage the geotextile. Stretch, align, and place the fabric in a wrinkle-free manner. Overlap adjacent borders of the fabric from 12-inches to 18-inches. Repair torn or punctured fabric by covering the damaged area with a piece of fabric large enough to cover the damaged area and meet the overlap requirement.

Place the porous backfill material in horizontal layers and thoroughly consolidate by the same methods specified for structure backfill. Prohibit ponding or jetting of porous backfill material or structure backfill material. Maintain a minimum of 6-inches of porous backfill material, structure backfill, or embankment material between the fabric and the equipment during spreading and compaction of the porous backfill material.

Place perforated collector pipe, when required, within the porous backfill material to the flow line elevations shown. Place outlet pipes at sags in the flow line and at the low end of the collector pipe. Construct rock slope protection, when required, at the end of outlet pipes, as shown on the Plans. Place cleanout pipes at the high ends of collector pipes.

c.	Geocomposite Drainage Systems. Place and secure the geocomposite drainage material tightly against the excavated face, lagging or back of wall. Protect the drainage material against physical damage and grout leakage when concrete is to be placed against geocomposite drainage material.

3.	Retaining Wall Construction. Construct mechanically stabilized earth walls consisting of a facing system (precast concrete panels) to which steel soil reinforcement is connected.

Provide a field representative from the proprietary wall system on-site and available during the erection of the wall.

Provide a cast-in-place concrete leveling pad, of the type shown in the Plans or approved working drawings, at each panel foundation level. Cure the concrete a minimum of 24 hours before placement of wall panels. Place panels and support to achieve the final position.

a.	Installation Tolerances.  Handle panels for erection as the MSE wall supplier recommends.  Panels shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds.  As backfill material is placed behind the panels, maintain the panels in the final position by means the wall supplier recommends.  Concrete panels vertical and horizontal alignment tolerances shall not exceed 3/4-inch when measured with a 10-foot straight edge.  During construction, the maximum allowable offset in any panel joint shall be 3/4-inch.  The overall vertical tolerance of the wall (top to bottom) shall not exceed 1/2-inch per 10-foot of wall height.  The plumb and tolerances of each panel row at the face shall be checked before erection of the next panel row.  Should panels be out of tolerance, remove the fill, and reset panels to proper tolerances.  Make joint openings between panels uniform and no larger than 1 1/4-inch and no smaller than 1/2-inch.

Place reinforcement elements normal to the face of the wall, unless otherwise shown on the Plans.  Before placement of the reinforcing elements, compact backfill according to Section 205 and below.

b.	Backfill Placement.  Place and compact backfill material following erection of each course of panels.  Place backfill in such a manner as to avoid distortion, damage, or displacement of the wall materials. Backfill to an elevation approximately 1 1/4-inch above the facing connection level before placing the next level of soil reinforcement. Roughly level the backfill material before placing the soil reinforcement. Uniformly tension all soil reinforcement to remove any slack in the connection or material.  Correct misalignment or distortion of the facing panels and soil reinforcement. Remove and replace wall materials that become damaged during backfill placement.

Compact backfill to 95-percent of the maximum density as determined by ATM 207, or ATM 212.  Where spread footings support bridge or other structural loads, compact the top 5-feet below the bottom of the footing elevation to 98-percent as determined by ATM 207, or ATM 212.  Do not exceed 8-inches maximum lift thickness after compaction.  Decrease this lift thickness, if necessary to obtain the specified density.  The Engineer will determine field density using ATM 213, and ATM 214.

Use a lightweight mechanical tamper, roller, or vibratory system with at least three passes to achieve compaction within 3-feet of the back face of the wall facing.

The Engineer will take a minimum of one density test at each level of soil reinforcement material.

Slope the last level of backfill away from the wall facing to permit rapid water runoff away from the wall face at the end of operations each day.  Do not allow surface runoff from adjacent areas to enter the wall construction site.

Install joint filler, bearing pads, and joint-covering material concurrently with face panel placement.

Furnish and install instrumentation for monitoring corrosion, where specified.

511-4.01 METHOD OF MEASUREMENT. Section 109, and the following:

Pay Item 511(1) Mechanically Stabilized Earth Wall: by the square foot of wall face. The vertical height of each section is measured on the outer face from the top of the leveling pad, to top of wall prior to installation of coping. Measure tapered wall sections using the average height resulting from the height measured at each end of the tapered section.

Pay Item 511(2) Mechanically Stabilized Earth Wall Coping: by the linear foot measured horizontally along the top of the wall.

511-5.01 BASIS OF PAYMENT.  The contract price includes full compensation for the earth retaining structure including incidentals required to complete the work; including but not limited to: facing panels, soil reinforcement, MSE and random backfill soil, bar reinforcing steel, excavation, leveling pad, coping, and all parts of or appurtenances to the earth reinforcement system, complete-in-place.

The field representative, replacing damaged face panels and other corrective work are subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

511(1)	Mechanically Stabilized Earth Wall	Square Foot

511(2)	Mechanically Stabilized Earth Wall Coping	Linear Foot

CR511-012016

Special Provision

Add the following Section:

SECTION 514
CONCRETE SURFACE FINISH AND TREATMENT

514-1.01 DESCRIPTION. Construct surface finish and apply surface treatment on concrete walls.

514-1.02 SUBMITTAL. All manufacturers are required to submit documentation for the Engineers review and approval. Allow 21 days for review. Refer to 105-1.02 Plans and Working Drawings. Submit:

1.	Shop drawings including form liner layout and termination details. Indicate backup, rustication, reveal, and chamfer strip locations. Show jointing, form tie location and pattern of placement.

2.	Product data verifying compliance with specification.

3.	Installation instructions.

4.	Samples 24-inch x 24-inch of each pattern required.

514-2.01 MATERIALS.

Rubbed Finish	Section 501, ACI 301.

Aesthetic Fascia	Reusable and nonporous form liner.

Pattern	Similar to PQR as supplied by XYZ

Replace pattern and company.  When selecting a pattern be consistent with existing patterns used in the surrounding area.

Anti-graffiti Protection	Permanent, no discoloration, and not a sealer or vapor barrier.

Two step system:

1.	Single component clear acrylic base coat

2.	Single component clear urethane finish

514-3.01 CONSTRUCTION REQUIREMENTS. Construct surface finish, and surface treatment with trained personnel according to these specifications, ACI 301 and the manufacturer.

514-3.02 SURFACE FINISH. Apply a rubbed finish, Section 501-3.09, to all exposed concrete surface, except where an aesthetic fascia is noted in the Plans.

Aesthetic Fascia. Apply an aesthetic fascia, using form liners, to exposed vertical concrete surface where noted in the Plans. Account for the concrete quantity and dimensions associated with the form liner. Wall dimensions and concrete quantities provided on the plans are minimums and do not include allowances for the thickness of the form liner.

Place the liner with a minimum of 2-inches and a maximum of 12-inches between the edge of the liner and wall edges including joints, and finish grade. The Engineer will inspect the liner placement and installation and provide directions for required changes, corrections, or adjustment. If the Engineer approves the installation and placement, written approval will be provided.  Do not place concrete before receiving written approval from the Engineer.

514-3.03 SURFACE TREATMENT.

Anti-graffiti Protection.  Allow 28 days after the forms are removed and the concrete finish is completed before applying anti-graffiti protection treatment.  Apply base coat and two top coats. Follow the manufacturer's instructions for application and curing of the treatment materials.  Protect surfaces from the treatment materials that are not specified for coating.

514-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

Aesthetic Fascia:  Measure aesthetic fascia by the square foot of actual design exposed in the finished structure regardless of type.

Anti-graffiti Protection:  Measure anti-graffiti protection by the square foot of surface area treated.

514-5.01 BASIS OF PAYMENT.

Designer, confirm the reinforcing, concrete, forming, concrete placement, curing and finishing of the support element is covered elsewhere.

Payment for aesthetic fascia is for the fascia work and materials and is separate from the supporting element item.

Work and materials required to construct the supporting element will be paid separately under the respective items listed in the bid schedule.

Rubbed finish is subsidiary to the item being finished.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

514(1)	Aesthetic Fascia	Square Foot

514(2)	Anti-graffiti Protection	Square Foot

CR514-092016

Paint Systems:

1K vs 2K

Single-component air dry paint sometimes referred to as a 1K coating.

1K coating does not require a hardener, catalyst or activator.

a.	Latex

b.	Acrylic lacquer.

Two-component paint requires a hardener, catalyst or activator and is sometimes referred to as a 2K coating.

2K coatings will not dry without the hardener, catalyst or activator.

a.	Urethane finishes

Single Stage Paints vs Two Stage Paints

Single stage paints do not require a top coat. Single stage paints can be 1K or 2K with or without a catalyst, hardener or activator. A clear top coat may be use for enhanced durability.

Two stage paints require both a base and clear coat. Two stage paints can be either 2K or 1K. The base coat provides the color and coverage, while the clear coat provides the gloss and protection, the durability.

DOT specifies a base/clear coat single component (1K) system for simplicity of application. This allows for a color to be added to the base coat and durability (permanence) provided by the two clear top coats.

SECTION 515
DRILLED SHAFTS

Sect 515:   	Section 515 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:  501, 503

SECTION 516
EXPANSION JOINTS AND BEARINGS

Sect 516 	Section 516 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp: 501, 720

SECTION 520
TEMPORARY CROSSINGS

Sect 520: Section Special: 	Section 520 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:

DIVISION 600 — MISCELLANEOUS
CONSTRUCTION

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 602
STRUCTURAL PLATE PIPE

Sect 602: CR601.2-010119

Related Sect/Sp:  204/CR204, 705/CR705.1, 707

Special Provisions

Replace Subsection 602-2.01 with the following:

602-2.01 MATERIALS.	Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Flexible Watertight Gaskets	Subsection 705-2.05

Corrugated Steel Pipe, Pipe Arches, and Underdrains	Subsection 707-2.01

Corrugated Aluminum Alloy Culvert Pipe and Underdrains	Subsection 707-2.03

Structural Plate Culverts	Subsection 707-2.04

Replace Subsection 602-3.01 with the following:

602-3.01 CONSTRUCTION REQUIREMENTS. Lay field-assembled plate pipes in conformance to the lines and grades approved by the Engineer. Excavation, grading, shaping, and backfill must conform to Subsection 204-3.01.

Repair damage to the zinc coating according to AASHTO M 36.

Comply with the manufacturer's recommendations and instructions. Provide the Engineer with a copy of the documentation.

Add the following Subsection 602-3.02 Joining Pipe:

602-3.02 JOINING PIPE. Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

CR602.1-010120

Temporary Waterway Diversion and Dewater Work Areas-Draft. This provision is available as an individual provision in the AllProvisions folder for addition to Section 205, 602, 603 and other sections as applicable to a specific project. Includes notes for use.

205-CR205.1-060117CrkDiversionDewaterWithNotes

Special Provision

Sect 603:  CR603-010119 (Replaces SSHC Section 603)

Related Sect/Sp:  203, 204/CR204, 205, 602/CR602.1, 605/CR605.1, 705/CR705.1, 706/CR706.1

Replace Section 603 with the following:

Use HDPE for culverts and storm drains as possible. See comments at the end of special for culvert and storm drain requirements and notes.

SECTION 603
CULVERTS AND STORM DRAINS

603-1.01 DESCRIPTION.  Construct or reconstruct culvert and storm drain pipe. Install culvert marker posts, and strap plastic culvert ends.

603-1.02 REFERENCES.

ASTM D3953	Standard Specification for Strapping, Flat Steel and Seals

ASTM D4675	Standard Guide for Selection and Use of Flat Strapping Materials

603-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Joint Mortar	Subsection 705-2.04

Flexible Watertight Gaskets	Subsection 705-2.05

Non-reinforced Concrete Pipe	Subsection 706-2.01

Reinforced Concrete Pipe	Subsection 706-2.02

Corrugated High Density Polyethylene (HDPE) Pipe	Subsection 706-2.07

Corrugated Steel Pipe and Pipe Arches	Subsection 707-2.01

Corrugated Aluminum Pipe	Subsection 707-2.03

Galvanize	Subsection 716-2.07

Culvert Marker Posts (Flexible Delineator Posts)	Subsection 730-2.05

Item 603(17-xx), Pipe, listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP), Corrugated Aluminum Pipe, Reinforced Concrete Pipe, or Corrugated Dual Wall HDPE (plastic) Pipe. Select pipe for each installation that meets or exceeds the requirements shown on the Plans for height of cover.

For steel and plastic pipe, match the end section material to the pipe material.

Separate dissimilar materials with an electrical insulating material.  The insulating material must be at least 1/16 inch thick and approved by the Engineer.

Culvert marker post is 6-foot tall by 2.5 inches wide with reinforcing ribs, capable of a 9-inch minimum bending radius, and blue with no marking.

Culvert marker Strap and Seals according to ASTM D3953. .625 inch x .02 inch, dry Type 1 regular-duty (magnetic, ferritic), galvanized Finish B (hot-dipped Grade 2 moderate coating, .18 oz./ft2 surface or .0002 inch thick minimum. Push type seals, Style III (overlap), regular duty, galvanized Finish B (hot-dipped coating) by 1.75-inch minimum length and matched to strapping width.

CONSTRUCTION REQUIREMENTS

603-3.01. GENERAL. Excavate, bed, and backfill according to the requirements of Subsections 204-2.01 and 204-3.01, and the Plans.

603-3.02. LAYING PIPE. Begin the pipe laying at the downstream end of the pipe. Keep the lower segment of the pipe in contact with the bedding throughout its full length. Place bell or groove ends of rigid pipe and outside circumferential laps of flexible pipe facing upstream.

Lay paved or partially lined pipe so that the longitudinal centerline of the paved segment coincides with the flow line. Install elliptical conduit and circular conduit reinforced with other than a full circular cage or cages so the orientation of a vertical plane through the longitudinal axis of the conduit does not vary more than 5 degrees from the design orientation.

Repair damaged metallic coating on metal pipe according to AASHTO M36.

603-3.03 JOINING PIPE.

Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

1.	Rigid Pipe. Use either bell and spigot or tongue and groove joints. Join pipe sections with the ends fully entered and the inner surfaces reasonably flush and even.

Use one or more of the following joint materials, or any other if approved:

a.	Portland cement mortar

b.	Portland cement grout

c.	Rubber gaskets

d.	Coupling bands

e.	Preformed plastic sealing compound

Make mortar joints using an excess of mortar to form a bead around the outside of the pipe.

For grouted joints, use molds or runners to retain the poured grout. Install rubber ring gaskets to form a flexible, watertight seal.

When using portland cement mixtures, protect the completed joints against rapid drying using suitable covering material.

2.	Metal Pipe.

Join the metal pipe firmly using connecting bands conforming to ASTM B745 (Corrugated Aluminum Pipe) and ASTM A760 (Corrugated Steel Pipe) and as noted herein. Use bands that are no more than two nominal sheet thicknesses lighter than the pipe jointed, and in no case more than 0.052 inches lighter. Include a gasket each side of the gap.

a.	Primary Band. Furnish and install corrugated bands so that the band corrugations match and conform to the corrugations of the pipe. Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than one corrugation width.

(2)	Band for 12-inch through 30-inch diameter pipe are at least 12 inches wide.

(3)	Bands for pipe with diameters greater than 30 inches are at least 22 inches wide.

b.	Secondary Band. Use this band only where it is not physically possible to use primary bands, such as on field-cut pipe ends, joining new pipe to existing pipe, etc. Furnish and install deformed metal sheet bands (dimple bands) so that the projections match and are the same depth as the pipe corrugations. Form these projections in circumferential rows with one projection for each corrugation of the helical pipe.

Conform to the following guidelines:

(1)	The gap between the pipes joined is in the center of the band and is no wider than 2 inches.

(2)	Bands for 12-inch diameter pipe are at least 12 inches wide and have one circumferential row of projections for each pipe end joined.

(3)	Bands for pipe with diameters greater than 12 inches are at least 24 inches wide and have two circumferential rows of projections for each pipe end joined.

3.	Plastic Pipe. Use push-on or mechanical joints. Ensure that the plastic pipe couplings' corrugation matches the pipe corrugation and that their width is not less than one-half the nominal pipe diameter.

Furnish all bolted connections on coupling bands with cut washers placed between the nut and the angle bracket or use nuts with integral washers.

Take up any pipe that is out of alignment, unduly settled, or damaged and re-lay or replace it.

603-3.04 CULVERT MARKER.

a.	Marker Post. Install a culvert marker on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed. Drive to maintain forty-two inches of post above the ground after driving, and

b.	Marker Strap. In addition to marker posts, install marker strap around the plastic pipe ends.

Position the strap in the valley of the first annular ring from the top end of the culvert. From the vertical centerline of the culvert, at the top, overlap the strap and extend the ends to approximately 30 degrees each side of the centerline. Place the strap loosely without twists in the valley, without compressing the pipe, and tight enough to keep the strap from moving out of the valley without deforming the pipe or pipe corrugation. Seal the strap at three locations, one at each of the ends, and one at the top of the culvert. Extend the strap ends beyond the end seals approximately 1/2-inch. Double crimp the seal, two pairs of crimps minimum each seal.

Repair the strap galvanizing where abraded and at cut ends according to ASTM A780. Prepare the surface with power tools per SSPC-SP11, hand tools per SSPC-SP2, and as required by the paint manufacturer. Apply paint, Type – paint containing zinc dust, to the prepared surfaces and allow enough time for curing as required by the manufacturer's printed instructions.

603-4.01 METHOD OF MEASUREMENT. Section 109, and as follows:

1.	Culvert Pipe. The length of pipe, measured in place, along the invert.

2.	Pipes for Storm Drains. The length of pipe, measured in place, along the invert, from center to center of structures. The length through the inlets, catch basins, and manholes is included in the measured length.

603-5.01 BASIS OF PAYMENT. Branch connections and elbows are subsidiary to the pipe unless included as a separate Pay Item.

Coupling bands, seals (gaskets), and other items necessary for the proper joining of the sections are subsidiary.

Culvert markers are subsidiary to the pipe.

Excavation, bedding, and backfill paid under Section 204.

Payment will be made under:

Pay Item No.	Pay Item	Pay Units

603(1)	CSP ___ Inch	Linear Foot

603(2)	___ Inch CSP Arch	Linear Foot

603(3)	End Section for CSP ___ Inch	Each

603(4)	End Section for ___ Inch CSP Arch	Each

603(9)	Corrugated Aluminum Pipe ___ Inch	Linear Foot

603(10)	___ Inch Corrugated Aluminum Pipe Arch	Linear Foot

603(11)	End Section for Corrugated Aluminum Pipe ___ Inch	Each

603(12)	End Section for ___ Inch Corrugated Aluminum Pipe Arch	Each

603(13)	Reinforced Concrete Pipe, ___ Inch, Class ___	Linear Foot

603(14)	Reinforced Concrete End Section, ___ Inch	Each

603(15)	Elbow, (Type & Size)	Each

603(16)	Branch Connection (Type & Size)	Each

603(17)	Pipe ___ Inch	Linear Foot

603(19)	___ Inch Pipe Arch	Linear Foot

603(20)	End Section for Pipe ___ Inch	Each

603(22)	Corrugated HDPE Pipe ___	Linear Foot

603(23)	End Section for Corrugated HDPE Pipe ___	Each

CR603-010120

Temporary Waterway Diversion and Dewater Work Areas-Draft. This provision is available as an individual provision in the AllProvisions folder for addition to Section 205, 602, 603 and other sections as applicable to a specific project. Includes notes for use.

205-CR205.1-060117CrkDiversionDewaterWithNotes

CULVERT AND STORM DRAINS

Pipe Material and Use:

Discuss the culvert and storm drain design, including the culvert material and the need for thaw pipes and wires (Section 616), with the CR Hydrologist and the Maintenance and Operations Department no later than the PIH design phase.

1.	Use HDPE material for culverts and storm drains (706-2.07), except as noted in 2, 3, and 4 below.

2.	Use galvanized steel culvert material (10 gage or lower):

a.	Culverts larger than the maximum size available for HDPE. HDPE is available up to 60 inches. (The cover requirement in D-04.21 Sheet 3 presently does not go beyond 48 inches.)

b.	Locations where the cover and/or live load is too high for HDPE. (D-04.21 sheets do not include the latest HS loading.)

c.	Culverts exposed to the combination of fresh water and floating ice.

d.	Culverts that must meet fish passage criteria.

3.	Use aluminum culvert material when in salt water with floating ice. Use a gage two below that permitted by D-04.21 Sheet 1.

4.	Project specific conditions may require thick walled HDPE. Evaluate conditions such as high abrasion, low pH, or high dead and or lived load on a cases-by-case basis. The minimum thickness required related to the standard dimension ratio (SDR – pipe diameter to wall thickness) of 32.5, included in 706-2.07.

Vertical and Horizontal Separation between Storm Drain Facilities and Water Lines

An Alaska Department of Environmental Conservation (ADEC) waiver may be required depending on the proximity of an Alaska Department of Transportation (ADOT) storm drain to a water line. This is a concern, primarily, in the Municipality of Anchorage (MOA) and the Matanuska Borough. If you believe a waiver may be required, provide DEC with plans and specifications for review. Under most project conditions, a DEC waiver will not be required.

Anchorage Water and Waste Utility

30.00 Design and Construction of Wastewater Facilities

30.02.06.04 Storm Drain Crossings

Where the sanitary sewer main crosses the storm drain, a vertical separation of three (3') feet is to be maintained. If this minimum cannot be maintained, then four (4") inches of insulation (high density extruded polystyrene board stock or equivalent as defined in MASS) is required between the lines. When the storm drain is within three (3') feet of a manhole, the ladder in the manhole must be rotated opposite the storm drain or insulation placed between the storm drain and sanitary sewer manhole to prevent icing on the manhole ladder.

The minimum horizontal separation between sanitary sewer mains and storm sewer mains is three (3') feet measured from the outside of the pipes when the pipes are at the same elevation. When the sanitary sewer mains and storm sewer mains are at different elevations, the horizontal separation distance must be such that neither pipe is located within the trench cross section of the other pipe. The cross section to use shall be OSHA compliant without the use of shoring or sheeting.

40.00 Design and Construction of Waterworks

40.02.09 Crossings

40.02.09.02 Storm Drains

Water lines crossing storm drains require a minimum vertical separation of three (3') feet. If this minimum cannot be attained, then four (4") inches of extruded or expanded polystyrene insulation is required between the lines. Eighteen (18") inches is the minimum insulated separation distance. If eighteen (18") inches cannot be obtained, the water line will have to be relocated. The more stringent of the ADEC or AWWU requirements will govern. Use the provided ADEC waiver flow chart in Section 20 to determine if an ADEC separation waiver is required.

Municipality of Anchorage

Municipality of Anchorage Standards and Specifications (MASS)

Standard Detail 20.9.	 Insulation = 4"

20.13 Trench Excavation and Backfill. Meet Specified R Value or better and conform to the requirements of AASHTO M230 Expanded and Extruded Foam Board (Polystyrene).

a.	Size (minimum)	2' x 8' x 4"

b.	Compressive Strength	415 kPa/60psi (MOA Reqd) M230 Table I, Type VII

b.	R Value	20 (typical R value for polystyrene insulation R = 5 per inch, 4" = R20)

For further discussion, refer to CR603 Separation between Storm Drain Facilities and Water Lines: hyd (\\dot\shared\avi) (S:) ►SPECIFICATIONS►USERS►AllProvisions►AllProvisions_2017.SSHC

SECTION 604
MANHOLES AND INLETS

Sect 604:  CR604.1

Related Sect/Sp:

In the Municipality of Anchorage.  Requires sanitary sewer and storm drain facility inspection, repair and replacement for manholes frames, manhole covers and lids; and catch basin inlets and grates.

Special Provisions

604-1.01 DESCRIPTION.  Add the following:

Sanitary Sewer and Storm Drain Facilities – Condition Inspections and Item Replacement

Sanitary Sewer Facilities:

Coordinate with the Engineer and AWWU; and participate in a pre-construction condition inspection, and a post-construction condition inspection of the sanitary sewer facilities.

Storm Drain Facilities:

Coordinate with the Engineer and participate in a pre-construction condition inspection of the storm drain facilities.

The pre-construction inspections may identify additional items, manhole metal frames, covers, lids, catch basin inlets and grates, to be repaired and or replaced.  Make repairs and or replace additional facility items as directed by the Engineer.

604-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

Sanitary Sewer and Storm Drain Facilities – Condition Inspections and Item Replacement

Contractor furnishes the required traffic control, including personnel to assist, while performing inspections.

The Contractor forfeits all right to assert pre-existing damage if the Contractor fails to participate in the inspections.

Make repairs and install the replacement facility items as shown in the Plans.

Sanitary Sewer Facilities:

During inspections the AWWU representative, the Engineer and the Contractor will observe each facility's location and condition.  The Engineer will indicate the additional facility items to be replaced.

Provide 3 days advance written notice to AWWU scheduling a pre-construction inspection of the facilities.  Conduct this inspection before pavement removal begins.  Contact the AWWU Project Manager to determine where to send the written notice, (907) 564-2717.

AWWU furnishes the sanitary sewer manhole frames and covers.  Contact the AWWU Project Manager to schedule the pick-up of the furnished materials.  Allow 3 working days from the time contact is made to pick-up of the materials.

Salvage the replaced manhole frames and covers.  Coordinate with, and deliver to AWWU the salvaged materials.

Provide written notice to AWWU scheduling a post-construction inspection of the facilities, after the paving operations are complete and 3 days in advance of the inspection.

Provide the Engineer a copy of the written notices.

Storm Drain Facilities:

Contact the Engineer, a minimum of 15 days in advance, to schedule a pre-construction inspection of the storm drain facilities.  Conduct this inspection before pavement removal begins.

During inspections the Engineer and Contractor will observe each facility's location and condition. The Engineer will indicate the additional facility items to be replaced.

Contractor furnishes the storm drain manhole frames and lids; and catch basin inlets and grates.

Dispose of storm drain materials and sanitary sewer materials not wanted by AWWU, according to the Municipality of Anchorage rules and regulations.

604-5.01 BASIS OF PAYMENT.  Add the following:

Pay Items 604(13B), Item 604(13D), and Item 604(13E) include full compensation for labor, equipment, and incidental materials for installation, complete-in-place after final paving as accepted by the Engineer, including but not limited to:

	inspections

	removal and disposal of existing manhole metal frame and cover/lid; and catch basin inlets and grates

	repairs and installing the replacement materials

	adjusting the facility item down prior to the planing operation

	adjusting the facility item up prior to the paving operation

Repairs to facilities damaged or rendered inoperable, after the pre-construction inspection and before the final inspection, are the responsibility of the Contractor and no additional payment will be made.

All traffic control required for the inspections will be paid under the 643 Pay Items.

Except as being paid under Pay Item 604(13B), (13D), and (13E), existing manholes being adjusted by raising or lowering the frame or ring casting 12" or less – comply with Subsection 604-3.01, paragraph beginning, "adjust existing manhole or inlet …" The corresponding Pay Item for this adjustment is 604(4) Adjust Existing Manhole.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

604(13B)	Replace Inlet Frame and Grate	Each

604(13D)	Remove and Replace Sewer Manhole Frame and Lid	Each

604(13E)	Remove and Replace Storm Drain Manhole Frame and Lid	Each

CR604.1-071519

SECTION 605
UNDERDRAINS

Special Provisions

Sect 605: CR605.1-010119R

Related Sect/Sp:  204/CR204, 705/CR705.1, 706/CR706.1

Replace Subsection 605-2.01 with the following:

605-2.01 MATERIALS. Use materials that conform to the following:

Porous Backfill Material	Subsection 703-2.10

Flexible Watertight Gaskets	Subsection 705-2.05

Perforated Concrete Pipe	Subsection 706-2.03

Corrugated High Density Polyethylene (HDPE) Pipe	Subsection 706-2.07

Corrugated Steel Pipe	Subsection 707-2.01

Corrugated Aluminum Pipe	Subsection 707-2.03

Gray Iron Casting	Subsection 719-2.02

Marker Post	Subsection 730-2.05

Replace Subsection 3.01 with the following:

605-3.01 PIPE INSTALLATION. Excavate, bed, and backfill according to the requirements of Subsection 204-2.01 and 204-3.01.

Class 1 perforations are for a combination storm and underdrain. If underdrain only, change the perforation Class to 2, and remove the sentence below, "Place the perforated pipe with the perforations down." Class 2 has the perforations all around, AASHTO M252/294. If the Class is not specified the supplier will provide Class 2 perforations. Consult with the ADOT hydrologist.

Provide perforated pipe with Class 1 perforations.

Place the perforated pipe on a compacted bedding layer. Place the pipe with the perforations down.

Joints shall provide circumferential and longitudinal strength to preserve the pipe alignment, prevent separation of pipe sections, and provide a watertight joint between new sections of pipe and joints between new and existing sections of pipe of similar and dissimilar materials. Include a continuous gasket (seal) in all joints. Construct the watertight joint capable of passing a laboratory hydrostatic pressure and vacuum test of at least 4 psi for 10 minutes.

Use push-on, screw-on, or corrugated couplings matching the pipe corrugation of bell and spigot or split collar type engaging at least two full corrugations on each pipe section. Use fittings supplied or recommended by the pipe manufacturer.

Join pipe end sections and plug or cap up-grade ends of subdrain pipe.

After the pipe installation inspection and approval, place and compact the porous backfill material to a minimum height of 12 inches above the top of pipe. Fill trench above the porous backfill with specified material.

605-5.01 BASIS OF PAYMENT.

Delete pay item 605(6) and (7).

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

605(8)	Perforated Corrugated HDPE Pipe ___	LF

CR605.1-010120

Special Provisions

Sect 606: CR606-020119. CR606.10 Crash Cushions are now in CR606. CR606.9, 13 are provisions to be included when applicable to the specific project, otherwise remove.

Related Sect/SP: 710/CR710.2.3.	Remove the code prior to the removed special, CR606-000000. SM4 content added as applicable.

Replace Section 606 with the following:

SECTION 606
GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, transition rail, and permanent crash cushions.

"Replace Section 606 with the following:" is the only instruction statement required with or without CR606.9 and or 13.

The permanent crash cushion, hereafter referred to as, "crash cushion," includes the complete assembly (crash cushion, foundation, backstop or transition) represented in the FHWA eligibility letter(s).

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, transition rail, and crash cushions.

CR606-020119R

Furnish and install bollard(s) included in the Plans and Specifications.

CR606.9-020119R

CR606.9 Use when installing Bollards.

Furnish and store new highway safety appurtenance essential replacement parts (replacement parts) listed in Table 606-1. Repair damage, from highway crashes, with the replacement parts.

CR606.13-050119

CR606.13. All projects with highway safety appurtenances. Essential replacement parts as part of the contract. FHWA memo "Eligibility of Replacement Parts for Safety-related Hardware" June 10, 2008.

606-1.02 SUBMITTALS.

1.	Submit the following at the preconstruction conference and receive approval before installation.

a.	Permanent Crash Cushions.

(1)	FHWA Eligibility Letter(s).  Eligibility letters demonstrating each crash cushion assembly is MASH 2016 compliant with the AASHTO 2016 Manual for Assessing Safety Hardware (MASH-16) Test Level 3.  Demonstrate the eligibility letter shielding widths cover the hazard widths and travel directions shown in the plans.

(2)	AASHTO Listing Category. AASHTO listing or documented updates for the crash cushion classification as listed in the 2011 AASHTO Roadside Design Guide, Section 8.4.

(3)	Manufacturers' Shop Drawings, Assembly, and Installation Instructions.  Submit shop drawings and detailed assembly and installation instructions for the crash cushion as included in the FHWA Eligibility Letters.

(4)	Manufacturer Certification Letter. Certify the crash cushion(s) meet the requirements of the FHWA eligibility letter(s), are suited to the Contract requirements including the environmental conditions at the installation site.

(5)	Manufacturers' Installer Certification Letter. Certify the installation contractor is familiar with and trained to install the crash cushion.

(6)	Manufacturers' Installation Checklist. Submit a crash cushion installation checklist.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit an Assembly Installation Checklist.

2.	Submit the following after installation.

a.	Permanent Crash Cushions.

(1)	Manufacturer Certification Letter. Certify the installed crash cushion(s) meet the requirements of the FHWA eligibility letters. Submit the certification letters(s) signed and dated no more than 14 days after installation.

(2)	Manufacturers' Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

b.	Parallel Terminals.

Manufacturer Installation Checklist. Submit the completed installation checklist signed by the Installer and Manufacturer no more than 14 days after installation. Complete the checklist after each assembly.

606-2.01 MATERIALS. Use materials that conform to the following:

Concrete, Class B	Section 550

Flexible Delineator Posts	Subsection 730-2.05

Guardrail Connection Plate	Section 722

Guardrail Hardware	Subsection 710-2.07

Guardrail Posts and Blockouts	Subsection 710-2.06

High Strength Bolts	Section 722

Metal Beam Rail	Subsection 710-2.04

Terminals	Subsection 710-2.11

Terminal Markers	Subsection 730-2.05

Wire Cable	Subsection 709-2.02

Guardrail Reflector Assembly Brackets, Side-Mounted. Aluminum alloy.

Retroreflective Sheeting.

1.	Post-Mounted Flexible Delineators and Guardrail Reflectors. ASTM D4956 Type IX or XI.

2.	Terminal Markers. ASTM D4956 Type VIII, IX or XI.

Permanent Crash Cushion Assembly.

Crash cushions include the complete assembly as included in the Eligibility Letter, the crash cushion, the foundation, and rigid backup anchorage, or transition connection. Install an added Terminal Marker or other flexible delineator to the front of the crash cushions as recommended by the Manufacturer.

Design the crash cushion for the installation location environment. Snow combined with frequent freeze-thaw cycles creates significant ice buildup that may impair the performance of the crash cushion.  Design to mitigate the effects from snow and ice. Crash cushions using supports that interlock and travel within fixed tracks at or below the first six inches from ground level, and crash cushions not designed to mitigate snow and Ice buildup are not acceptable for permanent use. Crash cushion covers, when available from the manufacturer, are required as part of the crash cushion installation.

Crash Cushion Classifications. 2011 AASHTO Roadside Design Guide, 4th Edition.  The Engineer will determine the final classification of each materials submittal.  Provide redirective and non-gating crash cushions of the type specified in the plans and matching the description noted below.

1.	Sacrificial:  Demonstrated designed for a single impact.

2.	Reusable Crash Cushion.  Demonstrated to have major components survive most impacts intact and salvageable.  Some components require replacement after a crash.

3.	Low-maintenance and Self-restoring Crash Cushion. Demonstrated to suffer very little, if any damage, upon impact and easily pulled back into their full operating condition.  They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.

CR606-020119R

Bollards.

CR606.9. Include each material reference whether there are only wood or only steel bollards.  Indicate the type of bollard in the plans.

CR606.9 Use when installing Bollards.

Concrete; Class B	Subsection 550-2.01

Shapes, Plates and Bars	ASTM A 36

Bollard Pipe	Subsection 716-2.06

Bollard Tube	ASTM A 500, Grade B

Welding	Subsection 716-2.02

Galvanizing	Subsection 716-2.07

Galvanizing Repair	ASTM A 780

Paint (Paint for Steel Structures/Paint of Timber)	Subsection 708-2.01/2.02

Bollard Post (WCLIB; Posts and Timbers, Douglas Fir-Larch No. 1)	Subsection 713-2.01

Preservatives and Pressure Treatment Process for Timber	Subsection 714-2.01

Backfill Material (Selected Material, Type A)	Subsection 703-2.07

Retroreflective Bands (6 inch wide reflector, smooth surface bands)	ASTM D4956, Type III-A

CR606.9-020119R

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform to the Alaska Standard Plans and these Specifications.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic encounters first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a crash cushion or truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run connects to existing barrier, buried in the backslope terminal, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may start at the point of connection.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the construction clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

When possible, proceed with construction of guardrails with the direction of traffic.

Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail. Use 25 linear feet of guardrail or two 12’ 6” pieces of guardrail to transition to match the existing or new guardrail elements and/or end treatments.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

Treat field cuts to timber posts and blockouts according to AWPA standard M 4.

Install blockouts according to manufacturer’s recommendations and as shown on the plans.

Install side-mounted guardrail reflectors and post-mounted flexible delineators as follows:

1.	at intervals noted on the plans or Alaska Standard Plans, starting with the first guardrail post beyond terminal sections

2.	with the retroreflective sheeting facing approaching traffic

3.	with retroreflective sheeting on both sides, on two-way roadways

4.	not on the terminal sections, except as shown on the plans

5.	at or below 500 feet in elevation, except as noted otherwise in the Plans.

Attach terminal markers, in a vertical position, to the P.T. post of Short Radius Guardrail sections and to the post where the flare begins for parallel guardrail terminals.  Coordinate terminal marker locations with the Engineer.

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

CR606-020119R

Do not remove existing highway safety appurtenances, guardrail and similar, before mobilization of the replacement parts to the project storage location.

CR606.13-050119

CR606.13. All projects with highway safety appurtenances. Essential replacement parts as part of the contract. FHWA memo "Eligibility of Replacement Parts for Safety-related Hardware" June 10, 2008.

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Set posts as follows:

1.	Set posts plumb, in the location and to the depth shown on the Plans or Alaska Standard Plans.

2.	Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

3.	Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

a.	The underlying material is no larger than six inch; and

b.	The posts are not damaged during installation.

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

5.	For placement in solid rock or broken rock embankment greater than six inch, set wood or steel posts in pre-dug, pre-drilled, or pre-punched holes.

6.	In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36 (ASTM A760).

Lap rail elements so that the exposed ends face away from approaching traffic in the adjacent lane.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

Locate bolts at expansion joints at the center of the slotted holes.

Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

606-3.04 CABLE RAIL. Install cable guardrail according to the Plans and Specifications. Install at the locations shown on the Plans.

606-3.05 TERMINAL SECTIONS.

Parallel Terminals.

Install terminal sections according to the manufacturer’s recommendations for the entire length of the terminal then, if required, transition rail height over 25’ to match guardrail height and splice location.

Install ASTM D4956 Type III, IV, or V retroreflective sheeting on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal according to guidance for Object Markers for Obstructions Adjacent to the Roadway in Chapter 2C of the ATM.

Submit the manufacturers' complete Assembly Installation Checklist signed and dated after completing installation to support acceptance for each installation, see Subsection 606-1.02 for further information.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Remove and reconstruct guardrail as specified. Replace lost or damaged materials without extra compensation.

When replacing existing guardrail complete the replacement run installed within 14 calendar days after removal.

For guardrail located within 50 feet of bridge ends, remove and replace the existing guardrail in the same work shift.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Remove the existing guardrail, including the rail, cable elements, terminal sections, hardware, posts, concrete bases, and steel tubes. Backfill resulting holes with material in 6-inch layers that is similar to the existing embankment and compact to the same approximate density.

Guardrail.

When salvaging guardrail insert the appropriate M & O station specific to the project in place of NA

Notify the Engineer a minimum of 5 days before removing guardrail.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of guardrail for salvage.  Deliver salvaged guardrail and associated hardware to the M & O station located at 			NA				.  Remaining items removed become the Contractor's property.

Permanent Crash Cushion.

When salvaging crash cushions insert the appropriate M & O station specific to the project in place of NA

Notify the Engineer a minimum of 5 days before removing permanent crash cushions.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of the crash cushion for salvage.  Deliver salvaged crash cushion and associated hardware to the M & O station located at 			NA	. Remaining items removed become the Contractor's property.

606-3.08 ADJUST EXISTING GUARDRAIL. When called for on the Plans, reset existing guardrail to the height shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail. Raise and lower the posts several times to prevent settlement and then re-drive them to the height shown on the Plans. Use other methods if approved.

606-3.09 INSTALL NEW GUARDRAIL. Install guardrail as shown on the applicable Alaska Standard Plan, measured from the top of the rail to the finished shoulder surface below the rail.

Install MASH-16 Test Level 3-compliant W31 guardrail as shown on the plans.  Install new guardrail in conformance with tolerances shown on the plans.

606-3.10 TERMINAL MARKERS. For each parallel rail terminal, attach a terminal marker to the extreme piece of rail.

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

Attach the flexible markers using hardware and attachment methods recommended by the manufacturer. The connection shall not negatively influence the performance of the guardrail as noted in 606-2.01.

606-3.11 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  When the Engineer determines additional guardrail is required, complete the installation immediately.

606-3.12 PERMANENT CRASH CUSHION.  Install crash cushions according to the manufacturer's instructions.

Construct crash cushions to shield the hazard width and travel direction shown in the plans.

Manufacturer's Crash Cushion Installation Certification. Submit the Manufacturer's Crash Cushion Installation Certification letter signed and dated after completing installation, see Subsection 606-1.02 for further information.

Manufacturer Certified Installers.  Install crash cushions using installers certified by the crash cushion manufacturer.  Install Crash cushions as follows:

1.	Parallel to the approach traveled way or as shown on the plans.

2.	Follow Section 203 for the excavation and embankment requirements of the concrete base component of the crash cushion.

3.	Follow Section 501 for a concrete pad, sized according to the manufacturer's recommendations, constructed on a minimum of 12 inches of Selected Material, Type B.

4.	Cut or fill to the top of the concrete pad with Selected Material, Type B at 12:1 or shallower on installations in grass median.

5.	Install top elevation of concrete pad flush to pavement edge when adjacent to or within asphalt pavement.

6.	Bolt crash cushion to median barrier with manufacturer approved barrier to crash cushion connector when attached to median barrier.

7.	Install a terminal marker or other flexible delineator on the nose of each crash cushion as recommended by the manufacturer.  The terminal marker is in addition to, not a substitute for, the retroreflective delineation installed on the crash cushion nose.

8.	Manufacturers' Crash Cushion Installation Checklist. Submit the installation checklist signed and dated after completing installation, see Subsection 606-1.02 for further information.

The crash cushion installation is not complete until the Crash Cushion Manufacturers' Installation Checklist and Installation Certification letter are submitted and the Engineer accepts the installation.

Excess excavated material is the property of the Contractor.

CR606-020119R

CR606.9 Use when installing Bollards.

606-3.13 BOLLARDS.

CR606.9 Include both steel and wood bollards; indicate the type of bollard in the plans.

1.	Steel Bollards.  Galvanize all steel members and hardware.

a.	Perform all welding according to AWS D1.1.

b.	Shop galvanize steel bollards and associated hardware, after fabrication.  Repair damage to galvanizing after installation.

2.	Wood Bollards.  Preservative treat all wood material.

a.	Treat field cuts, bolt holes, and similar according to AWPA Standard M4.

Install bollards in concrete, plumb, back fill with specified material, and compact to the satisfaction of the Engineer.  Provide the Engineer with lock keys.

Remove the keys if the removable bollard will not be locked or the Department is supplying the padlock.  Remove Paint and retroreflective bands if not part of the bollard installation…

Shop paint steel bollards with one coat of primer and two top coats of safety yellow. At the site repair nicks, scratches, and other damage.  In the shop and field, clean, prepare the surface and apply the materials as recommended by the manufacturer.

Apply two white retroreflective bands placed 3-4 inches from the top with a maximum of 6 inches between the bands.

CR606.9-020119R

606-3.14 HIGHWAY SAFETY APPURTENANCE – ESSENTIAL REPLACEMENT PARTS. Install replacement parts as directed.

CR606.13. Fill in the maintenance and operations station specific to the project.

Deliver the remaining new replacement parts, at time of substantial completion, to the State Maintenance and Operations Station, located at: 	.

Notify the Engineer no less than 7 days before delivery.

CR606.13-050119

CR606.13. All projects with highway safety appurtenances. Essential replacement parts as part of the contract. FHWA memo "Eligibility of Replacement Parts for Safety-related Hardware" June 10, 2008.

606-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

1.	Guardrail. Measured along the face of the rail or cable, from the center of the end posts.

Short Radius Guardrail. Per each, installed in place.

When the guardrail is connected to a terminal section, the pay limit for the rail ends where the specified terminal section begins.

2.	Terminals. (Bridge Rail Thrie Beam Transition or Bridge Rail W-Beam Transition). Per each, installed in place.

3.	Transition Rail. Per each accepted connection.

4.	Permanent Crash Cushion.  Each installed and accepted.

606-5.01 BASIS OF PAYMENT.

Payment for temporary crash cushions or TMA installed to protect motorists when guardrail installations are not completed within 10 calendar days of beginning installation is subsidiary to other items.

1.	Guardrail. Side-mounted guardrail reflectors, post-mounted flexible delineators, terminal markers, guardrail beam, posts, blockouts, and associated hardware are subsidiary.  Installation of downstream anchors, transitions for rail height and splice locations, long span guardrail sections, and guardrail stiffening sections are subsidiary to guardrail installation.

2.	Short Radius Guardrail Sections. The contract price includes all materials from the terminal anchor to and including the first wood or steel post of standard guardrail or guardrail end terminal, and including the terminal anchor assembly, in-line anchor, terminal posts, short radius guardrail posts, rail elements, terminal markers, and associated hardware required for a complete installation.

3.	Terminal Sections.

a.	Parallel Guardrail Terminal. The contract price includes rail elements, posts, blockouts, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

4.	Transition Rail. The contract price includes all brackets, beam sections, transition pieces, and all posts and associated hardware required for a complete connection of the guardrail section to a bridge rail or barrier.

5.	Permanent Crash Cushion.  The contract price includes all work and materials required to install each permanent crash cushion, foundations, and connections along with the manufacturer's field support, recommendations, and shop drawings.  Removal and salvage of existing crash cushions is subsidiary to Pay Item 606(18) Pay Item(s).

All material required for embankment widening for guardrail and terminal sections is paid for under the appropriate pay items shown in the bid schedule.

Guardrail salvage is subsidiary to Pay Item 606(6) Removing and Disposing of Guardrail.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

606(1)	W-Beam Guardrail	Linear Foot

606(2)	Thrie Beam Guardrail	Linear Foot

606(3)	Box Beam Guardrail	Linear Foot

606(4)	Cable Guardrail	Linear Foot

606(5)	Removing and Reconstructing Guardrail	Linear Foot

606(6)	Removing and Disposing of Guardrail	Linear Foot

606(8)	Double-faced, W-Beam Guardrail	Linear Foot

606(9)	Short Radius Guardrail	Each

606(13)	Parallel Guardrail Terminal	Each

606(15)	Adjust Existing Guardrail	Linear Foot

606(16)	Transition Rail	Each

606(18_)	Crash Cushion, Permanent 		Each

CR606-020119R

606(18)

Pay Item Number variations as noted below.

Pay Item.  Fill in the blank with the type name as in Crash Cushion, Permanent "Type Name"

Pay Item Type Names:		(18A)	Sacrificial

(18B)	Reusable

(18C)	Low Maintenance and Self-restoring

TABLE 606-1

HIGHWAY SAFETY APPURTENANCES – ESSENTIAL REPLACEMENT PARTS

Contact Burrell Nickeson for table items and quantities; Burrell.nickeson@alaska.gov, (907)-269-0757

| Essential Replacement Parts | Material Specification | Unit | Quantity |
| --- | --- | --- | --- |
| W-Beam Guardrail | Subsection 710-2.04 | Linear Foot |  |
| Thrie Beam Guardrail | Subsection 710-2.04 | Linear Foot |  |
| Cable Guardrail | Subsection 709-2.02 | Linear Foot |  |
| Box Beam Guardrail | Subsection 710-2.04 | Linear Foot |  |
| Wood Guardrail Post and Blockout | Subsection 710-2.06 | Each |  |
| Steel Guardrail Post and Blockout | Subsection 710-2.06 | Each |  |
| Short Radius Guardrail | Alaska Standard Plan G-26.00 | Each |  |
| Parallel Guardrail Terminal | Subsection 710-2.11 | Each |  |
| Transition Rail | Subsection 710-2.04 | Each |  |
| Crash Cushion, Permanent | Subsection 606-2.01 | Each |  |
| Precast Concrete Barrier | Subsection 501-3.01 & 709-2.01 | Linear Foot |  |
| Rigid Delineator | Subsection 730-2.05 | Each |  |
| Flexible Delineator | Subsection 730-2.05 | Each |  |

Replace damaged replacement parts at no additional cost to the Department.

6.	606(20) Essential Replacement Parts – Installation. Installation of the replacement parts according to the directive authorizing the work.

Pay Item No.	Pay Item	Pay Unit

606(19)	Essential Replacement Parts	Lump Sum

606(20)	Essential Replacement Parts – Installation	Contingent Sum

CR606.13-050119

CR606.13. Use this special all projects with highway safety appurtenances.

Make 606(20) estimated amount equal to 100% of 606(19).

Bollards are subsidiary to 					 including:

CR606.9. Use this special when installing bollards. If the bollard(s) are subsidiary to another Pay Item, reference the Pay Item below and include the subsidiary items listed below as applicable to the project, delete the others… Delete the Pay Items.  If not subsidiary, delete the  first paragraph, "Bollards are …".

7.	Bollard(s).  Payment for bollard Pay Items is full compensation for furnishing all labor, equipment, and materials required for a complete installation as shown in the Plans and included in the Specifications.  Consider the following part of a complete installation when in the Plans or included in the Specifications and are subsidiary to the Pay Item:

|  |  Concrete |  Marker(s) |  Removable bollard hardware |
| --- | --- | --- | --- |
|  |  Excavation & backfill |  Padlock(s) |  Retroreflective bands |
|  |  Galvanizing & repair |  Painting & repair |  Steel reinforcing |
|  |  Grading |  Preservative treatment & repair |  |
| Other items included in the Plans or Specifications associated with the bollards(s) |  |  |  |

Pay Item No.	Pay Item	Pay Unit

Select the applicable Pay Item(s), delete the others.

606(17)	Bollard	Each

606(17A)	Steel Bollard - Fixed	Each

606(17B)	Steel Bollard - Removable	Each

606(17C)	Wood Bollard - Fixed	Each

606(17D)	Wood Bollard - Removable	Each

CR606.9-020119R

SECTION 608

SIDEWALKS

CR6081.	Use CR608.1 where work includes either HMA pathways, medians or both.  Include only the item included in the project: "Construct HMA pathways;" "Construct HMA medians;" or "Construct HMA pathways and medians."

If there are no sidewalks or curb ramps replace the first sentence as in, "Replace the first sentence with the following" instead of "Add the following."

CR608.2.	Use CR608.2 for exposed aggregate concrete, colored concrete, painted HMA, pattern imprinted concrete and HMA.  CR608.2 and CR608.2 combined with CR608.1 are included in the ALLSPECIALS folder available to be added to the project specials. Painted and Painted/Imprinted is not recommended for use in CR.

Sect 608:  CR608.1.2

Related Sect/Sp:  401/CR401, 608/CR608.1.2, 703/CR703.1

Special Provisions

608-1.01 DESCRIPTION.  Add the following:

Construct asphalt (HMA) pathways and medians.

608-2.01 MATERIALS.  Delete paragraph number 2 and substitute the following:

2.	Asphalt (HMA)

Asphalt Binder, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

608-3.03 CURB RAMPS. Add the following: Measure curb ramp slopes with a 24-inch electronic level. Calibrate and operate the level according to the manufacturer's instructions.

Add the following Subsection 608-3.05:

608-3.05 ASPHALT PATHWAYS AND MEDIANS.  Construct pathways and medians according to Subsection 608-3.02, Asphalt Sidewalks.

608-4.01 METHOD OF MEASUREMENT.  Add the following:

Asphalt Pathways, and Medians are measured by the ton of HMA.

Additional HMA used for matching existing surfaces, such as paved parking lots behind a new sidewalk/pathway, will be included in the measurement of the related asphalt Pay Item.

608-5.01 BASIS OF PAYMENT.  Add the following:

Asphalt binder is subsidiary to related asphalt Pay Items.

Embankment and bed course materials will be furnished, placed, and paid under Sections 203 and 301, respectively.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

608(7)	Asphalt Pathway	Ton

608(8)	Asphalt Medians	Ton

CR608.1-040119

SECTION 609
CURBING

Sect 609:  CR609.1 (CR609.1 Rplcd CR48)

Related Sect/Sp:  703/CR703.1

Special Provisions

Add the following subsection:

609-3.06 BUMPER CURBS.  Concrete Parking Bumper shall conform to Subsection 609-3.03, Precast Concrete Curb, and the Plans.

609-4.01 METHOD OF MEASUREMENT.  Add the following:

Concrete Parking Bumper.  By each, complete installation.

609-5.01 BASIS OF PAYMENT.  Add the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

609(7)	Concrete Parking Bumper	Each

CR609.1-020100

Special Provisions

Sect 610:

Related Sect/Sp:  611

No mention is made of round stones to their exclusion.  Designer, if your project has significant slopes, that are 3:1 or flatter, you may allow round stones (place-rounded stones on slopes 3:1 or flatter). The use of round stones should be rare and should have the input from the PM, the hydrology and construction departments.

Replace Section 610 with the following:

SECTION 610
DITCH LINING

610-1.01 DESCRIPTION. Construct ditch lining at the locations on the Plans or as staked.

610-2.01. MATERIALS. Use crushed stones that are angular, hard, sound, and durable with at least one face resulting from fracture.

1.	Angular—stones, the particles of which possess well-defined edges formed at the intersection of roughly planar faces.

2.	Hardness—resistance of a material to indentation or scratching. AASHTO T96, not more than 50% wear at 500 revolutions.

3.	Soundness—measure of aggregates durability when exposed to the elements, AASHTO T104.

4.	Gradation—ATM 304:

a.	maximum of 6 inches in greatest dimension

b.	not more than 50% by weight passing a 3-inch sieve,

c.	not more than 5% passing a 1-inch sieve

5.	Breadth and Width—at least 1/3 of the length

610-3.01 CONSTRUCTION REQUIREMENTS. Place and spread ditch lining materials so that the finished face is uniform. 	Place stones on slopes 1.5:1 and flatter.

610-4.01 METHOD OF MEASUREMENT. Section 109.

610-5.01 BASIS OF PAYMENT. Excavation required below normal ditch grade is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

610(1)	Ditch Lining	Cubic Yard

610(2)	Ditch Lining	Ton

610(3)	Ditch Lining	Station

CR610-060117

SECTION 611
RIPRAP

Sect 611:  CR611.1 (CR611.1 Rplcd CR277)

Related Sect/Sp:

Special Provision

611-2.01 MATERIALS. Replace the first paragraph with the following:

Evenly graded stones that are hard, angular, and have no more than 50 percent wear at 500 revolutions as determined by AASHTO T 96.  Apparent specific gravity will be determined by ATM 308. Use stones with breadth and thickness at least 1/3 of its length. Do not use round boulders or cobbles on slopes steeper than 3:1.

CR611.1-020119

Special Provisions

Replace section 615 with the following:

SECTION 615
STANDARD SIGNS

Sect 615: Section Specials: CR615 Replaces SSHC 2017.

Related Sect/Sp:  730

615-1.01 DESCRIPTION. Furnish and install standard signs and delineators. Remove and relocate or remove and dispose of existing signs and markers, as specified.

615-2.01 MATERIALS. Use materials that conform to the following Subsections:

Sheet Aluminum 		730-2.01

High Density Overlaid Plywood		730-2.02

Retroreflective Sheeting, ASTM D4956 		730-2.03

Sign Posts		730-2.04

Delineator Posts		730-2.05

Acrylic Prismatic Reflectors		730-2.06

Sign Support Fasteners	730-2.07

1.	Shop Drawings. Submit shop drawings, for all signs that must meet the ASDS letter width and spacing charts, for approval before fabrication. Submit 4 sets of collated shop drawings prepared according to Subsection 105-1.02. Show the following on each sign drawing:

a.	Dimensions of all horizontal and vertical characters and spaces

b.	Overall dimensions

c.	Sign material and sheeting material type

d.	Panel thickness

e.	Legend and letter series

f.	Whether the sign will be framed

2.	Sign Fabrication. Use ASTM D4956 Type IV retroreflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX or XI fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting place on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white ASTM D4956 Type VIII or Type IX or XI retroreflective sheeting for background of sign and all strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use ASTM D4956 Type IX or XI retroreflective sheeting for legends and background. Create the legend in one of the following ways:

(1)	Cut border and legend from white ASTM D4956 Type IX or XI retroreflective sheeting and adhere them to a green ASTM D4956 Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white ASTM D4956 Type IX or XI retroreflective background.

d.	Fluorescent Yellow-Green School Area Signs: Use ASTM D4956 Type VIII, Type IX or XI retroreflective sheeting for background.

Use a manufacturer-recommended clear coat on all screened signs.

Use sign layouts (including characters, symbols, corner radii, and borders) that conform to the ASDS.

3.	Sign Posts and Bases. Use sign posts and bases of the types specified. The structural aspects of design and materials for sign supports must comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals. Do not splice sign posts.

Use Class A concrete meeting the requirements of Section 501 for overhead sign support foundations.

Use Class B concrete for steel-reinforced roadside sign foundations  meeting the requirements of Section 550. Concrete for other sign foundations may be Class W.

4.	Delineators. Use delineator assemblies that conform to the requirements shown on the Plans. Fabricate flexible delineators using ASTM 4956 Type III, IV, V, IX or XI Retroreflective Sheeting.

5.	Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured in accordance with ASTM E2301) for ten years according to the following criteria:

a.	Minimum Fluorescent Luminance Factor	YF: 20%

b.	Minimum Total Luminance Factor	YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication of the sign, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness. If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CONSTRUCTION REQUIREMENTS.

615-3.01 GENERAL.

1.	Place posts in excavated holes to the depth shown on the Alaska Standard Plans.

2.	Backfill the space around the posts and foundations placed in holes to finish ground with selected earth or sand, free of rocks or deleterious material. Place backfill in layers approximately 6 to 12 inches thick and thoroughly compact it.

3.	Dispose of surplus excavated material neatly along the adjacent roadway as directed.4.	Install flexible delineator posts according to the manufacturer's recommendations.

5.	Attach sign panels to posts, electroliers, traffic signal standards, bridge rails, piers, and abutments using the types and sizes of fastening hardware shown on the Plans.

6.	If using existing signs and mileposts that are removed and relocated, ensure they conform to the details shown on the Plans or as directed.

7.	Sign Salvage:

7. Verify the local Maintenance and Operations Station want salvaged signs from the project. Anchorage Station may not want the signs.

Notify the Engineer 5 working days prior to beginning sign salvage activities. The Engineer will physically identify those signs to salvage.

a.	Property of the State.  When 615-3.01 7a identifies a maintenance station to receive sign salvage, the signs (sign panels, posts, and hardware) are the property of the State.

Protect all items from damage during salvaging and delivery. For each sign so designated, disconnect sign post from panel and group the panels together. Group posts together with their hardware. Deliver sign panels, posts, and hardware to the State Maintenance Station noted in these Special Provisions. Do not deliver salvaged materials until inspected and approved by the Engineer. Replace any items damaged by you at no additional cost to the Department.

Deliver salvaged sign panels, posts, and hardware to the State Maintenance and Operations Station, located at:

7.	Place the Maintenance and Operations Station below, replacing "NA," when the station wants the salvaged signs,

NA	.

b.	Property of the Contractor. When 615-3.01 7a does not identify a State Maintenance and Operations Station; the signs salvaged (sign panels, posts, and hardware) are the property of the Contractor.

Remove project signs and/or parts designated for salvage, off the project site.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise). If abandoned in place, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to a depth of not less than 12 inches below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation considered as one unit.

Dispose of sign salvage not wanted by the Contractor, not used in the project, and not accepted by the Local Maintenance and Operations Station as required by Federal, State, and Municipal environmental regulations.

8.	All materials and finished signs are subject to inspection and acceptance in place.

a.	Surfaces exposed to weathering must be free of defects in the coating that impair serviceability or detract from general appearance or color match.

b.	Finished signs must be clean and have no chatter marks, burrs, sharp edges, loose rivets, delaminated reflective sheeting, or aluminum marks. Do not make repairs to the face sheet.

9.	Install the various breakaway assemblies according to the manufacturer’s written instructions. Meet MASH crashworthiness requirement for breakaway hardware, unless approved otherwise by the Engineer.

10.	Secure the anchors in templates and install them according to the manufacturer’s written instructions.

11.	Finish the foundation according to these tolerances:

a.	Do not use more than two shims per coupling.

b.	Do not use more than three shims to plumb each post.

Remove and replace all foundations requiring more than three shims to plumb a post without extra compensation.

12.	Construct the top of any foundation located on a slope so that the finished slope passes through the top center of the foundation. Grade the area 24 inches up and down slope of the foundation edge so that no portion of the foundation projects above the surrounding slope and water will drain away from the foundation.

13.	Attach a label to the back of all standard signs in the lower right corner. Make the label at least 15 square inches and show the year the sign was purchased from the manufacturer. Show the last two digits of the year in clear and bold numbers. Make the label from ASTM D4956 Type I or brighter retroreflective sheeting. Use background and legend colors meeting Table 615-1.

TABLE 615-1

DECAL COLORS

| YEAR | BACKGROUND COLOR | LEGEND COLOR |
| --- | --- | --- |
| XXX1 | Yellow | Black |
| XXX2 | Red | White |
| XXX3 | Blue | White |
| XXX4 | Green | White |
| XXX5 | Brown | White |
| XXX6 | Orange | Black |
| XXX7 | Black | White |
| XXX8 | White | Black |
| XXX9 | Purple | White |
| XXX0 | Strong Yellow-Green | Black |
| Central values and tolerance limits for each color, as referenced in the MUTCD, are available from the Federal Highway Administration, (HHS-30), 400 7th St. SW, Washington, D.C. 20590 |  |  |

615-3.02 SIGN PLACEMENT AND INSTALLATION. The location and type of installation will be as shown on the Plans. Sign locations are approximate and subject to field adjustment by the Engineer.

Do not allow the top of the embedded steel tube to extend more than 2 inches above the surrounding ground and concrete foundation.

On all signs, install 2-inch diameter wind washers, colored to match the sign face, between the fastener head and the sign. Use rust-resistant washers fabricated from a material equal in strength to the sign blank.

Mount signs on mast arms level.

Bring existing signs that are to remain, into conformance with Standard Drawing S-05. Keep existing signs in service until they are no longer needed.

615-4.01 METHOD OF MEASUREMENT.

Standard Signs and Object Markers. By the total area of legend-bearing sign panel erected in place. No deductions in quantity for corner rounding will be made. Nominal dimensions for sign sizes indicated on the Plans will be used to calculate sign pay quantities. Octagons and round signs will be measured as rectangles. Only one side of each double-faced sign will be measured for payment.

Removal and Relocation. By each, complete in place.

Delineators. By each, complete in place.  A single delineator consists of one post equipped with three reflectors.

Salvage Sign. By each complete sign delivered in acceptable condition.

615-5.01 BASIS OF PAYMENT. Sign posts, bases, and mounting hardware are subsidiary.

When Items 615(2), 615(3), or 615(6) do not appear on the bid schedule, this work is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

615(1)	Standard Sign	Square Foot

615(2)	Remove and Relocate Existing Sign	Each

615(3)	Remove and Relocate Milepost	Each

615(4)	Delineator, Rigid	Each

615(5)	Delineator, Flexible	Each

615(6)	Salvage Sign	Each

615(7)	Salvage and Dispose Sign	Each

CR615-010120

SECTION 617
RAILROAD CROSSINGS

Sect 617: Section Specials:

Related Sect/Sp:

Special Provisions

Delete Subsection 617-2.01 Materials and replace with the following:

617-2.01 MATERIALS. Use materials that conform to the kind, grade, type, and size specified on the Plans or as listed below:

Anchor Bolts	ASTM A307, Galvanize per AASHTO M 232, Class A

Rigid Metal Conduit, Couplings, Fittings	UL Standard UL-6, NEMA Standard C 80.1,

hot-dip galvanized

Concrete	Section 501 (Class A)

Railroad Crossing Pads	Rubber or high density polyethylene as manufactured by:

Railroad Friction Products Corp., Wilmerding, Pennsylvania 15148;

Omni Rubber Products, Inc., P.O. Box 2788, Portland, Oregon 97208;

or an approved equal.

Repair damage to galvanized coatings according to AASHTO M 36.

CR617.1-010116

Special Provisions

Replace Section 618 with the following:

SECTION 618
SEEDING

Sect 618: CR618

Related Sect/Sp:  619/CR619, 623/CR623, 641/CR641, 724/CR724.1, 726/CR726.1, 727/CR727

618-1.01 DESCRIPTION. Establish a healthy living perennial stand of grass or other vegetative living groundcover by seeding. Maintain the living cover for the term of the Contract.

618-2.01 MATERIALS. Use materials that conform to the following:

Water	Subsection 712-2.01

Seed	Section 724 (Grass Seed)

Fertilizer	Section 725

Topsoil	Section 726

Soil Stabilization	Section 619

Soil Stabilization Material	Section 727

See the blue boxes at the end of the provision for further seed mix information and options.

TABLE 618-1

GRASS SEED MIX, SOIL STABILIZER, AND FERTILIZER APPLICATION RATES

| Materials | Ingredients | Application Rate (per MSFc) |
| --- | --- | --- |
| Grass Seed Mix a, b | Nortan – Tufted Hairgrass Arctred – Red Fescue Wainwright - Slender Wheatgrass Annual Ryegrass | 0.60 lbs. 0.45 lbs. 0.37 lbs. 0.08 lbs. Total = 1.50 lbs. |
| Soil Stabilizer. |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12 lbs. |

a.	Do not remove the tags from seed bags.

b.	Submit an alternate seed mix when the specified seed is not commercially available. Provide a letter confirming the specified seed is not available. Include an agronomist certified seed mix design, including application rate, suited to the project site.

c.	MSF = 1000 ft2.

CONSTRUCTION REQUIREMENTS

618-3.01 SURFACE PREPARATION. Remove ruts, holes, humps and other irregularities from the surface. Clear stones four inches in diameter and larger, weeds, plant growth, sticks, stumps, and other debris that will interfere with the application of stabilization material, topsoil, the seeding operation, growth of vegetative groundcover, and subsequent maintenance of the cover.

Smooth the slopes for a uniform appearance and round the top and bottom of the slopes to facilitate tracking or raking. Do not disrupt drainage flow lines.

Evenly place stabilization material and or topsoil when specified.

Prepare the surface material by grooving the material in a uniform pattern that is perpendicular to the fall of the slope. Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rake;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board. Form one-inch wide grooves spaced no more than six inches apart.

618-3.02 SEEDING SEASON. Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.5 Soil Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Do not seed during windy conditions, when climatic conditions or ground conditions would hinder placement or proper growth.

Seed between May 15 and August 15.

618-3.03 APPLICATION. Seed, seeding, reseeding includes the application of seed, fertilizer, and stabilization material.

If the seed mix, fertilizer and stabilization material are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Do not seed areas of bedrock and plant beds.

Use any of the following methods:

1.	Hydraulic Method

Apply seed and stabilization material in one application when using the hydraulic method.  Apply fertilizer with the hydraulic method.  Include the fertilizer with the seed and stabilization material or apply separately.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other materials.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

2.	Dry Methods

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment.

b.	Spread fertilizer separately at the specified rate.

618-3.04 MAINTENANCE.  Maintenance includes but is not limited to the following:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the stabilization material and or topsoil for seeding.  Seed repaired area.  Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for healthy growth of vegetative cover.  Adjust the amount of water when directed.

618-3.05 ACCEPTANCE. The vegetative groundcover will be inspected considering each station and each side of the road a separate area.  Acceptance of the cover requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

618-3.06 PERIOD OF ESTABLISHMENT. For each area accepted, the establishment period extends one complete growing season following the date of Project Completion, Subsection 105-1.15.  Employ all possible means to preserve/maintain the new vegetative groundcover in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative cover, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Seeding by the Acre. By the area of ground surface acceptably seeded and maintained.

Seeding by the Pound.  By the weight of dry seed acceptably seeded and maintained.

Water for Seeding. If weighed, a conversion factor of 8.34 pounds per gallon will be used to convert weights to gallons.

M Gal equals 1000 gallons.

618-5.01 BASIS OF PAYMENT.

1.	Pay Items 618(1) and (2) Seeding. Payment is for healthy established vegetative groundcover through the establishment period.

a.	The initial surface preparation, seed, fertilizer, mulch when applied hydraulically, their application, and the water for hydraulic application are subsidiary.

b.	Maintenance fill, stabilization material, topsoil, surface preparation, seed, fertilizer, mulch when applied hydraulically, and the water required for hydraulic application are subsidiary.

2.	Pay Item 618(3) Water for Seeding. Payment is for water applied for growth of vegetative groundcover through the establishment period. Water for hydraulic application of materials is subsidiary to Pay Items 618(1) and (2).

Except for maintenance, stabilization material is paid under Section 619 and topsoil under Section 620.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

618(1)	Seeding	Acre

618(2)	Seeding	Pound

618(3)	Water for Seeding	M Gal.

CR618-050118R

Typically, mulch will be subsidiary as noted herein. The use of Pay Item, 619(1) Mulch, is very rare.  If mulch is included as a Pay Item, Section 618 will require editing to remove all references for applying mulch as part of the slurry, the initial and maintenance, and as subsidiary.  The application rate of mulch is included in Section 618 and not in Section 619 - this will have to be addressed in the project specials if mulch is paid as 619(1) Mulch.

Include: Section 619/CR619 Soil Stabilization; Section 724/CR724.1 Seed; 726/CR726.1 Topsoil and 727/CR727 Soil Stabilization Materials when including CR618.

Section 618 is not the place to specify soil stabilization material or topsoil.  Include topsoil, and soil stabilization material, general or specific, in the Estimate of Quantities, the Plans and the Bid Schedule.  Example:  "Soil Stabilization Material" in the Plans would be paid by Section 641; "Compost" or "Topsoil" in the Plans would be paid by Section 619, 620 or might be subsidiary to 618, etc.

Typical Seed Mixes

All mixes applied at 1.5 lb/MSF

Standard:

Seed mix as included in the provision.

Nortan – Tufted Hairgrass	40%	0.60 lbs.

Arctred – Red Fescue	30%	.45 lbs.

Wainwright – Slender Wheatgrass	25%	.38 lbs.

Annual Rye Grass	5%	.07 lbs.

Total = 100%	1.50 lbs.

Alpine: (possibly Turnagain Pass or similar)

Nortan – Tufted Hairgrass	40%	0.60 lbs.

Arctred – Red Fescue	30%	0.45 lbs.

Gruening – Alpine Bluegrass or Glaucous – Tundra Bluegrass	25%	0.38 lbs.

Annual Rye Grass	5%	0.07 lbs.

Total = 100%	1.50 lbs.

Wetland:

Egan Sloughgrass (American)	40%	0.60 lbs.

Norcoast – Tufted Hairgrass	30%	0.45 lbs.

Nortan – Tufted Hairgrass	20%	0.30 lbs.

Sourdough – Bluejoint Reedgrass	5%	0.08 lbs.

Annual Rye Grass	5%	0.07 lbs.

Total = 100%	1.50 lbs.

Recommend contacting the Alaska Plant Material Center to confirm each mix each project. Avoid seed mixes that are wildlife attractants (Bluegrass is an example of a wildlife attractant, Bluegrass is also not native to Alaska). Projects that need to reseed very small disturbed areas might use the Standard mix. At a minimum the Alpine and Wetland mixes might be used based on the designer's experience.

These seed mixtures are NOT meant to be used as a blanket recommendation for all projects.

Contact:

Alaska Plant Materials Center

5310 S. Bodenburg Spur

Palmer, Alaska 99645

Ph:	907 745 8108

Casey Dinkel			casey.dinkel@alaska.gov

Phil Czapla			phil.czapla@alaska.gov

Weed Free:  Do not add a project specific provision to include the requirement for "certified weed free seed mixture."  The SSHC requires the Contractor to meet the AK Seed Regulations. The regulations require the seed to be certified and certification requires the mixture to be free of noxious weeds.  Weed free is not a State or Federal regulation and there is likely no certification for such.  Stoney Wright at the Agriculture extension confirms this.  Contractors will not able to meet a weed free requirement.

Include Section 618 Seeding Special, CR618, when including CR724.1

SECTION 619

SOIL STABILIZATION

Special CR619 is a replacement special for the SSHC Section 619.

The special includes much of the SSHC section and adds additional subsections associated with stabilization materials and erosion control.

CR619 is intended to be general, generic, and not specific to a manufacturer's product.  With the number of stabilization materials available and more becoming available each day, writing a spec with the specifics of each type of product, let alone each manufacturer's products, becomes prohibitive.  CR727 and CR619 are written intending for the Contractor to provide the functional longevity and performance required to satisfy the CGP, the SWPPP and Section 641.

Many of the past specials written for stabilization materials have been specific to a manufacturer or a type of erosion control making it difficult for the Contractor to supply other products that may serve the functional longevity and performance as well or possibly better than that specified.  Typically, the Contract documents are not permitted to single out a specific manufacturer's product for use.  If you do not want a specific type of product, say so.  Be careful you have not eliminated viable options or actually restricted the Contractors ability to perform.

Special Provision CR690 is included in CR619 and has been removed from the typical regional specials.

CR727 is coordinated with CR619.  If you include CR619 you will also include CR727.

The materials listed are some of those available, hopefully the more common, if you are designing the stabilization for the project, temporary or permanent and there are materials required or specifics required, edit as needed, and identify the edits by adding the AKSAS-mmddyy at the end of the additions, modifications, etc.

Sect 619: CR619.  	Remove this page and the headers will realign similar to other sections.

Related Sect/Sp:  618/CR618.1.2.3; 618/724, 619/727, 620/726, 633/729, 641

Special Provision

Replace Section 619 with the following:

SECTION 619
SOIL STABILIZATION

619-1.01 DESCRIPTION.  Furnish, install, and maintain materials to stabilize the soil.  Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Alaska Department of Transportation and Public Facilities (ADOT&PF):

Standard Specifications for Highway Construction, 2017 Edition.

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	American Association of State Highway and Transportation Officials (AASHTO):

Standard Practice for:

	Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R 51

	Compost for Erosion/Sediment Control (Compost Blankets)	R 52

3.	United States Composting Council (USCC):

	Testing Methods for the Examination of Compost and Composting (TMECC)

	Seal of Testing Assurance Program (STA) documents

4.	Erosion Control Technology Council (ECTC)

	Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

	Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

5.	National Transportation Product Evaluation Program (NTPEP)

	Testing and Evaluation of Products Materials and/or Devices

6.	Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS.  Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.  Submit a sample of each material to the Engineer 7 days before the scheduled installation.

1)	Test compost, all applications, no more than 90 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS.  Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Stormwater Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch	Subsection 727-2.01

	Dry Erosion Control, Stabilization Products

	Hydraulic Erosion Control Products (HECPs)

2)	Matting	Subsection 727-2.02

	Rolled Erosion Control Products (RECPs)

3)	Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

	Filter Socks

	Compost Socks

	Coir Logs

4)	Compost	Subsection 727-2.04

5)	Tackifier	Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

7)	Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

8)	Sandbag	Subsection 727-2.08

9)	Manufactured Inlet Protection System	Subsection 727-2.09

10)	Clear Plastic Covering	Subsection 727-2.10

11)	Staples	Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL.  Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

1.	Material Storage and Protection.  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

	Precipitation

	Extended ultraviolet radiant including sunlight

	Chemicals that are strong acids or other

	Flames and welding sparks

	Excess temperatures

	Other environmental conditions that may damage the materials

2.	Fabrication.

a.	Sandbags.  Sand bags shall measure 15 inches by 30 inches.  Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack.  Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION.  Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material.  Section 618 and 620.

619-3.03 APPLICATION.  Apply stabilization material, including rate of application, according to the specifications.  If not specified, apply according to the manufacturer's requirements.  Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding.  Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers.  Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders.  Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets.  Construct compost blankets according to latest AASHTO R 52 and as specified.  Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified.  Apply material either by hand spreading and or pneumatically.  Compost will have no free water visible or produce dust when handled.  Place compost before seeding or mix seed with compost.

6.	Check Dams.  Place check dams as soon as possible and practicable or when and where if directed by the Engineer.  Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel.  Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag.  Place the initial row in tight contact with the ditchline for the length of the dam.  Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP.  All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag.  Place the initial row in tight contact with the surface perpendicular to the slope.  Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to latest AASHTO R 51.  Use coarse compost.

9.	Turf Reinforcement Mats.  According to manufacturer's installation instructions.

619-3.04 MAINTENANCE.  Maintain stabilized areas in a satisfactory condition for the term of the Contract.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately.  Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations.  Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

a.	Protecting stabilized areas against traffic by approved warning signs or barricades.

b.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

c.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

d.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP.  Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.  Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

619(1)	Mulching	Square Yard

619(2)	Matting	Square Yard

619(3)	Compost	Square Yard

619(4)	Turf Reinforcement Mat	Square Yard

619(5)	Sediment Retention Fiber Rolls (SRFRs)	Linear Foot

619(6)	Check Dam and Sediment Barrier - Geotextile	Linear Foot

619(8)	Compost Berm	Linear Foot

619(9)	Sandbags	Each

619(10)	Manufactured Inlet Protection System	Each

619(11)	Sandbag Inlet Protection System	Each

CR619-050118.SSHC2017

Above are included the primary Pay Items for this Section.  Supplement the primary Pay Items with the Pay Items listed here when more specific Pay Items are needed.

619(1AA)	Mulch - Straw	Square Yard

619(1AB)	Mulch - Shredded Bark Mulch	Square Yard

619(1AC…)	Mulch - 		Square Yard

619(1BA)	Mulch - Hydraulic Erosion Control Products	Square Yard

619(1BB)	Mulch - HECP Wood Strand, Fiber	Square Yard

619(1BC)	Mulch - HECP Dried Peat Moss	Square Yard

619(1BD)	Mulch - HECP SMM	Square Yard

619(1BE)	Mulch - HECP BFM	Square Yard

619(1BF)	Mulch - HECP MBFM	Square Yard

619(1BG)	Mulch - HECP PSFM	Square Yard

619(1BH)	Mulch - HECP FRM-FGM	Square Yard

619(1BI)	Mulch - HECP FRM-ET-FGM	Square Yard

619(1BJ…)	Mulch - HECP 		Square Yard

619(2AA)	Matting - RECP Control Nets	Square Yard

619(2AB)	Matting - RECP Netless Rolled ECB	Square Yard

619(2AC)	Matting - RECP Single-Net ECB	Square Yard

619(2AD)	Matting - RECP Single-Net OWT	Square Yard

619(2AE)	Matting - RECP Double-Net ECB	Square Yard

619(2AF…)	Matting - RECP 		Square Yard

619(4AA…)	Turf Reinforcement Mat 		Square Yard

619(5AA)	Fiber Rolls - SRFR Filter Sock	Linear Foot

619(5AB)	Fiber Rolls - SRFR Compost Sock	Linear Foot

619(5AC)	Fiber Rolls - SRFR Coir Log	Linear Foot

619(5AD)	Fiber Rolls - SRFR 		Linear Foot

619(6AA…)	Check Dam - 		Linear Foot

619(6BA…)	Sediment Barrier - 		Linear Foot

SECTION 621
PLANTING TREES AND SHRUBS

Sect 621: CR621.1

Related Sect/Sp:  CR618/618, CR619/CR619, 620, CR690/690, CR726.1/726, CR727/CR727

Special Provisions

Replace Subsection 621-1.01 with the following:

621-1.01 DESCRIPTION. Furnish and plant seedlings, shrubs, and willow bundles.  Maintain the plants for the term of the Contract.

621-2.01 PLANT STOCK.  Add the following:

Tree and shrub seedlings are 18 to 24 inches in height above the ground at time of planting.

Replace Subsection 621-2.02 with the following:

621-2.02 FERTILIZER. Use a regular release, 8-32-16 (N-P-K) fertilizer in granular form with seedlings, shrubs, and Willow bundles.  Mix the fertilizer with the soil at the manufacturer’s recommended application rate.

Replace Subsection 621-2.04 with the following:

621-2.04 MULCH. Use mulch that meets Section 727-2.01 MULCH, Dry Erosion Control, Stabilization Products, 2. Shredded Bark Mulch. Commercially available shredded wood fiber landscape mulch is acceptable, provided added color is natural dark brown.

Replace Subsection 621-2.05 with the following:

621-2.05 BACKFILL MIX. Use topsoil for backfill in planting beds of a natural friable surface soil without admixtures of undesirable refuse, foreign materials, roots, hard clay, noxious weeds, tall grasses, brush, sticks, stubble, litter, toxins and be free draining.  Local red loam or imported peat mix with nutritional and gradation data may be used to supplement topsoil.  Use topsoil backfill with 10-15 percent organic matter as determined by loss-on-ignition of oven-dried samples according to ATM 203, and meeting the following:

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 3/4 Inch | 100 |
| No. 4 | 95 – 100 |
| No. 16 | 30 – 55 |
| No. 200 | 25 - 55 |

Add the following Subsection 621-2.08:

621-2.08 EDGING. Use pure polyethylene plastic edging with 3 1/2 to 4 percent carbon black concentrate added for ultraviolet stabilization, a medium density and with a melt factor under 2.  Provide an average wall thickness between 95/1000 to 105/1000 inch, a height of 4 inches, with a 1-inch round top and 4-groove base.  Install per manufacturer's specifications, straight, level and secure.

621-3.03 PLANTING. Replace Item 1. with the following:

1.	Plant Season.

a.	Locally Grown.  Plant between June 1 and September 15.

b.	Imported.  Handle plants according to the nursery recommendations.  Plant between June 1 and August 15.

c.	Willow Bundles.  Plant Willow bundles between May 1 and June 15.

Replace 2.c. with the following:

c.	Construct planting pits for seedlings and shrubs, and trenches for Willow bundles.

Add the following to Item 6.

Backfill seedlings, shrubs, and willow bundles with a topsoil and fertilizer mix.

Replace Subsection 621-3.04 with the following:

621-3.04 PERIOD OF ESTABLISHMENT. The establishment period extends one complete growing season (May 1 to September 30) after the planting year, acceptance, and final inspection beginning from the date of Project completion, Subsection 105-1.15. The growing season is from May 1 to September 30. The growing season may include the time remaining after September 30, from the first 45 days of deep watering in the planting year resuming after May 1 of the following year, Subsection 621-3.07.

Employ all possible means to preserve/maintain the plants in a healthy and vigorous condition to ensure successful establishment. Maintain the plants according Subsection 621-3.07. In addition, apply fertilizer to seedlings and shrubs by driving a 1 1/2 ounce fertilizer spike, of the same material and proportions initially applied to the soil, into the ground at the drip line of each plant between May 15 and May 31; and again for the shrubs between June 15 and June 30.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of Project Completion.

Replace Subsection 621-3.06 with the following:

621-3.06 PLANT REPLACEMENTS.

Engineer and Contractor, in the growing season after the planting year and before June 30, inventory seedlings and shrubs planted to determine the number of dead and unhealthy plants.

For each species of seedling and shrub, replace the dead and unhealthy plants to maintain at least 75% of the number originally planted, in a healthy and vigorous condition. The Engineer will select the dead and unhealthy plants to replace. Remove the dead and unhealthy plants selected.

Provide healthy replacement plants of the same species and size as the original plantings. Complete replacement planting between July 1 and July 15.

Maintain the plants in an upright position and at the proper grade.

Replace Subsection 621-3.07 with the following:

621-3.07 MAINTENANCE. Maintenance includes but is not limited to the following:

1.	Protecting planted areas against traffic by approved warning signs, barricades, or other approved means and against erosion.

2.	Performing the necessary weeding, spraying (with approved insecticides or fungicides), cultivating, replacing mulch, and tightening or replacing guy wires and stakes as may be required.

3.	Deep water the seedlings and shrubs immediately after planting.  Deep watering shall provide water penetration throughout the entire root zone to the total depth of the plantings, planting pits and trenches with a minimum of runoff. Keep the immediate root areas moist at all times. Rain is not a substitute for deep watering unless permitted by the Engineer.

Deep water seedlings and shrubs according to the following maintenance schedule:

a.	Deep water the plants at least twice a week during the first 45 days after planting.

(1)	The 45 Days Extend Past September 30. Stop the twice weekly deep watering after September 30 and resume the twice weekly watering on May 1 of the following calendar year for the balance of the 45 days. Continue to water the plants as noted in Subsection 621-3.07.3.a.(2).

(2)	The 45 Days Does Not Extend Past September 30. After the 45 days of deep watering in the planting year, water the plants for the balance of the growing season.

(a)	Once a week in June and July

(b)	Once between August 10 and August 20

(c)	Once during the last week in September

b.	Deep water the plants during the Period of Establishment.

(1)	Once a week during May, June, and July

(2)	Once between August 10 and August 20

(3)	Once during the last week in September

c.	When directed, deep water seedlings and shrubs past September 30, or provide supplemental watering any time during the life of the project if weather conditions are excessively warm or dry.

d.	When directed, deep water tree seedlings and shrubs before freeze-up.

Equip watering equipment with, or following equipment with, a vehicle equipped with a Type B advance warning arrow panel using caution mode according to Part VI of the Alaska Traffic Manual

Replace Subsection 621-4.01 with the following:

621-4.01 METHOD OF MEASUREMENT. Section 109, by the number of plants or length of hedge alive, healthy and in a vigorous condition accepted at final inspection.

Replace Subsection 621-5.01 with the following:

621-5.01 BASIS OF PAYMENT. Excavation, top soil, backfill, fertilization, and disposal of all unsuitable and surplus material and water for planting are subsidiary.

Pay Item 621(8) Water for Maintenance. Payment is for water for maintenance, growth, and establishment through the term of the Contract. Type B Advance Warning Arrow Panel for watering is subsidiary. Water for planting is subsidiary to planting.

Pay Items, except Pay Item 621(8), paid at the rate of 90 percent of the bid unit price for the initial plantings. The balance withheld is after the establishment period and all dead and unhealthy plants, Subsection 621-3.06, are replaced, and established.

Pay Item No.	Pay Item	Pay Unit

621(1)	Tree	Each

621(2)	Shrub	Each

621(3)	Hedge	Linear Foot

621(4)	Vine	Each

621(7)	Furnishing and Planting Seedlings	Each

621(8)	Water for Maintenance	M. Gal.

621(9)	Furnishing and Planting Willow Bundles	Each

CR621.1-050118

If more than one species for Pay Items 621(1), (2), (3), (4), and (7) use pay items similar to 612(1A, B, C…; 2A, B, C…; 3A, B, C…; 4A, B, C…;

7A, B, C…).

Special Provisions

Replace Section 623 with the following:

SECTION 623
VEGETATIVE COVER

Sect 623: CR623/Section 623 Vegetative Cover replaces SSHC Section 623 Block Sodding.

Vegetative Mat, typically used in rural and urban areas where waterway bank revegetation and protection work (Section 690 Waterway) occurs. Include CR690 if including "Vegetative Mat" and vice versa, otherwise remove "Vegetative Mat" all places below. Contact the Spec Engineer for a copy of CR690 Draft.

Related Sect/Sp:  201, 618, 619, 620, 621, 690, 724, 725, 726, 727

Section 623 is about "vegetative cover" inclusive of sod, vegetative mat and sodding and not about curb ramps and related work. The specific work should be on the drawings. If you want to indicate sod related to a specific work and payed subsidiary to that work, (curb ramps) add the project provision to 4.01 and 5.01. No other reference, to the parent work (curb ramps) is required from Section 623.

623-1.01 DESCRIPTION. Establish a healthy living perennial vegetative groundcover (vegetative cover) by sodding. Maintain the living cover for the term of the Contract.

Rural Area Roadside. Topsoil, and seed are preferred.

623-2.01 MATERIALS. Furnish vegetative cover free of noxious weeds as included in, 11 AAC 34.020.a. Prohibited Noxious Weeds, items 1-14. If storing vegetative cover before installation, keep the material in a cool shaded area and moist throughout the root zone.  If required, water the sod prior to harvesting. Plant the vegetative cover material within 48 hours of harvest.

Lawn Sod. Topsoil and lawn sod may be used in urban areas. Discuss the option to use sod vs topsoil and seed with Construction. Topsoil and seed are still a good option.

Lawn Sod.

Grass sod commercially cultivated specifically for turf sod. Furnish healthy grass sod vegetation that is first-class representatives of the species, is free of diseases and harmful insects. Provide sod that is mature, not less than 18 months old, machine cut no less than 1-foot in width with clean cut edges, and a uniform thickness of 3/4-inch or more, excluding top growth and thatch. Broken pieces and torn or uneven ends will not be accepted.

Lawn sod may be substituted for seeding, Section 618. Seeding may not be substituted for lawn sod.

Vegetative Mat.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Furnish living native plants and grasses in at least 12-inch thick by 6-square feet sections, intact, and without damage to the plant shoots, roots, or rhizomes. Preferred plants include willow, alder, fireweed, calamagrostis, bearberry, red top, and other native species. Attain mats from within the right-of-way, that grow in the more fertile soils in the confines of the area to be cleared and grubbed, from areas out of sight of the roadway, and from areas where waterway bank revegetation and bank protection work is occurring. If vegetative mat is not available within the right-of-way, acquire the material from an offsite donor site similar to the transplanting site with the consent of the property owner; or with the approval of the Engineer, purchase material from a commercial supplier. Obtain approval of the material, in its original position, before cutting.

Fertilizer.

Furnish 16─16─16 (N-P-K) and meet the requirements of Section 725.

Topsoil.

Potential hydrogen (pH): 6 to 6.5. Meet the requirements of Section 726.

CONSTRUCTION REQUIREMENTS

623-3.01 SOIL PREPARATION.

Lawn Sod.

Clear the area(s) to be sodded of stones 2 inches and larger, plant growth, sticks, stumps, soil clods, trash, and other debris. Dispose of debris outside the project limits.

Make the area(s) reasonably free of ruts, holes, humps, and other irregularities that may interfere with the application of topsoil, the sodding operation, growth of cover, or subsequent maintenance of the vegetative-covered areas.

Apply topsoil 4" deep minimum, and spread evenly. Rake smooth, and roll to a firm consistency. Coordinate with the sod supplier, do not compact hard, or leave loose. Adjust initial grades so the final sod topsoil level is slightly below adjacent hard surface grades. Refer to Section 620 for further requirements.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

623-3.02 SODDING SEASON. Sod disturbed areas after permanent cessation of ground disturbing activities in that area, within the period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.5 Soil Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Sod between May 15 and September 15.

Sod is an insulation and therefore the planting period is to September 15 vs August 1.

623-3.03 APPLICATION.

Lawn Sod.

1.	Saturate the topsoil immediately before application of sod. Repair topsoil washout.

2.	Use approved methods to cut and place sod.

3.	Do not damage the plant shoots, roots, or rhizomes, except as required to harvest the sod.

4.	Keep the sod moist at all times.

5.	Maintain the soil around the roots and rhizomes during harvest, hauling, and planting.

6.	Lay the sod perpendicular to the slope. Lay the first sod row in a straight line, then place subsequent rows parallel to and tightly against each other, staggering lateral joints. Do not stretch or overlap the sod. Tightly butt all joints so that no opening exists for water to pass through, and the turf creates a continuous smooth surface. Secure pieces to ensure the final sod grade does not create a pedestrian tripping or mowing hazard.

Cut sod to fit irregular shaped areas.

On slopes greater than 3:1, stake sod pieces as directed.

Do not use sod segments containing less than 2-square feet of surface.

7.	Diagonally roll sod after placement.

8.	Apply fertilizer at a rate of 5 to 6 pounds per 1000 square feet (250 pounds per acre).

9.	Within one hour of placing, water the sod until fully saturated.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

623-3.04 MAINTENANCE AND WATERING. Maintenance includes but is not limited to:

Lawn Sod.

1.	Protecting sodded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following sodding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the topsoil for sodding.  Sod repaired area(s).  Refer to Subsections 623-3.01 and 3.03.

3.	Resod areas not showing evidence of satisfactory growth within 3 weeks of sodding and after repairs are complete.  Resod dead patches of sod. Contact ADNR for advice or corrective measures.

4.	Keep sod continuously moist until roots are established. Water the sod for healthy growth. Adjust the amount of water when directed.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

623-3.05 ACCEPTANCE.

Lawn Sod.

The vegetative ground cover will be inspected considering each station and each side of the road a separate area.  Acceptance of the vegetative cover requires satisfactory growth of the complete sodded area. Repair/resod areas that are not accepted.

Vegetative Mat. Section 690.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

623-3.06 PERIOD OF ESTABLISHMENT.

Lawn Sod.

For each area accepted, the establishment period extends one complete growing season following the date of Project Completion, subsection 105-1.15.  Employ all possible means to preserve/maintain the new vegetative cover in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative cover, according to Subsection 623-3.04, to not less than the requirements for acceptance, Subsection 623-3.05.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

4.01. Typical measurement - square yard. If you wish to make sod subsidiary to an item, remove the measurement of sod, and add a special under 5.01, making it subsidiary to the other item (Curb etc.).

623-4.01 MEASUREMENT. Section 109, lawn sod measured on the slope of the ground surface.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

623-5.01 BASIS OF PAYMENT. The contract price includes all cutting, hauling, placing, topsoil, ground (including topsoil) preparation, fertilizer, and application, water (for harvest, application, and maintenance), cleanup and maintenance for the term of the Contract, including the establishment period.

If using vegetative mat, include "Vegetative Mat".  If not using, delete "Vegetative Mat".

Vegetative Mat. Section 690.

Pay Item No.	Pay Item	Pay Unit

623(1)	Lawn Sod	Square Yard

CR623-050118

Topsoil. Be sure to include 618 and 620 pay items, if topsoil and seed are also included in the project, separate from the sod and the topsoil required for the sod. Be sure it is clear the topsoil for seed is not subsidiary to the sod item.

Water for sod is subsidiary. If the project requires water to be paid separate, include the Pay Item [623(2)	Water for Sod		M Gal.] and revise the 1st paragraph to exclude the water.

SECTION 627
WATER SYSTEM

CR627.1 - AWWU:  Remove and replace water valve box and lid.

AWWU:  Remove and replace water valve box and lid.

Sect 627:  CR627.1

Related Sect/Sp:

Special Provisions

627-1.01 DESCRIPTION.  Add the following:

Coordinate with the Engineer and AWWU; and participate in a pre-construction condition inspection, and a post-construction condition inspection of the water system facilities.

The inspections may identify main valve boxes, the top section, the lid and additional items, to be replaced.  Replace additional facility items as directed by the Engineer.

627-3.01 GENERAL.  Add the following:

Contractor furnishes the required traffic control, including personnel to assist, while performing inspections.

The Contractor forfeits all right to assert pre-existing damage if the Contractor fails to participate in the inspections.

Install the replacement facility items as shown in the Plans.

During inspections the AWWU representative, the Engineer and the Contractor will observe each facility's location and condition.  The Engineer will indicate the additional facility items to be replaced.

Provide 3 days advance written notice to AWWU scheduling a pre-construction inspection of the facilities.  Conduct this inspection before pavement removal begins.  Contact the AWWU Project Manager to determine where to send the written notice, (907) 564-2763.  Provide the Engineer a copy of the written notice.

AWWU furnishes the valve box top sections and lids.  Contact the AWWU Project Manager to schedule the pick-up of the furnished materials.  Allow 3 working days from the time contact is made to pick-up of the materials.

If service connection locates are required, contact AWWU Field Services at (907) 564-2762.  Allow 3 working days from the time of the request to the time of locate.

Salvage the replaced valve box top sections and lids.  Coordinate with, and deliver to AWWU the salvaged materials.  Dispose of water system facility materials not wanted by AWWU, according to the Municipality of Anchorage rules and regulations.

Provide a written notice to AWWU scheduling a post-construction inspection of the facilities, after the paving operations are complete and 3 days in advance of the inspection.

627-5.01 BASIS OF PAYMENT.  Add the following:

Pay Item 627(10A) includes full compensation for labor, equipment, and incidental materials for installation, complete-in-place after final paving as accepted by the Engineer, including but not limited to:

	inspections

	removal and disposal of existing valve box top sections and lids

	installing the replacement materials

	adjusting the facility item down prior to the planing operation

	adjusting the facility item up prior to the paving operation

Repairs to facilities damaged or rendered inoperable, after the pre-construction inspection and before the final inspection, are the responsibility of the Contractor and no additional payment will be made.

All traffic control required for the inspections will be paid under the 643 Pay Items.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

627(10A)	Remove and Replace Water Valve box and Lid	Each

CR627.1-060115

Special Provisions

CR630 is a replacement provision. Keep all, unless you specifically change a portion of the provision vs using one type or class in the project.

Sect  630

Related Sect/Sp:  619, 631, 632, 633, 634, 641, 727, 729

Replace Section 630 with the following:

SECTION 630
GEOTEXTILE FOR EMBANKMENT AND ROADWAY
SEPARATION, STABILIZATION AND REINFORCEMENT

630-1.01 DESCRIPTION.  Prepare ground surface, and furnish and place geotextiles for separation, stabilization, and/or reinforcement as shown on the Plans.

630-2.01 MATERIALS.  Use materials that conform to the following:

Geotextiles and Sewn Seam Strength	Subsection 729-2.01

Sewing Thread.  Use high strength polypropylene, or polyester. Do not use nylon thread.  Use thread of contrasting color to that of the geotextile itself.

630-3.01 CONSTRUCTION.

1.	Surface Preparation.  Prepare ground surface by removing stumps, brush, boulders, and sharp objects. Fill holes and large ruts, as directed by the Engineer, with material shown on the Plans or as approved by the Engineer.

2.	Geotextile Placement. Unroll geotextile directly onto the prepared surface.  Stretch geotextile to remove any creases, folds or wrinkles.  Do not drag the geotextile through mud or over sharp objects that could damage the geotextile.  Do not expose geotextiles to sunlight for longer than 14 days after removal of protective covering.  Do not allow geotextiles to get wet prior to installation.

a.	Separation and Stabilization.  Lay geotextile for embankment separation and stabilization parallel to roadway centerline.  On horizontal curves, place in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped.  On tangents, straighten the geotextile and sew or overlap butt ends.  Shingle overlaps in the same direction as fill placement.  Prevent overlapped edges from lifting during construction.

b.	Reinforcement. Lay the machine direction of the geotextile, for embankment reinforcement, perpendicular to the roadway centerline or as shown on the Plans.  Join segments by sewing or an approved bonding or attachment process.  Shingle overlaps in the same direction as fill placement if seams are not sewn.  Prevent overlapped edges from lifting during construction.

TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

| Degree of Curve | Maximum Segment Length (ft.) |
| --- | --- |
| 1 | 125 |
| 2 | 90 |
| 3 | 75 |
| 4 | 65 |
| 5 | 55 |
| 6 | 50 |

3.	Joining. Join adjacent geotextiles for separation or stabilization by overlapping or sewing.  Join adjacent geotextiles for reinforcement by sewing or as shown on the Plans.  Other attachment methods may be used if approved by the Engineer.

a.	Sew seams with a Butterfly or J-Seam. Use a double-thread chain stitch (lock stitch).  Bring adjacent sections of geotextile together and fold so that the stitching penetrates four layers of geotextile for the full seam length.  Make the stitching line 1 1/4-inches (± 1/4-inch) from the folded edge of the seam and at least 1/2-inch from the free edge of the geotextile.  Sew seams so that they face upward and can be easily inspected by the Engineer.  Illustrations showing correct stitch formation and seam configurations are provided in Figure 1-2 (page 1-28) of the FHWA publication, Geosynthetic Design & Construction Guidelines, FHWA-NHI-07-092, August 2008.

b.	Overlap geotextile sections by a minimum of 3-feet at all longitudinal and transverse joints.  Place the beginning of each new roll beneath the end of the previous roll to prevent the advancing fill from lifting the geotextile.  Shingle in the direction of construction.

4.	Material Placing and Spreading. Place embankment material closely following fabric laydown to avoid fabric displacement and exposure. During placing and spreading of material, maintain a minimum depth of 12-inches of cover material; or a minimum depth equal to the separation distance between multiple layers of geotextile as shown on the Plans when this separation distance is less than 12-inches; at all times between the geotextile and the wheels or tracks of construction equipment.  Limit the size and weight of construction equipment to reduce rutting in the initial lift above the geotextile to not greater than 3-inches deep to prevent overstressing the geotextile.

Spread the material in the direction of the upper overlapped geotextile.  Maintain proper overlap and geotextile continuity. If sewn or bonded seams are used, place the cover material and spread in only one direction for the entire length of the geotextile.  On weak subgrades limit height of dumped cover material to prevent localized subgrade and/or geotextile failure.  Do not drop stones or frozen material larger than 1-foot in diameter directly onto the geotextile from a height of more than 1-foot.

Compact using a smooth drum roller or in a manner approved the Engineer.  Do not allow construction equipment to make sudden stops and starts on the cover material.  Do not allow turning of vehicles on the initial lift of cover material above the geotextile.  Fill any ruts over 3-inches deep occurring during construction with additional material shown on the Plans; do not grade adjacent material into rut. Compact rut fill material to the specified density.

5.	Geotextile Repair. Should the geotextile be torn, punctured, or the overlaps or sewn joints disturbed – as evidenced by visible geotextile damage, subgrade pumping, intrusion, or embankment distortion – remove the backfill around and under (if required by the Engineer) the damaged or displaced area and repair or replace the damaged area.  Make repairs to the damaged area with a patch of the same type and class of geotextile originally placed.  Make patches overlap by a minimum of 3-feet or sew patches to the existing geotextile, as specified for joining of the same type and class of geotextile, unless otherwise directed by the Engineer.

a.	Separation and Stabilization.  Overlay torn area with geotextile with a minimum 3-feet overlap around the edges of the torn or damaged area or sew and bond according to Subsection 630-3.01.3.a. Ensure the patch remains in place when cover material is placed over the affected area.

b.	Reinforcement.  Sew according to Subsection 630-3.01.3.a unless joining by overlap is shown on the Plans. Ensure the patch remains in place when cover material is placed over the affected area.

630-4.01 METHOD OF MEASUREMENT.  Measure geotextile by the square yard of ground surface covered.  No allowance will be made for overlap, whether at joints or patches.

630-5.01 BASIS OF PAYMENT.  Payment will be at the Contract unit price. Repair and replacement costs for damaged geotextile are subsidiary to the Section 630 Pay Items.

Material used to fill ruts and holes will be paid for at the unit price for the type of material used.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

630(1)	Geotextile, Separation, Class 3	Square Yard

630(2)	Geotextile, Stabilization, Class 1	Square Yard

630(3A)	Geotextile, Reinforcement – Type 1	Square Yard

630(3B)	Geotextile, Reinforcement – Type 2	Square Yard

CR630-070115

Special Provisions

Replace Section 631 with the following:

SECTION 631
GEOTEXTILE FOR SUBSURFACE DRAINAGE AND EROSION CONTROL

CR631 is a replacement provision.  Keep all unless specifically changing a portion of the provision vs using one class compared to another.

Sect  631

Related Sect/Sp:  619, 630, 632, 633, 634, 641, 727, 729

631-1.01 DESCRIPTION. Prepare ground surface, and furnish and place geotextiles for subsurface drainage and erosion control, as shown on the Plans.

631-2.01 MATERIALS. Use materials that conform to the following, for the class specified in the bid schedule:

Geotextiles and Sewn Seam Strength	Subsection 729-2.01

Sewing Thread. Use high strength polypropylene, or polyester. Do not use nylon thread.  Use thread of contrasting color to that of the geotextile itself.

631-3.01 CONSTRUCTION.

1.	Surface Preparation. Prepare ground surface by removing stumps, brush, boulders, and sharp objects.  Fill holes and large ruts, as directed by the Engineer, with material shown on the Plans or as approved by the Engineer.  Construct smooth and stable trench walls.

2.	Geotextile Placement. Unroll geotextile directly onto the prepared surface.  Stretch geotextile to remove any creases, folds or wrinkles.  Place geotextile in a manner which ensures intimate contact between the trench wall and the geotextile (i.e., no voids, folds, or wrinkles).  The geotextile may be held in place with securing pins at 3-feet spacing along all edges (but not closer than 2-inches from the edge) to prevent movement during construction.  Do not expose geotextiles to sunlight for longer than 14 days after removal of protective covering.  Do not allow geotextile rolls to get wet prior to installation.

a.	Subsurface Drainage.  In trenches, after placing the geotextile and material shown on the Plans, fold the geotextile over the top of the material shown on the Plans to produce a minimum overlap of 12-inches, for trenches greater than 12-inches wide.  In trenches less than 12-inches wide, make the overlap equal to the width of the trench.  Then cover the geotextile with the subsequent course of material.

b.	Erosion Control.  Place and anchor the geotextile on the approved surface so not to tear or excessively stretch the geotextile by placement of the overlying materials.  Secure the geotextile to the slope but secure it loosely enough so that the geotextile will not tear when riprap or other cover material is placed on the geotextile.  The geotextile shall not be keyed at the top of the slope until the riprap or other cover material is in place at the top of the slope.  Anchor the terminal ends of the geotextile using key trenches or aprons with a minimum of 24-inch depth into the soil substrate at the crest and toe of slope, or as shown on the Plans.  Other temporary or permanent anchoring method may be used, as approved by the Engineer.  Place geotextile with the machine direction parallel to the direction of water flow (normally parallel to the slope for erosion control runoff and wave action, and parallel to the stream or channel).

3.	Joining. Join geotextile by sewing or overlapping. Joining by bonding or other attachment methods may be used, subject to approval by the Engineer.

a.	Sew seams with a Butterfly or J-Seam. Use a double thread chain stitch (lock stitch). Bring adjacent sections of geotextile together and fold so that the stitching penetrates four layers of geotextile for the full seam length.  Make the stitching line 1 1/4-inches (± 1/4-inch) from the seams so that they can be easily inspected by the Engineer or representative.  Illustrations showing correct stitch formation and seam configurations are provided in Figure 1-2 (page 1-28) of the FHWA publication, Geosynthetic Design & Construction Guidelines, FHWA-NHI-07-092,

August 2008. Conform both factory and field sewn seams to the strength requirements of Table 1 as outlined in the AASHTO M 288 for subsurface drainage and erosion control applications.

b.	Overlap geotextile sections by a minimum of 3-feet at all longitudinal and transverse joints.  Overlap successive geotextile sheets in the direction of flow so that the upstream sheet is placed over the downstream sheet and/or upslope over downslope.  In trenches, where overlapped seams are constructed in the longitudinal trench direction, make the overlap equal to the width of the trench.

4.	Placement of Cover Material. Following placement of the geotextile on the prepared surface, place cover material of the type shown on the Plans. Place the cover material and armor from the bottom to the top of the slope using methods which minimize tearing and/or excessive stretching of geotextile.  In underwater applications, place the geotextile and the required thickness of cover material in the same day.  Maintain proper overlap and geotextile continuity.  Do not exceed the allowable drop heights for cover material shown in Table 631-1.  Do not allow stones with a weight of more than 100-pounds to roll down the slope on the geotextile.  Do not grade the slope in a way that will disturb the cover material or armor stone once it has been placed.  Backfill all voids in the riprap or other cover material that exposes the geotextile, with material approved by the Engineer, so that the geotextile is completely covered.

TABLE 631-1

ALLOWABLE DROP HEIGHT FOR GEOTEXTILE

| INDIVIDUAL STONE Max. Weight (lbs.) | ALLOWABLE DROP HEIGHT (ft.) |  |
| --- | --- | --- |
|  | UNPROTECTED GEOTEXTILE | PROTECTED GEOTEXTILE * |
| < 5 | 3 | 3 |
| 5 – 250 | 0 | 3 |
| > 250 | 0 | 0 ** |

* Protected geotextile is defined as having a gravelly covering (cushion layer) at least 6-inches thick.

** If stones greater than 250-pounds must be dropped or if a height of drop greater than 3-feet is required, then perform field trials to determine the minimum cushion thickness and/or maximum height of safe drop without damaging the geotextile.

Maintain a minimum depth of 12 inches of cover material between the geotextile and the wheels or tracks of the construction equipment.

5.	Geotextile Repair. Should the geotextile be torn, punctured, or the overlaps or sewn joints disturbed – as evidenced by visible geotextile damage – remove the backfill around the damaged area and repair or replace the damaged area at no additional expense to the State.  Make repairs to the damaged area with a patch of the same type and class of geotextile originally placed.  Overlay torn area with geotextile with a minimum 3-feet overlap around the edges of the torn area.  Ensure that the patch remains in place when material is placed over the affected area.

631-4.01 METHOD OF MEASUREMENT.  By the area covered, measured along the ground surface.  No allowance will be made for geotextile in key trenches or for overlap, whether at joints or patches.

631-5.01 BASIS OF PAYMENT.  Payment will be at the Contract unit price.  Repair and replacement costs for damaged geotextile are subsidiary to the Section 631 Pay Items.

Material used to fill ruts and holes will be paid for at the unit price for the type of material used.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

631(1)	Geotextile, Drainage, Class 2	Square Yard

631(2)	Geotextile, Erosion Control, Class 1	Square Yard

CR631-070115

SECTION 632
PAVING FABRIC

Sect 632

Related Sect/Sp: 619, 630, 631, 633, 634, 641, 727, 729

Special Provisions

632-3.01 CONSTRUCTION.

2.	Application of Sealant. Replace the 2nd Sentence with:  Apply the asphalt sealant uniformly at 0.20 to 0.30 gallons per square yard and at a temperature of between 295 F min. and 320 F max. in the distributor tank, or as directed by the Engineer and/or Paving Fabric manufacturer.

4.	Fabric Placement. Add the following: Overlap geotextile joints to ensure full closure of the joint. Do not exceed a 6 inch overlap. Do not allow the Geotextile to become wet. Removal and replacement of damaged geotextiles is the responsibility of the Contractor.

5.	Bituminous Surface Course Overlay. Add the following: Do not allow the temperature of the hot-mix asphalt to exceed manufacturer's recommendations.

632-4.01 METHOD OF MEASUREMENT. Add the following:  No allowance will be made for overlap, whether at joints or patches.

632-5.01 BASIS OF PAYMENT. Add the following: Removal and replacement of damaged geotextiles is subsidiary to the Section 632 Pay Items.

CR632.1-070115

Special Provisions

Replace Section 633 with the following:

SECTION 633
SILT FENCE

CR633 is a replacement provision. Keep all unless specifically changing a portion of the provision.

Sect  633

Related Sect/Sp:  619, 630, 631, 632, 634, 641, 727, 729

633-1.01 DESCRIPTION. Furnish, install, maintain, and remove temporary silt fence as shown on the Plans or as directed by the Engineer.

633-2.01 MATERIALS. Use materials that conform to the following:

Geotextile	Subsection 729-2.01

Silt Fence	Subsection 729-2.04

Posts	Wood 1.5-inch x 1.5-inch x 36-inch min., steel, or approved synthetic material.

Prefabricated Silt Fence	Meet the Plans and Section 633 requirements.

Attachment Devices	Staples; wire; self-locking nylon, plastic or wire ties; or other approved means to attach fabric to posts.

Support Mesh between Posts	14-guage welded wire fencing, metal chain-link fabric, or geosynthetic mesh with equivalent strength. Use maximum mesh spacing of 6 inches. Height shown on the Plans, or specified in the Bid Schedule.

633-3.01 CONSTRUCTION.  Install silt fence according to Plans.  Use Trenchless Detail when installing silt fence over permanently frozen ground. Holes may need to be predrilled for support posts. When joining to another roll, place both end posts together and wrap them with silt fence by turning them one full rotation.  Drive the wrapped posts.

633-3.02 MAINTENANCE. Maintain the integrity of the fence to contain sediment in runoff until final stabilization.

633-3.04 REMOVAL. After disturbed area has been accepted as permanently stabilized or when sediment protection is no longer needed, remove silt fence according to the Plans.

633-4.01 METHOD OF MEASUREMENT. Section 109. Measure silt fence by the length of fence installed.  No allowance will be made for overlap, whether at joints or patches.

633-5.01 BASIS OF PAYMENT.  The contract price includes installation, maintenance, removal and disposal of the fence.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

633(1)	Silt Fence	Linear Foot

633(2)	Support Mesh Reinforced Silt Fence	Linear Foot

CR633-070115

Special Provisions

Replace Section 634 with the following:

CR634 is a replacement provision. Keep all, unless specifically changing a portion of the provision, not simply removing a type.

SECTION 634
GEOGRID SOIL REINFORCEMENT

Sect 634

Related Sect/Sp:  619, 630, 631, 632, 633, 641, 727, 729

634-1.01 DESCRIPTION. Furnish and install geogrid material at locations shown on the Plans.

634-2.01 MATERIALS. Use materials that conform to the following:

Geogrid	Subsection 729-2.05

CONSTRUCTION REQUIREMENTS

634-3.01 WEATHER LIMITATIONS. Do not expose geogrid to sunlight for longer than 14 days after removal of protective covering.

634-3.02 SURFACE PREPARATION.

1.	Very Soft Ground (CBR < 1).  Care should be taken to avoid disturbing any surface crust overlying softer soil.  In these cases the geogrid should be placed directly on the unprepared subgrade.

If directed by the Engineer, minimize disturbance of the subgrade by leaving root mats in place, cutting stumps and other projecting vegetation as close and even to the ground surface as practical.

Swampland, peat, muskeg or marshes may be difficult to smooth grade and/or compact.  Create a surface that is as uniformly smooth as possible.  Grade or crown the surface for positive drainage away from the construction zone.

2.	Firm Ground (CBR 1 – 3). Prepare surface by removal of stumps, brush, boulders, and sharp objects.  Fill holes and large ruts, as directed by the Engineer, with material shown on the Plans or as approved by the Engineer.

3.	Firm Ground (CBR > 3). Compact and finish subgrade or subbase prior to placement of the geogrid.

634-3.03 GEOGRID PLACEMENT.  Unroll geogrid directly onto the prepared ground surface in the direction of advancing construction, parallel to the centerline of the roadway or according to the Plans.  Do not drag the geogrid across the subgrade.  Install the geogrid in the longest continuous practical length, free from folds, creases or wrinkles.  Hold the geogrid in place with pins, staples, sandbags or piles of granular material.

1.	Very Soft Ground. Overlap geogrid panels a minimum of 36-inches at all joints with the upper geogrid in the direction that fill will be placed. Tie panels together securely with cable ties or hog rings at 5-feet intervals or as recommended by the manufacturer and approved by the Engineer.

To limit lateral spreading and separation of overlaps, if approved by the Engineer, the Contractor may unroll the geogrid transversely/perpendicular to the roadway embankment alignment. Overlap the adjacent rolls and tie together with cable ties or hog rings at 5-feet intervals.

2.	Soft Ground. Overlap geogrid panels a minimum of 24-inches at all joints with the upper geogrid in the direction that fill will be placed.  Tie panels together securely with cable ties or hog rings at 20-feet intervals or as recommended by the manufacturer and approved by the Engineer.

3.	Firm Ground. Overlap geogrid panels a minimum of 12-inches at all joints in the direction that fill will be placed.  Tie panels together securely with cable ties or hog rings at 20-feet intervals.  Hand-tension geogrid and stake to the ground at the edges, overlaps, and in the center of each roll, at 30-feet intervals or as specified on the Plans.

634-3.04 PLACINIG AND SPREADING COVER MATERIAL. Do not operate equipment directly on the unprotected geogrid. Spread fill material in the direction of the fabric overlap.  Compact using a smooth drum roller.  Do not allow construction equipment to make sudden stops, starts, or turns on the cover material.

1.	Very Soft Ground. End-dump material onto previously placed material and spread over the geogrid with a low ground pressure (LGP equates to tire pressure of 4 psf) dozer to the depth permitted.  Maintain a minimum depth of 12-inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment, unless otherwise shown on the Plans or directed by the Engineer.  Do not dump material directly on the geogrid.  To prevent a mud wave, end-dump fill along the edges of the geogrid to form toe berms or access roads that extend one to two panel widths ahead of the remainder of the embankment fill placement.  After constructing the two berms, spread fill in the area between the toe berms by placing material parallel to the alignment and symmetrical from the toe berms inward toward the center to maintain a U-shaped leading edge (i.e., concave outward) to contain the mud wave.  Limit height of dumped piles above the geogrid to avoid local bearing failure.  Traffic on the first lift should be parallel to the embankment alignment.  Do not allow construction equipment to turn on the first lift.  Compact the first lift by tracking in place with dozers or end-loaders.  Compact with specified compaction equipment once the embankment is at least 2-feet above the geogrid.

2.	Soft Ground.  End dump material onto previously placed material and spread over the geogrid with a LGP dozer to the depth permitted. Maintain a minimum depth of 6-inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment unless otherwise shown on the Plans or directed by the Engineer.  Place the end-dumped material along the roadway centerline and spread it outward to the roadway edges to prevent the development of wrinkles or movement of the geogrid during construction.  Fill in any ruts that form during construction with material shown on the Plans.  Do not cut down the fill adjacent to the ruts.

3.	Firm Ground. Maintain a minimum depth of 6 inches of cover material at all times between the geogrid and the wheels or tracks of the construction equipment.

634-3.05 GEOGRID REPAIR. If the geogrid is torn, punctured, or the overlaps disturbed – as evidenced by visible geogrid damage – remove the backfill around the damaged area and repair or replace the damaged area.  Make repairs to the damaged area with a patch of the same class of geogrid originally placed.  Overlay torn area with geogrid with a minimum 3-feet overlap around the edges of the torn area and secure as recommended by the geogrid manufacturer, unless otherwise directed by the Engineer.

634-4.01 METHOD OF MEASUREMENT.  Measure geogrid by the square yard of ground surface covered.  No allowance will be made for overlap, whether at joints or patches.

634-5.01 BASIS OF PAYMENT.  Payment will be made at the Contract unit price. Repair and replacement costs for damaged geogrid are subsidiary to the Section 634 Pay Items.

Coordinate the Class of geogrid with Subsection 729-2.05 and the Materials' Department.

Material used to fill ruts and holes will be paid for at the unit price for the class of material used.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

634(1)	Geogrid, Stabilization, Class 		Square Yard

634(2)	Geogrid, Reinforcement, Class 			Square Yard

CR634-090315

Special Provisions

Replace Section 639 with the following:

SECTION 639
DRIVEWAYS

Sect 639:  CR639 (CR639 Rplcd CR58)

Related Sect/Sp:  306/CR306, 401/CR401, 408/CR408, 702/CR702.1, 703/CR703.1

639-1.01 DESCRIPTION. Construct driveways and approaches.

Include materials specific to the project, if needed; otherwise, leave materials as reserved.

639-2.01 MATERIALS.  Reserved.

639-3.01 CONSTRUCTION.  Reserved.

Include construction requirements specific to the project, if needed; otherwise, leave construction as reserved.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed.

639-5.01 BASIS OF PAYMENT.  The Contract unit price for driveways and approaches is for furnishing equipment and labor.

Pavement removal and excavation required constructing driveways and approaches is subsidiary to the driveway and approach pay items.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(1)	Residence Driveway	Each

639(2)	Commercial Driveway	Each

639(3)	Public Approach	Each

639(4)	Driveway	Each

639(6)	Approach	Each

CR639-092016

STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION (SSHC), 2016 ED.

6CR41 Erosions, Sediment, and Pollution Control replaces 2017 SSHC Section 641; SSP53A, B, C, and SM2.

Notes to Designer and Construction Engineers.

Consider the following when including CR641 or a Section 641 project provision in the project specials and more importantly when modifying the special to fit the unique conditions/needs/requirements of the project.

Regulations:	Requirements of the Construction General Permit (CGP), and other Federal, State, and Local government regulations.

	It is not permitted to diminish the requirements of the Regulations

CR641:

	All projects require the complete CR641 provision, the typical ESCP and SWPPP. Do not use a reduced CR641, ESCP or SWPPP

	Additions, modifications, or deletions may create a conflict with the Regulations

	There are no key notes identifying what is/is not, directly or in summary, from the Regulations

1.03 Plan and Permit Submittals, 4.

Owners or operators of construction sites equal to or greater than one acre, or those designated by ADEC, are required to submit an eNOI to obtain permit coverage.  The NOI is, only, required for projects covered under the CGP or designated by ADEC.  The ESCP should clearly indicate the area of the construction site. CGP does not typically require a NOI for projects less than 1 acre.

Engineer - Carefully review the size of the construction site as presented in the SWPPP.  If less than one acre and the Contractor rounded up to one acre the Contractor and Department will both be required to submit a NOI to ADEC.

	Plane and Pave projects that do not include other work beyond the planed surface are generally viewed as maintenance by ADEC and do not typically require an NOI.

641 Pay Items.  Use Pay Items 641(1), (5), (6), and (7).  Do not use Pay Items (2), (3), and (4) unless specifically approved by the Project Manager and Construction Engineer. Pay Items (2), (3), and (4) have been removed from CR641.

Related Sections.  When CR641 is included in a Project - typically include specials CR619 and CR727.

Sect 641:  CR641. 	Remove this page and the headers will realign similar to other sections.

Related Sect/Sp: 618/CR618.1.2.3, 619/CR619, 621/CR621.1, 623/CR623.1, 724/CR724.1, 726/CR726.1, 727/CR727

Special Provision

Replace Section 641 with the following:

SECTION 641
EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the APDES Construction General Permit. The state APDES program is administered by DEC.  Section 301(a) of the Clean Water Act (CWA) and 18 AAC 83.015 provide that the discharge of pollutants to water of the U.S. is unlawful except as allowed by the CGP.

641-1.02 DEFINITIONS. These definitions apply only to Section 641.

ACTIVE TREATMENT SYSTEM (ATS) OPERATOR. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

ALASKA CERTIFIED EROSION AND SEDIMENT CONTROL LEAD (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years. (See Qualified Person)

ALASKA DEPARTMENT OF ENVIRONMENTAL CONSERVATION (DEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM (APDES). A system administered by DEC that issues and tracks permits for storm water discharges.

BEST MANAGEMENT PRACTICES (BMPS).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

CLEAN WATER ACT (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

CONSTRUCTION ACTIVITY. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute wash-down, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

CONSTRUCTION GENERAL PERMIT (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by Alaska DEC. It authorizes storm water discharges provided permit conditions and water quality standards are met.

CORPS OF ENGINEERS PERMIT (COE PERMIT). A U.S. Army Corps of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

ELECTRONIC NOTICE OF INTENT (ENOI). The electronic Notice of Intent submitted to DEC, to obtain coverage under the CGP.

ELECTRONIC NOTICE OF TERMINATION (ENOT). The electronic Notice of Termination submitted to DEC, to end coverage under the CGP.

ENVIRONMENTAL PROTECTION AGENCY (EPA). A federal agency charged to protect human health and the environment.

ERODIBLE STOCKPILE. Any material storage area or stockpile consisting of mineral aggregate, organic material, or a combination thereof, with greater than 5 percent passing the #200 sieve, and any material storage where wind or water transports sediments or other pollutants from the stockpile.  Erodible Stockpile also includes any material storage area or stockpile where the Engineer determines there is potential for wind or water transport of sediments or other pollutants away from the stockpile.

EROSION AND SEDIMENT CONTROL PLAN (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

FINAL STABILIZATION. Is defined in this section as it is defined in the CGP. Appendix C.

HAZARDOUS MATERIAL CONTROL PLAN (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

INSPECTION.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Storm Water Inspector.

MUNICIPAL SEPARATE STORM SEWER SYSTEM (MS4) PERMIT.  A DEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

MULTI-SECTOR GENERAL PERMIT (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

LOW-ERODIBLE STOCKPILE.  Any material stockpile identified in the CGP definition for Final Stabilization Section 1.b, and includes: riprap, gabion backfill, porous backfill, railroad ballast, and sub-ballast, ditch lining, or fill material with low erodibility. The stockpile shall not have a gradation of more than 5 percent passing the #200 sieve unless approved by an Engineer. There shall be no possibility of sediment transport due to water or wind erosion.

OPERATOR(S). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

POLLUTANT. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sediment, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

PROJECT ZONE. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

QUALIFIED PERSON. A person knowledgeable in the principles and practice of erosion and sediment controls. A qualified Person must be certified under the Alaska Certified Erosion and Sediment Control Lead (AK-CESCL) training program. One of the following training and certification programs may substitute for AK-CESCL certification: CPESC, CESSWI, CPSWQ, OR CISEC (CGP, Appendix C).

RECORDS. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC PLAN). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

SPILL RESPONSE FIELD REPRESENTATIVE. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

STORM EVENT. A rainfall event that produces more than 0.5-inch of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of less than 0.1 inch of rain per day.

STORM WATER POLLUTION PREVENTION PLAN (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules, and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

STORM WATER POLLUTION PREVENTION PLAN TWO (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

SUBCONTRACTOR SPILL RESPONSE COORDINATOR. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

SUBCONTRACTOR SWPPP COORDINATOR. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

SUPERINTENDENT. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP AMENDMENT. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP MANAGER. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP PREPARER. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

TEMPORARY STABILIZATION. Protecting soils from erosion and sediment loss by rainfall, snow melt, runoff, or wind with a temporary vegetative and/or non-vegetative protection cover. Temporary stabilization may include a combination of seeding, geotextiles, mulches, surface tackifiers, rolled erosion control products, low-erodible gravel or paving, or the mentioned BMP's combined together with trackwalking.

UTILITY SPILL RESPONSE COORDINATOR. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

UTILITY SWPPP COORDINATOR. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS. For plans listed in Subsection 108-1.03.5 (SWPPP, HMCP and SPCC), use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14-day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP using Form 25D-111. See Subsection 641-1.03.4 for further SWPPP submittal requirements.

2.	Hazardous Material Control Plan.  The HMCP Template can be found at the following webpage: http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml. Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to DEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and DEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than 3days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to DEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and DEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities on Forms 25D-107 and 25D-108, SWPPP Certifications on Forms 25D-111 and 25D-109, both permittee’s signed eNOIs and DEC’s written acknowledgement.

5.	Ending CGP Coverage. Submit an eNOT to DEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and DEC’s acknowledgement letter to the Department within 3 days of filing the eNOT or receiving a written response.

6.	DEC SWPPP Review.  When CGP Part 2.1.3, requires DEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to DEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within  7 days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within 7 days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within 7 days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within 7 days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI.  When required by the CGP Part 2.7, modify your eNOI to update or correct information within 30 calendar days of the change. Reasons for modification include a change in start or end dates, change in Owner/Operator address and contact information, change in site information, any changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change 	in location of SWPPP records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed.

641-1.04 PERSONNEL QUALIFICATIONS. Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

1.	The SWPPP Preparer.

a.	Total disturbed acreage, 20 acres or less, must meet at least one of the following qualifications:

(1).	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

(2).	Current certification as AK-CESCL, and at least two years' experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

(3).	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

b.	Total disturbed acreage greater than 20 acres, must meet Subsection 641-1.04.1.aabove, and complete a SWPPP Preparation course.

2.	The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

3.	The SWPPP Manager must have current certification as AK-CESCL  The SWPPP Manager must meet the experience, , and authority requirements identified in the CGP for the Storm Water Lead and Storm Water Inspector positions.

4.	The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principles and practices of treatment systems in general, and the operation of the project-specific ATS.  The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operator certification course.

5.	The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control; or

b.	CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation on Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify on Form 25D-105, that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials.  Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with DEC, COE, and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.4) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage.

3.	Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least 7 days advance notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

a.	Opportunities to phase construction activities;

b.	Appropriate BMPs and their sequencing; and

c.	Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.

Use the Department’s project ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and described in the CGP Part 5.0.

a.	Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

(1)	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

(2)	SWPPP Certification for DOT&PF (25D-109)

(3)	SWPPP Delayed Action Item Report (25D-113), if needed

b.	Use the following Department forms for recording information in the SWPPP:

(1)	SWPPP Amendment Log (25D-114)

(2)	SWPPP Certification for Contractor (25D-111)

(3)	SWPPP Construction Site Inspection Report (25D-100)

(4)	SWPPP Corrective Action Log (25D-112)

(5)	SWPPP Daily Record of Rainfall (25D-115)

(6)	SWPPP Delegation of Signature Authority – Contractor (25D-108)

(7)	SWPPP Grading and Stabilization Activities Log (25D-110)

(8)	SWPPP Pre-Construction Site Visit (25D-106)

(9)	SWPPP Project Staff Tracking (25D-127)

(10)	SWPPP Subcontractor Certification (25D-105)

(11)	SWPPP Training Log (25D-125)

(12)	SWPPP Noncompliance (25D-143)

SWPPP Template forms and instructions are available online at:

http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

a.	The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

b.	The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

(1)	Over which each operator has operational control; and

(2)	Where the Department and Contractor are co-operators.

c.	For work outside the Project Zone the SWPPP must identify the entity that has storm water permit coverage, the operator, and the areas that are:

(1)	Dedicated to the Project and where the Department is not an operator; and

(2)	Not dedicated to the project, but used for the project.

d.	Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

e.	Comply with the CGP Part 1.4.3 Authorized Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

f.	Include the Department’s Antidegradation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered a high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.6.

g.	Where the project intersects a Public Water System (PWS), the Engineer will notify the PWS contact for the Department and Contractor according to the CGP Part 4.10. Contractor Amend a copy of the communications in Appendix Q.

h.	There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Contractor shall implement a monitoring plan approved by the Department for the storm water within the Project Zone, and shall provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

i.	Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.2.1.  Use stakes, flags, or silt fence, etc. to identify areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.2.2.

j.	Comply with CGP Part 4.4, and the DEC General Permit for Excavation Dewatering (AKG002000), requirements for dewatering for trenches and excavations.

k.	The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

l.	Describe methods and time limits, to initiate temporary or final soil stabilization, CGP Part 4.5.1.1Begin stabilization no later than the end of the next work day, following the day when the earth-disturbing activities have permanently ceased on any portion of the site or temporarily ceased on any portion of the site and will not resume for a period exceeding:

(1)	Seven days for areas with mean annual precipitation 40 inches or greater; or

(2)	Fourteen days for areas with mean annual precipitation less than 40 inches.

Time allotted to complete temporary and final stabilization, 641-2.01, 3l.

m.	Within 7 days of initiating final stabilization, CGP Part 4.5.1.4, either complete final stabilization or continue maintenance of work until final stabilization is complete. Complete temporary stabilization within 14  days of initiating stabilization, CGP Part4.5.1.2.

n.	Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

o.	Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to  use of the system and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI, documented in the SWPPP, and meet with the requirements in the CGP Part 4.6.

p.	The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

q.	Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and final stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words, and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the manufacturer's or BMP manual specifications for installation (CGP Part 5.3.6.2). If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

r.	Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth-disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities. Include drawings showing each phase of the project with the BMPs implemented in the Phase.

s.	Provide a legible site map or set of maps in the SWPPP, showing the entire site and identifying boundaries of the property where construction and earth-disturbing activities will occur, as described in the CGP Part 5.3.5. Include all BMPs on the site map.

t.	Identify the inspection frequency in the SWPPP:

(1)	Inspect once every 7 days regardless of the precipitation amount.

u.	Linear Project Inspections, described in CGP Part 6.5, are not applicable to this contract.

v.	The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities that were not included in the Department’s permitting and consultation.

w.	The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, proof of AK-CESCL, or equivalent certifications for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager, record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24-hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24-hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, proof of AK-CESCL, or equivalent certifications of ATS operators. Record the names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide proof of AK-CESCL, or equivalent certifications for the Department's Project Engineer, Storm Water Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s staff certifications in Appendix E.  Include the Department’s staff names, dates acting, and assignments, in Section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

1.	Prepare the HMCP using the DOT&PF template located at the following DOT&PF link; (http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml) for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

2.	Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24-hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

3.	List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

4.	Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

5.	List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

6.	Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

7.	Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

8.	Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.  Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

1.	Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

2.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager.

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641(7) is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS. Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified and if not specified as directed.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw and straw products certified weed free of prohibited and restricted noxious weed seed and quarantined pests, according to Alaska Administrative Code, Title 11, Chapter 34 (11 AAC 34). When straw or straw products certified according to 11 AAC 34 are not available, use non-certified products manufactured within Alaska before products manufactured in another state, country or territory. Grass, legumes, or any other herbaceous plants produced as hay, shall not be substituted for straw, or straw products.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-3.01 CONSTRUCTION REQUIREMENTS. Comply with the SWPPP and the requirements of the CGP Part 5.0.

1.	Before Construction.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP Form (25D-106), and the SWPPP must be developed (or amended) with findings from the visit;

b.	The SWPPP must be approved by the Engineer on Form 25D-109;

c.	The Contractor must be authorized to begin by the Engineer;

d.	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the DEC website;

e.	The Department approved SWPPP must be submitted to DEC and Local Government (when required); and

f.	The Contractor has transmitted to the Engineer an electronic copy, and at least one hardcopy of the approved SWPPP.

g.	The Delegation of Authority (Forms 25D-108 and 25D-107) for both the Contractor and DOT&PF Engineer are signed.

h.	Begin winter construction activity according to CGP Part 4.12.2, provided actions a, c, and g are completed. If winter construction activities may extend beyond spring thaw, the following actions must be completed before spring thaw:

(1)	Actions a through g, listed above, and

(2)	Appropriate control measures to minimize erosion and sediment runoff during spring thaw and summer rainfall are installed.

I.	Post notices.

Include the following information:

(1)	Copy of all eNOIs related to this project;

(2)	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can safely read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

j.	Install an outdoor rain guage per manufacturer’s guidance in a readily accessible location on the Project.  Projects may utilize the nearest National Weather Service (NWS) precipitation gauge station, if within 20 miles of the project, to determine rainfall amounts during storm events.

k.	Delineate the site for both land disturbing activities and areas that will be left undisturbed.

l.	Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

2.	During Construction.

Before subcontractors or utility companies begin soil-disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and final stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures CGP 4.14. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log, Form 25D-125, the dates and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Comply with CGP Part 4.8.2 for fueling and maintenance activities. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

3.	Pollutant and Hazardous Materials Reporting Requirements.

If an incident of non-compliance occurs that may endanger health or the environment a report must be made, CGP, Appendix A, Part 3.4:

a.	Orally  report  to the Engineer as soon as the permittee becomes aware of the incident,,

b.	Orally report to DEC within 24 hours after the permittee becomes aware of the incident, , and

c.	In writing, report to DEC within 5 days after the permittee becomes aware of the circumstances To report in writing complete the written noncompliance report on Form 25D-143, and file the written report with DEC. Coordinate the report with the Engineer. Include in the report:

(1)	A description of the noncompliance and its causes;

(2)	The exact dates and times of noncompliance;

(3)	If not yet corrected the anticipated time the project will be brought back into compliance; and

(4)	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

Notify the Engineer and COE Regulatory Program as soon as the permittee becomes aware of an  incident of noncompliance with COE Permits.

Report spills of petroleum products or other hazardous materials to the Engineer as soon as the permittee becomes aware of the incident, the DEC (CGP Part 9.3),and other agencies as required by law.  Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

4.	Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

a.	Implement corrective action:

(1)	If an incident of noncompliance with the SWPPP, or CGP is identified;

(2)	If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

(3)	If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

(4)	If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

(5)	If sediment accumulates more than one-third of the distance of the above-ground height of the silt fence;

(6)	If sediment accumulates to more than one-half retention height for an inlet BMP, check dam, berm, wattle, or other control measures;

(7)	If a prohibited discharge of pollutants, as specified in CGP Part 4.7, is occurring or will occur; or

(8)	If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

b.	Implement corrective actions so that they comply with the following time requirements:

(1)	For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

(2)	If a discharge occurs during a local 2-year, 24-hour storm event, initiate a corrective action the day after the storm event ends;

(3)	If installation of a new control measure is needed or an existing control measure requires redesign and reconstruction or replacement to make it operational, the corrective action must be completed within 7 calendar days from the time discovered.

(4)	For all other conditions initiate corrective actions so both of the following requirements are met:

(a)	Corrective action is completed in time to protect water quality; and

(b)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within 3 days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

5.	Stabilization.

a.	Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

(1)	Not later than the end of the next work day, following the day when the earth-disturbing activities have temporarily or permanently ceased (CGP Part 4.5.1.1, Note:).

(2)	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

(3)	As identified in the SWPPP.

b.	Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

c.	Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, low-erodible cover,  dust palliatives, or other approved methods.

d.	When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

e.	Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

f.	Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

g.	When installing a culvert or other drainage structure where stream bypass is not used, install temporary, or final stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary or final stabilization:

(1)	At the culvert or drainage structure inlet and outlet; and

(2)	In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

h.	Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install final or temporary stabilization when approved by the Engineer:

(1)	At the inlet and outlet of the culvert, drainage structure, or bridge;

(2)	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

(3)	Under the bridge.

Within 7 days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete, CGP Part 4.5.1.5,

Complete temporary stabilization within 14 days of initiating stabilization, CGP Part 4.5.1.2

6.	Ending CGP Coverage and BMP Maintenance in the Project Zone.

a.	The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

(1)	Land disturbing activities have ceased;

(2)	Final Stabilization has been achieved on all portions of the Project Zone, according to the CGP PART 4.5.2 (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

(3)	Temporary BMPs have been removed.

b.	After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

(1)	Send written notice to the Contractor with the date that the conditions were met;

(2)	Submit an eNOT to DEC; and

(3)	Provide a copy of the eNOT and DEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to DEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to DEC, and insert copies of the Department’s and the Contractor’s eNOTs with DEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and DEC’s acknowledgement letter to the Department within 3days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices, and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and at least one hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or DEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or DEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.5.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS. Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log Form 25D-112, SWPPP Amendment Log Form 25D-114, SWPPP Grading and Stabilization Activities Log Form 25D-110, SWPPP Project Staff Tracking Form 25D-127, and SWPPP Daily Record of Rainfall Form 25D-115.  For active projects update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Storm Water Inspector jointly, unless approved by the Engineer, when:

a.	One of the inspectors is not on site, access is only by air, and weather delayed or canceled flights;

b.	One of the inspectors is sick;

c.	The project is on a reduced frequency inspection schedule with no staff on site, the only access to the site is by air, and it is economical to send only one inspector; or

d.	When the Engineer determines a safety concern that makes joint inspection impracticable.

When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within 3 days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Insert a Complete-by-Date for each corrective action listed that complies with:

a.	Section 641-3.01 (4), and

b.	The CGP.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by the end of the next business day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within 3 days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an amendment memo that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the amendment memo. The issuance of an amendment memo does not relieve the Contractor of liquidated damages that may have been incurred as a result of the error on the original certified inspection report.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

If the Engineer approves and the entire site is stabilized, the frequency of inspections may be reduced to at least one inspection every 30 days.  At actively staffed sites, inspect within 2business days of the end of a storm event that results in a discharge from the site.

When work is suspended due to fall freeze-up, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw. See CGP Part 6.2.3.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Fall Freeze-up and Spring Thaw.

Stabilize Construction Activities within the Project Zone  with appropriate BMPs prior to the anticipated date of fall freeze-up, in accordance with the CGP Part  4.12.

Exceptions to stabilization prior to anticipated date of fall freeze up include:

a.	When stabilization activities are precluded by snow cover or frozen ground conditions prior to the anticipated date of fall freeze up, or

b.	When winter construction activity is authorized by the Engineer and conducted according to the contract.

Stabilize Construction Activities within the Project Zone  with appropriate BMPs prior to spring thaw, as defined in the CGP.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that  any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than 7 days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection; or

b.	Discovery by the Department's or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP,  overdue BMP maintenance, or other reasons listed as corrective actions in 641-3.01.4 must be documented on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log Form 25D-112, with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.  If discovered outside of an inspection, update the log with the date of discovery, the proposed corrective action, and the date the corrective action was completed.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.5.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

13.	Staff Tracking Log.

Use the SWPPP Project Staff Tracking, Form 25D-127, to keep staff records current. Include Records of the AK-CESCL or equivalent qualifications for the Superintendent, SWPPP Manager, ATS operator, any acting Superintendent and acting SWPPP Managers, and beginning and end dates for temporary personnel assignments related to administration of the CGP or Section 641. Update the SWPPP Staff Tracking Log within 24 hours of any changes in personnel, qualifications, or other staffing items related to administration of the CGP or Section 641.

641-3.04 FAILURE TO PERFORM WORK. The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, or SWPPP, that may endanger health or the environment or for failure to perform work related to Section 641.

1.	Non-compliance.

a.	Incidents of Non-compliance. Failure to:

(1)	Obtain appropriate permits before Construction Activities occur;

(2)	Perform SWPPP Administration;

(3)	Perform timely Inspections;

(4)	Update the SWPPP;

(5)	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

(6)	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

(7)	Perform duties according to the requirements of Section 641; or

(8)	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

b.	Notice of non-compliance, either oral or written will include:

(1)	Reason/defects

(2)	Corrective actions required

(3)	Time allowed for completing the corrective action

c.	Levels of Non-compliance and Response correspond with harm to the workers, the public or the environment and whether the harm is:

(1)	Not-imminent, the Engineer will either orally or in writing, or both, provide notice to the Contractor indicating the incident of non-compliance.

Contractor's that take corrective action and complete the action to the satisfaction of the Engineer, within the time specified, may return to the status of compliance, and avoid elevating the response to imminent.

.

(2)	Imminent, the Engineer will orally provide notice to the Contractor of non-compliance and promptly provide written notice to suspend work until corrective action is completed.

Additional actions, taken against the Contract whether the level of non-compliance is Not-imminent or Imminent, may include:

(a)	Withholding monies until corrective action is completed

(b)	Assessing damages or equitable adjustments

(c)	Employing others to perform the corrective action and deduct the cost

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

See Section 109 and as follows:

Item 641(1), and 641(7), are lump sum.

Item 641(5), measured on a contingent sum basis as specified by the Directive authorizing the work.

Item 641(6), measured on a contingent sum basis with withholding determined by the Department.

TABLE 641-1 BMP VALUES - RESERVED

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department to the Contractor, independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2- VERSION C

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Section Number and Description | Deductible Amount in Dollars | Cumulative Deductible Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: (1) 641-2.01.1 Name of SWPPP Preparer (2) Not Applicable (3) 641-3.03.8 Sign and Date SWPPP amendments by qualified person. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | Not Applicable. |  |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to fall freeze-up | $5,000 per Project per year |  |
| E | 641-2.01.1. Failure to conduct pre-construction inspections before Construction Activities on all projects greater than 1 acre. | $2,000 per Project |  |
| F* | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information | $750 per Inspection | Additional $750 for every additional 7 day period without completing the required inspection. |
| G | 641-3.01.4 Corrective action, failure to timely accomplish BMP maintenance and/or repairs. In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day |  |
| H | 641-3.01.3 Failure to provide to the Engineer and DEC a timely oral noncompliance report of violations or for a deficient oral noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and DEC a timely written noncompliance report, use Form 25D-143, of violations or for a deficient written noncompliance report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the requirements of the CGP, approved SWPPP, and Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

*CODE F.	Liquidated Damages according to Code F will not be billed for typographic errors and minor data entry errors, except the liquidated damages will be assessed for these errors when:

a.	the Contractor has previously been notified and subsequent inspection reports repeat the same or similar error,

b.	multiple inspection reports are submitted after the submission due date and the same or similar errors are repeated on multiple overdue reports,

c.	an error in recording the inspector's AK-CESCL certification date results in an inspector performing the inspection during a period when their certification was lapsed or was otherwise invalid

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641(5) Temporary Erosion, Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(6) Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, and CGP are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641(7) SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641(7) appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641(7) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641(1).

Subsidiary Items.  Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

1.	Dewatering;

2.	Shoring;

3.	Bailing;

4.	Permanent seeding;

5.	Installation and removal of temporary work pads;

6.	Temporary accesses;

7.	Temporary drainage pipes and structures;

8.	Diversion channels;

9.	Settling impoundment; and

10.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment and pollution Control Administration	Lump Sum

641(5)	Temporary Erosion, Sediment and Pollution Control by Directive	Contingent Sum

641(6)	Withholding	Contingent Sum

641(7)	SWPPP Manager	Lump Sum

CR641-010120

5.01. Use Pay Item 641(1), (5), (6), (7). Do not use Pay Item (2), (3), (4) unless specifically approved by the Project Manager and Const. Eng.

641(2), (3), & (4) have been removed.

SECTION 642
CONSTRUCTION SURVEYING AND MONUMENTS

Sect 642: CR642.1.2

Related Sect/Sp:

Related Sect/Sp:

Special Provisions

642-2.01 MATERIALS.  Add the following:

4.	Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.ae-traffic.com), or approved equal.

642-3.01 GENERAL.  Add No. 11:

11.	Before work on the project starts, stake and reference the existing centerline on both sides of the roadway alignment.  Stake the existing centerline on tangents at 100 ft, and 50 ft intervals on curves from the beginning and ending of super-elevation changes when the roadway is no longer at normal crown.  Stake sign locations at proper offset.  Stakes shall be a minimum of 1" x 2" x 2'-0" and be offset 4 to 8 ft from the shoulder on both sides of the roadway.  Extend lath stakes a minimum of 2 ft above ground.  Show the offset distance to centerline and the station from the beginning of the project.  Maintain staking until the final roadway striping is completed.  Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor's vehicle.  Calibrate the DMI to roadway alignments as stationed in the Plans before beginning work.  Record the calibration and staking information in the field book.

Install a reference sign every 500 ft.  These reference signs shall meet the following requirements:

1.	mounted with the base a minimum of 5 ft above the shoulder,

2.	located a minimum of 10 ft from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 6 inch high permanent black lettering with a letter proportion height to width ration of 1:0.6 and a stroke width to height ratio of 1:6, on an orange background.

CR642.1-022015

Add No. 12:

12.	Passing Sight Distance. Record the existing centerline striping and final passing sight distance. A copy of the 8 1/2" x 11" Existing Striping, Passing Sight Distance and Final Striping form is included herein. Document the existing passing and sight distance similar to the example included.

Using the "Existing Striping, Passing Sight Distance and Final Striping" form:

a.	Document the existing striping.  Do not disturb the existing striping until the striping record is accepted by the Engineer.

1)	Project Information: Road Name, Stationing, Surveyor & license, Date surveyed.

2)	Col. 1.: Project Stationing in 100-foot intervals from beginning to end of project.

3)	Col. 2.: Posted operating speed per minimum passing sight distance (Table 642-1).

4)	Col. 3a & 4a: Each direction of travel (NB; SB, EB, WB) record the existing striping: passing (dashes) and no passing zones (continuous line) similar to the example. Maintain the orientation of travel to the form, each road, from the beginning of the project to the end of the project.

5)	Col. 6.: Add comments to help clarify the documentation and significant sight obstructions, as needed. Initial your comments.

Submit the form to the Engineer and make changes when directed by the Engineer.

b.	Document the passing sight distance. Use the form approved in a. for b. Measure and record, after the base course layer is complete, passing sight distance along the roadway in both directions of traveled way at 100-foot maximum intervals and referenced to the project station. Use a 3.5-foot object height or instrument height looking ahead to a 3.5-foot target height which is at the centerline or opposing edge of traveled way.

1)	Col. 3 & 4.: Each direction of travel (NB, SB, EB, WB) record the sight distance each station. Record the measurement to the nearest 100-foot up to 1200-foot where the passing sight distance exceeds the minimum passing sight distance. Where the passing sight distance exceeds 1200-foot, record the measurement as "1200+ Feet." Record the measurement to the nearest 10-foot at all stations that fall below the minimum passing sight distance.

2)	Col. 6.: Add comments to help clarify the documentation as needed. Initial your comments.

Submit the form to the Engineer and make changes when directed by the Engineer.

c.	Final Striping. Using the information approved in a. and b., the existing striping and passing sight distance, the Engineer will evaluate the existing striping and provide the final striping plan 14 days after the Contractor's passing sight distance submittal, 12b above.

1)	Col. 3 & 4: Engineer, indicate if the existing striping passes (P) or fails (F).

2)	Col. 5a & 5b: Engineer, indicate the final striping.

3)	Col. 6.: Engineer, add comments if needed to clarify the final striping. Initial your comments.

Do not begin striping until the Engineer returns the form, signed and dated with the final striping plan.

Engineer, provide the Regional Traffic and Safety Engineer an informational copy of the final striping plan.

TABLE 642-1

PASSING SIGHT DISTANCE REQUIREMENTS a

| Posted Speed (mph) | Minimum Passing Sight Distance and Minimum Length of Passing Zone (ft) | Minimum No-Passing Zone on Stopped Approaches to Intersections (ft) |
| --- | --- | --- |
| 30 | 500 | 220 |
| 35 | 550 | 255 |
| 40 | 600 | 295 |
| 45 | 700 | 330 |
| 50 | 800 | 365 |
| 55 | 900 | 405 |
| 60 | 1000 | 440 |
| 65 | 1100 | 480 |
| 70 | 1200 | 515 |

a.	One- and two-direction no-passing zones for one direction of traffic shall be no shorter than 500 feet

642-4.01 METHOD OF MEASUREMENT.  Add the following:

Pay Item 642(16) Passing Sight Distance Measurement.  By the number of stations of the project measured separately along centerline, once for each direction, only after the certified and recorded results (642-3.01 12a & 12b) have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT.  Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

642(16)	Passing Sight Distance Measurement	Station

CR642.2-072215

Existing Striping, Passing Sight Distance and Final Striping

Project Name and Number:  Example Project Striping, X-(XX)/XXXXX

Road Name:  Traveled Way

Stationing:  From   101+00	  To   129+00

Surveyor & License Number:   Name, License #	  Date of Survey:  	mmddyy

| 1. Station (ft.) | 2. Speed/ Req'd Dist. (mph/ft) | SB Travel |  |  | NB Travel |  |  | SB Travel |  | NB Travel |  | 6. Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 3. Sight Dist. (ft) | Existing |  | Striping |  | 4. Sight Dist. (ft) | 5. Final |  | Striping |  |  |
|  |  |  | 3a. | C | L | 4a. |  | 5a. | C | L | 5b. |  |
| 101+00 | 45/700 | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 102+00 | 45/700 | >550 F |  |  |  |  | >400 F |  |  |  |  |  |
| 103+00 | 45/700 | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 104+00 | 45/700 | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 105+00 |  | >600 F |  |  |  |  | >400 F |  |  |  |  |  |
| 106+00 |  | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 107+00 |  | >400 F |  |  |  |  | >500 F |  |  |  |  |  |
| 108+00 |  | >400 F |  |  |  |  | >600 F |  |  |  |  |  |
| 109+00 |  | >400 F |  |  |  |  | >550 F |  |  |  |  |  |
| 110+00 |  | >500 F |  |  |  |  | >500 F |  |  |  |  |  |
| 111+00 | 45/ 700 | >500 F |  |  |  |  | =700 P |  |  |  |  |  |
| 112+00 |  | =700 P |  |  |  |  | =700 P |  |  |  |  |  |
| 113+00 |  | =700 P |  |  |  |  | <800 P |  |  |  |  |  |
| 114+00 |  | <800 P |  |  |  |  | <800 P |  |  |  |  |  |
| 115+00 |  | <800 P |  |  |  |  | <800 P |  |  |  |  |  |
| 116+00 |  | <800 P |  |  |  |  | <900 P |  |  |  |  |  |
| 117+00 |  | <900 P |  |  |  |  | <900 P |  |  |  |  |  |
| 118+00 |  | <1200 P |  |  |  |  | <1000 P |  |  |  |  |  |
| 119+00 |  | <1200+ P |  |  |  |  | <1000 P |  |  |  |  |  |
| 120+00 | 45/700 | " |  |  |  |  | <1000 P |  |  |  |  |  |
| 121+00 | 30/500 | " |  |  |  |  | <1000 P |  |  |  |  |  |
| 122+00 | 30/500 | " |  |  |  |  | <1200 P |  |  |  |  |  |
| 123+00 | 30/500 | " |  |  |  |  | <1200+ P |  |  |  |  |  |
| 124+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 125+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 126+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 127+00 | 30/500 | " |  |  |  |  | " |  |  |  |  |  |
| 128+00 | 60/900 | " |  |  |  |  | " |  |  |  |  |  |
| 129+00 | 60/900 | <1200+ P |  |  |  |  | <1200+ P |  |  |  |  |  |

Existing Striping, Passing Sight Distance and Final Striping

Project Name and Number:

Road Name:

Stationing:  From  	  To

Surveyor & License Number:  	  Date of Survey:

| 1. Station (ft.) | 2. Speed/ Req'd Dist. (mph/ft) | Travel |  |  | Travel |  |  | Travel |  | Travel |  | 6. Comments |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 3. Sight Dist. | Existing |  | Striping |  | 4. Sight Dist. | 5. Final |  | Striping |  |  |
|  |  |  | 3a. | C | L | 4a. |  | 5a. | C | L | 5b. |  |

CR642.2-072215

Existing Striping 12a. – Date Received:

Date Returned:

DOT/PF Engineer

Sight Distance 12b. – Date Received:

Date Returned:

DOT/PF Engineer

Final Striping 12c. – Date Received:

Date Returned:

DOT/PF Engineer

CR642.2-072215

Special Provisions

Replace Section 643 with the following:

SECTION 643
TRAFFIC MAINTENANCE

Sect 643: CR643 replaces SSHC 2017

Related Sect/Sp:  306/CR306; 400/CR409.408.401; 606/CR606.1.2.3.4.6.7.8; 615/CR615; 670/CR670.1; 730/CR730.1, SSP35

Related Sect/Sp:

643-1.01 DESCRIPTION. Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move, and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and traversable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-4 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS. These definitions apply only to Section 643

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which he MUTCD with Alaska Supplement. Comprised of the Manual on Uniform Traffic Control Devices (MUTCD), the Alaska Traffic Manual Supplement, any adopted revisions or interim addenda to either document issued subsequently, and corrections to known errors to either document.

Balloon Light.  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.

Construction Phasing Plan. A plan for each phase of the project showing how to accommodate traffic. Show the sequence of work by segment or phase, if required.

Fixed Objects. Private vehicles, parked flagger vehicles, idle construction equipment, construction material stockpiles, culvert ends, individual trees, power poles, utility poles and appurtenances, and other items deemed by the Engineer to present a hazard to motorists, pedestrians, or bicyclists traveling through the work zone.

Night Work. Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the Table 643-1 below:

TABLE 643-1

PROJECT LOCATIONS – NIGHT TIME ILLUMINATION EXCLUSION

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| South of 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Tok, Delta, Nome |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

Traffic. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

Traffic Control Plan (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

Traffic Control Zone. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the Alaska Sign Design Specification (ASDS). Include longitudinal buffer space for the posted speed limit, according to Table 6C-2 of the ATM unless project conditions or geometric features prohibit including all or a portion of the buffer length.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. All TCPs must include the following information:

1.	Project name and number.

2.	A designated TCP number and name on each page.

3.	For TCPs more than one page, each page must be numbered.

4.	The posted speed limit for each roadway.

5.	Existing striping width, lane width, and road surfacing.

6.	Construction lane widths, striping layout, and temporary pavement marker layout.

7.	Provisions for Pedestrian, Bicycle, and ADA travel through the work zone.

8.	Dates and times the TCP will be in effect and why it is being used.

9.	The Worksite Traffic Supervisor’s signature certifying that all TCPs conform to the ATM and the Contract.

10.	The Project Superintendent’s signature confirming the TCP is compatible with the work plan.

11.	The name(s) of the Worksite Traffic Supervisor, his/her alternate and their 24-hour telephone number(s).

12.	Signs to be used and the ASDS designation number and size.

13.	Location and spacing of all devices and signs.

14.	A plan to address any possible slopes, drop offs, paving joints, or similar temporary features that may occur during use of the TCP.

15.	For TCPs proposed to be used at night, note how the requirements will be met for the required lighting and retroreflective material.

TCPs submitted for approval without all the required information will be rejected. Allow 7 days for review of each TCP submittal. All required modifications to a TCP require a new submission and an additional 7 days for review.

A minor revision to a previously approved TCP during construction requires 48 hours for review and approval by the Engineer.

The TCPs, Plans, and Alaska Standard Plans show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12-foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

1.	Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Temporary Traffic Control Technician, or Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor has a minimum 4000 hours of temporary traffic control work experience, is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

	Temporary traffic control work experience shall demonstrate an understanding of concepts, techniques, and practices in the installation and maintenance of traffic control devices, and skill in reading, interpreting, implementing, and modifying TCPs.

	Temporary traffic control work experience includes: flagging; installing traffic control devices in accordance with TCPs; monitoring traffic control devices and TCP performance; and recognizing and reporting deficiencies in traffic control devices and TCPs for correction.

	Temporary traffic control work experience is gained while serving as a Worksite Traffic Supervisor-in-training, temporary traffic control support personnel, and Flagger.

	Four thousand hours of experience serving solely as a Flagger does not satisfy these requirements.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

2.	Duties.

a.	Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

b.	Physically inspect the condition and position of all traffic control devices used on the project at least twice each day and at approximately 12-hour intervals.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection within 24 hours.  Use Traffic Control Daily Review Form 25D-104.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

e.	Review work areas, equipment storage, and traffic-safety material handling and storage.

f.	Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.

i	Supervise lighting for night work.

3.	Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

1.	Form 25D-124 designating the Worksite Traffic Supervisor, providing the 24-hour telephone number, and certifying minimum 4,000 hours of work experience as described in 643-1.04 Worksite Traffic Supervisor.

2.	A construction-phasing plan for each phase or segment of the project.

3.	TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a traffic control zone.

3.	Road Closure. The closure of a roadway with or without a specified detour route.

4.	One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

a.	Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Contract. For each direction of traffic, equip each 12.5-foot section of barrier with at least two side-mounted retroreflective tabs placed approximately 6 to 8 feet apart, or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use retroreflective sheeting that meets ASTM D4956 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

b.	Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

c.	Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use retroreflective sheeting that meets ASTM D4956 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

11.	Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with self-contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18-inch high characters

b.	Eight character display per message module

c.	Fully programmable message module

d.	Remote control cellular, wireless radio frequency (RF), landline

e.	Waterproof, lockable cover for the controller keyboard

f.	Capacity for electric/hydraulic sign raising or lowering

g.	Radar over speed detection

h.	Variable flash and sequence rates

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable and Mobile Signs, paragraphs 600.10(C)(1) Cords and 600.10(C)(2) Ground-Fault Circuit Interrupter (GFCI). The cord will have integral GFCI protection located in either the attachment plug or 12 inches or less from the plug.

13.	Plastic Safety Fence. Use 4-foot high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 1/2-inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

b.	Do not use unsupported 1-inch plywood longer than 30 inches.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 1/2-inch. Bevel overlap joints so the maximum slope of the overlapping edge is 2 horizontal to 1 vertical.

d.	Fasten so wind and traffic will not displace temporary surfacing.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use retroreflective sheeting that meets ASTM D4956 Type VIII, IX or XI. Use background colors of fluorescent orange on one side and red on the other side.

17.	Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations.

18.	Portable Steel Barriers. Use portable steel barriers that conform to the contract.  For each direction of traffic, equip each section of barrier with side-mounted retroreflective tabs placed approximately 6 to 8 feet apart,   or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier.    Use yellow tabs or stripe when barriers are placed at centerline. Use white tabs or stripe when barriers are placed on the roadway shoulder. Use retroreflective sheeting that meets ASTM D4956 Type III, IV, or V.

19.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-2.02 Crashworthiness. Temporary Work Zone devices, including portable barriers, manufactured after December 31, 2019, must have been successfully tested to the 2016 edition of Manual for Assessing Safety Hardware (MASH). Such devices manufactured on or before this date, and successfully tested to National Cooperative Highway Research Program (NCHRP) Report 350 or the 2009 edition of MASH, may continue to be used throughout their normal service lives.

TABLE 643-2

WORK ZONE TRAFFIC CONTROL DEVICE AND

BARRIER CRASH TESTING COMPLIANCE

| Category | Devices | Devices Manufactured Before Dec. 31, 20191 | Devices Manufactured after Dec. 31, 20191 | Method of Documentation |
| --- | --- | --- | --- | --- |
| 1 | Low-mass single-piece devices w/o attachments; traffic cones, tubular markers, single piece drums, delineators | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Category 1 devices with attachments, barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in Category 1 | NCHRP 350, MASH 2009, OR MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 32, or DOT&PF eligibility determination |
| 3 | Fixed sign supports, truck mounted attenuators, temporary crash cushions, bridge railing, bridge and guardrail transitions, and guardrail and barrier end treatments. | NCHRP 350, MASH 2009, 0R MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 32, or DOT&PF eligibility determination |
|  | Portable Concrete and steel barriers | NCHRP 350, MASH 2009, or MASH 2016 | MASH 2016 | FHWA eligibility letter, if available, at Test Level 3, or DOT&PF eligibility determination, unless otherwise required in the Contract |

1	The Engineer will determine whether a device is in serviceable condition. Serviceable means the device will function equivalent to a new device of the same manufacture.

2	When no test level is specified in a FHWA Eligibility letter; it is implied that the tests were run for Test Level 3.

In Table 643-2, Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices less than or equal to both the weight and height on the schedule below:

Device	Composition	Weight	Height

Cones	Rubber		20 lb.	36 in.

Plastic		20 lb.	48 in.

Candles	Rubber		13 lb.	36 in.

Plastic 		13 lb.	36 in.

Drums	Hi Density Plastic		77 lb.	36 in.

Low Density Plastic	77 lb.	36 in.

Delineators	Plastic or Fiberglass	N/A	48 in.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where the traveling public is redirected or stopped. Organize construction operations so the total of all construction related stoppages experienced by a vehicle traveling through the project does not exceed 20 minutes except when indicated otherwise in the Contract.

Stop equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists. Station a flagger, where construction activity encroaches onto the safe route in a traffic control zone, to assist pedestrians, and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as an employee or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before reducing existing roadway lane and shoulder widths and before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

Edit No. 1 and No. 2, Specified Gravel Surface & Gravel Surface Not Specified, to Project requirements.  Coordinate with the DOT Traffic & Safety Engineers. If not specified gravel, keep 1. and fill in the blanks with NA, including d.

1.	Specified Gravel Surface.  Traffic may be maintained on a continuous gravel surface where specified:

a.					 Highway:  					 weeks.

b.	BOP to Station 					 : No time restriction.

c.	Station 					 to Station 					 (or EOP).

d.	Other project roadways:  1000 ft/5000 … ft, no time restriction.

2.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

If maintaining traffic on an unpaved surface, provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part-width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate the construction activities from one side to the other. Route the traffic over the side opposite the one under construction.

Detour traffic when the Plans or an approved TCP allows. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If two-way traffic cannot be maintained on the existing roadway or detour, use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule the roadway closures to avoid delaying school buses, and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Give notice at least 3 days before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These telephone numbers are used to alert construction employees when emergency vehicles must pass through the project. When notified of emergencies make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator or 511 System for selected projects. Check the special provisions for those requirements.

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP, use flashing warning lights to mark obstructions or hazards and steady-burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with durable material that that fully blocks the view of signal head and will not be damaged or removed by weather.

Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet NCHRP 350 or MASH Test Level 3 unless otherwise noted.crashworthiness requirements of 643-2.02..

All items paid under this Section remain the property of the Contractor, unless noted otherwise in the contract. Remove them after completing the project.

1.	Embankments.  Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

Install portable concrete or steel barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations, and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. When paving lifts are 2 inches or greater and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install: W8-11 (Uneven Lanes), W8-9 (Low Shoulder), W8-17 (Shoulder Drop-Off), W14-3 (No Passing Zone), R4-1 (Do Not Pass), R4-2 (Pass with Care), and W8-1 (Bump) signs as appropriate. Place additional signs every 1500 feet if the section is longer than 1/2 mile.

3.	Fixed Objects And Construction Vehicles And Equipment Working On Or Next To The Traveled Way.  Do not park equipment in medians.  Locate fixed objects at least 30 feet from the edge of traveled way. Fixed objects that exist prior to construction activity are not subject to this requirement unless the proposed temporary traffic routing moves the edge of traveled way closer to the pre-existing fixed object.  Vehicles and other objects within parking lots in urban environments are considered preexisting fixed objects regardless of whether they are or are not present continuously throughout the day.

When worksite restrictions, land features, right of way limitations, environmental restrictions, construction phasing, or other construction conditions allow no practicable location meeting the preceding requirements, the Engineer may approve alternate locations for fixed objects. Alternate locations shall be as far as practicable from the edge of traveled way. When the alternate location provides 15 feet or more separation from the edge of traveled way, the Engineer may verbally approve the alternate location. When the alternate location provides less than 15 feet separation, written approval is required.

When the Engineer determines a fixed object or fixed objects present unacceptable hazard, use drums, or Type II barricades with flashing warning lights, or use portable concrete or steel barriers, or temporary crash cushion to delineate or shield the hazard, as approved by the Engineer.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA

b.	Flagger Certification by ATSSA

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned flagging location at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances.  Keep the flagger’s vehicle well off the roadway and away from the flagging location so the flagger can be easily seen.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When flagging a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

5.	Pilot Cars. You may use pilot cars when part of an approved TCP, if the Engineer determines one-way traffic is necessary, or if the route through the traffic control zone is particularly hazardous, involved, or frequently altered to preclude adequate signing,  Do not use pilot cars to avoid localized traffic control at several locations.  Pilot car operators may not control Automated Flagger Assistance Devices while operating a pilot car.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. Two or more pilot cars may be used to provide two-way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with the company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on all Pilot Cars. Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.  Identify the last vehicle in the column.

When pilot car operations are approved, establish all required pilot car traffic control devices before beginning work.  Continue pilot car operations until no longer necessary and an approved TCP is in place for operations without pilot car, including all required traffic control devices.

6.	Street Sweeping and Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-5, Traffic Control Rate Schedule, Street Sweeping

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface, causing fine particles to rise, and then caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved, surface sucking dirt, dust, and debris into a collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

7.	Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

Obtain an Alaska Department of Natural Resources permit for water removal before taking water from a lake, stream, or other natural water body. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

8.	Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

9.	Truck Mounted Attenuator (TMA.) TMAs are mounted on the rear of work vehicles. Impact attenuators shall meet crashworthiness requirements of 643-2.02. TMAs shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMAs shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the ATM. Do not use a damaged attenuator in the work. Replace any damaged TMA at your expense.

10.	Traffic Control Vehicles.  Use high intensity flashing strobe lights, oscillating beacons, or rotating beacons on the Work Zone Supervisor’s vehicle and on vehicles being used to transport and set-up traffic control devices.  Vehicle hazard warning lights may supplement but are not permitted to be used instead of high intensity flashing strobe lights, oscillating beacons, or rotating beacons.

643-3.05 AUTHORITY OF THE ENGINEER.  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice, and then a written notice according to Subsection 105-1.01, Authority of the Engineer. The notice will state the defect(s), the corrective action(s) required, and the time required to complete the corrective action(s). In no case shall this time exceed 24 hours.  If corrective action(s) are not completed within the specified time, the Engineer may immediately suspend work on the offending operations until the defect(s) are corrected. The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643(23), will be assessed for unauthorized lane closures or reductions. Unauthorized lane reductions will be assessed as one full lane closure, for each lane reduced without authorization.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing.

Unauthorized lane reductions include unacceptable roadway, pedestrian walkway or route, and bicycle route or pathway surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. Failure to install temporary crash cushions or barriers, when required according to the Contract or TCP, is also considered an unauthorized lane reduction. The Engineer will make the sole determination whether unauthorized lane reductions or closures are present.

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-3, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

The rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section. Adjustment rates for unauthorized reduction or closure of each lane of pedestrian walkways or route, and bicycle route or pathway, are the same as for one full roadway lane closure.

TABLE 643-3

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $30 |
| 5,000 + | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month before work is suspended for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the anticipated roadway condition and the work expected to be completed before shutdown. Schedule a field review with the Department for winter maintenance acceptance. At the field review, the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. The contractor is responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. The contractor retains all contractually required maintenance responsibilities until receipt of this letter.

If the contractor suspends work due to unfavorable weather (other than seasonal) or due to failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders. All costs for traffic maintenance during the suspended period will be borne by the Contractor.

When work is resumed, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. The construction sequencing detailed in these provisions, the Special Provisions, and the Plans is suggested only. The Contractor may propose alternative construction sequencing.

Throughout the project, maintain the existing roadway, pedestrian walkway, or route, and bicycle route or pathway configuration (such as the number of lanes and their respective widths) except for restrictions to traffic allowed in the Special Provisions or on the Plans, and addressed through approved TCPs. A restriction to traffic is any roadway surface condition, work operation, or traffic control setup that reduces the number of lanes or impedes traffic. Obtain an approved TCP before restricting traffic.

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below:

Coordinate No. 1 and No. 2 with DOT Traffic & Safety Engineers.  Tailor to Project requirements.

1.	Monday through Friday:  0530 hrs to 0800 hrs and 1630 hrs to 1900 hrs.

2.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs. on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs. on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs. on the Monday after the holiday.

3.	During the Alaska State Fair:  Friday from 1600 hrs. to Sunday 2300 hrs on all streets except Palmer-Wasilla Highway.  Weekend traffic restrictions not allowed on Palmer-Wasilla Highway.

No. 3 is a project specific restriction.  Coordinate w/ DOT Traffic & Safety Engineers.

Lane restrictions, if allowed, conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2640 feet) of traffic detained, allowed for motorists, except school buses.  If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Add 1st or 2nd paragraph below, coordinate w/ DOT Traffic & Safety Engineers.  Delete other paragraph.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, allowed for motorists, except school buses.  If a queue of traffic develops at a stop, empty the entire queue to include the last car that entered the queue at the time the queue was released.

Do not delay the school busses through the construction zone; obtain the local school bus schedule and coordinate work efforts.  Submit the plan, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when placing the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage the construction to avoid routing traffic over conflicting markings, for more than one continuous work shift. If traffic is routed over conflicting markings during a work shift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

Keep 1st paragraph below if using MMA, keep 2nd if using paint.  Delete other paragraph.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

Apply final pavement markings within 10 days of completing the final sweeping or brooming of the mainline seal coat or surface treatment.

643-3.10 LIGHTING FOR NIGHT WORK. Illuminate the night work areas according to Table 643-4.

Table 643-4 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to reduce glare.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to reduce glare to an acceptable level..

TABLE 643-4

NIGHT WORK ILLUMINATION EQUIPMENT AND LOCATION REQUIREMENTS

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least one machine-mounted balloon light of at least 2000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | One balloon light of at least 2000 watts, located within 30 feet of the flagger location. Locate so the flagger and the flagging location are illuminated. Provide additional lights or wattage if necessary to provide complete coverage of the flagging location. |
| Truck Crossings where haul vehicles cross or enter a road with more than 10,000 ADT, or where the haul vehicle crossing or entering location is controlled by portable traffic signals or flaggers | At least one balloon light of at least 2000 watts, located on the main road on the far right side of the intersection. Locate light within 30 feet of the edge of the side street. If there is a flagger at the crossing, locate the lights or lights so the lighting requirements for Flagging are also satisfied. |

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare, the Contractor shall cease all construction activities that require illumination, including flagging operations, until the condition or conditions are corrected.

. codesUse lighting equipment in good operating condition and that complies with applicable state and local adopted codes and standards, and OSHA, NEC, and NEMA requirements..

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position the ground and trailer-mounted towers and trailers, to minimize the risk of being impacted by traffic on the roadway, or by construction traffic, or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights may supplement but do not relieve the Contract requirement to provide lighting for night work, according to the requirements of Table 643-4.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350 or MASH compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004 or ANSI/ISEA 107-2010.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT. Section 109 and as follows: Quantities will not be measured during winter suspension of work.

1.	Traffic Maintenance. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day following receipt of the Notice to Proceed or on the first day of work at the project site, whichever is later, and ends on the date of project completion.

2.	Traffic Control Device Items. By the number of units of each bid item shown on the bid schedule (or the Traffic Control Rate Schedule, if item 643(25), Traffic Control, is included) that are installed, accepted, and operational. Incomplete or unsatisfactory devices will not be measured. Special Construction Signs are measured by the total area of legend-bearing sign panel, as determined under Subsection 615-4.01. Compensation for a 24-hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-5. Items measured by the day are for each item per 24-hour period.

3.	Traffic Maintenance Setup Items. By each lane closure or one-lane road in place per hour. By each detour or road closure in place per 24-hour period.

4.	Portable Concrete Barrier. By each nominal 12.5-foot section placed according to the approved TCPs, for the initial placement and for each subsequent relocation when moved more than 10 feet in any direction. Each transition piece (sloping end) will be measured as a single section.

5.	Temporary Crash Cushion. By each acceptable installation.

6.	Interim Pavement Marking. By the single-stripe station. A single stripe is a marking or a temporary raised pavement marker 4 inches wide. Wider striping is measured in multiples of 4 inches. Centerline gaps are not deducted from measurements.

7.	Flagging and Pilot Car. By the number of approved hours, supported by certified payroll.

8.	Street Sweeping. By the number of operated hours, supported by certified payroll and approved by the Engineer.

9.	Watering. By the 1,000 gallons (M-Gallon) of water applied. The Engineer may specify measurement by weight or volume. If by weight, convert to gallons at 8.34 pounds per gallon. If by volume, convert to gallons at 7.48 gallons per cubic foot.

10.	Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

11.	Traffic Control. By the units specified in the Special Provisions.

12.	Portable Changeable Message Board Sign. By the 24-hour period for each sign, as shown on an approved TCP and displaying an approved message.

13.	Plastic Safety Fence. By the linear foot, as placed, to protect or channelize pedestrian traffic as shown on an approved TCP. Any adjustment in configuration of the fence at the same location that does not result in an increased amount of fence is not measured. Opening and closing the fence to gain access to and from the worksite is not measured.

14.	Temporary Sidewalk Surfacing. By the square yard as shown on an approved TCP.

15.	Temporary Guardrail. By the linear foot, including end treatments, as shown on an approved TCP.

16.	Portable Steel Barrier. By the linear foot placed according to the manufacturer’s recommendation and approved TCPs, for the initial placement, and for each subsequent relocation when moved more than 10 feet in any direction.

17.	Hotline Road Report.  No measurement required to provide a 24-hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.

1.	Traffic Maintenance. The contract price includes all resources required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan, and the maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item also includes any Traffic Control Devices required but not shown on the bid schedule.

Items required by the Contract that are not listed on the bid schedule or not included in other items are subsidiary to Item 643(1) or 643(2) Traffic Maintenance, except the following:

Traffic Price Adjustment

Traffic Maintenance Setup

2.	Traffic Control Device Items. The contract price includes all resources required to provide, install, maintain, move, and remove the specified devices. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

3.	Traffic Maintenance Setup Items. Each setup consists of all traffic control devices, flaggers, pilot cars, and subsidiary items necessary to implement the TCP shown on the Plans. Warning lights, high-level warning devices, vertical panels, and sign supports required for traffic control devices are subsidiary.

Construction and obliteration of temporary roadways, when required on the Plans or approved TCP under a traffic maintenance setup item, is paid for under their respective roadway pay items.

When topsoil or seeding is required for detours, payment will be made under Sections 620 and/or 618.

4.	Portable Concrete Barrier. The contract price includes all resources required to provide, install, maintain, and remove each barrier section.

5.	Temporary Crash Cushion. The contract price includes all resources required to provide, install, maintain, repair, and remove each crash cushion.

6.	Interim Pavement Marking. The contract price includes all resources required to provide, install, maintain, and remove the specified markings. Installation of word and symbol markings are subsidiary. The No-Passing Zone signing, described in Subsection 643-3.04, is subsidiary.

7.	Flagging and Pilot Car. The contract price includes all required labor, vehicles, radios, flagger paddles and pilot car signs, and transportation to and from the worksite.

No. 7, use $58.00 flagger rate for projects advertised after October 22, 2017

The Engineer will pay for Item 643(15A) Flagging on a contingent sum basis at the rate of $58.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

8.	Street Sweeping. The contract price includes all resources required to keep the roadway free of loose material.

9.	Watering. The contract price includes all resources required to provide watering, as directed.

10.	Traffic Price Adjustment. If Item 643(23), Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for unauthorized lane reductions or closures, at the rates listed in Table 643-3.

11.	Traffic Control. Payment for Item 643(25), Traffic Control, will be made at the unit rate value contained in the Traffic Control Rate Schedule shown in the Special Provisions for the accepted units of traffic control devices. The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

12.	Portable Changeable Message Board Sign. The contract price includes all resources required to furnish, move, and operate the sign.

No. 12 requires two PCMBs be shown in the plans.  Confirm two are required.

Two Portable Changeable Message Board Signs used for Permanent Construction Signing paid for under Item 643(3) Permanent Construction Signs.  Additional portable changeable message board signs will be paid for under 643(25), Traffic Control.

13.	Plastic Safety Fence. The contract price includes all resources required to install, maintain, and remove the fence.

14.	Temporary Sidewalk Surfacing. The contract price includes all resources required to construct, maintain, and remove the surfacing.

15.	Temporary Guardrail. The contract price includes all resources required to construct, maintain, and remove the guardrail.

16.	Portable Steel Barrier. The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

17.	Lighting for Night Work.  Payment for illuminating night work areas and any required adjustments to work zone illumination is subsidiary to other items.

No. 18, tailor to Project requirements, delete if not applicable.  Coordinate Pay Item.

18.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401(1).

19.	Temporary Pavement Markings.  Except where specified as an individual Pay Item (Interim Pavement Markings) temporary pavement markings are subsidiary to Section 670 Pay Items. Refer to Section 670 Traffic Markings, for further information.

20.	Temporary Crash Cushion / Redirective.  The price listed in the Traffic Control Rate Schedule, Table 643-5, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Temporary Crash Cushion / Redirective unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations Station or as directed by the Engineer.

Traffic control devices, barriers, and crash cushions required to delineate or shield fixed objects will not be measured or paid for separately, but will be subsidiary

Traffic control devices, barriers, and crash cushions required to delineate or shield guardrail posts or non-crashworthy ends will not be measured or paid for separately, but will be subsidiary, when required for failure to meet completion timelines in subsection 606-3.01.

TABLE 643-5

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $36.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrier (all required per end) | Each | $2500.00 |
| Temporary Crash Cushion / Non-redirective Water Filled Barrels (all required per end) | Each | $3285.00 |
| Temporary Crash Cushion / Non-redirective Sand Filled Barrels (all required per end) | Each | $4325.00 |
| Temporary Crash Cushion / Redirective | Each | $9230.00 |
| Pilot Car (4x2, 1/2 ton truck) | Hour | $72.00 |
| Watering Truck – up to 4900 gallon capacity | M-Gallon | $28.00 |
| Watering Truck – more than 4900 gallon | M-Gallon | $21.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $214.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $162.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(1)	Traffic Maintenance	Calendar Day

643(2)	Traffic Maintenance	Lump Sum

643(3)	Permanent Construction Signs	Lump Sum

643(4)	Construction Sign	Day

643(5)	Type II Barricade	Day

643(6)	Type III Barricade	Day

643(7)	Traffic Cone/Tubular Marker	Day

643(8)	Plastic Safety Fence	Linear Foot

643(9)	Drum	Day

643(10)	Sequential Arrow Panel, Type C	Day

643(11)	Special Construction Signs	Square Foot

643(12)	Portable Concrete Barrier	Each

643(13)	Temporary Crash Cushion	Each

643(14)	Interim Pavement Marking	Station

643(15)	Flagging	Hour

643(16)	Pilot Car	Hour

643(17)	Street Sweeping	Hour

643(18)	Watering	M-Gallon

643(19)	Lane Closure	Hour

643(20)	Detour	Day

643(21)	Road Closure	Day

643(22)	One Lane Road	Hour

643(23)	Traffic Price Adjustment	Contingent Sum

643(24)	Portable Changeable Message Board Sign	Day

643(25)	Traffic Control	Contingent Sum

643(26)	Temporary Sidewalk Surfacing	Square Yard

643(27)	Temporary Guardrail	Linear Foot

643(30)	Portable Steel Barrier	Linear Foot

643(31)	Interim Pavement Marking	LS

643(32)	Flagging	CS

643(33)	Detour	LS

CR643-010120

Pay Items 643(32) Flagging, 643(23) Traffic Price Adjustment, 643(25) Traffic Control:  Typically include in the Engineers Estimate and the Plans (Estimate of Quantity) – together.  Only exclude these items (any or all) if approved by both the Project Construction Engineer and Traffic Control Engineer.

Sect 644: CR644.ATV.CMRA.FOCOM.LAB.LTSUV.UTV_SSHC2015.17

Related Sect/Sp:  Remove the pages before the first section page "Section 644" and the header will realign similar to other sections.

Section 644 Services to Be Furnished By the Contractor

CR644.CMRA:

Notes to Designer and Engineer.

This special is a combination of performance and detail and is intended to be modified to fit the needs of a project.  Included are options to consider when deciding the type of image documentation best suited to the project.  The information provided is an attempt to distill the many specific technical specifications of the materials, to provide background information about the equipment and to help qualify the level of performance required.  Image documentation continues to rapidly change…

Consider the following information when including "Image Documentation" in the project specials and more importantly when modifying the special to fit the unique conditions/needs/requirements of the project.

Code:  CR644CMRA (Documentation by Camera)

644-2.09 Image Documentation. (Digital Image, formerly a photo)

Item numbers match those in the actual special

3.	Ownership of Camera(s) and Accessories.  Consider Department ownership of the camera(s) where construction activity will repeat or where long term documentation may be required.  Possibly monitoring erosion control needs during construction or during winter shutdown etc.  The camera would be reset by the Vendor for each new use.  Service charge would only apply when in use.

4.	Submittal.  If you have a remote site, the submittals should include some of the following information to help judge whether the Vendor is supplying a workable system with proper support, etc.

·	Remote solar monitoring screen displaying the DC amperage output of solar panels (when solar panels are required to power the camera system)

·	Remote battery monitoring screen displaying battery voltage, temperature, and status

·	Remote cellular monitoring screen displaying connectivity, network traffic, and modem temperature

·	Remote wireless radio monitoring screen displaying connectivity, network traffic, and Google Map features or other including wireless radio locations

·	A contract to provide communication connections between a ground antenna and satellite

5.	Materials.

a.	Camera.

General:

·	Typically capture images up to a 1/2 mile away…

·	Typically can count vehicles and identify them…

·	Can be solar powered and portable, as in a trailer with a pole mount, etc.

·	Can be reusable from one project to another

Imager:

·	Imager is from 1 MP to 12 MP plus.  6 MP to 12 MP is common for most companies.

·	Motorized camera would likely be 8 MP to 12 MP.

·	Live video:  6 MP - 12 MP provides a better image for live video stream

·	Live video is typically streamed at 640 x 480.

b.	Online Access, Interface, and Online Software.

Viewing:

·	Typical TV is around one million pixels or 1 MP.

·	Typical computer screen:

	1024 pixels (width) x 768 pixels (height)

	75 pixels per inch (96 and 120 are available)

	Width: 1024/75 = 13.65 inch; height: 768/75 = 10.24 inch. Diagonal: [(13.652 + 10.242)]1/2 = 17 inch

	Pixels per 17 inch computer screen: 1024 x 768 = .786 MP.  This is less than the modern TV.

Ø	The image is sized in the player to show the entire image.

c.	Environmental:

Indoor Camera:

·	Enclosures are usually round with the ability for the camera to pivot, pan-tilt-zoom.

·	Typically provides a low quality image.  The imager pixel count is limited and the enclosure becomes dirty requiring regular cleaning.  Pixel count is approximately 1 MP to 6 MP.

Outdoor Camera:

·	Enclosures are usually rectangular and metal with a thick lens.  The base is motorized providing pan-tilt-zoom or pan-tilt-zoom is achieved inside of a HD image (no physical movement of the camera).

d.	Physical.

Round:

	Round camera housings may not be waterproof.  They normally are plastic, not heated; do not have a blower, and do not have a wiper to keep the field of view clear.  Round is best suited to indoors.  The life of a dome type camera is approximately 2 years.

Rectangular:

	Typically, the housing is rectangular, powder coated aluminum and sealed against moisture intrusion.  The life of a typical sealed camera is approximately 7 years.

	Lid may include a gas spring to facilitate opening.

	Viewing window is typically .25" thick. Remotely controlled washer/wiper helps maintain clear images.

	The weight of the cameras varies from 12 to 20 lbs.  The motorized is heavier than the fixed position camera.

	Not all cameras include an adjustable camera sled.

e.	Power. Vendor will require power to operate the camera; continuous uninterrupted power provided by a utility, generator, or solar source.

	Typical power is 120V AC, 230V AC occasionally required by the Vendor.

	Solar would be DC power.

9.	Documentation.

a.	Type

	Still Image Capture:   can be 5 minutes to 24 hours.  5 to 15 min is common.  Clarity is typically good at 4 - 6 MP and greater.  Can be captured using a fixed position camera or a robotic camera.  Digital image cameras do not take photos, they capture an image, they sample.

	Pan-Tilt-Zoom (PTZ):  Can provide high quality real-time video and stills.  Pan-tilt-zoom can be with a robotic/motorized camera, operable by remote control or by a fixed position camera in a HD image facilitated by the vendor's software.  With the robotic base, the camera can create panoramic images by piecing multiple images together with a resulting imager pixel count equaling the total number of pixels per image capture.  PTZ is generally available on an as needed basis except restricted each side of a scheduled capture and timed out at a predetermined interval.  Cameras with PTZ usually include an imager with 4 MP to 6 MP.

	Time-Lapse:  Video/movie created from stills provided at intervals determined specific to the project, at the end of a milestone or event and at the end of the project.

COSTS:

The relative cost of the camera whether a 4 MP basic fixed position camera or a motorized camera is typically minimal relative to the overall cost of the project.

Digital Image System Costs, 020111

Camera Purchase Price.

General camera types, costs of installation and materials;

General Camera:  	≈ 6 MP @ ≈ $2,700 ranging up to 12 MP @ ≈ $15,000/Each

Camera:  	8 MP @ $5000 - $6000/Each

Monthly Service Charge.

General Service:  	≈ 6 MP @ ≈ $465/Month ranging up to 12 MP @ ≈ $550/Month

Service/Hosting:  	When the camera is not in use, there would not be a hosting costing = $0/Month

Fly-Over Image Capture.  	Image capturing through Google Map ≈ $3000/Month

Remote Site.

Satellite Communication:  wireless 3G

Dish Antenna (communication):  	 $3000

General Install:  	$1500

General Connection:  	 $250

Solar Panels (power):  	(Lower 48 states ≈ $3000) Alaska ≈ $7000

These prices likely do not include the flight from Anchorage to the remote project site…

Recent Quote:  010711

Camera & Accessories:  (2) 6 MP Cameras with remote monitoring system, cellular hardware.  	(2) @ $4500 = $9000

Service: Service for 18 months each.  (20% discount for 18 month prepay Contract)  	(2) @ 18 months @ $392/Month = $14112

Mounting Hardware:  	(2) Included = $0

Time Lapse Video on DVD at completion:  	(2) Included = $0

Solar Unit 1.6 to 2.0:  	(2) @ $3950 = $7900

Total = $31012

Presently one of the suppliers has a camera at the Fairbanks Airport.  It is a round dome type and indoors.

Camera:  	 $2000

Service:  	 Hosting = $500/Month

Review historical bidtab results for further assistance with estimate.

SECTION 644
SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

CR644.FOCOM-010120

644-2.02 FIELD LABORATORY.  Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace Subsection 2.h.(2) and (3) with the following:

(2)	Wiring system to support a 100-amp user load demand with one 50-amp and two 20-amp circuits, all GFI protected

(3)	Outlets, 10 conveniently spaced around the lab, 20 amp capacity, with no more than 5 outlets per circuit, and  consistent with local codes

Add 2.h.(6):

(6)	Outside outlet, 220 volt

Replace Subsection 4.c.(3) with the following:

Wiring system with each circuit GFI protected to satisfy a 60-amp user load demand. Provide three 20-amp circuits each with a 20-amp outlet. Space the outlets around the shed for the users convenience.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

CR644.LAB-010120

Replace Subsection 644-2.03 with the following:

644-2.03 CURING SHED. Furnish and maintain a suitable weather tight shed for curing concrete test cylinders, with a suitable tank(s) for curing concrete test cylinders.

Provide a tank(s) large enough to contain at least 6 each 4”X8” test cylinders from each pour that you propose to make during any 28-day period. Use a tank(s) at least 18 inches high, insulated, and constructed of heavy duty plastic or non-corrosive metal. Construct a lid to provide access to the tank(s).

Provide suitable heating to maintain the temperature in the tank between 70 and 77 °F at all times when curing the test cylinders. In addition, provide suitable thermometers in the shed and tank(s) to check the temperature.

Provide a supply of calcium hydroxide (high-calcium hydrated lime) sufficient to maintain a fully saturated water bath in the tank(s).  Provide a source of potable water.

Provide electrical service and equipment for:

1.	Heating/Cooling adequate to maintain temperatures between 70 F to 77 F

2.	Two 100-watt incandescent or four 40-watt fluorescent, or equivalent LED fixtures.

3.	One combination smoke alarm and carbon monoxide detector.

SSHC2020.

644-2.05 VEHICLES.  Delete the second and third paragraphs and substitute the following:

Pickup(LT)/Sport Utility Vehicle (SUV):  Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s).  Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer.  Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equal equipment shall have the following characteristics:

	(4) 55 watt rotators with amber filters

	1200 flashes per minute

	(2) diamond mirrors

	55 inches in length

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The Department is responsible for damage to any vehicle caused by its own negligent operation.

CR644.LTSUV-022015_SSHC2015.17

Add the following:

All-Terrain Vehicle (ATV):  Provide a 4x4 all-terrain vehicle (ATV), 300 cc minimum, with a 500 lb capacity trailer.  The ATV must be less than three model years old and in good condition.  Equip, with a set of portable two-way radios with a secure transport anchor/holder and a vertically extended rotating beacon or strobe light.  All vehicle requirements for fuel, oil, maintenance, and insurance apply to the ATV.  Submit the ATV and accessory specifications including photos of the exterior to the Engineer and receive approval prior to providing the vehicle for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

CR644.ATV-022015_SSHC2015.17

Add the following:

Utility Vehicle (UTV).

Model Year	Three or less model years old

Good Condition

Body:	All original parts, straight, no rust, broken plastic or fiberglass, minor dings, chips, working head and tail lights

Frame:	Original factory condition, (Includes roll cage and bumpers)

Mechanical & Elec	Condition would not preclude manufacture warranty coverage

(actual warranty coverage is not required)

Tires/Rims	All purpose tires, less than 1/3 tread wear, straight rims

Seating	Side-by-side, buckets or bench, 2 person seating

Engine & Electrical

Type		4-cycle gas, liquid cooled, electronic fuel injection

Displacement	450 cc minimum, 20 hp minimum

Fuel Capacity	6 gallons, minimum

Ignition Type	Solid state 12V – electronic, keyed

Drive System

4WD	On-demand true four-wheel drive system

Front/Rear Differential	Auto-locking, 4 wheel shaft drive

Transmission	Automatic, dual range forward/reverse

Transaxle	Two speed

Brakes	Front/rear hydraulic disk

Park Brake	Mechanical, hand operated

Suspension

Front	Independent with Struts

Rear	Independent with coil over shock

Occupant Protective Sys (OPS)	Tubular overhead structure, passenger grab handles

Seat Belts	3-point seat belts

Certification	ROPS standards (Rollover Protective Structure)

All Weather Cab	Enclosed with hard top, storage glove box

Sound Rating@ Op Ear	87-90 dB

Tires	Dia. 25x, 14 psi max (fully loaded), all purpose

Wheelbase/Tread Centers	1.75 maximum, 12 inch min ground clearance

Towing Capacity	1300 lb, include hitch, ball mount and ball

Payload Capacity	1400 lbs

Cargo Box	Steel, 43L x 46W x 9D, 10 cu ft, 400 lb min, hinged tailgate,

cargo restraint system

Safety Lights	Safety Lights	Vertically extended operable rotating amber beacon or

strobe light.  SAE Spec. Class 1 or 2, J845 – 360 Rotating Lights or J1318 Flashing Strobe Lights.  Mount beacon to be visible at eye level at all times inside a 60 ft radius about the equipment, day or night.

Manufacturers:	Whelen Engineering Company,	Public Safety Equipment (PSE),

Federal Signal,	Or Approved Equal

UTV(s) meeting these specifications include, but are not limited to:

Polaris	Ranger 4x4	Kawasaki	Mule 4010 4x4

Honda	Big Red	John Deere	Gator HPX 4x4, or

Yamaha	Rhino 700	Approved Equal

Typical vehicle requirements including but not limited to: fuel, preventative maintenance, maintenance, and insurance apply to the UTV.

Submittal:  Submit the UTV vehicle and accessory specifications including photos of the UTV to the Engineer and receive approval prior to providing the vehicle for use.

CR644.UTV-022015_SSHC2015.17

Add the following subsection:

644-2.08 ENGINEERING COMMUNICATION.  Engineering Communications, minimum service includes:

a.	Three phone/facsimile lines and commercial phones (different phone numbers for each line)

(1)	One phone with built-in digital answering machine.

(2) Ancillary equipment for operational service and as required by the Engineer.

b.	High speed internet service with modem (DSL or Cable)

(1)	Send and receive capability supporting 1.0 Mbps download speed or higher and 0.5 Mbps upload speed at all times.

(2)	Data usage, 10 GB minimum monthly.

(3)	Wireless router.

(4)	Battery backup.

(5)	Ancillary equipment for operational service and as required by the Engineer.

CR644.FOCOM-010120

Add the following subsection:

644-2.09 IMAGE DOCUMENTATION.  Provide secure "digital image" (image) documentation of construction activity at the project site(s); inclusive of an integrated, professional-grade, high resolution digital webcam image system designed for the construction industry with camera(s) and related hardware, support structure, mounting equipment, software, data transmission service, website hosting, image hosting, storage/archiving and online interface for the system with technical support and as further defined herein.

IMAGE DOCUMENTATION. Designer, it is important that the image documentation, including the camera(s), is coordinated with the construction engineer and bridge engineer (if bridge related). All parties must understand what is required and ensure that the specification matches the project requirements. Construction understanding the specification, the requirements, will reduce the chance of approving unsatisfactory proposed work and materials.

1.	Period of Service.  Begin Image Documentation one week before construction begins through one week after project completion.

1.  Tailor the start & end times to each project. Consider need during winter shutdown.

2.	Ownership of Image Documentation.  All images are the copyright of the Department including still images and time-lapse movies.  The Contractor and Vendor may not use the image documentation without the written approval of the Department.

3.	Ownership of Camera(s) and Accessories.  The camera(s) is the property of the Contractor.

3.  If Dept ownership is desired, change the 1st sentence.  See "Notes to Designer and Engineer."

4.	Submittals.  Provide complete submittals (3 printed copies), to the Engineer for review and approval, at least 21 days before beginning Construction activity.  Submittals will be returned to the Contractor, within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.

Include the following:

a.	Shop Drawings.  Submit a key plan of the project site and construction to be documented with vantage points marked for location and direction of each camera. Coordinate layout and installation of cameras to avoid interference from site line obstructions such as trees and to prevent sunlight and light from fixtures entering directly into the camera lens.  Indicate camera mounting heights relative to ground and the construction being documented.  Include mounting structure, if required, and mount.

Approximate location of the camera(s) is provided in the Plans (plan and profile sheets coordinated with the summary sheets).  Coordinate with the Engineer the actual location(s) (plan and elevation) to capture the specified construction activity.

b.	Data Sheets and Certificates:  Submit the technical data sheets and certificates for materials including equipment and software.

c.	Maintenance:  Submit maintenance requirements with a schedule and service instructions.

d.	Qualifications:  Submit:

·	Technical Representative’s Resume:  name, education, training, and two years minimum experience providing same or similar service.  Include names of individuals and contact information for verification of service.

·	Vendor Qualifications:  Name and qualifications including five years minimum experience providing completed successful same service.  Include names of projects, project descriptions and contact information for individuals able to verify service.

5.	Materials.

a.	Camera.  Provide 	#	 camera(s) with specifications similar to those listed below with equivalent to or better performance. Provide pan-tilt-zoom for all cameras.

5a.  Camera.  Replace # with the overall number of cameras required. All cameras are PTZ as noted in the last sentence in 5a.

CAMERA SPECIFICATIONS

5a.  Camera Specification.  Indicate number (#) of cameras for each type.  When a camera(s) is not used, delete the col.

|  |  | Camera(s) |  |
| --- | --- | --- | --- |
|  | # | # | # |
| Features |  |  |  |
| Imager: | 6 Megapixels, minimum | 12 Megapixels, minimum | 8 Megapixels, minimum |
| Lens: |  |  |  |
| F-Stop | f/3.5 - f/5.6 | f/3.5 - f/5.6 | f/2.7 - f/3.5 |
| Zoom: | 18 mm - 55 mm | 18 mm - 55 mm | Motorized 6 mm - 72 mm |
| Optical: | 3x min. | 3x min. | 12x min. |
| Digital: | - | - | 4x min. |
| Resolution: (minimum) 5a. Panoramic: Requires a robotic base. Remove the panoramic specification below if the base is fixed. |  |  |  |
| Stills: | 3088 x 2056 | 4288 x 2848 | 3264 x 2448 |
| Panoramic: | - | - | 29376 x 9792 (288 MP) |
| Streaming Video: | 640 x 480 | 640 x 480 | 640 x 480 |
| Angle of View: | Cover intended site area |  |  |
| Auto Features: | ISO, shutter, white balance, and focus |  |  |
| Compression: | JPEG, Motion JPEG |  |  |
| Communication: |  |  |  |
| IP Addressing: | Dynamic or Static |  |  |
| Types: | Provide stable communication, by one or more of the following types, dependent on the availability with the order of precedence as follows: 1. Wired Broadband (10Base-T/100Base-TX) 2. Wireless (802.11n) 3. Cellular (3G min) 4. Satellite Broadband |  |  |
| Base: |  |  |  |
| Fixed Position a: | Yes/NA | Yes/NA | Yes/NA |
| Operable Motorized/robotic: | Yes/NA | Yes/NA | Yes/NA |
|  | Pan range: 360° continuous, Tilt range: level + 30° to -90°. Adjust as required to meet the documentation requirements. |  |  |

a.	Fixed Position: Pan-tilt-zoom control is within a high-definition image.

5a. Base:  in the Fixed Position row and the Operable Motorized/robotic row indicate "Yes" or "NA."

b.	Online Access, Interface, and Online Software.  Contractor's System Vendor shall provide an online based interface and online software as managed service to allow the viewing of all still images captured and stored/archived during construction, from any location with internet access using a PC computer and/or cellular device.  The Department will not be required to own specific software or operating equipment proprietary to the system vendor to utilize any part of the Vendors service.

1)	Solution Service:  provide solution service, including technical corrective service, continuous 24 hrs, 7 days a week during period of service.

2)	Machine to machine automated maintenance of the camera system providing continual operation without interruption.

3)	Communication:

a)	Broadband/High-Speed connection (1.5 Mbps)

b)	Wi-Fi G or N // 3G cellular connection

4)	Accessibility:  Vendor, provide a web page linked to the Department's Central Region web page;

"Alaska DOT & PF Project Information",

http://dot.alaska.gov/creg/project_info/,

5b.4)  Web page may change over time, adjust to current location, and verify each project. Add the "Project Name" web page two places.

5b.4) cont.	Start the project web page during design.  The Engineer will be reqd to start the web page if design does not.

"Central Region Projects", 		Project Name	.

Add the link to the 		Project Name	 web page through the Engineer.  The Engineer will coordinate with the Central Region Web Manager.

5b.4) cont.	The project web page should be a Dept page. If a consultant creates an information page, link it from the Dept project page.

a)	Public:  Provide the public with viewing access of still image documentation.

b)	Department:  Provide the Department with viewing access of the still images and live video as specified in 6) User Screen Viewing.

5)	System Navigation:  Calendar based.

6)	User Screen Viewing:  Display the Project Name and Number; Owner and Contractor Logo.  Multifunction image browsing (still images, multiple images, online time-lapse movies) per individual camera and between multiple cameras.  Additional viewing requirements include:

Public and Department.

·	Images: include time and date.

·	Navigation: calendar to navigate between documentation.

·	Weather Data:  graphical display of local weather data including long term forecast (4-7 day forecast including, sun, overcast, rain, snow, wind speed, temperature, high and low pressure systems and others).

·	Full-Screen:  screen maximizing view of images on users monitor.

·	Multiview Screen:  instant view/image of past days, weeks, months, or years at one time.

Public and Department.  Include any, all, or none of the following bulleted items.  Each is generally available.

·	Time-lapse movies:  not real-time video.

·	Split Screen:  Instant play back, two or more discreet images side by side from one or more cameras.

·	Share Image Tools:  save, print, email, and post to message board or, mobile devices.

·	Map:  aerial and satellite view by Google or other.

Department Only.  Provide password protection for Department only viewing.

Department Only.  The bulleted items not included in the Public and Department above and the Department Only bullets below:  include any, all, or none of the following bulleted items.  Each is generally available.

·	Pan-tilt-zoom control within a high-definition image (fixed base) or by operable motorized/robotic base. Refer to the "Camera Specifications" table for the base.

·	Real-Time Image Browsing/Viewing:  view images and video from all cameras in the same display at the same time by day, week, year, and event.

·	Overlays:  graphical mark-up tools for detailing and creating overlays from multiple discrete images.

·	Automated progress reports: Power Point, Open Office, and PDF formats.

c.	Environmental.  Camera and supporting equipment shall be designed for continual operation in all weather conditions relative to the project site, 24 hrs each day, each day of the week.  Weather conditions including but not limited to:

1)	Wet:  water proof.

2)	Operational Temperatures:  		-50˚F to +120˚F		 (thermostatically controlled heater and blower or other as required).

5c.2)  Temperatures from -10˚F to -50˚F are generally available.  Match temp. to the site.

3)	Winds:  110 mph (3sec gust)

4)	Fugitive Materials:  dust, rain, snow and similar.

d.	Physical.  Designed and constructed for the conditions existing at the project site.

1)	Housing:  impact resistant, water proof enclosure constructed of aluminum with stainless steel fittings and UL rated compression glands.

a)	Adjustability:  adjustable camera sled.

b)	Operational Options:  (See camera specifications for actual)

·	Fixed (pan-tilt-zoom in high-definition image provided by software interface)

·	Operable remotely controlled (pan-tilt-zoom)

2)	Viewing Window:  impact resistant with remotely controlled washer/wiper.

5d.2). See "Notes to Designer and Engineer."

3)	Security:  protect against vandalism.  Lockable housing secured in-place to prevent unauthorized removal from project site.

5d.3). Lockable housing is common.

e.	Power.  Provide continuous uninterrupted power as required by the Vendor to operate and maintain the image documentation system.

5e. See "Notes to Designer and Engineer."

6.	Vendors.  Vendors that may meet the requirements specified in this subsection include, but are not limited to the following:

| EarthCam, Inc. 84 Kennedy Street, Hackensack, NJ 07601 Ph: 800.327.8422 Ph: 201.488.1111 Fax: 201.488.1119 www.EarthCam.net | OxBlue Corporation 814 Bellemeade Ave. NW Atlanta, GA 30318 Ph: 888.849.2583 Ph: 404.917.0200 Fax: 404.917.0201 www.OxBlue.com | Work Zone CAM, LLC 331 W 57th St, Suite 310 New York, NY 10019 Ph: 877.966.3101 www.Workzonecam.com |
| --- | --- | --- |

7.	Security.  Provide security for the image documentation and documentation system.  Prevent; interruption of the continuous documentation, damage to the documentation (data corruption, theft, or loss of the data), and damage to the system (the physical equipment, interface, software, data collection, and storage).

Maintain all images on System Vendor owned and operated secure and redundant servers, in a secure area at a location owned by the Vendor.  Minimum levels of security include multiple levels of password protection, IP address block/permission and SSL protection of the user login password.

8.  Adjust the number of camera moves if you believe more than 1 move is required between beginning construction to project completion.

8.	Installation and Maintenance.  Provide initial installation by the Vendor, or other as approved by the Vendor, with the option to move the camera(s) 1 times(s); and maintain the system throughout the period of service without interruption except as may be specified in this specification.  Damaged or failed parts and service complications, resulting in documentation interruption, are to be repaired, replaced, and resolved within 48 hrs from the time of interruption.

Training:  provide training for the Engineer's staff in the use of the image documentation system as described in 5.b.6) and as applicable.  Schedule the training, coordinated with the Engineer, directly after the installation is completed and the system is operational.

9.	Documentation.  Throughout the Period of Service, during the day and night, document the construction activity.  Approximate times are included herein; the approximate location of the camera(s) is provided in the Plans (plan and profile sheets coordinated with the summary sheets).  Coordinate with the Engineer, adjusting the times of documentation and actual location(s) (plan and elevation) to capture the specified activity.

For all image documentation, include the project name and number with the date and time.  The date and time for a still image would be at the time of capture and for a time-lapse movie the time from start to finish of the movie.

a.	Type.

1)	Still Image Capture.  Capture still image at regular intervals.  	Intervals = 15 minutes.

9a.1)  Intervals may be 5 min. to 24 hrs - adjust to project needs, coordinate with construction.  An interval between 5 min. and 15 min. is fairly common.

2)	Pan-Tilt-Zoom.  Real-time video and stills with high-definition image.  Available on an as-needed basis, except restricted to periods each side of the scheduled still image capture and timed out after a predetermined set time coordinated with the Engineer.

3)	Time-Lapse.  Create time-lapse movies during the Period of Service as directed by the Engineer and as follows:

Regular Interval.	Time-Lapse Movie Interval = End of Each Month.

9a.3)  Examples provided below are for consideration, tailor intervals, seasons, milestones and events to the project, keep applicable items, use listed, add new, modify or delete those not applicable, discuss with the Engineer.

Seasons.

9a.3)  Consider leaving the camera in place to monitor erosion, sediment, and pollution.

	Construction season

	Winter shut-down

Milestones and Events.

·	BMP(s)

Ø	Installation:  permanent and temporary

Ø	Removal:  temporary

·	Bridge Work

9a.3)  New, modifications, maintenance, demolition.  Fill in the bridge number and name as applicable.

	Bridge abutments

	Bridge substructure or superstructure

| Bridge Number | Bridge Name |
| --- | --- |

·	Clearing and grubbing

·	Culvert construction and installation

·	Detours

·	Erosion, Sediment and Pollution Control - Monitoring:

Ø	Beginning of construction season

Ø	During active construction

Ø	Winter shutdown

Ø	Spring thaw

Ø	Storm Event:  before, during, after

·	Establishment Period:  start of, during, at end

·	Excavation - general

·	Excavation - 	Specific Event

·	Guardrail installation

·	Headwall construction

·	Lighting installation - general lighting

·	Lighting installation - hightower lighting

·	Paving

·	Pile driving

·	Signal(s):  installation, modification, removal

·	Striping

·

9a.3)  others as may be applicable to specific projects

Period of Service.  At the end of the Period of Service, create a time-lapse movie of the construction activity(s) from the beginning of service to the end of service.

10.	Removal.  Remove the complete documentation system after completion of the service period.  The Engineer may direct the system to be removed prior to the end of the service period.

11.	Deliverables.  Provide the Engineer with (2) DVDs (2 copies) of:

a.	Stills:  as originally recorded in the digital camera, without alteration, manipulation, editing, or modifications, in compressed JPEG format, no more than 7 days after the service period ends.

b.	Time Lapse-Movies: in compressed motion JPEG format, no more than 7 days after each interval, season change, milestone, event, and the Period of Service specified in 9) "Documentation."

CR644.CMRA-020118_SSHC2015.17

644-4.01 METHOD OF MEASUREMENT. Delete the third paragraph and substitute the following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644.LTSUV-022015_SSHC2015.17

Delete the third paragraph and substitute the following:

Vehicle (ATV).  For each vehicle provided.  If a replacement vehicle is necessary, no additional measurement will be made.

CR644.ATV-022015_SSHC2015.17

Delete the third paragraph and substitute the following:

Vehicle (UTV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644.UTV-022015_SSHC2015.17

Add the following:

Image Documentation.  No additional measurement will be made if any part of the documentation system requires replacement.

CR644.CMRA-020118_SSHC2015.17

644-5.01 BASIS OF PAYMENT.  Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644(2) Field Laboratory.

CR644.LAB-010120

Add the following:

Pay Item 644(8) Vehicle (LT/SUV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle (LT/SUV)	Each

CR644.LTSUV-022015_SSHC2015.17

Add the following:

Pay Item 644(9A) Vehicle (ATV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(9A)	Vehicle (ATV)	Each

CR644.ATV-022015_SSHC2015.17

Add the following:

Pay Item 644(9B) Vehicle (UTV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(9B)	Vehicle (UTV)	Each

CR644.UTV-022015_SSHC2015.17

Add the following:

Pay Item 644(10) Engineering Communications.  Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644(1) Field Office and as such are paid by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(10)	Engineering Communications	Contingent Sum

CR644.FOCOM-010120

Add the following:

Pay Item 644(17) Image Documentation.  At the Contract lump sum price to include labor, equipment, materials, fees, and service specified.  The lump sum price is inclusive of all cameras specified in Subsection 644-2.09.

Lump Sum Items.  Payment for lump sum items will be made as follows:

1.	A percentage of the Contract lump sum amount, to be determined by the Engineer, will be paid as full compensation for a complete, properly functioning, image documentation system including site installation(s), power, camera(s), and operating system(s), with automatic archiving, set up and interfaced with internet access via the specified device(s).

2.	The balance of the Contract lump sum amount will be prorated over the anticipated active construction Period of Service with a portion included as part of each interim payment, for maintenance, repairs, utilities, fees and for removing the complete documentation system from the site with the final payment being made after all deliverables are received as specified.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(17)	Image Documentation	Lump Sum

CR644.CMRA-020118_SSHC2015.17

Special Provision

S39. Include if Any FED funds.  Submit certification estimate to Construction's David Lee for number of apprentices/trainees and number of hours.  If "0" trainees are required leave out of specials, estimate of quantities and engineer's estimate. Exclude if SOA Only funds.

S99. Include if project has any federal funding.  Submit certification estimate to Construction's Mike Cray for number of apprentices/trainees and number of hours.  If "0" trainees are required leave out of specials, estimate of quantities and engineer's estimate.

Add the following Section:

SECTION 645
TRAINING PROGRAM

Sect 645:  Section Specials: SSP39.

Related Sect/Sp:

645-1.01 DESCRIPTION. This Statewide Special Provision for on-the-job training (OJT) implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301.

645-3.01 General. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Office of Apprenticeship (USDOL/OA); or one developed by the Contractor using Form 25A-310 and approved prior to contract award by the OJT Coordinator in the DOT&PF Civil Rights Office.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/OA apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/OA training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311 may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown in the Bid Schedule and approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown in the Bid Schedule and approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program,     Trainees/Apprentices	Labor Hour

SSP-39-010116

SECTION 646
CPM SCHEDULING

Sect 646:  CR646.1 (CR646.1 rplcd CR261)

Related Sect/Sp:  108/CR108.3; 658

CR6461. Include CR652-1.03 when using CR646.1.

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete No. 2.

2.	60-Day Preliminary Schedule.

Delete the first sentence of No. 3. Schedule Updates.  and substitute the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR646.1-070214

Special Provisions

This special is typically not permitted in projects with ARRA funding.  Confirm use in other federally funded projects.

This special is typically not permitted in projects with ARRA funding.  Confirm use in other federally funded projects.

Add the following Section:

SECTION 647
EQUIPMENT RENTAL

Sect 647:  CR647 (CR647 Rplcd CR15)

Related Sect/Sp: For use where miscellaneous equipment not part of typical construction may be required. Additional work or similar … commonly added.

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled, and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. Section 109.

Hourly Rental Rate: Includes the equipment rate plus the operating costs including: furnishing, travel time, operating, maintaining/servicing and repairing the equipment along with the costs incidental to the equipment and its' operation.

647-5.01 BASIS OF PAYMENT. Payment is for the time that fully operational equipment is engaged in the performance of the work directed by the Engineer. Time not payed for includes: idle periods, maintaining/servicing and repairing the equipment, making change-overs of equipment parts, and time to travel to and from the project.  Payment will only be for time supported by certified payroll.

Attain hourly rates from the Rental Rate Blue Book, by EquipmentWatch, Penton Media Inc. See 109-1.05 3a. Construction has access.

Furnishing and operating equipment that is heavier, has larger capacity, or greater power than specified will not entitle the Contractor to extra compensation.

Pay Item 647(1) Wide Pad Dozer, 65 hp min: payed at the rate of $0/hour.

Pay Item 647(5) Backhoe, 4WD, 1 cy Bucket, 75 hp min, 15 ft Depth: payed at the rate of $0/hour.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 hp Min	Contingent Sum

647(5)	Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth	Contingent Sum

CR647-110316

Special Provision

Add the following Section:

SECTION 651
CONTROL OF WORK – SUPPLEMENTAL REQUIREMENTS

Sect 651: CR651_SSHC2015.17, CR651. SSP9 Replaced by CR651.

Related Sect/Sp; SNtB, 105, 108, CR652

651-1.01 DESCRIPTION. Supplemental requirements for Section 105, Control of Work.

651-1.02 RELATED SECTIONS. Section 105, Control of Work

651-1.03 was a provision in Section 105. 105-1.06 Utilities; has been moved, with minor changes, here.

651-1.03 UTILITIES.  Request locates from the utilities having facilities in the area.

Use the Alaska Digline, Inc. "Locate Call Center" for the following utilities.

ALASKA DIGLINE, INC. Delete from the list below, companies not applicable to the project.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: Aircraft Service International Group (ASIG) Alaska Communications Systems (ACS) Alaska Fiber Star (WCI) Alaska Native Medical Center (ANMC) Alaska Railroad Corporation (ARRC) Anchorage School District (ASD) Anchorage Water & Wastewater Utility (AWWU) Arctic Slope Telephone Assoc. (ASTAC) AT & T Alascom (AT&T) Chevron-Union Oil of California (UNOCAL) Chugach Electric Association (CEA) City of Homer (HPW) City of Valdez Public Works (COV) City of Wasilla (CWPW) ConocoPhillips Alaska, Inc. (CPA) Cook Inlet Pipeline Co. (CIPC) Copper Valley Electric Assoc. (CVE) Copper Valley Telephone Coop. (CVTC) Doyon Utilities, LLC. (DOYON) ENSTAR Natural Gas (ENS) Fairbanks Natural Gas (FNG) Flint Hills Resources (FHR) General Communications, Inc. (GCI) Homer Electric Association (HEA) Kodiak Electric Association (KEA) Marathon Oil Company (MOC) Marathon Pipe Line LLC. (MARATHN) Matanuska Electric Association (MEA) Matanuska Telephone Association (MTA) Municipality of Anchorage Signal & Street Maint. Municipal Light & Power (ML&P) Northern Utility services (NUS) State of AK, DOT/PF Anchorage Street Lights (DOT) Ted Stevens International Airport (TSAIA) Telalaska Inc. (Interior Phone, Eyecom TV & Mukluk Telecom) Tesoro Alaska (TESORO) United Utilities, Inc. (UNITED) XTO Energy (XTO)

State Facility Utilities: before beginning work, contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the District Superintendent's phone number where the project is located, and request locates.

Always include the statement below, requiring the Contractor to call the Central Region Maintenance & Operations Office.

Call the following utilities and agencies directly:

Add utilities and agencies as needed below. Remove the below statement if no additional utilities or agencies added.

Utilities Relocated by Others.

Utility work by others includes relocation work done by utility companies, not the Contractor

	If Utilities are doing work concurrent with project construction include the 1st paragraph. "Utilities will be relocated …"

	If Utility work is not anticipated concurrent with project construction and you wish to include subtopic "Utilities Relocated by Others." Include the 2nd paragraph. Utility work is not anticipated …"

	If Utility work is not part of this project, Delete "Utilities Relocated by Others." thru "Work done by utility owner(s) is as follows:" Keeping Subsection 1.04.

Utilities will be relocated by others concurrently with construction of this project. The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

Utility work is not anticipated for this project, however; if utility work is added to the project the Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

For utilities being relocated, the Contractor will:

1.	include utility work on the Construction Phasing Plan and Progress Schedule;

Add/delete items 1-9 (below) that the Contractor is responsible for relative to utility work by others. Delete items not applicable.

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information;

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing;

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance;

5	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

8.	provide bedding and backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

8.  This does not apply to AWWU, they provide their own backfill.

9.	coordinate with the utility owner(s) and provide potholing services at the locations identified or as directed by the Engineer. Payment will be made under Section 682, Utility Potholing.

9.  Include as needed, slope staking, and potholing, in work done by Utility owners.

Work done by utility owner(s) is as follows:

Fill in utilities information as applicable.

651-1.04 COOPERATION BETWEEN CONTRACTORS.  The following state owned projects may be under construction concurrently with this project.

651-1.04  was a provision in Section 105. 105-1.07 Cooperation between Contractors, it has been moved here.

Add projects that may be ongoing in the same area.

| Project Name: | Project No.: |
| --- | --- |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

651-1.05 was a provision in Section 105. 105-1.19 Interim Completion; it has been moved here.  The following is an Example only.

651-1.05 INTERIM COMPLETION.  This project includes one interim completion phase.

When including 651-1.05 include SNtB Interim Completion Date and CR652-1.04.

Interim Completion Phase:

Date:	30 September, 2009

Work:	Complete all centerline rumble strip installations and replacement of centerline striping in centerline rumble strip installation locations by the interim completion date.

Final Completion Phase:

Date:	See the Invitation to Bid for the final completion date.

Work:	All remaining work in the Contract.

CR651-020118R_SSHC2015.17

The following instructions are the same as occur in Section 105.

Section 105 Control of Work, and Section 651 Control of Work – Supplemental Requirements

	There are no Standard Modifications or Statewide Special Provisions for Sections 105 and 651.

	Provisions intended for Section 105, except CR105.5 and CR105.7, are placed in Section 651 as noted below.

Region and Project Provisions

You will always include the Central Region special provision CR105.7. This provision is outside the instruction that follows.

1.	If you do have region or project provisions for Section 105/Section 651, proceed to Step 2 (nearly always), otherwise you are now done with Section 105 and Section 651.

2.	If you do have project provisions for Section 105 that modify Section 105, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 105 proceed to Step 3 (nearly always), otherwise you are now done with Section 105 and 651.

3.	If you do have region provisions that modify or add to Section 105, or project provisions for Section 105 that add to Section 105, include CR105.5 and CR651 as follows:

a.	In Section 105 include CR105.5

b.	In Section 651, CR651:

(1)	Region provisions identified by subsection:

(a)	651-1.01 Description (always include)

(b)	651-1.02 Related Sections (always include)

(c)	651-1.03 Utilities (include when applicable)

(d)	651-1.04 Cooperation Between Contractors (include when applicable)

(e)	651-1.05 Interim Completion (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	651-1.01 – 1.05 add to or modifying region provisions

(b)	651-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.

Special Provisions

Review comments/instructions below at end of provisions.

Replace Section 652 with the following:

SECTION 652
PROSECUTION AND PROGRESS – SUPPLEMENTAL REQUIREMENTS

Sect 652, Section Specials: CR652.1. SSP10 Replaced by CR652.

Related Sect/Sp:  SNtB, 105, 108, 651

652-1.01 DESCRIPTION.  Supplemental requirements for Section 108. Prosecution and Progress.

652-1.02 RELATED SECTIONS.  Section 108, Prosecution and Progress.

652-1.03 was a provision in Section 108. 108-1.03 Prosecution and Progress; has been moved, with minor changes, here.

652-1.03 PROSECUTION AND PROGRESS.  In Subsection 108-1.03:

	Replace the last sentence in the 1st paragraph with: "Submit the following at the Preconstruction Conference:"

Include CR646.1 (Section 646) when using CR652-1.03.

	Replace the last sentence in No. 1 with: "A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor, subcontractors and utilities will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer."

652-1.04 LIMITATION OF OPERATIONS. In Subsection 108-1.04:

Designer, include 652-1.04 in all projects. If 652-1.04 creates a conflict, attain permission to remove the provision from the Regional Construction Chief, or Highway Construction Group Chief.

652-1.04. Designer, consider the confines of the project transverse to the roadway with the length parallel to the roadway. If the length of the project is 13,000 feet parallel to the roadway and the width of the project between the DOT right-of-way is not unusual, it may not be necessary to limit the contractor to 11,000 ft. If the width of the project between DOT right-of-way is unusual, it may be that 11,000 ft. is too great. If physical restraints limit the project width, such as a rock cut, the railroad, a body of water, or a wetland, etc., one or both sides, it may be reasonable to increase the maximum length parallel to the roadway. Discuss the length of disturbed ground parallel to the roadway with Construction. Greater disturbed ground at one time, may take greater resources to temporarily contain the erosion, sediment and pollution thereby increasing the cost to the Department. Temporary stabilization payment is contingent sum. The greater the contained area, the more effort the Contractor may be required to expend, temporary stabilization paid by contingent sum (an open checkbook). Unusual is relative, and therefore, discussing the limit of disturbed ground with personnel with experience in these activities is all the more critical.

	Add: "Limit ground disturbed by construction activities and not permanently stabilized between all roadways combined, at any specific time, to a maximum of 11,000 feet parallel to the roadway(s), unless additional length is approved. Stabilize disturbed ground according to Section 641 Erosion, Sediment, and Pollution Control."

652-1.05 FAILURE TO COMPLETE ON TIME. In Subsection 108-1.07:

652-1.05 was a provision in Section 108. 108-1.07 Failure to Complete on Time; has been moved, with minor changes, here.

	Add: "for each calendar day that the work remains incomplete after the expiration of the interim completion date(s) as set forth in Subsection 651-1.05 Interim Completion, the liquidated damages per day given in the table below shall be deducted from any monies due the Contractor."

TABLE 652-1

INTERIM COMPLETION

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Completion Date | Daily Charge |
| --- | --- |
| 1st Interim Completion Date | $0,000 |
| 2nd Interim Completion Date | $0,000 |

CR652-071519

When including CR652-1.05, include CR651-1.05 and include SNtB "Interim Completion Date."  Adjust the number of completion dates and dollar amounts per project.  Coordinate with Construction.  This special is Not for Project Completion Date.

The following instructions are the same as occur in Section 108.

Section 108 Prosecution and Progress, and Section 652 Prosecution and Progress – Supplemental Requirements

	There are no Standard Modifications for Sections 108 and 652.

	Provisions intended for Section 108, except CR108.3, are placed in Section 652 as noted below.

Region and Project Provisions

1.	If you do have region or project provisions for Section 108/Section 652, proceed to Step 2 (nearly always), otherwise you are now done with Section 108 and Section 652.

2.	If you do have project provisions for Section 108 that modify Section 108, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 108 proceed to Step 3 (nearly always), otherwise you are now done with Section 108 and 652.

3.	If you do have region provisions that modify or add to Section 108, or project provisions for Section 108 that add to Section 108, include CR108.3 and CR652 as follows:

a.	In Section 108 include CR108.3

b.	In Section 652, CR652:

(1)	Region provisions identified by subsection:

(a)	652-1.01 Description (always include)

(b)	652-1.02 Related Sections (always include)

(c)	652-1.03 Prosecution and Progress (include when applicable)

(d)	652-1.04 Limitation of Operations (always include)

(e)	652-1.05 Failure to Complete on Time  (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	652-1.01 – 1.05 add to or modifying region provisions

(b)	652-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.

Special Provision

Add the following Section:

SECTION 654
MONITOR

Sect 654.	Previously this item was 648. Number has again been changed to accommodate other regions and aashtoware. Bidtab data will be shifted in the near future.

Related Sect/Sp:  107

Edit to the permit requirements.

654-1.01 DESCRIPTION. When authorized by directive, engage a Professional Service Contractor to monitor eagle(s) at their nests.

654-1.02 SUBMITTAL.

1.	Eagle Monitoring Plan and documentation as required by the monitoring plan.

2.	Professional Service Contractor resume(s).

654-1.03 QUALIFICATIONS. Each position is required to be an employee of the Professional Service Contractor.

Professional Service Contract Manager.

1.	Bachelor of Science degree in biology, environmental science, or ecology and working in the field of the degree, or

2.	Two years of experience monitoring or studying the habitat of birds of prey.

Monitor.

1.	Professional Service Contract Manager or a person trained and supervised by the Professional Service Contract Manager or other similarly qualified representative.

654-2.01 MATERIALS.

Video Camera	Optical zoom lens, minimum 10 power

654-3.01 CONSTRUCTION REQUIREMENTS.

Before beginning construction activity in the restricted area(s) specified in the directive, submit and receive approval for the following:

1.	The qualifications of the Professional Service Contract Manager and Monitor.

2.	An Eagle Monitoring Plan prepared by the Professional Service Contract Manager coordinated with the Contractors' Work Plan for work in the restricted area or any timing restricted period.

During Construction, submit and receive approval for the following:

1.	Eagle monitoring documentation, reports, forms, video as required by the approved Eagle Monitoring Plan and included in the authorizing directive.

Refer to Section 107-1.11 Eagles for further information.

654-4.01 METHOD OF MEASUREMENT. Eagle monitoring measured as specified in the authorizing directive.

654-5.01 BASIS OF PAYMENT. Eagle monitoring work specified in the authorizing directive.

Pay Item No.	Pay Item	Pay Unit

654(1)	Eagle Monitoring	Contingent Sum

CR654-100117

SECTION 660
SIGNALS AND LIGHTING

Sect 660: CR660.1 	660 is being updated. Attain the latest version from CR DOT Traffic Safety design personnel.

Related Sect/Sp:  SNtB; 105/CR105; 204/CR204.1; 504/CR504.1; 643/CR643.1.2; 661/CR661; 668; 740/CR740.1.2.3

Related Sect/Sp:

Special Provisions

660 is being updated by CR for CR. Attain the latest version from CR DOT Traffic Safety design personnel. Section 660 is being maintained as a placeholder, if you do not have signals and lighting, delete the Section. Confirm the provisions that are included below and remove as required. Included are past reminder notes to assist you in completing the 660 Section of provisions. CR660-110316 is available as an individual provision in the allprovision folder.

660-3.01 GENERAL.

Add the following new No. 10:

10.	Failed Equipment and Workmanship.  For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

High Towers: Removed from Sect 660 provisions. Projects including high towers, contact the traffic dept. for the 668 High Tower provisions.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the local Maintenance & Operations station within 72 hours of removal. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

Salvage of decommissioned and reusable traffic signal equipment, may require specifying the maintenance and operations station.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Pay Item 660(14) Temporary Electrolier.  By each electrolier and foundation furnished, installed, and maintained as directed by the Engineer.

Replace Subsection 5.01 with the following:

660-5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

(1)	General construction requirements,

(2)	Bonding and grounding,

(3)	Bored Casings,

(4)	Completing tests,

(5)	Conductors,

(6)	Conduit,

(7)	Dewatering excavations,

(8)	Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

(9)	Foundations including concrete to complete foundations,

(10)	J-boxes including adjustment to final grade,

(11)	Labeling conductors,

(12)	Maintaining temporary and existing electrical systems,

(13)	Minor routing changes directed by the Engineer

(14)	Preparing as-builts

(15)	Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

(16)	Removing, repairing and replacing improvements

(17)	Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

(18)	Repairing damage to finishes on new equipment

(19)	Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station including but not limited to existing signal structure

(19)  May require specifying the maintenance and operations station.

(20)	Wiring

(21)	Replacing failed equipment, equipment components and repairing failed workmanship.

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system.

Pay Item 660(1	) Traffic Signal System Complete (			).

1.	Signal structures

2.	Traffic controller assemblies including the assembly testing and preparation, vehicle and pedestrian indications, video detection systems, inductive loop detection, emergency vehicle preemption systems, auxiliary and test equipment, on-site manufacturer assisted start up and training when called for in the Plans.

3.	Work associated with installing loop detectors and conduit crossings, including:  Except when a separate Pay Item is used, saw cutting, asphalt removal, aggregate base course, tack coating, and installing new hot mix asphalt.

Pay Item 660(3	) Highway Lighting System Complete (			).

1.	Lighting structures.

Pay Item 660(11A) Data Sensor Replacement. Replace the loop detectors, piezoelectric sensors, RWIS or other data sensors inside the specified planing depth that are damaged during the planing operation (Section 202) at a rate of $		 each.

Pay Item 660(11A) Fill in the rate. Typical rate has been $1250 each.

. Pay Item 660(11A) is associated with pavement planning - do not delete 660(11A) if you have pavement planning

Pay Item 660(14	) Temporary Electrolier.

1.	Work to have plans and materials approved.

2.	Temporary electrolier including the structures, foundations, and load centers (as needed) and their removal.  Moving the electroliers, assembly and operational installation, removing and replacing, and installing conductors (in conduit or direct bury only).  Furnishing and installing temporary electrical load centers when existing load centers are not available for use.

3.	Temporary electrolier will be paid on a contingent sum basis at the unit price of $2400/each.  The Engineer does not require a change order/directive for this Pay Item.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

660(1_)	Traffic Signal System Complete 		Lump Sum

660(2)	Flashing Beacon System Complete	Lump Sum

660(3_)	Highway Lighting System Complete 		Lump Sum

660(4)	Sign Illumination System Complete	Lump Sum

660(5_)	Structure Illumination System Complete (Pedestrian Undercrossing)	Lump Sum

660(7_)	Temporary Signal System Complete 		Contingent Sum

660(8)	Underpass Lighting System Complete	Lump sum

660(9)	Bored Casing 	Inch Minimum Diameter	Linear Foot

660(11)	Traffic Loop	Each

660(11A)	Data Sensor Replacement	Each

660(12_)	Underpass Lighting System Complete (Pedestrian Undercrossing)	Lump Sum

660(13)	Relocate Electrolier	Each

660(14_)	Temporary Electrolier 		Contingent Sum

660(15_)	Signal and Lighting Salvage 		Lump Sum

660(16_)	Pedestrian Lighting 		Lump Sum

660(17_)	Traffic Signal System Modifications 		Lump Sum

660(18)	Adjust Junction Box	Each

660(19_)	Junction Box, Type 		Each

660(20_)	Signal System Timing and Adjustments 		Contingent Sum

Pay Items.  SSHC Section 109 the 2nd paragraph says: "When more than one type of material or work is specified for a pay item, letter or numeric suffixes included within parentheses following the pay item number are used to differentiate the types." Examples:

One type of material or work:

Pay Item No.	Pay Item	Pay Unit

660(1)	Traffic Signal System Complete	Lump Sum

More than on type of material or work:

660(1A)	Traffic Signal System Complete at Ruby Ave and Lake Rd	Lump Sum

[(1A, B …)]	[Add the cross streets to the end of the name, Ruby Ave and Lake Rd … ]

Typical for all Pay Items:

Pay Item No.:  Remove the blank, fill in the blank with a letter or add a letter to a number when there is not a blank.

Pay Item: Use the typical name, add intersection cross roads, add a road, add a school whether there is a blank or not.

Most importantly start with an established number (a like item) and then modify the number and name. This is very important in BIDTABS.  Further information regarding Pay Item numbers, names and pay units: see Network Drive: (hyd) S:\ESTIMATE\INSTRUCTIONS; ADOT FTP Site: http://www.dot.state.ak.us/creg/design/highways/ESTIMATE/INSTRUCTIONS

Miscellaneous Pay Item 660(99_) [Like pay item can be found in Bidtab CR Supplement for nearly all Sections of the SSHC & CR Sections]

This number is for work that is relative to Section 660 but not related to an SSHC or CR Supplement Pay Item. This number is to be used Only as the Exception, Not the Rule. Instructions are included with the Pay Item in BIDTABS.

660(22) Illumination Price Adjustment is a deduct.  When a large bank of new lighting replaces existing lighting, the Contractor is required to maintain the existing lighting until the Engineer accepts the new lighting as installed complete, functional.  Use this Pay Item to enforce this requirement.  When the Contractor does not maintain the existing lighting a price adjustment in the form of a deduct or similar will be assessed.  This Pay Item is not intended to be used for typical, smaller light installations and has been removed from the typical provisions. Where a project with a large amount of lighting is required and an existing bank of lights must be maintained - contact the CR specification engineer for a copy of the Illumination Price Adjustment provisions.

CR660-010120

SECTION 661
ELECTRICAL LOAD CENTERS

Sect 661: CR661.1.2

Related Sect/Sp: 660/CR660.1; 662/CR662; 667/CR667; 669/; 740/CR740.1.2.3

Special Provisions

CR661.1.  When load centers are included in the project add special CR661.1.  CR661.1 may be used without CR661.2.

CR661.2.  When a load center requires an uninterruptable power supply (UPS) add CR661.2 in addition to CR661.1.

661-1.01 DESCRIPTION.  Add the following:  Furnish and install load center assembly Type 1A with an integral uninterruptible power supply (secondary power source) to power intersection traffic and pedestrian signals (no lighting) and control equipment during interruptions to the utility power (primary power source).

Add the following load center type:

Type 1A with UPS:	Pad mounted with underground service (large)

Add the following Subsections 661-1.02 Acronyms, 661-1.03 Definitions:

661-1.02 ACRONYMS.

BBS	Battery Backup System

LC	Load Center

LCD	Liquid Crystal Display

LED	Light Emitting Diode

LC/UPS	Load Center with Integral Uninterruptible Power Supply

MBPS	Power Transfer Switch

MMU	Malfunction Management Unit

PLC	Powerline Communications

PTS	Power Transfer Switch

THD	Total Harmonic Distortion

UPS	Uninterruptible Power Supply

661-1.03 DEFINITIONS.

BUCK-BOOST.  Switch-mode voltage regulator in which voltage can be above or below the input voltage.

CR661.2-010120

661-2.01 MATERIALS.  Add the following:

Anchor Bolts	Section 740-2.02

Load Center.  Replace the 1st paragraph with the following:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

CR661.1-010120

Add the following:

1.	Load Center with Integral Uninterruptible Power Supply (LC/UPS).

Design, fabricate, deliver, and install as specified in the Specifications and Plans.

a.	Design of LC/UPS

Design and manufacture for outdoor applications and the environment specific to the project location.

The UPS shall be designed to provide for efficient fabrication and assembly using standard, readily available industry components facilitating the current project requirements.  The design shall provide for future quick replacement of the complete system or the individual components.  The design shall allow the maintenance department to quickly acquire a replacement UPS or replacement parts and personnel to easily remove the existing UPS and install the new UPS or UPS parts as may be needed (complete turnkey system with all necessary hardware).  Special tools shall not be required to install the UPS.

The design shall specifically include a shelf-mount, rack-mount, swing-tray mount, or combination thereof.  The UPS and PTS units individually shall not exceed 5.25” in height.  If swing-trays are used, a minimum of 6 bolts/fasteners shall be used to secure the tray to the cabinet rack.

b.	Submit.

Submit shop drawings, equipment technical specifications, and certifications for review and approval.  Do not begin manufacture of the LC/UPS prior to submitting and receiving approval of shop drawings and required certifications for the system assembly, the individual equipment pieces, components, and hardware.  Provide documentation confirming delivery dates of the individual pieces of equipment and overall system in-place completion date satisfying the project construction schedule.

c.	Manufacturers.

(1)	Meyers Power Products, Inc.

LC/UPS:  Power Model MEUG35-PB Metered/Unmetered with MP2000 UPS

Address:

2950 E Philadelphia Street

Ontario, CA 91761

Ph: (909) 923-1800 or (866) 696-9377

0

(2)	Or equal:

Manufacturers satisfying the requirements of the Plans, Specifications and Contractual requirements for the assembled system, including delivery, quality and timeliness of installation and responsive remote and onsite service, shall submit, as a substitution, for review and approval.

d.	UPS Run Time Capacity.

Power intersection LED traffic, pedestrian signals, and control equipment for the consecutive time periods noted below: (lighting and traffic controller auxiliary circuits are not included)

| RUN TIME CAPACITY |  |
| --- | --- |
| Operation Mode | Continuous Uninterruptible Operation Time* |
| Normal | 2 Hours |
| Flash | 2 Hours |
| Total (Normal + Flash) | 4 hours |

*Continuous uninterruptible operation time at 77 °F (25 °C) at load 875 W.

e.	Operation.

The transfer from utility power to the UPS shall not interfere with the normal operation of the traffic controller, MMU and other peripheral devices within the traffic controller assembly.

The MBPS shall be rated at 240 VAC, 40 Amps minimum.  The MBPS shall allow replacement of the UPS without interrupting power to the intersection. The MBPS and PTS shall be separate units.  Without interrupting power to the intersection, the MBPS shall permit the replacement of the PTS, and the MBPS and PTS shall each permit replacement of the UPS.

The UPS shall use a temperature compensated battery charging system. The charging system shall compensate over a range of 2.5 to 4 mV / °C / Cell and be rated 10 Amps at 48 VDC. Batteries shall not be charged when battery temperature exceeds 122 °F ± 5.4 °F (50 °C ± 3 °C). The temperature sensor shall be external to the UPS unit and supplied with 9' - 10" of wire.

The UPS shall automatically and continually monitor and display the current percent of battery power available for use.  A "Battery Not Connected" alarm shall be issued if battery power is not present. When utilizing battery power, the UPS output voltage shall be between 110 VAC and 125 VAC, pure sine wave output with THD < 3% at 60 Hz +/- 3 Hz.

The UPS shall provide adequate power capacity to supply an external fan with field programmable temperature setting capability located in the same or in a separate battery cabinet. The temperature setting shall be adjustable locally and remotely.  The temperature range shall be from +68 °F to +131 °F (+20 °C to +55 °C) in 1 degree F increment.

In the event of UPS failure, battery failure, or complete battery discharge, the PTS shall revert to the utility or line mode (in a de-energized state) where utility power is supplying the cabinet.

f.	Components:

The LC/UPS shall include all equipment, hardware, foundation and foundation materials, interconnecting wiring and other materials for a complete operable LC/UPS inclusive of materials and performance requirements specified herein, but not limited to:

(1)	UPS

(2)	UPS Controller Unit

(a)	Re-settable Inverter Event Counter

(b)	Cumulative Inverter Timer

(c)	Event log, Time and Dated (stores the last 100 events, minimum)

(d)	Self-Test (programmable in 1-minute increments from 1 min. to 255 min.)

(e)	Low Battery Alarm (programmable, adjustable in increments of .25 VDC)

(f)	Buck-Boost Mode (UPS shall be capable of Buck-Boost 10% ±)

(3)	PTS (activated during Buck-Boost operations; transfer times 10 milliseconds)

(4)	MBPS (non-electrical)

(5)	Batteries and Battery Enclosure

(6)	Battery Heater Mats

(7)	Cabinets and Enclosures

(8)	External Fan

g.	UPS Access and Password Protection.

	Provide local and remote access.

	Provide the UPS with a default password.

Access:

(1)	Local – provide an LCD display screen and touch pad as part of the UPS

(2)	Remote

(a)	RS232 interface

(b)	USB interface

Local and remote access shall provide same access use.

User:

(1)	The “User” includes the Department Traffic Engineers and Maintenance Personnel.

(2)	The User shall be able to monitor the following at the LC/UPS cabinet (locally) and remotely.

Use:

(1)	Provide the Department with the default password and administrative authority to add/change password protection.  Make the procedure intuitive and direct.

(2)	Control, programming, maintenance, and inquiry (view and adjust) including but not limited to:

Monitor:

(a)	Time,

(b)	Date,

(c)	Current battery charge status,

(d)	Input/output voltages,

(e)	Power output,

(f)	Battery temperature,

(g)	Field programmable relay settings

Current status shall be indicated by LED lights:

(a)	Green – Flashing for battery back-up mode

(b)	Green – Steady ON for normal line mode operation

(c)	Red – Flashing for ALARM conditions

(d)	Red – Steady ON for FAULT conditions

Maintenance Controls - password protect:

(a)	UPS Inverter ON/OF,

(b)	Battery Test,

(c)	Event Log (Retrieving, viewing and printing in plain English),

(d)	Changing Default Settings

Other Settings:

(a)	Temperature Settings,

(b)	Re-Settable Inverter Event Counter,

(c)	Cumulative Inverter Timer,

(d)	Self-Test,

(e)	Low Battery Alarm

(3)	Upload firmware software updates of the non-volatile, read-only memory type.

h.	Specifications.

(1)	Environmental:

The operating temperature for the (UPS), (PTS) and (MBPS) shall be -34.6 °F to 165.2 °F

(-37 °C to +74 °C).

(2)	UPS Input/Output:

| UPS SPECIFICATIONS |  |
| --- | --- |
| Input Specifications |  |
| Nominal Input Voltage | 120 VAC, Single Phase |
| Input Voltage Range | 120 VAC ± 25% |
| Input Frequency | 60 Hz ± 5% |
| Output Specifications |  |
| Nominal Output Voltage | 120 VAC, Single Phase |
| Power Rating* | 2000 VA (1500 Watts) |
| Output Frequency | 60 Hz ± 5% |
| Voltage Wave Form | Sine Wave, THD < 3% |
| Efficiency (nominal) | 95 – 97% |

*The UPS power rating of 2000 VA / 1500 Watts shall be with a minimum inverter efficiency of 80%.

(3)	Loss/Restoration of Utility Power:

When the utility line voltage is outside the High and Low Limits (100 & 130 VAC respectively set as defaults), the UPS shall transfer the load to battery power. The UPS shall return to line mode when the utility power has been restored to above 105 VAC or below 125 VAC; or the UPS shall return to line mode when the utility power is back to nominal for more than 30 seconds (the line qualification time).  The line qualification time shall be adjustable to 3, 10 or 30 seconds.

The maximum transfer time allowed, from disruption of normal utility line voltage to stabilized UPS line voltage from batteries, shall be 65 milliseconds. The same maximum allowable transfer time shall also apply when switching from UPS line voltage to utility line voltage.

(4)	Battery(s):

(a)	Batteries as part of the UPS provide the power.

Individual batteries shall be rated at 105 Amp-Hour minimum. Batteries shall be 12 VDC type and shall be easily replaced and commercially available off the shelf. The battery system used in the UPS shall consist of 4 batteries and shall be of a voltage not to exceed 60 VDC. Batteries shall be provided with quick disconnect terminals and a polarized - keyed battery cable for easy field installation.

Batteries shall be deep cycle, sealed prismatic lead-calcium based AGM/VRLA (Absorbed Glass Mat/Valve Regulated Lead Acid) batteries - able to withstand extreme temperature. Batteries shall be certified to operate over a temperature range of -4 °F to 165.2 °F (-20 °C to +74 °C).  The batteries shall be provided with appropriate interconnect wiring and a corrosion-resistant stationary or swing-out mounting tray and/or brackets appropriate for the cabinet into which they will be installed as specified in “Design of LC/UPS”.

Batteries shall indicate maximum recharge data and recharging cycles. Recharge time for the battery from protective low cutoff to 80% or more of full battery charge capacity, shall not exceed twenty (20) hours.

(b)	Battery Compartment:

The battery cabinet shall be vented through the use of louvered vents, filter, and one thermostatically controlled fan operated from the UPS. The fan will automatically turn ON at the temperature programmed into the UPS.

External battery compartments may be used to satisfy environmental and physical requirements.  When submitting shop drawings, material and equipment submittals, request in writing and demonstrate graphically the need for an external compartment(s).

(c)	Back-Feed and Other Protections:

The UPS shall be equipped to prevent a malfunction feedback to the cabinet or from feeding back to the utility service per UL 1778, Section 48 "Back-Feed Protection Test". The upstream back-feed voltage from the UPS shall be less than 1 VAC for the protection of persons accessing the equipment.

The UPS shall have lightning surge protection compliant with IEEE/ANSI C.62.41 for 2000 VAC.

(5)	Relay Contacts:

The UPS shall provide the user with 6 sets of fully programmable, relay contacts of type NO/NC, panel-mounted, potential free and rated 1 Amp, 120 VAC and labeled C1 through C6. Each relay's setting shall be programmable to activate under conditions through local access or remote access.  The minimum number of relay settings is outlined below.

Independently configure relay contacts C1 through C6 to activate under the following conditions:

(a)	ON BATTERY - relay activates when BBS switches to battery power.

(b)	LOW BATTERY - relay activates when batteries have reached a specified level of remaining useful capacity while on battery power. The specified level shall be adjustable from 0 to 100%.

(c)	TIMER- relay activates after being on battery power for a specified amount of time. The specified time shall be adjustable from 0 to 8 hours.

(d)	ALARM - relay activates after a specific or general alarm is detected. These alarm conditions include:

	Line frequency

	Low output voltage

	No temperature probe

	Overload

	Batteries not connected

	High temperature

	Low temperature

The relay shall be programmed to activate when any of these alarm conditions occur, or when a specified condition occurs.

(e)	FAULT- relay activates after a specific or general fault is detected. These fault conditions include:

	Short circuit

	Low battery voltage

	High battery voltage

	High internal temperature

	Overload

The relay shall be programmed to activate when any of these fault conditions occur, or when a specific condition occurs.

(f)	OFF- relay is disabled and shall not activate under any condition.

(6)	Default Relay Settings:

(a)	Relay C1 and C2 shall be set to activate whenever the UPS transfers to battery power and shall be labeled "ON BATT."

(b).	Relays C3 and C4 shall be set to activate whenever the batteries reach 40% of remaining useful capacity and shall be labeled "LOW BATT."

(c)	Relays C5 and C6 shall be set to activate whenever the UPS has been on battery power for 2 hours and shall be labeled "TIMER."

Terminal block position 19 & 20 shall be set to activate a self-test. This test confirms that a unit can transfer into and out of battery mode while supporting the output load.

(7)	Load Center for Temporary Power:

Use the following load centers for distribution of power for temporary lighting and signals including the control systems.  Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

(a)	Permanent load centers installed in their plan location.

(b)	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if approved.

(c)	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked “Suitable for use as service equipment.”

CR661.2-010120

Equipment List(s) and Drawings.

Delete No. 1. and replace with the following:

1.	Materials on the Qualified Products List:  The Qualified Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

3.	Materials Not Requiring Certification:  Replace the 2nd sentence with the following:

Submit these materials for review and approval if included on the Materials Certification List (MCL) or requested by the Engineer.

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.  Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.  Replace the 11th paragraph with the following:

Install two ground rods at least 8 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper grounding electrode conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Add the following:

Coordinate new load centers with existing and or new service utilities.

Failed Equipment and Workmanship

For the term of the Contract from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

661-5.01 BASIS OF PAYMENT.  Add the following:

The following work is subsidiary to 661 Pay Items:

	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

	All work including, but not limited to, contacting and coordinating with the utilities for service; maintenance and usage payments until the Engineer provides the notice of final acceptance.

	Replaced failed equipment, equipment components and repaired failed workmanship.

CR661.1-010120

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

661(2A)	Load Center, Type 1A with UPS (LC/UPS)	Each

CR661.2-010120

Special Provisions

Add the following Section:

SECTION 662
SIGNAL INTERCONNECT

Sect 662: CR662

Related Sect/Sp:  660/CR660.1, 661/CR661.1.2, 667/CR667, 669/ 740/CR740.740.1.2.3

662-1.01 DESCRIPTION.  This item consists of the work required to furnish and install signal interconnect in conduit between the controller assemblies shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 REGULATIONS AND CODE.  Complete the work according to these Specifications and Section 660, Signals and Lighting.  The Department requires third party certification for high density polyethylene conduit.  Equal to or exceeding UL 651 B and NEMA TC-7.

662-2.01 MATERIALS.  Submit the materials for review and approval according to the requirements of No 1. Equipment List and Drawings. of Subsection 660-2.01, Materials.

Furnish a 25 pair #19 telephone cable conforming to REA Specification PE-39 for the interconnect cable.  Install the interconnect cable in a 2 inch polyethylene conduit.

Encapsulate completed splices in waterproof reenterable type splice kits of the same type used for loop lead-in cable splices.  REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers" provides a list of acceptable splice materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a polyethylene duct system in which to pull the interconnect cable.  The Department will not permit the installation of the polyethylene conduit in a plowed trench.

Furnish a Type III polyethylene duct made from extra high molecular weight, high density, polyethylene (PE) pipe, with a cell classification equal to or exceeding 335444C when tested according to ASTM D 3350.

Furnish fittings used in the duct system, such as elbows, made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.  Except elbows weeping into junction boxes shall be rigid metal conduit.  Join the rigid metal conduit to the HDPE with Electrofusion Type Coupler.

Keep junction boxes and ends of conduit covered unless pulling conductors.

Mark underground conduits with a continuous strip of polyethylene marker taped.  Furnish marker tape with a black legend on a red background that is 4 mil thick and 6 inches wide.  Install the tape 6 inches below finished grade.

Use care during compaction operations to prevent damage to the junction boxes and conduits.  Remove and replace items damaged during the backfill and compaction operations at no additional cost to the Department.

After testing and installing the conductors, plug conduit openings with duct seal to prevent water from entering the duct system.

662-2.03 JUNCTION BOX.  Furnish precast, reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  Install junction box lids made of cast iron.

662-3.01 CONSTRUCTION REQUIREMENTS.  The signal interconnect consists of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.

Install the polyethylene conduits at least 30 inches below finished grade.

Install junction boxes at abrupt changes in conduit alignment and on 300 foot maximum centers.  Angle points and curves with delta angles greater than 45 degrees constitute an abrupt change.  Install Type 1A junction boxes, except when splicing interconnect cables together.  Complete the interconnect cable splices in Type II or III junction boxes.  Complete the splices according to Rural Electrification Administration (REA) Specification PC-2 for splicing telephone cables.  The Contractor shall determine the locations for making signal interconnect splices.  The Engineer, however, will not allow splices to be made at low points in the terrain or the bottom of sag vertical curves.  Keep splices in the interconnect cable to an absolute minimum and get the splice locations approved by the Engineer beforehand.

Furnish the controller cabinets with terminal blocks for the interconnect cable.

662-3.02 EXCAVATING AND BACKFILLING.  Backfill the excavations according to Section 204.

The Engineer will not allow ripping or plowing for installation of conduit.  Backfill around the polyethylene conduit with a 6 inch lift of material free of rocks exceeding a 1 inch maximum dimension.

662-4.01 METHOD OF MEASUREMENT.  The Engineer will measure signal interconnect by the linear foot from the center of junction box to center of the next junction box, following the slopes of the existing ground.

662-5.01 BASIS OF PAYMENT.  The contract unit price paid per linear foot for signal interconnect constitutes full compensation for furnishing work required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under Item 660(1) Traffic Signal System Complete.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

662(1) 	Signal Interconnect	Linear Foot

CR662-091311

Special Provisions

Add the following Section:

SECTION 667
TRAFFIC SIGNAL COMMUNICATION SYSTEM

Sect 667:  CR667

Related Sect/Sp:  660/CR660.1, 661/CR661.1.2, 667/CR667, 669/, 740/CR740.1.2.3

667-1.01 DESCRIPTION. Provide all labor, equipment and materials, mounting hardware and ancillary items to provide a fully functional traffic signal communication system. Requirements include all items detailed in this Section and the Plans including but not limited to:

1.	Installation and setup of radio interconnect system between traffic signal controllers shown in Plans

2.	Installation and setup of on-street master traffic signal controller at location shown in the Plans

3.	Installation and setup of uninterruptible power supply where required

4.	Providing other equipment and deliverables as specified

5.	Manufacturer assisted startup of the system

6.	Setup of ADOT owned Aries traffic signal software

7.	Telephone service

8.	Training

667-2.01 MATERIALS.

Approved Products List.  The Approved Products List does not apply to the 667 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

Materials Not Requiring Certification.  Only submit these materials for review and approval if they are included in the Materials Certification List (MCL).

Provide new materials that meet the requirements set forth in Section 740 of the Special Provisions, the Material Certification List (MCL) and the latest version of the Standard Specifications for Highway Construction. The following equipment is required as part of the Traffic Signal Communication System:

1.	Radio Interconnect System. Provide the following materials in the number and locations detailed in the Plans. All connecting cables, mounting hardware, conduit, and appurtenances are to be included.

a.	Master Radio

b.	Remote Radio

c.	Omni Antenna

d.	Yagi Antenna

e.	Antenna Cable

f.	AC Adaptor

g.	Lightning Protector

h.	Antenna Cable Connectors

2.	On-Street Master Traffic Signal Controller. Provide the following materials in the number and locations detailed in the Plans. All connecting cables, mounting hardware and appurtenances are to be included.

a.	Master Traffic Signal Controller

b.	56K Industrial Modem

c.	GPS Time Reference

3.	Other Equipment. Provide the following materials in the number and locations detailed in the Plans. All connecting cables, mounting hardware and appurtenances are to be included.

a.	Fully functioning TS2 test cabinet(s)

b.	Ultrasonic thickness gauge

c.	Lock Cores

667-3.01 CONSTRUCTION REQUIREMENTS. The Manufacturer’s Representative will be onsite and oversee the following work. The contractor must meet the requirements of Subsection 660-3.01, Construction Requirements of the Standard Specifications for Highway Construction, Special Provisions and the following:

1.	Radio Interconnect System.

a.	Site Survey:

Conduct an on-site site-survey to determine adequacy of radio placement. The manufacturer is to provide a representative on site to oversee installation of the Communication System components, set up, and tune the radios to provide a fully functioning communication system.

(1)	Verify and document:

(a)	Line of site signal strength using test radios operating at the power level and frequency matching the specifications of the permanent radios (recommended) while physically positioned to match the proposed location and orientation of same radios.

(b)	Neighboring radio usage.

(c)	AC outlets available for use in each cabinet.

(d)	Conduit space available for use in each cabinet.

(2)	Submit for review and approval:

(a)	Location/placement and orientation recommendations including the elevation/mounting height and plan/horizontal dimensions from an established reference point.

(b)	Neighboring radio usage.

(c)	AC outlet availability including recommendations for additional outlets where required.

(d)	Conduit space with recommendations for adding conduit if required.

(e)	Operating frequency and use of "drop and repeat" radio installation recommendations.

(3)	Installation:

(a)	Installation is to be neat and attractive.

(b)	Install shelf mounted radio(s) in each traffic signal controller cabinet shown in the Plans. Mount radios to the top of the existing shelves.  Where room is not available to mount the radios to the existing shelf top, provide under shelf mounts.

(c)	Provide additional AC outlets on wall of traffic signal controller cabinet as required.  Power strips are not permitted.

(d)	Install antenna wire between traffic controller and antenna according to manufacturer’s recommendations, the Plans, and Specifications.

(e)	Mount antenna on traffic signal pole nearest traffic controller, except where the radio site survey dictates placing the antenna at another location.

(f)	Antennas are to be mounted at least 10 feet above the mastarm on the vertical member of the signal pole or as shown in the Plans.  Only one 3/4" or smaller hole may be drilled in the pole. Deburr the hole and protect from corrosion with an approved zinc based finish.

(g)	Run antenna wire inside pole.

(h)	Utilize existing conduits for antenna wire or bury new conduit between the traffic controller cabinet and pole. Conduit shall be 2" RMC

(i)	Provide lightening suppression designed to protect radios and other signal controller assembly components.

(j)	Establish communication with On-Street Master traffic signal controller and local controller.

(k)	Enable radio diagnostics.

(l)	The vendor is to acquire FCC license(s) for all supplied radios on behalf of the Department.

2.	On-Street Master Traffic Signal Controller.

a.	Install On-Street Master Traffic Signal Controller.

b.	Program On-Street Master Traffic Signal Controller with timing plan provided by ADOT.

c.	Establish communications with local controller.

d.	Establish communication with master radio.

e.	Coordinate with the local telephone company to provide a "leased line" between the local ADOT Maintenance and Operations, Traffic Engineering and the Master Controller

f.	Install modem and establish communications between the On-Street Master Controller and the ADOT local Maintenance and Operations, and Traffic Engineering

g.	Provide and install GPS time reference

h.	Provide system map and intersection maps

i.	Setup Aries system at both the local Maintenance and Operations, and Traffic Engineering to provide communication between each

3.	Other Items.

Provide the following materials and equipment, or equal materials and equipment, and services when specified in the Plans (Equipment Communication Schedule).  Coordinate with the Plans, the Engineer, and the local ADOT & PF Maintenance and Operations Foreman the materials and services required, the number and where and when to make delivery.

Submit shop drawings, catalog cuts, product specifications, and industry standard certifications for the required materials, equipment and services specified in the plans to the Engineer for review and receive approval prior to fabrication, or delivery if prefabricated, to the project site or ADOT & PF Maintenance and Operations Station.

a.	Master Traffic Controller Test Cabinet:  Deliver fully functioning Master Traffic Controller test cabinet. The cabinets are to be identical to other cabinets being supplied with the project.

b.	Ultrasonic Thickness Gauge:  StressTel Ultrasonic Testing Equipment - Ultrasonic Thickness Gauge, Model T-Mike B.

c.	Locks:  Provide Best Series "CX." 7-pin, lock cores or approved equal.  To be considered an approved equal the locks must be compatible with All ADOT & PF traffic controller cabinets, be constructed of solid brass and, conform to requirements of ANSI/BHMA A156.11, Grade 2.  Lock cores are to be keyed alike with a level "A" tumbler-pin combination unique to the ADOT & PF.  Provide each lock with two "cabinet" keys.  For every 25 cores, provide one (1) control key.  Provide a total of 10 each, grandmaster keys.  All keys provided shall be marked with the words "Do Not Duplicate" and any marking necessary to identify the series of key.  Sequentially number all cabinet, control and grandmaster keys starting at one.

The Contractor is responsible for establishing an account with the lock manufacturer on behalf of the Alaska Department of Transportation.  Establish said account with authorized agents specified by ADOT.  Authorized agents must be able to order or reorder lock components as may be necessary.  The key manufacturer must have authorized agents located in Anchorage, Fairbanks, Juneau, Soldotna, and Wasilla Alaska.  Contact the ADOT & PF Traffic Engineer regarding lock cores.

The Contractor is responsible for ensuring provided cores work with existing lock sets.  The Contractor is not responsible for installation of lock cores.

4.	Failed Equipment and Workmanship. For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair failed workmanship.

667-3.02 MANUFACTURER ASSISTED START-UP.

1.	Manufacturer Representatives.

The Contractor shall retain the services of a representative from each of the manufacturers listed below:

a.	Radio Interconnect System

b.	On-Street Master Controller

c.	UPS

d.	Malfunction Management Unit

A single individual may represent one or more of the products listed provided the Manufacturer has trained the individual in use of their system, and certifies the individual is competent to provide the required services and is approved by the Engineer.

2.	Responsibilities of the Manufacturer’s Representative include.

a.	On-site supervision of the installation of all communication system components.

b.	Being on-site to perform setup/programming of all communication system components.

c.	Visit the site annually through final acceptance 105-1.16, to assess the condition of the communication system and perform routine maintenance.

d.	Provide on-site training as required.

e.	Provide all required test reports or other deliverables to the Engineer.

The Contractor shall inform the Department 15 days prior to planned start up, coordinate the actual date, and time for the start-up with the Traffic Engineer.

667-3.03 TELEPHONE SERVICE. The contractor shall provide telephone service to the master traffic signal controller cabinet. A master traffic signal controller cabinet is any cabinet in which there is an on-street master traffic signal controller such as the Econolite ASC/2-1000 or Traconex TMM-500. The telephone service shall be active inside the cabinet prior to Manufacturer Assisted Start-up. The contractor is financially responsible for the telephone service until 100% completion of the Communication System Pay Item.

Run 6PR22 telephone wire in 1 inch HDPE conduit between the NID and the cabinet. The telephone service must be terminated inside the master traffic signal controller in an RJ11 telephone jack. The contractor is responsible for coordination with the local telephone company to activate service.

667-3.04 TRAINING. Except as otherwise noted, immediately preceding or following the Manufacturers Startup of the Traffic Signal Communication System, the vendor shall provide training. All training is to be provided by a representative of the original equipment manufacturer. Training may be attended by any number of ADOT personnel from any of its three regions. Required training includes;

667-3.05 DELIVERABLES. The Manufacturer’s Representative shall provide the Engineer with each of the following prior to final acceptance of the item:

1.	FCC License. Provide original FCC license before activating radio interconnect system.

2.	Operations Manuals. Provide 2 complete sets of operations manuals for all equipment delivered as part of the Traffic Signal Communication System Item. This should include but not be limited to; on-street master traffic signal controller, local controller unit, master radio, remote radio, UPS equipment, MMU tester, and utility locator.

3.	Log Books.

a.	Boorum & Pease Extra-Durable Bookstyle Columnar Book 10 3/8" x 8 3/8", Stock No. 21-150-R or approved equal.

4.	System Map and Intersection Diagrams. Submit for review and approval and owner use fully functioning Intersection Diagrams compatible with the latest version of Aries.  Provide the Intersection Diagrams in pcx format.

Include physical features on the Intersection Diagrams; background, lane lines, pathways, railroad tracks and crossings, schools and school zones, firehouses, points of reference (public buildings, shopping centers, etc.) and Master Traffic Signal Cabinets, as applicable.

On the Intersection Diagrams include the additional features; edge of pavement lines, crosswalks, curbs and raised medians.

Label each Intersection Diagram with; street names, city name, ADOT logo in the upper left corner, the graphics design firm logo or name in lower right corner, north arrow, lane use arrows, traffic signal poles, mastarms, controller and load center.  Incorporate the active components into the drawings; detectors, signal faces, and pedestrian indications.

On the Intersection Diagrams include the additional active components into the drawings; phase diagram and ring termination cause.

Intersection Diagrams:	 800 x 600 pixels with the scale of each diagram equal to 1-pixel to 1-foot.

The following color scheme shall be used in the construction of the Intersection Diagrams.

FEATURE	COLOR

Background	Blue

Pavement	Dark Gray

Sidewalk/Pathway	Light Gray

White Lane Lines/EOP	White

Yellow Lane Lines	Yellow

Labels	Yellow

Detectors	Blue

Lane Markings	White

Vegetation/Shoulders	Green

Poles, Mastarms, TC, LC	Black

Signal Indications	Red, Yellow, Green

Ped Indications	White, Flashing Orange, Solid Orange

Phase Diagram Border	Yellow

North Arrow	Light Orange/White

5.	Site Survey Results.  Submit the results and recommendations of the radio site survey for review, comments, and approval 15 days in advance of starting work associated with the results.  In addition to the submittal requirements of 667-3.01 include the following for each site.

a.	Ambient radio noise in the licensed bandwidth

b.	Signal strength

c.	Error rate

d.	Data flow rate

667-4.01 METHOD OF MEASUREMENT.  Per Section 109.

667-5.01 BASIS OF PAYMENT. The radio site survey, manufacturer assisted start-up, training, software setup, production of system, intersection maps, and replacing failed equipment, equipment components and repairing workmanship are subsidiary to the 667 Pay Item(s), except when included as a separate Pay Item.

Withholding.  To ensure full compliance under this Section, 15 percent of all billings shall be withheld until Pay Item 667(1) Traffic Signal Communication System is accepted as complete by the Engineer.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

667(1)	Traffic Signal Communication System Complete	Lump Sum

CR667-050118

SECTION 668
HIGH TOWER LIGHTING

Contact DOT Traffic Department for latest version.

New special in progress.

Sect 668:  	Section 668 is being maintained as a placeholder, if you do not have high tower lighting, delete the Section.

Related Sect/Sp:

Special Provisions

Add the following Section:

SECTION 669
AUTOMATED TRAFFIC RECORDERS

Sect 669:  	Section 669 is being maintained as a placeholder, if you do not have Automated Traffic Recorders, delete the Section.

Related Sect/Sp:  660/CR660.1, 661/CR661.1.2, 667/CR667, 669/, 740/CR740.740.1.2

669-3.01 CONSTRUCTION REQUIRMENTS.

#.	Failed Equipment and Workmanship.  For the term of the Contract, from initial equipment installation through final acceptance, Subsection 105-1.16, when directed, promptly replace failed equipment, equipment components and repair workmanship.

669-5.01 BASIS OF PAYMENT.

	Replacing failed equipment, equipment components and repairing failed workmanship is subsidiary to 669 Pay Items.

AKSAS/IRIS #

For a starting point, contact Central Region Specification Engineer and coordinate with the Highway Data Department.

In your project special.

1.	Add as the last item under 669-3.01. Construction Requirements. "#.	Failed Equipment and Workmanship. For the term of … "

2.	Add to 667-5.01 Basis of Payment. "Replacing failed equipment, equipment components … " Include as a list of items as is in the typical version of 669, or add separately.

3.	If you have a "Warranty" subsection, delete it. Typically, this subsection has been included as, "669-3.03 Warranty." If you wish to avoid renumbering, change the warranty subsection to, "669-3.03. Not used."

SECTION 670
TRAFFIC MARKINGS

CR670.1. Include when the project includes MMA.  This special is not intended to be used for paint.  Paint is covered by the SSHC Section 670, except when a project requires a project specific special.  Include 712-CR712.1 when including 670-CR670.1.

CR246.  Include when the project includes MMA.  This special is not intended to be used for paint.  Paint is covered by the SSHC Section 670, except when a project requires a project specific special.  Include 712-CR246 when including 670-CR246.

Sect 670:  CR670.1 (CR670.1 Rplcd CR246)

Related Sect/Sp: 406/CR406, 643/CR643.7, 712/CR712.1

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings							Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Add the following

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.   Replace No. 4 with the following::

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Surface markings, 60 mils. For further info consult current version of the Central Region Striping Guide for marking application requirements.

Surface markings, 60 mils unless Traffic Engineer and Safety Engineer specifically directs otherwise.

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Consult current version of the Central Region Striping Guide for marking application requirements.  Insert 4 places.

Consult the Traffic Engineer and Safety Engineer for inlay depth, 60-500 mils.  Insert 4 places.

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of      mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of      mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of     mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of      mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils.  Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 670-3.06 with the following:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Replace No. 3 with the following::

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Replace No. 4 with the following:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10)	MMA Pavement Markings	Lump Sum

670(10A)	MMA Pavement Markings, Longitudinal Surface Applied	Linear Foot

670(10B)	MMA Pavement Markings, Symbols and Arrow(s) Surface Applied	Each

670(10C)	MMA Pavement Markings, Transverse and Gore Surface Applied	Linear Foot

670(10D)	MMA Pavement Markings, Longitudinal Inlaid	Linear Foot

670(10E)	MMA Pavement Markings, Symbols and Arrow(s) Inlaid	Each

670(10F)	MMA Pavement Markings, Transverse and Gore Inlaid	Linear Foot

CR670.1-110812R

Special Provision

Add the following Section:

SECTION 682
UTILITY POTHOLING

Sect 682: CR682

Related Sect/Sp:  105/CR105.3; 660, 740

Related Sect/Sp:

682-1.01 DESCRIPTION.  Expose subsurface utilities using a vacuum-extract truck.  Record the location of the utility(s). Backfill the pothole and dispose of waste materials.

682-2.01 MATERIALS.

Backfill Material:			Aggregate Base Course, Grading D-1		Section 703

Asphalt Patch Material:		Hot Mix Asphalt Type II, Class B				Section 401

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies not less than 7 days before starting potholing.

Deliver the vacuum-extract truck to the job-site with the debris tank empty.

Expose the subsurface utilities.  Log the as-built information, subsection 682-3.02.  Backfill the pothole immediately after the Engineer accepts the logged data.  Backfill the first 6 inch lift using the excavated material, compact the material.  Backfill the balance of the pothole using Aggregate Base Course, Grading D-1, compact the material.  In paved areas, use Hot Mix Asphalt Type II, Class B to patch over the pothole, match the thickness of the surrounding pavement.

Dispose of excavations off-site.  Before beginning potholing, provide to the Engineer a certificate, signed by the owner or owner's representative, identifying the disposal site and acceptance of the project potholing excavations.

Utilities damaged by the potholing operation require the Engineer to be immediately notified.  The Contractor is responsible for the repairs and the associated costs.  Contact and coordinate repairs with the utility owner.

682-3.02 AS-BUILTS.  Create a utility pothole log, as-built, recording for each pothole: the date of potholing operation, utility type and size, station, offset, elevation, groundwater, and other pertinent data.  Survey the utility location using the project horizontal and vertical control; comply with the requirements of Section 642.  Submit the completed log to the Engineer within two working days following the completion of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  The pay unit, contingent sum, is measured by the hour of work performed.

682-5.01 BASIS OF PAYMENT.  Pay Item No. 682(1) is paid at $450/hour for the work to pothole; expose the utility(s), backfill the hole, patch disturbed pavement and dispose of excavations.  The paid time includes the work; labor, and the fully operated vacuum truck or combination of vacuum truck and other Engineer approved equipment engaged in potholing at the area(s) identified in the Plans and/or identified by the Engineer.  The paid time includes the time to empty the vacuum truck of excavation material, including the travel time, from this project only, to a certified disposal site.

Discuss project location relative to disposal sites with the Engineer.  Include, modify or leave out the last sentence of the paragraph above.

Travel time to and from the project, idle time, maintenance and repairs (labor, material and time) are incidental and not included in the measured time.

As-built, utility pothole log, per subsection 682-3.02, will be paid under Section 642.

Potholes for the Contractor's information and potholes not accepted by the Engineer will not be paid for by the Department.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

682(1)	Vac-Truck Pothole	Contingent Sum

CR682-010114

Special Provision

Add the following Section:

SECTION 690
WATERWAY

Sect 690: CR690	 Section 690 is included as a placeholder. Use space if the project requires a project specific provision, otherwise delete.

Related Sect/Sp:  201, 621, 623

Related Sect/Sp:

Designer, request a copy of the Waterway provision draft, from the CR Specification Engineer. The draft provides a format for including waterway provisions.  Many waterway topics are discussed, not all are included.

DIVISION 700 — MATERIALS

	Keep this page to keep the page number field functioning when you remove a section..

Refer to Division 100 notes for further information.

	Page Numbers. Number specifications to allow every "Division" to begin on a "right hand," odd numbered page.

Sect 700s: HSP18-1, add to material specifications when naming products manufactured predominately of Steel or Iron, in the Contract.

Related Sect/Sp:  200s through 700s

INSERT HSP18-1 when Naming Products, manufactured predominately of steel or iron, in the Contract.

EDIT, add, or delete statements (a, b, c ...). Name each product separately, one line for each product named in the subsection (2.01, 02, 03 …).

The special applies to all specifications, Division 200 through 700, whether in the Standard Specifications for Highway Construction, Standard Modifications, or special provisions (State specials and region specials).

Do not name products (specifically products manufactured of steel or iron) in the specifications, and avoid the need for HSP18-1.

Special Provisions

Add the following:

Products identified by name in the list below are manufactured predominately of steel or iron. The information below represents the Department's knowledge at the time of advertisement regarding whether products are "Manufactured in the United States" as defined in Section 106 of the Contract. Including this information in the Contract does not relieve the Contractor of responsibility for complying with Section 106 of the Contract and the Buy America Act, and providing the Material Origin Certificate Form 25D-60 and the Certificate of By America Act Compliance Form 25D-62 as required in Subsection 106-1.01.

(a)	Named Product A is/is not "Manufactured in the United States".

(b)	Named Product A is/is not "Manufactured in the United States".

(c)	Named Product A is/is not "Manufactured in the United States".

HSP18-1-052518

Keep this page to keep the page number field functioning when you remove a section..

Blank Page

SECTION 702
ASPHALT MATERIALS

Sect 702: CR702.2R1.3

Related Sect/Sp:  306/CR306, 401/CR401, 408/CR408

Special Provision

702-2.01 ASPHALT BINDER. Replace the 1st paragraph with the following:

Meet AASHTO M 320 Performance-Graded Asphalt Binder and AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification; except, as included in Table 702-2.01-1 Performance-Graded Asphalt Binder – Exceptions.

TABLE 702-2.01-1

PERFORMANCE-GRADED ASPHALT BINDER - EXCEPTIONS

| Performance Grade | Viscosity AASHTO T 316 | Multiple Stress Creep Recovery MSCR, AASHTO T 350 |  |  | Dynamic Shear PAV, AASHTO T 315 | Direct Tension AASHTO T 314 | Elastic Recovery AASHTO T 301 |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | JNR3.2 kPa-1 | JNR Diff | % Recovery3.2 | G*Sinδ, kPa |  |  |
| AASHTO M320 Performance-Graded Asphalt Binder |  |  |  |  |  |  |  |
| PG 52-28 | None | — | — | — | None | Delete | None |
| PG 52-40 | None | — | — | — | None | Delete | None |
| PG 52-40 ER | None | — | — | — | None | Delete | 50% min. |
| PG 58-34 ER | None | — | — | — | None | Delete | 60% min. |
| PG 64-40 ER | None | — | — | — | None | Delete | 60% min. |
| AASHTO M332 Performance-Graded Asphalt Binder Using MSCR Test Specification |  |  |  |  |  |  |  |
| PG52-40 V | None | 0.50 max. | Delete | 75 min. | None | Delete | None |
| PG58-34 E | None | 0.25 max. | Delete | 85 min. | None | Delete | None |
| PG 64-40 E | 1 Pas max. | 0.10 max. | Delete | 95 min. | 5000 max. @ 4°C | Delete | None |

CR702.3-100118R

CR702.3. Include all projects with binders as listed in the tables below.

CR702.2. Include all projects with asphalt.

702-2.03 EMULSIFIED ASPHALT.

2.	Special Tack Emulsion, STE-1.

TESTS ON RESIDUE

Replace the first line: 	Penetration @ 77 °F	100-200,

with:	Penetration @ 77 °F	100-250

CR702.2-060115R1

SECTION 703
AGGREGATES

Sect 703: Section Specials:

Related Sect/Sp:  301/CR301.1.2; 306/CR306, 401/CR401, 408/CR408

Special Provisions

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

408 HMA. Type VH or V. If V remove the "H" from the sentence below.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, and V mixes.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

408 HMA. Type VH or V. If V remove the "H" from Table 703-3 far right column header below.

Meet Table 703-3 requirements:

TABLE 703-3

COARSE AGGREGATE QUALITY FOR HMA

| Description | Specification | Type II, Class A | Type I; Type II, Class B; Type III | Type IV | Type V |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max. | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, min. | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss, % max. (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, % min. | ATM 305 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Flat-Elongated Pieces, % max. | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| Absorption, % max. | ATM 308 | 2.0 | 2.0 | 2.0 | 2.0 |
| Nordic Abrasion, % max. | ATM 312 | - | - | - | 8 a |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

408 HMA. Type VH or V. If V remove from Table 703-3 far right column, bottom row "8.a " and  note "a." at the bottom of the Table.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type II, Class A mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate, and shall not exhibit rut depth larger than 1/4-inch, as determined by ATM 419.

408 HMA. Type VH or V. If V remove the "H" from the sentence below.

Fine aggregate for Type IV and V mixes:

	do not blend back natural sand

	shall be non-plastic as determined by ATM 205

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-4

408 HMA. Type VH or V. If V remove the "H" from Table 703-4, far right column header below.

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 |
| 1/2 inch | 60-84 | 77-99 | 100 | 100 | 65-90 |
| 3/8 inch | 48-78 | 68-88 | 80-90 | 80-95 | 55-80 |
| No. 4 | 28-63 | 48-68 | 44-81 | 55-70 | 40-60 |
| No. 8 | 14-55 | 33-53 | 26-70 | 35-50 | ≤ 45 |
| No. 16 | 9-44 | 20-40 | 16-59 | 20-40 | ≤ 35 |
| No. 30 | 6-34 | 14-30 | 9-49 | 15-30 | ≤ 25 |
| No. 50 | 5-24 | 9-21 | 6-36 | 10-24 | ≤ 20 |
| No. 100 | 4-16 | 6-16 | 4-22 | 5-15 | ≤ 12 |
| No. 200 | 4-7 | 3-6 | 4-7 | 4-7 | 4-7 |

703-2.07 SELECTED MATERIAL.

Replace 1. Type A. with the following:

1.	Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by ATM 204 and ATM 205.  Meet the following gradation as tested by ATM 304:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

703-2.13 STRUCTURAL FILL. Replace Table 703-12 with the following:

TABLE 703-12

AGGREGATE GRADATION FOR STRUCTURAL FILL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3-inch | 100 |
| 3/4-inch | 75-100 |
| No. 4 | 20-55 |
| No. 200 | 0-6 |

Replace Subsection 703-2.16 with the following:

703-2.16 RECYCLED ASPHALT PAVEMENT (RAP). RAP shall be free of contamination and deleterious materials.  RAP maximum particle size shall not exceed 1.5-inch.

CR703.1-100117R

SECTION 705
JOINT MATERIAL

Special Provisions

Sect 705: CR705.1

Related Sect/Sp:  602/CR602.1, 603/CR603, 605/CR605.1, 706/CR706.1

Replace Subsection 705-2.05 with the following:

705-2.05 FLEXIBLE WATERTIGHT GASKETS. Ring gaskets (seals):

1.	Joining rigid concrete (cast-in-place and precast) pipes, manholes, box sections and other structures:

a.	ASTM C443 Specification for Joints for Concrete Pipe and Manholes, Using Rubber Gaskets

b.	ASTM C990 Specification for Joints for Concrete Pipe, Manholes, and Precast Box Sections Using Preformed flexible Joint Sealants (Butyl Rubber Sealant)

c.	ASTM C1628 Specification for Joints for Concrete Gravity Flow Sewer Pipe, Using Rubber Gaskets

d.	ASTM C1619 Specification for Elastomeric Seals for Joining Concrete Structures

Class B (oil resistant performance)

2.	Joining flexible metal pipe (steel and aluminum):

a.	ASTM C443 Specification for Joints for Concrete Pipe and Manholes, Using Rubber Gaskets

b.	ASTM C1619 Specification for Elastomeric Seals for Joining Concrete Structures

Class B (oil resistant performance)

c.	ASTM D1056 Specification for Flexible Cellular Materials-Sponge or Expanded Rubber

(1)	Type 2-Closed cell rubber

(2)	Class B-Oil resistance with low mass change

(3)	Grade 3-Compression-deflection range from 9 to 13 psi

Use continuous flat gaskets with thickness 1/2-inch greater than the nominal depth of the corrugation for bands with projections or flat bands and 3/8-inch for corrugated bands.

3.	Joining plastic pipe:

a.	ASTM D3212 Specification for Joints for Drain and Sewer Plastic Pipes Using Flexible Elastomeric Seals

b.	ASTM F477 Specification for Elastomeric Seals (Gaskets) for Joining Plastic Pipe

Not less than 50% by volume oil resistant polymer

CR705.1-010119

SECTION 706
CONCRETE AND PLASTIC PIPE

Special Provisions

Sect 706: CR706.1-010119

Related Sect/Sp:  602/CR602.1, 603/CR603, 605/CR605.1, 705/CR705.1

Replace Subsection 706-2.07 with the following:

706-2.07 CORRUGATED HIGH DENSITY POLYETHYLENE (HDPE) PIPE FOR CULVERTS, STORM DRAINS, AND UNDERDRAINS. Meet the following:

Corrugated Pipe and Fittings (non-pressurized)

AASHTO M 294 and 252	Type S

Perforations

2.07. Designer clearly identify the type of perforation required for the underdrain, storm and underdrain pipe in Section 605.

1.	Underdrains	Class 2

2.	Underdrains and Storm Drains	Class 1

Joints	Subsection 705-2.05.3.

Polyethylene Pipe Manufacturer

1.	Participate in the National Transportation Product Evaluation Program (NTPEP) work plan for HDPE thermoplastic pipe and listed on the NTPEP audit website displaying NTPEP compliance.

2.	Conduct and maintain a quality control program under the NTPEP.

3.	Provide a manufacturer's certificate of compliance identifying production lots for all materials.

Provide corrugated polyethylene pipe and fittings manufactured from high-density polyethylene (HDPE) virgin compounds. May use clean, reworked polyethylene materials from the manufacturer's own production.

Do not install pipe that is more than two years from the date of manufacture.

CR706.1-050119

SECTION 710
FENCE AND GUARDRAIL

Sect 710: CR710.2.  (CR710.2-020119 combines HSM18-2 with CR requirements)

Related Sect/Sp:  606/CR606/CR606.9.10.13.  (CR606 replacement special for SSHC Section 606. Add CR606.9.10.13, as applicable)

Special Provisions

CR710.2.3. All projects with guardrail.

Replace Subsection 710-2.04 with the following:

710-2.04 METAL BEAM RAIL.

1.	W-Beam and Thrie Beam Guardrail. Meet AASHTO M 180, Class A, Type II. Galvanize after fabrication. Meet the coating requirements of AASHTO M 180 9, Type II Beams and AASHTO M 111 (ASTM A123) as referenced.

2.	Box-Beams Guardrail. Meet:

a.	ASTM A500 Grade B, or

b.	ASTM A501.

Galvanize after fabrication. Meet the coating requirements of AASHTO M 111 (ASTM A123).

CR710.3-020119

710-2.11 GUARDRAIL TERMINALS. W-beam shall meet requirements of AASHTO M 180, Class A, Type II. Galvanize after fabrication.

Components made from rolled pressed and forged shapes, castings, plates, bars, and strips shall meet the coating requirements of AASHTO M 111.  Galvanize after fabrication.

All hardware or fasteners supplied shall meet the coating requirements of AASHTO M 232.

Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail.  Design requirements: 31-inch top of rail height, 8-inch blockouts, W6 x 8.5 steel posts, 12ft-6in w-beam panels, and mid-span splice connection to run of rail.

1.	Parallel Terminals:

a.	Provide terminals meeting the following:

(1)	Crashworthiness: MASH-compliant Test Level 3 terminals

(2)	Length: 50 feet nominal effective length

(3)	End Offset: 0 to 2 feet (25:1 or flatter straight taper) Offset end as shown on the plans.

2.	Buried in Backslope Terminal: Provide MASH-compliant Test Level 3 terminals.

SSHC 2020

SECTION 712
MISCELLANEOUS

Sect 712: Section Specials: CR712.1

Related Sect/Sp:  501, 643/CR643.7, 670/CR670.1, 701

Related Sect/Sp:

Special Provisions

Include 670-CR670.1 when including 712-2.17 & 7.18 CR712.1.

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti-skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

4.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

CR712.1-010109R

SECTION 726
TOPSOIL

Sect 726:  CR726.1 (CR726.1 rplcd CR208)

Related Sect/Sp:  618/CR618.1.2.3, 619/CR619, 621/CR621.1, 641/CR641.1; 724/CR724.1, 727/CR727

Special Provision

Replace Subsection 726-2.01 with the following:

:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area,  and free of prohibited and restricted noxious weeds (Prohibited and Restricted Noxious Weeds 11AAC 34.020 http://plants.alaska.gov/invasives/noxious-weeds.htm ).  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

TABLE 726-1

LIMESTONE REQUIREMENTS

| Soil pH | Limestone, tons/acre |
| --- | --- |
| Above 6.0 | 0 |
| 5.0-6.0 | 1.5 |
| Below 5.0 | 3.0 |

CR726.1-010120

SECTION 727

SOIL STABILIZATION MATERIAL

Special CR727 is a replacement special for the SSHC Section 727.

The special includes much of the SSHC section and adds additional subsections associated with stabilization materials and erosion control.

CR727 is intended to be general, generic, and not specific to a manufacturer's product.  With the number of stabilization materials available and more becoming available each day, writing a spec with the specifics of each type of product, let alone each manufacturer's products, becomes prohibitive.  CR619 and CR727 are written intending for the Contractor to provide the functional longevity and performance required to satisfy the CGP, the SWPPP and Section 641.

Many of the past specials written for stabilization materials have been specific to a manufacturer or a type of erosion control making it difficult for the Contractor to supply other products that may serve the functional longevity and performance as well or possibly better than that specified.  Typically, the Contract documents are not permitted to single out a specific manufacturer's product for use.  If you do not want a specific type of product, say so.  Be careful you have not eliminated viable options or actually restricted the Contractors ability to perform.

Special Provision CR744 is included in CR727 and has been removed from the typical regional specials.

CR727 is coordinated with CR619.  If you include CR727 you will also include CR619.

The materials listed are some of those available, hopefully the more common, if you are designing the stabilization for the project, temporary or permanent and there are materials required or specifics required, edit as needed, and identify the edits by adding the AKSAS-mmddyy at the end of the additions, modifications, etc.

Sect 727:  CR727 Remove this page and the headers will align similar to other sections.

Related Sect/Sp:  618/CR618.1.2.3, 619/CR619, 621/CR621.1, 623/CR623.1, 641/CR641.1, 724/CR724.1, 726/CR726.1

Special Provisions

Replace Section 727 with the following:

SECTION 727
SOIL STABILIZATION MATERIAL

727-2.00 GENERAL.  Free of restricted and prohibited noxious weeds (11 AAC 34) , seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life.  Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH.  Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control.  Use one of the following:

Dry Erosion Control, Stabilization Products.  Hand applied or spread with mulch blower equipment.

1.	Straw.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Weed Management Association (NAWMA) Standards.  In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch.  Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made.  When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth.  The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period).  When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer.  The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise.  Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed.  Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch.  No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

2.	Dried Peat Moss.  Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING.  Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC.  Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs.  (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs.  (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs).  Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs).  Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless.  Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net.  Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs).  Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap.  Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric.  Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn.  Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter.  Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width:  45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight:  20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting.  Woven from twisted yarns available in rolls 45 to 48 inches wide.  Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings.  Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat.  Commercially manufactured ECB.  Use photodegradable netting and biodegradable thread.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life.  ECB may contain coconut or fiber to reinforce the straw.  Straw material shall be certified weed-free straw using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

5)	Woven/Curled Wood blanket.  Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket.  Smolder resistant without the use of chemical additives.  Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber).  Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat.  Use bio/photo degradable netting and thread.

2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs).  A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2.  TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs).  Fiber rolls also referred to as wattles.  Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears.  Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST.  Suitable for serving as a soil amendment or an erosion control material.  Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program.  Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503.  Additionally, meet the requirements of the AASHTO specifications:

1.	Compost Blankets.  Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52.

2.	Compost Filter Berms and Filter Socks.  Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51.

727-2.05 TACKIFIER.  Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground.  Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates.  Tackifier shall hydrate in water and readily blend with other slurry material.  Tackifier options include:

1.	Type A.  Organic tackifier with certification of plant sources; or

2.	Type B.  Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM).  Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

2.	Seam Thread.  Similar durability to the sandbag sack fabric.

3.	Sandbag Fill Material.

a.	Selected Material	703-2.07	Type B

4.	Cinch Ties.  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING.  A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES.  U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide.  Machine-made:  No. 11 gage or heavier steel wire.  Hand-made:  12-inch lengths of No. 9 gage or heavier steel wire.

CR727-050812R

Special Provision

Replace Section 729 with the following:

CR729 is a replacement provision.  Keep all, unless specifically changing a portion of the provision vs using one type or class in the project.

SECTION 729
GEOSYNTHETICS

Sect 729

Related Sect/Sp:  619, 630, 631, 632, 633, 634, 641, 727

729-2.01 GEOTEXTILE FOR SUBSURFACE DRAINAGE, SEPARATION, STABILIZATION, EROSION CONTROL AND EMBANKMENT REINFORCEMENT.

1.	Subsurface Drainage. Meet AASHTO M 288 for Subsurface Drainage, except provide a minimum permittivity of 0.5 sec-1, and meet Class 2 Strength Property Requirements.

2.	Separation. Meet AASHTO M 288 for Separation, except provide a minimum permittivity of 0.50 sec-1, and meet Class 3 Strength Property Requirements.

3.	Stabilization. Meet AASHTO M 288 for Stabilization, except provide a minimum permittivity of 0.50 sec-1, and meet Class 1 Strength Property Requirements.

4.	Erosion Control. Meets AASHTO M 288 for Permanent Erosion Control and meet Class 1 Strength Property Requirements.

5.	Reinforcement. Meet the requirements in Table 729-1 for Type 1 or Type 2.

Package, label, handle and store geotextile materials according to ASTM D 4873.

TABLE 729-1

GEOTEXTILE REINFORCEMENT PROPERTIES

| Property | Test Method | Units | Requirement a |  |
| --- | --- | --- | --- | --- |
|  |  |  | Type 1 | Type 2 |
| Grab Tensile | ASTM D 4632 | lb. | 200/200 | 400/400 |
| Grab Elongation | ASTM D 4632 | % (MD) | 10 | 10 |
| Wide Width Tensile | ASTM D 4595 | lb./in. (ultimate) | 200/200 | 400/400 |
| Wide Width Tensile | ASTM D 4595 | lb./in. (@ 5% strain) | 100/100 | 200/200 |
| Seam Breaking Strength | ASTM D 4632 | lb./in. | 180 | 360 |
| Puncture | ASTM D 6241 | lb. | 500 | 1500 |
| Trapezoidal Tear | ASTM D 4533 | lb. | 100 | 150 |
| AOS | ASTM D 4751 | U.S. sieve size | #30 b | #30 b |
| Permittivity | ASTM D 4491 | sec-1 | 0.20 | 0.20 |
| Flow Rate | ASTM D 4491 | gal./min./ft2 | 10 | 10 |

a.	Minimum Average Roll Values (MARV) in machine-direction (MD) and cross-machine direction (XD) unless otherwise specified.

b.	Maximum average roll value

729-2.02 RESERVED.

729-2.03 PAVING FABRIC. Meet AASHTO M 288 for Paving Fabric.

729-2.04 SILT FENCE. Meet AASHTO M 288 for Temporary Silt Fence.

729-2.05 GEOGRID FOR EMBANKMENT AND ROADWAY STABILIZATION AND REINFORCEMENT. Provide geogrid consisting of a regular network of connected polymer tensile elements with aperture geometry sufficient to provide significant mechanical interlock with the surrounding material.  Provide dimensionally stable geogrid that is able to retain its geometry during construction.  Provide geogrid structure that resists ultraviolet degradation and all forms of chemical and biological degradation encountered in the material in which it is buried.

Package, label, handle, and store geogrid material according to ASTM D 4873.

1.	Stabilization. Provide geogrid that meets the survivability requirements in Table 729-2 and meets the physical requirements in Table 729-3.

2.	Reinforcement. Provide geogrid that meets the survivability requirements in Table 729-2.

TABLE 729-2

GEOGRID SURVIVABILITY REQUIREMENTS

| Property | Test Method | Units | Requirement |  |
| --- | --- | --- | --- | --- |
|  |  |  | Class 1 | Class 2 |
| Ultimate Multi –Rib Tensile Strength a | ASTM D 6637 | lb./ft. | 1230 | 820 |
| Junction Strength a | ASTM D 7737 | lb. | 25 | 25 |
| Ultraviolet Stability (Retained Strength) | ASTM D 4355 | % | 50% after 500 hours of exposure |  |

a.	Minimum Average Roll Values (MARV) in any rib direction.

TABLE 729-3

Geogrid Physical Requirements

| Property | Test Method | Units | Requirement |
| --- | --- | --- | --- |
| 2% Tensile Strength a | ASTM D 6637 | lb./ft. |  400 |
| 5% Tensile Strength a | ASTM D 6637 | lb./ft. |  800 |
| Percent Open Area | COE, CW-02215 | % | 50 – 80 |
| Aperture Size b | Direct measure | in. | 0.5 – 3.0 |

a.	Minimum Average Roll Values (MARV) in machine-direction (MD) and cross-machine direction (XD).

b.	Measured as the spacing between parallel ribs.

CR729-050117

Added Section 731 from the SSHC.2020.

SECTION 730
SIGN MATERIALS

Sect 730:				Replaced SM6 with CR730.2 to match typical CR format. Content is the same. Terminal marker content moved from 606 to 730.

Related Sect/Sp:  606/CR606, 615/CR615

Special Provisions

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR730.1-062204

Replace Subsection 730-2.05 with the following:

730-2.05 FLEXIBLE DELINEATOR POSTS.  Durable fiberglass composite, polymer, or plastic material meeting the dimensions and colors shown on the Plans. Resistant to ultraviolet light, ozone and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

Provide durable markers: resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  Provide the flexibility in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively influence the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole (snow thrown from snowplows)

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering terminal markers.

CR730.2-122217

SECTION 740
SIGNALS AND LIGHTING MATERIALS

Sect 740:  CR740.1.2.3.4.5 	660 is being updated. Attain the latest version from CR DOT Traffic Safety design personnel.

Related Sect/Sp:  660/CR660.1, 661/CR661.1.2, 662/CR662, 667/CR667, 668/CR668.HTWR, 669/CR669.ATR

Special Provisions

740 is being updated by CR for CR. Attain the latest version from CR DOT Traffic Safety design personnel. Section 740 is being maintained as a placeholder, if you do not have signals and lighting materials, delete the Section. Included are past reminder notes to assist you in completing the 740 Section of provisions. CR740.1-060115, CR740.2-022015, CR740.3-050118, CR740.4-050118, CR740.5-050118 are available as individual provision in the AllProvision folder.

740-2.13 STANDARD AUXILIARY EQUIPMENT.

Designer. SOA provisions, replace 740-2.13 7.f. with the following:

7.	Video Detection System.

f.	Service and Support. Supplier, for the term of the Contract, from initial equipment installation through final acceptance Subsection 105-1.16, provide continuous software support, including updates of the MVP sensor, Terra Access Point and supervisor computer applications.

Provide this same service to the Department after acceptance under a separate Contract.

8.	Pan Tilt Zoom Video Camera System

Designer. SOA provision, delete 740-2.13 8.a.1) PAN-TILT ZOOM CAMERA SPECIFICATIONS, Additional Equipment, "Warranty" row.

a.	General.

1)	System Hardware. Furnish only functional new equipment of the name and type as stated on the Plans or approved equal. To be considered an approved equal, equipment must meet or exceed the listed specifications.

	Pan-Tilt-Zoom (PTZ) Camera. Furnish a Camera meeting the following specifications.

PAN-TILT-ZOOM CAMERA SPECIFICATIONS Cont.

| Additional Equipment | Detail |
| --- | --- |
| Enclosure | Outdoor vandal resistant housing with heater and blower |

740-2.11 CONTROLLER CABINET.

Designer.  MOA provision, 740-2.11 1.c.(4)(a) 2nd paragraph. Replace the last sentence with:

1.	Standard Features.

c.	Doors

(4)	Provide Generator Bypass Compartment

(a)

All LED's shall be field replaceable without putting the intersection in flash.

740-2.13 STANDARD AUXILIARY EQUIPMENT.

Designer. MOA provision, replace 740-2.13 7.f. with the following:

7.	Video Detection System.

f.	Service and Support. Supplier, for the term of the Contract, from initial equipment installation through final acceptance Subsection 105-1.16, provide continuous software support, including updates of the MVP sensor, Terra Access Point and supervisor computer applications.

Provide this same service to the Department after acceptance under a separate Contract.

8.	Pan Tilt Zoom Video Camera System.

Designer. MOA provision, delete 740-2.13 8.c.(12)

c.	General Specifications

740-2.18 ROADWAY LUMINAIRES

Designer. SOA/MOA provision, replace 740-2.18 General 2. Luminaires – LED g. Warranty. with the following:

Luminaries General

2.	Luminaries – LED

g.	Failed Equipment and Workmanship. The luminaire and all of its components, for the term of the Contract, from initial installation through final acceptance 105-1.16, when directed, promptly replace failed equipment and repair failed workmanship.

(1)	Negligible light output from more than 10% of the LED packages,

(2)	Moisture inside the optical assembly,

(3)	Driver that continues to operate at a reduced output, and/or

(4)	Other failed conditions that do not meet specifications.

CR740-010120

Designer. SOA/MOA provisions, 740-2.18 General 2. Luminaires – LED h. Submittal Requirements. (15) This item can remain as a submittal requirement … not a performance item.

Designer. 740 provisions require close review to conform to project requirements.  Add or remove individual sentence, paragraph, & subsection content per proj requirements.

Designer. 8. Pan Tilt Zoom Video Camera. Include if project includes a PTZ video camera. Remove if no PTZ video camera in project.  8.a1. Be sure to specify the camera name and type on the Plans, as noted in 8.a1.

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

	Appendix: Number specifications to allow every "Appendix" page to begin on a "right hand," odd numbered page and a blank page on the following page.

Blank Page

APPENDIX B

ENVIRONMENTAL PERMITS

	Appendix: Number specifications to allow every "Appendix" page to begin on a "right hand," odd numbered page and a blank page on the following page.

Blank Page

APPENDIX C

MATERIAL CERTIFICATION LIST

	Appendix: Number specifications to allow every "Appendix" page to begin on a "right hand," odd numbered page and a blank page on the following page.

Blank Page

APPENDIX D

SIGN SHOP DRAWINGS

	Appendix: Number specifications to allow every "Appendix" page to begin on a "right hand," odd numbered page and a blank page on the following page.

Blank Page

APPENDIX E

TEMPORARY CONSTRUCTION EASEMENTS

	Appendix: Number specifications to allow every "Appendix" page to begin on a "right hand," odd numbered page and a blank page on the following page.

Blank Page