SECTION 103
AWARD AND EXECUTION OF CONTRACT

Sect 103: ES11 and Escrow of Bid Affidavit and Escrow of Proposal affidavit

Related Sect/Sp: ES11 FED & SOA funded Proj.  Escrow of Affidavit form is at end of ES11, 103-1.11. See instructions with Affidavit form.

Special Provisions

Add the following Subsection 103-1.11 Escrow of Bid Documentation:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of your Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your Bid for this project.

ES11 application is high risk and or high cost. Use w/"ESCROW" Affidavit form at end of ES11. See instructions with Escrow Affidavit form.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department-designated document Depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that:

a.	The affiant has examined the bid documentation and that it includes all documents used to prepare the bid;

b.	The sealed container contains all bid documentation submitted;

c.	The escrow materials were relied on to prepare the bid; and

d.	Should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request, the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least five days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of any and all escrow documentation (whether hard copy, electronic, or otherwise); to use and review any copies made whether in the presence of the Contractor, or not; and to share copies with staff and consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in all significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders your bid non-responsive.  Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are your property.  Except as otherwise provided herein, the escrow materials cannot be released without your approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the Depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to you once litigation is concluded, outstanding claims are resolved, you have completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11-010106