Special Provisions

Replace Section 651 with the following:

SECTION 651
CONTROL OF WORK – SUPPLEMENTAL REQUIREMENTS

651-1.01 DESCRIPTION. Supplemental requirements for Section 105, Control of Work.

Sect 651:  CR651_SSHC2015.17 CR651. SSP9 Replaced by CR651.

Related Sect/Sp:  SNtB, 105, 108, CR652

Review comments/instructions below at end of Section.

651-1.02 RELATED SECTIONS. Section 105, Control of Work

651-1.03 was a provision in Section 105. 105-1.06 Utilities; has been moved, with minor changes, here.

651-1.03 UTILITIES.  Request locates from the utilities having facilities in the area.

Use the Alaska Digline, Inc. "Locate Call Center" for the following utilities.

ALASKA DIGLINE, INC. Delete from the list below, companies not applicable to the project.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: Aircraft Service International Group (ASIG) Alaska Communications Systems (ACS) Alaska Fiber Star (WCI) Alaska Native Medical Center (ANMC) Alaska Railroad Corporation (ARRC) Anchorage School District (ASD) Anchorage Water & Wastewater Utility (AWWU) Arctic Slope Telephone Assoc. (ASTAC) AT & T Alascom (AT&T) Chevron-Union Oil of California (UNOCAL) Chugach Electric Association (CEA) City of Homer (HPW) City of Valdez Public Works (COV) City of Wasilla (CWPW) ConocoPhillips Alaska, Inc. (CPA) Cook Inlet Pipeline Co. (CIPC) Copper Valley Electric Assoc. (CVE) Copper Valley Telephone Coop. (CVTC) Doyon Utilities, LLC. (DOYON) ENSTAR Natural Gas (ENS) Fairbanks Natural Gas (FNG) Flint Hills Resources (FHR) General Communications, Inc. (GCI) Homer Electric Association (HEA) Kodiak Electric Association (KEA) Marathon Oil Company (MOC) Marathon Pipe Line LLC. (MARATHN) Matanuska Electric Association (MEA) Matanuska Telephone Association (MTA) Municipality of Anchorage Signal & Street Maint. Municipal Light & Power (ML&P) Northern Utility services (NUS) State of AK, DOT/PF Anchorage Street Lights (DOT) Ted Stevens International Airport (TSAIA) Telalaska Inc. (Interior Phone, Eyecom TV & Mukluk Telecom) Tesoro Alaska (TESORO) United Utilities, Inc. (UNITED) XTO Energy (XTO)

State Facility Utilities: before beginning work, contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the District Superintendent's phone number where the project is located, and request locates.

Always include the statement below, requiring the Contractor to call the Central Region Maintenance & Operations Office.

Call the following utilities and agencies directly:

Add utilities and agencies as needed below. Remove the below statement if no additional utilities or agencies added.

Utilities Relocated by Others.

Utility work by others includes relocation work done by utility companies, not the Contractor

	If Utilities are doing work concurrent with project construction include the 1st paragraph. "Utilities will be relocated …"

	If Utility work is not anticipated concurrent with project construction and you wish to include subtopic "Utilities Relocated by Others." Include the 2nd paragraph. Utility work is not anticipated …"

	If Utility work is not part of this project, Delete "Utilities Relocated by Others." thru "Work done by utility owner(s) is as follows:" Keeping Subsection 1.04.

Utilities will be relocated by others concurrently with construction of this project. The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

Utility work is not anticipated for this project, however; if utility work is added to the project the Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.

For utilities being relocated, the Contractor will:

1.	include utility work on the Construction Phasing Plan and Progress Schedule;

Add/delete items 1-9 (below) that the Contractor is responsible for relative to utility work by others. Delete items not applicable.

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information;

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing;

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance;

5	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; Section 409, Hot Mix Asphalt and Surface Treatments, Type R (Crumb Rubber) and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

8.	provide bedding and backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

8.  This does not apply to AWWU, they provide their own backfill.

9.	coordinate with the utility owner(s) and provide potholing services at the locations identified or as directed by the Engineer. Payment will be made under Section 682, Utility Potholing.

9.  Include as needed, slope staking, and potholing, in work done by Utility owners.

Work done by utility owner(s) is as follows:

Fill in utilities information as applicable.

651-1.04 COOPERATION BETWEEN CONTRACTORS.  The following state owned projects may be under construction concurrently with this project.

651-1.04  was a provision in Section 105. 105-1.07 Cooperation between Contractors, it has been moved here.

Add projects that may be ongoing in the same area.

| Project Name: | Project No.: |
| --- | --- |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

651-1.05 was a provision in Section 105. 105-1.19 Interim Completion; it has been moved here.  The following is an Example only.

651-1.05 INTERIM COMPLETION.  This project includes one interim completion phase.

When including 651-1.05 include SNtB Interim Completion Date and CR652-1.04.

Interim Completion Phase:

Date:	30 September, 2009

Work:	Complete all centerline rumble strip installations and replacement of centerline striping in centerline rumble strip installation locations by the interim completion date.

Final Completion Phase:

Date:	See the Invitation to Bid for the final completion date.

Work:	All remaining work in the Contract.

CR651-020118R_SSHC2015.17

The following instructions are the same as occur in Section 105.

Section 105 Control of Work, and Section 651 Control of Work – Supplemental Requirements

	There are no Standard Modifications or Statewide Special Provisions for Sections 105 and 651.

	Provisions intended for Section 105, except CR105.5 and CR105.7, are placed in Section 651 as noted below.

Region and Project Provisions

You will always include the Central Region special provision CR105.7. This provision is outside the instruction that follows.

1.	If you do have region or project provisions for Section 105/Section 651, proceed to Step 2 (nearly always), otherwise you are now done with Section 105 and Section 651.

2.	If you do have project provisions for Section 105 that modify Section 105, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 105 proceed to Step 3 (nearly always), otherwise you are now done with Section 105 and 651.

3.	If you do have region provisions that modify or add to Section 105, or project provisions for Section 105 that add to Section 105, include CR105.5 and CR651 as follows:

a.	In Section 105 include CR105.5

b.	In Section 651, CR651:

(1)	Region provisions identified by subsection:

(a)	651-1.01 Description (always include)

(b)	651-1.02 Related Sections (always include)

(c)	651-1.03 Utilities (include when applicable)

(d)	651-1.04 Cooperation Between Contractors (include when applicable)

(e)	651-1.05 Interim Completion (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	651-1.01 – 1.05 add to or modifying region provisions

(b)	651-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.

Where ARRC draft permit is required, include it in an appendix.  The ARRC permit includes their specification; do not include a DOT&PF specification. Include the Letter of Non-Objection (LNO) and Draft Temporary Construction Permit (TCP) in the Appendix. The Contractor is required obtain the finished permit from the ARRC.