Special Provisions

Replace Section 652 with the following:

SECTION 652
PROSECUTION AND PROGRESS – SUPPLEMENTAL REQUIREMENTS

652-1.01 DESCRIPTION.  Supplemental requirements for Section 108. Prosecution and Progress.

Sect 652: C652	Related Sect/Sp:  CSNtB, 105, 108, 651

Apply to project – see notes

Review comments/instructions below at end of provisions.

652-1.02 RELATED SECTIONS.  Section 108, Prosecution and Progress.

652-1.03 was a provision in Section 108. 108-1.03 Prosecution and Progress; has been moved, with minor changes, here.

652-1.03 PROSECUTION AND PROGRESS.  In Subsection 108-1.03:

	Replace the last sentence in the 1st paragraph with: "Submit the following at the Preconstruction Conference:"

Include C646.1 (Section 646) when using C652-1.03.

	Replace No. 1 with: "A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out, and the contemplated dates the Contractor, subcontractors, and utilities will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated hours of operations and periods of multiple shift work.  Revise the proposed schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer."

652-1.04 LIMITATION OF OPERATIONS. In Subsection 108-1.04:

Designer, include 652-1.04 in all projects. If 652-1.04 creates a conflict, attain permission to remove the provision from the Regional Construction Chief, or Highway Construction Group Chief.

652-1.04. Designer, consider the confines of the project transverse to the roadway with the length parallel to the roadway. If the length of the project is 13,000 feet parallel to the roadway and the width of the project between the DOT&PF right-of-way is not unusual, it may not be necessary to limit the contractor to 11,000 ft. If the width of the project between DOT&PF right-of-way is unusual, it may be that 11,000 ft. is too great. If physical restraints limit the project width, such as a rock cut, the railroad, a body of water, or a wetland, etc., one or both sides, it may be reasonable to increase the maximum length parallel to the roadway. Discuss the length of disturbed ground parallel to the roadway with Construction. Greater disturbed ground at one time, may take greater resources to temporarily contain the erosion, sediment and pollution thereby increasing the cost to the Department. Temporary stabilization payment is contingent sum. The greater the contained area, the more effort the Contractor may be required to expend, temporary stabilization paid by contingent sum (an open checkbook). Unusual is relative, and therefore, discussing the limit of disturbed ground with personnel with experience in these activities is all the more critical.

	Add: "Limit ground disturbed by construction activities and not permanently stabilized between all roadways combined, at any specific time, to a maximum of 11,000 feet parallel to the roadway(s), unless additional length is approved. Stabilize disturbed ground according to Section 641 Erosion, Sediment, and Pollution Control."

652-1.05 FAILURE TO COMPLETE ON TIME. In Subsection 108-1.07:

652-1.05 was a provision in Section 108. 108-1.07 Failure to Complete on Time; has been moved, with minor changes, here.

	Add: "for each calendar day that the work remains incomplete after the expiration of the interim completion date(s) as set forth in Subsection 651-1.05 Interim Completion, the liquidated damages per day given in the table below shall be deducted from any monies due the Contractor."

TABLE 652-1

INTERIM COMPLETION

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Completion Date | Daily Charge |
| --- | --- |
| 1st Interim Completion Date | $0,000 |
| 2nd Interim Completion Date | $0,000 |

C652-24.0610

When including C652-1.05, include C651-1.05 and include SNtB "Interim Completion Date."  Adjust the number of completion dates and dollar amounts per project.  Coordinate with Construction.  This special is Not for Project Completion Date.

Use C652-071519 vs HSP20.3-113020. Central Region does not use pay items for interim completion dates.

The following instructions are the same as occur in Section 108.

Section 108 Prosecution and Progress, and Section 652 Prosecution and Progress – Supplemental Requirements

	Provisions intended for Section 108, except C108.3, C108.4, HSM20-41.43A and HSP20-09, are placed in Section 652 as noted below.

Region and Project Provisions

1.	If you do have region or project provisions for Section 108/Section 652, proceed to Step 2 (nearly always), otherwise you are now done with Section 108 and Section 652.

2.	If you do have project provisions for Section 108 that modify Section 108, submit to the AGs office for approval and incorporate the project provision as approved by the AGs office (very rare).  If you have region and or project provisions that add to Section 108 proceed to Step 3 (nearly always), otherwise you are now done with Section 108 and 652.

3.	If you do have region provisions that modify or add to Section 108, or project provisions for Section 108 that add to Section 108, include C108.3 and C652 as follows:

a.	In Section 108 include C108.3, C108.4, HSM20.41.43A and HSP20-09

b.	In Section 652, C652:

(1)	Region provisions identified by subsection:

(a)	652-1.01 Description (always include)

(b)	652-1.02 Related Sections (always include)

(c)	652-1.03 Prosecution and Progress (include when applicable)

(d)	652-1.04 Limitations of Operations (always include)

(e)	652-1.05 Failure to Complete on Time (include when applicable)

To not use a subsection identified by "include when applicable" is within the intent of the region provisions and therefore the provision region code remains applicable. This includes filling in the missing information as identified in the special's notes etc.

(2)	Project provisions identified by subsection:

(a)	652-1.01 – 1.05 add to or modifying region provisions

(b)	652-1.06, 1.07 …, provision in addition to the region provisions

To add to or modify the region provisions outside the intent, as noted in (1) above requires a project code. To add a new subsection provision requires a project code.

Identify project provision as required by the Project Provisions – Guide, Appendix F – Project Specific Edits – Identifying.