- PART 4

- STANDARD MODIFICATIONS

- AND SPECIAL PROVISIONS

to the STATE OF ALASKA

- STANDARD SPECIFICATIONS

- FOR

- HIGHWAY CONSTRUCTION

2004

- EDITION

- OLD GLENN HIGHWAY,

SOUTH BIRCHWOOD LOOP ROAD TO PETERS CREEK

- ARA-0558 (7) / 50946

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition.  ($25.00)

b.	Alaska Test Methods Manual (Lab & Field), 2007 Edition.  ($25.00)

c.	Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

d.	Quantity Computations

e.	Cross Sections

f.	Geotechnical Report Fire Lake to Ski Road Old Glenn Highway, dated November, 2007.

g.	Final Structural Foundation Engineering Report, Peters Creek Bridge No. 536, Old Glenn Highway, Peters Creek, Alaska, dated July 23, 2009.

h.	Report on Phase II Environmental Site Assessment, Old Glenn Highway Fire Lake to Ski Road, dated January 28. 2009.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix C.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is included in Appendix F.

4.	Laborers Mechanics Minimum Rate of Pay.  The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

5.	Hiring Apprentices.  Administrative Order 226, issued July 24, 2005 establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility, or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, visit http://labor.state.ak.us//lss/forms/ApprenHireReq.pdf

6.	Disadvantaged Business Enterprise (DBE) Program.  Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically Contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A336.  This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit and airport projects as appropriate.  A 0% DBE participation goal does not relieve the Contractor of the Requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, jon.dunham@alaska.gov

7.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

8.	Asphalt Laydown Temperatures.  The Department may monitor laydown temperatures using a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense as specified in Division 400.

9.	High Visibility Clothing.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See subsection 643-3.11.

10.	Signals, Lighting Poles, Load Centers, Controller Assemblies:  The Plans and Specifications are revised for these items including, anchors to the foundations, foundations and conduit installation.

11.	Section 670 Traffic Markings:  This section is recently revised including but not limited to submittal requirements and method of measurement.

12.	Section 107-1.05 of the Standard Specifications for Highway Construction 2004 has been modified to include the Monthly Employment Reporting requirements for construction projects with American Recovery and Reinvestment Act of 2009 (ARRA) funding.  Note the requirement for a Contractor DUNS number.  See www.dnb.com for information about obtaining a DUNS number.

TABLE OF CONTENTS

Section 101 Definitions and Terms	1

Section 102 Bidding Requirements and Conditions	2

Section 103 Award and Execution of Contract	3

Section 104 Scope of Work	6

Section 105 Control of Work	7

Section 106 Control of Material	17

Section 107 Legal Relations and Responsibility to Public	20

Section 108 Prosecution and Progress	28

Section 109 Measurement and Payment	29

Section 120 Disadvantaged Business Enterprise (DBE) Program	30

Section 201 Clearing and Grubbing	38

Section 202 Removal of Structures and Obstructions	39

Section 203 Excavation and Embankment	42

Section 204 Structure Excavation for Conduits and Minor Structures	45

Section 205 Excavation And Fill For Major Structures	46

Section 301 Aggregate Base Course	50

Section 306 Asphalt Treated Base Course	52

Section 401 Hot Mix Asphalt And Surface Treatments	55

Section 402 Tack Coat	73

Section 501 Structural Concrete	74

Section 502 Prestressing Concrete	116

Section 503 Reinforcing Steel	133

Section 504 Steel Structures	147

Section 505 Piling	148

Section 507 Bridge Railing	156

Section 603 Culverts and Storm Drains	158

Section 604 Manholes and Inlets	159

Section 606 Guardrail	160

Section 608 Sidewalks	162

Section 611 Riprap	164

Section 615 Standard Signs	165

Section 616 Thaw Pipe and Thaw Wires	167

Section 618 Seeding	168

Section 622 Interpretive Kiosk	172

Section 639 Approaches	176

Section 641 Erosion, Sediment, And Pollution Control	177

Section 642 Construction Surveying and Monuments	196

Section 643 Traffic Maintenance	199

Section 644 Services to be Furnished by the Contractor	208

Section 645 Training Program	210

Section 646 CPM Scheduling	213

Section 647 Equipment Rental	214

Section 660 Signals and Lighting	217

Section 661 Electrical Load Centers	234

Section 670 Traffic Markings	244

Section 690 Erosion, Sediment And Pollution Control – Measures	249

Section 701 Hydraulic Cement and Pozzolan	251

Section 703 Aggregates	254

Section 705 Joint Materials	257

Section 706 Concrete And Plastic Pipe	258

Section 709 Reinforcing Steel and Wire Rope	259

Section 710 Fence and Guardrail	260

Section 711 Concrete Curing Materials and Admixtures	261

Section 712 Miscellaneous	262

Section 715 Steel For Piles	265

Section 716 Structural Steel	266

Section 719 Steel, Gray-Iron and Malleable-Iron Castings	268

Section 720 Bearings	269

Section 721 Prestressing Steel and Fittings	272

Section 724 Seed	275

Section 726 Topsoil	276

Section 730 Sign Materials	277

Section 740 Signals and Lighting Materials	278

Section 744 Erosion, Sediment, And Pollution Control - Material	288

Appendix A	Erosion and Sediment Control Plan
Appendix B	Construction Surveying Requirements
Appendix C	Materials Certification List
Appendix D	Sign Details
Appendix E	Utility Company Requirements
Appendix F	Permits and Environmental Document

Section 101
Definitions and Terms

Standard Modification

101-1.03 DEFINITIONS. Replace the definitions of SUBGRADE with the following:

SUBGRADE. The soil or embankment upon which the pavement structure is constructed.

E22(1/1/06)

- Delete text of PLANS and replace with:

PLANS. The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32(01/27/07)

- Add the following definition:

QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.

E36(01/27/07)

Section 102
Bidding Requirements and Conditions

- Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE. Replace the second paragraph with the following: The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only. These records are not part of the Contract. These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated. They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records. Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources. The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor. The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23(1/1/06)

102-1.05 PREPARATION OF BID. Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18(6/30/04)

Section 103
Award and Execution of Contract

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65(02/20/09)

Special Provisions

Add the following subsection:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of the Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and information used to prepare the Bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department designated document depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that

a.	the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

b.	the sealed container contains all bid documentation submitted,

c.	the escrow materials were relied on to prepare the bid, and

d.	should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least 5 days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of escrow documentation (whether hard copy, electronic, or otherwise); to use and review copies consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders the bid non-responsive.  Failure or refusal to provide subcontractor bid documentation will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are the Contractor’s property.  Except as otherwise provided herein, the escrow materials cannot be released without the Contractor’s approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to the Contractor once litigation is concluded, outstanding claims are resolved, the Contractor has completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11(01/01/06)

Section 104
Scope of Work

Standard Modifications

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58(07/28/08)

Section 105
Control of Work

Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS. In the third paragraph delete: “(24”x36”)” and replace with: (22”x34”)

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS. In the first sentence of the first paragraph after: “Work performed and materials furnished shall conform to the Plans and Specifications” add: and approved Working Drawings,

In the first sentence of the second paragraph after: “Work or material not conforming to the Plans and Specifications” add: and approved Working Drawings,

E33(01/27/07)

- Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGLINE, INC. Locate Call Center Anchorage: 811 who will notify the following:

Anchorage School District Anchorage Water & Wastewater DOT Street Lights, State of Alaska Enstar Natural Gas GCI Communications Matanuska Electric Assoc Matanuska Telephone Assoc MOA Street Maint. Dept

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits. Utilities scheduled for relocation are addressed in the following utility specific sections.

Utilities will be relocated by others concurrently with construction of this project.  A utility company performing ground disturbing activity on the project shall be identified in the SWPPP.  The Contractor will be responsible for controlling sediment and erosion and stabilizing areas disturbed during underground utility relocation per Section 641.

Right of Way and/or Construction surveying is required before utility relocation.  Survey control such as centerline or right-of-way shall be provided prior to relocation commencing as well as any required structure locations.

Payment will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract and/or

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

R3(05/24/07)

Clearing and Grubbing is required to accommodate utility relocation.  Payment will be made under Item 201(3A) Clearing and Grubbing.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the time you have the relocations described below scheduled to begin. The Utility Companies shall not be required to work in more than one location at a time and shall be allowed to complete a specific section of work before beginning with another section.

Relocation or adjustment of underground utility appurtenances shall not normally be performed when the ground is frozen. In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

When utility company facilities are not proposed for relocation, use locate information to determine the final location of construction elements such as excavation limits, pole locations and other underground activities to avoid conflict with existing utilities.

Specific coordination requirements for the utilities are included below:

ALL UTILITY COMPANIES:  Additional time over that shown in the following descriptions of work may be required if contaminated soils are encountered by the utilities during their relocation work. If contaminated soils are encountered, the utility will stop work and notify the Engineer so that the Engineer and Contractor can deal with the contaminated material.

MATANUSKA ELECTRIC ASSOCIATION (MEA): MEA has existing overhead primary circuits running within the Old Glenn Highway (OGH) corridor. Some of these facilities are located in easements outside the highway right-of-way; others are located within the right-of-way. Allow time for MEA to relocate facilities as noted:

1)	Retirement of the existing OH pole in conflict with the proposed fill section between the roadway and pathway improvements at approx. OGH Station 333+75, 35’ Lt.  MEA will require one (1) Calendar day to complete this work.

2)	Two (2) MEA poles are in conflict with the cut slopes of the proposed roadway and pathway improvements.  MEA will retire the existing poles at approx. OGH Stas. 365+45, 33’ Lt. and 364+47, 82’ Lt.  These poles will be replaced with a new pole and a guy pole with down guy and anchor.  New conductor will be installed to the relocated poles.  MEA will require three (3) Calendar days to complete this work.

3)	Retirement of the two (2) existing OH poles in conflict with the proposed pathway improvements at approx. OGH Stations 377+55, 63’Lt. and 377+03, 107’ Lt.  MEA will require one (1) Calendar day to complete this work.

4)	An MEA pole is in conflict with the proposed pathway at approx. OGH Sta. 412+80, 30’ Lt. This pole will be retired.  A new pole will be installed at approx. Sta. 412+80, 45’ Lt. A guy pole will be installed at approx. OGH Sta. 414+65, 55’ Lt. with a down guy and anchor to complete this relocation.  MEA will require three (3) Calendar days to complete this work.

5)	An existing MEA pole is in conflict with the cut slope for the proposed pathway at approx. OGH Sta. 455+60, 50’ Lt.  This pole will be retired.  A new pole will be installed outside of the slope limits in alignment with the existing overhead facilities.  Another pole at approx. Sta. 455+75, 87’ Lt. with a double deadend assembly will also be required to complete this relocation.  MEA will require three (3) Calendar days to complete this work.

6)	A metered light pole at approx. OGH Sta. 463+15, 40’ Rt. is in conflict with the proposed drainage improvements.  This pole, conductor and associated guy will be retired.  No relocation is proposed at this location.  MEA will require one (1) Calendar day to complete this work.

7)	A light pole at approx. OGH Sta. 468+35, 25’ Rt. is within the roadway cut slopes. A service pole at approx. OGH Sta. 467+90, 40’ Lt. is in conflict with the proposed pathway improvements.  These poles and associated conductor will be retired.  No relocation is proposed at this location.  MEA will require one (1) Calendar day to complete this work.

8)	An existing down guy and anchor assembly are in conflict with the slope limits at Needels Loop at approx. OGH Sta. 476+50 Rt.  The down guy and anchor will be retired.  A new overhead guy and guy pole with down guy and anchor assembly will be installed across OGH at approx. Sta. 475+40, 98’ Lt.  MEA will require two (2) Calendar days to complete this work.

9)	An existing light pole at OGH Sta. 478+75, 35’ Lt. is in conflict with the proposed slope limits and drainage improvements.  MEA owns the meter and transformer on the existing light pole.  The meter and transformer will be retired by MEA.  The DOT contractor will remove this pole once MEA has removed their facilities.  MEA will require one (1) Calendar day to complete this work.

10)	At Sta. 485+30, 95’ Lt., MEA has two (2) poles side by side. The pole closest to OGH is in conflict with the proposed cut slopes.  This pole will be retired and replaced with a longer pole in the same position to support the existing pole which will remain in place.  MEA will require three (3) Calendar days to complete this work.

11)	Two (2) existing MEA poles are in conflict with the proposed pathway improvements at Raven Street and Old Glenn Highway.  Pole C75-11-7-3 at approx. Sta. 521+99, 48’ Rt., and Pole C75-11-7-2 at approx Sta. 523+35, 65’ Rt. will be retired and relocated into an easement south of the existing pole line.  New conductor will be installed as well as anchors and down guys to support the new poles.  MEA will require three (3) Calendar days to complete this work.

12)	LC 349L: MEA will tap into an existing transformer on an existing pole C135A near the Fire Station on Old Glenn Highway to provide service to LC349L. An additional secondary riser will be installed on this pole (C135A). MEA will trench secondary cable in conduit from the pole to the load center.   A meter will also be added.  MEA will require one (1) Calendar day to complete this work.

13)	LC 526L: MEA has provided a revised location for this load center.  This description is based on relocation of the new LC 526L to approx. OGH Station 523+40, 50’ RT to provide clear zone for the bike path.  MEA will install a transformer on the new pole C75-11-7-2. This pole will be relocated as part of the MEA Standard Agreement 1-50946-09-45.  The suggested location for the proposed load center is suggested to be northeast of the new pole C75-11-7-2.   MEA will install a secondary riser on the pole, install a meter and trench secondary cable in conduit from the pole to the load center. MEA will require one (1) Calendar day to complete this work.

14)	LC 486F and 486L: MEA will tap into an existing transformer on an existing pole C95-5 near the intersection of N. Birchwood Loop and Old Glenn Highway to provide services to LC486F and LC 486L through a new pedestal S1. Two secondary risers will be installed on this pole (C95-5). MEA will trench secondary cable in conduit from the pole to the service pedestal and then to two load centers as well as the existing Remote Meter Pedestal (RMP).   Two meters will also be added the RMP.  MEA will require one (1) Calendar day to complete this work.

The MEA contact is Eric Sanford at (907) 761-9274.  The MEA fax number for written notification is (907) 745-3260.

GENERAL COMMUNICATIONS, INC. (GCI): GCI has existing buried cable, overhead cable and fiber optics running within the Old Glenn Highway (OGH) corridor. Some of these facilities are located in easements outside the highway right-of-way; others are located within the right-of-way. GCI will be relocating facilities located on existing MEA poles requiring relocation:

1)	Delash and relash existing aerial GCI facilities - .875 coax on two (2) existing MEA poles, approx. Stas. 364+47, 90’ Lt. and 365+40, 30’ Lt., scheduled for retirement and replacement with one (1) new pole. GCI will coordinate with MEA to relocate aerial facilities.  GCI will require two (2) Calendar days to complete this work.

2)	Relocate existing UG .875, .500 (~ 100’ segment), .625 (~ 900’ segment) coax cables and the associated pedestals from approx. Sta. 405+75 through Amonson Road (approx. Sta. 423+25) and along the eastern side of Amonson Road to a riser pole approx. 450 ft south.  GCI will coordinate with Enstar to joint trench the relocated facilities to the extent that joint trench is available.  GCI will require three (3) Calendar days to complete this work.

3)	Relocate existing UG .875 and .500 (~350’ segment) coax cables and the associated pedestal from approx. Sta. 450+75 through Skyview Road (approx. Sta. 456+30) and along the eastern side of Skyview Road to a riser pole approx. 175 ft south.  GCI will coordinate with Enstar to joint trench the relocated facilities to the extent that joint trench is available.  GCI will require four (4) Calendar days to complete this work.

4)	Delash and relash existing aerial GCI facilities - .875 coax and FO 80 on an existing MEA pole, approx. Sta. 485+30, 100’ Lt., scheduled for retirement and replacement. GCI will coordinate with MEA to relocate aerial facilities.  GCI will require two (2) Calendar days to complete this work.

5)	Delash and relash existing aerial GCI facility - .500 coax on two existing MEA poles, approx. Stas. 521+95, 47’ Rt. and 523+30, 60’ Rt., scheduled for retirement and replacement within a new easement. GCI will coordinate with MEA to relocate aerial facilities.  GCI will require two (2) Calendar days to complete this work.

The GCI contact is Joe Whittaker at (907) 229-9176.

ENSTAR NATURAL GAS COMPANY (ENSTAR): ENSTAR relocation work will be conducted within the Old Glenn Highway project limits and will need to be coordinated with the Contractor’s work.  When ENSTAR is involved with joint trenching operations with MTA and/or GCI, ENSTAR will take the lead in trenching.

1)	The existing 6” plastic gas main from BOP (approx. Station 316+55 Lt. to North Birchwood Loop (Sta. 468+40 Lt.), is in conflict with the proposed roadway, storm drain and pathway improvements and will be relocated to the edge of right of way where possible.   There are some existing structures and existing fiber optic cables that require Enstar to move further away from the Right of Way line in some segments. The existing 2” gas mains providing gas to side streets will be tied into the relocated 6” gas main.  Existing services connections shall be tied into the relocated 6” main. This relocation work will be done in coordination with MTA relocation.  Enstar and MTA will relocate within a joint trench.  There will be boring for some segments of this main relocation.  Enstar will require forty-five (45) Calendar days to complete this work.

2)	The existing 4” plastic gas main from BOP (approx. OGH Sta. 316+55 Rt.) to Sta. 326+00 Rt. is in conflict with the drainage ditch improvements and will be relocated to 5’ from the Right of Way (ROW) line.  Two (2) existing 2” mains on Division and Laughlin Streets will be tied in to the relocated 4” gas main. Existing services connections shall be tied into the relocated 4” main.    There will be a 30” bore in this main relocation.  Coordination with the Department’s Contractor shall be required.  Enstar will require three (3) Calendar days to complete this work.

3)	An existing gas main ranging in size from 2” to 4” plastic crosses the OGH centerline at Sta. 324+35.  This crossing will be relocated due to conflict with the proposed roadway improvements.  The relocated facility shall be a 2” main installed at OGH Sta. 322+80.  This main will be tied in to the relocated 4” and 6” gas mains.  Enstar will require one (1) Calendar day to complete this work.

4)	The existing 4” plastic gas main, from OGH Sta. 328+50 Rt. to Sta. 333+50 Rt., is in conflict with the proposed cut slopes for the roadway improvements and will be relocated to 5’ from the ROW line. Existing services connections shall be tied into the relocated 4” main.  .  Enstar will require one (1) Calendar day to complete this work.

5)	The existing 4” plastic gas main from OGH Sta. 333+50 Rt. to Sta. 335+50 Rt., is in conflict with the proposed cut slopes for the roadway improvements and will be lowered in place.  Coordination with the Department’s Contractor shall be required.  Enstar will require one (1) Calendar days to complete this work.

6)	The existing 4” plastic gas main from OGH Sta. 338+30 Rt. to Sta. 339+00 Rt. will require lowering in place due to cut slopes.  An additional 70 ft. may also require lowering due to driveway cut slopes from approx. Sta. 339+00 to 339+70.  Coordination with the Department’s Contractor shall be required.  Enstar will require two (2) Calendar days to complete this work.

7)	The existing 4” plastic gas main from OGH Sta. 350+00 Rt. to Sta. 358+20 Rt., is in conflict with the proposed cut slopes and drainage ditches for the roadway improvements and will be relocated to 5’ from the ROW line.  Existing services connections shall be tied into the relocated 4” main.  Enstar will require three (3) Calendar days to complete this work.

8)	The existing 4” plastic gas main from OGH Sta. 359+40 Rt. to Sta. 372+12 Rt., is in conflict with the proposed cut slopes, drainage structures and ditches for the roadway improvements and will be relocated to 5’ from the ROW line.  Existing services connections shall be tied into the relocated 4” main.  Enstar will require four (4) Calendar days to complete this work.

9)	The existing 4” plastic gas main from OGH Sta. 375+40 Rt. to Sta. 377+40 Rt. will require lowering in place due to cut slopes.    Coordination with the Department’s Contractor shall be required.  Enstar will require two (2) Calendar days to complete this work.

10)	The existing 4” plastic gas main from OGH Sta. 377+40 Rt. to Sta. 396+75 Rt., is in conflict with the proposed cut slopes, driveway cuts, drainage structures and ditches for the roadway improvements and will be relocated to 5’ from the ROW line.  Existing services connections will be cut into the new 4” main.  Enstar will require nine (9) Calendar days to complete this work.

11)	The existing 4” plastic gas main from OGH Sta. 396+75 Rt. to Sta. 426+10 Rt., is in conflict with the proposed roadway, drainage and pathway improvements and will be relocated to 5’ from the ROW line where possible.  The existing 2” gas mains providing gas to side streets will be tied into the relocated 4” gas main.  The existing services connections will be cut into the new 4” main. There will be boring for some segments of this main relocation.  This work will be done in coordination with MTA and GCI relocation.  Enstar, GCI and MTA will relocate within a joint trench.  GCI will be in the joint trench from Sta. 405+75 to 423+30.  Enstar will require fifteen (15) Calendar days to complete this work.

12)	The existing 4” plastic gas main from OGH Sta. 426+10 Rt. to Sta. 456+50 Rt., is in conflict with the proposed roadway, drainage and pathway improvements and will be relocated to 5’ from the ROW line where possible.  The existing 2” gas mains providing gas to side streets will be tied into the relocated 4” gas main.  The existing services connections will be cut into the new 4” main. There will be boring for some segments of this main relocation.  This work will be done in coordination with segments of MTA and GCI relocation.  Enstar and MTA and Enstar and GCI will relocate within joint trenches.  GCI will be in the joint trench from Sta. 450+75 to 455+50. Enstar will require fifteen (15) Calendar days to complete this work.

13)	The existing 4” plastic gas main from OGH Sta. 456+50 Rt. to Sta. 489+30 Rt., is in conflict with the proposed roadway, drainage and pathway improvements and will be relocated to 5’ from the ROW line where possible.  The existing 2” gas mains providing gas to side streets will be tied into the relocated 4” gas main.  The existing services connections will be cut into the new 4” main.    Enstar will require eleven (11) Calendar days to complete this work.

14)	The existing 4” plastic gas main from OGH Sta. 493+60 Rt. to Sta. 502+70 Rt., is in conflict with the proposed roadway, drainage and pathway improvements and will be relocated to 5’ from the ROW line where possible.  The existing 2” gas mains providing gas to side streets will be tied into the relocated 4” gas main.  The existing services connections will be cut into the new 4” main.    Enstar will require three (3) Calendar days to complete this work.

15)	The existing 4” plastic gas main from OGH Sta. 502+70 Rt. to Sta. 513+00 Rt. shall require lowering in place due to a reduced depth of cover from the proposed cut slopes at this location. The existing 2” gas mains providing gas to the side street will be lowered for 40 ft. and tied into the lowered 4” gas main.  Coordination with the Department’s Contractor shall be required.  Enstar will require three (3) Calendar days to complete this work.

16)	The existing 4” plastic gas main from OGH Sta. 522+00 Rt. to Sta. 522+90 Rt. shall require lowering in place due to a reduced depth of cover from the proposed cut slopes at this location.  Coordination with the Department’s Contractor shall be required.  Enstar will require one (1) Calendar day to complete this work.

17)	The existing 4” plastic gas main from OGH Sta. 524+40 Rt. to Sta. 530+00 Rt. is in conflict with the proposed roadway, drainage and pathway improvements and will be relocated to 5’ from the ROW line where possible.   Coordination with the Department’s Contractor shall be required.  Enstar will require two (2) Calendar days to complete this work.

When working near Enstar Natural Gas facilities, adhere to the requirements set forth in “Safety Requirements for Excavation Adjacent to Natural Gas Pipelines”, attached to these specifications as an appendix.

The Enstar contact is Steve Cooper at (907) 264-3712.

MATANUSKA TELEPHONE ASSOCIATION (MTA): Conflicts exist with MTA lines within the project limits. MTA will be relocating telecommunications facilities.

1)	MTA’s 200 pair underground (UG) cable varies in location within the Right-of-Way (ROW) from the BOP to approximately Station 367+50 and conflicts with roadway, pathway and drainage construction. MTA will abandon the existing cable and replace with new 200 pair cable. The new cable will generally be located along the left edge of ROW, offset from 15 feet to 5 feet inside the ROW line. Most of this cable will be installed in a joint trench with ENSTAR.

Relocation through this section of highway includes a bore across an approach between Stations 323+85 and 324+35, left, and a bore across the Old Glenn Highway (OGH) at Station 333+50. The bored crossing will replace a 12 pair aerial cable, where a pole conflicts with the roadway, with a 25 pair UG cable in 2-inch conduit.

At Station 328+60, 95’ left, copper and fiber optic cable will be potholed to determine if there is a conflict. If so, enough cable will be exposed to recover sufficient slack to eliminate the conflict.

An UG crossing near Station 342+50 and a pedestal serving a structure within the ROW will be removed.

A 25 pair aerial crossing near Station 362+30 will be removed along with an MTA pole. A new 25 pair aerial crossing with poles will be installed on MEA poles C132 and C132-1 to span the ROW. This crossing is located near the boundary between the Eagle River (694) and Chugiak (688) exchanges. A new pedestal will be installed at approximately Station 362+30, 140 ft. left, marking the terminus of new cable installation within the Eagle River Exchange.

An existing 100 pair cable and pedestals will be removed between Station 365+43, 32 ft left and Station 366+74, 127 ft left. A new 100 pair crossing and 3.5 inch conduit will be installed by bore at Station 367+50. Approximately 74 feet of cable will be installed along the left edge of ROW in a joint trench with ENSTAR. The right side terminus will be connected with aerial facilities. Coordinate right side work with nearby culvert installations.

MTA will require thirty (30) Calendar days to complete this work.

2)	MTA will abandon an existing 50 pair UG crossing near Station 391+75 that is in conflict with roadway, pathway and guardrail work. No replacement crossing cable is needed; the feed will be brought in from the north by installing a 50-pair UG cable along with right edge of ROW from approximately Station 395+25, 43 ft right to Station 404+65, 55 ft right. Pedestals will be installed at each end. This cable will be installed in a joint trench with ENSTAR from 399+85 north.

A 100 pair UG crossing located near Station 404+80 and a 25 pair UG cable and buried filled cable service lines in conflict with roadway, pathway and guardrail work will be abandoned. A new 25 pair cable with pedestals will be installed along the left side of roadway using existing lines located along the ROW as a feed. This installation will be in a joint trench with ENSTAR.

A 6 pair service line between Station 404+75, 37 ft right and 405+90, 65 ft right will be abandoned where it conflicts with ditching and will be replaced with a new 6 pair UG cable installed along the edge of ROW.

MTA will abandon their 100 pair UG cable from Station 404+75, right to approximately 417+50 right. This cable conflicts with ditching. A new 100 pair cable will be installed along the edge of ROW in a joint trench with ENSTAR. From this location to approximately 70 ft south of the intersection of Swanee Court and Bending Birch Drive, MTA will abandon its remaining segment of 100 pair cable. This will be replaced with a 50 pair UG cable.

MTA will abandon a 300 pair UG cable that runs along Bending Birch Drive and continues along the OGH to approximately Station 426+11, 42 ft right. This cable is in conflict with ditching. MTA will replace this cable with a 200 pair cable extending from the new pedestal at Station 417+55, 54ft right to Station 423+85, 55 ft right. This will be installed in a joint trench with ENSTAR.

An existing 900 pair UG crossing located near Station 423+40 will be abandoned along with a segment of 900 pair cable  and 100 pair cable along the north side of Amonson Road. MTA will install a new 600 pair crossing in a bore at approximately Station 424+00. The north end will be connected to existing cable in a new handhole near Station 423+40, 135 ft left. The south end will be connected to new cables in a pedestal located at approximately 423+85, 55 ft right. A new 100 pair UG cable will extend sough along Amonson Road. A new 300 pair cable will be extended east to Station 426+11, 42 ft right where it will be spliced to an existing 300 pair cable in an existing pedestal. The cable along Amonson Road will be installed in a joint trench with GCI and ENSTAR.

Adjustments to 25 pair cable stubouts will be made in existing pedestals located at 428+68, 43 ft right, 430+58, 42 ft right and 432+59, 43 ft right.

MTA will require twenty-five (25) Calendar days to complete this work.

3)	MTA’s 300 pair UG cable from Station 444+94, 33 ft right to 456+97, 175 ft right is in conflict with ditching and excavated backslopes. MTA will abandon this cable and install a new 100 pair cable between Station 444+94, 33 ft right and Station 450+45, 47 ft right. New pedestals will be installed and cable will be placed in a joint trench with ENSTAR.

A new 12 pair crossing will be installed using a bore and 3.5 inch conduit near Station 456+50.  The north end will connect to existing cable in a new pedestal located at Station 455+63, 52 ft left. The south end will connect to existing cable in an existing pedestal at Station 456+97, 175 ft right.

MTA’s existing 400 pair UG cable is in conflict with drainage and ditching from Station 456+97, 175 right to Station 458+55, 51 ft right. This cable will be abandoned and replaced with a 300 pair cable and a pedestal located at Station 458+55, 51 right to connect to existing 400 pair cable.

MTA will require ten (10) Calendar days to complete this work.

4)	MTA has a 400 pair UG cable from Station 460+80, 49 ft right to 462+75, ~ 100 ft right. This cable is in conflict with ditching and excavation and will be abandoned. MTA has a 150 pair cable and a 300 pair cable from Station 462+75 to ~ Station 467+58, right. The 150 pair cable continues to Station 476+50, 60 ft right. These cables are in conflict with ditching and excavation and will be abandoned. MTA has a 900 pair UG crossing in duct near Station 467+58. This cable is in conflict with roadway, pathway and drainage work and will be abandoned. A 25 pair UG crossing near Station 477+37 and a 50 pair UG cable extending from Station 476+94, 65 ft right to Station 481+73, 157 ft right are in conflict with roadway and retaining wall work and will be abandoned.

Relocation work in this area includes installation of a 600 pair UG cable from Station 460+80, 49 ft right to Station 466+40, 40 ‘ right; then crossing the OGH by bore and 5.3 inch conduit at Station 466+50 and continuing to Station 467+94, 126 ft left in a joint trench with ENSTAR. A 200 pair UG cable will extend from Station 467+94, 126 ft left to Station 476+50, 105 ft left. From that point it will cross OGH with a bore and 3.5 inch conduit to Station 476+50, 60 ft right. A 50 pair cable will continue from that point to a new pedestal along Lace Road near Station 481+73, 157 ft right.

Other relocation work includes a 100 pair UG cable from Station 466+40, 40 ft right to a new pedestal at Station 467+58, 47 ft right. A 25 pair UG cable will extend from this pedestal to Station 468+35, 27 ft right. Another 25 pair UG cable will extend from Station 467+58 to the south side of Needels Loop, follow along Needels Loop and cross the side road in 2-inch conduit near the lot line between lots 26 and 24.

MTA will require five (5) Calendar days to complete this work.

5)	MTA has a 200 pair UG crossing of both the OGH and the Glenn Highway at approximately Station 511+20. This crossing will be abandoned and the 200 pair trimmed out near the aerial service line to Peters Creek Christian Center.

MTA will require one (1) Calendar day to complete this work.

6)	MTA has a 12 count fiber optic (FO) cable and a 600 pair cable crossing OGH from approximately Station 521+70 left to 522+50 right. A 100 pair cable is located along the east side of Raven Street and wrapping around the north side of Lot 1 along the OGH. MTA will require potholing in this area to determine the alignment and depth of cables and to determine if there is a conflict. If so, cables will be exposed an adequate length to acquire sufficient slack to eliminate the conflict.

MTA will require one (1) Calendar day to complete this work.

MTA’s contact is Jim Gage at (907) 761-2544

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following other project(s) may be under construction concurrently with this project:

1.	Old Glenn Highway, Fire Lake to South Birchwood Loop.  ADOT&PF Resident Engineer Mike Morris, phone 269-0460.

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impacts on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

Standard Modifications

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following at the end of this subsection: Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance. The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance. If the Contractor fails to take the corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33(01/27/07)

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:  “Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:  “Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

E59(07/28/08)

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue.

E19(6/30/04)

- Special Provisions

105-1.17 CLAIMS. Add the following: Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.

R93(3/21/01)

Section 106
Control of Material

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. In fifth paragraph, in two places remove the text: “Approved Products List” and replace with: Qualified Products List

E36(01/27/07)

- Special Provisions

106 1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap, pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

R13(02/07/05)

Standard Modification

106-1.02 LOCAL MATERIAL SOURCES.

1.	a.	General. Within Item a. delete text and replace with: Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4. When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources. Replace the first paragraph with the following: The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection. When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

4.	d.	Available Sources. Replace the second paragraph with the following: When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

4.	e.	Excluded Material Sources. Replace the paragraph with the following: Some material sources may not be considered acceptable regardless of location or ownership. The bid documents may identify some material sources excluded from use. The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.

E24(1/1/06)

- Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE. The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department. The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents. The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items. The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

Within 30 days after the Contract award submit 4 collated copies with tabbed item numbers of a complete portfolio of materials proposed for installation to the Project Engineer for review and acceptance.  Include a table of contents with item numbers in the portfolio(s).  The body of the portfolio shall contain the catalog cuts including the manufacturers name, certifications, type of product, size, model number, conformance to Contract specification and other data as may be required, including manufacturer’s maintenance and operations manuals.

Each copy of each submittal shall include a Submittal Summary sheet. The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department. The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received. The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed. The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections. The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department. The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.

E34(01/27/07)

Section 107
Legal Relations and Responsibility to Public

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual. The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits. Additionally, provide the Engineer a written statement that permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following: The Department has received the following permits on the Contractor’s behalf:

1.	The Alaska Department of Fish and Game, Division of Habitat issued a Fish Habitat Permit (No. FH 09-II-0188) dated November 19, 2009 for work in Peters Creek.  The Contractor shall submit a bridge demolition plan to the Division of Habitat for approval prior to removal of the existing bridge.  This permit expires December 31, 2011.

2.	The Alaska Department of Environmental Conservation (ADEC), Division of Water issued a Storm Water Disposal Non-objection letter dated November 18, 2009.

3.	A U.S. Army Corps of Engineers (COE) Nationwide Permit No. 14 (POA-2009-1069) was issued November 24, 2009 for work in wetlands.

4.	The Municipality of Anchorage (MOA), Department of Public Works, Flood Hazard Permit (No 09-0019-00) was issued November 20, 2009 for work in Peters Creek.

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements of this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

Special Provisions

107-1.05 FEDERAL AID PROVISIONS.

Add the following after paragraph two:

Monthly Employment Reports. Submit Monthly Employment Reports on Form 25D-1589. The Contractor shall submit both a hard copy with signed certification statement, and an electronic file copy in excel spreadsheet format, to the Engineer.

Each Monthly Employment Report is due at 5:00 pm five calendar days after the last Friday of the reporting month.

For each occurrence where a Monthly Employment Report is not submitted on or before the due date, the Department will deduct liquidated damages from the monies owed the Contractor in the amount of twenty-five hundred dollars ($2,500).  In addition to any damages for failure to report on-time, the Department will withhold one hundred percent (100%) of payment for all progress payments due the Contractor, until all Monthly Employment Reports which are due but have not been submitted are complete and delivered to the Project Engineer.  No interest will be paid on amounts withheld due to Contractor’s failure to submit Monthly Employment Reports on time and as required in this subsection.

Submit Monthly Employment Reports that include:

•	Contractor’s name and address.

•	Reported Month: mm/yyyy.

•	Certification Statement:

“Any intentional misrepresentation or omission made in connection with the attached Monthly Employment Report may be cause for suspension, a determination of non-responsibility on future bids, and may be cause for revocation of award, default, or debarment. The person or entity making the false statement or omission is subject to any and all civil and criminal penalties available pursuant to applicable state and federal law.

I certify the information contained in the attached Monthly Employment Report is true, correct, and complete. (Signature and printed name of the person preparing the Monthly Employment Report, and Date)”

Each month the Contractor shall provide all information required by the Form 25D-1589. Each Form 25D-1589 Monthly Employment Report shall include:

•	Report Month: the month and year covered by the report, as mm/yyyy. The reporting month includes the Saturday following the last Friday of the preceding month to and including the last Friday of the reporting month.

•	Contracting Agency: “State”

•	Federal-Aid Project Number: the federal-aid project number included on the title sheet of the plans.

•	State Project Number: the AKSAS project number included on the title sheet of the plans.

•	Project Location: “Alaska”

•	Contractor Name and Address: The name and address of the Contractor, including street address, city, state, and zip code.

•	Contractor DUNS Number: The Contractor’s unique nine-digit number issued by Dun & Bradstreet. Followed by the optional 4 digit DUNS Plus number.

•	Employment Data: The Contractor shall report the direct, on-the-project jobs for their workforce , and the workforce of all subcontractors, lower tier subcontractors, and owner-operators active during the reporting month. These jobs include all workers actively engaged in work on the jobsite or actively engaged in work directly related to the project occurring in the project office, in the home office or telework from a home or other alternative office location. This also includes any engineering personnel, inspectors, sampling and testing technicians, and lab technicians performing work directly in support of the project. This does not include material fabricator’s, material suppliers such as steel, culverts, guardrail, and does not include engineering personnel, inspectors, sampling and testing technicians, and lab technicians employed by the Department or the Department’s consultant.  The form requests specifically:

o	Subcontractor Name: The name of each subcontractor, lower tier subcontractor, and owner-operator that was active on the project for the reporting month.

o	Employees: The number of project employees on the Contractor’s workforce each month, and the number of project employees for each of the active subcontractors, lower tier subcontractors, and owner-operators for the reporting month. Do not include material suppliers.

o	Hours: The total hours on the specified project for all employees reported on the Contractor’s project workforce that month, and the total hours for all project employees reported for each of the active subcontractors, lower tier subcontractors, and owner-operators that month.

o	Payroll: The total dollar amount of wages paid by the Contractor that month for employees on the project, and the total dollar amount of wages paid by each of the active subcontractors, lower tier subcontractors, and owner-operators  that month. Payroll includes wages only, and does not include overhead or indirect costs.

•	Prepared by:

o	Name: The person responsible for preparation of the form and their job title.

o	Date: The date that the Contractor completed the employment form. Reported as mm/dd/yyyy.

ARRA Required Contract Provisions

Section 902 of the American Recovery and Reinvestment Act (ARRA) of 2009 requires that each contract awarded using ARRA funds must include a provision that provides the U.S. Comptroller General and his representatives with the authority to:

(1)	examine any records of the contractor or any of its subcontractors, or any State or local agency administering such contract, that directly pertain to, and involve transactions relating to, the contract or subcontract; and

(2)	interview any officer or employee of the contractor or any of its subcontractors, or of any State or local government agency administering the contract, regarding such transactions.”

Accordingly, the Comptroller General and his representatives shall have the authority and rights as provided under Section 902 of the ARRA with respect to this contract, which is funded with funds made available under the ARRA. Section 902 further states that nothing in this section shall be interpreted to limit or restrict in any way any existing authority of the Comptroller General.

Section 1515(a) of the ARRA provides authority for any representatives of the Inspector General to examine any records or interview any employee or officers working on this contract.  The contractor is advised that representatives of the inspector general have the authority to examine any record and interview any employee or officer of the contractor, its subcontractors or other firms working on this contract. Section 1515(b) further provides that nothing in this section shall be interpreted to limit or restrict in any way any existing authority of an inspector general.

The Contractor shall insert, in each subcontract, all of the stipulations contained in these ARRA Required Contract Provisions, and further require their inclusion in any lower tier subcontract or purchase order that may in turn be made. The ARRA Required Contract Provisions shall not be incorporated by reference in any case. The prime contractor shall be responsible for compliance by any subcontractor, lower tier subcontractor, and owner-operator, with these ARRA Required Contract Provisions.

(04/27/09)ES17

| MONTHLY EMPLOYMENT REPORT, FORM 25D-1589 |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AMERICAN RECOVERY AND REINVESTMENT ACT |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Report Month: (mm/yyyy) |  |  | 2. Contracting Agency |  |  |  |  |  |  |  |  |  |
| 3. Federal-Aid Project Number |  |  | 4. State Project Number or ID Number |  |  |  |  | 5. Project Location: State, County, or Federal Region |  |  |  |  |
| 6. CONTRACTOR NAME AND ADDRESS |  |  |  |  |  |  |  |  |  |  |  |  |
| Name: |  |  |  |  |  |  |  |  |  |  |  |  |
| Address: |  |  |  |  |  |  |  |  |  |  |  |  |
| City: |  |  |  |  |  | State: |  |  |  | Zip: |  |  |
| 7. Contractor/Subcontractor DUNS Number: |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Employment Data |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  | EMPLOYEES |  |  | HOURS | PAYROLL |  |
| Prime Contractor Direct, On-Project Jobs (see guidance for definitions) |  |  |  |  |  |  |  |  |  |  |  |  |
| Subcontractor Direct, On-Project Jobs |  |  |  |  |  |  |  |  |  |  |  |  |
| Subcontractor Name |  |  |  |  |  |  |  |  |  |  |  |  |
| Prime and Subcontractor Totals |  |  |  |  |  |  | 0 |  |  | 0 | 0.00 |  |
| 9. PREPARED BY CEO or Payroll Official: |  |  |  |  |  |  |  |  |  |  |  |  |
| Any intentional misrepresentation or omission made in connection with the attached Monthly Employment Report may be |  |  |  |  |  |  |  |  |  |  |  |  |
| cause for suspension, a determination of non-responsibility on future bids, and may be cause for revocation of award, default, or |  |  |  |  |  |  |  |  |  |  |  |  |
| debarment. The person or entity making the false statement or omission is subject to any and all civil and criminal penalties |  |  |  |  |  |  |  |  |  |  |  |  |
| available pursuant to applicable state and federal law. |  |  |  |  |  |  |  |  |  |  |  |  |
| I certify the information contained in the attached Monthly Employment Report is true, correct, and complete. |  |  |  |  |  |  |  |  |  |  |  |  |
| Signature: |  |  |  |  |  |  | Title: |  |  |  |  |  |
| Name: |  |  |  |  |  |  | Date: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | Form 25D-1589 (Rev. 3-25) |  |

Standard Modifications

107-1.05 FEDERAL AID PROVISIONS.  Add the following after Monthly Employment Reports on ARRA projects:

Form 25D-55H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the Contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds.  Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements.  During the performance of this Contract, the Contractor, for itself, its assignees and successors in interest (hereinafter referred to as the "Contractor") agrees as follows:

(1)	Compliance with Regulations:  The Contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this Contract.

(2)	Nondiscrimination:  The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The Contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, Section 21.5 of the regulations, including employment practices when the Contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitation for Subcontractors, Including Procurements of Materials and Equipment:  In all solicitations either by competitive bidding or negotiation made by the Contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the Contractor of the Contractor's obligations under this Contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports:  The Contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions.  Where any information required of a Contractor is in the exclusive possession of another who fails or refuses to furnish this information the Contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance:  In the event of the Contractor's noncompliance with the nondiscrimination provisions of this Contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a)	withholding of payments to the Contractor under the Contract until the Contractor complies, and/or

(b)	cancellation, termination, or suspension of the Contract, in whole or in part.

(6)	Incorporation of Provisions:  The Contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The Contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance:  Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the Contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the Contractor may request the United states to enter into such litigation to protect the interests of the United States.

E66(10/13/09)

- Special Provisions

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following: If required water for construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

R7(05/29/02)

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

- Add the following paragraphs:

7.	Restoring Areas. Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed. The original condition of an area shall be determined as follows: Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition. After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs. Before demobilization the Contractor shall repair damages attributed to its operations. The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites. Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping. A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property. The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35(01/27/07)

- Special Provisions

- Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S80

Section 108
Prosecution and Progress

Special Provisions

108-1.01 SUBLETTING OF CONTRACT. Delete paragraph four and replace with the following: Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract. The certification will be accepted by the Department in lieu of written approval of subcontracts. The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work. The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

a.	The Department is furnished with one completed Contractor Self certification, Form 25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

b.	The subcontractors have submitted a Bidder Registration, Form 25D-6;

c.	The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

d.	The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

e.	Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

R57(01/02/08)

108-1.03 PROSECUTION AND PROGRESS. Delete the last sentence of the first paragraph and substitute the following: Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule. and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor, Utility Companies, and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown. Indicate anticipated periods of multiple shift work in the CPM Schedule. Revise to the proposed CPM Schedule promptly. Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

R261(12/13/02)

Section 109
Measurement and Payment

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES. Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence: “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3. Equipment, item a. add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

R14 (4/31/05)

Standard Modification

109-1.08 FINAL PAYMENT. Add the following sentence to the first paragraph: The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16.

E11 (6/30/04)

- Add the following Section:

Section 120
Disadvantaged Business Enterprise (DBE) Program

Standard Modification

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

1.	Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer. A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

- 120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

1)	A description of the work that each DBE will perform;

2)	The dollar amount of participation by the DBE firm;

3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

1.	Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

d.	Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

a.	regular dealer;
b.	manufacturer;
c.	broker; 
d.	subcontractor; 
e.	joint-venture; or
f.	prime contractor.

2.	Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

1)	The work performed will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

6)	All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

7)	The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

1)	increasing the participation of other DBEs on the project;

2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

S33(11/17/00)

Section 201
Clearing and Grubbing

Special Provisions

201-3.01 GENERAL. Add the following: The Engineer will review and accept the clearing limits set by the Contractor. Any subsequent changes made by the Engineer in setting the clearing limits will not be cause for extra payment and will be subsidiary to Item 201(3B) Clearing and Grubbing.

Timber with a 5 inch diameter or larger at breast height shall be cut into 8-foot lengths, de-limbed, and stacked at locations approved by the Engineer for public removal. These locations shall be adjacent to the nearest side street or other approved site which does not create a traffic hazard due to lack of adequate parking for the public. The Contractor will notify the public of the availability of the timber once it has been stacked. The Contractor shall schedule the clearing and grubbing work so as to provide 2 weeks for the public to access those areas of the project where such timber is available prior to completion of the clearing and grubbing work in those areas. The Contractor shall dispose of the timber left by the public after the 2 week time period.

The Contractor shall perform the work necessary to preserve and/or restore land monuments and property corners from damage. A land monument or property corner that is disturbed shall be restored according to Section 642 at the Contractor's expense. An undisturbed area 5 foot in diameter may be left around existing monuments and property corners. A list of land monuments and property corners is shown on the Right of Way maps.

201-3.03 GENERAL. Remove the first sentence and replace with the following: Remove and dispose of all stumps, roots, moss, grass, turf, debris or other objectionable material within excavation and fill limits.

201-4.01 METHOD OF MEASUREMENT. Add the following: The work required to cut, de-limb and stack timber for public removal and to preserve and restore land monuments and property corners will be subsidiary to Item 201(3B) Clearing and Grubbing.

R107(06/10/04)

Section 202
Removal of Structures and Obstructions

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work includes removing the existing Peters Creek Bridge Number 536 in its entirety and removal and relocation of gates.

The existing Peters Creek Bridge is approximately 100 feet long and 28 feet wide.  Drawings for the existing bridge can be obtained from the office of the Chief Bridge Engineer at 3132 Channel Drive, Juneau, AK 99801.

These drawings are available for informational use only and the Department neither warrants nor represents that they accurately depict the configuration of the existing bridge. Where details of the work under this Contract are dependent on the dimensions of the existing bridge, verify the controlling field dimensions and adjust dimensions of the work to fit existing conditions.

202-3.01 GENERAL. Add the following: Remove or abandon wells according to DEC regulations.

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES. Remove this Subsection in its entirety and replace with the following:

Do not remove bridges, culverts and other drainage structures in use by traffic until satisfactory arrangements have been made to accommodate traffic.

1.	Culverts and minor structures. Do not remove manholes, inlets, valves or any other portion or portions of the sewer or water systems until the new systems are in operation or suitable arrangements have been made for the diversion, interruption, or a temporary system has been installed.

When flexible pipe is designated in the Contract documents to be abandoned in place, crush and flatten the ends before covering. Securely plug other conduits by an approved method.

2.	Bridges.

a.	Submittals.

No less than thirty (30) days prior to commencing bridge removal, submit for approval a Bridge Demolition Plan prepared by a Professional Engineer registered in the State of Alaska. The Bridge Demolition Plan will include, but is not limited to:

(1)	Proposed bridge removal date.

(2) 	Contact names and phone numbers for individuals responsible for the demolition.

(3) 	Design calculations demonstrating that the integrity of the undemolished portions of the structure will be maintained during all stages of the removal operations.

(4)	Schematic and detailed drawings identifying the method and sequence of removal.

(5) 	Schematic and detailed drawings identifying and detailing means of access to the bridge during demolition.

(6)	Methods to prevent debris from entering the Peters Creek.

(7)	A list of the type, number and size of all proposed equipment to be used.

(8)	Details of temporary support shoring and bracing, if required.

(9)	Schematic drawings specifying crane locations and lifting locations.

(10)	A listing of the size and weight of bridge subassemblies to be transported from the site.

(11)	Details of waste site location.

(12)	Details of lead paint containment and disposal.

Receipt of the Bridge Demolition Plan by the Engineer does not constitute approval of the plan or the adequacy of the plan. Do not commence bridge removal operations without the written authorization of the Engineer.

b.	Demolition.

Remove and dispose of all steel, concrete and timber elements entirely. Entirely remove existing substructure units.

Do not allow debris from bridge removal operations to enter the Peters Creek.

Steel on the existing Peters Creek Bridge is coated with lead-based paint. Follow all applicable OSHA, EPA, DEC, Federal, State, Local and Section 513 requirements for containing, handling and disposing of lead-based paint waste and debris when dismantling, removing and handling steel from the existing bridge.

Maintain the integrity of undemolished portions of the bridge structure during demolition operations.

c.	Disposal.

Deliver all steel generated during demolition (e.g. truss members, floor beams, rivets, etc.) to a steel mill or ferrous foundry where the steel will be melted down to a raw material and recycled. Follow all applicable OSHA, EPA, DEC, Federal, State, Local and Section 513 requirements for containing, handling and disposing of lead-based paint waste and debris when handling, transporting, delivering and recycling structural steel from the existing bridge. Submit to the Engineer certification from the mill or foundry attesting that all of the existing structural steel has been recycled and that the lead byproduct has been recycled or disposed of in accordance with applicable regulatory requirements. In the certification, provide the weight of steel recycled and the mill or foundry’s EPA regulated waste activity identification number.

Dispose of all non-salvageable and non-recyclable materials in a Contractor-furnished waste disposal site or in a manner approved by the Engineer.

d.	Cleanup. In addition to the requirements of Subsection 104-1.05, dress all bridge slopes or embankments according to the Contract documents. Dress slopes not designated in the Contract documents to conform to the natural ground surface or blend as directed. Fill all excavations and depressions.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Remove and stockpile all existing and temporary pavement, process it for reuse to fullest extent possible as Item 301(1) Aggregate Base Course, Item 306(1) ATB, or Item 401(1) Hot Mix Asphalt.

Asphalt material not used as specified above shall be removed from the project and will be the property of the Contractor.  Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment. A DEC permitting officer in Anchorage may be contacted at (907) 269-7590.

(3/29/01)R84

202-3.08 GROUND WATER WELL ABANDONMENT. This work will be in accordance with Municipality of Anchorage (MOA) well decommissioning regulations as stipulated under Anchorage Municipal Code (AMC) Title 15 Environmental Protection.

202 3.09 REMOVAL OF PIPE. Add the following: During project construction, ENSTAR Natural Gas Company will abandon existing gas pipelines. Follow the procedures given in subsection 105 1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned. Once the pipelines are abandoned, remove abandoned natural gas pipe within the right of way that are in conflict with the work and dispose of pipes off the project limits.

202-4.01 METHOD OF MEASUREMENT.  Add the following:

4.	Lump Sum. All work required without measurement of quantities.

202-5.01 BASIS OF PAYMENT. Add the following: Item 202(16). At the contract unit price for the length of pipe removed, regardless of size. Payment includes full compensation for labor, materials, and equipment required to remove and dispose of the pipes as shown in the Plans.  Remove and Relocate Planter Box shall be subsidiary to Item 202(1).

New materials necessary for removal and relocation of gates are subsidiary.

Item 202(23). At the contract unit price for each well capped according to MOA & DEC regulations.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

202(13)	Removal of Existing Bridge No. 536	Lump Sum

202(16)	Removal of Gas Pipe	Linear Foot

202(23)	Ground Water Well Abandonment	Each

Section 203
Excavation and Embankment

Special Provisions

203-1.01 DESCRIPTION. Add the following: This work includes contaminated material testing, excavation of contaminated material, and water sampling for contaminated materials encountered during construction performed by Contractor and by utility relocation work described in Section 105.

Add the following Subsections:

203-3.07 WATER SAMPLING.  If the water table is encountered during excavation of a contaminated material area, the Contractor will be required to retain an independent test laboratory to collect water samples from the water table at the locations directed by the Engineer.  Samples shall be tested, or stored for future testing at the Engineer’s option, according to the appropriate current EPA test methods.  Samples not tested by project completion may be disposed.  Transmit the results in writing directly to the Engineer.

During excavation, samples shall be taken and tested at intervals as directed by the Engineer (ie: hourly, daily, or weekly) depending on the adjacent operation.  After completion of the work final samples shall be obtained and tested.

203-3.08 CONTAMINATED MATERIAL TESTING.  This work shall consist of testing soils for contaminants.  Each truckload of soil imported from a suspected site or other location at the direction of the Engineer shall be examined for contamination.

According to Subsection 203-3.09, Excavation of Contaminated Material, the Contractor shall retain an independent test laboratory to conduct the following tests:

1.	Field Tests

a. Organic Vapor Analyzer (OVA) Analysis

b. Visual Analysis (Petroleum Odor)

2.	Laboratory Tests

a. Volatile Aromatic Hydrocarbons

b. Total Petroleum Hydrocarbons

The Contractor shall obtain the services of a hazardous waste professional to conduct field testing using an organic vapor analyzer (OVA) or equivalent equipped with a photoionizing detector (PID), or other approved DEC instrument.  The Contractor shall submit the name of the hazardous waste professional to the Engineer at the preconstruction conference.  The hazardous waste professional shall be available at all times hauling is in progress to conduct the required field tests.

The hazardous waste professional shall sample and test according to standard DEC approved testing procedures.  If an OVA response indicates the presence of any contamination, the soils will have failed the test and will be designated as contaminated.  If no response is observed, the soil will be examined for odor.  If a petroleum odor is detected, the soils will fail the test and will be designated as contaminated.  If no petroleum odor is detected, the soil will be considered to have passed field criteria.

The hazardous waste professional shall be responsible for ensuring soils exhibiting an OVA response that indicate the presence of any contamination, or soils exhibiting characteristics of fuel contamination (i.e. odor, sheen, or stain), are identified to the Engineer.

Contaminated material will not be accepted for borrow and shall be immediately removed from the site.

The OVA will be calibrated at the beginning and end of each day and after every four (4) hours of use.

203-3.09 EXCAVATION OF CONTAMINATED MATERIAL.  This work shall consist of removing and disposing of fuel contaminated soils encountered during the excavation.  Disposal of fuel contaminated soils shall be at a location approved by the Engineer.

1.	Determining Limits of Contaminated Soil.  Three sites are identified as potentially containing contaminated soil and/or water in the January 28, 2009 Phase II Environmental Site Assessment.  The exact limits of potential contaminated soil within the excavation cannot be determined until the material is exposed.  Once exposed, the soil shall be tested according to Subsection 203-3.08, Contaminated Material Testing.  Testing will verify the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation or if they will require special handling.  Soils that have a response from photoionizing detector or equivalent instrument of 1 part per million or more above background are considered to be “contaminated” and will require special handling and shall be disposed of according to this Subsection.

2.	Worker Health and Safety.  Before the excavation of any soils identified as contaminated, the Contractor shall assure the personnel working in the area of potential contamination have received the State of Alaska, Department of Labor, Health and Safety Training.  The Contractor shall provide the Engineer a list of the personnel and subcontractors that will be working within the area identified as being potentially contaminated.

The Contractor shall notify personnel and subcontractors, before their begin work at the site, they will be working in an area identified as being potentially contaminated with petroleum fuel.

3.	Contaminated Soil Removal and Segregation.  In the event the Contractor must stockpile contaminated soil, a liner, cover and temporary fencing will be required.

The size and location of the liner shall be as approved by the Engineer.  The Contractor shall cover and secure the stockpile at the end of each work day.  The Contractor shall be responsible for removal of the stockpile liner, safety fence, and cover once the fuel contaminated soil is removed.

The method of disposal shall be according to Department of Environmental Conservation guidelines for reducing BTEX or TPH in soils.   Additional testing required at the disposal site shall be done according to Subsection 203-3.08, Contaminated Material Testing, unless otherwise directed by the Engineer.

Before the Contractor backfilling the excavation, random samples from the excavation (bottom and sides) shall be taken for confirmation testing.  Backfill within the limits of planned excavation shall meet the requirements for the item of work involved.  Backfill outside plan excavation limits shall meet the requirements of Select Material, Type C or better.

4.	Responsibility.   With respect to preexisting hazardous substances or contaminated materials in the project area, nothing in this contract is intended to impose upon the Contractor, or to require the Contractor to assume, the status under state or federal environmental law of a facility owner or operator, or an owner or generator of those preexisting hazardous substances or contaminated materials.  The Contractor is advised, however, the Contractor shall assume the responsibility to obtain administrative approvals and to coordinate the activities with the Department of Environmental Conservation and/or any federal agency having jurisdiction, to carefully abide by the applicable laws, regulations, and the terms of any administrative approvals, and to otherwise use environmentally sound management practices such that the Contractor does not, as a result of its own actions, become a facility owner or operator, or an owner or generator of hazardous substances by reason of an unpermitted release of hazardous substances.

203-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 203(31), Contaminated Material Testing and Special Handling, will be measured for payment on a time and materials basis according to Subsection 109-1.05, Compensation for Extra Work on Time and Materials Basis.  Backfilling within the plan excavation limits will not be measured for payment but will be subsidiary to the respective items of work.  Backfilling outside plan excavation limits will be measured for payment as embankment construction.

Water sampling and contaminated material testing shall be reimbursed based on paid receipts for the authorized sampling and testing.

Providing a hazardous waste professional to test for contaminated soils will not be measured for payment.  Testing soils to determine contamination will be measured for payment under Item 203(31), Contaminated Material Testing and Special Handling.

203-5.01 BASIS OF PAYMENT.  Add the following:

Payment for authorized water sampling and contaminated material testing will be made on the receipts for authorized tests plus 15 percent, and shall be considered full compensation for the labor, equipment, and materials required to obtain samples and have tests performed.  A change order will not be required to initiate water sampling or contaminated material testing.

Excavating and disposing of fuel contaminated soil will be paid under Item 203(31), Contaminated Material Testing and Special Handling.  The Contractor will be paid on a time and materials basis for authorized Work according to Subsection 109-1.05.  Backfilling within plan excavation limits will be paid for under the items of work involved at the prices bid for that work.  Backfilling outside plan excavation limits will be paid for as embankment construction according to this Section.

No separate payment will be made for providing the hazardous waste professional, this will be subsidiary to Item 203(31), Contaminated Material Testing and Special Handling.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203(31)	Contaminated Material Testing and Special Handling	Contingent Sum

Section 204
Structure Excavation for Conduits and Minor Structures

Standard Modification

204-3.01 CONSTRUCTION REQUIREMENTS. In the first sentence of paragraph four, delete: “bedding and”

E37(01/27/07)

- Special Provisions

204-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third paragraph: Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.

R204(2/6/08)

204-5.01 BASIS OF PAYMENT. Delete the third paragraph and replace with the following: When item 204(1), Structure Excavation, does not appear in the bid schedule, structure excavation required to complete other items of work is subsidiary except that excavation and disposal of unsuitable material required from below a plane 12 inches below the invert elevation of conduits and 18 inches below the bottom of structures will be paid for as extra work.

Replace Section 205 with the following:

Section 205
Excavation And Fill For Major Structures

205-1.01 DESCRIPTION. Excavate and backfill for bridges, retaining walls, concrete box culverts, and other major structures.

Furnish all resources to place and remove cribbing or cofferdams. Perform all required sheeting, bracing, bailing, pumping, draining, and grouting.

Replace unsuitable material encountered below the elevation of the bottom of footings.

205-2.01 MATERIALS. Use materials that conform to the following:

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Silica Fume	Section 701

Fine Aggregate	Subsection 703-2.01

Porous Backfill Material	Subsection 703-2.10

Structural Fill	Subsection 703-2.13

Chemical Admixtures	Subsection 711-2.02

Water	Subsection 712-2.01

CONSTRUCTION REQUIREMENTS

205-3.01 EXCAVATION.

1.	General. Clear and grub prior to starting excavation according to the requirements of Section 201.

Cut all rock or other hard foundation material to a firm surface, either level, stepped, or serrated, as directed, and remove all loose material.

Do not disturb material below the bottom of spread footings, unless otherwise noted in the Contract.

Excavate to the bottom of footing prior to driving piles.  Do not excavate below the footing elevation unless otherwise noted in the Contract. When swell results from driving piles, excavate the footing area, to the elevation of the bottom of the footing, as shown on the Plans. When subsidence results from driving piles, backfill with structural fill material, to the elevation of the bottom of the footing, as shown on the Plans.

Dispose of all necessary excavated material as provided in Subsection 203-3.01.

Do not alter streambed channel and do not place excavated materials in natural stream channels, unless shown on the Plans or approved in writing.

Give the Engineer in writing no less than 15 days advance notice prior to beginning excavation for spread footings to allow for inspection of the excavated surface. With this notification, identify the location and specify a time period of no less than two days for the Department to inspect the excavated surface. Dewater and remove all debris from the surface prior to the Department's inspection. Obtain the Engineer’s approval of the excavated surface prior to the placement of any formwork or foundation materials. Account for the time required by the Department to perform the inspection in the progress schedule submitted under Subsection 108-1.03. Suspension of work to allow for inspection is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

2.	Foundations on Bedrock. Excavate for footings founded on bedrock, to the neat lines of the footings. Fill overbreak areas outside the neat lines of footings, with Class A concrete, at no additional cost to the Department.

3.	Cofferdams. Use suitable cofferdams as necessary wherever water-bearing strata are encountered above the elevation of the excavation. Construct foundation seals according to the requirements of Section 501.

Submit detailed drawings, designed and sealed by a professional engineer proficient in structural design and registered in the State of Alaska, showing proposed method of cofferdam construction. The details and clearance of cofferdams, which affect the character of the finished work, is subject to approval but other details of the design are your responsibility. Submit drawings at least 3 weeks in advance of cofferdam construction.

Extend cofferdams to the required depth or to bedrock. Adequately brace cofferdams and make them as watertight as practical. Provide sufficient clearance inside cofferdams to permit construction of forms and permit pumping outside of the forms.

Right or enlarge cofferdams which are tilted or moved out of position by any cause during the sinking process, to provide the necessary clearance and proper pier location.

When no foundation seal is shown on the Plans and the cofferdam cannot be dewatered, place a seal if the Engineer approves seal placement in writing.

Foundation seals, when shown on the Plans, may be eliminated as directed if the cofferdams can be dewatered without the seals when the excavation has been carried to the elevation of the bottom of the footing.

Construct cofferdams to protect concrete against damage from a sudden rising of the water and to prevent damage by erosion by venting cofferdams at low water or by other means that limit differential hydrostatic head.

No timber may extend into the completed substructure.

After substructure completion, remove sheet piling and other temporary structural materials in such a manner as to avoid disturbing the finished structure. Steel or concrete sheeting or bracing may be permitted to remain in the completed structure, subject to approval.

205-3.02 STRUCTURAL FILL. Remove material that is unsuitable for supporting foundations, from the bottom of the footing to the depth as shown on the Plans. Remove material that is unsuitable for approach slabs shown on the Plans. Place Structural Fill in 6-inch layers, compacted to meet Subsection 205-3.05. Place Structural Fill as uniformly as possible on all sides of structural units as shown on the Plans. Avoid unbalanced loading of Structural Fill material which could damage the structure. When placed against concrete, place Structural Fill in accordance with Section 501.

Controlled Low-Strength Material may be used as an alternative source for Structural Fill if approved by the Engineer.

205-3.03 BACKFILL. Unless otherwise noted, reuse excavated material for backfill where shown on the Plans. If additional backfill is required, use material meeting Selected Material, Type C (Subsection 703-2.07), or as approved by the Engineer. Place backfill material in layers, and compact to the satisfaction of the Engineer. Bench slopes within the area to be filled.

Place underwater backfill in natural stream channels without compaction or layer requirements.

Place backfill as uniformly as possible on all sides of structural units. Avoid unbalanced loading of backfill which could damage the structure. When placed against concrete, place backfill according to the requirements of Section 501.

No ponding or jetting of backfill is allowed.

205-3.04 POROUS BACKFILL. Place porous backfill material continuously within a vertical plane 1 foot behind retaining walls and abutments, unless otherwise shown on the Plans.

Where weep holes are shown on the Plans or required by the Specifications, place not less than 1 cubic foot of Porous Backfill material in the fill at each hole, securely tied in a burlap bag, or wrapped with an acceptable geotextile fabric. Extend the wrapped Porous Backfill material at least 6 inches above the hole.

205-3.05 COMPACTION.  Compact material in conformance with the following, using moisture and density control unless the Engineer determines that such controls are not feasible.

1.	Compaction With Moisture and Density Control. The maximum density will be determined by WAQTC FOP for AASHTO T 180 or ATM 212.

Water or aerate as necessary to provide the approximate optimum moisture content for compaction.  Compact each layer to not less than 98% of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

2.	Compaction Without Moisture and Density Control. Compact by routing construction equipment and/or rollers uniformly over the entire surface of each layer before the next layer is placed. Compact until the material does not rut under the loaded hauling equipment.

Keep dumping and rolling areas separate. Do not cover any lift by another until the Engineer has determined the required compaction is obtained.

205-2.01 CONTROLLED LOW-STRENGTH MATERIAL. Provide Controlled Low-Strength Material (CLSM) that is self compacting, cementitious, flowable material requiring no subsequent vibration or tamping to achieve consolidation. Provide a job mix design in writing to the Engineer on Form 25D-203. Do not place CLSM until the Engineer approves the mix design.

Design CLSM to have 28-day compressive strength between 100 psi minimum to 300 psi maximum as determined by ASTM D 4832 and a flowable consistency within a slump range of 3 to 10 inches as determined by WAQTC FOP for AASHTO T 119.

Calculate the water-cement ratio on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, and silica fume. Use admixtures in accordance with the manufacturer’s recommendations. Do not use admixtures containing calcium chloride.

Mix and batch CLSM in accordance with Subsection 501-3.01 to Subsection 501-3.03.

Do not place CLSM on frozen ground, in standing water, or during wet weather conditions. Place CLSM only if the air temperature is 40 °F minimum and rising. Ensure the material temperature is at least 50 °F while being placed.

Do not apply loads to the CLSM until the compressive strength reaches 50 psi.

Meet the proportion requirement of Subsection 501-3.05.5.a. Acceptance will be based on a Certificate of Compliance. Provide a Certificate of Compliance for each batch of CLSM in accordance with Subsection 501-3.05.2.

205-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Excavation. By the actual volume of material removed, excluding the following:

a.	Material removed prior to measurement of the original ground surface.

b.	Material outside of the vertical planes 18 inches outside of and parallel to the neat lines of the footings, except that the limit will be vertical planes coinciding with the neat lines of the seals when seals are shown on the Plans.

c.	Material outside of vertical planes coinciding with the neat lines of footings excavated in solid rock.

d.	Embankment material placed above the elevation of the bottom of footings.

e.	Material within the staked limits of other types of excavation for which payment is otherwise provided.

2.	Structural Fill. By the actual volume of material accepted in final position.

3.	Porous Backfill Material. By the actual volume of material accepted in final position.

4.	Backfill. Material for Backfill will not be measured for payment.

5.	Controlled Low-Strength Material. By the actual volume of material accepted in final position.

205-5.01 BASIS OF PAYMENT. Material for backfill is subsidiary.  Clearing and grubbing within the excavation limits is subsidiary.

Porous Backfill Material includes all materials and construction operations for making weep holes. When item 205(4), Porous Backfill Material, does not appear in the bid schedule, Porous Backfill is subsidiary.

Excavation, removal, and disposal of material unsuitable for Structural Fill is subsidiary.

Excavation for footings ordered by the Engineer, at a depth greater than 3 feet below the bottom of such footings shown on the Plans will be paid for as extra work under Subsection 109-1.05.

Where a bid item for cofferdams does not appear in the bid schedule, the work necessary to protect the excavation and control water is subsidiary.

When Controlled Low-Strength Material is used as an alternative to Structural Fill, Controlled Low-Strength Material is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

205(3)	Structural Fill	Cubic Yard

Section 301
Aggregate Base Course

Special Provisions

301-2.01 MATERIALS. Add the following after the first sentence: Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

R176(01/24/07)

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.

R26(09/01/89)

301-3.03 SHAPING AND COMPACTION. Add the following: Areas with less than 4 inches of aggregate base course shall be watered and compacted to the satisfaction of the Engineer. Field densities will not be performed in these areas.

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based determined by control strip method ATM 412. Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1) Aggregate Base Course at the unit price shown on the bid schedule for that item.

R176(01/24/07)

Section 306
Asphalt Treated Base Course

Special Provisions

306-2.01 MATERIALS. Delete items 1 and 2 and replace with the following:

1.	Aggregate. Conform to subsection 703-2.04.

2.	Asphalt. The total residual asphalt cement may be a combination of PG 52-28 and the asphalt binder in the existing asphalt or only PG 52-28. Documentation and conformance is only required for PG 52-28. The Engineer may conditionally accept asphalt cement at the source. Provide a manufacture’s certificate of compliance, according to subsection 106-1.05, and test results of applicable quality requirements of Section 702 before shipping the material.

- Add the following:

4.	Recycled Asphalt Pavement (RAP). Process existing pavement removed under subsection 202-3.05 so material passes the 1 ½ inch sieve. Stockpile the material separately from the crushed aggregates for pavement aggregates. Perform one gradation and one asphalt content test for every 1000 tons of RAP or a minimum of 10 sets of tests which ever is greater.

- CONSTRUCTION REQUIREMENTS

306-3.01 COMPOSITION OF MIXES. Replace this subsection with the following: If recycled materials are used, submit process control data of the RAP and of the asphalt concrete aggregates supporting proposed job mix design gradations.

At least 15 calendar days before the production, submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile and RAP. The proposed gradation of the virgin aggregate must meet the requirements of Table 703-3, Type II. Submit gradation and asphalt content process control data of RAP for the Job Mix Design.

2.	Provide representative samples of each of the aggregates in the blend.  Sample sizes: 100 pounds of each intermediate and/or coarse aggregate, 200 pounds of fine aggregate, 25 pounds of blend sand, and 200 pounds of RAP.

3.	A minimum of three 1 gallon samples of asphalt cement proposed for use in the mixture, including the name of the product, the manufacturer, test results as required in Section 702, manufacturer’s certificate of compliance according to Section 106, and a temperature viscosity curve for the asphalt cement.

4.	A 0.5 pint sample of the anti strip additive proposed, including the name of product, manufacturer, and manufacturer’s data sheet, and current Materials Safety Data Sheet (MSDS).

From this information, the Engineer will establish the Job Mix Design using ATM T-417, which will become a part of the Contract. The Job Mix Design shall meet the requirements of Type II, Class B in Table 401-1, Asphalt Concrete Mix Design Requirements, except Voids in Mineral Aggregate (VMA) and Dust/Asphalt ratio specifications do not apply. RAP may be used in the mixture. The design minimum residual asphalt content (RAP residual plus PG 52-28) is 5 percent by weight of total mix and with 1/4 percent antistrip by weight of PG 52-28. The Job Mix Design will specify the design aggregate gradation, gradation of virgin aggregate blend, percent of residual asphalt cement, percentage of RAP, and mixing and compaction temperature ranges.

Submit changes in the Job Mix design warranted by changes in the source of asphalt cement, the source of aggregates, aggregate quality, aggregate gradations, or blend ratios, in the same manner as the original submittal. A new Job Mix Design will only apply to asphalt concrete mixture produced after submitting the new aggregate gradation.

Approved Job Mix Designs will have the full tolerances shown in Table 401-2 applied and will not be limited to the broad band listed in Table 703-3.

306-3.02 WEATHER LIMITATIONS. Delete the requirements of this subsection and substitute the following: Apply the requirements of subsection 401-3.01.

306-3.03 STOCKPILING. Delete this subsection in its entirety.

306-3.04 EQUIPMENT. Add the following: Apply the requirements of subsection 401-3.02 to equipment.

- Add the following to item 1.

1.	If recycled materials are used, the asphalt plant shall combine RAP with asphalt concrete aggregates to produce a hot recycled asphalt treated base mixture.

Delete subsections 306-3.05 and 306-3.06 and substitute the requirements of subsections 401-3.08 and 401-3.09.

Delete subsections 306-3.08 and 306-3.09 and substitute the requirements of subsections 401-3.12 and 401-3.13.

Apply the requirements of subsections 401-3.07, 401-3.10, and 401-3.11.

- Add the following subsection:

306-3.12 PATCHING DEFECTIVE AREAS. Remove ATB that becomes contaminated with foreign material, is segregated, or is determined to be defective. Do not skin patch. Remove defective materials for the full thickness of the course. Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees. Coat edges with a tack coat conforming to Section 402 and allow to cure. Place and compact fresh ATB to grade and smoothness requirements.

306-4.01 METHOD OF MEASUREMENT. Change the third paragraph to read:

Antistrip additive. Will not be measured for payment, the cost of the antistrip additive will be subsidiary to Item 306(1) ATB.

- Add the following subsection:

306-4.02 ACCEPTANCE SAMPLING AND TESTING. The Department has the exclusive right and responsibility for determining the acceptability of materials incorporated into the project. The Engineer will perform acceptance sampling and testing. The Engineer will make the results of the acceptance testing available to the Contractor within seven working days from the date of sampling. Sample the blended virgin aggregate at the cold feed. The Contractor may select the sample location of mix to determine the asphalt content.

Within 24 hours of final rolling, cut one 6 inch diameter core, full depth, from the finished mat to determine density according to WAQTC FOP for AASHTO T166/T275. Neatly cut the sample using a core drill at the randomly selected location marked by the Engineer. Use a core extractor to prevent damage to the core. Do not cut a sample over a bridge deck.

Apply Tolerances shown in Table 401-2 to test results to determine compliance with mix design.

The Engineer will test for density, gradation, and asphalt content as specified in subsection 401-4.02; however, the price adjustments of Section 401 will not apply.

306-5.01 BASIS OF PAYMENT. Add the following: Antistrip shall not be paid separately but shall be subsidiary to and included in the Item 306 (1) ATB. If the Mix Design requires more than 5% asphalt cement, only the quantity in excess of 5% shall be paid for at the Contract unit price for Item 401(2) Asphalt Cement, Grade PG 52-28.

Patching defective areas shall be subsidiary to Item 306(1) ATB.

R226(02/05/03)

- Replace Section 401 with the following:

Section 401
Hot Mix Asphalt And Surface Treatments

Special Provisions

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

1.	In this Section, HMA refers to Type I, II, III and IV.

a.	Temporary Asphalt Pavement: HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course: HMA, Type IV, Class B.

- MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

TABLE 401-1
HMA DESIGN REQUIREMENTS

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Cement) |  |  |
| Stability, Pounds | 1800 Min. | 1200 min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix, % | 3 - 5 | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Cement |  |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 75 | 65 - 78 |
| Asphalt Cement Content, Min. % | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified. For acceptance testing, HMA mixture will have the full tolerances in Table 401-2 applied. The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits. Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving. HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile. The proposed gradation must meet the requirements of Table 703-3 for each Type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified. The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD. Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 401-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

•	The results do not to achieve the requirements specified in Table 401-1

•	The asphalt cement source is changed

•	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

•	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD. If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 401-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved. Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 401(6) Asphalt Price Adjustment – Quality.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04.

Use a minimum of three stockpiles for crushed HMA aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Conform to 702-2.01. If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD. At least 70% of the aggregate must remain coated when tested according to ATM 414. A minimum of 0.25% by weight of asphalt cement is required.

401-2.05 PROCESS QUALITY CONTROL. Sample and test materials for quality control of the HMA according to Subsection 106-1.03. Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results. When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations. Address the sequence of operations and joint construction. Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 401-4.02.

Provide copies of the documented sampling and testing results no more than 24 hrs from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer: provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles. Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints. Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined. Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include: all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops. The Engineer will identify these and other areas that require density testing.

2.	Test Strips. Construct test strips using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis. Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan. The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer. The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis. Make the equipment available for inspection as required by Subsection 401-3.02. Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips: Subsection 401-5.01 Basis of Payment and as noted here.

a.	Approved. Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed. The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

- CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. Do not place the HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix. Do not place HMA unless the roadway surface temperature is a minimum of 40° F and warmer.

401-3.02 EQUIPMENT, GENERAL. Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hrs before placement of the test strip HMA.

401-3.03 ASPHALT MIXING PLANT. Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT. Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent. Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use. Be prepared to demonstrate deployment of the cover when hauling material or empty. Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials. When directed by the Engineer cover the HMA in the hauling vehicle(s).

401-3.05 ASPHALT PAVERS. Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices. Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system. Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers. Use means and methods approved by the paver manufacturer. Means and methods may consist of chain curtains, deflector plates, or other similar devices or combination of devices. When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Avoid crushing or fracturing of aggregate. Use rollers designed to compact HMA mixtures and reverse without backlash.

Use pneumatic rollers to compact the prelevel/leveling course.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE. Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks. Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place. Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

●	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2-inch with HMA, Type IV. Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required. The Engineer will inspect the material and material installation. Correct material and material installations identified by the Engineer as required by the Engineer for approval. Density testing is not required for the leveling course (prelevel) material, material installation.

●	Where the planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with HMA, Type II, Class B.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402. Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material. Allow tack coat to break before placement of HMA on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate. HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

401-3.10 MIXING. Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

401-3.11 TEMPORARY STORAGE. Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered. Changes in the JMD, visible or otherwise, are cause for rejection. Changes may include: visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

401-3.12 PLACING AND SPREADING. Use asphalt pavers to distribute HMA, including leveling (preleveling) course and temporary HMA. Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities. The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity. Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25° F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours. Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling. In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract. The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209. The MSG of the JMD will be used for the first lot of each Type of HMA. The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core. (Acceptance testing for density of leveling course or temporary pavement is not required).

When directed by the Engineer provide density profiles of the mat and longitudinal joints with a nuclear density gauge. Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 401-2.05.

401-3.14 JOINTS. Minimize the number of joints. Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting. Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities. Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain. Use a power saw or other method approved by the Engineer. Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer. Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines. Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702. Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal. Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint. Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing. Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking. Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of .15 gallons per square yard. Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150°F. These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

401-3.15 SURFACE TOLERANCE. The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge. Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment. No measurements will be taken in turn lanes, lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

401-3.16 PATCHING DEFECTIVE AREAS. Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic. Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 401-3.13 to grade, and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

401-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing. No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

b)	By the final HMA surface.

2.	Asphalt Cement. By the ton, as follows.

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot. ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement. The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity. If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant. This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing. The procedure initially used will be the one used for the duration of the project. No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement. By weighing. No deduction will be made for the weight of asphalt cement or anti-stripping additive.

5.	Preleveling/Leveling Course. By weight or Lane-Station (12 foot width). No deduction will be made for the weight of asphalt cement or anti stripping additive.

6.	Asphalt Price Adjustment – Quality. Calculated by quality level analysis under Subsection 401-4.03. Also included in the measurement are the fees and deductions specified in Subsection 401-2.01 and Subsection 401-4.02.

Asphalt Price Adjustment – Quality, does not apply to, and measurements will not be made for: 1) Leveling Course/Prelevel (rut repair) HMA, 2) Temporary HMA, 3) Approach HMA.

7.	Longitudinal Joint and Joint Adhesive. By the linear foot of longitudinal joint.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 401-4.03 Evaluation of Materials for Acceptance, and is included in Item 401(6) Asphalt Price Adjustment-Quality. Penalties assessed are also included in Item 401(6).

An mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 401-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each class and Type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons. The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection. If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot. The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5,000 tons, the Contract quantity will be considered one lot. The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed. HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot. HMA quantities of 300 tons or greater will be treated as an individual sublot. The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (also for approaches and temporary pavement), HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance. Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer. The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content. Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer. HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants. Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T2 or from the same location as samples for the determination of asphalt cement content. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum. Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11. For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants. Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11. For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density. A separate set of random numbers, different from those used for mix acceptance, will be used to determine acceptance density locations. Cut full depth core samples from the finished HMA within 24 hours after final rolling. Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer. Use a core extractor to prevent damage to the core. The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275. Do not core HMA on bridge decks. Backfill and compact voids left by coring with new HMA within 24 hours. Densities will not be measured at milled edge of existing pavement.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location where the panel completing the joint is cored for mat density acceptance testing.

Failure to cut and backfill core samples within the specified period will result in a penalty being assessed.

Cores for longitudinal joint density shall be taken by the Contractor in the presence of the Engineer. The Engineer will take immediate possession of the samples.

4.	Retesting. A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot. The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core. The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample is allowed. Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons. If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot. If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection. Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03. Asphalt cement pay reduction factors for each sample will be determined from Table 401-4. Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 401(6) Asphalt Price Adjustment-Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each Type of HMA when the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors. The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content. The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer. A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection. A minimum of two samples will be collected from the rejected HMA and tested if requested. If test results are within specification limits, payment will be made for the HMA. If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment. Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test. Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment. The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier. If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier. If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean () of the remaining test results is determined:

Where		 = summation of

x = individual test value to xn

n = total number of test values

() is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

() is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:		(x2)	=   sum of the squares of individual test values.

(x)2	=   square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed. For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2. The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations. The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 98%.

TABLE 401-2
LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 98 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:

QU



USL

-

x

S

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:

QL



x

-

LSL

S

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined. See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined. See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factor from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

- CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 401-3
WEIGHT FACTORS

| Sieve Size | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| 3/4 inch sieve | 4 | 4 | - |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value. The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower.

- PAB = Price Adjustment Base = $133 per ton

- ASPHALT CEMENT

- The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

- Asphalt cement will be randomly sampled and tested in accordance with Subsection 401-4.02. Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

Table 401-4
ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure. Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal. The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question). The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing. This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction. If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

- PAVEMENT SMOOTHNESS

- The top layer of HMA will be measured according to 401-3.15 and evaluated for a smoothness price adjustment. The Engineer will calculate the smoothness price adjustment as follows:

- Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 		= Final quantity of HMA, tons

PrI		= Final measured hot mix smoothness, inches/mile

SF 		= Smoothness Factor

- If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

- LONGITUDINAL JOINT DENSITY

- Longitudinal joint density price adjustments apply when HMA quantities equal or greater than 1,500 tons. A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG, apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

401-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a)	additional compensation to the Contractor or

(b)	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402. Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401 and Approach HMA as included in 401 or 639.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index. The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month. The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period. Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

401-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Asphalt cement, anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, and patching defective areas are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 401(1F) Hot Mix Asphalt, Preleveling/Leveling Course, Type IV: Asphalt Cement, anti-stripping additives are subsidiary.

Item 401(3) Hot Mix Asphalt, Temporary, Type II, Class B: Asphalt cement, anti-stripping additives, removal and disposal are subsidiary.

Item 401(6) Asphalt Price Adjustment – Quality: is the sum of the price adjustments for each material lot (excluding the Preleveling/Leveling Course (rut repair) HMA, Temporary HMA and Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

•	Each mix design subsequent to the approved Job Mix Design (Subsection 401-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

•	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 401-4.02).

•	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 401-4.02).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Hot Mix Asphalt, Type II, Class B	Ton

401(2)	Asphalt Cement, Grade PG 52-28	Ton

401(6)	Asphalt Price Adjustment - Quality	Contingent Sum

401(10)	Asphalt Material Price Adjustment – Unit Price	Contingent Sum

CR401(050509)

Section 402
Tack Coat

Special Provisions

402-5.01 BASIS OF PAYMENT.  Delete the second paragraph and replace with the following:

When item 4020(1), STE-1 Asphalt for Tack Coat, does not appear in the bid schedule, STE-1 Asphalt for Tack Coat shall be subsidiary to Item 306(1).

Replace Section 501 with the following:

Section 501
Structural Concrete

501-1.01 DESCRIPTION. Furnish, place, finish, and cure Portland cement concrete for structures and incidental construction as shown on the Plans. Use the following classes of concrete, as specified on the Plans.

CLASSES OF CONCRETE

Class A:	General use concrete

Class A-A:	Concrete where improved strength and durability is required

Class P:	Concrete where strength in excess of 5000 psi is required

Class DS:	Concrete for drilled shaft foundations

Class S:	Seal concrete deposited under water

Class W:	Minor concrete construction

501-1.02 DEFINITIONS.

ADMIXTURE. A material other than water, aggregates, hydraulic cement, pozzolan, and fiber reinforcement, used as an ingredient of a cementitious mixture to modify its freshly mixed, setting, or hardened properties and that is added to the batch before or during its mixing.

AIR-ENTRAINING ADMIXTURE. An admixture that causes the development of a system of microscopic air bubbles in concrete, mortar, or cementitious material paste during mixing, usually to increase its workability and resistance to freezing and thawing.

SET-ACCELERATING ADMIXTURE. An admixture that causes an increase in the rate of hydration of the hydraulic cement and thus shortens the time of setting, increases the rate of strength development, or both.

SET-RETARDING ADMIXTURE. An admixture that causes a decrease in the rate of hydration of the hydraulic cement and lengthens the time of setting.

WATER-REDUCING ADMIXTURE. An admixture that either increases slump of freshly mixed mortar or concrete without increasing water content or maintains slump with a reduced amount of water, the effect being due to factors other than air entrainment.

AGITATION. The process of providing motion in mixed concrete just sufficient to prevent segregation or loss of plasticity.

BLEED WATER. The autogenous flow of mixing water within or its emergence from newly placed concrete caused by the settlement of the solid materials within the mass. The relative quantity of mix water that will bleed can be estimated by AASHTO T 158.

CAMBER. A deflection that is intentionally built into a structural element or form to improve appearance or to nullify the deflection of the element under the effects of loads, shrinkage, and creep.

CEMENT. A binding material that sets and hardens by chemical interaction with water and is capable of doing so underwater, sometimes called hydraulic cements

CEMENTITIOUS MATERIAL. Hydraulic cements and pozzolans with cementing properties.

CHAMFER. Either a beveled edge or corner formed in concrete work by means of a chamfer strip.

COLD WEATHER. Cold weather is when the air temperature is below 35°F in which conditions are created that impair the quality of freshly mixed or hardened concrete by retarding the rate of cement hydration and increasing the potential for damage to the concrete, including freezing and frost damage, delayed curing, plastic and drying shrinkage cracking, increased thermal stresses and cracking.

COMPRESSIVE STRENGTH, (fc). The measured maximum resistance of a concrete or mortar specimen to axial compressive loading; expressed as force per unit cross-sectional area; or the specified resistance used in design calculations.

SPECIFIED COMPRESSIVE STRENGTH, (f’c). The 28-day compressive strength used in structural design and specified in the Contract documents.

REQUIRED AVERAGE COMPRESSIVE STRENGTH, (f’cr). The 28-day compressive strength, used as the basis for selection of concrete proportions in the mix design process, that is sufficiently greater than the specified compressive strength to ensure acceptance criteria are met.

CONCRETE ANCHOR. Cast-in-place or post-installed fastening device installed in the concrete for the purpose of transferring loads to the concrete. See ASTM E 2265 for standard terminology.

CONSOLIDATION. The process of inducing a closer arrangement of the solid particles in freshly mixed concrete during placement by the reduction of voids, usually by vibration, rodding, tamping, or some combination of these actions.

CONSTRUCTION JOINT. The surface where two successive placements of concrete meet, across which adequate bonding is desirable and through which reinforcement may be continuous.

CURING. Action taken to maintain moisture and temperature conditions in a freshly placed cementitious mixture to allow hydraulic cement hydration and (if applicable) pozzolanic reactions to occur so that the desired properties of the mixture develop.

CURING PERIOD. The length of time in which continuous curing procedures are employed thereby allowing the concrete to properly hydrate and develop its required strength and durability.

INITIAL CURING PERIOD. The time period between placement and implementation of final curing methods in which deliberate action is taken to reduce the loss of moisture from the surface of the concrete.

FINAL CURING PERIOD. The time period after the concrete achieves final set in which deliberate action is taken, without damaging or marring the concrete surface, to maintain satisfactory moisture content and temperature in concrete.

CURING COMPOUND. A liquid that can be applied as a coating to the surface of newly placed concrete to retard the loss of water and, in the case of pigmented compounds, reflects heat to provide an opportunity for the concrete to develop its properties in a favorable temperature and moisture environment.

DURABILITY. The ability of concrete to resist weathering action, chemical attack, abrasion, and other conditions of service.

EVAPORATION RATE REDUCER. A material that generates a continuous thin film when spread over water on the surface of fresh concrete and thus retards the evaporation of bleed water.

FALSEWORK. The temporary structure erected to support the permanent structure, in the process of construction, until the permanent structure becomes self-supporting; composed of shoring or vertical posting, formwork for beams and slabs, and lateral bracing.

FIELD TEST RECORD. A compressive strength record of concrete used on prior projects that was produced by the production facility.

FORM. A temporary structure or mold used to retain the plastic or fluid concrete in its designated shape while the concrete is setting and gaining sufficient strength to maintain its designated shape.

HAUNCH. A deepened portion of a beam or deck in the vicinity of a support.

HONEYCOMB. Voids left in concrete due to failure of the mortar to effectively fill the spaces among coarse-aggregate particles.

HOT WEATHER. Hot weather is any combination of the following conditions that impair the quality of freshly mixed or hardened concrete by accelerating the rate of moisture loss and rate of cement hydration, or otherwise causing detrimental results, including high ambient temperature, high concrete temperature, low relative humidity, wind speed, and solar radiation.

KEYWAY. A recess or groove in one lift or placement of concrete that is filled with concrete of the next lift or grout, giving shear strength to the joint.

LAITANCE. A layer of weak material derived from cementitious material and aggregate fines either: 1) carried by bleeding to the surface or to internal cavities of freshly placed concrete; or 2) separated from the concrete and deposited on the concrete surface or internal cavities during placement of concrete underwater.

MORTAR. A mixture of cementitious material paste and fine aggregate occupying the space among particles of coarse aggregate.

RETEMPER. To add water and remix concrete or mortar to restore workability to a condition in which the mixture is placeable or usable.

ROCK POCKET. A porous, mortar-deficient portion of hardened concrete consisting primarily of coarse aggregate and open voids; caused by leakage of mortar from the form, separation (segregation) during placement, or insufficient consolidation.

SCREED. To strike off concrete lying beyond the desired plane or shape. A tool for striking off the concrete surface, sometimes referred to as a strikeoff.

SET. The condition reached by a cementitious material paste, mortar, or concrete that has lost plasticity to an arbitrary degree of stiffening generally stated as an empirical value indicating the time in hours and minutes required for cementitious material paste to stiffen sufficiently to resist the penetration of a weighted test needle to an established degree as prescribed by AASHTO T 197,

INITIAL SET. Initial set refers to the first stiffening of concrete.

FINAL SET. Final set refers to attainment of significant rigidity.

TREMIE. A pipe or tube through which concrete is deposited with, at its upper end, a hopper for filling and a bail for moving the assemblage.

501-2.01 MATERIALS. Use materials that conform to the following:

1.	Cementitious Materials

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Subsection 701-2.03

Silica Fume	Subsection 701-2.04

2.	Aggregate Materials

Fine Aggregate	Subsection 703-2.01

Coarse Aggregate	Subsection 703-2.02

Aggregate for Abrasive Finish	Subsection 703-2.14

3.	Water, Admixtures and Curing Materials

Curing Materials	Subsection 711-2.01

Chemical Admixtures	Subsection 711-2.02

Water and Ice	Subsection 712-2.01

4.	Joints and Bearings

Joint Materials	Section 705

Expanded Polyethylene	Subsection 705-2.06

Elastomeric Bearing Pads	Subsection 720-2.01

Polytetrafluoroethylene (PTFE) Bearings 	Subsection 720-2.03

Water Stops	Section 723

5.	Utilities and Inserts

Concrete Anchor Inserts	Submit for Engineer’s approval.

Utiliduct, HDPE	Subsection 706-2.08

Utiliduct, Steel	Subsection 716-2.06

Structural Steel	Section 716

Asphalt Felt	ASTM D 226, Type I (No. 15

Asphalt Felt)

6.	Grout and Epoxy

Grout	Subsection 701-2.05

DS Grout	Subsection 701-2.06

Epoxy Cartridge System	Subsection 712-2.19

Epoxy Adhesive for Elastomeric Bearing Pads	Subsection 720-2.02

Epoxy Adhesive for Crack Sealing	AASHTO M 235, Type IV, Grade 3

Epoxy Adhesive for Crack Injection	AASHTO M 235, Type IV, Grade 1

Low-Viscosity Resin	Subsection 712-2.20

Epoxy Bonding Agents	AASHTO M 235, Type V

501-2.02 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Be responsible for the design, construction, and performance of all concrete mixes used.

1.	Contractor Mix Design. Provide a Job Mix Design that complies with Table 501-1, meets the required average compressive strength (f’cr), and provides workability and consistency so the concrete can be worked readily into forms and around reinforcement without segregation or bleeding. Mix and test trial mixtures to determine final proportions of the Job Mix Design.

If the specified compressive strength (f'c) is not designated on the Plans, use a specified compressive strength of 4000 psi for the specified class of concrete.

TABLE 501-1

CONCRETE MIX DESIGN REQUIREMENTS

| Class of Concrete | Cementitious Material Content, | Water-Cement Ratio, maximum | Entrained Air Content | Coarse Aggregate Size Number | Fine Aggregate Gradation | Slump Range 1 |
| --- | --- | --- | --- | --- | --- | --- |
|  | lbs/yd3 | lbs/lbs | % | Specification | Specification | inches |
| A | 611 min., 800 max. | 0.45 | 6.0 | AASHTO M 43, No. 57 or 67 | AASHTO M 6 | 1 - 4 |
| A-A | 658 min., 800 max. | 0.44 | 7.0 | AASHTO M 43, No. 57 or 67 | AASHTO M 6 | 1 - 4 |
| P | 658 min., 1000 max. | 0.40 | 6.0 2 | AASHTO M 43, No. 67 | AASHTO M 6 | 0 - 3 |
| DS | 658 min., 800 max. | 0.50 | None | AASHTO M 43, No. 7 or 8 | AASHTO M 6 | 7 - 9 3 |
| S | 658 min., 800 max. | 0.53 | None | AASHTO M 43, No. 57 or 67 | AASHTO M 6 | 4 - 8 |
| W | 470 min., 800 max. | 0.58 | 5.0 | AASHTO M 43, No. 57 or 67 | AASHTO M 6 | 1 - 5 |

1 Slump may be increased 2 inches when a Type A water reducer is used and increased 5 inches when a Type F water reducer is used, but not to exceed 9 inches.

2 Air-entrained concrete is required only for the deck portion of deck-type precast concrete members.

3 Slump shown is for wet-shaft process placement. Slump may be decreased 1 inch for dry-shaft process placement.

a.	Required Average Compressive Strength. Provide a Job Mix Design meeting a required average compressive strength established from either the Empirical Method or the Statistical Method.

(1)	Empirical Method. When field test records are not available to establish a standard deviation, establish the required average compressive strength from the following equations:

f'cr = f'c + 1200	for f'c ≤ 5000 psi

f'cr = 1.1f'c + 700	for f'c > 5000 psi

Where:	f'cr = required average compressive strength, psi

f'c = specified compressive strength, psi

(2)	Statistical Method. If the production facility has records of field tests performed within the past 12 months and spanning a period of not less than 60 days for concrete with a compressive strength within 1000 psi of the specified compressive strength, establish the required average compressive strength based on the calculated standard deviation. Use field test records from concrete produced at the production facility, which represent materials, quality-control procedures, and climatic conditions similar to those expected in the work and were sampled, cured, and tested according to AASHTO T 141, AASHTO T 23, and AASHTO T 22. Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work. Use field test records representing a group of at least 15 consecutive compressive strength tests in which all concrete was produced using the same mixture proportions.

Calculate the standard deviation of the field test results as follows:

Where:	s = standard deviation, psi

n = number of field test record results considered

Xi = individual field test record result, psi

= average of n field test record results, psi

Establish the required average compressive strength using the largest result of the following the equations:

f'cr = f'c + 1.34ks

or,

f'cr = f'c + 2.33ks – 500	for f'c ≤ 5000 psi,

f'cr = 0.90f'c + 2.33ks	for f'c > 5000 psi,

Where:	f'cr = required average compressive strength, psi

f'c = specified compressive strength, psi

s = standard deviation from field test records, psi

k =	1.16 if 15 total tests are considered

1.08 if 20 total tests are considered

1.03 if 25 total tests are considered

1.00 if 30 or more total tests are considered

Linear interpolation to determine k for intermediate number of tests is acceptable.

b.	Proportioning Materials. Select proportions, based on trial mixtures, for the Job Mix Design to produce concrete satisfying the required average compressive strength and the requirements in Table 501-1. Determine proportions using the absolute volume method according to ACI Publication 211.1.

Calculate the water-cement ratio based on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, and silica fume.

Fly ash may be used as a substitute for Type I and II Portland cement up to a maximum of 35 percent by weight of the total cementitious materials. Do not use fly ash with Type III Portland cement. Silica fume may be used as a substitute for Portland cement up to a maximum of 10 percent by weight of the total cementitious materials.

Do not use admixtures containing chlorides.

For concrete containing aggregate mined from a marine environment, ensure the total water soluble chloride ion content of the mixed concrete does not exceed 0.06 percent by weight of cementitious material for precast concrete members or 0.15 percent by weight of cementitious material for all other concrete.

c.	Trial Mixtures. Make at least three trial mixtures with each trial mixture having different cementitious material contents. Select water-cement ratios that will produce a range of compressive strengths encompassing the required average compressive strength.

Use materials and material combinations for trial mixtures that are of the same brand and type and from the same manufacturer as the materials used in the work.

Record the temperature of the freshly mixed concrete according to AASHTO T 309 and ensure the temperature is within 10°F of the intended maximum temperature of the concrete as mixed and delivered.

Make and cure at least three 6.0 x 12.0 inch or at least four 4.0 x 8.0 inch compressive strength test cylinders for each test age of each test mixture according to AASHTO R 39. Test for compressive strength according to AASHTO T 22 at test ages of 7, and 28 days.

From the results of the 28 day compressive strength tests, plot a curve showing the relationship between water-cement ratio and compressive strength. From the curve of water-cement ratio versus compressive strength, select the water-cement ratio corresponding to the required average compressive strength.

Establish final mixture proportions based on the water-cement ratio using the selected ratio from the water-cement ratio versus compressive strength curve, or the water-cement ratio in Table 501-1, whichever is least.

Verify the Job Mix Design meets the required slump and air entrainment (if applicable) ranges in Table 501-1 by testing concrete, produced using the final mixture proportions, according to AASHTO T 119.

Verify the Job Mix Design meets the total water soluble chloride ion content (if applicable) in Section 501-2.02.1.b by testing concrete, produced using the final mixture proportions, according to AASHTO T 260.

2.	Job Mix Design Submittal. Submit a written mix design, signed and sealed by a Professional Engineer registered in the State of Alaska, for each specified class of concrete and for each specified compressive strength to the Engineer for approval at least 45 days prior to scheduled production. Submit the mix design on Form 25D-203. Include the following:

a.	Job Mix Design Proportions and Test Results. Submit concrete mixture proportions per cubic yard and test results for the proposed Job Mix Design. Include the following information:

(1)	Weights of all cementitious materials

(2)	Weight of fine aggregate in saturated surface-dry condition

(3)	Weight of coarse aggregate in saturated surface-dry condition

(4)	Volume of each admixture.

(5)	Weight of water

(6)	Water-cement ratio

(7)	Slump test results

(8)	Percentage of entrained air test results (if applicable)

(9)	Total water soluble chloride ion content test results (if applicable)

b.	Trial Mixture Proportions and Test Results. Submit concrete mixture proportions per cubic yard and test results for each trial mixture used in formulating the proposed Job Mix Design. Include the following information:

(1)	Weights of all cementitious materials

(2)	Weight of fine aggregate in saturated surface dry condition

(3)	Weight of coarse aggregate in saturated surface dry condition

(4)	Volume of each admixture

(5)	Weight of water

(6)	Water-cement ratio

(7)	7 day and 28 day compressive strength test results

c.	Concrete Materials. Submit the following:

(1)	For each cementitious material, include type/class, brand, producer, plant location, and certified test reports confirming the cementitious material meets these Specifications.

(2)	For coarse and fine aggregate, include pit or quarry locations, producers' names, specific gravities, absorption values, gradations for coarse and fine aggregate, and size number for coarse aggregate.

(3)	For each admixture, include type, brand, producer, and the manufacturer's product data sheet giving the procedure for admixture use and confirming the admixture meets these Specifications. When using two or more admixtures from different manufacturers in the same Job Mix Design, provide manufacturer’s certifications showing that they are compatible.

(4)	Include the source of supply for water and ice.

d.	Field Test Record Basis. When field test data is used as a basis for establishing the required average compressive strength, submit the following for each field test record:

(1)	28-day compressive strength test results of the tested concrete.

(2)	Standard test method used for determining compressive strength.

(3)	Date the compressive strength tests were performed

(4)	Aggregate source used for the tested concrete.

(5)	Specified strength of the tested concrete.

e.	Job Mix Design Slump. Report the Job Mix Design slump using the final proportions.

The Engineer may require samples of aggregate, cementitious materials, and admixtures to verify the mix design. If requested, furnish representative samples (330 pounds each) of both coarse and fine aggregates, 94 pounds each of Portland cement and fly ash, and enough admixture to allow for Job Mix Design verification testing. Ensure that the Department receives these samples at least 45 days before the mixture’s scheduled production for the project.

3.	Changes. Failure to meet the mix acceptance requirements of Section 501-3.04 or changes in the approved Job Mix Design proportions, materials, aggregate gradation, or aggregate quality requires a new Job Mix Design. Do not use new proportions or new materials until the Engineer has approved such materials and has approved a Job Mix Design designating new proportions.

4.	Approval. Obtain the Engineer’s approval of all mix designs prior to use. Approval of the Job Mix Design does not constitute acceptance of produced concrete and will not obligate the Department to accept or pay for concrete that does not meet the mix acceptance requirements of Section 501-3.04.

CONSTRUCTION REQUIREMENTS

501-3.01 BATCHING. Batch concrete according to the approved Job Mix Design.

1.	Certification and Calibration. Batch concrete using a certified batch plant obtained by at least one of the methods listed in this Subsection. Use and maintain calibrated weighing and measuring devices for all concrete batching equipment (including measuring devices for adding material on-site) meeting the requirements of this Subsection. Submit all documentation required for plant certification and weighing and measuring device calibration before commencing concrete work.

a.	Plant Certification by the National Ready Mix Concrete Association. Certification may be obtained from the National Ready Mix Concrete Association (NRMCA). Information concerning NRMCA certification may be obtained from the NRMCA at 900 Spring Street, Silver Springs, MD 20910 or online at www.nrmca.org. The NRMCA certification is considered valid for 2 years from the date of inspection.

b.	Plant Certification by a Professional Engineer. Certification may be obtained by an independent inspection and evaluation by a Professional Engineer, registered in the State of Alaska, using and completing the NRMCA Plant Certification Check List. Correct all deficiencies to the satisfaction of the Professional Engineer. The Professional Engineer must sign and seal the completed NRMCA Plant Certification Check List certifying all applicable items have been met. The certification by a Professional Engineer is considered valid for 2 years from the date of inspection.

c.	Plant Certification by the Plant Manager. Certification may be obtained by an inspection and evaluation conducted by the Plant Manager, defined as the person directly responsible for the daily plant operation, using and completing the NRMCA Plant Certification Check List. Correct all deficiencies to the satisfaction of the Plant Manager. The Plant Manager must sign the completed NRMCA Plant Certification Check List certifying all applicable items have been met. The certification by the Plant Manager is considered valid for 6 months from the date of inspection.

d.	Weighing and Measuring Devices. Use weighing and measuring devices that meet the requirements of the National Institute of Standards and Technology Handbook 44: Specifications, Tolerances, and other Technical Requirements for Weighing and Measuring Devices and are calibrated by a commercial scale service or certified by the DOT&PF Division of Measurement Standards & Commercial Vehicle Enforcement. Calibrate all weighing and measuring devices using equipment traceable to the Alaska State Standards of Weight and Measure as adopted by AS 45.75.020.

Calibrate all weighing and measuring devices within 12 months of placing concrete in the work, after each move, at least once every 12 months until the work is completed, and at such other times when in the opinion of the Engineer there is a question as to their accuracy or adequacy.

e.	Certification and Calibration Submittals. If the Plant Certification is by the NRMCA, then submit a copy of the NRMCA Certificate of Conformance. If the Plant Certification is by a Professional Engineer or the Plant Manager, then submit a copy of the completed NRMCA Plant Certification Check List and associated Fleet Inspection Reporting Spreadsheet.

Submit copies of inspection worksheets for all weighing and measuring devices including the most recent date of inspection and the calibrated accuracy for each weighing and measuring device.

2.	Measuring Materials.

a.	Cementitious Materials. Use cementitious materials that are of the same brand, type, and from the same plant of manufacture as the cementitious materials used in the trial mixtures of the approved Job Mix Design. Ensure the quantity of the Portland cement and the cumulative quantity of Portland cement plus other cementitious materials is proportioned in amounts required by the Job Mix Design and meets the mix acceptance requirements.

Unless otherwise noted, measure cementitious materials by mass. When other cementitious materials, including fly ash or silica fume, are specified in the concrete proportions, the mass may be cumulatively weighed with the Portland cement. Weigh all cementitious materials on a weighing device that is separate and distinct from those used for other cementitious materials. Weigh the Portland cement before other cementitious materials.

If approved by the Engineer, Portland cement is permitted to be measured in bags of standard mass (94 pounds). Do not use a fraction of a bag of cementitious materials unless its mass has been determined.

b.	Aggregates. Use aggregates from the same sources and have the same size ranges as the aggregates used in the trial mixtures of the approved Job Mix Design. Ensure the quantity of the aggregates is proportioned in amounts required by the Job Mix Design and meets the mix acceptance requirements.

Unless otherwise noted, measure aggregates by mass. Establish batch mass measurements on dry materials and adjust the actual scaled weight for the required masses of dry materials plus the total mass of moisture (both absorbed and surface) contained in the aggregate. Weigh all aggregates on a weighing device that is separate and distinct from those used for other aggregates.

c.	Water. The total quantity of mixing water includes water added to the batch, ice added to the batch, water occurring as surface moisture on the aggregates, and water introduced in the form of admixtures. Measure the added water by weight or volume. Measure added ice by weight. Discharge the flush water (wash water) prior to loading the next batch of concrete. Do not use flush water (wash water) as a portion of the mixing water.

d.	Admixtures. Use admixtures that are the same brand, type, and from the same manufacturer as the admixtures used in the trial mixtures of the approved Job Mix Design. Add concrete admixtures to the concrete mix according to the manufacturer's written procedure and as approved by the Engineer.

Measure powered admixtures by weight. Measure paste or liquid admixtures by weight or volume.

3.	Materials Storage and Handling.

a.	Cementitious Materials. Store cementitious materials in dry, watertight buildings, bins, or silos that will exclude contaminants. Do not use cementitious materials which for any reason have become partially set or which contain lumps of caked cementitious material. If cementitious material is held in storage for a period longer than 3 months if bagged or 6 months if bulk, or if the Engineer suspects the cementitious material is damaged, retest the cementitious material before being used in the work.

b.	Aggregates. Use methods that do not allow segregation of the aggregates or contamination with foreign materials when handling or storing aggregates. Store aggregates in separate stock piles sufficiently removed from each other to prevent the materials at the edges for the piles from becoming intermixed. When transporting aggregates, maintain a uniform grading of the material. Do not use aggregates that have become segregated or mixed with earth or foreign material.

Provide adequate drainage so that the moisture content of the aggregates is uniform at the time of batching. If aggregates have been produced or handled by hydraulic methods, or if they have been washed, store them for draining at least 12 hours before they are batched. If the aggregates contain high or non-uniform moisture content, storage periods may require more than 12 hours.

Do not use aggregates that contain ice, are frozen, or have been heated directly by gas or oil flame or on sheet metal over an open fire. Use steam-coil or water-coil heating when heating aggregates. Use other methods only when approved. If using live steam to thaw frozen aggregate piles, completely drain excess moisture.

c.	Admixtures. Protect stored admixtures against contamination, evaporation, or damage. Provide agitating equipment for admixtures used in the form of suspensions or non-stable solutions to ensure uniform distribution of the ingredients. Protect liquid admixtures from freezing and from temperature changes that would adversely affect their characteristics.

4.	Bins. Dispense coarse and fine aggregate from separate bins. Use bins that are designed to discharge freely into the weighing hoppers. Provide control so that as the material in the weighing hopper approaches the desired quantity, the bin adds material slowly and shuts off with precision. Provide a means of removing any overload. Use weighing hoppers constructed to eliminate accumulations of tare materials and to discharge fully.

501-3.02 MIXERS AND AGITATORS. Mixers may be stationary or truck mixers. Agitators may be truck mixers operating at agitation speed or truck agitators.

Equip stationary mixers with a metal plate or plates on which are plainly marked the mixing speed of the drum or paddles, and the maximum capacity in terms of the volume of mixed concrete. When used for the complete mixing of concrete, equip stationary mixers with an acceptable timing device that will not permit the batch to be discharged until the specified mixing time has elapsed.

Ensure each truck mixer or agitator displays the truck manufacturer's data plate or plates, permanently located in a prominent place, on which are plainly marked the gross volume of the drum, the capacity of the drum or container in terms of the volume of mixed concrete, and the minimum and maximum mixing speeds of rotation of the drum, blades, or paddles. In addition to the truck manufacturer's data plate, ensure each truck mixer has a permanently attached rating plate issued by and according to the capacity requirements of the Truck Mixer Manufacturers Bureau (TMMB), as approved by National Ready Mix Concrete Association (NRMCA), on which is stated the maximum capacity in terms of volume of mixed concrete for the various uses to which the equipment is applicable.

Use stationary and truck mixers capable of combining the ingredients of the concrete within the specified time or the specified number of revolutions, into a thoroughly mixed and uniform mass. Use truck mixers and agitators capable of maintaining the mixed concrete and discharging the concrete without segregation. Equip truck mixers and agitators with devices to readily determine the number of mixing revolutions of the drum, blades, or paddles. Clean mixers and agitators of accumulation of hardened concrete or mortar before use.

Whenever truck mixers are equipped with a water system, provide water measuring devices such as sight gauges, automatic cut-off siphons, or automatic shut-off water meters. Ensure the water measuring device is accurate to 1 percent of the total capacity of the system.

Examine mixers and agitators to determine changes in condition due to accumulations of hardened concrete or mortar and to detect wear of blades. When such changes are extensive enough to affect the performance, do not use the questionable mixer or agitator until the deficiencies are corrected or until proof-tests described in AASHTO M 157 Annex A1 indicate concrete uniformity is satisfied.

501-3.03 MIXING AND DELIVERY. Mix concrete in the proportioned amounts required by the Job Mix Design. Mix all ingredients into a thoroughly intermingled uniform mixture. Do not retemper concrete mixtures. Do not use concrete that has developed initial set prior to placement.

Mix and deliver concrete to the point of designation by means of truck-mixed concrete in which the concrete is mixed only in a truck mixer, central-mixed concrete in which the concrete is mixed completely in a stationary mixer, or shrink-mixed concrete in which the concrete is first partially mixed in a stationary mixer, and then mixed completely in a truck mixer.

1.	Truck-Mixed Concrete. After all ingredients including water are in the drum, immediately mix the concrete for 70 to 100 revolutions at the mixing speed designated by the manufacturer to produce thoroughly mixed concrete. If the concrete is not thoroughly mixed with 100 revolutions of mixing, do not use that mixer until the condition is corrected. While waiting to discharge the concrete, agitate the concrete mixture continuously, beyond the number of revolutions found to produce thoroughly mixed concrete, at the manufacturer designated agitating speed. To provide adequate mixing ability, do not mix concrete in volumes exceeding the maximum mixing capacity shown on the rating plate.

Do not use flush water (wash water) as a portion of the mixing water for the succeeding batch. Remove all water from the drum before batching concrete.

2.	Central-Mixed Concrete. Charge the batch into the mixer so that some water will enter in advance of the cementitious materials and aggregate, and all water is in the drum by the end of the first quarter of the specified mixing time. Begin counting the mixing time from the time all the solid materials are in the drum. Mix for at least 1 minute plus 15 seconds for each cubic yard of the mixer's capacity, unless mixer performance tests are performed according to AASHTO M 157 Annex A1. Operate the mixing equipment within the limits of capacity and speed designated by the manufacturer of the equipment.

Transport the concrete to the point of delivery either in a truck agitator, or a truck mixer operating at agitating speed. Do not allow the volume of concrete in the truck agitator, or truck mixer operating at agitating speed to exceed 80 percent of the total volume of the drum or container.

3.	Shrink-Mixed Concrete. Charge the batch into the mixer so that some water will enter in advance of the cementitious materials and aggregate, and all water is in the drum by the end of the first quarter of the specified mixing time. Begin counting the mixing time from the time all the solid materials are in the drum. Mix for at least 30 seconds or until the ingredients have been thoroughly blended. Operate the mixing equipment within the limits of capacity and speed designated by the manufacturer of the equipment.

After transfer to a truck mixer, immediately mix the concrete for 50 to 100 revolutions at the mixing speed designated by the manufacturer to produce thoroughly mixed concrete. Do not use truck agitators for shrink mixing. To provide adequate mixing ability, do not mix concrete in volumes exceeding the maximum mixing capacity shown on the rating plate.

4.	Addition of Water. A one-time addition of water from the truck water system or elsewhere may be added on-site provided all of the following are met:

a.	A truck mixer is used to transport the concrete and the volume of concrete in the truck mixer does not exceed the maximum mixing capacity shown on the rating plate.

b.	The water measuring device is calibrated according to Subsection 501-3.01.1.d.

c.	The truck mixer is stationary and essentially level.

d.	The slump of the concrete is less than the maximum slump in the approved Job Mix Design.

e.	The maximum water content for the batch as established by the approved Job Mix Design is not exceeded. If concrete has been discharged, account for the actual volume of concrete remaining in the truck mixer.

f.	No more than 1 cubic yard of concrete has been discharged.

g.	All water additions are completed within 30 minutes after the introduction of the mixing water to the cementitious materials.

The one-time addition of water is not prohibited from being several distinct additions of water provided that no concrete has been discharged except for slump testing. Inject additional water into the mixer under pressure and direction of flow to allow for proper distribution within the mixer. Provide at least 30 additional drum revolutions at mixing speed to ensure that a homogenous mixture is attained. Do not add water to the batch at any later time.

5.	Time for Placement. Complete discharging the concrete within 1.5 hours after the introduction of the mixing water to the cementitious materials and aggregates or the introduction of the cementitious materials to the aggregates, or before the drum has revolved 300 revolutions, whichever comes first.

501-3.04 EVALUATION OF MATERIAL FOR ACCEPTANCE. All concrete in the work will be evaluated for acceptance.

The Engineer may evaluate Class W concrete based on a Certificate of Compliance provided by the supplier according to Subsection 501-3.04.1.

The Engineer will evaluate all other concrete according to Subsection 501-3.04.2.

The Engineer may reject any batch or load of concrete that fails to meet the requirements for proportions, slump, entrained air content (if applicable), or temperature. The Engineer may reject any batch or load of concrete, prior to sampling that appears defective in composition. Do not incorporate rejected material into the structure.

The Engineer may reject any structure or portion of any structure that contains concrete that fails to meet the requirements for proportions, requirements for entrained air content (if applicable), requirements for compressive strength, was cured in a manner not meeting the required curing conditions, is cracked, spalled or otherwise defective, or is constructed in a manner that does not conform to this Section.

1.	Certification of Compliance. Certify that the concrete is in compliance with the approved Job Mix Design. Include the following information:

a.	Manufacturer plant (batching facility)

b.	Department contract number

c.	Date

d.	Time batched

e.	Truck number

f.	Initial revolution counter reading

g.	Quantity (quantity batched this load)

h.	Type of concrete by class and producer design mix number

i.	Portland cement producer, type, and manufacturer’s certified test report number

j.	Fly ash and silica fume brand and type (if used)

k.	Approved aggregate gradation designation

l.	Mix design weight per cubic yard and actual batched weights for:

(1)	Cementitious materials (each component)

(2)	Coarse concrete aggregate and moisture content (each size)

(4)	Fine concrete aggregate and moisture content

(5)	Water (including free moisture in aggregates)

(6)	Admixtures brand and total quantity batched

Provide a certification of compliance, signed by a responsible representative of the concrete producer, affirming the accuracy of the information provided.

2.	Evaluation for Acceptance. The Department will sample, test, and evaluate concrete according to this Subsection.

a.	Sampling. The Department will take samples at the discharge point of the placement system, except that Class S concrete and Class DS concrete will be sampled at the truck discharge.

Provide adequate and representative fresh concrete as directed at locations designated by the Engineer for sampling and testing of concrete properties and making of strength specimens. The Engineer will sample the concrete after a minimum of 1/2 cubic yard of concrete has discharged from the placement system. Once the concrete has been sampled for acceptance testing, do not make adjustments to the mix.

The Engineer will determine aggregate gradation for acceptance based on random samples taken at the plant.

b.	Test Methods. Acceptance sampling and testing will be performed by the Department according to the following test methods:

WAQTC TM 2	Sampling Freshly Mixed Concrete

WAQTC FOP for AASHTO T 309	Temperature of Freshly Mixed Portland

Cement Concrete

AASHTO T 22	Compressive Strength of Cylindrical

Concrete Specimens

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse

Aggregates, and Materials Finer Than

No. 200 Sieve in Mineral Aggregate by

Washing

WAQTC FOP for AASHTO T 23	Method of Making and Curing Concrete

Test Specimens in the Field

WAQTC FOP for AASHTO T 119	Slump of Hydraulic Cement Concrete

WAQTC FOP for AASHTO T 121	Density (Unit Weight), Yield, and Air

Content (Gravimetric) of Concrete

WAQTC FOP for AASHTO T 152	Air Content of Freshly Mixed Concrete

by the Pressure Method

AASHTO T 231	Capping Cylindrical Concrete

Specimens

c.	Batch Tickets. Provide a batch ticket with every batch or load of concrete delivered to the project. Include the following information:

(1)	Manufacturer plant (batching facility)

(2)	Department contract number

(3)	Date

(4)	Time batched

(5)	Truck number

(6)	Initial revolution counter reading

(7)	Quantity (quantity batched this load)

(8)	Type of concrete by class and producer design mix number

(9)	Weights of every type of Cementitious Material

(10)	Weight of Fine Aggregate

(11)	Weight of Coarse Aggregate

(12)	Weight or volume of every type of Admixture

(13)	Weight or volume of Water added at the plant

(14)	Percent moisture of Fine and Course Aggregates

d.	Proportion Requirements. Meet the proportion requirements of the approved Job Mix Design within the following tolerances:

(1)	Total Cementitious Material, weight 	±1%

(2)	Fine Aggregate, weight	±2%

(3)	Coarse Aggregate, weight	±2%

(4)	Admixtures, weight or volume	±3%

(5)	Total Water, weight or volume	±3%

If the total cementitious material weight is made up of different components, keep the component weights within the following tolerances:

(a)	Portland Cement	±1%

(b)	Fly Ash	±5%

(c)	Silica Fume	±10%

e.	Slump Requirements. Meet the slump requirement for the approved Job Mix Design within the following tolerances:

(1)	For Job Mix Design slump of 3 inches or less: +0.0 inches, -1.5 inches

(2)	For Job Mix Design slump greater than 3 inches: +0.0 inches, -2.5 inches

f.	Entrained Air Content Requirements. Meet the entrained air content (if applicable) for the approved Job Mix Design within a tolerance of ±1.5 percent.

g.	Temperature Requirements. Unless otherwise noted, ensure the concrete temperature is between 50°F and 90°F while being placed in the forms. Satisfy the requirements for cold weather and hot weather concrete.

h.	Compressive Strength Requirements. Meet the strength requirements for the specified compressive strength. Concrete of the approved Job Mix Design will be considered to meet the specified compressive strength requirements when both of the following conditions are met:

(1)	The individual strength tests do not fall below the specified compressive strength by more than 10.0 percent or 500 psi, whichever is greater.

(2)	The lowest averaged result of three consecutive individual strength tests meets or exceeds the specified compressive strength.

An individual strength test is the average 28-day strength of all cylinders fabricated for acceptance purposes from the same sample of concrete produced using the approved Job Mix Design and tested according to AASHTO T 22.

i.	Gradation Requirements. Meet the gradation requirements of Table 501-1 for fine aggregate sampled at the plant. Meet the gradation requirements of Table 501-1 for coarse aggregate sampled at the plant according the size number given in the approved Job Mix Design.

501-3.05 COLD WEATHER CONCRETE. When air temperatures are expected to be below 35°F during concrete placement or the curing period, have in place the materials and equipment required to heat mixing water and aggregate and to prevent the concrete temperature from falling below 35°F. Implement the cold weather plan when the descending air temperature in the shade, away from artificial heat, is less than 35°F or, in the opinion of the Engineer, will likely do so within 24 hours. Do not place concrete until the Engineer has approved the cold weather-concreting plan.

1.	Submittals. Submit, for approval, a written cold weather-concreting plan when air temperatures are expected to be below 35°F during concrete placement or the curing period. Submit detailed procedures for the production, transportation, placement, protection, curing, and temperature monitoring of concrete during cold weather for each concrete placement. Include procedures to be implemented upon abrupt changes in weather conditions or equipment failures.

2.	Preparation. Remove all snow, ice, and frost from the surfaces, including reinforcement, against which the concrete is to be placed. Before beginning concrete placement, thaw the subgrade to at least 2 feet below the concrete to be placed. Do not place concrete around or adjacent to forms, embedded items, concrete, steel, or any other material unless such items are preheated and maintained at a temperature above 35°F.

3.	Temperature of Concrete. Ensure that concrete being placed in forms is between 50°F and 70°F. Obtain these temperatures by heating the mixing water and/or aggregate. Heat mixing water to no more than 150°F. Heat aggregate as provided in Subsection 501-3.01.3.b.

When the temperature of the water or aggregate exceeds 100°F, mix them together so that the temperature of the combined ingredients does not exceed 80°F when the cementitious materials are added.

4.	Admixtures. Use only admixtures shown in the approved mix design.

5.	Protection of Concrete. Protect the concrete from damage due to cold weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.11.

If the minimum curing temperature cannot be maintained, do not allow the concrete temperature to drop below 35°F. Provide extra protection in areas especially vulnerable to temperatures below 35°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Maintain the concrete temperature using methods such as insulated forms, enclosures, and indirect heat. When using combustion heaters, vent flue gases from combustion heating units to the outside of the enclosure. Prevent overheating areas of concrete or drying during the curing period by directing heaters and ducts away from the concrete surface. Do not expose the concrete surface to air with a temperature more than 90°F, unless higher values are required by an accepted curing method.

Protection may be terminated when the ascending air temperature in the shade, away from artificial heat, rises above 35°F and is expected to remain above 35°F for at least 24 hours. At the end of the protection period, remove the protection so the concrete drops in temperature gradually at a rate not more than 1°F per hour. If water curing is used, terminate the addition of water to the surface and allow the concrete surface to dry prior to exposure of the concrete to freezing temperatures.

When concrete placed within cofferdams is cured by flooding the cofferdam with water, the above conditions do not apply if the water that contacts the concrete is not allowed to freeze.

The Engineer may reject concrete that has been inadequately protected, damaged by cold weather or overheating, or concrete whose temperature has fallen below 35°F during placement or during the curing period.

501-3.06 HOT WEATHER CONCRETE. If conditions exist that could result in concrete temperatures exceeding 90°F using normal methods, take temperature-reduction measures as required by the Engineer before placing the concrete. Provide concrete within the specified temperature limits as follows:

1.	Shade or cool aggregate piles. Do not sprinkle fine aggregate piles with water. If sprinkling coarse aggregates, monitor the moisture content and adjust the mixing water for the free water in the aggregate.

2.	Refrigerate mixing water or replace all or part of the mixing water with crushed ice, provided the ice is completely melted before concrete placement commences.

If the air temperature exceeds 90°F when placing concrete, use water spray or other methods to cool concrete-contact surfaces to less than 90°F. These surfaces include forms, reinforcing steel, steel beam flanges, and others that touch the mix. Reduce the time between mixing and placing and do not permit mixer trucks to remain in the sun while waiting to discharge concrete. Shade chutes, conveyors, and pump lines. Finish the concrete without delay.

Provide water-fogging equipment at the site if needed after finishing to prevent plastic cracks.

Figure 501-1

Surface Evaporation from Concrete

Surface Evaporation

From Concrete

- Enter chart at appropriate air temperature and relative humidity above.

- Move right to line corresponding to the concrete temperature.

- Move down to line approximating the wind velocity.

- Read evaporation rate on scale to left of this point.

When placing deck concrete that is 80°F or hotter, install equipment at the site to show relative humidity and wind velocity. If the evaporation rate at the concrete site is 0.1 lb/ft2/h or more (determined from Figure 501-1), surround the fresh concrete with an enclosure. This enclosure will protect the concrete from wind blowing across its surface until the curing compound is applied.

501-3.07 PREPARATION FOR CONCRETE PLACEMENT. Do not begin concrete placement without the Engineer's authorization. Allow time for inspection of forms, reinforcing steel, prestressing steel, ducts, utilities, joints, and other items embedded or attached to the concrete.

Remove all debris, concrete splatter, oil, paint, and other foreign substances from the surfaces of forms and reinforcing steel against which the concrete is to be placed.

During precipitation, or when the Engineer determines that precipitation is likely before the finishing is complete, employ all necessary materials and equipment needed to protect the concrete until completion of the finishing operations and final set has taken. Do not expose the concrete to rain or run-off before final set occurs.

As necessary, ensure all materials and equipment are in place according to the cold weather concreting plan. Heat the forms as necessary. Remove all water, snow, ice, and frost before placing concrete.

For piles, remove all water and foreign material from shells and pipes before placing concrete according to Section 505.

Prepare foundations according to Section 205.

Moisten all foundations and forms with water just before the concrete is placed. Remove standing water on the foundation or in the form before placing concrete.

501-3.08 PLACING CONCRETE. Place concrete conforming to the approved Job Mix Design. Reduce the time to discharge to ensure concrete is always plastic and workable. Place concrete continuously throughout each section of the structure or between indicated joints with no interruption longer than 30 minutes between adjoining layers. Consolidate the concrete mix to make a dense homogeneous concrete. Place and consolidate each layer before the preceding layer takes initial set.

If an emergency forces you to stop placing concrete before a section or layer is completed or if initial set occurs before the succeeding section or layer is placed, place construction joints according to Subsection 501-3.14. Treat the resulting joint as a construction joint. If, in the opinion of the Engineer, the location of the construction joint is of such extent or character as to affect the strength or durability of the concrete, the Engineer will reject the concrete.

Place concrete as near as possible to final position. Do not allow segregation of aggregate or displace reinforcing steel. Do not deposit a large quantity of concrete at any point and run or work the concrete along the forms. Regulate concrete placement so that the pressures caused by wet concrete do not exceed those used in the design of the forms. Limit layer thickness to no more than 2.5 feet deep, or the capacity of the vibrators to consolidate and merge the concrete with the previous layer, whichever is less. Consolidate each layer adequately leaving a compact, dense, and impervious concrete with smooth faces on exposed surfaces with no visible line of separation between adjoining layers.

Do not allow segregation of coarse or fine portions of the mixture while placing concrete. When placing operations would involve dropping the concrete more than 5.0 feet, use a tremie, tube, or other such device to limit the free-fall height to less than 5.0 feet and prevent segregation of the mix and spattering of mortar on the reinforcing steel and forms above the elevation of the lift being placed. Use clean, watertight equipment and material, but do not use those made of aluminum. Do not allow concrete to slide down the sides of the forms.

Prevent mortar from spattering on forms and reinforcing steel and from drying ahead of the final concrete covering.

After initial set, prevent movement of forms, projecting ends of reinforcing bars, and other embedded items.

Place concrete in the superstructure only after substructure forms are removed to allow inspection of supporting concrete.

Place concrete in precast concrete members in a sequence to obtain a well-consolidated concrete and to prevent settlement or shrinkage cracks.

The Engineer may reject structures with construction joints in locations other than those shown on the Plans or excessive honeycomb areas as determined by the Engineer.

1.	Pumping Concrete. Concrete may be pumped if the equipment will handle the class of concrete, with the slump and air content specified, and no equipment vibrations will damage freshly placed concrete. Use a pump that produces a continuous stream of concrete without air pockets. Do not use aluminum pump lines or aluminum components in contact with fresh concrete. When pumping is completed, the concrete remaining in the pipeline, if used, must eject without contaminating the concrete or separating the ingredients. Discard concrete contaminated by priming or cleaning the pump. Take concrete samples for testing at the discharge end of the pipe, unless otherwise noted. Provide the necessary samples of concrete as directed.

2.	Conveying Concrete. Concrete may be placed using a conveyor belt if the equipment will handle the class of concrete, with the slump and air content specified, without segregation of the aggregate and that no equipment vibrations will damage freshly placed concrete or reinforcing steel. Limit the length of conveyor belts to prevent aggregate segregation or 300 feet, whichever is least. Cover the belt to protect the concrete from heat, evaporation, precipitation, or when the Engineer determines that precipitation is likely.

3.	Vertical Members and Piles. Place concrete in columns, walls, substructures, and other similar vertical members in one continuous operation.

Place concrete immediately after the reinforcing steel is placed in piles and all standing water is removed from the pile. Do not place concrete underwater in piles. Concrete may be discharged directly into piles and permitted to free-fall into place if the concrete does not contact reinforcing steel or other objects while falling. Vibrate at least the top 5 feet of concrete in piles.

4.	Underwater Placement for Cofferdams. Only concrete used to seal the floor of cofferdams may be placed under water. Deposit concrete under water, using a tremie or pump. Carefully place the concrete in a compact mass with minimal disturbance. Maintain still water at the point of deposit. Vent cofferdams during placement and curing to equalize hydrostatic pressure and prevent flow of water through the concrete during this period.

a.	Tremie Concrete. Use a watertight tremie with an inside diameter of at least 10 inches. Do not use an aluminum tremie or aluminum components in contact with fresh concrete. Construct the tremie line to readily discharge concrete. Construct the discharge end of the tremie to prevent water intrusion and permit the free flow of concrete during concrete placement. Use caps, bottom plates, pigs, or other such devices inserted into or attached to the tremie pipe to separate the concrete from the water during initial charging of the tremie. Ensure that the tremie has sufficient length and weight to rest on the cofferdam bottom before starting concrete placement.

When using a tremie with a cap or bottom plate, tightly close the bottom of the tremie. Place enough concrete in the tremie to prevent the flow of water into the tremie.

If a pig is used, set the discharge orifice of the tremie loosely on the bottom. Insert the pig at the top and then place concrete to push the pig ahead, separating the concrete from the water. Take care to ensure that the pig is properly sized to fit in the tremie, and keeps the concrete separate from the water so that all fluid is expelled from the pipe during the initial charging process. When the pipe is filled with concrete, lift the pipe off the bottom the minimum amount needed to start the concrete flowing.

Once concrete flow has started, place concrete into the tremie at a sufficient rate to maintain a positive head of concrete inside the tremie relative to the water level. Position the discharge orifice within one tremie diameter from the bottom of the cofferdam until the orifice is at least 3 feet below the concrete surface. The discharge orifice may be re-positioned at any time provided the orifice is maintained at least 3 feet below the concrete surface at all times. Monitor the concrete level during placement to ensure that the tremie discharge orifice remains below the concrete surface throughout placement.

Provide adequate support so the tremie can be raised to increase the discharge of concrete and lowered to reduce the discharge of concrete. Do not rapidly raise or lower the tremie to increase the discharge of the concrete. Keep the flow continuous until the work is completed. Produce a concrete seal that is monolithic and homogeneous.

b.	Pumped Concrete. In addition to the pumping concrete requirements in Subsection 501-3.08.1, use concrete pump lines that are watertight with an inside diameter of at least 5 inches. Construct the discharge end of the pump line to prevent water intrusion and permit the free flow of concrete during placement operations. Use pigs or other such devices inserted into or attached to the pump line to separate the concrete from the water during initial charging of the line. Ensure that the pump line has sufficient length and weight to rest on the cofferdam bottom before starting concrete placement.

If a pig is used, insert the pig in the pump line to separate the concrete from the water. Take care to ensure that the pig is properly sized to fit in the line, and keeps the concrete separate from the water so that all fluid is expelled from the line during the initial charging of the line.

Position the discharge orifice within one pump line diameter from the bottom of the cofferdam. Prevent the pump line from moving until the orifice is at least 3 feet below the concrete surface. The discharge orifice may be re-positioned at any time provided the orifice is maintained at least 3 feet below the concrete surface at all times. Monitor the concrete level during placement to ensure that the pump line discharge orifice remains below the concrete surface throughout placement. Temporarily reduce the pump line pressure when repositioning the pump line from one level to the next higher level.

Maintain a continuous flow of concrete and a positive pressure differential of the concrete in the pump line at all times to prevent water intrusion into the concrete. Pump concrete continuously without producing air pockets.

The thickness of the seal will depend upon the hydrostatic head, bond and spacing of piles, size of cofferdam, and other related factors. However, the seal must be at least 2 feet thick or as shown on the plans.

After enough time has elapsed to ensure proper curing and strength, dewater the cofferdam and clean the top of the concrete of scum, laitance, and sediment. Before depositing fresh concrete, remove local high spots as necessary to provide proper clearance for reinforcing steel.

5.	Drilled Shaft Foundations. Place concrete in one continuous operation following either the wet-shaft process or dry-shaft process, as applicable. Do not begin concrete placement operations until the Engineer determines the shaft excavation requirements have been satisfied.

The dry-shaft process may be used only at sites where the ground water level and soil and rock conditions are suitable to permit construction of the shaft in a relatively dry excavation, and where the sides and bottom of the shaft can be visually inspected by the Engineer prior to placing the concrete. Relatively dry excavation conditions exist when excavation fluids have been removed from the shaft and the rate of water intrusion is less than 6 inches of water accumulating above the base in a 1-hour period when no pumping is permitted. Suitable soil and rock conditions exist when the sides and bottom of the hole remain stable without caving, sloughing, or swelling between completion of excavation and concrete placement; and any loose material and water can be satisfactorily removed prior to inspection and concrete placement. Less than 1 inch of water will be permitted in the bottom of the shaft excavation at the time of concrete placement. For shafts that do not meet the dry-shaft process requirements, use the wet-shaft process.

a.	Wet-Shaft Process. Place concrete as soon as possible after reinforcing steel placement using a tremie or concrete pump. Place concrete continuously until after the shaft is full and good quality concrete, as determined by the Engineer, is evident at the top of shaft. Good quality concrete is considered concrete of the same consistency, appearance, and quality as the concrete being delivered and meeting the applicable mix acceptance requirements. Remove a sufficient volume of concrete to ensure elimination of all contaminated concrete at the top of shaft before continuing with subsequent construction operations.

Concrete may be placed directly into the shaft without mechanical vibration, except vibrate the top 5 feet of concrete. Remove concrete laitance during or immediately after concrete placement operations have ended. Begin vibrating the concrete after good quality concrete is evident at the top of the shaft and after all fluids including water, slurry, drilling aids, and other materials other than concrete have been removed.

Do not expel water, fluids, drilling aids, or concrete from the top of the shaft into streams or other waterways.

(1)	Process Control Testing. Test for entrained air content and slump before placing each batch of concrete in the drilled shaft. Perform all sampling and testing according to Subsection 501-3.04.2.b using a WAQTC qualified concrete testing technician or ACI certified concrete field testing technician. Test every batch of concrete before placement. In addition, test for slump from a sample of the first batch of concrete immediately after concrete placement operations are completed to verify the concrete flowability requirements have been satisfied. Record and submit to the Engineer the results of each test.

(2)	Concrete Flowability Requirements. Ensure that all concrete placed in the shaft remains flowable throughout placement operations by maintaining a slump of at least 6 inches and limiting changes in slump to less than 2 inches until placement is completed.

(3)	Tremie Concrete. Use a watertight tremie with an inside diameter of at least 10 inches. Do not use an aluminum tremie or aluminum components in contact with fresh concrete. Construct the tremie line to readily discharge concrete. Construct the discharge end of the tremie to prevent water intrusion and permit the free flow of concrete during concrete placement. Use caps, bottom plates, pigs, or other such devices inserted into or attached to the tremie pipe to separate the concrete from the excavation fluid during initial charging of the tremie. Ensure that the tremie has sufficient length and weight to rest on the shaft bottom before starting concrete placement.

When using a tremie with a cap or bottom plate, tightly close the bottom of the tremie. Place enough concrete in the tremie to prevent the flow of excavation fluid into the tremie.

If a pig is used, set the discharge orifice of the tremie loosely on the bottom. Insert the pig at the top and then place concrete to push the pig ahead, separating the concrete from the excavation fluid. Take care to ensure that the pig is properly sized to fit in the tremie, and keeps the concrete separate from the excavation fluid so that all fluid is expelled from the pipe during the initial charging process. When the pipe is filled with concrete, lift the pipe off the bottom the minimum amount needed to start the concrete flowing.

Once concrete flow has started, place concrete into the tremie at a sufficient rate to maintain a positive head of concrete inside the tremie relative to the excavation fluid level. Position the discharge orifice within one tremie diameter from the base of the shaft until the orifice is at least 8 feet below the concrete surface. The discharge orifice may be re-positioned at any time provided the orifice is maintained at least 8 feet below the concrete surface at all times. Monitor the concrete level during placement to ensure that the tremie discharge orifice remains below the concrete surface throughout placement.

Provide adequate support so the tremie can be raised to increase the discharge of concrete and lowered to reduce the discharge of concrete. Do not rapidly raise or lower the tremie to increase the discharge of the concrete.

(4)	Pumped Concrete. In addition to the pumping concrete requirements in Subsection 501-3.08.1, use concrete pump lines that are watertight with an inside diameter of at least 5 inches. Construct the discharge end of the pump line to prevent water intrusion and permit the free flow of concrete during placement operations. Use pigs or other such devices inserted into or attached to the pump line to separate the concrete from the excavation fluid during initial charging of the line. Ensure that the pump line has sufficient length and weight to rest on the shaft bottom before starting concrete placement.

If a pig is used, insert the pig in the pump line to separate the concrete from the excavation fluid. Take care to ensure that the pig is properly sized to fit in the line, and keeps the concrete separate from the excavation fluid so that all fluid is expelled from the line during the initial charging of the line.

Position the discharge orifice within one pump line diameter from the base of the shaft. Prevent the pump line from moving until the orifice is at least 8 feet below the concrete surface. The discharge orifice may be re-positioned at any time provided the orifice is maintained at least 8 feet below the concrete surface at all times. Monitor the concrete level during placement to ensure that the pump line discharge orifice remains below the concrete surface throughout placement. Temporarily reduce the pump line pressure when repositioning the pump line from one level to the next higher level.

Maintain a continuous flow of concrete and a positive pressure differential of the concrete in the pump line at all times to prevent water or slurry intrusion into the concrete. Pump concrete continuously without producing air pockets.

If at any time the tremie or pump line discharge orifice is above the fluid concrete surface the shaft will be considered defective. Immediately terminate concrete placement operations and notify the Engineer. With the approval of the Engineer, implement the action plan to rectify the defect according to the drilled shaft installation plan in Section 515.

Provide operational standby equipment adequate to complete concrete placement in the time specified. Locate the standby concrete placement equipment at the job site during shaft concrete placement operations.

b.	Dry-Shaft Process. Place concrete as soon as possible after reinforcing steel placement. Place concrete continuously until after the shaft is completely filled with concrete. Concrete may be discharged directly into the shaft and permitted to free-fall into place if the concrete does not contact the sides of the shaft, reinforcing steel, or other objects while free falling. Otherwise, place concrete through a tremie or concrete pump.

Concrete may be placed directly into the shaft without mechanical vibration, except vibrate the top 5 feet of concrete. Remove concrete laitance during or immediately after concrete placement operations have ended.

(1)	Process Control Testing. Test for entrained air content and slump before placing each batch of concrete in the drilled shaft. Perform all sampling and testing according to Subsection 501-3.04.2.b using a WAQTC qualified concrete testing technician or ACI certified concrete field testing technician. Test every batch of concrete before placement. Record and submit to the Engineer the results of each test.

(2)	Concrete Plasticity Requirements. Ensure that all concrete placed in the shaft remains plastic throughout placement operations by completing placement operations before initial set occurs.

(3)	Tremie Concrete. Use a tremie with an inside diameter of at least 10 inches. Do not use an aluminum tremie or aluminum components in contact with fresh concrete. Ensure that the tremie has sufficient length to limit the free fall height to less than 5 feet. Construct the tremie line to readily discharge concrete. Construct the discharge end of the tremie to permit the free flow of concrete during concrete placement.

(4)	Pumped Concrete. In addition to the pumping concrete requirements in Subsection 501-3.08.1, use concrete pump lines with an inside diameter of at least 5 inches. Ensure that the pump line has sufficient length to limit the free fall height to less than 5 feet.

(5)	Free-Falling Concrete. Provide a centering drop chute at least 3 feet long.

Do not permit free falling concrete to strike the sides of the shaft, reinforcing steel cage, or any other obstruction. Reduce the height of free fall, the rate of concrete flow, or both if the concrete strikes the sides of the shaft, reinforcing steel cage, or any other obstruction.

Provide operational standby equipment adequate to complete concrete placement in the time specified. Locate the standby concrete placement equipment at the job site during shaft concrete placement operations.

6.	Concrete Slab and Girder Spans. Cast slabs and girders with spans of 30 feet or less in one continuous operation.

If casting girders spanning more than 30 feet in two operations, cast the girder stems to the bottom of the slab haunches, during the first operation. Provide approved shear keys meeting Subsection 501-3.14. Wait at least 24 hours between the girder casting and the slab casting. Immediately before the slab casting, check falsework for shrinkage and settlement and tighten wedges to ensure minimum deflection of the stems from the added weight of the slab.

7.	Concrete Decks and Approach Slabs. Submit a concrete placement plan to the Engineer, no less than 30 days prior to placing concrete. Do not place concrete until after the Engineer has approved the plan. Include in the concrete placement plan:

a.	concrete placement sequence,

b.	schedule of concrete placement and curing,

c.	estimated concrete volume of each section,

d.	placement rate and duration,

e.	description of finishing equipment,

f.	placement procedure,

g.	names of the screed operator, concrete foreman, and concrete finishers,

h.	curing materials, equipment, and procedure.

Hold a pre-concreting conference at least 5 working days before placing concrete. Discuss construction procedures, personnel, and equipment to be used. Include your superintendent and all foremen in charge of placing steel reinforcing bars, placing concrete, finishing concrete, and curing operations.

If the project includes more than one concrete placement operation, and if your key personnel change between concreting operations, hold additional conferences to include replacement personnel before placing successive concrete sections.

Before placing concrete, obtain the Engineer’s approval of the concrete production and placement rates, screed operator, concrete foreman, and concrete finishers. Ensure that adequate finishing tools and equipment are at the site.

Before placing any concrete, operate the finishing machine over the entire length of the bridge deck to check screed deflection, reinforcing steel clearance, and concrete thickness. Begin placing concrete only after the Engineer approves this test.

The placement operation must cover the full width of the concrete deck or approach slab and the full width between construction joints.

Do not place concrete for the deck surface more than 10 feet ahead of the strike off. Limit the rate of placing concrete to what can be finished before the beginning of the initial set.

During precipitation, or when the Engineer determines that precipitation is likely before the finishing is completed, do not place concrete in decks or other sections requiring finishing on the top surface, unless the materials and equipment needed to protect the concrete and complete the finishing operations are readily available.

a.	Concrete Decks on Non-continuous Spans. Place the concrete deck in the sequence shown on the Plans. If the placement sequence for deck on non-continuous spans is not shown on the Plans, place the concrete in not more than three sections with the first section centered on the span.

b.	Concrete Decks on Continuous Spans. Place the concrete deck in the sequence shown on the Plans. Subject to approval, you may deviate from the concrete placing sequence shown on the Plans by casting the concrete deck continuously from one end to the other provided that you:

(1)	Do not use Type III Portland cement.

(2)	Submit the methods and means, equipment, workers, and time schedule for conducting a continuous concrete placement and finishing operation in the concrete placement plan.

(3)	Stockpile the materials necessary to complete the placement and have the equipment, incidentals, and workers on the site before beginning concrete placement operations.

(4)	Ensure that the continuous concrete placement and finishing operation proceeds at a minimum rate of 30 feet per hour, measured longitudinally along the axis of the bridge.

If the Engineer approves the proposal for a continuous concrete placement operation, the Department will observe and evaluate performance to the first planned construction joint in the sequence. At this point, the Engineer may authorize you to proceed with the continuous concrete placement operation or suspend the placement and install a construction joint. The Engineer's decision will be based on whether you can produce, deliver, and finish the concrete according to the Specifications and at a continuous rate that will permit the structure to accommodate final dead load deflections while the concrete is plastic.

If the Engineer suspends the continuous concrete placement operations after the first sequential placement, submit significant modifications for improving the continuous concrete placement operations, beginning again at the other end of the bridge. Demonstrate this revised method as specified above for the initial placement.

If the Engineer suspends the continuous concrete placement operation after the second attempt, abandon the method and follow the deck placing sequence shown on the Plans.

501-3.09 CONSOLIDATION OF CONCRETE. Eliminate rock pockets and air bubbles. Vibrate along faces to obtain smooth surfaces.

Consolidate all concrete, except underwater or other exempted placements, by mechanical vibration at the point of deposit. Use internal vibration, except for thin sections, with forms designed for external vibration. Use properly sized and calibrated vibrators with a minimum frequency of 5,000 cycles per minute and capable of visibly affecting a properly designed mixture with a 1-inch slump for a distance of at least 18 inches from the vibrator.

Use enough vibrators to consolidate the fresh concrete within 15 minutes of placement in the forms, with one or more spare vibrators available in case of breakdown. Insert vibrators vertically to a depth that will effectively vibrate the full depth of each layer, penetrating into the previous layer. Withdraw vibrators slowly to avoid segregation or grout pockets. Vibrate in a uniform pattern spaced less than 1.5 times the radius of visible effectiveness.

Avoid vibration of initially set layers and reinforcing steel below the succeeding placement. Do not hold vibrators against forms or reinforcing steel or use them to flow or spread the concrete into place. Manipulate vibrators to produce concrete that is free of voids and that has the proper texture on exposed faces and the maximum consolidation. Do not hold vibrators so long that the concrete segregates, pools of mortar form, or laitance forms on the surface.

When immersion-type vibrators are used to consolidate concrete around epoxy-coated reinforcing steel, use rubber or nonmetallic vibrator heads that will not damage epoxy coatings.

501-3.10 FINISHING CONCRETE SURFACES. After the concrete has been consolidated and prior to the application of curing materials, strike-off all unformed concrete surfaces to the planned elevation and slope. Finish the surface by floating with a wooden or magnesium float to remove all local irregularities and leave sufficient mortar to seal the concrete surface. Do not use mortar topping for concrete surfaces.

Provide enough finishers to spread, straightedge, and float the concrete surface. Complete all initial floating operations before bleed water or excess moisture is present on the surface and before the concrete takes initial set. Complete final finishing before final set occurs. Do not use finishing aids or additional water to assist in finishing concrete surfaces. Do not finish concrete surfaces that have bleed water, excess moisture, or curing materials present.

Provide all formed concrete surfaces with an ordinary finish unless otherwise noted. In addition to an ordinary finish, provide all vertical concrete surfaces that are exposed in the completed work a rubbed finish as specified in item 2. Exposed surfaces extend to at least 1 foot below the finished ground line.

1.	Ordinary Finish. An ordinary finish is the finish left on a surface after removing the forms, filling the holes left by the form ties, and repairing defects. Ensure that the surface is true and even and free from rock pockets and depressions or projections.

Immediately after removing the forms, remove the metal devices holding the forms in place and passing through the body of the concrete, or cut them back at least 1 inch beneath the surface of the concrete. Remove fins of mortar and irregularities caused by form joints using a carborundum stone. Do not randomly grind surfaces.

Patch all cavities produced by form ties, depressions, holes, and voids greater than 1/4 inch. Fill the cavity with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand. Clean the cavity and saturate the concrete with water before filling the cavity. Thoroughly tamp the mixture into place. Float the surface of the mortar with a wooden float before initial set to make the surface neat in appearance. Cure the patch according to Subsection 501-3.11.

Do not repair concrete with honeycombs, rock pockets, cracks, or other defects until the concrete is inspected by the Engineer. Concrete repaired prior to inspection by the Engineer will be rejected. If, in the opinion of the Engineer, the defect is of such extent or character as to affect the strength or durability of the concrete, the Engineer will reject the concrete. Otherwise, if the defect is greater than 3/4 inch in depth, submit for approval a repair plan including complete details of the method, materials, and equipment proposed for use in repairing the concrete. Obtain the Engineer's approval of the repair plan before repairing the defect. A repair plan is not required if the defect is less than 3/4 inch in depth.

Repair all broken corners and edges, rock pockets, honeycombs, and other defects. If the defect is greater than 3/4 inch in depth, repair the defect according to the approved repair plan. If the defect is less than 3/4 inch in depth, chip away coarse or broken material according to Subsection 501-3.25 to obtain a dense, uniform surface of concrete exposing solid coarse aggregate. Cut away feathered edges to form faces perpendicular to the surface. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Patch the repaired area with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand.

When patching surfaces that will be exposed to view in the completed structure, match the color of the mortar to the concrete. Provide a rubbed finish to patched surfaces that do not satisfactorily match in color.

Repair cracks according to Subsection 501-3.27.

Perform all repairs prior to releasing falsework, prestressing, or applying additional loads to the concrete.

2.	Rubbed Finish. When forms can be removed from concrete that has set but not hardened appreciably, point and wet the surface and then rub with a wooden float until all irregularities and form marks are removed and the surface is covered with a lather composed of cement and water. If permitted, use a thin grout composed of one part Portland cement and one part fine aggregate in the rubbing. Allow this lather to set for at least 5 days. Then, smooth the surface by lightly rubbing with a fine carborundum stone.

If the concrete has hardened before being rubbed, use a medium coarse carborundum stone to finish the surface at least 4 days after placing the concrete. Spread a thin grout composed of one part Portland cement and one part fine aggregate over a small area of the surface. Immediately rub the surface with the stone until all form marks and irregularities are removed and the surface is covered with a lather. Allow this lather to set for at least 5 days. Then, smooth the surface by rubbing lightly with a fine carborundum stone.

The Engineer may waive the rubbing requirement if the concrete surfaces are formed with metal forms, form liners, or other forms specifically designed to provide a smooth concrete surface with uniform texture and color. The Engineer will not waive the rubbing requirement for plywood forms.

Complete ordinary finish work before applying the rubbed finish.

3.	Concrete Decks and Approach Slabs. Obtain a smooth riding surface of uniform texture that is true to the required grade and cross section.

Use a self-propelled mechanical finishing machine:

a.	capable of forward and reverse movement under positive control,

b.	with a rotating cylindrical single or double drum screed no more than 5 feet long,

c.	with necessary adjustments to produce the required cross-section, line, and grade,

d.	that allows all screeds to be raised and lowered under positive control, and

e.	with an upper vertical limit of screed travel that permits the screed to clear the finished concrete surface.

When placing concrete abutting previously placed concrete, the side of the finishing machine adjacent to the existing concrete must be equipped to travel on the existing concrete.

The Engineer may approve hand-operated motorized roller screeds (friction screeds) where jobsite conditions prohibit the use of conventional configuration finishing machines described above, for small areas less than 12 feet wide, and on approach slabs in which conventional configuration finishing machines are not used to finish the concrete deck. Do not use vibratory screeds.

Obtain the Engineer’s approval of the finishing machine, screed, rails, and other specially made equipment before use.

Use equipment that can strike off the full placement width without intermediate supports or rails. Use rails that rest on adjustable supports that can be removed with the least disturbance to the concrete. Place the supports on structural members or on forms rigid enough to resist deflection. Use supports that are removable to at least 2 inches below the finished surface. If possible, place rails outside the finishing area. If not possible, place them above the finished surface.

Use rails (with their supports) that are strong and stiff enough for operation of the equipment. Place and secure rails for the full length of the deck before placing concrete. Set to the proper grade and elevations to ensure the required profile is provided.

After placing and consolidating the concrete, carefully strike off the concrete surface.

Provide enough hand finishers with tools to correct imperfections left on the deck. Hand finish from rigidly constructed transverse finishing bridges that completely span the deck area being finished.

Give a float finish to surfaces that will receive a waterproof membrane. Texture all other surfaces with a heavy broom finish.

Do not place finishing machines or other loads on the screed rail supports or on features that support fresh concrete after the concrete has been placed and finished and has initially set, and before the concrete attains at least 80 percent of the specified compressive strength (f 'c) shown on the Plans.

Wait to release falsework or wedges supporting concrete on either side of a joint until each side has cured as these Specifications require.

The Engineer will test the finished surface of the concrete for surface irregularities using a 10-foot straightedge.

4.	Curb, Sidewalk, and Concrete Barrier Surfaces. Finish exposed faces of curbs, sidewalks, and concrete barriers to true surfaces and provide a broom finish.

5.	Sandblasted Finish. Sandblast the cured concrete surface with hard, sharp abrasive media to produce an even fine-grained surface in which the mortar has been cut away, leaving the aggregate exposed.

6.	Textured Concrete Surface. When the plans call for the use of aesthetic surface treatment, conform to the requirements of Section 514.

501-3.11 CURING CONCRETE. Maintain a satisfactory moisture content and temperature in the concrete commencing immediately after finishing operations are completed.

The Engineer may reject any structure or portion of a structure containing concrete that was cured in a manner not meeting the required curing conditions or is cracked, spalled, or otherwise defective. The Engineer will evaluate concrete that has cracked at any time during execution of the Contract for structural adequacy and durability. Repair cracks according to Subsection 501-3.27.

1.	Initial Curing Period. Before the final curing method can be applied, ensure the surface of the concrete is kept moist. If the concrete surface begins to dry before the final curing method can be applied, prevent further loss of moisture by one or more of the following methods:

a.	Fog Spray: Use equipment that produces a fog spray from an atomizing nozzle with sufficient velocity to cover the entire concrete surface. Direct the atomized water spray above the concrete surface to allow the fog to drift down to the concrete surface. Do not apply the discharge of the atomized water spray directly at the concrete surface. Generate sufficient velocity of the atomized water droplets to reach the extreme edges of the concrete surface. Continue fogging as necessary to maintain the reflective appearance of the damp concrete. Do not allow the surface to dry, or to undergo cycles of drying and wetting. Keep the concrete surface damp, but do not accumulate water until after final set has occurred. Use water meeting the requirements of Subsection 712-2.01.

b.	Evaporation Rate Reducer: Apply a monomolecular film intended specifically as an evaporation rate reducer to entrap bleed water or excess moisture on the concrete surface. Apply the evaporation rate reducer according to the manufacturer’s written instructions. Do not use the evaporation rate reducer during finishing operations or as a finishing aid. Do not use evaporation rate reducers on concrete surfaces that will receive a waterproofing membrane such as concrete decks, approach slabs, end diaphragms and decked precast concrete members.

2.	Final Curing Period. Unless otherwise noted, employ the final curing method immediately following the finisher or finishing machine.

Use wet curing on construction joints, concrete with a mix design water-cement ratio less than 0.40, and concrete decks, approach slabs, and other concrete surfaces subject to vehicular traffic. For all other concrete, use wet curing, liquid membrane-forming curing, forms-in-place curing, or a combination of these curing methods.

Do not use liquid membrane-forming curing compounds on concrete surfaces to which other materials will be cast against or bonded such as concrete and waterproofing membranes.

In addition to the requirements in this section, precast concrete member may use accelerated curing.

a.	Wet Curing. Until the end of the curing period, provide continuous moisture by:

(1)	watering a covering of heavy burlap blankets or quilted cotton mats,

(2)	keeping concrete surfaces wet with water continuously

(3)	wetting the outside surfaces of wood forms.

Wait to install curing materials until the concrete has sufficiently hardened to permit such operations without damaging the concrete or marring the finish. While waiting to employ curing materials, maintain the concrete surface moisture as specified for the initial curing period.

Uniformly distribute absorbent materials across the entire concrete surface. Apply water in a manner that will not displace the curing materials or erode the concrete surface. Keep the concrete surfaces continuously wet. Do not allow concrete surfaces to dry or alternate with wetting and drying cycles. Cover the concrete, wooden forms and absorbent material with impermeable white reflective type sheeting.

Do not use absorbent materials containing harmful substances such as sugar or fertilizer, or materials that will discolor the concrete.

b.	Liquid Membrane-Forming Curing Compounds. Apply liquid membrane-forming compounds immediately after final finishing and as soon as the free water has disappeared, no water sheen is visible, and bleeding has essentially ceased. Apply two coats of liquid membrane-forming compound with the second coat at right angles to the first. Apply both coats of liquid membrane-forming compounds uniformly until the original color of the concrete is obscured. Follow the manufacturer's instructions when applying the liquid membrane-forming compound, except apply at a total coverage rate of at least 1 gallon per 150 square feet.

Do not apply the liquid membrane-forming compound to dry concrete surfaces. Moisten the concrete surface, without standing water, before applying the liquid membrane-forming compound. Protect the membrane from damage for the duration of the curing period. Provide adequate ventilation during the formation of the membrane. Re-apply the liquid membrane-forming compound if the membrane is cracked or damaged during the curing period.

c.	Forms-In-Place Curing. Formed concrete surfaces may be cured by retaining the forms in place for the entire curing period. Keep the forms moisture tight. Do not loosen forms. For wooden forms, keep the forms wet as required for wet curing. If gaps develop betweens forms or between the forms and concrete:

(1)	remove the forms and implement another curing method

(2)	keep the gaps continuously filled with water for the remainder of the curing period.

d.	Accelerated Curing. This method may be used only for precast concrete members that are manufactured in established plants.

During the curing period, keep the concrete in a saturated curing atmosphere with a relative humidity of at least 90 percent until the concrete achieves the required release strength.

The curing period may be accelerated by using saturated low-pressure steam, convection-heat, or radiant-heat in a suitable curing chamber to contain the live steam or heat. Use curing chambers that are reasonably free of leakage and allow adequate circulation. Provide at least 3 inches of clearance between the enclosure and forms.

If accelerated curing methods are used, embed at least one temperature-recording device in the concrete to verify that the concrete temperatures are within the specified limits. Install one temperature-recording device, accurate to ±5°F, near the member’s midpoint, 6 to 8 inches from the top or bottom, and along the member’s centerline. Monitor the concrete temperature with the temperature-recording device sensor arranged and calibrated to continuously record, date, and identify the concrete temperature throughout the heating cycle. Begin recording temperatures once concrete is placed in the forms. Stop recording temperatures after the heating cycle is complete and when the concrete temperature is within 20°F of the air temperature to which the concrete will be exposed. Make this temperature record available to the Engineer.

While waiting to begin the heating cycle, maintain the concrete temperature between 50°F and 90°F and maintain concrete surface moisture as specified for the initial curing period. Do not apply steam, convention-heat or radiant-heat prior to initial set unless to maintain the concrete temperature. Determine the time of initial set for each mix design according to AASHTO T 197.

Begin the heating cycle immediately after the concrete initially sets. Prevent hot air and steam from blowing directly onto the concrete or forms. Increase the concrete temperature at an average rate not exceeding 40°F per hour until the curing temperature is reached. Limit curing temperature within the concrete to 175°F maximum. Decrease the concrete temperature not more than 40°F per hour until reaching a temperature 20°F above the temperature of the air to which the concrete will be exposed.

Apply radiant heat by pipes circulating steam, hot oil, or hot water, or by electric heating elements.

Transfer the stressing force to the concrete immediately after the heating cycle has been discontinued, while the concrete is still moist, and before the temperature of the concrete drops below 100°F.

3.	Curing Temperature. To achieve adequate curing, maintain the concrete temperature at or above 50°F during the curing period. If the concrete temperature falls below 50°F during the curing period, no curing time is awarded for that day.

4.	Curing Time. Continue curing operations uninterrupted until the required concrete properties, strength, and durability have developed or until there is reasonable assurance that these properties will be achieved after the curing operations have been terminated.

Curing operations may be terminated after all of the following are satisfied:

a.	The concrete has cured for at least 7 days.

b.	The concrete has cured for at least 10 days when pozzolans in excess of 10 percent by weight of the Portland cement are used in the mix.

c.	The compressive strength, as determined by the Engineer from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure, reaches the following:

(1)	70 percent of the specified compressive strength if post curing conditions allow the concrete temperature to remain at or above 50°F.

(2)	100 percent of the specified compressive strength, if post curing conditions limits the concrete temperature to less than 50°F.

501-3.12 PROTECTION OF CONCRETE. Protect concrete at all times. Do not apply loads to the concrete until curing operations are completed and the concrete has attained sufficient strength to safely carry the applied loads without damage. Unless otherwise noted, sufficient strength is attained after the concrete has a compressive strength of at least 80 percent of the specified compressive strength, as determined by the Engineer from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure.

Release forms and falsework according to Section 512.

During cold weather, protect the concrete according to Subsection 501-3.05

During the curing period, protect concrete from damaging mechanical disturbances including load stresses, shock, and harmful vibration. Protect concrete surfaces from damage by construction traffic, equipment, materials, rain or running water, and other adverse weather conditions.

The Engineer may reject any structure or portion of a structure containing concrete that is cracked, spalled, or otherwise damaged. Repair cracks according to Subsection 501-3.27.

Do not backfill against concrete structures until the end of the curing period and until the concrete has attained a compressive strength of at least 80 percent of the specified compressive strength, as determined by the Engineer from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure.

Obtain written authorization from the Engineer before driving construction related vehicles or equipment, or storing materials on the bridge. Keep the bridge closed to traffic until all concrete has been accepted. Obtain written authorization from the Engineer before opening the bridge to traffic.

501-3.13 TOLERANCES. Produce concrete elements conforming to the following tolerances:

1.	Length: ±1/4 inch per 25 feet of member length, but not to exceed ±1 inch.

2.	Cross-sectional Dimensions:

a.	For dimensions 6 inches or less: -1/8 inch to +1/4 inch.

b.	For dimensions over 6 inches but not over 18 inches: -1/8 inch to +3/8 inch.

c.	For dimensions over 18 inches: -1/4 inch to +3/8 inch.

3.	Distortion of Cross-section: Limit the slope with respect to the specified surface, plane, or line to a rate less than ±1/16 inch per foot, but not to exceed ±1/4 inch measured perpendicular from a line coincident with the specified surface.

4.	Warping (Twist): Limit the rate of deviation with respect to the specified surface, plane, or line to a rate less than ±1/16 inch per foot, but not to exceed ±1/2 inch, measured perpendicular from a line along the length of the member and coincident with the specified surface.

5.	Surface Irregularities (deviation from a 10-foot straight edge):

a.	For surfaces that will receive a topping or are buried: ±1/4 inch.

b.	For surfaces that will not receive a topping or are visible in the completed work: ±1/8 inch.

6.	Camber: Do not vary from approved camber more than ±1/8 inch per 10 feet of length, but not to exceed 1 inch. In addition, the camber of any girder may not differ from that of any other girder by more than 1 inch.

7.	Lateral Sweep (deviation from a straight line parallel to centerline of member):

a.	For member length 40 feet or less: ±1/4 inch.

b.	For member length over 40 feet but not over 60 feet: ±3/8 inch.

c.	For member length over 60 feet: ±1/2 inch.

8.	Deck Width (measured out-to-out): ±1/4 inch per 25 feet of width, but not to exceed ±3/4 inch, except not more than ±1/2 inch where more precision is dictated by substructure details such as anchor bolts, parallel wing walls, etc.

9.	Position and Alignment:

a.	Bottom of footing elevation: ±5/8 inch.

b.	Profile grade: ±1 inch.

c.	Lateral position: ±1 inch.

d.	Skew: ±0.05 degrees.

10.	Bearing Seats:

a.	Elevation: ±1/8 inch

b.	Variation between bearing seats: Do not vary from a straight line coincident with the centerline of bearings and parallel to the surface of the bottom flanges more than 1/8 inch.

c.	Grade and cross slope: ±1/16 inch per foot.

11.	Openings:

a.	Size of opening: ±1/4 inch.

b.	Location of centerline of opening: ±1/2 inch.

12.	Embedded Items:

a.	Bolts: ±1/4 inch.

b.	Utility hangers: ±1/2 inch.

c.	Weld Plates: ±1/2 inch measured along the length of the member, ±1/8 inch measured perpendicular to the length of the member.

d.	Inserts: ±1 inch.

e.	Rail post anchor plates: ±1/4 inch.

f.	Expansion joints: ±1/8 inch.

g.	Electrical conduits: ±1/2 inch.

h.	Deck drains: ±1/2 inch.

i.	Other embedded items: ±1/2 inch.

The Engineer may reject any structure or portion of a structure containing concrete that was not constructed within the required tolerances.

501-3.14 CONSTRUCTION JOINTS. Locate construction joints where specified in the Contract documents or as permitted. Make construction joints horizontal, vertical, or perpendicular to the longitudinal reinforcement. Obtain approval before adding, deleting, or relocating construction joints specified in the Contract documents. Make requests for such changes in writing, accompanied by a drawing that depicts the joint. The Engineer will evaluate the proposed construction joint to determine if the joint is of such extent or character as to affect the strength or durability of the concrete.

At horizontal construction joints, place gage strips 1-1/2 inches thick inside the forms along exposed faces to give the joints straight lines. Do not use wire mesh forming material. When permitted, place the joints where they will not be exposed to view in the finished structure. Where vertical construction joints are necessary, extend reinforcing bars across the joint.

If the Contract documents require a roughened surface on the joint, create grooves at right angles to the length of the member. Make grooves that are 1/2 inch to 1 inch wide, 1/4 inch to 1/2 inch deep, and spaced equally at twice the width of the groove.

If the Contract documents do not require a roughened surface, include shear keys at the joint. Make shear keys of formed depressions with slight beveling to ensure ready removal. Do not use raised shear keys. Make shear keys for the tops of beams, at the tops and bottoms of boxed girder webs, in diaphragms, and in crossbeams that are 1-1/2 inches deep, 8 inches long, 4 inches less than the width of the joint, and spaced at 16 inches. In other locations, make shear keys at least 1-1/2 inches deep and 1/3 of the joint width.

Clean all construction joints of surface laitance and other foreign materials before fresh concrete is placed against the surface of the joint. Flush all construction joints with water and allow the joint to dry to a surface-dry condition immediately prior to placing concrete.

501-3.15 EXPANSION JOINTS. Locate and form expansion joints as shown on the Plans.

1.	Open Joints. Place open joints where shown on the Plans. Remove forms without chipping or breaking the corners of the concrete. Do not extend reinforcement across an open joint, unless shown on the Plans.

2.	Filled Joints. Construct expansion joints with expanded polyethylene joint filler as thick as the width of the joint.

Cut the joint filler to the same shape and size as the adjoining surfaces. Fix the joint filler against the concrete surfaces in place to keep the joint filler from displacing when concrete is placed.

Immediately after removing the forms, inspect the expansion joints. Remove concrete or mortar that has sealed across the joint.

Use the type of joint sealant shown on the Plans meeting the requirements of Subsection 501-2.01. Remove foreign matter, paint, curing compound, oils, greases, dirt, free water, and laitance from the faces of joints to be sealed.

3.	Compression Seals. Shape the joint as shown on the Plans. Install the seal according to the manufacturer’s instructions.

Install the seal in one piece for the full width of the roadway joint. Install the seal immediately after the curing period of the concrete.

4.	Strip Seals. Use expansion joint strip seals in one piece for the length of the joint. Shape the steel shapes to conform to the section of the concrete. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

5.	Steel Joints. At the shop, shape the plates, angles, or other structural shapes to conform to the section of the concrete. Fabricate and paint structural shapes to meet the Specifications covering those items. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint. Meet the joint opening dimension shown on the Plans.

6.	Modular Seals. Shape the joint as shown on the Plans. Use expansion joint modular seals in one piece for the length of the joint. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

501-3.16 FORMS AND FALSEWORK.

1.	General. Use forms and falsework designed and constructed according to Section 512.

2.	Concrete Decks. Measure girder camber at the tenth points along the span after the girders are erected but before installing falsework, formwork, deck reinforcing or other loading. Submit the girder camber measurements to the Engineer. Adjust the falsework elevations to accommodate the measured girder camber. Submit the required haunch dimensions to the Engineer for review and approval. Do not install falsework, formwork, reinforcing steel or other loads without the Engineer’s approval. Install devices, such as telltales, to enable the Engineer to readily measure settlement and deflection.

a.	Forms. Provide concrete deck forms meeting the following requirements:

(1)	Maintain the deck thickness despite irregularities in and between the girders.

(2)	Accommodate camber variation along the length and between the girders.

b.	Haunches. Limit haunch dimensions to meet the following requirements:

(1)	1/2 inch maximum embedment of the top flange into the deck measured at the edge of the flange.

(2)	2-1/2 inch minimum clearance between the top of deck and shear stud.

(3)	2 inch minimum penetration of shear stud into the deck.

(4)	4 inch maximum haunch measured at the centerline of the girder.

Do not use permanent forms including metal, wood, or precast concrete for concrete deck construction, unless otherwise noted.

Threaded inserts may be cast into the exterior edge of deck to accommodate concrete curb forms. Place grout, colored and textured to match deck concrete, in recess after the curb forms are removed.

501-3.17 PRECAST CONCRETE MEMBERS. In addition to the requirements listed herein, conform to Section 502 when fabricating prestressed concrete members.

1.	Shop Drawings. Provide shop drawings for precast concrete members. Include in the drawings, details not provided in the Plans for the construction and erection of the members. Cast members only after shop drawings are approved. Use precast methods for cast-in-place elements when approved. Submit shop drawings, showing construction joint details and any other information required. Construct and place precast concrete members according to the details specified.

2.	Manufacture. Monitor the quality of the concrete when casting in an established yard. Perform tests for materials and strength with appropriate AASHTO or ASTM methods.

Prestress concrete according to Section 502. Fabricate and install reinforcing steel according to Section 503.

Unless otherwise noted, use Class P concrete for precast concrete members meeting the specified compressive strength noted on the Plans.

Cast members on rigid beds or pallets. Cast bearing surfaces so that they will join properly with other elements of the structure.

Remove forms only after the concrete has sufficient strength to prevent distorting the concrete surface and without interrupting the curing.

3.	Curing. Cure precast concrete members by the steam or radiant heat method, or by the water method.

4.	Storage and Handling. Handle and move precast concrete members without causing damage to the member. Lift members from casting beds according to Subsection 501-3.12. Store and transport precast concrete members in an upright position with the directions of the support reactions on the member during storage or transport as if in the final position. Locate support points during transport and storage within 30 inches of their final position, or as shown on approved shop drawings. Ship only after the member has cured at least 7 days and has a compressive strength not less than the specified compressive strength. Replace all damaged precast units.

5.	Erection. Maintain member stability to the satisfaction of the Engineer at all times. Provide all necessary hardware to ensure that member stability is maintained at all times. Limit tension stresses in members due to transportation, lifting, and erection operations to less than 500 psi. Do not crack or otherwise damage precast concrete members. The Engineer may reject cracked or damaged precast concrete members.

Secure the member to the structure, and provide temporary braces necessary to resist wind or other loads immediately after erecting each precast concrete member. Install cast-in-place end and intermediate diaphragms within 2 weeks after setting precast concrete members on their bearings.

If cast-in-place end and intermediate diaphragms cannot be placed within the prescribed time limit, ensure the members are adequately braced to resist movement and rotation. Submit for approval a bracing plan including complete details and substantiating calculations, signed and sealed by a Professional Engineer proficient in structural design and registered in the State of Alaska, describing the method, materials, and equipment proposed for use in bracing the precast concrete members.

Erect and place precast deck panels so that the mating surfaces do not allow excessive grout leakage. Dry-pack or seal with an acceptable caulking compound all joints where excessive grout leakage may occur. Provide end panels on skewed structures to fit the skew.

When the Plans require filling keyways between adjacent concrete members with grout, place grout meeting Subsection 701-2.03 and according to the manufacturer's written instructions. Do not place loads on the grouted members until the grout has reached 5000 psi.

Tightly pack and rod the grout in the keys and spaces. Keep the grout surface smooth and neat. Ensure that the grout surface meets the girder edges throughout their lengths and matches the surface elevation of the girders with a tolerance of ±1/8 inch. Patching and grinding may be required.

Set interchangeable girders so that the initial difference between the top surfaces of the edges of adjacent girders is no more than 1/2 inch at midspan and no more than 1/4 inch at the bearings.

Set and crib deck bulb tee girders within a span or otherwise brace them securely before making design shear connections or diaphragm connections. Before allowing connections to be made, the Engineer may require additional adjustments to the girder positioning or the use of forcing devices as described below to meet erection tolerances.

Provide and use forcing devices as shown in the Plans or as recommended by the girder manufacturer. Use devices that will maintain the top edges of adjacent girders at the same elevation while casting or welding diaphragms, welding shear connector plates, and while placing and curing grout in the shear keys.

Make field welds according to Section 503 and Section 504.

6	Method and Equipment. Submit an erection plan to the Engineer for approval.  Submit the erection plan not less than 30 days prior to erecting the structural steel.  Do not erect structural steel without the written approval of the Engineer. Include the following:

a.	Drawings indicating geometry, member sizes, material properties, foundations capacities, design assumptions, and other relevant information required to erect the precast member.

b.	Support and lifting reactions for each stage of the erection procedure.

c.	Equipment type, size, capacity, position, work radius and other relevant information.

d.	Schedule, duration of each portion of work and other timing considerations.

Submit changes needed to accommodate the erection plan to the Engineer for approval.  Do not deviate from the approved erection plan without the written permission of the Engineer.

501-3.18 PLACING ANCHOR BOLTS. Secure anchor bolt assemblies where shown on the Plans. Check the positions and make adjustments before the concrete or grout has been placed.

When installing anchor bolts in wet concrete, secure anchor bolts before placing concrete in the forms. Do not disturb anchor bolts after concrete has been placed.

When installing anchor bolts in pipe sleeves, pre-cast holes, or drilled holes, completely fill the cavity with grout meeting Subsection 701-2.03. Fill the cavity when placing the bearing assemblies. Do not allow water to freeze in the cavity.

501-3.19 BEARINGS. Set the bearing plates, sole plates and elastomeric bearing pads as shown on the Plans in the exact position with full and even bearing on properly finished bearing seats.

Finish bridge seat bearing areas or grind them to elevation and parallel to the roadway grade and parallel to the roadway cross slope or crown, unless otherwise shown on the Plans.

When shown on the plans, place grout that meets Subsection 701-2.03 under masonry plates. Mix and place grout according to the manufacturer’s written recommendations. Clean concrete areas that will contact the grout. Remove loose or foreign matter that would prevent the bond between the mortar and the concrete surfaces.

Tightly pack the grout under the masonry plates to provide full bearing. After placing, cover exposed surfaces of grout pads with a heavy thickness of burlap saturated with water for 3 days. Do not place a load on the grout until the grout has attained a compressive strength of 5000 psi as determined by field specimen.

Locate sole plates to correspond with the temperature during erection. Anchor bearing securely. Adjust the nuts on anchor bolts at the expansion ends of spans to permit the span to move freely. Burr threads sufficiently to prevent removal of nuts.

Apply epoxy adhesive to the bottom surface of the elastomeric bearing pads before placing them. Do not move the pad until the epoxy has cured and full adhesion is achieved. Do not apply epoxy adhesive to elastomeric bearings used in PTFE bearing assemblies.

501-3.20 UTILIDUCTS, PIPES, CONDUITS, DUCTS, AND UTILITY HOLES. When utiliducts, pipes, conduits, and ducts will be encased in concrete, install them in the forms before placing the concrete. Provide adequate rigid support so the pipe will not displace during concrete placement.

Install utiliducts and utility holes parallel to the roadway centerline. Prevent bond between the utiliducts and concrete by tightly wrapping the utiliducts with at least two layers of asphalt felt.

501-3.21 DRAINGAGE HOLES AND WEEP HOLES. Construct drainage and weep holes as shown on the Plans.

Form weep holes through concrete. If using wooden forms, remove them after the concrete is cured.

Provide weep holes in retaining walls and abutment walls where the height of the wall is over 5 feet measured from the top of the footing. Form weep holes 4 inches in diameter and space them no more than 15 feet apart. Place the outlet end of weep holes just above the finish ground line at the face of the wall, or as directed.

Mount hardware cloth in the forms prior to placing concrete in such a manner that the wire is firmly bonded to the concrete or fasten to the exterior of the concrete surface as approved by the Engineer.

501-3.22 GROUTING PERMANENT METAL CASING. For drilled shaft foundation casings installed in oversized holes or where gaps exist between the shaft excavation and the casing, grout the zone between the casing and the soil with DS Grout. Grout the casing the full depth of the shaft. Use at least six grout placement tubes placed uniformly around the perimeter the full length of the casing. Grout the casing in one continuous operation. Withdraw the grout tubes vertically during grout placement operations. Provide at least two water relief/release pipes on opposite sides of the casing. Withdraw the water relief/release pipes vertically during the grout placement operations.

Submit the grout placement procedure to the Engineer for approval.

501-3.23 DRILLING AND BONDING DOWELS. Drilling of concrete consists of drilling various diameter holes through reinforced or prestressed concrete members, where shown on the Plans or as authorized by the Engineer. Drill holes by methods that do not shatter or damage the concrete adjacent to the holes. Do not damage or otherwise contact reinforcing steel or prestressing steel strand when drilling through reinforced concrete members, unless approved by the Engineer.

Holes in which reinforcing steel or prestressing steel strand is encountered during drilling before the specified depth is attained will be rejected. Drill a new hole, which does not strike reinforcing steel or prestressing steel strand, adjacent to the rejected hole to the specified depth. With the approval of the Engineer, all holes including rejected holes may be cored through reinforcing steel to the correct depth. Fill all rejected holes with epoxy grout.

Drill holes to the diameters and depths recommended by the manufacturer to develop the ultimate strength of the steel dowel but to a depth not less than that shown on the Plans.

Clean and dry the holes according to the manufacturer’s written recommendations before placing the bonding material and the steel dowels. After bonding, support all dowels as necessary to prevent movement during curing. Completely fill drilled holes with epoxy using a method that will not trap air or create voids. Do not disturb the dowels until the epoxy has cured the minimum time specified by the manufacturer. Dowels that are improperly bonded, as determined by the Engineer, will be rejected. Drill new holes and place new securely bonded dowels at no expense to the State.

501-3.24 WATER STOPS. Furnish water stops in continuous, full-length segments without field splices. Do not field splice water stops. Manufacture’s shop splices shall be fully vulcanized.

Use spacers, supporting wires, or other approved devices to secure the water stop in the position shown on the plans.

Remove and replace water stops that are out of position or shape at no expense to the Department.

501-3.25 CHIPPING AND REMOVING CONCRETE. Where portions of a bridge are to be chipped or removed, perform the chipping and removal operations without damage to any portion of the structure that is to remain in place.

Before removing concrete, make a saw cut approximately 1 inch deep to a true line along the limits of removal on all faces of the element that will be visible in the completed work.

Use water meeting the requirements of Subsection 501-2.01 for removal operations.

501-3.26 CRACK REPAIR. The Engineer will evaluate concrete that has cracked at any time during execution of the Contract for structural adequacy and durability.

For concrete decks and approach slabs, if the surface crack intensity immediately after termination of concrete curing operations, before prestressing (if applicable), and before the release of falsework is such that in any 500 square foot portion of deck or approach slab there are cracks, whose width exceeds 0.020 inches at any location and combined lengths total more than 16 feet, treat the deck by performing Low-Viscosity Resin Crack Repair.

For all other concrete, if the crack is less than 0.013 inches wide, measured at the widest point of the crack, the crack will be considered acceptable with no additional evaluation or repairs required. Cracks greater than 0.060 inches wide, measured at the widest point of the crack, will not be evaluated and will not be considered acceptable. For all other cracks, repair the entire crack by performing Low-Pressure Crack Repair. If the crack is found to be unacceptable, then remove and replace the material.

Perform crack repairs and replace unacceptable concrete at no cost to the Department. No contract time extension will be given for repairing, removing, and replacing unacceptable material.

1.	Low-Pressure Crack Repair. Repair cracked concrete according to the following requirements:

a.	Crack Repair Plan. Submit a Crack Repair Plan to the Engineer for approval. Include the following in the Crack Repair Plan:

(1)	Experience of the injection equipment technicians

(2)	Evaluation of the crack width and the recommended epoxy viscosity that will allow the epoxy to achieve and maintain the penetration requirements

(3)	Material information including manufacturer's product data sheets

(4)	Equipment

(5)	Crack preparation and injection procedures

(6)	Cleanup procedures

b.	Experience. Provide epoxy injection technicians who have a minimum of 2 years of continuous relevant experience in performing similar repairs using the methods and materials of the selected system.

c.	Materials. Seal the crack with an epoxy adhesive that has the strength and adhesion to contain the injected epoxy in the crack during the injection process and while the injected epoxy cures, and does not leave a residue or damage the surfaces when removed. Inject the crack with an epoxy adhesive that will fill at least 90 percent of the depth of the crack.

d.	Equipment. Use positive displacement plural component pumps, specifically designed to meter, mix, and inject low viscosity materials.

e.	Crack Preparation. Remove contaminates such as water, oil, grease, dirt, fine particles of concrete, and all other materials that reduce the effectiveness of repairs from the crack. Allow adequate time for drying. If cleaning solutions are used, perform a trail test to determine the practical limitations and effectiveness of the contaminate removal procedure.

f.	Entry and Venting Ports. Install entry/venting ports spaced equal to the thickness of the concrete member along one face of the crack. Acceptable types of entry/venting ports are fittings inserted into drilled holes, bonded flush fittings, and interruptions in seal using special gasket devices that cover the unsealed portion of the crack and allow injection of epoxy directly into the crack without leaking.

g.	Surface Preparation. Prepare the surface according to the manufacturers written instructions. Seal the surface of the crack to prevent the epoxy from escaping. Apply an epoxy sealing material to the surface of the crack and allow the epoxy to harden.

h.	Epoxy. Mix the epoxy to the volume ratio prescribed by the manufacturer within a tolerance of ±5 percent by volume.

i.	Epoxy Injection. Inject the epoxy according to the epoxy manufacturer’s instructions. When injecting epoxy, limit injection pressure to prevent propagation of the crack, cause additional damage, or injection pressure in excess of 50 psi, whichever is least.

Start injecting epoxy into the entry port at the lowest end of the crack, unless otherwise approved by the Engineer. Continue injecting epoxy until the epoxy level reaches the succeeding port. When epoxy reaches the succeeding port, close the entry port and move to the succeeding port. Repeat the process until all ports have been initially filled. Ten minutes after initial injection has been completed at the final port, re-inject all ports until no additional epoxy can be injected and the pressure can be maintained.

j.	Finishing and Cleanup. After the injected epoxy has cured, remove all ports and surface seal by means that do not damage the injected epoxy. Do not heat the surface seal to aid in the removal.

Clean and remove all spills and leaks of injection adhesive and stains caused by the epoxy adhesives.

2.	Low-Viscosity Resin Crack Repair. Treat the area of concrete having a minimum width extending the entire width of deck or slab inside the concrete barriers and a minimum length extending at least 5 feet beyond the furthest single continuous crack outside the 500 square foot portion, measured from where that crack exceeds 0.020 inches in width, as determined by the Engineer. If grinding is required, treat the concrete before grinding.

Before treatment with low-viscosity resin, ensure the concrete surface is clean, sound and free of surface moisture. Remove dust, laitance, greases, oils, curing compounds, waxes, impregnations, foreign particles, coatings and disintegrated materials from the concrete surface by mechanical means such as abrasive blasting. Remove all loose material from cracks by vacuum cleaning or blowing with high-pressure air, 150 psi minimum. Ensure the concrete is dry when abrasive cleaning is performed. If the concrete surface becomes contaminated at any time before placing the resin, repeat the cleaning process.

Where abrasive blasting is being performed, remove the residue including dust immediately after contact between the abrasive and the surface being treated by a vacuum attachment operating concurrently with the abrasive blasting operation.

Apply low-viscosity resin only to the specified area. Protect barriers, railing, joints, and drainage facilities to prevent contamination by the treatment material. Repair contaminated items.

Completely cover the deck surface with resin so the resin penetrates and fills all cracks. Ensure the relative humidity is less than 80 percent, the prepared area is dry, and the surface temperature is at least 50°F and not more than 90°F when the resin is applied. Apply the resin and distribute excess material by squeegees or brooms within the manufacturer's listed pot life. For textured surfaces, including grooved surfaces, remove excess material from the texture indentations.

For concrete decks and approach slabs that do not receive a waterproofing membrane, apply aggregate for abrasive finish within 20 minutes of resin application and before any setting occurs. Broadcast the aggregate for abrasive finish evenly over the entire treated area at a rate of approximately 2 pounds per square yard.

501-3.27 CLEANUP. Upon completion of the structure and before final acceptance, leave the structure and entire site in a clean and orderly condition. Remove all concrete waste from the site. Remove all concrete splatter, paint marks, laitance, rust staining, chamfer strips, and all other material that does not provide a uniform texture and color to the concrete surface. Remove temporary buildings, equipment, unused materials, debris, forms, and falsework. Remove falsework piling at least 2 feet below the finished ground line.

501-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Cubic Yard. The lesser of the actual volume or neat line volume of each class of concrete accepted in place in the finished structure.

Class DS Concrete. The sum of the lengths of drilled shafts complete in place, measured along the centerline of the drilled shaft from the bottom to the top.

Precast Concrete Members. Measured per unit, complete in place.

Bridge Expansion Joint. The sum of the lengths of joints complete in place, measured along the centerline of the joint.

Drill and Bond Dowels. Measured per dowel, complete in place.

501-5.01 BASIS OF PAYMENT.

All material that does not appear in the Bid Schedule and is contained within, embedded or attached to concrete elements including conduits, drains, wire mesh, threaded inserts, anchors, utility hangers, utiliducts and other hardware is subsidiary. DS Grout used for grouting permanent metal casing is subsidiary.

Concrete. Thirty percent of the unit bid price for Items 501(1) through 501(7) will be withheld until satisfactory completion of concrete curing, finishing, and acceptance of compressive strength.

Precast Concrete Member. Payment for Precast Concrete Member includes all materials and work for the following items: concrete, reinforcing steel contained in the member (uncoated and/or epoxy coated), prestressing steel, plates, nuts, all other inserts contained within the concrete member, bolts, studs, anchor bars, blockouts, elastomeric bearing pads, grout, drains, and other miscellaneous steel embedded in or attached to the precast concrete member.

Bridge Expansion Joint. Payment for Bridge Expansion Joint includes all materials and work for steel shapes, glands, and all other materials necessary for installing elastomeric compression seals, strip seals, steel joint, and modular seals. All expanded polyethylene, joint filler, and silicone joint sealant material are subsidiary.

Drill and Bond Dowels. Payment for Drill and Bond Dowels includes all materials and work for installing dowels.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

501(1) 	Class A Concrete	Lump Sum

501(2)	Class A-A Concrete	Lump Sum

501(3)	Class W Concrete	Lump Sum

501(4)	Class A Concrete	Cubic Yard

501(5)	Class S Concrete	Cubic Yard

501(6)	Class W Concrete	Cubic Yard

501(7)	Class DS Concrete (identification)	Linear Foot

501(8)	Precast Concrete Member (134’ Decked Bulb-Tee)	Each

501(9)	Bridge Expansion Joint (identification)	Linear Foot

501(10)	Drill and Bond Dowels	Each

Replace Section 502 with the following:

Section 502
Prestressing Concrete

502-1.01 DESCRIPTION. Prestress precast or cast-in-place concrete by furnishing, placing, tensioning, and bonding prestressing steel by using either pretensioning or post-tensioning methods or a combination of the two methods according to the Contract documents.

For pretensioning, this work also includes furnishing and installing all materials and equipment necessary to prestress concrete as designated in the Contract documents.

For post-tensioning, this work includes furnishing and installing all post-tensioning systems and all other pertinent items necessary for the particular prestressing system used, including but not limited to ducts, anchorage assemblies, supplementary reinforcement, and grout used for pressure grouting ducts.

502-1.02 DEFINITIONS.

ANCHORAGE. An assembly of various hardware components that secure a tendon at its ends after it has been stressed imparting the tendon force into the concrete.

ANTICIPATED SET. The set that was assumed to occur in the design calculation of the post-tensioning forces immediately after load transfer.

BEARING PLATE. Hardware that transfers the tendon force directly into concrete.

BLEED. The autogenous flow of mixing water within or its emergence from newly placed grout caused by the settlement of the solid materials within the mass and filtering action of strands.

DUCT. Material forming a conduit to accommodate prestressing steel installation and provide an annular space for the grout that protects the prestressing steel.

FLUIDITY. A measure of time, expressed in seconds, necessary for a stated quantity of grout to pass through the orifice of a flow cone.

GROUT. A mixture of cementitious materials and water with or without mineral additives or admixtures proportioned to produce a pumpable consistency without segregation of the constituents when injected into the duct to fill the space around the prestressing steel.

GROUT CAP. A device that contains the grout and forms a protective cover sealing the post-tensioning steel at the anchorage.

POST-TENSIONING. A method of prestressing in which the tendons are tensioned after the concrete has reached a specified strength.

PRESTRESSING STEEL. The steel element of a post-tensioning tendon, which is elongated and anchored to provide the necessary permanent prestressing force.

POST-TENSIONING SCHEME OR LAYOUT. The pattern, size and locations of post-tensioning tendons.

POST-TENSIONING SYSTEM. An assembly of proprietary post-tensioning hardware, including but not limited to anchorage assembly, local zone reinforcement, wedge plate, wedges, bearing plate, prestressing steel, duct, duct connections, vents and grout cap, used to construct a tendon of a particular size and type.

SET (Also Anchor Set or Wedge Set). The total movement of a point on the strand outside the anchoring wedges during load transfer from the jack to the permanent anchorages. Set movement is the sum of slippage of the wedges with respect to the anchorage head and the elastic deformation of the anchor components.

STRAND. An assembly of several high-strength steel wires wound together. Strands usually have six outer wires helically wound around a single straight wire of a similar diameter.

STRAND COUPLER. An assembly by which the prestressing force may be transmitted from one partial length prestressing tendon to another. (Strand couplers are not permitted.)

TENDON. A single or group of prestressing steel elements and their anchorage assemblies that imparts prestress to a structural member. Also, included are ducts, grouting attachments, grout and corrosion protection filler materials or coatings.

TENDON SIZE. The number of individual strands of a certain strand diameter.

THIXOTROPIC. The material property exhibited by certain grouts that enable material to stiffen, achieve a higher viscosity, in a short time while at rest, but to become liquid, acquire a lower viscosity, when mechanically agitated.

VENT. Tubing or pipe used for injection of grout into the duct and to allow escape of air, water, grout and bleed water from the duct.

WEDGE. A conically shaped device that anchors the strand in the wedge plate.

WEDGE PLATE. The hardware that holds the wedges of a multi-strand tendon and transfers the tendon force to the anchorage assembly.

502-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501

Water	Subsection 712-2.01

Reinforcing steel 	Subsection 709-2.01

Epoxy-Coated Reinforcing Steel	Subsection 709-2.01

Prestressing Steel and Fittings	Section 721

Post-tension Grout	Subsection 701-2.07

Zinc-Rich Paint	Subsection 708-2.01.1

Epoxy Bonding Agents	AASHTO M 235, Type V

CONSTRUCTION REQUIREMENTS

502-3.01 PRETENSIONING METHODS. Select a pretensioning method that provides the magnitude and distribution of prestressing force specified in the Contract documents, subject to the requirements in this Section and approval by the Engineer.

1.	Shop Drawings. Before casting members to be prestressed, submit for approval shop drawings including complete details and substantiating calculations of the method, materials, and equipment proposed for use in the prestressing operations, any additions or rearrangement of reinforcing steel, and any revision in concrete dimensions.

Include an outline of the method and sequence of stressing, complete specifications and details of the prestressing steel and anchoring devices to be used, anchoring stresses, strand release sequence, and other data pertaining to the prestressing operations, including the proposed arrangement of the prestressing units in the members.

Compute the anticipated camber at the time of prestressing force transfer and at other significant times. Show the values on the shop drawings as a time/deflection curve, subject to approval.

Include on shop drawings embedded items such as reinforcing steel, lifting devices, coil anchors, anchor bolts, drainage systems, utility conduits and other such items. Ensure there will be no conflict between the planned positions of any embedded items and that concrete cover will be adequate.

2.	Quality Control Plan. Submit for approval a quality control plan that verifies that all materials and workmanship incorporated into the prestressed concrete members conform to the requirements.

Perform all pretensioning operations under the direct supervision and control of a qualified pretensioning technician. Provide a pretensioning technician, skilled in the prestressing method, to aid and instruct in using the prestressing equipment and in installing the materials to obtain required results.

3.	Protection of Prestressing Steel. Protect prestressing steel and anchor assemblies against physical damage and corrosion at all times. Keep prestressing steel and anchor assemblies clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials. The Engineer will reject prestressing steel that has at any time sustained physical damage. The Engineer will reject prestressing steel that has developed visible rust pitting or other results of corrosion, other than rust stain.

Protect prestressing steel and anchorage assemblies against physical damage and corrosion during shipping and storage by packaging the prestressing steel and anchorage assemblies in containers or shipping forms. Place a corrosion inhibitor in the package or form, incorporate a corrosion inhibitor carrier-type packaging material, or apply a corrosion inhibitor directly to the steel. Do not use corrosion inhibitors that have deleterious effect on the steel or concrete or bond strength of steel to concrete. Immediately replace packaging or forms damaged from any cause or restore packaging to original condition.

Clearly mark the shipping package or form with a statement that the package contains high-strength prestressing steel, and the type of corrosion inhibitor used, including the date packaged.

4.	Prestressing Equipment. Use hydraulic jacks to tension prestressing steel strands so that the force in the prestressing steel will not be less than the value specified in the Contract documents or as approved by the Engineer.

Equip each jack used to stress strands with either:

a.	two pressure gages

b.	one pressure gage and one load cell

In the event that any uncertainty exists regarding jack calibration, pressure gage usage, strand elongation or any other prestressing strand tensioning issue, provide and use a calibrated load cell when prestressing steel strands.

Permanently mark the jack body with the ram area. Ensure each pressure gage is fully functional, calibrated and has an accurately reading dial at least 6 inches in diameter.

Calibrate the jack and each gage, used to stress strands, as a unit within 6 months prior to use and after each repair. If used, provide a load cell calibrated within the past 12 months with an indicator that may be used to determine the prestressing force in the strand. The range of the load cell shall be such that the lower 10 percent of the manufacturer's rated capacity will not be used in determining the jacking stress.

Use the following calibration procedure; Perform three calibration test cycles with the cylinder extension of the jack in various positions (i.e. 2 inch, 4 inch, 8 inch stroke). At each pressure increment, average the forces from each test cycle to obtain an average force. Perform the calibration with the equipment setup in the same configuration that will be used at the job site. Use load cells calibrated within the past 12 months to calibrate stressing equipment.

For each jack and gauge unit used on the project, provide the Engineer with certified calibration curves prior to the start of the work and every 6 months thereafter, or as requested by the Engineer. If used, supply documentation denoting the load cell calibration date prior to the start of the work and every 6 months thereafter. Furnish certified calibration charts to the Engineer prior to stressing.

Recalibrate jacks requiring repair, such as replacing seals or changing the length of the hydraulic lines. No extra compensation will be allowed for the initial or subsequent calibrations.

5.	Placing Reinforcing Steel and Prestressing Steel. Place reinforcing steel according to Section 503, except as modified by this section.

Place prestressing steel in the position as designated in the Contract documents or on the approved shop drawings.

6.	Girder Inserts. Provide threaded inserts, coil anchors, or approved equal in the girder as indicated in the Contract documents.

With the written approval of the Engineer, additional inserts in the girder may be provided to accommodate diaphragm forms or other construction related requirements.

Provide holes in the girder web as indicated on the plans to accommodate reinforcing steel. Verify that the hole size is sufficient to accommodate reinforcement placement procedures.

7.	Pretensioning. Stress strands to the magnitude specified in the Contract documents by either single strand stressing or multiple strand stressing. Prior to applying full pretensioning, bring all strands to be stressed in a group (multiple strand stressing) to a uniform initial tension that is sufficient to eliminate all slack and equalize the stresses in the strands. Limit the strand stress in pretensioned members before seating (jacking stress) to 70 percent of the minimum breaking strength (0.70 fpu) of the prestressing steel.

Ensure that the tension load indicated by the gauge(s) is within 5 percent of the calculated tension load based on elongation measurements for each strand.

Use approved low-friction devices at all points of change in slope of strand trajectory when tensioning harped strands.

Tension harped strands from both ends of the bed if the prestressing force, as determined by elongation measurements, is less than 95 percent of that indicated by the jack gauges. Ensure the computed load from the sum of elongation at both ends is within 5 percent of that indicated by the jack gauges.

When splicing strands, locate all splices outside of the prestressed units. Account for additional elongation due to the splice when verifying the tension load based on elongation measurements.

Keep the temperature of the strands during tensioning and concrete placement within 25 °F of the concrete temperature during placement. During the interval between tensioning and concrete placement, do not let temperature changes alter the stress level in the strands more than 5 percent of the jacking stress, nor cause the stress in the strand to exceed 75 percent of the minimum breaking strength.

8.	Placing Concrete. Produce and place concrete according to the requirements of Section 501, except as modified by this section.

Before depositing concrete in the forms, obtain an inspection of the reinforcing steel, enclosures, anchorages, and prestressing steel by an authorized Department representative.

Consolidate the concrete using any combination of internal and external vibration that does not displace the reinforcing steel or other items embedded in the concrete.

9.	Release. Do not release prestressing strands or transfer prestressing forces to the member until concrete cylinder tests, manufactured according to AASHTO T 23 and tested according to AASHTO T 22 using the same concrete and maintained in the same curing conditions as the member, indicate that the concrete has attained the minimum initial compressive strength (release strength, f'ci) as indicated in the Contract documents.

Cut or release the elements in an order that minimizes the lateral eccentricity of the pre-stress. Cut all prestressing strands to a depth of at least 1 inch from the concrete surface. Fill the recess with cement mortar and finish flush to the concrete surface. Alternatively, cut all prestressing strands flush with the end of the member. Clean and paint the exposed ends of the strand and a 1-inch strip of adjoining concrete. Use a wire brush or abrasive blast cleaning to remove all dirt and residue not firmly bonded to the metal or concrete surfaces. Cover the surfaces with a thick application of zinc-rich paint.  Thoroughly mix the paint at the time of application and work it into any voids in the strands. Apply two applications to surfaces that are not covered by concrete or mortar.

502-3.02 POST-TENSIONING METHODS. Select a post-tensioning system that provides the magnitude and distribution of prestressing force specified in the Contract documents, subject to the requirements in this Section and approval by the Engineer.

For box girders, distribute the prestressing steel so that the force in each girder stem does not vary more than 5 percent from the required force per girder stem provided the required total force in the superstructure is obtained and the force is distributed symmetrically about the centerline of the typical section.

Do not exceed 75 percent of the minimum breaking strength of the prestressing steel for maximum temporary tensile stresses (jacking stresses) in prestressing steel. Do not exceed 70 percent of the minimum breaking strength of the prestressing steel at anchorages after anchor set.

Working force and working stress will be considered as the force and stress remaining in the prestressing steel after all losses (e.g., creep and shrinkage of concrete, elastic compression of concrete, creep of steel, losses in post-tensioned prestressing steel due to sequence of stressing, friction and take up of anchorages and all other losses peculiar to the method or system of prestressing) have taken place or have been accommodated. Calculate loss of prestress using industry recognized methods. The calculation and analysis methods are subject to approval by the Engineer.

1.	Shop Drawings and Calculations. Before casting members to be prestressed, submit shop drawings and supporting calculations of the prestressing system to the Engineer for approval no less than 45 days prior to the placement of bridge concrete. Submit four sets of the drawings for initial review. After the initial review has been reviewed and all comments from the Engineer have been received and implemented, submit drawings to the Engineer for approval and for use during construction according to Subsection 105-1.02.

Show complete details on the shop drawings of the prestressing system and all substantiating calculations of the method, materials, and equipment to be used in the prestressing operations, including any additions or rearrangement of reinforcing steel and any revision in concrete dimensions from that shown on the Plans. Outline in sufficient detail the method and sequence of stressing. Include complete specifications and details of the prestressing steel and anchoring assemblies, working stresses, anchoring stresses, type of ducts, initial prestress losses, final prestress losses and all other data pertaining to the prestressing operation. Show tendon geometry and locations complying with the plans and the limitations of the selected post-tensioning system. Show all vent locations, high point outlet inspection details, anchorage inspection details and grout caps, protection system materials and application limits. Include on the shop drawing the location of the anchorages, vents, and duct enclosures at 2-foot (maximum) intervals along the length of the girder.

Submit calculations for the anticipated camber at the time of prestressing force transfer and at other significant times. Show the values on the shop drawings as a time/deflection curve.

Submit calculations for the anticipated tendon elongation. Utilize the modulus of elasticity, based on nominal area, as furnished by the prestressing steel manufacturer for the lot of steel being tensioned. Show a typical tendon force diagram, after friction, wobble and anchor set losses, on the shop drawings based upon the expected friction curvature and wobble coefficients and values for the post-tensioning system used. Show the coefficients and values on the shop drawings.

Produce all shop drawings related to post-tensioning by a Professional Engineer specializing in post-tensioning concrete. Bear the signature and seal of the Professional Engineer who specializes in post-tensioning construction on all calculations, drawings, and procedures.

Include post-tensioning system certification(s) conforming to Subsection 721-2.04.

2.	Post-tensioning Technician. Perform all post-tensioning field operations under the direct supervision of a qualified post-tensioning technician. Provide a post-tensioning technician with at least five years of experience in construction of post-tensioned prestressed concrete structures. Provide a technician, skilled in the prestressing method, to aid and instruct in using the prestressing equipment and in installing the materials to obtain required results.

Perform all grouting under the direct supervision of a certified grouting technician. Provide a technician skilled in various aspects of grouting whom the American Segmental Bridge Institute certifies as an "ASBI Certified Grouting Technician".

The post-tensioning technician shall be present at all times during duct installation, tendon tensioning, and grouting operations and shall provide close observation and control of all post-tensioning and grouting operations, as necessary for compliance with the Contract. Submit the name of the post-tensioning technician and proof of certification to the Engineer no less than thirty days before the start of bridge concrete placement operations.

Do not substitute post-tensioning technicians without prior written approval from the Engineer. Provide documentation demonstrating that the proposed substitute individual meets the qualifications. All post-tensioning operations will be suspended if the Engineer has not approved the proposed substitution in writing. If work is delayed or suspended due to unapproved substitutions of special qualification personnel, no additional Contract time or additional compensation will be allowed according to Subsection 108-1.06.

3.	Protection of Prestressing Steel and Anchorages. Protect prestressing steel and anchor assemblies against physical damage and corrosion at all times from manufacture to grouting. Keep prestressing steel and anchor assemblies clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials. The Engineer will reject prestressing steel that has at any time sustained physical damage. The Engineer will reject prestressing steel that has developed visible rust pitting or other results of corrosion, other than rust stain.

Protect prestressing steel and anchorage assemblies against physical damage and corrosion during shipping and storage by packaging the prestressing steel and anchorage assemblies in containers or shipping forms. Place a corrosion inhibitor in the package or form, incorporate a corrosion inhibitor carrier-type packaging material, or apply a corrosion inhibitor directly to the steel. Do not use corrosion inhibitors that have deleterious effect on the steel or concrete or bond strength of steel to concrete. Immediately replace packaging or forms damaged from any cause or restore packaging to original condition.

Clearly mark the shipping package or form with a statement that the package contains high-strength prestressing steel, and the type of corrosion inhibitor used, including the date packaged.

If prestressing steel is installed in ducts but not tensioned and grouted within the seven days, perform Nondestructive Examination (NDE) by either videoscoping the entire length of the prestressing steel inside the ducts or visually inspecting the prestressing steel upon removing the prestressing steel from the duct for corrosion. Perform NDE inspection at least once every seven days until the prestressing steel is tensioned and grouted. Perform NDE inspection to the satisfaction of the Engineer. Provide a report of the tendon condition to the Engineer following each NDE inspection for each tendon installation.

If corrosion is not found on the prestressing steel upon completion of NDE inspection, the Engineer may require protecting prestressing steel corrosion by means of a corrosion inhibitor placed in the ducts. Do not place a corrosion inhibitor inside the duct if prestressing steel installation, tensioning, and grouting is performed within seven days. Do not use corrosion inhibitors that have deleterious effect on the steel or concrete or bond strength of steel to concrete. Submit for approval the name, manufacturer, and type of corrosion inhibitor to be used in the ducts at least seven days before installation of any prestressing steel. Prior to grouting, flush the corrosion inhibitor from the ducts using a solution of quick lime (calcium oxide) or slaked lime (calcium hydroxide) in the amount of 0.1 lbs/gal. Use compressed air that is oil free to blow out ducts and remove flush water.

Cover and protect the anchorages against corrosion at all times from installation of the prestressing steel to placement of the concrete pour-backs.

Do not weld on or near prestressing steel, ducts, anchorages, or other assemblages. Protect prestressing steel and hardware from weld spatter or other damage. Once the prestressing steel has been installed, do not make welds or grounds for welders on the forms, reinforcing steel, or adjacent steel members.

4.	Prestressing Equipment. Use hydraulic jacks to tension prestressing steel tendons so that the force in the prestressing steel will not be less than the value specified in the Contract documents or as approved by the Engineer. Do not use monostrand jacks to stress multi-strand tendons.

Equip each jack used to stress tendons with either:

a.	two pressure gages

b.	one pressure gage and one load cell

In the event that any uncertainty exists regarding jack calibration, pressure gage usage, strand elongation or any other prestressing strand tensioning issue, provide and use a calibrated load cell when prestressing steel tendons.

Permanently mark the jack body with the ram area. Ensure each pressure gage is fully functional, calibrated and has an accurately reading dial at least 6 inches in diameter.

Calibrate the jack and each gage used to stress tendons as a unit within 6 months prior to use and after each repair. If used, provide a load cell calibrated with in the past 12 months with an indicator that may be used to determine the prestressing force in the tendon. The range of the load cell shall be such that the lower 10 percent of the manufacturer's rated capacity will not be used in determining the jacking stress.

Use the following calibration procedure; Perform three calibration test cycles with the cylinder extension of the jack in various positions (i.e. 2 inch, 4 inch, 8 inch stroke). At each pressure increment, average the forces from each test cycle to obtain an average force. Perform the calibration with the equipment setup in the same configuration that will be used at the job site. Use load cells calibrated within the past 12 months to calibrate stressing equipment.

For each jack and gauge unit used on the project, provide the Engineer with certified calibration curves prior to the start of the work and every 6 months thereafter, or as requested by the Engineer. If used, supply documentation denoting the load cell calibration date prior to the start of the work and every 6 months thereafter. Furnish certified calibration charts to the Engineer prior to stressing.

Recalibrate jacks requiring repair, such as replacing seals or changing the length of the hydraulic lines. No extra compensation will be allowed for the initial or subsequent calibrations.

5.	Enclosures for Post-Tensioning. Accurately place enclosures (anchorages, ducts, and vents) for prestressing reinforcing according to the Plans or approved shop drawings.

Set and hold the anchorage assemblies and block-out templates for anchorages so that their axis coincides with the axis of the tendon and the wedge plates are normal in all directions to the tendon. Securely fasten anchorages and block-outs to prevent displacement during concrete placement. Unless otherwise specified in the Contract documents or shown on the approved shop drawings, recess the anchoring assemblies in formed block-outs so that the ends of the prestressing steel and all parts of the anchoring assemblies will be at least 3 inches inside of the end surface of the member. Construct all block-outs in leak proof forms that create neat lines with the end surface of the member.

Securely fasten ducts at the proper locations in the forms by ties to reinforcing steel that are adequate to prevent displacement during concrete placement. Use supplementary support bars where needed to maintain proper alignment of the duct. Use hold-down ties to prevent displacement due to duct buoyancy in the fluid concrete. Fasten ducts at 2-foot maximum intervals along the member.

Do not damage the ducts during installation. Do not crimp, flatten, or dent the ducts. Do not perforate the ducts or provide openings in the ducts except at locations designated in the Contract documents or shop drawings. After duct installation, inspect all ducts for damage. The Engineer will reject ducts with unintentional holes or openings and ducts that are dented, crimped, or flattened. Repair duct sections to the satisfaction of the Engineer at no additional cost to the Department and no adjustment in Contract time.

After installation in the forms, cover the ends of the ducts and anchorages at all times to prevent the entry of water or debris.

Prior to placing forms for closing slabs of box girder cells, demonstrate to the satisfaction of the Engineer that all ducts are unobstructed.

6.	Location of Grout Vents. Place grout vents at locations designated in the Contract documents and shop drawings. Equip all grout vents with positive shut-off devices. Extend grout tubes with sufficient distance out of the concrete member to allow for proper closing of the valves.

7.	Placing Reinforcing Steel and Prestressing Steel. Place reinforcing steel according to the requirements of Section 503 and as modified by this Section.

Place prestressing steel in the position as designated in the Contract documents or on the approved shop drawings. Install the prestressing steel in the enclosures by pushing or pulling the total number of strands in a tendon individually or as a unit.

For strands that are pushed, round off the end of the strand and fit the end of the strand with a smooth protective cap.

For strands that are pulled, use a special steel wire sock or other device attached to the end strands to pull the assembled tendon through the duct. Do not weld the ends of the strands together for this purpose. Round the end of the pre-assembled tendon for smooth passage through the duct. Cut strands using an abrasive saw or equal. Do not flame cut strands.

Immediately prior to installing the prestressing steel, demonstrate to the satisfaction of the Engineer that the ducts are free of water, debris, and other obstructions by passing a torpedo through the ducts. Use a torpedo having the same cross-sectional shape as the duct and is 1/4 inch smaller all around than the clear, nominal inside dimensions of the duct. Make no deductions to the torpedo section dimensions for tolerances allowed in the manufacture or fixing of the ducts. For straight ducts, use a torpedo at least 2 feet long. For curved ducts, determine the length so that when both ends touch the outermost wall of the duct, the torpedo is 1/4 inch clear of the innermost wall. If the torpedo will not travel completely through the duct, the Engineer will reject the member, unless a workable repair can be made to clear the duct. The torpedo must pass through the duct easily, by hand, without resorting to excessive effort or mechanical assistance.

If the strands do not easily pass through the duct or an obstruction is encountered, do not force strands through the duct.

Do not install the prestressing steel in the duct prior to placing and curing of the concrete.

Straighten prestressing steel strands that are to be stressed simultaneously or when necessary to ensure proper positioning in the ducts.

8.	Placing Concrete. Produce and place concrete according to the requirements of Section 501 and as modified by this section.

Before depositing concrete in the forms, obtain an inspection and approval of the placement of reinforcing, enclosures, anchorages, and prestressing steel. Vibrate the concrete internally, externally, or both, as directed by the Engineer. Vibrate carefully to avoid displacing the reinforcing steel, anchorages, ducts, grout vents, or other items embedded in the concrete.

9.	Post-tensioning. Do not begin tensioning operations until concrete cylinder tests, manufactured according to AASHTO T 23 and tested according to AASHTO T 22 using the same concrete and maintained in the same curing conditions as the member, indicate that the concrete has attained the minimum initial compressive strength (release strength, f'ci) indicated in the Contract documents. Do not begin tensioning operations until after the Engineer approved patches or repairs have been satisfactorily completed. Do not tension the prestressing steel until all concrete in the member has been placed.

Perform stressing of tendons in conformance with the sequence shown on the approved shop drawings and to the satisfaction of the Engineer. Stress tendons in such a sequence that lateral eccentricity of prestress and loss of prestress will be a minimum. Stress tendons symmetrically about the center of the typical section so no more than one tendon is eccentric about the centerline at any one time. Sequence the stressing of the tendons so the individual tendon force does not exceed the tendon force in all other tendons by more than 50 percent of the final jacking force of the tendon at any one time.

Stress all strands in each tendon simultaneously. Stress tendons by jacking from only one end of the member unless otherwise approved by the Engineer.

Conduct the tensioning process so that tension being applied and the elongation of the prestressing steel may be measured at all times. Measure elongation to the nearest 1/16 inch. Tension all tendons to a preliminary force between 5 and 25 percent of the final jacking force to eliminate any wedge slip or take-up in the tensioning system before elongation measurements are started. Record the preliminary force so that it can be used in the elongation measurement. Mark at least 25 percent of the strands in each tendon prior to final stressing to permit measurement of elongation and to ensure that all anchor wedges set properly.

For the required tendon force, the observed elongation must agree within 5 percent of the theoretical tendon elongation. In the event the observed elongation is not within acceptable tolerances, determine the source of error and revise the post-tensioning operation to the satisfaction of the Engineer before proceeding. Do not overstress the tendon to achieve the theoretical elongation. No claim for damages or additional compensation or adjustment in Contract time resulting from revisions to the post-tensioning operation will be made or allowed.

Multi-strand post-tensioning tendons having wires that fail, by breaking or slippage during stressing, will be rejected.

Cut post-tensioning steel with an abrasive saw within 1 to 2 inches from the anchoring device. Do not flame cut prestressing steel.

Provide a record of the post-tensioning operation to the Engineer following each tendon installation including, but not limited to, the following:

a.	Project name and bridge number;

b.	Contractor and / or subcontractor name;

c.	Tendon location, size, type;

d.	Date and time tendon was first installed in the duct;

e.	Reel number for strands;

f.	Tendon cross-sectional area;

g.	Modulus of elasticity;

h.	Date and time tendon was stressed;

i.	Jack and gage numbers per end of tendon;

j.	Required jacking force;

k.	Gauge pressure;

l.	Elongation (theoretical and actual);

m.	Anchor set; (anticipated and actual);

n.	Stressing sequence (i.e. tendons stressed before and after);

o.	Stressing mode (one end/ two ends/ simultaneous);

p.	Witnesses to stressing operation (signature); and

q.	Date grouted.

Cover ends of tendons and anchorages immediately after stressing in accordance with Subsection 502-3.02.3.

502-3.03 CAMBER. Camber is the upward deflection that occurs in prestressed concrete flexural members due to the combination of stressing forces and dead load. It does not include dimensional inaccuracies from manufacturing errors.

Form girders so the roadway surface conforms to the indicated grade line with an allowance for 1/2 inch of positive camber at midspan. Form girders to adjust for the predicted long-term camber from loss of prestress and from dead load deflection. When estimating this adjustment, assume that future paving will be applied 3 years after erection.

Control the concrete properties and the placing, curing, curing times, tensioning procedures, and the storage of precast prestressed beam sections. Control these elements so that the shape and amplitude of the deflection curves for all girders will be within specified tolerances and as nearly alike as possible.

Measure camber with the girder supported at bearing points only. When it is impractical to support the girder on its bearing points, you may use alternative support points. Obtain approval of the alternative supports and submit calculations of the effects of the supports on girder camber. Measure actual camber during prestressing force transfer and compare it with computed values and tolerances.

502-3.04 TOLERANCES. Produce prestressed concrete members conforming to the following dimensional tolerances:

1.	Camber: Do not vary from approved camber more than ±1/8 inch per 10 feet of length, but not to exceed 1 inch. In addition, the camber of any girder may not differ from that of any other girder by more than 1 inch.

2.	Position of Strands: ±1/4 inch (±1/2 inch where harped strands exit the member).

3.	Longitudinal Position of Deflection Point for Harped Strands: ±12 inches.

4.	Position of Ducts and Anchorages: ±1/4 inch

5.	Position of Local Zone Reinforcement: Center reinforcement on the duct and start within 1/2 inch of the back of the bearing plate.

6.	Position of Weld Plates: ±1 inch measured along joint. ±1/8 inch transverse to joint.

502-3.05 BONDING AND GROUTING. Conform to the following:

1.	General. Bond post-tensioned prestressing steel to the concrete by completely filling the entire void space between the duct and the tendon with grout. Grout tendons in accordance with the procedures set forth in the approved grouting operation plan. Grout all empty ducts.

2.	Personnel Qualifications. Carry out all grouting operations by workers trained for and experienced in the tasks required. Perform grouting under the immediate control of the post-tensioning technician as described in Subsection 502-3.02.

3.	Grouting Operation Plan. No less than 30 days prior to the initiation of production grouting, submit a grouting operation plan to the Engineer for approval. Devise the grouting procedures to ensure that the ducts will be properly filled by grout. As a minimum, address and provide procedures for the following items in the grouting operation plan:

a.	Type, quantity, and brand of materials used in the grouting including all material certifications;

b.	Type of equipment furnished, including capacity in relation to demand and working condition, as well as back-up equipment and spare parts;

c.	Types and locations of vents;

d.	Types and sizes of grout hoses and connections;

e.	Theoretical grout volume calculations;

f.	General grouting procedure;

g.	Duct cleaning method prior to grouting;

h.	Mixing and pumping procedures;

i.	Type and frequency of quality control production tests;

j.	Direction of grouting;

k.	Sequence of use of the vents;

l.	Method to be used to control the rate of flow and pressure within the ducts;

m.	Procedures for handling blockages, including flushing of ducts;

n.	Procedures for possible post grouting repair; and

o.	Names of the persons in charge and the other personnel who will perform the grouting operation, including their relevant certification, experience, and skill.

Do not commence production grouting until the Engineer provides written approval of the grouting operation plan.

Before initiation of production grouting, conduct a joint meeting with the grouting technician, subcontractors, grouting crew, and the Engineer to discuss the grouting operation plan, required testing, corrective procedures, and other relevant issues.

4.	Grout Storage. Store all grout materials in a dry enclosure or building that is convenient to the work site. Limit on site storage of grout to a maximum period of one month.

5.	Grout Production Tests. Carry out the minimum number of production grout tests as follows:

a.	Grout Strength Test. Prepare grout cube specimens in accordance with ASTM C 942, “Standard Test Method for Compressive Strength of Grouts for Preplaced-Aggregate Concrete in the Laboratory.” Perform a minimum of one strength test per day during grouting operations. Submit strength test results to the Engineer within 24 hours of test completion.

b.	Fluidity test. Perform the modified version of ASTM C 939 “Standard Tests Method for Flow of Grout for Preplaced-Aggregate Concrete (Flow Cone Method)” Test as specified in Subsection 701-2.05. Repeat testing at least every two hours of grouting operations. Submit fluidity test results to the Engineer within 24 hours of test completion.

6.	Field Trial Test. Demonstrate to the satisfaction of the Engineer that the grouting equipment, methods, and procedures are appropriate. Conduct field trial tests at least seven days prior to initiation of production grouting or as specified by the Engineer. Perform batching and testing with the same materials, personnel, and equipment used in production grouting. Furnish all materials and labor at no cost to the Department.

7.	Preparation of Enclosures. If a corrosion inhibitor, or any other material other than prestressing steel is inside the duct, flush the ducts using a solution of quick lime (calcium oxide) or slaked lime (calcium hydroxide) in the amount of 0.1 lbs/gal.

Blow duct with oil free compressed air to remove water and debris blockages that may interfere with the injection of grout.

Inspect valves to be sure that they can be opened and closed properly. Check that the grout hose connections and inlets are free of dirt.

8.	Equipment. Provide grouting equipment consisting of measuring devices for water, a high-speed shear colloidal mixer, a storage hopper (holding reservoir) and a pump with all the necessary connecting hoses, valves, and pressure gauge. Provide grouting equipment with sufficient capacity to ensure that the post-tensioning ducts to be grouted can be filled and vented without interruption in less than 20 minutes.

Provide an air compressor, flushing equipment, and hoses with sufficient output to perform the required functions.

At the direction of the Engineer, provide vacuum grouting equipment (volumetric measuring type) in the event that voids are encountered after the grouting operation is complete. No additional compensation will be made in the event that vacuum grouting equipment is required.

Provide the following equipment:

a.	Mixing Equipment. Provide a high speed shear colloidal mixer capable of continuous mechanical mixing producing a homogeneous and stable grout free of lumps and un-dispersed cement. Use only colloidal grout machinery that has separate charging and storage tanks. Equip the charging tank with a high shear colloidal mixer and fit the storage tank with an agitator to keep the grout moving continuously before it is pumped into the duct. Use grouting equipment with a gravity feed to the pump inlet from the storage tank.

Include a screen having clear openings of 1/8 inch maximum size to screen the grout prior to its introduction into the grout pump or storage hopper. Locate the screen between the charging tank and the storage tank so that the screen is easily accessible for inspection and cleaning.

Keep the holding tank agitated and at least 1/4 full at all times during the pumping operation to prevent air from being drawn into the post-tensioning duct.

Periodically inspect the screen during grouting operations. Do not use grout if lumps of cement remain on the screen.

Add water during the initial mixing by use of a calibrated flow meter or calibrated water reservoir with a measuring accuracy equal to one percent of the total water volume. Where water is not supplied through the public water supply system, provide a water storage tank of sufficient capacity.

b.	Grout Injecting Equipment. Provide pumping equipment capable of continuous operation with little variation of pressure that includes a system for circulating the grout when actual grouting is not in progress.

Use positive displacement type grout pumps that provide a continuous flow of grout and will be able to maintain a discharge pressure of at least 145 psi. Use grout pumps with adequate capacity so that an optimal rate of grouting can be achieved. Ensure pumps are constructed to have seals adequate to prevent oil, air or other foreign substances entering the grout and to prevent loss of grout or water.

Use equipment capable of maintaining pressure on completely grouted ducts and fitted with a valve that can be closed off without loss of pressure in the duct.

Install a pressure gauge having a full-scale reading of no more than 290 psi at the duct inlet. If hoses in excess of 100 feet total length are used, place and use two gauges, one at the pump and one at the inlet.

Use grout hoses with sufficient diameter, rated pressure capacity and that are compatible with the pump output. Install a sampling tee with stopcock that minimizes the number of bends, valves, and changes in diameter. Firmly connect grout hoses to pump outlets, pipes, and duct inlets.

Do not use compressed air to aid the pumping of grout.

c.	Air Compression. Provide equipment to supply oil-free and water-free compressed air to blow out excess water and to check the free passage of the ducts.

d.	Flushing Equipment. Provide standby flushing equipment using a potable water supply to facilitate complete removal of grout from the duct if difficult grouting conditions exist. This equipment is in addition to the grouting equipment. Utilize a different power source than the grouting equipment. Furnish equipment that is capable of delivering a pressure of at least 290 psi to flush out partially grouted enclosures.

e.	Vacuum Grouting Equipment. At the direction of the Engineer, provide vacuum grouting equipment. Use volumetric measuring type vacuum grouting equipment with the ability to measure a void and supply a measured volume of grout to fill the void.

f.	Standby Equipment. During grouting operations, provide a standby grout mixer and pump.

9.	Mixing of Grout. Mix grout using the entire contents of each bag in accordance with the manufacturer’s recommendations and using a metered amount of water. Mix the materials thoroughly to produce a homogeneous grout without excessive temperature increase or loss of properties. Do not mix grout longer than the manufacturer’s recommended duration. Continuously agitate the grout until grouting is complete.

Check the fluidity of the grout in accordance with Subsection 701-2.05. Do not commence grout pumping until fluidity requirements are satisfied.

Do not add water to increase fluidity that has decreased by delayed use of the grout.

10.	Injection of Grout. Use a method of injecting grout that will ensure complete filling of the ducts and complete encasement of the prestressing steel.

Open all grout vents before commencing grouting operations, unless otherwise approved by the Engineer.

Perform grouting in one operation, maintaining a continuous, one-way flow of grout at all times within a grouting stage. Grout tendons from the lowest vent in an uphill direction. Unless approved otherwise by the Engineer, pump grout at a rate of 15 feet to 50 feet of duct per minute to avoid air entrapment, segregation of the grout, and to ensure complete filling of the duct. Conduct normal grouting operations at a pressure range of 10 psi to 75 psi measured at the grout inlet. Do not exceed the maximum pumping pressure of 145 psi at the grout inlet.

Pump grout through the duct and continuously discharge grout from the first and subsequent outlets until any residual water and entrapped air has been removed and the consistency of the grout is equivalent to that of the grout being pumped into the inlet. Discharge at least 1/2 gallons of grout from each outlet prior to closing the vent. Close all outlet vents in a similar manner one after another in the direction of flow except that at intermediate crests, close outlet vents placed a short distance downstream of the crest before closing their associated high point vent. Discarded grout does not represent additional cost to the Department.

Pump grout through the duct and continuously discharge grout, to the satisfaction of the Engineer, at the anchorage and grout cap outlets until all free water and air are discharged and the consistency of the grout is equivalent to that of the grout being pumped into the inlet. Close the anchorage outlet vent and discharge a minimum of 1/2 gallon of grout from the grout cap. Close the grout cap outlet.

After all outlets have been bled and sealed, bleed the grout pressure to 5 psi and wait a minimum of ten minutes for entrapped air to flow to the high points. After ten minutes, increase the pressure as needed and discharge grout at each high point outlet to eliminate all entrapped air or water. Complete the process by locking a pressure of 30 psi into the tendon prior to closing the inlet vent.

If the actual grouting pressure exceeds the maximum allowed, close the inlet vent and pump grout at the next outlet, which has just been or is ready to be closed, as long as one-way flow is maintained. Do not pump grout into a succeeding outlet vent from which grout has not yet flowed. If this procedure is used, equip the new inlet vent with a positive shut-off and pressure gage.

11.	Temperature Considerations. Do not grout if the ambient air temperature exceeds 100°F. Do not grout if the ambient air temperature is expected to be less than 40°F within 48 hours. Ensure grout temperature upon mixing is between 50°F and 90°F.

If the ambient air temperature is below 32°F, keep ducts free of water to avoid damage due to freezing. Do not warm ducts with steam. Blow dry air (60% humidity or less) through the ducts to extract trapped water. Ensure ducts are free of frost and ice before commencing grouting operations.

12.	Post-Grouting Inspection. Do not remove or open vents until the grout has cured for at least 24 hours. After the grout has cured, remove all outlets and grout caps located at anchorages and high points along the tendon to facilitate inspection. If voids are suspected or if duct grouting operations were prematurely terminated prior to completely filling the duct, explore the voided area inside the duct with an endoscope, borescope, videoscope, or other visual means approved by the Engineer. Probing is not allowed. Determine the location and extent of all voided areas.

Depending on the location of the void, drilling may be required to penetrate the inner surface of the anchorage or duct. Use drilling equipment that will automatically shut-off when steel is encountered.

13.	Repairing and Filling Voids. Repair and fill all voids that occur in the ducts after the grouting operation is complete. If voids are found, submit a grouting repair plan to the Engineer for review and approval that describes the location and extent of the void and the method of repairing and filling the void. If the extent and location of the void is such that complete filling of the void is not possible using the grout injection equipment, repair and fill the void using a volumetric measuring vacuum grouting process utilizing the vacuum grouting equipment specified in Subsection 502-3.05.8.

14.	Finishing. Remove all valves, caps and pipes for each vent to a depth at least 1 inch below the surface of the concrete. Fill the void left by the vent pipe according to Subsection 501-3.10.1. Do not remove or open vents until the grout as set for at least 24 hours.

15.	Protection of End Anchorages. Within seven days upon completion of the grouting, permanently protect the anchorage of post-tensioning tendons to prevent access of water or other aggressive agents.

Immediately before casting the concrete pour-backs (within 24 hrs.), mechanically clean and roughen the mating concrete surfaces to remove any laitance and to expose small aggregate. Use abrasive blast cleaning or water blasting with a pressure washer capable of at least 10,000 psi nozzle pressure at all elevations to clean the concrete surfaces. Keep the nozzle tip no more than 12 inches from the surface during all phases of water blasting. Flush the surface with water and blow dry. Ensure surfaces are clean, sound and without standing water.

Unless otherwise specified in the Contract documents or shown on the approved shop drawings, ensure the prestressing steel and all parts of the anchoring assemblies are at least 3 inches inside of the end surface of the member. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Fill the recess with concrete and finish the concrete surface to true lines according to the Contract requirements.

16. 	Record of Grouting Operation. Submit a written report to the Engineer within 72 hours after grouting. Include in this report:

a.	the date of grouting;

b.	the number of days from tensioning to grouting;

c.	the tendons grouted;

d.	the quantities and types of materials used;

e.	the volume of grout pumped into the duct

f.	a summary of problems encountered during grouting and steps taken to resolve them;

g.	the maximum pumping pressure at the inlet;

h.	the temperature measurement of the air, water, prepackaged material, mix grout, and concrete member in the duct.

i.	the results of quality control testing.

502-4.01 METHOD OF MEASUREMENT. Section 109.

502-5.01 BASIS OF PAYMENT. The lump sum payment is full compensation for furnishing, installing, stressing, grouting, repairing, and inspecting all post-tensioned tendons accepted in place.

All items of the post-tensioning system embedded within the concrete including but not limited to prestressing steel, enclosures for prestressing steel, wedges, wedge plates, anchorage assemblies and associated supplemental reinforcing steel required by the supplier, grout vents, and grout gaps are subsidiary to post-tensioned concrete structural members.

All post-tensioning system hardware that is not embedded in concrete including but not limited to jacks, gauges, wire socks, and torpedoes are subsidiary to post-tensioned concrete structural members.

All items and equipment to fill the ducts with grout including but not limited to mixers, gauges, flushing equipment, and production tests are subsidiary to post-tensioned concrete structural members.

All materials for protecting the post-tensioning steel and anchorages including but not limited to corrosion inhibitors, flushing equipment, concrete bonding agents, and equipment to prepare the concrete block-outs are subsidiary to post-tensioned concrete structural members.

All labor, materials, tools, equipment and incidentals necessary for completing the work are subsidiary to post-tensioned concrete structural members.

Payment for prestressing precast concrete members is included in the Contract price paid for the precast members, as provided for Section 501.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

502(1)	Post-Tensioning (Type)	Lump Sum

Replace Section 503 with the following:

Section 503
Reinforcing Steel

503-1.01 DESCRIPTION. Furnish and place reinforcing steel according to the Contract documents.

503-1.02 DEFINITIONS.

STIRRUP. Reinforcement used to resist shear and diagonal tension stresses in a structural member, installed perpendicular to or at an angle to the longitudinal reinforcement; lateral reinforcement formed of individual or paired units, open or closed.

TIE. Reinforcement with hooked ends tied at right angles to and enclosing the longitudinal reinforcement.

HOOP. A one-piece closed tie or continuously wound tie, the ends of which are hooked or welded together, that encloses the longitudinal reinforcement.

BAR SIZE / DIAMETER. Nominal dimensions equivalent to those of a circular area having the same weight per foot as the AASHTO/ASTM designated bar.

SPIRAL. Continuously wound reinforcement in the form of a cylindrical helix.

LONGITUDINAL REINFORCEMENT. Reinforcement parallel to the length of a concrete member.

LATERAL REINFORCEMENT. Reinforcement perpendicular to the length of a concrete member.

COVER. The least distance between the surface of embedded reinforcement and the outer surface of the concrete.

HOOK. A bend in the end of a reinforcing bar.

LOT. A defined quantity.

503-2.01 MATERIALS.

Reinforcing Steel Bars	Subsection 709-2.01

Epoxy-Coated Reinforcing Steel Bars	Subsection 709-2.01

Headed Reinforcing Steel Bars	Subsection 709-2.01

Epoxy Coating Patch Material	Subsection 709-2.01

CONSTRUCTION REQUIREMENTS

503-3.01 BAR LIST. Furnish order lists and bending diagrams for approval according to Subsection 105-1.02. Furnish order lists and bending diagrams detailed in accordance with ACI 315, Chapter 3.

Do not substitute reinforcing bars of different size, material, coating, or grade without prior approval of the Engineer. When substituting epoxy-coated reinforcing steel for uncoated reinforcing steel, protect and repair all epoxy-coated bars according to Subsection 503-3.02.

503-3.02 PROTECTION OF MATERIALS. Protect reinforcing steel from damage at all times. Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of dirt, loose rust or scale, paint, oil, or other foreign substance. Pressure wash all reinforcing steel that has a surface coating of dirt, dust, or has been exposed to salt spray or other deleterious substances. Use a pressure washer with at least 2000 psi at all elevations. Keep the nozzle tip no more than 12 inches from the surface during all phases of power washing. Do not weld or tack weld reinforcing steel except as noted in the Contract documents and approved by the Engineer. When transporting, storing, or constructing in close proximity to bodies of salt water, keep all reinforcing steel in enclosures that provide protection from the elements.

Do not damage epoxy-coated reinforcing steel. When handling coated reinforcing steel, avoid bundle-to-bundle and bar-to-bar abrasion. Use padded bundling bands. Handle epoxy-coated bars using equipment with padded contact areas. Lift bundles with a strongback, multiple supports, or a platform bridge to prevent bar-to-bar abrasion from sags in the bar bundle. Do not drop or drag the bars or bundles. Off-load bars as close as possible to their points of placement to minimize re-handling.

Store epoxy-coated reinforcing steel off the ground. When stacking is necessary, place supports between bundles. Place supports sufficiently close to prevent sags in the bundles. Store coated and uncoated bars separately.

Protect epoxy-coated reinforcing steel from sunlight, salt spray, and weather exposure during shipping and storage. Cover epoxy-coated reinforcing steel and bundles with opaque polyethylene sheeting or other protective material. Secure covering and allow air circulation to minimize condensation under the covering. The Engineer will reject epoxy-coated reinforcing steel when the cumulative environmental exposure time, including all uncovered storage time after coating application to full embedment in concrete, exceeds 2 months.

The Engineer will reject epoxy-coated reinforcing steel when the extent of damaged coating exceeds 2 percent of the surface area in any 1-foot length of bar. When the extent of damaged coating does not exceed 2 percent of the surface area in any 1-foot length of bar, repair all damaged coating. Coating damage includes cracks, abrasions, chips, bond loss (the coating can be removed with a peeling action by the finger), and exposed steel areas visible to a person with normal or corrected vision prior to concrete placement. Repair coating damage as soon as possible and before visible oxidation appears on the steel surface. Repair coating damaged due to shipment, storage, and handling prior to placing the reinforcing steel.

Prepare coating damage prior to applying patch material. Clean and remove all disbonded areas of coating. Remove loose and deleterious materials. In cases when rust is present, remove rust by thoroughly cleaning the area using blast cleaning, filing, or power brushing in a manner that minimizes damage to the sound coating. The Engineer will reject epoxy-coated reinforcing steel when the removed coating exceeds 2 percent in any 1-foot length of bar or if the weight, dimensions, cross-sectional area, or tensile properties are less than the minimum requirements of the applicable specification.

Use an approved epoxy coating patch material according to the material manufacturer's recommendations. Apply patching material according to the written instructions furnished by the patching material manufacturer. Allow the patching material to fully cure before placing concrete. The Engineer will reject epoxy-coated reinforcing steel when the surface area covered by patching material exceeds 5 percent in any 1-foot length of bar.

Rejected epoxy-coated reinforcing steel may not be substituted for uncoated reinforcing steel or used as bar supports.

At all times, protect mechanical splice assemblies, headed bar assemblies, and connecting elements (including reinforcing bar ends) against physical damage and corrosion. Keep assemblies and connecting elements clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials that adversely affect fabrication or performance. The Engineer will reject mechanical butt splice assemblies, headed bar assemblies, or reinforcing steel that has sustained physical damage or corrosion at any time. Coating damage includes cracks, abrasions, chips, bond loss (the coating can be removed with a peeling action by the finger), exposed steel areas etc. visible to the naked eye. Repair coating damaged due to shipment, storage, and handling prior to placing the reinforcing steel.

503-3.03 FABRICATION. Fabricate reinforcing steel to the size and dimension shown in the Contract documents. Reinforcing steel dimensions shown are out-to-out of bar, unless otherwise noted.

Meet fabrication tolerances in ACI Publication 117, Section 2.1.

Weld reinforcing bars in accordance with AWS D1.4.

- Bends. Bend bars when the bar temperature is above 45°F and less than 150°F. Produce hooks and bends in reinforcing bars with inside diameters as shown in Table 503-1, unless otherwise noted. The Engineer may reject reinforcing steel bent at any time with an inside diameter less than the minimum diameter shown in Table 503-1.

TABLE 503-1

BEND DIAMETER

| BAR SIZE | Stirrups and ties | ALL OTHER BENDS |
| --- | --- | --- |
| No. 3 | 1½" | 2¼" |
| No. 4 | 2" | 3" |
| No. 5 | 2½" | 3¾" |
| No. 6 | 4½" | 4½" |
| No. 7 | 5¼" | 5¼" |
| No. 8 | 6" | 6" |
| No. 9 | - | 9½" |
| No. 10 | - | 10¾" |
| No. 11 | - | 12" |
| No. 14 | - | 18¼" |
| No. 18 | - | 24" |

For the purposes of these Specifications, the term "Standard Hook" means one of the following:

a.	Std 180° Hook: 180° bend plus a 4.0 nominal bar diameter extension, but not less than 2.5 inches, at the free end of the bar.

b.	Std 90° Hook: 90° bend plus a 12.0 nominal bar diameter extension at the free end of the bar.

Do not re-bend or straighten bars without approval by the Engineer.

2.	Bar Repairs. Implement all preventative measures necessary to prevent improperly bent bars including bars bent at locations not required by the Contract or with an inside diameter less than minimum diameter shown in Table 503-1. The Engineer will evaluate improperly bent bars at any time during execution of the Contract for structural adequacy and durability. Do not repair improperly bent bars until the bars are inspected by the Engineer. Bars repaired prior to inspection by the Engineer will be rejected. If, in the opinion of the Engineer, the bend is of such extent or character as to affect the strength or durability of the bar, the Engineer will reject the material. Otherwise, re-bend or straighten bars according to the requirements of this Section and in a manner that will not damage the material, coating, or concrete.

If the Engineer approves repairing the bar, preheat the reinforcing steel before bending. Apply heat by any method that does not damage the reinforcing steel or concrete. Preheat the reinforcing steel at least 5.0 nominal bar diameters in each direction from the center of the bend but do not extend preheating below the surface of the concrete. Insulate all concrete within 6 inches of the heated bar area. Do not allow the temperature of the reinforcing bar at the concrete interface to exceed 500°F. Preheat the reinforcing steel to at least 1100°F. Ensure, by using temperature-indicating crayons, contact pyrometer or other acceptable means, that the maximum reinforcing steel temperature never exceeds 1200°F. Use 2 heat tips simultaneously at opposite sides of bars larger than No. 6 to assure a uniform temperature throughout the thickness of the bar. For size No. 6 and smaller bars, use 2 heat tips, if necessary. Maintain the preheat temperature of the reinforcing steel until bending or straightening is complete. Make the bend gradually with smooth continuous application of force. Use a bending tool equipped with a bending diameter as listed in Table 503-1, unless otherwise noted.  When straightening, move a bender progressively around the bend. When bending or straightening is complete, gradually reduce the temperature of the reinforcing steel to the ambient air temperature. Do not artificially cool the bars with water, forced air, or any other means.

503-3.04 PLACING AND FASTENING. Place and secure reinforcing steel in position as noted in the Contract documents so that the reinforcing steel will be held firmly in place during placing and setting of the concrete. Do not place bars in addition to that noted in the Contract documents without prior approval of the Engineer. Do not place bars of different size, material, or grade than noted in the Contract documents without prior approval of the Engineer. Place all reinforcing steel evenly unless noted otherwise. Provide 2 inches of concrete clear cover, measured from the surface of the reinforcement to the outside surface of the concrete, unless noted otherwise.

Do not place bars on layers of fresh concrete or adjust bars while placing concrete.

Repair detectable coating damage on epoxy-coated reinforcing steel in accordance with Subsection 503-3.02.

1.	Fastening Requirements. In order to position the reinforcing steel as required in the Contract documents and ensure the steel does not move as the concrete is placed, tie the bars with No. 14 or No.16 gauge steel wire. When the spacing between bars is 1 foot or more, tie the bars at all intersections. When the bar spacing is less than 1 foot, tie every other intersection. If the Plans require bundled bars, tie bundled bars together at not more than 6-foot centers. Tie all intersections of epoxy-coated reinforcing steel in the top mat of concrete decks and approach slabs. Use wire coated with plastic, epoxy, or similar non-conductive material when tying epoxy-coated reinforcing steel. Obtain the Engineer’s written authorization before welding reinforcing steel. Provide at least 1 inch clear cover to the tie wire by turning all tie wire away from concrete surfaces.

For slip-formed concrete, tie reinforcing steel at all intersections. Provide additional reinforcing steel cross bracing to keep the cage form moving during concrete placement. Place cross bracing both longitudinally and transversely.

2.	Bar Supports. Maintain distances from the forms using approved precast mortar blocks, metal supports, or plastic supports strong enough to resist permanent movement under construction loads. If supports extend to exposed concrete surfaces, use metal or plastic supports. To support and fasten epoxy-coated reinforcing steel, use plastic supports or metal supports coated with plastic, epoxy, or similar non-conductive material. Do not use wooden or aluminum supports.

Place supports at frequent intervals so as to maintain the cover between the reinforcing and the surface of the concrete. Space supports under concrete deck reinforcement and approach slab reinforcement not more than 4 feet apart in each direction.

a.	Precast Mortar Blocks. Provide mortar blocks meeting the following:

(1)	Compressive strength equal to that of the concrete in which the mortar blocks are embedded.

(2)	Bearing area less than 2 inches in each dimension.

(3)	Have either a grooved top that will hold the reinforcing bar in place or a protruding embedded wire that is tied to the reinforcement.

Mortar blocks may be accepted on a Manufacturer's Certificate of Compliance that includes test results on sets of two 2-inch square specimens per AASHTO T 106. Each pair of specimens represents no more than 2,500 mortar blocks made of the same mortar as the blocks and cured under the same conditions.

b.	Metal Supports. Provide metal supports meeting at least one of the following:

(1)	Galvanized after fabrication in accordance with AASHTO M 232 Class D,

(2)	Stainless steel meeting the requirements of ASTM A 493, Type 302, or

(3)	Plastic coated using coatings that do not react chemically with the concrete, have a minimum thickness of 3/32 inch where the support touches the form, do not crack at or above -5°F, and do not deform enough to expose the metal at or below 200°F.

c.	Plastic Supports. Provide plastic supports meeting the following:

(1)	Non-porous.

(2)	Chemically inert in concrete.

(3)	Have rounded seats.

(4)	Do not deform under load during normal temperatures.

(5)	Do not shatter or crack under impact loading in cold weather.

(6)	Have at least 25 percent of their gross area perforated.

Do not use plastic supports that prevent complete concrete consolidation in and around the support or require supports less than 1 foot apart along the length of the bar.

503-3.05 SPLICING. Splice reinforcing steel bars at locations shown on the Plans or otherwise designated in the Contract documents. Obtain the written approval of the Engineer before splicing bars at other locations. The Engineer will evaluate splices at locations not designated in the Contract documents for structural adequacy.

Splice reinforcing steel bars using lap splicing, welded butt joints, welded lap splicing, mechanical butt splicing, or mechanical lap splicing, unless noted otherwise in the Contract documents. Do not splice reinforcing steel bars in locations identified in the Contract documents where splices in the reinforcing steel are not allowed.

Splices will not be permitted in bars 40 feet or less in plan length. For bars exceeding 40 feet in plan length, ensure the distance center-to-center of splices is not less than 40 feet, with no individual bar length less than 10 feet. Stagger splices in adjacent reinforcing bars, unless otherwise noted in the Contract documents. Stagger lap splices a distance greater than the lapped splice length. Stagger butt splices at least 2 feet.

Do not use lap splicing for No. 14 or No. 18 reinforcing bars.

Do not lap splice spiral reinforcing steel. Anchor each end unit of spiral reinforcing bar by lapping the free end of the bar to the continuous spiral and using either a welded lap splice or a mechanical lap splice.

Reinforcing steel may be continuous at locations where splices are noted in the Contract documents. Locate splices based upon available commercial lengths where practicable except where noted otherwise in the Contract documents.

Do not field weld epoxy coated reinforcing bars.

1.	Lap Splicing.

a.	General. Place reinforcing steel bars in contact and securely tie the bars together. Provide a minimum clear distance of 2 inches between the spliced bars and the nearest adjacent bar. Do not reduce the minimum clearance to the surface of the concrete specified in Subsection 503-3.04.

Use lapped splices meeting the minimum lengths as shown in Table 503-2, unless otherwise noted in the Contract documents:

TABLE 503-2

LAPPED SPLICE LENGTH

| BAR SIZE | UnCOATED | COATED |
| --- | --- | --- |
| No. 3 | 1' - 4" | 1'- 11" |
| No. 4 | 1' - 9" | 2' - 7" |
| No. 5 | 2' - 2" | 3' - 3" |
| No. 6 | 2' - 7" | 3' - 10" |
| No. 7 | 3' - 5" | 5' - 2" |
| No. 8 | 4' - 6" | 6' - 9" |
| No. 9 | 5' - 9" | 8' - 7" |
| No. 10 | 7' - 3" | 10' - 10" |
| No. 11 | 8' - 11" | 13' - 4" |

b.	Qualifications and Submittals. No qualifications apply when lap splicing.

c.	Testing/Inspection. Field verify lap splice length.

2.	Welded Butt Joints.

a.	General. Use complete joint penetration (CJP) groove welds conforming to the requirements in AWS D1.4 except as noted below.

Use the joint details and dimensions as shown in Figure 3.2 (A) (B) (D) and (E), "Direct Butt Joints" of AWS D1.4. Do not use split pipe backing.

Do not deviate the reinforcing bar alignment at a welded splice more than 1/4 inch per 4-foot length.

Use electrodes classified as "Nickel-Steel" as referenced in AWS A5.5, A5.28, or A5.29.

Protect welding areas from precipitation and wind velocities in excess of 5 mph.

Perform welds using qualified welders and qualified Welding Procedure Specifications (WPS) meeting AWS D1.4

Perform all quality control inspection necessary to ensure the materials and workmanship meets the requirements of the Contract documents using an inspector currently certified as an AWS Certified Welding Inspector (CWI) according to the provisions of AWS QC1.

Perform all nondestructive testing other than visual testing as required in the Contract documents using personnel currently qualified for NDT Level II or NDT Level I working directly under the NDT Level II according to the provisions of the American Society for Nondestructive Testing's Recommended Practice No. SNT-TC-1A.

Furnish all quality control inspection documents to the Engineer.

Correct all deficiencies in materials and workmanship revealed by the quality control inspector or the Engineer without additional compensation.

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract documents to the reinforcing steel, unless shown on the working drawings and approved by the Engineer.

b.	Qualifications and Submittals. At least 30 days prior to welding, submit for approval a welding plan stamped and signed by the CWI responsible for quality control and consisting of the following documents:

(1)	Quality control inspector qualifications including CWI number.

(2)	Welding Procedure Specifications (WPS).

(3)	Procedure Qualification Records (PQR) and test results.

(4)	Welder Performance Qualification Records (WPQR) with documentation of current welder certification.

(5)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications.

(6)	Nondestructive testing personnel qualifications.

(7)	Methods of protecting the welding area.

(8)	Mill test report(s).

c.	Testing/Inspection.

(1)	Shop Welds. Perform job control tests using a qualified testing laboratory. A job control test consists of the fabrication, under conditions used to produce the splice, and the physical testing of 6 sample splices for each lot of splices. An authorized Department representative will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced complete joint penetration welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

A sample splice consists of a splice to connect two 30-inch, or longer, bars using the same splice materials, position, location and equipment, and following the same procedures as used to make splices in the work. Shorter sample splice bars may be used if approved by the Engineer.

The Engineer or the Engineer's authorized representative shall witness the job control tests performed by the testing laboratory.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material or weld. Submit the test results to the Engineer for review and approval.

Should the average of the results of tests made on the 6 sample splices or should more than 1 sample splice in the job control test develop less than a minimum tensile strength of 80,000 psi, based on the nominal bar area, all splices in the lot represented by that test will be rejected. Replace rejected bar splices at no additional cost to the Department and no adjustment in contract time.

(2)	Field Welds. Perform nondestructive examination using radiographic examination (RT) in accordance with AWS D1.1, Section 6, except for Section 6.17, RT Procedures for field welded complete joint penetration direct butt joints. The standards of acceptance shall be in accordance with AWS D1.4, Section 4.4.2 and Section 4.4.8.

Perform radiographic examinations on a random sample of 25 percent of the total number of direct butt joint welds. The Engineer will select the direct butt joints that will compose the sample. Test sample joints in the presence of the Engineer or the Engineer's authorized representative. Submit the test results to the Engineer for review and approval.

If more than 12 percent of the welds that have been radiographically examined are defective, examine a second random sample of 25 percent of the total number of welds. If more than 12 percent of the welds that have been radiographically examined in the second sample are defective, radiographically examine all remaining welds.

Repair all weld defects in accordance with the requirements of AWS D1.4.

Provide sufficient access to the job site to permit the Engineer or the Engineer's authorized representative to perform any additional inspection or testing.

Notify the Engineer in writing 48 hours prior to performing any radiographic examinations.

Make 2 exposures for each complete joint penetration direct butt joint. For each of the exposures, center the radiation source on each bar to be radiographed. Make the first exposure with the radiation source placed at zero degrees from the top of the weld and perpendicular to the weld root and identify with a station mark of "0". Make the second exposure at 90 degrees to the "0" station mark and identify with a station mark of "90".

Clearly identify each direct butt joint on each radiograph. Establish the radiograph identification and marking system with the Engineer before radiographic inspection begins. Identify film using lead numbers and letters. Do not use etching, flashing or writing to identify film. Legibly mark each piece of film with identification information including, as a minimum, the following information:

(a)	Contractor's name

(b)	Date

(c)	Name of nondestructive testing firm

(d)	Initials of radiographer

(e)	Weld number

Identify a repaired weld by placing the letter "R" followed by the weld repair number on the radiographic film using lead numbers and letters.

Record the results of all radiographic interpretations on a signed certification. Keep a copy of the certification with the film packet.

3.	Welded Lap Splicing.

a.	General. Use direct lap joint welds conforming to the requirements in AWS D1.4 except as noted below.

Use the joint details and dimensions as shown in Figure 3.4 (A), "Direct Lap Joint with Bars in Contact" of AWS D1.4.

Use electrodes classified as "Nickel-Steel" as referenced in AWS A5.5, A5.28, or A5.29.

Preheat reinforcing bars in accordance with AWS D1.4 for a distance of not less than 6 inches on each side of the joint prior to welding. Protect welding areas from air currents, drafts and precipitation to prevent loss of heat or loss of arc shielding. Submit the method of protection of the welding area to the Engineer for approval.

Submit all AWS required test assemblies to the Engineer.

b.	Qualifications. The operator and procedure qualification tests may be performed simultaneously.

Submit a welding plan to the Engineer for approval containing at least the following items:

(1)	Quality Control personnel qualifications including CWI number.

(2)	Welding Procedure Specifications (WPS).

(3)	Procedure Qualification Records (PQR), if applicable.

(4)	Welder Performance Qualification Records (WPQR).

(5)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications.

c.	Testing/Inspection. Perform inspection in accordance with AWS D1.4. Submit the inspection results to the Engineer for review and approval.

4.	Mechanical Butt Splices.

a.	General. Use one of the following types of mechanical butt splices:

(1)	Sleeve-Threaded Mechanical Butt Splices. The sleeve-threaded type of mechanical butt splices consists of a steel splice sleeve with tapered interior threads that joins the reinforcing bars with matching tapered threads. Taper the threads to such a degree that cross threading will not occur during assembly.

Mark each splice sleeve with the heat treatment lot number.

After completion of the assembly, tighten the splice to a torque value recommended by the manufacturer for bars smaller than a No. 8 reinforcing bar and to a torque value of not less than 2400 in-lbs for bars equal to or greater than a No. 8 reinforcing bar.

(2)	Sleeve-Swaged Mechanical Butt Splices. The sleeve-swaged type of mechanical butt splices consists of a seamless steel sleeve applied over the ends of the reinforcing bars and swaged to the bars by means of a hydraulic press.

(3)	Sleeve-Lockshear Bolt Mechanical Butt Splices. The sleeve-lockshear bolt type of mechanical butt splices consists of a seamless steel sleeve, serrated steel strips welded to the inside of the sleeve, center hole with centering pin, and bolts that are tightened until the bolt heads shear off, and the bolt ends are embedded in the reinforcing bars.

(4)	Two-Part Sleeve-Friction Bar Mechanical Butt Splices. The two-part sleeve-friction bar type of mechanical butt splices consists of a shop machined two-part threaded steel sleeve whose ends are friction welded, in the shop, to the reinforcing bars ends.

Engineer's approval of a mechanical butt splice will be based upon manufacturer's technical data, test results, and other necessary proof of satisfactory performance. Resubmit a design for approval if there is any change in the details or materials previously submitted.

Provide a splicing system that when used in accordance with the manufacturer's procedures, except as modified in this section, will develop not less than a minimum tensile strength of 80,000 psi, based on the nominal bar area, and does not exceed a total slip of the reinforcing bars within the splice sleeve, after loading in tension to 29000 psi and relaxing to 2900 psi, of 10 mils for bars smaller than a No. 18 reinforcing bar or 30 mils for No. 18 reinforcing bar. Measure the slip between gage points clear of the splice sleeve.

Conform to the manufacturer's recommendations when splicing, except as modified in this section. Make splices using the manufacturer's standard equipment, jigs, clamps and other required accessories.

Cut square the ends of reinforcing bars to be spliced.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcement if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices or an approved equal.

Submit the following information for each shipment of splice material for review and approval by the Engineer:

(1)	The type or series identification of the splice material.

(2)	The heat treatment lot number for sleeve-threaded type sleeves.

(3)	The bar grade and size number to be spliced by the material.

(4)	A copy of the manufacturer's catalog giving complete data on the splice material and procedure.

(5)	Test results that the splicing system and materials used in accordance with the manufacturer's procedures complies with the minimum tensile strength requirements, the total slip requirements, and other requirements in these specifications.

(6)	A statement that the splice material conforms in all respects to the details and materials of a specific approved design.

b.	Qualifications. Qualify procedures and operators to be used in making splices in reinforcing bars by performing tests on sample splices of the type to be used, before making splices to be used in the work.

Each operator qualification test for mechanical splices consists of 2 sample splices. Each mechanical splice procedure test consists of 2 sample splices.

For sleeve-threaded, sleeve-lockshear bolt and two-part sleeve friction bar mechanical butt splices, make sample splices on the largest reinforcing bar size to be spliced by the procedure or operator being tested, except that No. 14 bars may be substituted for No. 18 bars.

For sleeve-swaged mechanical butt splices, make sample splices on the largest reinforcing bar size of each deformation pattern to be spliced by the procedure or operator being tested.

Each operator qualified for mechanical splicing of reinforcing bars of a given size and mechanical splice type is also considered qualified for all reinforcing bar sizes smaller than those used in making the operator qualification test for that type of mechanical splice.

Perform a separate operator qualification test or procedure test for each mechanical splicing position and procedure that the operator is expected to use on the work.

Mechanical splice procedures and operators may be approved by the Engineer based upon approval of previous tests performed on appropriate sample splices.

Make sample splices at least 3 feet long with the splice at mid-length. Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative. Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

c.	Testing/Inspection. When mechanical butt splices are used, perform job control tests using a qualified testing laboratory. A job control test consists of the fabrication, under conditions used to produce the splice, and the physical testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt splices is defined as no more than 150 of the same type of mechanical butt splices used for each combination of bar size and bar deformation pattern that is used in the work.

A sample splice consists of a splice made to connect two 30-inch, or longer, bars using the same splice materials, position, location and equipment, and following the same procedures as are being used to make splices in the work. Shorter sample splice bars may be used if approved by the Engineer.

Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

For sleeve-threaded mechanical butt splices, fabricate the reinforcing bars to be used for job control tests on a random basis during the cutting of threads on the reinforcing bars of each lot and ship to the job site with the material they represent.

Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

Should the average of the test results for the 6 sample splices or should more than 1 sample splice in any job control test fail to meet the requirements, all splices in the lot represented by that test will be rejected. Replace rejected bar splices at no additional cost to the Department and no adjustment in contract time.

5.	Mechanical Lap Splices.

a.	General. Engineer's approval of a mechanical lap splice will be based upon manufacturer's technical data, test results, and other necessary proof of satisfactory performance. Resubmit a design for approval if there is any change in the details or materials previously submitted.

Provide a splicing system that when used in accordance with the manufacturer's procedures, except as modified in this section, will develop not less than a minimum tensile strength of 75,000 psi, based on the nominal bar area.

Conform to the manufacturer's recommendations when splicing, except as modified in this section. Make splices using the manufacturer's standard equipment, jigs, clamps and other required accessories.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcement if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices or an approved equal.

Submit the following information for each shipment of splice material for review and approval by the Engineer:

(1)	The type or series identification of the splice material.

(2)	The heat treatment lot number for sleeve-threaded type sleeves.

(3)	The bar grade and size number to be spliced by the material.

(4)	A copy of the manufacturer's catalog giving complete data on the splice material and procedure.

(5)	Test results that the splicing system and materials used in accordance with the manufacturer's procedures complies with the minimum tensile strength requirements and other requirements in these specifications.

(6)	A statement that the splice material conforms in all respects to the details and materials of a specific approved design.

b.	Qualifications. Qualify procedures and operators to be used in making splices in reinforcing bars by performing tests on sample splices of the type to be used, before making splices to be used in the work.

Each operator qualification test for mechanical splices consists of 2 sample splices. Each mechanical splice procedure test consists of 2 sample splices.

Each operator qualified for mechanical splicing of reinforcing bars of a given size and mechanical splice type is also considered qualified for all reinforcing bar sizes smaller than those used in making the operator qualification test for that type of mechanical splice.

Perform a separate operator qualification test or procedure test for each mechanical splicing position and procedure that the operator is expected to use on the work.

Mechanical splice procedures and operators may be approved by the Engineer based upon approval of previous tests performed on appropriate sample splices.

Make sample splices at least 3 feet long with the splice at mid-length. Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative. Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

c.	Testing/Inspection. When mechanical splices are used, perform job control tests using a qualified testing laboratory. A job control test consists of the fabrication, under conditions used to produce the splice, and the physical testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical lap splices is defined as no more than 150 of the same type of mechanical butt splices used for each combination of bar size and bar deformation pattern that is used in the work.

A sample splice consists of a splice made to connect two 30-inch, or longer, bars using the same splice materials, position, location and equipment, and following the same procedures as are being used to make splices in the work. Shorter sample splice bars may be used if approved by the Engineer.

Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

Should the average of the test results for the 6 sample splices or should more than 1 sample splice in any job control test fail to meet the requirements, all splices in the lot represented by that test will be rejected. Replace rejected bar splices at no additional cost to the Department and no adjustment in contract time.

503-3.06 HEADED BAR REINFORCEMENT. Headed bar reinforcement consists of deformed steel reinforcing bars in cut lengths with a head attached to one or both ends. Attachment can be accomplished through welding or forging of heads onto the bar ends, by internal threads in the head mating to threads on the bar end or by a separate threaded nut to secure the head to the bar. Heads are forge formed, machined from bar stock, or cut from plate.

For epoxy-coated reinforcing steel, coat headed bar reinforcement after fabrication. Prior to epoxy-coating, remove sharp edges and burrs by rounding the edge of the bar head, and remove weld flash from the bar heads that would prevent proper coating of the headed bar. Do not use thread type headed bar reinforcement with epoxy-coated reinforcing steel.

Perform inspection and test prior to, during, and after manufacturing headed bar reinforcement and as necessary to ensure that the material and workmanship conform to the requirements of the Contract.

When headed bar reinforcement is used, perform production control tests using a qualified testing laboratory. A production control test consists of the fabrication, under conditions used to produce the head, and the physical testing of 3 sample heads for each lot of heads.

A production lot of headed bar reinforcement is defined as no more than 150 splices of the same bar size, with heads of the same size and type, and manufactured by the same method, produced from bar material of a single heat number and head material of a single heat number. If 1 reinforcing bar has a head on both ends, it will be counted as 2 reinforcing bars for the purposes of establishing and testing production lots. Start a new production lot if the heat number of either the bar material of the head material changes before the maximum production lot size is reached.

Test each sample to failure in accordance with ASTM A 370. Failure is defined as partial or total fracture of the parent bar material or the head, or head-to-bar connection. Submit the test results to the Engineer for review and approval.

Should the results of one test made on any of the 3 samples fail to meet ASTM A370, perform 1 retest on 1 additional sample from the same production lot. If the additional test specimen or if more than 1 of the original test specimens fail to meet ASTM A370, all headed reinforcement bars in the production lot represented by that test will be rejected. Replace rejected bars at no additional cost to the Department and no adjustment in contract time.

503-3.07 PLACEMENT TOLERANCES. When placing reinforcing steel, do not reduce the total number of bars specified. Place reinforcing steel within the following tolerances:

1.	Clear Cover: +1/4 inch, -3/8 inch. Do not reduce the clear cover to less than 1 inch.

2.	Placement of Reinforcement: +1/2 inch.

3.	Spacing of Reinforcement: ± One-quarter of the specified spacing, but not to exceed 1 inch.

4.	Spacing for Bundled Reinforcement: Provide at least 1 inch or 2 times the individual nominal bar diameter between bundles, whichever is greater.

5.	Embedment Length and Length of Lap Splices: -1 inch for No. 3 through No. 11 bars, -2 inches for No. 14 and No. 18 (embedment only).

6.	Location of Bends in Bars and Ends of Bars: ±2 inch.

503-4.01 METHOD OF MEASUREMENT. See Section 109.

503-5.01 BASIS OF PAYMENT. Reinforcing steel will be paid for at the Contract lump sum price. The lump sum price is full compensation for furnishing, fabricating, placing, splicing, heading and testing reinforcing steel as indicated in the Contract documents. Increase in weight of reinforcing due to splices, heads, and additional support bars will not be paid for. All materials, equipment and labor required to install reinforcement will be paid for under the Contract lump sum price.

Payment for reinforcing steel used in precast or precast prestressed concrete structural members is included in the Contract price for the precast members, as provided for Section 501.

Payment for reinforcing steel used in minor structures is subsidiary to the structure.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

503(1)	Reinforcing Steel	Lump Sum

503(2)	Epoxy-Coated Reinforcing Steel	Lump Sum

Section 504
Steel Structures

Special Provisions

504-3.01  FABRICATION.  Replace the fourth paragraph of numbered Item 8 with the following:

Using a CWI, perform all Quality Control inspection necessary to ensure the materials and workmanship meet the requirements of the contract documents.

504-3.01  FABRICATION.  Add the following to numbered Item 8:

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract Documents to the permanent structure, unless shown on the working drawings and approved by the Engineer.

504-5.01 BASIS OF PAYMENT. Add the following: Welding and fabrication inspection is subsidiary.

Replace Section 505 with the following:

Section 505
Piling

505-1.01 DESCRIPTION. Furnish and drive piles, and assist in pile testing.

The Engineer will perform high-strain dynamic pile testing on two piles, one pile at each abutment for Peters Creek Bridge, Bridge No. 536.  After the test pile program is completed, the installation and construction control criteria for the remaining bridge foundation piles will be established.

505-1.02 DEFINITIONS.

CAP BLOCK. Cast steel insert between the hammer and the helmet which houses the hammer cushion.  Also called Bonnet, Helmet, or Pile Cap.

CUT-OFF. The cut off end of a pile, or cutting a pileat the finish elevation.

DRIVECAP. A pile driver component that is used to transmit impact forces from the hammer ram to the pile top. The drivecap includes the anvil or striker plate, hammer cushion (capblock), helmet, and pile cushion, if used. (Also termed the driving head).

DRIVING RESISTANCE. The required axial resistance, in units of force, to be achieved during pile driving.

ESTIMATED PILE TIP ELEVATION. The elevation at which the Department expects the Driving Resistance to be achieved.

FRESH HEADING. Cutting the top of a pile perpendicular to the long axis to remove damage, and to obtain a proper driving or splicing surface.

HAMMER CUSHION. A section of material placed in a pot shaped recess on top of the helmet below the striker plate such that the cushion material is compressed as uniformly as possible.  The hammer cushion primarily protects the hammer.

HAMMER ENERGY:  Is a measure of the hammers’ ability to drive the piles.  Ram weight and ram stroke are used to calculate hammer energy.  Hammers are sized and compared using their rated energy.  Comparing the hammers’ nominal rated energy with field measured PDA/CAPWAP tested energy can tell one how the tested hammer is performing.  Hammer energy is in foot-pounds, that is the weight of the ram times the height of the falling ram in the downward stroke in feet.

MAXIMUM RATED HAMMER ENERGY. The theoretical maximum amount of gross energy that a pile driving hammer can generate.

TRANSFERRED HAMMER ENERGY. The amount of energy transferred to the pile for a given blow accounting for friction energy during the ram down stroke, energy retained in the ram and drivecap during rebound, and other impact losses.

HELMET. A pile driver component located between the hammer and the pile.  For steel piles, the helmet contains the striker plate and a hammer cushion only on top of the helmet.  The helmet fits closely on top of the pile to ensure the impact force is transmitted uniformly across the top of the pile and concentric with the axis of the pile.

LEADS. The function of the leads is to hold the pile driving hammer in good alignment with the pile during driving.  Two types of leads commonly used are:

SWINGING LEADS. These leads are attached to the crane at the top by the cable.  They should have a gate at the bottom, which holds the leads around the pile and will often have spikes at the bottom, which are stuck into the ground or template to assist in aligning the hammer.  This type of lead is best suited for piles with no batter driven with a template.

FIXED LEADS. This type of lead has connections at both the top or mid point and the bottom of the leads.  The connection at the top is normally a pivot or rotational type connection.  At the bottom, there is normally a brace which extends from the crane to the leads.  This connection normally has the ability to adjust the leads in or out from the crane and left or right of the crane for driving battered pile.

MINIMUM PENETRATION. The minimum length of pile below the footing to which the pile must be driven.

OBSTRUCTION. An unanticipated object projecting within the path of the pile that causes pile refusal or impedes the pile's advance within required tolerances.

PILE GATE. A device at the base of the leads that is closed around the pile to maintain alignment between the pile and the leads.

REFUSAL. The condition reached when a pile being driven by a hammer has a specified number of blows per inch with the hammer operating at the highest energy setting, or at a condition established by the Engineer.

TEST PILE. An exploratory pile driven to develop recommendations for the installation of permanent piles, to determine information on the hammer, pile, soil and method of installation.  Test pile information can be used to determine pile lengths or driving criteria for production piles.  A test pile may be used as a permanent pile.

TEMPLATE. A structure affixed to the ground used to maintain proper pile alignment during driving.

WAVE EQUATION ANALYSIS. A numerical method of analysis for the behavior of driven piles that predicts the pile capacity versus blow count relationship (bearing graph) and pile driving stress.

505-2.01 MATERIALS. Use materials that conform to the following:

Selected Material, Type A	Section 703-2.07

Structural Steel Piles	Section 715

Sand	Subsection 703-2.12

CONSTRUCTION REQUIREMENTS

505-3.01 PILES. Furnish piles sufficient in length to obtain the Driving Resistance and to extend to the Estimated Pile Tip Elevation specified in the Contract documents. Furnish full-length piles where practical. Where splices are required, follow the provisions of Subsection 505-3.05. Furnish additional pile length to provide for fresh heading and to suit the method of installation. Use metal shoes or reinforced tips as required. Store and handle piles in a manner that protects them from damage.

1.	Steel Piles. Furnish H-pile sections, pipe piles, sheet piles or other structural steel sections described in the Contract.

Do not furnish spirally welded pipe piles.

The Engineer will reject steel piles that exceed the camber and sweep permitted by allowable mill tolerance.

Hot-dip galvanize steel piles to a minimum thickness of 4 mils from the top to a distance not less than 10 feet below the finished ground line according to Subsection 716-2.07. Steel piles and pile shells that do not protrude above the final ground line do not require galvanizing.

505-3.02 EQUIPMENT AND PLAN FOR DRIVING PILES. Use impact hammers to drive piles and to determine resistance during pile driving. Vibratory hammers may be used to drive piles, except vibratory hammers may be used only for initial placement of test piles up to a penetration of 15 feet. If a vibratory hammer is used, use an impact hammer to determine pile resistance by driving the pile an additional penetration of at least 5 feet. Use pile driver leads that allow the hammer to move freely. The use of a follower to drive piles shall be allowed only if approved by the Engineer.

The pile driving hammer and associated equipment shall be sized such that the piles can be driven to the required ultimate bearing capacity without damage to the piles and have compressive driving stresses as indicated by the wave equation analysis, or high strain dynamic testing not exceeding 90 percent of the pile yield stress.

Approval of the pile driving hammer shall be based on a wave equation analysis and a properly operating pile driving hammer.  Approval of a pile hammer shall not relieve the Contractor of responsibility for piles damaged from misalignment of leads, failure of cap block or cushion materials, failures of splices, malfunctioning of the pile hammer or other improper construction methods.

Fit the pile driving hammer with a helmet that is recommended in the hammer manufacturer’s guidelines, is compatible with the pile, and aligns concentrically and fits closely with the top of the pile.

Equip pile driving hammers and associated driving systems with an appropriate thickness of hammer cushion to prevent damage to the hammer and the pile and to ensure uniform driving performance. Inspect the hammer cushion in the presence of the Engineer prior to beginning pile driving and after each 60 hours of pile driving with a particular hammer cushion. Replace any hammer cushion with a reduction in thickness exceeding 25 percent of the original hammer cushion thickness. Do not use wood, wire rope, or asbestos hammer cushions.

Support piles in line and position with leads while being driven.  Construct pile driver leads in a manner that affords freedom of movement of the hammer while maintaining alignment of the hammer and the pile to ensure concentric impact for each blow.  Leads may be either fixed or swinging type as the project site, structure, and conditions demand.  When used, fit swinging leads with a pile gate at the bottom of the leads.  The pile being driven shall not extend above the leads.  Adequately embed the leads in the ground or constrain the pile in a structural frame such as a template to maintain horizontal and vertical alignment.  The leads shall be of sufficient length to make the use of a follower unnecessary.

No less than 30 days prior to the anticipated start of pile driving, submit for approval a pile driving plan. Include in the pile driving plan:

1.	A completed Pile Driving Equipment Data form (Form 25D-098).

2.	Manufacturer’s catalog cuts, specifications, manuals, guidelines, and technical bulletins for all pile driving and prebore equipment to be used.

3.	A description of the techniques to be used for ensuring proper placement and alignment of the piles, obtaining the Driving Resistance, and advancing the piles to the Estimated Pile Tip Elevation.

4.	Alternate methods of prebore in the event obstructions are encountered.

The Engineer will base approval of the pile driving plan on a Wave Equation Analysis of the hammer-pile-soil system, performed by the Department, and the requirements in this Subsection. The Department will perform the Wave Equation Analysis using the computer program “GRLWEAP” and GRLWEAP industry standard hammer input data in addition to the Contractor furnished hammer information from Form 25D-098 to determine the suitability of the pile driving equipment and verify compressive stress limits are not exceeded.

Approval by the Engineer of the pile driving plan will not relieve the Contractor of responsibility for piles damaged during pile driving operations. Do not mobilize pile installation and driving equipment to the site without an approved pile driving plan.

Submit all revisions to the approved pile driving plan to the Engineer for approval. For all pile driving equipment not previously identified in the pile driving plan, include in the submittal all of the information required above for the pile driving plan. Explain to the Engineer, in writing, which portions of the approved pile driving plan will be superseded by the revision and which portions remain unchanged. Allow at least 5 days for the Engineer’s approval of pile driving plan revisions.

Use only equipment included in the pile driving plan. The Engineer will inspect the pile driving equipment for conformance with the approved pile driving plan after it has been mobilized to the site and prior to beginning pile driving operations. Remove and replace pile driving equipment found out of conformance with the approved pile driving plan at no extra cost to the Department and with no adjustment to contract time.

505-3.03 PILE TESTING AND PILE DRIVING CRITERIA. The Engineer will use one or more of the following to set criteria to monitor pile driving performance and the resistance of the pile during driving. The Engineer will also perform pile testing to confirm hammer-system efficiency, pile driving stresses and pile integrity. Attend a meeting with the Engineer at least 14 days prior to the beginning of pile driving operations to evaluate and discuss the test pile program. Give the Engineer 7 days advance notice before driving each test pile.

1.	Wave Equation Analysis. The Engineer will provide pile driving criteria based on a Wave Equation Analysis. The Wave Equation Analysis computer program to be used will be the "GRLWEAP" program using the GRLWEAP industry standard hammer input data in addition to the Contractor furnished information from Form 25D-098.

2.	High-Strain Dynamic Testing. The Engineer will perform high-strain dynamic testing at locations noted on the Plans and at other sites if, in the opinion of the Engineer, the performance of the hammer-pile-soil system changes from that of the original Wave Equation Analysis or the test pile program. The Engineer will perform the high-strain dynamic testing in accordance with the latest version of ASTM D 4945. Piles tested using high-strain dynamic testing may be incorporated into the work.

The Engineer will test the first pile driven at each substructure unit designated for pile testing. Do not drive any production piles, except the test pile, at the substructure unit until the test pile has been installed to the Driving Resistance and the Penetration specified in the Contract documents. The Engineer will require 4 hours at each test pile to set up and install the test equipment. The Engineer will attach testing instruments near the top of the test pile through drilled and threaded holes. The Department will furnish the testing equipment and labor necessary to mount the testing instruments to the pile. Provide a reasonable and safe means of access to the top of the test pile after the pile is placed in the leads. Furnish electrical power (a 115 volt, 55-60 cycle AC outlet, 10 amp minimum) for the Engineer’s use during the installation and operation of the testing instruments.

Drive each test pile to the driving resistance and penetration specified in the Contract documents as indicated by the Wave Equation Analysis. The Engineer will record driving data for the test pile. If an obstruction is encountered during driving of the test pile, testing will stop on that pile and the next pile driven at the substructure unit will be designated as a test pile.

The Engineer shall evaluate each test pile by re-striking the test pile a minimum of 48 hours after completion of the end of drive (EOD) of the test pile to the specified pile tip elevation.  The re-strike of the test piles shall be performed by the Contractor with simultaneous high strain dynamic testing performed by the Engineer.The re-strike testing shall be performed with a warmed up hammer the energy or fuel setting adjusted to the maximum position and the procedure shall consist of striking the test pile with 60 consecutive blows or until the pile penetrates an additional 3 inches, whichever comes first.  In the event the piles downward movement less than 1 inch during the re-strike, the re-strike test may be terminated after 25 blows.

If the results from the high-strain dynamic testing are acceptable to the Engineer, drive the remaining piles at the substructure unit. Otherwise, drive the remaining piles at the substructure unit using criteria set by the Engineer and based on the results of the high-strain dynamic testing.

Account for the entire allotted equipment installation time and restrike suspension time required by the Engineer in the progress schedule submitted under Subsection 108-1.03 or Section 646, as applicable. Suspension of pile driving operations at a testing location to allow for testing instrument installation or a re-strike of a test pile is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

505-3.04 DRIVING PILES. Drive all piles to the Driving Resistance and Minimum Penetration specified in the Contract documents using the pile driving criteria provided by the Engineer. Use the same pile driving system used to set pile driving criteria to drive all piles. Install piles in groups starting from the center of the group and proceed outward in either direction.

If the pile is driven to the Estimated Pile Tip Elevation and does not achieve the Driving Resistance, continue driving the pile to a penetration established by the written direction of the Engineer.

For each pile to be installed at this site, provide prebored hole to an elevation ten feet above the specified estimated pile tip elevation.  Drive the piles with an impact hammer from the bottom of the prebored hole to the estimated tip elevation.  Start the final drive in the center of the pile group and then proceed outward in either direction.

Provide prebore excavation and drilling equipment that has adequate capacity to excavate the required diameter and depth through the very dense soils, rocks, cobbles and boulders.  The required diameter of the finished prebored holes shall be about equal to the diagonal of the H Piles.  Maintain a stable open prebored hole until the pile has been installed and advanced to the bottom of the prebored hole.  Control sloughing, caving, water intrusion, water erosion effects, excess water, unstable layers, or deleterious material entering the prebore hole by using temporary casing.  Material resulting from drilling the prebored holes may be reintroduced back into the bore hole or shall be disposed of as approved by the Engineer.  If additional material is required to backfill the holes, use Selected Material, Type A having a maximum particle size of 3-inches or less.

1.	Driving Through New Embankment. When driving piles through new embankment and the depth of the embankment at the pile location is in excess of 5 feet, drive the pile in a prebored hole made through the embankment. Make the prebored hole diameter 6 inches greater than the pile. After driving the pile, fill the annular space around the pile with sand meeting Subsection 703-2.12.

2.	Placement and Alignment. Ensure proper placement and alignment of the piles. The Engineer will reject piles that are bent or otherwise damaged by forcing the pile into the leads template or position.

Drive piles within an allowed variation as to direction of pile of not more than 1/4 inch per foot. Limit the rotation of steel piles about their longitudinal axis to 15 degrees from the plan position. In addition, position piles to the following tolerances:

a.	Abutments. Position the piles at the bottom of an abutment within 3 inches of the position specified in the Contract documents. Do not vary the distance between any two piles more than 3 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 6 inches.

b.	Pier Footings. Position the piles at the bottom of a footing within 6 inches of the position specified in the Contract documents. Do not vary the distance between any 2 piles more than 6 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches.

c.	Exposed Pile Piers. Position the piles within 2 inches of the position specified in the Contract documents at cut-off elevation and within 3 inches of the position specified in the Contract documents at the original ground line elevation.

3	Protection of New Concrete. To minimize the detrimental effects of pile driving vibrations on new concrete less than 28 days old, do not drive piles closer to the new concrete than the distance determined by the following formula:

Where:	D = Distance in feet

E = Maximum rated hammer energy in foot-pounds

C = Vibration coefficient shown in Table 505-1 based on the number of calendar days after concrete placement

Where:	D = Distance in feet

E = Maximum rated hammer energy in foot-pounds

C = Vibration coefficient shown in Table 505-1 based on the number of calendar days after concrete placement

TABLE 505-1

VIBRATION COEFFICIENT

| Concrete Age | Coefficient |
| --- | --- |
| (days) |  |
| 1 | 0.34 |
| 2 | 0.23 |
| 3 | 0.18 |
| 4 | 0.15 |
| 5 | 0.13 |
| 6 | 0.12 |
| 7-9 | 0.11 |
| 10-13 | 0.10 |
| 14-20 | 0.09 |
| 21-28 | 0.08 |

4.	Obstructions. Use alternate methods to drive through or remove obstructions. Obtain written approval from the Engineer before employing any alternative methods of pile advancement.

After exhausting all practicable means to obtain the minimum penetration, but without success, the Engineer will evaluate the structural adequacy of the bridge at a lesser penetration. This review will be based on the resistance of the pile during driving. If the Engineer finds the structure to be adequate, the pile will be accepted at the lesser pile penetration.

5.	Concrete Filled Pipe Piles. After driving pile, clean out the pile to the bottom of concrete elevation specified in the Contract documents. If there is a delay between cleanout and placing concrete, verify that the soil level in the pile has not rebounded before placing concrete.

505-3.05 SPLICES, EXTENSIONS AND BUILD-UPS. If the length of a steel pile is not sufficient to obtain the Estimated Pile Tip Elevation and Driving Resistance specified in the Contract documents, the pile may be spliced in order to obtain the length required to reach the Minimum Penetration and Driving Resistance. Use additions with cross sections identical to the pile cross sections.

Do not deviate the alignment of piles at a splice more than 1/4 inch per ten foot length.

Make splices with complete penetration butt welds over the entire cross section. If approved, piles may be spliced using pile cut-offs and short pieces if no piece used is less than 10 feet long.

Meet the welding requirements of Section 504.

505-3.06 DEFECTIVE PILES. Use a pile driving method which does not damage the pile. Do not manipulate the piles to force them into proper position. Correct damaged or improperly driven piles using a method approved by the Engineer. Approved methods may include one of the following:

1.	Withdraw and replace the pile with a new and, when necessary, longer pile.

2.	Drive a second pile adjacent to the defective pile.

3.	Splice or build up the pile.

4.	Extend a sufficient portion of the footing to properly embed the pile.

505-3.07 CUTTING OFF PILES. Cut off the piles at the elevations indicated on the Plans. Ensure that all injured material is removed.

When steel piles are shown embedded in concrete footings or pile caps, cut off piles within -1/2 inch to +3 inches of the plan embedment, but do not interfere with reinforcing steel or other items embedded in concrete. When steel pipe piles are shown cutoff below concrete footings or pile caps, cut off piles within -1/2 inch to +1/2 inch of the plan elevation. In pile bents with steel cap beams, make accurate cut-offs to ensure full bearing between the caps and piles.

505-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Furnish Piles. The sum of the lengths of the piles in place in the completed structure, measured along the centerline of piles from the tip of pile to the cut-off elevation.

Drive Piles. The number of piles in place in the completed structure.

Pile Restrike. Calendar Day: Every day shown on the calendar, beginning and ending at midnight. Measurement begins on the day pile driving operations are ceased at a substructure unit to allow a restrike directed by the Engineer and ends on the day the Engineer authorizes pile driving operations to be resumed.

Sheet Piles.  The projected area of furnished and driven sheet piles remaining in place in the permanent structure as called for on the Plans, measured in final position.

Prebore.  The number of piles in place in the completed structure.

505-5.01 BASIS OF PAYMENT.

Furnish Piles. The contract price includes pile materials delivered to the site, pile shoes, reinforced tips and casing. Unused pile lengths removed by cut-offs and fresh heading are subsidiary. The payment amount will be calculated using the quantity of pile indicated on the bid schedule, or the quantity of installed piles, whichever is greater.

Drive Piles. The contract price includes:

1.	All related work required to drive the piles including: pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items incurred during pile driving, fresh heading, splicing, pile cleanout and cutting off.

2.	All related work required to construct preformed pile holes in locations identified in the Contract and sand backfill material.

3.	All related work required to assist the Engineer in performing High Strain Dynamic Testing is subsidiary.

Pile Driving Equipment. The contract price includes pile driving equipment movements and the construction of templates and work platforms.

Sheet Piles.  Sheet piles used as temporary shoring for excavation, whether removed or left in place at your option with permission of the Engineer, are subsidiary.

Pile Restrike. The contract price includes all pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items that occur during suspension of pile driving operations. Pile Restrike is not subject to the compensation for altered quantities provisions of Subsection 109-1.04.

Obstruction Removal. Alternate methods of pile advancement through obstructions performed at the direction of the Engineer will be paid according to Subsection 104-1.02.

Prebore.  The contract price includes all equipment, materials and labor to prebore holes to the specified depth and backfill the annulus of the installed piles.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

505(5)	Furnish Structural Steel Piles (HP14X117)	Linear Foot

505(6)	Drive Structural Steel Piles (HP14X117)	Each

505(7)	Pile Driving Equipment	Lump Sum

505(9)	Structural Steel Sheet Piles	Square Foot

505(11)	Pile Restrike	Day

505(12)	Pre Bore	Each

Replace Section 507 with the following:

Section 507
Bridge Railing

507-1.01 DESCRIPTION. Construct concrete, timber, or steel bridge railing, pedestrian railing and safety railing as shown on the Plans. Furnish and install bridge number plates as shown on the Plans.

507-2.01 MATERIALS. Use materials that conform to the following:

Steel Railing	Section 722

Timber Railing	Section 506

Concrete	Section 501

Reinforcing Bars	Section 709

Grout	Section 701

Cable	Use ¼ inch galvanized wire rope with a

minimum breaking force of 7,000

pounds.

507-3.01 CONSTRUCTION REQUIREMENTS.

1.	General. Construct railing to the line and grade shown on the Plans. Ensure that the rail does not reflect any unevenness of the bridge structure. Set rail posts plumb. Place railing after all falsework is removed and the span is self-supporting. Do not paint bridge railing.

Furnish and install concrete curbing, associated reinforcing steel, and the approach rail transition bracket for steel bridge railing.

2.	Steel. Erect steel railing in conformance with Section 504, except do not use load indicating washers.  Weld in conformance with Section 504. Complete welding before galvanizing.

3.	Timber. Fabricate and install timber railing in conformance with Section 506.

4.	Concrete. Construct concrete rail to meet applicable requirements of Sections 501 and 503. Base concrete mix design on Class A, except use a minimum 28-day compressive strength of 3000 psi. Apply a rubbed finish to exposed surfaces of concrete.

507-4.01 METHOD OF MEASUREMENT. Section 109.

507-5.01 BASIS OF PAYMENT. The contract price includes all rail elements, rail posts, brackets, spacers, fastenings and anchors required to attach the railing to the structure; concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section or within the limits of the concrete curb for the steel bridge rail section; and bridge number plates.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

507(1)	Steel Bridge Railing 	Linear Foot

507(2)	Pedestrian Railing	Linear Foot

507(3)	Thrie Beam Bridge Railing	Linear Foot

507(4)	Concrete Bridge Railing	Linear Foot

507(5)	Timber Bridge Railing	Linear Foot

507(6)	Safety Railing	Linear Foot

Section 603
Culverts and Storm Drains

Special Provisions

603-1.01 DESCRIPTION. Add the following:

This work shall also consist of installing culvert marker posts.

Delete the second paragraph and substitute the following:

When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe. Corrugated Polyethylene Pipe is not allowed. End Sections for Metal Pipe must be of the same material as the pipe.

Add the following: Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts. The color shall be blue with no other markings. The 2.5 inch by 6 foot post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

- Add the following subsection:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. Forty-two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Delete the second paragraph and replace with the following: Excavation, bedding, and backfill are subsidiary to the 603(17-xx) Pipe pay items.

Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(08/27/03)R42

Section 604
Manholes and Inlets

Special Provisions

Delete Items 604(1) Storm Sewer Manhole

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

604(1B)	Storm Sewer Manhole, Type II	Each

Section 606
Guardrail

Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an overall length of 72 inches. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel. The flexible marker shall have an orange HDPE flag which provides approximately 20 square inches of surface area. Use stainless or galvanized steel attaching hardware. The following is an example of an acceptable flexible marker:

- Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

(04/06/06)R45

606-3.01 GENERAL. Replace the second sentence of the first paragraph with the following: Conform to these Specifications and the Standard Drawings with the following exception. Modify Standard Drawing G-20.10 to only allow an offset of 1.5 feet for the ET-2000.

(05/12/04)R266

606-3.02 POSTS. Delete the first two numbered items in this subsection and substitute the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 14 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

(04/06/06)R45

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Delete the last sentence and substitute the following: Notify the Engineer a minimum of 5 days before removing guardrail for disposal. The Engineer will notify ADOT&PF M&O (907-338-1466) and have a M&O representative physically identify portions of guardrail to be salvaged. Deliver guardrail and associated hardware designated for salvage to the ADOT&PF M&O yard located at 5300 East Tudor Road. Remaining items removed becomes the Contractor’s property.

(06/12/03)R259

- Add the following subsections:

606-3.09 FLEXIBLE MARKERS. For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION. After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

(04/06/06)R45

Section 608
Sidewalks

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work also consists of constructing asphalt pathway(s) and median(s) to conform to the Plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

- 2. Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG52-28	Subsection 702-2.01
Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, pounds, min.	1,000
Percent Voids, Total Mix	2-5
Compaction, Blows/side	50

(05/22/07)R47

608-3.02 ASPHALT SIDEWALKS. Add the following:

Asphalt Pathway will be accepted for payment based on the Engineer's approval of a Job Mix Design (JMD) and the placement and compaction of the Asphalt Pathway to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any Asphalt Pathway that does not conform to the approved JMD.

- Add new subsection:

608-3.04 DETECTABLE WARNING TILES. Construct detectable warning tiles according to the details and the locations shown on the Plans.

Install cast in place tactile tiles integral with construction of concrete curb ramps. Install tile so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch. Align pattern on a square grid in the predominant direction of travel. Install Detectable warnings that are made of composite materials, safety yellow color, slip resistant with truncated dome pattern.

When detectable warning tiles are required for uncurbed asphalt pathway to road way intersections, install Top Mark or approved equal heat activated glue down 12” x 24” panels according to the manufacturer’s instructions full width of the path.

Furnish and install detectable warning tiles according to the Americans with Disabilities Act Accessible Guideline.

- Special Provisions

Add the following subsection:

608-3.05 ASPHALT PATHWAY. Construct asphalt pathway according to subsection 608-3.02, Asphalt Sidewalks.

(05/22/07)R47

- Special Provisions

608-4.01 METHOD OF MEASUREMENT. Add the following:

Asphalt Pathway. By the ton of asphalt concrete according to Section 109, Measurement and Payment. Asphalt cement will not be measured for payment.

(01/24/07)R47

Detectable Warning Tiles. Will be measured by the square foot complete in place.

608-5.01 BASIS OF PAYMENT. Add the following:

Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to Item 608(7) Asphalt Pathway.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

(05/22/07)R47

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

608(7)	Asphalt Pathway	Ton

608(10)	Detectable Warning Tiles	Square Foot

Section 611
Riprap

Special Provision

611-2.01 MATERIALS. Add the following after the first sentence: Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.

R277 (11/07/05)

Section 615
Standard Signs

Standard Modification

615-2.01 MATERIALS.

- Delete the first paragraph of Item 2, including subitems a., b., c., and replace with:

2.	Sign Fabrication. Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs. Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

For temporary installations the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

For flexible signs (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use Type IX reflective sheeting for legends and background. Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow-Green School Area Signs: Use Type VIII or Type IX reflective sheeting for background.

- Add the following paragraph:

Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor 	YF: 20%

Minimum Total Luminance Factor		YT: 35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

R615(06/17/08)

615-3.01 CONSTRUCTION REQUIREMENTS.

- Add the following to Item 7. after the first paragraph:

Contractor will deliver signs identified for salvage to the ADOT M&O Station at 5300 E. Tudor Road.

Section 616
Thaw Pipe and Thaw Wires

Standard Modifications

616-2.01 THAW PIPE.  Second sentence delete:  “and Fittings”

Add the following sentence:  Fittings 	ASTM A 234 galvanized according to AASHTO M 111.

E14(6/30/04)

Section 618
Seeding

Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed new or disturbed slopes and other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil according to Section 620. Complete slope preparation as soon as topsoil is placed on the slopes.

(01/27/07)R52

Standard Modification

- Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope. Use one or more of the following grooving methods prior to the application of seed:

1.	Manual raking with landscaping rakes;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS. Add the following: Seed disturbed areas that require seeding within 14 days of the permanent cessation of ground disturbing activities in that area.

Apply Seeding, Schedule A between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.  Apply Seeding, Schedule B between May 15 and August 1, or obtain written approval from the Engineer to seed at a different date.

618-3.03 APPLICATION. Delete the first three sentences and replace with: Apply seed mix, fertilizer, and mulch (if required) at the rate specified in the Special Provisions. If no seed mix, seed mix application rate, or fertilizer rate are specified in the special provisions, use the recommendations of the Alaska Department of Natural Resources (ADNR) and the Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated on the plans as “no seeding”.

Water and fertilizer required for application are subsidiary to the Seeding bid item.

E42(01/27/07)

- Special Provision

Add the following: Apply seed, mulch, and fertilizer as follows per MSF. Apply seed and mulch in one application if using the hydraulic method. Apply fertilizer with the hydraulic method.

Seeding, Schedule A:

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Seeding, Schedule B:

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Hairgrass (Norcoast or Nortran) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.75 lbs. 0.20 lbs. 0.05 lbs. Total = 1.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable. If this substitution is made, at the same application rate.

(01/27/07)R52

Standard Modification

- Delete subsection 618-3.04 in its entirety, and add the following new subsections:

618-3.04 MAINTENANCE AND WATERING. Protect seeded areas against traffic by approved warning signs or barricades. Repair surfaces gullied or otherwise damaged following seeding. Maintain seeded areas in a satisfactory condition until final acceptance of work.

Water and maintain seeded areas.  Water applied by this subsection is a paid Contract item. If, in the opinion of the Engineer, too much water is being applied, reduce amount of water as directed.

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding. Bare patches of soil more than 10 square feet in area must be reseeded. Erosion gullies over 4 inches deep must be filled and reseeded. Fill the entire erosion gully to surrounding grade, even the portions less than 4 inches deep.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for retracking, reseeding, refertilizing and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE. During final inspection the Engineer will perform a visual inspection of seeding to determine final stabilization. During the visual inspection each station and each side of the road will be considered a separate area. The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-3.06 PERIOD OF ESTABLISHMENT. Establishment periods extend for one complete growing season following acceptable seeding. Employ possible means to preserve the new vegetative matt in a healthy and vigorous condition to ensure successful establishment. Reseed areas that do not meet the specifications. Watering and reseeding after the final inspection are subsidiary.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance. After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with subsection 105-1.16.

618-4.01 METHOD OF MEASUREMENT. After Seeding by the Pound, delete text and replace with: By the weight of dry seed acceptably seeded and maintained.

618-5.01 BASIS OF PAYMENT. Delete paragraphs beginning: “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre. Payment is for established vegetative matt. Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Seeding by the Pound. Payment is for established vegetative matt. Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Add new pay description:

Water for Seeding. Water applied for growth of vegetative matt. Water for hydraulic seeding, fertilizing or mulching is subsidiary. Water after project completion is subsidiary.

E42(01/27/07)

Special Provisions

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

618(2A)	Seeding, Schedule A	Pound

618(2B)	Seeding, Schedule B	Pound

Add the following Section:

Section 622
Interpretive Kiosk

Special Provision

622-1.01 DESCRIPTION. This work shall consist of furnishing, constructing and placing an interpretive kiosk in conformance with the plans and Special Provisions.

622-1.02 APPLICABLE ACCESSIBILITY STANDARD.  Americans with Disabilities Act (ADA) Accessibility Guidelines for Buildings and Facilities.

622-1.03 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

MATERIALS

622-2.01 GENERAL.  All materials shall be new and conform to the details shown on the plans or as specified.

622-2.02 BACKFILL.  Selected Material, Type A conforming to Subsection 703-2.07.

622-2.03 CONCRETE.  5-Sack and 6-Sack Concrete conforming to Section 501.

622-2.04 GALVANIZING.  Conform to AASHTO M111/ASTM A123 (Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products), or AASHTO M232/ASTM A153 (Standard Specification for Zinc Coating[Hot-Dip] on Iron and Steel Hardware). Repair damaged galvanizing by using low melting point zinc repair rods in conformance with ASTM A780-00 (Standard Practice for Repair of Damaged and Uncoated Areas of Hot-Dip Galvanized Coatings).

622-2.05 LUMBER.  Conform to Section 713.  Wood species shall be Douglas Fir or Hem-fir unless otherwise specified.

1.	Dimensional.  Dimensional lumber and timbers are shown on the plans in nominal dimensions, i.e.; 2x4, indicating surfaced four sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Use classification for structural joists and planks shall be No. 2 Grade or Better.  Manufacturing classification shall be Dressed (Surfaced) Lumber. Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

622-2.06 TREATED LUMBER.  Wood species conforms to Subsection 622-2.06.

Treatment shall be as follows:

1.	Above Ground Applications. Preservative pressure treatment shall conform to Section 714.  Pressure treat with preservative Ammonical Copper Quat - Type A,B,C, or D(ACQ-A,B,C, or D) or Copper Azole – Type A (CBA-A).  Minimum retention shall be 0.40 pounds per cubic foot or to refusal. Treated materials shall be uniformly brown in color and nonincised.  This type of treated lumber is commonly used for residential decks for above ground applications.   Incising may be used on 4x and thicker material to obtain minimum retention.

2.	Ground Contact Applications. Preservative pressure treatment shall conform to Section 714.  Pressure treat with preservative Ammonical Copper Quat - Type A,B,C, or D(ACQ-A,B,C, or D) or Copper Azole – Type A (CBA-A).  Minimum retention shall be 0.60 pounds per cubic foot.    Exposed treated materials shall be pigmented uniformly brown in color by manufacturer.

622-2.07 TREATED PLYWOOD.  Preservative-treated plywood shall be pressure-treated in accordance with AWPA Standard U1 with oxine copper preservatives as required for above ground exposure. Preservative-treated plywood shall be all-veneer APA RATED SHEATHING EXP 1 marked Custom Product or APA Custom Product V-600, or EXT marked Custom Product or APA Custom Product V-611.

Preservative-treated plywood shall be marked by an approved inspection agency certified to inspect preservative-treated wood, indicating compliance with the treating, drying, retention and penetration requirements of applicable AWPA Standards or equivalent code-approved preservative-treating and quality control requirements.

622-2.08 ROOFING SYSTEM.

Leak Barrier. Self-adhering, self sealing, bituminous leak barrier surfaced with a smooth polyethylene film.

Shingles. Self sealing, granule surfaced, architectural style asphalt shingle with a fiberglass reinforced core with a 5” or 5 5/8” exposure.  UL 790 Class A rated with UL 997 Wind Resistance Label;  ASTM D 7158, Class H; ASTM D 3161, Type 1; ASTM D 3018, Type 1;  ASTM D 3462. A minimum 30 yr Ltd Warranty product shall be used.

622-2.9 FASTENERS.  Commercial quality and type of nails and screws as required to securely hold all members in place in accordance with National Design Specifications (NDS).  Nails shall be hot dipped galvanized.  All other fasteners shall be corrosion resistant.  Fasteners in pressure treated wood shall be stainless steel unless otherwise noted in the plan set.

622-2.10 PAINT.  Unless otherwise specified, use the following paint types and colors, or approved equals:

1.	Semi-Transparent Oil Stain.  Exterior alkyd based stain, color to match solid oil stain “Russet”.  Stains for pressure treated wood shall be recommended by manufacturer for use on pressure treated wood.

2.	Concrete Sealer.  Clear acrylic copolymer conforming to AASHTO M148/ASTM C 309 (Standard Specification for Liquid Membrane-Forming Compounds for Curing Concrete, for Type 1 Compounds).

3.	Above Ground Wood Preservative.  Brown preservative with active ingredient of minimum 9.08 percent copper naphthenate (equivalent to minimum 1 percent metallic copper).  Color to be approved by Engineer.

4.	Below Ground Wood Preservative. Preservative with active ingredient of minimum 16 percent copper naphthenate (equivalent to minimum 2 percent metallic copper).

5.	End Cut Preservative for Treated Wood.  Brown preservative with active ingredient of minimum 10 percent copper naphthenate (equivalent to minimum 1 percent metallic copper).  Color to match preservative pressure treatment color.

6.	Paint that has been frozen or is out of date shall be replaced at no additional cost to the Department.

622-2.11 INTERPRETIVE KIOSK.  Conform to Plans.  Interpretation board frame shall be surfaced four-sides clear cedar.

CONSTRUCTION REQUIREMENTS

622-3.01 GENERAL. The location shown on the drawings for park facilities placement are approximate.  The Engineer will field locate park facilities at the time of construction.

622-3.02 EXCAVATION AND BACKFILL.  Conform to the requirements of Section 204 and the details on the plans.

622-3.03 CONCRETE.  Conform to the requirements of Section 501 and the details on the plans.

622-3.04 WOOD.  Competent carpenters shall be employed and all framing shall be true and exact.  Unless otherwise specified, nails and spikes shall be hand driven with just sufficient force to set the heads flush with the surface of wood.  Power nail guns are prohibited.  All non-removable shipping, storage, weathering and erection marks on fabricated lumber shall be hidden from view in the completed work.  Use of damaged lumber shall not be allowed.  Store on-site lumber above the ground and protected from damage and weathering.

Holes for round drift-bolts and dowels shall be bored with a bit 1/16 inch smaller in diameter than that of the bolt or dowel used.  Holes for machine and carriage bolts shall be bored with a bit of the same diameter as that of the bolt.  Holes for lag screws shall be bored with a bit not larger than the body of the screw at the root of the thread.

Unless otherwise specified, USS flat washers shall be used in contact with all bolt heads and nuts that would otherwise be in contact with wood.

622-3.05 PAINT.  Deliver in sealed containers with labels legible and intact.  Remove dirt, grease, oil and other construction debris prior to painting.  Ensure that surfaces to be painted are even, smooth, sound, clean, dry, and free from defects affecting proper application.  Metal surfaces to receive paint shall be corrosion free. Apply per manufacturer's recommendations.  Apply paint material evenly without runs, sags, or other defects.  Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer.  Cover surfaces completely to provide uniform color and appearance.  Remove all paint, stain, or other finish material where it has spilled or spattered.

1.	General.  Unless otherwise specified, schedule finishes as follows:

a.	Non-Treated Wood, Surfaced.  Finish surfaces with semi-transparent oil stain in accordance with manufactures directions.

b.	Non-Treated Wood, Rough Cut.  Saturate below and above ground surfaces not scheduled to receive stain with wood preservative.

c.	Treated Wood, Hidden.  Dado cuts, cut ends, drilled holes and field cuts in wood materials shall be brush coated to saturation with end cut preservative.

d.	Treated Wood, Exposed.  Saturate cut surfaces with scheduled finish. Finish surfaces not scheduled to receive stain with wood preservative.

e.	Concrete and Masonry.  Seal exposed surfaces.

f.	Metal.  Prime and paint exposed metal surfaces that are not fabricated of corrosion resistant material or galvanized.

2.	Interpretive Kiosk.

a.	Interpretation Board Frame and Exposed T&G Wood.  Clear Oil Stain

b.	Other Wood.  Semi-Transparent Oil Stain

c.	Metal.  Primer and Enamel Paint

d.	Bulletin Board Sound Board.  Off White Flat Latex Paint

622-3.06 INTERPRETIVE KIOSK.  Construct in accordance with Plans.

622-4.01 METHOD OF MEASUREMENT.  Kiosks with the unit measure each will be measured by the actual number of facilities completed and accepted.

Excavation and embankment for kiosks outside the limits shown on the plans will be measured for pay¬ment only if directed by the Engineer.  Excava¬tion and backfill required for items paid for under this Section will not be measured for payment.

622-5.01 BASIS OF PAYMENT.  The accepted quantity of kiosks will be paid for at the contract unit price per unit of measurement for the type specified completed in place, and listed below excluding all clearing, grubbing, topsoil and crushed aggregate base course, which shall be paid for separately at contract unit prices.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

622(16)	Interpretive Kiosk	Each

- Delete this Section in its entirety and substitute the following:

Section 639
Approaches

Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed.

639-5.01 BASIS OF PAYMENT. At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Pavement removal, excavation, and materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to Item 639(6) Approach.

(05/09/02)R58

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approach	Each

Delete Section 641 in its entirety and substitute the following:

Special Provision

Section 641
Erosion, Sediment, And Pollution Control

641-1.01 DESCRIPTION. As approved by the Engineer, providerovide project administration and construction activities to control erosion, sedimentation, and pollution from the Project, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.  These definitions apply only to Section 641.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). Certification documenting the person has completed training, testing, and other requirements recognized by the Department to satisfy the APDES Construction General Permit requirement for “qualified personnel.”  AK-CESCL certificates issued in conformance with, and under the authority of the AK-CESCL Memorandum of Understanding are recognized by the Department as meeting this standard.  Certifications published on the Department’s Construction website under the title “AK-CESCL Equivalent Certifications” will also be recognized.  Other certifications may be approved by the Engineer on a case-by-case basis.

Alaska Department of Environmental Conservation (ADEC).  The state department that has been authorized to administer the Clean Water Act’s National Pollutand Discharge Elimination System in a phased process.

Alaska Pollutant Discharge Elimination System (APDES).  The Alaska Pollutant Discharge Elimination System, administered by ADEC.

Area of Land Disturbance.  The area of land (soil) that will be disturbed by Construction Activity.  Area of Land disturbance does not include pavement removal or pavement milling if the activity does not remove the aggregate underlying the pavement.

Best Management Practices (BMPs).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or reduce the discharge of pollutants to waters of the United States.  BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leads, sludge or waste disposal.

Clean Water Act (CWA).  United States Federal Water Pollution Control Act (33 U.S.C. 1251 et seq.)

Construction Activity. Physical activity by the Contractor or any Subcontractor or Utility Company  that may result in land disturbance. Construction Activity includes, but is not limited to, clearing, grubbing, excavating, constructing embankment, grading, stockpiling erodible material, processing material, and installation or maintenance of BMPs.

Construction General Permit (CGP). The Alaska Pollutant Discharge Elimination System General Permit for Discharges from Large and Small Construction Activities.

Certified Professional in Erosion and Sediment Control (CPESC).  A recognized specialist in soil erosion and sediment control.  CPESCs have educational training, demonstrated expertise, experience in controlling erosion and sedimentation, and meet certification standards.

Department Furnished Disposal Site.  Areas designated in the Contract for disposal of unsuitable materials.

Department Furnished Haul Route.  Areas designated in the Contract for construction, reconstruction, or rehabilitation of the roadway, or areas designated in the Contract for temporary use as transport route for material or equipment related to the Project.

Department Furnished Materials Site.  A material site identified in the Contract as a “Mandatory Source”, or excavated portions within the Project limits where useable material is excavated for use as fill, embankment, or cover in other areas of the Project.  A material site identified in the Contract as “Designated Source” is considered a Department Furnished Materials Site if the Contract defines the Department as co-operator for the site.  Material sites identified in the Contract as “Available Sources” are not considered Department Furnished for the purpose of defining who has operational control.

Department Furnished Staging and Equipment Areas.  Areas designated in the Contract for storage or staging of material or equipment related to the Project.

Electronic Notice of Intent (eNOI). The Electronic Notice of Intent submitted to ADEC, to begin Construction Activity under the CGP.

Environmental Protection Agency (EPA).  The United States Environmental Protection Agency.

Erosion and Sediment Control Plan (ESCP). A project-specific document prepared by the Department to identify specific information about the Project.  The ESCP may include measures to minimize erosion and contain sediment within the Project site.  The ESCP provides information for the Contractor’s use in developing the Project SWPPP.

Final Stabilization. Soil disturbing activities at the site have been completed and one of the following methods, as identified in the contract, has been completed:

- establish a uniform and evenly distributed perennial vegetative cover with a density of 70 percent of the native background vegetative cover, or

- construct non-erodible permanent stabilization measures (such as riprap, gabions, geotextiles, pavement, or crushed aggregate base course) where vegetative cover is not required.

Haul Route.  Existing or newly constructed road where construction materials are transported and where deposition of sediments or erodible materials may result from the material hauling activity or from the Contractors activity to construct or maintain the road.

Hazardous Material Control Plan (HMCP). The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material, including but not limited to, petroleum products related to construction activities and equipment.  The HMCP is included as an appendix to the SWPPP.

Joint Inspection.  SWPPP inspection performed together as a collaborative effort of the Contractor and the Department.  Contractor’s staff performing the inspection must be the Superintendent, SWPPP Manager, or SWPPP Manager’s Representative.  The Department’s staff performing the inspection will be the Engineer or Engineer’s qualified representative.

Multi-Sector General Permit (MSGP).  The Alaska Pollutant Discharge Elimination System General Permit for Storm Water Discharges associated with Industrial Activity.

Operator.  The party associated with a regulated activity that has responsibility to obtain storm water permit coverage.  Operator is defined separately in the storm water general permits (construction and industrial general permits).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR 122.2

Project Area.  The physical limits of the construction site, Department furnished project staging and equipment areas, Department furnished haul routes where deposition of sediments or erodible materials may result from material hauling activities and Department furnished material and disposal sites directly related to the Contract.  The project area also includes all areas of utility relocation and installation, including adjacent utility easements and tie-ins that may extend beyond the defined project limits.  Contractor or Commercial Operator furnished material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas are not included in the Project Area.

Spill Prevention, Control and Countermeasure Plan (SPCC).  The Contractor’s detailed plan for petroleum spill prevention and control measures that meets the requirements of 40 CFR 112.

Spill Response Field Representative.  The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC, and for the Contractor’s compliance with 40 CFR 112, and other applicable federal, state, and local laws and regulations related to hazardous materials.

Stormwater Discharges From Municipal Separate Storm Sewer Systems (MS4s).  A conveyance or system of conveyances including roads with drainage systems, municipal streets, catch basins, curbs, gutters, ditches, man-made channels, or storm drains that discharges into waters of the United States and is owned or operated by a public agency.

Storm Water Pollution Prevention Plan (SWPPP).  The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project site, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but may not be limited to, amendments, records of activities, inspection schedules and reports, qualifications of key personnel, and all other documentation required by the CGP and this specification.

Subcontractor Spill Response Coordinator. The Subcontractor’s representative with authority and responsibility for coordinating the Subcontractor’s activities in compliance with HMCP and SPCC.

Subcontractor SWPPP Coordinator. The Subcontractor’s representative with authority to direct the Subcontractor’s work, and who is responsible for coordination with the SWPPP Manager and for the Subcontractor’s compliance with the SWPPP.

Superintendent.  The Contractor’s authorized representative in responsible charge of the work, who is duly authorized by the Contractor, in accordance with CGP, Appendix G, Part 11, B.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP Amendment.   A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager.   The Contractor’s qualified representative responsible for CGP compliance, implementing the SWPPP, conducting inspections, updating the SWPPP, supervising Section 641 work, monitoring construction activities, and with authority to suspend work and implement corrective actions.

SWPPP Manager’s Representative.   The Contractor’s qualified representative who may be assigned certain SWPPP Manager’s tasks and authorities.

SWPPP Preparer.  The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

SWPPP Template. EPA’s template for the Contractor’s use in developing the SWPPP.  The template is available online at EPA’s website.  Select “SWPPP Template – Unauthorized States”.

Temporary Stabilization. The protection of exposed soils (disturbed land) from wind and water erosion during the construction process, until final stabilization is established.

Utility Company. A Utility Company or their contractor performing work concurrently with the construction of this project as outlined in Section 105-1.06.

Utility Spill Response Coordinator.  The Utility's representative with authority and responsibility for coordinating the utility's activities in compliance with HMCP and SPCC.

Utility SWPPP Coordinator.  The Utility's representative with authority to direct the Utility's work, and who is responsible for coordination with the SWPPP Manager and for the Utility's compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.  Contractor submission and department review deadlines in this section supersede subsection 1.06-1.08 and 108-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline.

1.	SWPPP. Submit three signed copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 calendar days before you plan to begin Construction Activity.  Organize and bind the SWPPP and related documents for submittal according to the requirements of 641-2.01, paragragh 2.

The Department will review the SWPPP submittals within 14 calendar days after they are received. Submittals will be returned to the Contractor, and marked as either requiring modification or as approved by the Department.

2.	HMCP.  Submit three copies of the HMCP as an appendix to the SWPPP, and in accordance with the requirements for submitting the SWPPP.

3.	SPCC. When SPCC is required under subsection 641-2.03, submit three signed copies of the SPCC to the Engineer. Deliver these documents to the Engineer at least 21 calendar days before you plan to begin construction activity.

The Department will keep the SPCC as a record document, and reserves the right to review it and require modifications.

4.	eNOI.  Obtain APDES construction authorization for the Project under the CGP.  APDES authorization and compliance for Contractor furnished and commercial operator furnished areas are the sole responsibility of the Operators.

The Contractor and the Engineer must sign and certify the approved SWPPP in accordance with CGP, Appendix G, before the Contractor submits their eNOI for the Project to ADEC. The certification statement cannot be amended or edited.

Submit an eNOI for the Project to ADEC with the required fee.  Submit three copies of the  eNOI to the Engineer when the eNOI is submitted to ADEC. The Department will submit the Department’s eNOI to the ADEC and provide a copy to the Contractor for inclusion in the SWPPP.  Allow adequate time for state processing of the eNOI, and for the ADEC to list the eNOIs as active status, before beginning Construction Activity.

5.	eNOT.  Within 30 days after the Engineer has determined you may end SWPPP activities for the Project, submit your eNOT for the Project to ADEC and send a copy of the eNOT to the Engineer.  Within 30 days of the Engineer’s determination, the Department will submit the Department’s eNOT to the ADEC, and will terminate the Department’s CGP coverage for the Project and send a copy to the contractor.

6.	ADEC SWPPP Review.  When CGP, Part 10. F requires ADEC SWPPP review; transmit a copy of the Department approved SWPPP with the required fee to ADEC using delivery receipt confirmation.  Transmit a copy of the delivery receipt confirmation to the Engineer within seven (7) calendar days of receiving the confirmation. Transmit a copy of the ADEC SWPPP review letter to the Engineer within seven (7) calendar days of receipt from ADEC.  Amend the SWPPP as necessary to address ADEC comments and transmit a copy of the SWPPP Amendments to the Engineer within seven (7) calendar days of receipt of ADEC review comments.  Include a copy of the ADEC SWPPP review letter in the SWPPP.

7.	Local Government SWPPP Review.  When CGP, Part 10.F requires local government review, transmit a copy of the Department-approved SWPPP with the required fee using delivery receipt confirmation.  Transmit a copy of the delivery receipt confirmation to the Engineer within seven (7) calendar days of receiving the confirmation.  Transmit a copy of any comments by the local government to the Engineer within seven (7) days of receipt.  Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven (7) days of receipt of the comments.

641-1.04 PERSONNEL QUALIFICATIONS.  Include qualifications of the Superintendent, SWPPP Preparer, SWPPP Manager, and SWPPP Manager’s Representatives in the SWPPP.

The SWPPP Preparer must meet at least one of the following qualifications:

•	current certification as a CPESC

•	current certification as AK-CESCL, and at least three years experience in erosion and sediment control (provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement)

•	Professional Engineer registered in the State of Alaska and current certification as AK-CESCL

The Superintendent must meet all the following qualifications:

•	current certification as AK-CESCL

•	duly authorized representative, as defined in the CGP, Appendix G

The SWPPP Manager and SWPPP Manager’s Representative must hold current AK-CESCL certification.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT.  The eNOI and eNOT must be signed and certified by a responsible corporate officer, in accordance with CGP Appendix G, Section 11.  Signature and certification authority for the  eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Delegate signature and certification authority to the Superintendent, in accordance with CGP Appendix G, Section 11.B, for the SWPPP. SWPPP inspections, and other reports required by the CGP.  Use form 25D-108.  The form and certification must be used verbatim and must not be altered other than to insert names, dates, and signatures as included on the form.  Include a copy of the written delegation form 25D-108, and the Department’s delegation form 25D-107 in the SWPPP.  Delegation is not required if the Superintendent is a responsible corporate officer for the Contractor, as defined in CGP Appendix G, Section 11.A.

641-1.06 OPERATORS.

1.	The Department and the Contractor are both Operators for the Project and for Department furnished:

•	material sites

•	disposal sites

•	haul routes where deposition of erodible materials may result from material hauling activity

•	staging areas

•	equipment storage areas

•	utility relocation and installation activities associated with the project

2.	The Department is not an operator for Contractor furnished:

•	material sites

•	material processing sites

•	disposal sites

•	haul routes where deposition of erodible materials may result from material hauling activity

•	staging areas

•	equipment storage areas

The Contractor is an operator for the above listed Contractor furnished areas.  Compliance with APDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these Contractor furnished areas are the sole responsibility of the Contractor.  Document the name of each operator, and the locations of these areas in the Project SWPPP.  The control measures for these sites may be included in the Project SWPPP if they are eligible for CGP coverage.  If this is the case, then the Contractor’s and the Department’s eNOI acreage will be different.  If the area must be covered by the industrial storm water permit, note that there is a 30-day waiting period for the eNOI to become active.

3.	The Department is not an operator for commercial and utility operator furnished:

•	material sites

•	material processing sites

•	disposal sites

•	haul routes

•	staging areas

•	equipment storage areas

The commercial operator is an operator for the above-listed commercially operator-furnished sites.  Compliance with APDES and other applicable federal, state, and local requirements, and securing all necessary clearances, rights, and permits for these commercial operator furnished areas are the sole responsibility of the commercial operator.  Document the name of each operator, and the locations of these areas in the Project SWPPP.

4.	A Utility company is not an Operator when utility relocation is performed concurrently with the Project.  The Department maintains operational control over the plans and specifications, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

The Department and a Utility company are both Operators for the Project when utility relocation is performed in advance of Project construction.  After the Highway Contractor has an active NOI for the Project, the Utility company no longer has Operator status and files a NOT for the SWPPP covering only the utility work.  Remaining relocation is identified in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Use a SWPPP preparer to develop the SWPPP and associated documents, in accordance with the requirements of the CGP.

Use the Department’s ESCP as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.  Develop the SWPPP in accordance with EPA’s SWPPP template for Unauthorized States, with the following exceptions:

•	In Section 3 (Good Housekeeping), add a subsection to describe dedicated asphalt plants and/or dedicated concrete plants, give their locations and identify the controls that will be used to minimize pollutants from them.  If there are no dedicated asphalt or concrete plants, then state that in the SWPPP.

•	Appendix H is not required

•	Add appendices for:

○	Endangered Species Act and historic preservation documents

○	Other Permits (404, Section 10, etc.)

○	Hazardous Material Control Plan

○	Subcontractor and Utility Certifications

○	BMP descriptions

○	Rainfall logs

○	NOT form

○	Personnel qualification & training certifications for:

▪	Superintendent

▪	SWPPP Preparer

▪	SWPPP Manager

▪	SWPPP Manager’s Representative

▪	Department's SWPPP Inspector

•	Add forms completed by the Department:

SWPPP Delegation of Signature Authority (25D-107)

DOT&PF SWPPP Certification (25D-109)

•	Use Department forms for:

○	Construction Site Inspection Report (25D-100 parts 1&2)

○	Contractor’s Delegation of Signature Authority (25D-108)

○	Contractor’s SWPPP Certification (25D-111)

○	SWPPP Grading and Stabilization Log (25D-110)

○	SWPPP Corrective Action Log (25D-112)

○	SWPPP Amendment Log (25D-114)

○	SWPPP Daily Record of Rainfall (25D-115)

○	Utilility Certification Form

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix included in EPA’s template for Unauthorized States.  Incorporate and cite applicable requirements of the project permits and environmental commitments into the SWPPP. Incorporate SWPPP activities into the Project CPM Schedule.

Use the Department’s documentation of consultation with the State Historic Preservation Officer and federal agencies for consideration of historic properties and endangered species.  Make additional consultations as necessary for Contractor or commercial operators’ specific activities which fall outside the Project limits, or which may result in changes to the Project footprint or timeline. You may cover these activities within the project SWPPP provided they are eligible for coverage under the CGP, and provided the SWPPP clearly and specifically identifies the Operators, their activities, and the portions of the SWPPP and project areas for which they are responsible.

The SWPPP Preparer must visit the project site before construction activity begins. The findings of the visit must be incorporated in the development of the SWPPP, or by amendment if the SWPPP was submitted prior to the visit. The SWPPP preparer must visit the site accompanied by a representative of the Contractor and the Department. Select appropriate application and sequencing of BMPs in relation to progress schedule.  Document the SWPPP Preparer’s visit in the SWPPP.  Include the date, and the names of the personnel participating in the visit.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.  Describe site specific BMPs, source controls, sediment controls, discharge points, and a plan including schedule and implementation procedures for temporary and final stabilization.  Describe all temporary and permanent stabilization measures.  Include typical installation drawings for all BMPs that will be incorporated in the Project.  Include the Contractor’s schedule and the schedule for stabilization and installation of other BMPs.

The SWPPP must provide erosion and sediment control measures for all land disturbances resulting from the Contractor, Utility Companies and all Subcontractors activities during the course of the contract.  The SWPPP must consider the activities of utility companies performing work on the Project.  The SWPPP must describe the roles and responsibilities of the Contractor, Utility Companies, subcontractors, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project and identify the areas over which each operator has operational control.

Specify the line of authority and designate a Superintendent, SWPPP Manager, and each SWPPP Manager’s Representative.  Provide 24 hour contact information for the Superintendent, SWPPP Manager, and for each SWPPP Manager’s Representative.  The Superintendent, SWPPP Manager, and each SWPPP Manager’s Representative must have 24 hour contact information for all Subcontractor SWPPP Coordinators.

Identify the SWPPP inspection schedule in the SWPPP.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, inspection reports, corrective action logs, records of land disturbance and stabilization, and any other documents necessary to satisfy the requirements of the CGP and this specification.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment (See 40 CFR 117 and 302 for listing of hazardous materials).

Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

List and give the location and estimated quantities of hazardous materials to be used or stored on the Project.  Store hazardous materials in covered storage areas.  Include secondary containment for all hazardous material storage areas.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc).

Designate a Spill Response Field Representative and identify the line of authority.  Designate a Subcontractor Spill Response Coordinator for each subcontractor. Provide 24 hour contact information for the Contractor’s Spill Response Field Representative.  The Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor  Spill Response Coordinator .

Identify the locations where storage, fueling and maintenance activities will take place, describe the maintenance activities, and list controls to prevent the accidental spillage of oil, petroleum products, and other hazardous materials.

Detail procedures for containment and cleanup of hazardous substances.  Detail a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Detail a plan for dealing with contaminated soil and water encountered during construction.

Detail methods of disposing of waste petroleum products and other hazardous materials generated by the Project.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Store spill response materials, appropriate to the hazards associated with that site, in sufficient quantity at each identified location.

Include the HMCP as an appendix to the SWPPP.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC) REQUIREMENTS.  Prepare and implement an SPCC when required by 40 CFR 112; when both of the following conditions are present on the Project:

•	oil or petroleum products from a spill may reach navigable waters, and

•	total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC in the SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT, SWPPP MANAGER, AND SWPPP MANAGER’S REPRESENTATIVE.  The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project.  The Superintendent shall sign and certify the SWPPP, SWPPP inspections, and other reports required by the CGP, except the NOI and NOT.  The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP, SWPPP inspections, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager. Those duties may include:

1.	Ensuring Contractor’s compliance with the SWPPP and CGP,

2.	Ensuring construction activity does not result in discharge of pollutants that exceed applicable water quality standards,

3.	Performing SWPPP inspections,

4.	Updating the SWPPP with amendments and forms, and

5.	Directing and overseeing installation, maintenance, and removal of BMPs

The SWPPP Manager may assign their duties to a SWPPP Manager’s Representative.

The Superintendent, SWPPP Manager and the SWPPP Manager’s Representative shall be knowledgeable in the requirements of this section, the SWPPP, CGP, BMPs, HMCP, SPCC, environmental permits and environmental commitments.

The Superintendent, SWPPP Manager, and the SWPPP Manager’s Representative shall have the Contractor’s complete authority to suspend construction activities that do not conform to the SWPPP or CGP.

641-2.05  MATERIALS.  Comply with the material requirements described in the Plans and Specifications.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments in accordance with the requirements of the CGP.

Straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil and Water Conservative District, Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

Silt fences 	Subsection 729-2.04, Sediment Control.

Temporary Seed 	Section 724.

Erosion, Sediment, and Pollution Control - Material	Section 744

641 3.01 CONSTRUCTION REQUIREMENTS.  Comply with the SWPPP and the requirements of the CGP.

Ensure all subcontractors and utility companies understand and comply with the SWPPP and the CGP. Provide SWPPP information to utility companies.  Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP. Provide training to subcontractors & utility companies on control measures at the site and applicable storm water pollution prevention procedures and document the dates and attendees to these trainings in Appendix J of the SWPPP.

1.	Starting Construction:

Do not begin Construction Activity until:

•	the SWPPP has been approved by the Engineer

•	authorized by the Engineer

•	the Project eNOI for the Department and for the Contractor are both listed as Active Status on the ADEC website

•	the SWPPP preparer has visited the Project and the SWPPP has been developed (or amended) with findings from the visit. Also document in the SWPPP the date of the visit and the persons conducting the visit.

Post notices on the outside wall of the Contractor’s project office, and at publicly accessible locations near the beginning and end of the Project. Protect postings from the weather and locate so the public can read them without obstructing construction activities (for example, at an existing pullout).  Include the following information in each of the posted notices:

•	Copy of all eNOIs related to this project

•	Name and phone number of SWPPP Manager

•	Location of the SWPPP available for public viewing.

Install an outdoor rain gauge in an approved and readily accessible location on the Project.

2.	During Construction:

Comply with requirements of the HMCP and SPCC, and all state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and other hazardous materials.  Place absorbent pads or other suitable containment under fill ports while fueling, and under equipment during maintenance or repairs.  Install secondary containment under all stationary equipment that contains petroleum products.

Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report petroleum product spills as required by federal, state and local law, and as described in the HMCP and SPCC.

Comply with the requirements of the SWPPP.  Implement temporary and permanent erosion and sediment control measures identified in the SWPPP and as directed by the Engineer. Keep the SWPPP current.  If storm water discharges threaten water quality, take immediate action. Comply with the requirements of 18 AAC 70 State of Alaska Water Quality Standards, AS 16.05.841 and 16.05.871  Protection of Fish and Game, 11 AAC 112 Alaska Coastal Management Program, Section 404 of the CWA, and all other applicable federal, state, and local statutes and regulations.

Coordinate with subcontractors and utility companies doing work in the project area so BMPs, and temporary and permanent stabilization are installed, maintained, and protected from damage.

If you suspect or have determined that there has been an incident of CGP non-compliance that may endanger health or the environment, then immediately report it to the Engineer.  The Engineer will determine whether the incident is required to be reported to the ADEC as described in Appendix G, part 12, of the CGP, and if so, the Department will submit oral and written reports on behalf of the Department and the Contractor.  Notify the Engineer within 24 hours of the time you become aware of the incident.  The SWPPP Manager or the Superintendent will co-sign the written report to ADEC.

3.	Corrective Action and Maintenance of BMPs:

Maintain temporary and permanent erosion and sediment control measures in effective operating condition.  Remove sediment and debris from sediment traps, silt fences, and sediment ponds before sediment or debris accumulates to 50% of the BMP’s design capacity.

Implement corrective action:

•	if an  incident of non-compliance with the SWPPP, or CGP is identified

•	if an inspection identifies the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

•	if the Engineer determines the SWPPP or any part of the SWPPP is ineffective in preventing the discharge of pollutants that exceed applicable water quality standards

•	if any BMP is damaged, undercut, or unable to effectively perform the intended function

•	if any BMP is at or exceeding 50% of its design storage capacity

•	whenever there is a change in conditions, design, construction, operation, or maintenance that could affect the discharge of pollutants in storm water leaving the Project

Implement corrective actions as soon as possible, and before the next storm event whenever practicable.  If implementation before the next storm event is impracticable, the situation must be documented in the SWPPP and alternative BMPs must be implemented as soon as possible.

4.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed areas, stockpiles, and of erodible aggregate layers so that all of the following conditions are satisfied:

•	as soon as practicable

•	as soon as necessary to avoid discharge of pollutants that exceed applicable water quality standards

•	as identified in the SWPPP schedule and/or phasing

•	in accordance with stabilization schedule requirements of applicable project permits

•	no later than 14 days after each cessation of land-disturbing activities

Land may be disturbed multiple times during a project. Coordinate work to minimize area of land disturbance as much as practicable. Do not disturb more area than you can stabilize in the time limits specified, and with the resources available.

Stabilize disturbed areas prior to freezing conditions that may limit or eliminate options for temporary stabilization.

Temporary stabilization measures may include individual or a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover.  Maintain seeded areas.  Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed in accordance with Section 618, at locations where permanent seed is indicated on the plans and land-disturbing activity is permanently ceased.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install stabilization up to ordinary high water:

•	at the inlet and outlet of the culvert, drainage structure, or bridge

•	in the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge

•	under the bridge

Immediately after placing a culvert or drainage structure, install temporary or permanent stabilization when a stream bypass is not used for construction:

•	at the culvert or drainage structure inlet and outlet

•	in the area upstream and downstream of the culvert or drainage structure, that is disturbed in the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure

5.	Ending SWPPP Activities and SWPPP Maintenance.

The Engineer will determine SWPPP activities have ended when all of the following requirements are met:

•	Land disturbing activities have ceased

•	The Project site (including Department furnished material sources, disposal sites, staging areas, equipment areas, etc.) has achieved final stabilization

•	Temporary BMPs have been removed

Submit eNOT in accordance with Subsection 641-1.03.5.

If the contractor’s eNOI acreage includes areas where the Department is not an operator and co-permittee, then the contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must state in the SWPPP which project areas have reached final stabilization.

The Department will provide a copy of its eNOT to the contractor for inclusion in the SWPPP.

6.	Record Retention.

Transmit one copy of the final SWPPP, including all amendments and appendixes, to the Engineer when the project eNOTs are filed.

Retain copies of the SWPPP, including documents listed under 641-3.02 SWPPP DOCUMENTS, for at least three years after the date of eNOT.  If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the three year retention period expires, retain the SWPPP and all records related to the SWPPP and CGP until EPA and/or ADEC has determined all issues related to the investigation  are settled.

641-3.02 SWPPP DOCUMENTS.  The SWPPP and related documents maintained by the Contractor are the record documents for demonstrating compliance with the CGP.  SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the approved SWPPP, HMCP and SPCC at the on-site project office. If there isn’t an on-site project office, keep the information in an office that is within 30 miles, by road from the Project.

Maintain all SWPPP documents in binders in one common location.  Include the following items in the SWPPP binders:

•	eNOI (all applicable)

•	Acknowledgement letters from EPA or ADEC to each operator filing an eNOI

•	Signature Delegations (25D-108 Contractor, 25D-107 Department)

•	Copies of current AK-CESCL card for Superintendent, SWPPP Manager, SWPPP Manager’s Representative, and Department's SWPPP Inspector(s)

•	Approved SWPPP

•	SWPPP Certification (25D-111 Contractor, 25D-109 Department)

•	HMCP (with lines of authority and contract information)

•	SPCC when required

•	SWPPP Preparer's qualifications

•	Documentation of the SWPPP Preparer's preconstruction project visit

•	SWPPP Amendments

•	SWPPP Amendment Log (25D-114)

•	SWPPP Inspection Reports (25D-100 parts 1&2)

•	SWPPP Corrective Action Log (25D-112)

•	SWPPP Grading and Stabilization Activities Logs (25D-110)

•	SWPPP Daily Record of Rainfall Log (25D-115)

•	Lines of Authority and Contact Information for Superintendent, SWPPP Manager, SWPPP Manager’s Representative, and Subcontractor SWPPP Coordinators

•	ADEC SWPPP Review Letter (when required and once received)

•	eNOT (all applicable)

•	Any other records related to the SWPPP, SWPPP compliance, or CGP reporting requirements

641 3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.  Perform inspections, prepare inspection reports, and prepare SWPPP amendments in compliance with the SWPPP and the CGP.  Prepare SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Logs, and  SWPPP Daily Record of Rainfall forms.  Joint SWPPP inspections must be performed by the Superintendent, SWPPP Manager, or the SWPPP Manager’s Representative; and by the Engineer or Engineer’s qualified representative.

1.	Before Construction.

Before beginning Construction Activity, conduct a Joint Inspection of the Project with the SWPPP Preparer. Incorporated the results of the visit into the SWPPP and document the date of the visit and personnel attending the visit in the SWPPP.

2.	During Construction.

Conduct Joint Inspections (see Definitions 641-1.02) on one of the following schedules:

•	at least once every seven days during construction, or

•	at least once every 14 days during construction and within 24 hours of the end of a storm event of 1/2 inch or greater rainfall in a 24 hour period (1/2 inch rainfall as recorded at the project site rain gauge)

Indicate the inspection schedule in the SWPPP and conduct Joint Inspections in accordance with the selected schedule.

3.	Before Seasonal Suspension of Work.

Conduct Joint Inspection before seasonal suspension of work to review condition and applicability of BMPs and SWPPP.  Confirm SWPPP, temporary stabilization, and BMPs are installed and functioning in accordance with the requirements of Subsection 641-3.01.

4.	During Seasonal Suspension of Work.

Conduct Joint, or as otherwise approved by the Engineer, Inspections in accordance with the inspection schedule indicated in the approved SWPPP.  Inspection frequency during seasonal suspension of work may be reduced to at least one inspection every month if approved by the Engineer and the revised inspection frequency is documented as an amendment to the SWPPP, and either of the following requirements is met:

•	the entire site is temporarily stabilized, or

•	runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

The Engineer may waive winter monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

•	below-freezing conditions are anticipated to continue for more than one month

•	land disturbance activities have been suspended, and

•	beginning and ending dates of the waiver period are documented as an amendment to the SWPPP.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall form during seasonal suspension of work.  Resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in a discharge.  Resume recording land disturbance and stabilization activities on the Grading Activities Log when Construction Activity resumes.

5.	During Winter Work.

Conduct Joint Inspections in accordance with the inspection schedule indicated in the approved SWPPP.

Inspection frequency during winter work may be reduced to at least one inspection every month if all of the following requirements are met:

•	runoff is unlikely due to winter conditions (e.g. the site is covered with snow, ice or the ground is frozen)

•	approval from the Engineer

•	the revised inspection frequency is documented as an amendment to the SWPPP.

6.	Project Completion.

Conduct Joint Inspection to ensure final stabilization is complete throughout the Project and all temporary BMPs are removed.

7.	Items and Areas to Inspect.

Inspect all items and areas covered under both the Department’s and the Contractor’s Project eNOIs; and items and areas included in the SWPPP.

Areas referenced in the Project SWPPP that are Contractor furnished, commercially, or utility furnished, and the Department is not an operator, do not require Joint Inspection in accordance with this contract.  For Contractor, commercial, or utility operator furnished areas, the Contractor or commercial operator is solely responsible for inspecting and assuring compliance with all APDES requirements, and any other federal, state, local, or tribal permitting requirements.

8.	Inspection Reports.

Use DOT&PF SWPPP Construction Inspection Report, Form 25D-100 to record SWPPP inspections.  Complete all fields included on the inspection form.

The Superintendent must sign and certify the inspection report on the day of the inspection, and must provide the report to the Engineer the same day.  The Engineer will sign and certify the inspection report and will return the original to the Contractor within three working days.

9.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent, SWPPP Manager, or SWPPP Manger’s Representative are responsible for amending the SWPPP.  They shall initial amendments to the SWPPP; and update and initial DOT& PF Form 25D-114, SWPPP Amendment Log.  Amend the SWPPP:

•	whenever there is a change in design, construction operation, or maintenance at the construction site that has or could have significant effect on the discharge of pollutants that has not been previously addressed in the SWPPP

•	if a Joint Inspection identifies the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

•	if the Engineer or Contractor determines the SWPPP or any portion of the SWPPP is ineffective in preventing the discharge of pollutants from the Project, that exceed applicable water quality standards

•	whenever an inspection identifies a problem that requires additional or modified BMPs

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven (7) calendar days following an inspection.

Include the following information when documenting modifications to the SWPPP:

•	date the action was completed

•	initials of person documenting the action

•	description of the action

Update the SWPPP drawings including date, location, action taken, and initials of the person recording the action for:

•	installation of BMP

•	modification of BMP (including any changes to BMP typical installation details)

•	removal of BMP

Keep the SWPPP Amendment Log current and submit a copy to the Engineer, including copies of any documents amending the SWPPP, prior to performing each scheduled SWPPP inspection.

Include the current SWPPP Amendment Log as an appendix to the SWPPP.

10.	Corrective Action.

Action required to restore effective function of BMPs is corrective action and must be documented.

Use DOT&PF SWPPP Corrective Action Log, Form 25D-112, to document corrective actions to the SWPPP and to BMPs.  The Superintendent, SWPPP Manager, or SWPPP Manger’s Representative shall initial all entries on Form 25D-112.

After each inspection report has been signed and certified, update the corrective action log to include all corrective actions noted on the inspection report.

After the corrective action has been accomplished, note the action taken, and date and initial the entry.

Keep the corrective action log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.

Keep the corrective action log as an appendix to the SWPPP.

11.	Grading and Stabilization.

Use DOT&PF SWPPP Grading and Stabilization Activities Log, Form 25D-110, to record land disturbance and stabilization activities.  The Superintendent, SWPPP Manager, or SWPPP Manger’s Representative shall initial all entries or all dates on Form 25D-110.

Keep the grading and stabilization activities log current and submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.

Keep the grading and stabilization activities log as an appendix to the SWPPP.

12.	Daily Weather Records.

Use DOT&PF SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled SWPPP inspection.

Include the daily record of rainfall form as an appendix to the SWPPP.

641-3.04 EROSION, SEDIMENT, AND POLLUTION CONTROL PRICE ADJUSTMENT.  The total value of this contract will be adjusted as specified herein. A price adjustment, under Item 641(5), will be assessed as follows.

1.	Fines and Penalties: A Price adjustment equal to any penalties and fines levied against the Department by local, state or federal agencies for pollutant violations, including violations of the CWA and the CGP, except when due to Department negligence.  An amount equal to the anticipated penalties and fines for the violation or violations, excluding any due to negligence by the Department, will be withheld temporarily until the actual cost of the penalties and fines is known.  Anticipated penalties and fines will be determined by the Engineer.  The Contractor is also responsible for the payment of penalties and fines levied against the Contractor.

2.	Failure to perform Inspections: By each 24 hour period that a required SWPPP inspection is delayed or is not signed, certified, or completed in accordance with the schedule identified in the approved SWPPP a price adjustment of $750 will be assessed.

3.	Failure to perform Corrective Action.  By each 24 hour period following 24 hours after written notice by the Engineer, per occurrence, a price adjustment of $750 will be assessed where the Contractor:

•	fails to complete SWPPP administrative requirements as identified in the Contract or the CGP,

•	fails to initiate work required by the SWPPP, or

•	fails to initiate corrective action to respond to a deficiency noted during an inspection or by the Engineer.

The same deficiency remaining uncorrected will be considered an additional occurrence for each additional 24 hour period, without requiring additional written notice by the Engineer.

641-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2), or items 641(1), (3), and (4). The Bid Schedule may or may not, include Items 641(5) and 641(6). When 641(6) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to other items of work.

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC preparation, agency fees for SWPPP reviews, SWPPP amendments, inspections, monitoring, reporting, and all record keeping related to the SWPPP and required by the CGP.

Item 641(2) Temporary Erosion, Sediment and Pollution Control. At the contingent sum prices specified in the Contract or the Directive authorizing the work to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures required to complete the project using the approved SWPPP, SPCC and HMCP.

Item 641(3) Temporary Erosion, Sediment and Pollution Control. At the contract lump sum price to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs identified in the ESCP, and for BMPs and other measures included in the HMCP and SPCC.

Item 641(4) Temporary Erosion Sediment and Pollution Control Additives. At the contingent sum prices specified in the Directive for extra, additional, or unanticipated work to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control measures. All work paid under this Item will be shown as amendments to the original approved SWPPP or HMCP

Item 641(5) Erosion, Sediment, and Pollution Control Price Adjustment.  As specified in Section 641-3.04.

Item 641(6) SWPPP Manager. At the contract lump sum price for a SWPPP Manager and SWPPP Manager’s Representative that conforms to this specification.

Temporary erosion, sediment and pollution control measures that are required at Department furnished, Contractor furnished, or commercial operator furnished material sources, disposal sites, haul routes, fuel and material storage areas, and at equipment or material staging areas, will not be paid for separately but are subsidiary to other items of work. Work required by the HMCP and SPCC including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to other items of work.

Work that is paid for directly or indirectly under other pay items will not be measured and paid for under this Section 641. This work includes but is not limited to dewatering, shoring, bailing, permanent seeding, installation and removal of temporary work pads, temporary accesses, temporary drainage pipes and structures, diversion channels, settling impoundment, filtration, etc.

Temporary erosion, sediment and pollution control measures that are required due to negligence, carelessness, or failure to install permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Permanent erosion, sediment and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

If, after 24 hours following written notice by the Engineer, the Contractor fails to pursue work required by the SWPPP, respond to inspection recommendations or deficiencies in the SWPPP, or implement erosion and sedimentation controls identified by the Engineer, or fails to perform any of the contract obligations, the Engineer may employ others to correct the condition and deduct the cost from the Contract amount.

The Engineer may suspend earthwork operations and withhold any monies due the Contractor for failure to:

•	perform SWPPP Administration

•	perform timely SWPPP inspections

•	update the SWPPP

•	transmit SWPPP, SWPPP Inspection Reports, and associated Section 641 submittals to the Engineer

•	maintain effective BMPs that minimize erosion, control sediment, or prevent discharge of pollutants that exceed applicable water quality standards

•	perform duties in accordance with the requirements of this Section 641

•	meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control

The Contractor shall be due no additional monies or Contract time extension as result of delays resulting from suspension of earthwork for failure to perform required erosion, sedimentation, or pollution duties as outlined in this Section 641.

-

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

| 641(1) | Erosion, Sediment and Pollution Control Administration | Lump Sum |
| --- | --- | --- |
| 641(2) | Temporary Erosion, Sediment and Pollution Control | Contingent Sum |
| 641(3) | Temporary Erosion, Sediment and Pollution Control | Lump Sum |
| 641(4) | Temporary Erosion, Sediment and Pollution Control Additives | Contingent Sum |
| 641(5) | Erosion, Sediment and Pollution Control Price Adjustment | Contingent Sum |
| 641(6) | SWPPP Manager | Lump Sum |

(020310)CR641

Section 642
Construction Surveying and Monuments

642-2.01 MATERIALS. Add the following:

Digital Measuring Instrument: Nu-metrics, Nitestar DMI (www.nu-metrics.com)

642-3.01 GENERAL. Add the following:

11.	Document the Stationing of the beginning and ending of existing passing zones before work that will remove or obliterate the existing striping. Measure, as outlined below, sight distance for passing zones after the base course layer or pavement milling has been accepted. Use Table 642-1 to establish Minimum Passing Sight Distance. Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit. Record the sight distance for each station location that falls below the posted speed limit plus 10 MPH. Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH should be marked as “Pass” or “+”. Stations observed to fall below the values required for the posted speed limit should be marked as “Fail” or “-”.

Measure from the roadway edge of traveled way, using a 3.5 foot object height (or “instrument height”) at 100 foot station marks looking ahead to a 3.5 foot target height at the edge of traveled way for opposing traffic. Provide a list of each station result for each direction of travel along the roadway edge of traveled way. Certify and record the results on standard “letter” sized paper and provide 2 copies to the Engineer at least two weeks before laying out final pavement markings.

The Engineer will forward one copy of the existing and proposed sight distance measurements on the form provided herein, to the Regional Traffic Engineer. Table 642-1 does not automatically ensure passing striping will be provided. The Regional Traffic Engineer’s office will take up to two weeks to review and approve pass/no pass striping against operating speeds for the roadway before installation, using Table 642-1 and the Alaska Traffic Manual as a guide. No pass striping zones shall be at least 500 feet in length. Passing striping shall be long enough to meet the distances in Table 642-1. Passing striping will not extend into a segment of road without minimum sight distance.

TABLE 642-1
PASSING SIGHT DISTANCE

| Operating Speed (mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 25 | 450 |
| 30 | 500 |
| 35 | 550 |
| 40 | 600 |
| 45 | 700 |
| 50 | 800 |
| 55 | 900 |
| 60 | 1,000 |
| 65 | 1,100 |
| 70 | 1,200 |

- Passing Sight Distance Survey Table

- ROAD NAME:___________________________________________________

Stationing 	FROM:______________________________	DATE:_____________

TO:_________________________________	Surveyor:____________________

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Remarks |
| --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

Accepted By: _____________________________________________Date:    ______________

DOT/PF Project Engineer

Passing Sight Distance

Review Checked By: _______________________________________Date:    ______________

DOT/PF Regional Traffic Engineer

642-4.01 METHOD OF MEASUREMENT. Add the following:

Item 642(16) Passing Sight Distance Measurement. By the number of stations on the project measured separately along centerline, once for each direction, only after the certified and recorded results have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

642(16)	Passing Sight Distance Measurement 	Station

R61(3/22/06)

Section 643
Traffic Maintenance

Special Provisions

643-1.01 DESCRIPTION.  Add the following as a third paragraph:

Illuminate construction activities listed in Table 643-3 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS.  Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work: Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the table below:

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| < 61 | Lighting Required All Year |  | Everything S of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14((03/15/06)

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing. If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan. Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public. The Traffic Control plan shall specify the traffic control devices required for these operations.

R222(05/05/08)

Standard Modification

643-1.04 WORKSITE TRAFFIC SUPERVISOR.

Add the following to Item 2. Duties:

i.  Supervise lighting of Night Work.

ES14(03/15/06)

Add Item 3. Authority:

- Authority.  The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS. In item 10. Temporary Crash Cushions, delete the second sentence:

“Do not use permanent crash cushions as temporary crash cushions.”

E62(07/28/08)

643-2.01 MATERIALS. Under Item 16. Flagger Paddles, replace the last sentence with the following: Use reflective sheeting that meets AASHTO M 268 Type VIII or IX. Use background colors of fluorescent orange on one side and red on the other side.

E56(5/01/07)

- Special Provisions

643-2.01 MATERIALS.  Add the following:

12.	l.	Power cords shall comply with the National Electrical Code Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter.   The cord must have an integral GFCI  Protection located either in the attachment plug or within 12 inches of the plug

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

R222(05/05/08)

Standard Modification

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

E56(5/01/07)

- Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business accesses during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  Traffic may be maintained on a continuous gravel surface for 5,000 feet.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

Standard Modification

643-3.04 TRAFFIC CONTROL DEVICES.

- In the sixth paragraph and also in Item 4.b., delete: “ATTSA” and replace with “ATSSA”.

E56(5/01/07)

- Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.

Delete the first sentence of the eighth paragraph and substitute the following: Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to item 1. Embankments.: Close trenches and excavations at the end of each continuous work shift.

Add the following to item 3. Fixed Objects.: Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 4.b. and replace with the following: Flagger Certification by ATSSA

- Delete item 6. and replace with the following:

6.	Street Sweeping. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming. Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

- Change items 7 and 8 to 8 and 9 respectively.Add the following:

10.	ET-2000 LET. The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s). Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Replace the first sentence with the following: When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice. A written notice will follow the oral notice according to subsection 105-1.01 Authority of the Engineer.

Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time the roadway or pedestrian facility is in an unacceptable condition.

- Delete Table 643-1 and substitute the following:

TABLE 643-1
ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-5,000 | $30 |
| 5,001+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following:

A full, closure of the highway will be allowed for a duration of 60 days at Peters Creek between May 23, 2011 and August 12, 2011.

A full closure of the highway will be allowed for a duration of 3 days (Friday, Saturday, and Sunday) at Parks Creek between May 23, 2011 and August 12, 2011.

With the exception of the highway closures and unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

- No traffic restrictions between 0600 to 0800 and 1600 to 1800 Monday through Friday.

- Around the July 4th holidays:

- If the holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

- If the holiday falls on a Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

- If the holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/16 mile (330 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists. During paving operations a 10 minute stopped delay, 40 vehicles, or 1/8 mile (660 feet) of traffic detained, will be allowed for motorists except school buses. If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone. This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to subsection 670-3.01, Construction Requirements of these Special Provisions.

Add the following new subsection:

643-3.10 LIGHTING OF NIGHT WORK.

Illuminate the night work areas specified in Table 643-2 to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Table 643-3 Night Work Illumination Level and Area of Coverage

| Type of Work/ Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): | Two balloon lights of at least 2000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |
| 1) with roads with ADTs over 10,000 or |  |
| 2) that are controlled by portable signals or flaggers |  |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to meet required lighting equipment or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-2.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14(03/15/06)

Standard Modification

- Add the following new subsection:

643-3.11. HIGH VISIBILITY CLOTHING. Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

1.	Standards.

Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.

Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.

Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.

Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.

Wear raingear tops and bottoms conforming to requirements of in this subsection 643-3.11.

6.	Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

7.	Condition.

Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

- Special Provision

643-4.01 METHOD OF MEASUREMENT.

Replace the second sentence of Item 2 with the following: Special Construction Signs are measured by the total area of legend bearing sign panel, as determined under subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates. Work will be subsidiary to Item 643(1) or 643(2) Traffic Maintenance.

R222(05/05/08)

- Replace item 12. with the following:

12.	Portable Changeable Message Board Signs. By the 24-hour period for each sign (beyond 2), as shown on an approved TCP and displaying an approved message.

- Standard Modification

643-5.01 BASIS OF PAYMENT. Add the following: Payment for high visibility garments for workers is subsidiary to other items.

E56(05/01/07)

- Special Provision

643-5.01 BASIS OF PAYMENT. Add the following:16.  Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14(03/15/06)

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

- TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $24.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier, Type F | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $.75 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $46/hour. The Engineer does not require a change order/directive for the flagging pay item. Flagging associated with Change Order work will be paid at the prices according to subsection 109-1.05 Compensation for Extra Work.

- Delete Item 643(15) and substitute the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

R222(05/05/08)

Section 644
Services to be Furnished by the Contractor

Standard Modification

644-2.02 FIELD LABORATORY. Add the following to the end of the second sentence of the first paragraph: through one week after Project Completion.

E44(01/27/07)

- Special Provisions

644-2.02 FIELD LABORATORY.

- Delete sub-item g of item 2 and substitute the following:

- 500 gallon capacity tank with a pressure pump or a commercial pressurized system.

- Replace item 6. a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Add the following:

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

R63(01/11/07)

644-3.01 METHOD OF MEASUREMENT.

This item will not be measured for payment. The Engineers acceptance will constitute measurement.

- Standard Modification

644-4.01 BASIS OF PAYMENT. Add the following items:

Lump Sum Items. Payment for lump sum items will be made as follows:

1.	A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

2.	The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site. If anticipated construction period changes, the final increment will be held until final payment.

E44(01/27/07)

- Special Provisions

Add the following: Long distance calls made by State personnel and the will be paid by the State. Local calls, connection fees and Internet service provider fees shall be paid by the Contractor.

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

R63(01/11/07)

Add the following Section:

Section 645
Training Program

Special Provision

645-1.01 DESCRIPTION. This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General. Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/BAT apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A-310. Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts. In the event  a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker according to the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project. No payment or partial payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

S16(10/29/91)

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program, 3 Trainees/Apprentices	Labor Hour

Section 646
CPM Scheduling

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE. Delete this Subsection in its entirety and replace with the following: Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time. Allow the Engineer 14 days to review the initial CPM Schedule. Revise promptly. The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE. Delete item 2. 60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates. and substitute the following: Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule. Meet with the Engineer monthly or as deemed necessary by the Engineer.

R261(12/13/02)

- Add the following Section:

Section 647
Equipment Rental and utility potholing

Special Provisions

647-1.01 DESCRIPTION. This item consists of determining and recording the horizontal and vertical location of subsurface utilities and furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 MATERIALS.

Backfill Material		Use aggregate conforming to Aggregate Base Course, Grading D-1

Asphalt Patch Material	Use Hot Mix Asphalt, Type II, Class A

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 EQUIPMENT RENTAL CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer. Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-3.02 utility potholing CONSTRUCTION REQUIREMENTS. Submit the utility potholing schedule to the Engineer and utility companies at least 5 days before starting potholing.  Remove materials using a vacuum-extract truck to expose and identify the utilities.  Survey the location and elevation of the utilities using the project horizontal and vertical control.  Log as-built information at each pothole location.

Unless the location and elevation results indicate utilities need to be further exposed for adjustment, backfill immediately after the Engineer accepts the logged data.  Backfill and compact the first six vertical inches using the excavated material or other approved materials.  Backfill and compact the remaining pothole void using Aggregate Base Course, Grading D-1.  If the pothole is located in a paved area, provide a pavement patch using Hot Mix Asphalt. Type II, Class A material of the thickness equal to the adjacent asphalt concrete.

Immediately contact the Engineer and the affected utility if utility facilities are damaged during the potholing operations.  Costs associated with repairing damaged utilities will be borne by the Contractor.

647-3.03 utility potholing AS-BUILTS. Maintain a complete log of pothole information, including station, offset, elevation, utility types/sizes encountered, date of potholing operation, groundwater elevation, and other pertinent data.  Submit the completed log to the Engineer within two working days following the start of the pothole excavation.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

Measure Vac-Truck Pothole by the total number of locations verified and accepted.  Other related work, including but not limited to removal of pavement, backfilling, pavement patching, shoring, labor, and surveying will not be paid separately, but shall be subsidiary to the Item.  Potholing for the Contractors information and not shown on the Plans or directed by the Engineer will be the Contractor’s responsibility and will not be paid.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1) Wide Pad Dozer, 65 hp Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule. This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

R15(08/24/05)

Payment for Item 647(2) Vac-Truck Pothole will be paid on a contingent sum basis at the rate of $450/each for the locations shown in the Plans or as directed by the Engineer.  The price for Vac-Truck Potholing includes full compensation for furnishing equipment, labor and materials necessary to complete the work as specified.  Payment will be based on the verified and accepted log.  Payment will not be made for potholing not listed in the verified log, or for exposing utilities during the course of other excavation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 HP Minimum	Contingent Sum

647(2)	Vac-Truck Pothole	Contingent Sum

Section 660
Signals and Lighting

Special Provisions

660-1.02 DEFINITIONS.  Revise the first sentence to read:

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements, Section 1, Definitions, along with the following:

Under No. 2. Luminaire. Revise the second sentence to read:

Luminaires consist of hood (including socket, lamp, and ballast), reflector, and glass globe or refractor.

Standard Modificaitons

660-2.01 MATERIALS Under No. 1.b. change title by removing:  Materials Not on the "Qualified Products List:" and replace with:  Materials on the "Qualified Products List:"

E36(01/27/07)

Special Provisions

660-2.01 MATERIALS.  Add the following:

Anchor Bolts:			Section 740-2.02

1.	Equipment List(s) and Drawings. Delete item a in its entirety and the last sentence in item d and substitute the following:

a.	Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items. Provide catalog cuts of materials to the Engineer for review and approval.

d.	Materials Not Requiring Certification: Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

2.	As-Built Plans. Add the following:

Place 1 copy of the controller cabinet diagram, detector assignment sheet and the intersection and phase diagram as reviewed by the Engineer in clear plastic envelopes and attach to the inside of each controller cabinet.

- CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL. In No. 1., Scheduling of Work. Add the following to the first paragraph:  Contact the regional Traffic Signal Technician DOT&PF 24 hours in advance of work on a signal or lighting system. Contact shall be made through the Engineer.

Flashing Beacon systems system must be ready and scheduled for testing by MOA Signal Electronics at least 72 hours prior to stated activation date.

After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, J-boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications.

Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt Patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

In No. 2., Safety Precautions. Add the following:

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

Delete items 3 through 8 in their entirety and substitute the following:

3.	Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors. Provide traffic control to complete this work according to the requirements of Section 643. Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified side by side, to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches, and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit. Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process, shall be accomplished according to Subsection 203-3.03.  Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in subsection 703-2.07.  Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations. Backfill excavations with materials that meet the following requirements

a.	Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift,

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material gleaned free of rocks exceeding a 1 inch maximum dimension. Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to subsection 203-3.04. In other locations, compaction may be as approved by the Engineer.

4.	Welding. Complete welding according to subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval. The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes, which were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface. For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole. Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole. Grind the welds smooth and flush with the adjoining pole and disk surfaces. Repair the damaged finish according to subsection 660-3.01.8.

5.	Removing and Replacing Improvements. The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the non-reusable improvements the Contractor removed to complete the work, unless other items in the contract cover the improvements.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements that the Contractor damaged or removed, that do not conflict with the work and are not scheduled for removal.

Non-reusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings. Reusable improvements include the items that were made before installation. Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition. In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil. Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621. Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment. When the Plans include existing electrical equipment scheduled for removal or relocation, remove and store the equipment listed in the following paragraph without damaging it. Deliver removed equipment not scheduled for reuse to the nearest District Maintenance Station or place specified in the Plans or Special Provisions. Notify the district superintendent or person specified by telephone one-week before planned delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation. The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations. Raze the tops of foundations abandoned in place according to subsection 660-3.02. Fill the holes left by removing junction boxes and foundations with Selected Material, Type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place with a credit taken by the Department. Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer. Note the location and condition of the materials. When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material, which will be paid for as extra work under subsection 109-1.05. Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to subsection 660-3.01.4. Welding and repair the finishes according to subsection 660-3.01.8.

When ordered, the Engineer will pay for repairing damaged finishes on existing equipment according to subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to subsection 660-2.01.1.

Deliver all components of the Chugiak Elementary School flashing beacon system to the MOA Traffic Signal warehouse at 5923 Rowan Street.  The light pole with mast arm left of 478+77 and the two flashing beacon poles shall be delivered to the MOA Traffic Signal Pole Yard at 3rd Ave. & Orca Street. Allow MOA maintenance personnel to select the equipment and pole items they would like to salvage and contractor to dispose of all remaining equipment and pole items. Contact Bill Sosnowski, Foreman, at 343-8355 one week before your tentative delivery date.

Deliver the salvaged materials undamaged to the Anchorage DOT&PF Maintenance and Operations Yard at 5300 East Tudor Road.

Contact the local state Electrician one week before planned delivery.

7.	Field Tests. Electrical circuits must pass the following tests before the Engineer will accept the work for payment. Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis. Retain a copy of test results and give the original documents to the Engineer. Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests. After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests. The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity. Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable. Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet. Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables. The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test. Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors. At 500 volts DC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground. In each multiconductor cable, complete the test between conductors and between each conductor and ground. After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test. Measure each detector loop and lead-in cable system at the controller or detector cabinet. The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit. Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional. Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation. The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Friday, Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes. Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service. Repair the damaged finishes found according to the following:

a.	Galvanized. Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying a minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted. Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy-duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt. Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines. Perform the work in a neat and workmanlike manner. The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

- Add the following new item 9:

9.	Regulations and Code. Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

660-3.02 FOUNDATIONS. Under item 1. Cast-in-Place Foundations., add the following to the first paragraph: Locate the tops of traffic signal post and pole foundations flush with the adjacent finished: walkway, shoulder, or surrounding ground.

1.	Cast-in-Place Foundations. In subparagraph f, revise the second sentence to read: Before placing the form or reinforcing steel cage, remove loose material from the bottom of the hole to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of sub-item i, delete “prior to grouting.” and substitute ”before attaching the skirt.”

In the first sentence of sub-item j, delete “concrete pile caps” and add “foundations”

Add the following to the end of paragraph of sub-item j: Protect foundation anchor bolts from damage before installing controller cabinets.  The Engineer must approve the method used for protection.  This work does not relieve the Contractor of responsibility specified under Subsection 107-1.15.

Replace k with the following:

k.	Furnish anchor bolts that conform to ASTM F1554, the grade and supplementary Charpy V-Notch requirements listed in the Plans. Furnish each anchor bolt with three nuts and two washers.

Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten top nuts to a "snug" condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the "snug" top nuts.

After the top nuts are tightened to the correct torque, use a hydraulic wrench to rotate top nuts an additional one sixth (60) turn, while preventing the leveling nuts from turning.

Add l.

l.	Attach a #4 AWG, bare, copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled #4 AWG, bare, copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, PVC or HDPE, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2. 	Pile Foundations. Add the following new subparagraph:

g.	Use no more than one splice per foundation.  Locate the splice at least 10 feet from the top of pile.

- All foundations.

d.	Replace the last sentence with the following: Backfill the resulting hole with Selected Material, Type A and compact material as directed by the Engineer.

- Replace subsection 660-3.03 with the following:

660-3.03 CONDUIT. Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified. Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits. Install conduits of the sizes specified along the routes detailed on the Plans. When routing is not shown, route conduits as directed by the Engineer.

1.	Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

2.	Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches. Excavate, bed conduits, and backfill trenches according to subsection 660-3.01.3, Excavating and Backfilling.

3.	Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods. Jacking conduits into position is allowed. However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

4.	If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 11/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

5.	Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs. To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

6.	Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box. Extend the ends a minimum of 2 inches beyond the inside wall of the box.

7.	Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs. Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors. Cover the holes with a wrap of approved filter cloth secured with 2 self clinching nylon cable ties.

8.	Keep conduits clean. Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

9.	At the low points of conduit runs, install sumps containing a minimum 2 cubic-feet of coarse concrete aggregate material that conforms to subsection 703-2.02. Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

10.	Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary. Install additional drains and aggregate sumps at the low spots, if any.

11.	Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

12.	Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit. Cut the same number of threads as found on the factory threaded ends. Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges. Do not use slip joints or pieces of running thread pipe.

13.	Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

14.	When standard couplings cannot be used to join conduit components, use approved threaded unions.

15.	Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs. Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings. Furnish tapes with a black legend on a red background.

16.	When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

17.	In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans. Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

18.	Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

19.	Install expansion fittings in conduits that cross expansion joints.

20.	Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs. Double back at least two feet of pull rope into both ends of each conduit.

21.	The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run. Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

22.	Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch. Clean the conduits before pulling in new cables and after removing cables specified to be removed or replaced as follows:

a.	When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

b.	Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

23.	When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit. When extending existing conduits, add no more than 90 degrees of horizontal bend to the extension.

24.	When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

25.	When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

26.	Remove the ends of abandoned conduits from junction boxes that will remain in service.

27.	When Plans call for connecting polyethylene conduit to RMC use an electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits. Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC. Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

- Replace subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES. Install precast reinforced concrete junction boxes of the types specified. For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them. For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

- Junction Box Location

When shown, install junction boxes at the station and offset locations specified. When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement. If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility.  When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing type 1A junction boxes in driveways and in locations subject to use by heavy trucks. When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

- Fout (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits that exclusively contain two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work, otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria. In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade. In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to subsection 660-3.06. Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box. Drains shall consist of coarse aggregate for concrete that conforms to subsection 703-2.02. Minimum drain dimensions include an 18” depth and a length and width equal to those of the junction box it drains. Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker that consists of an antenna encapsulated in a 4 inch diameter red polyethylene ball. Furnish markers that conform to the American Public Works Association standards for locating power. Markers shall respond to locator devices up to 5 feet away, work at all temperatures, and contain no internal power source.

660-3.05 WIRING. Change last sentence of the first paragraph to read: Run signal cabling continuously without splices from the controller cabinet to the termination lugs in the signal housing.  Do not splice conductors within cabinets, poles, signal heads, and luminaires.

Delete the second paragraph in its entirety and substitute the following:

- Conditions

Do not pull conductors into conduits until the following conditions are met:

a.	The prescribed clearances around conduit ends are provided,

b.	Crushed rock sumps are installed under junction boxes,

c.	Conduit ends protrude above the bottom of junction boxes within the prescribed range,

d.	New conduits are free of material that became lodged in them during the completion of the work,

e.	Reused conduits are cleaned according to subsection 660-3.03,

f.	Junction boxes are set to grade, and

g.	Grounding bushings are installed on the ends of metallic conduits.

- Add the following line to Table 660-1 under a. of No. 9:

| LOOP DETECTOR NUMBER | COLORED PAIR |
| --- | --- |
| Usually a spare pair | Orange and Black |

- Delete items 11 and 12 in their entirety and substitute the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin. Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin. Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin. Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases;

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 liner feet or more.

When a cable is spliced it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound. Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide reuseable four piece molds that are held together with stainless steel hose clamps.  Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry. Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full ¼ inch of insulating compound to flow between the splice and the inside of the mold. Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is noncorrosive to copper, and does not support fungi or mold growth.

- Add the following items:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors can not be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector. Insulate the splice with heat shrink tubing. Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductor to 5 feet.

20.	Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

- Replace subsection 660-3.06 with the following:

660 3.06 BONDING AND GROUNDING. Bond and ground branch circuits according to the NEC and the following requirements. Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use. Install size 8 AWG conductors, unless indicated otherwise, except in those conduits that contain circuit conductors larger than 8 AWG. In this case, install a wire equal in size to the largest circuit conductor. Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing. Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings. When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to an #8 AWG conductor and eyelets spaced at 6 inch intervals. Connect bonding jumpers to the grounding conductors using irreversible compression type connectors. Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the 6 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations. For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 4 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

- Replace subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS. Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners: frangible couplings, mechanical grounding connectors, bolts that secure hand hole covers and signal mounting hardware to poles and mast arms. Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces which secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads “out of service” and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation. Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm. After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Flashing Beacon Installation.  When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher.  Furnish and leave 5 feet of cable in the cabinet.  Others will install the fused block and terminate the beacon cables.

Replace Subsection 660-3.09 with the following:

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

One week before school begins in each year of the contract, have the school speed limit sign flashing beacon system fully operational and ready for testing by the MOA Signal Maintenance group.  The flashing beacon system may consist of the existing system, relocated components of the existing system, the new system, or combinations the three aforementioned systems.  All work to provide the fully operational flashing beacon system each year shall be incidental to other items of work.

If existing lighting systems are not kept fully operational as specified herein, the Engineer will reduce the payments under Pay Item 660(22) Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference. Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility. Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment. If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer. If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records. When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 16 feet.

When no longer required, salvage original and Department provided equipment according to the Plans and item 6. Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove other materials used in the temporary systems from the project.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Pay Item 660(14) Temporary Electrolier.  By each electrolier and foundation furnished, installed, and maintained as directed by the Engineer.

Pay Item 660(22) Illumination Price Adjustment.  By the mile of roadway with all or part of the existing illumination systems inoperative.   A divided roadway is considered one roadway.  Ramps are considered a separate roadway.  The Engineer will measure each unlit section less than one mile long as one mile.

660 5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

(1)	General construction requirements,

(2)	Bonding and grounding,

(3)	Bored Casings,

(4)	Completing tests,

(5)	Conductors,

(6)	Conduit,

(7)	Dewatering excavations,

(8)	Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

(9)	Foundations including concrete to complete foundations,

(10)	J-boxes including adjustment to final grade,

(11)	Labeling conductors,

(12)	Maintaining temporary and existing electrical systems,

(13)	Minor routing changes directed by the Engineer

(14)	Preparing as-builts

(15)	Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

(16)	Removing, repairing and replacing improvements

(17)	Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

(18)	Repairing damage to finishes on new equipment

(19)	Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station.

(20)	Wiring,

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system.

Pay Item 660(2) Flashing Beacon System Comlete

1.	Flashing beacon structures

2.	Flashing beacon controller assemblies including assembly testing and preparation, on-site manufacturer assisted start up, minimum 2 year equipment warranty, and training when called for in the Plans.

Pay Item 660(3) Highway Lighting System Complete

1.	Lighting structures.

Pay Item 660(13) Relocate Electrolier.

1.	Relocate lighting structures.

Pay Item 660(14) Temporary Electrolier.

1.	Work to have plans and materials approved.

2.	Temporary electrolier including the structures, foundations, and load centers (as needed) and their removal.  Moving the electroliers, assembly and operational installation, removing and replacing, and installing conductors (in conduit or direct bury only).  Furnishing and installing temporary electrical load centers when existing load centers are not available for use.

3.	Temporary electrolier will be paid on a contingent sum basis at the unit price of $2400/each.  The Engineer does not require a change order/directive for this Pay Item.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

660(2)	Flashing Beacon Signal System Complete	Lump Sum

660(3)	Highway Lighting System Complete	Lump sum

660(13)	Relocate Electrolier	Each

660(14)	Temporary Electrolier	Contingent Sum

CR660(07/01/09)

Section 661
Electrical Load Centers

Special Provisions

661-1.01 DESCRIPTION.

Add the following:  Furnish and install load center assembly Type 1A with an integral uninterruptible power supply (secondary power source) to power intersection traffic and pedestrian signals (no lighting) and control equipment during interruptions to the utility power (primary power source).

Replace the second paragraph and load center type list with the following:

Use load centers of the following types as shown on the load center detail sheets:

Type 1:	Pad mounted with underground service (large)

Type 1A:	Pad mounted with underground service (small)

Type 1A with UPS:	Pad mounted with underground service (large)

Type 2:	Post mounted with underground service

Type 3:	Pole mounted with overhead service

Add the following Subsections 661-1.02 Acronyms, 661-1.03 Definitions:

661-1.02 ACRONYMS.

BBS	Battery Backup System

LC	Load Center

LCD	Liquid Crystal Display

LED	Light Emitting Diode

LC/UPS	Load Center with Integral Uninterruptible Power Supply

MBPS	Power Transfer Switch

MMU	Malfunction Management Unit

PLC	Powerline Communications

PTS	Power Transfer Switch

THD	Total Harmonic Distortion

UPS	Uninterruptible Power Supply

661-1.03 DEFINITIONS.

BUCK-BOOST.  Switch-mode voltage regulator in which voltage can be above or below the input voltage.

661-2.01 MATERIALS. Add the following:

- Anchor Bolts		Section 740-2.02

Load Center.  Replace the 1st paragraph with the following:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

Add the following:

1.	Load Center with Integral Uninterruptible Power Supply (LC/UPS).

Design, fabricate, deliver, and install as specified in the Specifications and Plans.

a.	Design of LC/UPS

Design and manufacture for outdoor applications and the environment specific to the project location.

The UPS shall be designed to provide for efficient fabrication and assembly using standard, readily available industry components facilitating the current project requirements.  The design shall provide for future quick replacement of the complete system or the individual components.  The design shall allow the maintenance department to quickly acquire a replacement UPS or replacement parts and personnel to easily remove the existing UPS and install the new UPS or UPS parts as may be needed (complete turnkey system with all necessary hardware).  Special tools shall not be required to install the UPS.

The design shall specifically include a shelf-mount, rack-mount, swing-tray mount, or combination thereof.  The UPS and PTS units individually shall not exceed 5.25” in height.  If swing-trays are used, a minimum of 6 bolts/fasteners shall be used to secure the tray to the cabinet rack.

b.	Submit.

Submit shop drawings, equipment technical specifications, and certifications for review and approval.  Do not begin manufacture of the LC/UPS prior to submitting and receiving approval of shop drawings and required certifications for the system assembly, the individual equipment pieces, components, and hardware.  Provide documentation confirming delivery dates of the individual pieces of equipment and overall system in-place completion date satisfying the project construction schedule.

c.	Manufacturers.

(1)	Meyers Power Products, Inc.

LC/UPS:  Power Model MEUG35-PB Metered/Unmetered with MP2000 UPS

Address:

725 E. Harrison Street

Corona, CA 92879

Ph:  (951) 520 - 1900

(2)	Or equal:

Manufacturers satisfying the requirements of the Plans, Specifications and Contractual requirements for the assembled system, including delivery, quality and timeliness of installation and responsive remote and onsite service, shall submit, as a substitution, for review and approval.

d.	UPS Run Time Capacity.

Power intersection LED traffic, pedestrian signals, and control equipment for the consecutive time periods noted below: (lighting and traffic controller auxiliary circuits are not included)

| RUN TIME CAPACITY |  |
| --- | --- |
| Operation Mode | Continuous Uninterruptible Operation Time* |
| Normal | 2 Hours |
| Flash | 2 Hours |
| Total (Normal + Flash) | 4 hours |

*Continuous uninterruptible operation time at 77 °F (25 °C) at load 875 W.

e.	Operation.

The transfer from utility power to the UPS shall not interfere with the normal operation of the traffic controller, MMU and other peripheral devices within the traffic controller assembly.

The MBPS shall be rated at 240 VAC, 40 Amps minimum.  The MBPS shall allow replacement of the UPS without interrupting power to the intersection. The MBPS and PTS shall be separate units.  Without interrupting power to the intersection, the MBPS shall permit the replacement of the PTS, and the MBPS and PTS shall each permit replacement of the UPS.

The UPS shall use a temperature compensated battery charging system. The charging system shall compensate over a range of 2.5 to 4 mV / °C / Cell and be rated 10 Amps at 48 VDC. Batteries shall not be charged when battery temperature exceeds 122 °F ± 5.4 °F (50 °C ± 3 °C). The temperature sensor shall be external to the UPS unit and supplied with 9' - 10" of wire.

The UPS shall automatically and continually monitor and display the current percent of battery power available for use.  A "Battery Not Connected" alarm shall be issued if battery power is not present. When utilizing battery power, the UPS output voltage shall be between 110 VAC and 125 VAC, pure sine wave output with THD < 3% at 60 Hz +/- 3 Hz.

The UPS shall provide the power beyond the temperature that would be field programmable for an external fan located in the same or in a separate battery cabinet. The temperature setting shall be adjustable locally and remotely.  The temperature range shall be from +68 °F to +131 °F (+20 °C to +55 °C) in 1 degree F increment.

In the event of UPS failure, battery failure, or complete battery discharge, the PTS shall revert to the utility or line mode (in a de-energized state) where utility power is supplying the cabinet.

f.	Components:

The LC/UPS shall include all equipment, hardware, foundation and foundation materials, interconnecting wiring and other materials for a complete operable LC/UPS inclusive of materials and performance requirements specified herein, but not limited to:

(1)	UPS

(2)	UPS Controller Unit

(a)	Re-settable Inverter Event Counter

(b)	Cumulative Inverter Timer

(c)	Event log, Time and Dated (stores the last 100 events, minimum)

(d)	Self-Test (programmable in 1-minute increments from 1 min. to 255 min.)

(e)	Low Battery Alarm (programmable, adjustable in increments of .25 VDC)

(f)	Buck-Boost Mode (UPS shall be capable of Buck-Boost 10% ±)

(3)	PTS (activated during Buck-Boost operations; transfer times 10 milliseconds)

(4)	MBPS (non-electrical)

(5)	Batteries and Battery Enclosure

(6)	Battery Heater Mats

(7)	Cabinets and Enclosures

(8)	External Fan

g.	UPS Access and Password Protection.

	Provide local and remote access.

	Provide the UPS with a default password.

Access:

(1)	Local – provide an LCD display screen and touch pad as part of the UPS

(2)	Remote

(a)	RS232 interface

(b)	USB interface

Local and remote access shall provide same access use.

User:

(1)	The “User” includes the Department Traffic Engineers and Maintenance Personnel.

(2)	The User shall be able to monitor the following at the LC/UPS cabinet (locally) and remotely.

Use:

(1)	Provide the Department with the default password and administrative authority to add/change password protection.  Make the procedure intuitive and direct.

(2)	Control, programming, maintenance, and inquiry (view and adjust) including but not limited to:

Monitor:

(a)	Time,

(b)	Date,

(c)	Current battery charge status,

(d)	Input/output voltages,

(e)	Power output,

(f)	Battery temperature,

(g)	Field programmable relay settings

Current status shall be indicated by LED lights:

(a)	Green – Flashing for battery back-up mode

(b)	Green – Steady ON for normal line mode operation

(c)	Red – Flashing for ALARM conditions

(d)	Red – Steady ON for FAULT conditions

Maintenance Controls - password protect:

(a)	UPS Inverter ON/OF,

(b)	Battery Test,

(c)	Event Log (Retrieving, viewing and printing in plain English),

(d)	Changing Default Settings

Other settings:

(a)	Temperature Settings,

(b)	Re-Settable Inverter Event Counter,

(c)	Cumulative Inverter Timer,

(d)	Self-Test,

(e)	Low Battery Alarm

(3)	Upload firmware software updates of the non-volatile, read-only memory type.

h.	Specifications.

(1)	Environmental:

The operating temperature for the (UPS), (PTS) and (MBPS) shall be -34.6 °F to 165.2 °F (-37 °C to +74 °C).

(2)	UPS Input/Output:

| UPS SPECIFICATIONS |  |
| --- | --- |
| Input Specifications |  |
| Nominal Input Voltage | 120 VAC, Single Phase |
| Input Voltage Range | 120 VAC ± 25% |
| Input Frequency | 60 Hz ± 5% |
| Output Specifications |  |
| Nominal Output Voltage | 120 VAC, Single Phase |
| Power Rating* | 2000 VA (1500 Watts) |
| Output Frequency | 60 Hz ± 5% |
| Voltage Wave Form | Sine Wave, THD < 3% |
| Efficiency (nominal) | 95 – 97% |

*The UPS power rating of 2000 VA / 1500 Watts shall be with a minimum inverter efficiency of 80%.670-

(3)	Loss/Restoration of Utility Power:

When the utility line voltage is outside the High and Low Limits (100 & 130 VAC respectively set as defaults), the UPS shall transfer the load to battery power. The UPS shall return to line mode when the utility power has been restored to above 105 VAC or below 125 VAC; or the UPS shall return to line mode when the utility power is back to nominal for more than 30 seconds (the line qualification time).  The line qualification time shall be adjustable to 3, 10 or 30 seconds.

The maximum transfer time allowed, from disruption of normal utility line voltage to stabilized UPS line voltage from batteries, shall be 65 milliseconds. The same maximum allowable transfer time shall also apply when switching from UPS line voltage to utility line voltage.

(4)	Battery(s):

(a)	Batteries as part of the UPS provide the power.

Individual batteries shall be rated at 105 Amp-Hour minimum. Batteries shall be 12 VDC type and shall be easily replaced and commercially available off the shelf. The battery system used in the UPS shall consist of 4 batteries and shall be of a voltage not to exceed 60 VDC. Batteries shall be provided with quick disconnect terminals and a polarized - keyed battery cable for easy field installation.

Batteries shall be deep cycle, sealed prismatic lead-calcium based AGMNRLA (Absorbed Glass Mat/Valve Regulated Lead Acid) batteries - able to withstand extreme temperature. Batteries shall be certified to operate over a temperature range -4 °F to 165.2 °F (-20 °C to +74 °C).  The batteries shall be provided with appropriate interconnect wiring and a corrosion-resistant stationary or swing-out mounting tray and/or brackets appropriate for the cabinet into which they will be installed as specified in “Design of LC/UPS”.

Batteries shall indicate maximum recharge data and recharging cycles. Recharge time for the battery from protective low cutoff to 80% or more of full battery charge capacity, shall not exceed twenty (20) hours.

(b)	Battery Compartment:

The battery cabinet shall be vented through the use of louvered vents, filter, and one thermostatically controlled fan operated from the UPS. The fan will automatically turn ON at the temperature programmed into the UPS.

External battery compartments may be used to satisfy environmental and physical requirements.  When submitting shop drawings, material and equipment submittals, request in writing and demonstrate graphically the need for an external compartment(s).

(c)	Back-Feed and Other Protections:

The UPS shall be equipped to prevent a malfunction feedback to the cabinet or from feeding back to the utility service per UL 1778, Section 48 "Back-Feed Protection Test". The upstream back-feed voltage from the UPS shall be less than 1 VAC for the protection of persons accessing the equipment.

The UPS shall have lightning surge protection compliant with IEEE/ANSI C.62.41 for 2000 VAC.

(5)	Relay Contacts:

The UPS shall provide the user with 6 sets of fully programmable, relay contacts of type NO/NC, panel-mounted, potential free and rated 1 Amp, 120 VAC and labeled C1 through C6. Each relay's setting shall be programmable to activate under conditions through local access or remote access.  The minimum number of relay settings is outlined below.

Independently configure relay contacts C1 through C6 to activate under the following conditions:

(a)	ON BATTERY - relay activates when BBS switches to battery power.

(b)	LOW BATTERY - relay activates when batteries have reached a specified level of remaining useful capacity while on battery power. The specified level shall be adjustable from 0 to 100%.

(c)	TIMER- relay activates after being on battery power for a specified amount of time. The specified time shall be adjustable from 0 to 8 hours.

(d)	ALARM - relay activates after a specific or general alarm is detected. These alarm conditions include:

	Line frequency

	Low output voltage

	No temperature probe

	Overload

	Batteries not connected

	High temperature

	Low temperature

The relay shall be programmed to activate when any of these alarm conditions occur, or when a specified condition occurs.

(e)	FAULT- relay activates after a specific or general fault is detected. These fault conditions include:

	Short circuit

	Low battery voltage

	High battery voltage

	High internal temperature

	Overload

The relay shall be programmed to activate when any of these fault conditions occur, or when a specific condition occurs.

(f)	OFF- relay is disabled and shall not activate under any condition.

(6)	Default Relay Settings:

(a)	Relay C1 and C2 shall be set to activate whenever the UPS transfers to battery power and shall be labeled "ON BATT."

(b).	Relays C3 and C4 shall be set to activate whenever the batteries reach 40% of remaining useful capacity and shall be labeled "LOW BATT."

(c)	Relays C5 and C6 shall be set to activate whenever the UPS has been on battery power for 2 hours and shall be labeled "TIMER."

Terminal block position 19 & 20 shall be set to activate a self-test. This test confirms that a unit can transfer into and out of battery mode while supporting the output load.

(7)	Load Center for Temporary Power:

Use the following load centers for distribution of power for temporary lighting and signals including the control systems.  Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

(a)	Permanent load centers installed in their plan location.

(b)	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if approved.

(c)	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked “Suitable for use as service equipment.”

Equipment List(s) and Drawings.

Delete No. 1. and replace with the following:

1.	Materials on the Qualified Products List:  The Qualified Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

Under No. 2. Change title by removing:  Materials Not on the "Approved Products List." and replace with Materials Not on the "Qualified Products List."

Add No. 3.:

3.	Materials Not Requiring Certification:  Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.  Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.  Replace the 11th paragraph with the following:

Install two ground rods at least 6 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Add the following:

New Load Centers Type 1A and Type 1A with UPS.  Coordinate with existing and or new service utilities.

661-3.02 CONTRACTOR’S WARRANTY.

Load Center Type 1A with UPS (LC/UPS)

The period of performance for this warranty shall be two (2) years from the time the Department assumes maintenance responsibilities.  The price for this warranty will be included in the bid price for the LC/UPS assembly.

The LC/UPS system, all equipment, components, hardware, accessories, factory and field workmanship shall be warranted against failure from normal usage during the first two years of service from the time the Department assumes maintenance responsibilities.  Manufacturer warranties, guarantees, and instruction sheets and all parts used in the work shall be delivered to the Engineer before the Department assumes maintenance responsibilities.  Where repairs cannot be made via telephone support or modem the Contractor shall respond at the site to service or repair the malfunctioning equipment within two (2) weeks of the initial notification of the malfunction.  All materials and equipment shall be repaired or replaced at the Manufacturer’s expense including labor to complete the repair and an onsite representative to inspect and certify the repaired LC/UPS meets the requirements of the original specifications using original equipment manufacturer (OEM) parts, and equipment.  All expenses associated with the repair shall be included in the Manufacturer’s Warranty.

The warranty period will stop at the time of the failure.  The Manufacturer shall warrant the repairs as part of the original warranty.  At the completion of the repairs, the Manufacturer shall supply the Department Traffic Engineer with additional equipment and part warranties, guarantees, and instruction sheets as applicable to the repairs as required for the original equipment and work.  The Manufacturer will supply a letter certifying the repairs satisfy the specifications for the original work.  The remaining time of the warranty, the original warranty period less the time passed from the date established as the warranty start date, will begin after the repair is complete and the Department Traffic Engineer receives the repair certification letter.

661-5.01 BASIS OF PAYMENT.  Add the following:

The following work is subsidiary to 661 Pay Items:	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

	All work including, but not limited to, contacting and coordinating with the utilities for service; the utility costs, fees, installation, activation, maintenance and usage payments until the Engineer provides the notice of final acceptance.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

661(2)	Load Center, Type II	Each

CR661(070109)

Section 670
Traffic Markings

Special Provisions

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings	Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings	Subsection 712-2.17

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads, and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete No. 4 and substitute the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

Marking thickness will be measured from the pavement surface.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Crosswalk Markings.

Groove the area for inlaid markings to a depth of 125 mils.  Apply marking for crosswalks to yield a thickness of 125 mils.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

INLAID

(1)	For all inlaid markings other than longitudinal lines measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

670-3.05 PRELIMINARY SPOTTING.  Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01).

670-3.06 TOLERANCE FOR LANE STRIPING.  Delete this subsection and add the following:

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within 4-inches of the planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

Add the following Subsection:

670-3.07 CONTRACTOR’S WARRANTY.  Provide a warranty, for the Methyl Methacrylate Pavement Markings, as specified herein.

The period of warranty is 2 years.  The warranty period will start on the date the Engineer accepts the work and authorizes payment.

Pavement markings that do not satisfy the specified performance requirements will be repaired and or replaced by the Contractor.  The Department will determine if the failed markings will be repaired or replaced.  The Contractor will be notified, in writing, of the marking failure(s) and the corrective measures required including repairs and or replacement.

The Contractor will have 6 months to complete repairs.  The Contractor will coordinate the repair start and end dates with the Department.

The warranty period, for all project MMA pavement markings, will stop until corrective work is approved complete by the Department.

Performance Requirements.

1.	Retroreflectivity.  If retroreflectivity becomes a concern during the warranty period, the Engineer will measure the retroreflectivity of the area in question.  The roadway surface will not be cleaned in preparation for taking readings, but areas of obvious contamination or debris will be avoided.

a.	Longitudinal sample areas will be a minimum length of 500 feet and have at least three samples taken.

b.	Transverse, symbols and gore samples will be three per transverse line or symbol.

Table 670-1

PAVEMENT MARKING MINIMUM RETROREFLECTIVITY REQUIREMENTS

| Marking Color | Retroreflectivity, Minimum Levels |  |  |
| --- | --- | --- | --- |
|  | Initial Retroreflectivity a | 6 Months b | 2 Years b |
| Yellow, White | 200 mcd/m2-lux | 150 mcd/m2-lux | 40 mcd/m2-lux |

Footnotes:

a.	The initial retroreflectivity readings will be completed after the MMA has cured and no more than 7 days prior to the Engineer accepting the work.

b.	The 6 month and 2 year readings will be measured from the date of the initial retroreflectivity readings.

2.	Color Stability.  The pavement markings shall retain color throughout the warranty period.  Yellow striping will be compared to the PR-1 chart, and shall meet 33538 Federal Yellow.  White striping shall have a minimum daylight reflectance of 84 throughout the Warranty period.

3.	Adhesion.  For the purpose of the warranty a cumulative 5% or greater loss of longitudinal line of any 500 foot segment of marking and 5% or greater loss of each transverse line, gore stripe and symbol, due to nonadhesion, shall constitute failure of the material in that segment.

Repair.  Repair pavement markings as specified by the Department.

Replacement.  Replace pavement markings as specified in Section 670-3.01 Construction Requirements 4.f. Application and as specified by the Department.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measure from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Add the following No. 4:

4.	Linear Foot Basis.  Inlaid crosswalk pavement markings will be measured by the linear foot of 24-inch wide line.

670-5.01 BASIS OF PAYMENT.  Add the following:

Payment for Methyl Methacrylate (MMA) Pavement Markings includes furnishing the Warranty.  Payment for the installation of the pavement markings will be limited to 80% of the amount due until the Department has received a signed Warranty.

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10F)	MMA Pavement Markings, Transverse and Gore Inlaid	Linear Foot

Delete Items 670(11) and 670(12).

CR246(01/01/09)

Add the following Section:

Section 690
Erosion, Sediment And Pollution Control – Measures

690-1.01 DESCRIPTION.  Furnish, install and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

•	Permanent Measures – include, the materials, hardware, equipment and labor required for installation and maintenance of erosion, sediment and pollution control material(s).

•	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control	Section 641

Silt Fence	Section 633

Seeding	Section 618

Soil Stabilization	Section 619

690 2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials	Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL. BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil blinders, non-erodible cover, dustless sweeping, dust palliatives. Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.03 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the NPDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls: By length, measured along the centerline of the fiber roll, complete in place.

Manufactured Inlet Protection Systems:  By each, complete in place.

Sandbag Inlet Sediment Trap:  By each, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

CR690(022309)

Replace Section 701 with the following:

Section 701
Hydraulic Cement and Pozzolan

701-1.01 GENERAL. Meet the following general requirements for all cementitious materials furnished:

Provide product from only one mill for each brand and type of cementitious material except to reduce excessive air entrainment when using air-entraining cement.

Cement may be shipped from pretested approved bins.

Before using, retest Portland cement that has been stored longer than 3 months if bagged or 6 months if bulk for compressive strength, time of setting, and loss on ignition according to AASHTO M 85. Store separately different types or brands of cementitious materials, or cementitious materials from different mills.

Protect cementitious materials from dampness during shipment and storage. Do not use partially set cement or cement which contains caked lumps. Do not use cement salvaged from discarded or used bags.

701-2.01 PORTLAND CEMENT. Meet AASHTO M 85, Type I, II, or III, including the low-alkali cement requirement shown in Table 2. Furnish a certificate of compliance meeting AASHTO M 85, Section 15 as required by Subsection 106-1.05.

701-2.02 BLENDED HYDRAULIC CEMENT. Meet AASHTO M 240, Type IP. Furnish a certificate of compliance meeting AASHTO M 240, Section 14 as required by Subsection 106-1.05.

701-2.03 FLY ASH. Class C or Class F meeting AASHTO M 295, including optional chemical requirements as set forth in Table 2 and with the following revisions:

Table 1 Chemical Requirements

Moisture content, max percent	1.0

Table 3 Physical Requirements

Amount retained when wet-sieved on

45-μm (No. 325) sieve, max percent	30

701-2.04 SILICA FUME. Meet AASHTO M 307. Furnish a certificate of compliance meeting AASHTO M 307, Section 23 as required by Subsection 106-1.05.

701-2.05 GROUT. Non-shrink, non-corrosive, non-metallic, cement-based grout meeting ASTM C 1107, except develop a 28-day compressive strength of at least 9,000 psi from specimens made in accordance with ATM 507.

701-2.06 DS GROUT. Use drilled shaft (DS) grout  that conforms to the following requirements:

1.	Portland Cement Type I or Type II cement meeting the requirements of Subsection 701-2.01.

2.	Fine Aggregate: Use fine aggregate meeting Subsection 703-2.01, except 100 percent passing the No. 4 sieve.

3.	Potable Water: Use water meeting the requirements of Subsection 712-2.01.

4.	Proportioning: Mix grout in proportions using at least 564 lbs/yd3 of Portland cement, fine aggregate, and with enough water to produce a flowable mixture.  Do not exceed 67 gal/yd3 of water.

Thoroughly mixed DS grout before injecting into soil surrounding drilled shaft casing and CSL tubes.

701-2.07 POST-TENSION GROUT. Use pre-packaged thixotropic grout formulated specifically for bonded post-tensioned concrete structures in aggressive exposures.

Ship grout in weather proof packages, plainly marked with the name, weight, and volume of the grout, together with the lot number, date of manufacture, mixing instructions, and the name and address of the manufacturer.

Protect grout against dampness. Do not use grout that has become partially set or which contains lumps of caked grout. Do not use grout salvaged from discarded or used bags. Do not use grout with a total time from manufacture to usage in excess of six months unless the manufacturer tests and certifies the product meets the requirements in Table 701-1.

Batch grout using the entire contents of each bag in accordance with all of the manufacturer’s written recommendations and instructions.

1.	Materials. Use grout that conforms to the following requirements:

a.	Portland Cement. Type I or Type II cement meeting the requirements of Subsection 701-2.01.

b.	Potable Water. Use water meeting the requirements of Subsection 712-2.01.

c.	Fly Ash. Class C or Class F fly ash meeting the requirements of Subsection 711-2.03. Limit fly ash content to a maximum of 20% by weight of Portland cement.

d.	Ground Granulated Blast Furnace Slag. Grade 120 slag conforming to ASTM C 989. Limit blast furnace slag content to a maximum of 40% of the weight of Portland cement.

e.	Silica Fume. Silica fume conforming to ASTM C 1240. Limit silica fume content to a maximum of 15% of the weight of Portland cement.

f.	Set Control and Water-Reducing Admixtures. Type D, Type F, and Type G admixtures conforming to AASHTO M 194. Limit Type F and Type G admixtures to 45 oz. per 100 pounds of Portland cement. Consider adding these to Section 711.

g.	Air Entraining Admixtures. Do not use grout with air entraining admixtures.

h.	Expansion Causing Admixtures. Do not use grout with expansive cement or expansion causing admixtures that contain aluminum powder or components that produce hydrogen, carbon dioxide or oxygen gas.

i.	Corrosion Inhibitor Admixtures. Do not use grout with corrosion inhibitor admixtures.

j.	Pumping Aid Admixtures. Do not use pumping aid admixtures.

2.	Physical Properties. Use grout that satisfies the requirements in Table 701-1.

3.	Material Certification. Submit 5 copies of a quality control data sheet covering the chemical and physical tests conducted on the grout for the material in each shipment. Submit 5 copies of a certified test report from an independent laboratory, audited by the Cement Concrete Research Laboratory that shows the material meets all property requirements.

TABLE 701-1

POST TENSION GROUT

| Property | Requirements | Test Method |
| --- | --- | --- |
| Total Chloride Ions | Max. 0.08% by weight of cementitious materials | ASTM C 1152 |
| Setting Time | Min. 3 hours Max. 12 hours | ASTM C 953 |
| Strength | Min 3000 psi after 7 days Min 5000 psi after 28 days | ASTM C 942 |
| Permeability @ 28 days | Max. 2500 Coulombs at 30 V after 6 hours | ASTM C 1202 |
| Volume Change | Maximum 0.0% after 24 hours Maximum +0.2% after 28 days | ASTM C 1090 (modified)* |
| Expansion | ≤ 2.0 % for up to 3 hours | ASTM C 940 |
| Fluidity | Immediately after mixing: Min. 9 sec. Max. 20 sec. 30 minutes after mixing: Max. 30 sec. | ASTM C 939 (modified)** |
| Wick Induced Bleed | Max 0.0% | ASTM C 940 (modified)*** |
| Wet Density | Report maximum and minimum obtained test value in pounds per cubic foot | ASTM C 185 |

*	Modify ASTM C1090 to include verification at both 24 hours and 28 days.

**	Modify the ASTM C 939 test by filling the flow cone to the top instead of to the standard level. The efflux time is the time to fill a one liter container placed directly under the flow cone.

***	Modify ASTM C940 to conform with the wick induced bleed test as follows:

(a)	Use a wick made of a 20-inch length of ASTM A416 seven-wire 1/2 inch diameter strand. Wrap the strand with 2-inch wide duct or electrical tape at each end prior to cutting to avoid splaying of the wires when it is cut. Degrease (with acetone or hexane solvent) and wire brush to remove any surface rust on the strand before temperature conditioning.

(b)	Condition the dry ingredients, mixing water, prestressing strand and test apparatus overnight at 65° F to 75° F.

(c)	Mix the conditioned dry ingredients with the conditioned mixing water and place 800 ml of the resulting grout into the 1,000 ml graduate cylinder. Measure and record the level of the top of the grout.

(d)	Completely insert the strand into the graduated cylinder. Center and fasten the strand so it remains essentially parallel to the vertical axis of the cylinder. Measure and record the level of the top of the grout.

(e)	Store the mixed grout at the temperature range listed above in (b).

(f)	Measure the level of the bleed water every 15 minutes for the first hour and hourly for two successive readings thereafter.

(g)	Calculate the bleed water, if any, at the end of the three hour test period and the resulting expansion per the procedures outlined in ASTM C940, with the quantity of bleed water expressed as a percent of the initial grout volume. Note if the bleed water remains above or below the top of the original grout height. Note if any bleed water is absorbed into the specimen during the test.

Section 703
Aggregates

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

- TABLE 703-2

AGGREGATE FOR UNTREATED BASE

(Percent Passing By Weight)

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| ¾ inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No, 4 sieve before crushing aggregates for Type IV, V and R mixtures.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet the following requirements:

| Description | Specification | Type IIA | Type I, IIB, III | Type IV | Type V, R |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP 61 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % 1:5 1:3 | ATM 306 | 8 20 | 8 - | 8 - | 8 20 |
| Absorption, max. % | AASHTO T85 | 2.0 | 2.0 | 2.0 | 2.0 |

Fine Aggregate  Aggregate passing the #4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type IV, V, and R mixes:

•	do not blend back natural sand

•	shall be non-plastic as determined by WAQTC FOP for AASHTO T 90

•	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-3
BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

Percent Passing by Weight

| SIEVE |  |  | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II |  | Type III | Type IV | Type V | Type R |
| 1 inch | 100 |  |  |  |  |  |  |
| ¾ inch | 80-90 | 100 |  |  |  | 100 | 100 |
| ½ inch | 60-84 | 75-90 |  | 100 | 100 | 65-90 | 70-100 |
| 3/8 inch | 48-78 | 60-84 |  | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 |  | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 |  | 26-70 | 35-50 | < 45 | 20-32 |
| No. 16 | 9-44 | 10-44 |  | 16-59 | 20-40 | < 35 | 15-25 |
| No. 30 | 6-34 | 7-34 |  | 9-49 | 15-30 | < 25 | 10-20 |
| No. 50 | 5-24 | 5-24 |  | 6-36 | 10-24 | < 20 | 7-15 |
| No. 100 | 4-16 | 4-16 |  | 4-22 | 5-15 | < 12 | 5-12 |
| No. 200 | 3-8 | 3-8 |  | 3-8 | 4-8 | 3-8 | 4-10 |

Note:

1.	No tolerance is allowed beyond the Broad Band Limits of the No. 200 Sieve.

2.	For Type R, the mix design gradation JMD shall provide a minimum of 8 % difference of percent passing the No. 4 and the No. 8 sieve.

CR703 (11/27/09)

Add Subsection 703-2.13 as follows:

703-2.13 STRUCTURAL FILL. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

TABLE 703-9

REQUIREMENTS FOR GRADING FOR STRUCTURAL FILL MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3 in. | 100 |
| 3/4 in. | 75-100 |
| No. 4 | 35-65 |
| No. 40 | 0-50 |
| No. 200 | 0-6 |

Add Subsection 703-2.14 as follows:

703-2.14 AGGREGATE FOR ABRASIVE FINISH. Crushed sand consisting of sound, tough, durable rock of uniform quality, oven dried, and stored in moisture-proof bags. Free from clay balls, vegetative matter, or other deleterious matters (AASHTO T 112). Not coated with dirt or other finely divided mineral matter. Meet the grading requirements of Table 703-10 (WAQTC FOP for AASHTO T 27/T 11).

TABLE 703-10

REQUIREMENTS FOR SAND FOR ABRASIVE FINISH

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| No. 8 | 100 |
| No. 20 | 0-5 |

Replace Section 705 with the following:

Section 705
Joint Materials

705-2.01 JOINT FILLERS. Meet AASHTO M 213.

705-2.02 JOINT SEALER.

Silicone Joint Sealer	ASTM D 5893

Hot Pour Joint Sealer (Asphalt)	AASHTO M 324, Type IV

Hot Applied Joint Sealer (Concrete)	AASHTO M 282

Hot Pour Joint Sealant (Concrete, Fuel-Resistant)	ASTM	D 3581

705-2.03 BRIDGE SEAL.

1.	Preformed Strip Seals and Compression Seals. Use preformed seals

.  Use preformed material meeting ASTM D 3542.

Submit five copies of a certified test report for preformed seal materials.

2.	Silicone Expansion Joint Sealant. Use formed-in-place seals composed of 100 percent silicone meeting the requirements of ASTM D 5893, Type SL (Self-Leveling) for horizontal joints and ASTM D 5893, Type NS (Non-Sag) for curb, rail, and other vertical joints. Do not use acid cure sealants.  Ensure the silicone sealant is compatible with the surface to which it is applied. Use a backer rod meeting ASTM C 578 when the joint width is 1/2 inch or greater.

705-2.04 JOINT MORTAR. Use a mixture of one part portland cement and two parts approved sand with water as necessary to obtain the required consistency. Use mortar within 30 minutes after its preparation.

705-2.05 FLEXIBLE WATERTIGHT GASKETS.

1.	Ring gaskets for rigid pipe and precast manhole sections meeting AASHTO M 198.

2.	Ring gaskets for flexible metal pipe meeting ASTM C 443. Continuous flat gaskets for flexible metal pipe meeting ASTM D 1056, Grade 2B3. Use gaskets with a thickness 1/2 inch greater than the nominal depth of the corrugation for bands with projections or flat bands and 3/8 inch for corrugated bands.

705-2.06 EXPANDED POLYETHYLENE. Use closed-cell expanded polyethylene planks with a density of 2.2 +/- 0.5 lb/ft3 as determined by ASTM D3575 and with a maximum compressive deflection of 50% at 17 psi +/- 5 as determined by ASTM D3575.

Section 706
Concrete And Plastic Pipe

Standard Modifications

706-2.06 PLASTIC PIPE.  Delete the first sentence and replace with the following:

Semi-rigid, smooth-wall pipe meeting the following:

E63 (07/28/08)

Replace Section 709 with the following:

Section 709
Reinforcing Steel and Wire Rope

709-2.01 REINFORCING STEEL.

1.	Reinforcing Steel Bars. Furnish deformed steel bars of the type, grade, and size as specified. For steel reinforcing bars used in bridge structures, furnish bars meeting ASTM A 706. For all other structures, furnish bars meeting AASHTO M 31, Grade 60.

2.	Headed Reinforcing Steel Bars. Furnish headed steel bars meeting the requirements of ASTM A 970. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

3.	Epoxy-Coated Reinforcing Steel Bars. Furnish epoxy-coated steel bars meeting the requirements of AASHTO M 284. Coat epoxy-coating reinforcing steel in an epoxy coating applicator plant certified in accordance with the Concrete Reinforcing Steel Institute (CRSI) Voluntary Certification Program. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

4.	Steel Wire. Furnish plain steel wire of the size specified that meets the requirements of AASHTO M 32.

5.	Steel Bar Mats. Furnish deformed steel bar mats of the type, grade, size, and spacing as specified. Unless otherwise noted, furnish steel bar mats meeting the requirements of AASHTO M 54, Grade 60.

6.	Steel Welded Wire Fabric. Furnish plain steel welded wire fabric of the size and spacing specified that meets the requirements of AASHTO M 55.

7.	Epoxy-Coating Patch Material. Furnish epoxy-coating patch material meeting the requirements of AASHTO M 317.

8.	Certification. Submit five copies of a certified test report covering chemical and physical tests conducted on all reinforcing steel to the Department for the material in each shipment.

709-2.02 WIRE ROPE OR WIRE CABLE. Meeting AASHTO M 30, 3/4 inch Type 1, Class A.

Section 710
Fence and Guardrail

Standard Modification

712-2.04 METAL BEAM RAIL.  Meet AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding and riveting.

(07/28/08)E64

Special Provisions

710-2.03 CHAIN LINK FABRIC. Change Class D coating to Class C coating.

R275(9/13/04)

Replace Section 711 with the following:

Section 711
Concrete Curing Materials and Admixtures

711-2.01 CURING MATERIALS.

Burlap Cloth made from Jute or Kenaf	AASHTO M 182, Class 4

Sheet Materials for Curing Concrete	AASHTO M 171

Liquid Membrane-Forming

Compounds for Curing Concrete	AASHTO M 148, Type I-D Class B, except

do not use compounds containing linseed oil.

711-2.02 CHEMICAL ADMIXTURES.

Air-Entraining Admixtures	AASHTO M 154

Water-Reducing Admixtures	AASHTO M 194

Set-Retarding Admixtures	AASHTO M 194

Set-Accelerating Admixtures	AASHTO M 194

Section 712
Miscellaneous

- Special Provisions

Replace Section 712-2.01  with the following:

712-2.01 WATER. Use water in mixing or curing concrete that is clean and free of oil, salt, acid, alkali, sugar, vegetable or other substances injurious to the finished product. Meet the suggested requirements of AASHTO T 26. Use mix water that contains less than 500 parts per million of chlorides as CI or of sulphates as SO4. Water known to be of potable quality will not require testing. Where the source of water is relatively shallow, enclose the intake to exclude silt, mud, grass, or other foreign materials.

Use water for irrigating trees, plants, and seeded areas that is free of elements harmful to plant growth.

Standard Modification

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS. In Gray iron castings, delete text and replace with: AASHTO M 306 and AASHTO M 105, Class 35B.

E46(01/27/07)

712-2.11 GUARDRAIL TERMINALS. Add the following as the first paragraph:

Meet coating requirements of AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding and riveting.

(07/28/08)E64

- Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retroreflectivity.  For the two year specified Warranty Period and retroreflectivity levels, Subsection 670-3.07.  The Engineer will determine the test location.

(010109)CR246

Add  the following Section:

712-2.19 EPOXY CARTRIDGE SYSTEM. Use an epoxy cartridge system that consists of the following:

1.	A bonding material that is a two-component epoxy contained in a cartridge having two separate chambers

2.	An applicator that is a special dispensing gun having a replaceable static mixing nozzle.

3.	Use an epoxy cartridge system appropriate for the service temperature and ambient concrete temperature at the time of installation.

Epoxy cartridge systems are subject to the approval of the Engineer. Use epoxy cartridge systems that meet the requirements of the “Acceptance Criteria for Adhesive Anchors in Concrete and Masonry Elements,” AC58, by the International Code Council Evaluation Service (ICC-ES). Meet the suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic qualification of these acceptance criteria. Approval of epoxy cartridge systems is contingent upon the Contractor submitting to the Engineer one sample of each type of epoxy cartridge system, manufacturer’s installation instructions, and certified results of tests, either by a private testing laboratory or the manufacturer, indicating compliance with the above requirements.

Unless shown otherwise, do note use epoxy cartridge systems when:

1.	Temperature of concrete is above 110°F or below 40°F

2.	There is a likelihood of fire

3.	Coated bars or rods are specified unless the embedment depth is increased by 50%

Provide epoxy cartridges clearly and permanently marked with the manufacturer’s name, model number of epoxy cartridge system, manufacturing date, and lot number. For each carton of epoxy cartridges, provide the manufacturer’s recommended installation procedures, minimum cure time, and such warning or precautions concerning the contents as may be required by State or Federal Laws and Regulations.

Provide a certificate of compliance with each shipment of the epoxy cartridge system, regardless of which epoxy product is furnished, as provided in Section 106-1.05. Provide a certificate of compliance to the Engineer that the repair procedure using the epoxy cartridge system was completed in conformance with the manufacture's recommendations.

712-2.18 LOW-VISCOSITY RESIN.  Meet AASHTO M 235, Type IV, Grade 1, with the following revisions:

Amend Table 1 as follows:

Replace “2.0[20]” with “0.105[105]” in the row labeled “Grade 1, max”.

Replace Section 715 with the following:

Section 715
Steel For Piles

715-2.01 SCOPE. Steel used for Structural Steel Piling and Sheet Piling.

715-2.02 GENERAL REQUIREMENTS. Furnish steel piles of the dimensions, weights, cross-sections, and grades specified. Satisfy the impact test requirements of Subsection 716-2.02. Meet the following:

1.	Structural Steel for Piling.

a.	Furnish "HP" shape piles meeting AASHTO M 270, Grade 50.

b.	Furnish pipe piles meeting AASHTO M 270, Grade 50 fabricated in accordance with the American Petroleum Institute (API) 2B or API 5L X52 PSL2.

2.	Pile Tip Reinforcing. Use pile tip reinforcement conforming to the requirements of ASTM A 27 Grade 65-35 or ASTM A 148 Grade 90-60. Make each pile tip in one piece of cast steel. Weld tip reinforcing to the piles in conformance with the manufacturer's written directions.

3.	Structural Steel Sheet Piling. Furnish sheet piles meeting AASHTO M 202.

715-2.03 CERTIFICATION. Furnish 4 copies of a certified mill test report covering chemical and physical tests conducted on the steel to the Department for each heat number of metal included in the shipment. In addition to other requirements of Subsection 106-1.08, certificates for steel material shall include information on country of origin, type of steel, Charpy V-notch toughness for base and weld metals, and type of finish coating. For pipe manufactured to API 5L, submit certificates of compliance, per API 5L SR15.1, covering the entire length of pipe pile furnished.

Replace Section 716 with the following:

Section 716
Structural Steel

716-2.01 SCOPE. Structural steel for highway bridges and other structural purposes.

716-2.02 GENERAL REQUIREMENTS. Meet the following:

1.	General requirements for delivery of rolled steel plates,

shapes, sheet piling, and bars for structural use			ASTM A 6

2.	Structural Steel							ASTM A 709

3.	High Strength Low-Alloy Columbium

Vanadium Steels of Structural Quality				ASTM A 709

4.	High Strength Low-Alloy Steel with 50,000 psi

minimum yield point to 4 inches thick				ASTM A 709

5.	High Yield Strength, Quenched and Tempered

Alloy Steel Plate Suitable for Welding				ASTM A 709

6.	Hot-Formed and Seamless High Strength Low-Alloy Tubing 	ASTM A 618 Grades Ib, II, III

7.	Filler Metal for Applicable Arc-Welding Electrodes		AWS Specifications

8.	Stud Shear Connectors						ASTM A 108

Gr. 1015, or 1020

9.	Raised Pattern Plate. Where shown on the Plans, use plates for steel expansion joints fabricated from steel plate, with a raised pattern surface meeting the following requirements:

a.	Use diagonal type pattern, with the intersecting diagonals at right angles to one another. Use the same material for the raised portions of the pattern as the base metal of the plate. The raised pattern must be an inherent part of the plate. The pattern must be continuous throughout the surface of the plate and the projections along any diagonal must be spaced alternately with the projections along the normal diagonals.

b.	Use plate with projections that are self-draining and self-cleaning and provide a skid-resistant surface from all angles of approach. The projections must have flat tops and be designed not to chip, crack, split, or buckle at their intersection with the base metal.

10.	Impact Test Requirements.

a.	Unless noted as Fracture Critical (F), meet the impact test requirements for impact toughness testing (Charpy V-Notch) and marking under ASTM A 709, Non-Fracture Critical (T) Tension Components, Zone 3.  For material designated on the Plans as Fracture Critical (F), meet the impact test requirements for impact toughness testing (Charpy V-Notch) and marking under ASTM A 709, Fracture Critical (F) Tension Components, Zone 3.

b.	Submit impact test reports to the Engineer.

716-2.03 HIGH TENSILE STRENGTH BOLTS. Meet the following:

High Strength Bolts for Structural Steel Joints 	AASHTO M 164

Nuts for AASHTO M 164 bolts	AASHTO M 291

Hardened Steel Washers	AASHTO M 293

Zinc Coated Load Indicating Washers	ASTM F 959 Type 325

716-2.04 STEEL GRID FLOORS. Meet ASTM A 709, Grade 36. Unless the material is galvanized, it must have a copper content of 0.2% minimum.

Unless painting of floors is specified in the Special Provisions, open type floors must be galvanized.

716-2.05 MACHINE BOLTS. Meet ASTM A 307.

716-2.06 STEEL PIPE. Meet ASTM A 53 Grade B.

716-2.07 GALVANIZING. Hot-dip galvanize structural steel shapes, plates, bars and their products according to AASHTO M 111. Galvanize tubes and piles on inside and outside surfaces.

Hot-dip galvanize steel poles, mast arms, pedestals, and posts, according to AASHTO M 111. Submerge each component in the galvanizing kettle in one dip. Use only the dry kettle method of fluxing for high tower poles.

Hot-dip galvanize all anchor bolts, nuts, washers, tie-rods, clamps, and other miscellaneous ferrous parts in conformance with AASHTO M 232. After galvanizing, ensure that the bolt threads accept galvanized standard nuts without requiring tools or causing removal of protective coatings.

Galvanize rigid metal conduit in conformance with AASHTO M 232.

For Steel Bridge members, apply 10 mils zinc galvanizing by spray-metalizing process according to Steel Structures Painting Council (SSPC) Coating System Guide No. 23.00. Prepare surfaces before galvanizing in accordance with SSPC-SP 5 White Metal Blast Cleaning.

Repair damaged coatings in accordance with ASTM A 780.

716-2.08 CERTIFICATION. Submit five copies of a certified test report covering chemical and physical tests conducted on all structural steel to the Department for the material in each shipment.

Section 719
Steel, Gray-Iron and Malleable-Iron Castings

Standard Modification

719-2.02 GENERAL REQUIREMENTS. In Gray-Iron Castings, delete text and replace with: AASHTO M 306 and AASHTO M 105, Class 35B.

E47(01/27/07)

Replace Section 720 with the following:

Section 720
Bearings

720-2.01 ELASTOMERIC BEARING PADS. Elastomeric bearing pads include plain pads, consisting of elastomer only, and laminated pads with steel laminates.

1.	General. Meet AASHTO M 251, with the following revisions:

4.1 Properties of the Elastomer. Replace the first sentence with the following: Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer. Do not use neoprene. Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) do not apply.

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraph 8.9.

Add the following paragraph:

5.5. Fabricate pads over 3/4 inch thick with alternating laminations of elastomer and metal or fabric reinforcements. The outside laminations must be metal or fabric with a minimum elastomer cover as shown on the Plans.

2.	Certification. Submit five copies of a certified test report for each elastomeric pad configuration.

720-2.02 EPOXY ADHESIVE FOR ELASTOMERIC BEARING PADS. Meet AASHTO M 235, Type IV, Grade 3.

720-2.03 POLYTETRAFLUOROETHYLENE (PTFE) BEARINGS. PTFE bearing assemblies consist of elastomeric bearing pads, polytetrafluoroethylene (PTFE) surfacing, and stainless steel and steel plates.

1.	Materials.

Elastomeric Bearing Pads	Subsection 720-2.01

Stainless Steel Plates	ASTM A 240, Type 304

Steel Plates	ASTM A 709, Grade 36

Use PTFE from virgin material (not reprocessed) meeting the requirements of ASTM D 4894 or D 4895, and Table 720-1.

2.	Fabrication. Fabricate the PTFE sliding surface with lubricant dimples having a maximum diameter of 0.32 inch, a minimum depth of 0.08 inch and a maximum depth of one half of the PTFE sheet thickness. Distribute the dimples uniformly within the area ¼ inch from the edges of the PTFE sheet and occupying between 20 percent and 30 percent of the PTFE sheet area.

For welding of structural steel, conform to the requirements of Section 504.

TABLE 720-1

POLYTETRAFLUOROETHYLENE (PTFE)

| Test | Requirements |
| --- | --- |
| Specific Gravity | 2.13 - 2.19 |
| Peak Melting Temperature | 623oF (2oF) |
| Tensile strength (Minimum) | 2800 psi |
| Elongation (Minimum) | 200% |

Bond the PTFE sheet in the recess of steel plate under controlled factory conditions. Use adhesive material that is an epoxy resin conforming to the requirements of Federal Specification MMM-A-134.

Uniformly roughen the contact surfaces of PTFE sheet and steel plate to be bonded to a minimum roughness height value of 250 micro-inches.

Factory treat the side of the PTFE sheet to be bonded by the sodium naphthalene or sodium ammonia process, after the contact surface is roughened.

Fully bond the PTFE sheet in the recess. Ensure the PTFE surface is smooth and free from bubbles after completion of the bonding operation. PTFE sheets that are delaminated will be rejected.

Perimeter seal weld the stainless steel plate to the steel sole plate. Use stainless steel electrodes in accordance with the requirements of the electrode manufacturer. After the completion of the weld operation, ensure the stainless steel plate is smooth and free from waves.

Control the flatness of the bearing elements such that upon completion of the bearing assembly the PTFE/stainless steel sliding interface is in full bearing.

Provide a mating surface of the stainless steel plate with the PTFE surfacing with a surface finish of less than 8 micro inches root-mean-square (rms), determined according to ANSI Standard B46.1. Do not exceed a first movement static coefficient of friction of 0.05 for the sliding element of the production bearings, when tested without the coating of silicone grease.

Fully vulcanize elastomeric bearing pads to the steel plates under factory controlled conditions. Provide a bond with a peel-strength of at least 30 pounds per inch as determined by AASHTO M 251, appendix X2.

Prepare and paint metal surfaces, except stainless steel surfaces, of bearings exposed to the atmosphere in the completed work. Prepare and paint the surfaces according to Section 504.

After installation of the bottom portion of the bearing assembly, apply a 1/16 inch thick coating of silicone grease to the entire PTFE surface and reassemble the bearing without damage to the mating sliding surfaces. Use silicone grease conforming to Military Specification: MIL-S-8660.

At your expense and without contract extension time return damaged bearings and bearings with scratched mating surfaces to the factory for replacement or resurfacing.

Prior to proof testing, permanent die stamp all individual components on 2 of 4 sides with markings consisting of bearing number and contract number. Provide each bearing with a unique bearing number and match marks on plate edges to insure correct assembly at the job site.

3.	Testing. Proof test and evaluate full sized PTFE bearings for compression and coefficient of friction in the presence of the Engineer, unless otherwise directed. Perform proof tests on samples randomly selected by the Engineer from the production bearings to be used in the work. Perform proof tests at an approved independent laboratory. If proof tests are not performed at the specified load, perform additional physical tests in the presence of the Engineer, unless otherwise directed, to demonstrate that the requirements for proof testing at the specified load are satisfied. Give the Engineer at least 7 working days notice before beginning proof testing.

Proof test one bearing per lot of production PTFE bearings. A lot is defined as 25 PTFE bearings or fraction thereof of the number of PTFE bearings shown on the Project Plans.

Clean the bearing surfaces prior to testing.

Proof test bearings after conditioning specimen for 12 hours at 75o 5oF.

Perform the tests with the dead load as specified in the Contract for the bearing with the test load applied for 12 hours prior to friction measurement and the following:

Arrange the tests to allow measurement of the static coefficient of friction on the first movement of the bearing.

Measure the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

Subject the test bearings to a minimum of 100 movements of at least one inch of relative movement at a sliding speed not exceeding 12 inches per minute. After cycling, measure again the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

The proof tested bearings are to show no visible sign of: (1) bond failure of bearing surfaces, (2) separation or lift-off of plates from each other or from PTFE surfaces, (3) other defects. When a proof tested bearing fails to comply with the Contract Documents, test each bearing in that lot for acceptance.

Proof test results are to be certified correct and signed by the testing laboratory personnel who conducted the test and interpreted the test results. Include the bearing numbers of the bearings tested on the proof test results.

Test a minimum of one pad per lot for bond strength per AASHTO Test M 251. Test specimens are to show no indication of deterioration of elastomer or loss of bond between the elastomer and steel laminates.

Protect all PTFE and stainless steel surfaces from contamination and weather damage.

4.	Certification. Submit a certified test report for each bearing configuration.

Replace Section 721 with the following:

Section 721
Prestressing Steel and Fittings

721-2.01 SCOPE. Prestressing steel and fittings used in pre-tensioned and post-tensioned concrete construction.

721-2.02 PRESTRESSING STEEL. Meet the following:

Steel Strand	AASHTO M 203

Uncoated Stress-Relieved Steel Wire	AASHTO M 204. Do not use oil-

tempered wires.

High Strength Steel Bars	AASHTO M 275

721-2.03 POST-TENSIONING SYSTEM. Use only post-tensioning systems that utilize tendons fully encapsulated in anchorages and ducts. Systems that transfer prestress force by bonding the prestress steel directly to concrete are not allowed. Use only post-tensioning systems that are approved by the Engineer and meet the following requirements:

1.	Anchorage and Distribution. Secure prestressing steel at the ends by means of approved permanent type anchoring assemblies.

Use anchorage devices for post-tensioning that hold the prestressing steel at a load producing a stress of not less than 95 percent of the guaranteed ultimate tensile strength (GUTS) of the prestressing steel, when tested in an unbonded state, without exceeding the anticipated set.

Distribute the load from the anchoring assemblies to the concrete by means of approved devices or bearing plates that will effectively distribute the load to the concrete. Construct the bearing plate and wedge plate from ferrous metal. For bending stresses in the bearing plates or assemblies induced by the pull of the prestressing steel, do not exceed the yield point of the material or cause visible distortion in the bearing plate when 95 percent of the GUTS of the tendons is applied as determined by the Engineer. Do not exceed 3500 psi directly underneath the bearing plate or assembly for the final unit compressive stress on the concrete.

Galvanize the body of the anchorage assembly in accordance with AASHTO M 111. Other components of the anchorage assembly including wedges, wedge plate and local zone reinforcement need not be galvanized.

Construct anchorage assemblies with grout vents suitable for post-grouting inspection access as approved by the Engineer. Equip all anchorages with a grout cap that is vented and bolted to the anchorage.

Recess the anchoring assemblies so that the ends of the prestressing steel and all parts of the anchoring assemblies will be at least 3 inches inside of the end surface of the members, unless shown otherwise on the plans. After post-tensioning all tendons, fill the recesses with concrete conforming to the provisions for the structure and then finished flush with the abutment end diaphragm.

2.	Strand Couplers. Do not use strand couplers.

3.	Enclosures for Post-tensioning. Use rigid ferrous metal duct enclosures for prestressing steel that are galvanized, mortar tight, and capable of withstanding concrete pressures without deforming. Use rigid ducts with smooth inner walls that can be curved to the proper configuration without crimping or flattening and have sufficient strength to maintain their correct alignment during placing of concrete. Do not use semi-rigid ducts. Fabricate ducts with either welded or interlocked seams.

Connect sections of rigid ducts using galvanized ferrous metal couplings that are mortar tight and do not result in angle changes at the joints. Do not use split metal couplings. Use waterproof tape to seal all connections to the duct. Connect ducts to anchoring assemblies using transition couplings that are galvanized ferrous metal or polyethylene, mortar tight, and of sufficient strength to prevent displacement of the ducts during concrete placement.

Use ducts for multi-strand tendons with a minimum diameter that provides an inside area at least 2.5 times the net area of the prestressing steel in the tendon.

Do not use ducts with diameters that exceed 0.4 times the least gross concrete thickness at the duct location.

Use duct enclosures with vents for the injection of grout after post-tensioning.

4.	Grout Vents. Use vents with positive means for allowing the escapement of air, water, grout, and bleed water out of the vents, injecting grout through the vents, and sealing to prevent grout leakage from the vents. Use 3/4 inch minimum diameter standard pipe or suitable plastic pipe vents with positive shut-off designed to withstand the grouting pressure. Do not crimp or bend the vent pipe. Use metallic or plastic structural fasteners to connect the vent with the duct. Do not use plastic components that react with the concrete or enhance corrosion of the prestressing steel, or contain water-soluble chlorides. Make all vents mortar tight, taped as necessary. Make vents with sufficient length out of the concrete member to allow proper closing of the vents. Remove ends of vents at least 1 inch below the roadway surface after grouting has been completed.

Place vents at the following locations:

a.	At anchorages.

b.	At the high points of the duct, when the vertical distance between the highest and lowest point is more than 20 inches.

c.	At a location down flow from all high point vents where the duct is approximately one-half duct diameter lower than the crest, but not to exceed 3 feet downstream.

d.	At the lowest point of the duct.

e.	At major changes in the cross-section of the duct.

f.	At other locations designated by the Engineer.

5.	Grout Caps. Use grout caps that completely cover and seal all exposed ends of prestressing steel at the anchorage. Seal the cap with neoprene “O” ring seals and place a grout vent on the top of the cap. Use caps rated for a minimum pressure of 150 psi.

721-2.04 CERTIFICATION.

1.	Prestressing Steel. Submit five copies of a certified test report covering chemical and physical tests conducted on all prestressing steel to the Department for the material in each shipment.

2.	Post-Tensioning Systems. Submit certified test reports to the Engineer that shows the post-tensioning system meets all the requirements specified herein. Submit the certified test reports with the shop drawing submittal. If any component of the post-tensioning system is modified or replaced, the entire system must be retested and resubmitted to the Engineer for approval.

Ensure that all components of a system are stamped with the supplier’s name, trademark model number and size corresponding to catalog designation.

Submit certification stating the manufacturer's minimum guaranteed ultimate tensile strength of all prestressing steel used for this project.

Assign an individual lot number for each manufactured reel of prestressing steel to be shipped to the site. Tag each reel in such a manner that each lot can be accurately identified at the site. All unidentified prestressing steel received at the site will be rejected.

Assign and tag each lot of anchorage assemblies to be installed at the site. Tag each anchorage assembly in such a manner it can be accurately identified at the site. All unidentified anchorage assemblies received at the site will be rejected.

Section 724
Seed

Special Provisions

724-2-02. MATERIALS. Delete Table 724-1 and substitute the following:

- TABLE 724-1

SEED REQUIREMENTS

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(01/27/07)R52

- Delete this Section, except for Table 726-1 and substitute the following:

Section 726
Topsoil

Special Provisions

726-2.01 TOPSOIL. Furnish topsoil that is representative of the existing, natural organic blanket of the project area. Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil. Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans. Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project. In this case, furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5 percent or more, as determined by ATM 203. The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic. Notify the Engineer of the location topsoil is to be furnished at least 30 calendar days before delivery of topsoil to the project from that location. The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

R208(11/27/07)

Section 730
Sign Materials

Special Provisions

730-2.04 SIGN POSTS. Add the following item:

7.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized according to 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

R81(06/22/04)

Section 740
Signals and Lighting Materials

Special Provisions

- Replace subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design. Design and fabricate highway lighting structures to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans. Use a wind speed of 100mph with a gust factor of 1.3.  Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 ft above the pole base.

Design and fabricate traffic signal structures to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category III, with galloping using a basic wind speed of 100mph and Central Region standard loads.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations. Submit the stamped drawings and calculations for each pole to the Engineer for approval. Design for stresses on the completed structure with hardware in place.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including: design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including: materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication. Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section. Orient hand holes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece. Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice. For slip type joints, provide a minimum overlap of two and one halt (2.5) feet or the overlap specified in the Plans, whichever is greater.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1. Fabricate elements greater than ½ inch thick from steel that conforms to ASTM M270 and meets the Fracture Critical Impact Test requirements for zone 3. The Department will not accept structures that contain or are made with laminated steel elements.

Fabricate each tube from no more than 2 pieces of steel. When using 2 pieces, place the longitudinal welded seams directly opposite one another. Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans.  Fabricate signal poles 10 to 15 feet long from 7 gage (US Standard) sheet steel. Fabricate each post with a minimum inside diameter at the base plate as shown in the Plans. Use 4 inch diameter by 4 inch Schedule 40,ASTM A 53, Grade B pipe as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms. To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments. Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a. Lift points added to the inside of tubes in place may be left in place.

Hot dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Galvanizinf kettles will be large enough to completely submerge each element, the mast arem, and the pole.  Submerge the compelte/whole element in the galganizing process.  An element galvanized in sections will not be accepted. Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding ¾ inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

c.	Out of round. Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50. Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld. Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding. Perform welding to conform to subsection 504-3.01 8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip joints, the length of the slip fit joint plus one half diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100% of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25% of PJP and fillet welds by magnetic particle (MT). If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.3.

d.	Only visually inspect welds made on luminaire mast arms.

4.	Anchor Rods & Bolts. Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

5.	Miscellaneous. Finish the edges of poles and mast arms to conform to the following requirements. Before hot dip galvanizing, neatly round the following features to the radius specified

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another. First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively. Then for the length of the joint plus 6 inches grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1. The measurements shown are for illustration purposes only. Use tags large enough to include required information using ¼ inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text. Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms. If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.  Provide the holes for the blind rivets before galvanizing.

| TABLE 740-1 |  |  |
| --- | --- | --- |
| POLE MARKINGS |  |  |
| Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms. |  |  |
|  | MEASUREMENTS | TAG MARKINGS |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

Replace No. 5. with the following:

5.	Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

Replace "6 twisted pairs" in the second sentence of the 4th subparagraph of No. 6. with the following:

"7 twisted pairs"

Replace TABLE 740-3 with the following:

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Pair No. | Tip | Ring | Pair No. | Tip | Ring |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

Replace subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS. Unless specified otherwise, use rigid metal conduit and fittings for raceways. Furnish galvanized rigid type conduit and elbows that conform to UL-6 and are manufactured of mild steel according to ANSI C80.1. Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL-651. Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL 651 B.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle. Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline. The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws. For loop detectors, furnish type X bodies and, for photoelectric control installation, furnish types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it. The movements include: axial expansion or contraction to ¾ inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to ¾ inch. The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Replace Subsection 740-2.12 with the following:

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

1.	Three Circuit Solid State Load Switches.  Use load switches conforming to NEMA TS-2, Section 6.2 Three Circuit Solid State Load Switches and as a minimum include Light Emitting Diode indicators on the DC input circuitry.  The load switch must have three independent switching circuits, each being an individually replaceable solid state module.

2.	Solid State Flasher.  Use a NEMA Type III flasher unit that conforms to NEMA TS-2, Section 6.3 Solid State Flashers.

3.	Malfunction Management Unit (MMU).  Provide Type 16 MMU to be fully compliant with the requirements of NEMA TS-2, Section 4.  In addition, the MMU shall have a full intersection LCD back lighted signal on the front panel and shall be downward compatible with TS-1 CMUs.

4.	Flash Transfer Relay.  Use flash transfer relays that meet the requirements of NEMA TS-2, Section 6.4 Flash Transfer Relays.

- Replace subsection 740-2.17 with the following:

740-2.17  FLASHING BEACONS.   The beacon mounted above the  ‘SCHOOL SPEED LIMIT 20 WHEN FLASHING’ (S5-1) sign shall consist of four (4) signal heads with 12-inch diameter yellow LED signal indications.  They shall be mounted horizontally directly above the S5-1 sign.  The two upper beacons shall be illuminated alternately and face oncoming traffic.  The lower beacons shall face the opposite direction and be illuminated alternately also.

The beacon mounted above the  ‘Fire Truck Warning Sign’ (W11-8) sign shall consist of two (2) signal heads with 12-inch diameter yellow LED signal indications.  They shall be mounted horizontally directly above the W11-8  sign.  The two beacons shall be illuminated alternately and face oncoming traffic.

Use the flasher in signal controller cabinets to energize beacons that flash continuously and are installed near traffic signals.  Otherwise, each flashing beacon controller assembly consists of the following 120 VAC equipment housed in a NEMA 3R enclosure:  a 20-ampere, single pole, circuit breaker, a radio interference suppressor, a transient voltage suppressor, a NEMA Type 3 flasher, flasher socket, a thermostatically controlled  incandescent cabinet light with door activated bypass switch neutral and ground busses, and terminal blocks.

Controller assemblies for school zone speed limit sign beacons shall also include a time switch and a thermostat for the cabinet light.  Controller assemblies for the entering Fire Truck sign beacons shall also include a timer and a thermostat for the cabinet light.

The NEMA 3R enclosure shall include vents and feature a single shelf and a hinged door with a hasp and staple for sealing and locking the cabinet door.

The radio interference and transient voltage suppressors shall meet the requirements of Subsections 740-2.11.1.k.(3) and (4), respectively.

Use a solid state NEMA Type 3 flasher meeting the requirements of NEMA Standard TS 1-1989, Traffic Control Systems.

Use 20 ampere, 600 volt barrier type phenolic terminal blocks with plated brass screw type terminals and integral strips can be marked with a pen or pencil, except that a single 3-position Box Lug type terminal block capable of accepting three No. 4 AWG wires for terminating power cables must be supplied in all control units.

Flasher socket shall be Cinch-Jones socket S-406-SB, or equivalent

Furnish an RTC Manufacturing model AP41-L time switch complete with wiring harness, or an approved, calendar programmable, solid state time switch with liquid crystal display, keyboard, input/output port, and wiring harness.  The approved time switch shall:

1.	Operate on line voltages from 95 to 135 VAC, operate in temperatures from -22 F to 165 F, and include a capacitor that provides 48 hours of backup power to retain programming and time when the unit is disconnected from AC voltage.

2.	Include a backlit display and provide 2 lines of alphanumeric legend with 16 characters per line.  The display shall automatically prompt the operator while programming the device through the keyboard for ease of use.

3.	Include an input/output port and keyboard activated special functions that transfer the program to other units and download the program to a printer for a hard copy record of the program.

4.	Automatically compensate for changes in Daylight Savings Time and leap years and include a keyboard activated special function to quickly change the dates for the begin and end of Daylight Savings Time.

5.	Provide at least 10 basic plans for daily and/or weekly use and at least 200 program steps that are equally divided amongst the actual number of basic plans.  Each program step shall be assignable to a single day, weekend, weekday, or every day.  The time switch shall also include 20 plans that activate the basic plans to provide one year of time based control.

6.	Include at least 4 single pole double throw, relay controlled outputs rated for 15 amperes of resistive load at 115 VAC.  Each pole shall be independently activated for steady on or momentary on and be manually switched on through the keyboard.

Furnish an IDEC model RTE-P2AF20 timer complete with isolation relay RR2P-U AC120 and socket.  The approved time switch shall:

1.	Operate on line voltages from 95 to 135 VAC, operate in temperatures from -4 F to 150 F.

When a signal controller cabinet flasher is used to energize a beacon, furnish a two pole, fused block with built in fuse pullers to protect the flasher.  Furnish third party certified blocks that hold 13/32" x 1-1/2" midget ferrule fuses, are rated for 30 amperes, and feature tubular screw terminals that accommodate conductors to 8 AWG.  Furnish blocks with two fast acting, 3 ampere (BAF-3) fuses, and flat bases that can be directly mounted on a dead panel.

Special Provision

- Replace subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES. Furnish luminaires that conform to the following specifications and provide the light distributions specified. When luminaire performance criteria are specified, luminaires shall also:

•	Meet or exceed the minimum initial light levels indicated.

•	Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified: luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage. Furnish roadway lighting lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to subsection 740-2.21.

1.	Luminaries General

Install luminaires that feature:

a.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

b.	Third party certification for use in wet locations.

c.	Glass lenses, unless polycarbonate resin refractors are specified.

d.	Terminal blocks for attaching the illumination tap conductors.

e.	Aluminum reflectors with an ALZAK or ALGLAS finish.

f.	Optical components free of substances that affect photometric performance, e.g. paint.

g.	Housings cast with no provision for a photoelectric control receptacle.

h.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components. Gasket material must withstand the temperatures involved and be securely held in place.

i.	Plug in starting aids in fixtures with lamps through 400 watts.

- Luminaries – Cobrahead and Offset

Each cobrahead luminaire shall also include:

a.	An easily removed hinged door used exclusively for mounting the ballast.

b.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

c.	A four bolt mounting brackets that fit 2 inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

3.	LED Luminaire

LED Luminaires shall be UL listed for wet locations and enclosure classified IP66 per IEC 529.  The fixture shall be resistant to corrosion, ultraviolet degradation and abrasion.  Nickel-chrome plated wire guard shall be used for providing anti-fouling protection from leaf/debris and animals nesting to assure cool LED operation.

The luminaire shall have five years warranty on the LED’s and the driver.  Average delivered lumens over 50,000 hours should be a minimum of 85% of initial delivered lumens.

The LEDs shall operate over the temperature range of -40 °F to +165 °F.  The LEDs shall be wired in series parallel strings.  The failure of many one LED, and its associated string of LEDs, shall not cause the loss of more than 20% of the light output of the complete LED module.

4.	High Tower Luminaire

a.	A 1,000 watt, high pressure sodium lamp that provide 140,000 minimum initial lumens, or as otherwise stated in the Plans.

b.	A side entry 4 bolt mounting bracket designed for 2 inch nominal diameter pipe with provision for leveling the luminaire.

c.	A die cast aluminum housing attached to the mounting bracket that provides a weather tight enclosure for the ballast and terminal block and is readily removable without removing the luminaire from the bracket arm.

d.	A cover and reflector that readily detaches from the mounting bracket without removing the luminaire from the bracket arm.

e.	A double fused 480 volt ballast with fuses sized by the luminaire manufacturer.

f.	A hinged lens compatible with add on light shields.

g.	A stainless steel lamp clamp to prevent lamps from loosening, which is separate from the socket.

When the Plans specify shielding areas from illumination, install light shields on luminaires on hightower poles whose templates touch the shielded areas.  Provide shields that limit light levels to 0.1 foot-candle or less at the right of way line.  Whenever stock shields fail to limit light levels to the 0.1 foot-candle level, hire the luminaire manufacturer to custom design, and fabricate shields.  If the first generation of custom fabricated shields fails to limit light levels to the 0.1 foot-candle level, the Engineer may waive the 0.1 foot-candle requirement.

5.	Lenses.

When polycarbonate resin lenses are specified, furnish lenses the fabricator certifies conforms to the following criteria.

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by ½ inch bar molded according to ASTM recommended practice.

R98(07/01/09)

Add the following Section:

Special Provisions

Section 744
Erosion, Sediment, And Pollution Control - Material

744-2.01 MATERIAL.

Fiber Roll:  (commonly called straw wattle)

a.	Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

Manufactured Inlet Protection System:

a.	Manufacturers:

Ultra Tech International – Ultra-DrainGuard

Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

Enpac - Catch Basin Insert, Oil and Sediment or

b.	Approved equal.

Sand Bag Inlet Sediment Trap:

a.	Sandbag sack fabric shall be a nonwoven, needle punched design meeting the following requirements:

Grab Tensile Strength	ASTM D 4632	200 pounds (min.)

Grab Elongation	ASTM D 4632	15 – 70%

Mullen Burst Strength	ASTM D 3786	400 psi. (min.)

Trapezoidal Tear Strength	ASTM D 4533	95 lbs. (min.)

Apparent Opening Size	ASTM D 4751	No. 30 U.S. STD sieve (max)

Permittivity	ASTM D 4491	0.01 sec-1 (min.)

Ultraviolet Light Stability,

Retained Strength	ASTM D 4355	90%

Puncture Strength	ASTM D 4833	120 lbs. (min.)

These requirements are for Minimum Average Roll Values (MARV) verified in accordance with ASTM D 4759.

b.	Seam Thread:

Similar durability to the sandbag sack fabric.

c.	Sandbag Fill Material:

Select Material	Type B	703-2.07.

d.	Cinch Ties:  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

CR744(022309)

APPENDIX A

EROSION AND SEDIMENT CONTROL PLAN (ESCP)

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

APPENDIX D

SIGN DETAILS

APPENDIX E

UTILITY COMPANY REQUIREMENTS

APPENDIX F

PERMITS AND ENVIRONMENTAL DOCUMENT