SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

- Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition ($25.00).

b.	Alaska Test Methods Manual (Lab & Field), 2010 Edition ($25.00). Available online at:

http://www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/pop_testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

d.	Quantity Computations

e.	Cross Sections

f.	Supplemental Geotechnical Data Report, Trunk Road Reconstruction Phase II Palmer-Wasilla Hwy to Fishhook Road. Project Number 52432, December 2009, Prepared by DOT&PF.  Included as an appendix to this report is Geology Data Report, Trunk Road Reconstruction, Project Number 52432, September 2005, Prepared by DOT&PF.

g.	Erosion and Sediment Control Plan (ESCP), Trunk Road Reconstruction Phase II Palmer-Wasilla Hwy to Palmer-Fishhook Road, Project Number 51132, September 2011, Prepared by DOT&PF

h.	Project Base Drawing and Digital Terrain Model:  On compact disk(s), For information only.

The Department expressly states that the information contained on the disk(s) is not and shall not be considered part of the bidding documents.  The Department makes no representation, warranty or guarantee, expressed, implied, or statutory, as to the accuracy, reliability, suitability, functionality, or results derived from the use of the information contained therein.  The Department shall NOT accept, review, hear, or consider any bid protest or construction claims arising from use of the information on the disk(s).  The user assumes all risk and liability for use of information on the disks(s).

- Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix C.

- Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

- Hiring Apprentices.  Administrative Order 226, issued July 24, 2005 establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility, or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, visit http://labor.state.ak.us//lss/forms/ApprenHireReq.pdf

5.	Disadvantaged Business Enterprise (DBE) Program.  Effective August 1, 2011, the Alaska Department of Transportation & Public Facilities returned to DBE Utilization Goals for projects funded with Federal Highway Administration (FHWA) funds for all Regions.  FHWA approved the return to DBE goals based on recommendations of the Department's completed Disparity Study and approval of a DBE Program waiver.

The Department received approval and implemented in 2010 a return to DBE Utilization Goals for Federal Aviation Administration (FAA) and Federal Transit Administration (FTA).

FHWA has approved the Department's request to return to DBE Utilization Goals for Central Region.  A waiver to exclude a DBE group from DBE goal setting because that group had achieved parity with other contractors was requested and approved by the US Secretary of Transportation.  This waiver request was based on the finding of the Department's completed Disparity Study.

Contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A336 for FHWA funded projects.  This will allow the Department to continue to accurately report DBE participation to the FHWA, FAA and FTA.

Any questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, or email jon.dunham@alaska.gov

6.	How the US DOT Waiver for the DBE Program will be implemented on Central Region Construction Projects.  August 1, 2011, the Alaska Department of Transportation & Public Facilities returned to DBE Utilization Goals for projects with Federal Highway Administration (FHWA) funds for Central Region.  FHWA approved the return to DBE goals based on recommendations of the Department's completed Disparity Study and approval of a DBE Program Waiver.  The DBE Program Waiver approved by USDOT addresses the issue identified in the Department's Disparity Study which found that DBE firms that are owned by Non-Minority Women were participating on the Department's construction contracts and subcontracts on an equal basis similar to other non-DBE contractors and non-DBE subcontractors for Central Region only.

As a result, goals will be set using minority-owned DBEs only, and DBE project goals can only be met through the use of minority owned DBEs.  This Waiver does not affect DBE project goals for airports or transit projects anywhere in Alaska, and does not apply to professional service agreements or highway construction projects in Northern or Southeast Regions.

The decision to continue or discontinue the use of the Waiver will be made on an annual basis in June.

Any questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, or email jon.dunham@alaska.gov

7. 	Section 120 Supplies and Materials Purchased by DBEs.  During August 2010, the FHWA National Review Team identified a practice of DBE firms purchasing supplies and materials from companies affiliated with the prime contractor on USDOT-assisted projects.

49 CFR 26.71 requires DBE firms to operate independently of the prime contractor, which also includes sister companies or companies that have a common parent corporation as the prime contractor.

As a result, FHWA has determined that the cost of materials and supplies purchased by a DBE from a sister company of the prime contractor cannot be credited towards the DBE Goal.

This notice was issued October 6, 2011.

All questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, or e-mail jon.dunham@alaska.gov.

8.	Prevailing Wage Requirements.  The Department of Labor and Workforce Development (DOLWD) proposed a revised regulatory definition of "on-site" in 8 AAC 30.910 to clarify the scope of activities covered by Alaska's Little Davis Bacon Act (AS 36.05.010 - AS 36.05.110).  for a copy of the revised definition of 8 AAC 30.910, go to:  http://www.labor.state.ak.us/lss/forms/400-revised-definition-of-on-site.pdf

DOLWD will enforce the revised provisions on all projects with bid opening date on or after February 15, 2011.  Prospective bidders on projects with a bid opening date on or after February 15, 2011, must consider the impact of the revised regulation and bid accordingly.  DOLWD will not enforce the new "on-site" definition on projects with a bid opening date prior to February 15, 2011.

- Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

- Asphalt Laydown Temperatures.  The Department may monitor laydown temperatures using a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense as specified in Division 400.

- High Visibility Garments.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See subsection 643-3.11.

- Signals, Lighting Poles, Load Centers, Controller Assemblies:  The Plans and Specifications are revised for these items including, anchors to the foundations, foundations and conduit installation.

- Section 670 Traffic Markings:  This section is recently revised including but not limited to submittal requirements and method of measurement.

- Roadbed Reclamation. This project includes reclaiming existing Trunk Road north of Palmer-Wasilla Highway and south of Bogard Road in accordance with the Plans and Specifications.  This work includes reclaiming the roadbed in accordance with Section 619, excavation in accordance with Section 203, placing wetland soil in accordance with Section 620, placing seed in accordance with Section 618, and other associated items.

- Rootwad Salvage. This project includes salvaging and transporting rootwads for the Alaska Department of Fish and Game (ADF&G) for future projects in accordance with Section 201.

- Digital Terrain Modeling (DTM):

- Section 203, Excavation and Embankment is modified for this project.  The Department requires volumetric quantities to be calculated using DTM methods outlined in Section 642, Construction Surveying.

Notwithstanding the requirement for calculation of volumetric quantities using DTM methods, the Contract estimated quantities were determined using the average end area method.

- Section 642, Construction Surveying is modified for this project.  The Department requires a mandatory Pre-Survey Conference to discuss modifications to the surveying requirements.  New specifications require “Contractor Furnished Computations” under Pay Item 642(13), as well as “Contractor Furnished Engineering Tools” under Pay Item 642(14).  Other modifications address GPS, Topographic, and As-Built Surveying practices.

- Section 306 Asphalt Treated Base.  This Section is recently revised by replacement special provision.  The format is similar to Section 401 Hot Mix Asphalt and Surface Treatments.  Review for specific requirements including but not limited to a 0.5 multiplier applied to the Asphalt Treated Base Price Adjustment, 306-4.03, Evaluation of Materials For Acceptance.

- Section 641 Erosion, Sediment, and Pollution Control – SWPPP Requirements.  The ADEC issued (May 19, 2011) an APDES Construction General Permit (CGP) for Discharges from Large and Small Construction Activities (effective July 1, 2011 through January 31, 2016) replacing the CGP, of same name, expiring on June 30, 2011.  Refer to the ADEC internet site, www.dec.alaska.gov:

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM

GENERAL PERMIT FOR DISCHARGES FROM LARGE AND SMALL CONSTRUCTION ACTIVITIES

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.

PLANS.  Delete Text of PLANS and replace with:

The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32-012707

Add the following definition:

QUALIFIED PRODUCTS LIST.  A list of companies and products that the Department has found conforms to the SSHC.

E36-012707

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22-010106

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.

Replace the second paragraph with the following:

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23-010106

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after:

“If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18-063004

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65-022309

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence, or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58-072808

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete:

"(24"x36")" and replace with: (22"x34")

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after:

"Work performed and materials furnished shall conform to the Plans and Specifications" add:  and approved Working Drawings,

In the first sentence of the second paragraph after: "All work or material not conforming to the Plans and Specifications" add: and approved Working Drawings,

E33-012707

Special Provisions

105-1.06 UTILITIES.  Add the following:

Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities.

ALASKA DIGLINE, INC.

Locate Call Centers: Anchorage 278-3121 Statewide (800) 478-3121

Call Centers will notify the following: AT & T Alascom (AT&T) ENSTAR Natural Gas (Enstar) General Communications, Inc. (GCI) Matanuska Electric Association (MEA) Matanuska Telephone Association (MTA)

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent's phone number for this project.

Utility Support Work by Contractor.

Utilities will be constructed and relocated by others concurrently with construction of this project.  The Contractor shall give each Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the Utility owner is required to begin operations.  For utilities being constructed and/or relocated, the Contractor shall:

1.	Include utility work on the Construction Phasing Plan and Progress Schedule.

2.	Provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all Utility companies performing ground disturbing activity in the Storm Water Pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information.

3.	Clear and grub.  Payment will be made under Section 201, Clearing and Grubbing.

4.	Provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance.

5	Provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information.

	Slope staking.

	Proposed utility facilities and appurtenances.

Payment will be made as follows:

- Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

- Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The Utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

6.	Provide classified backfill material, in accordance with Section 204, Structure Excavation for Conduits and Minor Structures, and the project typical sections.

7.	Pothole excavate for utilities.  Payment will be made under Section 682, Utility Potholing.  Existing utilities shall be excavated at the following locations.  (Stations and offsets shown below are approximate and subject to adjustment by the Engineer in the field.):

- Buried telephone copper paired cable at Bogard Road Stations 10+25 Left, 11+00 Left, 12+00 Left, and 13+00 Left.

- Buried telephone fiber optics and copper paired cables and/or ducts at Bogard Road Stations 16+00 Left, 16+50 Left, 17+25 Left, and 17+75 Left.

- Natural gas service crossing Palmer Fishhook Road at Station 103+55; excavate at 25 feet Right and 25 feet Left.

- Natural gas service crossing Palmer Fishhook Road at Station 107+45; excavate at 25 feet Right and 25 feet Left.

- Buried telephone copper paired cable and natural gas main crossing Palmer Fishhook Road at Station 200+50; excavate at 25 feet Right and 25 feet Left.

Pothole excavating and surveying shall be completed at least 14 calendar days prior to relocations of the utilities listed above.

Provide as-found survey stations, offsets, and elevations to the Engineer within 3 calendar days of obtaining this information.

Utility Construction and Relocation by Others.

Utility company working days shall be Monday through Saturday, 10 hours per day, excluding holidays and associated holiday weekends, unless specifically stated otherwise in these Special Provisions.

Work by Enstar Natural Gas Company (Enstar), General Communications Inc. (GCI), Matanuska Electric Association (MEA), and Matanuska Telephone Association (MTA) is described below:

| Plan & Profile Sheet(s) (Road) | Approximate Stations | Utility or Utilities | Utility Work Required | Duration of Utility Relocation Work (Working Days) |
| --- | --- | --- | --- | --- |
| F4 & F5 (Trunk) & F16 (Bogard) | 208+40 Right to 215+70 Right (Trunk) | MTA | Existing underground telephone service retirement, existing underground telephone service relocation, and new underground telephone copper cable construction. | 5 |
| F5 (Trunk), F15, F16, & F17 (Bogard and Colony Schools) | 210+20 Right to 212+80 Right (Trunk), 10+00 Right and 14+30 Left to 32+50 Right to 32+40 Left, 13+40 Left to 13+50 Right, and 18+10 Right to 18+20 Right (Bogard and Colony Schools) | MEA | Existing overhead electric distribution line retirement, and new overhead and underground electric distribution line construction, new overhead electric tap construction, and underground electric service construction. | 17 |
| F5 (Trunk) & F16 (Bogard) | 215+70 Right (Trunk) to 217+80 Right (Trunk) to 18+90 Left (Bogard) | Enstar & MTA | Existing natural gas main retirement, new natural gas main construction, existing underground telephone copper and fiber optics cable retirement, and new underground telephone copper and fiber optics cable construction. | 3 |
| F5 (Trunk), F16, & F17 (Bogard) | 215+70 Right (Trunk) to 32+70 Left (Bogard) | Enstar & MTA | Existing natural gas main retirement, new natural gas main construction, existing underground telephone fiber optics cable retirement, and new underground telephone fiber optics cable construction. | 6 |
| F11 (Trunk) | 290+60 Right to 290+90 Left | Enstar | Existing natural gas main retirement and new natural gas main construction. | 3 |
| F11 (Trunk) | 291+00 Right to 291+20 Right | MEA | Existing street light and overhead electric secondary line retirement, new street light and underground electric secondary line construction. | 1 |

| Plan & Profile Sheet(s) (Road) | Approximate Stations | Utility or Utilities | Utility Work Required | Duration of Utility Relocation Work (Working Days) |
| --- | --- | --- | --- | --- |
| F11 - F14 (Trunk) | 291+20 Left to 320+50 Left to 320+50 Right | MTA | Existing underground telephone copper cable retirement, existing underground telephone copper cable relocation, and new underground telephone copper cable and service construction. | 12 |
| F12 - F14 (Trunk) | 300+00 Left to 328+90 Right | MEA | Existing overhead electric distribution line, overhead secondary line, underground electric service, and street light retirement, new overhead distribution line construction, and new underground electric service construction. | 16 |
| F12 (Trunk) | 301+40 Right to 302+40 Right | MEA & MTA | Existing underground electric service retirement, existing underground telephone service retirement, new underground electric service construction, and new underground telephone service construction. | 2 |
| F12 (Trunk) | 303+30 Right to 303+30 Left and 305+40 Right | Enstar | Existing natural gas service retirement and new natural gas service construction. | 3 |
| F13 (Trunk) | 306+90 Right and 307+50 Right to 307+60 Left | Enstar | Existing natural gas service retirement and new natural gas service construction. | 3 |
| F13 (Trunk) | 307+20 Right to 307+40 Left | GCI & MTA | Existing overhead CATV line retirement, existing overhead telephone line retirement, and new overhead CATV cable construction. | 2 |
| F13 (Trunk) | 307+20 Right to 313+40 Right | MTA | Existing underground telephone copper cable retirement and new underground telephone copper cable construction. | 3 |

| Plan & Profile Sheet(s) (Road) | Approximate Stations | Utility or Utilities | Utility Work Required | Duration of Utility Relocation Work (Working Days) |
| --- | --- | --- | --- | --- |
| F13 (Trunk) | 307+40 Left to 308+00 Left | GCI | Existing underground CATV service retirement and new underground CATV service construction. | 1 |
| F13 - F14 (Trunk) | 313+40 Right to 328+40 Right | Enstar & MTA | Existing natural gas main retirement, new natural gas main construction, connection of existing natural gas service to new main, existing underground telephone copper cable retirement, and new underground telephone copper cable construction and service construction. | 7 |
| F13 (Trunk) | 314+00 Right to 314+00 Left | Enstar | Existing natural gas service retirement and new natural gas service construction. | 3 |
| F14 (Trunk) | 327+90 Left to 328+30 Right | Enstar & MTA | Existing natural gas main retirement and new natural gas main construction, existing underground telephone copper and fiber optics cable retirement, existing underground telephone fiber optics cable relocation, and new underground telephone copper and fiber optics cable construction. | 15 |
| F14 & F19 (Palmer Fishhook) | 95+60 Right to 96+00 Left | Enstar | Existing natural gas service retirement and new natural gas service construction. | 1 |
| F15 (Bogard) | 14+60 Left to 15+30 Left | GCI | Existing CATV fiber optics hand hole adjustment or relocation, existing underground CATV fiber optics retirement, and new CATV fiber optics duct and cable placing and splicing. | 3 |

| Plan & Profile Sheet(s) (Road) | Approximate Stations | Utility or Utilities | Utility Work Required | Duration of Utility Relocation Work (Working Days) |
| --- | --- | --- | --- | --- |
| F15 (Bogard) | 15+00 Left to 15+50 Left | MTA | Existing underground telephone copper cable relocation. | 1 |
| F15 (Bogard) | 15+30 Left | MTA | New fiber optics hand hole placement, and new fiber optics cable splicing. | 3 |
| F15 (Bogard) | 15+30 Left to 15+70 Left | GCI & MTA | Existing underground CATV fiber optics cable retirement, new underground CATV fiber optics cable construction, existing underground telephone copper and fiber optics cable retirement, and new underground telephone copper and fiber optics cable construction. | 1 |
| F15 (Bogard) | 15+40 Right to 15+50 Left | Enstar | Existing natural gas service lowering. | 1 |
| F15 & F16 (Bogard) | 15+70 Left to 18+90 Left | Enstar, GCI, & MTA | Existing natural gas main retirement, new natural gas main construction, existing underground CATV fiber optics retirement, new underground CATV fiber optics construction, existing underground telephone copper and fiber optics cable retirement, and new underground telephone copper and fiber optics cable construction. | 9 |
| F16 (Bogard) | 18+25 Left and 18+00 Right to 22+80 Right | Enstar | New natural gas main construction. | 2 |
| F16 (Bogard) | 18+40 Left to 18+60 Left | MTA | New underground telephone copper and fiber optics cable construction. | 3 |

| Plan & Profile Sheet(s) (Road) | Approximate Stations | Utility or Utilities | Utility Work Required | Duration of Utility Relocation Work (Working Days) |
| --- | --- | --- | --- | --- |
| F16 (Bogard) | 18+90 Left | GCI | New CATV fiber optics hand hole placement, and new CATV fiber optics cable splicing. | 3 |
| F17 (Bogard) | 32+70 Left to 34+70 Left | MTA | Existing underground telephone fiber optics retirement, new underground telephone fiber optics construction, new telephone fiber optics hand hole placement, and new telephone fiber optics cable splicing. | 4 |
| F20 (Palmer Fishhook) | 103+50 Right to 103+60 Left and 107+40 Left to 107+50 Right | Enstar | Existing natural gas service lowering (two places). | 2 |
| F21 (Palmer Fishhook) | 198+60 Left to 200+70 Left to 200+70 Right to 199+30 Right | MTA | Existing underground telephone copper cable retirement and new underground telephone copper cable construction. | 6 |
| F21 (Palmer Fishhook) | 200+70 Left to 200+30 Right and 200+40 Left | Enstar | Existing natural gas main retirement and new natural gas main construction. | 3 |
| F21 (Palmer Fishhook) | 201+30 Left to 203+90 Left | Enstar | Existing natural gas main retirement and new natural gas main construction. | 3 |
| F21 (Palmer Fishhook) | 201+30 Left to 205+20 Left | MTA | Existing underground telephone copper cable retirement and new underground telephone copper cable construction. | 4 |
| F36 & F37 (Stringfield) | 1+40 Left to 2+20 Right | MTA | Existing overhead telephone copper cable demolition, existing telephone pole retirement, existing underground telephone copper cable retirement, new telephone pole installation, and new underground telephone copper cable construction. | 5 |

51132-062611

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:

The following state owned projects may be under construction concurrently with this project.

| Project Name: | Project No.: |
| --- | --- |
| Glenn Hwy Signing Anch to Palmer (GF) | 52334 |
| Seward Meridian Pkwy Imp - Ph I Parks to Pal-Was GARVE | 51184 |
| HSIP: Bogard Rd & Peck St Intersection Improvements | 51847 |
| Trunk Road Reconstruction, Phase I Parks to Palmer-Wasilla Highway | 59301 |
| Glenn Highway Eklutna to Parks Hwy Resurfacing | 52110 |
| Glenn Hwy Culvert MP 13.0 (Farm Avenue) | 52385 |
| CR: ITS Signal Control Upgrades | 51865 |

The following Mat-Su Borough projects may be under construction concurrently with this project:

Bogard Road Extension

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

CR1051-110309

Standard Modification

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:

Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer's opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33-012707

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

E59-072808

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4. after:

“DOLWD” add: and State Department of Revenue.

E19-063004

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:

Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.

CR93-032101

Standard Modification

Add the following Subsection 105-1.18:

105-1.18 RESERVED FOR WARRANTIES.

E33-012707

SECTION 106

CONTROL OF MATERIAL

Standard Modifications

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text. “Approved Products List” and replace with:  Qualified Products List

E36-012707

Special Provision

Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and submit a completed Material Origin Certificate, Form 25D-60, before award of the Contract.

Steel and iron products, which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the Project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating process must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

CR13-020705

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient, Useable Excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:

The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:

When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:

Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material source or any portion of a material source, at any time after Contract Award that is determined by material testing to be unsuitable for use on the Project.

E24-010106

Add new Subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified Project document.  The Contractor shall fill it out sequentially by bid Item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation, and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department of a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract Item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract Item.

When material invoices, freight bills, and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); Project name and number where material will be incorporated, manufacturer, product number, quantity and cost.

Add the following Subsection 106-1.09:

106-1.09 RESERVED.

E34-012707

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.01 LAWS TO BE OBSERVED.  Add the following:

The Contractor is required to follow bird clearing restrictions between April 15 to July 15 in accordance with the Migratory Bird Treaty Act, 16 U.S.C. 703.

51132-032311

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following:

Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling, or staging, on or off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also, provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following:

The Department has received the following permits on the Contractor’s behalf:

1.	Corps of Engineers, Section 404/10 permit POA-1998-184 with permit modifications M, N, O and M4, Expires June 30, 2015.

2.	Department of Fish and Game (ADF&G), Title 16, Fish Habitat Permit FH – 11 – IV – 0426, Expires September 15, 2012.

3.	Department of Fish and Game (ADF&G), Title 16, Fish Habitat Permit FH – 11 – IV – 0536, Expires September 15, 2012.

4.	Department of Fish and Game (ADF&G), Title 16, Fish Habitat Permit FH – 11 – IV – 0537, Expires September 15, 2012.

5.	Department of Fish and Game (ADF&G), Title 16, Fish Habitat Permit FH – 11 – IV – 0538, Expires September 15, 2012.

6.	Department of Fish and Game (ADF&G), Title 16, Fish Habitat Permit FH – 11 – IV – 0539, Expires September 15, 2012.

7.	Alaska Department of Environmental Conservation (ADEC) Non – Objection Letter dated February 24, 2011.

8.   Matanuska-Susitna Borough, Flood Hazard Development Permit FHDP 172920110007, Expires April 7, 2013.

Provide information to comply with the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

CR7-020810

Standard Modifications

107-1.05 FEDERAL AID PROVISIONS.  Add the following after paragraph two:

Form 25D-55H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the Contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds.  Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements.  During the performance of this Contract, the Contractor, for itself, its assignees, and successors in interest (hereinafter referred to as the "Contractor") agrees as follows:

(1)	Compliance with Regulations:  The Contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") Title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this Contract.

(2)	Nondiscrimination:  The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The Contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, Section 21.5 of the regulations, including employment practices when the Contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitation for Subcontractors, Including Procurements of Materials and Equipment:  In all solicitations either by competitive bidding or negotiation made by the Contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the Contractor of the Contractor's obligations under this Contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports:  The Contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions.  Where any information required of a Contractor is in the exclusive possession of another who fails or refuses to furnish this information the Contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance:  In the event of the Contractor's noncompliance with the nondiscrimination provisions of this Contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a)	withholding of payments to the Contractor under the Contract until the Contractor complies, and/or

(b)	cancellation, termination, or suspension of the Contract, in whole or in part.

(6)	Incorporation of Provisions:  The Contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The Contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance:  Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the Contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the Contractor may request the United States to enter into such litigation to protect the interests of the United States.

E67-101509

Special Provision

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:

When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

CR7-020810

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following paragraphs:

7.	Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:

Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization, the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35-012707

Special Provisions

Add the following:

If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR7-020810

Add the following:

Bald Eagles are protected under the Bald Eagle Protection Act (16 U.S.C. 668-668c) which prohibits “takes” of bald eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of a minimum 330 ft as an undisturbed habitat buffer around nesting bald eagles.  If topography or vegetation does not provide an adequate screen or separation, extend this buffer to 0.25 miles, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330 ft and 660 ft from eagles nest tree no obtrusive facilities or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, this buffer shall extend up to 0.5 miles.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (March 1 – August 31) within the primary or secondary zones.

Extremely noisy activities such as road construction or other activities that occur within the Secondary Zone shall be conducted outside the nesting period to avoid disturbance to eagles.  If activities occur in proximity to a nest site, employ an individual qualified to observe and assess the impact of such activities on nesting eagles.  Behavior generally associated with disturbed eagles includes alarm calls, birds flushed from their nest or perch, and aggressiveness.

If nest trees are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 786-3503 or (907) 271–2722, before starting construction activities, for further site evaluation.  This is an advisory.  Do what is required to keep from disturbing a nesting eagle.

CR1071-081210

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity Disadvantaged Business Enterprise and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A 301

EEO-1 Certification	Form 25A 304

ADOT&PF Training Program Request	Form 25A 310

Training Utilization Report	Form 25A 311

Contact Report	Form 25A 321A

DBE Subcontractable Items	Form 25A 324

DBE Utilization Report	Form 25A 325C

Summary of Good Faith Effort Documentation	Form 25A 332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D 55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

S80-012202

SECTION 108

PROSECUTION AND PROGRESS

Special Provision

108-1.01 SUBLETTING OF CONTRACT. Delete paragraph four and replace with the following:

Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract.  The certification will be accepted by the Department in lieu of written approval of subcontracts.  The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

a.	The Department is furnished with one completed Contractor Self certification, Form   25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

b.	The subcontractors have submitted a Bidder Registration; Form 25D-6;

c.	The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

d.	The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

e.	Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

CR57-010208

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:

Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in No. 1.  A progress schedule, and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

CR261-121302

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.

Add the following to No. 3:

f.	Digital Terrain Model.  Using Department approved Computer-Aided Design (CAD) software compute the volume between two Digital Terrain Model surfaces.

51132-081010

Under subtitle Electronic Computerized Weighing System Item (1) add the following to the end of the first sentence:

", CD, or a USB device."

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

CR14-043105

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of Subsection 105-1.16.

E11-063004

Special Provisions

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as the Department deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

1.	Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE).  An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification.  For purposes of soliciting DBE participation on a project and to count toward a Contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer.  A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A 324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A 325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A 325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE.

1.	Phase I - Bid.  Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment.  Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

(1)	A description of the work that each DBE will perform;

(2)	The dollar amount of participation by the DBE firm;

(3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

(4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report.  Form 25A 325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A 332A and attachments) and DBE Contact Reports (Form 25A 321A) if the Contractor submits less DBE utilization on Form 25A 325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A 325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement.  If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

(1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

(2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT.

1.	Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A 324) prior to bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening.  The bidder must give the DBEs no less than 5 days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.  DBEs certified to perform work items identified on Form 25A 324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A 321A).

d.	Non-competitive DBE quotes may be rejected by the bidder.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10 percent higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service.  Bidders must have a non-DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A 321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

2.	Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appeal able to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.  CUF is limited to that of a:

a.	regular dealer;

b.	manufacturer;

c.	broker;

d.	subcontractor;

e.	joint-venture; or

f.	prime contractor.

2.	Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.  (This does not affect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of:

(1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

(2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

(1)	The work performed will be necessary and useful work required for the execution of the Contract.

(2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

(3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

(4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

(5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

(6)	Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

(7)	The DBE will control all business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, report on Form 25A 336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either:

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either:

(1)	increasing the participation of other DBEs on the project;

(2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

(3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of No CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appeal able to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100 percent of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product, or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A 325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.

S33-111700

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.  Add the following:

Designate the clearing limits with survey flagging and stakes. Survey flagging spacing shall be no greater than 50 feet.

No heavy equipment may be used for clearing within wetland areas shown on the Plans, unless the work is performed when the ground is frozen.  When clearing in areas outside the slope limits, minimize disturbance to the underlying root mat.

Except for timber disposed as root wads, under Subsection 201-3.06, timber with a 5 inch diameter or larger at breast height shall be cut into 8-foot lengths, de-limbed, and stacked to a height no greater than 6 feet at locations approved by the Engineer for public removal. These locations shall be adjacent to the nearest turnout, side street, or other approved site which does not create a traffic hazard due to lack of adequate parking for the public. Access to the sites shall be maintained, controlled by flaggers, in accordance with Subsection 643-3.04.  The Contractor shall provide and maintain a separate firewood telephone hotline that details when and where the wood is available to the public. Special Construction Signs, in accordance with Subsection 643-2.01, shall be used to advertise the firewood telephone hotline. No mechanical loading by the public will be allowed.  Provide two weeks for the public to access each area of the project where timber is made available. The Contractor shall dispose of the timber left by the public after the two week time period.

51132-081010

The Contractor shall perform the work necessary to preserve and/or restore land monuments and property corners from damage.  A land monument or property corner that is disturbed shall be restored according to Section 642 at the Contractor’s expense.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR107-061004

See subsection 107-1.01 for limitations on clearing and grubbing during the migratory bird window of April 15 to July 15.

51132-032311

201-3.02 CLEARING.  Replace the last sentence in the second paragraph with the following:

Trees and brush shall be cut/ground flush to the surrounding ground level.

201-3.06 DISPOSAL.  Replace this section with the following:

Dispose of all vegetation and debris removed by clearing or grubbing by burying, or other approved methods and at approved locations.  Burning of vegetation and debris is not permitted.

Obtain the property owner’s written permission to dispose of vegetation and debris at locations outside the right-of-way limits and a waiver of all claims against the State for any damage to such land which may result.  Obtain all permits required by law for such disposal.  Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work.

Rootwad Salvage.

50 Spruce and/or cottonwood rootwads shall be salvaged from areas designated for grubbing and delivered to DNR at 5310 S. Bodenburg Loop, Palmer, AK to be stored for the State of Alaska for future projects. Contact the DNR representative, Stoney Wright (phone 907-745-8105), 10 days prior to delivery to coordinate delivery.  Acceptable rootwads shall be a minimum of 6 feet in diameter with at least 10 feet of trunk (bole) attached with the bole diameter at breast height (dbh) equal to 8 inches.  Handle the rootwads carefully to prevent damage.  Contractor is responsible for all transport and handling of rootwads.  Do not include birch rootwads.

Remove rootwads when soils are not frozen: Grub around each tree, push it over and trim the trunk (boles) and rootwad to the required dimensions keeping the bole attached to the rootwad.  Soil may be removed from the rootwad as required for ease of handling.

Contact ADF&G Lands Manager Joe Meehan (267-2281) and ADF&G Habitat Biologist Mark Fink (267-2338) for transporting and handling instructions prior to beginning clearing activities and again upon completion of activities.

All merchantable timber remaining from the clearing area after firewood removal by the public and rootwad salvage becomes your property, unless otherwise specified.

201-4.01 METHOD OF MEASUREMENT.  Add the following:

The work required for cutting, de-limbing, and stacking timber for public removal and to preserve and restore land monuments and property corners will be subsidiary to Section 201 items.

201-5.01 BASIS OF PAYMENT.  Add the following:

Item 201(9) Rootwad Salvage. Payment includes work and materials required for harvesting, trimming, transporting, and delivering 50 rootwads as specified in this Section. Delivery of rootwads includes providing means at the final destination for unloading, moving, and placing rootwads in storage location.

Work associated with providing and maintaining the firewood telephone hotline will be subsidiary to Section 201 items.

Flagging and Special Construction Signs required for public notification and to control access points to firewood made available to the public will be paid under the respective bid items listed in the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

201(9)	Rootwad Salvage	Lump Sum

51132-033011

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.  Add the following:

This work shall also include the removal of dowelled curbs and the repair of the cavities left after the removal.

This work shall also include the capping, grouting, and abandoning culvert pipes shown in the plans.

51132-081910

This work shall also include the removal of gas pipe, removal of storage tanks (either fuel or septic) and the decommissioning of ground water wells.

CR112-010610

202-3.01 GENERAL.  Add the following:

The removal of buildings, foundations, and structures shall include removal of utility lines, sidewalks, and other attached appurtenances.

Buildings being removed may contain asbestos.  Take special handling measures when removing this material.

Cut the ends of retaining walls to remain after partial removal neat and true with no shatter outside the removal area.

Remove septic or fuel tanks according to the Department of Environmental Conservation (DEC) regulation.  Remove or decommission wells according to DEC regulations.

CR112-010610

Carefully remove fences designated by the Engineer to the right-of-way limit, or to the end of the span beyond the right-of-way limit.  These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After the construction of noise barrier or fence is complete, use salvaged fencing to fill possible fencing gaps behind the property line.  Use salvaged fencing according to Section 607, for reconstructed fences.

CR17-102402

For purposes of this Contract, “other obstructions” may include abandoned items within the Right-of-Way and may include appliances, vehicles, tanks, tools, equipment, and other such considered junk items.

Fill the cavities left after the removal of dowelled curb in a manner acceptable to the Engineer.

202-3.02 MAIL BOXES.  Add the following:

Contact Dan Carper (USPS Postmaster, 745-5051) one week in advance of mail box removing or resetting so he can coordinate the locations and notify affected property owners.

202-3.03 REMOVAL OF BRIDGES, CULVERTS, AND OTHER DRAINAGE STRUCTURES.  Replace the third paragraph with the following:

When culvert pipe is designated on the Plans to be abandoned in place, grout the entirety of the pipe from end to end by an approved method. Securely plug other conduits by an approved method.

51132-033011

202-3.04 REMOVAL OF PIPE.  Add the following:

During project construction, ENSTAR Natural Gas Company will abandon existing gas pipelines.  Follow the procedures given in Subsection 105-1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned.  Once the pipelines are abandoned, remove abandoned natural gas pipe within the right-of-way that are in conflict with the work and dispose of pipes off the project limits.

CR112-010610

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:

Removed pavement material, including sidewalks and curbs, is the property of the Contractor.  Handle and transport materials according to the Alaska Department of Environmental Conservation (DEC) regulations.  Store materials at the Contractor’s DEC approved site.

Removed pavement, sidewalks, and curbs may be used for embankment construction if it is not exposed at the completed embankment surface.  Maximum allowable dimension of broken materials is 6 inches.  The use of pavement, sidewalk, and curb in the embankment requires written approval and direction for use from the Engineer.

CR2022-010610

Dowels from curb may not be placed in the embankment.

Dowelled curb shall be removed in a manner that leaves the underlying pavement intact. Damage done to the pavement during the removal of the dowelled curb shall be repaired by the Contractor, in a manner acceptable to the Engineer, at no additional cost to the Department. Remove the existing aggregate base course placed on the asphalt between the existing curb and gutter and dowelled curb from Station 156+25 to Station 163+75. Wash and/or sweep the paved surface clean and free of loose materials to the satisfaction of the Engineer.

51132-081910

Dispose of removed pavement, sidewalks, and curbs not wanted by the Contractor and not used in the project, according to subsection 202-3.09.

CR2022-010610

Add the following Subsection 3.06:

202-3.06 - RESERVED

51132-032211

Add the following Subsection 3.07:

202-3.07 GROUND WATER WELL DECOMMISSIONING.  Decommission the water wells according to DEC requirements conforming to 18AAC 80.015 Well Protection Source Water Protection, and Well Decommissioning, or a DEC approved alternate method.  Develop and submit a detailed Ground Water Well Decommissioning Plan to the Engineer.  Contact the Wasilla DEC office at (907) 376-5038, for plan review requirements of alternate methods.

CR112-010610

Add the following Subsection 3.08:

202-3.08 - RESERVED

51132-032211

Add the following Subsection 3.09.

202-3.09 DISPOSAL OF PAVEMENT, SIDEWALKS, AND CURBS.

Disposal sites shall be outside the project limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Dispose of solid waste materials, pavement, sidewalk, and curb (including handling, transporting, storing and disposing) according to the Alaska Department of Environmental Conservation (DEC) Regulations.

A DEC Permitting Officer in Anchorage may be contacted at (907) 269-7590.

CR2021-010610

202-5.01 BASIS OF PAYMENT.  Add the following:

Acquiring a solid waste disposal permit from DEC is subsidiary to 202 Pay Items.

CR2021-010610

Item 202(1).  Also includes removing and disposing all “other obstructions” (aka junk items) within the Right-of-Way.

Add the following to the end of the second paragraph

Removal of dowelled curb shall be paid for as item 202(9) Removal of Curb and Gutter. Payment includes full compensation for labor, materials, and equipment for the removal, disposal, repair of cavities, removal of aggregate base course on the existing pavement, and cleaning of the paved surface. Grouting and abandoning of culvert pipes is subsidiary to 202(4) Removal of Culvert Pipe.

51132-080510

Add the following:

Item 202(13).  At the Contract Unit price for the actual length of fence taken down, disposed or delivered to the owner, regardless of the type or height.  Payment includes full compensation for labor and materials required to perform this work.

CR17-102402

Item 202(16).  At the Contract Unit price for the length of pipe removed, regardless of size.  Payment includes full compensation for labor, materials, and equipment required to remove and dispose of the pipes as shown in the Plans.

Item 202(18).  At the Contract Lump Sum price for each tank removed and disposed of according to DEC regulations.  Payment includes full compensation for labor, materials, necessary excavation, purging, processing, or removing fuel contaminated soils around the tanks, and backfilling the resultant hole.

Item 202(23A).  At the Contract Unit price for each well decommissioned according to DEC regulations.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

202(13)	Removal of Fence	Linear Foot

CR17-102402

Pay Item No.	Pay Item	Pay Unit

202(16)	Removal of Gas Pipe	Linear Foot

202(18)	Removal of Storage Tanks	Each

202(23A)	Ground Water Well Decommissioning	Each

CR112-010610

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-3.01 GENERAL.  Replace the last sentence in the third paragraph with the following:

Prevent disturbing material and vegetation outside of the clearing limits shown on the Plans.

203-3.03 EMBANKMENT CONSTRUCTION.  Add the following:

Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements.  Reduction in excavation or Borrow quantities because of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.

Delete the first sentence of the tenth paragraph and substitute the following:  Place roadway embankment of earth materials in horizontal layers not exceeding 8 inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by 1 foot and transversely by 10 feet.

203-4.01 METHOD OF MEASUREMENT.  Replace No. 1. with:

1.	Items 203(1) through 203(5) and 203(8).  The volume measured in original position according to Subsection 642-3.08, Contractor Furnished Computations.

Add the following:

No deduction from the excavation quantities will be made for grubbing removed under 201(2A) Grubbing, or pavement removed under Item 202(2) Removal of Pavement.

203-5.01 BASIS OF PAYMENT.  Add the following:

Progress payments will be made using interim volume reports per Subsection 642-3.08.1.d(1).  Progress payments require the submittal of neat-line and topographic surfaces with each request for payment.  10% of the Contract excavation quantity will be withheld until the final computations are accepted by the Engineer.  Final Payment will be made per Subsection 642-3.08.1.d(2).

51132-080510

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Standard Modifications

204-3.01 CONSTRUCTION REQUIREMENTS.  In the first sentence of paragraph four, delete:

“bedding and”

E37-012707

Special Provisions

Add the following after the third paragraph:

Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.

CR204-020608

204-5.01 BASIS OF PAYMENT.  In the third paragraph, in each instance, replace “12 inches” with “24 inches.”

51132-033011

SECTION 206

FILTER BLANKET

Special Provisions

Replace Subsection 206-4.01 with the following:

206-4.01 METHOD OF MEASUREMENT.

Filter Blanket will not be measured for payment.

Replace Subsection 206-5.01 with the following:

206-5.01 BASIS OF PAYMENT.

Filter Blanket shall be subsidiary to other items.

51132-081010

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

Special Provision

301-2.01 MATERIALS.  Add the following after the first sentence:

Recycled Asphalt Material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70 – 100 |
| 3/8 inch | 42 – 90 |
| No. 4 | 28 – 78 |
| No. 16 | 11 – 54 |
| No. 50 | 5 – 34 |
| No. 100 | 3 - 22 |
| No. 200 | 2 – 12 |

3.	The asphalt content shall be 2.5 – 5.0 percent by weight of the RAM.

CR176-012407

301-3.01 PLACING.  Add the following:

Base course material used for the sidewalk and pathway foundation shall be placed with a “Layton box” or similar equipment capable of providing a specified depth with a uniform surface.

CR26-090189

301-3.03 SHAPING AND COMPACTION.  Add the following:

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi ( 5 psi) and the roller shall have a minimum operating weight per tire of 3,000 pounds.

CR176-012407

Areas with 3 inches or less of Aggregate Base Course shall be compacted to the satisfaction of the Engineer.

51132-080510

301-5.01 BASIS OF PAYMENT.  Add the following:

Recycled asphalt material substituted for aggregate base course will be paid for as Item 301(1) Aggregate Base Course, at the unit price shown in the bid schedule for that Item.

CR176-012407

Special Provisions

Replace Section 306 with the following:

SECTION 306

ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt cement in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Cement) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Cement |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt cement content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if WAQTC FOP for AASHTO T308 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt cement proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306(6) Asphalt Price Adjustment - Quality.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04.  Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT CEMENT.  Conform to 702-2.01 and the following:

The total asphalt cement content may be a combination of PG 52-28 and the residual asphalt cement/binder in the RAP, or only PG 52-28.  Documentation and conformance is required for the PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt cement is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.05 and 3.06 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt cement content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11, unless the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

2.	Asphalt Cement.  By the ton, as follows.

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement, except ATM 405 will not be used when RAP is included in the mixture.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste ATB will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimal asphalt cement content specified in the JMD.

3.	Asphalt Price Adjustment - Quality.  Determined under Subsection 306-4.03 Evaluation of Materials for Acceptance.  Also included in the measurement are the fees specified in Subsections 306-2.01, 4.02, 4.03 and 5.01.

306-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 306-4.03 Evaluation of Materials for Acceptance, and is included in Item 306(6) Asphalt Price Adjustment - Quality.  Fees assessed are also included in Item 306(6).

ASPHALT TREATED BASE

The quantity of ATB produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 10,000 tons.  The lot will be divided into sublots of 1000 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.

If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 306-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 3,000 tons and 10,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 1000 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 306-4.03 except as noted.

For Contract quantity of less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any ATB that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Asphalt treated base mix samples taken for the determination of asphalt cement content will be taken randomly from behind the paver screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308, except ATM 405 will not be used when RAP is included in the mixture.

2.	Aggregate Gradation.

ATB without RAP.  Samples taken for the determination of virgin aggregate (aggregate) gradation will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2.  Locate diverter devices for obtaining aggregate samples on the conveyor system delivering combined aggregates, not including RAP, into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the ATB.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Aggregate samples from the cold feed conveyor will be used to determined the gradation according to WAQTC FOP for AASHTO T 27/T 11 or the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

ATB with RAP.  For ATB samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

The Engineer will determine and mark the location(s) where the Contractor will take each mat core sample.  The location(s) for taking mat core samples will be determined using a set of random numbers and the Engineer's judgment.

Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new ATB within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A fee will be assessed for each failure to take core samples, backfill core sample voids, backfill core samples within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.

A retest of any sample outside the limits specified in Table 306-2 may be requested provided the quality control requirements of 306-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 306-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 306-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt cement after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

Price adjustments in this subsection are addressed under Pay Item 306(6) Asphalt Price Adjustment-Quality.

Price Adjustment Base (PAB)

PAB = $98 per ton

ASPHALT TREATED BASE

The total Asphalt Treated Base price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to ATB when the contract quantity equals or exceeds 3000 tons, except as specified in Subsection 306-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03.3 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors for the ATB.  The first factor is the composite pay factor (CPF) and includes gradation and asphalt cement content.  The second factor is the density pay factor (DPF).

A lot containing ATB with a pay factor less than 1.00 will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing ATB that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

ATB rejected based on visual inspection will be tested if requested by the Contractor.  A minimum of two samples will be collected from the rejected ATB and tested.  If test results are within specification limits, payment will be made for the ATB.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be assessed as a fee and paid by the Contractor under Pay Item 306(6) Asphalt Price Adjustment - Quality.  Costs associated with removal and disposal of the rejected ATB are subsidiary to the Asphalt Treated Base Pay Items.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

For a sublot, when gradation and asphalt cement content are determined from separate samples, the individual test results for density, gradation, and cement content, that are not an outlier, will be included in price adjustment.

Quality Level Analysis (QLA).

Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

Pay factors for the remaining test results are computed as follows:

x

1.	Arithmetic mean:

n

x =

∑x

Where:		∑	=	summation of

x 	=	individual test value to xn

n 	=	total number of test values

x

x

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation:	s

n∑(x2) – (∑x)2

s =

n(n-1)

Where:		∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

s 	is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.

s 	is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If s < 0.001:

	Density and all sieves, except the No. 200, s = 0.20.

	Asphalt cement content and the No. 200 sieve, s = 0.02.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 306-2.  The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 99% of MSG.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 99 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index:	QU

USL  -  x

QU  =

s

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

s

5.	The Lower Quality Index:	QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit corresponding to a given QU), Subsection 106-1.03.

7.	PL (percent within the lower specification limit corresponding to a given QL), Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation (PFsieve size) and asphalt cement content (PFac) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) combines the gradation and asphalt cement content pay factor from Step 9 for the lot and is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 306-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 306-3

WEIGHT FACTORS

| Sieve Size | Type II Factor “f” |
| --- | --- |
| 1 inch sieve | - |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt % | 40 |

Asphalt Treated Base Price Adjustment = PAB x Q x 0.5 x [(CPF or DPF)* -1.00]

PAB		= Price Adjustment Base

Q 		= tons in Lot

CPF 	= Composite Pay Factor

DPF 	= Density Pay Factor

*CPF or DPF, whichever is lower.

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 306-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 306-4.

Table 306-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 | --- | > 3 | --- | --- | --- | --- | --- | --- |
| Dynamic Shear | > 1.00 kPa | > 1.00 | --- | 0.88-0.99 | --- | --- | --- | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 | --- | --- | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 | --- | --- | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 | --- | 1.001-1.092 | --- | --- | --- | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 | --- | 1.816-2.199 | --- | --- | --- | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 | --- | 5001-5289 | --- | --- | --- | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 | --- | 301-338 | --- | --- | --- | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 | --- | 0.287-0.299 | --- | --- | --- | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF 		= Pay Reduction Factor from Table 306-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to, a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401, Approach HMA as included in 401 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt cement, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306(6) Asphalt Price Adjustment - Quality: is the sum of the price adjustments for each material lot and for fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

306(1)	ATB	Ton

306(2)	Asphalt Cement, Grade PG 52-28	Ton

306(6)	Asphalt Price Adjustment - Quality	Contingent Sum

306(10)	Asphalt Material Price Adjustment – Unit Price	Contingent Sum

CR306-101110

Special Provisions

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

CR401-101110

Do not place the final lift of HMA on Trunk Road until the embankment has settled for one winter.

1.	In this Section, HMA refers to Type I, II, III and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

c.	Use of Recycled Asphalt Pavement (RAP) is not permitted in HMA, except RAP may be used in HMA, Type II, Class B.

d.	Warm Mix Asphalt (WMA) is not permitted in HMA.

51132-033011

MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

TABLE 401-1

hMA Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Cement) |  |  |
| Stability, Pounds | 1800 Min. | 1200 min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix, % | 3 - 5 | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Cement |  |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 75 | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 401-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving.  HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each Type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified.  The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD.  Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 401-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 401-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 401-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.  Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 401(6) Asphalt Price Adjustment – Quality.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04.

Use a minimum of three stockpiles for crushed HMA aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Conform to 702-2.01.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt cement is required.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 401-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.02.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips:  Subsection 401-5.01 Basis of Payment and as noted here.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed.  The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is a minimum of 40° F or warmer.  HMA Type II, Class A - Do not place mix after September 15 unless approved by the Engineer in writing.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hours before placement of the test strip HMA.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT.  Costs associated with Subsection 401-3.04 are subsidiary to Section 401 Pay Items.

Vehicles/Equipment.  Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer cover the HMA in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 401-3.16 Patching Defective Areas.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.  Use means and methods approved by the paver manufacturer.  Means and methods may consist of chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact HMA mixtures and reverse without backlash.

Use pneumatic rollers to compact the prelevel/leveling course.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place.  Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2 inch with HMA, Type IV.  Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

	Where the planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with HMA, Type II, Class B.  Cold mix HMA prohibited.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of HMA on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

401-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

401-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling (preleveling) course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place the final lift until curb and gutter, all types, are installed complete, except as approved by the Engineer.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of each Type of HMA.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required).

When directed by the Engineer, provide density profiles of the mat and longitudinal joints with a nuclear density gauge.  Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in Process Quality Control Subsection 401-2.05.

401-3.14 JOINTS. Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702.  Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal.  Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in elevation of the final surface of adjacent mats each side of the longitudinal joint, at the joint, with a straight edge and by requiring the Contractor to flood the joint surface with water.  The Engineer will determine where and how often to evaluate the joint.  All differences in the surface elevations greater than 1/8 inch or that pond water shall be repaired at no cost to the Department.  Heat the HMA pavement to be repaired with an infrared heater (310˚ F max) and roll flat or add HMA until the joint differential is within tolerance.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to subsection 401-4.03.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, intersections, ramps, and lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to subsection 401-3.13 to grade, and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

b)	By the final HMA surface area.

2.	Asphalt Cement.  By the ton, as follows:

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

5.	Preleveling/Leveling Course.  By weight or Lane-Station (12 foot width).  No deduction will be made for the weight of asphalt cement or anti stripping additive.

6.	Asphalt Price Adjustment – Quality.  Calculated by quality level analysis under Subsection 401-4.03.  Also included in the measurement are the fees and deductions specified in Subsection 401-2.01 and Subsection 401-4.02.

Asphalt Price Adjustment – Quality, does not apply to, and measurements will not be made for: 1) Leveling Course/Prelevel (rut repair) HMA, 2) Temporary HMA, 3) Approach HMA.

7.	Longitudinal Joint and Joint Adhesive.  By the linear foot of longitudinal joint.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 401-4.03 Evaluation of Materials for Acceptance, and is included in Item 401(6) Asphalt Price Adjustment-Quality.  Penalties assessed are also included in Item 401(6).

A mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 401-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each Class and Type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (also for approaches and temporary pavement), HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T2 or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

a.	Acceptance Testing.

The Engineer will determine and mark the location(s) where the Contractor will take each core sample.  Core samples will not be taken at bridge decks or the milled edge of existing pavement.

1)	Mat Cores:  The location(s) for taking core samples will be determined using a set of random numbers and the Engineer's judgment.

2)	Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.  Take joint core samples in the presence of the Engineer.

Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new HMA within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A penalty will be assessed for each failure to take core samples or backfill core sample voids within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 401(6) Asphalt Price Adjustment-Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each Type of HMA when the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean 	 of the remaining test results is determined:

n

x =

∑x

Where:		∑	= summation of

x 	= individual test value to xn

n 	= total number of test values

(x)

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:		∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 98 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:

USL  -  x

QU  =

S

Where:		USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:		LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| Sieve Size | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| 3/4 inch sieve | 4 | 4 | - |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $100 per ton

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 401-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

Table 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF 		= Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

PAVEMENT SMOOTHNESS

The top layer of HMA will be measured according to 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 		= Final quantity of HMA, tons

PrI		= Final measured hot mix smoothness, inches/mile

SF 		= Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities equal or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG, apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

401-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401, Approach HMA as included in 401 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

401-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Asphalt cement, anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, patching defective areas, repair work and materials when planing equipment breaks through existing pavement - Subsection 401-3.07 Preparation of Existing Surface, and the work and materials associated with Subsection 401-3.04 Hauling Equipment are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 401(1F) Hot Mix Asphalt, Preleveling/Leveling Course, Type IV: Asphalt Cement, anti-stripping additives are subsidiary.

Item 401(3) Hot Mix Asphalt, Temporary, Type II, Class B: Asphalt cement, anti-stripping additives, removal and disposal are subsidiary.

Item 401(6) Asphalt Price Adjustment – Quality:  is the sum of the price adjustments for each material lot (excluding the Preleveling/Leveling Course (rut repair) HMA, Temporary HMA and Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

	Each mix design subsequent to the approved Job Mix Design (Subsection 401-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 401-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 401-4.02).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1A)	Hot Mix Asphalt, Type II; Class A	Ton

401(1F)	Hot Mix Asphalt, Preleveling/Leveling Course, Type IV; Class B	Lane-Station

401(2)	Asphalt Cement, Grade PG 52-28	Ton

401(3)	Hot Mix Asphalt, Temporary, Type II; Class B	Ton

401(4)	Hot Mix Asphalt, Type     ; Class     	Square Yard

401(6)	Asphalt Price Adjustment - Quality	Contingent Sum

401(8)	Hot Mix Asphalt, Approach, Type     ; Class     	Ton

401(9)	Longitudinal Joint Adhesive	Linear Foot

401(10)	Asphalt Material Price Adjustment – Unit Price	Contingent Sum

CR401-101110

SECTION 504

STEEL STRUCTURES

Standard Modification

504-3.01 FABRICATION.

Delete subsection 8 in its entirety and replace with the following:

8.	Welding.  Perform welding and Nondestructive Examination (NDE) as specified or shown on the Plans.  Conform to the ANSI/AASHTO/AWS Bridge Welding Code D1.5 when welding new steel bridge girders, beams, and stringers.  Conform to the Structural Welding Code AWS D1.1 when welding all other steel structures.

At least 30 days before welding, submit for approval a welding plan that has been signed and stamped by a Certified Welding Inspector (CWI) responsible for Quality Control (QC) and consisting of the following documents.

a.	Quality Control personnel qualifications listing CWI number;

b.	Welding Procedure Specifications (WPS) using forms in AWS D1.1, Sample Welding Forms;

c.	Procedure Qualification Records (PQR) when applicable, using forms in AWS D1.1, Sample Welding Forms;

d.	Welder Performance Qualification Records (WPQR) using forms in AWS D1.1, Sample Welding Forms with the documentation of current welder certification;

e.	Sample daily inspection sheet; and

f.	Type and extent of NDE to be conducted, as required in the specifications.

E39-012707

Perform Quality Control inspection necessary to ensure the materials and workmanship meet the requirements of the Contract documents.  Use a current AWS CWI for welding inspection.

51132-120610

Correct deficiencies in materials and workmanship revealed by Quality Control and Quality Assurance inspections without additional compensation.

Furnish completed Quality Control inspection documents to the Engineer and to the Quality Assurance representative designated by the State (when designated).

Meet Charpy V-notch impact test requirements as shown on the Plans and according to Sections 715 and 716, except that the impact energy values for filler metals must not be less than that of the base metals to be joined, when tested at the same temperature as the base metal.

E39-012707

SECTION 505

PILING

Special Provisions

505-3.03 PILE BEARING VALUES.  Delete the first paragraph of this subsection and substitute the following:

Drive piles, except piles for lighting standards, to the required ultimate bearing capacity.  For lighting standards, install piles of sufficient length to cut the pile at the required cut off elevation and to provide the minimum installed length shown on the Plans.

505-3.09 DRIVING PILES.  Add the following:

Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length shown on the Plans for a lighting standard foundation cannot be achieved, install the pile tip to an elevation established by the Engineer.

505-4.01 METHOD OF MEASUREMENT.  Add the following to the second paragraph:

Do not measure piles for lighting standards for payment.

505-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

Include costs of furnishing and installing piles for lighting standards for Pay Item 660(3) Highway Lighting System Complete.

CR65-041505

SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

602-1.01 DESCRIPTION.  Add the following:

This work shall also consist of installing temporary creek diversion(s).

This work also includes installing baffles and boulders inside structural plate pipes as shown on the Plans.

602-2.01 MATERIALS.  Add the following:

Materials and fabrication for baffles shall conform to Section 504.

Add the following subsection:

602-3.02 TEMPORARY CREEK DIVERSION.  The Contractor shall submit a temporary creek diversion plan to the Engineer for approval before pipe installation.  The diversion plans shall be in compliance with applicable permits.

Areas used for temporary diversions shall be restored in accordance with Subsection 107-1.11.7.

Add the following subsection:

602-3.03 CREST STAGE GAUGES.  Crest stage gauges are located at Wasilla Creek near the existing culvert inlet on N. Palmer Fishhook Road and are shown in the Plans.  Do not damage, disturb, or remove the existing gauges.

Coordinate installation of the Structural Plate Pipe at the Wasilla Creek N. Palmer-Fishhook crossing with the United States Geological Survey (USGS) water resource office.

Contact the USGS water resource office two (2) times; 1) one week before starting installation and 2) at the time of pipe and associated riprap installation completion.

Contact Chad Smith at the USGS water resource office at (907) 786-7103.

602-5.01 BASIS OF PAYMENT.  Add the following:

The following items will not be paid for directly, but will be subsidiary to 602 items:

- Bedding for pipe

- Furnishing, fabricating, installing and watertight sealing the baffles.

- Furnishing and installing boulders inside the pipe at Carnegie Creek

- Creating temporary creek diversions or drainage diversions including but not limited to diverting water, dewatering, excavation, installing and removing temporary pipes, temporary pipes, installing and removing lined channels, restoring disturbed areas, and other associated items.

51132-033011

SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:

This work shall also consist of installing temporary creek diversion(s) ***Deleted*** as shown on the Plans.

51132-033010

Add the following:

This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following:

Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9 inches.

CR42-082703

***Deleted***

603-3.03 JOINING PIPE.

2.	Metal Pipe.  Add the following after the 2nd sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe of similar or dissimilar materials, regardless of the type of coupling band.  Except, the end section joint does not require a gasket.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

3.	Polyethylene Pipe.  Add the following after the 1st sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe.  Except, the end section joint, and where the pipe is manufactured with a locking joint such that the joint seals watertight, a gasket is not required.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

CR6031-032411

Add the following subsection:

603-3.04 TEMPORARY CREEK DIVERSION.  The Contractor shall submit a temporary creek diversion plan to the Engineer for approval before 60 inch pipe installation.  The diversion plans shall be in compliance with applicable permits.

Areas used for temporary diversions shall be restored in accordance with Subsection 107-1.11.7.

51132-033010

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:

Culvert marker posts will not be measured for payment.

CR42-082703

603-5.01 BASIS OF PAYMENT.  Replace the first sentence with:

Coupling bands, gaskets and other items necessary for the proper joining of the sections are subsidiary.

CR6031-032411

Add the following:

Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items:

CR42-082703

Add the following:

The following items will not be paid for directly, but will be subsidiary to 603 items:

- Bedding for pipe

- ***Deleted***

- Creating temporary creek diversions or drainage diversions including but not limited to diverting water, dewatering, excavation, installing and removing temporary pipes, temporary pipes, installing and removing lined channels, restoring disturbed areas, and other associated items.

Add the following:

The Engineer may withhold payment for 603(20) End Section Items until the corresponding energy dissipaters are in place and accepted.

51132-033010

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01 CONSTRUCTION REQUIREMENTS.  Add the following after the first paragraph:

Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch of concrete or asphalt, as applicable.

Curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  Keep the openings functional.  This may require temporary dikes, and RMC extensions, as necessary.  Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-5.01 BASIS OF PAYMENT

Pay Item 604(1) Storm Sewer Manhole, add the following, Type I.

Add the following:

Frames, grates, and lids are subsidiary to Pay Item 604(1) Storm Sewer Manhole, Type I.

51132-081010

SECTION 606

GUARDRAIL

Special Provisions

Delete Subsection 606-2.01 and replace with the following:

606-2.01 MATERIALS.  Use materials that conform to the following:

Concrete, Class A or W

(or an approved, pre-mixed, sacked concrete)	Subsection 501-3.01

Wire Cable	Subsection 709-2.02

Metal Beam Rail	Subsection 710-2.04

Guardrail Posts and Blocks	Subsection 710-2.06

Guardrail Hardware	Subsection 710-2.07

Guardrail Terminals	Subsection 710-2.11

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

The marker materials shall be durable, resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  The flexibility may be in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively impact the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole as a result of snow thrown from snowplows

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel may not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering markers.

CR6062-110410

Guardrail Reflector Assembly Brackets	Section 730

Fabricate from aluminum alloy or hot dipped galvanized steel.

Retroreflective Sheeting	AASHTO M 268, Type VIII or IX

51132-033011

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL.  Replace the second paragraph with the following:

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals that are required to completely install a segment of guardrail before beginning work on the segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic will encounter first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run will connect to existing barrier, buried in the backslope, or guardrail, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may be started at the point of connection.  The exception allows for starting at the downstream end, a temporary crash cushion or TMA is required at all incomplete upstream guardrail ends.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test Level 3 at all non-crashworthy guardrail ends within the clear zone.  Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

CR6063-110410

Replace the fourth paragraph with the following:

Install Long Span W Beam Guardrail at each pipe-arch location per Standard Drawing G-28 and the Plans.   After shaping the slopes and staking the proposed locations of Long Span W Beam Guardrail and guardrail terminal sections, adjust guardrail post locations for the entire run as necessary to ensure that the Long Spans will straddle the pipe-arches and that post installation will avoid impacts to the pipe-arches and utilities.  Request the Engineer to field verify all guardrail post locations.  Receive approval of the staked locations before installing guardrail and terminal sections.

51132-040411

606-3.02 POSTS.  Delete the first two numbered items and replace with:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Replace 3.a. with:

a.	The underlying material is no larger than six inches; and

Replace No. 4. with:

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically.  Compact under and around posts to the Engineer's satisfaction.

CR6064-110410

606-3.03 BEAM RAIL.  In the first paragraph, second sentence, replace "150 feet" with "100 feet"

CR6065-110410

606-3.05 TERMINAL SECTIONS.  Delete the second paragraph.

Replace the fourth paragraph with the following:

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Attach flexible markers to the "P.T." post of the Controlled Release Terminals.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

The connection shall not negatively impact the performance of the guardrail as noted in 606-2.01.

CR6062-110410

Add the following Subsection 606-3.09 Flexible Markers:

606-3.09 FLEXIBLE MARKERS. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

51132-033011

Add the following Subsection 606-3.10 Length of Need Verification.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

CR6068-110410

606-5.01 BASIS OF PAYMENT.  Add the following:

Payment for temporary crash cushions or TMA installed to protect motorists from guardrail installations that have not been completed within 10 calendar days of beginning installation is subsidiary to other items.

2.	Terminal Sections.  Replace a. with the following:

a.	Parallel Guardrail Terminal.  The contract price includes rail elements, posts, blocks, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

Delete b.

c.	Controlled Release Terminals (CRT).

Replace "object markers" with "terminal markers"

Add d.:

d.	Buried in Backslope Guardrail Terminal.  The contract price includes rail elements, posts, blocks, concrete, rebar, anchors, and all associated hardware required for a complete installation.

Payment will be made under:

Delete Pay Item 606(10) Slotted Rail Terminal and 606(11) Extruder Terminals.

Add Pay Item 606(13) Parallel Guardrail Terminal:

Pay Item No.	Pay Item	Pay Unit

606(13)	Parallel Guardrail Terminal	Each

CR6061-110410

SECTION 607

FENCES

Special Provisions

607-1.01 DESCRIPTION.  Add the following:

This work includes relocating decorative cobbles and boulders as part of fence reconstruction.

607-3.01 CONSTRUCTION REQUIREMENTS.  Add the following to the last paragraph:

Relocate the decorative cobbles and boulders from the base of the existing fence as directed by the Engineer.  Any cobbles and boulders remaining after fence reconstruction, and not wanted by the home owner, become your property.

607-5.01 BASIS OF PAYMENT.  Add the following:

Relocating decorative cobbles and boulders is subsidiary.

51132-040111

SECTION 608

SIDEWALKS

Special Provisions

608-1.01 description.  Add the following:

This work also consists of constructing to conform to the Plans:

1.	Asphalt pathway(s),

2.	Pattern imprinted colored concrete median(s) and roundabout truck apron.

51132-033011

608-2.01 MATERIALS.  Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM 417)

Marshall Stability, pounds, min.	1,000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

CR47-052207

3.	Colored, Cast-In-Place, Pattern Imprinted, Concrete Median(s), and Roundabout Truck Apron.

Concrete, Class A		Section 501

Reinforcing Steel		Section 503

Joint Fillers		Subsection 705-2.01

Joint Sealers		Subsection 705-2.02

Pattern Imprinting:

Patterned concrete shall be imprinted using Brickform Texturing System or equal.  Other equal imprinting system, color, color hardening, form release and sealer shall be approved by the Engineer prior to use.

Imprinted Pattern:	Brickform “European Fan” TM-400

Release Agent:	Non-staining, Dissipative Type as Acceptable to Concrete Colorant Manufacturer

Integral Color:	Red Clay, ASTM C979 and C494

Color Hardener:	Bomanite “Franciscan Red” (Heavy Duty Grade)

Cure Agent:	Membrane Color Cure ASTM C309 Water Based Emulsion as Acceptable to Manufacturer

Concrete Sealer:	Bomaseal C-18

51132-080510

Standard Modifications

608-3.03 CURB RAMPS.  Delete subsection in its entirety and replace with the following:

Construct curb ramps according to the details and the locations shown on the Plans.  Follow the construction requirements of Subsection 608-3.01.  Give the exposed concrete surface a coarse broom finish.  Install detectable warnings.

Add new subsection:

608-3.04 DETECTABLE WARNINGS.  Construct detectable warnings according to the details and the locations shown on the Plans.  Install detectable warning tile by embedding tile flanges into cast in place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch.  Align pattern on a square grid in the predominant direction of travel.  Install the same type of detectable warning tile throughout the project.

Install cast iron, yellow polymer soaked or black asphalt dip finish, with slip resistant surface with handle or flange on bottom, and with truncated dome pattern; or approved equal.

Detectable warnings shall be manufactured and installed according to the Americans with Disabilities Act Accessibility Guidelines.

- E61-072808

Special Provisions

When detectable warnings are required for existing and new uncurbed asphalt pathway/roadway intersections, place the detectable warnings in concrete as shown on the Plans.

51132-080510

- Add following subsections:

608-3.05 ASPHALT PATHWAY.  Construct asphalt pathway according to subsection 608-3.02, Asphalt Sidewalks.

CR47-052207

608-3.06 RESERVED.

608-3.07 PATTERNED CONCRETE.

Construct patterned concrete for the 1) Median(s), and 2) Roundabout Truck Apron, in accordance with the Plans.

Provide one (1) sample, 3ft x 3ft, of the proposed finish for approval by the Engineer prior to beginning work.  All patterned concrete shall match the approved sample.  Layout and place pattern to provide a uniform appearance and texture.  Significant difference in appearance (texture, pattern or other) between adjacent concrete panels from the approved sample panel including adjacent panels similar to the approved sample yet significantly different to each other will result in removal and replacement.  Removal and replacement will be at no cost to the Department.

Prevent surrounding materials from being discolored by the colored concrete.

608-4.01 METHOD OF MEASUREMENT.

Delete fifth paragraph beginning with:  “Curb Ramp” and replace with the following:

Curb Ramp.  By each installation, complete in place, including ramp runs, backing curbs, detectable warnings, flares, and landings necessary to provide a single street-level access. At the roundabout intersection, each island or median pedestrian crossing shall be measured as 2 curb ramp installations.

Asphalt Pathway.  By the ton of asphalt concrete according to Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment. Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section. Detectable warnings installed complete in place in asphalt pathway shall not be measured for payment.

Patterned Concrete.  By the square yard of finished surface area regardless of thickness, accepted by the Engineer.

608-5.01 BASIS OF PAYMENT.  Add the following:

Detectable warnings complete in place shall be subsidiary to other pay items. Concrete that detectable warnings are placed in at existing and new uncurbed asphalt pathway/roadway intersections shall be subsidiary to other items.

Patterned Concrete.  Item 608(17B) will be paid at the Contract unit price and will be full compensation for furnishing materials, surface preparation, labor, equipment, and incidentals necessary to complete the work as specified.

Forms, form release, reinforcing, reinforcing supports and ties, joint materials and sealers, color hardener, sealers, and related miscellaneous associated items, including the required test panel, are subsidiary to Item 608(17B).

Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary.

51132-033011

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

608(7) 	Asphalt Pathway 	Ton

R47-052207

608(17B)	Patterned Concrete	Square Yard

51132-080510

SECTION 610

DITCH LINING

Special Provisions

610-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

Fill the voids in Ditch Lining where specified in the Plans and by the Engineer with Selected Material, Type A (Subsection 703-2.07). Blend material prior to placing. Mixing proportions shall be as directed by the Engineer. This material is intended to inhibit subsurface stream flow through the voids provided by typical riprap installations by adding a sandy gravel to fill the voids.

610-4.01 METHOD OF MEASUREMENT.  Add the following:

Selected Material, Type A used to fill in the voids of ditch lining shall paid for as Item 203(6A) Borrow, Type A.  Labor and equipment to mix the ditch lining and Selected Material are subsidiary to 610 items.

51132-033011

SECTION 611

RIPRAP

Special Provisions

611-1.01 DESCRIPTION.  Add the following:

This work also includes placing Riprap in stream channels and inside pipes as shown on the Plans.

51132-033011

611-2.01 MATERIALS.  Add the following after the first sentence:

Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.

CR277-110705

611-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

Fill the voids in Riprap placed in stream channels and inside pipes where specified with Selected Material, Type A (Subsection 703-2.07). Blend Riprap with Selected Material prior to placing. Mixing proportions shall be as directed by the Engineer. This combined material is intended to inhibit subsurface stream flow through the voids in typical Riprap installations by adding a sandy gravel to fill the voids.

611-4.01 METHOD OF MEASUREMENT.  Add the following:

Selected Material, Type A used to fill Riprap voids shall paid for as Item 203(6A) Borrow, Type A.  Labor and equipment to mix and place the Riprap and Selected Material are subsidiary to 611 items.

611-5.01 BASIS OF PAYMENT.  Add the following:

Shaping riprap within the pipes to form low-flow channels as indicated in the Plans is subsidiary.

51132-091511

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS.  Delete first paragraph of Item 2. Including subitems a., b., c., and replace with:

2.	Sign Fabrication.	Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports.  Use white Type VIII or Type IX reflective sheeting for background of sign and stripes.

c.	Non-illuminated Overhead Signs with White Legends on Green Backgrounds.  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow Green School Area Signs.  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow green (measured according to ASTM E 2301) for ten years according to the following criteria:

	Minimum Fluorescent Luminance Factor:	YF = 20%

	Minimum Total Luminance Factor:			YT = 35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CR615-061708

Add the following:

Delineator, Flexible (Type A)	Subsection 730-2.05

Delineator, Flexible (Type B)	Subsection 730-2.05

615-3.01 CONSTRUCTION REQUIREMENTS.

4. Add the following:

Delineator, Flexible (Type B) is intended to be temporarily placed along roadways during winter shutdown. Delineator, Flexible (Type B) shall be placed at locations as directed by the Engineer and shall be removed when directed by the Engineer.

51132-303011

7. Add the following after the first paragraph:

Deliver salvaged signs panels, posts, and hardware to the State Maintenance Yard, located at:

289 Inner Springer Loop Road, Palmer Alaska.

CR6151-032411

7. Add the following:

Patch the pavement after the salvaging of signs at the intersection of Palmer-Wasilla Highway and Trunk Road in a manner acceptable to the Engineer.

615-4.01 METHOD OF MEASUREMENT.  Replace Delineators item with the following:

Delineator, Flexible (Type A). By each, complete in place. A single delineator consists of one post and ground anchor assembly equipped with reflectors.

Delineator, Flexible (Type B). The contract price includes all resources required to provide, install, and remove a single delineator. A single delineator consists of one post equipped with three reflectors.

615-5.01 BASIS OF PAYMENT.  Add the following:

Patching the asphalt at the salvaged sign locations shall be subsidiary.

Pay Item No.	Pay Item	Pay Unit

615(5A)	Delineator, Flexible (Type A)	Each

615(5B)	Delineator, Flexible (Type B)	Each

51132-120210

SECTION 616

THAW PIPE AND THAW WIRES

Standard Modifications

616-2.01 THAW PIPE.  Second sentence delete:

“and Fittings”

Add the following sentence:  Fittings ASTM A234 galvanized according to AASHTO M 111.

E14-063004

Special Provisions

616-5.01 BASIS OF PAYMENT.

Thaw pipe will not be paid for directly, but will be subsidiary to pipe items.

51132-080910

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Topsoil and seed new or disturbed slopes and other areas as directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

CR52-012707

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes.  Cover all slopes to be seeded with topsoil according to Section 620, unless otherwise specified.  Complete slope preparation as soon as topsoil is placed on the slopes.

51132-081110

Standard Modification

CONSTRUCTION REQUIREMENTS

618-3.01 SOIL PREPARATION.  Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rakes;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS.  Add the following:  Seed disturbed areas that require seeding within 14 days of the permanent cessation of ground disturbing activities in that area.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

618-3.03 APPLICATION.  Delete the first three sentences and replace with:  Apply seed mix, fertilizer, and mulch (if required) at the rate specified in the Special Provisions.  If no seed mix, seed mix application rate, or fertilizer rate are specified in the special provisions, use the recommendations of the Alaska Department of Natural Resources (ADNR) and the Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated on the plans as “no seeding.”

Water and fertilizer required for application are subsidiary to the Seeding bid item.

E42-012707

Special Provisions

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch, and fertilizer as follows.  Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed, Type A | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
| Seed, Type B | Tufted Hairgrass (Nortran) Red Fescue (Arctared) American Sloughgrass (Egan) | 0.05 lbs. 0.20 lbs. 0.20 lbs. Total = 0.45 lbs |
| Soil Stabilizer |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

51132-081110

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

R52-012707

Standard Modification

Delete Subsection 618-3.04 in its entirety, and add the following new subsections:

618-3.04 MAINTENANCE AND WATERING.  Protect seeded areas against traffic by approved warning signs or barricades. Repair surfaces gullied or otherwise damaged following seeding.  Maintain seeded areas in a satisfactory condition until final acceptance of work.

E42-012707

Special Provisions

Water and maintain seeded areas.  Water applied by this subsection is a paid Contract item, unless otherwise specified.  If, in the opinion of the Engineer, too much water is being applied, reduce amount of water as directed.

51132-081110

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding.  Bare patches of soil more than 10 square feet in area must be reseeded.  Erosion gullies over 4 inches deep must be filled and reseeded.  Fill the entire erosion gully to surrounding grade, including the portions less than 4 inches deep.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for retracking, reseeding, refertilizing, and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE.  During final inspection, the Engineer will perform a visual inspection of seeding to determine final stabilization.  During the visual inspection, each station and each side of the road will be considered a separate area.  The Engineer will accept seeding that has become a vegetative mat with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-3.06 PERIOD OF ESTABLISHMENT.  Establishment periods extend for one complete growing season following acceptable seeding.  Employ all possible means to preserve/maintain the new vegetative mat in a healthy and vigorous condition to ensure successful establishment.  Reseed areas that do not meet the specifications.  Watering and reseeding after the final inspection are subsidiary.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with subsection 105-1.16.

E42-012707

Special Provisions

618-4.01 METHOD OF MEASUREMENT.

Delete the paragraph beginning: “Seeding by the Pound” and substitute the following:

Seeding by the Pound.

Seeding, Type A: By the weight of dry seed acceptably seeded and maintained.

Seeding, Type B: Shall not be measured for payment.

Add the following:  Water used for watering and maintaining areas of Seeding, Type B shall not be measured for payment.

618-5.01 BASIS OF PAYMENT.  Delete paragraphs beginning: “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Payment is for established vegetative mat.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Seeding, Type A by the Pound.  Payment is for established vegetative mat in the areas seeded with Seeding, Type A.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Seeding, Type B.  Establishing a vegetative mat in the areas seeded with Seeding, Type B shall be Subsidiary to Pay Item 619(20) Roadbed Reclamation.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Add new pay description:

Water for Seeding. Water applied for growth of vegetative mat for areas seeded with Seeding, Type A, including water for maintenance. Water for hydraulic seeding, fertilizing, or mulching are subsidiary.  Water for these areas after project completion is subsidiary.

Add the following:

Water used for growth of vegetative mat for areas seeded with Seeding, Type B, including maintenance, water for hydraulic seeding, fertilizing, or mulching are subsidiary to 619(20) Roadbed Reclamation. Water for these areas after project completion is subsidiary.

Partial payments shall be made at 40% upon seeding, 30% at the end of the first growing season in which seeding is done (first season’s maintenance) and 30% upon final acceptance.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

618(2A) 	Seeding, Type A 	Pound

51132-081210

SECTION 619

SOIL STABILIZATION

Special Provisions

619-1.01 DESCRIPTION.  Add the following:

Roadbed Reclamation work includes excavation of existing Trunk Road, placing wetland soil, seeding, and other associated items. This work also includes supplying and installing living Wetland Mats, stream restoration, and installing safety fence.  The purpose of this work is to expedite the revegetation of restored wetland areas as required under the Corps of Engineers Permit for approximately 3200 feet of the existing Trunk Road alignment. Roadbed Reclamation work shall not begin until 2014.

51132-082410

619-2.01 MATERIALS.  Replace matting requirement with the following:

Matting	Subsection 727-2.02 Item 4.

CR6191-070609

Add the following:

Seeding, Type B	Section 618

Wetland Soil	Section 620

Plastic Safety Fence	Subsection 643-2.01

Fertilizer	Section 725

Wetland Mats. Provide Wetland mats for installation in the stream restoration area. The Wetland Mats shall be a minimum of 3 ft x 3 ft and a minimum of 2 ft in depth. Wetland Mats shall be of like vegetation and character of the wetlands adjacent to the roadbed reclamation area. A source for Wetland Mats includes the Plant Materials Center in Palmer. Submit to the Engineer documentation and samples of the mats for approval, prior to installation. Insure that the mats are protected during transport and that they do not dry out.  If Wetland Mats must be stored on site prior to installation, the storage area shall be shaded and mats kept moist throughout the root zone.  Installation shall occur within 48 hours of harvesting.

619-3.01 SURFACE PREPARATION.  Add the following:

Submit a roadbed reclamation plan for approval by the Engineer. The plan shall include details for staging, scheduling, watering, and other associated items required to perform the work.

Roadbed Reclamation includes all excavation necessary to remove the existing embankment to 1 foot below the adjacent natural topography, in accordance with Section 203, as shown in the Plans.

619-3.02 APPLICATION.  Add the following:

Place Wetland Soil and Seeding, Type B in accordance with Sections 620 and 618, as shown in the Plans.

Wetland Mats.

- Layout.  Stake all areas to be planted with Wetland Mats as shown on the Plans prior to installation.  Notify the Engineer of the delineated areas 3 working days prior to installation, and installation shall commence only after approval by the Engineer.

- Installation. The Wetland Mats shall be installed between May 15 and August 1. Commencement of work assumes that the Engineer accepts the conditions of the grades of areas in question.  Before installing the Wetland Mats, the Contractor must insure that the soil surface is moist. Wetland Mats shall be placed in position insuring complete contact of root mass to the soil surface. Tamp into place. Staple or stake mats into place as directed.  Water Wetland Mats within one hour of final placement. Continue to keep mats moist until final acceptance of the project.

- Fertilization.  Apply a slow-release granular fertilizer, 8-32-16, at an application rate of 4.1 lbs per MSF between May 1 and June 1 of the growing season following installation.

619-3.03 MAINTENANCE.  Add  the following:

Upon completion of placing wetland soil and seeding in the roadbed reclamation area, place Plastic Safety Fence at the beginning and end of the area across the full width of improvements to deter pedestrian and vehicular traffic from entering the area.   Maintain Wetland Mats and seeded areas in a satisfactory condition until final acceptance of work.  Repair surfaces gullied or otherwise damaged.

Water and maintain Wetland Mats and seeded areas.  Water shall be applied using a temporary irrigation system, or other method approved by the Engineer. Water applied by this subsection is subsidiary, including labor, materials, and equipment.  If, in the opinion of the Engineer, not enough or too much water is being applied, adjust the amount of water as directed, at no additional cost to the Department.

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding.  Bare patches of soil more than 10 square feet in area must be reseeded.

Contact ADNR for advice or corrective measures, when Wetland Mats or seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for replacing Wetland Mats, and reseeding, refertilizing, and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

Add the following subsections:

619-3.04 ACCEPTANCE.  During final inspection, the Engineer will perform a visual inspection of Wetland Mats and seeded areas to determine final stabilization.  The Engineer will accept Wetland Mats and seeding that has become a living vegetative mat with 70% cover density in the inspection area.

Reseed areas and replace Wetland Mats that are not acceptable to the Engineer.

619-3.05 PERIOD OF ESTABLISHMENT.  Establishment periods for the Wetland Mats and seeded areas extend till the end of the growing season concurrent with planting, not withstanding the requirement for fertilization per subsection 619-3.02.3.  Employ all possible means to preserve/maintain the Wetland Mats and seeded areas in a healthy and vigorous condition to ensure successful establishment.  Repair damaged areas and replace dead vegetation as necessary and directed by the Engineer during the Period of Establishment. Watering, repairing, and replacing during the Period of Establishment are subsidiary.

619-5.01 BASIS OF PAYMENT.  Add the following:

Payment for Roadbed Reclamation is full compensation for stream restoration, furnishing, installing, watering and maintaining of wetland soil, Wetland Mats, and Seeding, Type B as shown on the Plans. Excavation, fertilization, and staking, and furnishing and installing Plastic Safety Fence as detailed in this Section are subsidiary to Item 619 (20). Removal of pavement and removal of culvert pipe shall be paid under Section 202.

Pay Item No.	Pay Item	Pay Unit

619 (20)	Roadbed Reclamation	Lump Sum

51132-082410

Replace Section 620 with the following:

SECTION 620

TOPSOIL

Special Provisions

620-1.01 DESCRIPTION. Furnish and spread topsoil and wetland soil where shown on the Plans.

620-2.01 MATERIALS. Use materials that conform to the following:

Topsoil	Subsection 726-2.01

Wetland Soil	Subsection 726-2.02

620-3.01 PLACING. Spread the topsoil and wetland soil evenly on the designated areas to the depth (after settlement) shown on the Plans. Do not place when the ground or topsoil or wetland soil is frozen, excessively wet, or in a condition detrimental to the work. Keep the roadway surfaces clean of topsoil and wetland soil during hauling and spreading operations.

620·3.02 MAINTENANCE AND REPAIR.  Maintain the areas covered by topsoil and wetland soil until subsequent seeding or landscaping is accomplished. Complete any repairs or topsoil or wetland soil replacement, including damage or loss resulting from winter shutdown, without extra compensation.

620-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

Wetland soil shall not be measured for payment.

620-5.01 BASIS OF PAYMENT.  Stockpiling and rehandling of topsoil and wetland soil during the stripping operations or during placement are subsidiary.

Topsoil and wetland soil repair, maintenance, and replacement are subsidiary.

Furnishing and spreading wetland soil shall be Subsidiary to Pay Item 619(20) Roadbed Reclamation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

620 (1)	Topsoil	Square Yard

51132-080910

SECTION 621

PLANTING TREES AND SHRUBS

Special Provisions

621-1.01 DESCRIPTION.  Delete this subsection and substitute the following:

This work shall consist of furnishing, planting and maintaining plants as shown in the Plans, including construction of planting pits/beds in the roundabout central median.  Seedlings shall consist of plant species shown in the Plans and shall be at least the height above the ground shown in the plant schedule at time of planting. Furnish and install shredded bark mulch and weed barrier geotextile as shown in the Plans.

621-2.01 PLANT STOCK.  Add the following after the second paragraph:

Plants are not to be bare root.

Under Item 1. Nursery Stock, delete subparagraph b. and add the following:

b.	Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound. Root mass shall not contain grasses, clovers, or noxious weeds.

621-2.02 FERTILIZER.  Delete this subsection and substitute the following:

Use a regular release, 8-32-16 (nitrogen-phosphoric acid-potassium) fertilizer in granular form.  The fertilizer shall be mixed with soil at the manufacturer’s recommended application rate.

Replace, 621-2.04 Mulch, with the following:

621-2.04 SHREDDED BARK MULCH.  Shredded bark mulch shall consist of Spruce, Douglas Fir, Pine, or Hemlock bark shredded, with a maximum length of 2 inches and no more than 30% of the mix with particles less than 1/4 inch in size.  The shredded mulch shall not contain resin, tannin, non-organic or foreign elements in quantities that could inhibit plant growth.  The mulch shall have the characteristics to be spread evenly so as to form a uniform consistent mat that inhibits weed growth and will not blow or wash away.  The shredded bark mulch shall be aged at least one year and be a deep, dark, brown color.  Chipped wood and sawdust shall be limited to no more than 30% of mix and shall be aged for no less than one year.

621-2.05 BACKFILL MIX.  Delete this subsection and substitute the following:

Topsoil used for backfill in planting beds shall consist of a natural friable surface soil without admixtures of undesirable refuse or foreign materials.  It shall be free from roots, hard clay, noxious weeds, tall grasses, brush, sticks, stubble, or other litter, and shall be free draining and non-toxic.  Local red loam or imported peat mix having nutritional and gradation requirements may be used.  Topsoil backfill shall have 10-15 percent organic matter as determined by loss-on-ignition of oven dried samples according to ASTM 203, and shall meet the following:

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 3/4 Inch | 100 |
| No. 4 | 95 – 100 |
| No. 16 | 30 – 55 |
| No. 200 | 25 - 55 |

621-2.08 WEED BARRIER GEOTEXTILE. Add the following subsection: All planting beds, as shown on the Plans, shall receive a weed barrier geotextile beneath the mulch.  Seams shall be overlapped 12 inches and cut for plants.  Submit a 12 inch x 12 inch sample to the Engineer for approval before installation.

Weed Barrier Geotextile	Section 729

621-3.03 PLANTING.  Delete Item 1. Plant Season, and substitute the following:

1.	Plant Season.

a.	Locally Grown:  When locally grown plants are furnished for the project, plant them between June 1 and September 15.

b.	Imported:  Handle plants shipped in from out-of-state according to the nursery recommendations.  Place plants imported from out-of-state between June 1 and August 15.

Delete paragraph c. under Item 2. Excavation and substitute the following:

c.	Construct planting pits as shown on the Plans.

Add the following to item 5. Placing Plants:

d.	Place plants as shown on the Plans and as directed by the Engineer.

Add the following to Item 6.  Backfilling:

Backfill perennials with topsoil mixed with fertilizer at the manufacturer’s recommended application rate.

Replace Item 8. Staking and Guying, with the following:

8.	Staking and Guying.  As shown on the Plans.

Add the following:

9.	Fertilizing:  Newly planted trees and shrubs shall not be fertilized during the season they are planted.  Perennials shall be fertilized during the season they are planted.  Mix the fertilizer with soil as recommended by the manufacturer.

621-3.04 PERIOD OF ESTABLISHMENT.  Add the following:

The Period of Establishment for plantings shall extend from May 1 to September 30.

Provide fertilizer to trees and shrubs by driving a 1 ½ ounce fertilizer spike of the chemical proportions specified into the ground at the drip line of each plant.  For perennials, provide a reapplication of fertilizer of the same chemical proportions as the initial application.

Apply the fertilizer between June 15 and June 30 of the growing season following planting.

51132-120110

Standard Modifications

Add the following second paragraph:

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance according to Subsection 105-1.16.

E43-012707

621-3.06 PLANT REPLACEMENTS.  Delete this subsection and substitute the following:

In the spring of the year following the planting year and before June 30, the Engineer and the Contractor’s representative shall inventory plants planted on the project to determine the number of dead or unhealthy plants, or plants with rootballs infested with grasses, clovers, or noxious weeds.

For each species, if the number of dead or unhealthy plants is lower than 25 percent of the quantities originally planted, then no plant replacements shall be required.

For each species, if the number of dead or unhealthy plants is higher than 25 percent of the quantities originally planted, replace a sufficient number of plants to increase the number of healthy plants to 75 percent of the quantities originally planted.

All plants with rootballs infested with grasses, clovers, or noxious weeds shall be replaced.

Provide healthy replacement plants of the same species and size as the original plantings. Perform replacement planting between July 1 and July 15, according to the original planting procedures.  The Engineer will select the dead, unhealthy, or infested plants to replace.

Plants askew (tilted, angled, sloped, skewed, shifted in plan, etc.) shall be repositioned, placed upright and to the proper grade.  Remove and dispose of dead, unhealthy, or infested plants.

621-3.07 MAINTENANCE.  Add the following:

Deep water plants immediately after planting.  Deep watering shall provide water penetration throughout the entire root zone to the total depth of the planting pits with a minimum of runoff.  Rain will not be considered a substitute for deep watering unless permitted by the Engineer.

Deep water the plants according to the following maintenance schedule:

1.	Deep water plants at least twice a week during the first 45 days after planting.  If these 45 days extend past September 30, cease the twice weekly deep watering after that date and resume on May 1 of the following calendar year.  If the 45 days does not extend past September 30, additional deep watering in the planting year after the 45 days expire shall be as follows:

a.	Once a week in June and July.

b.	Once between August 10 and August 20.

c.	Once during the last week in September.

2.	Deep water plants during the Period of Establishment as follows:

a.	Once a week during May, June and July.

b.	Once between August 10 and August 20.

c.	Once during the last week in September.

3.	Warm or dry conditions.  The Engineer may direct the Contractor to deep water the plants past September 30, or provide supplemental watering during the life of the project during warm or dry periods.

4.	Over-wintering desiccation.  The Engineer may direct the Contractor to deep water the trees and shrubs before freeze-up to minimize over-wintering desiccation.

Watering equipment shall be equipped with, or followed by a vehicle equipped with a Type B advance warning arrow panel using caution mode according to Part VI of the Alaska Traffic Manual

621-4.01 METHOD OF MEASUREMENT.  Delete this subsection in its entirety and substitute the following:

The quantity to be paid for shall be the actual number of plants furnished, planted and maintained according to the Plans, Specifications, and as accepted by the Engineer.

621-5.01 BASIS OF PAYMENT.  Add the following:

Use of a Type B Advance Warning arrow panel for watering under this section will not be paid for directly, but will be subsidiary to Item 621(12) Landscaping.

Fertilization as indicated in Subsection 621-3.04, Period of Establishment will not be paid for directly, but will be subsidiary to Item 621(12) Landscaping.

Payment is full compensation for furnishing, installing, and maintaining of trees, shrubs, and perennial plants as shown on the Plans.  Excavation of planting beds, placement and supply of weed barrier geotextile, backfill mix, shredded bark mulch, fertilization, tree wrap, staking, guying, and disposal of unsuitable and surplus material are subsidiary to Item 621(12) Landscaping.

Selected Material, Type D is subsidiary to Pay Item 621(12).

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

621(12)	Landscaping	Lump Sum

51132-120110

Special Provision

Delete Section 622 and substitute the following:

SECTION 622

PARK FACILITIES

622-1.01 DESCRIPTION.  This work shall consist of furnishing materials, equipment, and labor to construct and install an Interpretive Sign, Type B as shown in the Plans near the existing Park N Ride located near the intersection of Trunk Road and the Parks Highway as directed by the Engineer.

622-1.02 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

MATERIALS

622-2.01 GENERAL.  All materials shall be as shown on the Plans and as specified herein, new.

622-2.02 BACKFILL.  Selected Material, Type A conforming to Subsection 703-2.07.

622-2.03 CONCRETE.  Conform to the requirements of the American Concrete Association (ACI) and Section 501.  Concrete, Class W in accordance with Section 501.

622-2.04 STRUCTURAL STEEL.  Conform to the requirements of the American Institute of Steel Construction (AISC) and Section 504.  Structural steel, ASTM A36 Standard Specification for Carbon Structural Steel.

622-2.05 ALUMINUM.  Interpretive Sign back plate:  Aluminum conforming to the requirements of the American National Standards Institute, ANSI 6061 T-6.

622-2.06 GALVANIZING.  Conform to ASTM A123, Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products, ASTM A153, Standard Specification for Zinc Coating [Hot-Dip] on Iron and Steel Hardware and ASTM A780, Standard Practice for Repair of Damaged and Uncoated Areas of Hot-Dip Galvanized Coatings.

622-2.07 LUMBER.  Lumber/timber (lumber) shall conform to the requirements of the Western Woods Product Association (WWPA), the National Design Specification (NDS) for Wood and as noted below:

All wood materials shall be pressure preservative treated per Subsection 622-2.08.

Posts (5x5 or greater):  Species Hem-Fir, Grade No. 1 or better.

Structural Framing, (all other wood framing materials):  Hem-Fir Species, Grade No. 2 or Better.

Kiln Dry materials. Maximum moisture content 19%.

1.	Dimensional.  Dimensional lumber and timbers are shown on the Plans in nominal dimensions, i.e.; 6x6 (5 1/2" x 5 1/2") and finished S4S (surfaced four sides).

622-2.08 TREATED LUMBER.  Preservative treatments to conform to the Western Wood Preservers Institute (WWPI), the American Wood Protection Association (AWPA), the manufacturer’s recommendations and as follows:

1.	Sign Post(s):  Color – Uniformly brown.  Color to be approved by the Engineer.

a.	Prior to Fabrications:  Pressure treat with:

Oilborne preservative, Copper Naphthenate, minimum retention .06 lb/cu ft or,

Waterborne preservative, Copper Azole CA-B, minimum retention .21 lb/cu ft.

Not Permitted:  Ammonia Copper Quat.

b.	Field Exposed Untreated Material:  Water or oilborne Copper Naphthenate – specified in AWPA M4, preservative concentration no less than 2% copper metal.  Coordinate use with the specifications and instructions of the pressure applied treatment manufacturer.

622-2.09 FASTENERS.  Fasteners and framing anchors in accordance with the National Design Specification (NDS) for Wood and the American National Standards Institute (ANSI) and as noted below:

1.	Interpretive Panel to Aluminum Back Panel:  Stainless steel screws as shown on the Plans.

2.	Bolts, Lag Screws:  ASTM A307.

3.	Washers: ANSI Type B, regular or wide series, plain.

Except where noted otherwise, fasteners (nails, screws, lag screws, bolts, washers, nuts etc.) and framing anchors, including post bases, proprietary or shop fabricated shall be hot dipped galvanized per Subsection 622-2.06.

622-2.10 PAINT.  Paint/Preservatives (coatings):

As follows or approved equal by the Engineer:

1.	Interpretive Sign Panel:  By others.

2.	Interpretive Sign Lumber:  Type and color as noted in Subsection 622-2.08.

3.	End Cut Preservative for Treated Wood.  Coordinate with the pressure preservative manufacturer.  See Subsection 622-2.08, match color.

4.	Concrete Sealer:  Clear acrylic copolymer conforming to ASTM C 309 Standard Specification for Liquid Membrane-Forming Compounds for Curing Concrete, for Type 1 Compounds.

622-2.11 INTERPRETIVE PANEL.  Interpretive panel by others:

Interpretive panel:  Plywood panel, 1/2" x 2’-6 1/2" x 3’-0 1/2"

The Interpretive Panel will be provided by the Engineer.

622-2.12 INTERPRETIVE SIGN.  Provide one pin-in-head torx machine bolt driver per sign. Embed column bases in wet concrete for subsequent connection of wood post to concrete foundation.  Size column base to fit the post dimensions. Post base may be proprietary or custom fabricated.  Custom fabricate post base similar to the proprietary base manufactured by the Simpson Company, CB66R.  Stirrups shall be provided with holes for two bolts with washers.

| Post Size |  | Base Plate Gage & Dimension |  | Stirrup Material |  | Post Bolts |  | Allowable Uplift Load |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 6" X 6" |  | 7 ga & 6" X 6" |  | 7 ga x 3" strap |  | 2 each 5/8" |  | 4,200 pounds |

CONSTRUCTION REQUIREMENTS

622-3.01 GENERAL.  Install the interpretive sign adjacent to the existing interpretive sign installations at the Park N Ride located at the south end of Trunk Road near the Parks Highway as directed by the Engineer, or where directed by the Engineer.

622-3.02 EXCAVATION AND BACKFILL.  Conform to the requirements of Section 204 and the details on the Plans.

622-3.03 CONCRETE.  Conform to the requirements of the American Concrete Institute (ACI), the requirements of Section 501 and the details on the Plans.

622-3.04 STRUCTURAL STEEL.  Fabrication shall be in accordance with the requirements of the American Institute of Steel Construction (AISC).  Welding shall be in accordance with the requirements of the American Welding Society (AWS) D1.1.

622-3.05 WOOD.  Store lumber on site above the ground, dry, under ventilated cover, and protected from environmental and physical damage.  Do not use damaged lumber.

Framing shall be aligned true, plumb and level.  All shipping, storage, weathering and erection marks on fabricated lumber shall be removed.

Bolt and lag screw holes shall not be oversized/reamed and shall be straight and tight to the fastener.  Holes for bolts shall be bored with a bit of the same diameter as that of the bolt.  Holes for lag screws shall be bored with a bit not larger than the body of the screw at the root of the thread.  Place plain washers in contact with all bolt heads, lag screw heads and nuts.

At the post base stirrups, place washers as follows:

1.	Plain washer between the bolt head and the outside of the stirrup.

2.	Plain washer between the inside of the stirrup and the post.

3.	Plain washer between the inside of the opposing stirrup and the post.

4.	Plain washer to the outside of the opposing stirrup with a lock washer between the plain washer and the nut.

Provide counter sink equal to and not greater than the thickness and diameter of the plain washer.  Contractor has the option to press the washer face into the wood resulting in the washer surface flush with the surface of the wood.  Tighten bolts engaging the lock washer.  Tighten the stirrup bolts: (1) at the time the sign is erected, (2) at the end of the project and, (3) as directed by the Engineer.

622-3.06 PAINT.  (Coatings)

Manufacturer Applied Coatings:  Manufacturer applied coatings, wood preservative treatment, hot-dip galvanizing, and concrete sealer shall be applied in accordance with the referenced national specifications and governing industry organizations listed in “MATERIALS”, Subsections 622-2.06, 08, 09, 10 of this Special Provision.

Apply Coating as follows:

1.	Steel:  Hot Dip Galvanize all steel.

2.	Fasteners:  Hot Dip Galvanize all fasteners, except use stainless steel fasteners attaching Interpretive Panel to the Back Plate.

3.	Wood:  Pressure Preservative Treat all lumber.

4.	Plywood Interpretive Panel:  By Other’s including coatings.

5.	Aluminum Back Panel:  No coating.

Field Applied Coatings:  Field applied coatings shall be delivered in sealed containers with labels legible and intact.  Coating material that has been frozen or is out of date shall not be used.  Surfaces to be painted shall be even, smooth, sound, clean, dry and free from defects affecting proper application.  Apply coatings as recommended by the manufacturer and as noted in this Special Provision.  Cover surfaces completely to provide uniform color and appearance.  Apply coating material evenly without runs, sags, or other defects.  Remove coatings where spilled or spattered onto other materials.  Do not permit coating to drip into surrounding soil.  The temperature of coating materials, the materials being coated and the ambient air temperature shall be in the temperature range specified by the manufacturer during the application and through the required cure time.

Apply coatings as follows:

1.	Concrete Sealer:  Seal all exposed surfaces.  Apply sealer per industry standards and per manufacturer’s instructions.

Apply repair for damaged coatings as follows:

1.	Hot Dip Galvanizing, Fabrications:  In accordance with ASTM A780.

2.	Hot Dip Galvanized Fasteners:  Replace.

3.	Exposed Wood:  Exposed wood surfaces resulting from field fabrication (cutting, scraping, drilling or other) and/or handling abuse shall be field treated by brushing, dipping or soaking as recommended by manufacturer.

622-4.01 METHOD OF MEASUREMENT.   The number of units installed and accepted.

Excavation and backfill required for item(s) paid for under this section will be subsidiary to the item unit.

622-5.01 BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price per unit type, complete-in-place, as listed below.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 622(6B) | Interpretive Sign, Type B | Each |

51132-082311

Special Provisions

Replace Section 639 with the following:

SECTION 639

DRIVEWAYS

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

CR58-050902

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be measured and paid for under their respective pay items.

51132-090810

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approach	Each

CR58-050902

- Special Provisions

- Replace Section 641 with the following:

- SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.  Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.  These definitions apply only to Section 641.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

Alaska Department of Environmental Conservation (ADEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

Alaska Pollutant Discharge Elimination System (APDES). A system administered by ADEC that issues and tracks permits for storm water discharges.

Best Management Practices (BMPs).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

Clean Water Act (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

Consent Decree. The decree entered by the United States District Court for the District of Alaska on September 21, 2010, regarding compliance with the CWA and implementation of the CGP, to which the United States and the Department are parties.

Construction Activity. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and construction materials or equipment storage or maintenance (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and other industrial storm water directly related to the construction process (e.g. concrete or asphalt batch plants).

Construction General Permit (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by ADEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

Electronic Notice of Intent (eNOI). The electronic Notice of Intent submitted to ADEC, to obtain coverage under the CGP.

Electronic Notice of Termination (eNOT). The electronic Notice of Termination submitted to ADEC, to end coverage under the CGP.

Environmental Protection Agency (EPA). A federal agency charged to protect human health and the environment.

Erosion and Sediment Control Plan (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

Final Stabilization. Is defined in this section as it is defined in the CGP.

Hazardous Material Control Plan (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

Inspection.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s stormwater inspector.

Multi-Sector General Permit (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

Operator(s). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of stormwater associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

Project Zone. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Department by the Contract and are directly related to the Contract.

Support Activities including material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

Records. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the Consent Decree, the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

Storm Water Discharges From Municipal Separate Storm Sewer Systems (MS4s).  A conveyance or system of conveyances including roads with drainage systems, municipal streets, catch basins, curbs, gutters, ditches, man-made channels, or storm drains that discharges into waters of the United States and is owned or operated by a public agency.

Spill Prevention, Control, and Countermeasure Plan (SPCC Plan). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

Spill Response Field Representative. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

Storm Water Pollution Prevention Plan Two (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related Support Activities outside the Project Zone.

Subcontractor Spill Response Coordinator. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

Subcontractor SWPPP Coordinator. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

Superintendent. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

Support Activities. See ADEC CGP definition. Further defined as construction activities in which the Department is not an operator and the activity is outside the Project Zone.

SWPPP Amendment. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager. The Contractor’s qualified representative who conducts Inspections and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP Preparer. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

Utility Spill Response Coordinator. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

Utility SWPPP Coordinator. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.  For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP) use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14 day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP.

2.	Hazardous Material Control Plan.  Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. The Contractor cannot use the SWPPP for  Support Activities outside the Project Zone where the Department is not an operator.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to ADEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and ADEC’s acknowledgement letter to the Engineer when the eNOI is submitted to ADEC.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to ADEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and ADEC’s acknowledgment letter, for inclusion in the SWPPP.

5.	Ending CGP Coverage. Submit an eNOT to ADEC, and submit both a copy of the signed eNOT and ADEC’s acknowledgement letter to the Department, within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met.

6.	ADEC SWPPP Review.  When CGP, Part 2.1.3 - requires ADEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to ADEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4 requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information, as required, to local government, with the required fee using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	Before ending permit coverage file a project ending notification with local government and allow them to inspect the work.

8.	Modifying Contractor’s eNOI.  When required by The CGP Part 2.7, modify your eNOI to update or correct the information. Reasons for modification include change to the start or end dates, small changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or changed location of SWPPP Records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed, the original eNOI indicates disturbed area less than five acres and the project will disturb more than five acres, or a project over five disturbed acres grows by more than 50%.

641-1.04 PERSONNEL QUALIFICATIONS.  The SWPPP Preparer must meet at least one of the following qualifications:

a.	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

b.	Current certification as AK-CESCL, and at least two years experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

c.	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL

For Projects disturbing more than 20 acres, the SWPPP Preparer must also have completed a Department approved SWPPP Preparation course. Approved courses will be posted on the Department’s D&ES, Environmental website.

The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3

The SWPPP Manager (identified in the CGP as the Storm Water Lead) and the Storm Water Inspector must have current certification as AK-CESCL, and be knowledgeable in the requirements of that position as defined in the CGP, Appendix C, Qualified Person. The SWPPP Manager has authority to work in each position concurrently.

The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principals and practices of treatment systems in general, and the operation of the ATS in particular. Minimum experience to be 6 months field experience or completion of an ATS manufacturer’s training course.

The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control;

b.	CISEC, Certified Inspector in Sediment and Erosion Control; or

c.	CESCL, Washington Department of Ecology Certified Erosion and Sediment Control Lead (Through Nov. 30, 2011 only. Will not be accepted as an equivalent substitution after Nov. 30, 2011).

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12.2. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Engineer will provide the Department’s delegation Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify that they have read and will abide by the CGP and the conditions of the project SWPPP.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone for Support Activities. The Contractor has sole responsibility for compliance with ADEC and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

3.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas or Support Activities outside the Project Zone; and

b.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY RELOCATION COVERAGE.  A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.  Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

a.	Opportunities to phase construction activities;

b.	Appropriate BMPs and their sequencing; and

c.	Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.  Use the Department’s ESCP and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP framework according to the ADEC SWPPP template with additional information as required. Include information required by the CGP, Part 5, and this specification.

When using the SWPPP template:

	In Section 3 (Good Housekeeping), add a subsection to describe dedicated asphalt plants and/or dedicated concrete plants, give their locations and identify the BMPs that will be used to minimize pollutants from them.  If there are no dedicated asphalt or concrete plants, then state that in the SWPPP.

·	Include the following appendices:

·	Appendix A	–	Site Maps and Drawings

·	Appendix B	–	BMP Details

·	Appendix C	–	Project Schedule

·	Appendix D	–	Supporting Documentation: TMDLs, Endangered Species, & Historical Properties

·	Appendix E	–	Project Permits

·	Appendix F	–	Delegation of Authority

·	Appendix G	–	Subcontractor Certifications/Agreements

·	Appendix H	–	Construction General Permit

·	Appendix I	–	Notice of Intent and Delivery Confirmation, Letter from ADEC, Notice of Termination (Include both Department’s and Contractor’s)

·	Appendix J	–	Monitoring Plan (If Applicable) and Reports

·	Appendix K	–	SWPPP Preparer’s Site Visit

·	Appendix L	–	Hazardous Material Control Plan (HMCP)

·	Appendix M	–	Personnel Qualifications and Training Certificates for:

○	Superintendent

○	SWPPP Preparer

○	SWPPP Manager/Storm Water Lead/Inspector

○	Contractor’s ATS Operator

○	Department’s Project Engineer and Inspector(s)

○	Qualified personnel must be described in a list with names and dates in positions

·	Appendix N	–	Training Log

·	Appendix O	–	Corrective Action Log

·	Appendix P	–	Grading and Stabilization Activities Log

·	Appendix Q	–	Rain Record

·	Appendix R	–	Inspection Reports

·	Appendix V	–	Monitoring Reports

·	Appendix W	–	Antidegradation Analysis

·	Appendix X	–	Dewatering Permit

Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

	SWPPP Certification for DOT&PF (25D-109)

	SWPPP Delayed Action Item Report (25D-113)

Use the following Department forms for recording information in the SWPPP:

	SWPPP Amendment Log (25D-114)

	SWPPP Certification for Contractor (25D-111)

	SWPPP Construction Site Inspection Report (25D-100)

	SWPPP Corrective Action Log (25D-112)

	SWPPP Daily Record of Rainfall (25D-115)

	SWPPP Delegation of Signature Authority – Contractor (25D-108)

	SWPPP Grading and Stabilization Activities Log (25D-110)

	SWPPP Pre-Construction Site Visit (25D-106)

	SWPPP Project Staff Tracking (25D-127)

	SWPPP Subcontractor Certification (25D-105)

	SWPPP Training Log (25D-125)

SWPPP Forms are at:  http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Support Activities outside the Project Zone must have permit coverage, using separate SWPPP2s, and separate Contractor Inspections.

The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

a.	Over which each operator has operational control; and

b.	Where the Department and Contractor are co-operators.

For work outside the Project Zone the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

a.	Dedicated to the Project and where the Department is not an operator; and

b.	Not dedicated to the project, but used for the project.

Develop the SWPPP according to the requirements of the CGP and this specification, and account for the Contractor’s construction methods and phasing.

Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and all temporary and permanent stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words and drawings as appropriate. Provide a citation to the BMP Manual or publication used as a source for the BMP, including the title of the BMP Manual or publication, the author (individual or agency), and date of publication. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities.

Identify in the SWPPP whether Inspections are conducted:

a.	Areas where the mean annual precipitation is between 14 and 40 inches: once every seven (7) days;

b.	Areas where the mean annual precipitation is 40 inches or greater: once every seven (7) days, and twice every seven days during periods of relatively continuous precipitation or sequential storm events.

Linear Project Inspections, as per CGP 6.5, are prohibited unless permitted by the Project Engineer.

The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the Consent Decree, CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Include in the SWPPP, Records of the AK-CESCL cards or certificates for the Superintendent and SWPPP Manager/Storm Water Lead, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager; record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24 hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24 hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, Records of the AK-CESCL cards or certificates of storm water inspectors, and ATS operators. Record their beginning and ending dates.

The Department will provide Records of AK-CESCL cards or certificates for the Project Engineer and the Stormwater Inspectors, and names and dates they are acting in that position. Include the Department’s Records in the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, and under equipment during maintenance or repairs.

Use secondary containment under all stationary equipment (equipment that does not have a seat for driving) that contains petroleum products. Use secondary containment under pumps, compressors, and generators.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up of spills or contaminated surfaces must be initiated immediately and completed as soon as practicable.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.  Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

- Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

- Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP and the Consent Decree, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP and the Consent Decree.

The Superintendent may assign certain duties to the SWPPP Manager; those duties may include:

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

The SWPPP Manager has authority to work in the following positions named in the CGP, Appendix C, Qualified Person: Storm Water Lead (CGP position equivalent to SWPPP Manager), and Storm Water Inspector. The SWPPP Manager has authority to work in all the position of ATS Operator if they meet the knowledge and experience qualifications listed in 1.04..

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.  Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

·	Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

·	Use soil stabilization material as specified in Section 727.

·	Use silt fences as specified in Section 729.

·	Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

·	Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS. The Contractor must be familiar with the requirements of the CGP because Contractor’s employees will be conducting duties that relate to compliance with the CGP.

641-3.01 CONSTRUCTION REQUIREMENTS.  Comply with the SWPPP and CGP requirements.

- Before Construction Activity may Begin.

a.	Confirm the following:

1)	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP, and the SWPPP must be developed (or amended) with findings from the visit;

2)	The SWPPP must be approved by the Engineer;

3)	The Contractor must be authorized to begin by the Engineer;

4)	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the ADEC website; and

5)	The Department approved SWPPP must be submitted to ADEC and Local Government (when required).

b.	Post notices containing the following information:

1)	Copy of all eNOIs related to this project;

2)	Name and 24 hour phone number of SWPPP Manager; and

3)	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes, for instance if the location of the SWPPP or contact person changes during the winter.

c.	Install an outdoor rain gauge per manufacturer’s guidance, in a accessible location on the Project.

d.	Delineate the site for both land disturbing activities and areas that will be left undisturbed. Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

The CGP Part 4.10.2 allows winter construction of ice roads or the placement of sand or gravel on frozen tundra with no excavation or potential to pollute waters of the U.S., without submitting an eNOI. The Contractor is responsible for resulting erosion or sediment runoff during spring thaw and summer. The CGP Part 4.10.3 allows cutting of trees and brush while the ground is frozen, without disturbing the vegetative mat, prior to submitting an eNOI.

- During Construction.

Make copies of the applicable portions of the SWPPP available to subcontractors and utility companies before they begin soil disturbing activities. Inform subcontractors and utility companies of amendments that affect them in a timely manner. Ensure all subcontractors who engage in soil-disturbing activities understand and comply with the SWPPP and the CGP, and have signed a SWPPP Subcontractor Certification, Form 25D-105, before they conduct the activity. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Provide SWPPP information to utility companies. Coordinate with subcontractors and utility companies doing work in the Project Zone so that BMPs, including temporary and permanent stabilization, are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures. Document on the SWPPP Training Log. Form 25D-125, the dates and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Do not install concrete washout containment within 100 feet of wetlands and/or other water bodies.

Fuel in designated areas. Place absorbent pads or other suitable containment under fill ports while fueling, and under equipment during maintenance or repairs. Install secondary containment under all stationary equipment that contains petroleum products.

Comply with requirements of the HMCP and SPCC Plan, and all local, state and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

3.	Pollutant and Hazardous Materials Reporting Requirements.

If there has been an incident of non-compliance with the CGP that may endanger health or the environment, immediately report the incident to ADEC according to the CGP, Appendix A, Part 3.0. Notify the Engineer immediately and to the extent possible coordinate reports to ADEC with the Engineer. The report must include:

·	A description of the noncompliance and its causes;

·	The exact dates and times of noncompliance ;

·	If not yet corrected the anticipated time the project will be brought back into compliance; and

·	The corrective actions taken, or planned, to reduce, eliminate and prevent reoccurrence.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law. Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies. See CGP Part 4.8.

4.	Corrective Action and Maintenance of BMPs.

a.	Implement corrective action:

1)	If an incident of non-compliance with the SWPPP, or CGP is identified;

2)	If an Inspection identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

3)	If the Engineer determines the SWPPP or any part of the SWPPP is ineffective in preventing the erosion, sedimentation, or the discharge of pollutants;

4)	If a required BMP was never installed, was installed incorrectly, or not in accordance with the CGP Part 4.0;

5)	If any BMP is not operating as intended, or has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

6)	Before sediment or debris fills a BMP to the percentage of design capacity or available storage allowed by the CGP (or manufacturer’s specifications or SWPPP requirements, whichever is lower);

7)	Whenever there is a change in conditions, design, construction, operation, or maintenance that could result in erosion, sedimentation, or the discharge of pollutants;

8)	If a prohibited discharge as specified in CGP Part 4.6 is occurring or will occur; or

9)	If there are accumulations and tracking of sediment or other pollutants, in or near any storm water conveyance channels, on roadways or parking lots within and adjacent to the project zone, in the immediate vicinity of control measures, at discharge points or entry points into the storm sewer system, or in other areas within the project zone.

b.	Implement corrective actions so that all of the following time requirements are satisfied:

1)	Conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

2)	Corrective action is completed before the next storm event;

3)	Corrective action is completed in time to protect water quality; and

4)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action.

Train subcontractors to identify conditions that require corrective action.  Subcontractors are required to notify the Contractor within 24 hours of becoming aware of a condition(s) that requires corrective action.

5.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

a.	As soon as practicable;

b.	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

c.	As identified in the SWPPP.

Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

Temporary or Permanent Seeding.

When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community the hydro-seeder must be located at the project.

Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the Contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

Stream By Pass.

When installing a culvert or other drainage structure where stream bypass is not used, install temporary or permanent stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants.

Install temporary and permanent stabilization:

a.	At the culvert or drainage structure inlet and outlet; and

b.	In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install permanent stabilization:

a.	At the inlet and outlet of the culvert, drainage structure, or bridge;

b.	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

c.	Under the bridge.

6.	Ending CGP Coverage and BMP Maintenance.

The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

a.	Land disturbing activities have ceased;

b.	Final Stabilization has been achieved (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

c.	Temporary BMPs have been removed.

After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

a.	Send written notice to the Contractor with the date that the conditions were met;

b.	Submit an eNOT to ADEC; and

c.	Provide a copy of the eNOT and ADEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to ADEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to ADEC, and insert copies of the Department’s and the Contractor’s eNOTs with ADEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and ADEC’s acknowledgement letter to the Department within 30 days of receiving them.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments and appendices, to the Engineer when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.  The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP and the Consent Decree. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown, but this will require updating on-site posted notices. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or ADEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them. The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies.   See CGP Parts 5.10, 6.6 and 9.4.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.  Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Activities Log, and SWPPP Daily Record of Rainfall forms. For active projects update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP:

a.	Every seven (7) days in areas where the mean annual precipitation is between 15 and 40 inches,

b.	Areas where the mean annual precipitation is 40 inches or greater, once every seven (7) days, and twice every seven days during periods of relatively continuous precipitation or sequential storm events.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s stormwater inspector jointly, unless impracticable. For this paragraph, “impracticable” means when both inspectors must fly to a remote area in the winter or when one inspector is sick or unable to travel to the site due to weather.  When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Unless otherwise directed by the Engineer, insert a Complete-by-Date for each corrective action listed that is (1) a date that complies with the time requirements listed in Subsection 641-3.01.4, or (2) seven days from the date of the Inspection, whichever is sooner. Provide a copy of the completed, unsigned Inspection Report to the Engineer by noon of the day after inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an addendum that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the addendum.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

Inspection frequency during winter work or seasonal suspension of work may be reduced to at least one Inspection every 30 days if approved by the Engineer and the entire site is temporarily stabilized.

The Engineer may waive winter Inspection requirements 14 days after the freeze-up.  Inspections must resume inspections 21 days before thawing conditions are expected to result in a discharge, if all the following requirements are met:

a.	Frozen conditions are anticipated to continue for more than one month; and

b.	Soil disturbing or soil stabilizing activities have been suspended.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Seasonal Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to seasonal thaw. Seasonal thaw is the annual (first) recurrence of snow and ice melting after a prolonged period of freezing conditions.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log, Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction, or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Do not record removal of BMPs as amendments to the SWPPP. See Subsection 641-3.03.9 for documenting removal of BMPs.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of discovery.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP, or overdue maintenance (after a sediment trap exceeds 50% of design capacity) is a corrective action and must be documented on the Corrective Action Log. Do not record removal of BMPs on the Corrective Action Log.

After each Inspection Report has been signed and certified, update the corrective action log with the date of inspection and include all proposed corrective actions noted on the Inspection Report.

After the corrective action has been accomplished, note the action taken,  if a SWPPP amendment was needed, and date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

641-3.04 FAILURE TO PERFORM WORK.  The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, Consent Decree or SWPPP, that may endanger health or the environment. If the suspension is to protect workers, the public, or the environment from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions.

1.	If the Contractor fails to take the corrective action within the specified time, the Engineer may:

a.	Suspend the work until corrective action is completed;

b.	Withhold monies due the Contractor until corrective action is completed;

c.	Assess damages or equitable adjustments against the Contract Amount; and

d.	Employ others to perform the corrective action and deduct the cost from the Contract amount.

2.	Reasons for the Engineer to take action under this section include, but are not limited to, the Contractor’s failure to:

a.	Obtain appropriate permits before Construction Activities occur;

b.	Perform SWPPP Administration;

c.	Perform timely Inspections;

d.	Update the SWPPP;

e.	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms  to the Engineer;

f.	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

g.	Perform duties according to the requirements of this Section 641; or

h.	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work under this subsection.

641-4.01 METHOD OF MEASUREMENT.  Section 109.

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

The total value of this Contract will be adjusted as specified herein.  Withholding will be determined by the Department and assessed under Pay Item 641(6) SWPPP Price Adjustment, as follows:

TABLE 641-1 BMP VALUES

- RESERVED -

TABLE 641-2 EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

- RESERVED -

1.	Fines and Penalties:  A Price adjustment equal to any penalties and fines levied against the Department by local, state, or federal agencies for pollutant violations, including violations of the CWA and the CGP, except when due to Department negligence. An amount equal to the anticipated penalties and fines for the violation or violations, excluding any due to negligence by the Department, will be withheld until the actual cost of the penalties and fines is known.  Anticipated penalties and fines will be determined by the Engineer.  The Contractor is also responsible for the payment of penalties and fines levied against the Contractor.

2.	Failure to perform Inspections:  By each 24 hour period that a required SWPPP inspection is delayed or is not signed, certified, or completed in accordance with the schedule identified in the approved SWPPP a price adjustment of $750 will be assessed.

3.	Failure to perform Corrective Action.  By each 24 hour period following 24 hours after written notice by the Engineer, per occurrence, a price adjustment of $750 will be assessed where the Contractor:

·	fails to complete SWPPP administrative requirements as identified in the Contract or the CGP,

·	fails to initiate work required by the SWPPP, or

·	fails to initiate corrective action to respond to a deficiency noted during an inspection or by the Engineer.

The same deficiency remaining uncorrected will be considered an additional occurrence for each additional 24 hour period, without requiring additional written notice by the Engineer.

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP Manager (when not included as a separate Pay Item under 641(7)) SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Pay Item 641(1) Erosion, Sediment and Pollution Control Administration.

Item 641(2) Temporary Erosion, Sediment and Pollution Control. At the contingent sum prices specified for all labor, supervision, material, equipment, and incidentals to install, maintain, remove and dispose of approved temporary erosion, sedimentation, and pollution control BMPs required to implement the SWPPP and SPCC Plan.

Item 641(3) Temporary Erosion, Sediment and Pollution Control. At the Contract lump sum price for all labor, supervision, material, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs identified in the SWPPP and SPCC Plan.

Item 641(4) Temporary Erosion Sediment and Pollution Control Additives. At the contingent sum prices specified in the Directive to authorize the work, for all labor, supervision, materials, equipment, and incidentals for extra, additional, or unanticipated work, to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(5) Temporary Erosion Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor.  All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(6) SWPPP Price Adjustment.  Withholding according to Section 641-3.04, equal to any penalties and fines levied against the Department by local, state, or federal agencies for pollutant violations, including violations of the CWA, CGP, and any other Permit, except when due to the Department’s sole negligence. The Contractor is also responsible for the payment of any and all penalties and fines levied against the Department or Contractor by entities (including agencies) other than the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641(7) SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641(7) appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be on-site during construction activity with duties and authority described in Subsection 641-2.04. When Item 641(7) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641(1).

Subsidiary Items.  Temporary erosion, sediment and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

a.	Dewatering;

b.	Shoring;

c.	Bailing;

d.	Permanent seeding;

e.	Installation and removal of temporary work pads;

f.	Temporary accesses;

g.	Temporary drainage pipes and structures;

h.	Diversion channels;

i.	Settling impoundment; and

j.	Filtration.

Permanent erosion, sediment and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment, and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion, Sediment, and Pollution Control	Contingent Sum

641(3)	Temporary Erosion, Sediment, and Pollution Control	Lump Sum

641(4)	Temporary Erosion, Sediment, and Pollution Control Additives	Contingent Sum

641(5)	Temporary Erosion, Sediment, and Pollution Control by Directive	Contingent Sum

641(6)	SWPPP Price Adjustment	Contingent Sum

641(7)	SWPPP Manager	Lump Sum

CR641-072211

Special Provisions

Replace Section 642 with the following:

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

642-1.01 DESCRIPTION. Perform surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the Plans and Specifications and industry standard engineering and survey practice.

Furnish and maintain facilities, equipment, and services specified in this section for Digital Terrain Modeling (DTM).  All furnished facilities and equipment remain your property when you complete the work.

642-1.02 DEFINITIONS.

1.	Break Line: A break line defines the horizontal location where TIN lines must break, and snap to the vertical location of the break line.

2.	Catch Point: In the cross section of a road, the point at which the fill or cut slope intersects the edge of the existing ground.

3.	CAD:  Computer-Aided Design.

4.	CORS:  Continuously Operating Reference Station.

5.	DTM: Digital Terrain Model. A computer generated 3D model representing the project terrain, and based on the association of features such as alignments, profiles, sections, grading lines, points, and surfaces.

6.	GLONASS: A radio-based satellite navigation system operated by Russia. GLONASS is an alternative and is complementary to the United States Global Positioning System.

7.	GNSS:  Global Navigation Satellite System.

8.	GPS: Global Positioning System; A radio-based satellite navigation system operated by the United States.

9.	Hinge Point: In the cross section of a road, the point at which any slope intersects another slope of different angle.

10.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown in the Plans.

11.	Neat-line: Defines the geometric limits of a material, as indicated by the typical section, profile, and alignment.

12.	NGS: National Geodetic Survey; United States Government Agency that provides information and products related to the definition and management of the NSRS.

13.	NSRS: The National Spatial Reference System.

14.	OPUS: On-line Positioning User Service; The National Geodetic Survey operates OPUS as a means to provide GPS users easier access to the NSRS.

15.	Point: An identified spot located on the surface of the earth. For the purpose of this definition, a point can be either physical or electronic depending on the context in which it is used. Physical points include PK nails, wooden hubs, rebar, large nails, or other structures capable of being utilized as a marker. Electronic points include all points generated by computers or electronic surveying equipment.

16.	PPK: Post Processed Kinematic; PPK surveys are similar to RTK surveys, except there is no radio communication between the reference station and the rover, so the rover cannot process a position in “real time”. Survey data from both the reference station and rover is imported into GPS processing software to determine the measured position.

17.	Reference Monument: A monument placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

18.	RTK: Real Time Kinematic; RTK surveys utilize two or more receivers with at least one receiver remaining stationary over a known coordinate. The radio at the reference station broadcasts its position to the rovers and the system processes the baselines in “real time” allowing for project coordinate information to be gathered and analyzed during the actual field survey.

19.	Slope Staking: The process of using measurements and calculations to determine where to begin a cut or fill, the slope ratio, and the depth of the cut or fill.

20.	Static: Static survey methods require multiple GPS receivers to collect data over the course of a long period of time. The data collected by the receivers is downloaded into a GPS processing software program to determine the measured position.

21.	Surveyor: The Contractor’s Professional Land Surveyor placed in “responsible charge”, and currently registered in the State of Alaska as defined in AS 08.48.341.

22.	Tessellation Spacing: The distance along a line or an arc that a TIN point is created.

23.	TIN: Triangulated Irregular Network; A vector based representation of a physical land surface.

24.	Witness Corner: A point or monument placed at a known distance and direction from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

25.	Weeding: A procedure used to limit the frequency of information displayed.

642-2.01 MATERIALS.

1.	Monument Cases: Use castings meeting AASHTO M 105, Class No. 30A. Coat castings with a bituminous damp-proof coating. Bolting tops shall be used.

2.	Primary Monument: A minimum 2 3/8” diameter nonferrous pipe at least 30 inches long, with a minimum 4-inch flange at the bottom and having magnets attached at the top and bottom. A minimum 3 1/4” diameter nonferrous metal cap shall be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments that will be oriented to be read facing up-station.

3.	Secondary Monument: A minimum 5/8 inch x 30 inch rebar with a 2-inch aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number, the point/corner identification, and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL REQUIREMENTS. Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or directly under the responsible charge of the Surveyor.

Use competent, qualified personnel and suitable equipment for construction surveying activities. The Surveyor’s personnel shall be supervised and trained in the avoidance of systematic errors. The Surveyor’s personnel shall be familiar with geodetic concepts and least-squares adjustments. Correcting errors resulting from the operations of said personnel shall be at the Contractor expense. The Contractor is responsible for the accuracy of the work.

Schedule a mandatory Pre-Survey Conference with the Engineer, Contractor, Surveyor, and all personnel who are to be involved in the survey work, two weeks prior to beginning survey work. The purpose of this meeting will be to discuss methods and practices of accomplishing the required survey work.

Furnish computer services to accomplish the work. All data shall be signed by the Surveyor for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver field books, computer forms and computer output data to the Engineer. Furnish all computer generated data in a file format and medium that is compatible with Department software. This data becomes the property of the State of Alaska.

Furnish field survey notes. Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with the State of Alaska DOT&PF Construction Surveying Requirements. Make field books available for inspection by the Engineer’s project personnel at any time. Copies of the field books shall be kept in a separate secure location.

Furnish all equipment including but not limited to vehicles, stakes, measuring tapes, levels, rods, lasers, GPS receivers, total stations, traffic control devices, safety devices and other equipment necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish traffic control necessary for surveying activities in accordance with Section 643, and the latest edition of the Alaska Traffic Manual (ATM). Outfit all field employees with appropriate High Visibility Garments as defined in Subsection 643- 3.11.

The Engineer may randomly spot check the Contractor's surveys, staking, and computations. The Department assumes no responsibility for the accuracy of the work.

The Engineer has the right to communicate directly with the Surveyor. Any communication regarding changes to the original scope of work shall go through the Contractor.

The Surveyor is responsible for:

1.	Maintaining registration as a Professional Land Surveyor in the State of Alaska.

2.	Maintaining familiarity with the site conditions and progress of the project.

3.	Determining the accuracy required for each survey stake.

4.	Following the State of Alaska DOT&PF Construction Surveying Requirements.

5.	Notifying the Engineer of conflicts and changes necessary due to utilities, match point variations, design revisions, or other variables.

6.	Slope Staking.

7.	Flagging and staking all clearing and/or grubbing limits in accordance with Section 201. Clearly identify all trees that are specified to remain.

8.	Staking and hubbing all layers of material shown in the typical sections, including the bottom of excavation, top of borrow, top of base course, and top of surcharge.

9.	Staking all culverts, curbs, inlets, and other drainage appurtenances.

10.	Staking all bridge and pedestrian over/under-crossings.

11.	Staking all right-of-way and material source limits.

12.	Rabbit tracking for temporary and permanent pavement striping, and pavement marking devices.

13.	Development of DTM’s, and plotted cross sections.

14.	As-built and Topographic surveying.

15.	Removal and disposal of all flagging, lath, stakes and other staking material after the Project is completed. Burning of material is not allowed on the project.

16.	All other surveying and staking necessary to complete the project.

17.	Document the Station at the beginning and ending of existing passing zones before work that will remove or obliterate the existing striping.  Measure, as outlined below, sight distance for passing zones after the base course layer or pavement milling has been accepted.  Use Table 642-1 to establish Minimum Passing Sight Distance.  Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit.  Record the sight distance for each station location that falls below the posted speed limit plus 10 MPH.  Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH are not required to be recorded.  If recorded mark them as "Pass" or "+."  Mark stations observed to fall below the values required for the posted speed limit as “Fail” or “-.”

Measure from the roadway edge of traveled way, using a 3.5 ft object height (or “instrument height”) at 100 ft station marks looking ahead to a 3.5 ft target height at the edge of traveled way for opposing traffic.  Provide a list of each station result for each direction of travel along the roadway edge of traveled way.  Certify and record the results on standard “letter” sized paper and provide a copy to the Engineer at least 14 days before laying out final pavement markings.

The Engineer will forward one copy of the existing and proposed sight distance measurements on the form provided herein, to the Regional Traffic Engineer.  Table 642-1 does not automatically ensure passing striping will be provided.  The Regional Traffic Engineer’s office will take up to 14 days to review and approve pass/no pass striping against operating speeds for the roadway before installation, using Table 642-1 and the Alaska Traffic Manual as a guide.  No pass striping zones shall be at least 500 ft in length.  Passing striping shall be no less than 400 ft minimum and long enough to meet the distances in Table 642-1.  Establish no passing zones at all at-grade railroad crossings.  Passing striping will not extend into a segment of road without minimum sight distance.

TABLE 642-1

PASSING SIGHT DISTANCE

| Operating Speed (mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 25 | 450 |
| 30 | 500 |
| 35 | 550 |
| 40 | 600 |
| 45 | 700 |
| 50 | 800 |
| 55 | 900 |
| 60 | 1000 |
| 65 | 1100 |
| 70 | 1200 |

Passing Sight Distance Survey Table.

ROAD NAME:

Stationing:  From  	  To

Surveyor:  	  Date:

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Existing Striping: Pass or No-Pass | Engineer's Striping Requirement |
| --- | --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

4.

5.

Accepted By:  	  Date:

DOT/PF Project Engineer

642-3.02 MONUMENTS.  The Department will reference and replace all monuments identified on the plans. The Surveyor shall notify the Engineer immediately of any monuments encountered that are not identified on the plans. The Engineer will determine whether the monuments encountered are to be referenced or adjusted by the Surveyor or the Department.

If directed by the Engineer, the adjustment of monument cases or the referencing of monuments not identified on the plans will be considered additional work and paid by 642(3), Three Person Survey Party. Set existing monument cases to be adjusted to new elevations in the manner and at the elevations directed.

The Surveyor shall complete and stamp a State of Alaska Land Survey Monument Record form for each primary and secondary monument referenced. Provide the required survey information on the form in accordance with statutory requirements, including the project name/number, section, township, and range. Meet requirements for recording at the District Recorder’s Office in which the project is located for each monument record. Deliver conforming copies of the recorded forms to the Engineer before monument removal or disturbance.

642-3.03 SURVEY CONTROL. The basis of project control is identified in the Survey Control Sheet. Use the calibration parameters shown in the Survey Control Sheet to Calibrate/Localize/Convert to the local project coordinate system. Contact the AK DOT&PF Central Region Survey Manager through the Engineer for calibration parameters if they are not shown in the plans. Independently recover and verify all survey control points shown in the Survey Control Sheet. Establish and verify new reference points where required, to replace missing points. Notify the Engineer immediately if a reference point is discovered to be in error, or a reset point is not in harmonious relationship to the existing control points. Provide the Engineer a signed hard copy verifying vertical loop closure of project control points.

The use of RTK is not an acceptable method for establishing additional horizontal or vertical control. Horizontal control points may be established using Static GPS or conventional traversing methods. Vertical control points shall be established with differential levels.

Survey accuracy requirements shall conform to the minimums listed in the State of Alaska DOT&PF Construction Surveying Requirements.

642-3.04 GPS SURVEYS. The specifications described in this Section are not intended to discourage the use of new GPS procedures and techniques. Procedures that are not defined by this specification may be allowed if approved by the AK DOT&PF Central Region Survey Manager, through the Engineer.

1.	General Requirements:

a.	All surveying shall be done in the local project coordinate system.

b.	OPUS shall be used for the determination of Reference Station positions only, and shall not be used directly for producing final positions for any Static, Fast Static, RTK or PPK surveys. OPUS may be used as a tool for verification of the final positions obtained from these types of surveys.

2.	GPS Equipment: Survey Grade dual frequency GPS receivers shall be used. For static surveys these shall be set up on adjustable leg tripods at a minimum. Fast or Rapid Static GPS surveys require a bipod at a minimum. RTK or PPK surveys may use fixed or adjustable poles, or secure lashings to vehicles.

3.	GPS Reference Stations:

a.	All Reference Stations shall be approved by the AK DOT&PF Central Region Survey Manager through the Engineer, prior to conducting any GPS surveys.

b.	Primary Reference Stations shall meet current NGS CORS standards. Secondary Reference Stations may be used temporarily when a Primary Reference Station is not available.

c.	Primary Reference Stations shall be permanently mounted and shall not change throughout the duration of the project.

d.	Secondary Reference Stations may be tripod mounted, however, GPS receivers shall never be mounted on aluminum tripods.

e.	All Reference Stations shall be tied to an OPUS derived position, and on the NAD83 datum. Submit GPS data files for a minimum of 2 days, 12 hours per day, 5 second epoch to OPUS to determine the final position. The OPUS derived position shall be determined at the beginning of the project, and shall not change throughout the duration of the project unless approved by the Engineer. Notify all users immediately if any changes are made to the Reference Station’s position. If OPUS is unable to process a position, the Reference Station shall be tied to existing project control.

f.	Reference Stations shall be physically located in clear view of the sky. Avoid locations near cellular towers or other areas that may disrupt satellite signal reception. Avoid locations near large flat surfaces such as buildings, large signs, fences, and other objects that may cause multi-path interference.

g.	Reference Stations shall be located to provide maximum coverage of the project area.

h.	Store 5 second epoch data, and post data online for use by the Engineer.

i.	GNSS enabled Reference Stations are allowed.

4.	RTK Surveys:

a.	The Surveyor shall follow prudent practices when conducting RTK surveys. The NGS has published a draft manual titled National Geodetic Survey User Guidelines For Classical Real Time GNSS Positioning, v.2.0.3 issued in September, 2008. The Surveyor shall become familiar with this manual, in order to better understand prudent practices. Copies of the draft manual may be available upon request or may be downloaded from the following web site: http://www.ngs.noaa.gov/PUBS_LIB/NGSRealTimeUserGuidelines.v2.0.4.pdf.

b.	RTK surveys may not be used to permanently mark or delineate Right-Of-Way.

5.	Local Coordinate Calibration:

a.	Use GPS calibration parameters if they are provided on the Survey Control Sheet. If GPS calibration parameters are not given, develop a local site calibration based on existing project control. All included control points shall have WGS84 positions that were observed by either a GPS Static or Fast Static network, as well as the final adjusted project control coordinate values that match the values listed on the Survey Control Sheet. The calibration shall consist of the following conversion parameters; Rotation, Translation, Scale, and GPS derived orthometric heights. Values listed on the Survey Control Sheet shall be held fixed in any adjustment, barring any large residuals. Notify the Engineer of any large residuals so that the problems can be identified and corrected. Submit a signed hard copy of the calibration parameters, residuals, and related control points to the Engineer for approval before staking activities begin.

b.	Perform a local calibration each time the coordinates of the reference station change.

6.	GPS Data Summary Report:

a.	Generate reports for all surveyed points, including the Point Number, Northing, Easting, Elevation, Point Code, Annotation(s), Date, Time, residuals, observation (start and stop) times, and antenna height information. Summary reports shall bear the signature and seal of the Surveyor.

b.	The Engineer may require the Contractor to re-survey specified points at no cost to the Department if the Survey doesn’t meet the minimum accuracy requirements defined in the State of Alaska DOT&PF Construction Surveying Requirements.

7.	Weather Conditions: The Surveyor shall follow prudent practices when conducting GPS surveys in inclement weather. The following is recommended as a guideline:

a.	Regularly observe surface and solar weather forecasts prior to planning survey activities.

b.	Use sound practical judgment when performing surveys during inclement weather conditions.

c.	Observations should never be conducted during an electrical storm.

d.	Note significant or unusual weather conditions in the field notes, data collector, or receiver.

642-3.05 TOPOGRAPHIC SURVEYS. Topographic surveys shall be conducted under the direct supervision of the Surveyor. The purpose of a topographic survey is to gather field data to determine the configuration (relief) of the surface of the earth (ground). Use all data collected to generate topographic DTM surfaces as defined in Section 642-3.07, Digital Terrain Models. All data becomes the property of the State of Alaska. Conduct topographic surveys as follows:

1.	General Requirements:

a.	Collect topographic data within the right-of-way limits.

b.	Keep all shots 50 ft or closer, as necessary to accurately define all surface features within the roadway corridor.

c. 	Keep a field book of notes describing changes or errors of rod heights, point descriptors, or other annotations necessary to verify all electronic data.

- Identify each point with a point number. Multiple points with the same point number are not permitted.

- Identify each shot with the appropriate point code. Break line points shall be separately identifiable from ground shots.

f. 	Append any additional information required to further describe a point with point annotations.

g. 	Develop a summary of standard point codes for all points used on the project.

h. 	Develop a summary of standard point descriptors to identify all point codes used on the project (i.e. Edge of Pavement is the point descriptor corresponding to the EP point code).

2.	Functional Requirements: The purpose of a topographic survey is to develop an appropriate DTM as defined in Section 642-3.07. Conduct a topographic survey to meet the appropriate functional requirements as defined below:

a.	As-built Surfaces – Conduct a survey of all finished roadway surfaces, embankments, ditches and other topographic features as required to accurately define the project topography.

b.	Excavation Surfaces – Conduct a survey of original grade (upper) surfaces, and bottom of excavation (lower) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey prior to excavation.

(2)	Lower surface – Survey after the final grade has been established by excavation.

c.	Embankment Surfaces – Conduct a survey of excavated or original grade (lower) surfaces, and top of embankment (upper) surfaces, as necessary to produce DTM volumetric quantities. Follow the requirements listed below:

(1)	Upper surface – Survey after the final grade has been established.

(2)	Lower surface – Survey prior to the placement of embankment. If only grubbing or pavement removal is required prior to placement of embankment, the topographic data may be collected prior to grubbing and pavement removal and adjusted by the average depth removed, as measured in the field. If excavation is required prior to placement of embankment, survey only after excavation activities have been completed.

3.	Accuracy Tolerance Limits: The Surveyor shall check into and collect primary control monument locations to ensure the data being collected meets the minimum Horizontal and Vertical Accuracy Tolerances. This shall serve as a basis of acceptance for the topographic data collected by the Surveyor. The Horizontal and Vertical Accuracy Tolerances will be used to check for systematic error, and will be evaluated by comparing all control check shots taken during the topographic survey to the monument’s location as defined on the Survey Control Sheet. The Volumetric Accuracy Tolerance will be used to check for random and operator error, and will be evaluated by comparing the Contractor furnished DTM with an independent DTM developed by the Department. The Volumetric Accuracy Tolerance shall be applied only to survey data that is used to calculate volumetric quantities.

a.	Horizontal Accuracy Tolerance – Check shots shall be within ± five hundredths (0.05) of a foot of the monument’s horizontal position. If any of the data doesn’t meet the minimum the horizontal tolerance, the Engineer may require the Contractor to re-survey the non-conforming points at no additional cost to the Department.

b.	Vertical Accuracy Tolerance – Check shots shall be within ± one tenth (0.10) of a foot of the monument’s vertical position. If any of the data doesn’t meet the minimum vertical tolerance, the Engineer may direct the Contractor to re-survey the non-conforming points at no additional cost to the Department.

c.	Volumetric Accuracy Tolerance – The Department will determine the volumetric error on randomly selected areas, including at least 20% of the area within the slope limits.  The Department will calculate the volumetric error as follows:

(1)	Determine the net volume by comparing the Contractor’s DTM to the Department’s DTM.

(2)	Determine the accepted volume by comparing the Department’s DTM to the appropriate neat-line surface.

(3)	Determine the volumetric error by dividing the net volume by the accepted volume.

The Engineer may require the Contractor to re-survey any areas that exceed 5% error at no additional cost to the Department.

4.	Control Check Requirements: Collect local project control data at the following minimum frequency:

a.	Every time the instrument is turned on, at the beginning of the survey session.

b.	Prior to every time the instrument is turned off, at the end of the survey session.

c.	Every time the instrument is moved (radial survey).

d.	Every time the backsight is moved (radial survey).

e.	Every time the actual or broadcasted position of the Reference Station changes (GPS survey).

5.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted and electronic as-built surfaces (developed per Section 642-3.07) showing major and minor contours. Standard contour intervals shall be 5 ft (major) and 1 ft (minor).

b.	All field books noting any errors, corrections, or changes to the data.

c.	All electronic survey data in a comma delimited ASCII file in PNEZD format (Point number, Northing, Easting, Elevation, and Description).

d.	Letter of conformance signed and sealed by the Surveyor, certifying that the Topographic Survey meets the minimum Horizontal and Vertical accuracy requirements. Attach all backup data and calculations.

642-3.06 AS-BUILT SURVEYS. As-built surveys shall be conducted under the supervision of the Surveyor. The as-built survey shall document the final locations of roadways, topographic surfaces, structures, and utilities within the ROW project limits. The Surveyor shall maintain communication with the Contractor, Sub-Contractor or Utility Company as necessary to coordinate surveying activities. Surveying activities shall be conducted as soon as possible as each phase of the project is completed, and to avoid scheduling conflicts. The survey will be used to verify that the contracted work items conform to the plans and specifications. All survey data becomes the property of the State of Alaska.

1.	General Requirements:

a.	Topographic Survey of all roadway and pedestrian corridors, in accordance with Section 642-3.05, Topographic Surveys.

b.	Utility Survey of all existing and re-located utilities. Record the horizontal and vertical location of all underground and overhead utilities. Take digital photos of all exposed utility crossings. Identify the location of each photo taken, including the approximate northing, easting, and bearing.

c.	Structural Survey of all existing and re-located structures, including bridges, tunnels, manholes, signs, fences, guard rails, walls, and foundations.

2.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted as-built drawings showing the final surveyed locations of all roadways, topographic surfaces, structures, and utilities. Plotted drawings shall be identified by the Project name and number, and bear the signature and seal of the Surveyor.

b.	Printed color photos, identifying the location of all underground utility crossings.

c.	All field books used to conduct the as-built survey.

d.	All DTM and point data files generated by the as-built survey.

642-3.07 DIGITAL TERRAIN MODELS. Develop all Digital Terrain Models using CAD software that is compatible with the latest release of software used by the Department. All DTM’s shall be approved by the Engineer.

1.	DTM Development Methods:  Develop all DTM’s using the appropriate method as defined below:

a.	Engineering Method - Use this method to define all neat-line surfaces. Develop the DTM by associating all appropriate engineered features such as alignments, profiles, sections, daylight surfaces, grading lines, and other features.

(1)	CAD software shall generate and automatically update surfaces based on the association of alignments, profiles, sections, grading lines, and other parameters necessary to accurately represent neat-line geometry.

(2)	Limit tessellation spacing to allow an accurate representation of a surface feature. The Engineer may require changes to the tessellation spacing, if necessary to allow an accurate representation of the feature.

(3)	If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, only the neat-line limit shall be used.

b.	Topographic Method - Use this method to define all topographic surfaces. Each vertex of a triangle in the TIN shall be formed by a field measured data point, and shall be located by its (XYZ) coordinate. Develop the TIN surface by connecting Topographic Survey points to their nearest neighboring points (in XY), except as outlined below:

(1)	Break Lines – Create break lines by connecting Topographic Survey points that are identified by their appropriate break line descriptors. Break lines shall snap to vertices on adjacent break lines when two break lines intersect. Break lines shall not cross. Use break lines to establish the following features:

(a) 	Centerline of roadway.

(b)	Lane separations (for multiple lane roadways).

(c)	Edge of pavement.

(d)	Shoulder hinge points.

(e)	Bottom of ditch.

(f)	Ditch back slope catch point.

(g) 	For curb and gutter sections, break lines shall be collected at the flow line and back of curb.

(h)	Ridge lines.

(i)	Rim of pits or significant depressions.

(j) 	Areas of slope change or undulations in slope.

(k) 	Bottom of valleys or draws.

(l) 	Hydraulic features.

(m)	Around buildings and structures (including top and bottom of walls).

(2)	Boundaries – Boundaries break the TIN lines and define the edge of the surface. Use boundaries to trim all non-relevant edges from the DTM. Use either non-destructive or destructive trimming as necessary to preserve the accuracy of the DTM. Use boundaries to establish the following features:

(a)	Outer boundary of the DTM.

(b)	Edge of a void inside the surface.

(c)	Edge of an island inside of a void.

(3)	Surface Editing – Surface Editing allows changes that more accurately represent the actual terrain. Use surface editing to delete or swap edges of the triangulated network as necessary to best represent the actual site condition. Mathematically computed points for the purpose of surface smoothing may be used only if approved by the Engineer. The creation of contour lines for the purpose of DTM surface extraction is not acceptable.

c.	Combination Method - Use this method when the Engineer approves a change to the neat-line limit.

(1)	In areas where the Engineer approves a change to the neat-line limit, develop new surfaces using the Topographic Method.

(2)	Replace the neat-line surface with the new topographic surfaces to create an appropriate single surface.

642-3.08 CONTRACTOR FURNISHED COMPUTATIONS. Provide computations for volumetric pay items using DTM’s developed per Section 642-3.07. Cross sections developed from the appropriate DTM’s will be used as a supplementary quality control check on DTM parameters and quantities, and not for pay. The Contractor may use the Average End Area Method in accordance with Section 109, only if approved in writing by the Engineer.

1.	Deliverables: Provide copies of the following to the Engineer:

a.	Plotted cross sections from the DTM surfaces. Develop separate cross sections for each volumetric pay item. More than one pay item per plotted cross section is not allowed.

(1)	Plot every 50 ft on Station, including intermediate stations as required to define angle points, curves, or other significant changes in the roadway geometry.

(2) 	Show the elevation and offset information for all vertex points. Weeding vertex point labels is not allowed. Provide separate report in station, offset, and elevation format, of all vertex points per section, including all surface intersection points.

(3)	Show the area for each cross section.

(4)	Label each plot with the project name, project number, pay item number, and pay item name.

(5)	Label each plot with the Surveyor’s Company name and address.

b.	Plotted profiles from the DTM surfaces. Develop separate plots for each volumetric pay item. Each plot shall only identify the profiles appropriate to the volumetric pay item.

(1)	Plot the profile along the alignment centerline as shown in the plans.

(2)	Label each profile as original ground, bottom of excavation, and the top or bottom of embankment, as appropriate.

(3)	Label topographic profiles with elevation and station information, using a weeding frequency of every 100 ft, or as necessary to match the frequency shown on the plans.

(4)	Label the neat-line profiles with elevation and station information every 100 ft, and for the beginning, end, and VPI of all vertical curves and grade breaks. Label the percent slope between all grade breaks, to the fourth significant decimal.

(5)	Label each plot with the project name, project number, pay item number, and pay item name.

(6)	Label each plot with the Surveyor’s Company name and address.

c.	Electronic Data

(1)	Provide copies of all Topographic, Neat-line, and Combination surfaces to the Engineer. Include all electronic features (alignments, profiles, sections, etc.) used to generate the surfaces.

(2)	All data shall be delivered on a clearly labeled CD-ROM or DVD, unless specified otherwise by the Engineer. The label shall include the project name, project number, Surveyor’s company name, and date. All data becomes the property of the State of Alaska.

(3)	DTM files shall be saved in Autodesk, TIN, XML, or other approved formats compatible with Department software.

(4)	Provide separate spread sheet point file in station, offset, and elevation format, of all vertex points per section, including all surface intersection points.

d.	Volume Reports

(1)	Provide interim volume reports showing quantities between every 50 ft station. The volume reports shall be summarized to allow the Department to reference the quantities per individual plan sheet, or as defined in any earthwork summary shown on the plan sheets.

(2)	Provide a final volume report reflecting the final total quantity. Attach all data, calculations, and plots to the report. The report shall be signed, sealed, and dated by the Surveyor. This report shall be used as the basis for final pay.

642-3.09 CONTRACTOR FURNISHED ENGINEERING TOOLS. Furnish and maintain Engineering Tools as directed by the Engineer, for the exclusive use of the Engineer throughout the duration of the project. The Contractor shall furnish all equipment specifications to the Engineer for approval, prior to furnishing equipment. The equipment shall be in good working condition not more than 1 model year old. The Contractor shall insure and indemnify the Department against normal wear and tear, damage, theft, and all other events that may cause a loss of function of the furnished tools. The equipment shall be returned to the Contractor upon completion of the project, or when services are terminated by the Engineer. Furnish training for the Engineer’s staff, as directed by the Engineer.

1.	GPS Rover Unit – All components shall be fully compatible to provide a stand-alone GPS Rover Unit. The Rover Unit shall be an “all on the pole” system equipped with the following:

a.	Receiver

(1)	Bluetooth compatible.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Dual frequency receiver capable of tracking at least twelve (12) satellites simultaneously on parallel channels.

(5)	Capable of RTK, Static, and Fast Static occupations.

(6)	Capable of receiving L1, L2, and GNSS frequencies.

(7)	Antenna model shall have undergone antenna calibration by the NGS.

(8)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(9)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Bluetooth compatible.

(2)	Equipped with onboard software allowing for the configuration of RTK, PPK, or Static rover modes.

(3)	Meet waterproof specification IPX7.

(4)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(5)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(6)	Capable of collecting data in WGS84 and displaying local project coordinates.

(7)	Equipped with onboard software that allows automatic point logging.

(8)	Capable of creating and storing line-work in DFX or DWG format.

(9)	Equipped with onboard software to allow the user to stake-out points, 3D lines, and DTM surfaces. Software shall allow the user to read cut/fill elevations relative to a DTM surface.

(10)	Capable of importing, exporting, and storing point, line, and DTM data.

(11)	Capable of showing satellite, radio, and battery status.

(12)	Equipped with onboard software that allow the user to create and manage survey jobs, point data, coordinate systems, and alignments.

(13)	Equipped with a removable memory storage device with a minimum capacity of 512MB.

(14)	Capable of storing custom configuration settings for the GPS Rover Unit.

(15)	Ensure the controller contains the manufacturer’s latest firmware upgrades.

(16)	Provide the manufacturer’s user guide.

c.	Radio System

(1)	Meet waterproof specification IPX7.

(2)	Support a frequency compatible with the Reference Station.

(3)	Capable of storing multiple radio frequencies.

(4)	Compatible with the Reference Station’s broadcasting format and protocol.

(5)	Power and programming cables.

(6)	Provide the manufacturer’s user guide.

d.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Rover Unit.

(2)	Batteries shall be capable of powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5)	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all onboard batteries to be charged simultaneously, and that safeguard against overcharging.

e.	Rod

(1)	Fixed height (non-adjustable).

(2)	Mounting hardware for GPS controller and radio.

(3)	Pole grip with bubble level.

(4)	Detachable bipod.

(5)	Interchangeable flat and pointed footings.

(6)	Quick release adapter for the GPS receiver.

f.	Carrying Case

(1)	Hard Shell.

(2)	Shockproof.

(3)	Waterproof.

(4)	Capacity to hold all components of the GPS rover, minus the rod.

2.	Continually Operating Reference Station – The location of the CORS shall not change for the duration of the project. The CORS shall be permanently mounted per NGS CORS standards. All structures, mounting hardware, power supply, computers, software, networking, and personnel required to support and operate the CORS is considered subsidiary to this item. Store CORS data for the duration of the project, and post online for use by the Engineer. The CORS shall include and conform to the following requirements:

a.	GPS Receiver

(1)	Choke-ring antenna, model shall have undergone antenna calibration by the NGS.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Able to operate in temperatures between -20º F to +140º F.

(5)	Capable of logging L1/L2 data continuously for 180 days, and storing at 1 second intervals. If onboard memory storage capacity is insufficient, backup all data on an external memory storage device.

(6)	Support multiple, simultaneous data logging sessions at different collection rates.

(7)	Equipped with a dual frequency receiver capable of tracking L1, L2, and GNSS frequencies on at least 12 satellites. Receiver shall have a minimum of 24 channels.

(8)	Support CMR/CMR+ and RTCM output simultaneously via separate ports.

(9)	Use multi-path mitigation techniques.

(10)	Satellite acquisition technology shall provide improved tracking in areas of high radio interference such as under power lines, around airports, near radio-intensive construction sites.

(11)	Capable of 1PPS output with an accuracy of 1usec.

(12)	Equipped with 1 primary and 1 secondary power input port.

(13)	The system shall automatically switch between power sources.

(14)	Equipped with over-voltage protection on all power inputs.

(15)	Capable of reporting Signal-to-Noise Ratio (SNR) values for L1 and L2.

(16)	Capable of logging data at operator selected intervals of 0.5, 1, 5, and 30 seconds.

(17)	Provide the manufacturer’s user guide.

b.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(4)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(5)	Provide the manufacturer’s user guide.

c.	CORS Facility – Provide a facility to mount and house CORS station equipment.

(1)	Facility shall meet NGS CORS mounting requirements, and shall be approved by the Engineer.

(2)	Shall be physically located in a clear view of the sky, away from objects that may cause multi-path interference.

(3)	Location shall provide for maximum strength of geometry relative to the primary control network and the project limits.

(4)	Shall be connected to a primary power source, and a backup power source capable of providing uninterrupted backup power for a minimum of 48 hours.

3.	GPS Base/Repeater Station – All components shall be fully compatible to provide a stand-alone GPS Base/Repeater Station setup. The setup shall include the following:

a.	Receiver

(1)	Meet waterproof specification IPX7.

(2)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(3)	Dual frequency receiver capable of tracking at least 12 satellites simultaneously on parallel channels.

(4)	Antenna model shall have undergone antenna calibration by the NGS.

(5)	Ensure the receiver contains the manufacturer’s latest firmware upgrades.

(6)	Carrying case.

(7)	Tribrach with optical plummet and height rod.

(8)	Provide the manufacturer’s user guide.

b.	Controller

(1)	Equipped with onboard software allowing for configuration as a GPS reference station in RTK, PPK, Static, and Fast Static modes.

(2) 	Capable of logging raw observations for post processing.

(3)	Capable of showing satellite, radio, and battery status.

(4)	Meet waterproof specification IPX7.

(5)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(6)	Full QWERTY keyboard with numeric keypad, and/or equivalent touch screen interface.

(7)	Equipped with a removable memory storage device with a minimum capacity of 512MB.

(8)	Equipped with 1 primary and 1 secondary power input port.

(9)	Ensure the controller contains the manufacturer’s latest firmware upgrades.

(10)	Provide the manufacturer’s user guide.

c.	Radio

(1)	Transmission power, 25 watt minimum.

(2)	Meet waterproof specification IPX7.

(3)	Shockproof for a drop onto a hard surface from a height of 4 feet.

(4)	Support a frequency compatible with the Reference Station.

(5)	Capable of storing multiple radio frequencies.

(6)	Compatible with the CORS broadcasting format and protocol.

(7)	Ensure the radio has a current license to broadcast in accordance with FCC requirements.

(8)	Ensure the radio broadcast frequency doesn’t conflict with other nearby broadcasting sources.

(9)	Equipped with onboard software/firmware allowing for configuration as either a Reference Station or a Repeater Station.

(10)	Carrying case.

(11)	Antenna.

(12)	Antenna/pole mounting adapter.

(13)	Provide the manufacturer’s user guide.

d.	Tripods – Provide one of each:

(1) Conventional tripod with extendible range pole. Include carrying case.

(2) Conventional wood tripod.

e.	Batteries

(1)	Provide all batteries required to fully power and operate the GPS Base/Repeater Station.

(2)	Batteries shall be capable powering their respective equipment continuously, for not less than 6 hours under normal operating conditions.

(3)	Each battery shall be rechargeable and commercially available.

(4)	Provide an identical replacement backup battery for each primary battery required.

(5) 	Provide all power connectors necessary to connect the batteries to the equipment.

(6)	Provide battery chargers to allow all batteries to be properly charged, and that safeguard against overcharging.

4.	Computer Hardware – Hardware shall meet the following minimum requirements:

a.	Laptop Computer

(1)	2.8 GHz multi-core CPU.

(2)	120GB Internal Hard Drive.

(3)	4 GB System RAM.

(4)	Display 13” with 1,600 x 1,200 resolution.

(5)	512MB video memory.

(6)	DVD Burner Drive.

(7)	Internal Bluetooth and Wi-fi.

(8)	Internal Battery.

(9)	120v AC Adapter.

(10)	12v DC Adapter.

(11)	Built-in CF, SD, and PCMCIA card ports.

(12)	4 USB 2.0 ports.

(13)	1394 (firewire) port.

(14)	Mouse (wireless).

(15)	Travel Case (hard) for laptop and accessories.

b.	Laptop Computer Mount

(1)	Permanently installed in a vehicle, as directed by the Engineer.

(2)	Fastened to the passenger side of the vehicle.

(3)	Shock and vibration resistant.

(4)	Fully adjustable positioning with mechanically locking hinge points.

c.	Desktop Computer

(1)	3 GHz multi-core CPU

(2)	120GB Internal Hard Drive

(3)	4 GB System RAM

(4)	Compatible DVI 19” monitor with 1,600 x 1,200 resolution

(5)	Internal video card/chip, 512MB, 2 DVI ports

(6)	Internal DVD Burner Drive

(7)	CF and SD media card reader

(8)	6 USB ports

(9)	1394 (firewire) port

(10)	Internal wireless (IEEE 802.11 b/g) network card

(11)	Internal Ethernet card (10/100 Mbps).

(12)	Uninterruptible Power Source (UPS), 8 outlets, 390 Watt

(13)	250 GB Backup Hard Drive (external)

(14)	Mouse and Keyboard

d.	Laser Printer

(1)	45 pages per minute print speed.

(2)	1200 x 1200 dpi print quality.

(3)	Main tray capacity shall hold no less than 500, 8.5 x 11 inch sheets.

(4)	Multipurpose tray capable of custom sizes up to 11 x 17 inch sheets.

(5)	128 MB of onboard memory, minimum.

5.	Computer Software – All software shall be licensed and fully operational. Provide software that is similar or approved equal in accordance with the following:

a.	Operating System Software – Provide an operating system that supports the drivers of all onboard and auxiliary computer hardware systems. The operating system shall be of the latest release, with the most current updates installed. The operating system shall support all of the applications listed below.

b.	CAD Software – Provide CAD software that is capable of dynamically associating and updating alignment, profile, section, grading, point, and surface data. The software shall be capable of saving all data to formats that are compatible with the latest release of CAD software currently used by the Department. Formatting shall preserve the dynamic relationship of all DTM features. Software that doesn’t dynamically associate all DTM features is not acceptable.

c.	Word Processing Software – Provide software that is compatible with the latest release of word processing software currently used by the Department.

d.	Spreadsheet Processing Software – Provide software that is compatible with the latest release of spreadsheet processing software currently used by the Department.

e.	Anti-Virus Software – Provide software to protect against viruses and other security threats. Software shall be equipped with a firewall containing industry standards of system protection. The software shall be capable of backing up all hard drive data.

f.	GPS Processing Software – Provide GPS processing software of the latest release and from the same vendor as the GPS equipment furnished. Include all necessary hardware/software keys to enable L1 & L2 Static, PPK, and RTK processing, GNSS processing, network adjustments, datum and map transformations, and RINEX data importing and exporting.

642-4.01 METHOD OF MEASUREMENT. The work will be measured according to Section 109, and as follows:

Item 642(1) Construction Surveying.  Prior to beginning work, develop a Lump Sum Agreement that itemizes major contract work requirements by percentage. Work will be measured by the percent completion of all major contract work requirements defined in the Lump Sum Agreement.

Item 642(3) Three Person Survey Party.  By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed, and as supported by certified payrolls. Work accomplished by a three person survey party will be paid at 100% of the contract unit price. Work accomplished by a two person survey party will be paid at 75% of the contract unit price. Work accomplished by a one person survey party will be paid at 32% of the contract unit price.

Item 642(13) Contractor Furnished Computations.  Prior to beginning work, develop a Lump Sum Agreement that itemizes all plan sheets labeled “Plan and Profile” (or similar) by percentage. Work will be measured by the percent completion of all computations required, per plan sheet defined in the Lump Sum Agreement.

Item 642(14) Contractor Furnished Engineering Tools.  Contingent sum work will be measured in accordance with the directive authorizing the work.

Item 642(16) Passing Sight Distance Measurement.  By the number of stations of the project measured separately along centerline, once for each direction, only after the certified and recorded results have been accepted by the Engineer.

642-5.01 BASIS OF PAYMENT. Pay Items include all necessary personnel, equipment, transportation, traffic control, and supplies to accomplish the work described in the Contract, or directed by the Engineer.

Pay Item 642(1) Construction Surveying.  This item includes all surveying work described in the Contract except for work paid for under 642(3), 642(13), and 642(14). 5% of the contract lump sum bid price will be withheld until the final As-Built Survey is completed and accepted by the Engineer.  Surveying required for determining volumetric quantities is considered subsidiary to Item 642(13).

Pay Item 642(3) Three Person Survey Party.  Adjustment according to 109-1.04 is not allowed for this pay item. When directed by the Engineer to reference an existing monument not shown in the plans, payment will be made after the Monument Record Forms are prepared and recorded in the local Recorder’s Office and accepted by the Engineer.

Pay Item 642(13) Contractor Furnished Computations.  This item includes all work required to develop and furnish quantity computations in accordance with methods required by the contract. Earthwork computations, digital terrain model development, plotted cross sections, quantity reports, and associated topographic surveying are subsidiary to this item. The Engineer may withhold payment for this item if the minimum specifications are not met.  10% of the contract lump sum bid price will be withheld until final computations are accepted by the Engineer. If the Contractor excavates or fills beyond the neat-line limit without the direction of the Engineer, the calculated volume shall only extend to the neat-line limit.

Pay Item 642(14) Contractor Furnished Engineering Tools.  The Engineer shall issue a directive defining and authorizing the work. Payment for a GPS Rover, Base/Repeater Station, CORS, or Computer System will be made on a time and materials basis in accordance with Subsection 109-1.05-3e, Leased or Rented Equipment. Payment for training will be made on a time and materials basis in accordance with Section 109-1.05. If the training is beyond the Contractor’s ability or expertise, payment will be made in accordance with Subsection 109-1.05-4, Work by a Specialty Subcontractor. The Engineer may withhold payment for this item if the minimum specifications are not met. The Engineer may issue a directive at any time to terminate or re-authorize the work, at no additional cost to the Department.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

642(1)	Construction Surveying	Lump Sum

642(3)	Three Person Survey Party	Hour

642(13)	Contractor Furnished Computations	Lump Sum

642(14)	Contractor Furnished Engineering Tools	Contingent Sum

642(16)	Passing Sight Distance Measurement	Station

51132-080910

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following:

Additional work:

	Illuminate construction activities listed in Table 643-3, Night Work Illumination Level, and Area of Coverage, during hours of night work on roads open to the public inside the project limits.

ES14-031506

This work also includes installing temporary signing and striping at the roundabout in accordance with the Plans, and installing winter barricades as directed by the Engineer.

CR6431-032611

643-1.02 DEFINITIONS. Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding’s by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work:  Work occurring between sunset and sunrise on all days, except the “No Lighting Required” period shown in Table 643-2, Night Work Lighting Requirements.

TABLE 643-2

NIGHT WORK LIGHTING REQUIREMENTS

| Latitude (degrees) | No Lighting Required |  | Nearby Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| < 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14-031506

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Add the following:

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

CR6431-032611

643-1.04 WORKSITE SUPERVISOR.

1.	Qualifications. Replace with the following:

Qualifications.  The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements.  The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, your proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this Section.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

CR6432-110410

2.	Duties.  Add the following:

I.	Supervise lighting of Night Work.

ES14-031506

Add No. 3:

3.	Authority.	The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.

4.	Portable Concrete Barriers.  Add the following:

Use reflective sheeting that meets AASHTO M 268 Type III, IV or V.

10.	Temporary Crash Cushions.  Replace with the following:

Temporary Crash Cushions.  Must have FHWA Acceptance letter for National Cooperative Highway Research Program (NCHRP) 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3.  Use reflective sheeting that meets AASHTO M 268 Type III, IV or V.  Application of crash cushion must be appropriate for the intended use and be installed per manufacturer's recommendation.  Temporary crash cushions used as rail or barrier end treatments must be redirective.  Temporary crash cushions that are barrels or barricade filled with sand or water are considered nonredirective and may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

CR6432-110410

12.	Portable Changeable Message Board Sign.  Replace with the following:

Portable Changeable Message Board Sign.  Use new truck or trailer mounted portable changeable message board signs with self contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18 inch high characters.

b.	Eight character display per message module.

c.	Fully programmable message module.

d.	Remote control cellular, wireless radio frequency (RF), landline.

e.	Waterproof, lockable cover for the controller keyboard.

f.	Capacity for electric/hydraulic sign raising or lowering.

g.	Radar over speed detection.

h.	Variable flash and sequence rates.

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages.

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load.

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter (GFCI).  The chord will have integral GFCI protection located either in the attachment plug or 12 inches or less from the plug.

CR6431-032611

13.	Plastic Safety Fence.  Replace a., b., and c. with the following:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

16.	Flagger Paddles.  Replace the last sentence with the following:

Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.

Add No. 17:

17.	Truck Mounted Attenuator (TMA).  The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer's recommendations.  The TMA shall comply with NCHRP 350 or MASH, Test Level 3 requirements.

CR6432-110410

Add No. 18:

18.	Terminal Markers-Flexible (marker).  Refer to Subsection 606-2.01 Materials.

Add No. 19:

19.	Winter Barricade.  Winter Barricades are intended to be placed on roadways to deter the public from traveling on unopened roads during winter shutdown. A Winter Barricade shall consist of a Type III Barricade, signs, and sand as follows:

- Type III Barricade. Shall meet the requirements of subsection 643-2.01 item 2.

- Signs. Mount one R11-2 (30” x 48”) sign flanked by two OM-4 (18” x 18”) signs on the barricade. Signs shall meet the requirements of subsection 643-2.01 item 1. Signs shall face the direction specified by the Engineer.

- Sand. Place approximately 1 cubic yard of sand, evenly mounded on both sides of the barricade, across the entire width of the barricade. Sand gradation shall not be prone to wind erosion and shall be approved by the Engineer.

51132-033111

Standard Modification

Replace Subsection 643-2.02 CRASHWORTHINESS with the following:

643-2.02 CRASHWORTHINESS.  Submit documentation, by the method indicated, that the following devices comply with the requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3 on the given schedule.

Submit documentation of compliance to the Engineer before installing devices on the project.

| Work Zone Traffic Control Device Compliance with NCHRP 350 or MASH |  |  |
| --- | --- | --- |
| Category | Devices | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
|  | Portable concrete barriers | FHWA acceptance letter specifying the Test Level required in the Plans or Specifications. |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3.  This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

| Device | Composition | Weight | Height |
| --- | --- | --- | --- |
| Cones | Rubber | 20 lb. | 36 in. |
|  | Plastic | 20 lb. | 48 in. |
| Candles | Rubber | 13 lb. | 36 in. |
|  | Plastic | 13 lb. | 36 in. |
| Drums | Hi Density Plastic | 77 lb. | 36 in. |
|  | Lo Density Plastic | 77 lb. | 36 in. |
| Delineators | Plastic or Fiberglass | N/A | 48 in. |

E77-100410

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

E90-100410

Add the following:

Where construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

1.	Specified Gravel Surface.  Traffic may be maintained on a continuous gravel surface where specified:

- Sta. 250+00  to E.O.P.: No time restriction.

- Other Project Roadways:  5,000 ft, no time restriction.

- Palmer-Fishhook Road and Tie-ins to Existing Trunk Road:  As approved by the Engineer.

2.	Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

CR6431-032611

Standard Modification

Replace Subsection 643-3.03 PUBLIC NOTICE with the following:

643-3.03 PUBLIC NOTICE.  Make sure the Worksite Traffic Supervisor gives a minimum of 3 days notice before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Carriers Association

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.  Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent.  Tell them to use these numbers to alert you when emergency vehicles must pass through the project.  When notified of emergencies, use all equipment and make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator System for selected projects.  Check the special provisions for those requirements.

E78-100410

643-3.04 TRAFFIC CONTROL DEVICES.  Replace paragraphs 6 and 7 with the following:

Use only traffic control devices that meet the requirements of the "Acceptable" category in the American Traffic Safety Services Association (ATSSA) "Quality Guidelines for Temporary Traffic Control Devices" and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project.  Stock repair parts for each Temporary Crash Cushion used on the project.  Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware.  All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the Plans, Specifications, and approved TCPs until permanent roadside safety hardware is installed.  All temporary roadside safety hardware shall meet NCHRP 350 or MASH, Test Level 3 unless otherwise noted.

CR6432-110410

After the sixth paragraph add the following

Winter Barricades shall be placed at locations as directed by the Engineer. Winter Barricades shall be removed when directed by the Engineer.

51132-120310

Replace paragraph 8 with the following:

Items paid under this Section remain the Contractor’s property unless stated otherwise.  Remove them after completing the project.

1.	Embankments.  Add the following:

Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

3.	Fixed Objects.  Add the following:

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging.  Replace with the following:

Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone.  The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA (International Municipal Signal Association)

b.	Flagger Certification by ATSSA (American Traffic Safety Services Association)

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned posts at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements.  Remove, fully cover, or lay down flagger signs when no flagger is present.  Keep the flaggers' area free of encumbrances, such as parked vehicles, so that flaggers can be seen easily.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer's written approval before flagging signalized intersections.  When you flag a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode.  Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer.  Get their written approval in advance.  Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

6.	Street Sweeping and Power Brooming.  Replace with the following:

Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-4, Traffic Control Rate Schedule, Street Sweeping.

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface causing fine particles to rise and be caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved surface sucking dirt, dust, and debris into the collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

CR6431-032611

Add No. 9:

9.	Truck Mounted Attenuator (TMA).  TMAs are mounted on the rear of work vehicles.  TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer's recommendations.  TMA shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting.  Approach ends of TMAs shall have impact attenuator markings in accordance with the MUTCD.  Do not use a damaged attenuator in the work.  Replace at your expense, an attenuator damaged from an impact during work.

Add No. 10:

10.	Parallel Guardrail Terminal.  The price listed in the Traffic Control Rate Schedule, Table 643-4, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Parallel Guardrail Terminal unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations yard or as directed by the Engineer.

CR6432-110410

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with:

When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to Subsection 105-1.01, Authority of the Engineer.

Add the following after the second sentence:

In no case shall this time exceed 24 hours.

CR6431-032611

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following in the 2nd paragraph after the 2nd sentence:

Temporary crash cushions required to protect motorists from incomplete guardrail installations, as described in Section 606-5.01 is also an unauthorized lane reduction.

CR6432-110410

Add the following after the 3rd paragraph:

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

Replace Table 643-1 with the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $ 30 |
| 5,000 + | $ 40 |

CR6431-032611

643-3.08 CONSTRUCTION SEQUENCING.  Replace the last sentence with:

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

- Monday through Friday:  0530 hrs to 0800 hrs and 1630 hrs to 1900 hrs on all streets, except Palmer-Wasilla Highway.

- No traffic restrictions between 0530 hours to 2000 hours on the Palmer-Wasilla Highway.

- Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs on the Monday after the holiday.

- During the Alaska State Fair:  Friday from 1600 hrs to Sunday 2300 hrs on all streets except Palmer-Wasilla Highway.  No weekend traffic restrictions will be allowed on Palmer-Wasilla Highway during the Fair.

- Road Closures: The following road closures will be allowed, however none may be concurrent or during normal school operating dates, unless otherwise specified:

  - Bogard Road Culverts Installation at Wasilla Creek - A one week closure of Bogard Road will be allowed.

  - Palmer-Fishhook Road Culvert Installation at Wasilla Creek - A one week closure of Palmer-Fishhook Road will be allowed.

  - Palmer-Fishhook Road Culvert Installation at Carnegie Creek - A three day closure of Palmer-Fishhook Road will be allowed.

  - Bogard Road and Trunk Road Roundabout Construction, Bogard Road Culvert Installation at Wasilla Creek Tributary - A three week closure of Bogard Road at the proposed roundabout and pipe crossing will be allowed.  Upon completion of this closure the roundabout shall have the following in place: curb and gutter, final lift of asphalt, temporary signs, temporary striping, temporary barricades and other items specified in the Temporary Signing and Striping – Roundabout details.  In addition, upon completion of this closure, all highway lighting shall be in place and operational.

51132-121710

Lane restrictions, if allowed, shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2640 feet) of traffic detained, will be allowed for motorists, except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

CR6431-032611

Prior to Winter Shutdown, surface traveled roadways entirely with temporary, existing, or permanent pavement and install all pavement markings, signs and roadway delineators by October 1 of each construction year, unless otherwise approved by the Engineer.. If existing pavement has become damaged, the Contractor shall make repairs to the satisfaction of the Engineer. Asphalt Treated Base Course in the final configuration may serve as a paved surface during winter shutdown. Any temporary pavement will be subsidiary to 643(2) Traffic Maintenance. Provide positive drainage away from the roadway prior to acceptance for winter shutdown. Provide roadside safety protection measures in accordance with Traffic Control Devices for Roadside drawing.

51132-121710

643-3.09 INTERIM PAVEMENT MARKING.  In the second paragraph, delete the words:

“or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

CR6431-032611

Add the following Subsection 643-3.10:

643-3.10 LIGHTING OF NIGHT WORK.  Illuminate the night work areas specified in Table 643-3, Night Work Illumination Level, and Area of Coverage, to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least two machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, Pavement Sweeping | At least four sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) Roads with ADTs over 10,000 2) That are controlled by portable signals or flaggers | Two balloon lights of at least 2000 watts each located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide the lighting equipment specified in Table 643-3 or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibrations.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14-031506

Standard Modification

Add the following Subsection 643-3.11:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to requirements in this Subsection, 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic Pay Items.

E90-100410

643-4.01 METHOD OF MEASUREMENT.

Replace the second sentence of the first paragraph with: Quantities will not be measured during winter suspension of work, except item 643 (6B) Winter Barricade.

51132-120310

2.	Traffic Control Device Items.  Replace the second sentence with the following:

Special Construction signs are measured by the total area of legend bearing sign panel, as determined under Subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-4.

CR6431-032611

Standard Modification

Add No. 16:

16.	Steel F Shape Barrier.  Shall be measured and paid for by the linear foot.

E81-100410

Add No. 17:

17.	Hotline Road Report.  No measurement required to provide a 24 hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643(1) or 643(2), Traffic Maintenance.

CR6431-032611

Add No. 18:

18.	Winter Barricade. By each complete unit. A unit shall consist of a barricade, signs, and sand as specified in subsection 643-2.01 item 19.

51132-120310

643-5.01 BASIS OF PAYMENT.

7.	Flagging and Pilot Car.  Add the following:

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $48.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work will be paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

11.	Traffic Control.  Add the following:

The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

CR6431-032611

12.	Portable Changeable Message Board Sign.  Add the following:

Seven Portable Changeable Message Board Signs used for Permanent Construction Signing will be paid for under Item 643(3) Permanent Construction Signs.  Other portable changeable message board signs will be paid for under 643(25), Traffic Control.

51132-040111

Standard Modification

Add No. 16:

16.	Steel F Shaped Barrier.  The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

E82-100410

Add No. 17:

17.	Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14-031506

Add No. 18:

18.	High Visibility Garments.  Payment for high visibility garments for workers is subsidiary to other Pay Items.

Add No. 19:

19.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401(1A).

CR6431-032611

Add No. 20:

20.	Winter Barricade.  The contract price includes all resources required to provide, install, and remove each Winter Barricade.

Add the following:

Item 643(20B) Temporary Signing and Striping - Roundabout.  The contract price includes all labor, materials, and equipment required to install, maintain, and remove the temporary signs, striping, and barricades, as shown and specified in the Plans. Upon removal, the temporary items shall become the property of the Contractor.

51132-031111

Add the following:

All Temporary Pavement Markings installation and removal is subsidiary to Item 670, except that required under item 643(20B) Temporary Signing and Striping – Roundabout.  All Traffic Control required for the installation and removal of Temporary Pavement Markings is subsidiary to Item 670.

Add the following:

TABLE 643-4

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete or Steel F Shape Barrier | Each | $80.00 |
| Temporary Crash Cushion / Sand or Water Filled Barrels or Barrier (all required per end) | Each | $1250.00 |
| Temporary Crash Cushion / Redirective | Each | $2500.00 |
| Pilot Car | Hour | $73.00 |
| Pilot Car w/Sequential Arrows | Hour | $76.00 |
| Watering | M-Gallon | $25.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $175.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $97.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| ***Deleted*** |  |  |
| Temporary Guardrail | Lineal Foot | $25.00 |

CR6431-032611

Add Pay Item 643(6B):

Pay Item No.	Pay Item	Pay Unit

643(6B)	Winter Barricade	Each

51132-120310

Replace Pay Item 643(15) with the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

CR6431-032611

Add Pay Items 643(20A) and 643(20B):

Pay Item No.	Pay Item	Pay Unit

643(20B)	Temporary Signing and Striping - Roundabout	Lump Sum

51132-031111

Standard Modification

Add Pay Item 643(29):

Pay Item No.	Pay Item	Pay Unit

643(29)	Steel F Shaped Barrier	Linear Foot

E82-100410

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

CR644FOCOM-080511

Standard Modifications

644-2.02 FIELD LABORATORY.  Add the following to the end of the second sentence of the first paragraph:

through one week after Project Completion.

E44-012707

Special Provisions

Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

CR644LAB-071009

644-2.05 VEHICLES.  Delete the second and third paragraphs and substitute the following:

Pickup(LT)/Sport Utility Vehicle (SUV):  Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s).  Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer.  Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equal equipment shall have the following characteristics:

	(4) 55 watt rotators with amber filters

	1200 flashes per minute

	(2) diamond mirrors

	55 inches in length

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The Department is responsible for damage to any vehicle caused by its own negligent operation.

CR644LTSUV-033111

Standard Modifications

Add the following new subsection:

644-2.06 NUCLEAR TESTING EQUIPMENT STORAGE SHED.  Design, furnish and maintain a weatherproof, heated, and ventilated nuclear densometer/testing equipment storage shed for the Engineer to use exclusively throughout the Contract.  Install the building at least 15 feet from an occupied area at a location approved by the Engineer.  Install the shed before beginning of construction activities and maintain it until one week after project completion.  Provide sufficient floor area for the nuclear testing equipment and a portable electric heater to maintain a minimum room temperature of 50 °F in freezing weather.  Design the building with enough floor area to provide sufficient clearance between the equipment, heater, and combustibles.  Provide a commercial grade metal clad exterior entrance door of 3’-0” minimum width by 6’-8” height with dead-bolt lockset.  Hang the door so that hinge pins are not accessible from the exterior.  Provide the Engineer with 2 keys to control access.  Provide a 5/16” x 10 foot long welded steel security chain securely attached inside the structure with tamperproof hardware for the Engineer to secure the testing equipment.  Provide 120 volt, 60 cycle power, an interior light, and a wall receptacle for the heater.  Secure the structure to the ground with tamperproof anchors to resist wind loads and prevent unauthorized movement of the building.  The nuclear testing equipment storage shed remains the property of the Contractor.  Remove the shed from the site following project completion.

Add the following new subsection:

644-2.07 STORAGE CONTAINER.  Furnish, transport, and maintain a weather tight, lockable, steel enclosed 20 foot long X 8 foot wide X 8 foot high wooden floored container for the storage of the Department’s materials, supplies and testing equipment (but not nuclear equipment). Provide twenty equally spaced fastening points on the interior walls that are capable of securing the Department’s contents.  Door opening dimensions of the storage container shall be greater than 60 square feet.  Supply necessary equipment to lift and move container with minimal disturbance to the Department’s contents.  The container shall not be moved by skidding or hook lift.  The Contractor shall be listed as the shipper on documents listing and acknowledging receipt of the Department’s goods for shipment.

Deliver an empty and clean container to the Regional Materials Laboratory, or location acceptable to the Engineer, three weeks before transporting to the project site.  Allow 7 days for the Department to load the container.  Transport the loaded container to the project site.  Set up container at a location approved by the Engineer prior to commencing construction work.

1.	Provide electrical service and other facilities as follows:

a.	Electrical current, 120V (ac), 60 cycle on a 24 hour a day basis.

b.	Wiring system to support a 20 amp user load demand.

c.	2 GFI protected outlets conveniently spaced on the interior walls.

d.	Four 100 watt incandescent or eight 40 watt fluorescent lights located for maximum illumination.

e.	Provide a stairway with railing, built to meet the International Building Code, if there is more than 12-inch difference in floor entry and existing ground elevation.

Return the container to the Regional Materials Laboratory or location acceptable to the Engineer, upon project completion.  Allow 7 days for the Department to unload the container.  The storage container remains your property after completing the work.

E44-012707

Add the following subsection:

644-2.08 ENGINEERING COMMUNICATION.  Engineering Communications, minimum service includes:

a.	Three phone/facsimile lines (different phone numbers for each line)

b.	High speed internet service with modem (DSL or Cable)

CR644FOCOM-080511

644-3.01 METHOD OF MEASUREMENT. Delete the third paragraph and substitute the following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644LTSUV-033111

Standard Modification

Add the following Pay Items:

Nuclear Testing Equipment Storage Shed.  By the number of storage sheds specified, to including components, installation and accepted as completed units and ready for equipment storage.

Storage Container.  By the number of storage containers specified, to including components, installed and accepted as completed units and ready for materials and equipment storage.

E44-012707

644-4.01 BASIS OF PAYMENT.  Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644(2) Field Laboratory.

CR644LAB-071009

Pay Item 644(8) Vehicle (LT/SUV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle (LT/SUV)	Each

CR644LTSUV-033111

Add the following:

Pay Item 644(10) Engineering Communications.  Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644(1) Field Office and as such are paid by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(10)	Engineering Communications	Contingent Sum

CR644FOCOM-080511

Standard Modifications

Add the following Pay Items:

Lump Sum Items. Payment for lump sum items will be made as follows:

1.	A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

2.	The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Nuclear Testing Equipment Storage Shed. At the Contract unit price to include labor, materials, tools, equipment, and supplies required to furnish and install the shed before beginning construction, to maintain it for the duration of the project and to remove the shed and electrical service after project completion.  Electrical service and utility costs are subsidiary to this item.

Storage Container.  At the Contract unit price to including labor, materials, tools, equipment and supplies required to deliver the storage shed to the regional office for loading, to deliver it to the project office, to install it before beginning construction, to maintain it for the duration of the project, to remove the shed and electrical service after project completion, to deliver it to the regional office for unloading, and to remove the storage shed.  Electrical service and utility costs are subsidiary to this item.

Add to Pay Items:

Pay Item No.	Pay Item	Pay Unit

644(15)	Nuclear Testing Equipment Storage Shed	Each

644(16)	Storage Container	Each

E44-012707

Special Provision

Add the following Section:

SECTION 645

TRAINING PROGRAM

645-1.01 DESCRIPTION. This Training Special Provision implements 23CFR230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.l, located in the "yellow pages" of this document.

645-3.01 GENERAL.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicted above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor's judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 SUBCONTRACTS.  In the event a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to Subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor's discretion, graduates early and is employed as a journey worker according to the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial  payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be ducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program, 3 Trainees/Apprentices	Labor Hour

S16-102991

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete No. 2.

2.	60-Day Preliminary Schedule.

Delete the first sentence of No. 3. Schedule Updates.  and substitute the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR261-121302

Special Provision

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.  Hours paid shall be supported by certified payroll.

647-5.01 BASIS OF PAYMENT.

Payment for Item 647(1) Wide Pad Dozer, 65 hp Min will be paid on a contingent sum basis on a per hour basis of $150/hour.

This shall be full compensation for furnishing, operating, maintaining, servicing, and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 hp Min	Contingent Sum

647(2)	Wide Pad Dozer, 65 hp Min	Hour

647(5)	Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth	Contingent Sum

647(6)	Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth	Hour

CR15-082405

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.02 DEFINITIONS.  Revise the first sentence to read:

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements, Section 1, Definitions, along with the following:

Under No. 2. Luminaire. Revise the second sentence to read:

Luminaires consist of hood (including socket, lamp, and ballast), reflector, and glass globe or refractor.

CR660-032411

Standard Modifications

660-2.01 MATERIALS Under No. 1.b. change title by removing:  Materials Not on the "Approved Products List:" and replace with:  Materials Not on the "Qualified Products List:"

E36-012707

660-2.01 MATERIALS.  Add the following:

Anchor Bolts:						Section 740-2.02

1.	Equipment List(s) and Drawings. Delete No. a. in its entirety and the last sentence in No. d. and substitute the following:

a.	Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

d.	Materials Not Requiring Certification: Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

2.	As-Built Plans.  Add the following:  Place 1 copy of the controller cabinet diagram, detector assignment sheet and the intersection and phase diagram as reviewed by the Engineer in clear plastic envelopes and attach to the inside of each controller cabinet.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.  In No. 1., Scheduling of Work. Add the following to the first paragraph:  Contact the regional DOT&PF Traffic Signal Technician 24 hours in advance of work on a signal or lighting system. Contact shall be made through the Engineer.

After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, J-boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications.

Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.

Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt Patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

In No. 2., Safety Precautions. Add the following:

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

Delete No.s 3. through 8. in their entirety and substitute the following:

3.	Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors before final lift paving.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process, shall be accomplished according to Subsection 204-3.01. Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to Subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in Subsection 703-2.07. Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

a.	Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material cleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

4.	Welding.  Complete welding according to Subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes that were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the nonreusable improvements the Contractor removed to complete the work.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements damaged or removed by the Contractor not conflicting with the work and not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment.  When the Plans include existing electrical equipment scheduled for removal or relocation, remove, and store the equipment listed in the following paragraph without damaging it.  Deliver removed equipment not scheduled for reuse to the local District Maintenance Station or place specified in the Plans or Special Provisions.  Notify the district superintendent or person specified by telephone one week before planned delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to Subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with Selected Material, Type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place.  The Department may require a credit for this waiver.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material that will be paid for as extra work under Subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to Subsection 660-3.01.4 Welding and repair the finishes according to Subsection 660-3.01.8 Repairing Damaged Finishes.

When ordered, the Engineer will pay for repairing existing damaged finishes on existing equipment according to Subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to Subsection 660-2.01.1.

Deliver the salvaged materials undamaged to the local DOT & PF Maintenance and Operations Yard.

Contact the local state Electrician one week before planned delivery.

7.	Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by Subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 VDC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test. Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

(1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to Subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

(2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

(3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

(4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

Add the following new No. 9:

9.	Regulation and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the Authority Having Jurisdiction.

660-3.02 FOUNDATIONS.  Under No. 1.  Cast-in-Place Foundations. Add the following to the first paragraph:  Locate the tops of traffic signal post and pole foundations flush with the adjacent finished walkway, shoulder, or surrounding ground.

1.	Cast-in-Place Foundations.

f.	Revise the second sentence to read:  Before placing the form or reinforcing steel cage, remove loose material to ensure the foundation rests on firm, undisturbed ground.

i.	In the second sentence delete "prior to grouting." and substitute "before attaching the skirt."

j.	In the first sentence delete "concrete pile caps" and add, "foundations." Add the following to the end of the paragraph:  Protect foundation anchor bolts from damage before installing controller cabinets.  The Engineer must approve the method used for protection.  This work does not relieve the Contractor of responsibility specified under Subsection 107-1.15.

Replace k with the following:

k.	Furnish anchor bolts that conform to ASTM F1554, the grade and supplementary Charpy V-Notch requirements listed in the Plans. Furnish each anchor bolt with three nuts and two washers.

Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten top nuts to a "snug" condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the "snug" top nuts.

After the top nuts are tightened to the correct torque, use a hydraulic wrench to rotate top nuts an additional one sixth (60) turn, while preventing the leveling nuts from turning.

Add l.

l.	Attach a #4 AWG, bare, copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled #4 AWG, bare, copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, PVC or HDPE, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2.	Pile Foundations.  Add the following new subparagraph:

g.	Use no more than one splice per foundation.  Locate the splice at least 10 feet from the top of pile.

3.	All Foundations.

d.	Replace the last sentence with the following:  Backfill the resulting hole with Selected Material, Type A and compact material as directed by the Engineer.

Replace Subsection 660-3.03 with the following:

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

1.	Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

2.	Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to Subsection 660-3.01.3, Excavating and Backfilling.

3.	Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

4.	If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 1 1/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

5.	Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

6.	Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

7.	Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self clinching nylon cable ties.

8.	Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

9.	At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to Subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

10.	Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

11.	Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 21/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

12.	Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

13.	Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

14.	When standard couplings cannot be used to join conduit components, use approved threaded unions.

15.	Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

16.	When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

17.	In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

18.	Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

19.	Install expansion fittings in conduits that cross expansion joints.

20.	Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back pull rope, at least two feet, into both ends of each conduit.

21.	The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

22.	Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables to be removed or replaced as follows:

a.	When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

b.	Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

23.	When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than a 90 degree horizontal bend to the extension.

24.	When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

25.	When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

26.	Remove the ends of abandoned conduits from junction boxes that will remain in service.

27.	When Plans call for connecting polyethylene conduit to RMC use a UL listed electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits.  Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

Replace Subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing Type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

Four (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits, that exclusively contains two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits, that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of porous backfill material that conforms to Subsection 703-2.10.  Minimum drain dimensions include an 18" depth and a length and width equal to those of the junction box it drains.  Compact the porous backfill material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker.  Conform markers to the American Public Works Association Standards including but not limited to:

	Color - red

	Material - high-density polyethylene

	Shape - round (ball like)

	Size - 4 to 5 inches in diameter

	Configuration - encapsulating an antenna tuned to the appropriate frequency for locating power

	Responsive range - up to 5 feet away from the locator device

	Environmental conditions - including extremes in temperature at the installation site

	Contain no internal power source

Acceptable marker manufacturers include:

	3M, Dynatel EMS ball marker model no. 1402-XR

	Tempo (a Textron Company), Omni Marker

	Substituted, equivalent approved equal device

660-3.05 WIRING. Change last sentence of the first paragraph to read: Run signal cabling continuously without splices from the controller cabinet to the termination lugs in the signal housing.  Do not splice conductors within cabinets, poles, signal heads, and luminaries.

Delete the second paragraph in its entirety and substitute the following:

Conditions.

Do not pull conductors into conduits until the following conditions are met:

	The prescribed clearances around conduit ends are provided,

	Crushed rock sumps are installed under junction boxes,

	Conduit ends protrude above the bottom of junction boxes within the prescribed range,

	New conduits are free of material that became lodged in them during the completion of the work,

	Reused conduits are cleaned according to Subsection 660-3.03,

	Junction boxes are set to grade, and

	Grounding bushings are installed on the ends of metallic conduits.

Add the following line to Table 660-1 under a. of No. 9.

| LOOP DETECTOR NUMBER | COLORED PAIR |
| --- | --- |
| Usually a spare pair | Orange and Black |

Delete subparagraph 11 and 12 and replace with the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 VAC operation, feature fill, and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced, it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 VAC operation and direct burial.

Provide reusable four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full 1/4 inch of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is noncorrosive to copper, and does not support fungi or mold growth.

Add the following No. 18, 19, and 20:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductors to 5 feet.

20.	Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

Replace Subsection 660-3.06 with the following:

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements:  Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size #8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than #8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to a #8 AWG and eyelet spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the #4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the handhole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the handhole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a 3/4 inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES.

In the 3rd subparagraph revise the first sentence to read: At the time the controller assembly is delivered submit the following for each assembly:  and add the following to the last sentence (1 paper copy and 1 electronic copy in Adobe pdf format)

In the 4th subparagraph replace "3.5 inch floppy" with "compact"

Delete 1. Shop Tests. Replace with the following:

1.	Shop Tests.  The Controller Assembly manufacturer shall conduct a pretest of the cabinet and controller assembly. The pretest includes but is not limited to:

a.	Ensure the cabinet is free of paint scratches, dents, sharp edges, and other physical defect.

b.	Ensure cabinet hinges, heater, ventilation system, lighting, and door locking mechanism function properly.

c.	Ensure that there are no shorts between AC+, AC-, and GND anywhere in the cabinet.

d.	Check that there is no continuity between AC+ and DC+.

e.	Check for continuity between any green wire connection point and GND.

f.	Ensure devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly.  Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of; flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation and, proper police & auxiliary panel operation.

Upon completing the final test the cabinet shall be run, "burned in," under full loads for a period of not less than 48 hours with a test timing plan in effect which utilizes full cabinet phases and functionality.

In the course of testing, a component found to function incorrectly or exhibit physical damage must be replaced with an equivalent new component before delivery.  Should the cabinet fail during burn in, the cause of the failure must be remedied and the test restarted with another 48 hours of burn in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pretest, final test, and burn in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note defects found and the remedial action taken.  Further, the certification shall state the assembly conforms to the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements.  Submit the certification letter and copies of the test results to the Engineer.

The work required in this subsection is subsidiary to the associated traffic signal system under Pay Item 660(1X-X) Traffic Signal System Complete.

Replace Subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure handhole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces that secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads "out of service" and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts as described in Subsection 660-3.02.1k.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

3.	Vehicular Signal Head Installation.  With two piece mast arms, do not install signal heads within 12 inches on either side of the slip type field splice.

Attach each side mounted terminal compartment with two 1/2" x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on the Traffic Signal Hardware Detail Sheet in the Plans.  Install the vertical pipe members plumb.

When installing 5 sections vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

| TABLE 660-2 |  |
| --- | --- |
| THROUGH PHASE SIGNAL FACE AIMING POINTS |  |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

4.	Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two 1/2" x 13 bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install R10-3E (R or L) push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

Replace Subsection 660-3.09 with the following:

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the Contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If existing lighting systems are not kept fully operational as specified herein, the Engineer will reduce the payments under Pay Item 660(22) Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the Crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 15.0 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 18.0 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20 degrees, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

a.	With two or more through lanes, center one signal head over each lane.

b.	With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

c.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in Subsection 660-3.08 Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and No. 6.  Salvaging or Reusing Electrical Equipment, found in Subsection 660-3.01.  Remove other materials used in the temporary systems from the project.

Add the following new subsection:

660-3.16 TRAFFIC SIGNAL MODIFICATIONS.  Required work is detailed in the Plan sheets and notes and the following.  Work related to the Traffic Signal Communications System will be paid for separately.

The Contractor will have 10 hours to "changeover" the new controller assembly. Changeover includes but is not limited to: removing the existing controller assembly, replacing with new controller assembly, landing new and existing wires, programming the new controller unit, and bringing the signal back to full functionality.  The 10 hour window will only occur on the days Monday through Thursday at a time determined by the Engineer.  The Contractor will be assessed a Traffic Price Adjustment for an unauthorized lane closure according to Subsection 643-3.06.

Traffic control during the changeover will be paid for under section 643 Pay Items.  At a minimum, traffic control will include the following:

	A portable changeable message board in advance of each approach with the message "Traffic Signal Work, New Traffic Pattern Ahead, from 00:00 AM/PM mm/dd/yy to 00:00 AM/PM mm/dd/yy

	A flagger for each approach

Traffic signal modifications are subject to the full Standard Specification for Highway Construction, the Special Provisions and the following:

1.	Traffic Controller Cabinet: When a new traffic controller cabinet is called for, ensure legible labeling of all cabinet cables including but not limited to; control, loop, EVP, UPS, interconnect, and telephone. Label loops and signal heads individually.

2.	Traffic Signal Heads:  When new traffic signal heads are required, provide with new LED units and new mounting hardware. If new heads are not called for, replace any missing visors or backplates subsidiary to the Traffic Signal Modification Pay Item.

When replacing traffic signal or pedestrian indications conform to Subsections 740-2.14 and 2.15 and maintain brand consistency throughout intersection. When new heads are provided aim heads according to Table 660-2.

3.	Loops: When shown in the plans, replace inductive loops including homerun cable and required splice. Loop tests are required per Section 660-3.01.7.

4.	Conduits: Unless new conduits are called for reuse existing conduits.  When new conductors are being added to existing conduits, conform to sections 660-3.03, 3.05, and 3.06.

5.	EVP Components: When called for in the plans provide EVP components including all cables and mounting hardware. Ensure proper operation of EVP system.

6.	UPS: When called for in the plans provide fully function UPS system. If no separate UPS item exist, the UPS will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

7.	Load Center: When called for in the plans provide fully functioning Load Center. If no separate load center item exists, the load center will be paid for subsidiary to the Traffic Signal Modifications Pay Item.

8.	Conductors: Reuse existing conductors except where the plans call for new conductors.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the Palmer Maintenance & Operations station within 72 hours of removal. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Pay Item 660(14A) Temporary Electrolier.  By each electrolier and foundation furnished, installed, and maintained as directed by the Engineer.

Pay Item 660(22) Illumination Price Adjustment.  By the mile of roadway with all or part of the existing illumination systems inoperative.   A divided roadway is considered one roadway.  Ramps are considered a separate roadway.  The Engineer will measure each unlit section less than one mile long as one mile.

660-5.01 BASIS OF PAYMENT.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

(1)	General construction requirements,

(2)	Bonding and grounding,

(3)	Bored Casings,

(4)	Completing tests,

(5)	Conductors,

(6)	Conduit,

(7)	Dewatering excavations,

(8)	Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

(9)	Foundations including concrete to complete foundations,

(10)	J-boxes including adjustment to final grade,

(11)	Labeling conductors,

(12)	Maintaining temporary and existing electrical systems,

(13)	Minor routing changes directed by the Engineer,

(14)	Preparing as-builts,

(15)	Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

(16)	Removing, repairing and replacing improvements,

(17)	Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

(18)	Repairing damage to finishes on new equipment,

(19)	Salvaging reusable equipment and materials and delivering to the Palmer Maintenance and Operations station including but not limited to existing signal structures,

(20)	Wiring.

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system.

Pay Item 660(3) Highway Lighting System Complete.

1.	Lighting structures.

Pay Item 660(14A) Temporary Electrolier.

1.	Work to have plans and materials approved.

2.	Temporary electrolier including the structures, foundations, and load centers (as needed) and their removal.  Moving the electroliers, assembly and operational installation, removing and replacing, and installing conductors (in conduit or direct bury only).  Furnishing and installing temporary electrical load centers when existing load centers are not available for use.

3.	Temporary electrolier will be paid on a contingent sum basis at the unit price of $2400/each.  The Engineer does not require a change order/directive for this Pay Item.

Pay Item 660(17) Traffic Signal Modifications at Palmer Wasilla Highway.		Includes full compensation for modifying the existing signal system to conform with the plans.

Pay Item 660(22) Illumination Price Adjustment.  Each day the existing illumination system(s) is inoperative, partially or completely, the Engineer will deduct $1275 per mile from the total value of the Contract.  A mile is measured as noted in 660-4.01 under Pay Item 660(22) Illumination Price Adjustment.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

660(3)		Highway Lighting System Complete		Lump Sum

660(14A)		Temporary Electrolier		Contingent Sum

660(17)		Traffic Signal Modifications at Palmer Wasilla Highway		Lump Sum

660(22)		Illumination Price Adjustment		Contingent Sum

CR660-032411

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-1.01 DESCRIPTION.

Add the following:  Furnish and install load center assembly Type 1A with an integral uninterruptible power supply (secondary power source) to power intersection traffic and pedestrian signals (no lighting) and control equipment during interruptions to the utility power (primary power source).

Replace the second paragraph and load center type list with the following:

Use load centers of the following types as shown on the load center detail sheets:

Type 1:	Pad mounted with underground service (large)

Type 1A:	Pad mounted with underground service (small)

Type 1A with UPS:	Pad mounted with underground service (large)

Type 2:	Post mounted with underground service

Type 3:	Pole mounted with overhead service

Add the following Subsections 661-1.02 Acronyms, 661-1.03 Definitions:

661-1.02 ACRONYMS.

BBS	Battery Backup System

LC	Load Center

LCD	Liquid Crystal Display

LED	Light Emitting Diode

LC/UPS	Load Center with Integral Uninterruptible Power Supply

MBPS	Power Transfer Switch

MMU	Malfunction Management Unit

PLC	Powerline Communications

PTS	Power Transfer Switch

THD	Total Harmonic Distortion

UPS	Uninterruptible Power Supply

661-1.03 DEFINITIONS.

BUCK-BOOST.  Switch-mode voltage regulator in which voltage can be above or below the input voltage.

661-2.01 MATERIALS.  Add the following:

Anchor Bolts	Section 740-2.02

Load Center.  Replace the 1st paragraph with the following:

NEMA 3R enclosure constructed of .125” thick aluminum, with no external screws, bolts, or nuts.

Add the following:

1.	Load Center with Integral Uninterruptible Power Supply (LC/UPS).

Design, fabricate, deliver, and install as specified in the Specifications and Plans.

a.	Design of LC/UPS

Design and manufacture for outdoor applications and the environment specific to the project location.

The UPS shall be designed to provide for efficient fabrication and assembly using standard, readily available industry components facilitating the current project requirements.  The design shall provide for future quick replacement of the complete system or the individual components.  The design shall allow the maintenance department to quickly acquire a replacement UPS or replacement parts and personnel to easily remove the existing UPS and install the new UPS or UPS parts as may be needed (complete turnkey system with all necessary hardware).  Special tools shall not be required to install the UPS.

The design shall specifically include a shelf-mount, rack-mount, swing-tray mount, or combination thereof.  The UPS and PTS units individually shall not exceed 5.25” in height.  If swing-trays are used, a minimum of 6 bolts/fasteners shall be used to secure the tray to the cabinet rack.

b.	Submit.

Submit shop drawings, equipment technical specifications, and certifications for review and approval.  Do not begin manufacture of the LC/UPS prior to submitting and receiving approval of shop drawings and required certifications for the system assembly, the individual equipment pieces, components, and hardware.  Provide documentation confirming delivery dates of the individual pieces of equipment and overall system in-place completion date satisfying the project construction schedule.

c.	Manufacturers.

(1)	Meyers Power Products, Inc.

LC/UPS:  Power Model MEUG35-PB Metered/Unmetered with MP2000 UPS

Address:

725 E. Harrison Street

Corona, CA 92879

Ph:  (951) 520 - 1900

(2)	Or equal:

Manufacturers satisfying the requirements of the Plans, Specifications and Contractual requirements for the assembled system, including delivery, quality and timeliness of installation and responsive remote and onsite service, shall submit, as a substitution, for review and approval.

d.	UPS Run Time Capacity.

Power intersection LED traffic, pedestrian signals, and control equipment for the consecutive time periods noted below: (lighting and traffic controller auxiliary circuits are not included)

| RUN TIME CAPACITY |  |
| --- | --- |
| Operation Mode | Continuous Uninterruptible Operation Time* |
| Normal | 2 Hours |
| Flash | 2 Hours |
| Total (Normal + Flash) | 4 hours |

*Continuous uninterruptible operation time at 77 °F (25 °C) at load 875 W.

e.	Operation.

The transfer from utility power to the UPS shall not interfere with the normal operation of the traffic controller, MMU and other peripheral devices within the traffic controller assembly.

The MBPS shall be rated at 240 VAC, 40 Amps minimum.  The MBPS shall allow replacement of the UPS without interrupting power to the intersection. The MBPS and PTS shall be separate units.  Without interrupting power to the intersection, the MBPS shall permit the replacement of the PTS, and the MBPS and PTS shall each permit replacement of the UPS.

The UPS shall use a temperature compensated battery charging system. The charging system shall compensate over a range of 2.5 to 4 mV / °C / Cell and be rated 10 Amps at 48 VDC. Batteries shall not be charged when battery temperature exceeds 122 °F ± 5.4 °F (50 °C ± 3 °C). The temperature sensor shall be external to the UPS unit and supplied with 9' - 10" of wire.

The UPS shall automatically and continually monitor and display the current percent of battery power available for use.  A "Battery Not Connected" alarm shall be issued if battery power is not present. When utilizing battery power, the UPS output voltage shall be between 110 VAC and 125 VAC, pure sine wave output with THD < 3% at 60 Hz +/- 3 Hz.

The UPS shall provide the power beyond the temperature that would be field programmable for an external fan located in the same or in a separate battery cabinet. The temperature setting shall be adjustable locally and remotely.  The temperature range shall be from +68 °F to +131 °F (+20 °C to +55 °C) in 1 degree F increment.

In the event of UPS failure, battery failure, or complete battery discharge, the PTS shall revert to the utility or line mode (in a de-energized state) where utility power is supplying the cabinet.

f.	Components:

The LC/UPS shall include all equipment, hardware, foundation and foundation materials, interconnecting wiring and other materials for a complete operable LC/UPS inclusive of materials and performance requirements specified herein, but not limited to:

(1)	UPS

(2)	UPS Controller Unit

(a)	Re-settable Inverter Event Counter

(b)	Cumulative Inverter Timer

(c)	Event log, Time and Dated (stores the last 100 events, minimum)

(d)	Self-Test (programmable in 1-minute increments from 1 min. to 255 min.)

(e)	Low Battery Alarm (programmable, adjustable in increments of .25 VDC)

(f)	Buck-Boost Mode (UPS shall be capable of Buck-Boost 10% ±)

(3)	PTS (activated during Buck-Boost operations; transfer times 10 milliseconds)

(4)	MBPS (non-electrical)

(5)	Batteries and Battery Enclosure

(6)	Battery Heater Mats

(7)	Cabinets and Enclosures

(8)	External Fan

g.	UPS Access and Password Protection.

	Provide local and remote access.

	Provide the UPS with a default password.

Access:

(1)	Local – provide an LCD display screen and touch pad as part of the UPS

(2)	Remote

(a)	RS232 interface

(b)	USB interface

Local and remote access shall provide same access use.

User:

(1)	The “User” includes the Department Traffic Engineers and Maintenance Personnel.

(2)	The User shall be able to monitor the following at the LC/UPS cabinet (locally) and remotely.

Use:

(1)	Provide the Department with the default password and administrative authority to add/change password protection.  Make the procedure intuitive and direct.

(2)	Control, programming, maintenance, and inquiry (view and adjust) including but not limited to:

Monitor:

(a)	Time,

(b)	Date,

(c)	Current battery charge status,

(d)	Input/output voltages,

(e)	Power output,

(f)	Battery temperature,

(g)	Field programmable relay settings

Current status shall be indicated by LED lights:

(a)	Green – Flashing for battery back-up mode

(b)	Green – Steady ON for normal line mode operation

(c)	Red – Flashing for ALARM conditions

(d)	Red – Steady ON for FAULT conditions

Maintenance Controls - password protect:

(a)	UPS Inverter ON/OF,

(b)	Battery Test,

(c)	Event Log (Retrieving, viewing and printing in plain English),

(d)	Changing Default Settings

Other Settings:

(a)	Temperature Settings,

(b)	Re-Settable Inverter Event Counter,

(c)	Cumulative Inverter Timer,

(d)	Self-Test,

(e)	Low Battery Alarm

(3)	Upload firmware software updates of the non-volatile, read-only memory type.

h.	Specifications.

(1)	Environmental:

The operating temperature for the (UPS), (PTS) and (MBPS) shall be -34.6 °F to 165.2 °F

(-37 °C to +74 °C).

(2)	UPS Input/Output:

| UPS SPECIFICATIONS |  |
| --- | --- |
| Input Specifications |  |
| Nominal Input Voltage | 120 VAC, Single Phase |
| Input Voltage Range | 120 VAC ± 25% |
| Input Frequency | 60 Hz ± 5% |
| Output Specifications |  |
| Nominal Output Voltage | 120 VAC, Single Phase |
| Power Rating* | 2000 VA (1500 Watts) |
| Output Frequency | 60 Hz ± 5% |
| Voltage Wave Form | Sine Wave, THD < 3% |
| Efficiency (nominal) | 95 – 97% |

*The UPS power rating of 2000 VA / 1500 Watts shall be with a minimum inverter efficiency of 80%.

(3)	Loss/Restoration of Utility Power:

When the utility line voltage is outside the High and Low Limits (100 & 130 VAC respectively set as defaults), the UPS shall transfer the load to battery power. The UPS shall return to line mode when the utility power has been restored to above 105 VAC or below 125 VAC; or the UPS shall return to line mode when the utility power is back to nominal for more than 30 seconds (the line qualification time).  The line qualification time shall be adjustable to 3, 10 or 30 seconds.

The maximum transfer time allowed, from disruption of normal utility line voltage to stabilized UPS line voltage from batteries, shall be 65 milliseconds. The same maximum allowable transfer time shall also apply when switching from UPS line voltage to utility line voltage.

(4)	Battery(s):

(a)	Batteries as part of the UPS provide the power.

Individual batteries shall be rated at 105 Amp-Hour minimum. Batteries shall be 12 VDC type and shall be easily replaced and commercially available off the shelf. The battery system used in the UPS shall consist of 4 batteries and shall be of a voltage not to exceed 60 VDC. Batteries shall be provided with quick disconnect terminals and a polarized - keyed battery cable for easy field installation.

Batteries shall be deep cycle, sealed prismatic lead-calcium based AGMNRLA (Absorbed Glass Mat/Valve Regulated Lead Acid) batteries - able to withstand extreme temperature. Batteries shall be certified to operate over a temperature range -4 °F to 165.2 °F (-20 °C to +74 °C).  The batteries shall be provided with appropriate interconnect wiring and a corrosion-resistant stationary or swing-out mounting tray and/or brackets appropriate for the cabinet into which they will be installed as specified in Subsection 661-2.01.1(a) Design of LC/UPS.

Batteries shall indicate maximum recharge data and recharging cycles. Recharge time for the battery from protective low cutoff to 80% or more of full battery charge capacity, shall not exceed twenty (20) hours.

(b)	Battery Compartment:

The battery cabinet shall be vented through the use of louvered vents, filter, and one thermostatically controlled fan operated from the UPS. The fan will automatically turn ON at the temperature programmed into the UPS.

External battery compartments may be used to satisfy environmental and physical requirements.  When submitting shop drawings, material and equipment submittals, request in writing and demonstrate graphically the need for an external compartment(s).

(c)	Back-Feed and Other Protections:

The UPS shall be equipped to prevent a malfunction feedback to the cabinet or from feeding back to the utility service per UL 1778, Section 48 "Back-Feed Protection Test". The upstream back-feed voltage from the UPS shall be less than 1 VAC for the protection of persons accessing the equipment.

The UPS shall have lightning surge protection compliant with IEEE/ANSI C.62.41 for 2000 VAC.

(5)	Relay Contacts:

The UPS shall provide the user with 6 sets of fully programmable, relay contacts of type NO/NC, panel-mounted, potential free and rated 1 Amp, 120 VAC and labeled C1 through C6. Each relay's setting shall be programmable to activate under conditions through local access or remote access.  The minimum number of relay settings is outlined below.

Independently configure relay contacts C1 through C6 to activate under the following conditions:

(a)	ON BATTERY - relay activates when BBS switches to battery power.

(b)	LOW BATTERY - relay activates when batteries have reached a specified level of remaining useful capacity while on battery power. The specified level shall be adjustable from 0 to 100%.

(c)	TIMER- relay activates after being on battery power for a specified amount of time. The specified time shall be adjustable from 0 to 8 hours.

(d)	ALARM - relay activates after a specific or general alarm is detected. These alarm conditions include:

	Line frequency

	Low output voltage

	No temperature probe

	Overload

	Batteries not connected

	High temperature

	Low temperature

The relay shall be programmed to activate when any of these alarm conditions occur, or when a specified condition occurs.

(e)	FAULT- relay activates after a specific or general fault is detected. These fault conditions include:

	Short circuit

	Low battery voltage

	High battery voltage

	High internal temperature

	Overload

The relay shall be programmed to activate when any of these fault conditions occur, or when a specific condition occurs.

(f)	OFF- relay is disabled and shall not activate under any condition.

(6)	Default Relay Settings:

(a)	Relay C1 and C2 shall be set to activate whenever the UPS transfers to battery power and shall be labeled "ON BATT."

(b).	Relays C3 and C4 shall be set to activate whenever the batteries reach 40% of remaining useful capacity and shall be labeled "LOW BATT."

(c)	Relays C5 and C6 shall be set to activate whenever the UPS has been on battery power for 2 hours and shall be labeled "TIMER."

Terminal block position 19 & 20 shall be set to activate a self-test. This test confirms that a unit can transfer into and out of battery mode while supporting the output load.

(7)	Load Center for Temporary Power:

Use the following load centers for distribution of power for temporary lighting and signals including the control systems.  Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

(a)	Permanent load centers installed in their plan location.

(b)	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if approved.

(c)	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked “Suitable for use as service equipment.”

Equipment List(s) and Drawings.

Delete No. 1. and replace with the following:

1.	Materials on the Approved Products List:  The Approved Products List does not apply to the 661 Pay Items.  Provide catalog cuts of materials to the Engineer for review and approval.

Under No. 2. Change title by removing:  Materials Not on the "Approved Products List." and replace with Materials Not on the "Qualified Products List."

Add No. 3.:

3.	Materials Not Requiring Certification:  Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

Add the following materials:

Ground Rods.  Furnish one piece 3/4” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head set-screw that are suitable for direct burial and for use with copper clad ground rods.

Meters.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Photoelectric Controls.  Delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Extend screens to the top of the control units.  Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3 1/2 to 4 1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

661-3.01 CONSTRUCTION REQUIREMENTS.  Replace the 11th paragraph with the following:

Install two ground rods at least 6 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper conductor sized per the NEC, 6 AWG minimum.  Bond non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Replace the 12th paragraph with the following:

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body.  Fabricate the conduit at least 3 ft long and locate the photoelectric control 1 ft above the top of the load center.  Mount the photoelectric control adapter on the Type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Add the following:

New Load Centers Type 1A and Type 1A with UPS.  Coordinate with existing and or new service utilities.

661-3.02 CONTRACTOR’S WARRANTY.

Load Center Type 1A with UPS (LC/UPS)

The period of performance for this warranty shall be two (2) years from the time the Department assumes maintenance responsibilities.  The price for this warranty will be included in the bid price for the LC/UPS assembly.

The LC/UPS system, all equipment, components, hardware, accessories, factory and field workmanship shall be warranted against failure from normal usage during the first two years of service from the time the Department assumes maintenance responsibilities.  Manufacturer warranties, guarantees, and instruction sheets and all parts used in the work shall be delivered to the Engineer before the Department assumes maintenance responsibilities.  Where repairs cannot be made via telephone support or modem the Contractor shall respond at the site to service or repair the malfunctioning equipment within two (2) weeks of the initial notification of the malfunction.  All materials and equipment shall be repaired or replaced at the Manufacturer’s expense including labor to complete the repair and an onsite representative to inspect and certify the repaired LC/UPS meets the requirements of the original specifications using original equipment manufacturer (OEM) parts, and equipment.  All expenses associated with the repair shall be included in the Manufacturer’s Warranty.

The warranty period will stop at the time of the failure.  The Manufacturer shall warrant the repairs as part of the original warranty.  At the completion of the repairs, the Manufacturer shall supply the Department Traffic Engineer with additional equipment and part warranties, guarantees, and instruction sheets as applicable to the repairs as required for the original equipment and work.  The Manufacturer will supply a letter certifying the repairs satisfy the specifications for the original work.  The remaining time of the warranty, the original warranty period less the time passed from the date established as the warranty start date, will begin after the repair is complete and the Department Traffic Engineer receives the repair certification letter.

661-5.01 BASIS OF PAYMENT.  Add the following:

The following work is subsidiary to 661 Pay Items:

	All necessary hardware for mounting (shelf angles, rack, shelving, harness, etc.).

	Removing existing load centers being replaced with new load centers, their foundations, and ground rods.

	Payment of fees required by the local authority for electrical inspection(s) and the costs of correcting the deficiencies noted during the inspection(s).

	All work including, but not limited to, contacting and coordinating with the utilities for service; the utility costs, fees, installation, activation, maintenance and usage payments until the Engineer provides the notice of final acceptance.

CR661-070109

Special Provisions

Add the following Section:

SECTION 662

FIBER OPTIC Signal interconnect system

662-1.01 DESCRIPTION.  Furnish and install fiber-optic signal interconnect system as shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 INSTRUCTIONS AND GUARANTEES.  One set of maintenance and repair manuals shall be included with each project installation and submitted to the Engineer.

No changes or substitutions in these requirements will be acceptable unless authorized in writing.

The supplied conduit shall carry a two-year warranty from the date of project acceptance to be free of defects. The installer shall be fully responsible for the installation of defect free conduit and for the replacement of any conduit found to be defective.

662-2.01 MATERIALS.  Submit materials for review and approval per the requirements of subsection 106-1.05, Certificates of Compliance and subsection 660-2.01, Materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a high density polyethylene (HDPE) duct system in which to pull the interconnect cable. Unless otherwise noted on the plans, install conduit per the requirements of 660-3.03, Conduit.

Unless otherwise specified on the plans, furnish 1-1/4-inch HDPE conforming to the requirements of subsection 740-2.06 Electrical Conduit and Fittings.

Furnish fittings used in the duct system such as elbows, etc., made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.

Mark underground conduits with a continuous strip of polyethylene marker tape. Marking tape shall feature the words “Buried Fiber-optic Cable” (or similar). Two strips shall be laid horizontally side by side above the conduit(s) 12 inches below final grade.  The marking tape shall be at least 6 inches wide, at least 4 mils thick and orange in color.

Keep junction boxes and ends of the conduit covered unless pulling conductors.

Use care during compaction operations to prevent damage to the junction boxes and conduits.  Remove and replace items damaged as per subsection 105-1.11.

After testing and installing the conductors, plug conduit openings with duct seal to prevent water from entering the duct system.

662-2.03 FIBER-OPTIC CABLE.  Cable shall be suitable for placement in an underground duct and shall conform to:

	United States Department of Agriculture Rural Utilities Service (RUS) standard 7 CFR 1755.900.

	Department of Agriculture Rural Electrification Administration (REA) Bulletin 1753f-601 (PE-90) dated August 4, 1994, and these specifications.

	National Electrical Code (NEC) Article 770; NFPA-National Fire Protection Agency.

	Telecommunications Industry Association/Electronic Industries Association (TIA/EIA) FOTP-Fiber-optic Test Procedures.

1.	Fibers.

a.	Fiber-optic cables shall be loose tube, all-dielectric, non-metallic slotted core with an integral dry water blocking tape and sheath designed for indoor/outdoor installation. Each cable shall be equipped with 6 kink resistant buffer tubes containing 12 optical fibers each.

b.	Each buffer tube shall have an inside diameter much larger than total diameter of the fiber it supports.

c.	Fillers are allowed in the cable to achieve cable cross-section symmetry.

d.	All cable fibers shall be usable and shall be sufficiently free of surface imperfections and inclusions to meet or exceed the optical, mechanical, and environmental requirements contained in this specification.

e.	Each optical fiber shall consist of a doped silica core surrounded by a concentric silica cladding.

f.	Fibers shall contain no factory splices.

- Fiber coating shall be a dual-layered, UV cured acrylate applied by the fiber manufacturer.  The coating shall be mechanically or chemically strippable without damaging the fiber.

- Repairs to the fiber coatings are not allowed except as determined by the State Traffic Signal personnel at designated splice locations.

- Two (polyester or aramid) yarn binders shall be applied contra-helically with sufficient tension to secure each buffer tube layer to the central strength member without crushing the buffer tubes.  The binders shall be non-hygroscopic, non-wicking, and dielectric with low shrinkage.

- Tensile strength shall be provided in the cable by a combination of high tensile strength yarns helically stranded around the cable core.  High tensile strength yarns shall be wrapped helically around the buffer tubes before the application of the outer jacket (sheath).

- Individual buffer tubes and optical fibers shall be distinguishable by means of distinct and recognizable color-coding in accordance with TIA/EIA-598-B, “Optical Fiber Cable Color Coding.”  The colors shall be stable during temperature cycling and not subject to fading or smearing onto each other or into the gel filling material.  Ensure colors do not cause fibers to stick together.

l.	Distinguish each fiber and buffer from others by means of color-coding according to the following:

| 1. Blue | 5. Slate | 9. Yellow |
| --- | --- | --- |
| 2. Orange | 6. White | 10. Violet |
| 3. Green | 7. Red | 11. Rose |
| 4. Brown | 8. Black | 12. Aqua |

- For cables containing more than 12 buffer tubes, use the color code shown above for tubes 1 through 12, and use stripes or tracers in conjunction with the standard color code for tubes 13 through 24.

2.	Jacket.

a.	The outer jacketing (sheath) material shall be applied directly over the high tensile strength yarns.  The minimum nominal jacket thickness shall be 55 mils.

- The outer jacket material shall be a medium density polyethylene (MDPE) conforming to ASTM D1248, Type II, Class C, Category 4 or 5, Grade J4.  The light absorption coefficient, when measured in accordance with ASTM D3349, shall be a minimum of 400 at a wavelength of 375 nanometers.

- The polyethylene jacket (sheath) shall contain carbon black to provide ultra-violet light protection.  The jacket material shall be fungus inert as described in ASTM G21.

- The jacket shall be free of any holes, splits, or blisters.

3.	Cable Features.

a.	The cable shall contain at least one ripcord under the sheath for easy sheath removal.

- The shipping, storage and operating temperature range of the cable shall be –400 F to +1600 F.

- The fiber-optic cable shall be capable of withstanding a maximum pulling tension of 600 lbs during installation (short-term loading) and 200 lbs (long term loading) with no damage. Tensions on the cables shall not be exceeded under any circumstances.

4.	Manufacturer.

- All Fiber-optic Cable shall be supplied by an ISO9001 certified manufacturer who is regularly engaged in the production of these specifications for fiber-optic cable.

- Fiber-optic cables shall be manufactured, tested, and prepared for shipping by one manufacturer. That manufacturer shall provide all fiber-optic cables and connectors called for on the project.

5.	Cable Markings.

- Markings shall be approximately 1/8-inch (3 mm) nominal height.

- Be clearly legible and distinguishable.

- Made at 2-foot intervals to be used as length markers.

- If initial markings fail to meet marking criteria (i.e., non-legible, incorrect spacing, spelling error, etc.), cables may be remarked to meet criteria.  Cable markings shall include:

- Cable ID

- Sequential numbers in whole foot or meter intervals to determine the length of the cable and amount remaining on the reel.

- Number of fibers

- “SM” (for Single Mode Fiber)

- “ADOT Fiber”

662-2.04 FIBER-OPTIC DROP CABLE.  Drop Cable is defined as the assembly or pigtail consisting of fiber-optic cable, connectors, protective tubing, fan-outs (if required) and all incidental materials. This is used for connectivity between a fiber trunk cable and field devices (i.e., signal controller, modems etc.).  Drop cables shall be factory assembled.  Drop cables shall be packaged individually within a plastic bag marked clearly with the manufacturer’s part number.

Cable design and installation shall meet requirements for outdoor use as described in subsection 662-2.03, Fiber-optic Cable.  Optical jackets (3mm), where used, shall be yellow for single mode fibers.  No splices are allowed within the cable length.  Non-connectorized ends shall be suitable for heat fusion splicing as described in subsection 662-3.09, Splices.

Factory testing information of each Fiber-optic Drop cable (fully assembled) shall be provided for each connector/fiber. The information shall be provided in test tags attached to individual or paired connector/fiber.

Field testing information of each Fiber-optic Drop cable (fully assembled) shall in accordance with subsection 662-3.04, Field Testing and Performance of Fibers.  Documentation of testing shall be in accordance with subsection 662-3.05, Documentation of Testing.

Fiber-optic drop cables shall be equipped with:

1.	Twelve (12) optical fibers or as specified on the plans.

2.	Fiber-optic connectors shall be:

a.	Compatible with the equipment being used for fiber strands with preset usage.

b.	In accordance with subsection 662-3.07, Connectorization.

c.	Factory installed unless otherwise allowed by Engineer.

3.	Drop Cable Fan-out Kits:

a.	heavy-duty Spider design.

b.	Install fan-out kits for all connectorized ends to build up to a 3 mm jacket.

4.	Tubing that is 900 µm or 3 mm fan-out as required by the application.

5.	Buffer tubes shall be protected by the cable sheath or fan out kit.  Exposed buffer tubes are not acceptable.

6.	Individual fiber strands shall be protected by aramid fiber tubes.

662-2.05 SINGLE-MODE OPTICAL FIBERS.  Single mode (SM) fibers utilized in the cable shall be fabricated from 100 kpsi proof stress glass and primarily composed of silica which shall provide a matched clad index of refraction (n) profile and the following physical and performance characteristics:

1.	Core Diameter: 8.3µm

2.	Maximum Attenuation: 0.4/0.25 dB/Km at 1310/1550 nm, respectively

3.	Maximum Dispersion:  < 3.2 ps/nm-km from 1285 nm to 1330 nm; < 17 ps/nm-km at 1550 nm

4.	Dispersion Wavelength (ZWD): 1301.5 to 1321.5 nm

5.	Zero Dispersion Slope:  0.092 ps/nm2-km

6.	Cladding Diameter: 125 +/- 1.0 µm

7.	Core-to-Cladding Offset (concentricity): < 0.8 µm

8.	Cladding Non-Circularity:  < 1.0 percent

9.	Fiber Coating Diameter:  245 +/- 10  µm

10.	Secondary Coating:  900 µm (as specified for breakout cable/kits, distribution cable, pigtails and patch chords only)

11.	Fiber Colored Diameter:  250 +/- 10 µm nominal

12.	Mode-Field Diameter:  9.3 +/- 0.5 µm at 1310 nm; 10.5 +/- 1 µm at 1550 nm

13.	Attenuation Uniformity:  No point discontinuity greater than 0.10 dB at either 1310nm or 1550nm

14.	Cutoff Wavelength:  <1260 nm

15.	Maximum End-to-End Attenuation per cable length 15 db.

16.	Maximum cable outside diameter: 0.5-inch

17.	Fiber Polarization Mode Dispersion (PMD): 0.5 ps/km1/2

18.	Proof Test:  All Optical fibers shall be proof tested by fiber manufacturer

19.	Attenuation at Water Peak:  The attenuation at 1383 ± 3 nm shall not exceed 2.1 dB/km.

20.	Numerical Aperture:  0.13

- 662-2.06 FIBER-OPTIC MANHOLES AND VAULTS.

- 1.	General.

- Shall be spaced at intervals no greater than 2,640 feet (1,320 feet typical).  In extreme cases where conduit has no bend as permitted by the Engineer, 5,280 feet is allowable (conduit shall be lubricated with no bends).

- Shall be installed at locations where the cumulative, conduit bends, measured from the last manhole/vault, exceed 360 degrees.

- Are not required for change in conduit installation method.

- Shall not be greater than 5 feet in depth as measured from the lid to the base.

- Covers shall meet the Heavy Duty requirements of AASHTO M306, Drainage, Sewer, Utility, and Related Castings.

- Finished grade shall be in accordance with pertinent sections of section 660-3.04, Junction Boxes. Manholes and vaults shall be located in the field to avoid drainage swales.

- When communication conduit is located in the same trench as conduit intended for other purposes (i.e., electrical circuits), manholes shall be offset a minimum of 2 feet from the conduit trench.

- A fiber-optic cable support assembly shall consist of multiple brackets, racks, and/or rails required to suspend the required surplus cabling and any splice enclosures for a single vault.  The support assemblies shall be recommended and approved by the manufacturer of the fiber-optic cable and splice enclosure. The support assembly shall be made from or coated weather resistant material such that there is no corrosion of the supports. The support assemblies shall be anchored to the existing wall using stainless steel hardware.  The fiber-optic cable support assemblies shall be incidental to the manholes/vaults.

- Void areas between openings and conduit shall be filled with a self-curing caulk that will provide a permanent, flexible rubber seal. The caulk shall be unaffected by sunlight, water, oils, mild acids, alkali, mildew and is non-flammable. The material shall provide a permanent bond between the conduit entering the manhole/vault and the polymer concrete. The caulking shall be gray in color.

- All openings in manhole/vaults shall be machined at the time of fabrication, as shown on the plans, or punch-driven at the time of placement. Openings shall be sized to facilitate conduit called for in the plan.

- Manhole/vault walls that receive only one or no conduits shall be provided with at least one 5-3/4 inch diameter knockouts for future multi-duct installation. The knockouts shall be aligned across from each other.

- 2.	Manholes.

- All openings in Type 1 manholes shall be cored or blocked out at the time of fabrication, or cored at the time of placement.  Where conduit is terminated in a manhole, the coring shall be no larger than 1/2 inch from each side of conduit.

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- Shall have a 1-inch-diameter drain hole in the base.

- Proposed manholes shall be fabricated with fiber-optic cable support assemblies, as specified herein, and as shown on the plans.  The cost to provide the fiber-optic support assemblies shall be incidental to manholes.

- Type M covers are required for manholes when installed within terrace, median or off-roadway areas.  Type K covers are required for manholes when installed in the roadway.

- 3.	Vaults.

- Shall be 30 x 48 inches and shall have an effective height of 57 inches (one 24-inch tall stackable vault and one 36-inch stackable vault with a 3-inch overlap).

- Shall be constructed on top of 12 inches of porous backfill material (subsection 703-2.10).

- The vault lid shall have a minimum design load of 15,000 pounds and shall have a permanently recessed logo that reads "TRAFFIC.” The vault lid shall have two (2) 1/2-inch x 4-inch pull slots. The lid surface shall have a coefficient of friction of 0.50 in accordance with ASTM C1028.

- The vault and vault lid shall be constructed of the polymer concrete material, "cosmopolite" and be gray in color. The vault lid shall have steel rebar or mesh added to it so the vault can be easily found with a metal detector under heavy snow. The steel rebar and mesh shall be completely enclosed within the lid such that grounding is not required. The added steel shall have 1 in of cover and not add excess weight to the lid.

- Manufacturer approved gasketing to resist water from entering the vault shall be installed between the lid and the top 24-inch-deep stackable vault.

- The vault lid shall be secured to the vault with two 3/8-inch 16 UNC stainless steel pentahead bolts in which to lock the lid and shall include the appropriate stainless steel washers.

662-3.01 CONSTRUCTION REQUIREMENTS.

1.	Fiber-optic Cable.  All splicing, testing and terminating of optical fibers shall be performed by a technician in accordance with subsection 662-3.02, Certified Fiber-optic Technician.

Physical condition of the cable upon receipt shall be recorded as outlined in subsection 662-3.05, Documentation of Testing.  Cable reel shall be inspected for nails, staples and other materials that might otherwise kink or damage the cable when unreeling.  All fibers should be tested upon receiving cable. The Contractor shall assume full responsibility of cable that is damaged if testing is not performed after receiving cable.

A detailed construction plan and installation procedure shall be submitted and approved by the Engineer before cable installation.  Cable shall only be spliced at designated splice points as specified on the plan.

Before installation, all cables shall be inspected to be free of damage (nail or staple holes, jacket tears, kinks, etc.), material defects, manufacturing defects, and dimensional non-uniformity that would:

- Interfere with the cable installation using accepted cable installation practices.

- Degrade the transmission performance and environmental resistance after installation.

- Inhibit proper connection to interfacing elements.

- Otherwise yield an inferior product.

Take all necessary precautions to protect reeled cable from possible damage while unattended. Exposed cable shall be protected at all times from vehicular and public traffic.  If cable ends are exposed and unattended, cable caps shall be taped onto cable ends to prevent ingress of moisture into the cable.

When cable is installed by pulling, a swivel and woven cable grip designed for fiber-optic cable shall be used.  Materials for lubricating shall be utilized when pulling. Cable shall be pulled in one continuous run.  Splicing is not allowed until the entire length of cable is installed.  Cable shall be pulled in multiple runs when 2 or more 90o bends occur in the run. One continuous cable pull shall not contain more than one 90o bend.

Cable installation in conduit (duct) systems shall conform to Corning Cable Systems procedure SRP-005-011, “Fiber-optic Cable Placing-Duct,” or manufacturer approved methods of jetting or pulling. Cable shall not be kinked or forced abruptly against conduit edge when pulling cable from conduit ends. Cable feed systems (reels, rollers, guide, tubes etc.) shall be used to install or retrieve cable from conduit ends in vaults, manholes, or junction boxes.

Equipment shall be provided to monitor tensile forces on long cable runs. Monitoring equipment shall measure pulling tension as it occurs and record the maximum tension incurred during the pull.

Unless cable is assisted by jetting or winching, lengthy cables requiring multiple pulls shall be coiled in a “figure-eight” pattern. Coiled cable will be staged at intermediated access points to avoid twisting of cable. The figure-eight patterns shall be approximately 15 feet in length. Cardboard shims shall be installed between cable layers at the crossover of the “figure eight” to relieve pressure on the cable.  Fiber-optic cable lengths greater than 100 ft shall not be coiled in one continuous direction.

Minimum bend radii (20 x diameter of the cable with loading, 10 x cable diameters without loading) on the cable shall not be exceeding at any time.

Temporary aerial installation methods shall be consistent with Corning Cable Systems SRP-005-010, “Fiber-optic Cable Placing-Lashed Aerial” or manufacturers approved method.

Excess fiber cable slack shall be stored in vaults and manholes on hooks in accordance with the plans.  Cable slack shall be neatly coiled around the inside perimeter of manholes and vaults and shall be supported by cable brackets.  Cable slack shall be supported as to not interfere with access into manholes and vaults.  Excess fiber cable slack shall be provided as follows:

- Approximately 100 feet per manhole and vaults containing splices.

- 65 feet per splice vault.

- 20 feet per junction box or vault not containing splices.

- 6 feet per controller cabinet.

All fiber-optic cable shall be installed with marking tape, copper wire tracer and above ground markers.

- 2.	Vaults.  Vaults shall not be placed near drainage collection areas or where vehicle traffic is anticipated.  To the extent possible, vaults shall be placed so that they are accessible by service vehicles driving close to them.

Brackets for splice enclosures shall be mounted as per vault manufacturer recommendations.  Mounting equipment for cable or splice closures shall not fully penetrate the vaults in order to prevent water intrusion.

Where applicable, conduits shall be terminated in vaults to allow for proper grounding and bonding of metallic conduit. Multi-duct conduit termination kits shall terminate at vaults inside wall (or slightly into the vaults interior) to the extent possible.

Conduit, conduit terminations, and caulking shall be allowed to fully cure as per the manufacture’s specification before backfilling vault.  Openings required to install special or directional conduit shall be sealed with manufacturer approved termination kit.

- 662-3.02 CERTIFIED FIBER-OPTIC TECHNICIAN.  The Fiber-Optic Technician shall have attended and successfully completed at least one four-day "Installation of Fiber-optic Products School." This school shall be conducted by a major manufacturer of fiber-optic products and encompasses all aspects of fiber-optic technician certification.

Employ only technicians demonstrating a minimum of two years work experience with the splicing, termination, and testing of fiber-optic cable.

The approved technician shall provide evidence of completed courses within one week before the beginning of construction. The Engineer reserves the right to revoke the approval of any technician not demonstrating the skill and knowledge to perform at accepted industry standards or to the quality required in these specifications.

- 662-3.03 TESTING AND PERFORMANCE BY MANUFACTURER.  All outdoor cable installations shall meet or exceed requirements of the Fiber-optic Test Procedure (FOTP) criteria referenced in RUS 7 CFR 1755.9 and Bulletin 1753f-601 (PE-90) and these specifications.

Following specifications shall apply to the appropriate Fiber-optic Test Procedures (FOTP):

1.	TIA-455-3-A, FOTP-3 “Procedure to Measure Temperature Cycling Effects on Optical Fibers, Optical Cable, and Other Passive Fiber Optic Components”:  The average change in attenuation at extreme operational temperatures (-400 F to +1600 F) shall not exceed 0.05 dB/km at 1,550 nm for single-mode fiber.  The magnitude of the maximum attenuation change of each individual fiber shall not be greater than 0.15 dB/km at 1,550 nm.

2.	TIA-45-82-B, FOTP-82, “Fluid Penetration Test for Fluid-Blocked Fiber-optic Cable.”  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of un-aged cable for 24 hours, no water shall leak through the open cable end.  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of aged cable of one hour, no water shall leak through the open cable end.  The aging cycle is defined as exposing the cable to 850C for 168 hours and two cycles of –400C to +700C with cable held at these temperatures for 24 hours.  At the end of this cycle, the cable will be decreased to +230C and held for 24 hours. The water penetration test is completed at the end of the 24 hours hold period.

3.	TIA/EIA-455-81-B, FOTP-81, “Compound Flow (Drip) Test for Filled Fiber-optic Cable”:  The cable shall exhibit no flow (drip or leak) of filling and/or flooding material at +650C.

4.	TIA/EIA-455-41-A, FOTP-41, “Compressive Loading Resistance of Fiber-optic Cables”:  Ten percent of the fibers shall not experience a magnitude of attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The magnitude of the attenuation change shall be within the repeatability of the measurement system for the remaining 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  No fibers shall exhibit a measurable change in attenuation after test load is removed.

5.	TIA/EIA-455-104-A, FOTP-104, “Fiber-optic Cable Cyclic Flexing Test.”  Change in attenuation shall not exceed 0.1 dB at 1550 nm for single mode fiber.  The magnitude of the attenuation change shall be within the repeatability of the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

6.	TIA/EIA-455-25-C FOTP-25, “Repeated Impact Testing of Fiber-optic Cables and Cable Assemblies.”  The magnitude of the attenuation change shall be within the repeatability of the measurement of 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

7.	TIA-455-33-A FOTP-33, “Fiber-optic Cable Tensile Loading and Bending Test.”  While subjected to a minimum load of 600 lbf, the cable sample shall be able to withstand a twist of 360 degrees in less than 3 meters of length.  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable shall not experience a measurable increase in attenuation when subjected to the rated residual tensile load, 200 lbf.

8.	TIA/EIA-455-85-A FOTP-85, “Fiber-optic Cable Twist Test”:  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The average increase in attenuation for the fibers shall be <0.40 dB at 1300 nm.  The cable jacket will exhibit no cracking or splitting under a 5x magnification after completion of test.

9.	TIA/EIA-455-181 FOTP-181, “Lightning Damage Susceptibility Test for Optic Cables with Metallic Components.”

10.	TIA/EIA-455-37-A FOTP-37, “Low or High Temperature Bend Test for Fiber-optic Cable”.

11.	TIA/EIA-455-98, FOTP-98-A, “Fiber-optic Cable External Freezing Test”.

662-3.04 FIELD TESTING AND PERFORMANCE OF FIBERS.  All testing of optical fibers shall be performed by a Certified Technician as described in subsection 662-3.02, Certified Fiber-Optic Technician.

The Contractor shall schedule the date, time, and location of any tests required by this specification with the Engineer at least 72 hours before performing the tests.  The Engineer or designee shall be present when the tests are conducted.  The Certified Technician shall demonstrate clearly how the tests are being performed and shall be made available to discuss testing strategies with the Engineer.

Tests shall be conducted using standard operating procedures as defined by the manufacturer of the test equipment.

The following tests shall be conducted after the cable has been installed, spliced, and connectorized.  Test results shall be submitted in accordance with subsection 662-3.05, Documentation of Testing.  Tests shall be performed before any permanent equipment connections.  All fibers shall be tests for continuity, events above 0.05 dB and total attenuation of the cable.  If the fiber-optic cable installed is connected to an existing fiber-optic cable, perform installation tests the installed cable and all existing fibers to which it is spliced or connected:

1.	End-to-end OTDR (Optical Time Domain Reflectometer) Testing. This test shall be conducted to identify attenuation associated with each fiber. Traces shall be provided for each operational wavelength for the type of fiber in the system to indicate attenuations and their locations.

A Certified Technician utilizing an OTDR and Optical Source/Power Meter shall conduct the tests after installation. The Technician shall conduct the test according to the standard operating procedure as defined by the manufacturer of the test equipment.

To eliminate or shift the “dead zone,” either a factory patch chord or “fiber launch box” of length greater than the dead zone shall be used.

Measurement shall be conducted for 1310 nm and 1550 nm for single mode fiber.

2.	Attenuation Test.  All fiber links shall be tested with a standard power-meter test and all attenuation shall be documented. For every fiber installed or connected to under this Contract, perform end to-end attenuation test.

For the test, use a calibrated optical source and power meter using the standard three-stage procedure.  Determine acceptable link attenuation by the cumulative value of standard losses based on length, number, and type of splices and connectors.

Provide test results of the fiber-optic cable that demonstrate the dB/km loss does not exceed +3 percent of the factory test or 1 percent of the cables published production loss.  The Engineer may elect to allow bi-directional averaging of OTDR testing due to splice loss core alignments.  Fiber-optic cable loss limits shall be in accordance with the following:

a.	No event shall exceed 0.10 dB.  If any event is above 0.10 dB, repair or replace that event location.

b.	Total dB loss of a cable fiber less events shall not exceed +3 percent of the factory test or 1 percent of the manufacturer’s published production loss at 1310 and 1550 nm.  Cable fiber loss shall not exceed Maximum Attenuation Limits as defined in subsection, “Single Mode Fiber-optic Cable.”

Cable Fiber Loss (dB)  =   Total Loss (dB)  - ∑ events (dB)

Cable Fiber Loss (dB/km) =  Cable Fiber Loss (dB)

Cable Fiber Length (km)

c.	Where total or event losses exceed these specifications, replace or repair that cable run and assume all expenses, both labor and materials. Elevated attenuation due to exceeding pulling tension during installation will require replacement of cable at the Contractor’s expense.

d.	Fusion splice losses shall not exceed 0.10 dB per fiber.  Mechanical splices, where allowed, shall not exceed 0.30 dB.

e.	Each connector, after factory assembled, shall not exceed the maximum loss of 0.50 dB (typical loss is 0.25dB) and optical return reflective loss of <-0.45dB.

f.	If event losses exceed these specifications, event locations shall be replaced or repaired without additional cost reimbursement for expenses.

g.	If total loss exceeds these specifications, Fiber-optic cable shall be replaced or repaired without reimbursement for expenses.

h.	All fibers within the cable shall be tested and proven usable in accordance with these specifications.

- 662-3.05 DOCUMENTATION OF TESTING.  Upon completion of the field test, the Contractor shall provide three copies of all documentation to the Engineer.  Except for standard bound materials, documentation shall be neatly bound in 8.5” x 11” (size A4) documentation in logical groupings.  Bindings shall be of either the 3-ring or plastic slide-ring type.  Permanently and appropriately label each such bound grouping of documentation.

Documentation from manufacturer shall include manufacturer data of cable and fiber including:

- Optical performance (OTDR) including dB/km loss measured at 1310 and 1550 nm for single mode.

- Manufacturer’s name

- Date of manufacture

- Index of Refraction

- Cable ID

- Connector losses and bandwidth/dispersion data

Documentation of field testing shall include a map. This map shall show:

- Cable part numbers

- Manufacturer

- Cable length markings

- As-built cable routing

- Location of splice points and hardware at each splice point location (see below under testing also).

Documentation shall include the information below for end-to-end testing, splice loss measurements, OTDR traces.

The documentation shall be neatly tabulated for each field test and shall include the following:

- Cable and Fiber Identification.

- Manufacturer

- Cable ID

- Fiber ID (include tube and fiber color)

- Cable Location – begin and end point

- Operator Name

- Date and Time

- Date of installation

- Fiber Count

2.	Setup Parameters.

- Wavelength

- Pulse Width (OTDR)

- Refractory index (OTDR)

- Jumper and/or Launch Box Length

- Range (OTDR)

- Scale (OTDR)

3.	Test Results.

a.	OTDR Test:

- Total Fiber Trace (mile)

- Splice Loss/Gain

- Measured Length (Cable Marking)

- Provide traces on Diskette to Engineer

- Total Length (OTDR) (mile)

- Events > 0.05 dB

- Backscatter

- End-to-End Attenuation Test:

- Length

- Number and type of splices and connectors

- Link Attenuation

Fiber-optic cable test results shall demonstrate that dB/km losses do not exceed limits in accordance with subsection, 662-3.04 Field Testing and Performance of Fibers.

- 662-3.06 PACKAGING.  Fiber-optic cables shall be shipped on wooden reels.  The diameter of the drum shall be a least 20 times the diameter of the cable.  The following information shall be either stenciled on the reel or on a weatherproof tag firmly attached to the reel or a combination of both in order to trace the manufacturing history of the cable:

- Optical Cable

- Number of Fibers

- Date cable was tested

- Non-armored

- Year of cable manufacture

- Name of cable manufacturer

- Gross weight

- Part Number

- Handling Instructions

- Arrow indicating cable wind direction

Cable data sheets shall be supplied to Engineer containing the following:

- Manufacturer Name

- Cable ID Number and fiber type

- Factory Order Number

- Cable Length

- Factory measured attenuation (each fiber)

- Index of Refraction

- Bandwidth Specification (where applicable

Sufficient cable length, in addition to the quantities shown on the plan, shall be provided for testing.  Both ends of the cable shall be available for testing.  Pack one continuous length of fiber-optic cable per reel; maximum overage shall not exceed 10 percent unless approved by The Engineer.  Compensation will not be granted for overage or excess cable needed for testing and installation methods.

Package the cable for shipping to prevent the cable from coming loose in transit.  Secure the outer and inner end of the cable.  Cover the reel with thermal wrap to protect the cable.  Apply end seals to each end of the cable to prevent moisture and from entering the cable.

Include the manufacturers test documentation with each reel. This documentation indicates the attenuation of each cable fiber in dB/km (dB/ft), measured at 1310 and 1550 nm for single mode fiber.

- 662-3.07 CONNECTORIZATION.

- 1.	Connectors.  This subsection shall consist of furnishing and installing connectors (in-line or terminated ends), attenuators as required in the plans, or as required for working fiber-optic system. All connectors shall be installed by a Certified Technician as described in this specification.

Hybrid adaptors shall not be used to connect two different connectors.  Hybrid jumpers with different connectors at each end of cable shall interface with equipment or cables with different connectors where needed.

Connectors shall be SC connectors for single mode fibers.  FC and ST connectors are allowed only where compatibility with equipment is required for fibers with a preset usage. These must be approved by the Engineer.

Connectors shall be installed with ceramic ferrules.  The fibers shall be secured within ferrule with epoxy, heat set or air dried, as specified by the manufacturer.  Machine polished mating faces shall be provided.  Install connectors per manufacturer application and recommendations, including proper termination to the outer tubing (900 micron, 3 mm fan-out) as required by the application.  Connectors shall be rated for operating temperatures of -400 F to 1600 F.  Connectors shall be factory-installed for all applications except where approved by the Engineer.

If connections are made, connectors shall be cleaned once before the first connection and once every time thereafter before reconnection. Connectors shall be cleaned according to manufacturers recommended practice.

Connector losses shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers.  Repeatability of keyed connectors shall not exceed 0.2 dB.

Boots shall be provided for durable cable strain relief.

Dust caps shall be provided and installed at all times when connector is not in use.

2.	Patch Panels.  Terminate and secure 4 fiber pairs from one buffer tube in the cable to a Gator Patch TM type drop cable located in the traffic signal controller cabinet that the fiber is shown to enter in the plans.

Ensure the fibers used throughout the system are matched correctly to allow for communications from one cabinet to the next in the system.

Ensure that the patch is compatible with the fiber optic cable/cables being terminated and color-coded to match the optical fiber color scheme.

All patch connectors shall be clearly labeled. The panel shall have a minimum of 8 SC type connectors, and shall be din rail mountable.

All installed patch panels shall include documentation regarding the identification, route, and function of each patch panel connector at that location.

Place at least one copy of this information alongside the installed equipment or in the controller cabinet door pouch.

- 662-3.08 ATTENUATORS.  Attenuators shall be provided at no extra payment to the Contractor to achieve the desirable signal loss. Attenuators shall only be installed on the receiving end closest to the originating transmission (typically closest to the Traffic Signal Management Center).

Connecting ends shall be compatible to connectors described in subsection 662-3.07, Connectorization.

662-3.09 SPLICES.  Two weeks before the start of the fiber-optic cabling installation, the Contractor shall submit the following:

- Proposed locations of the mainline spliced points for review by the Engineer.

- Proposed process to be used for splicing including procedure.

- Cleave tool and specific fusion splicer to be used.

- 1.	All Splices.

- a.	Splicing and termination of optical fibers shall be performed by a Certified Technician as described in 662-3.02 Certified Fiber-Optic Technician.

b.	Splicing shall only be allowed in areas as designated on the plans or as approved by the Engineer.

c.	Splices and stripped cable shall be housed by a fiber splice closure (FCS) in designated locations shown on the plans.

d.	Cable ends involved in splicing shall match colors of the fibers and buffer tubes to the extent possible.

e.	No stresses shall be placed on the fibers before or after the splice is completed.

f.	Splice loss shall not exceed limits as described in subsection 662-3.04, Field Testing and Performance of Fibers

g.	Fan-out kits are required for splices to multiple fibers in the buffer tubes for single mode fiber.

h.	Splices shall be located in the center of the slack cable in manholes or vaults.

2. 	End-To-End Splices.

a.	End-to-end splicing shall be performed as per manufacturer instructions for the supplied splice closure units.

b.	End-to-end fusion splicing shall be conducted for any disturbed fibers within the disturbed buffer tube(s).  Remaining buffer tube(s) that are not required for splicing shall be undisturbed and protected in the Splice Closure.

c.	End-to-end fusion splices shall be used on mainline splices for all fibers (72 fibers typical) within the fiber-optic cable where designated in the plans.

3.	Fusion Splices.

a.	Fusion splices shall be made with a portable fusion splicer, capable of AC or internal battery-powered operation.  The unit shall be able to splice fibers specified herein with 250  micrometercoating and 900 micrometer coating with little or no modification in the field.  The fusion splicer shall be capable of full battery recharge in an eight-hour charging period.

4.	Drop Fiber Splices.

a.	Drop fiber splices (6 fiber typical) and drop cables (6-fibers typical) shall be used for connectivity between a primary mainline fiber-optic cable (72-count typical) and field devices (i.e., traffic signal controller cabinet) as identified in the plans.

b.	Drop fiber splices shall consist of breaking out the required buffer tube(s) from the fiber-optic trunk cable (72-count typical) and fusion splicing the appropriate number of fibers to the fiber-optic drop cable (6 fibers typical). Remaining undisturbed fibers, if any, shall be protected in the splice tray.

- Drop fiber splice shall be performed for each device location at locations shown on the plans.  Splicing shall be performed as per Corning Cabling Systems Recommended Procedure SRP-004-013, Mid-Span Access of Fiber-optic Cable (Cable Slack Present), or an equivalent manufacturer’s 	recommended procedure approved by the Engineer.

- 662-3.10 SPLICE CLOSURES.  Fiber-optic splice closures (FSC) shall be installed in the locations on the plans at designated splice locations. Closures shall contain splice trays or organizers that contain the splices.

Before installation, the Contractor shall provide certification from the manufacturer that the splice closures conform to the specifications and test procedures.

1.	Closures.

a.	Splice closures shall be designed for use under the most severe conditions such as moisture, vibration, impact, cable stress, and flex temperature extremes. This will be demonstrated by successfully passing factory test procedures and these specifications.  The closure shall prevent the intrusion of water without the use of encapsulates.

b.	Closure re-entry and subsequent reassemble shall not require specialized tools or equipment; these operations shall not require the use of additional parts.

c.	Splice closures shall provide housing and storage for all splices, stripped cable, and undisturbed buffer tubes.  All splices enclosures shall provide protection and strain relief to optical fibers. Splice closures shall be suitable to handle straight, butt or branch splices.

d.	Splice closures requiring greater than 48 splices shall provide for the following requirements:

1)	6-inch diameter by 22-inch length.

2)	One, six-cable entry end plate.

3)	One blank end plate.

4)	All endplates shall be 3-section, pre-molded, and suitable for use with Coyote closures.

5)	Required accessories to complete splice.

6)	One future cable entry kit for each splice closure.

e.	Closures shall be provided with external valve pressurization ports.  Closure shells shall be glass-filled high-density thermoplastic that effectively withstands corrosion; high impact and freeze thaw stresses.

f.	Closure endplates shall be interchangeable with each size of closure available from the closure supplier.

g.	Where additional access is required into an existing splice closure, replace the existing endplate with an endplate suitable for the task.

h.	Splice closures shall accept up to six cables in a butt configuration, and 12 for in-line configuration without special adaptors.

i.	Closure shall contain a permanent neoprene gasket seal.

j.	All closures, including closing hardware, shall be from the same supplier.

k.	External Shrader valve pressurization port shall be supplied.

l.	The splice closure shall be designed and equipped with the necessary mounting hardware to be attached to the side of the manhole or vault, and to be suspended with sufficient clearance at each end for acceptable cable bends.

m.	All cables shall be properly dressed and affixed to rails or racks within the manhole or vault.  No cables or enclosures will be permitted to lie on the floor.

n.	Fiber-optic cables shall be restrained within the splice enclosure such that there is no discernible tensile force on the optical fiber.

o.	The splice closure shall have provisions for storing fiber splices in an orderly manner, mountings for splice organizer assemblies and space for excess or unspliced fiber.  Splice organizers shall be re-enterable and re-sealable.

p.	The closure shall be capable of accommodating a minimum of 2 splice organizer trays, which shall accept mechanical, fusion, or multi-fiber array splices.

q.	Splice closures shall contain a basket allowing fiber buffer tube storage of exposed buffer tubes. The splice case shall be UL rated.

r.	The closure shall be installed according to the manufacturer’s recommended guidelines.

2.	Splice Tray.

a.	One splice tray shall be designed to hold a minimum of 12 mechanical splices.  A second splice tray (for Fiber-optic Drop Cable splicing) shall be designed to hold a minimum of 12 fusion splices.  All other splice trays provided in the closure shall be designed to hold fusion splices of 12 (typical) up to 36 splices. Total number of splices supported shall be 96 splices.

b.	Splice trays shall allow for optical fiber storage as recommended by the manufacturer.  The splice closure shall have provisions for controlling the fiber bend radius (1.5 inches typical) to a minimum as required by the manufacturer.

662-3.11 SPLICE CLOSURES -FACTORY TESTING REQUIREMENTS.  The construction and testing of the fiber-optic splices and splice enclosures shall comply with all applicable industry standards including Electronic Industry Standards (EIA/TIA), ANSI and ASTM standards.

Splice closures shall meet the following test requirements:

1.	Compression Test.  The closure shall not deform more than 10 percent in its largest cross-sectional dimension. When 	subjected to a uniformly distributed load of 300 lbf (1335 N) at temperatures between 00F and 1000F 	(–180C 	and +380C).  The test shall be performed after stabilizing at the required temperature for a minimum of 2 hours.  It shall consist of placing an assembled closure between two flat paralleled surfaces, with the 	longest 	closure dimension parallel to the surfaces.  The weight shall be placed on the upper surface 	for a minimum of 15 minutes. The measurement shall then be taken with weight in place.

2.	Impact Test.  The assembled closure shall be capable of withstanding an impact of 21 ft-lbf (28 N-m) at 	temperatures of 100F and 1000F (-120C and 380C).  The test shall be performed after stabilizing the 	closure at the required temperature for a minimum of 2 hours.  The test fixture shall consist of a 20 lb (9 kg) cylindrical steel impacting head with a 2-inch (5 cm) 	spherical radius at the point where it contacts the closure.  It shall be dropped from a height of 12 inches (30 cm).  The closure shall not exhibit any cracks or fractures to the housing that would preclude it from passing the water immersion test.  There shall be no permanent deformation to the original diameter or characteristic vertical dimension by more than 5 percent.

3.	Cable Gripping and Sealing Testing.  The cable gripping and sealing hardware shall not cause an increase in fiber attenuation in excess of 0.05 dB/fiber @ 1550 nm when attached to the cables and the closure assembly. The test shall consist of measurements from six fibers, from each buffer tube or channel, or randomly 	selected in the case of a single fiber bundle.  The measurements shall be taken from the test fibers, before and after assembly. This will determine the effects of the cable gripping and sealing hardware on the optical transmission of the fibers.

4.	Vibrations Test. The fiber splice organizers and splice retaining hardware shall be tested per EIA standard FOTP-11, 	Test condition I. The individual fibers shall not show an increase in attenuation in excess of 0.1 dB/fiber.

5.	Water Immersion Test.  The closure shall be capable of preventing a 10-ft (3-meter) waterhead from intruding into the splice 	compartment for a period of 7 days.  Testing of splice closure is to be accomplished by the placing the closure into a pressure vessel and filling the vessel with tap water to cover the closure.  Apply continuous pressure to the vessel and maintain a hydrostatic head equivalent to 10 ft (3 m) on the closure and cable.  This process shall be continued for 7 days.  Remove the closure and open to check for the presence of water.  Any intrusion of water into the compartment containing the splices constitutes a failure.

6.	Certification.  It is the responsibility of the Contractor to insure that all of the above tests have been performed by either the manufacturer, or an independent testing laboratory, and the appropriate documentation has 	been submitted to the Engineer.  Manufacturer certification is necessary for the model of closure supplied. It is not necessary to subject each supplied closure to the actual tests described herein.

662-3.12 WARRANTY AND MAINTENANCE.  Manufacturer’s support (customary warranties) period shall be provided for all equipment and materials furnished and installed as part of the fiber-optic system. This includes end equipment such as modems, panels, switches and etc. Manufacturer’s and Contractor’s warranties or guarantees shall be continuous throughout their intended duration and be stated that they are subject to transfer.

662-4.01 METHOD OF MEASUREMENT.  The Engineer will measure all work required to install a complete signal interconnect system as lump sum.

662-5.01 BASIS OF PAYMENT.  The contract lump sum price for 662(3) pay item(s) shall be full compensation for furnishing all work and materials required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under item 660(1), Traffic Signal System Complete.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

662(3)	Signal Interconnect System Complete - Fiber	Lump Sum

51132-041211

Special Provisions

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDERS

669-1.01 DESCRIPTION.  Furnish and install two permanent traffic detection and recording stations for the automated collection of traffic data.  Add new equipment as shown in the Plans.

Highway Data Section (HDS).  220 E. 42nd Ave., Anchorage, (907) 269-0876.

Traffic Data Site (TDS).

TDS H1 and H2:  Automated Traffic Recorder (ATR) System.

ATR Type:  Automated Vehicle Detection (AVD).

a.	AVD:  Inductive loops sensors connect to a traffic counter. In each traffic lane, buried beneath the pavement, is a single loop.  Lead wires run in underground conduit from the sensors to a Type CBA1 cabinet located at the side of the road.  Inside the cabinet, the lead wires connect to a portable, battery-operated traffic counter.  Through the inductive loop, the traffic counter detects the presence of passing vehicles.  The traffic counter records and stores the data for each passing vehicle for later retrieval.

Closely conform to the location and layout of conduit runs shown in the Plans.  Do not deviate from the locations and layout without direction from the Engineer.

General descriptions of the Automated Traffic Recorders are as follows:

TDS H1:  Trunk Road, Station “C” 204+50:

Four lane vehicle sensor array with one Presence Loop per lane, 75 ft right offset, CBA1 cabinet without electrical and/or telephone service.

Furnish and install the CBA1 cabinet, Junction Boxes, Conduit, wire, and loop presence sensors as shown in the Plans.

TDS H2:  Trunk Road, Station 271+00:

Two lane vehicle sensor array with one Presence Loop per lane, 60 ft left offset, CBA1 cabinet without electrical and/or telephone service.

Furnish and install the CBA1 cabinet, Junction Boxes, Conduit, wire, and loop presence sensors as shown in the Plans.

669-1.02 REGULATIONS AND CODE.  Materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

Electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01 MATERIALS.

1.	Wiring.  Subsection 740-2.05, Conductors.  Use single wire conductors and cables that have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer’s name or trademark, insulation type-letter designation, conductor size, voltage rating and the number of conductors if a cable.  Home run label all wires and cables in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the Plans.

2.	Conduit.  Subsection 740-2.06, Electrical Conduit and Fittings.  Use galvanized rigid metal for conduits, except for PVC conduit forming the inductive loops.  Provide grounding bushings with plastic-sleeves to minimize the potential for insulation damage during wire pulls.

3.	Junction Boxes.  Subsection 660-3.04, Junction Boxes.  Label the covers of all junction boxes used for loops or sensor wires “TRAFFIC.”  Label the covers of all junction boxes used to provide electrical service to ATR installations “ELECTRIC.”  Keep junction boxes for 120V/240V electrical service completely separate from junction boxes containing loop or sensor wiring.

4.	Presence Loops.  Use UL listed IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG conductors for detector presence loops.

Use twisted pairs of 18 AWG stranded tinned copper wire for multiple pair loop lead-in cable.  Each twisted pair shall have its own 20 AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire.  Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

5.	Cabinets, Style CBA1.  Use cabinets that meet or exceed a NEMA Type 3R rating and are third party certified assemblies.  Meet the following:

a.	Construction:  Construct the cabinet and hinged door from 5052-H32 or better unpainted sheet aluminum alloy with a minimum thickness of 1/8 inch and a smooth grain finish on the exterior.  Make welds neatly formed and free of cracks, blowholes and other irregularities.  Make inside and outside edges free of burrs or similar.  Slope the roof of the cabinet sufficient to prevent water accumulation on, and unimpeded flow from the surface.  Make the high side the door side.

b.	Door:  Make the door opening double flanged on four sides designed to prevent dirt and liquids from entering the enclosure when the door is opened.  Provide door restraint, when open and unattended, to prevent door movement in windy conditions.  Make the door at least 80% of the cabinet frontal surface area with hinges on the right side when facing the cabinet.  Provide a weather tight seal between the door and the cabinet.  Use gasket material meeting the physical properties found in UL508 table 21.1.  The hinge will be continuous and made of stainless steel or .087 inch thick minimum.  Securely anchor the hinge to the door and cabinet either welding the hinge in place for a quarter of its length or bolting in place.  The bolts will be stainless steel with nonslip nuts and neoprene washers to prevent water from passing from the outside of the enclosure to the inside.

c.	Latch/lock:  Use a 3 point draw roller type latching mechanism.  Use stainless steel or cadmium plated, Type II, Class 1, or better center catch and pushrods.  Use nylon rollers with a minimum diameter of 3/4 inch.  Furnish a stainless steel operating handle with a 3/4 inch shank.  Provide a Corbin #2 keyed lock matching existing HDS cabinets with two keys for each lock.

d.	Terminal Blocks.  Use terminal blocks with nickel, silver, or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600 VAC at 20A, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.  Label and terminate conductors at a terminal block.

6.	Pavement.  With the Engineer’s approval, use the following materials:

a.	Asphalt Pavement:  Section 401, Hot Mix Asphalt, and Surface Treatments.

HMA, Type II, Class A.

669-3.01 CONSTRUCTION REQUIREMENTS.

1.	Wiring.  Subsection 660-3.05 Wiring, and as indicated in the Plans.

a.	Termination:  Terminate unused pairs at junction boxes within splices.  Terminate unused pairs in terminal blocks at cabinets.

b.	Relief:  Provide at least 2 ft of slack cable for wiring in each junction box and at least 6 ft of slack cable available in the equipment cabinet before the terminal block.

c.	Labeling:  Label wiring in junction boxes and at terminal blocks.

2.	Conduit.  Subsection 660-3.03 Conduit, and as indicated in the Plans.

a.	Pull Chords:  Leave nylon pull cords in all conduits larger than 1 inch and in spare conduits.

b.	Bushings:  Install the plastic or plastic-sleeved bushings before wire pulls are performed.

3.	Junction Boxes.  Subsection 660-3.04 Junction Boxes, and as indicated in the Plans.

a.	Voltage Limitation:  Do not place wiring or conduits carrying wiring from systems at 24V or greater in Junction boxes used for ATR installations.

4.	Terminal Blocks.

a.	Terminal Block Placement:  Mount terminal blocks within cabinets so that terminals are easily accessible from the front of the cabinet.

b.	Labeling:  Clearly label terminal blocks and wire pairs on the block.

c.	Termination:  Terminate and solder conductors, including unused spares to “spade” type terminal lugs.

5.	Presence Loops.

a.	Placement Design Adherence:  Closely conform to the location and layout of conduit runs shown in the Plans.  Do not deviate from the location without direction from the Engineer.

b.	Presence Loop Dimensions:  Unless otherwise noted, form presence loops using four turns of wire, making a 6 ft x 6 ft square with a tolerance of ± 1 inch.

c.	Presence Loop Dimensions for On-Ramps and Off-Ramps:  Form presence loops in On-Ramps and Off-Ramps using four turns of wire, making a rectangular 8 ft wide and 6 inches long with a tolerance of ± 1 inch.

d.	Lead-in Conduit:  Place lead-in conduits straight and perpendicular to the centerline of the road from the edge of pavement to the presence loops.

e.	Presence Loop Alignment: Center presence detector loops in the traffic lane with a tolerance of ± 1 inch.

f.	Presence Loops in Asphalt:

I.	Loop Placement:  Locate presence loops 16 ft from leading edge of loop to leading edge loop unless otherwise noted on the Plans with a tolerance of ± 1 inch.  Align presence loops in adjacent lanes within a tolerance of ± 1 inch.

II.	Compaction Tests:  Compaction test requirements are at the discretion of the Engineer.

6.	Cabinets.

a.	Cabinet Placement and Orientation:  Install cabinets out of the Clear Zone with the doors facing away from the road.

b.	Conduit Entry:  Install conduit entries for above-ground enclosure through the bottom of the enclosure.  Do not install conduit runs through the sides or top of an above-ground enclosure.

c.	Style CBA1 Cabinets.

1)	Mounting:  Mount style CBA1 cabinets on 2.5 inch square galvanized perforated steel tube and support with reinforced concrete foundations as shown on the Plans.

2)	Terminal Blocks:  Terminal blocks in CBA1 cabinets shall be mounted vertically as shown on the Plans.

7.	Utilities.

a.	Asphalt Pavement Roughness:  Transverse seams, joints, or roughness within 50 ft of inductive loops placed in asphalt pavement is not allowed.  Test the finished surface of the asphalt with a straightedge 10 ft long.  Do not permit the surface to vary more than 1/4 inch from the lower edge of the straightedge within 50 ft of sensors at the ATR installations.  At the Engineer’s discretion, run an inertial profiler or a profilograph equipped with a chart recorder down each wheel path of each lane for a distance of 50 ft before and after each ATR installation.  HDS will supply the profilograph and the Contractor’s personnel will operate it.  Repair any asphalt where more than 1/4 inch variance in the surface is recorded by the chart recorder in 10 ft.

b.	Field Inspection:  Notify the Engineer in writing a minimum of 3 working days in advance (excluding Saturday, Sunday and State or Federal Holidays) before installing conduit/wiring, inductive loops, and cabinets.  The Engineer shall be present to approve the installation before final burial or encasement.

Correct unacceptable installations and allow the Engineer to inspect the repair for completeness before burial or encasement.  Installations buried or encased without first receiving the Engineers approval will be uncovered, removed, and replaced by the Contractor.  Repairs for unacceptable installation and installations buried or encased, without the Engineers approval, are at the Contractor’s expense.

669-3.02 ACCEPTANCE TESTING.

1.	General Tests.  Test ATR installations according to Subsection 660-3.01.7, Field Tests.

669-3.03 DELIVERABLES.  Submit deliverables to HDS before final approval of the work or as otherwise called for herein.

1.	Materials Submittal.

a.	Format and Contents:  Provide a Materials Submittal of proposed equipment and materials for the ATR installations.  The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio.  Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

b.	Equipment and Materials:  Each portfolio shall include a table of contents listing each item’s intended uses, item description, product name, manufacturer, model, or part number and reference to associated information within the portfolio.

c.	Reference Drawings:  The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of mounted components.

d.	Delivery Interval:  Deliver Materials Submittal for review and approval to the Engineer within thirty days following award of the Contract.

e.	Liability:  The State of Alaska will not be liable for any materials purchased, labor performed, equipment used or delay to the work before equipment and materials have been reviewed and approved.

2.	As-Built Plans.

a.	Prepare four complete sets of as-built plans.  Maintain the as-built plans current with the progress of construction.  The as-built plans shall detail construction changes made to the ATR design and include the following information on the appropriate sheets:

I.	Location and depth of inductive loops, conduit runs.

II.	Locations of equipment cabinets and junction boxes.

b.	Present three sets of as-built plans to the Engineer, and affix one set to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a water proof, clear plastic holder.

c.	Redlines of full size construction plans will be acceptable as-builts.

3.	Photographs.

a.	Provide digital photographic prints, and formatted CD ROMs documenting sensor installations.

b.	Deliver photographs and CD ROMs organized in one or more white colored, D-ring style, 3 ring binders with clear insert overlays on front and spines.  Place prints in clear storage sheets, and CD ROMs in CD storage sheets inside the binders.

c.	The photographs shall show the inductive loops and conduit in place before covering with gravel and pavement for asphalt pavement sites, or before covering with epoxy compound for concrete pavement sites.  The photographs shall include:

I.	Two or more overall views of each ATR installation showing placement of the inductive loops.

II.	One or more views of each loop showing the loop and the conduit to the nearest junction box.

4.	Test Results.  Written or printed copies of the final results of tests, signed by the Contractor, shall be provided to the Engineer before acceptance of the Automated Traffic Recorder Installation.

5.	Deliverable Materials.  Deliver, where directed by the Engineer, any ATR equipment, sensors, and epoxy grout remaining after installation.

a.	Palletize the Deliverable Materials.

b.	Group the contents of each pallet by like items.

c.	Attach to each pallet a sealed plastic pouch containing complete copies of Material Safety Data Sheets that apply to the contents of that pallet.

d.	Provide an itemized list of Deliverable Materials.  For each item, the list shall detail:

I.	Item description:  including nature of the item, brand name, manufacturer name, model number, type number, and serial number.

II.	Item condition

III.	Item quantity

e.	Provide complete copies of Material Safety Data Sheets that apply to the Deliverable Materials.  Attach Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT.  Section 109.

669-5.01 BASIS OF PAYMENT.

Withholding.  Twenty percent (20%) of the billings for the 669 Pay Item will be withheld until deliverables have been provided to the Engineer as required and approval of the deliverables by the HDS has been received in writing.

669 Pay Item.  Payment is full compensation for the Traffic Data Sites combined under one Pay Item and includes full compensation for furnishing equipment, labor, and materials necessary to complete the work as specified.  Subsidiary to the 669 Pay item is the associated Excavation, As-Built Plans, and Acceptance Testing.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1)	Automated Traffic Recorder	Lump Sum

51132-033111

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

“Methyl Methacrylate Markings							Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings				Subsection 712-2.17

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete No. 4 and substitute the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of n/a mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of n/a mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of n/a mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of 250 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of 250 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 250 mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils.  Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Replace Subsection 670-3.06 with the following:

670-3.06 TOLERANCES FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Delete No. 3 and replace with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Add the following No. 4:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with pavement markings, except that required under item 643(20B) Temporary Signing and Striping – Roundabout, are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Temporary pavement markings and removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

CR246-010109

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10-250)	MMA Pavement Markings - 250 mil Inlaid	Lump Sum

670(10-500)	MMA Pavement Markings - 500 mil Inlaid	Lump Sum

51132-303111

Delete Items 670(11) and 670(12).

CR246-010109

Special Provisions

Add the following Section:

SECTION 682

UTILITY POTHOLING

682-1.01 DESCRIPTION.  Determine and record the horizontal and vertical location of subsurface utilities using a vacuum-extract truck.

682-2.01 MATERIALS.

Backfill Material  					Subsection 703-2.03, Aggregate Base Course, Grading D-1

Asphalt Patch Material  				Section 401, HMA, Type II; Class B

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies at least 5 days before starting potholing.  Remove materials using a vacuum-extract truck to expose and identify the utilities.  Survey the location and elevation of the utilities using the project horizontal and vertical control.  Log as-built information at each pothole location.

The contractor shall deliver the vacuum-extract truck to the job-site with the debris tank empty.

Backfill immediately after the Engineer accepts the logged data.  Backfill and compact the first six vertical inches using the excavated material or other approved materials.  Backfill and compact the remaining pothole void using Aggregate Base Course, Grading D-1.  If the pothole is located in a paved area, provide a pavement patch using Hot Mix Asphalt (HMA) material of the thickness equal to the adjacent asphalt concrete.

Immediately contact the Engineer and the affected utility if utility facilities are damaged during the potholing operations.  Costs associated with repairing damaged utilities will be borne by the Contractor.

682-3.02 AS-BUILTS.  Maintain a complete log of pothole information, including the station, offset, and elevation of subsurface utilities located, and other pertinent data.  Comply with the requirements of Subsection 642-3.06. Submit the completed log to the Engineer within two working days following the start of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for the time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. The pay time will include the time to empty the Vac-Truck debris tank of material for this project only. Travel time to or from the project, will not be authorized for payment. Other related work, including but not limited to removal of pavement, backfilling, pavement patching, shoring, labor, and equipment, will not be paid for separately, but will be subsidiary to 682 Items. Potholing for the Contractors information and not shown on the Plans, specified in the Specifications, or directed by the Engineer will be the Contractor’s responsibility and will not be paid for.  As-built surveying per Subsection 682-3.02 will be paid under Section 642.

682-5.01 BASIS OF PAYMENT.  Payment for Item 682(1) Vac-Truck Pothole will be paid on a contingent sum basis at the rate of $450/hour for the locations shown in the Plans or as directed by the Engineer.

Pay Item No.	Pay Item	Pay Unit

682(1)	Vac-Truck Pothole	Contingent Sum

51132-052511

Special Provisions

Add the following Section:

SECTION 690

EROSION, SEDIMENT AND POLLUTION CONTROL - MEASURES

690-1.01 DESCRIPTION.  Furnish, install and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

	Permanent Measures – include, the materials, hardware, equipment and labor required for installation and maintenance of erosion, sediment and pollution control material(s).

	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control	Section 641

Silt Fence	Section 633

Seeding	Section 618

Soil Stabilization	Section 619

690-2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials	Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL.  BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil binders, non-erodible cover, dustless sweeping, dust palliatives.   Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.03 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the APDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls: By length, measured along the centerline of the fiber roll, complete in place.

Manufactured Inlet Protection Systems:  By each, complete in place.

Sandbag Inlet Sediment Trap:  By each, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

CR690-081210

Fiber rolls include materials, hardware, equipment , labor, and maintenance required for permanent and temporary installations, and includes removal if placed as a temporary BMP.

SECTION 701

HYDRAULIC CEMENT

Special Provision

701-2.03 GROUT.  Add to end of last sentence:

from specimens made according to WAQTC TM 12.

CR7011-081210

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

(Percent Passing By Weight)

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, V and R mixtures.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet the following requirements:

| Description | Specification | Type IIA | Type I, IIB, III | Type IV | Type V, R |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, Min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP 61 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Flat-Elongated Pieces, max % | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| 1:3 |  | 20 | - | - | 20 |
| Absorption, max. % | AASHTO T 85 | 2.0 | 2.0 | 2.0 | 2.0 |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type IV, V, and R mixes:

	do not blend back natural sand

	shall be non-plastic as determined by WAQTC FOP for AASHTO T 90

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

(Percent Passing by Weight)

| Sieve | Gradation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V | Type R |
| 1 inch | 100 | - | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 | 100 |
| 1/2 inch | 60-84 | 75-90 | 100 | 100 | 65-90 | 70-100 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | ≤ 45 | 20-32 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | ≤ 35 | 15-25 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | ≤ 25 | 10-20 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | ≤ 20 | 7-15 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | ≤ 12 | 5-12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 4-8 | 3-8 | 4-10 |

Note:

1.	No tolerance is allowed beyond the Broad Band Limits of the No. 200 Sieve.

2.	For Type R, the mix design gradation JMD shall provide a minimum of 8% difference of percent passing the No. 4 and the No. 8 sieve.

CR7031-101110

703-2.07 SELECTED MATERIAL.  Add the following.

4.	Type D.  Earth, sand, gravel, or rock materials or combination thereof obtained from the excavation and containing no concrete, asphalt, muck, peat, frozen material, trees, brush, roots, sod, or other deleterious material, unless approved in writing by the Engineer.

Compact the material by walking the equipment over the entire fill area.

703-2.08 FILTER BLANKET.  Replace this Subsection with the following:

Meet AASHTO M 80, Class A.

Meet the following gradation:  AASHTO M 43 and the following requirements:

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 1 ½ in. | 100 |
| 1 in. | 85 – 100 |
| No. 4 | 10 – 15 |
| No. 200 | 0 - 5 |

51132-122810

SECTION 707

METAL PIPE

Standard Modification

Delete Subsection 707-2.07 and replace with the following:

707-2.07 GALVANIZED STEEL WATER CONDUIT.  Meet the following:

Galvanized Pipe		ASTM A 53 or ASTM A 120, galvanized according to AASHTO 111

Galvanized Fittings		ASTM A 234 galvanized according to AASHTO M 232

E17-063004

SECTION 710

FENCE AND GUARDRAIL

Special Provisions

710-2.03 CHAIN LINK FABRIC.

In the 1st sentence between the parenthesis, replace "Class D" with the following:

(Class C or D coating)

CR7101-110410

Standard Modification

Delete Subsection 710-2.04 METAL BEAM RAIL and replace with the following:

710-2.04 METAL BEAM RAIL.  Meet AASHTO M 180-00, Class A, Type II.  Galvanize the rail per ASTM A653 after factory roll formed and punched.

E83-100410

Delete Subsection 710-2.06 GUARDRAIL POSTS AND BLOCKS and replace with the following:

710-2.06 GUARDRAIL POSTS AND BLOCKS.  Furnish posts and blocks, as specified, meeting the following requirements.

1.	Wood Posts and Blocks.  Use timber with a stress grade of 1200 psi or more.  Testing must meet the standards of the West Coast Lumber Inspection Bureau.  Use timber for posts and blocks that is either rough sawn (unplaned) or S4S with nominal dimensions indicated.  Allowable size tolerance of rough sawn blocks in the direction of the bolt holes is  1/4 inch.  Only one combination of post and block finish may be used for any one continuous length of guardrail.  Treat all timber to meet Section 714.

2.	Steel Posts and Blocks.  Meet the section and length specified or shown on the Plans.  Use copper bearing steel when so specified.  Use steel meeting the requirements of ASTM A 36 and galvanized per ASTM A 123.

3.	Synthetic Blocks.  Product made from alternate materials may be used if accepted by the FHWA for use on the National Highway System.

E84-100410

Delete Subsection 710-2.11 GUARDRAIL TERMINALS and replace with the following:

710-2.11 GUARDRAIL TERMINALS.  Meet coating requirements of AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding, and riveting.  Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail.  Provide terminals that pass NCHRP 350 or MASH Test Level 3 and meet the following requirements:

1.	Controlled Release Terminal.	Meet the requirements of Standard Drawing G-25.

E85-100410

Special Provision

2.	Parallel Terminal.

a.	Requirements:

(1)	Crashworthiness:  Provide terminals that pass NCHRP 350 or Mash Test Level 3.

(2)	Length:  50 feet.

(3)	End Offset:  2 feet offset end.

(4)	Posts:  Use posts that are:

(a)	Steel post with hinge or

(b)	Yielding or breakaway steel post in steel tube

b.	Acceptable models include the following or approved equivalent:

(1)	Sequential Kinking Terminal (SKT) manufactured by Road Systems, Inc., 3616 Old Howard County Airport, Big Spring, Texas 79720, Telephone (432) 263-2435.

(2)	Extruder Terminal (ET-Plus) manufactured by Trinity Highway Products, L.L.C., 950 West 400 South, Centerville, Utah 84014, Telephone (801) 292-4461.

c.	Install AASHTO M 268, Type III, IV, or V retro-reflective sheeting (2.0 square feet, minimum) on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal.

3.	Buried in Backslope Terminal.  Meet the requirements of Standard Drawing G-15.

51132-091511

SECTION 712

MISCELLANEOUS

Standard Modifications

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS.  In Gray iron castings, delete text and replace with:

AASHTO M 306 and AASHTO M 105, Class 35B.

E46-012707

Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

CR246-010109

SECTION 724

SEED

Special Provision

724-2.02 MATERIALS.

Delete Table 724-1 and replace with the following:

TABLE 724-1

SEED REQUIREMENTS

| Species | Sproutable Seed, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

*Sproutable Seed is the mathematical product of Germination and Purity.

CR52-012707

SECTION 726

TOPSOIL

Special Provision

Delete Subsection 726-2.01, except for Table 726-1 and replace with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

CR208-112707

Add the following:

726-2.02 WETLAND SOIL.  Furnish wetland soil that is representative of the existing, natural organic blanket of the adjacent wetland area.  The wetland soil shall contain more than 5% organic matter as determined by loss-on-ignition of oven dried samples according to ATM 203. Notify the Engineer of the wetland soil source location at least 30 calendar days before delivery of the wetland soil to the project from the identified location.  The Engineer will inspect the wetland soil and its sources before approval will be granted for its use. The wetland soil pH shall be between 5 and 5.75. The grading requirements of the wetland soil are:

| Sieve | Percent Passing |
| --- | --- |
| No. 4 | 95-100 |
| No. 10 | 90-100 |
| No. 40 | 60-90 |
| No. 100 | 30-70 |
| No. 200 | 15-50 |

51132-082510

SECTION 729

GEOSYNTHETICS

Special Provisions

Add the following new subsection:

729-2.06 WEED BARRIER GEOTEXTILE.  Weed barrier geotextile must meet the physical requirements of Table 729-2.

TABLE 729-2

WEED BARRIER GEOTEXTILE

| PROPERTY* | TEST METHOD (ASTM) | TEST VALUE |
| --- | --- | --- |
| Grab Tensile Strength, lbs., min. | D-4632 | 70 |
| Grab Elongation, (at 35lbs. tensile strength) percent, max. | D-4632 | <50 |
| Bursting Strength, psi, min. | D-3786 | 115 |
| Water Permittivity 1/sec., min. | D-4491 | 0.04 |
| Apparent Opening Size, max. | D-4751 | No. 50 |
| Ultraviolet Degradation at 500 hour exposure, % strength retained | D-4355 | 70 |
| Geotextile Acceptance, pass or fail | D-4759 | Pass |

*	Geotextile Property Values = Minimum average roll values at a 95% confidence level in the weaker

principal direction.

51132-081010

SECTION 730

SIGN MATERIALS

Standard Modification

Delete Subsection 730-2.01 SHEET ALUMINUM and replace with the following:

730-2.01 SHEET ALUMINUM.  Use alloy 6061-T6, 5052-H36, 5052-H38, or recycled aluminum meeting alloy 3105, as specified in ASTM B 209.  Meet the thickness of aluminum sheet designated on the Plans.  Verify alloy and temper designation by mill certification.

Before January 1, 2011, treat the aluminum base metal sheets with chromate conversion coating for aluminum to meet ASTM B449, Class 2.

After January 1, 2011, treat the aluminum base metal sheets with a rinsed non-hexavalent chromium conversion coating for aluminum and aluminum alloys that meets ASTM B 921, class one.  Handle the cleaned and coated base metal only by a mechanical device or by operators wearing clean cotton or rubber gloves.  After cleaning and coating operations, protect the panels at all times from contact or exposure to greases, oils, dust, or other contaminants.

Make each sign panel a continuous sheet for all lengths 72 inches or less in the horizontal direction.  Use no more than one vertical splice for signs up to 144 inches in length and 48 inches or less in height.

Meet the panel dimensions specified with a tolerance of 1/16 inch.  Furnish metal panels that are cut to size and shape and free of buckles, warp, dents, cockles, burrs, and any other defects resulting from fabrication.  Complete all possible fabrication, including shearing, cutting, and punching of holes prior to the base metal preparation.

E86-041210

Special Provision

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR81-062204

730-2.05 FLEXIBLE DELINEATOR POSTS.  Add the following:

- Delineator, Flexible (Type A) shall be a two part system consisting of a drivable ground anchor socket and a replaceable, impact-resistant flexible post. Delineator, Flexible (Type A) shall be Carsonite Composites Flexguard CFGR0, or approved equal. The system shall have the following properties:

- Post. The post shall be a flexible polymer material meeting the dimensions and colors shown on the plans. The post shall be resistant to ultraviolet light, ozone, and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

- Ground Anchor Socket. The ground anchor socket shall be comprised of rigid material that does not collapse or buckle when driven into dense soil. Metallic materials shall be galvanized for corrosion resistance.

- Delineator, Flexible (Type B) shall be white with white reflectors on both sides with no other markings.  The 3.75” x 62” post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

51132-033011

SECTION 740

SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace Subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design.  Design and fabricate highway lighting structures to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans.  Use a wind speed of 100 mph with a gust factor of 1.3.  Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 ft above the pole base.

Design and fabricate traffic signal structures to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category III, with galloping using a basic wind speed of 100 mph and Central Region standard loads.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for the complete-in-place structure including the supported hardware.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient handholes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide a minimum overlap of two and one half (2.5) feet or the overlap specified in the Plans, whichever is greater.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to 1/2 inch thick from the prequalified base metals listed in AWS D1.1.  Fabricate elements greater than 1/2 inch thick from steel that conforms to AASHTO M270 and meets the Fracture Critical Impact Test requirements for Zone 3.  The Department will not accept structures that use laminated steel elements.

Fabricate the cross section of each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conform to ASTM A 53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans. Fabricate signal poles 10 to 15 feet long from 7 gage (US Standard) sheet steel.  Fabricate each post with a minimum inside diameter at the base plate as shown in the Plans.  Use 4 inch diameter by 4 inch Schedule 40, ASTM A53, Grade B pipe as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments.  Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot-dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Galvanizing kettles will be large enough to completely submerge each element, the mast arm, and the pole.  Submerge the complete/whole element in the galvanizing process.  An element galvanized in sections will not be accepted.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

(1).	Not fabricated according to these specifications or the approved shop drawings,

(2)	Bowed with sweeps exceeding 3/4 inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

(3)	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to Subsection 504-3.01.8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints for the length of the slip fit joint plus one half the diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

d.	Only visually inspect welds made on luminaire mast arms.

4.	Anchor Rods & Bolts.  Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

5.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified.

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using 1/4 inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms.  If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.  Provide the holes for the blind rivets before galvanizing.

TABLE 740-1

POLE MARKINGS

Note:

Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms.

| POLES (Including Mast Arms ) | MEASUREMENTS | TAG MARKINGS |
| --- | --- | --- |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

.

740-2.05 CONDUCTORS.  Replace Table 740-2 with the following:

TABLE 740-2

CONDUCTOR TERMINATION TABLE

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG. NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |
| 4 | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Black |  |  |
| 4 | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
|  | Spare | Green |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |

TABLE 740-2

CONDUCTOR TERMINATION TABLE

(Continued)

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Preemption | Orange | 20 | "PRE" |
|  | Neutral | Blue |  |  |
|  | Spare | Yellow |  |  |
| 3 | Preemption Confirmation | Black | 14 | "PRECON" |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 3 | Service to Controller | Black | 6 or 4 | "SIG" |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |

Replace No. 5. with the following:

5.	Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

Replace "6 twisted pairs" in the second sentence of the 4th subparagraph of No. 6. with the following:

"7 twisted pairs"

Replace TABLE 740-3 with the following:

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Pair No. | Tip | Ring | Pair No. | Tip | Ring |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

Replace Subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows conforming to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL Standard 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish Type X bodies and, for photoelectric control installation, furnish Types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Delete 740-2.14 VEHICULAR SIGNAL HEADS and replace with the following:

740-2.14 VEHICULAR SIGNAL HEADS.  Provide Light Emitting Diode, (LED) Signal Heads that conform to the following publications:

	Circular Indications:  Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) circular Signal Supplement, 6/27/05 (ITE Publication ST-052).  This is hereafter referred to as "VTCSH-Circular-05".

	Arrow Indications:  Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement, 7/1/07 (ITE Publication ST-054).  This is hereafter referred to as "VTCSH-Arrow-07".

"The applicable ITE Specification", as used in this specification, means VTCSH-Circular-05 for circular LED indications and VTCSH-Arrow-07 for arrow LED indications.

1.	Signal Heads.

Use signal heads that:  are the adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; are adjustable through 360 degrees about a vertical axis; and are mounted at the location and in the manner shown on the Plans.  Ensure that all vehicular signal heads at any one intersection are of the same make and type, except for programmed visibility signal heads.

Programmed Visibility Signal Heads.

·	Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

·	Provide each section with a 1 inch cutaway visor.

·	Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

·	The signal must be mountable with ordinary tools and capable of being serviced without tools.  Preset the adjustment at 4 degrees below the horizontal.

·	The visibility of each signal face must be capable of adjustment or programming within the face.  When programmed, each signal face's indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness, a faint glow to each side will be permissible.

·	Program the head as recommended by the manufacturer and as directed by the Engineer.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.

a.	LED Optical Units.  Use Led optical units and lenses meeting the requirement of the applicable ITE specification for all indications.  Also meet the following requirements:

(1)	Gaskets.  Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

(2)	Markings.  Provide LED Signal module with manufacturer applied markings listed in Section 3.6, Module Identification, of the applicable ITE Specification.  For circular indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads:  LED Vehicle Circular Traffic Signal Supplement (June 27, 2005)."  For arrow indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads:  LED Vehicle Arrow Traffic Signal Supplement (July 1, 2007)."

(3)	Compatibility.  Use LED signal modules that are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

(4)	Testing Requirements.

(a)	All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

(b)	Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

(c)	Production Testing and Inspection.  Submit manufacturer's certification that all tests in Section 6.3 of the applicable ITE Specification have been successfully completed on each LED module to be used on the project.

(d)	Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA "Nationally Recognized Testing Laboratory" do the following:

i.	Perform an initial assessment of the manufacturer's factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

ii.	Perform initial Design Qualification Testing as specified in Section 6.4 of the applicable ITE specification.

iii.	Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of the applicable ITE specification:

6.4.2 Conditioning

6.4.4.1 - 6.4.4.4 Luminous Intensity

6.4.4.6 Chromaticity

6.4.6.1 Current Consumption

6.4.6.6 Power Factor

6.4.6.7 Total Harmonic Distortion

iv.	Provide a certification label on each certified LED traffic signal module verifying the manufacturer's factory and modules passed the tests listed in i. through iv. above.

(5)	Warranty.  Provide written warranty by the signal module manufacturer that covers defects in materials, workmanship, and compliance with the applicable ITE specification for a period of 60 months after the manufacture date.  No new LED module will be accepted if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules.

The warranty does not include the cost of removing failed modules or reinstalling new modules.

Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

b.	Lens.  Use only clear lenses for all green signal modules.  Use lenses that meet the requirements of the applicable ITE Specification.

c.	Housing.

(1)	Use die cast aluminum, meeting ASTM B 85, for all parts of the housing, including the doors and end plates.  Ensure all parts are clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

(2)	Use a one-piece housing with integral top, bottom, sides, and with square doors, for each signal section.

(3)	Use stainless steel for all exposed bolts, screws, hinges, pins, and door-locking devices.  Use stainless steel or approved non-ferrous, corrosion-resistant material for all interior screws and fittings.

(4)	Provide an opening in the top and bottom of each housing to accommodate standard 1-1/2 inch pipe fittings and brackets.

(5)	Provide the top and bottom openings of each housing with integral serrated bosses that will provide positive positioning of the signal head in 5-degree increments to eliminate undesirable rotation or misalignment of the signal head as well as between sections.  Provide a total of 72 teeth in the serrated boss.  Ensure teeth are clean and sharp to provide positive position with the grooves of the mating section or framework.

(6)	Fasten individual signal sections together with a cadmium-plated tri-stud connector, lock washers, and nuts with access holes for the passage of electrical conductors form one section to another.

(7)	Provide 2 integral hinge lugs on the left side of each signal housing for mounting the door.

(8)	Provide 2 latches with stainless steel wing nut assemblies on the right side of each signal housing to engage the door latches.

(9)	Provide each signal housing door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal in a NEMA Type 3R enclosure.

(10)	Provide a round opening designed to accommodate any standard traffic signal lens in each signal housing door.

d.	Backplates.  Backplates shall not be louvered.  Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.100 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 3 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

e.	Signal Mounting Hardware:  Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1 1/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Post top adapters without a terminal compartment or compartments - provide manufactured of bronze metal.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish (2) 1/2" x 13 hot dip galvanized bolts that conform to ASTM A325 and (2) 1/2" hot dip galvanized washers that conform to ASTM F 436.

When replacing signal heads include all mounting hardware, backplates and visors.

f.	Finish. Factory finish housing, backplates and visors, each face, with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

CR7401-110410

Delete 740-2.15 PEDESTRIAN SIGNALS and replace with the following:

740-2.15 PEDESTRIAN SIGNALS.  Use LED Pedestrian Countdown modules that use the international "HAND/WALKING PERSON" symbols.  Except for the countdown indication and as otherwise noted in this specification, use modules that conform to "Pedestrian Traffic Control Signal Indications - Part 2:  Light Emitting Diode (LED) Pedestrian Traffic Signal Modules" Institute of Transportation Engineers, 3/19/2004, (hereafter referred to in this document as "PTCSI-04") and to the applicable Sections of the current Alaska Traffic Manual.

1.	Pedestrian Signal Heads.

a.	Signal Modules:  Provide Portland Orange "HAND" and "COUNTDOWN DIGITS" and lunar white "WALKING PERSON."  Locate COUNTDOWN DIGITS adjacent to the associated UPRAISED HAND.  Make "HAND" and "WALKING PERSON" symbols a minimum of 11 inches high and 7 inches wide and COUNTDOWN DIGITS a minimum of 9 inches high and 7 inches wide.  Provide incandescent looking WALKING PERSON, HAND, and COUNTDOWN DIGITS.  Ensure the WALKING PERSON, UPRAISED HAND and COUNTDOWN DIGITS are not readily visible when not illuminated.  Provide "AllnGaP" Portland Orange LEDs or equivalent, rated for 100,000 hours or more at 77˚ F and 20 mA.  Provide "InGaN" White LEDs.

Make all exposed components of modules suitable for prolonged exposure to the environment, without appreciable degradation that would interfere with function or appearance.

Provide modules with an installed gasket to seal the junction with the signal housing.

(1)	Lens.  Use modules with internal masks to prevent the icons and digits from being visible when not in operation.  No external silk-screen is permitted.  Provide smooth or textured lens of transparent polycarbonate material, frosted to prevent sun phantom.  Use lenses that will not crack, craze or yellow due to solar UV exposure typical for a south-facing Arizona desert installation, after a minimum of 60 months in service.

(2)	Retrofit.  When a module will replace an existing module in an existing signal housing, furnish signal modules designed as retrofit replacements for existing neon type pedestrian signals (ICC 4090 and/or 4094).  Provide modules that do not require special tools for installation.  Provide modules that fit securely into existing pedestrian signal housings without any modification to the housing, connect directly to existing electrical wiring, and form a weather-tight seal.  Provide modules and components constructed so each retrofit of existing pedestrian signals only requires the removal of the existing neon message module, gasket, and power supply and installation of the new LED pedestrian countdown module.  Provide all necessary components to complete conversion including a one piece gasket.

(3)	Photometric Requirements.  Meet the following requirements:

·	Minimum Luminance.  Maintain the following minimum luminance values for at least 60 months, under the operating conditions defined in Sections 3.3.1 and 5.2.1 of PTCSI-04 (when measured normal to the plane of the icon surface):

	WALKING PERSON 2,200 cd/m2,

	UPRAISED HAND 1,400 cd/m2,

	DIGITS 1,400 cd/m2 (when "88" is displayed).

·	Maximum Luminance.  Provide modules for which the actual luminance of a module does not exceed three times the minimum maintained luminance, as defined is Section 4.1.1 of PTCSI-04, when operated within the temperature range -40˚ F to +165˚ F.

·	Uniformity.  Provide modules for which the uniformity of the signal output across the emitting section of the module lens (i.e. icons or digits) does not exceed a ratio of 5 to 1 between the maximum and minimum luminance values as measured in 0.5 inch diameter spots.

·	Markings.  Permanently mark the back of each LED signal module with:

Ø	Manufacturer's name, trademark, and other necessary identification

Ø	Warranty information

Ø	Rated voltage and power consumption in volt-amperes

Ø	An up arrow or the word "UP" or "TOP" for orientation within a signal housing.

(4)	Electrical.  Provide LED pedestrian countdown signal modules that:

(a)	are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

(b)	have a maximum of 4 each secured, color coded, 36 inches long, 600V, 18 AWG minimum, jacketed wires, conforming to the National Electrical Code, rated for service at +221˚ F for electrical connection.

(c)	operate from a 60 3 Hz AC line over a voltage range of 80 VAC to 135 VAC. Test voltage for all photometric performance measurements shall be 120 3 volts rms.

(d)	use LED circuitry that prevents perceptible flicker over the voltage range specified above.

(e)	include voltage surge protection against high-repetition noise transients and low-repetition noise transients as stated in Section 2.1.8, NEMA Standard TS-2, 2003.  Module must meet the following test requirements:  Section 8.2 IEC 1000-4-5 & Section 6.1.2 ANSI/IEEE C62.41.2-2002, 3kV, 2 ohm and Section 8.0 IEC 1000-4-12 & Section 6.1.1 ANSI/IEEE C62.41.2-2000, 6kV, 30 ohm.

(f)	have a current draw sufficient to ensure compatibility and proper triggering and operation of load current switches and conflict monitors in signal controller units.  When the module is switched from the On state to the Off state the terminal voltage shall decay to a value less than 10VAC RMS in less than 100 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliamps peak (7.1 milliamps AC).

(g)	have a maximum power consumption at 77˚ F of: Hand 11.0 watts, Walking Person 8.0 watts, Digits 10.0 watts (when display shows "88").

(h)	have waterproof strain relief and anti-capillary wires, or have electrical wires that do not penetrate the LED module housing.  This is intended to prevent water seepage between the back cover and the electrical wires, or between the copper and insulation of the wires (Connection may be made by use of an over molded connector).

(i)	will default to the hand symbol for abnormal conditions when nominal voltage is applied to the unit across the two phase wires (rather than being applied to the phase wire and the neutral wire).

(j)	have three separate power supplies:  one each for the Walking Person, the Upraised Hand and the countdown digits.  Use separate circuitry to power the LED Walking Person icon and the LED Upraised Hand icon, in order to virtually eliminate the risk of displaying the wrong icon.

(5)	Countdown Module Functions.

(a)	General.  Begin the countdown at the beginning of the FLASHING HAND indication.  End the countdown at "0" at the end of the FLASHING HAND indication.  Make the countdown display dark from the end of one FLASHING HAND indication until the beginning of the next.  Display steady, not flashing, countdown digits.  Do not provide user accessible switches, controls, or options that would allow modification of cycle time, icons, digits or that would allow the countdown to operate while the WALKING PERSON or STEADY HAND is displayed.

(b)	Learning Cycle.  At power on, make the countdown display dark for one learning cycle in which it will determine the duration of the FLASHING HAND indication.

(c)	Normal Operation.  Display the countdown/FLASHING HAND for the duration measure in the learning cycle for every cycle until the module measures a different FLASHING HAND duration.

(d)	Countdown Duration Modification.  When a different duration is measured, make the countdown dark for the next cycle, and enter a Learning Cycle as previously described.  Resume Normal Operation with the new FLASHING HAND duration if the measured FLASHING HAND DURATION for the next cycle is the same as for the first cycle when a change was detected.  Continue Learning Cycles, if the duration is different, until the measured FLASHING HAND duration is the same for two cycles.  Resume Normal Operation with new duration when that happens.

(e)	Countdown Truncation.  Make the digits dark if the controller output displays a STEADY HAND or if both the HAND and WALKING PERSON go dark, regardless of whether the countdown to zero has been completed.

(f)	Preemption.  Handle preemption events as described under Countdown Duration Modification and, if necessary, Countdown Truncation.

(g)	Recycling.  Allow for consecutive cycles without display of the STEADY HAND.

(h)	Power Outage.  Maintain an uninterrupted countdown during short power failures (<1.5 seconds).  Make the digits dark after a loss of power of more than 1.5 seconds and enter a Learning Cycle when the power is restored.

(6)	Testing Requirements.

(a)	All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

(b)	Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

(c)	Production Testing and Inspection by Manufacturer.  Submit manufacturer's certification that all tests in Section 6.3 of PTCSI-04 have been successfully completed on each LED module to be used on the project.  Show result of each individual test on the certification.

(d)	Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA "Nationally Recognized Testing Laboratory" do the following:

i.	Perform an initial assessment of the manufacturer's factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

ii.	Perform initial Design Qualification Testing as specified in Section 6.4 of the PTCSI-04.

iii.	Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following section of PTCSI-04.

6.4.2 Conditioning

6.4.4.1 - 6.4.4.4 Luminous Intensity

6.4.4.6 Chromaticity

6.4.6.1 Current Consumption

6.4.6.6 Power Factor

6.4.6.7 Total Harmonic Distortion

iv.	Provide a certification label on each certified LED traffic signal module verifying the manufacturer's factory and modules passed the tests listed in (a) through (c) above.

(7)	Warranty.  Provide a manufacturer's written warranty that covers defects in materials, workmanship, and compliance with PTCSI-04 for a period of 60 months after the manufacture date.  No new LED module will be accepted on a project if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules.

The warranty does not include the cost of removing failed modules or reinstalling new modules.

Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

b.	Housing:

(1)	Provide signal housings that have maximum overall dimensions of 18-1/2 inches wide, 18-3/4 inches high, and 9 inches deep, including Z-crate-type visor and hinges.

(2)	Provide a dustproof and weatherproof housing that allows easy access to and replacement of all components.

(3)	Provide a one-piece, corrosion-resistant, aluminum-alloy die-cast case complete with integrally cast top, bottom, sides and back.  Provide 4 integrally cast hinge lug pairs, 2 at the top and 2 at the bottom of each case, for operation of a swing-down door.

(4)	Provide 1 of the following 3 versions of the case, according to project specifications:

·	Clamshell mount, with hardware, for "pole left of message" installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

·	Clamshell mount, with hardware, for "pole right of message" installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

·	Make suitable for either post top or bracket mounting with upper and lower openings to accommodate standard 1-1/2 inch pipe brackets.  Plug unused openings to be weather-tight.  Integrally cast a shurlock boss into the bottom opening of the signal case.  Make the dimensions of the shurlock boss as follows:  outside diameter, 2-5/8 inch; inside diameter, 1-31/32 inch; number of radial teeth, 72; and depth of teeth, 5/64 inch.  Use clean and sharp teeth that provide full engagement to eliminate rotation or misalignment of the signal.

(5)	Make the door frame a one-piece, corrosion-resistant, aluminum-alloy die-casting, complete with 2 hinge lugs cast at the bottom and 2 latch slots cast at the top of each door.  Attach the door to the case by means of two Type 304 stainless steel spring pins.  Attach 2 stainless steel hinged bolts with captive stainless steel wing nuts and washers to the case with the use of stainless steel spring pins.  Provide a door that will latch and unlatch without the use of tools.

c.	Conductors:  Meet IMSA specifications 20-1 with No. 14 AWG or larger.

d.	Load Switches.  Place all load switches for operation of pedestrian signals in the controller cabinet.

e.	Fasteners.  Use machine screws, studs, and washers that are stainless steel.

f.	Gaskets.  Use gaskets that conform to ASTM D 1056, Grade 2C2.

g.	Terminal Blocks:  Provide a rain tight terminal compartment with a 12 position terminal block.

h.	Finish.  Factory finish the outside of pedestrian signal head housings and visors and signal visor interiors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363 and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595-37038.

CR7402-110410

Replace Subsection 740-2.16 with the following:

740-2.16 PEDESTRIAN PUSH BUTTONS.  Push buttons shall be Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch. Furnish Polara model RBDLM2-B-4H or approved equal with the following features.  Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 VAC.  Must have the following characteristics:

1.	Switching unit that is solid state electronic piezo rated for 100 million cycles.

2.	Sealed to prevent ice from impeding function.

3.	Must hold the call for a minimum of 5 seconds.

4.	Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

5.	Provide an LED indication and an audible tone or beep within the button when pushed.

6.	Must have a raised rim or ridges to protect the button from side impacts.

7.	Powder coated cast switch housing of dark olive green or black.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

Replace Subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform to the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

	Meet or exceed the minimum initial light levels indicated.

	Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage.  Furnish lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21.

1.	Luminaries General

Install luminaires that feature:

a.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

b.	Third party certification for use in wet locations.

c.	Glass lenses, unless polycarbonate resin refractors are specified.

d.	Terminal blocks for attaching the illumination tap conductors.

e.	Aluminum reflectors with an ALZAK or ALGLAS finish.

f.	Optical components free of substances that affect photometric performance, paint.

g.	Housings cast with no provision for a photoelectric control receptacle.

h.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

i.	Plug in starting aids in fixtures with lamps through 400 watts.

2.	Luminaries – Cobrahead and Offset

Each cobrahead or offset luminaire shall also include:

a.	An easily removed hinged door used exclusively for mounting the ballast.

b.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

c.	A four bolt mounting brackets that fit 2 inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

3.	LED Luminaire

LED Luminaires shall be UL listed for wet locations and enclosure classified IP66 per IEC 529.  The fixture shall be resistant to corrosion, ultraviolet degradation and abrasion.  Nickel-chrome plated wire guard shall be used for providing anti-fouling protection from leaf/debris and animals nesting to assure cool LED operation.

The luminaire shall have five years warranty on the LED’s and the driver.  Average delivered lumens over 50,000 hours should be a minimum of 85% of initial delivered lumens.

The LEDs shall operate over the temperature range of -40 °F to +165 °F.  The LEDs shall be wired in series parallel strings.  The failure of many one LED, and its associated string of LEDs, shall not cause the loss of more than 20% of the light output of the complete LED module.

4.	Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

51132-040111

Special Provisions

Add the following Section:

SECTION 744

EROSION, SEDIMENT, AND POLLUTION CONTROL - MATERIAL

744-2.01 MATERIAL.

Fiber Roll:  (commonly called straw wattle)

a.	Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

Manufactured Inlet Protection System:

a.	Manufacturers:

Ultra Tech International – Ultra-DrainGuard

Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

Enpac - Catch Basin Insert, Oil and Sediment or

b.	Approved equal.

Sand Bag Inlet Sediment Trap:

a.	Sandbag sack fabric shall be a nonwoven, needle punched design meeting the following requirements:

Grab Tensile Strength	ASTM D 4632	200 pounds (min.)

Grab Elongation	ASTM D 4632	15 – 70%

Mullen Burst Strength	ASTM D 3786	400 psi. (min.)

Trapezoidal Tear Strength	ASTM D 4533	95 lbs. (min.)

Apparent Opening Size	ASTM D 4751	No. 30 U.S. STD sieve (max)

Permittivity	ASTM D 4491	0.01 sec-1 (min.)

Ultraviolet Light Stability,

Retained Strength	ASTM D 4355	90%

Puncture Strength	ASTM D 4833	120 lbs. (min.)

These requirements are for Minimum Average Roll Values (MARV) verified in accordance with ASTM D 4759.

b.	Seam Thread:

Similar durability to the sandbag sack fabric.

c.	Sandbag Fill Material:

Select Material	Type B	703-2.07.

d.	Cinch Ties:  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

CR744-022309

INDEX

Standard Modification

INDEX Remove the text. “Approved Products List” and replace with: Qualified Products List

E36-012707

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

APPENDIX B

ENVIRONMENTAL PERMITS

APPENDIX C

MATERIAL CERTIFICATION LIST

APPENDIX D

SIGN SHOP DRAWINGS

APPENDIX E

TEMPORARY CONSTRUCTION EASEMENTS

TEMPORARY CONSTRUCTION PERMITS