SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Design Computations

b.	Cross Sections

c.	Laboratory Manual of Alaska Test Methods and Standard Practices (Price $20.00)

d.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

e.	Interim Standard Specifications for Highway Construction (Metric) 94M. ($25.00)

2.	The following item is available for review in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Geotechnical report titled "Dillingham to Aleknagik, Station 10+00 to 1142+42, Project No. S-0411(4), August 1967, Anchorage District," which is from a previous project in the area.

b.	Geotechnical report titled “Dillingham-Aleknagik Road Rehabilitation, Project No. STP-0410(1)/51192, September 1997"

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0639.

4.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

5.	Contractor is advised that due to the particular requirements of the asphalt surface treatment on this project, the painted traffic markings are required to be installed in the year following the installation of the asphalt surface treatment. See subsection 105-1.15 and Section 670.

6.	This is to notify all bidders that effective January 1, 1998, contract items under Section 643, Traffic Maintenance, will no longer be creditable under the Disadvantaged Business Enterprise Program for DBE credit as subcontractable items. The only current exception is item 643(3), Permanent Construction Signs.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

7.	The Department’s procedure for providing for the costs of on-site flagging has changed. In recognition of the benefits derived from a well coordinated flagging operation to both the traveling public and the Contractor’s operation, the Department’s position is that the Contractor is a full partner in this contract and should participate in the cost of flagging. Therefore, the amount paid by the Department to provide flagging has been changed from $45.00/hour to a shared $22.50/hour. The additional actual cost to provide a flagger shall be considered as incidental to other items of work. This change shall in no way relieve the Contractor from his responsibility to provide for safety and convenience of the public.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

INTERIM

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

94M

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Special Provisions

102-1.12 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (10/28/96)R171

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01 CONSIDERATION OF PROPOSALS. In the second and third paragraphs, replace form 25D-5 with the following: "form 25D-5(C)".

(5/5/95)R82M

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall call the following utilities and agencies directly:

Nushagak Electric Cooperative (NEC)..........................................	842-5251

Nushagak Telephone Cooperative, Inc. (NTC)..............................	842-5251

Nusagak Telephone Cooperative, Inc., CATV Division (CATV)	842-5251

City of Dillingham, Public Works Dept........................................	842-5148

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits. The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor shall work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen. Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

Prior to the relocation of the utility's facilities, construction staking may be required. The Contractor shall give the utility 14 days advance notice as to when the staking will be available and maintain the stakes until the utility relocation is completed.

Payment for this staking will be as follows:

1.	If, as part of the contract, the Contractor is required to provide staking in the area needed by the utility, this work will be subsidiary to Item 642(1), Construction Surveying.

2.	If construction staking or right-of-way staking is required by the utility in advance of the Contractor's normal schedule, the utility will request the staking, through the Engineer, 14 days prior to the time the staking is required for the utility to start their relocation. This staking will be paid under Item 642(3), Three Person Survey Party.

3.	If right-of-way staking is required by the utility, and staking the right-of-way is not a part of the contract, the utility will request the staking, through the Engineer, 14 days prior to the time the staking is required for the utility to start their relocation. This staking will be paid under Item 642(3), Three Person Survey Party.

(11/13/97)R3

It is the Contractors responsibility to schedule and coordinate the utility relocations with the project as set forth in Section 108-1.03, Prosecution and Progress.

The utility relocations are divided into construction segments detailed below. Any changes to the contract construction sequencing plan shall take into account all impacts on utility relocations. Additional coordination with the affected utility companies is the responsibility of the Contractor.

Each utility requires fifteen (15) calendar days advance written notice prior to beginning relocation on a segment. The utility will not be required to work on more than one item within the segment at a time. NTC relocations will require that staking of right-of-way and/or slope staking be completed prior to NTC starting relocation in any segment that they have work.

NTC abandonment of the existing underground telephone facility in conflict with the road improvements in the location listed below will be accomplished by NTC or their contractor after the new facility is in operation.

The NEC and CATV relocation for the most part may be completed prior to the start of road construction. The Contractor will need to confirm with NEC which item of relocation has been completed. If any of the relocation is not completed prior to start of road construction, than the list below indicates the required number of calendar days necessary to accomplish the NEC and CATV relocation.

The Contractor shall schedule his operations to allow each Utility the required number of calendar days to complete the relocation. Specific coordination requirements for NEC, NTC and CATV are included below:

Segment A-Station 2+242 Lt. & Station 2+553 Rt.

NEC

1.	NEC will be placing a taller pole at approximate Sta. 2+242 Lt. and will retire an existing anchor guy at approximate Sta. 2+553 Rt. The Contractor shall allow NEC or their contractor four (4) calendar days to accomplish the relocation in this location.

CATV

2.	CATV will detach the existing aerial coaxial TV cable from the existing pole at Sta. 2+242 Lt. and attach the existing coaxial TV cable to the new pole at Sta. 2+241 Lt. The Contractor shall allow CATV or their contractor one (1) calendar days to accomplish the relocation in this location.

Segment B-Station 10+070 to Station 10+400

NEC

1.	NEC or their contractor will be relocating the existing aerial electric. NEC or their contractor will be realigning the existing three phase pole line to the west by relocating 5 three phase poles between Sta. 10+070 Lt. and Sta. 10+400 Rt. When the new poles, conductors and coaxial cables are in place and working, the existing facilities will be retired. The Contractor shall allow NEC or their contractor seven (7) calendar days to accomplish the relocation in this location.

CATV

2.	CATV will be placing new coaxial TV cable on the 5 new three phase poles between Sta. 10+070 Lt. and Sta. 10+400 Rt. after NEC has completed their relocation. Once NEC has completed their relocation as listed above, the Contractor shall allow CATV or their contractor three (3) calendar days to accomplish the relocation in this location.

NTC

3.	NTC or their contractor will be placing new underground cables and new telephone pedestals from approximate Sta. 10+190 Lt. to Sta. 10+370 Lt. and a roadway crossing at approximate Sta. 10+250. The Contractor shall allow NTC or their contractor five (5) calendar days to accomplish the relocation in this location.

Segment C-Station 10+400 to Station 10+700

NTC

1. 	NTC or their contractor will be placing new underground telephone cables and pedestals between Sta. 10+540 Lt. and Sta. 10+690 Lt., and between Sta. 10+400 Rt. and Sta. 10+685 Rt. The Contractor shall allow NTC or their contractor five (5) calendar days to accomplish the relocation in this location.

Segment D-Station 11+050 to Station 11+296

NEC

1.	NEC or their contractor will be placing a new single phase pole at approximately Sta. 11+296 Lt., and will be placing an anchor guy on the existing pole at Sta. 11+275 Rt. The Contractor shall allow NEC or their contractor three (3) calendar days to accomplish installation of the new aerial facilities.

CATV

2.	CATV or their contractor will be detaching the existing coaxial TV cable from the existing pole at Sta. 11+296 Lt. and will be reattaching the existing coaxial TV cable to the new pole once it is installed and NEC has completed their relocation. The Contractor shall allow CATV or their contractor two (2) calendar days to accomplish installation of the new aerial facilities.

NTC

3.	NTC or their contractor will be placing new underground cables and pedestals, and will lower in place the existing underground cable between Sta. 11+085 Lt. and Sta. 11+210 Rt., and between Sta. 11+100 Rt. and Sta. 11+180 Rt., as well as a roadway crossing at Sta. 11+190. The Contractor shall allow NTC or their contractor five (5) calendar days to accomplish installation of the new facilities.

Segment E-Station 11+296 to station 11+751

NEC

1.	NEC or their contractor will be placing new aerial electric facilities within the above station area. The existing single phase pole line will be realigned from the left side of the Aleknagik Lake road to the right side between Sta. 11+390 and Sta. 11+520. Four new single phase poles will be relocated in the above area. NEC or their contractor will be placing two aerial guy poles and anchors at Sta. 11+639 Rt. and Sta. 11+751 Rt. The Contractor shall allow NEC or their contractor nine (9) calendar days to accomplish relocation and retirement of the existing aerial facilities.

CATV

2.	CATV or their contractor will be placing new coaxial TV cable on the new single phase poles in the realigned area between Sta. 11+390 Lt. and Sta. 11+520 Rt., once NEC has completed their relocation. The Contractor shall allow CATV or their contractor four (4) calendar days to accomplish relocation and retirement of the existing aerial facilities.

NTC

3.	NTC or their contractor will be placing new underground telephone cables and pedestals along the right side of the Aleknagik Lake road between approximate Sta. 11+390 Rt. and Sta. 11+642 Rt., with a roadway crossing at Sta. 11+545. The Contractor shall allow NTC or their contractor eight (8) calendar days to accomplish relocation and retirement of the existing facilities.

Segment F-Station 11+780 to Station 12+040

NTC

1.	NTC or their contractor will be adjusting an existing telephone pedestal at Sta. 11+786 Rt., if there is enough slack in the existing underground telephone cables to allow adjustment. If it’s determined that there is not enough slack in the existing underground telephone cables to adjust the existing pedestal, than NTC or their contractor will be placing two new cables from the existing pedestal at Sta. 11+786 Rt. to the existing pedestal at Sta. 11+872 Rt. The Contractor shall allow NTC or their contractor three (3) calendar days to adjust the existing pedestal. If it is determined that there is not enough slack in the existing cables, then the Contractor shall allow five (5) calendar days for NTC or their contractor to place two new cables as described above.

NTC

2.	NTC or their contractor will be placing a new underground telephone cable roadway crossing at approximate Sta. 11+870. The Contractor shall allow NTC or their contractor three (3) calendar days to complete the placement of this road crossing.

NTC

3.	NTC or their contractor will be placing an new underground telephone cable from an existing pedestal at Sta. 11+846 Lt. to approximate Sta. 12+042 Lt. The Contractor shall allow NTC or their contractor four (4) calendar days to accomplish this relocation.

Segment G-Station 12+045 to Station 12+848

NEC

1.	NEC or their contractor will be placing a new pole at approximate Sta. 12+125 Rt. The Contractor shall allow NEC or their contractor two (2) calendar days to place the new pole.

CATV

2.	CATV or their contractor will be attaching the existing aerial coaxial TV cable to the new insert pole at Sta. 12+125 Rt., once NEC installs the new pole. The Contractor shall allow CATV or their contractor one (1) calendar days to accomplish the aerial cable attachment in this location.

NTC

3.	NTC or their contractor will be placing two new underground telephone cables from approximately Sta. 12+045 Rt. to Sta. 12+750 Rt. and will be placing two cable from approximate Sta. 12+750 Lt. to Sta. 12+848 Lt. In addition NTC or their contractor will be placing three single cable road crossings at the following approximate locations: Sta. 12+210, Sta. 12+480 and Sta. 12+617, as well as one two cable road crossing at Sta. 12+750. The Contractor shall allow NTC or their contractor seventeen (17) calendar days to accomplish the underground cable telephone relocation and four roadway crossings in this area.

Segment H-Station 12+900 to Station 13+140

NTC

1.	NTC or their contractor will be placing two new underground telephone cables, from approximately Sta. 12+906 Lt. to Sta. 13+140 Lt., which includes placing cables across Squaw Creek. In addition, one underground roadway telephone cable crossing will be placed at approximately Sta. 13+005. The Contractor shall allow NTC or their contractor eight (8) calendar days to accomplish this relocation.

Segment I-Station 13+140 to Station 13+980

NEC

1.	NEC or their contractor will be realigning the existing single phase pole line to the west by relocating 6 three phase poles, between approximate Sta. 13+148 Lt. and Sta. 13+542 Lt. This includes the relocation of an aerial roadway crossing at approximate Sta. 13+440. The Contractor shall allow NEC or their contractor seven (7) calendar days to complete the placing of the new poles and retire the existing poles.

CATV

2.	CATV or their contractor will be placing new coaxial TV cable on the new poles between Sta. 13+148 Lt. and Sta. 13+542 Lt. after NEC has completed their relocation in this location. When the placement of coaxial TV cable placement is completed, the existing coaxial TV cable will be retired. The Contractor shall allow CATV or their contractor three (3) calendar days to complete this relocation.

NTC

3.	NTC or their contractor will be placing two new underground telephone cables from Sta. 13+140 Lt. along the left to approximate Sta. 13+980 Lt. One new underground cable roadway crossing will be placed at approximate Sta. 13+260. The Contractor shall allow NTC or their contractor twelve (12) calendar days to complete the cable placement in this location.

Segment J-Station 14+080 to Station 14+400

NTC

1.	NTC or their contractor will be placing two new underground telephone cables and pedestals from approximate Sta. 14+080 Lt. to Sta. 14+380 Lt. In addition, one underground roadway cable crossing will be placed at approximately Sta. 14+105. The Contractor shall allow NTC or their contractor six (6) calendar days to place these underground cables.

Segment K-Station 14+520 to Station 15+190

NEC

1.	NEC or their contractor will be placing two new poles. One three phase pole will be placed at Sta. 14+622 Lt. and one single phase pole will be placed at approximate Sta. 14+650 Rt. When the new poles are in place the existing poles will be retired. The Contractor shall allow NEC or their contractor four (4) calendar days to place these poles and retire the existing poles.

CATV

2.	CATV or their contractor will be detaching the existing coaxial TV cable from the existing poles at Sta. 14+662 Lt. and Sta. 14+650 Rt. after NEC or their contractor has completed the above relocation in this area. CATV or their contractor will then attach the existing coaxial TV cable to the new poles at Sta. 14+662 Lt and 14+650 Rt. The Contractor shall allow CATV or their contractor two (2) calendar days to complete this cable relocation.

NTC

3.	NTC or their contractor will be placing two underground cables and pedestals from approximate Sta. 14+520 Lt. to Sta. 14+985 Lt. An underground single cable roadway crossing is to be placed at approximate Sta. 15+160. The Contractor shall allow NTC or their contractor eight (8) calendar days for the cable placement in this location.

Segment L-Station 15+190 to Station 15+725

NEC

1.	NEC or their contractor will place two new single phase poles at approximate Sta. 15+325 Rt. and Sta. 15+612 Rt. Once the new poles have been placed the existing poles will be retired. The Contractor shall allow NEC or their contractor four (4) calendar days to place both poles and retire the existing poles.

CATV

2.	CATV or their contractor will detach the existing aerial coaxial TV cable from two existing single phase poles at Sta. 15+612 Rt. and Sta. 15+325 Rt. after NEC or their contractor has completed placing the new poles in the above locations. Then CATV or their contractor will detach the existing aerial coaxial TV cable from the existing poles and attach it to the new poles at the above stations. The Contractor shall allow CATV or their contractor two (2) calendar days to complete the cable relocation.

NTC

3.	NTC or their contractor will be placing one underground cable from approximate Sta. 15+190 Rt. to Sta. 15+495 Rt., and from approximate Sta. 15+460 Lt. to Sta. 15+724 Lt. The Contractor will shall NTC or their contractor six (6) calendar days to complete the cable relocation.

4.	NTC or their contractor will be placing one new underground cable from a new pedestal at approximate Sta. 15+190 Lt. to the existing pedestal at approximate Sta. 15+330 Lt. The Contractor shall allow NTC or their contractor four (4) calendar days to complete the cable relocation.

Segment M-Station 15+800 to Station 16+265

NEC

1.	NEC or their contractor will be realigning the single phase aerial line by placing five new single phase poles from approximate Sta. 15+810 Rt. to Sta. 16+265 Rt. The Contractor shall allow NEC or their contractor six (6) calendar days to place the new poles and to retire the existing poles.

CATV

2.	CATV or their contractor will be placing new aerial coaxial TV cable on to the new poles between Sta. 15+810 Lt. and Sta. 16+265 Lt., after NEC or their contractor completes their relocation as mentioned above. When the new aerial coaxial TV cable has been placed, the existing aerial coaxial TV cable will be retired from the existing poles. In addition, the existing aerial coaxial TV crossing will be detached from the existing pole at Sta. 16+240 Rt. and will be reattached to the new pole in this location. The Contractor shall allow CATV or their contractor four (4) calendar day to place the coaxial TV cable and retire the existing coaxial TV cable.

NTC

3.	NTC or their contractor will be placing a new underground cable from approximately Sta. 16+087 Lt. to Sta. 16+192 Lt. with a roadway crossing at Sta. 16+192. The Contractor shall allow NTC or their contractor four (4) calendar day to complete this cable placement.

Segment N-Station 16+470 to Station 16+760

NTC

1.	NTC or their contractor will be placing two new underground cables between approximate Sta. 16+500 Rt. and Sta. 16+760 Rt. with an underground roadway crossing at Sta. 16+500. The Contractor shall allow NTC or their contractor five (5) calendar days to place their underground cables in this area.

Segment O-Station 16+980 to Station 17+660

NEC

1. 	NEC or their contractor will be realigning the single phase aerial line by placing six new poles from approximate Sta. 17+040 Rt. to Sta. 17+640 Rt. In addition, a new guy pole and anchor will be placed at approx. Sta. 16+227 Lt. When all the new poles and conductor have been placed, the existing poles will be retired. The Contractor shall allow NEC or their contractor seven (7) calendar days to complete the relocation in this area.

CATV

2.	CATV or their contractor will place new aerial coaxial TV cable between Sta. 17+040 Rt. and Sta. 17+640 Rt., after NEC or their contractor completes the installation of the new poles in this location. When the new aerial coaxial cable has been installed and working, the existing aerial coaxial TV cable will be retired. The Contractor shall allow CATV or their contractor three (3) calendar days to complete TV cable placement.

NTC

3.	NTC or their contractor will be placing new underground cables from approximate Sta. 16+980 Rt. to Sta. 17+660 Rt. The Contractor shall allow NTC or their contractor ten (10) calendar days to complete this underground cable placement.

105-1.15 PROJECT COMPLETION. Delete the first sentence of the third paragraph and substitute the following: When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas, and Section 670, a letter of project completion will be issued by the Engineer.

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following: Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage. (8/5/93)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater. Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(7/2/93)S13

106-1.02 LOCAL MATERIAL SOURCES. Add the following after the first paragraph: The Contractor shall provide process control for reasonable assurance, that all materials submitted for acceptance conform to the contract specifications. Sampling and testing of all materials for process control, including screening, crushing, blending, stockpiling of aggregates, production and laydown of aggregate courses or mixtures, asphalt concrete mixtures, and monitoring of compaction, is the responsibility of the Contractor. Process control tests shall be made in accordance with the applicable test methods specified in the contract.

A process control plan shall be submitted at the pre-construction conference. The process control plan shall include, for each item being produced, the methods to be used for sampling and testing, the proposed testing frequency, personnel qualifications, and equipment descriptions. Process control will not be measured for payment but will be subsidiary to the applicable items being processed.

The Department has the exclusive right and responsibility for determining the acceptability of the construction and all incorporated materials. Acceptance testing by the Department is not to be considered as a replacement for process control testing by the Contractor. When the Contractor is not providing adequate process control testing, the Engineer may refuse to retest materials which have been shown to be unacceptable by standard acceptance testing procedures.

(2/14/95)R201

Add the following: Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources. A copy of this statement shall be provided to the Engineer. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified. (5/24/96)R5

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO

PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Prior to removing, stockpiling, staging or disposing of any material or equipment in, on or from a location not previously permitted by the contract, the Contractor shall obtain all necessary permits and clearances required. These permits and clearances may include, but are not limited to, State Historic Preservation Office clearance, a Division of Governmental Coordination Coastal Consistency Determination, Alaska Department of Natural Resources Mining Reclamation Permit, Alaska Department of Environmental Conservation permits, Alaska Department of Fish and Game Title 16 permit, US Fish and Wildlife endangered species clearance, US Army Corps of Engineers clearances and permits regarding wetlands, City or Borough Flood Hazard permit, local development permits, permission of property owner, etc.

The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified.

The Contractor shall provide a wetland specialist to conduct a wetlands determination in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, that will be impacted by the Contractor's operations.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that all permits or clearances necessary have been obtained. Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action was required on the part of the Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following to the third paragraph: When working near wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits. Refueling and servicing of equipment shall not be performed adjacent to wetlands.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

Add the following: The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels. The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for material extraction, excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract. If the Contractor chooses to pursue permit modifications, such modifications shall be requested through the Engineer.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work which is permitted and specified by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(7/17/97)R7M

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Delete paragraphs four and five in their entirety, and substitute the following: If utility facilities are damaged by the Contractor, the owning utility has the choice of making the repair or having the Contractor correct the damage. The Contractor shall reimburse the utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The utility mislocates the facility in the field by more than 0.75 m (2.5 feet) horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the utility.

(2/7/96)R8M

107-1.21 PERMITS. Add the following subsection: The following permits have been received on the Contractor's behalf by the Department:

1.	Department of the Army, Corps of Engineers Nationwide Permit 23 to excavate from and to place fill into wetlands and waters of the United States.

2.	Department of Fish and Game Title 16 Permit No. FG 97-II-0147 dated June 12, 1997 and expires December 31, 1998.

3.	Department of Fish and Game Title 16 Permit No. FG 97-II-0356 dated June 13, 1997 and expires December 31, 1998.

4.	Department of Fish and Game Title 16 Permit No. FG 97-II-0148 dated June 12, 1997 and expires July 15, 1998.

The Contractor shall provide the information necessary to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge stormwater from the construction site. Requirements for this permit are given under Section 641, Erosion and Pollution Control

The permits obtained by the Department are attached to these specifications as Appendix A. The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications. It is the Contractor's responsibility to abide by the stipulations contained in each permit. If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer. The Engineer will then decide if a permit modification is necessary. The Engineer will have copies of the permits posted in the project office.

It is the Contractor’s responsibility to obtain all permits required for actions not permitted previously by ADOT&PF. The Contractor is responsible for complying with all permit stipulations, conditions and/or terms. Agencies to contact for permit information may include, but is not limited to, the U.S. Army Corps of Engineers, the Environmental Protection Agency, the U.S. Fish and Wildlife Service, the Alaska Department of Fish and Game, the Alaska Department of Environmental Conservation, the Alaska Department of Natural Resources, and local or regional governments. The Contractor shall provide timely notification of such actions and permit acquisitions as may be required by federal, state, regional, and local authorities. The Contractor shall provide copies of all permits, and applicable Federal and State notifications to the Project Engineer.

(5/23/96)R9aM

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01 SUBLETTING OF CONTRACT. Delete numbered item 1. in the second paragraph and substitute the following:

1.	Alaska Commercial Driver's License, with the appropriate endorsements for the class of vehicle to be operated.

Delete the next to last paragraph in this sub-section on page 38.

(11/6/95)R207M

108-1.03 PROSECUTION AND PROGRESS. Delete Item 5., and substitute the following:

5.	A draft Storm Water Pollution Prevention Plan, Hazardous Material Control Plan, Notice of Intent, and activities description, as required under Section 641. (3/12/97)R160

Add the following: The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule. The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule. At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule. The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly. The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements. The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	Schedule Updates. Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions. The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting. The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is shared equally.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks. This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

Preparation and updating of the CPM schedule and two week work plans will not be paid for directly. Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.

(12/13/96)R11A

108-1.05 CHARACTER OF WORKMEN, METHODS AND EQUIPMENT. Add the following: The Contractor shall provide the Engineer with make, model, year, capacity, watts, and the related information of every piece of powered equipment used on the project. This information shall be updated weekly unless otherwise directed by the Engineer. (6/6/95)R13M

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES. After the ninth paragraph, insert the following: The Contractor shall furnish competent scale operators to weigh all materials measured and paid for on a weight basis.

The scale operator shall record to the nearest 50 kilograms the weights of all loads of material on a daily tally sheet. The scale operator shall also make out a weigh slip ticket for each load hauled showing the gross, tare and net weights. The original shall accompany the load and one copy shall be retained until any discrepancies have been resolved at the end of each day.

The scale operator's daily tally sheet shall also include the following information as applicable to the type of scales used:

1.	Name and number of project,

2.	Contract item number,

3.	Description of source,

4	Date,

5.	Load number,

6.	Truck identification mark,

7.	Time of weighing,

8.	Gross weight of each load,

9.	Tare weights,

10.	Net weights,

11.	Scale operator's signature, and

12.	Contractor's certification.

The original daily weight record shall be furnished to the Engineer at the end of each shift.

The Engineer may, at random intervals, designate previously weighed vehicles to be reweighed, in his presence, to verify the weight of the materials being purchased. This will include empty or loaded vehicles as the Engineer may designate.

No direct payment will be made for furnishing scale operators, equipment, and incidentals required. Costs thereof will be subsidiary to bid prices of the material being weighed.

(7/26/95)S11M

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by K-III Directory Corp., 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (3/24/97)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon receipt of current schedules from the Contractor. (9/21/92)R137

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section shall be considered a material breach of contract. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04 DEFINITIONS AND TERMS

1.	Broker. A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with its own equipment and employees within its certified category. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE). A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts. The affirmative action measures that shall be taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer. A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer. A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver

the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis.

8.	Revised DBE Utilization Goal. The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C. The Revised DBE Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved. Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01 UTILIZATION GOAL. The Original DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total basic bid amount. In order for the work of the DBE to be credited towards meeting the Original DBE Utilization Goal at time of contract award, the DBE must be certified by the Department in a category covering the CUF to be performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid and Award. In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the contractor submits less DBE utilization on Form 25A325C than is required to meet the Original DBE Utilization Goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (25A321A) shall be submitted. If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than is required by the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

2.	Phase II - Construction. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE. Prior written request by the Contractor and approval from the Engineer is required for the replacement of a DBE for any reason. If DBE replacement is approved, the Contractor is obligated to replace the DBE with another DBE for the same work in order to still meet the Revised DBE Utilization Goal. If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work to have been performed by the replaced DBE in order to have the Revised DBE Utilization Goal reduced.

120-3.02 GOOD FAITH EFFORT. The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract. Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

1.	Consideration of all subcontractable items. The Contractor shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification at least 10 calendar days prior to bid opening to all DBEs listed in the Department's most current DBE Directory certified to perform those work items identified in Form 25A324 of the bidder's/Contractor's interest in securing the DBE's participation in the execution of the work. Each contact with the DBE shall be logged on a "Contact Report" (Form 25A321A).

4.	Request for DBE participation on specific items of work or services. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE quotes are for the exact same work or service. Where the Contractor rejects a DBE quote as being non-competitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding. Documentation of follow-up contacts shall be logged on the "Contact Report" (Form 25A321A).

Items 4. through 7. will be utilized to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF). Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

a.	regular dealer,

b.	manufacturer,

c.	broker,

d.	subcontractor

e.	joint-venture, or

f.	prime contractor.

In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE shall be certified in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b.	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

2.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

3.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted within that category to the CUF of a broker. (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation which could include the hauling of materials for that work.)

4.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

5.	Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the Revised DBE Utilization Goal.

6.	Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm shall not be credited toward the Revised DBE Utilization Goal. The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01), or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

7.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the Revised DBE Utilization Goal.

8.	The Engineer shall consider the following criteria when determining what CUF is being performed by the DBE:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below. Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site. All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work. An exception to this requirement may be permitted where the DBE must perform a specialty task or where the work is in a remote area. In such instance, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the work, if the Department considers this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value. Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved. Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control. DBE leases and payments for equipment must be documented; Contractor withholding or retainage for DBE labor and equipment usage is not permissible. Two-party checks to individuals are not permissible.

e.	The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as defined by the Department. The work or provision of goods or services shall have a market outside of the DBE program (must be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed a superfluous step in the contracting or purchasing process and no DBE credit will be allowed.

There shall be no DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

g.	All subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE shall control all business administration, accounting, billing, and payment transactions (this requirement does not preclude the two-party check allowance described under i., below). The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

i.	Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE.

Two-party checks may be issued by the Contractor on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Engineer shall be notified in writing in advance. DBE credit will not be given for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before any DBE credit may be credited. The DBE supervisor must be regularly employed by the DBE and designated as a key employee in the DBE's certification records with the Department prior to prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identify payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the quantity of work of a bid item which involves a DBE is reduced by the Department, the Original and Revised DBE Utilization Goals on Form 25A325C are reduced proportionately.

120-3.04 DEFAULT OF DBE. In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default. The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, both of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Revised DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, retainage may be withheld from progress payments. The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, payments will be reduced as a disincentive. The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after the Original DBE Utilization Goal established on Form 25A325C in terms of dollars has been met, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUF work performed by DBE subcontractors not needed in the calculation to meet the Original DBE Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

Payment of the incentive will be made on the final estimate. The disincentive will be withheld in the form of retainage during the course of the project. If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

A Change Order is not required for DBE Adjustment. The Notice To Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(6/6/94)S33

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-2.02 CLEARING. Add the following: No equipment on wheels or tracks shall be used when clearing in wetland areas. Care shall be taken during the clearing operation to protect the grass and/or moss cover. Stumps shall be cut flush with the ground, or left a maximum of 0.6 meters above the natural ground where a minimum cover below subgrade will be 1.2 meters.

201-4.01 BASIS OF PAYMENT. Add the following: Clearing in wetland areas will be paid under Item 201(3B), Clearing and Grubbing.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-2.01 GENERAL. Add the following: This work also includes the removal and disposal of two derelict boats located on parcel No.5, approximately Station 4+950 LT. One boat is a 9.75 meter (32 foot) commercial fishing boat, No. 8601. The second boat is a double ender sail boat about 6 meter (20 foot) in length.

Burning of creosote-treated wood is not permitted.

202-2.03 REMOVAL OF PIPE. Delete this subsection in its entirety and substitute the following: Structural plate pipes arches, pipes and headwalls identified on the plans to be salvaged shall be carefully removed, marked for reassembly, disassembled, cleaned and delivered to the State of Alaska Maintenance Facility in Dillingham. Cleaning shall consist of washing individual pieces to remove dirt and debris. Small items such as bolts, nuts, washers, angle brackets, etc. shall be segregated and placed in large plastic buckets. Buckets shall be loaded to not more than 20 kg. All other pipes listed for removal will become the property of the Contractor.

202-4.01 BASIS OF PAYMENT. Delete the second paragraph and substitute the following: Pipe removal and pavement removal will be paid for at the contract price per unit specified in the contract, which price shall be full compensation for removal and disposal, or removal and salvage, of such items, including excavation and subsequent backfill incidental to their removal. The price shall also include salvage of materials removed, their custody, preservation, transportation to storage area, stockpiling as required, and disposal as provided herein.

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-3.02 EMBANKMENT CONSTRUCTION. Delete the last sentence in the last paragraph and replace with the following: The top surface of the surcharge shall be compacted to provide a firm driving surface during construction.

On page 62, delete the first sentence of the fourth paragraph, and substitute the following: Roadway embankments shall be placed in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m. (12/13/96)R23M

Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work. (12/13/96)R23M

Add the following: When geotextile is encountered during excavation, the geotextile shall be carefully cut and removed within the area to be excavated. The Contractor shall take care not to disturb the geotextile under the existing road beyond the excavation limit. If the existing geotextile beyond the excavation limit is damaged by the Contractor, the damaged geotextile shall be replaced at the Contractor's expense.

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL. Delete the second paragraph and substitute the following: Embankment material, other than Select Material Type D, shall be compacted to not less than 95 percent of the maximum density. Maximum densities will be determined by AASHTO T 180, or ATM T-12. In place field densities will be determined by ATM T-3 or ATM T-11. (1/8/97)R193

Add the following: The top 200 mm of embankment shall be compacted to not less than 98% of maximum density.

203-5.01 BASIS OF PAYMENT. Delete the sixth paragraph and replace with the following: The placing of temporary surcharge material will be paid as Borrow. Removing temporary surcharge and placing the material to the location shown on the plans will be paid as Unclassified Excavation.

Add the following: Cutting, removing and disposing of geotextile encountered during excavation will not be paid for directly but will be considered subsidiary to other items.

Excavation for special ditches and stream channels will be paid as Unclassified Excavation.

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Bedding and backfill materials shall meet the requirements for Selected Material, Type A, as specified in subsection 703-2.07 Selected Material. Pipe bedding and backfill material shall also pass the 75 mm sieve.

Selected Material, Type A pipe backfill shall extend a minimum of 300 mm above the pipe or to bottom of asphalt treated base, whichever is less. Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material. Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material. All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the third paragraph: Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material. Compaction may be as approved by the Engineer.

(11/04/94)R25M

SECTION 304

SUBBASE

Special Provisions

304-2.01 MATERIALS. Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for subbase, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 300 µm | 5-34 |
| 150 µm | 3-22 |
| 75 µm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

304-3.01 CONSTRUCTION REQUIREMENTS. Add the following: If recycled asphalt material is substituted for subbase, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

304-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for subbase, it will be paid for as Item 304(1) Subbase, Grading C, at the unit price shown on the bid schedule for that item.

R176M

SECTION 306

ASPHALT TREATED BASE COURSE

Special Provisions

306-1.01 DESCRIPTION. Add the following: The Contractor will have the option of using emulsified asphalt for the manufacture of the asphalt treated base. Asphalt treated base course will be manufactured using 3% by weight of mix of AC-5 asphalt cement, or 5% by weight of mix of CSS-1 asphalt emulsion. If the Contractor chooses to use emulsified asphalt, Section 307 specifications shall be applicable. In either case, payment will be made under 306(4) Asphalt Treated Base Course (Includes oil).

306-2.01 AGGREGATES. Delete this subsection in its entirety and substitute the following: The aggregate shall conform to the requirements of Subsection 703-2.03. The gradation shall be D-1 as shown in table 703-2.

The acceptance of aggregate shall be based on representative samples taken from the aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt. The aggregate gradation will be determined by ATM T-7.

306-2.02 ASPHALT. Delete the first sentence and substitute the following: Asphalt material shall be AC-5.

306-2.03 COMPOSITION OF MIXES. Delete this subsection in its entirety.

306-3.03 ASPHALT PLANTS. Delete this subsection in its entirety and substitute the following: Mixing plants shall conform to Subsection 401-3.03.

306-3.04 HAULING EQUIPMENT. Delete this subsection in its entirety and substitute the following: Hauling equipment shall conform to Subsection 401-3.04.

306-3.05 SPREADING EQUIPMENT. Delete this subsection in its entirety and substitute the following: The asphalt mixture shall be placed with a self-propelled paving machine.

306-3.06 ROLLERS. Delete this subsection in its entirety and substitute the following: The number and the weight of the rollers shall be sufficient to compact the mixture to the required density and smoothness while the mixture is still in a workable condition, and be capable of maintaining the pace of the placement operation.

306-3.07 PREPARATION OF ASPHALT. Delete this subsection in its entirety and substitute the following: Preparation of asphalt shall conform to Subsection 401-3.08.

306-3.09 MIXING. Delete this subsection in its entirety and substitute the following: Mixing of asphalt treated base course materials shall conform to Subsection 401-3.10.

306-3.11 COMPACTION. Delete this subsection in its entirety and substitute the following: The amount of compactive effort required shall be determined by the control strip method. The control strip shall be evaluated with the use of a nuclear density gauge to establish a roller pattern. The location of the control strip will be designated by the Engineer and shall be one half the finished roadway width and 100 meters long.

The Contractor shall be responsible for the development of the control strip. The Contractor shall select a minimum of two sites on the control strip and take a 15 second minimum reading with the nuclear densometer at each site for every roller pass over the test site. Rolling shall continue until there is less than 16 kg/m³ increase in unit weight in the averaged density readings per roller pass. This process will establish the roller pattern to be used for the compaction of the asphalt treated base course. A copy of the density readings developing the control strip will be supplied to the Engineer. Acceptance of the compaction effort is based on Engineer's approval.

306-4.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: Asphalt treated base course will be measured by the megagram in accordance with Section 109 and shall include the asphalt material (AC-5 or CSS-1). If the Engineer determines that anti-stripping additive is needed, the anti-stripping additive will be included in the weight measured for payment at no increase in the contract unit price.

306-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

306(4)	Asphalt Treated Base Course (Includes Oil)	Megagram

SECTION 307

EMULSIFIED ASPHALT TREATED BASE

Special Provisions

307-2.01 AGGREGATE. Delete the fist and second paragraphs and substitute the following: The aggregate shall conform to the requirements of Subsection 703-2.03. The gradation shall be D-1 as shown in table 703-2.

The acceptance of aggregate shall be based on representative samples taken from the aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt. The aggregate gradation will be determined by ATM T-7.

Add the following to the third paragraph: The aggregate material shall be moistened or dried, as necessary, to achieve 2-4 percent moisture content at the time of mixing. Covering the stockpile with a tarp is recommended.

307-2.02 ASPHALT. Delete the last sentence and substitute the following: Emulsified asphalt shall be CSS-1.

307-2.03 PORTLAND CEMENT. Delete this subsection in its entirety.

307-2.04 COMPOSITION OF MIXES. Delete this subsection in its entirety.

Add the following subsection:

307-3.00 PROCESS QUALITY CONTROL. The Contractor is responsible for process control sampling and testing of the aggregates in accordance with Subsection 106-1.02.

The Contractor shall employ a qualified person or company to perform the process control testing. Failure to perform process control forfeits the Contractor's right to retests. A pre-placement meeting will be held a minimum of 5 days prior to the initial placement of the emulsified asphalt treated base control strip.

307-3.01 MIXING. Delete this subsection in its entirety and substitute the following:

1.	Emulsified asphalt treated base material shall be mixed at an approved central mixing plant. Water, if required, shall be added and mixed with the aggregate prior to the application of the asphalt emulsion.

2.	Central plants may be either batch or continuous twin-shaft pugmill units and shall be equipped with adequate proportioning devices to control aggregate, asphalt, and water.

The aggregate, emulsified asphalt, and water shall be combined in the mixing plant in the specified proportions. The mixing time shall be adjusted to the minimum time which will provide a complete coating of the aggregate particles.

307-3.04 HAULING EQUIPMENT. Delete this subsection in its entirety and substitute the following: Hauling equipment shall conform to Subsection 401-3.04.

307-3.05 SPREADING EQUIPMENT. Delete this subsection in its entirety and substitute the following: The asphalt mixture shall be placed and/or spread with an approved mechanical spreader. Motor graders will not be permitted.

307-3.06 ROLLERS. Delete this subsection in its entirety and substitute the following: The number and the weight of the rollers shall be sufficient to compact the mixture to the required density and smoothness while the mixture is still in a workable condition, and shall be capable of maintaining the pace of the placement operation.

307-3.08 COMPACTION. Delete this subsection in its entirety and substitute the following: The amount of compactive effort required shall be determined by the control strip method. The control strip shall be evaluated with the use of a nuclear density guage to establish a roller pattern. The location of the control strip will be designated by the Engineer and shall be one half the finished roadway width and 100 meters long.

The Contractor shall be responsible for the development of the control strip. The Contractor shall select a minimum of two sites on the control strip and take 15 second minimum reading with the nuclear densometer at each site for every roller pass over the test site. Rolling shall continue until there is less than 16 kg/m³ increase in unit weight in the averaged density readings per roller pass. This process will establish the roller pattern to be used for the compaction of the asphalt treated base course. A copy of the density readings developing the control strip will be supplied to the Engineer. Acceptance of the compaction effort is based on Engineer's approval.

307-4.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: See Subsection 306-4.01 for the method of measurement.

307-5.01 BASIS OF PAYMENT. Delete this subsection in its entirety and substitute the following: This work will be paid under Subsection 306-5.01 and Item 306(4) Asphalt Treated Base Course (Includes oil).

Delete Section 401 in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-1.01 DESCRIPTION. This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

401-2.01 COMPOSITION OF ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN. Asphalt concrete mixtures shall be composed of aggregate, asphalt cement, and required additives combined within the limits for the type and class of asphalt concrete specified in the contract.

The Contractor shall provide an asphalt concrete mixture that meets the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete.

At least 15 calendar days prior to the production of asphalt concrete pavement mixture, the Contractor shall submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile. The proposed gradations must meet the requirements of Table 703-3, Asphalt Concrete Aggregate, for each type of asphalt concrete pavement specified in the bid schedule. Asphalt concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended. Sample sizes: 45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance in accordance with Section 106, and a temperature viscosity curve for the asphalt cement.

4.	A 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

From this information, the Engineer will establish the Job Mix Design which will become a part of the contract and shall be followed unless modified in writing. The Job Mix Design will be determined in accordance with ATM T-17 (version 01/93) and evaluated for conformance with the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete. Job Mix Design test results will be available within 7 working days after submittal. Approved Job Mix Designs will specify the target value for asphalt cement, additives, and the allowable temperature range for mixing.

Changes in the Job Mix Design warranted by changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio shall be submitted by the contractor in the same manner as the original submittal. A new Job Mix Design will only apply to asphalt concrete mixture produced after the Contractor submittal of the new aggregate gradation.

All mix designs after a Job Mix Design has been approved for the Type and Class of Asphalt Concrete will be assessed a fixed fee of $1,500.00 each.

Approved Job Mix Designs will have the full tolerances shown in Table 401-2 applied and will not be limited to the broad band listed in Table 703-3. Tolerances for the largest sieve specified will be plus 0% and minus 1%.

Temporary pavement shall meet the minimum asphalt concrete mix design requirements for Asphalt Concrete Type II, Class B.

Table 401-1

Asphaltic Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS "A" | CLASS "B" | CLASS "C" |
| --- | --- | --- | --- |
| Stability, newton, min. | 8,000 | 5,340 | 3,340 |
| Flow, 0.25 mm | 8-14 | 8-16 | 8-18 |
| Voids in total mix, percent | 3-5 | 3-5 | 2-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 | 35 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 | N/A |
| Voids in the mineral aggregate (VMA), min. |  |  |  |
| Type I Type II Type III | 12.0 13.0 14.0 | 11.0 12.0 13.0 | N/A N/A N/A |

*Dust-asphalt ratio is defined as the percent of material passing the 75μm sieve divided by the percent of asphalt (calculated by weight of mix).

401-2.02 AGGREGATES. Aggregate shall conform to the requirements of Subsection 703-2.04.

Aggregates for asphalt concrete mixtures shall be divided into a minimum of 2 piles, one coarse and one fine. If blend sand is used, it shall be an additional pile.

401-2.03 ASPHALT MATERIALS. The grade of asphalt cement will be specified in the bid schedule. The asphalt cement shall conform to the applicable requirements of Section 702. Asphalt cement may be conditionally accepted at the source. If the material is to be conditionally accepted at the source, the Contractor shall provide a manufacture's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the material is shipped.

If there is a change in the source of the asphalt cement, or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted for approval.

401-2.04 ANTI-STRIP ADDITIVES. Anti-strip agents shall be used in the proportions determined by ATM T-14 and shall be included in the approved Job Mix Design. At least 70% of the aggregate shall remain coated when tested in accordance with ATM T-14.

401-2.05 PROCESS QUALITY CONTROL. It is expressly understood that the contractor is solely responsible for the sampling and testing of material for process control of the asphalt concrete mixture in accordance with Subsection 106-1.02.

The Contractor shall employ a qualified person or company to perform process control testing. A process control plan shall be submitted at the project pre-construction conference in accordance with Subsection 106-1.02. Failure to perform process control forfeits the Contractor's right to retests as provided for in Subsection 401-4.02.

A paving and plant control plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations. The paving and plant control plan shall address joint construction, outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the asphalt concrete mixture. This plan shall also include a proposed testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. The asphalt concrete mixture shall not be placed on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture. No asphalt concrete mixture for a leveling course shall be placed unless the surface temperature is 5 degrees Celsius or warmer.

401-3.02 EQUIPMENT. All equipment shall be in good working order and free of asphalt concrete mixture buildup. All equipment shall be available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

401-3.03 BITUMINOUS MIXING PLANTS. The Contractor shall use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. The Contractor shall calibrate the asphalt mixing plant and furnish copies of the data to the Engineer at least 2 days prior to asphalt concrete mixture production.

The asphalt mixing plant shall have a scalping screen to prevent oversize material or debris from being incorporated into the asphalt concrete mixture. Aggregate and asphalt cement sampling locations meeting OSHA safety requirements shall be provided.

Proportioning (batch) scales shall not be used for weighing material for payment. Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.04 HAULING EQUIPMENT. Trucks used for hauling asphalt mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List. Diesel fuel or fuel oil shall not be used as an asphalt release agent.

Each truck shall have a cover of canvas or other suitable material of such size as to protect the asphalt concrete mixture, when required, so that the mixture shall be delivered to the asphalt paver at the proper temperature.

401-3.05 ASPHALT PAVERS. Asphalt pavers shall be self-propelled units provided with a heated vibratory screed. Grade and cross slope shall be controlled through the use of automatic grade and slope control devices. The paver screed control system shall be automatically actuated by the use of an erected string line, mobile stringline (ski) on the high side of the paver at least 9 meters in length, or other approved grade follower. Grade control shall be used on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation. The hopper shall be equipped with a distribution system to place the asphalt concrete mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture. Screed extensions used for paving a constant width shall be heated and vibrated. Auger extensions shall be within 0.5 meters of the screed extension on both sides.

The use of a Layton Box will be allowed on bikepaths, sidewalks, pathways and medians.

401-3.06 ROLLERS. The Contractor shall supply a sufficient number and weight of rollers to compact the mixture to the required density while maintaining the pace of the paving operations. Rollers shall be static or vibratory steel wheel and pneumatic tire type rollers. The rollers shall be self propelled and capable of reversing without backlash. They shall be specifically designed to compact hot asphalt concrete mixtures. The use of equipment which results in crushing of the aggregate will not be permitted. Pneumatic tire rollers shall be fully skirted, have an operating weight per tire of at least 1,360 kilograms and be operated in accordance with the manufacturer's instructions.

401-3.07 PREPARATION OF EXISTING SURFACE. Existing surfaces shall be prepared in conformance with the plans and specifications. Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

Contact surfaces of curbing, gutters, manholes, sawcut pavement, and other structures shall be coated with a uniform coating of tack coat material conforming to Section 402 prior to the asphalt concrete mixture being placed.

Surfaces which have received a prime coat shall be allowed to cure. Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixture.

401-3.08 PREPARATION OF ASPHALT. A continuous supply of the asphalt cement shall be supplied to the mixer at a uniform temperature, within 14 degrees Celsius of the Job Mix Design mixing temperature.

401-3.09 PREPARATION OF AGGREGATES. The aggregate for the asphalt concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified. The burner on the dryer shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate. Any asphalt concrete mixture in which soot or fuel is present shall be wasted and no payment made.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by ATM T-25.

401-3.10 MIXING. The aggregate, asphalt cement and additives shall be combined in the mixer in the amounts required by the Job Mix Design.

The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained. For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement. Wet mixing time shall be adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

The temperature of the asphalt concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Asphalt concrete mixture drawn from silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Rejected asphalt concrete mixture shall be disposed of by the Contractor at no cost to the State.

401-3.12 SPREADING AND PLACING. The asphalt concrete mixture shall be laid upon a surface approved by the Engineer, spread and struck off and compacted to the required compacted thickness. Asphalt pavers shall be used to distribute the asphalt concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of Subsection 401-3.14. Asphalt pavers shall also be used to distribute asphalt concrete mixture for leveling course unless otherwise allowed.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the asphalt concrete mixture shall be spread, raked and luted by hand tools. For such areas the asphalt concrete mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge dropoff. When the outside pavement edge dropoff exceeds 50 millimeters, approved material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted. Paving shall not begin until all adjacent curb has been poured and cured for 72 hours.

Asphalt concrete pavement to be placed over bridge deck membranes shall not be placed until the membrane has cured according to the manufacturer's specifications. Vehicles, except the paving machine and trucks hauling the asphalt concrete mixture for the overlay, shall not be operated on the membrane. Paving machines used on the membrane shall be rubber-tired or rubber-tracked. The Contractor shall follow the manufacturer's published minimum and maximum temperature limitations for the asphalt concrete mixture. Vibratory rollers, with the vibrator engaged, shall not be used on bridge decks.

401-3.13 COMPACTION. Immediately after the asphalt concrete mixture has been spread, struck-off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.

The target value for density will be 94% of the maximum specific gravity (MSG), as determined in accordance with AASHTO T 209. For the first lot of each type of asphalt concrete pavement, the MSG will be determined by the Job Mix Design. For additional lots, the MSG will be determined by the sample from the first sublot of the lot. Acceptance testing for field density will be determined in accordance with ATM T-18 except that a minimum 150 mm diameter core is required. (Acceptance testing for field density of leveling course or temporary pavement will not be done.)

The asphalt concrete pavement, including leveling course, shall receive a minimum of 3 complete passes with a pneumatic-tired roller. A pass is defined as once over each point on the pavement surface.

Areas not accessible to the rollers shall be graded with rakes and lutes and compacted with mechanical tampers. For depressed areas a trench roller may be used to achieve the required compaction.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Joints shall be constructed to ensure a continuous bond between sections of the course. All joints shall present the same texture and smoothness as other sections of the course.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Improperly formed joints resulting in surface irregularities shall be removed full depth, replaced with new material, and thoroughly compacted. Rolling of joints after the material has cooled below 65 degrees Celsius shall not be allowed. All pavement removal shall be precut to a neat line with a power driven saw.

A tack coat of asphalt cement or asphalt emulsion shall be applied on all cold joints and allowed to break prior to placing any fresh asphalt concrete mixture against the joint. This work shall be completed by the Contractor just prior to paving.

Transverse joints shall be formed by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead. Transverse joints shall not be perpendicular to centerline, but at a skew between 15-25 degrees.

The longitudinal joints in one layer shall offset those in the layer immediately below by at least 150 millimeters. The joints shall be at centerline or lane lines. Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset 50 to not more than 150 millimeters from the edge of the stripe.

401-3.15 SURFACE TOLERANCE. The surface will be tested after final rolling at selected locations using a 3 meter straightedge. The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 5 millimeters.

401-3.16 PATCHING DEFECTIVE AREAS. Any asphalt concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective as determined by the Engineer shall be removed. Skin patching will not be permitted. Defective materials shall be removed for the full thickness of the course. The pavement shall be cut so that the sides are parallel to the direction of traffic and so that the edges are vertical. Edges shall be coated with a tack coat of material conforming to Section 402 and allowed to cure. Fresh asphalt concrete mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements. The asphalt concrete mixture shall be compacted to the density specified. All costs associated with the patching of defective areas shall be borne by the Contractor.

Any asphalt concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective shall be removed and replaced with fresh hot asphalt concrete mixture, which shall be compacted to conform with the surrounding area. Any area showing an excess or deficiency of asphalt cement shall be removed and replaced.

401-4.01 METHOD OF MEASUREMENT. The asphalt concrete mixture will be measured by the megagram or by the square meter in accordance with Section 109. The weight used will be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material and anti-stripping additive in the mixture.

The weight of asphalt cement will be calculated using the percent of asphalt cement for each sublot multiplied by the total megagrams represented by that sublot. Percent of asphalt cement will be determined by ATM T-23. The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

No payment will be made for any asphalt cement in excess of 0.4% above the optimum asphalt content specified in the Job Mix Design.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of each type of asphalt concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance. The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project. Acceptance sampling and testing shall be performed by the Engineer. The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams. The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection. If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot shall include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot. The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density, and gradation in accordance with this subsection. The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing. If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed. If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result. If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with Sub-section 401-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, asphalt concrete pavement will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the asphalt concrete pavement to the specified depth and finished surface requirements and tolerances. Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees Celsius prior to completing compaction, or is in any other way defective, shall be removed and replaced with new asphalt concrete pavement. Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction, or at the end of the auger. Asphalt cement content will be determined by ATM T-23.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device or from the stopped conveyor belt. The aggregate gradation will be determined according to ATM T-7. Sampling devices for obtaining aggregate samples on drum mix plants shall be located on the conveyor system delivering combined aggregates into the drum. The sampling device shall divert aggregate from the full width of the conveyor system and shall be maintained to provide a representative sample of aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to ATM T-7. The size of samples for extraction will be in conformance with AASHTO T 164 and extracted gradations will be determined according to AASHTO T 30.

Within 24 hours of final rolling, the Contractor shall cut full depth samples from the finished mat lift for density acceptance testing. One core sample with a minimum diameter of 6 inches shall be taken from each sublot. The samples shall be neatly cut by a core drill at the randomly selected locations marked by the Engineer. ATM T-18 will be used to determine density. No samples shall be cut from asphalt concrete mats on bridge decks. Failure to cut core samples for density acceptance testing within the specified period will result in a penalty of $100.00 per sample per day. The accrued amount will be subtracted from the Contractor's payment for asphalt concrete pavement.

All voids left by sampling shall be backfilled with new asphalt concrete mixture and compacted within 24 hours of sampling. Failure to backfill voids left by sampling in the specified period will result in a penalty of $100.00 per hole per day. The accrued amount will be subtracted from the Contractor's payment for asphalt concrete pavement.

The Contractor may request a retest of any sample not within specification limits. This request shall be in writing and delivered to the Engineer within 7 days of receipt of the initial test result. Verbal requests with the written request to be delivered after the specified 7 days will not be accepted. The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s). The Engineer will mark the sample location for the retest. Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s). The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample will be allowed.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 4,500 megagrams, except as defined in Subsection 401-4.02.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis - Standard Deviation (Specification Conformance Analysis) Method using the procedures listed to determine the total estimated percent of the lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results shall not be included in the price adjustment calculations. If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment. The density test results for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s). Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0% and a contractor's risk of 5.0% unless otherwise specified. AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100% pay. The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained. The maximum pay factor obtainable is 1.05. The maximum pay factor for the largest sieve size specification for gradation will be 1.00. The price adjustment is based on the lowest of two pay factors. The first factor is a composite pay factor for asphalt concrete mixture which includes gradation and asphalt cement content. The second factor is a separate pay factor for density.

A lot containing material with less than a 1.00 pay factor, may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.

A lot containing material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11. The Contractor may submit a written request for acceptance of the material at a reduced price or approved correction. Such a request shall include an engineering analysis showing expected effects on performance. The Engineer will determine whether or not the material may remain in place at the reduced price.

The Engineer can reject material which appears to be defective based on visual inspection. Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis. Procedures for computation of composite pay factor are as follows:

1.	Eliminate test results found to be outliers by SP-7 (the Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ	= summation of

x=Σxn

x	= individual test value to xn

n	= total number of test values

x	is rounded to the nearest tenth for density and all sieve sizes except the 75 μm sieve. x is rounded to the nearest hundredth for asphalt cement content and the 75 μm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)	=	summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2	=	square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the 75 μm sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the 75 μm sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieve sizes except the 75 μm sieve. Use s = 0.020 for asphalt cement content and the 75 μm sieve.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL). For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2. The TV is the specification value defined by the Job Mix Design. The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

4.	Compute the Upper Quality Index (QU):

Where:	USL	= Upper Specification Limit

QU=USL-xs

QU	is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

QL=x-LSLs

Where:	LSL	= Lower Specification Limit

QL	is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 401-3.

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 401-3.

8.	Determine the Quality Level (the total percent within specification limits) for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, determine the lot Density Pay Factor (DPF) and gradation and asphalt cement content pay factors (PF) from Table 401-4.

10.	Compute the asphalt concrete mixture Composite Pay Factor (CPF) for asphalt content and gradation using the following formula:

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 401-5 is used to determine the weight factor (f) for each sieve size, and asphalt cement content.

Table 401-2

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

Measured Characteristics		LSL			USL

19.0 mm				TV-6.0		TV+6.0

12.5 mm				TV-6.0		TV+6.0

9.5 mm				TV-6.0		TV+6.0

4.75 mm				TV-6.0		TV+6.0

2.36 mm				TV-6.0		TV+6.0

1.18 mm				TV-5.0		TV+5.0

600 μm				TV-4.0		TV+4.0

300 μm				TV-4.0		TV+4.0

150 μm				TV-3.0		TV+3.0

75 μm					TV-2.0		TV+2.0

Asphalt %				TV-0.40		TV+0.40

Density				 92%			 98%

TABLE 401-3

Upper Quality Index (QU) or Lower Quality Index (QL)

| PU or PL | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 100 | 1.16-10.0 | 1.48-10.0 | 1.68-10.0 | 1.81-10.0 | 1.90-10.0 | 1.96-10.0 | 2.01-10.0 | 2.05-10.0 | 2.10-10.0 | 2.15-10.0 |
| 99 | - | 1.45-1.47 | 1.61-1.67 | 1.71-1.80 | 1.77-1.89 | 1.82-1.95 | 1.85-2.00 | 1.87-2.04 | 1.92-2.09 | 1.94-2.14 |
| 98 | 1.15 | 1.42-1.44 | 1.55-1.60 | 1.63-1.70 | 1.68-1.76 | 1.71-1.81 | 1.73-1.84 | 1.75-1.86 | 1.78-1.91 | 1.80-1.93 |
| 97 | - | 1.39-1.41 | 1.50-1.54 | 1.56-1.62 | 1.60-1.67 | 1.62-1.70 | 1.64-1.72 | 1.66-1.74 | 1.68-1.77 | 1.69-1.79 |
| 96 | 1.14 | 1.36-1.38 | 1.45-1.49 | 1.50-1.55 | 1.53-1.59 | 1.55-1.61 | 1.56-1.63 | 1.57-1.65 | 1.59-1.67 | 1.60-1.68 |
| 95 | - | 1.33-1.35 | 1.40-1.44 | 1.44-1.49 | 1.47-1.52 | 1.48-1.54 | 1.49-1.55 | 1.50-1.56 | 1.51-1.58 | 1.52-1.59 |
| 94 | 1.13 | 1.30-1.32 | 1.36-1.39 | 1.39-1.43 | 1.41-1.46 | 1.42-1.47 | 1.43-1.48 | 1.44-1.49 | 1.45-1.50 | 1.45-1.51 |
| 93 | - | 1.27-1.29 | 1.32-1.35 | 1.34-1.38 | 1.36-1.40 | 1.37-1.41 | 1.37-1.42 | 1.38-1.43 | 1.38-1.44 | 1.39-1.44 |
| 92 | 1.12 | 1.24-1.26 | 1.28-1.31 | 1.30-1.33 | 1.31-1.35 | 1.31-1.36 | 1.32-1.36 | 1.32-1.37 | 1.33-1.37 | 1.33-1.38 |
| 91 | 1.11 | 1.21-1.23 | 1.24-1.27 | 1.25-1.29 | 1.26-1.30 | 1.26-1.30 | 1.27-1.31 | 1.27-1.31 | 1.27-1.32 | 1.28-1.32 |
| 90 | 1.10 | 1.18-1.20 | 1.20-1.23 | 1.21-1.24 | 1.21-1.25 | 1.22-1.25 | 1.22-1.26 | 1.22-1.26 | 1.22-1.26 | 1.23-1.27 |
| 89 | 1.08-1.09 | 1.15-1.17 | 1.16-1.19 | 1.17-1.20 | 1.17-1.20 | 1.17-1.21 | 1.17-1.21 | 1.18-1.21 | 1.18-1.21 | 1.18-1.22 |
| 88 | 1.07 | 1.12-1.14 | 1.13-1.15 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.17 | 1.13-1.17 | 1.13-1.17 |
| 87 | 1.05-1.06 | 1.09-1.11 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.04 | 1.06-1.08 | 1.06-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.02-1.03 | 1.03-1.05 | 1.02-1.05 | 1.02-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 |
| 84 | 1.01 | 1.00-1.02 | 0.99-1.01 | 0.98-1.01 | 0.98-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 |
| 83 | 0.98-1.00 | 0.97-0.99 | 0.96-0.98 | 0.95-0.97 | 0.94-0.97 | 0.94-0.96 | 0.94-0.96 | 0.93-0.96 | 0.93-0.96 | 0.93-0.96 |
| 82 | 0.97 | 0.94-0.96 | 0.92-0.95 | 0.91-0.94 | 0.91-0.93 | 0.90-0.93 | 0.90-0.93 | 0.90-0.92 | 0.90-0.92 | 0.89-0.92 |
| 81 | 0.94-0.96 | 0.91-0.93 | 0.89-0.91 | 0.88-0.90 | 0.87-0.90 | 0.87-0.89 | 0.87-0.89 | 0.86-0.89 | 0.86-0.89 | 0.86-0.88 |
| 80 | 0.92-0.93 | 0.88-0.90 | 0.86-0.88 | 0.85-0.87 | 0.84-0.86 | 0.83-0.86 | 0.83-0.86 | 0.83-0.85 | 0.83-0.85 | 0.82-0.85 |
| 79 | 0.90-0.91 | 0.85-0.87 | 0.83-0.85 | 0.81-0.84 | 0.81-0.83 | 0.80-0.82 | 0.80-0.82 | 0.80-0.82 | 0.79-0.82 | 0.79-0.81 |
| 78 | 0.88-0.89 | 0.82-0.84 | 0.79-0.82 | 0.78-0.80 | 0.77-0.80 | 0.77-0.79 | 0.77-0.79 | 0.76-0.79 | 0.76-0.78 | 0.76-0.78 |
| 77 | 0.85-0.87 | 0.79-0.81 | 0.76-0.78 | 0.75-0.77 | 0.74-0.76 | 0.74-0.76 | 0.73-0.76 | 0.73-0.75 | 0.73-0.75 | 0.72-0.75 |
| 76 | 0.83-0.84 | 0.76-0.78 | 0.73-0.75 | 0.72-0.74 | 0.71-0.73 | 0.71-0.73 | 0.70-0.72 | 0.70-0.72 | 0.70-0.72 | 0.69-0.71 |
| 75 | 0.80-0.82 | 0.73-0.75 | 0.70-0.72 | 0.69-0.71 | 0.68-0.70 | 0.67-0.70 | 0.67-0.69 | 0.67-0.69 | 0.67-0.69 | 0.66-0.68 |
| 74 | 0.77-0.79 | 0.70-0.72 | 0.67-0.69 | 0.66-0.68 | 0.65-0.67 | 0.64-0.66 | 0.64-0.66 | 0.64-0.66 | 0.63-0.66 | 0.63-0.65 |
| 73 | 0.75-0.76 | 0.67-0.69 | 0.64-0.66 | 0.63-0.65 | 0.62-0.64 | 0.61-0.63 | 0.61-0.63 | 0.61-0.63 | 0.60-0.62 | 0.60-0.62 |
| 72 | 0.72-0.74 | 0.64-0.66 | 0.61-0.63 | 0.60-0.62 | 0.59-0.61 | 0.58-0.60 | 0.58-0.60 | 0.58-0.60 | 0.58-0.59 | 0.57-0.59 |
| 71 | 0.69-0.71 | 0.61-0.63 | 0.58-0.60 | 0.57-0.59 | 0.56-0.58 | 0.56-0.57 | 0.55-0.57 | 0.55-0.57 | 0.55-0.57 | 0.54-0.56 |
| 70 | 0.66-0.68 | 0.58-0.60 | 0.55-0.57 | 0.54-0.56 | 0.53-0.55 | 0.53-0.55 | 0.52-0.54 | 0.52-0.54 | 0.52-0.54 | 0.51-0.53 |
| 69 | 0.63-0.65 | 0.55-0.57 | 0.52-0.54 | 0.51-0.53 | 0.50-0.52 | 0.50-0.52 | 0.49-0.51 | 0.49-0.51 | 0.49-0.51 | 0.49-0.50 |
| 68 | 0.60-0.62 | 0.52-0.54 | 0.48-0.51 | 0.48-0.50 | 0.47-0.49 | 0.47-0.49 | 0.47-0.48 | 0.46-0.48 | 0.46-0.48 | 0.46-0.48 |
| 67 | 0.57-0.59 | 0.49-0.51 | 0.46-0.47 | 0.45-0.47 | 0.45-0.46 | 0.44-0.46 | 0.44-0.46 | 0.44-0.45 | 0.43-0.45 | 0.43-0.45 |
| 66 | 0.53-0.56 | 0.46-0.48 | 0.44-0.45 | 0.42-0.44 | 0.42-0.44 | 0.41-0.43 | 0.41-0.43 | 0.41-0.43 | 0.41-0.42 | 0.40-0.42 |
| 65 | 0.50-0.52 | 0.43-0.45 | 0.41-0.43 | 0.40-0.41 | 0.39-0.41 | 0.39-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.39 |
| 64 | 0.47-0.49 | 0.40-0.42 | 0.38-0.40 | 0.37-0.39 | 0.36-0.38 | 0.36-0.38 | 0.36-0.37 | 0.35-0.37 | 0.35-0.37 | 0.35-0.37 |
| 63 | 0.44-0.46 | 0.37-0.39 | 0.35-0.37 | 0.34-0.36 | 0.33-0.35 | 0.33-0.35 | 0.33-0.35 | 0.33-0.34 | 0.32-0.34 | 0.32-0.34 |
| 62 | 0.40-0.43 | 0.34-0.36 | 0.32-0.34 | 0.31-0.33 | 0.31-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.31 | 0.30-0.31 |
| 61 | 0.37-0.39 | 0.31-0.33 | 0.29-0.31 | 0.28-0.30 | 0.28-0.30 | 0.28-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 |
| 60 | 0.33-0.36 | 0.28-0.30 | 0.26-0.28 | 0.26-0.27 | 0.25-0.27 | 0.25-0.27 | 0.25-0.26 | 0.25-0.26 | 0.24-0.26 | 0.24-0.26 |
| 59 | 0.30-0.32 | 0.25-0.27 | 0.24-0.25 | 0.23-0.25 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.23 | 0.22-0.23 |
| 58 | 0.26-0.29 | 0.22-0.24 | 0.21-0.23 | 0.20-0.22 | 0.20-0.21 | 0.20-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 |
| 57 | 0.23-0.25 | 0.19-0.21 | 0.18-0.20 | 0.17-0.19 | 0.17-0.19 | 0.17-0.19 | 0.17-0.18 | 0.17-0.18 | 0.17-0.18 | 0.16-0.18 |
| 56 | 0.19-0.22 | 0.16-0.18 | 0.15-0.17 | 0.15-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.15 |
| 55 | 0.15-0.18 | 0.13-0.15 | 0.12-0.14 | 0.12-0.14 | 0.12-0.13 | 0.12-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 |
| 54 | 0.12-0.14 | 0.10-0.12 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 |
| 53 | 0.08-0.11 | 0.07-0.09 | 0.07-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.05-0.07 | 0.04-0.06 | 0.04-0.06 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.04 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

NOTE: For negative values of QU or QL, use absolute values of QU or QL. PU or PL is then equal to 100 minus the table value of PU or PL.

TABLE 401-4

Required Quality Level (QL) for a given sample size (n) and

a given Pay Factor (PF)

| Pay Factor | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.05 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 1.04 | 90-99 | 91-99 | 92-99 | 93-99 | 93-99 | 93-99 | 94-99 | 94-99 | 95-99 | 95-99 |
| 1.03 | 80-89 | 85-90 | 87-91 | 88-92 | 89-92 | 90-92 | 91-93 | 91-93 | 92-94 | 93-94 |
| 1.02 | 75-79 | 80-84 | 83-86 | 85-87 | 86-88 | 87-89 | 88-90 | 88-90 | 89-91 | 90-92 |
| 1.01 | 71-74 | 77-79 | 80-82 | 82-84 | 84-85 | 85-86 | 85-87 | 86-87 | 87-88 | 88-89 |
| 1.00 | 68-70 | 74-76 | 78-79 | 80-81 | 81-83 | 82-84 | 83-84 | 84-85 | 85-86 | 86-87 |
| 0.99 | 66-67 | 72-73 | 75-77 | 77-79 | 79-80 | 80-81 | 81-82 | 82-83 | 83-84 | 85 |
| 0.98 | 64-65 | 70-71 | 73-74 | 75-76 | 77-78 | 78-79 | 79-80 | 80-81 | 81-82 | 83-84 |
| 0.97 | 62-63 | 68-69 | 71-72 | 74 | 75-76 | 77 | 78 | 78-79 | 80 | 81-82 |
| 0.96 | 60-61 | 66-67 | 69-70 | 72-73 | 73-74 | 75-76 | 76-77 | 77 | 78-79 | 80 |
| 0.95 | 59 | 64-65 | 68 | 70-71 | 72 | 73-74 | 74-75 | 75-76 | 77 | 78-79 |
| 0.94 | 57-58 | 63 | 66-67 | 68-69 | 70-71 | 72 | 73 | 74 | 75-76 | 77 |
| 0.93 | 56 | 61-62 | 65 | 67 | 69 | 70-71 | 71-72 | 72-73 | 74 | 75-76 |
| 0.92 | 55 | 60 | 63-64 | 65-66 | 67-68 | 69 | 70 | 71 | 72-73 | 74 |
| 0.91 | 53-54 | 58-59 | 62 | 64 | 66 | 67-68 | 68-69 | 69-70 | 71 | 73 |
| 0.90 | 52 | 57 | 60-61 | 63 | 64-65 | 66 | 67 | 68 | 70 | 71-72 |
| 0.89 | 51 | 55-56 | 59 | 61-62 | 63 | 64-65 | 66 | 67 | 68-69 | 70 |
| 0.88 | 50 | 54 | 57-58 | 60 | 62 | 63 | 64-65 | 65-66 | 67 | 69 |
| 0.87 | 48-49 | 53 | 56 | 58-59 | 60-61 | 62 | 63 | 64 | 66 | 67-68 |
| 0.86 | 47 | 51-52 | 55 | 57 | 59 | 60-61 | 62 | 63 | 64-65 | 66 |
| 0.85 | 46 | 50 | 53-54 | 56 | 58 | 59 | 60-61 | 61-62 | 63 | 65 |
| 0.84 | 45 | 49 | 52 | 55 | 56-57 | 58 | 59 | 60 | 62 | 64 |
| 0.83 | 44 | 48 | 51 | 53-54 | 55 | 57 | 58 | 59 | 61 | 63 |
| 0.82 | 42-43 | 46-47 | 50 | 52 | 54 | 55-56 | 57 | 58 | 60 | 61-62 |
| 0.81 | 41 | 45 | 48-49 | 51 | 53 | 54 | 56 | 57 | 58-59 | 60 |
| 0.80 | 40 | 44 | 47 | 50 | 52 | 53 | 54-55 | 55-56 | 57 | 59 |
| 0.79 | 38-39 | 43 | 46 | 48-49 | 50-51 | 52 | 53 | 54 | 56 | 58 |
| 0.78 | 37 | 41-42 | 45 | 47 | 49 | 51 | 52 | 53 | 55 | 57 |
| 0.77 | 36 | 40 | 43-44 | 46 | 48 | 50 | 51 | 52 | 54 | 56 |
| 0.76 | 34-35 | 39 | 42 | 45 | 47 | 48-49 | 50 | 51 | 53 | 55 |
| 0.75 | 33 | 38 | 41 | 44 | 46 | 47 | 49 | 50 | 51-52 | 53-54 |
| 0 | 0-32 | 0-37 | 0-40 | 0-43 | 0-45 | 0-46 | 0-48 | 0-49 | 0-50 | 0-52 |

Table 401-5

WEIGHT FACTORS

Gradation				Factor "f"

19.0 mm sieve				4

12.5 mm sieve				4

9.5 mm sieve					4

4.75 mm sieve				4

2.36 mm sieve				4

1.18 mm sieve				5

600 μm sieve					5

300 μm sieve					5

150 μm sieve					5

75 μm sieve					20

Asphalt %					40

401-5.01 BASIS OF PAYMENT. The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Tack coat will be subsidiary to asphalt cement unless specified as a pay item.

A change order/directive is not required for anti-stripping additive pay item. The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $4.95 per .25 percent additive per megagram of asphalt cement.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot and added to the Contractor's payment for Asphalt Concrete. The fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 401-2.01 will be subtracted from the Contractor's payment. The price adjustment will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value. The price adjustment for each individual lot shall be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $    /Megagram

* Composite Pay Factor (CPF) or Density Pay Factor (DPF) whichever is lower value.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete Pavement, Type___, Class ___	Megagram

401(2)	___ Asphalt Cement	Megagram

401(3)	Asphalt Concrete Pavement, Type___, Class___	Square Meter

401(4)	Anti-Stripping Additive	Contingent Sum

401(5)	Asphalt Price Adjustment	Contingent Sum

401(6)	Temporary Pavement	Megagram

When more than one type of Asphalt Concrete Pavement or Asphalt Cement appears on the plans and bid schedule, letter suffixes will be included within the parentheses of the pay item numbers in order to differentiate between different types.

Separate payment will not be made for asphalt cement, or anti-strip additives for Item 401(6), Temporary Pavement, or asphalt concrete for leveling course. Price adjustments will also not apply to Item 401(6), Temporary Pavement, asphalt concrete for leveling course, or Item 401(1), Asphalt Concrete Pavement, when total quantities are less than 4,500 Megagrams except as defined in Subsection 401-4.02.

(3/10/97)R199M

SECTION 404

SEAL COAT

Special Provisions

404-3.02 EQUIPMENT. Delete numbered item 1. in its entirety and substitute the following:

1.	The Contractor shall provide equipment for heating and applying the asphalt material. This equipment shall conform to the following requirements:

The distributor shall be so designed, equipped, maintained and operated that asphalt material at even heat may be applied uniformly on variable widths of surface up to half the roadway width plus 0.15 meter, at readily determined and controlled rates from 0.2 to 5.0 liters per square meter, with uniform pressure and with an allowable variation from any specified rate not to exceed 0.1 liters per square meter. Distributor equipment shall include the following:

a.	Computerized control of liquid asphalt spread rates to automatically deliver specified delivery rates and capable of changing rates when directed to do so.

b.	Computer monitoring of spread rate, truck speed and distance traveled.

c.	A thermometer for measuring temperature of the tank's contents, visible from outside.

Each nozzle in the spray bar shall be turned to make a constant angle with the longitudinal axis of the spray bar that is recommended by the manufacturer of the distributor. All nozzles in the spray bar shall be the same manufacture, type and size. The spray bar height shall provide triple overlap of the asphalt emulsion being applied by the spray nozzles.

Before the application of asphalt, the Contractor shall ensure that the distributor meets the following requirements:

a.	The spray bar can be maintained at a constant height throughout the entire operation.

b.	Spray bar nozzles are clean and in good working condition.

c.	The spray bar has been provided with a positive shutoff to prevent dribbling.

d.	The distributor is capable of maintaining a uniform speed.

The distributor will be inspected by the Engineer prior to the commencement of the operation. Any adjustments and other requirements shall be performed prior to being used.

The distributor shall be calibrated in accordance with the manufacturer’s recommendations. The Engineer may require the Contractor to prove the accuracy of the distributor. Any change in settings on the distributor after calibrating will require the distributor to be calibrated.

Calibration of the distributor will be done prior to commencing the asphalt application and any time thereafter if deemed necessary by the Engineer.

Should any of the nozzles on the spray bar fail to provide a constant, uniform flow during the application of asphalt material, the distributor shall immediately cease application of the asphalt material. The distributor shall not be allowed to resume applying asphalt material until all of the nozzles are in good working order. Nozzle adjustments and/or repairs must be approved by the Engineer.

Delete numbered item 3. in its entirety and substitute the following:

3.	A minimum of two self-propelled pneumatic tired rollers weighing not less than 9 Mg, equipped with not less than seven tires staggered back and front, inflated to 400 kPa. All tires shall have equal pressure. Each roller shall be equipped with a suitable tire pressure gauge for checking tire inflation pressure. Pneumatic tire rollers shall be operated at a maximum speed of 10 kilometers per hour.

Add the following to Item 4:

The aggregate spreader shall be capable of applying cover coat material to the specified roadway width in a maximum of two passes. The aggregate spreader shall be computer controlled to automatically maintain the specified delivery rate of cover coat material regardless of variations in machine speed. The spreader shall have a sufficient size feed system to maintain cover coat material in the spread hopper at all times.

Stopping the aggregate spreader to refill the receiving hopper will be permitted provided that the spreader is backed up at least 4 meters from the last cover aggregate application. The aggregate spreader will be permitted to slow down to allow trucks to backup and discharge loads into the receiving hopper. The aggregate spreader shall be constructed to eliminate material segregation in the various hoppers.

Immediately before using the aggregate spreader on the project, the aggregate spreader shall be calibrated for the cover coat material to be applied. The forward speed of the aggregate spreader during calibration shall approximate the speed required to apply the cover coat material over the asphalt material within the time allowed in Subsection 405-3.02 Surface Treatment. The aggregate spreader shall be calibrated in accordance with the Manufacturer’s recommendations. The Engineer may require the Contractor to prove the accuracy of the spreader.

The aggregate spreader shall be calibrated whenever directed by the Engineer. The calibration procedure will be observed by the Engineer each time it is done.

404-3.06 CONTROL STRIPS. Add the following subsection: A control strip shall be constructed at the start of the project to ensure that the equipment is providing a consistent mix, and repeated as directed by the Engineer.

Each control strip shall be constructed with the approved materials and the equipment to be used on the project. If the control strip meets the requirements of these specifications it shall remain in place as a section of the completed work. If it does not meet the specification requirements, it shall be removed and a new control strip constructed, at the Contractor's expense, in accordance with Subsection 105-1.03, Conformity with Plans and Specifications. Paving operations shall not proceed beyond the control strip until it has been confirmed that the mixture conforms to specifications and production paving is authorized. Each control strip shall be at least one lane in width, and up to 300 meters in length as directed by the Engineer.

(7/28/95)R204M

SECTION 405

SURFACE TREATMENT

Special Provisions

405-1.01 DESCRIPTION. Add the following: This work shall also consist of sweeping the treated road surface to move the loose aggregate off the road surface and onto the embankment.

405-2.02 AGGREGATES. Delete this subsection in its entirety and substitute the following: Cover aggregate shall conform to the requirements of Section 703-2.03, Grading CC-1. Blotter material shall be suitable clean sand. Covering the stockpile with a tarp is recommended. The aggregate will be accepted from samples taken from the grade during placement as determined by ATM T-7.

Add the following subsections:

405-2.03 COMPOSITION OF SURFACE TREATMENT. At least 15 days prior to the application of asphalt surface treatment, the Contractor shall submit a representative 30 kg sample of cover aggregate proposed for use on the project and a four liter sample of the asphalt proposed for compatibility testing and approval.

The quantities of materials per square meter shown in the following table are estimated application rates. The Engineer shall determine the actual application rates based on aggregate, actual field conditions, and engineering judgement. The Engineer may readjust application rates as required by changing field conditions.

| MATERIAL | APPLICATION RATE | TOLERANCE |
| --- | --- | --- |
| HFMS-2S Asphalt | 3.4 liters/m2 | 0.1 liters/m2 |
| Cover Aggregate CC-1 | 42 kg/m2 | 1 kg/m2 |

405-2.04 PROCESS QUALITY CONTROL. Process quality control will be required as per Subsection 307-3.00.

405-2.05 EQUIPMENT. Sweeping equipment shall meet the following requirements and be approve by the Engineer:

1.	The sweeper shall be self propelled.

2.	The brushes on the sweeper shall be a minimum of 2.4 meters wide and shall be adjustable in height relative to the road surface.

3.	The sweeper shall be capable of traveling at a minimum speed of 10 kph while sweeping the paved surface.

All equipment shall be in first-class working condition and be capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and be based on the manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at a time when, in the opinion of the Engineer, their condition is below what is normal for efficient output and production.

405-3.02 SEAL COAT. Delete this subsection in its entirety.

Add the following subsection:

405-3.02 SURFACE PREPARATION. The surface treatment shall be applied in accordance with Section 404, Seal Coat, and the following:

Preparation of surface shall include rolling with a steel wheeled soil compactor immediately prior to application of asphalt materials. The Contractor shall not leave windrows of materials on or adjacent to the surface treatment area that may impede drainage.

Weather conditions shall be such that proper construction of the surface treatment and adequate curing time is available prior to inclement weather or freeze-up. No surface treatment shall be applied between August 15th and May 1st.

The ambient air temperature at the project shall be 10 degrees Celsius or above, as measured in the shade away form any heat source.

The cover coat material shall be moistened or dried, as necessary, to achieve 2-4 percent moisture content at the time of application.

Surface treatment shall be applied only when the prepared surface is dry or only slightly damp, as determined by the Engineer, and when rain or fog is not present or imminent. If the surface is too dry, the Engineer may require a light spray of water to the surface prior to asphalt material application.

No traffic is allowed on freshly sprayed asphalt material. The specified application rate of cover coat material shall be placed within 1.5 minutes after the application of asphalt material. The Engineer's documentation that this time limit has not been satisfied will be grounds for rejection of the surface treatment.

Immediately after cover coat material is spread, the cover coat material shall be compacted by at least three passes by pneumatic tired rollers or until the cover coat material is bound tightly, to the satisfaction of the Engineer.

The maximum length of completed surface treatment lane shall be equivalent to the length that one distributor truck can cover. The work shall be performed in a manner such that asphalt and cover material are completed full road width at the end of each shift. End joints shall be protected with building paper in accordance with Section 404-3.04.

R205M

405-4.01 METHOD OF MEASUREMENT. Add the following: Sweeping will be measured by the hour of operation, including driver and operating costs. Transportation to and from the work site and idle time will not be measured.

Any traffic control or watering required to perform the sweeping will be paid under the appropriate traffic control item.

405-5.01 BASIS OF PAYMENT. Add the following: Payment for Item 405(3) Sweeping, will be paid on a contingent sum basis at the rate of $150.00 per hour.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

405(3)	Sweeping	Contingent Sum

SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

602-2.01 MATERIALS. Add the following to Standard Drawing D-05.10(M) for plate pipe arch:

| Minimum & Maximum Cover For 150 mm x 50 mm Steel Pipe Arch** |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 800 kg Corner Bearing Pressure |  |  |
| Span x Rise (mm x mm) | Corner Radius (mm) | Minimum Sheet Thickness (mm) | Minimum Cover (mm) | Maximum Cover (m) |
| 2 135 x 1 550 | 450 | 2.67 | 460 | 4.2 |

**Longitudinal seams use four (4) 19 mm bolts per .3048 meter.

General notes on Standard Drawing D-05.10 (M) apply

602-5.01 BASIS OF PAYMENT. Delete the third paragraph and substitute the following: Excavation shall be subsidiary to Item 602(2). Bedding and backfill will be paid under Item 203(6A) Borrow, Type A.

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS. Add the following: Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm.

(5/31/96)R42M

603-3.04 JOINING PIPE. Delete the last sentence of numbered paragraph 1., and substitute the following: Bands for pipe with diameters greater than 750 mm shall have a minimum width of 1.2 m. (8/28/96)R125M

603-3.06 CULVERT MARKER POSTS. Add the following subsection: Culvert marker posts shall be installed at each end of each cross culvert, on the side of the culvert facing approaching traffic. 1070 mm of post shall remain above the ground after driving. Approach culverts do not require the installation of culvert marker posts.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

R42M

SECTION 606

GUARDRAIL

Special Provisions

606-1.01 DESCRIPTION. Add the following: This work shall also consist of installing slotted rail terminals and controlled release terminals at the locations shown on the plans.

606-2.01 MATERIALS. Add the following: Slotted Rail Terminals shall be SRT-350's manufactured by Syro, Inc., Western Division, P.O. Box 99, Centerville, Utah 84014. Telephone 801-292-4461.

Flexible markers shall have yellow reflective sheeting and be one of the following types or equivalent:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

606-3.01 POSTS. Add the following: Posts for slotted rail terminals shall be installed per the manufacturer's recommendations. All guardrail posts, wood or steel, shall be 2.2 meters in length.

606-3.02 RAIL ELEMENTS. Add the following: Guardrail elements shall be factory bent for all radii less than 25 meter. Rail elements for slotted rail terminals shall be installed per the manufacturer's recommendations.

606-3.03 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 15 meter of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.06 FLEXIBLE MARKERS. Add the following subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer. The flexible markers shall have a minimum of 530 millimeters of marker extending above the top of the guardrail. The reflective tape shall face the nearest oncoming traffic.

606-3.07 EMBANKMENT WIDENING. Add the following subsection: Embankment widening for guardrail end treatments shall be constructed of selected material, Type A in accordance with Section 203.

606-3.08 LENGTH OF NEED VERIFICATION. Add the following subsection: After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends. The staked location of the guardrail will be approved by the Engineer prior to installation. The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.

606-4.01 METHOD OF MEASUREMENT. Delete the third paragraph and replace with the following: Item 606(27), Slotted Rail Terminal, will be measured per each completed installation which shall include all labor, equipment and materials. Materials for the slotted rail terminals include the anchor cable assembly, terminal posts, terminal end, rail elements, posts and blocking, flexible marker, and all associated hardware necessary to install the terminal. These items will not be measured for payment. The end of the slotted rail terminal and the beginning of W-beam guardrail will be as shown on the manufacturer's drawings.

Controlled Release Terminals shall be measured per each installation which consists of all materials from the terminal end to and including the breakaway cable terminal anchor cable assembly, terminal posts and associated hardware. (10/1/91)R129

606-5.01 BASIS OF PAYMENT. Add the following: Selected material, Type A will be measured and paid in accordance with Section 203.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

606(9)	Controlled Release Terminal	Each

606(27)	Slotted Rail Terminal	Each

SECTI0N 611

RIPRAP

Special Provisions

611-4.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: Riprap will not be measured for payment.

611-5.01 BASIS OF PAYMENT. Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

611(5A)	Riprap, Class II	Lump Sum

611(5B)	Riprap, Class III	Lump Sum

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS. Add the following to the end of the first sentence of the fifth paragraph: "the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual."

Add the following: Wide flange posts shall also be hinged and equipped with the multi-directional breakaway load concentration coupler hinge plates.

615-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the sixth paragraph: When existing signs are to be salvaged, the remaining foundation shall be removed, abandoned in place, or if located within the roadway structural section shall be disposed of in a manner as approved by the Engineer. If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

Add the following after the sixth paragraph: Salvaged sign panels shall be delivered to the State Maintenance Yard in Dillingham.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Existing signs shall not be removed without authorization from the Engineer. They shall be kept in service until either the new signs have been installed, or they are no longer needed. As the work progresses, if their locations do not conform to Standard Drawing S-05.00[M], they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign. Installation dates shall be written in the format of month/day/year, using black permanent marker, with numbers a minimum of 75 mm in height, so as to be readable from the roadside after installation.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01 BASIS OF PAYMENT. Add the following: Payment for keeping existing signs in service until they are not longer needed, temporarily relocating existing signs, or salvaging signs, will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Payment for removal of existing sign post foundations, or work required to abandon them in place, shall be included in Item 615(1), Standard Signs.

R50M

Delete section 616 in its entirety and substitute the following:

SECTION 616

CULVERT THAW PIPE

Special Provisions

616-1.01 DESCRIPTION. This work consists of furnishing, fabricating, and installing thaw pipes in conformance with the plans.

616-2.01 THAW PIPE. Shapes, pipes, fittings, and castings shall conform to the

following:

1.	Bolts and nuts shall conform to ASTM A 307. All bolts and nuts shall be galvanized in accordance with AASHTO M 232.

2.	All pipe and fittings shall be galvanized and conform to ASTM A 53.

3.	Pipe hangers shall be Grade 24018 malleable iron conforming to ASTM A 47. All pipe hangers shall be galvanized in accordance with AASHTO M 111.

4.	The braces for the standpipe shall conform to AASHTO M 183. Braces shall be galvanized in accordance with AASHTO M 111.

CONSTRUCTION REQUIREMENTS

616-3.01 THAW PIPE.

1.	Pipe Hangers. The bolt holes shall be drilled or field punched and reamed and the diameter of the holes shall not exceed the diameter of the bolt by more than 3 mm. The bolt heads and nuts shall be drawn tightly against the pipe.

2.	Pipe Jointing. All scale shall be removed from the pipe. After cutting, all pipe shall be reamed. All pipe and fittings shall be assembled with an application of pipe compound.

3.	Installation. The Contractor shall prevent dirt or other foreign matter from entering the pipe. After the thaw pipe is fully assembled and installed, it shall be thoroughly flushed with water.

616-4.01 METHOD OF MEASUREMENT. Thaw Pipe will be measured by each complete installation of a thaw pipe system.

616-5.01 BASIS OF PAYMENT. The payment for Item 616(2) 40 mm Diameter Thaw Pipe, shall be full compensation for furnishing and installing each complete system as shown on the drawings.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

616(2)	40 mm Diameter Thaw Pipe	Each

R216M

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION. Delete this subsection and substitute the following: All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded. This work shall consist of tracking the soil, followed by the application of seed, mulch, fertilizer and water. It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Seed shall be applied as detailed below immediately after the shaping of the slopes. All slopes to be seeded shall be covered with topsoil in accordance with Section 620 and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. This should be completed as soon as topsoil is placed on the slopes. The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted. Where the fill is adjacent to wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.

618-3.03 APPLICATION METHOD. In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following: "Item 619(1), and/or limestone, Item 618(4),".

Add the following: Seed, mulch and fertilizer shall be applied as follows per hectare (ha). If the hydraulic method for seed and mulch is used, it shall be made in one application. All fertilizer shall be applied by the hydraulic method.

| Item | Ingredients | Application Rate (per ha) |
| --- | --- | --- |
| Seed Mix | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.4 kg 19.5 kg 4.9 kg Total=48.8 kg |
| Mulch | -- | 1710 kg |
| Fertilizer | 20-20-10 | 586 kg |

The Contractor shall not remove the required tags from the seed bags.

618-3.04 MAINTENANCE OF SEEDED AREAS. Add the following: A reapplication of fertilizer shall be applied with water between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

618-4.01 METHOD OF MEASUREMENT. Delete the second paragraph and substitute the following: Seeding by the kilogram will be the number of kilograms of seed (dry measure) accepted in place. The amount of fertilizer, mulch and water for application used in this work, including any required reseeding, will be subsidiary to this item and will not be measured separately for payment.

Delete the third paragraph and substitute the following: Water used in maintenance of seeded areas will be measured by the kiloliter, by means of calibrated tanks or distributors, accurate water meters or by weighing. The conversion factor of 1.00 kilogram per liter will be used in converting weights to liters.

Delete the fourth paragraph and substitute the following: Ground limestone, when required, will be measured by the megagram of material acceptably placed.

Delete the last paragraph.

618-5.01 BASIS OF PAYMENT. Add the following after the first paragraph: Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to seeding.

The work described under subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

R52M

SECTION 620

TOPSOIL

Special Provisions

620-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Topsoil shall conform to the requirements of Section 726.

R53

SECTION 636

GABIONS

Special Provisions

636-5.01 BASIS OF PAYMENT. Delete the second paragraph and substitute the following: Excavation and backfill for gabions shall be subsidiary to this item. Grading around gabions and existing structural plate pipes shall also be subsidiary to this pay item.

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION. Delete this subsection in its entirety and substitute the following: This work consists of the excavation, forming, shaping and construction of approaches.

639-1.02 CONSTRUCTION REQUIREMENTS. Add the following subsection: Placement of materials used in approaches shall meet the requirements specified as follows:

Selected Material, Type A				Section 203

Subbase						Section 304

Asphalt Treated Base	Course			Section 306

HFMS-2S Asphalt					Section 405

Cover Aggregate Grading CC-1			Section 405

Emulsified Asphalt, Type CSS-1			Section 702

639-2.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: Approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01 BASIS OF PAYMENT. Add the following: Payment for approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approaches	Each

Delete the last paragraph and substitute the following: The contract unit price for approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified. Selected Material Type A, Subbase, Asphalt Treated Base Course, HFMS-2S Asphalt, Grading CC-1 Cover Coat Material and Emulsified Asphalt Type CSS-1 required to construct approaches will be paid for separately under the respective items listed in the bid schedule. Selected Material, Type C will not be paid for directly, but will be considered subsidiary to Item 639(6) Approaches. For each approach, 50 m³ of excavation will be considered subsidiary to Item 639(6) Approaches. Excavation in excess of 50 m³ will be paid under Item 203(3) Unclassified Excavation.

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01 DESCRIPTION. This work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

This work shall also include installation of silt fence as shown on the plans or as directed by the Engineer.

641-1.02 DEFINITIONS.

1.	Erosion and Sediment Control Plan (ESCP). The Department's general plan for the permanent and temporary control of erosion and sedimentation during construction of the project as contained in the plans and specifications, and supplemented by the AASHTO Guidelines for Erosion and Sediment Control in Highway Construction, Volume III. The ESCP is prepared by the Department.

2.	Storm Water Pollution Prevention Plan (SWPPP). The detailed site-specific plan prepared by the Contractor for the temporary and permanent control of erosion and sedimentation during construction of the project. The SWPPP is based upon the ESCP, and prepared according to guidance provided in the AASHTO Guidelines for Erosion and Sediment Control in Highway Construction, Volume III, the EPA's Storm Water Management for Construction Activities: Developing Pollution and Prevention Plans and Best Management Practices (EPA 832 R-92-005), and the Final National Pollutant Discharge Elimination System General Permit for Storm Water Discharges from Construction Sites (NPDES General Permit).

3.	Hazardous Material Control Plan (HMCP). The Contractor's detailed plan for the prevention, containment, cleanup, and disposal of hazardous waste material, including petroleum products generated by construction equipment or activities. Included in the HMCP is a list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup. The plan also describes how and where construction equipment fueling and maintenance activities will be carried out and controlled.

4.	Notice of Intent (NOI), to utilize the NPDES General Permit for Alaska. This is a standard form (EPA Form 3510-698-98) giving notice to the U.S. Environmental Protection Agency (EPA) that work will be conducted in compliance with the NPDES General Permit. The NPDES General Permit authorizes discharges of storm water from construction activities involving more than 2.02 hectares of land. The Contractor prepares the NOI, and submits it a minimum of 5 days prior to the preconstruction conference for approval.

5.	Notice of Termination (NOT) of coverage under the NPDES General Permit for Alaska. This is a standard form (EPA Form 3510-7(8-98)) that constitutes notice that the project site has been finally stabilized or when an Operator of a construction activity, as defined in the NPDES General Permit, changes. The Contractor prepares the NOT, and submits it to the Engineer once final stabilization of the project site has been completed.

6.	Final Stabilization is when all soil disturbing activities at the site have been completed, and a uniform perennial vegetative cover with a density of 70 percent of the cover for unpaved areas not covered by permanent structures has been established or equivalent permanent stabilization measures (such as the use of riprap, gabions, or geotextiles) have been employed. The Engineer determines when final stabilization has occurred.

7.	Department of Environmental Conservation Summary (DEC Summary). A brief description of the activities to be covered under the NPDES General Permit. This shall be on a single sheet and shall describe the areas to be disturbed to the nearest hectare, the primary pollutants expected from the activities, and the type of treatment to be provided.

641-1.03 SUBMITTALS. The Contractor shall submit the following items for approval a minimum of 5 days prior to the preconstruction conference:

1.	Draft Storm Water Pollution Prevention Plan (SWPPP).

2.	Hazardous Material Control Plan (HMCP).

3.	Notice of Intent (NOI).

4.	Department of Environmental Conservation Summary (DEC Summary).

The Engineer will review submittals within 14 calendar days. If required for approval, the Contractor shall modify the submittals within 5 calendar days of receiving comments from the Engineer.

The Contractor’s draft SWPPP shall be prepared and stamped by a professional engineer currently registered in the State of Alaska. The Department will review the draft SWPPP, and either approve it, or recommend changes. The Contractor shall make the necessary revisions to obtain the Department’s approval of the SWPPP. The approved SWPPP becomes the project SWPPP and shall be signed and certified by the Contractor, the Department, and subcontractors in accordance with the NPDES General Permit.

The Contractor shall implement all measures in the SWPPP and ensure that it remains current.

Once the Contractor's SWPPP is approved, the Engineer will submit the Contractor’s NOI along with the Department’s NOI to the EPA via Certified Mail. The Engineer will also submit copies of the NOI and the DEC Summary to the State of Alaska Department of Environmental Conservation (DEC) Storm Water Coordinator. Earth disturbing work shall not begin until the Contractor receives in writing: 1) Department approval of the Contractor's SWPPP, and 2) notification that 48 hours have passed since the NOIs were postmarked to EPA and DEC.

A copy of the NOI, or other indication that storm water discharges from the site are covered under an NPDES permit, shall be posted at the construction site in a prominent place for public viewing.

The Contractor shall amend the SWPPP when requested by the Engineer within 7 days. All SWPPP amendments shall be prepared and stamped by a professional engineer currently registered in Alaska. The approval process for amendments to the SWPPP is the same as with the Contractor's draft SWPPP.

If a storm event occurs, where storm water discharges pose a threat to water quality, the Contractor shall take immediate action to preclude pollution subject to the directive of the Engineer. An amended SWPPP covering the emergency measures that were taken shall be submitted to the Engineer within 7 days of the storm event.

Prior to project closeout and Contractor demobilization, the Contractor and Engineer shall review the project to determine if all areas disturbed by construction meet the requirements for final stabilization. When final stabilization has been accomplished, the Contractor shall submit a signed Notice of Termination (NOT) to the Engineer.

641-1.04 STORM WATER POLLUTION PREVENTION PLAN REQUIREMENTS. The Contractor shall prepare the SWPPP. The SWPPP shall follow the format presented in the NPDES General Permits For Storm Water Discharges from Construction Activities that are classified as "Associated With Industrial Activity," Part IV. (CFR Vol. 57, No. 175, Sept. 9, 1992, page 41176) The NPDES General Permit (GP) for Alaska will be expiring during 1997. New provisions under consideration for the GP may require the Contractor's SWPPP to be modified during implementation of this contract. The SWPPP shall address all storm water discharge control and management issues identified by the ESCP. The SWPPP shall include the following items:

1) Site Description. The SWPPP shall provide a description of pollutant sources and other information as indicated below:

a.	A description of the nature of the construction activity;

b.	A description of the intended sequence of major activities which disturb soils for major portions of the site (e.g. grubbing, excavation, grading, work in or in proximity to surface waters);

c.	Estimates of the total area of the site and the total area of the site that is expected to be disturbed by excavation, grading, or other activities;

d.	An estimate of the runoff coefficient of the site before, during, and after construction activities are completed and existing data describing the soil and the quality of any discharge from the site (Reference Table 1, page 6, of EPA Report EPA 832-R-92-005, Storm Water Management For Construction Activities - Developing Pollution Prevention Plans And Best Management Practices);

e.	A site map indicating drainage patterns and approximate slopes anticipated after major grading activities, areas of soil disturbance, an outline of the areas which will not be disturbed, the location of major structural and nonstructural controls identified in the plans, the location of areas where stabilization practices are expected to occur, surface waters (including wetlands), and locations where storm water is discharged to a surface water; and

f.	The name of the receiving water(s), and the extent of wetland area, in hectares, at the site.

2) Controls. The SWPPP shall include a description of appropriate controls and measures that will be implemented at the construction site. It shall clearly describe for each major activity, appropriate control measures and the period during the construction process that the measures will be implemented. The description and implementation of controls shall address erosion and sediment controls, stabilization practices, structural practices, and permanent storm water management as defined in the NPDES General Permit. The SWPPP shall also address the specific plan for controlling and managing erosion and sedimentation during construction at the following locations:

a.	All construction adjacent to major drainages, streams, lakes, water bodies, wetlands, and other sensitive areas.

Station 2+220			Scandinavian Creek

Station 4+820 to 4+920	Squaw Creek

Station 11+590		Squaw Creek

Station 12+940		Squaw Creek

b.	Culvert Installations

Station 11+590		Squaw Creek

Station 12+940		Squaw Creek

c.	Any additional sites which may be sensitive due to the Contractor’s proposed construction operation (e.g. contractor supplied material and disposal sites, staging areas, stockpile locations, treatment of slopes opened up after the seeding deadline, etc.).

3) Maintenance. The SWPPP shall include a description of procedures for the timely maintenance of vegetation, temporary and permanent erosion and sediment control measures, and other protective measures identified in the SWPPP and the project plans and specifications.

4) Inspections. The SWPPP shall identify the Contractor personnel responsible for inspection of the project’s erosion and pollution control measures and their qualifications. Qualified personnel shall inspect disturbed areas of the construction site that have not been finally stabilized, areas used for storage of materials that are exposed to precipitation, structural control measures, and locations where vehicles enter or exit the site, at least once every 7 calendar days and within 24 hours of the end of a storm resulting in rainfall of 0.5 inches or greater.

During winter shutdown, the Contractor shall conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 0.5 inches or greater. In some areas where ground is frozen and/or snow or ice covered throughout the winter, fewer inspections may be allowed. However, the justification for fewer inspections must be documented in the SWPPP and are subject to the approval of the Engineer.

The Contractor shall prepare a report summarizing the scope of the inspection, name(s) and qualifications of personnel making the inspection, the date(s) of the inspection, major observations relating to the implementation of the SWPPP, and actions taken in accordance with paragraph IV.D.4.b of the NPDES General Permit. The report shall be retained as part of the SWPPP for at least three years from the date that the site is finally stabilized. Reports shall identify any incidents of non-compliance, contain a certification that the facility is in compliance with the SWPPP and the NPDES General Permit. The inspection reports shall be submitted to the Engineer within 3 days of the inspection.

5. Non-storm Water Discharges. Except for flows from fire fighting activities, sources of non-storm water listed in Part III.A.2 of the NPDES General Permit that are combined with storm water discharges associated with the construction activity shall be identified in the SWPPP. The SWPPP shall identify and ensure the implementation of appropriate pollution prevention measures for the non-storm water component(s) of the discharge.

6. Contractor/subcontractor. The SWPPP shall clearly identify for each measure identified in the plan, the Contractor and/or subcontractors that will implement the measure. The Contractor and all subcontractors shall sign a copy of the certification statement I Part IV E. 2 of the NPDES General Permit in accordance with Part VI.G of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

7. Appendix - The NPDES General Permit shall be appended to the SWPPP.

641-1.05 HAZARDOUS MATERIAL CONTROL PLAN REQUIREMENTS. The Contractor shall comply with all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products and or other hazardous substances. The Contractor shall prepare the HMCP . The HMCP shall detail the Contractor’s plan for fueling and maintaining equipment and machinery. The locations where fueling and maintenance activity is to take place, and any controls to contain the accidental spillage of petroleum products shall be identified. A list of potentially hazardous materials, including petroleum products, to be used and/or stored on site, and their estimated quantities shall be provided in the HMCP . The Contractor’s plan for the disposal of waste petroleum products and/or other hazardous wastes generated by the project shall also be identified in the HMCP . Additionally, the Contractor’s plan for prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills, and the Contractor’s plan for encountering unexpected contaminated soil and water during construction shall be detailed in the HMCP .

641-2.01 MATERIALS. Erosion and pollution control measures shall be accomplished utilizing Best Management Practices (BMP) as specified in the SWPPP and HMCP . Ground disturbing activities shall only be undertaken after the seeding deadline when:

1) The SWPPP describes the work and controls to be taken to control storm water runoff after the seeding deadline;

2) Men, materials, and equipment are on hand to accomplish the control measures identified in the SWPPP; and

3) All disturbed areas will be stabilized against erosion within 7 days of the temporary or permanent cessation of work on the slopes. Stabilization practices may include; mulching, geotextile, sod, covering with sheet plastic, or other equivalent measures.

The silt fence filtration material shall meet the requirements of subsection 729-2.04 Sediment Control.

The silt fence support framework shall be finished 50 mm x 50 mm wood, 75 mm diameter wood, #6 rebar with PVC sleeves, iron pipe, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-3.01 CONSTRUCTION REQUIREMENTS. The Contractor shall comply with all requirements of the NPDES General Permit for Alaska, and shall implement all temporary and permanent measures identified in the SWPPP and plans. The Department and Contractor shall share responsibility for inspecting, and the Contractor’s representative shall prepare inspection reports per the requirements of the NPDES General Permit. Compliance with the NPDES General Permit does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate. The Department reserves the right to hire another contractor to perform this work if the Contractor is unresponsive or a suitable agreement cannot be reached with the Contractor.

Prior to start of construction, the Contractor, his representative, the professional engineer who stamped the SWPPP, and the Engineer shall have an on site inspection to discuss the SWPPP implementation and the requirements under that plan.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. The Contractor shall also be responsible for performing all fueling operations in a safe and environmentally responsible manner. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of subsection 107-1.11, Protection and Restoration of Property and Landscape. Additional silt fencing may be required at other sites as directed by the Engineer.

The silt fence shall not be removed until slopes are stabilized from further erosion as determined by the Engineer. The silt fence shall be removed and disposed of off the project upon completion of construction at those sites. The fabric shall be cut off at ground level and the wire and posts shall be removed. The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands or waterbodies. If a sediment height in excess of 100 mm above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.

641-4.01 METHOD OF MEASUREMENT. Item 641(1) Erosion and Pollution Control Administration, will not be measured for payment. The Engineer’s acceptance will constitute measurement.

Item 641(2) Erosion and Pollution Control, will be measured in the manner specified in the directive authorizing the work.

Silt fence will be measured by the meter along the top of the fence.

641-5.01 BASIS OF PAYMENT. Item 641(1) Erosion and Pollution Control Administration, will be full compensation for administration of erosion control including plan preparation and amendments, inspection, monitoring, reporting and record keeping.

Item 641(2) Erosion and Pollution Control, will be full compensation for providing all labor, equipment, and materials required to accomplish the work, as specified in the directive authorizing the work.

Payment for Item 641(3), Silt Fence, will be full compensation for all labor, equipment and materials required to furnish, install, maintain and remove the silt fence in accordance with these specifications.

Failure to diligently a) pursue work required by the approved SWPPP, b) respond to inspection recommendations and/or deficiencies in the SWPPP, c) implement erosion and sedimentation controls identified by the Engineer, will result in a permanent price adjustment under Item 641(6). If the Contractor does not respond within 2 hours of the Engineer’s directive, then an amount equal to five percent of the total amount earned from all previous and subsequent progress payments on the contract or $50,000 which ever is greater, will be withheld, and a permanent price adjustment made equivalent to:

1)	$500 per hour for the first 4 hours of non-action;

2)	$1,000 per hour for every hour over four, but less than 10;

3)	$1,500 per hour for every hour over 10 hours of non-action.

The Price Adjustment will cease when corrective actions are accepted by the Engineer. The Department reserves the right to hire another contractor to do corrective action, and to reduce the contract amount by this cost plus the cost to the Department implementing another contract.

In addition, a price adjustment equivalent to any penalties levied against the Department by the EPA or any other state and/or federal agencies for violations of the Clean Water Act and the NPDES General Permit will be made if the Department is issued a notice of violation by these agencies. This price adjustment shall be the actual cost of any fines levied against the Department. An amount equal to the maximum fine for the violation will be withheld temporarily until the actual cost of the fine is known. The difference, excluding any price adjustments will be released by the Engineer upon satisfactory completion of the requirements of the General Permit. Penalties for violations are as stated in Part VI.A.2 of the Standard Permit Conditions of the NPDES General Permit. The Contractor shall also be responsible for the payment of his own fines.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(2)	Erosion and Pollution Control	Contingent Sum

641(3)	Silt Fence	Meter

641(6)	Erosion and Pollution Price Adjustment	Contingent Sum

(1/20/98)R59aM

Delete Sections 614 and 642 and replace with the following:

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION. Perform all surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the plans and specifications and standard engineering practice.

Furnish and install survey monuments and monument cases in conformance with the Plans or as directed.

Adjust existing monuments and monument cases to conform to the new elevations.

642-1.02 DEFINITIONS

1.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown on the plans.

2.	Point: Any identified spot located on the surface of the earth. For purposes of this definition, a point can be a PK nail, wooden hub, rebar, large nail or any other structure capable of being utilized as a marker.

3.	Witness Corner: A material mark or point usually placed on a property or survey line, at a known distance from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

4.	Reference Monument: A material mark or point placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

5.	Surveyor: The Contractor’s Professional Land Surveyor, currently registered in the State of Alaska.

642-2.01 MATERIALS.

1.	Monument Cases. Castings shall conform to AASHTO M 105, Class 30A. Castings shall be coated with a bituminous damp-proof coating. The tops shall bear evenly on the frames.

2.	Primary Monument: A minimum 50 mm diameter nonferrous pipe at least 750 mm long, with a minimum 100 mm flange at the bottom and having magnets attached at the top and bottom. A minimum 60 mm diameter nonferrous metal cap must be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments which will be oriented so as to be read facing up-station.

3.	Secondary Monument: A minimum 15 mm x 750 mm rebar with a 50 mm aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL. Use competent, qualified personnel and suitable equipment for the layout work required and furnish all traffic control, stakes, templates, straight-edges and other devices necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish such computer services as necessary to accomplish the work. Check all data received from the computer for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver all field books, computer forms and computer output data to the Engineer. This data shall become the property of the Department.

Supervise construction surveying personnel. Correct any errors resulting from the operations of said personnel at Contractor expense . The Contractor is responsible for the accuracy of the work.

Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or under the responsible charge of a Professional Land Surveyor.

Follow the Department’s Construction Surveying Requirements (Metric). A copy of this document is attached to these Special Provisions in Appendix B.

Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with Departmental procedures, including titles, numbering, and indexing. Make field books available for inspection by the Department’s project personnel at any time. Store the field books in the Department’s Project Office During periods of non-use.

Perform the following:

1.	staking necessary to delineate clearing and/or grubbing limits

2.	cross sections necessary for determination of excavation and embankment quantities, including intermediate and/or remeasure cross sections as needed

3.	slope staking

4.	staking of signs, culverts, minor drainage structures and other appurtenances, including the necessary checking to establish the proper location and grade to best fit the conditions on site

5.	bridge staking

6.	the setting of such finishing stakes as may be required

7.	the measurement of pay quantities that require measurement

8.	the staking of right-of-way and material source limits when it is deemed necessary

9.	the staking, referencing and other actions as may be required to preserve or restore land monuments and property corners

10.	and all other surveying and staking necessary to complete the project

When the right-of-way centerline points have been established as a part of the Department’s Preconstruction surveys, the Department will furnish the Contractor with copies of the reference field books. Recover these control points and verify these references. Reestablish any missing points from the Department’s references prior to the initiation of clearing, grubbing, or excavation.

When the right-of-way centerline points have not been established by the Department but the survey control points were established as a part of the Department’s Preconstruction surveys (as detailed on the project Survey Control Sheet) recover these points and use them as the basis for establishing the right-of-way centerline. Verify the position of these points and establish new points where required to replace missing points, prior to the initiation of clearing, grubbing, or excavation.

Notify the Engineer immediately if a Department-established reference point is discovered to be in error or a reset point is not in harmonious relationship to the adjacent centerline points.

Furnish a notekeeper to record all field survey notes, including those which become documentation from which quantities for payment are computed. The notekeeper shall be thoroughly familiar with generally accepted standards of good survey notekeeping practice and the Department’s Construction Surveying Requirements (Metric).

The Engineer may randomly spot check the Contractor's surveys, staking and computations. After the survey or staking has been completed, provide the Engineer with a minimum of 72 hours notice prior to performing any work, and furnish the appropriate data as required, to allow for such random spot checking. The Department assumes no responsibility for the accuracy of the work.

642-3.02 CROSS-SECTION SURVEYS. When required, obtain right-angle cross sections to the construction centerline at the interval detailed in the Department’s Construction Surveying Requirements (Metric).

The following shall be supplied by the Department:

1.	One set of Construction Plans and Specifications.

2.	Field Books (Level, Cross-Section, Slope Stake, etc. ). Books will be labeled and the pages numbered by the Department. Field books shall remain the property of the Department upon completion of the work.

3.	Design Cross Sections, if any.

4.	Sufficient centerline or reference thereto, and at least one benchmark per kilometer to enable the establishment of planned elevations and centerline.

5.	State of Alaska Land Survey Monument Record forms. These forms are to be completed by the Contractor.

6.	One copy of the Department’s Construction Surveying Requirements (Metric).

7.	Design centerline grades, except when Item 642(2), Office Engineering is used.

The following shall be required of the Contractor:

1.	A heading in the appropriate book (date, weather, names and duties of crew members) shall be made at the beginning of each day's work.

2.	The notekeeper shall update the index of the appropriate book at the end of each day's work.

3.	Level notes shall be reduced, checked and adjusted.

4.	Cross-section level notes and slope stake catches shall be computed by the notekeeper and checked by a different crew member in the field on a continual basis.

5.	The Contractor shall enter the grade data, shoulder width and/or ditch distance, stationing, slope, etc., in the slope stake books.

6.	The position and identifying marks of slope stakes and reference points shall be maintained until used for their intended purpose.

7.	Errors shall have a line drawn through them with the correct entry made directly above. Erasures will not be allowed.

8.	Field books or copies of the field books shall be returned to the Project office at the end of each work day or as directed.

9.	The Contractor shall provide copies of all grade sheets and temporary bench mark elevations to the Engineer 48 hours before commencing work on unclassified excavation or embankment.

10.	The Contractor’s survey crews shall comply with all approved traffic control plans. Crews shall coordinate their activities with the Contractor’s Worksite Traffic Supervisor.

11.	A survey Party Chief diary shall be kept daily and contain the following information, (a copy shall be given to the Engineer daily):

a.	Date.

b	Weather.

c.	Crew members’ names and duties.

d. 	Type and location of work performed.

e. 	Hours worked.

f. 	Type of equipment used (brand) and date equipment was double centered or “peg” test was performed.

g. 	Signature of person in responsible charge.

12.	The Contractor shall submit the survey field notes, for any specific area, relating to monument referencing prior to any initiation of clearing, grubbing or excavation.

642-3.03 MONUMENTS. Install primary and secondary monuments, as called for in the plans, at the positions established by the Department. Reference all monuments, property markers/corners, or accessories which may be disturbed or buried during construction, and re-establish them in their original position prior to the completion of the project. Keep such records and report to the Engineer evidence that a monument has been disturbed and is no longer reliable or cannot be located and is presumed to be missing. The referencing work shall consist of a minimum of two in-line reference points, or three swing-tie reference points in situations where in-line referencing is not desirable. Set all reference points outside of the construction limits. Measure distances from the monument to the nearest l mm. Record all referencing of monuments in a separate field book stamped by the Surveyor.

Replace all existing monuments disturbed by construction with Primary or Secondary Monuments meeting the requirements of Subsection 642-1.02. When it is impractical to establish a monument in its original position, install a witness corner (WC). Place the WC to a property corner on the property line when the other property corner which defines said line is existing or there has been sufficient retracement to define said line. In other cases, place a reference monument (RM) perpendicular to the centerline at the station of the original position and at a distance from the original position measured in whole meters.

Those monuments found that are not shown on the plans will be recognized by the Engineer when the following is provided by the Surveyor: Field notes identifying type and location of the monument, and a description of the point the monument marks, with the reason to preserve its location. Monuments not shown on the plans will be considered additional work and paid by 642(3), Three Person Survey Party.

The Surveyor shall complete a State of Alaska Land Survey Monument Record form for each primary and secondary monument installed, relocated or replaced. In addition to the required survey information, including section, township and range, each record shall meet all requirements for recording at the District Recorder’s Office in which the project is located. Deliver these forms to the Engineer prior to project completion. The Department will file all original records as required by current State Statutes using the information provided by the Contractor.

Set each monument and monument case accurately to lines established at the required location and in such a manner as to insure its being held firmly in place. Set existing monuments and monument cases to be adjusted to new elevations in the manner and at the elevations directed.

642-3.03 OFFICE ENGINEERING. Calculate finish grades for the roadway as specified per plans and/or specifications. Use information available in the field, on as-builts, or as provided by the Engineer. This work shall be performed by or under the responsible charge of a Professional Land Surveyor or a Professional Engineer currently Registered in the State of Alaska.

642-3.04 FINAL TRAVERSE. Within 30 days after the Engineer receives from the Contractor a letter which states that all construction activities that may disturb the monuments have ceased, the Surveyor shall run a final traverse to verify the positional accuracy of installed survey monuments. This traverse will begin and end at different Department provided control points. The primary and secondary monuments placed or replaced and any undisturbed department provided control points shall be tied to the traverse. Under no circumstance shall the final traverse run more than 4 km without a tie to a department provided monument/control point. All traverse points established during this work shall meet the requirements of a secondary monument. The Surveyor shall sign and stamp a letter which lists each monument and its coordinates. The letter shall certify that the monuments are each located within 50 mm of their proposed position based on the project survey control points provided by the Department. Deliver the certification letter and field notes for this work to the Engineer.

642-4.01 METHOD OF MEASUREMENT.

Item 642(1) Construction Surveying. No measurement of quantities will be made.

Item 642(2) Office Engineering. By the kilometer along centerline for all completed office engineering accepted.

Item 642(3) Three Person Survey Party. By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed.

Items 642(4) through 642(8). The actual number of monuments installed as shown on the “State of Alaska Land Survey Monument Record” forms delivered to and accepted by the Engineer.

Item 642(9) Reference Existing Monument. The actual number of monuments referenced as shown in the Surveyor’s field notes delivered to and accepted by the Engineer.

642(10) and 642(11). The actual number of monument cases furnished and installed, or adjusted to new elevation, and accepted.

642(12) Final Traverse. No measurement of quantities will be made.

Survey monuments that are placed on bridges will not be measured for payment but will be considered incidental to other bridge items.

Calculations of all pay quantities will be performed by Department personnel.

642-5.01 BASIS OF PAYMENT. Construction Surveying and Final Traverse shall include all field and office work required to accomplish the work, including furnishing all necessary personnel, equipment, transportation and supplies. Payment for Final Traverse is based on the Engineer’s acceptance of the Surveyor’s certification letter and field notes.

Construction Engineering when required, will be in addition to Construction Surveying. Both items will appear on the bid schedule.

If staking for extra, additional or unanticipated work, as stated above, is performed by a two person survey party, payment will be made at 75 percent of the unit price under Item 642(3), Three Person Survey Party. If a single person is required for additional office computations or other work requiring only one person, payment will be made at 32 percent of the unit price of Item 642(3).

Traffic control devices necessary for the survey parties will be considered subsidiary. Payment for Traffic Control Plans as approved will be paid under Section 643, Traffic Maintenance.

The accepted quantities will be paid for at the contract price, per unit of measurement for each of the particular pay items shown in the bid schedule.

Pay Item No.	Pay Item	Unit

642(1)	Construction Surveying	Lump Sum

642(2)	Office Engineering	Kilometer

642(3)	Three Person Survey Party	Hour

642(4)	Set Primary Monument	Each

642(5)	Set Secondary Monument	Each

642(6)	Replace Existing with Primary Monument	Each

642(7)	Replace Existing with Secondary Monument	Each

642(8)	Adjust Existing Monument	Each

642(9)	Reference Existing Monument	Each

642(10)	Monument Case	Each

642(11)	Adjust Existing Monument Case	Each

642(12)	Final Traverse	Lump Sum

(3/17/97)R214M

Delete Section 643 in its entirety and substitute the following:

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION. This work consists of the necessary measures to protect and control traffic during the life of the contract including, but not limited to, furnishing, erecting, maintaining, replacing, cleaning, moving and removing the traffic control devices required to insure the safety of the traveling public and all administrative responsibilities necessary to implement this work.

The Contractor shall maintain all roadways, pedestrian and bicycle facilities affected by the work and shall construct and maintain approaches, crossings, intersections and other features as may be necessary throughout the life of the contract.

643-1.02 DEFINITIONS.

Construction Phasing Plan - A plan for each phase of the project showing how traffic will be accommodated. It should show the sequence of work by segment or phase if required.

Traffic - The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, incident zones or similar operations.

Traffic Control Plan - A Traffic Control Plan (TCP) is a drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. It depicts the traffic control devices to be used, their placement and times of use.

Traffic Control Zone - A portion of a road construction project, maintenance operation, utility work, incident zone or similar operation where traffic is affected by the operation and traffic control is needed to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. The TCP may include, but not be limited to, such items as signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary roadways and all other items required to direct traffic through or around the construction zone in accordance with these specifications and the Alaska Traffic Manual (ATM). The TCPs shall also address placement of traffic control devices including location, size, mounting height and type. The details shown for signs shall include the code designation, size, and legend per the ATM and the Alaska Sign Design Specifications (ASDS). Plan sheets developed on Auto Cad can be made available, upon request, for use in preparing TCPs.

When a TCP is included in the plans the Contractor may use it, modify it or design an alternative TCP. Any modifications to the TCP or any new TCP shall be submitted for approval of the Engineer. The Contractor shall allow 1 week for review of any TCP or each subsequent correction. Changes in the TCP may be allowed during construction provided 48 hours are allowed for review and the changes are approved by the Engineer.

When a TCP is not included in the plans the Contractor shall provide one in accordance with this Section and the ATM. The Contractor's superintendent shall review and sign all TCPs prior to submittal. Acceptance of a TCP is based on the Contractor's certification that the plan is in conformance with the ATM and the specifications.

All TCPs submitted shall indicate the periods for which the TCP will be in effect. Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

When a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements is in effect for this project, all movements of oversize and overweight vehicles in or near traffic within the project limits will be in accordance with the provisions of the approved TCP. The TCP shall specify traffic control devices that will be required for these operations.

There shall be no work within the project limits until the Contractor has implemented an approved TCP for the work proposed. The number of traffic control devices indicated on the TCPs, plans, and Standard Drawings are a minimum. If unsafe conditions occur, the Engineer may require additional traffic control devices.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. The Contractor shall provide a Worksite Traffic Supervisor who shall be responsible for the Contractor's maintenance of traffic operations on a 24-hour basis.

1.	Qualifications. The Worksite Traffic Supervisor shall understand the requirements of the ATM, the plans and the specifications and meet at least one of the following:

a.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA).

b.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Markings Specialist by the International Municipal Signal Association (IMSA).

c.	Be currently certified as a Worksite Traffic Technician by (ATSSA).

Items b and c require documentation of a minimum of twelve months of supervisory level worksite traffic control or twelve months of responsible charge of such work. "Responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system. Having persons that actually perform labor under one's control would satisfy this requirement.

2.	Duties. The Worksite Traffic Supervisor's duties shall include the following:

a.	Prepare the TCPs and public notices and coordinate traffic control operations with the Engineer.

b.	Inspect the condition and position of all traffic control devices in use on the project at least once each day and once each night, to ensure that devices are in proper working order, clean, visible and conform to the approved TCPs in use. Furnish a detailed written report of each inspection to the Engineer within 24 hours.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate appropriate traffic control needs and ensure that the proper traffic control devices necessary for safe and efficient traffic movement are available.

e.	Review work areas, storage of equipment, and handling and storage of materials relative to traffic safety.

f.	Hold traffic safety meetings with the superintendents and foremen of the Contractor and subcontractors prior to beginning construction, and periodically thereafter as necessary or as directed by the Engineer. The Engineer shall be provided the opportunity to attend these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all of the flaggers meet the requirements of Subsection 643-3.04.

643-1.05 CONSTRUCTION PHASING PLAN. A Construction Phasing Plan shall be submitted at least 5 working days prior to the Preconstruction Conference for approval by the Engineer and consist of the following:

1.	Designation of a Worksite Traffic Supervisor including his resume, written verification of his credentials and the telephone numbers where he can be reached 24-hours a day.

2.	A plan for each phase or segment of the project. Changes shall be submitted to the Engineer for approval 15 days in advance of their proposed implementation.

3.	TCPs for the first phase of the project with both the permanent and temporary traffic control measures shown including the times of use of each TCP.

643-2.01 MATERIALS. Materials for traffic control devices shall conform to the requirements set forth below:

1.	Signs. Permanent Construction Signs, Construction Signs and Special Construction Signs including sign supports shall conform to the requirement of Section 615, Standard Signs, the ATM and ASDS. The size of each Special Construction Sign shall be clearly and neatly marked in 75 mm high black numerals on its back.

2.	Portable Sign Supports. Portable sign supports shall be wind resistant with no external ballasting and capable of supporting a 1.2 m X 1.2 m traffic control sign such that the height of the sign above the adjacent roadway surface is that required by the ATM. The sign support shall support the traffic control sign vertically.

3.	Barricades and Vertical Panels. Barricades and vertical panels shall be constructed of wood, metal or plastic and conform to the requirements of the ATM and the Standard Drawings. Type III Barricades shall have a minimum length of 2.4 m.

4.	Portable Concrete Barriers. Portable concrete barriers shall conform to the requirements of Standard Drawing G-45. Each barrier shall be equipped with at least two side-mounted retroreflective reflectors (or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm from the top of the barrier), for each direction of traffic. The reflectors (or tape) shall be yellow if the barriers are used at centerline and white if used on the roadway shoulder.

5.	Warning Lights. Warning lights shall be Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) conforming to the requirements of the ATM.

6.	Drums. Drums shall be plastic and conform to the requirements of the ATM and the Standard Drawings.

7.	Traffic Cones. Traffic cones and/or tubular markers shall conform to the requirements of the ATM and the Standard Drawings. The minimum height shall be 710 mm. All cones and tubular markers shall be reflectorized.

8.	Interim Pavement Markings. Interim pavement markings shall be either paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate. The markings shall be applied in accordance with Section 670 and the manufacturer's recommendations.

9.	High Level Warning Devices. High level warning devices shall conform to the ATM and the Standard Drawings.

10.	Temporary Crash Cushions. Temporary crash cushions shall have been tested as per the procedures set forth in National Cooperative Highway Research Program (NCHRP) Report 350, Test Level 3. Certification shall be provided by the manufacturer directly to the Engineer. Permanent crash cushions shall not be used as temporary crash cushions.

11.	Sequential Arrow Panels. Sequential arrow panels shall be Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) conforming to the requirement of the ATM and the Standard Drawings.

12.	Portable Changeable Message Board Signs. Portable changeable message board signs shall conform to the requirements of the ATM.

13.	Plastic safety fence shall be construction orange, 1.2 m high and shall be as manufactured by one of the following companies, or approved equal:

a.	“Safety Fence” as manufactured by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” as manufactured by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” as manufactured by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. This item shall consist of providing all labor, equipment and materials to provide a temporary sidewalk surfacing as required by an approved Traffic Control Plan.

a.	The materials shall be a minimum of 12 mm plywood for areas that are continuously supported by subgrade and 25 mm plywood for areas that are not continuously supported.

b.	The maximum unsupported length of 25 mm plywood shall be 750 mm.

c.	The surface of the plywood shall be free of irregularities. The height of plywood overlap joints shall not exceed 25 mm.

d.	The temporary surfacing shall be held in place by a method that will withstand 25 mph wind velocities.

15.	Temporary Guardrail. Temporary Guardrail shall conform to the standard drawings and section 606 of the standard specifications.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. The Contractor shall keep the work, and portions of the project affected by the work, in such condition that traffic will be accommodated safely. Traffic control devices and services shall be provided and maintained both inside and outside the project limits both day and night as needed to facilitate traffic guidance.

Unless otherwise provided herein, the Contractor shall keep all roadways undergoing improvement open to traffic. Temporary closure of residential, commercial or street approaches requires prior approval of the Engineer. The Contractor shall provide access through the project for emergency vehicles and school and transit busses. All locations requiring redirection or stopping of the traveling public shall be properly signed and/or flagged by the Contractor.

The Contractor's equipment shall stop at all points of intersection with the traveling public unless satisfactory traffic control measures, are shown on the approved TCP.

All illumination and signalization shall remain operational as per the requirements of Subsection 660-1.05, Maintaining Existing and Temporary Electrical Systems. Signal heads shall be re-aligned as necessary in accordance with the ATM when approach lanes are moved. Any modifications to existing traffic signals shall be coordinated with the agency responsible for their maintenance and operation. Flood lighting at night shall be in accordance with the ATM and be adjusted such that it does not shine into oncoming traffic.

The Contractor shall provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times except when pedestrians or bicyclists are prohibited by regulation. Whenever construction activity encroaches onto the safe route in a traffic control zone the Contractor shall station an employee at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Roadway lane and shoulder widths in existence prior to the start of construction shall not be reduced without an approved TCP The Contractor shall maintain a 0.6 m minimum clear area between the edge of traveled way and the work area. Use either barricades, traffic cones, or drums for delineation of this area. These traffic control devices shall be placed on the work side of the clear area and be spaced in accordance with the ATM.

If the Contractor is allowed to maintain traffic on an unpaved surface, the construction shall be conducted in such a manner as to provide a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage. In advance of other grading operations, sufficient fill shall be placed at culverts and bridges to permit traffic to cross smoothly and unimpeded. Part width construction techniques shall be employed when the traffic is routed through roadway cuts or over embankments under construction. The material shall be excavated or placed in layers and the construction activities shall be alternated from one side to the other, with traffic routed over the side opposite the one under construction.

Where so provided on the plans or an approved TCP, the Contractor may detour traffic. The detour routes shall be maintained by the Contractor during times of use in such condition that traffic will be accommodated safely. When no longer required, the detour shall be obliterated and appropriate areas topsoiled and seeded.

In general, all roadway crossings should be made while maintaining traffic as described above. If two-way traffic cannot be maintained, whether on the existing roadway or a detour, half-width construction or a road closure may be allowed and must be shown on an approved TCP. The TCP shall indicate the duration and conditions of closure. Roadway crossings shall be scheduled so as not to delay school busses and peak hour traffic. For road closures the Contractor shall post at the site of the closure, within view of waiting traffic, the time the closure started and the time the road will again be open to traffic.

643-3.03 PUBLIC NOTICE. The Worksite Traffic Supervisor shall give notices of changes, delays or road closures to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Visitor's Association

Alaska Carriers Association

Alaska State Troopers

Local Police Department

Local Fire Department

Local School & Transit Authorities

Local Emergency Medical Services

Local Media (Newspapers, Radio, Television)

Railroads (Where applicable)

U.S. Postal Service

The Contractor shall also provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project, and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These shall be for alerting the Contractor of emergencies which will require passage of emergency vehicles through the project. When so notified the Contractor shall use all equipment and effort necessary to expedite rapid passage.

The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance of commencing construction, resuming construction after seasonal suspension, or any scheduled delay, or closure of driving lanes within the project corridor. The Contractor shall then run continuous one-sixteenth page newspaper advertisements for the duration of that delay, or closure. The advertisements shall be published in the following newspapers:

1.	Anchorage Daily News

2	Bristol Bay Times.

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section. These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractor's name and a "hot-line road report" telephone number for the public to access a pre-recorded message with current roadway status.

Advertisements shall be promptly cancelled when they have served their purpose. The Worksite Traffic Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order is not required for newspaper advertisements, the Notice to Proceed shall constitute the notice required to initiate newspaper advertisements.

643-3.04 TRAFFIC CONTROL DEVICES. Prior to the start of construction operations, the Contractor shall erect such permanent and temporary traffic control devices as may be required by the approved TCPs. Traffic control devices shall be used only when they are needed. Advisory speeds, when necessary, shall be determined by the Engineer.

For lane closures on multilane roadways, sequential arrow panels shall be used. When required for night time operations, flashing warning lights shall be used to mark obstructions or hazards and steady-burn lights shall be used for channelization.

During non-working hours and following the completion of a particular construction operation, all unnecessary traffic control devices shall be removed. Sign panels that are post mounted and cannot be readily removed shall be entirely covered with either metal or plywood sheeting.

Reflective sheeting on signs, drums, barricades and other devices shall be kept clean.

All traffic control devices shall meet the requirements of American Traffic Safety Services Association (ATSSA), "Quality Standard for Work Zone Traffic Control Devices".

Any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while their use is required on the project shall be immediately replaced by the Contractor. The Contractor shall stock repair parts for each Temporary Crash Cushion used on the project. If a crash cushion is damaged it shall be repaired within 24 hours.

All items paid for under this section shall remain the property of the Contractor and shall be removed upon completion of the project.

1.	Embankments. Install portable concrete barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as called for on the plans or TCPs to delineate open trenches, ditches, other excavations and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. The Contractor shall limit pavement edge and lane edge drop-offs as specified under Subsection 401-3.11. When the depth of paving is greater than 50 mm and the paving of adjacent travel lanes or paved shoulders cannot for some unforeseen circumstance be completed to the same elevation before the end of the paving shift, the appropriate signing shall be installed: CW24-1, (Uneven Lanes), CW8-9A, (Low Shoulder), CW14-3, (No Passing Zone), R4-1, (Do Not Pass), and R4-2, (Pass with Care). If the section in question is longer than 800 m in length additional signs shall be placed at 460 m intervals.

3.	Fixed Objects. Vehicles working within 4.6 m of the edge of traveled way shall be equipped with flashing warning lights. The vehicle's flashing warning lights may be emergency flashers, flashing strobes or rotating beacons.

Private vehicles, idle construction equipment, construction material stockpiles and other items deemed by the Engineer to be fixed objects shall be located outside the clear zone at all times. Parking of equipment in medians will not be allowed.

Where, due to land features or lack of right-of-way, it is not feasible to meet the above restrictions, equipment shall be parked as far away as practical but a minimum of 4.6 m from the edge of traveled way as approved by the Engineer. Traffic control devices for identifying hazards including flashing warning lights shall be used to delineate the equipment when parked in this manner. These traffic control devices will not be paid for but will be considered the Contractor's responsibility.

4.	Flagging. Flagging shall include the furnishing of trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, for the control of traffic through the work zone. Each flagging operation shall be approved by the Engineer prior to its implementation and shall be adjusted as conditions change or as directed by the Engineer

Prior to beginning work, and at the start of each construction season thereafter, flaggers shall attend the special videotape training session provided by the Engineer. The Worksite Traffic Supervisor shall certify in writing that all flaggers are personally familiar with and meet the requirements of the ATM and have attended the annual training before being allowed to direct traffic.

Flaggers shall maintain their assigned posts at all times, unless relieved by another qualified flagger or the need for flagging traffic no longer exists. Flagger signs are to be removed when a flagger is not present. The flaggers area should be free of encumbrances, such as parked vehicles, so the flaggers are readily visible.

The Contractor shall provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

No signalized intersection shall be flagged without prior written approval of the Engineer. When a signalized intersection is flagged the traffic signal shall either be turned off and covered or be placed in the All-Red Flash mode. Changing traffic signal modes, turning off or turning on traffic signals, shall be coordinated with and approved in writing by the agency responsible for signal maintenance and operation, and by the Engineer.

5.	Pilot Cars. Pilot car operations may be approved where the route through a construction work zone is particularly hazardous, so involved or frequently altered as to preclude adequate signing, or where one-way traffic is deemed by the Engineer to be necessary. Pilot cars shall not be used to avoid localized traffic control at several locations. The operation shall be organized so that no individual vehicle has a waiting period of more than 20 minutes, but this does not imply that twenty minutes will be allowed in all cases. Multiple pilot car operations within a project or adjoining projects shall be coordinated to minimize the inconvenience of the traveling public. Two or more pilot cars may be specified to provide two-way traffic through the work zone to reduce the waiting period. The flagger or pilot car operator shall record each departure time of the pilot car in a bound field book furnished by the Engineer. Whenever practicable, the flagger shall advise the motorist of the reason for the delay and the approximate length of time that the traffic will be delayed. The Contractor must make every reasonable effort to yield right-of-way to the driving public and prevent excessive delay. The vehicle selected for a pilot car shall be an automobile or pickup with the name of the Contractor prominently displayed and shall be equipped with a two-way radio for contact between flaggers and other pilot cars. A G20-4 sign, (Pilot Car Follow Me), shall be mounted on the rear a minimum height of 1.5 m above the driving surface. Provisions shall be made for identification of the last vehicle in the column.

When pilot cars are authorized, they shall be in force prior to beginning work and continue until no longer required or all traffic control devices required for non-working hours are properly in place and functioning.

6.	Street Sweeping. All paved portions of the roadway and haul routes open to the public shall be kept free of loose material, including sections of roadway off of the project where loose material is deposited as a result of the contractors operations. The street sweeper shall be capable of collecting materials rather than ejecting them to the shoulder of the road.

7.	Watering. The Contractor shall furnish, haul and place water for dust control and pavement flushing, as directed. Water trucks shall be capable of providing a high pressure water stream to flush the pavement and a light water spray for dust control. If the flushing operations contaminate or fill adjacent catch basins the contractor shall clean and restore them to the same condition they were in prior to his operations, including sections of roadway off of the project where flushing is required. The application of water shall be under control of the Engineer.

If water is to be taken from a lake, stream, or other natural water body, the Contractor shall obtain a water removal permit from Alaska Department of Natural Resources. The Contractor shall also comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

643-3.05 AUTHORITY OF THE ENGINEER. When, in the opinion of the Engineer, conditions are such that the safety and/or convenience of the traveling public are adversely affected, the Contractor will be immediately notified in writing. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). In no case shall this time exceed 24 hours. In the event that the Contractor fails to take the corrective action(s) within the specified time, (a) The Engineer will immediately direct that the offending operations cease until the defect(s) is (are) corrected and (b) the Engineer reserves the right to order the corrective action(s) be accomplished by outside forces. The cost of work by outside forces shall be deducted from any moneys due or that may become due under the terms of this contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. When Item 643(23), Traffic Price Adjustment, is shown on the bid schedule, for each minute that any lane of traffic is not open to full use by the traveling public, the Contractor will have payment for this contract reduced at the rate listed below (based on highway user costs), measured to the nearest minute for the ADT published by the Department's Planning section. The Engineer shall determine whether the roadway is opened to full use.

The Traffic Price Adjustment shall be assessed for lane closures or reductions that are unauthorized. Lane closures and/or lane reductions that have been shown in the contract or authorized in writing by the Engineer are not subject to the Traffic Price Adjustment.

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| Less than 1,000 | $2 |
| 1,000 - 4,999 | $10 |
| 5,000 - 9,999 | $30 |
| 10,000+ | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month prior to seasonal suspension of work, the Contractor shall schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the work he expects to complete before shutdown and the condition the roadway is to be in. The Contractor shall then schedule a field review for acceptance by the Department for winter maintenance. At the field review a punch list will be prepared for implementation prior to acceptance. In order for the Contractor to be relieved of winter maintenance responsibility, all roads shall be left with a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage and adequate safety facilities shall be in place. All illumination and signals, including vehicle detectors, shall be in good working order. After acceptance for winter maintenance and until issuance of an order for the resumption of construction operations, maintenance of the facility agreed upon will be the responsibility of the Department. The Department will only accept maintenance responsibility for those portions of the work that are open to the public for use, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. Maintenance for all other portions of the work, shall remain the responsibility of the Contractor. The Engineer will list all portions of the work for which the Department will accept maintenance responsibility during a seasonal suspension of work in a letter of "Acceptance for Winter Maintenance." The Contractor shall retain all contractually required maintenance responsibilities until receipt of this letter.

If work is suspended due to unfavorable weather, other than seasonal, failure of the Contractor to correct conditions unsafe for the workmen or the general public, failure to carry out provisions of the contract, or for failure to carry out orders of the Engineer, all costs for maintenance of traffic during the suspended period shall be borne by the Contractor.

When work is resumed, the Contractor shall replace or renew any work or materials lost or damaged because of temporary use of the project. Remove to the extent directed by the Engineer, any work or materials used in the temporary maintenance and shall complete the project as though its prosecution had been continuous and without interference.

643-3.08 CONSTRUCTION SEQUENCING. Construction sequencing detailed in these Special Provisions, and the plans is a suggestion only and is not intended to prevent the Contractor from proposing alternative construction sequencing.

Throughout the duration of the project, the existing roadway configuration shall be maintained (i.e., the number of lanes and their respective widths) except for restrictions to traffic allowed in the special provisions and addressed through approved TCPs. A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or stops traffic. An approved TCP is required before any restriction to traffic is implemented.

No restriction to traffic will be allowed during the times listed below:

1.	On Monday through Friday, two traffic lanes shall be maintained between the hours of 7:00 AM to 9:00 AM, and 4:00 PM to 6:00 PM.

2.	During a work shift, a minimum of one traffic lane shall be maintained at all times except that a full road closure of two hours duration, for each occurrence, will be allowed for the installation or removal of pipes crossing the road. A full road closure between 10:00 PM and 6:00 AM will also be allowed to install or remove each structural plate pipe arch. Short duration road closures, not to exceed 20 minutes, may be allowed with the approval of the Engineer.

3.	Two lanes of traffic shall be restored at the end of a work shift.

643-3.09 INTERIM PAVEMENT MARKINGS. Permanent or Interim Pavement Markings in accordance with this subsection, details shown on the plans, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift. This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal or covered with black removable preformed marking tape.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings.

The Contractor shall maintain all Interim Pavement Markings for their intended life without additional compensation for any reapplication that may be required. There will be no compensation to upgrade Interim Pavement Markings required for work operations lasting up to 3 days to those required for work operations lasting up to 2 weeks.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Interim Pavement Markings on final pavement surfaces. When used they shall be completely removed and disposed of in conjunction with the placement of the final markings. The complete removal shall include any residual adhesive that might misguide motorists. Final pavement markings on finished pavement surfaces and interim pavement surfaces shall be in place before work is suspended for the winter.

Construction should be staged so that no traffic is routed over conflicting markings for more than one continuous workshift. If traffic is routed over conflicting markings during a workshift the roadway shall be delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.

Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for interim pavement markings on seal coat and surface treatment pavements. The markers shall be installed in accordance with the manufacturers instructions prior to the application of the asphalt surface material and cover coat. The vinyl protective covers shall be removed after application of the asphalt pavement.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat. The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days. Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment. Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

643-4.01 METHOD OF MEASUREMENT. During winter suspension of work no measurement of quantities will be made.

1.	Traffic Maintenance will be measured by the calendar day or lump sum and shall consist of all labor, materials and equipment required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan and maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required.

2.	Traffic Control Devices will be measured by the units shown in the Traffic Control Rate Schedule. The quantities to be paid for shall be the number of units of each of the items, installed and accepted, in place. Construction Signs are regulatory, guide or construction warning signs for which there is a designation in the ASDS. Permanent Construction Signs shall be as detailed in the plans. All other signs will be considered Special Construction Signs. Flagger paddles will not be measured for payment.

Warning lights, high level warning devices, vertical panels and sign supports required for individual traffic control devices will be considered subsidiary to their respective bid item. If a subsidiary item is not installed and operational on a traffic control device when required, the respective device will not be measured for payment.

3.	Portable Concrete Barrier will be measured per each nominal 3 m section placed to protect or channelize traffic as called for on the approved TCPs. Measurement for placement will be made for the initial placement and for each subsequent relocation when moved more than 3 m in any direction.

4.	Temporary Crash Cushions will be measured per each installation. Repair of temporary crash cushions will not be measured.

5.	Interim Pavement Markings will be measured by the single stripe station. A single stripe is a marking or a temporary raised pavement marker 100 mm in width. Wider striping will be measured as multiples of 100 mm. Centerline gaps will not be deducted from measurements. Installation of any word and symbol markings as well as the removal of the Interim Pavement Markings will be subsidiary to this item. The No-Passing Zone signing, as described in Subsection 643-3.09, will be subsidiary to this item.

6.	Flagging and Pilot Car will be measured by the hour for the actual number of hours such operations were performed as approved by the Engineer. Transportation to and from the work site will not be measured.

7.	Street Sweeping will be measured by the hour for the actual number of hours such operations were performed as approved by the Engineer. Time required to empty the sweeper will not be measured.

8.	Watering will be measured by the kiloliter of water applied. Weight measure or volume measure may be used at the discretion of the Engineer. If weight measure is used, the weight will be converted to kiloliters at 1.00 megagram per kiloliter for payment purposes. If volume measure is used, the volume will be converted to liters at 1.00 kiloliter per cubic meter for payment purposes.

9.	Portable Changeable Message Board Signs shall be measured by the calendar day for each sign used as shown on an approved TCP.

10.	Newspaper advertisements will not be measured for payment.

Providing a 24-hour toll free (1-800-###-####) "hot-line road report" telephone with pre-recorded message, and providing weekly notices with daily updates will not be measured for payment but will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. The accepted quantities, determined as provided above, will be paid for at the contract price per unit of measurement, respectively, for each of the pay items listed below that are shown in the Bid Schedule, which price and payment shall be full compensation for the work prescribed in this section.

Items required by this specification that are not included on a unit price basis on the Bid Schedule or not included in other items shall be considered subsidiary to Item 643(1) or 643(2) Traffic Maintenance, except the following:

Traffic Price Adjustment

If Item 643(23), Traffic Price Adjustment, is shown on the Bid Schedule the total value of this contract will be adjusted as appropriate for lane restrictions, closures or delays in completing the directed work, as determined by the Engineer.

Payment for Item 643(27), Traffic Control Devices will be made for the pay unit of accepted traffic control devices (construction signs, barricades, traffic cones and/or tubular markers, drums, plastic safety fence, sequential arrow panels, portable changeable message board signs, special construction signs, portable concrete median barriers, temporary pavement markings, temporary crash cushions, and watering) times the unit rate value contained in the Traffic Control Rate Schedule.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.50 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 4.00 |
| Sequential Arrow Panel, Type C | Each/Day | $55.00 |
| Portable Concrete Barrier | Meter | $20.00 |
| Temporary Crash Cushion | Each | $3,500.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Pedestrian Fence | Meter | $16.40 |
| Portable Changeable Message Board | Calendar Day | $100.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Temporary Pavement Markings Painted Markings Preformed Markings Raised Pavement Markings Temporary Cover Markings | Station Station Station Station | $984.25 $4265.00 $492.00 $10,000.00 |

Payment for Item 643(15) Flagging, will be on a contingent sum basis at the rate of $22.50/hour. Flagging used for the convenience of the Contractor, as determined by the Engineer, will not be paid.

Payment for Item 643(16) Pilot Car, will be on a contingent sum basis at the rate of$65.00/hour. Pilot cars used for the convenience of the Contractor, as determined by the Engineer, will not be paid.

Payment for Item 643(29), Newspaper Advertisements will be made at cost plus 15 percent. Payment will be authorized upon evidence of payment to the newspaper (paid receipt).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(1)	Traffic Maintenance	Calendar Day

643(2)	Traffic Maintenance	Lump Sum

643(3)	Permanent Construction Signs	Lump Sum

643(15)	Flagging	Contingent Sum

643(16)	Pilot Car	Contingent Sum

643(23)	Traffic Price Adjustment	Contingent Sum

643(27)	Traffic Control Devices	Contingent Sum

643(29)	Newspaper Advertisements	Contingent Sum

R222M

SECTION 644

SERVICES TO BE FURNISHED BY THE

CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion. The following office requirements shall be met:

1.	A minimum of 60 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area and an operable window of at least 0.25 m².

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of two electrical outlets..

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 10 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities provided.

7.	Telephone service available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

10.	Located within 1600 meters of the project.

644-2.02 FIELD LABORATORY. Delete the sixth sentence of the first paragraph and substitute the following: The water supply shall consist of a 1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following: The laboratory shall include a concrete slab, 2.4 meters by 3 meters by 100 millimeters thick, suitable for mounting a Gilson shaker and other equipment. The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, and adequate lighting and heat.

644-2.05 FIELD TRANSPORTATION. Delete the second sentence of the first paragraph and substitute the following: The vehicles shall be available from two weeks prior to commencing work through 30 days after issuance of the notice of project completion.

Delete the second paragraph and substitute the following: Vehicles of 450 kg minimum capacity shall be provided for this project. Each vehicle shall be a 1993 or newer model having less than 48,000 kilometers, and shall be equipped with flashing beacons and CB radios. Two of the vehicles shall have four wheel drive. All fuels, maintenance and insurance for the vehicles shall be furnished by the Contractor.

R63aM

644-2.06 SCALES. Delete the first and second sentences and substitute the following: When the bid schedule calls for payment on a megagram basis for material, the Contractor shall furnish and maintain platform scales, scalehouse, and an electronic computerized weighing system, as hereinafter specified. A permanent certified commercial scale may be used with the Engineer's written approval. Belt conveyor scales are not acceptable for determining pay weight when the contract documents provide for payment on a megagram basis.

Delete the second paragraph and substitute the following: Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following: Furnishing platform scales, tickets, scale house, and the electronic computerized weighing system, including all supplies such as: weigh tickets, paper, printer ribbons, diskettes, etc, and all maintenance and repair services necessary to keep the system functional, shall be supplied by the Contractor and are not a pay item but will be considered a subsidiary obligation. Platform scales, scale house and the electronic computerized weighing system shall remain the property of the Contractor upon completion of the work.

The Scales Diary is a bound book provided by the Engineer, to be completed by the Contractor’s scale person, that contains dates of action, type of material, source, time the scale opened and time the scale closed, times of scale balance, ticket sequence, time the haul for each material started and stopped, voided ticket numbers, truck numbers, times of tare and tare weights, and the scale person’s signature. In addition, the following information on any scale used to weigh materials for payment shall be provided in the Scale Diary:

a.	Owner of the scales, and scale locations.

b.	Manufacturer’s name, model serial number, maximum capacity, and type of scales (single beam, double beam, self-reading, etc).

c.	Date(s) the scales were installed and/or adjusted.

d.	Scale service company inspections and accuracy checks (attach copy).

e.	Division of Weights & Measures inspections and accuracy checks (attach copy).

f.	Time and dates of notification of any malfunctions.

The Scales Diary(ies) shall remain the property of the Engineer.

Delete the second sentence of the last paragraph and substitute the following: Platform scales shall include a weatherproof housing constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the weigh indicator, scale computer, ticket printer, and the printer used to produce the Transaction Summary Report. All components of the platform scales which could be physically manipulated in a manner to alter weights shall be protected by sealed enclosures, acceptable to the Engineer.

Add the following: The Contractor shall provide an electronic computerized weighing system with the following capabilities:

COMPUTER

1.	The scale computer shall have the ability to store project numbers and all pay item descriptions for multiple projects and products which are weighed with the scale system.

The self-reading scale system shall include the scale load cell, a sealed direct reading weight indicator, scale computer, ticket printer, sequential Transaction Summary Report printer, and the ability to record a complete shift's transaction on a 3½-inch high density diskette.

The scale computer shall read the output data from the weight indicator without any unit conversion. If a conversion of pounds to kilograms is necessary, the Transaction Summary printer shall also print the Gross Vehicle Weight of each load in pounds for the Engineer's review of the metric conversion factor. The conversion factor shall be 907.1847 kg/ton. All individual parts of the system shall be compatible with each other and suitable for field conditions.

Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic computerized weighing system.

2.	The scale computer shall store the following for each hauling vehicle utilized on the Project: vehicle identification number or the permanent commercial scales’ assigned unique vehicle identification number if so marked on the vehicle, the tractor license number, associated trailer license number(s) or the permanent commercial scales’ assigned unique vehicle identification number(s) if so marked on the trailer, tare weight, and maximum allowable vehicle weight (MAVW).

Vehicles shall be tared a minimum of once daily by the scale operator. The Engineer may request additional tares to be done at any time the scale is operational. The Engineer may also require that he be present when tares are done.

The MAVW shall be calculated by the Engineer and a listing of all vehicles and their MAVW(s) will be placed in the scalehouse by the Engineer. The MAVW will be the maximum allowable legal weight, as determined by the Engineer when overloads cannot be hauled in the traffic stream; the manufacturer's recommended maximum allowable gross vehicle weight as certified by the Contractor when on-road vehicles are allowed to haul overloads in the traffic stream; or an arbitrary number of 500 Mg when the Engineer allows unrestricted overloads out of the traffic stream.

The scale operator shall only utilize MAVWs which have been provided by the Engineer in writing. No tickets shall be issued to a vehicle until the Engineer provides the MAVW.

3.	During weighing operations, the electronic computerized weighing system shall compare each vehicle's gross weight to its MAVW. If the vehicle exceeds its MAVW the system shall alert the scale operator that an "overload" exists and the system shall not issue a ticket.

No payment will be made for any material hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions, and this Subsection. Non-conforming vehicles shall dump sufficient material so that they conform, and then be reweighed.

4.	The computer system shall have a battery backup as well as protection for power surges or brown outs. The computer system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage to allow shutdown of the hard drive without the loss of information.

TICKETS

The ticket printer furnished by the Contractor shall print a legible weigh ticket for the Engineer on continuous feed 10 kg paper with nominal dimensions of 215 mm by 140 mm, and with the following information on each ticket in the order listed:

a.	Sequential ticket number (8 digits, the first 3 digits being a Project code, the next being a product code [A, B, and C for the borrow classifications, D for Crushed Aggregate Base Course, E for asphalt, etc, as directed by the Engineer], and the last 4 digits being the sequential number for each product).

The permanent commercial scales may use “load number” to count the sequential loads for the Project. The load number shall be the different for each project and product hauled, and shall be reset to “O” at the beginning for each shift.

Whichever is used, this number shall be output to the data diskette given to the Engineer as Field 1, TKT.

b.	Project information (20 digits, the first 5 being the Project AKSAS number, the next 11 for the Project name, and the last 4 for a materials source reference).

c.	Date and Time of Dispatch (24 hour time).

d.	Pay Item name in words with "-Job Total", "-Shift Total", "-Daily Total", or "- Cumulative" Megagrams (Product Total This Ticket Sequence, Starting with "1", in megagrams, with each shift starting with “O”).

e.	Vehicle identification number, license number, and trailer license number(s). The permanent commercial scales may assign a permanently affixed tractor and trailer vehicle identification numbers, and shall maintain a current record of the corresponding license numbers.

f.	MAVW, as provided by the Engineer in writing.

g.	Gross weight in megagrams, rounded to the nearest megagram after conversion.

h.	Tare weight in megagrams, rounded to the nearest megagram after conversion.

I.	Net weight in megagrams, rounded to the nearest megagram after conversion.

All of the above items are to be printed by the ticket printer with a minimum of a 12 point font, and Items b. through c. above shall not be pre-printed. After printing, the weigh ticket shall be automatically advanced to a position where it can be torn off at a perforation and handed to the driver.

TRANSACTION SUMMARY REPORT PRINTER

The electronic computerized weighing system shall include a sequential Transaction Summary Report printer that will print out all transactions (keystrokes) made by the computer concurrently with the ticket printer. For permanent commercial scales, the Transaction Summary Report may be printed at the end of the company's daily shift with the Engineer's approval. The printer shall print all scales transactions including tares, voided tickets, and data changes made by the scale operator. The printer shall allow for the paper to be manually advanced so that the scale operator can write notes on the paper when special situations occur such as voided tickets, incorrect hauling unit number used, etc, which shall also be noted in the Scales Diary as provided under Subsection 109-1.02, Measurement of Quantities.

Transaction Summary Reports will be printed concurrently, or at the end of the shift in the case of a commercial scale if approved by the Engineer. The Report shall include the following information:

a.	Project number (first 5 characters of Field 11, PROJECT).

b.	Date (Field 2, DATE).

c.	Pay item.

d.	Materials source number (last 3 or first 2 characters of Field 10, PRODUCT, at the Engineer’s option).

e.	Sequential ticket number, or load number, at the Engineer’s option.

The sequential weigh ticket number shall be set to "1" at time 0:00 (12:00 pm) or prior to the first load being hauled at the beginning of each shift for each unique project number, pit number, and pay item combination. The project information, date, pay item, hauling unit identification number(s), their MAVW's, and the scale operator's name shall also be able to be set by the scale operator. Tare weights shall only be able to be changed by a tare weighing operation.

DATA DISKETTES

The electronic computerized weigh system shall also provide the Engineer with a 3½-inch high-density diskette at the end of the shift. The disk shall record all ticket information which was produced during the shift.

The data shall be stored in two files with the same information but different formats. The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation. The naming convention for this file shall be "yymmdd.dbf". The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end-of-file-mark following the last record. The naming convention for this file shall be "yymmdd.csv". If more than one scale is used on the Project, a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

If the Contractor is hauling from a permanent commercial scales operation, then the commercial vendor shall download his hard drive directly to a disk without conversion or manipulation at the end of the shift. He shall also provide conversion programs and training so that data can be converted into the information the Engineers requires.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, the Contractor shall correct, construct, or reconstruct the data file utilizing the sequential Transaction Summary Report or other information, as directed by the Engineer, as a data source. No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer. If written permission is obtained from the Engineer to weigh without the electronic computerized weighing system for a minor equipment failure, a data file, acceptable to the Engineer, shall be constructed as described above.

The fields for each record shall be in the following format and order. Other data fields may also be provided but shall follow the fields in the required format.

| Field | Field Name | Type | Width |
| --- | --- | --- | --- |
| 1 | TKT | Character | 4 (right justified w/leading blanks) |
| 2 | DATE | Character | 8 (mm/dd/yy) |
| 3 | TIME | Character | 5 (hh:mm) (24 hour) |
| 4 | UNIT_ID | Character | 5 (right justified w/leading blanks) |
| 5 | MAVW | Numeric | 6 (kilograms) |
| 6 | GROSS | Numeric | 6 (kilograms) |
| 7 | TARE | Numeric | 6 (kilograms) |
| 8 | NET | Numeric | 6 (kilograms) |
| 9 | COMMENTS | Character | 20 |
| 10 | PRODUCT | Character | 20 |
| 11 | PROJECT | Character | 20 |
| 12 | GROSS | Numeric | 6 (pounds) |

The system shall be able to generate the summary Report, either during or at the end of the day or shift, which summarizes the number of loads and total net weight for each Date, Project, and Product. The original of the end of day Report shall be given to the Engineer at the end of each shift.

A user instructional manual shall be available for each scale which explains the complete scale operation. A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities, an amount equal to the value of those expenses will be deducted from the value of the item before payment.

(1/9/97)R145M

644-3.01 METHOD OF MEASUREMENT. Add the following: Field transportation will be measured per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made.

644-4.01 BASIS OF PAYMENT. Delete the sixth paragraph and substitute the following: Field Transportation. The price per vehicle will be full compensation for furnishing the vehicle, fuel, and all required maintenance and insurance.

Change the pay unit for Item No. 644(6), Field Transportation, from "Lump Sum" to "Each".

(01/24/97)R63aM

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01 DESCRIPTION. This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01 GENERAL. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/BAT apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 WAGES. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A310. Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 SUBCONTRACTS. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program For	Labor Hour

1 Trainee/Apprentice

(10/29/91)S16

Add the following Section:

SECTION 646

EQUIPMENT RENTAL

Special Provisions

646-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

646-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

646-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

646-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

646-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

646-5.01 BASIS OF PAYMENT. The pertinent contract bid price per hour for the equipment shown in the Bid Schedule shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

646(1)	Wide Pad Dozer, 48 kW Minimum	Hour

(6/6/95)R15M

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Add the following under

1. Paint:

g.	All painted traffic markings shall be applied in the year following construction of the asphalt surface treatment, between May 1 and June 30. The entire road surface shall be swept within 48 hours preceding the application of the painted traffic markings.

The Contractor shall submit a schedule for the application of pavement markings to the Engineer for approval prior to the final inspection of the project, not including the painted traffic markings.

670-3.05 PRELIMINARY SPOTTING. Add the following: After acceptance of the asphalt treated base layer, but prior to surfacing, the Engineer will check all horizontal and vertical curves to verify the accuracy of the initial passing/no passing zone layout in the plans. The Engineer will adjust the no passing zones in accordance with Chapter 3 of the Alaska Traffic Manual. R192

670-5.01 BASIS OF PAYMENT. Delete the second paragraph and substitute the following: Payment will be made separately from the remainder of the contract following completion of the work, and shall be full compensation for layout, cleaning of pavement, painting traffic markings, furnishing paint and all other materials, equipment and labor necessary to complete the work prescribed in this section. Contract completion time shown in the Invitation For Bids shall not include the application of traffic markings.

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.04 STORAGE AND APPLICATION TEMPERATURES. Add the following to Table 702-1:

| Type and Grade of Material | Spray C | Mix C | Storage C |
| --- | --- | --- | --- |
| HFMS-2S | 65-75 | - | 65-75 |

(7/28/95)R204M

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 | Grading CC-1 |
| --- | --- | --- |
| 25 mm | 100 |  |
| 19 mm | 70-100 | 100 |
| 9.5 mm | 50-79 | 54-84 |
| 4.75 mm | 35-58 | 34-54 |
| 2.36 mm | 20-47 | 17-37 |
| 600 µm | 10-26 | 7-22 |
| 300 µm | 6-19 | 4-17 |
| 75 µm | 0-6 | 0-5 |

R117M

703-2.07 SELECTED MATERIAL. Add the following to Item 1., Selected Material, Type A: It shall have 20 to 55 percent by weight of particles passing the 4.75 mm sieve. R89M

703-2.09 SUBBASE. Delete the grading for Subbase C in Table 703-6 and add the following:

703-6

REQUIREMENTS FOR GRADING FOR SUBBASE

Percent Passing by Weight

|  | Grading |
| --- | --- |
| Sieve Designation | C |
| 25 mm | 100 |
| 4.75 mm | 40-75 |
| 2 mm | 25-55 |
| 75 µm* | 8-12 |

* Gradation shall be determined on that portion passing the 75 mm screen.

703-2.10 POROUS BACKFILL MATERIAL. Delete this subsection in its entirety and substitute the following: Porous backfill material shall consist of crushed or naturally occurring sand, gravel, or rock, devoid of muck, frozen matter, roots, sod or other deleterious matter. It shall conform to the grading requirements of Table 703-7, as determined by ATM T-7.

TABLE 703-7

REQUIREMENTS FOR GRADING FOR

POROUS BACKFILL MATERIAL

| Sieve Designation | Percent by Weight Passing |
| --- | --- |
| 200 mm | 100 |
| 6.7 mm | 0-10 |
| 75 µm | 0-5 |

Delete this section in it's entirety and substitute with the following:

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL. Topsoil furnished by the Contractor may consist of the existing, natural organic blanket representative of the project area. A quality test, as defined by ATM T-6, shall be performed on the soil to determine the organic content of the soil. The results shall be supplied to the Engineer.

If the soil is found to have an organic content of 5% or more the soil may be reused and spread on the finished slopes where topsoil is noted on the plans. Roots, stumps, unnatural material, and rocks greater than 75 mm in diameter shall be removed from the organic material before it is graded onto the finished slope.

If the soil is found to have an organic content of less 5% the soil cannot be used as topsoil for the project. In that case the Contractor shall furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5% or more, as determined by ATM T-6. The material shall be reasonably free from roots, clods, hard clay, rocks greater than 75 mm in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free-draining and non-toxic. The Contractor shall notify the Engineer of the location from which he proposes to furnish topsoil at least 30 calendar days prior to delivery of topsoil to the project from that location. The topsoil and its sources will be inspected by the Engineer before approval will be granted for its use.

(11/8/95)R208M

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Wood Fiber, Paper Cellulose Fiber or Blended Wood-Paper Mulch. Wood cellulose fiber mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors. The fiber mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry. The processed mulch material shall have characteristics to form a blotter-like ground cover on application, having moisture absorption and percolation properties and the ability to cover and hold grass seed in contact with soil.

The wood or cellulose fiber mulch material shall be shipped in packages of uniform weight (plus or minus 5%) and bear the name of the manufacturer and the air-dry weight content.

The wood or cellulose fiber shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial tackifier shall be used on slopes of 1V:2H. The amount added will be as recommended by the manufacturer.

(3/17/97)R206M

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT. Delete this subsection in its entirety and substitute the following: Geotextile materials for embankment separation shall meet the requirements of AASHTO M 288 for Separation (medium survivability). The Apparent Opening Size (AOS) of the fabric shall be less than 0.6 mm.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL. Delete this subsection in its entirety and substitute the following: Geotextile materials for subsurface drainage shall meet the requirements of AASHTO M 288 for Subsurface Drainage. The Apparent Opening Size (AOS) of the fabric shall be less than 0.6 mm.

729-2.04 SEDIMENT CONTROL. Delete this subsection in its entirety and substitute the following: Geotextile materials for Sediment Control shall meet the requirements of AASHTO M 288 for Sediment Control. The Apparent Opening Size (AOS) of the fabric shall be less than 0.84 mm.

R209M

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(1/21/95)R81M

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS (METRIC)