SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The following are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Geotechnical Report, "-NA-".

b.	Laboratory Manual of Alaska Test Methods and Standard Practices (Price $20.00)

c.	Design Computations

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0639.

3.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

4.	Sieve weight factors for Sonte Mastic Asphalt (SMA) in Table 407-7 have been changed.  A deduction to the Contractor’s payment for SMA pavement has been added to 407-4.02 for failure to cut cores and/or backfill voids left by sampling in a timely fashion.  An upper specification limit for density has been included.

- There are special weather restrictions related to Stone Mastic Asphalt.  Refer to Special Provision sections 108-1.04 Limitations of Operations, 108-1.07 Failure to Complete on Time, 407-3.01 Weather Limitations, and 643-3.07 Maintenance of Traffic During Suspension of Work.

PART 4

SPECIAL PROVISIONS

to the STATE OF ALASKA

INTERIM STANDARD SPECIFICATIONS

FOR HIGHWAY CONSTRUCTION (METRIC)

94M

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.73 NON-FROST SUSCEPTIBLE. Add the following subsection: Material that contains 6 percent or less passing the 75 μm screen as determined by sieve analysis performed on minus 75 mm material. (01/31/94)R1M

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Special Provisions

102-1.12 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (10/28/96)R171

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01 CONSIDERATION OF PROPOSALS. In the second and third paragraphs, replace form 25D-5 with the following: "form 25D-5(C)".

(5/5/95)R82M

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. Contractor shall use the locate call center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Anchorage Telephone Utility Anchorage Water & Wastewater Utility Chugach Electric Association ENSTAR Natural Gas Company Municipal Light & Power (Anchorage) Municipal Street Lights, Storm Drains & Traffic Lights (Anchorage) Prime Cable of Alaska

The Contractor shall call the following agency directly:

State (DOT & PF) Street Lights & Storm Drains	333-2411

All existing utilities shall remain in service until the new utilities are installed and placed in service.

There are various utility appurtenances located within the project limits. The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen. Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

The following specific coordination requirements are required for each utility:

Anchorage Water and Wastewater Utility (AWWU)

The Contractor shall schedule and coordinate preconstruction and post-construction inspections of AWWU facilities in the project area.  The Contractor shall call AWWU Field Services at 562-2762 to obtain a point of contact.  At least fourteen (14) calendar days prior to beginning construction, the Contractor shall notify the AWWU point of contact in writing.  A copy of the notice shall be provided to the Engineer.

The Contractor shall furnish traffic control to facilitate both inspections and for any work required to correct deficiencies noted during the inspections.  The Engineer, Contractor, and AWWU shall witness the condition and location of each AWWU facility anticipated to be impacted by the project.  The Contractor shall have no claim that AWWU facilities were deficient prior to construction except for deficiencies specifically listed in the record of the preconstruction inspection.  If preconstruction deficiencies are noted, the Contractor shall coordinate with AWWU so that AWWU or the Contractor, at AWWU’s option, may correct the deficiencies.

During construction, the Contractor shall protect and maintain all AWWU plant impacted by the project in operable condition during all phases of construction.  Following construction, the Engineer, Contractor, and AWWU shall verify the condition of each AWWU facility within the project limits.  Any deficiencies noted during the post-construction inspection, (other than deficiencies noted in the pre-construction inspection record which had not previously been corrected)

shall be corrected by the Contractor at the Contractor’s expense.

Municipal Light & Power (ML&P)

The Contractor shall install culverts for future ML&P electrical conduits.  Reference Section 603 and the drawings for specific information.

ML&P and Chugach Electric Association

When working near facilities belonging to either of these agencies, the Contractor shall adhere to requirements set forth in “Construction or Maintenance Near Electrical Facilities” and “Electrical Facility Clearance Requirements” attached to these specifications as Appendix A.

Prime Cable

The Contractor shall install pipes for future Prime Cable plant.  Reference Section 680 and the drawings for specific information.

Anchorage Telephone Utility (ATU)

The Contractor shall install ducts for future ATU plant.  Reference Section 680 and the drawings for specific information.  R3

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following:  Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage. (8/5/93)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater. Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(7/2/93)S13

106-1.02 LOCAL MATERIAL SOURCES. Add the following after the first paragraph: The Contractor shall provide process control for reasonable assurance, that all materials submitted for acceptance conform to the contract specifications. Sampling and testing of all materials for process control, including screening, crushing, blending, stockpiling of aggregates, production and laydown of aggregate courses or mixtures, asphalt concrete mixtures, and monitoring of compaction, is the responsibility of the Contractor. Process control tests shall be made in accordance with the applicable test methods specified in the contract.

A process control plan shall be submitted at the pre-construction conference. The process control plan shall include, for each item being produced, the methods to be used for sampling and testing, the proposed testing frequency, personnel qualifications, and equipment descriptions. Process control will not be measured for payment but will be subsidiary to the applicable items being processed.

The Department has the exclusive right and responsibility for determining the acceptability of the construction and all incorporated materials. Acceptance testing by the Department is not to be considered as a replacement for process control testing by the Contractor. When the Contractor is not providing adequate process control testing, the Engineer may refuse to retest materials which have been shown to be unacceptable by standard acceptance testing procedures.

(2/14/95)R201

106-1.02 LOCAL MATERIAL SOURCES. Add the following: Prior to placing or removing any material in/from a location that is outside the project limits, the Contractor shall obtain a written statement from the State Historic Preservation Officer that material placement/extraction is not expected to impact any cultural resources. A copy of this statement shall be provided to the Engineer. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified. (5/24/96)R5

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO

PUBLIC

Special Provisions

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following to the third paragraph: When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits. Refueling and servicing of equipment shall not be performed adjacent to wetlands.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at 762-2575.

Add the following: The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels. The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract.  If the Contractor chooses to pursue permit modifications, such modifications shall be requested through the Engineer.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work which is permitted and specified by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(12/13/95)R7M

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Prior to removing, stockpiling, staging or disposing of any material or equipment in, on or from a location not previously permitted by the contract, the Contractor shall obtain all necessary permits and clearances required. These permits and clearances may include, but are not limited to, State Historic Preservation Office clearance, a Division of Governmental Coordination Coastal Consistency Determination, Alaska Department of Natural Resources Mining Reclamation Permit, Alaska Department of Environmental Conservation permits, Alaska Department of Fish and Game Title 16 permit, US Fish and Wildlife endangered species clearance, US Army Corps of Engineers clearances and permits regarding wetlands, City or Borough Flood Hazard permit, local development permits, permission of property owner, etc.

The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified.

The Contractor shall provide an environmental professional, approved by the US Army Corps of Engineers, to conduct a wetlands determination in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, that will be impacted by the Contractor's operations.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that all permits or clearances necessary have been obtained. Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action was required on the part of the Contractor.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

Add the following: The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels. The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for material extraction, excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract. If the Contractor chooses to pursue permit modifications, such modifications shall be requested through the Engineer.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work which is permitted and specified by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of at a location approved by the Engineer.

(1/31/97)R7M

107-1.16  CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.  Delete paragraphs four and five in their entirety, and substitute the following:  If utility facilities are damaged by the Contractor, the owning utility has the choice of making the repair or having the Contractor correct the damage.  The Contractor shall reimburse the utility for repair costs, or provide at no cost, all materials, labor and equipment if he repairs the damage.

The Contractor will not be responsible for the costs of repairing damaged facilities when:

1.	The utility mislocates the facility in the field by more than 0.75 m (2.5 feet) horizontally for non-frozen soil conditions, or

2.	When the location or existence of the buried facility is unknown by the utility.

(2/7/96)R8M

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01 SUBLETTING OF CONTRACT. Delete numbered item 1. in the second paragraph and substitute the following:

1.	Alaska Commercial Driver's License, with the appropriate endorsements for the class of vehicle to be operated.

Delete the next to last paragraph in this sub-section on page 38.

(11/6/95)R207M

108-1.03 PROSECUTION AND PROGRESS. Add the following: The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule. The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule. At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule. The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly. The CPM schedule must be finalized within 10 days of the Notice to Proceed.

2.	Schedule Requirements. The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	Schedule Updates. Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions. The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting. The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is shared equally.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks. This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

Preparation and updating of the CPM schedule and two week work plans will not be paid for directly. Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.

R11A

108-1.04 LIMITATIONS OF OPERATIONS.  Add the following paragraph:

The Contractor shall complete all pavement planing,  removal & replacement, and all pavement striping by September 10, 1997, for the portion of the project listed below:

Station “I” 11+500 to 12+620;

Station “G” 16+360 to 17+500;

It is the intent of this specification to complete work which may otherwise conflict with the upcoming 5th/6th Avenue rehabilitation project.  Therefore, the last three (3) weeks before the weather restriction (Section 407-3.01), the Contractor is urged to schedule work in these areas to proceed from Stations “I” 12+620 toward Station 11+500, and from Station “G” 17+500 toward Station 16+360.

108-1.05 CHARACTER OF WORKMEN, METHODS AND EQUIPMENT.  Add the following: The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project. This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)R13

108-1.07   FAILURE TO COMPLETE ON TIME.  Add the following to the first paragraph:

For each calendar day after September 10th that the completion requirements in 108-1.04 LIMITATIONS OF OPERATIONS are not met, $500.00 shall be deducted from any monies due the Contractor.  For the purposes of this deadline, the suspension of calendar days as specified in 108-1.06, item 1, Calendar Days shall not apply.  The amount of these deductions is to cover estimated expenses incurred by the Department  as a result of the Contractor’s failure to complete this work by the specified date.  Such deductions are liquidated damages and are not to be considered as penalties.

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES. After the ninth paragraph, insert the following: The Contractor shall furnish competent scale operators to weigh all materials measured and paid for on a weight basis.

The scale operator shall record to the nearest 50 kilograms the weights of all loads of material on a daily tally sheet. The scale operator shall also make out a weigh slip ticket for each load hauled showing the gross, tare and net weights. The original shall accompany the load and one copy shall be retained until any discrepancies have been resolved at the end of each day.

The scale operator's daily tally sheet shall also include the following information as applicable to the type of scales used:

1.	Name and number of project,

2.	Contract item number,

3.	Description of source,

4		Date,

5.	Load number,

6.	Truck identification mark,

7.	Time of weighing,

8.	Gross weight of each load,

9.	Tare weights,

10.	Net weights,

11.	Scale operator's signature, and

12.	Contractor's certification.

The original daily weight record shall be furnished to the Engineer at the end of each shift.

The Engineer may, at random intervals, designate previously weighed vehicles to be reweighed, in his presence, to verify the weight of the materials being purchased. This will include empty or loaded vehicles as the Engineer may designate.

No direct payment will be made for furnishing scale operators, equipment, and incidentals required. Costs thereof will be subsidiary to bid prices of the material being weighed.

(7/26/95)S11M

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by K-III Directory Corp., 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska -South Region. (3/24/97)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon receipt of current schedules from the Contractor. (9/21/92)R137

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section shall be considered a material breach of contract. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04 DEFINITIONS AND TERMS

1.	Broker. A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with its own equipment and employees within its certified category. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE). A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts. The affirmative action measures that shall be taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer. A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer. A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis.

8.	Revised DBE Utilization Goal. The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C. The Revised DBE Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved. Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01 UTILIZATION GOAL. The Original DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total basic bid amount. In order for the work of the DBE to be credited towards meeting the Original DBE Utilization Goal at time of contract award, the DBE must be certified by the Department in a category covering the CUF to be performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid and Award. In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the contractor submits less DBE utilization on Form 25A325C than is required to meet the Original DBE Utilization Goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (25A321A) shall be submitted. If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than is required by the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

2.	Phase II - Construction. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE. Prior written request by the Contractor and approval from the Engineer is required for the replacement of a DBE for any reason. If DBE replacement is approved, the Contractor is obligated to replace the DBE with another DBE for the same work in order to still meet the Revised DBE Utilization Goal. If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work to have been performed by the replaced DBE in order to have the Revised DBE Utilization Goal reduced.

120-3.02 GOOD FAITH EFFORT. The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract. Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

1.	Consideration of all subcontractable items. The Contractor shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification at least 10 calendar days prior to bid opening to all DBEs listed in the Department's most current DBE Directory certified to perform those work items identified in Form 25A324 of the bidder's/Contractor's interest in securing the DBE's participation in the execution of the work. Each contact with the DBE shall be logged on a "Contact Report" (Form 25A321A).

4.	Request for DBE participation on specific items of work or services. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE quotes are for the exact same work or service. Where the Contractor rejects a DBE quote as being non-competitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding. Documentation of follow-up contacts shall be logged on the "Contact Report" (Form 25A321A).

Items 4. through 7. will be utilized to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF). Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

a.	regular dealer,

b.	manufacturer,

c.	broker,

d.	subcontractor

e.	joint-venture, or

f.	prime contractor.

In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE shall be certified in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b.	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

2.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

3.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted within that category to the CUF of a broker. (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation which could include the hauling of materials for that work.)

4.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

5.	Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the Revised DBE Utilization Goal.

6.	Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm shall not be credited toward the Revised DBE Utilization Goal. The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01), or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

7.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the Revised DBE Utilization Goal.

8.	The Engineer shall consider the following criteria when determining what CUF is being performed by the DBE:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below. Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site. All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work. An exception to this requirement may be permitted where the DBE must perform a specialty task or where the work is in a remote area. In such instance, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the work, if the Department considers this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value. Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved. Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control. DBE leases and payments for equipment must be documented; Contractor withholding or retainage for DBE labor and equipment usage is not permissible. Two-party checks to individuals are not permissible.

e.	The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as defined by the Department. The work or provision of goods or services shall have a market outside of the DBE program (must be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed a superfluous step in the contracting or purchasing process and no DBE credit will be allowed.

There shall be no DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

g.	All subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE shall control all business administration, accounting, billing, and payment transactions (this requirement does not preclude the two-party check allowance described under i., below). The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

i.	Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE.

Two-party checks may be issued by the Contractor on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Engineer shall be notified in writing in advance. DBE credit will not be given for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before any DBE credit may be credited. The DBE supervisor must be regularly employed by the DBE and designated as a key employee in the DBE's certification records with the Department prior to prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identify payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the quantity of work of a bid item which involves a DBE is reduced by the Department, the Original and Revised DBE Utilization Goals on Form 25A325C are reduced proportionately.

120-3.04 DEFAULT OF DBE. In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default. The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, both of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Revised DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, retainage may be withheld from progress payments. The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, payments will be reduced as a disincentive. The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after the Original DBE Utilization Goal established on Form 25A325C in terms of dollars has been met, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUF work performed by DBE subcontractors not needed in the calculation to meet the Original DBE Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

Payment of the incentive will be made on the final estimate. The disincentive will be withheld in the form of retainage during the course of the project. If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

A Change Order is not required for DBE Adjustment. The Notice To Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(6/6/94)S33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-2.01 GENERAL. Add the following:

All fences designated by the Engineer shall be carefully removed to the right-of-way limit, or to the end of the span beyond the right-of-way limit. These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.

R112

202-2.04  REMOVAL OF PAVEMENT, SIDEWALKS, CURBS, ETC.  Add the following:  This work shall also include asphalt curbs designated for removal.

For disposal of waste asphalt pavement, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  A DEC permitting officer in Anchorage may be contacted at 269-7501.

Where existing curb & gutter is to be removed adjacent to existing inlets, catchbasins or other drainage-critical features, the Contractor shall asbuilt the existing curb & gutter to ensure proper replacement of curb.

R84aM

202-2.05  PAVEMENT PLANING.  Add the following Subsection:  The Contractor shall remove existing asphalt concrete pavement by cold planing at locations shown on the plans.  The surface of the pavement after planing shall be uniformly rough grooved or ridged.

The Contractor shall remove all planed material from the project immediately after planing.  Disposal areas shall be outside the project limits and in accordance with Subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc.

During the planing operation, the Contractor shall sweep the streets with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove all loosened material from the planed areas.  The removal operation shall follow within 15 meters of the planing machine. Street sweeping after the planing operation shall be paid under Item 643(17) Street Sweeping.

The Contractor shall not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 50 millimeters.  In the event that it is necessary to route traffic across such edges, an asphalt concrete transition not exceeding 1 vertical to 4 horizontal shall be placed adjacent to the edge and to all gutters.

A tolerance of 3 millimeters shall be maintained by the planer between adjacent passes.

The Contractor shall remove existing asphalt concrete pavement overlay from gutters adjacent to the area being planed.

The existing curb and gutter not designated for removal shall not be damaged or disturbed.  Any damage caused by the planing operation shall be removed and replaced by the Contractor at his expense.

The planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 1.5 meters wide and shall be equipped with cutting teeth placed in a variable lacing pattern to produce the desired finish.

The planing machine shall have the following capabilities:

1.	operating speeds from 0 to 12 meters per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the planing operation without leaving the controls,

6.	adjustable as to slope and depth,

7.	longitudinal grade control automatically actuated by the use of a 9-meter ski, and

8.	able to cut up to 76 millimeters without producing fumes or smoke.

The Contractor shall provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.

202-4.01  BASIS OF PAYMENT.  Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

202(15)	Pavement Planing	Square Meter

R143M

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Bedding and backfill materials shall meet the requirements for Selected Material, Type A, as specified in subsection 703-2.07 Selected Material. Pipe bedding and backfill material shall also pass the 75 mm sieve.

Selected Material, Type A pipe backfill shall extend a minimum of 300 mm above the pipe. Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material. Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material. All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the third paragraph: Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material.  Compaction shall be as approved by the Engineer.

(4/18/97)R25M

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01 MATERIALS. Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for crushed aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 300 µm | 5-34 |
| 150 µm | 3-22 |
| 75 µm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for crushed aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Crushed Aggregate Base Course at the unit price shown on the bid schedule for that item.

(12/11/96)R176M

Delete Section 401 in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-1.01 DESCRIPTION. This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

401-2.01 COMPOSITION OF ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN. Asphalt concrete mixtures shall be composed of aggregate, asphalt cement, and required additives combined within the limits for the type and class of asphalt concrete specified in the contract.

The Contractor shall provide an asphalt concrete mixture that meets the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete.

At least 15 calendar days prior to the production of asphalt concrete pavement mixture, the Contractor shall submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile. The proposed gradations must meet the requirements of Table 703-3, Asphalt Concrete Aggregate, for each type of asphalt concrete pavement specified in the bid schedule. Asphalt concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended. Sample sizes: 45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance in accordance with Section 106, and a temperature viscosity curve for the asphalt cement.

4.	A 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

From this information, the Engineer will establish the Job Mix Design which will become a part of the contract and shall be followed unless modified in writing. The Job Mix Design will be determined in accordance with ATM T-17 (version 01/93) and evaluated for conformance with the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete. Job Mix Design test results will be available within 7 working days after submittal. Approved Job Mix Designs will specify the target value for asphalt cement, additives, and the allowable temperature range for mixing.

Changes in the Job Mix Design warranted by changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio shall be submitted by the contractor in the same manner as the original submittal. A new Job Mix Design will only apply to asphalt concrete mixture produced after the Contractor submittal of the new aggregate gradation.

All mix designs after a Job Mix Design has been approved for the Type and Class of Asphalt Concrete will be assessed a fixed fee of $1,500.00 each.

Approved Job Mix Designs will have the full tolerances shown in Table 401-2 applied and will not be limited to the broad band listed in Table 703-3. Tolerances for the largest sieve specified will be plus 0% and minus 1%.

Temporary pavement shall meet the minimum asphalt concrete mix design requirements for Asphalt Concrete Type II, Class B.

Table 401-1

Asphaltic Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS "A" | CLASS "B" | CLASS "C" |
| --- | --- | --- | --- |
| Stability, newton, min. | 8,000 | 5,340 | 3,340 |
| Flow, 0.25 mm | 8-14 | 8-16 | 8-18 |
| Voids in total mix, percent | 3-5 | 3-5 | 2-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 | 35 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 | N/A |
| Voids in the mineral aggregate (VMA), min. |  |  |  |
| Type I Type II Type III | 12.0 13.0 14.0 | 11.0 12.0 13.0 | N/A N/A N/A |

*Dust-asphalt ratio is defined as the percent of material passing the 75μm sieve divided by the percent of asphalt (calculated by weight of mix).

401-2.02 AGGREGATES. Aggregate shall conform to the requirements of Subsection 703-2.04.

Aggregates for asphalt concrete mixtures shall be divided into a minimum of 2 piles, one coarse and one fine. If blend sand is used, it shall be an additional pile.

401-2.03 ASPHALT MATERIALS. The grade of asphalt cement will be specified in the bid schedule. The asphalt cement shall conform to the applicable requirements of Section 702. Asphalt cement may be conditionally accepted at the source. If the material is to be conditionally accepted at the source, the Contractor shall provide a manufacture's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the material is shipped.

If there is a change in the source of the asphalt cement, or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted for approval.

401-2.04 ANTI-STRIP ADDITIVES. Anti-strip agents shall be used in the proportions determined by ATM T-14 and shall be included in the approved Job Mix Design. At least 70% of the aggregate shall remain coated when tested in accordance with ATM T-14.

401-2.05 PROCESS QUALITY CONTROL. It is expressly understood that the contractor is solely responsible for the sampling and testing of material for process control of the asphalt concrete mixture in accordance with Subsection 106-1.02.

The Contractor shall employ a qualified person or company to perform process control testing. A process control plan shall be submitted at the project pre-construction conference in accordance with Subsection 106-1.02. Failure to perform process control forfeits the Contractor's right to retests as provided for in Subsection 401-4.02.

A paving and plant control plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations. The paving and plant control plan shall address joint construction, outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the asphalt concrete mixture. This plan shall also include a proposed testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. The asphalt concrete mixture shall not be placed on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture. No asphalt concrete mixture for a leveling course shall be placed unless the surface temperature is 5 degrees Celsius or warmer.

401-3.02 EQUIPMENT. All equipment shall be in good working order and free of asphalt concrete mixture buildup. All equipment shall be available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

401-3.03 BITUMINOUS MIXING PLANTS. The Contractor shall use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. The Contractor shall calibrate the asphalt mixing plant and furnish copies of the data to the Engineer at least 2 days prior to asphalt concrete mixture production.

The asphalt mixing plant shall have a scalping screen to prevent oversize material or debris from being incorporated into the asphalt concrete mixture. Aggregate and asphalt cement sampling locations meeting OSHA safety requirements shall be provided.

Proportioning (batch) scales shall not be used for weighing material for payment. Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.04 HAULING EQUIPMENT. Trucks used for hauling asphalt mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List. Diesel fuel or fuel oil shall not be used as an asphalt release agent.

Each truck shall have a cover of canvas or other suitable material of such size as to protect the asphalt concrete mixture, when required, so that the mixture shall be delivered to the asphalt paver at the proper temperature.

401-3.05 ASPHALT PAVERS. Asphalt pavers shall be self-propelled units provided with a heated vibratory screed. Grade and cross slope shall be controlled through the use of automatic grade and slope control devices. The paver screed control system shall be automatically actuated by the use of an erected string line, mobile stringline (ski) on the high side of the paver at least 9 meters in length, or other approved grade follower. Grade control shall be used on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation. The hopper shall be equipped with a distribution system to place the asphalt concrete mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture. Screed extensions used for paving a constant width shall be heated and vibrated. Auger extensions shall be within 0.5 meters of the screed extension on both sides.

The use of a Layton Box will be allowed on bikepaths, sidewalks, pathways and medians.

401-3.06 ROLLERS. The Contractor shall supply a sufficient number and weight of rollers to compact the mixture to the required density while maintaining the pace of the paving operations. Rollers shall be static or vibratory steel wheel and pneumatic tire type rollers. The rollers shall be self propelled and capable of reversing without backlash. They shall be specifically designed to compact hot asphalt concrete mixtures. The use of equipment which results in crushing of the aggregate will not be permitted. Pneumatic tire rollers shall be fully skirted, have an operating weight per tire of at least 1,360 kilograms and be operated in accordance with the manufacturer's instructions.

401-3.07 PREPARATION OF EXISTING SURFACE. Existing surfaces shall be prepared in conformance with the plans and specifications. Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

Contact surfaces of curbing, gutters, manholes, sawcut pavement, and other structures shall be coated with a uniform coating of tack coat material conforming to Section 402 prior to the asphalt concrete mixture being placed.

Surfaces which have received a prime coat shall be allowed to cure. Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixture.

401-3.08 PREPARATION OF ASPHALT. A continuous supply of the asphalt cement shall be supplied to the mixer at a uniform temperature, within 14 degrees Celsius of the Job Mix Design mixing temperature.

401-3.09 PREPARATION OF AGGREGATES. The aggregate for the asphalt concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified. The burner on the dryer shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate. Any asphalt concrete mixture in which soot or fuel is present shall be wasted and no payment made.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by ATM T-25.

401-3.10 MIXING. The aggregate, asphalt cement and additives shall be combined in the mixer in the amounts required by the Job Mix Design.

The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained. For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement. Wet mixing time shall be adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

The temperature of the asphalt concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Asphalt concrete mixture drawn from silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Rejected asphalt concrete mixture shall be disposed of by the Contractor at no cost to the State.

401-3.12 SPREADING AND PLACING. The asphalt concrete mixture shall be laid upon a surface approved by the Engineer, spread and struck off and compacted to the required compacted thickness. Asphalt pavers shall be used to distribute the asphalt concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of Subsection 401-3.14. Asphalt pavers shall also be used to distribute asphalt concrete mixture for leveling course unless otherwise allowed.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the asphalt concrete mixture shall be spread, raked and luted by hand tools. For such areas the asphalt concrete mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge dropoff. When the outside pavement edge dropoff exceeds 50 millimeters, approved material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted. Paving shall not begin until all adjacent curb has been poured and cured for 72 hours.

Asphalt concrete pavement to be placed over bridge deck membranes shall not be placed until the membrane has cured according to the manufacturer's specifications. Vehicles, except the paving machine and trucks hauling the asphalt concrete mixture for the overlay, shall not be operated on the membrane. Paving machines used on the membrane shall be rubber-tired or rubber-tracked. The Contractor shall follow the manufacturer's published minimum and maximum temperature limitations for the asphalt concrete mixture. Vibratory rollers, with the vibrator engaged, shall not be used on bridge decks.

401-3.13 COMPACTION. Immediately after the asphalt concrete mixture has been spread, struck-off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.

The target value for density will be 94% of the maximum specific gravity (MSG), as determined in accordance with AASHTO T 209. For the first lot of each type of asphalt concrete pavement, the MSG will be determined by the Job Mix Design. For additional lots, the MSG will be determined by the sample from the first sublot of the lot. Acceptance testing for field density will be determined in accordance with ATM T-18 except that a minimum 150 mm diameter core is required. (Acceptance testing for field density of leveling course or temporary pavement will not be done.)

The asphalt concrete pavement, including leveling course, shall receive a minimum of 3 complete passes with a pneumatic-tired roller. A pass is defined as once over each point on the pavement surface.

Areas not accessible to the rollers shall be graded with rakes and lutes and compacted with mechanical tampers. For depressed areas a trench roller may be used to achieve the required compaction.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Joints shall be constructed to ensure a continuous bond between sections of the course. All joints shall present the same texture and smoothness as other sections of the course.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Improperly formed joints resulting in surface irregularities shall be removed full depth, replaced with new material, and thoroughly compacted. Rolling of joints after the material has cooled below 65 degrees Celsius shall not be allowed. All pavement removal shall be precut to a neat line with a power driven saw.

A tack coat of asphalt cement or asphalt emulsion shall be applied on all cold joints and allowed to break prior to placing any fresh asphalt concrete mixture against the joint. This work shall be completed by the Contractor just prior to paving.

Transverse joints shall be formed by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead. Transverse joints shall not be perpendicular to centerline, but at a skew between 15-25 degrees.

The longitudinal joints in one layer shall offset those in the layer immediately below by at least 150 millimeters. The joints shall be at centerline or lane lines. Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset 50 to not more than 150 millimeters from the edge of the stripe.

401-3.15 SURFACE TOLERANCE. The surface will be tested after final rolling at selected locations using a 3 meter straightedge. The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 5 millimeters.

401-3.16 PATCHING DEFECTIVE AREAS. Any asphalt concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective as determined by the Engineer shall be removed. Skin patching will not be permitted. Defective materials shall be removed for the full thickness of the course. The pavement shall be cut so that the sides are parallel to the direction of traffic and so that the edges are vertical. Edges shall be coated with a tack coat of material conforming to Section 402 and allowed to cure. Fresh asphalt concrete mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements. The asphalt concrete mixture shall be compacted to the density specified. All costs associated with the patching of defective areas shall be borne by the Contractor.

Any asphalt concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective shall be removed and replaced with fresh hot asphalt concrete mixture, which shall be compacted to conform with the surrounding area. Any area showing an excess or deficiency of asphalt cement shall be removed and replaced.

401-4.01 METHOD OF MEASUREMENT. The asphalt concrete mixture will be measured by the megagram or by the square meter in accordance with Section 109. The weight used will be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material and anti-stripping additive in the mixture.

The weight of asphalt cement will be calculated using the percent of asphalt cement for each sublot multiplied by the total megagrams represented by that sublot. Percent of asphalt cement will be determined by ATM T-23. The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

No payment will be made for any asphalt cement in excess of 0.4% above the optimum asphalt content specified in the Job Mix Design.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of each type of asphalt concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance. The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project. Acceptance sampling and testing shall be performed by the Engineer. The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams. The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection. If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot shall include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot. The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density, and gradation in accordance with this subsection. The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing. If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed. If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result. If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with Sub-section 401-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, asphalt concrete pavement will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the asphalt concrete pavement to the specified depth and finished surface requirements and tolerances. Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees Celsius prior to completing compaction, or is in any other way defective, shall be removed and replaced with new asphalt concrete pavement. Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction, or at the end of the auger. Asphalt cement content will be determined by ATM T-23.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device or from the stopped conveyor belt. The aggregate gradation will be determined according to ATM T-7. Sampling devices for obtaining aggregate samples on drum mix plants shall be located on the conveyor system delivering combined aggregates into the drum. The sampling device shall divert aggregate from the full width of the conveyor system and shall be maintained to provide a representative sample of aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to ATM T-7. The size of samples for extraction will be in conformance with AASHTO T 164 and extracted gradations will be determined according to AASHTO T 30.

Within 24 hours of final rolling, the Contractor shall cut full depth samples from the finished mat lift for density acceptance testing. One core sample with a minimum diameter of 6 inches shall be taken from each sublot. The samples shall be neatly cut by a core drill at the randomly selected locations  marked by the Engineer. ATM T-18 will be used to determine density. No samples shall be cut from asphalt concrete mats on bridge decks. Failure to cut core samples for density acceptance testing within the specified period will result in a penalty of $100.00 per sample per day. The accrued amount will be subtracted from the Contractor's payment for asphalt concrete pavement.

All voids left by sampling shall be backfilled with new asphalt concrete mixture and compacted within 24 hours of sampling. Failure to backfill voids left by sampling in the specified period will result in a penalty of $100.00 per hole per day. The accrued amount will be subtracted from the Contractor's payment for asphalt concrete pavement.

The Contractor may request a retest of any sample not within specification limits. This request shall be in writing and delivered to the Engineer within 7 days of receipt of the initial test result. Verbal requests with the written request to be delivered after the specified 7 days will not be accepted. The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s). The Engineer will mark the sample location for the retest. Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s). The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample will be allowed.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 4,500 megagrams, except as defined in Subsection 401-4.02.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis - Standard Deviation (Specification Conformance Analysis) Method using the procedures listed to determine the total estimated percent of the lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results shall not be included in the price adjustment calculations. If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment. The density test results for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s). Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0% and a contractor's risk of 5.0% unless otherwise specified. AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100% pay. The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained. The maximum pay factor obtainable is 1.05. The maximum pay factor for the largest sieve size specification for gradation will be 1.00. The price adjustment is based on the lowest of two pay factors. The first factor is a composite pay factor for asphalt concrete mixture which includes gradation and asphalt cement content. The second factor is a separate pay factor for density.

A lot containing material with less than a 1.00 pay factor, may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.

A lot containing material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11. The Contractor may submit a written request for acceptance of the material at a reduced price or approved correction. Such a request shall include an engineering analysis showing expected effects on performance. The Engineer will determine whether or not the material may remain in place at the reduced price.

The Engineer can reject material which appears to be defective based on visual inspection. Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis. Procedures for computation of composite pay factor are as follows:

1.	Eliminate test results found to be outliers by SP-7 (the Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ	= summation of

x=Σxn

x	= individual test value to xn

n	= total number of test values

x	is rounded to the nearest tenth for density and all sieve sizes except the 75 μm sieve. x is rounded to the nearest hundredth for asphalt cement content and the 75 μm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)	=	summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2	=	square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the 75 μm sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the 75 μm sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieve sizes except the 75 μm sieve. Use s = 0.020 for asphalt cement content and the 75 μm sieve.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL). For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2. The TV is the specification value defined by the Job Mix Design. The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

4.	Compute the Upper Quality Index (QU):

Where:	USL	= Upper Specification Limit

QU=USL-xs

QU	is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

QL=x-LSLs

Where:	LSL	= Lower Specification Limit

QL	is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 401-3.

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 401-3.

8.	Determine the Quality Level (the total percent within specification limits) for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, determine the lot Density Pay Factor (DPF) and gradation and asphalt cement content pay factors (PF) from Table 401-4.

10.	Compute the asphalt concrete mixture Composite Pay Factor (CPF) for asphalt content and gradation using the following formula:

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 401-5 is used to determine the weight factor (f) for each sieve size, and asphalt cement content.

Table 401-2

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

Measured Characteristics		LSL			USL

19.0 mm				TV-6.0		TV+6.0

12.5 mm				TV-6.0		TV+6.0

9.5 mm				TV-6.0		TV+6.0

4.75 mm				TV-6.0		TV+6.0

2.36 mm				TV-6.0		TV+6.0

1.18 mm				TV-5.0		TV+5.0

600 μm				TV-4.0		TV+4.0

300 μm				TV-4.0		TV+4.0

150 μm				TV-3.0		TV+3.0

75 μm					TV-2.0		TV+2.0

Asphalt %				TV-0.40		TV+0.40

Density				 92%			 98%

TABLE 401-3

Upper Quality Index (QU) or Lower Quality Index (QL)

| PU or PL | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 100 | 1.16-10.0 | 1.48-10.0 | 1.68-10.0 | 1.81-10.0 | 1.90-10.0 | 1.96-10.0 | 2.01-10.0 | 2.05-10.0 | 2.10-10.0 | 2.15-10.0 |
| 99 | - | 1.45-1.47 | 1.61-1.67 | 1.71-1.80 | 1.77-1.89 | 1.82-1.95 | 1.85-2.00 | 1.87-2.04 | 1.92-2.09 | 1.94-2.14 |
| 98 | 1.15 | 1.42-1.44 | 1.55-1.60 | 1.63-1.70 | 1.68-1.76 | 1.71-1.81 | 1.73-1.84 | 1.75-1.86 | 1.78-1.91 | 1.80-1.93 |
| 97 | - | 1.39-1.41 | 1.50-1.54 | 1.56-1.62 | 1.60-1.67 | 1.62-1.70 | 1.64-1.72 | 1.66-1.74 | 1.68-1.77 | 1.69-1.79 |
| 96 | 1.14 | 1.36-1.38 | 1.45-1.49 | 1.50-1.55 | 1.53-1.59 | 1.55-1.61 | 1.56-1.63 | 1.57-1.65 | 1.59-1.67 | 1.60-1.68 |
| 95 | - | 1.33-1.35 | 1.40-1.44 | 1.44-1.49 | 1.47-1.52 | 1.48-1.54 | 1.49-1.55 | 1.50-1.56 | 1.51-1.58 | 1.52-1.59 |
| 94 | 1.13 | 1.30-1.32 | 1.36-1.39 | 1.39-1.43 | 1.41-1.46 | 1.42-1.47 | 1.43-1.48 | 1.44-1.49 | 1.45-1.50 | 1.45-1.51 |
| 93 | - | 1.27-1.29 | 1.32-1.35 | 1.34-1.38 | 1.36-1.40 | 1.37-1.41 | 1.37-1.42 | 1.38-1.43 | 1.38-1.44 | 1.39-1.44 |
| 92 | 1.12 | 1.24-1.26 | 1.28-1.31 | 1.30-1.33 | 1.31-1.35 | 1.31-1.36 | 1.32-1.36 | 1.32-1.37 | 1.33-1.37 | 1.33-1.38 |
| 91 | 1.11 | 1.21-1.23 | 1.24-1.27 | 1.25-1.29 | 1.26-1.30 | 1.26-1.30 | 1.27-1.31 | 1.27-1.31 | 1.27-1.32 | 1.28-1.32 |
| 90 | 1.10 | 1.18-1.20 | 1.20-1.23 | 1.21-1.24 | 1.21-1.25 | 1.22-1.25 | 1.22-1.26 | 1.22-1.26 | 1.22-1.26 | 1.23-1.27 |
| 89 | 1.08-1.09 | 1.15-1.17 | 1.16-1.19 | 1.17-1.20 | 1.17-1.20 | 1.17-1.21 | 1.17-1.21 | 1.18-1.21 | 1.18-1.21 | 1.18-1.22 |
| 88 | 1.07 | 1.12-1.14 | 1.13-1.15 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.17 | 1.13-1.17 | 1.13-1.17 |
| 87 | 1.05-1.06 | 1.09-1.11 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.04 | 1.06-1.08 | 1.06-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.02-1.03 | 1.03-1.05 | 1.02-1.05 | 1.02-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 |
| 84 | 1.01 | 1.00-1.02 | 0.99-1.01 | 0.98-1.01 | 0.98-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 |
| 83 | 0.98-1.00 | 0.97-0.99 | 0.96-0.98 | 0.95-0.97 | 0.94-0.97 | 0.94-0.96 | 0.94-0.96 | 0.93-0.96 | 0.93-0.96 | 0.93-0.96 |
| 82 | 0.97 | 0.94-0.96 | 0.92-0.95 | 0.91-0.94 | 0.91-0.93 | 0.90-0.93 | 0.90-0.93 | 0.90-0.92 | 0.90-0.92 | 0.89-0.92 |
| 81 | 0.94-0.96 | 0.91-0.93 | 0.89-0.91 | 0.88-0.90 | 0.87-0.90 | 0.87-0.89 | 0.87-0.89 | 0.86-0.89 | 0.86-0.89 | 0.86-0.88 |
| 80 | 0.92-0.93 | 0.88-0.90 | 0.86-0.88 | 0.85-0.87 | 0.84-0.86 | 0.83-0.86 | 0.83-0.86 | 0.83-0.85 | 0.83-0.85 | 0.82-0.85 |
| 79 | 0.90-0.91 | 0.85-0.87 | 0.83-0.85 | 0.81-0.84 | 0.81-0.83 | 0.80-0.82 | 0.80-0.82 | 0.80-0.82 | 0.79-0.82 | 0.79-0.81 |
| 78 | 0.88-0.89 | 0.82-0.84 | 0.79-0.82 | 0.78-0.80 | 0.77-0.80 | 0.77-0.79 | 0.77-0.79 | 0.76-0.79 | 0.76-0.78 | 0.76-0.78 |
| 77 | 0.85-0.87 | 0.79-0.81 | 0.76-0.78 | 0.75-0.77 | 0.74-0.76 | 0.74-0.76 | 0.73-0.76 | 0.73-0.75 | 0.73-0.75 | 0.72-0.75 |
| 76 | 0.83-0.84 | 0.76-0.78 | 0.73-0.75 | 0.72-0.74 | 0.71-0.73 | 0.71-0.73 | 0.70-0.72 | 0.70-0.72 | 0.70-0.72 | 0.69-0.71 |
| 75 | 0.80-0.82 | 0.73-0.75 | 0.70-0.72 | 0.69-0.71 | 0.68-0.70 | 0.67-0.70 | 0.67-0.69 | 0.67-0.69 | 0.67-0.69 | 0.66-0.68 |
| 74 | 0.77-0.79 | 0.70-0.72 | 0.67-0.69 | 0.66-0.68 | 0.65-0.67 | 0.64-0.66 | 0.64-0.66 | 0.64-0.66 | 0.63-0.66 | 0.63-0.65 |
| 73 | 0.75-0.76 | 0.67-0.69 | 0.64-0.66 | 0.63-0.65 | 0.62-0.64 | 0.61-0.63 | 0.61-0.63 | 0.61-0.63 | 0.60-0.62 | 0.60-0.62 |
| 72 | 0.72-0.74 | 0.64-0.66 | 0.61-0.63 | 0.60-0.62 | 0.59-0.61 | 0.58-0.60 | 0.58-0.60 | 0.58-0.60 | 0.58-0.59 | 0.57-0.59 |
| 71 | 0.69-0.71 | 0.61-0.63 | 0.58-0.60 | 0.57-0.59 | 0.56-0.58 | 0.56-0.57 | 0.55-0.57 | 0.55-0.57 | 0.55-0.57 | 0.54-0.56 |
| 70 | 0.66-0.68 | 0.58-0.60 | 0.55-0.57 | 0.54-0.56 | 0.53-0.55 | 0.53-0.55 | 0.52-0.54 | 0.52-0.54 | 0.52-0.54 | 0.51-0.53 |
| 69 | 0.63-0.65 | 0.55-0.57 | 0.52-0.54 | 0.51-0.53 | 0.50-0.52 | 0.50-0.52 | 0.49-0.51 | 0.49-0.51 | 0.49-0.51 | 0.49-0.50 |
| 68 | 0.60-0.62 | 0.52-0.54 | 0.48-0.51 | 0.48-0.50 | 0.47-0.49 | 0.47-0.49 | 0.47-0.48 | 0.46-0.48 | 0.46-0.48 | 0.46-0.48 |
| 67 | 0.57-0.59 | 0.49-0.51 | 0.46-0.47 | 0.45-0.47 | 0.45-0.46 | 0.44-0.46 | 0.44-0.46 | 0.44-0.45 | 0.43-0.45 | 0.43-0.45 |
| 66 | 0.53-0.56 | 0.46-0.48 | 0.44-0.45 | 0.42-0.44 | 0.42-0.44 | 0.41-0.43 | 0.41-0.43 | 0.41-0.43 | 0.41-0.42 | 0.40-0.42 |
| 65 | 0.50-0.52 | 0.43-0.45 | 0.41-0.43 | 0.40-0.41 | 0.39-0.41 | 0.39-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.39 |
| 64 | 0.47-0.49 | 0.40-0.42 | 0.38-0.40 | 0.37-0.39 | 0.36-0.38 | 0.36-0.38 | 0.36-0.37 | 0.35-0.37 | 0.35-0.37 | 0.35-0.37 |
| 63 | 0.44-0.46 | 0.37-0.39 | 0.35-0.37 | 0.34-0.36 | 0.33-0.35 | 0.33-0.35 | 0.33-0.35 | 0.33-0.34 | 0.32-0.34 | 0.32-0.34 |
| 62 | 0.40-0.43 | 0.34-0.36 | 0.32-0.34 | 0.31-0.33 | 0.31-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.31 | 0.30-0.31 |
| 61 | 0.37-0.39 | 0.31-0.33 | 0.29-0.31 | 0.28-0.30 | 0.28-0.30 | 0.28-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 |
| 60 | 0.33-0.36 | 0.28-0.30 | 0.26-0.28 | 0.26-0.27 | 0.25-0.27 | 0.25-0.27 | 0.25-0.26 | 0.25-0.26 | 0.24-0.26 | 0.24-0.26 |
| 59 | 0.30-0.32 | 0.25-0.27 | 0.24-0.25 | 0.23-0.25 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.23 | 0.22-0.23 |
| 58 | 0.26-0.29 | 0.22-0.24 | 0.21-0.23 | 0.20-0.22 | 0.20-0.21 | 0.20-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 |
| 57 | 0.23-0.25 | 0.19-0.21 | 0.18-0.20 | 0.17-0.19 | 0.17-0.19 | 0.17-0.19 | 0.17-0.18 | 0.17-0.18 | 0.17-0.18 | 0.16-0.18 |
| 56 | 0.19-0.22 | 0.16-0.18 | 0.15-0.17 | 0.15-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.15 |
| 55 | 0.15-0.18 | 0.13-0.15 | 0.12-0.14 | 0.12-0.14 | 0.12-0.13 | 0.12-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 |
| 54 | 0.12-0.14 | 0.10-0.12 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 |
| 53 | 0.08-0.11 | 0.07-0.09 | 0.07-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.05-0.07 | 0.04-0.06 | 0.04-0.06 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.04 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

NOTE: For negative values of QU or QL, use absolute values of QU or QL. PU or PL is then equal to 100 minus the table value of PU or PL.

TABLE 401-4

Required Quality Level (QL) for a given sample size (n) and a given Pay Factor (PF)

| Pay Factor | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.05 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 1.04 | 90-99 | 91-99 | 92-99 | 93-99 | 93-99 | 93-99 | 94-99 | 94-99 | 95-99 | 95-99 |
| 1.03 | 80-89 | 85-90 | 87-91 | 88-92 | 89-92 | 90-92 | 91-93 | 91-93 | 92-94 | 93-94 |
| 1.02 | 75-79 | 80-84 | 83-86 | 85-87 | 86-88 | 87-89 | 88-90 | 88-90 | 89-91 | 90-92 |
| 1.01 | 71-74 | 77-79 | 80-82 | 82-84 | 84-85 | 85-86 | 85-87 | 86-87 | 87-88 | 88-89 |
| 1.00 | 68-70 | 74-76 | 78-79 | 80-81 | 81-83 | 82-84 | 83-84 | 84-85 | 85-86 | 86-87 |
| 0.99 | 66-67 | 72-73 | 75-77 | 77-79 | 79-80 | 80-81 | 81-82 | 82-83 | 83-84 | 85 |
| 0.98 | 64-65 | 70-71 | 73-74 | 75-76 | 77-78 | 78-79 | 79-80 | 80-81 | 81-82 | 83-84 |
| 0.97 | 62-63 | 68-69 | 71-72 | 74 | 75-76 | 77 | 78 | 78-79 | 80 | 81-82 |
| 0.96 | 60-61 | 66-67 | 69-70 | 72-73 | 73-74 | 75-76 | 76-77 | 77 | 78-79 | 80 |
| 0.95 | 59 | 64-65 | 68 | 70-71 | 72 | 73-74 | 74-75 | 75-76 | 77 | 78-79 |
| 0.94 | 57-58 | 63 | 66-67 | 68-69 | 70-71 | 72 | 73 | 74 | 75-76 | 77 |
| 0.93 | 56 | 61-62 | 65 | 67 | 69 | 70-71 | 71-72 | 72-73 | 74 | 75-76 |
| 0.92 | 55 | 60 | 63-64 | 65-66 | 67-68 | 69 | 70 | 71 | 72-73 | 74 |
| 0.91 | 53-54 | 58-59 | 62 | 64 | 66 | 67-68 | 68-69 | 69-70 | 71 | 73 |
| 0.90 | 52 | 57 | 60-61 | 63 | 64-65 | 66 | 67 | 68 | 70 | 71-72 |
| 0.89 | 51 | 55-56 | 59 | 61-62 | 63 | 64-65 | 66 | 67 | 68-69 | 70 |
| 0.88 | 50 | 54 | 57-58 | 60 | 62 | 63 | 64-65 | 65-66 | 67 | 69 |
| 0.87 | 48-49 | 53 | 56 | 58-59 | 60-61 | 62 | 63 | 64 | 66 | 67-68 |
| 0.86 | 47 | 51-52 | 55 | 57 | 59 | 60-61 | 62 | 63 | 64-65 | 66 |
| 0.85 | 46 | 50 | 53-54 | 56 | 58 | 59 | 60-61 | 61-62 | 63 | 65 |
| 0.84 | 45 | 49 | 52 | 55 | 56-57 | 58 | 59 | 60 | 62 | 64 |
| 0.83 | 44 | 48 | 51 | 53-54 | 55 | 57 | 58 | 59 | 61 | 63 |
| 0.82 | 42-43 | 46-47 | 50 | 52 | 54 | 55-56 | 57 | 58 | 60 | 61-62 |
| 0.81 | 41 | 45 | 48-49 | 51 | 53 | 54 | 56 | 57 | 58-59 | 60 |
| 0.80 | 40 | 44 | 47 | 50 | 52 | 53 | 54-55 | 55-56 | 57 | 59 |
| 0.79 | 38-39 | 43 | 46 | 48-49 | 50-51 | 52 | 53 | 54 | 56 | 58 |
| 0.78 | 37 | 41-42 | 45 | 47 | 49 | 51 | 52 | 53 | 55 | 57 |
| 0.77 | 36 | 40 | 43-44 | 46 | 48 | 50 | 51 | 52 | 54 | 56 |
| 0.76 | 34-35 | 39 | 42 | 45 | 47 | 48-49 | 50 | 51 | 53 | 55 |
| 0.75 | 33 | 38 | 41 | 44 | 46 | 47 | 49 | 50 | 51-52 | 53-54 |
| 0 | 0-32 | 0-37 | 0-40 | 0-43 | 0-45 | 0-46 | 0-48 | 0-49 | 0-50 | 0-52 |

Table 401-5

WEIGHT FACTORS

Gradation				Factor "f"

19.0 mm sieve				4

12.5 mm sieve				4

9.5 mm sieve					4

4.75 mm sieve				4

2.36 mm sieve				4

1.18 mm sieve				5

600 μm sieve					5

300 μm sieve					5

150 μm sieve					5

75 μm sieve					20

Asphalt %					40

401-5.01 BASIS OF PAYMENT. The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Tack coat, anti-stripping additive, and asphalt cement shall be subsidiary to Asphalt Concrete Pavement, Type II, Class A.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot and added to the Contractor's payment for Asphalt Concrete. The fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 401-2.01 will be subtracted from the Contractor's payment. The price adjustment will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value. The price adjustment for each individual lot shall be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $60 / Megagram

* Composite Pay Factor (CPF) or Density Pay Factor (DPF) whichever is lower value.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(5)	Asphalt Price Adjustment	Contingent Sum

401(9A)	Asphalt Concrete Pavement, Type_II, Class A ___	Megagram

Separate payment will not be made for asphalt cement, or anti-strip additives for Item 401(9A), Asphalt Concrete Pavement, Type II, Class A.

R199M

SECTION 402

TACK COAT

Special Provisions

402-2.01 ASPHALT MATERIAL. Delete "CSS-1" and substitute "STE-1".

402-3.04 DILUTION OF ASPHALT MATERIAL. Delete this subsection in its entirety.

402-3.05 APPLICATION OF ASPHALT MATERIAL. Delete the first paragraph and substitute the following: The tack coat shall be uniformly applied with a pressure distributor at a rate of 100 to 450 mL per square meter, as directed.

402-4.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: The asphalt material for tack coat will be measured by the megagram in accordance with Section 109.

402-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

402(3)	STE-1 Asphalt for Tack Coat	Megagram

(6/14/95)R33M

Add the following Section:

SECTION 407

STONE MASTIC ASPHALT CONCRETE PAVEMENT

Special Provisions

407-1.01 DESCRIPTION. This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

407-2.01 COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN. Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

The Contractor shall provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

At least 15 calendar days prior to the production of Stone Mastic Asphalt Concrete mixture, the Contractor shall submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile. The proposed gradation must meet the requirements of Table 703-8, Stone Mastic Asphalt Concrete Aggregate. Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended. Sample sizes: 45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand and/or mineral filler.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature/viscosity curve for the asphalt cement.

4.	A 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 2.5 kilogram sample of the stabilizing additive (cellulose or polyolefin) proposed for use in the mixture, including name of product, manufacture, test results as required in Section 407-2.05 and manufactures certificate of compliance with Section 407-2.05.

From this information, the Engineer will establish the Job Mix Design which will become a part of the contract and shall be followed unless modified in writing. The Job Mix Design will be determined in accordance with ATM T-7 (version 01/93) and evaluated for conformance with the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1. Job Mix Design test results will be available within 10 working days after submittal of the materials. Approved Job Mix Designs will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.

Changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio shall be submitted by the Contractor in the same manner as the original submittal. A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after Contractor submittal of the new proposed aggregate gradation and blend ratio.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $1,500.00 each.

TABLE 407-1

STONE MASTIC ASPHALT CONCRETE

MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement |
| --- | --- |
| Stability, newton, min. | 4450 |
| Flow, 0.25 mm | 8-16 |
| Voids in total mix, percent | 2-4 |
| Compaction, number of blows each side of test specimen | 50 |
| Dust-asphalt ratio (the percent of material passing the No. 0.075 mm sieve divided by the percent of asphalt, by weight of mix) | 0.6-1.4 |
| Voids in the mineral aggregate (VMA), min. | 15.0 |

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in table 703-8. Tolerances for the largest sieve specified will be plus 0% and minus 1%.

407-2.02 AGGREGATES. Aggregates shall be of the type specified in the contract and shall conform to the requirements of Table 703-8 in Subsection 703-2.12.

407-2.03 ASPHALT MATERIALS. The grade of asphalt cement will be specified in the contract. The asphalt cement shall conform to the applicable requirements of Section 702. Asphalt cement may be conditionally accepted at the source if the Contractor provides a manufacture's certificate of compliance in accordance with Subsection 106-1.05, and test results of the applicable quality requirements of Section 702 before the material is shipped.

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted for approval.

407-2.04 ANTI-STRIP ADDITIVES. Anti-strip agents shall be used in the proportions determined by ATM T-14 and shall be included in the approved Job Mix Design. At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05 STABILIZING ADDITIVES. Cellulose or polyolefin stabilizing additive shall be used. The dosage rate for the cellulose is 0.3 percent by weight of the total mix. The dosage rate for the polyolefin is 0.4 percent by weight of the total mix. The allowable tolerance per ton shall not exceed ± 10 percent of the required weight of the stabilizing additive.

The cellulose stabilizing additive shall conform to the properties shown in Table 407-2; the polyolefin stabilizing additive shall conform to the properties shown in Table 407-3.

TABLE 407-2

CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis(1): Fiber Length Percent passing 0.150 mm sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing 0.850 mm sieve Percent passing 0.425 mm sieve Percent passing 0.106 mm sieve | 6.4 mm (max) 60-80 0.9-1.5 mm (avg) 75-95 55-75 10-30 |
| Ash Content(3) | 20% non-volatiles (max) |
| pH(4) | 7.5 +/-1.0 |
| Oil Absorption(5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content(6) | < 5% |
| Bulk Density(7) | 20.0-40.0 kg/m3 |

Notes:

(1)	Method A - Alpine Sieve Analysis. This test is performed using an Alpine Air Jet Sieve (Type 200 LS). A representative five gram sample of fiber is sieved for 14 minutes at a controlled vacuum of 0.56 meters (+/- 75 mm) of water. The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis. This test is performed using 0.850, 0.425, 0.250, 0.180, 0.150 and 0.106 mm sieves, nylon brushes and a shaker. A representative 10 gram sample of fiber is sieved, using a shaker and two nylon brushes on each screen. The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content. A representative 2-3 gram sample of fiber is placed in a tared crucible and heated between 593 and 649 C for not less than two hours. The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test. Five grams of fiber is added to 100 ml of distilled water, stirred and let sit for 30 minutes. The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test. Five grams of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation. It is then placed in a screen mesh strainer (approximately 0.5 square millimeter hole size) and shaken on a wrist action shaker for ten minutes (approximately 31.75 mm motion at 240 shakes/minute). The shaken mass is then transferred without touching, to a tared container and weighed. Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content. Ten grams of fiber is weighed and placed in a 121 C forced air oven for two hours. The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density. Fluff fiber with air or Hobart Mixer, weigh out 25 grams of fiber, place in 100 ml cylinder, tap cylinder and measure volume.

TABLE 407-3

POLYOLEFIN STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Chemical Property | Ethylene, Propylene, Butane 1, Terpolymer, double bond free with no other functional group. |
| Specific Gravity | 0.86 |
| Size | Approx. 3 mm dia. by 3 mm length |
| Softening Point | 93 C |

407-2.06 PROCESS QUALITY CONTROL. It is expressly understood that the contractor is solely responsible for the sampling and testing of material for process control of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.02.

Failure to perform process control forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

CONSTRUCTION REQUIREMENTS

407-3.01 WEATHER LIMITATIONS. Stone Mastic Asphalt Concrete mixture shall not be placed when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture. No Stone Mastic Asphalt Concrete mixture shall be placed unless the surface temperature is 10 degrees C or warmer. Stone Mastic Asphalt Concrete mixture will not be placed after September 10 of any year.

407-3.02 EQUIPMENT. All equipment shall be in good working order and free of asphalt concrete mix buildup. All equipment shall be available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

407-3.03 BITUMINOUS MIXING PLANTS. The Contractor shall use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. The Contractor shall calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.

The asphalt plant shall have a scalping screen to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture. Aggregate and asphalt cement sampling locations meeting OSHA safety requirements shall be provided.

Proportioning (batch) scales shall not be used for weighing material for payment. Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified. The asphalt plant shall maintain a current Air Quality Permit issued by the State Of Alaska.

407-3.04 HAULING EQUIPMENT. Trucks used for hauling asphalt mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List. Diesel fuel or fuel oil shall not be used as an asphalt release agent.

Each truck shall have a watertight canvas cover of such size as to extend at least one foot over the sides and end of the truck bed and be adequately secured to protect the Stone Mastic Asphalt Concrete mixture. The use of the canvas cover shall be at the Engineer's direction.

407-3.05 ASPHALT PAVERS. Asphalt pavers shall be self-propelled units provided with a heated vibratory screed. Grade and cross slope shall be controlled through the use of automatic grade and slope control devices. The paver screed control system shall be automatically actuated by the use of an erected string line or a mobile string-line (ski) at least 9 meters in length on the high side of the paver. Grade control shall be used on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation. The hopper shall be equipped with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture. Screed extensions used for paving a constant width shall be heated and vibrated. Auger extensions shall be within 0.45 meters of the screed extension on both sides.

The use of a pickup machine to transfer the Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collection of the windrowed material without damage to the underlying course. The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06 ROLLERS. The Contractor shall supply a minimum of three rollers weighing a minimum of 11 megagrams each to compact the mixture to the required density while maintaining the pace of the paving operations. Rollers shall be of the static steel wheel or vibratory steel wheel type. The roller drums shall be a minimum of 2.1 meters wide. The rollers shall be self- propelled and capable of reversing without backlash. They shall be specifically designed to compact hot asphalt concrete mixtures. The use of equipment which results in crushing of the aggregate, or pick up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

407-3.07 PREPARATION OF EXISTING SURFACE. Existing surfaces shall be prepared in conformance with the plans and specifications. Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After planing of a section of the roadway has been completed, that section shall be inspected by the Contractor and the Engineer for areas of distress or failure.  The Contractor and the Engineer shall coordinate to select among the following repair methods for each distinct area requiring repair:

- Ruts or depressions deeper than 12 mm shall be leveled to proper grade with Asphalt Concrete Pavement Type III, Class B.  The mix shall meet the requirements of the asphalt sidewalk portion of Section 608.  AC leveling courses shall be placed with a self-powered paver, Layton Box, or other approved method.  Compaction shall be completed using methods approved by the Engineer to the satisfaction of the Engineer.  Ruts or depressions less than 12 mm deep will be filled in the Stone Mastic Asphalt overlay operation.

- In planing breakthrough areas, the remaining pavement shall be removed and the distressed area shall be excavated to the depth and limits directed by the Engineer. The excavated area shall be patched to match the planed surface, layer for layer, with selected material Type A, crushed aggregate base course, and Asphalt Concrete Type II , Class A or Asphalt Concrete Type III, Class B, as directed by the Engineer.  Where Asphalt Concrete Pavement, Type II, Class A is used, it shall conform with the requirements of Section 401, however, no Asphalt Price Adjustment will be applied for this use.

- In areas where the pavement is peeling or layers are separating, existing pavement shall be removed to the separation surface by planing or other means approved by the Engineer.  Once the separated material is removed, an AC leveling course shall be placed to match the surrounding planed surface if the new surface is deeper than 12 mm below the surrounding planed surface.  If the new surface is 12 mm or less than below the surrounding planed surface, the area will be filled by the Stone Mastic Asphalt pavement overlay.

Pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures shall receive a uniform coating of tack coat material in conformance with Section 402 prior to Stone Mastic Asphalt Concrete mixture being placed.

407-3.08 PREPARATION OF ASPHALT. A continuous supply of the asphalt cement shall be supplied to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09 PREPARATION OF AGGREGATES. The aggregate for the Stone Mastic Asphalt Concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified. The burner on the dryer shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate. Any Stone Mastic Asphalt Concrete mixture in which soot or fuel is present shall be wasted and no payment made.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by AASHTO T 110. Adequate dry storage shall be provided for the mineral filler and the stabilizing additive.

407-3.10 MIXING. The aggregate, asphalt cement, additives, and stabilizing additives shall be combined uniformly in the amounts required by the Job Mix Design. The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants. Stabilizing additive shall be added through a separate inlet directly into the weigh hopper above the pugmill. The addition of the stabilizing additive shall be timed to occur during the hot aggregate charging of the hopper. Adequate dry mixing time is required to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants. Cellulose stabilizing additive shall be introduced into the drum mixer at the same point the asphalt cement is added. The polyolefin stabilizing additive shall be added directly into the drum mixer through the RAP inlet. Polyolefin stabilizing additive shall not be used in a drum mix plant without a RAP inlet. Operation of the drum mixer will be such to ensure complete blending of the stabilizing additive into the mix.

The dry mixing and wet mixing times for Stone Mastic Asphalt Concrete with cellulose stabilizing additive shall be a minimum of 15 seconds and 40 seconds, respectively. The dry mixing and wet mixing times for Stone Mastic Asphalt Concrete with polyolefin shall be a minimum of 4 seconds and 30 seconds, respectively. For batch plants, dry aggregate shall be placed in motion immediately prior to the addition of asphalt cement. Wet mixing time shall be adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

The temperature of the Stone Mastic Asphalt Concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

Provisions shall be made for proportioning the mineral filler into the mixture uniformly and in the desired quantities. Special attention shall be directed to providing appropriate equipment for accurately proportioning the relative large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding of Stone Mastic Asphalt Concrete mixture in silo type storage bins will be permitted.

All of the Stone Mastic Asphalt Concrete mixture drawn from the silo type storage bins shall conform to all of the requirements for Stone Mastic Asphalt Concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Rejected Stone Mastic Asphalt Concrete mixture shall be disposed of by the Contractor at no cost to the State.

407-3.12 SPREADING AND PLACING. The Contractor shall submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations. The plan shall consist of but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate. Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, weight, and operating speed of rollers.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

The Stone Mastic Asphalt Concrete mixture shall be laid upon a surface approved by the Engineer, spread and struck off and compacted to the required compacted thickness. It shall be spread and compacted in one layer if the total thickness is 75 mm or less. Asphalt pavers shall be used to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the Stone Mastic Asphalt Concrete mixture shall be spread, raked and luted by hand tools. For such areas the Stone Mastic Asphalt Concrete mixture shall be placed to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture which is contaminated or segregated will be rejected.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge drop-off. When the pavement edge drop-off exceeds 50 mm, shoulder material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that section, as defined by the Paving Plan, has been placed and accepted. Paving shall not begin until all adjacent curb has been poured and cured for 72 hours or until satisfactory strength is achieved.

407-3.13 COMPACTION. Immediately after the Stone Mastic Asphalt Concrete mixture has been spread, struck-off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.

Due to the nature of Stone Mastic Asphalt Concrete mixtures, the surface shall be rolled immediately. Rolling shall be accomplished with a minimum of three steel wheel rollers of a minimum weight of 11 megagrams each. Rolling procedures should be adjusted to provide the specified pavement density. Rollers shall move at a uniform speed not to exceed 5 kilometers/hour with the drive roller nearest the paver. Rolling shall be continued until all roller marks are eliminated and the minimum density has been obtained.

To prevent adhesion of the mixture to the rollers, it shall be necessary to keep the wheels properly moistened with water mixed with detergent or other approved material. Rollers showing evidence of excessive pick-up will be replaced.

Once sufficient in-place density has been achieved, rolling operations shall cease. If migration of asphalt cement and filler to the compacted pavement surface has occurred, the Contractor shall remove the defective area and replace it with fresh Stone Mastic Asphalt Concrete mixture, at his expense.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with AASHTO T 209. For the first lot of Stone Mastic Asphalt Concrete, the MSG will be determined by the Job Mix Design. For additional lots, the MSG will be determined by the sample from the first sublot of the lot. Acceptance testing for field density will be determined in accordance with ATM T-18 except that a minimum 150 mm diameter core is required. (Acceptance testing for field density of leveling course will not be done.)

Areas not accessible to the rollers shall be graded with rakes and lutes and compacted with mechanical tampers. For depressed areas a trench roller may be used to achieve the required compaction.

Any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture, which shall be compacted to conform with the surrounding area. Any area showing an excess or deficiency of asphalt cement shall be removed and replaced.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14 JOINTS. Joints shall be constructed to ensure a continuous bond between old and new sections of the course. All joints shall present the same texture and smoothness as other sections of the course.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Improperly formed joints resulting in surface irregularities shall be removed full depth, replaced with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compacted. Rolling of joints after the material has cooled below 65 degrees Celsius shall not be allowed. All pavement removal shall be precut to a neat line with a power driven saw.

A tack coat of asphalt cement or asphalt emulsion shall be applied on all cold joints and allowed to break prior to placing any fresh Stone Mastic Asphalt Concrete mixture against the joint. This work shall be completed by the Contractor just prior to paving.

Transverse joints shall be formed by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead. Transverse joints shall not be perpendicular to centerline, but at a skew between 15-25 degrees.

The longitudinal joints in one layer shall offset those in the layer immediately below by at least 150 mm. The joints shall be at lane lines. Where pre-formed marking tape striping is required, the longitudinal joint in the top layer shall be offset not more than 150 mm from the edge of the stripe.

407-3.15 SURFACE TOLERANCE. The surface will be tested after final rolling at selected locations using a 3 meter straightedge. The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 5 mm. The Stone Mastic Asphalt Concrete mixture in all defective areas shall be removed and replaced. All costs associated with removal and replacement of Stone Mastic Asphalt Concrete mixture in the defective areas shall be borne by the Contractor.

407-3.16 PATCHING DEFECTIVE AREAS. Any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material or is in any way defective as determined by the Engineer shall be removed. Skin patching will not be permitted. Defective materials shall be removed for the full thickness of the course. The pavement shall be cut so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees. Edges shall be coated with a thin tack coat of material conforming to Section 402. Fresh Stone Mastic Asphalt Concrete mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements. The Stone Mastic Asphalt Concrete mixture shall be compacted to the density specified. No payment shall be made for material replacing defective material. All costs associated with the patching of defective areas shall be borne by the Contractor.

407-3.17 TEST SECTION. A minimum 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving, the Contractor shall place a minimum of 270 megagrams of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer. The test section will be used to adjust the Job Mix Design asphalt cement content and to also familiarize the Contractor's personnel with the laydown and compaction of Stone Mastic Asphalt Concrete mixture.

Stone Mastic Asphalt Concrete mixture placed in the test strip that meets specifications will be measured and paid for at contract prices. No payment will be made for mixture that does not meet specifications. If the test strip is placed within the project limits and does not meet specifications, it shall be removed at the Contractor's expense.

407-3.18 STUDDED TIRE TEST SITE.  The site will be prepared according to all other requirements of the total project (such as roto-milling and overlay thickness).  The test site will begin at Station 5+660 and continue until Station 5+745 (85 m).  The width will be from curb to curb for the northbound three lanes (approximately 11m).  The intent of the site is to test the performance of an aggregate more resistant to studded tire wear than common locally-supplied aggregate.

All of the aggregate used to construct the Stone Mastic test site shall be wear-resistant aggregate, except for the mineral filler.  The Stone Mastic Asphalt for this test site shall be processed from material acquired, by the Contractor, for State of Alaska designated Material Site 522-058-2, owned by AHTNA Corporation.  A site sketch is shown on the following page.

The Department has paid the royalty on the aggregate.  The site is located 10.9 km north of the intersection of the Parks and Denali Highways at approximate Historical Milepost 217, on the Parks Highway.  This Materials Site was developed in the early 1960's and the required material is on the surface. The Department will remove the alders on the access road (approximately 100 m) to the proposed work area.  The maximum grade on the access road is approximately twenty percent (20%).  The larger aggregate size is generally 0.6 m.  Photos are available for review at Department of

insert sketch of Ahatna

Transportation and Public Facilities Building Plans Room at 4111 Aviation Avenue, however, a visit to the site is highly recommended prior to bidding.

The Contractor shall contact Jack Phipps, (phone: 907-451-5283), and the Chief Geologist (phone: 907-269-6236), fourteen (14) calendar days in advance to schedule the department-supplied loader and operator to load the Contractor’s trucks.  The Chief Geologist will direct the loader operator to portion of the site to be mined (the east side of the site).  The Contractor shall schedule a sufficient quantity of trucks to load and legally transport an approximate quantity of 200 Megagrams of material to the Contractor’s crushing plant.

At all times, the Contractor shall store the wear-resistant aggregate in separate stockpiles from other aggregates.  After the crushing operation, the Contractor shall schedule the Department’s sample collection of one (1) megagram of the crushed material.

The wear-resistant Stone Mastic Asphalt Concrete for this item shall conform to all requirements of Section 407.  The Contractor shall notify the Engineer of Tests (907-269-6242) or the Chief Geologist one week before paving the test section.

The Contractor shall schedule paving operations so that this test section is paved within ten (10) calendar days of the paving on adjacent sections.

407-4.01 METHOD OF MEASUREMENT.

The Stone Mastic Asphalt Concrete mixture, whether Item 407(1) or Item 407(8) will be measured by the megagram in accordance with Section 109. The weight used shall be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

Stone Mastic Asphalt for the Wear-Resistant Stone Mastic Asphalt Test Site [Item 407(8)] shall be measured in accordance with all other requirements of this section.  All extraordinary operations necessary to complete the test section shall be subsidiary including, but not limited to, maintaining separate aggregate stockpiles and preventing intermixture of wear-resistant and other aggregates during the crushing, batching, and hauling operations and any other similar items.

Item 407(8A), Test Site Aggregate Hauling, shall be measured by the megagram for all Department-supplied aggregate transported to the Contractor’s plant for processing.  Following Test Site construction, excess aggregate shall become the property of the Contractor.

The method of measurement to be used for asphalt cement will be based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by ATM T-23. These tests shall be the basis for acceptance of the lot. If the Stone Mastic Asphalt Concrete with polyolefin is used, the percent of asphalt cement for each sublot shall be reduced by 0.4 percent, regardless of the actual percent of polyolefin.

The Engineer may direct at any time that tankers shall be weighed before and after unloading in the presence of the Engineer. If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste and diversion will be computed in a manner to be determined by the Engineer.

407-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance. The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project. Acceptance sampling and testing shall be performed by the Engineer. The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams. The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection. If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot. The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection. The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing. If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed. If only one asphalt cement content test is preformed, the weight of asphalt cement for the lot will be calculated from that one test result. If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances. Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees C prior to completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture. Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction, or at the end of the auger. Asphalt cement content will be determined by ATM T-23.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed via a diverter device or from the stopped conveyor belt. The aggregate gradation will be determined by ATM T-7. Diverter devices for obtaining aggregate samples on drum mix plants shall be located on the conveyor system delivering combined aggregates into the drum. The diverter device shall divert aggregate from the full width of the conveyor system and shall be maintained to provide a representative sample of aggregate incorporated into the Stone Mastic Asphalt Concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. Dry batched aggregate gradations will be determined according to ATM T-7. Extracted gradations will be determined in accordance with AASHTO T 30.

Within 24 hours of final rolling, the Contractor shall cut full depth samples from the finished lift for density acceptance testing. One core sample with a minimum diameter of 6 inches shall be taken from each sublot. The samples shall be neatly cut by a core drill at the randomly selected locations marked by the Engineer. ATM T-18 will be used to determine density. No samples shall be cut from asphalt concrete mats on bridge decks. Failure to cut core samples for density acceptance testing within the specified period will result in a deduction of $100.00 per sample per day from the Contractor’s payment for Stone Mastic Asphalt Concrete pavement.

All voids left by sampling shall be backfilled with fresh Stone Mastic Asphalt Concrete mixture and compacted within 24 hours of sampling. Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day from the Contractor’s payment for Stone Mastic Asphalt Concrete pavement.

Samples will be evaluated for acceptance in accordance with Subsection 401-4.03.

The Contractor may request a retest of any sample not within specification limits. This request shall be in writing and delivered to the Engineer within 7 days of receipt of the initial test result. Verbal requests with the written request to be delivered after the specified 7 days will not be accepted. The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s). The Engineer will mark the sample location for the retest. Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s). The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample will be allowed.

407-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when the contract quantity equals or exceeds 4,500 megagrams except as defined in Subsection 407-4.02.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis - Standard Deviation (Specification Conformance Analysis) Method using the procedures listed to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results shall not be included in the price adjustment calculations. If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment. The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s). Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified. AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay. The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained. The maximum pay factor obtainable is 1.05. The maximum pay factor for the largest sieve size specification for gradation shall be 1.00. The price adjustment is based on the lowest of two pay factors. The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture which includes gradation and asphalt cement content. The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer. A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material which appears to be defective based on visual inspection. Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis. Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ = summation of

x=Σxn

x = individual test value to xn

n = total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the 0.075 mm sieve. x is rounded to the nearest hundredth for asphalt content and the 0.075 mm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2) = summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2 = square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the 0.075 mm sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the 0.075 mm sieve.

If the computed sample standard deviation (s) is <0.020, and the arithmetic mean (x) is between the Upper Specification (USL) and Lower Specification (LSL) Limits calculated in step 3., set QU and QL equal to 10 in steps 4 and 5 respectively. If the computed standard deviation (s) is <0.020 and the arithmetic mean (x) is outside the USL or LSL, then use 0.020 for the standard deviation.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL). For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 407-4. The TV is the specification value defined by the Job Mix Design. The TV for density is 94 percent of the maximum specific gravity (MSG). The LSL for density is 92 percent of MSG and the USL is 98%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU=USL-xs

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL=x-LSLs

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 407-5. For negative values of QU, see note at bottom of Table 407-5.

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 407-5. For negative values of QL, see note at bottom Table 407-5.

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 407-6.

10.	Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

CPF=[f3/4} }  \(  { ital PF}  rSub { size 8{ ital 34
                                        )+f1/2} }  \(  { ital PF}  rSub { size 8{ ital 12
                                        )+.......fac(PFac)]Σf

Table 407-7 is used to determine the weight factor (f) for each sieve size and asphalt cement content.

Table 407-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 19.0 mm sieve | TV-6.0 | TV+6.0 |
| 12.5 mm sieve | TV-6.0 | TV+6.0 |
| 9.5 mm sieve | TV-6.0 | TV+6.0 |
| 4.75 mm sieve | TV-6.0 | TV+6.0 |
| 2.36 mm sieve | TV-6.0 | TV+6.0 |
| 1.18 mm sieve | TV-5.0 | TV+5.0 |
| 0.600 mm sieve | TV-4.0 | TV+4.0 |
| 0.300 mm sieve | TV-4.0 | TV+4.0 |
| 0.150 mm sieve | TV-3.0 | TV+3.0 |
| 0.075 mm sieve | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.40 | TV+0.40 |
| Density | 92% | 98% |

TABLE 407-5

Upper Quality Index (QU) or Lower Quality Index (QL)

| PU or PL | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 100 | 1.16-50.0 | 1.48-50.0 | 1.68-50.0 | 1.81-50.0 | 1.90-50.0 | 1.96-50.0 | 2.01-50.0 | 2.05-50.0 | 2.10-50.0 | 2.15-50.0 |
| 99 | - | 1.45-1.47 | 1.61-1.67 | 1.71-1.80 | 1.77-1.89 | 1.82-1.95 | 1.85-2.00 | 1.87-2.04 | 1.92-2.09 | 1.94-2.14 |
| 98 | 1.15 | 1.42-1.44 | 1.55-1.60 | 1.63-1.70 | 1.68-1.76 | 1.71-1.81 | 1.73-1.84 | 1.75-1.86 | 1.78-1.91 | 1.80-1.93 |
| 97 | - | 1.39-1.41 | 1.50-1.54 | 1.56-1.62 | 1.60-1.67 | 1.62-1.70 | 1.64-1.72 | 1.66-1.74 | 1.68-1.77 | 1.69-1.79 |
| 96 | 1.14 | 1.36-1.38 | 1.45-1.49 | 1.50-1.55 | 1.53-1.59 | 1.55-1.61 | 1.56-1.63 | 1.57-1.65 | 1.59-1.67 | 1.60-1.68 |
| 95 | - | 1.33-1.35 | 1.40-1.44 | 1.44-1.49 | 1.47-1.52 | 1.48-1.54 | 1.49-1.55 | 1.50-1.56 | 1.51-1.58 | 1.52-1.59 |
| 94 | 1.13 | 1.30-1.32 | 1.36-1.39 | 1.39-1.43 | 1.41-1.46 | 1.42-1.47 | 1.43-1.48 | 1.44-1.49 | 1.45-1.50 | 1.45-1.51 |
| 93 | - | 1.27-1.29 | 1.32-1.35 | 1.34-1.38 | 1.36-1.40 | 1.37-1.41 | 1.37-1.42 | 1.38-1.43 | 1.38-1.44 | 1.39-1.44 |
| 92 | 1.12 | 1.24-1.26 | 1.28-1.31 | 1.30-1.33 | 1.31-1.35 | 1.31-1.36 | 1.32-1.36 | 1.32-1.37 | 1.33-1.37 | 1.33-1.38 |
| 91 | 1.11 | 1.21-1.23 | 1.24-1.27 | 1.25-1.29 | 1.26-1.30 | 1.26-1.30 | 1.27-1.31 | 1.27-1.31 | 1.27-1.32 | 1.28-1.32 |
| 90 | 1.10 | 1.18-1.20 | 1.20-1.23 | 1.21-1.24 | 1.21-1.25 | 1.22-1.25 | 1.22-1.26 | 1.22-1.26 | 1.22-1.26 | 1.23-1.27 |
| 89 | 1.08-1.09 | 1.15-1.17 | 1.16-1.19 | 1.17-1.20 | 1.17-1.20 | 1.17-1.21 | 1.17-1.21 | 1.18-1.21 | 1.18-1.21 | 1.18-1.22 |
| 88 | 1.07 | 1.12-1.14 | 1.13-1.15 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.17 | 1.13-1.17 | 1.13-1.17 |
| 87 | 1.05-1.06 | 1.09-1.11 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.04 | 1.06-1.08 | 1.06-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.02-1.03 | 1.03-1.05 | 1.02-1.05 | 1.02-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 |
| 84 | 1.01 | 1.00-1.02 | 0.99-1.01 | 0.98-1.01 | 0.98-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 |
| 83 | 0.98-1.00 | 0.97-0.99 | 0.96-0.98 | 0.95-0.97 | 0.94-0.97 | 0.94-0.96 | 0.94-0.96 | 0.93-0.96 | 0.93-0.96 | 0.93-0.96 |
| 82 | 0.97 | 0.94-0.96 | 0.92-0.95 | 0.91-0.94 | 0.91-0.93 | 0.90-0.93 | 0.90-0.93 | 0.90-0.92 | 0.90-0.92 | 0.89-0.92 |
| 81 | 0.94-0.96 | 0.91-0.93 | 0.89-0.91 | 0.88-0.90 | 0.87-0.90 | 0.87-0.89 | 0.87-0.89 | 0.86-0.89 | 0.86-0.89 | 0.86-0.88 |
| 80 | 0.92-0.93 | 0.88-0.90 | 0.86-0.88 | 0.85-0.87 | 0.84-0.86 | 0.83-0.86 | 0.83-0.86 | 0.83-0.85 | 0.83-0.85 | 0.82-0.85 |
| 79 | 0.90-0.91 | 0.85-0.87 | 0.83-0.85 | 0.81-0.84 | 0.81-0.83 | 0.80-0.82 | 0.80-0.82 | 0.80-0.82 | 0.79-0.82 | 0.79-0.81 |
| 78 | 0.88-0.89 | 0.82-0.84 | 0.79-0.82 | 0.78-0.80 | 0.77-0.80 | 0.77-0.79 | 0.77-0.79 | 0.76-0.79 | 0.76-0.78 | 0.76-0.78 |
| 77 | 0.85-0.87 | 0.79-0.81 | 0.76-0.78 | 0.75-0.77 | 0.74-0.76 | 0.74-0.76 | 0.73-0.76 | 0.73-0.75 | 0.73-0.75 | 0.72-0.75 |
| 76 | 0.83-0.84 | 0.76-0.78 | 0.73-0.75 | 0.72-0.74 | 0.71-0.73 | 0.71-0.73 | 0.70-0.72 | 0.70-0.72 | 0.70-0.72 | 0.69-0.71 |
| 75 | 0.80-0.82 | 0.73-0.75 | 0.70-0.72 | 0.69-0.71 | 0.68-0.70 | 0.67-0.70 | 0.67-0.69 | 0.67-0.69 | 0.67-0.69 | 0.66-0.68 |
| 74 | 0.77-0.79 | 0.70-0.72 | 0.67-0.69 | 0.66-0.68 | 0.65-0.67 | 0.64-0.66 | 0.64-0.66 | 0.64-0.66 | 0.63-0.66 | 0.63-0.65 |
| 73 | 0.75-0.76 | 0.67-0.69 | 0.64-0.66 | 0.63-0.65 | 0.62-0.64 | 0.61-0.63 | 0.61-0.63 | 0.61-0.63 | 0.60-0.62 | 0.60-0.62 |
| 72 | 0.72-0.74 | 0.64-0.66 | 0.61-0.63 | 0.60-0.62 | 0.59-0.61 | 0.58-0.60 | 0.58-0.60 | 0.58-0.60 | 0.58-0.59 | 0.57-0.59 |
| 71 | 0.69-0.71 | 0.61-0.63 | 0.58-0.60 | 0.57-0.59 | 0.56-0.58 | 0.56-0.57 | 0.55-0.57 | 0.55-0.57 | 0.55-0.57 | 0.54-0.56 |
| 70 | 0.66-0.68 | 0.58-0.60 | 0.55-0.57 | 0.54-0.56 | 0.53-0.55 | 0.53-0.55 | 0.52-0.54 | 0.52-0.54 | 0.52-0.54 | 0.51-0.53 |
| 69 | 0.63-0.65 | 0.55-0.57 | 0.52-0.54 | 0.51-0.53 | 0.50-0.52 | 0.50-0.52 | 0.49-0.51 | 0.49-0.51 | 0.49-0.51 | 0.49-0.50 |
| 68 | 0.60-0.62 | 0.52-0.54 | 0.48-0.51 | 0.48-0.50 | 0.47-0.49 | 0.47-0.49 | 0.47-0.48 | 0.46-0.48 | 0.46-0.48 | 0.46-0.48 |
| 67 | 0.57-0.59 | 0.49-0.51 | 0.46-0.47 | 0.45-0.47 | 0.45-0.46 | 0.44-0.46 | 0.44-0.46 | 0.44-0.45 | 0.43-0.45 | 0.43-0.45 |
| 66 | 0.53-0.56 | 0.46-0.48 | 0.44-0.45 | 0.42-0.44 | 0.42-0.44 | 0.41-0.43 | 0.41-0.43 | 0.41-0.43 | 0.41-0.42 | 0.40-0.42 |
| 65 | 0.50-0.52 | 0.43-0.45 | 0.41-0.43 | 0.40-0.41 | 0.39-0.41 | 0.39-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.39 |
| 64 | 0.47-0.49 | 0.40-0.42 | 0.38-0.40 | 0.37-0.39 | 0.36-0.38 | 0.36-0.38 | 0.36-0.37 | 0.35-0.37 | 0.35-0.37 | 0.35-0.37 |
| 63 | 0.44-0.46 | 0.37-0.39 | 0.35-0.37 | 0.34-0.36 | 0.33-0.35 | 0.33-0.35 | 0.33-0.35 | 0.33-0.34 | 0.32-0.34 | 0.32-0.34 |
| 62 | 0.40-0.43 | 0.34-0.36 | 0.32-0.34 | 0.31-0.33 | 0.31-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.31 | 0.30-0.31 |
| 61 | 0.37-0.39 | 0.31-0.33 | 0.29-0.31 | 0.28-0.30 | 0.28-0.30 | 0.28-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 |
| 60 | 0.33-0.36 | 0.28-0.30 | 0.26-0.28 | 0.26-0.27 | 0.25-0.27 | 0.25-0.27 | 0.25-0.26 | 0.25-0.26 | 0.24-0.26 | 0.24-0.26 |
| 59 | 0.30-0.32 | 0.25-0.27 | 0.24-0.25 | 0.23-0.25 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.23 | 0.22-0.23 |
| 58 | 0.26-0.29 | 0.22-0.24 | 0.21-0.23 | 0.20-0.22 | 0.20-0.21 | 0.20-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 |
| 57 | 0.23-0.25 | 0.19-0.21 | 0.18-0.20 | 0.17-0.19 | 0.17-0.19 | 0.17-0.19 | 0.17-0.18 | 0.17-0.18 | 0.17-0.18 | 0.16-0.18 |
| 56 | 0.19-0.22 | 0.16-0.18 | 0.15-0.17 | 0.15-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.15 |
| 55 | 0.15-0.18 | 0.13-0.15 | 0.12-0.14 | 0.12-0.14 | 0.12-0.13 | 0.12-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 |
| 54 | 0.12-0.14 | 0.10-0.12 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 |
| 53 | 0.08-0.11 | 0.07-0.09 | 0.07-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.05-0.07 | 0.04-0.06 | 0.04-0.06 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.04 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

TABLE 407-6

Required Quality Level (QL) for a given sample size (n) and

a given Pay Factor (PF)

| Pay Factor | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.05 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 1.04 | 90-99 | 91-99 | 92-99 | 93-99 | 93-99 | 93-99 | 94-99 | 94-99 | 95-99 | 95-99 |
| 1.03 | 80-89 | 85-90 | 87-91 | 88-92 | 89-92 | 90-92 | 91-93 | 91-93 | 92-94 | 93-94 |
| 1.02 | 75-79 | 80-84 | 83-86 | 85-87 | 86-88 | 87-89 | 88-90 | 88-90 | 89-91 | 90-92 |
| 1.01 | 71-74 | 77-79 | 80-82 | 82-84 | 84-85 | 85-86 | 85-87 | 86-87 | 87-88 | 88-89 |
| 1.00 | 68-70 | 74-76 | 78-79 | 80-81 | 81-83 | 82-84 | 83-84 | 84-85 | 85-86 | 86-87 |
| 0.99 | 66-67 | 72-73 | 75-77 | 77-79 | 79-80 | 80-81 | 81-82 | 82-83 | 83-84 | 85 |
| 0.98 | 64-65 | 70-71 | 73-74 | 75-76 | 77-78 | 78-79 | 79-80 | 80-81 | 81-82 | 83-84 |
| 0.97 | 62-63 | 68-69 | 71-72 | 74 | 75-76 | 77 | 78 | 78-79 | 80 | 81-82 |
| 0.96 | 60-61 | 66-67 | 69-70 | 72-73 | 73-74 | 75-76 | 76-77 | 77 | 78-79 | 80 |
| 0.95 | 59 | 64-65 | 68 | 70-71 | 72 | 73-74 | 74-75 | 75-76 | 77 | 78-79 |
| 0.94 | 57-58 | 63 | 66-67 | 68-69 | 70-71 | 72 | 73 | 74 | 75-76 | 77 |
| 0.93 | 56 | 61-62 | 65 | 67 | 69 | 70-71 | 71-72 | 72-73 | 74 | 75-76 |
| 0.92 | 55 | 60 | 63-64 | 65-66 | 67-68 | 69 | 70 | 71 | 72-73 | 74 |
| 0.91 | 53-54 | 58-59 | 62 | 64 | 66 | 67-68 | 68-69 | 69-70 | 71 | 73 |
| 0.90 | 52 | 57 | 60-61 | 63 | 64-65 | 66 | 67 | 68 | 70 | 71-72 |
| 0.89 | 51 | 55-56 | 59 | 61-62 | 63 | 64-65 | 66 | 67 | 68-69 | 70 |
| 0.88 | 50 | 54 | 57-58 | 60 | 62 | 63 | 64-65 | 65-66 | 67 | 69 |
| 0.87 | 48-49 | 53 | 56 | 58-59 | 60-61 | 62 | 63 | 64 | 66 | 67-68 |
| 0.86 | 47 | 51-52 | 55 | 57 | 59 | 60-61 | 62 | 63 | 64-65 | 66 |
| 0.85 | 46 | 50 | 53-54 | 56 | 58 | 59 | 60-61 | 61-62 | 63 | 65 |
| 0.84 | 45 | 49 | 52 | 55 | 56-57 | 58 | 59 | 60 | 62 | 64 |
| 0.83 | 44 | 48 | 51 | 53-54 | 55 | 57 | 58 | 59 | 61 | 63 |
| 0.82 | 42-43 | 46-47 | 50 | 52 | 54 | 55-56 | 57 | 58 | 60 | 61-62 |
| 0.81 | 41 | 45 | 48-49 | 51 | 53 | 54 | 56 | 57 | 58-59 | 60 |
| 0.80 | 40 | 44 | 47 | 50 | 52 | 53 | 54-55 | 55-56 | 57 | 59 |
| 0.79 | 38-39 | 43 | 46 | 48-49 | 50-51 | 52 | 53 | 54 | 56 | 58 |
| 0.78 | 37 | 41-42 | 45 | 47 | 49 | 51 | 52 | 53 | 55 | 57 |
| 0.77 | 36 | 40 | 43-44 | 46 | 48 | 50 | 51 | 52 | 54 | 56 |
| 0.76 | 34-35 | 39 | 42 | 45 | 47 | 48-49 | 50 | 51 | 53 | 55 |
| 0.75 | 33 | 38 | 41 | 44 | 46 | 47 | 49 | 50 | 51-52 | 53-54 |
| 0 | 0-32 | 0-37 | 0-40 | 0-43 | 0-45 | 0-46 | 0-48 | 0-49 | 0-50 | 0-52 |

Table 407-7

WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| 19.0 mm sieve | 3 |
| 12.5 mm sieve | 8 |
| 9.5 mm sieve | 7 |
| 4.75 mm sieve | 6 |
| 2.36 mm sieve | 5 |
| 1.18 mm sieve | 4 |
| 0.600 mm sieve | 4 |
| 0.300 mm sieve | 4 |
| 0.150 mm sieve | 4 |
| 0.075 mm sieve | 15 |
| Asphalt % | 40 |

407-5.01 BASIS OF PAYMENT. The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $4.95 per 0.25 percent additive per megagram of asphalt cement.

Cellulose stabilizing additive or  Polyolefin stabilizing additive will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for anti-stripping additive or Asphalt price adjustment pay items. The approved Job Mix Design will initiate Item 407(3), Anti-Stripping Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(4), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 407-4.02. The Asphalt Price Adjustment will be algebraically added to the Contractor's payment for Stone Mastic Asphalt Concrete. Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value. The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $60/mg

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest  value.

Item 407(7), Asphalt Concrete Leveling Course, will pay for any asphalt concrete placed under the Stone Mastic Asphalt Concrete, regardless of whether that material is Asphalt Concrete, Type II, Class A, in accordance with Section 401, or Asphalt Concrete, Type III, Class B in accordance with Section 608.  No Price Adjustments will be applied for Item 407(7).

Item 407(8A), Test Site Aggregate Hauling, will pay for transporting Department-supplied aggregate to the Contractor’s plant.  Approximately 120 cubic meters will be supplied.  Before concluding the hauling operation, the Contractor shall verify that this quantity is sufficient to produce the approximately 120 mg required for the test site.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

407(1)	Stone Mastic Asphalt Concrete	Megagram

407(2)	AC-5 Asphalt Cement	Megagram

407(3)	Anti-Stripping Additive	Contingent Sum

407(4)	Asphalt Price Adjustment	Contingent Sum

407(7)	Asphalt Concrete Leveling Course	Megagram

407(8)	Wear-Resistant Stone Mastic Asphalt Test Site	Megagram

407(8A)	Test Site Aggregate Hauling	Megagram

R163M

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

Add the following paragraph:

603-3.06 PIPES FOR FUTURE UTILITY CROSSINGS.  The Contractor shall install pipes for future utility crossings in locations shown on the drawings.  Crossings shown are approximate station only.  Prior to installing the pipe, the Contractor shall obtain existing underground utility locations in each of the proposed crossing locations and then confirm the field location of each crossing with the Engineer and Engineering personnel for each participating Utility.  In each case, the Contractor shall provide the Engineer and ML&P with the proposed schedule for each crossing a minimum of three (3) working days and a maximum of seven (7) calendar days in advance of construction.

The minimum depth of bury for each crossing is 1220 millimeters.  The depth of bury shall not exceed 1830 millimeters without approval of the Engineer and the Utility.

ML&P.  The Contractor can obtain a point of contact in ML&P Engineering by calling 263-5244 or 263-5245.  The Contractor shall coordinate with ML&P Engineering to obtain EMS locators, which the Contractor shall place at the ends of each ML&P crossing in accordance with the drawings.

The Contractor shall provide as-built drawings for ML&P’s use, sealed by a Professional Land Surveyor, which lists the station, offset, and elevation of the centerline and each end of the crossing.

603-4.01 METHOD OF MEASUREMENT.  Add the following: Pipes for Utility Crossings shall be measured complete in place per meter from end to end as shown on the sealed asbuilt drawing.  All associated items shown on the drawing such as end caps and EMS locators will not be measured for payment, but will be considered subsidiary.

603-5.01 BASIS OF PAYMENT.  Add the following:

Pay Item No.	Pay Item	Pay Unit

603(17-450A)	450 mm Pipe for Utility Crossing	Meter

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01 CONSTRUCTION REQUIREMENTS.  Add the following: The work required to Replace Inlet Frame and Grate, or Replace Manhole Cover, Frame and Grade Ring shall be completed in accordance with the requirements for “Adjustment of Existing Manholes,” with the exception that new materials shall be provided, and no salvage items shall be used.

In paved areas, the work shall be completed such that the top of the finished manhole cover shall be within a tolerance of 6 mm to 10 mm below the pavement.

604-5.01  BASIS OF PAYMENT.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

604(13A)	Replace Inlet Frame and Grate	Each

604(36)	Replace Manhole Cover, Frame and Grade Ring	Each

SECTION 607

FENCES

Special Provisions

607-1.01 DESCRIPTION.  Add the following: This work shall also include construction and installation of special landscape bollards, fences, and decorative sign arches and decorative sign posts as shown on plans.

607-2.01 MATERIALS.  Add the following:

Galvanized Metal			716

607-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:  Welding shall comply with American Welding Society specifications.

Add the following:

607-3.02 PAINT FOR GALVANIZED SURFACES.

- Preparing Galvanized Surfaces for Painting.  Surfaces of galvanized metal to be painted shall be prepared as follows:  Clean surfaces with steel cleaner using Iron Etch (Martin Seynour Paints Iron-Etch 6878) or equal to create a clean surface free of rust, oil, grease, pitted, or heavily oxidized surfaces.  Steel cleaner shall be phosphoric acid based, multi-purpose cleaner and conditioner for metal that removes oxidation, deep cleans, and deposits a thin layer of iron phosphate to prevent flash rusting, promote paint adhesion and improve corrosion resistance.

2.  Schedule of Paints.  All metal surfaces shall be painted with a minimum of three coats:

a.	Prime coat shall be an Acrylic Urethane Primer-Surfacer, Tec/Prime (Martin Seynour Paints Iron-Etch 6878) or equal.

b.	Intermediate coat shall be Acrylic Enamel Paint, Acrylic Enamel System (Martin Seynour Paints) or equal.  Available in colors as shown on plans and herein.

c.	Hardener coat shall be Urethane Hardener, (Martin Seynour Paints Super Catyl-Ad 8870 Urethane Hardener) or equal.  Hardener shall improve gloss, durability, reparability, and chemical/solvent resistance.

3.	Schedule of Colors.  All fences, bollards, decorative sign posts and decorative sign arches shall be painted in colors as noted on plans.  The following colors listed  on plans equal the Munsell System of Color Notation:

Fireweed Pink = Red-Purple (Bright Magenta 5RP 6/12)

Alpine Purple = Purplish Red Purple (Royal Purple 10P 5/12)

Deep Green = Greenish Blue Green (Evergreen 10G 5/4)

4. 	Painting Surfaces.

a.	All paint shall be applied in the shop.  Touch up work may be field applied but must include appropriate surface preparation and all coats.

b.	Time of Application. The prime coat of paint shall be applied as soon as possible after the surface has been cleaned and before deterioration of the surface occurs.  Any oil, grease, soil, dust, or foreign matter deposited on the surface after preparation is completed shall be removed prior to painting.  In the event that rusting or contamination by foreign substances occurs after completion of the surface preparation, the surfaces shall be cleaned again.

c.	Paint Storage.  All paint and related chemicals should preferably be stored in a separate building or room that is well ventilated and free from excessive heat, sparks, flame, direct sun, temperature fluctuations, or from freezing that could result in damage to the paint.

All containers of paint shall remain unopened until required for use.  Paint which has "livered", "gelled", or otherwise deteriorated during storage shall not be used unless they can be stirred to attain a normal consistency.

d.	Mixing and Thinning.  All ingredients in any container of paint shall be thoroughly mixed before use and shall be agitated often enough during  application to keep the pigment in suspension.

Paint mixed in the original container shall not be transferred until all settled pigment is incorporated into the vehicle.  This does not imply that part of the vehicle cannot be poured off temporarily to simplify the mixing.

Mixing shall be by mechanical methods, except that hand mixing will be permitted for containers up to  20 liters in size.

Mixing in open containers shall be done in a well-ventilated area away from sparks or flames.

Paint shall not be mixed or kept in suspension by means of an air stream bubbling under the paint surface.

Where a skin has formed in the container the skin shall be cut loose from the sides of the container, removed, and discarded.  If such skins are thick enough to have a practical effect on the composition and quality of the paint, the paint shall not be used.

The paint shall be mixed in a manner which will insure breaking up of all lumps, complete dispersion of settled pigment, and a uniform composition.  If mixing is done by hand, most of the vehicle shall be poured off into a clean container.

The pigment in the paint shall be lifted from the bottom of the container with a broad, flat paddle, lumps shall be broken up, and the pigment thoroughly  mixed with the vehicle.  The poured-off vehicle shall be returned to the paint with simultaneous stirring or pouring repeatedly from one container to another until the composition is uniform.  The bottom of the container shall be inspected for unmixed pigment.

Tinting pastes or colors shall be wetted with a small amount of thinner, vehicle paint and thoroughly mixed.  The thinned mixture shall then be added to the large container of paint and mixed until the color is uniform.

Paint which does not have a limited pot life, or does not deteriorate on standing, may be mixed at any time before using, but, if settling has occurred it must be remixed immediately before using.  Paint shall not remain in spray pots, painters’ buckets, etc., overnight, but shall be gathered into a container and remixed before use.

Paint thinner conforming to the manufacturer’s instructions may be added, when deemed necessary by the Engineer to obtain satisfactory application.  In any case, the amount added shall not exceed 125 mL of thinner per liter of paint.

e.	Application of Paint.  The oldest of each kind of paint shall be used first.  Paint shall be  applied by brushing or spraying or a combination of these methods.  Dipping, roller coating, or flow coating shall be used only when specifically authorized.

Paint shall not be applied when the surrounding air temperature is below 60 degrees C or when application to steel will cause blistering or porosity or otherwise will be detrimental to the life of the paint.

When paint must be applied in damp or cold weather, the steel must be painted under cover, protected, sheltered or the surrounding air and the steel heated to a satisfactory temperature.  In all such cases, the above temperature and humidity conditions must be met.  Such steel shall remain under cover or be protected until dry or until weather conditions permit its exposure.

Any applied paint exposed to freezing, excess humidity, rain, snow or condensation shall first be permitted to dry.  Then damaged areas of paint shall be removed, the surface again prepared and then repainted with the same kind as the undamaged areas.

To the maximum extent practical, each coat of paint shall be applied as a continuous film of uniform thickness, free of pores.  Any thin spots or areas missed in the application shall be repainted and permitted to dry before the next coat is applied.

Each coat of paint shall be in proper state of cure or dryness before the application of the succeeding coat.

The prime and intermediate coats shall each have a minimum dry film thickness of 40 μm.  The finish coat shall have a minimum dry film thickness of 25 μm.  The dry film thickness of the paint will be measured in place with a calibrated magnetic film thickness gauge.  If any coat of paint is thinner than specified.  The minimum dry film thickness shall be obtained by the application of additional coats of paint and no additional payment will be made for such work.

f.	Brush Application.  Paint shall be worked into all crevices and corners where possible and surface not accessible to brushes shall be painted by spray daubers or sheepskins.  All runs or sags shall be brushed out.  There shall be a minimum of brush  marks left in the applied paint.

g.	Spray Application of Paint.  The equipment used for spray application of paint shall be suitable for the intended purpose, shall be capable of properly atomizing the paint to be applied, and shall be equipped with suitable pressure regulators and gauges.  The air caps, nozzles and needles shall be those recommended by the manufacturer of the equipment for the material being sprayed.  The equipment shall be kept in satisfactory condition to permit proper paint application.  In closed or recirculation paint spray systems, where gas under pressure is used over the liquid, the gas shall be an inert one, such as nitrogen.

Traps or separators shall be provided to remove oil an water from the compressed air.  These traps or separators shall be of adequate size and shall be drained periodically during operations.  The air from the spray gun impinging against the surface shall show no water or oil.

Paint ingredients shall be kept  properly mixed in the spray pots or containers during paint application either by continuous mechanical agitation or by intermittent agitation as frequently as necessary.

The pressure on the material in the pot and of the air at the gun shall be adjusted for optimum spraying effectiveness.  The pressure on the material in the pot shall be adjusted when necessary for changes in elevation of the gun above the pot.  The atomizing air pressure at the gun shall be high enough to atomize the paint properly but not so high as to cause excessive fogging of paint, excessive evaporation of solvent, or loss by overspray.

Spray equipment shall be kept sufficiently clean so that dirt, dried paint, and other foreign materials are not deposited in the paint film.  Any solvents left in the equipment shall be completely removed before applying paint to the surface being painted.

Paint shall be applied in a uniform layer, with overlapping at the edge of the spray pattern.  During the application, the gun shall be held perpendicular to the surface and at a distance which will insure that a wet layer of paint is deposited on the surface.  The trigger of the gun should be released at the end of each stroke.

All runs and sags shall be brushed out immediately  or the paint shall be removed and the surface repainted.

Areas inaccessible to spray gun shall be painted by brush.  If not accessible by brush, daubers or sheepskins shall be used.  Brushes shall be used to work paint into cracks, crevices, and blind spots which are not adequately painted by spray.

h.	Shop Painting.  Shop painting shall be done after fabrication and before any damage to the surface occurs from weather or other exposure.  Shop contact surfaces shall not be painted except where the paint will interfere with assembly.  High strength bolted connection contact surfaces shall not be painted.  Surfaces not to be in contact but which will be inaccessible after assembly shall receive either the full paint coats.  The areas of steel surfaces to be in contact with concrete need not be painted.

The steel shall not be painted within 50 mm from the edges to be welded, until after welding is completed.

Anti-weld spatter coatings shall be removed before painting.  Weld slag and flux shall be removed as specified in Section 504.

Machine-finished or similar surfaces that are not to be painted shall be protected with a coating of rust inhibitive petroleum, or other coatings which may be more suitable for special conditions.

Erection marks and weight marks shall be copied on areas that have been previously painted with the shop coat.

i.	Drying of Painted Metal.  The maximum practicable time shall be allowed for paint to dry before recoating or exposure.  No dryer shall be added to paint on the job unless called for in the specification for the paint.  Painted metal shall not be immersed until paint has dried.  Paint shall be protected form rain, condensation, contamination, snow, and freezing until dry to the fullest extent practicable.

j.	Handling of Painted Steel.  Painted steel shall not be handled until the paint has dried except for necessary handling in turning for painting or stacking for drying.

Paint which is damaged in handling shall be scraped off and touched up with the same number of coats and kinds of paint as were previously applied to the steel.

Painted steel shall not be loaded for shipment or shipped until it is dry.

Precautions shall be taken to minimize damage to paint films resulting from stacking members.

607-4.01 METHOD OF MEASUREMENT.  Delete section in its entirety and add the following:  Special landscape bollards, and fences will be measured by the meter.  Measurement will be parallel to the ground, measured at the base of the structure, not including gates.

Decorative sign arches, decorative sign posts, and gates will be measured as complete units of the size and type specified.

607-4.01 BASIS OF PAYMENT.  Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

607(23)	Decorative Fence	Meter

607(24)	Bollard Fence	Meter

607(25)	Decorative Sign Arch	Each

607(26)	Decorative Sign Post	Each

SECTION 608

SIDEWALKS

Special Provisions

608-2.01  MATERIALS.  Add the following:  AC-5 asphalt cement shall be used in the asphalt concrete pavement mix for asphalt sidewalks, and shall conform to the requirements of subsection 702-2.01, Asphalt Cements.  Aggregate shall meet the gradation requirements of subsection 703-2.04, Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete Type III, class B.  In addition, the asphalt concrete shall conform to the following:

Asphaltic Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS "B" |
| --- | --- |
| Stability, newton, min. | 5,340 |
| Flow, 0.25 mm | 8-16 |
| Voids in total mix, percent | 3-5 |
| Compaction, number of blows each side of test specimen | 50 |
| Dust-asphalt ratio* | 0.6-1.4 |
| Voids in the mineral aggregate (VMA), min., Type III | 13.0 |

*Dust-asphalt ratio is defined as the percent of material passing the 75μm sieve divided by the percent of asphalt (calculated by weight of mix).

608-4.01  METHOD OF MEASUREMENT.  Add the following:  Asphalt concrete for sidewalk paving will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.

Additional asphalt pavement used for patching asphalt medians or matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.

608-5.01  BASIS OF PAYMENT.  Add the following:  Asphalt cement will not be paid for separately, but will be subsidiary to Item 608(2), Asphalt Sidewalk.

Numerical suffixes included within the parentheses of the item numbers in order to denote different depths of concrete in millimeters.

SECTION 609

CURBING

Special Provisions

609-2.01 MATERIALS. Delete the second paragraph and substitute the following: Concrete for curbing shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.02 Batching is modified as follows:

Under item 3. Aggregates, delete the third paragraph.

609-3.01 CAST-IN-PLACE CONCRETE CURBING. Add the following to the seventh paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.

(5/1/95)R202M

609-3.04 CURB RAMPS.  Add the following: Curb ramps adjacent to concrete sidewalks shall have pigment thoroughly mixed to a depth of 15 millimeters. Color in the dry state shall closely match FED. STD. 595, color 30252, brick red. Curb ramps adjacent to asphalt pathways shall have no added coloring. (8/4/95)R162M

SECTION 614

SURVEY MONUMENTS AND MONUMENT CASES

Delete this Section in its entirety and refer to Section 642 of these Special Provisions.

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS.  Add the following to the end of the first sentence of the fifth paragraph: "the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual."

615-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the sixth paragraph: When existing signs are to be salvaged, the remaining foundation shall be removed, abandoned in place, or if located within the roadway structural section shall be disposed of in a manner as approved by the Engineer. If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

Add the following after the sixth paragraph: Salvaged sign panels shall be delivered to the State Maintenance Yard at 5700 Tudor Road.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Existing signs shall not be removed without authorization from the Engineer. They shall be kept in service until either the new signs have been installed, or they are no longer needed. As the work progresses, if their locations do not conform to Standard Drawing S-05[M], they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the installation date on the back of the sign. Installation dates shall be written in the month/day/year format, using black permanent marker, with numbers a minimum of 75 mm high, so as to be readable from the roadside after installation.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01 BASIS OF PAYMENT. Add the following: Payment for keeping existing signs in service until they are not longer needed, or temporarily relocating existing signs, will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Payment for removal of existing sign post foundations, or work required to abandon them in place, shall be included in Item 615(7), Salvage Signs.

R50M

SECTION 621

PLANTING TREES AND SHRUBS

Special Provisions

621-1.01  DESCRIPTION.  Add the following: This work shall also include preparation of landscape beds, furnishing and installing concrete planters, furnishing and installing topsoil backfill, wood chip mulch and edging as shown on plans.

621-1.02  PLANT STOCK.

- Nursery stock.  Add the following:

c.	Perennials shall have been growing for at least one year and exhibit strong root growth pattern within containers.  Perennial roots shall be visible and thriving when plant is pulled out of its container for inspection.  Weeds, grasses and foreign materials shall be completely removed from the containers of all plants.  Complete removal includes removal of all related roots.  Perennials shall be easily identifiable through thick healthy leaf growth.  Dormant plants will not be accepted.

- Collected stock.  Add the following:

Weeds, grasses and foreign materials shall be completely removed from the rootball and containers of all plants.  Complete removal includes removal of all related roots.

621-2.02  FERTILIZER.  Add the following:  Newly planted trees, shrubs and perennials shall not be fertilized during the season they are planted.

621-2.08  SHREDDED BARK MULCH.  Add the following subsection:  Shredded bark mulch shall consist of Spruce, Douglas Fir, Pine or Hemlock bark shredded with maximum length of 5 cm.  The shredded mulch shall not contain resin, tannin, non-organic or foreign elements in quantities that could inhibit plant growth.  The mulch shall have the characteristics to be spread evenly so as to form a uniform consistent mat that inhibits weed growth and will not blow or wash away.

621-3.03  PLANTING.  Delete item 1.  Plant season, and substitute the following:

- Plant season.

- Locally grown: When native species of locally grown trees and shrubs are furnished for the project, they shall be planted between June 1st and September 15th.  Shrubs shall be fully leafed-out prior to planting.

- Imported: When plants shipped in from out-of-state, handling shall be in accordance with nursery recommendations.  Plants imported from out-of-state shall be planted between May 15th and September 1st.

Delete item 2.  Excavation and substitute the following:

- Prepare Planting Bed.

- Planting beds must be completely prepared prior to placement of plants.  Planting bed preparation includes excavation, loosening of subgrade soils and placement of edging and topsoil.  Planting beds shall be prepared no more than five days prior to planting.

- Prior to the excavation of planting beds, the Contractor shall ascertain the location of all utilities so that proper precautions may be taken not to disturb or damage any subsurface improvements.  Should obstructions be found, the Contractor shall promptly notify the Engineer who will arrange to relocate the plant material.

- Planting beds shall be excavated to a depth of 60 cm.  All excavation is to be removed from the site and disposed according to specifications.

- Planting beds are to be tilled to a depth of 60 cm.  All excavation is to be removed from the site and disposed according to specifications.

- Once tilled subgrade shall not be mechanically compacted.  Heavy equipment shall not be used within planting beds.

- Backfill planting beds with topsoil.  Tamp gently, do not over compact.

- Dig planting holes within planting bed.  Firmly tamp the base of the planting hole to assure plants will not settle to lower than their proper planting depth.

Delete paragraph b under item 5 Placing Plants and substitute with the following:

- Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container or basket and not the plant itself.  Wire baskets shall be stripped to the base of the root ball, trimmed and removed from the site.  Containers shall be removed from the site.

Delete item 7.  Wrapping. In its entirety and add the following:

- Wrapping.  Plant materials shall not be wrapped.

Delete item 8. In its entirety and substitute the following:

- Staking and Guying.  Delete item a. and substitute the following:

- Trees shall not be staked unless the Contractor determines staking to be essential to establishment of trees on the site.  In which case the Contractor shall submit complete design of staking procedures prior to performing work.  The Contractor shall also be responsible for removing stakes one year after installation.  Staking shall follow the most recent guidelines provided by the State of Alaska, Division of Forestry, Urban and Community Forestry Program recommended guidelines for staking plants.

621-3.04  PERIOD OF ESTABLISHMENT.  Add the following:  At the end of the period of establishment, in the season following the planting the Contractor shall apply 8-32-16 fertilizer at the recommended horticultural rates for the caliper size of each tree planted and at a rate of 2 kilograms/90 square meters for planting beds.

621-4.01  METHOD OF MEASUREMENT.  Delete this subsection in its entirety and substitute the following: Each landscaped area denoted on the plans and in the bid items shall be measured as one unit, complete and accepted in place, at the date of Final Inspection.  Preparing Planting Beds, Plant Materials, Mulch, Staking, Edging, Topsoil, Fertilizer, Watering, and all other materials and work items required to construct the work according to the details and establish a healthy grouping of plants shall all be subsidiary.

621-5.01  BASIS OF PAYMENT.  Add the following to Pay Items:

Pay Item No.	Pay Item	Pay Unit

621 (15A)	10th Avenue Landscaping per Detail	Lump Sum

621 (15B)	12th Avenue Landscaping per Detail	Lump Sum

621 (15C)	13th Avenue Landscaping per Detail	Lump Sum

621 (15D)	14th Avenue Landscaping per Detail	Lump Sum

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01 DESCRIPTION add the following:  The Contractor is notified that the property owner, Wadeen Hepworth of Lot 5, S1/2 & Lot 6, S1/2, Block 6D, East Addition, at 831 Gambell Street is planning to install a water service to this property. The diameter of the service line has yet to be determined.   The location of this water service tap is on the east side of Gambell Street between 8th and 9th Avenues at approximate Station 17+140.  The placement of this water service shall be completed prior to final paving in this location.  The Contractor shall notify Wadeen Hepworth at least fourteen (14) calendar days prior to placing finish pavement in the water service location.

The water service installation work may be performed during the completion of the Project. The property owner may elect to contract the work with the Contractor or another party.  All work to be performed shall be coordinated with the Contractor.  The property owner shall be responsible for all costs, scheduling and securing all necessary permits to facilitate the installation of the new water service. No separate payment shall be made by the Department or Anchorage Water and Wastewater Utility.

627-2.01 MATERIALS.  Under Item 5. Valve Boxes, add the following: The Contractor shall furnish and install each Valve Box to be installed in accordance with Section 712-2.11, AWWU shall furnish and the Contractor shall install each lid.

The Contractor shall contact Steve Bryant, (907 267-5417) forty-eight (48) in advance to establish the schedule for the Contractor to pick up the material at AWWU’s Operations and Maintenance Facility at 325 E. 94th Court, (94th Avenue & King Street, Anchorage) The Contractor will be given all materials at one time.  Storage and safekeeping of all materials after pickup shall be the Contractor’s responsibility.  All unused materials shall be returned to the warehouse upon completion of the project.

627-3.05.  Add the following: Where AWWU-supplied lids are installed, the dust pan shall not be required, and The Contractor shall paint the lids safety blue.

627-5.01 BASIS OF PAYMENT.  Add the following: Disposing existing valves shall be subsidiary to Item 627(3) Install Valve Box.

SECTION 639

DRIVEWAYS

Special Provisions

639-3.01 BASIS OF PAYMENT.  Delete the last paragraph and substitute the following: The contract unit price for driveways shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified. Selected Material, Type A, Crushed Aggregate Base Course, and Asphalt Concrete Type II required to construct driveways will be paid for separately under the respective items listed in the bid schedule. Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary.

Work required for Public Approaches shall be subsidiary to other bid items.

R58

Delete Section 641 in its entirety and substitute the following:

SECTION 641

TEMPORARY EROSION AND POLLUTION

CONTROL

Special Provisions

641-1.01 DESCRIPTION. This work shall consist of temporary control measures as shown on the plans, or ordered during the life of the contract, to control temporary erosion and water pollution. This work shall include preparation of a Temporary Erosion and Pollution Control (TEPC) Plan. The Contractor shall conduct construction activities in accordance with the approved TEPC Plan.

641-1.02 TEMPORARY EROSION AND POLLUTION CONTROL PLAN. At least five (5) days prior to the preconstruction conference, the Contractor shall submit for approval by the Department's Environmental Section, a TEPC Plan consisting of the following:

1.	Methods for clearing and grubbing.

2.	Plan for installation of temporary erosion and sediment control measures, in accordance with the Department's Storm Water Manual, including, but not limited to, the following activities:

a.	Excavation and embankment construction;

b.	Construction of temporary and permanent drainage features;

c.	Construction in and around waterbodies and wetlands; and

d.	Haul roads and material sites.

3.	Disposal of waste material.

4.	Containment, cleanup, and disposal of such substances, as well as the methods to be utilized for disposing of, petroleum products or other hazardous substances generated by construction equipment or activities. The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.

The Department will review the TEPC Plan for approval within five (5) working days. If corrections or modifications are necessary to the plan, the corrected plan shall be resubmitted by the Contractor within five (5) days of receipt of the comments.

641-2.01 CONSTRUCTION REQUIREMENTS. The Engineer shall limit the surface area of erodible earth material exposed by clearing and grubbing, excavation, borrow and fill operations and direct the Contractor to provide immediate permanent or temporary pollution control measures to prevent contamination of adjacent streams, lakes, ponds or other areas of water impoundment. As necessary such work may involve the construction of temporary berms, dikes, dams, sediment basins, slope drains, and use of temporary mulches, seeding or other control devices or methods as necessary to control erosion. Temporary pollution control measures shall be used to correct conditions that develop during construction that were not foreseen during the design stage, that are needed prior to installation of permanent pollution control features, but are not associated with permanent control features on the project.

The Contractor shall be required to incorporate all permanent erosion control features into the project at the earliest practicable time as outlined in his accepted schedule.

Cut slopes shall be seeded and mulched as the excavation proceeds to the extent considered desirable and practicable.

Where erosion is likely to be a problem, clearing and grubbing operations shall be so scheduled and performed that grading operations and permanent erosion control features can follow immediately thereafter if the project conditions permit; otherwise temporary erosion control measures may be required between successive construction stages. The surface area of erodible earth material exposed at one time by clearing and grubbing shall not exceed 2.02 hectares without written approval.

The Engineer shall limit the area of excavation, borrow and embankment operations in progress commensurate with the Contractor's capability and progress in keeping the finish grading, mulching, seeding and other such permanent pollution control measures current in accordance with the accepted schedule. Should seasonal limitations make such coordination unrealistic, temporary erosion control measures shall be taken immediately to the extent feasible and justified.

In the event of conflict between these requirements and pollution control laws, rules or regulations of other federal or state or local agencies, the more restrictive laws, rules or regulations shall apply.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-3.01 METHOD OF MEASUREMENT. The method of measurement shall be as specified in the order authorizing the work.

641-4.01 BASIS OF PAYMENT. Temporary erosion and pollution control work required, which is not attributed to the Contractor's negligence, carelessness or failure to install permanent controls, will be paid for as specified in the order authorizing the work.

In the event that temporary erosion and pollution control measures are required due to the Contractor's negligence, carelessness or failure to install permanent controls as a part of the work as scheduled and as ordered, such work shall be performed by the Contractor at his own expense.

In case of repeated failures on the part of the Contractor to control erosion, pollution and/or siltation, the Engineer reserves the right to employ outside assistance or to use his own forces to provide the necessary corrective measures. Such incurred direct costs plus project engineering costs will be charged to the Contractor and appropriate deductions made from the Contractor's monthly progress estimate.

Temporary pollution control may include construction work outside the right-of-way where such work is necessary as a result of roadway construction, such as State Furnished Material sources. Temporary erosion and pollution control in connection with contractor furnished material sources shall be at the expense of the Contractor.

The erosion control features installed by the Contractor shall be acceptably maintained by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(2)	Erosion and Pollution Control	Contingent Sum

R203M

Delete Sections 614 and 642 and replace with the following:

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION. Perform all surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the plans and specifications and standard engineering practice.

Furnish & install survey monuments and monument cases according to the Plans or as directed.

Adjust existing monuments and monument cases to conform to the new elevations.

642-1.02 DEFINITIONS

- Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown on the plans.

2.	Point: Any identified spot located on the surface of the earth. For purposes of this definition, a point can be a PK nail, wooden hub, rebar, large nail or any other structure capable of being utilized as a marker.

- Witness Corner: A material mark or point usually placed on a property or survey line, at a known distance from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

4.	Reference Monument: A material mark or point placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

- Surveyor: The Contractor’s Professional Land Surveyor, currently registered in the State of Alaska.

642-2.01 MATERIALS.

1.	Monument Cases. Castings shall conform to AASHTO M 105, Class 30A. Castings shall be coated with a bituminous damp-proof coating. The tops shall bear evenly on the frames.

- Primary Monument: A minimum 50 mm diameter nonferrous pipe at least 750 mm long, with a minimum 100 mm flange at the bottom and having magnets attached at the top and bottom. A minimum 60 mm diameter nonferrous metal cap must be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments which will be oriented so as to be read facing up-station.

3.	Secondary Monument: A minimum 15 mm x 750 mm rebar with a 50 mm aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL. Use competent, qualified personnel and suitable equipment for the layout work required and furnish all traffic control, stakes, templates, straight-edges and other devices necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish such computer services as necessary to accomplish the work. Check all data received from the computer for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver all field books, computer forms and computer output data to the Engineer. This data shall become the property of the Department.

Supervise construction surveying personnel. Correct any errors resulting from the operations of said personnel at Contractor expense . The Contractor is responsible for the accuracy of the work.

Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or under the responsible charge of a Professional Land Surveyor.

Follow the Department’s Construction Surveying Requirements (Metric).

Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with Departmental procedures, including titles, numbering, and indexing. Make field books available for inspection by the Department’s project personnel at any time. Store the field books in the Department’s Project Office During periods of non-use.

Perform the following:

- staking necessary to delineate clearing and/or grubbing limits

2.	cross sections necessary for determination of excavation and embankment quantities, including intermediate and/or remeasure cross sections as needed

3.	slope staking

- staking of signs, culverts, minor drainage structures and other appurtenances, including the necessary checking to establish the proper location and grade to best fit the conditions on site

5.	bridge staking

- the setting of such finishing stakes as may be required

7.	the measurement of pay quantities that require measurement

- the staking of right-of-way and material source limits when it is deemed necessary

9.	the staking, referencing and other actions as may be required to preserve or restore land monuments and property corners

- and all other surveying and staking necessary to complete the project

When the right-of-way centerline points have been established as a part of the Department’s Preconstruction surveys, the Department will furnish the Contractor with copies of the reference field books. Recover these control points and verify these references. Reestablish any missing points from the Department’s references prior to the initiation of clearing, grubbing, or excavation.

When the right-of-way centerline points have not been established by the Department but the survey control points were established as a part of the Department’s Preconstruction surveys (as detailed on the project Survey Control Sheet) recover these points and use them as the basis for establishing the right-of-way centerline. Verify the position of these points and establish new points where required to replace missing points, prior to the initiation of clearing, grubbing, or excavation.

Notify the Engineer immediately if a Department-established reference point is discovered to be in error or a reset point is not in harmonious relationship to the adjacent centerline points.

Furnish a notekeeper to record all field survey notes, including those which become documentation from which quantities for payment are computed. The notekeeper shall be thoroughly familiar with generally accepted standards of good survey notekeeping practice and the Department’s Construction Surveying Requirements (Metric).

The Engineer may randomly spot check the Contractor's surveys, staking and computations. After the survey or staking has been completed, provide the Engineer with a minimum of 72 hours notice prior to performing any work, and furnish the appropriate data as required, to allow for such random spot checking. The Department assumes no responsibility for the accuracy of the work.

642-3.02 CROSS-SECTION SURVEYS. When required, obtain right-angle cross sections to the construction centerline at the interval detailed in the Department’s “Construction Surveying Requirements (Metric)”.

The following shall be supplied by the Department:

1.	One set of Construction Plans and Specifications.

- Field Books (Level, Cross-Section, Slope Stake, etc. ). Books will be labeled and the pages numbered by the Department. Field books shall remain the property of the Department upon completion of the work.

3.	Design Cross Sections, if any.

- Sufficient centerline or reference thereto, and at least one benchmark per kilometer to enable the establishment of planned elevations and centerline.

5.	State of Alaska Land Survey Monument Record forms. These forms are to be completed by the Contractor.

- One copy of the Department’s Construction Surveying Requirements (Metric).

7.	Design centerline grades, except when Item 642(2), Office Engineering is used.

The following shall be required of the Contractor:

- A heading in the appropriate book (date, weather, names and duties of crew members) shall be made at the beginning of each day's work.

2.	The notekeeper shall update the index of the appropriate book at the end of each day's work.

- Level notes shall be reduced, checked and adjusted.

4.	Cross-section level notes and slope stake catches shall be computed by the notekeeper and checked by a different crew member in the field on a continual basis.

- The Contractor shall enter the grade data, shoulder width and/or ditch distance, stationing, slope, etc., in the slope stake books.

6.	The position and identifying marks of slope stakes and reference points shall be maintained until used for their intended purpose.

- Errors shall have a line drawn through them with the correct entry made directly above. Erasures will not be allowed.

8.	Field books or copies of the field books shall be returned to the Project office at the end of each work day or as directed.

- The Contractor shall provide copies of all grade sheets and temporary bench mark elevations to the Engineer 48 hours before commencing work on unclassified excavation or embankment.

10.	The Contractor’s survey crews shall comply with all approved traffic control plans. Crews shall coordinate their activities with the Contractor’s Worksite Traffic Supervisor.

- A survey Party Chief diary shall be kept daily and contain the following information, (a copy shall be given to the Engineer daily):

a.	Date.

b.	Weather.

c.	Crew members’ names and duties.

d. 	Type and location of work performed.

e. 	Hours worked.

f.	Type of equipment used (brand) and date equipment was double centered or “peg” test was performed.

g.	 Signature of person in responsible charge.

- The Contractor shall submit the survey field notes, for any specific area, relating to monument referencing prior to any initiation of clearing, grubbing or excavation.

642-3.03 MONUMENTS. Install primary and secondary monuments, as called for in the plans, at the positions established by the Department. Reference all monuments, property markers/corners, or accessories which may be disturbed or buried during construction, and re-establish them in their original position prior to the completion of the project. Keep such records and report to the Engineer evidence that a monument has been disturbed and is no longer reliable or cannot be located and is presumed to be missing. The referencing work shall consist of a minimum of two in-line reference points, or three swing-tie reference points in situations where in-line referencing is not desirable. Set all reference points outside of the construction limits. Measure distances from the monument to the nearest l mm. Record all referencing of monuments in a separate field book stamped by the Surveyor.

Replace all existing monuments disturbed by construction with Primary or Secondary Monuments meeting the requirements of Subsection 642-1.02. When it is impractical to establish a monument in its original position, install a witness corner (WC). Place the WC to a property corner on the property line when the other property corner which defines said line is existing or there has been sufficient retracement to define said line. In other cases, place a reference monument (RM) perpendicular to the centerline at the station of the original position and at a distance from the original position measured in whole meters.

Those monuments found that are not shown on the plans will be recognized by the Engineer when the following is provided by the Surveyor: Field notes identifying type and location of the monument, and a description of the point the monument marks, with the reason to preserve its location. Monuments not shown on the plans will be considered additional work and paid by 642(3), Three Person Survey Party.

The Surveyor shall complete a State of Alaska Land Survey Monument Record form for each primary and secondary monument installed, relocated or replaced. In addition to the required survey information, including section, township and range, each record shall meet all requirements for recording at the District Recorder’s Office in which the project is located. Deliver these forms to the Engineer prior to project completion. The Department will file all original records as required by current State Statutes using the information provided by the Contractor.

Set each monument and monument case accurately to lines established at the required location and in such a manner as to insure its being held firmly in place. Set existing monuments and monument cases to be adjusted to new elevations in the manner and at the elevations directed.

Monument cases in paved areas shall be set within a tolerance of six to ten millimeters (6-10 mm) below the final asphalt grade.

642-3.03 OFFICE ENGINEERING. Calculate finish grades for the roadway as specified per plans and/or specifications. Use information available in the field, on as-builts, or as provided by the Engineer. This work shall be performed by or under the responsible charge of a Professional Land Surveyor or a Professional Engineer currently Registered in the State of Alaska.

642-3.04 FINAL TRAVERSE. Within 30 days after the Engineer receives from the Contractor a letter which states that all construction activities that may disturb the monuments have ceased, the Surveyor shall run a final traverse to verify the positional accuracy of installed survey monuments. This traverse will begin and end at different Department provided control points. The primary and secondary monuments placed or replaced and any undisturbed department provided control points shall be tied to the traverse. Under no circumstance shall the final traverse run more than 4 km without a tie to a department provided monument/control point. All traverse points established during this work shall meet the requirements of a secondary monument. The Surveyor shall sign and stamp a letter which lists each monument and its coordinates. The letter shall certify that the monuments are each located within 50 mm of their proposed position based on the project survey control points provided by the Department. Deliver the certification letter and field notes for this work to the Engineer.

642-4.01 METHOD OF MEASUREMENT.  Item 642(1) Construction Surveying. No measurement of quantities will be made.  Office Engineering required to complete Construction Surveying shall be subsidiary to Item 642(1) and no separate measurement shall be made.  Referencing Existing Monuments shall be subsidiary to other work items and no separate measurement shall be made.

Item 642(3) Three Person Survey Party. By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed.

Items 642(4). The actual number of monuments installed as shown on the “State of Alaska Land Survey Monument Record” forms delivered to and accepted by the Engineer.  642(10) & 642(11). The actual number of monument cases furnished & installed or adjusted, and accepted in place.

642(12) Final Traverse. No measurement of quantities will be made.

Calculations of all pay quantities will be performed by Department personnel.

642-5.01 BASIS OF PAYMENT. Construction Surveying and Final Traverse shall include all field and office work required to accomplish the work, including furnishing all necessary personnel, equipment, transportation and supplies. Payment for Final Traverse is based on the Engineer’s acceptance of the Surveyor’s certification letter and field notes.

Payment for Item 642(3) shall be by contingent sum at $190.00/hour.  If staking for extra, additional or unanticipated work, as stated above, is performed by a two person survey party, payment will be made at 75 percent of the unit price under Item 642(3), Three Person Survey Party. If a single person is required for additional office computations or other work requiring only one person, payment will be made at 32 percent of the unit price of Item 642(3).

Traffic control devices necessary for the survey parties will be considered subsidiary. Payment for Traffic Control Plans as approved will be paid under Section 643, Traffic Maintenance.

The accepted quantities will be paid for at the contract price, per unit of measurement for each of the particular pay items shown in the bid schedule.

Pay Item No.	Pay Item	Unit

642(1)	Construction Surveying	Lump Sum

642(3)	Three Person Survey Party	Contingent Sum

642(4)	Set Primary Monument	Each

642(10)	Monument Case	Each

642(11)	Adjust Existing Monument Case	Each

642(12)	Final Traverse	Lump Sum

R214M

Delete Section 643 in its entirety and substitute the following:

SECTION 643

TRAFFIC MAINTENANCE

643-1.01 DESCRIPTION. This work consists of the necessary measures to protect and control traffic during the life of the contract including, but not limited to, furnishing, erecting, maintaining, replacing, cleaning, moving and removing the traffic control devices required to insure the safety of the traveling public and all administrative responsibilities necessary to implement this work.

The Contractor shall maintain all roadways and pedestrian and bicycle facilities affected by the work and shall construct and maintain approaches, crossings, intersections and other features as may be necessary throughout the life of the contract.

643-1.02 DEFINITIONS.

Construction Phasing Plan - A plan for each phase of the project showing how traffic will be accommodated. It should show the sequence of work by segment or phase if required.

Traffic - The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, incident zones or similar operations.

Traffic Control Plan - A Traffic Control Plan (TCP) is a drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. It depicts the traffic control devices to be used, their placement and times of use.

Traffic Control Zone - A portion of a road construction project, maintenance operation, utility work, incident zone or similar operation where traffic is affected by the operation and traffic control is needed to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. The TCP may include, but not be limited to, such items as signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary roadways and all other items required to direct traffic through or around the construction zone in accordance with these specifications and the Alaska Traffic Manual (ATM). The TCPs shall also address placement of traffic control devices including location, size, mounting height and type. The details shown for signs shall include the code designation, size, and legend per the ATM and the Alaska Sign Design Specifications (ASDS). Plan sheets developed on AutoCADTM can be made available, upon request, for use in preparing TCPs.

When a TCP is included in the plans the Contractor may use it, modify it or design an alternative TCP. Any modifications to the TCP or any new TCP shall be submitted for approval of the Engineer. The Contractor shall allow 1 week for review of any TCP or each subsequent correction. Changes in the TCP may be allowed during construction provided 48 hours are allowed for review and the changes are approved by the Engineer.

When a TCP is not included in the plans the Contractor shall provide one in accordance with this Section and the ATM. The Contractor's superintendent shall review and sign all TCPs prior to submittal. Acceptance of a TCP is based on the Contractor's certification that the plan is in conformance with the ATM and the specifications.

All TCPs submitted shall indicate the periods for which the TCP will be in effect. Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

When a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements is in effect for this project, all movements of oversize and overweight vehicles in or near traffic within the project limits will be in accordance with the provisions of the approved TCP. The TCP shall specify traffic control devices that will be required for these operations.

There shall be no work within the project limits until the Contractor has implemented an approved TCP for the work proposed. The number of traffic control devices indicated on the TCPs, plans, and Standard Drawings are a minimum. If unsafe conditions occur, the Engineer may require additional traffic control devices.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. The Contractor shall provide a Worksite Traffic Supervisor who shall be responsible for the Contractor's maintenance of traffic operations on a 24-hour basis.

1.	Qualifications. The Worksite Traffic Supervisor shall understand the requirements of the ATM, the plans and the specifications and meet at least one of the following:

a.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA).

b.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Markings Specialist by the International Municipal Signal Association (IMSA).

c.	Be currently certified as a Worksite Traffic Technician by (ATSSA).

Items b and c require documentation of a minimum of twelve months of supervisory level worksite traffic control or twelve months of responsible charge of such work. "Responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system. Having persons that actually perform labor under one's control would satisfy this requirement.

2.	Duties. The Worksite Traffic Supervisor's duties shall include the following:

a.	Prepare the TCPs and public notices and coordinate traffic control operations with the Engineer.

b.	Inspect the condition and position of all traffic control devices in use on the project at least once each day and once each night, to ensure that devices are in proper working order, clean, visible and conform to the approved TCPs in use. Furnish a detailed written report of each inspection to the Engineer within 24 hours.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate appropriate traffic control needs and ensure that the proper traffic control devices necessary for safe and efficient traffic movement are available.

e.	Review work areas, storage of equipment, and handling and storage of materials relative to traffic safety.

f.	Hold traffic safety meetings with the superintendents and foremen of the Contractor and subcontractors prior to beginning construction, and periodically thereafter as necessary or as directed by the Engineer. The Engineer shall be provided the opportunity to attend these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all of the flaggers meet the requirements of Subsection 643-3.04.

643-1.05 CONSTRUCTION PHASING PLAN. A Construction Phasing Plan shall be submitted at least 5 working days prior to the Preconstruction Conference for approval by the Engineer and consist of the following:

1.	Designation of a Worksite Traffic Supervisor including his resume, written verification of his credentials and the telephone numbers where he can be reached 24-hours a day.

2.	A plan for each phase or segment of the project, possibly divided into segments showing how traffic will be accommodated. The Construction Phasing Plan will show the sequence of work by segment or phase as necessary.  Changes shall be submitted to the Engineer for approval 15 days in advance of their proposed implementation.

3.	TCPs for the first phase of the project with both the permanent and temporary traffic control measures shown including the times of use of each TCP.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setups are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to safely and efficiently route traffic when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a construction zone.

3.	Road Closure. The closure of a roadway with or without a detour route specified.

4.	One Lane Road. The reduction of a two-way roadway to a single lane roadway with flaggers or pilot cars.

Each setup shall include all items required, but not be limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement marking and all other items necessary to direct traffic through or around the construction zone in accordance with these specification and the ATM.

643-2.01 MATERIALS. Materials for traffic control devices shall conform to the requirements set forth below:

1.	Signs. Permanent Construction Signs, Construction Signs and Special Construction Signs including sign supports shall conform to the requirement of Section 615, Standard Signs, the ATM and ASDS. The size of each Special Construction Sign shall be clearly and neatly marked in 75 mm high black numerals on its back.

2.	Portable Sign Supports. Portable sign supports shall be wind resistant with no external ballasting and capable of supporting a 1.2 m X 1.2 m traffic control sign such that the height of the sign above the adjacent roadway surface is that required by the ATM. The sign support shall support the traffic control sign vertically.

3.	Barricades and Vertical Panels. Barricades and vertical panels shall be constructed of wood, metal or plastic and conform to the requirements of the ATM and the Standard Drawings. Type III Barricades shall have a minimum length of 2.4 m.

4.	Portable Concrete Barriers. Portable concrete barriers shall conform to the requirements of Standard Drawing G-45. Each barrier shall be equipped with at least two side-mounted retroreflective reflectors (or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm from the top of the barrier), for each direction of traffic. The reflectors (or tape) shall be yellow if the barriers are used at centerline and white if used on the roadway shoulder.

5.	Warning Lights. Warning lights shall be Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) conforming to the requirements of the ATM.

6.	Drums. Drums shall be plastic and conform to the requirements of the ATM and the Standard Drawings.

7.	Traffic Cones. Traffic cones and/or tubular markers shall conform to the requirements of the ATM and the Standard Drawings. The minimum height shall be 710 mm. All cones and tubular markers shall be reflectorized.

8.	Interim Pavement Markings. Interim pavement markings shall be either paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08, preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate. The markings shall be applied in accordance with Section 670 and the manufacturer's recommendations.

9.	High Level Warning Devices. High level warning devices shall conform to the ATM and the Standard Drawings.

10.	Temporary Crash Cushions. Temporary crash cushions shall have been tested as per the procedures set forth in National Cooperative Highway Research Program (NCHRP) Report 350, Test Level 3. Certification shall be provided by the manufacturer directly to the Engineer. Permanent crash cushions shall not be used as temporary crash cushions.

11.	Sequential Arrow Panels. Sequential arrow panels shall be Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) conforming to the requirement of the ATM and the Standard Drawings.

12.	Portable Changeable Message Board Signs. Portable changeable message board signs shall conform to the requirements of the ATM.

13.	Plastic safety fence shall be construction orange, 1.2 m high and shall be as manufactured by one of the following companies, or approved equal:

a.	“Safety Fence” as manufactured by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” as manufactured by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” as manufactured by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. This item shall consist of providing all labor, equipment and materials to provide a temporary sidewalk surfacing as required by an approved Traffic Control Plan and in accordance with sheet H12 of the plans. This work is incidental to Item 643(2) Traffic Maintenance.

a.	The materials shall be a minimum of 12 mm plywood for areas that are continuously supported by subgrade and 25 mm plywood for areas that are not continuously supported.

b.	The maximum unsupported length of 25 mm plywood shall be 750 mm.

c.	The surface of the plywood shall be free of irregularities. The height of plywood overlap joints shall not exceed 12 mm.

d.	The temporary surfacing shall be held in place by a method that will withstand 40 kph wind velocities.

15.	Temporary Guardrail. Temporary Guardrail shall conform to the standard drawings and section 606 of the standard specifications.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. The Contractor shall keep the work, and portions of the project affected by the work, in such condition that traffic will be accommodated safely. Traffic control devices and services shall be provided and maintained both inside and outside the project limits both day and night as needed to facilitate traffic guidance.

Unless otherwise provided herein, the Contractor shall keep all roadways undergoing improvement open to traffic. Temporary closure of residential, commercial or street approaches requires prior

approval of the Engineer. The Contractor shall provide access through the project for emergency vehicles and school and transit busses. All locations requiring redirection or stopping of the traveling public shall be properly signed and/or flagged by the Contractor.

The Contractor's equipment shall stop at all points of intersection with the traveling public unless satisfactory traffic control measures, are shown on the approved TCP.

All illumination and signalization shall remain operational as per the requirements of Subsection 660-1.05, Maintaining Existing and Temporary Electrical Systems. Signal heads shall be re-aligned as necessary in accordance with the ATM when approach lanes are moved. Any modifications to existing traffic signals shall be coordinated with the agency responsible for their maintenance and operation. Flood lighting at night shall be in accordance with the ATM and be adjusted such that it does not shine into oncoming traffic.

The Contractor shall provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times except when pedestrians or bicyclists are prohibited by regulation. Whenever construction activity encroaches onto the safe route in a traffic control zone the Contractor shall station an employee at the encroachment to assist pedestrians and bicyclists past the construction activity.

The safe route for pedestrians in a traffic control zone should be clearly marked with thraffic control devices.  Typical traffic controls for pedestrian are shown on the plans.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Roadway lane and shoulder widths in existence prior to the start of construction shall not be reduced without an approved TCP The Contractor shall maintain a 0.6 m minimum clear area between the edge of traveled way and the work area. Use either barricades, traffic cones, or drums for delineation of this area. These traffic control devices shall be placed on the work side of the clear area and be spaced in accordance with the ATM.

If the Contractor is allowed to maintain traffic on an unpaved surface, the construction shall be conducted in such a manner as to provide a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage. In advance of other grading operations, sufficient fill shall be placed at culverts and bridges to permit traffic to cross smoothly and unimpeded. Part width construction techniques shall be employed when the traffic is routed through roadway cuts or over embankments under construction. The material shall be excavated or placed in layers and the construction activities shall be alternated from one side to the other, with traffic routed over the side opposite the one under construction.

Where so provided on the plans or an approved TCP, the Contractor may detour traffic. The detour routes shall be maintained by the Contractor during times of use in such condition that traffic will be accommodated safely. When no longer required, the detour shall be obliterated and appropriate areas topsoiled and seeded.

In general, all roadway crossings should be made while maintaining traffic as described above. If two-way traffic cannot be maintained, whether on the existing roadway or a detour, half-width construction or a road closure may be allowed and must be shown on an approved TCP. The TCP shall indicate the duration and conditions of closure. Roadway crossings shall be scheduled so as not to delay school busses and peak hour traffic. For road closures the Contractor shall post at the site of the closure, within view of waiting traffic, the time the closure started and the time the road will again be open to traffic.

643-3.03 PUBLIC NOTICE. The Worksite Traffic Supervisor shall give notices of changes, delays or road closures to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska State Troopers

Local Police Department

Local Fire Department

Local School & Transit Authorities

Local Emergency Medical Services

Local Media (Newspapers, Radio, Television)

Railroads (Where applicable)

U.S. Postal Service

The Contractor shall also provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project, and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These shall be for alerting the Contractor of emergencies which will require passage of emergency vehicles through the project. When so notified the Contractor shall use all equipment and effort necessary to expedite rapid passage.

Open House Meetings.  The following Contractor personnel shall attend monthly open house meetings at the Engineer’s office:

1.	Superintendent

2.	Worksite Traffic Supervisor

The Contractor’s personnel shall be prepared to respond to questions during the open house and be authorized to commit the Contractor to courses of action when needed to resolve problems.

Weekly Notices.  The Contractor shall write and submit weekly public information notices that identify road closures, restrictions to traffic, and detours.  Areas of potential traffic delay shall be emphasized and alternate routes noted.  Telephone numbers for further information and the date and time of the next scheduled open house meeting shall be provided.  The Contractor shall redraft notices until approved by the Engineer.  Approved notices shall be hand-carried or faxed to the list of local news broadcasting media, emergency services and public service organizations provided by the Department.  Notices shall be submitted at the following times:

1.	One week prior to the beginning of construction,

2.	Wednesday of each week during construction, and

3.	Prior to any major change or disruption to traffic or local access.

The Contractor shall provide daily updates of the weekly notices to those news broadcasting media which provide non-paid public service road reports or “eye in the sky” road reporting.

643-3.04 TRAFFIC CONTROL DEVICES. Prior to the start of construction operations, the Contractor shall erect such permanent and temporary traffic control devices as may be required by the approved TCPs. Traffic control devices shall be used only when they are needed. Advisory speeds, when necessary, shall be determined by the Engineer.

For lane closures on multilane roadways, sequential arrow panels shall be used. When required for night time operations, flashing warning lights shall be used to mark obstructions or hazards and steady-burn lights shall be used for channelization.

During non-working hours and following the completion of a particular construction operation, all unnecessary traffic control devices shall be removed. Sign panels that are post mounted and cannot be readily removed shall be entirely covered with either metal or plywood sheeting.

Reflective sheeting on signs, drums, barricades and other devices shall be kept clean.

All traffic control devices shall meet the requirements of American Traffic Safety Services Association (ATSSA), "Quality Standard for Work Zone Traffic Control Devices".

Any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while their use is required on the project shall be immediately replaced by the Contractor. The Contractor shall stock repair parts for each Temporary Crash Cushion used on the project. If a crash cushion is damaged it shall be repaired within 24 hours.

All items paid for under this section shall remain the property of the Contractor and shall be removed upon completion of the project.

1.	Embankments. Install portable concrete barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as called for on the plans or TCPs to delineate open trenches, ditches, other excavations and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. The Contractor shall limit pavement edge and lane edge drop-offs as specified under Subsection 401-3.11. When the depth of paving is greater than 50 mm and the paving of adjacent travel lanes or paved shoulders cannot for some unforeseen circumstance be completed to the same elevation before the end of the paving shift, the appropriate signing shall be installed: CW24-1, (Uneven Lanes), CW8-9A, (Low Shoulder), CW14-3, (No Passing Zone), R4-1, (Do Not Pass), and R4-2, (Pass with Care). If the section in question is longer than 800 m in length additional signs shall be placed at 460 m intervals.

3.	Fixed Objects. Vehicles working within 4.6 m of the edge of traveled way shall be equipped with flashing warning lights. The vehicle's flashing warning lights may be emergency flashers, flashing strobes or rotating beacons.

Private vehicles, idle construction equipment, construction material stockpiles and other items deemed by the Engineer to be fixed objects shall be located outside the clear zone at all times. Parking of equipment in medians will not be allowed.

Where, due to land features or lack of right-of-way, it is not feasible to meet the above restrictions, equipment shall be parked as far away as practical but a minimum of 4.6 m from the edge of traveled way as approved by the Engineer. Traffic control devices for identifying hazards including flashing warning lights shall be used to delineate the equipment when parked in this manner. These traffic control devices will not be paid for but will be considered the Contractor's responsibility.

4.	Flagging. Flagging shall include the furnishing of trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, for the control of traffic through the work zone. Each flagging operation shall be approved by the Engineer prior to its implementation and shall be adjusted as conditions change or as directed by the Engineer

Prior to beginning work, and at the start of each construction season thereafter, flaggers shall attend the special videotape training session provided by the Engineer. The Worksite Traffic Supervisor shall certify in writing that all flaggers are personally familiar with and meet the requirements of the ATM and have attended the annual training before being allowed to direct traffic.

Flaggers shall maintain their assigned posts at all times, unless relieved by another qualified flagger or the need for flagging traffic no longer exists. Flagger signs are to be removed when a flagger is not present. The flaggers area should be free of encumbrances, such as parked vehicles, so the flaggers are readily visible.

The Contractor shall provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

No signalized intersection shall be flagged without prior written approval of the Engineer. When a signalized intersection is flagged the traffic signal shall either be turned off and covered or be placed in the All-Red Flash mode. Changing traffic signal modes, turning off or turning on traffic signals, shall be coordinated with and approved in writing by the agency responsible for signal maintenance and operation, and by the Engineer.

5.	Pilot Cars. Pilot car operations may be approved where the route through a construction work zone is particularly hazardous, so involved or frequently altered as to preclude adequate signing, or where one-way traffic is deemed by the Engineer to be necessary. Pilot cars shall not be used to avoid localized traffic control at several locations. The operation shall be organized so that no individual vehicle has a waiting period of more than 20 minutes, but this does not imply that twenty minutes will be allowed in all cases. Multiple pilot car operations within a project or adjoining projects shall be coordinated to minimize the inconvenience of the traveling public. Two or more pilot cars may be specified to provide two-way traffic through the work zone to reduce the waiting period. The flagger or pilot car operator shall record each departure time of the pilot car in a bound field book furnished by the Engineer. Whenever practicable, the flagger shall advise the motorist of the reason for the delay and the approximate length of time that the traffic will be delayed. The Contractor must make every reasonable effort to yield right-of-way to the driving public and prevent excessive delay. The vehicle selected for a pilot car shall be an automobile or pickup with the name of the Contractor prominently displayed and shall be equipped with a two-way radio for contact between flaggers and other pilot cars. A G20-4 sign, (Pilot Car Follow Me), shall be mounted on the rear a minimum height of 1.5 m above the driving surface. Provisions shall be made for identification of the last vehicle in the column.

When pilot cars are authorized, they shall be in force prior to beginning work and continue until no longer required or all traffic control devices required for non-working hours are properly in place and functioning.

6.	Street Sweeping. All paved portions of the roadway and haul routes open to the public shall be kept free of loose material, including sections of roadway off of the project where loose material is deposited as a result of the contractors operations. The street sweeper shall be capable of collecting materials rather than ejecting them to the shoulder of the road.

7.	Watering. The Contractor shall furnish, haul and place water for dust control and pavement flushing, as directed. Water trucks shall be capable of providing a high pressure water stream to flush the pavement and a light water spray for dust control. If the flushing operations contaminate or fill adjacent catch basins the contractor shall clean and restore them to the same condition they were in prior to his operations, including sections of roadway off of the project where flushing is required. The application of water shall be under control of the Engineer.

If water is to be taken from a lake, stream, or other natural water body, the Contractor shall obtain a water removal permit from Alaska Department of Natural Resources. The Contractor shall also comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

643-3.05 AUTHORITY OF THE ENGINEER. When, in the opinion of the Engineer, conditions are such that the safety and/or convenience of the traveling public are adversely affected, the Contractor will be immediately notified in writing. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). In no case shall this time exceed 24 hours. In the event that the Contractor fails to take the corrective action(s) within the specified time, (a) The Engineer will immediately direct that the offending operations cease until the defect(s) is (are) corrected and (b) the Engineer reserves the right to order the corrective action(s) be accomplished by outside forces. The cost of work by outside forces shall be deducted from any moneys due or that may become due under the terms of this contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. When Item 643(23), Traffic Price Adjustment, is shown on the bid schedule, for each minute that any lane of traffic is not open to full use by the traveling public, the Contractor will have payment for this contract reduced at the rate listed below (based on highway user costs), measured to the nearest minute for the ADT published by the Department's Planning section. The Engineer shall determine whether the roadway is opened to full use.

The Traffic Price Adjustment shall be assessed for lane closures or reductions that are unauthorized. Lane closures and/or lane reductions that have been shown in the contract or authorized in writing by the Engineer are not subject to the Traffic Price Adjustment.

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| Less than 1,000 | $2 |
| 1,000 - 4,999 | $10 |
| 5,000 - 9,999 | $30 |
| 10,000+ | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month prior to seasonal suspension of work, the Contractor shall schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the work he expects to complete before shutdown and the condition the roadway is to be in. The Contractor shall then schedule a field review for acceptance by the Department for winter maintenance. At the field review a punch list will be prepared for implementation prior to acceptance. In order for the Contractor to be relieved of winter maintenance responsibility, all roads shall be left with a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage and adequate safety facilities shall be in place. All illumination and signals, including vehicle detectors, shall be in good working order. After acceptance for winter maintenance and until issuance of an order for the resumption of construction operations, maintenance of the facility agreed upon will be the responsibility of the Department. The Department will only accept maintenance responsibility for those portions of the work that are open to the public for use, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. Maintenance for all other portions of the work, shall remain the responsibility of the Contractor. The Engineer will list all portions of the work for which the Department will accept maintenance responsibility during a seasonal suspension of work in a letter of "Acceptance for Winter Maintenance." The Contractor shall retain all contractually required maintenance responsibilities until receipt of this letter.

If work is suspended due to unfavorable weather, other than seasonal, failure of the Contractor to correct conditions unsafe for the workmen or the general public, failure to carry out provisions of the contract, or for failure to carry out orders of the Engineer, all costs for maintenance of traffic during the suspended period shall be borne by the Contractor.

When work is resumed, the Contractor shall replace or renew any work or materials lost or damaged because of temporary use of the project. Remove to the extent directed by the Engineer, any work or materials used in the temporary maintenance and shall complete the project as though its prosecution had been continuous and without interference.

643-3.08 CONSTRUCTION SEQUENCING. Construction sequencing detailed in these provisions, the Special Provisions, and the plans is a suggestion only and is not intended to prevent the Contractor from proposing alternative construction sequencing.

Throughout the duration of the project, the existing roadway configuration shall be maintained (i.e., the number of lanes and their respective widths) except for restrictions to traffic allowed in the special provisions and addressed through approved TCPs. A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or stops traffic. An approved TCP is required before any restriction to traffic is implemented.

No restriction to traffic will be allowed during the times listed in the special provisions.

The Contractor shall maintain at least two lanes of through traffic in each mainline direction at all times, with the following exceptions:

- Complete closure of the following major intersections will be permitted:

1.	Benson Blvd and Northern Lights Blvd and the northbound New Seward Highway between those intersections.

2.	Benson Blvd and Northern Lights Blvd and the southbound New Seward Highway between those intersections.

3.	Fireweed Land at northbound Seward Highway and the northbound Seward Highway from Northern Lights Blvd to Fireweed Lane.

4.	Fireweed Land at southbound Seward Highway and the southbound Seward Highway from Northern Lights Blvd to Fireweed Lane.

5.	15th Avenue and 13th Avenue at Gambell Street.

6.	15th Avenue and 13th Avenue at Ingra Street.

7.	9th Avenue at Gambell Street.

8.	9th Avenue at Ingra Street.

9.	6th Avenue at Gambell Street.

10.	6th Avenue at Ingra Street.

These closures will be contingent upon meeting the following restrictions:

a.	Closure times shall only extend from 10:00 PM Friday to 6:00 AM of the following Monday.

b.	Nighttime construction operations will be permitted if the Contractor can obtain a noise ordinance waiver as outlined in the Anchorage Noise Control Ordinance, Title 21, Chapter 15.70.

c.	Closure of more than one intersection during the same weekend will only be permitted with the approval of the Engineer, and the work must be accomplished with no overlap or conflict in the detour routes of each intersection.

d.	It is the intent of full closure permission to complete all paving and striping operations within each intersection during the single closure period.

- Closure of all minor intersecting side streets is permitted during the period of active construction work on the mainline at each intersection.  Such closures will require adequate advance notice, and appropriate construction signing and barricades for a full street closure.  The Contractor shall open the side street to through traffic at the earliest opportunity.

- Three areas: 1) the Seward Highway northbound and southbound from 36th Avenue to immediately south of the Benson Blvd intersection, 2) Gambell Street from Fireweed Lane to immediately south of 15th Avenue, and 3) Ingra Street from Fireweed Lane to immediately south of 15th Avenue, can be constructed with the initial work area of two lanes wide so that traffic may use a single wide lane per the TCP.

643-3.09 INTERIM PAVEMENT MARKINGS. Permanent or Interim Pavement Markings in accordance with this subsection, details shown on the plans, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift. This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal or covered with black removable preformed marking tape.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings unless otherwise shown on the plans, an approved traffic control plan, or as directed by the Engineer.

The Contractor shall maintain all Interim Pavement Markings for their intended life without additional compensation for any reapplication that may be required. There will be no compensation to upgrade Interim Pavement Markings required for work operations lasting up to 3 days to those required for work operations lasting up to 2 weeks.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Interim Pavement Markings on final pavement surfaces. When used they shall be completely removed and disposed of in conjunction with the placement of the final markings. The complete removal shall include any residual adhesive that might misguide motorists. Final pavement markings on finished pavement surfaces and interim pavement surfaces shall be in place before work is suspended for the winter.

Construction should be staged so that no traffic is routed over conflicting markings for more than one continuous workshift. If traffic is routed over conflicting markings during a workshift the roadway shall be delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.

Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for interim pavement markings on seal coat and surface treatment pavements. The markers shall be installed in accordance with the manufacturers instructions prior to the application of the asphalt surface material and cover coat. The vinyl protective covers shall be removed after application of the asphalt pavement.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat. The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment.

643-4.01 METHOD OF MEASUREMENT. During winter suspension of work no measurement of quantities will be made.

1.	Traffic Maintenance will be measured by the calendar day or lump sum and shall consist of all labor, materials and equipment required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan and maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required. This item will also include any Traffic Control Devices 643(3) through 643(22) required but not shown on the bid schedule.

2.	Traffic Control Device items will be measured by the units shown on the bid schedule or the Traffic Control Rate Schedule, if item 643(25), Traffic Control is included. The quantities to be paid for shall be the number of units of each of the bid items, installed and accepted, are in place. Construction Signs are regulatory, guide or construction warning signs for which there is a designation in the ASDS. Permanent Construction Signing shall be as detailed in the plans. All other signs will be considered Special Construction Signs. Flagger paddles will not be measured for payment.

Warning lights, high level warning devices, vertical panels and sign supports required for individual traffic control devices will be considered subsidiary to their respective bid item. If a subsidiary item is not installed and operational on a traffic control device when required, the respective device will not be measured for payment.

3.	Traffic Maintenance Setup items, when shown on the bid schedule, will be measured by the units shown in the bid schedule for lane closures, detours, road closures and one lane roads. Each setup shall consist of all traffic control devices, flaggers, pilot cars and subsidiary items necessary to implement the particular TCP shown on the plans. The quantities to be paid for shall be the number of hours or days that the setups, installed and accepted, are in place.

Warning lights, high level warning devices, vertical panels and sign supports required for a particular traffic maintenance setup will not be measured separately but will be considered included in the setup item.

If alterations to a traffic maintenance setup are required during construction, the cost for the setup will be modified by adding or deleting the required number of traffic control devices per their respective unit bid prices or unit rate as shown in the Traffic Control Rate Schedule, if item 643(25), Traffic Control is used.

When the proposal contains a traffic maintenance setup item which requires the construction and obliteration of temporary roadways, payment for such items will be made under their respective roadway pay items.

4.	Portable Concrete Barrier will be measured per each nominal 3 m section placed to protect or channelize traffic as called for on the approved TCPs. Measurement for placement will be made for the initial placement and for each subsequent relocation when moved more than 3 m in any direction.

5.	Temporary Crash Cushions will be measured per each installation. Repair of temporary crash cushions will not be measured.

6.	Interim Pavement Markings will be measured by the single stripe station. A single stripe is a marking or a temporary raised pavement marker 100 mm in width. Wider striping will be measured as multiples of 100 mm. Centerline gaps will not be deducted from measurements. Installation of any word and symbol markings as well as the removal of the Interim Pavement Markings will be subsidiary to this item. The No-Passing Zone signing, as described in Subsection 643-3.09, will be subsidiary to this item.

7.	Flagging and Pilot Car will be measured by the hour for the actual number of hours such operations were performed as approved by the Engineer. Transportation to and from the work site will not be measured.

8.	Street Sweeping will be measured by the hour for the actual number of hours such operations were performed as approved by the Engineer. Time required to empty the sweeper will not be measured.

9.	Watering will be measured by the kiloliter of water applied. Weight measure or volume measure may be used at the discretion of the Engineer. If weight measure is used, the weight will be converted to kiloliters at 1.00 megagram per kiloliter for payment purposes. If volume measure is used, the volume will be converted to liters at 1.00 kiloliter per cubic meter for payment purposes.

10.	Portable Changeable Message Board Signs shall be measured by the calendar day for each sign used as shown on an approved TCP.

643-5.01 BASIS OF PAYMENT. The accepted quantities, determined as provided above, will be paid for at the contract price per unit of measurement, respectively, for each of the pay items listed below that are shown in the Bid Schedule, which price and payment shall be full compensation for the work prescribed in this section.

Items required by this specification that are not included on a unit price basis on the Bid Schedule or not included in other items shall be considered subsidiary to Item 643(1) or 643(2) Traffic Maintenance, except the following:

Traffic Price Adjustment

If Item 643(23), Traffic Price Adjustment, is shown on the Bid Schedule the total value of this contract will be adjusted as appropriate for lane restrictions, closures or delays in completing the directed work, as determined by the Engineer.

Payment for Item 643(25), Traffic Control Devices will be made for the pay unit of accepted traffic control devices multiplied by the unit rate value contained in the following rate schedule:

TABLE 643-4

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.50 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 4.00 |
| Sequential Arrow Panel, Type C | Each/Day | $55.00 |
| Portable Concrete Barrier | Meter | $20.00 |
| Pilot Car | Hour | $50.00 |
| Watering | Kiloliter | $5.25 |
| Pedestrian Fence | Meter | $15.00 |
| Portable Changeable Message Board | Calendar Day | $100.00 |
| Temporary Pavement Markings Painted Markings Preformed Markings Raised Pavement Markings Temporary Cover Markings | Station Station Station Station | $984.25 $4265.00 $492.00 $10000.00 |

The bid schedule reflects a contingent sum amount to provide adequate traffic control for the project.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(2)	Traffic Maintenance	Lump Sum

643(3)	Permanent Construction Signs	Lump Sum

643(15)	Flagging	Hour

643(17)	Street Sweeping	Hour

643(23)	Traffic Price Adjustment	Contingent Sum

643(25)	Traffic Control Devices	Contingent Sum

R194M

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

Add the following:

644-2.06 SCALES. Delete the first and second sentences and substitute the following: When the bid schedule calls for payment on a megagram basis for material, the Contractor shall furnish and maintain platform scales, scalehouse, and an electronic computerized weighing system, as hereinafter specified. A permanent certified commercial scale may be used with the Engineer's written approval. Belt conveyor scales are not acceptable for determining pay weight when the contract documents provide for payment on a megagram basis.

Delete the second paragraph and substitute the following: Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following: Furnishing platform scales, tickets, scale house, and the electronic computerized weighing system, including all supplies such as: weigh tickets, paper, printer ribbons, diskettes, etc, and all maintenance and repair services necessary to keep the system functional, shall be supplied by the Contractor and are not a pay item but will be considered a subsidiary obligation. Platform scales, scale house and the electronic computerized weighing system shall remain the property of the Contractor upon completion of the work.

The Scales Diary is a bound book provided by the Engineer, to be completed by the Contractor’s scale person, that contains dates of action, type of material, source, time the scale opened and time the scale closed, times of scale balance, ticket sequence, time the haul for each material started and stopped, voided ticket numbers, truck numbers, times of tare and tare weights, and the scale person’s signature. In addition, the following information on any scale used to weigh materials for payment shall be provided in the Scale Diary:

a.	Owner of the scales, and scale locations.

b.	Manufacturer’s name, model serial number, maximum capacity, and type of scales (single beam, double beam, self-reading, etc).

c.	Date(s) the scales were installed and/or adjusted.

d.	Scale service company inspections and accuracy checks (attach copy).

e.	Division of Weights & Measures inspections and accuracy checks (attach copy).

f.	Time and dates of notification of any malfunctions.

The Scales Diary(ies) shall remain the property of the Engineer.

Delete the second sentence of the last paragraph and substitute the following: Platform scales shall include a weatherproof housing constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the weigh indicator, scale computer, ticket printer, and the printer used to produce the Transaction Summary Report. All components of the platform scales which could be physically manipulated in a manner to alter weights shall be protected by sealed enclosures, acceptable to the Engineer.

Add the following: The Contractor shall provide an electronic computerized weighing system with the following capabilities:

COMPUTER

1.	The scale computer shall have the ability to store project numbers and all pay item descriptions for multiple projects and products which are weighed with the scale system.

The self-reading scale system shall include the scale load cell, a sealed direct reading weight indicator, scale computer, ticket printer, sequential Transaction Summary Report printer, and the ability to record a complete shift's transaction on a 3½-inch high density diskette.

The scale computer shall read the output data from the weight indicator without any unit conversion. If a conversion of pounds to kilograms is necessary, the Transaction Summary printer shall also print the Gross Vehicle Weight of each load in pounds for the Engineer's review of the metric conversion factor. The conversion factor shall be 907.1847 kg/ton. All individual parts of the system shall be compatible with each other and suitable for field conditions.

Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic computerized weighing system.

2.	The scale computer shall store the following for each hauling vehicle utilized on the Project: vehicle identification number or the permanent commercial scales’ assigned unique vehicle identification number if so marked on the vehicle, the tractor license number, associated trailer license number(s) or the permanent commercial scales’ assigned unique vehicle identification number(s) if so marked on the trailer, tare weight, and maximum allowable vehicle weight (MAVW).

Vehicles shall be tared a minimum of once daily by the scale operator. The Engineer may request additional tares to be done at any time the scale is operational. The Engineer may also require that he be present when tares are done.

The MAVW shall be calculated by the Engineer and a listing of all vehicles and their MAVW(s) will be placed in the scalehouse by the Engineer. The MAVW will be the maximum allowable legal weight, as determined by the Engineer when overloads cannot be hauled in the traffic stream; the manufacturer's recommended maximum allowable gross vehicle weight as certified by the Contractor when on-road vehicles are allowed to haul overloads in the traffic stream; or an arbitrary number of 500 Mg when the Engineer allows unrestricted overloads out of the traffic stream.

The scale operator shall only utilize MAVWs which have been provided by the Engineer in writing. No tickets shall be issued to a vehicle until the Engineer provides the MAVW.

3.	During weighing operations, the electronic computerized weighing system shall compare each vehicle's gross weight to its MAVW. If the vehicle exceeds its MAVW the system shall alert the scale operator that an "overload" exists and the system shall not issue a ticket.

No payment will be made for any material hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions, and this Subsection. Non-conforming vehicles shall dump sufficient material so that they conform, and then be reweighed.

4.	The computer system shall have a battery backup as well as protection for power surges or brown outs. The computer system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage to allow shutdown of the hard drive without the loss of information.

TICKETS

The ticket printer furnished by the Contractor shall print a legible weigh ticket for the Engineer on continuous feed 10 kg paper with nominal dimensions of 215 mm by 140 mm, and with the following information on each ticket in the order listed:

a.	Sequential ticket number (8 digits, the first 3 digits being a Project code, the next being a product code [A, B, and C for the borrow classifications, D for Crushed Aggregate Base Course, E for asphalt, etc, as directed by the Engineer], and the last 4 digits being the sequential number for each product).

The permanent commercial scales may use “load number” to count the sequential loads for the Project. The load number shall be the different for each project and product hauled, and shall be reset to “O” at the beginning for each shift.

Whichever is used, this number shall be output to the data diskette given to the Engineer as Field 1, TKT.

b.	Project information (20 digits, the first 5 being the Project AKSAS number, the next 11 for the Project name, and the last 4 for a materials source reference).

c.	Date and Time of Dispatch (24 hour time).

d.	Pay Item name in words with "-Job Total", "-Shift Total", "-Daily Total", or "- Cumulative" Megagrams (Product Total This Ticket Sequence, Starting with "1", in megagrams, with each shift starting with “O”).

e.	Vehicle identification number, license number, and trailer license number(s). The permanent commercial scales may assign a permanently affixed tractor and trailer vehicle identification numbers, and shall maintain a current record of the corresponding license numbers.

f.	MAVW, as provided by the Engineer in writing.

g.	Gross weight in megagrams, rounded to the nearest megagram after conversion.

h.	Tare weight in megagrams, rounded to the nearest megagram after conversion.

I.	Net weight in megagrams, rounded to the nearest megagram after conversion.

All of the above items are to be printed by the ticket printer with a minimum of a 12 point font, and Items b. through c. above shall not be pre-printed. After printing, the weigh ticket shall be automatically advanced to a position where it can be torn off at a perforation and handed to the driver.

TRANSACTION SUMMARY REPORT PRINTER

The electronic computerized weighing system shall include a sequential Transaction Summary Report printer that will print out all transactions (keystrokes) made by the computer concurrently with the ticket printer. For permanent commercial scales, the Transaction Summary Report may be printed at the end of the company's daily shift with the Engineer's approval. The printer shall print all scales transactions including tares, voided tickets, and data changes made by the scale operator. The printer shall allow for the paper to be manually advanced so that the scale operator can write notes on the paper when special situations occur such as voided tickets, incorrect hauling unit number used, etc, which shall also be noted in the Scales Diary as provided under Subsection 109-1.02, Measurement of Quantities.

Transaction Summary Reports will be printed concurrently, or at the end of the shift in the case of a commercial scale if approved by the Engineer. The Report shall include the following information:

a.	Project number (first 5 characters of Field 11, PROJECT).

b.	Date (Field 2, DATE).

c.	Pay item.

d.	Materials source number (last 3 or first 2 characters of Field 10, PRODUCT, at the Engineer’s option).

e.	Sequential ticket number, or load number, at the Engineer’s option.

The sequential weigh ticket number shall be set to "1" at time 0:00 (12:00 pm) or prior to the first load being hauled at the beginning of each shift for each unique project number, pit number, and pay item combination. The project information, date, pay item, hauling unit identification number(s), their MAVW's, and the scale operator's name shall also be able to be set by the scale operator. Tare weights shall only be able to be changed by a tare weighing operation.

DATA DISKETTES

The electronic computerized weigh system shall also provide the Engineer with a 3½-inch high-density diskette at the end of the shift. The disk shall record all ticket information which was produced during the shift.

The data shall be stored in two files with the same information but different formats. The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation. The naming convention for this file shall be "yymmdd.dbf". The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end-of-file-mark following the last record. The naming convention for this file shall be "yymmdd.csv". If more than one scale is used on the Project, a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

If the Contractor is hauling from a permanent commercial scales operation, then the commercial vendor shall download his hard drive directly to a disk without conversion or manipulation at the end of the shift. He shall also provide conversion programs and training so that data can be converted into the information the Engineers requires.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, the Contractor shall correct, construct, or reconstruct the data file utilizing the sequential Transaction Summary Report or other information, as directed by the Engineer, as a data source. No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer. If written permission is obtained from the Engineer to weigh without the electronic computerized weighing system for a minor equipment failure, a data file, acceptable to the Engineer, shall be constructed as described above.

The fields for each record shall be in the following format and order. Other data fields may also be provided but shall follow the fields in the required format.

| Field | Field Name | Type | Width |
| --- | --- | --- | --- |
| 1 | TKT | Character | 4 (right justified w/leading blanks) |
| 2 | DATE | Character | 8 (mm/dd/yy) |
| 3 | TIME | Character | 5 (hh:mm) (24 hour) |
| 4 | UNIT_ID | Character | 5 (right justified w/leading blanks) |
| 5 | MAVW | Numeric | 6 (kilograms) |
| 6 | GROSS | Numeric | 6 (kilograms) |
| 7 | TARE | Numeric | 6 (kilograms) |
| 8 | NET | Numeric | 6 (kilograms) |
| 9 | COMMENTS | Character | 20 |
| 10 | PRODUCT | Character | 20 |
| 11 | PROJECT | Character | 20 |
| 12 | GROSS | Numeric | 6 (pounds) |

The system shall be able to generate the summary Report, either during or at the end of the day or shift, which summarizes the number of loads and total net weight for each Date, Project, and Product. The original of the end of day Report shall be given to the Engineer at the end of each shift.

A user instructional manual shall be available for each scale which explains the complete scale operation. A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities, an amount equal to the value of those expenses will be deducted from the value of the item before payment. (1/9/97)R145M

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-3.07 SHOP TESTS. In the second paragraph, change "6 weeks" to "2 weeks".

Delete the sixth paragraph and replace with the following: Testing subsequent to rejection of the equipment for failure to comply with the plan and specification requirements will be at the expense of the Contractor. Deductions to cover the costs of such testing will be in accordance with Subsection 660-7.01, Basis of Payment.

Add the following subsection:

660-6.09 SIGNAL SYSTEM TIMING AND ADJUSTMENTS. Municipality of Anchorage traffic signal personnel will be utilized to perform certain functions on this project. Functions will consist of temporary timing changes and loop detector and interconnect wiring in existing traffic cabinets.

1.	Timing Adjustments. During the project the Municipality of Anchorage may be required to adjust the system and intersection operational times to accommodate project conditions.

2.	Loop Detector and Interconnect Wiring. The Municipality of Anchorage will test and perform tie down of new detectors and interconnect in existing traffic controller cabinets.

660-7.01  BASIS OF PAYMENT.  Add the following:

Payment for Item 660(3A), Highway Lighting System, East Side, Complete shall include all work required to salvage the existing system, and to complete the total system represented by Luminaire 13 through Luminaire 24, as shown on detail 2, sheet L1 and details 1 & 2, sheet L2 and associated details and standard drawings.  Individual components in this work such as j-boxes, conduit and wire shall not be measured for separate payment.  Any pavement patching required shall be paid according to Item 407(7) Asphalt Concrete Leveling Course, or Item 401(9A), Asphalt Concrete Pavement, Type II, Class A, as directed by the Engineer.

Payment for Item 660(3B), Highway Lighting System, West Side, Complete shall include all work required to salvage the existing system, and to complete the total system represented by Luminaire 1 through Luminaire 10, as shown on details 1 & 2, sheet L1 and associated details and standard drawings.    Individual components in this work such as j-boxes, conduit and wire shall not be measured for separate payment.  Any pavement patching required shall be paid according to Item 407(7) Asphalt Concrete Leveling Course, or Item 401(9A), Asphalt Concrete Pavement, Type II, Class A, as directed by the Engineer.  Delivery of two (2) spare poles and mast arms to the Department’s Maintenance Yard shall be subsidiary to this pay item.

Payment for Item 660(12), Relocate Electrolier, shall include all work required to complete the relocation including salvaging existing components, disposing of abandoned components including the foundations, and reinstalling a complete, working system.    Any pavement patching required shall be paid according to Item 407(7) Asphalt Concrete Leveling Course, or Item 401(9A), Asphalt Concrete Pavement, Type II, Class A, as directed by the Engineer.

Payment for Item 660(14), Traffic Detector Loops, shall include all work required to install each loop, including all materials and work between the loop and the junction box required to connect the loop into a complete, working system.  Removal of all existing loops being replaced shall be subsidiary to this pay item.  The junction box, and the wire and conduit between the junction box and the controller will be paid under separate bid items.  Any pavement patching required shall be paid according to Item 407(7) Asphalt Concrete Leveling Course, or Item 401(9A) as directed by the Engineer.

Payment for Item 660(15), Signal Interconnect System, Complete shall include all work required to complete the total system shown on drawings S5 through S9, inclusive, along with associated details and standard drawings.  Individual components in this work such as j-boxes, conduit and wire shall not be measured for separate payment.

Payment for Item 660(18), Adjust Junction Box, shall include all work required to adjust each junction box to finish grade, regardless of type, wherever encountered on the project, as directed by the Engineer.  Payment will not be made under Item 660(18), Adjust Junction Box, for new junction boxes installed on this project, or any junction boxes reused in place as a portion of other traffic or illumination work on this project.  Adjusting new or reused junction boxes shall be subsidiary to other bid items.

Payment for Item 660(24A), Conduit, 50 mm RMC, will be paid by the linear meter of conduit  installed.  Pavement excavation, and trench excavation and backfill shall be subsidiary.    Any pavement patching required shall be paid according to Item 407(7) Asphalt Concrete Leveling Course, or Item 401(9A) as directed by the Engineer.

Payment for Item 660(26), Signal System Timing and Adjustments, will be made based on paid receipts plus 15 percent for authorized work performed by the Municipality of Anchorage. A directive will not be required to initiate payment for work performed under Item 660(26).  All retesting of equipment for failure to comply with the plans and specifications will be at the expense of the Contractor. Invoice cost will be deducted under Item 660(26) and the total value of this Contract will be adjusted accordingly.

Payment for Item 660(27A), 6 Pair Detector Leads, will be paid by the linear meter of wire installed and accepted in place, measured by meter markings factory labeled on the cable jacket.

Payment for Item 660(29), Type 1A Junction Box, will be paid by each junction box installed, and accepted in place.

Conduit, wire, and detector loops for Automated Traffic Recorder Stations shall not be paid under this Section, but will be paid under Section 669, Automated Traffic Recorder Stations.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

660(3A)	Highway Lighting System, East Side, Complete	Lump Sum

660(3B)	Highway Lighting System, West Side, Complete	Lump Sum

660(12)	Relocate Electrolier	Each

660(14)	Traffic Detector Loops	Each

660(15)	Signal Interconnect System, Complete	Lump Sum

660(18)	Adjust Junction Box	Each

660(24A)	Conduit, 50 mm RMC	Meter

660(26)	Signal System Timing and Adjustments	Contingent Sum

660(27A)	6 Pair Detector Leads	Meter

660(29)	Type 1A Junction Box	Each

R190

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDER STATIONS

669-1.01 DESCRIPTION.  This work shall consist of furnishing and installing twelve complete traffic count stations for the automated collection of traffic data.

An Automated Traffic Recorder (ATR) station is a vehicle detection system, and may contain a traffic volume count system, an automated vehicle classifier (AVC) system, a weigh-in-motion (WIM system), and/or other equipment.  The multiple systems may be connected to a telephone line through an electronic switch, which enables the data from each unit to be retrieved by a computer located at the HDS offices.  Alternately, telecommunications my be provided by cellular telephones installed directly in the cabinets.  ATRs are operated and maintained by personnel of the Highway Data Section (HDS), main office located at 2200 East 42nd Street, phone (907) 762-4250, Fax (907) 672-4245.

The simplest form of ATR is an intermittent traffic volume counter, which consists of single inductive loops buried beneath the asphalt in each traffic lane, with lead wires run to the side of the road and terminated either in a cabinet or a junction box.  Traffic volume information is collected when a portable, battery-operated traffic counter is connected to the inductive loop wires; the traffic counter detects passage of vehicles and stores the data for later retrieval.

A Permanent Traffic Recorder (PTR) is formed when a traffic volume counter is connected to electrical and telephone service.  Electrical service enables the volume counter to be operated continuously, and the data is retrieved periodically over the telephone line by a computer located at the offices of the Highway Data Section.

An Automated Vehicle Classifier (AVC) station consists of two inductive loops in each lane, a piezoelectric axle sensor mounted in the pavement between the loops, and connected to a set of electronics located in a cabinet at the side of the road.  The dual inductive loops detect the presence and speed of passing vehicles, and the axle sensor determines the number and center-to-center spacing of all axles on the vehicle.  The raw data is processed by the electronics to classify the number and type of vehicles, which is stored in the electronics for later retrieval.  AVC stations may be configured to collect data on an intermittent or continuous basis.  If the electronics are permanently installed and with the addition of electrical and telephone service, the AVC can collect data on a continuous basis.

A general description of the Automated Traffic Recorders on this project is as follows:

Assembly H1.	Contains a continuous traffic volume counter, a continuous AVC system.  Includes a twelve inductive loop configuration, six piezoelectric cable axle sensors for vehicle classification.  Traffic volume and AVC electronics are housed in a controller cabinet (Style CBA2) equipped with heater and light.  A remote load center will supply 480V power to a step-down transformer and Type 2 load center adjacent to the cabinet.  All loops, piezoelectric sensors, cabinet, transformer and load center(s) shall be supplied, installed and commissioned as a working system by the Contractor.  Traffic volume counter, AVC electronics, telephone modem and remotely controllable code operated switch shall be provided, installed and commissioned by the Highway Data Section (HDS).

Assemblies H2, H3, H4 and H5.	Consist of a three inductive loop configuration, intermittent traffic recorder, without electrical or telephone service.  The inductive loop wiring is terminated to a weatherproof plug in a roadside junction box.  The complete installation shall be provided and installed by the Contractor.

Assembly H6.	Contains a continuous traffic volume counter, a continuous AVC system, in an eight inductive loop configuration.  Traffic volume electronics are housed in a controller cabinet (Style CBA2) equipped with heater and light.  A remote load center will supply 480V power to a step-down transformer and Type 2 load center adjacent to the cabinet.  All loops are existing including the conduit to the first junction box out of the traffic lanes.  Contractor’s work includes furnishing and installation of the replacement junction box, cabinet, transformer, and load center, as well as conduit, wire and cable and new junction box at the cabinet.  HDS will provide and install the traffic volume counter, cellular telephone, modem and remotely controllable code operated switch and commission the system.

Assemblies H7, H8, H9, H10, Hll and H12.	Consist of a four inductive loop configuration, intermittent traffic recorder, without electrical or telephone service.  The inductive loop wiring is terminated to a weatherproof plug in a roadside junction box.  The complete installation shall be provided and installed by the Contractor.

669-1.02  REGULATION AND CODE.  All materials and workmanship shall conform to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01  MATERIALS.  All materials provided for the work shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable. All wires and cables must be home run labeled for field location in each junction box and cabinet, i.e., V1SLA (for wire) and GaSLA (for coaxial cable).

2.	Conduit.  All conduit shall be in accordance with subsection 660-2.05, Conduit. All conduit, except for PVC conduit forming the inductive loops, shall be rigid metal.

3.	Junction Boxes.  All junction boxes shall be in accordance with subsection 660-2.06, Junction Boxes.  Junction boxes used for loops and sensor wires shall not contain any wiring or conduit greater than 24 volts. The covers of all junction boxes used loops and/or sensor wires shall be labeled 'TRAFFIC'. Junction boxes for 120/240 or greater electrical service shall be kept completely separate from junction boxes containing loop and/or sensor wiring. The covers of all junction boxes used to provide electrical service to ATR installations shall be labeled 'ELECTRIC'.

4.	Inductive Loops.  Inductive loops shall be supplied and installed by the Contractor.  All inductive loops shall be in accordance with subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.

Loop lead-in cable home run shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, an aluminum shield and overall PVC or PE jacket.

5.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, rated 600 vac/20 amps, capacity for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.  All conductors shall be terminated to a terminal block, including unused or spares.

6.	Asphalt Pavement.  Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement.

7.	Terminal Plugs.  All terminal plugs for Assemblies H2, H3, H4, H5, H7, H8, H9, H10, Hll, and H12 shall be provided and installed by the Contractor.  Terminal plugs shall be 14 pin socket contact receptacle, equal to or better than AMP brand part number 206037-1, with cable clamp AMP part number 206070-1, shell size 17, cable grip AMP part number 207387-1, rubber boot AMP part number 206398-1, cable boot AMP part number 207241-1.  Receptacle sealing caps shall be supplied for all terminal plugs, equal to or better than AMP part number 208652-1.

8.	Cabinets.  All cabinets shall be unpainted brushed aluminum with a NEMA 3R rating and comply with the latest National Electric Code article 90-7.  The cabinets shall include a Corbin #2 lock keyed to match existing Highway Data Section (HDS) cabinets Corbin locks.  Specific keying details may be obtained from the Highway Data Supervisor by contacting the HDS office.

Style CBA2 cabinets shall be in accordance with Subsection 660-3.05, Controller cabinets. The cabinet shall be a minimum of 1/8" thick sheet aluminum with continuously welded seams grounded to a smooth finish, unpainted, with a smooth grain finish on the exterior, with stainless steel (SS) hinges and fittings. The cabinet shall be totally enclosed with six (6) sides and a full front access. The cabinet shall be sized and mounted as shown the plans.

a.	Shelves.  Adjustable equipment shelves shall be mounted on rails inside of cabinet and be supported on both sides.  Shelves shall be grounded to cabinet.  A retractable keyboard tray shall be mounted under the lower shelf.

b.	Door.  The door is to be full front access with rolled flanges and neoprene rubber gaskets with stops to hold the doors in a full open position.  Door to have stiffeners on interior, plan pocket mounted inside and no other auxiliary door or openings. Ventilation to be provided with louvers and replaceable filters in lower part of door.  Filters shall allow air flow and block dust and snow from entering cabinet. Filters should be protected with a ventilated metal plate on the exterior.

c.	Fan.	 A thermostatically controlled fan in top of cabinet to operate at setable high temperature limit and exhaust air through a filtered and hooded vent in top of cabinet.

d.	Light. An interior light shall be supplied to operate with switch. The light shall be a 60W incandescent T-10 style bulb in sheet metal housing with SS wire guard, approximately 1" in profile, similar or equal to A-LTDA1.

e.	Heater. Cabinet heaters similar or equal to Hoffman DAH8001B shall be installed and thermostatically controlled.

f.	Thermostats. Thermostats shall have remote bulbs for heating and ventilation. Thermostats shall be Tradeline T6031A1029 (equal or better) and set for heat ON at 50 degrees F or less, ventilation at 90 degrees F or greater.

g.	Terminal Blocks. Terminal Blocks in CBA2 cabinets shall be mounted and located as shown on the plans.

h.	Wiring. All wiring for all 120V equipment including circuit breaker panelboard, heater, light, vent fan, and power receptacles to be in EMT, or liquid tight metal flex conduit.  Other low voltage wiring to be terminated on terminal blocks and trained within cabinet using wiring duct or ties.

i.	Circuit Breaker Panel. There shall be a combination transformer/load centers mounted on the posts on which the cabinets are mounted.  The load centers shall be Square D, or equal, Mini-Power Zone as indicated on the drawings.

j.	Certification. All cabinets must be in compliance with the latest National Electrical Code article 90-7.  The cabinet assembly consists of the cabinet itself and all high voltage (greater then 24 volts) components that are permanently installed.  All individual electrical components not permanently installed must comply with the NEC's artical 90-7 where applicable. The Contractor must obtain certification through authorized local or national testing agency.

9.	Automated Vehicle Classification (AVC) Counters and Sensors.  The contractor shall supply and install a 6-lane automated vehicle classification system at Assembly H1.  The piezoelectric axle sensors shall be PAT brand, from PAT Equipment Corporation, Inc., 1665 Orchard Drive, Chambersburg, PA 17201, phone (717) 263-7655. AVC sensors shall include:

a.	Piezo axle sensor (1 per lane), with coaxial leads long enough to reach the controller cabinet without spices

b.	Epoxy with hardener for each piezo axle sensor

c.	Two (2) year extended warranty

669-3.01  CONSTRUCTION REGULATIONS.

1.	Field Inspection.

a.	Prior to commencement of any field work, the Contractor shall obtain an initial inspection of the ATR sites accompanied by the HDS Supervisor or his designee.

b.	For all actions requiring the presence of HDS personnel, the Contractor shall notify the HDS Supervisor or his designee in writing a minimum of 3 working days (excluding Saturday, Sunday and State or Federal Holidays) prior to the work.

c.	The HDS Supervisor or his designee shall be present to approve installation of all underground conduit, wiring, and cabinet placement prior to final burial or encasement.

d.	Any installations deemed unacceptable by the HDS Supervisor or his designee shall be corrected and re-inspected prior to burial or encasement.  Any installation buried or encased without approval by HDS personnel shall, at the discretion of the HDS Supervisor, be uncovered, removed, and/or replaced at the Contractor's expense.

e.	Any expense or delay caused to the project scheduling by failure to properly notify the HDS supervisor and obtain the approvals noted in this section shall be the responsibility of the Contractor.

2.	Wiring.	All wiring shall be installed in accordance with subsection 660-2.09(A), Wiring.

a.	All wiring shall have at least 500 mm of slack cable in each junction box and at least 1 meter of slack cable available in the junction box nearest to the equipment cabinet.

b.	All wiring shall be labeled in all junction boxes.  Cable runs shall be labeled with plastic tags marked with indelible ink.

c.	All conductors shall terminate and be soldered to "spade" type terminals.

d.	All unused wire pairs shall be properly terminated.  In junction boxes, unused pairs shall be terminated within splices and labeled.  At cabinets unused pairs shall be terminated to a terminal block and labeled.

3.	Conduit.	All conduit shall be installed in accordance with subsection 660-2.05, Conduit or as indicated on the plans.

a.	Drain holes (T-drains) shall be placed at the low points of all conduit.  The interior of all conduit and the cut ends shall be de-burred; there shall be no sharp edges which can abrade or breach the insulation of wiring pulled through the conduit.

b.	Nylon pull cords shall be left in all conduit larger than 25 mm.

4.	Junction Boxes.  All junction boxes shall be installed in accordance with subsection 660-2.06, Junction Boxes or as indicated on the plans.

a.	Junction boxes used for ATR inductive loops and other sensors shall contain no wiring carrying greater then 24 volts.

b.	The covers of junction boxes shall be horizontal.  Junction boxes installed in gravel or earth shall be installed with the lids 30 mm below the lowest ground adjacent to the box.  Material surrounding the junction box shall be contoured back from the lid at no greater than a 45 degree slope.  Junction boxes mounted in or immediately adjacent to curbs and/or concrete or asphalt sidewalks shall be installed flush with the surrounding surface.

c.	Drain rock shall be placed below all junction boxes to a depth of at least 300 mm and extending beyond all outside edges of the box at least 100 mm.  The drain rock shall be washed river gravel no smaller than 25 mm.  Material below the junction box shall be compacted as necessary to prevent excessive settling of the junction box.

5.	Inductive Loops. All inductive loops used for ATRs shall be installed and constructed in accordance with subsection 660-4.01, Installation Details, unless otherwise specified in this Section or on the plans.

The plans are not schematics. Installation of the inductive loops shall be centered within the travel lane and shall closely conform to the location and layout of conduit runs shown in the plans. Inductive loops used for AVC within a lane shall be located five meters from leading edge to leading edge with a plus-or-minus twenty five millimeters tolerance.

All inductive loops installed through existing asphalt paving shall be installed using full-lane-width cuts a minimum of three meters in length, with the inductive loops centered in the 3 meter cut with a minimum distance of 300 millimeters to the edge of the cut. All edges of the cuts shall be tack-coated during patching to ensure full adhesion.  All full-width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from 'telegraphing' through the final lift asphalt.  Compaction tests shall be required at the discretion of the Highway Data Supervisor.

All loops installed in new asphalt paving shall be installed immediately prior to final paving of the particular section of road. Installation of loops after final lift paving shall not be permitted.

a.	Loop Size. All inductive loops shall be formed of four turns of wire, and shall be two meters square with plus-or-minus 25 millimeters tolerance.

b.	Lead-in Conduit. All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road. The loops shall be installed such that the weather-sealed cover plate on the 'T' body connector is on the top.

6.	Terminal Plugs.  The Contractor shall install 14-pin terminal plugs at Assemblies H2, H3, H4, H5, H6, H7, H8, H9, H10, H11, and H12 on the end of the six pair wire in junction boxes JB02.  Two meters of slack wire shall be left in junction boxes JB01 and JB02, the wire shall be run back to junction box JB01, spliced to the appropriate inductive loop wires and encased in a weatherproof splice kit.

7.	Cabinets.  The Highway Data Supervisor shall be consulted prior to cabinet placement.

All cabinets shall comply with the National Electrical Code article 90-7 as a cabinet assembly. The cabinet assembly shall include all electrical service, wiring, circuit breakers, surge protection, receptacles, etc. which carries more than 24 VDC.

All cabinets shall be installed out of the clear zone unless protected by safety barriers.

All cabinets shall be installed with the doors facing away from the road.

All conduit leading to the cabinet shall be brought down through the bottom of the cabinet; no conduit runs shall be cut through the sides or top of the cabinet.

All terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks shall be mounted so that all terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.

8.	Installation and Commissioning of the Traffic Volume Counter. The Contractor shall install and commission the traffic volume counter as a working system.  The counter system must be able to detect and record the presence of vehicles in all lanes, and communicate via telemetry to the computers at the main office or field office of the Highway Data Section.

Per manufacturer's instructions, the inductive loop sensors shall be connected to the electronics, the traffic volume counter shall be connected to 120 volt electrical power through a battery and battery charger, the counter shall be connected to telephone service through the code operated matrix switch and the telephone modem, and all internal parameters shall be set and adjusted as needed.

Specific operating parameters and communication software may be obtained from the Highway Data Section.  Commissioning of the traffic volume counter system requires the temporary use of a MS DOS compatible laptop microcomputer.

9.	Installation and commissioning of the AVC Piezoelectric Sensors and Electronics.  The contractor shall install and commission the AVC Piezoelectric Sensors.  The HDS shall commission the electronics and the system as a whole.  The AVC system must be able to detect, properly classify and record vehicles per FHWA Scheme F, and communicate via telemetry to the computers at the main office or field office of the Highway Data Section.

All permanent piezoelectric sensors shall be installed per AVC equipment manufacturer's recommendations.  A suggested installation sequence is available from the Highway Data Section.  Piezoelectric sensors for AVC shall be installed in sawcut slots in final pavement. "Blockouts" shall not be used. All coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least to meters of slack cable available in the equipment cabinet prior to the terminal block.

10.	Utilities.

a.	Load Center Installation. The Contractor shall provide and install a Square D Mini-Power Zone combination Transformer and loadcenter at the cabinet for Assemblies H1 and H6 as shown on the plans.  The load centers shall be installed per the plans, specifications and the requirements of the appropriate Electrical Utility.  Conductors shall be brought into the cabinet through separate conduit and junction boxes solely for that purpose; there shall be no wiring carrying more than 24 volts in any conduit or junction box containing wiring from the data collection sensors.

b.	Inspection. The Contractor shall request inspection of the Load Center and cabinet by the Department of Labor, Division of Mechanical Inspection (DOL/DMI), and/or by any local authority that may be required.

c.	Electrical Utility Connection. After approval of the Load Center by the DOL/DMI and/or the local authority, the Contractor shall inform the Project Engineer as to when electrical service is needed at the Load Center, with sufficient time to enable the Project Engineer to schedule the installation with the Electrical Utility prior to commissioning of the equipment.  The Project Engineer will make arrangements in writing with the Electrical Utility to connect to the Load Center.  The Electrical Utility will provide service to the Load Center upon request of the Project Engineer.

669-3.02 ACCEPTANCE TESTING. The Contractor shall perform acceptance testing on all ATR installations.

All ATR installations shall have general tests conducted by the Contractor in accordance with subsection 660-4.01

In addition to the general tests, Acceptance Tests shall be performed by the Contractor on all Automated Vehicle Classification installations. Acceptance tests shall be performed to demonstrate that the AVC system performs at or above the required accuracy. The classification standard used shall be in accordance with FHWA Schedule F. Exact measurements for the axle spacings to be used for each vehicle classification shall be obtained from the Highway Data Supervisor.

1.	Accuracy Requirements.  The accuracy of Automated Vehicle Classifiers is such that, if good lane discipline is maintained:

a.	not more than plus or minus ten percent (+ 10 %) of the total vehicles in FHWA Class 1 through Class 3 and,

b.	not more than plus or minus five percent (+ 5 %) of the total vehicles in FHWA Class 4 through Class 13 are classified in the wrong bin when compared with a concurrent manual classification count.

c.	The AVC Acceptance Test shall consist of an hour-by-hour and summary comparison of a manual classification count with the output of the permanent AVC.  A manual vehicle classification count shall be performed for sixteen consecutive hours (16 hrs) at the AVC site.  During that 16 hour period, a minimum of five (5) vehicles in an individual vehicle type bin is required in order to be included in the final comparison.

d.	The difference between the number of vehicles in each type bin as observed manually and as recorded by the AVC system shall be computed.  If more than the allowed percentages as listed above are classified in the wrong bin when compared with a concurrent manual classification count, the AVC equipment shall be recalibrated and the test performed again until the system meets the required accuracy.

2.	Alternate Acceptance test. An alternate acceptance test for AVC equipment may be performed using a test vehicle.  A class 9, 5 axle semi-tractor-trailer is driven over the AVC sensors.  The distance between the axles measured by the AVC is compared to that measured at rest.  The AVC equipment is adjusted until all axle spacing measurements from ten consecutive passes of the test vehicle are measured accurately within plus-or-minus 150 millimeters.

669-3.05  SUBMITTALS.  All submittals shall be provided to the Highway Data Supervisor prior to final approval of the work or as otherwise called for herein.

1.	Equipment List(s) and Drawings. The Contractor shall submit for review and approval by the Highway Data Supervisor within thirty days following award of the contract, three collated copies of a portfolio of equipment and materials which he proposes to install for the ATRs.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Materials Submittal shall include a detailed shop drawing of the Style CBA2 cabinets showing the location of all mounted components, including the thermostatically controlled heater, thermostatically controlled exhaust (cooling) fan, switched fluorescent light, shelves, Corbin #2 locks keyed to match existing Highway Data Section cabinets with Corbin locks, Ground Fault Circuit Interrupt (GFCI) circuit breakers, receptacles, terminal blocks, and surge protectors for all electrical.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed, submitted and approved.

2.	Utility Schedule. The Contractor shall submit for review and approval by the Highway Data Supervisor within sixty days following award of the contract, three collated copies of a schedule to install and activate the electrical and telephone utilities to the ATR cabinet at Assemblies H1 and H6. The Utility Schedule will clearly identify in detail what actions will be taken to ensure timely activation of electrical and telephone service, when the activity will occur, and who is responsible for completing each action. The schedule shall include the name, employer, position title and telephone number of both who is to be contacted and who is to be responsible for completing each action.

3.	As-Built Plans. The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the plans.  As-builts shall include the following information on the appropriate sheets; the location and depth of all inductive loops and conduit runs, and, the station and offset of all junction boxes.  Redlines of full size construction plans will be acceptable. Three sets of as-built plans shall be presented to the Project Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

4.	Photographs. The Contractor shall present photographs and 35 mm negatives documenting the installation of all inductive loops. The photos shall show the loops in place prior to covering with gravel and asphalt pavement. The photographs shall include at least one view of each loop showing the conduit to the nearest junction box, and at least two overall views of each ATR installation showing placement of the inductive loops. the photographs shall be 125 mm x 175 mm (5" X 7") color prints, and shall be labeled with the identification of each loop as indicated on the plans (for example; H1 - V1NLA).

5.	Test Results. Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Highway Data Supervisor prior to acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted in accordance with subsection 660-4.01, Installation Details.

6.	Manuals. The Contractor shall provide to the Highway Data Supervisor all installation, repair and operation manuals for all traffic volume and classification equipment.

7.	Materials. The Contractor shall provide to the Highway Data Supervisor any and all epoxy grout remaining after installation.

669-4.01  METHOD OF MEASUREMENT. The quantity to be paid for will be all completed and accepted Automated Traffic Recorder Installations as shown on the plans or as directed by the Project Engineer.

669-5.01  BASIS OF PAYMENT.  The contract unit bid price for all Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	Backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under Item 407(7), Asphalt Concrete Leveling Course, or Item 401(9A), Asphalt Concrete Pavement, Type II, Class A, as directed by the Engineer.

3.	Traffic Control shall be paid for under the appropriate pay item(s).

4.	Installation of wiring and service to the Load Center(s) will be paid for under the Utility Agreement for Electrical Service.  Installation of wiring and service to the Network Interface Device(s) (NIDs) will be paid for under the Utility Agreement for Telephone Service.

5.	All other materials, installation, commissioning, acceptance testing, photographs and as-built plans required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorders.

6.	A sum equal to one-tenth (1/10) of the total cost for Pay Item 669(1) shall be withheld until after the Highway Data Supervisor certifies in writing that the installations have passed all Acceptance Tests in section 669-3.02 and that all Deliverables in Section 669-3.05 have been submitted.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1)	Automated Traffic Recorders	Lump Sum

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION. Delete the first sentence and substitute the following: This work shall consist of placing durable pavement markings. Durable pavement markings consist of either preformed marking tape or methylmethacrylate pavement markings at the Contractor's option.

Durable pavement markings will be considered in three groups: 1) Transverse Pavement Marking Lines, 2) Transverse Markings, Words and Legends, and 3) Longitudinal Stripes.  For each of these three groups, once preformed marking tape or methylmethacrylate is selected, only that one durable pavement marking type shall be used for that group throughout the project, unless otherwise approved by the Engineer.

670-2.01 MATERIALS. Add the following: Methylmethacrylate pavement markings shall conform to Subsection 712-2.17.

The methylmethacrylate pavement markings shall be applied using an ambient temperature curing, two component methylmethacrylate system for application on either asphalt or cement concrete surfaces. The material shall be free from defects or imperfections which might adversely affect the serviceability of the finished product. It shall be free from dirt and other foreign material and cure to a tough serviceable film.

Glass beads for drop-on application shall be those recommended in writing by the striping material manufacturer and as approved by the Engineer.

670-3.01 CONSTRUCTION REQUIREMENTS. Add the following after Item 3:

4.	Methylmethacrylate Pavement Markings. Pavement receiving methylmethacrylate pavement markings shall be prepared according to this Section and the manufacturer's recommendations.

Methylmethacrylate pavement markings shall be applied at a minimum thickness of 1.5 mm. The thickness will be measured without the glass beads.

A manufacturer's representative shall be present on the first day of striping for each type (sprayed or extruded) and additional days as required by the Engineer.

Methylmethacrylate pavement markings shall not be applied to new asphalt until the asphalt has cured to the satisfaction of the manufacturer's representative.

All dirt, gravel and other deleterious matter shall be removed from the pavement areas upon which the traffic markings are to be applied immediately prior to traffic marking installation.

The application rate of beading on sprayed markings shall be 2.3 kilograms of beads per liter and 60 kilograms of beads per 100 square meters for extruded markings.

The surface temperature of the roadway shall be in the range of 0 to 40 degrees Celsius for stripe application. The roadway surface shall be thoroughly dry.

Methylmethacrylate stripe material shall be applied with truck mounted equipment designed and capable of properly mixing at the point and time of application in accordance with the manufacturer's recommendations.

670-3.04 PAINT REMOVAL. Change the title of this subsection to "Pavement Markings Removal."

Replace the first sentence of the second paragraph with the following: Pavement markings shall be removed to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.05 PRELIMINARY SPOTTING. Add the following: After acceptance of the crushed aggregate base course layer, but prior to paving, the Engineer will establish passing/no passing zones. The Engineer will establish the no passing zones in accordance with Chapter 3 of the Alaska Traffic Manual. (3/30/94)R192

670-4.01 METHOD OF MEASUREMENT.

Under Item 2, “Mile Basis”: Replace each occurrence of “mile” with “kilometer.”  Under Item “b. Kilometers of double or wide stripe:” change “which exceed 150 mm in width” to “which are equal to, or exceed, 150 mm in width”.  Add the following: Durable Pavement Markings for all longitudinal stripes, including those longitudinal stripes that outline gores, will be measured by the kilometer, under Item 670(2) Single Stripe, or 670(3) Double or Wide Stripe, as applicable.

Under Item 3, “Square foot basis”: Replace “Square foot” with “Square Meter.”  Add the following: Durable Pavement Markings, under Item 670(4) Transverse Pavement Marking Lines, will measure stop bars, crosswalks, and gore markings (transverse gore markings only) by the square meter.

Unless Durable Pavement Markings are installed simultaneously with the paving operation, all temporary pavement markings and traffic control for installing Durable Pavement Markings shall be subsidiary to Section 670 bid items.

670-5.01 BASIS OF PAYMENT. Add the following: Repair of any damaged pavement or surfacing caused by the pavement marking removal operation will not be paid for directly, but will be subsidiary to Section 670 bid items and work performed under Section 643.     R198M

Add the following section:

SECTION 680

TELEPHONE RELOCATION

Special Provisions

680-1.01 DESCRIPTION. This work shall consist of furnishing of all labor, equipment and material necessary to place electrical conduit in a roadway crossing in accordance with these plans and specification.

680-2.01 MATERIALS. Conduit materials shall meet the applicable standards of ANSI, ASTM, NEMA, REA,(RUS), UL and all local codes and permits. Conduit components shall be installed in accordance with applicable requirements of the NEC. In case of a conflict between the requirements of any of the above referenced codes and standards and these specifications, the requirements of these specifications shall govern. All materials, devices, and practices shall meet the applicable requirements of the Federal "Occupational Safety and Health Standards."

All conduit shall be polyvinyl chloride (PVC), 100 millimeters in diameter (4-inch), schedule 40 minimum, in accordance with ASTM D-2447. Nylon pull cords shall be 6 mm in diameter and 227-Kilograms rated. Pull cords shall be left in all the conduit crossings. Conduit shall be plugged with plastic end plugs approved by the Anchorage Telephone Utility (ATU) and Prime Cable prior to installation.

680-3.01 GENERAL CONSTRUCTION REQUIREMENTS. The ATU or Prime Cable inspector, through the Engineer, reserves the right to suspend the conduit installation at any time that the Contractor fails to meet the requirements set forth in these specifications and until such time as the Contractor makes the necessary corrections. Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The conduit crossing stations are approximate only and each crossing will need to be field located and confirmed with the Engineer, ATU and Prime Cable prior to starting work. The Contractor can obtain a point of contact with ATU engineering by calling 564-1820 or 564-1465 and Prime Cable engineering at 786-9382 or 786-9381. Prior to installing the conduit crossing, the Contractor shall obtain locates of existing underground utility, signal and lighting conduits at each of the proposed crossing locations in accordance with subsection 105-1.06 of these specifications. Contractor shall confirm the field location of each crossing with the Engineer and ATU and Prime Cable personal prior to construction.

The Contractor shall be responsible for location, shoring and protection of all property (real and personal), in the vicinity of the roadway crossings within the project.

All foreign material, earth sand, and gravel shall be removed from the conduit prior to placing the end caps and pull line.

All temporary bridging for traffic will be inspected and approved by the Engineer prior to installation. This does not relieve the Contractor of responsibility for providing bridging of sufficient size of strength. Any bridging open to public traffic will provide a smooth driving joint.

The minimum depth of bury for each conduit crossing is 1200 mm below the finish pavement grade to the top of the duct and /or 900 mm below the ditch grade which ever is deeper. The depth of bury shall not exceed 1830 millimeters unless approved by the Engineer, ATU and Prime Cable. The ends of each conduit crossing shall be covered with end caps in such a way that material will not enter the conduits. The Contractor shall coordinate with ATU and Prime Cable engineering to obtain EMS "locators " to be placed above the ends of each conduit crossing prior to backfilling, as detailed on the plans. In addition, the Contractor shall, through the Engineer, provide ATU and Prime Cable with the schedule for each crossing a minimum of three (3) calendar days in advance of construction.

680-3.02 GENERAL CONDUIT INSTALLATION REQUIREMENTS FOR ROAD CROSSINGS. The conduit crossing shall be installed in accordance with details shown on the ATU and Prime Cable plans. The conduit shall be trenched under the road.

Conduit joints shall be non-threaded solvent cement type as recommended by the conduit manufacturer. The contact surfaces of the conduit and fitting shall be cleaned with methylethylketone, or acetone, then liberally coated with solvent cement and promptly and fully engaged. Either the conduit or fitting shall be rotated approximately 1/4 turn to dispel air and evenly distribute solvent cement over contact surfaces. Total elapsed time between the start of cement application to the surfaces being joined and final assembly of the joint shall not exceed 60 seconds. The initial strength of the joint will permit continued conduit installation; however, additional stress at the joint shall be avoided for at least 24 hours after jointing.

Plastic conduit shall be shaded from sunlight as required to prevent curvature and deterioration due to thermal expansion and exposure to sunlight.

Defective conduit shall not be installed and shall be removed immediately from the site of work.

680-3.03 TRENCHING AND EXCAVATION. The Contractor shall excavate 600 mm below conduit grade if unsuitable material is encountered and backfill with Selected Material, Type A. If saturated material is encountered, the Contractor shall excavate 600 mm below conduit grade those materials with a moisture content 2.0 percent over the optimum moisture when tested in accordance with AASHTO T-180.

The existing asphalt pavement to be removed shall be removed in accordance with Section 202, Removal of Structures and Obstructions.

680-3.04 BACKFILL AND COMPACTION. Backfill shall be in accordance to Section 203, Excavation and Embankment. All backfill for the conduit crossings shall be in 200 mm lifts to 95 percent of the maximum density in accordance with subsection 203-3.03, Construction of Embankment with Moisture and Density Control.

Backfill materials shall meet the requirements of Selected Material, Type A. If large quantities of water are evident, the Contractor may elect to install backfill with 50 mm to 150 mm course oversized rock overlaid with geotextile. Compaction shall be by a minimum of six full width passes with a mechanical compactor. The conduit shall then be placed on a 25 mm sand bedding on the trench bottom, with the sand being water compacted to 25 mm above the conduit. The Contractor shall then use such materials as have been excavated from the trench that meet the requirements of Selected Material, Type A above the conduit sand bedding, up to the bottom of the roadway structural section.

The soil compaction of the trenches shall be randomly tested at various depths by the Engineer.

The asphalt pavement shall be replaced in accordance with Section 401 Asphalt Concrete Pavement.

Patching roadway crossing areas after the installation of the conduit crossing shall be done within two (2) calendar days after the completion of the roadway crossing or as approved by the Engineer. The Contractor shall maintain the roadway surface in the conduit crossing locations in such a manner that traffic is not impeded, as directed and approved by the Engineer, until the roadway crossings are paved.

680-3.07 SURVEYING AND STAKING. The Contractor shall as-built each conduit crossing. The elevation of the finish grade project centerline at the crossing location and at the end of each conduit crossing shall be recorded. In addition, the distance left and right of the project centerline of each end of each crossing will also be referenced. Location and elevation information for each conduit crossings will be documented by a Land Surveyor registered in the State and be provided to ATU and Prime Cable at the end of construction.

680-4.01 METHOD OF MEASUREMENT. Conduit crossings will be measured by the meter of conduit installed.

6805-5.01 BASIS OF PAYMENT. Item 680(4A-100), 100 mm Conduit Crossing shall be full compensation for furnishing and installing conduit, pull cords, and end caps, at the required locations. Removal of existing asphalt pavement and any materials required to backfill the excavation, including sand bedding, Select Material Type A, crushed aggregate base course, geotextile fabric and 50-150 mm course rock shall be considered incidental to this item. Any other items impacted by the installation (curb and gutter, concrete sidewalk etc. will be paid for under the applicable bid item. Additional excavation required in areas of unsuitable material or material with excess moisture content shall be considered subsidiary to Item 680(4A-100). The costs for as-builting all the conduit crossings, the placing of end caps, the installation of nylon pull cords and the placing of the EMS "Locators" will not be paid for directly, but will be subsidiary to Item 680(4A-100).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

680(4A-100)	100 mm Conduit Crossing	Meter

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.03 EMULSIFIED ASPHALTS. Delete this subsection in its entirety and substitute the following: The STE-1 cationic emulsified asphalt shall comply with the requirements listed below when tested in accordance with ASTM D 244:

TESTS ON EMULSION

Viscosity, Saybolt Furol at 25o C	30 max.

Storage Stability, 1 day, %	1 max.

Demulsibility, 35 ml, 0.8% Sodium dioctyl

sulfosuccinate solution, %	25 min.

Sieve Test, % retained	0.10 max.

Particle Charge	Positive *

Distillation Oil by Volume of Emulsion, %	5 max.

Distillation Residual by Weight of Emulsion, %	45 min.

*	If particle charge test is inconclusive, materials having a maximum pH value of 6.7 will be acceptable.

TESTS ON RESIDUE

Penetration, 25o C, tenths of a mm	100 min./200 max.

Ductility, 25o C, 5 cm/min., cm	40 min.

Solubility in Trichloroethylene, %	97.5 min.

702-2.04 STORAGE AND APPLICATION TEMPERATURES. Add the following to Table 702-1:

| Type and Grade of Material | Spray (oC) | Mix (oC) | Storage (oC) |
| --- | --- | --- | --- |
| STE-1 | 20-60 | 20-65 | 10-50 |

(6/14/95)R183M

SECTION 703

AGGREGATES

Special Provisions

703-2.03  AGGREGATE FOR BASE.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 50-79 |
| 4.75 mm | 35-58 |
| 2.36 mm | 20-47 |
| 600 µm | 10-26 |
| 300 µm | 6-19 |
| 75 µm | 0-6 |

(11/04/94)R117M

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT. Replace this subsection with the following:

Coarse Aggregate. Coarse aggregate (that material retained on the 4.75 mm Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality. All material shall be free from clay balls, vegetative matter or other deleterious matters. Coarse aggregate shall not be coated with dirt or other finely divided mineral matter. In addition, coarse aggregate shall meet the following requirements:

| Percent of Wear | AASHTO T 96 | 45 max. |
| --- | --- | --- |
| Degradation Value | ATM T-13 | 30 min. |
| Percent Sodium Sulfate loss | AASHTO T 104 | 9 max. (5 cycles) |
| Percent Fracture | ATM T-4 | 80 min. single face |
| Thin-Elongated pieces | ATM T-9 | 8% max. |

Fine Aggregate. Fine aggregate (passing the 4.75 mm sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate. The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3. The fraction actually retained between any two consecutive sieves larger than the 150 μm shall be not less than 2 percent of the total. The size of samples for extraction will be in conformance with AASHTO T 164. Extracted gradations will be determined according to AASHTO T 30.

703-2.07 SELECTED MATERIAL. Add the following to Item 1., Selected Material, Type A: It shall have 20 to 55 percent by weight of particles passing the 4.75 mm sieve.

(4/18/97)R89M

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT

CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| Sieve Designation | Gradation Designation |  |  |
| --- | --- | --- | --- |
|  | Type I | Type II | Type III |
| 25 mm | 100 | - | - |
| 19 mm | 75-90 | 100 | - |
| 12.5 mm | 60-86 | 75-90 | 100 |
| 9.5 mm | 50-78 | 60-84 | 75-90 |
| 4.75 mm | 34-62 | 33-70 | 50-78 |
| 2.36 mm | 24-52 | 19-56 | 32-60 |
| 1.18 mm | 16-42 | 10-44 | 20-45 |
| 600 μm | 10-32 | 7-34 | 12-34 |
| 300 μm | 8-24 | 5-24 | 8-24 |
| 150 μm | 5-16 | 4-16 | 4-15 |
| 75 μm | 3-8 | 3-7 | 3-8 |

(9/17/96)R200M

703-2.12 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT. Add the following subsection:

Coarse Aggregate. Coarse aggregate (that material retained on the 4.75 mm sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality. All material shall be free from clay balls, vegetative matter or other deleterious matters. Coarse aggregate shall not be coated with dirt or other finely divided mineral matter. In addition, coarse aggregate shall meet the following requirements:

| Property | Test Method | Requirement |
| --- | --- | --- |
| Percent of Wear | AASHTO T 96 | 45 max. |
| Degradation Value | ATM T-13 | 30 min. |
| Percent Sodium Sulfate Loss | AASHTO T 104 | 9 max. (5 cycles) |
| Percent Fracture single face double face | ATM T-4 | 90 min. 75 min. |
| Flat and Elongated Particles 3:1 5:1 | ATM T-9 | 35% max. 8% max. |
| Absorption | AASHTO T 85 | 2% max. |

Fine Aggregate. Fine aggregate (passing the 4.75 mm sieve) shall meet the quality requirements of AASHTO M 29, shall consist of 100 percent crushed aggregate and shall be nonplastic (AASHTO T 90).

Mineral Filler. Mineral filler shall conform to the requirements of AASHTO M 17. The mineral filler shall be free organic impurities and have a plastic index not greater than 4. The mineral filler shall be sufficiently dry to flow freely and free from agglomerations. The mineral filler shall not have more than 40 percent by weight smaller in size than 0.02 mm.

Blended Aggregate. The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-8. Aggregate gradations will be determined by ATM T-7. Extracted gradations will be determined in accordance with AASHTO T 30.

TABLE 703-8

STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

| Sieve Designation | Requirement |
| --- | --- |
| 19 mm | 100 |
| 12.5 mm | 82-88 |
| 9.5 mm | 60-70 |
| 4.75 mm | 25-29 |
| 2.36 mm | 18-24 |
| 1.18 mm | 15-20 |
| 600 μm | 12-18 |
| 300 μm | 11-15 |
| 150 μm | 10-14 |
| 75 μm | 8.0-11.0 |

(6/18/96)R164M

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

Quality Requirements: The markings shall be formulated and manufactured from new materials. It shall be free from defects and imperfections that might adversely affect the serviceability of the finished product. It shall be free from dirt and other foreign material and cure within the time specified to a tough serviceable film. Part "A" resin system shall be methyl methacrylate based. Part "B" shall be benzoyl peroxide in liquid plasticizer.

The quality of material supplied shall be that of Dura-Stripe Type IV or equal.

Performance Properties:

Viscosity: 5 - 12 Pa sec (ASTM D2196 Method B, LV Model, Spindle #4 at 60 RPM.

No Tract Time: Material shall be track free after 15 minutes when applied at 1 mm (ASTM D711).

Hardness: Shore Durometer, A-1, 80 minimum after 24 hours.

Tensile Strength: At break, minimum 862 kPa (ASTM D638)

Percent Elongation: Minimum 20% (ASTM D638).

Water Absorption: Maximum 0.5% (ASTM D570).

Chemical Resistance: Seven day immersion

Anti-freeze				No effect

Motor Oil					No effect

Diesel Fuel				No effect

Gasoline					No effect

Calcium Chloride			No effect

Sodium Chloride			No effect

Transmission Fluid		No effect

The marking compound shall be resistant to the effects of ultra-violet light.

Adhesion: To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

Skid Resistance: Minimum 45 (ASTM E303) in units (British pendulum).

Reflectivity: Initial, minimum 200 millicandella (as applied).

Composition: The composition is at the discretion of the manufacturer, but shall be essentially comprised of resins, reactive monomers, pigments, aggregate and glass beads. When mixed in the stated ratio, the material shall cure to 99% minimum by weight and volume solids.

(8/30/96)R198M

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(1/21/95)R81M

APPENDIX A

ELECTRICAL FACILITY CLEARANCE REQUIREMENTS

FOR

CONSTRUCTION OR MAINTENANCE NEAR ELECTRICAL FACILITIES