PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	State of Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

b.	Standard Specifications for Highway Construction 2004.  ($25.00)

c.	Alaska Test Methods Manual (Lab & Field), 2007 Edition. ($25.00)

2.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

3.	The Materials Certification List (MCL) has been included in Appendix B.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

4.	The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retro reflectivity.  See subsection 643-3.11, High Visibility Clothing for requirements.

5.	Permits allow for the construction of work pads in Cook Inlet within the boundaries shown on Sheet E2.  These pads may be constructed as described in the permits, at the discretion of the Contractor, but are not a requirement of the Contract.

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.03 DEFINITIONS.  Replace the definition of BID and CONSTRUCTION with the following:

CONSTRUCTION.  Physical activity by the Contractor or any subcontractor using labor, materials, or equipment within the Maintenance Project, or within materials sources planned for use on the Maintenance Project.

Standard Modifications

101-1.03 DEFINITIONS

PLANS Delete text of PLANS and replace with:  The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32 (01/27/07)

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22 (01/01/06)

Add the following definition:

QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.

E36 (01/27/07)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.  Replace the second paragraph with the following:  The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.  E23 (01/01/06)

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.  E18 (06/30/04)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01 CONSIDERATION OF BIDS.  Add the following:  In determination of the low bidder for state funded projects, a 5% bid preference will be given to Alaska bidders, as required under AS 36.30.170. “Alaska bidder means a person who:

1.	holds a current Alaska business license;

2.	submits a bid for goods, services, or construction under the name as appearing on the person’s current Alaska business license;

3.	has maintained a place of business within the state staffed by the bidder or an employee of the bidder for a period of six months immediately preceding the date of the bid;

4.	is incorporated or qualified to do business under the laws of the state, is a sole proprietorship, and the proprietor is a resident of the state or is a partnership, and partners are residents of the state; and

5.	if a joint venture, is composed entirely of ventures that qualify under 1. through 4. above.

Except for timber, lumber, and manufactured lumber products used in the construction project under AS 36.30.322(b), an Alaska products preference will be given as required under AS 36.30.326-36.30.332 when the bidder designates the use of Alaska products.  The bidder shall complete the Alaska Products Preference Worksheet, according to instructions, and submits it whit the bid to indicate those Alaska products that are proposed for use.  If the successful bidder/Contractor proposes to use an Alaska product and does not do so, a penalty will be assessed against the successful bidder/Contractor in an amount equal to the product preferences percentage granted to the successful bidder/Contractor plus one percent multiplied by the total declared value of the Alaska products proposed but not used.  ES09(6/30/04)

SECTION 105

CONTROL OF WORK

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete: “(24”x36”)” and replace with: (22”x34”)

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after: “Work performed and materials furnished shall conform to the Plans and Specifications” add: and approved Working Drawings,

In the first sentence of the second paragraph after: “Work or material not conforming to the Plans and Specifications” add: and approved Working Drawings,

E33 (01/27/07)

Special Provisions

105-1.06 UTILITIES.  Add the following:  Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGLINE, INC. Locate Call Centers Anchorage 278-3121 Statewide (800) 478 3121

Call Centers will notify the following: Anchorage Communication System (ACS) Aircraft Service International Group Alaska Fiberstar Alaska Native Hospital (ANHC) Alaska Railroad Corp (ARRC) Anchorage School District (ASD) Alyeska Cable AT&T Alascom, Inc. Chugach Electric Assoc (CEA) DOT Street Lights, State of Alaska Enstar Natural Gas Eyecom TV/Interior Telephone General Communications, Inc. (GCI) Interior Telecom. Marathon Oil Corporation Tesoro Alaska Pipeline Mukluk Telephone Association (MTA) Phillips Petroleum Pacific Telecom, Inc. (PTI) Telalaska Unocal United Utilities World Telecommunications, Inc. (Worldcom)

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.

Construction surveying is required before utility relocation.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.  R3 (05/24/07)

ENSTAR Natural Gas Company (ENSTAR) and General Communications, Inc. (GCI) own and operate underground natural gas and fiber optic telecommunications facilities within the project limits. Locate and protect the facilities.

An ENSTAR and GCI representative must be on site when equipment operates within ten feet of the utilities. Hand dig when within two feet of the pipeline or cable. Submit a dig plan to ENSTAR and GCI, through the Engineer, prior to exposing the utilities.

Comply with ENSTAR’s “Safety Requirements for excavation adjacent to Natural Gas Pipelines,” attached as Appendix C.

Special Provisions

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following state owned projects may be under construction concurrently with this project:

Crow Creek Road

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contracts.

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Replace the first sentence with the following:

The Contractor shall maintain the entire highway and related highway facilities located within the project from the date construction begins until the Contractor receives a letter of substantial completion.

Standard Modification

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue.  E19 (06/30/04)

Special Provision

105-1.17 CLAIMS.  Add the following:  Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.  R93 (03/21/01)

Add the following subsection:

105-1.18 INTERIM COMPLETION.  This project includes one interim completion phase.

Interim Completion Phase

Date: November 26, 2008.

Work:  The Contractor shall complete pipe removal, pipe installation, detour removal, and temporary asphalt, and traffic markings.

Final Completion Phase:

Dates:  May 1 - May 20, 2009.

Work: Complete application of final asphalt surface, seeding, and traffic marking material.

Coordinate interim and final traffic marking with Section 670.

Liquidated damages will be assessed according to subsection 108-1.07 Failure to Complete on Time, for failure to complete work under this Contract within the interim completion date and final completion date specified.

# SECTION 106

CONTROL OF MATERIAL

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text: “Approved Products List” and replace with:  Qualified Products List.   E36 (01/27/07)

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award that is determined by material testing to be unsuitable for use on the project.  E24 (01/01/06)

Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents.  The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.  E34 (01/27/07)

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.

Add the following:

Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If  cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following: The Department has received the following permits on the Contractor’s behalf:

- U. S. Corps of Engineers, Nationwide Permit 3 – Maintenance

- Alaska Department of Natural Resources Division of Coastal and Ocean Management, Coastal Consistency Review

- Municipality of Anchorage, Flood Hazard Permit

- Alaska Department of Fish and Game, Title 16 – Fish Habitat Permit

5.	Alaska Railroad Corporation, Temporary Construction Permit

***deleted***

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.

Change the first sentence to the following:

When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

Replace subsection 107-1.08 with the following:

# 107-1.08 RAILWAY-HIGHWAY PROVISIONS.

# 107-1.08-SECTION 1.  DEFINITION OF TERMS

ARRC	Alaska Railroad Corporation, P.O. Box 107500, Anchorage, AK 99510-7500.

ARRC Property	all lands owned or withdrawn for the use of the ARRC, including the ARRC's track right-of-way and communications pole line right-of-way.

Chief Engineer	the person employed by the ARRC as head of its Engineering Department or Branch, or his/her authorized representative.

Contractor	any agent of the Permittee, including contractors or subcontractors employed to construct, reconstruct, operate and/or maintain the Facility.  The term "Contractor" shall be synonymous with the term "Permittee" when the Permittee performs the construction, reconstruction, operation and/or maintenance of the Facility with its own personnel.

Facility	any improvements owned by the Permittee which are to be placed on ARRC property in accordance with written permission executed by ARRC and Permittee.

Roadway Worker	any employee of a railroad, or of a contractor to a railroad, whose duties include inspection, construction, maintenance, or repair of railroad track, bridges, roadway, signal and communication systems, electric traction systems, roadway facilities, or roadway machinery on or near track or with the potential of fouling a track.

Signals Supervisor  	the person employed by the ARRC as head of its Signals and Telecommunications Department or Branch, or his/her authorized representative.

Permittee	the Department is the governmental agency to whom the right to enter upon ARRC Property was given in the form of a written permit or contract executed by the ARRC and Permittee.

Trackwork	all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

Track Materials	all hardware, excluding signals and controllers, associated with the running of a railroad.

# 107-1.08-SECTION 2.  GENERAL REQUIREMENTS

2.1	All construction, reconstruction, operation, and maintenance on ARRC Property shall be performed in compliance with these specifications contained in 107-1.08, including all revisions thereto.

2.2	Failure to comply with these specifications shall result in suspension of all work on ARRC Property.

2.3	All work on or about ARRC Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with approved ARRC practices, and as specified herein.  ARRC traffic and property shall be protected at all times.

2.4	The safety and continuity of the operation of the traffic of ARRC shall be of first importance and shall be at all times protected and safeguarded.  The Contractor and its subcontractors shall be required to perform and arrange their work accordingly.  Whenever, in the opinion of the Chief Engineer or his or her representatives, the work or its performance may affect or involve the safety of ARRC's facilities and/or operation of its railroad, the method of doing such work shall first be submitted by the Contractor to the Chief Engineer for his/her approval, without which it shall not be commenced or prosecuted.  The approval of the Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which ARRC may suffer, or for which it may be liable, as a result of the acts or omissions of the Contractor, its subcontractors or employees.

2.5	Whenever, in the opinion of the Chief Engineer, the construction may cause a hazard to the safe operation of ARRC, ARRC may, in its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Contractor and its subcontractors from liability for the payment of damages caused by their operations.  ARRC shall be the sole judge of the necessity for, and as to the number and classification of employees required. The Contractor shall reimburse ARRC for the cost and expense incurred in providing such employees.

107-1.08-SECTION 3.  SAFETY REQUIREMENTS

3.1	The safety of personnel, property, rail operations, and the public is of paramount importance in the prosecution of any work on ARRC Property.  The Contractor shall comply with all Federal, State and local governmental regulations (e.g. OSHA, NESC, etc.) applicable to the construction, installation, or maintenance of any Facility.   As reinforcement and in furtherance of overall safety measures to be observed by Contractor (and not by way of limitation), the special safety rules set forth in this SECTION 3 shall be followed while working on ARRC Property.  Further railroad safety information may be obtained from the ARRC Safety Office at 907-265-2440.  Safety information is also available on the ARRC website at www.akrr.com.

3.2.	ARRC flag protection is required before any activity can occur on or near a railroad operating facility such as a track, yard, bridge or shop building.  For incidental work, such as surveying or inspection, an ARRC furnished flagman will provide a safety briefing prior to the commencement of the work   For any activity involving a disturbance or potential disturbance to the track, track embankment, or any railroad facility, ARRC may require the Contractor to submit a specific Railroad Safety Plan prior to startup.  Projects that involve activities that cross the tracks or are longitudinal to the tracks will require a specific Railroad Safety Plan and a one-hour ARRC provided training course for Contractor’s project supervisors prior to the initiation of work on ARRC Property.  Specific information on Railroad Safety Plans may be obtained from the ARRC Safety Office at 907-265-2440.

3.3	The Contractor shall arrange for ARRC flag protection when performing any work within 20 feet of any track.  All work within 20 feet of the track shall cease when a train passes and all Contractor employees shall maintain a distance of at least 20 feet from the track until the train has safely passed.  [See 107-1.08-SECTION 6.3 for definition of when train is “passing” the work site.]  In addition, any work that could come within 20 feet of the track will cease when a train passes.  For example, crane or pile driving activities shall stop when trains pass when the maximum boom and suspended load radius can come within 20 feet of the tracks.  Pile driving shall not be done when trains are passing the work site.  Vehicles and other construction equipment shall not be operated or parked closer than 20 feet from any track without ARRC flag protection.

3.4	In the event Contractor will be performing construction or other activities on or within 20 feet of a railroad track, the Contractor shall be responsible for compliance with applicable Federal Railroad Administration’s Roadway Worker Protection (“RWP”) regulations (49 CFR 214, Subpart C) if its employees qualify as “Roadway Workers”.  Under 49 CFR 214, Subpart C, railroad contractors are responsible for the training of their employees on these regulations.  All RWP related Work shall be conducted in strict compliance with the RWP safety standards set forth in 49 CFR 214, Subpart C and the Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any RWP related Work.

3.5	In the event Contractor will be performing construction or other activities on a railroad bridge, the provisions of 49 CFR 214 regarding bridge worker safety shall apply.  All bridge related work shall be conducted in strict compliance with the bridge worker safety standards set forth in 49 CFR 214 and the Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any bridge related work.

# 107-1.08-SECTION 4.  INSURANCE REQUIREMENTS

4.1 	The Contractor shall procure and maintain at all times while performing work on ARRC Property, and be covered by the types of insurance with the minimum limits as specified in 107-1.08-SECTION 4.4.

4.2	Each policy specified in 107-1.08-SECTION 4.4 shall be:  (1) endorsed to include ARRC as an additional named insured with respect to the performance of the work; (2) endorsed whereby the insurance company will notify ARRC of any material change, cancellation, non-renewal or expiration of the insurance policy in writing not less than thirty (30) days prior to the effective date; (3) endorsed with a waiver of subrogation rights in favor of ARRC; and (4) endorsed with the Alaska Suit Endorsement.

4.3	Prior to commencement of any work on ARRC Property, the Contractor shall deliver to ARRC certificate(s) of insurance showing evidence of the insurance required in 107-1.08-SECTION 4.4.

4.4	Alaska Railroad Corporation Minimum Insurance Requirements.

a.	Commercial General Liability insurance with limits not less than $2,000,000/$4,000,000 Combined Single Limit for Bodily Injury and Property Damage, including coverage for Premises and Operations Liability, Products and Completed Operations Liability, Contractual Liability, and Broad Form Property Damage Liability. Coverage shall not contain any exclusions of Explosion, Collapse, Underground, or Rail Operations.

b.	Automobile Liability insurance on all owned, non-owned, hired and rented vehicles with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

c.	Worker's Compensation insurance in accordance with the statutory coverage required by the State of Alaska and, where applicable, insurance in compliance with any other statutory obligations, whether State or Federal, pertaining to the compensation of injured employees assigned to the Work, including but not limited to Voluntary Compensation, Federal Longshoremen and Harbor Workers Act, and the Federal Employers Liability Act.

d.	If any part of the work to be performed on ARRC Property is located within 100 feet of a railroad track, then the Contractor shall also obtain Railroad Protective Liability insurance (Alaska Railroad Corporation as named insured) with limits of liability of not less than $5,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

# 107-1.08-SECTION 5.  NOTICE

5.1	A pre-construction meeting shall be held with ARRC's Chief Engineer and representatives of the Department, the Contractor and subcontractors prior to the commencement of any work on ARRC Property by the Contractor or its subcontractors.  Contact Judi Shapiro at 907-265-2587 to schedule meeting.  At Department’s request, ARRC representatives will attend a designated time within the Department’s project pre-construction meeting in order to afford Contractor and Department a convenient method of satisfying the foregoing requirement.

5.2	The Contractor shall give written notice to the Chief Engineer not less than ten (10) business days in advance of the commencement of any construction, reconstruction or major maintenance activity on ARRC Property, in order that the necessary arrangements may be made for the protection of ARRC's operations.  This notice shall include a description of the proposed work on ARRC Property, schedule of work, and the names of any Department, Contractor and/or subcontractor personnel who may also be working on ARRC Property.

# 107-1.08-SECTION 6.  FLAG PROTECTION AND PROTECTION OF ARRC TRAFFIC

6.1	Whenever ARRC flag protection is required, it will be provided by ARRC at Permittee/Contractor's expense.  ARRC flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the ARRC rules on flagging.  A minimum of five (5) business days prior notice is required for ARRC to provide flag protection. Contact Crystal Wilson at 907-265-2490.

6.2	ARRC will, during the progress of the work, utilize as many qualified flag people as in the opinion of the ARRC may be required for the adequate protection of ARRC traffic.  All expense for providing such flagpersons shall be paid by the Contractor to ARRC.

6.3	The Contractor shall arrange with ARRC to keep itself informed on the time of arrival of all trains and shall stop any of Contractor's operations which might be or cause a hazard to the safe passage of the train past the site of the work from ten (10) minutes before the expected arrival of the train until the last car of the train has safely passed, unless otherwise determined by the Railroad flagperson on site, if any.

6.4	Track outages will only be approved in exceptional cases for limited durations.  See 107-1.08-SECTION 7.1.c for details.

# 107-1.08-SECTION 7.  TRAIN DELAYS; ANTICIPATED WORK WINDOWS DURING CONSTRUCTION

7.1	All work on ARRC Property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by ARRC.  The ARRC will provide a weekly forecast of train traffic and the ARRC flagpersons will provide daily updates of anticipated train traffic.  Under no circumstances, however, will the ARRC be liable in any way for delays to the Contractor’s work created by any changes or deviations from anticipated train schedules.

a.	ARRC Track Maintenance Work Window:  Railroad section and summer work crews may need access into the work area to perform routine track maintenance work and scheduled summer major track replacement work.  The routine track work is performed as necessary for the safe passage of trains.  Railroad on-track equipment also travels through the project as needed.  Railroad traffic has full and absolute priority over Contractor work except as may be otherwise authorized in writing by ARRC under 107-1.08-SECTION 7.1.c below.

- b.	Train Traffic: The track through the project is very active.  The approximate number of trains in a 24-hour period is given below as an planning tool for Contractor and cannot be relied upon to assume times are available for track outage.  Contractor must obtain prior approval of any period of track outage from ARRC under 107-1.08 SECTION 7.1.c below.

- Summer Season - (May 6 to September 24) Approximate Daily Trains:  2 to 4 scheduled Passenger Trains; ARRC also charters passenger trains, which may run on any day; Up to 3 Freight Trains, 1 Coal Train and up to 2 Work Trains per day.

- Shoulder - (April 1 to May 5 and September 25 to October 28) Approximate Daily Trains:  Up to 2 scheduled Passenger Trains; ARRC also charters passenger trains, which may run on any day; Up to 3 Freight Trains, 2 Work Trains and 1 Coal Train.

- Off Season -  Approximate Daily Trains:  Up to 2 scheduled Passenger Trains; ARRC also charters passenger trains, which may run on any day; Up to 3 Freight Trains, 1 Coal Train and 1 Work or Snow Service Train.

- c.	Tracks out of Service (Track Outages): The work shall be planned so as to minimize track service outages.  The Contractor shall submit a closure plan and request the track outage ten (10) business days prior to the proposed date.  The plan will describe the work to be accomplished, the equipment, manpower and other resources required, and the work schedule, specifying dates and times.  Once approved by ARRC, the Contractor shall follow the plan without any variation whatsoever unless a modification is approved by the Chief Engineer.  ARRC reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  The Contractor shall bear all costs and damages which may result from failure to meet the closure schedule, in addition to the train delay charges provided for in the contract.  As indicated above, ARRC anticipates the longest outage allowed during the summer season will be six (6) hours, and twelve (12) hours in the shoulder and winter seasons.

- The ARRC will not grant any track outages for this project.

- 7.2	Should any of the Contractor's or its subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor by ARRC.

- Passenger trains each:	$50 per minute of delay, 60-minute minimum charge.

- All other rail traffic:		$50 per minute for each delay over five minutes, 30

- minute minimum charge.

- Rail barges, or other		No charge for delays of one hour or less; $1,000 per hour

- connecting carrier vessels:	for each hour or any part of an hour thereafter with a

- minimum charge of $6,000.

- 7.3	Delay time will be taken from the train sheet in ARRC’s Dispatcher's Office, Anchorage (907-265-2421) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

# 107-1.08-SECTION 8.  PROTECTION OF ARRC SIGNAL AND COMMUNICATION LINES

- 8.1	All work on ARRC Property shall be conducted in such a manner as to protect ARRC's signal and communication facilities at all times from outages resulting directly or indirectly from the Contractor's or its subcontractor's operations.

- 8.2	Should any of the Contractor’s or its subcontractor's operations cause outages to said signal or communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

##### Signal and Communication cable:	$1.00 per minute per cable

- 8.3	A minimum charge of $250.00 will be made for each outage plus the total repair costs.  The outage time shall be that as established by ARRC's Test Board, Anchorage.

- 8.4	There shall be no equipment operated or excavation made within 15 feet of any ARRC communication pole guy, anchor, or other signal or communications apparatus unless authorized in advance by the Signals Supervisor.

# 107-1.08-SECTION 9.  ROAD CROSSINGS

- 9.1	Whenever automatic railroad crossing signals are in the work area, these signals must remain in operating condition at all times.  If, as a result of the Contractor's or subcontractor's activities the signals become inoperable, the crossing shall be continuously flag protected until the signals are again operable.  See 107-1.08-SECTION 6 for flagging specifications.

- 9.2	When regular railroad crossings are used as haul routes inside or outside the work area, flagpersons shall be provided by the Contractor for said crossings in all situations at the discretion of the ARRC.

- 9.3	Temporary road crossings may be installed provided the Contractor has acquired from ARRC a temporary road crossing permit for said crossing.  If a requested crossing is not shown on the project plans as approved by ARRC, then it will be at ARRC’s sole discretion whether to allow the crossing.  ARRC shall install a temporary crossing  for this Kern Creek Project.

- 9.4	The temporary road crossing shall be constructed to the length and the standards specified in the temporary road crossing permit.  All protective signs required by ARRC shall be provided and properly maintained by the Contractor.  The temporary road crossing shall be installed under ARRC flag protection in accordance with 107-1.08-SECTION 6 of these specifications.

- 9.5	The flange ways of all road crossings used by the Contractor or its subcontractor as haul routes or temporary road crossings shall be kept clean and free of gravel at all times and shall otherwise be maintained to the satisfaction of the Chief Engineer.

- 9.6	When a temporary road crossing is in use, ARRC flag protection shall be provided at all times.  See 107-1.08-SECTION 6 for specifications.

- 9.7	When a temporary or private road crossing is not in use, the Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

- 9.8	When not in use during the winter season, the temporary road crossing shall be removed.  Upon completion of the work or termination of the crossing permit, the temporary crossing shall be removed and the area restored to its original condition.

- 9.9	The Contractor agrees that all others using the private road crossing, except ARRC and its employees, shall be considered agents of the Contractor.

- 9.10	Sight Triangles at road crossings shall be maintained by Contractor free of vegetation and other obstructions to vision in accordance with the table entitled "Sight Triangle Distance" attached and as otherwise established and revised from time to time by ARRC.

- 9.11	Temporary public road crossings must be included in a traffic control plan submitted by the Contractor to the Department for review and approval prior to constructing the crossing. The traffic control plan will recognize the necessary safety precautions required around railroad crossings. For example, traffic may not be backed up onto the crossing from highway flagging or from adjacent traffic lights.

- Highway flagmen are not qualified to provide railroad flag protection.

# 107-1.08-SECTION 10.  POWER AND COMMUNICATION LINES

- 10.1	All power and communication lines shall be designed and constructed in accordance with the current edition of the National Electric Safety Code (NESC).

- 10.2	Underground power and communication lines shall be installed in accordance with 107-1.08-SECTION 11 of these specifications.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

- 10.3	The minimum clearance above the top of rail of ARRC track shall be in accordance with the handbook referenced in 107-1.08-SECTION 11.1, plus 6” to allow for future grade raises.

- 10.4	The minimum clearance above ARRC communication lines shall be in accordance with the handbook referenced in 107-1.08-SECTION 11.1.

- 10.5	Additional lines may not be added, or the characteristics of the line(s) changed without the prior written approval of ARRC's Chief Engineer.

- 10.6	Wires shall be strung across ARRC tracks only when ARRC flag protection is provided in accordance with 107-1.08-SECTION 6 of these specifications.

- 10.7	No wires shall be strung across ARRC's communications lines without first receiving prior written approval from ARRC's Signals Supervisor, and such work must be accomplished only at a time and in a manner prescribed by said Signals Supervisor.

# 107-1.08-SECTION 11.  UNDERGROUND UTILITIES

- 11.1	All underground utilities, including culverts, pipelines, and underground power and communication lines, on ARRC Property shall conform to the current American Railway Engineering and Maintenance-of-way Association (AREMA) Specifications.

- 11.2	Unless the Chief Engineer authorizes another method in advance and in writing, all underground utilities shall be installed under tracks and roads by boring, jacking or tunneling.

- 11.3	Boring, jacking or tunneling shall be done under ARRC tracks only when ARRC flag protection is provided in accordance with 107-1.08-SECTION 6 of these specifications.

- 11.4	The proposed plan for boring, jacking or tunneling shall be approved by the Chief Engineer prior to commencing the operation.

- 11.5	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring and/or cribbing as necessary.

# 107-1.08-SECTION 12.  OPEN TRENCHING

- 12.1	Only when authorized in advance and in writing by ARRC shall any portion of the track be removed to allow trenching for installation of the Facility.

- 12.2	If allowed to open trench, the track may be removed from service only at the time authorized by the Chief Engineer and shall be restored to service within the time period specified by the Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with 107-1.08-SECTION 7 of these specifications, whichever is greater, and shall be collected from the Contractor.

- 12.3	All track work shall be accomplished by qualified track persons.

- 12.4	Only that portion of the track structure necessary to excavate, stockpile and install the Facility shall be removed.  All track material removed shall be handled, stockpiled and relayed in a manner to avoid damage.  Any material that is damaged shall be replaced by the Contractor at its own expense.

- 12.5	The backfill of the trench under the track and in the road bed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction shall be in one foot lifts with a compaction of 95% of maximum density in the area affecting the road bed prism.

- 12.6	The ballast used in replacing the track shall be equal in depth and quality as that which was removed.  The track shall be relayed and brought to original grade in accordance with standard ARRC practices.  The track shall be resurfaced as often as necessary for a period of 12 months after completion of construction to remove any settlement that may have occurred.

# 107-1.08-SECTION 13.  EXCAVATIONS

- 13.1	Unless authorized in advance and in writing by ARRC, the top of any excavation shall not be within 20 feet of the centerline of any track, nor shall any excavation exceed 10 feet in depth regardless of its proximity to track.

- 13.2	No water shall be allowed to stand in open excavations in the track area.

- 13.3	Bridging and shoring shall be adequate to safely carry ARRC traffic and the decision of the Chief Engineer pertaining to same shall be final.

- 13.4	All open excavations shall be continuously protected by flags, flares, barricades or watchpersons, as directed by ARRC.

- 13.5	No excavation shall be left open more than three days, unless authorized by the Chief Engineer.

- 13.6	ARRC embankments and cut slopes shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

- 13.7	ARRC ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

# 107-1.08-SECTION 14.  ARRC INSPECTIONS

- 14.1	ARRC may furnish an inspector during the periods of construction on ARRC Property.  The ARRC inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The ARRC inspector will work directly with the representatives of the Department and Contractor and the decision of the ARRC inspector in matters pertaining to ARRC operations and safety shall be final.  In the event more than one shift is worked, an ARRC inspector will be required for each shift.  Presence or absence of an ARRC inspector shall not relieve the Contractor of liability for damage done to property of ARRC, or the property of ARRC lessees or permittees having installations on ARRC Property.  All ARRC cost and expense for furnishing said inspector(s) shall be collected from the Permittee/Contractor.

# 107-1.08-SECTION 15.  USE OF EXPLOSIVES

- 15.1	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding same.

- 15.2	No blasting of any kind will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, ARRC flag protection in accordance with 107-1.08-SECTION 6 of these specifications shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

# 107-1.08-SECTION 16.  SNOW REMOVAL

- 16.1	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of ARRC; (2) where it interferes with the normal operation of the automatic crossing signals; or (3) where it impairs the visibility of either highway or rail traffic at the crossing.

- 16.2	Snow removal operations shall be conducted in accordance with 107-1.08-SECTION 3 of these specifications.

# 107-1.08-SECTION 17.  CLEAN-UP

- 17.1	At all times, all work and activities on ARRC Property shall be accomplished in such a manner as to keep the ARRC Property in a neat, orderly and safe condition satisfactory to ARRC.

- 17.2	Upon completion of Contractor’s work, all equipment and unused materials shall be removed and the ARRC Property shall be left in a neat and clean condition satisfactory to ARRC.

- 17.3	Should the Contractor or its subcontractor fail to comply with 107-1.08-SECTIONS 17.1 and 17.2 above, ARRC may perform the required clean-up.  All ARRC costs and expenses for performing this work shall be collected from the Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

If water for construction purpose is required from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  R7 (05/29/02)

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following paragraphs:

  - Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:  Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

  - Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.  E35 (01/27/07)

SECTION 108

PROSECUTION AND PROGRESS

Special Provision

108-1.01 SUBLETTING OF CONTRACT.   Replace the last sentence in the second paragraph with the following:  The Engineer will determine the value of the subcontracts based upon reasonable value.

Delete paragraph four and replace with the following:

Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract.  The certification will be accepted by the Department in lieu of written approval of subcontracts.  The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

  - The Department is furnished with one completed Contractor Self certification, Form   25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

  - The subcontractors have submitted a Bidder Registration, Form 25D-6;

  - The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

  - The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

  - Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

R57 (01/02/08)

108-1.07 FAILURE TO COMPLETE ON TIME.  Delete the first sentence of the first paragraph and substitute the following: For each calendar day that the work remains incomplete after the expiration of the Contract time or the interim completion date as indicated in subsection 105-1.18 Interim Completion, the liquidated damages per day give in the table below shall be deducted from monies due the Contractor.  For the purposes of computing liquidated damages calendar days will be counted between November 1st and April 30th as well as between May 1st and October 31st.

Replace Table 108-1 with the following

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Completion Date | Daily Charge |
| --- | --- |
| Interim Completion Date | $1,000 |
| Contract Completion Date | $550 |

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence:  “, CD, or a USB device.”  R14 (04/31/05)

Delete subsection 109-1.04.

109–1.05 COMPENSATION FOR EXTRA WORK.

Under item 3.  Equipment, item a. add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  R14 (04/31/05)

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16.  E11 (06/30/04)

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:  Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 6 inches.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at (907) 269-7590.  (03/29/01)R84

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION.  Construct one or more layers of plant-mixed hot asphalt concrete pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

###### MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN.  Meet the requirements of Table 401-1 for the Job Mix Design performed according to ATM 417.

TABLE 401-1

hOT MIX Asphalt Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| Stability, pounds | 1800 min. | 1200 min. |
| Flow, 0.01 inch | 8-14 | 8-16 |
| Voids in Total Mix, % | 3-5 | 3-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 |
| Percent Voids Filled with Asphalt (VFA) | 65-75 | 65-78 |
| Asphalt Content, min. % | 5.0 | 5.0 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |
| Type I Type II Type III, IV | 12.0 13.0 14.0 | 11.0 12.0 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt (calculated by weight of mix).

The approved Job Mix Design will specify the target values for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the hot mix asphalt, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broad band limits shown in Table 703-3, for the type of hot mix asphalt specified.  For acceptance testing, hot mix asphalt concrete mixture will have the full tolerances in Table 401-2 applied.  Except the tolerances for the No. 200 sieve, the tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3.  The tolerance limits for the No. 200 sieve will be confined by the broad band shown in Table 703-3.  Tolerance limits will not be applied to the largest sieve specified.

Do not produce hot mix asphalt for payment until the Engineer approves the Job Mix Design.  Do not mix asphalt produced from different plants.

Use Hot Mix Asphalt Type II, Class B, minimum, for temporary pavement.

Submit the following to the Engineer at least 15 days before the production of hot mix asphalt:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each type of hot mix asphalt specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the hot mix asphalt.  Include name of product, manufacturer, test results of the applicable quality requirements of subsection 702-2.01, manufacturer's certificate of compliance according to subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate type and class of hot mix asphalt specified and establish the approved Job Mix Design that will become a part of the Contract.

No payment for hot mix asphalt for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved.  Approved changes apply only to hot mix asphalt produced after the submittal of the changes.

Changes. Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design.  Submit changes and new samples in the same manner as the original submittal.

401-2.02 AGGREGATES. Conform to subsection 703-2.04.

Use a minimum of three stockpiles for crushed hot mix asphalt aggregate (coarse, intermediate, and fine).  Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Provide the grade of asphalt cement specified in the Contract meeting the applicable requirements of Section 702.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.                  Manufacturer’s certificate of compliance (106-1.05).

2.                  Conformance test reports for the batch (Section 702).

3.                  Batch number and storage tanks used.

4.                  Date and time of load out for delivery.

5.                  Type, grade, temperature, and quantity of asphalt cement loaded.

6.                  Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design.  At least 70% of the aggregate must remain coated when tested according to ATM 414.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the hot mix asphalt according to subsection 106-1.03.  Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits the Contractor’s right to a retest under subsection 401-4.02.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the hot mix asphalt.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the hot mix asphalt on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place hot mix asphalt unless the roadway surface temperature is 40 °F or warmer.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of hot mix asphalt buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of hot mix asphalt.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before hot mix asphalt production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the hot mix asphalt.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling conditions meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT.  Haul hot mix asphalt in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

Cover the hot mix asphalt in the hauling vehicle, when directed.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip the hopper with a distribution system to place the hot mix asphalt uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the hot mix asphalt.  Heat and vibrate screed extensions.  Place auger extensions within 20 inches of the screed extensions or according to written manufacturer’s recommendations.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous plant mix when that mix is carried from the paver hopper back to the paver augers.  The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified bituminous pavers:

(1)              Blaw-Knox bituminous pavers shall be equipped with the Blaw-Knox Materials Management Kit (MMK).

(2)              Cedarapids bituminous pavers must have been manufactured in 1989 or later.

(3)              Caterpillar bituminous pavers shall be equipped with deflector plates.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Operate rollers according to manufacturer's instructions.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact hot mix asphalt and reverse without backlash.

Use fully skirted pneumatic-tire rollers with a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications.  Before applying tack coat to the existing surface, clean out loose material from cracks in existing pavement wider than 1 inch in width full depth then fill using asphalt concrete tamped in place.  Clean, wash, and sweep existing paved surfaces of loose material.

Preparation of a milled surface,

        	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than ½-inch with Asphalt Concrete, Type IV.  No density testing is required for the leveling course material.  The Engineer will inspect and accept this material.

        	If planing breaks through existing pavement remove 2 inches of existing base and fill with Asphalt Concrete, Type II.  Notify the Engineer of pavement areas that might be considered thin or unstable during pavement removal.

The Engineer must approve the existing surface before applying tack coat.  Clean existing pave surfaces of loose material.

Before placing the hot asphalt mix, uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material meeting Section 402.

Allow prime coat to cure and emulsion tack coat to break before placement of hot mix asphalt on these surfaces.

401-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the hot mix asphalt, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the hot mix asphalt to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Hot mix asphalt concrete containing soot or fuel is considered unacceptable according to subsection 105-1.11.

401-3.10 MIXING.  Combine the aggregate, asphalt cement and additives in the mixer in the amounts required by the Job Mix Design.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

Mix the hot mix asphalt within the temperature range determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided that the characteristics of the hot mix asphalt are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the hot mix asphalt are causes for rejection.

401-3.12 PLACING AND SPREADING.  Place the hot mix asphalt upon the approved surface, spread, strike off, and adjust surface irregularities.  Use asphalt pavers to distribute hot mix asphalt, including leveling courses.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer may evaluate the hot mix asphalt immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25oF lower than the surrounding hot mix asphalt are likely to produce areas of low density.  Any thermal images or thermal profile data will become part of the project record and shared with the Contractor.  The Contractor shall immediately adjust laydown procedures to correct the problem.

Use hand tools to spread, rake, and lute the hot mix asphalt in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland concrete curbing until it has cured for at least 72 hours.

Place hot mix asphalt over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION.  Thoroughly and uniformly compact the hot mix asphalt by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each type of hot mix asphalt, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed in according to WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on hot mix asphalt that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS.  Minimize the number of joints.  Place and compact the hot mix asphalt to ensure a continuous bond, texture, and smoothness between adjacent sections of the hot mix asphalt.

Remove to full depth improperly formed joints resulting in surface irregularities, replace with new hot mix asphalt, and thoroughly compact.

Precut pavement removal to a neat line with a power saw or by other method approved by the Engineer.

Form transverse joints by saw cutting back on the previous run to expose the full depth of layer with a power saw or other method approved by the Engineer or use a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 12 inches from the edge of the stripe.

Uniformly coat joint surfaces below the final lift with tack coat conforming to Section 703 before placing any fresh HMA against the joint.

For the top layer of hot mix asphalt, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the hot mix asphalt is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and an application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will be measured but not evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to subsection 401-4.03.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch to the nearest 0.1 inch.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove hot mix asphalt that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch. Remove defective hot mix asphalt for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh hot mix asphalt according to subsection 401-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the Hot Mix Asphalt pay item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

b)	By the area of final hot mix asphalt surface.

Asphalt Price Adjustment.  Calculated by quality level analysis under subsection 401-4.03.

Asphalt Cement.  By the ton, as follows.

1.	Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASTHO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the Job Mix Design.

2.	Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing hot mix asphalt for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineers presence before and after unloading.  If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement.  The Engineer will determine the method.  The weight of asphalt cement in waste hot mix asphalt will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Method 1 will be used for determining asphalt quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt content specified in the Job Mix Design.

Job Mix Design. When specified, Contractor furnished Job Mix Designs will be measured at one according to the hot mix asphalt class and type.

Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

Longitudinal Joint Adhesive and Sealing.  By the linear foot of longitudinal joint.

Preleveling.  By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of each class and type of hot mix asphalt produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  Hot mix asphalt quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.

Hot mix asphalt quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (also for approaches and temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any hot mix asphalt that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

1. 	Asphalt Cement.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, at the end of the auger, or from the windrow according to WATC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  Hot mix asphalt samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AAHSTO T2, or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the hot mix asphalt.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

- Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.  Cut full depth core samples from the finished hot mix asphalt within 24 hours after final rolling.  Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Use a core extractor to prevent damage to the core.

The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core hot mix asphalt on bridge decks.  Backfill and compact voids left by coring with new hot mix asphalt within 24 hours.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location the panel completing the joint is cored for mat density acceptance testing.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for

gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

5.	Asphalt Cement.

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 199 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

The total asphalt cement price adjustment is the sum of the individual lot price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment - Quality.

SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

Replace subsection 603-1.01 with the following:

603-1.01 DESCRIPTION.  Remove and replace portions of the existing pipes at Kern Creek as shown on the Plans.  Install 200 feet of 120 inch pipe (or length as directed by the Engineer).

603-3.01 GENERAL. Add the following:  This item of work shall be done according to applicable Sections of the Specifications.

603-4.01 METHOD OF MEASUREMENT.  Add the following:

5.	Item 603(23-120) will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Payment of item 603(23-120) includes all materials, labor, and equipment required to remove and replace portions of the existing 2 pipes at Kern Creek. This item includes mobilization and demobilization, clearing and grubbing, removal of pavement, removal of temporary pavement, excavation, disposal of unusable excavation, aggregate base course, hot mix asphalt, temporary pavement, removal and replacement of guardrail with end terminal (ET 2000), riprap, detour, necessary stream diversion, surveying, protection of existing utilities, traffic maintenance, and striping.  Work also includes material, excavation, maintenance, and removal of temporary road/detours.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

603(23-120)	120 Inch Pipe	Lump Sum

SECTION 606

GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an overall length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacturer:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval before ordering the markers.

606-3.02 POSTS.  Delete the first two numbered items in this subsection and substitute the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 14 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and substitute the following:  Notify the Engineer a minimum of 5 days before removing guardrail for disposal.  The Engineer will notify ADOT&PF M&O (907-338-1466) and have an M&O representative physically identify portions of guardrail to be salvaged.  Deliver guardrail and associated hardware designated for salvage to the ADOT&PF M&O yard located in Girdwood.  Remaining items removed becomes the Contractor’s property.  (06/12/03)R259

Add the following subsections:

606-3.09 FLEXIBLE MARKERS.  For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.  (4/06/06)R45

SECTION 617

RAILROAD CROSSINGS

Special Provision

Add the following subsection:

617-3.02 TEMPORARY RAILROAD CROSSING.  The Alaska Railroad will install a temporary railroad crossing.

SECTION 619

SOIL STABILIZATION

Special Provisions

619-2.01 MATERIALS.  Add the following:  Straw rolls, also commonly called straw wattles, shall be comprised of ultra violet degradable plastic netting and rice straw.  The Contractor shall provide the Engineer a certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting, certification of the weed free status from the manufacturer, and a sample of the material.  Furnish samples of the proposed materials to the Engineer seven days before the scheduled installation.

Keep rolled matting materials elevated off the ground and adequately covered to protect from the following: construction damage, precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or strong basis, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

619-3.02 APPLICATION.  Add the following:  Install Straw Rolls as indicated on the Plans.

In the vicinity of stream crossings, in addition to the straw rolls, apply a 4 inch layer of stockpiled organs with hydromatting (bonded fiber matrix) and fertilizer.

Apply 20-20-10 fertilizer at the rate of 12 pounds per MSF.

Apply mulch and tackifier at the following pounds per MSF:

| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| --- | --- | --- |

619-4.01 METHOD OF MEASUREMENT.  Add the following:  Straw rolls will not be measured for payment.

619-5.01 BASIS OF PAYMENT.   Replace this subsection with the following:  Straw rolls will be subsidiary to 641 items.

Special Provisions

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.  Plan, provide, inspect, and maintain control of erosion, sedimentation, water pollution, and hazardous materials contamination.

Utilities will be relocated by others concurrently with construction of this project.  The Contractor will be responsible for controlling sediment and erosion and stabilizing areas disturbed during underground utility relocation.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands.  BMP include temporary or permanent structural and nonstructural devices and practices.  Common BMP can be found on the EPA website: National Menu of Storm Water Best Management Practices.  [www.epa.gov/npdes/stormwater/menuofbmps]

- ESCP (Erosion and Sediment Control Plan).  The ESCP is a project specific document that illustrates measures to control erosion and sediment problems on a project.  The ESCP normally consists of a general narrative and a map or site plan.  It is developed by the Department and included in the project plans and specifications.  It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization.  A point in time when  ground disturbing activities are complete and permanent erosion and sediment controls are established and functional.  The stabilized site is protected from erosive forces of raindrop impact and water flow.  Typically,  unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan).  The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- eNOT. Electronic Notice of Termination of coverage under the NPDES General Permit.  Use EPA Form 3510-13 found at www.epa.gov/npdes/stormwater/cgp

- NPDES General Permit. The Storm Water General Permit for Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES).  It requires an approved SWPPP and NOIs listed as active status by the EPA before ground disturbing activities for the project.

- SPCC Plan (Spill Prevention, Control and Countermeasure).  The Contractor’s detailed plan for oil spill prevention and control measures that meets the requirements of 40 CFR 112.

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management.  The SWPPP is developed by the Contractor and identifies specific areas where erosion may occur, describes site specific controls to prevent erosion and manage sediment and establishes a record of the installation and removal of these controls.  The approved SWPPP replaces the ESCP.

641-1.03 REFERENCES.

The following websites have up to date information about erosion, sediment and pollution control.

Developing the SWPPP.  EPA.  January 2007.  Includes a SWPPP template in WORD [www.epa.gov/npdes/swpppguide]

National Menu of Storm Water Best Management Practices.  EPA.   [www.epa.gov/npdes/stormwater/menuofbmps]

International Erosion Control Association website [www.ieca.org/Resources/Resources.asp]

Construction Industry Compliance Assistance Center website  [www.CICAcenter.org/bmps.html]

641-1.04 SUBMITTALS.  Submit two copies each of the SWPPP and HMCP to the Engineer for approval.  Submit one copy of the SPCC Plan (if required under subsection 641-2.03) to the Engineer.  Sign submittals.  Deliver these documents to the Engineer.

The Department will review the SWPPP and HMCP submittals within 14 calendar days. Submittals will be returned to the Contractor as either requiring modification, or as approved by the Department.  The approved SWPPP must contain certifications, and be signed according to the Standard Permit Conditions of the NPDES General Permit.  Approval of the SWPPP must be received before submitting the eNOI to the EPA.

For projects that disturb five acres or more of ground, submit a copy of the approved and signed SWPPP, with the required permit fee to the Alaska Department of Environmental Conservation (ADEC) Storm Water Coordinator.  Transmit proof of this submission to the Engineer.

For projects that disturb one acre or more, submit the signed eNOI to EPA.  Submit copies of the signed eNOI receipt to the Engineer and to ADEC.  Transmit proof of the ADEC submission to the Engineer.  The Department will transmit the Department’s NOI to the EPA.  Allow adequate time for state and federal processing, before beginning ground disturbing activities.

The active status NOIs, approved SWPPP, approved HMCP, and submitted SPCC Plan (when required) become the basis of the work required for the project’s erosion, sediment, and pollution control.

Submit the signed eNOT to EPA with a copy to the Engineer when notified by the Engineer that the Project is stabilized.  The Department will transmit the Department’s eNOT to the EPA.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Prepare a Storm Water Pollution Prevention Plan.  Use the Department's ESCP to develop a SWPPP based on scheduling, equipment, and use of alternative BMPs.  The SWPPP Preparer must visit the project site before preparing the SWPPP.  The plan must include both erosion control and sediment control measures.  The plan must address first preventing erosion, then minimizing erosion, and finally trapping sediment before it leaves the project site.

The SWPPP must follow the format presented in Appendix A of Developing Your Storm Water Pollution Prevention Plan (EPA, January 2007) found at http://cfpub.epa.gov/npdes/stormwater/swppp.cfm.

The plan must address site specific controls and management plan for the construction site as well as for material sites, waste disposal sites, haul roads, and other affected areas, public or private.  The plan must also incorporate the requirements of the project permits.

The Contractor is responsible for identifying, in their SWPPP, other work that is on going or will be undertaken within or adjacent to the project during the contract period and to coordinate erosion and sediment control measures with other operators.

Specify the line of authority and designate a field representative for implementing SWPPP compliance.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances.  (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of hazardous materials, including office materials, to be used and/or stored on site, and estimated quantities.  Detail a plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where storage, fueling, and maintenance activities will take place, describe the maintenance activities, and list controls to prevent the accidental spillage of oil, petroleum products, and other hazardous materials.

Detail procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills.  Detail a plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate a field representative for spill response and one representative for each subcontractor.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE (SPCC) PLAN REQUIREMENTS.  Prepare and implement a SPCC Plan when required by 40 CFR 112, including:

Control

Prepare and implement a SPCC Plan when required by 40 CFR 112, including:

- When oil spills may reach navigable waters; and

- Total above ground oil storage capacity is greater than 1,320 gallons.

Prevention and Countermeasures

Comply with 40 CFR 112 and address the following issues in the SPCC Plan:

- Operating procedures that prevent oil spills;

- Control measures installed to prevent a spill from reaching navigable waters; and

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill.

Self certify the SPCC Plan if the total above ground oil storage capacity is 10,000 gallons or less, and the requirements for self certification in 40 CFR 112 is met.  Otherwise the SPCC Plan must be certified, stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska.

641-3.01 CONSTRUCTION REQUIREMENTS.  On projects with 1 acre or more of ground disturbing activity, do not begin construction activities until the EPA has acknowledged receipt of the Contractor’s NOI and Department’s NOI, and has listed both as active status.  The EPA will post the status of the NOIs on the EPA website.  On projects with less than 1 acre of ground disturbing activity, where submittal of an eNOI to EPA is not required, do not begin construction activities until authorized by the Engineer.

Postings.

Post at the construction site:

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	Name and phone number of the Contractor’s local contact person, and

3.	Location of a SWPPP available for viewing by the public.

The above notices must be posted at publicly accessible locations.  At a minimum post notices at the BOP, EOP, near the intersection of the highway with a major side street, and the Project Office.

Comply with requirements of the approved HMCP, the submitted SPCC Plan, and state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and other materials hazardous to the land, air, water, and organic life forms.  Perform fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.  Report oil spills as required by federal, state and local law, and as described in the SPCC Plan.

Comply with requirements of the NPDES General Permit, implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.  Maintain temporary and permanent erosion and sediment control measures in effective operating condition.

Coordinate BMPs with Utility Companies doing work in the project area.

Inspections

Perform inspections and prepare inspection reports to comply with the project SWPPP and the NPDES General Permit.

- Joint Inspections.  Before start of construction, conduct a joint on site inspection with the Engineer, the SWPPP Preparer, and the Contractor’s field representative to discuss the implementation of the SWPPP.

Conduct the following additional joint on site inspections with the Engineer:

a.	During construction, inspect the following at least once every seven days and within 24 hours of the end of a storm exceeding ½ inch in 24 hours (as recorded at or near the project site):

(1)	Disturbed areas that have not been finally stabilized

(2)	Areas used for storage of erodible materials that are exposed to precipitation

(3)	Sediment and erosion control measures

(4)	Locations where vehicles enter or exit the site

(5)	Offsite materials sources and waste sites

(6) 	Staging and equipment storage areas.

b.	During construction, the SWPPP preparer shall review the Project Site, Materials Sites, Waste Sites, and the SWPPP for conformance with the NPDES General Permit at least once per month and after every major change in earth disturbing activities for compliance with the General Permit.

c.	Before winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

d.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 1/2 inch or greater.  The Engineer may waive monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports.  Prepare and submit, within three working days of each inspection, a report on the DOT&PF SWPPP Construction Site Inspection Report (Form 25D-100 - 4/08).  At a minimum the report will contain the following information:

a.	A summary of the scope of the inspection

b.	Name(s) of personnel making the inspection

c.	The date of the inspection

d.	Observations relating to the implementation of the SWPPP

e.	Any actions taken as the result of the inspection

f.	Incidents of noncompliance

Where a report does not identify any incidents of noncompliance, certify that the facility is in compliance with the SWPPP and NPDES General Permit.

The Contractor and the Engineer will sign the report according to the Standard Permit Conditions of the NPDES General Permit.  Include reports as an appendix to the SWPPP.

Record Retention

Keep the SWPPP up to date at all times.  The SWPPP shall denote the location, date of installation, date maintenance was performed, and the date of removal for BMPs.  It shall also contain copies of inspection reports and amendments.

Maintain the following records as part of the SWPPP:

1.	Dates when major grading activities occur;

2.	Dates when construction activities temporarily or permanently cease on a portion of the site; and

3.	Dates when stabilization measures are initiated.

4.	Daily precipitation as measured from an on site rain gauge.

Provide the Engineer with copies of SWPPP revisions, up dates, records, and inspection reports at least weekly.

Retain copies of the SWPPP and other records required by the NPDES General Permit for at least three years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Amendments

Submit amendments to the SWPPP to correct problems identified as a result of:

1.	Storm or other circumstance that threatens water quality, and

2.	Inspection that identifies existing or potential problems.

Submit SWPPP amendments to the Engineer within seven days following the storm or inspection.  Detail additional emergency measures required and taken, to include additional or modified measures.  If modifications to existing measures are necessary, complete the implementation within seven days.

Stabilize areas disturbed after the seeding deadline within seven days of the temporary or permanent cessation of ground disturbing activities.

## Notice of Termination

For projects that disturb one acre or more of land, submit the signed eNOT to EPA with a copy to the Engineer when the Engineer notifies that:

- The Project site (including material sources, and disposal sites) has been finally stabilized and that storm water discharges from construction activities authorized by this permit have ceased, or

- The construction activity operator (as defined in the NPDES General Permit) has changed.

641-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the Contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1), (2), and (5) or items 641(1), (3), (4), and (5).

- Item 641(1) Erosion and Pollution Control Administration.  At the Contract lump sum price for administration of work under this Section.  Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting, and record keeping.

- Item 641(2) Temporary Erosion and Pollution Control.  At the prices specified in the Contract or as provided in the Directive authorizing the work to install and maintain temporary erosion, sedimentation, and pollution control measures.

- Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures required to complete the project according to Plan and with the BMP, the ESCP, and the original approved SWPPP and HMCP.

- Item 641(4) Temporary Erosion and Pollution Control Amendments.  At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures.  Work paid under this Item will be shown as amendments to the original approved SWPPP or HMCP.

- Item 641(5) Erosion and Pollution Control Price Adjustment.  The total value of this Contract will be adjusted as specified in subsection 641-3.01.  In addition, a price adjustment equivalent to penalties levied against the Department by the EPA or other state and federal agencies for violations of the Clean Water Act and the NPDES General Permit will be made if the Department is issued a Notice of Violation (NOV) by these agencies.  This price adjustment is the actual cost of fines levied against the Department.  An amount equal to the maximum fine for the violation will be withheld temporarily until the actual cost of the fine is known.  The difference, excluding price adjustments will be released by the Engineer upon satisfactory completion of the requirements of the NPDES General Permit.  The Contractor is responsible for the payment of the Contractor’s fines.

Temporary erosion and pollution control measures that are required at Contractor furnished sites are subsidiary.

Work that is paid for directly or indirectly under other pay items will not be measured and paid for under this Section, including but not limited to dewatering, shoring, bailing, installation and removal of temporary work pads, temporary accesses, temporary drainage pipes and structures, and diversion channels.

Perform temporary erosion and pollution control measures that are required due to negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for the Contractor’s convenience, at the Contractor’s expense.

Permanent erosion and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Failure

If the Contractor fails to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend earthwork operations and withhold monies due on current estimates for such earthwork items until aspects of the work are coordinated in a satisfactory manner.

If there is failure to:

- Pursue the work required by the approved SWPPP,

- Respond to inspection recommendations and/or deficiencies in the SWPPP, or

- Implement erosion and sedimentation controls identified by the Engineer,

The Contractor will be assessed a permanent price adjustment of $500 per day for each day of nonaction.  In addition, the Engineer may, after giving written notice, proceed to perform the work and deduct the cost thereof, including project engineering costs, from progress payments under item 641(5).

Payment will be made under:

641(1) 	Erosion and Pollution Control Administration 	Lump Sum

641(2) 	Temporary Erosion and Pollution Control 	Contingent Sum

641(3) 	Temporary Erosion and Pollution Control 	Lump Sum

641(4) 	Temporary Erosion and Pollution Control Amendments 	Contingent Sum

641(5)	Erosion and Pollution Control Price Adjustment	Contingent Sum

(05/08/08)R272

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following as a third paragraph:

Illuminate construction activities listed in Table 643-3 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS.  Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work: Work occurring between sunset and sunrise on all days except the “No Lighting Required” period shown in the table below:

| Latitude | No Lighting Required |  | Nearby |
| --- | --- | --- | --- |
| (degrees) | Start | End | Cities |
| < 61 | Lighting Required All Year |  | Everything S of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle City |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14 (03/15/06)

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following: A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the no street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. R222 (05/25/07)

643-1.04 WORKSITE SUPERVISOR.  Add the following to Item 2. Duties:

i. Supervise lighting of Night Work.  ES14 (03/15/06)

Standard Modifications

643-2.01 MATERIALS.  Under Item 16. Flagger Paddles, replace the last sentence with the following:  Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.  E56 (05/01/07)

Special Provisions

643-2.01 MATERIALS.  Replace No. 12 with the following:

12.		Portable Changeable Message Board Signs.  Use new truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign with the following:

a.		Message sign panel large enough to display 3 lines of 18 inch high characters.

b.	Ten character display per message line.

c.	Fully programmable message module.

d.	Remote Control Cellular, Wireless RF, Landline.

e.	A waterproof, lockable cover for the controller keyboard.

f.	Capacity for electric/hydraulic sign raising or lowering.

g.	Radar over speed detection.

h.	Variable flash and sequence rates.

i.	LED display, using ITE Amber/Yellow.

j.	The capacity for a minimum of 150 pre-programmed messages.

k.	Operate with a battery pack a minimum of 55 hours under full load.

l.	Power cords shall comply with the National Electrical Code Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter.   The cord must have an integral GFCI Protection located either in the attachment plug or within 12 inches of the plug.

Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.  R222 (05/25/07)

Standard Modifications

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as becoming aware of the accident.  E56 (05/01/07)

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business accesses during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  Traffic may be maintained on a continuous gravel surface for 1,000 feet.

Pave lanes next to the median first.  Pave lanes next to exit and entrance ramps last.  Place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps.  Do not open the roadway to traffic until slope wedges are in place.

R222 (05/01/07)

Standard Modification

643-3.04 TRAFFIC CONTROL DEVICES.

In the sixth paragraph and also in Item 4.b., delete: “ATTSA” and replace with “ATSSA”.  E56 (05/01/07)

Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.

Delete the first sentence of the eighth paragraph and substitute the following: Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to item 1. Embankments.:  Close trenches and excavations at the end of each continuous work shift.

Add the following to item 3. Fixed Objects.:  Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 4.b. and replace with the following:  Flagger Certification by ATSSA

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with the following:  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to subsection 105-1.01 Authority of the Engineer.

Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-5,000 | $30 |
| 5,001+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

Maintain one lane traffic throughout the day other than full road closures.

Lane restrictions, if allowed, shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 1/4 mile (1,320 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 20 minute stopped delay, 80 vehicles, or 1/2 mile (2,640 feet) of traffic detained, will be allowed for motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  R222 (05/25/07)

Add the following new subsection:

643-3.10 LIGHTING OF NIGHT WORK.

Illuminate the night work areas specified in Table 643-2 to the light levels specified.

Table 643-2 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

Table 643-2 Night Work Illumination Level and Area of Coverage

| Type of Work/ Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): | Two balloon lights of at least 2000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |
| 1) with roads with ADTs over 10,000 or |  |
| 2) that are controlled by portable signals or flaggers |  |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to meet required lighting equipment or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-2.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.  ES14 (03/15/06)

Standard Modification

- Add the following new subsection:

643-3.11. HIGH VISIBILITY CLOTHING.  Ensure workers within project limits wear an outer visible surface or layer that complies with the following requirements:

- Standards.

Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

- Labeling.

Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.

Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.

Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.

Wear raingear tops and bottoms conforming to requirements of in this subsection 643-3.11.

- Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility clothing.

- Condition.

Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.  E56 (05/07/07)

Special Provision

Add the following subsection:

643-3.12 DETOUR.  Construct detour to accommodate WB-67 vehicle through the project.

643-4.01 METHOD OF MEASUREMENT.  Replace the second sentence of Item 2 with the following: Special Construction Signs are measured by the total area of legend bearing sign panel, as determined under subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule.

Add the following:

Add the following:  No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2) Traffic Maintenance.  (05/05/08)R222

Standard Modification

643-5.01 BASIS OF PAYMENT. 	Add the following:  Payment for high visibility garments for workers is subsidiary to other items.  E56 (05/01/07)

Special Provisions

643-5.01 BASIS OF PAYMENT.   .   Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $24.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $0.75 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

Add the following:

- Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14 (03/15/06)

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $41/hour.  The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices according to subsection 109-1.05 Compensation for Extra Work.  (05/05/08)R222

Delete Item 643(15) and substitute the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging 	Contingent Sum

(05/05/08)R222

## SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

R199 (01/02/08)

Replace subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.

Coarse Aggregate (retained on the No. 4 sieve). Crushed stone or crushed gravel consisting of sound, tough, durable rock of uniform quality.  Remove natural fines passing a #4 sieve before crushing aggregates for Type V or VH asphalt concrete mixtures.  Free from clay balls, organic matter, and other deleterious material.  Not coated with dirt or other finely divided mineral matter.  Meet the following requirements (note A or B indicate class of mix, see Table 401-1), the Engineer may modify the fracture requirements if the hard aggregate sources stated in 106-1.02 do not meet specifications:

| Description | Specification | Type IIA, IV | Type I, IIB, III | Type V | Type VH |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T96 | 45 | 45 | 45 | 45 |
| Degradation Value, min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss % max (5 cycles) | AASHTO T104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP61 | 90, 2 face | 80, 1 face | 98, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % 1:5 1:3 | ATM 306 | 8 20 | 8 - | 3 8 | 3 8 |
| Nordic Abrasion, max. % | ATM 312 |  |  | 12 | 8 |
| Absorption, max. % | AASHTO T85 | 2.0 | 2.0 | 2.0 | 2.0 |

R199 (01/02/08)

TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT

AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V, VH |
| 1 inch | 100 | - | - | - | - |
| 3/4 inch | 80 - 90 | 100 | - | - | 100 |
| 1/2 inch | 60 - 84 | 75 - 90 | 100 | 100 | 65 - 80 |
| 3/8 inch | 48 - 78 | 60 - 84 | 80 - 90 | 80 - 95 | 48 - 60 |
| No. 4 | 28 - 63 | 33 - 70 | 44 - 81 | 55 - 70 | 30 - 45 |
| No. 8 | 14 - 55 | 19 - 56 | 26 - 70 | 35 - 50 | 20 - 30 |
| No. 16 | 9 - 44 | 10 - 44 | 16 - 59 | 20 - 40 | < 22 |
| No. 30 | 6 - 34 | 7 - 34 | 9 - 49 | 15 - 30 | < 17 |
| No. 50 | 5 - 24 | 5 - 24 | 6 - 36 | 10 - 24 | < 14 |
| No. 100 | 4 - 16 | 4 - 16 | 4 - 22 | 5 - 15 | < 12 |
| No. 200 | 3 - 8 | 3 - 8 | 3 - 8 | 3 - 8 | 3 - 8 |

Fine Aggregate (passing the #4 sieve). Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

For Type IV, V and VH mixes, remove natural fines passing a #4 sieve before crushing aggregates for this hot mix asphalt mixture.  Consist entirely of aggregate produced from aggregate crushing process and be non-plastic as determined by WAQTC FOP for AASHTO T 90, and meets the following:

Property	Test Method	Requirement

Fine Aggregate Angularity	AASHTO T 304	45% min.

R199 (01/02/08)

APPENDIX D

ENVIRONMENTAL PERMITS

APPENDIX A

EROSION AND SEDIMENT CONTROL PLAN

APPENDIX B

MATERIALS CERTIFICATION LIST

APPENDIX E

RAILROAD PERMIT

APPENDIX C

UTILITY REQUIREMENTS