PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

STANDARD SPECIFICATIONS

FOR HIGHWAY CONSTRUCTION

1998

METRIC EDITION

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	Cross Sections

- Geotechnical Report, "FDW Analysis, Homer East End Road, MP 0 to 3.75, Homer, Alaska".

d.	State of Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

e.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

- Standard Specifications for Highway Construction (Metric) 98M. ($25.00)

- Bidders are hereby notified that data to review for preparing bids is available follows in the Plans Room (4111 Aviation Avenue):

a.	Memorandum of Agreements

b.	Temporary Construction Permits

c.	Phase 1 Environmental Assessments

4.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

5.	The Department has an approved environmental document addressing concerns and environmental commitments and it is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

6.	The Materials Certification List (MCL) has been included in Appendix A.  This list is provided for the Contractor to determine which materials will require submittal to the project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

SECTION 101

# DEFINITIONS AND TERMS

Standard Modification

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

## (06/25/99)M 68

Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075-mm screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75-mm material. (11/29/01) R1M98

SECTION 102

## BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

# SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modification

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.:

In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.

(10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”.

(06/25/99)M 69

Add the following Subsection:

103-1.10. Escrow of Bid Documentation. Furnish a legible copy of your bid documentation and an affidavit, as instructed in writing by the Contracting Officer. Bid documentation consists of written documentation of all quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor with a subcontract exceeding $200,000, regardless of tier.

Meet the following requirements:

- Submitting Bid Documentation. Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number. Deliver the sealed container to the Department-designated document depository for safekeeping.

- Affidavit. Submit directly to the Contracting Officer the completed and certified affidavit located at the end of this Subsection, attesting that:

- the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

- the sealed container contains all bid documentation submitted,

- the escrow materials were relied on to prepare the bid, and

- should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

- Duration and Use. The bid documentation will remain in escrow, without access by either party, until one of the following occurs:

- There is a dispute related to Change Order. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor files a written claim or initiates Contract-related litigation against the Department. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor completes the Contract and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed. Such action is sufficient grounds for the Contractor to obtain the release and custody of the escrow documentation.

- Failure to Provide Bid Documentation. Refusal or failure to provide your bid documentation or affidavit renders your bid nonresponsive. Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

- Confidentiality of Bid Documentation. Materials held in escrow are your property. Except as otherwise provided herein, the escrow materials cannot be released without your approval. The original escrow materials are returned to you once any litigation is concluded, outstanding claims are resolved, and the final release is executed.

- Cost and Escrow Instruction. The Department pays to store all escrowed materials and instructs the depository regarding escrow.

- Payment. Include within the overall Contract bid price all costs to comply with this subsection.

# (02/12/02) S 86

THIS PAGE INTENTIONAL LEFT BLANK

SECTION 105

## CONTROL OF WORK

### Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Communications Systems GCI Cable Inc. Homer Electric Association

The Contractor shall call the following utilities and agency directly:

DOT/PF Maintenance and Operations…………………262-2199

City of Homer, Public Works………………………….235-3170

There are various utility appurtenances located within the project limits. Some of the existing utilities are scheduled for relocation as addressed in the following utility specific sections. The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

It shall be the responsibility of the Contractor to work around those utilities not designated for relocation in the plans and the following utility specific coordination. Any changes or additional relocation requested for Contractor convenience shall be at the Contractor’s expense.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

It is the Contractor’s responsibility to schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required of the Contractor prior to utility relocation. Payment to the Contractor will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen  (15) calendar days advance written notice for required staking.

The Contractor will be required to provide the Utility Company’s fifteen (15) calendar days advance written notice of the relocations described below to begin. The utility Company’s will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific Coordination requirements for the specific utilities are included below:

The utility relocation work will be performed in three segments as outlined below. The relocation work will be completed for each segment prior to the utility companies beginning work on the next segment.

The installation of the utility duct system by the Contractor will be completed by segment in order starting at the BOP. Each segment of the utility duct system will be completed in its entirety and inspected and accepted by each utility company. The utility companies may elect to inspect and accept the duct from structure to structure.

After placement of the cables, each segment will be spliced and cut over into service before any retirement of the existing facilities will begin. Each utility company will have to remove their existing cables from the existing poles before the pole removal can be completed by HEA.

Alaska Communications Systems (ACS) has existing underground telephone cables along and across East End Road throughout the project. Most of the existing cables are in conflict with project embankment construction. The Contractor will install a new utility duct system for ACS to place the new facility in. The utility duct system installation for ACS has been divided into three segments. Segment I, from Station 0+170 to Station 1+325, Segment II, from Station 1+325 to Station 2+420, and Segment III, from Station 2+420 to Station 3+625.  Additionally, ACS will be relocating some of the existing telephone cables between stations 3+625 and 5+960, beyond the end of segment III of the duct system. The segments will be completed in this order. After the Contractor has completed each segment of the utility duct system ACS will inspect and accept the segment and begin installing cables and pedestals along with termination and service connects. ACS may elect to inspect and accept the duct from structure to structure and begin placing cables. The new relocation must be completed for each segment, including service connects, before ACS can begin the retirement of the existing facilities.

The Contractor will allow ACS forty-six (46) calendar days to complete Segment I of work after duct acceptance.

The Contractor will allow ACS forty (40) calendar days to complete Segment II after duct acceptance.

The Contractor will allow ACS forty (40) calendar days to complete Segment III after duct acceptance.

The Contractor will allow ACS forty (40) calendar days to complete the underground relocation work between the end of segment III of the duct system and the EOP.

GCI Cable, Inc. (GCI) has existing underground television cables along and across East End Road. Most of the existing cables are in conflict with project embankment construction. The Contractor will install a new utility duct system for GCI to place the new facility in. The utility duct system installation for GCI has been divided into three segments. Segment I, from Station 0+170 to Station 1+325, Segment II, from Station 1+325 to Station 2+420, and Segment III, from Station 2+420 to Station 3+625. Additionally, GCI will be relocating some of the existing television cables between stations 3+625 and the EOP, beyond the end of segment III of the duct system. The segments will be completed in this order. After the Contractor has completed each segment of the utility duct system GCI will inspect and accept the segment and begin placing new television cables in the duct and then begin termination and service connects. The new relocation must be completed, including service connects, for each segment before GCI can begin the retirement of the existing facilities.

The Contractor will allow GCI twenty-seven (27) calendar days to complete each segment of work after duct acceptance, and twenty (20) calendar days to complete the relocation work between the end of segment III of the duct system and the EOP.

Homer Electric Association, Inc. (HEA) has an existing overhead electric line along and across East End Road through out the project limits. This overhead facility is in conflict with project embankment construction and will be replaced with a new underground electric system. The Contractor will install a new utility duct system for HEA to place the new facility in. The utility duct system installation for HEA has been divided into three segments. Segment I, from Station 0+170 to Station 1+420, Segment II, from Station 1+420 to Station 2+440, and Segment III, from Station 2+440 to Station 3+625. HEA will be relocating the existing overhead facility with new overhead lines and poles from Station 3+625 to the EOP.  The segments will be completed in this order. After the Contractor has completed each segment of the utility duct system, HEA will inspect and accept the segment and begin placing new electric cables in the duct and installing switch cabinets, pedestals, and pad mount transformers along with termination and service connects. The new relocation must be completed, including service connects and all retirement by ACS and GCI, for each segment before HEA can begin the retirement of the existing facilities.

The Contractor will allow HEA forty-five (45) calendar days to complete Segment I, after duct acceptance.

The Contractor will allow HEA twenty-five (25) calendar days to complete Segment II after duct acceptance.

The Contractor will allow HEA eighty (80) calendar days to complete Segment III after duct acceptance.

The Contractor will allow HEA twenty-five (25) calendar days to complete the relocation work between the end of segment III of the duct system and the EOP.

HEA will provide service connects to the three (3) new load centers being installed by the Contractor for this project. After the load centers have been installed by the Contractor, and inspected and tagged by the Department of Labor, the Contractor will notify HEA by calling 235-8167 to schedule the service connect. The Contractor will allow HEA two (2) weeks to schedule the work and two (2) calendar days to complete the work to connect each load center.

(2/1/00)R3M98

105-1.12 LOAD RESTRICTIONS.  All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the Permit Officer.  The Permit Officer may be contacted at (800) 478-7636 or (907) 345-7636.

Alternate axle configurations and loading which may reduce the overload movement restrictions and conditions may be submitted to the Engineer for review.

(01/08/97)R103m

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

### Standard Modification

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.

(03/26/01) M 101

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

## CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

(08/31/99)S 13

106-1.02  LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of the sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) before beginning any operations in your surface mine.  Offer the training at each surface mine that will be used to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following: When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

### ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 244

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T166/T275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87

SECTION 107

## LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineation’s of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES. Change the first sentence to the following: When your operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, such as shell heaps, land or sea mammal bones or tusks, or other items of historical significance, cease operations at that location immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (5/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: Where the Contractor's activities meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99) R170M98

Add the following subsections:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

107-1.22 PERMITS. Add the following: The Contractor shall provide the information necessary to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for construction activities in Alaska to discharge stormwater from the construction site. Refer to Section 641, Erosion and Pollution Control for requirements for this permit.

The following permits were obtained by the Department on behalf of the Contractor and are contained in Appendix B attached to these specifications.

- Department of the Army, Corps of Engineers, Nationwide Permit No. 23, D- 1999-1981, Kachemak Bay. Issued October 7, 2002. Expires October 7, 2004.

- Department of the Army, Corps of Engineers, Nationwide Permit No. 13, D-2001-0909. Issued October 17, 2002. Expires October 17, 2004.

- Alaska Department of Fish & Game, Permit # FG 01-II-0487 (Amendment I). 	Issued July 26, 2002.  Expires December 31, 2003.

- Kenai Peninsula Borough Habitat Permit, KRC #4501. Issued February 3, 2003. Expires December 31, 2003.

- Alaska Department of Environmental Conservation, letter of non-objection 0121-WW-207-009. Dated September 19, 2000.

The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications.  It is the Contractor’s responsibility to abide by the stipulations contained in each permit.  If it is determined that an activity cannot be performed as specified in one of these permits, The Contractor shall cease work and immediately notify the Engineer.  The Engineer will then decide if a permit modification is necessary.  The Engineer will have copies of the permits posted in the project office.

It is the Contractor’s responsibility to obtain all permits required for actions not permitted previously by ADOT&PF.  The Contractor is responsible for complying with all permit stipulations, conditions and/or terms.  Agencies to contact for permit information may include, but is not limited to, the U.S. Army Corps of Engineers, the Environmental Protection Agency, the U.S. Fish and Wildlife Service, the Alaska Department of Fish and Game, the Alaska Department of Environmental Conservation, the Alaska Department of Natural Resources, and local or regional governments.  The Contractor shall provide timely notification of such actions and permit acquisitions as may be required by federal, state, regional, and local authorities.  The Contractor shall provide copies of all permits, and applicable Federal and State notifications to the Project Engineer.

## SECTION 108

## PROSECUTION AND PROGRESS

# Standard Modification

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts.

(10/28/99)M70

Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (2/15/01)R242M98

SECTION 109

## MEASUREMENT AND PAYMENT

Standard Modification

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(5/31/00) M90

1. 	Labor. Replace sub-paragraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

Delete item 5. and substitute the following:

# 5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor. (02/08/01) M71

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Homer, Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the Department reduces the quantity of work of a bid item involving a DBE firm, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If the Engineer approves a DBE replacement, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form

25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control

of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES. Delete the fourth paragraph and replace with the following:  Remove drainage structures designated for removal in their entirety.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

Waste asphalt pavement may be stockpiled at the State Maintenance Yard in Homer. In order to use this site, the Contractor shall meet the following requirements:

1.	Stockpiling shall be done in a manner acceptable and coordinated with the Maintenance office.

2.	Base course material may be included with removed asphalt if it does not exceed 30 percent of the total volume delivered.

3.	The broken asphalt pieces shall be 150 mm or less in maximum dimension.

202-5.01  BASIS OF PAYMENT.  Add the following:   Sawcutting, if required, will not be paid for directly, but will be subsidiary to Item 202(2), Removal of Pavement.

Activities associated with pipes to be abandoned in place are subsidiary to Removal of Culvert Pipe and will not be measured for payment.

SECTION 203

#### EXCAVATION AND EMBANKMENT

Special Provisions

203-2.05 BORROW. Add the following: Borrow, Type A, B, or C when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, or C, respectively.

Add the following:

203-2.07 WASTE OR UNUSABLE MATERIAL Soils deemed unsuitable, which do not contain organics, or excess usable material.

203-3.01 GENERAL CONSTRUCTION REQUIREMENTS.   Delete the third paragraph and substitute the following:  Excavate material which would classify as rock to a minimum depth of 150 mm below subgrade, within the limits of the roadbed.  Backfill with material specified for placement on the subgrade.

On page 86, Delete  the seventh paragraph and substitute  the following: Unsuitable excavation which contains no organics and excess usable material shall be placed at the closed landfill site owned by the City of Homer. Prior to using this site, the Contractor shall grub the access road location, and construct the access road in accordance with the plans, using gravel provided under this contract.  Material to be disposed of shall be placed and graded as detailed on the plans.  In addition, ditch and slope erosion control measures shall be accomplished as directed.

At the discretion of the Engineer, unsuitable and excess usable material may be disposed of at additional disposal locations provided the following steps are completed:

- Obtain a written agreement between the Contractor and the property owner allowing fill to be placed.

- Obtain a written statement from the State Historic Preservation Officer (SHPO) stating that the material is not expected to impact any cultural resources. The SHPO may be contacted at (907) 269-8715.

- Provide a wetland specialist able to conduct wetlands determinations
and delineations in accordance with the Corps of Engineers 1987 
Wetland Delineation Manual. These delineations will be subject to 
 Corps of Engineers approval.

- Check for other required permits from Alaska Department of Natural
Resources (ADNR), Alaska Department of Fish & Game (ADF&G) etc.

- Set up silt fence or other Best Management Practices (BMP's) if
stormwater runoff is a potential.

6.	Provide the Engineer a copy of the following information:

- All clearances and permits prior to placing any material.

- A map showing location of the property which will receive 
fill in relation to a main highway or town.

- Site plans showing the boundary of the property and location 
of the fill.

- A drawing showing potential BMP locations for storm water control.

- A copy of the written agreement between the landowner and
Contractor allowing fill to be placed.

- A written statement that all necessary permits or clearances have been obtained. Also, provide a written statement listing agencies or offices contacted which responded that no additional action is required.

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

(03/14/02)R23M98

Standard Modifications

203-3.02 EMBANKMENT CONSTRUCTION. In the 12th paragraph, first sentence, delete the words “from excavation”.

In the 12th paragraph, third sentence, insert the words “from excavation” after “wasted rock”.

(02/08/01) M 92

Special Provisions

203-3.02 EMBANKMENT CONSTRUCTION. Add the following: Where the plans call for placement of selected material and/or excavation, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work. (2/9/00)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

203-3.04 COMPACTION OF EMBANKMENTS NOT CONSTRUCTED WITH MOISTURE AND DENSITY CONTROL. Delete the second and third paragraphs and substitute the following:  In areas of subgrade excavation and/or subgrade embankment construction, the subgrade shall be compacted with a vibratory roller having  a minimum static weight of 10,900 kg until the roller drum rebounds back off the subgrade.  Do not cover any lift by another lift until compaction has been completed.

203-4.01 METHOD OF MEASUREMENT. Add the following   Backfilling within the plan excavation limits will not be measured for payment but will be subsidiary to the respective items of work. Backfilling outside plan excavation limits will measured for payment as embankment construction.

203-5.01 BASIS OF PAYMENT. Add the following: Backfilling within plan excavation limits will be paid for under the items of work involved at the prices bid for that work. Backfilling outside plan excavation limits will be paid for as embankment construction in accordance with this Section.

Add the following:  No deduction for pavement removed will be made from the quantity of excavation.

No additional payment will be made for preparing and constructing the access road, placing excess usable material, or performing ditch and erosion control measures for the City of Homer landfill disposal site. This work will be considered subsidiary to Items 203(3), Unclassified Excavation, or 202(2), Removal of Pavement.

SECTION 301

#### AGGREGATE BASE COURSE

Special Provisions

301-2.01 MATERIALS. Replace this subsection with the following: The gradation of base course material shall conform to the requirements of Grading D-1.

301-2.01 MATERIALS. Add the following after the first paragraph: At the Contractor's option, crushed asphalt base course (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing the specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

# SECTION 306

## ASPHALT TREATED BASE COURSE

# Special Provisions

306-2.01 MATERIALS. Add the following to item 1.: The acceptance of aggregate shall be at the plant cold feed as specified in Section 401 for hot mix asphalt aggregates. The Contractor shall perform process control testing to verify conformance to the specifications and give the results to the Engineer within 24 hours.

Up to 30 percent of the aggregate material may be recycled asphalt pavement material produced from asphalt pavement that has been crushed and processed.  All agglomerated particles shall be sized to pass a 37.5 mm sieve.  Test for aggregate and asphalt cement shall apply to the delivered product.

306-3.08 SPREADING AND FINISHING. Change the first sentence to read: The ATB mixture may be spread in one layer if the resulting density is acceptable to the Engineer.

Add the following sentence to the second paragraph: Public traffic shall not be allowed on the asphalt treated base until it has been compacted and cooled to where no surface distress, deformation, shoving, or displacement occurs from use.

306-3.09 COMPACTION. Delete this subsection in its entirety and substitute the following: The amount of compactive effort required shall be determined by the control strip method. The control strip shall be evaluated with the use of a nuclear density gauge to establish a roller pattern. The location of the control strip will be designated by the Engineer.

The Contractor shall be responsible for the development of the control strip. The Contractor shall select a minimum of two sites on the control strip and take a 15 second (minimum) reading with the nuclear densometer at each site for every roller pass over the test site. Rolling shall continue until there is less than 16 kg/m3 increase in unit weight in the averaged density readings per roller pass. This process will establish the roller pattern to be used for the compaction of the asphalt treated base course. A copy of the density readings developing the control strip will be supplied to the Engineer. The Engineer will obtain ten nuclear densometer readings randomly on the completed control strip. A density standard for the project will be determined by averaging the ten readings. Compaction criteria shall be 98% of the density standard.

306-3.12 SURFACE TEST. Add the following: Check surface tolerance prior to paving. Correct areas out of tolerance prior to acceptance by the Engineer for paving.

306-4.01 METHOD OF MEASUREMENT.  xxxDELETEDxxx

Delete the third paragraph and substitute the following: The cost of anti-stripping additive will be considered incidental to the price of asphalt treated base course.

306-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

(9/18/00)R226M98

# SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Add the following after ATM T-17 in the first paragraph: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14  Joints.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

Delete the last paragraph.

401-3.15  Surface Tolerance.  Add the following: The Engineer will measure the smoothness of the asphalt concrete pavement in all driving lanes with a California-type profilograph within 15 days after mainline paving is completed and all defects are corrected.  No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or matches with an existing pavement.  The profilograph results (PrI) will be reduced and a price adjustment calculated in accordance with Subsection 401-5.01.  Furnish required traffic control devices or flagging in accordance with Section 643.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equidistant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One 150 mm diameter core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Delete all reference to Temporary Paving and add the following: Temporary Pavement used for traffic control detours and transitions shall be paid for under Items 401(1), Asphalt Concrete Pavement, Type II, Class B, and 401(2), Asphalt Cement, Grade PG 52-28.  No separate payment will be made for anti-strip additives for Temporary Pavement. Price adjustments will not apply to Temporary Pavement.  Acceptance testing for Temporary Pavement will not be required.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined in Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-4 and applied under Item 401(6), Asphalt Price Adjustment.

TABLE 401-4

| Average Profile Index (PrI) (Millimeters per 1000 Lane Meters) | Adjustment to Item 401(6), Asphalt Price Adjustment, for Pavement Smoothness |
| --- | --- |
| 0 to 60 | Add $335 multiplied by (61PrI) |
| 61 to 94 | No Adjustment |
| 95 and greater | Deduct $335 multiplied by (PrI94) but not to exceed $10,000 |

(08/19/02)R199M98

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-2.01 MATERIALS. Add the following: Reinforcing steel shall conform to the requirements of Section 503.

501-3.01 PROPORTIONING. Under 1.  Determining Proportions and Batch Weights., delete the first sentence and substitute the following: Submit a mix design developed in accordance with ACI 211 and 301, Section 4 to the Engineer for approval.  (7/6/99) R37M98

SECTION 507

BRIDGE RAILING

Special Provisions

507-1.01  DESCRIPTION.  Add the following:  This work shall also consist of the installation of balustrade handrailing for pedestrians and bicyclists in accordance with specifications for bridge railing.

507-4.01  METHOD OF MEASUREMENT.  Add the following:  Balustrade handrailing will be measured by the meter from out to out of the end posts.

507-5.01  BASIS OF PAYMENT.  Add the following:  Payment for Item 507(5) Balustrade Handrailing will be full compensation for all labor, equipment and materials required for installation, complete and in place.  (2/7/00)R40M98

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 507(5) Balustrade Handrailing | Meter |

Add the following Section:

SECTION 515

# CABLE-TIED CONCRETE BLOCK MAT SYSTEM

515-1.01 DESCRIPTION.  This work consists of sizing the concrete blocks; constructing; and supplying all labor, equipment, and materials required for the articulating cable-tied precast concrete block mat system, including anchors, geotextile, grout, and bedding material in accordance with the lines, grades, and dimensions shown on the Plans and as specified herein.  This system consists of cable-tied concrete block mats placed side by side and clamped together to provide one homogeneous erosion protection system.  Work will also include traffic control during installation of the mat system.

515-2.01 MATERIALS.  Meet the following requirements for the Cable-tied Concrete Block Mat System:

Concrete:	The minimum required concrete strength is 28 MPa at 28 days.  Use concrete mix recommended by the manufacturer and approved by the Engineer.  Use materials that conform with the following:

Portland Cement 	Subsection 701-2.01

Fine aggregate	Subsection 703-2.01

Coarse aggregate	Subsection 703-2.02

Cables:	Use stainless steel with minimum breaking strength of 67.2 kN meeting the current ASTM A 368 specifications

Geotextile:	Use a needle-punched nonwoven fabric.  Use materials that conform to Subsection 729-2.02 Subsurface Drainage, Class 2.

Clamps:	Use stainless steel clamps recommended by the manufacturer.

Anchors:	Use earth anchors recommended by the manufacturer.

Grout:	Use materials that conform to Section 701, Hydraulic Cement.

Bedding:	Meet AASHTO M 80, Class A.  Gradation: AASHTO M 43, size no. 68.

# DESIGN AND CONSTRUCTION REQUIREMENTS

515-3.01 SUBMITTALS.  Prepare and submit drawings according to Subsection 105-1.02.  Show the following as applicable:

1.	Furnish design calculations for the sizing of  the concrete blocks.

2.	Furnish details for constructing the precast articulating cable-tied concrete block mat system to the lines, grades and dimensions shown on the Plans.

3.	Precisely describe all proposed materials and furnish manufacturer’s certificates of compliance for the concrete blocks, geotextile, cable, anchors, and cable fittings and connectors prior to fabricating the mat.

4.	Furnish shop drawings for the fabrication of the cable-tied concrete block mats and any recommendations, if applicable, 14 days prior to assembly of the mats.

515-3.02 DESIGN.  Concrete block sizing is to be performed by a Professional Engineer licensed in the State of Alaska.  Use Factor-of-Safety methodology described in Section 4.3, Design Guide 4 of Publication No. FHWA NHI 01-003, HEC-23 Bridge Scour and Stream Instability Countermeasures to size the concrete blocks.  Design the block size for the cable-tied concrete block mats to a minimum safety factor of 1.5.  Use a closed cell concrete block.  Perform analysis based upon the stability of the mat due to gravity forces alone, neglecting forces which may be due to cabling, mechanical anchorage, contact with adjacent blocks, or other restraints not attributable to gravity based forces.  Account for a 13 mm block projection in the design.  See Subsection 515-3.03 for design hydraulic parameters.  If more than one side slope is present, design for the most critical/stringent situation.

515-3.03 DESIGN HYDRAULIC PARAMETERS.  The following hydraulic parameters for Bridge No. 666 South Fork Anchor River are provided for use in the sizing of the concrete blocks:

Channel Slope:	0.0068 m/m (ft/ft)

Side (Cross) Slope:	Streambed: 2H:1V

Banks:  NA

Discharge:	243 m3/s (8,564 cfs)

Velocity:	4.7 m/s (15.3 ft/s)

Depth:	2.9 m (9.5 ft)

Hydraulic Radius:	1.91 m (6.25 ft)

Bed Shear:	62.89 kg/m2 (2.65 psf)

Parameters are provided in their United States Customary (USC) units of measure for use with the Factor-of-Safety methodology.

515-3.04 CLOSED CELL CONCRETE BLOCKS.  Provide blocks sound and free of defects that would interfere with the proper placing of the mats or impair the strength or permanence of the construction.  Surface cracks incidental to the usual methods of manufacture, or surface chipping resulting from customary methods of handling in shipment and delivery, shall not be deemed grounds for rejection.

Cracks exceeding 7 mm in width and/or 25 mm in depth shall be deemed grounds for rejection.

Chipping resulting in a weight loss exceeding 10% of the average weight of the blocks shall be deemed grounds for rejection.

Repair blocks rejected at the project location with structural grout at no expense to the State.

515-3.05 COOPERATION WITH USGS.  USGS will remove sensor line attached to the north abutment prior to mat placement.  Once Contractor provides schedule for work, the Engineer will contact Ron Rickman, USGS, 907-786-7131 for removal and replacement of sensor line.

515-3.06 FOUNDATION PREPARATION.  Remove all rocks greater than 75 mm, vegetation, and debris from the existing surface within the defined limits for the cable-tied concrete block mat.  Retain riprap removed for placement along mat edges as indicated on the Plans.  Grade surface to a smooth plane reasonably free of mounds, dips, or windrows.  Surface need not be horizontal.  Slopes flatter than 3H:1V are acceptable for mat placement.  Place bedding material, if necessary, to flatten slopes.  Compaction is not required.

515-3.07 GEOTEXTILE.  During all periods of shipment and storage, protect the geotextile from direct sunlight, ultraviolet rays, and temperatures greater than 60°C. Place geotextile on the prepared surface so that the upstream strip of fabric overlaps on top of the downstream strip.  Overlap longitudinal and transverse joints a minimum of 600 mm.  Extend the geotextile a minimum of 300 mm beyond the top edge of the concrete block mat and attach to the existing timber plank abutments/wing walls.  Do not place geotextile fabric within 2 meters of the upstream, downstream, and streamward edges of the cable-tied concrete block mat.

515-3.08 CABLE-TIED CONCRETE BLOCK MAT PLACEMENT.  Place mats from the downstream end of the bridge to the upstream end.  Abut adjacent mats with less than a 50 mm gap.  Cables between mats shall not protrude above top surface of concrete blocks.  Entrench and bury at least two blocks on the upstream edge of the mat system into the ground.  Backfill trenches flush with the top of the non-entrenched blocks.

Per the ADF&G permit, if the construction area is not completely dewatered, isolate the in-water work completely from the flowing waters of the Anchor River.

There is limited height under the bridge.  Verify field conditions prior to submitting placement method plan for approval.

515-3.09 ANCHOR SYSTEM.  Anchor the upstream edge, edge along the abutment, and the edge along the embankment.  (See notes on Drawing N2)  Use anchors with a minimum pull resistance of 17.8 kN.  Install anchors at a maximum spacing of 2 meters and a minimum embedment depth of 2 meters.  Anchors shall have the capability of being load-tested to the specified pull-out capacity.

515-3.10 SEAL.  Seal along abutments as shown in the Plans.  Place grout so the seal thickness is the full height of the concrete blocks.

515-4.01 METHOD OF MEASUREMENT.  Cable-tied Concrete Block Mats will not be measured for payment.

515-5.01 BASIS OF PAYMENT.  At the contract lump sum price. Traffic control is subsidiary to Item 515(1), Cable-tied Concrete Block Mat System.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

515(1)	Cable-tied Concrete Block Mat System	Lump Sum

SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01  DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts, and utility conduits.

603-2.01 MATERIALS.  Add the following to the second paragraph: New pipe being installed in existing manholes shall have the same outside diameter as the pipe being replaced, except as noted otherwise.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts.  The color shall be blue with no other markings.  The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm.

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.

603-3.03 JOINING PIPE.

2.	Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.”

(02/08/01)M 95

Special Provisions

603-3.03 JOINING PIPE.

2.	Metal Pipe. Add the following to the first paragraph:  Furnish and install all bands with a gasket that resists infiltration and leakage.

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(5/31/96)R42M

#### SECTION 604

#### MANHOLES AND INLETS

Special Provisions

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 25 mm concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

6.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the local DOT maintenance station.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 50 mm larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 75 mm formed hole approximately 0.6 m below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-4.01 METHOD OF MEASUREMENT. Add the following: Frames, grates and lids will not be measured for payment.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.

Delete Item 604(1) Storm Sewer Manhole and add the following pay items:

Pay Item No.	Pay Item	Pay Unit

604(1)	Storm Drain Manhole, Type__	Each

(9/1/00)R43M98

SECTION 605

UNDERDRAINS

Special Provisions

605-1.01 DESCRIPTION. Add the following: This work shall also include furnishing and installing fin drains, fin drain cleanouts, and flexible marker posts.

605-2.01 MATERIALS. Add the following: Fin drain shall consist of the following components

1.	Perforated corrugated polyethylene pipe meeting the requirements of AASHTO M-252.

2.	Geocomposite drain vertical member manufactured from synthetic, nonbiodegradable material meeting the requirements of subsection 729-2.06 Geocomposite Drain.

3.	Drainage geotextile meeting the requirements of subsection 729-2.02 Subsurface Drainage and Riprap Liner.

4.	Backfill meeting the requirements of Selected Material, Type A.

The fin drain pipe and geocomposite drain shall be equal in length. Fin drain pipe that is slotted longitudinally to allow for the connection with the geocomposite drain shall not be used.

Cleanout pipe shall be nonperforated corrugated polyethylene pipe meeting the specifications of AASHTO M-252.

Cleanout marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 80 mm (min) by 1.8 m post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm. One meter of post shall remain above the ground after driving.

605-3.04 FIN DRAIN INSTALLATION. Add the following subsection: Fin drain pipe shall be installed as specified in subsection 605-3.01 Pipe Installation.

The geocomposite drain shall be installed in accordance with the manufacturer's recommendations.

The geocomposite drain and the perforated pipe shall be totally enclosed in drainage geotextile. The drainage geotextile shall be attached and overlapped as recommended by the geocomposite drain manufacturer.

605-4.01 METHOD OF MEASUREMENT. Add the following: Fin drains will be measured by the meter of pipe.

Cleanout pipe and flexible marker posts will not be measured for payment.

605-5.01 BASIS OF PAYMENT. Add the following:  No separate payment will be made for excavation, backfill, geocomposite drain,  cleanout pipe, or flexible marker posts, these items will be subsidiary to the fin drain pay item.

Drainage geotextile for underdrains and fin drains will be paid for under Item 631(1) Geotextile, Drainage.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

605(10-200)	200 mm Fin Drain	Meter

(6/12/95)R44M

SECTION 606

GUARDRAIL

Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 129 cm2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

(10/17/02)R45aM98

# Standard Modifications

606-3.01  GENERAL.  Add  the following:   Treat field cuts to timber posts and blocks according to AWPA standard M 4. (10/19/98)M 67

Special Provisions

606-3.02 POSTS. Delete the first two numbered items in this Subsection and substitute the following:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

606-3.09 FLEXIBLE MARKERS. Add the following Subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION. Add the following Subsection: After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine that additional guardrail is necessary, and comply without delay.

(10/17/02)R45aM98

Standard Modifications

606-4.01 METHOD OF MEASUREMENT. Delete the second to the last paragraph and substitute the following:

Guardrail/Bridge Rail Connection. Per each, installed in place. Each connection includes all brackets, beam sections, transition pieces, and all posts and associated hardware required to connect the guardrail section to a bridge rail according to the Plans and the Special Provisions. (10/19/98)M 66

## SECTION 608

SIDEWALKS

Special Provisions

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

- 2.	Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG 52-28	Subsection 702-2.01

Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.	4450

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

608-3.03 SIDEWALK RAMPS. Delete this subsection and substitute the following:

608-3.03 CURB RAMPS.  Replace the first sentence with the following:  Remove existing curb ramps and construct curb ramps according to the details and locations shown on the Plans. Install composite detectable warning tiles such as Armor Tile Cast-In-Place In-Line Tactile Panels, manufactured by Engineered Plastics, Inc., or approved tactile warning bumps as shown in the details on the plans.

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish. (06/11/02)R256M98

Standard Modification

608-4.01 METHOD OF MEASUREMENT.  In both the first and second paragraphs, after “finished surface” insert “, including ramps”.  (06/25/99) M 74

Special Provisions

608-4.01 METHOD OF MEASUREMENT. Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp. By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles backing curb and landings necessary to provide a single street-level access.

(06/11/02)R256M98

Add the following: Asphalt cement for Asphalt Sidewalks or Pathways, will not be measured for payment.

Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.

608-5.01 BASIS OF PAYMENT.  Add the following: Asphalt cement for Asphalt Sidewalk or Pathways will not be paid for separately, but will be subsidiary to the pay item.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.  (2/1/00) R47M98

Backing curb, will be subsidiary to Item 608(6), Curb Ramp. The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp. (06/11/02)R256M98

Delete Item 608(6), Sidewalk Ramp, and add the following pay items:

Pay Item No.	Pay Item	Pay Unit

608(6)	Curb Ramp	Each

608(7)	Asphalt Pathway	Megagram

(06/11/02)R256M98

#### SECTION 609

#### CURBING

#### Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.  (2/1/00)R202M98

609-3.05 CURB RAMPS. Delete this Subsection in its entirety.  (06/11/02)R256M98

Standard Modifications

609-4.01 METHOD OF MEASUREMENT.  In the first paragraph, after “drainage structures” insert “or ramps”.  (06/25/99) M 75

Special Provisions

609-4.01 METHOD OF MEASUREMENT. Delete the second paragraph.

609-5.01 BASIS OF PAYMENT. Delete Pay Item 609(3), Curb Ramp.

(06/11/02)R256M98

#### SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Homer.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

Delete this Section in its entirety and substitute the following:

## SECTION 618

## SEEDING

Standard Modifications

618-1.01 DESCRIPTION. This work consists of establishing a perennial stand of grass or other specified living vegetative cover in the areas indicated on the Plans and to acceptably maintain the cover for the term of the Contract.

(02/08/01)M99

# Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.  (08/28/01)R52M98

Standard Modifications

618-2.01 MATERIALS. Use materials that conform to the Special Provisions and the following:

Seed 	Section 724

Fertilizer (20-20-10)	Section 725

(02/08/01)M99

Special Provisions

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

(08/28/01)R52M98

Standard Modifications

CONSTRUCTION REQUIREMENTS

618-3.01 SOIL PREPARATION. Clear all areas to be seeded of stones 100 mm in diameter and larger and of all weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the seeding operation, growth of grass, or subsequent maintenance of the grass-covered areas.

Make areas to be seeded reasonably free of ruts, holes, and humps.

When specified, apply topsoil according to Section 620.

Roughen the surface slightly by means of dozer-tracking or other approved method.

(02/08/01)M99

Special Provisions

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.  (08/28/01)R52M98

Standard Modifications

618-3.02 SEEDING SEASONS. Seed and fertilize during the local growing season.

Do not seed during windy conditions or when climatic conditions or ground conditions would hinder placement or proper growth.

(02/08/01)M99

Special Provisions

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.  (08/28/01)R52M98

Standard Modifications

618-3.03 APPLICATION. Apply seed mix at the rate specified in the Special Provisions.

Apply fertilizer at rate given in table 30 days after seeding.

Apply mulch at the rate specified in the Special Provisions.

Use any of the following methods:

1.	Hydraulic Method.

a.	Furnish and place a slurry made of seed, water  and other components as required by the Special Provisions.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

2.	Dry Methods.

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment when seed and fertilizer are to be applied in dry form.

b.	Spread fertilizer separately at the specified rate.

(02/08/01)M99

Special Provisions

618-3.03 APPLICATION. Add the following: For East End Road, apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

SEED MIX- East End Road

| Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- |
| Seed | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total = 49.0 kg |
| Soil Stabilizer Slope < 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
| Fertilizer | 20-20-10 | 586 kg |

At the Anchor River site, seed shall be hand applied in the spaces between the concrete blocks and all other areas disturbed by construction (above OHW).  Areas under the bridge shall not be seeded.

The Contractor shall not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Bering Hairgrass if Bering Hairgrass is commercially unavailable.  Substitute Nortran Tufted Hairgrass at the same application rate.

(08/28/01)R52M98

Standard Modifications

618-3.04 Plant Establishment AND MAINTENANCE. Protect seeded areas against traffic and erosion.

Promptly repair surfaces that are gullied or otherwise damaged following seeding by regrading, reseeding, and remulching as needed.

Water and maintain seeded areas in a satisfactory condition until final inspection and acceptance of the work. Use equipment that can water all seeded areas without damaging the seed bed.

Reseed any areas not showing evidence of satisfactory growth within 3 weeks of seeding.

618-4.01 METHOD OF MEASUREMENT.  Seeding by the hectare. By the area of ground surface acceptably seeded and maintained. Seed, water, and fertilizer are subsidiary.

Seeding by the kilogram. Weight of seed acceptably placed. Any other work required will be measured separately.

Water for seeding. By the kiloliter using calibrated tanks or distributors, accurate water meters, or by weighing. The conversion factor of 1 kilogram per liter will be used to convert weight to volume.

Mulching will be measured and paid for under Section 619.

(02/08/01)M99

Special Provisions

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

Seeding required at the Anchor River will not be measured for payment.

618-5.01 BASIS OF PAYMENT. The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(08/28/01)R52M98

No separate payment will be made for seeding at the Anchor River.  This work will be subsidiary to Item 515(1), Cable-Tied Concrete Block Mat System.

Standard Modifications

618-5.01 BASIS OF PAYMENT. At the contract unit price per unit of measurement for the pay items listed below that appear on the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

618(1)	Seeding	Hector

618(2)	Seeding	Kilogram

618(3)	Water for Seeding	Kiloliter

(02/08/01)M99

SECTION 620

TOPSOIL

# Special Provisions

620-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Topsoil shall conform to the requirements of Section 726, Class A.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(9/11/96)R53

SECTION 626

SANITARY SEWER SYSTEM

Special Provisions

626-1.01 DESCRIPTION. In the first sentence, after the word “constructing” add the following:

“, relocating,”

Add the following after the first paragraph: Work shall also include all coordination with the Engineer and City of Homer, including all efforts required under Section 103-1.06.

626-3.01 CONSTRUCTION REQUIREMENTS. Delete the fifth paragraph and substitute the following: Relocate pressure sewer main as shown on the Drawings.  Contractor shall perform all work necessary to protect the gravity sewer main buried adjacent to the pressure main.  Any damage to the grade of the gravity main shall be repaired to the satisfaction of the Engineer at the Contractor’s expense.  Any physical damage to either pipe shall be repaired at the Contractor’s expense.

Contractor shall add pipe to the pressure main as required to allow the existing main to be lowered to the grade shown on the plans.  With the exception of cutting the existing main to facilitate the addition of new pipe, the pressure sewer shall be relocated while the main is in service.  Contractor shall coordinate any shutdown of the pressure main with the City of Homer.  Written notice shall be given a minimum of 48 hours in advance of a proposed shutdown.  The maximum length of the shutdown shall be agreed upon with the City of Homer prior to any work occurring.

The Contractor shall move the pressure main horizontally as required to avoid undermining the gravity sewer main.  The final horizontal location of the pressure sewer main after relocation shall be coordinated with the Engineer.

Butt fusion of the pipe and fittings shall be performed in accordance with the pipe manufacturer’s recommendations as to equipment and technique.  The fusion operation shall be performed by an individual who has demonstrated the ability to fuse polyethylene pipe in the manner recommended by the pipe supplier.  The individual performing the fusing procedure must hold a current certification for fusing HDPE as stated in Title 49.1 DOT Certification.

All HDPE and PVC pipe shall be installed with No. 6 bare copper locate trace wire directly above it.

626-4.01 METHOD OF MEASUREMENT. Add the following:

New Sewer Service.  Measurement for furnishing and installing sewer service shall be per each, complete in place.

626-5.01  BASIS OF PAYMENT. Add the following: All additional piping required to relocate existing sewer main shall be considered subsidiary.

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 626(1-6) 6-inch HDPE Sanitary Sewer Main | Meter |
| 626(1-8a) 8-inch DIP Sanitary Sewer Conduit, CL50 | Meter |
| 626(1-8b) 8-inch DIP Sanitary Sewer Conduit, CL50 Encased in HDPE | Meter |
| 626(1-10) 10-inch PVC Sanitary Sewer Conduit, CL50 | Meter |
| 626(4) Reconnect Sewer Service | Each |
| 626(15-1.5) 1.5-inch HDPE Sanitary Sewer Service | Each |
| 626(15-2) 2-inch HDPE Sanitary Sewer Service | Each |
| 626(15-4) 4-inch CI Sanitary Sewer Service | Each |
| 626(15-6) 6-inch DIP Sanitary Sewer Service | Each |
| 626(19) Relocate Existing Sewer Main | Meter |

SECTION 627

WATER SYSTEM

## Special Provisions

627-1.01 DESCRIPTION. Add the following: For purposes of these specifications, Water Utility shall mean the City of Homer, Department of Public Works. The Contractor shall also provide as-builts in accordance with the conditions prescribed herein.

# CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL. Add the following: All sheeting and bracing used in excavation shall be removed by the Contractor following the completion of the work.

Delete the sixth paragraphs and substitute the following: The Contractor shall notify the Water Utility 48 hours prior to an interruption of water service. The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 6 hours.

The Contractor shall make specific arrangements with any and all home owners for continuous temporary water service where work to water main requires loss of water services to those lots for 6 or more consecutive hours.  Each service line shall be 1” minimum diameter, and may not exceed 305m long.  This work is incidental to work accomplished under this item.

Prior to commencement of work, the Contractor shall submit to the Engineer for review, a detailed plan for the installation of the new water systems and for removal/abandonment of existing water systems that are to be removed or abandoned. The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, and disruption of water service.

627-3.02 INSTALLATION OF CONDUIT. Add the following to the first paragraph: Polyethylene pipe shall be field joined by butt fusion as per the manufacturer’s recommendations. Pipe ends shall be dressed for field butt fusion as necessary. End surfaces shall be smooth and their orientation perpendicular to the pipe centerline axis and shall be suitable for field butt fusion. Conduit may be joined above ground and lowered into the trench afterwards. Contractor shall have a representative of the polyethylene pipe supplier on site at the start of the butt fusion process to instruct the Contractor’s operators in operation of butt fusion equipment and inspection of finished joints. The representative shall remain on site as long as necessary to insure proper joining of the pipe to the satisfaction of the Engineer.

Add the following to the second paragraph: However, at a sufficient distance prior to encountering a known obstacle or tying into an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled. The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Add the following after the seventh paragraph: Pipe location tape shall be installed directly above the water conduit in the trench and shall be approximately 458 mm above the water conduit. The tape shall be placed during backfill operations. Tape installation shall be performed in a continuous operation. A 1 meter overlap shall be provided between the ends of rolls.

The locator wire shall be installed directly above the water conduit in the trench and shall be 153 mm above water conduit. The wire shall be placed during backfill operations in a continuous operation. Wire shall be spliced as required to form a continuous strand along the length of the water conduit. The locator wire shall be brought to the surface at the point of connection at each end of the HDPE water conduits and at the gate valves.

Add the following after the eighth paragraph: A maximum 15 mm per 12 m and 30 mm cumulative deviation from design alignment and elevation will be allowed. Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed. All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the water conduit and not by blocking or wedging up. Radius of bends shall not be less than the minimum set by the pipe manufacturer.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs. He shall also have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides. The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly installed conduit and appurtenances. The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

Conduit that has the grade or joint disturbed after being laid shall be taken up and re-laid. Water shall be kept out of the trench until the jointing is completed.

627-3.03 FIRE HYDRANTS. Delete the third and fourth paragraphs and substitute the following: The Contractor shall provide all trench excavation, and compaction necessary to install the fire hydrant assembly in accordance with these plans and specifications.  Imported backfill shall  not be measured for payment.

The Contractor shall install the hydrant assemblies in accordance with the details of these drawings and specifications.

All fire hydrant legs shall be installed level.  The fire hydrant barrel shall be installed plumb.  Any adjustments to the fire hydrant traffic flange shall be made by the Contractor at no cost.

Hydrants installed, but not available for use, shall be covered with burlap and securely tied.

In lieu of valve box markers for the auxiliary gate valves, the Contractor shall paint in 51mm (2”) black lettered stencils, the direction and distances, to the nearest 30mm (1/10’), the distance to the valve box on the face of the fire hydrant directly below the bonnet flange.

627-3.06 TESTING WATER SYSTEM. Delete this subsection in its entirety and substitute the following: The Contractor shall notify the Engineer in writing 48 hours in advance (two working days) prior to any test. The Water Utility and the Engineer shall be present during all tests. Two hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or canceled. There shall be a minimum of 1.2 meters of cover over the water conduit prior to flushing and testing.

1.	Flushing. All flushing shall be coordinated with the Water Utility. All newly laid water conduit shall be "open-bore" flushed to remove any foreign matter to the satisfaction of the Water Utility. A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to hydrostatic testing and disinfection. The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing. Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.  All flushing of newly installed conduit shall be accomplished between the hours of 8:00 AM and 4:00 PM, unless otherwise authorized by the controlling Water Utility. Flushing shall be considered incidental to this work and no separate payment will be made.

2.	Hydrostatic Testing. A 19 mm, copper pipe installed at the main according to the typical water service detail, shall be run to the surface, adjacent to the water main, for testing.  The hydrostatic pressure shall be not less than 1035 Kpa (150 psi) any place within the system being tested. The test procedure consists of two steps; the initial expansion phase, and the test period.

A. 	Initial Expansion Phase.

The initial expansion phase shall last 4 hours. In order to accommodate the initial expansion of the pipe being tested, sufficient make-up water shall be added to the system 3 hours after initial pressurization, as required to return to the specified test pressure. At the completion of the initial expansion phase, a final quantity of makeup water shall be added to restore the system to the specified test pressure and the test period shall commence.

B. 	Test Period.

The test period shall be 3 hours. After this test period, a measured amount of make-up water shall be added to return to the test pressure. The amount of make-up water shall not exceed the allowance given in Table 1.

Under no circumstances shall the total time under test, including the initial expansion period exceed 8 hours at 1-1/2 times the pipe pressure rating. If the test is not completed, due to leakage, equipment failure, etc., the test section shall be permitted to "relax" for 8 hours prior to the next testing sequence.

Table 1

Allowance for Expansion Under Test Pressure *

Allowance for Expansion in Liters / 30 Meters of Pipe

3 Hour Test Period

Nominal

Pipe Size			Liters / 30 meters of Pipe

6”				3.4

8”				5.7

10”				7.9

12”				12.9

*These allowances shall refer to the actual test period and do not include water added during the initial expansion period.

The Engineer may alter these allowances based on temperature. Repair and re-testing shall continue until a passing test is obtained.

3. 	Test Pipe Removal:

Once the test is done, test sections of pipe shall be removed down to the water main and capped with a 19 mm, molded cap.

627-3.07 DISINFECTION. Delete the first paragraph and substitute the following: All portions of the water system shall be disinfected, including all valves and stops and any portion of the existing water system that might have become contaminated during construction activities. Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with AWWA C651, Disinfecting Water Mains. Water service pipe connections shall be made after the new water conduit is constructed, pressure tested, chlorinated and accepted for use by the Water Utility.

Delete the third paragraph and substitute the following: The affected system shall be treated with chlorine solution and all taps, valves, etc., shall be opened and left open until a strong odor of chlorine is noticeable in the water coming from the outlets, after which the taps, valves, etc., shall be closed. A residual of not less than 5 ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply. In no instance will a water conduit be chlorinated before "open-bore" flushing.

Add the following subsections:

627-3.08 AS-BUILT PLANS AND WORKING DRAWINGS. A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed. This as-built information shall be recorded on a print of the plans affected and on the applicable pages of the specifications with supplementary notes. This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed. Conduit and appurtenances shall be referenced by stationing, showing design line and grade, and as-built line and grade.

When the water system is completed, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specifications by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by the Water Utility.

627-3.09 WATER SERVICE CONNECTION.  The contractor shall provide water service connection in accordance with the plans.

Excavation and Backfill.  The Contractor shall provide all excavation, backfill, and compaction necessary to install water service lines in accordance with these plans and specifications.

The Contractor shall expose the mains to be tapped for distances of 1.2m (4’) in length.  Excavation on both sides of the pipe shall be carried to the bottom of the pipe.  Excess excavation below the required level shall be backfilled and compacted with sand or gravel at the Contractor’s expense as directed by the Engineer.

No water service shall be installed within a horizontal distance of 3m (10’) from a sewer service.

Hydrostatic Testing.  All 19mm through 51mm copper water service lines, fittings, and connections will be inspected for leaks under system pressure prior to backfilling.  All water service lines larger than 51mm shall undergo the requirements for Flushing, Hydrostatic Testing, and Disinfection as specified in these plans and specifications.

Abandon Water Service.  Abandon existing water services as shown on the plans.  Salvage materials and deliver to the City of Homer.  If required by the plans, replace abandoned service with a new water service as required.

627-3.10  TEMPORARY BYPASS LINE.  The Contractor shall install 6” temporary bypass line in accordance with the plans and specifications.

Construct temporary water system bypass lines as shown on the plans.  All materials used in the construction of the Temporary Bypass Line shall conform to the requirements of this section.  All required valves, pipe, fittings and incidental items required to build a functioning system, shall be part of the Temporary Bypass Line item.

Pipe may be placed on the ground surface in areas where it is not subject to damage from construction or other traffic.  Where pipe crosses driveways or side streets, it shall be buried at a sufficient depth to protect it from damage.

Contractor shall be responsible for maintaining temporary system and protecting it from damage at all times.  Water service shall not be interrupted for more than six (6) consecutive hours.

Temporary Bypass Line shall be flushed and disinfected as required in this section, prior to being put into service.  Testing of the Temporary Bypass Line will NOT be required.  If a visual inspection of any portion of the system reveals leaks, the leak shall be repaired at the Contractors expense.

After permanent water main has been installed, Temporary Bypass Line will be disconnected at all main line connections, and the main shall be plugged using a blind flange and thrust block.  Materials used to build Temporary Bypass Line, including pipe, valves, and fittings shall then be removed.  All salvaged materials will be the property of the Contractor.

627-3.11 AIR RELIEF VALVE.  The Contractor shall install air relief valves in accordance to the plans and specifications.

Excavation and Backfill.  The Contractor shall provide all excavation, backfill, and compaction necessary to install air relief valve in accordance with these plans and specifications.

After completion of all testing, all test and air vent pipe shall be removed and the corporation cock closed at the main in the presence of the Engineer and the Water Utility.

627-3.12 WATER METER VAULT.  The Contractor shall install a water meter vault, associated sump discharge line, and electrical conduit at the locations indicated on the plans and in accordance with the specifications.

The Contractor shall furnish and install a Model 777-LA vault manufactured by Utility Vault Company, Seattle, Washington, (Phone: 1-253-839-3500).  The Contractor shall furnish and install a Model 77-42C cover with offset access hole and 1.07m diameter cast iron cover. The vault shall be equipped with ladder rungs that are directly below the access.  The Contractor shall also furnish and install required risers to bring structure to the top of casting elevation shown on the plans. No more than 0.3 meters of grade rings shall be used to bring the top of casting to the elevation shown on the plans.  The Contractor shall submit shop drawings to the Engineer for approval prior to fabrication of the vault.

Any section of the PVC water main required to be removed for the vault installation shall be replaced with 12-inch DIP.

627-4.01 METHOD OF MEASUREMENT. Delete this section in its entirety and substitute the following:

1.	HDPE Water Conduit.  Measurement for furnishing and installing water main shall be per meter of horizontal distance of the various sizes as set forth in the Bid Schedule.  Measurement will be from station to station as staked in the field and as shown on the drawings, except where the grade exceeds twenty-five percent (25%), in which case measurement will be by actual pipe length.  Connecting to existing main, pressure testing, and disinfection will be considered a subsidiary obligation of the Contractor and will not be measured for payment.

2.	Furnish & Install Fire Hydrant Assembly.  Single pumper fire hydrants, complete with a 600mm to 900mm long, 152mm diameter leg, 152mm auxiliary gate valve and valve box, guard post installation, and tie rods shall be paid for per each as a unit as set forth in the Bid Schedule.  The price shall include full compensation for furnishing and installing single pumper hydrants as shown in the drawings and specifications.  Hydrant leg from water main to hydrant assembly will be paid for separately under Item 627(1-6).

3.	Remove Existing Fire Hydrant Assembly.  Fire hydrant assemblies to be removed shall be measured per each.  This shall include all work required on the plans, including, but not limited to, removing fire hydrant assembly and hydrant leg, installing blind flange and thrust block on tee in main, and salvaging and delivering hydrant assembly to the City of Homer.

4.	Gave Valves and Valve Boxes.  By the number of valves and valve boxes adjusted or installed.

5.	Waterline Asbuilts.  This item shall be paid for as a lump sum and shall include all work as stated in these specifications.

6.	Furnish & Install 6” HDPE Water Bypass.  All 6” HDPE bypass lines shown on the plans shall be measured as a complete item, on a lump sum basis.  All required labor, equipment and materials, including but not limited to, valves, pipe, fittings and incidental items required to build a functioning system, shall be part of this bid item.  No measurement of individual components required to build a functioning system, as shown on the plans, will be made.

7.	Air Relief Valve.  This item shall be measured per each.  The price shall include full compensation for all work required to complete this item as shown on the plans.

8.	Verify Existing Water Service.  Expose existing water services as shown on the plans and verify the material type of the existing pipe.  If the existing pipe is galvanized, then replace the entire service line from the main to the curb stop.  If replacement of a service line is necessary, payment shall be made under item 627(30b) and no payment shall be made for that service under item 627(30a).  Otherwise, this item shall be measured per each, and payment shall be made for exposing services under item 627(30a).

9.	Abandon and Replace Existing Water Service.  This item shall be measured per each.  The price shall include full compensation for all work required to complete these items as shown on the plans.

10.	Install New Water Service.  This item shall be measured per each.  The price shall include full compensation for all work required to complete these items as shown on the plans.

11.	Abandon Existing Water Service.  This item shall be measured per each.  The price shall include full compensation for all work required to abandon existing water service, including but not limited to, turning off corp stop at water main, disconnecting water service from corp stop, salvaging existing curb stop, key box and rod, and abandon rest of service line in place.

12.	Water Meter Vault.  This item shall be measured per each.  The price shall include full compensation for all work required to install the vault, associated sump discharge line, electrical conduit, and 12-inch DIP as shown on the plans.

627-5.01 BASIS OF PAYMENT.  Delete the fourth and fifth paragraphs.

Add the following: Abandoning existing water main or abandoning existing water service lines at locations other than at the corporation stop as designated on the Plans is subsidiary.

Add the following pay items:

| Pay Item | Pay Unit |
| --- | --- |
| 627(1-6) Furnish & Install 6” HDPE Water Conduit | Per Meter |
| 627(1-8) Furnish & Install 8” HDPE Water Conduit | Per Meter |
| 627(1-10) Furnish & Install 10” HDPE Water Conduit | Per Meter |
| 627(1-12) Furnish & Install 12” HDPE Water Conduit | Per Meter |
| 627(5) Furnish & Install Fire Hydrant Assembly | Per Each |
| 627(7) Remove Existing Fire Hydrant Assembly | Per Each |
| 627(9-6) Furnish & Install 6” Gate Valve | Per Each |
| 627(9-8) Furnish & Install 8” Gate Valve | Per Each |
| 627(9-10) Furnish & Install 10” Gate Valve | Per Each |
| 627(9-12) Furnish & Install 12” Gate Valve | Per Each |
| 627(20) Waterline Asbuilts | Lump Sum |
| 627(28) Furnish & Install 6” HDPE Water Bypass | Lump Sum |
| 627(29) Air Relief Valve | Per Each |
| 627(30a) Verify Existing Water Service | Per Each |
| 627(30b) Abandon & Replace Existing Water Service | Per Each |
| 627(30c) Install New Water Service (19mm to 51mm) | Per Each |
| 627(30d) Abandon Existing Water Service | Per Each |
| 627(32) Water Meter Vault | Per Each |

SECTION 635

INSULATION BOARD

### Special Provisions

635-2.01 MATERIALS.  Insulation Boards.  Add the following sentences: For freeze protection of existing and new water lines and sanitary sewers shall meet the following criteria.  Individual board thickness shall be 50.8 mm.  R-value shall be 0.0315 K-sq. m/W-mm minimum per ASTM C177/C518.  Compressive strength shall be 414-kPa minimum per ASTM D1621.  Water absorption shall be 0.10% by volume per ASTM C272.  Submit manufacturer’s literature for insulation board for the Engineer’s review and approval.

635-3.01 CONSTRUCTION REQUIREMENTS. Add the following paragraphs after the second paragraph: If no insulation is shown on the drawings, but the separation between the drainage facilities and existing water and sewer facilities is less than the following, then provide 50mm of insulation between them.

Water	0.6m
Pressure or Gravity Sewer	0.45m

635-4.01 METHOD OF MEASUREMENT.  Add the following after the first paragraph: For insulation installed for freeze protection of existing and new water and sanitary sewer facilities, by the square meter of 50 mm nominal thickness of insulation board in place.

635-5.01 BASIS OF PAYMENT.  Delete the words “Cubic Meter” and replace them with the following: “Square Meter”. (11/15/00)Raven

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing  equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.(05/09/02)R58M98

Payment will be made under:

| ## Pay Item | Pay Unit |
| --- | --- |
| 639(1) Residence Driveway | Each |
| 639(2) Commercial Driveway | Each |
| 639(3) Public Approach | Each |
| 639(4) Driveway | Each |
| 639(6) Approach | Each |
| 639(7) Fire Hydrant Approach | Each |

# SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

# EROSION, SEDIMENT, AND POLLUTION CONTROL

Standard Modification

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and is included in Appendix C attached to these specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT. Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 10 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9 or most current form) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.  Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or,

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-3.02 STRAW BALE BARRIERS. The Contractor shall install straw bale barriers at the quantity and location directed by the Engineer in accordance with the Alaska Storm Water Pollution Prevention Guide.  When the Engineer determines the barruers are no longer required, the Contractor shall remove and dispose of the barriers in accordance with local and state regulations.

641-4.01 METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(4) will be measured as specified in the Contract or Directive authorizing the work.

Item 641(8a) will be measured per each straw bale barrier installed at the direction of the Engineer.

641-5.01 BASIS OF PAYMENT.

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

3.	Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

- Item 641(8a) Straw Bale Barrier. At the contract unit price shown on the bid schedule to furnish and install straw bale barriers at the direction of the Engineer.

Permanent erosion and pollution control measures will be measured and paid for under the following contract items, when shown on the bid schedule:

- Rock sediment traps will be paid under Item 610(1), Ditch Lining.

- Rock check dams, rock flumes, and riprap inlet/outlet protection will be paid under Item 611(1), Riprap.

- Permanent seeding will be paid under Item 618(2), Seeding.

Silt fence will be paid under Item 633(1), Geotextile, Sediment Control.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(3)	Temporary Erosion and Pollution Control	Lump Sum

641(4)	Temporary Erosion and Pollution	Contingent Sum

Control Amendments

641(8a)	Straw Bale Barrier	Each

(08/15/01)M78

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Standard Modification

642-3.01 GENERAL.  Delete the seventh paragraph.

(06/25/99)M 79

Special Provisions

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.

(3/31/00) R252M98

Special Provision

642-3.01 GENERAL.  Add the following items after Item 10 on page 355:

11.	Measure and document the actual intersection sight distance triangles at all public intersections.  List the actual sight distance available up to 200 m.  Note locations with greater than 200 m of sight distance as “200+”.  Measure sight distance triangles as shown in Figure 1190-1 of the Highway Preconstruction Manual by setting up an instrument at the driver’s eye location.   Certify and record the results on standard “letter” sized paper and provide it to the Engineer at least 2 weeks prior to submitting shop drawings for permanent signing.  Provide an additional copy to the Regional Traffic Engineer.  (3/12/03)R269M98

642-3.03 MONUMENTS. Delete the second sentence of the first paragraph and substitute the following:  Reference all property markers/corners, monuments or accessories which may be disturbed or buried during construction.  Prepare and record Monument Record Forms in the appropriate Recorder’s Office prior to disturbing monuments.  Monument Record Forms may be obtained from the Engineer.  Reestablish monuments in their original position prior to the completion of the Project. (3/12/03)R269M98

642-5.01 BASIS OF PAYMENT.  Add the following after the first paragraph: You will not receive any payment for Item 642(9), Reference Existing Monument until the Monument Record Forms are recorded in the local Recorder’s Office. (3/12/03)R269M98

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

Standard Modification

643-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

- Signs.  Use signs, including sign supports, which conform to Section 615, the ATM and ASDS.

- Construction Signs: as designated on the Plans or on an approved TCP.

- Permanent Construction Signs: As designated on the Plans or on an approved TCP.

- Special Construction Signs: All other signs are Special Construction Signs.  Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

- Portable Sign Supports.  Use wind-resistant sign supports with no external ballasting.  Use sign supports that can vertically support a 1.2-m x 1.2-m traffic control sign at the height above the adjacent roadway surface required by the ATM.

- Barricades and Vertical Panels.  Use barricades and vertical panel supports that conform to the ATM.  Use Type III Barricades at least 2.4 m long.  Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Portable concrete Barriers.  Use portable concrete barriers that conform to the Plans.  For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe or preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section.  Use yellow reflectors or tape if the Contractor uses barriers at centerline.  The Contractor may use yellow reflectors or tape if barriers are to be installed at the centerline.  White reflectors or tape may be used if barriers are used on the roadway shoulder.

- Warning Lights.  Use Type A (low intensity flashing), Type B (high intensity flashing) or type C (steady burn) warning lights that conform to the ATM.

- Drums.  Use plastic drums that conform to the requirements of the ATM.  Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Traffic Cones and Tubular Markers.  Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular makers at least 710 mm high.  Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Interim Pavement Marking: Apply markings according to Section 670 and the manufacturer’s recommendations.  Use either:

- Paint conforming to subsection 708-2.03 with glass beads conforming to subsection 712-2.14, or

- Preformed marking tape (removable or non-removable) conforming to subsection 712-2.14, or

- Temporary raised pavement markers conforming to subsection 712-2.15 or 712-2.16 as appropriate.

- High-Level Warning Devices.  Use high-level warning devices that conform to the ATM.

- Temporary Crash Cushions.  Use approved temporary crash cushions conforming to the ATM.  Use reflective sheeting that meets AASHTO M 268 Type II or III.  Do not use permanent crash cushions as temporary crash cushions.  Use sand or water filled crash cushions only when the forecasted temperature, when used, is above 5  C.

- Sequential Arrow Panels.  Use Type a (610 x 1220 mm), Type B (762-x 1524 mm) or Type C (1220-x 2438 mm) panels that conform to the ATM.

- Portable Changeable Message Board Signs.  Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229-mm high characters.

- Eight characters display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

- Plastic Safety Fence.  Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

- “Safety Fence” by Services and Materials Company, Inc., 2200 South “J”Street, Elwood, Indian, 46036. Phone (800) 428-8185.

- “Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706.  Phone (800) 648-7974.

- “Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120.  Phone (800) 662-6338.

- Temporary Sidewalk Surfacing.  Provide temporary sidewalk surfacing as required by an approved TCP and the following:

- Use plywood at least 12 mm thick for areas continuously supported by subgrade.  Use plywood at least 25 mm thick for areas that are not continuously supported.

- Do not use unsupported 25-mm plywood longer than 750 mm

- Use plywood with regular surfaces.  Do not overlap plywood joints higher than 25 mm.

- Use a method that will withstand 40km/h wind velocities to hold temporary surfacing in place.

- Temporary Guardrail.  Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as frozen ground.

- Flagger Paddles.  Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

(10/1/00) M91

Special Provisions

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

(01/29/02)R222M98

Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://www.fhwa.dot.gov/.)

Submit documentation of compliance to the Engineer before using devices on the project.

(09/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.

(06/25/99)M 80

Special Provisions

643-3.03 PUBLIC NOTICE.  Add the following: The Contractor shall run one-sixteenth page newspaper advertisements for a minimum of one (1) week in advance on any scheduled delay, or closure of driving lanes within the project corridor. Advertisements shall be published in the Homer News and Homer Tribune.

The Contractor shall indicate on the ad order a first preference for the local news section and an exclusion for the classified section.  These advertisements shall have the project name, a map, detailed traffic information, effective dates, and provide the Contractors name and a hot-line road report telephone number for the public to access a pre-recorded message with current roadway status.

Advertisements shall be promptly canceled when they have served their purpose.  The Traffic Control Supervisor shall submit proof advertisements, on the form provided, to the Engineer for review and approval at least forty-eight (48) hours prior to intended release and a copy of the Proof of Publication with tear sheet immediately after publication.

A change order is not required for newspaper advertisements, the Notice to Proceed shall constitute the notice required to initiate newspaper advertisements.

643-3.04 TRAFFIC CONTROL DEVICES.  Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

- Power Brooming.  The Contractor shall use a power broom capable of ejecting all loose material to the shoulder of the road.  The Contractor shall remove all loose material from all pave portions of the roadway and haul routes open to the public.  This includes sections of roadway off the project where the Contractor’s operations have deposited loose material.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Add the following: No restriction to traffic will be allowed during the times listed below unless authorized by the Engineer:

1.	Monday through Friday from 0800 to 1000

2.	Monday through Friday from 1600 to 1800

Three main segments for Construction Sequencing are as follows:

- STA 0+000 – STA 0+239

- STA 0+239 – STA 1+300

- STA 1+300 – STA 6+090

All road closures and temporary construction permits are subject to approval by the Department. Final approval of road closures may be affected by other construction activities along the project route and the associated impacts on area traffic.

Allowable restrictions to traffic are:

1. 	Closure of the East End Road will be allowed in 12 hour segments at night (night defined as 1900-0700 hours) to install the culvert at Station 0+137 and to remove the existing culvert. During this period, detour traffic to Lake Street and Ben Walters Lane.

2. 	Closure of the East End Road will be allowed in 12 hour segments at night to install the culvert at Station 3+546 and to remove the existing culvert. During this period, divert detour traffic to Kachemak Drive.

3.	Closure of the East End Road will be allowed in 12 hour segments at night to install the culverts at Station 3+796 and to remove the existing culverts. During this period, divert detour traffic to Kachemak Drive.

4.	Closure of the East End Road will be allowed in 12 hour segments at night to install the culvert at Station 5+875 and to remove the existing culvert. During this period, divert detour traffic to Kachemak Drive.

5.	Side Street Closures: The following side streets may be closed at their intersection with the East End Road under the conditions specified for each street and following approval of the Contractor's street closure plan. Present the planned closures to the public at the monthly open house meeting preceding the proposed closure.

a.	Ben Walters Lane may be closed for 24 hours, with traffic diverted to Lake Street.

b.	Pennock Street may be closed for 24 hours, with traffic diverted to Ben Walters Lane and Lake Street.

c.	Alder Lane may be closed for 12 hours to install the culvert at Station 3+600 20m RT, with access arrangements to be made between the Contractor and property owners.

d.	Fairview Avenue, Kramer Lane, Kallman Road, North Mattox Street, East Hill Road, Mariner Drive, Sabrina Road, Tamara Street, Triton Court, Rochelle Road, Thompson Drive, Scenic View Drive, Williams Place, Slavin Drive, Clover Lane, Spencer Drive, East Bear Creek Drive, Meadow Drive, Little Fireweed Lane, West Bear Creek Drive, Crested Crane Street, Collie Circle, Davis Street, Jones Road, and Kachemak Drive may have one lane closed for 24 hours each, with the other lane open to traffic. Flagging will be required for traffic control.

Lane restrictions, if allowed, shall be conducted so that no more than 5 minute accumulated stopped delay is encountered by a waiting motorist through the entire length of the project, except during paving operations when 10 minutes delay will be allowed for all motorists.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following: The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET 2000 LET | Each | $3,000 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.

Payment for Item 643(29), the Engineer will pay for Newspaper Advertisements at cost plus 15 percent. The Engineer will authorize payment upon evidence of payment to the newspaper (paid receipt).

Delete Pay Item 643(15), Flagging by the hour, and add the following pay items:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

643(29)	Newspaper Advertisements	Contingent Sum

(01/29/02)R222M98

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE. Delete the third, fifth, and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 200 square meters of floor area. A minimum of 15 square meters of window area and adequate ventilation. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of ten electrical outlets.

4.	Adequate parking for a minimum of 16 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Four (4) telephone service lines available at the office location, with 1 dedicated internet service.

7.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

8.	Located in Homer, Alaska.

- Provide one move in and one move out for state office furniture and equipment.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

Standard Modification

644-2.01 FIELD OFFICE.  In the third paragraph, change “the final inspection” to “project completion”. (06/25/99)M 81

Special Provisions

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

7.	Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

644-2.05 VEHICLES.  Delete first sentence in the first paragraph and substitute the following: Furnish and maintain six (6) vehicles for the exclusive use of the Department throughout the project.  One vehicle shall be a full size 4-wheel drive shorted “crew Cab”, ½-ton minimum GVW; three vehicles shall be full size 4-wheel drive “stretch-cab”, ½-ton GVW pickups; the remaining two vehicles shall be full size ½-ton GVW, 2-wheel drive pickups.  All vehicles shall have flashing beacons.

Add the following: Equip vehicles used by the Department with CB radios and yellow rotating beacons wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

The Contractor is responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The Department is responsible for damage to any vehicle caused by its own negligent during operation. The Department will provide non-owned auto liability insurance providing third party liability coverage for any accident during the Department’s operation and use.

644-3.01 METHOD OF MEASUREMENT. Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made. (01/28/02)R245M98

Standard Modifications

644-4.01 BASIS OF PAYMENT. In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators, “.  (06/25/99)M 81

Special Provisions

644-4.01 BASIS OF PAYMENT. Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

Delete Item 644 (7), Vehicle by the day and add the following pay item:

Pay Item No.	Pay Item	Pay Unit

644(7)	Vehicle	Each

(01/28/02)R245M98

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01  DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01  OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01  GENERAL.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02  WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03  SUBCONTRACTS.  In the event the Contractor subcontracts a portion  of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01  METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01  BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

2Trainees/Apprentices

(10/29/91)S16

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION. Furnish construction equipment, operated, fueled and maintained, on a rental basis.  This equipment is for use in construction of extra or unanticipated work, only at the direction of the Engineer. The definition of construction equipment is that equipment actually used for performing the items of work specified. The definition shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

Accomplish this work under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. The Department will not be liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. Furnish, operate, maintain, service and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. Use skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth must meet minimum requirements. Furnish the number of pieces of each equipment that the Engineer considers necessary for economical and expeditious performance of the work. Use only the equipment that the Engineer directs.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturers’ specifications. Do not alter equipment to achieve the minimum rating. Replace equipment when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Fully operate all equipment. This includes the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Use competent and experienced equipment operators capable of operating the equipment to its capacity. All personnel are employees solely of the Contractor.

Provide a job superintendent or Contractor’s representative together with such other needed personnel for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and material. Furnish without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. Perform work in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer. Commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. Record time to the nearest one-quarter hour for each item of equipment listed in the bid schedule, during which equipment is actively engaged in construction of the project. Also, record the serial number and brief description of each item of equipment listed in the bid schedule. Record each day's activity on a separate sheet or sheets. A Contractor’s representative shall verify the data and sign at the end of each shift. Provide a copy to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work, on the designated areas, in accordance with the instruction of the Engineer. The pay time will not include idle periods, or time spent oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. The Engineer will not authorize payment for travel time to or from the project.

647-5.01 BASIS OF PAYMENT. This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(2)	Wide Pad Dozer, 48 kW Minimum	Hour

(11/12/98)R15M98

SECTION 660

SIGNALS AND LIGHTING

# Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-2.01 EXCAVATING AND BACKFILLING. Add the following to the first paragraph: Excavate trenches for installing rigid metal conduit to a depth 150 mm below the bottom of the rigid metal conduit.

In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following to the fourth paragraph: Embed conduits between two 150 mm lifts of material that are free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS.  DELETED

Delete the Pile Foundations subsection and substitute the following:

Pile Foundations.  Install pile foundations for light poles with shaft lengths less than 18 meters according to the following requirements

- Materials. Furnish pipe piles that feature the diameter, minimum length, and wall thickness shown on the Plans.  Furnish piles that conform to ASTM A252, grade 3.  The Department will only accept seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Furnish pile cap adapters fabricated by the pole manufacturer.

- Construction Requirements. Install the steel pipe piles open ended according to Section 505. Complete all splices and extensions in piles according to Section 505. Attach the pile cap adapter to the pipe pile with a full penetration circumferential weld.

Complete all welding shown on the Plans and as specified herein according to the Structural Welding Code –Steel, AWS D1.1-2000. At least 30 calendar days before you begin welding, submit a welding plan and mill certification reports for the pipe piles and pile caps to the Engineer for approval.  Do not begin welding until the Engineer has returned these items approved in writing.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS),

- Procedure Qualification Record (PQR),

- Welder Performance Qualification Record (WPQR),

- Visual Inspection Form,

- Report of Nondestructive Examination (NDE) of Welds, and

- The name of the Contractor’s Quality Control (QC) manager with documentation of qualifications.

Furnish all Quality Control inspection necessary to ensure the materials meet the requirements of the contract documents and workmanship meets the requirements of AWS D1.1.

- Visually inspect (VT) the entire length of each weld.

- Inspect all full penetration welds by ultrasonic NDE (UT).

Correct all deficiencies in materials and workmanship revealed by QC and Quality Assurance (QA) inspections according to AWS D1.1 without additional compensation.

Furnish all completed QC inspection documents to the Quality Assurance representative designated by the State.

Install the frangible couplings according to the manufacturer’s written installation instructions.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Add the following: Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas according to Subsection 660-2.15, Galvanizing.

Fabricate pile cap adapters from steel piles that conform to ASTM A252 grade 3 and steel plate that conforms to ASTM A709 grade 50.  Only use seamless piles or piles with a single longitudinal seam that is electric resistance welded.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Furnish the adapters hot dip galvanized according to ASTM A123, except leave the beveled edge free of zinc.  Fabricate the anchor plate to match the base plate of the lighting standard.  See the detail sheet in the plans for all dimensional information.

Complete all welding design, fabrication, and inspection according to the latest edition of the AWS D1.1, Structural Welding Code-Steel

- Circumferential Welded Splices

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Longitudinal Seam Welds

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Inspect 25% of all PJP welds of longitudinal seams by magnetic particle testing (MT)

- Base Connection Welds

- Inspect 100% of all base connection welds.

- Inspect CJP welds by UT

- Inspect fillet welds by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Quality Assurance (QA) representative for approval.  Do not begin welding until these items have been returned approved in writing by the QA representative.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS)

- Procedure Qualification Record (PQR)

- Welder Performance Qualification Record (WPQR)

- Visual Inspection Form

- Report of Nondestructive Examination (NDE) of Welds according to Annex K, latest edition of AWS D1.1

- NDE personnel qualification records

- The Contractor’s Quality Control (QC) manager with documentation of qualifications

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid and will not allow trenching after you place the final lift of asphalt.

Delete paragraph 17 and add the following: Wherever the plans show reusing existing conduits, clean them using compressed air before pulling in the new cables.  Existing illumination cables that will be reused may be left in the conduits while you clean them.  Use a heavy-duty air compressor that delivers at least 3.540 cubic meters per minute (125 cfm) of air at 0.758 MPa (110 psi).

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS. Delete the first paragraph of item 2 “Power Conductors and Cables” and add the following: Use power conductors and cables manufactured according to ICEA publication S-66-524 and NEMA Publication No. WC7, and which are UL listed and labeled for direct burial and resistance to sunlight. Furnish conductors insulated with chemically cross-linked polyethylene UL listed and labeled as type XHHW-2. Furnish cables rated for 600 volts AC operation and which do not contain an integral ground conductor.

Furnish cables consisting of three #8 AWG conductors with conductor insulation colored black, white, and red. Furnish cables with three conductors larger than #8 AWG with conductor insulation colored black, white, and red, or with all black conductor insulation with printed numbers identifying each conductor per ICEA method 4.

Delete subparagraph “d” of item 2. Power Conductors and Cables and add the following: Furnish highway and sign illumination cables that contain #8AWG conductors with a low density, high molecular weight polyethylene jacket.

660-2.08 CONDUCTORS. Delete item 2. Power Conductors and Cables and add the following:

- Power Conductors. For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, ICEA publication S-66-524, and NEMA Publication No. WC7.  Furnish conductors insulated with cross-linked polyethylene, UL listed as type XHHW-2 and rated for 600 volts AC operation.

Provide the following markings on the conductor insulation: manufacturer, conductor size, 600V, the symbol of an Approved Independent Testing Laboratory, and XHHW-2 on intervals of 2 feet or less.

Use size 10 AWG wire for illumination tap conductors.  In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors.  Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables. For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket.  Use conductors UL listed as type XHHW-2.  Furnish these cables with one black, one white, and one red colored conductor and no ground conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors that meet the requirements of ICEA publication S-66-524 and Underwriters Laboratories for Type XHHW.  The jacket shall also meet the requirement of ICEA publication S-66-524.

Provide the following markings on the jacket: manufacturer, conductor size, number of conductors, and 600V on intervals of 2 feet or less.

- Power Cables. For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene, and a PVC jacket.  Furnish these cables with no ground conductor. Use cables manufactured according to ICEA publication S-95-658 and NEMA Publication No. WC70.  Provide cables UL listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor. Provide conductors UL listed as type XHHW-2.

Provide the following markings on the jacket: manufacturer, number and size of conductors, TYPE TC, 600V, sunlight resistant, 90oC Dry 75oC Wet, and symbol of an Approved Independent Testing Laboratory on intervals of 2 feet or less.

Delete item 4. Loop Lead-In Cables and add the following:

- Loop Lead-In Cables. Unless otherwise specified, use a cable that conforms to the following specifications to connect the loop detectors to the terminal blocks in the controller cabinet.  Furnish this cable, also known as Snyder Cable; third party certified for use in underground conduit or as an aerial cable supported by a messenger, and rated for 600 volts AC operation.

Use size 18 AWG, 16 strand, tinned copper conductors per ASTM B-33 insulated with wet-rated, cross-linked polyethylene similar to XHHW.  Furnish conductors with insulation colors that match TABLE 660-1 twisted into pairs.

Provide each twisted pair with an overall aluminum foil coated mylar shield that provides 100% coverage and a 20 AWG tinned copper drain wire that is in constant contact with the foil side of the shield.

Apply a tight fitting polyvinyl chloride jacket over the conductor assembly.  Provide the following markings on the jacket: manufacturer, year of manufacture, TYPE TC, 600V, 6pr#18, sunlight resistant, 90oC Dry 75oC Wet, and name of Approved Independent Testing Laboratory on intervals of 2 feet or less.

Only use the following loop lead-in cable to rewiring existing traffic signals when specified. Use cables that consist of 6 twisted pairs that consist of stranded, size 18 AWG tinned copper wire and polyethylene or polypropylene insulation.  Furnish each pair covered with an aluminum foil shield, stranded copper drain wire, and an overall PVC or PE jacket.  Use cable rated for 300 volts and whose colored pairs match those specified in TABLE 660-1.

660-2.10 FUSED SPLICE CONNECTORS. Add the following: Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING.  Add the following after the first paragraph: Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph: All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a zinc or galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Retrofit all existing spare conduits that will contain new cables exclusively with new grounding bushings. Whenever you reuse an existing conduit that contains no ground conductor, install a bare No. 8 AWG copper wire as the ground conductor. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted. (3/30/00)R215M98

660-3.16 LUMINAIRES. Add the following: Furnish high-pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.

Furnish luminaires that

- Are UL 1572 listed for use in wet locations.

- Include a terminal block for terminating the illumination tap conductors.

- Feature an easily removed hinged door or tray used exclusively for mounting the ballast.

- Provide the illumination levels and uniformity specified (or better) in the arrangements listed on the plans when calculated according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 1983.

- Include a lamp-starting aid that plugs into a socket for easy replacement.

- Feature a wire way that meets NEC requirements for installing three #10 AWG conductors with type XHHW-2 insulation between the pole and a terminal block located in the luminaire.

- Are free of substances (such as paint) that affect photometric performance.

Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.

Luminaire Type Definitions:

MC-3:	Mast arm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

SC-5:	Short Cutoff, Type 5 as defined by the I.E.S.

Offset:	Pole top mounted luminaires designed to be offset between 6 and 15 meters from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT. Add the following: Transport all signal equipment from the project, to the State of Alaska, Highway Maintenance Yard. Allow maintenance personnel to select the equipment they would like to salvage, and dispose of all remaining equipment. Contact Maintenance Foreman shall provide one week notice of the Contractor’s intent to deliver salvaged materials.

Two existing flashing beacon systems on East End Road, including wiring and conduit, shall be salvaged and relocated as detailed on the plans.  The existing beacon off of East Hill may remain in its present location.

660-5.01 BASIS OF PAYMENT. Add the following: The prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans. This includes: completing all excavation to install foundations, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

(04/30/02)R65M98

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDERS

Special Provisions

669-1.01 DESCRIPTION.  This work shall consist of furnishing and installing, Automatic Traffic Recorder Stations for the automated collection of traffic data, and the removal of an existing ATR counter.  This work shall be accomplished prior to placement of pavement so that no cutting of new pavement will be done.

An Automated Traffic Recorder (ATR) station is a vehicle detection system, and may contain a traffic volume counter (VC), an automated vehicle classifier (AVC), a weigh in motion (WIM) system and/or other equipment.  ATRs are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Street, phone (907) 269-0885 or 269-0876.

The AVC stations in this project consist of two inductive loops and a piezoelectric axle sensor mounted in the pavement between the loops, in each lane.  All wiring from the sensors is run underground in conduit and connected to a set of electronics located in a cabinet at the side of the road.  The dual inductive loops detect the presence and speed of passing vehicles, and the axle sensor determines the number and center-to-center spacing of all axles on the vehicle.  The raw data is processed by the electronics to classify the number and type of vehicles, which is stored in the electronics for later retrieval.

The VC stations in this project consist of one inductive loop, mounted in the pavement, in each lane either independent of, or in conjunction with AVC detectors.

The AVC and VC stations may be configured to collect data on an intermittent or continuous basis.

A general description of the Automated Traffic Recorders on the project is as follows:

1.	Assembly H1. 	Automatic Vehicle Classification Site (AVC).  Contains a continuous traffic volume counter, and a continuous Automatic Vehicle Classification system in a 2-lane road section with a center left-turn lane.  No detection devices will be placed in the left-turn lane.  The traffic volume system includes two inductive loops for vehicle detection.  The AVC system includes a Three inductive loops with one piezoelectric axle sensors per lane for vehicle classification.

Electronics for the traffic volume and AVC are housed in a large controller cabinet Type AM@(Style CBA2). A Type 2, load center will supply 2.5 KVA of electrical power at 120/240V, single-phase, three-wire for system power and cellular telephone service to the cabinet. The multiple systems will be connected to the cellular telephone, which enables the data from each unit to be retrieved by a computer located at the HDS offices.  All loops, sensors, cabinet, PEEK volume counter, AVC, electronics, telephone modem, and remotely controllable code operated switch shall be supplied, installed and commissioned by the Contractor.

The existing ATR counter at this location shall be removed in its entirety which consists of a post mounted CBA2 style cabinet with power and cellular phone.  The cabinet is located on the north side of the road approximately 25 feet from the edge of curb.   The utility pole number next to the cabinet and supplying power is S3 17 7F, transformer number is 09950.  There are two loops per lane with conduit and junction boxes as required.

2.	Assembly H2. Intermitent Traffic Volumne Counter Site (VC). A single inductive loop per lane system that allows vehicle count date to be collected thru a CBA1 Type data collection cabinet.  No power or telephone connections required.

669-1.02  REGULATIONS AND CODE.  All materials and workmanship shall conform to section 660-1.02, REGULATIONS AND CODE, Standard Specifications for Highway Construction 1998 (Metric)(98M).

669-2.01  MATERIALS.  All materials provided for the work shall be new, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with subsection 660-2.09(A), Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable. All wires and cables must be home run labeled for field location in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable).

2.	Conduit.  All conduit shall be in accordance with subsection 660-2.05, Conduit.  All conduit, except for PVC conduit forming the inductive loops, shall be galvanized rigid metal.

3.	Junction Boxes.  All junction boxes shall be in accordance with subsection 660-2.06, Junction Boxes.  Junction boxes used for loops and sensor wires shall not contain any wiring or conduit greater than 24 volts.  The covers of all junction boxes used for loops or sensor wires shall be labeled ATRAFFIC@.  Junction boxes for 120/240 electrical service shall be kept completely separate from junction boxes containing loop or sensor wiring.  The covers of all junction boxes used to provide electrical service to ATR installations shall be labeled 'ELECTRIC'.

4.	Terminal Blocks.  All terminal blocks shall be provided with nickel, silver or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600vac, @20 amps, capacity for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.  All conductors shall be terminated to a terminal block, including unused or spares.

5.	Inductive Loops.  All inductive loops shall be in accordance with subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be 14 AWG copper in polyethylene tubing conforming to IMSA 51-5.

Loop lead-in cable home run shall consist of a twisted pair 18AWG stranded tinned copper wire with polyethylene insulation, covered with an aluminum foil shield, stranded copper drain wire, and PE outer jacket conforming to IMSA specification 50-2.

Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, an aluminum shield and overall PVC or PE jacket.

6.	Cabinets.  The control cabinet(s) shall be installed according to subsection 660-4.01, Installation Details.

Style CBA1 cabinets. Shall be mounted on a pedestal which is supported with a foundation per standard details as noted on the plans.

Style CBA2 cabinets.  All cabinets shall meet or exceed a NEMA 3R rating.  All cabinets shall be third party certified as an assembly.  Style CBA2 cabinets shall meet the following requirements:

a.	Cabinet Dimensions.  Unless otherwise shown on the plans, the cabinet shall be 1016-mm high, 0.560-mm wide, and 380-mm deep. The cabinet shall be mounted on a slip-base post as shown in the plans.

b.	Cabinet Construction.  The cabinet and door shall be constructed from 5052-H32 or better sheet aluminum alloy which has a minimum thickness of 3.15-mm.  The cabinet shall be unpainted, with a smooth grain finish on the exterior.  All welds shall be neatly formed and free of cracks, blow holes and other irregularities.  All inside and outside edges of the cabinet shall be free of burrs.  The cabinet shall be designed with a sloped top to prevent the accumulation of water on its top surface.

c.	Door.  The door opening shall be double flanged on all four sides which increases strength around openings and keeps dirt and liquids from entering the enclosure when the door is opened.  A door restraint shall be provided to prevent door movement in windy conditions. The cabinet door shall be a minimum of 80% of the front surface area and shall be hinged on the right side when facing the cabinet.  The door shall be furnished with a gasket that satisfies the physical properties found in UL508 table 21.1 and shall form a weather tight seal between the cabinet and the door.  The hinge shall be continuous and made either of stainless steel or of a minimum of 2.29-mm thick aluminum.  The hinge shall either be securely welded along a quarter or more of its length, or bolted to the cabinet utilizing stainless steel bolts and non-slip nuts.

d.	Latch/Lock.  The latching mechanism shall be a 3-point draw roller type.  The center catch and pushrods shall be either stainless steel or cadmium plated, Type II Class 1, equal or better.  Rollers shall have a minimum diameter of 19-mm and will be made of nylon.  A stainless steel operating handle shall be furnished with a 19-mm shank.  The lock shall be a Corbin #2 lock keyed to match existing Highway Data Section (HDS) cabinets.  Two keys shall be furnished with each lock.

e.	Shelves.  Adjustable equipment shelves shall be mounted on "C" mounting channels inside of cabinet and be supported on both sides. There shall be 2 vertical channels mounted on both sides of the cabinet and on the back, for a total of 6 inside each CBA2 cabinet. Shelves shall be constructed from 5052-H32 or better sheet aluminum alloy with a minimum thickness of 3.15-mm.  The shelf depth shall be a minimum of 267-mm.  Shelves shall be adjustable to within 100-mm of the bottom and to within eight inches of the top of the cabinet.

f.	Ventilation.  Ventilation shall be provided with louvered vents in the front door with a removable air filter.  Louvers shall satisfy the NEMA rod entry test for 3R ventilated cabinets.  The filter shall cover the vents and shall be held firmly in place with bottom and top brackets and a spring-loaded top clamp.  Exhaust air shall be vented out between the top of the cabinet and the door.

g.	Terminal Blocks.  Terminal Blocks in CBA2 cabinets shall be mounted horizontally to the inside lower left side of the cabinet.

Style CBA2 cabinets which include electrical service shall also meet the following requirements:

a.	Circuit Breaker Panel.  Shall be an enclosed circuit breaker panel conforming to FSS W-P-115C, Type 1 B Circuit Breaker Panelboards, UL67 B Panelboards, and NEMA PB1 B Panelboards with Molded Case Circuit Breakers.  The panel shall be a 40 Amp (minimum) MLO, 120/240 Volts, Two-Pole, 3 wire, type with separate neutral and ground buses in a NEMA 1 enclosure.  Circuit breakers shall consist of two 20 amp single-pole types with a minimum short-circuit interrupting rating of 10,000 AIC.  Surge protection shall be provided with the CB panel board either as a stand alone Transient Voltage Surge Suppressor (TVSS), [500 volt @ 3000 amps], mounted in the panel, or integral to the circuit breakers such as the Siemans model QSA2020TVSS. Circuit breaker #1 to serve the receptacles, and circuit breaker #2 to serve the heater, cooling fan, and cabinet light.

b.	Receptacles.  Provide Class-A [5 ma], Ground Fault Circuit Interrupting (GFCI), NEMA 5-20 [125 volt, 20 amp], Hospital Grade, duplex receptacles with indicating lights that are lighted when power is available [Leviton #6898-HG, Equal or better], mounted in outlet boxes with a metal face plates, and mounted on the inside surface of the cabinet as shown on the project drawings. Circuit all receptacles to one single-pole, 20-amp circuit breaker

c.	Cooling Fan.  A thermostatically controlled fan in the top of cabinet shall operate at a settable high temperature limit and exhaust air through a filtered and hooded vent at the top front of the cabinet. Set integral thermostat at a temperature lower than the thermostat noted in item Am@ below so that fan is controlled by the auxiliary thermostat, and not its integral thermostat.

d.	Light: The interior light fixture shall be a fluorescent, 120 volt single-tube or compact twin-tube lamp rated 13 watts minimum with a ballast that will start the lamp at temperatures down to -18o C.,similar or equal to Lightway Industries model TW13 (Equal or better). The light to be switched by a single pole switch with a locator light in the toggle mounted inside of the door.

e.	Heater:  A fan forced electric cabinet heater rated 800 to 1000 watts @ 120 VAC, similar or equal to Hoffman DAH8001B shall be installed and thermostatically controlled. Set the integral thermostat at a temperature higher than the thermostat noted in item Am@ below so that the heater is controlled by the auxiliary thermostat and not its integral thermostat.

f.	Thermostats:  Thermostats for the cabinet heater and cooling fan shall be remote bulb types with SPDT contacts rated for 16 amps @ 120 VAC for combined motor and resistive loads.  Thermostats shall be Tradeline T6031A1029 (equal or better), White-Rogers, Johnson Controls, or Sunne brands). Thermostats for the AHeater@ shall have a contact that closes on lowering temperature and set at 10 degrees C. The thermostat for the ACooling Fan@ shall have a contact that closes on rising temperature and set at 32 degrees C. Mount sensing bulbs as shown on the cabinet drawings.

g.	Certification: The Cabinet Assembly consists of the cabinet itself and all high voltage (greater than 24 volts) components that are permanently installed, including the circuit breaker panel, receptacles, light, heater, and fan as shown on the drawings or described herein.  The Contractor shall obtain certification, that the cabinet and associated permanently installed equipment, as a unit, complies with recognized applicable national standards through an authorized local or national testing agency or fabrication shop that complies with ANSI Z34.1-1987 AThird-Party Certification Programs for Products, Processes, and Services@, including but not limited to; Electrical Testing Laboratories (ETL), Underwriters Laboratories (UL), Canadian Standards Association (CSA), Electro Test Incorporated (ETI), or other certified testing agency recognized by the Labor Standards & Safety Division of the State of Alaska Department of Labor.

h.	Timer Resets:  Electronic digital timer with internal battery backup shall be installed on the power to the  code switch and modem.  The timer shall be set to momentarily turn power AOFF@ at 1:40 AM and ON at 1:42 AM each day, causing the modem and code switch to reset.  Timer shall be Intermatic Digi-set Model DT1C programmable heavy duty grounded digital timers (equal or better), available from Intermatic Incorporated, Intermatic Plaza Spring Grove , IL 60081-9698 (also available locally).  Timers shall meet the following requirements:

(1)	Rated Capacity: 15 Amps (1875 Watts) Resistive, 15 Amps (1875 Watts) Inductive, 4 Amps (500 Watts) Tungsten, 251-watt Motor Load, 120 Volts AC, 60 Hz.

(2)	ON Time: Max.- 23 Hours,59 Minutes, Min. - 1 Minute.

(3)	Manual ON/OFF Switch: permits normal use anytime without resetting.

i.	All wiring for all 120V equipment including circuit breaker panelboard, heater, light, vent fan, and power receptacles shall be in EMT, liquid tight metal flex conduit or metal clad.  Other low voltage wiring to be terminated on terminal blocks and neatly trained within cabinet using wiring duct or ties.

j.	Keyboard Tray:  A retractable tray shall be mounted to the bottom of the shelf at a convenient height for operation of a lap top computer.

7.	Asphalt Pavement.  Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement for Asphalt Concrete, Type II.

8.	Modem. The Contractor shall supply and install a Cellular Telephone/Modem.  The modem shall meet the following requirements:

CDS 8800 Kit includes:

Cellular ready MNP-1OEC Rockwell modem with TX-Cell

RS-232 interface

Real time clock

CDS telemetry software package

Controller board(Mounted in an enclosure)

Programming cable

Operations manual

- Remotely Controllable Code Operated Switch. The Contractor shall supply and install one remotely controllable code operated switch. The code-operated switch shall meet the following requirements:

Minimum four addressable ports

Speed: 1200 BPS to 115.2 KBPS, each port individually settable

Flow Control: Hardware and/or X-ON/X-OFF

Data Format: 7 or 8 data bits; odd, even, or no parity

Connectors: DB25s (female); DTE/DCE strap-settable

Power: 115 VAC, 60 Hz, 5 watts

Suggested model GS-SW283A, 4-port (COS-4) available from Black Box Corporation equivalent.

10.	Traffic Volume Counter.  The Contractor shall supply and install traffic volume equipment at Assembly H2 with the capability of counting traffic in all lanes. The permanent traffic volume counter shall be a PEEK brand unit available from PEEK Traffic Inc, 1500 N. Washington Blvd., Sarasota, Fl 34236.  Ph.(800) 245-7660, Fax (941) 365-0837.  The permanent traffic volume counter shall include:

PEEK model ADR 1000

loop card

Communications card

Rechargeable battery

2MB internal memory

Battery charger

Connective cable

Modem cable

User manual

Two (2) year extended warrantee

Automated Vehicle Classification (AVC) Counters and Sensors.  The contractor shall supply and install a 2-lane automated vehicle classification system at Assembly H1. The AVC counters and piezoelectric axle sensors shall be a PEEK brand unit available from PEEK Traffic Inc, 1500 N. Washington Blvd., Sarasota, Fl 34236.  Ph.(800) 245-7660, Fax (941) 365-0837. AVC counters and sensors shall include:

PEEK Model 2000 ADR

Digital Loop Card

Communications card

Loop cable

Power cable

Axle detector cable

Modem cable

2MB internal memory

User manual

Rechargeable battery

Battery charger

Piezo axle sensor (1 per lane), with coaxial leads long enough to reach the controller cabinet without splices

Epoxy with hardener for each piezo axle sensor

Digital Piezo Signal Analyzer Card

Two (2) year extended warrantee

669-3.01  CONSTRUCTION REQUIREMENTS.

1.	Field Inspection.  Before installation (of conduit/wiring, inductive loops, piezoelectric cable axle sensors, and cabinets) the Contractor shall notify the Highway Data Section (HDS) in writing a minimum of 3 working days (excluding Saturday, Sunday and State or Federal Holidays). A representative of the HDS shall be present to approve the installation prior to final burial or encasement. Any unacceptable installations shall be corrected and re-inspected for completeness prior to burial or encasement. Any installation buried or encased without approval by HDS personnel shall be uncovered, removed, and/or replaced at the Contractor's expense.  Any expense or delay in the project scheduling will be the responsibility of the Contractor.

2.	Wiring.  All wiring shall be installed in accordance with subsection 660-2.09(A), Wiring.  All conductors shall terminate and be soldered to "spade" type terminal lugs.

a.	All unused pairs shall be properly terminated.  At junction boxes, unused pairs shall be terminated within splices and labeled.  At cabinets, unused pairs shall be terminated to a terminal block and labeled.

b.	All wiring shall have at least two feet of slack cable in each junction box and at least six feet of slack cable available in the equipment cabinet prior to the terminal block.

c.	All wiring shall be labeled in all junction boxes.

3.	Conduit.  All conduit shall be installed in accordance with subsection 660-2.05, Conduit or as indicated on the plans.  Nylon pull cords shall be left in all conduit larger than 1 inch.  Drain holes shall be placed at the low points of all conduit.

4.	Junction Boxes.  All junction boxes shall be installed in accordance with subsection 660-2.06, Junction Boxes or as indicated on the plans.  Junction boxes used for ATR inductive loops and other sensors shall not contain wiring carrying greater then 12 volts.

5.	Terminal Blocks.  All terminal blocks shall be permanently and clearly labeled.  All wire pairs shall be permanently and clearly labeled on the block. Wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.  All conductors shall terminate and be soldered to "spade" type terminal lugs. Terminal Blocks in CBA2 cabinets shall be mounted to the inside lower left side of the cabinet.

6.	Inductive Loops.  All inductive loops shall be installed and constructed in accordance with subsection 660-4.01, Installation Details, unless otherwise specified on the plans.  In addition:

a.	Placement:  The plans are not schematics; installation of the inductive loops shall be centered within the travel lane and shall closely conform to the location and layout of conduit runs shown in the plans.  Inductive loops used for AVC within a lane shall be located 4.88-meters from leading edge to leading edge with plus-or-minus 25mm tolerance.

b.	Loops in Asphalt: All inductive loops installed through existing asphalt paving shall be installed using full-lane-width cuts a minimum of 2.44-metrers in length, with the inductive loops centered in the driving lane with a minimum distance of 300-mm to the edge of the cut. All edges of the cuts shall be tack-coated during patching to ensure full adhesion.  All full-width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from Atelegraphing@ through the final lift asphalt.  Compaction tests shall be required at the discretion of the Highway Data Manager.

c.	Installation Sequence:  All loops installed in new asphalt paving shall be installed immediately prior to final paving of the particular section of road.  Installation of loops after final lift paving shall not be permitted.

d.	Loop Size:  All inductive loops shall be formed of four turns of wire, and shall be 1.83 meters square  with plus-or-minus 25-mm tolerance.

e.	Lead-in Conduit: All lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the center line of the road.  The loops shall be installed such that the weather-sealed cover plate on the AX@' body connector is on the top.

7.	Cabinets.  The Highway Data Manager shall be consulted prior to cabinet placement, whom will verify that:

a.	All cabinets are third-party certified by a nationally recognized independent testing agency, per paragraph 669-2.01,6,n - Certification.

b.	All cabinets shall be installed out of the clear zone unless protected by safety barriers.

c.	All cabinets shall be installed with the doors facing away from the road.

- Pavement Roughness. There shall be no transverse seams, joints or roughness within fifty feet (50') of any inductive loops placed in asphalt pavement section.  The finished surface of the asphalt shall be tested with a straightedge ten (10) feet long. The surface shall not vary more than 0.5-mm from the lower edge of the straightedge in an area within fifteen meters (15m) of all sensors at the ATR installations.

At the discretion of the Highway Data Manager, a profilograph equipped with a chart recorder shall be run down each wheelpath of each lane for a distance of fifteen meters (15m)before and after each ATR installation.  The profilograph will be supplied by the Highway Data Section and shall be operated by Contractor personnel.  The asphalt surface as recorded by the chart recorder shall not vary more than 0.02 foot in ten feet (10').

9.	Piezoelectric Sensors and Electronics for AVC.

a.	Manufacturer's Recommendations:  All permanent piezoelectric sensors shall be installed per AVC equipment manufacturer's recommendations.

- Inductive Loops For AVC:  Inductive loops for AVC shall be installed prior to final pavement.  In asphalt installations, loops shall be placed in the base course (D1 gravel) beneath the asphalt.  In concrete pavement installations, the loops shall be placed on saddles above reinforcing steel.  Photos shall be taken prior to encasement.

c.	Piezoelectric Sensors for AVC:  Piezoelectric sensors for AVC shall be installed in sawcut slots in final pavement.  "Blockouts" shall not be used.  All coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least six feet of slack cable available in the equipment cabinet prior to the terminal block.

Lead-in conduits for both inductive loop wires and coaxial cables for piezoelectric sensors are installed prior to placement of the pavement.  Lead-in conduits are run at least beyond the width of the pavement, and may either be run to the junction boxes at this time or after the pavement has been completed.  The lead-in conduit for the piezoelectric sensors is capped with tape or sealant.

d.	Acceptance Testing:  Acceptance testing shall be performed by the Contractor to ensure compliance with subsection 669-3.02 Acceptance Testing.

10.	Utilities.

a.	Inspection: The Contractor shall request inspection of the Load Center by the Authority Having Jurisdiction (AHJ), the Department of Labor, Division of Mechanical Inspection (DOL/DMI) for areas outside of incorporated municipalities, or other entities, having inspection authority.

b.	Electric and Telephone Utility Connections: After approval of the Load Center by the AHJ, the Contractor shall inform the Resident Engineer as to when electric and telephone services are needed at the Load Center / Cabinet, with sufficient time to enable the Resident Engineer to schedule the service installations prior to commissioning of the equipment.  The Resident Engineer will make arrangements in writing with the Electric and Telephone Utilities to provide service to the Load Center / Cabinet.  The Utilities will provide service to the Load Center upon request of the Resident Engineer.

669-3.02 ACCEPTANCE TESTING.  The Contractor shall perform acceptance testing on all ATR installations.

1.	General Tests.  All ATR installations shall have tests conducted in accordance with subsection 660-4.01, Installation Details.

2.	AVC Acceptance Tests.  In addition to the General Tests, Acceptance Tests shall be performed by the contractor on all AVC installations. Acceptance tests shall be performed to demonstrate that the AVC system performs at or above the required accuracy.  A representative of the Highway Data Section shall be on-site during final acceptance testing.  The Highway Data Manager shall certify in writing when the installation has met the requirements of the acceptance tests.

a.	Acceptance Tests shall consist of three vehicles which will make ten passes over the AVC sensors in each lane at speeds varying from 40 to 70 kilometers per hour.  The vehicles shall be supplied by the Contractor.  Descriptions of the proposed test vehicles shall be submitted in writing by the Contractor at least 24 hours prior to scheduled performance of the test and shall be approved in writing by a representative of the Highway Data Section.

b.	The three test vehicles shall consist of a five axle, eighteen wheel single trailer vehicle (FHWA Class 9), a three axle, ten wheel single unit vehicle (FHWA Class 6), and a two axle, six wheel single unit vehicle (FHWA Class 5).

The Class 5 vehicle shall have a minimum spacing of four meters (4m) and a maximum of seven meters (7m) between the steering and drive axles, a minimum weight of one ton (1,000 KG) and a maximum of 5.5 tons (5.5 KG)on the steering axle, a minimum weight of 6.8 tons (6,800 KG) and a maximum of 8.2 tons (8,200 KG) on the driving axle.

The Class 6 vehicle shall have a minimum spacing of four meters (4m)and a maximum of seven meters (7m) between the steering axle and the drive axle group, a minimum of 1.2 meters (1200-mm) and a maximum spacing of 1.8 meters (1,800mm)between the drive axles, a minimum weight of 6000 pounds and a maximum of 12,000 pounds on the front (steering) axle for normal-width tires or a maximum of 2.7 tons (2,700 KG) for wide tires, and a minimum weight of 9 tons (9,000 KG) and a maximum of 17 tons (17,000 KG) on the rear (drive) axle group.

The Class 9 vehicle shall have a minimum spacing of four meters (4m)and a maximum of seven meters (7m) between the steering axle and the drive axle group, a minimum spacing of 1.2 meters (1200-mm) and a maximum spacing of 1.8 meters (1,800mm)between the drive axles, a minimum spacing of 7.5 meters (7.5m) and a maximum of 13.7 meters (13.7m) between the drive axle group and the trailer axle group, a minimum spacing of 1.2 meters (1200-mm) and a maximum spacing of 1.8 meters between the trailer axles, a minimum weight of 2.7 tons (2,700 KG)and a maximum of 5.5 tons (5,500 KG) on the steering axle, a minimum weight of 9 tons (9,000 KG) and a maximum of 17 tons (17,000 KG) on the trailer axle group.

All three test vehicles shall be fully loaded with non-shifting material to near legal weight limits.

c.	All tires on all three test vehicles shall be inflated to recommended pressures.

d.	The gross weight of the vehicles and the weight of each axle group shall be determined by weighing on a static scale at a scale house operated by the State of Alaska Department of Commerce, Division of Weights and Measures.  An axle group is defined as any two axles whose midpoints are within eight feet of each other.  For the test vehicles, the Class 9 single trailer vehicle has three axle groups, while the Class 6 and Class 5 each has two axle groups.

e.	Accuracy Requirements - The accuracy of Automated Vehicle Classifiers is such that, if good lane discipline is maintained:

(1)	not more than plus or minus ten percent (+ 10 %) of the total vehicles in FHWA class one through class three (1 thru 3) and,

(2)	not more than plus or minus five percent (+ 5 %) of the total vehicles in FHWA class four through class thirteen (4 thru 13) are classified in the wrong bin when compared with a concurrent manual classification count.

669-3.05  DELIVERABLES.  All deliverables shall be submitted to the Highway Data Manager prior to final approval of the work or as otherwise called for herein.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval by the Highway Data Manager within thirty days following award of the contract, three collated copies of a portfolio of equipment and materials which he proposes to install for the ATRs.  The portfolio(s) shall consist of a table of contents which includes each item's intended use(s), and a description that includes product name, manufacturer, and model or part number.

The Materials Submittal shall include a detailed shop drawing of the Style CBA2 cabinet showing the location of all mounted components, including the thermostatically controlled heater, thermostatically controlled exhaust (cooling) fan, switched fluorescent light, shelves, Corbin #2 locks keyed to match existing Highway Data Section cabinets with Corbin locks, Ground Fault Interrupt (GFI) circuit breakers, three sets of four 110 volt receptacles, eight sets of twelve position terminal blocks, surge protectors for all electrical and telephone equipment.

The Department will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

2.	Utility Schedule.  The Contractor shall submit for review and approval by the Highway Data Manager within sixty days following award of the contract, three collated copies of a schedule to install and activate electrical and telephone utilities to the ATR cabinets requiring these services.  The Utility Schedule will clearly identify in detail what actions will be taken to ensure timely activation of electrical and telephone serve, when the activity will occur, and who is responsible for completing each action.  The schedule shall include the name, employer, position title and telephone number of both who is to be contacted and who is to be responsible for completing each action.

3.	As-Built Plans.  The Contractor shall prepare four complete sets of as-built plans which will be kept current with the construction.  These as-built plans shall detail all  construction changes made to the plans and also include the following information on the appropriate sheets:

a.	The location and depth of all inductive loops and conduit runs, and,

b.	The station and offset of all junction boxes.

Redlines of full size construction plans will be acceptable.

Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

4.	Photographs.  The Contractor shall present photographs and 35 mm negatives documenting the installation of all inductive loops.  The photos shall show the loops in place prior to covering with gravel and asphalt pavement.  The photographs shall include at least one view of each loop showing the conduit to the nearest junction box, and at least two overall views of each ATR installation showing placement of the inductive loops.  The photographs shall be 5" x 7" color prints, and shall be labeled with the identification of each loop as indicated on the plans (for example;  H1 - W1NLA ).

5.	Test Results.  Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Highway Data Manager prior to acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted in accordance with subsection 660-4.01, Installation Details.

Written (computer printout) results and copies of the electronic data files collected during performance of the WIM System acceptance test shall submitted to the Highway Data Manager prior to acceptance of completion of the WIM system.

6.	Manuals.  The Contractor shall provide to the Highway Data Manager all installation, repair and operation manuals for all traffic volume and classification units.

7.	Materials.  The Contractor shall provide to the Highway Data Manager any and all epoxy grout remaining after installation.

669-4.01  METHOD OF MEASUREMENT.  The quantity to be paid for will be the completed and accepted Automated Traffic Recorder Installations as shown on the plans or as directed by the Engineer.

669-5.01  BASIS OF PAYMENT.

1.	The contract unit bid price for all Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

a.	Excavation and backfill materials required will be paid for under their respective pay items.

- Concrete Pavement required shall be paid for under a separate pay item.

c.	Asphalt required will be paid for under a separate pay item.

d.	Traffic Control shall be paid for under the appropriate pay item(s).

2.	Materials, load centers, as-built plans, the manufacturer's representative(s) and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorders.

3.	A sum equal to one-tenth (1/10) of the total cost for Pay Item 669(1) shall be withheld until after the Highway Data Manager certifies in writing that the installations have passed all Acceptance Tests in Section 669-3.02 and that all Deliverables in Section 669-3.05 have been submitted.

4.	Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1)	Automated Traffic Recorders	Lump Sum

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. 	Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps. The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display. The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 580 g/m2 for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

#### METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 90 mils (2.3 mm) | 230 mils (5.8 mm) |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils (3.0 mm) | 230 mils (5.8 mm) |
| Neutral Area (Diagonals, Chevrons) | 60 mils (1.5 mm) | Do not inlay these markings |

1. 	Measure Type V spray without glass beads.  Tolerance is ±4 mils (±0.1 mm). Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6” x 12” (150 mm x 300 mm) flat sheet of 80 mils (2 mm) thick aluminum placed in the path of the striping guns.

2. 	Cut the inlaid slots to a depth of 250 mils (6.35 mm).  Do not over fill the slots.

3.  	Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils (1.5 mm) per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 30 mils (0.75 mm).

Unless directed otherwise by the Engineer, apply the final 60 mils (1.5 mm) of the Longitudinal Type markings once the asphalt has cured for the duration listed below:

Stone Mastic Asphalt Concrete	30 days

All other				15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

Inlaid Markings

Apply markings in the milled groves after all millings have been removed. The extruded Methyl Methacrylate may be installed at the final yield thickness at the Engineer’s discretion.

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15 m longitudinal run from the width shown in the Plans.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:  All costs associated with the MMAMS are subsidiary to Methyl Methacrylate Pavement Markings and no separate payment will be made for furnishing and maintaining the MMAMS. (08/21/02)R246

# Add the following Section:

# SECTION 680

## TELEPHONE RELOCATION

# Special Provisions

680-1.01 DESCRIPTION.  This section covers the furnishing and field installation of ACS conduit system in accordance with these specifications and plans.

The conduit system includes the 2” and multiple runs of 4” PVC conduit installed by trenching, boring, cabinets and pedestals, and all appurtenances, materials and devices required to install, support, secure and provide a complete system for support and protection of the copper cable.  Upon completion and acceptance of the system, the utility or its contractor will pull the cable and install the remainder of the telephone and television system.

The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

680-1.02  CODES AND STANDARDS.  Conduit system materials and devices furnished shall be in accordance with applicable standard of ANSI, ASTM, NEMA,UL, AND ALL LOCAL CODES AND PERMITS.  Conduit systems components shall be installed in accordance with applicable requirements of the NESC.  In a case of conflict between the requirements of any of the above referenced codes and standards and requirements of these Specifications, the requirements of these Specifications shall govern.  All materials, devices, and practices shall be in accordance with the applicable requirements of the Federal “ Occupational Safety and Health Standards.”

680-1.03  LICENSING REQUIREMENTS.  The Contractor doing the actual work for ACS, HEA, and GCI shall be a licensed electrical contractor licensed by the State of Alaska and must have an employee on staff that possesses and Electrical Administrators License in the Outside Linework category.  The license must be assigned to the electrical contractor.  All employees of the Contractor installing rigid steel conduit or PVC conduit shall possess a certificate of fitness for electrical work as defined in 8 AAC 90.160, 8 AAC 90.165, and 8 AAC 90.170.  These requirements do not extend engineering or supervisory personnel of the Contractor.

680-2.01 MATERIALS.  The following materials will be furnished by ACS at no cost to the Contractor:

1.	BD8, BD7, and BD4 Pedestals.

2.	Cross Connect cabinet 1200 pair.

3.	EMS (Electronic Marker System).

4.	Ground Rods, #6 SDC ground wire, and clamps.

5.	Buried Warning Tape Orange Rolls.

- Duct Spacers.

- PVC Schedule 40 conduit, sweeps, couplings and solvent.

- 24” Cross Plate Anchors with appropriate ¾” X 8’ rods.

Within seven (7) days of receipt of Notice-to-Proceed, the Contractor shall determine the material take-off requirements and shall prepare a complete itemized list of materials for submittal to ACS.  A list of needed materials will be delivered to ACS, through the ACS Construction Clerk, at least seven (7) days in advance of delivery time.  Material shall picked up for the complete project and not on an as needed or on a daily basis.  If material is ordered at least seven (7) days in advance, ACS will stage the material for drop shipment.

All materials furnished by ACS will be located at ACS’s warehouse, 600 Telephone Avenue, Anchorage, Alaska 99503.

The Contractor shall sign for materials at the time of receipt.  The ACS warehouse foreman will be available for materials issuance between the hours of 8:00 AM to 12:00 noon and 1:00 PM to 4:30 PM daily except Saturdays, Sundays, and ACS holidays.  When necessary to open the warehouse for the Contractor’s convenience and to procure special issuing of material other than during these normal working periods, the Contractor will be billed for the loaded labor rate time involved plus 25 percent handling overhead.  Storage and safekeeping of all materials after pickup from ACS shall be the Contractor’s responsibility.  All unused materials shall be returned to the warehouse upon completion of the project.

The following items shall be furnished by the Contractor:

- Visqueen or other covering materials for concrete curing.

- Separation geotextile.

- Urethane Foam expanding 2 lbs./cu. Ft. (2 part).

- Pre-measured jet line.

- ¼” three strand poly pull line.

- All miscellaneous tools and hardware, and non-furnished material necessary to construct and install this system.

680-2.02  VERIFICATION OF DIMENSIONS.  The exactness of dimensions given on the plans is not guaranteed, and therefore the Contractor shall field verify the accuracy of all dimensions.  In all cases of interrelation with other work, the Contractor shall verify in the field all the dimensions relating to the contiguous work.  Any errors due to the Contractor’s failure to verify shall be rectified promptly at the Contractor’s expense.

680-3.01  GENERAL CONSTURCTION REQUIREMENTS. The ACS Inspector reserves the right to suspend the conduit system installation, through the Engineer, at any time the Contractor fails to meet the requirements set forth herein, until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project and will not entitle him extra payment for costs incurred.

The Contractor shall coordinate construction operations with the ACS Inspector and the on-site crew foreman.  ACS crews shall be allowed access to the job site for cable installation and splicing operations with an advanced 24-hour notice to the Contractor.

The Contractor shall be responsible for locating, shoring, and protecting of all property, (real and personal) in the vicinity of the project.  While ACS has endeavored to reflect the location of all sewer, water, storm drains, electric, telephone, gas lines, key boxes, valves, and poles in the plans, it shall be the Contractor’s responsibility to establish the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.  Offsets from project centerline and road centerline for ACS are for informational purposes only.

Once the work commences, the Contractor, the Engineer, and ACS Inspector shall meet once each week to review and validate the work completed to date and review the Contractor’s schedule for the following week’s work.  The Contractor shall submit in writing his anticipated hourly work shift schedule by the Wednesday noon prior to the workweek.

All telephone pedestals shall be constructed within an allowable tolerance of 0.03-meters of the plan location and elevation in any phase of the construction. Final grade of telephone pedestals shall be field verified by the ACS Inspector prior to backfill.  The Contractor will backfill all pedestal and trench excavations within 48 hours. At no time shall the Contractor leave exposed more than 30 meters of trench at end of shift.

The Contractor is advised that project operations are within a restricted access corridor and all staged materials, equipment, and vehicles shall stay off the traveled surface.  Use of all wide shoulders and turnouts shall be at the permission of the Engineer.  Use of private property for this purpose shall be granted in writing by the property owner and approved by the Engineer prior to its use.

The Contractor is advised that only ACS pre-qualified contractors may install ACS telephone facilities. The Contractors shall be pre-qualified at the time of bidding. A list of qualified contractors may be obtained by contacting the ACS purchasing office at (907) 564-1414.

680-3.02 TRENCH AND PAD EXCAVATION AND BACKFILL.  Excavation work shall be accomplished in accordance with these Special Provisions and Section 204, Structure Excavation for Conduits and Minor Structures.

When the telephone and electrical power utilities are jointly installed in the same trench, the trench excavation and backfill shall meet the requirements of subsection 681-3.02, Trench and Pad Excavation and Backfill.  The work will be paid under item 681(UR4).

When the telephone utility is installed by itself, the trench excavation and backfill work will be paid under item 680(10).

All existing underground utilities shall be identified, located, and proper care taken not to damage them.  It shall be the Contractor’s responsibility to establish the location of each facility by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

Trench depth shall be as shown on the plans, and as staked in the field.  Trenches shall be of the necessary width that will allow compaction equipment to be utilized, and for proper laying of conduit and installation of pads.  The trench unit shall include all labor and equipment necessary to construct the facility in accordance with the plans and specifications.  Extra compensation shall not be granted for hand digging and/or utilization of an “air knife”.  The banks of the excavation shall be sloped so as to conform to the prevailing safety requirements.

All trench transition areas shall be gradual in terms of depth.  Offset conduit bends shall not be permitted.  At all transition locations, the “shallow” trench transition to meet the “deep” trench at a slope not to exceed 10:1.  Work associated with the trench transitions shall be incidental to the construction of the trench unit and not be considered a separate pay item.

Construction shall be arranged so the trenches will be left open for the shortest practical time to avoid creating a hazard, and to minimize the likelihood of trench collapse due to other construction activity, rain, and accumulation of water in the trench, etc.  All temporary bridging utilized by the Contractor shall be approved by the Engineer prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength. Any bridging open to public traffic will provide a smooth driving joint.

The Contractor shall not begin excavation of the trench until all personnel, materials, and equipment are present to complete the work in the most expedient manner.  The Contractor shall backfill all vault and trench excavations within 48-hours.  There shall be no more than 30 meters of open trench at the end of the work day, unless approved by the Engineer.

The routing of the ducts shall be as shown on the plans unless the conditions encountered are such that changes are necessary to accomplish the work.  In the event that rock or other obstructions are encountered during the trenching operation so the ducts and pads cannot be installed, the Contractor shall inform the Engineer of the nature and extent of the difficulty encountered for his review and verifications.  The Engineer, with the approval of ACS, will determine whether the duct is to be rerouted, trenched through the obstructed area or advise on another suitable change.

All excavation shall be inspected and approved by the Engineer before the duct installation is started.

The bottom of the trench must be transversely level to provide a uniform support for ducts.  All rocks or other materials, which could damage the duct, shall be removed from the trench bottom before placing the duct.  Care shall be exercised to minimize the likelihood of water flow since this may cause trench damage and reduction in trench depth.  When this occurs, the trench must be cleared to the required depth before installing the ducts.

Native materials may be utilized for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07,Selected Material, shall also pass a 75-mm.  Native backfill material shall be placed in layers and compacted as directed by the Engineer.

Disposal of waste excavation shall meet the requirements of the subsection 680-3.07, Disposal of waste Excavation.

Sand bedding shall meet the requirements of subsection 680-3.09, Sand Bedding.

It shall be the Contractor’s responsibility, with the Engineer’s approval, to determine the most expedient method to complete the required trench work.  All work across the roadway shall be accomplished in accordance with Section 643, Traffic Maintenance.

680-3.03  GENERAL CONDUIT  INSTALLATION REQUIREMENTS. Conduit shall be laid in the trench as shown in the plans.  All rocks or other materials, which could damage the conduit, shall be removed from the trench bottom before placing the conduit.  Where a minimum cover of 1200 mm when in the DOT ROW embankment cannot be maintained, the Contractor shall, obtain written approval from the ACS Inspector to vary the depth requirement.  Where design depth cannot be obtained the Contractor shall supply concrete encasement for protection of the installed ACS facilities.

In cases where the conduit passes above or below an underground utility line, culvert or other buried inverts the Contractor shall maintain a minimum clearance of 600 mm from the conflicting obstruction.  Contractor may be required to over excavate trench in order to provide adequate cover for the conduit installation.  Contractor shall ensure smooth transitions of trench over abrupt terrain and will be required to over excavate to provide a smooth uniform installation of the conduit.  Such over-excavation is to be incorporated within the provided units; no other compensation shall be considered or authorized.  Contractor is advised to contact the ACS Inspector and the Engineer to determine if an over excavation is required.

The Contractor shall be required to transition ACS conduit to terminate in pedestals and cabinets. Such transitions may require sweeps and elbows to maintain adequate clearance from other utility facilities.  The Contractor shall not be allowed to install ACS conduit under other utility surface equipment.  Any transition of ACS conduit to provide proper clearance shall be incorporated within the trench units no other compensation shall be considered or authorized.

Defective conduit shall not be installed and shall be removed immediately from the site of the work.  Particular care shall be taken to keep concrete or other substances from the inside of the conduits during construction.  All reinforcing materials and other magnetic materials shall be parallel to the lengths of the conduits, except for anchoring material.  The Contractor is responsible for anchoring the installed system to ensure that flotation does not occur.  The Contractor shall submit an anchoring design to the Engineer for approval prior to its use.  Carlon plastic spacers shall be utilized in joint trench to maintain separation of utility facilities.  Spacers shall be placed at five (5) foot intervals and plastic bases shall be adjusted in lose trench bottom to minimize sag in the conduit installation.  Trench bottom shall be smooth and leveled prior to conduit installation.

Prior to ACS installing cable in the conduits, the Contractor shall clean and test the conduits.  Conduit, which will not be immediately used, shall be plugged with an airtight seal at each end and marked with an EMS marker by the Contractor.  All foreign materials, earth, sand, and gravel shall be removed from the conduit.  As a clearance test, all ducting shall be mandrel with a flexible mandrel being ¼” less in diameter than the interior diameter of the conduit.  Prior to clearance testing the Contractor shall install a Green Lee pre-measured jet line in one (1) ACS conduit from access point to access point.  A 4” wire brush shall back up all mandreling of 4” PVC.  The Contractor shall leave in place a contractor provided ¼” three strand poly pull line.  This work shall take place in the presence of the ACS Inspector.  The pre-measured jet line for ACS duct shall be measured and recorded by the Inspector and verified by the Contractor’s signature in the presence of the Engineer.  The above requirements shall take place prior to the installation’s acceptance by ACS.  The Contractor shall identify and expose any area that cannot pass a missile and repair any Contractor caused defect at the Contractor’s cost.  The Contractor and the ACS Inspector shall measure and record the ped to ped distance of the installed duct and record that measurement on the drawings provided by the Engineer.  Proofing of duct shall immediately follow conduit installation from access point to access point.  Proofing of ducting shall be considered incidental.

The Contractor shall maintain a complete and accurate record of conduit offsets and conduit distances.  The Contractor shall supply the Engineer with a complete log of conduit distances within five (5) days after installation all conduit.

680-3.04  INSTALLING SCHEDULE 40- 2” and 4” PVC CONDUIT.  All ducts and conduits shall be installed to conform to the line and grade shown on the plans or as directed by the Engineer.

The inside of all PVC conduit fittings and the ends of all PVC ducting shall be painted with PVC solvent cement as prescribed by the manufacturer to make a waterproof connection.

The Contractor shall install PVC conduit in open trench as to manufacturer’s recommendations and as depicted in the plans, with no more than 5 degree deflection per 3.05 meters of run.  All conduit installations shall be cleaned of dirt and debris.  As a clearance test, the Contractor shall pass a ridged mandrel being not less than 300 mm long, and not less than 6.25 mm diameter than the I.D. of the conduit.  The Contractor shall then leave in place an ACS provided pull line.  The cost of mandreling and installation of jet line shall be considered incidental to this contract and shall be incorporated in the cost of ducting.

All terminating conduit ends shall be secured with temporary end caps, and those terminations below grade shall be installed with an EMS.  Terminations in a telephone vault shall be either duct sealed, mortared, or urethane foamed at the direction of the ACS Administrator.  Some PVC conduit runs may require the installation of owner-furnished expansion couplings as directed by the Engineer and the ACS Inspector.

The Contractor may be required to field bend the PVC conduit as set forth on the plans; however, ACS will make available standard 5, 221/2, 30, 45, and 90 degree PVC conduit sweeps.  The ACS Inspector prior to installation will inspect all PVC conduit that is formed and bent by the Contractor.  Any bent conduit that is deformed will be unacceptable and will be removed and replaced at the Contractor's expense.  The cost of field bending conduit shall be considered incidental to this contract.

The Contractor shall design and provide all anchor stakes to prevent the conduit from floating.  The Contractor shall be responsible for the effectiveness and shall bear all costs incurred if "flotation" or misalignment occurs.

All conduit encasement shall be as detailed on the plans.

680-3.05  Pedestal Placement.  The Contractor shall place an above ground pedestal to conform to industry standards as depicted in Exhibit A.  Pedestal installation and placement shall include of all pedestal parts, extensions (U-Guards), stakes and/or post, gravel, ground rod, and copper wire. required tamping, and the placement of conduit as required at each location.

680-3.06  Cross Connect Cabinet Placement.  This unit will consist of the labor and materials to pole mount a BDS1S-300 cross connect in place.  This unit includes all the labor and materials to complete the installation, with the exception of the modules or screw blocks.  Included in this unit shall be the cabinet, cabinet mounting accessories, internal mounting hardware such as frames, mounting brackets, splicing ladders and talk block, grounding connector, bonding connectors and harnesses in accordance with ACS specs, pea gravel if required, or sealer, such interface number and direction markings and conduit placement and such labor and materials to complete the installation.

680-3.07  DISPOSAL OF WASTE EXCAVATION.  Waste excavation may be disposed of within the project limits at locations approved by the Engineer.  Waste disposal areas shall be feathered into surrounding grounds with no noticeable break or variation readily discernible and existing drainage patterns shall be maintained.

DELETED

680-3.09  SAND BEDDING.  DELETED  The Contractor shall provide bedding sand meeting the following:

Sieve Size	Present Passing by Weight

6.25mm or ¼ -inch	100 %

0.075mm or No. 200	0-6%

680-3.10  SURVEYING AND STAKING.  Conduit alignment and any changes to the alignment shall, as per the plans, be subject to the approval of the Engineer and the ACS Inspector.  All pedestals and telephone conduit shall be located and staked at the alignment and elevations indicated on the plans.  It shall be the Contractor’s responsibility to schedule a physical check of all line and grades prior to placing any of the pedestals and conduit.

All ducts shall be constructed to within an allowable vertical tolerance of 3 mm and a horizontal tolerance of 6 mm from the indicated plan locations.

680-3.11  AS-BUILT DRAWINGS.  A complete and accurately dimensioned record of all deviations, deletions, additions, and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.  A read only CD disk with ACS’s Auto Cad R14 design drawing files will be provided by ACS to the Contractor.  Two (2) of each final red-lined as-build drawings shall be delivered to the ACS Inspector and the Engineer prior to final acceptance of the system.

The Contractor shall maintain an accurate record of the underground location of all the telephone conduits installed on the prints provided by ACS.  The prints shall include all references to the road centerline, existing land marks, and exact locations of all peds.  As-builts shall note all obstructions i.e. existing utilities, culverts and line grade and elevation changes.  Reference to ACS orientation in joint trench shall also be noted.  When the ACS conduit system is completed, the Contractor shall certify the accuracy of the construction survey notes and each revision on the plans by written signature endorsement, by a land surveyor registered in the State of Alaska.  The Contractor shall deliver them to the Engineer prior to final acceptance of the system by ACS.  In addition the Contractor shall provide one (1) CD to ACS with each utilities as-built Auto Cad R14 files in the layering pattern provided by ACS on the read only CD and deliver them to the Engineer.

680-3.12  ACS INSPECTION.  ACS may at any time have access to the project site for the purpose of inspection.  The Contractor agrees to notify ACS at least forty-eight (48) hours prior to the start of this project.  The manner of undergrounding of the  PVC conduit, materials, and equipment used therein, shall be subject to the inspection of ACS.  Prior to backfilling any of the trenches for the ACS conduit, the ACS Inspector will measure the conduit.  ACS will conduct a final inspection within ten (10) days of the Contractor’s informing ACS’s Inspector, in writing, that the ACS system is complete.  Incomplete items (punch list) as noted in final inspection report, shall be completed by the Contractor within ten (10) days of the final inspection.

680-4.01 METHOD OF MEASUREMENT.  All surveying and staking required for the staking of the 680 Items for this project will be measured and paid for under Item 642(2), Construction Surveying.

Item 680(2), Telephone As-Builts will not be measured for payment but will be compensated as a Lump Sum item.

Item 680(3-1), Install 2-Inch PVC Conduit.  The 2-inch PVC conduit placed in sand bedding will be measured by the meter.  Measurements between vaults will be wall to wall measurements.

Item 680(3-2), Install 4-Inch PVC Conduit.  The 4-inch PVC conduit placed in sand bedding will be measured by the meter.  Measurements between vaults will be wall to wall measurements.

Item 680(8), Pedestal Installation.  This item will be measured by the unit completed as per the plan detail and accepted in final position.

Item 680(10), ACS only trench will be measured by the meter along the trench at the required width and depths as specified on the plans.  Joint trench with HEA will be paid under 681(UR4).

680-5.01 BASIS OF PAYMENT.  All surveying and staking required for the 680 Items for this project will be measured and paid for under Item 642(2), Construction Surveying.

Payment for item 680(2), Telephone As-Builts.  As-builts will be full compensation for providing two (2) sets of red-lined drawings as set forth in subsection 680-3.11.  The Contractor shall be required to have a land surveyor registered in the State of Alaska stamp the as-built drawings.

Payment for Item 680(3-1), Install 2-Inch PVC Conduit.  The 2-inch PVC conduit to be placed into a common trench or separate trench as indicated on the plans, at the quantity indicated on the plans.  The installation of the grounding wire, warning tape, sweeps, couplings, solvent, BSW, marker tape, conduit spacers, and conduit mandrelling are all considered subsidiary to this item.

Payment for Item 680(3-2), Install 4-Inch PVC Conduit.  The 4-inch PVC conduit to be placed into a common trench or separate trench as indicated on the plans, at the quantity indicated on the plans.  The installation of the grounding wire, warning tape, sweeps, couplings, solvent, BSW, marker tape, conduit spacers, and conduit mandrelling are all considered subsidiary to this item.

Payment for Item 680(8), Pedestal Installation.  Pedestals (BD4, BD7, BD8, and DBS1S-300) will be full compensation for installing the ACS furnished vaults as detailed on the plans.  No separate payment will be made for the grading excavation, bedding, backfill, ground rods, and ground wire, EMS marker, conduit sweeps, and transitions into handholes or vaults and other items necessary to install a complete unit.  These items will be subsidiary to Item 680(8).

Payment for Item 680(10), Trench Excavation and Backfill.  The payment for the trench shall be paid by the meter.  The payment shall be full compensation for labor and equipment for trenching and backfilling for placement of conduits, as detailed on the plans.  The disposal of waste excavation shall be subsidiary to the trench.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 680(2) | Telephone As-Builts | Lump Sum |
| 680(3-1) | Install 2-Inch PVC Conduit | Meter |
| 680(1) | Install 4-Inch PVC Conduit | Meter |
| 680(8) | Pedestal Installation | Each |
| 680(10) | Trench Excavation and Backfill | Meter |

Add the following Section:

## SECTION 681

## ELECTRICAL POWER RELOCATION

Special Provisions

    - DESCRIPTION.  The Contractor shall be responsible for furnishing all labor, equipment, and materials (other than listed on the Owner Furnished Materials Listing) necessary to construct electrical duct banks (both concrete encased and direct buried), junction boxes, switching cabinet pads, fiberglass pedestals, transformer pads and associated electrical grounding for Homer Electric Association (HEA).  The electrical duct banks will consist of multiple conduits of the number and size shown on the staking sheets and plans.  Upon completion and acceptance of the duct system, HEA will provide and install the electrical power cable, switching cabinets transformers, and other electrical equipment.  HEA will remove the existing aerial facilities including the existing poles. The utility staking sheets and details are included for the Contractor’s information.

The Contractor shall also provide as-built drawings in accordance with the conditions prescribed herein.

The Contractor doing this work shall be a licensed electrical contractor licensed by the State of Alaska, must be approved by HEA, and must have an employee on staff who possesses an Electrical Administrators license in the Outside Linework category. The Contractor shall also be on HEA’s pre-qualified Contractor list at the time of bidding.  The Contractor’s work will be closely inspected by HEA with their instructions relayed to the Contractor through the Engineer.  The HEA representative will be assigned for the entire underground installation, and no work shall proceed without him on site.  The Contractor shall advise HEA in writing at least 24 hours in advance of his actual duct system work indicating both location and time.

    - MATERIALS.  Owner furnished materials (all conduit, PVC and RMC sweeps, conduit plugs, concrete pads, fiberglass pedestals, ground rods, and misc. materials shown on the material issue ticket) will be available for the Contractor to pick up during regular HEA working hours, at the HEA yard located at 3977 Lake Drive in Homer, Alaska.  The Contractor shall be responsible for all handling, loading, and transportation to the jobsite.

Within five (5) days of receipt of Notice-to-Proceed, the Contractor shall determine his material take-off requirements and shall prepare a complete itemized list of materials for submittal to HEA.  The materials will be staged for pickup at the agreed upon time, based on submittal of a material list four (4) calendar days prior.  Materials shall be picked up for the complete project and not on an as needed basis.  Materials will be loaded on the Contractor’s vehicle by others at no cost to the Contractor.  The Contractor shall sign for materials at the time of receipt.

HEA’s warehouse foreman will be available for material issuance between the hours of 9:00 AM to 11:30 AM and 1:00 PM to 3:30 PM daily except Saturdays, Sundays, and legal holidays.  HEA will require a minimum of 24 hours notice prior to pickup; the Contractor should contact HEA at (907) 235-8551.  Where it is necessary to open the warehouse for the Contractor’s convenience and to procure special issuing of material other than during these normal working periods, the Contractor will be billed for the loaded labor rate time involved plus 25 percent handling overhead.  Storage and safekeeping of all materials after pickup from HEA shall be the Contractor’s responsibility.  All unused materials will be returned to the warehouse upon completion of the project.

The duct banks will consist of rigid steel conduit (RSC) and/or Schedule 40 rigid polyvinyl chloride (PVC) conduit.  RSC or Schedule 40 PVC conduit shall be used for all duct banks.  RSC conduit shall be manufactured of mild steel with a galvanized coating.  Conduit locator plates shall be supplied by the Contractor and be standard materials for locating the ends of buried conduits when not brought above ground.  All conduits shall have a pull line installed. All open conduit ends shall be plugged with blank duct plugs equipped with means of securing pull line to the back plate of the plug.

Concrete encased duct bank shall be installed where so dictated in the plans.  For all concrete encased duct bank sections the cement shall be a recognized standard brand Portland Cement contained in 42.6-kg sacks or 170.4-kg barrels bearing the manufacturers name.  The cement shall conform to the AASHTO M-85. The concrete mix shall be designed to produce a plastic and workable mixture, and a compressive strength at 28 days of at least 17237 kPa.  Only pre-mix concrete will be allowed.

    - APPLICABLE STANDARDS AND CODES.  In order to resolve any questions on safety regulations, installation practices, and testing procedures, the Contractor shall consult and make himself familiar with the applicable parts of the current editions of the following standards and codes:

- Alaska State Safety Code

- Homer Electric Association Safety Code

- Arctic and Sub Arctic Construction - Utilities, US Army Corps of Engineers

- Alaska State Safety Code

- National Electrical Code

- National Electrical Safety Code

- National Electrical Manufacturers Association

- Occupational Safety Health Act

- Underwriters Laboratories

All equipment and material furnished under this Section shall conform to the latest applicable specifications and rules of the National Electrical Manufacturers Association, American Standards Association, Institute of Electrical and Electronic Engineers and the Federal Specifications cited hereinafter.  As appropriate, all materials used shall be listed on the latest "List of Material Acceptable for Use on Systems of RUS Electrification Borrowers", and approved for this electrical system by HEA.

All materials furnished shall be standard equipment and be of the manufacturer’s latest design.  These materials shall be new, and not used, manufacturer’s seconds or rejects.  Where two or more units of the same class of material are required, they shall be like products of the same manufacturer.

    - VERIFICATION OF DIMENSIONS.  The exactness of dimensions given on any HEA drawing is not guaranteed, and therefore the Contractor shall field verify the accuracy of all dimensions.  In all cases of interrelation with other work, he shall verify in the field all the dimensions relating to the contiguous work.  Any errors due to the Contractor’s failure to verify shall be rectified promptly at the Contractor’s cost.

    - GENERAL CONSTRUCTION REQUIREMENTS.  HEA, through the Engineer, reserves the right to suspend the electrical duct bank installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project and will not entitle him to extra payment for costs incurred.

The Contractor shall work continuously a minimum of six (6), 10-hour days per week to accomplish the work in a timely manner to allow road work contingent upon the electrical relocation to be performed.  The Contractor shall complete the relocation in three segments, beginning only one segment and completing that segment before beginning another.  The segments will be completed in the order listed unless otherwise approved in writing by HEA.  The electrical relocation segments will be as follows:

Segment 1:  Equipment # S3/20/5300 to # S3/16/3053

Segment 2:  Equipment # S3/16/2954 to # S3/16/6721A

Segment 3:  Equipment # S3/16/6721 to # S3/11/6148

Close coordination with HEA will be necessary to assure the operation of the electric distribution system is not impacted.

The electrical duct banks shall be installed to result in the maximum degree of reliability and maintenance-free operation.  Kinked ducts, inadequately supported, protected or swabbed ducts, and ducts that are carelessly jointed are not reliable and therefore unacceptable.  Any section of this electrical duct system that is not acceptable will be removed and replaced in accordance with these Special Provisions.

All conduit shall be stored to prevent damage or contamination prior to installation.  Conduit shall not be laid directly on the ground or floor.  It is preferable to store the conduit in a vertical position.  They shall be kept clean and dry as possible and free from damaging or deteriorating elements.  Temporary storage and installation of electrical duct banks shall be in accordance with NEMA Bulletin TCB-2 (1976), "Users Manual for the Installation of Underground Plastic Duct".

The existing electrical and/or public easements restrict the area available for the Contractor’s construction activities.  Throughout the project, the Contractor shall take all necessary precautions to insure the construction activities do not impact areas outside the existing electrical and/or public easements.  Existing HEA facilities also restrict construction areas.  The Contractor shall protect HEA facilities and at all times maintain them in good operational condition.  Shoring of trenches, existing power poles, and existing pad mounted equipment shall be completed by Contractor with all associated costs covered in the trenching unit bid price.

If construction or excavation require the removal of any existing privately owned facilities on the provided electrical easements, the Contractor shall be responsible for coordinating with the owner and for restoring lawns, driveways, parking lots, etc., to their original condition.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two (2) weeks.  All restorative work shall be inclusive to the trench unit bid price.

A program of cleanup operations shall be carried out on a continuous basis throughout the progress of construction and the site shall be left neat and clean.  All equipment, devices, and structures shall be inspected after installation has been completed and any damage shall be repaired or replaced as directed.

One (1) week prior to the pre-construction meeting the Contractor shall submit a written work plan for approval.  This work plan shall detail equipment, manpower, and schedule Contractor will use to complete the project.  Shoring techniques to maintain existing facilities during adjacent excavation shall also be stated in this work plan.  Once work commences, the Contractor, the Engineer, and HEA’s Inspector will meet at the end of each week to review the work to date and plan the following week’s work.  The Contractor shall submit in writing his anticipated hourly work shift schedule by noon on the Wednesday prior to the next work week.

    - SURVEYING AND STAKING.  Conduit alignments shall be per the plans and any changes to the alignment will be subject to the approval of the Engineer. All vaults and electrical conduit shall be located and staked at the alignment and elevations indicated on the plans.  If elevations are not provided on the plans, the conduits shall be installed at the depth specified on the plan set.

All vaults, pads, and electrical duct systems shall be located and staked by the Contractor at the elevations indicated on the plans.  It shall be the Contractor’s responsibility to schedule a physical inspection of all line and grade prior to placing any vaults, pads, or ducts.  These elevation checks shall include top of pad elevations to assure adequate clearance for the pads from final grade.

All duct systems shall be constructed to within an allowable vertical tolerance of 30.5mm, and a horizontal tolerance of 61.0mm from the indicated plan location.

    - TRENCH AND PAD EXCAVATION AND BACKFILL.  Excavation work shall be accomplished in accordance with these Special Provisions and Section 204, Structure Excavation for Conduits and Minor Structures.

All existing underground utilities shall be identified and located and proper care taken not to damage them.  It shall be the Contractor’s responsibility to establish the location of all existing underground facilities by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

The excavation shall be dug in such a manner as to provide a foundation of non-frost susceptible material on which to install the vaults, pads, or electrical duct banks as shown in the plans.  Trench and equipment foundation depth shall be as shown on the plans.  Trenches shall be of the necessary width that will allow compaction equipment to be utilized and for proper installation of structures or conduit.  The trench unit shall include all labor and equipment necessary to construct the facility in accordance with the plans and specifications.  Extra compensation shall not be granted for hand digging and/or utilization of an “air knife”.  The banks of the excavation shall be sloped/shored so as to conform to the prevailing safety requirements.

The trenches shall be maintained in a safe manner at all times to protect workers from cave-ins.  Appropriate shoring shall be employed to assure safety of workers while working in trenches.  Barriers and warning signs shall be employed to protect the public and employees from falling into trenches where such trenches are in areas vulnerable to these accidents.  Vehicles and excavation equipment must not cross over or run near trenches that could cause potential cave-ins.

Construction shall be arranged so the trenches will be left open for the shortest practical time to avoid creating a hazard and to minimize the likelihood of trench collapse due to other construction activity, rain, and accumulation of water in the trench, etc.  All temporary bridging utilized by the Contractor will be inspected and approved by the Engineer prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength.  Any bridging open to public traffic will provide a smooth driving surface.

The Contractor shall not begin excavation of the trench until all personnel, materials, and equipment are present to complete the work in the most expedient manner.  Not more than 122 meters of trench shall be open in advance of the installation unless authorized in writing by the Engineer.  The Contractor shall backfill all pad and trench excavations within 48-hours.  There shall be no more than 30 meters of open trench at the end of the work day, unless approved by the Engineer.

The routing of the duct banks shall be as shown on the plans and staking sheets unless the conditions encountered are such that changes are necessary to accomplish the work.  In the event that rock or other obstructions are encountered during the trenching operation such that the ducts or pads cannot be installed, the Contractor shall inform the Engineer on the nature and extent of the difficulty encountered for his review and verification.  The Engineer, with the approval of HEA, will determine whether the duct is to be rerouted, trenched through the obstructed area, or advise another suitable change.

All excavation shall be inspected and approved by the Engineer before duct bank installation is started.  After the ducts are installed, the Engineer shall approve their line and grade prior to concrete encasement or sand backfill.  Trench, conduit installation, and concrete placement acceptance forms shall be filled out by HEA and signed by the electrical subcontractor after approval of each stage.  Failure to complete these forms will result in the rejection of the work.  The Contractor shall provide 24-hour written notification to HEA when a section of the duct system is ready for an acceptance inspection and a time for this inspection shall be mutually agreed upon.  Failure by HEA to attend the prearranged inspection shall not relieve the Contractor of the requirement to have the section accepted by HEA.  However, any additional costs involved will be in accordance with Section 104, Scope of Work.

All material below the specified trench depth shall be removed to a depth of 0.6 meters below specified trench depth.  Backfill shall be composed of materials meeting the requirements as specified on the plan drawings.  All materials shall be deposited in layers not exceeding 200mm and each lift (excluding sand) shall be compacted to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankments with Moisture and Density Control.  Note the final 50mm of over excavation fill shall be sand as shown in the plans.

All costs associated with the excavation, backfill importation, and excavation disposal shall be included in the trench unit bid price.  Disposal of waste excavation shall meet the requirements of subsection 681-3.07, Disposal of Waste Excavation.

All material below the specified equipment pads shall be removed to a depth of 0.6 meters below specified trench depth.  As shown in the plans, separation geotextile will be placed below the equipment pad at the over excavation elevation.  Backfill to the equipment pad grade will be with material meeting the requirements of Selected Material, Type A for Utilities, and deposited in layers not exceeding 200mm.  Each lift shall be compacted to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankments with Moisture and Density Control.  All cost associated with the excavation, backfill importation, separation geotextile, and excavation disposal shall be included in the equipment pad assembly unit bid price.  The separation geotextile shall meet the requirements of subsections 630-1.01 to 630-3.01.

All trench transition areas shall be gradual in terms of depth.  Offset conduit bends shall not be permitted.  At all transition locations, the “shallow” trench transition to meet the “deep” trench at a slope not to exceed 10:1.  Work associated with the trench transitions shall be incidental to the construction of the trench unit and not be considered a separate pay item.

The bottom of the trench must be transversely level to provide a uniform support for ducts.  Care shall be exercised to minimize the likelihood of water flow since this may cause trench damage and reduction in trench depth.  When this occurs, the trench must be cleared to the required depth before installing the ducts.

If large quantities of water are evident, the Contractor may elect to backfill with 50mm to 150mm coarse rock overlaid with a separation geotextile fabric.  All costs associated with this or any other option shall be included in the trenching unit bid prices.

When the duct bank passes below the structural section of the roadway, Selected Material, Type A Trench Backfill, shall be utilized for backfill to 200mm above the sand bedding over the duct.  The balance of the trench above the electrical duct banks shall be backfilled and compacted in 200mm lifts with material meeting the requirements of Selected Material,  Type C, to 95 percent of the maximum density in accordance with Subsection 203-3.03, Construction of Embankments with Moisture and Density Control, up to the bottom of the roadway structural section.  The desired compaction shall be obtained with mechanical tamping machines.  No construction or other activity shall be permitted across any trench until a depth of 1 meter of fill above the duct banks has been placed and compacted in accordance with these Special Provisions.

    - CONDUITS.  Schedule 40 PVC and the Galvanized Rigid Steel conduit shall be provided by HEA.  Defective conduit shall not be installed and shall be removed immediately from the worksite.

The Contractor shall install the conduit in open trench as to the manufacturer’s recommendations and as depicted in the plans, with no more than 5 degrees deflection per 3.05 meters of run.

All conduit sweeps and conduit entrances into pads/pedestals shall be installed within the pad window area or pedestal to allow for future installation of conductors without removal or adjustment of the pad or pedestal.

All terminating of conduit ends shall be secured with temporary end caps, and buried terminations shall be marked with a UM-47 above them as shown on the plans, at the time the conduit termination is backfilled.

PVC Fittings - Conduits and fittings shall be jointed by means of a primer solvent and welding cement (Contractor furnished) to provide a watertight and root-proof joint.  All conduits shall be cut off square with a hacksaw.  The cut end shall be face flat and properly reamed with a reamer designed for the purpose of removing the sharp edge.

Plastic spacers (Contractor furnished) with a maximum horizontal spacing of 2.44 meters are to be used to maintain conduit placement and separation for concrete encased ducts.

Only tools and equipment designed for the particular use and operation shall be used.  Tools and equipment shall be kept in good condition.  Worn or broken tools shall be removed from the job immediately.

Bending - All bending of conduit will be by means of infrared heating and bending equipment, such as a Carlon "Hotbox Bender" or equivalent.  No cold bending of conduit will be accepted.  Any bent conduit that is deformed will be unacceptable and will be removed and replaced at the Contractor’s expense.  The cost of field bending the conduit shall be subsidiary to the appropriate Conduit Item.

All conduit shall be field bent to follow the trench line and grade with a minimum radius of 7.62-meters.  All bends will be per the manufacturer’s recommendations.  The minimum allowable bending radius for equipment entrances is 1200mm.  Preformed sweeps and preformed elbows with bending radii less than 1200mm will not be allowed.  The material for all 4 and 6 inch conduit preformed elbows of 90 degrees will be RSC conduit.  All bends will be approved by the Engineer.

Duct Finishing - After completion of backfilling and compaction, the electrical duct systems will be mandreled, brushed, and swabbed to confirm the integrity of the duct run.  All bell ends shall be beveled.  The steel mandrel and steel brush shall be 1-3/4 inches in diameter for the 2-inch conduit, 3-3/4 inches in diameter for the 4-inch conduit, and 5-3/4 inches in diameter for the 6-inch conduit.  If the duct will not accept the mandrel, the duct will be removed and replaced at no additional expense.  All mandreling must be done in the presence of the Engineer and HEA representative.  All conduit entrances and exits into the vaults shall then be sealed and plugged.  The cost of mandreling and installing the jet line shall be considered subsidiary to the appropriate conduit item.

A 5-mm diameter polyethylene or polypropylene pull rope, with a minimum breaking strength of 3114N, shall be left in each conduit.  A conduit plug shall be furnished by the Contractor and placed on each conduit end with the pull rope securely tied to internal portion of the plug.  The conduit plugs shall be water, airtight, removable, and reusable, Manufacture: JACKMOON USA, INC or equivalent.  All pull ropes shall be new and continuous with no spliced sections.

Each conduit run destination shall be identified by 18.75-mm letters on 75 x 125-mm metal or plastic tag secured to the conduit, identifying the terminus of the conduit run, for example: "To SC 000".

    - ELECTRICAL DUCT BANK INSTALLATION.  All electrical duct banks on this project will be comprised of multiple PVC or RSC conduits of the configuration shown on the plans.  The conduits for the primary distribution circuit will be concrete encased or direct bury as noted on the plans.

It shall be the Contractor’s responsibility, with the Engineer’s approval, to determine the most expedient method to complete the required electrical duct bank installation.  All work across the roadway shall be accomplished in accordance with Section 643, Traffic Maintenance.

Concrete Encased Duct Banks - Concrete forms, when required by the Contractor’s operation, shall be secured and braced to resist all deformation or displacement while under load, and shall be constructed to line, grade, and dimensions shown on the plans.  The forms shall be installed in such a manner as to be easily removed without hammering or prying against green concrete.  Reinforcing bars shall be provided at all locations detailed on the plans.

The Contractor shall tie down the conduit prior to placement of concrete to avoid conduit flotation.  All concrete shall be placed by means of a concrete vibrator and in such a manner as to prevent damage or displacement to forms, ducts, spacers, steel reinforcing, or other insert accessories.  If flotation or misalignment of the conduit(s) occurs the Contractor shall make all the necessary repairs at Contractor expense.

Concrete shall not be placed if there is standing water in the forms or if the subgrade is saturated.  Placing of concrete may be initiated when the temperature is not less than 4.44 C and rising, and the soil temperature is greater that 1.11 C.  The concrete shall have a minimum temperature of 10 C and the addition of anti-freeze salts or solutions will not be allowed.  At temperatures of 4.44 C and below, the Contractor shall keep the concrete covered and apply heat to maintain a minimum temperature of 5 C during the total curing period.

All concrete forms shall be left in place for a minimum of 24 hours until the concrete becomes firmly set.

    - SWITCHING CABINET PADS, PRIMARY J-BOX PADS, AND TRANSFORMER PADS.  The switch cabinet pads, primary J-box pads, and transformer pads shall be placed to the dimensions detailed in the plans.

Before installation the Contractor shall verify the orientation of the pads with the Engineer.  The Contractor shall install grounding rods in all equipment pads in accordance with the UM6-6L or UM6-6 specification shown on the drawings.  The Contractor shall install grounding bushings on all GRSC elbows, which terminate inside equipment pads, in accordance with the UM6-6L or UM6-6 specification.

The Contractor shall assume all responsibility of the cost of transportation, installation, repair, and maintenance of HEA pads until the pads are accepted by HEA.  During the placement of a pad, if the gravel foundation proves to be inadequate to support the pad to designed line or grade (elevation), the Contractor shall remove the pad and re-compact to meet the requirements shown on the plans and specifications.

The pads shall conform to the final grade after completion of the entire road project.

681-3.07  DISPOSAL OF WASTE EXCAVATION.  Waste excavation shall be disposed of by the Contractor outside the project limits at locations approved by the Engineer.  All waste excavation shall be considered subsidiary to the trench unit bid item.

680-3.08  BEDDING MATERIAL.  All conduits installed for HEA shall be bedded with sand or with ¾ inch minus rock material.  If native material meets the following requirements it may be used as bedding material, with prior approval by the Engineer.  Sand bedding shall meeting the following:

Sieve Size	Present Passing by Weight

6.25 mm or ¼ -inch	100 %

0.075 mm or No. 200	0-6%

681-3.09  CABLE PULLING.  HEA shall install and splice the electric power cable.

681-3.10  AS-BUILT DRAWINGS.  An as-built survey, by a land surveyor registered in the State of Alaska, will be completed by the Contractor.  All electrical duct banks and pads, including the locations, alignment and installed depth shall be included.  The information will be referenced to established survey monuments.

The HEA as-built prints shall include all references to the road centerline at 30.48-meter intervals, alignment changes, deviations and exact locations of all vaults and pads.  The Contractor’s as-built plans shall note all obstructions i.e. existing utilities, culverts, and line grade and elevation changes.  On the HEA as-built plans in the joint trench locations the Contractor shall note and reference the orientation of HEA facilities.  When the HEA conduit system is completed, the Contractor shall certify the accuracy of the construction survey notes and each revision on the plans by written signature endorsement, by a registered land surveyor and deliver them to the Engineer prior to final acceptance of the system by HEA.  In addition the Contractor shall provide two (2) CDs with the as-built information in Auto Cad R14 files in the layering pattern provided by the Department on the read only CD and deliver them to the Engineer.  Delivery shall be to the Engineer prior to acceptance of the electrical duct system by HEA.

680-3.11  INSPECTION.  The HEA Inspector may at any time have access to the project site for the purpose of inspection.  The Contractor agrees to notify the HEA inspector at least seven (7) calendar days prior to the start of this project.  The manner of installation of the conduit, materials, and equipment used therein, shall be subject to the inspection of HEA Inspector.  Prior to backfilling any of the trenches for the HEA, the HEA Inspector will measure the conduit installed.  HEA will conduct a final inspection within ten (10) calendar days of the Contractor’s informing the HEA Inspector, in writing, that the HEA conduit system is complete.  Incomplete items (punch list) as noted in the final inspection report, shall be completed by the Contractor within ten (10) calendar days of the final inspection.

    - METHOD OF MEASUREMENT.  Concrete encased conduit, RSC, and Schedule 40 PVC conduit will be measured by the meter along the horizontal length of the installed construction unit.  Trench and concrete encased duct bank will be measured by the meter, at the required width and depths as specified on the plans.

The ground rod, ground rod assembly, sweep conduit, electrical switching cabinet pads, transformer pads, transformer pad assemblies, primary J-box pads shall be measured by the unit, complete and accepted in the final position.

Bedding material shall not be measured for payment but will be subsidiary to the conduit items.

Separation geotextile shall not be measured for payment but will be subsidiary to the equipment pad assembly items.

    - BASIS OF PAYMENT.  Payment will be full compensation for all labor, equipment, and materials necessary to complete this work.

Payment for a concrete encased duct bank and electrical conduit system will be the length of the construction unit conduits installed times the unit bid price per meter for each construction unit.  The price paid for the electrical duct system shall include all necessary fittings.  Splice kits shall be subsidiary to the duct bank installation.

Junction and pull box installations will be paid per each, as an electrical transformer pad.

The unit bid prices will include all necessary excavation to plan grade, backfill of native materials outside the normal lines of the roadway structural section. Borrow materials to elevate equipment pads and to replace unsuitable material will be paid under Item 203(6A), Selected Material, Type A.

Payment will be made under:

| Pay Item No. | Pay Item | # Pay Unit |
| --- | --- | --- |
| 681 (1-2 PVC) | UM6P920, Conduit, 1-2” Schedule 40 PVC | Meter |
| 681 (1-4 PVC) | UM6P940, Conduit, 1-4” Schedule 40 PVC | Meter |
| 681 (1-6 PVC) | UM6P960, Conduit, 1-6” Schedule 40 PVC | Meter |
| 681 (1-2, 90 PVC) | UM6PE20, Sweep Conduit, 1-2”, 90 Schedule 40 PVC, 48” | Each |
| 681 (1-4, 90 PVC) | UM6PE40, Sweep Conduit, 1-4”, 90 Schedule 40 PVC, 48” | Each |
| 681 (1-2, 90S) | UM6SE20, Sweep Conduit, 1-2”, 90 Rigid Steel | Each |
| 681 (1-4, 90S) | UM6SE40, Sweep Conduit, 1-4”, 90 Rigid Steel | Each |
| 681 (1-6, 90S) | UM6SE60, Sweep Conduit, 1-6”, 90 Rigid Steel | Each |
| 681 (1-4, 45S) | UM6SF40, Sweep Conduit, 1-4”, 45 Rigid Steel | Each |
| 681 (1-6, 45S) | UM6SF60, Sweep Conduit, 1-6”, 45 Rigid Steel | Each |
| 681 (1-2S) | UM6S920, Conduit, 1-2” Rigid Steel | Meter |
| 681 (1-4S) | UM6S940, Conduit, 1-4” Rigid Steel | Meter |
| 681 (2-6S) | UM6S960, Conduit, 1-6” Rigid Steel | Meter |
| 681 (XUR4) | XUR4, Concrete Encased Duct Bank | Meter |
| 681 (UR4) | Trench Excavation and Backfill | Meter |
| 681 (UM1-4) | UM1-4, Transformer Pad Assembly, Poly | Each |
| 681 (UM1-4L) | UM1-4L, Transformer Pad Lid Assembly | Each |
| 681 (UM1-PC) | UM1-PC, Transformer Pad Assembly, Concrete | Each |
| 681 (UM1-PCL) | UM1-PCL, Transformer Pad Lid Assembly | Each |
| 681 (UM1-FG) | UM1-FG, Fiberglass Pad Assembly | Each |
| 681 (UM1-FGL) | UM1-FGL, Fiberglass Pad Lid Assembly | Each |
| 681 (UM3-14) | UG Enclosure Assembly, 1 Phase | Each |
| 681 (1UM33) | UG Enclosure Assembly, 3 Phase | Each |
| 681 (UM6-6) | Ground Rod | Each |
| 681 (UM6-6L) | Ground Rod Assembly | Each |
| 681 (UK5) | Secondary Pedestal | Each |
| 681 (UM-47) | Underground Locate Target | Each |
| 681(15) | Electric As-Builts | # Lump Sum |

# Add the following Section:

# SECTION 684

### CABLE TELEVISION RELOCATION

## Special Provisions

684-1.01  DESCRIPTION.  The Contractor shall provide all labor and equipment, and perform all operations necessary to complete the construction and installation of the owner-furnished conduits required for the completion of the project.  The cable television system will consist of multiple conduits of the size and number shown on the plans.  This work is to be performed in accordance with this contract, the National Electric Code and the National Electric Safety Code.

The Contractor shall provide as-builts in accordance with the conditions prescribed herein.

This work shall be inspected by GCI Cable, Inc. (GCI) with their instructions relayed by the Engineer to the Contractor.

684-1.02  LICENSING REQUIREMENTS.  The Contractor doing the actual work for ACS, HEA, and GCI shall be a licensed electrical contractor licensed by the State of Alaska and must have an employee on staff that possesses and Electrical Administrators License in the Outside Linework category.  The license must be assigned to the electrical contractor.  All employees of the Contractor installing rigid steel conduit or PVC conduit shall possess a certificate of fitness for electrical work as defined in 8 AAC 90.160, 8 AAC 90.165, and 8 AAC 90.170.  These requirements do not extend engineering or supervisory personnel of the Contractor.

684-2.01  MATERIALS.  The following materials will be furnished by GCI at no cost to the Contractor:

1.	All PVC conduits, fittings, and caps.

2.	All pull wires.

The Contractor shall be responsible for all handling, loading, and transportation to the jobsite.  The Contractor shall provide an advance 48-hour written notice to GCI stating the time the Contractor intends to pickup GCI furnished materials.

Within five (5) days of receipt of Notice-to-Proceed, the Contractor shall determine the material take-off requirements and shall prepare a complete itemized list of materials for submittal to GCI.  The materials will be staged for pickup at the agreed upon time, based on submittal of a material list four (4) calendar days prior.  Materials shall be picked up for the complete project and not on an as needed basis.  Materials will be loaded on the Contractor’s vehicle by others at no cost to the Contractor.  The Contractor shall sign for materials at the time of receipt.

All furnished materials may be obtained at the GCI Cable, Inc. warehouse, 5151 Fairbanks Street, Anchorage, Alaska between the hours of 8:00 AM and 4:00 PM, Monday through Friday.  When necessary to open the warehouse for the Contractor’s convenience and to procure special issuing of material other than during these normal working periods, the Contractor will be billed for the loaded labor rate time involved plus 25 percent handling overhead.  The Contractor shall be responsible for pickup, storage and safekeeping of all materials after receipt.  All materials will be inspected by representative from both parties and an acceptance document stating materials are free from defects will be signed.  All unused materials shall be returned to the warehouse upon completion of the project.

684-2.02  VERIFICATION OF DIMENSIONS.  The exactness of dimensions given on any GCI drawing is not guaranteed, and therefore the Contractor shall field verify the accuracy of all dimensions.  In all cases of interrelation with other work, he shall verify in the field all the dimensions relating to the contiguous work.  Any errors due to the Contractor’s failure to verify shall be rectified promptly at the Contractor’s cost.

684-3.01  GENERAL CONSTRUCTION REQUIREMENTS.  The GCI Inspector reserves the right to suspend the conduit system installation, through the Engineer, at any time the Contractor fails to meet the requirements set forth herein, until such time as the Contractor makes the necessary corrections.  Suspension of work will not entitle the Contractor to an extension of time for the completion of the project and will not entitle extra payment for costs incurred.

All cable television conduit systems shall be located as shown on the plans.  Alignment shall be such that there are no protrusions which will harm the cable being pulled through the conduit.

If construction or excavation require the removal of any existing privately owned facilities on the provided television easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at unit bid prices.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two (2) weeks.

All backfill for the television system shall be approved native material compacted in 200 mm lifts to 95 percent of the maximum density in accordance with subsection 203-3.03, Construction of Embankment with Moisture and Density Controls, up to the bottom of the roadway structural section.  If outside the structural section, native backfill material shall be placed in layers and compacted as approved by the Engineer.

All television conduit shall be laid to a minimum depth of 1.2 meters below the finished roadway grade.

The clearance between various duct or conduit systems shall be as large as possible to permit maintenance of the system without damage to other parallel systems.  Separation between conductors of 300 volts or more and the television conduit shall be either:

1.	300 mm of well compacted native materials,

2.	100 mm of masonry, or

3.	75 mm of concrete.

The ends of all conduits, whether shop or field cut, shall be reamed to remove burrs and rough edges.  Cuts shall be made square and true so that the ends will butt together for the full circumference.  When a standard coupling cannot be used for coupling metal type conduit, an approved threaded union coupling shall be used.  All couplings for the metal conduit shall be tightened until the ends of the conduit are brought together, providing a good electrical connection throughout the entire length of the conduit run.

All metal conduit ends shall be threaded and capped with standard plastic pipe caps or approved threaded electrical plug and coupling combinations until wiring is started.  When caps are removed, the threaded ends shall be provided with approved conduit bushings.  All conduit runs shall be capped where open to ground until wiring is started.  Conduit shall be restrained to resist movement during backfilling and cable pulling.

All dirt, gravel, ice, and other debris shall be cleaned from all conduits prior to acceptance.  Pull wires shall then be placed in all conduits with ends 0.6 meters in length wrapped and tied around tops of conduit.

Should moisture, galvanic action, or corrosion be observed which is attributed to Contractors workmanship (i.e., waterproofing, nongalvanic and corrosion preventative methods or materials used) the Contractor shall immediately take corrective action to resolve and correct the problems at own expense.

684-3.02  TRENCH AND PAD EXCAVATION AND BACKFILL.  Excavation work shall be accomplished in accordance with these Special Provisions and Section 204, Structure Excavation for Conduits and Minor Structures.

When the cable television and electrical power utilities are jointly installed in the same trench, the trench excavation and backfill shall meet the requirements of subsection 681-3.02, Trench and Pad Excavation and Backfill.  The work will be paid under Item 681(UR4).

When only the cable television and telephone utilities are jointly installed in the same trench, the trench excavation and backfill shall meet the requirements of subsection 680-3.02, Trench and Pad Excavation and Backfill.  The work will be paid under Item 680(10).

When the telephone utility is installed by itself, the trench excavation and backfill work will be paid under item 680(10).

All existing underground utilities shall be identified, located, and proper care taken not to damage them.  It shall be the Contractor’s responsibility to establish the location of each facility by calling for a field locate in accordance with Subsection 105-1.06, Cooperation with Utilities.

Trench depth shall be as shown on the plans, and as staked in the field.  Trenches shall be of the necessary width that will allow compaction equipment to be utilized, and for proper laying of conduit and installation of pads.  The trench unit shall include all labor and equipment necessary to construct the facility in accordance with the plans and specifications.  Extra compensation shall not be granted for hand digging and/or utilization of an “air knife”.  The banks of the excavation shall be sloped so as to conform to the prevailing safety requirements.

All trench transition areas shall be gradual in terms of depth.  Offset conduit bends shall not be permitted.  At all transition locations, the “shallow” trench transition to meet the “deep” trench at a slope not to exceed 10:1.  Work associated with the trench transitions shall be incidental to the construction of the trench unit and not be considered a separate pay item.

Construction shall be arranged so the trenches will be left open for the shortest practical time to avoid creating a hazard, and to minimize the likelihood of trench collapse due to other construction activity, rain, and accumulation of water in the trench, etc.  All temporary bridging utilized by the Contractor shall be approved by the Engineer prior to installation.  This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength. Any bridging open to public traffic will provide a smooth driving joint.

The Contractor shall not begin excavation of the trench until all personnel, materials, and equipment are present to complete the work in the most expedient manner.  The Contractor shall backfill all vault and trench excavations within 48-hours.  There shall be no more than 30 meters of open trench at the end of the work-day, unless approved by the Engineer.

The routing of the ducts shall be as shown on the plans unless the conditions encountered are such that changes are necessary to accomplish the work.  In the event that rock or other obstructions are encountered during the trenching operation so the ducts and pads cannot be installed, the Contractor shall inform the Engineer of the nature and extent of the difficulty encountered for his review and verifications.  The Engineer, with the approval of ACS, will determine whether the duct is to be rerouted, trenched through the obstructed area or advise on another suitable change.

All excavation shall be inspected and approved by the Engineer before the duct installation is started.

The bottom of the trench must be transversely level to provide a uniform support for ducts.  All rocks or other materials, which could damage the duct, shall be removed from the trench bottom before placing the duct.  Care shall be exercised to minimize the likelihood of water flow since this may cause trench damage and reduction in trench depth.  When this occurs, the trench must be cleared to the required depth before installing the ducts.

Native materials may be utilized for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07,Selected Material, shall also pass a 75-mm.  Native backfill material shall be placed in layers and compacted as directed by the Engineer.

Disposal of waste excavation shall meet the requirements of the subsection 684-3.03, Disposal of Waste Excavation.

Sand bedding shall meet the requirements of subsection 684-3.04, Sand Bedding.

It shall be the Contractor’s responsibility, with the Engineer’s approval, to determine the most expedient method to complete the required trench work.  All work across the roadway shall be accomplished in accordance with Section 643, Traffic Maintenance.

684-3.03  DISPOSAL OF WASTE EXCAVATION.  Waste excavation may be disposed of within the project limits at locations approved by the Engineer.  Waste disposal areas shall be feathered into surrounding grounds with no noticeable break or variation readily discernible and existing drainage patterns shall be maintained.

684-3.04  SAND BEDDING.  Where existing material is unsuitable for the conduit bedding, as determined by the GCI Inspector, the Contractor shall provide bedding sand meeting the following:

Sieve Size	Present Passing by Weight

6.25mm or ¼ -inch		100 %

0.075mm or No. 200	0-6%

684-3.05  CABLE PULLING.  GCI shall install and splice the television cable and install the pedestals.

684-3.06  SURVEYING AND STAKING.  Conduit alignment and any changes to the alignment shall, as per the plans, be subject to the approval of the Engineer and the GCI Inspector.  All cable television conduit shall be located and staked at the alignment and elevations indicated on the plans.  It shall be the Contractor’s responsibility to schedule a physical check of all line and grades prior to placing the conduit.

684-3.07  AS-BUILT DRAWINGS.  A complete and accurately dimensioned record of all deviations, deletions, additions, and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed.  Two (2) of each final as-built drawings shall be delivered to the Engineer prior to final acceptance of the system by GCI.  The Contractor shall provide as-built location of underground construction on plat maps supplied by GCI.  The Contractor shall maintain accurate records of underground routing of the television system.  This shall be achieved by drawing the conduit offset from the roadway centerline to where the conduit has been buried.

The as-built drawings shall include all references to the road centerline, existing land marks, and exact locations of all pedestals.  As-builts shall note all obstructions i.e. existing utilities, culverts and line grade and elevation changes.  Reference to GCI orientation in joint trench shall also be noted.  When the GCI conduit system is completed, the Contractor shall certify the accuracy of the construction survey notes and each revision on the plans by written signature endorsement, by a land surveyor registered in the State of Alaska.  The Contractor shall deliver them to the Engineer prior to final acceptance of the system by GCI.  In addition the Contractor shall provide two (2) CDs to GCI with each utilities as-built Auto Cad R14 files in the layering pattern, provided by GCI, on the read only CD and deliver them to the Engineer.

684-3.08  INSPECTION.  The GCI Inspector may at any time have access to the project site for the purpose of inspection.  The Contractor agrees to notify the GCI inspector at least seven (7) calendar days prior to the start of this project.  The manner of installation of the conduit, materials, and equipment used therein, shall be subject to the inspection of GCI Inspector.  Prior to backfilling any of the trenches for HEA, the GCI Inspector will measure the conduit installed.  GCI will conduct a final inspection within ten (10) calendar days of the Contractor’s informing the GCI Inspector, in writing, that the GCI conduit system is complete.  Incomplete items (punch list) as noted in the final inspection report, shall be completed by the Contractor within ten (10) calendar days of the final inspection.

684-4.01  METHOD OF MEASUREMENT.  Measurement for payment for the cable television system will be the number of meters of individual PVC conduit of the size indicated, installed, and accepted.

Item 684(1A), 2-Inch PVC Television Conduit.  The 2-inch PVC conduit placed in sand bedding will be measured by the meter as per the plan detail, installed, and accepted in final position.  Measurements between vaults will be wall to wall measurements.

Item 684(1B), 4-Inch PVC Television Conduit.  The 4-inch PVC conduit placed in sand bedding will be measured by the meter as per the plan detail, installed, and accepted in final position.  Measurements between vaults will be wall to wall measurements.

Item 684(2), Cable Television As-Builts.  As-builts will not be measured for payment but will be compensated as a Lump Sum item.

Item 684(3), Trench Excavation and Backfill.  GCI only trench will be measured by the meter along the trench at the required width and depths as specified on the plans.  Joint trench with HEA will be paid under 681(UR4).  Joint trench with ACS will be paid under 680(10).

684-5.01  BASIS OF PAYMENT.  All surveying and staking required for the 684 items for this project will be measured and paid for under Item 642(2), Construction Surveying.

Payment for Item 684(1A), 2-Inch PVC Television Conduit.  The 2-inch PVC conduit to be placed into a common trench as indicated on the plans, at the quantity indicated on the plans.  The installation of the grounding wire, warning tape, sweeps, couplings, solvent, BSW, marker tape, conduit spacers, and conduit mandrelling are all considered subsidiary to this item.

Payment for Item 684(1B), 4-Inch PVC Television Conduit.  The 4-inch PVC conduit to be placed into a common trench as indicated on the plans, at the quantity indicated on the plans.  The installation of the grounding wire, warning tape, sweeps, couplings, solvent, BSW, marker tape, conduit spacers, and conduit mandrelling are all considered subsidiary to this item.

Payment for item 684(2), Cable Television As-Builts.  As-builts will be full compensation for providing two (2) sets of red-lined Auto Cad R14 drawings as set forth in subsection 684-3.07.  The Contractor shall be required to have a land surveyor registered in the State of Alaska stamp the as-built drawings.

Payment for Item 684(3), Trench Excavation and Backfill.  The payment for the trench shall be paid by the meter.  The payment shall be full compensation for labor and equipment for trenching and backfilling for placement of conduits, as detailed on the plans.  The disposal of waste excavation shall be subsidiary to the trench.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 684(1A) | 2-Inch PVC Television Conduit | Meter |
| 684(1B) | 4-Inch PVC Television Conduit | Meter |
| 684(2) | Cable Television As-Builts | Lump Sum |
| 684(3) | Trench Excavation and Backfill | Meter |

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following sentence:  Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

Performance Graded Asphalt Cement

PG 52-28	PG 58-28	PG 64-28

Softening Point	(none)	49C	52C

AASHTO T-53

Toughness min.	(none)	12.4 N-m	12.4 N-m

ASTM D5801

Tenacity min.		(none)	8.5 N-m	8.5 N-m

ASTM D5801

(9/18/00) R244M98

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Coarse Aggregate, in the table, change Percent of Wear to 50 max., and Degradation Value to 45 min.

Under Percent Fracture, delete 80 min. (single face), and replace with 90 min. (two face).

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total." (06/25/99)M 82

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material. (06/25/99)M 82

Special Provisions

703-2.07 SELECTED MATERIAL.  Add the following:  The source of selected material shall be tested before use, and the percent passing the 0.02 mm sieve shall not exceed 3 percent, as determined on the minus 75 mm material.

Add the following to Item 1, Select Material, Type A:  All Select Material, Type A placed in the top 300mm of the embankment shall have a maximum size of 75mm.

Under Item 2. Selected Material, Type B, change “10%” to “13%”.

SECTION 706

CONCRETE & PLASTIC PIPE

Standard Modifications

706-2.06 PLASTIC PIPE FOR SANITARY SEWERS. Replace “Type S” with “Type S or Type D”. (02/08/01)M 97

### Special Provisions

706-2.06 PLASTIC PIPE FOR SANITARY SEWERS Delete the reference to Polyethylene Pipe and substitute the following:

HIGH DENSITY POLYETHYLENE (HDPE)

The pipe and fitting material shall have a cell classification of 345434C or better in accordance with ASTM D3350.  In addition, the material must exceed 1000 hours when tested in accordance with the ASTM F1248, the Ring Environmental Stress Crack Resistance Test with fewer than 50 percent (50%) failures.  The material shall be listed by the NSF (National Sanitation Foundation) for potable water service and be indicated as such on the pipe.

Standard Modifications

706-2.07 CORRUGATED POLYETHYLENE PIPE.  For culverts replace “Type S” with “Type S or Type D”. (02/08/01)M 97

For underdrains, replace AASHTO M252 with AASHTO M294, Type SP.

SECTION 707

METAL PIPE

### Special Provisions

707 2.06 SERVICE PIPE.

Delete this Section in its entirety and substitute the following:

1.	Copper Pipe.  Pipe used under this specification shall be soft-drawn, seamless, annealed copper pipe suitable for use as underground service water connections for general plumbing purposes and shall comply with the requirements of ASTM B 88 for Type K soft copper as manufactured by the American Brass Company, or equal.

2.	High Density Polyethylene Pipe.  The pipe and fitting material shall have a cell classification of 345434C or better in accordance with ASTM D3350.  In addition, the material must exceed 1000 hours when tested in accordance with the ASTM F1248, the Ring Environmental Stress Crack Resistance Test with fewer than 50 percent (50%) failures.  The extruded pipe shall have impact strengths greater than three feet pounds per inch (3 ft.# / inch), in accordance with the ASTM D256 Izod Impact Test.  The material shall be listed by the NSF (National Sanitation Foundation) for potable water service and be indicated as such on the pipe.

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.06 FRAMES, GRATES, COVERS AND LADDER RUNGS. Add the following:

Ductile iron castings			ASTM A536 for grade 60-401.

(2/22/00)R78M98

    - CORPORATION STOPS AND CURB STOPS.

Delete Sections 2.09 thru 2.12 in their entirety and substitute the following:

# 712-2.09  CORPORATION STOP, CURB STOP AND CURB BOX. Only Mueller brands will be accepted.

1.	Corporation stops shall be flare type, brass only.

2.	Curb stops shall be flare type, brass only.

3.	Curb boxes must be furnished with stationary operating rods.  The curb box shall provide a clear and unobstructed access to a valve or curb stop to enable the City of Homer operation of the valve or curb stop. The curb box shall be placed 600 mm within the State ROW unless otherwise directed by the Engineer.

712-2.10  GATE VALVES.

Gate Valves.  Gate valves shall be iron body, fully bronze mounted, double disc, parallel seat valves as manufactured in accordance with the requirements of AWWA C-500, Gate Valves for Ordinary Water Works Service.  All valves shall be non-rising stem type with an O-ring seal and a 2” square operating nut, and shall open counter clockwise.  Valves shall have mechanical joint ends.

    - VALVE BOXES.

Valve Boxes.  Valve boxes shall be cast iron of sliding, adjustable height type with round or oval bottom hood sections to fit over the top of the valve.  The top section shall be recessed to receive a close fitting “eared” lid with the word “WATER” cast into it.  Internal diameter of the smallest section shall be not less than 5”.  Minimum thickness of the metal shall not be less than 5/16”.  Castings shall be smooth and workmanship shall be first class.  Valve boxes shall be provided with dust covers.

Valve boxes shall be of sufficient length for the pipe cover depth on the profile drawings and in accordance with the standard details, of these specifications.

Valve boxes shall be supplied with valve operator extension rods such that the maximum depth from the ground surface to the operator nut does not exceed 3’.

Markers.  Valve boxes shall be marked with markers consisting of 2-1/2” O. D. galvanized steel pipe sections, 7’ in length, with 3’ buried in the ground.  Markers shall be shop painted “Caterpillar Yellow” and painted with stenciled 2” black numerals, showing the appropriate references.  Markers shall be located on the nearest property line, due north, south, east or west of the valve at a maximum distance of 15m unless otherwise directed by the Engineer.  Markers shall carry the notation:

VB	(feet)		(direction)

When valve boxes are located in a paved area, the valve marker posts are not required.  The Contractor’s surveyor shall provide a minimum of two swing ties from prominent nearby physical features to each valve box located in paved areas.

712-2.12  HYDRANTS.

Fire Hydrants.  Fire hydrants shall conform to the requirements of AWWA C-502 for Dry Barrel Fire Hydrants.  Fire hydrants shall be American Darling B-62-B; to include, without limitation, the following:

1.  	All fire hydrants shall be supplied with a 133mm (5-1/4”) main valve opening.

2.  	All hydrants shall be single pump hydrants furnished with a 152mm (6”) ASA Class 125 standard mechanical joint end with two (2) cast-on lugs for tie backs.

3.  	All connections shall be mechanical joint unless otherwise indicated in the contract documents.

4.  	Single pumper hydrants shall be furnished with 64mm (2-1/2”) hose connections and one (1) 114mm (4-1/2”) pumper connection.

5.  	Unless otherwise required by the contract documents, all hydrants shall be furnished with a barrel length that will allow 2.1m (7’) bury.

6.   	The main valves shall be of the compression type, where water pressure holds the main valve closed permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

7.  	All fire hydrants shall be furnished with a breakaway flange of the type that allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

8.  	Painting and coating shall be in accordance with cited AWWA Specifications.  After installation, the hydrant section from the traffic flange to the top of the operating nut shall be painted “Caterpillar Yellow.”

9. 	Operating and nozzle nuts shall be pentagon shaped with 38mm (1-1/2”) point to flat measurement.

10. 	Hose nozzle threading shall be in conformance with NFPA #194 for National (American) Standard Fire Hose Coupling Screw Threads.

11. 	All working parts shall be bronze or noncorrosive metal in accordance with the requirements of AWWA C-502.

12.  	All hydrants shall be left hand opening (counter clockwise).

13. 	All hydrants shall have drain outlets at the base of the barrel.  Brass manufacturer plugs must be installed prior to installation.

Tie Rods.  All tie rods must be 19mm (3/4”) O. D. black iron or mild steel.  Tie Rods may be substituted with Megalug series 1100 mechanical joint restraints.

Guard Posts.  The Contractor shall install guard posts at each hydrant installation in accordance with the City of Homer standard details.  If, in the opinion of the Engineer, the guard posts are not to be installed, they shall be delivered to the City of Homer Public Works Shop.  Measurement and payment for guard posts shall be incidental to the Bid Item, Furnish and Install Fire Hydrant Assembly.

Restrained Joints.  Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for fittings, piping, or deflection points.

Restrained joint pipe shall utilize EBAA Iron MEGALUG, Romac Industries GripRing, U.S. Pipe Field LOK Gasket System, or approved equal. Restrained joint installation areas shall include where the water conduit changes alignment utilizing a tee, cross, bend, or similar fitting.

The Contractor shall provide manufacturer submittals for each type of thrust restraint to be used. Such submittals shall include thrust restraint calculations and other appropriate data.

If the restrained joint or joint restraining system submitted for use is other than EBAA Iron MEGALUG, Romac Industries GripRing, or U.S. Pipe Field LOK Gasket System, and the general method and approach to restraint is accepted by the Engineer, the Contractor shall field demonstrate to the Engineer the installation and/or construction of each new restrained joint or restraining system. The Contractor shall provide the Water Utility a minimum of 48 hours notice, excluding non-working days, to coordinate review of the field demonstration. The Contractor shall first certify that the restrained joint system is installed in accordance with the manufacturer’s instructions, then subject the test assembly to a minimum test pressure of 1.1 MPa (160 psi) for a period of 30 minutes.

To pass the pressure test, there shall be no noticeable movement of the restrained joints and no loss of pressure during the test period. All costs associated with the submittal and field demonstration shall be assumed by the Contractor.

Flanged Adapter Couplings.  Flanged adapter couplings shall be ROMAC FCA501 ductile iron fittings.

Flanged fittings.  Flanged fittings shall be Class 150 Ductile Iron, with minimum design pressure rating of1.034 MPa(150 psi.).

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following Subsection:

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

SECTION 724

SEED

Standard Modifications

724-2.02 MATERIALS Delete this Subsection in its entirety and substitute the following: Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

(2/8/01) M100

Special Provisions

724-2-02. MATERIALS. Delete this Subsection in its entirety and substitute the following:

Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(03/05/02)R52M98

SECTION 726

TOPSOIL

# Special Provisions

726-2.01 TOPSOIL. Replace Item No. 2 with the following:

2.	Contain between 10% and 40% organic maters determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267

3.	Replace the grading requirements table with the following

## TABLE 726-1

## TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 75 mm | - | 100 |
| 12.5 mm | 100 | - |
| 4.75 mm | 95-100 | 75-100 |
| 1.18 mm | 64-90 | 50-95 |
| .075 mm | 30-60 | 20-80 |
| Organic Content | DELETED | DELETED |
| DELETED | DELETED | - |

Delete the third paragraph in its entirety.

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber Recycled Paper (“wood cellulose”) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch. Blended mulch may contain up to 50%-recycled paper.  The mulch shall meet the following requirements:

a.	Contains no growth or germination inhibiting factors.

b.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry.

c.	Mulch can be applied uniformly on the soil surface.

d.	Will not create a hard crust upon drying and have moisture absorption and retention properties and the ability to hold grass seed in contact with the soil.

e.	Dyed a suitable color to facilitate inspection of its placement.

Ship the mulch material in packages of uniform weight (plus or minus 5%) and bear the name of the manufacturer and the air-dry weight content.

Use a commercial tackifier on all areas steeper than 3:1.  Use the amount recommended by the manufacturer.

(8/19/99)R206M98

SECTION 729

GEOTEXTILES

Standard Modifications

729-2.01 Embankment Separation and Reinforcement.  Under 1. Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2.  Reinforcement, replace ‘Separation (high survivability)’ with:  ‘Stabilization’.

729-2.02 Subsurface Drainage and Erosion Control.  Under 2. Erosion control, replace “0.1 sec-1” with “0.5 sec -1”.

729-2.04 Sediment Control.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with:  ‘Meet AASHTO M 288 for Temporary Silt Fence’.

(2/8/01) M98

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Standard Modification

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

Special Provisions

Add the following:

6.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

MATERIALS CERTIFICATION LIST

APPENDIX B

PERMITS

#### APPENDIX C

EROSION AND SEDIMENT CONTROL PLAN

#### APPENDIX D

UTILITY STAKING SHEETS