SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	Cross Sections

c.	Geotechnical Report, “Glenn Highway MP 55-61, Moose Creek to Sutton”, dated February 1999.

d.	Foundation Report, "Glenn Highway: MP 55-61, Moose Creek to Sutton, Eska Creek Bridge No. 542" dated September 1997.

e.	State of Alaska Department of Transportation and Public Facilities publication, Best Management Practices For Construction Erosion and Sediment Control and Maintenance and Operations Activities

f.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

g.	Interim Standard Specifications for Highway Construction (Metric) 94M. ($25.00)

h.	Advance utility relocation, Storm Water Pollution Prevention Plan (SWPPP).

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

3.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

4.	This is to notify all bidders that effective January 1, 1998, contract items under Section 643, Traffic Maintenance, will no longer be creditable under the Disadvantaged Business Enterprise Program for DBE credit as subcontractable items. The only current exception is item 643(3), Permanent Construction Signs.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

5.	The Department’s procedure for providing for the costs of on-site flagging has changed. In recognition of the benefits derived from a well coordinated flagging operation to both the traveling public and the Contractor’s operation, the Department’s position is that the Contractor is a full partner in this contract and should participate in the cost of flagging. Therefore, the amount paid by the Department to provide flagging has been changed from $45.00 / hour to a shared $32.00 / hour. The additional actual cost to provide a flagger shall be considered as incidental to other items of work. This change shall in no way relieve the Contractor from his responsibility to provide for safety and convenience of the public.

6.	This is to notify all bidders that the contract award process, when a DBE Goal is specified, will be modified as explained below.

Prior to award, the Department has been allowing a low bidder who did not submit sufficient good faith efforts (GFE) documentation to then submit additional DBE participation to meet the goal stated in the bid documents. The FHWA has informed us that this practice is not allowable. If GFE documentation is submitted and found to be insufficient, the bidder is to be declared nonresponsive.

For contract DBE requirements, refer to Section 120, DBE Program.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

7.	See Special Provision 703-2.07 for changes to borrow material requirements.

8.	There are restrictions to the Contractor’s operations in the project area. See subsections 107-1.21, 108-1.04, 401-3.01, 628-3.02, and 643-3.08 of these Special Provisions.

9.	The United States Department of Transportation has recently issued new regulations for the DBE Program (49 CFR Part 26).  New eligibility criteria for DBE firms have been added, including consideration of Personal Net Worth (PNW) of the DBE owner(s).  This new criteria will be used to verify continued certification in the DBE Program.  Contractors are requested to continue to use the same procedure they have been using until the Department can establish the PNW.  If a DBE firm on a Project awarded after March 3, 1999 is decertified for failure to meet the PNW criteria, the Department will deal with the issue on a case by case basis.

PART 4

SPECIAL PROVISIONS

to the

ALASKA DEPARTMENT OF TRANSPORTATION

and PUBLIC FACILITIES

INTERIM

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

94M

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.26 HIGHWAY, STREET OR ROAD. Delete this subsection in its entirety and substitute the following: A general term denoting a public way used by vehicles and pedestrians, including the entire area within the right-of-way.

101-1.30 MAJOR CONTRACT ITEM. Replace “10%” with “5%”.

101-1.33 MINOR CONTRACT ITEM. Replace “10%” with “5%”.

Add the following subsection:

101-1.62a SUBSIDIARY. Not paid for directly. Compensation for such work is included in the payment for other items of work and no separate payment will be made.

(2/18/99)R230

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Special Provisions

102-1.06 PREPARATION OF PROPOSAL. Replace the first sentence with the following: The bidder shall submit his proposal on the forms furnished by the Department, or legible copies thereof.

102-1.07 NON-RESPONSIVE PROPOSALS. Replace item 1. with the following:

1.	If the proposal is on a form other than that furnished by the Department, or legible copies thereof; or if the form is altered or any part thereof is detached; or if the proposal is improperly signed.

102-1.09 DELIVERY OF PROPOSALS. Delete the third paragraph.

(2/18/99)R231

102-1.12 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (10/3/94)R171

102-1.16 NON-COLLUSION AFFIDAVIT. Delete this subsection. (2/18/99)R231

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01 CONSIDERATION OF PROPOSALS. In the second and third paragraphs, replace form 25D-5 with the following: "form 25D-5(C)".

(5/5/95)R82M

103-1.04 PERFORMANCE AND PAYMENT BONDS. In the third paragraph, under item 1.delete the first sentence and substitute the following: Escrow account, with a Federally-insured financial institution, in the name of the Department.

103-1.05 INSURANCE REQUIREMENTS. Delete this subsection in its entirety and substitute the following: The Contractor shall provide evidence of insurance with a carrier or carriers satisfactory to the Department covering injury to persons and/or property suffered by the State of Alaska or a third party, as a result of operations under this contract by the Contractor or by any subcontractor. This coverage will also provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this contract. The delivery to the Department of a written 30 day notice is required before cancellation of any coverage or reduction in any limits of liability. Insurance carriers providing coverage shall have an acceptable financial rating.

The Contractor shall maintain in force at all times, during the performance of work under this contract, the following policies of insurance. All insurance policies shall comply with, and be issued by insurers licensed to transact the business of insurance under AS 21. Failure to maintain the specified insurance may, at the option of the Contracting Officer, be deemed as unacceptable work and remedied under Subsection 105-1.11. Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor's indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

1.	Workers' Compensation Insurance: The Contractor shall provide and maintain, for all employees of the Contractor engaged in work under this contract, Workers' Compensation Insurance as required by AS 23.30.045. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who provides services under this contract, to include:

a.	Waiver of subrogation against the State and Employer's Liability Protection in the amount of $500,000 each accident/$500,000 each disease.

b.	If the Contractor directly utilizes labor outside of the State of Alaska in the prosecution of the work, “Other States” endorsement shall be required as a condition of the contract.

c.	Whenever the work involves activity on or about navigable waters, the Workers' Compensation policy shall contain a United States Longshoreman’s and Harbor Worker’s Act endorsement, and when appropriate, a Maritime Employer’s Liability (Jones Act) endorsement with a minimum limit of $1,000,000.

Commercial General Liability Insurance: on an occurrence policy form covering all operations by or on behalf of the Contractor with combined single limits not less than:

$1,000,000 each occurrence

$1,000,000 for Personal Injury Liability

$2,000,000 aggregate for Products-Completed Operations

$2,000,000 general aggregate

The State of Alaska shall be named as additional insured. This insurance shall be considered to be primary and non-contributory to any other insurance carried by the State through self insurance or otherwise.

Automobile Liability Insurance: covering all vehicles used by the Contractor in the performance of services under this agreement with combined single limits not less than $1,000,000 each occurrence.

In addition to providing the above coverages the Contractor shall, in any contract or agreement with subcontractors performing work, require that all indemnities and waivers of subrogation it obtains, and that any stipulation to be named as an additional insured it obtains, also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as additional named indemnitee and as additional insured.

Evidence of insurance shall be furnished to the Department prior to the award of the contract. Such evidence, executed by the carrier's representative and issued to the Department, shall consist of a certificate of insurance or the policy declaration page with required endorsements attached thereto which denote the type, amount, class of operations covered, effective (and retroactive) dates, and dates of expiration. Acceptance by the Department of deficient evidence does not constitute a waiver of contract requirements.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number).”

(2/18/99)R232

SECTION 104

SCOPE OF WORK

Special Provisions

104-1.02 CHANGES. Delete the fourth paragraph and substitute the following:

Before a Change Order or Supplemental Agreement covering work for which there is no established contract price is approved, the Contractor shall submit detailed cost or pricing data regarding the changed or extra work. The cost or pricing data shall include an itemization of all costs including labor, materials, and equipment required for the work. The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work. (2/18/99)R233M

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.01 AUTHORITY OF THE ENGINEER. Add the following paragraph:

When, in the opinion of the Engineer, conditions are such that the safety and/or convenience of the traveling public are adversely affected, the Contractor will be immediately notified in writing. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). In no case shall this time exceed 24 hours. In the event that the Contractor fails to take the corrective action within the specified time, the Engineer may direct that the offending operations cease until the defect(s) is (are) corrected. The Engineer reserves the right to have corrective action taken by outside forces. The cost of work by outside forces shall be deducted from any monies due or that may become due under the terms of this Contract.

105-1.02 PLANS AND WORKING DRAWINGS. Delete the last two sentences of the second paragraph and substitute the following: All working and detail drawings shall be full size, on white paper, and have dark blue or black lines.

In the next to last paragraph, delete “of the drawings for use by the Engineer” and substitute the following: “or an Autocad drawing interchange file format (.DFX) on 3.5-inch disk.”

105-1.05 COOPERATION BY CONTRACTOR. In the last paragraph, insert the following before the last sentence: The superintendent shall have the authority to sign Directives for the Contractor.

(2/18/99)R234

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. Contractor shall use the locate call center for the following utilities:

Locate Call Center Statewide 800-478-3121 who will notify the following:

AT&T Alascom, Inc ENSTAR Natural Gas, Inc. Matanuska Electric Association Matanuska Telephone Association PTI Communications, Inc.

The Contractor shall call the following utilities and agencies directly:

Alaska Railroad Corporation	265-2520

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits. The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen. Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

Right of Way and/or Construction surveying is required of the Contractor prior to utility relocation. Payment to the Contractor will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract, and/or;

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor”s two (2) week work plan, or not required by the contract.

The Utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice of the staking required.

It is the Contractor”s responsibility to schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

The Contractor shall give each utility fifteen (15) calendar days advance written notice that relocation is required. The utility will only be required to work in one location at a time.

Specific coordination requirements for the specific utilities are included below:

MATANUSKA ELECTRIC ASSOCIATION, INC. (MEA)

1.	MEA will relocate existing pole J103 at Station 1+916, 10 left, to allow for slope construction.

The Contractor shall allow MEA four (4) calendar days to complete the relocation after completing the required clearing.

2.	MEA will relocate the existing electrical pole line along the north side of the Glenn Highway between Stations 6+200, 41 left, and 7+017, 32 left, to allow for construction of the special ditch and benched slope.

The Contractor shall allow MEA twenty (20) calendar days to complete the relocation after completing the required clearing.

3.	MEA will raise the existing aerial crossing at Station 7+663 to maintain the required clearance over the highway.

The Contractor shall allow MEA three (3) calendar days to complete the relocation.

4.	MEA will relocate existing pole J182-1A, Station 10+148, 28 right, to allow for approach construction.

The Contractor shall allow MEA one (1) calendar days to complete the relocation.

MATANUSKA TELEPHONE ASSOCIATION, INC. (MTA)

1.	MTA will relocate the existing underground crossing at Station 1+883.

The Contractor shall allow MTA seven (7) calendar days to complete the relocation after the Contractor has completed the required clearing and grubbing.

2.	MTA will lower the existing underground BFC100x24 cable to allow for ditch construction between Stations 2+010 and 2+110, right.

The Contractor shall allow MTA three (3) calendar days to complete the relocation.

3.	MTA will relocate the existing underground BFC100x24 cable between Station 2+280, 40 right, and Station 3+750, 58 right.

The Contractor shall allow MTA fourteen (14) calendar days to complete the relocation after the Contractor has completed the required, clearing, grubbing, and benching at Approach B.

4.	MTA will relocate the underground BFC100x24 cable between Station 4+470, 19 right, and Station 5+432, 22 right. MTA will install a new underground road crossing at Station 5+429.

The Contractor shall allow MTA fourteen (14) calendar days to complete the relocation after the Contractor has completed the required clearing and grubbing.

5.	MTA will relocate the existing underground BFC100x24 and BJ25x19 cables along the north side of the Glenn Highway between Stations 6+210 and 6+825 in conflict with construction of special ditch and benched slope.

The Contractor shall allow MTA eight (8) calendar days to complete the relocation after the Contractor has completed the required clearing and grubbing.

6.	MTA will raise the existing aerial C25x24 crossing at Station 7+663.

The Contractor shall allow MTA one (1) calendar days to complete the adjustment after MEA replaces the pole.

7.	MTA will extend the existing conduit outside the proposed slope limits, both left and right, at Station 8+071.

The Contractor shall allow MTA one (1) calendar day to complete the extensions.

8.	MTA will lower the existing underground cables and install new 100 mm conduit crossing the new Eska Street alignment.

The Contractor shall allow MTA one (1) calendar day to complete the adjustment and conduit installation.

9.	MTA will remove the cable attachment to existing MEA pole to be retired at Station 10+148, 28 left, and reattach to new pole at Station 10+146.5, 41 left.

The Contractor shall allow MTA one (1) calendar day to complete the adjustment.

105-1.12 LOAD RESTRICTIONS. Add the following: Overload and oversize permits are required to move the prestressed concrete girders between the Port of Anchorage or an Anchorage fabricating yard and the job site. Unless otherwise permitted by the overload permit officer, any permit will be subject to the following limitations:

Maximum Single Axle Load	13,610 kg (30,005 lbs)

Maximum Tandem Axle Load	22,680 kg (50,001 lbs)

Maximum Triple Axle Load	31,750 kg (69,997 lbs)

Maximum Four Axle Load	40,820 kg (89,993 lbs)

Minimum Spacing of Axle Group	6.1 m (20 ft) center to

center axle groups

Minimum Spacing Within Group	1.2 m (3.9 ft) center to

center axles

Maximum Vehicle Speed on any Structure	5 km/h (3.1 mph)

The maximum axle loads tabulated above are applicable to hauling equipment with fixed axles only; variable load suspension (VLS) axles shall not be considered part of an axle group for purposes of this specification.

Girder hauling methods, where one tractor is required to travel backwards, will not be permitted on public roads or streets for one-way travel distances totaling more than 16 kilometers.

Vehicles shall cross structures at a constant speed with load centered on roadway and no shifting of gears. Whenever the load exceeds 36,290 kg, the vehicle shall be preceded by a walking flagman when crossing structures.

This overload allowance shall not apply to the transportation of construction materials other than precast prestressed concrete girders.

All overload permits are subject to seasonal load restrictions.

Routing shall be as prescribed by the Permit Officer. The Permit Officer may be contacted at (800) 478-7636 or (907) 345-7636.

Alternate axle configurations and loading which may reduce the overload movement restrictions and conditions may be submitted to the Engineer for review.

(01/08/97)R103M

105-1.13 MAINTENANCE DURING CONSTRUCTION. Delete the first paragraph and substitute the following: The Contractor shall maintain the work, and those portions of the project affected by the work, from the date physical construction begins until project completion. This maintenance shall be a continual and effective effort prosecuted day by day, with adequate equipment and forces to the end that the work, and those portions of the project affected by the work, are kept in satisfactory condition at all times.

The Contractor may be relieved of specified portions of this maintenance responsibility during a seasonal suspension of work (Subsection 643-3.07), following partial acceptance (Subsection 105-1.14), or following substantial completion (Subsection 108-1.07). The Department will be responsible for routine snow removal and ice control on only those portions of the project which are open for public use.

(2/18/99)R236

105-1.15 PROJECT COMPLETION. Delete the first sentence of the third paragraph and substitute the following: When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas, and Section 628, Experimental Slope Stabilization, a letter of project completion will be issued by the Engineer.

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Delete the ninth paragraph and substitute the following: Any appeal must be in writing, must be limited to the issues that were before the Engineer, and must list the specific exceptions to the Engineer's decision including specific provisions of the Contract which the Contractor intends to rely upon in his appeal. (2/18/99)R237

Add the following: Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage. (8/5/93)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: All steel and iron products which are incorporated into the work and the action of applying a coating to a covered product (i.e., steel and iron) shall be manufactured in the United States except that minor amounts of products of foreign manufacture may be used provided the aggregate cost of such does not exceed one tenth of one percent (0.1 percent) of the total contract amount, or $2500, whichever is greater. Coating includes epoxy coating, galvanizing, painting, and any other coating that protects or enhances the value of a material subject to the requirements of this paragraph. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project.

A certification of materials origin, attesting to compliance with this provision, shall be furnished to the Engineer prior to incorporating any steel or iron products into the project.

(7/2/93)S13

Add the following: YEAR 2000 WARRANTY: The Contractor warrants that each hardware, software, or firmware product or item delivered or developed under this contract shall accurately process date data (including, but not limited to calculating, comparing, and sequencing) from, into, during, and between the twentieth and twenty-first centuries, including leap year calculations, when used in accordance with the documentation provided by the Contractor.

If the contract requires that specific products or items perform as a system, then this Year 2000 Warranty shall also apply to those listed items as a system.

The duration and remedies available to the State for breach of the Year 2000 Warranty shall be as defined in, and subject to, the year 2000 terms and limitations of any general warranty provisions contained in this solicitation. In the absence of any such general warranty provision(s), the remedies available to the State shall include repair or replacement, without any cost to the State, of any listed product or

item whose noncompliance is discovered and made known to the Contractor in writing by April 1, 2000 or within one (1) year after acceptance, or within the time limits of the Contractor’s warranty, whichever is longer.

Nothing in this Year 2000 Warranty shall be construed to limit any rights or remedies the State may otherwise have under the Uniform Commercial Code, State or Federal law, or with respect to defects other than Year 2000 performance.

The warranties contained herein are separate and distinct from any other warranties expressed or implied and are not subject to any disclaimer of warranty or limitation of the supplier’s liability.

(3/4/98)S79

106-1.02 LOCAL MATERIAL SOURCES. Add the following after the first paragraph: The Contractor shall provide process control for reasonable assurance, that all materials submitted for acceptance conform to the contract specifications. Sampling and testing of all materials for process control, including screening, crushing, blending, stockpiling of aggregates, production and laydown of aggregate courses or mixtures, asphalt concrete mixtures, and monitoring of compaction, is the responsibility of the Contractor. Process control tests shall be made in accordance with the applicable test methods specified in the contract.

A process control plan shall be submitted at the pre-construction conference. The process control plan shall include, for each item being produced, the methods to be used for sampling and testing, the proposed testing frequency, personnel qualifications, and equipment descriptions. Process control will not be measured for payment but will be subsidiary to the applicable items being processed.

The Department has the exclusive right and responsibility for determining the acceptability of the construction and all incorporated materials. Acceptance testing by the Department is not to be considered as a replacement for process control testing by the Contractor. When the Contractor is not providing adequate process control testing, the Engineer may refuse to retest materials which have been shown to be unacceptable by standard acceptance testing procedures.

(2/14/95)R201

Add the following after Item 5:

6.	Available Sources. The following material site is available to produce aggregates used for borrow, base course, or asphalt aggregate on this project.

M.S. 42-2-005-1 (DL 26878) is located at Milepost 66.1 on the Glenn Highway.

This material site is on lands managed by the Department. There are no royalty fees for materials removed and incorporated in the project.

The following guidelines pertain to the development and use of this site for borrow, base, and asphalt aggregate materials extraction for the subject project. All work necessary to develop and operate this site, including the removal and disposal of timber, overburden, reject materials, providing site facilities, dust control, protecting and restoring adjacent property, and performing site cleanup and rehabilitation, will not be paid for directly, but will be subsidiary to the respective pay items.

GENERAL CONDITIONS.

a.	Contractor's Responsibility. The Contractor and his agents, employees, and subcontractors are bound by all pertinent conditions of the development guidelines and the approved mining plan, along with all applicable State and local laws. Any variations from the specific or general stipulations must be approved through the Engineer, by the Regional Materials Engineer or his representative.

b.	Contractor's Mining Plan.

1)	Prior to use of the site for a specific project, a mining plan shall be submitted to the Engineer by the Contractor for approval by the Regional Materials Engineer, allowing 3 weeks for review. The mining plan will require a sketch map showing the site boundaries, the working boundary, proposed access route(s), temporary building and processing plant locations, and drainage diversion measures, if any. A mining plan narrative must accompany the sketch map and shall include dust suppression measures, measures to insure oil spill containment, and measures to prevent working area runoff contamination to water bodies.

2)	In addition to the mining sketch plan and narrative, the Contractor shall comply with all applicable conditions in the development guidelines.

c.	Changes in Conditions. Unforseen conditions arising during construction and operation, in accordance with the development and mining plans, may make it necessary to revise or amend the development and/or mining plan. In that event, the Contractor and the Engineer shall agree as to what revisions or amendments shall be made.

DEVELOPMENT PLAN GUIDELINES.

a.	Development of Site. Contractor shall develop the site to eliminate or minimize unauthorized uses, including dumping of waste, discharge of firearms, and unauthorized removal of materials. Prior to use of the site, the Contractor shall submit a mining plan containing the following:

1)	A sketch map showing the site boundaries, the working boundaries, development stages, proposed access, temporary and final stockpile locations, location of site facilities, and approximate contours before and after excavation including site drainage measures. Section and profile drawings should be used as appropriate.

2)	An accompanying narrative describing methods of operation, length and times of operation (day, month, year and working hours), and rehabilitation measures.

b.	Survey Monuments. The Contractor shall mark and protect all survey monuments within or near the site against destruction, obliteration, or damage during the life of this contract. If any public land monuments, or corners, or accessories, including but not limited to, U.S. Coast and Geodetic, U.S. Geological Survey, and/or Bureau of Land Management survey monuments, are destroyed, obliterated or damaged, the Contractor, by utilization of a registered land surveyor, shall reestablish or restore the monuments, corners or accessories using surveying procedures in accordance with the "Manual of Instruction for the Survey of Public Lands of the United States, 1973 Ed.," and shall record such survey in the appropriate records.

c.	Vegetation Screens and Buffer Areas. A 30 meter vegetation screen of undisturbed land (with the exception of access roads) will be maintained between site clearing, excavation or disposal site and any public roads or navigable waterbodies.

A 15 meter undisturbed buffer shall be maintained adjacent to any permanent streams or site boundaries not adjacent to public roads or navigable waterbodies, with the exception of sites situated on flood plains or submerged lands or sites requiring drainage ditches or connections to waterbodies, such as sites developed in connection with fishery enhancement purposes.

d.	Cultural/Archaeological. Reasonable measures shall be taken to avoid destroying, damaging, or removing paleontological, historical, or archaeological sites or artifacts. In the event that objects of historic or scientific interest, or antiquities are discovered on the land, they will be left intact and immediately brought to the attention of the Engineer, and operations upon that portion of the site shall cease.

e.	Fire Suppression. The Contractor shall take all reasonable steps to prevent and suppress forest, brush, grass, or tundra fires on the site and in its vicinity.

f.	Access Roads. The existing access road shall be the only access into this site. During dry conditions, dust along the access routes shall be controlled by the application of water or calcium chloride.

g.	Clearing. Clearing of vegetation and overburden shall be limited to the minimum acreage necessary to provide the required volume of materials. Additional clearing may not exceed 2.0 hectare increments in advance of excavation. Areas where any doubt exists about quantity or quality of material shall be proven with minimal disturbance prior to clearing and stripping.

h.	Timber. Standing timber over 13 centimeter breast height diameter in areas to be excavated will be offered to the public for cutting prior to clearing operations. The clearing area must be flagged and measures taken to prevent public cutting of timber in vegetation screens and buffers. In lieu of offering the timber for public cutting, said timber may be cut into 2.5 meter sections, limbed, and stacked in an area made available for public removal. All trees, snag and other woody material cut in connection with clearing operations shall be felled into the permit area and away from live water courses. All trees, snags, or other woody material cut in connection with clearing operations shall be cut so that the resulting stumps shall not be higher than 150 mm measured from the ground on the uphill side.

I.	Chipping. All brush and waste timber shall be chipped and stockpiled for spreading with or beneath the overburden for rehabilitation of non-expandable slopes and surfaces. Non-chippable stumps shall be buried in depleted portions of the site and covered by a minimum of 150 mm of earthen materials.

j.	Overburden. Overburden will be cleared only to the extent necessary to provide specific project quantities and stripped overburden will be stockpiled within the confines of the site. After excavation and contouring is complete, the stockpiled overburden will be spread evenly over worked-out portions of the site and non-expandable slopes as directed by the Engineer. Pushing overburden into standing timber or drainage courses is not authorized.

k.	Slopes. The site will be excavated leaving side slopes of 1V:2H or flatter and all excavated surfaces dressed to smooth contours. All excavation shall proceed toward non-expandable slopes. The excavation of the sides of the pit shall be done in such a way that at no time will backfilling be required in order to meet the final 1V:2H slope stipulations. Excavated slopes suitable for future site expansion shall not be rehabilitated until site expansion is completed.

l.	Excavation Depth. This site will be excavated no lower than 0.6 meter above any existing water table.

m.	Reject Materials. Reject materials shall be stockpiled separately within the site at a location identified and approved through the mining plan. No materials less than 0.25 meter diameter (except for overburden and designated waste or unusable materials) shall be rejected and stockpiled in the site, unless specifically authorized by the Engineer.

n.	Streams and Drainages.

1)	Existing drainage patterns should be altered only if necessary to prevent runoff contamination from the site causing erosion to adjacent lands or the entry of unacceptable levels of sediments into local water bodies.

2)	Upland site excavations shall be daylighted and graded to drain when necessary and feasible to prevent seasonal ponding, except when fishery or wildlife enhancement is intended.

o.	Site Facilities.

1)	The Contractor shall provide portable sanitation facilities. The Contractor may also install a trailer or mobile home for an office or night watchman's use. If a trailer or mobile home is provided, provisions must be made for sanitary waste and garbage disposal. If the grantee constructs any camp on the land, such location shall be indicated on the mining plan and approved by the Engineer, and the Engineer will have authority to require that said camp be kept in a neat and sanitary condition. The Contractor may leave equipment on the site until completion of project utilization with the understanding that the State does not accept any responsibility for theft or damage.

2)	No garbage or trash generated during site use will be buried or disposed of within the site.

3)	If a wash plant is to be located on the site, in accordance with the Contractor's mining plan, sediment settling basins shall be constructed to permit the removal of silt prior to runoff entering any water	bodies. Sediments shall not be released in any lake or water drainage in such concentrations as would exceed acceptable water standards.

4)	Petroleum product storage tanks shall be surrounded by berms of sufficient volume to contain 150 percent of the total volume of the tank and have an impervious liner within the berm and under the tank. Measures must be taken during equipment servicing to prevent any petroleum products from spilling on the ground. Said storage tanks and liner shall be removed and the containment berm shall be graded to conform with the site floor upon completion of the project.

5)	Crushers, asphalt hot plants, or other processing facilities may be located on the site in accordance with the Contractor's mining plan and must be operated in such a manner that no local, state, or federal laws, regulations, and guidelines are violated.

6)	No construction materials shall be stored in the site unless directly associated with the site operation or production of aggregate products for the State construction project.

p.	Emissions. Emissions from pumps, motors, equipment, installations, and burning material must meet the air quality standards of the United States Public Health Service and the State of Alaska. All burning shall meet the requirements of all applicable State and Federal laws and regulations and shall be used with maximum precautions to prevent forest and tundra fires. After burning, unconsumed material shall be disposed of in a manner approved in advance by the Engineer.

q.	Explosives. No blasting materials, blasting caps, and related materials may be stored on the site. No blasting will be permitted within one-quarter mile of streams or lakes, without a permit from the Alaska Department of Fish and Game. Personnel engaged in blasting activities shall be licensed by the State for these purposes and shall observe all applicable laws and regulations. Storage and handling of explosives shall be in accordance with Subsection 107-1.10, Use of Explosives.

r.	Petroleum Products. Petroleum spills of any size will be reported immediately to the Department of Environmental Conservation and the Engineer. Waste petroleum products shall be removed from the material site and disposed elsewhere.

s.	Maintenance and Operations. This site is utilized by Department of Transportation maintenance personnel, and shall be left open for their use.

t.	Use of Materials.

1)	The site is available for the Contractor's use in the production of borrow, base and asphalt aggregates. If the Contractor elects to utilize this site, he shall abide by the stipulations of the development and mining plan.

2)	State Contractors shall not remove material of any kind or quantity other than that needed for use on State projects.

3)	Should the Contractor decide to use the site, it is his responsibility to determine the suitability of the site for the project quality and volume requirements. The State does not assume any liability or responsibility to guarantee the quantity or suitability of site materials.

u.	Hazards. The site shall be operated in a manner that is not hazardous to humans or to wildlife.

v.	Rehabilitation.

1)	The rehabilitation of worked-out portions of the site not susceptible to erosion and not required for access or staging areas shall be by scarifying and fertilizing to allow natural revegetation.

2)	Rehabilitation areas susceptible to erosion will be seeded with 1.2 kilogram of arctared fescue per 100 square meters. Fertilizer application will consist of 450 kilogram per hectare of 10-20-10.

3)	If it is not possible to have seeding completed by August 15, seeding and fertilizing shall be performed at the beginning of the next growing season.

4)	A final pit inspection will be done by the Engineer or his representative, and the Contractor's representative, after completion of operations and prior to the removal of equipment to ensure compliance with the appropriate stipulations. Release of the Contractor's bond will not be authorized until the Engineer determines that the mining plan and site use conditions have been satisfactorily observed. The Engineer shall be notified by the Contractor at least 21 days prior to the scheduled removal of rehabilitation equipment from the site in order that an inspection can be performed.

5)	Upon site depletion and prior to vacating the site, the Contractor shall smooth out the pit to conform to the surrounding topography and distribute overburden over slopes and floor surfaces prior to site depletion. The access road to the pit will be similarly restored. No sharp depression or steep mounds will be left in the pit area.

w.	Site Clean-Up. All site clean-up shall be performed and all Contractor's equipment shall be removed from the site within 30 days following the completion of aggregate haul from this site by the Contractor.

MINING PLAN GUIDELINES.

a.	General.

1)	The mining plan, by sketch map and narrative, describes the Contractors proposed method of operation and must be in compliance with the conditions of the controlling development guidelines. After approval of the mining plan by the Engineer, it will be used as a site use field guide by the Contractor and the Engineer.

2)	Sketch maps shall have a scale sufficient for clarity under field conditions and should not be overly complex or inflexible.

3)	All data that can be shown graphically should be shown in that manner unless it can be better described in the accompanying narrative.

4)	The use of multiple sheets should be avoided, if practical.

5)	Section and profile drawings should be used as appropriate.

b.	Sketch Maps. Items to be shown on sketch maps, when appropriate, shall include:

1)	site boundary,

2)	existing or proposed access route and design,

3)	proposed working limits to be marked on the ground,

4)	development stages,

5)	approximate contours before and after excavation,

6)	high and low water lines,

7)	vegetation lines and type of vegetation, screens and dimensions,

8)	material stockpiling areas,

9)	overburden and reject stockpiling areas,

10)	other planned features, such as processing plants, temporary housing, wells, weigh scales, etc.,

11)	final slope ratios and site drainage measures including grade and, when appropriate, daylighting ditches or stream diversions,

12)	scale of drawing, north arrow, and specific dimensions as appropriate, and

13)	when sites are to be developed as wildlife or fishery enhancement ponds, pond configurations, connections to existing bodies of water, final pond depths, slopes, and any islands shall be shown on the sketch maps.

c.	Narrative. The mining plan narrative may be made part of the mining plan sketch map or may be attached to the sketch map as conditions allow. Items to be addressed in the mining plan narrative shall include:

1)	methods of operation,

2)	length and times of operation (day, month, year, and working hours),

3)	air and water pollution control measures, and

4)	rehabilitation measures.

d.	Supplements and Amendments. Supplements and amendments to an approved mining plan may be initiated by the Contractor or the Engineer when conditions warrant such action. Supplements shall be agreed to prior to commencement of work of a changed nature.

1)	Minor changes are those that affect the handling of the details of the operation, but remain in compliance with the development guidelines. These changes may be authorized by the Engineer.

2)	Major changes are those which cause the final outcome of the site to be significantly different from the approved mining plan or are not in compliance with the development guidelines.

3)	Changes in final site outcome must be approved in writing by the Regional Materials Engineer, through the Engineer.

4)	Changes not in compliance with the development guidelines must be authorized in writing by the Regional Materials Engineer and approved by the proper official of the Department of Natural Resources through the Engineer.

(07/9/97)R6M

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO

PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Prior to removing, stockpiling, staging or disposing of any material or equipment in, on or from a location not previously permitted by the contract, the Contractor shall obtain all necessary permits and clearances required. These permits and clearances may include, but are not limited to, State Historic Preservation Office clearance, a Division of Governmental Coordination Coastal Consistency Determination, Alaska Department of Natural Resources Mining Reclamation Permit, Alaska Department of Environmental Conservation permits, Alaska Department of Fish and Game Title 16 permit, US Fish and Wildlife endangered species clearance, US Army Corps of Engineers clearances and permits regarding wetlands, City or Borough Flood Hazard permit, local development permits, permission of property owner, etc.

The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, that will be impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that all permits or clearances necessary have been obtained. Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action was required on the part of the Contractor.

107-1.08 RAILWAY-HIGHWAY PROVISIONS. Delete the first paragraph and substitute the following: If the Department determines that the construction of the project will require that materials be hauled across the tracks of any railway, the Department will make arrangements with the railway for the use of such crossings. The Contractor shall obtain permits from the Railroad if additional temporary crossings are needed. (2/18/99)R239

Delete the second paragraph and add the following:

1.	Definition of Terms.

a.	Railroad's Manager of Telecommunications and Signaling - the person employed by the Railroad as head of its Telecommunications Department or his authorized representative.

b.	Railroad's Chief Engineer - the person employed by the Railroad as head of its Engineering Department or his authorized representative.

c.	Railroad's Contracting Officer - the person authorized by the Railroad to execute contractual agreements on behalf of the Railroad.

d.	Facility - any improvements owned by the Department which are to be placed on Railroad Property in accordance with a written permit executed by the Railroad and the Department.

e.	Permit Area - the space on Railroad property that is or will be occupied by the Facility plus reasonable working area and reasonable ingress and egress to the Facility.

f.	Railroad - the Alaska Railroad Corporation, P.O. Box 107500, Anchorage, Alaska 99510-7500.

g.	Railroad Property - all lands owned or withdrawn for the use of the Railroad, in and including the track right-of-way and communications pole right-of-way.

h.	Trackwork - all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

I.	Track Materials - all hardware, excluding signals and controllers, associated with the running of a railroad.

2.	General Requirements.

a.	All construction, reconstruction, operation and maintenance on the Railroad Property shall be performed in compliance with these specifications.

b.	Failure to comply with these specifications shall result in the suspension of all work on Railroad Property. The Contractor shall comply immediately upon notification from the Department, either verbal or written.

c.	All negotiations between the Railroad and the Contractor shall be handled through the Department.

d.	All work on or about the Railroad Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with the approved Railroad practices, and as specified herein. Railroad traffic and property shall be protected at all times.

e.	The safety and continuity of the operation of the railroad traffic shall be of first importance and shall be at all times protected and safeguarded. The Contractor and his subcontractors shall perform and arrange their work accordingly. The Railroad's Chief Engineer shall decide all matters involving the safety of Railroad facilities and the operation of it's railroad. The approval of the Railroad's Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which the Railroad may suffer or for which it may be liable, as a result of the acts of the Contractor, his subcontractor or employees.

f.	Whenever in the opinion of the Railroad's Chief Engineer, the construction may cause a hazard to the safe operation of the Railroad, the Railroad may, at its discretion, place at the site of the work the required number of qualified employees to protect its operations. The providing of such employees and such other precautions as may be taken shall not relieve the Contractor and his subcontractors from liability for the payment of damages caused by their operations. The Railroad shall be the sole judge of necessity, as to the number and classification of employees required. All Railroad cost and expense for providing such employees shall be collected from the Contractor, except for flagging which shall be paid for as described in Subsection 107-1.08.5.b.

g.	The Contractor shall be responsible for maintaining sight triangles at existing railroad crossings as well as at any temporary crossings within the project limits and at any railroad crossing outside the project limits that is designated and used as an alternate route for traffic.

3.	Insurance Requirements.

a.	The Contractor shall comply with all insurance requirements and conditions specified under Subsection 103-1.05, except that the following minimum limits shall apply for Comprehensive or General Liability Insurance:

Bodily Injury - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Property Damage - $1,000,000 each occurrence

Premises Operations

Independent Contractors

Products

Completed Operations

Blanket Contractual

b.	Prior to commencement of work on Railroad Property, the Contractor shall provide evidence of Railroad Protective Liability insurance (Alaska Railroad and State of Alaska as insureds) with the following limits:

Bodily Injury - $2,000,000 per occurrence

Property Damage - $2,000,000 per occurrence

4.	Notice.

a.	The Contractor shall give written notice to the Department and the Railroad not less than 10 days in advance of the commencement of any construction, reconstruction or major maintenance activity on Railroad Property, in order that the necessary arrangements may be made for the protection of the Railroad's operation. This notice shall include the proposed schedule of work, and the names of the subcontractors who may also be working on Railroad Property.

b.	A preconstruction meeting shall be held with the Railroad's Chief Engineer and representatives of the Department and Contractor prior to the commencement of any work on Railroad Property by the Contractor or his subcontractors.

5.	Excavations.

a.	All open excavations shall be continuously protected by flags, barricades or watchmen, as directed by the Railroad.

b.	No excavation shall be left open more than three days, unless authorized by the Railroad's Chief Engineer.

6.	Railroad Inspectors.

a.	The Railroad may furnish an inspector during the periods of construction on Railroad Property. The Railroad inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary. The Railroad inspector will work directly with the representative of the Department and the decision of the Railroad inspector in matters pertaining to Railroad operations and safety shall be final. In the event more than one shift is worked, a Railroad inspector will be required for each shift. Presence or absence of a Railroad inspector shall not relieve the Contractor of liability for damage done to property of the Railroad, Railroad lessees or permittees having installations on Railroad Property.

7.	Use of Explosives.

a.	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding the same.

8.	Clean-Up.

a.	At all times, all work and activities on the Facility shall be accomplished in such a manner as to keep the Railroad Property in a neat and orderly condition satisfactory to the Railroad.

b.	Upon completion of work, all equipment and unused materials shall be removed and the Railroad property shall be left in a neat and clean condition satisfactory to the Railroad.

c.	Should the Contractor or subcontractor fail to comply with Subsections 107-1.08.16.a. and 16.b., the Railroad may perform the required clean-up. All Railroad costs and expenses for performing this work shall be collected from the Contractor.

9.	Payment Guarantee.

a.	The Department shall withhold 10 percent of the contract price or $10,000.00, whichever is smaller, from the final payment to apply against damages or other direct costs which may be assessed by the Railroad as a result of the Contractor's operations.

b.	The amount withheld above shall not be released until after the Department has received a written statement from the Railroad's Contracting Officer agreeing to release the payment.

(5/7/91)S2M revised 3/10/99

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following to the third paragraph: When working near wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits. Refueling and servicing of equipment shall not be performed within 30 meters of wetlands.

Add the following after Item 10:

11.	If water for any construction purpose is required from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

Add the following: The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels. The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum fuels.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for material extraction, excess fill disposal, construction staging activities, equipment or material storage, or for any other purposes unless permitted by the contract. If the Contractor chooses to pursue permit modifications, such modifications shall be requested through the Engineer.

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work which is permitted and specified by the Contract.

All debris from the project construction shall be removed from the area as soon as possible and disposed of according to approved methods of the ADEC Solid Waste Program.

(7/8/98)R7M

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES. Delete items 1. through 3. under the fourth paragraph and substitute the following:

1.	When the utility is shown on the Plans or other contract documents.

2.	When the utility has been field located by the owner or operator.

3.	When a proper or timely field locate request was not made by the Contractor.

(2/18/99)R240

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m (10 feet) of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m (3 feet) of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m (10 feet) of an overhead electrical line.

The notice shall indicate the location and duration of the work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will not be paid for separately, but will be subsidiary to the item(s) of work being performed requiring these services.

(2/7/96)R170M

Add the following: All work undertaken near energized high voltage overhead electrical lines or conductors shall conform to AS 18.60.670, AS18.60.675, and AS18.60.680. (2/18/99)R240

107-1.21 PERMITS. Add the following subsection: The following permits have been received on the Contractor's behalf by the Department:

1.	Department of the Army, Corps of Engineers Permit No. 4-970618, dated December 9, 1997, and expiring November 30, 2000, to discharge approximately 765 cubic meters (1,000 cubic yards) of fill into wetlands and to place approximately 1,677 cubic meters (2,194 cubic yards) of material in 0.3 hectares (0.8 acres) of Eska Creek.

2.	Department of Fish and Game Title 16 Permit No. FG 97-II-0740 Amendment I, dated August 26, 1998 and expires December 31, 1999.

Note: This permit restricts inwater work at Eska Creek to the period of May 15 through August 1.

The Contractor shall provide the information necessary to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Construction in Alaska. Requirements for this permit are given under Section 641, Erosion and Pollution Control. Preparation of a Storm Water Pollution Prevention Plan (SWPPP), will be an amendment to the SWPPP prepared for the advance utility relocation work. This plan is available at the Anchorage Department of Transportation and Public Facilities Building Plans Room.

The permits obtained by the Department are attached to these specifications as Appendix A. The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications. It is the Contractor's responsibility to abide by the stipulations contained in each permit. If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer. The Engineer will then decide if a permit modification is necessary. The Engineer will have copies of the permits posted in the project office.

(9/10/92)R9A

Add the following subsection:

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A301

EEO-1 Certification							Form 25A304

DBE Subcontractable Items						Form 25A324

ADOT&PF Training Program Request				Form 25A310

Training Utilization Report						Form 25A311

Contact Report							Form 25A321A

DBE Utilization Report						Form 25A325C

Summary of Good Faith Effort Documentation			Form 25A332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

In addition to the reports required in the above references, the Contractor shall submit a copy of Form CC-257 to the Department by the 15th of each month of the current construction season, reflecting the composition of the previous month’s workforce. This information must also be made available, upon request, to the US Department of Labor, Office of Federal Contract Compliance Programs.

(8/13/98)S80

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01 SUBLETTING OF CONTRACT. Delete the next to last paragraph in this sub-section on page 38 and substitute the following: The hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor (or an approved subcontractor) shall not be considered as subcontracting under these provisions. Truck owner-operators shall be required to submit documentation to the Contractor as is necessary to prove the trucker is a bona fide owner-operator. As a minimum, those records, for each truck owner-operator, shall include current and valid copies of:

1.	Alaska Commercial Driver's License, with the appropriate endorsements for the class of vehicle to be operated,

2.	business license for trucking together with supporting documents that list the driver as the business owner or corporate officer,

3.	documents showing the driver's ownership interest in the truck including:

a.	truck registration, and

b.	lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of such records for a period of at least three years after final acceptance of the project.

Additionally, to be classified as a valid owner-operator a truck driver must also qualify as an independent contractor under the following Alaska Department of Labor (DOL) criteria which establish whether or not they are an employee or an independent contractor. The status of owner-operators is subject to evaluation throughout the project period and when the criteria for an independent contractor are not found to exist, amended payrolls must be submitted listing the driver as an employee subject to all labor provisions of the contract. These criteria are:

1.	The owner-operator's right to control the manner in which the work is to be performed,

2.	the owner-operator's opportunity for profit or loss depending upon their managerial skill,

3.	the owner-operator's investment in equipment or materials required for their task, or the employment of helpers,

4.	whether the service rendered requires a special skill,

5.	the degree of permanence of the working relationship, or

6.	whether the service rendered is an integral part of the owner-operator's business.

The Contractor shall issue a placard to each owner-operator. The placard shall identify both the truck driver and the vehicle and shall be prominently displayed such that it is visible to the scale person or inspectors. The identification system must be approved by the Engineer prior to use.

(5/7/91)S49M

108-1.03 PROSECUTION AND PROGRESS. Delete Items 5.and 7, of the first paragraph and substitute the following:

5.	A draft Storm Water Pollution Prevention Plan, Hazardous Material Control Plan, Notice of Intent, and activities description, as required under Section 641.

7.	A letter designating the EEO Officer and the DBE Officer and those persons' responsibilities and authority.

(2/18/99)R160

Add the following: The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule. The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule. At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule. The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly. The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements. The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60-Day Preliminary Schedule. Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule. Schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates. Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions. The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting. The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is shared equally.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks. This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

Preparation and updating of the CPM schedule and two week work plans will not be paid for directly. Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.

(12/13/96)R11

108-1.04 LIMITATION OF OPERATIONS. Add the following: The following special conditions apply:

1.	The Contractor shall be limited to a 60 consecutive day work window between Station 7+200 and Station 7+900. Work to be accomplished in the 60 day period shall include excavation, installation of drainage facilities for the new alignment and approaches, and embankment to the top of crushed aggregate base course. All other construction activities may occur in the normal phase of building. Contractor shall give the Engineer two weeks written notice before work begins in this area.

2.	Contractor shall notify the Engineer in writing two (2) weeks prior to start of work on Approach C. No work shall be performed outside the Right-of-Way on Approach C without prior approval of the Engineer.

3.	The Contractor shall notify the Engineer in writing two (2) weeks prior to driving piles.

108-1.05 CHARACTER OF WORKMEN, METHODS AND EQUIPMENT. Add the following: The Contractor shall provide the Engineer with make, model, year, capacity, watts, and the related information of every piece of powered equipment used on the project. This information shall be updated weekly unless otherwise directed by the Engineer. (6/6/95)R13M

108-1.07 FAILURE TO COMPLETE ON TIME. Add the following: For each calendar day after October 1, 1999 that the Glenn Highway is not paved, as required in subsection 643-3.08, $660.00 shall be deducted from any monies due the Contractor. For the purposes of this deadline, the suspension of calendar days as specified in 108-1.06, item 1. Calendar Days, shall not apply. The amount of these deductions is to cover estimated expenses incurred by the Department as a result of the Contractor's failure to complete this work within the time specified. Such deductions are liquidated damages and are not to be considered as penalties.

Add the following after Table 108-1:

The daily charges may be terminated at or following the final inspection, if the Department has determined that the work is substantially complete and is in a condition for safe and convenient use by the traveling public. The work will be considered substantially complete when all necessary signing, striping, guardrail, and other safety appurtenances have been installed. For projects that will not be opened to the traveling public, the work will be considered substantially complete when it is ready for the subsequent project. This shall not be construed as a contractual right and its application will be contingent upon the Contractor's diligence in completing the remaining items of work.

108-1.09 TERMINATION OF WORK FOR DEPARTMENT'S CONVENIENCE. Delete the second sentence of the fourth paragraph and substitute the following Payment for partially completed work will be made at actual costs incurred plus a reasonable profit.

Delete the fifth and sixth paragraphs and substitute the following:

After receipt of a Notice of Termination, the Contractor shall submit to the Contracting Officer, his claim for additional costs not covered above or elsewhere in these Specifications. Such claim may include such cost items as reasonable idle equipment time, mobilization efforts, bidding and project investigative costs, overhead expenses directly allocable to the project termination and not covered under work paid for in the preceding paragraph, legal and accounting charges and other expenses reasonably necessary in claim preparation, subcontractor costs not otherwise paid for, actual idle labor costs if work is stopped in advance of termination date, guaranteed payments for private land usage as part of the original Contract, and any other costs for which the Contractor feels reimbursement should be made. The intent of negotiating this claim would be to reach an equitable settlement figure with the Contractor for the actual costs incurred. In no event, however, will loss of anticipated profits or consequential damages be considered as part of any settlement.

For any claim related to operating equipment owned by the Contractor, the Contractor is entitled to recover equipment costs based on the Contractor's actual costs for ownership and actual operating expenses. For any claim related to idle equipment time for equipment owned by the Contractor, the Contractor is entitled to recover equipment rates based on the Contractor's internal ownership costs. Recovery for operating equipment or idle equipment time shall not be based on published rental rates. Claims for idle equipment time following termination of the contract are limited to a maximum of 30 days, and may not include any operating expenses. In the case of rented or leased equipment, the Contractor shall recover the lesser of its actual rental costs or fair market rental costs, and the amount paid shall not exceed 30 days rental.

(2/18/99)R241

SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES. After the ninth paragraph, insert the following: The Contractor shall furnish competent scale operators to weigh all materials measured and paid for on a weight basis.

The scale operator shall record to the nearest 50 kilograms the weights of all loads of material on a daily tally sheet. The scale operator shall also make out a weigh slip ticket for each load hauled showing the gross, tare and net weights. The original shall accompany the load and one copy shall be retained until any discrepancies have been resolved at the end of each day.

The scale operator's daily tally sheet shall also include the following information as applicable to the type of scales used:

1.	Name and number of project,

2.	Contract item number,

3.	Description of source,

4	Date,

5.	Load number,

6.	Truck identification mark,

7.	Time of weighing,

8.	Gross weight of each load,

9.	Tare weights,

10.	Net weights,

11.	Scale operator's signature, and

12.	Contractor's certification.

The original daily weight record shall be furnished to the Engineer at the end of each shift.

The Engineer may, at random intervals, designate previously weighed vehicles to be reweighed, in his presence, to verify the weight of the materials being purchased. This will include empty or loaded vehicles as the Engineer may designate.

No direct payment will be made for furnishing scale operators, equipment, and incidentals required. Costs thereof will be subsidiary to bid prices of the material being weighed.

(7/26/95)S11M

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia Information, Inc., 10 Lake Drive, Hightstown, NJ 08520-5397.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

(2/18/99)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon receipt of current schedules from the Contractor.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(9/21/92)R137A

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer. (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract. The Contractor shall carry out applicable requirements of 49 CFR part 26 in the award and administration of DOT-assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section shall be considered a material breach of contract. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04 DEFINITIONS AND TERMS

1.	Broker. A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with

its own equipment and employees within its certified category. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE). A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts. The affirmative action measures that shall be taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer. A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer. A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis.

8.	Revised DBE Utilization Goal. The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C. The Revised DBE Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved. Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01 UTILIZATION GOAL. The Original DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total basic bid amount. In order for the work of the DBE to be credited towards meeting the Original DBE Utilization Goal at time of contract award, the DBE must be certified by the Department in a category covering the CUF to be performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid and Award. In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the contractor submits less DBE utilization on Form 25A325C than is required to meet the Original DBE Utilization Goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (25A321A) shall be submitted. If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than is required by the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

2.	Phase II - Construction. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE. Prior written request by the Contractor and approval from the Engineer is required for the replacement of a DBE for any reason. If DBE replacement is approved, the Contractor is obligated to replace the DBE with another DBE for the same work in order to still meet the Revised DBE Utilization Goal. If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work to have been performed by the replaced DBE in order to have the Revised DBE Utilization Goal reduced.

120-3.02 GOOD FAITH EFFORT. The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract. Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

1.	Consideration of all subcontractable items. The Contractor shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification at least 10 calendar days prior to bid opening to all DBEs listed in the Department's most current DBE Directory certified to perform those work items identified in Form 25A324 of the bidder's/Contractor's interest

in securing the DBE's participation in the execution of the work. Each contact with the DBE shall be logged on a "Contact Report" (Form 25A321A).

4.	Request for DBE participation on specific items of work or services. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE quotes are for the exact same work or service. Where the Contractor rejects a DBE quote as being non-competitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding. Documentation of follow-up contacts shall be logged on the "Contact Report" (Form 25A321A).

Items 4. through 7. will be utilized to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF). Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

a.	regular dealer,

b.	manufacturer,

c.	broker,

d.	subcontractor,

e.	joint-venture, or

f.	prime contractor.

In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE shall be certified in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b.	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

2.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

3.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted within that category to the CUF of a broker. (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation which could include the hauling of materials for that work.)

4.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

5.	Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the Revised DBE Utilization Goal.

6.	Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm shall not be credited toward the Revised DBE Utilization Goal. The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01), or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

7.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the Revised DBE Utilization Goal.

8.	The Engineer shall consider the following criteria when determining what CUF is being performed by the DBE:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below. Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site. All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work. An exception to this requirement may be permitted where the DBE must perform a specialty task or where the work is in a remote area. In such instance, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the work, if the Department considers this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value. Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved. Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control. DBE leases and payments for equipment must be documented; Contractor withholding or retainage for DBE labor and equipment usage is not permissible. Two-party checks to individuals are not permissible.

e.	The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as defined by the Department. The work or provision of goods or services shall have a market outside of the DBE program (must be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed a superfluous step in the contracting or purchasing process and no DBE credit will be allowed.

There shall be no DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

g.	All subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The DBE shall control all business administration, accounting, billing, and payment transactions (this requirement does not preclude the two-party check allowance described under I., below). The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

i.	Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE.

Two-party checks may be issued by the Contractor on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Engineer shall be notified in writing in advance. DBE credit will not be given for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before any DBE credit may be credited. The DBE supervisor must be regularly employed by the DBE and designated as a key employee in the DBE's certification records with the Department prior to prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identify payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the quantity of work of a bid item which involves a DBE is reduced by the Department, the Original and Revised DBE Utilization Goals on Form 25A325C are reduced proportionately.

120-3.04 DEFAULT OF DBE. In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default. The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the

event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, both of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Revised DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, retainage may be withheld from progress payments. The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, payments will be reduced as a disincentive. The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after the Original DBE Utilization Goal established on Form 25A325C in terms of dollars has been met, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUF work performed by DBE subcontractors not needed in the calculation to meet the Original DBE Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

Payment of the incentive will be made on the final estimate. The disincentive will be withheld in the form of retainage during the course of the project. If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

A Change Order is not required for DBE Adjustment. The Notice To Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(6/6/94)S33

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-2.04 HAND CLEARING. Add the following: Clearing in wetlands shall be by hand. Tree roots or trunks outside clearing limits shall not be damaged by heavy equipment.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work shall also include the removal and disposal of the existing Bridge No. 542 at Eska Creek. Contractor shall salvage the girders and transport them to the State Maintenance Yard, 289 Springer Loop Road, Palmer, Alaska. The girders shall be transported in a whole condition and set on sleepers, furnished by the Contractor, at a location designated by the Engineer.

Bridge No. 542 at Eska Creek is a single span bridge, 9.6 meters long by 7.9 meters wide, consisting of a reinforced concrete deck, four W460 x 74 girders and reinforced concrete abutments supported on 3-rail steel piles.

202-2.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: The construction of mail box installations shall use new posts and mail boxes. Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 530 mm, minimum width of 200 mm and minimum height of 265 mm. Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground. (10/5/93)R74M

202-2.04 REMOVAL OF PAVEMENT, SIDEWALKS, CURBS, ETC. Add the following: Pavement removed on this project which is to be stockpiled, shall be processed and sized so that 98 per cent of the materials pass the 37.5 mm sieve. This material shall be hauled and stockpiled at locations shown on the plans. Stockpiles shall be built using radial stacking conveyors. No equipment shall operate on the stockpiles. (2/12/99)

Any removed pavement not used on this project as stockpiled material, recycled asphalt pavement base course, or substituted as RAM for aggregate base course, shall be processed and sized so that 98 per cent of the materials pass the 37.5 mm sieve and delivered to the State Maintenance Yard, 289 Springer Loop Road, Palmer, Alaska.

202-4.01 BASIS OF PAYMENT. Add the following: Payment for Item 202(17) Removal of Bridge No. 542, will include all labor, equipment and materials necessary to remove, salvage and transport the superstructures, remove and dispose of the reinforced concrete abutments and wingwalls, and steel piling.

202-4.01 BASIS OF PAYMENT. Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

202(17)	Removal of Bridge No. 542	Lump Sum

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-2.03 UNCLASSIFIED EXCAVATION. Add the following: This shall also include the removal of existing survey monuments as indicated on the plans.

203-2.05 BORROW. Delete the second paragraph and substitute the following: Borrow, Type A, B, C, or D when required, shall meet the requirements of Subsection 703-2.07, Selected Material, Type A, B, C, or D, respectively.

203-3.01 GENERAL. Add the following to the fifth paragraph: Prior to obliterating the existing roadway, the existing pavement shall be removed and disposed of in accordance with Subsection 202-2.04, Removal of Pavement, Sidewalks, Curbs, Etc. (11/19/93)R177

Add the following: Between Station 6+200 and 6+900 Left, the excavated slope shall be covered with plastic sheeting. No more than 8 vertical meters shall be unprotected at any time. See Section 628 for installation details.

203-3.02 EMBANKMENT CONSTRUCTION. On page 62, delete the first sentence of the fourth paragraph, and substitute the following: Roadway embankments shall be placed in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

The surface of Selected Material, Type D, shall be compacted by coverage of the Contractor's placement equipment to provide a smooth and firm slope. The surface of Selected Material, Type D shall be free of surface irregularities, rutting, slope breaks or unconsolidated material.

(12/13/96)R23M

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL. Delete the second paragraph and substitute the following: Embankment material, other than Select Material Type D, shall be compacted to not less than 95 percent of the maximum density. Maximum densities will be determined by AASHTO T 180, or ATM T-12. In place field densities will be determined by ATM T-3 or ATM T-11. (1/8/97)R193

Add the following: All embankment within 6 meters of a bridge abutment shall be compacted full width to not less than 100 percent of the maximum density. All material used within this zone shall be graded to pass the 75-millimeter sieve. (5/31/96)R113M

203-5.01 BASIS OF PAYMENT. Add the following: Grading and placement of material used within 6 meters of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(6A) Borrow, Type A. (5/31/96)R113M

The removal of existing survey monuments shall be subsidiary to Item 203(3) Unclassified Excavation.

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Bedding and backfill materials shall meet the requirements for Selected Material, Type A, as specified in subsection 703-2.07 Selected Material. Pipe bedding and backfill material shall also pass the 75 mm sieve.

Selected Material, Type A pipe backfill shall extend a minimum of 300 mm above the pipe. Excavated native material shall be utilized for the remainder of the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material. Bedding and backfill materials within the pavement structure shall meet the requirements for the applicable lift of material. All suitable material from structure excavation shall be used for bedding and backfill prior to using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the third paragraph: Native material may be utilized for electrical conduit bedding and backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in subsection 703-2.07 Selected Material. Compaction may be as approved by the Engineer.

(11/04/94)R25M

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for crushed aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 300 µm | 5-34 |
| 150 µm | 3-22 |
| 75 µm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.01 PLACING. Add the following: Base course material used for the pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for crushed aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for crushed aggregate base course, it will be paid for as Item 301(1), Crushed Aggregate Base Course at the unit price shown on the bid schedule for that item.

(12/11/96)R176M

Add the following section:

SECTION 310

RECYCLED ASPHALT PAVEMENT BASE COURSE

Special Provisions

310-1.01 DESCRIPTION. This work shall consist of furnishing and placing recycled asphalt pavement base course on an approved surface in conformance with the plans.

310-2.01 MATERIALS. Recycled asphalt pavement base course shall be produced from asphalt pavement that has been crushed and processed. All agglomerated particles shall be sized to pass a 37.5 mm sieve. Tests for aggregate and asphalt cement shall apply to the delivered product.

310-2.02 AGGREGATE. The gradation of the extracted aggregate shall be determined in accordance with AASHTO T 30 and shall meet the following grading specifications:

Sieve			Percent Passing by Weight

25 mm			100

19 mm			70-100

9.5 mm			42-90

4.75 mm			28-78

1.18 mm			11-54

300 µm			5-34

150 µm			3-22

75 µm				2-12

310-2.03 ASPHALT CEMENT. Asphalt cement content shall be between 2.5 - 5.0 percent by weight as determined by ATM T-16, AASHTO T 164, or AASHTO TP 53.

CONSTRUCTION REQUIREMENTS

310-3.01 PLACING. The recycled asphalt pavement base course shall be placed and uniformly spread on the approved grade in one layer. Any material that becomes segregated shall be remixed before compaction occurs.

310-3.02 COMPACTION. The amount of compactive effort required shall be determined by the control strip method using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The control strip shall be evaluated with the use of a nuclear density gauge to establish a roller pattern. The location of the control strip will be designated by the Engineer.

The Contractor shall be responsible for the development of the control strip. Adequate water shall be added to facilitate compaction of the recycled asphalt pavement base course. The Contractor shall select a minimum of two test sites on the control strip and take 15 second (minimum) readings with the nuclear densometer at each test site for every roller pass over the test site. Rolling shall continue until there is less than a 16 kg/m³ increase in unit weight in the averaged density readings per roller pass. A copy of the density readings developing the control strip will be supplied to the Engineer. The Engineer will obtain ten random nuclear density readings on the completed control strip. A density standard for the project will be determined by averaging the ten readings. Compaction requirements will be 98% of the density standard.

After the recycled asphalt pavement base course layer has received the appropriate compaction with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Pneumatic roller tires shall be inflated to 550 kPa (± 34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

310-3.03 SURFACE TOLERANCE. The finished surface shall not show any variances in excess of 12 mm when tested with a 3 meter straight edge. Areas which are out of tolerance must be corrected by methods approved by the Engineer.

310-3.04 SURFACE MAINTENANCE. The surface may require repair due to traffic and weather, this shall be considered incidental to this item of work.

310-4.01 METHOD OF MEASUREMENT. Recycled asphalt pavement base course shall be measured by the megagram in accordance with Section 109. Water needed for compaction will be considered a subsidiary obligation.

310-5.01 BASIS OF PAYMENT. The accepted quantity of recycled asphalt pavement base course will be paid at the contract bid price, per unit measurement, complete and in place.

Pay Item No.	Pay Item	Pay Unit

310(1)	Recycled Asphalt Pavement Base Course	Megagram

R227M

Delete Section 401 in its entirety and substitute the following:

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-1.01 DESCRIPTION. This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the asphalt concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

401-2.01 COMPOSITION OF ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN. Asphalt concrete mixtures shall be composed of aggregate, asphalt cement, and required additives combined within the limits for the type and class of asphalt concrete specified in the contract.

The Contractor shall provide an asphalt concrete mixture that meets the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete.

At least 15 calendar days prior to the production of asphalt concrete pavement mixture, the Contractor shall submit the following to the Engineer:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile. The proposed gradations must meet the requirements of Table 703-3, Asphalt Concrete Aggregate, for each type of asphalt concrete pavement specified in the bid schedule. Asphalt concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended. Sample sizes: 45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance in accordance with Section 106, and a temperature viscosity curve for the asphalt cement.

4.	A 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

From this information, the Engineer will establish the Job Mix Design which will become a part of the contract and shall be followed unless modified in writing. The Job Mix Design will be determined in accordance with ATM T-17 (version 01/93) and evaluated for conformance with the asphalt concrete mix design requirements of Table 401-1 for the appropriate type and class of asphalt concrete. Job Mix Design test results will be available within 7 working days after submittal. Approved Job Mix Designs will specify the target value for asphalt cement, additives, and the allowable temperature range for mixing.

Changes in the Job Mix Design warranted by changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio shall be submitted by the contractor in the same manner as the original submittal. A new Job Mix Design will only apply to asphalt concrete mixture produced after the Contractor submittal of the new aggregate gradation.

All mix designs after a Job Mix Design has been approved for the Type and Class of Asphalt Concrete will be assessed a fixed fee of $1,500.00 each.

Approved Job Mix Designs will have the full tolerances shown in Table 401-2 applied and will not be limited to the broad band listed in Table 703-3. Tolerances for the largest sieve specified will be plus 0% and minus 1%.

Temporary pavement shall meet the minimum asphalt concrete mix design requirements for Asphalt Concrete Type II, Class B.

Table 401-1

Asphaltic Concrete Mix Design Requirements

| DESIGN PARAMETERS | CLASS "A" | CLASS "B" | CLASS "C" |
| --- | --- | --- | --- |
| Stability, newton, min. | 8,000 | 5,340 | 3,340 |
| Flow, 0.25 mm | 8-14 | 8-16 | 8-18 |
| Voids in total mix, percent | 3-5 | 3-5 | 2-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 | 35 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 | N/A |
| Voids in the mineral aggregate (VMA), min. |  |  |  |
| Type I Type II Type III | 12.0 13.0 14.0 | 11.0 12.0 13.0 | N/A N/A N/A |

*Dust-asphalt ratio is defined as the percent of material passing the 75μm sieve divided by the percent of asphalt (calculated by weight of mix).

401-2.02 AGGREGATES. Aggregate shall conform to the requirements of Subsection 703-2.04.

Aggregates for asphalt concrete mixtures shall be divided into a minimum of 2 piles, one coarse and one fine. If blend sand is used, it shall be an additional pile.

401-2.03 ASPHALT MATERIALS. The grade of asphalt cement will be specified in the bid schedule. The asphalt cement shall conform to the applicable requirements of Section 702. Asphalt cement may be conditionally accepted at the source. If the material is to be conditionally accepted at the source, the Contractor shall provide a manufacture's certificate of compliance in accordance with Subsection 106-1.05 and test results of the applicable quality requirements of Section 702 before the material is shipped.

If there is a change in the source of the asphalt cement, or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt cement supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted for approval.

401-2.04 ANTI-STRIP ADDITIVES. Anti-strip agents shall be used in the proportions determined by ATM T-14 and shall be included in the approved Job Mix Design. At least 70% of the aggregate shall remain coated when tested in accordance with ATM T-14.

401-2.05 PROCESS QUALITY CONTROL. It is expressly understood that the contractor is solely responsible for the sampling and testing of material for process control of the asphalt concrete mixture in accordance with Subsection 106-1.02.

The Contractor shall employ a qualified person or company to perform process control testing. A process control plan shall be submitted at the project pre-construction conference in accordance with Subsection 106-1.02. Failure to perform process control forfeits the Contractor's right to retests as provided for in Subsection 401-4.02.

A paving and plant control plan shall be submitted at a pre-paving meeting to be held a minimum of 5 working days prior to initiating paving operations. The paving and plant control plan shall address joint construction, outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the asphalt concrete mixture. This plan shall also include a proposed testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. The asphalt concrete mixture shall not be placed on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture. No asphalt concrete mixture for a leveling course shall be placed unless the surface temperature is 5 degrees Celsius or warmer. Final paving will not be permitted between September 15, 1999 and May 1, 2000.

401-3.02 EQUIPMENT. All equipment shall be in good working order and free of asphalt concrete mixture buildup. All equipment shall be available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

401-3.03 BITUMINOUS MIXING PLANTS. The Contractor shall use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. The Contractor shall calibrate the asphalt mixing plant and furnish copies of the data to the Engineer at least 2 days prior to asphalt concrete mixture production.

The asphalt mixing plant shall have a scalping screen to prevent oversize material or debris from being incorporated into the asphalt concrete mixture. Aggregate and asphalt cement sampling locations meeting OSHA safety requirements shall be provided.

Proportioning (batch) scales shall not be used for weighing material for payment. Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

401-3.04 HAULING EQUIPMENT. Trucks used for hauling asphalt mixtures shall have tight, clean, smooth metal beds which have been thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List. Diesel fuel or fuel oil shall not be used as an asphalt release agent.

Each truck shall have a cover of canvas or other suitable material of such size as to protect the asphalt concrete mixture, when required, so that the mixture shall be delivered to the asphalt paver at the proper temperature.

401-3.05 ASPHALT PAVERS. Asphalt pavers shall be self-propelled units provided with a heated vibratory screed. Grade and cross slope shall be controlled through the use of automatic grade and slope control devices. The paver screed control system shall be automatically actuated by the use of an erected string line, mobile stringline (ski) on the high side of the paver at least 9 meters in length, or other approved grade follower. Grade control shall be used on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

The paver shall be equipped with a receiving hopper having sufficient capacity for a uniform spreading operation. The hopper shall be equipped with a distribution system to place the asphalt concrete mixture uniformly in front of the screed.

The screed assembly shall produce a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the asphalt concrete mixture. Screed extensions used for paving a constant width shall be heated and vibrated. Auger extensions shall be within 0.5 meters of the screed extension on both sides.

The use of a Layton Box will be allowed on bikepaths, sidewalks, pathways and medians.

401-3.06 ROLLERS. The Contractor shall supply a sufficient number and weight of rollers to compact the mixture to the required density while maintaining the pace of the paving operations. Rollers shall be static or vibratory steel wheel and pneumatic tire type rollers. The rollers shall be self propelled and capable of reversing without backlash. They shall be specifically designed to compact hot asphalt concrete mixtures. The use of equipment which results in crushing of the aggregate will not be permitted. Pneumatic tire rollers shall be fully skirted, have an operating weight per tire of at least 1,360 kilograms and be operated in accordance with the manufacturer's instructions.

401-3.07 PREPARATION OF EXISTING SURFACE. Existing surfaces shall be prepared in conformance with the plans and specifications. Existing paved surfaces shall be cleaned of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

Contact surfaces of curbing, gutters, manholes, sawcut pavement, and other structures shall be coated with a uniform coating of tack coat material conforming to Section 402 prior to the asphalt concrete mixture being placed.

Surfaces which have received a prime coat shall be allowed to cure. Surfaces which have received an emulsion tack coat shall be allowed to break prior to placement of asphalt concrete mixture.

401-3.08 PREPARATION OF ASPHALT. A continuous supply of the asphalt cement shall be supplied to the mixer at a uniform temperature, within 14 degrees Celsius of the Job Mix Design mixing temperature.

401-3.09 PREPARATION OF AGGREGATES. The aggregate for the asphalt concrete mixture shall be heated and dried to a temperature compatible with the mix requirements specified. The burner on the dryer shall be properly adjusted to avoid damage to the aggregate and to avoid the presence of unburned fuel on the aggregate. Any asphalt concrete mixture in which soot or fuel is present shall be wasted and no payment made.

Drying operations shall reduce the aggregate moisture content so that the moisture content of the asphalt concrete mixture, sampled at the point of acceptance for asphalt cement content, shall be no more than 0.5% (by total weight of mix), as determined by ATM T-25.

401-3.10 MIXING. The aggregate, asphalt cement and additives shall be combined in the mixer in the amounts required by the Job Mix Design.

The materials shall be mixed such that a complete and uniform coating of the aggregate is obtained. For batch plants, dry aggregate shall be in motion prior to the addition of asphalt cement. Wet mixing time shall be adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

The temperature of the asphalt concrete mixture at the time of the mixing shall be as determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Asphalt concrete mixture drawn from silo type storage bins shall conform to all of the requirements for asphalt concrete mixtures as if loaded directly into hauling equipment from the mixing plant. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Rejected asphalt concrete mixture shall be disposed of by the Contractor at no cost to the State.

401-3.12 SPREADING AND PLACING. The asphalt concrete mixture shall be laid upon a surface approved by the Engineer, spread and struck off and compacted to the required compacted thickness. Asphalt pavers shall be used to distribute the asphalt concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of Subsection 401-3.14. Asphalt pavers shall also be used to distribute asphalt concrete mixture for leveling course unless otherwise allowed.

On areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable, the asphalt concrete mixture shall be spread, raked and luted by hand tools. For such areas the asphalt concrete mixture shall be placed to the required compacted thickness.

When the section of roadway being paved is open to traffic, adjacent traffic lanes shall be paved to the same elevation within 24 hours unless prevented by weather or other factors beyond the Contractor's control, in order to prevent lane edge dropoff. When the outside pavement edge dropoff exceeds 50 millimeters, approved material shall be placed against the pavement edge.

When multiple lifts are specified in the contract, the final lift shall not be placed until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted. Paving shall not begin until all adjacent curb has been poured and cured for 72 hours.

Asphalt concrete pavement to be placed over bridge deck membranes shall not be placed until the membrane has cured according to the manufacturer's specifications. Vehicles, except the paving machine and trucks hauling the asphalt concrete mixture for the overlay, shall not be operated on the membrane. Paving machines used on the membrane shall be rubber-tired or rubber-tracked. The Contractor shall follow the manufacturer's published minimum and maximum temperature limitations for the asphalt concrete mixture. Vibratory rollers, with the vibrator engaged, shall not be used on bridge decks.

401-3.13 COMPACTION. Immediately after the asphalt concrete mixture has been spread, struck-off and surface irregularities adjusted, it shall be thoroughly and uniformly compacted by rolling.

The target value for density will be 94% of the maximum specific gravity (MSG), as determined in accordance with AASHTO T 209. For the first lot of each type of asphalt concrete pavement, the MSG will be determined by the Job Mix Design. For additional lots, the MSG will be determined by the sample from the first sublot of the lot. Acceptance testing for field density will be determined in accordance with ATM T-18 except that two 200 mm diameter core are required. (Acceptance testing for field density of leveling course or temporary pavement will not be done.)

The asphalt concrete pavement, including leveling course, shall receive a minimum of 3 complete passes with a pneumatic-tired roller. A pass is defined as once over each point on the pavement surface.

Areas not accessible to the rollers shall be graded with rakes and lutes and compacted with mechanical tampers. For depressed areas a trench roller may be used to achieve the required compaction.

Rollers or other vehicles shall not be parked or left standing on pavement that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Joints shall be constructed to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement. The minimum specification limit for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint. The Contractor shall cut one 200 mm core centered on the longitudinal joint at each location the mat is cored for acceptance density testing. Density will be determined in accordance with ATM T-18.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Improperly formed joints resulting in surface irregularities shall be removed full depth, replaced with new material, and thoroughly compacted. Rolling of joints after the material has cooled below 65 degrees Celsius shall not be allowed. All pavement removal shall be precut to a neat line with a power driven saw.

A tack coat of asphalt cement or asphalt emulsion shall be applied on all cold joints and allowed to break prior to placing any fresh asphalt concrete mixture against the joint. This work shall be completed by the Contractor just prior to paving.

Transverse joints shall be formed by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead. Transverse joints shall not be perpendicular to centerline, but at a skew between 15-25 degrees.

The longitudinal joints in one layer shall offset those in the layer immediately below by at least 150 millimeters. The joints shall be at centerline or lane lines. Where preformed marking tape striping is required, the longitudinal joint in the top layer shall be offset 50 to not more than 150 millimeters from the edge of the stripe.

401-3.15 SURFACE TOLERANCE. The surface of the Asphalt Concrete Pavement will be measured after final rolling at selected locations using a 3 meter straightedge. The variation of the surface from the testing edge of the straightedge between any two contacts with the surface shall not exceed 5 millimeters.

The smoothness of the Asphalt Concrete Pavement in all driving lanes will be measured by the Engineer with a California-type profilograph within 14 days after mainline paving is completed and all defects are corrected. No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or matches with an existing pavement. The profilograph results (PrI) will be reduced within the 14 day period and a price adjustment will be calculated in accordance with Subsection 401-5.01. Any required traffic control devices or flagging shall be furnished by the Contractor in accordance with Section 643.

401-3.16 PATCHING DEFECTIVE AREAS. Any asphalt concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective as determined by the Engineer shall be removed. Skin patching will not be permitted. Defective materials shall be removed for the full thickness of the course. The pavement shall be cut so that the sides are parallel to the direction of traffic and so that the edges are vertical. Edges shall be coated with a tack coat of material conforming to Section 402 and allowed to cure. Fresh asphalt concrete mixture shall be placed in sufficient quantity so that the finished surface will conform to grade and smoothness requirements. The asphalt concrete mixture shall be compacted to the density specified. All costs associated with the patching of defective areas shall be borne by the Contractor.

Any asphalt concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective shall be removed and replaced with fresh hot asphalt concrete mixture, which shall be compacted to conform with the surrounding area. Any area showing an excess or deficiency of asphalt cement shall be removed and replaced.

401-4.01 METHOD OF MEASUREMENT. The asphalt concrete mixture will be measured by the megagram or by the square meter in accordance with Section 109. The weight used will be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material and anti-stripping additive in the mixture.

The weight of asphalt cement will be calculated using the percent of asphalt cement for each sublot multiplied by the total megagrams represented by that sublot. Percent of asphalt cement will be determined by AASHTO TP53. The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

No payment will be made for any asphalt cement in excess of 0.4% above the optimum asphalt content specified in the Job Mix Design.

Longitudinal joints will be measured by the meter. The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of each type of asphalt concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance. The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project. Acceptance sampling and testing shall be performed by the Engineer. The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams. The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection. If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot shall include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot. The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density, and gradation in accordance with this subsection. The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing. If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed. If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result. If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with Sub-section 401-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, asphalt concrete pavement will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the asphalt concrete pavement to the specified depth and finished surface requirements and tolerances. Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees Celsius prior to completing compaction, or is in any other way defective, shall be removed and replaced with new asphalt concrete pavement. Removal and replacement of defective pavement shall be at no additional cost to the Department.

Within 24 hours of final rolling, the Contractor shall cut two 200 mm full depth samples from the finished mat and cut one 200 mm full depth sample from the longitudinal joint. The samples shall be neatly cut by a core drill at the randomly selected locations marked by the Engineer. A core extractor shall be used to prevent damage to the core. No samples shall be cut over bridge decks. Failure to cut core samples within the specified period will result in a price disincentive of $100 per day per sample. The accrued amount will be subtracted from the Contractor’s payment under Item 401(5) Asphalt Price Adjustment.

The two 200 mm cores taken from the mat will be used to determine density, asphalt content, and aggregate gradation. The cores will be tested separately and then the results averaged for the reported value. This average will be used to determine acceptance.

The core from the longitudinal joint shall be used to determine joint density.

Density Test - ATM T18

Asphalt cement content - AASHTO TP 53 (ignition method)

(moisture correction - ATM T 25)

Aggregate Gradation - AASHTO T-30

(on aggregate remaining from AASHTO TP 53)

All voids left by sampling shall be backfilled with new asphalt concrete mixture and compacted within 24 hours of sampling. Failure to backfill voids left by sampling in the specified period will result in a penalty of $100.00 per hole per day. The accrued amount will be subtracted from the Contractor's payment under Item 401(5) Asphalt Price Adjustment.

The Contractor may request a retest of any sample not within specification limits. This request shall be in writing and delivered to the Engineer within 7 days of receipt of the initial test result. Verbal requests with the written request to be delivered after the specified 7 days will not be accepted. The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s). The Engineer will mark the sample location for the retest. Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s). The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample will be allowed.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to each type of Asphalt Concrete Pavement for which the contract quantity equals or exceeds 4,500 megagrams, except as defined in Subsection 401-4.02. The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis - Standard Deviation (Specification Conformance Analysis) Method using the procedures listed to determine the total estimated percent of the lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results shall not be included in the price adjustment calculations. If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment. The density test results for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s). Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0% and a contractor's risk of 5.0% unless otherwise specified. AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100% pay. The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained. The maximum pay factor obtainable is 1.05. The maximum pay factor for the largest sieve size specification for gradation will be 1.00. The price adjustment is based on the lowest of two pay factors. The first factor is a composite pay factor for asphalt concrete mixture which includes gradation and asphalt cement content. The second factor is a separate pay factor for density.

A lot containing material with less than a 1.00 pay factor, may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.

A lot containing material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11. The Contractor may submit a written request for acceptance of the material at a reduced price or approved correction. Such a request shall include an engineering analysis showing expected effects on performance. The Engineer will determine whether or not the material may remain in place at the reduced price.

The Engineer can reject material which appears to be defective based on visual inspection. Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis. Procedures for computation of composite pay factor are as follows:

1.	Eliminate test results found to be outliers by SP-7 (the Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ	= summation of

x=Σxn

x	= individual test value to xn

n	= total number of test values

x	is rounded to the nearest tenth for density and all sieve sizes except the 75 μm sieve. x is rounded to the nearest hundredth for asphalt cement content and the 75 μm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)	=	summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2	=	square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the 75 μm sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the 75 μm sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieve sizes except the 75 μm sieve. Use s = 0.020 for asphalt cement content and the 75 μm sieve.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL). For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2. The tolerances for the largest sieve specified will be plus 0% and minus 1%. The TV is the specification value defined by the Job Mix Design. The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

4.	Compute the Upper Quality Index (QU):

Where:	USL	= Upper Specification Limit

QU=USL-xs

QU	is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

QL=x-LSLs

Where:	LSL	= Lower Specification Limit

QL	is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 401-3.

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 401-3.

8.	Determine the Quality Level (the total percent within specification limits) for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, determine the lot Density Pay Factor (DPF) and gradation and asphalt cement content pay factors (PF) from Table 401-4.

10.	Compute the asphalt concrete mixture Composite Pay Factor (CPF) for asphalt content and gradation using the following formula:

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 401-5 is used to determine the weight factor (f) for each sieve size, and asphalt cement content.

Table 401-2

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

Measured Characteristics		LSL			USL

19.0 mm				TV-6.0		TV+6.0

12.5 mm				TV-6.0		TV+6.0

9.5 mm				TV-6.0		TV+6.0

4.75 mm				TV-6.0		TV+6.0

2.36 mm				TV-6.0		TV+6.0

1.18 mm				TV-5.0		TV+5.0

600 μm				TV-4.0		TV+4.0

300 μm				TV-4.0		TV+4.0

150 μm				TV-3.0		TV+3.0

75 μm					TV-2.0		TV+2.0

Asphalt %				TV-0.40		TV+0.40

Density				 92%			 98%

TABLE 401-3

Upper Quality Index (QU) or Lower Quality Index (QL)

| PU or PL | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 100 | 1.16-10.0 | 1.48-10.0 | 1.68-10.0 | 1.81-10.0 | 1.90-10.0 | 1.96-10.0 | 2.01-10.0 | 2.05-10.0 | 2.10-10.0 | 2.15-10.0 |
| 99 | - | 1.45-1.47 | 1.61-1.67 | 1.71-1.80 | 1.77-1.89 | 1.82-1.95 | 1.85-2.00 | 1.87-2.04 | 1.92-2.09 | 1.94-2.14 |
| 98 | 1.15 | 1.42-1.44 | 1.55-1.60 | 1.63-1.70 | 1.68-1.76 | 1.71-1.81 | 1.73-1.84 | 1.75-1.86 | 1.78-1.91 | 1.80-1.93 |
| 97 | - | 1.39-1.41 | 1.50-1.54 | 1.56-1.62 | 1.60-1.67 | 1.62-1.70 | 1.64-1.72 | 1.66-1.74 | 1.68-1.77 | 1.69-1.79 |
| 96 | 1.14 | 1.36-1.38 | 1.45-1.49 | 1.50-1.55 | 1.53-1.59 | 1.55-1.61 | 1.56-1.63 | 1.57-1.65 | 1.59-1.67 | 1.60-1.68 |
| 95 | - | 1.33-1.35 | 1.40-1.44 | 1.44-1.49 | 1.47-1.52 | 1.48-1.54 | 1.49-1.55 | 1.50-1.56 | 1.51-1.58 | 1.52-1.59 |
| 94 | 1.13 | 1.30-1.32 | 1.36-1.39 | 1.39-1.43 | 1.41-1.46 | 1.42-1.47 | 1.43-1.48 | 1.44-1.49 | 1.45-1.50 | 1.45-1.51 |
| 93 | - | 1.27-1.29 | 1.32-1.35 | 1.34-1.38 | 1.36-1.40 | 1.37-1.41 | 1.37-1.42 | 1.38-1.43 | 1.38-1.44 | 1.39-1.44 |
| 92 | 1.12 | 1.24-1.26 | 1.28-1.31 | 1.30-1.33 | 1.31-1.35 | 1.31-1.36 | 1.32-1.36 | 1.32-1.37 | 1.33-1.37 | 1.33-1.38 |
| 91 | 1.11 | 1.21-1.23 | 1.24-1.27 | 1.25-1.29 | 1.26-1.30 | 1.26-1.30 | 1.27-1.31 | 1.27-1.31 | 1.27-1.32 | 1.28-1.32 |
| 90 | 1.10 | 1.18-1.20 | 1.20-1.23 | 1.21-1.24 | 1.21-1.25 | 1.22-1.25 | 1.22-1.26 | 1.22-1.26 | 1.22-1.26 | 1.23-1.27 |
| 89 | 1.08-1.09 | 1.15-1.17 | 1.16-1.19 | 1.17-1.20 | 1.17-1.20 | 1.17-1.21 | 1.17-1.21 | 1.18-1.21 | 1.18-1.21 | 1.18-1.22 |
| 88 | 1.07 | 1.12-1.14 | 1.13-1.15 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.16 | 1.13-1.17 | 1.13-1.17 | 1.13-1.17 |
| 87 | 1.05-1.06 | 1.09-1.11 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.04 | 1.06-1.08 | 1.06-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.02-1.03 | 1.03-1.05 | 1.02-1.05 | 1.02-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 |
| 84 | 1.01 | 1.00-1.02 | 0.99-1.01 | 0.98-1.01 | 0.98-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 |
| 83 | 0.98-1.00 | 0.97-0.99 | 0.96-0.98 | 0.95-0.97 | 0.94-0.97 | 0.94-0.96 | 0.94-0.96 | 0.93-0.96 | 0.93-0.96 | 0.93-0.96 |
| 82 | 0.97 | 0.94-0.96 | 0.92-0.95 | 0.91-0.94 | 0.91-0.93 | 0.90-0.93 | 0.90-0.93 | 0.90-0.92 | 0.90-0.92 | 0.89-0.92 |
| 81 | 0.94-0.96 | 0.91-0.93 | 0.89-0.91 | 0.88-0.90 | 0.87-0.90 | 0.87-0.89 | 0.87-0.89 | 0.86-0.89 | 0.86-0.89 | 0.86-0.88 |
| 80 | 0.92-0.93 | 0.88-0.90 | 0.86-0.88 | 0.85-0.87 | 0.84-0.86 | 0.83-0.86 | 0.83-0.86 | 0.83-0.85 | 0.83-0.85 | 0.82-0.85 |
| 79 | 0.90-0.91 | 0.85-0.87 | 0.83-0.85 | 0.81-0.84 | 0.81-0.83 | 0.80-0.82 | 0.80-0.82 | 0.80-0.82 | 0.79-0.82 | 0.79-0.81 |
| 78 | 0.88-0.89 | 0.82-0.84 | 0.79-0.82 | 0.78-0.80 | 0.77-0.80 | 0.77-0.79 | 0.77-0.79 | 0.76-0.79 | 0.76-0.78 | 0.76-0.78 |
| 77 | 0.85-0.87 | 0.79-0.81 | 0.76-0.78 | 0.75-0.77 | 0.74-0.76 | 0.74-0.76 | 0.73-0.76 | 0.73-0.75 | 0.73-0.75 | 0.72-0.75 |
| 76 | 0.83-0.84 | 0.76-0.78 | 0.73-0.75 | 0.72-0.74 | 0.71-0.73 | 0.71-0.73 | 0.70-0.72 | 0.70-0.72 | 0.70-0.72 | 0.69-0.71 |
| 75 | 0.80-0.82 | 0.73-0.75 | 0.70-0.72 | 0.69-0.71 | 0.68-0.70 | 0.67-0.70 | 0.67-0.69 | 0.67-0.69 | 0.67-0.69 | 0.66-0.68 |
| 74 | 0.77-0.79 | 0.70-0.72 | 0.67-0.69 | 0.66-0.68 | 0.65-0.67 | 0.64-0.66 | 0.64-0.66 | 0.64-0.66 | 0.63-0.66 | 0.63-0.65 |
| 73 | 0.75-0.76 | 0.67-0.69 | 0.64-0.66 | 0.63-0.65 | 0.62-0.64 | 0.61-0.63 | 0.61-0.63 | 0.61-0.63 | 0.60-0.62 | 0.60-0.62 |
| 72 | 0.72-0.74 | 0.64-0.66 | 0.61-0.63 | 0.60-0.62 | 0.59-0.61 | 0.58-0.60 | 0.58-0.60 | 0.58-0.60 | 0.58-0.59 | 0.57-0.59 |
| 71 | 0.69-0.71 | 0.61-0.63 | 0.58-0.60 | 0.57-0.59 | 0.56-0.58 | 0.56-0.57 | 0.55-0.57 | 0.55-0.57 | 0.55-0.57 | 0.54-0.56 |
| 70 | 0.66-0.68 | 0.58-0.60 | 0.55-0.57 | 0.54-0.56 | 0.53-0.55 | 0.53-0.55 | 0.52-0.54 | 0.52-0.54 | 0.52-0.54 | 0.51-0.53 |
| 69 | 0.63-0.65 | 0.55-0.57 | 0.52-0.54 | 0.51-0.53 | 0.50-0.52 | 0.50-0.52 | 0.49-0.51 | 0.49-0.51 | 0.49-0.51 | 0.49-0.50 |
| 68 | 0.60-0.62 | 0.52-0.54 | 0.48-0.51 | 0.48-0.50 | 0.47-0.49 | 0.47-0.49 | 0.47-0.48 | 0.46-0.48 | 0.46-0.48 | 0.46-0.48 |
| 67 | 0.57-0.59 | 0.49-0.51 | 0.46-0.47 | 0.45-0.47 | 0.45-0.46 | 0.44-0.46 | 0.44-0.46 | 0.44-0.45 | 0.43-0.45 | 0.43-0.45 |
| 66 | 0.53-0.56 | 0.46-0.48 | 0.44-0.45 | 0.42-0.44 | 0.42-0.44 | 0.41-0.43 | 0.41-0.43 | 0.41-0.43 | 0.41-0.42 | 0.40-0.42 |
| 65 | 0.50-0.52 | 0.43-0.45 | 0.41-0.43 | 0.40-0.41 | 0.39-0.41 | 0.39-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.39 |
| 64 | 0.47-0.49 | 0.40-0.42 | 0.38-0.40 | 0.37-0.39 | 0.36-0.38 | 0.36-0.38 | 0.36-0.37 | 0.35-0.37 | 0.35-0.37 | 0.35-0.37 |
| 63 | 0.44-0.46 | 0.37-0.39 | 0.35-0.37 | 0.34-0.36 | 0.33-0.35 | 0.33-0.35 | 0.33-0.35 | 0.33-0.34 | 0.32-0.34 | 0.32-0.34 |
| 62 | 0.40-0.43 | 0.34-0.36 | 0.32-0.34 | 0.31-0.33 | 0.31-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.31 | 0.30-0.31 |
| 61 | 0.37-0.39 | 0.31-0.33 | 0.29-0.31 | 0.28-0.30 | 0.28-0.30 | 0.28-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 |
| 60 | 0.33-0.36 | 0.28-0.30 | 0.26-0.28 | 0.26-0.27 | 0.25-0.27 | 0.25-0.27 | 0.25-0.26 | 0.25-0.26 | 0.24-0.26 | 0.24-0.26 |
| 59 | 0.30-0.32 | 0.25-0.27 | 0.24-0.25 | 0.23-0.25 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.23 | 0.22-0.23 |
| 58 | 0.26-0.29 | 0.22-0.24 | 0.21-0.23 | 0.20-0.22 | 0.20-0.21 | 0.20-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 |
| 57 | 0.23-0.25 | 0.19-0.21 | 0.18-0.20 | 0.17-0.19 | 0.17-0.19 | 0.17-0.19 | 0.17-0.18 | 0.17-0.18 | 0.17-0.18 | 0.16-0.18 |
| 56 | 0.19-0.22 | 0.16-0.18 | 0.15-0.17 | 0.15-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.15 |
| 55 | 0.15-0.18 | 0.13-0.15 | 0.12-0.14 | 0.12-0.14 | 0.12-0.13 | 0.12-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 |
| 54 | 0.12-0.14 | 0.10-0.12 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 |
| 53 | 0.08-0.11 | 0.07-0.09 | 0.07-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.05-0.07 | 0.04-0.06 | 0.04-0.06 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.04 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

NOTE: For negative values of QU or QL, use absolute values of QU or QL. PU or PL is then equal to 100 minus the table value of PU or PL.

TABLE 401-4

Required Quality Level (QL) for a given sample size (n) and

a given Pay Factor (PF)

| Pay Factor | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.05 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 1.04 | 90-99 | 91-99 | 92-99 | 93-99 | 93-99 | 93-99 | 94-99 | 94-99 | 95-99 | 95-99 |
| 1.03 | 80-89 | 85-90 | 87-91 | 88-92 | 89-92 | 90-92 | 91-93 | 91-93 | 92-94 | 93-94 |
| 1.02 | 75-79 | 80-84 | 83-86 | 85-87 | 86-88 | 87-89 | 88-90 | 88-90 | 89-91 | 90-92 |
| 1.01 | 71-74 | 77-79 | 80-82 | 82-84 | 84-85 | 85-86 | 85-87 | 86-87 | 87-88 | 88-89 |
| 1.00 | 68-70 | 74-76 | 78-79 | 80-81 | 81-83 | 82-84 | 83-84 | 84-85 | 85-86 | 86-87 |
| 0.99 | 66-67 | 72-73 | 75-77 | 77-79 | 79-80 | 80-81 | 81-82 | 82-83 | 83-84 | 85 |
| 0.98 | 64-65 | 70-71 | 73-74 | 75-76 | 77-78 | 78-79 | 79-80 | 80-81 | 81-82 | 83-84 |
| 0.97 | 62-63 | 68-69 | 71-72 | 74 | 75-76 | 77 | 78 | 78-79 | 80 | 81-82 |
| 0.96 | 60-61 | 66-67 | 69-70 | 72-73 | 73-74 | 75-76 | 76-77 | 77 | 78-79 | 80 |
| 0.95 | 59 | 64-65 | 68 | 70-71 | 72 | 73-74 | 74-75 | 75-76 | 77 | 78-79 |
| 0.94 | 57-58 | 63 | 66-67 | 68-69 | 70-71 | 72 | 73 | 74 | 75-76 | 77 |
| 0.93 | 56 | 61-62 | 65 | 67 | 69 | 70-71 | 71-72 | 72-73 | 74 | 75-76 |
| 0.92 | 55 | 60 | 63-64 | 65-66 | 67-68 | 69 | 70 | 71 | 72-73 | 74 |
| 0.91 | 53-54 | 58-59 | 62 | 64 | 66 | 67-68 | 68-69 | 69-70 | 71 | 73 |
| 0.90 | 52 | 57 | 60-61 | 63 | 64-65 | 66 | 67 | 68 | 70 | 71-72 |
| 0.89 | 51 | 55-56 | 59 | 61-62 | 63 | 64-65 | 66 | 67 | 68-69 | 70 |
| 0.88 | 50 | 54 | 57-58 | 60 | 62 | 63 | 64-65 | 65-66 | 67 | 69 |
| 0.87 | 48-49 | 53 | 56 | 58-59 | 60-61 | 62 | 63 | 64 | 66 | 67-68 |
| 0.86 | 47 | 51-52 | 55 | 57 | 59 | 60-61 | 62 | 63 | 64-65 | 66 |
| 0.85 | 46 | 50 | 53-54 | 56 | 58 | 59 | 60-61 | 61-62 | 63 | 65 |
| 0.84 | 45 | 49 | 52 | 55 | 56-57 | 58 | 59 | 60 | 62 | 64 |
| 0.83 | 44 | 48 | 51 | 53-54 | 55 | 57 | 58 | 59 | 61 | 63 |
| 0.82 | 42-43 | 46-47 | 50 | 52 | 54 | 55-56 | 57 | 58 | 60 | 61-62 |
| 0.81 | 41 | 45 | 48-49 | 51 | 53 | 54 | 56 | 57 | 58-59 | 60 |
| 0.80 | 40 | 44 | 47 | 50 | 52 | 53 | 54-55 | 55-56 | 57 | 59 |
| 0.79 | 38-39 | 43 | 46 | 48-49 | 50-51 | 52 | 53 | 54 | 56 | 58 |
| 0.78 | 37 | 41-42 | 45 | 47 | 49 | 51 | 52 | 53 | 55 | 57 |
| 0.77 | 36 | 40 | 43-44 | 46 | 48 | 50 | 51 | 52 | 54 | 56 |
| 0.76 | 34-35 | 39 | 42 | 45 | 47 | 48-49 | 50 | 51 | 53 | 55 |
| 0.75 | 33 | 38 | 41 | 44 | 46 | 47 | 49 | 50 | 51-52 | 53-54 |
| 0 | 0-32 | 0-37 | 0-40 | 0-43 | 0-45 | 0-46 | 0-48 | 0-49 | 0-50 | 0-52 |

Table 401-5

WEIGHT FACTORS

Gradation				Factor "f"

19.0 mm sieve				4

12.5 mm sieve				4

9.5 mm sieve					4

4.75 mm sieve				4

2.36 mm sieve				4

1.18 mm sieve				5

600 μm sieve					5

300 μm sieve					5

150 μm sieve					5

75 μm sieve					20

Asphalt %					40

401-5.01 BASIS OF PAYMENT. The accepted quantity will be paid for at the contract unit price for the pay item listed below, complete in place.

Tack coat will be subsidiary to asphalt cement unless specified as a pay item.

A change order/directive is not required for anti-stripping additive pay item. The approved mix design will initiate Item 401(4), Anti-Stripping Additive at the prescribed rate.

Anti-stripping additives will be paid on a contingent sum basis at a rate of $4.95 per .25 percent additive per megagram of asphalt cement.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot and added to the Contractor's payment for Asphalt Concrete. The fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 401-2.01 will be subtracted from the Contractor's payment. The price adjustment will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value. A change order/directive is not required for the asphalt price adjustment pay item. The price adjustment for each individual lot shall be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $33.00/Megagram

* Composite Pay Factor (CPF) or Density Pay Factor (DPF) whichever is lower value.

Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $0.25 per meter. The accrued amount will be deducted under Item 401(5) Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-6 and applied under Item 401(5) Asphalt Price Adjustment.

TABLE 401-6

| Average Profile Index (PrI) (Millimeters per 1000 Lane Meters) | Adjustment to Item 401(5) Asphalt Price Adjustment for pavement smoothness |
| --- | --- |
| 0 to 60 | Add $335 multiplied by (61-PrI) |
| 61 to 94 | No Adjustment |
| 95 and greater | Deduct $335 multiplied by (PrI-94) but not to exceed $10,000 |

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1)	Asphalt Concrete Pavement, Type___, Class ___	Megagram

401(2)	___ Asphalt Cement	Megagram

401(4)	Anti-Stripping Additive	Contingent Sum

401(5)	Asphalt Price Adjustment	Contingent Sum

401(6)	Temporary Pavement	Megagram

Separate payment will not be made for asphalt cement, or anti-strip additives for Item 401(6), Temporary Pavement; or asphalt concrete for leveling course. Price adjustments will also not apply to Item 401(6), Temporary Pavement; asphalt concrete for leveling course; or Item 401(1), Asphalt Concrete Pavement, when total quantities are less than 4,500 Megagrams except as defined in Subsection 401-4.02.

(12/17/98)R199M

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-2.01 MATERIALS. Add the following: Reinforcing steel shall conform to

the requirements of Section 503.

501-3.01 PROPORTIONING. Revise this subsection as follows: In Table 501-1, Class of Concrete, under the category Coarse Aggregate Gradation AASHTO M43, provide either the No. 57 or the No. 67 gradation for Class A, S, W and A-A concrete.

Add the following to subparagraph 4: Fly ash may be used only in the abutments of the Eska Creek Bridge. Fly ash shall not be used in the girders on this project.

501-3.02 BATCHING. Add the following to item No. 5. Batching: Furnish the mix design number and a list of all ingredients, their individual weights, moisture contents of the various aggregates and the individual truck water meter reading when batched, with each truck load or batch of concrete supplied.

501-3.06 PLACING CONCRETE. Replace the last sentence of Item 2. Pumping Concrete, with the following: Concrete samples for testing shall be taken at the discharge end of the pipe. The Contractor shall provide the necessary samples of concrete as directed.

Under Item 10. Setting Shoes and Bearing Plates, add the following: Unless otherwise shown on the plans, pier and abutment caps on bridges shall be finished parallel to the roadway grade and parallel to the roadway cross slope or crown. Grade strips on each side of the caps shall be independently set and the grade at the centerline of the bearings shall be carefully checked prior to casting the concrete.

SECTION 502

PRESTRESSED CONCRETE STRUCTURES

Special Provisions

502-2.01 Materials. Add the following: Grout for keyways between adjacent concrete members shall be a non-shrink, non-corrosive, non-metallic, cement-based grout conforming to ASTM C107, Grade C. The grout shall develop a 28 day compressive strength of 62 MPa minimum, when tested in conformance with ASTM C109. The grout shall meet the requirements of Alaska Test Method T-30.

502 3.04 PLACING. Delete paragraphs three and four and substitute the following: When the plans provide for keyways between adjacent concrete members to be filled with grout, the grout shall be placed according to the manufacturer's written instructions. Unless recommended otherwise by the manufacturer, the grout shall be mixed to a "plastic" consistency for placement in the keyways.

Add the following to the sixth paragraph: The grout shall be packed and rodded into the keyways to form a dense, impermeable filling. The dry consistency of the grout tends to result in a porous filling, so additional compaction effort will be needed to achieve the required density. The grout surface shall be smooth and neat in appearance. The grout surface shall meet the girder edges throughout their lengths, and shall match the elevation of the surface of the girders with a tolerance of 3 mm. Patching and grinding may be required.

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01 DESCRIPTION. Add the following: This work will include the epoxy coating of appropriate reinforcing steel bars. All reinforcing steel in precast concrete girders, concrete curbs and other locations as noted on the plans, shall be epoxy coated.

SECTION 504

STEEL STRUCTURES

Special Provisions

504-3.02 ERECTION. Under Item 8. Setting Shoes and Bearings, add the following: Epoxy adhesive, conforming to AASHTO M-200, shall be applied to the bottom surface of the elastomeric bearing pads prior to placement, and the pad shall be secured and restrained from movement until the epoxy has cured and full adhesion is achieved between the pad and the concrete.

SECTION 505

PILING

Special Provisions

505-1.01 DESCRIPTION. Delete the first sentence in the second paragraph and substitute the following: The Contractor shall be responsible for furnishing piles of sufficient length to obtain the required ultimate bearing capacity, extend to the estimated pile tip elevation shown on the plans, and penetrate to the pile driving criteria as described below.

505-3.03 PILE BEARING VALUES. Delete this subsection in its entirety and substitute the following: All piles shall be driven to a required ultimate bearing capacity. The required ultimate bearing capacity is the design pile load as indicated on the bridge plans multiplied by a factor of safety of 2.75 at Bridge No. 542. The pile driving criteria shall be determined by the Engineer using a wave equation analysis.

505-3.07 EXTENSIONS, SPLICES AND BUILDUPS. Add the following: All welding shall be performed in accordance with AWS Dl.1-96, Structural Welding Code-Steel. At least 30 calendar days prior to any field welding on the piles, the Contractor shall submit to the Engineer for review and approval, all pile field welding specifications and details, and the welder(s) qualification test record with results. The field welding quality control will be performed by the Contractor as specified in AWS Dl.1-96. Visual welding inspection and quality assurance welding testing shall be performed by the Engineer as specified in AWS Dl.1-96. For the Engineer's quality assurance inspection, fillet welds shall be inspected by magnetic particle and full penetration welds shall be inspected by Nondestructive methods of radiography and/or ultrasonics. The percentage of welding to be nondestructive tested shall be established by the Engineer based on the visual inspection of the Contractor's welding. If necessary, weld repair shall be performed as directed by the Engineer. The recommended submittal forms for the Welding Procedure Specification and Welder Qualification Test Record are found in AWS Dl.1-96 or can be furnished by the Engineer.

505-3.09 DRIVING PILES In the first paragraph, fifth sentence, change "13 mm" to "25 mm."

Delete the tenth paragraph and substitute the following: All pile driving equipment used by the Contractor shall be subject to approval by the Engineer. All pile driving systems shall be equipped with an appropriate thickness of hammer cushion to prevent damage to the hammer or pile and to insure uniform driving performance. Hammer cushions shall be made of durable, manufactured materials, and provided in accordance with the hammer manufacturer's guidelines except that wood, wire rope, and asbestos hammer cushions shall not be used. The hammer cushion shall be inspected in the presence of the Engineer prior to beginning pile driving and after each 50 hours of pile driving on this project. Any reduction of hammer cushion thickness exceeding 25% of the original thickness shall be replaced by the Contractor before driving is permitted to continue.

The pile driving equipment shall be sized such that the piles can be driven to the required ultimate bearing capacity without damage. Approval of the pile driving equipment will be based on the wave equation and the Engineer's recommendations.

All piles shall be driven at least to the desirable tip elevation as shown in the bridge plans or to a tip elevation based on the wave equation and the Engineer's recommendations. Piles not achieving the required ultimate bearing capacity within the limits of the tip elevations shown on the bridge plans shall be driven to a tip elevation established by the Engineer.

At least thirty calendar days prior to driving the first pile, the Contractor shall submit pile driving equipment information on the "Pile Driving Equipment Data Form" provided by the Engineer. Approval of the pile driving equipment will be based on a wave equation analysis.

The Contractor shall use the approved driving system to install the piles. No variations in the driving system will be permitted without the Engineer's written approval. Any change in the driving system will only be considered after the Contractor has submitted a revised Pile Driving Equipment Data Form for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result. The Contractor will be notified of the acceptance or rejection of the revised driving system within 7 calendar days of the Engineer's receipt of the requested change. The time required for submission, review and approval of a revised driving system shall not constitute the basis for a contract time extension.

For the pile driving system to be acceptable, the compressive driving stresses as indicated by the wave equation analysis shall not exceed 90% of the pile yield stress.

Add the following to the eleventh paragraph: It is anticipated that the Contractor will encounter cobbles and/or boulders during pile driving at this site. The Contractor is advised to have adequate size and type of equipment such as an excavator,. drilling equipment, boulder extractor, and/or boulder rooter to assist in advancing the piles down through the cobbles and/or boulders to the required pile tip elevation and the specified bearing capacity without damage to the piles.

505-4.01 METHOD OF MEASUREMENT. Delete numbered paragraph 6. and substitute the following:

6.	Piles not achieving the required ultimate bearing capacity within 1.5 m (below) the estimated pile tip elevation shown on the plans shall be driven to a penetration established by the Engineer. Requirement to drive the piles more than 1.5 m deeper than the estimated pile tip elevations shown on the plans shall be at the written direction of the Engineer. For depths up to 3 m below the estimated pile tip elevations, the contract bid price for piling shall be applied. For depths beyond 3 m below the estimated pile tip elevations, the pile unit costs shall be determined as per Section 109.

SECTION 507

BRIDGE RAILING

Special Provisions

507-4.01 METHOD OF MEASUREMENT. Add the following: For the Eska Creek Bridge Number 542, metal bridge railing shall include structural steel; railing expansion joints; hardware; installation of two bridge number plates; baseplate grout; curb concrete, curb drains and associated reinforcing steel.

Delete this Section in its entirety and substitute the following:

SECTION 508

MEMBRANE WATERPROOFING

Special Provisions

508-1.01 DESCRIPTION. This work consists of furnishing and installing preformed waterproofing membrane on concrete bridge decks as specified.

508-2.01 MATERIALS.

1.	Membrane Material. Membranes for bridge deck waterproofing shall be a manufactured type membrane as specified herein. The material shall consist of a cold-applied, self-adhering membrane incorporating a non-woven geotextile embedded between 2 layers of SBS modified asphalt, a primer, and a mastic. The membrane shall have a top layer of non-structural non-woven geotextile for protection against construction traffic. The sheet membrane shall have the following properties:

| Property | Test Method | Specific Value |
| --- | --- | --- |
| Tensile Strength (kPa) | ASTM D 412 Modified Method A | 345 |
| Elongation (percent) | ASTM D 412 Modified Method A | 60 min. |
| Thickness (mm) | ASTM D 1777 | 1.5 min. |
| Puncture Resistance (kg) | ASTM E 154 | 11 min. |
| Permeance (perms) (g/Pa·s·m²) | ASTM E 96B | 2.87 max |
| Pliability | ASTM D 146 | No cracks bent 180 around 6 mm mandrel at -32C |
| Asphalt Concrete Mat Surface Compaction Temperature (C) | None | 120 |

2.	Overlay Material. Material requirements for pavement overlays on waterproof membranes shall conform to those specified in Section 401.

CONSTRUCTION REQUIREMENTS

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING.

1.	General. Membrane shall be installed in a manner to assure the following results:

a.	A complete bond between the membrane and the concrete surface of deck and curb face.

b.	An unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay.

c.	A complete bond between the membrane and the asphalt overlay.

The membranes shall be installed under the supervision of a representative from the membrane manufacturing company and in accordance with the manufacturer's published instructions.

2.	Preparation of Concrete Deck. All concrete surfaces including grout in girder keyways to receive membranes shall have attained a compressive strength of not less than 80 percent of the specified 28 day compressive strength (f'c) prior to application of the membrane. The entire deck shall be free of all foreign materials such as dirt, dust, moisture, loose concrete, etc. Prior to applying the membrane primer, all dust and loose materials shall be removed from the deck by power sweeping followed by a thorough cleaning with compressed air. Any sharp concrete edges on the deck surface which would puncture the membrane shall be corrected in a satisfactory manner prior to application of the membrane. Grease, oil, paint, etc., shall be removed with solvents, detergents or sand blasting on decks that are to receive manufactured membranes.

Additional power sweeping, vacuuming, compressed air cleaning, or hand brooming shall be performed immediately before applying the primer if deemed necessary by the Engineer or Manufacturer's representative.

3.	Weather and Moisture Limitations. Work shall not be done during wet weather conditions, nor when the deck and ambient air temperatures are below 4 C.

4.	Overlaying and Protection of Membrane. The asphalt overlay shall not be placed until the bond between the concrete deck and the membrane has fully developed. Vehicles, except the spreader and trucks used for hauling the asphalt overlay mix, shall not be operated on the membrane.

Paving machines used over the membrane shall be rubber tired or rubber tracked. Steel-wheeled rollers only shall be used to compact the asphalt paving on the bridge decks.

The asphalt shall be placed, spread, and rolled in such a manner that the membrane will not be damaged. The Contractor shall adhere to the manufacturer's published instructions for preparation, laydown, compaction, minimum and maximum temperature limitations for asphalt overlay material. The use of vibratory rollers, with vibrator on, will not be permitted.

508-4.01 METHOD OF MEASUREMENT. Membrane will not be measured for payment.

All materials for the asphalt overlay will be included in the measurements of quantities for the appropriate paving items.

No adjustments will be made in the quantities or prices of materials for asphalt overlay because of any variations resulting from utilizing waterproof membranes of greater or lesser thickness.

508-5.01 BASIS OF PAYMENT. Membrane Waterproofing will be paid for at the contract lump sum price. Payment shall also include all costs of furnishing and installing primers.

Payment for the asphalt overlay will be made under the appropriate paving items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

508(1)	Membrane Waterproofing	Lump Sum

(7/23/98)R172M

SECTION 601

METAL FLUME DOWNDRAINS

Special Provisions

601-3.01 CONSTRUCTION REQUIREMENTS. Add the following: This work shall consist of installation of new metal flume downdrain inlets to match the batter board flow line as shown on the plans.

601-5.01 BASIS OF PAYMENT. Add the following: Metal flume downdrain inlets shall be subsidiary to Item 606(1) W-Beam Guardrail.

R124M

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS. Add the following: Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 95 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm.

(11/04/94)R42M

603-3.04 JOINING PIPE. Delete the last sentence of numbered paragraph 1., and substitute the following: Bands for pipe with diameters greater than 760 mm shall have a minimum width of 1.2 m. (10/1/91)R125M

603-3.06 CULVERT MARKER POSTS. Add the following subsection: Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(11/04/94)R42M

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Drain Manhole, Type I	Each

R43M

SECTION 606

GUARDRAIL

Special Provisions

606-1.01 DESCRIPTION. Add the following: This work shall also consist of installing batter boards and slotted rail terminals at the locations shown on the plans. (7/24/96)R45aM

This work shall also consist of installing guardrail/bridgerail connections at the locations shown on the plans. (10/1/91)R126

606-2.01 MATERIALS. Add the following: Slotted Rail Terminals shall be SRT-350's manufactured by Syro, Inc., Western Division, P.O. Box 99, Centerville, Utah 84014. Telephone 801-292-4461.

Flexible markers shall have yellow reflective sheeting and be one of the following types or equivalent:

1.	"Guardrail Delineator Post" manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevada 89701.

2.	"Guardrail Delineator" manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

3.	"Flex-o-Guide", Model EY426 manufactured by Flexible Safety Zoning Company, 4152 Warren Avenue, Hillside, Illinois 60162.

Batter board shall consist of nominal 50 x 200 millimeter treated lumber. It shall be of a timber stress grade of 8,275 kiloPascals or more in accordance with the American Institute of Timber Construction. Timber shall be treated in accordance with Section 714. AC-5 asphalt cement shall conform to the requirements of Section 702, Asphalt Materials. Cover coat material shall meet the requirements of Table 703-5, Grading D, E, F or G.

606-3.01 POSTS. Add the following: Posts for slotted rail terminals shall be installed per the manufacturer's recommendations. All guardrail posts, wood or steel, shall be 2.2 meters in length.

606-3.02 RAIL ELEMENTS. Add the following: Guardrail elements shall be factory bent for all radii less than 25 meter. Rail elements for slotted rail terminals shall be installed per the manufacturer's recommendations.

606-3.03 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail located within 15 meters of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.06 FLEXIBLE MARKERS. Add the following subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer. The flexible markers shall have a minimum of 530 millimeters of marker extending above the top of the guardrail. The reflective tape shall face the nearest oncoming traffic.

606-3.07 EMBANKMENT WIDENING. Add the following subsection: Embankment widening for guardrail end treatments shall be constructed of selected material, Type A in accordance with Section 203.

606-3.08 LENGTH OF NEED VERIFICATION. Add the following subsection: After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends. The staked location of the guardrail will be approved by the Engineer prior to installation. The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.

Add the following subsection:

606-3.09 BATTER BOARDS. After installation, roadside face of batter boards shall be coated with AC-5 asphalt cement and covered with cover coat material.

606-4.01 METHOD OF MEASUREMENT. Delete the first sentence and substitute the following: W-Beam and Thrie Beam guardrail will be measured by length in meters by multiplying the number of panels by 3.81 meters.

Delete the third paragraph and replace with the following: Item 606(27), Slotted Rail Terminal, will be measured per each completed installation which shall include all labor, equipment and materials. Materials for the slotted rail terminals include the anchor cable assembly, terminal posts, terminal end, rail elements, posts and blocking, flexible marker, and all associated hardware necessary to install the terminal. These items will not be measured for payment. The end of the slotted rail terminal and the beginning of W-beam guardrail will be as shown on the manufacturer's drawings.

Add the following: Guardrail/bridge-rail connections shall be measured per each installation which shall include a section of nested thrie beam guardrail, thrie beam to standard W-beam transition, thrie beam transition bracket, posts and all associated hardware. (10/1/91)R126

Batter boards, AC-5 asphalt cement coating, and cover coat material will not be measured for payment.

606-5.01 BASIS OF PAYMENT. Add the following: Selected material, Type A will be measured and paid in accordance with Section 203.

Batter boards , AC-5 asphalt cement, and cover coat material will not be paid for directly, but will be subsidiary to Item 606(1), W-Beam Guardrail.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

606(12)	Guardrail/Bridgerail Connection	Each

606(27)	Slotted Rail Terminal	Each

(7/24/96)R45aM

SECTION 608

SIDEWALKS

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work shall also consist of construction of asphalt pathway as shown on the plans.

608-2.01 MATERIALS. Add the following: AC-5 asphalt cement shall be used for the asphalt concrete pavement mix for asphalt pathways and shall conform to the requirements of subsection 702-2.01 Asphalt Cements. Aggregate shall meet the gradation requirements of subsection 703-2.04 Aggregate for Plant Mix Asphalt Pavement, for Asphalt Concrete Pavement Type II. In addition, the asphalt concrete shall conform to the following:

Marshall Stability, Newtons, minimum		4500 N

Voids, Total Mix, percent				3-5 %

Compaction Blows per Side				50

608-3.02 ASPHALT SIDEWALKS. Add the following: Asphalt pathways shall be constructed in accordance with this subsection.

608-4.01 METHOD OF MEASUREMENT. Add the following: Asphalt pathways will be measured by the megagram in accordance with Section 109, Measurement and Payment. Asphalt cement will not be measured for payment.

Additional asphalt pavement used for matching existing surfaces such as approaches behind a new pathway will be measured and paid under this Section.

608-4.01 METHOD OF MEASUREMENT. Add the following: Asphalt concrete for pathway paving will be measured by the megagram in accordance with Section 109, Measurement and Payment. Asphalt cement and anti-stripping additive will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement and anti-stripping additive will not be paid for separately, but will be subsidiary to Item 608(8), Asphalt Pathway. Bed course materials, as detailed on the plans, will be furnished, placed and paid under their respective bid items.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

608(8)	Asphalt Pathway	Megagram

SECTION 611

RIPRAP

Special Provision

611-5.01 BASIS OF PAYMENT. Delete the third paragraph and substitute the following: Excavation at Eska Creek shall be paid under Item 203(3) Unclassified Excavation. Excavation at other riprap locations shall be subsidiary to Item 611(1) Riprap, Class II.

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS. Change all Type III-A reflective sheeting to Type III reflective sheeting.

Add the following to the end of the first sentence of the fifth paragraph: "the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual."

Add the following: Wide flange posts shall also be hinged and equipped with the multi-directional breakaway load concentration coupler hinge plates.

615-3.01 CONSTRUCTION REQUIREMENTS. Add the following to the sixth paragraph: When existing signs are to be salvaged, the remaining foundation shall be removed, abandoned in place, or if located within the roadway structural section shall be disposed of in a manner as approved by the Engineer. If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

Add the following after the sixth paragraph: Salvaged sign panels shall be delivered to the State Maintenance Yard at 289 Springer Loop, Palmer, Alaska.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Existing signs shall not be removed without authorization from the Engineer. They shall be kept in service until either the new signs have been installed, or they are no longer needed. As the work progresses, if their locations do not conform to Standard Drawing S-05.00[M], they shall be reinstalled at locations approved by the Engineer.

Prior to mounting the sign panel, the Contractor shall mark the date of installation on the back of the sign. Installation dates shall be written in the format of month/day/year, using black permanent marker, with numbers a minimum of 75 mm in height, so as to be readable from the roadside after installation.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases will be considered subsidiary to other work under this section and will not be measured for payment.

615-5.01 BASIS OF PAYMENT. Add the following: Payment for keeping existing signs in service until they are no longer needed, or temporarily relocating existing signs, will not be paid for directly, but will be subsidiary to Item 615(1), Standard Signs.

Payment for removal of existing sign post foundations, or work required to abandon them in place, shall be included in Item 615(7), Salvage Signs.

(10/12/98)R50M

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION. Delete this subsection and substitute the following: All areas shown on the plans, and any other areas directed by the Engineer, shall be overlaid with topsoil and seeded. This work shall consist of tracking the soil, followed by the two step application of seed and mulch tracer, immediately followed by an application of mulch, fertilizer and water. It is intended to provide a living ground cover as soon as possible on all slopes and provide good ground seed contact.

The areas designated as Experimental Slope Stabilization shall not receive topsoil but shall be tracked with a dozer as described below, and stabilized as detailed in Section 628.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Seed shall be applied as detailed below immediately after the shaping of the slopes. All slopes to be seeded, except the Experimental Slope Stabilization, shall be covered with topsoil in accordance with Section 620 and prepared by "walking" a dozer transversely up and down the slopes, or graded with a scarifying slope board. The resultant indentations shall be perpendicular to the fall of the slope. This should be completed as soon as topsoil is placed on the slopes. The Contractor may round the top and bottom of the slopes to facilitate tracking and to create a pleasing appearance, but drainage flow lines shall not be disrupted. Where the fill is adjacent to wetlands, the equipment performing this operation must be kept entirely on the fill slope and must not encroach on the wetlands.

618-3.03 APPLICATION METHOD. Delete the first sentence of subparagraph a., under numbered paragraph 1. and substitute the following: Apply seed, mulch and fertilizer at the rates specified. Use the method below when applying Seed Mix Types A and B. Use methods specified in Section 628 when applying Seed Mix, Type C.

1.	Hydraulic Method Two Step Application.

a.	First Application: Furnish and place slurry of seed, fertilizer, and water at the following application rate. Dyed mulch shall be added at a quantity sufficient to provide a visible tracer.

b.	Second application: Furnish and place slurry of mulch, water and other components as required. This shall be hydraulically applied immediately following the first application of seed and water with tracer.

Seed, mulch and fertilizer shall be applied as follows per hectare (ha) in a two step application. All fertilizer shall be applied by hydraulic methods.

In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following: "and/or limestone, Item 618(4),".

| Item | Ingredients | Application Rate (per ha) |
| --- | --- | --- |
| Seed Mix, Type A | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total=49.0 kg |
| Mulch | -- | 1710 kg |
| Fertilizer | 20-20-10 | 586 kg |
| Seed Mix, Type B | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) Ox Eye Daisy (Chrysanthemum Leucanthemum) Iceland Poppy (Papaver nudicaule) Lupine Nootkatensis | 29.0 kg 15.0 kg 5.0 kg 2.0 kg 2.0 kg 2.0 kg 55.0 kg |
| Mulch | -- | 1710 kg |
| Fertilizer | 20-20-10 | 586 kg |
| Seed Mix, Type C | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 36.0 kg 28.7 kg 7.3 kg Total=72.0 kg |
| Fertilizer | 20-20-10 | 586 kg |

The Contractor shall not remove the required tags from the seed bags.

618-3.04 MAINTENANCE OF SEEDED AREAS. Add the following: A reapplication of fertilizer shall be applied with water between May 1 and September 15 of the year following seeding at a rate of one-half the initial application.

At least two waterings shall be done in the second growing season, at least one week apart and one week after fertilization, between May 15th and July 1st.

618-4.01 METHOD OF MEASUREMENT. Delete the second paragraph and substitute the following: Seeding by the kilogram will be the number of kilograms of seed (dry measure) accepted in place. The amount of fertilizer, mulch and water for application used in this work, including any required reseeding, will be subsidiary to this item and will not be measured separately for payment.

Delete the third paragraph and substitute the following: Water used in maintenance of seeded areas will be measured by the kiloliter, by means of calibrated tanks or distributors, accurate water meters or by weighing. The conversion factor of 1.00 kilogram per liter will be used in converting weights to liters.

Delete the last paragraph.

618-5.01 BASIS OF PAYMENT. Add the following after the first paragraph: Fertilizer, mulch and water for application, including any required reseeding, will not be paid for directly, but will be subsidiary to seeding.

The work described under subsection 618-3.01 Soil Preparation will not be paid for directly but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

(5/21/97)R52M

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

618(2A)	Seeding, Type A	Kilogram

618(2B)	Seeding, Type B	Kilogram

SECTION 619

SOIL STABILIZATION

Special Provisions

619-1.01 DESCRIPTION. Add the following: This work also includes the furnishing, application and maintenance of hydraulically applied soil stabilization matting.

619-2.01 MATERIALS. Add the following to the first paragraph:

Hydro Matting			727-2.04

Add the following: Hydraulically applied soil stabilization matting shall contain the seed and fertilizer specified in Section 618, Seeding. It shall be applied at the rate of 3,360 kg/ha or in accordance with the manufacturer's written recommendations and application parameters. Where hydro matting is required by the plans on 1V:1½H cut or fill slopes 6 meters or more in height, the slopes shall be stabilized as the faces are exposed, as practical, in accordance with the NPDES Storm Water Pollution Prevention Plan.

Slopes with lateral seeps shall be allowed to dry before treating with hydro matting. Treatment of such areas may be deferred until the end of slope finishing unless there is a risk of a major failure. In such event, the Engineer will direct repairs to be made by redressing and hydro matting, by rock buttressing, or by other means in accordance with Section 641.

619-3.-1 SURFACE PREPARATION. Add the following: The surface shall be tracked as required in Section 618.

619-3.02 APPLICATION. Add the following: Seed shall be applied using the hydraulic method two step application process described in Section 618. Hydro matting shall be substituted for mulch in step 2 of the two step application process.

619-3.03 MAINTENANCE AND REPAIR. Add the following: Hydraulically applied soil stabilization matting shall be maintained and repaired in accordance with the manufacturer's written recommendations and subsection 618-3.04, Maintenance of Seeded Areas, or as directed by the Engineer.

619-4.01 METHOD OF MEASUREMENT. Add the following: The unit price for Item 619(3), Hydro Matting, shall include seed and fertilizer at application rates specified in Section 618.

619-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

619(3)	Hydro Matting	Square Meter

Add the following: There shall be no adjustment to price in the event that weather, soil conditions or other conditions preclude the use of hydro matting.

R223M

Add the following section:

SECTION 628

EXPERIMENTAL SLOPE STABILIZATION

Special Provisions

628-1.01 DESCRIPTION. This work shall consist of installing experimental slope stabilization treatments on a series of test plots in conformance with the plans. The slope and benches shall be covered with plastic sheeting as the excavation progresses for erosion protection. The experimental slope stabilization shall be installed during the second construction season.

628-2.01 MATERIALS.

HYDRO MULCHES

Hydro mulch products shall be Astromulch and EcoFiber.

BONDED FIBER MATRICES

Bonded fiber matrix (BFM) products shall be Soil Guard, EcoAegis, Hydro-Blanket, and Fibriform.

ROLLED MATTING

Items 628(9A) and 628(9B) Rolled Straw/Coir blends and Item 628(10) Rolled Jute, require wire staples to hold materials in place. Staples shall be 150 mm long.

Item 628(11A) and 628(11B) Rolled Coir with Biod blends shall be installed with wire staples 200 mm long, 11 gage or stronger. If the option of wooden pegs is chosen, pegs shall be a minimum of 300 mm long.

BIO-ENGINEERED METHODS

Dormant cuttings for Item 628(12)Brush Layered Benches, Item 628(13)Straw Roll with Live Stakes, and Item 628(14)Wattles, shall be harvested from living woody plants. Prepare the cuttings from branches of woody plants when the plant is in a dormant state. Collect cuttings that can easily be rooted without special treatment. Use plant species from the following table for the uses indicated:

| COMMON NAME | SCIENTIFIC NAME | ACCEPTABLE USES * |
| --- | --- | --- |
| Balsam poplar (cottonwood) | Populus trichocarpa P. balsamifera | LS, W, BL |
| Barclay willow | Salix barclayi | W, BL |
| Feltleaf willow | Salix alaxensis | LS, W, BL |
| Pacific willow | Salix lasiandra | LS, W, BL |
| Little tree willow | Salix arbusculoides | LS, W, BL |
| Diamond leaf willow | Salix planifolia, ssp. pulchra | LS, W, BL |

*	LS = Live stakes

W = Wattles

BL = Brush Layers

Buds must be present on the cuttings, particularly near the top of each cutting. Avoid flower buds (“pussy willows”) if possible.

Collect cuttings during winter/early spring before leaves appear for spring and early summer plantings. Plants shall be collected within a 160 kilometer (100 mile) radius of the project limits. Cuttings may be obtained from State Public Lands and the Department of Transportation Right of Way. The Contractor shall obtain the appropriate permits prior to removing the cuttings.

Cuttings shall be 10-50 mm diameter at the cut end. Leave as long as possible, at least 1 meter in length. Cut branches to required length at the time of installation.

Maintain viable cuttings with proper storage. Freeze or refrigerate until installation if collection occurs while daytime temperatures remain below 0.5 C. Refrigerate cuttings if the daytime temperature exceeds 0.5C. Frozen cuttings can be stored with a small amount of snow to reduce drying. Store refrigerated cuttings at 0.5 C to 5C and 60 to 70 percent humidity. Monitor the condition of the cuttings regularly to detect problems such as desiccation, sprouting or mold. Cuttings remain viable for only one season.

Take cuttings directly from storage to the planting site. Remove only that amount of material from storage that can be planted that day, particularly if windy or warm weather conditions exist. Store cuttings away from direct sunlight, heeled into moist soil or stored in water until planting.

Item 628(13) Straw Roll with Live Stakes requires straw wrapped in tubular plastic netting.

SEED

Seed shall meet the requirements of Seed Mix, Type C as described in Section 618. J-Tack tackifier shall be used on all seeded areas. The amount of tackifier added will be as recommended by the manufacturer.

PLASTIC SHEETING

Plastic sheeting shall be a minimum 10 mils reinforced.

628-2.02 SOURCES.

Items 628(1A) and 628(1B) Astromulch and 628(8) Fibriform are manufactured by:

ThermoKool Alaska Inc.

6348 Quinhagak

Anchorage, Alaska 99502

(907) 563-3644

FAX (907) 561-2758

Items 628(2A) and 628(2B) EcoFiber; Item 628(6) EcoAegis, and J-Tack tackifier, are manufactured by Canfor Corp. For questions and consultations contact:

Fiber Marketing International Inc.

4311 NE Sunset Blvd.

Renton, WA. 98059

(206) 277-9966

(800) 426-6002

FAX (206) 277-9971

Websites: www.canfor.com, and www.canforpfd.com

Compost for Item 628(4) Compost Blend, is available from:

Anchorage Regional Compost Facility

Point Woronzof Drive

Anchorage, AK

(907) 243-8577

Contact: John Dean

Item 628(5) Soil Guard, is produced by Mat, Inc. For further information contact:

Ron Perez

Sales and Marketing

Mat, Inc.

12402 Highway 2

Floodwood, MN. 55736

(888) 477-3028

FAX (218) 476-2039

Item 628(7) Hydro-Blanket, is manufactured by Wood Recycling, Inc. For further information and consultation contact:

Wood Recycling, Inc.

3 Wheeling Avenue

Woburn, MA. 01801

(800) 982-8732

FAX (781) 932-0945

Website: www.woodrecycling.com

Item 628(9A) Rolled Straw/Coir Blend with SC150, and Item 628(9B) Rolled Straw/Coir Blend with SC150BN, are produced by North American Green. For further information and consultation contact:

North American Green

14649 Highway 41 North

Evansville, Indiana 47711

(800) 772-2041

FAX (812) 867-0247

Website: www.nagreen.com

Item 628(10) Rolled Jute, shall be Anti-wash/Geojute manufactured by Belton Industries, Inc. For further information contact:

Belton Industries

8613 Roswell Road #200

Atlanta, GA 30350

(800) 225-4099

Item 628(11A) Rolled Coir with Biod-SCF 30, and Item 628(11B) Rolled Coir with Biod-OCF 30, are manufactured by RoLanka International, Inc. For further information and consultation contact:

RoLanka International, Inc.

365 Toccoa Place

Jonesboro, Ga 30236

(800) 760-3215

FAX (770) 506-8211

E-mail: rolanka@rolanka.com

Website: www.rolanka.com

Straw rolls for Item 628(13) Straw Roll with Live Stakes, shall be straw wattles manufactured by California Straw Works. For further information contact:

California Straw Works

Phone/FAX (916) 453-1456

Website: www.strawwattles.com

Consultation concerning acceptable Bio-Engineered techniques can be directed to:

Nancy Moore

Plant Material Specialist

Plant Materials Center

Palmer Alaska

Phone (907) 745-4469

Provide Engineer and Plant Material Specialist 72 hours advance notice of plant material harvesting and installation.

628-3.01 CONSTRUCTION. Plastic sheeting shall be installed so that no more than 8 vertical meters shall be exposed at any time. This plastic sheeting shall be installed and maintained in accordance with the approved SWPPP and Section 641 until replacement with the experimental slope stabilization methods.

Plastic sheeting shall be installed as follows:

Start at the top of the slope by anchoring the plastic sheeting in a 150 mm by 150 mm trench. Place plastic sheeting in the trench and anchor with wire staples at least 150 mm long. Backfill and compact trench. All seams shall be overlapped a minimum of 0.5 meters. At both horizontal and vertical seams, a predrilled piece of lumber, 50 mm x 100 mm nominal dimension, shall be anchored with #10 reinforcing bar, 0.5 meters in length, having a right angle bend at the top. Holes shall be a tight fit for the reinforcing bar and be drilled on 1 meter centers and the reinforcing bar driven into each hole. The exposed edges of the plastic sheeting shall be trenched in at sides and toe of slope as well as at the top of the slope.

Corners of test plots shall be staked with rebar. A weather resistant sign identifying the test plot designation listed on the plans, shall be placed on the lowest bench and at the top of each test plot. Signs shall be readable from the shoulder of the road. Material for signs shall be as approved by the Engineer.

The following construction requirements shall apply to the specific material being installed.

HYDRO MULCH

Items 628(1A), 628(1B), 628(2A), 628(2B), 628(3), and 628(4), are all hydro-mulches and shall be applied as specified in Section 618 under step 2 of the two step application process.

Item 628(3) Astromulch/EcoFiber shall consist of equal proportions of each type of mulch. Apply the mixture at a rate of 3000 kg/ha.

Item 628(4) Compost Blend shall consist of equal proportions of compost from the Anchorage Regional Compost Facility and EcoFiber. Apply the combined mixture at the rate of 3000 kg/ha.

BONDED FIBER MATRIX

For Items 628(5), 628(6), 628(7), 628(8), and 628(15), prepare slopes, apply fertilizer and seed according to step 1 of the two step application process and Section 618 of the Special Provisions. Immediately following seeding, apply Bonded Fiber Matrix slurry as described below in lieu of step 2.

Items 628(5) Soil Guard, 628(6) EcoAegis, 628(7) Hydro-Blanket, 628(8) Fibriform, and 628(15) BFM shall be installed per the manufacturer’s recommendations for mixing and applying these products. The Contractor shall provide evidence of the manufacturer’s training certification for Soil Guard and material samples for the other Bonded Fiber Matrices to the Engineer seven days prior to the scheduled installation. The Contractor shall cover 100% of the exposed soil for the specified test site for the Bonded Fiber Matrix product. Application of Bonded Fiber Matrix shall be permitted only when the soil is dry or slightly damp and if no rainfall is predicted for 24 hours after the installation.

Apply Item 628(5) Soil Guard at a rate of 3925 kg/ha.

Item 628(6) EcoAegis must be installed when the day and night low temperature is no lower than 4  C, and preferably above 10C. Wet surface areas, caused by subsurface water seepage, must be remedied prior to applying EcoAegis. Apply EcoAegis at 3365 kg/ha, or as specified by the manufacturer. EcoAegis shall be applied by one of the following methods:

1.Mechanical agitation hydroseeder:

Fill the tank 1/4 full of water. Begin agitation. Begin adding 5 kg of EcoAegis per 100 L and work up to a rate of 5.6 kg/100 L or more depending on the condition of the equipment. Keep adding water and EcoAegis at the final rate until the desired amount of each is reached.

2.Recirculation type hydroseeder:

Fill the tank 3/4 full of water. Begin circulation. Add EcoAegis slowly, breaking up large pieces before dropping them into the tank. Keep adding water and EcoAegis at a steady rate until the desired amount of each is reached, starting with 3.75 to 4.4 kg of EcoAegis per 100 L of water.

Mix the slurry for 10 minutes after adding the final amount of EcoAegis.

Apply EcoAegis in a uniform blanket. Coverage should be to a minimum depth of 3 mm. No soil should be visible. Apply EcoAegis in two directions to minimize shadowing. Avoid runoff or excessive slumping. Allow EcoAegis to dry between applications.

Apply 628(7) Hydro-Blanket at a rate of 3300 kg/ha. If mechanical agitation equipment is used, mix 48 kg of Hydro-Blanket with each kiloliter of water. If jet agitated machines are used, mix 30-36 kg of Hydro-Blanket with each kiloliter of water. If a hose is used, reduce the ratio of Hydro-Blanket to water by 20%. Spray in two or more directions to avoid a shadowing effect. Rough textured sites may require additional product to increase coverage of the surface area.

Apply Item 628(8) Fibriform at a rate of 3925 kg/ha. Fill tank 1/4 full of water, begin agitation. Continue filling with water and add the Fibriform. Mix for at least 10 minutes. Apply to slope in successive layers, in two or more directions.

ROLLED MATTING

Contractor shall supply samples of each material to the Engineer seven days prior to the scheduled installation. Keep all rolled matting materials dry prior to installation.

For Items 628(9A), 628(9B), 628(10), 628(11A), and 628(11B), prepare slopes, apply fertilizer and seed according to step 1 of the two step application process described in subsection 618-3.03 of the Special Provisions. Immediately following seeding, cover the slope with rolled matting as described below in lieu of step 2.

Install Item 628(9A) Rolled Straw/Coir Blend w/SC150 and Item 628(9B)Rolled Straw/Coir Blend w/SC150 BN in the following manner:

1.	Beginning at the top of the slope, anchor the end of the blanket in a 150 mm deep by 150 mm wide trench with staples. Backfill and compact the trench. Gradually unroll the blankets down the slope stapling at the appropriate locations as the blanket is unrolled. Overlap the edges of parallel blankets 50 mm and staple.

2.	When blankets are spliced down the slope, place blankets end over end (shingle style) with approximately 100 mm overlap. Staple through overlapped area, approximately 300 mm apart.

3.	Place staples on 0.5 meter vertical centers and 1 meter horizontal centers, minimum. Create a diamond pattern with the centers staggered.

4.	Use North America Green’s Surelock Staple Gun, or approved equal, to install staples on the Item 628(9A) and Item 628(9B) test sites.

Install Item 628 (10) Rolled Jute in the following manner:

1.	Secure fabric at the top of the cut and on each bench by trenching it in 150 mm deep. Staple the top of the roll with at least 5 staples, spacing each about 0.5 meters apart and covering with soil.

2.	Gradually unroll the jute from the top of the slope securing the jute with staples in the appropriate locations as it is being unrolled. The fabric should be loose, not stretched. Secure the jute in place with staples at 0.5 meter intervals. Stagger each row of staples to create a diamond pattern. Drive staples flush with the soil surface.

3.	Overlap the edges of the fabric 50 to 150 mm. At the end of each roll, fold back 100 to 200 mm of the fabric. Overlap shingle style, 100 to 200 mm over the start of the next roll. Securely staple the two layers to the ground.

4.	Terminate the fabric on a level area. Fold 150 mm of fabric under, secure with staples and cover with soil.

Install Item 628(11A) Rolled Coir with Biod-SCF 30 and Item 628(11B) Rolled Coir with Biod-OCF 30 as follows:

1.	Create trenches 150 mm deep and 150 mm wide at the top of the cut, at the back of each bench, and at the toe of the slope. Anchor blankets in trenches with staples. Insert a minimum of three staples every 0.5 meters along the trench. Two staples tack the blanket to the bottom of the trench, the third to the down slope side of the trench wall. Backfill and compact.

2.	Gradually unroll the blanket down the slope, anchoring in the appropriate locations as the blanket is unrolled. Lay blankets loosely on the ground allowing good contact between soil and blankets. Place staples on 0.5 meter vertical centers and 1 meter horizontal centers. Create a diamond pattern with the centers staggered.

3.	Use 200 mm overlaps when splicing blankets. Use two rows of staples to anchor blankets at overlap locations. Space staples at 0.25 meters apart. Overlap the sides of the blanket in the same manner.

BIO-ENGINEERED METHODS

Bio-engineered test sites involve a combination of brush layered benches, straw rolls and live stakes, and wattles. In all cases prepare the slopes between the benches according to subsection 618-3.01 of the Special Provisions. No willow species shall be installed on the lowest bench or slope nearest the roadway. All dormant cuttings shall be collected and stored as indicated in subsection 628-2.01 Materials.

After installing the specified bio-engineered method, apply seed and fertilizer in conjunction with a Bonded Fiber Matrix , Item 628(15) BFM. Either EcoAegis at an application rate of 3365 kg/ha, or Soil Guard at an application rate of 3925 kg/ha, is acceptable. Avoid spraying the Bonded Fiber Matrix on woody cuttings.

Install Item 628(12) Brush Layered Benches, as follows:

Place a minimum of 30 branches per meter on the bench in a slight crisscross fashion. Place the cut ends into the slope with the tips extending beyond the edge of the bench no more than 1/4 of the total branch length. Place a minimum of 100 mm of soil on top of the branches and tamp into place and water.

Install Item 628(13) Straw Roll with Live Stakes, in the following manner:

1.	Starting at the bottom of each slope, dig trenches along contour deep enough to accommodate half the thickness of the roll. If the soil is loose and uncompacted, the trench should be deep enough to bury the roll 2/3 of its thickness.

2.	As trenches are completed, place straw rolls in trenches. Rolls shall fit snugly against the soil. No gaps shall exist between the soil and the straw roll. Runoff must not be allowed to run under or around rolls. Soil from trench excavation shall be placed on the uphill side of each roll.

3.	Drive holes, as shown on the plans, through the rolls and into the soil below with a straight section of rebar. Install live stakes into the prepared holes. In between each stake driven through the roll, install a live stake on the down slope side of the trench into a hole made with driven rebar.

4.	Plant live stakes on each bench as shown on the plans. Do not drive stakes. Use a shovel or bar to create planting holes. Plant stakes upright with at least 3/4 of the stake below ground. Lightly pack soil around each stake and water to remove air pockets.

Item 628(14) Wattles, shall be installed as follows:

1.	Create wattles of dormant cuttings as shown on the plans with the growing tips and butt ends oriented in alternating directions. Stagger the cuttings in the bundles so that the tips are evenly distributed throughout the length of the wattle bundle. Store wattles at the work site in shade and under cover, preferably in water.

2.	Starting at the bottom of each slope, dig a shallow trench along contour. Set ½ of the wattle into the trench. Drive construction stakes into the down slope side of the wattle to secure it in the trench. Drive a second row of stakes into the wattle. Overlap the tapered ends of the wattles so that the overall thickness is continuous and uniform. Backfill wattles with soil from the trench excavation. Water while backfilling. A quarter of the wattle should be visible after installation. Continue the process as shown on plans to the top of the slope.

Item 628(16A) Water System Installation, shall be a Contractor designed and installed watering system capable of throughly watering the entire test plot area at a uniform rate without causing excessive runoff or flooding. System shall be capable of metering all water used. Watering system may be any combination of fixed or mobile watering equipment that will perform the required watering.

628-3.02 TIMING. The pay items shall be constructed during the time period shown below:

Item 628(1A) thru Item 628(17)		May 1- June 30, 2000

628-3.03 MAINTENANCE AND REPAIR OF SLOPES. Maintain and repair all slope treatments in accordance with the manufacturer’s written recommendations and subsection 618-3.04, or as directed by the Engineer. Slope maintenance and repair shall continue until accepted by the Engineer. Slope failures resulting from faulty installation will be subsidiary to that particular test plot and will not be measured and paid for separately. Slope failures that result from natural erosion not related to improper installation shall be directed by the Engineer for repair and paid for under 641, Temporary Erosion and Pollution Control. Watering shall be applied as directed by the Engineer.

628-4.01 METHOD OF MEASUREMENT. Items measured by the square meter will be measured by the area on the slope of the ground surface. Plastic sheeting will be measured by the area on the slope of the ground covered. The amount of water used for installing experimental slope stabilization items will be subsidiary to these items and will not be measured separately for payment. Those items measured by the meter shall be measured along the centerline of the of the trench or bench. Seed, Type C will be measured by the kilogram of seed mix used. Item 628(16B) Watering will be measured by the kiloliter of water used in maintaining the test plots.

628-5.01 BASIS OF PAYMENT. All work will be paid under the respective pay item. Site preparation, including trenching, staking and backfilling will be subsidiary to the specified items. Fertilizer, tackifier and water for application of seed will not be paid directly but will be subsidiary to Item 628(17) Seed, Type C. Payment for Item 628(16A) Water System Installation, will be full compensation for designing, installing, operating and dismantling the required watering system. Payment for Item 628(16B) Watering, will be on a contingent basis at the rate of $5.00 per kiloliter. Payment for Item 628(18) Plastic Sheeting, will be full compensation for all materials, labor and equipment to install, maintain, remove, and dispose of the plastic sheeting required on the test plots.

Payment will be made under the following:

Pay Item No.	Pay Item	Pay Unit

628(1A)	Astromulch - 1710 kg/ha	Square Meter

628(1B)	Astromulch - 3000 kg/ha	Square Meter

628(2A)	EcoFiber - 1710 kg/ha	Square Meter

628(2B)	EcoFiber - 3000 kg/ha	Square Meter

628(3)	Astromulch/EcoFiber	Square Meter

628(4)	Compost Blend	Square Meter

628(5)	Soil Guard	Square Meter

628(6)	EcoAegis	Square Meter

628(7)	Hydro-Blanket	Square Meter

628(8)	Fibriform	Square Meter

628(9A)	Rolled Straw/Coir Blend w/ SC150	Square Meter

628(9B)	Rolled Straw/Coir Blend w/ SC150BN	Square Meter

628(10)	Rolled Jute	Square Meter

628(11A)	Rolled Coir w/ Biod-SCF 30	Square Meter

628(11B)	Rolled Coir w/ Biod-OCF 30	Square Meter

628(12)	Brush Layered Benches	Meter

628(13)	Straw Roll w/ Live Stakes	 Meter

628(14)	Wattles	Meter

628(15)	BFM	Square Meter

628(16A)	Water System Installation	Lump Sum

628(16B)	Watering	Contingent Sum

628(17)	Seed, Type C	Kilogram

628(18)	Plastic Sheeting	Square Meter

SECTION 639

DRIVEWAYS

Special Provisions

639-1.01 DESCRIPTION. Delete this subsection in its entirety and substitute the following: This work consists of the excavation, forming, shaping and construction of approaches.

639-1.02 CONSTRUCTION REQUIREMENTS. Add the following subsection: Placement of materials used in approaches shall meet the requirements specified as follows:

Selected Material, Type A				Section 203

Crushed Aggregate Base Course			Section 301

Asphalt Concrete Pavement, Type II			Section 401

639-2.01 METHOD OF MEASUREMENT. Delete this subsection in its entirety and substitute the following: Approaches will be measured per each constructed as shown on the plans, or as directed.

639-3.01 BASIS OF PAYMENT. Add the following: Payment for approaches will be full compensation for furnishing all equipment and labor necessary to complete the work as indicated.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approaches	Each

Delete the last paragraph and substitute the following: The contract unit price for approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified. Selected Material, Type A, Asphalt Treated Base Course, and Asphalt Concrete Pavement required to construct approaches will be paid for separately under the respective items listed in the bid schedule. For each approach, 50 m³ of excavation will be considered subsidiary to Item 639(6) Approaches. Excavation in excess of 50 m³ per approach will be paid under Item 203(3) Unclassified Excavation.

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION AND POLLUTION CONTROL

Special Provisions

641-1.01 DESCRIPTION. This work shall consist of planning, providing, and maintaining control of erosion, water pollution, and hazardous materials contamination.

A Storm Water Pollution Prevention Plan (SWPPP) was developed for the utility work done in advance of this road construction project. This SWPPP is still in effect. Erosion structures and/or controls installed under the advance utility SWPPP shall be maintained and removed by the Contractor, as directed by the Engineer. The SWPPP prepared by the Contractor for this project shall be an amendment to the advance utility SWPPP and shall cover all work required by these contract documents. A copy of the advance utility SWPPP is available at the Plans Room in the Anchorage office of the Department.

641-1.02 DEFINITIONS.

1.	Erosion and Sediment Control Plan (ESCP). The Department's general plan for the permanent and temporary control of erosion and sedimentation during construction of the project as contained in the plans and specifications, and supplemented by the Department’s Erosion Prevention and Sediment Control Plan - Policy and Procedures; Guide to Preparing Erosion Prevention and Sediment Control Plans and Best Management Practices for Construction Erosion and Sediment Control. The ESCP is prepared by the Department and is attached to these specifications in Appendix “Permits.”

2.	Storm Water Pollution Prevention Plan (SWPPP). The detailed site-specific plan prepared by the Contractor for the temporary and permanent control of erosion and sedimentation during construction of the project. The SWPPP is based upon the ESCP, and prepared according to guidance provided in the National Pollutant Discharge Elimination System General Permit for Storm Water Discharges from Construction Sites (NPDES General Permit).

3.	Hazardous Material Control Plan (HMCP). The Contractor's detailed plan for the prevention, containment, cleanup, and disposal of hazardous waste material, including petroleum products generated by construction equipment or activities. Included in the HMCP is a list of quantities and types of equipment and materials available on site to be used for hazardous substance containment and cleanup. The plan also describes how and where construction equipment fueling and maintenance activities will be carried out and controlled.

4.	Notice of Intent (NOI) to utilize the NPDES General Permit for Alaska. This is a standard form (EPA Form 3510-9) giving notice to the U.S. Environmental Protection Agency (EPA) that work will be conducted in compliance with the NPDES General Permit. The NPDES General Permit authorizes discharges of storm water from construction activities involving more than 2.02 hectares of land. The Contractor prepares the NOI, and submits it to the Department a minimum of 5 days before the preconstruction conference for approval.

5.	Notice of Termination (NOT) of coverage under the NPDES General Permit for Alaska. This is a standard form (EPA Form 3510-7(8-98)) that constitutes notice that the project site has been finally stabilized or when an Operator of a construction activity, as defined in the NPDES General Permit, changes. The Contractor prepares the NOT, and submits it to the Engineer once final stabilization of the project site has been completed.

6.	Final Stabilization is when all soil disturbing activities at the site have been completed and a uniform perennial vegetative cover, with a density of 70 percent of the cover for unpaved areas not covered by permanent structures, has been established, or equivalent permanent stabilization measures (such as the use of riprap, gabions, or geotextiles) have been employed. The Engineer determines when final stabilization has occurred.

7.	Project Summary is a brief description of the activities to be covered under the NPDES General Permit. This shall be on a single sheet and shall describe the areas to be disturbed to the nearest hectare, the primary pollutants expected from the activities, and the type of treatment to be provided.

8.	Best Management Practices (BMP) is defined as any program, technology, process, siting criteria, operating method, measure, or device which controls, prevents, removes, or reduces pollution.

641-1.03 SUBMITTALS. The Contractor shall submit the following items for approval a minimum of 5 days prior to the preconstruction conference:

1.	Draft Storm Water Pollution Prevention Plan (SWPPP), an amendment to the advance utility SWPPP.

2.	Hazardous Material Control Plan (HMCP).

3.	Notice of Intent (NOI).

4.	Project Summary.

The Engineer will review submittals within 14 calendar days. If required for approval, the Contractor shall modify the submittals within 5 calendar days of receiving comments from the Engineer.

The Contractor’s SWPPP shall be prepared and stamped by a professional engineer currently registered in the State of Alaska. The Department will review the draft SWPPP, and either approve it, or recommend changes. The Contractor shall make the necessary revisions to obtain the Department’s approval of the SWPPP. The approved SWPPP becomes the project SWPPP and shall be signed and certified by the Contractor and the Department in accordance with the NPDES General Permit.

The Contractor shall implement all measures in the SWPPP and ensure that it remains current.

Once the Contractor's SWPPP is approved, the Engineer will submit the Contractor’s NOI along with the Department’s NOI to the EPA via Certified Mail. The Engineer will also submit copies of the NOI, the SWPPP, and the Project Summary to the State of Alaska Department of Environmental Conservation (DEC) Storm Water Coordinator. Earth disturbing work shall not begin until the Contractor receives in writing: 1) Department approval of the Contractor's SWPPP, and 2) notification that 48 hours have passed since the NOIs were postmarked to EPA and DEC.

The following shall be posted at the construction site:

1.	NPDES Permit number if available, or a copy of the NOI.

2.	Name and phone number of Contractor’s local contact person.

3.	Project Summary.

4.	The location of a SWPPP available for viewing by the public.

The Contractor shall amend the SWPPP within 7 days, when requested by the Engineer. All SWPPP amendments shall be prepared and stamped by a professional engineer currently registered in Alaska. The approval process for amendments to the SWPPP is the same as with the Contractor's draft SWPPP.

If a storm event occurs where storm water discharges pose a threat to water quality, the Contractor shall take immediate action to preclude pollution subject to the directive of the Engineer. An amended SWPPP covering the emergency measures that were taken shall be submitted to the Engineer within 7 days of the storm event.

Prior to project closeout and Contractor demobilization, the Contractor and Engineer shall review the project to determine if all areas disturbed by construction meet the requirements for final stabilization. When final stabilization has been accomplished, the Contractor shall submit a signed Notice of Termination (NOT) to the Engineer.

641-1.04 STORM WATER POLLUTION PREVENTION PLAN.

The Contractor shall prepare the SWPPP. The SWPPP shall cover all ground disturbing activities designated by the contract including offsite support activities. Examples of support activities are; concrete or asphalt batch plants, equipment staging yards, overburden and material stockpiles, excavated material disposal areas, borrow areas, etc., which are used solely by the permitted project. In contrast, commercial operations which can not be covered under this permit, are defined as those operations that serve multiple unrelated projects and would continue to operate after project completion.

A detailed description of the required contents of the SWPPP are found in the 1998 NPDES General Permit for construction activities in Alaska. The SWPPP shall follow the format presented in the NPDES General Permit and address all storm water discharge control and management issues identified in the ESCP. The SWPPP shall include the following:

1. Site Description.

a.	A description of the nature of the construction activity.

b.	A description of the intended sequence of major ground disturbing activities such as grubbing, excavation, grading, or utility installation.

c.	Estimates of the total area of the site and the total area of the site that is expected to be disturbed including offsite support areas.

d.	Estimates of the runoff coefficient of the site for pre-construction and post-construction conditions and data describing the soil or quality of any discharge from the site.

e.	A general location map and a site map showing the following:

(1)	drainage patterns

(2)	approximate slopes after grading

(3)	areas of soil disturbance and undisturbed areas

(4)	locations of major structural and nonstructural controls identified in the SWPPP and locations where stabilization is expected to occur

(5)	locations of offsite material, waste, borrow or equipment storage areas

(6)	locations of surface waters, including wetlands, and the locations where storm water discharges to surface waters

f.	Location and description of any discharge associated with industrial activity other than construction, and location of storm water discharges from dedicated asphalt or concrete plants covered by this permit.

g.	Name of the storm water discharge receiving water(s). The aerial extent and description of wetlands or special aquatic sites at or near the project site which will be disturbed or receive storm water discharge.

h.	A copy of the 1998 NPDES General Permit which can be an appendix to the SWPPP.

I.	Information on whether listed threatened or endangered species, or their critical habitat, are found in proximity to the project and off site support areas, and whether such species or habitat may be affected by storm water discharges or related activities.

2. Controls. The SWPPP shall include a description of appropriate control measures (BMP) which will be implemented as part of the construction activity to control pollutants in storm water discharges.

The SWPPP shall clearly describe, for each major soil disturbing activity described in 1b above, the appropriate control measures and the general timing (or sequence) during the construction process that the measures will be implemented, and who (Contractor or subcontractor) will be responsible for implementation.

The description and implementation of controls shall address the following minimum components:

a.	Erosion and Sediment Controls.

(1)	Short and Long Term Goals and Criteria designed to retain sediment on site to the extent practicable, and shall include off site support areas.

(2)	Stabilization Practices and implementation schedule. This shall include a description of interim and permanent stabilization practices such as the preservation of vegetative cover, temporary and permanent vegetation establishment, mulching, geotextiles, etc.

The following records shall be maintained and attached to the SWPPP:

(a)	the dates when major grading activities occur;

(b)	the dates when construction activities cease on a portion of the site, either temporarily or permanently;

(d)	and the dates when stabilization measures are initiated.

(3)	Structural Practices. This shall include a description of structural practices to divert flows from exposed soils, store flows, or otherwise limit runoff and discharges. Examples of structural practices include but are not limited to silt fences, earth dikes, drainage swales, sediment traps, check dams, subsurface drains, and temporary and permanent sediment basins.

b.	Storm Water Management. A description of measures that will be installed during construction to control pollutants in storm water discharges that will occur after construction operations. Examples of storm water management measures include but are not limited to storm water detention structures (wet ponds), storm water retention structures, flow attenuation, on site filtration, and sequential systems.

c.	Other Controls. This section shall address measures to be used to minimize dust and offsite vehicle tracking of sediments; a description of any on site material storage and measures to be used to minimize exposure of the materials to storm water, and measures to be used for spill prevention and response; a description of pollutant sources from areas other than construction and a description of controls. The SWPPP shall also include a description of measures necessary to protect listed endangered or threatened species or critical habitat.

The SWPPP shall be amended whenever there is a change in design, construction, operation, or maintenance, and shall be updated to remain consistent with any changes applicable to protecting surface water resources.

3. Maintenance. All erosion and sediment control measures and other protective measures identified in the SWPPP must be maintained in effective operating condition. This includes controls and measures implemented during the advance utility work. If the required inspections described in the following item identify BMP that are not operating effectively, maintenance shall be performed before the next anticipated storm event, or as necessary to maintain the continued effectiveness of storm water controls. If maintenance prior to the next anticipated storm event is impracticable, maintenance must be scheduled and accomplished as soon as practicable.

4. Inspections. Qualified personnel shall inspect the following:

a.	Disturbed areas of the construction site that have not been finally stabilized.

b.	Areas used for storage of materials that are exposed to precipitation.

c.	Structural control measures.

d.	Locations where vehicles enter or exit the site.

Inspections shall occur at least once every 7 calendar days and within 24 hours of the end of a storm event of 12.5 mm or greater of rain. Based on the results of the inspection, the SWPPP shall be modified as necessary to include additional or modified BMP to correct identified problems. Revisions to the SWPPP shall be completed within 7 days following inspections. If modifications to existing BMP are necessary, implementation shall be completed within 7 days.

The Contractor is eligible for a waiver of monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	The project is located in an area where frozen conditions are anticipated to continue for extended periods of time (ie, more than one month).

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

5. Inspection Reports. The Contractor shall prepare a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) and qualifications of personnel making the inspection.

c.	The date of the inspection.

d.	Major observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

Inspection reports shall be made and retained as part of the SWPPP for at least three years from the date of final stabilization. The report shall also identify any areas of non-compliance. Where a report does not identify any incidents of non-compliance, the report shall contain a certification that the facility is in compliance with the SWPPP and NPDES General Permit and be signed by the Contractor in accordance with Part VI.G of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP. Inspection reports shall be submitted to the Engineer within three (3) days of the inspection.

6. Non-Storm Water Discharges. Except for flows from fire fighting activities, sources of non-storm water listed in Part III.A.2 or 3 of the NPDES General Permit that are combined with storm water discharges associated with construction activity, shall be identified in the SWPPP. The SWPPP shall identify and ensure the implementation of appropriate pollution prevention measures for the non-storm water component(s) of the discharge.

641-1.05 HAZARDOUS MATERIAL CONTROL PLAN REQUIREMENTS. The Contractor shall comply with all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. The Contractor shall prepare the HMCP. The HMCP shall detail the Contractor’s plan for fueling and maintaining equipment and machinery. The locations where fueling and maintenance activities are to take place, and any controls to contain the accidental spillage of petroleum products shall be identified. A list of potentially hazardous materials, including petroleum products to be used and/or stored on site, and their estimated quantities shall be provided in the HMCP. The Contractor’s plan for the disposal of waste petroleum products and/or other hazardous wastes generated by the project shall also be identified in the HMCP. Additionally, the Contractor’s plan for prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills, and the Contractor’s plan for encountering unexpected contaminated soil and water during construction shall be detailed in the HMCP.

641-2.01 MATERIALS. Erosion and pollution control measures shall be accomplished utilizing BMP as specified in the SWPPP and HMCP. Ground disturbing activities shall only be undertaken after the seeding deadline under the following conditions:

1.	The SWPPP describes the work and controls to be taken to control storm water runoff after the seeding deadline.

2.	Personnel, materials, and equipment are on hand to accomplish the control measures identified in the SWPPP.

3.	All disturbed areas will be stabilized against erosion within 7 days of the temporary or permanent cessation of work on the slopes. Stabilization practices may include mulching, geotextile, sod, covering with sheet plastic, or other equivalent measures.

641-3.01 CONSTRUCTION REQUIREMENTS. The Contractor shall comply with all requirements of the NPDES General Permit for Alaska, and shall implement all temporary and permanent measures identified in the SWPPP and plans. The Department and Contractor shall share responsibility for inspecting, and the Contractor’s representative shall prepare inspection reports per the requirements of the NPDES General Permit. Compliance with the NPDES General Permit does not reduce the Engineer's authority to direct additional erosion control measures deemed appropriate. The Department reserves the right to hire another contractor to perform this work if the Contractor is unresponsive or a suitable agreement cannot be reached with the Contractor.

Prior to start of construction, the Contractor, his representative, the professional engineer who stamped the SWPPP, and the Engineer shall have an on site inspection to discuss the SWPPP implementation and the requirements under that plan.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. The Contractor shall also be responsible for performing all fueling operations in a safe and environmentally responsible manner. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-4.01 METHOD OF MEASUREMENT. Item 641(1) Erosion and Pollution Control Administration, will not be measured for payment. The Engineer’s acceptance will constitute measurement.

Item 641(2) Erosion and Pollution Control, will be measured in the manner specified in the directive authorizing the work.

641-5.01 BASIS OF PAYMENT. Item 641(1) Erosion and Pollution Control Administration, will be full compensation for administration of erosion control including plan preparation and amendments, inspection, monitoring, reporting and record keeping.

Item 641(2) Erosion and Pollution Control, will be full compensation for providing all labor, equipment, and materials required to accomplish the work, as specified in the directive authorizing the work.

Failure to diligently a) pursue work required by the approved SWPPP, b) respond to inspection recommendations and/or deficiencies in the SWPPP, c) implement erosion and sedimentation controls identified by the Engineer, will result in a permanent price adjustment under Item 641(6). If the Contractor does not respond within 2 hours of the Engineer’s directive, then an amount equal to five percent of the total amount earned from all previous and subsequent progress payments on the contract or $50,000 which ever is greater, will be withheld, and a permanent price adjustment made equivalent to:

1.	$500 per hour for the first 4 hours of non-action;

2.	$1,000 per hour for every hour over four, but less than 10;

3.	$1,500 per hour for every hour over 10 hours of non-action.

The Price Adjustment will cease when corrective actions are accepted by the Engineer. The Department reserves the right to hire another contractor to do corrective action, and to reduce the contract amount by this cost plus the cost to the Department implementing another contract.

In addition, a price adjustment equivalent to any penalties levied against the Department by the EPA or any other state and/or federal agencies for violations of the Clean Water Act and the NPDES General Permit will be made if the Department is issued a notice of violation by these agencies. This price adjustment shall be the actual cost of any fines levied against the Department. An amount equal to the maximum fine for the violation will be withheld temporarily until the actual cost of the fine is known. The difference, excluding any price adjustments will be released by the Engineer upon satisfactory completion of the requirements of the NPDES General Permit. Penalties for violations are as stated in Part VI.A.2 of the Standard Permit Conditions of the NPDES General Permit. The Contractor shall also be responsible for the payment of his own fines.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(2)	Erosion and Pollution Control	Contingent Sum

641(6)	Erosion and Pollution Price Adjustment	Contingent Sum

(4/30/98)R59M

Delete Sections 614 and 642 and replace with the following:

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION. Perform all surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the plans and specifications and standard engineering practice.

Furnish and install survey monuments and monument cases in conformance with the Plans or as directed.

Adjust existing monuments and monument cases to conform to the new elevations.

642-1.02 DEFINITIONS

1.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown on the plans.

2.	Point: Any identified spot located on the surface of the earth. For purposes of this definition, a point can be a PK nail, wooden hub, rebar, large nail or any other structure capable of being utilized as a marker.

3.	Witness Corner: A material mark or point usually placed on a property or survey line, at a known distance from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

4.	Reference Monument: A material mark or point placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

5.	Surveyor: The Contractor’s Professional Land Surveyor, currently registered in the State of Alaska.

642-2.01 MATERIALS.

1.	Monument Cases. Castings shall conform to AASHTO M 105, Class 30A. Castings shall be coated with a bituminous damp-proof coating. The tops shall bear evenly on the frames.

2.	Primary Monument: A minimum 50 mm diameter nonferrous pipe at least 750 mm long, with a minimum 100 mm flange at the bottom and having magnets attached at the top and bottom. A minimum 60 mm diameter nonferrous metal cap must be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments which will be oriented so as to be read facing up-station.

3.	Secondary Monument: A minimum 15 mm x 750 mm rebar with a 50 mm aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number and the year set.

CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL. Use competent, qualified personnel and suitable equipment for the layout work required and furnish all traffic control, stakes, templates, straight-edges and other devices necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish such computer services as necessary to accomplish the work. Check all data received from the computer for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver all field books, computer forms and computer output data to the Engineer. This data shall become the property of the Department.

Supervise construction surveying personnel. Correct any errors resulting from the operations of said personnel at Contractor expense. The Contractor is responsible for the accuracy of the work.

Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, shall be performed by or under the responsible charge of a Professional Land Surveyor.

Follow the Department’s Construction Surveying Requirements (Metric). A copy of this document is attached to these Special Provisions in Appendix B.

Keep field notes in standard bound notebooks in a clear, orderly, and neat manner consistent with Departmental procedures, including titles, numbering, and indexing. Make field books available for inspection by the Department’s project personnel at any time. Store the field books in the Department’s Project Office During periods of non-use.

Perform the following:

1.	calculate clearing and/or grubbing limits as shown on the plans and stake as necessary to delineate the same

2.	cross sections necessary for determination of excavation and embankment quantities, including intermediate and/or remeasure cross sections as needed

3.	slope staking

4.	staking of signs, culverts, minor drainage structures and other appurtenances, including the necessary checking to establish the proper location and grade to best fit the conditions on site

5.	bridge staking

6.	the setting of such finishing stakes as may be required

7.	the measurement of pay quantities that require measurement

8.	the staking of right-of-way and material source limits when it is deemed necessary

9.	the staking, referencing and other actions as may be required to preserve or restore land monuments and property corners

10.	and all other surveying and staking necessary to complete the project

When the right-of-way centerline points have been established as a part of the Department’s Preconstruction surveys, the Department will furnish the Contractor with copies of the reference field books. Recover these control points and verify these references. Reestablish any missing points from the Department’s references prior to the initiation of clearing, grubbing, or excavation.

When the right-of-way centerline points have not been established by the Department but the survey control points were established as a part of the Department’s Preconstruction surveys (as detailed on the project Survey Control Sheet) recover these points and use them as the basis for establishing the right-of-way centerline. Verify the position of these points and establish new points where required to replace missing points, prior to the initiation of clearing, grubbing, or excavation.

Notify the Engineer immediately if a Department-established reference point is discovered to be in error or a reset point is not in harmonious relationship to the adjacent centerline points.

Furnish a notekeeper to record all field survey notes, including those which become documentation from which quantities for payment are computed. The notekeeper shall be thoroughly familiar with generally accepted standards of good survey notekeeping practice and the Department’s Construction Surveying Requirements (Metric).

The Engineer may randomly spot check the Contractor's surveys, staking and computations. Prior to staking for clearing and/or grubbing limits, the Contractor shall furnish the calculated offsets to the Engineer a minimum of 48 hours prior to staking. After the survey or staking has been completed, provide the Engineer with a minimum of 72 hours notice prior to performing any work, and furnish the appropriate data as required, to allow for such random spot checking. The Department assumes no responsibility for the accuracy of the work. This time period may also be used by the Engineer for any redesign due to field conditions. If restaking is necessary due to these changes, the staking will be paid at the contract unit price for Item 642(3) Three Person Survey Party.

642-3.02 CROSS-SECTION SURVEYS. When required, obtain right-angle cross sections to the construction centerline at the interval detailed in the Department’s Construction Surveying Requirements (Metric).

The following shall be supplied by the Department:

1.	One set of Construction Plans and Specifications.

2.	Field Books (Level, Cross-Section, Slope Stake, etc. ). Books will be labeled and the pages numbered by the Department. Field books shall remain the property of the Department upon completion of the work.

3.	Design Cross Sections, if any.

4.	Sufficient centerline or reference thereto, and at least one benchmark per kilometer to enable the establishment of planned elevations and centerline.

5.	State of Alaska Land Survey Monument Record forms. These forms are to be completed by the Contractor.

6.	One copy of the Department’s Construction Surveying Requirements (Metric).

7.	Design centerline grades, except when Item 642(2), Office Engineering is used.

The following shall be required of the Contractor:

1.	A heading in the appropriate book (date, weather, names and duties of crew members) shall be made at the beginning of each day's work.

2.	The notekeeper shall update the index of the appropriate book at the end of each day's work.

3.	Level notes shall be reduced, checked and adjusted.

4.	Cross-section level notes and slope stake catches shall be computed by the notekeeper and checked by a different crew member in the field on a continual basis.

5.	The Contractor shall enter the grade data, shoulder width and/or ditch distance, stationing, slope, etc., in the slope stake books.

6.	The position and identifying marks of slope stakes and reference points shall be maintained until used for their intended purpose.

7.	Errors shall have a line drawn through them with the correct entry made directly above. Erasures will not be allowed.

8.	Field books or copies of the field books shall be returned to the Project office at the end of each work day or as directed.

9.	The Contractor shall provide copies of all grade sheets and temporary bench mark elevations to the Engineer 48 hours before commencing work on unclassified excavation or embankment.

10.	The Contractor’s survey crews shall comply with all approved traffic control plans. Crews shall coordinate their activities with the Contractor’s Worksite Traffic Supervisor.

11.	A survey Party Chief diary shall be kept daily and contain the following information, (a copy shall be given to the Engineer daily):

a.	Date.

b	Weather.

c.	Crew members’ names and duties.

d. 	Type and location of work performed.

e. 	Hours worked.

f. 	Type of equipment used (brand) and date equipment was double centered or “peg” test was performed.

g. 	Signature of person in responsible charge.

12.	The Contractor shall submit the survey field notes, for any specific area, relating to monument referencing prior to any initiation of clearing, grubbing or excavation.

642-3.03 MONUMENTS. Install primary and secondary monuments, as called for in the plans, at the positions established by the Department. Reference all monuments, property markers/corners, or accessories which may be disturbed or buried during construction, and re-establish them in their original position prior to the completion of the project. Keep such records and report to the Engineer evidence that a monument has been disturbed and is no longer reliable or cannot be located and is presumed to be missing. The referencing work shall consist of a minimum of two in-line reference points, or three swing-tie reference points in situations where in-line referencing is not desirable. Set all reference points outside of the construction limits. Measure distances from the monument to the nearest l mm. Record all referencing of monuments in a separate field book stamped by the Surveyor.

Replace all existing monuments disturbed by construction with Primary or Secondary Monuments meeting the requirements of Subsection 642-1.02. When it is impractical to establish a monument in its original position, install a witness corner (WC). Place the WC to a property corner on the property line when the other property corner which defines said line is existing or there has been sufficient retracement to define said line. In other cases, place a reference monument (RM) perpendicular to the centerline at the station of the original position and at a distance from the original position measured in whole meters.

Those monuments found that are not shown on the plans will be recognized by the Engineer when the following is provided by the Surveyor: Field notes identifying type and location of the monument, and a description of the point the monument marks, with the reason to preserve its location. Monuments not shown on the plans will be considered additional work and paid by 642(3), Three Person Survey Party.

The Surveyor shall complete a State of Alaska Land Survey Monument Record form for each primary and secondary monument installed, relocated or replaced. In addition to the required survey information, including section, township and range, each record shall meet all requirements for recording at the District Recorder’s Office in which the project is located. Deliver these forms to the Engineer prior to project completion. The Department will file all original records as required by current State Statutes using the information provided by the Contractor.

Set each monument and monument case accurately to lines established at the required location and in such a manner as to insure its being held firmly in place. Set existing monuments and monument cases to be adjusted to new elevations in the manner and at the elevations directed.

642-3.04 OFFICE ENGINEERING. Calculate finish grades for the roadway as specified per plans and/or specifications. Use information available in the field, on as-builts, or as provided by the Engineer. This work shall be performed by or under the responsible charge of a Professional Land Surveyor or a Professional Engineer currently Registered in the State of Alaska.

642-3.05 FINAL TRAVERSE. Within 30 days after the Engineer receives from the Contractor a letter which states that all construction activities that may disturb the monuments have ceased, the Surveyor shall run a final traverse to verify the positional accuracy of installed survey monuments. This traverse will begin and end at different Department provided control points. The primary and secondary monuments placed or replaced and any undisturbed department provided control points shall be tied to the traverse. Under no circumstance shall the final traverse run more than 4 km without a tie to a department provided monument/control point. All traverse points established during this work shall meet the requirements of a secondary monument. The Surveyor shall sign and stamp a letter which lists each monument and its coordinates. The letter shall certify that the monuments are each located within 50 mm of their proposed position based on the project survey control points provided by the Department. Deliver the certification letter and field notes for this work to the Engineer.

642-4.01 METHOD OF MEASUREMENT.

Item 642(1) Construction Surveying. No measurement of quantities will be made.

Item 642(2) Office Engineering. By the kilometer along centerline for all completed office engineering accepted.

Item 642(3) Three Person Survey Party. By the hour for extra, additional, or unanticipated work made necessary by changes in the project, as directed.

Items 642(4) through 642(8). The actual number of monuments installed as shown on the “State of Alaska Land Survey Monument Record” forms delivered to and accepted by the Engineer.

Item 642(9) Reference Existing Monument. The actual number of monuments referenced as shown in the Surveyor’s field notes delivered to and accepted by the Engineer.

642(10) and 642(11). The actual number of monument cases furnished and installed, or adjusted to new elevation, and accepted.

642(12) Final Traverse. No measurement of quantities will be made.

Survey monuments that are placed on bridges will not be measured for payment but will be considered incidental to other bridge items.

Calculations of all pay quantities will be performed by Department personnel.

642-5.01 BASIS OF PAYMENT. Construction Surveying and Final Traverse shall include all field and office work required to accomplish the work, including furnishing all necessary personnel, equipment, transportation and supplies. Staking of right-of-way will be paid under Construction Surveying. Payment for Final Traverse is based on the Engineer’s acceptance of the Surveyor’s certification letter and field notes.

Office Engineering when required, will be in addition to Construction Surveying. Both items will appear on the bid schedule.

If staking for extra, additional or unanticipated work, as stated above, is performed by a two person survey party, payment will be made at 75 percent of the unit price under Item 642(3), Three Person Survey Party. If a single person is required for additional office computations or other work requiring only one person, payment will be made at 32 percent of the unit price of Item 642(3).

Traffic control devices necessary for the survey parties will be considered subsidiary. Payment for Traffic Control Plans as approved will be paid under Section 643, Traffic Maintenance.

The accepted quantities will be paid for at the contract price, per unit of measurement for each of the particular pay items shown in the bid schedule.

Pay Item No.	Pay Item	Unit

642(1)	Construction Surveying	Lump Sum

642(2)	Office Engineering	Kilometer

642(3)	Three Person Survey Party	Hour

642(4)	Set Primary Monument	Each

642(5)	Set Secondary Monument	Each

642(6)	Replace Existing with Primary Monument	Each

642(7)	Replace Existing with Secondary Monument	Each

642(8)	Adjust Existing Monument	Each

642(9)	Reference Existing Monument	Each

642(10)	Monument Case	Each

642(11)	Adjust Existing Monument Case	Each

642(12)	Final Traverse	Lump Sum

(7/15/98)R214M

Delete Section 643 in its entirety and substitute the following:

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION. This work consists of the necessary measures to protect and control traffic during the life of the contract including, but not limited to, furnishing, erecting, maintaining, replacing, cleaning, moving and removing the traffic control devices required to insure the safety of the traveling public and all administrative responsibilities necessary to implement this work.

The Contractor shall maintain all roadways, pedestrian and bicycle facilities affected by the work and shall construct and maintain approaches, crossings, intersections and other features as may be necessary throughout the life of the contract.

643-1.02 DEFINITIONS.

Construction Phasing Plan - A plan for each phase of the project showing how traffic will be accommodated. It should show the sequence of work by segment or phase if required.

Traffic - The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, incident zones or similar operations.

Traffic Control Plan - A Traffic Control Plan (TCP) is a drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. It depicts the traffic control devices to be used, their placement and times of use.

Traffic Control Zone - A portion of a road construction project, maintenance operation, utility work, incident zone or similar operation where traffic is affected by the operation and traffic control is needed to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. The TCP may include, but not be limited to, such items as signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary roadways and all other items required to direct traffic through or around the construction zone in accordance with these specifications and the Alaska Traffic Manual (ATM). The TCPs shall also address placement of traffic control devices including location, size, mounting height and type. The details shown for signs shall include the code designation, size, and legend per the ATM and the Alaska Sign Design Specifications (ASDS). Plan sheets developed on Auto Cad can be made available, upon request, for use in preparing TCPs.

When a TCP is included in the plans the Contractor may use it, modify it or design an alternative TCP. Any modifications to the TCP or any new TCP shall be submitted for approval of the Engineer. The Contractor shall allow 1 week for review of any TCP or each subsequent correction. Changes in the TCP may be allowed during construction provided 48 hours are allowed for review and the changes are approved by the Engineer.

When a TCP is not included in the plans the Contractor shall provide one in accordance with this Section and the ATM. The Contractor's superintendent shall review and sign all TCPs prior to submittal. Acceptance of a TCP is based on the Contractor's certification that the plan is in conformance with the ATM and the specifications.

All TCPs submitted shall indicate the periods for which the TCP will be in effect. Each TCP shall provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

When a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements is in effect for this project, all movements of oversize and overweight vehicles in or near traffic within the project limits will be in accordance with the provisions of an approved TCP. The TCP shall specify traffic control devices that will be required for these operations.

There shall be no work within the project limits until the Contractor has implemented an approved TCP for the work proposed. The number of traffic control devices indicated on the TCPs, plans, and Standard Drawings are a minimum. If unsafe conditions occur, the Engineer may require additional traffic control devices.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. The Contractor shall provide a Worksite Traffic Supervisor who shall be responsible for the Contractor's maintenance of traffic operations on a 24-hour basis.

1.	Qualifications. The Worksite Traffic Supervisor shall understand the requirements of the ATM, the plans and the specifications and meet at least one of the following:

a.	Be currently certified as a Worksite Traffic Supervisor by the American Traffic Safety Services Association (ATSSA).

b.	Be currently certified as a Work Zone Traffic Safety Specialist or a Signs and Markings Specialist by the International Municipal Signal Association (IMSA).

c.	Be currently certified as a Worksite Traffic Technician by (ATSSA).

Items b and c require documentation of a minimum of twelve months of supervisory level worksite traffic control or twelve months of responsible charge of such work. "Responsible charge" shall be construed to mean having been in a position of accountability for the selection of devices and for their placement in the traffic control system, or for the continued operation of the system. Having persons that actually perform labor under one's control would satisfy this requirement.

2.	Duties. The Worksite Traffic Supervisor's duties shall include the following:

a.	Prepare the TCPs and public notices and coordinate traffic control operations with the Engineer.

b.	Inspect the condition and position of all traffic control devices in use on the project at least once each day and once each night, to ensure that devices are in proper working order, clean, visible and conform to the approved TCPs in use. Furnish a detailed written report of each inspection to the Engineer within 24 hours.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate appropriate traffic control needs and ensure that the proper traffic control devices necessary for safe and efficient traffic movement are available.

e.	Review work areas, storage of equipment, and handling and storage of materials relative to traffic safety.

f.	Hold traffic safety meetings with the superintendents and foremen of the Contractor and subcontractors prior to beginning construction, and periodically thereafter as necessary or as directed by the Engineer. The Engineer shall be provided the opportunity to attend these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all of the flaggers meet the requirements of Subsection 643-3.04.

643-1.05 CONSTRUCTION PHASING PLAN. A Construction Phasing Plan shall be submitted at least 5 working days prior to the Preconstruction Conference for approval by the Engineer and consist of the following:

1.	Designation of a Worksite Traffic Supervisor including his resume, written verification of his credentials and the telephone numbers where he can be reached 24-hours a day.

2.	A plan for each phase or segment of the project. Changes shall be submitted to the Engineer for approval 15 days in advance of their proposed implementation.

3.	TCPs for the first phase of the project with both the permanent and temporary traffic control measures shown including the times of use of each TCP.

643-2.01 MATERIALS. Materials for traffic control devices shall conform to the requirements set forth below:

1.	Signs. Permanent Construction Signs, Construction Signs and Special Construction Signs including sign supports shall conform to the requirement of Section 615, Standard Signs, the ATM and ASDS. The size of each Special Construction Sign shall be clearly and neatly marked in 75 mm high black numerals on its back.

2.	Portable Sign Supports. Portable sign supports shall be wind resistant with no external ballasting and capable of supporting a 1.2 m X 1.2 m traffic control sign such that the height of the sign above the adjacent roadway surface is that required by the ATM. The sign support shall support the traffic control sign vertically.

3.	Barricades and Vertical Panels. Barricades and vertical panels shall be constructed of wood, metal or plastic and conform to the requirements of the ATM and the Standard Drawings. Type III Barricades shall have a minimum length of 2.4 m.

4.	Portable Concrete Barriers. Portable concrete barriers shall conform to the requirements of Standard Drawing G-45. Each barrier shall be equipped with at least two side-mounted retroreflective reflectors (or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm from the top of the barrier), for each direction of traffic. The reflectors (or tape) shall be yellow if the barriers are used at centerline and white if used on the roadway shoulder.

5.	Warning Lights. Warning lights shall be Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) conforming to the requirements of the ATM.

6.	Drums. Drums shall be plastic and conform to the requirements of the ATM and the Standard Drawings.

7.	Traffic Cones. Traffic cones and/or tubular markers shall conform to the requirements of the ATM and the Standard Drawings. The minimum height shall be 710 mm. All cones and tubular markers shall be reflectorized.

8.	Interim Pavement Markings. Interim pavement markings shall be paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08. The markings shall be applied in accordance with Section 670 and the manufacturer's recommendations.

9.	High Level Warning Devices. High level warning devices shall conform to the ATM and the Standard Drawings.

10.	Temporary Crash Cushions. Temporary crash cushions shall have been tested as per the procedures set forth in National Cooperative Highway Research Program (NCHRP) Report 350, Test Level 3. Certification shall be provided by the manufacturer directly to the Engineer. Permanent crash cushions shall not be used as temporary crash cushions.

11.	Sequential Arrow Panels. Sequential arrow panels shall be Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) conforming to the requirement of the ATM and the Standard Drawings.

12.	Portable Changeable Message Board Signs. Portable changeable message board signs shall conform to the requirements of the ATM.

13.	Plastic safety fence shall be construction orange, 1.2 m high and shall be as manufactured by one of the following companies, or approved equal:

a.	“Safety Fence” as manufactured by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” as manufactured by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” as manufactured by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. This item shall consist of providing all labor, equipment and materials to provide a temporary sidewalk surfacing as required by an approved Traffic Control Plan.

a.	The materials shall be a minimum of 12 mm plywood for areas that are continuously supported by subgrade and 25 mm plywood for areas that are not continuously supported.

b.	The maximum unsupported length of 25 mm plywood shall be 750 mm.

c.	The surface of the plywood shall be free of irregularities. The height of plywood overlap joints shall not exceed 25 mm.

d.	The temporary surfacing shall be held in place by a method that will withstand 25 mph wind velocities.

15.	Temporary Guardrail. Temporary Guardrail shall conform to the standard drawings and section 606 of the standard specifications.

Traffic cones, candles, drums, and delineators that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, test level 3. This certification may be a one page affidavit signed by the vendor. It shall be given to the Engineer before the devices are used on the project. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.

Composition		Weight		Height

Cones		Rubber		 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber		 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Truck-mounted attenuators and portable crash cushions purchased after October 1, 1998 must be certified as compliant with National Cooperative Research Program 350, test level 3, crashworthiness requirements. Certification, consisting of a letter of NCHRP-350 compliance from the Federal Highway Administration, shall be provided to the Engineer for each of these devices before they are used on the project.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. The Contractor shall keep the work, and portions of the project affected by the work, in such condition that traffic will be accommodated safely. Traffic control devices and services shall be provided and maintained both inside and outside the project limits both day and night as needed to facilitate traffic guidance.

Unless otherwise provided herein, the Contractor shall keep all roadways undergoing improvement open to traffic. Temporary closure of residential, commercial or street approaches requires prior approval of the Engineer. The Contractor shall provide access through the project for emergency vehicles and school and transit busses. All locations requiring redirection or stopping of the traveling public shall be properly signed and/or flagged by the Contractor.

The Contractor's equipment shall stop at all points of intersection with the traveling public unless satisfactory traffic control measures, are shown on the approved TCP.

All illumination and signalization shall remain operational as per the requirements of Subsection 660-1.05, Maintaining Existing and Temporary Electrical Systems. Signal heads shall be re-aligned as necessary in accordance with the ATM when approach lanes are moved. Any modifications to existing traffic signals shall be coordinated with the agency responsible for their maintenance and operation. Flood lighting at night shall be in accordance with the ATM and be adjusted such that it does not shine into oncoming traffic.

The Contractor shall provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times except when pedestrians or bicyclists are prohibited by regulation. Whenever construction activity encroaches onto the safe route in a traffic control zone the Contractor shall station an employee at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Roadway lane and shoulder widths in existence prior to the start of construction shall not be reduced without an approved TCP. The Contractor shall maintain a 0.6 m minimum clear area between the edge of traveled way and the work area. Use either barricades, traffic cones, or drums for delineation of this area. These traffic control devices shall be placed on the work side of the clear area and be spaced in accordance with the ATM.

If the Contractor is allowed to maintain traffic on an unpaved surface, the construction shall be conducted in such a manner as to provide a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage. In advance of other grading operations, sufficient fill shall be placed at culverts and bridges to permit traffic to cross smoothly and unimpeded. Part width construction techniques shall be employed when the traffic is routed through roadway cuts or over embankments under construction. The material shall be excavated or placed in layers and the construction activities shall be alternated from one side to the other, with traffic routed over the side opposite the one under construction.

Where so provided on the plans or an approved TCP, the Contractor may detour traffic. The detour routes shall be maintained by the Contractor during times of use in such condition that traffic will be accommodated safely. When no longer required, the detour shall be obliterated and appropriate areas topsoiled and seeded.

In general, all roadway crossings should be made while maintaining traffic as described above. If two-way traffic cannot be maintained, whether on the existing roadway or a detour, half-width construction or a road closure may be allowed and must be shown on an approved TCP. The TCP shall indicate the duration and conditions of closure. Roadway crossings shall be scheduled so as not to delay school busses and peak hour traffic. For road closures the Contractor shall post at the site of the closure, within view of waiting traffic, the time the closure started and the time the road will again be open to traffic.

643-3.03 PUBLIC NOTICE. The Worksite Traffic Supervisor shall give notices of changes, delays or road closures to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska State Troopers

Matanuska-Susitna Borough Public Safety

Matanuska-Susitna Borough Central Emergency Services

Sutton Chamber of Commerce

Sutton Community Council

Local Fire Department

Local School & Transit Authorities

Local Emergency Medical Services

Local Media (Newspapers, Radio, Television)

Railroads (Where applicable)

U.S. Postal Service

The Contractor shall also provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project, and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. These shall be for alerting the Contractor of emergencies which will require passage of emergency vehicles through the project. When so notified the Contractor shall use all equipment and effort necessary to expedite rapid passage.

643-3.04 TRAFFIC CONTROL DEVICES. Prior to the start of construction operations, the Contractor shall erect such permanent and temporary traffic control devices as may be required by the approved TCPs. Traffic control devices shall be used only when they are needed. Advisory speeds, when necessary, shall be determined by the Engineer.

For lane closures on multilane roadways, sequential arrow panels shall be used. When required for night time operations, flashing warning lights shall be used to mark obstructions or hazards and steady-burn lights shall be used for channelization.

During non-working hours and following the completion of a particular construction operation, all unnecessary traffic control devices shall be removed. Sign panels that are post mounted and cannot be readily removed shall be entirely covered with either metal or plywood sheeting.

Reflective sheeting on signs, drums, barricades and other devices shall be kept clean.

All traffic control devices shall meet the requirements of American Traffic Safety Services Association (ATSSA), "Quality Standard for Work Zone Traffic Control Devices".

Any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while their use is required on the project shall be immediately replaced by the Contractor. The Contractor shall stock repair parts for each Temporary Crash Cushion used on the project. If a crash cushion is damaged it shall be repaired within 24 hours.

All items paid for under this section shall remain the property of the Contractor and shall be removed upon completion of the project.

1.	Embankments. Install portable concrete barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as called for on the plans or TCPs to delineate open trenches, ditches, other excavations and hazardous areas when they exist along the roadway for more than one continuous work shift.

2.	Adjacent Travel Lane Paving. The Contractor shall limit pavement edge and lane edge drop-offs as specified under Subsection 401-3.11. When the depth of paving is greater than 50 mm and the paving of adjacent travel lanes or paved shoulders cannot for some unforeseen circumstance be completed to the same elevation before the end of the paving shift, the appropriate signing shall be installed: CW24-1, (Uneven Lanes), CW8-9A, (Low Shoulder), CW14-3, (No Passing Zone), R4-1, (Do Not Pass), and R4-2, (Pass with Care). If the section in question is longer than 800 m in length additional signs shall be placed at 460 m intervals.

3.	Fixed Objects. Vehicles working within 4.6 m of the edge of traveled way shall be equipped with flashing warning lights. The vehicle's flashing warning lights may be emergency flashers, flashing strobes or rotating beacons.

Private vehicles, idle construction equipment, construction material stockpiles and other items deemed by the Engineer to be fixed objects shall be located outside the clear zone at all times. Parking of equipment in medians will not be allowed.

Where, due to land features or lack of right-of-way, it is not feasible to meet the above restrictions, equipment shall be parked as far away as practical but a minimum of 4.6 m from the edge of traveled way as approved by the Engineer. Traffic control devices for identifying hazards including flashing warning lights shall be used to delineate the equipment when parked in this manner. These traffic control devices will not be paid for but will be considered the Contractor's responsibility.

4.	Flagging. Flagging shall include the furnishing of trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, for the control of traffic through the work zone. Each flagging operation shall be approved by the Engineer prior to its implementation and shall be adjusted as conditions change or as directed by the Engineer

Prior to beginning work, and at the start of each construction season thereafter, flaggers shall attend the special videotape training session provided by the Engineer. The Worksite Traffic Supervisor shall certify in writing that all flaggers are personally familiar with and meet the requirements of the ATM and have attended the annual training before being allowed to direct traffic.

Flaggers shall maintain their assigned posts at all times, unless relieved by another qualified flagger or the need for flagging traffic no longer exists. Flagger signs are to be removed when a flagger is not present. The flaggers area should be free of encumbrances, such as parked vehicles, so the flaggers are readily visible.

The Contractor shall provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

No signalized intersection shall be flagged without prior written approval of the Engineer. When a signalized intersection is flagged the traffic signal shall either be turned off and covered or be placed in the All-Red Flash mode. Changing traffic signal modes, turning off or turning on traffic signals, shall be coordinated with and approved in writing by the agency responsible for signal maintenance and operation, and by the Engineer.

5.	Pilot Cars. Pilot car operations may be approved where the route through a construction work zone is particularly hazardous, so involved or frequently altered as to preclude adequate signing, or where one-way traffic is deemed by the Engineer to be necessary. Pilot cars shall not be used to avoid localized traffic control at several locations. The operation shall be organized so that no individual vehicle has a waiting period of more than 20 minutes, but this does not imply that twenty minutes will be allowed in all cases. Multiple pilot car operations within a project or adjoining projects shall be coordinated to minimize the inconvenience of the traveling public. Two or more pilot cars may be specified to provide two-way traffic through the work zone to reduce the waiting period. The flagger or pilot car operator shall record each departure time of the pilot car in a bound field book furnished by the Engineer. Whenever practicable, the flagger shall advise the motorist of the reason for the delay and the approximate length of time that the traffic will be delayed. The Contractor must make every reasonable effort to yield right-of-way to the driving public and prevent excessive delay. The vehicle selected for a pilot car shall be an automobile or pickup with the name of the Contractor prominently displayed and shall be equipped with a two-way radio for contact between flaggers and other pilot cars. A G20-4 sign, (Pilot Car Follow Me), shall be mounted on the rear a minimum height of 1.5 m above the driving surface. Provisions shall be made for identification of the last vehicle in the column.

When pilot cars are authorized, they shall be in force prior to beginning work and continue until no longer required or all traffic control devices required for non-working hours are properly in place and functioning.

6.	Street Sweeping. All paved portions of the roadway and haul routes open to the public shall be kept free of loose material, including sections of roadway off of the project where loose material is deposited as a result of the contractors operations. The street sweeper shall be capable of collecting materials rather than ejecting them to the shoulder of the road.

7.	Watering. The Contractor shall furnish, haul and place water for dust control and pavement flushing, as directed. Water trucks shall be capable of providing a high pressure water stream to flush the pavement and a light water spray for dust control. If the flushing operations contaminate or fill adjacent catch basins the contractor shall clean and restore them to the same condition they were in prior to his operations, including sections of roadway off of the project where flushing is required. The application of water shall be under control of the Engineer.

If water is to be taken from a lake, stream, or other natural water body, the Contractor shall obtain a water removal permit from Alaska Department of Natural Resources. The Contractor shall also comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

643-3.05 AUTHORITY OF THE ENGINEER. When, in the opinion of the Engineer, conditions are such that the safety and/or convenience of the traveling public are adversely affected, the Contractor will be immediately notified in writing. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). In no case shall this time exceed 24 hours. In the event that the Contractor fails to take the corrective action(s) within the specified time, (a) The Engineer will immediately direct that the offending operations cease until the defect(s) is (are) corrected and (b) the Engineer reserves the right to order the corrective action(s) be accomplished by outside forces. The cost of work by outside forces shall be deducted from any moneys due or that may become due under the terms of this contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. When Item 643(23) Traffic Price Adjustment, is shown on the bid schedule, the contract amount will be adjusted for each minute that the traffic is delayed if corrective measures directed by the Engineer are not promptly acted upon. The contract will be reduced at the rate listed in Table 643-1 (based on highway user costs), for each minute that any lane of traffic is not open to full use by the traveling public. Time will be measured to the nearest minute for the ADT published by the Department's Planning section. The Engineer shall determine whether the roadway is opened to full use by the traveling public.

The Traffic Price Adjustment shall be assessed for lane closures or reductions that are unauthorized. Lane closures and/or lane reductions that have been shown in the contract or authorized in writing by the Engineer are not subject to the Traffic Price Adjustment.

Traffic Price Adjustment will also be applied to unacceptable driving conditions, such as severe bumps, washboarding, potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway is acceptable for full unimpeded use by the public. Failure to comply will result in a price adjustment equal to 10 percent of the applicable rate shown in Table 643-1, for the time that the roadway is in an unacceptable condition.

TABLE 643-1

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| Less than 1,000 | $2 |
| 1,000 - 4,999 | $10 |
| 5,000 - 9,999 | $30 |
| 10,000+ | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month prior to seasonal suspension of work, the Contractor shall schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the work he expects to complete before shutdown and the condition the roadway is to be in. The Contractor shall then schedule a field review for acceptance by the Department for winter maintenance. At the field review a punch list will be prepared for implementation prior to acceptance. In order for the Contractor to be relieved of winter maintenance responsibility, all roads shall be left with a reasonably smooth and even surface satisfactory for use by public traffic at all times. The surface of the roadbed shall be properly crowned for drainage and adequate safety facilities shall be in place. All illumination and signals, including vehicle detectors, shall be in good working order. After acceptance for winter maintenance and until issuance of an order for the resumption of construction operations, maintenance of the facility agreed upon will be the responsibility of the Department. The Department will only accept maintenance responsibility for those portions of the work that are open to the public for use, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. Maintenance for all other portions of the work, shall remain the responsibility of the Contractor. The Engineer will list all portions of the work for which the Department will accept maintenance responsibility during a seasonal suspension of work in a letter of "Acceptance for Winter Maintenance." The Contractor shall retain all contractually required maintenance responsibilities until receipt of this letter.

If work is suspended due to unfavorable weather, other than seasonal, failure of the Contractor to correct conditions unsafe for the workmen or the general public, failure to carry out provisions of the contract, or for failure to carry out orders of the Engineer, all costs for maintenance of traffic during the suspended period shall be borne by the Contractor.

When work is resumed, the Contractor shall replace or renew any work or materials lost or damaged because of temporary use of the project. Remove to the extent directed by the Engineer, any work or materials used in the temporary maintenance and shall complete the project as though its prosecution had been continuous and without interference.

643-3.08 CONSTRUCTION SEQUENCING. Construction sequencing detailed in these Special Provisions, and the plans is a suggestion only and is not intended to prevent the Contractor from proposing alternative construction sequencing.

Throughout the duration of the project, the existing roadway configuration shall be maintained (i.e., the number of lanes and their respective widths) except for restrictions to traffic allowed in the special provisions and addressed through approved TCPs. A restriction to traffic shall be considered any condition of the roadway surface or any work operation or traffic control setup that reduces the number of lanes or stops traffic. An approved TCP is required before any restriction to traffic is implemented.

Lane Closure Limitations

No restriction to traffic will be allowed during the times listed below:

1.	Friday from 3:00 PM to Saturday at 6:00 AM.

2.	Sunday from 12:00 noon to Sunday at 10:00 PM.

3.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 3:00 PM on the Friday before the holiday to 3:00 AM on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 3:00 PM on the Tuesday before the holiday to 3:00 AM on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 3:00 PM on the day before the holiday to 3:00 AM on the Monday after the holiday.

Contractor shall make every effort not to delay school buses through the construction work zone.

When lane restrictions are allowed by the specifications or the Engineer, lane restrictions shall be conducted so that no more than a 10 minute accumulated stopped delay is encountered by a motorist through the entire length of the project. During paving operations, a 20 minute delay will be allowed for all motorists. If a queue of traffic develops at a stop, the entire queue must be emptied.

Winter Shutdown

The traveled way of the Glenn Highway shall be paved by October 1, 1999 with temporary or permanent pavement. If the Contractor removes existing paving from a section of roadway that is being incorporated into the new alignment and fails to complete final paving of that section, he shall provide a 50 mm thick by 7.2 meter wide paved surface with painted traffic markings at his own expense. Removal of any temporary pavement and required reconditioning of base course shall also be subsidiary.

Eska Creek Bridge

Traffic shall be maintained at the location of the Eska Creek Bridge 542 by using a temporary detour bridge. This will require maintaining traffic at all times unless other restrictions to traffic are addressed through approved Traffic Control Plans.

The detour shall conform to the following requirements:

1.	The detour shall be designed to support HS 20-44 live loads with no overstress, and the Contractor's maximum construction equipment or vehicle load with an overstress less than 25 percent, whichever is greater. The detour bridge shall be a single span between abutments without a center pier.

2.	A clear roadway width of not less than 7.3 meters shall be provided for a double lane bridge.

3.	The detour bridge shall have portable concrete barrier or equivalent traffic protection device along the edges of the traveled way.

4.	The detour shall be so constructed that vehicular traffic can move safely through the construction area under its own power at all times.

5.	Materials used in the construction of the detour shall conform to the requirements of the applicable specifications.

6.	Sufficient waterway to allow passage of the maximum flow expected during the construction period shall be provided.

7.	The detour bridge shall have posted load limits.

8.	The detour and corresponding structure shall be designed and sealed by an Engineer registered in Alaska.

The Contractor shall submit drawings of the proposed temporary detour bridge and approaches to the Engineer prior to the beginning of the construction. No work on the detour shall begin without written approval of the Engineer.

643-3.09 INTERIM PAVEMENT MARKINGS. Permanent or Interim Pavement Markings in accordance with this subsection, details shown on the plans, approved traffic control plans, and Parts III and VI of the Alaska Traffic Manual shall be in place before existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments are opened to traffic for longer than one continuous work shift. This work may include restriping of the existing roadway prior to beginning construction of the project.

Conflicting pavement markings shall be removed in accordance with subsection 670-3.04, Paint Removal or covered with black removable preformed marking tape.

Sections of existing roadway that will be opened to traffic during the winter shall be marked at the same location as the existing lines and markings.

The Contractor shall maintain all Interim Pavement Markings for their intended life without additional compensation for any reapplication that may be required. There will be no compensation to upgrade Interim Pavement Markings required for work operations lasting up to 3 days to those required for work operations lasting up to 2 weeks.

Only temporary raised pavement markers or removable preformed retroreflective marking tape shall be used as Interim Pavement Markings on final pavement surfaces. When used they shall be completely removed and disposed of in conjunction with the placement of the final markings. The complete removal shall include any residual adhesive that might misguide motorists. Final pavement markings on finished pavement surfaces and interim pavement surfaces shall be in place before work is suspended for the winter.

Construction should be staged so that no traffic is routed over conflicting markings for more than one continuous workshift. If traffic is routed over conflicting markings during a workshift the roadway shall be delineated with a complement of warning signs, channelizing devices, and flaggers as required by the Alaska Traffic Manual.

Only temporary raised pavement markers conforming to Subsection 712-2.16 shall be used for interim pavement markings on seal coat and surface treatment pavements. The markers shall be installed in accordance with the manufacturers instructions prior to the application of the asphalt surface material and cover coat. The vinyl protective covers shall be removed after application of the asphalt pavement.

On multicourse surface treatments the temporary raised pavement markers shall be installed following the full width application of the first layer of cover coat. The markers shall be installed on each day's completed surface before the pilot car operations are removed and unescorted traffic is allowed on the surface treatment.

Final pavement markings shall not be placed until the seal coat or surface treatment has been opened to traffic for at least 14 days. Final pavement markings shall be applied within 10 days of the completion of the final sweeping or brooming of the mainline seal coat or surface treatment. Seal coat and surface treatment pavements are exempt from the two week requirement stated in short-term operations.

643-4.01 METHOD OF MEASUREMENT. During winter suspension of work no measurement of quantities will be made.

1.	Traffic Maintenance will be measured by the calendar day or lump sum and shall consist of all labor, materials and equipment required to provide the Worksite Traffic Supervisor, all required TCPs and public notices, the Construction Phasing Plan and maintenance of all roadways, approaches, crossings, intersections and pedestrian and bicycle facilities, as required.

2.	Traffic Control Devices will be measured by the units shown in the Traffic Control Rate Schedule. The quantities to be paid for shall be the number of units of each of the items, installed and accepted, in place. Construction Signs are regulatory, guide or construction warning signs for which there is a designation in the ASDS. Permanent Construction Signs shall be as detailed in the plans. All other signs will be considered Special Construction Signs. Flagger paddles will not be measured for payment.

Warning lights, high level warning devices, vertical panels and sign supports required for individual traffic control devices will be considered subsidiary to their respective bid item. If a subsidiary item is not installed and operational on a traffic control device when required, the respective device will not be measured for payment.

3.	Portable Concrete Barrier will be measured per each nominal 3 m section (± 0.3 m) placed to protect or channelize traffic as called for on the approved TCPs. Measurement for payment will be made for the initial placement and for each subsequent relocation when moved more than 3 m in any direction.

4.	Temporary Crash Cushions will be measured per each installation. Repair of temporary crash cushions will not be measured.

5.	Interim Pavement Markings will be measured by the single stripe station. A single stripe is a marking or a temporary raised pavement marker 100 mm in width. Wider striping will be measured as multiples of 100 mm. Centerline gaps will not be deducted from measurements. Installation of any word and symbol markings as well as the removal of the Interim Pavement Markings will be subsidiary to this item. The No-Passing Zone signing, as described in Subsection 643-3.09, will be subsidiary to this item.

6.	Flagging and Pilot Car will be measured by the hour but will be paid on a contingent sum basis at the rate shown below.

7.	Street Sweeping will be measured by the hour for the actual number of hours such operations were performed as approved by the Engineer. Time required to empty the sweeper will not be measured.

8.	Watering will be measured by the kiloliter of water applied. Weight measure or volume measure may be used at the discretion of the Engineer. If weight measure is used, the weight will be converted to kiloliters at 1.00 megagram per kiloliter for payment purposes. If volume measure is used, the volume will be converted to liters at 1.00 kiloliter per cubic meter for payment purposes.

9.	Portable Changeable Message Board Signs shall be measured by the calendar day for each sign used as shown on an approved TCP.

10.	Plastic Safety Fence, placed to protect or channelize pedestrian traffic as called for on an approved TCP, will be measured by the meter for the initial placement. Movement of the plastic safety fence to gain access to or from the work site shall not be measured and shall be subsidiary to the item.

11.	Temporary Sidewalk Surfacing, as called for on an approved TCP, will be measured by the square meter of plywood surface exposed for each placement. Overlaps will not be included in the measurement.

12.	Temporary Crossing will not be measured for payment.

Providing a 24-hour toll free (1-800-###-####) "hot-line road report" telephone with pre-recorded message, and providing weekly notices with daily updates will not be measured for payment but will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. The accepted quantities, determined as provided above, will be paid for at the contract price per unit of measurement, respectively, for each of the pay items listed below that are shown in the Bid Schedule, which price and payment shall be full compensation for the work prescribed in this section.

Items required by this specification that are not included on a unit price basis on the Bid Schedule or not included in other items shall be considered subsidiary to Item 643(1) or 643(2) Traffic Maintenance, except the following:

Traffic Price Adjustment

If Item 643(23), Traffic Price Adjustment, is shown on the Bid Schedule the total value of this contract will be adjusted as appropriate for lane restrictions, closures or delays in completing the directed work, as determined by the Engineer.

Payment for Item 643(27), Traffic Control Devices will be made for the pay unit of accepted traffic control devices (construction signs, barricades, traffic cones and/or tubular markers, drums, plastic safety fence, sequential arrow panels, portable changeable message board signs, special construction signs, portable concrete median barriers, pilot cars, temporary pavement markings, temporary crash cushions, temporary sidewalk surfacing, and watering) times the unit rate value contained in the Traffic Control Rate Schedule. A change order/directive is not required for the traffic control devices pay item.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion | Each | $2,500.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Plastic Safety Fence | Meter | $16.40 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Temporary Cover Markings | Station Station Station Station | $656.20 $4265.00 $492.00 $10,000.00 |

Payment for Item 643(15) Flagging, will be paid on a contingent sum basis at the rate of $32.00/hour. A change order/directive is not required for the flagging pay item.

Payment for Item 643(16) Pilot Car, will be paid on a contingent sum basis at the rate of $65.00/hour.

Payment for Item 643(30) Temporary Crossing, will include all labor, equipment and materials necessary to install, maintain, and remove the temporary bridge and approaches accepted by the Engineer. All temporary bridge elements are the property of the Contractor. Excavation, backfill and embankment required for the temporary crossing will be paid for under their respective pay items for select material and asphalt concrete pavement.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(1)	Traffic Maintenance	Calendar Day

643(3)	Permanent Construction Signs	Lump Sum

643(15)	Flagging	Contingent Sum

643(16)	Pilot Car	Contingent Sum

643(23)	Traffic Price Adjustment	Contingent Sum

643(27)	Traffic Control Devices	Contingent Sum

643(30)	Temporary Crossing	Lump Sum

(3/3/99)R222Mgz

SECTION 644

SERVICES TO BE FURNISHED BY THE

CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: The Contractor shall furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets..

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

10.	Located within 1600 meters of the project.

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete the sixth sentence of the first paragraph and substitute the following: The water supply shall consist of a 1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Delete the second paragraph and substitute the following: The laboratory shall include a concrete slab, 2.4 meters by 3 meters by 100 millimeters thick, suitable for mounting a Gilson shaker and other equipment. The slab shall be installed within an enclosed adjacent structure having a door, a window, a worktable, an exhaust fan, and adequate lighting and heat.

Add the following: The Contractor shall supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

R63aM

644-2.06 SCALES. Delete the first and second sentences and substitute the following: When the bid schedule calls for payment on a megagram basis for material, the Contractor shall furnish and maintain platform scales, scalehouse, and an electronic computerized weighing system, as hereinafter specified. A permanent certified commercial scale may be used with the Engineer's written approval. Belt conveyor scales are not acceptable for determining pay weight when the contract documents provide for payment on a megagram basis.

Delete the second paragraph and substitute the following: Sanitary lavatory facilities, heating, adequate electrical lighting and 120 volt, 60 cycle power shall be furnished to the scale house.

Delete paragraph three in its entirety.

Delete the fourth paragraph and substitute the following: Furnishing platform scales, tickets, scale house, and the electronic computerized weighing system, including all supplies such as: weigh tickets, paper, printer ribbons, diskettes, etc, and all maintenance and repair services necessary to keep the system functional, shall be supplied by the Contractor and are not a pay item but will be considered a subsidiary obligation. Platform scales, scale house and the electronic computerized weighing system shall remain the property of the Contractor upon completion of the work.

The Scales Diary is a bound book provided by the Engineer, to be completed by the Contractor’s scale person, that contains dates of action, type of material, source, time the scale opened and time the scale closed, times of scale balance, ticket sequence, time the haul for each material started and stopped, voided ticket numbers, truck numbers, times of tare and tare weights, and the scale person’s signature. In addition, the following information on any scale used to weigh materials for payment shall be provided in the Scale Diary:

a.	Owner of the scales, and scale locations.

b.	Manufacturer’s name, model serial number, maximum capacity, and type of scales (single beam, double beam, self-reading, etc).

c.	Date(s) the scales were installed and/or adjusted.

d.	Scale service company inspections and accuracy checks (attach copy).

e.	Division of Weights & Measures inspections and accuracy checks (attach copy).

f.	Time and dates of notification of any malfunctions.

The Scales Diary(ies) shall remain the property of the Engineer.

Delete the second sentence of the last paragraph and substitute the following: Platform scales shall include a weatherproof housing constructed in a manner that protects the recording equipment and allows the scale operator convenient access to the weigh indicator, scale computer, ticket printer, and the printer used to produce the Transaction Summary Report. All components of the platform scales which could be physically manipulated in a manner to alter weights shall be protected by sealed enclosures, acceptable to the Engineer.

Add the following: The Contractor shall provide an electronic computerized weighing system with the following capabilities:

COMPUTER

1.	The scale computer shall have the ability to store project numbers and all pay item descriptions for multiple projects and products which are weighed with the scale system.

The self-reading scale system shall include the scale load cell, a sealed direct reading weight indicator, scale computer, ticket printer, sequential Transaction Summary Report printer, and the ability to record a complete shift's transaction on a 3½-inch high density diskette.

The scale computer shall read the output data from the weight indicator without any unit conversion. If a conversion of pounds to kilograms is necessary, the Transaction Summary printer shall also print the Gross Vehicle Weight of each load in pounds for the Engineer's review of the metric conversion factor. The conversion factor shall be 907.1847 kg/ton. All individual parts of the system shall be compatible with each other and suitable for field conditions.

Unless prior written authorization is obtained from the Engineer, no payment will be allowed for any material weighed without using the electronic computerized weighing system.

2.	The scale computer shall store the following for each hauling vehicle utilized on the Project: vehicle identification number or the permanent commercial scales’ assigned unique vehicle identification number if so marked on the vehicle, the tractor license number, associated trailer license number(s) or the permanent commercial scales’ assigned unique vehicle identification number(s) if so marked on the trailer, tare weight, and maximum allowable vehicle weight (MAVW).

Vehicles shall be tared a minimum of once daily by the scale operator. The Engineer may request additional tares to be done at any time the scale is operational. The Engineer may also require that he be present when tares are done.

The MAVW shall be calculated by the Engineer and a listing of all vehicles and their MAVW(s) will be placed in the scalehouse by the Engineer. The MAVW will be the maximum allowable legal weight, as determined by the Engineer when overloads cannot be hauled in the traffic stream; the manufacturer's recommended maximum allowable gross vehicle weight as certified by the Contractor when on-road vehicles are allowed to haul overloads in the traffic stream; or an arbitrary number of 500 Mg when the Engineer allows unrestricted overloads out of the traffic stream.

The scale operator shall only utilize MAVWs which have been provided by the Engineer in writing. No tickets shall be issued to a vehicle until the Engineer provides the MAVW.

3.	During weighing operations, the electronic computerized weighing system shall compare each vehicle's gross weight to its MAVW. If the vehicle exceeds its MAVW the system shall alert the scale operator that an "overload" exists and the system shall not issue a ticket.

No payment will be made for any material hauled in a vehicle which is not in conformance with the requirements of Subsection 105-1.12, Load Restrictions, and this Subsection. Non-conforming vehicles shall dump sufficient material so that they conform, and then be reweighed.

4.	The computer system shall have a battery backup as well as protection for power surges or brown outs. The computer system shall be capable of retaining all stored data during a power outage and shall be operable during a power outage to allow shutdown of the hard drive without the loss of information.

TICKETS

The ticket printer furnished by the Contractor shall print a legible weigh ticket for the Engineer on continuous feed 10 kg paper with nominal dimensions of 215 mm by 140 mm, and with the following information on each ticket in the order listed:

a.	Sequential ticket number (8 digits, the first 3 digits being a Project code, the next being a product code [A, B, and C for the borrow classifications, D for Crushed Aggregate Base Course, E for asphalt, etc, as directed by the Engineer], and the last 4 digits being the sequential number for each product).

The permanent commercial scales may use “load number” to count the sequential loads for the Project. The load number shall be the different for each project and product hauled, and shall be reset to “O” at the beginning for each shift.

Whichever is used, this number shall be output to the data diskette given to the Engineer as Field 1, TKT.

b.	Project information (20 digits, the first 5 being the Project AKSAS number, the next 11 for the Project name, and the last 4 for a materials source reference).

c.	Date and Time of Dispatch (24 hour time).

d.	Pay Item name in words with "-Job Total", "-Shift Total", "-Daily Total", or "- Cumulative" Megagrams (Product Total This Ticket Sequence, Starting with "1", in megagrams, with each shift starting with “O”).

e.	Vehicle identification number, license number, and trailer license number(s). The permanent commercial scales may assign a permanently affixed tractor and trailer vehicle identification numbers, and shall maintain a current record of the corresponding license numbers.

f.	MAVW, as provided by the Engineer in writing.

g.	Gross weight in megagrams, rounded to the nearest megagram after conversion.

h.	Tare weight in megagrams, rounded to the nearest megagram after conversion.

I.	Net weight in megagrams, rounded to the nearest megagram after conversion.

All of the above items are to be printed by the ticket printer with a minimum of a 12 point font, and Items b. through c. above shall not be pre-printed. After printing, the weigh ticket shall be automatically advanced to a position where it can be torn off at a perforation and handed to the driver.

TRANSACTION SUMMARY REPORT PRINTER

The electronic computerized weighing system shall include a sequential Transaction Summary Report printer that will print out all transactions (keystrokes) made by the computer concurrently with the ticket printer. For permanent commercial scales, the Transaction Summary Report may be printed at the end of the company's daily shift with the Engineer's approval. The printer shall print all scales transactions including tares, voided tickets, and data changes made by the scale operator. The printer shall allow for the paper to be manually advanced so that the scale operator can write notes on the paper when special situations occur such as voided tickets, incorrect hauling unit number used, etc, which shall also be noted in the Scales Diary as provided under Subsection 109-1.02, Measurement of Quantities.

Transaction Summary Reports will be printed concurrently, or at the end of the shift in the case of a commercial scale if approved by the Engineer. The Report shall include the following information:

a.	Project number (first 5 characters of Field 11, PROJECT).

b.	Date (Field 2, DATE).

c.	Pay item.

d.	Materials source number (last 3 or first 2 characters of Field 10, PRODUCT, at the Engineer’s option).

e.	Sequential ticket number, or load number, at the Engineer’s option.

The sequential weigh ticket number shall be set to "1" at time 0:00 (12:00 pm) or prior to the first load being hauled at the beginning of each shift for each unique project number, pit number, and pay item combination. The project information, date, pay item, hauling unit identification number(s), their MAVW's, and the scale operator's name shall also be able to be set by the scale operator. Tare weights shall only be able to be changed by a tare weighing operation.

DATA DISKETTES

The electronic computerized weigh system shall also provide the Engineer with a 3½-inch high-density diskette at the end of the shift. The disk shall record all ticket information which was produced during the shift.

The data shall be stored in two files with the same information but different formats. The first file shall be in dBASE IV format (IBM) and shall be useable by the program without any conversion or manipulation. The naming convention for this file shall be "yymmdd.dbf". The second file shall be a raw data file in ASCII format with fields separated by commas, character fields enclosed in double quotes, a carriage return at the end of each record, and an end-of-file-mark following the last record. The naming convention for this file shall be "yymmdd.csv". If more than one scale is used on the Project, a scale location designation acceptable to the Engineer shall be utilized for the 7th and 8th characters of the filename.

If the Contractor is hauling from a permanent commercial scales operation, then the commercial vendor shall download his hard drive directly to a disk without conversion or manipulation at the end of the shift. He shall also provide conversion programs and training so that data can be converted into the information the Engineers requires.

In the event both data files on the diskette are not completely useable to obtain all truck weighing data, the Contractor shall correct, construct, or reconstruct the data file utilizing the sequential Transaction Summary Report or other information, as directed by the Engineer, as a data source. No payment will be made for any hauled material on a given date until an accurate "daily" data file has been delivered to the Engineer. If written permission is obtained from the Engineer to weigh without the electronic computerized weighing system for a minor equipment failure, a data file, acceptable to the Engineer, shall be constructed as described above.

The fields for each record shall be in the following format and order. Other data fields may also be provided but shall follow the fields in the required format.

| Field | Field Name | Type | Width |
| --- | --- | --- | --- |
| 1 | TKT | Character | 4 (right justified w/leading blanks) |
| 2 | DATE | Character | 8 (mm/dd/yy) |
| 3 | TIME | Character | 5 (hh:mm) (24 hour) |
| 4 | UNIT_ID | Character | 5 (right justified w/leading blanks) |
| 5 | MAVW | Numeric | 6 (kilograms) |
| 6 | GROSS | Numeric | 6 (kilograms) |
| 7 | TARE | Numeric | 6 (kilograms) |
| 8 | NET | Numeric | 6 (kilograms) |
| 9 | COMMENTS | Character | 20 |
| 10 | PRODUCT | Character | 20 |
| 11 | PROJECT | Character | 20 |
| 12 | GROSS | Numeric | 6 (pounds) |

The system shall be able to generate the summary Report, either during or at the end of the day or shift, which summarizes the number of loads and total net weight for each Date, Project, and Product. The original of the end of day Report shall be given to the Engineer at the end of each shift.

A user instructional manual shall be available for each scale which explains the complete scale operation. A copy of this manual shall be kept in each scalehouse and be available for review by the Engineer at all times.

In the event that extra construction engineering expenses are incurred due to checking non-machine data entries or other data irregularities, an amount equal to the value of those expenses will be deducted from the value of the item before payment.

(1/9/97)R145M

644-4.01 BASIS OF PAYMENT. Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

R63aM

Add the following Section:

SECTION 645

TRAINING PROGRAM

Special Provisions

645-1.01 DESCRIPTION. This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved. The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE. Training and upgrading of minorities and women toward journey status is the primary objective of this program. The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision. Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.1, located in the "green pages" of this document.

645-3.01 GENERAL. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive. Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor. Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed. It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project. Existing USDOL/BAT apprentices should already have a copy of their program. No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 WAGES. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period. Trainee wages shall be identified on Form 25A310. Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program. Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 SUBCONTRACTS. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor. Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate. However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-

compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls. There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section. Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT. Payment will be made at the contract unit price for each hour of training credited. Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project. No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or,

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry. Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program. Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits. The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program for	Labor Hour

3 Trainees/Apprentices

(10/29/91)S16

Add the following Section:

SECTION 646

EQUIPMENT RENTAL

Special Provisions

646-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a contingent sum basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

646-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

646-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

646-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listed in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer. Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

646-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

646-5.01 BASIS OF PAYMENT. Item 646(2) Wide Pad Dozer, 48-kW Min., will be paid on a contingent sum basis at the rate of $150.00 / hour.

The contingent price per hour for the equipment shown above shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

646(2)	Wide Pad Dozer, 48-kW Min.	Contingent Sum

(3/10/98)R15aM

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-1.01 DESCRIPTION. Delete the first sentence and substitute the following: This work shall consist of placing methylmethacrylate pavement markings as designated on the plans.

670-2.01 MATERIALS. Add the following: Markings shall conform to Subsection 712-2.17, Methylmethacrylate Pavement Markings.

Methylmethacrylate pavement markings shall be applied using an ambient temperature curing, two component methylmethacrylate system for application on either asphalt or cement concrete surfaces. The material shall be free from defects or imperfections which might adversely affect the serviceability of the finished product. It shall be free from dirt and other foreign material and cure to a tough serviceable film.

Glass beads for drop on application shall be those recommended in writing by the striping material manufacturer and as approved by the Engineer.

670-3.01 CONSTRUCTION REQUIREMENTS. Add the following after Item 3:

4.	Methylmethacrylate Pavement Markings.

A manufacturer's representative shall be present on the first day of striping and for all additional days required by the Engineer.

The Contractor shall only install the methylmethacrylate materials when the following conditions are met:

1.	New asphalt pavement has cured to the satisfaction of the manufacturer's representative.

2.	The asphalt pavement surface is thoroughly dry, and the pavement temperature is greater than 0 degrees Celsius and less than 40 degrees Celsius.

3.	The pavement is clean. Remove all dirt, oil, grease, and other foreign matter by approved methods from all pavement areas that will be painted.

The Contractor shall install the methylmethacrylate materials with spray type equipment mounted on a truck, using equipment approved by the Engineer. The equipment shall produce markings with clear-cut edges, a true and smooth alignment, and uniform film thickness. Use equipment made by a company experienced in the design and manufacture of truck mounted sprayers. Minimum requirements include the capability of striping two 100 mm yellow center lines and one 100 mm white edge line simultaneously.

The Contractor shall protect the markings with traffic control devices until they have sufficiently cured to prevent tracking by vehicles running over them. If the pavement markings are tracked, the Contractor shall remove the errant markings at his own expense regardless of who is at fault.

Apply transverse type methylmethacrylate markings at 3 mm thickness, measured without beads. This includes crosswalks, stop bars, symbols, transverse markings between gore and channelization striping, and legend markings.

Apply markings for lane lines, edge lines, and center lines at a thickness of 1.5 mm, measured without beads.

The Contractor shall complete test strips until the Engineer is satisfied with the yield rate.

From a mechanical dispenser, drop glass beads on the wet stripes at a uniform rate of 2.3 kilograms per liter of methylmethacrylate material. Mount the mechanical dispenser no more than 300 mm behind the spray nozzle.

670-4.01 METHOD OF MEASUREMENT. Add the following after Item 5:

6.	Liter Basis: The Engineer will measure the methylmethacrylate material used to form the pavement markings accepted by the Engineer in liters. The Department will limit the final quantity to 115% of the plan quantity.

670-5.01 BASIS OF PAYMENT. Add the following :For the accepted methylmethacrylate volume, the Department will pay the unit price bid to a maximum of 115% of the plan quantity.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

670(11)	Methylmethacrylate Pavement Markings	Liter

(10/12/98)R228M

Add the following section:

SECTION 680

TELEPHONE RELOCATION

Special Provisions

680-1.01 DESCRIPTION. This work shall consist of furnishing and installing telephone replacements and improvements, including all appurtenant facilities, as shown on the plans or as specified herein.

For the purpose of these specifications, “Telephone Utility” shall mean Matanuska Telephone Association (MTA), which owns and operates aerial and underground telephone distribution facilities along and crossing the Glenn Highway throughout the length of the project.

Matanuska Telephone Association

1740 South Chugach

Palmer, Alaska

907-745-9546

680-2.01 MATERIALS. Conduit materials furnished shall be in accordance with the applicable standards of ANSI, ASTM, NEMA, REA, RUS, UL, and all local codes and permits. Conduit components shall be installed in accordance with applicable requirements of the NEC. In case of a conflict between the requirements of any of the above referenced codes and standards and these specifications, the requirements of these specifications shall govern. All materials, devices, and practices shall be in accordance with the applicable requirements of the Federal “Occupational Safety and Health Standards.”

All rigid metal conduit shall be 100 mm in diameter and in accordance with the subsection 660-2.05 Conduit.

All high density polyethylene conduit (HDPE) conduit shall be 100 mm in diameter and have a minimum wall thickness in accordance with SDR-13.5 (.33) ASTM D-3035 for a 100 mm HDPE conduit, and shall be orange in color.

All polyvinyl chloride (PVC) conduit shall be 100 mm in diameter and be a schedule 40 in accordance with ASTM D-2447.

Nylon pull cords shall be 6.35 mm (.025-inch), 226.8 kg (500 lb) rated cord that shall be left in all 100 mm conduit crossings. Plastic end plugs shall be approved by MTA prior to installation.

680-3.01 GENERAL CONSTRUCTION REQUIREMENTS. MTA, through the Engineer, reserves the right to suspend the conduit installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections. Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle him to extra payment for costs incurred.

The Contractor shall be responsible for the location, shoring, and protecting of all property (real and personal), in the vicinity of the roadway crossings within the project. It shall be the Contractor’s responsibility to establish the location of each facility by calling for field locates in accordance with subsection 105-1.06, Cooperation with Utilities.

The conduit locations are approximate only, and must be field located and confirmed with the Engineer and MTA Engineering prior to starting work.

All temporary bridging for traffic utilized by the Contractor shall be inspected and approved by the Engineer prior to installation. This does not relieve the Contractor of responsibility for providing bridging of sufficient size and strength. Any bridging open to public traffic will provide a smooth driving joint.

The minimum depth of bury for each conduit crossing is 1.2 meters ( four feet) below the finished pavement grade to top of duct, or below ditch bottom grade, whichever is deeper. The ends of each conduit crossing shall be covered with end caps in such a way that material will not enter the conduits. The Contractor shall coordinate with MTA Engineering to obtain EMS locators to be placed above the ends of each conduit crossing prior to backfill as detailed on the plans. Locators can be obtained at MTA’s Palmer Office, 1740 South Chugach Street. In addition, the Contractor shall, through the Engineer, provide MTA with the schedule for each crossing a minimum of three calendar days in advance of construction.

680-3.02 GENERAL CONDUIT INSTALLATION REQUIREMENTS FOR ROAD CROSSINGS. The road crossings shall be installed in accordance with the MTA Conduit Crossing detail shown in the plans. The conduit shall be trenched, bored, jacked or otherwise forced underneath the highway, or the conduit may be installed in a casing.

Polyvinyl chloride conduit shall be installed in accordance with the following requirements:

Joints shall be solvent cement type as recommended by the conduit manufacturer. The contact surfaces of the conduit and fitting shall be cleaned with solvent, methyl ethyl ketone or acetone, then liberally coated with solvent cement, promptly and fully engaged, and either conduit or fitting rotated approximately ¼ turn to dispel any air and evenly distribute solvent cement over contact surfaces. Total elapsed time between the start of cement application to the surface being joined and final assembly of joint shall not exceed 60 seconds. The initial strength of the joint will permit continuous conduit installation. However, additional stress at the joint shall be avoided for at least 24 hours after joining.

Rigid galvanized steel conduit shall be installed in accordance with these specifications.

High Density Polyethylene Duct (HDPE) shall be one continuous piece.

Plastic pipe shall be shaded from sunlight as required to prevent curvature and deterioration due to thermal expansion and exposure to sunlight.

Defective conduit shall not be installed and shall be removed immediately from the site of work.

680-3.03 CONDUIT ROAD CROSSING USING A CASING. There shall be no space between the earth and the outside of the conduit or casing pipe. No wet bores will be permitted. Only enough water to lubricate the casing during installation may be used.

Casing pipe shall be installed using jacking equipment. Casing shall be installed such that the hole is cased as the earth is removed through the interior of the casing.

Boring without the concurrent installation of the casing pipe will not be permitted. The installation shall be performed in a manner that will neither disrupt traffic nor damage the subgrade, and will provide accurate alignment and grade of pipe.

Smooth wall casing pipe shall be new and fabricated from welded steel. The diameter and wall thickness shall be selected by the Contractor to allow for the type of materials encountered.

Joints in the casing pipe shall be welded. Pipe ends shall be welded. Pipe ends shall be machine cut and beveled at an angle of 37 ½ degrees. The beveled ends shall be butted and aligned axially and welded to provide a full strength joint capable of resisting all stresses, including jacking stresses.

Before starting work on a crossing that will be using any type of boring equipment, the Contractor shall submit complete details of his proposed methods, materials, and time schedule to the Engineer. Work shall not begin until written notification to proceed has been obtained from the Engineer.

Casing pipe shall have an inside diameter that will accommodate a 100 mm conduit, and the conduit couplings that connect the lengths of conduit. Alignment of the bore casing shall be within .61 meters (2 feet) of the staked requirements per 30 meters of casing installed. At no time shall the depth of the bore be less than indicated on the plans. The successful bore shall meet the above requirements and allow for 97% utilization of the ordered size bore to be considered successful.

Upon completion of the boring and the installation of the conduit, the Contractor shall clean and test the conduit. Conduit which is not used or tested immediately shall be plugged at each end. Prior to starting the testing of the conduit crossing placed by directional boring, the Contractor shall notify MTA five (5) calendar days in advance of testing.

The Contractor shall coordinate with MTA so that when testing is started and completed that an MTA inspector is on site for the testing of the directional bore conduit installation. As a clearance test, the conduit shall pass a rigid mandrel with a length not less than .30 meter (12-inches) and a diameter of 6.35 mm (1/4-inch) less than the inside diameter of the conduit. All foreign material, earth, sand, and gravel, shall be removed from the conduit.

680-3.05 BACKFILL AND COMPACTION. Backfill shall be in accordance to Section 203, Excavation and Embankment. All backfill for the conduit crossings shall be in 200 mm (8-inch) lifts to 95 percent of the maximum density.

Backfill to the bottom of trench grade, if necessary, shall be compacted in 200 mm (8-inch) lifts with material meeting the requirements of Selected Material, Type A. If large quantities of water are evident, the Contractor may elect to install backfill with 60 mm to 153 mm (2” to 6”) course oversized rock overlaid with geotextile. Compaction shall be by a minimum of six full width coverages with a mechanical compactor. The conduit shall then be placed on a 100 mm sand bedding on the trench bottom, with the sand being water compacted to 100 mm above the conduit. The Contractor shall then use such materials as have been excavated from the trench that meet the requirements of Select Material, Type C, above the conduit sand bedding, up to the bottom of the roadway structural section.

The soil compaction of the trenches shall be randomly tested at various depths by the Engineer.

The existing asphalt pavement shall be replaced in accordance with Section 401, Asphalt Concrete Pavement.

Patching roadway crossing areas after the installation of the conduit crossing shall be done within two calendar days after the completion of the roadway crossing or as approved by the Engineer. The Contractor shall maintain the roadway surface in the conduit crossing locations in such a manner that traffic is not impeded, as directed and approved by the Engineer, until the roadway crossings are paved.

680-3.06 SURVEYING AND STAKING. Crossings are approximate station only and each crossing will need to be field located and confirmed with the Engineer and MTA engineering personnel prior to starting work.

The Contractor shall as-built each crossing. The elevation of the finish grade, project centerline at the crossing location and at the end of each conduit crossing shall be recorded. In addition, the distance left and right of the project centerline of each crossing will also be referenced. Location and elevation information for each conduit crossing will be documented by a Registered Land Surveyor, and be provided to the Engineer.

680-4.01 METHOD OF MEASUREMENT. Item 680(1) 100 mm Telephone Conduit Installation, shall be measured by the meter of conduit installed.

680-5.01 BASIS OF PAYMENT. Crossings may be trenched, jacked or bored at the Contractor’s option. Jacking or boring in lieu of trenching shall not be a basis for extra payment.

If open trenching is used for the installation of the 100 mm conduit crossings, the backfill materials shall be considered subsidiary to the conduit installation.

If unsuitable material is encountered and excavated .61 meters (2 feet) below the conduit, and Select Material, Type A is placed as bedding, the excavation will be subsidiary to Item 203(6A) Borrow, Type A. In addition, the costs for as-builts, placing end caps, installing pull cords, and placement of EMS markers will not be paid directly, but will be subsidiary to the conduit installation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

680(1)	100 mm Telephone Conduit Installation	Meter

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 50-79 |
| 4.75 mm | 35-58 |
| 2.36 mm | 20-47 |
| 600 µm | 10-26 |
| 300 µm | 6-19 |
| 75 µm | 0-6 |

(11/04/94)R117M

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT. Replace this subsection with the following:

Coarse Aggregate. Coarse aggregate (that material retained on the 4.75 mm Sieve) shall be crushed stone or crushed gravel and shall consist of sound, tough, durable rock of uniform quality. All material shall be free from clay balls, vegetative matter or other deleterious matters. Coarse aggregate shall not be coated with dirt or other finely divided mineral matter. In addition, coarse aggregate shall meet the following requirements:

| Percent of Wear | AASHTO T 96 | 45 max. |
| --- | --- | --- |
| Degradation Value | ATM T-13 | 30 min. |
| Percent Sodium Sulfate loss | AASHTO T 104 | 9 max. (5 cycles) |
| Percent Fracture | ATM T-4 | 90 min. Single face (Type IIA) 80 min. Single face (Type IIB) |
| Thin-Elongated pieces | ATM T-9 | 8% max. |

Fine Aggregate. Fine aggregate (passing the 4.75 mm sieve) shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness Test.

Blended Aggregate. The several aggregate fractions for the mixture shall be sized, graded, and combined in such proportions that the resulting composite blend conforms to the grading requirements of Table 703-3. The fraction actually retained between any two consecutive sieves larger than the 150 μm shall be not less than 2 percent of the total. The size of samples for extraction will be in conformance with AASHTO T 164. Extracted gradations will be determined according to AASHTO T 30.

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT

CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| Sieve Designation | Gradation Designation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III |
| 25 mm | 100 | - | - |
| 19 mm | 75-90 | 100 | - |
| 12.5 mm | 60-86 | 75-90 | 100 |
| 9.5 mm | 50-78 | 60-84 | 75-90 |
| 4.75 mm | 34-62 | 33-70 | 50-78 |
| 2.36 mm | 24-52 | 19-56 | 32-60 |
| 1.18 mm | 16-42 | 10-44 | 20-45 |
| 600 μm | 10-32 | 7-34 | 12-34 |
| 300 μm | 8-24 | 5-24 | 8-24 |
| 150 μm | 5-16 | 4-16 | 4-15 |
| 75 μm | 3-8 | 3-7 | 3-8 |

(4/24/98)R200M

703-2.07 SELECTED MATERIAL. Add the following to Item 1., Selected material, type A: It shall have 20 to 55 percent by weight of particles passing the 4.75 mm sieve.

In Item 2., Selected material, type B, delete the third sentence and replace with the following: It shall consist of not more than 25 % by weight of particles that pass the 75 µm sieve as determined by ATM T-7.

Add the following:

4.	Selected material, type D, shall consist of earth, sand, gravel or rock materials obtained from the excavation, and shall contain no wood, concrete or other debris.

(12/13/96)R89M

703-2.10 POROUS BACKFILL MATERIAL. Replace Table 703-7 with the following:

TABLE 703-7

REQUIREMENTS FOR GRADING FOR

POROUS BACKFILL MATERIAL

| Sieve Designation | Percent by Weight Passing |
| --- | --- |
| 37.5 mm | 100 |
| 25 mm | 95-100 |
| 12.5 mm | 25-60 |
| 4.75 mm | 0-10 |
| 2.36 mm | 0-5 |

(7/6/95)R10M

SECTION 712

MISCELLANEOUS

Special Provisions

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

Quality Requirements: The markings shall be formulated and manufactured from new materials. It shall be free from defects and imperfections that might adversely affect the serviceability of the finished product. It shall be free from dirt and other foreign material and cure within the time specified to a tough serviceable film. Part "A" resin system shall be methyl methacrylate based. Part "B" shall be benzoyl peroxide in liquid plasticizer.

The quality of material supplied shall be that of Dura-Stripe Type V or equal.

Performance Properties:

Viscosity: 5 - 12 Pa sec (ASTM D2196 Method B, LV Model, Spindle #4 at 60 RPM.

No Tract Time: Material shall be track free after 15 minutes when applied at 1 mm (ASTM D711).

Hardness: Shore Durometer, A-1, 80 minimum after 24 hours.

Tensile Strength: At break, minimum 862 kPa (ASTM D638)

Percent Elongation: Minimum 20% (ASTM D638).

Water Absorption: Maximum 0.5% (ASTM D570).

Chemical Resistance: Seven day immersion

Anti-freeze			No effect

Motor Oil			No effect

Diesel Fuel			No effect

Gasoline			No effect

Calcium Chloride		No effect

Sodium Chloride		No effect

Transmission Fluid		No effect

The marking compound shall be resistant to the effects of ultra-violet light.

Adhesion: To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

Skid Resistance: Minimum 45 (ASTM E303) in units (British pendulum).

Reflectivity: Initial, minimum 200 millicandella (as applied).

Composition: The composition is at the discretion of the manufacturer, but shall be essentially comprised of resins, reactive monomers, pigments, aggregate and glass beads. When mixed in the stated ratio, the material shall cure to 99% minimum by weight and volume solids.

(6/16/98)R221M

Delete this section in it's entirety and substitute with the following:

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL. Topsoil furnished by the Contractor may consist of the existing, natural organic blanket representative of the project area. A quality test, as defined by ATM T-6, shall be performed on the soil to determine the organic content of the soil. The results shall be supplied to the Engineer.

If the soil is found to have an organic content of 5% or more the soil may be reused and spread on the finished slopes where topsoil is noted on the plans. Roots, stumps, unnatural material, and rocks greater than 75 mm in diameter shall be removed from the organic material before it is graded onto the finished slope.

If the soil is found to have an organic content of less 5% the soil cannot be used as topsoil for the project. In that case the Contractor shall furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5% or more, as determined by ATM T-6. The material shall be reasonably free from roots, clods, hard clay, rocks greater than 75 mm in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free-draining and non-toxic. The Contractor shall notify the Engineer of the location from which he proposes to furnish topsoil at least 30 calendar days prior to delivery of topsoil to the project from that location. The topsoil and its sources will be inspected by the Engineer before approval will be granted for its use.

(11/8/95)R208M

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Recycled Paper (“wood cellulose”) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch. Blended mulch may contain up to 50% recycled paper. Mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors. The mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry. The mulch shall be of a texture such that it can be applied uniformly to the soil surface. Mulch shall not create a hard crust upon drying and shall have moisture absorption and retention properties as well as the ability to hold grass seed in contact with the soil.

The mulch shall be shipped in packages of uniform weight (plus or minus 5%) bearing the name of the manufacturer and the air-dry weight content.

The mulch shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial tackifier shall be used on all seeded areas. The amount added will be as recommended by the manufacturer.

(2/19/99)R206

Add the following subsection:

727-2.04 HYDRO MATTING. Hydro matting shall be a hydraulically applied system of long strand fibers joined together by a high-strength adhesive to create a continuous three dimensional blanket that adheres to the soil surface to form a bonded fiber matrix. The system shall be applied to the soil as a viscous mixture, which upon drying, creates a high strength, porous and erosion resistant mat. Upon drying, the matrix shall not inhibit the germination and growth of plants beneath the layer. The matrix shall retain its form despite rewetting.

(6/30/97)R223M

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT. Delete the first sentence and substitute the following: Geotextile materials for embankment separation shall meet the requirements of AASHTO M 288 for Separation (medium survivability). The Apparent Opening Size (AOS) of the fabric shall be less than 0.6 mm.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL. Delete the first sentence and substitute the following: Geotextile materials for subsurface drainage shall meet the requirements of AASHTO M 288 for Subsurface Drainage. The fabric shall be a Class B material. The Apparent Opening Size (AOS) of the fabric shall be less than 0.297 mm.

Geotextile materials for riprap liner shall meet the requirements of AASHTO M 288 for Class A Erosion Control. The fabric shall be a Class A material. The Apparent Opening Size (AOS) of the fabric shall be less than 0.6 mm.

729-2.04 SEDIMENT CONTROL. Delete this subsection in its entirety and substitute the following: Geotextile materials for Sediment Control shall meet the requirements of AASHTO M 288 for Sediment Control. The Apparent Opening Size (AOS) of the fabric shall be less than 0.84 mm.

R229M

729-2.06 GEOCOMPOSITE DRAIN. Add the following subsection: The geocomposite drain shall consist of a structural core providing in-plane high flow capacity under cross-plane compressive stress with the following properties:

| Property | Test Method | Requirement |
| --- | --- | --- |
| Thickness (cross-plane) 10 kPa loading | ASTM D-1777 | 5 mm, min. |
| Crushing Strength (cross-plane) | ASTM D-1621 | 250 kPa, min. |
| Transmissivity (in-plane) 0.25 drainage gradient 100 kPa pressure | ASTM D-4716 | 8 gal/min/ft, min. |

(12/23/96)R97M

SECTION 730

SIGN MATERIALS

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Under Item 2., Perforated Steel Posts, in the first sentence of paragraph a, change “ASTM A 446" to read “ASTM A653 and ASTM A924".

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(1/7/99)R81M

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS (METRIC)