- ESCROW OF PROPOSAL DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF PROPOSAL DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE PROPOSAL AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE PROPOSAL PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

CREscrow-050509

- SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition ($25.00).

b.	Alaska Test Methods Manual (Lab & Field), April 30, 2012 Edition ($25.00). Available online at:

http://www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/pop_testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, February, 2011.

http://www.dot.state.ak.us/stwddes/desenviron/pop_swppp.shtml

d.	Quantity Computations

e.	Cross Sections

f.	Geotechnical Report, Centerline Investigation – Aleknagik Wood River Bridge Design (1902), July 2011, By State of Alaska DOT&PF Central Region Materials Section.

g.	Foundation Geology Report – Wood River Bridge No. 1902, July 2011, By State of Alaska DOT&PF Statewide Geotechnical Services.

h.	Geotechnical Foundation Engineering Report, Wood River Bridge (No. 1902), January 2013, By R & M Consultants, Inc.

j.	Erosion, Sediment Control Plan (ESCP) – Aleknagik Wood River Bridge Construction, Phase I 	0001(458)/52972	February, 2013.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix C.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Laborers Mechanics Minimum Rate of Pay.  The current Laborers Mechanics Minimum Rate of Pay contains information on remote sites and per diem.  The Department of Labor has issued WHPL #197, which further clarifies this requirement.  See pay item 640(4).

- 5.	Section 120, Disadvantaged Business Enterprise (DBE) Program.  Effective for FHWA funded projects advertised on or after March 5, 2012, there is a revised Statewide Special Provision for Section 120 DBE Program, revised DBE forms, and other revised construction contract forms.  Contractors are encouraged to review the construction contract forms and the revised Statewide Special Provision for Section 120 DBE Program which includes changes to timelines for submission of the DBE Utilization Report and DBE Good Faith Effort documentation, if applicable.  See also the revised Required Documents form, 25D-4A.

- Any questions about this notice may be directed to Dennis Good, Manager of the Civil Rights Office, (907) 269-0848, or email dennis.good@alaska.gov.

- 6.	DBE Program Waiver - Central Region Projects.  The US DOT Waiver for the DBE Program has been implemented on Central Region Projects since August 1, 2011.  The DBE Program Waiver approved by USDOT addresses the issue identified in the Department's Disparity Study which found that DBE firms that are owned by Non-Minority Women were participating on the Department's construction contracts and subcontracts on an equal basis similar to other non-DBE contractors and non-DBE subcontractors for Central Region only.

- As a result, DBE contract goals cannot be met through the use of female caucasian owned DBEs.  This Waiver does not affect DBE project goals for airports or transit projects anywhere in Alaska, and does not apply to professional service agreements or highway construction projects in Northern or Southeast Regions.

- The decision to continue or discontinue the use of the Waiver will be made on an annual basis.

- Any questions about this notice may be directed to Dennis Good, Manager of the Civil Rights Office, (907) 269-0848, or email dennis.good@alaska.gov.

7.	Section 645 Training Program.  Effective for FHWA funded projects advertised on or after May 20, 2012 there is a revised Statewide Special Provision for Section 645 Training Program and revised construction contract forms.  Contractors are encouraged to review the new construction contract forms 25A-312 Apprentice Employment Report and 25A-313 Monthly Training Report and the revised Statewide Special Provision for Section 645 Training Program.  See also the revised Required Documents form, 25D-4A.

- Any question about this notice shall be directed to Norma M Lucero, Statewide Support Services Coordinator - Civil Rights Office, (907) 269-0844, or email norma.lucero@alaska.gov.

8.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

9.	High Visibility Clothing.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See subsection 643-3.11.

- 10.	Interim Completion Date.  The interim completion date for the placement of all roadway embankment, as directed by the Engineer, is October 31, 2014.  Refer to Subsection 105-1.19 Interim Completion for further information.

11.	Section 644 Services To Be Furnished By The Contractor.  644-2.09 Image Documentation is new to Section 644.

12.	Local Hire.  The contractor is encouraged to contact Administrator Kay Andrews, or Clerk Jeri Alakayak with the Aleknagik Community Job Bank (at the contact information below) for any potential employment of local residents during construction of this project.

Aleknagik Community Job Bank

City of Aleknagik

P.O. Box 33

Aleknagik, Alaska 99555

Contact Phones:  (907) 842-5953 or 842-2528

Facsimile:  (907) 842-2107

0001(458)/52972-080913

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

- SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.

PLANS.  Delete Text of PLANS and replace with:

The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32-012707

Add the following definition:

QUALIFIED PRODUCTS LIST.  A list of companies and products that the Department has found conforms to the SSHC.

E36-012707

Insert the following definition after RESPONSIVE BID:

RETAINAGE.  A percentage of a payment established in advance under a contract or subcontract to be withheld from progress payment due on the contract or subcontract.  Payment or a percentage of payment withheld for unsatisfactory performance is not retainage.

E101-030512

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22-010106

- SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.

Replace the second paragraph with the following:

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23-010106

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after:

“If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18-063004

- SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these Costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check, made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65-022309

SECTION 104

SCOPE OF WORK

Standard Modifications

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence, or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58-072808

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete:

"(24"x36")" and replace with: (22"x34")

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after:

"Work performed and materials furnished shall conform to the Plans and Specifications" add:  and approved Working Drawings,

In the first sentence of the second paragraph after: "All work or material not conforming to the Plans and Specifications" add: and approved Working Drawings,

E33-012707

Special Provisions

105-1.06 UTILITIES.  Add the following:

Call the following utilities and agencies directly:

City of Dillingham, Department of Public Works	(907) 842-4592

Nushagak Cooperative	(907) 842-5251

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

Utilities Relocated by Others.

Utilities will be relocated by others concurrently with construction of this project.  The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.  For utilities being relocated, the Contractor will:

- Include utility work on the Construction Phasing Plan and Progress Schedule.

2.	Provide erosion, sediment, and pollution control including the stabilization of 	areas disturbed during utility work.  Identify all utility companies performing 	ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP). 	 Refer to Section 641 for further information.

3.	Clear and grub.  Payment will be made under Section 201, Clearing and Grubbing.

4.	Provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance.

5	Provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either Right Of Way or Centerline staking with Station information,

	Slope staking,

	Proposed structures, not including utilities to be relocated by others.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

Work done by utility owner(s) is as follows:

Nushagak Electric Cooperative (NEC) and Nushagak Telephone Cooperative (NTC) own and operate aerial and underground facilities along and crossing Suravak road.

NEC and NTC underground facilities are in conflict with road reconstruction between stations 74+00 and 77+00.

Coordinate clearing, excavation and grading activities with NEC and NTC to allow for relocation of electrical and telephone facilities, as follows;

- NTC- Relocate telephone cables along right of way on project left from BOP to station 76+00 left.

Allow NTC seven (7) calendar days to complete the relocation.

- NEC- Relocate underground electrical facility to an overhead electrical facility between stations 76+00 and 77+00.

Allow NEC seven (7) calendar days to complete the relocation.

0001(458)/52972-053013

Standard Modification

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following at the end of this subsection:

Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer's opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33-012707

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:

“Subsection 621-3.04” and replace with:  Subsection 618-3.06 and 621-3.04.

E59-072808

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. Modify the first paragraph, Item 4. after:

“DOLWD” add: and State Department of Revenue.

E19-063004

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:

Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.

CR93-032101

Standard Modification

Add the following Subsection 105-1.18:

105-1.18 RESERVED FOR WARRANTIES.

E33-012707

Special Provision

Add the following Subsection 105-1.19:

105-1.19 INTERIM COMPLETION.  This project includes one interim completion phase.

Interim Completion Phase:

Date:	31 October, 2014

Work:	Complete placement of all roadway embankment, as directed by the Engineer, by the interim completion date.

0001(458)/52972-080913

SECTION 106

CONTROL OF MATERIAL

Standard Modifications

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text. “Approved Products List” and replace with:  Qualified Products List

E36-012707

Special Provision

Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and submit a completed Material Origin Certificate, Form 25D-60, before award of the Contract.

Steel and iron products, which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the Project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating process must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

CR13-020705

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient, Useable Excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:

The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:

When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:

Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material source or any portion of a material source, at any time after Contract Award that is determined by material testing to be unsuitable for use on the Project.

E24-010106

Add new Subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified Project document.  The Contractor shall fill it out sequentially by bid Item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation, and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department of a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract Item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract Item.

When material invoices, freight bills, and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); Project name and number where material will be incorporated, manufacturer, product number, quantity and cost.

Add the following Subsection 106-1.09:

106-1.09 RESERVED.

E34-012707

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.

The Department will:  Add No. 3.:

3.	The Department has received the following permits on the Contractor’s behalf:

a.	USCG Section 9 Bridge Permit

b.	ADF&G Fish Habitat Permit (Individual permits issued for Mission Creek, Wood River and Unnamed Pond)

c.	ADNR Temporary Water Use Permit (one permit issued authorizing water use from Lake Aleknagik, Wood River and Unnamed Pond)

d.	USACE Section 404/10 Permit (Work authorized under USACE Nationwide Permits 14 and 15)

e.	ADEC Section 401 Water Quality Certification

f.	ADNR SHPO Concurrence (Finding of no historic properties adversely affected)

The Contractor shall:  Add the following:

9.	Obtain through the Engineer a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling, or staging, on or off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

10.	Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual, and the Regional Supplement to the Corps of Engineers Wetland Delineations Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

11.	Provide information to comply with the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

12.	USCG Section 9 Bridge Permit General Notes:  Condition 6 of the permit requires that the contractor submit plans of a temporary bridge (spans shore to shore) or a temporary work trestle (does not span shore to shore) to the USCG for review.  This submittal involves a simple plan and cross-section, showing the minimum horizontal and vertical clearances, on 8.5x11 sheets.  The plan(s) do not need to be stamped by a professional engineer.  Plan review and approval of a temporary bridge or trestle will be completed in-house at the USCG Juneau office.  Once submitted, the plans should be approved in approximately 1 week.

Condition 4 Bridge fendering system and Condition 5 Clearance Gauges are not required for this project.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also, provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

0001(458)/52972-062113

- Standard Modifications

107-1.05 FEDERAL AID PROVISIONS.  Add the following after paragraph two:

Add the following:

Form 25D-55H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the Contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds.  Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements.  During the performance of this Contract, the Contractor, for itself, its assignees and successors in interest (hereinafter referred to as the "Contractor") agrees as follows:

(1)	Compliance with Regulations:  The Contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this Contract.

(2)	Nondiscrimination:  The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The Contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, Section 21.5 of the regulations, including employment practices when the Contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitation for Subcontractors, Including Procurements of Materials and Equipment:  In all solicitations either by competitive bidding or negotiation made by the Contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the Contractor of the Contractor's obligations under this Contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports:  The Contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions.  Where any information required of a Contractor is in the exclusive possession of another who fails or refuses to furnish this information the Contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance:  In the event of the Contractor's noncompliance with the nondiscrimination provisions of this Contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a)	withholding of payments to the Contractor under the Contract until the Contractor complies, and/or

(b)	cancellation, termination, or suspension of the Contract, in whole or in part.

(6)	Incorporation of Provisions:  The Contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The Contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance:  Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the Contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the Contractor may request the United states to enter into such litigation to protect the interests of the United States.

E67-101509

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:

When operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANSDCAPE.  Add the following:

If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR1072-042313

Standard Modification

Add the following paragraphs:

7.	Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:

Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization, the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35-012707

Add the following:

Bald Eagles are protected under the Bald Eagle Protection Act (16 U.S.C. 668-668c) which prohibits “takes” of bald eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of a minimum 330 ft as an undisturbed habitat buffer around nesting bald eagles.  If topography or vegetation does not provide an adequate screen or separation, extend this buffer to 0.25 miles, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330 ft and 660 ft from eagles nest tree no obtrusive facilities or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, this buffer shall extend up to 0.5 miles.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (March 1 – August 31) within the primary or secondary zones.

Extremely noisy activities such as road construction or other activities that occur within the Secondary Zone shall be conducted outside the nesting period to avoid disturbance to eagles.  If activities occur in proximity to a nest site, employ an individual qualified to observe and assess the impact of such activities on nesting eagles.  Behavior generally associated with disturbed eagles includes alarm calls, birds flushed from their nest or perch, and aggressiveness.

If nest trees are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 786-3503 or (907) 271–2772, before starting construction activities, for further site evaluation.  This is an advisory.  Do what is required to keep from disturbing a nesting eagle.

CR1071-081210

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity Disadvantaged Business Enterprise and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A 301

EEO-1 Certification	Form 25A 304

ADOT&PF Training Program Request	Form 25A 310

Training Utilization Report	Form 25A 311

Contact Report	Form 25A 321A

DBE Subcontractable Items	Form 25A 324

DBE Utilization Report	Form 25A 325C

Summary of Good Faith Effort Documentation	Form 25A 332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D 55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

S80-012202

- SECTION 108

PROSECUTION AND PROGRESS

Standard Modification

Delete Subsection 108-1.01 in its entirety and replace with the following:

108-1.01 SUBCONTRACTING OF CONTRACT.  The Contractor shall submit a Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or any subcontractor subcontracts, sells, transfers, assigns, or otherwise disposes of the Contract or any portion of the Contract.  The Department has authority to review subcontracts and to deny permission to subcontract work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

The Contractor shall perform, with the Contractor's own organization, work amounting to at least 30 percent of the difference between the original Contract price and the price of designated Specialty Items.  For the purpose of this Subsection, work is defined as the dollar value of the services, equipment, materials, and manufactured products furnished under the Contract.  The Engineer will determine the value of the subcontracts based on Contract unit prices or upon reasonable value, if entire items are not subcontracted.

The Department's consent to the subcontracting, sale, transfer, assignment, or disposal of all or a part of the Contract shall not relieve the Contractor and the Surety of responsibility for fulfillment of the Contract or for liability under bonds regardless of the terms of the transfer or sublet approvals.

1.	The Contractor shall ensure that for all subcontracts (agreements):

a.	The Department is furnished with one completed Contractor Self Certification, Form 25D-042, for each subcontract;

b.	The subcontractors have submitted a Bidder Registration; Form 25D-6;

c.	The required prompt payment provisions of AS 36.90.210 are included in all subcontracts;

d.	A clause is included requiring the Contractor to pay the subcontractor for satisfactory performance according to AS 36.90.210 and within eight (8) working days after receiving payment for which the subcontractor is to be paid.

e.	A clause is included requiring the Contractor to pay the subcontractor interest, according to AS 45.45.100(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made;

f.	A clause is included requiring the Contractor to pay the subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received from the Department, or after the notice period under AS 36.25.020(b) expires, whichever is later;

g.	A clause is included requiring the Contractor to pay interest on retainage, according to AS 36.90.250 and AS 45.45.101(a);

h.	Other required items listed in Form 25D-042 are included in the subcontracts;

i.	The subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

j.	Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

2.	The Contractor shall ensure that for all lower tier subcontracts (agreements between subcontractors and lower tier subcontractors):

a.	The required prompt payment provisions of AS 36.90.210 are included in all lower tier subcontracts;

b.	A clause is included requiring the subcontractor to pay the lower tier subcontractor for satisfactory performance according to AS 36.90.210, and within eight (8) working days after receiving payment from which the subcontractor is to be paid;

c.	A clause is included requiring the subcontractor to pay the lower tier subcontractor interest, according to AS 45.45.010(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made;

d.	A clause is included requiring the subcontractor to pay the lower tier subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received, or after the notice period under AS 36.25.020(b) expires, whichever is later;

e.	A clause is included requiring the subcontractor to pay the lower tier subcontractor interest on retainage, according to AS 36.90.250 and AS 45.45.101(a);

f.	Other required items listed in Form 25D-042 are included in the lower tier subcontracts;

g.	The lower tier subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

h.	Upon receipt of a receipt for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

3.	The following will be considered as subcontracting, unless performed by the Contractor:

a.	Roadside Production.  Roadside production of crushed stone, gravel, and other materials with portable or semi-portable crushing, screening, or washing plants set up or reopened in the vicinity of the project to supply materials for the project, including borrow pits used exclusively or nearly exclusively for the project.

b.	Temporary Plants.  Production of aggregate mix, concrete mix, asphalt mix, other materials, or fabricated items from temporary batching plants, temporary mixing plants, or temporary factories that are set up or reopened in the vicinity of the project to supply materials exclusively or nearly exclusively for the project.

c.	Hauling.  Hauling from the project to roadside production, temporary plants, or commercial plants, from roadside production or temporary plants to the project, from roadside production or temporary plants to commercial plants, and all other hauling not specifically excluded in this subsection.

d.	Other Contractors.  All other contractors working on the project site under contract with the Contractor are considered subcontractors unless specifically excluded in this subsection.

4.	The following will not be considered as subcontracting, but the Contractor shall comply with the prompt payment provisions AS 36.90:

a.	Commercial Plants.  The purchase of sand, gravel, crushed stone, crushed slag, batched concrete aggregates, ready-mixed concrete, asphalt paving mix, and any other materials or fabrication produced at and furnished from established and recognized commercial plants that sell to both public and private purchasers.

b.	Hauling.  Delivery of materials from a commercial plant to a different commercial plant, and delivery from a commercial plant to the project site by vehicles owned and operated by the commercial plants or by commercial freight companies that have a contract with the commercial plant.  Commercial freight companies are trucking or hauling companies that deliver multiple types of materials to multiple clients, both public and private, on an established route, and on a recurrent basis.

c.	Contractors' General Business.  Work within permanent home offices, branch plants, fabrication plants, tool yards, and other establishments that are part of a contractor's or subcontractor's general business operations.

5.	Owner-Operators.  Hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor or approved subcontractor is not considered subcontracting for purposes of AS 36.30.115.

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in contracts with owner-operators.

The Contractor shall collect and maintain at the project site current and valid copies of the following to prove that each trucker listed is a bona fide owner-operator.

a.	Alaska Driver's License with appropriate CDL class and endorsements;

b.	Business license for trucking with supporting documents that list the driver as the business owner or corporate officer;

c.	Documents showing the driver's ownership interest in the truck, including copies of:

(1)	Truck registration; and

(2)	Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of these records for a period of at least three years after final acceptance of the project.

Owner-operators must qualify as independent contractors under the current Alaska Department of Labor's criteria.  Owner-operators may be required to show:

a.	The owner-operator's right to control the manner in which the work is to be performed;

b.	The owner-operator's opportunity for profit or loss depending upon their managerial skill;

c.	The owner-operator's investment in equipment or materials required for their task, or the employment of helpers;

d.	Whether the service rendered requires a special skill;

e.	The degree of permanence of the working relationship; and

f.	Whether the service rendered is an integral part of the owner-operator's business.

The status of owner-operators is subject to evaluation throughout the project period.  If the criteria for an independent contractor are not met, the Contractor shall submit amended payrolls listing the driver as an employee subject to all labor provisions of the Contract.

The Contractor shall issue each owner-operator a placard in a form approved by the Engineer that identifies both the truck driver and the vehicle.  The placard shall be prominently displayed on the vehicle so that it is visible to scale operators and inspectors.

Not withstanding the Department's definitions of contracting and subcontracting, the Contractor shall be responsible for determining and complying with all federal and state laws and regulations regarding contracting, subcontracting, and payment of wages.  The Contractor shall promptly pay any fines or penalties assessed for violations of those laws and regulations, and shall promptly comply with the directives of any government agency having jurisdiction over those matters.

E102-030512

Special Provision

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:

Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in No. 1.  A progress schedule, and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

CR261-121302

Special Provision

- 108-1.07 FAILURE TO COMPLETE ON TIME.  Add the following:

- For each calendar day that the work remains incomplete after the expiration of the interim completion date(s) as set forth in Subsection 105-1.19 Interim Completion, the liquidated damages per day given in Table 108-1 shall be deducted from any monies due the Contractor.

- AKSAS 52972-080913

- SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System Item (1) add the following to the end of the first sentence:

", CD, or a USB device."

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS.  Under Item 3. Equipment, Item a. add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska – South Region.

CR14-043105

Standard Modification

Delete Subsection 109-1.06 in its entirety and replace with the following:

109-1.06 PROGRESS PAYMENTS.  The Department will make monthly progress payments to the Contractor based on estimates of the value of work performed and materials on hand under Subsection 109-1.07.  At the Departments discretion, a progress payment may be made twice monthly if the value of the estimate exceeds $10,000.

Contractor's failure to pay subcontractors or subcontractor's failure to pay lower tier subcontractors, according to prompt payment provisions required under Subsection 108-1.01 is considered unsatisfactory performance.

The Department will not withhold payment as retainage but may withhold payment for unsatisfactory performance.  If satisfactory progress is being made and subcontractors are paid according to Subsection 108-1.01 and AS 36.90.210, the Engineer will authorize 100 percent payment for the estimated value of work accomplished, less any authorized deductions.

If the Engineer finds that satisfactory progress is not being made or payment for satisfactory work by a subcontractor or lower tier subcontractor is not paid according to Subsection 108-1.01, the Engineer may withhold up to 100 percent of the total amount earned from subsequent progress payments.  The Engineer may withhold up to 200 percent of the estimated cost to complete final punch list items for unsatisfactory performance until those items are complete.  The Engineer will notify the Contractor in writing within eight (8) working days of a request for a progress payment of the reasons why part or all of the payment is being withheld for unsatisfactory performance and what actions may be taken by the Contractor to receive full payment.

Payments of withheld amounts will be made in accordance with AS 36.90.200.  No interest will be paid to the Contractor for amounts withheld for unsatisfactory performance except if the Department fails to pay the amount withheld within twenty one (21) calendar days after the Contractor satisfactorily completes the remedial actions identified by the Engineer, as provided in AS 36.90.200(e).

The Contractor shall pay interest on retainage withheld from subcontractors, and at an interest rate according to AS 36.90.250 and AS 45.45.010(a).

E103-030512

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of Subsection 105-1.16.

E11-063004

- Special Provisions

- Add the following Section:

- SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, the opportunity to participate fairly with other contractors in the performance of contracts financed with federal funds.  The Contractor and subcontractors shall not discriminate on the basis of race, color, national origin, or sex in the performance of this Contract.  The Contractor will carry out applicable requirements of 49 CFR Part 26 in the award and administration of US DOT assisted contracts.

120-1.02 INTERPRETATION.  This Section implements the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this Section is a material breach of contract, which may result in contract termination or other remedy as DOT&PF deems appropriate.  Failure to comply with this Section is justification for debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.

1.	Administrative Reconsideration.  A process by which the low bidder may request reconsideration when the Department determines the Good Faith Effort (GFE) requirements have not been met.

2.	Broker.  A certified DBE for the delivery of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary to complete the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and ensuring that the materials meet specifications before credit will be given.

3.	Civil Rights Office. The Department's Civil Rights Office.

4.	Contract Compliance Officer.  Individual within the Civil Rights Office with the authority to administer the Department's compliance programs.

5.	Disadvantaged Business Enterprise.  A Disadvantage Business Enterprise which is a for-profit small business concern that is certified in accordance with 49 CFR, Part 26 and listed in the Alaska DBE Directory.

6.	DBE Key Employee.  A permanent, year-round employee of the DBE and whose name is on file with the Civil Rights Office as a key employee.  A key employee may act as an on-site representative when the owner is not on-site.

7.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs.  The goal is established by the Department and specified in the Contract.

8.	DBE Officer.  Individual designated in writing as a representative of the Contractor concerning DBE issues.

9.	Manufacturer.  A DBE certified in a supply category that changes the shape, form, or composition of original material in some way.  The DBE must provide that material to the general public or the construction industry at large on a regular basis.

10.	Race Conscious Participation.  DBE participation used to meet a specified DBE Utilization Goal.

11.	Race Neutral Participation.  DBE participation that is in excess of the specified DBE Utilization Goal.

12.	Regular Dealer.  A DBE certified in a supply category who operates in a manner consistent with industry practice and who:

a.	maintain an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally fabricate (assemble large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

d.	a person may be a regular dealer in such bulk items as petroleum products, steel, cement, gravel, stone, or asphalt without owning, operating, or maintaining a place of business, if the person both owns and operates distribution equipment for the products.  Any supplementing of regular dealers' own distribution equipment shall be by a long-term lease agreement and not on an ad hoc or contract-by-contract basis.

120-2.01 MEETING THE DBE UTILIZATION GOAL.  A DBE's proposed work may be used to demonstrate the successful bidder's ability to meet the DBE Utilization Goal before Contract award.  The DBE must be certified in a category covering the Commercially Useful Function to be performed at the time of listing on Form 25A-325C (DBE Utilization Report).

A bidder may meet the DBE Utilization Goal through (1) the participation of certified DBE firms, or (2) documentation of required Good Faith Effort (Subsection 120-3.01), or (3) a combination of participation and Good Faith Effort to be eligible for Contract award.

DBE participation on contingent sum items will count as RACE Neutral DBE participation and not towards fulfilling a minimum DBE Utilization Goal, which is RACE Conscious DBE participation.

120-3.01 DETERMINATION OF COMPLIANCE.

1.	Phase I-Bid.  All DBE Good Faith Efforts must be completed prior to bid opening.

2.	Phase II-Award.  The apparent low bidder shall submit evidence of DBE commitment(s) within five working days after receipt of written notification by the Department of the successful low bid.  The apparent low bidder may not supplement its DBE efforts after opening, nor may offer new or additional DBE participation after submitting the DBE Utilization Report (Form 25A-325C).

a.	Written DBE Commitment:  Complete Form 25A-326 for each DBE subcontractor.

b.	DBE Utilization Report.  Submit a completed DBE Utilization Report Form 25A-325C listing certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation.  Submit a completed Summary of Good Faith Effort Documentation Form 25A-332A (with attachments) and contact Report Form 25A-321A if the DBE Utilization Goal is not demonstrated on Form 25A-325C.

If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Effort (as specified below), the Contracting Officer will determine the bidder to be not responsible.

120-3.02 GOOD FAITH EFFORTS (GFE).

1.	Good Faith Effort Criteria.  When a bidder fails to meet DBE Utilization Goals, the Civil Rights Office will use the following criteria to judge whether they have demonstrated sufficient Good Faith Effort to be eligible for award of the Contract.

a.	Consider All Subcontractable Items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items with an established DBE goal as identified on Form 25A-324, before bid opening.  It is the bidder's responsibility to facilitate DBE participation by making the work listed on the subcontractable items list available to DBE firms.

If the bidder cannot achieve the DBE Utilization Goal, then the bidder may also consider other items not listed that could be subcontracted to DBEs.

b.	Initial DBE Notification.  All DBEs listed in the Department's current DBE Directory that have a "Yes" Under Required GFE Contact and "Yes" under the specific Work Area (Region) must be contacted at least seven calendar days prior to bid opening.  DBEs certified to perform work items identified on Form 25A-324 must be contacted to solicit their interest.  Each contact with a DBE firm will be logged on a Contact Report, Form 25A-321A.

The bidder must give DBEs at least five calendar days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.

The only acceptable methods of initial and follow up notification are:

1)	By fax with a confirmation receipt of successful transmission to the DBE's fax number listed in the DBE Directory.  A fax transmission without receipt of successful transmission is unsatisfactory.

2)	By email with a confirmation of successful receipt by DBE's email address listed in the DBE Directory.  Email without confirmation of successful receipt is unsatisfactory.

3)	By U.S. Mail to the DBE's address listed in the DBE Directory with a return receipt requested.  Letters mailed without a return receipt signed by the DBE or DBE Key employee are unsatisfactory.  Delivery confirmation with evidence of successful delivery is an acceptable substitute for Return Receipt.

4)	By telephone solicitation with a record of the date and time of the telephone call made to the DBE's telephone number listed in the DBE Directory.  Telephone solicitation without a record of date and time is unsatisfactory.

c.	Non-Competitive DBE Quotes.  DBE quotes more than 10 percent higher than an accepted non-DBE quote will be deemed non-competitive, provided they are for the exact same work or service.

All evidence in support on a non-competitive bid determination must be provided at the time of the Good Faith Effort submittal.  When a DBE quote is rejected as being non-competitive, the work must be performed by the non-DBE subcontractor whose quote was used to provide the basis of the determination.  Payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the accepted quote.  This does not preclude increases due to change documents issued by the Department.

d.	Assistance To DBEs.  Contractors must provide DBEs with:

1)	Information about bonding or insurance required by the bidder.

2)	Information about securing equipment, supplies, materials, or related assistance or services.

3)	Adequate information about the requirements of the Contract regarding the specific item work or service sought from the DBE.

e.	Follow-up DBE Notifications.  Contact the DBEs to determine if they will be bidding.  For acceptable forms of notification and required documentation see 120-3.02, subsection 1.b items 1 through 4.

Failure to submit a bid by the deadline is evidence of the DBE's lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report, Form 25-321A.

f.	Good Faith Effort Evaluation.  Subsections (a) through (e) must be completed for a Good Faith Effort based submission to be considered.  Failure to perform and document actions contained in subsection (a) through (e) constitutes insufficient Good Faith Effort.  After submitting a Good Faith Effort, bidders may only clarify efforts taken before opening.  No new efforts or additional DBE participation is permitted after opening.

2.	Administrative Reconsideration.  49 CFR Part 26.53(d) provides an opportunity for administrative reconsideration when the Department determines that Good Faith Effort is insufficient.  This opportunity must be exercised within three working days of notification that Good Faith Efforts were unsatisfactory.  For reconsideration, the bidder must provide written documentation or argument concerning efforts to meet the DBE Utilization Goal.  No new or additional contact information may be provided.  Only contact information the bidder provided in support of its initial request for a Good Faith Effort determination by the Civil Rights Office may be presented to support the request for administrative reconsideration.

The process for an Administrative Reconsideration is as follows:

a.	The bidder will have the opportunity to meet with the DBE Liaison Officer in person to discuss the issue.  If so desired, the bidder must be ready to meet with the DBE Liaison Officer within four working days of receipt of notice that it failed to meet the requirements of this subsection.

b.	The DBE Liaison Officer will render a written decision and provide notification to the bidder within four working days after the meeting.  The written decision will explain the basis for finding.

c.	The finding of the DBE Liaison Officer cannot be appealed to the U.S. DOT.

3.	Phase III-Construction.

a.	DBE Creditable Work.  The Commercially Useful Function work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report, Form 25A-325C, shall be included in any subcontract, purchase order of service agreement with that DBE.

b.	DBE replacement.  The Contractor shall submit a written request to replace a DBE to the Engineer.  If approved, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  If the Engineer and the Civil rights Office agree that the criteria of Subsection 120-3.04 have been met, the DBE may be replaced by the Contractor with a non-DBE subcontractor.

c.	DBE Utilization Goal Adjustment.  The DBE Utilization Goal will be adjusted only if a DBE replacement is approved by the Engineer, and only to the extent the Contractor cannot obtain another DBE subcontractor to perform the work.

120-3.03 COMMERCIALLY USEFUL FUNCTION.

1.	Creditable Work.  Measuring the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable Commercially Useful Function work on this project.  This is determined by the Engineer in accordance with this Section.

Commercially Useful Function is limited to:

a.	Prime Contractors;

b.	Subcontractors;

c.	Manufacturers;

d.	Regular Dealers;

e.	Brokers; or

f.	Joint Ventures

2.	Determination of Commercially Useful Function.  In order for the Commercially Useful Function work of the DBE to be credited toward the goal, the Contractor will ensure that the DBE is certified in the appropriate category at the time of the submittal of the subcontract, or the issuance of a purchase order or service agreement.  Subcontracts, purchase orders and service agreements shall be consistent with written DBE commitment.

a.	The Commercially Useful Function performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, a regular dealer, or manufacturer of the product provided to this project.

b.	The following factors will be used in determining whether a DBE trucking company is performing a Commercially Useful Function:

1)	The DBE must be responsible for the management and supervision of the entire trucking operation for which it is responsible on a particular contract, and there cannot be a contrived arrangement for the purpose of meeting DBE goals.

2)	The DBE must itself own and operate at least one fully licensed, insured, and operational truck used on the Contract.

3)	The DBE receives credit for the total value of the transportation services it provides on the Contract using trucks it owns, insures, and operates using drivers it employs.

4)	The DBE may lease trucks from another DBE firm, including an owner-operator who is certified as a DBE.  The DBE who leases trucks from another DBE receives credit for the total value of the transportation services the lessee DBE provides on the Contract.

5)	The DBE may also lease trucks from a non-DBE firm, including from an owner-operator.  The DBE who leases trucks from a non-DBE is entitled to credit for the total value of transportation services provided by non-DBE lessees not to exceed the value of transportation services provided by DBE-owned trucks on the Contract.  Additional participation by non-DBE lessees receives credit only for the fee or commission it receives as a result of the lease arrangement.

6)	A lease must indicate the DBE has exclusive use of and control over the truck.  This does not preclude the leased truck from working for others during the term of the lease with the consent of the DBE, so long as the lease gives the DBE absolute priority for use of the leased truck.  Leased trucks must display the name and identification number of the DBE.

c.	The Contractor will receive credit for the Commercially Useful Function performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding Commercially Useful Function and potential DBE credit.

d.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the Commercially Useful Function criteria may be credited toward the DBE Utilization Goal.

e.	DBE work shall conform to the following requirements to be a Commercially Useful Function:

1)	It will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	It will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE's own equipment.  Either the DBE owner of DBE On-Site Representative will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling their delivery and fully responsible for ensuring that they meet specifications.  The cost of materials purchased from the Contractor or its affiliates is not creditable.

6)	Subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless approved in advance by the Engineer.

7)	The DBE will control all business administration, accounting, billing and payment transactions.  The Contractor cannot perform these functions for the DBE.

In accordance with AS 36.30.420(b), the Engineer may inspect the offices of the DBE and audit their records to assure compliance.

3.	Rebuttal of a Finding of No Commercially Useful Function.  Consistent with the provisions of 49 CFR, Part §26.55(c)(4)&(5), before the Engineer makes a final finding that no Commercially Useful Function has been performed by a DBE, the Engineer will coordinate transmittal of the presumptive finding through the Civil Rights Office to the Contractor, who will in-turn, notify the DBE.  The Contractor will provide the DBE the opportunity to provide rebuttal information.  The Contractor shall present the information to the Engineer.

The Engineer, together with the Civil Rights Office, will make a final determination on whether the DBE is performing a Commercially Useful Function.  Under no circumstances will the Contractor take any action with respect to the DBE until the final determination is made.  The Engineer's decisions on Commercially Useful Function matters are subject to review by the Department, but are not administratively appealable to the US DOT.

4.	Monthly Required Reporting.  On a monthly basis, the Contractor shall submit the Monthly Summary of Disadvantaged Business Enterprise Participation, Form 25A-336, to the Civil Rights Office.  Reports are due by the 15th of the following month.  Also attach copies of canceled checks or bank statements that identify payer, payee, and amount of transfer to verify payment information shown on the form.

5.	Removal of DBE Certification.  Should a DBE performing a Commercially Useful Function lose its DBE certification during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

The Contractor must still meet the DBE Utilization Goal by expending Good Faith Effort (Subsection 120-3.03, 2.) and either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE to replace it with a currently certified DBE for that same work or service; or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and finding other work not already committed to DBEs in an amount that meets the DBE Utilization Goal.

120-3.04 TERMINATION OF A DBE SUBCONTRACT.  In accordance with 49 CFR 26.53(f)(1) the Contractor shall not terminate a DBE subcontractor without the written consent of the DBE Liaison Officer.  This includes, but is not limited to, instances in which the Contractor seeks to perform work originally designated for a DBE subcontractor with its own forces or those of an affiliate, a non-DBE firm, or with another DBE firm.  The Contractor must give the DBE subcontractor written notice of an approved subcontract termination.

120-3.05 DEFAULT OF DBE.  If a DBE defaults on their obligation for any reason, the Contractor shall take immediate steps to retain the services of other DBEs to perform the defaulted work.  If the Contractor cannot obtain replacement DBE participation, the DBE Utilization Goal will not be adjusted.  However, the Engineer may consider the following criteria as satisfying that portion of DBE participation that cannot be replaced:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.03 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities for DBEs.

If a DBE firm defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding it.

120-4.01 DETERMINING DBE CREDIT.  The Contractor is entitle to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for Commercially Useful Function work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the Commercially Useful Function of a DBE prime contractor is 100 percent of the monies actually paid to the DBE under the Contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the Commercially Useful Function of a subcontractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the Commercially Useful Function of a subcontractor performing hauling/transportation is 100 percent of the monies actually paid to the DBE under the subcontractor for creditable work for those firms certified in the 100 percent credit category.  Leasing trucks from another DBE firm also qualifies for credit and must conform to the provisions of 49 CFR 26.55(d).  Credit for the Commercially Useful Function of a subcontractor performing hauling/transportation is 5 percent of the monies actually paid to the DBE under the subcontract for creditable work for those firms certified in the 5 percent credit category.

4.	Credit for the Commercially Useful Function of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

5.	Credit for the Commercially Useful Function of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value is the actual cost paid to the DBE not to exceed the bid price for such item.

6.	Credit for the Commercially Useful Function of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

7.	Credit for the Commercially Useful Function of a broker performed by a DBE certified in a bonding or insurance category is limited to a reasonable brokerage fee, not to exceed 5 percent of the premium cost.

8.	Credit for the Commercially Useful Function of a joint venture (JV) either as the prime contractor or as a subcontractor may not exceed the percent of the DBE's participation in the JV agreement, as certified by the Civil Rights Office.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 ACHIEVEMENT OF DBE GOALS.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A-325C as scheduled or fails to submit proof of payment, requested documentation, or otherwise cooperate with a DBE review or investigation, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Effort to replace a DBE, regardless of fault (except for Subsection 120-3.05 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

S97-030512

SECTION 201

CLEARING AND GRUBBING

Special Provisions

201-3.01 GENERAL.  Add the following:

Cut timber, with a 5 inch diameter or larger at breast height, into 8 foot lengths, de-limbed, and stacked to a height no greater than 6 feet at locations approved by the Engineer for public removal.  Make locations adjacent to the nearest turnout, side street or other approved site that does not create a traffic hazard due to lack of adequate parking for the public.  Access to the site(s) shall be maintained and controlled by flaggers, in accordance with Subsection 643-3.04.  The Contractor shall provide and maintain a separate firewood telephone hotline that details when and where the wood is available to the public.  Special Construction signs, in accordance with Subsection 643-2.01, shall be used to advertise the firewood telephone hotline.  Provide two weeks for the public to access each area of the project where timber is made available. Dispose of the timber left by the public after the two week time period.

Mechanical loading by the public is not permitted.

CR2012-042313

Add the following:

Perform the work necessary to preserve and/or restore land monuments and property corners from damage.  Restore land monuments and/or property corners that are disturbed according to Section 642.  An undisturbed area five feet in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

CR2013-042313

Add the following:

Clearing and grubbing is not permitted within open, marshy areas during the migratory bird window of May 1 to July 15 or within wooded areas during the migratory bird window of April 10 to July 15; except as permitted by Federal, State and local laws approved by the Engineer.

0001(458)/52972-062013

201-4.01 METHOD OF MEASUREMENT.  Add the following:

The work required to cut, de-limb, and stack timber for public removal is subsidiary to 201 Pay Items.

CR2012-042313

Add the following:

The work required to preserve and restore land monuments and property corners is subsidiary to 201 Pay Items.

CR2013-042313

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION.  Add the following:

Comply with permit in-water noise limitations.

0001(458)/52972-012412

Add the following:

Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

CR20-022603

203-2.01 MATERIALS.  Add the following:

7.	Select Materials. As specified on the Plans, and conforming to subsection 703-2.01, except all select materials placed within 20 feet horizontally of the abutment piling, from original ground to finish grade, shall not contain any particles retained on the 3 inch sieve.

0001(458)/52972-012412

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Add the following:

Compact the embankment within 50 feet of a bridge abutment full width to not less than 98 percent of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

203-4.01 METHOD OF MEASUREMENT.  Delete Note 2 and replace with the following:

2.	Item 203(6A). By weighing.

Add the following:

8.	There will be no measurement of ditch linear grading.

203-5.01 BASIS OF PAYMENT.  Add the following:

Grading and placement of material used within 50 feet of bridge abutments will be subsidiary to the pay item.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

203(6A)	Borrow, Type A	Ton

Add the following:

Ditch linear grading is subsidiary to other items and includes furnishing equipment, labor, tools, and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

0001(458)/52972-120412

- SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS

AND MINOR STRUCTURES

Special Provision

204-2.01 MATERIALS.  In paragraph three replace: "pavement" with "roadbed."

CR2041-121212

Special Provisions

Replace Section 205 with the following:

SECTION 205

EXCAVATION AND

FILL FOR MAJOR STRUCTURES

205-1.01 DESCRIPTION. Excavate and backfill for bridges, retaining walls, concrete box culverts, and other major structures.

Furnish all resources to place and remove cribbing or cofferdams. Perform all required sheeting, bracing, bailing, pumping, draining, and grouting.

Replace unsuitable material encountered below the elevation of the bottom of footings.

Comply with permit in-water noise limitations.

205-2.01 MATERIALS. Use materials that conform to the following:

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Silica Fume	Section 701

Fine Aggregate	Subsection 703-2.01

Porous Backfill Material	Subsection 703-2.10

Structural Fill	Subsection 703-2.13

Chemical Admixtures	Subsection 711-2.02

Water	Subsection 712-2.01

CONSTRUCTION REQUIREMENTS

205-3.01 EXCAVATION.

1.	General. Clear and grub prior to starting excavation according to the requirements of Section 201.

Cut all rock or other hard foundation material to a firm surface, either level, stepped, or serrated, as directed, and remove all loose material.

Do not disturb material below the bottom of spread footings, unless otherwise noted in the Contract.

Excavate to the bottom of footing prior to driving piles.  Do not excavate below the footing elevation unless otherwise noted in the Contract. When swell results from driving piles, excavate the footing area, to the elevation of the bottom of the footing, as shown on the Plans. When subsidence results from driving piles, backfill with structural fill material, to the elevation of the bottom of the footing, as shown on the Plans.

Dispose of all necessary excavated material as provided in Subsection 203-3.01.

Do not alter streambed channel and do not place excavated materials in natural stream channels, unless shown on the Plans or approved in writing.

Give the Engineer in writing no less than 15 days advance notice prior to beginning excavation for spread footings to allow for inspection of the excavated surface. With this notification, identify the location and specify a time period of no less than two days for the Department to inspect the excavated surface. Dewater and remove all debris from the surface prior to the Department's inspection. Obtain the Engineer’s approval of the excavated surface prior to the placement of any formwork or foundation materials. Account for the time required by the Department to perform the inspection in the progress schedule submitted under Subsection 108-1.03. Suspension of work to allow for inspection is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

2.	Foundations on Bedrock. Excavate for footings founded on bedrock, to the neat lines of the footings. Fill overbreak areas outside the neat lines of footings, with Class A concrete, at no additional cost to the Department.

3.	Cofferdams. Use suitable cofferdams as necessary wherever water-bearing strata are encountered above the elevation of the excavation. Construct foundation seals according to the requirements of Section 501.

Submit detailed drawings, designed and sealed by a professional engineer proficient in structural design and registered in the State of Alaska, showing proposed method of cofferdam construction. The details and clearance of cofferdams, which affect the character of the finished work, is subject to approval but other details of the design are your responsibility. Submit drawings at least 3 weeks in advance of cofferdam construction.

Extend cofferdams to the required depth or to bedrock. Adequately brace cofferdams and make them as watertight as practical. Provide sufficient clearance inside cofferdams to permit construction of forms and permit pumping outside of the forms.

Right or enlarge cofferdams which are tilted or moved out of position by any cause during the sinking process, to provide the necessary clearance and proper pier location.

When no foundation seal is shown on the Plans and the cofferdam cannot be dewatered, place a seal if the Engineer approves seal placement in writing.

Foundation seals, when shown on the Plans, may be eliminated as directed if the cofferdams can be dewatered without the seals when the excavation has been carried to the elevation of the bottom of the footing.

Construct cofferdams to protect concrete against damage from a sudden rising of the water and to prevent damage by erosion by venting cofferdams at low water or by other means that limit differential hydrostatic head.

No timber may extend into the completed substructure.

After substructure completion, remove sheet piling and other temporary structural materials in such a manner as to avoid disturbing the finished structure. Steel or concrete sheeting or bracing may be permitted to remain in the completed structure, subject to approval.

205-3.02 STRUCTURAL FILL. Remove material that is unsuitable for supporting foundations, from the bottom of the footing to the depth as shown on the Plans. Remove material that is unsuitable for approach slabs shown on the Plans. Place Structural Fill in 6-inch layers, compacted to meet Subsection 205-3.05. Place Structural Fill as uniformly as possible on all sides of structural units as shown on the Plans. Avoid unbalanced loading of Structural Fill material which could damage the structure. When placed against concrete, place Structural Fill in accordance with Section 501.

Controlled Low-Strength Material may be used as an alternative source for Structural Fill if approved by the Engineer.

205-3.03 BACKFILL. Unless otherwise noted, reuse excavated material for backfill where shown on the Plans. If additional backfill is required, use material meeting Selected Material, Type D (Subsection 703-2.07), or as approved by the Engineer. Place backfill material in layers, and compact in accordance with Section 203.

Place underwater backfill in natural stream channels without compaction or layer requirements.

Place backfill as uniformly as possible on all sides of structural units. Avoid unbalanced loading of backfill which could damage the structure. When placed against concrete, place backfill according to the requirements of Section 501.

No ponding or jetting of backfill is allowed.

205-3.04 POROUS BACKFILL. Place porous backfill material continuously within a vertical plane 1 foot behind retaining walls and abutments, unless otherwise shown on the Plans. Place Porous Backfill in 6-inch layers, compacted to meet Subsection 205-3.05. Place Porous Backfill as uniformly as possible. When placed against concrete, place Porous Backfill in accordance with Section 501.

Where weep holes are shown on the Plans or required by the Specifications, place not less than 1 cubic foot of Porous Backfill material in the fill at each hole, securely tied in a burlap bag, or wrapped with an acceptable geotextile fabric. Extend the wrapped Porous Backfill material at least 6 inches above the hole.

205-3.05 COMPACTION. Compact material in conformance with the following, using moisture and density control unless the Engineer determines that such controls are not feasible.

1.	Compaction With Moisture and Density Control. The maximum density will be determined by WAQTC FOP for AASHTO T 180 or ATM 212.

Water or aerate as necessary to provide the approximate optimum moisture content for compaction. Compact each layer to not less than 98% of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

205-3.06 CONTROLLED LOW-STRENGTH MATERIAL. Provide Controlled Low-Strength Material (CLSM) that is self-compacting, cementitious, flowable material requiring no subsequent vibration or tamping to achieve consolidation. Provide a job mix design in writing to the Engineer on Form 25D-203. Do not place CLSM until the Engineer approves the mix design.

Design CLSM to have 28-day compressive strength between 100 psi minimum to 300 psi maximum as determined by ASTM D 4832 and a flowable consistency within a slump range of 3 to 10 inches as determined by WAQTC FOP for AASHTO T 119.

Calculate the water-cement ratio on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, and silica fume. Use admixtures in accordance with the manufacturer’s recommendations. Do not use admixtures containing calcium chloride.

Mix and batch CLSM in accordance with Subsection 501-3.01 to Subsection 501-3.03.

Do not place CLSM on frozen ground, in standing water, or during wet weather conditions. Place CLSM only if the air temperature is 40 °F minimum and rising. Ensure the material temperature is at least 50 °F while being placed.

Do not apply loads to the CLSM until the compressive strength reaches 50 psi.

Meet the proportion requirement of Subsection 501-3.05.5.a. Acceptance will be based on a Certificate of Compliance. Provide a Certificate of Compliance for each batch of CLSM in accordance with Subsection 501-3.05.2.

205-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Excavation. By the actual volume of material removed, excluding the following:

a.	Material removed prior to measurement of the original ground surface.

b.	Material outside of the vertical planes 18 inches outside of and parallel to the neat lines of the footings, except that the limit will be vertical planes coinciding with the neat lines of the seals when seals are shown on the Plans.

c.	Material outside of vertical planes coinciding with the neat lines of footings excavated in solid rock.

d.	Embankment material placed above the elevation of the bottom of footings.

e.	Material within the staked limits of other types of excavation for which payment is otherwise provided.

2.	Structural Fill. By the actual volume of material accepted in final position.

3.	Porous Backfill Material. By the actual volume of material accepted in final position.

4.	Backfill. Material for Backfill will not be measured for payment.

5.	Controlled Low-Strength Material. By the actual volume of material accepted in final position.

205-5.01 BASIS OF PAYMENT. Material for backfill is subsidiary.  Clearing and grubbing within the excavation limits is subsidiary.

Porous Backfill Material includes all materials and construction operations for making weep holes. When item 205(4), Porous Backfill Material, does not appear in the bid schedule, Porous Backfill is subsidiary.

Excavation, removal, and disposal of material unsuitable for Structural Fill is subsidiary.

Excavation for footings ordered by the Engineer, at a depth greater than 3 feet below the bottom of such footings shown on the Plans will be paid for as extra work under Subsection 109-1.05.

Where a bid item for cofferdams does not appear in the bid schedule, the work necessary to protect the excavation and control water is subsidiary.

When Controlled Low-Strength Material is used as an alternative to Structural Fill, Controlled Low-Strength Material is paid at the Structural Fill value.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

205(1)	Excavation for Structures	Cubic Yard

205(2)	Cofferdam	Lump Sum

205(3)	Structural Fill	Cubic Yard

205(4)	Porous Backfill Material	Cubic Yard

205(5)	Controlled Low-Strength Material	Cubic Yard

0001(458)/52972-082712

Special Provisions

Replace Section 501 with the following:

- SECTION 501

- STRUCTURAL CONCRETE

501-1.01 DESCRIPTION. Furnish, place, finish, and cure Portland cement concrete for structure construction. Use the class of concrete noted on the Plans unless otherwise specified.

- classes of concrete

- Class A:	General use concrete

Class A-A:	Concrete where improved strength and durability is required

Class P:	Concrete where strength in excess of 5000 psi is required

Class DS:	Concrete for drilled shaft foundations

501-1.02 DEFINITIONS.

ADMIXTURE. A material other than water, aggregates, hydraulic cement, pozzolan, and fiber reinforcement, used as an ingredient of a cementitious mixture to modify its freshly mixed, setting, or hardened properties and is added to the batch before or during its mixing.

AIR-ENTRAINING ADMIXTURE. An admixture causing the development of a system of microscopic air bubbles in concrete, mortar, or cementitious material paste during mixing, usually to improve its workability and resistance to damage by freezing and thawing.

SET-ACCELERATING ADMIXTURE. An admixture causing an increase in the rate of hydration of the hydraulic cement and shortens the time of setting, increases the rate of strength development, or both.

SET-RETARDING ADMIXTURE. An admixture causing a decrease in the rate of hydration of the hydraulic cement and lengthens the time of setting, decreases the rate of strength development, or both.

WATER-REDUCING ADMIXTURE. An admixture either increasing slump of freshly mixed mortar or concrete without increasing water content or maintaining slump with a reduced amount of water, due to factors other than air entrainment.

AGITATION. The process of providing motion in mixed concrete just sufficient to prevent segregation or loss of plasticity.

BLEED WATER. The autogenous flow of water emerging from newly placed concrete, and caused by the settlement of the solid materials within the mass. The relative quantity of mix water that will bleed can be estimated by AASHTO T 158.

CAMBER. For prestressed concrete members, camber is the net upward deflection of an eccentrically prestressed concrete member due to the combined loads, shrinkage, creep, and eccentricity of the prestress force. For non-prestressed members, camber is a deflection intentionally built into a structural element or form to improve appearance or to nullify the deflection of the element under the effects of loads, shrinkage, and creep.

CEMENT. A binding material that sets and hardens by hydration and is capable of doing so underwater, sometimes called hydraulic cements

- CEMENTITIOUS MATERIAL. Hydraulic cements and pozzolans with cementing properties.

CHAMFER. A beveled edge or corner formed into finished concrete.

COMPRESSIVE STRENGTH, (fc). The measured maximum resistance of a concrete or mortar specimen to axial compressive loading; expressed as force per unit cross-sectional area; or the specified resistance used in design calculations.

SPECIFIED COMPRESSIVE STRENGTH, (f’c). The 28-day compressive strength used in structural design and specified in the Contract documents.

REQUIRED AVERAGE COMPRESSIVE STRENGTH, (f’cr). The 28-day compressive strength, used as the basis for selection of concrete proportions in the mix design process, sufficiently greater than the Specified Compressive Strength to ensure the acceptance criteria are met.

COMPRESSIVE STRENGTH TEST. The average strength test of concrete, from at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders sampled according to AASHTO T 141, cured according to AASHTO R 39 or WAQTC FOP for AASHTO T 23, and tested according to AASHTO T 22 or sampled, cured, and tested to equivalent ASTM test methods. Unless otherwise noted, tested at an age of 28 days.

The average strength test of grout, from at least three specimens from a batch and tested according to WAQTC TM 12, AASHTO T 106, or ASTM C 109.

CONCRETE ANCHOR. Cast-in-place or post-installed fastening device installed in the concrete for the purpose of transferring loads to the concrete. See ASTM E 2265 for standard terminology.

CONSOLIDATION. The process of inducing a closer arrangement of the solid particles in freshly mixed concrete during placement by the reduction of voids, usually by vibration, rodding, tamping, or some combination of these actions.

CONSTRUCTION JOINT. The surface where two successive placements of concrete meet.

CURING. Action taken to maintain moisture and temperature conditions in a freshly placed cementitious mixture to allow hydraulic cement hydration and (if applicable) pozzolanic reactions to occur so the desired properties of the mixture develop.

CURING PERIOD. The length of time in which continuous curing operations are maintained thereby allowing the concrete to properly hydrate and develop its required strength and durability.

INITIAL CURING PERIOD. The time period between placement and implementation of final curing methods in which deliberate action is taken to reduce the loss of moisture from the surface of the concrete.

FINAL CURING PERIOD. The time period after the concrete achieves final set in which deliberate action is taken, without damaging or marring the concrete surface, to maintain satisfactory moisture content and temperature in concrete.

CURING COMPOUND. A liquid applied as a coating to the surface of newly placed concrete to retard the loss of water and, in the case of pigmented compounds, reflects heat to provide an opportunity for the concrete to develop its properties in a favorable temperature and moisture environment.

DURABILITY. The ability of concrete to resist weathering action, chemical attack, abrasion, and other conditions of service.

EVAPORATION RATE REDUCER. A material generating a continuous thin film when spread over water on the surface of fresh concrete to retard the evaporation of bleed water.

FIELD TEST RECORD. A record of compressive strength test results from concrete used on prior projects and produced by the concrete production facility.

INFORMATIONAL FIELD TEST. A compressive strength test, determined by the Engineer, from field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure; except, the compressive strength test may consist of one 6.0 x 12.0 inch or one 4.0 x 8.0 inch compressive strength test cylinder.

KEYWAY. A recess or groove in one lift or placement of concrete and filled with concrete of the next lift or grout, giving shear strength to the joint.

LAITANCE. A layer of weak material derived from cementitious material and aggregate fines either: 1) carried by bleeding to the surface or to internal cavities of freshly placed concrete; or 2) separated from the concrete and deposited on the concrete surface or internal cavities during placement of concrete underwater.

MORTAR. A mixture of cementitious material paste and fine aggregate occupying the space between particles of coarse aggregate.

RETEMPER. To add water and remix concrete or mortar to restore workability to a condition in which the mixture is placeable or usable.

ROCK POCKET. A porous, mortar-deficient portion of hardened concrete consisting primarily of coarse aggregate and open voids.

SCREED. To strike off concrete lying beyond the desired plane or shape. A tool for striking off the concrete surface, sometimes referred to as a strikeoff.

SET. The condition reached by a cementitious material paste, mortar, or concrete that has lost plasticity to a degree of stiffening generally stated as the time in hours and minutes required for cementitious material paste to stiffen sufficiently to resist the penetration of a weighted test needle as prescribed by AASHTO T 197,

- INITIAL SET. The first stiffening of concrete.

- FINAL SET. Attainment of significant rigidity in which rainfall, foot traffic, and curing materials contacting the concrete surface do not damage or mare the concrete surface and do not alter the properties of the finished surface.

TREMIE. A pipe or tube with a hopper for filling at its upper end through which concrete is deposited.

501-2.01 MATERIALS. Use materials conforming to the following:

- 1.	Cementitious Materials

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Ground Granulated Blast-Furnace Slag	Section 701

Silica Fume	Section 701

- 2.	Aggregate Materials

Fine Aggregate	Subsection 703-2.01

Coarse Aggregate	Subsection 703-2.02

Aggregate for Abrasive Finish	Subsection 703-2.14

- 3.	Water, Admixtures and Curing Materials

Curing Materials	Subsection 711-2.01

Chemical Admixtures	Subsection 711-2.02

Water and Ice	Subsection 712-2.01

- 4.	Utilities and Inserts

Concrete Anchor Inserts	Subsection 712-2.20

Utiliduct, HDPE	Subsection 706-2.08

Utiliduct, Steel	Section 716

Structural Steel	Section 716

Asphalt Felt	ASTM D 226, Type I (No. 15 Asphalt Felt)

- 5.	Grout and Epoxy

Grout	Subsection 701-2.03

Epoxy Adhesive for Crack Sealing	AASHTO M 235, Type IV, Grade 3

Epoxy Adhesive for Crack Injection	AASHTO M 235, Type IV, Grade 1

Low-Viscosity Resin	Subsection 712-2.19

Epoxy Bonding Agents	AASHTO M 235, Type V

501-2.02 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Provide a Job Mix Design, for each required class of concrete and Specified Compressive Strength (f'c), which meets the requirements of this Subsection and provides workability and consistency so the concrete can be worked readily into the forms and around reinforcement without segregation or bleeding. Determine proportions using the absolute volume method according to ACI 211.1.

1.	Water-Cement Ratio and Cementitious Materials. Provide a Job Mix Design meeting the water-cement ratio requirements in Table 501-1.

Calculate the water-cement ratio based on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, ground granulated blast-furnace slag, and silica fume.

Fly ash, ground granulated blast-furnace slag, silica fume, and combinations of these materials may be used as a substitute for Type I and II Portland cement provided the quantity meets the limits of Table 501-2 and the total quantity of combined fly ash, ground granulated blast-furnace slag, and silica fume does not exceed 40 percent of the total cementitious material by weight. Do not use fly ash with Type III Portland cement.

- TABLE 501-1

WATER-CEMENT RATIO REQUIREMENTS

| Class of Concrete | Water-Cement Ratio, maximum |
| --- | --- |
|  | lbs/lbs |
| A | 0.45 |
| A-A | 0.40 |
| P | 0.35 |
| DS | 0.45 |

- TABLE 501-2

SUPPLEMENTARY CEMENTITIOUS MATERIAL LIMITS

| Cementitious Material | Percent of Total Cementitious Material by Weight1 |
| --- | --- |
|  | Maximum |
| Fly Ash | 35% |
| Ground Granulated Blast-Furnace Slag | 40% |
| Silica Fume | 10% |

1	The maximum percent includes initial quantities in blended hydraulic cement plus additional supplementary cementations materials.

2.	Aggregate Gradations. Provide a Job Mix Design meeting the fine aggregate gradation requirements in Subsection 703-2.01 and the coarse aggregate gradation requirements in Table 501-3. Blending of several sizes of aggregate to achieve the specified gradation is permitted.

- TABLE 501-3

COARSE AGGREGATE GRADATION REQUIREMENTS

| Class of Concrete | Coarse Aggregate Size Number |
| --- | --- |
|  | AASHTO M 43 |
| A | No. 57 or 67 |
| A-A | No. 57 or 67 |
| P | No. 67 |
| DS | No. 7 or 8 |

3.	Air Content. Provide a Job Mix Design with a total air content of 6.0 percent. The total air content for Class P concrete having a water/cement ratio less than 0.33 may be reduced 3.0 percent. Air-entrained concrete is required only for the deck portion of prestressed precast concrete members. Air-entrained concrete is not required for Class DS concrete.

4.	Slump. Provide a Job Mix Design meeting the slump requirements in Table 501-4.

- TABLE 501-4

SLUMP REQUIREMENTS

| Condition | Slump |
| --- | --- |
| Concrete without a water-reducing admixture | 4" max. |
| Concrete with a Type A, D, or E water-reducing admixture | 6" max. |
| Concrete with a Type F or G high-range water-reducing admixture | 9" max. |
| Class DS concrete, wet-shaft process | 7" min. 9" max. |
| Class DS concrete, dry-shaft process | 6" min. 9" max. |

5.	Chloride Ion Content. Provide a Job Mix Design with a total water soluble chloride ion content of the concrete that does not exceed 0.06 percent by weight of cementitious material for precast concrete members or 0.08 percent by weight of cementitious material for other concrete, tested according to ASTM C 1218.

6.	Required Averaged Compressive Strength. Provide a Job Mix Design meeting a Required Average Compressive Strength (f'cr) established from either the Empirical Method or the Statistical Method.

If the Specified Compressive Strength (f'c) is not designated on the Plans, use a Specified Compressive Strength listed in Table 501-5.

- TABLE 501-5

COMPRESSIVE STRENGTH REQUIREMENTS

| Class of Concrete | Specified Compressive Strength (f'c) |
| --- | --- |
|  | (psi) |
| A | 4000 |
| A-A | 5000 |
| P | 8000 |
| DS | 4000 |

a.	Empirical Method. Establish the Required Average Compressive Strength from the following equations:

f'cr = f'c + 1200	for f'c ≤ 5000 psi

f'cr = 1.1f'c + 700	for f'c > 5000 psi

Where:	f'cr = Required Average Compressive Strength, psi

f'c = Specified Compressive Strength, psi

b.	Statistical Method. If the production facility has field test records of compressive strength tests, establish the Required Average Compressive Strength based on the calculated standard deviation of the field test records and using the largest result of the following the equations:

f'cr = f'c + 1.34ks	for all f'c

or,

f'cr = f'c + 2.33ks – 500	for f'c ≤ 5000 psi,

f'cr = 0.90f'c + 2.33ks	for f'c > 5000 psi,

Where:	f'cr	=	Required Average Compressive Strength, psi

f'c	=	Specified Compressive Strength, psi

k	=	1.16 if 15 total tests are considered

1.08 if 20 total tests are considered

1.03 if 25 total tests are considered

1.00 if 30 or more total tests are considered

s	=	standard deviation, psi

Linear interpolation to determine k for intermediate number of tests is acceptable.

Use field test records performed within the past 12 months and spanning a period of more than 60 days for a class of concrete within 1000 psi of the Specified Compressive Strength. Use field test records from concrete produced at the production facility, which represent materials, quality-control procedures, and climatic conditions similar to those expected in the work. Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work. Use field test records meeting one of the following:

(1)	One Group of Field Test Records. Use field test records representing a group of at least 15 consecutive compressive strength tests in which all concrete was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation, psi

- n	=	number of compressive strength test results considered

Xi	=	individual compressive strength test result, psi

=	average of n compressive strength test results, psi

(2)	Two Groups of Field Test Records. Use field test records representing two groups of consecutive compressive strength tests totaling at least 30 tests. Ensure each group is comprised of at least 10 consecutive compressive strength tests, and all concrete in each group was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation for the two groups combined, psi

s1, s2	=	standard deviation for groups 1 and 2, respectively, calculated according to Subsection 501-2.02.6.b.(1), psi

n1, n2	=	number of test results in groups 1 and 2, respectively

7.	Job Mix Design Verification.

a.	Required Average Compressive Strength. Verify the Job Mix Design satisfies the Required Average Compressive Strength by meeting at least one of the following requirements:

(1)	Field Test Records. Use field test records that:

(a)	use materials of the same brand and type and from the same manufacturer as the materials used in the work;

(b)	were from concrete produced at the production facility;

(c)	use quality-control procedures, and had climatic conditions similar to those expected in the work; and

(d)	encompass a period of not less than 60 days.

Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work.

For a single group of at least 10 consecutive compressive strength tests for one mixture, verify the average of the compressive strength tests equals or exceeds the Required Average Compressive Strength.

For two groups, each having at least 10 consecutive compressive strength tests, for two mixtures representing classes of concrete within 1000 psi of the Specified Compressive Strength, plot the average strength X1 and X2 of each group versus the water-cementitious material ratio of the corresponding mixture proportions and interpolate between them to determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the interpolated compressive strength equals or exceeds the Required Average Compressive Strength.

(2)	Laboratory Trial Mixtures. Use materials and material combinations for trial mixtures of the same brand and type and from the same manufacturer as the materials used in the work.

Record the temperature of the freshly mixed concrete according to AASHTO T 309 and ensure the temperature is within 10°F of the intended maximum temperature of the concrete as mixed and delivered.

For each trial mixture, make and cure at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders for each test age according to AASHTO R 39. Test for compressive strength according to AASHTO T 22 at test ages of 7, 14 and 28 days.

For a single trial mixture, verify the compressive strength test equals or exceeds the Required Average Compressive Strength.

For a group of trial mixtures, make at least three trial mixtures with each mixture having a different cementitious material content. Select water-cement ratios producing a range of compressive strengths encompassing the Required Average Compressive Strength. From the results of the 28-day compressive strength tests, plot a curve showing the relationship between water-cement ratio and compressive strength. From the curve of water-cement ratio versus compressive strength, determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the compressive strength equals or exceeds the Required Average Compressive Strength.

b.	Flowability Requirements for Class DS Concrete (Wet-Shaft Process). Verify the Job Mix Design satisfies the concrete flowability requirements of Subsection 501-3.05.4.a.1. Develop a slump loss table showing the slump at 1 hour intervals since batching until the concrete takes initial set.

c.	Plasticity Requirements for Class DS Concrete (Dry-Shaft Process). Verify the Job Mix Design satisfies the concrete plasticity requirements of Subsection 501-3.05.4.b.1. Ensure initial set occurs after placement operations are complete.

8.	Job Mix Design Submittal. Submit a written mix design, signed and sealed by a Professional Engineer registered in the State of Alaska, for each specified class of concrete and for each Specified Compressive Strength, to the Engineer at least 45 days prior to scheduled production. Submit the mix design on Form 25D-203. Include the following:

a.	Job Mix Design Proportions and Test Results. Submit concrete mixture proportions per cubic yard and test results for the proposed Job Mix Design. Include the following information:

- (1)	Weights of cementitious materials

- (2)	Weights of aggregates in saturated surface dry condition

- (3)	Volume or weight of each admixture.

- (4)	Weight of water

- (5)	Water-cement ratio

- (6)	Percentage of air by volume

- (7)	Total water soluble chloride ion content

- (8)	Wet unit weight

- (9)	Expected slump

- (10)	Expected 7, 14, and 28 day compressive strength

- (11)	Slump loss table for flowability requirements of Class DS concrete (if applicable)

- (12)	Time of initial set for plasticity requirements of Class DS concrete (if applicable)

b.	Materials. The Engineer may require samples of aggregate, cementitious materials, and admixtures to verify the mix design. If requested, furnish representative samples (330 pounds each) of both coarse and fine aggregates, 94 pounds of each cementitious material, and enough admixture to allow for Job Mix Design verification testing. Ensure the Department receives these samples at least 45 days before the mixture’s scheduled production for the project. Submit the following:

(1)	For each cementitious material, include:

(a)	Type/Class

(b)	Brand

(c)	Producer

(d)	Plant location

(e)	Certified test reports confirming the cementitious material meets these Specifications.

(2)	For aggregates, include:

(a)	Pit or quarry location(s)

(b)	Bulk dry specific gravity, bulk saturated surface dry specific gravity, and apparent specific gravity

(c)	Absorption values

(d)	AASHTO size number for coarse aggregates

(e)	Gradations for aggregates

(3)	For each admixture, include:

(a)	Type

(b)	Manufacturer

(c)	Manufacturer's product data sheet giving the procedure for admixture use and confirming the admixture meets these Specifications.

(d)	The batching process step and mixing instructions when each admixture is added.

(e)	When using two or more admixtures in the same Job Mix Design, provide manufacturer’s certifications showing the admixtures are compatible and if they can be added simultaneously.

(4)	Include the source of supply for water and ice.

c.	Basis of Required Average Compressive Strength. If the Statistical Method is used, submit the following for each field test record:

(1)	Compressive strength test results of the tested concrete.

(2)	Standard test method used for determining compressive strength.

(3)	Date the compressive strength tests were performed

(4)	Aggregate source used for the tested concrete.

(5)	Specified strength of the tested concrete.

(6)	Batched weights for the concrete used for each compressive strength test.

d.	Documentation of Required Average Compressive Strength. Submit documentation indicating the proposed concrete proportions will produce an average compressive strength equal to or greater than the Required Average Compressive Strength meeting one of the following requirements:

(1)	Field Test Records. If field test records were used to verify the Required Average Compressive Strength, submit the following for each field test record:

(a)	Compressive strength test results of the tested concrete.

(b)	Standard test method used for determining compressive strength.

(c)	Date the compressive strength tests were performed

(d)	Aggregate source used for the tested concrete.

(e)	Specified strength of the tested concrete.

(f)	Batched weights for the concrete used for each compressive strength test.

(2)	Trial Mixtures. If trial mixtures were used to verify the Required Average Compressive Strength, submit concrete mixture proportions per cubic yard and test results for each trial mixture. Include the following information:

(a)	Weights of cementitious materials

(b)	Weight of aggregates in saturated surface dry condition

(c)	Volume or weight of each admixture

(d)	Weight of water

(e)	Water-cement ratio

(f)	7-day, 14-day, and 28-day compressive strength test results

(g)	Percentage of air by volume

(h)	Wet unit weight

9.	Changes. A change in the approved Job Mix Design proportions, materials, aggregate gradation, or aggregate quality requires a new Job Mix Design; except, a change in Type A, D, E, F, and G admixture proportions, or the addition of a Type A, D, E, F, and G admixture, does not require a new Job Mix Design.

10.	Approval. Obtain the Engineer’s approval of each mix design prior to use. Approval of the Job Mix Design does not constitute acceptance of produced concrete and will not obligate the Department to accept or pay for concrete that does not meet the mix acceptance requirements of Subsection 501-3.03.

- CONSTRUCTION REQUIREMENTS

501-3.01 BATCHING. Batch concrete, in proportioned amounts, according to the approved Job Mix Design.

1.	Certification and Calibration. Batch concrete using a certified batch plant. Obtain plant certification meeting the requirements in this Subsection. Use and maintain calibrated weighing and measuring devices for concrete batching equipment, including measuring devices for adding material on-site, meeting the requirements of this Subsection. Submit documentation required for plant certification and weighing and measuring device calibration meeting the requirements of this Subsection before commencing concrete work.

a.	Plant Certification by the National Ready Mix Concrete Association. Certification may be obtained from the National Ready Mix Concrete Association (NRMCA). Information concerning NRMCA certification may be obtained from the NRMCA at 900 Spring Street, Silver Springs, MD 20910 or online at www.nrmca.org. The NRMCA certification is valid for 2 years from the date of inspection.

b.	Plant Certification by a Professional Engineer. Certification may be obtained by an independent inspection and evaluation by a Professional Engineer registered in the State of Alaska using and completing the NRMCA Plant Certification Check List. Correct deficiencies to the satisfaction of the Professional Engineer. The Professional Engineer must sign and seal the completed NRMCA Plant Certification Check List certifying all applicable items have been met. The certification by a Professional Engineer is valid for 2 years from the date of inspection.

c.	Calibration of Weighing and Measuring Devices. Use weighing and measuring devices meeting the requirements of the National Institute of Standards and Technology Handbook 44: Specifications, Tolerances, and other Technical Requirements for Weighing and Measuring Devices, and are calibrated by a commercial scale service or certified by the DOT&PF Division of Measurement Standards & Commercial Vehicle Enforcement. Calibrate weighing and measuring devices using equipment traceable to the Alaska State Standards of Weight and Measure as adopted by AS 45.75.020.

Calibrate weighing and measuring devices:

(1)	no more than 12 months before commencing concrete work,

(2)	after each relocation,

(3)	at least once every 12 months until the work is completed, and

(4)	when, in the opinion of the Engineer, there is a question as to the accuracy or adequacy of the device.

d.	Certification and Calibration Submittals. If the Plant Certification is by the NRMCA, submit a copy of the NRMCA Certificate of Conformance. If the Plant Certification is by a Professional Engineer, submit a copy of the completed NRMCA Plant Certification Check List and associated Fleet Inspection Reporting Spreadsheet.

Submit copies of the calibration worksheets for weighing and measuring devices including the most recent date of inspection and the calibrated accuracy for each weighing and measuring device.

2.	Measuring Materials.

a.	Cementitious Materials. Use cementitious materials of the same brand, type, and from the same plant of manufacture as the cementitious materials used to verify the approved Job Mix Design according to Subsection 501-2.02.7. Ensure the quantity of the Portland cement and the cumulative quantity of Portland cement plus other cementitious materials is proportioned in amounts required by the Job Mix Design and meets the mix acceptance requirements.

Measure cementitious materials by weight. When other cementitious materials, including fly ash, ground granulated blast-furnace slag, or silica fume, are specified in the concrete proportions, the material may be cumulatively weighed with the Portland cement. Weigh cementitious materials on a weighing device that is separate and distinct from those used for other materials. Weigh the Portland cement before other cementitious materials.

Portland cement is permitted to be measured in bags of standard weight (94 pounds). Do not use a fraction of a bag of cementitious materials unless its weight has been determined by calibrated weighting devices.

b.	Aggregates. Use aggregates from the same sources and having the same size ranges as the aggregates used in the trial mixtures or field test record verified approved Job Mix Design. Ensure the quantity of the aggregates is proportioned in amounts required by the Job Mix Design.

Measure aggregates by weight. Establish batch weight measurements on dry materials and adjust the actual scaled weight for the required dry materials weight plus the total weight of moisture, both absorbed and surface, contained in the aggregate.

c.	Water. The total quantity of mixing water includes water added to the batch, ice added to the batch, and water occurring as surface moisture on the aggregates. Measure the added water by weight or volume. Measure added ice by weight. Discharge the flush water (wash water) prior to loading the next batch of concrete. Do not use flush water (wash water) as a portion of the mixing water.

d.	Admixtures. Use concrete admixtures according to the manufacturer's instructions and the approved Job Mix Design. Type A, D, E, F, and G admixtures not included in the approved Job Mix Design may be added according to Subsection 501-2.02.9.

Measure powdered admixtures by weight. Measure paste or liquid admixtures by weight or volume.

3.	Materials Storage and Handling.

a.	Cementitious Materials. Keep cementitious materials dry and free from contaminants. Do not use cementitious materials which have become partially hydrated or which contain lumps of caked cementitious material. If cementitious material is stored longer than 3 months in bags or 6 months in bulk, retest the cementitious material before using, as required in Section 701.

b.	Aggregates. Do not allow segregation of the aggregates or contamination with foreign materials. Separate aggregate to prevent intermixing of specified gradations.

Drain aggregate so the moisture content is uniform and is accounted for during the batching process.

Do not use aggregates that contain ice, are frozen, or have been heated directly by combustible materials. Use steam-coil or water-coil heating when heating aggregates. Use other heating methods only when approved. If using live steam to thaw frozen aggregate piles, drain aggregates to uniform moisture content.

c.	Admixtures. Protect admixtures from contamination, evaporation, or damage. Store admixtures according to the manufacturer’s instructions. Protect liquid admixtures from freezing and from temperature changes affecting the admixture’s performance.

501-3.02 MIXING AND DELIVERY. Mix concrete, in proportioned amounts, according to the approved Job Mix Design. Mix ingredients into a thoroughly intermingled uniform mixture. Do not retemper concrete mixtures. Do not use concrete that has developed initial set prior to placement.

1.	Addition of Water. Additional water may be added on-site provided the following are met:

a.	The volume of concrete in the mixer after the additional water is added does not exceed the maximum mixing capacity.

b.	The water measuring device is calibrated according to Subsection 501-3.01.1.c.

c.	No concrete has been discharged except for slump testing.

d.	The maximum water content for the batch as established by the approved Job Mix Design is not exceeded. Account for the actual volume of concrete remaining in the mixer.

e.	Water additions are completed within 30 minutes after the introduction of the mixing water to the cementitious materials.

The addition of water is not prohibited from being several distinct additions of water. Inject additional water into the mixer under pressure and direction of flow to allow for proper distribution within the mixer. Provide additional mixing to ensure a thoroughly intermingled uniform mixture is attained.

2.	Time for Placement. Discharge the concrete within 1.5 hours of the following:

a.	after adding the mixing water to the cementitious materials, and

b.	after adding the cementitious materials to the aggregates.

The time to complete discharging the concrete may be extended 2 minutes for every degree of temperature at which the concrete is delivered below 70°F, to a maximum total time of 2 hours. The Engineer may waive the time to discharge requirement provided the concrete can be placed without the addition of water.

501-3.03 EVALUATION OF MATERIAL FOR ACCEPTANCE. All concrete in the work will be evaluated for acceptance.

The Engineer may reject a batch or load of concrete failing to meet the requirements for proportions, slump, total air content (if applicable), or temperature. The Engineer may reject a batch or load of concrete, prior to sampling appearing defective in composition.

The Engineer may reject a structure or portion of a structure containing concrete failing to meet the requirements for proportions, requirements for total air content, requirements for compressive strength, was cured in a manner not meeting the required curing conditions, is cracked, spalled or otherwise defective, or is constructed in a manner that does not conform to this Section.

1.	Sampling. The Department will take samples at the discharge point of the placement system, except Class DS concrete will be sampled at the truck discharge.

Provide adequate and representative fresh concrete for sampling and testing as directed by the Engineer. The Engineer will sample the concrete after a minimum of 1/2 cubic yard of concrete has discharged from the placement system. Do not add water or admixtures to the mix after the concrete has been sampled for acceptance testing.

The Engineer will determine aggregate gradation for acceptance based on random samples taken at the plant.

2.	Sampling and Test Methods. The Department will sample and test according to the following:

WAQTC TM 2	Sampling Freshly Mixed Concrete

WAQTC FOP for AASHTO T 309	Temperature of Freshly Mixed Portland Cement Concrete

AASHTO T 22	Compressive Strength of Cylindrical Concrete Specimens

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse Aggregates, and Materials Finer Than No. 200 Sieve in Mineral Aggregate by Washing

WAQTC FOP for AASHTO T 23	Method of Making and Curing Concrete Test Specimens in the Field

WAQTC FOP for AASHTO T 119	Slump of Hydraulic Cement Concrete

WAQTC FOP for AASHTO T 121	Density (Unit Weight), Yield, and Air Content (Gravimetric) of Concrete

WAQTC FOP for AASHTO T 152	Air Content of Freshly Mixed Concrete by the Pressure Method

AASHTO T 231	Capping Cylindrical Concrete Specimens

WAQTC TM 12	Field Sampling and Fabrication of 50-mm (2-in) Cube Specimens using Grout (Non-Shrink) and or Mortar

3.	Batch Tickets. Provide a ticket with each batch of concrete delivered to the project. Include the following information:

a.	Manufacturer plant (batching facility)

b.	Department contract number

c.	Date

d.	Time batched

e.	Time discharge completed

f.	Truck number

g.	Quantity (quantity batched this load)

h.	Type of concrete by class and producer design mix number

i.	Weights of every type of cementitious material

j.	Weights of each aggregate

k.	Weight or volume of each admixture

l	Weight or volume of water added at the plant

m.	Total moisture and absorption percentage for each aggregate

n.	Final water/cement ratio (the concrete placed in the forms)

4.	Proportion Requirements. Meet the proportion requirements of the approved Job Mix Design within the following proportion tolerances:

a.	Total Cementitious Material, weight 	±1%

b.	Aggregates, weight	±2%

c.	Total Water, weight or volume	±3%

d.	Air-Entraining Admixtures, weight or volume	manufacturer's limits

e.	Type B, C, and S Admixtures, weight or volume	±3%

f.	Type A, D, E, F, and G Admixtures, weight or volume	manufacturer's limits

If the total cementitious material weight is made up of different components, keep the component weights within the following tolerances:

(1)	Portland Cement	±1%

(2)	Fly Ash	±5%

(3)	Ground Granulated Blast-Furnace Slag	±5%

(3)	Silica Fume	±10%

Proportion tolerance will be calculated using consistent units for MJMD and MA as follows:

- Where:	P	=	Proportion tolerance, percentage

- MJMD	=	Weight or Volume of component according the approved Job Mix Design

MA	=	Weight or Volume of actual batched component

5.	Slump Requirements. For Class DS concrete, meet the following slump tolerances:

a.	Using the wet-shaft process: 7 inches minimum, 9 inches maximum

b.	Using the dry-shaft process: 6 inches minimum, 9 inches maximum

6.	Total Air Content Requirements. Meet the total air content percentage within a tolerance of ±1.5 of the approved Job Mix Design percentage.

7.	Temperature Requirements. Unless otherwise noted, ensure the concrete temperature is between 50°F and 90°F while being placed in the forms.

8.	Compressive Strength Requirements. Meet the strength requirements for the Specified Compressive Strength. Concrete of the approved Job Mix Design will be considered to meet the Specified Compressive Strength requirements when both of the following conditions are met:

a.	The lowest individual compressive strength test result is not less than the Specified Compressive Strength minus 500 psi, or 90.0 percent of the Specified Compressive Strength, whichever is lower.

b.	The lowest averaged result of three consecutive individual compressive strength tests meets or exceeds the Specified Compressive Strength.

501-3.04 PREPARATION FOR CONCRETE PLACEMENT. Allow time for inspection prior to concrete placement. Do not begin concrete placement without the Engineer's authorization.

Remove debris, concrete splatter, oil, paint, and other foreign substances from the surfaces of forms and reinforcing steel, against which the concrete is to be placed.

During precipitation, or when the Engineer determines precipitation is likely before final set, employ materials and equipment to protect the concrete until final set occurs. Do not expose the concrete to rain or flowing water before final set occurs.

During cold temperatures, ensure materials and equipment are in place according to the cold temperature concreting plan. Heat the forms as necessary. Remove water, snow, ice, and frost before placing concrete.

Remove soil and other debris from pipe piles to the bottom of concrete elevation shown on the Plan.

- Prepare foundations according to Section 205.

Moisten foundations and forms with water before the concrete is placed. Remove standing water on the foundation, in the pile, and in the form before placing concrete.

501-3.05 PLACING CONCRETE. Place concrete conforming to the approved Job Mix Design. Place and consolidate each layer within 30 minutes or before the preceding layer takes initial set, whichever occurs first.

If concrete placement operations are delayed so initial set occurs before placement of the succeeding section or layer, place a joint according to Subsection 501-3.11. The resulting joint will be considered a construction joint. If, in the opinion of the Engineer, the location of the construction joint will affect the strength or durability of the concrete, the Engineer may reject the concrete.

Place concrete in a sequence to obtain a well-consolidated concrete and to prevent cracks. Place concrete as near as possible to final position. Prevent segregation of the mix, displacement of reinforcing steel, and spattering of mortar on the reinforcing steel and forms above the elevation of the layer being placed. Do not deposit a large quantity of concrete at any point and run or work the concrete along the forms. Do not allow concrete to slide down the sides of the forms.

Limit layer thickness to no more than 2.5 feet deep, or the capacity of the vibrators to consolidate and merge the concrete with the previous layer, whichever is less.

Unless otherwise noted, use a tremie, tube, or other such device to limit the free-fall height to less than 5.0 feet when placing operations would involve dropping the concrete more than 5.0 feet.

After initial set, prevent movement of forms, projecting ends of reinforcing steel, and other embedded items.

Do not use aluminum components in contact with fresh concrete.

Place concrete in the superstructure only after substructure forms are removed and the substructure has been inspected.

1.	Pumping Concrete. Concrete may be pumped if the equipment will handle the class of concrete, with the slump and air content specified, and no equipment vibrations will damage freshly placed concrete. Use a pump producing a continuous stream of concrete without air pockets. When pumping is completed, the concrete remaining in the pipeline, if used, must eject without contaminating the concrete or separating the ingredients. Discard concrete contaminated by priming or cleaning the pump. Take concrete samples for testing at the discharge end of the pipe, unless otherwise noted. Provide samples of concrete as directed by the Engineer.

2.	Conveying Concrete. Concrete may be conveyed if the equipment will handle the class of concrete, with the slump and air content specified and without segregation of the aggregate, and no equipment vibrations will damage freshly placed concrete or reinforcing steel. Limit the length of conveyor belts to prevent aggregate segregation or 300 feet, whichever is least. Cover the belt to protect the concrete from heat, evaporation, precipitation, or when the Engineer determines precipitation is likely. Take concrete samples for testing at the discharge end of the conveyor belt. Provide samples of concrete as directed by the Engineer.

3.	Piles. Do not place concrete underwater in piles.

Concrete may be discharged directly into piles and permitted to free-fall into place if the concrete does not contact reinforcing steel or other objects while falling.

4.	Drilled Shaft Foundations. Place concrete following either the wet-shaft process or dry-shaft process, as applicable. Do not begin concrete placement until authorized by the Engineer.

The dry-shaft process may be used where the ground water level and soil and rock conditions are suitable to permit construction of the shaft in a relatively dry excavation, and where the sides and bottom of the shaft can be visually inspected by the Engineer prior to placing the concrete. Relatively dry excavation conditions exist when excavation fluids have been removed from the shaft and the rate of water intrusion is less than 6 inches of water accumulating above the base in a 1-hour period when no pumping is permitted. Suitable soil and rock conditions exist when the sides and bottom of the hole remain stable without caving, sloughing, or swelling between completion of excavation and concrete placement; and loose material and water can be satisfactorily removed prior to inspection and concrete placement. Less than 1 inch of water will be permitted in the bottom of the shaft excavation at the time of concrete placement. For shafts not meeting the dry-shaft process requirements, use the wet-shaft process.

Provide process control testing during concrete placement. Test total air content and slump before placing each batch of concrete in the drilled shaft. Perform sampling and testing according to Subsection 501-3.03.2 using a WAQTC qualified concrete testing technician or ACI certified concrete field testing technician. Test every batch of concrete before placement. Record the time when each sample is collected. Submit test results to the Engineer within 72 hours of completing each test.

When using a tremie to place concrete, use a watertight tremie with an inside diameter of at least 10 inches.

When using a concrete pump to place concrete, meet the requirements in Subsection 501-3.05.1 and use concrete pump lines that are watertight with an inside diameter of at least 5 inches.

a.	Wet-Shaft Process. Place concrete using a tremie or concrete pump. Place concrete continuously until good quality concrete, as determined by the Engineer, is evident at top of the shaft or nearest construction joint. Good quality concrete is considered concrete of the same consistency, appearance, and quality as the concrete being delivered and meeting the applicable mix acceptance requirements. Remove a sufficient volume of concrete to ensure elimination of contaminated concrete at the top of shaft before continuing with subsequent construction operations.

Remove concrete laitance during or immediately after concrete placement operations have ended.

Do not allow water, fluids, drilling aids, or concrete from the top of the shaft to enter streams or other waterways.

Construct the discharge end of the tremie or pump line to prevent water intrusion and permit the free flow of concrete during concrete placement. Use caps, bottom plates, pigs, or other such devices inserted into or attached to discharge pipe to separate the concrete from the excavation fluid during initial charging of the discharge pipe. Ensure the discharge pipe has sufficient length and weight to rest on the shaft base before starting concrete placement.

When using a tremie, provide adequate support so the tremie can be raised to increase the discharge of concrete and lowered to reduce the discharge of concrete. Do not rapidly raise or lower the tremie to increase the discharge of the concrete.

Maintain a positive head of concrete inside the tremie or pump line relative to the excavation fluid level. Position the discharge orifice within one pipe diameter of the shaft base. Do not re-position the discharge pipe until the orifice is at least 8 feet below the concrete surface. Maintain at least 8 feet of concrete above the discharge orifice during concrete placement. Monitor the concrete level during placement to ensure the tremie or pump line discharge orifice remains at least 8 feet below the concrete surface throughout placement.

If the discharge orifice rises above the concrete surface before concrete placement is complete, the shaft will be considered defective. Immediately terminate concrete placement operations and notify the Engineer.

(1)	Concrete Flowability Requirements. Ensure concrete placed in the shaft remains flowable throughout placement operations by maintaining a slump of at least 6 inches and limiting changes in slump to less than 2 inches, until placement is completed. Collect samples from the first batch of concrete. Test slump from the first batch of concrete at the beginning of the concrete placement operations and immediately after concrete placement operations are complete. Record the time when samples are collected and when tests are performed. Submit test results to the Engineer within 72 hours of completing each test.

b.	Dry-Shaft Process. Place concrete continuously until concrete is evident at top of the shaft or nearest construction joint. Concrete may be permitted to free-fall into place if the concrete does not contact the sides of the shaft, reinforcing steel, or other objects while free falling.

When using a tremie or pump line to place concrete, limit the free-fall height to less than 5 feet.

When free falling concrete without a tremie or pump line, use a centering drop chute at least 3 feet long.

Remove concrete laitance during or immediately after concrete placement operations have ended.

(1)	Concrete Plasticity Requirements. Ensure concrete placed in the shaft remains plastic throughout placement operations by completing placement operations before initial set occurs.

5.	Concrete Decks and Approach Slabs. Before placing concrete, operate the finishing machine over the entire length of the deck to check screed deflection, reinforcing steel clearance, and concrete thickness.

Limit the rate of placing concrete to what can be finished before initial set.

Do not place concrete in decks or approach slabs during precipitation, or when the Engineer determines precipitation is likely before final set.

a.	Submittals. Submit a concrete placement plan to the Engineer, at least 30 days before placing concrete. Do not place concrete until after the Engineer has approved the plan. Include the following:

(1)	concrete placement sequence,

(2)	schedule of concrete placement and curing,

(3)	estimated concrete volume of each section,

(4)	placement rate and duration,

(5)	description of finishing equipment,

(6)	placement procedure,

(7)	name of the concrete foreman,

(8)	curing materials, equipment, and procedure.

b.	Pre-concreting Conference. Hold a pre-concreting conference at least 5 working days before placing concrete. Include the Engineer, the superintendent and foremen in charge of placing reinforcing steel, placing concrete, finishing concrete, and curing operations. Discuss construction procedures, personnel, and equipment to be used.

If the project includes more than one concrete placement operation, and if key personnel change between concreting operations, hold additional conferences to include replacement personnel before placing successive concrete sections.

c.	Concrete Decks. Place the concrete deck in the sequence shown on the Plans. The Engineer may approve a revised placement sequence for casting the concrete deck continuously from one end to the other provided the following:

(1)	Do not use Type III Portland cement.

(2)	Submit the means and methods, equipment, workers, and time schedule for conducting a continuous concrete placement and finishing operation in the concrete placement plan.

(3)	Stockpile the materials necessary to complete the placement and have the equipment, incidentals, and workers on the site before beginning concrete placement operations.

(4)	Ensure the continuous concrete placement and finishing operation proceeds at a minimum rate of 30 feet per hour, measured longitudinally along the axis of the span.

(5)	The Engineer determines the revised placement sequence will not reduce the stability during construction and will not reduce the quality, capacity, or durability of the completed structure.

If the Engineer approves the proposal for a continuous concrete placement operation, the Department will observe and evaluate performance to the first planned construction joint in the sequence. At this point, the Engineer may authorize you to proceed with the continuous concrete placement operation or suspend the placement and install a construction joint. The Engineer's decision will be based on whether the concrete can be produced, delivered, and finished at a continuous rate permitting the structure to accommodate final dead load deflections while the concrete is plastic.

If the Engineer suspends the continuous concrete placement operations after the first sequential placement, submit modifications for improving the continuous concrete placement operations, beginning at the other end of the deck. If a second attempt at continuous concrete placement is authorized, the placement will be evaluated and allowed or terminated based on the same criteria as the first sequential placement.

If the Engineer suspends the continuous concrete placement operation after the second attempt, additional attempts will not be permitted. Follow the deck placing sequence shown on the Plans.

501-3.06 CONSOLIDATION OF CONCRETE. Consolidate concrete to make a dense homogeneous mass free of voids and rock pockets. Adequately consolidate each layer to leave a compact, dense, and impervious concrete with smooth faces on exposed surfaces with no visible line of separation between adjoining layers.

Consolidate concrete, except underwater or other exempted placements, by mechanical vibration at the point of deposit. Use vibrators capable of visibly affecting concrete with a 1-inch slump for a distance of at least 18 inches from the vibrator.

Effectively vibrate the full depth of each layer.

For immersion-type vibrators, insert vibrators vertically to a depth penetrating into the previous layer. Withdraw vibrators slowly to avoid segregation or grout pockets. Vibrate in a uniform pattern spaced less than 1.5 times the radius of visible effectiveness.

Avoid vibration of initially set layers and reinforcing steel below the succeeding placement. Do not hold vibrators against reinforcing steel or use them to flow or spread the concrete into place. Manipulate vibrators to produce concrete free of voids, with proper texture on exposed faces, and maximum consolidation. Do not allow the concrete to segregate, form pools of mortar, or form laitance on the surface.

When immersion-type vibrators are used to consolidate concrete around epoxy-coated reinforcing steel, use rubber or nonmetallic vibrator heads that will not damage epoxy coatings.

Concrete may be placed directly into drilled shaft foundations and piles without mechanical vibration; except, vibrate the top 5 feet of concrete. For drilled shaft foundations, consolidate the top 5 feet of concrete after good quality concrete is evident at the top of the shaft and after water, slurry, drilling aids, and other materials other than concrete have been removed.

501-3.07 FINISHING CONCRETE SURFACES. After the concrete is consolidated and prior to the application of curing materials, strike-off unformed concrete surfaces to the required elevation and slope. Finish the surface by floating the surface to remove local irregularities and leave sufficient mortar to seal the concrete surface. Do not use mortar topping for concrete surfaces. Do not use aluminum finishing equipment.

Complete initial floating operations before bleed water or excess moisture is present on the surface and before the concrete takes initial set. Complete final finishing before final set occurs. Do not use finishing aids or additional water to assist in finishing concrete surfaces. Do not finish concrete surfaces if bleed water, excess moisture, or curing materials are present.

Provide formed concrete surfaces with an ordinary finish unless otherwise noted.

1.	Ordinary Finish. An ordinary finish is the finish left on a surface after removing the forms, filling the holes left by the form ties, and repairing defects. Ensure the surface is true and even and free from rock pockets and depressions or projections.

Immediately after removing the forms, remove the metal devices holding the forms in place and passing through the body of the concrete, or cut them back at least 1 inch beneath the surface of the concrete. Remove fins of mortar and irregularities caused by form joints.

Patch cavities produced by form ties, depressions, holes, and voids greater than 1/4 inch. Fill the cavity with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand. Clean the cavity and saturate the concrete with water before filling the cavity. Thoroughly tamp the mixture into place. Float the surface of the mortar before initial set to make the surface neat in appearance. Cure the patch according to Subsection 501-3.08.

Do not repair concrete with rock pockets, cracks, or other defects until the concrete is inspected by the Engineer. Concrete repaired prior to inspection by the Engineer may be rejected. If, in the opinion of the Engineer, the defect will affect the strength or durability of the concrete, the Engineer may reject the concrete. If the defect is greater than 3/4 inch in depth, submit a repair plan including complete details of the method, materials, and equipment proposed for use in repairing the concrete. Obtain the Engineer's approval of the repair plan before repairing the defect. A repair plan is not required if the defect is less than 3/4 inch in depth.

Repair broken corners and edges, rock pockets, and other defects. If the defect is greater than 3/4 inch in depth, repair the defect according to the approved repair plan. If the defect is less than 3/4 inch in depth, chip away coarse or broken material according to Subsection 501-3.16 to obtain a dense, uniform surface of concrete exposing solid coarse aggregate. Cut feathered edges to form faces perpendicular to the surface. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Patch the repaired area with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand.

- Repair cracks according to Subsection 501-3.17.

Perform repairs prior to releasing falsework, prestressing, or applying additional loads to the concrete.

2.	Rubbed Finish. Provide a rubbed finish at locations shown on the Plans. When forms can be removed, wet the surface and then rub with a wooden float until irregularities and form marks are removed and the surface is covered with a lather composed of cement and water. A thin grout composed of one part Portland cement and one part fine aggregate may be used. Allow this lather to set for at least 5 days. Then, smooth the surface by lightly rubbing with a fine carborundum stone.

If the concrete has hardened before being rubbed, use a medium coarse carborundum stone to finish the surface at least 4 days after placing the concrete. Spread a thin grout composed of one part Portland cement and one part fine aggregate over a small area of the surface. Immediately rub the surface with the stone until form marks and irregularities are removed and the surface is covered with a lather. Allow this lather to set for at least 5 days. Then, smooth the surface by rubbing lightly with a fine carborundum stone.

- Complete ordinary finish work before applying the rubbed finish.

3.	Concrete Decks and Approach Slabs. Obtain a smooth riding surface of uniform texture, true to the required grade and cross section.

Use a self-propelled mechanical finishing machine:

a.	capable of forward and reverse movement,

b.	with a rotating cylindrical single or double drum screed,

c.	with necessary adjustments to produce the required cross-section, line, and grade,

d.	allowing screeds to be raised and lowered, and

e.	with an upper vertical limit of screed travel permitting the screed to clear the finished concrete surface.

When placing concrete abutting previously placed concrete, equip the finishing machine to travel on the existing concrete.

The Engineer may approve hand-operated motorized roller screeds (friction screeds) where jobsite conditions prohibit the use of conventional configuration finishing machines described above, for small areas less than 12 feet wide, and on approach slabs in which conventional configuration finishing machines are not used to finish the concrete deck. Do not use vibratory screeds.

Use equipment capable of striking off the full placement width without intermediate supports or rails. Use rails resting on adjustable supports that can be removed with the least disturbance to the concrete. Place the supports on structural members or on forms rigid enough to resist deflection. Use supports that are removable to at least 2 inches below the finished surface. If possible, place rails outside the finishing area. If not possible, place them above the finished surface.

Use rails (with their supports) that are strong and stiff enough for operation of the equipment without excessive deflection. Place and secure rails for the full length of the deck before placing concrete. Set the rails to the proper grade and elevations to ensure the required profile is provided.

- After placing and consolidating the concrete, carefully strike off the concrete surface. Correct imperfections left on the deck. Provide a float finish to surfaces receiving a waterproof membrane. Texture other surfaces with a heavy-broom finish perpendicular to the direction of traffic.

Do not place finishing machines or other loads on the screed rail supports or on features supporting fresh concrete after the concrete has initially set and before the concrete attains at least 80 percent of the Specified Compressive Strength.

Do not release falsework or wedges supporting concrete on either side of a joint until each side has cured as specified.

4.	Curb, Sidewalk, and Concrete Barrier Surfaces. Finish exposed faces of curbs, sidewalks, and concrete barriers to true surfaces and provide a broom finish. Broom finish sidewalks perpendicular to the direction of traffic.

5.	Sandblasted Finish. Sandblast the cured concrete surface with hard, sharp abrasive media to produce an even fine-grained surface in which the mortar has been cut away, leaving the aggregate exposed.

6.	Trowel Finish. Trowel the surface smooth and free of trowel marks.

501-3.08 CURING CONCRETE. Maintain a satisfactory moisture content and temperature in the concrete immediately after finishing operations are completed.

The Engineer may reject a structure or portion of a structure containing concrete cured in a manner not meeting the required curing conditions or is cracked, spalled, or otherwise defective.

1.	Initial Curing Period. Before final curing, ensure the surface of the concrete is kept moist. If the concrete surface begins to dry before the final curing method can be applied, prevent further loss of moisture by one or more of the following methods:

a.	Fog Spray. Use equipment producing a fog spray from an atomizing nozzle with sufficient velocity to cover the entire concrete surface. Direct the atomized water spray above the concrete surface to allow the fog to drift down to the concrete surface. Do not apply the discharge of the atomized water spray directly at the concrete surface. Continue fogging to maintain the reflective appearance of the damp concrete. Do not allow the surface to dry, or to undergo cycles of drying and wetting. Keep the concrete surface damp, but do not accumulate water until after final set has occurred. Use water meeting the requirements of Subsection 712-2.01.

b.	Evaporation Rate Reducer. Apply a monomolecular film intended specifically as an evaporation rate reducer to entrap bleed water or excess moisture on the concrete surface. Apply the evaporation rate reducer according to the manufacturer’s written instructions. Do not use the evaporation rate reducer during finishing operations or as a finishing aid. Do not use evaporation rate reducers on concrete surfaces receiving a waterproofing membrane such as concrete decks, approach slabs, end diaphragms and decked precast concrete members.

2.	Final Curing Period. Unless otherwise noted, employ the final curing method immediately following finishing operations.

Use wet curing on construction joints, concrete with a mix design water-cement ratio less than 0.40, and concrete decks, approach slabs, and other concrete surfaces subject to tire contact in the completed structure. For other concrete, use wet curing, liquid membrane-forming curing, forms-in-place curing, or a combination of these curing methods.

Do not use liquid membrane-forming curing compounds on concrete surfaces to which other materials will be cast against or bonded such as concrete and waterproofing membranes.

In addition to the requirements in this section, precast concrete members may use accelerated curing.

a.	Wet Curing. Until the end of the curing period, provide continuous moisture by:

(1)	watering a covering of heavy burlap blankets or quilted cotton mats,

(2)	keeping concrete surfaces wet with water continuously,

(3)	wetting the outside surfaces of wood forms.

Wait to install curing materials until the concrete has sufficiently hardened to permit such operations without damaging the concrete or marring the finish. While waiting to employ curing materials, maintain the concrete surface moisture as specified for the initial curing period.

Uniformly distribute absorbent materials across the entire concrete surface. Apply water in a manner that will not displace the curing materials or erode the concrete surface. Keep the concrete surfaces continuously wet. Do not allow concrete surfaces to dry or alternate with wetting and drying cycles. Cover the concrete, wooden forms and absorbent material with impermeable sheeting. Use white reflective impermeable sheeting if direct sunlight is present, or if the Engineer determines direct sunlight may be present during the curing period.

Do not use absorbent materials containing harmful substances such as sugar or fertilizer, or materials that may discolor the concrete.

b.	Liquid Membrane-Forming Curing Compounds. Apply liquid membrane-forming compounds immediately after final finishing and as soon as the free water has disappeared, no water sheen is visible, and bleeding has essentially ceased. Apply two coats of liquid membrane-forming compound with the second coat at right angles to the first. Apply both coats of liquid membrane-forming compounds uniformly until the original color of the concrete is obscured. Follow the manufacturer's instructions when applying the liquid membrane-forming compound, except apply at a total coverage rate of at least 1 gallon per 150 square feet.

Do not apply the liquid membrane-forming compound to dry concrete surfaces. Moisten the concrete surface, without standing water, before applying the liquid membrane-forming compound. Protect the membrane from damage for the duration of the curing period. Re-apply the liquid membrane-forming compound if the membrane is cracked or damaged during the curing period.

c.	Forms-In-Place Curing. Formed concrete surfaces may be cured by retaining the forms in place for the entire curing period. Keep the forms moisture tight. Do not loosen forms. For wooden forms, keep the forms wet as required for wet curing. If gaps develop between the forms or between the forms and concrete:

(1)	remove the forms and implement another curing method

(2)	keep the gaps continuously filled with water for the remainder of the curing period.

d.	Accelerated Curing. This method may be used only for precast concrete members manufactured in plants with at least five years of experience precasting concrete using accelerated curing methods.

During the curing period, keep the concrete in a saturated curing atmosphere with a relative humidity of at least 90 percent until the concrete achieves the required release strength.

The curing period may be accelerated by using saturated low-pressure steam, convection-heat, or radiant-heat in a suitable curing chamber to contain the live steam or heat. Provide at least 3 inches of clearance between the enclosure and forms to allow adequate circulation.

If accelerated curing methods are used, embed at least one temperature-recording device in the concrete to verify concrete temperatures are within the specified limits. Install one temperature-recording device, accurate to ±5°F, near the member’s midpoint, 6 to 8 inches from the top or bottom, and along the member’s centerline. Monitor the concrete temperature with the temperature-recording device sensor arranged and calibrated to continuously record, date, and identify the concrete temperature throughout the heating cycle. Begin recording temperatures once concrete is placed in the forms. Stop recording temperatures after the heating cycle is complete and when the concrete temperature is within 20°F of the air temperature to which the concrete will be exposed. Upon request, submit the temperature record to the Engineer for each precast concrete member.

While waiting to begin the heating cycle, maintain the concrete temperature between 50°F and 90°F and maintain concrete surface moisture as specified for the initial curing period. Do not apply steam, convection-heat or radiant-heat prior to initial set except to maintain the concrete temperature. Determine the time of initial set according to AASHTO T 197.

Begin the heating cycle immediately after the initial set. Prevent hot air and steam from blowing directly onto the concrete or forms. Increase the concrete temperature at an average rate not exceeding 40°F per hour until the curing temperature is reached. Limit curing temperature within the concrete to 175°F maximum. Decrease the concrete temperature not more than 40°F per hour until reaching a temperature 20°F above the temperature of the air to which the concrete will be exposed.

Apply radiant heat by pipes circulating steam, hot oil, or hot water, or by electric heating elements.

3.	Curing Temperature. To achieve adequate curing, maintain the concrete temperature at or above 50°F during the curing period. Add one addition day of curing for each day or portion of a day the concrete temperature falls below 50°F during the curing period.

4.	Ending Curing Operations. Continue curing operations uninterrupted until the required concrete properties, strength, and durability have developed or until there is reasonable assurance these properties will be achieved after the curing operations have been terminated.

Curing operations may be terminated after following are satisfied:

a.	The concrete has cured for:

(1)	at least 7 days.

(2)	at least 10 days when fly ash or ground granulated blast furnace slag in excess of 10 percent by weight of the Portland cement are used in the mix.

b.	The compressive strength from informational field tests reaches the following:

(1)	70 percent of the Specified Compressive Strength if post curing concrete temperature is expected to remain at or above 50°F until 100 percent of the Specified Compressive Strength is attained.

(2)	100 percent of the Specified Compressive Strength, if post curing conditions are expected to allow the concrete temperature to fall below 50°F before 100 percent of the Specified Compressive Strength is attained.

501-3.09 PROTECTION OF CONCRETE. Protect concrete from damage. Do not apply loads to the concrete until curing operations are completed and until the Engineer determines the concrete has attained sufficient strength to safely carry the applied loads without damage. Unless otherwise noted, sufficient strength is attained when the concrete has a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

- Release forms and falsework according to Section 512.

During the curing period, protect concrete from damaging mechanical disturbances. Protect concrete surfaces from damage by construction traffic, equipment, materials, rain or running water, and other adverse weather conditions. Meet the vibration limits during pile driving of Section 505.

The Engineer may reject a structure or portion of a structure containing concrete cracked, spalled, or otherwise damaged. Repair cracks according to Subsection 501-3.17.

Do not backfill against concrete structures until the end of the curing period and until the concrete has attained a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

Obtain authorization from the Engineer before driving vehicles or equipment, or storing materials on the structure. Keep the structure closed to traffic until the concrete has been accepted. Obtain authorization from the Engineer before opening the structure to traffic.

1.	Cold Temperature Protection. When air temperatures are expected to be below 35°F during concrete placement or the curing period, have materials and equipment in place to prevent the concrete temperature from falling below 35°F. Implement the cold temperature concreting plan when the air temperature in the shade, away from artificial heat, is less than 35°F or, in the opinion of the Engineer, is likely within 24 hours.

a.	Submittals. Submit a cold temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to be below 35°F during the concrete placement or during the curing period. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during cold weather for each concrete placement. Include procedures for abrupt changes in weather conditions and equipment failures.

b.	Preparation. Remove snow, ice, and frost from surfaces that will touch the concrete. Before beginning concrete placement, thaw the subgrade to at least 2 feet below the concrete to be placed. Do not place concrete around or adjacent to forms, embedded items, concrete, steel, or other materials unless such items are preheated and maintained at a temperature above 35°F.

c.	Temperature of Concrete Before Placement. Ensure concrete is between 50°F and 70°F during placement. Obtain these temperatures by heating the mixing water and/or aggregate. Heat mixing water to no more than 150°F. Heat aggregate as provided in Subsection 501-3.01.3.b.

When the temperature of the water or aggregate exceeds 100°F, mix them together so temperature of the combined ingredients does not exceed 80°F when the cementitious materials are added.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to cold weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

If the minimum curing temperature cannot be maintained, do not allow the concrete temperature to drop below 35°F. Provide extra protection in areas especially vulnerable to temperatures below 35°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Maintain the concrete temperature using methods such as insulated forms, enclosures, and indirect heat. When using combustion heaters, vent flue gases to the outside of the enclosure. Prevent overheating areas of concrete or drying during the curing period by directing heaters and ducts away from the concrete surface. Do not expose the concrete surface to air with a temperature more than 90°F, unless higher values are required by an accepted curing method.

Protection may be terminated when the air temperature in the shade, away from artificial heat is rising, above 35°F, and is expected to remain above 35°F until the end of the curing period. At the end of the protection period, remove the protection so the concrete surface drops in temperature gradually at a rate not more than 1.25°F per hour until the concrete temperature is within 20°F of the air temperature in the shade, away from artificial heat. If water curing is used, terminate the addition of water to the surface and allow the concrete surface to dry prior to exposure of the concrete to freezing temperatures.

2.	Hot Temperature Protection. When air temperatures are expected to exceed 90°F during concrete placement, have materials and equipment in place to prevent the concrete temperature from exceeding 90°F before final set and exceeding 150°F during the final curing period. Implement the hot temperature concreting plan when the air temperature in direct sunlight is greater than 90°F.

a.	Submittals. Submit a hot temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to exceed 90°F during the concrete placement. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during hot temperature for each concrete placement. Include procedures for abrupt changes in temperature conditions or equipment failures.

b.	Preparation. Prior to placing concrete, plan to minimize the exposure of the concrete to hot temperatures and direct sunlight. Cool surfaces that will touch the concrete to less than 90°F.

Do not sprinkle fine aggregate piles with water. If sprinkling coarse aggregates, monitor the moisture content and adjust the mixing water for the free water in the aggregate.

If replacing all or part of the mixing water with crushed ice, then ensure the ice is completely melted and thoroughly mixed with the other concrete materials before concrete placement commences.

c.	Temperature of Concrete Before Placement. Ensure concrete being placed in forms is between 50°F and 70°F. Obtain these temperatures by cooling the mixing water and/or aggregate.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to hot weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

Provide extra protection in areas especially vulnerable to temperatures above 90°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Protection may be terminated when the air temperature in direct sunlight drops below 90°F and is expected to remain below 90°F for at least 24 hours.

501-3.10 TOLERANCES. Produce concrete elements conforming to the following tolerances:

1.	Length: ±1/4 inch per 25 feet of member length, but not to exceed ±1 inch.

2.	Cross-sectional Dimensions:

a.	For dimensions 6 inches or less: -1/8 inch to +1/4 inch.

b.	For dimensions over 6 inches but not over 18 inches: -1/8 inch to +3/8 inch.

c.	For dimensions over 18 inches: -1/4 inch to +3/8 inch.

3.	Distortion of Cross-section: Limit the slope with respect to the specified surface, plane, or line to less than ±1/16 inch per foot, but not to exceed ±1/4 inch measured perpendicular to the long axis of member.

4.	Surface Irregularities (deviation from a 10-foot straight edge):

a.	For surfaces receiving a topping or are buried: ±1/4 inch.

b.	For surfaces not receiving a topping or are visible in the completed work: ±1/8 inch.

5.	Camber: Do not vary from the approved camber more than ±1/8 inch per 10 feet of length, but not to exceed 1 inch. In addition, the camber of each girder may not differ from the camber or the other girders by more than 1 inch.

6.	Lateral Sweep (deviation from a straight line parallel to centerline of member):

a.	For member length 40 feet or less: ±1/4 inch.

b.	For member length over 40 feet but not over 60 feet: ±3/8 inch.

c.	For member length over 60 feet: ±1/2 inch.

7.	Deck Width (measured out-to-out): ±1/4 inch per 25 feet of width, but not to exceed ±3/4 inch, except not more than ±1/2 inch where more precision is dictated by details such as anchor bolts, parallel wing walls, bridge rail and barriers, etc.

8.	Position and Alignment:

a.	Bottom of footing elevation: ±0.1 feet.

b.	Profile grade: ±0.05 feet.

c.	Lateral position: ±0.1 feet.

d.	Skew: ±0.05 degrees.

9.	Bearing Seats:

a.	Elevation: ±0.01 feet

b.	Variation between bearing seats: Do not vary from a straight line coincident with the centerline of bearings and parallel to the surface of the bottom flanges more than 0.01 feet.

c.	Grade and cross slope: ±0.005 feet per foot.

10.	Openings:

a.	Size of opening: ±1/4 inch.

b.	Location of centerline of opening: ±1/2 inch.

11.	Embedded Items:

a.	Bolts: ±1/4 inch.

b.	Utility hangers: ±1/2 inch.

c.	Weld Plates: ±1/2 inch measured along the length of the member, ±1/8 inch measured perpendicular to the length of the member.

d.	Inserts: ±1 inch.

e.	Rail post anchor plates: ±1/4 inch.

f.	Expansion joints: ±1/8 inch.

g.	Electrical conduits: ±1/2 inch.

h.	Deck drains: ±1/2 inch.

i.	Other embedded items: ±1/2 inch.

501-3.11 CONSTRUCTION JOINTS. Unless otherwise noted, locate construction joints where specified in the Contract documents. Obtain approval before adding, deleting, or relocating construction joints specified in the Contract documents. Make requests for such changes in writing, accompanied by a drawing depicting the joint. The Engineer will evaluate the proposed construction joint to determine if the joint will affect the strength or durability of the concrete. Joints noted as "permissible" do not need the Engineer's approval before deleting. When permitted, place the joints where they will not be exposed to view in the finished structure.

At horizontal construction joints, place gage strips 1-1/2 inches thick inside the forms along exposed faces to give the joints straight lines.

Do not use wire mesh forming material.

If the Plans require a roughened surface on the joint, create grooves at right angles to the length of the member. Make grooves that are 1/2 to 1 inch wide, 1/4 to 1/2 inch deep, and spaced equally at twice the width of the groove. Terminate the grooves within 1-1/2 to 2 inches from the edges of the joint.

If the Plans require a smooth surface on the joint, provide a trowel finish.

Include shear keys at the joint when the Contract documents do not require a roughened surface or a smooth surface. Make shear keys of formed depressions with slight beveling to ensure ready form removal. Do not use raised shear keys. Make shear keys that meet the following:

1.	For tops of beams, at the tops and bottoms of boxed girder webs, in diaphragms, and in crossbeams, use shear keys 1-1/2 inches deep, 8 inches long, and spaced at 16 inches.

2.	In other locations, use shear keys at least 1-1/2 inches deep and 1/3 of the joint width.

Terminate the shear keys within 1-1/2 to 2 inches from the edges of the joint.

Clean construction joints of surface laitance and other foreign materials before fresh concrete is placed against the surface of the joint. Flush construction joints with water and allow the joint to dry to a surface-dry condition immediately prior to placing concrete.

501-3.12 FORMS AND FALSEWORK. Use forms and falsework designed and constructed according to Section 512.

501-3.13 PRECAST CONCRETE MEMBERS. In addition to the requirements listed in this Section, conform to Section 502 when fabricating prestressed concrete members.

1.	Shop Drawings. Provide shop drawings for precast concrete members. Include details not provided in the Plans for the construction and erection of the members. Cast members only after shop drawings are approved. Use precast methods for cast-in-place elements when approved. Submit shop drawings, showing construction joint details and other required information.

2.	Manufacture. Prestress concrete according to Section 502. Fabricate and install reinforcing steel according to Section 503.

Unless otherwise noted, use Class P concrete for precast concrete members meeting the Specified Compressive Strength noted on the Plans.

3.	Storage and Handling. Handle and move precast concrete members without damage. Store and transport precast concrete members in an upright position with the directions of the support reactions on the member during storage or transport as if in the final position. Locate support points during transport and storage within 30 inches of their final position, or as shown on approved shop drawings. Ship only after the member has cured at least 7 days and has a compressive strength not less than 100 percent of the Specified Compressive Strength.

4.	Erection. Maintain member stability during transport, lifting, and erection operations. Limit concrete tension stresses due to transport, lifting, and erection operations to less than 500 psi.

Set interchangeable precast concrete members so the initial difference between the top surfaces of the edges of adjacent precast concrete members is no more than 1/2 inch at midspan and no more than 1/4 inch at the bearings.

Set and securely brace precast concrete members within a span before making shear connections. Secure the member to the structure, and provide temporary braces necessary to resist wind or other loads immediately after erecting each precast concrete member.

Provide and use forcing devices as shown in the Plans or as recommended by the precast concrete member manufacturer. Use devices maintaining the top edges of adjacent members at the same elevation while casting or welding diaphragms, welding shear connector plates, and while placing and curing grout in the shear keys.

Make field welds according to Section 503 and Section 504.

Install cast-in-place diaphragms within 2 weeks after setting precast concrete members on their bearings.

If cast-in-place diaphragms cannot be placed within the prescribed time limit, ensure the members are adequately braced to resist movement and rotation. Submit a bracing plan including complete details and substantiating calculations, sealed by a Professional Engineer registered in the State of Alaska.

Erect and place precast deck panels so the mating surfaces do not allow grout leakage. Seal joints where grout leakage may occur.

When the Plans require filling keyways between adjacent concrete members with grout, place grout meeting Subsection 701-2.03 and according to the manufacturer's written instructions. Clean joints of surface laitance and other foreign material before placing grout. Do not place loads on the grouted members until the grout compressive strength has reached 5000 psi.

Tightly pack and rod the grout in the keys and spaces. Keep the grout surface smooth and neat. Ensure the grout surface meets the member edges throughout their lengths and matches the surface elevation of the members with a tolerance of ±1/8 inch.

501-3.14 PLACING ANCHOR BOLTS. Secure anchor bolt assemblies where shown on the Plans.

When casting anchor bolts in concrete, secure anchor bolts before placing concrete in the forms. Do not disturb anchor bolts after concrete has been placed.

When installing anchor bolts in pipe sleeves, pre-cast holes, cored holes, or drilled holes, completely fill the cavity with grout meeting Subsection 701-2.03. Do not allow water to freeze in the cavity. Do not allow foreign material in the cavity.

501-3.15 UTILIDUCTS, PIPES, CONDUITS, DUCTS, AND UTILITY HOLES. When utiliducts, pipes, conduits, and ducts will be encased in concrete, install them in the forms before placing the concrete. Support the utiliducts, pipes, conduits, and ducts to prevent displacement during concrete placement.

Install utiliducts and utility holes parallel to the roadway centerline unless noted otherwise. Prevent bond between the utiliducts and concrete by tightly wrapping the utiliducts with at least two layers of asphalt felt.

501-3.16 REMOVING CONCRETE. Do not damage other portions of the structure remaining in place when removing concrete.

Determine and delineate the extent of removal area. Outline the area with a 3/4-inch deep saw cut to form faces perpendicular to the surface prior to the removal of concrete. Do not cut or damage existing reinforcing steel or prestressing steel. During the course of removal, the Engineer may suspend removal or may require additional removal and outline saw cut.

Use any combination of mechanical methods, water-blast cleaning, or abrasive-blast cleaning to remove coarse or broken concrete until a dense, uniform surface of concrete exposing solid coarse aggregate is obtained. When using mechanical methods for removal of concrete, meet the following:

1.	Use impact tools weighing less than 15 lbs.

2.	Operate impact tools at an angle less than 45 degrees relative to the surface of the concrete being removed.

3.	Use hand tools such as hammers and chisels or small air chisels, water blast cleaning, or abrasive blast cleaning to remove final particles of unsound concrete.

During the removal operation do not damage existing reinforcing steel, prestressing steel, or concrete to remain in place.

- Before applying the repair material, clean the surface according to ASTM D 4258 within 24 hours of applying the repair material.

- Use water meeting the requirements of Subsection 712-2.01 for removal operations.

501-3.17 CRACK REPAIR. The Engineer will evaluate concrete that is cracked during execution of the Contract. Measure cracks at their widest point.

For concrete decks and approach slabs, allow the Engineer to inspect any surface cracking immediately after termination of concrete curing operations, before prestressing (if applicable), and before releasing falsework. If any 500 square foot portion of the concrete deck or approach slab has cracks, whose width exceeds 0.020 inches and combined lengths total more than 16 feet, treat the surface by performing low-viscosity resin crack repair.

For other concrete, cracks will be evaluated based on the crack width.

1.	For crack widths equal to and greater than 0.060 inches, the concrete will be considered unacceptable. Remove and replace the material.

2.	For cracks widths equal to and greater than 0.013 inches but less than 0.060 inches, the Engineer will evaluate the cracked concrete for structural adequacy and durability. If the Engineer determines the cracked concrete is unacceptable, remove and replace the material. Otherwise, repair the crack by performing low-pressure crack repair.

3.	For cracks widths less than 0.013 inches wide, the crack will be considered acceptable with no additional evaluation or repairs required.

Perform crack repairs and replace unacceptable concrete at no cost to the Department. No contract time extension will be given for repairing, removing, and replacing unacceptable material.

1.	Low-Pressure Crack Repair. Repair cracked concrete according to the following requirements:

a.	Crack Repair Plan. Submit a crack repair plan to the Engineer. Do not repair the crack until the Engineer has approved the crack repair plan. Include the following in the crack repair plan:

(1)	Experience of the injection equipment technicians

(2)	Evaluation of the crack width and the recommended epoxy viscosity allowing the epoxy to achieve and maintain the penetration requirements

(3)	Material information including manufacturer's product data sheets

(4)	Equipment

(5)	Crack preparation, injection procedures, and injection sequence

(6)	Cleanup procedures

b.	Experience. Provide epoxy injection technicians who have a minimum of 2 years experience in performing repairs using the methods and materials of the selected system.

c.	Materials. Use epoxy adhesive for crack sealing meeting the requirements of Subsection 501-2.01.5 and capable of containing the crack injection epoxy. Use epoxy adhesive for crack injection meeting the requirements of Subsection 501-2.01.5 and of viscosity capable of filling at least 90 percent of the crack volume.

d.	Equipment. Use positive displacement plural component pumps, specifically designed to meter, mix, and to inject epoxy, and capable of filling at least 90 percent of the crack volume.

e.	Surface and Crack Preparation. Remove contaminants and other foreign material reducing the effectiveness of the surface seal and repaired crack. Allow adequate time for drying. If cleaning solutions are used, perform trial tests to verify the contaminants can be removed. Prepare the surface and crack according to the epoxy manufacturer’s instructions.

f.	Entry and Venting Ports. Install entry/venting ports spaced equal to the thickness of the concrete member along one face of the crack. Acceptable types of entry/venting ports are fittings inserted into drilled holes, bonded flush fittings, and gasket devices covering unsealed portions of interrupted seals, allowing injection of epoxy directly into the crack without leaking epoxy.

g.	Mixing Epoxy for Crack Sealing. Mix the epoxy adhesive for crack sealing to the volume ratio prescribed by the manufacturer.

h.	Surface Sealing. Seal the surface of the crack with epoxy adhesive for crack sealing.

i.	Mixing Epoxy for Crack Injection. Mix the epoxy adhesive for crack injection to the volume ratio prescribed by the manufacturer.

j.	Epoxy Injection. Assure the crack seal is cured and capable of containing the crack injection epoxy. Inject the epoxy according to the epoxy manufacturer’s instructions. Do not inject epoxy until the air, substrate, and epoxy are within the manufacturer's application temperature range. Limit injection pressure to prevent propagation of the crack, prevent additional damage, and injection pressure in excess of 50 psi.

Inject the epoxy in the sequence noted in the approved crack repair plan. Ensure at least 90 percent of the crack volume is filled.

Maintain the epoxy temperature within the manufacturer's application temperature range during injection operations and until the epoxy is cured.

k.	Finishing and Cleanup. After the injected epoxy is cured, remove ports and surface seal flush with the concrete surface. Do not damage the injected epoxy and do not heat the surface seal to aid in removal.

2.	Low-Viscosity Resin Crack Repair. When concrete deck or approach slab crack repair is required, the Engineer will define the repair area with the following boundary limits:

a.	Beginning and ending on straight lines perpendicular to the direction of traffic and extending across the entire width of the concrete deck or approach slab, between the concrete barriers or curbs.

b.	Beginning and ending at least 5 feet beyond the furthest opposing cracks, measured from where the crack widths exceeds 0.020 inches

If grinding is required, treat the concrete before grinding.

Before treatment, ensure the concrete surface is clean, sound and free of foreign materials that may reduce the effectiveness of the repaired cracks. If the concrete surface becomes contaminated before placing the resin, repeat the cleaning process.

Apply low-viscosity resin to the repair area. Protect barriers, railing, joints, and drainage facilities to prevent contamination by the treatment material.

Completely cover the deck surface with resin so the resin penetrates and fills cracks. Ensure the relative humidity is less than 80 percent, the prepared area is dry, and the surface temperature is at least 50°F and not more than 90°F when the resin is applied. Apply the resin and distribute excess material within the manufacturer's listed pot life. For textured surfaces, including grooved surfaces, remove excess material from the texture indentations.

For concrete decks and approach slabs not receiving a waterproofing membrane, apply aggregate for abrasive finish within 20 minutes of resin application and before setting occurs. Broadcast the aggregate for abrasive finish evenly over the entire treated area at a rate of 1.5 to 2.5 pounds per square yard.

501-3.18 CLEANUP. Remove concrete splatter, paint marks, laitance, rust staining, chamfer strips, and other material not providing a uniform texture and color to the concrete surface.

501-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Cubic Yard. The lesser of the actual volume or neat line volume of each class of concrete accepted in place in the finished structure.

Class DS Concrete. The sum of the lengths of drilled shafts complete in place, measured along the centerline of the drilled shaft from the bottom to the top.

- Precast Concrete Members. Measured per unit, complete in place.

- Crack repair for unacceptable concrete will not be measured for payment.

501-5.01 BASIS OF PAYMENT.

Material not appearing in the Bid Schedule and is contained within, embedded, or attached to concrete elements is subsidiary.

- Crack repair for unacceptable concrete is subsidiary.

Precast Concrete Member. Payment for precast concrete member includes materials and work for the following items: Class P concrete, reinforcing steel contained in the member, prestressing steel, plates, nuts, inserts contained within the concrete member, bolts, studs, anchor bars, blockouts, elastomeric bearing pads, grout, drains, and other miscellaneous steel embedded in or attached to the precast concrete member.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

501(1)	Class A Concrete	Lump Sum

501(2)	Class A-A Concrete	Lump Sum

501(3)	Class A Concrete	Cubic Yard

501(4)	Class DS Concrete (8’-0” Dia.)	Linear Foot

DOT BRIDGE-082912

Special Provisions

Replace Section 503 with the following:

SECTION 503

REINFORCING STEEL

503-1.01 DESCRIPTION. Furnish and place reinforcing steel according to the Contract documents.

503-1.02 DEFINITIONS.

STIRRUP. Reinforcement used to resist shear and diagonal tension stresses in a structural member, installed perpendicular to or at an angle to the longitudinal reinforcement; lateral reinforcement formed of individual or paired units, open or closed.

TIE. Reinforcement with hooked ends tied at right angles to and enclosing the longitudinal reinforcement.

HOOP. A one-piece closed tie or continuously wound tie, the ends of which are hooked or welded together, that encloses the longitudinal reinforcement.

BAR SIZE / DIAMETER. Nominal dimensions equivalent to those of a circular area having the same weight per foot as the AASHTO/ASTM designated bar.

SPIRAL. Continuously wound reinforcement in the form of a cylindrical helix.

LONGITUDINAL REINFORCEMENT. Reinforcement parallel to the length of a concrete member.

LATERAL REINFORCEMENT. Reinforcement perpendicular to the length of a concrete member.

COVER. The least distance between the surface of embedded reinforcement and the outer surface of the concrete.

HOOK. A bend in the end of a reinforcing bar.

LOT. A defined quantity.

503-2.01 MATERIALS.

Reinforcing Steel Bars	Subsection 709-2.01

Epoxy-Coated Reinforcing Steel Bars	Subsection 709-2.01

Headed Reinforcing Steel Bars	Subsection 709-2.01

Epoxy Coating Patch Material	Subsection 709-2.01

Zinc-coated Galvanized Reinforcing Steel	Subsection 709-2.01

Zinc-coated galvanized reinforcing bars may be substituted for epoxy-coated reinforcing bars. Use only zinc-coated galvanized reinforcing bars or epoxy-coated reinforcing bars and not a combination thereof.

CONSTRUCTION REQUIREMENTS

503-3.01 BAR LIST. Furnish order lists and bending diagrams for approval according to Subsection 105-1.02. Furnish order lists and bending diagrams detailed in accordance with ACI 315, Chapter 3.

Do not substitute reinforcing bars of different size, material, coating, or grade without prior approval of the Engineer. When substituting epoxy-coated reinforcing steel for uncoated reinforcing steel, protect and repair all epoxy-coated bars according to Subsection 503-3.02.

503-3.02 PROTECTION OF MATERIALS. Protect reinforcing steel from damage at all times. Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of dirt, loose rust or scale, paint, oil, or other foreign substance. Pressure wash all reinforcing steel that has a surface coating of dirt, dust, or has been exposed to salt spray or other deleterious substances. Use a pressure washer with at least 2000 psi at all elevations. Keep the nozzle tip no more than 12 inches from the surface during all phases of power washing. Do not weld or tack weld reinforcing steel except as noted in the Contract documents and approved by the Engineer. When transporting, storing, or constructing in close proximity to bodies of salt water, keep all reinforcing steel in enclosures that provide protection from the elements.

Do not damage galvanized or epoxy-coated reinforcing steel. When handling coated reinforcing steel, avoid bundle-to-bundle and bar-to-bar abrasion. Use padded bundling bands. Handle coated bars using equipment with padded contact areas. Lift bundles with a strongback, multiple supports, or a platform bridge to prevent bar-to-bar abrasion from sags in the bar bundle. Do not drop or drag the bars or bundles. Off-load bars as close as possible to their points of placement to minimize re-handling.

Store coated reinforcing steel off the ground. When stacking of bars is necessary, place supports between bundles. Place supports sufficiently close to prevent sags in the bundles. Store coated and uncoated bars separately.

Protect epoxy-coated reinforcing steel from sunlight, and weather exposure during shipping and storage. Cover epoxy-coated reinforcing steel and bundles with opaque polyethylene sheeting or other protective material. Secure covering and allow air circulation to minimize condensation under the covering. The Engineer will reject epoxy-coated reinforcing steel when the cumulative environmental exposure time, including all uncovered storage time after coating application to full embedment in concrete, exceeds 2 months.

The Engineer will reject epoxy-coated reinforcing steel when the extent of damaged coating exceeds 2 percent of the surface area in any 1-foot length of bar. When the extent of damaged coating does not exceed 2 percent of the surface area in any 1-foot length of bar, repair all damaged coating. Coating damage includes cracks, abrasions, chips, bond loss (the coating can be removed with a peeling action by the finger), and exposed steel areas visible to a person with normal or corrected vision prior to concrete placement. Repair coating damage as soon as possible and before visible oxidation appears on the steel surface. Repair coating damaged due to shipment, storage, and handling prior to placing the reinforcing steel.

Prepare coating damage prior to applying patch material. Clean and remove all disbonded areas of coating. Remove loose and deleterious materials. In cases when rust is present, remove rust by thoroughly cleaning the area using blast cleaning, filing, or power brushing in a manner that minimizes damage to the sound coating. The Engineer will reject epoxy-coated reinforcing steel when the removed coating exceeds 2 percent in any 1-foot length of bar or if the weight, dimensions, cross-sectional area, or tensile properties are less than the minimum requirements of the applicable specification.

Use an approved epoxy coating patch material according to the material manufacturer's recommendations. Apply patching material according to the written instructions furnished by the patching material manufacturer. Allow the patching material to fully cure before placing concrete. The Engineer will reject epoxy-coated reinforcing steel when the surface area covered by patching material exceeds 5 percent in any 1-foot length of bar.

Rejected epoxy-coated reinforcing steel may not be substituted for uncoated reinforcing steel or used as bar supports.

Repair galvanized steel bars in accordance with ASTM A780 Annex A1 or Annex A3.

At all times, protect mechanical splice assemblies, headed bar assemblies, and connecting elements (including reinforcing bar ends) against physical damage and corrosion. Keep assemblies and connecting elements clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials that adversely affect fabrication or performance. The Engineer will reject mechanical butt splice assemblies, headed bar assemblies, or reinforcing steel that has sustained physical damage or corrosion at any time. Coating damage includes cracks, abrasions, chips, bond loss (the coating can be removed with a peeling action by the finger), exposed steel areas etc. visible to the naked eye. Repair coating damaged due to shipment, storage, and handling prior to placing the reinforcing steel.

503-3.03 FABRICATION. Fabricate reinforcing steel to the size and dimension shown in the Contract documents. Reinforcing steel dimensions shown are out-to-out of bar, unless otherwise noted.

Meet fabrication tolerances in ACI Publication 117, Section 2.1.

Weld reinforcing bars in accordance with AWS D1.4.

1.	Bends. Bend bars when the bar temperature is above 45°F and less than 150°F. Produce hooks and bends in reinforcing bars with inside diameters as shown in Table 503-1, unless otherwise noted. The Engineer may reject reinforcing steel bent at any time with an inside diameter less than the minimum diameter shown in Table 503-1.

TABLE 503-1

BEND DIAMETER

| BAR SIZE | Stirrups and ties | ALL OTHER BENDS |
| --- | --- | --- |
| No. 3 | 1½" | 2¼" |
| No. 4 | 2" | 3" |
| No. 5 | 2½" | 3¾" |
| No. 6 | 4½" | 4½" |
| No. 7 | 5¼" | 5¼" |
| No. 8 | 6" | 6" |
| No. 9 | - | 9½" |
| No. 10 | - | 10¾" |
| No. 11 | - | 12" |
| No. 14 | - | 18¼" |
| No. 18 | - | 24" |

For the purposes of these Specifications, the term "Standard Hook" means one of the following:

a.	Std 180° Hook: 180° bend plus a 4.0 nominal bar diameter extension, but not less than 2.5 inches, at the free end of the bar.

b.	Std 90° Hook: 90° bend plus a 12.0 nominal bar diameter extension at the free end of the bar.

Do not re-bend or straighten bars without approval by the Engineer.

2.	Bar Repairs. Implement all preventative measures necessary to prevent improperly bent bars including bars bent at locations not required by the Contract or with an inside diameter less than minimum diameter shown in Table 503-1. The Engineer will evaluate improperly bent bars at any time during execution of the Contract for structural adequacy and durability. Do not repair improperly bent bars until the bars are inspected by the Engineer. Bars repaired prior to inspection by the Engineer will be rejected. If, in the opinion of the Engineer, the bend is of such extent or character as to affect the strength or durability of the bar, the Engineer will reject the material. Otherwise, re-bend or straighten bars according to the requirements of this Section and in a manner that will not damage the material, coating, or concrete.

If the Engineer approves repairing the bar, preheat the reinforcing steel before bending. Apply heat by any method that does not damage the reinforcing steel or concrete. Preheat the reinforcing steel at least 5.0 nominal bar diameters in each direction from the center of the bend but do not extend preheating below the surface of the concrete. Insulate all concrete within 6 inches of the heated bar area. Do not allow the temperature of the reinforcing bar at the concrete interface to exceed 500°F. Preheat the reinforcing steel to at least 1100°F. Ensure, by using temperature-indicating crayons, contact pyrometer or other acceptable means, that the maximum reinforcing steel temperature never exceeds 1200°F. Use 2 heat tips simultaneously at opposite sides of bars larger than No. 6 to assure a uniform temperature throughout the thickness of the bar. For size No. 6 and smaller bars, use 2 heat tips, if necessary. Maintain the preheat temperature of the reinforcing steel until bending or straightening is complete. Make the bend gradually with smooth continuous application of force. Use a bending tool equipped with a bending diameter as listed in Table 503-1, unless otherwise noted.  When straightening, move a bender progressively around the bend. When bending or straightening is complete, gradually reduce the temperature of the reinforcing steel to the ambient air temperature. Do not artificially cool the bars with water, forced air, or any other means.

503-3.04 PLACING AND FASTENING. Place and secure reinforcing steel in position as noted in the Contract documents so that the reinforcing steel will be held firmly in place during placing and setting of the concrete. Do not place bars in addition to that noted in the Contract documents without prior approval of the Engineer. Do not place bars of different size, material, or grade than noted in the Contract documents without prior approval of the Engineer. Place all reinforcing steel evenly unless noted otherwise. Provide 2 inches of concrete clear cover, measured from the surface of the reinforcement to the outside surface of the concrete, unless noted otherwise.

Do not place bars on layers of fresh concrete or adjust bars while placing concrete.

Repair detectable coating damage on epoxy-coated reinforcing steel in accordance with Subsection 503-3.02.

1.	Fastening Requirements. In order to position the reinforcing steel as required in the Contract documents and ensure the steel does not move as the concrete is placed, tie the bars with No. 14 or No.16 gauge steel wire. When the spacing between bars is 1 foot or more, tie the bars at all intersections. When the bar spacing is less than 1 foot, tie every other intersection. If the Plans require bundled bars, tie bundled bars together at not more than 6-foot centers. Tie all intersections of epoxy-coated reinforcing steel in the top mat of concrete decks and approach slabs. Use wire coated with plastic, epoxy, or similar non-conductive material when tying epoxy-coated reinforcing steel. Use galvanized wire when tying galvanized reinforcing steel. Obtain the Engineer’s written authorization before welding reinforcing steel. Provide at least 1 inch clear cover to the tie wire by turning all tie wire away from concrete surfaces.

For slip-formed concrete, tie reinforcing steel at all intersections. Provide additional reinforcing steel cross bracing to keep the cage form moving during concrete placement. Place cross bracing both longitudinally and transversely.

2.	Bar Supports. Maintain distances from the forms using approved precast mortar blocks, metal supports, or plastic supports strong enough to resist permanent movement under construction loads. If supports extend to exposed concrete surfaces, use metal or plastic supports. To support and fasten epoxy-coated reinforcing steel, use plastic supports or metal supports coated with plastic, epoxy, or similar non-conductive material. To support and fasten galvanized reinforcing steel, use plastic supports or galvanized metal supports. Do not use wooden or aluminum supports.

Place supports at frequent intervals so as to maintain the cover between the reinforcing and the surface of the concrete. Space supports under concrete deck reinforcement and approach slab reinforcement not more than 4 feet apart in each direction.

a.	Precast Mortar Blocks. Provide mortar blocks meeting the following:

(1)	Compressive strength equal to that of the concrete in which the mortar blocks are embedded.

(2)	Bearing area less than 2 inches in each dimension.

(3)	Have either a grooved top that will hold the reinforcing bar in place or a protruding embedded wire that is tied to the reinforcement.

Mortar blocks may be accepted on a Manufacturer's Certificate of Compliance that includes test results on sets of two 2-inch square specimens per AASHTO T 106. Each pair of specimens represents no more than 2,500 mortar blocks made of the same mortar as the blocks and cured under the same conditions.

b.	Metal Supports. Provide metal supports meeting at least one of the following:

(1)	Galvanized after fabrication in accordance with AASHTO M 232 Class D,

(2)	Stainless steel meeting the requirements of ASTM A 493, Type 302, or

(3)	Plastic coated using coatings that do not react chemically with the concrete, have a minimum thickness of 3/32 inch where the support touches the form, do not crack at or above -5°F, and do not deform enough to expose the metal at or below 200°F.

c.	Plastic Supports. Provide plastic supports meeting the following:

(1)	Non-porous.

(2)	Chemically inert in concrete.

(3)	Have rounded seats.

(4)	Do not deform under load during normal temperatures.

(5)	Do not shatter or crack under impact loading in cold weather.

(6)	Have at least 25 percent of their gross area perforated.

Do not use plastic supports that prevent complete concrete consolidation in and around the support or require supports less than 1 foot apart along the length of the bar.

503-3.05 SPLICING. Splice reinforcing steel bars at locations shown on the Plans or otherwise designated in the Contract documents. Obtain the written approval of the Engineer before splicing bars at other locations. The Engineer will evaluate splices at locations not designated in the Contract documents for structural adequacy.

Splice reinforcing steel bars using lap splicing, electric resistance butt welded, welded lap splicing, mechanical butt splicing, or mechanical lap splicing, unless noted otherwise in the Contract documents. Do not splice reinforcing steel bars in locations identified in the Contract documents where splices in the reinforcing steel are not allowed.

Splices will not be permitted in bars 40 feet or less in plan length. For bars exceeding 40 feet in plan length, ensure the distance center-to-center of splices is not less than 40 feet, with no individual bar length less than 10 feet. Stagger splices in adjacent reinforcing bars, unless otherwise noted in the Contract documents. Stagger lap splices a distance greater than the lapped splice length. Stagger butt splices at least 2 feet.

Do not use lap splicing for No. 14 or No. 18 reinforcing bars.

Do not lap splice spiral reinforcing steel. Anchor each end unit of spiral reinforcing bar by lapping the free end of the bar to the continuous spiral and using either a welded lap splice or a mechanical lap splice.

Reinforcing steel may be continuous at locations where splices are noted in the Contract documents. Locate splices based upon available commercial lengths where practicable except where noted otherwise in the Contract documents.

Do not field weld epoxy coated reinforcing bars.

1.	Lap Splicing.

a.	General. Place reinforcing steel bars in contact and securely tie the bars together. Provide a minimum clear distance of 2 inches between the spliced bars and the nearest adjacent bar. Do not reduce the minimum clearance to the surface of the concrete specified in Subsection 503-3.04.

Use lapped splices meeting the minimum lengths as shown in Table 503-2, unless otherwise noted in the Contract documents:

TABLE 503-2

LAPPED SPLICE LENGTH

| BAR SIZE | UnCOATED | COATED |
| --- | --- | --- |
| No. 3 | 1' - 4" | 1'- 11" |
| No. 4 | 1' - 9" | 2' - 7" |
| No. 5 | 2' - 2" | 3' - 3" |
| No. 6 | 2' - 7" | 3' - 10" |
| No. 7 | 3' - 5" | 5' - 2" |
| No. 8 | 4' - 6" | 6' - 9" |
| No. 9 | 5' - 9" | 8' - 7" |
| No. 10 | 7' - 3" | 10' - 10" |
| No. 11 | 8' - 11" | 13' - 4" |

b.	Qualifications and Submittals. No qualifications apply when lap splicing.

c.	Testing/Inspection. Field verify lap splice length.

2.	Electric Resistance Butt Welded Joints.

a.	General.

Produce electric resistance butt welds by a fabricator listed on the Caltrans Pre-Qualified Products List.

Furnish all Certificate of Compliance documents to the Engineer.

Correct deficiencies in materials and workmanship without additional compensation.

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract documents to the reinforcing steel, unless shown on the working drawings and approved by the Engineer.

b.	Qualifications and Submittals. At least 30 days prior to welding, submit for approval the fabricator’s signed Evaluation Letter on Caltrans letterhead and the following:

- Welding procedure (WPS) and pertinent welding information and calibration

- Equipment operators’ name and qualifications

- Equipment name and serial number

- Description of identification and tracking system

- Quality control inspector’s name and qualifications

- Quality control manual and procedures

(7)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications

(8)	Nondestructive testing personnel qualifications

(9)	Sample QC and Test Reports

c.	Testing/Inspection.

Perform job control tests using a testing laboratory with experience with ASTM A 370 and California Test 670. A job control test consists of the fabrication, under the same conditions used to produce the splice, and the physical testing of 4 sample splices for each lot of splices. An authorized Department representative will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced resistance welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

The Engineer or the Engineer's authorized representative shall witness the job control tests performed by the testing laboratory.

Identify sample splices with tamper proof and weatherproof markings prior to shipment to the testing laboratory.

The sample shall consist of a resistance welded butt splice bar and a control bar that are identified and marked as a set. The same reinforcing bar (hoop) may be used to provide the test weld and control bar.

Test each sample to failure in accordance with ASTM A 370 including Appendix A9, Methods for Testing Steel Reinforcing Bars, and Caltrans Test 670. Determine the ultimate tensile strength for all control bars by testing the bars to failure.

The production lot will be rejected if:

- a sample fails within one bar diameter of the splice at less than 95% of the ultimate tensile strength of the associated control bar

- necking of the bar prior to rupture, as defined in California Test 670, is not observed

- less than three sample splices achieve a minimum tensile strength of 80,000 psi

- all four samples reach 60,000 psi prior to yielding

3.	Welded Lap Splicing.

a.	General. Use direct lap joint welds conforming to the requirements in AWS D1.4 except as noted below.

Use the joint details and dimensions as shown in Figure 3.4 (A), "Direct Lap Joint with Bars in Contact" of AWS D1.4.

Use electrodes classified as "Nickel-Steel" as referenced in AWS A5.5, A5.28, or A5.29.

Preheat reinforcing bars in accordance with AWS D1.4 for a distance of not less than 6 inches on each side of the joint prior to welding. Protect welding areas from air currents, drafts and precipitation to prevent loss of heat or loss of arc shielding. Submit the method of protection of the welding area to the Engineer for approval.

Submit all AWS required test assemblies to the Engineer.

b.	Qualifications. The operator and procedure qualification tests may be performed simultaneously.

Submit a welding plan to the Engineer for approval containing at least the following items:

(1)	Quality Control personnel qualifications including CWI number.

(2)	Welding Procedure Specifications (WPS).

(3)	Procedure Qualification Records (PQR), if applicable.

(4)	Welder Performance Qualification Records (WPQR).

(5)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications.

c.	Testing/Inspection. Perform inspection in accordance with AWS D1.4. Submit the inspection results to the Engineer for review and approval.

4.	Mechanical Butt Splices.

a.	General. Use one of the following types of mechanical butt splices:

(1)	Sleeve-Threaded Mechanical Butt Splices. The sleeve-threaded type of mechanical butt splices consists of a steel splice sleeve with tapered interior threads that joins the reinforcing bars with matching tapered threads. Taper the threads to such a degree that cross threading will not occur during assembly.

Mark each splice sleeve with the heat treatment lot number.

After completion of the assembly, tighten the splice to a torque value recommended by the manufacturer for bars smaller than a No. 8 reinforcing bar and to a torque value of not less than 2400 in-lbs for bars equal to or greater than a No. 8 reinforcing bar.

(2)	Sleeve-Swaged Mechanical Butt Splices. The sleeve-swaged type of mechanical butt splices consists of a seamless steel sleeve applied over the ends of the reinforcing bars and swaged to the bars by means of a hydraulic press.

(3)	Sleeve-Lockshear Bolt Mechanical Butt Splices. The sleeve-lockshear bolt type of mechanical butt splices consists of a seamless steel sleeve, serrated steel strips welded to the inside of the sleeve, center hole with centering pin, and bolts that are tightened until the bolt heads shear off, and the bolt ends are embedded in the reinforcing bars.

(4)	Two-Part Sleeve-Friction Bar Mechanical Butt Splices. The two-part sleeve-friction bar type of mechanical butt splices consists of a shop machined two-part threaded steel sleeve whose ends are friction welded, in the shop, to the reinforcing bars ends.

Engineer's approval of a mechanical butt splice will be based upon manufacturer's technical data, test results, and other necessary proof of satisfactory performance. Resubmit a design for approval if there is any change in the details or materials previously submitted.

Provide a splicing system that when used in accordance with the manufacturer's procedures, except as modified in this section, will develop not less than a minimum tensile strength of 80,000 psi, based on the nominal bar area, and does not exceed a total slip of the reinforcing bars within the splice sleeve, after loading in tension to 29000 psi and relaxing to 2900 psi, of 10 mils for bars smaller than a No. 18 reinforcing bar or 30 mils for No. 18 reinforcing bar. Measure the slip between gage points clear of the splice sleeve.

Conform to the manufacturer's recommendations when splicing, except as modified in this section. Make splices using the manufacturer's standard equipment, jigs, clamps and other required accessories.

Cut square the ends of reinforcing bars to be spliced.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcement if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices or an approved equal.

Submit the following information for each shipment of splice material for review and approval by the Engineer:

(1)	The type or series identification of the splice material.

(2)	The heat treatment lot number for sleeve-threaded type sleeves.

(3)	The bar grade and size number to be spliced by the material.

(4)	A copy of the manufacturer's catalog giving complete data on the splice material and procedure.

(5)	Test results that the splicing system and materials used in accordance with the manufacturer's procedures complies with the minimum tensile strength requirements, the total slip requirements, and other requirements in these specifications.

(6)	A statement that the splice material conforms in all respects to the details and materials of a specific approved design.

b.	Qualifications. Qualify procedures and operators to be used in making splices in reinforcing bars by performing tests on sample splices of the type to be used, before making splices to be used in the work.

Each operator qualification test for mechanical splices consists of 2 sample splices. Each mechanical splice procedure test consists of 2 sample splices.

For sleeve-threaded, sleeve-lockshear bolt and two-part sleeve friction bar mechanical butt splices, make sample splices on the largest reinforcing bar size to be spliced by the procedure or operator being tested, except that No. 14 bars may be substituted for No. 18 bars.

For sleeve-swaged mechanical butt splices, make sample splices on the largest reinforcing bar size of each deformation pattern to be spliced by the procedure or operator being tested.

Each operator qualified for mechanical splicing of reinforcing bars of a given size and mechanical splice type is also considered qualified for all reinforcing bar sizes smaller than those used in making the operator qualification test for that type of mechanical splice.

Perform a separate operator qualification test or procedure test for each mechanical splicing position and procedure that the operator is expected to use on the work.

Mechanical splice procedures and operators may be approved by the Engineer based upon approval of previous tests performed on appropriate sample splices.

Make sample splices at least 3 feet long with the splice at mid-length. Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative. Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

c.	Testing/Inspection. When mechanical butt splices are used, perform job control tests using a qualified testing laboratory. A job control test consists of the fabrication, under conditions used to produce the splice, and the physical testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt splices is defined as no more than 150 of the same type of mechanical butt splices used for each combination of bar size and bar deformation pattern that is used in the work.

A sample splice consists of a splice made to connect two 30-inch, or longer, bars using the same splice materials, position, location and equipment, and following the same procedures as are being used to make splices in the work. Shorter sample splice bars may be used if approved by the Engineer.

Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

For sleeve-threaded mechanical butt splices, fabricate the reinforcing bars to be used for job control tests on a random basis during the cutting of threads on the reinforcing bars of each lot and ship to the job site with the material they represent.

Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

Should the average of the test results for the 6 sample splices or should more than 1 sample splice in any job control test fail to meet the requirements, all splices in the lot represented by that test will be rejected. Replace rejected bar splices at no additional cost to the Department and no adjustment in contract time.

5.	Mechanical Lap Splices.

a.	General. Engineer's approval of a mechanical lap splice will be based upon manufacturer's technical data, test results, and other necessary proof of satisfactory performance. Resubmit a design for approval if there is any change in the details or materials previously submitted.

Provide a splicing system that when used in accordance with the manufacturer's procedures, except as modified in this section, will develop not less than a minimum tensile strength of 75,000 psi, based on the nominal bar area.

Conform to the manufacturer's recommendations when splicing, except as modified in this section. Make splices using the manufacturer's standard equipment, jigs, clamps and other required accessories.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcement if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices or an approved equal.

Submit the following information for each shipment of splice material for review and approval by the Engineer:

(1)	The type or series identification of the splice material.

(2)	The heat treatment lot number for sleeve-threaded type sleeves.

(3)	The bar grade and size number to be spliced by the material.

(4)	A copy of the manufacturer's catalog giving complete data on the splice material and procedure.

(5)	Test results that the splicing system and materials used in accordance with the manufacturer's procedures complies with the minimum tensile strength requirements and other requirements in these specifications.

(6)	A statement that the splice material conforms in all respects to the details and materials of a specific approved design.

b.	Qualifications. Qualify procedures and operators to be used in making splices in reinforcing bars by performing tests on sample splices of the type to be used, before making splices to be used in the work.

Each operator qualification test for mechanical splices consists of 2 sample splices. Each mechanical splice procedure test consists of 2 sample splices.

Each operator qualified for mechanical splicing of reinforcing bars of a given size and mechanical splice type is also considered qualified for all reinforcing bar sizes smaller than those used in making the operator qualification test for that type of mechanical splice.

Perform a separate operator qualification test or procedure test for each mechanical splicing position and procedure that the operator is expected to use on the work.

Mechanical splice procedures and operators may be approved by the Engineer based upon approval of previous tests performed on appropriate sample splices.

Make sample splices at least 3 feet long with the splice at mid-length. Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative. Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

c.	Testing/Inspection. When mechanical splices are used, perform job control tests using a qualified testing laboratory. A job control test consists of the fabrication, under conditions used to produce the splice, and the physical testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical lap splices is defined as no more than 150 of the same type of mechanical butt splices used for each combination of bar size and bar deformation pattern that is used in the work.

A sample splice consists of a splice made to connect two 30-inch, or longer, bars using the same splice materials, position, location and equipment, and following the same procedures as are being used to make splices in the work. Shorter sample splice bars may be used if approved by the Engineer.

Make and test the sample splices in the presence of the Engineer or the Engineer's authorized representative.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample to failure in accordance with ASTM A 370 and Appendix A9, Methods for Testing Steel Reinforcing Bars, of ASTM A 370. Failure is defined as partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection. Submit the test results to the Engineer for review and approval.

Should the average of the test results for the 6 sample splices or should more than 1 sample splice in any job control test fail to meet the requirements, all splices in the lot represented by that test will be rejected. Replace rejected bar splices at no additional cost to the Department and no adjustment in contract time.

503-3.06 HEADED BAR REINFORCEMENT. Headed bar reinforcement consists of deformed steel reinforcing bars in cut lengths with a head attached to one or both ends. Attachment can be accomplished through welding or forging of heads onto the bar ends, by internal threads in the head mating to threads on the bar end or by a separate threaded nut to secure the head to the bar. Heads are forge formed, machined from bar stock, or cut from plate.

For epoxy-coated or zinc-coated reinforcing steel, coat headed bar reinforcement after fabrication. Prior to coating, remove sharp edges and burrs by rounding the edge of the bar head, and remove weld flash from the bar heads that would prevent proper coating of the headed bar. Do not use thread type headed bar reinforcement with epoxy-coated reinforcing steel.

Perform inspection and test prior to, during, and after manufacturing headed bar reinforcement and as necessary to ensure that the material and workmanship conform to the requirements of the Contract.

When headed bar reinforcement is used, perform production control tests using a qualified testing laboratory. A production control test consists of the fabrication, under conditions used to produce the head, and the physical testing of 3 sample heads for each lot of heads.

A production lot of headed bar reinforcement is defined as no more than 150 splices of the same bar size, with heads of the same size and type, and manufactured by the same method, produced from bar material of a single heat number and head material of a single heat number. If 1 reinforcing bar has a head on both ends, it will be counted as 2 reinforcing bars for the purposes of establishing and testing production lots. Start a new production lot if the heat number of either the bar material of the head material changes before the maximum production lot size is reached.

Test each sample to failure in accordance with ASTM A 370. Failure is defined as partial or total fracture of the parent bar material or the head, or head-to-bar connection. Submit the test results to the Engineer for review and approval.

Should the results of one test made on any of the 3 samples fail to meet ASTM A370, perform 1 retest on 1 additional sample from the same production lot. If the additional test specimen or if more than 1 of the original test specimens fail to meet ASTM A370, all headed reinforcement bars in the production lot represented by that test will be rejected. Replace rejected bars at no additional cost to the Department and no adjustment in contract time.

503-3.07 PLACEMENT TOLERANCES. When placing reinforcing steel, do not reduce the total number of bars specified. Place reinforcing steel within the following tolerances:

1.	Clear Cover: +1/4 inch, -3/8 inch. Do not reduce the clear cover to less than 1 inch.

2.	Placement of Reinforcement: +1/2 inch.

3.	Spacing of Reinforcement: ± One-quarter of the specified spacing, but not to exceed 1 inch.

4.	Spacing for Bundled Reinforcement: Provide at least 1 inch or 2 times the individual nominal bar diameter between bundles, whichever is greater.

5.	Embedment Length and Length of Lap Splices: -1 inch for No. 3 through No. 11 bars, -2 inches for No. 14 and No. 18 (embedment only).

6.	Location of Bends in Bars and Ends of Bars: ±2 inch.

503-4.01 METHOD OF MEASUREMENT. See Section 109.

503-5.01 BASIS OF PAYMENT. Reinforcing steel will be paid for at the Contract lump sum price. The lump sum price is full compensation for furnishing, fabricating, placing, splicing, heading and testing reinforcing steel as indicated in the Contract documents. Increase in weight of reinforcing due to splices, heads, coatings and additional support bars will not be paid for. All materials, equipment and labor required to install reinforcement will be paid for under the Contract lump sum price.

Payment for reinforcing steel used in precast or precast prestressed concrete structural members is included in the Contract price for the precast members, as provided for Section 501.

Payment for reinforcing steel used in minor structures is subsidiary to the structure.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

503(1)	Reinforcing Steel	Lump Sum

503(2)	Epoxy-Coated Reinforcing Steel	Lump Sum

DOT BRIDGE-012012

Special Provisions

Replace Section 504 with the following:

SECTION 504

STEEL STRUCTURES

504-1.01 DESCRIPTION. Construct steel structures and the structural metal portions of composite structures according to the Plans.

Furnish, fabricate, erect, and coat structural metals shown on the Plans, including structural steel of all grades, bolts and fasteners, stud shear connectors, welding, special and alloy steels, metallic electrodes, steel forgings and castings, and iron castings. Furnish, fabricate, and install incidental metal construction and elastomeric material not otherwise provided for, according to the Contract.

504-2.01 MATERIALS. Use materials that conform to the following:

Paint	Subsection 708-2.01

Structural Steel	Section 716

Arc Welding Electrodes	Section 716

Fasteners	Section 716

Steel Grid Floors	Section 716

Steel Pipe	Section 716

Galvanizing	Section 716

Steel Forgings	Section 718

Steel Pins & Rollers	Section 718

Castings	Section 719

Expansion Joints and Bearings	Section 516

With written approval, substitute a grade of steel, for that specified, for a particular application where it is desired. Substituted steel must be equal or superior in both physical and chemical properties.

CONSTRUCTION REQUIREMENTS

504-3.01 FABRICATION.

1.	Shop Inspection. Furnish 30 days notice of when work will begin at the fabrication shop to allow for an inspection.

Furnish 4 signed copies of mill reports covering all steel used on the project.

2.	General. Fabricate steel members, except for rolled shapes, at a plant certified under the American Institute of Steel Construction (AISC) Quality Certification Program as “Major Steel Bridge,” with endorsement “F” for at least the last five consecutive years.

Submit shop drawings in one complete submittal package.  Partial or incomplete submittals will not be reviewed or considered.  Partial or incomplete submittals will be rejected.

Protect structural steel from corrosion, dirt, grease, or other foreign matter. Store structural steel at least 12 inches above the ground.

Ensure that rolled material is straight before being laid off or worked. If straightening is necessary, use methods that will not injure the metal. Do not use material with sharp kinks or bends.

Steel or wrought iron may be flame cut provided a mechanical guide is used to secure a smooth surface. Flame cut by hand only where approved, and smooth the surface by planing, chipping, or grinding. Manipulate the cutting flame to avoid cutting beyond the prescribed lines. Fillet re-entrant cuts to a radius of at least 3/4 inch.

Ensure that finished members are true to line and free from twists, bends, and open joints.

Plane sheared edges of plates more than 5/8 inch thick and carrying calculated stresses to a depth of 1/4 inch deep. Fillet re-entrant cuts before cutting.

Make sure the surface finish of bearing and base plates and other bearing surfaces that will contact each other or concrete meets the surface roughness requirements as defined in ANSI/ASME B-46.1, surface roughness, waviness and lay, Part I:

Steel slabs	ANSI 2,000

Milled ends of compression

members, stiffeners, and fillers	ANSI 500

Slide bearings	ANSI 125

Face and bring to an even bearing abutting joints in compression members and girder flanges, and in tension members where specified on the drawings. Where joints are not faced, keep the opening at 1/4 inch or less.

Build floor beams, stringers, and girders with end construction angles to the exact length shown on the Plans, as measured between the heels of the connection angles. The permissible tolerance is plus 0 inch to minus 1/16 inch. Where continuity is required, face end connections.

Cold bend load-carrying rolled-steel plates as follows:

Take the rolled-steel plates from the stock plates so that the bend line is at right angles to the direction of rolling.

Bend until the radius of the bends, measured to the concave face of the metal, is not less, and preferably more, than shown in the following table, where T is the thickness of the plate.

| Angle Through Which Plate is Bent | Minimum Radius |
| --- | --- |
| 61-90 degrees | 1.0 T |
| 91-120 degrees | 1.5 T |
| 121-150 degrees | 2.0 T |

If a shorter radius is essential, bend the plates when hot, but not shorter than a radius of 1.0 T.

Before bending, round the edges of the plate to a radius of 1/16 inch throughout the portion of the plate to be bent.

Fit up and attach end and intermediate stiffeners as shown on the Plans. Do not weld ends of stiffeners and other attachments to flanges unless shown on the Plans.

Do not incorporate laminated, pitted or other materially deficient steel into the completed structure.

3.	Shop Splices. In addition to those shown on the Plans, girder webs and flanges may contain a maximum of 2 shop splices per plate per span. Indicate all splices on the shop drawings. These splices are subject to approval and are subject to the following limitations:

Make splices complete penetration butt welds. Grind flange splices flush. Grind web splices flush on the outside face of exterior girders only. Grind parallel to the longitudinal axis of the girder.

Do not place a bottom flange splice within the middle third of any span. Use tension flange splices only as shown on the Plans or as approved.

Completely weld each element of a girder, such as flange or web, before attaching it to another element.

Make all splices at least 6 inches from the nearest stiffener plate. Offset web and flange splices at least 6 inches.

4.	Bolt Holes. Unless otherwise noted, either drill or punch bolt holes. Make finished bolt holes 1/16 inch larger than the nominal diameter of the bolt. Ensure holes are clean cut and without burrs or ragged edges. Material with poorly matched holes will be rejected.

When material forming parts of a member is composed of not more than 5 thicknesses of metal, and whenever the thickness of the metal is not greater than 3/4 inch for structural carbon steel or 5/8 inch for alloy steel, either punch or drill the holes to full size.

When there are more than 5 thicknesses or when any of the main material is thicker than 3/4 inch in carbon steel, or 5/8 inch in alloy steel, or when required under paragraph 7 below, subpunch or subdrill the holes 3/16 inch smaller. After assembling, ream them to size or drill them from the solid to full size.

For punched holes, the diameter of the die must not exceed the diameter of the punch by more than 1/16 inch. Ream any holes that must be enlarged to admit bolts.

Ream holes cylindrical and perpendicular to the member. Direct reamers mechanically, where practicable.

Ream and drill using twist drills. Assemble connecting parts requiring reamed or drilled holes and securely hold them while reaming or drilling them. Match mark them before disassembling.

Subpunch (or subdrill if required) holes for field connections and field splices of arch members, continuous beams, towers (each face), bents, plate girders, and rigid frames while assembled in the shop. Obtain approval of the assembly, including camber, alignment, and accuracy of holes and milled joints before beginning reaming.

Subpunch and ream holes for floor beam and stringer field end connections to a steel template, or ream them while assembled. When partial assembly is permitted ream holes for web member connections with steel templates.

When using templates to ream field connections of web members of an arch, bent or tower, mill or scribe at least one end of each web member normal to the long axis of the member. Accurately set the templates at both ends from this milled or scribed end.

Ream or drill the full size of the field connection through templates after carefully locating the templates as to position and angle and firmly bolting them. Use exact duplicate templates used to ream matching members or the opposite faces of one member. Accurately locate templates for connections that duplicate so that like members are duplicates and require no matchmarking.

Accurately punch holes full-size, subpunch them, or subdrill them so that after assembling (before reaming), a cylindrical pin 1/8 inch smaller in diameter than the nominal size of the punched hole may be entered perpendicular to the face of the member, without drifting, in at least 75% of the contiguous holes in the same plane. If the requirement is not fulfilled, the badly punched pieces will be rejected. If any hole will not pass a pin 3/16 inch smaller in diameter than the nominal size of the punched hole, the material will be rejected.

Ream or drill holes so that 85% of the holes in any contiguous group after being reamed or drilled show no offset greater than 1/32 inch between adjacent thicknesses of metal.

Provide in steel templates hardened steel bushings in holes accurately dimensioned from the center lines of the connection as inscribed on the template. Use the center lines to locate accurately the template from the milled or scribed ends of the members.

5.	Shop Assembling. Shop assemble continuous beams and diaphragms in lengths of not less than 3 or more adjoining girder segments.

Clean metal surfaces in contact before assembling them. Assemble, pin well, and firmly draw together the parts of a member with bolts before beginning reaming. Make milled ends of compression members in full bearing before starting reaming.  Take apart assembled pieces, if necessary, to remove burrs and shavings produced by reaming. Keep the members free of twists, bends, and other deformities.

To prepare to shop bolt material punched full-size, spear-ream the bolt holes, if necessary, to admit the bolts. Make the reamed holes no more than 1/16 inch larger than the nominal diameter of the bolts.

Secure end connection angles, stiffeners, and similar parts using shipping bolts to prevent damage in shipment and handling.

Furnish a camber diagram showing the camber at each panel for each truss. Take the camber from actual measurement while the truss is assembled, or base it on calculated values when full assembly is not required.

Allow holes to drift during assembly only as needed to position the parts, and not enough to enlarge the holes or distort the metal. To enlarge holes to admit the bolts, ream them.

Match mark connecting parts assembled in the shop to allow for reaming holes in field connections. Furnish a diagram showing the marks.

6.	Bolted Connections, High-Strength Bolts. Determine bolt lengths by adding the values given in Table 504-1 to the total thickness of connected material. These values compensate for thickness of nut, bolt point, and washers. Add 5/32 inch to the grip length per each additional flat washer. Adjust the total length to the next longer 1/4 inch increment up to a 5 inch length and to the next longer 1/2 inch increment for lengths over 5 inches.

Fit bolted parts solidly together when assembling them and do not separate them by gaskets or other interposed compressible material. Place hardened washers under the turned element.

TABLE 504-1

BOLT LENGTH DETERMINATION

| Bolt Diameter (inches) | Added Length (inches) |
| --- | --- |
| 1/2 | 11/16 |
| 5/8 | 7/8 |
| 3/4 | 1 |
| 7/8 | 1-1/8 |
| 1 | 1-1/4 |
| 1-1/8 | 1-1/2 |
| 1-1/4 | 1-5/8 |

Keep assembled joint surfaces, including those adjacent to washers, free of scale except tight mill scale. Clean off dirt, loose rust, burrs, and other defects that would prevent the parts from seating. Keep contact surfaces free of oil, paint, or lacquer.

When the outer face of the bolted parts has a slope of more than 1:20, use a smooth beveled washer in contact with the sloped surface.

Tighten fasteners to give at least the required minimum tension values shown in Table 504-2 when the joint is completed. Use bolts and nuts made by the same manufacturer in a connection.

TABLE 504-2

REQUIRED BOLT TENSION

| Bolt Size (inches) | Required Minimum Tension (pounds) |
| --- | --- |
| 3/4 | 28,400 |
| 7/8 | 39,250 |
| 1 | 51,500 |

Use zinc coated load indicating washers. Demonstrate the suitability of the device by testing a representative sample of at least three devices for each diameter and grade of fastener used in the structure. Test with a calibration device capable of indicating bolt tension. Include in the test assembly flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned. Demonstrate with the calibration test that the device indicates a tension at least 5% greater than that required by Table 504-2. Follow manufacturer's installation procedures when installing bolts in the calibration device and in all connections. Be careful to properly install flat, hardened washers when using load indicating devices with bolts installed in oversized or slotted holes and when using the load indicating devices under the turned element. The load indicating device will count as one washer for the purpose of determining bolt length.

Place the load indicating device under the bolt head and turn only the nut when tightening the bolt. The device must indicate full tensioning of the bolt when the opening reaches zero.

Install bolts in all holes of the connection and bring them to a snug tight condition. Then, tighten fasteners, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed. Keep previously tightened fasteners from relaxing. Multiple systematic tightening cycles may be required.

Do not reuse high-strength bolts. Remove previously fully tightened bolts that were loosened by tightening adjacent bolts. Replace them with new bolts, nuts, and load indicating devices.

7.	Welding. Perform all welding and Nondestructive Examination (NDE) as specified or shown on the Plans.  Conform to ANSI/AASHTO/AWS Bridge Welding Code D1.5 when welding new steel bridge girders, beams, and stringers.  Conform to the Structural Welding Code AWS D1.1 when welding all other steel structures.

At least 30 days prior to welding, submit for approval a welding plan stamped and signed by a Certified Welding Inspector (CWI) responsible for the Quality Control (QC) and consisting of the following documents:

- Quality control personnel qualifications including CWI number

- Welding Procedure Specifications (WPS) using forms in AWS D1.1, Sample Welding Forms;

- Procedure Qualification Records (PQR) when applicable, using forms in AWS D1.1, Sample Welding Forms;

- Welder Performance Qualification Records (WPQR) using forms in AWS D1.1, Sample Welding Forms with the documentation of current welder certification;

- Sample daily inspection sheet; and Type and extent of NDE to be conducted, as required in the specifications

Using a CWI, perform all quality control inspection necessary to ensure the materials and workmanship meet the requirements of the contract documents.

Correct all deficiencies in materials and workmanship revealed by Quality Control and Quality Assurance inspections without additional compensation.

Furnish all completed Quality Control inspection documents to the Engineer and to the Quality Assurance representative designated by the State (when designated).

Meet Charpy V-notch impact test requirements as shown on the Plans and according to Sections 715 and 716; except that the impact energy values for filler metals must not be less than that of the base metals to be joined, when tested at the same temperature as the base metal.

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract documents to the permanent structure, unless shown on the working drawings and approved by the Engineer.

504-3.02 ERECTION.

1.	General. Provide the falsework and all tools, machinery, and appliances, including driftpins and fitting-up bolts, needed to perform the work efficiently. Erect the structural steel, remove the temporary construction, and do the work to complete the structure, as required by the Contract Documents. Make temporary field welds to structural steel according to the procedures required by these Specifications. Steel with sharp kinks or bends will be rejected.

2.	Handling and Storing Materials. Store material on skids above the ground. Keep it clean and properly drained. Place girders and beams upright and shore them. Adequately support long members, such as columns and chords, on skids to prevent injury from deflection.

3.	Falsework. Use falsework according to Section 512.

4.	Method and Equipment.  Submit an erection plan for approval.  Submit the erection plan not less than 30 days prior to erecting the structural steel.  Do not erect structural steel without the written approval of the Engineer.

The erection plan must include, but is not limited to the following:

- Drawings indicating geometry, member sizes, material properties, foundations capacities, design assumptions, and other relevant information required to erect the structural steel.

- Support and lifting reactions for each stage of the erection procedure.

- Equipment type, size, capacity, position, work radius and other relevant information.

- Schedule, duration of each portion of work and other timing considerations.

If multiple segments will be connected and supported or lifted as a single member, the following additional information is required:

- Stress sheets for each state of the erection procedure.

- Deflection diagrams including camber effects and adjustments.

- Bolted field splice stress calculations

- Falsework, if required, details and supporting calculations in accordance with Section 512.

The erection plan shall conform to the requirements of the most recent edition of the AASHTO LRFD Bridge Design Specifications and the Contract Documents.  Do not exceed the permissible stresses defined in the most recent edition of the AASHTO LRFD Bridge Design Specifications using a construction load factor of 1.25 for essentially static loads and 1.50 for dynamically applied loads.  The Engineer will make the determination which loads shall be designated as static and dynamic loads.

Do not induce buckling or other instabilities at any time during shipping, handling or erection.

Submit changes needed to accommodate the erection plan for approval.  Do not submit shop drawings until the Engineer has approved the erection plan.

Submit plans and calculations for the erection plan in one complete submittal package.  Partial or incomplete submittals will not be reviewed or considered.  Partial or incomplete submittals will be rejected.  No additional contract time will be permitted due to partial, incomplete, or inadequate submittals.

Do not deviate from the approved erection plan without the written permission of the Engineer.

Maintain responsibility for the safety of the method or equipment and complete the work according to the Contract Documents.

5.	Assembling Steel. Accurately assemble the parts as shown on the Plans and follow match-marks. Handle the material carefully to avoid bending, breaking, or otherwise damaging the parts. Do not hammer if doing so will injure or distort the members. Clean bearing surfaces and surfaces to be in permanent contact before assembling the members.

6.	Attachment of Formwork. When approved, use 1-inch maximum diameter holes in steel girder webs for attaching formwork. Place holes 6 inches minimum clear distance from all horizontal or vertical welds and space them at least 4 feet center to center. Drill or subpunch and ream holes. Place and tighten high strength bolts in holes.

Include in the request enough detail of the formwork for determining the stresses that will be imposed on the girder.

504-3.03 PAINTING.

1.	Preparing Metal Surfaces for Painting. Prepare metal surfaces according to Specification SSPC-SP 10, Near White Blast Cleaning to a profile depth of 1 to 3 mils. Use a profile comparator to ensure minimum profile depth. Do not reuse sand or flint abrasives.

Clean grit or shot of contamination before reusing it. Blow dust and grit from the surface with clean dry air. Remove weld spatter and round sharp edges to a smooth curve. To remove contamination, jet wash or scrub with a stiff brush and clear water or brush blast. Remove light rust with a steel brush or mechanical tool.

2.	Schedule of Paint Coats for Metals. Unless otherwise specified, if structural steel will be exposed to weathering, shop-paint it at least 3 coats: prime coat, intermediate coat, and finish coat.

3.	Painting Metal Surfaces.

a.	Time of Application. Apply 1 or more applications of prime coat. Apply the initial application within 4 hours after blast cleaning. Allow at least 30 minutes of drying time between primer applications. Before painting and after preparing the surface, remove any oil, grease, soil, dust, or foreign matter on the surface. If rusting occurs after the surface is prepared, clean the surface again.

Avoid contaminating cleaned surfaces with salts, acids, alkali, or other corrosive chemicals before applying the prime coat and between applications of the remaining coats of paint. Remove any contamination from the surface.

b.	Storage of Paint and Thinner. Store paint and thinner in a separate building or in a room that is well ventilated and free from excessive heat, sparks, flame, or direct sun rays. Keep paints susceptible to damage from freezing in a heated storage space when necessary.

Leave paint containers unopened until required for use. Use open containers first. Seal left-over, partial containers.

Do not use paint that has begun to polymerize, solidify, gel, or deteriorate.

c.	Mixing and Thinning. Mix paint thoroughly before use and agitate often during application.

Do not transfer paint mixed in the original container until all settled pigment is incorporated into the vehicle. Pouring off part of the vehicle temporarily to simplify mixing, is permitted.

Mix by mechanical methods, except use hand mixing for containers up to 5 gallons.

Do not use an air stream bubbling under the paint surface to mix paint or keep it in suspension. Remove and discard any skin that has formed in the container. Do not use the paint if the skin exceeds 2% of the paint volume.

When mixing paint, break up all lumps, completely disperse settled pigment, and create a uniform composition. If mixing by hand, pour off most of the vehicle into a clean container.

Lift the pigment in the paint from the bottom of the container using a broad, flat paddle. Break up lumps and thoroughly mix the pigment with the vehicle. Return the poured-off vehicle to the paint by simultaneously stirring or pouring repeatedly from one container to another until the composition is uniform. Inspect the bottom of the container for unmixed pigment.

Wet tinting pastes or colors with a small amount of thinner, vehicle, or paint and thoroughly mix them. Add the thinned mixture to the large container of paint and mix until the color is uniform.

If paint does not have a limited pot life, or does not deteriorate on standing, mix it at any time before use. However, if it has settled, remix it immediately before use. Do not keep paint in spray pots, painters' buckets, etc., overnight. Gather it into a container and remix it before use.

When the engineer deems it necessary to obtain satisfactory application, add paint thinner according to the manufacturer's instructions.

d.	Application of Paint. Use the oldest of each kind of paint first. Apply paint by spraying. Use brushes, daubers, or sheepskins when no other method can properly apply paint in difficult access areas. Use dipping, roller coating, or flow coating only when authorized.

Blast clean all areas with mudcracking in the zinc-rich primer and then paint them with primer to the specified thickness.

After applying the prime coat, apply the intermediate and finish coats to exposed surfaces according to the manufacturer's recommendations.

Apply the intermediate coat in 2 applications. Apply the first application as a mist coat. Apply the second application after the mist coat has dried to a set-to-touch condition.

Apply the finish coat in 1 application.

Apply paint within the environmental limitations specified by the coating manufacturer. Do not apply paint when the temperature of the steel surface is less than 40 °F or more than 125 °F.

Do not apply paint in fog or mist, when it is raining or snowing, or when the relative humidity exceeds the manufacturer’s recommendations. Do not apply paint to wet or damp surfaces. Do not apply paint on frosted or ice-coated surfaces.

With approval, apply paint in damp or cold weather, and only under the following conditions. Paint the steel under cover and protect and shelter it, or heat the surrounding air and the steel to a satisfactory temperature. Meet the above temperature and humidity conditions. Keep the steel under cover or protected until it is dry or until weather conditions permit its exposure.

Allow to dry any applied paint exposed to freezing, excess humidity, rain, snow, or condensation. Then, remove damaged areas of paint, prepare the surface again, and repaint it with the same kind as the undamaged areas.

Stripe paint before applying each coat of paint. Spot paint edges, corners, crevices, rivets, bolts, welds, and sharp edges before applying the full coat of paint on the steel. Extend striping for at least 1 inch from the edge. Let this stripe coat dry before applying the full coat, if possible. Otherwise, set-to-touch the stripe coat before applying the full coat. However, do not permit the stripe coat to dry long enough to allow the unprimed steel to rust.

Apply each coat of paint as a continuous film of uniform thickness, free of pores. Repaint any thin spots or areas missed in the application. Allow them to dry before applying the next coat.

Wait until each coat of paint is in the proper state of cure or dryness before applying the next coat.

Ensure a minimum dry film thickness of 3 mils and a maximum dry film thickness of 5 mils for each coat of paint. The dry film thickness of the paint will be measured in place with a calibrated magnetic film thickness gauge. If any coat of paint is thinner than specified, obtain the minimum dry film thickness by applying additional coats of paint.

A Tooke gauge may be used to perform destructive testing of each coat’s dry film thickness. Repair damaged areas.

e.	Brush Application. Brush paint areas inaccessible to a spray gun. Work paint into crevices and corners. Paint surfaces not accessible to brushes using daubers or sheepskins. Brush out runs or sags. Leave a minimum of brush marks in the applied paint.

f.	Spray Application of Paint. To apply paint by spraying, use equipment capable of properly atomizing the paint to be applied. Use equipment with pressure regulators and gauges and use air caps, nozzles, and needles recommended by the equipment manufacturer for the material being sprayed. Keep the equipment in satisfactory condition to permit proper paint application. In closed or recirculating paint spray systems, where gas is used under pressure over the liquid, use an inert gas, such as nitrogen.

Provide adequately sized traps or separators to remove oil and water from the compressed air. Drain them periodically during operations. Ensure that the air from the spray gun impinging against the surface shows no water or oil.

Keep paint ingredients properly mixed in the spray pots or containers while applying the paint. Use either continuous mechanical agitation or frequent intermittent agitation.

Adjust the pressure on the material in the pot and adjust the air pressure at the gun for optimum spraying effectiveness. Adjust the pressure on the material in the pot when changing the elevation of the gun above the pot. Keep the atomizing air pressure at the gun high enough to atomize the paint properly but not so high as to cause the paint to fog or the solvent to evaporate, or to cause loss by overspray.

Keep spray equipment clean to avoid depositing dirt, dried paint, and other foreign materials in the paint film. Remove any solvents left in the equipment before applying paint to the surface.

Apply paint in a uniform layer, overlapping at the edge of the spray pattern. During application, hold the gun perpendicular to the surface and at a distance that will deposit a wet layer of paint on the surface. Release the gun’s trigger at the end of each stroke.

Apply coats free of runs, sags, and dry spray.

g.	Shop Painting. Perform shop painting after fabrication and before the surface is damaged from weather or other exposure.

Do not paint shop contact surfaces. Paint surfaces to be in contact after field erection.

Apply only a mist coat (0.5 to 0.8 mil dry film thickness) of inorganic zinc-rich primer, meeting SSPC Paint Specification No. 30, Weld-Through Inorganic Zinc Primer, Class 5, on the following surfaces:

1.	High strength bolted connection contact surfaces

2.	Top flange steel surfaces

3.	Areas within 2 inches from the edges to be welded

4.	Areas where the full 3 coats of paint will interfere with field assembly

Apply the full paint coats specified to steel surfaces that will contact wood.

Remove anti-weld spatter coatings before painting.

Before abrasive blasting, grind smooth all metal defects, fins, slivers, burrs, weld spatter, and sharp edges from shearing or similar operations, including flame hardened edges from cutting or burning. Grind flame hardened edges to a 1/16 inch minimum radius. Repair defects that become evident after abrasive blasting or prime coat application. Retexture the surface to match the blasted profile.

Copy erection marks and weight marks on areas that have been previously painted with the shop coat.

h.	Field Painting. If steel surfaces have not received the full paint coats, paint them as soon as possible after erection.

Touch up metal that has been shop coated with the same type of paint as the shop coat. Touch up by cleaning and painting field connections, welds, bolts and all damaged or defective paint and rusted areas.

If concreting or other operations damage any paint, clean the surface and repaint it. Remove concrete spatter and drippings before applying paint.

Protect wet paint against damage from dust or other detrimental foreign matter.

i.	Drying of Painted Metal. Allow the paint to dry before recoating or exposing it. Do not add a dryer to paint on the job unless the paint specification calls for one. Do not immerse painted metal until the paint has dried. Protect paint from rain, condensation, contamination, snow, and freezing until dry.

j.	Handling of Painted Steel. Do not handle painted steel until the paint has dried except for turning it for painting or stacking it for drying. Minimize damage to paint films from stacking steel members.

Remove paint that is damaged during handling and touch it up with the same number of coats and kinds of paint previously applied.

Wait until painted steel is dry before loading it for shipment.

Repair damaged galvanized coating per AASHTO M 36, Section 11. Use inorganic zinc rich primer meeting Subsection 708-2.01.

k.	System Durability and Certification. Have the coating manufacturer review the project and the proposed service environment and issue you written recommendations and instructions to properly prepare the surface, apply the coating, and achieve maximum durability on this project.

Certify to the Department that the system was applied according to the manufacturer’s recommendations and instructions. Enclose a copy of the recommendations and instructions with the certificate.

504-3.04 CLEANUP. Upon completion and before final acceptance of the structure, remove falsework and falsework piling down to 2 feet below the finished ground line.

504-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Structural steel measured by weight, will include castings, forgings, alloy steels, steel plates, high-strength bolts and nuts, anchor bolts and nuts, stud shear connectors, shoes, rockers, rollers, pins and nuts, expansion dams, roadway drains and scuppers, weld metal, and structural shapes for expansion joints and pier protection.

The weight of the metal in the completed structure will be computed, based on the following:

1.	Unit Weights, pounds per cubic foot:

Aluminum, cast or rolled	173

Bronze or copper alloy	536

Copper sheet	558

Iron, cast	445

Iron, malleable	470

Lead, sheet	707

Steel, cast or rolled, including alloy,

copper bearing, and stainless	490

Zinc	450

2.	Shapes, Plates, Railing and Flooring. By their nominal weights and dimensions as shown on the contract drawings, deducting for copes, cuts and open holes, exclusive of bolt holes. The weights of plates more than 36 inches wide will include an estimated overrun computed as one-half the “permissible variation in thickness and weight” as tabulated in ASTM A 6.

The weight of railing will be included as structural steel unless the bid schedule contains a pay item for bridge railing under Section 507.

The weight of steel grid flooring will be computed separately.

3.	Castings. From the dimensions shown on the Plans, deducting for open holes. To this weight will be added 5% for fillets and overruns. Scale weights may be used for castings of small complex parts, since it would be difficult to compute their weight accurately.

4.	Welds. From the following for shop and field fillet welds:

Size of weld (inches)	Pounds per linear foot

1/4	0.20

5/16	0.25

3/8	0.35

1/2	0.55

5/8	0.80

3/4	1.10

7/8	1.50

1	2.00

The weight of other welds will be computed on the basis of the theoretical volume from dimensions of the welds, adding 50% to the weight to allow for overrun.

5.	High-Strength Bolts. From the following for bolt heads and nuts for high-strength bolts:

Bolt Diameter (inches)	Pounds per 100 Heads or Nuts

5/8	15

3/4	25

7/8	37

1	50

1-1/8	75

6.	Excluded Items. The weight of the following will not be measured: erection bolts, shop and field paint, galvanizing; boxes, crates, and other containers used for shipping; together with sills, struts, and rods used for supporting members during transportation; and bridge hardware connectors used for joining timber members.

504-5.01 BASIS OF PAYMENT. If no pay item is included in the bid schedule for structural steel, the quantities of metal drains, scuppers, conduits, ducts and structural shapes for expansion joints and pier protection measured as provided above, will be paid for as reinforcing steel under Section 503.

Welding and fabrication inspection are subsidiary.

No additional payment will be made for increases in structural steel quantities due to your erection method.

Structural steel for precast or prestressed concrete bridges is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

504(1)	Structural Steel	Lump Sum

DOT BRIDGE-111612

Special Provisions

Delete Section 505 in its entirety and replace with the following:

SECTION 505

PILING

505-1.01 DESCRIPTION. Furnish and drive piles, and assist in pile testing.

Comply with permit in-water noise limitations.

505-1.02 DEFINITIONS.

CUT-OFF. The cut off end of a pile, or cutting a pile end at the finish elevation.

DRIVECAP. A pile driver component that is used to transmit impact forces from the hammer ram to the pile top. The drivecap includes the anvil or striker plate, hammer cushion (cap block), helmet, and pile cushion, if used. (Also termed the driving head).

DRIVING RESISTANCE. The required axial resistance, in units of force, to be achieved during pile driving; or the axial resistance anticipated to reach minimum pile penetration.

ESTIMATED PILE TIP ELEVATION. The elevation at which the Department expects the driving resistance, or end-bearing condition to be achieved.

FRESH HEADING. Cutting the end of a pile perpendicular to the long axis to remove damage, and to obtain a proper driving or splicing surface.

FOLLOWER. A pile driving aid placed between the helmet and the pile top when the pile head is below the reach of the hammer.

HAMMER CUSHION. A disk of material placed on top of the helmet but below the anvil or striker plate to relieve impact shock and provide protection for the hammer and pile.

HAMMER ENERGY:

MAXIMUM RATED HAMMER ENERGY. The theoretical maximum amount of gross energy that a pile driving hammer can generate.

TRANSFERRED HAMMER ENERGY. The amount of energy transferred to the pile for a given blow accounting for friction energy during the ram down stroke, energy retained in the ram and drivecap during rebound, and other impact losses.

HELMET. A pile driver component that fits closely on top of the pile to ensure the impact force is transmitted uniformly across the top of the pile and concentric with the axis of the pile.

LEADS. Pile driver components used to maintain pile and hammer alignment during driving, and on which the pile hammer may travel. Types of leads include :

FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and to the crane at the bottom with a brace. The pile is held at the top by the helmet and is guided at the bottom by the pile gate.

SEMI-FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and supported by the lead line. The lead can slide axially along the pivoted boom point and may be fitted with an extendable brace at the bottom of the leads.

SWINGING LEADS. Pile driving leads that are suspended from the boom by the cable and are not attached to the crane at the bottom with a brace. (Also known as offshore leads)

MINIMUM PENETRATION. The minimum length of pile below the footing or finished ground elevation to which the pile must be driven.

OBSTRUCTION. An unanticipated object projecting within the path of the pile that causes pile refusal or impedes the pile's advance within required tolerances.

PILE GATE. A device at the base of the leads that is closed around the pile to maintain alignment.

REFUSAL. Refusal occurs when the hammer requires 15 or more blows to move the pile one inch, and the hammer is operating near the maximum allowable compressive driving stress (within 80-90% of the specified pile yield stress).

SUBSTRUCTURE UNIT. A unit of the substructure such as an abutment or pier that transmits loads directly from the superstructure to the ground.

TEST PILE. A pile that has a high-strain dynamic test performed on it.

TEMPLATE. A structure affixed to the ground used to maintain proper pile alignment during driving.

WAVE EQUATION ANALYSIS. A numerical method of analysis for the behavior of driven piles that predicts the pile capacity versus blow count relationship (bearing graph) and pile driving stress. Wave equation analysis is performed using the wave equation analysis program (WEAP) with a version dated 1987 or later.

505-2.01 MATERIALS. Use materials that conform to the following:

Structural Steel Piles		Section 715

Structural Steel Sheet Piles		Section 715

Sand		Subsection 703-2.12

Welding		Subsection 504-3.01

- Metal plates, shapes, bolts, nuts, and other appurtenant fabrication and installation materials shall conform to manufacturer's standards and to the requirements specified in Section 504. Nuts and bolts shall be hot dip galvanized.

- Pile Tip Reinforcing. Use manufactured high-strength pile tips with a profile and teeth specifically designed to engage sloping bedrock without sliding.

- Materials delivered to the site shall be new and undamaged and shall be accompanied by certified test reports. Store and handle piling in the manner recommended by the manufacturer to prevent permanent deflection, distortion or damage to the interlocks; as a minimum, support on level blocks or racks spaced not more than 10 feet apart and not more than 2 feet from the ends.  Storage of piling should also facilitate required inspection activities and prevent damage to coatings and corrosion prior to installation. Provide standard handling holes as required by Contractor.

505-2.02 PILES. Furnish piles sufficient in length to obtain the driving resistance and to extend to the estimated pile tip elevation specified in the Contract documents. Furnish full-length piles where practical. Where splices are required, follow the provisions of Subsection 505-3.04. Furnish additional pile length to provide for fresh heading and to suit the method of installation. Use metal shoes or reinforced tips as required. Store and handle piles in a manner that protects them from damage.

1.	Steel Piles. Furnish structural steel piles shown in the plans.

Spirally welded pipe piles may be furnished for pipe pile diameters of 2’-0” and smaller.

The Engineer will reject steel piles that exceed the camber and sweep permitted by allowable mill tolerance.

- Steel Sheet Piles. Furnish hot-rolled steel sheet pile sections indicated on the plans and shown below, or sections of equivalent thickness and strength. The Engineer will reject steel piles that exceed the camber and sweep permitted by allowable mill tolerance

Sheet piling including special fabricated sections shall be full-length sections. Fabricated sections shall conform to the requirement and the piling manufacturer's recommendations for fabricated sections. Metalwork fabrication for sheet piling shall be as specified and in Section 504.

The interlocks of sheet piling shall be free-sliding, provide a swing angle suitable for the intended installation but not less than 5 degrees when interlocked, and maintain continuous interlocking when installed.

CONSTRUCTION REQUIREMENTS

505-3.01 PILE DRIVING EQUIPMENT.

1.	Pile Driving System. Use impact or vibratory hammers to drive steel piles; use impact hammers to determine resistance during pile driving. Use a vibratory hammer to advance all piles placed in anadromous fish streams or navigable water to the depth practical. If a vibratory hammer is used to drive structural steel piles, use an impact hammer to determine pile resistance by driving the pile an additional penetration of at least 5 feet or refusal. Use pile driver leads that allow the hammer to move freely. Do not use followers to drive piles.

Fit the pile driving hammer with a cast-steel driving head (or similar device) that is recommended in the hammer manufacturer’s guidelines, is compatible with the pile, and aligns concentrically and fits closely with the top of the pile.

If the pile driving hammer is fitted with a hammer cushion, use a cushion that satisfies the recommendation in the hammer manufacturer’s guidelines, is appropriate to prevent damage to the hammer or pile, and ensures uniform driving performance. If not new, ensure the hammer cushion is at least 75 percent of the manufactured thickness. Replace driving hammer cushions with a reduction in cushion thickness exceeding 25 percent of the manufactured thickness. Do not use wood, wire rope, or asbestos hammer cushions.

For piles that will not be exposed in the completed work, use fixed leads, a ground template, or other means to ensure proper placement and alignment of piles.

For piles that will be exposed in the completed work, use fixed leads, a two-tiered template that laterally supports the pile within 5 feet of the finished ground or water elevation and within 5 feet of the cut-off elevation, or other means to ensure proper placement and alignment of piles.

To ensure rigid lateral support to the pile during driving when using fixed leads, hold the leads in position at the top and bottom by using guys, steel braces, or other means of restraint that provide sufficient lateral support to prevent movement of the pile. Do not use semi-fixed leads or swinging leads without other means of providing sufficient lateral support to prevent movement of the pile. Wooden templates are not permitted.

Use only equipment included in the approved pile driving plan. The Engineer will inspect the pile driving equipment for conformance with the approved pile driving plan after it has been mobilized to the site and prior to beginning pile driving operations. Remove and replace pile driving equipment found out of conformance with the approved pile driving plan at no extra cost to the Department and with no adjustment to contract time.

2.	Wave Equation Analysis. Perform a wave equation analysis for all pile driving systems used to drive piling according to the requirements of this subsection and the user’s manual for the program. Verify that the pile driving system proposed does not produce stresses greater than 90-percent of the yield stress. Also verify that the pile driving system does not exceed the refusal criteria at the depth of penetration anticipated for achieving the required driving resistance and minimum penetration. Furthermore, verify that at the driving resistance specified in the Contract, the rate of pile penetration is 120-blows per foot or less.

Unless otherwise specified in the Contract, or directed by the Engineer, use the following default values and the applicable values from Table 505-1 as input to the wave equation analysis program:

Output option (IOUT)	0

Factor of safety applied to (Rult)	1.0

Type of damping	Smith

Residual stress option	No

TABLE 505-1

HAMMER EFFICIENCIES USED IN HAMMER APPROVAL

| Hammer Type | For Analysis of Driving Resistance | For Analysis of Driving Stresses |
| --- | --- | --- |
| Single acting diesel hammers | 0.72 | 0.84 |
| Closed-ended diesel hammers | 0.72 | 0.84 |
| Single acting air/steam hammers | 0.60 | 0.70 |
| Double acting air/steam hammers | 0.45 | 0.53 |
| Hydraulic hammers or other external combustion hammers having ram velocity monitors that may be used to assign an equivalent stroke. | 0.85 | 1.00 |

3.	Pile Driving Plan. No less than 30 days prior to the anticipated start of pile driving, submit for approval the details of each proposed pile driving system. Include in the pile driving plan:

a.	A completed Pile Driving Equipment Data form (Form 25D-098).

b.	Manufacturer’s catalog cuts, specifications, manuals, guidelines, and technical bulletins for all pile driving equipment to be used.

c.	A description of the techniques to be used for ensuring proper placement and alignment of the piles, obtaining the driving resistance, and advancing the piles to the estimated pile tip elevation.

d.	Alternate methods of pile installation in the event obstructions are encountered.

e.	A wave equation analysis for each pile driving system.

f.	Certification that all available geotechnical information provided by the Department has been reviewed and considered in the bid preparation, including but not limited to the reports listed in Special Notice to Bidders.

The Engineer will base approval of the pile driving plan on the wave equation analysis submitted by the Contractor, and the requirements in this Subsection. The Department will verify the wave equation analysis using the computer program “GRLWEAP” and GRLWEAP industry standard hammer input data.

Approval by the Engineer of the pile driving plan will not relieve the Contractor of responsibility for piles damaged during pile driving operations. Do not mobilize pile driving equipment to the site without an approved pile driving plan.

Submit all revisions to the approved pile driving plan to the Engineer for approval. For all pile driving equipment not previously identified in the pile driving plan, include in the submittal all of the information required above for the pile driving plan. Explain to the Engineer, in writing, which portions of the approved pile driving plan will be superseded by the revision and which portions remain unchanged. Allow at least 5 days for the Engineer’s approval of pile driving plan revisions.

505-3.02 PILE TESTING AND PILE DRIVING CRITERIA. The Engineer will use one or more of the following to set criteria to monitor pile driving performance and the resistance of the pile during driving. The Engineer will also perform pile testing to confirm hammer-system efficiency, pile driving stresses and pile integrity. Attend a meeting with the Engineer at least 14 days prior to the beginning of pile driving operations to evaluate and discuss the test pile program. Give the Engineer 7 days advance notice before driving each test pile.

1.	Wave Equation Analysis. The Engineer will provide pile driving criteria based on a wave equation analysis. The wave equation analysis computer program to be used will be the "GRLWEAP" program using the GRLWEAP industry standard hammer input data.

2.	High-Strain Dynamic Testing. The Engineer will perform high-strain dynamic testing at locations determined by the Engineer. The Engineer will perform the high-strain dynamic testing in accordance with ASTM D 4945. Piles tested using high-strain dynamic testing may be incorporated into the work.

The Engineer will test the first pile driven at each substructure unit designated for pile testing. Do not drive any production piles, except the test pile, at the substructure unit until the test pile has been driven to the driving resistance and minimum penetration specified in the Contract documents. The Engineer will require 4 hours at each test pile to set up and install the test equipment. The Engineer will attach testing instruments near the top of the test pile through drilled and threaded holes. The Department will furnish the testing equipment and labor necessary to mount the testing instruments to the pile. Provide a reasonable and safe means of access to the top of the test pile after the pile is placed in the leads. Furnish electrical power (a 115 volt, 55-60 cycle AC outlet, 10 amp minimum) for the Engineer’s use during the installation and operation of the testing instruments.

Drive each test pile to the driving resistance and minimum penetration specified in the Contract documents as indicated by the wave equation analysis. The Engineer will record driving data for the test pile. If an obstruction is encountered during driving of the test pile, testing will stop on that pile and the next pile driven at the substructure unit will be designated as a test pile.

If the test results do not conclude the driving resistance has been obtained, the Engineer may direct suspension of pile driving operations for up to 72 hours and then require restriking the pile with the Engineer present to record driving data. Perform the restrike with a warmed-up hammer with the energy or fuel setting adjusted to the position indicated in the approved pile driving plan. Strike the test pile with 60 consecutive blows or until the pile penetrates an additional 3 inches, whichever comes first. The Engineer may terminate the re-strike after 25 blows if pile penetration is less than 1 inch.

If the results from the high-strain dynamic testing are acceptable to the Engineer, drive the remaining piles at the substructure unit using the criteria set by the Engineer and based on the results of the high-strain dynamic testing. The Engineer will provide new driving criteria within 1 day of the completion of high-strain dynamic testing that confirms the driving resistance of a test pile.

Account for the entire allotted equipment installation time and restrike suspension time required by the Engineer in the progress schedule submitted under Subsection 108-1.03 or Section 646, as applicable. Suspension of pile driving operations at a testing location to allow for testing instrument installation or a re-strike of a test pile is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

505-3.03 DRIVING PILES. Drive all piles to the driving resistance and minimum penetration specified in the Contract documents using the pile driving criteria provided by the Engineer. Use the same pile driving system used to set pile driving criteria to drive all piles. Install piles in groups starting from the center of the group and proceed outward in either direction.

If the pile is driven to the estimated pile tip elevation and does not achieve the driving resistance, continue driving the pile to a penetration established by the written direction of the Engineer.

1.	Driving Through New Embankment. When driving piles through new embankment and the depth of the embankment at the pile location is in excess of 5 feet, drive the pile in a hole made through the embankment. Make the hole diameter 6 inches greater than the pile. After driving the pile, fill the annular space around the pile with sand.

2.	Placement and Alignment. Ensure proper placement and alignment of the piles. The Engineer will reject piles that are bent or otherwise damaged by forcing the pile into the leads or template.

Drive piles within an allowed variation as to direction of pile of not more than 1/4 inch per foot. Limit the rotation of steel piles about their longitudinal axis to 15 degrees from the plan position. In addition, position piles to the following tolerances:

- Abutments. Position the piles at the bottom of an abutment within 3 inches of the position specified in the Contract documents. Do not vary the distance between any two piles more than 3 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches.

- Sheet Pile Foundations. To the extent practical, any excavation required within the area where sheet pilings are to be installed shall be completed prior to placing sheet pilings.

Pilings properly placed and driven shall be interlocked throughout their length with adjacent pilings to form a continuous diaphragm throughout the length or run of piling. Pilings shall be carefully located as shown. Pilings shall be placed plumb with out-of-plumbness not exceeding 1/8 inch per foot of length and true to line. Top of pile at elevation of cut-off shall be within 1 inch horizontally. Temporary wales, templates, or guide structures shall be provided to ensure that the pilings are placed and driven to the correct alignment.

3.	Protection of New Concrete. When driving a pile near concrete placed within 28 days, ensure the distance between the pile being driven and the nearest edge of concrete is not less than the distance determined by the following formula:

Where:	D = Distance in feet

E = Maximum rated hammer energy in foot-pounds

C = Vibration coefficient shown in Table 505-2 based on the number of calendar days after concrete placement

TABLE 505-2

VIBRATION COEFFICIENT

| Concrete Age (days) | Coefficient |
| --- | --- |
| 1 | 0.34 |
| 2 | 0.23 |
| 3 | 0.18 |
| 4 | 0.15 |
| 5 | 0.13 |
| 6 | 0.12 |
| 7-9 | 0.11 |
| 10-13 | 0.10 |
| 14-20 | 0.09 |
| 21-28 | 0.08 |

4.	Obstructions. Use alternate methods to drive through or remove obstructions. Obtain written approval from the Engineer before employing any alternative methods of pile advancement.

After exhausting all practicable means to obtain the minimum penetration, but without success, the Engineer will evaluate the structural adequacy of the bridge at a lesser penetration. This review will be based on the resistance of the pile during driving. If the Engineer finds the structure to be adequate, the pile will be accepted at the lesser pile penetration.

5.	Concrete Filled Pipe Piles. After driving pile, clean out the pile to the bottom of concrete elevation specified in the Contract documents. If there is a delay between cleanout and placing concrete, verify that the soil level in the pile has not rebounded before placing concrete.

505-3.04 SPLICES, EXTENSIONS AND BUILD-UPS. If the length of a steel pile is not sufficient to obtain the estimated pile tip elevation and driving resistance specified in the Contract documents, the pile may be spliced in order to obtain the length required to reach the minimum penetration and driving resistance. Use additions with cross sections identical to the pile cross sections.

Make splices with complete joint penetration welds over the entire cross section. If approved, piles may be spliced using pile cut-offs and short pieces if no piece used is less than 10 feet long.

Meet the welding requirements of Section 504. Align the piles at a splice to meet the dimensional tolerances for the allowable variation in straightness of welded columns in AWS D1.1.

505-3.05 DEFECTIVE PILES. Use a pile driving method which does not damage the pile. Do not manipulate the piles to force them into proper position. Correct damaged or improperly driven piles using a method approved by the Engineer. Drive down all piles pushed up by driving adjacent piles or by any other cause. Approved methods may include: withdraw and replace the pile with a new and, when necessary, longer pile; drive a second pile adjacent to the defective pile; splice or build up the pile; or extend a sufficient portion of the footing to properly imbed the pile.

505-3.06 CUTTING OFF PILES. Cut off the piles at the elevations indicated on the Plans. Ensure that all injured material is removed.

When steel piles are shown embedded in concrete footings or pile caps, cut off piles within -1/2 inch to +3 inches of the plan embedment, but do not interfere with reinforcing steel or other items embedded in concrete. When steel pipe piles are shown cutoff below concrete footings or pile caps, cut off piles within -1/2 inch to +1/2 inch of the plan elevation. In pile bents with steel cap beams, make accurate cut-offs to ensure full bearing between the caps and piles.

505-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Furnish Structural Steel Piles. The sum of the lengths of the structural steel piles in place in the completed structure, measured along the centerline of piles from the tip of pile to the cut-off elevation.

Drive Structural Steel Piles. The number of structural steel piles driven in place in the completed structure conforming to the contract.

Structural Steel Sheet Piles. The accepted projected area of furnished and driven structural steel sheet piles measured from plan tip elevation to top cap elevation as called for on the Plans.

505-5.01 BASIS OF PAYMENT.

Furnish Structural Steel Piles. The contract price includes structural steel pile materials delivered to the site, pile shoes, reinforced tips and casing. Unused pile lengths removed by cut-offs and fresh heading are subsidiary. The payment amount will be calculated using the quantity of pile indicated on the bid schedule, or the quantity of installed piles, whichever is greater.

Drive Structural Steel Piles. The contract price includes all related work required to drive the piles including: pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items incurred during pile driving, fresh heading, splicing, restrike, pile cleanout and cutting off.

All related work required to assist the Engineer in performing High Strain Dynamic Testing is subsidiary.

Structural Steel Sheet Piles. The contract price includes sheet pile materials delivered to the site; pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items such as pile splices, cutoffs, templates, wall cap, wales, appurtenant metal materials, tie back rods and settlement ducts, and deadmen, complete and in-place.

Sheet piles used as temporary shoring for excavation, whether removed or left in place at your option with permission of the Engineer, are subsidiary.

Obstruction Removal. Alternate methods of pile advancement through obstructions performed at the direction of the Engineer will be paid as 505(14) Special Pile Excavation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

505(5)	Furnish Structural Steel Piles (HP14x117)	Linear Foot

505(6)	Drive Structural Steel Piles (HP14x117)	Each

505(9)	Structural Steel Sheet Piles	Square Foot

505(14)	Special Pile Excavation	Contingent Sum

0001(458)/52972-020813

Special Provisions

Delete Section 507 in its entirety and replace with the following:

SECTION 507

BRIDGE RAILING

507-1.01 DESCRIPTION. Construct concrete, timber, or steel bridge railing, pedestrian railing, and safety railing as shown on the Plans. Furnish and install bridge number plates as shown on the Plans.

507-2.01 MATERIALS. Use materials that conform to the following:

Steel Railing	Section 722

Timber Railing	Section 506

Concrete	Section 501

Reinforcing Bars	Section 709

Grout	Section 701

Cable	Use ¼ inch galvanized wire rope with a minimum breaking force of 7,000 pounds.

507-3.01 CONSTRUCTION REQUIREMENTS.

1.	General. Construct railing to the line and grade shown on the Plans. Ensure that the rail does not reflect any unevenness of the bridge structure. Set rail posts plumb. Place railing after all falsework is removed and the span is self-supporting. Do not paint bridge railing.

Furnish and install concrete curbing, associated reinforcing steel, and the approach rail transition bracket for steel bridge railing.

2.	Steel. Erect steel railing in conformance with Section 504, except do not use load indicating washers.  Weld in conformance with Section 504. Complete welding before galvanizing.

3.	Timber. Fabricate and install timber railing in conformance with Section 506.

4.	Concrete. Construct concrete rail to meet applicable requirements of Sections 501 and 503. Base concrete mix design on Class A, except use a minimum 28-day compressive strength of 3000 psi. Apply a rubbed finish to exposed surfaces of concrete.

507-4.01 METHOD OF MEASUREMENT. Section 109.

507-5.01 BASIS OF PAYMENT. The contract price includes all rail elements, rail posts, brackets, spacers, fastenings and anchors required to attach the railing to the structure; concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section or within the limits of the concrete curb for the steel bridge rail section; and bridge number plates.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

507(1)	Steel Bridge Railing	Linear Foot

DOT BRIDGE-012012

Special Provisions

Delete Section 512 in its entirety and replace with the following:

SECTION 512

FORMS AND FALSEWORK

512-1.01 Description. Design, construct, maintain and remove forms and falsework used to temporarily support structural concrete until the structure is self-supporting.

Comply with permit in-water noise limitations.

512-1.02 DEFINITIONS.

FALSEWORK. A temporary structure erected to support the permanent structure, in the process of construction, until the permanent structure becomes self-supporting and capable of supporting other imposed loads.

FORMS. Also known as formwork, are a temporary structure or mold used to retain the plastic concrete in its designated shape while the concrete is hydrating and gaining sufficient strength to maintain its designated shape.

HAUNCH. A deepened portion of a concrete deck defined as the distance between the top of the girder and the bottom of the roadway slab.

512-2.01 MATERIALS. As specified or approved.

design and construction requirements

512-3.01 SUBMITTALS.

1.	Falsework Plan. When complete details for falsework are not shown on the Plans, prepare and submit a falsework plan, prepared and sealed by a Professional Engineer registered in the State of Alaska.  When the structure is not open to traffic and is not over or adjacent to railroads or roadways, a falsework plan is not required for falsework supporting decks.

Include detailed working drawings, material specifications, and supporting calculations to allow for complete review of the falsework plan.  For manufactured or proprietary falsework components, include the manufacturer's information, technical bulletins, design data, and other necessary information used in the calculations.

Include an independent design check to verify that the design satisfies the Contract requirements. Perform the independent design check by a Professional Engineer registered in the State of Alaska that is unaffiliated with the Professional Engineer responsible for the falsework design.

2.	Falsework Inspection Verification. Prior to placing reinforcing steel or other loads, perform a falsework inspection by the Professional Engineer responsible for the falsework design.  Do not place reinforcing steel or other loads until a written verification, signed by the Professional Engineer responsible for the falsework design, stating that the falsework meets all of the design and construction requirements is provided to the Engineer.

3.	Concrete Deck Haunch Dimensions. Prior to placing falsework, submit the girder elevations, required haunch dimensions, and supporting calculations to the Engineer for review.  Ensure the haunch dimensions meet the requirements of Subsection 512-3.05.

512-3.02 FALSEWORK Design. Design falsework according to the AASHTO Guide Design Specifications for Bridge Temporary Works and these specifications. When the structure is supported by falsework and is open to traffic, also design the falsework for highway loads according to the AASHTO Standard Specifications for Highway Bridges.

1.	Falsework Foundations. Where spread footing type foundations are used, determine the bearing capacity of the soil and include the bearing capacity on the plans.

2.	Falsework Over Or Adjacent to Roadways. Provide a minimum vertical clearance of 16 feet through falsework, unless otherwise shown on the Plans. Install advance warning devices and vertical clearance signs at falsework openings according to Section 643. Indicate the minimum vertical clearance as 3 inches less than the minimum measurement.

3.	Falsework Over Or Adjacent to Railroads. Design falsework over or adjacent to railroads according to the American Railway Engineering and Maintenance-of-Way Association Manual for Railway Engineering.

512-3.03 Falsework Construction. Construct falsework to conform to the approved falsework plan. Do not begin falsework construction without an approved falsework plan.  Do not modify or alter the structure to accommodate falsework unless otherwise noted or authorized by the Engineer.

Construct pile type foundations according to this specification and Section 505. Use a vibratory hammer to advance piles placed in anadromous fish streams or navigable water to the maximum depth practical.

When welding falsework, meet the welding requirements of Section 504.

Build camber into the falsework to compensate for falsework deflection and anticipated structure deflection. Camber shown on the Plans or specified by the Engineer is for anticipated structure deflection only.

Do not modify or alter the structure to attach falsework unless otherwise noted or authorized by the Engineer.

512-3.04 Forms. For surfaces that are exposed in the completed work, use plywood forms meeting the requirements of the American Plywood Association (APA) grade High Density Overlaid (HDO) Plyform Class I or other approved material that will produce an equivalent smooth and uniform concrete surface. For other surfaces, use plywood forms meeting the requirements of the American Plywood Association (APA) grade B-B Plyform Class I. Use only form panels in good condition free of defects on surfaces in contact with concrete.

Arrange form panels in symmetrical patterns conforming to the general lines of the structure. Place panels for vertical surfaces with the long dimension horizontal and with horizontal joints level and continuous. For walls with sloping footings that do not abut other walls, placement of panels with the long dimension parallel to the footing is permitted.

Follow the manufacturer’s written recommendations when using form liners.

Increase the thickness of concrete members that receive an architectural finish to maintain the specified minimum cover to reinforcing steel.

Bevel exposed corners and edges with 3/4 inch triangular fillets built into the forms.

Do not modify or alter the structure to attach forms unless otherwise noted or authorized by the Engineer. Form ties, anchors, and other devices may be cast into the concrete for supporting forms or for lifting precast members. Ensure form ties and anchors can be removed without damaging the concrete surface. Do not use driven devices or anchors coated with materials that will stain the concrete for supporting forms. Construct metal ties or anchorages within the forms to permit their removal to a depth of at least 1 inch from the concrete surface without damage to the concrete.

Construct concrete forms mortar-tight. Clean the inside surfaces of forms free of dirt, mortar, and debris. When forms are supported by existing concrete, ensure that the forms fit tightly against the hardened concrete and that no mortar can pass through the joint.

Forms may be omitted when the sides of a footing excavation is in rock. If the excavation is larger than the plan dimensions, any additional concrete placed will be at the Contractor’s expense.

Coat forms to be removed with form release agent prior to use. Use a commercial quality product designed specifically to readily release forms and does not discolor the concrete surfaces.

512-3.05 FORMS AND FALSEWORK FOR CONCRETE DECKS. Use forms and falsework that span between adjacent girders without altering or damaging the supporting girders. Hangers may be cast into the concrete for supporting deck falsework. Do not use driven devices or materials that will stain the concrete to support the falsework. Construct hangers to permit their removal to a depth of at least 1 inch from the concrete surface without damage to the concrete.

Adjust the falsework haunch dimensions to accommodate the actual camber and elevation of the installed girders. Measure the installed girder elevations along the centerline of the girders at locations shown on the Plans after erection but before installing falsework, forms, reinforcing steel, or applying other loads. Determine the required haunch dimensions accounting for the variations in the girder elevations.

For prestressed concrete girders, the girder elevations shown in the Plans are based on estimated girder deflections assuming a time lapse of 40 and 120 days after release of the prestressing strands. The girder elevations shown in the Plans are intended to advise the Contractor as to the expected range of girder deflection at the time of deck forming.

1.	Forms. Do not use permanent forms including metal, wood, or precast concrete for concrete deck construction, unless otherwise noted. Provide concrete deck forms meeting the following requirements:

a.	Maintain the deck thickness despite irregularities in and between the girders.

b.	Accommodate haunch variation along the length and between the girders.

2.	Haunches. Limit haunch dimensions to meet the following requirements:

a.	1/2 inch maximum embedment of the top flange into the deck measured at the edge of the flange.

b.	2-1/2 inch minimum clearance between the top of deck and shear stud or shear stirrup.

c.	2 inch minimum penetration of shear stud or shear stirrup into the deck.

d.	4 inch maximum haunch measured at the centerline of the girder.

512-3.06 Removal of Forms and Falsework. Remove forms and falsework without damaging the concrete member.

Forms may be removed after the concrete has cured for at least 24 hours and has a compressive strength of at least 1400 psi as determined from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure. Protect exposed concrete surfaces from damage. Do not let the concrete surface become dry if the forms are removed during the curing period.

Falsework may be removed after the concrete has a compressive strength, determined from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure, as specified in Table 512-1.  If informational field test cylinders are not available, meet the minimum number of curing days specified in Table 512-1.

Do not release falsework for cast-in-place post-tensioned portions of structures until after the prestressing steel has been tensioned.

Table 512-1

FALSEWORK Release Criteria

| Structural Element | Percent of Specified 28-Day Strength (f ’c), min. | Curing Days, min. |
| --- | --- | --- |
| (a) Concrete decks | 70 | 10 |
| (b) Simple span girders, slab bridges, cross beams, pier caps, struts, and top slabs of concrete box culverts | 80 | 14 |
| (c) Box girders | 90 | 21 |
| (d) Continuous span girders | 90 | 21 |
| (e) Other elements | 80 | 14 |

512-3.07 CLEANUP. Upon completion of the structure and before final acceptance, leave the structure and entire site in a clean and orderly condition. Remove temporary structures, equipment, unused materials, debris, forms, and falsework. Remove falsework piling in their entirety.

512-4.01 METHOD OF MEASUREMENT. Forms and Falsework will not be measured for payment.

512-5.01 BASIS OF PAYMENT. When either Item 512(1) Forms or 512(2) Falsework, does not appear in the bid schedule, the work required for that item is subsidiary.

0001(458)/52972-082812

Special Provisions

Add the following new section:

SECTION 515

DRILLED SHAFTS

515-1.01 DESCRIPTION. Construct drilled shaft foundations where indicated in the Plans. This work includes all labor, materials, equipment, incidentals and services necessary to perform all operations to complete drilled shaft installation.

Comply with permit in-water noise limitations.

515-1.02 Definitions.

Overreaming. The unclassified excavation required to enlarge the drilled shaft diameter to advance the metal casing.

Permanent Casing Method. A shaft drilling method where a steel casing is either placed in a predrilled hole or advanced through the ground by twisting, driving or vibration before being cleaned out. The casing then remains in place as the shaft excavation is filled with concrete and becomes part of the structure.

Wet Construction Method. A shaft drilling method where water or slurry (mineral or polymer) is employed to maintain stability of the shaft perimeter while advancing the excavation to final depth.

515-1.02 QUALITY CONTROL. Provide a Quality Control Inspector to ensure that all materials, techniques and methods are suitable to meet or exceed the minimum requirements of the Contract. Demonstrate that the Quality Control Inspector has performed inspection duties similar to those required by this Contract, all for the installation of drilled shafts of at least four feet in diameter, on at least three projects in the past ten years.

The Quality Control Inspector shall submit daily reports to the Engineer during drilled shaft installation and testing operations verifying the Contractor’s compliance with requirements of the Contract. Include field measurement data, procedural discrepancies, installation problems, names of personnel, equipment usage data, and all other significant information in the daily reports.

515-1.03 Contractor Qualifications. Demonstrate that you or your subcontractor for shaft excavation operations possess experience constructing drilled shafts at least six feet in diameter and lengths similar to those indicated on the Plans in environmental conditions and geotechnical material similar to that described in the Contract documents. Prepare and submit for approval a Contractor Qualifications Submittal no more than one week after the Notice to Proceed. Include in the Submittal:

1.	Contractor Experience. Provide a list of three drilled shaft projects in the previous ten years performed by you or the subcontractor for shaft excavation operations where drilling in remote locations, in flowing water through sand, gravel, and sloping rock similar to those conditions expected at this project location were experienced. Provide the drilled shaft plans, logs of test holes, dates of work, type of work, description of work, and amount of work performed. Provide the name and telephone number of a contact person at the agency or company for which the work was completed.

2.	Personnel Experience. Provide a list of the key personnel involved in the drilled shaft construction. Include in the submittal information on the superintendent and staff that will be directing and performing the actual drilling operations, including a resume of each demonstrating:

- A minimum of five years experience in drilled shaft construction of which two years being in responsible charge or operating equipment proposed for this project.

- The number of years of recent continuous relevant experience in performing similar drilling operations and operating the contractor proposed equipment for this job.

- Detailed recent relevant experience (three project minimum) including project description, date of work, actual work performed by individual, and a reference for each project including telephone number.

- A list of relevant equipment operated including type of equipment and amount and nature of experience.

Only those personnel approved by the Engineer may work on the drilled shaft construction. The Engineer may suspend the drilled shaft work if you substitute unauthorized personnel for authorized personnel prior to or during construction. If work is suspended due to unauthorized substitution of personnel, you shall be fully liable for all additional costs resulting from the suspension of work and no adjustment in contract time will be allowed.

515-1.04 Drilled Shaft INstallation Plan. Construct drilled shafts in accordance with the Contract documents and the approved Drilled Shaft Installation Plan. Submit for approval a Drilled Shaft Installation Plan no less than 45 days prior to the scheduled start of drilling operations. Include in the Plan:

1.	A listing of the type, number and size of all proposed equipment, including cranes, barges, drills, augers, bailing buckets, final cleaning equipment, desanding equipment, slurry pumps, tremies, concrete pumps, casings, grout pumps, etc. Include manufacturer’s recommended capacities for each piece of equipment.

2.	Details and methods required for construction including plans for temporary work structures, prepared and sealed by a Professional Engineer registered in the State of Alaska, cofferdams or shoring, and access roads.

3.	Details of sequence of construction operations and sequence of shaft construction including dates and anticipated duration of work.

4.	Details of shaft excavation methods, including methods to monitor excavation while drilling.

5.	Details of provisions for processing and disposing of excavated materials and rock cuttings in accordance with permit requirements.

6.	Procedure for maintaining correct horizontal and vertical alignment during shaft installation.

7.	Details of permanent and temporary shaft casing. Details of casing tip reinforcement.

8.	Method to advance casing.

9.	Methods and equipment proposed to prevent displacement of casing and/or shafts throughout shaft construction.

10.	Details for obstruction removal.

11.	Casing grouting plan and procedure if required.

12.	Details of proposed methods to clean shaft after initial excavation.

13.	Details of shaft reinforcement, including methods to ensure centering/required cover, reinforcement cage integrity during placement, placement procedures, cage support, tie downs, etc.

14.	Details of concrete placement, including proposed operational procedures for concrete tremie or pump, concrete placement rates, initial concrete placement procedure, method for raising tremie during concrete placement, and overfilling of the shaft concrete. Also provide provisions to ensure proper final shaft cutoff elevation.

15.	Method of forming horizontal construction joints in accordance with Section 501-3.11.

16.	Action plan for correcting defects in the shaft. Defects include but are not limited to the following: tilted casing, partially or completely collapsed casing, partially or completely collapsed reinforcement cage, improper concrete placement, and equipment failure.

17.	Required submittals, including shop drawing, mill certification and concrete mix designs.

18.	Welding plan conforming to the requirements of Section 504.

19.	Details for CSL testing procedure including testing schedule, inspector’s name, inspector’s qualifications, required instrumentation and power sources.

20.	Details of environmental control procedures used to prevent loss of slurry, concrete or other shaft materials into waterways or other protected areas.

21.	Wastewater and concrete disposal procedures.

22.	Other information shown in the Plans, requested by the Engineer or deemed necessary by the Contractor.

23.	Certification that all available geotechnical information provided by the Department has been reviewed and considered in the bid preparation, including but not limited to the reports listed in Special Notice to Bidders.

Partial submittals will not be accepted for approval. Allow 20 working days for the Engineer to review the drilled shaft installation plan, at which time the Engineer may approve the plan or request changes, clarifications or additional information. Make all corrections, clarifications and additions requested by the Engineer and resubmit the plan for review. Allow 15 working days for the Engineer to review this and all future Drilled Shaft Installation Plan resubmittals.

Submit modifications to the approved Drilled Shaft Installation Plan to the Engineer for review. Drilled Shaft Installation Plan approval is subject to satisfactory performance in the field.

Do not begin any drilled shaft work without an approved Drilled Shaft Installation Plan.

515-2.01 MATERIALS. Use materials that conform to the following:

| DS Concrete | Section 501 |
| --- | --- |
| DS Grout | Section 701 |
| Reinforcing Steel | Section 503 |
| Casing | ASTM A 709, GR50T3 |
| Corrugated Steel Pipe | Section 707 |
| CSL Tubes | ASTM A53 |

CONSTRUCTION REQUIREMENTS

515-3.01 General. Perform drilled shaft excavations through all materials encountered to the dimensions and elevations shown in the Plans. Use methods and equipment suitable for the intended purpose and the materials encountered. Provide equipment capable of constructing shafts to a depth equal to the deepest shaft shown in the plans plus three times the shaft diameter.

Construct the drilled shafts at Piers 2 and 3 using the permanent casing method.

Barges and temporary work structures and roads may be required to install the drilled shaft foundation, piers, and bridge superstructure.

515-3.02 POSITION AND ALIGNMENT. Provide a fixed template, adequate to maintain shaft position and alignment during all excavation and concreting operations. Do not use floating templates (e.g. attached to a barge). A fixed template for shafts drilled on land will not be required if you demonstrate satisfactorily to the Engineer that shaft position and alignment can be properly maintained. The Engineer will require a fixed template adequate to maintain shaft position and alignment during all excavation and concreting operations for shafts drilled on land if you fail to demonstrate to the Engineer’s satisfaction that you can properly maintain shaft position and alignment without use of a template.

515-3.03 Shaft EXCAVATION.

1.	Equipment. Use excavation and drilling equipment having adequate capacity, power, torque, and downthrust and excavation and overreaming tools of adequate design, size, and strength to perform the work. If the material encountered cannot be drilled using conventional earth augers and/or underreaming tools, provide special drilling equipment, including but not limited to rock augers, core barrels, rock tools, air tools, and other equipment as necessary to continue the shaft excavation to the size and depth required.

2.	Excavation. All shaft excavation is Unclassified Shaft Excavation. The Engineer will require Drilled Shaft Sidewall Overreaming when necessary. When overreaming, increase the shaft radius a maximum of 1/2 inch or pressure grout the annulus.

If the Engineer determines that the material encountered while drilling the shaft excavation is unsuitable and/or is not the same as anticipated in the design of the drilled shaft, extend the drilled shaft excavations as required by the Engineer.

3.	Inspection. Verify the following under the observation and direction of the Engineer:

a.	Shaft excavation dimensions, alignment and depth. Reference the depth of the shaft during drilling using marks on the Kelly bar or other suitable methods. Measure final shaft depths with a suitable weighted tape or other approved methods after final cleaning.

b.	Casing dimensions and alignment throughout the installation process.

4.	Shaft Excavation Cleanliness. Clean the shaft so that at least 50 percent of the base of each shaft has less than ¾ inch of sediment at the time of concrete placement. Ensure that the maximum depth of sedimentary deposits or other debris does not exceed 1½ inches at any location on the bottom of the excavation. Verify shaft cleanliness using a weighted tape, divers, or other appropriate methods.

5.	Disposal of Drilling Spoils. Provide areas for the disposal of unsuitable materials and excess materials that are removed from shaft excavations, and dispose of them subject to permit requirements and in a manner meeting all requirements pertaining to the approved storm water pollution prevention (SWPP) plan.

515-3.04 CASINGS.

1.	Permanent Shaft Casings. Use casings that are smooth and water tight. Provide a casing that is continuous along the entire length shown on the Plans. Meet the welding requirements of Section 504.

Install permanent casing using methods that do not include an impact hammer.

Oversized casing may be used with the Engineer’s approval. The Department will not provide extra compensation for excess concrete required to fill an oversize casing.

Galvanize permanent casing from the top a distance not less than 30 feet. Galvanize by the hot dip galvanizing process in accordance with AASHTO M 111 or the spray-metalizing process according to Steel Structure Painting Council (SSPC) Coating System Guide No. 23.00 to a thickness of 10 mils. Prepare surfaces before galvanizing in accordance with SSPC-SP 5 White Metal Blast Cleaning.

If the installed casing does not satisfy the requirements of Subsection 515-3.10, submit casing repair procedure to the Engineer for approval.

515-3.05 REINFORCING STEEL PLACEMENT. Conform to the requirements of Section 503, modified by the following:

1. 	Reinforcement Cage Construction and Placement: Tie all intersections of drilled shaft reinforcing steel with cross ties or "figure 8" ties. Use double strand ties or ties with larger tie wire when necessary. The Engineer will give final approval of the cage construction subject to satisfactory performance in the field.

Assemble and place as a single unit the cage of reinforcing steel consisting of; longitudinal bars, ties, spirals, cage stiffener bars, crosshole sonic logging (CSL) tubes and all other components. Place the cage immediately after the Engineer inspects and accepts the shaft excavation and immediately prior to placing concrete. The Engineer will give final approval of the placement subject to satisfactory performance in the field.

If the bottom of the constructed shaft elevation is lower than the bottom of the shaft elevation in the plans, extend a minimum of one half of the longitudinal bars required in the lower portion of the shaft the additional length. Continue the tie bars throughout the extra depth and extend the stiffener bars to the final depth. Splice the longitudinal bar extensions as required.

2. 	Support, Alignment, and Tolerance: Tie and support the reinforcing steel in the shaft so that the reinforcing steel will remain within allowable tolerances as specified in Section 515-3.08.

Use bent reinforcing steel spacers or other approved, non-corrosive spacing devices near the bottom and at intervals not exceeding 15 feet up the shaft to ensure concentric spacing for the entire length of the cage. Do not use plastic wheels, mortar block or wire type spacers. Use a minimum of one spacer for each 30 inches of cage circumference.

Provide concrete or other Engineer-approved spacers at the bottom of the drilled shaft reinforcing cage. Maintain the specified distance between the bottom of the cage and the bottom of the shaft. Use one spacer per longitudinal bar unless directed otherwise by the Engineer. Use spacers sized to prevent vertical movement of the cage. Use spacers constructed of material equal in quality and durability to the shaft concrete. Submit spacer information to the Engineer for approval.

Check the elevation of the top of the steel cage before and after placing the concrete. If the cage is not maintained within the specified tolerances, correct it as approved by the Engineer. Do not construct additional shafts until modifying the reinforcement cage support in a manner satisfactory to the Engineer.

515-3.06 FLUID IN EXCAVATION AT TIME OF CONCRETE PLACEMENT. Prior to placing concrete in any shaft excavation, ensure that contaminated suspensions which could impair the free flow of concrete have not accumulated in the bottom of the shaft. Take samples of the fluid in the shaft from the base of the shaft and at intervals not exceeding 10 feet up the shaft, using an approved sampling tool. Ensure that the density of the fluid in the shaft excavation prior to concreting is less than 75 pounds per cubic foot. If desanding equipment is required, ensure that the sand content does not exceed four percent. Take whatever action is necessary to modify the fluid in the shaft excavation prior to placing the concrete to bring the fluid within the Contract requirements.

515-3.07 CONCRETE PLACEMENT. Conform to the requirements of Section 501 and the following:

At no expense to the Department, furnish the additional drilled shaft concrete (over the theoretical amount required to fill the shaft as shown in the Plans) required to complete filling shafts larger than required by the Plans or authorized by the Engineer.

515-3.08 CONSTRUCTION TOLERANCES. Produce drilled shafts conforming to the following tolerances:

1.	Lateral Placement. Top of drilled shaft location within three inches of the position indicated on the Plans.

2.	Vertical Placement. Top elevation of the drilled shaft concrete within one inch of the top of shaft elevation shown in the plans.

3.	Vertical Alignment. Not to vary by more than ¼ inch horizontally for each foot of depth. Ensure that the cutting edges of excavation equipment are normal to the vertical axis of the equipment within a tolerance of ±3/8 inch per foot of shaft diameter.

4.	Bottom Flatness. The completed shaft excavation shall have a flat bottom as shown on the plans and be level within ±3/8 inch per foot of shaft diameter. Where the shaft tip is shown on the Plans to be in rock, the flat bottom of the shaft excavation shall be fully founded on rock.

5.	Reinforcement Cage, Vertical. Top of the reinforcement cage no more than two inches above and no more than three inches below plan position after concrete placement. Do not exceed a differential vertical displacement (racking) of the reinforcement cage of 5/16 inch per foot of cage diameter.

6	Reinforcement Cage, Lateral. Column and shaft reinforcement cages concentric with the shaft within a tolerance of one inch. Concrete cover within 1½ inches of the plan dimension.

7.	Shaft Casing. Do not exceed a difference between the major and minor outside diameters at any point along the length of the permanent metal casing (out-of-roundness) of one percent of the nominal diameter. The circumference of the permanent metal casing shall not vary more than ⅜ inch from the nominal circumference.

8.	Soundness. Provide a solid concrete shaft without voids or sections of unsound concrete.

515-3.09 INSTRUMENTATION AND DATA COLLECTION.

1.	Production Log. Maintain a construction method and soil log during shaft excavation. Submit copies of the log to the Engineer daily. Resolve all differences in the production logs between the Engineer and the Contractor within 24 hours of submittal to the Engineer. Provide at least the following items in the log:

a.	Description and approximate top and bottom elevation of each soil or rock material encountered

b.	Location of all obstructions and time spent removing the obstruction

c.	Drilling penetration rate, down thrust, rotation speed, and torque

d.	Seepage or groundwater

e.	Remarks and comments

2.	Crosshole Sonic Logging. Where crosshole sonic logging (CSL) inspection tubes are shown on the Plans, perform CSL logging of drilled shaft foundations along their entire length. Provide an independent CSL inspector with at least three years of experience in CSL testing to inspect the drilled shaft and prepare the CSL report.

a.	CSL Tubes. Use watertight CSL tubes comprised of schedule 40 pipes that provide an inside diameter of at least two inches and have a smooth, regular inside surface free of defects and obstructions (including pipe joints) to permit the free movement of a 1¼ inch diameter probe over the entire length of the tube. Provide a watertight cap at the bottom of the CSL tube and a watertight, removable cap at the top of the CSL tube. Fill CSL tubes with potable water prior to or within one hour after placement of shaft concrete.

The exterior surface of CSL tubes must be free from corrosion, oil, and coatings and provide a good bond between the concrete and the tube.

Secure CSL tubes to the inside of the reinforcing steel cage on regular intervals. Place CSL tubes as near parallel and plumb as possible and around the reinforcement cage perimeter. Extend the CSL tube from the bottom of the shaft to at least three feet above the top of the shaft or as directed by the Engineer. Use mechanical couplers to extend CSL tubes. Seal all CSL tube joints. Do not weld CSL tube joints.

Do not damage CSL tubes. Prior to beginning CSL testing, assure that the test probes can pass through every tube to the bottom. If a tube is obstructed, at your expense core a hole that is near to the obstructed tube and extends to its full depth. The corehole should be large enough to accommodate the CSL probe.

Prior to coring, submit to the Engineer for approval a coring plan including corehole locations and coring equipment and procedures. Provide for complete core recovery and minimize abrasion and erosion of the core. Place the core hole at a position in the shaft that will not produce damage to the reinforcing steel in the shaft. Log the corehole and submit the log to the Engineer. Indicate in the log voids and defects located in the core hole. Preserve the cores and make them available for inspection by the Engineer. Commence downhole testing with the corehole treated as an access tube.

b.	CSL Testing. Test the drilled shaft no sooner than three days and no later than 10 days after placement of drilled shaft concrete.

Provide the shaft installation and drilling record to the Engineer and CSL Inspector within three days of placing shaft concrete.

Perform CSL testing between all adjacent tube pairs and across at least two major diagonals. Perform additional diagonal testing if shaft defects are identified. Perform as many additional diagonal tests as needed to determine the extent of the shaft defect.

If the CSL results indicate a potential defect, core the location of the defect as described above for blocked CSL tubes.

If the cores indicate the presence of a defect, repair the shaft in accordance with the approved Drilled Shaft Installation Plan at your expense and at no extra cost to the Department. If a defect is not observed in the cores, the Department will pay for all coring costs and compensation for the delay will be granted by an appropriate time extension.

After CSL testing has been completed and accepted by the Engineer, remove water from the CSL tube, cut the tube flush with the top of the shaft, and fill the tube with DS Grout.

c.	CSL Test Report. Submit the Crosshole Sonic Logging (CSL) results to the Engineer within five days of testing. Provide a Crosshole Sonic Testing Report containing the following:

- The CSL logs for all tested tube pairs. Identify the CSL log for each test tube pair indicating the orientation relative to the structure.

- The traditional signal peak diagram (time versus depth).

- The computed first pulse arrival time verses depth.

- The computed pulse wave speed versus depth.

- The computed relative pulse energy or amplitude versus depth.

- Identification of defect zones, if any, on the CSL logs. Defect zones are defined by an increase in arrival time of more than 20 percent relative to arrival time in a nearby zone of good concrete.

3.	Low Strain Integrity Testing. Where crosshole sonic logging tubes are not shown on the Plans, perform low strain integrity testing of drilled shaft foundations.

If the low strain integrity testing indicates the presence of a defect in a shaft, core a two inch diameter hole the length of the shaft.  If the core confirms the presence of a defect, repair the shaft at your expense and at no extra cost to the Department.  If a defect is not observed in the cores, the Department will pay for all coring costs and compensation for the delay will be granted by an appropriate time extension.

515-3.10 Shaft Defects. Repair all shaft defects identified. Submit repair procedure to the Engineer for review and approval.

515-3.11 TEMPORARY WORK STRUCTURES. Design temporary work structures according to the AASHTO Guide Design Specifications for Bridge Temporary Works and these specifications. Design and construct cofferdams, if required, in accordance with Subsection 205-3.01.3.

When temporary work structures are not shown on the Plans, the plans for temporary work structures that are submitted with the drilled shaft installation plan shall be prepared and sealed by a Professional Engineer registered in the State of Alaska. Include detailed working drawings, material specifications, and supporting calculations to allow for complete review of the temporary work structure plan. For manufactured or proprietary components, include the manufacturer's information, technical bulletins, design data, and other necessary information used in the calculations. Include an independent design check to verify that the design satisfies the Contract requirements. Perform the independent design check by a Professional Engineer registered in the State of Alaska that is unaffiliated with the Professional Engineer responsible for the temporary work structure design.

Design and construct pile foundations to support temporary work structures according to this specification and Section 505. Use a vibratory hammer to advance piles placed in anadromous fish streams or navigable water to the maximum depth practical.

Upon completion of the structure and before final acceptance, leave the structure and entire site in a clean and orderly condition. Remove all temporary work structures, cofferdams, equipment, unused materials and debris in their entirety.

515-4.01 METHOD OF MEASUREMENT.

1.	Drilled Shaft: This item will not be measured for payment.

2.	Unclassified Shaft Excavation: The sum of the lengths of the shaft excavations measured along the centerline of the shaft from the original ground elevation to the tip of the shaft.

3.	Casings: The sum of the lengths of the casing in place in the completed structure. The length will be measured along the casing from the top to the bottom of the casing at each shaft location.

4.	Instrumentation and Data Collection: This item will not be measured for payment.

515-5.01 BASIS OF PAYMENT.

1.	Drilled Shaft. Payment will be full compensation for furnishing, erecting, operating, maintaining, dismantling and transporting all drilled shaft equipment necessary to drill foundation shafts and place the casing as indicated on the plans.

Payment will be full compensation for all Quality Control Inspection.

Payment will be full compensation for the design, fabrication, installation, maintenance and removal of all temporary work structure(s) required to construct the bridge substructure and superstructure.

Payment of 85 percent of the amount bid for this bid item will be made when all equipment is at the site, assembled and ready to begin operation and all temporary work structures are installed and ready for use.

Payment of 10 percent will be made when the all shafts have been drilled, all shaft concrete is in place to the top of the shaft, all Instrumentation and Data Collection is complete, and after all shafts have been accepted by the Engineer.

Payment of the remaining five percent will be made after the temporary work structure(s) has been removed in its (their) entirety.

2.	Unclassified Shaft Excavation. Payment will be for all processes required to excavate a drilled shaft of the dimensions shown in the Contract, completed and accepted. Include in the work all shaft excavation, whether the material encountered is soil, rock, boulders, weathered rock, stone, natural or man-made obstructions, or any other materials.

Payment will be full compensation for the shaft excavation; sidewall overreaming; disposal of excavated materials; preparation of the site as required; cleaning and inspecting shaft excavations; using desanding equipment as necessary; using drilling equipment; and furnishing all other labor and materials necessary to complete the work.

3.	Casings. Payment will be full compensation for all costs necessary for furnishing and placing the casing in the shaft excavation.

Furnishing, placing and protecting isolation casings is subsidiary.

4.	Instrumentation and Data Collection. Payment will be for all labor, equipment, materials, transportation, storage, and insurance required for the instrumentation, data collection and reporting of shaft testing.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

515(1)	Drilled Shaft	Lump Sum

515(2)	Unclassified Excavation (8’-0” Dia.)	Linear Foot

515(3)	Shaft Casing (8’-0” x 1”)	Linear Foot

515(4)	Shaft Instrumentation and Data Collection	Lump Sum

0001(458)/52972-020813

Special Provisions

Add the following new Section:

SECTION 516

EXPANSION JOINTS AND BEARINGS

516-1.01 DESCRIPTION. Furnish and install expansion joints and bearings according to the Plans.

516-2.01 MATERIALS. Use materials that conform to the following:

Bridge Seals	Subsection 705-2.03

Expanded Polyethylene	Subsection 705-2.06

Structural Steel	Section 716

Elastomeric Bearing Pads	Subsection 720-2.01

Epoxy Adhesive for Elastomeric Bearing Pads	Subsection 720-2.02

Polytetrafluoroethylene (PTFE) Bearings 	Subsection 720-2.03

Water Stops	Section 723

CONSTRUCTION REQUIREMENTS

516-3.01 EXPANSION JOINTS. Locate and form expansion joints as shown on the Plans.

1.	Shop Drawings. Provide shop drawings for expansion joints having a total movement of more than 1.75 inches. Submit drawings showing installation procedures and joint assembly details. Install joints only after shop drawings are approved.

2.	Manufacture and Fabrication.

a.	Open Joints. Place open joints where shown on the Plans. Remove forms without chipping or breaking the corners of the concrete. Do not extend reinforcement across an open joint, unless shown on the Plans.

b.	Filled Joints. Construct expansion joints with expanded polyethylene joint filler as thick as the width of the joint.

Cut the joint filler to the same shape and size as the adjoining surfaces. Fix the joint filler against the concrete surfaces in place to keep the joint filler from displacing when concrete is placed.

Immediately after removing the forms, inspect the expansion joints. Remove concrete or mortar that has sealed across the joint.

c.	Compression Seals. Shape the joint as shown on the Plans. Install the seal according to the manufacturer’s instructions.

Install the seal in one piece for the full width of the roadway joint. Install the seal immediately after the curing period of the concrete.

d.	Strip Seals. Use expansion joint strip seals in one piece for the length of the joint. Shape the steel components to conform to the section of the concrete. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

e.	Steel Joints. At the shop, shape the plates, angles, or other structural components to conform to the section of the concrete. Fabricate and paint structural shapes to meet the specifications covering those items. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint. Meet the joint opening dimension shown on the Plans.

f.	Modular Seals. Shape the joint as shown on the Plans. Use expansion joint modular seals in one piece for the length of the joint. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

g.	Silicone Expansion Joint Seals.  Prepare concrete surface by sandblasting each face until the surface is roughened and all contaminants are removed.  Ensure all joint faces are sound, clean, dry, and free of frost immediately prior to sealant application.  Install a bond breaking backing material that is configured per the sealant manufacturer’s specifications.  Install the sealant according to the manufacturer’s recommendations.

3.	Tolerances. Install expansion joints conforming to the following tolerances:

a.	Top Surface Profile: 1/4 to 5/8 inch recessed from the finished roadway profile.

b.	Surface Irregularities (deviation from a 10-foot straight edge): ±1/8 inch.

c.	Gap Width: ±1/4 inch.

516-3.02 BEARINGS. Install bearing at locations shown on the Plans.

1.	Shop Drawings. Provide shop drawings showing all details of the bearings and of the materials proposed for use. Fabricate bearings only after shop drawings are approved.

2.	Packaging, Handling, and Storage. Prior to shipment from the point of manufacture, package the bearings in a manner to ensure that each bearing will be protected from damage during shipment, handling, and storage. Store the bearings in an area that provides protection from environmental and physical damage. Prior to installation, clean the bearings of all foreign substances.

3.	Construction and Installation. Set the bearing plates, sole plates and elastomeric bearing pads as shown on the Plans in the exact position with full and even bearing on properly finished bearing seats.

Finish bearing areas or grind them to elevation and parallel to the roadway grade and parallel to the roadway cross slope or crown, unless otherwise shown on the Plans.

When shown on the plans, place grout that meets Subsection 701-2.03 under masonry plates. Mix and place grout according to the manufacturer’s written recommendations. Clean concrete areas that will contact the grout. Remove loose or foreign matter that would prevent the bond between the mortar and the concrete surfaces.

Tightly pack the grout under the masonry plates to provide full bearing. After placing, cover exposed surfaces of grout pads with a heavy thickness of burlap saturated with water for 3 days. Do not place a load on the grout until the grout has attained a compressive strength of 5000 psi as determined by field specimen.

Locate sole plates to correspond with the temperature during erection. Anchor bearing securely. Adjust the nuts on anchor bolts at the expansion ends of spans to permit the span to move freely. Burr threads sufficiently to prevent removal of nuts.

Apply epoxy adhesive to the bottom surface of the elastomeric bearing pads before placing them. Do not move the pad until the epoxy has cured and full adhesion is achieved. Do not apply epoxy adhesive to elastomeric bearings used in PTFE bearing assemblies.

4.	Tolerances. Install bearings conforming to the following tolerances:

a.	Horizontal Position: ±1/8 inch

b.	Elevation: ±1/8 inch

c.	Grade and cross slope: ±1/16 inch per foot.

516-3.03 WATER STOPS. Furnish water stops in continuous, full-length segments without field splices. Do not field splice water stops. Ensure all spliced performed by the Manufacturer are fully vulcanized.

Use spacers, supporting wires, or other approved devices to secure the water stop in the position shown on the plans.

Remove and replace water stops that are out of position or shape at no expense to the Department.

516-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Expansion Joint. Will not be measured for payment.

Bearings. Will not be measured for payment.

Water Stops. Will not be measured for payment.

516-5.01 BASIS OF PAYMENT.

Expansion Joints, Bearings, and Water Stops are subsidiary.

DOT BRIDGE-012012

- SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

603-1.01 DESCRIPTION.  Add the following:

This work shall also include the low strength concrete used for the leveling slab and for void filler as called out in the Plans.

603-5.01 BASIS OF PAYMENT.  Add the following after the first sentance:

Low strength concrete for the leveling slab and void filler is incidental to item 602(3).

0001(458)/52972-020813

- SECTION 603

CULVERTS AND STORM DRAINS

Special Provisions

603-1.01 DESCRIPTION.  Add the following:

This work shall also consist of installing culvert marker posts.

CR42-082703

Add the following:

This work shall also consist of removing and disposing existing Mission Creek bridges.

0001(458)/52972-071813

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following:

Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9 inches.

CR42-082703

603-3.01 GENERAL.

Add the following:

Removal and disposal of Mission Creek bridges shall meet the requirements of Section 202, Removal of Structures and Obstructions.

0001(458)/52972-071813

603-3.03 JOINING PIPE.

2.	Metal Pipe.  Add the following after the 2nd sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe of similar or dissimilar materials, regardless of the type of coupling band.  Except, the end section joint does not require a gasket.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

3.	Polyethylene Pipe.  Add the following after the 1st sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe.  Except, the end section joint, and where the pipe is manufactured with a locking joint such that the joint seals watertight, a gasket is not required.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

CR6031-032411

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:

- Mission Creek Bridges.  By the complete removal and disposal of all Mission Creek bridges.

0001(458)/52972-071813

Add the following:

Culvert marker posts will not be measured for payment.

CR42-082703

603-5.01 BASIS OF PAYMENT.  Replace the first sentence with:

Coupling bands, gaskets and other items necessary for the proper joining of the sections are subsidiary.

CR6031-032411

Add the following:

Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

CR42-082703

Add the following:

Removal and disposal of all Mission Creek bridges will not be paid for directly, but will be subsidiary to Item 603(2).

0001(458)/52972-071813

SECTION 606

GUARDRAIL

Special Provisions

Delete Subsection 606-2.01 and replace with the following:

606-2.01 MATERIALS.  Use materials that conform to the following:

Concrete, Class A or W

(or an approved, pre-mixed, sacked concrete)	Subsection 501-3.01

Wire Cable	Subsection 709-2.02

Metal Beam Rail	Subsection 710-2.04

Guardrail Posts and Blocks	Subsection 710-2.06

Guardrail Hardware	Subsection 710-2.07

Guardrail Terminals	Subsection 710-2.11

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

The marker materials shall be durable, resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  The flexibility may be in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively impact the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole as a result of snow thrown from snowplows

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel may not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering markers.

Guardrail Reflector Assembly Brackets	Section 730

Fabricate from aluminum alloy or galvanized steel.

Retroreflective Sheeting	AASHTO M 268, Type VIII or IX

CR6062-051513

Add the following:

Guardrail Connection Plate	Subsection 722

High Strength Bolts	Subsection 722

CR60611-051513

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL.  Replace the second paragraph with the following:

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals that are required to completely install a segment of guardrail before beginning work on the segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic will encounter first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run will connect to existing barrier, buried in the backslope, or guardrail, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may be started at the point of connection.  The exception allows for starting at the downstream end, a temporary crash cushion or TMA is required at all incomplete upstream guardrail ends.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test Level 3 at all non-crashworthy guardrail ends within the clear zone.  Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

CR6063-110410

606-3.02 POSTS.  Delete the first two numbered items and replace with:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Replace 3.a. with:

a.	The underlying material is no larger than six inches; and

Replace No. 4. with:

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically.  Compact under and around posts to the Engineer's satisfaction.

CR6064-110410

606-3.03 BEAM RAIL.  In the first paragraph, second sentence, replace "150 feet" with "100 feet"

CR6065-110410

606-3.05 TERMINAL SECTIONS.  Delete the second paragraph.

Replace the fourth paragraph with the following:

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each parallel guardrail terminal.  Attach flexible markers to the "P.T." post of the Controlled Release Terminals.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

The connection shall not negatively impact the performance of the guardrail as noted in 606-2.01.

CR6062-051513

Add the following subsection 606-3.09 Install New Guardrail.

606-3.09 INSTALL NEW GUARDRAIL.  Install guardrail as shown on the applicable Standard Drawings, measured from the top of the rail to the finished shoulder surface below the rail.  New guardrail installed with height less than 28", or greater than 30" is unacceptable and must be adjusted according to Subsection 606-3.08.  Adjusting new guardrail will not be paid for separately, but is subsidiary to other 606 pay items.

CR60611-051513

Add the following Subsection 606-3.10 Flexible Markers:

606-3.10 FLEXIBLE MARKERS. For each parallel rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

CR6062-051513

Add the following Subsection 606-3.11 Length of Need Verification.

606-3.11 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

CR6068-051513

606-5.01 BASIS OF PAYMENT.

2.	Terminal Sections.  Replace a. with the following:

a.	Parallel Guardrail Terminal.  The contract price includes rail elements, posts, blocks, pipe sleeves, cable assemblies, guardrail extruders, terminal markers, and all associated hardware required for a complete installation.

Delete b.

c.	Controlled Release Terminals (CRT).

Replace "object markers" with "terminal markers"

0001(458)/52972-020312

Delete Pay Item 606(10) Slotted Rail Terminal and 606(11) Extruder Terminals.

Add Pay Item 606(13) Parallel Guardrail Terminal:

Pay Item No.	Pay Item	Pay Unit

606(13)	Parallel Guardrail Terminal	Each

CR6061-110410

- SECTION 611

RIPRAP

Special Provision

611-2.01 MATERIALS.  Add the following after the first sentence:

Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.

CR277-110705

611-5.01 BASIS OF PAYMENT.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

611(1)	Riprap, Class II	Cubic Yard

0001(458)/52972-103012

- SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS.  Delete first paragraph of Item 2. Including subitems a., b., c., and replace with:

2.	Sign Fabrication.	Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

(1)	For temporary installations, the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

(2)	For flexible signs, (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports.  Use white Type VIII or Type IX reflective sheeting for background of sign and stripes.

c.	Non-illuminated Overhead Signs with White Legends on Green Backgrounds.  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow Green School Area Signs.  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow green (measured according to ASTM E 2301) for ten years according to the following criteria:

	Minimum Fluorescent Luminance Factor:		YF = 20%

	Minimum Total Luminance Factor:			YT = 35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

CR6151-091311

615-4.01 METHOD OF MEASUREMENT.  Replace the 3rd paragraph, "Delineators," with:

Delineators.  By each, complete in place.  A single delineator consists of one post equipped with three reflectors.

CR6153-091311

- SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Replace the 1st sentence with:  Establish a perennial stand of grass or other specified living vegetative cover, by clearing, applying soil stabilization material(s) and seeding the area(s) shown in the Plans, including new and disturbed area(s), and area(s) identified by the Engineer.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Soil Stabilization Material	Section 727 (Stabilization Material)

Topsoil	Section 726

(In this specification, topsoil is included when referencing Stabilization Material)

CR6181-092012

Replace Subsection 618-3.01 with the following:

618-3.01 SURFACE PREPARATION.  Clear area(s) to be seeded; make the area(s) reasonably free of ruts, holes, and humps. Clear area(s) of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the application of stabilization material, the seeding operation, growth of cover, or subsequent maintenance of the vegetative-covered areas.

Apply stabilization material after clearing is complete, refer to 618-3.02.

Mix the seed with the stabilization material before applying the material (not including topsoil), or seed the stabilization material immediately after the material is applied for the best results as recommended by the supplier/manufacturer.

Prepare the stabilization material by grooving the material in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rakes;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

CR6182-092012

618-3.02 SEEDING SEASONS.  Replace the 1st sentence with the following:  Seed disturbed areas after permanent cessation of ground disturbing activities in that area, within the time period specified in the Alaska Department of Environmental Conservation (ADEC) Alaska Pollutant Discharge Elimination System (APDES) Construction General Permit (CGP) for Alaska, Section 4.4 Final Stabilization, and Section 641 Erosion, Sediment, and Pollution Control.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

CR6183-101711

618-3.03 APPLICATION.  Replace the first three sentences with the following:  Seed, seeding, reseeding includes the application of seed, fertilizer and stabilization material.

Apply seed mix, fertilizer, and stabilization material at the rate specified.  If the seed mix, fertilizer and stabilization material are not included in the Plans or Specifications, including their application rates, use the recommendations of the ADNR and the Revegetation Manual for Alaska.

Do not seed areas of bedrock, plant beds, and areas indicated in the plans as “no seeding.”

Add the following:

Apply seed and stabilization material in one application when using the hydraulic method.  Apply fertilizer with the hydraulic method.  Include the fertilizer with the seed and stabilization material or apply separately.

TABLE 618-1

APPLICATION RATES

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) | 0.50 lbs. 0.50 lbs. Total = 1.00 lbs. |
| Soil Stabilizera |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12 lbs. |

a.	Soil Stabilizer/Stabilization Material.  Refer to Section 619 and 727 for additional soil stabilization and soil stabilization materials.

Do not remove required tags from seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

0001(458)/52972-102912

Replace Subsection 3.04 with the following:

618-3.04 MAINTENANCE.  Maintain seeded areas in a satisfactory condition for the term of the Contract, including warranty obligations.

Maintenance includes but is not limited to:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep.  Apply and prepare the stabilization material for seeding.  Seed repaired area(s).  Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete.  Reseed bare patches of soil more than 10 square feet in area.  Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for growth of vegetative cover.  If in the opinion of the Engineer, too little or too much water is being applied, adjust the amount of water as directed.

Add Subsections 618-3.05:

618-3.05 ACCEPTANCE.  The Engineer will perform a visual inspection of the vegetative mat considering each station and each side of the road a separate area.  Acceptance of the vegetative mat requires a minimum of 70% cover density in the inspection area, gullies repaired and reseeded, and no bare patches of soil more than 10 square feet in area.

Repair/reseed areas that are not accepted.

Add Subsection 618-3.06:

618-3.06 PERIOD OF ESTABLISHMENT.  For each area accepted, the establishment period extends one complete growing season following the date of acceptance.  Employ all possible means to preserve/maintain the new vegetative mat in a healthy and vigorous condition to ensure successful establishment.  Maintain the vegetative mat, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

618-4.01 METHOD OF MEASUREMENT.  Delete the 3rd paragraph, "Seeding by the Pound," and replace with:

Seeding by the Pound. By the weight of dry seed acceptably seeded and maintained.

Add the following:

M Gal is equal to 1000 gallons.

618-5.01 BASIS OF PAYMENT.  Delete the 1st sentence:  "Mulching will be paid for under Section 619".

Delete paragraphs beginning: “Seeding by the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Pay Item 618(1), Seeding:  Payment is for established vegetative mat.  Stabilization material preparation (seed, fertilizer, stabilization material, and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, stabilization material and preparation for seeding, seed, fertilizer,  and the water required for hydraulic application.

Seeding by the Pound.  Pay Item 618(2), Seeding:  Payment is for established vegetative mat.  Stabilization material preparation (seed, fertilizer, stabilization material and the water required for all hydraulic applications) are subsidiary.  Maintenance including:  1. Protection, 2. Repairs, 3. Reseeding, is also subsidiary.  Repairs and reseeding include, but are not limited to:  fill, stabilization material and preparation for seeding, seed, fertilizer, and the water required for hydraulic application.

Add new pay description:

Water for Seeding.

	Water for hydraulic application is subsidiary to Pay Items 618(1) and 618(2), and includes, but is not limited to:  the initial application of seed, fertilizer, and stabilization material and the reapplication for repairs and reseeding.

	Water applied for growth of vegetative mat (Subsection 618-3.04.4 Watering), for the term of the Contract, including warranty obligations, is paid under Pay Item 618(3).

Add the following:

Stabilization materials are paid under Section 619 and 620 Pay Items, except as noted for "Seeding by the Acre", "Seeding by the Pound" and warranty obligations, Subsection 105-1.16.

CR6182-092012

- Special Provision

- Replace Section 619 with the following:

- SECTION 619

SOIL STABILIZATION

619-1.01 DESCRIPTION.  Furnish, install, and maintain materials to stabilize the soil.  Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Alaska Department of Transportation and Public Facilities (ADOT&PF):

Standard Specifications for Highway Construction, 2004 Edition.

Seeding	Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	American Association of State Highway and Transportation Officials (AASHTO):

Standard Practice for:

	Compost for Erosion/Sediment Control (Filter Berms and Filter Socks)	R51-10

	Compost for Erosion/Sediment Control (Compost Blankets)	R52-10

3.	United States Composting Council (USCC):

	Testing Methods for the Examination of Compost and Composting (TMECC)

	Seal of Testing Assurance Program (STA) documents

4.	Erosion Control Technology Council (ECTC)

	Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

	Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

5.	National Transportation Product Evaluation Program (NTPEP)

	Testing and Evaluation of Products Materials and/or Devices

6.	Texas DOT/Texas Transportation Institute (TTI) Hydraulics and Erosion Control Laboratory

619-1.03 SUBMITTALS.  Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.  Submit a sample of each material to the Engineer 7 days before the scheduled installation.

1)	Test compost, all applications, no more than 90 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS.  Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Stormwater Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch	Subsection 727-2.01

	Dry Erosion Control, Stabilization Products

	Hydraulic Erosion Control Products (HECPs)

2)	Matting	Subsection 727-2.02

	Rolled Erosion Control Products (RECPs)

3)	Sediment Retention Fiber Rolls (SRFRs)	Subsection 727-2.03

	Filter Socks

	Compost Socks

	Coir Logs

4)	Compost	Subsection 727-2.04

5)	Tackifier	Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))	Subsection 727-2.06

7)	Geotextile-Encased Check Dams and Sediment Barriers	Subsection 727-2.07

8)	Sandbag	Subsection 727-2.08

9)	Manufactured Inlet Protection System	Subsection 727-2.09

10)	Clear Plastic Covering	Subsection 727-2.10

11)	Staples	Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL.  Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

1.	Material Storage and Protection.  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

	Precipitation

	Extended ultraviolet radiant including sunlight

	Chemicals that are strong acids or other

	Flames and welding sparks

	Excess temperatures

	Other environmental conditions that may damage the materials

2.	Fabrication.

a.	Sandbags.  Sand bags shall measure 15 inches by 30 inches.  Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack.  Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION.  Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material.  Section 618 and 620.

619-3.03 APPLICATION.  Apply stabilization material, including rate of application, according to the specifications.  If not specified, apply according to the manufacturer's requirements.  Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding.  Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers.  Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders.  Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets.  Construct compost blankets according to AASHTO R 52-10 and as specified.  Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified.  Apply material either by hand spreading and or pneumatically.  Compost will have no free water visible or produce dust when handled.  Place compost before seeding or mix seed with compost.

6.	Check Dams.  Place check dams as soon as possible and practicable or when and where if directed by the Engineer.  Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel.  Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag.  Place the initial row in tight contact with the ditchline for the length of the dam.  Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance.

Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP.  All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag.  Place the initial row in tight contact with the surface perpendicular to the slope.  Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to AASHTO R 51-10.  Use coarse compost.

9.	Turf Reinforcement Mats.  According to manufacturers installation instructions.

619-3.04 MAINTENANCE.  Maintain stabilized areas in a satisfactory condition for the term of the Contract, including warranty obligations.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately.  Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations.  Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

a.	Protecting stabilized areas against traffic by approved warning signs or barricades.

b.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

c.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

d.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP.  Make repairs as required by same and as directed.

619-4.01 METHOD OF MEASUREMENT.  Section 109, measured on the slope of the ground surface.

619-5.01 BASIS OF PAYMENT.  Water, maintenance, repair, removal, and disposal of temporary stabilization materials are subsidiary.

Seeding is paid under Section 618 Pay Items, topsoil under Section 620 Pay Items, silt fence under Section 633 Pay Items and temporary erosion, sediment, and pollution control under 641 Pay Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

619(1)	Mulching	Square Yard

619(2)	Matting	Square Yard

619(3)	Compost	Square Yard

619(4)	Turf Reinforcement Mat	Square Yard

619(5)	Sediment Retention Fiber Rolls (SRFRs)	Linear Foot

619(6)	Check Dam and Sediment Barrier - Geotextile	Linear Foot

619(8)	Compost Berm	Linear Foot

619(9)	Sandbags	Each

619(10)	Manufactured Inlet Protection System	Each

619(11)	Sandbag Inlet Protection System	Each

CR619-092612

Special Provision

Add the following Section:

SECTION 622

PARK FACILITIES

622-1.01 DESCRIPTION.  This work shall consist of furnishing, constructing and placing park facilities in conformance with the plans and Special Provisions.

622-1.02 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

MATERIALS

622-2.01 GENERAL.  All materials shall be new and conform to the details shown on the plans or as specified.

622-2.02 STRUCTURAL STEEL.  Structural steel shall conform to the requirements of ASTM Specification A 36 (Standard Specification for Carbon Structural Steel).

622-2.03 GALVANIZING.  Conform to AASHTO M111/ASTM A123 (Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products), or AASHTO M232/ASTM A153 (Standard Specification for Zinc Coating [Hot-Dip] on Iron and Steel Hardware). Repair damaged galvanizing by using low melting point zinc repair rods in conformance with ASTM a780-00 (Standard Practice for Repair of Damaged and Uncoated Areas of Hot-Dip Galvanized Coatings).

622-2.04 LUMBER.  Conform to Section 713. Wood species shall be Douglas Fir, Western Hemlock or Hem-fir unless otherwise specified.

  - Dimensional. Dimensional lumber and timbers are shown on the plans in nominal dimensions, i.e.; 2x4, indicating surfaced four sides (S4S) or planed material. Use classification for light framing shall be No. 2 Grade or Better. Manufacturing classification shall be Dressed (Surfaced) Lumber. Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

622-2.05 TREATED LUMBER.  Wood species conforms to Subsection 622-2.04.

Treatment shall be as follows:

- Above Ground Applications.  Preservative pressure treatment shall conform to Section 714. Pressure treat with preservative Ammonical Copper Quat – Type A,B,C or D(ACQ-A,B,C, or D) or Copper Azole – Type A (CBA-A). Minimum retention shall be 0.40 pounds per cubic foot or to refusal. Treated materials shall be uniformly brown in color and nonincised. This type of treated lumber is commonly used for residential decks for above ground applications. Incising may be used on 4x and thicker material to obtain minimum retention.

622-2.06 FASTENERS.  Commercial quality and type of nails and screws as required to securely hold all members in place in accordance with National Design Specifications. Nails shall be hot dipped galvanized. All other fasteners shall be corrosion resistant. Fasteners in pressure treated wood shall be hot dipped galvanized. Nails and wood screws below grade in pressure treated wood shall be stainless steel.

622-2.07 PAINT.  Unless otherwise specified, use the following paint types and colors, or approved equals:

- Solid Oil Stain.  Exterior oil/alkyd flat finish stain, color “Russet”. DF7XX as manufactured by Fuller O’Brien/ Devoe Products, Russet as manufactured by Pittsburgh Paint Company, Behr Plus 10 Solid Stain #354 Russet, or Olympic Russet as manufactured by PPG Architectural Finishes, Inc. Submit color samples of proposed substitutions for approval.

- Semi-Transparent Oil Stain.  Exterior alkyd based stain, color to match solid oil stain “Russet”. Stains for pressure treated wood shall be recommended by manufacturer for use on pressure treated wood.

- Metal Primer Paint.  As recommended by enamel pain manufacturer.

- Enamel Paint.  Exterior alkyd base gloss enamel. Color to match solid oil stain color.

- Above Ground Wood Preservative.  Brown preservative with active ingredient of minimum 9.08 percent copper naphthenate (equivalent to minimum 1 percent metallic copper). Color to be approved by Engineer.

- End Cut Preservative for Treated Wood.  Brown preservative with active ingredient of minimum 10 percent copper naphthenate (equivalent to minimum 1 percent metallic copper). Color to match preservative pressure treatment color.

Paint that has been frozen or is out of date shall be replaced at no additional cost to the Department.

622-2.08 STEEL / FIBERGLASS BOARDWALK AND STAIRWAY TREAD.  All material shall be new and conform to the following:

Structural Steel and Steel Members.  Shall conform to the requirements of Subsection 622-2.02. Member sizes and dimensions shall be as shown in the plans.

Fiberglass Grating.  Shall be fiberglass vinyl ester resin. Load bar depth shall be 1-1/2 inches square mesh grate. Color shall be dark gray. Product similar to Fibergrate Fiberglass Grating: Fibergrate Molded Grate for landings and Fibergrate Fibertred for stair treads. Fibergrate Composite Structures Inc.; 4285 Kellway Circle, Suite 224; Addison, TX 75001; Phone 800-527-4043 or www.fibergrate.com.

Fiberglass grating hold-down clips shall be M-clip, saddle type, similar to Fibergrate MI-40 or approved equal.

Edge sealing kit shall be as specified by manufacturer.

Lumber.  All lumber shall be surfaced four sides in conformance with Subsection 622-2.04 and preservative pressure treated in conformance with Subsection 622-2.05.

Fasteners.  Fastener types and dimensions shall be as shown in the Plans and in conformance with Subsection 622-2.06.

622-2.09 ALUMINUM STAIRWAY TREAD.  Structural aluminum shall conform to the requirements of ANSI 6061-T6, 3003-H14, or 3003-H112.

Aluminum treads for stairway construction shall be serrated rectangular bar grating with a corrugated angle nosing. Bearing bars shall be 1-3/4” x 3/16” with a 1-3/16” center to center spacing.

622-2.10 BARRIER RAIL.  Conform to the Plans. Steel posts and other steel members shall conform to the requirements of Subsection 622-2.02. 2x4 railing shall conform to the requirements of Subsection 622-2.05.

CONSTRUCTION REQUIREMENTS

622-3.01 GENERAL.  The location for the stairway is shown on the drawings.

622-3.02 EXCAVATION AND BACKFILL.  Conform to the requirements of Section 204 and the details on the plans.

622-3.03 STRUCTURAL STEEL.  Welding to be performed by competent certified welders and shall conform to American Welding Society D1.1.

622-3.04 WOOD.  Competent carpenters shall be employed and all framing shall be true and exact. Unless otherwise specified, nails and spikes shall be hand driven with just sufficient force to set the heads flush with the surface of the wood. Power nail guns are prohibited. All non-removable shipping, storage, weathering and erection marks on fabricated lumber shall be hidden from view in the completed work. Use of damaged lumber shall not be allowed. Store on-site lumber above the ground and protected from damage and weathering.

Holes for machine and carriage bolts shall be bored with a bit of the same diameter as that of the bolt. Holes for lag screws shall be bored with a bit not larger than the body of the screw at the root of the thread.

Unless otherwise specified, USS flat washers shall be used in contact with all bolt heads and nuts that would otherwise be in contact with wood.

622-3.05 PAINT.  Deliver in sealed containers with labels legible and intact. Remove dirt, grease, oil and other construction debris prior to painting. Ensure that surfaces to be painted are even, smooth, sound, clean, dry, and free from defects affecting proper application. Apply per manufacturer’s recommendations. Apply paint material evenly without runs, sags, or other defects. Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer. Cover surfaces completely to provide uniform color and appearance. Remove all paint, stain, or other finish material where it has spilled or spattered.

- General.  Unless otherwise specified, schedule finishes as follows:

- Treated Wood, Surfaced.  Finish surfaces not scheduled to receive stain or oil stain with wood preservative.

- Treated Wood, Rough Cut.  Saturate below and above ground surfaces not scheduled to receive stain with wood preservative.

- Treated Wood, Hidden.  Dado cuts, cut ends, drilled holes and field cuts in wood materials shall be brush coated to saturation with end cut preservative.

- Treated Wood, Exposed.  Saturate cut surfaces with scheduled finish. Finish surfaces not scheduled to receive stain with wood preservative.

- Metal.  Prime and paint exposed metal surfaces that are not fabricated of corrosion resistant material or galvanized.

- Landing Grate and Stairway Tread – Steel Walkway

- Fiberglass Grating. Factory Finish, Color Dark Gray

- Wood, Visible Surfaces. Semi-Transparent Oil Stain

- Above Ground Non-Galvanized Metal. Primer and Enamel Paint

- Stairway Tread – Aluminum.

- Structural Aluminum. No Finish Required

- Stair Tread. No Finish Required

- Handrail and Posts. No Finish Required

622-3.06 BOARDWALK AND STAIRWAY TREAD.  Submit shop drawings for approval prior to construction of landings and stairs. Construct in accordance with the Plans and Specifications. A 25 foot wide construction corridor for the length of the boardwalk shall be established. No equipment, access, or material storage is allowed outside the construction corridor. Any disturbed area outside the construction corridor shall be revegetated and restored to its original appearance at no additional cost to the Department. Ground cover disturbed by boardwalk construction within the construction corridor shall be revegetated to its original condition, or to the satisfaction of the Engineer.

Structural Steel.  Steel beams shall be set parallel to adjacent steel beams where the Plans call for straight alignments. Steel beams shall be angled symmetrically between adjacent steel beams where the Plans call for turns on the boardwalk alignment.

Steel members serving as railing support posts shall be set plumb vertically. Top of steel posts shall be constructed to the line and grades shown on the Plans.

Welding type and size shall be as shown in the Plans and in accordance with the standard practices of the American Welding Society D1.1.

Fiberglass Grating.  Follow manufacturer’s recommendations for installation and safety procedures. Install fiberglass grating panels in full lengths and widths whenever possible. Panel ends shall rest supported securely on top of steel beams. Fasten fiberglass grating panels onto steel beams using saddle type hold-down clips, as recommended by the manufacturer. A minimum of 4 clips per panel, spaced a maximum of 48 inches shall be used. Any cuts made shall be sealed by manufacturer recommended or approved methods.

Lumber.  Store all lumber minimum 6 inches above ground on framework or blocking and protected with waterproof covering allowing for adequate air circulation and ventilation. Do not store materials in wet or damp conditions.

Horizontal railing shall be constructed to the line and grades shown on the Plans. Fasten onto steel posts as shown in the Plans.

622-3.07 ALUMINUM STAIRWAY TREAD.  Submit shop drawings for approval prior to construction of landings and stairs. Construct in accordance with the Plans and Specifications. Aluminum welding shall conform to the requirements of the American Welding Society D1.2.

622-4.01 METHOD OF MEASUREMENT.  Facilities with the unit measure each will be measured by the actual number of facilities completed and accepted.

Excavation and embankment for facilities outside the limits shown on the Plans will be measured for payment only if said activity is directed by the Engineer. Excavation and backfill required for items paid for under this Section will not be measured for payment.

Steel Stairway is a lump sum item and will not be measured separately for payment. The Engineer’s acceptance constitutes method of measurement. All labor, material, and equipment required to construct the steel stairway, the landings, and the handrail will be subsidiary to Item 622(12A) Steel Stairway and will not be measured separately for payment.

Aluminum Stairway is a lump sum item and will not be measured separately for payment. The Engineer’s acceptance constitutes method of measurement. All labor, material, and equipment required to construct the aluminum stairway, and all handrail will be subsidiary to Item 622(12B) Aluminum Stairway and will not be measured separately for payment.

622-5.01 BASIS OF PAYMENT.  The accepted quantity of facilities will be paid for at the contract unit price per unit of measurement for the type specified completed in place, and listed below excluding all clearing and topsoil, which shall be paid for separately at contract unit prices.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

622(1)	Steel Stairway	Lump Sum

622(2)	Aluminum Stairway	Lump Sum

0001(458)/52972-022212

Special Provisions

Replace Section 639 with the following:

SECTION 639

DRIVEWAYS

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 Items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(1)	Residence Driveway	Each

639(2)	Commercial Driveway	Each

639(3)	Public Approach	Each

639(4)	Driveway	Each

639(6)	Approach	Each

CR58-050902

- SECTION 640

MOBILIZATION AND DEMOBILIZATION

Special Provisions

640-1.01 DESCRIPTION.  Add the following:

6.	Comply with the Alaska Department of Labor and Workforce Development (DOLWD) requirements for Worker Meals and Lodging, or Per Diem; as described in their September 1, 2009 memo WHPL #197 (A3) and the State Laborer’s and Mechanic’s Minimum Rates of Pay (current issue).  On Federal-aid projects, PL 109-59, 119 STAT. 1233, Sec. 1409(c) also applies.

Ensure subcontractors comply with the Federal and State DOLWD requirements.

Ensure facilities meet the Alaska Administrative Code 8 AAC 61.1010 and 8 AAC 61.1040 Occupational Safety and Health Standards, 18 AAC 31 Alaska Food Code, and U.S. Code of Federal Regulations 29 CFR Section 1910.142 Temporary Labor Camps.

Do not consider the cost of Meals and Lodging, or Per Diem in setting wages for the worker or in meeting wage requirements under AS 23.10.065 or AS 36.05.

640-4.01 METHOD OF MEASUREMENT.  Delete the numbered paragraph 3 and substitute the following:

3.	The remaining balance of the amount bid for Mobilization and Demobilization will be paid after all submittals required under the Contract are received and approved.

Add the following:

4.	Progress payments for Worker Meals and Lodging, or Per Diem will be computed as equivalent to the percentage, rounded to the nearest whole percent, of the original Contract amount earned.

640-5.01 BASIS OF PAYMENT.  Add the following Pay Item:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

640(4)	Worker Meals and Lodging, or Per Diem	Lump Sum

CR6401-033012

Special Provisions

- Replace Section 641 with the following:

- SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.

Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.

These definitions apply only to Section 641.

Active Treatment System Operator. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

Alaska Department of Environmental Conservation (ADEC). The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

Alaska Pollutant Discharge Elimination System (APDES). A system administered by ADEC that issues and tracks permits for storm water discharges.

Best Management Practices (BMPs). Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

Clean Water Act (CWA). Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

Consent Decree. The decree entered by the United States District Court for the District of Alaska on September 21, 2010, regarding compliance with the CWA and implementation of the CGP, to which the United States and the Department are parties.

Construction Activity. Physical activity by the Contractor, Subcontractor, or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

Construction General Permit (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by ADEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

Corp of Engineers Permit (COE Permit). A U.S. Army Corp of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

Electronic Notice of Intent (eNOI). The electronic Notice of Intent submitted to ADEC, to obtain coverage under the CGP.

Electronic Notice of Termination (eNOT). The electronic Notice of Termination submitted to ADEC, to end coverage under the CGP.

Environmental Protection Agency (EPA). A federal agency charged to protect human health and the environment.

Erosion and Sediment Control Plan (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

Final Stabilization. Is defined in this section as it is defined in the CGP.

Hazardous Material Control Plan (HMCP). The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

Inspection. An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Stormwater Inspector.

Municipal Separate Storm Sewer System (MS4) Permit. An ADEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

Multi-Sector General Permit (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

Operator(s). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

Project Zone. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Department by the Contract and are directly related to the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

Records. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the Consent Decree, the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

Spill Prevention, Control, and Countermeasure Plan (SPCC Plan). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

Spill Response Field Representative. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

Storm Event. A rainfall event that produces more than 0.5 inch of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of dry weather.

Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules, and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

Storm Water Pollution Prevention Plan Two (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

Subcontractor Spill Response Coordinator. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

Subcontractor SWPPP Coordinator. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

Superintendent. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

SWPPP Amendment. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP Preparer. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

Utility Spill Response Coordinator. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

Utility SWPPP Coordinator. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.

For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP) use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14 day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP. See Item 4 for further SWPPP submittal requirements.

2.	Hazardous Material Control Plan.  Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control, and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to ADEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and ADEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to ADEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and ADEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur, transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities, SWPPP Certifications, both permittee’s signed eNOIs and ADEC’s written acknowledgement.

5.	Ending CGP Coverage. Submit an eNOT to ADEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

6.	ADEC SWPPP Review. When CGP Part 2.1.3, requires ADEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to ADEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review. When local government or the CGP Part 2.1.4, requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI. When required by The CGP Part 2.7, modify your eNOI to update or correct information. Reasons for modification include a change in start or end dates, small changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change in location of SWPPP Records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed, the original eNOI indicates disturbed area less than five acres and the project will disturb more than five acres, or a project over five disturbed acres grows by more than 50%.

641-1.04 PERSONNEL QUALIFICATIONS.

Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

The SWPPP Preparer must meet at least one of the following qualifications:

a.	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

b.	Current certification as AK-CESCL, and at least two years experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

c.	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

For Projects disturbing more than 20 acres, the SWPPP Preparer must also have completed a SWPPP Preparation course.

The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

The SWPPP Manager must have current certification as AK-CESCL and must meet the CGP experience, training, and authority requirements identified for the Storm Water Lead and Storm Water Inspector positions as defined in the CGP, Appendix C, Qualified Person.

The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principals and practices of treatment systems in general, and the operation of the project-specific ATS. The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operator's certification course.

The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control; or

b.	CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12.2. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports. Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify that they have read and will abide by the CGP and the conditions of the project SWPPP.

4.	Signatures and Initials. Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with ADEC, COE and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

3.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY.

Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

- Opportunities to phase construction activities;

- Appropriate BMPs and their sequencing; and

- Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.

Use the Department’s ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and the CGP.

Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

	SWPPP Certification for DOT&PF (25D-109)

	SWPPP Delayed Action Item Report (25D-113)

Use the following Department forms for recording information in the SWPPP:

	SWPPP Amendment Log (25D-114)

	SWPPP Certification for Contractor (25D-111)

	SWPPP Construction Site Inspection Report (25D-100)

	SWPPP Corrective Action Log (25D-112)

	SWPPP Daily Record of Rainfall (25D-115)

	SWPPP Delegation of Signature Authority – Contractor (25D-108)

	SWPPP Grading and Stabilization Activities Log (25D-110)

	SWPPP Pre-Construction Site Visit (25D-106)

	SWPPP Project Staff Tracking (25D-127)

	SWPPP Subcontractor Certification (25D-105)

	SWPPP Training Log (25D-125)

SWPPP Template and Forms are available online at:

http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

a.	Over which each operator has operational control; and

b.	Where the Department and Contractor are co-operators.

For work outside the Project Zone, the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

a.	Dedicated to the Project and where the Department is not an operator; and

b.	Not dedicated to the project, but used for the project.

Develop the SWPPP according to the requirements of the CGP and this specification. Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

Comply with the CGP Part 1.4 .2 Allowable Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

Include the Department’s Antidegradation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.5.

There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Department will initiate a monitoring program for the storm water within the Project Zone, and will provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.1.  Use stakes, flags, or silt fence, etc. to identifying areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.1.2.

Comply with CGP Part 4.3, requirements for dewatering for trenches and excavations.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

Describe methods and time limits, to initiate temporary or permanent soil stabilization. For areas with mean annual precipitation of:

a.	40 inches or less, initiate stabilization as soon as practicable and within 14 days; or

b.	Greater than 40 inches, initiate stabilization as soon as practicable and within seven days.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to their use and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI.

The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and permanent stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words, and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the title of the BMP Manual or publication, the author (individual or agency), and date of publication. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities.

Identify the inspection frequency in the SWPPP:

•	For areas where the mean annual precipitation is 15 inches or less, inspect at least once every 14 days during construction and within 24 hours of the end of a storm event that resulted in a discharge.

•	For areas where the mean annual precipitation is between 15 to 40 inches, inspect once every seven days.

•	For areas where the mean annual precipitation is 40 inches or greater, inspect twice every seven days.

Linear Project Inspections, described in CGP Part 6.5, are not applicable to this project.

The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the Consent Decree, CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

a.	Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

b.	Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, Records of the AK-CESCL cards or certificates for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager, record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24 hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24 hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, Records of the AK-CESCL cards or certificates of ATS operators. Record the names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide Records of AK-CESCL cards or certificates for the Project Engineer, Stormwater Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s Records in the SWPPP Appendix.   Include the department’s Storm Water Inspector and Storm Water Monitoring Person (if applicable) in section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state, and local agencies.

641-2.03 SPILL PREVENTION, CONTROL, AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.

Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

a.	Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

b.	Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons).

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager those duties may include:

a.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

b.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

c.	Directing and overseeing installation, maintenance, and removal of BMPs;

d.	Performing Inspections; and

e.	Updating the SWPPP including adding amendments and forms.

When Bid Item 641(7) is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

Use soil stabilization material as specified in Section 727.

Use silt fences as specified in Section 729.

Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil, and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS.

The Contractor must be familiar with the requirements of the CGP and Consent Decree because Contractor’s employees will be conducting duties that relate to compliance with the CGP and the Consent Decree. A copy of the Consent Decree is available on the Department’s Statewide Environmental Office web page.

641-3.01 CONSTRUCTION REQUIREMENTS.

Comply with the SWPPP and the requirements of the CGP.

1.	Before Construction Activity may Begin.

The following actions must be completed before Construction Activity begins:

a.	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP, and the SWPPP must be developed (or amended) with findings from the visit;

b.	The SWPPP must be approved by the Engineer;

c.	The Contractor must be authorized to begin by the Engineer;

d.	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the ADEC website;

e.	The Department approved SWPPP must be submitted to ADEC and Local Government (when required); and

f.	The Contractor has transmitted to the Engineer an electronic copy of the approved SWPPP.

You may begin Winter Construction activity according to CGP Part 4.10.3, provided actions a through c above is completed before winter construction activity begins.

Post notices containing the following information:

a.	Copy of all eNOIs related to this project;

b.	Name and 24 hour phone number of SWPPP Manager; and

c.	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

Install an outdoor rain gauge in per manufacturer’s guidance in a readily accessible location on the Project.

Delineate the site for both land disturbing activities and areas that will be left undisturbed. Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

2.	During Construction.

Before subcontractors or utility companies begin soil disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and permanent stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log. Form 25D-125, the dates, and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Fuel the equipment in designated areas. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

Comply with requirements of the HMCP and SPCC Plan, and all local, state, and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents).

3.	Pollutant and Hazardous Materials Reporting Requirements.

If there has been an incident of non-compliance with the CGP that may endanger health or the environment, immediately report the incident to ADEC according to the CGP, Appendix A, Part 3.0. Notify the Engineer immediately and to the extent possible coordinate reports to ADEC with the Engineer.

The report must include:

a.	A description of the noncompliance and its causes;

b.	The exact dates and times of noncompliance;

c.	If not yet corrected the anticipated time the project will be brought back into compliance; and

d.	The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

If there has been an incident of non-compliance with COE Permits, then notify the Engineer immediately of the non-compliance.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law. Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

4.	Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

Implement corrective action:

a.	If an incident of non-compliance with the SWPPP or CGP is identified;

b.	If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

c.	If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

d.	If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

e.	If a prohibited discharge of pollutants, as specified in CGP Part 4.6, is occurring or will occur; or

f.	If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

Implement corrective actions so that they comply with the following time requirements:

a.	For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

b.	For all other conditions, meet both requirements:

(1)	Corrective action is completed in time to protect water quality; and

(2)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

5.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures. Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

a.	As soon as practicable;

b.	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

c.	As identified in the SWPPP.

Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community, the hydro-seeder must be located at the project.

Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

When installing a culvert or other drainage structure where stream bypass is not used, install temporary or permanent stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary and permanent stabilization:

a.	At the culvert or drainage structure inlet and outlet; and

b.	In the areas upstream and downstream, that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install permanent stabilization:

a.	At the inlet and outlet of the culvert, drainage structure, or bridge;

b.	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

c.	Under the bridge.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

6.	Ending CGP Coverage and BMP Maintenance.

The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

a.	Land disturbing activities have ceased;

b.	Final Stabilization has been achieved (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

c.	Temporary BMPs have been removed.

After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

a.	Send written notice to the Contractor with the date that the conditions were met;

b.	Submit an eNOT to ADEC; and

c.	Provide a copy of the eNOT and ADEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to ADEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to ADEC, and insert copies of the Department’s and the Contractor’s eNOTs with ADEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices, and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP and the Consent Decree. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP, and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or ADEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.4.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Activities Log, and SWPPP Daily Record of Rainfall forms. For active projects, update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Stormwater Inspector jointly, unless impracticable. For this paragraph, “impracticable” means when both inspectors must fly to a remote area in the winter or when one inspector is sick or unable to travel to the site due to weather.  When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Unless otherwise directed by the Engineer, insert a Complete-by-Date for each corrective action listed that complies with:

a.	In time to protect water quality;

b.	less than seven calendar days after the date the inspection was performed; and

c.	before the next scheduled inspection.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by noon on the day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an addendum that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the addendum.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

Inspection frequency may be reduced to at least one Inspection every 30 days if approved by the Engineer and the entire site is temporarily stabilized.

When work is suspended due to freezing conditions, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Seasonal Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to seasonal thaw. Seasonal thaw is the annual (first) recurrence of snow and ice melting after a prolonged period of freezing conditions.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log, Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Do not record removal of BMPs as amendments to the SWPPP. See Subsection 641-3.03.9 for documenting removal of BMPs.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document the installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

a.	Identification during an inspection; or

b.	Discovery by the Department’s or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP, or overdue maintenance (after sediment accumulated in sediment basins (including sediment traps and ponds) exceeds 50% of design capacity; or after sediment accumulates to more than half the above ground height on silt fences, check dams, or berms) is a corrective action and must be documented on the Corrective Action Log. Do not record removal of BMPs on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.4.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

641-3.04 FAILURE TO PERFORM WORK.

The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, Consent Decree, or SWPPP, that may endanger health or the environment or for failure to perform work related to this Section 641. If the suspension is to protect workers, the public, or the environment from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions.

If the Contractor fails to take the corrective action within the specified time, the Engineer may:

a.	Suspend the work until corrective action is completed;

b.	Withhold monies due the Contractor until corrective action is completed;

c.	Assess damages or equitable adjustments against the Contract Amount; and

d.	Employ others to perform the corrective action and deduct the cost from the Contract amount.

Reasons for the Engineer to take action under this section include, but are not limited to, the Contractor’s failure to:

a.	Obtain appropriate permits before Construction Activities occur;

b.	Perform SWPPP Administration;

c.	Perform timely Inspections;

d.	Update the SWPPP;

e.	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms to the Engineer;

f.	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

g.	Perform duties according to the requirements of this Section 641; or

h.	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work under this subsection.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

Section 109 and as follows:

Item 641(1), 641(3) and 641(7), are lump sum.

Items 641(2), 641(4) and 641(5), will be measured on a contingent sum basis as specified by the Directive authorizing the work.

Item 641(6) will be measured on a contingent sum basis with withholding determined by the Department.

TABLE 641-1 BMP VALUES - (Reserved)

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

TABLE 641-2 Version B

EROSION, SEDIMENT, AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Subsection Number and Description | Deductable Dollars | Cumulative Deductable Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) Superintendent or SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: - 641-2.01.1 Name of SWPPP Preparer and Date of Pre-Construction Inspection - Not Applicable - 641-3.03.8 Sign and Date SWPPP amendments with qualified person. 641-2.01.4 SWPPP Include approving person’s name and AK-CESCL expiration date. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | 641-2.01.3 and 641-303.8 Failure to either reference a BMP manual or publication, or state that no BMP manual or publication was used | $250 per omission |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to Seasonal Thaw | $5,000 per Project per year |  |
| E | 641-2.01.1 Failure to conduct pre-construction inspections before Construction Activities | $2,000 per Project |  |
| F | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information according to the Consent Decree paragraph 7.c, parts (1) through (11) | $750 per Inspection |  |
| G | 641-3.01.4 Failure to timely accomplish BMP maintenance and/or repairs, In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day | Not to exceed $250,000 per year for all projects |
| H | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely oral endangerment report of violations or for a deficient oral endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely written endangerment report of violations or for a deficient written endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| J | 641-3.04 Failure to comply with the most restrictive requirements of the CGP, approved SWPPP, or Section 641, except as listed above | $750 per occurrence for the first day of noncompliance | Additional $750 for every day the deficiency remains uncorrected |

641-5.01 BASIS OF PAYMENT.

See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641(1) Erosion, Sediment, and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Item 641(2) Temporary Erosion, Sediment, and Pollution Control. At the contingent sum prices specified for all labor, supervision, material, equipment, and incidentals to install, maintain, remove, and dispose of approved temporary erosion, sedimentation, and pollution control BMPs required to implement the SWPPP and SPCC Plan.

Item 641(3) Temporary Erosion, Sediment, and Pollution Control. At the Contract lump sum price for all labor, supervision, material, equipment, and incidentals to install, maintain, remove, and dispose of temporary erosion, sedimentation, and pollution control BMPs identified in the SWPPP and SPCC Plan.

Item 641(4) Temporary Erosion Sediment and Pollution Control Additives. At the contingent sum prices specified in the Directive to authorize the work, for all labor, supervision, materials, equipment, and incidentals for extra, additional, or unanticipated work, to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(5) Temporary Erosion Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor.  All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(6) Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, CGP, or Consent Decree are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Item 641(7) SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641(7) appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be physically present during construction activity with duties and authority as described in Subsection 641-2.04. When Item 641(7) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641(1).

Subsidiary Items. Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641.

This work includes but is not limited to:

a.	Dewatering;

b.	Shoring;

c.	Bailing;

d.	Permanent seeding;

e.	Installation and removal of temporary work pads;

f.	Temporary accesses;

g.	Temporary drainage pipes and structures;

h.	Diversion channels;

i.	Settling impoundment; and

j.	Filtration.

Permanent erosion, sediment, and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense. Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment, and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion, Sediment, and Pollution Control	Contingent Sum

641(3)	Temporary Erosion, Sediment, and Pollution Control	Lump Sum

641(4)	Temporary Erosion, Sediment, and Pollution Control Additives	Contingent Sum

641(5)	Temporary Erosion, Sediment, and Pollution Control by Directive	Contingent Sum

641(6)	Withholding	Contingent Sum

641(7)	SWPPP Manager	Lump Sum

CR641-041312

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-2.01 MATERIALS.  Add the following:

4.	Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.nu-metrics.com)

642-3.01 GENERAL.  Add No. 11:

11.	Before work on the project starts, stake and reference the existing centerline on both sides of the roadway alignment.  Stake the existing centerline on tangents at 100 ft, and 50 ft intervals on curves from the beginning and ending of super-elevation changes when the roadway is no longer at normal crown.  Stake sign locations at proper offset.  Stakes shall be a minimum of 1" x 2" x 2'-0" and be offset 4 to 8 ft from the shoulder on both sides of the roadway.  Extend lath stakes a minimum of 2 ft above ground.  Show the offset distance to centerline and the station from the beginning of the project.  Maintain staking until the final roadway striping is completed.  Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor's vehicle.  Calibrate the DMI to roadway alignments as stationed in the Plans before beginning work.  Record the calibration and staking information in the field book.

Install a reference sign every 500 ft.  These reference signs shall meet the following requirements:

1.	mounted with the base a minimum of 5 ft above the shoulder,

2.	located a minimum of 10 ft from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 6 inch high permanent black lettering with a letter proportion height to width ration of 1:0.6 and a stroke width to height ratio of 1:6, on an orange background.

CR6421-110812

Standard Modifications

642-3.04 OFFICE ENGINEERING.  Delete third sentence and replace with:

Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.

E53-050107

- SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following:

Additional work:

	Illuminate construction activities listed in Table 643-3, Night Work Illumination Level, and Area of Coverage, during hours of night work on roads open to the public inside the project limits.

ES14-031506

643-1.02 DEFINITIONS. Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding’s by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work:  Work occurring between sunset and sunrise on all days, except the “No Lighting Required” period shown in Table 643-2, Night Work Lighting Requirements.

TABLE 643-2

NIGHT WORK LIGHTING REQUIREMENTS

| Latitude (degrees) | No Lighting Required |  | Nearby Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| < 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14-031506

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Add the following:

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

CR6431-051513

643-1.04 WORKSITE SUPERVISOR.

1.	Qualifications. Replace with the following:

Qualifications.  The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements.  The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, your proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this Section.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

CR6432-110410

2.	Duties.  Add the following:

I.	Supervise lighting of Night Work.

ES14-031506

Add No. 3:

3.	Authority.	The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.

4.	Portable Concrete Barriers.  Replace with the following:

Portable Concrete and Steel F Shape Barriers.  Use Portable Concrete and Steel F Shape Barriers that conform to the Plans.  For each direction of traffic, equip each barrier section with at least two side-mounted retroreflective reflectors or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier.  Place the individual reflectors 2-foot or less from each end and space not more than 10-foot apart.  Use yellow reflectors or stripe if you use barriers at centerline.  Use white reflectors or stripe if you use barriers on the roadway shoulder.

CR6431-051513

13.	Plastic Safety Fence.  Replace a., b., and c. with the following:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

16.	Flagger Paddles.  Replace the last sentence with the following:

Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.

CR6432-110410

Add No. 18:

18.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

CR6431-051513

Standard Modification

Replace Subsection 643-2.02 CRASHWORTHINESS with the following:

643-2.02 CRASHWORTHINESS.  Submit documentation, by the method indicated, that the following devices comply with the requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3 on the given schedule.

Submit documentation of compliance to the Engineer before installing devices on the project.

| Work Zone Traffic Control Device Compliance with NCHRP 350 or MASH |  |  |
| --- | --- | --- |
| Category | Devices | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
|  | Portable concrete barriers | FHWA acceptance letter specifying the Test Level required in the Plans or Specifications. |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3.  This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

| Device | Composition | Weight | Height |
| --- | --- | --- | --- |
| Cones | Rubber | 20 lb. | 36 in. |
|  | Plastic | 20 lb. | 48 in. |
| Candles | Rubber | 13 lb. | 36 in. |
|  | Plastic | 13 lb. | 36 in. |
| Drums | Hi Density Plastic | 77 lb. | 36 in. |
|  | Lo Density Plastic | 77 lb. | 36 in. |
| Delineators | Plastic or Fiberglass | N/A | 48 in. |

E77-100410

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

E90-100410

Add the following:

Where construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

CR6431-051513

Standard Modification

Replace Subsection 643-3.03 PUBLIC NOTICE with the following:

643-3.03 PUBLIC NOTICE.  Make sure the Worksite Traffic Supervisor gives a minimum of 3 days notice before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Carriers Association

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.  Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent.  Tell them to use these numbers to alert you when emergency vehicles must pass through the project.  When notified of emergencies, use all equipment and make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator System for selected projects.  Check the special provisions for those requirements.

E78-100410

643-3.04 TRAFFIC CONTROL DEVICES.  Replace paragraphs 6 and 7 with the following:

Use only traffic control devices that meet the requirements of the "Acceptable" category in the American Traffic Safety Services Association (ATSSA) "Quality Guidelines for Temporary Traffic Control Devices" and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project.  Stock repair parts for each Temporary Crash Cushion used on the project.  Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware.  All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the Plans, Specifications, and approved TCPs until permanent roadside safety hardware is installed.  All temporary roadside safety hardware shall meet NCHRP 350 or MASH, Test Level 3 unless otherwise noted.

CR6432-110410

Replace paragraph 8 with the following:

Items paid under this Section remain the Contractor’s property unless stated otherwise.  Remove them after completing the project.

1.	Embankments.  Add the following:

Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

2.	Adjacent Travel Lane Paving.  Replace 2. With the following:

Limit pavement-edge and lane-edge drop-offs as specified in Section 401.  When paving is deeper than 1 inch and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install one of the following, as appropriate:  CW8-11 (Uneven Lanes), CW8-9 (Low Shoulder), CW14-3 (no Passing Zone), R4-1 (Do Not Pass), and R4-2 (Pass with Care).  If the Section is longer than 1/2 mile, place additional signs every 1500 feet.

3.	Fixed Objects.  Add the following:

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Replace paragraph three with the following:

If you cannot meet the preceding restrictions because of land features or lack of right-of-way, place vehicles, equipment, material stockpiles, and other items deemed by the Engineer to be fixed objects as far away as practical but at least 15 feet from the edge of traveled way, as approved by the Engineer.  Use drums or Type II barricades with flashing warning lights to delineate vehicles, equipment, material stockpiles, and other fixed objects.  These traffic control devices are subsidiary.

4.	Flagging.  Replace with the following:

Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone.  The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA (International Municipal Signal Association)

b.	Flagger Certification by ATSSA (American Traffic Safety Services Association)

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned posts at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements.  Remove, fully cover, or lay down flagger signs when no flagger is present.  Keep the flaggers' area free of encumbrances, keep the flagger vehicle well off the roadway and not close to the flagger station, so that flaggers can be seen easily.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer's written approval before flagging signalized intersections.  When you flag a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode.  Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer.  Get their written approval in advance.  Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

CR6431-051513

Add No. 10:

10.	Parallel Guardrail Terminal.  The price listed in the Traffic Control Rate Schedule, Table 643-4, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Parallel Guardrail Terminal unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations yard or as directed by the Engineer.

CR6432-110410

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with:

When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to Subsection 105-1.01, Authority of the Engineer.

Add the following after the second sentence:

In no case shall this time exceed 24 hours.

CR6431-051513

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following in the 2nd paragraph after the 2nd sentence:

Temporary crash cushions required to protect motorists from incomplete guardrail installations, as described in Section 606-5.01 is also an unauthorized lane reduction.

CR6432-110410

Add the following after the 3rd paragraph:

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

Replace Table 643-1 with the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $ 30 |
| 5,000 + | $ 40 |

CR6431-051513

643-3.08 CONSTRUCTION SEQUENCING.  Replace the last sentence with:

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Monday through Friday:  0530 hrs to 0800 hrs and 1630 hrs to 1900 hrs.

2.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs on the Monday after the holiday.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, will be allowed for motorists, except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

CR6436-041413

Add the following Subsection 643-3.10:

643-3.10 LIGHTING OF NIGHT WORK.  Illuminate the night work areas specified in Table 643-3, Night Work Illumination Level, and Area of Coverage, to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least two machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, Pavement Sweeping | At least four sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) Roads with ADTs over 10,000 2) That are controlled by portable signals or flaggers | Two Balloon lights of at least 2000 watts each located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide the lighting equipment specified in Table 643-3 or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibrations.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14-031506

Standard Modification

Add the following Subsection 643-3.11:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to requirements in this Subsection, 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic Pay Items.

E90-100410

Special Provision

Add the following Subsection 643-3.12:

643-3.12 MARINE TRAFFIC CONTROL.  Prepare and maintain an approved “Nautical Traffic Control and Public Notice Plan” in conformance with the USCG Permit stipulations. Including the following items:

- A draft “Nautical Traffic Control and Public Notice Plan” shall be submitted to the Project Engineer for approval at least 5 days prior to the preconstruction meeting.

- Contractor shall submit final “Nautical Traffic Control and Public Notice Plan” 30 days prior to construction below Mean High Water (MHW).

- Maintain a 180-ft wide by 38-ft tall navigational opening through or under the bridge between 1) May 15 and June 1 (Spring); and 2) September 15 and October 1 (Fall).

- Provide advanced notices to mariners via newspaper, radio, and posting such as warning signs on the river banks and local docks.

0001(458)/52972-110912

643-4.01 METHOD OF MEASUREMENT.

2.	Traffic Control Device Items.  Replace the second sentence with the following:

Special Construction signs are measured by the total area of legend bearing sign panel, as determined under Subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-4.

Add No. 17:

17.	Hotline Road Report.  No measurement required to provide a 24 hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.

7.	Flagging and Pilot Car.  Add the following:

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $51.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work will be paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

11.	Traffic Control.  Add the following:

The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

CR6431-051513

Add No. 17:

17.	Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14-031506

Add No. 18:

18.	High Visibility Garments.  Payment for high visibility garments for workers is subsidiary to other Pay Items.

CR6431-051513

Add No. 19:

19.	Marine Traffic Control.  Payment for marine traffic control is subsidiary to other items.

0001(458)/52972-081412

Add the following:

TABLE 643-4

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete or Steel F Shape Barrier (12.5 foot long or $8/foot for other lengths) | Each | $100.00 |
| Temporary Crash Cushion / Sand or Water Filled Barrels or Barrier (all required per end) | Each | $1250.00 |
| Temporary Crash Cushion / Redirective | Each | $2500.00 |
| Pilot Car | Hour | $70.00 |
| Watering | M-Gallon | $26.40 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $183.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $130.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Temporary Guardrail | Lineal Foot | $25.00 |

CR6431-051513

Delete Pay Item 643(12).

CR6434-110812

Replace Pay Item 643(15) with the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

CR6431-051513

- SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

CR644FOCOM-080511

Standard Modifications

644-2.02 FIELD LABORATORY.  Add the following to the end of the second sentence of the first paragraph:

through one week after Project Completion.

E44-012707REV

Replace 2.g. with the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace 6.a. with the following:

a.	Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

7.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

CR644LAB-071009

644-2.05 VEHICLES.  Delete the second and third paragraphs and substitute the following:

Pickup(LT)/Sport Utility Vehicle (SUV):  Furnish full-size, four-wheel drive vehicles, either pickup/light truck(s) with crew cabs or sport utility vehicle(s).  Provide vehicles less than three model years old, in good condition, and with less than 36,000 miles on the odometer.  Furnish all fuels, maintenance and parts, and insurance during the Department’s operation and use.

Equip each vehicle with lightbars wired into the vehicle’s electrical system with a dash mounted switch easily accessible to the vehicle operator.  Provide Code 3; Model 6005H (formerly PE 6200 LE) lightbars, or approved equal.  Approved equal equipment shall have the following characteristics:

	(4) 55 watt rotators with amber filters

	1200 flashes per minute

	(2) diamond mirrors

	55 inches in length

If you are working after October 1, provide four studded snow tires mounted on each vehicle.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use.  The Department is responsible for damage to any vehicle caused by its own negligent operation.

CR644LTSUV-033111

Add the following:

All-Terrain Vehicle (ATV):  Provide a 4x4 all-terrain vehicle (ATV), 350 cc minimum, electric start, reverse, and a ball hitch with a 500 lb capacity trailer.  The ATV must be less than two model years old, in good condition, with less than 500 miles on the odometer.  Equip, with a set of portable two-way radios with a secure transport anchor/holder and a vertically extended rotating beacon or strobe light.  All vehicle requirements for fuel, oil, maintenance, and insurance apply to the ATV.  Submit the ATV and accessory specifications including photos of the exterior to the Engineer and receive approval prior to providing the vehicle for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

Trailer (ATV):  Provide a trailer with minimum dimensions of 42”L x 30”W x 16”D, equipped with all-terrain tires or similar to those on ATV, and must have tie downs and hasp for nuclear box lock down.  All requirements for maintenance apply to the ATV.  Submit the trailer specifications including photos of the exterior to the Engineer and receive approval prior to providing the trailer for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

Aluminum Skiff:  Provide a 16 foot minimum aluminum skiff, Lund SSV or equivalent, 30 hp four stroke engine, two oars and pins.  The skiff and engine must be less than two model years old and in good working condition.  All requirements for fuel, oil, maintenance, and insurance apply to the skiff.  Submit the skiff and engine specifications including photos of the exterior to the Engineer and receive approval prior to providing the skiff for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

Snowmachine:  Contingent upon the need for winter work, provide a snowmachine with 440 cc minimum engine size, and with a 500-lb capacity sled.  The snowmachine must be less than three model years old and in good working condition.  All requirements for fuel, oil, maintenance, and insurance apply to the snowmachine.  Submit the snowmachine specifications including photos of the exterior to the Engineer and receive approval prior to providing the snowmachine for use.  Coordinate the schedule for submittal and delivery (for use) with the Engineer.

0001(458)/52972-061313

Standard Modifications

Add the following new subsection:

644-2.06 NUCLEAR TESTING EQUIPMENT STORAGE SHED.  Design, furnish and maintain a weatherproof, heated, and ventilated nuclear densometer/testing equipment storage shed for the Engineer to use exclusively throughout the Contract.  Install the building at least 15 feet from an occupied area at a location approved by the Engineer.  Install the shed before beginning of construction activities and maintain it until one week after project completion.  Provide sufficient floor area for the nuclear testing equipment and a portable electric heater to maintain a minimum room temperature of 50 °F in freezing weather.  Design the building with enough floor area to provide sufficient clearance between the equipment, heater, and combustibles.  Provide a commercial grade metal clad exterior entrance door of 3’-0” minimum width by 6’-8” height with dead-bolt lockset.  Hang the door so that hinge pins are not accessible from the exterior.  Provide the Engineer with 2 keys to control access.  Provide a 5/16” x 10 foot long welded steel security chain securely attached inside the structure with tamperproof hardware for the Engineer to secure the testing equipment.  Provide 120 volt, 60 cycle power, an interior light, and a wall receptacle for the heater.  Secure the structure to the ground with tamperproof anchors to resist wind loads and prevent unauthorized movement of the building.  The nuclear testing equipment storage shed remains the property of the Contractor.  Remove the shed from the site following project completion.

Add the following new subsection:

644-2.07 STORAGE CONTAINER.  Furnish, transport, and maintain a weather tight, lockable, steel enclosed 20 foot long X 8 foot wide X 8 foot high wooden floored container for the storage of the Department’s materials, supplies and testing equipment (but not nuclear equipment). Provide twenty equally spaced fastening points on the interior walls that are capable of securing the Department’s contents.  Door opening dimensions of the storage container shall be greater than 60 square feet.  Supply necessary equipment to lift and move container with minimal disturbance to the Department’s contents.  The container shall not be moved by skidding or hook lift.  The Contractor shall be listed as the shipper on documents listing and acknowledging receipt of the Department’s goods for shipment.

Deliver an empty and clean container to the Regional Materials Laboratory, or location acceptable to the Engineer, three weeks before transporting to the project site.  Allow 7 days for the Department to load the container.  Transport the loaded container to the project site.  Set up container at a location approved by the Engineer prior to commencing construction work.

1.	Provide electrical service and other facilities as follows:

a.	Electrical current, 120V (ac), 60 cycle on a 24 hour a day basis.

b.	Wiring system to support a 20 amp user load demand.

c.	2 GFI protected outlets conveniently spaced on the interior walls.

d.	Four 100 watt incandescent or eight 40 watt fluorescent lights located for maximum illumination.

e.	Provide a stairway with railing, built to meet the International Building Code, if there is more than 12-inch difference in floor entry and existing ground elevation.

Return the container to the Regional Materials Laboratory or location acceptable to the Engineer, upon project completion.  Allow 7 days for the Department to unload the container.  The storage container remains your property after completing the work.

E44-012707REV

Add the following subsection:

644-2.08 ENGINEERING COMMUNICATION.  Engineering Communications, minimum service includes:

a.	Three phone/facsimile lines (different phone numbers for each line)

b.	High speed internet service with modem (DSL or Cable)

CR644FOCOM-080511

Add the following subsection:

644-2.09 IMAGE DOCUMENTATION.  Provide secure "digital image" (image) documentation of construction activity at the project site(s); inclusive of an integrated, professional-grade, high resolution digital webcam image system designed for the construction industry with camera(s) and related hardware, support structure, mounting equipment, software, data transmission service, website hosting, image hosting, storage/archiving and online interface for the system with technical support and as further defined herein.

1.	Period of Service.  Begin Image Documentation one week before construction begins through one week after project completion.

2.	Ownership of Image Documentation.  All images are the copyright of the Department including still images and time-lapse movies.  The Contractor and Vendor may not use the image documentation without the written approval of the Department.

3.	Ownership of Camera(s) and Accessories.  The camera(s) is the property of the Contractor.

4.	Submittals.  Provide complete submittals (3 printed copies), to the Engineer for review and approval, at least 21 days before beginning Construction activity.  Submittals will be returned to the Contractor, within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.

Include the following:

a.	Shop Drawings.  Submit a key plan of the project site and construction to be documented with vantage points marked for location and direction of each camera. Coordinate layout and installation of cameras to avoid interference from site line obstructions such as trees and to prevent sunlight and light from fixtures entering directly into the camera lens.  Indicate camera mounting heights relative to ground and the construction being documented.  Include mounting structure, if required, and mount.

Coordinate with Engineer the locations (plan and elevation) to capture specified activity.

b.	Data Sheets and Certificates:  Submit the technical data sheets and certificates for materials including equipment and software.

c.	Maintenance:  Submit maintenance requirements with a schedule and service instructions.

d.	Qualifications:  Submit:

·	Technical Representative’s Resume:  name, education, training, and two years minimum experience providing same or similar service.  Include names of individuals and contact information for verification of service.

·	Vendor Qualifications:  Name and qualifications including five years minimum experience providing completed successful same service.  Include names of projects, project descriptions and contact information for individuals able to verify service.

5.	Materials.

a.	Camera.  Provide 	3	 camera(s) with specifications similar to those listed below with equivalent to or better performance.

CAMERA SPECIFICATIONS

|  |  | Camera(s) |  |
| --- | --- | --- | --- |
|  | # | # | # |
| Features |  |  |  |
| Imager: | 6 Megapixels, minimum | 12 Megapixels, minimum | 8 Megapixels, minimum |
| Lens: |  |  |  |
| F-Stop | f/3.5 - f/5.6 | f/3.5 - f/5.6 | f/2.7 - f/3.5 |
| Zoom: | 18 mm - 55 mm | 18 mm - 55 mm | Motorized 6 mm - 72 mm |
| Optical: | 3x min. | 3x min. | 12x min. |
| Digital: | - | - | 4x min. |
| Resolution: (minimum) |  |  |  |
| Stills: | 3088 x 2056 | 4288 x 2848 | 3264 x 2448 |
| Panoramic: | - | - | 29376 x 9792 (288 MP) |
| Streaming Video: | 640 x 480 | 640 x 480 | 640 x 480 |
| Angle of View: | Cover intended site area |  |  |
| Auto Features: | ISO, shutter, white balance, and focus |  |  |
| Compression: | JPEG, Motion JPEG |  |  |
| Communication: |  |  |  |
| IP Addressing: | Dynamic or Static |  |  |
| Types: | Provide stable communication, by one or more of the following types, dependant on the availability with the order of precedence as follows: 1. Wired Broadband (10Base-T/100Base-TX) 2. Wireless (802.11n) 3. Cellular (3G min) 4. Satellite Broadband |  |  |
| Base: |  |  |  |
| Fixed Position: | Yes/NA | Yes/NA | Yes/NA |
| Operable Motorized/Robotic: | Yes/NA | Yes/NA | Yes/NA |
|  | Pan range: 360° continuous, Tilt range: level + 30° to -90°. Adjust as required to meet the documentation requirements. |  |  |

b.	Online Access, Interface, and Online Software.  Contractor's System Vendor shall provide an online based interface and online software as managed service to allow the viewing of all still images captured and stored/archived during construction, from any location with internet access using a PC computer and/or cellular device.  The Department will not be required to own specific software or operating equipment proprietary to the system vendor to utilize any part of the Vendors service.

1)	Solution Service:  provide solution service, including technical corrective service, continuous 24 hrs, 7 days a week during period of service.

2)	Machine to machine automated maintenance of the camera system providing continual operation without interruption.

3)	Communication:

a)	Broadband/High-Speed connection (1.5 Mbps)

b)	Wi-Fi G or N // 3G cellular connection

4)	Accessibility:  Vendor, provide a web page linked to the Department's Central Region web page;

"Alaska DOT & PF Project Information",

http://www.dot.state.ak.us/stwdplng/projectinfo/central.shtml,

"Central Region Projects", Aleknagik Wood River Bridge Construction, Phase I.

Add the link to the 	Aleknagik Wood River Bridge Consturction, Phase I web page through the Engineer.  The Engineer will coordinate with the Central Region Web Manager.

a)	Public:  Provide the public with viewing access of still image documentation.

b)	Department:  Provide the Department with viewing access of the still images and live video as specified in 6) User Screen Viewing.

5)	System Navigation:  Calendar based.

6)	User Screen Viewing:  Display the Project Name and Number; Owner and Contractor Logo.  Multifunction image browsing (still images, multiple images, online time-lapse movies) per individual camera and between multiple cameras.  Additional viewing requirements include:

Public and Department.

·	Images: include time and date.

·	Navigation: calendar to navigate between documentation.

·	Weather Data:  graphical display of local weather data including long term forecast (4-7 day forecast including, sun, overcast, rain, snow, wind speed, temperature, high and low pressure systems and others).

·	Full-Screen:  screen maximizing view of images on users monitor.

·	Multiview Screen:  instant view/image of past days, weeks, months, or years at one time.

·	Time-lapse movies:  not real-time video.

·	Split Screen:  Instant play back, two or more discreet images side by side from one or more cameras.

·	Share Image Tools:  save, print, email, and post to message board or, mobile devices.

·	Map:  aerial and satellite view by Google or other.

Department Only.  Provide password protection for Department only viewing.

·	Pan-tilt-zoom control within a high-definition image and by operable motorized/robotic base when included in camera types specified.

·	Real-Time Image Browsing/Viewing:  view images and video from all cameras in the same display at the same time by day, week, year, and event.

·	Overlays:  graphical mark-up tools for detailing and creating overlays from multiple discrete images.

·	Automated progress reports: Power Point, Open Office, and PDF formats.

c.	Environmental.  Camera and supporting equipment shall be designed for continual operation in all weather conditions relative to the project site, 24 hrs each day, each day of the week.  Weather conditions including but not limited to:

1)	Wet:  water proof.

2)	Operational Temperatures:  		-50˚F to +120˚F		 (thermostatically controlled heater and blower or other as required).

3)	Winds:  110 mph (3sec gust)

4)	Fugitive Materials:  dust, rain, snow and similar.

d.	Physical.  Designed and constructed for the conditions existing at the project site.

1)	Housing:  impact resistant, water proof enclosure constructed of aluminum with stainless steel fittings and UL rated compression glands.

a)	Adjustability:  adjustable camera sled.

b)	Operational Options:  (See camera specifications for actual)

·	Fixed (pan-tilt-zoom in high-definition image provided by software interface)

·	Operable remotely controlled (pan-tilt-zoom)

2)	Viewing Window:  impact resistant with remotely controlled washer/wiper.

3)	Security:  protect against vandalism.  Lockable housing secured in-place to prevent unauthorized removal from project site.

e.	Power.  Provide continuous uninterrupted power as required by the Vendor to operate and maintain the image documentation system.

6.	Vendors.  Vendors that may meet the requirements specified in this subsection include, but are not limited to the following:

| EarthCam, Inc. 84 Kennedy Street, Hackensack, NJ 07601 Ph: 800.327.8422 Ph: 201.488.1111 Fax: 201.488.1119 www.EarthCam.net | OnsiteView, Inc. Shipping: 7901 Cameron Rd Bldg. 3, Suite 301 Austin, Tx 78754 Mail: P.O. Box 190139 Dallas, Texas 75219 Ph: 866.701.2020 Ph: 512.301.2848 www.OnsiteView.com | OxBlue Corporation 814 Bellemeade Ave. NW Atlanta, GA 30318 Ph: 888.849.2583 Ph: 404.917.0200 Fax: 404.917.0201 www.OxBlue.com | Work Zone CAM, LLC 331 W 57th St, Suite 310 New York, NY 10019 Ph: 877.966.3101 www.Workzonecam.com |
| --- | --- | --- | --- |

7.	Security.  Provide security for the image documentation and documentation system.  Prevent; interruption of the continuous documentation, damage to the documentation (data corruption, theft, or loss of the data), and damage to the system (the physical equipment, interface, software, data collection, and storage).

Maintain all images on System Vendor owned and operated secure and redundant servers, in a secure area at a location owned by the Vendor.  Minimum levels of security include multiple levels of password protection, IP address block/permission and SSL protection of the user login password.

8.	Installation and Maintenance.  Provide initial installation by the Vendor, or other as approved by the Vendor, with the option to move the camera(s) 1 times(s); and maintain the system throughout the period of service without interruption except as may be specified in this specification.  Damaged or failed parts and service complications, resulting in documentation interruption, are to be repaired, replaced, and resolved within 48 hrs from the time of interruption.

Training:  provide training for the Engineer's staff in the use of the image documentation system as described in 5.b.6) and as applicable.  Schedule the training, coordinated with the Engineer, directly after the installation is completed and the system is operational.

9.	Documentation.  Throughout the Period of Service, during the day and night, document the construction activity.  Approximate times are included herein; the approximate location of the camera(s) is provided in the Plans (plan and profile sheets coordinated with the summary sheets).  Coordinate with the Engineer, adjusting the times of documentation and actual location(s) (plan and elevation) to capture the specified activity.

For all image documentation, include the project name and number with the date and time.  The date and time for a still image would be at the time of capture and for a time-lapse movie the time from start to finish of the movie.

a.	Type.

1)	Still Image Capture.  Capture still image at regular intervals.  	Intervals = 15 minutes.

2)	Pan-Tilt-Zoom.  Real-time video and stills with high-definition image.  Available on an as-needed basis, except restricted to periods each side of the scheduled still image capture and timed out after a predetermined set time coordinated with the Engineer.

3)	Time-Lapse.  Create time-lapse movies during the Period of Service as directed by the Engineer and as follows:

Regular Interval.	Time-Lapse Movie Interval = End of Each Month.

Seasons.

	Construction season

	Winter shut-down

Milestones and Events.

·	BMP(s)

Ø	Installation:  permanent and temporary

Ø	Removal:  temporary

·	Bridge Work

	Bridge abutments

	Bridge substructure or superstructure

| Bridge Number | Bridge Name |
| --- | --- |
| 1902 | Wood River Bridge |

·	Clearing and grubbing

·	Culvert construction and installation

·	Detours

·	Erosion, Sediment and Pollution Control - Monitoring:

Ø	Beginning of construction season

Ø	During active construction

Ø	Winter shutdown

Ø	Spring thaw

Ø	Storm Event:  before, during, after

·	Establishment Period:  start of, during, at end

·	Excavation - general

·	Guardrail installation

·	Headwall construction

·	Paving

·	Pile driving

Period of Service.  At the end of the Period of Service, create a time-lapse movie of the construction activity(s) from the beginning of service to the end of service.

10.	Removal.  Remove the complete documentation system after completion of the service period.  The Engineer may direct the system to be removed prior to the end of the service period.

11.	Deliverables.  Provide the Engineer with (2) DVDs (2 copies) of:

a.	Stills:  as originally recorded in the digital camera, without alteration, manipulation, editing, or modifications, in compressed JPEG format, no more than 7 days after the service period ends.

b.	Time Lapse-Movies:  in compressed motion JPEG format, no more than 7 days after each interval, season change, milestone, event, and the Period of Service specified in 9) "Documentation."

CR644CMRA-032211

644-3.01 METHOD OF MEASUREMENT. Delete the third paragraph and substitute the following:

Vehicle (LT/SUV). For each vehicle provided. If a replacement vehicle is necessary, no additional measurement will be made.

CR644LTSUV-033111

Delete the third paragraph and substitute the following:

Vehicle (ATV).  For each vehicle provided.  If a replacement vehicle is necessary, no additional measurement will be made.

CR644ATV-033111

Add the following:

Trailer (ATV). For each trailer provided. If a replacement trailer is necessary, no additional measurement will be made.

0001(458)/52972-102412

Standard Modification

Add the following Pay Items:

Nuclear Testing Equipment Storage Shed.  By the number of storage sheds specified, to including components, installation and accepted as completed units and ready for equipment storage.

Storage Container.  By the number of storage containers specified, to including components, installed and accepted as completed units and ready for materials and equipment storage.

E44-012707REV

Add the following:

Image Documentation.  No additional measurement will be made if any part of the documentation system requires replacement.

CR644CMRA-032211

Special Provisions

Add the following Pay Item:

Aluminum Skiff. For each skiff provided. If a replacement skiff is necessary, no additional measurement will be made.

0001(458)/52972-102412

Add the following Pay Item:

Snowmachine.  For each snowmachine with sled provided.  If a replacement snowmachine is necessary, no additional measurement will be made.

0001(458)/52972-061313

644-4.01 BASIS OF PAYMENT.  Add the following:

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Pay Item 644(2) Field Laboratory.

CR644LAB-071009

Add the following:

Pay Item 644(8) Vehicle (LT/SUV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(8)	Vehicle (LT/SUV)	Each

CR644LTSUV-033111

Add the following:

Pay Item 644(9A) Vehicle (ATV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the vehicle at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(9A)	Vehicle (ATV)	Each

CR644ATV-033111

Add the following:

Pay Item 644(9B) Vehicle (UTV):

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the trailer at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and, at the end of the project, for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(9B)	Trailer (ATV)	Each

0001(458)/52972-102412

Add the following:

Pay Item 644(10) Engineering Communications.  Usage services including long distance calls made by State personnel and the Internet service provider will be reimbursed by the State.  Payment for communication usage services shall be based on paid receipts to the service provider plus 15%.

Connection fees (initial connection) local calls, providing equipment and disconnection are subsidiary to Pay Item 644(1) Field Office and as such are paid by the Contractor.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(10)	Engineering Communications	Contingent Sum

CR644FOCOM-080511

Standard Modifications

Add the following Pay Items:

Lump Sum Items. Payment for lump sum items will be made as follows:

1.	A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

2.	The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Nuclear Testing Equipment Storage Shed. At the Contract unit price to include labor, materials, tools, equipment, and supplies required to furnish and install the shed before beginning construction, to maintain it for the duration of the project and to remove the shed and electrical service after project completion.  Electrical service and utility costs are subsidiary to this item.

Storage Container.  At the Contract unit price to including labor, materials, tools, equipment and supplies required to deliver the storage container to the regional office for loading, to deliver it to the project office, to install it before beginning construction, to maintain it for the duration of the project, to remove the container and electrical service after project completion, to deliver it to the regional office for unloading, and to remove the storage container.  Electrical service and utility costs are subsidiary to this item.

Add to Pay Items:

Pay Item No.	Pay Item	Pay Unit

644(15)	Nuclear Testing Equipment Storage Shed	Each

644(16)	Storage Container	Each

E44-012707REV

Add the following:

Pay Item 644(17) Image Documentation.  At the Contract lump sum price to include labor, equipment, materials, fees, and service specified.  The lump sum price is inclusive of all cameras specified in Subsection 644-2.09.

Lump Sum Items.  Payment for lump sum items will be made as follows:

1.	A percentage of the Contract lump sum amount, to be determined by the Engineer, will be paid as full compensation for a complete, properly functioning, image documentation system including site installation(s), power, camera(s), and operating system(s), with automatic archiving, set up and interfaced with internet access via the specified device(s).

2.	The balance of the Contract lump sum amount will be prorated over the anticipated active construction Period of Service with a portion included as part of each interim payment, for maintenance, repairs, utilities, fees and for removing the complete documentation system from the site with the final payment being made after all deliverables are received as specified.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(17)	Image Documentation	Lump Sum

CR644CMRA-032211

Special Provisions

Add the following:

Pay Item 644(18) Aluminum Skiff:

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the aluminum skiff at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If the anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(18)	Aluminum Skiff	Each

0001(458)/52972-102412

Add the following:

Pay Item 644(19) Snowmachine:

1.	A percentage of the Contract unit price, to be determined by the Engineer, will be paid as full compensation for furnishing the snowmachine at the site.

2.	The balance of the Contract unit price will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, and fuel and, at the end of the project, for removing it from the site.  If the anticipated construction period changes, the final increment will be held until final payment.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(19)	Snowmachine	Each

0001(458)/52972-061313

- Special Provision

- Add the following Section:

- SECTION 645

TRAINING PROGRAM

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 6.b, 6.c, 6.d, 6.e, 6.i, 6.j and 6.l, located in the "green pages" of this document.

645-3.01 GENERAL.  The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following:  contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/OA), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 SUBCONTRACTS.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311)

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program, 2 Trainees/Apprentices	Labor Hour

S99-092112

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:

Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete No. 2.

2.	60-Day Preliminary Schedule.

Delete the first sentence of No. 3. Schedule Updates.  and substitute the following:

Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

CR261-121302

- Special Provisions

- Add the following Section:

- SECTION 647

EQUIPMENT RENTAL

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, except holidays.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.  Hours paid shall be supported by certified payroll.

647-5.01 BASIS OF PAYMENT.

Payment for Item 647(5) Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth will be paid on a contingent sum basis on a per hour basis of $150.00/hour.

This shall be full compensation for furnishing, operating, maintaining, servicing, and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(5)	Backhoe, 4WD, 1 cy Bucket, 75 hp Min, 15 ft Depth	Contingent Sum

0001(458)/52972-020312

Special Provisions

Add the following section:

SECTION 685

UTILITY CONDUITS

685-1.01 DESCRIPTION.

Furnish all labor, equipment, and materials necessary to construct utility conduits and utility pads as shown on the drawings, coordinate inspections and acceptance of the work, and provide as-built drawings as described in this section.

685-1.02 COORDINATION.

Coordinate with the Engineer to schedule inspections and gain acceptance of the utility pads by the appropriate utility company. Advise the owning utility in writing at least seven (7) calendar days in advance of actual conduit crossing work indicating both location and the time the work will be completed. The following contacts will coordinate the work :

Utility Contact No.

Nushagak Cooperative, (907) 842-5251

685-1.03 LICENSING REQUIREMENTS.

All employees of the Contractor installing PVC conduit shall possess a certificate of fitness for electrical work as defined by 8 AAC90.160, AAC 90.165, and 8 AAC 90.170. These requirements do not extend to engineering or supervisory personnel of the Contractor.

685-2.01 MATERIALS.

All equipment and material furnished under this section shall conform to the latest applicable specifications and rules of the National Electrical Manufacturers Association, American Standards Association, American Institute of Electrical Engineers, and the Federal Specifications cited hereinafter. All materials shall be new, standard equipment, and the manufacturer's latest design. No manufacturer's second or rejected materials may be used. Where two or more units of the same class of material are required, they shall be like products of the same manufacturer. Provide all PVC conduit, couplings, cements, and required hardware. All PVC shall be Schedule 80. Culverts and the type of pipe shall be smooth interior wall. Fittings - PVC conduits and fittings shall be jointed by means of a solvent welding cement to provide a watertight and root-proof joint. Pipe Caps - All conduit crossings shall be capped upon completion with caps approved by the pipe manufacturer. Supply and install conduit locator posts as shown on the drawings.

685-2.02 APPLICABLE STANDARDS AND CODES.

In order to resolve any questions on safety regulations, installation practices, and testing procedures, consult and become familiar with the applicable parts of the current editions of the following standards and codes:

I.	Alaska State Safety Code

2.	Arctic and Subarctic Construction- Utilities, U.S. Anny Corps of Engineers

3.	Electrical Facility Clearance Requirements

4.	National Electrical Code

5.	National Electrical Safety Code

6.	National Electrical Manufacturers Association

7.	Occupational Safety Health Act

8.	Underwriters Laboratories

685-3.01 GENERAL CONSTRUCTION REQUIREMENTS.

The owning utility, through the Engineer, reserves the right to suspend the utility conduit installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections. Such a suspension of work will not entitle the Contractor to extension of time for the completion of the project and will not entitle him to extra payment for costs incurred. Each utility conduit shall be installed to result in the maximum degree of reliability and maintenance-free operation and must be installed on a continuous grade from end to end in order to allow placement of the utility facilities within the conduits. Kinked ducts, inadequately supported, protected or swabbed ducts, and ducts that are carelessly jointed are not reliable and therefore, unacceptable. At the Contractor's expense, remove and replace any installation that is not accepted by the utility company as required to gain acceptance of the work.

If construction or excavation requires the removal of any existing privately owned facilities on the provided easements, coordinate with the owner for reestablishing lawns, driveways, parking lots, etc., at unit bid prices. Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two weeks.

685-3.02 SURVEYING AND STAKING.

Locate the stake all conduits at the elevations indicated on the plans. Schedule a physical inspection of all line and grade prior to placing conduits. All conduit crossings shall be constructed to within an allowable vertical tolerance of I inch and a horizontal tolerance of 2 inches from the indicated plan location.

685-3.03 CROSSING EXCAVATION.

Identify and locate all underground utilities, and take proper care not to damage them. Call for field utility location in accordance with subsection I 05-1.06, Cooperation with Utilities. Do not begin trench excavation until all personnel, materials, and equipment are present to complete the work in the most expedient manner. Complete all trenching and backfill, operations in conformance with safety requirements.

Provide a foundation of undisturbed non-frost susceptible material for the conduits. All conduits shall be bedded in compacted clean sand. Where directed by the Engineer, over excavate native material to provide a minimum of 24 inches of non-frost susceptible material under the conduits. Level the bottom of the trench to provide a uniform support for conduits. Trench depth shall be as shown on the plans, and as staked in the field. Dig trenches of the necessary width to properly use compaction equipment and place conduits. Compact foundation material and trench backfill in 8-inch lifts to 95 percent of the maximum density in accordance with subsection 203-3.03, Embankment Construction, and subsection 203-3.04, Compaction with Moisture and Density Control, up to the bottom of the roadway structural section. Place warning tape at the depths shown on the Plans. Outside and below the structural section, place native backfill material in layers and compacted as approved by the Engineer. Do not permit construction activity or traffic across any trench until a minimum depth of 3 feet of fill above the conduits has been placed and compacted. Provide written notification to the owning utility when a utility crossing is ready for an acceptance inspection at least 24 hours in advance. The Contractor, the Engineer, and the appropriate utility company shall mutually agree upon a time for the inspection. Failure of the utility company to attend a prearranged inspection shall not relieve the requirement to have the work accepted by the utility company. However, if additional costs are incurred due to a utility company's failure to attend an agreed-upon inspection, you may submit a request for a contract change order in accordance with subsection 105-1.17, Claims.

685-3.04 CONDUITS.

The ends of all conduits, whether shop or field but, shall be reamed to remove burrs and rough edges. Cuts shall be made square and true so that the ends will butt together for the full circumference.

Place locator post at the ends of all conduits. The clearance between various duct or conduit systems shall be as large as possible to permit maintenance of the system without damage to other parallel systems. A 3/16-inch diameter polyethylene or polypropylene pull rope, with a minimum breaking strength of 700 pounds, shall be left in each conduit with 3 feet of rope projecting beyond each end of the conduit. Securely tie the rope to the conduit cap in a manner approved by the Engineer. All pull ropes shall be new and without splices.

Determine the most expedient method to complete each utility conduit installation and obtain the Engineer's approval for the plan. All work across the roadway shall be accomplished in accordance with Section 643, Traffic Maintenance.

685-3.10 AS-BUILT DRAWINGS.

Provide an as-built drawing for each crossing location. The as-built drawings shall consist of a redlined markup of the plan sheets, as well as Contractor-furnished cross-section sheets, including the installed station and offset and elevations at each end and at the center. Reference the information to established survey ·monuments. The Engineer's approval of as-built drawings is required to gain acceptance of the conduit crossing.

685-4.01 METHOD OF MEASUREMENT.

Section 109 and as follows:

Utility Conduits is a lump sum item and will not be measured separately for payment. The Engineer’s acceptance constitutes method of measurement. All labor material and equipment required to construct the utility conduits will be subsidiary to Item 685 (5) Utility Conduits and will not be measured separately for payment.

685-5.01 BASIS OF PAYMENT.

Payment for utility conduits and utility pads will be full compensation for all coordination, labor, equipment, and materials necessary to complete this work including necessary fittings and plugs, pull wires, locator posts, marking tape, and as-built drawings. Bedding material is subsidiary. Embankment materials will be paid for under their respective pay items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

685(5)	Utility Conduits	Lump Sum

0001(458)/52972-020312

Special Provisions

Replace Section 701 with the following:

SECTION 701

HYDRAULIC CEMENT AND SUPPLEMENTARY CEMENTITIOUS MATERIALS

701-1.01 GENERAL. Meet the following general requirements for all cementitious materials furnished:

Before using, retest Portland cement stored longer than 3 months in bags or 6 months in bulk for compressive strength, time of setting, and loss on ignition according to AASHTO M 85. Store separately different types or brands of cementitious materials, or cementitious materials from different mills.

Protect cementitious materials from dampness during shipment and storage. Do not use partially set cement or cement which contains caked lumps. Do not use cement salvaged from discarded or used bags.

701-2.01 PORTLAND CEMENT. Meet AASHTO M 85, Type I, II, or III including the low-alkali cement requirement shown in Table 2.

701-2.02 BLENDED HYDRAULIC CEMENT. Meet AASHTO M 240, Type IP, or Type IS. Report the weight of pozzolan and ground granulated blast furnace slag as percent of weight of the total cementitious material.  Do not vary the pozzolan and ground granulated blast furnace slag constituent content from the certified value more than ±5 percent by weight of the total cementitious material. Limit pozzolan in Type IP to fly ash.  Meet the replacement limits in Table 701-1

- TABLE 701-1

BLENDED HYDRAULIC CEMENT LIMITS

| Cement Type | Constituent | Percent of Total Cementitious Material by Weight |
| --- | --- | --- |
|  |  | Maximum |
| Type IP | Fly Ash | 35% |
| Type IS | Slag cement | 40% |

701-2.03 GROUT. Non-shrink, non-corrosive, non-metallic, cement-based grout meeting ASTM C 1107, except develop a 28-day compressive strength of at least 9,000 psi when tested according to AASHTO T 106 or ASTM C 109.

701-2.04 FLY ASH. Meet AASHTO M 295, Class C or Class F, including optional chemical requirements as set forth in Table 2.

701-2.05 GROUND GRANULATED BLAST-FURNACE SLAG. Meet AASHTO M 302, Grade 100 or Grade 120.

701-2.06 SILICA FUME. Meet AASHTO M 307.

701-2.07 DS GROUT. Use drilled shaft (DS) grout  that conforms to the following requirements:

1.	Portland Cement Type I or Type II cement meeting the requirements of Subsection 701-2.01.

2.	Fine Aggregate: Use fine aggregate meeting Subsection 703-2.01, except 100 percent passing the No. 4 sieve.

3.	Potable Water: Use water meeting the requirements of Subsection 712-2.01.

4.	Proportioning: Mix grout in proportions using at least 564 lbs/yd3 of Portland cement, fine aggregate, and with enough water to produce a flowable mixture.  Do not exceed 67 gal/yd3 of water.

Thoroughly mixed DS grout before injecting into soil surrounding drilled shaft casing and CSL tubes.

701-2.08 POST-TENSION GROUT. Use pre-packaged thixotropic grout formulated specifically for bonded post-tensioned concrete structures in aggressive exposures.

Ship grout in weather proof packages, plainly marked with the name, weight, and volume of the grout, together with the lot number, date of manufacture, mixing instructions, and the name and address of the manufacturer.

Protect grout against dampness. Do not use grout that has become partially set or which contains lumps of caked grout. Do not use grout salvaged from discarded or used bags. Do not use grout with a total time from manufacture to usage in excess of six months unless the manufacturer tests and certifies the product meets the requirements in Table 701-1.

Batch grout using the entire contents of each bag in accordance with all of the manufacturer’s written recommendations and instructions.

1.	Materials. Use grout that conforms to the following requirements:

a.	Portland Cement. Type I or Type II cement meeting the requirements of Subsection 701-2.01.

b.	Potable Water. Use water meeting the requirements of Subsection 712-2.01.

c.	Fly Ash. Class C or Class F fly ash meeting the requirements of Subsection 711-2.03. Limit fly ash content to a maximum of 20% by weight of Portland cement.

d.	Ground Granulated Blast Furnace Slag. Grade 120 slag conforming to ASTM C 989. Limit blast furnace slag content to a maximum of 40% of the weight of Portland cement.

e.	Silica Fume. Silica fume conforming to ASTM C 1240. Limit silica fume content to a maximum of 15% of the weight of Portland cement.

f.	Set Control and Water-Reducing Admixtures. Type D, Type F, and Type G admixtures conforming to AASHTO M 194. Limit Type F and Type G admixtures to 45 oz. per 100 pounds of Portland cement.

g.	Air Entraining Admixtures. Do not use grout with air entraining admixtures.

h.	Expansion Causing Admixtures. Do not use grout with expansive cement or expansion causing admixtures that contain aluminum powder or components that produce hydrogen, carbon dioxide or oxygen gas.

i.	Corrosion Inhibitor Admixtures. Do not use grout with corrosion inhibitor admixtures.

j.	Pumping Aid Admixtures. Do not use pumping aid admixtures.

2.	Physical Properties. Use grout that satisfies the requirements in Table 701-2.

TABLE 701-2

POST TENSION GROUT

| Property | Requirements | Test Method |
| --- | --- | --- |
| Total Chloride Ions | Max. 0.08% by weight of cementitious materials | ASTM C 1152 |
| Setting Time | Min. 3 hours Max. 12 hours | ASTM C 953 |
| Strength | Min 3000 psi after 7 days Min 5000 psi after 28 days | ASTM C 942 |
| Permeability @ 28 days | Max. 2500 Coulombs at 30 V after 6 hours | ASTM C 1202 |
| Volume Change | Maximum 0.0% after 24 hours Maximum +0.2% after 28 days | ASTM C 1090 (modified)* |
| Expansion | ≤ 2.0 % for up to 3 hours | ASTM C 940 |
| Fluidity | - Immediately after mixing: Min. 9 sec. Max. 20 sec. - 30 minutes after mixing: Max. 30 sec. | ASTM C 939 (modified)** |
| Wick Induced Bleed | Max 0.0% | ASTM C 940 (modified)*** |
| Wet Density | Report maximum and minimum obtained test value in pounds per cubic foot | ASTM C 185 |

*	Modify ASTM C1090 to include verification at both 24 hours and 28 days.

**	Modify the ASTM C 939 test by filling the flow cone to the top instead of to the standard level. The efflux time is the time to fill a one liter container placed directly under the flow cone.

***	Modify ASTM C940 to conform with the wick induced bleed test as follows:

(a)	Use a wick made of a 20-inch length of ASTM A416 seven-wire 1/2 inch diameter strand. Wrap the strand with 2-inch wide duct or electrical tape at each end prior to cutting to avoid splaying of the wires when it is cut. Degrease (with acetone or hexane solvent) and wire brush to remove any surface rust on the strand before temperature conditioning.

(b)	Condition the dry ingredients, mixing water, prestressing strand and test apparatus overnight at 65° F to 75° F.

(c)	Mix the conditioned dry ingredients with the conditioned mixing water and place 800 ml of the resulting grout into the 1,000 ml graduate cylinder. Measure and record the level of the top of the grout.

(d)	Completely insert the strand into the graduated cylinder. Center and fasten the strand so it remains essentially parallel to the vertical axis of the cylinder. Measure and record the level of the top of the grout.

(e)	Store the mixed grout at the temperature range listed above in (b).

(f)	Measure the level of the bleed water every 15 minutes for the first hour and hourly for two successive readings thereafter.

(g)	Calculate the bleed water, if any, at the end of the three hour test period and the resulting expansion per the procedures outlined in ASTM C940, with the quantity of bleed water expressed as a percent of the initial grout volume. Note if the bleed water remains above or below the top of the original grout height. Note if any bleed water is absorbed into the specimen during the test.

701-2.08 CERTIFICATION. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 709-2.07.6;

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

DOT BRIDGE-012012

- SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

(Percent Passing By Weight)

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, V and R mixtures.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet the following requirements:

| Description | Specification | Type IIA | Type I, IIB, III | Type IV | Type V, R |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, Min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP 61 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Flat-Elongated Pieces, max % | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| 1:3 |  | 20 | - | - | 20 |
| Absorption, max. % | AASHTO T 85 | 2.0 | 2.0 | 2.0 | 2.0 |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type II, Class A mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate.

Aggregate for Type IV, V, and R mixes:

	do not blend back natural sand

	shall be non-plastic as determined by WAQTC FOP for AASHTO T 90

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

(Percent Passing by Weight)

| Sieve | Gradation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V | Type R |
| 1 inch | 100 | - | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 | 100 |
| 1/2 inch | 60-84 | 75-90 | 100 | 100 | 65-90 | 70-100 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | ≤ 45 | 20-32 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | ≤ 35 | 15-25 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | ≤ 25 | 10-20 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | ≤ 20 | 7-15 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | ≤ 12 | 5-12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 4-8 | 3-8 | 4-10 |

Note:

1.	No tolerance is allowed beyond the Broad Band Limits of the No. 200 Sieve.

2.	For Type R, the mix design gradation JMD shall provide a minimum of 8% difference of percent passing the No. 4 and the No. 8 sieve.

CR7031-053112

703-2.07 SELECTED MATERIAL. Add the following:

- Type D. Earth, sand, gravel, rock or combinations thereof containing no muck, frozen material, roots, sod, or other deleterious matter, with a plasticity index not greater than 6 as tested by WAQTQ FOPs for AASHTO T 89 and T 90, and with no more than 15% by weight passing the No. 200 sieve, determined on the minus 3-inch portion of the sample, as tested by WAQTC FOP for AASHTO T 27 and T 11.

0001(458)/52972-072612

Add the following subsection:

703-2.13 STRUCTURAL FILL. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

TABLE 703-9

REQUIREMENTS FOR GRADING FOR STRUCTURAL FILL MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3 in. | 100 |
| 3/4 in. | 75-100 |
| No. 4 | 35-65 |
| No. 50 | 0-50 |
| No. 200 | 0-6 |

Add the following subsection:

703-2.14 AGGREGATE FOR ABRASIVE FINISH. Crushed sand consisting of sound, tough, durable rock of uniform quality, oven dried, and stored in moisture-proof bags. Free from clay balls, vegetative matter, or other deleterious matters (AASHTO T 112). Not coated with dirt or other finely divided mineral matter. Meet the grading requirements of Table 703-10 (WAQTC FOP for AASHTO T 27/T 11).

TABLE 703-10

REQUIREMENTS FOR SAND FOR ABRASIVE FINISH

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| No. 8 | 100 |
| No. 20 | 0-5 |

DOT BRIDGE-082912

Special Provisions

Replace Section 705 with the following:

SECTION 705

JOINT MATERIALS

705-2.01 JOINT FILLERS. Meet AASHTO M 213.

705-2.02 JOINT SEALER.

Silicone Joint Sealer	ASTM D 5893

Hot Pour Joint Sealer (Asphalt)	AASHTO M 324, Type IV

Hot Applied Joint Sealer (Concrete)	AASHTO M 282

Hot Pour Joint Sealant (Concrete, Fuel-Resistant)	ASTM	D 3581

705-2.03 BRIDGE SEAL.

1.	Preformed Strip Seals and Compression Seals. Use preformed seals. Use preformed material meeting ASTM D 3542.

Submit five copies of a certified test report for preformed seal materials.

2.	Silicone Expansion Joint Sealant. Use formed-in-place seals composed of 100 percent silicone meeting the requirements of ASTM D 5893, Type SL (Self-Leveling) for horizontal joints and ASTM D 5893, Type NS (Non-Sag) for curb, rail, and other vertical joints. Do not use acid cure sealants.  Ensure the silicone sealant is compatible with the surface to which it is applied. Use a backer rod meeting ASTM C 578 when the joint width is 1/2 inch or greater.

705-2.04 JOINT MORTAR. Use a mixture of one part portland cement and two parts approved sand with water as necessary to obtain the required consistency. Use mortar within 30 minutes after its preparation.

705-2.05 FLEXIBLE WATERTIGHT GASKETS.

1.	Ring gaskets for rigid pipe and precast manhole sections meeting AASHTO M 198.

2.	Ring gaskets for flexible metal pipe meeting ASTM C 443. Continuous flat gaskets for flexible metal pipe meeting ASTM D 1056, Grade 2B3. Use gaskets with a thickness 1/2 inch greater than the nominal depth of the corrugation for bands with projections or flat bands and 3/8 inch for corrugated bands.

705-2.06 EXPANDED POLYETHYLENE. Use closed-cell expanded polyethylene planks with a density of 2.2 +/- 0.5 lb/ft3 as determined by ASTM D3575 and with a maximum compressive deflection of 50% at 17 psi +/- 5 as determined by ASTM D3575.

DOT BRIDGE-012012

SECTION 706

CONCRETE AND PLASTIC PIPE

Standard Modifications

706-2.06 PLASTIC PIPE.  Delete the first sentence and replace with the following:

Semi-rigid, smooth-wall pipe meeting the following:

E63-072808

Special Provisions

Replace Section 709 with the following:

SECTION 709

REINFORCING STEEL AND WIRE ROPE

709-2.01 REINFORCING STEEL.

1.	Reinforcing Steel Bars. Furnish deformed steel bars of the type, grade, and size as specified. For steel reinforcing bars used in bridge structures, furnish bars meeting ASTM A 706. For all other structures, furnish bars meeting AASHTO M 31, Grade 60.

2.	Headed Reinforcing Steel Bars. Furnish headed steel bars meeting the requirements of ASTM A 970, Class HA. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

3.	Epoxy-Coated Reinforcing Steel Bars. Furnish epoxy-coated steel bars meeting the requirements of AASHTO M 284. Coat epoxy-coating reinforcing steel in an epoxy coating applicator plant certified in accordance with the Concrete Reinforcing Steel Institute (CRSI) Voluntary Certification Program. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

4.	Steel Wire. Furnish plain steel wire of the size specified that meets the requirements of AASHTO M 32.

5.	Steel Bar Mats. Furnish deformed steel bar mats of the type, grade, size, and spacing as specified. Unless otherwise noted, furnish steel bar mats meeting the requirements of AASHTO M 54, Grade 60.

6.	Steel Welded Wire Fabric. Furnish plain steel welded wire fabric of the size and spacing specified that meets the requirements of AASHTO M 55.

7.	Epoxy-Coating Patch Material. Furnish epoxy-coating patch material meeting the requirements of AASHTO M 317.

8.	Zinc-coated Galvanized Reinforcing Steel Bars.  Use hot-dip galvanized according to ASTM A767, Class I.  Galvanize the bars after fabrication.  Do not bend reinforcing steel after galvanizing. Repair galvanized bars in accordance with ASTM A 780 Annex A1 or Annex A3.

9.	Certification. Submit five copies of a certified test report covering chemical and physical tests conducted on all reinforcing steel to the Department for the material in each shipment.

709-2.02 WIRE ROPE OR WIRE CABLE. Meeting AASHTO M 30, 3/4 inch Type 1, Class A.

DOT BRIDGE-012012

SECTION 710

FENCE AND GUARDRAIL

Special Provisions

710-2.03 CHAIN LINK FABRIC.

In the 1st sentence between the parenthesis, replace "Class D" with the following:

(Class C or D coating)

CR7101-110410

Standard Modification

Delete Subsection 710-2.04 METAL BEAM RAIL and replace with the following:

710-2.04 METAL BEAM RAIL.  Meet AASHTO M 180-00, Class A, Type II.  Galvanize the rail per ASTM A653 after factory roll formed and punched.

E83-100410

Delete Subsection 710-2.06 GUARDRAIL POSTS AND BLOCKS and replace with the following:

710-2.06 GUARDRAIL POSTS AND BLOCKS.  Furnish posts and blocks, as specified, meeting the following requirements.

1.	Wood Posts and Blocks.  Use timber with a stress grade of 1200 psi or more.  Testing must meet the standards of the West Coast Lumber Inspection Bureau.  Use timber for posts and blocks that is either rough sawn (unplaned) or S4S with nominal dimensions indicated.  Allowable size tolerance of rough sawn blocks in the direction of the bolt holes is  1/4 inch.  Only one combination of post and block finish may be used for any one continuous length of guardrail.  Treat all timber to meet Section 714.

2.	Steel Posts and Blocks.  Meet the section and length specified or shown on the Plans.  Use copper bearing steel when so specified.  Use steel meeting the requirements of ASTM A 36 and galvanized per ASTM A 123.

3.	Synthetic Blocks.  Product made from alternate materials may be used if accepted by the FHWA for use on the National Highway System.

E84-100410

Delete Subsection 710-2.11 GUARDRAIL TERMINALS and replace with the following:

710-2.11 GUARDRAIL TERMINALS.  Meet coating requirements of AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding, and riveting.  Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail.  Provide terminals that pass NCHRP 350 or MASH Test Level 3 and meet the following requirements:

1.	Controlled Release Terminal.	Meet the requirements of Standard Drawing G-25.

2.	Parallel Terminal.

a.	Requirements:

(1)	Crashworthiness:  Provide terminals that pass NCHRP 350 or Mash Test Level 3.

(2)	Length:  50 feet.

(3)	End Offset:  0 to 2 feet (25:1 or flatter straight taper) offset end as shown on the plans.

(4)	Posts:  Use posts that are:

(a)	Steel post with hinge or

(b)	Yielding or breakaway steel post in steel tube

b.	Acceptable models include the following or approved equivalent:

(1)	Sequential Kinking Terminal (SKT) manufactured by Road Systems, Inc., 3616 Old Howard County Airport, Big Spring, Texas 79720, Telephone (432) 263-2435.

(2)	Extruder Terminal (ET-Plus) manufactured by Trinity Highway Products, L.L.C., 950 West 400 South, Centerville, Utah 84014, Telephone (801) 292-4461.

c.	Install AASHTO M 268, Type III, IV, or V retro-reflective sheeting (2.0 square feet, minimum) on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal.

3.	Buried in Backslope Terminal.  Meet the requirements of Standard Drawing G-15.

E85-100410

Special Provisions

Replace Section 711 with the following:

SECTION 711

CONCRETE CURING MATERIALS

AND ADMIXTURES

711-2.01 CURING MATERIALS.

Burlap Cloth made from Jute or Kenaf	AASHTO M 182, Class 4

Sheet Materials for Curing Concrete	AASHTO M 171

Liquid Membrane-Forming

Compounds for Curing Concrete	AASHTO M 148, Type I-D Class B, except do not use compounds containing linseed oil.

711-2.02 CHEMICAL ADMIXTURES.

Air-Entraining Admixtures	AASHTO M 154

Water-Reducing Admixtures	AASHTO M 194, Type A

Set-Retarding Admixtures	AASHTO M 194, Type B

Set-Accelerating Admixtures	AASHTO M 194, Type C

Water-Reducing and Set-Retarding Admixtures	AASHTO M 194, Type D

Water-Reducing and Set-Accelerating Admixtures	AASHTO M 194, Type E

Water-Reducing Admixtures	AASHTO M 194, Type F

High Range Water-Reducing and Set-Retarding Admixtures	AASHTO M 194, Type G

Specific Performance Admixtures	ASTM C 494, Type S

DOT BRIDGE-012012

Special Provisions

Replace Section 712 with the following:

SECTION 712

MISCELLANEOUS

712-2.01 WATER. Use water in mixing or curing concrete that is clean and free of oil, salt, acid, alkali, sugar, vegetable or other substances injurious to the finished product. Meet the suggested requirements of AASHTO T 26. Use mix water that contains less than 500 parts per million of chlorides as CI or of sulphates as SO4. Water known to be of potable quality will not require testing. Where the source of water is relatively shallow, enclose the intake to exclude silt, mud, grass, or other foreign materials.

Use water for irrigating trees, plants, and seeded areas that is free of elements harmful to plant growth.

712-2.02 CALCIUM CHLORIDE. AASHTO M 144.

712-2.03 LIMESTONE. Use limestone containing not less than 85% of calcium and magnesium carbonates. Meet the standards of the Association of Official Agricultural Chemists. Meet the following gradation for agricultural ground limestone suitable for application by a fertilizer spreader:

TABLE 712-1

| Sieve | Percent Passing, by Weight, Min. |
| --- | --- |
| No. 10 | 100 |
| No. 20 | 90 |
| No. 100 | 50 |

Use soluble or ground limestone in a hydraulic sprayer. Ground limestone must permit complete suspension of insoluble particles in water.

712-2.04 PRECAST CONCRETE CURBING. Portland cement concrete curb units conforming to the lengths, shapes, and other details of the Plans. Use steel reinforcement, where shown on the Plans, meeting Subsection 709-2.01.

Furnish a depressed or modified section of curb, when shown on the Plans, for driveways, crossing, closures, or for other reasons.

712-2.05 PRECAST CONCRETE MANHOLE SECTIONS. Meet AASHTO M 199, except that the absorption test will not be required. Reject units with cracks and honeycombed or patched areas in excess of 30 square inches.

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS. Conform to the plan dimensions and to the following materials requirements.

Gray iron castings	AASHTO M 105, Class 35 B.

Carbon-steel castings 	AASHTO M 103. Grade is optional.

Structural steel 	ASTM A 709

Galvanizing	AASHTO M 111

Malleable iron castings 	ASTM A 47. Grade is optional.

712-2.07 CORRUGATED METAL UNITS. Meet AASHTO M 36. When bituminous coating is specified, meet AASHTO M 190, Type A.

712-2.08 GLASS BEADS. Meet AASHTO M 247 Type 1, with a moisture resistant coating.

712-2.13 GABIONS.

Wire Mesh: Use 11 gage minimum wire, except that the selvedge may be heavier. Meet or exceed ASTM A 641 medium hardness and tensile strength; Class 3 coating. Furnish at least one sample of each component of the mesh for testing.

Use mesh with 4-inch openings in the longest dimension.

Use wire mesh that is designed to be nonraveling. It must resist pulling apart at any of the connections forming the mesh when a single wire strand in a section of mesh is cut.

Tie and Connecting Wire: Conform to the same specifications as wire used in the mesh except that it may be not more than 2 gauges smaller. Supply sufficient quantity for securing and fastening all edges of the gabion baskets and diaphragms, for fastening adjacent gabion baskets together, and to provide cross connecting wires in each gabion cell as specified below.

Gabion Baskets. Supply baskets, as specified, in various lengths and heights. Make the lengths multiples (2, 3, or more) of the horizontal width. Furnish all gabion baskets in uniform width of not less than 24 inches or more than 48 inches.

Fabricate the sides, ends, lid, and diaphragms for field assembly into a rectangular basket of the required size. Construct gabions as a unit. The base, ends and sides are either to be woven into a single unit or one edge of these members connected to the base so that strength and flexibility at the point of connection is at least equal to that of the mesh.

Diaphragms. Where the length of the gabion exceeds its horizontal width, divide the gabion equally with diaphragms of the same mesh and gage as the gabion basket and make compartments of a length approximately equal to horizontal width. Furnish the gabion with the necessary diaphragms secured in proper position on the base section so that no additional tying at this juncture is necessary.

Securely selvedge or bind all perimeter edges so that the joints formed by tying the selvedges have approximately the same strength as the body of the mesh.

712-2.17 EPOXY FOR BONDING DOWELS. Use an epoxy cartridge system that consists of the following:

1.	A bonding material that is a two-component epoxy contained in a cartridge having two separate chambers

2.	An applicator that is a special dispensing gun having a replaceable static mixing nozzle.

3.	Use an epoxy cartridge system appropriate for the service temperature and ambient concrete temperature at the time of installation.

Epoxy cartridge systems are subject to the approval of the Engineer. Use epoxy cartridge systems that meet the requirements of the “Acceptance Criteria for Adhesive Anchors in Concrete and Masonry Elements,” AC58, by the International Code Council Evaluation Service (ICC-ES). Meet the suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic qualification of these acceptance criteria. Approval of epoxy cartridge systems is contingent upon the Contractor submitting to the Engineer one sample of each type of epoxy cartridge system, manufacturer’s installation instructions, and certified results of tests, either by a private testing laboratory or the manufacturer, indicating compliance with the above requirements.

Unless shown otherwise, do not use epoxy cartridge systems when:

1.	Temperature of concrete is above 110°F or below 40°F

2.	There is a likelihood of fire

3.	Coated bars or rods are specified unless the embedment depth is increased by 50%

Provide epoxy cartridges clearly and permanently marked with the manufacturer’s name, model number of epoxy cartridge system, manufacturing date, and lot number. For each carton of epoxy cartridges, provide the manufacturer’s recommended installation procedures, minimum cure time, and such warning or precautions concerning the contents as may be required by State or Federal Laws and Regulations.

Provide a certificate of compliance with each shipment of the epoxy cartridge system, regardless of which epoxy product is furnished, as provided in Section 106-1.05. Provide a certificate of compliance to the Engineer that the repair procedure using the epoxy cartridge system was completed in conformance with the manufacture's recommendations.

712-2.18 LOW-VISCOSITY RESIN. Meet AASHTO M 235, Type IV, Grade 1, with the following revisions:

Amend Table 1 as follows:

Replace "2.0[20]" with "0.105[1.05]" in the row labeled "Grade 1, max".

712-2.19 CONCRETE ANCHOR INSERTS.

- Coil Anchor Inserts. Use 1 inch diameter galvanized inserts with a minimum safe working load of 7,500 pounds.  Hot-dip galvanize anchors according to AASHTO M 111 or AASHTO M 232.

- Threaded Anchor Inserts. Use 1 inch diameter galvanized ferrule inserts with a minimum safe working load of 6,500 pounds.

DOT BRIDGE-012012

Special Provisions

Replace Section 715 with the following:

SECTION 715

STEEL FOR PILES

715-2.01 SCOPE. Steel used for Structural Steel Piling and Sheet Piling.

715-2.02 GENERAL REQUIREMENTS. Furnish steel piles of the dimensions, weights, cross-sections, and grades specified. Satisfy the impact test requirements of Subsection 716-2.02. Meet the following:

- Structural Steel HP Piling. Furnish "HP" shape piles meeting ASTM A 709, Grade 50T3.

- Structural Steel Pipe Piling. Furnish 2’ 0” and smaller in diameter pipe piles meeting one of the following; except 6 inch diameter structural steel pipe shall meet ASTM A53 Grade B, Schedule 80.

a.	American Petroleum Institute (API) 5L X52 PSL2.

b.	ASTM A 709, Grade 50T3 fabricated and monogrammed according to API 2B

c.	ASTM A 709, Grade 50T3 fabricated according to the following:

(1)	General. Fabricate pipe piling using coiled steel with one helical seam weld. Use skelp material that does not contain repair welds. Use skelp having a width not less than 0.8 times the outside diameter of the pipe and not greater than 3.0 times the outside diameter of the pipe. Form pipe when the steel temperature is below 400°F. Locate junctions of skelp end welds and the helical seam welds at distances greater than 1.0 times the outside diameter of the pipe from the pipe ends and at distances greater than 5.0 times the outside diameter of the pipe from other junctions of skelp end welds and helical seam welds.

(2)	Welding. Use complete joint penetration welds produced by the automatic submerged–arc welding process, the automatic gas metal-arc welding process, or a combination of both processes. Perform welding according to Section 504.

(3)	Welding Inspection. Perform welding inspection according to AWS D1.1. Provide visual inspection of welds on the inside surfaces and outside surfaces of the pipe.

(4)	Non-Destructive Examination. Randomly examine 10 percent of the total length of helical seam welds and skelp end welds. Examine welds by performing one or more of the following tests:

(a)	Radiographic testing according to the requirements of AWS D1.1 Section 6, Part E with Subsection 6.12.3 of AWS D1.1.

(b)	Ultrasonic testing according to the requirements of AWS D1.1 Section 6, Part F with Subsection 6.13.3.1 of AWS D1.1.

If more than 10 percent of the welds examined are defective, examine a second random sample of 25 percent of the total length of welds. If more than 10 percent of the welds examined in the second sample are defective, examine 100% of the total length of welds.

Repair all weld defects.

(5)	Destructive Examination. Perform destructive examination on specimens from finished pipe of each specified outside diameter, wall thickness, steel type, and grade. Examine specimens at a frequency of at least one set of tests for each lot representing 2000 linear feet of finished pipe or once per week during each production run, whichever occurs first. Do not use specimens containing repaired welds.

(a)	Tensile Tests. Meet the specified tensile requirements for yield strength, tensile strength, and elongation. Perform tension tests according to ASTM A 307 using one base metal specimen and two weld specimens taken at 90° to the length of the weld with the weld across the center of the sample. For base metal specimen, determine and report yield point, yield strength, tensile strength, and elongation. For weld test specimens, determine and report tensile strength.

Each lot of pipe will be considered to meet the tensile requirements if the base metal test results exceed the specified yield strength, tensile strength, and elongation and the weld test results exceed the specified tensile strength result.

(b)	Bend Tests. Perform transverse side bend tests according to ASTM E 190. Each lot of pipe will be considered to meet the bend test requirements if the no cracks occur in the specimen.

(6)	Tolerances. Meet the following tolerances:

(a)	Roundness. Limit the difference between the major and minor outside diameter to 1 percent of the specified outside diameter of the pipe or 1/4 inch, whichever is less.

(b)	Circumference. Limit the outside circumference to 1 percent of the nominal outside circumference of the pipe or 1/2 inch, whichever is less.

(c)	Straightness. Do not deviation from a straight line parallel to centerline of the pile more than ±1/8 inch per 10 feet of length, but not to exceed 3/8 inch.

(d)	Length. ±1-1/2 inch per 10 feet of length.

(7)	Defects. The Engineer may reject piles containing surface defects. The depth of the surface defect will be measured as the gap between the lowest point of the defect and a prolongation of the original contour of the pipe. Use of piles containing surface defects may be authorized according to the following requirements based on the depth of the surface defect:

(a)	If the surface defect is not greater than 5 percent of the wall thickness in depth, the defect need not be repaired.

(b)	If the surface defect is deeper than 5 percent, but not greater than 7 percent, of the specified wall thickness, grind smooth the surface defect. Remove abrupt changes in contour, but do not reduce the thickness in the ground area more than 7 percent of the specified wall thickness.

(c)	If the surface defect is deeper than 7 percent, but not greater than 20 percent, of the specified wall thickness, repair the defect by welding according to Section 504.

(d)	If the surface defect is deeper than 20 percent of the specified wall thickness, repairs will not be permitted and the pile will be rejected.

3.	Pile Tip Reinforcing. Use pile tip reinforcement conforming to the requirements of ASTM A 27 Grade 65-35 or ASTM A 148 Grade 90-60. Make each pile tip in one piece of cast steel. Weld tip reinforcing to the piles in conformance with the manufacturer's written directions.

4.	Structural Steel Sheet Piling. Furnish sheet piles meeting AASHTO M 202. Fabricate structural steel sheet pile sections with ASTM A572, Grade 50 steel.

715-2.03 CERTIFICATION. Furnish 5 copies of a certified test report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 715-2.03.6;

8.	an affidavit, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

For pipe manufactured to API 5L, submit a certified test report according to API 5L SR15.1.

715-2.04 MARKING. Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying certified test report.

For helical welded pipe piles, mark each pipe on the inside surface and outside surface of both ends indicating: the fabricators name, type of steel, grade of steel, steel heat number, welding process, total pipe weight or weight per lineal foot of pipe, length, nominal outside diameter, and

DOT BRIDGE-012012

Special Provisions

Replace Section 716 with the following:

SECTION 716

STRUCTURAL STEEL

716-2.01 SCOPE. Structural steel for highway bridges and other structural purposes.

716-2.02 GENERAL REQUIREMENTS. Meet the following:

1.	General requirements for delivery of rolled steel plates,

shapes, sheet piling, and bars for structural use	ASTM A 6

2.	Structural Steel	ASTM A 709

3.	High Strength Low-Alloy Columbium

Vanadium Steels of Structural Quality	ASTM A 709

4.	High Strength Low-Alloy Steel with 50,000 psi

minimum yield point to 4 inches thick	ASTM A 709

5.	High Yield Strength, Quenched and Tempered

Alloy Steel Plate Suitable for Welding	ASTM A 709

6.	Hot-Formed and Seamless High Strength Low-Alloy Tubing 	ASTM A 618 Grades Ib, II, III

7.	Filler Metal for Applicable Arc-Welding Electrodes	AWS Specifications

8.	Stud Shear Connectors	ASTM A 108

Gr. 1015, or 1020

9.	Raised Pattern Plate. Where shown on the Plans, use plates for steel expansion joints fabricated from steel plate, with a raised pattern surface meeting the following requirements:

a.	Use diagonal type pattern, with the intersecting diagonals at right angles to one another. Use the same material for the raised portions of the pattern as the base metal of the plate. The raised pattern must be an inherent part of the plate. The pattern must be continuous throughout the surface of the plate and the projections along any diagonal must be spaced alternately with the projections along the normal diagonals.

b.	Use plate with projections that are self-draining and self-cleaning and provide a skid-resistant surface from all angles of approach. The projections must have flat tops and be designed not to chip, crack, split, or buckle at their intersection with the base metal.

10.	Impact Test Requirements.

a.	Unless noted as Fracture Critical (F), meet the impact test requirements for impact toughness testing (Charpy V-Notch) and marking under ASTM A 709, Non-Fracture Critical (T) Tension Components, Zone 3.  For material designated on the Plans as Fracture Critical (F), meet the impact test requirements for impact toughness testing (Charpy V-Notch) and marking under ASTM A 709, Fracture Critical (F) Tension Components, Zone 3.

b.	Submit impact test reports to the Engineer.

716-2.03 HIGH TENSILE STRENGTH BOLTS. Meet the following:

High Strength Bolts	ASTM A 325

Nuts	ASTM A 563

Hardened Steel Washers	ASTM F 436

Zinc Coated Load Indicating Washers	ASTM F 959 Type 325

716-2.04 Steel Grid Floors. Meet ASTM A 709, Grade 36. Unless the material is galvanized, it must have a copper content of 0.2% minimum.

Unless painting of floors is specified in the Special Provisions, open type floors must be galvanized.

716-2.05 Machine Bolts. Meet ASTM A 307.

716-2.06 STEEL PIPE. Meet ASTM A 53 Grade B.

716-2.07 GALVANIZING. Hot-dip galvanize structural steel shapes, plates, bars and their products according to AASHTO M 111. Galvanize tubes and piles on inside and outside surfaces.

Hot-dip galvanize steel poles, mast arms, pedestals, and posts, according to AASHTO M 111. Submerge each component in the galvanizing kettle in one dip. Use only the dry kettle method of fluxing for high tower poles.

Hot-dip galvanize all anchor bolts, nuts, washers, tie-rods, clamps, and other miscellaneous ferrous parts in conformance with AASHTO M 232. After galvanizing, ensure that the bolt threads accept galvanized standard nuts without requiring tools or causing removal of protective coatings.

Galvanize rigid metal conduit in conformance with AASHTO M 232.

For Steel Bridge members, apply 10 mils zinc galvanizing by spray-metalizing process according to Steel Structures Painting Council (SSPC) Coating System Guide No. 23.00. Prepare surfaces before galvanizing in accordance with SSPC-SP 5 White Metal Blast Cleaning.

Repair damaged coatings in accordance with ASTM A 780 Annex A1 or Annex A3.

716-2.08 CERTIFICATION. Submit five copies of a certified test report covering chemical and physical tests conducted on all structural steel to the Department for the material in each shipment.

DOT BRIDGE-082912

SECTION 719

STEEL, GRAY-IRON AND

MALLEABLE IRON CASTINGS

Standard Modification

719-2.02 GENERAL REQUIREMENTS.  In Gray-Iron Castings, delete text and replace with:

AASHTO M 306 and AASHTO M 105, Class 35B.

E47-012707

Special Provision

Replace Section 720 with the following:

SECTION 720

BEARINGS

720-2.01 ELASTOMERIC BEARING PADS. Elastomeric bearing pads include plain pads, consisting of elastomer only, and laminated pads with steel laminates.

1.	General. Meet AASHTO M 251, with the following revisions:

4.1 Properties of the Elastomer. Replace the first sentence with the following: Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer. Do not use neoprene. Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) do not apply.

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraph 8.9.

Add the following paragraph:

5.5. Fabricate pads over 3/4 inch thick with alternating laminations of elastomer and metal or fabric reinforcements. The outside laminations must be metal or fabric with a minimum elastomer cover as shown on the Plans.

2.	Certification. Submit five copies of a certified test report for each elastomeric pad configuration.

720-2.02 EPOXY ADHESIVE FOR ELASTOMERIC BEARING PADS. Meet AASHTO M 235, Type IV, Grade 3.

720-2.03 POLYTETRAFLUOROETHYLENE (PTFE) BEARINGS. PTFE bearing assemblies consist of elastomeric bearing pads, polytetrafluoroethylene (PTFE) surfacing, and stainless steel and steel plates.

1.	Materials.

Elastomeric Bearing Pads	Subsection 720-2.01

Stainless Steel Plates	ASTM A 240, Type 304

Steel Plates	ASTM A 709, Grade 36

Use PTFE from virgin material (not reprocessed) meeting the requirements of ASTM D 4894 or D 4895, and Table 720-1.

2.	Fabrication. Fabricate the PTFE sliding surface with lubricant dimples having a maximum diameter of 0.32 inch, a minimum depth of 0.08 inch and a maximum depth of one half of the PTFE sheet thickness. Distribute the dimples uniformly within the area ¼ inch from the edges of the PTFE sheet and occupying between 20 percent and 30 percent of the PTFE sheet area.

For welding of structural steel, conform to the requirements of Section 504.

TABLE 720-1

POLYTETRAFLUOROETHYLENE (PTFE)

| Test | Requirements |
| --- | --- |
| Specific Gravity | 2.13 - 2.19 |
| Peak Melting Temperature | 623oF (2oF) |
| Tensile strength (Minimum) | 2800 psi |
| Elongation (Minimum) | 200% |

Bond the PTFE sheet in the recess of steel plate under controlled factory conditions. Use adhesive material that is an epoxy resin conforming to the requirements of Federal Specification MMM-A-134.

Uniformly roughen the contact surfaces of PTFE sheet and steel plate to be bonded to a minimum roughness height value of 250 micro-inches.

Factory treat the side of the PTFE sheet to be bonded by the sodium naphthalene or sodium ammonia process, after the contact surface is roughened.

Fully bond the PTFE sheet in the recess. Ensure the PTFE surface is smooth and free from bubbles after completion of the bonding operation. PTFE sheets that are delaminated will be rejected.

Perimeter seal weld the stainless steel plate to the steel sole plate. Use stainless steel electrodes in accordance with the requirements of the electrode manufacturer. After the completion of the weld operation, ensure the stainless steel plate is smooth and free from waves.

Control the flatness of the bearing elements such that upon completion of the bearing assembly the PTFE/stainless steel sliding interface is in full bearing.

Provide a mating surface of the stainless steel plate with the PTFE surfacing with a surface finish of less than 8 micro inches root-mean-square (rms), determined according to ANSI Standard B46.1. Do not exceed a first movement static coefficient of friction of 0.05 for the sliding element of the production bearings, when tested without the coating of silicone grease.

Fully vulcanize elastomeric bearing pads to the steel plates under factory controlled conditions. Provide a bond with a peel-strength of at least 30 pounds per inch as determined by AASHTO M 251, appendix X2.

Prepare and paint metal surfaces, except stainless steel surfaces, of bearings exposed to the atmosphere in the completed work. Prepare and paint the surfaces according to Section 504.

After installation of the bottom portion of the bearing assembly, apply a 1/16 inch thick coating of silicone grease to the entire PTFE surface and reassemble the bearing without damage to the mating sliding surfaces. Use silicone grease conforming to Military Specification: MIL-S-8660.

At your expense and without contract extension time return damaged bearings and bearings with scratched mating surfaces to the factory for replacement or resurfacing.

Prior to proof testing, permanent die stamp all individual components on 2 of 4 sides with markings consisting of bearing number and contract number. Provide each bearing with a unique bearing number and match marks on plate edges to insure correct assembly at the job site.

3.	Testing. Proof test and evaluate full sized PTFE bearings for compression and coefficient of friction in the presence of the Engineer, unless otherwise directed. Perform proof tests on samples randomly selected by the Engineer from the production bearings to be used in the work. Perform proof tests at an approved independent laboratory. If proof tests are not performed at the specified load, perform additional physical tests in the presence of the Engineer, unless otherwise directed, to demonstrate that the requirements for proof testing at the specified load are satisfied. Give the Engineer at least 7 working days notice before beginning proof testing.

Proof test one bearing per lot of production PTFE bearings. A lot is defined as 25 PTFE bearings or fraction thereof of the number of PTFE bearings shown on the Project Plans.

Clean the bearing surfaces prior to testing.

Proof test bearings after conditioning specimen for 12 hours at 75o 5oF.

Perform the tests with the dead load as specified in the Contract for the bearing with the test load applied for 12 hours prior to friction measurement and the following:

Arrange the tests to allow measurement of the static coefficient of friction on the first movement of the bearing.

Measure the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

Subject the test bearings to a minimum of 100 movements of at least one inch of relative movement at a sliding speed not exceeding 12 inches per minute. After cycling, measure again the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

The proof tested bearings are to show no visible sign of: (1) bond failure of bearing surfaces, (2) separation or lift-off of plates from each other or from PTFE surfaces, (3) other defects. When a proof tested bearing fails to comply with the Contract Documents, test each bearing in that lot for acceptance.

Proof test results are to be certified correct and signed by the testing laboratory personnel who conducted the test and interpreted the test results. Include the bearing numbers of the bearings tested on the proof test results.

Test a minimum of one pad per lot for bond strength per AASHTO Test M 251. Test specimens are to show no indication of deterioration of elastomer or loss of bond between the elastomer and steel laminates.

Protect all PTFE and stainless steel surfaces from contamination and weather damage.

4.	Certification. Submit a certified test report for each bearing configuration.

DOT BRIDGE-012012

SECTION 724

SEED

Special Provision

724-2.02 MATERIALS.

Delete Table 724-1 and replace with the following:

TABLE 724-1

SEED REQUIREMENTS

| Species | Sproutable Seed, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

*Sproutable Seed is the mathematical product of Germination and Purity.

CR7241-101711

- SECTION 726

TOPSOIL

Special Provision

Delete Subsection 726-2.01, except for Table 726-1 and replace with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

CR208-112707

- Special Provisions

- Replace Section 727 with the following:

- SECTION 727

SOIL STABILIZATION MATERIAL

727-2.00 GENERAL.  Free of noxious weeds, seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life.  Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH.  Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control.  Use one of the following:

Dry Erosion Control, Stabilization Products.  Hand applied or spread with mulch blower equipment.

1.	Straw.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Weed Management Association (NAWMA) Standards.  In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch.  Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

Hydraulic Erosion Control Products (HECPs) Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made.  When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth.  The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period).  When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer.  The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise.  Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

The HECP shall contain a dye to facilitate placement and inspection of the material.

1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed.  Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch.  No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

2.	Dried Peat Moss.  Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING.  Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC.  Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

Functional Longevity.

1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs.  (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs.  (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs).  Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs).  Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless.  Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net.  Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs).  Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap.  Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric.  Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn.  Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter.  Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width:  45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight:  20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting.  Woven from twisted yarns available in rolls 45 to 48 inches wide.  Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings.  Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat.  Commercially manufactured ECB.  Use photodegradable netting and biodegradable thread.  Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life.  ECB may contain coconut or fiber to reinforce the straw.  Straw material shall be certified weed-free straw using NAWMA Standards.  In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

5)	Woven/Curled Wood blanket.  Machine produced mat of curled wood shavings with a minimum of 80% 6-inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket.  Smolder resistant without the use of chemical additives.  Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber).  Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat.  Use bio/photo degradable netting and thread.

2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs).  A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2.  TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs).  Fiber rolls also referred to as wattles.  Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears.  Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST.  Suitable for serving as a soil amendment or an erosion control material.  Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program.  Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503.  Additionally, meet the requirements of the AASHTO specifications:

1.	Compost Blankets.  Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52-10.

2.	Compost Filter Berms and Filter Socks.  Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51-10.

727-2.05 TACKIFIER.  Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground.  Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates.  Tackifier shall hydrate in water and readily blend with other slurry material.  Tackifier options include:

1.	Type A.  Organic tackifier with certification of plant sources; or

2.	Type B.  Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM).  Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER.  Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

2.	Seam Thread.  Similar durability to the sandbag sack fabric.

3.	Sandbag Fill Material.

a.	Selected Material	703-2.07	Type B

4.	Cinch Ties.  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING.  A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES.  U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide.  Machine-made:  No. 11 gage or heavier steel wire.  Hand-made:  12-inch lengths of No. 9 gage or heavier steel wire.

CR727-050812

SECTION 729

GEOSYNTHETICS

Special Provision

729-2.01 GEOTEXTILE, SEPARATION AND STABILIZATION.

Add to the end of 1. (Separation):

and meet the AASHTO M 288 Class 1 strength property requirements.

0001(458)/52972-082712

SECTION 730

SIGN MATERIALS

Standard Modification

Delete Subsection 730-2.01 SHEET ALUMINUM and replace with the following:

730-2.01 SHEET ALUMINUM.  Use alloy 6061-T6, 5052-H36, 5052-H38, or recycled aluminum meeting alloy 3105, as specified in ASTM B 209.  Meet the thickness of aluminum sheet designated on the Plans.  Verify alloy and temper designation by mill certification.

Before January 1, 2011, treat the aluminum base metal sheets with chromate conversion coating for aluminum to meet ASTM B449, Class 2.

After January 1, 2011, treat the aluminum base metal sheets with a rinsed non-hexavalent chromium conversion coating for aluminum and aluminum alloys that meets ASTM B 921, class one.  Handle the cleaned and coated base metal only by a mechanical device or by operators wearing clean cotton or rubber gloves.  After cleaning and coating operations, protect the panels at all times from contact or exposure to greases, oils, dust, or other contaminants.

Make each sign panel a continuous sheet for all lengths 72 inches or less in the horizontal direction.  Use no more than one vertical splice for signs up to 144 inches in length and 48 inches or less in height.

Meet the panel dimensions specified with a tolerance of 1/16 inch.  Furnish metal panels that are cut to size and shape and free of buckles, warp, dents, cockles, burrs, and any other defects resulting from fabrication.  Complete all possible fabrication, including shearing, cutting, and punching of holes prior to the base metal preparation.

E86-041210

Special Provision

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR81-062204

INDEX

Standard Modification

INDEX Remove the text. “Approved Products List” and replace with: Qualified Products List

E36-012707

APPENDIX A

CONSTRUCTION SURVEY REQUIREMENTS

APPENDIX B

ENVIRONMENTAL PERMITS

APPENDIX C

MATERIAL CERTIFICATION LIST

APPENDIX D

SIGN SHOP DRAWINGS

APPENDIX E

TEMPORARY CONSTRUCTION EASEMENTS