ESCROW OF BID DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF BID DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE BID AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 103-1.11. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE BID PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in bid preparation is available from the Department of Transportation and Public Facilities, Anchorage office, located at 4111 Aviation Avenue.

1.	Publications.  The following are available from the Plans Room:

a.	Standard Specifications for Highway Construction, 2004 Edition ($25.00).

b.	Alaska Test Methods Manual (Lab & Field), 2009 Edition ($25.00). Available online at:

http://www.dot.state.ak.us/stwddes/desmaterials/mat_waqtc/pop_testman.shtml

c.	Alaska Storm Water Pollution Prevention Plan Guide, January 19, 2005.

d.	Quantity Computations

e.	Cross Sections

f.	Geotechnical Reports, West Dowling Road – Phase 1 Geotechnical Recommendations, DOT&PF 2009.  Cordova Street Extension Test Holes, DOT&PF 2009.

g.	Final Structural Foundation Engineering Report, Dowling Campbell Creek Bridge, Bridge No. 972, DOT&PF 2009.

h.	Erosion and Sediment Control Plan (ESCP).  West Dowling Road, Phase I, Federal/State Project No. STP-0532(007)/50898 and Cordova Street Extension, State Project No. 53454, DOWL HKM August 2011.

i.	Campbell Creek Bridge 972 as-builts, 1980.

2.	Materials Certification List (MCL).  The MCL provides the Engineer with the appropriate approving authority.  Contractor, submit certification for each material to the Engineer.  The MCL is included in Appendix D.

3.	Environmental Documents.  The Department has approved an environmental document addressing concerns and environmental commitments.  This document is available for review in the Department Section of Preliminary Design and Environmental.  (907) 269-0542.

4.	Hiring Apprentices.  Administrative Order 226, issued July 24, 2005 establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility, or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, visit http://labor.state.ak.us//lss/forms/ApprenHireReq.pdf

5.	Disadvantaged Business Enterprise (DBE) Program.  Effective August 1, 2011, the Alaska Department of Transportation & Public Facilities returned to DBE Utilization Goals for projects with Federal Highway Administration (FHWA) funds for all Regions.  FHWA approved the return to DBE goals based on recommendations of the Department's completed Disparity Study and approval of a DBE Program waiver.

The Department received approval and implemented in 2010 a return to DBE Utilization Goals for Federal Aviation Administration (FAA) and Federal Transit Administration (FTA).

FHWA has approved the Department’s request to return to DBE Utilization Goals for Central Region. A waiver to exclude a DBE group from DBE goal setting because that group had achieved parity with other contractors was requested and approved by the US Secretary of Transportation. This waiver request was based on the finding of the Department’s completed Disparity Study.

Contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A336 for FHWA funded projects. This will allow the Department to continue to accurately report DBE participation to the FHWA, FAA and FTA.

Any questions about this notice may be directed to Jon Dunham, Manager of the Civil Rights Office, (907) 2698-0850, or email jon.dunham@alaska.gov.

6.	How the US DOT Waiver for the DBE Program will be Implemented on Central Region Construction Projects. August 1, 2011, the Alaska Department of Transportation & Public Facilities returned to DBE Utilization Goals for projects with Federal Highway Administration (FHWA) funds for Central Region. FHWA approved the return to DBE goals based on recommendations of the Department’s completed Disparity Study and approval of a DBE Program Waiver. The DBE Program Waiver approved by USDOT addresses the issue identified in the Department’s Disparity Study which found that DBE firms that are owned by Non-Minority Women were participating on the Department’s construction contracts and subcontracts on an equal basis similar to other non-DBE contractors and non-DBE subcontractors for Central Region only.

As a result, goals will be set using minority-owned DBEs only, and DBE project goals can only be met through the use of minority owned DBEs.  This Waiver does not affect DBE project goals for airports or transit projects anywhere in Alaska, and does not apply to professional service agreements or highway construction projects in Northern or Southeast Regions.

The decision to continue or discontinue the use of the Waiver will be made on an annual basis in June.

Any questions about this notice may directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, or email jon.dunham@alaska.gov.

7.	Prevailing Wage Requirements.  The Department of Labor and Workforce Development (DOLWD) proposed a revised regulatory definition of "on-site" in 8 AAC 30.910 to clarify the scope of activities covered by Alaska's Little Davis Bacon Act (AS 36.05.010 - AS 36.05.110).  for a copy of the revised definition of 8 AAC 30.910, go to:  http://labor.alaska.gov/lss/forms/400-revised-definition-of-on-site.pdf.

DOLWD will enforce the revised provisions on all projects with bid opening date on or after February 15, 2011.  Prospective bidders on projects with a bid opening date on or after February 15, 2011, must consider the impact of the revised regulation and bid accordingly.  DOLWD will not enforce the new "on-site" definition on projects with a bid opening date prior to February 15, 2011.

8.	Utilities.

a.	Agreements and Dispositions.  Utility Agreements and dispositions are available for review at the office of the Utilities Engineer, (907) 269-0650.  Copies may be available, coordinate with the Utility Engineer.

b.	Utilities, and Erosion, Sediment and Pollution Control.  Utilities will be relocated by others concurrently with construction of this project.  The Contractor is responsible for the coordination with Other Contractor’s and for control of erosion, sediment and pollution including stabilization of areas disturbed during utility relocation, as described in Section 105-1.06.

The Contractor will identify, in their SWPPP, other work that is or will occur inside or adjacent to the project limits during the contract period.

9.	Asphalt Laydown Temperatures.  The Department may monitor laydown temperatures using a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense as specified in Division 400.

10.	High Visibility Clothing.  The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retroreflectivity.  See subsection 643-3.11.

11.	Signals, Lighting Poles, Load Centers, Controller Assemblies.  The Plans and Specifications are revised for these items including, anchors to the foundations, foundations and conduit installation.

12.	Section 670 Traffic Markings.  This section is recently revised including but not limited to submittal requirements and method of measurement.

13.	Section 306 Asphalt Treated Base.  This Section is recently revised by replacement special provision.  The format is similar to Section 401 Hot Mix Asphalt and Surface Treatments.  Review for specific requirements including but not limited to a 0.5 multiplier applied to the Asphalt Treated Base Price Adjustment, 306-4.03, Evaluation of Materials For Acceptance.

14.	Section 641 Erosion, Sediment, and Pollution Control – SWPPP Requirements.  Amend a SWPPP approved under an expired CGP to meet the requirements of a new, replacement CGP.  Amendments are included in and paid for under Pay Item 641(1) Erosion, Sediment, and Pollution Control Administration.

The ADEC issued (May 19, 2011) an APDES Construction General Permit (CGP) for Discharges from Large and Small Construction Activities (effective July 1, 2011 through January 31, 2016) replacing the CGP, of same name, expiring on June 30, 2011.  Refer to the ADEC internet site, www.dec.alaska.gov:

ALASKA POLLUTANT DISCHARGE ELIMINATION SYSTEM

GENERAL PERMIT FOR DISCHARGES FROM LARGE AND SMALL CONSTRUCTION ACTIVITIES

15.	Section 644 Services To Be Furnished By The Contractor.  644-2.09 Image Documentation is new to Section 644.

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

To the STATE OF ALASKA

STANDARD

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2004

EDITION

SECTION 101

DEFINITIONS AND TERMS

Standard Modification

101-1.03 DEFINITIONS.  Delete text of PLANS and replace with:  The Department’s contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32(01/27/07)

Add the following definition:  QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.  E36(01/27/07)

Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.  E22(1/1/06)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.  Add the following after the first sentence in the first paragraph: The Erosion and Sediment Control Plan (ESCP) is only for informational purposes.

Replace the second paragraph with the following:

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development.

E23(1/1/06)

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18(6/30/04)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modification

Delete Subsection 103-1.05 and replace with the following:

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract.  If no sum is specified, the successful bidder shall comply with AS 36.25.010.  The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond.  Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety.  In no event will the Department be liable for these costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department.  Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3.	Cashier’s or certified check made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

1.	Becomes insolvent or is declared bankrupt;

2.	Loses its right to do business in any state affecting the work;

3.	Ceases to meet Contract requirements;

4.	Fails to furnish reports of financial condition upon request; or

5.	Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

1.	An individual surety with a corporate surety; or

2.	Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department’s discretion, be grounds for declaring the Contractor in default.

E65 (02/23/09)

Special Provision

Add the following subsection:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of the Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and information used to prepare the Bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department designated document depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that

a.	the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

b.	the sealed container contains all bid documentation submitted,

c.	the escrow materials were relied on to prepare the bid, and

d.	should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least 5 days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of escrow documentation (whether hard copy, electronic, or otherwise); to use and review copies consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders the bid non-responsive.  Failure or refusal to provide subcontractor bid documentation will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are the Contractor’s property.  Except as otherwise provided herein, the escrow materials cannot be released without the Contractor’s approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to the Contractor once litigation is concluded, outstanding claims are resolved, the Contractor has completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11 (01/01/06)

SECTION 104

SCOPE OF WORK

Standard Modification

104-1.01 INTENT OF CONTRACT.  Add to the end of this subsection:

The Contractor is responsible for the means, methods, techniques, sequence or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

E58 (07/28/08)

- SECTION 105

- CONTROL OF WORK

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete: “(24”x36”)” and replace with: (22”x34”)

Remove the first sentence of the third paragraph and replace with the following: Submit to the Engineer for approval three sets of all required detail or working drawings.

After the fourth paragraph, add the following:  Provide a signed statement with each submittal affirming the delivered submittal has been reviewed by the Contractor as being in conformance with the applicable Contract requirements and the Contractor’s working plan, equipment, schedule, etc. Make individual submittals for each item of work. Allow at least fifteen (15) working days, or as otherwise indicated in the Contract documents, for the Department's review of each submittal. Partial or incomplete submittals will not be accepted for review and approval. In the event that several submittals are delivered simultaneously or additional submittals are delivered for review before the review of the previously delivered submittal has been completed, designate the sequence in which the submittals are to be reviewed. In such an event, the time to be provided for the review of any submittal in the sequence shall be not less than the review time specified above for that submittal, plus fifteen (15) working days for each submittal of higher priority that is still under review.

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after: “Work performed and materials furnished shall conform to the Plans and Specifications” add: and approved Working Drawings,

In the first sentence of the second paragraph after: “All work or material not conforming to the Plans and Specifications” add: and approved Working Drawings.

E33(01/27/07)

Special Provision

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

| ALASKA DIGLINE, INC. Locate Call Center Anchorage: 811 who will notify the following: |  |
| --- | --- |
| ACS Anchorage School District Anchorage Water and Wastewater Utilities Chugach Electrical Association DOT&PF Street Lights, State of Alaska | ENSTAR Natural Gas GCI Communications MOA Street Maintenance Department Municipality of Anchorage |

Call the following utilities and agencies directly:

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation by utility owner’s is as follows.

Utilities Relocated by Others.

Utilities will be relocated by others concurrently with construction of this project.  The Contractor will give the Utility, through the Engineer, 15 calendar days advance written notice regarding the dates when the utility owner is required to begin and end operations.  For utilities being relocated, the Contractor will:

1.	include utility work on the Construction Phasing Plan and Progress Schedule.

2.	provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work.  Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP).  Refer to Section 641 for further information.

3.	clear and grub.  Payment will be made under Section 201, Clearing and Grubbing.

4.	provide traffic control and flagging.  Payment will be made under Section 643, Traffic Maintenance.

5	provide Right-of-Way and/or Construction Surveying before utility relocation.  Include:

	Control for utility relocation - either ROW or Centerline staking with Station information,

	Slope staking,

	Proposed utility facilities and appurtenances.

Payment will be made as follows:

a.	Subsidiary to Pay Item 642(1) Construction Surveying, if the Contractor is required to provide the surveying as part of the Contract and/or,

b.	Under Pay Item 642(3) Three Person Survey Party, if the Construction or Right of Way staking required by the utility is either in advance of the 2 week work plan, or not required by the Contract.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

6.	remove and replace pavement.  Payment will be made under Section 202, Removal of Structures and Obstructions; Section 401, Hot Mix Asphalt and Surface Treatments; Section 408, Hot Mix Asphalt and Surface Treatments, Type V; Section 409, Hot Mix Asphalt and Surface Treatments, Type R (Crumb Rubber) and according to project typical section.

7.	remove and replace sidewalk and curb and gutter.  Payment will be made under Section 202, Removal of Structures and Obstructions, Section 608, Sidewalks, and Section 609, Curbing.

Specific coordination requirements for each Utility are listed below:

ENSTAR Natural Gas Company (ENSTAR) owns and operates natural gas distribution mains and service lines within the project limits. The following facilities will require relocation/adjustment:

ENSTAR will replace the existing main along Franklin Drive.  The replacement will move the main from the northwest side of the street to the southeast side.  This replacement will eliminate two gas services from crossing Franklin Drive and create one new gas service crossing.  Allow ENSTAR ten (10) calendar days to complete the replacement.

ENSTAR maintains gas service(s) on Cordova Street that will be adjusted as part of the project.  Allow ENSTAR two (2) calendar days to complete the adjustment(s).

WEST DOWLING ROAD - ENSTAR’s existing three (3) inch steel gas main falls within five feet of the proposed east abutment for the new Campbell Creek Bridge and will be relocated. New gas main will be installed from station 21+25 RT to 34+50 RT, with new pipe being directional drilled under the creek. In addition the service crossing at station 30+65 will be replaced due to a conflict with the proposed bio-swale. The new crossing will be coordinated with placement of the new driveway located at station 29+70 LT. The gas main crossing at station 34+50 will be extended outside the structural section and reconnected to the existing service. Allow ENSTAR twenty (20) calendar days to complete the relocation.

ENSTAR’s gas main crossing at station 21+60 is in conflict with the Potter Road realignment and will be replaced with a new crossing of Dowling Road at station 21+25, which then crosses Potter Drive to the west and extending to the north to tie to the existing gas main. The main will extend to the east of the crossing with new gas main extending along the east side of Franklin Street as described below under Cordova Street. Allow ENSTAR seven (7) calendar days to complete the relocation.

Between station 36+50 RT and 38+50 RT cover will be reduced over the existing gas main and lowering of the main will be required. Once the area is staked identifying the proposed cuts, allow ENSTAR four (4) calendar days to complete the adjustments.

CORDOVA EXTENSION – ENSTAR will replace the existing main along Franklin Drive, the replacement will move the main from the northwest side to the southeast side. Existing services will be reconnected to the new main as required. Allow ENSTAR seven (7) calendar days to complete the relocation.

ENSTAR’s existing service on Cordova Street, station 904+95, will require adjustment due to drainage along the LT side. Allow ENSTAR two (2) calendar days to complete the adjustments.

CHUGACH ELECTRIC ASSOCIATION (CEA) owns and operates overhead electrical transmission and overhead and underground electrical distribution within the project limits. The following facilities will require relocation.

Distribution - At station 16+00 LT overhead distribution enters the project from the north, turns east and parallels the project to station 39+00 LT.  At station 39+00 the overhead ends and underground continues to station 42+40 LT, terminating in a switch cabinet in the NW quadrant of the Old Seward Highway intersection.

In order to begin bridge construction concurrently with relocation of the aerial facilities, CEA will install a new switch cabinet and a portion of underground at a location off project. Once this work is complete CEA will install dead-end structures on each side of the bridge and abandon the existing overhead between stations 28+10 LT and 35+78 LT.  Prior to CEA abandoning the overhead facilities GCI will place a temporary aerial shoe-fly of their aerial fiber optic cable around the proposed bridge construction. CEA will require twenty five (25) calendar days to complete the new installation, dead-end placement, GCI shoe-fly placement and abandoning of the overhead above the bridge.

The overhead distribution will be within the proposed roadway for the entire length and will require relocation in an underground configuration. The underground will parallel the project utilizing the outer portion of the ROW or utility easements. The overhead will terminate on the north side of the project at station 16+00 LT, the underground will cross to the south side and continue to the east to station 36+50 RT where it will cross back to the north side. New underground will be placed from 36+50 LT to station 42+30 LT, where the underground will terminate in a new switch cabinet which will be placed north of the proposed improvements. The existing underground circuit which crosses Old Seward Highway and Dowling Road at station 42+60 will be extended north to terminate in the new switch cabinet. To allow retirement of the existing aerial and underground in conflict the proposed circuit will require installation for the entire length. CEA will require ninety-five (95) calendar days to complete the new installation and retirement of the existing aerial in conflict.

The existing aerial circuit to the north at station 36+75 will be terminated and tied into the new underground. Due to the proposed undergrounding the aerial circuit to the north will require a loop connection. CEA will require twenty (20) calendar days to complete the new loop installation.

At station 9+00 RT CEA’s existing pole will fall within the proposed alignment, CEA will replace the overhead circuit to the north with a new underground circuit, which will tie into the existing underground to the north. CEA will require ten (10) calendar days to complete the new installation and retirement of the existing aerial in conflict.

Once LC’s have been inspected and green tagged, provide CEA the appropriate information with location for service and the tag ID numbers. Electrical service will be scheduled based on the current workload of the utility.

Transmission - CEA’s existing overhead transmission parallels the south side of the project for the entire length with conflicts at the following locations.

Station 14+75 RT, the existing down guys to the north of angle structure will be in conflict with the roadway. The pole also has wood swamp braces attached which will conflict with the proposed sidewalk and will be replaced with steel piling. A guy pole will be installed on the north side of the road and pathway with down guys installed to the north. An overhead span guy will be installed between the pole and the new guy pole allowing retirement of the down guys. CEA will require fifteen (15) calendar days to complete the new installation and retirement of the facilities in conflict.

Station 32+85 RT, the existing transmission structure will be in conflict with the proposed pathway under the new Campbell Creek Bridge and will be relocated in line to the east. CEA will require seven (7) calendar days to complete the new installation and retirement of the facilities in conflict.

Station 36+45 RT, the existing transmission structure will be in conflict with the proposed curb and gutter and sidewalk and will be relocated in line to the east. CEA will require seven (7) calendar days to complete the new installation and retirement of the facilities in conflict.

ALASKA COMMUNICATIONS SYSTEMS (ACS) owns and operates overhead and underground telecommunications within the project limits. The following facilities will require relocation.

ACS’s existing aerial cable attached to CEA’s distribution poles will be in conflict and will require relocation. ACS will install a new section of cable outside the project which will provide service to the remaining lots on the north side and the existing aerial cable can be retired. Allow ACS fifteen (15) calendar days to complete the installation and retirement of the aerial cable.

The existing buried cables at Campbell Creek will be in conflict with the proposed rip-rap placement. The crossing at station 35+80 and extending east to ACS’s existing manhole at the NW corner of the Old Seward Highway intersection will be in conflict with the structural section and will be relocated. New conduit will be placed jointly with CEA from station 18+50 RT to 42+65 LT. Once trench and conduit installation has been completed, ACS will place new cable in the conduit. ACS will place a new section of conduit and cable along Austin Street south of the project. Once CEA has completed the conduit installation allow ACS thirty-five (35) calendar days to complete the cable placement and splicing required to abandon the existing facilities.

GENERAL COMMUNICATIONS INC. (GCI) owns and operates overhead and underground telecommunications within the project limits. The following facilities will require relocation.

GCI’s existing aerial fiber optic cable, CATV trunk and feeder cables attached to the CEA distribution poles to be removed will be relocated underground in a joint trench with CEA.

The CATV trunk and feeder cables and fiber optic cable enter the project at station 16+00 from the north. A second fiber optic cable enters the project at station 19+00 from the south. The CATV trunk cable and the fiber cables extend east through the limits of the project. The feeder cable extends to station 36+75 where it feeds both north and south of the project.

In order to begin bridge construction concurrently with relocation of the aerial facilities, CEA will install dead-end structures on each side of the bridge and abandon the existing overhead between stations 28+10 LT and 35+78 LT.  Prior to CEA abandoning the overhead facilities, GCI will place a temporary aerial shoe-fly of their aerial fiber optic cable around the proposed bridge construction. GCI will require fifteen (15) calendar days to complete the shoe-fly placement of the existing fiber optic around the area of the proposed bridge construction.

The fiber optic cable will require relocation from station 19+00 RT to 42+10 LT in its entirety prior to cutover of the existing cable.  The CATV cables will follow the CEA distribution system through the project. Once CEA has completed installation of the underground conduit system allow GCI twenty (20) calendar days to install the new CATV and fiber optic cables, complete cutover to the new cables, and retire the aerial systems.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  The following state and municipal owned projects may be under construction concurrently with this project:

| Project Name | DOT&PF Project Number | MOA Project Number |
| --- | --- | --- |
| Seward Highway: Dowling – Tudor Reconstruct | 50816 |  |

Coordinate traffic control, construction, and material hauling operations with the prime Contractor of the above projects to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other Contracts.

CR1051-110309

Standard Modification

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:  Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take the corrective action within the specified time, the Engineer may:

Suspend the work until corrective maintenance is completed;

Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33(01/27/07)

105-1.15 PROJECT COMPLETION.  In the second paragraph, second sentence, delete:  “Subsection 621-3.04” and replace with:  Subsections 618-3.06 and 621-3.04.

In the third paragraph, first sentence, delete:  “Subsection 621-3.04” and replace with:  Subsections 618-3.06 and 621-3.04.

E59 (07/28/08)

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue. E19(6/30/04)

Special Provision

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:  Appeals to the superior court under AS 36.30.685 must be filed in the Third Judicial District.  R93(03/21/01)

- SECTION 106

CONTROL OF MATERIAL

Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text. “Approved Products List” and replace with:  Qualified Products List

E36-012707

Special Provision

Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and submit a completed Material Origin Certificate, Form 25D-60, before award of the Contract.

Steel and iron products, which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2,500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the Project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating process must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

CR13-020705

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.  E24(1/1/06)

Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents.  The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.

Add the following Subsection 106-1.09

106-1.09 RESERVED

E34(01/27/07)

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

- Special Provision

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following:  Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If  cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Regional Supplement to the Corps of Engineers Wetland Delineation Manual (Alaska Region, Version 2.0, September 2007).  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following:  The Department has received the following permits on the Contractor’s behalf (see Appendix A):

- Alaska State Historic Preservation Office Concurrence Letters, 2007 and 2010

- Coastal Zone Consistency Review (Coastal Project Questionnaire), December 2009

- Alaska Department of Fish and Game Title 16 Fish Habitat Permit, December 2009

- Municipality of Anchorage Flood Hazard Permit, April 2010

- State of Alaska Department of Environmental Conservation Stormwater Review, September 2009

- State of Alaska Department of Environmental Conservation Approval to Construct Water System, August 2011

- State of Alaska Department of Environmental Conservation Approval to Construct Wastewater System, July 2011

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

Contractor shall obtain a Municipality of Anchorage Noise Permit for work at the intersection of C Street and Dowling Road as well as at the intersection of Old Seward Highway and Dowling Road.  This Noise Permit is subsidiary to the contract pay items.

Standard Modifications

107-1.05 FEDERAL AID PROVISIONS.  Add the following after paragraph two:

Form 25D-55H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts.  The FHWA no longer requires the Contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds.  Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements.  During the performance of this Contract, the Contractor, for itself, its assignees and successors in interest (hereinafter referred to as the "Contractor") agrees as follows:

(1)	Compliance with Regulations:  The Contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this Contract.

(2)	Nondiscrimination:  The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment.  The Contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, Section 21.5 of the regulations, including employment practices when the Contract covers a program set forth in Appendix B of the Regulations.

(3)	Solicitation for Subcontractors, Including Procurements of Materials and Equipment:  In all solicitations either by competitive bidding or negotiation made by the Contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the Contractor of the Contractor's obligations under this Contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

(4)	Information and Reports:  The Contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions.  Where any information required of a Contractor is in the exclusive possession of another who fails or refuses to furnish this information the Contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

(5)	Sanctions for Noncompliance:  In the event of the Contractor's noncompliance with the nondiscrimination provisions of this Contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

(a)	withholding of payments to the Contractor under the Contract until the Contractor complies, and/or

(b)	cancellation, termination, or suspension of the Contract, in whole or in part.

(6)	Incorporation of Provisions:  The Contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The Contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance:  Provided, however, that in the event a Contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the Contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the Contractor may request the United states to enter into such litigation to protect the interests of the United States.

E67(10/15/09)

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:

When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer.

CR7(02/08/10)

Special Provisions

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following:

Bald Eagles are protected under the Bald Eagle Protection Act (16 U.S.C. 668-668c) which prohibits “takes” of bald eagles, their eggs, nests, or any part of the bird.  The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of a minimum 330 ft as an undisturbed habitat buffer around nesting bald eagles.  If topography or vegetation does not provide an adequate screen or separation, extend this buffer to 0.25 miles, or a sufficient distance to screen the nest from human activities.  The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity.  Within the Secondary Zone, between 330 ft and 660 ft from eagles nest tree no obtrusive facilities or major habitat modifications shall occur.  If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, this buffer shall extend up to 0.5 miles.  No blasting, logging and other noisy, disturbing activities should occur during the nesting period (March 1 – August 31) within the primary or secondary zones.

Extremely noisy activities such as road construction or other activities that occur within the Secondary Zone shall be conducted outside the nesting period to avoid disturbance to eagles.  If activities occur in proximity to a nest site, employ an individual qualified to observe and assess the impact of such activities on nesting eagles.  Behavior generally associated with disturbed eagles includes alarm calls, birds flushed from their nest or perch, and aggressiveness.

If nest trees are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 786-3503 or (907) 271 – 2772, before starting construction activities, for further site evaluation.  This is an advisory.  Do what is required to keep from disturbing a nesting eagle.

CR1071-081210

Special Provision

Add the following:

If water is required for a construction purpose from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource manager, and provide a copy to the Engineer.  The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8645.

CR7(02/08/10)

Add the following:

Prior to clearing near wetland areas, flagging, staking, or fencing of the clearing limits shall be installed along the clearing boundaries in a clearly visible manner to ensure that no incidental disturbance occurs outside the permitted boundaries.  Prior to commencement of ground-disturbing work adjacent to wetlands or creeks, a more conspicuous, semi-permanent barrier fence, e.g. orange snow fencing attached to posts that also could serve to support the silt fencing, shall be installed along the clearing limits approved by this permit in order to prevent construction-related physical disturbances, e.g., the operation of equipment, placement of temporary stockpiles, clearing, etc., outside the footprint of the area to be developed.  The fencing shall be installed immediately after the clearing, but before ground disturbance activities take place.  The fence shall be maintained in good working order throughout active construction, and shall be removed when construction is complete.

Fill material must be clean, free from petroleum products and toxic contaminants in toxic amounts.  All fill shall come from previously authorized sources.  Temporary storage of excavated materials within the project boundaries, and disposal of excavated materials off-site must be managed to prevent sediment from being carried into adjacent wetlands and waters, and to prevent leachate from degrading water quality.  No fill shall be temporarily stored or placed in wetland areas.

Standard Modification

Add the following paragraphs:

7.	Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:

Before beginning operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Before demobilization, the Contractor shall repair damages attributed to its operations.  The Contractor agrees that costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result there from, together with permits required by law for such dumping.  A copy of permission, waiver of claims, and permits shall be filed with the Engineer before beginning work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.

E35-012707

Special Provision

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity Disadvantaged Business Enterprise and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A 301

EEO-1 Certification	Form 25A 304

ADOT&PF Training Program Request	Form 25A 310

Training Utilization Report	Form 25A 311

Contact Report	Form 25A 321A

DBE Subcontractable Items	Form 25A 324

DBE Utilization Report	Form 25A 325C

Summary of Good Faith Effort Documentation	Form 25A 332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D 55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

S80(01/22/02)

SECTION 108

PROSECUTION AND PROGRESS

- Special Provision

108-1.01 SUBLETTING OF CONTRACT. Delete paragraph four and replace with the following:

Submit the Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or a subcontractor sublets any portion of the Contract.  The certification will be accepted by the Department in lieu of written approval of subcontracts.  The Department maintains the authority to review subcontracts, require prior written approval of subcontracts, and to deny permission to sublet work.  The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

1.	The Contractor shall ensure the following for each subcontract (agreement):

- The Department is furnished with one completed Contractor Self certification, Form   25D-042, and two copies of the subcontract signed by both parties and including item descriptions and prices of subcontracted work before the subcontracted work begins;

- The subcontractors have submitted a Bidder Registration, Form 25D-6;

- The required prompt payment provisions of AS 36.90.210, as well as other items listed in Form 25D-042, are included in the subcontracts;

- The subcontractors pay current prevailing rate of wages according to subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for work performed on the project; and

- Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

R57(01/02/08)

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete the last sentence of the first paragraph in item 1. A progress schedule. and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

R261(12/13/02)

Add the following:

A dewatering plan shall be submitted to the Department at least 45 days prior to dewatering activities so that the Department can coordinate with the Corps of Engineers and provide at least 30 days for their review, as required by the Section 404 permit.

Agency Pre-construction Meeting – The Contractor shall meet with the Engineer, the Corps of Engineers, and other interested federal, state, and local agencies to review permit conditions and discuss authorized work to ensure the goals and requirements of this permit are understood.  The agency pre-construction meeting shall be held a minimum of 10 days prior to commencement of construction.  Subcontractors responsible for sensitive dirt work shall be included.

Construction Meetings – Regularly scheduled bi-weekly meetings with the parties noted above shall be conducted during construction.  The purpose of the meetings will be to discuss project progress, schedule, permit compliance, and other issues as deemed necessary.  The first meeting will be held after the staking of the clearing limits, but prior to actual clearing.  Additional meetings besides those that are regularly scheduled also may be warranted and may be called by either the Corps of Engineers or the Department.  The Engineer will arrange the meeting place and time for these bi-weekly meetings.

SECTION 109

MEASUREMENT AND PAYMENT

- Special Provision

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence:  “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK.

Under item 3.  Equipment, item a. add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

R14(4/31/05)

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:

The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16.

E11(6/30/04)

Special Provisions

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as the Department deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

1.	Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE).  An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification.  For purposes of soliciting DBE participation on a project and to count toward a Contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer.  A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A 324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A 325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A 325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE.

1.	Phase I - Bid.  Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment.  Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

(1)	A description of the work that each DBE will perform;

(2)	The dollar amount of participation by the DBE firm;

(3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

(4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report.  Form 25A 325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A 332A and attachments) and DBE Contact Reports (Form 25A 321A) if the Contractor submits less DBE utilization on Form 25A 325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A 325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement.  If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

(1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

(2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT.

1.	Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A 324) prior to bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening.  The bidder must give the DBEs no less than 5 days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.  DBEs certified to perform work items identified on Form 25A 324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A 321A).

d.	Non-competitive DBE quotes may be rejected by the bidder.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10 percent higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service.  Bidders must have a non-DBE subcontractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A 321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

2.	Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appeal able to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.  CUF is limited to that of a:

a.	regular dealer;

b.	manufacturer;

c.	broker;

d.	subcontractor;

e.	joint-venture; or

f.	prime contractor.

2.	Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.  (This does not affect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of:

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

(1)	The work performed will be necessary and useful work required for the execution of the Contract.

(2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

(3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

(4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

(5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

(6)	Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

(7)	The DBE will control all business administration, accounting, billing, and payment transactions.  The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, report on Form 25A 336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either:

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either:

(1)	increasing the participation of other DBEs on the project;

(2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

(3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of No CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appeal able to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100 percent of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subcontractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A 325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.

S33(11/17/00)

- SECTION 201

CLEARING AND GRUBBING

Special Provision

201-3.01 GENERAL.  Add the following:  The Engineer will designate the clearing limits with survey flagging and stakes.  Timber with a 5 inch diameter or larger at breast height shall be cut into 8-foot lengths, de-limbed, and stacked at locations approved by the Engineer for public removal.  These locations shall be adjacent to the nearest side street or other approved site which does not create a traffic hazard due to lack of adequate parking for the public.  The Department will notify the public of the availability of the timber once it has been stacked.  The Contractor shall schedule the clearing and grubbing work so as to provide two weeks for the public to access those areas of the project where such timber is available prior to completion of the clearing and grubbing work in those areas. The Contractor shall dispose of the timber left by the public after the 2 week time period.

The Contractor shall perform the work necessary to preserve and/or restore land monuments and property corners from damage.  A land monument or property corner that is disturbed shall be restored according to Section 642 at the Contractor's expense.  An undisturbed area 5 foot in diameter may be left around existing monuments and property corners.  A list of land monuments and property corners is shown on the Right of Way maps.

The Contractor shall be responsible for replacement of trees removed beyond the staked clearing limits as approved by the Engineer.  Provide replacement at the same size and of the same species removed.  If the size of unauthorized removed trees renders replacement infeasible on a one-for-one replacement basis, then the Engineer will determine the cumulative caliper size removed and replace the trees on the basis of one-inch caliper per every half inch of caliper removed.  Trees provided for replacement shall have a minimum caliper size of three inches and shall be approved by the Engineer.

Bird Timing Window:  To prevent impacts to nesting birds, no land clearing, fill placement, excavation, or other construction activities will be allowed between May 1 and July 15, unless the site has been sufficiently disturbed by May 1 to eliminate suitable nesting habitat, and continuous activity will occur on the site through July 1.  Any deviation from the schedule shall be coordinated with the U.S. Fish and Wildlife Service.

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15.

CR2011-081210

Grubbing (disturbing the vegetative mat) shall not occur in areas that are cleared beyond the toe of the permanent fill.

No spruce wood shall be cut and given away as firewood unless the wood is completely debarked.

201-4.01 METHOD OF MEASUREMENT.  Add the following:  The work required to cut, de-limb, and stack timber for public removal and to preserve and restore land monuments and property corners will be subsidiary to Item 201(3B) Clearing and Grubbing.

- SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

- Special Provision

202-1.01 DESCRIPTION.  Add the following:  This work shall also include the removal of gas pipe, removal of storage tanks (either fuel or septic) and the abandonment of ground water wells.

This work includes removing the existing Campbell Creek Bridge Number 972.

The existing Campbell Creek Bridge is approximately 63 feet long and 29 feet wide. The original Contract Drawings and Shop Drawings for the existing bridge can be obtained from the office of the Chief Bridge Engineer at 3132 Channel Drive, Juneau, AK 99801.

These drawings are available for informational use only and the Department neither warrants nor represents that they accurately depict the configuration of the existing bridge. Where details of the work under this Contract are dependent on the dimensions of the existing bridge, verify the controlling field dimensions and adjust dimensions of the work to fit existing conditions.

202-3.01 GENERAL.  Add the following:  The removal of foundations and structures shall include removal of utility lines, sidewalks, and other attached appurtenances.

Cut the ends of retaining walls to remain after partial removal neat and true with no shatter outside the removal area.

Remove septic or fuel tanks according to the State of Alaska Department of Environmental Conservation (DEC) regulations.  Remove or abandon wells according to DEC regulations.

Remove and dispose of asbestos cement pipe in accordance with local, state, and federal regulations.

Add the following:

Carefully remove fences designated by the Engineer to the right-of-way limit, or to the end of the span beyond the right-of-way limit.  These materials belong to the property owners, and shall be salvaged and stacked neatly in their yards.  After the construction of noise barrier or fence is complete, use salvaged fencing to fill possible fencing gaps behind the property line.  Use salvaged fencing according to Section 607, for reconstructed fences.

CR17(10/24/02)

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES.  Remove this Subsection in its entirety and replace with the following:

Do not remove bridges, culverts and other drainage structures in use by traffic until satisfactory arrangements have been made to accommodate traffic.

1.	Culverts and minor structures. Do not remove manholes, inlets, valves or any other portion or portions of the sewer or water systems until the new systems are in operation or suitable arrangements have been made for the diversion, interruption, or a temporary system has been installed.

When flexible pipe is designated in the Contract documents to be abandoned in place, crush and flatten the ends before covering. Securely plug other conduits by an approved method.

2.	Bridges.

a.	Submittals. No less than sixty (60) days prior to commencing bridge removal, submit a Bridge Demolition Plan. The Bridge Demolition Plan will include, but is not limited to:

(1)	Proposed bridge removal date.

(2)	Contact names and phone numbers for individuals responsible for the demolition.

(3)	Schematic and detailed drawings identifying the method and sequence of removal.

(4)	Schematic and detailed drawings identifying and detailing means of access to the bridge during demolition.

(6)	Methods to prevent debris from entering the waterway.

(6)	A list of the type, number and size of all proposed equipment to be used.

(7)	Details of temporary support shoring and bracing, if required.

(8)	Schematic drawings specifying crane locations and lifting locations.

(9)	A listing of the size and weight of bridge subassemblies to be transported from the site.

(10)	A schematic drawing identifying the proposed waste site location.

Receipt of the Bridge Demolition Plan by the Engineer does not constitute approval of the plan or the adequacy of the plan.

b.	Demolition.	 Remove and dispose of all bridge steel, concrete and timber bridge elements. Do not damage new construction during demolition operations.

Do not allow debris from bridge removal operations to enter the waterway.

Maintain the integrity of undemolished portions of the bridge structure during demolition operations.

c.	Disposal. Dispose of all materials in a Contractor-furnished waste disposal site or in a manner approved by the Engineer.

d.	Cleanup. In addition to the requirements of Subsection 104-1.05, dress all bridge slopes or embankments according to the Contract documents. Dress slopes not designated in the Contract documents to conform to the natural ground surface or blend as directed. Fill all excavations and depressions.

202-3.04 REMOVAL OF PIPE.  Add the following:  During project construction, ENSTAR Natural Gas Company will abandon existing gas pipelines.  Follow the procedures given in subsection 105-1.06 Cooperation With Utilities, when working around gas pipelines until they have been abandoned.  Once the pipelines are abandoned, remove abandoned natural gas pipe within the right-of-way that are in conflict with the work and dispose of pipes off the project limits.

R112(10/24/02)

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:

Removed pavement material, including sidewalks and curbs, is the property of the Contractor.  Handle and transport materials according to the DEC regulations.  Store materials at a Contractor DEC approved site.

Removed pavement, sidewalks, and curbs may be used for embankment construction if it is not exposed at the completed embankment surface.  Maximum allowable dimension of broken materials is 6 inches.  The use of pavement, sidewalk, and curb in the embankment requires written approval and direction for use from the Engineer.

Dispose of removed pavement, sidewalks, and curbs not wanted by the Contractor and not used in the project, according to Subsection 3.09.

Add the following Subsection.

202-3.09 DISPOSAL OF PAVEMENT, SIDEWALKS, AND CURBS.

Pavement planing materials not being used in the project, stored at a Contractor DEC approved site, provided to the local DOT Maintenance and Operations Yard, or disposed of at a previously approved DEC disposal site require a DEC Solid Waste Disposal Permit.

Disposal sites shall be outside the project limits unless directed otherwise, in writing, by the Engineer.  Obtain written consent from the property owner.  Dispose of solid waste materials, pavement, sidewalk, and curb (including handling, transporting, storing and disposing) according to the DEC regulations.

A DEC Permitting Officer in Anchorage may be contacted at (907) 269-7590.

202-4.01 METHOD OF MEASUREMENT.  Add the following:

4.	Lump Sum. All work required without measurement of quantities.

5.	Remove and Reinstall Single Mail Box. By each existing mail box removed and reinstalled in the same location or in a new location as directed by the Engineer.

6.	Remove and Replace Fence. By the linear foot of existing fence removed and replaced.  Fence shall be replaced with like fencing.

7.	Remove and Reinstall Sign. By each existing sign removed and reinstalled in the same location or in a new location as directed by the Engineer.

202-5.01 BASIS OF PAYMENT.  Add the following:

Costs incurred from hiring a moving company to relocate the DOT&PF’s field office equipment shall be subsidiary to the Removal of Structures and Obstructions pay items.

Payment includes removing, handling, transporting, and disposing of the existing Campbell Creek Bridge, Bridge Number 972, in its entirety in accordance with this Contract.  This work includes the removal of any utilities or other facilities mounted to the bridge.

Removal of gas pipe shall be subsidiary to Removal of Structures and Obstructions pay items.

Acquiring a solid waste disposal permit from DEC is subsidiary to 202 Pay Items.

Removal and disposal of asbestos cement pipe is subsidiary to Pay Item 202(5).

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

202(10A)	Remove and Reinstall Single Mail Box	Each

202(12A)	Relocate Cluster Mail Box	Each

202(13)	Removal of Existing Bridge No. 972	Lump Sum

202(13A)	Remove and Replace Fence	Linear Foot

202(17A)	Remove and Reinstall Sign	Each

- SECTION 203

EXCAVATION AND EMBANKMENT

Special Provision

203-1.01 DESCRIPTION.  Add the following:

This work shall consist of excavation, grading, seeding, and filling at the location(s) shown in the Plans.

Provide compost socks shown on Q Sheets and as specified in Section 690 and 744 of these Special Provisions.

203-3.01 GENERAL.  Add the following:  The Contractor shall submit required permits and clearances for Contractor-supplied material sites (as required by subsection 107-1.01) for submittal to the Corps of Engineers before beginning use of these sites.

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL.  Add the following:

Compact the embankment within 20 feet of a bridge abutment full width to not less than 100 percent of the maximum density.  Material used within this zone shall be graded to pass the 3 inch sieve.

203-4.01 METHOD OF MEASUREMENT.

Add the following:

9.	Item 203(27).  Measurement of bioswale grading, whether flat bottom or “V” ditch, will be measured for payment by lump sum for excavation grading and fill for shaping bioswales as designated, constructed, and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT.  Add the following:

Payment for bioswale grading will be full compensation for furnishing equipment, labor, tools, and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

Seeding of bioswales will be paid for under Item 618(1C) Seeding, Schedule C.

Payment for Item 203(6A) will be full compensation for material, labor, equipment, tools, and incidentals necessary to complete the work.  This includes clearing and grubbing not already paid for under 201(3B).

Grading and placement of material used within 20 feet of bridge abutments will not be paid for directly but will be subsidiary to Pay Item 203(6A) Borrow, Type A.

Payment for excavated and embankment material for landscape items outside of the roadway template shall be incidental to their respective 621 pay item.

Disposal of excavated material will be paid for under Item 203(3) Unclassified Excavation.

Grading the ditch for Cordova Street Extension will be paid for under Item 203(3) Unclassified Excavation.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 203(6A) | Borrow, Type A | Ton |
| 203(27) | Bioswale Grading | Lump Sum |

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS
AND MINOR STRUCTURES

Special Provisions

204-2.01 MATERIALS.  Add the following:

Bedding and foundation material pay item is for sanitary sewer replacement in Cordova Extension project.  It shall conform to the following gradation and shall be screened alluvial material, uncrushed:

| U.S. Standard Sieve Size | Cumulative Percent Passing By Weight |
| --- | --- |
| 1/2" | 100 |
| 3/8” | 85 - 100 |
| No. 4 | 10 - 30 |
| No. 8 | 0 – 10 |
| No. 16 | 0 - 5 |

Standard Modifications

204-3.01 CONSTRUCTION REQUIREMENTS.  In the first sentence of paragraph four, delete:

“bedding and”

E37(01/27/07)

Special Provisions

Add the following after the third paragraph:

Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.

CR204(02/06/08)

Add the following:

Bedding and foundation material shall extend from the PVC pipe out 12 inches on the top and sides of the pipe and 3 feet under the pipe.  Provide bedding and foundation material for sanitary sewer manholes on Franklin Drive a directed by the Engineer.

204-4.01 METHOD OF MEASUREMENT.  Add the following:

Bedding and Foundation Material shall be measured per ton.

204-5.01 BASIS OF PAYMENT.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

204(6)	Bedding and Foundation Material	Ton

Replace Section 205 with the following:

SECTION 205

EXCAVATION AND FILL FOR MAJOR STRUCTURES

205-1.01 DESCRIPTION. Excavate and backfill for bridges, retaining walls, concrete box culverts, and other major structures.

Furnish all resources to place and remove cribbing or cofferdams. Perform all required sheeting, bracing, bailing, pumping, draining, and grouting.

Replace unsuitable material encountered below the elevation of the bottom of footings.

205-2.01 MATERIALS. Use materials that conform to the following:

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Silica Fume	Section 701

Fine Aggregate	Subsection 703-2.01

Porous Backfill Material	Subsection 703-2.10

Structural Fill	Subsection 703-2.13

Chemical Admixtures	Subsection 711-2.02

Water	Subsection 712-2.01

CONSTRUCTION REQUIREMENTS

205-3.01 EXCAVATION.

1.	General. Clear and grub prior to starting excavation according to the requirements of Section 201.

Cut all rock or other hard foundation material to a firm surface, either level, stepped, or serrated, as directed, and remove all loose material.

Do not disturb material below the bottom of spread footings, unless otherwise noted in the Contract.

Excavate to the bottom of footing prior to driving piles.  Do not excavate below the footing elevation unless otherwise noted in the Contract. When swell results from driving piles, excavate the footing area, to the elevation of the bottom of the footing, as shown on the Plans. When subsidence results from driving piles, backfill with structural fill material, to the elevation of the bottom of the footing, as shown on the Plans.

Dispose of all necessary excavated material as provided in Subsection 203-3.01.

Do not alter streambed channel and do not place excavated materials in natural stream channels, unless shown on the Plans or approved in writing.

Give the Engineer in writing no less than 15 days advance notice prior to beginning excavation for spread footings to allow for inspection of the excavated surface. With this notification, identify the location and specify a time period of no less than two days for the Department to inspect the excavated surface. Dewater and remove all debris from the surface prior to the Department's inspection. Obtain the Engineer’s approval of the excavated surface prior to the placement of any formwork or foundation materials. Account for the time required by the Department to perform the inspection in the progress schedule submitted under Subsection 108-1.03. Suspension of work to allow for inspection is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

2.	Foundations on Bedrock. Excavate for footings founded on bedrock, to the neat lines of the footings. Fill overbreak areas outside the neat lines of footings, with Class A concrete, at no additional cost to the Department.

3.	Cofferdams. Use cofferdams that do not affect the character of the finished work.

Design cofferdams according to the AASHTO Guide Design Specifications for Bridge Temporary Works. Submit detailed drawings, designed and sealed by a Professional Engineer registered in the State of Alaska.

205-3.02 STRUCTURAL FILL. Place Structural Fill in 6-inch layers, compacted to meet Section 205. Place Structural Fill as uniformly as possible on the sides of structure. Avoid placing the fill material in a manner that could damage the structure. When placed against concrete, place Structural Fill in accordance with Section 501.

Controlled Low-Strength Material may be used as an alternative source for Structural Fill if approved by the Engineer.

205-3.03 BACKFILL. Unless otherwise noted, reuse excavated material for backfill where shown on the Plans. If additional backfill is required, use material meeting Selected Material, Type C (Subsection 703-2.07), or as approved by the Engineer. Place backfill material in layers, and compact to the satisfaction of the Engineer. Bench slopes within the area to be filled.

Place underwater backfill in natural stream channels without compaction or layer requirements.

Place backfill as uniformly as possible on all sides of structural units. Avoid unbalanced loading of backfill which could damage the structure. When placed against concrete, place backfill according to the requirements of Section 501.

No ponding or jetting of backfill is allowed.

205-3.04 POROUS BACKFILL. Place porous backfill material continuously within a vertical plane 1 foot behind retaining walls and abutments, unless otherwise shown on the Plans.

Where weep holes are shown on the Plans or required by the Specifications, place not less than 1 cubic foot of Porous Backfill material in the fill at each hole, securely tied in a burlap bag, or wrapped with an acceptable geotextile fabric. Extend the wrapped Porous Backfill material at least 6 inches above the hole.

205-3.05 COMPACTION.  Compact material in conformance with the following, using moisture and density control unless the Engineer determines that such controls are not feasible.

1.	Compaction With Moisture and Density Control. The maximum density will be determined by WAQTC FOP for AASHTO T 180 or ATM 212.

Water or aerate as necessary to provide the approximate optimum moisture content for compaction.  Compact each layer to not less than 98% of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

2.	Compaction Without Moisture and Density Control. Compact by routing construction equipment and/or rollers uniformly over the entire surface of each layer before the next layer is placed. Compact until the material does not rut under the loaded hauling equipment.

Keep dumping and rolling areas separate. Do not cover any lift by another until the Engineer has determined the required compaction is obtained.

205-3.06 CONTROLLED LOW-STRENGTH MATERIAL. Provide Controlled Low-Strength Material (CLSM) that is a self compacting, cementitious, flowable material requiring no subsequent vibration or tamping to achieve consolidation and meeting the following:

1.	28-day compressive strength between 100 psi minimum to 300 psi maximum as determined by ASTM D 4832.

2.	Slump between 3 inches minimum to 10 inches maximum as determined by WAQTC FOP for AASHTO T 119.

3.	Aggregate consisting of crushed or naturally occurring granular material, containing no deleterious matter, and with 100 percent of the aggregate passing a 3-inch sieve.

Do not place CLSM on frozen ground, in standing water, or during wet weather conditions. Place CLSM only if the air temperature is 40 °F minimum and rising. Ensure the material temperature is at least 50 °F while being placed.

Do not apply loads to the CLSM until the compressive strength reaches 50 psi.

Acceptance will be based on a Certificate of Compliance. Provide a Certificate of Compliance for each batch of CLSM according to Section 106.

205-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Excavation. By the actual volume of material removed, excluding the following:

a.	Material removed prior to measurement of the original ground surface.

b.	Material outside of the vertical planes 18 inches outside of and parallel to the neat lines of the footings, except that the limit will be vertical planes coinciding with the neat lines of the seals when seals are shown on the Plans.

c.	Material outside of vertical planes coinciding with the neat lines of footings excavated in solid rock.

d.	Embankment material placed above the elevation of the bottom of footings.

e.	Material within the staked limits of other types of excavation for which payment is otherwise provided.

2.	Structural Fill. By the actual volume of material accepted in final position.

3.	Porous Backfill Material. By the actual volume of material accepted in final position.

4.	Backfill. Material for Backfill will not be measured for payment.

5.	Controlled Low-Strength Material. By the actual volume of material accepted in final position.

205-5.01 BASIS OF PAYMENT. Material for backfill is subsidiary.  Clearing and grubbing within the excavation limits is subsidiary.

Porous Backfill Material includes all materials and construction operations for making weep holes. When item 205(4), Porous Backfill Material, does not appear in the bid schedule, Porous Backfill is subsidiary.

Excavation, removal, and disposal of material unsuitable for Structural Fill is subsidiary.

Excavation for footings ordered by the Engineer, at a depth greater than 3 feet below the bottom of such footings shown on the Plans will be paid for as extra work under Subsection 109-1.05.

Where a bid item for cofferdams does not appear in the bid schedule, the work necessary to protect the excavation and control water is subsidiary.

When Controlled Low-Strength Material is used as an alternative to Structural Fill, Controlled Low-Strength Material is paid at the Structural Fill value.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

205(1)	Excavation for Structures	Cubic Yard

205(2)	Cofferdam	Lump Sum

205(3)	Structural Fill	Ton

205(4)	Porous Backfill Material	Cubic Yard

205(5)	Controlled Low-Strength Material	Cubic Yard

- SECTION 301

AGGREGATE BASE AND SURFACE COURSE

- Special Provision

301-2.01 MATERIALS.  Add the following after the first sentence:  Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| - Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.  R176(01/24/07)

301-3.01 PLACING.  Add the following:  Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  R26(09/01/89)

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based determined by control strip method ATM 412.  Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1) Aggregate Base Course at the unit price shown on the bid schedule for that item.  R176(01/24/07)

Special Provisions

Replace Section 306 with the following:

SECTION 306

ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION.  Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown in the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein.  Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt cement in the ATB.

TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Cement) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Cement |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |

*	Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3.  For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile.  Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt cement content.  For mixes with RAP, provide JMD gradation with and without RAP.  Provide calibration data if WAQTC FOP for AASHTO T308 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD.  Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt cement proposed for use in the ATB.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved.  Approved changes apply only to ATB produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.  The fee will be included under Pay Item 306(6) Asphalt Price Adjustment - Quality.

306-2.02 AGGREGATES.  Conform to Subsection 703-2.04.  Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT CEMENT.  Conform to 702-2.01 and the following:

The total asphalt cement content may be a combination of PG 52-28 and the residual asphalt cement/binder in the RAP, or only PG 52-28.  Documentation and conformance is required for the PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702, before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt cement is required.

306-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the ATB according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations.  Address the sequence of operations.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP).  Process existing pavement removed under Subsection 202-3.05 and 3.06 so material passes the 1 1/2" sieve.  Stockpile the material separately from the crushed aggregates.  Perform one gradation and one asphalt cement content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS.  Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of ATB buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT.  Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment.  Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material.  Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT.  Use self propelled asphalt pavers with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations.  Specifically equip pavers to prevent segregation between the hopper and augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE.  Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss; and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute ATB.  Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not the cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION.  Compact the ATB by rolling thoroughly and uniformly.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Prevent indentation of ATB.  Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of ATB.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

306-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE.  Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 ft straightedge.  Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS.  Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch.  Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

306-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Asphalt Treated Base.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

2.	Asphalt Cement.  By the ton, as follows.

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement, except ATM 405 will not be used when RAP is included in the mixture.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing ATB for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste ATB will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimal asphalt cement content specified in the JMD.

3.	Asphalt Price Adjustment - Quality.  Determined under Subsection 306-4.03 Evaluation of Materials for Acceptance.  Also included in the measurement are the fees specified in Subsections 306-2.01, 4.02, 4.03 and 5.01.

306-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 306-4.03 Evaluation of Materials for Acceptance, and is included in Item 306(6) Asphalt Price Adjustment - Quality.  Fees assessed are also included in Item 306(6).

ASPHALT TREATED BASE

The quantity of ATB produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 10,000 tons.  The lot will be divided into sublots of 1000 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.

If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 306-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 3,000 tons and 10,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 1000 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  ATB quantities of less than 600 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  ATB quantities of 600 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 306-4.03 except as noted.

For Contract quantity of less than 3,000 tons, ATB will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the ATB to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any ATB that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Asphalt treated base mix samples taken for the determination of asphalt cement content will be taken randomly from behind the paver screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308, except ATM 405 will not be used when RAP is included in the mixture.

2.	Aggregate Gradation.

ATB without RAP.  Samples taken for the determination of virgin aggregate (aggregate) gradation will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2.  Locate diverter devices for obtaining aggregate samples on the conveyor system delivering combined aggregates, not including RAP, into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the ATB.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Aggregate samples from the cold feed conveyor will be used to determined the gradation according to WAQTC FOP for AASHTO T 27/T 11 or the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

ATB with RAP.  For ATB samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

The Engineer will determine and mark the location(s) where the Contractor will take each mat core sample.  The location(s) for taking mat core samples will be determined using a set of random numbers and the Engineer's judgment.

Cut full depth core samples centered on the marks from the finished ATB within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new ATB within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A fee will be assessed for each failure to take core samples, backfill core sample voids, backfill core samples within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.

A retest of any sample outside the limits specified in Table 306-2 may be requested provided the quality control requirements of 306-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 306-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 306-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

306-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  A mat area of finished surfacing that is contaminated with foreign material; is segregated (determined visually or by testing), has a lower density than specified, fails to meet surface tolerance requirements, is flushing or bleeding asphalt cement after compaction is complete, or in any other way determined to be defective is unacceptable according to Subsection 105-1.11.  Correct unacceptable work and materials according to Subsection 306-3.16 and as directed by the Engineer.

Price adjustments in this subsection are addressed under Pay Item 306(6) Asphalt Price Adjustment-Quality.

Price Adjustment Base (PAB)

PAB = $141.25 per ton

ASPHALT TREATED BASE

The total Asphalt Treated Base price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to ATB when the contract quantity equals or exceeds 3000 tons, except as specified in Subsection 306-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03.3 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors for the ATB.  The first factor is the composite pay factor (CPF) and includes gradation and asphalt cement content.  The second factor is the density pay factor (DPF).

A lot containing ATB with a pay factor less than 1.00 will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing ATB that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

ATB rejected based on visual inspection will be tested if requested by the Contractor.  A minimum of two samples will be collected from the rejected ATB and tested.  If test results are within specification limits, payment will be made for the ATB.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be assessed as a fee and paid by the Contractor under Pay Item 306(6) Asphalt Price Adjustment - Quality.  Costs associated with removal and disposal of the rejected ATB are subsidiary to the Asphalt Treated Base Pay Items.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

For a sublot, when gradation and asphalt cement content are determined from separate samples, the individual test results for density, gradation, and cement content, that are not an outlier, will be included in price adjustment.

Quality Level Analysis (QLA).

Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

Pay factors for the remaining test results are computed as follows:

x

1.	Arithmetic mean:

n

x =

∑x

Where:		∑	=	summation of

x 	=	individual test value to xn

n 	=	total number of test values

x

x

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation:  s

n∑(x2) – (∑x)2

s =

n(n-1)

Where:		∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

s 	is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.

s 	is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If s < 0.001:

	Density and all sieves, except the No. 200, s = 0.20.

	Asphalt cement content and the No. 200 sieve, s = 0.02.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 306-2.  The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 99% of MSG.

TABLE 306-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 99 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index:	QU

USL  -  x

QU  =

s

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

s

5.	The Lower Quality Index:	QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit corresponding to a given QU), Subsection 106-1.03.

7.	PL (percent within the lower specification limit corresponding to a given QL), Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation (PFsieve size) and asphalt cement content (PFac) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) combines the gradation and asphalt cement content pay factor from Step 9 for the lot and is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 306-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 306-3

WEIGHT FACTORS

| Sieve Size | Type II Factor “f” |
| --- | --- |
| 1 inch sieve | - |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt % | 40 |

Asphalt Treated Base Price Adjustment = PAB x Q x 0.5 x [(CPF or DPF)* -1.00]

PAB		= Price Adjustment Base

Q 		= tons in Lot

CPF 	= Composite Pay Factor

DPF 	= Density Pay Factor

*CPF or DPF, whichever is lower.

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 306-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 306-4.

Table 306-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 | --- | > 3 | --- | --- | --- | --- | --- | --- |
| Dynamic Shear | > 1.00 kPa | > 1.00 | --- | 0.88-0.99 | --- | --- | --- | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 | --- | --- | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 | --- | --- | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 | --- | 1.001-1.092 | --- | --- | --- | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 | --- | 1.816-2.199 | --- | --- | --- | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 | --- | 5001-5289 | --- | --- | --- | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 | --- | 301-338 | --- | --- | --- | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 | --- | 0.287-0.299 | --- | --- | --- | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF 		= Pay Reduction Factor from Table 306-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to, a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

306-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401, Approach HMA as included in 401 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

306-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items the work and materials associated with:

Asphalt cement, anti-stripping additives, surface tolerance corrections, patching defective areas; removal and disposal of rejected ATB, and the hauling equipment are subsidiary to the Asphalt Treated Base Pay Items.

Item 306(6) Asphalt Price Adjustment - Quality: is the sum of the price adjustments for each material lot and for fees assessed the Contractor including:

	Each mix design subsequent to the approved Job Mix Design (Subsection 306-2.01) will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a fee of $100.00 per sample per day (Subsection 306-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a fee of $100 per hole per day (Subsection 306-4.02).

	Contractor retesting, referee sample testing and Contractor requested testing for visually inspected and rejected asphalt treated base failing to meet specifications will result in a fee being assessed for all costs associated with the test (Subsection 306-4.02, 4.03).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

306(1)	Asphalt Treated Base	Ton

306(2)	Asphalt Cement, Grade PG 52-28	Ton

306(6)	Asphalt Price Adjustment - Quality	Contingent Sum

306(10)	Asphalt Material Price Adjustment - Unit Price	Contingent Sum

CR306-101110

Special Provisions

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

1.	In this Section, HMA refers to Type I, II, III and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

c.	Use of Reclaimed Asphalt Pavement (RAP) is not permitted in HMA, except RAP may be used in HMA, Type II, Class B.

d.	Warm Mix Asphalt (WMA) is not permitted in HMA.

MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

TABLE 401-1
hMA Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| HMA (Including Asphalt Cement) |  |  |
| Stability, Pounds | 1800 Min. | 1200 min. |
| Flow, 0.01 Inch | 8 – 14 | 8 - 16 |
| Voids in Total Mix, % | 3 - 5 | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 75 | 50 |
| Asphalt Cement |  |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 75 | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |  |
| Type I | 12.0 | 11.0 |
| Type II | 13.0 | 12.0 |
| Type III, IV | 14.0 | 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement.

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 401-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving.  HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each Type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate Type and Class of HMA specified.  The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD.  Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 401-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 401-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 401-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.  Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 401(6) Asphalt Price Adjustment – Quality.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04.

Use a minimum of three stockpiles for crushed HMA aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Conform to 702-2.01.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate must remain coated when tested according to ATM 414.  A minimum of 0.25% by weight of asphalt cement is required.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 401-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer:  provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 401-3.02.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips:  Subsection 401-5.01 Basis of Payment and as noted here.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed.  The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is a minimum of 40° F or warmer.  HMA Type II, Class A - Do not place mix after September 15 unless approved by the Engineer in writing.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hours before placement of the test strip HMA.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT.  Costs associated with Subsection 401-3.04 are subsidiary to Section 401 Pay Items.

Vehicles/Equipment.  Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer cover the HMA in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 401-3.16 Patching Defective Areas.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.  Use means and methods approved by the paver manufacturer.  Means and methods may consist of chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact HMA mixtures and reverse without backlash.

Use pneumatic rollers to compact the prelevel/leveling course.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place.  Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2 inch with HMA, Type IV.  Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

	Where the planing equipment breaks through existing pavement, remove 2 inches of existing base material depth and replace with HMA, Type II, Class B.  Cold mix HMA prohibited.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of HMA on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

401-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

401-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA, including leveling (preleveling) course and temporary HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place the final lift until curb and gutter, all types, are installed complete, except as approved by the Engineer.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of each Type of HMA.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required).

When directed by the Engineer, provide density profiles of the mat and longitudinal joints with a nuclear density gauge.  Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 401-2.05.

401-3.14 JOINTS. Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702.  Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal.  Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in elevation of the final surface of adjacent mats each side of the longitudinal joint, at the joint, with a straight edge and by requiring the Contractor to flood the joint surface with water.  The Engineer will determine where and how often to evaluate the joint.  All differences in the surface elevations greater than 1/8 inch or that pond water shall be repaired at no cost to the Department.  Heat the HMA pavement to be repaired with an infrared heater (310˚ F max) and roll flat or add HMA until the joint differential is within tolerance.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 401-4.03.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

NEXT TWO PARAGRAPHS ONLY APPLY TO WEST DOWLING PHASE I PROJECT:

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, intersections, ramps, and lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing, or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 401-3.13 to grade, and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

401-4.01 METHOD OF MEASUREMENT.  Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive or cutting back joints.

b)	By the final HMA surface.

2.	Asphalt Cement.  By the ton, as follows.

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time that tankers be weighed in the Engineer’s presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

5.	Preleveling/Leveling Course.  By weight or Lane-Station (12 foot width).  No deduction will be made for the weight of asphalt cement or anti stripping additive.

6.	Asphalt Price Adjustment – Quality.  Calculated by quality level analysis under Subsection 401-4.03.  Also included in the measurement are the fees and deductions specified in Subsection 401-2.01 and Subsection 401-4.02.

Asphalt Price Adjustment – Quality, does not apply to, and measurements will not be made for: 1) Leveling Course/Prelevel (rut repair) HMA, 2) Temporary HMA, 3) Approach HMA.

7.	Longitudinal Joint and Joint Adhesive.  By the linear foot of longitudinal joint.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 401-4.03 Evaluation of Materials for Acceptance, and is included in Item 401(6) Asphalt Price Adjustment-Quality.  Penalties assessed are also included in Item 401(6).

A mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 401-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each class and Type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5,000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (also for approaches and temporary pavement), HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device or from the stopped conveyor belt according to WAQTC FOP for AASHTO T2 or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

a.	Acceptance Testing.

The Engineer will determine and mark the location(s) where the Contractor will take each core sample.  Core samples will not be taken at bridge decks or the milled edge of existing pavement.

1)	Mat Cores:  The location(s) for taking core samples will be determined using a set of random numbers and the Engineer's judgment.

2)	Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.  Take joint core samples in the presence of the Engineer.

Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new HMA within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A penalty will be assessed for each failure to take core samples or backfill core sample voids within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 200 tons, the contract quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 401(6) Asphalt Price Adjustment-Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each Type of HMA when the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean 	 of the remaining test results is determined:

n

x =

∑x

Where:	∑	= summation of

x 	= individual test value to xn

n 	= total number of test values

(x)

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:	    ∑(x2)      =	sum of the squares of individual test values.

(∑x)2	    =	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 95% of the MSG, the LSL is 92% of MSG, and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt % | TV -0.4 | TV + 0.4 |
| Mat Density % | 92 | 98 |

*Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

USL  -  x

QU  = S

4.	The Upper Quality Index (QU) is computed:

Where:		USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:  LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| Sieve Size | Type I Factor “f” | Type II Factor “f” | Type III Factor “f” |
| --- | --- | --- | --- |
| 1 inch sieve | 4 | - | - |
| 3/4 inch sieve | 4 | 4 | - |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $147.50 per ton

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 401-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

Table 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

PAVEMENT SMOOTHNESS (APPLIES ONLY TO WEST DOWLING PHASE I PROJECT)

The top layer of HMA will be measured according to 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 	= Final quantity of HMA, tons

PrI	= Final measured hot mix smoothness, inches/mile

SF 	= Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities equal or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG, apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

401-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Prelevel/Leveling Course (rut repair) HMA and Temporary HMA as part of 401, Approach HMA as included in 401 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hrs, and ends 00:00 hrs the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP–IB)–(0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB–IPP)–(0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

6.	Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

401-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Asphalt cement, anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, patching defective areas, repair work and materials when planing equipment breaks through existing pavement - Subsection 401-3.07 Preparation of Existing Surface, and the work and materials associated with Subsection 401-3.04 Hauling Equipment are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 401(1F) Hot Mix Asphalt, Preleveling/Leveling Course, Type IV: Asphalt Cement, anti-stripping additives are subsidiary.

Item 401(3) Hot Mix Asphalt, Temporary, Type II, Class B: Asphalt cement, anti-stripping additives, removal and disposal are subsidiary.

Item 401(6) Asphalt Price Adjustment – Quality:  is the sum of the price adjustments for each material lot (excluding the Preleveling/Leveling Course (rut repair) HMA, Temporary HMA and Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

	Each mix design subsequent to the approved Job Mix Design (Subsection 401-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 401-4.02).

	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 401-4.02).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

401(1A)	Hot Mix Asphalt, Type II; Class  A 	Ton

401(1F)	Hot Mix Asphalt, Preleveling/Leveling Course, Type IV; Class B	Lane-Station

401(2)	Asphalt Cement, Grade PG 52-28	Ton

401(3)	Hot Mix Asphalt, Temporary, Type II; Class B	Ton

401(4)	Hot Mix Asphalt, Type     ; Class     	Square Yard

401(6)	Asphalt Price Adjustment - Quality	Contingent Sum

401(8)	Hot Mix Asphalt, Approach, Type     ; Class     	Ton

401(9)	Longitudinal Joint Adhesive	Linear Foot

401(10)	Asphalt Material Price Adjustment - Unit Price	Contingent Sum

CR401(10/11/10)

SECTION 402

TACK COAT

Special Provision

Replace Subsection 402-5.01 with the following:

402-5.01 BASIS OF PAYMENT.  Payment will be made under the pay item asphalt tack coat is applied on.

Special Provision

Add the following Section:

SECTION 408

HOT MIX ASPHALT AND SURFACE TREATMENTS

TYPE V

(Superpave)

408-1.01 DESCRIPTION.  Construct one or more layers of plant-mixed Hot Mix Asphalt (HMA) pavement on an approved surface, to the lines, grades, and depths shown in the Plans.

1.	In this Section HMA refers to Type V, except where noted otherwise.

a.	Use of Reclaimed Asphalt Pavement (RAP) is not permitted in HMA.

b.	Warm Mix Asphalt (WMA) is not permitted in HMA.

408-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.  HMA, Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

MATERIALS

408-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD).  Design the JMD according to AASHTO R35 using the design requirements of Table 408-1, except evaluate the moisture sensitivity using the Alaska Test Manual (ATM) 414 and not AASHTO T 283.

TABLE 408-1

HMA Design Requirements

| DESIGN PARAMETERS |  |
| --- | --- |
| Design ESALs, Millions | 0.3 to < 3 |
| Rut Index, Max., ATM 419 | 3 |
| Asphalt Cement Content, Min. % | 5.0 |

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified.  For acceptance testing, HMA mixture will have the full tolerances in Table 408-2 applied.  The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits.  Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving.  HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1 gallon samples of the asphalt cement proposed for use in the HMA.  Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using the requirements of Table 408-1 for Type V Hot Mix Asphalt.  The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD.  Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 408-2.05, Test Strip construction.

FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 408-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.  If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 408-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved.  Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will asses a fee for each mix design subsequent to the approved Job Mix Design.  The fee will be included under Item 408(6) Asphalt Price Adjustment – Quality.

408-2.02 AGGREGATES.  Conform to Subsection 703-2.04.

Use a minimum of 3 stockpiles for crushed HMA aggregate (coarse, intermediate, and fine).  Place blend material or mineral filler, if any, in a separate pile.

408-2.03 ASPHALT CEMENT.  Conform to 702-2.01.  If not specified, use PG 64-34.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturers certificate of compliance (Subsection 106-1.05).

2.	Conformance test results of the batch (provide prior to delivery as noted above)

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of materials loaded.

6.	Type and percent of anti-strip added.

408-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD.  At least 70% of the aggregate shall remain coated when tested according to ATM 414. A minimum of 0.25% by weight of asphalt cement is required.

408-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the HMA according to Subsection 106-1.03.  Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results.  When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 408-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing.  Include the supplemental process quality controls in the documentation plan.

When directed by the Engineer; provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles.  Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints.  Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined.  Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include:  all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops.  The Engineer will identify these and other areas that require density testing.

2.	Test Strips.  Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis.  Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan.  The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved.  The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer.  The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis.  Make the equipment available for inspection as required by Subsection 408-3.02.  Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Payment for Test Strips:  Subsection 408-5.01 Basis of Payment and as noted here.

a.	Approved.  Test strip construction and material, approved by the Engineer in writing, as meeting the specification requirements will be paid for at the Contract unit prices.  Price adjustments will not be included for quality, unit price, or other.

b.	Failed.  The Engineer may direct the Contractor to remove and dispose of test strips not meeting specification requirements.  Contractor, construct a new test strip or return the surface materials and grade to their original condition as directed by the Engineer.  The materials, construction of, removal and disposal of a failed test strip will be at the Contractor’s expense.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

CONSTRUCTION REQUIREMENTS

408-3.01 WEATHER LIMITATIONS.  Do not place HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place HMA unless the roadway surface temperature is 40F or warmer.  Do not place mix after September 15 unless approved by the Engineer in writing.

408-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of HMA buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hours before placement of the test strip HMA.

408-3.03 ASPHALT MIXING PLANTS.  Meet AASHTO M 156.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

408-3.04 HAULING EQUIPMENT.  Costs associated with Subsection 408-3.04 are subsidiary to Section 408 Pay Items.

Vehicles/Equipment.  Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use.  Be prepared to demonstrate deployment of the cover when hauling material or empty.  Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials.  When directed by the Engineer cover the HMA in the hauling vehicle(s).

Roadway Maintenance.  Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations.  Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options.  At a minimum, the cleaning station will include the materials and means to:

(1)	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

(2)	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

(3)	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris.  The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s).  Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 408-3.16 Patching Defective Areas.

408-3.05 ASPHALT PAVERS.   Use self propelled asphalt pavers having a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers.  Use means and methods approved by the paver manufacturer.  Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices.  When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

408-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact HMA mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

408-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks.  Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place.  Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2 inch with HMA, Type IV.  Compact the prelevel/leveling course using pneumatic-tire rollers.  The Engineer’s approval of the material and material installation is required.  The Engineer will inspect the material and material installation.  Correct material and material installations identified by the Engineer as required by the Engineer for approval.  Density testing is not required for the leveling course (prelevel) material, material installation.

	Where the planing equipment breaks through the existing pavement, remove 2 inches of existing base material depth and replace with Section 401 HMA; Type II, Class B.  If Section 401 is not included in the project special provisions use the HMA Type specified for the immediate layer of HMA to be placed over the planed surface.  Cold mix HMA prohibited.  Repair work and materials are subsidiary to the HMA Pay Items.

During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402.  Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material.  Allow tack coat to break before placement of HMA on these surfaces.

408-3.08 PREPARATION OF ASPHALT.  Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

408-3.09 PREPARATION OF AGGREGATES.  Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

408-3.10 MIXING.  Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD.  Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

408-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered.  Changes in the JMD, visible or otherwise, are cause for rejection.  Changes may include:  visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

408-3.12 PLACING AND SPREADING.  Use asphalt pavers to distribute HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density.  Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less.  Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place the final lift until curb and gutter, all types, are installed complete, except as approved by the Engineer.

Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

408-3.13 COMPACTION.  Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.  Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 93% MSG is considered segregated and not in conformance with the requirements of the Contract.  The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 96% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of each type of HMA.  The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

When directed by the Engineer, provide density profiles of the mat and longitudinal joints with a nuclear density gauge.  Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 408-2.05.

408-3.14 JOINTS.  Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting.  Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities.  Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain.  Use a power saw or other method approved by the Engineer.  Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer.  Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702.  Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal.  Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in elevation of the final surface of adjacent mats each side of the longitudinal joint, at the joint, with a straight edge and by requiring the Contractor to flood the joint surface with water.  The Engineer will determine where and how often to evaluate the joint.  All differences in the surface elevations greater than 1/8 inch or that pond water shall be repaired at no cost to the Department.  Heat the HMA pavement to be repaired with an infrared heater (310˚ F max) and roll flat or add HMA until the joint differential is within tolerance.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location that the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the HMA is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150°F.  These joints do not need to be tacked and will not be measured or evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

408-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge.  Correct variations from the testing edge, between any two contacts, greater than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, intersections, ramps, and lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band.  Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

408-3.16 PATCHING DEFECTIVE AREAS.  . Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing or bleeding asphalt after compaction is completed or is in any way determined to be defective.  Do not skin patch. Remove defective HMA for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh HMA according to Subsection 408-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the HMA Pay Item.

408-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

1.	Hot Mix Asphalt.

a)	By weighing, no deduction will be made for the weight of asphalt cement, anti-stripping additive or cutting back joints.

b)	By the area of final HMA surface.

2.	Asphalt Cement. By the ton as follows:

Method 1:

Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the JMD.

Method 2:

Supplier's invoices minus waste, diversion, and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing HMA for one project only.

The Engineer may direct, at any time tankers be weighed in the Engineers presence before and after unloading.  If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement.  The Engineer will determine the method.  The weight of asphalt cement in waste HMA will be calculated using the target value for asphalt cement as specified in the JMD.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the JMD.

3.	Job Mix Design. When specified, Contractor furnished JMD(s) will be measured as one according to the HMA Class and Type.

4.	Temporary Pavement.  Section 401.

5.	Preleveling/Leveling Course.  Section 401.

6.	Asphalt Price Adjustment – Quality.  Calculated by quality level analysis under Subsection 408-4.03.  Also included in the measurement are the fees and deductions specified in Subsection 408-2.01 and Subsection 408-4.02.

Asphalt Price Adjustment – Quality, does not apply to, and measurements will not be made for Approach HMA.

7.	Longitudinal Joint and Joint Adhesive.  By the linear foot of longitudinal joint.

408-4.02 ACCEPTANCE SAMPLING AND TESTING.  The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 408-4.03 Evaluation of Materials for Acceptance and is included in Item 408(6) Asphalt Price Adjustment-Quality.  Penalties assessed are also included in Item 408(6).

A mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 408-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

HOT MIX ASPHALT

The quantity of each class and type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to Subsection 408-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  HMA quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to Subsection 408-4.03 except as noted.

For Contract quantity of less than 1,500 tons, (also for approaches) HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

The Engineer will determine where samples are taken.

1.	Asphalt Cement Content.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403 as directed by the Engineer.  HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2, or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

a.	Acceptance Testing.

The Engineer will determine and mark the location(s) where the Contractor will take each core sample.  Core samples will not be taken at bridge decks or the milled edge of existing pavement.

1)	Mat Cores:  The location(s) for taking core samples will be determined using a set of random numbers and the Engineer's judgment.

2)	Longitudinal Joint Cores:  The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint.  Take joint core samples in the presence of the Engineer.

Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling.  Neatly core drill one six inch diameter sample at each marked location.  Use a core extractor to remove the core - do not damage the core.  Backfill and compact voids left by coring with new HMA within 24 hours.

The Engineer will immediately take possession of the samples.  Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A penalty will be assessed for each failure to take core samples or backfill core sample voids within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting.  A retest of any sample outside the limits specified in Table 408-2 may be requested provided the quality control requirements of 408-2.05 are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot.  The Engineer will mark the sample for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

ASPHALT CEMENT

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the Contract quantity of asphalt cement is between 85 – 200 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 408-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

Price adjustments in this subsection are addressed under Item 408(6) Asphalt Price Adjustment – Quality.

HOT MIX ASPHALT

The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each type of HMA when the contract quantity equals or exceeds 1,500 tons, except as defined in Subsection 408-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected HMA and tested if requested.  If test results are within specification limits, payment will be made for the HMA.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment.  Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if a sieve size on the gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

( x )

The arithmetic mean 	of the remaining test results is determined:

n

x =

∑x

Where:		∑  = summation of

x   = individual test value to xn

n   = total number of test values

(x)

(x)

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.

is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation (s) after the outliers have been excluded, is computed:

n∑(x2) – (∑x)2

s =

n(n-1)

Where:	∑(x2)	=	sum of the squares of individual test values.

(∑x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2.  The TV is the specified value in the approved JMD.  Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations.  The TV for density is 96% of the MSG, the LSL is 93% of MSG, and the USL is 99%.

TABLE 408-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt Cement % | TV -0.4 | TV + 0.4 |
| Mat Density % | 93 | 99 |

*Tolerances for the No. 200 sieve may not exceed the broadband limits in Table 703-3.

USL  -  x

QU  =

S

4.	The Upper Quality Index (QU) is computed:

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

x -  LSL

QL  =

S

5.	The Lower Quality Index (QL) is computed:

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined.

See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined.

See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) – 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 408-3 gives the weight factor (f), for each sieve size and asphalt cement content.

TABLE 408-3

WEIGHT FACTORS

| Sieve Size | Type V Factor “f” |
| --- | --- |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt Cement Content, % | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $144 per ton

ASPHALT CEMENT

The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 408-4.02.  Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.

Table 408-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339-388 | 389-450 | > 450 |
| Creep Stiffness, m-value m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF	 	= Pay Reduction Factor from Table 408-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

PAVEMENT SMOOTHNESS

The top layer of HMA will be measured according to 408-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= Price Adjustment Base

PQ 	= Final quantity of HMA, tons

PrI	= Final measured hot mix smoothness, inches/mile

SF 	= Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities are equal to or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 408-3.14.

2.	If project average joint density is greater than 92% MSG apply the following incentive:

a.	Longitudinal joint density price adjustment equal to $1.50 per linear foot is added.

408-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402.  Also included is the asphalt material in the Approach HMA as included in 408 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

b.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index.  The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month.  The index applies from the beginning of the period start day 00:00 hours, and ends 00:00 hours the start of the next period.  Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period.  The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation 	= [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

408-5.01 BASIS OF PAYMENT.

Except where specified as individual Pay Items:

Anti-stripping additives, tack coat, crack sealing, surface sealing of longitudinal joints, surface tolerance corrections, patching defective areas, repair work and materials when planing equipment breaks through existing pavement - Subsection 408-3.07 Preparation of Existing Surface, and the work and materials associated with Subsection 408-3.04 Hauling Equipment are subsidiary to the associated Hot Mix Asphalt Pay Items.

Item 408(6) Asphalt Price Adjustment – Quality:  is the sum of the price adjustments for each material lot (excluding Approach HMA) and for deductions and fees assessed.

Deductions and fees assessed:

•	Each mix design subsequent to the approved Job Mix Design (Subsection 408-2.01) for each Type and Class of Hot Mix Asphalt specified will result in a fee of $2500.00 each.

•	Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day (Subsection 408-4.02).

•	Failure to backfill voids left by sampling within the specified period will result in a deduction of $100 per hole per day (Subsection 408-4.02).

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

408(1) 	Hot Mix Asphalt, Type V 	Ton

408(2) 	Asphalt Cement, Grade PG 58-34 	Ton

408(4)	Hot Mix Asphalt, Type    ; Class    	Square Yard

408(6)	Asphalt Price Adjustment – Quality	Contingent Sum

408(8)	Hot Mix Asphalt, Approach, Type     ; Class     	Ton

408(9) 	Longitudinal Joint Adhesive	Linear Foot

408(10)	Asphalt Material Price Adjustment – Unit Price	Contingent Sum

CR408-081210

- SECTION 501

STRUCTURAL CONCRETE

Replace Section 501 with the following:

- SECTION 501

- CONCRETE FOR STRUCTURES

501-1.01 DESCRIPTION. Furnish, place, finish, and cure Portland cement concrete for structure construction. Use the class of concrete noted on the Plans unless otherwise specified.  Concrete headwall shall be constructed of Class W concrete.

- classes of concrete

- Class A:	General use concrete

Class A-A:	Concrete where improved strength and durability is required

Class P:	Concrete where strength in excess of 5000 psi is required

Class DS:	Concrete for drilled shaft foundations

Class W:	Minor concrete that meets the requirements of Subsection 501-2.02 for Class A concrete

501-1.02 DEFINITIONS.

ADMIXTURE. A material other than water, aggregate, hydraulic cement, pozzolan, and fiber reinforcement, added to the batch before or during mixing, used as an ingredient of a cementitious mixture to modify its freshly mixed, setting, or hardened properties.

AIR-ENTRAINING ADMIXTURE. An admixture causing the development of a system of microscopic air bubbles in concrete, mortar, or cementitious material paste during mixing, usually to improve its workability and resistance to damage by freezing and thawing.

SET-ACCELERATING ADMIXTURE. An admixture causing an increase in the rate of hydration of the hydraulic cement and shortens the time of setting, increases the rate of strength development, or both.

SET-RETARDING ADMIXTURE. An admixture causing a decrease in the rate of hydration of the hydraulic cement and lengthens the time of setting, decreases the rate of strength development, or both.

WATER-REDUCING ADMIXTURE. An admixture either increasing slump of freshly mixed mortar or concrete without increasing water content or maintaining slump with a reduced amount of water, due to factors other than air entrainment.

AGITATION. The process of providing motion in mixed concrete just sufficient to prevent segregation or loss of plasticity.

BLEED WATER. The autogenous flow of water emerging from newly placed concrete, and caused by the settlement of the solid materials within the mass. The relative quantity of mix water that will bleed can be estimated by AASHTO T 158.

CAMBER. For prestressed concrete members, camber is the net upward deflection of an eccentrically prestressed concrete member due to the combined loads, shrinkage, creep, and eccentricity of the prestress force. For non-prestressed members, camber is a deflection intentionally built into a structural element or form to improve appearance or to nullify the deflection of the element under the effects of loads, shrinkage, and creep.

CEMENT. A binding material that sets and hardens by hydration and is capable of doing so underwater, sometimes called hydraulic cements

- CEMENTITIOUS MATERIAL. Hydraulic cements and pozzolans with cementing properties.

CHAMFER. A beveled edge or corner formed into finished concrete.

COMPRESSIVE STRENGTH, (fc). The measured maximum resistance of a concrete or mortar specimen to axial compressive loading; expressed as force per unit cross-sectional area; or the specified resistance used in design calculations.

SPECIFIED COMPRESSIVE STRENGTH, (f’c). The 28-day compressive strength used in structural design and specified in the Contract documents.

REQUIRED AVERAGE COMPRESSIVE STRENGTH, (f’cr). The 28-day compressive strength, used as the basis for selection of concrete proportions in the mix design process, sufficiently greater than the Specified Compressive Strength to ensure the acceptance criteria are met.

COMPRESSIVE STRENGTH TEST. The average strength test of concrete, from at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders sampled according to AASHTO T 141, cured according to AASHTO R 39 or WAQTC FOP for AASHTO T 23, and tested according to AASHTO T 22 or sampled, cured, and tested to equivalent ASTM test methods. Unless otherwise noted, tested at an age of 28 days.

The average strength test of grout, from at least three specimens from a batch and tested according to WAQTC TM 12, AASHTO T 106, or ASTM C 109.

CONCRETE ANCHOR. Cast-in-place or post-installed fastening device installed in the concrete for the purpose of transferring loads to the concrete. See ASTM E 2265 for standard terminology.

CONSOLIDATION. The process of inducing a closer arrangement of the solid particles in freshly mixed concrete during placement by the reduction of voids, usually by vibration, rodding, tamping, or some combination of these actions.

CONSTRUCTION JOINT. The surface where two successive placements of concrete meet.

CURING. Action taken to maintain moisture and temperature conditions in a freshly placed cementitious mixture to allow hydraulic cement hydration and (if applicable) pozzolanic reactions to occur so the desired properties of the mixture develop.

CURING PERIOD. The length of time in which continuous curing operations are maintained thereby allowing the concrete to properly hydrate and develop its required strength and durability.

INITIAL CURING PERIOD. The time period between placement and implementation of final curing methods in which deliberate action is taken to reduce the loss of moisture from the surface of the concrete.

FINAL CURING PERIOD. The time period after the concrete achieves final set in which deliberate action is taken, without damaging or marring the concrete surface, to maintain satisfactory moisture content and temperature in concrete.

CURING COMPOUND. A liquid applied as a coating to the surface of newly placed concrete to retard the loss of water and, in the case of pigmented compounds, reflects heat to provide an opportunity for the concrete to develop its properties in a favorable temperature and moisture environment.

DURABILITY. The ability of concrete to resist weathering action, chemical attack, abrasion, and other conditions of service.

EVAPORATION RATE REDUCER. A material generating a continuous thin film when spread over water on the surface of fresh concrete to retard the evaporation of bleed water.

FIELD TEST RECORD. A record of compressive strength test results from concrete used on prior projects and produced by the concrete production facility.

INFORMATIONAL FIELD TEST. A compressive strength test, determined by the Engineer, from field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure; except, the compressive strength test may consist of one 6.0 x 12.0 inch or one 4.0 x 8.0 inch compressive strength test cylinder.

KEYWAY. A recess or groove in one lift or placement of concrete and filled with concrete of the next lift or grout, giving shear strength to the joint.

LAITANCE. A layer of weak material derived from cementitious material and aggregate fines either: 1) carried by bleeding to the surface or to internal cavities of freshly placed concrete; or 2) separated from the concrete and deposited on the concrete surface or internal cavities during placement of concrete underwater.

MORTAR. A mixture of cementitious material paste and fine aggregate occupying the space between particles of coarse aggregate.

RETEMPER. To add water and remix concrete or mortar to restore workability to a condition in which the mixture is placeable or usable.

ROCK POCKET. A porous, mortar-deficient portion of hardened concrete consisting primarily of coarse aggregate and open voids.

SCREED. To strike off concrete lying beyond the desired plane or shape. A tool for striking off the concrete surface, sometimes referred to as a strikeoff.

SET. The condition reached by a cementitious material paste, mortar, or concrete that has lost plasticity to a degree of stiffening generally stated as the time in hours and minutes required for cementitious material paste to stiffen sufficiently to resist the penetration of a weighted test needle as prescribed by AASHTO T 197,

- INITIAL SET. The first stiffening of concrete.

- FINAL SET. Attainment of significant rigidity in which rainfall, foot traffic, and curing materials contacting the concrete surface do not damage or mare the concrete surface and do not alter the properties of the finished surface.

TREMIE. A pipe or tube with a hopper for filling at its upper end through which concrete is deposited.

501-2.01 MATERIALS. Use materials conforming to the following:

- 1.	Cementitious Materials

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Ground Granulated Blast-Furnace Slag	Section 701

Silica Fume	Section 701

- 2.	Aggregate Materials

Fine Aggregate	Subsection 703-2.01

Coarse Aggregate	Subsection 703-2.02

Aggregate for Abrasive Finish	Subsection 703-2.14

- 3.	Water, Admixtures and Curing Materials

Curing Materials	Subsection 711-2.01

Chemical Admixtures	Subsection 711-2.02

Water and Ice	Subsection 712-2.01

- 4.	Anchors and Inserts

Concrete Anchor Bolts	Subsection 712-2.20

Concrete Anchor Inserts	Subsection 712-2.20

Utiliduct, HDPE	Subsection 706-2.08

Utiliduct, Steel	Section 716

Structural Steel	Section 716

Asphalt Felt	ASTM D 226, Type I (No. 15 Asphalt Felt)

- 5.	Grout and Epoxy

Grout	Subsection 701-2.03

Epoxy Adhesive for Crack Sealing	AASHTO M 235, Type IV, Grade 3

Epoxy Adhesive for Crack Injection	AASHTO M 235, Type IV, Grade 1

Low-Viscosity Resin	Subsection 712-2.19

Epoxy Bonding Agents	AASHTO M 235, Type V

501-2.02 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Provide a Job Mix Design, for each required class of concrete and Specified Compressive Strength (f'c), which meets the requirements of this Subsection and provides workability and consistency so the concrete can be worked readily into the forms and around reinforcement without segregation or bleeding. Determine proportions using the absolute volume method according to ACI 211.1.

1.	Water-Cement Ratio and Cementitious Materials. Provide a Job Mix Design meeting the water-cement ratio requirements in Table 501-1.

Calculate the water-cement ratio based on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, ground granulated blast-furnace slag, and silica fume.

Fly ash, ground granulated blast-furnace slag, silica fume, and combinations of these materials may be used as a substitute for Type I and II Portland cement provided the quantity meets the limits of Table 501-2 and the total quantity of combined fly ash, ground granulated blast-furnace slag, and silica fume does not exceed 40 percent of the total cementitious material by weight. Do not use fly ash with Type III Portland cement.

- TABLE 501-1

WATER-CEMENT RATIO REQUIREMENTS

| Class of Concrete | Water-Cement Ratio, maximum |
| --- | --- |
|  | lbs/lbs |
| A | 0.45 |
| A-A | 0.40 |
| P | 0.35 |
| DS | 0.45 |

- TABLE 501-2

SUPPLEMENTARY CEMENTITIOUS MATERIAL LIMITS

| Cementitious Material | Percent of Total Cementitious Material by Weight1 |
| --- | --- |
|  | Maximum |
| Fly Ash | 35% |
| Ground Granulated Blast-Furnace Slag | 40% |
| Silica Fume | 10% |

1	The maximum percent includes initial quantities in blended hydraulic cement plus additional supplementary cementations materials.

2.	Aggregate Gradations. Provide a Job Mix Design meeting the fine aggregate gradation requirements in Subsection 703-2.01 and the coarse aggregate gradation requirements in Table 501-3

- TABLE 501-3

COARSE AGGREGATE GRADATION REQUIREMENTS

| Class of Concrete | Coarse Aggregate Size Number |
| --- | --- |
|  | AASHTO M 43 |
| A | No. 57 or 67 |
| A-A | No. 57 or 67 |
| P | No. 67 |
| DS | No. 7 or 8 |

3.	Air Content. Provide a Job Mix Design with a total air content of 6.0 percent. The total air content for Class P concrete having a water/cement ratio less than 0.33 may be reduced 3.0 percent. Air-entrained concrete is required only for the deck portion of prestressed precast concrete members. Air-entrained concrete is not required for Class DS concrete.

4.	Slump. Provide a Job Mix Design meeting the slump requirements in Table 501-4.

- TABLE 501-4

SLUMP REQUIREMENTS

| Condition | Slump |
| --- | --- |
| Concrete without a water-reducing admixture | 4" max. |
| Concrete with a Type A, D, or E water-reducing admixture | 6" max. |
| Concrete with a Type F or G high-range water-reducing admixture | 9" max. |
| Class DS concrete, wet-shaft process | 7" min. 9" max. |
| Class DS concrete, dry-shaft process | 6" min. 9" max. |

5.	Chloride Ion Content. For Class A-A and Class P Concrete, provide a Job Mix Design with a total water soluble chloride ion content of the concrete that does not exceed 0.06 percent by weight of cementitious material for precast concrete members or 0.08 percent by weight of cementitious material for other concrete, tested according to ASTM C 1218.

6.	Required Averaged Compressive Strength. Provide a Job Mix Design meeting a Required Average Compressive Strength (f'cr) established from either the Empirical Method or the Statistical Method.

If the Specified Compressive Strength (f'c) is not designated on the Plans, use a Specified Compressive Strength listed in Table 501-5.

- TABLE 501-5

COMPRESSIVE STRENGTH REQUIREMENTS

| Class of Concrete | Specified Compressive Strength (f'c) |
| --- | --- |
|  | (psi) |
| A | 4000 |
| A-A | 5000 |
| P | 8000 |
| DS | 4000 |

a.	Empirical Method. Establish the Required Average Compressive Strength from the following equations:

f'cr = f'c + 1200	for f'c ≤ 5000 psi

f'cr = 1.1f'c + 700	for f'c > 5000 psi

Where:	f'cr = Required Average Compressive Strength, psi

f'c = Specified Compressive Strength, psi

b.	Statistical Method. If the production facility has field test records of compressive strength tests, establish the Required Average Compressive Strength based on the calculated standard deviation of the field test records and using the largest result of the following the equations:

f'cr = f'c + 1.34ks	for all f'c

or,

f'cr = f'c + 2.33ks – 500	for f'c ≤ 5000 psi,

f'cr = 0.90f'c + 2.33ks	for f'c > 5000 psi,

Where:	f'cr	=	Required Average Compressive Strength, psi

f'c	=	Specified Compressive Strength, psi

k	=	1.16 if 15 total tests are considered

1.08 if 20 total tests are considered

1.03 if 25 total tests are considered

1.00 if 30 or more total tests are considered

s	=	standard deviation, psi

Linear interpolation to determine k for intermediate number of tests is acceptable.

Use field test records performed within the past 12 months and spanning a period of more than 60 days for a class of concrete within 1000 psi of the Specified Compressive Strength. Use field test records from concrete produced at the production facility, which represent materials, quality-control procedures, and climatic conditions similar to those expected in the work. Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work. Use field test records meeting one of the following:

(1)	One Group of Field Test Records. Use field test records representing a group of at least 15 consecutive compressive strength tests in which all concrete was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation, psi

- n	=	number of compressive strength test results considered

Xi	=	individual compressive strength test result, psi

=	average of n compressive strength test results, psi

(2)	Two Groups of Field Test Records. Use field test records representing two groups of consecutive compressive strength tests totaling at least 30 tests. Ensure each group is comprised of at least 10 consecutive compressive strength tests, and all concrete in each group was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation for the two groups combined, psi

s1, s2	=	standard deviation for groups 1 and 2, respectively, calculated according to Subsection 501-2.02.6.b.(1), psi

n1, n2	=	number of test results in groups 1 and 2, respectively

7.	Job Mix Design Verification.

a.	Required Average Compressive Strength. Verify the Job Mix Design satisfies the Required Average Compressive Strength by meeting at least one of the following requirements:

(1)	Field Test Records. Use field test records that:

(a)	use materials of the same brand and type and from the same manufacturer as the materials used in the work;

(b)	were from concrete produced at the production facility;

(c)	use quality-control procedures, and had climatic conditions similar to those expected in the work; and

(d)	encompass a period of not less than 60 days.

Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work.

For a single group of at least 10 consecutive compressive strength tests for one mixture, verify the average of the compressive strength tests equals or exceeds the Required Average Compressive Strength.

For two groups, each having at least 10 consecutive compressive strength tests, for two mixtures representing classes of concrete within 1000 psi of the Specified Compressive Strength, plot the average strength of each group versus the water-cementitious material ratio of the corresponding mixture proportions and interpolate between them to determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the interpolated compressive strength equals or exceeds the Required Average Compressive Strength.

(2)	Laboratory Trial Mixtures. Use materials and material combinations for trial mixtures of the same brand and type and from the same manufacturer as the materials used in the work.

Record the temperature of the freshly mixed concrete according to AASHTO T 309 and ensure the temperature is within 10°F of the intended maximum temperature of the concrete as mixed and delivered.

For each trial mixture, make and cure at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders for each test age according to AASHTO R 39. Test for compressive strength according to AASHTO T 22 at test ages of 7, 14 and 28 days.

For a single trial mixture, verify the compressive strength test equals or exceeds the Required Average Compressive Strength.

For a group of trial mixtures, make at least three trial mixtures with each mixture having a different cementitious material content. Select water-cement ratios producing a range of compressive strengths encompassing the Required Average Compressive Strength. From the results of the 28-day compressive strength tests, plot a curve showing the relationship between water-cement ratio and compressive strength. From the curve of water-cement ratio versus compressive strength, determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the compressive strength equals or exceeds the Required Average Compressive Strength.

b.	Flowability Requirements for Class DS Concrete (Wet-Shaft Process). Verify the Job Mix Design satisfies the concrete flowability requirements of Subsection 501-3.05.6.a.1. Develop a slump loss table showing the slump at 1 hour intervals since batching until the concrete takes initial set.

c.	Plasticity Requirements for Class DS Concrete (Dry-Shaft Process). Verify the Job Mix Design satisfies the concrete plasticity requirements of Subsection 501-3.05.6.b.1. Ensure initial set occurs after placement operations are complete.

8.	Job Mix Design Submittal. Submit a written mix design, signed and sealed by a Professional Engineer registered in the State of Alaska, for each specified class of concrete and for each Specified Compressive Strength, to the Engineer at least 45 days prior to scheduled production. Submit the mix design on Form 25D-203. Include the following:

a.	Job Mix Design Proportions and Test Results. Submit concrete mixture proportions per cubic yard and test results for the proposed Job Mix Design. Include the following information:

- (1)	Weights of cementitious materials

- (2)	Weights of aggregates in saturated surface dry condition

- (3)	Volume or weight of each admixture.

- (4)	Weight of water

- (5)	Water-cement ratio

- (6)	Percentage of air by volume

- (7)	Total water soluble chloride ion content

- (8)	Wet unit weight

- (9)	Expected slump

- (10)	Expected 7, 14, and 28 day compressive strength

- (11)	Slump loss table for flowability requirements of Class DS concrete (if applicable)

- (12)	Time of initial set for plasticity requirements of Class DS concrete (if applicable)

b.	Materials Documentation. Submit the following:

(1)	For each cementitious material, include:

(a)	Type/Class

(b)	Brand

(c)	Producer

(d)	Plant location

(e)	Certified test reports confirming the cementitious material meets these Specifications.

(2)	For aggregates, include:

(a)	Pit or quarry location(s)

(b)	Bulk dry specific gravity, bulk saturated surface dry specific gravity, and apparent specific gravity

(c)	Absorption values

(d)	AASHTO size number for coarse aggregates

(e)	Gradations for aggregates

(3)	For each admixture, include:

(a)	Type

(b)	Manufacturer

(c)	Manufacturer's product data sheet giving the procedure for admixture use and confirming the admixture meets these Specifications.

(d)	The batching process step and mixing instructions when each admixture is added.

(e)	When using two or more admixtures in the same Job Mix Design, provide manufacturer’s certifications showing the admixtures are compatible and if they can be added simultaneously.

(4)	Include the source of supply for water and ice.

c.	Materials Samples. The Engineer may require samples of aggregate, cementitious materials, and admixtures to verify the mix design. If requested, furnish representative samples (330 pounds each) of both coarse and fine aggregates, 94 pounds of each cementitious material, and enough admixture to allow for Job Mix Design verification testing. Ensure the Department receives these samples at least 45 days before the mixture’s scheduled production for the project.

d.	Basis of Required Average Compressive Strength. If the Statistical Method is used, submit the following for each field test record:

(1)	Compressive strength test results of the tested concrete.

(2)	Standard test method used for determining compressive strength.

(3)	Date the compressive strength tests were performed

(4)	Aggregate source used for the tested concrete.

(5)	Specified strength of the tested concrete.

(6)	Batched weights of constituent materials for the concrete used for each compressive strength test.

e.	Documentation of Required Average Compressive Strength. Submit documentation indicating the proposed concrete proportions will produce an average compressive strength equal to or greater than the Required Average Compressive Strength meeting one of the following requirements:

(1)	Field Test Records. If field test records were used to verify the Required Average Compressive Strength, submit the following for each field test record:

(a)	Compressive strength test results of the tested concrete.

(b)	Standard test method used for determining compressive strength.

(c)	Date the compressive strength tests were performed

(d)	Aggregate source used for the tested concrete.

(e)	Specified strength of the tested concrete.

(f)	Batched weights of constituent materials for the concrete used for each compressive strength test.

(2)	Trial Mixtures. If a single or group of trial mixtures were used to verify the Required Average Compressive Strength, submit concrete mixture proportions per cubic yard and test results for each trial mixture. Include the following information:

(a)	Weights of cementitious materials

(b)	Weight of aggregates in saturated surface dry condition

(c)	Volume or weight of each admixture

(d)	Weight of water

(e)	Water-cement ratio

(f)	7-day, 14-day, and 28-day compressive strength test results

(g)	Percentage of air by volume

(h)	Wet unit weight

9.	Changes. A change in the approved Job Mix Design proportions, materials, aggregate gradation, or aggregate quality requires a new Job Mix Design; except, a change in Type A, D, E, F, and G admixture proportions, or the addition of a Type A, D, E, F, and G admixture, does not require a new Job Mix Design.

10.	Approval. Obtain the Engineer’s approval of each mix design prior to use. Approval of the Job Mix Design does not constitute acceptance of produced concrete and will not obligate the Department to accept or pay for concrete that does not meet the mix acceptance requirements of Subsection 501-3.03.

- CONSTRUCTION REQUIREMENTS

501-3.01 BATCHING. Batch concrete, in proportioned amounts, according to the approved Job Mix Design.

1.	Certification and Calibration. Batch concrete using a certified batch plant. Obtain plant certification meeting the requirements in this Subsection. Use and maintain calibrated weighing and measuring devices for concrete batching equipment, including measuring devices for adding material on-site, meeting the requirements of this Subsection. Submit documentation required for plant certification and weighing and measuring device calibration meeting the requirements of this Subsection before commencing concrete work.

a.	Plant Certification by the National Ready Mix Concrete Association. Certification may be obtained from the National Ready Mix Concrete Association (NRMCA). Information concerning NRMCA certification may be obtained from the NRMCA at 900 Spring Street, Silver Springs, MD 20910 or online at www.nrmca.org. The NRMCA certification is valid for 2 years from the date of inspection.

b.	Plant Certification by a Professional Engineer. Certification may be obtained by an independent inspection and evaluation by a Professional Engineer registered in the State of Alaska using and completing the NRMCA Plant Certification Check List. Correct deficiencies to the satisfaction of the Professional Engineer. The Professional Engineer must sign and seal the completed NRMCA Plant Certification Check List certifying all applicable items have been met. The certification by a Professional Engineer is valid for 2 years from the date of inspection.

c.	Calibration of Weighing and Measuring Devices. Use weighing and measuring devices meeting the requirements of the National Institute of Standards and Technology Handbook 44: Specifications, Tolerances, and other Technical Requirements for Weighing and Measuring Devices, and are calibrated by a commercial scale service or certified by the DOT&PF Division of Measurement Standards & Commercial Vehicle Enforcement. Calibrate weighing and measuring devices using equipment traceable to the Alaska State Standards of Weight and Measure as adopted by AS 45.75.020.

Calibrate weighing and measuring devices:

(1)	no more than 12 months before commencing concrete work,

(2)	after each relocation,

(3)	at least once every 12 months until the work is completed, and

(4)	when, in the opinion of the Engineer, there is a question as to the accuracy or adequacy of the device.

d.	Certification and Calibration Submittals. If the Plant Certification is by the NRMCA, submit a copy of the NRMCA Certificate of Conformance. If the Plant Certification is by a Professional Engineer, submit a copy of the completed NRMCA Plant Certification Check List and associated Fleet Inspection Reporting Spreadsheet.

Submit copies of the calibration worksheets for weighing and measuring devices including the most recent date of inspection and the calibrated accuracy for each weighing and measuring device. Submit copies of updated calibration worksheets for each additional calibration required according to 501-3.01.c.

2.	Measuring Materials.

a.	Cementitious Materials. Use cementitious materials of the same brand, type, and from the same plant of manufacture as the cementitious materials used to verify the approved Job Mix Design according to Subsection 501-2.02.7. Ensure the quantity of the Portland cement and the cumulative quantity of Portland cement plus other cementitious materials is proportioned in amounts required by the Job Mix Design and meets the mix acceptance requirements.

Measure cementitious materials by weight. When other cementitious materials, including fly ash, ground granulated blast-furnace slag, or silica fume, are specified in the concrete proportions, the material may be cumulatively weighed with the Portland cement. Weigh cementitious materials on a weighing device that is separate and distinct from those used for other materials. Weigh the Portland cement before other cementitious materials.

Portland cement is permitted to be measured in bags of standard weight (94 pounds). Do not use a fraction of a bag of cementitious materials unless its weight has been determined by calibrated weighting devices.

b.	Aggregates. Use aggregates from the same sources and having the same size ranges as the aggregates used in the trial mixtures or field test records used to verify the required average compressive strength. Ensure the quantity of the aggregates is proportioned in amounts required by the Job Mix Design.

Measure aggregates by weight. Establish batch weight measurements on dry materials and adjust the actual scaled weight for the required dry materials weight plus the total weight of moisture, both absorbed and surface, contained in the aggregate.

c.	Water. The total quantity of mixing water includes water added to the batch, ice added to the batch, and water occurring as surface moisture on the aggregates. Measure the added water by weight or volume. Measure added ice by weight. Discharge the flush water (wash water) prior to loading the next batch of concrete. Do not use flush water (wash water) as a portion of the mixing water.

d.	Admixtures. Use concrete admixtures according to the manufacturer's instructions and the approved Job Mix Design. Type A, D, E, F, and G admixtures not included in the approved Job Mix Design may be added according to Subsection 501-2.02.9.

Measure powdered admixtures by weight. Measure paste or liquid admixtures by weight or volume.

3.	Materials Storage and Handling.

a.	Cementitious Materials. Keep cementitious materials dry and free from contaminants. Do not use cementitious materials which have become partially hydrated or which contain lumps of caked cementitious material.

b.	Aggregates. Do not allow segregation of the aggregates or contamination with foreign materials. Separate aggregate to prevent intermixing of specified gradations.

Drain aggregate so the moisture content is uniform and is accounted for during the batching process.

Do not use aggregates that contain ice, are frozen, or have been heated directly by combustible materials. Use direct steam, steam-coil, or water-coil heating when heating aggregates. When direct steam is used to thaw aggregate piles, drain aggregates to uniform moisture content before batching.

c.	Admixtures. Protect admixtures from contamination, evaporation, or damage. Store admixtures according to the manufacturer’s instructions. Protect liquid admixtures from freezing and from temperature changes affecting the admixture’s performance.

501-3.02 MIXING AND DELIVERY. Mix concrete, in proportioned amounts, according to the approved Job Mix Design. Mix ingredients into a thoroughly intermingled uniform mixture. Do not retemper concrete mixtures. Do not use concrete that has developed initial set prior to placement.

1.	Addition of Water. Additional water may be added on-site provided the following are met:

a.	The volume of concrete in the mixer after the additional water is added does not exceed the maximum mixing capacity.

b.	The water measuring device is calibrated according to Subsection 501-3.01.1.c.

c.	The Water-cement ratio for the batch as established by the approved Job Mix Design is not exceeded. Account for the actual volume of concrete remaining in the mixer.

d.	Water additions are completed within 30 minutes after the introduction of the mixing water to the cementitious materials.

The addition of water is not prohibited from being several distinct additions of water. Inject additional water into the mixer under pressure and direction of flow to allow for proper distribution within the mixer. Provide additional mixing to ensure a thoroughly intermingled uniform mixture is attained.

2.	Time for Placement. Discharge the concrete within 1.5 hours of the following:

a.	after adding the mixing water to the cementitious materials, and

b.	after adding the cementitious materials to the aggregates.

The time to complete discharging the concrete may be extended 2 minutes for every degree of temperature at which the concrete is discharged below 70°F, to a maximum total time of 2 hours. The Engineer may increase the time to discharge requirement provided the concrete can be placed before initial set occurs and without the addition of water.

501-3.03 EVALUATION OF MATERIAL FOR ACCEPTANCE. All concrete in the work will be evaluated for acceptance.

The Engineer may reject a batch or load of concrete failing to meet the requirements for proportions, slump, total air content, or temperature. Prior to sampling, the Engineer may reject a batch or load of concrete that appears defective in composition.

1.	Sampling. The Department will take samples at the discharge point of the placement system, except Class DS concrete will be sampled at the truck discharge.

Provide adequate and representative fresh concrete for sampling and testing as directed by the Engineer. The Engineer will sample the concrete after a minimum of 1/2 cubic yard of concrete has discharged from the placement system. Do not add water or admixtures to the mix after the concrete has been sampled for acceptance testing.

The Engineer will determine aggregate gradation for acceptance based on random samples taken at the plant.

2.	Sampling and Test Methods. The Department will sample and test according to the following:

WAQTC TM 2	Sampling Freshly Mixed Concrete

WAQTC FOP for AASHTO T 309	Temperature of Freshly Mixed Portland Cement Concrete

AASHTO T 22	Compressive Strength of Cylindrical Concrete Specimens

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse Aggregates, and Materials Finer Than No. 200 Sieve in Mineral Aggregate by Washing

WAQTC FOP for AASHTO T 23	Method of Making and Curing Concrete Test Specimens in the Field

WAQTC FOP for AASHTO T 119	Slump of Hydraulic Cement Concrete

WAQTC FOP for AASHTO T 121	Density (Unit Weight), Yield, and Air Content (Gravimetric) of Concrete

WAQTC FOP for AASHTO T 152	Air Content of Freshly Mixed Concrete by the Pressure Method

AASHTO T 231	Capping Cylindrical Concrete Specimens

WAQTC FOP for AASHTO TP 83	Field Sampling and Fabrication of 50-mm (2-in) Cube Specimens using Grout (Non-Shrink) and or Mortar

3.	Batch Tickets. Provide a ticket with each batch of concrete delivered to the project. Include the following information:

a.	Manufacturer plant (batching facility)

b.	Department contract number

c.	Date

d.	Time batched

e.	Time discharge completed

f.	Truck number

g.	Quantity (quantity batched this load)

h.	Batch facility mix identification number

i.	Weights of every type of cementitious material

j.	Weights of each aggregate

k.	Weight or volume of each admixture

l	Weight or volume of water added at the plant

m.	Total moisture and absorption percentage for each aggregate

n.	Total weight or volume of water (water added at the plant plus water added in the field)

4.	Proportion Requirements. Meet the proportion requirements of the approved Job Mix Design within the following proportion tolerances:

a.	Total Cementitious Material, weight 	±1%

b.	Aggregates, weight	±2%

c.	Total Water, weight or volume	±3%

d.	Air-Entraining Admixtures, weight or volume	manufacturer's limits

e.	Type S Admixture, weight or volume	±3%

f.	Type A, B, C, D, E, F, G Admixtures, weight or volume	manufacturer's limits

If the total cementitious material weight is made up of different components, keep the component weights within the following tolerances:

(1)	Portland Cement	±1%

(2)	Fly Ash	±5%

(3)	Ground Granulated Blast-Furnace Slag	±5%

(3)	Silica Fume	±10%

Proportion tolerance will be calculated using consistent units for MJMD and MA as follows:

- Where:	P	=	Proportion tolerance, percentage

- MJMD	=	Weight or Volume of component according the approved Job Mix Design

MA	=	Weight or Volume of actual batched component

5.	Slump Requirements. Do not exceed 9” slump for all classes of concrete. For Class DS concrete, meet the following slump tolerances:

a.	Using the wet-shaft process: 7 inches minimum, 9 inches maximum

b.	Using the dry-shaft process: 6 inches minimum, 9 inches maximum

6.	Total Air Content Requirements. Meet the total air content percentage within a tolerance of ±1.5 of the approved Job Mix Design percentage.

7.	Temperature Requirements. Unless otherwise noted, ensure the concrete temperature is between 50°F and 90°F when placed in the forms.

8.	Compressive Strength Requirements. Meet the strength requirements for the Specified Compressive Strength. Concrete of the approved Job Mix Design will be considered to meet the Specified Compressive Strength requirements when both of the following conditions are met:

a.	The lowest individual compressive strength test result is not less than the Specified Compressive Strength minus 500 psi, or 90.0 percent of the Specified Compressive Strength, whichever is lower.

b.	The lowest averaged result of three consecutive individual compressive strength tests meets or exceeds the Specified Compressive Strength.

501-3.04 PREPARATION FOR CONCRETE PLACEMENT. Allow time for inspection prior to concrete placement.

Remove debris, concrete splatter, oil, paint, and other foreign substances from the surfaces of forms and reinforcing steel, against which the concrete is to be placed.

Remove soil and other debris from pipe piles to the bottom of concrete elevation shown on the Plan.

- Prepare foundations according to Section 205.

Moisten foundations and forms with water before the concrete is placed. Remove standing water on the foundation, in the pile, and in the forms before placing concrete.

501-3.05 PLACING CONCRETE. Do not begin concrete placement without the Engineer's authorization. Place concrete conforming to the approved Job Mix Design. Place and consolidate each layer within 30 minutes and before the preceding layer takes initial set.

If concrete placement operations are delayed so initial set occurs before placement of the succeeding section or layer, place a joint according to Subsection 501-3.11. The resulting joint will be considered a construction joint. If, in the opinion of the Engineer, the location of the construction joint will affect the strength or durability of the concrete, the Engineer may reject the concrete, the structure, or a portion of the structure.

Place concrete in a sequence to obtain a well-consolidated concrete and to prevent cracks. Place concrete as near as possible to final position. Prevent segregation of the mix, displacement of reinforcing steel, and spattering of mortar on the reinforcing steel and forms above the elevation of the layer being placed. Do not deposit a large quantity of concrete at any point and run or work the concrete along the forms. Do not allow concrete to slide down the sides of the forms.

Regulate concrete placement so the pressures do not exceed the load capacity of the forms. Limit layer thickness to no more than 2.5 feet, or the capacity of the vibrators to consolidate and merge the concrete with the previous layer, whichever is less.

Unless otherwise specified, use a tremie, tube, or other such device to limit the free-fall height to less than 5.0 feet when placing operations would otherwise allow concrete to drop more than 5.0 feet. When using a tremie to place concrete, use a watertight tremie with an inside diameter of at least 10 inches. When using a concrete pump to place concrete, use concrete pump lines that are watertight with an inside diameter of at least 5 inches.

Concrete placed in piles or in dry-shaft process may free-fall more than 5.0 without use of tremie, tube or other such device, provided the falling concrete does not contact rebar or other objects before reaching the top surface of the placed concrete. When free-falling concrete more than 5.0 feet, use a drop chute at least 3.0 feet long.

After initial set, prevent movement of forms, projecting ends of reinforcing steel, and other embedded items.

Do not use aluminum components in contact with fresh concrete.

Place concrete in the superstructure only after substructure forms are removed and the substructure has been inspected.

1.	Concrete Placement Plan. Submit a concrete placement plan to the Engineer, for concrete decks and drilled shafts. Submit each concrete placement plan to the Engineer, at least 30 days before placing concrete. Do not place concrete until after the Engineer has approved the plan. Include the following in each concrete placement plan:

(1)	concrete placement sequence,

(2)	schedule of concrete placement and curing,

(3)	estimated concrete volume of each section,

(4)	placement rate and duration,

(5)	description of finishing equipment,

(6)	placement procedure,

(7)	name of the concrete foreman,

(8)	curing materials, equipment, and procedure.

2.	Pre-concreting Conference. Hold a pre-concreting conference for concrete decks and Drilled Shafts, at least 5 working days before placing concrete. Include the Engineer, the Superintendent and foremen in charge of placing reinforcing steel, placing concrete, finishing concrete, and curing operations. Discuss construction procedures, personnel, and equipment to be used.

If the project includes more than one concrete placement operation, and if key personnel change between concreting operations, hold additional conferences to include replacement personnel before placing successive concrete sections.

3.	Pumping Concrete. Use a pump producing a continuous stream of concrete without air pockets. When pumping is completed, the concrete remaining in the pipeline, if used, must eject without contaminating the concrete or separating the ingredients. Discard concrete contaminated by priming or cleaning the pump.

4.	Conveying Concrete. Concrete may be conveyed if the equipment will handle the class of concrete, with the slump and air content specified and without segregation of the aggregate, and no equipment vibrations will damage freshly placed concrete or reinforcing steel. Limit the length of conveyor belts to prevent aggregate segregation or 300 feet, whichever is less. Cover the belt to protect the concrete from heat, evaporation, precipitation, or when the Engineer determines precipitation is likely.

5.	Piles. Do not place concrete underwater in piles.

6.	Drilled Shaft Foundations. Place concrete following either the wet-shaft process or dry-shaft process, as applicable.

The dry-shaft process may be used where the ground water level and soil and rock conditions are suitable to permit construction of the shaft in a relatively dry excavation, and where the sides and bottom of the shaft can be visually inspected by the Engineer prior to placing the concrete. Relatively dry excavation conditions exist when excavation fluids have been removed from the shaft and the rate of water intrusion is less than 6 inches of water accumulating above the base in a 1-hour period without pumping or other methods to drain or remove water. Suitable soil and rock conditions exist when the sides and bottom of the hole remain stable without caving, sloughing, or swelling between completion of excavation and concrete placement; and loose material and water can be satisfactorily removed prior to inspection and concrete placement. Do not begin concrete placement if there is more than 1 inch of water in the bottom of the shaft excavation. Use wet-shaft process if the requirements for dry-shaft process cannot be satisfied.

Provide process control testing during concrete placement. Test total air content and slump before placing each batch of concrete in the drilled shaft. Perform sampling and testing according to Subsection 501-3.03.2 using a WAQTC qualified concrete testing technician or ACI certified concrete field testing technician. Test every batch of concrete before placement. Record the time when each sample is collected. Submit test results to the Engineer within 72 hours of completing each test.

a.	Wet-Shaft Process. Place concrete using a tremie or concrete pump. Place concrete continuously until good quality concrete, as determined by the Engineer, is evident at top of the shaft or nearest construction joint. Good quality concrete is considered concrete of the same consistency, appearance, and quality as the concrete being delivered and meeting the applicable mix acceptance requirements. Remove a sufficient volume of concrete to ensure elimination of contaminated concrete at the top of shaft before continuing with subsequent construction operations.

Remove concrete laitance during or immediately after concrete placement operations have ended.

Do not allow water, fluids, drilling aids, or concrete from the top of the shaft to enter streams or other waterways.

Construct the discharge end of the tremie or pump line to prevent water intrusion and permit the free flow of concrete during concrete placement. Use caps, bottom plates, pigs, or other such devices inserted into or attached to discharge pipe to separate the concrete from the excavation fluid during initial charging of the discharge pipe. Ensure the discharge pipe has sufficient length and weight to rest on the shaft base before starting concrete placement.

When using a tremie, provide adequate support so the tremie can be raised to increase the discharge of concrete and lowered to reduce the discharge of concrete. Do not shake, vibrate, or rapidly raise or lower the tremie to increase the discharge of the concrete.

Maintain a positive head of concrete inside the tremie or pump line relative to the excavation fluid level. Position the discharge orifice within one pipe diameter of the shaft base. Do not re-position the discharge pipe until the orifice is at least 8 feet below the concrete surface. Maintain at least 8 feet of concrete above the discharge orifice during concrete placement. Monitor the concrete level during placement to ensure the tremie or pump line discharge orifice remains at least 8 feet below the concrete surface throughout placement.

If the discharge orifice rises above the concrete surface before concrete placement is complete, the shaft will be considered defective. Immediately terminate concrete placement operations and notify the Engineer.

(1)	Concrete Flowability Requirements. Ensure concrete placed in the shaft remains flowable throughout placement operations by maintaining a slump of at least 6 inches until placement is completed. Collect samples from the first batch of concrete. Test slump from the first batch of concrete at the beginning of the concrete placement operations and immediately after concrete placement operations are complete. Record the time when samples are collected and when tests are performed. Submit test results to the Engineer within 72 hours of completing each test.

b.	Dry-Shaft Process. Place concrete continuously until concrete is evident at top of the shaft or nearest construction joint. Concrete may be permitted to free-fall into place if the concrete does not contact the sides of the shaft, reinforcing steel, or other objects while free falling.

Remove concrete laitance during or immediately after concrete placement operations have ended.

(1)	Concrete Plasticity Requirements. Ensure concrete placed in the shaft remains plastic throughout placement operations by completing placement operations before initial set occurs.

7.	Concrete Decks and Approach Slabs. Before placing concrete, operate the finishing machine over the entire length of the deck to check screed deflection, reinforcing steel clearance, and concrete thickness.

Limit the rate of placing concrete to what can be finished before initial set.

a.	Placement Sequence. Place the concrete deck in the sequence shown on the Plans. The Engineer may approve a revised placement sequence for casting the concrete deck continuously from one end to the other provided the following:

(1)	Do not use Type III Portland cement.

(2)	Stockpile the materials necessary to complete the placement and have the equipment, incidentals, and workers on the site before beginning concrete placement operations.

(3)	Ensure the continuous concrete placement and finishing operation proceeds at a minimum rate of 30 feet per hour, measured longitudinally along the axis of the span.

(4)	The Engineer determines the revised placement sequence will not reduce the stability during construction and will not reduce the quality, capacity, or durability of the completed structure.

If the Engineer approves the proposal for a continuous concrete placement operation, the Department will observe and evaluate performance to the first planned construction joint in the sequence. At this point, the Engineer may authorize you to proceed with the continuous concrete placement operation or suspend the placement and install a construction joint. The Engineer's decision will be based on whether the concrete can be produced, delivered, and finished at a continuous rate permitting the structure to accommodate final dead load deflections while the concrete is plastic.

If the Engineer suspends the continuous concrete placement operations after the first sequential placement, submit modifications for improving the continuous concrete placement operations, beginning at the other end of the deck. If a second attempt at continuous concrete placement is authorized, the placement will be evaluated and allowed or terminated based on the same criteria as the first sequential placement.

If the Engineer suspends the continuous concrete placement operation after the second attempt, additional attempts will not be permitted. Follow the deck placing sequence shown on the Plans.

501-3.06 CONSOLIDATION OF CONCRETE. Consolidate concrete to make a dense homogeneous mass free of voids and rock pockets. Consolidate each layer to leave a compact, dense, and impervious concrete with smooth faces on exposed surfaces with no visible line of separation between adjoining layers.

Consolidate concrete, except underwater or other exempted placements, by mechanical vibration at the point of deposit. Use vibrators capable of visibly affecting concrete with a 1-inch slump for a distance of at least 18 inches from the vibrator.

Use vibrators and regulate placement in order to consolidate the fresh concrete within 15 minutes of placement and before initial set. Effectively vibrate the full depth of each layer.

For immersion-type vibrators, insert vibrators vertically to a depth penetrating into the previous layer. Withdraw vibrators slowly to avoid segregation or grout pockets. Vibrate in a uniform pattern spaced less than 1.5 times the radius of visible effectiveness.

Avoid vibration of initially set layers and reinforcing steel below the succeeding placement. Do not hold vibrators against reinforcing steel or use them to flow or spread the concrete into place. Manipulate vibrators to produce concrete free of voids, with proper texture on exposed faces, and maximum consolidation. Do not allow the concrete to segregate, form pools of mortar, or form laitance on the surface.

When immersion-type vibrators are used to consolidate concrete around epoxy-coated reinforcing steel, use rubber or nonmetallic vibrator heads that will not damage epoxy coatings.

Concrete may be placed directly into drilled shaft foundations and piles without mechanical vibration; except, vibrate the top 5 feet of concrete. For drilled shaft foundations, consolidate the top 5 feet of concrete after good quality concrete is evident at the top of the shaft and after water, slurry, drilling aids, and other materials other than concrete have been removed.

501-3.07 FINISHING CONCRETE SURFACES. After the concrete is consolidated and prior to the application of curing materials, strike-off unformed concrete surfaces to the required elevation and slope. Finish the surface by floating the surface to remove local irregularities and leave sufficient mortar to seal the concrete surface. Do not use mortar topping for concrete surfaces. Do not use aluminum finishing equipment.

Complete initial floating operations before bleed water or excess moisture is present on the surface and before the concrete takes initial set. Complete final finishing before final set occurs. Do not use finishing aids or additional water to assist in finishing concrete surfaces. Do not finish concrete surfaces if bleed water, excess moisture, or curing materials are present.

Provide formed concrete surfaces with an ordinary finish unless otherwise noted.

1.	Ordinary Finish. An ordinary finish is the finish left on a surface after removing the forms, filling the holes left by the form ties, and repairing defects. Ensure the surface is true and even and free from rock pockets and depressions or projections.

Immediately after removing the forms, remove the metal devices holding the forms in place and passing through the body of the concrete, or cut them back at least 1 inch beneath the surface of the concrete. Remove fins of mortar and irregularities caused by form joints.

Patch cavities produced by form ties, depressions, holes, and voids greater than 1/4 inch. Fill the cavity with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand. Clean the cavity and saturate the concrete with water before filling the cavity. Thoroughly tamp the mixture into place. Float the surface of the mortar before initial set to make the surface neat in appearance. Cure the patch according to Subsection 501-3.08.

Do not repair concrete with rock pockets, cracks, or other defects until the concrete is inspected by the Engineer. Concrete repaired prior to inspection by the Engineer may be rejected. If, in the opinion of the Engineer, the defect will affect the strength or durability of the concrete, the Engineer may reject the concrete, the structure, or portion of the structure. If the defect is greater than 3/4 inch in depth, submit a repair plan including complete details of the method, materials, and equipment proposed for use in repairing the concrete. Obtain the Engineer's approval of the repair plan before repairing the defect. A repair plan is not required if the defect is less than 3/4 inch in depth.

Repair broken corners and edges, rock pockets, and other defects. If the defect is greater than 3/4 inch in depth, repair the defect according to the approved repair plan. If the defect is less than 3/4 inch in depth, chip away coarse or broken material according to Subsection 501-3.16 to obtain a dense, uniform surface of concrete exposing solid coarse aggregate. Cut feathered edges to form faces perpendicular to the surface. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Patch the repaired area with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand.

Perform repairs prior to releasing falsework, prestressing, or applying additional loads to the concrete.

2.	Rubbed Finish. Provide a rubbed finish at locations shown on the Plans. When forms can be removed, wet the surface and then rub with a wooden float until irregularities and form marks are removed and the surface is covered with a lather composed of cement and water. A thin grout composed of one part Portland cement and one part fine aggregate may be used. Allow this lather to set for at least 5 days. Then, smooth the surface by lightly rubbing with a fine carborundum stone.

If the concrete has hardened before being rubbed, use a medium coarse carborundum stone to finish the surface at least 4 days after placing the concrete. Spread a thin grout composed of one part Portland cement and one part fine aggregate over a small area of the surface. Immediately rub the surface with the stone until form marks and irregularities are removed and the surface is covered with a lather. Allow this lather to set for at least 5 days. Then, smooth the surface by rubbing lightly with a fine carborundum stone.

- Complete ordinary finish work before applying the rubbed finish.

3.	Concrete Decks and Approach Slabs. Obtain a smooth riding surface of uniform texture, true to the required grade and cross section.

Use a self-propelled mechanical finishing machine:

a.	capable of forward and reverse movement,

b.	with a rotating cylindrical single or double drum screed,

c.	with necessary adjustments to produce the required cross-section, line, and grade,

d.	allowing screeds to be raised and lowered, and

e.	with an upper vertical limit of screed travel permitting the screed to clear the finished concrete surface.

When placing concrete abutting previously placed concrete, equip the finishing machine to travel on the existing concrete.

The Engineer may approve hand-operated motorized roller screeds (friction screeds) where jobsite conditions prohibit the use of conventional configuration finishing machines described above, for small areas less than 12 feet wide, and on approach slabs in which conventional configuration finishing machines are not used to finish the concrete deck. Do not use vibratory screeds.

Use equipment capable of striking off the full placement width without intermediate supports or rails. Use rails resting on adjustable supports that can be removed with the least disturbance to the concrete. Place the supports on structural members or on forms rigid enough to resist deflection. Use supports that are removable to at least 2 inches below the finished surface. If possible, place rails outside the finishing area. If not possible, place them above the finished surface.

Use rails (with their supports) that are strong and stiff enough for operation of the equipment without excessive deflection. Place and secure rails for the full length of the deck before placing concrete. Set the rails to the proper grade and elevations to ensure the required profile is provided.

- After placing and consolidating the concrete, carefully strike off the concrete surface. Correct imperfections left on the deck. Provide a float finish to surfaces receiving a waterproof membrane. Texture other surfaces with a heavy-broom finish perpendicular to the direction of traffic.

Do not place finishing machines or other loads on the screed rail supports or on features supporting fresh concrete after the concrete has initially set and before the concrete attains at least 80 percent of the Specified Compressive Strength.

Do not release falsework or wedges supporting concrete on either side of a joint until each side has cured as specified.

4.	Curb, Sidewalk, and Concrete Barrier Surfaces. Finish exposed faces of curbs, sidewalks, and concrete barriers to true surfaces and provide a broom finish. Broom finish sidewalks perpendicular to the direction of traffic.

5.	Sandblasted Finish. Sandblast the cured concrete surface with hard, sharp abrasive media to produce an even fine-grained surface in which the mortar has been cut away, leaving the aggregate exposed.

6.	Trowel Finish. Trowel the surface smooth and free of trowel marks.

501-3.08 CURING CONCRETE. Maintain a satisfactory moisture content and temperature in the concrete immediately after finishing operations are completed.

1.	Initial Curing Period. Before final curing, ensure the surface of the concrete is kept moist. Concrete surface is beginning to dry when no bleed water is present and the surface color changes. If the concrete surface begins to dry before the final curing method can be applied, prevent further loss of moisture by one or more of the following methods:

a.	Fog Spray. Use equipment producing a fog spray from an atomizing nozzle with sufficient velocity to cover the entire concrete surface. Direct the atomized water spray above the concrete surface to allow the fog to drift down to the concrete surface. Do not apply the discharge of the atomized water spray directly at the concrete surface. Continue fogging to maintain the reflective appearance of the damp concrete. Do not allow the surface to dry, or to undergo cycles of drying and wetting. Keep the concrete surface damp, but do not accumulate water until after final set has occurred. Use water meeting the requirements of Subsection 712-2.01.

b.	Evaporation Rate Reducer. Apply a monomolecular film intended specifically as an evaporation rate reducer to entrap bleed water or excess moisture on the concrete surface. Apply the evaporation rate reducer according to the manufacturer’s written instructions. Do not use the evaporation rate reducer during finishing operations or as a finishing aid. Do not use evaporation rate reducers on concrete surfaces receiving a waterproofing membrane such as concrete decks, approach slabs, end diaphragms and decked precast concrete members.

2.	Final Curing Period. Unless otherwise noted, employ the final curing method immediately following finishing operations.

Use wet curing on construction joints, concrete with a mix design water-cement ratio less than 0.40, and concrete decks, approach slabs, and other concrete surfaces subject to tire contact in the completed structure. For other concrete, use wet curing, liquid membrane-forming curing, forms-in-place curing, or a combination of these curing methods.

Do not use liquid membrane-forming curing compounds on concrete surfaces to which other materials will be cast against or bonded such as concrete and waterproofing membranes.

In addition to the requirements in this section, precast concrete members may use accelerated curing.

a.	Wet Curing. Until the end of the curing period, provide continuous moisture by:

(1)	watering a covering of heavy burlap blankets or quilted cotton mats,

(2)	keeping concrete surfaces wet with water continuously,

(3)	wetting the outside surfaces of wood forms.

Wait to install curing materials until the concrete has sufficiently hardened to permit such operations without damaging the concrete or marring the finish. While waiting to employ curing materials, maintain the concrete surface moisture as specified for the initial curing period.

Uniformly distribute absorbent materials across the entire concrete surface. Apply water in a manner that will not displace the curing materials or erode the concrete surface. Keep the concrete surfaces continuously wet. Do not allow concrete surfaces to dry or alternate with wetting and drying cycles. Cover the concrete, wooden forms and absorbent material with impermeable sheeting. Use white reflective impermeable sheeting if direct sunlight is present, or if the Engineer determines direct sunlight may be present during the curing period.

Do not use absorbent materials containing harmful substances such as sugar or fertilizer, or materials that may discolor the concrete.

b.	Liquid Membrane-Forming Curing Compounds. Apply liquid membrane-forming compounds immediately after final finishing and as soon as the free water has disappeared, no water sheen is visible, and bleeding has essentially ceased. Apply two coats of liquid membrane-forming compound with the second coat at right angles to the first. Apply both coats of liquid membrane-forming compounds uniformly until the original color of the concrete is obscured. Apply liquid membrane-forming compound according to the manufacturer’s instructions.

Do not apply the liquid membrane-forming compound to dry concrete surfaces. Moisten the concrete surface, without standing water, before applying the liquid membrane-forming compound. Protect the membrane from damage for the duration of the curing period. Re-apply the liquid membrane-forming compound if the membrane is cracked or damaged during the curing period.

c.	Forms-In-Place Curing. Formed concrete surfaces may be cured by retaining the forms in place for the entire curing period. Keep the forms moisture tight. Do not loosen forms. For wooden forms, keep the forms wet as required for wet curing. If gaps develop between the forms or between the forms and concrete:

(1)	remove the forms and implement another curing method

(2)	keep the gaps continuously filled with water for the remainder of the curing period.

d.	Accelerated Curing. Accelerated curing may be used only on Class P Concrete with a water-cement ratio of less than 0.35.

During the curing period, keep the concrete in a saturated curing atmosphere until the concrete achieves the required release strength.

The curing period may be accelerated by using saturated low-pressure steam, convection-heat, or radiant-heat in a suitable curing chamber to contain the live steam or heat. Provide at least 3 inches of clearance between the enclosure and forms to allow adequate circulation.

If accelerated curing methods are used, embed at least one temperature-recording device in the concrete to verify concrete temperatures are within the specified limits. Install one temperature-recording device, accurate to ±5°F, near the member’s midpoint, 6 to 8 inches from the top or bottom, and along the member’s centerline. Monitor the concrete temperature with the temperature-recording device sensor arranged and calibrated to continuously record, date, and identify the concrete temperature throughout the heating cycle. Begin recording temperatures once concrete is placed in the forms. Stop recording temperatures after the heating cycle is complete and when the concrete temperature is within 20°F of the air temperature to which the concrete will be exposed. Upon request, submit the temperature record to the Engineer for each precast concrete member.

While waiting to begin the heating cycle, maintain the concrete temperature between 50°F and 90°F and maintain concrete surface moisture as specified for the initial curing period. Do not apply steam, convection-heat or radiant-heat prior to initial set except to maintain the concrete temperature. Determine the time of initial set according to AASHTO T 197.

Begin the heating cycle immediately after the initial set. Prevent hot air and steam from blowing directly onto the concrete or forms. Increase the concrete temperature at an average rate not exceeding 40°F per hour until the curing temperature is reached. Limit curing temperature within the concrete to 175°F maximum. Decrease the concrete temperature not more than 40°F per hour until reaching a temperature 20°F above the temperature of the air to which the concrete will be exposed.

Apply radiant heat by pipes circulating steam, hot oil, or hot water, or by electric heating elements.

3.	Curing Temperature. To achieve adequate curing, maintain the concrete temperature at or above 50°F during the curing period. Add one addition day of curing for each day or portion of a day the concrete temperature falls below 50°F during the curing period.

4.	Ending Curing Operations. Continue curing operations uninterrupted until the required concrete properties, strength, and durability have developed or until there is reasonable assurance these properties will be achieved after the curing operations have been terminated.

Curing operations may be terminated after following are satisfied:

a.	The concrete has cured for:

(1)	at least 7 days.

(2)	at least 10 days when fly ash or ground granulated blast furnace slag in excess of 10 percent by weight of the Portland cement are used in the mix.

b.	The compressive strength from informational field tests reaches the following:

(1)	70 percent of the Specified Compressive Strength if post curing concrete temperature is expected to remain at or above 50°F until 100 percent of the Specified Compressive Strength is attained.

(2)	100 percent of the Specified Compressive Strength, if post curing conditions are expected to allow the concrete temperature to fall below 50°F before 100 percent of the Specified Compressive Strength is attained.

501-3.09 PROTECTION OF CONCRETE. Protect concrete from damage. Do not apply loads to the concrete until curing operations are completed and until the Engineer determines the concrete has attained sufficient strength to safely carry the applied loads without damage. Unless otherwise noted, sufficient strength is attained when the concrete has a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

- Release forms and falsework according to Section 512.

During the curing period, protect concrete from damaging mechanical disturbances. Protect concrete surfaces from damage by construction traffic, equipment, materials, rain or running water, and other adverse weather conditions. Meet the vibration limits during pile driving of Section 505.

Do not place fill materials against concrete structures until the end of the curing period and until the concrete has attained a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

Obtain authorization from the Engineer before driving vehicles or equipment, or storing materials on the structure. Keep the structure closed to traffic until the concrete has been accepted. Obtain authorization from the Engineer before opening the structure to traffic.

1.	Rain Protection. Provide materials and equipment on site to protect concrete until final set. During precipitation, or when the Engineer determines precipitation is likely before final set, employ materials and equipment to protect the concrete until final set occurs. Do not expose the concrete to rain or flowing water before final set occurs.

2.	Cold Temperature Protection. When air temperatures are expected to be below 35°F during concrete placement or the curing period, have materials and equipment in place to prevent the concrete temperature from falling below 35°F. Implement the cold temperature concreting plan when the air temperature in the shade, away from artificial heat, is less than 35°F or, in the opinion of the Engineer, is likely within 24 hours.

a.	Submittals. Submit a cold temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to be below 35°F during the concrete placement or during the curing period. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during cold weather for each concrete placement. Include procedures for abrupt changes in weather conditions and equipment failures.

b.	Preparation. Remove snow, ice, and frost from surfaces that will touch the concrete. Before beginning concrete placement, thaw the subgrade to at least 2 feet below the concrete to be placed. Do not place concrete around or adjacent to forms, embedded items, concrete, steel, or other materials unless such items are preheated and maintained at a temperature above 35°F.

c.	Temperature of Concrete Before Placement. Ensure concrete is between 50°F and 70°F during placement. Obtain these temperatures by heating the mixing water and/or aggregate. Heat mixing water to no more than 150°F.

When the temperature of the water or aggregate exceeds 100°F, mix them together so temperature of the combined ingredients does not exceed 80°F when the cementitious materials are added.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to cold weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

If the minimum curing temperature cannot be maintained, do not allow the concrete temperature to drop below 35°F. Provide extra protection in areas especially vulnerable to temperatures below 35°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Maintain the concrete temperature using methods such as insulated forms, enclosures, and indirect heat. When using combustion heaters, vent flue gases to the outside of the enclosure. Prevent overheating areas of concrete or drying during the curing period by directing heaters and ducts away from the concrete surface. Do not expose the concrete surface to air with a temperature more than 90°F, unless higher values are allowed according to the curing method.

Protection may be terminated when the air temperature in the shade, away from artificial heat is rising, above 35°F, and is expected to remain above 35°F until the end of the curing period. At the end of the protection period, remove the protection so the concrete surface drops in temperature gradually at a rate not more than 1.25°F per hour until the concrete temperature is within 20°F of the air temperature in the shade, away from artificial heat. If water curing is used, terminate the addition of water to the surface and allow the concrete surface to dry prior to exposure of the concrete to freezing temperatures.

3.	Hot Temperature Protection. When air temperatures are expected to exceed 90°F during concrete placement, have materials and equipment in place to prevent the concrete temperature from exceeding 90°F before final set and exceeding 150°F during the final curing period. Implement the hot temperature concreting plan when the air temperature in direct sunlight is greater than 90°F.

a.	Submittals. Submit a hot temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to exceed 90°F during the concrete placement. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during hot temperature for each concrete placement. Include procedures for abrupt changes in temperature conditions or equipment failures.

b.	Preparation. Prior to placing concrete, plan to minimize the exposure of the concrete to hot temperatures and direct sunlight. Cool surfaces that will touch the concrete to less than 90°F.

Do not sprinkle fine aggregate piles with water. If sprinkling coarse aggregates, monitor the moisture content and adjust the mixing water for the free water in the aggregate.

If replacing all or part of the mixing water with crushed ice, then ensure the ice is completely melted and thoroughly mixed with the other concrete materials before concrete placement commences.

c.	Temperature of Concrete Before Placement. Ensure concrete being placed in forms is between 50°F and 90°F. Obtain these temperatures by cooling the mixing water and/or aggregate.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to hot weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

Provide extra protection in areas especially vulnerable to temperatures above 90°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Protection may be terminated when the air temperature in direct sunlight drops below 90°F and is expected to remain below 90°F for at least 24 hours.

501-3.10 TOLERANCES. Produce concrete elements conforming to the following tolerances:

1.	Length:

a.	For dimensions 100 feet or less: ±3/4 inch.

b.	For dimensions over 100 feet: ±1 inch.

2.	Cross-sectional Dimensions:

a.	For dimensions 6 inches or less: -1/8 inch to +1/4 inch.

b.	For dimensions over 6 inches but not over 18 inches: -1/8 inch to +3/8 inch.

c.	For dimensions over 18 inches: -1/4 inch to +3/8 inch.

3.	Distortion of Cross-section: Limit the slope with respect to the specified surface, plane, or line to less than ±1/16 inch per foot, but not to exceed ±1/4 inch measured perpendicular to the long axis of member.

4.	Surface Irregularities (deviation from a 10-foot straight edge):

a.	For surfaces receiving a topping or are buried: ±1/4 inch.

b.	For surfaces not receiving a topping or are visible in the completed work: ±1/8 inch.

5.	Camber:

a.	For each member: ±1/8 inch per 10 feet of length, but not to exceed 1 inch from the approved camber.

b.	Variation between members: ±1 inch.

6.	Lateral Sweep (deviation from a straight line parallel to centerline of member):

a.	For member length 40 feet or less: ±1/4 inch.

b.	For member length over 40 feet but not over 60 feet: ±3/8 inch.

c.	For member length over 60 feet: ±1/2 inch.

7.	Deck Width (measured out-to-out): 0 inches to +2 inches.

8.	Position and Alignment:

a.	Bottom of footing elevation: ±0.1 feet.

b.	Profile grade: ±0.05 feet.

c.	Lateral position: ±0.1 feet.

d.	Skew: ±0.05 degrees.

9.	Bearing Seats:

a.	Elevation: ±0.01 feet

b.	Variation between bearing seats: Do not vary from a straight line coincident with the centerline of bearings and parallel to the surface of the bottom flanges more than 0.01 feet.

c.	Grade and cross slope: ±0.005 feet per foot.

10.	Openings:

a.	Size of opening: ±1/4 inch.

b.	Location of centerline of opening: ±1/2 inch.

11.	Embedded Items:

a.	Bolts: ±1/4 inch.

b.	Utility hangers: ±1/2 inch.

c.	Weld Plates: ±1/2 inch measured along the length of the member, ±1/8 inch measured perpendicular to the length of the member.

d.	Inserts: ±1 inch.

e.	Rail post anchor plates: ±1/4 inch.

f.	Expansion joints: ±1/8 inch.

g.	Electrical conduits: ±1/2 inch.

h.	Deck drains: ±1/2 inch.

i.	Other embedded items: ±1/2 inch.

501-3.11 CONSTRUCTION JOINTS. Unless otherwise noted, locate construction joints where specified in the Contract documents. Obtain approval before adding, deleting, or relocating construction joints specified in the Contract documents. Make requests for such changes in writing, accompanied by a drawing depicting the joint. The Engineer will evaluate the proposed construction joint to determine if the joint will affect the strength or durability of the concrete. Joints noted as "permissible" do not need the Engineer's approval before deleting. When permitted, place the joints where they will not be exposed to view in the finished structure.

At horizontal construction joints, place gage strips 1-1/2 inches thick inside the forms along exposed faces to give the joints straight lines.

Do not use wire mesh forming material.

If the Plans require a roughened surface on the joint, create grooves at right angles to the length of the member. Make grooves that are 1/2 to 1 inch wide, 1/4 to 1/2 inch deep, and spaced equally at twice the width of the groove. Terminate the grooves within 1-1/2 to 2 inches from the edges of the joint.

If the Plans require a smooth surface on the joint, provide a trowel finish.

Include shear keys at the joint when the Contract documents do not require a roughened surface or a smooth surface. Make shear keys of formed depressions with slight beveling to ensure ready form removal. Do not use raised shear keys. Make shear keys that meet the following:

1.	For tops of beams, at the tops and bottoms of boxed girder webs, in diaphragms, and in crossbeams, use shear keys 1-1/2 inches deep, 8 inches long, and spaced at 16 inches.

2.	In other locations, use shear keys at least 1-1/2 inches deep and 1/3 of the joint width.

Terminate the shear keys within 1-1/2 to 2 inches of the joint edge.

Clean construction joints of surface laitance and other foreign materials before fresh concrete is placed against the surface of the joint. Flush construction joints with water and allow the joint to dry to a surface-dry condition immediately prior to placing concrete.

501-3.12 FORMS AND FALSEWORK. Use forms and falsework designed and constructed according to Section 512.

501-3.13 PRECAST CONCRETE MEMBERS. In addition to the requirements listed in this Section, conform to Section 502 when fabricating prestressed concrete members.

1.	Shop Drawings. Provide shop drawings for precast concrete members. Include details not provided in the Plans for the construction and erection of the members. Cast members only after shop drawings are approved. Use precast methods for cast-in-place elements when approved. Submit shop drawings, showing construction joint details and other required information.

2.	Manufacture. Prestress concrete according to Section 502. Fabricate and install reinforcing steel according to Section 503.

Unless otherwise noted, use Class P concrete for precast concrete members meeting the Specified Compressive Strength noted on the Plans.

3.	Storage and Handling. Handle and move precast concrete members without damage. Store and transport precast concrete members in an upright position with the directions of the support reactions on the member during storage or transport as if in the final position. Locate support points during transport and storage within 30 inches of their final position, or as shown on approved shop drawings. Ship only after the member has cured at least 7 days and has a compressive strength not less than 100 percent of the Specified Compressive Strength.

4.	Erection. Maintain member stability during transport, lifting, and erection operations. Limit concrete tension stresses due to transport, lifting, and erection operations to less than 500 psi.

Set interchangeable precast concrete members so the initial difference between the top surfaces of the edges of adjacent precast concrete members is no more than 1/2 inch at midspan and no more than 1/4 inch at the bearings.

Set and securely brace precast concrete members within a span before making shear connections. Secure the member to the structure, and provide temporary braces necessary to resist wind or other loads immediately after erecting each precast concrete member.

Provide and use forcing devices as shown in the Plans or as recommended by the precast concrete member manufacturer. Use devices maintaining the top edges of adjacent members at the same elevation while casting or welding diaphragms, welding shear connector plates, and while placing and curing grout in the shear keys.

Make field welds according to Section 503 and Section 504.

Install cast-in-place diaphragms within 2 weeks after setting precast concrete members on their bearings.

If cast-in-place diaphragms cannot be placed within the prescribed time limit, ensure the members are adequately braced to resist movement and rotation. Submit a bracing plan including complete details and substantiating calculations, sealed by a Professional Engineer registered in the State of Alaska.

Erect and place precast deck panels so the mating surfaces do not allow grout leakage. Seal joints where grout leakage may occur.

When the Plans require filling keyways between adjacent concrete members with grout, place grout meeting Subsection 701-2.03 and according to the manufacturer's written instructions. Clean joints of surface laitance and other foreign material before placing grout. Do not place loads on the grouted members until the grout compressive strength has reached 5000 psi.

Tightly pack and rod the grout in the keys and spaces. Keep the grout surface smooth and neat. Ensure the grout surface meets the member edges throughout their lengths and matches the surface elevation of the members with a tolerance of ±1/8 inch.

501-3.14 PLACING ANCHOR BOLTS. Secure anchor bolt assemblies where shown on the Plans.

When casting anchor bolts in concrete, secure anchor bolts before placing concrete in the forms. Do not disturb anchor bolts after concrete has been placed.

When installing anchor bolts in pipe sleeves, pre-cast holes, cored holes, or drilled holes, completely fill the cavity with grout meeting Subsection 701-2.03. Do not allow water to freeze in the cavity. Do not allow foreign material in the cavity.

501-3.15 UTILIDUCTS, PIPES, CONDUITS, DUCTS, AND UTILITY HOLES. When utiliducts, pipes, conduits, and ducts will be encased in concrete, install them in the forms before placing the concrete. Support the utiliducts, pipes, conduits, and ducts to prevent displacement during concrete placement.

Install utiliducts and utility holes parallel to the roadway centerline unless noted otherwise. Prevent bond between the utiliducts and concrete by tightly wrapping the utiliducts with at least two layers of asphalt felt.

501-3.16 REMOVING CONCRETE. Do not damage other portions of the structure remaining in place when removing concrete.

Determine and delineate the extent of removal area. Outline the area with a 3/4-inch deep saw cut to form faces perpendicular to the surface prior to the removal of concrete. Do not cut or damage existing reinforcing steel or prestressing steel. During the course of removal, the Engineer may suspend removal or may require additional removal and outline saw cut.

Use any combination of mechanical methods, water-blast cleaning, or abrasive-blast cleaning to remove coarse or broken concrete until a dense, uniform surface of concrete exposing solid coarse aggregate is obtained. When using mechanical methods for removal of concrete, meet the following:

1.	Use impact tools weighing less than 15 lbs.

2.	Operate impact tools at an angle less than 45 degrees relative to the surface of the concrete being removed.

3.	Use hand tools such as hammers and chisels or small air chisels, water blast cleaning, or abrasive blast cleaning to remove final particles of unsound concrete.

During the removal operation do not damage existing reinforcing steel, prestressing steel, or concrete to remain in place.

- Before applying the repair material, clean the surface according to ASTM D 4258 within 24 hours of applying the repair material.

- Use water meeting the requirements of Subsection 712-2.01 for removal operations.

501-3.17 CRACK EVALUATION. The Engineer will evaluate concrete that is cracked during execution of the Contract. Measure cracks at their widest point.

For concrete decks and approach slabs, allow the Engineer to inspect any surface cracking immediately after termination of concrete curing operations, before prestressing (if applicable), and before releasing falsework. If any 500 square foot portion of the concrete deck or approach slab has cracks, whose width exceeds 0.020 inches and combined lengths total more than 16 feet, treat the surface by performing low-viscosity resin crack repair.

For other concrete, cracks will be evaluated based on the crack width.

1.	For crack widths equal to and greater than 0.060 inches, the concrete will be considered unacceptable.

2.	For cracks widths equal to and greater than 0.013 inches but less than 0.060 inches, the Engineer will evaluate the cracked concrete for structural adequacy and durability. If the Engineer determines the crack may affect structural adequacy or durability, the Engineer may reject the concrete, the structure, or a portion of the structure. If the Engineer determines the cracked concrete is acceptable, repair the crack by performing low-pressure crack repair according to 501-3.18.

3.	For cracks widths less than 0.013 inches wide, the crack will be considered acceptable with no additional evaluation or repairs required.

501-3.18 CRACK REPAIR. Perform crack repairs and replace unacceptable concrete at no cost to the Department. No contract time extension will be given for repairing, removing, and replacing unacceptable material.

1.	Low-Pressure Crack Repair. Repair cracked concrete according to the following requirements:

a.	Crack Repair Plan. Submit a crack repair plan to the Engineer. Do not repair the crack until the Engineer has approved the crack repair plan. Include the following in the crack repair plan:

(1)	Experience of the injection equipment technicians

(2)	Evaluation of the crack width and the recommended epoxy viscosity allowing the epoxy to achieve and maintain the penetration requirements

(3)	Material information including manufacturer's product data sheets

(4)	Equipment

(5)	Crack preparation, injection procedures, and injection sequence

(6)	Cleanup procedures

b.	Experience. Provide epoxy injection technicians who have a minimum of 2 years experience in performing repairs using the methods and materials of the selected system.

c.	Materials. Use epoxy adhesive for crack sealing meeting the requirements of Subsection 501-2.01.5 and capable of containing the crack injection epoxy. Use epoxy adhesive for crack injection meeting the requirements of Subsection 501-2.01.5 and of viscosity capable of filling at least 90 percent of the crack volume.

d.	Equipment. Use positive displacement plural component pumps, specifically designed to meter, mix, and to inject epoxy, and capable of filling at least 90 percent of the crack volume.

e.	Surface and Crack Preparation. Remove contaminants and other foreign material reducing the effectiveness of the surface seal and repaired crack. Allow adequate time for drying. If cleaning solutions are used, perform trial tests to verify the contaminants can be removed. Prepare the surface and crack according to the epoxy manufacturer’s instructions.

f.	Entry and Venting Ports. Install entry/venting ports spaced equal to the thickness of the concrete member along one face of the crack. Acceptable types of entry/venting ports are fittings inserted into drilled holes, bonded flush fittings, and gasket devices covering unsealed portions of interrupted seals, allowing injection of epoxy directly into the crack without leaking epoxy.

g.	Mixing Epoxy for Crack Sealing. Mix the epoxy adhesive for crack sealing to the volume ratio prescribed by the manufacturer.

h.	Surface Sealing. Seal the surface of the crack with epoxy adhesive for crack sealing.

i.	Mixing Epoxy for Crack Injection. Mix the epoxy adhesive for crack injection to the volume ratio prescribed by the manufacturer.

j.	Epoxy Injection. Assure the crack seal is cured and capable of containing the crack injection epoxy. Inject the epoxy according to the epoxy manufacturer’s instructions. Do not inject epoxy until the air, substrate, and epoxy are within the manufacturer's application temperature range. Limit injection pressure to prevent propagation of the crack, prevent additional damage, and injection pressure in excess of 50 psi.

Inject the epoxy in the sequence noted in the approved crack repair plan. Ensure at least 90 percent of the crack volume is filled.

Maintain the epoxy temperature within the manufacturer's application temperature range during injection operations and until the epoxy is cured.

k.	Finishing and Cleanup. After the injected epoxy is cured, remove ports and surface seal flush with the concrete surface. Do not damage the injected epoxy and do not heat the surface seal to aid in removal.

2.	Low-Viscosity Resin Crack Repair. When concrete deck or approach slab crack repair is required, the Engineer will define the repair area with the following boundary limits:

a.	Beginning and ending on straight lines perpendicular to the direction of traffic and extending across the entire width of the concrete deck or approach slab, between the concrete barriers or curbs.

b.	Beginning and ending at least 5 feet beyond the furthest opposing cracks, measured from where the crack widths exceeds 0.020 inches

If grinding is required, treat the concrete before grinding.

Before treatment, ensure the concrete surface is clean, sound and free of foreign materials that may reduce the effectiveness of the repaired cracks. If the concrete surface becomes contaminated before placing the resin, repeat the cleaning process.

Apply low-viscosity resin to the repair area. Protect barriers, railing, joints, and drainage facilities to prevent contamination by the treatment material.

Completely cover the deck surface with resin so the resin penetrates and fills cracks. Ensure the relative humidity is less than 80 percent, the prepared area is dry, and the surface temperature is at least 50°F and not more than 90°F when the resin is applied. Apply the resin and distribute excess material within the manufacturer's listed pot life. For textured surfaces, including grooved surfaces, remove excess material from the texture indentations.

For concrete decks and approach slabs not receiving a waterproofing membrane, apply aggregate for abrasive finish within 20 minutes of resin application and before setting occurs. Broadcast the aggregate for abrasive finish evenly over the entire treated area at a rate of 1.5 to 2.5 pounds per square yard.

501-3.19 CLEANUP. Remove concrete splatter, paint marks, laitance, rust staining, chamfer strips, and other material not providing a uniform texture and color to the concrete surface.

501-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Cubic Yard. The lesser of the actual volume or neat line volume of each class of concrete accepted in place in the finished structure.

Class DS Concrete. The sum of the lengths of drilled shafts complete in place, measured along the centerline of the drilled shaft from the bottom to the top.

Concrete Headwall.  Measured by lump sum.  Includes material and labor to construct the headwall.

- Precast Concrete Members. Measured per unit, complete in place.

- Crack repair for unacceptable concrete will not be measured for payment.

501-5.01 BASIS OF PAYMENT.

Material not appearing in the Bid Schedule and is contained within, embedded, or attached to concrete elements is subsidiary.

- Crack repair for unacceptable concrete is subsidiary.

Precast Concrete Member. Payment for precast concrete member includes materials and work for the following items: Class P concrete, reinforcing steel contained in the member, prestressing steel, plates, nuts, inserts contained within the concrete member, bolts, studs, anchor bars, blockouts, elastomeric bearing pads, grout, drains, and other miscellaneous steel embedded in or attached to the precast concrete member.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

501(1) 	Class A Concrete	Lump Sum

501(2) 	Class A-A Concrete	Lump Sum

501(5)	Prestressed Concrete Member (125’ Decked Bulb-Tee)	Each

501(10)	Concrete Headwall	Lump Sum

Replace Section 502 with the following:

SECTION 502

PRESTRESSING CONCRETE

502-1.01 DESCRIPTION. Prestress precast or cast-in-place concrete by furnishing, placing, tensioning, and bonding prestressing steel by using either pretensioning or post-tensioning methods or a combination of the two methods according to the Contract documents.

For pretensioning, this work also includes furnishing and installing materials and equipment necessary to prestress concrete as designated in the Contract documents.

For post-tensioning, this work includes furnishing and installing post-tensioning systems and other pertinent items necessary for the particular prestressing system used, including but not limited to ducts, anchorage assemblies, supplementary reinforcement, and grout used for pressure grouting ducts.

502-1.02 DEFINITIONS.

ANCHORAGE. An assembly of various hardware components that secure a tendon at its ends after it has been stressed imparting the tendon force into the concrete.

ANTICIPATED SET. The set that was assumed to occur in the design calculation of the post-tensioning forces immediately after load transfer.

BEARING PLATE. Hardware that transfers the prestressing force directly into concrete.

BLEED. The autogenous flow of mixing water within or its emergence from newly placed grout caused by the settlement of the solid materials within the mass and filtering action of strands.

COMPRESSIVE STRENGTH TEST. The average strength test of concrete, from at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders sampled according to AASHTO T 141, cured according to AASHTO R 39 or WAQTC FOP for AASHTO T 23, and tested according to AASHTO T 22 or sampled, cured, and tested to equivalent ASTM test methods. Unless otherwise noted, tested at an age of 28 days.

DUCT. Material forming a conduit to accommodate prestressing steel installation and provide an annular space for the grout that protects the prestressing steel.

FLUIDITY. A measure of time, expressed in seconds, necessary for a stated quantity of grout to pass through the orifice of a flow cone.

GROUT. A mixture of cementitious materials and water with or without admixtures proportioned to produce a pumpable consistency without segregation of the constituents when injected into the duct to fill the space around the prestressing steel.

GROUT CAP. A device that contains the grout and forms a protective cover sealing the post-tensioning steel at the anchorage.

INFORMATIONAL FIELD TEST. A compressive strength test, determined by the Engineer, from field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure; except, the compressive strength test may consist of one 6.0 x 12.0 inch or one 4.0 x 8.0 inch compressive strength test cylinder.

POST-TENSIONING. A method of prestressing in which the tendons are tensioned after the concrete has reached a specified compressive strength.

POST-TENSIONING SCHEME OR LAYOUT. The pattern, size and locations of post-tensioning tendons.

POST-TENSIONING SYSTEM. An assembly of proprietary post-tensioning hardware, including but not limited to anchorage assembly, local zone reinforcement, wedge plate, wedges, bearing plate, prestressing steel, duct, duct connections, vents and grout cap, used to construct a tendon of a particular size and type.

PRESTRESSING STEEL. The steel element of a post-tensioning tendon, which is elongated and anchored to provide the necessary permanent prestressing force.

SET (Also Anchor Set or Wedge Set). The total movement of a point on the strand outside the anchoring wedges during load transfer from the jack to the permanent anchorages. Set movement is the sum of slippage of the wedges with respect to the anchorage head and the elastic deformation of the anchor components.

STRAND. An assembly of several high-strength steel wires wound together. Strands usually have six outer wires helically wound around a single straight wire of a similar diameter.

STRAND COUPLER. An assembly by which the prestressing force may be transmitted from one partial length prestressing tendon to another. (Strand couplers are not permitted.)

TENDON. A single or group of prestressing steel elements and their anchorage assemblies that imparts prestress to a structural member. Also, included are ducts, grouting attachments, grout and corrosion protection filler materials or coatings.

TENDON SIZE. The number of individual strands of a certain strand diameter.

THIXOTROPIC. The material property exhibited by certain grouts that enable material to stiffen, achieve a higher viscosity, in a short time while at rest, but to become liquid, acquire a lower viscosity, when mechanically agitated.

VENT. Tubing or pipe used for injection of grout into the duct and to allow escape of air, water, grout and bleed water from the duct.

WEDGE. A conically shaped device that anchors the strand in the wedge plate.

WEDGE PLATE. The hardware that holds the wedges of a multi-strand tendon and transfers the tendon force to the anchorage assembly.

502-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501

Water	Subsection 712-2.01

Reinforcing steel 	Subsection 709-2.01

Epoxy-Coated Reinforcing Steel	Subsection 709-2.01

Prestressing Steel and Fittings	Section 721

Post-tension Grout	Subsection 701-2.08

Zinc-Rich Paint	Subsection 708-2.01.1

Epoxy Bonding Agents	AASHTO M 235, Type V

CONSTRUCTION REQUIREMENTS

502-3.01 PRETENSIONING METHODS. Select a pretensioning method providing the magnitude and distribution of prestressing force required in the Contract documents.

1.	Shop Drawings. Before casting members to be prestressed, submit shop drawings including the following:

a.	Complete details and substantiating calculations of the method, materials, and equipment proposed for use in the prestressing operations.

b.	Details and locations of embedded items including reinforcing steel, lifting devices, coil anchors, anchor bolts, drainage systems, utility conduits and other such items.

c.	Details of the arrangement and locations of prestressing steel in the member.

d.	Details of additional reinforcing steel or rearrangement of reinforcing steel.

e.	Details of revisions to the concrete dimensions.

f.	Complete specifications and details of the prestressing steel and anchoring devices to be used.

g.	An outline of the method and sequence of stressing

h.	The anchoring stresses, strand release sequence, and other data pertaining to the prestressing operations.

i.	The anticipated camber immediately after prestressing force transfer and at other times after prestressing force transfer when loads are applied to the member.

2.	Quality Control Plan. Submit a quality control plan to verify the materials and workmanship incorporated into the prestressed concrete members conform to the requirements.

Perform pretensioning operations under the direct supervision and control of a pretensioning technician, skilled in the prestressing method, to aid and instruct in using the prestressing equipment and in installing the materials to obtain required results.

3.	Protection of Prestressing Steel. Protect prestressing steel and anchor assemblies against physical damage and corrosion. Keep prestressing steel and anchor assemblies clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials.

A corrosion inhibitor may be placed in the package or form, incorporated into the packaging material, or applied directly to the steel. Do not use corrosion inhibitors that have deleterious effect on the steel, concrete, or bond strength of steel to concrete. Clearly mark the shipping package or form with a statement that the package contains high-strength prestressing steel, and the type of corrosion inhibitor used, including the date packaged.

4.	Prestressing Equipment. Use hydraulic jacks to tension the prestressing steel strands.

Equip each jack used to stress strands with either two calibrated pressure gages or one calibrated pressure gage and one calibrated load cell.

Permanently mark the jack body with the ram area. Ensure each pressure gage is fully functional, calibrated and has an accurately reading dial at least 6 inches in diameter. Calibrate the jack and each pressure gage as a unit within 6 months prior to stressing strands, after each repair, and every 6 months until stressing operations are complete.

Meet the following calibration requirements for each jack and gauge unit used on the project:

a.	Provide calibration tests at various jack cylinder extensions including 25 percent, 50 percent, and 75 percent of the maximum cylinder extension

b.	Provide the ram force, as indicated on a calibrated load cell, for at least 5 gage pressure increments for each cylinder extension.

c.	Perform the calibration with the equipment setup in the same configuration that will be used at the job site.

d.	Use load cells calibrated within the past 12 months to calibrate stressing equipment.

e.	Provide a certified calibration curve prior to stressing strands and after each calibration.

Equip each load cell with an indicator to determine the prestressing force in the strand. Ensure the range of the load cell is such that the lower 10 percent of the manufacturer's rated capacity will not be used in determining the prestressing force. Calibrate each load cell within 12 months prior to stressing strands, after each repair, and every 12 months until the stressing operations are complete.  Provide a certified calibration chart to the Engineer prior to stressing strands and after each calibration.

5.	Placing Reinforcing Steel and Prestressing Steel. Place reinforcing steel according to Section 503, except as modified by this Section.

Place prestressing steel in the position required in the Contract documents or on the approved shop drawings.

6.	Girder Inserts. Provide threaded inserts, coil anchors, or approved equal in the girder as required in the Contract documents.

Additional inserts may be cast into the member to accommodate forms or other construction related requirements provided the insert does not affect the character of the finished work.

7.	Pretensioning. Stress strands to the magnitude specified in the Contract documents by either single strand stressing or multiple strand stressing. Prior to applying full pretensioning, bring strands to be stressed in a group, for multiple strand stressing, to a uniform initial tension that is sufficient to eliminate slack and equalize the stresses in the strands. Limit the jacking stress, strand stress before seating, to 70 percent of the minimum breaking strength (0.70 fpu) of the prestressing steel.

Ensure that the tension load indicated by the gauge(s) is within 5 percent of the calculated tension load based on elongation measurements for each strand.

Use approved low-friction devices at points of change in slope of strand trajectory when tensioning harped strands.

Tension harped strands from both ends of the member if the prestressing force, as determined by elongation measurements, is less than 95 percent of force indicated by the jack gauges. Ensure the prestressing force from the sum of elongation measures at both ends of the member is within 5 percent of the force indicated by the jack gauges.

When splicing strands, locate splices outside of the prestressed units. Account for additional elongation due to the splice when verifying the prestressing force based on elongation measurements.

Keep the temperature of the strands during tensioning and concrete placement within 25 °F of the concrete temperature during placement. During the interval between tensioning and concrete placement, do not let changes in the temperature of the strands alter the stress level in the strands more than 5 percent of the jacking stress.

8.	Placing Concrete. Produce and place concrete according to the requirements of Section 501, except as modified by this section.

Consolidate the concrete using any combination of internal and external vibration that does not displace the reinforcing steel or other items embedded in the concrete.

9.	Release. Do not release prestressing strands and transfer prestressing forces to the member until the concrete compressive strength, as determined from informational field tests, has attained the minimum initial compressive strength, release strength (f'ci), as indicated in the Contract documents.

Cut or release the elements in an order that minimizes the lateral eccentricity of the pre-stress. Cut prestressing strands to a depth of at least 1 inch from the concrete surface. Fill the recess with cement mortar and finish flush to the concrete surface. Alternatively, cut prestressing strands flush with the end of the member. Clean and paint the exposed ends of the strand and a 1-inch strip of adjoining concrete. Use a wire brush or abrasive blast cleaning to remove dirt and residue not firmly bonded to the metal or concrete surfaces. Cover the surfaces with a thick application of zinc-rich paint. Thoroughly mix the paint at the time of application and work it into any voids in the strands. Apply two applications to surfaces that are not covered by concrete or mortar.

If the member's curing is accelerated according to Section 501, transfer the stressing force to the concrete immediately after the heating cycle has been discontinued, while the concrete is still moist, and before the temperature of the concrete drops below 100°F.

502-3.02 POST-TENSIONING METHODS. Select a post-tensioning system that provides the magnitude and distribution of prestressing force specified in the Contract documents.

For box girders, distribute the prestressing steel so the force in each girder stem does not vary more than 5 percent from the required force per girder stem and the required total force in the superstructure is obtained and distributed symmetrically about the centerline of the typical section.

Do not exceed 75 percent of the minimum breaking strength of the prestressing steel for jacking stresses and temporary tensile stresses in the prestressing steel. Do not exceed 70 percent of the minimum breaking strength of the prestressing steel at anchorages after anchor set.

Working force and working stress will be considered as the force and stress remaining in the prestressing steel after losses, due to creep and shrinkage of concrete, elastic compression of concrete, relaxation of steel, set, sequence of stressing, friction, take up of anchorages and other losses peculiar to the method and system of prestressing, have taken place and have been accommodated. Calculate loss of prestress according to the AASHTO LRFD Bridge Design Specifications.

1.	Shop Drawings and Calculations. Before casting members to be prestressed, submit shop drawings and supporting calculations of the prestressing system to the Engineer no less than 45 days prior to the placement of bridge concrete. Submit four sets of the drawings for initial review. After the initial submittal has been reviewed and comments from the Engineer have been received and implemented, submit additional drawings to the Engineer for approval and for use during construction according to Subsection 105-1.02.

Proide complete details on the shop drawings of the prestressing system and substantiating calculations of the method, materials, and equipment to be used in the prestressing operations, including any additions or rearrangement of reinforcing steel and any revision in concrete dimensions from that shown on the Plans. Provide details of the method and sequence of stressing. Include complete specifications and details of the prestressing steel and anchoring assemblies, working stresses, anchoring stresses, type of ducts, initial prestress losses, final prestress losses and other data pertaining to the prestressing operation. Show tendon geometry and locations complying with the plans and the limitations of the selected post-tensioning system. Provide vent details including locations, high point outlet inspection details, anchorage inspection details, grout caps, protection system materials and application limits. Include on the shop drawing the location of the anchorages, vents, and duct enclosures at 2-foot maximum intervals along the length of the member.

Submit calculations for the anticipated camber immediately after prestressing force transfer and at other times after prestressing force transfer when loads are applied to the member.

Submit calculations for the anticipated tendon elongation. Utilize the modulus of elasticity, based on nominal area, as furnished by the prestressing steel manufacturer for the lot of steel being tensioned. Provide tendon force diagrams, after friction, wobble and anchor set losses, on the shop drawings based upon the expected friction curvature and wobble coefficients and values for the post-tensioning system used. Show the coefficients and values on the shop drawings.

Provide shop drawings, calculations, and procedures related to post-tensioning, prepared and sealed by a Professional Engineer registered in the State of Alaska specializing in post-tensioning concrete. Bear the signature and seal of the Professional Engineer who specializes in post-tensioning construction on all calculations, drawings, and procedures.

Include post-tensioning system certification(s) conforming to Section 721.

2.	Post-tensioning Technician. Perform post-tensioning field operations under the direct supervision of a qualified post-tensioning technician. Provide a post-tensioning technician with at least five years of experience in the construction of post-tensioned prestressed concrete structures. Provide a technician, skilled in the prestressing method, to aid and instruct in using the prestressing equipment and in installing the materials to obtain required results.

Perform grouting under the direct supervision of a certified grouting technician. Provide a technician skilled in various aspects of grouting whom the American Segmental Bridge Institute certifies as an "ASBI Certified Grouting Technician".

Ensure the post-tensioning technician is present during duct installation, tendon tensioning, and grouting operations and provides close observation and control of post-tensioning and grouting operations, as necessary for compliance with the Contract. Submit the name of the post-tensioning technician and proof of certification to the Engineer no less than thirty days before the start of bridge concrete placement operations.

3.	Protection of Prestressing Steel and Anchorages. Protect prestressing steel and anchor assemblies against physical damage and corrosion. Keep prestressing steel and anchor assemblies clean and free of deleterious material such as grease, oil, wax, paint, or other foreign materials.

A corrosion inhibitor may be placed in the package or form, incorporated into the packaging material, or applied directly to the steel. Do not use corrosion inhibitors that have deleterious effect on the steel, concrete, or bond strength of steel to concrete. Clearly mark the shipping package or form with a statement that the package contains high-strength prestressing steel, and the type of corrosion inhibitor used, including the date packaged.

A corrosion inhibitor may be placed in the ducts unless prestressing steel installation, tensioning, and grouting is performed within seven days. Do not use corrosion inhibitors that have deleterious effect on the steel, concrete, or bond strength of steel to concrete. Submit the name, manufacturer, and type of corrosion inhibitor to be used in the ducts at least seven days before installation of any prestressing steel.

If prestressing steel is installed in ducts but not tensioned and grouted within the seven days, perform Nondestructive Examination (NDE) by either videoscoping the entire length of the prestressing steel inside the ducts or visually inspecting the prestressing steel upon removing the prestressing steel from the duct for corrosion. Perform NDE inspection at least once every seven days until the prestressing steel is tensioned and grouted. Perform NDE inspection to the satisfaction of the Engineer. Provide a report of the tendon condition to the Engineer following each NDE inspection for each tendon installation.

Do not weld on or near prestressing steel, ducts, anchorages, or other assemblages. Protect prestressing steel and hardware from weld spatter or other damage. Once the prestressing steel has been installed, do not make welds or grounds for welders on the forms, reinforcing steel, or adjacent steel members.

4.	Prestressing Equipment. Use hydraulic jacks to tension the prestressing steel strands.

Equip each jack used to stress strands with either two calibrated pressure gages or one calibrated pressure gage and one calibrated load cell.

Permanently mark the jack body with the ram area. Ensure each pressure gage is fully functional, calibrated and has an accurately reading dial at least 6 inches in diameter. Calibrate the jack and each pressure gage as a unit within 6 months prior to stressing strands, after each repair, and every 6 months until stressing operations are complete.

Meet the following calibration requirements for each jack and gauge unit used on the project:

a.	Provide calibration tests at various jack cylinder extensions including 25 percent, 50 percent, and 75 percent of the maximum cylinder extension

b.	Provide the ram force, as indicated on a calibrated load cell, for at least 5 gage pressure increments for each cylinder extension.

c.	Perform the calibration with the equipment setup in the same configuration that will be used at the job site.

d.	Use load cells calibrated within the past 12 months to calibrate stressing equipment.

e.	Provide a certified calibration curve prior to stressing strands and after each calibration.

Equip each load cell with an indicator to determine the prestressing force in the strand. Ensure the range of the load cell is such that the lower 10 percent of the manufacturer's rated capacity will not be used in determining the prestressing force. Calibrate each load cell within 12 months prior to stressing strands, after each repair, and every 12 months until the stressing operations are complete.  Provide a certified calibration chart to the Engineer prior to stressing strands and after each calibration.

5.	Enclosures for Post-Tensioning. Accurately place enclosures (anchorages, ducts, and vents) for prestressing reinforcing according to the Plans or approved shop drawings.

Set and hold the anchorage assemblies and block-out templates for anchorages so their axis coincides with the axis of the tendon and the wedge plates are normal in all directions to the tendon. Securely fasten anchorages and block-outs to prevent displacement during concrete placement. Unless otherwise specified in the Contract documents or shown on the approved shop drawings, recess the anchoring assemblies in formed block-outs so that the ends of the prestressing steel and anchoring assemblies will be at least 3 inches inside of the end surface of the member. Construct block-outs in leak proof forms that create neat lines with the end surface of the member.

Securely fasten ducts at the proper locations in the forms by ties to reinforcing steel that are adequate to prevent displacement during concrete placement. Use supplementary support bars where needed to maintain proper alignment of the duct. Use hold-down ties to prevent displacement due to duct buoyancy in the fluid concrete. Fasten ducts at 2-foot maximum intervals along the member.

Do not damage the ducts during installation. Do not crimp, flatten, or dent the ducts. Do not perforate the ducts or provide openings in the ducts except at locations designated in the Contract documents or shop drawings. After duct installation, inspect ducts for damage. Repair duct sections to the satisfaction of the Engineer at no additional cost to the Department and no adjustment in Contract time.

After installation in the forms, prevent the entry of water or debris into the ducts and anchorages.

Prior to placing forms for closing slabs of box girder cells, demonstrate to the Engineer that the ducts are unobstructed.

6.	Location of Grout Vents. Place grout vents at locations designated in the Contract documents or on the approved shop drawings. Equip grout vents with positive shut-off devices. Extend grout tubes with sufficient distance out of the concrete member to allow for proper closing of the valves.

7.	Placing Reinforcing Steel and Prestressing Steel. Place reinforcing steel according to the requirements of Section 503 and as modified by this Section.

Place prestressing steel in the position as designated in the Contract documents or on the approved shop drawings. Install the prestressing steel in the enclosures by pushing or pulling the total number of strands in a tendon individually or as a unit.

For strands that are pushed, the end of the strands may be rounded or fitted with a smooth protective cap.

For strands that are pulled, the end of the strands may be fitted with a special steel wire sock or other device attached to the end strands to pull the assembled tendon through the duct. Do not weld the ends of the strands together for this purpose. The end of the pre-assembled tendon may be rounded for smooth passage through the duct.

Cut strands using an abrasive saw or equal. Do not flame cut strands.

Immediately prior to installing the prestressing steel, demonstrate to the Engineer that the ducts are free of water, debris, and obstructions by passing a torpedo through the ducts. Use a torpedo having the same cross-sectional shape as the duct and is 1/4 inch smaller all around than the clear, nominal inside dimensions of the duct. Make no deductions to the torpedo section dimensions for tolerances allowed in the manufacture or fixing of the ducts. For straight ducts, use a torpedo at least 2 feet long. For curved ducts, determine the length so that when both ends touch the outermost wall of the duct, the torpedo is 1/4 inch clear of the innermost wall. If the torpedo will not travel completely through the duct, the Engineer may reject the member, unless a workable repair can be made to clear the duct. Ensure the torpedo passes through the duct easily, by hand, without resorting to excessive effort or mechanical assistance.

If the strands do not easily pass through the duct or an obstruction is encountered, do not force strands through the duct.

Do not install the prestressing steel in the duct prior to placing and curing of the concrete.

Straighten prestressing steel strands that are to be stressed simultaneously or when necessary to ensure proper positioning in the ducts.

8.	Placing Concrete. Produce and place concrete according to the requirements of Section 501 and as modified by this section.

Consolidate the concrete using any combination of internal and external vibration that does not displace the reinforcing steel, anchorages, ducts, grout vents, or other items embedded in the concrete.

9.	Post-tensioning. Do not begin tensioning operations until the concrete compressive strength, as determined from informational field tests, has attained the minimum initial compressive strength, release strength (f'ci), as indicated in the Contract documents. Do not begin tensioning operations until after the Engineer approved patches or repairs have been satisfactorily completed.

Perform stressing of tendons in conformance with the sequence shown on the approved shop drawings. Stress tendons in such a sequence that lateral eccentricity of prestress and loss of prestress will be a minimum. Stress tendons symmetrically about the center of the typical section so no more than one tendon is eccentric about the centerline at any one time. Sequence the stressing of the tendons so the individual tendon force does not exceed the tendon force in other tendons by more than 50 percent of the final jacking force of the tendon.

Stress strands in each tendon simultaneously. Stress tendons by jacking from only one end of the member unless otherwise approved by the Engineer.

Conduct the tensioning process so that tension being applied and the elongation of the prestressing steel may be measured. Measure the tendon elongation to the nearest 1/16 inch. Tension tendons to a preliminary force between 5 and 25 percent of the final jacking force to eliminate any wedge slip or take-up in the tensioning system before elongation measurements are started. Record the preliminary force so that it can be used in the elongation measurement. Mark at least 25 percent of the strands in each tendon prior to final stressing to permit measurement of elongation and to ensure the anchor wedges are set properly.

For the required tendon force, ensure the observed elongation agrees within 5 percent of the anticipated tendon elongation. In the event the observed elongation is not within 5 percent of the anticipated tendon elongation, determine the source of error and revise the post-tensioning operation to the satisfaction of the Engineer before proceeding. Do not overstress the tendon to achieve the theoretical elongation. No claim for damages or additional compensation or adjustment in Contract time resulting from revisions to the post-tensioning operation will be made or allowed.

Multi-strand post-tensioning tendons having wires that fail, by breaking or slippage during stressing, may be rejected.

Cut post-tensioning steel with an abrasive saw within 1 to 2 inches from the anchoring device. Do not flame cut prestressing steel.

Provide a record of the post-tensioning operation to the Engineer following each tendon installation including the following:

a.	Project name and bridge number;

b.	Contractor and / or subcontractor name;

c.	Tendon location, size, type;

d.	Date and time tendon was first installed in the duct;

e.	Reel number for strands;

f.	Tendon cross-sectional area;

g.	Modulus of elasticity;

h.	Date and time tendon was stressed;

i.	Jack and gage numbers per end of tendon;

j.	Required jacking force;

k.	Gauge pressure;

l.	Elongation (anticipated and actual);

m.	Anchor set; (anticipated and actual);

n.	Stressing sequence (i.e. tendons stressed before and after);

o.	Stressing mode (one end/ two ends/ simultaneous);

p.	Witnesses to stressing operation (signature); and

q.	Date grouted.

502-3.03 TOLERANCES. Produce prestressed concrete members conforming to the following dimensional tolerances:

1.	Position of Strands: ±1/4 inch (±1/2 inch where harped strands exit the member).

2.	Longitudinal Position of Deflection Point for Harped Strands: ±12 inches.

3.	Position of Ducts and Anchorages: ±1/4 inch

4.	Position of Local Zone Reinforcement: Center reinforcement on the duct and start within 1/2 inch of the back of the bearing plate.

502-3.04 BONDING AND GROUTING. Conform to the following:

1.	General. Bond post-tensioned prestressing steel to the concrete by completely filling the entire void space between the duct and the tendon with grout. Grout tendons according to the procedures set forth in the grouting operation plan. Grout empty ducts.

2.	Personnel Qualifications. Carry out grouting operations by workers trained for and experienced in the tasks required. Perform grouting under the immediate control of the post-tensioning technician as described in Subsection 502-3.02.

3.	Grouting Operation Plan. Submit a grouting operation plan to the Engineer prior to the initiation of production grouting. Devise the grouting procedures to ensure the ducts will be completely filled by grout. Include the following items in the grouting operation plan:

a.	Type, quantity, and brand of materials used in the grouting including material certifications;

b.	Type of equipment furnished, including capacity in relation to demand and working condition, as well as back-up equipment and spare parts;

c.	Types and locations of vents;

d.	Types and sizes of grout hoses and connections;

e.	Theoretical grout volume calculations;

f.	General grouting procedure;

g.	Duct cleaning method prior to grouting;

h.	Mixing and pumping procedures;

i.	Type and frequency of quality control production tests;

j.	Direction of grouting;

k.	Sequence of use of the vents;

l.	Method to be used to control the rate of flow and pressure within the ducts;

m.	Procedures for handling blockages, including flushing of ducts;

n.	Procedures for possible post grouting repair; and

o.	Names of the persons in charge and the other personnel who will perform the grouting operation, including their relevant certification, experience, and skill.

Do not commence production grouting until the Engineer reviews the grouting operation plan.

Before initiation of production grouting, conduct a joint meeting with the grouting technician, subcontractors, grouting crew, and the Engineer to discuss the grouting operation plan, required testing, corrective procedures, and other relevant issues.

4.	Grout Storage. Protect grout materials from dampness.

Limit on site storage of grout to a maximum period of one month.

5.	Grout Production Tests. Provide process control testing during grouting operations. Perform the following grout production tests:

a.	Grout Strength Test. Prepare grout cube specimens according to ASTM C 942. Perform a minimum of one strength test per day during grouting operations. Submit strength test results to the Engineer within 24 hours of test completion.

b.	Fluidity test. Perform the modified version of ASTM C 939 as specified in Subsection 701-2.08. Repeat testing at least every two hours of grouting operations. Submit fluidity test results to the Engineer within 24 hours of test completion.

6.	Field Trial Test. Conduct field trial tests at least seven days prior to initiation of production grouting to demonstrate to the Engineer the grouting equipment, methods, and procedures. Perform batching and testing with the same materials, personnel, and equipment used in production grouting.

7.	Preparation of Enclosures. If a corrosion inhibitor is used, remove the corrosion inhibitor from the ducts prior to grouting. A solution of quick lime (calcium oxide) or slaked lime (calcium hydroxide) in the amount of 0.1 lbs/gal may be used to flush the corrosion inhibitor from the duct provided the flush water is completely removed from the duct.

Remove water and debris blockages that may interfere with the injection of grout.

Inspect valves to be sure that they can be opened and closed properly. Check that the grout hose connections and inlets are free of dirt.

8.	Equipment. Provide grouting equipment with sufficient capacity to ensure that the post-tensioning ducts to be grouted can be filled and vented without interruption in less than 20 minutes.

Provide the following equipment:

a.	Mixing Equipment. Provide a high speed shear colloidal mixer capable of continuous mechanical mixing producing a homogeneous and stable grout free of lumps and un-dispersed cement. Use only colloidal grout machinery that has separate charging and storage tanks. Equip the charging tank with a high shear colloidal mixer and fit the storage tank with an agitator to keep the grout moving continuously before it is pumped into the duct. Use grouting equipment with a gravity feed to the pump inlet from the storage tank.

Include a screen having clear openings of 1/8 inch maximum size to screen the grout prior to its introduction into the grout pump or storage hopper. Locate the screen between the charging tank and the storage tank so that the screen is easily accessible for inspection and cleaning.

Add water by use of a calibrated flow meter or calibrated water reservoir with a measuring accuracy equal to one percent of the total water volume. Where water is not supplied through the public water supply system, provide a water storage tank of sufficient capacity.

b.	Grout Injecting Equipment. Provide pumping equipment capable of continuous operation with little variation of pressure and that includes a system for circulating the grout when actual grouting is not in progress.

Use positive displacement type grout pumps that provide a continuous flow of grout and will be able to maintain a discharge pressure of at least 145 psi. Ensure pumps are constructed to have seals adequate to prevent oil, air or other foreign substances entering the grout and to prevent loss of grout or water.

Use equipment capable of maintaining pressure on completely grouted ducts and fitted with a valve that can be closed off without loss of pressure in the duct.

Install a pressure gauge having a full-scale reading of no more than 290 psi at the duct inlet. If hoses in excess of 100 feet total length are used, place and use two gauges, one at the pump and one at the inlet.

Use grout hoses with sufficient diameter, rated pressure capacity and that are compatible with the pump output. Install a sampling tee with stopcock that minimizes the number of bends, valves, and changes in diameter. Firmly connect grout hoses to pump outlets, pipes, and duct inlets.

Do not use compressed air to aid the pumping of grout.

c.	Air Compression. Provide equipment to supply oil-free and water-free compressed air to blow out excess water and to check the free passage of the ducts.

d.	Flushing Equipment. Provide standby flushing equipment using a potable water supply to facilitate complete removal of grout from the duct if difficult grouting conditions exist. This equipment is in addition to the grouting equipment. Utilize a different power source than the grouting equipment. Furnish equipment that is capable of delivering a pressure of at least 290 psi to flush out partially grouted enclosures.

e.	Vacuum Grouting Equipment. Provide vacuum grouting equipment (volumetric measuring type) to repair voids found after the grouting operations are complete. Use volumetric measuring type vacuum grouting equipment with the ability to measure a void and supply a measured volume of grout to fill the void.

f.	Standby Equipment. During grouting operations, provide a standby grout mixer and pump.

9.	Mixing of Grout. Mix grout using the entire contents of each bag in accordance with the manufacturer’s recommendations and using a metered amount of water. Mix the materials thoroughly to produce a homogeneous grout without excessive temperature increase or loss of properties. Do not mix grout longer than the manufacturer’s recommended duration. Continuously agitate the grout until grouting is complete.

Check the fluidity of the grout in accordance with Subsection 701-2.08. Do not commence grout pumping until fluidity requirements are satisfied.

Do not add water to increase fluidity that has decreased by delayed use of the grout.

Prevent air from being drawn into the post-tensioning duct by keeping the holding tank agitated and at least 1/4 full during the pumping operation.

Periodically inspect the screen during grouting operations. Do not use grout if lumps of cement remain on the screen.

10.	Injection of Grout. Use a method of injecting grout that will ensure complete filling of the ducts and complete encasement of the prestressing steel.

Open grout vents before commencing grouting operations, unless otherwise approved by the Engineer.

Perform grouting in one operation, maintaining a continuous, one-way flow of grout. Grout tendons from the lowest vent in an uphill direction. Unless approved otherwise by the Engineer, pump grout at a rate of 15 feet to 50 feet of duct per minute to avoid air entrapment, segregation of the grout, and to ensure complete filling of the duct. Conduct normal grouting operations at a pressure range of 10 psi to 75 psi measured at the grout inlet. Do not exceed the maximum pumping pressure of 145 psi at the grout inlet.

Pump grout through the duct and continuously discharge grout from the first and subsequent outlets until residual water and entrapped air have been removed and until the consistency of the grout is equivalent to that of the grout being pumped into the inlet. Discharge at least 1/2 gallon of grout from each outlet prior to closing the vent. For outlet vents at intermediate crests, close the outlet vent placed a short distance downstream of the crest before closing their associated high point vent. Close the anchorage outlet vent and allow grout to discharge from the grout cap before closing the grout cap outlet.

After the outlets have been bled and sealed, bleed the grout pressure to 5 psi and wait a minimum of ten minutes for entrapped air to flow to the high points. After ten minutes, increase the pressure as needed and discharge grout at each high point outlet to eliminate entrapped air or water. Complete the process by locking a pressure of 30 psi into the tendon prior to closing the inlet vent.

If the actual grouting pressure exceeds the maximum allowed, close the inlet vent and pump grout at the next outlet, which has just been or is ready to be closed, as long as one-way flow is maintained. Do not pump grout into a succeeding outlet vent from which grout has not yet flowed. Equip the new inlet vent with a positive shut-off and pressure gage.

11.	Temperature Considerations. Do not grout if the ambient air temperature exceeds 100°F. Do not grout if the ambient air temperature is expected to be less than 40°F within 48 hours. Ensure grout temperature upon mixing is between 50°F and 90°F.

If the ambient air temperature is below 32°F, keep ducts free of water to avoid damage due to freezing. Do not warm ducts with steam. Blow dry air (60% humidity or less) through the ducts to extract trapped water. Ensure ducts are free of frost and ice before commencing grouting operations.

12.	Post-Grouting Inspection. Do not remove or open vents until the grout has cured for at least 24 hours. After the grout has cured, remove outlets and grout caps located at anchorages and high points along the tendon to facilitate inspection. If voids are suspected or if duct grouting operations were prematurely terminated prior to completely filling the duct, explore the voided area inside the duct with an endoscope, borescope, videoscope, or other visual means. Do not probe the duct. Determine the location and extent of voided areas.

Depending on the location of the void, drilling may be required to penetrate the inner surface of the anchorage or duct. Use drilling equipment that will automatically shut-off when steel is encountered.

13.	Repairing and Filling Voids. Repair and fill voids that occur in the ducts after the grouting operation is complete. If voids are found, submit a grouting repair plan describing the location and extent of the void and the method of repairing and filling the void to the Engineer for review. If the extent and location of the void is such that complete filling of the void is not possible using the grout injection equipment, repair and fill the void using a volumetric measuring vacuum grouting process utilizing the vacuum grouting equipment specified in Subsection 502-3.04.8.e.

14.	Finishing. Remove valves, caps and pipes for each vent to a depth at least 1 inch below the surface of the concrete. Fill the void left by the vent pipe according to Subsection 501-307.1. Do not remove or open vents until the grout as set for at least 24 hours.

15.	Protection of End Anchorages. Within seven days upon completion of the grouting, place the concrete pour-backs.

Clean and roughen the mating concrete surfaces to remove laitance and to expose small aggregate before casting the concrete pour-backs. Ensure surfaces are clean, sound and without standing water.

Ensure the prestressing steel and the anchoring assemblies are at least 3 inches inside of the end surface of the member, unless otherwise specified in the Contract documents or shown on the approved shop drawings. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Fill the recess with concrete and finish the concrete surface to true lines according to the Contract requirements.

16. 	Record of Grouting Operation. Submit a written report to the Engineer within 72 hours after grouting. Include in this report:

a.	the date of grouting;

b.	the number of days from tensioning to grouting;

c.	the tendons grouted;

d.	the quantities and types of materials used;

e.	the volume of grout pumped into the duct

f.	a summary of problems encountered during grouting and steps taken to resolve them;

g.	the maximum pumping pressure at the inlet;

h.	the temperature measurement of the air, water, prepackaged material, mix grout, and concrete member in the duct.

i.	the results of quality control testing.

502-4.01 METHOD OF MEASUREMENT. Section 109.

502-5.01 BASIS OF PAYMENT. The lump sum payment is full compensation for furnishing, installing, stressing, grouting, repairing, and inspecting post-tensioned tendons accepted in place.

Items of the post-tensioning system embedded within the concrete including but not limited to prestressing steel, enclosures for prestressing steel, wedges, wedge plates, anchorage assemblies and associated supplemental reinforcing steel required by the supplier, grout vents, and grout gaps are included in the Contract price paid for the post-tensioned concrete structural members.

Post-tensioning system hardware that is not embedded in concrete including but not limited to jacks, gauges, wire socks, and torpedoes are included in the Contract price paid for the post-tensioned concrete structural members.

Items and equipment to fill the ducts with grout including but not limited to mixers, gauges, flushing equipment, and production tests are included in the Contract price paid for the post-tensioned concrete structural members.

Materials for protecting the post-tensioning steel and anchorages including but not limited to corrosion inhibitors, flushing equipment, concrete bonding agents, and equipment to prepare the concrete block-outs are included in the Contract price paid for the post-tensioned concrete structural members.

Labor, materials, tools, equipment and incidentals necessary for completing the work are included in the Contract price paid for the post-tensioned concrete structural members.

Payment for prestressing precast concrete members is included in the Contract price paid for the precast members, as provided for in Section 501.

Replace Section 503 with the following:

SECTION 503

REINFORCING STEEL

503-1.01 DESCRIPTION. Furnish and place reinforcing steel for reinforced concrete structures.

503-1.02 DEFINITIONS.

BAR SIZE / DIAMETER. Nominal dimensions equivalent to those of a circular area having the same weight per foot as the AASHTO/ASTM designated bar.

COVER. The minimum distance between the surface of embedded reinforcing steel and the outer surface of the concrete.

HOOK. A bend in the end of a bar.

HOOP. A one-piece closed tie or continuously wound tie, with hooked or welded ends, enclosing the longitudinal reinforcing steel.

LATERAL REINFORCING STEEL. Reinforcing steel perpendicular to the length of a concrete member.

LONGITUDINAL REINFORCING STEEL. Reinforcing steel parallel to the length of a concrete member.

LOT. A defined quantity.

SPIRAL. Continuously wound reinforcing steel in the form of a cylindrical helix.

STIRRUP. Lateral reinforcing steel formed of individual or paired units, open or closed, used to resist shear and diagonal tension stresses in a structural member.

TIE. Reinforcing steel with hooked ends tied at right angles to and enclosing the other reinforcing steel, and used to provide confinement.

503-2.01 MATERIALS.

Reinforcing Steel Bars	Subsection 709-2.01

Epoxy-Coated Reinforcing Steel Bars	Subsection 709-2.01

Headed Reinforcing Steel Bars	Subsection 709-2.01

Epoxy Coating Patch Material	Subsection 709-2.01

Bar Supports	Subsection 709-2.03

Epoxy for Bonding Dowels	Subsection 712-2.21

CONSTRUCTION REQUIREMENTS

503-3.01 PLACING DRAWINGS. Submit placing drawings, detailed according to ACI 315, Chapter 3, to the Engineer.

Do not substitute reinforcing steel bars of different size, material, coating, or grade without prior approval of the Engineer. When substituting epoxy-coated reinforcing steel for uncoated reinforcing steel, protect and repair epoxy-coated bars according to Subsection 503-3.02.

503-3.02 PROTECTION OF MATERIALS. Protect reinforcing steel from damage. Before placing reinforcing steel in the work, ensure that the reinforcing steel is free of salt and foreign substances that may affect the performance of the reinforcing steel.

Do not weld or tack weld reinforcing steel, unless otherwise noted.

Do not drop or drag the epoxy-coated reinforcing steel bars or bundles.

Store epoxy-coated reinforcing steel off the ground.

Protect epoxy-coated reinforcing steel from sunlight, salt spray, and weather exposure. The Engineer may reject epoxy-coated reinforcing steel when the cumulative environmental exposure time, including uncovered storage time after coating application to full embedment in concrete, exceeds 2 months.

The Engineer may reject epoxy-coated reinforcing steel when the extent of damaged coating exceeds 2 percent of the surface area in any 1-foot length of bar. When the extent of damaged coating does not exceed 2 percent of the surface area in any 1-foot length of bar, repair damaged coating. Coating damage includes cracks, abrasions, chips, bond loss (the coating can be removed with a peeling action by the finger), and exposed steel areas visible to a person with normal or corrected vision. Repair coating damage before visible oxidation appears on the steel surface.

Protect mechanical splice assemblies, headed bar assemblies, and connecting elements (including bar ends) against physical damage, corrosion, and coating damage. Keep assemblies and connecting elements clean and free of foreign materials that adversely affect the performance of the assembly.

1.	Repairing Damaged Epoxy-Coating. Clean and remove disbonded areas of coating. Remove loose and deleterious materials. The Engineer may reject epoxy-coated reinforcing steel when the removed coating exceeds 2 percent in any 1-foot length of bar or if the weight, dimensions, cross-sectional area, or tensile properties are less than the minimum requirements of the applicable specification.

Use an approved epoxy coating patch material according to the material manufacturer's recommendations. Apply patching material according to the patching material manufacturer's instructions. Allow the patching material to cure before placing concrete. The Engineer may reject epoxy-coated reinforcing steel when the surface area covered by patching material exceeds 5 percent in any 1-foot length of bar.

Rejected epoxy-coated reinforcing steel may not be substituted for uncoated reinforcing steel or used as bar supports.

503-3.03 FABRICATION. Fabricate reinforcing steel to the size and dimension shown on the Plans. Reinforcing steel dimensions shown are out-to-out of bar, unless otherwise noted.

Meet fabrication tolerances in ACI 117, Section 2.1.

Weld reinforcing steel according to AWS D1.4.

1.	Bends. Bend bars when the bar temperature is above 45°F and less than 150°F. Bend bars to the diameter shown on the Plans. If the bend diameter is not shown, bend the bar with inside diameters as shown in Table 503-1. The Engineer may reject reinforcing steel bent with an inside diameter less than the minimum diameter shown in Table 503-1.

Do not re-bend or straighten bars without approval by the Engineer.

TABLE 503-1

BEND DIAMETER

| BAR SIZE | Stirrups and ties | STANDARD HOOKS AND OTHER BENDS |
| --- | --- | --- |
| No. 3 | 1½" | 2¼" |
| No. 4 | 2" | 3" |
| No. 5 | 2½" | 3¾" |
| No. 6 | 4½" | 4½" |
| No. 7 | 5¼" | 5¼" |
| No. 8 | 6" | 6" |
| No. 9 | - | 9½" |
| No. 10 | - | 10¾" |
| No. 11 | - | 12" |
| No. 14 | - | 18¼" |
| No. 18 | - | 24" |

Fabricate bar end hooks meeting the following requirements:

a.	Stirrup and Tie Hooks.

(1)	90° Hook: 90° bend plus:

(a)	For No. 5 bar and smaller, a 6.0 nominal bar diameter extension at the free end of the bar.

(b)	For No 6, No. 7, and No. 8 bars, a 12.0 nominal bar diameter extension at the free end of the bar.

(2)	135° Hook: 135° bend plus a 6.0 nominal bar diameter extension, but not less than 2.5 inches, at the free end of the bar.

b.	Standard Hooks.

(1).	Std 180° Hook: 180° bend plus a 4.0 nominal bar diameter extension, but not less than 2.5 inches, at the free end of the bar.

(2).	Std 90° Hook: 90° bend plus a 12.0 nominal bar diameter extension at the free end of the bar.

2.	Bar Repairs. The Engineer will evaluate improperly bent bars and bars bent at locations not required by the Plans for structural adequacy and durability. Do not repair improperly bent bars until the bars are inspected by the Engineer and the Engineer approves repairing the bar. Bars repaired prior to inspection by the Engineer may be rejected. If, in the opinion of the Engineer, the bend is of such extent or character as to affect the strength or durability of the bar, the Engineer may reject the bar. Otherwise, the bar may be re-bent or straightened by means meeting the requirements of this Section and in a manner that will not damage the material, coating, or concrete.

If the Engineer approves repairing the bar, preheat the reinforcing steel before bending. Apply heat by any method that does not damage the reinforcing steel or concrete. Preheat the reinforcing steel at least 5.0 nominal bar diameters in each direction from the center of the bend but do not extend preheating below the surface of the concrete. Insulate concrete within 6 inches of the heated bar area. Do not allow the temperature of the reinforcing steel at the concrete interface to exceed 500°F. Preheat the reinforcing steel to at least 1100°F. Ensure the maximum reinforcing steel temperature never exceeds 1200°F. Maintain a uniform temperature throughout the thickness of the bar by using at least 2 heat tips simultaneously at opposite sides of bars larger than No. 6. Maintain the preheat temperature of the reinforcing steel until bending or straightening is complete. Make the bend gradually with smooth continuous application of force. When straightening, move a bender progressively around the bend. When bending or straightening is complete, gradually reduce the temperature of the reinforcing steel to the ambient air temperature. Do not artificially cool the bars with water, forced air, or any other means.

503-3.04 PLACING AND FASTENING. Place reinforcing steel in the position as shown on the Plans.  Secure the reinforcing steel to prevent movement during concrete placement. Do not place bars in addition to those shown on the Plans without prior approval of the Engineer. Do not place bars of different size, material, or grade without prior approval of the Engineer. Space reinforcing steel evenly unless noted otherwise. Provide 2 inches of concrete clear cover, measured from the surface of the reinforcing steel to the outside surface of the concrete, unless noted otherwise.

Do not place bars on layers of fresh concrete or adjust bars while placing concrete.

1.	Fastening Requirements. Tie the bars with No. 14 or No.16 gauge steel wire. When the spacing between bars is 1 foot or more, tie the bars at all intersections. When the bar spacing is less than 1 foot, tie every other intersection. If the Plans require bundled bars, tie bundled bars together at not more than 6-foot centers. Tie all intersections of epoxy-coated reinforcing steel in the top mat of concrete decks and approach slabs. Use wire coated with plastic, epoxy, or similar non-conductive material when tying epoxy-coated reinforcing steel. Obtain the Engineer’s written authorization before welding reinforcing steel. Provide at least 1 inch clear cover to the tie wire by turning the tie wire away from concrete surfaces.

For slip-formed concrete, tie reinforcing steel at all intersections. Provide additional reinforcing steel cross bracing to keep the cage form moving during concrete placement. Place cross bracing both longitudinally and transversely.

2.	Bar Supports. Maintain distances from the forms using approved precast mortar blocks, metal supports, or plastic supports strong enough to resist permanent movement under construction loads. If supports extend to exposed concrete surfaces, use metal or plastic supports. To support and fasten epoxy-coated reinforcing steel, use plastic supports or metal supports coated with plastic, epoxy, or similar non-conductive material. Do not use wooden or aluminum supports.

Place supports at frequent intervals to maintain the cover between the reinforcing and the surface of the concrete. Space supports under concrete deck reinforcing steel and approach slab reinforcing steel not more than 4 feet apart in each direction.

503-3.05 SPLICING. Splice reinforcing steel bars at locations shown on the Plans and specified in this Section. Obtain the written approval of the Engineer before splicing bars at other locations. The Engineer will evaluate splices at locations not designated in the Contract documents for structural adequacy.

Splice reinforcing steel bars using lap splicing, welded butt joints, welded lap splicing, mechanical butt splicing, or mechanical lap splicing, unless noted otherwise. Do not splice reinforcing steel bars at locations where splices in the reinforcing steel are not allowed.

Splices will not be permitted in bars 40 feet or less in plan length, unless otherwise noted in the Contract documents. For bars exceeding 40 feet in plan length, ensure the distance center-to-center of splices is not less than 30 feet, with no individual bar length less than 10 feet. Stagger splices in adjacent bars, unless otherwise noted. Stagger lap splices a distance greater than the lapped splice length. Stagger butt splices at least 2 feet.

Reinforcing steel may be continuous at locations where splices are noted in the Contract documents.

Do not use lap splicing for No. 14 or No. 18 bars.

Do not lap splice spiral reinforcing steel. Anchor each end unit of reinforcing steel spiral by lapping the free end of the spiral to the continuous spiral and using either a welded lap splice or a mechanical lap splice.

Do not field weld epoxy-coated reinforcing steel bars.

1.	Lap Splicing.

a.	General. Place reinforcing steel bars in contact and securely tie the bars together. Provide a minimum clear distance of 2 inches between the spliced bars and the nearest adjacent bar. Do not reduce the minimum clearance to the surface of the concrete.

Use lapped splices meeting the minimum lengths as shown in Table 503-2, unless otherwise noted:

TABLE 503-2
LAPPED SPLICE LENGTH

| BAR SIZE | UnCOATED | EPOXY-COATED |
| --- | --- | --- |
| No. 3 | 1' - 4" | 1'- 11" |
| No. 4 | 1' - 9" | 2' - 7" |
| No. 5 | 2' - 2" | 3' - 3" |
| No. 6 | 2' - 7" | 3' - 10" |
| No. 7 | 3' - 5" | 5' - 2" |
| No. 8 | 4' - 6" | 6' - 9" |
| No. 9 | 5' - 9" | 8' - 7" |
| No. 10 | 7' - 3" | 10' - 10" |
| No. 11 | 8' - 11" | 13' - 4" |

b.	Qualifications and Submittals. No qualifications apply when lap splicing.

c.	Testing/Inspection. Field verify lap splice length.

2.	Welded Butt Joints.

a.	General. Use complete joint penetration (CJP) groove welds conforming to the requirements in AWS D1.4 except as noted below.

Use the joint details and dimensions as shown in Figure 3.2 (A) (B) (D) and (E), "Direct Butt Joints" of AWS D1.4. Do not use split pipe backing.

Do not deviate the bar alignment at a welded splice more than 1/8 inch per 10-foot length.

Use electrodes classified as "Nickel-Steel" as referenced in AWS A5.5, A5.28, or A5.29.

Protect welding areas from precipitation and wind velocities in excess of 5 mph.

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract documents to the reinforcing steel, unless shown on the working drawings and approved by the Engineer.

b.	Qualifications and Submittals. Perform welds using qualified welders and qualified Welding Procedure Specifications (WPS) meeting AWS D1.4. The operator and procedure qualification tests may be performed simultaneously.

Perform quality control inspection necessary to ensure the materials and workmanship meets the requirements of the Contract documents using an inspector currently certified as an AWS Certified Welding Inspector (CWI) according to the provisions of AWS QC1.

Perform nondestructive testing other than visual testing as required in the Contract documents using personnel currently qualified for NDT Level II or NDT Level I working directly under the NDT Level II according to the provisions of the American Society for Nondestructive Testing's Recommended Practice No. SNT-TC-1A.

Submit a welding plan stamped and signed by the CWI responsible for quality control and consisting of the following documents:

(1)	Quality control inspector qualifications including CWI number.

(2)	Welding Procedure Specifications (WPS).

(3)	Procedure Qualification Records (PQR) and test results.

(4)	Welder Performance Qualification Records (WPQR) with documentation of current welder certification.

(5)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications.

(6)	Nondestructive testing personnel qualifications.

(7)	Methods of protecting the welding area.

(8)	Certified test report(s).

Submit quality control inspection documents and test results to the Engineer.

c.	Testing/Inspection.

(1)	Shop Welds. Perform job control tests consisting of the fabrication, under conditions used to produce the splice, and tensile testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of shop produced complete joint penetration welded butt joints is defined as no more than 150 splices of the same type of welds used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 48 hours prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to ASTM A 370, including Appendix A9. Tensile test each sample until partial or total fracture of the parent bar material or weld occurs.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when both of the following conditions are met:

(a)	The average tensile strength of the sampled splices is not less than 80000 psi, based on the nominal bar area.

(b)	The individual tensile strength of at least 5 sample splices have a minimum tensile strength of at least 80000 psi, based on the nominal bar area.

(2)	Field Welds. Perform radiographic testing on a random sample, selected by the Engineer, of at least 25 percent of the total number of direct butt joint welds.

Perform tests in the presence of the Engineer. Welds tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 48 hours prior to performing radiographic testing.

Perform nondestructive examination using radiographic testing according to AWS D1.4.

Make 2 exposures for each complete joint penetration direct butt joint. For each of the exposures, center the radiation source on each bar to be radiographed. Make the first exposure with the radiation source placed at zero degrees from the top of the weld and perpendicular to the weld root and identify with a station mark of "0". Make the second exposure at 90 degrees to the "0" station mark and identify with a station mark of "90".

Clearly identify each direct butt joint on each radiograph. Establish the radiograph identification and marking system with the Engineer before radiographic inspection begins. Identify film using lead numbers and letters. Do not use etching, flashing or writing to identify film. Legibly mark each piece of film with identification information including, as a minimum, the following information:

(a)	Contractor's name

(b)	Date

(c)	Name of nondestructive testing firm

(d)	Initials of radiographer

(e)	Weld number

Identify a repaired weld by placing the letter "R" followed by the weld repair number on the radiographic film using lead numbers and letters.

Record the results of radiographic interpretations on a signed certification. Keep a copy of the certification with the film packet.

If more than 10 percent of the tested welds do not meet AWS D1.4, test a second random sample from untested welds, selected by the Engineer, of at least 25 percent of the total number of welds. If more than 10 percent of the tested welds in the second sample do not meet AWS D1.4, perform radiographic testing on remaining untested welds.

Repair weld defects according to the requirements of AWS D1.4.

3.	Welded Lap Splicing.

a.	General. Use direct lap joint welds conforming to the requirements in AWS D1.4 except as noted below.

Use the joint details and dimensions as shown in Figure 3.4 (A), "Direct Lap Joint with Bars in Contact" of AWS D1.4.

Use electrodes classified as "Nickel-Steel" as referenced in AWS A5.5, A5.28, or A5.29.

b.	Qualifications and Submittals. Perform welds using qualified welders and qualified Welding Procedure Specifications (WPS) meeting AWS D1.4. The operator and procedure qualification tests may be performed simultaneously.

Perform quality control inspection necessary to ensure the materials and workmanship meets the requirements of the Contract documents using an inspector currently certified as an AWS Certified Welding Inspector (CWI) according to the provisions of AWS QC1.

Submit a welding plan stamped and signed by the CWI responsible for quality control and consisting of the following documents:

(1)	Quality control inspector qualifications including CWI number.

(2)	Welding Procedure Specifications (WPS).

(3)	Procedure Qualification Records (PQR) and test results.

(4)	Welder Performance Qualification Records (WPQR) with documentation of current welder certification.

(5)	Type and extent of Nondestructive Examination (NDE) to be conducted, as required in the specifications.

(6)	Nondestructive testing personnel qualifications.

(7)	Methods of protecting the welding area.

(8)	Certified test report(s).

Submit quality control inspection documents, test results, and required test assemblies to the Engineer.

c.	Testing/Inspection. Perform inspection according to AWS D1.4.

4.	Mechanical Butt Splices.

a.	Types. Use one of the following types of mechanical butt splices:

(1)	Sleeve-Threaded Mechanical Butt Splices. Use a sleeve-threaded mechanical butt splice consisting of a steel splice sleeve with tapered interior threads that joins the bars with matching tapered threads.

(2)	Sleeve-Swaged Mechanical Butt Splices. Use a sleeve-swaged mechanical butt splice consisting of a seamless steel sleeve applied over the ends of the reinforcing steel bars and swaged to the bars by means of a hydraulic press.

(3)	Sleeve-Lock Shear Bolt Mechanical Butt Splices. Use a sleeve-lock shear bolt mechanical butt splice consisting of a seamless steel sleeve with serrated steel strips welded to the inside of the sleeve, center hole with centering pin, and bolts tightened until the bolt heads shear off and the bolt ends are embedded in the reinforcing steel bars.

(4)	Two-Part Sleeve-Forged Ends Mechanical Butt Splices. The two-part sleeve-forged ends bar type of mechanical butt splices consists of a shop machined two-part threaded steel sleeve coupling forged ends of the reinforcing steel bar.

b.	General. Conform to the manufacturer's instructions when splicing.

Cut the reinforcing steel bars perpendicular to the long axis of the bar.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcing steel if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices.

Mark each splice with the lot, heat, or batch number that identifies the splice.

c.	Qualifications and Submittals. A splice will be considered qualified if the splice can develop a minimum tensile strength of 80000 psi, based on the nominal bar area, and the bars within the splice do not exceed a total slip, after loading in tension to 29000 psi and relaxing to 2900 psi, of 10 mils for bars smaller than a No. 18 bar or 30 mils for No. 18 bar when tested according to ASTM A 370, including Appendix A9.

Submit the following information:

(1)	the manufacturer's name;

(2)	the name of the product or assembly;

(2)	the lot, heat, or batch number that identifies the splice;

(3)	the bar grade and size number to be spliced by the material;

(4)	a complete description of the splice and installation procedure; and,

(5)	test results indicating the splice, used according to the manufacturer's procedures, complies with the minimum tensile strength requirements and the total slip requirements.

d.	Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice, and tensile testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 48 hours prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to ASTM A 370, including Appendix A9. Tensile test each sample until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when the minimum individual tensile strength of the sampled splices is not less than 80000 psi, based on the nominal bar area.

5.	Mechanical Lap Splices.

a.	General. Conform to the manufacturer's instructions when splicing.

Provide a clear cover of not less than 1-1/2 inches measured from the surface of the concrete to the outside of the splice sleeve. Adjust stirrups, ties and other reinforcing steel if necessary to provide clear cover.

For epoxy-coated bars, use epoxy-coated mechanical splices.

Mark each splice with the lot, heat, or batch number that identifies the splice.

b.	Qualifications. A splice will be considered qualified if the splice can develop a minimum tensile strength of 75000 psi, based on the nominal bar area, when tested according to ASTM A 370, including Appendix A9.

Submit the following information:

(1)	the manufacturer's name;

(2)	the name of the product or assembly;

(2)	the lot, heat, or batch number that identifies the splice;

(3)	the bar grade and size number to be spliced by the material;

(4)	a complete description of the splice and installation procedure; and,

(5)	test results indicating the splice, used according to the manufacturer's procedures, complies with the minimum tensile strength requirements.

c.	Testing/Inspection. Perform job control tests consisting of the fabrication, under conditions used to produce the splice, and tensile testing of 6 sample splices for each lot of splices. The Engineer will designate when samples for job control tests are to be fabricated and will determine the limits of the lot represented by each job control test.

A lot of mechanical butt joints is defined as no more than 150 splices of the same type of mechanical butt splice used for each combination of bar size and bar deformation pattern that is used in the work.

Make splice samples using the same splice materials, position, equipment, and following the same procedures as used to make splices in the work. Make splice samples at least 5 feet long with the splice at mid-length. Shorter sample splice bars may be used if approved by the Engineer.

Perform job control tests in the presence of the Engineer. Splices tested in the absence of the Engineer may be rejected. Notify the Engineer, in writing, at least 48 hours prior to performing testing.

Identify sample splices with weatherproof markings prior to shipment to the testing laboratory.

Test each sample according to ASTM A 370, including Appendix A9. Tensile test each sample until partial or total fracture of the parent bar material, mechanical splice material, or bar-to-splice connection.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when the minimum individual tensile strength of the sampled splices is not less than 75000 psi, based on the nominal bar area.

503-3.06 HEADED BAR REINFORCING STEEL. Use Headed bar reinforcing steel consisting of deformed reinforcing steel bars with a head attached to one or both ends. Attachment can be accomplished through welding or forging of heads onto the bar ends, by internal threads in the head mating to threads on the bar end or by a separate threaded nut to secure the head to the bar. Heads may be forge formed, machined from bar stock, or cut from plate.

Perform production control tests consisting of the installation, using the same procedure as used in the work, and tensile testing of 3 sample splices for each lot of heads.

A production lot of headed bar reinforcing steel is defined as no more than 150 splices of the same bar size, with heads of the same size and type, and manufactured by the same method, produced from bar material of a single heat number and head material of a single heat number. For bars having heads on both ends, the bar will be counted as 2 reinforcing steel bars for the purposes of establishing and testing production lots.

Test each sample according to ASTM A 970.

All splices in the lot represented by a test will be considered to meet the tensile strength requirements when the minimum individual tensile strength of the sampled splices meets the tensile strength requirements of ASTM A 970.

503-3.07 DRILLING AND BONDING DOWELS. Install dowels at locations shown on the Plans or as authorized by the Engineer. Drill holes by methods that do not shatter or damage the concrete adjacent to the holes. Do not damage reinforcing steel or prestressing steel when drilling through reinforced concrete members, unless approved by the Engineer. The Engineer will evaluate holes in which reinforcing steel or prestressing steel is encountered during drilling for structural adequacy and durability.

Drill each hole to the diameter and depth recommended by the manufacturer to develop the ultimate strength of the dowel or to the depth shown on the Plans, whichever is greater.

Prepare each hole according to the manufacturer’s instructions before placing the epoxy and the dowels. Fill the hole with epoxy and install the dowel according to the manufacturer's instructions. Completely fill drilled holes with epoxy using a method that will not trap air or create voids. Support dowels and prevent movement during curing. Do not disturb the dowels until the epoxy has cured.

Do not use dowels made from epoxy-coated reinforcing steel.

503-3.08 PLACEMENT TOLERANCES. When placing reinforcing steel, do not reduce the total number of bars specified. Place reinforcing steel within the following tolerances:

1.	Clear Cover: +1/4 inch, -3/8 inch, but not reducing the clear cover to less than 1 inch.

2.	Placement of Reinforcing Steel: ±1/2 inch.

3.	Spacing of Reinforcing Steel: ± One-quarter of the specified spacing, but not to exceed 1 inch.

4.	Spacing for Bundled Reinforcing Steel: 1 inch or 2 times the individual nominal bar diameter between bundles, whichever is greater.

5.	Embedment Length and Length of Lap Splices: -1 inch for No. 3 through No. 11 bars, -2 inches for No. 14 and No. 18 (embedment only).

6.	Location of Bends in Bars and Ends of Bars: ±2 inch.

503-4.01 METHOD OF MEASUREMENT. See Section 109 and the following:

Drill and Bond Dowels. Measured per dowel, complete in place.

503-5.01 BASIS OF PAYMENT.

Reinforcing Steel. Reinforcing steel will be paid for at the Contract lump sum price. The lump sum price is full compensation for furnishing, fabricating, placing, splicing, heading and testing reinforcing steel as indicated in the Contract documents. Increase in weight of reinforcing due to splices, heads, and additional support bars will not be paid for. Materials, equipment and labor required to install reinforcing steel will be paid for under the Contract lump sum price.

Payment for reinforcing steel used in precast concrete members is included in the Contract price for the precast members, as provided in Section 501.

Drill and Bond Dowels. Payment for Drill and Bond Dowels includes materials and work for installing dowels.

Payment for reinforcing steel used in minor structures is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

503(1)	Reinforcing Steel	Lump Sum

503(2)	Epoxy-Coated Reinforcing Steel	Lump Sum

SECTION 504

STEEL STRUCTURES

504-3.01  Fabrication.  Replace the fourth paragraph of numbered Item 8 with the following:

Using a CWI, perform all Quality Control inspection necessary to ensure the materials and workmanship meet the requirements of the contract documents.

504-3.01  Fabrication.  Add the following to numbered Item 8:

Do not weld or tack brackets, clips, shipping devices or other material not required by the Contract Documents to the permanent structure, unless shown on the working drawings and approved by the Engineer.

504-5.01 BASIS OF PAYMENT. Add the following: Welding and fabrication inspection is subsidiary.

Replace Section 505 with the following:

SECTION 505

PILING

505-1.01 DESCRIPTION. Furnish and drive piles, and assist in pile testing.

505-1.02 DEFINITIONS.

CUT-OFF. The cut off end of a pile, or cutting a pile end at the finish elevation.

DRIVECAP. A pile driver component that is used to transmit impact forces from the hammer ram to the pile top. The drivecap includes the anvil or striker plate, hammer cushion (capblock), helmet, and pile cushion, if used. (Also termed the driving head).

DRIVING RESISTANCE. The required axial resistance, in units of force, to be achieved during pile driving.

ESTIMATED PILE TIP ELEVATION. The elevation at which the Department expects the driving resistance to be achieved.

FRESH HEADING. Cutting the end of a pile perpendicular to the long axis to remove damage, and to obtain a proper driving or splicing surface.

FOLLOWER. A pile driving aid placed between the helmet and the pile top when the pile head is below the reach of the hammer.

HAMMER CUSHION. A disk of material placed on top of the helmet but below the anvil or striker plate to relieve impact shock and provide protection for the hammer and pile.

HAMMER ENERGY:

MAXIMUM RATED HAMMER ENERGY. The theoretical maximum amount of gross energy that a pile driving hammer can generate.

TRANSFERRED HAMMER ENERGY. The amount of energy transferred to the pile for a given blow accounting for friction energy during the ram down stroke, energy retained in the ram and drivecap during rebound, and other impact losses.

HELMET. A pile driver component that fits closely on top of the pile to ensure the impact force is transmitted uniformly across the top of the pile and concentric with the axis of the pile.

LEADS. Pile driver components used to maintain pile and hammer alignment during driving, and on which the pile hammer may travel. Types of leads include :

FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and to the crane at the bottom with a brace. The pile is held at the top by the helmet and is guided at the bottom by the pile gate.

SEMI-FIXED LEADS. Pile driving leads that are attached at the top of the boom by a pivot and supported by the lead line. The lead can slide axially along the pivoted boom point and may be fitted with an extendable brace at the bottom of the leads.

SWINGING LEADS. Pile driving leads that are suspended from the boom by the cable and are not attached to the crane at the bottom with a brace. (Also known as offshore leads)

MINIMUM PENETRATION. The minimum length of pile below the footing or finished ground elevation to which the pile must be driven.

OBSTRUCTION. An unanticipated object projecting within the path of the pile that causes pile refusal or impedes the pile's advance within required tolerances.

PILE GATE. A device at the base of the leads that is closed around the pile to maintain alignment.

REFUSAL. Refusal occurs when the hammer requires 15 or more blows to move the pile one inch, and the hammer is operating near the maximum allowable compressive driving stress (within 80-90% of the specified pile yield stress).

SUBSTRUCTURE UNIT. A unit of the substructure such as an abutment or pier that transmits loads directly from the superstructure to the ground.

TEST PILE. A pile that has a high-strain dynamic test performed on it.

TEMPLATE. A structure affixed to the ground used to maintain proper pile alignment during driving.

WAVE EQUATION ANALYSIS. A numerical method of analysis for the behavior of driven piles that predicts the pile capacity versus blow count relationship (bearing graph) and pile driving stress. Wave equation analysis is performed using the wave equation analysis program (WEAP) with a version dated 1987 or later.

505-2.01 MATERIALS. Use materials that conform to the following:

Structural Steel Piles	Section 715

Sand	Subsection 703-2.12

505-2.02 PILES. Furnish piles sufficient in length to obtain the driving resistance and to extend to the estimated pile tip elevation specified in the Contract documents. Furnish full-length piles where practical. Where splices are required, follow the provisions of Subsection 505-3.04. Furnish additional pile length to provide for fresh heading and to suit the method of installation. Use metal shoes or reinforced tips as required. Store and handle piles in a manner that protects them from damage.

1.	Steel Piles. Furnish H-pile sections described in the Contract.

The Engineer will reject steel piles that exceed the camber and sweep permitted by allowable mill tolerance.

CONSTRUCTION REQUIREMENTS

505-3.01 PILE DRIVING EQUIPMENT.

1.	Pile Driving System. Use impact hammers to drive piles and to determine resistance during pile driving. If a vibratory hammer is used, use an impact hammer to determine pile resistance by driving the pile an additional penetration of at least 5 feet. Use pile driver leads that allow the hammer to move freely. Do not use followers to drive piles.

Fit the pile driving hammer with a cast-steel driving head (or similar device) that is recommended in the hammer manufacturer’s guidelines, is compatible with the pile, and aligns concentrically and fits closely with the top of the pile.

If the pile driving hammer is fitted with a hammer cushion, use a cushion that satisfies the recommendation in the hammer manufacturer’s guidelines, is appropriate to prevent damage to the hammer or pile, and ensures uniform driving performance. If not new, ensure the hammer cushion is at least 75 percent of the manufactured thickness. Replace driving hammer cushions with a reduction in cushion thickness exceeding 25 percent of the manufactured thickness. Do not use wood, wire rope, or asbestos hammer cushions.

For piles that will not be exposed in the completed work, use fixed leads, a ground template, or other means to ensure proper placement and alignment of piles.

For piles that will be exposed in the completed work, use fixed leads, a two-tiered template that laterally supports the pile within 5 feet of the finished ground or water elevation and within 5 feet of the cut-off elevation, or other means to ensure proper placement and alignment of piles.

To ensure rigid lateral support to the pile during driving when using fixed leads, hold the leads in position at the top and bottom by using guys, steel braces, or other means of restraint that provide sufficient lateral support to prevent movement of the pile. Do not use semi-fixed leads or swinging leads without other means of providing sufficient lateral support to prevent movement of the pile. Wooden templates are not permitted.

Use only equipment included in the approved pile driving plan. The Engineer will inspect the pile driving equipment for conformance with the approved pile driving plan after it has been mobilized to the site and prior to beginning pile driving operations. Remove and replace pile driving equipment found out of conformance with the approved pile driving plan at no extra cost to the Department and with no adjustment to contract time.

2.	Wave Equation Analysis. Perform a wave equation analysis for all pile driving systems used to drive piling according to the requirements of this subsection and the user’s manual for the program. Verify that the pile driving system proposed does not produce stresses greater than 90-percent of the yield stress. Also verify that the pile driving system does not exceed the refusal criteria at the depth of penetration anticipated for achieving the required driving resistance and minimum penetration. Furthermore, verify that at the driving resistance specified in the Contract, the rate of pile penetration is 100-blows per foot or less.

TABLE 505-1

HAMMER EFFICIENCIES USED IN HAMMER APPROVAL

| Hammer Type | For Analysis of Driving Resistance | For Analysis of Driving Stresses |
| --- | --- | --- |
| Single acting diesel hammers | 0.72 | 0.84 |
| Closed-ended diesel hammers | 0.72 | 0.84 |
| Single acting air/steam hammers | 0.60 | 0.70 |
| Double acting air/steam hammers | 0.45 | 0.53 |
| Hydraulic hammers or other external combustion hammers having ram velocity monitors that may be used to assign an equivalent stroke. | 0.85 | 1.00 |

Unless otherwise specified in the Contract, or directed by the Engineer, use the following default values and the applicable values from Table 1 as input to the wave equation analysis program:

Output option (IOUT)	0

Factor of safety applied to (Rult)	1.0

Type of damping	Smith

Residual stress option	No

3.	Pile Driving Plan. No less than 30 days prior to the anticipated start of pile driving, submit for approval the details of each proposed pile driving system. Include in the pile driving plan:

a.	A completed Pile Driving Equipment Data form (Form 25D-098).

b.	Manufacturer’s catalog cuts, specifications, manuals, guidelines, and technical bulletins for all pile driving equipment to be used.

c.	A description of the techniques to be used for ensuring proper placement and alignment of the piles, obtaining the driving resistance, and advancing the piles to the estimated pile tip elevation.

d.	Alternate methods of pile installation in the event obstructions are encountered.

e.	A wave equation analysis for each pile driving system.

The Engineer will base approval of the pile driving plan on the wave equation analysis submitted by the Contractor, and the requirements in this Subsection. The Department will verify the wave equation analysis using the computer program “GRLWEAP” and GRLWEAP industry standard hammer input data.

Approval by the Engineer of the pile driving plan will not relieve the Contractor of responsibility for piles damaged during pile driving operations. Do not mobilize pile driving equipment to the site without an approved pile driving plan.

Submit all revisions to the approved pile driving plan to the Engineer for approval. For all pile driving equipment not previously identified in the pile driving plan, include in the submittal all of the information required above for the pile driving plan. Explain to the Engineer, in writing, which portions of the approved pile driving plan will be superseded by the revision and which portions remain unchanged. Allow at least 5 days for the Engineer’s approval of pile driving plan revisions.

505-3.02 PILE TESTING AND PILE DRIVING CRITERIA. The Engineer will use one or more of the following to set criteria to monitor pile driving performance and the resistance of the pile during driving. The Engineer will also perform pile testing to confirm hammer-system efficiency, pile driving stresses and pile integrity. Attend a meeting with the Engineer at least 14 days prior to the beginning of pile driving operations to evaluate and discuss the test pile program. Give the Engineer 7 days advance notice before driving each test pile.

1.	Wave Equation Analysis. The Engineer will provide pile driving criteria based on a wave equation analysis. The wave equation analysis computer program to be used will be the "GRLWEAP" program using the GRLWEAP industry standard hammer input data.

2.	High-Strain Dynamic Testing. The Engineer will perform high-strain dynamic testing at locations determined by the Engineer. The Engineer will perform the high-strain dynamic testing in accordance with ASTM D 4945. Piles tested using high-strain dynamic testing may be incorporated into the work.

The Engineer will test the first pile driven at each substructure unit designated for pile testing. Do not drive any production piles, except the test pile, at the substructure unit until the test pile has been driven to the driving resistance and minimum penetration specified in the Contract documents. The Engineer will require 4 hours at each test pile to set up and install the test equipment. The Engineer will attach testing instruments near the top of the test pile through drilled and threaded holes. The Department will furnish the testing equipment and labor necessary to mount the testing instruments to the pile. Provide a reasonable and safe means of access to the top of the test pile after the pile is placed in the leads. Furnish electrical power (a 115 volt, 55-60 cycle AC outlet, 10 amp minimum) for the Engineer’s use during the installation and operation of the testing instruments.

Drive each test pile to the driving resistance and minimum penetration specified in the Contract documents as indicated by the wave equation analysis. The Engineer will record driving data for the test pile. If an obstruction is encountered during driving of the test pile, testing will stop on that pile and the next pile driven at the substructure unit will be designated as a test pile.

If the test results do not conclude the driving resistance has been obtained, the Engineer may direct suspension of pile driving operations for up to 72 hours and then require restriking the pile with the Engineer present to record driving data. Perform the restrike with a warmed-up hammer with the energy or fuel setting adjusted to the position indicated in the approved pile driving plan. Strike the test pile with 60 consecutive blows or until the pile penetrates an additional 3 inches, whichever comes first. The Engineer may terminate the re-strike after 25 blows if pile penetration is less than 1 inch.

If the results from the high-strain dynamic testing are acceptable to the Engineer, drive the remaining piles at the substructure unit using the criteria set by the Engineer and based on the results of the high-strain dynamic testing. The Engineer will provide new driving criteria within 1 day of the completion of high-strain dynamic testing that confirms the driving resistance of a test pile.

Account for the entire allotted equipment installation time and restrike suspension time required by the Engineer in the progress schedule submitted under Subsection 108-1.03 or Section 646, as applicable. Suspension of pile driving operations at a testing location to allow for testing instrument installation or a re-strike of a test pile is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

505-3.03 DRIVING PILES. Drive all piles to the driving resistance and minimum penetration specified in the Contract documents using the pile driving criteria provided by the Engineer. Use the same pile driving system used to set pile driving criteria to drive all piles. Install piles in groups starting from the center of the group and proceed outward in either direction.

If the pile is driven to the estimated pile tip elevation and does not achieve the driving resistance, continue driving the pile to a penetration established by the written direction of the Engineer.

1.	Driving Through New Embankment. When driving piles through new embankment and the depth of the embankment at the pile location is in excess of 5 feet, drive the pile in a hole made through the embankment. Make the hole diameter 6 inches greater than the pile. After driving the pile, fill the annular space around the pile with sand.

2.	Placement and Alignment. Ensure proper placement and alignment of the piles. The Engineer will reject piles that are bent or otherwise damaged by forcing the pile into the leads or template.

Drive piles within an allowed variation as to direction of pile of not more than 1/4 inch per foot. Limit the rotation of steel piles about their longitudinal axis to 15 degrees from the plan position. In addition, position piles to the following tolerances:

a.	Abutments. Position the piles at the bottom of an abutment within 3 inches of the position specified in the Contract documents. Do not vary the distance between any two piles more than 3 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches.

b.	Pier Footings. Position the piles at the bottom of a footing within 6 inches of the position specified in the Contract documents. Do not vary the distance between any 2 piles more than 6 inches from that specified in the Contract documents, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches.

c.	Exposed Pile Piers. Position the piles within 2 inches of the position specified in the Contract documents at cut-off elevation and within 3 inches of the position specified in the Contract documents at the original ground line elevation.

3.	Protection of New Concrete. When driving a pile near concrete placed within 28 days, ensure the distance between the pile being driven and the nearest edge of concrete is not less than the distance determined by the following formula:

Where:	D = Distance in feet

E = Maximum rated hammer energy in foot-pounds

C = Vibration coefficient shown in Table 505-2 based on the number of calendar days after concrete placement

4.	Obstructions. Use alternate methods to drive through or remove obstructions. Obtain written approval from the Engineer before employing any alternative methods of pile advancement.

After exhausting all practicable means to obtain the minimum penetration, but without success, the Engineer will evaluate the structural adequacy of the bridge at a lesser penetration. This review will be based on the resistance of the pile during driving. If the Engineer finds the structure to be adequate, the pile will be accepted at the lesser pile penetration.

5.	Concrete Filled Pipe Piles. After driving pile, clean out the pile to the bottom of concrete elevation specified in the Contract documents. If there is a delay between cleanout and placing concrete, verify that the soil level in the pile has not rebounded before placing concrete.

TABLE 505-2
VIBRATION COEFFICIENT

| Concrete Age (days) | Coefficient |
| --- | --- |
| 1 | 0.34 |
| 2 | 0.23 |
| 3 | 0.18 |
| 4 | 0.15 |
| 5 | 0.13 |
| 6 | 0.12 |
| 7-9 | 0.11 |
| 10-13 | 0.10 |
| 14-20 | 0.09 |
| 21-28 | 0.08 |

505-3.04 SPLICES, EXTENSIONS AND BUILD-UPS. If the length of a steel pile is not sufficient to obtain the estimated pile tip elevation and driving resistance specified in the Contract documents, the pile may be spliced in order to obtain the length required to reach the minimum penetration and driving resistance. Use additions with cross sections identical to the pile cross sections.

Make splices with complete joint penetration welds over the entire cross section. If approved, piles may be spliced using pile cut-offs and short pieces if no piece used is less than 10 feet long.

Meet the welding requirements of Section 504. Align the piles at a splice to meet the dimensional tolerances for the allowable variation in straightness of welded columns in AWS D1.1.

505-3.05 DEFECTIVE PILES. Use a pile driving method which does not damage the pile. Do not manipulate the piles to force them into proper position. Correct damaged or improperly driven piles using a method approved by the Engineer. Drive down all piles pushed up by driving adjacent piles or by any other cause. Approved methods may include one of the following:

1.	Withdraw and replace the pile with a new and, when necessary, longer pile.

2.	Drive a second pile adjacent to the defective pile.

3.	Splice or build up the pile.

4.	Extend a sufficient portion of the footing to properly imbed the pile.

505-3.06 CUTTING OFF PILES. Cut off the piles at the elevations indicated on the Plans. Ensure that all injured material is removed.

When steel piles are shown embedded in concrete footings or pile caps, cut off piles within -1/2 inch to +3 inches of the plan embedment, but do not interfere with reinforcing steel or other items embedded in concrete. When steel pipe piles are shown cutoff below concrete footings or pile caps, cut off piles within -1/2 inch to +1/2 inch of the plan elevation. In pile bents with steel cap beams, make accurate cut-offs to ensure full bearing between the caps and piles.

505-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Furnish Piles. The sum of the lengths of the piles in place in the completed structure, measured along the centerline of piles from the tip of pile to the cut-off elevation.

Drive Piles. The number of piles driven in place in the completed structure conforming to the contract.

Sheet Piles. The projected area of furnished and driven sheet piles remaining in place in the permanent structure as called for on the Plans, measured in final position.

505-5.01 BASIS OF PAYMENT.

Furnish Piles. The contract price includes pile materials delivered to the site, pile shoes, reinforced tips and casing. Unused pile lengths removed by cut-offs and fresh heading are subsidiary. The payment amount will be calculated using the quantity of pile indicated on the bid schedule, or the quantity of installed piles, whichever is greater.

Drive Piles. The contract price includes:

1.	All related work required to drive the piles including: pile crew time (including payroll and administrative additives), equipment costs, and other fixed or variable items incurred during pile driving, fresh heading, splicing, restrike, pile cleanout and cutting off.

2.	All related work required to assist the Engineer in performing High Strain Dynamic Testing is subsidiary.

Sheet Piles. Sheet piles used as temporary shoring for excavation, whether removed or left in place at your option with permission of the Engineer, are subsidiary.

Obstruction Removal. Alternate methods of pile advancement through obstructions performed at the direction of the Engineer will be paid as 505(14) Special Pile Excavation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

505(5)	Furnish Structural Steel Piles (HP 14 X 117)	Linear Foot

505(6)	Drive Structural Steel Piles (HP 14 X 117)	Each

Replace Section 507 with the following:

SECTION 507

BRIDGE BARRIERS AND RAILING

507-1.01 DESCRIPTION. Construct concrete, timber, or steel bridge railing, pedestrian railing and safety railing as shown on the Plans. Furnish and install bridge number plates as shown on the Plans.

507-2.01 MATERIALS. Use materials that conform to the following:

Steel Railing	Section 722

Timber Railing	Section 506

Concrete	Section 501

Epoxy-Coated Reinforcing Bars	Subsection 709

Grout	Section 701

Cable	Use 1/4-inch galvanized wire rope with a minimum breaking force of 7,000 pounds.

Bronze	ASTM B98, UNS Alloys C65100 or C65500

507-3.01 CONSTRUCTION REQUIREMENTS.

1.	General. Construct railing to the line and grade shown on the Plans. Ensure that the rail does not reflect any unevenness of the bridge structure. Set rail posts plumb. Place railing after all falsework is removed and the span is self-supporting. Do not paint bridge railing.

Furnish and install concrete curbing, associated reinforcing steel, and the approach rail transition bracket for steel bridge railing.

2.	Steel. Erect steel railing in conformance with Subsection 504-3.02, except do not use load indicating washers. Weld in conformance with Subsection 504-3.01.7. Complete welding before galvanizing the railing.

3.	Timber. Fabricate and install timber railing according to Section 506.

4.	Concrete. Construct concrete barriers to meet applicable requirements of Sections 501 and 503. Use Class A concrete having a specified compressive strength of 4000 psi. Apply a rubbed finish to exposed surfaces of concrete.

507-4.01 METHOD OF MEASUREMENT. Section 109.

507-5.01 BASIS OF PAYMENT. The contract price includes all rail elements, rail posts, brackets, spacers, fastenings and anchors required to attach the railing to the structure; concrete and associated reinforcing steel included or partially contained within the limits of the concrete rail section or within the limits of the concrete curb for the steel bridge rail section; and bridge number plates.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

507(4)	Concrete Barrier	Linear Foot

SECTION 508

WATERPROOFING MEMBRANE

Special Provisions

508-1.01 DESCRIPTION.  Add the following:

Comply with the Construction General Permit, issued by the ADEC under the APDES and Section 641 during all phases of construction including the removal of existing asphalt pavement, the waterproofing membrane, and the application of a new membrane, asphalt, and concrete materials.

Remove the existing asphalt pavement and membrane waterproofing on the following bridges:

| Bridge Number | Bridge Name |
| --- | --- |
| 972 | Campbell Creek Bridge |

CR5081-112409

Standard Modifications

508-2.01 MATERIALS.  In paragraph titled Membrane Material, remove the text:  "Approved Products List" and replace with:  Qualified Products List

E36-012707

Special Provisions

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING.

1. 	General.  Replace a. b. c with the following and add d.

a.	Complete bond between the leveling course and concrete bridge deck.

b.	Complete bond between the membrane and the leveling course.

c.	Unbroken waterproof membrane in place between the leveling course and the asphalt overlay.

d.	Complete bond between the membrane and the asphalt overlay.

2.	Preparation of Concrete Deck.  Before applying membrane:  Replace a. through f. with the following:

a.	Remove existing asphalt, concrete, and membrane down to the base concrete bridge deck.

b.	Do not employ removal methods, manual or mechanical, that damage the concrete deck.  Mechanical milling machines such as a reclaimer or planer must not damage the concrete deck.

c.	Remove any contaminants such as grease, oil or paint with solvents, detergents or by sand blasting as approved by the Engineer.  Do not damage the existing concrete deck and deck materials.

d.	Sweep the deck to remove all foreign materials such as dirt, dust, moisture, and loose concrete.  Sweep and or power broom per Subsection 643-3.04 Traffic Control Devices, Item 6., Street Sweeping and Power Brooming.

e.	Before applying the tack coat, primer, or emulsion, thoroughly clean the deck with compressed air.  Disturbed particles, dust or other shall be contained similar to the requirements for street sweeping and power brooming.

f.	Prevent foreign material from entering streams including fugitive dust particles.

508-5.01 BASIS OF PAYMENT.  Replace the second paragraph with the following:

Leveling course and asphalt overlay are paid for under the paving items.

Pavement planing on bridge decks is paid for under 202(15) Pavement Planing.  Additional removal of existing pavement below the pavement planing depth to bare concrete deck is subsidiary to 508 pay items.  Removal of existing waterproof membrane is subsidiary to 508 Pay Items.

Replace Section 512 with the following:

SECTION 512

FORMS AND FALSEWORK

512-1.01 Description. Design, construct, maintain and remove forms and falsework used to temporarily support structural concrete until the structure is self supporting.

512-1.02 DEFINITIONS.

FALSEWORK. A temporary structure erected to support the permanent structure, in the process of construction, until the permanent structure becomes self-supporting and capable of supporting other imposed loads.

FORMS. Also know as formwork, are a temporary structure or mold used to retain the plastic concrete in its designated shape while the concrete is hydrating and gaining sufficient strength to maintain its designated shape.

HAUNCH. A deepened portion of a concrete deck defined as the distance between the top of the girder and the bottom of the roadway slab.

512-2.01 MATERIALS. As specified or approved.

design and construction requirements

512-3.01 SUBMITTALS.

1.	Falsework Plan. When complete details for falsework are not shown on the Plans, prepare and submit a falsework plan, prepared and sealed by a Professional Engineer registered with the State of Alaska.  When the structure is not open to traffic and is not over or adjacent to railroads or roadways, a falsework plan is not required for falsework supporting construction of the following:

a.	Concrete decks

b.	Pier caps

c.	Diaphragms

Include detailed working drawings, material specifications, and supporting calculations to allow for complete review of the falsework plan.  For manufactured or proprietary falsework components, include the manufacturer's information, technical bulletins, design data, and other necessary information used in the calculations.

Include an independent design check to verify that the design satisfies the Contract requirements. Perform the independent design check by a Professional Engineer registered in the State of Alaska that is unaffiliated with the Professional Engineer responsible for the falsework design.

2.	Falsework Inspection Verification. Prior to placing reinforcing steel, perform a falsework inspection by the Professional Engineer responsible for the falsework design.  Do not place reinforcing steel until a written verification, signed by the Professional Engineer responsible for the falsework design, stating that the falsework meets all of the design and construction requirements is provided to the Engineer.

3.	Concrete Deck Haunch Dimensions. Prior to placing falsework, submit the girder elevations, required haunch dimensions, and supporting calculations to the Engineer for review.  Ensure the haunch dimensions meet the requirements of Subsection 512-3.05.

512-3.02 FALSEWORK Design. Design falsework according to the AASHTO Guide Design Specifications for Bridge Temporary Works and these specifications. When the structure is supported by falsework and is open to traffic, also design the falsework for highway loads according to the AASHTO Standard Specifications for Highway Bridges.

1.	Falsework Foundations. Where spread footing type foundations are used, determine the bearing capacity of the soil.

Design and construct pile type foundation according to this specification and Section 505.

2.	Falsework Over Or Adjacent to Roadways. Provide a minimum vertical clearance of 15 feet through falsework, unless otherwise shown on the Plans. Install advance warning devices and vertical clearance signs at falsework openings according to Section 643. Indicate the minimum vertical clearance as 3 inches less than the minimum measurement.

3.	Falsework Over Or Adjacent to Railroads. Design falsework over or adjacent to railroads according to the American Railway Engineering and Maintenance-of-Way Association Manual for Railway Engineering.

512-3.03 Falsework Construction. Construct falsework to conform to the approved falsework plan. Do not begin falsework construction without an approved falsework plan.  Do not modify or alter the structure to accommodate falsework unless otherwise noted or authorized by the Engineer.

When welding falsework, meet the welding requirements of Section 504.

Build camber into the falsework to compensate for falsework deflection and anticipated structure deflection. Camber shown on the Plans or specified by the Engineer is for anticipated structure deflection only.

Do not modify or alter the structure to attach falsework unless otherwise noted or authorized by the Engineer.

512-3.04 Forms. For surfaces that are exposed in the completed work, use plywood forms meeting the requirements of the American Plywood Association (APA) grade High Density Overlaid (HDO) Plyform Class I or other approved material that will produce an equivalent smooth and uniform concrete surface. For other surfaces, use plywood forms meeting the requirements of the American Plywood Association (APA) grade B-B Plyform Class I. Use only form panels in good condition free of defects on surfaces in contact with concrete.

Furnish and place form panels for exposed surfaces in uniform widths of not less than 3 feet and in uniform lengths of not less than 6 feet except where the width of the member formed is less than 3 feet.

Arrange panels in symmetrical patterns conforming to the general lines of the structure. Place panels for vertical surfaces with the long dimension horizontal and with horizontal joints level and continuous. For walls with sloping footings that do not abut other walls, placement of panels with the long dimension parallel to the footing is permitted.

Follow the manufacturer’s written recommendations when using form liners.

Increase the overall thickness of concrete members that receive an architectural finish to maintain the specified minimum cover to reinforcing steel.

Bevel exposed corners and edges with 3/4 inch triangular fillets built into the forms.

Do not modify or alter the structure to attach forms unless otherwise noted or authorized by the Engineer. Form ties, anchors, and other devices may be cast into the concrete for supporting forms or for lifting precast members. Ensure form ties and anchors can be removed without damaging the concrete surface. Do not use driven devices or anchors coated with materials that will stain the concrete for supporting forms. Construct metal ties or anchorages within the forms to permit their removal to a depth of at least 1 inch from the concrete surface without damage to the concrete.

Construct concrete forms mortar-tight. Clean the inside surfaces of forms free of dirt, mortar, and debris. When forms are supported by existing concrete, ensure that the forms fit tightly against the hardened concrete and that no mortar can pass through the joint.

Forms may be omitted when the sides of a footing excavation is in rock. If the excavation is larger than the plan dimensions, any additional concrete placed will be at the Contractor’s expense.

Coat forms to be removed with form release agent prior to use. Use a commercial quality product designed specifically to readily release forms and does not discolor the concrete surfaces.

512-3.05 FORMS AND FALSEWORK FOR CONCRETE DECKS. Use forms and falsework that span between adjacent girders without altering or damaging the supporting girders. Hangers may be cast into the concrete for supporting deck falsework. Do not use driven devices or materials that will stain the concrete to support the falsework. Construct hangers to permit their removal to a depth of at least 1 inch from the concrete surface without damage to the concrete.

Adjust the falsework haunch dimensions to accommodate the actual camber and elevation of the installed girders. Measure the installed girder elevations along the centerline of the girders at locations shown on the Plans after erection but before installing falsework, forms, reinforcing steel, or applying other loads. Determine the required haunch dimensions accounting for the variations in the girder elevations.

For prestressed concrete girders, the girder elevations shown in the Plans are based on estimated girder deflections assuming a time lapse of 40 and 120 days after release of the prestressing strands. The girder elevations shown in the Plans are intended to advise the Contractor as to the expected range of girder deflection at the time of deck forming.

Construct falsework supporting concrete work on steel structures so that loads applied to girder webs are applied within 6 inch of the flange or stiffener. Construct Falsework to distribute loads so that local distortion of the web is not produced.

1.	Forms. Do not use permanent forms including metal, wood, or precast concrete for concrete deck construction, unless otherwise noted. Provide concrete deck forms meeting the following requirements:

a.	Maintain the deck thickness despite irregularities in and between the girders.

b.	Accommodate haunch variation along the length and between the girders.

2.	Haunches. Limit haunch dimensions to meet the following requirements:

a.	1/2 inch maximum embedment of the top flange into the deck measured at the edge of the flange.

b.	2-1/2 inch minimum clearance between the top of deck and shear stud or shear stirrup.

c.	2 inch minimum penetration of shear stud or shear stirrup into the deck.

d.	4 inch maximum haunch measured at the centerline of the girder.

512-3.06 Removal of Forms and Falsework. Remove forms and falsework without damaging the concrete member.

Forms may be removed after the concrete has cured for at least 24 hours, will not be damaged, and has a compressive strength of at least 1400 psi as determined from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure. Protect exposed concrete surfaces from damage. Do not let the concrete surface to become dry if the forms are removed during the curing period.

Completely remove forms, including the roadway deck forms, from cells of box girders which have permanent access. Unless otherwise shown in the Plans, the roadway slab interior forms in cells where no permanent access is available may be left in place.

Falsework may be removed after the concrete has a compressive strength, determined from informational field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure, as specified in Table 512-3.  If informational field test cylinders are not available, meet the minimum number of curing days specified in Table 512-3.

Do not release falsework for cast-in-place prestressed portions of structures until after the prestressing steel has been tensioned.

Table 512-3

FALSEWORK Release Criteria

| Structural Element | Percent of Specified 28-Day Strength (f ’c), min. | Curing Days, min. |
| --- | --- | --- |
| (a) Pier caps | 60 | 7 |
| (b) Concrete decks | 70 | 10 |
| (c) Simple span girders, T-beam girders, slab bridges, cross beams, caps, pier caps not continuously supported, struts, and top slabs of concrete box culverts | 80 | 14 |
| (d) Box girders | 90 | 21 |
| (e) Continuous span girders | 90 | 21 |
| (f) Other elements not previously covered | 80 | 14 |

512-3.07 CLEANUP. Upon completion of the structure and before final acceptance, leave the structure and entire site in a clean and orderly condition. Remove temporary structures, equipment, unused materials, debris, forms, and falsework. Remove falsework piling at least 2 feet below the finished ground line, unless noted otherwise.

512-4.01 METHOD OF MEASUREMENT. Forms and Falsework will not be measured for payment.

512-5.01 BASIS OF PAYMENT. Forms and Falsework are subsidiary to the bridge pay items.

Add the following Section:

SECTION 516

EXPANSION JOINTS AND BEARINGS

516-1.01 DESCRIPTION. Furnish and install expansion joints and bearings according to the Plans.

516-2.01 MATERIALS. Use materials that conform to the following:

Bridge Seals	Subsection 705-2.03

Expanded Polyethylene	Subsection 705-2.06

Structural Steel	Section 716

Elastomeric Bearing Pads	Subsection 720-2.01

Polytetrafluoroethylene (PTFE) Bearings 	Subsection 720-2.03

Water Stops	Section 723

CONSTRUCTION REQUIREMENTS

516-3.01 EXPANSION JOINTS. Locate and form expansion joints as shown on the Plans.

1.	Shop Drawings. Provide shop drawings for expansion joints having a total movement of more than 1.75 inches. Submit drawings showing installation procedures and joint assembly details. Install joints only after shop drawings are approved.

2.	Manufacture and Fabrication.

a.	Open Joints. Place open joints where shown on the Plans. Remove forms without chipping or breaking the corners of the concrete. Do not extend reinforcement across an open joint, unless shown on the Plans.

b.	Filled Joints. Construct expansion joints with expanded polyethylene joint filler as thick as the width of the joint.

Cut the joint filler to the same shape and size as the adjoining surfaces. Fix the joint filler against the concrete surfaces in place to keep the joint filler from displacing when concrete is placed.

Immediately after removing the forms, inspect the expansion joints. Remove concrete or mortar that has sealed across the joint.

c.	Compression Seals. Shape the joint as shown on the Plans. Install the seal according to the manufacturer’s instructions.

Install the seal in one piece for the full width of the roadway joint. Install the seal immediately after the curing period of the concrete.

d.	Strip Seals. Use expansion joint strip seals in one piece for the length of the joint. Shape the steel components to conform to the section of the concrete. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

e.	Steel Joints. At the shop, shape the plates, angles, or other structural components to conform to the section of the concrete. Fabricate and paint structural shapes to meet the specifications covering those items. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint. Meet the joint opening dimension shown on the Plans.

f.	Modular Seals. Shape the joint as shown on the Plans. Use expansion joint modular seals in one piece for the length of the joint. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

g.	Silicone Expansion Joint Seals.  Prepare concrete surface by sandblasting each face until the surface is roughened and all contaminants are removed.  Ensure all joint faces are sound, clean, dry, and free of frost immediately prior to sealant application.  Install a bond breaking backing material that is configured per the sealant manufacturer’s specifications.  Install the sealant according to the manufacturer’s recommendations.

3.	Tolerances. Install expansion joints conforming to the following tolerances:

a.	Top Surface Profile: 1/4 to 5/8 inch recessed from the finished roadway profile.

b.	Surface Irregularities (deviation from a 10-foot straight edge): ±1/8 inch.

c.	Gap Width: ±1/4 inch.

516-3.02 BEARINGS. Install bearing at locations shown on the Plans.

1.	Shop Drawings. Provide shop drawings showing all details of the bearings and of the materials proposed for use. Fabricate bearings only after shop drawings are approved.

2.	Packaging, Handling, and Storage. Prior to shipment from the point of manufacture, package the bearings in a manner to ensure that each bearing will be protected from damage during shipment, handling, and storage. Store the bearings in an area that provides protection from environmental and physical damage. Prior to installation, clean the bearings of all foreign substances.

3.	Construction and Installation. Set the bearing plates, sole plates and elastomeric bearing pads as shown on the Plans in the exact position with full and even bearing on properly finished bearing seats.

Finish bearing areas or grind them to elevation and parallel to the roadway grade and parallel to the roadway cross slope or crown, unless otherwise shown on the Plans.

When shown on the plans, place grout that meets Subsection 701-2.03 under masonry plates. Mix and place grout according to the manufacturer’s written recommendations. Clean concrete areas that will contact the grout. Remove loose or foreign matter that would prevent the bond between the mortar and the concrete surfaces.

Tightly pack the grout under the masonry plates to provide full bearing. After placing, cover exposed surfaces of grout pads with a heavy thickness of burlap saturated with water for 3 days. Do not place a load on the grout until the grout has attained a compressive strength of 5000 psi as determined by field specimen.

Locate sole plates to correspond with the temperature during erection. Anchor bearing securely. Adjust the nuts on anchor bolts at the expansion ends of spans to permit the span to move freely. Burr threads sufficiently to prevent removal of nuts.

Apply epoxy adhesive to the bottom surface of the elastomeric bearing pads before placing them. Do not move the pad until the epoxy has cured and full adhesion is achieved. Do not apply epoxy adhesive to elastomeric bearings used in PTFE bearing assemblies.

4.	Tolerances. Install bearings conforming to the following tolerances:

a.	Horizontal Position: ±1/8 inch

b.	Elevation: ±1/8 inch

c.	Grade and cross slope: ±1/16 inch per foot.

516-3.03 WATER STOPS. Furnish water stops in continuous, full-length segments without field splices. Do not field splice water stops. Ensure all spliced performed by the Manufacturer are fully vulcanized.

Use spacers, supporting wires, or other approved devices to secure the water stop in the position shown on the plans.

Remove and replace water stops that are out of position or shape at no expense to the Department.

516-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Expansion Joint. The sum of the lengths of joints complete in place, measured along the centerline of the joint.

Bearings. Measured per unit, complete in place.

Water Stops. The sum of the lengths of water stops complete in place, measured along the centerline of the water stop.

516-5.01 BASIS OF PAYMENT.

Expansion Joint. Payment for Expansion Joint includes all materials and work necessary for furnishing and installing expansion joints. If no pay item is included in the Bid Schedule for expansion joints, payment for expansion joint is subsidiary.

Bearings. Payment for Bearings includes all materials, testing, and work necessary for furnishing and installing bearings. If no pay item is included in the Bid Schedule for bearings, payment for bearings is subsidiary.

Water Stops. Payment for Water Stops includes all materials, and work necessary for furnishing and installing water stops. If no pay item is included in the Bid Schedule for water stops, payment for water stops is subsidiary.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

516(1)	Expansion Joint (identification)	Linear Foot

516(2)	Bearings (identification)	Each

516(3)	Water Stops	Linear Foot

SECTION 603

CULVERTS AND STORM DRAINS

- Special Provision

603-1.01 DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:  When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  End Sections for Corrugated Polyethylene Pipe must be steel.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9 inches.

CR42-082703

Add the following: Item 603 (21-xx) may be substituted by a like item with review and approval of the engineer. The substitution shall  provide an equivalent pipe diameter with a  Manning’s “n” value of 0.012.

603-3.03 JOINING PIPE.

2.	Metal Pipe.  Add the following after the 2nd sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe of similar or dissimilar materials, regardless of the type of coupling band.  Except, the end section joint does not require a gasket.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

3.	Polyethylene Pipe.  Add the following after the 1st sentence:

Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe.  Except, the end section joint, and where the pipe is manufactured with a locking joint such that the joint seals watertight, a gasket is not required.  Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

CR6031-032411

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty two inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

CR42-082703

Replace the first sentence with:

Coupling bands, gaskets and other items necessary for the proper joining of the sections are subsidiary.

CR6031-032411

- SECTION 604

MANHOLES AND INLETS

- Special Provision

604-1.01 DESCRIPTION.  Add the following:  This work also consists of providing and installing Oil/Grit Separators.

For the purposes of these Special Provisions, "AWWU" shall mean the Anchorage Water and Wastewater Utility, Engineering Division at (907) 564-2774.

Contact AWWU to coordinate a pre-inspection of the sanitary sewer facilities located within the project limits before pavement removal begins and a post inspection after paving operations are complete.  Any deficiencies found during the pre-inspection of the AWWU sanitary sewer facilities and before the Contractor begins work on the project will be AWWU’s responsibility to correct.

Replace sanitary sewer manhole metal frames and covers, where determined by the Engineer, within the project with AWWU supplied materials.  Furnish and install the catch basin inlets and manhole frames and grates as shown on the Plans.

Contact the Engineer for a pre-inspection of the condition of the storm drain manhole metal frames and covers located within the project limits 15 days before pavement removal begins.  The Engineer will determine which storm drain manhole metal frames and covers will be replaced.

604-2.01 MATERIALS.  Add the following:

Oil/Grit Separator:  Provide oil/grit separator units from one of the following manufacturers or approved equal meeting the minimum specification:

Vortechnics			Aquashield, Inc.			Stormwater Management, Inc.

200 Enterprise Drive		2733 Kanasita Drive		10891 James Way Drive SE

Scarborough, ME 04074	Hixson, TN 37343		Aumsville, OR 97325

(877) 907-8676			(423) 870-8888			(800) 548-4667

Minimum Specification:  A structure or pair of structures in parallel or series, which together as a unit treat a minimum of 0.06 cubic yards per second (cy/s).  The water flowing out of the oil/grit separator unit shall meet the water quality standards of 18 AAC 70.020(5)(A)(iii).

Submit shop drawings for proposed oil/grit separator(s) to the Engineer for approval before ordering.

Curb Inlets:  Provide R-3246-CL inlet grates manufactured by Neenah Foundry Company or approved equal.  The approved equal shall meet the following criteria:

Minimum loading capacity:	H20

Minimum captured flow capacity:	0.05 cy/s at a longitudinal grade of 5%

Grate style:	Bicycle friendly*

*Bicycle friendly is defined as:

- The style of grate employed should allow bicycle travel from accessible directions.  Grates located in open areas, or adjacent to driveways, or in other locations where they are not adjacent to barrier curbs, require special attention in this regard.

- If slotted grates or vane-type grates are considered, they should have sufficiently narrow openings, and/or should have appropriately spaced transverse (cross) bars, to ensure that any foreseeable width and diameter of bicycle tire cannot drop down into openings to an unsafe extent.

- Gutter slopes should not be substantially swaled into the curb so as to create a disturbance in the roadway that might affect the ability of bicycles or other traffic to traverse them.

Field inlets:  Use “beehive” type inlet covers for field inlets.

Provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  Provide traffic control while cleaning storm drains.

AWWU will provide new sanitary sewer lids as determined by a pre construction inspection conducted by AWWU.  Contractor shall provide traffic control for this pre construction inspection.

Sanitary Sewer Manholes: Materials used in the construction of manholes shall conform to the requirements of ASTM C-478 (AASHTO-199) and the plans.  Cones shall be Type (b), eccentric, unless otherwise approved.

Cement for mortar used in the construction of sanitary sewer manholes shall conform to the requirements of ASTM C-150, Type II.  Sand shall conform to AASHTO Specification M-45.  Use mortar composed of one (1) part cement and three (3) parts sand.  Construct joints so as to produce a smooth regular watertight surface.  Add only enough water to provide plasticity in placing the mortar.

Frames and Covers: The tensile strength of the gray cast iron for sanitary sewer manhole frames, covers, and pavement-adjusting rings [Inland Foundary Co., Inc., Model #845-3 (or equal)] shall be 30,000-PSI minimum, conforming to the requirements of ASTM A-48.  The requirements for traverse breaking load shall be 2,000 pounds, conforming to the requirements ASTM A-438.  Contact surfaces between frames and covers shall conform to the details of the Plans.  Where lockable manhole covers are specified, the Contractor shall submit Working Drawings of the locking device for approval of the Engineer.

Each pre-cast sanitary sewer manhole concrete barrel section, pre-cast concrete eccentric cone section, concrete adjusting ring, and manhole cover/frame shall be set and sealed by use of a plastic gasket joint sealer as manufactured by Henry Co., Inc., Ram-Nek Sealant Division, or approved equal and installed according to the manufacturer’s specification.

All sanitary sewer manhole joints shall be sealed with MacWrap external joint seals as manufactured by MarMac Manufacturing Company, or approved equal.  External joint seals to be applied per manufacturer’s written recommendations.

All sewer exterior manhole concrete surfaces shall be coated for damp proofing with Henry Company #794 Synko-Mastic, or approved equal, brush grade foundation coating applied per manufacturer’s written recommendations.

Sanitary sewer manholes shall be installed with no less than three (3) layers of 8-mil polyethylene encasement on the outside of the manhole.

Refer to Section 501 for concrete.  The use of Transite or Asbestos Cement (AC) pipe to form manhole inverts is prohibited.

Rubber waterstops used in pipe-to-sewer manhole joints, shall be rings of resilient material that will fit snugly over a pipe.  The resilient material shall be held firmly against pipe surface by means of a stainless steel mechanical take-up device which, when tightened will compress the resilient material or, by a stretch, fit.  The rubber waterstop shall be designed and installed so that leakage between pipe and manhole is eliminated.  Material and manufacture of waterstops shall conform to applicable provision of the ASTM Standard Specifications for Resilient Connectors between Reinforced Concrete Manhole Structure and Pipes, ASTM C923.  Waterstops at manhole pipe penetrations shall be sealed with “Z-lok” and “A-lok” manhole pipe connections or approved equal.

604-3.01 CONSTRUCTION REQUIREMENTS.  Delete the second paragraph and substitute the following:

Install DOT&PF Inlet, Type A, consisting of a precast concrete catch basin structure, grade rings, and metal frames and grate as shown on the Plans.  Grout pipes in place.

Upon removal of manhole component parts, the Contractor shall clean and prepare existing component parts before installation of replacement parts.  This will include, but not be limited to, removing existing grout and Ram-Nek-type sealant from remaining and connecting component parts.

The Contractor shall provide a disposal site for all materials (manhole covers, frames, etc.) removed or replaced.

Add the following:

Probe the manholes with a calibrated bar.  If 50% or more of the manhole sump is filled with debris, remove the debris.  Remove debris from catch basins and inlets regardless of the quantity of debris.  No more than 5% to 10% of debris should remain.  Remove debris (sticks, plastic bags) blocking culvert inlets and outlets.  Record the date of inspection, the depth of sediments, and whether the manhole was cleaned or not, in a grid map book provided by the Engineer.

The Contractor shall provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  The contractor shall provide traffic control while cleaning storm drains.

The work shall include disposal of silt, trash, debris and other material removed from the system.  This material may be disposed at the Municipality of Anchorage Hazardous Materials Waste Disposal site.

Contractor shall install the manhole and separator in accordance with this section and in accordance to manufacturer’s specifications.

Add the following after the third sentence:  A proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

8.	Remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Notify the Engineer a minimum of 5 days before removing the frame and grate.  The Engineer will notify DOT&PF M&O (262-2199) and have an M&O representative physically identify frames and grates to be salvaged.  Frames and grates not designated for salvage by DOT&PF M&O shall become the Contractor’s property.

When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe.  Then, grout joint with non-shrinking cement mortar.

Curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  Keep the openings functional.  This may require temporary dikes, RMC extensions, as necessary.  Fill these holes with grout upon final paving.

Cast standard drainage structure steps or threaded dowels to receive steps during structure pour or install them before concrete hardens.

Install Item 604(1D) according to the manufacturer’s instructions.  Adjust the inverts of the oil/grit separator(s) as necessary to accommodate the selected model while maintaining the minimum amount of cover.

Add the following: Contact the AWWU Project Manager in writing a minimum of three (3) working days in advance of beginning construction to schedule a pre-inspection of the sanitary sewer manholes and a post inspection after paving operations are complete. Provide the Engineer a copy of the written notice. Contractor shall be responsible for furnishing all the required traffic control and personnel to assist AWWU while locating and performing the pre-construction and post-construction inspections.  Both the Contractor and the Engineer shall witness the condition and location of each sanitary sewer manhole. Contractor forfeits all rights to deny damages done by Contractor or Contractor’s agents during the course of work if Contractor fails to participate in this inspection.

Sanitary sewer manhole covers identified as worn in the pre-inspection shall be replaced with new covers provided by AWWU.  Coordinate with the AWWU Project Manager to obtain replacement covers from the AWWU warehouse.

Delete the fifth paragraph and add the following:  The manhole frames and covers shall be brought to grades as shown on the Plans. Manhole grade rings shall be set in and made secure by the use of “Ram-Nek” with primer (or equal).  In paved streets manhole grade rings and frames shall be placed on a full bed of mortar to prevent settlement.   Each manhole must have a minimum of one (1) six-inch grade ring and a two-inch pavement adjusting ring (Inland Foundary Co. Inc. Model #845-3 or equal).

Use of, and installation of a plastic gasket joint sealer (“Ram-Nek” or equal) for manhole construction shall be strictly in accordance with the manufacturer's printed instructions.  Gaskets shall be trimmed on the inside of the manhole to prevent the excess gasket material from entering the sanitary sewer and storm sewer lines.

Add the following to the sixth paragraph:  Prior to backfilling, the Contractor shall apply a bituminous damp proofing coating to the exterior of all sanitary sewer manholes; MacWrap (or equal) at all sanitary sewer manhole joints; and three (3) layers of 8-mil polyethylene encasement on the outside of the sanitary sewer manhole.

Delete the third sentence of the tenth paragraph and add the following:  Changes in directions of flow shall be made by forming a smooth radius sized to allow adequate access of a C.C.T.V. camera and/or maintenance equipment into the served sewer pipe.

Delete the eleventh paragraph and add the following:  The invert channels may be formed and poured in place, or may be constructed by laying a full section of sewer conduit through the manhole and breaking out the top half after the surrounding concrete has hardened.

Add the following after the twelfth paragraph:  All dead-end sanitary sewer manholes shall have an invert installed thru the entire sanitary sewer manhole for insertion of C.C.T.V. and/or maintenance equipment.

Add the following after the thirteenth paragraph:  Storm sewer manholes and catch basin manholes shall be constructed in accordance with the Plans. With reinforced concrete manholes, after the mortar has firmly set, the pipe is to be cut off evenly so that not more than two (2”) inches of the pipe protrudes into the manhole.

604-4.01 METHOD OF MEASUREMENT.  Add the following:

Oil/Grit Separator:  Will be measured as a complete unit in place and shall include the concrete structure, diversion apparatus, frames, and covers.

Frames, grates, and lids will not be measured for payment.  An oil/grit separator unit may consist of one or two structures, as needed, to treat the water as specified.

Adjust Existing Manhole:  The number of existing manholes or inlets adjusted and accepted as complete-in-place.

604-5.01 BASIS OF PAYMENT.  Add the following:

Existing manholes being adjusted by raising or lowering the frame or ring casting 12” or less - comply with Subsection 604-3.01, paragraph beginning, “Adjust existing manhole or Inlet…”  The corresponding Pay Item for this adjustment is 604(4) Adjust Existing Manhole.

All traffic control required for the pre-inspections and post-inspection will be paid under the specific 643 Items.

Frames, grates, and lids are subsidiary to the drainage structure.

Component parts of existing or new manholes shall be included in the unit price for the bid item being constructed, reset, or replaced, and shall be paid for by a cumulative total of each unit constructed.

Payment will be made under:

Add the following pay items:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 604(1A) | Storm Drain Manhole, Type I | Each |
| 604(1B) | Storm Drain Manhole, Type II | Each |
| 604(1D) | Oil/Grit Separator | Each |
| 604(2A) | Sanitary Sewer Manhole, Type A | Each |

- SECTION 606

GUARDRAIL

Special Provisions

606-1.01 DESCRIPTION.  Add the following:

Furnish and install bollard(s) included in the Plans and Specifications.

CR6069-062911

Delete Subsection 606-2.01 and replace with the following:

606-2.01 MATERIALS.  Use materials that conform to the following:

Concrete, Class A or W
(or an approved, pre-mixed, sacked concrete)	Subsection 501-3.01

Wire Cable	Subsection 709-2.02

Metal Beam Rail	Subsection 710-2.04

Guardrail Posts and Blocks	Subsection 710-2.06

Guardrail Hardware	Subsection 710-2.07

Guardrail Terminals	Subsection 710-2.11

Terminal Markers - Flexible (marker).  The marker includes the pole/post/rod (pole), reflective and retroreflective sheeting and mounting hardware.

The marker materials shall be durable, resistant to impact from (snow and vehicle), vandals, ultraviolet light, moisture, ozone, and hydrocarbons.

When the pole is loaded, the marker shall bend/flex, remain flexible and oriented as installed continuing to function as designed without permanent displacement along the length of the member.  The flexibility may be in the primary vertical element, a connecting device between the vertical element and connection to the support member (spring or other) or a combination.

Provide a connection sufficient to transfer the loads from the pole to the supporting member without reducing the strength, flexibility, or durability of either.  The connection shall not negatively impact the performance of the guardrail.  Provide approval of the connection from the marker manufacturer and support member manufacturer (if proprietary).

	Design Loads:

	Impact load from snow thrown by snowplows

Ø	Weight of snow covering the pole as a result of snow thrown from snowplows

Ø	Wind loads (100 mph, 3 sec gust)

·	Service Temperature Range:	-40˚ F to +140˚ F.

·	Pole:

1.	Material:

Ø	Steel, or

Ø	Stainless Steel, or

Ø	Other Poles:

(a)	Continuous glass fiber and marble reinforced thermosetting composite, or

(b)	Engineered plastic alloy, or

(c)	Fiberglass Reinforced Polyester (FRP)

(d)	High-Impact Polyolefins

2.	Dimensions

Ø	Top of Pole:  60 inches to 84 inches above top of guardrail

Ø	Width/Diameter:  minimum = 1 1/4 inches, maximum = 2 inches (steel/stainless steel may not be greater than 5/8 inch diameter)

Ø	Thickness:  as required by design

3.	Visibility:

Ø	Daytime: Pole - color orange

a.	Steel and Stainless Steel Poles:  Applied permanent finish.

b.	Other Poles:  Color pigment ultraviolet stabilized and solid through the cross section from end to end.

Ø	Nighttime:  Added retroreflective sheeting - color white

a.	Approximately 12 square inches visible from the traveled way before and after the marker.  Applied to a flag attached to the pole or as banding applied directly to the pole.  (A flag is required when using steel/stainless steel poles.)

b.	Place top edge of flag/banding 1 inch from top of pole.

(1)	Flag:  Single retroreflective sheet each face

(2)	Banding:  Two bands completely around marker, 4 inches between bands

·	Hardware and Fasteners:

Ø	Steel, and/or

Ø	Stainless Steel, or

Ø	Aluminum alloy (hardware only)

Manufacturers of flexible markers (snowpoles):

| Manufacturer | Model | Type | Contact |
| --- | --- | --- | --- |
| Nordic Fiberglass, Inc. | FF2 | Steel Pole w/ Flag | Ph: (218) 745-5095 |
| PEXCO | Model 3639 | High-Impact Polyolefins | Ph: (404) 564-8560 |
| New Century Northwest, LLC | NCN2549 | Engineered Plastic Alloy | Ph: (541) 485-5566 |
| Carsonite Composites, LLC | SNFB | Continuous glass fiber and marble reinforced thermosetting composite | Ph: (800) 648-7916 |

Submit manufacturer's specifications to the Engineer for review and approval before ordering markers.

Guardrail Reflector Assembly Brackets	Section 730

Fabricate from aluminum alloy or galvanized steel.

Retroreflective Sheeting	AASHTO M 268, Type VIII or IX

CR6062-110410

Add the following:

Bollards.

Concrete; Class A	Subsection 501-3.01

Shapes, Plates and Bars	ASTM A 36

Bollard Pipe	Subsection 716-2.06

Bollard Tube	ASTM A 500, Grade B

Welding	Subsection 716-2.02

Galvanizing	Subsection 716-2.07

Galvanizing Repair	ASTM A 780

Paint (Paint for Steel Structures/Paint of Timber)	Subsection 708-2.01/2.02

Bollard Post (WCLIB; Posts and Timbers, Douglas Fir-Larch No. 1)	Subsection 713-2.01

Preservatives and Pressure Treatment Process for Timber	Subsection 714-2.01

Backfill Material (Selected Material, Type A)	Subsection 703-2.07

Retroreflective Bands (6 inch wide reflector, smooth surface bands)	AASHTO M 268, Type III-A

CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL.  Replace the first sentence in the first paragraph with:

Install bollards, guardrail, and terminals at the locations shown in the Plans.

CR6069-062911

Replace the second paragraph with the following:

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals that are required to completely install a segment of guardrail before beginning work on the segment.

Start guardrail installation at the "upstream" end (the end adjacent traffic will encounter first) by either installing a crashworthy terminal, connecting to an existing barrier or shielding the end with a truck mounted attenuator (TMA) meeting NCHRP 350, Test Level 3.  Continue installation in the direction of traffic.  Exception:  if the guardrail run will connect to existing barrier, buried in the backslope, or guardrail, existing or new bridge railing, or other existing structure at the "downstream" end, guardrail installation may be started at the point of connection.  The exception allows for starting at the downstream end, a temporary crash cushion or TMA is required at all incomplete upstream guardrail ends.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test Level 3 at all non-crashworthy guardrail ends within the clear zone.  Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

CR6063-110410

606-3.02 POSTS.  Delete the first two numbered items and replace with:

1.	Exclusive of end treatments, use one type of post in each run of guardrail.

Replace 3.a. with:

a.	The underlying material is no larger than six inches; and

Replace No. 4. with:

4.	Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically.  Compact under and around posts to the Engineer's satisfaction.

CR6064-110410

606-3.03 BEAM RAIL.  In the first paragraph, second sentence, replace "150 feet" with "100 feet"

CR6065-110410

606-3.05 TERMINAL SECTIONS.  Delete the second paragraph.

Replace the fourth paragraph with the following:

Attach flexible markers, in a vertical position, to the terminal end directly to the backside of the rail face, the face away from the traveled way, or the first post of each guardrail terminal.  Attach flexible markers to the "P.T." post of the Controlled Release Terminals.  Provide an additional marker where the flare begins for guardrail terminal widening.  Provide two markers at the end of each run of guardrail; coordinate the locations with the Engineer.

The connection shall not negatively impact the performance of the guardrail as noted in 606-2.01.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:

Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 14 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

CR6066-110410

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and replace with:

Notify the Engineer a minimum of 5 days before removing guardrail for disposal.  The Engineer will notify the ADOT & PF, M & O, and have an M & O representative designate portions of guardrail for salvage.  Deliver salvaged guardrail and associated hardware to the M & O yard located at 5300 East Tudor Road, Anchorage, Alaska 99507.  Remaining items removed become the Contractor's property.

CR6067-032311

Add the following Subsection 606-3.09 Flexible Markers:

606-3.09 FLEXIBLE MARKERS. For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

CR6062-110410

Add the following Subsection 606-3.10 Length of Need Verification.

606-3.10 LENGTH OF NEED VERIFICATION.  After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends.  The Engineer will approve the staked location of the guardrail before installation.  The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

CR6068-110410

Add the following Subsection 606-3.11 Bollards:

606-3.11 BOLLARDS.

Steel Bollards.  Galvanize all steel members and hardware.

a.	Perform all welding according to AWS D1.1.

b.	Shop galvanize steel bollards and associated hardware, after fabrication.  Repair damage to galvanizing after installation.

Wood Bollards.  Preservative treat all wood material.

a.	Treat field cuts, bolt holes and similar according to AWPA Standard M4.

Installation.  Install bollards in concrete, plumb, back fill with specified material, and compact to the satisfaction of the Engineer.  Padlocks for removable bollards shall be American Lock, WWE Series 3560 to be purchased from Action Locksmith, 243 West 5th Avenue, Anchorage, Alaska, Telephone (907) 279-7050, or approved equal.  Cores are to be keyed to Municipality of Anchorage (MOA) cores matched to a 645 key.  Installation of the cores must be authorized by Allan Pickett with the MOA, Telephone (907) 343-8270.  Padlock keys shall be given to the Engineer.

Retroreflective Bands.  Apply two white retroreflective bands placed 3-4 inches from the top with a maximum of 6 inches between the bands.

606-4.01 METHOD OF MEASUREMENT.  Add the following:

Bollard(s).  Measured by each unit installed and accepted.

CR6069-062911

606-5.01 BASIS OF PAYMENT.  Add the following:

Payment for temporary crash cushions or TMA installed to protect motorists from guardrail installations that have not been completed within 10 calendar days of beginning installation is subsidiary to other items.

2.	Terminal Sections.

c.	Controlled Release Terminals (CRT).

Replace "object markers" with "terminal markers"

Add d.:

d.	Buried in Backslope Guardrail Terminal.  The contract price includes rail elements, posts, blocks, concrete, rebar, anchors, and all associated hardware required for a complete installation.

Add the following:

Guardrail salvage is subsidiary to Pay Item 606(6) Removing and Disposing of Guardrail.

CR6067-032311

Add the following:

Bollard(s).  Payment for bollard Pay Items is full compensation for furnishing all labor, equipment, and materials required for a complete installation as shown in the Plans and included in the Specifications.  The following are considered part of a complete installation when shown in the Plans or included in the Specifications and are subsidiary to the Pay Item:

|  Concrete |  Marker(s) |  Removable bollard hardware |
| --- | --- | --- |
|  Excavation & backfill |  Padlock(s) |  Retroreflective bands |
|  Galvanizing & repair |  Painting & repair |  Steel reinforcing |
|  Grading |  Preservative treatment & repair |  |
| Other items included in the Plans or Specifications associated with the bollards(s) |  |  |

Payment will be made under:

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

606(17)	Bollard	Each

606(17A)	Steel Bollard - Fixed	Each

606(17B)	Steel Bollard - Removable	Each

606(17C)	Wood Bollard - Fixed	Each

606(17D)	Wood Bollard - Removable	Each

CR6069-062911

SECTION 607

FENCES

Special Provisions

607-1.01  DESCRIPTION.  Add the following:

- Scope of Work.  The work under this section includes but is not limited to all labor, materials, transportation, testing, maintenance, and service necessary to furnish and install a Trail Protection Fence as shown on the drawings and specified herein.  Contractor shall recognize that the Trail Protection Fence will require inspection during construction on a routine basis throughout the fabrication process.  ***deleted***

Alternative methods of fabrication may be provided through shop drawings for approval by the Engineer.

- Definitions.

Structural Steel:  Elements of structural-steel frame, as classified by AISC’s “Code of Standard Practice for Steel Buildings and Bridges,” that support design loads.

607-2.01  MATERIALS.  Add the following:

Stainless Steel Cable

1.	Provide stainless steel cable from one of the following manufacturers or an approved equal:

Feeney Inc.	The Cable Connection	Atlantis Rail Systems

2603 Union Street	52 Heppner Drive	70 Armstrong Road

Oakland, CA 94607	Carson City, NV 89706	Plymouth, MA 02360

(800) 888-2418	(800) 851-2961	(800) 541-6829

www.feeneyarchitectural.com	www.thecableconnection.com	www.atlantisrail.com

The Feeney, Inc. cable shall be CableRail.  The Cable Connection cable shall be Ultra-tec Stainless Steel Cable Railing.  The Atlantis Rail Systems’ cable shall be Stainless Railing.

2.	Cable assemblies and fittings.

  - Cables:  3/16” diameter stainless steel cables.

  - Fittings:  Use stainless steel fittings, swages, and any other connections that are a part of one manufacturer’s cable system.

  - Components:  Use Standard Cable Assemblies from one manufacturer.  Cable shall be 3/16” diameter, with nylon flat washers, stainless steel washer-nuts, stainless steel end caps, and stainless steel fittings/connectors for assemblies.

  - Accessories:  Stainless steel protector sleeves, rubber grommets, beveled washers and additional accessories as recommended by manufacturer for installation conditions.

Materials:

- W-Shapes:  ASTM A992.

- Plate and Bar:  ASTM A 36/A 36M.

- Steel Pipe:  ASTM A 53/A 53M, Type E or S, Grade B.

  - Weight Class:  As indicated on drawings.

- Tube Shapes:  ASTM A500, Grade B.

- Welding Electrodes:  Comply with AWS requirements.

Bolts, Connectors, and Anchors:

- Bolts:  ASTM A 307, Grade B, as indicated on drawings.

  - Configuration:  Straight.

  - Nuts:  ASTM A 563 hex carbon steel.

  - Plate Washers:  ASTM A 36/A 36M carbon steel.

  - Washers:  ASTM F 436 hardened carbon steel.

  - Finish:  Mechanically deposited zinc coating, ASTM B 695, Class 50.

Fabrication:

1.	Fabricate and assemble in shop to greatest extent possible.  Fabricate according to AISC's "Code of Standard Practice for Steel Buildings and Bridges" and AISC's "Specification for Structural Steel Buildings--Allowable Stress Design and Plastic Design."

a.	Mark and match-mark materials for field assembly.

b.	Complete structural-steel assemblies, including welding of units, before priming and painting.

2.	Thermal Cutting:  Perform thermal cutting by machine to greatest extent possible.

a.	Plane thermally cut edges to be welded to comply with requirements in AWS D1.1.

3.	Bolt Holes:  Cut, drill, or punch standard bolt holes perpendicular to metal surfaces.

4.	Finishing:  Accurately finish ends of columns and other members transmitting bearing loads.

5.	Holes:  Provide holes required for securing other work to structural steel and for passage of other work through steel framing members.

a.	Cut, drill, or punch holes perpendicular to steel surfaces. [Do not thermally cut bolt holes or enlarge holes by burning.]

b.	Base-Plate Holes:  Cut, drill, mechanically thermal cut, or punch holes perpendicular to steel surfaces.

c.	Weld threaded nuts to framing and other specialty items indicated to receive other work.

Shop Connections

1.	Weld Connections:  Comply with AWS D1.1 for welding procedure specifications, tolerances, appearance, and quality of welds and for methods used in correcting welding work.

a.	Remove backing bars or runoff tabs, back gouge, and grind steel smooth.

b.	Assemble and weld built-up sections by methods that will maintain true alignment of axes without exceeding tolerances of AISC's "Code of Standard Practice for Steel Buildings and Bridges" for mill material.

c.	Verify that weld sizes, fabrication sequence, and equipment used for architecturally exposed structural steel will limit distortions to allowable tolerances. Prevent weld show-through on exposed steel surfaces.

i.	Grind butt welds flush.

ii.	Grind or fill exposed fillet welds to smooth profile.  Dress exposed welds.

Preparation, Priming, and Painting

- Powder coating shall be applied through a seven-step process to provide an acceptable finish:

  - Abrasive sandblast to SSPC-SP10, near white sandblast, with a surface profile of no greater than 1.5 mils.

  - Iron phosphate treatment to etch surfaces and remove foreign material.

  - Rinse with clear water.

  - Non-chrome seal rinse.

  - Oven drying surfaces prior to powder coating.

  - Apply powder coat base of 3 mils of a zinc rich primer electrostatically and cure partially.

  - Apply final surface finish of polyester powder electrostatically to a thickness of 3 mils and bake to proper cure schedule.

- All non-stainless steel components shall be painted with a polyester powder coating system for exterior applications.  The structural steel posts of the Trail Protection Fence shall receive a Jet Black finish, RAL #9005, polyester powder coating.

Source Quality Control

- Owner will engage an independent testing and inspecting agency to perform shop tests and inspections and prepare test reports.

  - Provide testing agency with access to places where structural-steel work is being fabricated or produced to perform tests and inspections.

Decorative Fence Fabric

1.	Provide fence fabric from one of the following manufacturers or an approved equal:

Seattle Textile, Co.	Fence Fabric	Emerald City Products

3434 2nd Avenue South		P.O. Box 2604

Seattle, WA 98134		Renton, WA 98056

(206) 233-0595	(888) 336-2350	(866) 478-5312

www.fencefabric.com	www.privacyfencesolutions.com

2.	Fence fabric shall be “Woven Mesh,” see-through with an image printed on both sides of the fabric.

3.	Image for the fabric shall be supplied to the fabricator by the Landscape Architect.  The Landscape Architect will provide the fabricator with a digital file, showing both sides of the fabric, in .pdf, .jpg, or .tif format for use in creating the fence fabric.

607-3.01  CONSTRUCTION REQUIREMENTS.

Submit following items:

1.	Product Data:  For each type of product indicated.

2.	Shop Drawings

a.	Stainless Steel Cables:  Indicate materials, sizes, fabrication, anchorage and installation details, and lengths for cable systems on shop drawings prepared by fabricator of cable supporting structure.

b.	Structural Steel Components (show structural-steel components):

i.	Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld.

ii.	Indicate type, size, and length of bolts, distinguishing between shop and field bolts.  Identify pre-tensioned and slip-critical high-strength bolted connections.

- Maintenance Instructions:

a.	Manufacturer’s recommendation for periodic checking and adjustment of cables to maintain uniform cable tension.

b.	Manufacturer’s recommendation for periodic cleaning to remove accumulated dirt, debris, and stains.

- Quality Assurance/Control Submittals:

a.	Qualifications:

i.	Proof of manufacturer’s qualifications.

ii.	Fabricator Qualifications: A qualified fabricator who participates in the AISC Quality Certification Program and is designated an AISC-Certified Plant, Category 1.

iii.	Welding: Qualify procedures and personnel according to AWS D1.1, “Structural Welding Code—Steel.”

b.	Manufacturer’s Installation Instructions.

c.	Welding certificates.

d.	Mill Test Reports: Signed by manufacturers certifying that the following products comply with requirements:

i.	Structural Steel including chemical and physical properties.

ii.	Bolts, nuts, and washers including mechanical properties and chemical analysis.

Manufacturer Qualifications: Minimum five years experience in producing cable assemblies of the type specified.

Follow manufacturer’s instructions.

Store materials to permit easy access for inspection and identification.  Keep steel members off ground and spaced by using pallets, dunnage, or other supports and spacers.  Protect steel members and packaged materials from erosion and deterioration.

Store fasteners in a protected place.  Clean and relubricate bolts and nuts that become dry or rusty before use.

Do not store materials on structure in a manner that might cause distortion, damage, or overload to members or supporting structures.  Repair or replace damaged materials or structures as directed.

Furnish anchorage items to be embedded in or attached to other construction without delaying the Work.  Provide setting diagrams, sheet metal templates, instructions, and directions for installation.

Examination:

- Examine work to which cables will be anchored or will penetrate. Coordinate with responsible entity to perform corrective work as necessary.

- Take field measurements and compare installation conditions to shop drawings. Notify manufacturer if field measurements vary from shop drawings.

- Verify elevations of concrete- and masonry-bearing surfaces and locations of anchor rods, bearing plates, and other embedments, with steel erector present, for compliance with requirements.

- Proceed with installation only after unsatisfactory conditions have been corrected.

Preparation:

  - Provide temporary shores, guys, braces, and other supports during erection to keep structural steel secure, plumb, and in alignment against temporary construction loads and loads equal in intensity to design loads.  Remove temporary supports when permanent structural steel, connections, and bracing are in place, unless otherwise indicated.

Installation and Erection:

    - Follow manufacturer’s installation instructions.

    - Isolate dissimilar metals with grommets or bushings.

    - Decorative Fence Fabric shall be attached to the trail protection fence with stainless steel cabling (through the grommets), cinching the fabric to the fence framing.

    - Set structural steel accurately in locations and to elevations indicated and according to AISC's "Code of Standard Practice for Steel Buildings and Bridges" and "[Specification for Structural Steel Buildings--Allowable Stress Design and Plastic Design]

    - Base Plates:  Clean concrete- and masonry-bearing surfaces of bond-reducing materials, and roughen surfaces prior to setting base plates.  Clean bottom surface of base plates.

  - Set base plates for structural members on wedges, shims, or setting nuts as required.

  - Weld plate washers to top of base plate.

  - Snug-tighten anchor rods after supported members have been positioned and plumbed.  Do not remove wedges or shims but, if protruding, cut off flush with edge of base plate before packing with grout.

6. 	Maintain erection tolerances of structural steel within AISC's "Code of Standard Practice for Steel Buildings and Bridges."

7. 	Align and adjust various members forming part of complete frame or structure before permanently fastening.  Before assembly, clean bearing surfaces and other surfaces that will be in permanent contact with members.  Perform necessary adjustments to compensate for discrepancies in elevations and alignment.

- Level and plumb individual members of structure.

- Make allowances for difference between temperature at time of erection and mean temperature when structure is completed and in service.

- Splice members only where indicated.

- Remove erection bolts on welded, architecturally exposed structural steel; fill holes with plug welds; and grind smooth at exposed surfaces.

- Do not use thermal cutting during erection.

- Do not enlarge unfair holes in members by burning or using drift pins.  Ream holes that must be enlarged to admit bolts.

Cleaning:

1.	Clean cables thoroughly using synthetic scotch type pads and hot soapy water (or denatured alcohol) to remove residual lubricants; rinse thoroughly with clear water and wipe dry.

607-4.01  METHOD OF MEASUREMENT

Trail Protection Fence.  Measured lump sum for fabrication and as complete units in place.  All preparation required for construction of Trail Protection Fence shall not be measured separately, but as an incidental part of the full installation.

607-5.01  BASIS OF PAYMENT.  Basis of payment shall include full payment for work described in this section.

Payment shall be made under:

Pay Item No.	Pay Item	Pay Unit

607(12)	Trail Protection Fence 	Lump Sum

- SECTION 608

- SIDEWALKS

- Special Provision

608-1.01 description.  Add the following:  This work also consists of constructing asphalt pathway(s) and patterned concrete median(s) to conform to the Plans.

608-2.01 MATERIALS.  Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

- Asphalt Cement, PG 52-28	subsection 702-2.01

Aggregate, Type II or III	subsection 703-2.04

Mix Design Requirements (ATM 417)

- Marshall Stability, pounds, min.	1,000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

R47(05/22/07)

Add the following:

3.	Patterned Concrete shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.03 Batching shall be modified as follows:

- Air Entrainment.  5 to 7%.  Air entraining agents complying with ASTM C 260 may be used

- Color.  The Patterend Concrete shall be colored full depth with a pigment which closely matches Bomanite Integral color “Coal Gray” and use a color hardener treatment similar to the Bomanite color hardener “Coal Gray.”  Colors and hardeners shall be approved by the Engineer before use.

- Release Agent.  A liquid Bomacron Release Agent, available from Bomanite Corporation, shall be applied to all concrete surfaces to be imprinted and textured.  The color shall be “Black.”  Color shall be submitted for Engineer approval.

608-3.01 CONCRETE SIDEWALKS.  Replace the fifth paragraph with the following:

Joints:	Tooled control joints shall be spaced evenly every 6 feet and shall coincide with the curb and gutter control joints.

Expansion joints shall be placed every 102 feet and at each end of the work and shall have tooled edges.  No "zip strips" will be allowed as a substitution for full depth joint filler.

Fill expansion joints with the type of preformed expansion joint filler specified.

Add the following:

Concrete sidewalk shall be 6 inches thick through driveway sections.

Standard Modification

608-3.03 CURB RAMPS.  Delete subsection in its entirety and replace with the following:

Construct curb ramps according to the details and the locations shown on the Plans.  Follow the construction requirements of Subsection 608-3.01.  Give the exposed concrete surface a coarse broom finish.  Install detectable warnings.

Add new subsection:

608-3.04 DETECTABLE WARNINGS.  Construct detectable warnings according to the details and the locations shown on the Plans.  Install detectable warning tile by embedding tile flanges into cast in place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch.  Align pattern on a square grid in the predominant direction of travel.  Install the same type of detectable warning tile throughout the project.

Install cast iron, yellow polymer soaked or black asphalt dip finish, with slip resistant surface with handle or flange on bottom, and with truncated dome pattern; or approved equal.

Detectable warnings shall be manufactured and installed according to the Americans with Disabilities Act Accessibility Guidelines.

E61(07/28/08)

- Special Provisions

- Add the following:

608-3.05 ASPHALT PATHWAY.  Construct asphalt pathway according to subsection 608-3.02, Asphalt Sidewalks.

608-3.06 ASPHALT PATHWAYS AND MEDIANS.  Construct asphalt pathways and medians according to subsection 608-3.02, Asphalt Sidewalks.

- 608-3.07 PATTERNED CONCRETE.  The excavation and embankment, forms and fine grading, placing and finishing, curing and protection operations for patterned concrete shall conform to Section 608-3.01 Concrete Sidewalks.

- The medians will consist of stamped concrete with the following pattern:

Patterned Concrete shall be stamped with a pattern from one of the following manufacturers or an approved equal:

L.M. Scofield Company	Patterned Concrete	Pattern Paving Products

6533 Bandini Boulevard		1750 Highway 160 West, Suite 101-222

Los Angeles, CA 90040		Fort Mill, SC 29708

(800) 800-9900	(800) 252-4619	(888) 434-8611

www.scofield.com	www.patternedconcrete.com	www.patternpaving.com

The L.M. Scofield Company pattern shall be “Canyon Stone” Random Interlocking (38 inch x 36 inch) pattern # 401A.  The Patterned Concrete pattern shall be “Random Stone.”  The Pattern Paving Products’ pattern shall be “Fieldstone."

- Place patterned concrete in dry weather with temperatures above 40 degrees Fahrenheit.

- Brickform Color Hardener shall be applied evenly to the plastic surface by the dry-shake method using a minimum of 60 pounds per 100 square feet.  It shall be applied in two or more shakes, floated after each shake, and finished with a steel float.

- The patterned concrete shall be colored with a pigment that closely matches Bomanite Integral color “Coal Gray” and use a color hardener treatment similar to the Bomanite color hardener “Coal Gray.”  Colors and hardeners shall be approved by the Engineer before use.

- A Bomacron Release Agent, available from Bomanite Corporation or an approved equal, shall be applied to all concrete surfaces to be imprinted and textured.  The color shall closely match Bomanite “Black.”  Color shall be approved by the Engineer before use.

- Bomacrom Color Curing Compound, thinned in the proportion of one part cure to one part mineral spirits (paint thinner), shall be applied uniformly with a roller or sprayer immediately after patterning.  The coverage shall be approximately 600 to 650 square feet per gallon of unthinned curing compound.

- At times when the air temperature is at or near freezing, the slab shall instead be cured using a suitable curing blanket, and if possible, the slab shall later be sealed with Bomanite Color Curing Compund or approved equal at such time as the temperature is safely above freeing.  If, at any time during the curing period, any of the forms are removed, a coat of curing compound shall be applied immediately to the exposed surface.  Additional coats shall be applied if the Engineer determines that the coverage is not adequate.

Standard Modification

608-4.01 METHOD OF MEASUREMENT.  Delete fifth paragraph beginning with:  “Curb Ramp” and replace with the following:

Curb Ramp.  By each installation, complete in place, including detectable warnings, ramp runs, backing curbs, flares, and landings necessary to provide a single street-level access.

E61(07/28/08)

- Special Provision

Add the following:

Asphalt Pathway.  By the ton of asphalt concrete according to Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.

Patterned Concrete, 4 Inches Thick.  Measured by the square yard of finished surface area.

608-5.01 BASIS OF PAYMENT.  Add the following:  Asphalt cement for Asphalt Pathway and Asphalt Pathways and Medians will not be paid for separately, but will be subsidiary to respective pay items.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

Additional 2 inch thickness for concrete sidewalk through driveway sections shall be subsidiary to Pay Item 608(1a).

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

608(7) 	Asphalt Pathway 	Ton

608(10)	Detectable Warning Tiles	Each

608(17B)	Patterned Concrete, 4 Inches Thick	Square Yard

SECTION 609

CURBING

Special Provisions

609-3.01 GENERAL.  Replace the first sentence of the second paragraph with the following:

Tooled control joints shall be spaced in the curb and gutter every 12 feet.

Expansion joints shall be placed at all radius points, driveways, curb inlets and as directed by the Engineer.  In no case shall expansion joints be placed more than 300 feet apart.

Add the following subsection:

609-3.06 BUMPER CURBS.  Concrete Bumper shall conform to Subsection 609-3.03, Precast Concrete Curb, and the Plans.

609-4.01 METHOD OF MEASUREMENT.  Add the following:

Concrete Bumper.  By each complete installation.

609-5.01 BASIS OF PAYMENT.

Add the following Pay item:

Pay Item No.	Pay Item	Pay Unit

609(7)	Concrete Bumper	Each

SECTION 611

RIPRAP

Special Provision

611-2.01 MATERIALS.   Add the following after the first sentence:  Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.

R277(11/07/05)

611-5.01 BASIS OF PAYMENT.  Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

611(1A)	Riprap, Class 1	Cubic Yard

611(1B)	Riprap, Class 2	Cubic Yard

SECTION 615

STANDARD SIGNS

Special Provision

615-2.01 MATERIALS.  Delete the first paragraph of Item 2, including subitems a., b., c., and replace with:

2.	Sign Fabrication.  Use Type IV reflective sheeting (for lettering symbols, borders, and background) on sheet aluminum panels for all signs except the following:

a.	Orange Background Signs.  Use Type IX fluorescent orange reflective sheeting placed on sheet aluminum panels, except:

For temporary installations the reflective sheeting may be placed on aluminum, plastic, or plywood sheet panels.

For flexible signs (Roll-Up Signs) use fluorescent reflective sheeting Type VI or better (based on durability and reflectivity, as determined by the Engineer).  Roll-Up Sign – 3M Series RS 24, Reflexite Marathon Orange, or approved equal.

b.	Railroad Crossbucks and Vertical Crossbuck Supports:  Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

c.	Non-Illuminated Overhead Signs with White Legends on Green Backgrounds:  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

d.	Fluorescent Yellow-Green School Area Signs:  Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor			YF = 20%

Minimum Total Luminance Factor			YT = 35%

The warranty shall stipulate:  If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

R615 (06/17/08)

Standard Modification

In Item 2.a Orange Background Signs, add:  Roll Up Signs: Use 3M series Rs 24, Reflexite Marathon Orange, or approved equal (based on durability and reflectivity, as determined by the Engineer).  Use flexible signs with fluorescent reflective sheeting that is Type VI or better.

E41(01/27/07)

Special Provision

615-3.01 CONSTRUCTION REQUIREMENTS.

7.	Add the following after the first paragraph:

Deliver salvaged signs panels, posts, and hardware to the State Maintenance Yard, located at 5300 East Tudor Road, Anchorage, Alaska 99507.

CR6151-032411

SECTION 616

THAW PIPE AND THAW WIRES

Standard Modifications

616-2.01 THAW PIPE.  Second sentence delete:

“and Fittings”

Add the following sentence:  Fittings ASTM A234 galvanized according to AASHTO M 111.

E14-063004

SECTION 618

- SEEDING

- Special Provision

618-1.01 DESCRIPTION. Delete this subsection in its entirety and substitute the following:  All new or disturbed areas shown on the Plans and any other areas identified by the Engineer within the project limits shall be seeded.

This work shall consist of topsoil preparation, hydraulic application or hand broadcasting of the seed, finishing work including raking seed into the soil, fertilizing and limestone application in conformance with the Plans and Specifications.

618-2.01 MATERIALS.  Add the following to the list of materials:

- Schedule A	Subsection 724-2.02, Table 724-1

- Schedule B	Subsection 724-2.02, Table 724-2

- Schedule C	Subsection 724-2.02, Table 724-3

- Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes.  Cover all slopes to be seeded with compost blanket according to Section 619.  Complete slope preparation as soon as compost blanket is placed on the slopes.

Standard Modification

Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods with associated equipment before the application of seed:

1.	Manual raking with landscaping rakes;

2.	Mechanical track walking with track equipment; or

3.	Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS.  Add the following: Application of Seed Mix A, Seed Mix B and Seed Mix C shall be performed between May 15 and August 15.  Seeding outside of the specified timeframe may be approved by the Engineer.  The Contractor shall submit request for extension of seeding season in writing and provide appropriate guarantee for remedy if seeding proves to be unsuccessful.

618-3.03 APPLICATION.  Add the following as subparagraph e.) to subsection 1.) Hydraulic Method: Seed, mulch and fertilizer for seeding shall be applied adhering to the application rates shown in the following table.

Item	Application Rate (per acre)

Schedule A, B, C	As Specified

Mulch	1500 lbs

Fertilizer (16-16-16)	350 lbs

Prior to applying Schedule B Seed Mix with the hydraulic method, the tank shall be thoroughly flushed, cleaned and drained to prevent seeds of species that are not part of Schedule B Seed Mix from contaminating Schedule B Seed Mix, the wildflower seed mix.  The Engineer shall have the authority for inspection.

618-3.04 PLANT ESTABLISHMENT AND MAINTENANCE.

Add the following:

Fertilizing.  Fertilizer shall be reapplied with water twice between May 31 and September 1 at a rate of one-half the initial application to all seeded areas, as shown on Plans, during the maintenance period.

Fertilizer shall be reapplied once between May 15 and June 15 at a rate of one-half the initial application to all seeded areas, as shown on the Plans, during the maintenance period.

- Watering during establishment.  Contractor shall ensure that the seeded areas stay moist during germination and seedling establishment (as defined by the grass plants attaining a height of approximately 3 inches).  The Contractor shall be prepared to water the seeded areas 3 times a day if weather conditions warrant it, until seedlings have become established.

- If the Contractor fails to apply adequate moisture during the germination period for 4 consecutive days, or after 2 notices without immediate response, the Engineer may declare all affected seeding unacceptable.  The Contractor will be required to reseed areas that have not been kept moist.

- Weeding.  The Contractor shall maintain all areas in a weed-free condition. Weed removal shall be a routine maintenance activity.  Chemical application must be in compliance with State of Alaska rules and regulations.

- Mowing.  To control successional growth of voluntary species all seeded areas with Schedule A, B, and C Seed Mixes shall be mowed once at the end of the growing season after October 1 when plants are dormant.

Maintenance period.

One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract.  Seeding will only be accepted as fully complete for maintenance requirement purposes, no partial acceptance will be given.

For roadsides and other areas the maintenance period shall be 90 days following their acceptance.  This period shall fall within the time defined for growing seasons.

The Contractor shall repair any damage to all seeded areas within their respective maintenance periods upon request by the Engineer.

Acceptance:

During final inspection, the Engineer will perform a visual inspection of seeding to determine final stabilization.  During the visual inspection, each station and each side of the road will be considered a separate area.  The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-4.01 METHOD OF MEASUREMENT.  Delete full paragraph and substitute the following:  Seeding with Schedule A, B, and C Seed Mixes shall be measured by the pound.  Measurement by the pound shall be the number of pounds of seed (Dry Measure) for Schedule A, B, and C Seed Mixes accepted in place.

The amount of mulch, fertilizer, limestone and water for maintenance in this work, including any required reseeding, will be subsidiary to Pay Items 618(2A-2C) and shall not be measured separately for payment.

The work described under subsection 618-3.01 Soil Preparation shall not be measured but will be subsidiary to Items 618(2A-2C).

Maintenance for seeded areas will not be measured separately, but shall be subsidiary to Items 618(2A-2C).

Seeding by the Square Yard. By the area of ground surface acceptably seeded and maintained.

618-5.01 BASIS OF PAYMENT.  Add the following:

Seeding by the Square Yard.  Payment is for established vegetative matt.  Soil preparation, fertilizer, and water required for hydraulic method are subsidiary.

Water for Seeding. Water applied for growth of vegetative matt, including maintenance and water for hydraulic seeding and fertilizing are subsidiary.  Water after project completion is subsidiary.

Partial payments of up to 90% of full amount may be authorized for seeded areas with 90 day maintenance period requirement at the time of acceptance.  The balance shall be paid at the completion of the maintenance period.

- Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

618(1A)	Seeding, Schedule A	Square Yard

618(1B)	Seeding, Schedule B	Square Yard

618(1C)	Seeding, Schedule C	Square Yard

- Replace Section 619 with the following:

- SECTION 619

- SOIL STABILIZATION

- 619-1.01 DESCRIPTION.  Furnish, place, and maintain mulch or compost blanket material where shown on the Plans. Compost blanket shall be applied to a sloped soil surface to reduce erosion for long term stabilization riparian buffer areas.

- 619-2.01 MATERIALS. Use materials that conform to the following:

Mulch 	Subsection 727-2.01

Compost Blanket	Subsection 727-2.04

- CONSTRUCTION REQUIREMENTS

- 619-3.01 SURFACE PREPARATION.  Smooth the surface and backfill all gullies and potholes before application.

Remove all sticks and other foreign material that prevent contact of the compost blanket and surface.

Ensure the surface is moist at the time of application.

619-3.02 APPLICATION.  Apply compost blanket to soil surface no steeper than 2H:1V in a uniform thickness of 2 inches minimum. The compost may be distributed by hand using a hand shovel, spreader unit, or pneumatic blower.  Project compost directly at soil surface, thereby preventing water from moving between the soil-compost interface.  Where applicable, the compost blanket shall extend at least 3 feet over the shoulder of the slope. Use compost on areas that only have sheet flow drainage patterns. Do not use compost as mulch on areas that receive concentrated flows. Avoid very coarse compost if the slope is to be landscaped or seeded as it will make planting and vegetation establishment more difficult. Slightly roughen (scarify) slopes and remove large clods, rocks, stumps, roots larger than two (2) inches in diameter and debris on slopes where vegetation is to be established. Where it is practical, track (compact) perpendicular to contours on the slope using a bulldozer before applying the compost. On highly unstable soils, use compost in conjunction with appropriate structural and diversion measures.

Use only well-composted product that contains no substances toxic plants where planting; immediate grass, wildflower, or ornamental planting. Dry or hydraulic seeding may be completed following compost application, as required or during the compost application itself, where a pneumatic unit is used to apply the compost. Do not use vehicles or equipment which cause rutting or displacement of the subgrade or compost blanket.

- 619-3.03 MAINTENANCE.  Compost blanket shall be checked after each major rainfall. Reshape and reseed any damaged areas and repair the straw matting or compost blanket as required.

Maintain the mulch and compost blanket until all work on the project is complete and accepted.

- 619-4.01 METHOD OF MEASUREMENT.

Add the following:  Preparation of slopes as described above shall be subsidiary to Item 619(3) Compost Blanket (2 Inch Depth).

Measurement shall be made on the slope of the ground surface, per section 109.

Furnishing and installing mulch shall be subsidiary to Pay Items 621 (1A-1F) and 621(2A-2E).

619-5.01 BASIS OF PAYMENT.  Payment includes full compensation for loading, hauling, stockpiling, placing, materials, labor, tools, equipment, maintenance, and other materials, labor, equipment, tools, supplies, transportation, water, repair, and incidentals necessary to fulfill the requirements of the pay item in accordance with the Plans, the Specifications.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

619(3) 	Compost Blanket (2 Inch Depth)	Square Yard

SECTION 620

# TOPSOIL

Special Provisions

620-3.01 PLACING.  Delete paragraph in its entirety and substitute with the following:

Topsoil shall be evenly spread to a minimum depth of 24 inches after settlement on all areas to be established as planting beds for trees or shrubs as shown on the Plans or as directed by the Engineer.

An even finish grade for topsoil shall be established after compaction at the elevation shown on the Plans or as directed by the Engineer in the field.  Topsoil shall be placed only after excavation, rough grading, and other subgrade preparation has been completed and approved by the Engineer.

Topsoil shall not be placed in heavy rainfall, snowfall, when the soil is frozen or during other conditions detrimental to the work.  Contractor shall keep all roadway surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT.  Add the following:  Limestone, if required, will not be measured for payment, but will be subsidiary to Pay Item 620(1).

620-5.01 BASIS OF PAYMENT.  Replace Pay Item 620(1) with the following:

Pay Item No.	Pay Item	Pay Unit

620(1)	Topsoil (24 Inch Depth)	Square Yard

SECTION 621

- PLANTING TREES AND SHRUBS

- Special Provision

621-1.01 DESCRIPTION.  Delete this subsection in its entirety and substitute the following: This work shall consist of collecting, furnishing, planting, transplanting and maintaining Trees, Shrubs, and other plants on prepared areas as shown and scheduled on the Plans.

This work shall also include preparation of planting beds and pits including furnishing and installing shredded bark mulch, rock mulch, and Steel Landscape Edging as shown on the Plans.

Contractor shall preserve existing trees and vegetation on project parcel 22 as shown on the Plans.

Add the following subsection:

621-1.02 QUALIFICATIONS FOR LANDSCAPE CONTRACTOR.  The Contractor shall provide documentation which verifies the experience of the Landscape Contractor performing the work described in this section and maintaining landscaping projects comparable in scope, materials and diversity in three (3) construction projects and one (1) maintenance project within the last five (5) years prior to the bid date of this project.  This experience shall only include projects from cold climate states or provinces and three (3) shall be from South-central Alaska.  The Contractor shall demonstrate experience in landscape installation, tree and shrub planting and transplanting

Add the following subsection:

621-1.04 SUBMITTALS.  The Landscape Contractor performing the work shall meet the following minimum requirements and shall submit the necessary documentation to show compliance to the Engineer for review and approval:

- Project Experience:  Documentation shall be submitted with the Bid Proposal that lists three (3) construction and (1) maintenance projects completed by the Landscape Contractor under the same company name that are similar in scope, landscape materials, plant materials, methods of installation and maintenance to the project in the Plans and Specifications.  The list shall include at a minimum the dates, type, description and amount of work performed and the name and telephone number of a contact person at the agency or entity for which the work was performed.

- Personnel:  A list of proposed key personnel including the name of the superintendent and his assistant(s) who will direct the actual installation shall be submitted to the Engineer fourteen (14) days after Notice to Proceed. The list of personnel shall be accompanied with a resume from the superintendent and his assistant(s).  The superintendent shall be assigned full time to this project during installation.

The superintendent and his assistant shall have a minimum of five (5) years experience in directing landscape projects prior to the bid date of this project three (3) of which shall have been in Alaska.  The resumes shall include the following information and demonstrate compliance with any requirements requested:

- Number of years of continuous relevant experience in landscaping projects.  Significant projects shall be listed in the resume.

- Recent relevant landscaping, vegetation restoration,  including project description, date of work, individual’s role on the project, and one reference for each project.

The Engineer shall have the right to approve or reject the personnel based on the qualifications as submitted.  Upon approval, the Landscape Contractor, the superintendent and his assistant(s) shall be authorized to work on this project. The Engineer may suspend work if the Contractor substitutes unauthorized Landscape Contractor for authorized Landscape Contractor or unauthorized personnel for authorized personnel during construction without approval.  If work is suspended due to such substitutions the Contractor shall be fully liable for additional costs resulting from the suspension of work and no adjustments in Contract time resulting from suspension of work shall be allowed.

621-2.01 PLANT STOCK.  Delete this subsection in its entirety and substitute the following:  All plants shall be true to type and name in accordance with the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature, except that plant species which are scheduled, but not included in the current edition of Standardized Plant Names, shall be certified by a botanist.  Each bundle, flat, or plant if not bundled, shall be labeled with the scientific name.

Variety and species shall be as scheduled on the Plans.  All trees and shrubs shall be typical of the species or variety and shall, unless otherwise specified, conform to the American Standard for Nursery Stock (ANSI-Z 60.1-2004) of the American Association of Nurserymen (AAN) for type and grade.  Plant stock having severely damaged bark or trunks, broken leaders or main branches, severed main roots, or evidence of disease or injurious insects will be rejected.  Bare root trees and shrubs will also be rejected.

1.	Nursery Stock.

a.	Trees and shrubs furnished from a nursery shall have a fibrous compact root system suitable for the various species and sizes called for on the plans.

b.	Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

2.	Collected Stock.  These materials shall be plants growing under natural conditions in soils and in locations, which lend themselves to proper collecting practices.  The Contractor shall obtain any permits required for collection of plant stock from natural areas.  The root system of collected stock shall be larger than those specified for nursery grown material in accordance with ANSI-Z60.1-2004, Section 1.5.2, 2.4.8, 3.3.6 - Collected.

- Dormant Cuttings: Dormant willow cuttings will be harvested from live, woody plants in a dormant (not actively growing) state. Collect cuttings during winter/early spring before leaves appear, preferably before March 31, if they are to be used for spring and early summer planting. For fall plantings, collect cuttings in the late summer/ early fall after plants have gone dormant, the leaves have changed color or have dropped.

- Selection: Select cuttings with leaf buds near the top of each cut line. Select braches ¼ to 2 inches in diameter and at least 3 to 4 feet long. If necessary, branches can be cut to a shorter length at the time of installation. The potential for drying during storage is reduced when the cuttings are stored in longer pieces.

- Taking: Take cuttings directly from cold storage to the planting site. Only the plant material required for each day should be removed from storage, particularly if the weather is windy and/or warm. On site, the cuttings should be stored away from direct sunlight, heeled into moist soil, or stored in water until planting.

- Planting: plant the dormant cuttings as soon as the soil has thawed and no later than July 1; or plant in late summer/fall before the ground freezes. The ability of plantings to become established and resume growth the following spring declines quickly for plantings made after July 1. If the project is delayed and rescheduled for fall do not try to store the cuttings that were collected in the spring until fall.

3.	Balled and Burlapped Plants.

a.	The diameter and depths of balls on balled and burlapped Trees and Shrubs shall be in accordance with ANSI-Z60.1-2004.

- All balled and burlapped Trees and Shrubs shall be furnished with a firm ball of earth from the original and undisturbed soil in which the plant was growing.  The ball shall be wrapped with burlap or similar approved material and tightly laced to hold the ball firm and intact.  Any balled and burlapped designated plant material arriving at the planting site with broken or loose balls or of manufactured earth will be rejected.

- All plants found to be rootbound by the determination of the Engineer will be rejected.

- Substitutions.  No substitutions of plant stock will be permitted without written approval of the Engineer.  Request for substitutions for Trees and Shrubs shall be submitted in writing six (6) months prior to installation.

5.	Storage and Packing.  All plant material shall be handled and packed in accordance with good nursery practices as required by soil and climatic conditions.  Plants that show signs of improper storage or handling will be rejected.

6.	Inspection.

a.	All planting stock shall be available for inspection in the nursery or collection field before it is dug.  The contractor shall furnish complete and detailed information concerning the source of supply for each item of plant materials not less than 14 working days in advance of digging operations.

- Final inspection and acceptance for size of rootball, color, absence of defects, and for other requirements will be made at the planting site by the Engineer prior to placing the plants in their permanent positions.

- Plant material installed prior to acceptance by the Engineer will be removed, inspected and reinstalled if found unacceptable.

7.	Plant Quality

- Tree Trunk Specifications

Tree trunks shall be straight and well-tapered. Trees with multiple leaders, unless specified, will be rejected. Damaged, cut, or crooked leaders; included bark, bark abrasions, sunscald, disfiguring knots, mold, and prematurely opened buds, or cut limbs over three-quarter inch (3/4”) diameter that are not completely callused are cause for rejection.  Trunk diameter and taper shall be sufficient so that tree remains vertical without support.

- Crown Configuration Specification

Crown ratio (distance from bottom of canopy to tree top/tree height) should be at least sixty-six percent (66%) of total tree height.  One-half (1/2) or more of the foliage should be on branches originating on the lower two-thirds (2/3) of the trunk, and one-half (1/2) or less should originate on the upper one third (1/3).  Where formal arrangements of consecutive order of trees are shown; select stock for uniform height, structure, and spread.

- Branch Specifications

All branches shall be less than two thirds (2/3) the diameter of the trunk measured one inch (1”) above the branch.  The attachment of branches shall contain no bark inclusions.

There shall be one dominant leader straight to the top of the tree.  Larger branches shall be spaced at least six inches (6”) apart and arranged radially and vertically along the stem.  There shall be live buds or foliage to the ends of all twigs.  All pruning cuts shall comply with ANSI A300 Standards and shall be made outside the branch collar and branch bark ridge. Branches shall not be pruned immediately prior to delivery. Needled evergreens shall not have been sheared.

- Root Flare and Root Ball Specifications

No root in the root ball larger than one-quarter inch (1/4”) diameter shall circle more than one-third around the root ball. There shall be no roots in the root ball that make an abrupt turn of ninety degrees (90°) or more. There shall be no roots in the root ball that are ‘J’ roots, kinked, stem girdling, or potentially stem girdling. For all plants, including bare root, roots shall exhibit healthy, well-branched root systems characteristic of the species with adequate spread.

Roots in ball-in-burlap root balls or in containers shall be well-rooted and uniform throughout soil mix or growth media. Roots shall not be pot bound.

Major roots shall be less than two inches (2”) from the top of root flare. The root flare (trunk flare, root collar) shall be at the surface of the root ball (container media). As defined by ANSI Z60.1, root ball depth measurement is from the top of the ball, which in all cases shall begin at the root flare. Soil above the root flare shall not be included in ball depth measurement and should be removed.

Root ball size shall meet ANSI Z60.1.

Nursery Stock root balls shall be of sufficient depth to include absorbing roots. Balls shall be securely wrapped in burlap and tightly bound with rope or twine. Trees may be wire baskets lined with burlap and tightly bound with rope or twine. Balled-in-burlap plants with manufactured balls or container plants that are dry, cracked, or broken before the plant operation will be rejected.  The Engineer reserves the right to inspect root system of trees and shrubs and to reject any material found to be non-compliant.

8.	Size and Grading Standards

Plants shall have a standard balance between height, crown spread, diameter and root ball size according to the ANSI Z60.1. All plants shall be typical of their species or variety.

Plants shall conform to the measurements specified except that plants larger than those specified may be used, if approved by the Engineer. If larger plants are approved, the root ball, root spread, or container shall be increased in proportion of the size of the plant.

Caliper measurements shall be taken six inches (6”) above the trunk flare for trees up to four inches (4”) in caliper, and 12 inches (12”) above the trunk flare for trees over four inches (4”) in caliper. Plants shall be measured when branches are in their normal position. If a range of size is given, no plant shall be less than the minimum size, and no less than fifty percent (50%) of the plants shall be as large as the maximum size specified. Plants that meet measurements but do not possess a normal balance between height and spread shall be rejected.

Plants shall not be altered by pruning or other means to meet specifications.

621-2.02 FERTILIZER.  Add the following: Fertilizer shall be delivered in moisture-proof containers marked with weight and manufacturer’s guaranteed analysis showing proportions of the chemical ingredients of nitrogen, phosphoric acid, and potassium within a tolerance of +/- 2 percent. A slow release fertilizer 8-32-16 (N-P-K) shall be used with all Trees, Shrubs, early in the first full growing season following installation.  Fertilizer shall be applied at a rate determined by the Engineer, as described in Section 726, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.    The fertilizer tablets shall be placed near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.

621-2.03 LIMESTONE. Add the following: Limestone shall be applied at a rate determined by the Engineer, as described in Section 726, in Table 726-1, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

621-2.06 STAKES.  Add the following:  Stakes shall be installed as shown on Plans.

621-2.07 TREE WOUND DRESSING.  Delete this subsection in its entirety.

Add the following subsection:

621-2.08 STEEL LANDSCAPE EDGING.  Steel landscape edging shall be obtained from one of the following manufacturers or approved equal:

Sure-Loc Edging Corporation	COL-MET	Border Concepts

494 East 64th Street	3333 Miller Park South	P.O. Box 471185

Holland, MI 49423	Garland, TX 75042	Charlotte, NC 28247

(800) 787-3562	(800) 829-8225	(704) 541-5509

www.surelocedging.com	www.colmet.com	www.borderconcepts.com

The steel edging shall be black in color, 4” in depth, and 3/16” thickness with 12” standard steel stakes.

621-2.09 TEMPORARY PROTECTION FOR PLANT MATERIAL.  Contractor shall apply approved spray-applied moose repellent for seasonal protection of plant material against moose browse damage.

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Areas which receive group plantings shall be laid out as shown on Plans.  Contractor shall mark these areas individually with flags, or other approved methods to delineate between planting areas.  Engineer shall approve the shape, size, location and general layout of planting areas before the work may proceed.

Contractor shall stake or mark with other approved methods the location of individual trees within each planting area for approval by the Engineer, before planting.

621-3.03 PLANTING.  Delete Items 1 and 2 and substitute the following:

1.	Plant Season.

a.	Locally grown:  Locally grown native species of trees and shrubs shall be planted between June 1 and September 15.  Trees and shrubs shall be fully leafed out prior to planting.

b.	Imported: Imported nursery grown plants shall be handled in accordance with nursery recommendations.  Plants imported from out of state shall be planted between May 15 and August 1.

c.	Live Stake: Install dormant cuttings (see section 621-2.01) directly into the ground. Prepare several live stakes from one dormant cutting. Cut stakes 10-24 inches long, ¼ to ½ inches in diameter. Water stakes deeply during the first six weeks after planting. Use a drain spade shovel to create a pocket to receive live stakes. Tightly pack topsoil around stake so no air pockets remain. Plant stakes upright 1 to 3 feet on center. Stakes should be planted as vertically as possible, placing at least ¾ of the stake below ground so that only one or two leaf buds are left exposed above the ground. If more than one or two buds, ¼ of the stake, or 4 inches of the live stake is extending above the soil surface, trim the stake.

2.	Excavation.

a.	Topsoil shall be kept separate from subsoil and shall be rendered loose and friable.  Any material detrimental to plant growth shall be separated and disposed at approved locations.

b.	Planting pits for trees and shrubs shall be in accordance with the details shown on the Plans.

Delete paragraphs (c.) and (d.)

- Pruning.  Delete paragraph b in its entirety and replace with the following:

b.	Branches.  Pruning shall conform to the American Standard for Tree Care Operation, ANSI A300.  No pruning paint or other wound dressing shall be used.

- Transplanting.  Add the following:

Transplanting of existing trees shall include healthy plant material from areas to be demolished.  The plant material shall be healed-in in the temporary nursery and replanted at locations shown on Plans as the project progresses.

  - Transplanting shall provide for the number and type of plants shown on Plans as part of the landscape installation.  Contractor shall mark the individual trees and shrubs to be transplanted for approval by the Engineer.

  - In case the Contractor can’t provide the required number of transplanted plants in acceptable condition at the time of replanting the Engineer shall allow a substitution of maximum 15% of the total amount of each type.  The substitution shall be new plant material of the same species in the largest size specified for the project.

- Placing Plants.

Add the following to paragraph a.:  Trees and Shrubs shall be planted as shown on the Plans and as directed on site by the Engineer. Tree and shrub locations shall be marked with stakes and approved by landscape architect before planting occurs.

Delete paragraph b and substitute the following: Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the plant itself.  Wire baskets shall be removed, and burlap shall be clipped and laid flat on the bottom of the planting pit as indicated on the Plans.  Containers shall be removed from the plant and the site.  The Engineer may reject any plants whose rootballs collapse during planting. This is a sensitive site and no heavy motorized equipment, such as a bobcat or track hoe may be used to transport plant material to planting location. Compaction is to be kept to a minimum. Therefore plant material shall be put in place manually without the use of motorized equipment.

- Backfilling.  Delete in its entirety and substitute the following:

Hold plants upright during the backfilling operation.  Backfill around the roots and lightly compact the soil to eliminate air pockets.  Avoid damaging roots.  When the backfilling is 1/3 complete, wire baskets and burlap shall be clipped from around the root ball and removed.  The engineer may reject any plants where root balls collapse during planting.  Add water while placing backfill, allowing the soil to soak up the water.  When backfilling is complete, build an earth berm approximately 3 inches high around the outer edge of the planting area to facilitate watering.  Remove berm after one growing season.

7.	Wrapping.  Delete this paragraph in its entirety.

- Staking and Guying.  Delete in its entirety.

Do not use wire for staking or guying.  Stake trees as required by engineer and wind conditions.  Use at least two 2x2 wooden stakes driven approximately three feet into the ground outside of root ball.  Tie trees securely to stakes at one third of tree height with broad ties of soft flexible material.  Do not use wire or cable.  Cut off stakes four inches above the tie.  Remove the ties after one full growing season.

Add the following:

9.	Certified Arborist.  The Contractor shall retain the services of an arborist certified by the International Society of Arboriculture or the American Association of Nurserymen whose experience and qualifications are acceptable to the Engineer.  The arborist’s resume shall be submitted at least 10 calendar days before the delivery of plant material.  The certified arborist shall oversee quality assurance of trees, their installation and shall inspect trees for health and vigor.  Specifically, the arborist shall be responsible to carry out the following:

The certified arborist shall inspect plants for health and vigor prior to installation, to assure the requirements of Section 621-2.01 for plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected prior to installation.  The certified arborist shall also be responsible for the following:

  - Inspect the tree planting process to assure that planting techniques meet the specifications of the Contract documents and match standard industry practices.

  - Inspect the plantings after installation is complete to assure that they are ready to be accepted by the Engineer.

c.	Inspect plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.

621-3.04 PERIOD OF ESTABLISHMENT.  Delete the first sentence and substitute the following:  Period of establishment shall extend for two (2) full growing seasons after acceptance of all work described in this section and under Sections 618 and 620.

One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract.  The work under Section 621 will only be accepted as fully complete for period of establishment requirement purposes, no partial acceptance will be given.  The two (2) full growing season period of establishment starts on May 1st after the acceptance of the work as complete.  Partial growing seasons will not be counted against the one full growing season requirement.

Standard Modifications

Add the following:

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance according to Subsection 105-1.16.

E43(01/27/07)

621-3.05 CLEANUP.  Add the following: Planted Trees, Shrubs, shall be kept clean of litter and garbage.

621-3.06 PLANT REPLACEMENTS.  Delete the last sentence and substitute the following:  Plants shall be replaced following the same details and specifications as used in the original plans. Plants which are dead or dying shall be replaced immediately during the months of June through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

621-3.07 MAINTENANCE.  Delete the paragraph and substitute with the following:  Maintenance includes the care of all Trees and Shrubs during the period of establishment, including the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of planted areas.  At the beginning and end of each growing season, the Engineer and Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of plantings.

1.	Watering. The Contractor shall water all trees and shrubs to maintain the plants in a healthy, vigorous growing condition.  The root zone of plants shall be kept moist at all times.

2.	Disease Control. The Contractor shall apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained prior to the application of any regulated products.

3.	Pruning.   Pruning shall only be conducted for repair or as specified by the Engineer.  Pruning shall conform to ANSI A300 Standards and shall be done under the supervision of a certified arborist.  Dead, broken, or damaged branches may be pruned at any time.  Pruning for form shall begin no sooner than two years after installation.  No tree shall be topped.  Any tree damaged by improper pruning shall be replaced by the Contractor.

4.	Fertilizing.  Trees and Shrubs shall receive an application of fertilizer in accordance with Section 621-2.02 Fertilizer.  The application shall occur between May 15 and June 15 of each growing season following planting.  The fertilizer tablets shall be placed near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.  The Contractor shall notify the Engineer in writing 4 working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

5.	Weeding.  The Contractor shall maintain all areas in a weed-free condition.  Weed removal shall be a routine maintenance activity.  Chemical application must be in compliance with State of Alaska rules and regulations.

TABLE 621-1
MAINTENANCE FERTILIZER SCHEDULE

Plant Type	Fertilizer	Application Rate

Coniferous Trees	8-32-16	1/3 lb for each 1 inch of Caliper

Deciduous Trees	8-32-16	1/3 lb for each 1 inch of Caliper

Shrubs and Ground Cover	8-32-16		7 lbs per 1,000 square feet.

Add the following subsection:

621-3.08 PROTECTIVE FENCE.  The placement of protective fence shall occur after the trees have been installed.  The protective fence shall be routed at the outside edges of tree planting areas as shown on the Plans.  Minor modifications and adjustments to layout and post spacing shall be made to better fit the site conditions.  All protected trees shall be enclosed in such a manner that the fabric will not damage the branches and will not allow branches to protrude.

Fence shall be erected at the end of the growing season no later than October 5th.  They shall remain in place until the next growing season and shall be removed no later than May 10th.  Contractor shall be responsible for erecting and removing the protective fence during the period of establishment as described under 621-3.04, Period of Establishment.

Contractor shall conduct periodic visual inspections and repair immediately any damage due to moose, other wildlife, or vandalism.

Contractor shall erect the protective fence at the end of the final growing season of the period of establishment and leave it in place for Owner to assume maintenance from that point.

Protective fence shall be fabricated of the mesh and posts specified on the Creekbank Revegetation sheets on the plans.

621-3.09 TEMPORARY PROTECTION FOR PLANT MATERIAL.  Apply approved moose repellent after the trees have been installed.

Spray repellent at the end of the growing season no later than October 5.  Continue spray maintenance until the next growing season.

Conduct periodic visual inspections and re-spray immediately if damage due to moose, other wildlife, or vandalism occurs.

621-4.01 METHOD OF MEASUREMENT.  Delete this entire subsection and substitute the following: Measurement of new or transplanted Trees and Shrubs , Pay Items 621(1A-1F) and 621(2A-2E), shall be by the actual number planted and maintained in accordance with the Plans and Specifications, and as accepted by the Engineer.

Furnishing and installing shredded bark mulch, additional topsoil backfill mix, fertilizing, temporary fence, steel landscape edging, disposal of unsuitable and surplus material, water for maintenance used and all work required during the two full growing season period of establishment shall not be paid for separately, but shall be subsidiary to Pay Items 621(1A-1F) and 621(2A-2E).

Transportation, excavation, equipment and labor for placement shall not be measured separately, but shall be subsidiary to Pay Items 621.

Moose repellent is subsidiary to the 621 pay items.

Removal of dead vegetation, protective fence, topsoil (24” depth), picea mariana trees, balsam poplar trees, alnus tenuifolia shrubs, and salix alaxensis shrubs are subsidiary to Pay Item 621(9) Creekbank Revegetation.  The rosa acicularis shrubs that are south of the protective fence are subsidiary to Pay Item 621(9) Creekbank Revegetation.

621-5.01 BASIS OF PAYMENT.  Delete second sentence.  Add the following:   Partial payments of up to 80% of full amount may be authorized for Items 621(1A-1F) and 621(2A-2E) at the time of acceptance. The balance shall be paid during the period of establishment with one final payment of minimum 10% of the full amount paid at the completion of the period of establishment.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

621(1A)		Tree, Picea Glauca ‘Densata’ – 6’ Ht.	Each

621(1B)		Tree, Larix Siberica – 6’ Ht.	Each

621(1C)	Tree, Prunus Maackii – 2” Cal.	Each

621(1D)	Tree, Betula Papyrifera, Single-Stem – 2.5” Cal.	Each

621(1E)	Tree, Prunus Virginiana ‘Canada Red’ – 2” Cal.	Each

621(1F)	Tree, Populus Tremuloides – 2” Cal.	Each

621(2A)	Shrub, Rosa Acicularis	Each

621(2B)	Shrub, Potentilla Fruticosa ‘Goldfinger’	Each

621(2C)	Shrub, Cornus Sericea	Each

621(2D)	Shrub, Viburnum Edule	Each

621(2E)	Shrub, Picea Pungens ‘Glauca Globosa’	Each

621(5)	Edging, 4” Steel Landscaping	Linear Foot

621(9)	Creekbank Revegetation	Lump Sum

SECTION 626

SANITARY SEWER SYSTEM

Special Provisions

626-1.01 DESCRIPTION. Add the following: For the purposes of these Special Provisions, "AWWU" shall mean the Anchorage Water and Wastewater Utility, Engineering Division at (907) 564-2774. This work shall include the installation and testing of sanitary sewer systems for acceptance by AWWU.  The Contractor shall also provide record drawings in accordance with the conditions prescribed herein.

Project Parcel 17 Sewer Service Connection pay item is for new service at Station “WDR” 30+93.76

Contact Chugach Electric Association to coordinate shoring of utility/light pole at the northwest end of Franklin Drive, adjacent to Cordova Street, prior to working near the pole.

626-2.01 MATERIALS. Add the following:

Unless otherwise indicated on the drawings all materials used in the manufacture of pipe, fittings, and accessories shall conform to the governing standards.

626-3.01 CONSTRUCTION REQUIREMENTS. Add the following: Contact the AWWU in writing a minimum of three (3) working days in advance of beginning construction to schedule a pre-inspection of the sanitary sewer and a post inspection after paving operations are complete. Provide AWWU a copy of the written notice. Contractor shall be responsible for furnishing all the required traffic control and personnel to assist AWWU while locating and performing the pre-construction and post-construction inspections. Contractor forfeits all rights to deny damages done by Contractor or Contractor’s agents during the course of work if Contractor fails to participate in this inspection.

Sanitary sewer manhole covers identified as worn in the pre-inspection shall be replaced with new covers provided by AWWU.  Coordinate with the AWWU to obtain replacement covers from the AWWU warehouse.

Trench Shoring

The Contractor shall obtain approval from the Engineer for all sheeting, bracing, and shoring materials and/or equipment to be used on the project.  Materials used shall be in accordance with Section 1926.651, Subparagraph 1 of the Federal Register, Volume 37, No. 243, page 27553, OSHA Regs., December 1972.

All construction requirements for design, installation, and use of sheeting, shoring, bracing, and shielding shall be in accordance with current safety regulations.  All sheeting, shoring, bracing, and shielding shall be designed by a Professional Engineer registered in the State of Alaska, hired by the Contractor.  All working drawings and design data shall be submitted to the Engineer for approval.

When shoring and sheeting is left in the trench, sheeting must be driven lower than the bottom of the pipe and cut off on (1) foot below road structural fill.  No traverse bracing will be permitted to remain.

No bracing requiring driven or vibratory installation methods shall be used on this Project. Any Contractor provided portable trench shielding shall comply with relevant OSHA regulations. The Contractor shall provide the Engineer certification of such compliance from the portable shield manufacturer or supplier.

Add the following to the second paragraph:  The Contractor shall remove and dispose of all sewage saturated soils encountered within the trench area.  All sewage-saturated soils shall be considered unsuitable material. Sewage saturated soils may not be used as fill material anywhere within the Municipality and shall be disposed of at the Municipal Landfill. There shall be no separate payment for removal and disposal of sewage saturated soils. Removal and disposal of sewage saturated soils shall be considered incidental to the pay item for the pipe.

Delete the words "or flexible connection" from the third paragraph.

Add the following to the fourth paragraph:  Both line and grade shall be checked and recorded in a field book for each piece of pipe laid, except at tunnels where methods acceptable to the Engineer shall be used to carry forward line and grade.

PVC pipe shall be installed in accordance with AWWA M23 “PVC Pipe - Design and Installation (M23)”, latest edition, and the manufacturer’s requirements.

Delete the fifth paragraph and substitute the following:  When installing new sewer conduit, including grouting and assemblage of fittings, the Contractor shall take every precaution to preclude foreign debris from entering the sanitary sewer system. All temporary screening techniques of the downstream manholes shall be provided by the Contractor and approved by the Engineer. Contractor shall be responsible for removing and cleaning any foreign debris that may have entered the sanitary sewer system, and all costs associated shall be incidental to the Contract.

For PVC pipe connection to exiting sewer main, use ROMAC 501 couplings, or approved equal.

Pipe shall not be laid when the bottom of the ditch or the sides to one foot above the pipe is frozen. Backfill material shall not contain frozen material.  The trench shall not be left open during freezing weather so that the temperature of the material near the pipe goes below freezing.

Cordova Street Extension project

Bedding material for PVC pipe shall be as specified in Section 204.

West Dowling Road project

Bedding material shall be Select Material, Type A.

Delete the seventh paragraph and substitute the following: Installation shall be in accordance with these specifications and current AWWU Design and Construction Practices Manual.

The Contractor shall stagger the joints for the sanitary sewer conduit such that no joint shall be closer than 10 feet from the centerline crossing of the water and sewer conduits. In addition, the vertical separation between the water and sewer conduits shall be 18 inches minimum, outside of pipe to outside of pipe.

Suspension of Work. AWWU, through the Engineer, reserves the right to suspend the sanitary sewer installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle the Contractor to extra payment for costs incurred.

Interruption of Sewer Service.  Contractor shall provide for continuous sewer service.  If an outage is required, the Contractor shall notify affected customers seven (7) days in advance of the scheduled suspension of service. A temporary sewer service connection shall be provided by the Contractor to provide sewer service in the event of an outage longer than 4 hours. For emergency suspension of service, the Contractor shall provide such notice as is reasonably practicable under the circumstances.  The notification provided shall be done by knocking and leaving a door hanger at each premise notifying the customer of the date and times the suspension of service will be in effect.

Polyethylene Wrapping of Sanitary Sewer Conduit. The outside of all ductile iron and cast iron pipe, fittings and other appurtenances used in sewer conduit construction shall be encased with one (1) layer of 8-mil thick (0.2 mm) polyethylene film.  The polyethylene encasement shall be installed using the following method:

Method

- Cut polyethylene tube to a length approximately 2-feet longer than the length of the pipe section. Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

- Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

- After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube. Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place. Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

- Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

Verification of Existing Utilities. At a sufficient distance prior to encountering a known utility crossing, buried obstacle, pipe, or tying into an existing manhole or sewer pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe inverts so proper alignment and grade may be determined before the pipe sections are laid in the trench and backfilled.

The cost incurred for removal and realignment of backfilled pipe sections due to improper verification methods shall be borne by the Contractor.

626-3.02 TESTING. Delete in its entirety and substitute the following: The Contractor shall install clean sanitary sewer pipe prior to testing and final inspection.  The Contractor shall notify the Engineer 72 hours in advance of any test.  The Engineer and AWWU shall be present during all tests.  Two hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or cancelled.

The Contractor shall furnish all tools, equipment, and labor necessary to complete the tests and shall verify from their own observations, or preliminary tests, that each line conforms to this specification before requesting AWWU to observe and record the actual leakage.

All sanitary sewer pipe installed shall be subject to either an infiltration test or an exfiltration test.  In those areas where, in the opinion of AWWU, the water table is high enough to subject the pipe to a satisfactory infiltration test, it is not anticipated that an exfiltration test shall be required.  In checking leakage, there will be no allowance made for external hydrostatic head.  Where in the opinion of AWWU the water table is not high enough to provide a satisfactory infiltration test, an exfiltration test shall be required.

The type of test, either infiltration or exfiltration, shall be determined by AWWU. The Contractor shall have the option of choosing only one method (air or water) of testing for each section tested. All testing shall be considered a subsidiary obligation under this Contract and no extra payment will be allowed for this portion of work.

All wyes, tees, or ends of side sewer stubs and service connections shall be plugged or capped and the plug or cap shall be securely fastened to withstand the internal test pressures. Such plugs or caps shall be readily removable and their removal shall provide a socket suitable for extending the lateral connection.

Infiltration Test. Infiltration testing may be allowed at AWWU's option when the natural ground water table is 6-feet above the crown of the higher end of the test section. The maximum allowable limit for infiltration shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

The Engineer may require the Contractor to repair obvious leaks even though the total length of the test section falls within the maximum allowable leakage of the test used.

Exfiltration Test (Using Water). On completion of a section of sanitary sewer between manholes, or otherwise, the ends of all pipe shall be plugged, including service connections, and the pipe subjected to hydrostatic pressure.  All testing is to be conducted after backfilling, prior to resurfacing, and after service connections are made.

A minimum head of 6-feet of water above the crown at the upper end of the test section shall be maintained for a period of 4 hours, during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of 1 hour for the actual test of leakage.  During this 1-hour period the measured loss shall not exceed the rate of 50 gallons per inch diameter per mile per 24 hours.

The above listed leakage rate shall also be applied to infiltration of ground water and infiltration or exfiltration in greater amounts will be cause for rejection of the sanitary sewer and all repairs necessary to meet these requirements and retesting shall be at the expense of the Contractor.

The maximum length of sanitary sewer for the above allowable leakage test shall be one thousand feet (1000’).  If it is not apparent that the leakage test results between any two manholes is satisfactory, then the Engineer may require subsequent tests to establish the more exact location of the leakage areas.  Any section of sanitary sewer between any two manholes that does not meet the above requirements shall be rejected and the Contractor, at his expense, shall make the necessary repairs to the sanitary sewer to meet the requirements, and shall make subsequent tests after repairs to assure compliance with the Specifications.

Exfiltration Test (Using Air).  The Contractor shall furnish all facilities and personnel for conducting the test under the observation of AWWU.  The equipment and personnel shall be subject to the approval of the Engineer.  The Contractor may desire to make an air test prior to backfilling for the Contractor’s own purpose. However, the acceptance air test shall be made after backfilling has been completed, and compacted.

Immediately following the pipe cleaning, the pipe installation shall be tested with low pressure air.  Air shall be slowly supplied to the plugged pipe installation until the internal air pressure reaches 4.0 pounds per square inch greater than the greatest back pressure of any ground water in contact with the pipe.  At least 2 minutes shall be allowed for temperature stabilization before proceeding further.

The pipe shall be considered acceptable when tested at an average pressure of 4.0 psi greater than the greatest back pressure of any ground water in contact with the pipe, if:

The total rate of air loss from any section tested in its entirety between manholes or between manhole and cleanout structures does not exceed 2.0 cubic feet per minute.  The following table may be used as a guideline for a satisfactory test by air for pipe sizes shown:

| Pipe Diameter | Allowable Pressure Drop in 10 Minutes |
| --- | --- |
| 8 inches | 2.7 psi |
| 10 inches | 2.1 psi |
| 12 inches | 1.8 psi |
| 16 inches | 1.4 psi |
| 18 inches | 1.2 psi |
| 24 inches | 0.9 psi |
| 48 inches | 0.5 psi |

Pressure gauges shall be marked in not more than ½ pound increments for accurate tests.

Safety braces shall be required to hold plugs in place and to prevent the sudden release of the compressed air.  Due to the large forces exerted by an escaping plug during the testing of the pipe, workmen shall not be allowed in the manholes in which plugs have been placed while tests are being conducted.  The Contractor’s testing equipment shall be arranged in such a manner that a pressure relief device will prohibit the pressure in the pipe from exceeding 10 psi.

If the pipe installation fails to meet test requirements, the Contractor shall determine at their own expense the source of leakage, and he shall repair (if the extent and type of repairs proposed by the Contractor are acceptable to the Engineer) or replace all defective materials or workmanship.  The completed pipe installation shall meet the requirements of this Section before being considered acceptable.

Check of Line and Grade. After backfilling and cleaning, but before final acceptance, all sections of installed sanitary sewer lines may be checked for line and grade. Excluding service connections, all size sanitary sewer mains 30 inches in diameter and smaller may be checked for line and grade by closed circuit television.  A full circle of light must be seen and no pipe misplaced in line or grade. Any excess deviation in line and grade shall be corrected by the Contractor, at their expense, prior to final acceptance of the pipe line.

Final Inspection. The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project.  This inspection will be performed in the presence of the Engineer, AWWU and the Contractor. A punch list of deficiencies found during the inspection will be furnished to the Contractor by the Engineer for remedial action. The Contractor shall notify the Engineer when all corrective action has been completed. Then a final acceptance inspection will be performed.

The Contractor shall take precautions to allow no sewage to enter the new sewer conduit until it has been inspected, tested, and accepted for operation and maintenance by AWWU.  Any deviations shall require written approval.  The new sewer line may be tested and inspected in incremental runs.

626-3.03 AS-BUILT DRAWINGS AND RECORD DOCUMENTS.  Add the following subsection: The Contractor shall maintain record documents on the job site consisting of a complete set of plans, survey line and grade books, and other contract documents, and keep them current on a daily basis.  Record documents shall be available to the Engineer at all times.  The Engineer may periodically review the status of the record documents during the course of the work.  Failure to keep the record documents current and in the required condition will be considered cause for withholding progress payments.

The Contractor shall prepare as-built drawings as the work progresses and final record drawings as described below.  Acceptable as-built drawings will be prepared on copies of the project construction drawings to depict all lines, grades, locations, materials, and other elements of the work as actually constructed with clearly marked final elevations and locations with actual dimensions.  Noted stations, elevations, slopes and other design dimensions shall be shown on the construction drawings with “ASB” if no change occurs in the field.

The Contractor shall survey the work and all utilities and obstructions encountered during construction in a manner producing an accuracy of 0.03 feet vertically and 0.5 feet horizontally, and reference that as-built information to both project survey control and to pipe stationing.

The Contractor shall submit as-built drawings to the Engineer for review each month, providing five (5) working days to review and approve the information, or to return the drawings for additional information.  The Engineer and AWWU will review all Record Documents for completeness and conformance to standards.  The Contractor shall make all corrections, changes, additions, and deletions required by the Engineer.

The Contractor shall prepare final record drawings on a clean set of full-sized construction plans at the completion of sewer construction as follows:

- Note the name of the person who prepared the record drawings, the Contractor, and the date of preparation in the appropriate title block on each record drawing sheet.

- Make all additions and collections neat, clean, and legible in red ink or red pencil to clearly describe the work as actually constructed.  Identify any and all changes to the original design.  If additional plan sheets are required, prepare them on reproducible mylar-type material and sized as the original plans.

- Complete the revisions in conformance with the scale of the drawings.

- Show each change, deletion, or omission with the appropriate entries and symbols.  Draw one straight line through stationing, elevations, and/or notes. Crossed out information must remain legible.  For every entry on the construction drawings that was not changed in the field, mark “ASB” next to that entry.

- Cross-hatch any deleted or relocated sanitary sewer.

- Note reference information used to prepare record drawings, such as change orders and field books.

- Make profile changes with new elevations or stationing entries only, unless the change is significant.  If the change exceeds 1.5 feet, cross-hatch the original pipe and redraw the profile line.

- Provide complete information for all sanitary sewer service connects that are reconnected or constructed.  If the service is reconnected, record the size and material of the service and the pipe station at the main.  If the service is newly constructed, provide horizontal and vertical locations at the property or lease lot line, including swing ties and offsets to property or lease lot corners. Include two or more swing ties from prominent, permanent features to show the location of each installed sanitary sewer service connection on the final record drawings.  Swing ties are to be as close to perpendicular to each other as possible.  Where property lot corners are in place, use them as swing tie reference points.

- Provide complete tables for each sanitary sewer service connect showing the material and size of the service pipe, pipe stationing of the service at the main and the location and elevation of each service at the property line.

The Contractor shall clearly stamp the as-built drawings “Record Drawings”, and submit them to the Engineer for approval by AWWU. Approved final Record Documents, bearing certification by the Contractor that the Record Documents are a complete and accurate representation of the project as constructed must be delivered to the Engineer within thirty (30) days of Substantial Completion of sewer construction.

Add the following subsection:

626-3.04  DISCONNECT/RECONNECT SANITARY SEWER SERVICE

For all current AWWU customers affected by the new sewer main, the Contractor shall disconnect the existing sewer service from the old main and reconnect it to the new main using new service materials.  This work includes disconnecting the existing sewer services at the main and reconnecting the existing sewer services to the new main.  The Contractor shall provide all necessary fittings, adapters, pipe, and other appurtenances to make a complete functioning system.

The Contractor shall notify the Engineer and the property owner seventy-two (72) hours prior to any interruption of sewer service.  The Contractor shall provide temporary service during the period of interruption.  This temporary service is subsidiary to the disconnect/reconnect pay item.

The actual location, type, and size of the existing sewer service may vary from that shown on the Plans.  The Contractor shall use whatever reasonable means or methods necessary to determine the actual location of the sewer service prior to beginning excavation.  All information provided in the Plans and Specifications has been obtained from maintenance records, record drawings, C.C.T.V., or field survey, and represents AWWU's best indication of the services location, type, and size.

The disconnection, new service materials, and reconnection of the existing sanitary sewer service shall be in accordance with this specification and the most recent version of the AWWU Design and Construction Practices Manual.

The removal and disposal of existing service piping and connection appurtenances encountered in the excavation will be subsidiary to the disconnect/reconnect pay item.

All ductile iron pipe and/or cast iron pipe shall be encased in one (1) layer of polyethylene encasement in accordance with Subsection 626-3.01 CONSTRUCTION REQUIREMENTS.

All surface areas disturbed or damaged by the installation of sewer service lines or other related construction activities of the Contractor shall be restored to their original condition.  The Contractor shall replace surfacing or cover material with new material in kind.

Any manmade objects or improvements that conflict with the installation of the service lines shall be carefully removed by the Contractor and replaced in their original condition and at their original location at the completion of the work.  The restorations of manmade objects or improvements for a given lot, including landscaping, will be subsidiary to the disconnect/reconnect pay item.  Compaction of the sewer service trench will be subsidiary to the disconnect/reconnect pay item.

626-3.05 DISCONNECT SANITARY SEWER SERVICE

Disconnect sanitary sewer services at the main.  Pipe disconnected from the main with a diameter of 4 inches or greater shall be filled with slurry where pipe is beneath the road structural section.  Method of slurry is to place one foot of concrete at the beginning of the pipe, calculate the total internal volume of the pipe, fill the pipe with slurry equal to the total calculated volume, and place one foot of concrete at the end of the pipe.  Slurry shall consist of a mixture of water and sand with an approximate ratio of seven gallons of water per cubic foot of sand.  The total lineal footage of pipe filled with slurry shall be shown on the record drawings.

626-3.06 REPLACE SANITARY SEWER SERVICE PIPE

This work includes disconnecting the existing sewer service and replacing the existing pipe as shown on the Plans.  The Contractor shall provide all necessary fittings, adapters, pipe, and other appurtenances to make a complete functioning system.

The Contractor shall notify the Engineer and the property owner seventy-two (72) hours prior to any interruption of sewer service.  The Contractor shall provide temporary service during the period of interruption.  This temporary service is subsidiary to the replace sanitary sewer service pipe pay item.

The actual location, type, and size of the existing sewer service may vary from that shown on the Plans.  The Contractor shall use whatever reasonable means or methods necessary to determine the actual location of the sewer service prior to beginning excavation.  All information provided represents AWWU's best indication of the service location, type, and size.

The replacement of sanitary sewer service shall be in accordance with this specification and the most recent version of the AWWU Design and Construction Practices Manual.

The removal and disposal of existing service piping and connection appurtenances encountered in the excavation will be subsidiary to the replace sanitary sewer service pay item.

All cast iron pipe and/or ductile iron pipe shall be encased in one (1) layer of polyethylene encasement in accordance with Subsection 626-3.01 CONSTRUCTION REQUIREMENTS.

All surface areas disturbed or damaged by the installation of sewer service lines or other related construction activities of the Contractor shall be restored to their original condition.  The Contractor shall replace surfacing or cover material with new material in kind.

Any manmade objects or improvements that conflict with the service line shall be carefully removed by the Contractor and replaced in their original condition and at their original location at the completion of the work.  The restoration of manmade objects or improvements and compaction of the sewer service trench shall be subsidiary.

626-4.01 METHOD OF MEASUREMENT.  Add the following:  Remove and dispose of unusable pipe and fittings.  Disposal shall be subsidiary to 626 pay items.

Project Parcel 17 Sewer Service Connection.  Lump sum price to provide labor, excavation, and materials (excluding sanitary sewer manholes) to install a new sanitary sewer service connection as shown on the Plans.

Disconnect Sanitary Sewer Service.  Each sanitary sewer service disconnect shall be measured by each service disconnected.  Slurry of pipe beneath road structural section shall be subsidiary.

Disconnect/Reconnect Sanitary Sewer Service.  Each sanitary sewer service disconnect/reconnect shall be measured as a completed unit in place.  Measurement for disconnection and reconnection of sanitary sewer services shall be for each service.

Replace Sanitary Sewer Service Pipe.  By the linear foot of sanitary sewer service replaced.

626-5.01 BASIS OF PAYMENT. Delete the second paragraph and substitute the following: The unit bid prices will include shoring.  Unclassified Excavation and Backfill are paid under Section 203.  Bedding and Foundation Material is paid under Section 204.

No separate payment will be made for couplings, adjustment of existing sewer cleanouts, providing pumping of effluent during construction, mechanical plugs, encasing the sewer conduit in polyethylene wrap, lowering water service pipes smaller than 2 inches, shoring, mechanical compaction, abandoning in place existing sanitary sewer lines or appurtenances designated on the plans or as directed by the Engineer, and all restoration work associated with the installation of sewer services. These items will be subsidiary to the sewer conduit.

Payment for pay item 626(10) will be withheld until such time that record drawings are approved by AWWU and Contractor signs final record drawings.

Payment for sewer manholes will be made under Section 604.

Dewatering shall be subsidiary to the 626 pay items.

Payment for coordinating and/or shoring utility/light pole at the northwest end of Franklin Drive, adjacent to Cordova Street, shall be subsidiary to the 626 pay items.

Disconnection of sanitary sewer service on the Cordova Street Extension S Sheets shall be subsidiary to the 626 pay items.

Add the following pay items:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 626(1A) | 8 Inch PVC Sanitary Sewer Conduit, SDR 18 | Linear Foot |
| 626(1B) | 12 Inch PVC Sanitary Sewer Conduit, SDR 18 | Linear Foot |
| 626(2A) | Project Parcel 17 Sewer Service Connection | Lump Sum |
| 626(3) | Disconnect Sanitary Sewer Service | Each |
| 626(4A) | Disconnect/Reconnect Sanitary Sewer Service | Each |
| 626(10) | Sanitary Sewer As Builts | Lump Sum |
| 626(13) | Replace Sanitary Sewer Service Pipe | Linear Foot |

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01 DESCRIPTION. Add the following before the first paragraph: For purposes of these specifications, “AWWU” shall mean the Anchorage Water and Wastewater Utility, Engineering Division at (907) 564-2774.  This work shall include the installation, testing, flushing, and disinfection of the water system for acceptance by AWWU.  The Contractor shall provide record drawings in accordance with the conditions prescribed herein.

Add the following to the first paragraph: It is the intent of this contract that the Contractor shall maintain water service to all current customers in the project area during the entire period of construction activities.

The locations of the existing water utility shown on the Plans are not exact.  The Contractor shall be responsible for all work required locating the existing water mains for connection as shown on the Plans.  No additional compensation shall be allowed for discrepancies in the water utility locations.

Add the following:

Coordinate a pre-inspection of the AWWU facilities located within the project limits before pavement removal begins and a post inspection after paving operations are complete. Any deficiencies found during the pre-inspection of the AWWU facilities and before the Contractor begins work on the project will be AWWU’s responsibility to correct.

Existing main valve boxes may require the lid and top section to be replaced.  Where directed by the Engineer and using materials supplied by AWWU, replace the main valve box lid and top section.

Where valve boxes need to be adjusted due to construction work, remove and replace to the final grade.  If a valve box is removed, a new valve box will be supplied by the Anchorage Water and Wastewater Utility (AWWU).  Contact AWWU Operations and Maintenance Warehouse at 550-5946 two weeks in advance to schedule a time to obtain the new valve box.

627-2.01 MATERIALS. Delete the subsection and replace with the following:

1. 	Water Conduit.  All water mains, hydrant lines and service lines 3 inches and larger shall be SDR-11 High Density Polyethylene Pipe (HDPE); except for the horizontal directionally drilled pipe, which shall be SDR-9 HDPE.  Pipe and fitting material shall have a cell classification of 445574C in accordance with ASTM D3350. In addition, the material must exceed 1000 hours when tested in accordance with the Ring Environmental Stress Crack Resistance Test (Radar Ring Test) with fewer than 20 percent failures.  Also, the extruded pipe shall have impact strengths greater than 15 ft-lb/in. at 32 degrees Fahrenheit when tested in accordance with the ASTM D 256 Charpie Impact Test.  The material shall be listed by the N.S.F. for potable water service and shall be precompounded.  In plant blending shall not be allowed.  HDPE pipe, tubing, and fittings, shall conform to all applicable provisions and requirements of the latest revision of AWWA C901 and AWWA C906 and by inclusion, all appropriate standards referenced therein.

The pipe shall be homogenous throughout and free of visible cracks, holes, foreign inclusions or other injurious defects.  It shall be uniform in color, opacity, density, and other physical properties.

All HDPE water main piping and fittings shall be butt fused in accordance with ASTM D-2657.  Butt fusion of the pipe and fittings shall be performed in accordance with the pipe manufacturer’s recommendations as to the equipment and technique.  The fusion operation shall be performed by an individual who has demonstrated the ability to fuse polyethylene pipe in the manner recommended by the pipe supplier and has provided written certification from an HDPE pipe manufacturer stating he/she has successfully completed an 8-hour (minimum) certification class on butt fusion techniques and procedures.  In addition this individual shall have fused a combined total of more than 5,000 feet of HDPE piping in diameters of 4-inches and larger.  The pipe supplier shall supply a representative to instruct the Contractor’s crew on butt fusion and installation and witness the first twenty joints.

The Contractor shall inspect HDPE piping for damage immediately prior to joining.  Damage is defined as cuts or gouges exceeding 10% of the pipe wall thickness, kinked pipe sections, pipe sections flattened to more than 5% of the original diameter, or any abrasion or cutting of the inside surface of the piping. Damage portions of piping shall be cut out and discarded.

The Contractor shall ensure that each joint is fused at the temperature and pressure recommended by the pipe manufacturer in order to achieve the maximum pressure rating for that joint.  All butt-fused joints and fabricated fittings shall be documented by a computer data logger that records pressure and temperature applied at each at each fused joint, along with the date and time the joint was fused.  Computer printouts and electronic data for each fitting shall be submitted to AWWU prior to installation of the fitting.  All fittings shall be labeled with a unique identifier that corresponds with the fusion computer printouts for each fitting.

The use of electro-fusion couplings to join HDPE piping may be allowed upon written approval by AWWU.  Electro-fusion couplings shall comply with ASTM F-1055.  The Contractor shall as-built the exact location of any installed electrofusion couplings.

A maximum of three joints selected at random by AWWU may be tested for compliance with ASTM D-638 as a quality control measure.  Specimens to be tested shall be obtained by cutting the water main piping at least 12-inches on each side of a field made joint.  The Contractor shall then rejoin the ends of the piping and work may proceed.  Cost for removal and repair of butt-fused joints shall be incidental to the Contract.  Labs costs associated with the test of butt-fused joints will be paid by AWWU.

The handling of joined pipe shall be in such a manner that the pipe is not damaged.  Ropes, fabric, or rubber protected slings, or straps shall be used when handling pipe.  Chains, cables, or hooks, inserted into the pipe ends shall not be allowed.  Two slings spread apart shall be used for lifting each length of pipe. Slings for handling the pipe shall not be positioned at butt-fused joints.

A tracer wire shall be installed above all HDPE water mains in accordance with the manufacturers recommendations.  Tracer wire shall be suitable for direct bury applications and shall be 10 AWG with 30-mil HDPE jacket (jacket color blue), capable of a 575-pound average tensile break load.  Tracer wire shall be Copperhead Industries reinforced tracer wire.  Trace wire shall be installed in continous lengths with no splices.  Terminate each end of the tracer wire at ground surface in a valve box top section with cap.  Provide a minimum  5 feet of additional wire neatly coiled within valve box at each end.

Water service connection lines smaller than 3 inches shall be soft drawn seamless, Type K copper with type stamped on exterior. Water service connection lines 3 inches and larger shall be HDPE SDR-11. Gate valves for the HDPE water service connections shall have the same nominal diameter as the service piping and shall have mechanical joint (MJ) connections as described herein.

All new copper water services, valves, and fittings shall be tape coated as shown in the Plans.  Tape coat and primer shall be products of the same manufacturer. Prepare surfaces by hand-removing all loose dirt, dust, or other foreign matter that may interfere with the tape adhesion.  Power tool cleaning of the surfaces is not required.  Ensure conduit, valves, and fitting surfaces are clean and dry prior to beginning coating application.  Apply a thin coat of primer to the surfaces and spiral wrap the tape with a 50% overlap.  Continuously wrap the tape coat between valve box and base section.  While wrapping, press air pockets out and smooth all lap seams.

- Select Material Type “A”. Material shall conform to Subsection 703-2.07.

- Pipe Bedding. All HDPE water system piping shall be installed in Select Material, Type A.

- Restrained Joints. HDPE pipe restrained joints shall be achieved with HDPE mechanical joint (MJ) adapters where shown in the Plans and complying with AWWA C901 and C906.  Adapters shall be molded from a resin compatible with the HDPE pipe, and shall be as manufactured by Central Plastics, ISCO Pipe or approved equal.

Where specified on the Drawings and/or required in these specifications, ductile iron pipe shall be installed with restrained joint thrust restraint systems. Ductile iron thrust restraint systems shall be EBAA Iron MEGALUG®, Romac Industries GripRing®, or U.S. Pipe Field LOK Gasket System or approved equal.  If the ductile iron pipe restrained joint system proposed for use in the Work is not one of these systems, the Contractor must field demonstrate to the Engineer the installation and/or construction of each new restrained joint or restraining system. The Contractor shall provide AWWU with a minimum of forty-eight (48) hours notice, excluding non-working days, to coordinate the review of the field demonstration. The Engineer will ask for verification that the restrained joint system is installed in accordance with the jointing system manufacturer’s written instructions. If in the opinion of the Engineer the Contractor fails to install the restrained joint system in accordance with the jointing system manufacturer’s recommendations, the Contractor shall remove the disapproved system and replace with a new restrained joint system. The Contractor shall provide access to the field demonstration location and all trench excavation, dewatering and backfill operations prior to, during, and after the restrained joint system is reviewed by the Engineer. The cost for coordinating and providing access for review of the Contractor’s installation and/or construction of the restrained joint system shall be incidental to the bid item under construction.

All restrained joint ductile iron installation areas shall include joints, fittings, valves, and piping deflection points.

The Contractor shall provide pipe manufacturer submittals, which include thrust restraint calculations prior to construction.

Tie back rods and/or tie back rod and shackle assemblies will not be acceptable as restrained joints or restraining system for fittings, piping, deflection points, or inside casings.

- Gate Valves. Gate valves shall be iron body, fully bronzed mounted, double disc, parallel or resilient seat valves as manufactured in accordance with the requirements of AWWA C500 “Gate Valves for Water and Sewer Systems.”  All valves shall be nonrising stem type with an O-ring seal and a two (2) inch square operating nut, and shall open counter-clockwise.  Valves shall be mechanical joint ends.

Valve nuts, bolts, and washers shall be stainless steel, Type 316.  Carbon steel galvanized or zinc plated nuts, bolts, and washers shall not be allowed.

- Butterfly Valves.  Butterfly valves shall be of the rubber-seated tight-closing type. They shall meet or exceed the performance requirements of AWWA C504 for operational pressures of 150 psi working pressure and 300 psi hydrostatic pressure.

Mechanical joint valve ends shall be per AWWA C110/ANSI 21.10 and AWWA C111/ANSI 21.11 of the latest revision, and "Short-Body" in accordance with the requirements of Table 2 of ANSI/AWWA C504. Accessories (bolts, glands, and gaskets) shall be supplied by the valve manufacturer.

Butterfly valve actuator bolts that are exposed shall be Type 316 stainless steel with a minimum tensile strength of 75,000 PSI and shall conform to ASTM F593 and F594. All bolts shall be stamped with the grade marking on the head of the bolt, and shall be “T-316”, “316”, or “F593”.

Valves must use full ANSI/AWWA C504 Class 150 B valve shaft diameter and full Class 150 B underground service operator torque rating throughout entire travel to provide capability for operation in emergency service.

Valve body shall be high-strength cast iron ASTM A126 Class B. For valves with the rubber seat mounted on the disc, the mating surface in the body shall be 304 or 316 steel. For valves containing the rubber seat in the body, the method of seat retention shall be in accordance with the requirements of ANSI/AWWA C504, except that no retaining fasteners or other hardware shall be permitted in the flow stream.

Valve operators, unless otherwise required by the Contract Documents, shall be of the traveling nut type, sealed, gasketed, and lubricated for underground service and capable of withstanding on overload input torque of four hundred fifty (450) foot-pounds at full open or closed position without damage to the valve or valve operator. The number of turns to operate the valve shall be a minimum of two (2) turns per inch of valve diameter for ninety degrees (90°) of closure travel at a maximum pull of eighty (80) pounds. All valves shall open counterclockwise and be equipped with two inch (2”) square AWWA operating nut.

For butterfly valves twenty inches (20") and less, the valve shaft shall be one piece extending full size through valve bearings, disc and shaft seal. In the event that the shaft is turned down to fit connections to the operator, the limits of ANSI/AWWA C504, Section 3.3.2 shall be strictly observed. Carbon steel shafts, if used, shall have 304 or 316 stainless steel journals with static seals to isolate the interior of the disc and the shaft from the water.

For butterfly valves over twenty inches (20"), the valve shaft shall be of two-piece stub shaft type, made of 18-8 Type 304 stainless steel. Valve bearings and shaft seals for valves of all sizes shall meet the requirements of ANSI/AWWA C504 Section 3.6 and 3.7 respectively, with the following additional requirements:

a.	Sleeve bearings shall have a maximum coefficient of friction of 0.1.

b.	For underground service, packing shall be pressure-energized chevron or "O" ring type, not requiring adjustment and suitable for permanent duty.

- Valve Boxes. Valve boxes shall be cast iron of sliding, adjustable height type with round or oval bottom hood sections to fit over the top of the valve. The top section shall be recessed to receive a close fitting "eared" lid with the word "water" cast into it. Internal diameter of the smallest section shall not be less than five (5) inches.  Minimum thickness of the metal shall not be less than five-sixteenth (5/16) inch.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.

Valve boxes shall be of sufficient length for the pipe cover depth on the profile drawings and in accordance with the Plans.

Valve box and valve box base sections shall be tape coated as shown in the Plans. Tape coat and primer shall be products of the same manufacturer.  Prepare surfaces by hand-removing all loose dirt, dust, or other foreign matter that may interfere with the tape adhesion.  Power tool cleaning of the surfaces is not required.  Ensure valve box and base section surfaces are clean and dry prior to beginning coating application.  Apply a thin coat of primer to the surfaces and spiral wrap the tape with a 50% overlap.  Continuously wrap the tape coat between valve box and base section.  While wrapping, press air pockets out and smooth all lap seams.

AWWU will supply the main valve box lids and top sections at no cost to the Contractor.

- Fire Hydrants. Fire hydrants shall conform to the requirements of ANSI/AWWA C502 for Dry Barrel Fire Hydrants.  Fire hydrants shall be Mueller Centurian or equal.

a.	All fire hydrants shall be supplied with 5-1/4-inch main valve opening.

b.	All double pumper hydrants shall be furnished with a 8-inch ANSI Class 125 standard mechanical joint end with restrained joint.

c.	All connections shall be restrained mechanical joints unless otherwise indicated in the Contract Documents.

d.	Fire hydrants shall be double pumper, furnished with one (1) 2-1/2 inch hose connection and two (2) 4-1/2-inch pumper connections.

e.	Unless otherwise required by the Contract Documents, all hydrants shall be furnished with a barrel length that will allow a minimum of 10 feet of bury.

f.	The main valves shall be of the compression type, where water pressure holds the main valve closed permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shut-off.

g.	All fire hydrants shall be furnished with a breakaway flange which allows both barrel and stem to break clean upon impact from any angle. Traffic flange design must be such that repair and replacement can be accomplished above ground.

h.	Painting and coating shall be in accordance with cited AWWA specifications. After installation, the hydrant section from the traffic flange to the top of the operating nut shall be painted "Caterpillar Yellow".

i.	Operating and nozzle nuts shall be pentagon shaped with 1-1/2 inch point to flat measurements.

j.	Hose nozzle threading shall be in conformance with NFPA #194 for National (America) Standard Fire Hose Coupling Screw Threads.

k.	All working parts shall be bronze or noncorrosive metal in accordance with the requirements of ANSI/AWWA C502.

l.	All hydrants shall be right-hand opening (clockwise).

m.	All hydrants shall be non-draining. Drain plugs shall not be removed.

n.	Hydrant lower barrel, shoe and HDPE MJ adapter shall be tape coated in a manner similar to copper services and valve boxes as shown in the Plans.

- Galvanic Anode.  Anodes shall be High Potential Cast Magnesium Anodes. Anodes utilized for the galvanic anode system installation shall be prepackaged magnesium style anodes weighing twenty pounds bare and seventy pounds packaged.

Anode composition shall consist of the following:

| Element | Amount (%) |
| --- | --- |
| Cu | 0.001 |
| Si | 0.01 |
| Zn | 2.5-3.5 |
| Mn | 0.2-0.5 |
| Ni | 0.001 |
| Al | 5.5-6.5 |
| Fe | 0.005 |
| All Others | 0.01 |
| Magnesium | Balance |

Anodes shall be packaged in a low resistive backfill consisting of 75% gypsum, 20% bentonite, and 5% sodium sulfate.

Anodes shall be provided with No. 10 AWG stranded copper, single conductor cable with HMWPE insulation.  Lead wire cable shall be rated for 600 volts and designed for direct burial applications.

Equipment and materials used to bond the No. 10 AWG HMWPE to the pipeline shall be “CADWELD” type as manufactured by ERICO Products, Inc. of Cleveland, Ohio, or approved equal.  Exothermic weld areas shall be repaired with Royston “Handy Caps 2”, Tapecoat TC Mastic or approved equal.

Anodes shall be provided for all water main gate valves, butterfly valves, water service gate valves, water service curb stops, and fire hydrants.  Jumper wires shall be installed between valves and hydrants as shown in the Plans.  If more than one one gate valve and/or hydrant is within a 30-foot radius, use two AWG 10 HMWPE lead wires to bond the hydrant and valves.  Use only one anode for the cluster

- Temporary Water System.

The Contractor shall only use those materials and equipment listed in this Section to supply temporary water service.  Temporary water service shall be supplied under the service criteria outlined in this Section.  All equipment used shall be specifically designed and properly disinfected for the storage, handling, and delivery of potable water.

The following conditions apply for all temporary water systems.

- The use of the temporary water system is for short term use only, not to exceed 30 days.

- The temporary water system source must be from the AWWU public water system.

- A backflow prevention device must be installed at the connection to the existing public water system.

- If the temporary water system is to be operated during winter conditions, freeze protection should be provided.

- All materials used in the temporary water system, in contact with the potable water, must be certified under the NSF International Standard 61.

- At least 20 psi of service pressure should be maintained at the highest elevation of the distribution main, under peak flow conditions.

- The temporary water distribution system must be disinfected and flushed in accordance with AWWA C651.

- The temporary water system may not serve water to the public until analytical test reports for water sample(s), taken at the furthest end of the temporary distribution, confirms that the system is free from coliform bacteria.

- Approval/acknowledgment is obtained from AWWU to connect and operate the temporary system.

Construction and operation of the temporary water system may be performed if all conditions and requirements listed above are met.  If all conditions and requirements listed above are not met, a temporary water system plan shall be submitted to DEC for review and approval.

Service shall be supplied to each structure presently served by AWWU.  The following minimum criteria shall be used for service to each structure:

- Forty (40) psi minimum, one hundred (100) psi maximum delivery pressure measured at the connection to the structure.

- Five (5) gallons per minute flow at the above delivery pressure measured at the connection to the structure.  Commercial and other business structures may require higher water flows.

- Potable water system and water quality shall conform to 18 AAC 80 Alaska Drinking Water Standards.

- All services to structures shall be valved to allow individual control of service to each structure.

The temporary water service system shall be constructed from one or more of the following materials:  polyvinyl chloride (PVC), high-density polyethylene (HDPE), copper, ductile iron, cast iron or galvanized steel.

The primary water feeder pipe shall be a minimum of three inches (3”) in diameter.

CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL. Delete the first paragraph and add the following: Contact the AWWU in writing a minimum of three (3) working days in advance of beginning construction to schedule a pre-inspection of the valves and valve boxes and a post inspection after paving operations are complete. Provide the AWWU a copy of the written notice. Contractor shall be responsible for furnishing all the required traffic control and personnel to assist AWWU while locating and performing the pre-construction and post-construction inspections. Contractor forfeits all rights to deny damages done by Contractor or Contractor’s agents during the course of work if Contractor fails to participate in this inspection.  It is the Contractor’s responsibility to protect and maintain valves and valve boxes in an operable condition during construction. If AWWU finds valves or valve boxes damaged or rendered inoperable after the above inspection and before final inspection the Contractor shall repair the valves and/or valve boxes at the Contractor’s expense.

Existing valve box covers identified as worn in the pre-inspection shall be replaced by the Contractor with new covers provided by AWWU.  Coordinate with the AWWU to obtain replacement covers from the AWWU warehouse.

Contact the AWWU project manager and schedule the pick-up of AWWU supplied materials.  Allow 3 working days from the time contact is made to schedule the pick-up and the actual pick-up of the materials.

If service connection locates are required, contact AWWU Field Services at (907) 564-2762.  Allow a minimum of 3 working days from the time of the request to the time of the locate.

Prior to commencement of work to install the water system, the Contractor shall submit to the Engineer for review, a detailed plan for the installation of the new water systems. The plan shall be of sufficient detail to clearly indicate the proposed work sequence, schedules, disruption of water service, and temporary water services.

AWWU, through the Engineer, reserves the right to suspend the water system installation at any time that the Contractor fails to meet the requirements set forth herein until such time as the Contractor makes the necessary corrections.  Suspensions of work will not entitle the Contractor to an extension of time for the completion of the project, and will not entitle the Contractor to extra payment for costs incurred.

If construction or excavation require the removal of any existing privately owned facilities or improvements within and outside of the provided temporary construction easements, the Contractor shall be responsible for coordinating with the owner and for reestablishing lawns, driveways, parking lots, etc., at the Contractor’s cost.  Any restorative work will be completed as soon as practicable after the installation, but in no case shall the period of time exceed two weeks.  The Contractor shall restore property disturbed by contract activity to the preconstruction condition.

Trench Shoring

The Contractor shall obtain approval from the Engineer for all sheeting, bracing, and shoring materials and/or equipment to be used on the project.  Materials used shall be in accordance with Section 1926.651, Subparagraph 1 of the Federal Register, Volume 37, No. 243, page 27553, OSHA Regs., December 1972.

All construction requirements for design, installation, and use of sheeting, shoring, bracing, and shielding shall be in accordance with current safety regulations.  All sheeting, shoring, bracing, and shielding shall be designed by a Professional Engineer registered in the State of Alaska, hired by the Contractor.  All working drawings and design data shall be submitted to the Engineer for approval.

When shoring and sheeting is left in the trench, sheeting must be driven lower than the bottom of the pipe and cut off (1) foot minimum below road structural fill.  No traverse bracing will be permitted to remain.

No bracing requiring driven or vibratory installation methods shall be used on this Project. Any Contractor provided portable trench shielding shall comply with relevant OSHA regulations. The Contractor shall provide the Engineer certification of such compliance from the portable shield manufacturer or supplier.

Delete the second paragraph.

Add the following to the fourth sentence of the third paragraph: "so proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.”

Add the following after the fourth paragraph:  Contractor shall take every effort to protect existing services, both located and unlocated, from damage and shall anticipate one service to each developed lot adjacent to the sewer main.

Repairs to any damaged sewer services shall be made using Class 50 DIP and Romac (or approved equal) repair couplings with stainless steel bands.  Pipe inside diameter shall match the existing pipe or, if the exact match is not available, the new pipe may be slightly larger.  The inverts of the new pipe shall match the inverts of the existing pipe, regardless of pipe diameter.  Pipe shall be bedded and backfilled in accordance with the trench detail.

Contractor shall notify the sewer service user immediately if a service is damaged and advise the user to not introduce any flow into the service until it is repaired. Contractor shall perform the repair immediately to restore service and shall advise the user when the service is usable.  Contractor shall contain any flow that spills from the damaged service and shall dispose of waste and contaminated soil in accordance with the State of Alaska Department of Environmental Conservation (DEC) regulations.

Repair to any sewer services is incidental to the water pipe construction and no separate payment will be made.

Delete the fifth and sixth paragraphs and substitute the following: At least 72 hours prior to removing or disrupting service to fire hydrants, the Contractor shall contact both the Anchorage Fire Chief, and AWWU.  Any hydrant taken out of service shall be immediately and securely wrapped in burlap to indicate its status.

Contractor shall provide seventy-two (72) hours written notice to the Engineer, AWWU, the Anchorage Fire Department, and affected property owners/businesses prior to anticipated mainline flow interruptions.  It shall be the Contractor’s responsibility to coordinate “turn-off” and “turn-on” with the Engineer.  Additionally, the Contractor shall notify all affected property owners and the Engineer, 72 hours prior to interruption of AWWU's water service.  The Contractor shall provide temporary service to all those property owners with disrupted water service if the interruption exceeds 6 hours duration.

Add the following:

Temporary Water Systems. The Contractor shall submit the name and phone number of a contact person and at least one alternative who shall be available 24-hour basis for repair and/or maintenance of the temporary water system.  In the event that the Contractor fails to repair and/or maintain the temporary system and AWWU is required to perform the repairs and/or maintenance, all costs associated with said repairs and/or maintenance shall be deducted from the Contract amount.

Prior to the construction of the temporary water system the Contractor shall obtain a written “Permission to Enter” from the property owner.  Such permission shall hold the Department, the Municipality of Anchorage, AWWU, and its agent harmless for any claims resulting from damage or harm sustained due to the Contractor’s operation.  The Contractor shall provide a copy of each “Permission to Enter” to the Engineer and AWWU.

The Contractor shall provide any necessary fittings, valves, temporary connections or appurtenances necessary in order to maintain the water distribution system.  Any costs involved in service changeovers and providing temporary water service shall be subsidiary.

All temporary water service equipment shall be disinfected per ANSI/AWWA C652, Disinfection of Water Storage Facilities and ANSI /AWWA C651, Disinfection of Water Mains.  All bacteriological samples required under these Specifications shall be done by a testing laboratory certified by the State of Alaska.  Two bacteriological samples shall be taken 24 hours apart to confirm the system is free of coliform bacteria before commissioning a temporary water system.

Following the successful installation of the temporary water system, the existing water service shall be appropriately disconnected at a main shutoff valve inside the structure. Qualified personnel who are familiar with building plumbing systems shall accomplish the disconnection of the existing water service.  The Work shall be done to prevent backfeeding water through the service connection.

Fire hydrants may be used as a water source for a temporary water system.  The Contractor shall be required to obtain a hydrant permit from AWWU and will be required to meet all permit conditions (winter use of a hydrant shall require special permission from AWWU).  In addition the Contractor shall provide a backflow preventer and gate valve assembly at the fire hydrant as a shut off valve and a for the temporary water system. The Contractor shall be responsible for any damage to the hydrant and temporary service piping and shall repair such damage at no cost to the Department.

The Contractor shall be responsible for all damages incidental to interruption of service that may be due to the Contractor operations.

Delete the tenth and eleventh paragraphs and substitute the following: Where new water mains cross existing sanitary sewer or storm sewer pipes, the new water main shall be installed a minimum of 18 inches vertically from the sanitary sewer or storm sewer pipe. Water pipe joints shall be a minimum of 9 feet horizontally from sanitary sewer pipes, storm sewer pipes, manholes, or catch basins.

Where the required clearance cannot be obtained, the existing pipe is to be encased with a jacket of Class A concrete, 4 inches thick for 10 feet on each side of the crossing.

Alternately, the existing sanitary sewer pipe may be replaced with Class 52 DIP with joints spaced at least 9 feet from the crossing.  Heat shrink wrap joints within 10 feet of the pipe intersection.

Add the following:

Trench Excavation and Backfill. Excavation and backfill shall be to the width and depth as shown on the drawings.  Trench width at or below the top of the pipe shall be of a width that will allow compaction equipment to be used at the sides of the pipe.

Contractor shall erect and maintain barricades to prevent access around all excavations left open at the end of the workday.  Contractor shall provide and maintain adequate barricades to ensure public safety at all times during the prosecution of the Work.

Contractor shall perform all excavation of every material encountered.  Excavated material shall be placed in an orderly manner and at a distance from the trench conforming to all State and/or Federal safety codes.  Excavated material meeting the requirements of Select Material shall be stockpiled separately and reused in the Work.

Not more than 200 feet of trench shall be open in advance of the pipe installation unless written authorization is obtained from the Engineer.  Not more than 100 feet of trench shall be left open at the end of the workday, unless otherwise approved by the Engineer.

All bedding material and backfill material shall be placed in uniform layers of not more than 12 inches in depth and compacted in accordance with Subsection 203 3.04. In no case shall bedding material be placed above the springline of the pipe in a single lift.  Ponding or jetting of backfill will not be permitted.

When existing conduits or utilities, which are not scheduled for removal or abandonment, are encountered in the excavation, they shall be adequately supported and protected from damage.

All sheeting and bracing used in excavation shall be removed by the Contractor following the completion of the work.

Disconnect Water Service.  Disconnect water services at the main.

Remove Existing Pipe.  Pipe and appurtenances called out on the plans to be removed shall be an incidental item of construction.  All removed materials shall become the property of the Contractor, unless specifically addressed otherwise in these special provisions.

Abandon Water Main.  Water abandonment work shall be accomplished by using the abandon in place method.  This method is to place one foot of concrete at the beginning of the pipe, calculate the total internal volume of the pipe, fill the pipe with slurry equal to the total calculated volume, and place one foot of concrete at the end of the pipe.  Slurry shall consist of a mixture of water and sand with an approximate ratio of seven gallons of water per cubic foot of sand.  The total lineal footage of the water main abandoned shall be shown on the record drawings.

Depth of Bury. All water mains and services shall have a minimum of 10 feet of bury at all points except where otherwise indicated.

Final Acceptance. The Contractor shall, upon completion of all work involved, notify the Engineer in writing of completion and request a pre-final inspection of the project. This inspection will be performed in the presence of the Engineer, AWWU, and the Contractor. Copies of a list of any deficiencies indicated by this inspection will be furnished to the Contractor for remedial action.  When all corrective action has been completed, the Contractor shall notify the Engineer, and a final inspection will be performed.

627-3.02 INSTALLATION OF CONDUIT. Delete the first and second paragraphs and substitute the following: Installation shall be in accordance with these specifications, AWWA C600, and the current AWWU Design and Construction Practices Manual. The interior of the conduit and accessories shall be thoroughly cleaned of foreign matter before being lowered into the trench.  The conduit shall be kept clean during laying operations by plugging.  Lay conduit to the grades and lines shown on the Plans. However, at a sufficient distance prior to encountering a known obstacle or tying into an existing conduit, the Contractor shall expose and verify the exact location of the obstacle or conduit so proper alignment and/or grade may be determined before the conduit sections are laid in the trench and backfilled. The costs incurred for removal and realignment of backfilled conduit sections due to improper verification methods shall be borne by the Contractor.

Delete the seventh and eighth paragraphs and substitute the following: Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or offsets shall not exceed 80 percent of the manufacturer's recommended maximum deflection.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable. Wherever possible, the Contractor shall achieve the desired deflection by taking advantage of reduced deflections over multiple joints. Short-radius curves and closures shall be formed by shorter lengths of conduit, bevels, or fabricated specials.  No pipe lengths less than 8 feet are allowed.

Conduit shall be laid in the trench such that after the line is completed the bottom of the conduit conforms accurately to the grades and alignment shown on the Plans. A maximum 0.2-foot deviation from design alignment and elevation will be allowed. Both line and grade shall be checked and recorded in a field book for each piece of conduit and appurtenance installed.  All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the conduit and not by blocking or wedging up.

The Contractor shall have survey instruments such as transit and level for transferring alignment and grades from offset hubs.  The Contractor shall also employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides. The Contractor shall furnish to the Engineer a copy of the surveyor's record notes for the newly installed conduit and appurtenances. The practice of placing backfill over a section of conduit to provide a platform for the instruments shall be subject to the approval of the Engineer.

A minimum vertical separation of 18 inches shall be maintained at water and sewer or water and storm sewer crossings.  Where a sanitary sewer or storm sewer and water main cross with less than 3-feet of vertical separation (outside of conduit to outside of conduit), insulate the water main with 4-inch thick extruded rigid insulation board (minimum of R-20 per 4-inch thick insulation).

Conduit that has the grade or joint disturbed after laying shall be taken up and relaid. Water shall be kept out of the trench until the jointing is completed.  No conduit length less than 8 feet shall be incorporated into the system except those necessary for fire hydrants or valve locations unless restrained by use of mechanical joint adapters for HDPE pipe or Field LOK gaskets, MEGALUG fittings, or approved equal for ductile iron pipe sections.

Polyethylene Encasement. The outside of all ductile iron and cast iron conduit and fittings used in water system construction shall be encased with one layer of 8 mil thick polyethylene film.  Valves and other appurtenances used in water system construction shall be encased with three layers of 8-mil thick polyethylene film. The polyethylene encasement material for conduit shall conform to AWWA C105/ANSI A21.5. The polyethylene encasement shall be installed using the following method:

Method

a.	Cut polyethylene tube to a length approximately 2-feet longer than the length of the pipe section. Slip the tube around the pipe, centering it to provide a 1-foot overlap on each adjacent pipe section and bunch it accordion-fashion lengthwise until it clears the pipe.

b.	Lower the pipe into the trench and make up the pipe joint with the preceding section of pipe.  A shallow bell hole must be made at the joints to facilitate installation of the polyethylene tube.

c.	After assembling the pipe joint and testing the bonded joint, make the overlap of the polyethylene tube. Pull the bunched polyethylene from the preceding length of pipe, slip it over the end of the new length of pipe, and secure in place. Then slip the end of the polyethylene from the new pipe section over the end of the first wrap until it overlaps the joint at the end of the preceding length of pipe.  Secure the overlap in place.  Take up the slack width to make a snug, but not tight fit along the barrel of the pipe, securing the fold at quarter points.

d.	Repair any rips, punctures, or other damage to the polyethylene with adhesive tape or with a short length of polyethylene tube cut open, wrapped around the pipe, and secured in place.  Proceed with installation of the next section of pipe in the same manner.

627-3.03 FIRE HYDRANTS. Delete this subsection in its entirety and substitute the following:

The Work under this section consists of the performance of all Work required for furnishing all necessary hydrants, pipe, auxiliary valve, and associated appurtenances required to install new or relocate a hydrant to a location indicated on the plans.  The Contractor shall provide all trench excavation, backfill, and compaction necessary to install the fire hydrant assembly in accordance with the plans.

Auxiliary Gate Valve and Valve Box. Auxiliary gate valves and valve boxes shall be furnished and installed in accordance with 627-2.01, 627-3.04, and 627-3.05.

The auxiliary valve shall be closed during installation and remain closed during all main line open bore flushing operations.  The auxiliary gate valve shall be opened for hydrostatic pressure testing, disinfection, and while the hydrant is being raised by AWWU under pressure.

Joint Restraint. The Contractor will be required to use restrained joints on all fire hydrant leads. The Engineer may check any or all restrained joints to assure proper torque as specified by the manufacturer.  All joints shall be restrained in accordance with 627-2.01.

Guard Posts. Contractor shall install guard posts at each hydrant installation in accordance with the Plans.  If, in the opinion of the Engineer, the guard posts are not to be installed, they shall be delivered to the AWWU Operations and Maintenance Facility.

Hydrant legs shall be installed level and barrels installed plumb.

The AWWU Operations Division will adjust Fire Hydrants to final grade.  The Contractor shall provide AWWU with a minimum of seventy-two (72) hours’ notice, excluding non-working days, to coordinate fire hydrant adjustment.  The Contractor shall be responsible for access to the hydrant location and all trench excavation, dewatering, and backfill operations prior to, during, and after the fire hydrants are adjusted by AWWU personnel.  The cost for coordinating and providing trenching are incidental to the fire hydrant installation.

Hydrants installed but not available for use shall be covered with burlap and securely tied.

Contractor shall paint or use permanent-ink marker to stencil 2-inch black letters on the face of the fire hydrant directly below the bonnet flange indicating the direction and distance to the auxiliary valve box, to the nearest 0.1 foot.

627-3.04 VALVES. Delete this subsection and substitute the following: Valves shall be installed where shown on the plans with valve operator placed on the side of the water line away from the centerline of the street or easement. Valves shall be installed plumb. Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling.  The valve shall be inspected by AWWU's representative, in the open and closed positions to ascertain that all parts are in good working condition.

627-3.05 VALVE BOXES. Delete this subsection and substitute the following: Valve box components shall be installed plumb over the valves as shown on the plans, with base section centered over the operating nut of the valve and resting on well compacted backfill. Top section shall be so set as to allow equal movement above and below finished grade. Final elevation shall be as shown on the Plans.

Top of base section shall be approximately on line with nut at top of valve stem, and the entire assembly shall be plumb.  Provisions shall be made to restrict the soils from entering the bottom section of the valve box.  Wrap burlap inside bottom section under the packing gland and wrap three layers of non-woven geotextile fabric around the outside of the valve and base section of the valve box and secure the fabric at the top and bottom with wire or tape.  Encase the valve box with three layers of 8-mil polyethylene, taped securely in place.

The Contractor shall expose all valve boxes for pre-final and final inspection. After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.06 TESTING WATER SYSTEM. Delete this subsection and substitute the following: The Contractor shall notify the Engineer in writing 72 hours in advance  prior to any test.  AWWU and the Engineer shall be present during all tests. Two hours notice in advance of the scheduled time shall be given to the Engineer if the test is to be postponed or canceled.

Contractor shall submit a request to supply water for flushing, testing and disinfecting in writing to the Engineer at least 24 hours prior to obtaining AWWU supplied water. The request for water will be subject to water availability and meeting the Contractor’s schedule may not be possible.

AWWU reserves the right to provide a test gauge or to check and test the Contractor’s test gauge at any time.

Flushing. All flushing shall be coordinated with AWWU.  All newly laid water conduit shall be "open-bore" flushed to remove any foreign matter to the satisfaction of AWWU. A detailed plan for cleaning of the lines shall be submitted to the Engineer for review and approval prior to commencement of work.

"Open-bore" flushing shall be accomplished prior to hydrostatic testing and disinfection at all extremities including all stubouts and dead-ends.  The Contractor shall furnish, install and remove all fittings and conduit necessary to perform the flushing.  Under no circumstances will "open-bore" flushing through hydrants or reduced outlets be permitted.  Fire hydrant auxiliary valves shall be closed during flushing.

Flushing of newly installed conduit may be required to occur between the hours of 1:00 AM and 6:00 AM, depending on availability of water, as authorized by AWWU. Flushing shall be considered incidental to this work and no separate payment will be made.

When in the opinion of the Engineer, the Contractor’s proposed testing and flushing plan is deficient, inadequate, improper, or conditions are such that the impact to existing water service area are adversely affected by service interruptions, the Contractor will be notified in writing by the Engineer.  Such notification shall be accompanied by a statement of the corrective action to be taken.  Contractor shall adhere to the testing and flushing schedule and comply with instruction as directed by the Engineer.

Hydrostatic Testing. A hydrostatic test shall be conducted on all newly constructed water conduit, service lines, fire hydrant leads and stub-outs after "open-bore" flushing in the presence of the Engineer and AWWU in accordance with the requirements of ANSI/AWWA C600 unless hereinafter modified.  The Contractor shall use a pressure test.

The Contractor shall furnish all necessary assistance, equipment, labor, materials and supplies (including the test pressure gauge) necessary to complete the test to the satisfaction of AWWU.  The Contractor shall suitably valve off or plug the outlet to the existing or previously-tested water main at the Contractor expense, prior to making the required hydrostatic test.

Prior to testing, all air shall be expelled from the conduit. If permanent air vents are not located at all high points, the Contractor shall, at the Contractor expense, install corporation stops at such points so the air can be expelled as the conduit is slowly filled with water.

No hydrostatic test section shall exceed 1,000 feet unless approved by AWWU in writing. All main line valves, fire hydrant auxiliary valves, fire hydrant main valves and plugs shall be tested.  All intermediate valves within the section being tested will be fully closed and reopened as directed by the Engineer during the actual test. Only static pressure will be allowed on the opposite side of the end valves of the section being tested.

All hydrostatic testing will be performed through test copper.  Use of fire hydrants and service connections for testing will not be allowed.

The hydrostatic leak test procedure consists of filling the conduit with water, an initial expansion phase, a test phase, and depressurizing.  Before applying pressure, all conduit and all components in the test section shall be restrained and the trench section backfilled.  The maximum test duration is 8 hours to pressurize, allow initial expansion, test, and depressurize the test section.  If the test is not completed due to leakage, equipment failure, or for any other reason, depressurize the test section completely, and allow it to relax for at least 8 hours before pressurizing the test section again.

The hydrostatic pressure shall be 160 psi.  Gradually pressurize the test section to test pressure and maintain the test pressure for 4 hours.  During the initial expansion phase, polyethylene pipe will expand slightly and additional test liquid will be required to maintain pressure.  It will not be necessary to monitor the amount of water added during the initial expansion phase.  Immediately following the initial expansion phase, reduce the test pressure by 10 psi and stop adding test liquid. If the pressure remains constant for 1 hour with no visible leaks, that section of the conduit will not be subjected to any further hydrostatic tests.

Cracked or defective conduit, gaskets, mechanical joints, fittings, valves or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense. The test shall then be repeated until there is no measurable leakage.

In the instance where connection is made to an existing water conduit, a new valve shall be installed on the connection.  The Contractor shall suitably seal off the outlet leading to the existing conduit prior to making the field tests.

Continuity Tests. The Contractor shall perform electrical conductivity tests on all DIP water mains in the presence of the Engineer and AWWU.  Continuity testing shall also be performed on all DIP water service connections and extensions greater than two inches in diameter.  The Contractor shall maintain a circuit of 600 amperes DC current for a period of 15 minutes.  Return current shall be at least 90 percent of the input current.  All equipment necessary to maintain the circuit shall be supplied by the Contractor.

All continuity tests will be through wires brought to the surface or through 3/4-inch minimum copper pipe connected to the main.  The use of water service thaw wires, fire hydrants and valves, as substitutes for wires will not be accepted.  All wires brought to the surface to complete the continuity test shall be removed to a depth of two feet below finished street grade upon completion of the tests.

Removal of Test and Air Vent Copper Pipe. After completion of testing, all test and air vent copper pipe shall be removed and the corporation stop closed at the main with a copper disk and flare nut installed, in the presence of the Engineer and AWWU.  In addition, a visual inspection for leaks will be performed in the presence of the Engineer and AWWU.

627-3.07 DISINFECTION OF WATER LINES. Delete this subsection and substitute the following: All portions of the water system shall be disinfected, including all valves and stops and any portion of the existing connection system that might have become contaminated during construction activities.  Disinfection shall be accomplished after completion of pressure and/or leakage tests in compliance with ANSI/AWWA C651, Disinfecting Water Mains.

Chlorine shall be used for disinfection, and shall be applied only by one of the following methods:

- liquid chlorine gas and water mixture

- direct chlorine gas feed

- calcium hypochlorite and water mixture

Calcium hypochlorite shall be comparable to commercial products known as High-Test Hypochlorite (HTH), Perchloren or Machochlor. The chlorinating agent shall be applied at the beginning of the section adjacent to the feeder connection, insuring treatment of the entire line. Water shall be fed slowly into the new conduit with chlorine applied in amounts to produce a dosage of 40 to 50 parts per million (ppm). Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly-laid conduit. Under no circumstances shall the chlorinating agent be introduced through a fire hydrant.

Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device. Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and effective diffusion of gas within the conduit. Calcium hypochlorite shall be injected or pumped into the water conduit. During the chlorination process, all intermediate valves and accessories shall be manipulated so that the strong chlorine solution in the conduit being treated will not flow back into the conduit supplying the water. Hydrostatic testing of water conduit containing the chlorine mixture will not be allowed. The Contractor shall provide a plan for approval by the Engineer and AWWU for disposal of chlorinated waters from the disinfection of the system.  Under no circumstances shall the spent chlorine solution be discharged to the sewer system.  AWWU shall approve the discharge location.

A residual of not less than 10 ppm chlorine shall be produced in all parts of the water conduit and retained for a minimum period of 24 hours, after which it shall be flushed from the conduit at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply. Two bacteriological samples shall be taken 24 hours apart. In no instance will a water conduit be chlorinated before "open-bore" flushing.

CHLORINATION

| CONDUIT DIAMETER | DOSAGE (OZ. PER 100 FEET) |
| --- | --- |
| 6-inch | 1.35 oz |
| 8-inch | 2.75 oz |
| 10-inch | 4.30 oz |
| 12-inch | 6.19 oz |
| 16-inch | 11.00 oz |
| 18-inch | 13.93 oz |

The above table is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method.  The given dosage per 100 feet results in a minimum chlorine solution of 40 to 50 ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is 65 percent pure.  If another chlorinating agent is used, the dosage must be adjusted.  Caution should be exercised against producing too high a concentration of chlorine in the conduit.

After completion of all testing, including bacteriological tests, all test and air vent copper pipe shall be removed and the corporation stop closed at the main with a copper disk and a flare nut installed, in the presence of the Engineer and AWWU.

Contractor shall prepare and submit a written plan to DEC for disposal of chlorine solution used for disinfection of water lines.  Upon DEC approval, Contractor shall dispose of chlorine solution in accordance with the plan.

Add the following subsection:

627-3.08 GALVANIC ANODES: Galvanic anode installation shall be accomplished as shown on the Drawings and as specified herein.  The following is a list of general procedures utilized for typical installation of galvanic anodes.

a.	Anode Installation

Anodes shall be installed 12”-36” from the sidewall of the pipe, to a centerline depth in-line with the approximate horizontal plane of the pipe’s bottom dead center.  Anodes shall be placed on both sides of the pipeline (opposite side of the pipe for every other pipe joint).  Exact anode location shall be shown on the Record Drawings.

b.	Lead Wire Connection to Pipe

The No. 10 AWG HMWPE lead wires shall be attached to the top of the pipe. Lead wire connection to the pipe shall utilize exothermic weld connection methodology as outlined above and on the drawings.  Contractor shall follow exothermic manufacturer’s recommendations and instructions for use.

c.	Backfilling

Anodes or lead wires damaged during backfill procedures shall be repaired at no additional cost to the Department.

Add the following subsection:

627-3.09 AS-BUILT DRAWINGS AND RECORD DOCUMENTS. A complete and accurately dimensioned record of all deviations, deletions, additions and alterations from and to the contract plans and specifications shall be maintained by the Contractor to indicate the work as actually installed. This as-built information shall be recorded on a print of plans affected and on the applicable pages of the specifications with supplementary notes. This record set of plans and specifications shall be kept by the Contractor showing record conditions of all conduit and appurtenances installed.

The Contractor shall maintain record documents on the job site consisting of a complete set of plans, survey line and grade books, and other contract documents, and keep them current on a daily basis. Record documents shall be available to the Engineer at all times.  The Engineer may periodically review the status of the record documents during the course of the work.  Failure to keep the record documents current and in the required condition will be considered cause for withholding progress payments.

Conduit and appurtenances shall be referenced by stationing, showing design line and grade and as-built line and grade.

The Contractor shall prepare as-built drawings as the work progresses and final record drawings as described below.  Acceptable record drawings will be prepared on copies of the project construction drawings to depict all lines, grades, locations, materials, and other elements of the work as actually constructed with clearly marked final elevations and locations with actual dimensions.  Noted stations, elevations, slopes and other design dimensions shall be shown on the construction drawings with “ASB” if no change occurs in the field.

The Contractor shall survey the work and all utilities and obstructions encountered during construction in a manner producing an accuracy of 0.03 feet vertically and 0.5 feet horizontally, and reference that as-built information to both project survey control and to pipe stationing. The Contractor shall submit as-built drawings to the Engineer for review each month, providing five (5) working days to review and approve the information, or to return the drawings for additional information.  The Engineer and AWWU will review all Record Documents for completeness and conformance to standards.  The Contractor shall make all corrections, changes, additions, and deletions required by the Engineer. The Contractor shall prepare final record drawings on a clean set of full-sized construction plans at the completion of water & sewer construction as follows:

- Note the name of the person who prepared the record drawings, the Contractor, and the date of preparation in the appropriate title block on each record drawing sheet.

- Make all additions and collections neat, clean, and legible in red ink or red pencil to clearly describe the work as actually constructed.  Identify any and all changes to the original design.  If additional plan sheets are required, prepare them on reproducible Mylar-type material and sized as the original plans.

- Complete the revisions in conformance with the scale of the drawings.

- Show each change, deletion, or omission with the appropriate entries and symbols.  Draw one straight line through stationing, elevations, and/or notes. Crossed out information must remain legible.  For every entry on the construction drawings that was not changed in the field, mark “ASB” next to that entry.

- Cross-hatch any deleted or relocated water or sanitary sewer.

- Note reference information used to prepare record drawings, such as change orders and field books.

- Make profile changes with new elevations or stationing entries only, unless the change is significant.  If the change exceeds 1.5 feet, cross-hatch the original pipe and redraw the profile line.

- Provide complete information for all water and sanitary sewer services that were reconnected or constructed.  If the service was reconnected, record the size and material of the service and the pipe station at the main.  If the service was constructed, provide horizontal and vertical locations at the property or lease lot line, including swing ties and offsets to property or lease lot corners. Include two or more swing ties from prominent, permanent features to show the location of each installed water service connection on the final record drawings.  Swing ties are to be as close to perpendicular to each other as possible. Where property lot corners are in place, use them as swing tie reference points.

- Provide complete tables for each water service showing the material and size of the service pipe, pipe stationing of the service at the main and the location and elevation of each service at the property line.

The Contractor shall clearly stamp the as-built drawings “Record Drawings”, and submit them to the Engineer for approval by AWWU. Approved final Record Documents, bearing certification by the Contractor that the Record Documents are a complete and accurate representation of the project as constructed must be delivered to the Engineer within thirty (30) days of Substantial Completion of water construction.

When the water system additions are complete, the Contractor shall certify the accuracy of the construction survey notes and of each revision on the plans and in the specification by written signature endorsement, and deliver them to the Engineer prior to final acceptance of the system by AWWU.  The Contractor will be required to provide signed Record Drawings approved by AWWU prior to final payment.

Add the following subsection

627-3.10 Horizontal Directional Drilling (HDD)

1. 	Work Description

Project scope consists of supplying all equipment, labor of the proper jurisdiction, tools, and materials to install a water main from Point A (STA “W” 306+88.45) to Point B (STA “W” 300+77.54) using the horizontal directional drilling (HDD) method of pipe installation.

2.	Definitions

a. 	Conductor Barrel.  A conductor barrel is a steel pipe casing that is laid into an inclined trench, pushed in with the drill rig in softer soils or rammed into the ground with a pipe-ramming machine at the entry pit where drill string entry is planned.  This casing is intended to prevent inadvertent near-surface returns, and allows for easy monitoring of drilling mud return levels.  Installation of conductor barrels is typically determined by the composition of the soils between the surface at the entry point and the designated soil strata to be drilled.

b. 	Horizontal directional Drilling.  Horizontal directional drilling is a process whereby a steel pilot string is drilled along the centerline of the desired pipe pathway from an entry point at the surface to an exit point also at the surface.  The pilot string alignment and grade can be controlled precisely during installation.  Upon completion of the pilot drill work, the drill rod head is fitted with a back reamer to which a welded product pipe string is attached and the whole assembly is pulled back into the ground towards the original entry point.  Any pipe depth can be selected consistent with the allowable radius of curvature of the pilot string and the product pipe.  Swabbing can be performed if required to insure an open conduit and smoother product pipe installation.

3.	Material

a.	Pipe.  The pipe material for this project will be 18” diameter, SDR 9.0, and approximately 665 feet long high-density polyethylene (HDPE) pipe.

b.	Fittings and other Materials.  Fittings and other materials for use with the HDD method shall be as specified in Article 8, Pipe Materials, or as specified within subsection 627-2.01 MATERIALS of these special provisions.  Fittings and all other material shall be compatible with other pipes being connected to the new main.  No materials other than those specified shall be incorporated in the construction without prior written approval of the Engineer.

c.	Pipe installation Lubricants.

1.	Drilling fluid shall be bentonite-based and its composition shall be submitted to the Department and AWWU for review prior to use.  No fluid shall be used that does not comply with permit and current environmental regulations.

4.	Equipment. Contractor shall use a horizontal directional drilling machine with minimum 
110,000-pound pullback capability to install an 18” diameter HDPE pipe between Point A and Point B.  This equipment will be reviewed by the engineer, and must be approved prior to beginning construction.

The equipment shall include drill heads, reamers, swabbing heads and other tooling that is suitable for the soil conditions.  Soil information can be obtained from the Final Structural Foundation Engineering Report for the bridge.  Information on obtaining this report can be found on the Special Notice to Bidders page in the contract documents.

All equipment shall be capable of completing the defined scope of work within the constraints and staging allowances as defined by the existing roadway, creek Right-of-Way, and the construction permits issued for this project (see subsection 107-1.02 PERMITS, LICENSES, AND TAXES). No equipment shall damage or otherwise harm existing utilities or improvements. Any damage to these facilities or to private property, either accidental or as a consequence of agreed to and approved land infringement for purposes of performing the work, shall be repaired promptly by the Contractor at the Contractor’s expense following completion of the work.

5.	Contractor Qualifications. Installation of pipeline by the horizontally drilled, directionally controlled method shall be only by a contractor with a nominated resident Superintendent and equipment operator each having a minimum of five (5) years experience in horizontal directional drilling.  The Superintendent and Operator shall have successfully completed a minimum of three (3) directionally drilled pipe installations, 16” or greater in diameter and in excess of 600 feet in length.  Contractor shall furnish the Department and AWWU with a list of references substantiating this requirement.

6.	Submittals

a.	General. The Contractor shall submit the following information for review by the Engineer a minimum of two weeks prior to commencing operations:

1.	Name, business address, telephone number, and qualifications of the Contractor or sub-Contractor performing the horizontal directional drilling work.

2.	Names and previous applicable experience of all supervisory and operating personnel to be directly involved in the work.

3.	Written descriptions and/or literature identifying and describing the horizontal directional drilling equipment and tools to be used, including capacity ratings and principals of operation.

b.	Specific. One week prior to commencing the work, contractor shall submit a detailed installation plan to the Department and AWWU for review.  The plan shall include a detailed plan and profile of the bore to be plotted on a scale no smaller than 1” = 20’ horizontally and 1” = 10’ vertically.  This plan must also include calculations showing anticipated maximum pipe stresses during pulling, required drilling fluid pressures, and safety factors for potential drilling fluid excursions (“frac-outs”).  At a minimum the plan will provide:

1.	Ground entry angle (5-20 degrees maximum from horizontal).  Contractor has the option to decide precise angle of entry necessary to install pipe within alignment parameters shown on the Drawings.  Contractor also has the option of excavating an inclined base to allow drill head entry at an angle steeper than specified (up to 20 degrees maximum)

2.	Ground exit angle from horizontal (0-20 degrees).  Contractor has the option to decide precise angle of exit necessary to install pipe within alignment parameters shown on the Drawings.

3.	Ground exit point shall be plus or minus 3 feet transversely from the centerline of the pipeline as shown on the drawings.

4.	Profile of drilled section.

5.	Radius of curvature of the drilled hole (not to be less than 900 feet).

6.	Maximum pulling force to be exerted on the pipe during pullback for the pipe to be provided (not to exceed 110,000 pounds).

7.	Layout of rollers or dirt berms under exposed pipe during pullback. Confirm maximum spacing between rollers.

8.	The bending radius of exposed pipe entering the ground during pullback shall not be less than 900 feet for the 18” diameter pipe.

9.	Drilling fluid shall be bentonite-based and its composition shall be submitted to the Department and AWWU for review prior to use.  No fluid shall be used that does not comply with permit and current environmental regulations.

10.	Copies of sonde logs created as part of construction.

11.	Contractor will submit description of buoyancy control plan for product pipe as it is being drawn under the creek.

12.	Contractor shall prepare a work schedule that meets key target dates as agreed to with the Department and AWWU that includes the following:

i.	Site stakeout of control points.

ii.	Mobilization and rig setup.

iii.	Pipe delivery, staging and assembly.

iv.	Pipe pressure pre-testing.

v.	Pilot hole drilling.

vi.	Pre-reaming (if selected).

vii.	Reaming.

viii.	Swabbing (if selected).

ix.	Pipe pulling.

x.	Target date for exit from receiving pit.

xi.	Post-pull testing.

xii.	Site restoration and demobilization

xiii.	Drill Continuance Plan

7.	Construction

a.	General. The work shall include, but not be limited, to the following:

b.	HDD Pipe Installation. Contractor shall install the horizontally drilled section of pipe as shown on Plans.  The Plans show the desired beginning and end points for the installed sections of pipe.  The Contractor shall identify the minimum space required at each pipe entry pit, pipe staging area and pipe exit point to achieve the desired start and end points for the new pipeline.  A profile has been included which shows known existing utilities, pipes, structures, equipment and foundations overlying the desired pipe routes.  This profile is representative only and may not indicate all structures, pipes and features that are present. The contractor shall establish the recommended depth of the pipeline with the provision that it will be at a minimum depth of 18 feet under the shallowest area of the penetration, i.e., the bottom of the creek bed.

c.	Contractor’s Responsibilities. Contractor shall provide all materials, labor, tools and equipment necessary to complete the specified pipe installation and adequate protection of the work, except as noted herein.

Contractor shall employ his best efforts to maintain the pipe alignment in accordance with the Drawings, Specifications, and other Contract documents.  This will include alignment changes in the drill bore if it deviates from the specified route.

Contractor shall comply with provisions of all permits secured by the Department and AWWU for construction of the pipeline.

The Contractor shall supply storage tanks of sufficient capacity or take-away vacuum tanks to contain and transport the residual drilling fluids produced by the drilling activities.  The contractor will also insure that all return fluids during drilling operations are contained in suitable drilling entry and access pits.  The Contractor shall be responsible for cleaning up all drilling fluids lost through spillage or excursions (“frac-outs”) during drilling operations.  The Contractor shall take special care in monitoring and controlling lubricant pressures and volumes to prevent frac-outs as the drill head and reamer enter and exit the end pits at both ends of the pipe run.

The Contractor shall promptly remove from the project site and properly dispose of all drilling fluids and associated cuttings to a suitable disposal site designated by the Department and AWWU following completion of the pipe installation.

If the pipe becomes stuck in the drill hole during pullback and cannot be recovered in whole or in part, contractor shall seal the pipe and existing drill hole and repeat efforts to achieve a successful drill beginning with a new pilot hole.  Contractor shall bear all costs connected with supplying replacement pipe string as required and installing it per Plans and Specifications.

Contractor shall employ a wired sonde behind the drill head to generate a locator signal for the drill operator.  It is not expected that the contractor will encounter magnetic signal interference along the pipeline alignment caused by soil composition or nearby operating equipment.  If magnetic signal interference is encountered, Contractor shall be prepared to install a surface magnetic grid to generate a backup locator signal of suitable strength during installation of the drill and pipe strings.

Contractor shall furnish to the Department and AWWU a copy of each drilling day’s original computer printout of the drill head location during the drilling operation at a maximum spacing of 60 feet and an as-built map of the horizontally drilled section showing the “x”, “y” and “z” coordinates of the final location of the pipeline. The maximum distance between coordinate points shall be 100 feet.  Contractor shall furnish the as-built map within 30 days after project completion.  The as-built map shall have a minimum horizontal scale of 1” = 20’ and a minimum vertical scale of 1” = 100’. The survey coordinate points shall also be in table form on this map.

Contractor shall prepare a Drill Continuance Plan prior to beginning work, as stated in Part 12 Inadvertent Returns of Drilling Fluids during HDD in Subsection 627-3.10 Horizontal Directional Drilling (HDD).

d.	The Department and AWWU’s Responsibilities. The Department and AWWU shall obtain permits required for access to the assigned staging areas.

The Department and AWWU shall provide a staging area for the horizontal directional drilling machine and all related equipment necessary for completion of the project.

The Department and AWWU shall provide space for an office trailer, chemical toilet facilities and other miscellaneous structures needed as part of the pipe project.

The Department and AWWU shall assign a pipe string assembly and laydown site to be used to store unassembled pipe segments and stage assembly of pipe strings.

The Department and AWWU retains the right to employ independent quality assurance services as required to insure quality execution of the work.

The Department and AWWU shall designate a suitable disposal site for recovered drilling fluid and cuttings.

e.	Services for Construction. The AWWU shall furnish water in limited quantities from fire hydrants for the purpose of pipe buoyancy, pipe testing, wash down and cleanup.

The Department and AWWU shall provide temporary workspace for the drilling site.  Contractor shall be responsible for paying for any damage caused by Contractor’s equipment and activities in areas outside the Department/AWWU-assigned workspace.

Contractor shall supply all utility services required at the site such as compressed air, fuel, DC grid power source, electric power, shelter from weather, pipe joint fusion power, etc.

f.	 Limited and/or Restricted Access. Contractor's personnel shall wear identification tags or hardhat labels provided by the Contractor while working on this project.

g.	Receiving, Storing and Handling Materials. The 18” diameter HDPE pipe will be stored in the open in a suitable area to be designated by the Department and AWWU.  Purchase and handling of all pipe and other materials required for the work will be the responsibility of the Contractor.  This includes off-loading, transporting into storage, assembling and transporting from storage to the work area.

h.	Drawings. All drawings listed in the work description form a part of these specifications showing the extent of the work to be done under the terms of the contract.  Should a contradiction exist between the Department and AWWU's drawings, the pipe manufacturer's specifications, the ASTM HDPE fusion welding standards and the Department and AWWU's specifications, the Contractor shall consult the Department and AWWU's representative to resolve the contradiction.

8.	Pipe Materials. High-density polyethylene solid wall pipe to be used for the HDD shall comply with ASTM D 3350 and ASTM F 714.  Pipe will be 18” diameter, SDR 9.0, HDPE pipe with carbon black additive for environmental stress corrosion resistance.  Pipe and fittings shall be made from HDPE compounds conforming to ASTM D 3350, Cell Classification 445574C.

At installation, HDPE materials shall not be more than 6 months old from date of manufacture.

a.	Welding Specifications. A trained technician will perform welding by fusion.  ASTM D 2657, Standard Practice for Heat-Joining Polyolefin Pipe, as well as HDPE pipe manufacturer's instructions and recommendations shall apply.  It shall be the contractor’s responsibility to insure that each fusion weld meets minimum strength and integrity suitable to withstand tensile pulling and bending forces expected to be exerted on the pipe string during pullback.  It is recommended that the contractor make use of a commercially available fusion weld monitoring system (logger) to record fusion weld data for each fused joint so that remedial action can be taken immediately if the joint is shown to not have been welded properly.

b.	Pipe Storage and Handling. HDPE pipe shall be properly stored and handled to prevent damage in accordance with the manufacturer's recommendations and as approved by the Department and AWWU.  Damage is described as, but is not limited to, gouging, abrasion, flattening, cutting, puncturing, or ultra-violet light (UV) degradation.  Thorough inspection of the pipe materials shall be performed prior to installation.

c.	Repair and Rejection. HDPE pipe may be repaired for minor superficial damage.  Damaged liner pipe which has been penetrated over 10% of the wall thickness at either the inner or outer wall surface, shall be repaired by cutting out the damaged section and replacing it with new pipe.  All repair methods shall be submitted to the Department and AWWU for prior approval.  HDPE pipe shall be inspected for damage immediately prior to installation.  If product pipe is found to be superficially damaged, the Department and AWWU's Representative may allow the pipe to be repaired or may reject it.  Rejected liner pipe shall be replaced with a new section of liner pipe.

9.	Safety. All work performed under this contract shall be done in accordance with applicable Federal and State OSHA safety standards and Municipality of Anchorage Regulations.

10.	Soil Conditions. The soils along the proposed alignment between Point A and Point B are made of combinations of silt, clay, sand, and gravels.  The proposed pipe route has been selected to meet minimum acceptable depth of cover and also traverse soils estimated to be suitable for HDD pipe installation.

11.	Pipe Installation

a.	Procedure. Contractor shall install the specified pipeline by the horizontally drilled, directionally controlled method of construction as shown on Plan and Profile Drawings.  This method shall consist of the drilling of a small diameter pilot hole in a vertical arc from the entry point to the exit point followed by an enlarged (back-reamed) hole through which the product pipe is then pulled.  The exact method and techniques for completing the directionally drilled installation will be determined by the Contractor, subject to the requirements of these special provisions.

Contractor will at all times provide and maintain instrumentation that will locate accurately the pilot hole and measure drilling flow pressures and discharge rates.  The Department and AWWU shall have access to these instruments and their readings at all times.

Contractor shall plot the actual horizontal and vertical alignment of the pilot bore at intervals not exceeding 60 feet.  This as-built plan and profile shall be updated as the pilot bore advances.  Contractor shall employ experienced personnel to operate the directional drilling equipment and, in particular, the position monitoring and steering equipment.  No information pertaining to the position or inclination of the pilot bore shall be withheld from the Department and AWWU.  At the end of the bore the Contractor shall provide the Department and AWWU with the coordinates of the pilot hole.

The entry point for the pilot hole is shown on the Plan and Profile Drawings.  The Contractor shall establish this point and stake it in the field using experienced surveying personnel.

The desired pilot hole exit point is also shown on the Plan and Profile Drawings. The actual exit point can be within 3 feet east or west of the desired exit point.  If the pilot hole bore fails to arrive within the stated parameters, the Department and AWWU, at their discretion, can request that a new pilot bore hole be drilled.  The Contractor shall stake this point in the field using experienced surveying personnel.

The pipe alignment shown on the drawings has been set with the expectation that the hole will be drilled from Point A to Point B and that the 18” diameter product pipe will be staged between Potter Drive and Campbell Creek on the north side of Dowling Road.  The actual method and selection of drilling entry/exit procedures and locations for accomplishing the work will be left to the Contractor.

b.	Drilling Mud and Cuttings. The Contractor shall dispose of all recovered drilling fluid and cuttings at a suitable disposal site designated by the Department and AWWU.  All removal and disposal activities shall meet current environmental regulations and permit requirements (if applicable).  All collection and transportation costs for disposal shall be borne by the Contractor.

Inadvertent drilling fluid excursions (“frac-outs”) other than at the entry and exit pits shall be minimized.  Contractor shall seal and clean up all drilling fluid excursions immediately.

c.	Testing. The following criteria shall be followed in conjunction with subsection 627-3.06 TESTING WATER SYSTEM.

1.	All continuous HDPE pipe strings shall be pre-tested before installation.

2.	Testing the pipe using pressurized air is not permitted.

3.	Following assembly into a continuous string, the pipe shall be tested hydrostatically to 160 psig for a minimum duration of 4 hours and maximum duration of 8 hours without leakage prior to pullback.

4.	A water source for testing the pipe will be provided by the AWWU.

5.	Pipe may be tested hydrostatically while on skids or rollers. If the contractor decides to test the pipe on skids or rollers, he shall follow pipe manufacturer’s recommendations.

6.	Following installation of the HDPE pipe, the pipe string will again be tested to a pressure of 160 psig for a period of 4 hours.

d.	Pre-Reaming and Pullback. Pre-reaming for all pipe strings shown on the Plans shall be conducted at the discretion of the contractor.

e.	Reaming. Size and type of reamer for all pipe strings shown on the Plans shall be selected at the discretion of the contractor.

f.	Swabbing (optional). At Contractor’s option, the finished reamed hole can be swabbed to confirm that it is open and ready for product pipe.  A suitable swabbing tool will be selected consistent with soil composition along the HDD route.

g.	Pulling loads. Contractor shall be responsible for determining pulling loads required for his method of installation.  Such loads shall be minimized to prevent failure of the pipe string during installation.  A load cell between the reamer and the product pipe is recommended to monitor pulling loads in real time during pipe installation.

h	Torsional stress. A swivel connection shall be employed between the product pipe and the reamer (and back reamer, if applicable) to eliminate torsional stress on the product pipe.

i.	Buckling stress. The Contractor shall fill the underground portion of the pipe during pullback to prevent buckling and reduce buoyancy.

j.	Exposed pipe string. The exposed pipe string shall be supported on rollers, skids or soil mounds as appropriate to reduce friction resistance and pipe damage.

k.	Pull section length. If space allows, the pipe string shall be installed in one continuous pull with no tie-in welds.  If staging space is not available, tie-in welds must be minimized.

l.	Coordination of work. Most of the pipe to be installed on this project will likely be assembled on or in close proximity to private property along West Dowling Road.  All work on this project must be coordinated with the Department and AWWU with regard to scheduling the work and gaining access to third party property for pipe staging and installation.

m.	Water for drilling, testing and buoyancy control. The AWWU shall provide water from fire hydrants needed for drilling, pipe pre-testing, buoyancy control, post-testing and cleanup.

n.	Over-pulling. After the pipe string has been pulled into the reamed borehole, the pipe shall be pulled so that 10 feet of pipeline is exposed on the end of the bore.

Optional: At the Department and AWWU’s option the new pipe string can be pulled to a point 10 feet beyond the eventual underground tie-in point at the existing underground water main.

o.	Post-testing. Following installation of the pipe strings, the new pipe shall be tested at 160 psig for 4 hours.

p.	Alignment and grade. The installed pipe shall be surveyed at all exposed points.  The collected data shall be recorded in the Contractor’s field book and on the as built drawings.

q.	Testing, flushing and disinfecting. Hydrostatic testing, flushing and disinfecting of the installed pipe shall be performed as specified in subsections 627-3.06 TESTING WATER SYSTEM and 627-3.07 DISINFECTION OF WATER LINES.

r.	Work completion. If the directionally drilled pipe is not installed or the Contractor abandons the effort, the contractor shall forfeit all payment for the applicable item.

Completion and successful testing of the approved pipeline shall entitle the Contractor to full payment for applicable waterline relocation bid items.

12.	Inadvertent Returns of Drilling Fluids during HDD

a.	General

1.	The applicable regulatory agencies discussed herein are defined as follows:

i.	State of Alaska Department of Transportation & Public Facilities (Department)

ii.	State of Alaska Department of Environmental Conservation (DEC)

iii.	U.S. Environmental Protection Agency (EPA)

iv.	U.S. Army Corps of Engineers / Alaska District / Regulatory Division (Corps)

v.	Alaska Department of Fish & Game (ADFG)

vi.	Municipality of Anchorage / Watershed Management Division (MOA)

2.	An inadvertent release of drilling mud (frac-out) is considered reportable to the applicable regulatory agencies when:

i.	the inadvertent release occurs in or close to sensitive aquatic or terrestrial receptors, or

ii.	onto land and the release is in excess of 5 feet within the right-of-way, or

iii.	any size of release outside the right-of-way that may cause, is causing or has caused an adverse effect.

Depending on the circumstances of the inadvertent release, the person responsible shall immediately report the release to the applicable regulatory agencies and affected landowners.

b.	Inadvertent Release Response in Water

1.	The HDD Contractor is to stop the drilling operations immediately.

2.	The HDD Contractor or party designated to be responsible, as determined in the Drill Continuance Plan, is to contain the drilling mud and prevent further migration into the water body.  In the case of an in stream release, the downstream movement of drilling mud should be prevented if possible by isolating the release point or diverting higher velocities around the release.

3.	The HDD Contractor will immediately notify the Department and AWWU or designate who will immediately contact the Department’s project engineer and other applicable regulatory agencies.

4.	The drilling mud must be cleaned up immediately by the HDD Contractor and/or drilling mud disposal Contractor, if conditions allow, and disposed of as per local, state, and federal requirements.  If the potential exists for greater environmental impact due to the clean-up process than the presence of the drilling mud, the applicable regulatory agencies should be notified if clean-up of drilling mud is not to be conducted immediately and the rationale for the delay should be provided.  A qualified aquatic environment specialist should determine the appropriate actions to be taken and a schedule of activities to mitigate the issue.

5.	Drilling activities will not be resumed until a site-specific Drill Continuance Plan and monitoring program have been approved by the Department and AWWU.  A third party drilling or geotechnical consultant may be needed to review and assess the Drill Continuance Plan.

6.	Prepare a report summarizing the events leading up to the release as well as measures taken following the release to minimize impacts on the environment.  Submit the report to the applicable regulatory agencies within 7 days.

c.	Inadvertent Release Response on Land

1.	The HDD Contractor is to stop all operations immediately.

2.	The HDD Contractor or party designated to be responsible as determined in the Drill Continuance Plan is to contain the drilling mud and prevent further migration using berms, sandbags or other appropriate structures or materials.  Where appropriate, use vacuum truck or mud/trash pumps to recover fluids and drilling mud.

3.	The HDD Contractor will immediately notify the Department and AWWU or designate who will determine if the release is reportable (see Article 12. Inadvertent Returns of Drilling Fluids during HDD / Part a. General, for definition of reportable inadvertent release) and, if reportable, contact the applicable regulatory agencies.

4.	The drilling mud must be cleaned up immediately by the HDD Contractor and/or drilling mud disposal Contractor if conditions allow, and disposed of as specified by the Department and AWWU’s Representative.

5.	An assessment may be necessary in the unlikely event that the potential exists for greater environmental impact due to the clean-up process than the presence of drilling mud.  Involve applicable regulatory agencies in the discussion process.

6.	Drilling activities will not be resumed until a site-specific Drill Continuance Plan and a monitoring program have been approved by the Department and AWWU’s Representative.  A third party drilling or geotechnical consultant may be needed to review and assess the Drill Continuance Plan.

7.	Prepare a report summarizing the events leading up to the release as well as measures taken following the release to minimize impacts on the environment.  Submit the report to the applicable regulatory agencies within 7 days.

d.	Drill Continuance Plan. Collectively the Department, AWWU, HDD Contractor, and applicable regulatory agencies should determine the Drill Continuance Plan. Depending on the situation being encountered and the potential impacts to the environment, specialists from the applicable regulatory agencies may be needed to review and assess the plan. The Drill Continuance Plan may include each of the following four strategies.

1.	Fracture Plugging (Bridging) Agents. In certain types of formations or conditions, fracture plugging agents (non-toxic) have been utilized with limited success.  These agents include ground pieces of carpet, ground corn husks, sawdust, bentonite pellets, walnut husks, sealant or other commercially available products.  These are pumped down the drill hole and left undisturbed for a predetermined length of time where upon drilling is restarted.  If positive circulation is restored, drilling is continued using the same principles and the Drill Continuance Plan; if not, drilling is halted.

2.	Down Hole Cementing. If the fracture zone is determined to be too large for the use of plugging agents, the drill string may be inserted to a predetermine depth to allow a quick setting cement or thermal resin (non-toxic) to be pumped down-hole in sufficient quantities to seal off the problem zone. After setting up, the hole is redrilled through the sealed zone.  If no further fracturing occurs, drilling is continued using the same principles and the Drill Continuance Plan; if not, drilling is halted.

3.	Contain and Control. If the inadvertent release is on land, determined not to be causing an adverse effect and the surface migration of the drilling mud can be adequately contained and controlled, then drilling can continue with the following conditions:

i.	there are no impacts to the environment or other adverse effects. (i.e., no potential to contaminate surface or groundwater, third party property damage or safety risks to the landowner, public or animals);

ii.	the area affected by the inadvertent release is minor and limited to only one spot (affected area is less than 108 square feet);

iii.	the surface migration of the drilling mud is adequately contained (bermed with subsoil or a catch pit excavated);

iv.	the contained free drilling mud is adequately controlled (any free drilling mud migrating to the surface is immediately and continually removed for the duration of the remaining drilling phases);

v.	the site is monitored at appropriate periods during the drilling cycle and the drilling contractor reduces pump/hole pressure accordingly in order to maintain control of the amount of mud being contained (note that some release points may not need continuous monitoring since they are only prone to releases during a particular period in the drilling cycle);

vi.	the affected landowner is notified and permission for continued drilling is granted;

vii.	the plan is discussed with the applicable regulatory agencies and their approval is obtained; and

viii.	the affected site is mitigated and reclaimed to meet the DEC’s requirements for a contaminated site.

4.	Partial Hole Recovery. In the event that both of the above procedures are unsuccessful, down-hole cementing could be used to seal off a substantial portion of the existing hole back to a point where a "kick-off" can take place.  The drilling is then advanced along a different path usually at a lower elevation.  Again, careful monitoring of drilling fluids and the drill path will be carried out using the same principles and the Drill Continuance Plan; if not, drilling is halted.

5.	Hole Abandonment. In the event that none of the above procedures are successful or considered feasible, the hole will be abandoned, and a re-drill will be considered at a second location if it can be determined that more favorable geotechnical conditions exist, using the same principles and the Drill Continuance Plan.  Hole abandonment shall follow procedures established by the applicable regulatory agencies.

13.	Restoration. After completion of drilling, the Contractor shall restore entry and access pits and staging areas to their original condition or as directed by the Department and AWWU.  Contractor shall clear all work areas of debris and returned drilling fluid and dispose of same at a suitable disposal site designated by the Department and AWWU.

Contractor shall restore any areas where subsidence has occurred due to drilling activities.

Contractor shall restore entry and exits pits as soon as the work is completed.

Contractor shall restore any areas on private or public property where incidental damage may have occurred as part of performing the work.

14.	Measurement and Payment. The lump sum price shall be considered full compensation for furnishing all labor, pipe, incidental materials, tools, equipment, apparatus, and incidentals for doing all the work required.  If a separate bid item is not included, then full compensation shall be considered to be included in the bid price for the work.

The lump sum for pipeline installation shall be considered full compensation for installing all fittings, connections, seals, and special work shown on the Drawings and Specifications.  Additionally, the lump sum price shall include all labor, incidental materials, and equipment necessary for staging, fusion joining and placing of HDPE pipe and all other work necessary for the new pipe installation complete and in place.

627-4.01 METHOD OF MEASUREMENT. Delete this subsection and substitute the following:

1.	Water Conduit. Measurement for water conduit with appurtenances will be per linear foot of horizontal distance of the various sizes and classes furnished and installed as set forth in the Bid Schedule. Measurement will be from station to station as staked in the field and as shown on the plans. No deduction in length will be made for valves and fittings.

2.	Fire Hydrant Relocation.  Measurement for fire hydrant relocation shall be per each relocated hydrant.

3.	Fire Hydrant Installation or Removal.  Measurement for fire hydrant installation or removal shall be per each new hydrant assembly installed or each old fire hydrant removed.  Fire hydrant assembly includes components shown in the hydrant assembly detail on the plans.

4.	Galvanic Bag Anode. The quantity to be paid will be the actual number furnished, installed, and accepted.

5.	Butterfly Valves, Gate Valves, and Valve Boxes.  By the number of valves  and valve boxes adjusted or installed.  One adjustment includes the adjustment of the valve box one time down and up.

6.	Record Drawings. Water line record drawings will be measured by acceptance of completed As-built drawings.

7.	Temporary Water System. Measurement shall be a single lump sum for all temporary systems required, regardless of number of locations.

8.	Water Service Connection/Disconnection.  The quantity will be paid by the number of services installed or disconnected.

9.	Water Main Horizontal Directional Drilling.  Paid by lump sum, which includes 18 inch HDPE water conduit.

10.	Remove and Replace Valve Box and Lid.  Each valve box removed and replaced.  This includes excavation, backfill, labor, and obtaining new valve box from the AWWU.

11.	Abandon Water Main.  Paid by lump sum, which includes equipment, material, and labor to slurry water main as specified in subsection 627-3.01 of these special provisions.

627-5.01 BASIS OF PAYMENT. Delete the first through fifth paragraphs and substitute the following:

All labor, tools, equipment, fittings, pipe, and demolition necessary to connect new water main to the existing water mains as shown on the drawings, is subsidiary.

The contract price for Water Conduit includes trench excavation, shoring as required, bedding, backfill with native soils, compaction, pipe, fittings, tees, reducers, crosses, bends, repair of or provision of polyethylene encasement on ductile iron pipe, couplings, flushing, testing, disinfection, connection to existing mains, abandonment or removal of the existing conduit, etc.  Any excavation below plan grade approved by the Engineer shall be paid under Item 203(3) Unclassified Excavation.  Backfill and bedding to replace unsuitable material shall be paid in accordance with Section 203.  The cost for coordinating and providing trenching operations are subsidiary to the fire hydrant installation.

Measurement and payment for the guard posts shall be subsidiary to Pay Item 627(5) Fire Hydrant Installation.  No deduction will be made for guard posts not installed at the direction of the Engineer.  Labor and material for installing the tee and hydrant leg shall be subsidiary to Pay Item 627(5) Fire Hydrant Installation.

The contract price for Water Service Connection includes installation of curb stop, valve box, service pipe and connection to a new or existing water main with a service saddle, tapped, coupling or corporation stop, anode, and tape coating, as shown on the Plans.

Payment for Pay Item 627 (13B) will be held until such time that record drawings are approved by AWWU and Contractor signs final record drawings.

Repair and/or restoration of existing improvements on private property and repair of existing utilities damaged by the Contractor will not be paid for directly but will be considered subsidiary.

Traffic control required for pre-inspections and post inspections will be paid under the 643 Pay Items.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

627(1A)	16 Inch HDPE Water Conduit, SDR 11	Linear Foot

627(8-10A)	10 Inch Water Service Connection	Lump Sum

627(9A)	Install 8 Inch Gate Valve	Each

627(9B)	Install 16 Inch Butterfly Valve	Each

627(13B)	Disconnect Water Service	Each

627(16)	Abandon Water Main	Lump Sum

627(17)	Water Main Horizontal Directional Drilling	Lump Sum

627(20)	Water As Builts	Lump Sum

Replace Pay Item 627(10) with the following:

Pay Item No.	Pay Item	Pay Unit

627(10)	Remove and Replace Valve Box and Lid	Each

SECTION 635

INSULATION BOARD

Special Provisions

635-1.01 DESCRIPTION.  Replace with the following:

Furnish and install high density extruded polystyrene insulation board where shown on the Plans and where storm drain pipe has less than 4 feet of ground cover, sanitary sewer pipe has less than 8 feet of ground cover, or water pipe has less than 10 feet of ground cover.  Furnish and install insulation when vertical separation between storm drain, sanitary sewer, or water pipe is less than 3 feet.

635-2.01 MATERIALS.

Insulation Board.  Replace with the following:

Having a minimum 60 PSI compressive strength equivalent to R-20 per 4 inch thick insulation meeting ASTM C578 Type VII.  Maximum water absorption of 0.05% per ASTM C272.

635-4.01 METHOD OF MEASUREMENT.  Delete this subsection

635-5.01 BASIS OF PAYMENT.  Replace with the following:

Furnishing and installing insulation board is subsidiary to pipe pay items.

Replace Section 639 with the following:

SECTION 639

DRIVEWAYS

- Special Provision

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing  equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(1)  	Residence Driveway 	Each

639(2)  	Commercial Driveway 	Each

639(3)  	Public Approach 	Each

639(4)  	Driveway 	Each

639(6)	Approach 	Each

- R58(05/09/02)

- Special Provisions

- Replace Section 641 with the following:

- SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION.  Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.  These definitions apply only to Section 641.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

Alaska Department of Environmental Conservation (ADEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

Alaska Pollutant Discharge Elimination System (APDES). A system administered by ADEC that issues and tracks permits for storm water discharges.

Best Management Practices (BMPs).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

Clean Water Act (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

Consent Decree. The decree entered by the United States District Court for the District of Alaska on September 21, 2010, regarding compliance with the CWA and implementation of the CGP, to which the United States and the Department are parties.

Construction Activity. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and construction materials or equipment storage or maintenance (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and other industrial storm water directly related to the construction process (e.g. concrete or asphalt batch plants).

Construction General Permit (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by ADEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

Electronic Notice of Intent (eNOI). The electronic Notice of Intent submitted to ADEC, to obtain coverage under the CGP.

Electronic Notice of Termination (eNOT). The electronic Notice of Termination submitted to ADEC, to end coverage under the CGP.

Environmental Protection Agency (EPA). A federal agency charged to protect human health and the environment.

Erosion and Sediment Control Plan (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

Final Stabilization. Is defined in this section as it is defined in the CGP.

Hazardous Material Control Plan (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

Inspection.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s stormwater inspector.

Multi-Sector General Permit (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

Operator(s). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of stormwater associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

1.	The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

2.	The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

Project Zone. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Department by the Contract and are directly related to the Contract.

Support Activities including material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

Records. Any record, report, information, document, or photograph required to be created or maintained pursuant to the requirements of the Consent Decree, the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

Storm Water Discharges From Municipal Separate Storm Sewer Systems (MS4s).  A conveyance or system of conveyances including roads with drainage systems, municipal streets, catch basins, curbs, gutters, ditches, man-made channels, or storm drains that discharges into waters of the United States and is owned or operated by a public agency.

Spill Prevention, Control, and Countermeasure Plan (SPCC Plan). The Contractor’s detailed plan for petroleum spill prevention and control measures that meet the requirements of 40 CFR 112.

Spill Response Field Representative. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

Storm Water Pollution Prevention Plan Two (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related Support Activities outside the Project Zone.

Subcontractor Spill Response Coordinator. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

Subcontractor SWPPP Coordinator. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

Superintendent. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

Support Activities. See ADEC CGP definition. Further defined as construction activities in which the Department is not an operator and the activity is outside the Project Zone.

SWPPP Amendment. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager. The Contractor’s qualified representative who conducts Inspections and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP Preparer. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

Utility Spill Response Coordinator. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

Utility SWPPP Coordinator. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.  For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP) use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

1.	Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14 day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP.

2.	Hazardous Material Control Plan.  Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

3.	Spill Prevention, Control and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

4.	CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. The Contractor cannot use the SWPPP for  Support Activities outside the Project Zone where the Department is not an operator.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to ADEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and ADEC’s acknowledgement letter to the Engineer when the eNOI is submitted to ADEC.

Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to ADEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and ADEC’s acknowledgment letter, for inclusion in the SWPPP.

5.	Ending CGP Coverage. Submit an eNOT to ADEC, and submit both a copy of the signed eNOT and ADEC’s acknowledgement letter to the Department, within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met.

6.	ADEC SWPPP Review.  When CGP, Part 2.1.3 - requires ADEC SWPPP review:

a.	Transmit a copy of the Department-approved SWPPP to ADEC using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

c.	Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4 requires local government review:

a.	Transmit a copy of the Department-approved SWPPP and other information, as required, to local government, with the required fee using delivery receipt confirmation;

b.	Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

c.	Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

d.	Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

e.	Include a copy of local government SWPPP review letter in the SWPPP; and

f.	Before ending permit coverage file a project ending notification with local government and allow them to inspect the work.

8.	Modifying Contractor’s eNOI.  When required by The CGP Part 2.7, modify your eNOI to update or correct the information. Reasons for modification include change to the start or end dates, small changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or changed location of SWPPP Records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed, the original eNOI indicates disturbed area less than five acres and the project will disturb more than five acres, or a project over five disturbed acres grows by more than 50%.

641-1.04 PERSONNEL QUALIFICATIONS.  The SWPPP Preparer must meet at least one of the following qualifications:

a.	Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

b.	Current certification as AK-CESCL, and at least two years experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

c.	Professional Engineer registered in the State of Alaska with current certification as AK-CESCL

For Projects disturbing more than 20 acres, the SWPPP Preparer must also have completed a Department approved SWPPP Preparation course. Approved courses will be posted on the Department’s D&ES, Environmental website.

The Superintendent must meet the following qualifications:

a.	Current certification as AK-CESCL; and

b.	Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3

The SWPPP Manager (identified in the CGP as the Storm Water Lead) and the Storm Water Inspector must have current certification as AK-CESCL, and be knowledgeable in the requirements of that position as defined in the CGP, Appendix C, Qualified Person. The SWPPP Manager has authority to work in each position concurrently.

The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principals and practices of treatment systems in general, and the operation of the ATS in particular. Minimum experience to be 6 months field experience or completion of an ATS manufacturer’s training course.

The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

a.	CPESC, Certified Professional in Erosion and Sediment Control;

b.	CISEC, Certified Inspector in Sediment and Erosion Control; or

c.	CESCL, Washington Department of Ecology Certified Erosion and Sediment Control Lead (Through Nov. 30, 2011 only. Will not be accepted as an equivalent substitution after Nov. 30, 2011).

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

1.	eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12.2. Signature and certification authority for the eNOI and eNOT cannot be delegated.

2.	Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Engineer will provide the Department’s delegation Form 25D-107, which the Contractor must include in the SWPPP.

3.	Subcontractor Certification. Subcontractors must certify that they have read and will abide by the CGP and the conditions of the project SWPPP.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

1.	The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

2.	The Contractor is responsible for permitting and permit compliance outside the Project Zone for Support Activities. The Contractor has sole responsibility for compliance with ADEC and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

3.	An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

4.	The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas or Support Activities outside the Project Zone; and

b.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY RELOCATION COVERAGE.  A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06.  The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project.  A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work.  Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

1.	SWPPP Preparer and Pre-Construction Site Visit.  Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

a.	Opportunities to phase construction activities;

b.	Appropriate BMPs and their sequencing; and

c.	Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

2.	Developing the SWPPP.  Use the Department’s ESCP and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP framework according to the ADEC SWPPP template with additional information as required. Include information required by the CGP, Part 5, and this specification.

When using the SWPPP template:

	In Section 3 (Good Housekeeping), add a subsection to describe dedicated asphalt plants and/or dedicated concrete plants, give their locations and identify the BMPs that will be used to minimize pollutants from them.  If there are no dedicated asphalt or concrete plants, then state that in the SWPPP.

·	Include the following appendices:

·	Appendix A	–	Site Maps and Drawings

·	Appendix B	–	BMP Details

·	Appendix C	–	Project Schedule

·	Appendix D	–	Supporting Documentation: TMDLs, Endangered Species, & Historical Properties

·	Appendix E	–	Project Permits

·	Appendix F	–	Delegation of Authority

·	Appendix G	–	Subcontractor Certifications/Agreements

·	Appendix H	–	Construction General Permit

·	Appendix I	–	Notice of Intent and Delivery Confirmation, Letter from ADEC, Notice of Termination (Include both Department’s and Contractor’s)

·	Appendix J	–	Monitoring Plan (If Applicable) and Reports

·	Appendix K	–	SWPPP Preparer’s Site Visit

·	Appendix L	–	Hazardous Material Control Plan (HMCP)

·	Appendix M	–	Personnel Qualifications and Training Certificates for:

○	Superintendent

○	SWPPP Preparer

○	SWPPP Manager/Storm Water Lead/Inspector

○	Contractor’s ATS Operator

○	Department’s Project Engineer and Inspector(s)

○	Qualified personnel must be described in a list with names and dates in positions

·	Appendix N	–	Training Log

·	Appendix O	–	Corrective Action Log

·	Appendix P	–	Grading and Stabilization Activities Log

·	Appendix Q	–	Rain Record

·	Appendix R	–	Inspection Reports

·	Appendix V	–	Monitoring Reports

·	Appendix W	–	Antidegradation Analysis

·	Appendix X	–	Dewatering Permit

Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

	SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

	SWPPP Certification for DOT&PF (25D-109)

	SWPPP Delayed Action Item Report (25D-113)

Use the following Department forms for recording information in the SWPPP:

	SWPPP Amendment Log (25D-114)

	SWPPP Certification for Contractor (25D-111)

	SWPPP Construction Site Inspection Report (25D-100)

	SWPPP Corrective Action Log (25D-112)

	SWPPP Daily Record of Rainfall (25D-115)

	SWPPP Delegation of Signature Authority – Contractor (25D-108)

	SWPPP Grading and Stabilization Activities Log (25D-110)

	SWPPP Pre-Construction Site Visit (25D-106)

	SWPPP Project Staff Tracking (25D-127)

	SWPPP Subcontractor Certification (25D-105)

	SWPPP Training Log (25D-125)

SWPPP Forms are at:  http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

3.	SWPPP Considerations and Contents.

The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Support Activities outside the Project Zone must have permit coverage, using separate SWPPP2s, and separate Contractor Inspections.

The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

a.	Over which each operator has operational control; and

b.	Where the Department and Contractor are co-operators.

For work outside the Project Zone the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

a.	Dedicated to the Project and where the Department is not an operator; and

b.	Not dedicated to the project, but used for the project.

Develop the SWPPP according to the requirements of the CGP and this specification, and account for the Contractor’s construction methods and phasing.

Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and all temporary and permanent stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words and drawings as appropriate. Provide a citation to the BMP Manual or publication used as a source for the BMP, including the title of the BMP Manual or publication, the author (individual or agency), and date of publication. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment, and grading activities.

Identify in the SWPPP whether Inspections are conducted:

a.	Areas where the mean annual precipitation is between 14 and 40 inches: once every seven (7) days;

b.	Areas where the mean annual precipitation is 40 inches or greater: once every seven (7) days, and twice every seven days during periods of relatively continuous precipitation or sequential storm events.

Linear Project Inspections, as per CGP 6.5, are prohibited unless permitted by the Project Engineer.

The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the Consent Decree, CGP and this specification. See Subsection 641-3.03 for more information.

4.	Recording Personnel and Contact Information in the SWPPP.

Include in the SWPPP, Records of the AK-CESCL cards or certificates for the Superintendent and SWPPP Manager/Storm Water Lead, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager; record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24 hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24 hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, Records of the AK-CESCL cards or certificates of storm water inspectors, and ATS operators. Record their beginning and ending dates.

The Department will provide Records of AK-CESCL cards or certificates for the Project Engineer and the Stormwater Inspectors, and names and dates they are acting in that position. Include the Department’s Records in the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.  Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, and under equipment during maintenance or repairs.

Use secondary containment under all stationary equipment (equipment that does not have a seat for driving) that contains petroleum products. Use secondary containment under pumps, compressors, and generators.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up of spills or contaminated surfaces must be initiated immediately and completed as soon as practicable.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.  Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

- Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

- Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP and the Consent Decree, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP and the Consent Decree.

The Superintendent may assign certain duties to the SWPPP Manager; those duties may include:

1.	Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

2.	Ensuring the control of erosion, sedimentation, or discharge of pollutants;

3.	Directing and overseeing installation, maintenance, and removal of BMPs;

4.	Performing Inspections; and

5.	Updating the SWPPP including adding amendments and forms.

The SWPPP Manager has authority to work in the following positions named in the CGP, Appendix C, Qualified Person: Storm Water Lead (CGP position equivalent to SWPPP Manager), and Storm Water Inspector. The SWPPP Manager has authority to work in all the position of ATS Operator if they meet the knowledge and experience qualifications listed in 1.04..

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.  Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

·	Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

·	Use soil stabilization material as specified in Section 727.

·	Use silt fences as specified in Section 729.

·	Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

·	Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS. The Contractor must be familiar with the requirements of the CGP because Contractor’s employees will be conducting duties that relate to compliance with the CGP.

641-3.01 CONSTRUCTION REQUIREMENTS.  Comply with the SWPPP and CGP requirements.

- Before Construction Activity may Begin.

a.	Confirm the following:

1)	The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP, and the SWPPP must be developed (or amended) with findings from the visit;

2)	The SWPPP must be approved by the Engineer;

3)	The Contractor must be authorized to begin by the Engineer;

4)	The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the ADEC website; and

5)	The Department approved SWPPP must be submitted to ADEC and Local Government (when required).

b.	Post notices containing the following information:

1)	Copy of all eNOIs related to this project;

2)	Name and 24 hour phone number of SWPPP Manager; and

3)	Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes, for instance if the location of the SWPPP or contact person changes during the winter.

c.	Install an outdoor rain gauge per manufacturer’s guidance, in a accessible location on the Project.

d.	Delineate the site for both land disturbing activities and areas that will be left undisturbed. Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

The CGP Part 4.10.2 allows winter construction of ice roads or the placement of sand or gravel on frozen tundra with no excavation or potential to pollute waters of the U.S., without submitting an eNOI. The Contractor is responsible for resulting erosion or sediment runoff during spring thaw and summer. The CGP Part 4.10.3 allows cutting of trees and brush while the ground is frozen, without disturbing the vegetative mat, prior to submitting an eNOI.

- During Construction.

Make copies of the applicable portions of the SWPPP available to subcontractors and utility companies before they begin soil disturbing activities. Inform subcontractors and utility companies of amendments that affect them in a timely manner. Ensure all subcontractors who engage in soil-disturbing activities understand and comply with the SWPPP and the CGP, and have signed a SWPPP Subcontractor Certification, Form 25D-105, before they conduct the activity. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Provide SWPPP information to utility companies. Coordinate with subcontractors and utility companies doing work in the Project Zone so that BMPs, including temporary and permanent stabilization, are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures. Document on the SWPPP Training Log. Form 25D-125, the dates and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Do not install concrete washout containment within 100 feet of wetlands and/or other water bodies.

Fuel in designated areas. Place absorbent pads or other suitable containment under fill ports while fueling, and under equipment during maintenance or repairs. Install secondary containment under all stationary equipment that contains petroleum products.

Comply with requirements of the HMCP and SPCC Plan, and all local, state and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

3.	Pollutant and Hazardous Materials Reporting Requirements.

If there has been an incident of non-compliance with the CGP that may endanger health or the environment, immediately report the incident to ADEC according to the CGP, Appendix A, Part 3.0. Notify the Engineer immediately and to the extent possible coordinate reports to ADEC with the Engineer. The report must include:

·	A description of the noncompliance and its causes;

·	The exact dates and times of noncompliance ;

·	If not yet corrected the anticipated time the project will be brought back into compliance; and

·	The corrective actions taken, or planned, to reduce, eliminate and prevent reoccurrence.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law. Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies. See CGP Part 4.8.

4.	Corrective Action and Maintenance of BMPs.

a.	Implement corrective action:

1)	If an incident of non-compliance with the SWPPP, or CGP is identified;

2)	If an Inspection identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

3)	If the Engineer determines the SWPPP or any part of the SWPPP is ineffective in preventing the erosion, sedimentation, or the discharge of pollutants;

4)	If a required BMP was never installed, was installed incorrectly, or not in accordance with the CGP Part 4.0;

5)	If any BMP is not operating as intended, or has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

6)	Before sediment or debris fills a BMP to the percentage of design capacity or available storage allowed by the CGP (or manufacturer’s specifications or SWPPP requirements, whichever is lower);

7)	Whenever there is a change in conditions, design, construction, operation, or maintenance that could result in erosion, sedimentation, or the discharge of pollutants;

8)	If a prohibited discharge as specified in CGP Part 4.6 is occurring or will occur; or

9)	If there are accumulations and tracking of sediment or other pollutants, in or near any storm water conveyance channels, on roadways or parking lots within and adjacent to the project zone, in the immediate vicinity of control measures, at discharge points or entry points into the storm sewer system, or in other areas within the project zone.

b.	Implement corrective actions so that all of the following time requirements are satisfied:

1)	Conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

2)	Corrective action is completed before the next storm event;

3)	Corrective action is completed in time to protect water quality; and

4)	Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer, and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action.

Train subcontractors to identify conditions that require corrective action.  Subcontractors are required to notify the Contractor within 24 hours of becoming aware of a condition(s) that requires corrective action.

5.	Stabilization.

Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

a.	As soon as practicable;

b.	As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

c.	As identified in the SWPPP.

Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

Temporary or Permanent Seeding.

When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community the hydro-seeder must be located at the project.

Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the Contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

Stream By Pass.

When installing a culvert or other drainage structure where stream bypass is not used, install temporary or permanent stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants.

Install temporary and permanent stabilization:

a.	At the culvert or drainage structure inlet and outlet; and

b.	In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install permanent stabilization:

a.	At the inlet and outlet of the culvert, drainage structure, or bridge;

b.	In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

c.	Under the bridge.

6.	Ending CGP Coverage and BMP Maintenance.

The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

a.	Land disturbing activities have ceased;

b.	Final Stabilization has been achieved (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

c.	Temporary BMPs have been removed.

After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

a.	Send written notice to the Contractor with the date that the conditions were met;

b.	Submit an eNOT to ADEC; and

c.	Provide a copy of the eNOT and ADEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to ADEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to ADEC, and insert copies of the Department’s and the Contractor’s eNOTs with ADEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and ADEC’s acknowledgement letter to the Department within 30 days of receiving them.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments and appendices, to the Engineer when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.  The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP and the Consent Decree. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown, but this will require updating on-site posted notices. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or ADEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them. The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies.   See CGP Parts 5.10, 6.6 and 9.4.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.  Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Activities Log, and SWPPP Daily Record of Rainfall forms. For active projects update the Records daily.

1.	Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP:

a.	Every seven (7) days in areas where the mean annual precipitation is between 15 and 40 inches,

b.	Areas where the mean annual precipitation is 40 inches or greater, once every seven (7) days, and twice every seven days during periods of relatively continuous precipitation or sequential storm events.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s stormwater inspector jointly, unless impracticable. For this paragraph, “impracticable” means when both inspectors must fly to a remote area in the winter or when one inspector is sick or unable to travel to the site due to weather.  When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

2.	Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Unless otherwise directed by the Engineer, insert a Complete-by-Date for each corrective action listed that is (1) a date that complies with the time requirements listed in Subsection 641-3.01.4, or (2) seven days from the date of the Inspection, whichever is sooner. Provide a copy of the completed, unsigned Inspection Report to the Engineer by noon of the day after inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an addendum that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the addendum.

3.	Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

4.	Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

Inspection frequency during winter work or seasonal suspension of work may be reduced to at least one Inspection every 30 days if approved by the Engineer and the entire site is temporarily stabilized.

The Engineer may waive winter Inspection requirements 14 days after the freeze-up.  Inspections must resume inspections 21 days before thawing conditions are expected to result in a discharge, if all the following requirements are met:

a.	Frozen conditions are anticipated to continue for more than one month; and

b.	Soil disturbing or soil stabilizing activities have been suspended.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

5.	Stabilization before Seasonal Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to seasonal thaw. Seasonal thaw is the annual (first) recurrence of snow and ice melting after a prolonged period of freezing conditions.

6.	Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

7.	Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

8.	SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log, Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

a.	Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

b.	If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

c.	Whenever an Inspection identifies a problem that requires additional or modified BMPs

d.	Whenever a BMP is modified during construction, or a BMP not shown in the original SWPPP is added;

e.	If the Inspection frequency is modified (note beginning and ending dates); or

f.	When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Do not record removal of BMPs as amendments to the SWPPP. See Subsection 641-3.03.9 for documenting removal of BMPs.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10.	Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of discovery.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP, or overdue maintenance (after a sediment trap exceeds 50% of design capacity) is a corrective action and must be documented on the Corrective Action Log. Do not record removal of BMPs on the Corrective Action Log.

After each Inspection Report has been signed and certified, update the corrective action log with the date of inspection and include all proposed corrective actions noted on the Inspection Report.

After the corrective action has been accomplished, note the action taken,  if a SWPPP amendment was needed, and date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11.	Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12.	Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

641-3.04 FAILURE TO PERFORM WORK.  The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, Consent Decree or SWPPP, that may endanger health or the environment. If the suspension is to protect workers, the public, or the environment from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions.

1.	If the Contractor fails to take the corrective action within the specified time, the Engineer may:

a.	Suspend the work until corrective action is completed;

b.	Withhold monies due the Contractor until corrective action is completed;

c.	Assess damages or equitable adjustments against the Contract Amount; and

d.	Employ others to perform the corrective action and deduct the cost from the Contract amount.

2.	Reasons for the Engineer to take action under this section include, but are not limited to, the Contractor’s failure to:

a.	Obtain appropriate permits before Construction Activities occur;

b.	Perform SWPPP Administration;

c.	Perform timely Inspections;

d.	Update the SWPPP;

e.	Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms  to the Engineer;

f.	Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

g.	Perform duties according to the requirements of this Section 641; or

h.	Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work under this subsection.

641-4.01 METHOD OF MEASUREMENT.  Section 109.

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

The total value of this Contract will be adjusted as specified herein.  Withholding will be determined by the Department and assessed under Pay Item 641(6) SWPPP Price Adjustment, as follows:

TABLE 641-1 BMP VALUES

- RESERVED -

TABLE 641-2 EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

- RESERVED -

1.	Fines and Penalties:  A Price adjustment equal to any penalties and fines levied against the Department by local, state, or federal agencies for pollutant violations, including violations of the CWA and the CGP, except when due to Department negligence. An amount equal to the anticipated penalties and fines for the violation or violations, excluding any due to negligence by the Department, will be withheld until the actual cost of the penalties and fines is known.  Anticipated penalties and fines will be determined by the Engineer.  The Contractor is also responsible for the payment of penalties and fines levied against the Contractor.

2.	Failure to perform Inspections:  By each 24 hour period, that a required SWPPP inspection is delayed or is not signed, certified, or completed in accordance with the schedule identified in the approved SWPPP a price adjustment of $750 will be assessed.

3.	Failure to perform Corrective Action.  By each 24 hour period following 24 hours after written notice by the Engineer, per occurrence, a price adjustment of $750 will be assessed where the Contractor:

·	fails to complete SWPPP administrative requirements as identified in the Contract or the CGP,

·	fails to initiate work required by the SWPPP, or

·	fails to initiate corrective action to respond to a deficiency noted during an inspection or by the Engineer.

The same deficiency remaining uncorrected will be considered an additional occurrence for each additional 24 hour period, without requiring additional written notice by the Engineer.

Item 641(1) Erosion, Sediment and Pollution Control Administration. At the Contract lump sum price for administration of all work under this Section. Includes, but is not limited to, SWPPP and HMCP and SPCC Plan preparation, agency fees for SWPPP reviews, SWPPP Manager (when not included as a separate Pay Item under 641(7)) SWPPP amendments, pre-construction Inspections, Inspections, monitoring, reporting, and Record keeping or copying Records related to the SWPPP and required by the CGP, and Record retention.

Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Pay Item 641(1) Erosion, Sediment and Pollution Control Administration.

Item 641(2) Temporary Erosion, Sediment and Pollution Control. At the contingent sum prices specified for all labor, supervision, material, equipment, and incidentals to install, maintain, remove and dispose of approved temporary erosion, sedimentation, and pollution control BMPs required to implement the SWPPP and SPCC Plan.

Item 641(3) Temporary Erosion, Sediment and Pollution Control. At the Contract lump sum price for all labor, supervision, material, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs identified in the SWPPP and SPCC Plan.

Item 641(4) Temporary Erosion Sediment and Pollution Control Additives. At the contingent sum prices specified in the Directive to authorize the work, for all labor, supervision, materials, equipment, and incidentals for extra, additional, or unanticipated work, to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(5) Temporary Erosion Sediment and Pollution Control by Directive. At the contingent sum prices specified in the Directive using time and materials to authorize the work, for all labor, supervision, materials, equipment, and incidentals to install, maintain, remove and dispose of temporary erosion, sedimentation, and pollution control BMPs. Prices for this item will be by time and materials according to Subsection 109-1.05, or by mutual agreement between the Engineer and Contractor.  All additional Erosion, Sediment, and Pollution Control Administration necessary due to this item will not be paid for separately but will be subsidiary to other bid items.

Item 641(6) SWPPP Price Adjustment.  Withholding according to Section 641-3.04, equal to any penalties and fines levied against the Department by local, state, or federal agencies for pollutant violations, including violations of the CWA, CGP, and any other Permit, except when due to the Department’s sole negligence. The Contractor is also responsible for the payment of any and all penalties and fines levied against the Department or Contractor by entities (including agencies) other than the Department.

The Department will not release performance bonds until penalties and fines, assessed according to Section 641, are paid to the Department; and all requirements, according to Subsection 103-1.05, are satisfied.

Item 641(7) SWPPP Manager. At the Contract lump sum price for a SWPPP Manager that conforms to this specification. When Item 641(7) appears in the Bid Schedule, the SWPPP Manager must be a different person than the superintendent, and must be on-site during construction activity with duties and authority described in Subsection 641-2.04. When Item 641(7) does not appear in the Bid Schedule, the SWPPP Manager is subsidiary to Item 641(1).

Subsidiary Items.  Temporary erosion, sediment, and pollution control measures that are required outside the Project Zone are subsidiary. Work required by the HMCP and SPCC Plan including hazardous material storage, containment, removal, cleanup and disposal, are subsidiary to Item 641(1) Erosion, Sediment and Pollution Control Administration.

Work under other pay items. Work that is paid for directly or indirectly under other pay items will not be measured and paid for under Section 641. This work includes but is not limited to:

a.	Dewatering;

b.	Shoring;

c.	Bailing;

d.	Permanent seeding;

e.	Installation and removal of temporary work pads;

f.	Temporary accesses;

g.	Temporary drainage pipes and structures;

h.	Diversion channels;

i.	Settling impoundment; and

j.	Filtration.

Permanent erosion, sediment and pollution control measures will be measured and paid for under other Contract items, when shown on the bid schedule.

Work at the Contractor’s Expense.  Temporary erosion, sediment, and pollution control measures that are required due to carelessness, negligence, or failure to install temporary or permanent controls as scheduled or ordered by the Engineer, or for the Contractor’s convenience, are at the Contractor’s expense.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion, Sediment, and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion, Sediment, and Pollution Control	Contingent Sum

641(3)	Temporary Erosion, Sediment, and Pollution Control	Lump Sum

641(4)	Temporary Erosion, Sediment, and Pollution Control Additives	Contingent Sum

641(5)	Temporary Erosion, Sediment, and Pollution Control by Directive	Contingent Sum

641(6)	SWPPP Price Adjustment	Contingent Sum

641(7)	SWPPP Manager	Lump Sum

CR641-072211

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-2.01 MATERIALS.  Add the following:

4.	Digital Measuring Instrument:  Nu-metrics, Nitestar DMI (www.nu-metrics.com)

***deleted***

Standard Modifications

642-3.04 OFFICE ENGINEERING.  Delete third sentence and replace with:

Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.

E53(05/01/07)

- SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.01 DESCRIPTION.  Add the following:

Additional work:

	Illuminate construction activities listed in Table 643-3, Night Work Illumination Level, and Area of Coverage, during hours of night work on roads open to the public inside the project limits.

ES14-031506

Add the following:

Pay Item 643(25A) Traffic Control - Roadway and Pay Item 643(25B) Traffic Control - Trail shall include all associated traffic control devices as shown on the J Sheets.

643-1.02 DEFINITIONS. Add the following paragraphs after paragraph titled “Construction Phasing Plan”:

Balloon Light:  Light surrounding’s by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The top half of the balloon enclosure shall be constructed of an opaque material.

Night Work:  Work occurring between sunset and sunrise on all days, except the “No Lighting Required” period shown in Table 643-2, Night Work Lighting Requirements.

TABLE 643-2

NIGHT WORK LIGHTING REQUIREMENTS

| Latitude (degrees) | No Lighting Required |  | Nearby Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| < 61 | Lighting Required All Year |  | Everything South of Hope |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |
| 62 | June 2 | July 13 | Wasilla, Palmer, Glennallen, Talkeetna |
| 63 | May 27 | July 17 | Cantwell, Paxson, McGrath |
| 64 | May 22 | July 21 | Delta Junction, Nome, Tok |
| 65 | May 18 | July 25 | Fairbanks |
| 66 | May 14 | July 29 | Circle |
| 67 | May 10 | August 2 | Coldfoot, Kotzebue |
| 68 | May 7 | August 6 | Galbraith Lake |
| 69 | May 3 | August 9 | Happy Valley |
| 70 | April 30 | August 12 | Deadhorse |
| 71 | April 27 | August 15 | Barrow |
| 72 | April 24 | August 19 |  |

ES14-031506

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following:

A waiver may be requested, in writing, of regulation 17 AAC 25 regarding oversize and overweight vehicle movements inside the project limits.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic inside the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum 12 foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control Plan shall specify the traffic control devices required for these operations.

Add the following:

Road Closures and Major Traffic Sequencing (events).  Submit a written request to the Engineer for review and approval of each proposed event and event date.  Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections.  The proposed event date will be no less than 14 days from the date of written approval.

CR6431-032611

643-1.04 WORKSITE SUPERVISOR.

1.	Qualifications. Replace with the following:

Qualifications.  The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements.  The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, your proposed operations, and certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-124 that the Worksite Traffic Supervisor is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this Section.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

CR6432-110410

2.	Duties.  Add the following:

I.	Supervise lighting of Night Work.

ES14-031506

Add No. 3:

3.	Authority.	The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-2.01 MATERIALS.

4.	Portable Concrete Barriers.  Add the following:

Use reflective sheeting that meets AASHTO M 268 Type III, IV or V.

10.	Temporary Crash Cushions.  Replace with the following:

Temporary Crash Cushions.  Must have FHWA Acceptance letter for National Cooperative Highway Research Program (NCHRP) 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3.  Use reflective sheeting that meets AASHTO M 268 Type III, IV or V.  Application of crash cushion must be appropriate for the intended use and be installed per manufacturer's recommendation.  Temporary crash cushions used as rail or barrier end treatments must be redirective.  Temporary crash cushions that are barrels or barricade filled with sand or water are considered nonredirective and may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

CR6432-110410

12.	Portable Changeable Message Board Sign.  Replace with the following:

Portable Changeable Message Board Sign.  Use new truck or trailer mounted portable changeable message board signs with self contained power supply for the sign and with:

a.	Message sign panel large enough to display 3 lines of 18 inch high characters.

b.	Eight character display per message module.

c.	Fully programmable message module.

d.	Remote control cellular, wireless radio frequency (RF), landline.

e.	Waterproof, lockable cover for the controller keyboard.

f.	Capacity for electric/hydraulic sign raising or lowering.

g.	Radar over speed detection.

h.	Variable flash and sequence rates.

i.	Light emitting diode (LED) display, using Institute of Transportation Engineers (ITE) amber/yellow

j.	The capacity for a minimum of 150 pre-programmed messages.

k.	Battery-Pack Operation Duration:  minimum of 55 hours under full load.

l.	Power chords shall comply with the National Electrical Code (NEC) Article 600.10 Portable and Mobile Signs, paragraph 600.10(c) (2) ground fault circuit interrupter (GFCI).  The chord will have integral GFCI protection located either in the attachment plug or 12 inches or less from the plug.

CR6431-032611

13.	Plastic Safety Fence.  Replace a., b., and c. with the following:

a.	"Safety Fence" by Jackson Safety, Inc., Manufacturing and Distribution Center, 5801 Safety Drive NE, Belmont, Michigan, 49306.  Phone (800) 428-8185.

b.	"Flexible Safety Fencing" by Carsonite Composites, LLC, 19845 U.S. Highway 76, Newberry, South Carolina, 29108.  Phone (800) 648-7916.

c.	"Reflective Fencing" by Plastic Safety Systems, Inc., 2444 Baldwin Road, Cleveland, Ohio 44104.  Phone (800) 662-6338.

16.	Flagger Paddles.  Replace the last sentence with the following:

Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.

Add No. 17:

17.	Truck Mounted Attenuator (TMA).  The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer's recommendations.  The TMA shall comply with NCHRP 350 or MASH, Test Level 3 requirements.

CR6432-110410

Add No. 18:

18.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

CR6431-032611

Standard Modification

Replace Subsection 643-2.02 CRASHWORTHINESS with the following:

643-2.02 CRASHWORTHINESS.  Submit documentation, by the method indicated, that the following devices comply with the requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or Manual for Assessing Safety Hardware (MASH), Test Level 3 on the given schedule.

Submit documentation of compliance to the Engineer before installing devices on the project.

| Work Zone Traffic Control Device Compliance with NCHRP 350 or MASH |  |  |
| --- | --- | --- |
| Category | Devices | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |
|  | Portable concrete barriers | FHWA acceptance letter specifying the Test Level required in the Plans or Specifications. |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3.  This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

| Device | Composition | Weight | Height |
| --- | --- | --- | --- |
| Cones | Rubber | 20 lb. | 36 in. |
|  | Plastic | 20 lb. | 48 in. |
| Candles | Rubber | 13 lb. | 36 in. |
|  | Plastic | 13 lb. | 36 in. |
| Drums | Hi Density Plastic | 77 lb. | 36 in. |
|  | Lo Density Plastic | 77 lb. | 36 in. |
| Delineators | Plastic or Fiberglass | N/A | 48 in. |

E77-100410

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

E90-100410

Add the following:

Where construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business access(s) during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:

Where specified in the Plans, Specifications, Special Provisions, and or the TCP:  traffic may be maintained on a continuous gravel surface.

1.		Gravel Surface Not Specified.

a.	Through traffic shall not traverse more than two gravel sections of roadway in any given period.

b.	Pavement Break(s) for Culvert or Utility Work:  Patch pavement breaks(s), with hot mix asphalt, not more than 48 hours after removing the existing pavement.

c.	When approved by the Engineer.

Pave lanes next to the median first.

CR6431-032611

Standard Modification

Replace Subsection 643-3.03 PUBLIC NOTICE with the following:

643-3.03 PUBLIC NOTICE.  Make sure the Worksite Traffic Supervisor gives a minimum of 3 days notice before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

	Alaska Carriers Association

	Alaska Trucking Association

	Alaska State Troopers

	Division of Measurement Standards

	Local Police Department

	Local Fire Department

	Local Government Traffic Engineer

	School and Transit Authorities

	Local Emergency Medical Services

	Local Media (newspapers, radio, television)

	Railroads (where applicable)

	U.S. Postal Service

	Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.  Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent.  Tell them to use these numbers to alert you when emergency vehicles must pass through the project.  When notified of emergencies, use all equipment and make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator System for selected projects.  Check the special provisions for those requirements.

E78-100410

643-3.04 TRAFFIC CONTROL DEVICES.  Replace paragraphs 6 and 7 with the following:

Use only traffic control devices that meet the requirements of the "Acceptable" category in the American Traffic Safety Services Association (ATSSA) "Quality Guidelines for Temporary Traffic Control Devices" and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project.  Stock repair parts for each Temporary Crash Cushion used on the project.  Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware.  All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the Plans, Specifications, and approved TCPs until permanent roadside safety hardware is installed.  All temporary roadside safety hardware shall meet NCHRP 350 or MASH, Test Level 3 unless otherwise noted.

CR6432-110410

Replace paragraph 8 with the following:

Items paid under this Section remain the Contractor’s property unless stated otherwise.  Remove them after completing the project.

1.	Embankments.  Add the following:

Close trenches and excavations at the end of each continuous work shift, except as indicated by the Engineer.

3.	Fixed Objects.  Add the following:

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

4.	Flagging.  Replace with the following:

Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone.  The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

a.	Flagging Level I Certification by IMSA (International Municipal Signal Association)

b.	Flagger Certification by ATSSA (American Traffic Safety Services Association)

c.	Traffic Control Supervisor, ATSSA

d.	Work Zone Safety Specialist, IMSA

e.	ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned posts at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements.  Remove, fully cover, or lay down flagger signs when no flagger is present.  Keep the flaggers' area free of encumbrances, such as parked vehicles, so that flaggers can be seen easily.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer's written approval before flagging signalized intersections.  When you flag a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode.  Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer.  Get their written approval in advance.  Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

6.	Street Sweeping and Power Brooming.  Replace with the following:

Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material.  Use equipment for brooming and sweeping as recommended by the manufacturer and the following:

Dirt, dust and construction materials, mobilized as a result of power brooming and or sweeping, shall not be pushed, ejected, thrown or drift beyond the lesser of, 2 feet from the equipment perimeter or the edge of the paved surface.

All equipment shall operate to typical industry standards.  Maintain equipment to operate as designed by the manufacturer.  Equipment will employ safety equipment, warning lights, and other as required by the Specifications and these Special Provisions.

Sweeper and Broom Options:  Table 643-4, Traffic Control Rate Schedule, Street Sweeping.

a.	Regenerative Sweeper:  Sweeper that blows a stream of air at the paved surface causing fine particles to rise and be caught through a vacuum system.

b.	Vacuum Sweeper:  Sweeper that creates a vacuum at the paved surface sucking dirt, dust, and debris into the collection system.

c.	Mechanical Broom Sweeper:  Sweeper designed to pick up and collect larger size road debris, stones and litter, etc.  In addition to the requirements noted in these Specifications, use of a mechanical broom sweeper requires the Engineer to approve the sweeper for the intended use.

d.	Power Broom:  Power brooming that wets, pushes and or ejects loose material directly into an attached collection/pickup container may be used when approved by the Engineer.  The added moisture will be contained to the paved roadway surface.

Dry Power Brooming is not permitted.  Power brooming without direct/immediate means of collection/pickup is not permitted.

CR6431-032611

Add No. 9:

9.	Truck Mounted Attenuator (TMA).  TMAs are mounted on the rear of work vehicles.  TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer's recommendations.  TMA shall have an adjustable height so that it can be placed at the correct elevation during usage and to a safe height for transporting.  Approach ends of TMAs shall have impact attenuator markings in accordance with the MUTCD.  Do not use a damaged attenuator in the work.  Replace at your expense, an attenuator damaged from an impact during work.

Add No. 10:

10.	Parallel Guardrail Terminal.  The price listed in the Traffic Control Rate Schedule, Table 643-4, will be full compensation for the purchase, installation, maintenance during construction, removal, and salvaging the Parallel Guardrail Terminal unit(s).  Deliver the salvaged unit(s) to the nearest ADOT & PF Maintenance & Operations yard or as directed by the Engineer.

CR6432-110410

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with:

When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to Subsection 105-1.01, Authority of the Engineer.

Add the following after the second sentence:

In no case shall this time exceed 24 hours.

CR6431-032611

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following in the 2nd paragraph after the 2nd sentence:

Temporary crash cushions required to protect motorists from incomplete guardrail installations, as described in Section 606-5.01 is also an unauthorized lane reduction.

CR6432-110410

Add the following after the 3rd paragraph:

Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, Adjustment Rates, for the time the roadway or pedestrian facility is in an unacceptable condition.

Replace Table 643-1 with the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0 – 5,000 | $ 30 |
| 5,000 + | $ 40 |

643-3.08 CONSTRUCTION SEQUENCING.  Replace the last sentence with:

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Monday through Friday:  0530 hrs to 0800 hrs and 1630 hrs to 1900 hrs.

2.	Around any Holiday:

a.	If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 hrs on the Friday before the holiday to 0300 hrs on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 hrs on the Tuesday before the holiday to 0300 hrs on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday, or Saturday, the above stipulations apply from 1200 hrs on the day before the holiday to 0300 hrs on the Monday after the holiday.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations, a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1320 feet) of traffic detained, will be allowed for motorists, except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

3.	Road Closures: Two weekend closures will be allowed at the intersection of C Street and Dowling Road.  Two weekend closures will be allowed at the intersection of Old Seward Highway and Dowling Road.  A full road closure will be allowed for 120 days on Dowling Road from Potter Drive to Old Seward Highway.  Local traffic shall be maintained.  Within this closure, the proposed bridge shall be completed and all road work shall be complete to the top of the asphalt treated base layer.

643-3.09 INTERIM PAVEMENT MARKING.  In the second paragraph, delete the words:

“or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:

Apply final pavement markings according to Subsection 670-3.01, Construction Requirements, of these Special Provisions.

CR6431-032611

Add the following Subsection 643-3.10:

643-3.10 LIGHTING OF NIGHT WORK.  Illuminate the night work areas specified in Table 643-3, Night Work Illumination Level, and Area of Coverage, to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work/Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least two machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, Pavement Sweeping | At least four sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) Roads with ADTs over 10,000 2) That are controlled by portable signals or flaggers | Two Balloon lights of at least 2000 watts each located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without prior approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide the lighting equipment specified in Table 643-3 or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operations that require illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they do not interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibrations.

Ensure ground, trailer, and equipment mounted light towers are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels.  Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of failure of the lighting system, discontinue the operation until the required level and quality of illumination is restored.

Maintain a supply of at least 20 emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Provide NCHRP 350-compliant breakaway bases for post mounted electroliers located within the clear zone.

ES14-031506

Standard Modification

Add the following Subsection 643-3.11:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

1.	Standards.  Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

2.	Labeling.  Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004.

3.	Tops.  Wear high visibility vests, jackets, or coverall tops at all times.

4.	Bottoms.  Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise).  Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottoms at all times.

5.	Outer Raingear.  Wear raingear tops and bottoms conforming to requirements in this Subsection, 643-3.11.

6.	Exceptions.  When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

7.	Condition.  Furnish and maintain vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition.  Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic Pay Items.

E90-100410

643-4.01 METHOD OF MEASUREMENT.

2.	Traffic Control Device Items.  Replace the second sentence with the following:

Special Construction signs are measured by the total area of legend bearing sign panel, as determined under Subsection 615-4.01 and compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule, Table 643-4.

CR6431-032611

Standard Modification

Add No. 16:

16.	Steel F Shape Barrier.  Shall be measured and paid for by the linear foot.

E81-100410

Add No. 17:

17.	Hotline Road Report.  No measurement required to provide a 24 hour toll free (1-800 ###-####) “Hotline Road Report” telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Pay Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT.

7.	Flagging and Pilot Car.  Add the following:

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $48.00/hour.  The Engineer does not require a change order/directive for the flagging Pay Item.  Flagging associated with Change Order work will be paid at the prices according to Subsection 109-1.05 Compensation for Extra Work.

11.	Traffic Control.  Add the following:

The Engineer does not require a change order/directive for Pay Item 643(25), Traffic Control.

12.	Portable Changeable Message Board Sign.  Add the following:

Two Portable Changeable Message Board Signs used for Permanent Construction Signing will be paid for under Item 643(3) Permanent Construction Signs.  Other portable changeable message board signs will be paid for under 643(25), Traffic Control.

CR6431-032611

Standard Modification

Add No. 16:

16.	Steel F Shaped Barrier.  The contract price includes all resources required to provide, install, maintain, move, and remove each barrier.

E82-100410

Add No. 17:

17.	Work Zone Illumination.  Payment for work zone illumination is subsidiary to other items.

ES14-031506

Add No. 18:

18.	High Visibility Garments.  Payment for high visibility garments for workers is subsidiary to other Pay Items.

Add No. 19:

19.	Pavement Breaks.  Temporary hot mix asphalt at pavement breaks, as noted in Subsection 643-3.02.2. Gravel Surface Not Specified is subsidiary to Pay Item 401(1A).

TABLE 643-4

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $6.50 |
| Special Construction Signs | Square Foot | $28.00 |
| Type II Barricade | Each/Day | $3.30 |
| Type III Barricade | Each/Day | $11.00 |
| Traffic Cone or Tubular Marker | Each/Day | $1.10 |
| Drums | Each/Day | $3.30 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete or Steel F Shape Barrier | Each | $80.00 |
| Temporary Crash Cushion / Sand or Water Filled Barrels or Barrier (all required per end) | Each | $1250.00 |
| Temporary Crash Cushion / Redirective | Each | $2500.00 |
| Pilot Car | Hour | $73.00 |
| Pilot Car w/Sequential Arrows | Hour | $76.00 |
| Watering | M-Gallon | $25.00 |
| Street Sweeping: Regenerative Sweeper, Vacuum Sweeper, Mechanical or Power Broom with Vacuum | Hour | $175.00 |
| 40,000 GVW Truck with Crash Attenuator | Hour | $97.00 |
| Plastic Safety Fence | Lineal Foot | $1.00 |
| Portable Changeable Message Board Sign | Calendar Day | $130.00 |
| Temporary Sidewalk Surfacing | Square Foot | $2.00 |
| Flexible Markers (Flat Whip, Reflective) | Each | $60.00 |
| Removal of Pavement Markings | Lineal Foot | $1.25 |
| Temporary Guardrail | Lineal Foot | $25.00 |

Replace Pay Item 643(15) with the following:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

CR6431-032611

Standard Modification

Add Pay Item 643(29):

Pay Item No.	Pay Item	Pay Unit

643(29)	Steel F Shaped Barrier	Linear Foot

E82-100410

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

643(25A)	Traffic Control - Roadway	Lump Sum

643(25B)	Traffic Control - Trail	Lump Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Provide engineering communication services to the field office, Subsection 644-2.08.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area, and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer's office equipment and furniture.

CR644FOCOM-080511

644-2.02 FIELD LABORATORY.  Add the following to the end of the second sentence of the first paragraph: through one week after Project Completion.

Add the following new subsection:

644-2.06 NUCLEAR TESTING EQUIPMENT STORAGE SHED.  Design, furnish and maintain a weatherproof, heated, and ventilated nuclear densometer/testing equipment storage shed for the Engineer to use exclusively throughout the Contract.  Install the building at least 15 feet from an occupied area at a location approved by the Engineer.  Install the shed before beginning of construction activities and maintain it until one week after project completion.  Provide sufficient floor area for the nuclear testing equipment and a portable electric heater to maintain a minimum room temperature of 50 °F in freezing weather.  Design the building with enough floor area to provide sufficient clearance between the equipment, heater, and combustibles.  Provide a commercial grade metal clad exterior entrance door of 3’-0” minimum width by 6’-8” height with dead-bolt lockset.  Hang the door so that hinge pins are not accessible from the exterior.  Provide the Engineer with 2 keys to control access.  Provide a 5/16” x 10 foot long welded steel security chain securely attached inside the structure with tamperproof hardware for the Engineer to secure the testing equipment.  Provide 120 volt, 60 cycle power, an interior light, and a wall receptacle for the heater.  Secure the structure to the ground with tamperproof anchors to resist wind loads and prevent unauthorized movement of the building.  The nuclear testing equipment storage shed remains the property of the Contractor.  Remove the shed from the site following project completion.

Add the following new subsection:

644-2.07 STORAGE CONTAINER.  Furnish, transport and maintain a weathertight, lockable, steel enclosed 20 foot long X 8 foot wide X 8 foot high wooden floored container for the storage of the Department’s materials, supplies and testing equipment (but not nuclear equipment). Provide twenty equally spaced fastening points on the interior walls that are capable of securing the Department’s contents.  Door opening dimensions of the storage container shall be greater than 60 square feet.  Supply necessary equipment to lift and move container with minimal disturbance to the Department’s contents.  The container shall not be moved by skidding or hook lift.  The Contractor shall be listed as the shipper on documents listing and acknowledging receipt of the Department’s goods for shipment.

Deliver an empty and clean container to the Regional Materials Laboratory, or location acceptable to the Engineer, three weeks before transporting to the project site.  Allow 7 days for the Department to load the container.  Transport the loaded container to the project site.  Set up container at a location approved by the Engineer prior to commencing construction work.

Provide electrical service and other facilities as follows:

- Electrical current, 120V (ac), 60 cycle on a 24 hour a day basis.

- Wiring system to support a 20 amp user load demand.

- 2 GFI protected outlets conveniently spaced on the interior walls.

- Four 100 watt incandescent or eight 40 watt fluorescent lights located for maximum illumination.

- Provide a stairway with railing, built to meet the International Building Code, if there is more than 12-inch difference in floor entry and existing ground elevation.

Return the container to the Regional Materials Laboratory, or location acceptable to the Engineer, upon project completion.  Allow 7 days for the Department to unload the container.  The storage container remains your property after completing the work.

E44(01/27/07)

- Add the following subsection:

644-2.09 IMAGE DOCUMENTATION.  Provide secure "digital image" (image) documentation of construction activity at the project site(s); inclusive of an integrated, professional-grade, high resolution digital webcam image system designed for the construction industry with camera and related hardware, support structure, mounting equipment, software, data transmission service, website hosting, image hosting, storage/archiving and online interface for the system with technical support and as further defined herein.

1.	Period of Service.  Begin Image Documentation one week before construction begins through one week after project completion.

2.	Ownership of Image Documentation.  All images are the copyright of the Department including still images and time-lapse movies.  The Contractor and Vendor may not use the image documentation without the written approval of the Department.

3.	Ownership of Camera and Accessories.  The camera is the property of the Contractor.

4.	Submittals.  Provide complete submittals (3 printed copies), to the Engineer for review and approval, at least 21 days before beginning Construction activity.  Submittals will be returned to the Contractor, within 14 days from the date submitted, marked as approved by the Department, or requiring revisions.  Amend and resubmit the documents for review until approved by the Engineer.

Include the following:

a.	Shop Drawings.  Submit a key plan of the project site and construction to be documented with vantage points marked for location and direction of each camera. Coordinate layout and installation of cameras to avoid interference from site line obstructions such as trees and to prevent sunlight and light from fixtures entering directly into the camera lens.  Indicate camera mounting heights relative to ground and the construction being documented.  Include mounting structure, if required, and mount.

Coordinate camera location with the Engineer to capture the specified construction activity.

b.	Data Sheets and Certificates:  Submit the technical data sheets and certificates for materials including equipment and software.

c.	Maintenance:  Submit maintenance requirements with a schedule and service instructions.

d.	Qualifications:  Submit:

·	Technical Representative’s Resume:  name, education, training, and two years minimum experience providing same or similar service.  Include names of individuals and contact information for verification of service.

·	Vendor Qualifications:  Name and qualifications including five years minimum experience providing completed successful same service.  Include names of projects, project descriptions and contact information for individuals able to verify service.

5.	Materials.

a.	Camera.  Provide 	1	 camera with specifications similar to those listed below with equivalent to or better performance.

CAMERA SPECIFICATIONS

|  |  | Camera |  |
| --- | --- | --- | --- |
|  | 1 |  |  |
| Features |  |  |  |
| Imager: | 6 Megapixels, minimum |  |  |
| Lens: |  |  |  |
| F-Stop | f/3.5 - f/5.6 |  |  |
| Zoom: | 18 mm - 55 mm |  |  |
| Optical: | 3x min. |  |  |
| Digital: | - |  |  |
| Resolution: (minimum) |  |  |  |
| Stills: | 3088 x 2056 |  |  |
| Angle of View: | Cover intended site area |  |  |
| Auto Features: | ISO, shutter, white balance, and focus |  |  |
| Compression: | JPEG, Motion JPEG |  |  |
| Communication: |  |  |  |
| IP Addressing: | Dynamic or Static |  |  |
| Types: | Provide stable communication, by one or more of the following types, dependant on the availability with the order of precedence as follows: 1. Wired Broadband (10Base-T/100Base-TX) 2. Wireless (802.11n) 3. Cellular (3G min) 4. Satellite Broadband |  |  |
| Base: |  |  |  |
| Fixed Position: | Yes |  |  |

b.	Online Access, Interface, and Online Software.  Contractor's System Vendor shall provide an online based interface and online software as managed service to allow the viewing of all still images captured and stored/archived during construction, from any location with internet access using a PC computer and/or cellular device.  The Department will not be required to own specific software or operating equipment proprietary to the system vendor to utilize any part of the Vendors service.

1)	Solution Service:  provide solution service, including technical corrective service, continuous 24 hrs, 7 days a week during period of service.

2)	Machine to machine automated maintenance of the camera system providing continual operation without interruption.

3)	Communication:

a)	Broadband/High-Speed connection (1.5 Mbps)

b)	Wi-Fi G or N // 3G cellular connection

4)	Accessibility:  Vendor, provide a web page linked to the Department's Central Region web page;

"Alaska DOT&PF Project Information",

http://www.dot.state.ak.us/stwdplng/projectinfo/central.shtml,

"Central Region Projects", West Dowling Road -  Phase I – Old Seward Highway to C Street.

Add the link to the West Dowling Road -  Phase I – Old Seward Highway to C Street web page through the Engineer.  The Engineer will coordinate with the Central Region Web Manager.

a)	Public:  Provide the public with viewing access of still image documentation.

b)	Department:  Provide the Department with viewing access of the still images and live video as specified in 6) User Screen Viewing.

5)	System Navigation:  Calendar based.

6)	User Screen Viewing:  Display the Project Name and Number; Owner and Contractor Logo.  Multifunction image browsing (still images, multiple images, online time-lapse movies) per individual camera and between multiple cameras.  Additional viewing requirements include:

Public and Department.

·	Images: include time and date.

·	Navigation: calendar to navigate between documentation.

·	Full-Screen:  screen maximizing view of images on users monitor.

·	Time-lapse movies:  not real-time video.

·	Share Image Tools:  save, print, email, and post to message board or, mobile devices.

·	Map:  aerial and satellite view by Google or other.

c.	Environmental.  Camera and supporting equipment shall be designed for continual operation in all weather conditions relative to the project site, 24 hrs each day, each day of the week.  Weather conditions including but not limited to:

1)	Wet:  water proof.

2)	Operational Temperatures: -10˚F to +120˚F (thermostatically controlled heater and blower or other as required).

3)	Winds:  110 mph (3sec gust)

4)	Fugitive Materials:  dust, rain, snow and similar.

d.	Physical.  Designed and constructed for the conditions existing at the project site.

1)	Housing:  impact resistant, water proof enclosure constructed of aluminum with stainless steel fittings and UL rated compression glands.

a)	Adjustability:  adjustable camera sled.

b)	Operational Options:  (See camera specifications for actual)

·	Fixed (pan-tilt-zoom in high-definition image provided by software interface)

2)	Viewing Window:  impact resistant with remotely controlled washer/wiper.

3)	Security:  protect against vandalism.  Lockable housing secured in-place to prevent unauthorized removal from project site.

e.	Power.  Provide continuous uninterrupted power as required by the Vendor to operate and maintain the image documentation system.

6.	Vendors.  Vendors that may meet the requirements specified in this subsection include, but are not limited to the following:

| EarthCam, Inc. 84 Kennedy Street, Hackensack, NJ 07601 Ph: 800.327.8422 Ph: 201.488.1111 Fax: 201.488.1119 www.EarthCam.net | OnsiteView, Inc. Shipping: 7901 Cameron Rd Bldg. 3, Suite 301 Austin, Tx 78754 Mail: P.O. Box 190139 Dallas, Texas 75219 Ph: 866.701.2020 Ph: 512.301.2848 www.OnsiteView.com | OxBlue Corporation 814 Bellemeade Ave. NW Atlanta, GA 30318 Ph: 888.849.2583 Ph: 404.917.0200 Fax: 404.917.0201 www.OxBlue.com | Work Zone CAM, LLC 331 W 57th St, Suite 310 New York, NY 10019 Ph: 877.966.3101 www.Workzonecam.com |
| --- | --- | --- | --- |

7.	Security.  Provide security for the image documentation and documentation system.  Prevent; interruption of the continuous documentation, damage to the documentation (data corruption, theft, or loss of the data), and damage to the system (the physical equipment, interface, software, data collection, and storage).

Maintain all images on System Vendor owned and operated secure and redundant servers, in a secure area at a location owned by the Vendor.  Minimum levels of security include multiple levels of password protection, IP address block/permission and SSL protection of the user login password.

8.	Installation and Maintenance.  Provide initial installation by the Vendor, or other as approved by the Vendor, with the option to move the camera 1 times; and maintain the system throughout the period of service without interruption except as may be specified in this specification.  Damaged or failed parts and service complications, resulting in documentation interruption, are to be repaired, replaced, and resolved within 48 hrs from the time of interruption.

Training:  provide training for the Engineer's staff in the use of the image documentation system as described in 5.b.6) and as applicable.  Schedule the training, coordinated with the Engineer, directly after the installation is completed and the system is operational.

9.	Documentation.  Throughout the Period of Service, during the day and night, document the construction activity.  Approximate times are included herein; the approximate location of the camera is provided in the Plans (plan and profile sheets coordinated with the summary sheets).  Coordinate with the Engineer, adjusting the times of documentation and actual location(s) (plan and elevation) to capture the specified activity.

For all image documentation, include the project name and number with the date and time.  The date and time for a still image would be at the time of capture and for a time-lapse movie the time from start to finish of the movie.

a.	Type.

1)	Still Image Capture.  Capture still image at regular intervals.  	Intervals = 15 minutes.

2)	Time-Lapse.  Create time-lapse movies during the Period of Service as directed by the Engineer and as follows:

Regular Interval.	Time-Lapse Movie Interval = End of Each Month.

Period of Service.  At the end of the Period of Service, create a time-lapse movie of the construction activity(s) from the beginning of service to the end of service.

10.	Removal.  Remove the complete documentation system after completion of the service period.  The Engineer may direct the system to be removed prior to the end of the service period.

11.	Deliverables.  Provide the Engineer with (2) DVDs (2 copies) of:

a.	Stills:  as originally recorded in the digital camera, without alteration, manipulation, editing, or modifications, in compressed JPEG format, no more than 7 days after the service period ends.

b.	Time Lapse-Movies: in compressed motion JPEG format, no more than 7 days after each interval, season change, milestone, event, and the Period of Service specified in 9) "Documentation."

CR644CMRA-032211

644-3.01 METHOD OF MEASUREMENT.  Add the following items:

Nuclear Testing Equipment Storage Shed.  By the number of storage sheds specified, to including components, installed and accepted as completed units and ready for equipment storage.

Storage Container.  By the number of storage containers specified, to including components, installed and accepted as completed units and ready for materials and equipment storage.

E44(01/27/07)

Add the following:

Image Documentation.  No additional measurement will be made if any part of the documentation system requires replacement.

CR644CMRA-032211

644-4.01 BASIS OF PAYMENT. Add the following items:

Lump Sum Items. Payment for lump sum items will be made as follows:

- A percentage of the lump sum amount, to be determined by the Engineer, will be paid as full compensation for furnishing the facility at the site.

- The balance of the lump sum amount will be prorated over the anticipated active construction period with a portion included as part of each interim payment, for maintenance, repairs, providing all utilities, and for removing it from the site.  If anticipated construction period changes, the final increment will be held until final payment.

Nuclear Testing Equipment Storage Shed. At the Contract unit price to include labor, materials, tools, equipment and supplies required to furnish and install the shed before beginning construction, to maintain it for the duration of the project and to remove the shed and electrical service after project completion.  Electrical service and utility costs are subsidiary to this item.

Storage Container.  At the Contract unit price to including labor, materials, tools, equipment and supplies required to deliver the storage shed to the regional office for loading, to deliver it to the project office, to install it before beginning construction, to maintain it for the duration of the project, to remove the shed and electrical service after project completion, to deliver it to the regional office for unloading, and to remove the storage shed.  Electrical service and utility costs are subsidiary to this item.

E44(01/27/07)

Add the following:

Pay Item 644(17) Image Documentation.  At the Contract lump sum price to include labor, equipment, materials, fees, and service specified.  The lump sum price is inclusive of all cameras specified in 2.09.

Lump Sum Items.  Payment for lump sum items will be made as follows:

1.	A percentage of the Contract lump sum amount, to be determined by the Engineer, will be paid as full compensation for a complete, properly functioning, image documentation system including site installation(s), power, camera, and operating system(s), with automatic archiving, set up and interfaced with internet access via the specified device(s).

2.	The balance of the Contract lump sum amount will be prorated over the anticipated active construction Period of Service with a portion included as part of each interim payment, for maintenance, repairs, utilities, fees and for removing the complete documentation system from the site with the final payment being made after all deliverables are received as specified.

CR644CMRA-032211

Add to Pay Items:

Pay Item No.	Pay Item	Pay Unit

644(15)	Nuclear Testing Equipment Storage Shed	Each

644(16)	Storage Container	Each

E44(01/27/07)

Pay Item No.	Pay Item	Pay Unit

644(17)	Image Documentation	Lump Sum

CR644CMRA-032211

Special Provision

Add the following Section:

SECTION 645

TRAINING PROGRAM

645-1.01 DESCRIPTION. This Training Special Provision implements 23CFR230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 OBJECTIVE.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j, and 7.l, located in the "yellow pages" of this document.

645-3.01 GENERAL.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicted above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public Facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor's judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee. Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 WAGES.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 SUBCONTRACTS.  In the event a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to Subsection 645-5.01, Basis of Payment.

645-4.01 METHOD OF MEASUREMENT.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor's submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 BASIS OF PAYMENT.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor's discretion, graduates early and is employed as a journey worker according to the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial  payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be ducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program, 3 Trainees/Apprentices	Hour

S16(10/29/91)

SECTION 646

CPM SCHEDULING

Special Provision

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this Subsection with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.

R261(12/13/02)

Add the following Section:

- SECTION 647

- EQUIPMENT RENTAL

Special Provision

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions.  These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers.  In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be, as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and  incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, 6 days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.  Hours paid shall be supported by certified payroll.

647-5.01 BASIS OF PAYMENT. Payment for Items 647(1) Wide Pad Dozer, 65 hp Minimum and 647(1A1) Backhoe, Self-Propelled, 4WD, 1.0cy Bucket, 75 hp Minimum, 14 ft Depth will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment.  Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 65 HP Minimum	Contingent Sum

647(1A1)	Backhoe, 4WD, 1 CY Bucket, 75 HP Min, 14 Foot Depth	Contingent Sum

- SECTION 660

- SIGNALS AND LIGHTING

Special Provisions

660-1.01 DESCRIPTION.  Add the following:

This work shall include installing Emergency Vehicle Preemption (EVP) detection, and additional work and materials as noted or detailed on the Plans.  This work shall also include installing pedestrian lighting for Campbell Creek Trail under the bridge.

660-1.02 DEFINITIONS.  Revise the first sentence to read:

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements, Section 1, Definitions, along with the following:

Under No. 2. Luminaire. Revise the second sentence to read:

Luminaires consist of hood (including socket, lamp, and ballast), reflector, and glass globe or refractor.

Standard Modifications

660-2.01 MATERIALS Under No. 1.b. change title by removing:  Materials Not on the "Approved Products List:" and replace with:  Materials on the "Qualified Products List:"

E36 (01/27/07)

Special Provisions

660-2.01 MATERIALS.  Add the following:

Anchor Bolts:						Section 740-2.02

1.	Equipment List(s) and Drawings. Delete No. a. in its entirety and the last sentence in No. d. and substitute the following:

a.	Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

d.	Materials Not Requiring Certification: Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

2.	As-Built Plans.  Add the following:  Place 1 copy of the controller cabinet diagram, detector assignment sheet and the intersection and phase diagram as reviewed by the Engineer in clear plastic envelopes and attach to the inside of each controller cabinet.

In addition, submit 2 complete sets of all electrical related plan sheets.  The Engineer will deliver 1 copy of each to the MOA Signal Electronics and the MOA Street Light Maintenance.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.  In No. 1., Scheduling of Work. Add the following to the first paragraph:  Contact the MOA Signal Electronics Shop 24 hours in advance of work on a signal or lighting system. Contact shall be made through the Engineer.

After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, J-boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications.

Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.

Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt Patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

In No. 2., Safety Precautions. Add the following:

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

Delete No.s 3. through 8. in their entirety and substitute the following:

3.	Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors before final lift paving.  Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

When conditions allow HDPE conduit to be installed by a plowed technique, restoring the area disturbed from the process, shall be accomplished according to Subsection 204-3.01. Density testing may be waived and compactive effort substituted at the discretion of the Engineer.  This work is subsidiary to conduit installation.  Use Selected Material, Type A for backfill.

Dispose of, according to Subsection 203-3.01, excavated materials that remain after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in Subsection 703-2.07. Disposal of this material is subsidiary to the 660 Pay Items.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements:

a.	Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift.

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material cleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

4.	Welding.  Complete welding according to Subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes that were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the nonreusable improvements the Contractor removed to complete the work.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements damaged or removed by the Contractor not conflicting with the work and not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment.  When the Plans include existing traffic signal electrical equipment scheduled for removal or relocation, remove, and store the equipment listed in the following paragraph without damaging it.  Deliver removed equipment not scheduled for reuse to the MOA Traffic Signal warehouse at 5923 Rowan Street in Anchorage, Alaska.  Signal poles and mast arms shall be delivered to the MOA Traffic Signal Pole yard at 3rd Avenue & Orca Street.  Allow MOA maintenance personnel to select the equipment and pole items they would like to salvage.  Contractor shall dispose of all remaining equipment and pole items.  Contact the Foreman at 343-8355 one week before delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to Subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with Selected Material, Type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place.  The Department may require a credit for this waiver.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material that will be paid for as extra work under Subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to Subsection 660-3.01.4 Welding and repair the finishes according to Subsection 660-3.01.8 Repairing Damaged Finishes.

When ordered, the Engineer will pay for repairing existing damaged finishes on existing equipment according to Subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to Subsection 660-2.01.1.

7.	Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by Subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 VDC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test. Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

(1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to Subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

(2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

(3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

(4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

(1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

(2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

(3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

(4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

(5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

Add the following new No. 9:

9.	Regulation and Code.  Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the Authority Having Jurisdiction.

660-3.02 FOUNDATIONS.  Under No. 1.  Cast-in-Place Foundations. Add the following to the first paragraph:  Locate the tops of traffic signal post and pole foundations flush with the adjacent finished walkway, shoulder, or surrounding ground.

1.	Cast-in-Place Foundations.

f.	Revise the second sentence to read:  Before placing the form or reinforcing steel cage, remove loose material to ensure the foundation rests on firm, undisturbed ground.

i.	In the second sentence delete "prior to grouting." and substitute "before attaching the skirt."

j.	In the first sentence delete "concrete pile caps" and add, "foundations." Add the following to the end of the paragraph:  Protect foundation anchor bolts from damage before installing controller cabinets.  The Engineer must approve the method used for protection.  This work does not relieve the Contractor of responsibility specified under Subsection 107-1.15.

Replace k with the following:

k.	Furnish anchor bolts that conform to ASTM F1554, the grade and supplementary Charpy V-Notch requirements listed in the Plans. Furnish each anchor bolt with three nuts and two washers.

Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations.  Adjust nuts until their tops form a level plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten top nuts to a "snug" condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the "snug" top nuts.

After the top nuts are tightened to the correct torque, use a hydraulic wrench to rotate top nuts an additional one sixth (60) turn, while preventing the leveling nuts from turning.

Add l.

l.	Attach a #4 AWG, bare, copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled #4 AWG, bare, copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, PVC or HDPE, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2.	Pile Foundations.  Add the following new subparagraph:

g.	Use no more than one splice per foundation.  Locate the splice at least 10 feet from the top of pile.

3.	All Foundations.

d.	Replace the last sentence with the following:  Backfill the resulting hole with Selected Material, Type A and compact material as directed by the Engineer.

Replace Subsection 660-3.03 with the following:

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

1.	Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

2.	Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to Subsection 660-3.01.3, Excavating and Backfilling.

3.	Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

4.	If encountering obstructions during jacking or drilling operations obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 11/4 to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

5.	Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

6.	Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

7.	Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self clinching nylon cable ties.

8.	Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

9.	At the low points of conduit runs, install sumps containing a minimum 2 cubic feet of coarse concrete aggregate material that conforms to Subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

10.	Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

11.	Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 21/2 inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

12.	Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

13.	Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

14.	When standard couplings cannot be used to join conduit components, use approved threaded unions.

15.	Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

16.	When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

17.	In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

18.	Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

19.	Install expansion fittings in conduits that cross expansion joints.

20.	Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back pull rope, at least two feet, into both ends of each conduit.

21.	The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

22.	Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables to be removed or replaced as follows:

a.	When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

b.	Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

23.	When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than a 90 degree horizontal bend to the extension.

24.	When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

25.	When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

26.	Remove the ends of abandoned conduits from junction boxes that will remain in service.

27.	When Plans call for connecting polyethylene conduit to RMC use a UL listed electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits.  Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

Replace Subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3.	Outside the right of way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing Type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.  When installing copper signal interconnect cable use minimum size Type II junction boxes.

Four (4) Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits, that exclusively contains two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits, that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work; otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade.  In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of porous backfill material that conforms to Subsection 703-2.10.  Minimum drain dimensions include an 18" depth and a length and width equal to those of the junction box it drains.  Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker.  Conform markers to the American Public Works Association Standards including but not limited to:

	Color - red

	Material - high-density polyethylene

	Shape - round (ball like)

	Size - 4 to 5 inches in diameter

	Configuration - encapsulating an antenna tuned to the appropriate frequency for locating power

	Responsive range - up to 5 feet away from the locator device

	Environmental conditions - including extremes in temperature at the installation site

	Contain no internal power source

Acceptable marker manufacturers include:

	3M, Dynatel EMS ball marker model no. 1402-XR

	Tempo (a Textron Company), Omni Marker

	Substituted, equivalent approved equal device

660-3.05 WIRING. Change last sentence of the first paragraph to read: Run signal cabling continuously without splices from the controller cabinet to the termination lugs in the signal housing.  Do not splice conductors within cabinets, poles, signal heads, and luminaries.

Delete the second paragraph in its entirety and substitute the following:

Conditions.

Do not pull conductors into conduits until the following conditions are met:

	The prescribed clearances around conduit ends are provided,

	Crushed rock sumps are installed under junction boxes,

	Conduit ends protrude above the bottom of junction boxes within the prescribed range,

	New conduits are free of material that became lodged in them during the completion of the work,

	Reused conduits are cleaned according to Subsection 660-3.03,

	Junction boxes are set to grade, and

	Grounding bushings are installed on the ends of metallic conduits.

Add the following line to Table 660-1 under a. of No. 9.

| LOOP DETECTOR NUMBER | COLORED PAIR |
| --- | --- |
| Usually a spare pair | Orange and Black |

Delete subparagraph 11 and 12 and replace with the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 VAC operation, feature fill, and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, one splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced, it shall occur within an appropriately sized junction box or in the base of an electrolier designed for said splice.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 VAC operation and direct burial.

Provide reusable four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full 1/4 inch of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is noncorrosive to copper, and does not support fungi or mold growth.

Add the following No. 18, 19, and 20:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductors to 5 feet.

20.	Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

Replace Subsection 660-3.06 with the following:

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements:  Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size #8 AWG grounding conductors, except in those conduits that contain circuit conductors larger than #8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to a #8 AWG and eyelet spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the #4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the handhole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the handhole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a 3/4 inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

When routing a new conduit into an existing junction box or replacing an existing junction box, new and existing conduits shall have the grounding improved to current specifications.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES.

In the 4th subparagraph replace "3.5-inch floppy" with "compact"

In the 3rd subparagraph revise the first sentence to read: At the time the controller assembly is delivered submit the following for each assembly: and add the following to the last sentence (2 paper copies and 2 electronic copies one, in Adobe pdf format and the other in AutoCAD v2004 or later format).

Delete 1. Shop Tests. Replace with the following:

1.	Shop Tests.  The Controller Assembly manufacturer shall conduct a pretest of the cabinet and controller assembly. The pretest includes but is not limited to:

a.	Ensure the cabinet is free of paint scratches, dents, sharp edges, and other physical defect.

b.	Ensure cabinet hinges, heater, ventilation system, lighting, and door locking mechanism function properly.

c.	Ensure that there are no shorts between AC+, AC-, and GND anywhere in the cabinet.

d.	Check that there is no continuity between AC+ and DC+.

e.	Check for continuity between any green wire connection point and GND.

f.	Ensure devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly.  Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of; flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation and, proper police & auxiliary panel operation.

Upon completing the final test the cabinet shall be run, "burned in," under full loads for a period of not less than 48 hours with a test timing plan in effect which utilizes full cabinet phases and functionality.

In the course of testing, a component found to function incorrectly or exhibit physical damage must be replaced with an equivalent new component before delivery.  Should the cabinet fail during burn in, the cause of the failure must be remedied and the test restarted with another 48 hours of burn in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pretest, final test, and burn in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note defects found and the remedial action taken.  Further, the certification shall state the assembly conforms to the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements.  Submit the certification letter and copies of the test results to the Engineer.

The work required in this subsection is subsidiary to the associated traffic signal system under Pay Items 660(1A) Traffic Signal System Complete at C Street and 660(1B) Traffic Signal System Modifications at Old Seward Highway.

Replace Subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure handhole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces that secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Mast arm mounted signal head offsets shown on the plans are approximate.  Signal heads shall be installed over lane lines or over the center of lanes, as shown on the plans.  Mounting locations shall be verified using the as-built lane markings and signal pole foundation location.  Obtain the approval of the Engineer before wire access holes are drilled in mast arms.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads "out of service" and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts as described in Subsection 660-3.02.1k.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

3.	Vehicular Signal Head Installation.  With two piece mast arms, do not install signal heads within 12 inches on either side of the slip type field splice.

Attach each side mounted terminal compartment with two 1/2" x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on the Traffic Signal Hardware Detail Sheet in the Plans.  Install the vertical pipe members plumb.

When installing 4 or 5 sections vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

| TABLE 660-2 |  |
| --- | --- |
| THROUGH PHASE SIGNAL FACE AIMING POINTS |  |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

4.	Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two 1/2" x 13 bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install R10-3E (R or L) push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

5.	Underpass Lighting System Installation.  Mount the luminaires as detailed on the drawings to orient the axis of the lamp perpendicular to the axis of the underpass.

6.	Flashing Beacon Installation.  When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher.  Furnish and leave 5 feet of cable in the cabinet.  Others will install the fused block and terminate the beacon cables.

7.	Wood Pole Installation.  Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material.  Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

Replace Subsection 660-3.09 with the following:

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the Contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If existing lighting systems are not kept fully operational as specified herein, the Engineer will reduce the payments under Pay Item 660(22) Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the Crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 15.0 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 19.0 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20 degrees, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

a.	With two or more through lanes, center one signal head over each lane.

b.	With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

c.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in Subsection 660-3.08 Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and No. 6.  Salvaging or Reusing Electrical Equipment, found in Subsection 660-3.01.  Remove other materials used in the temporary systems from the project.

Add the following subsection:

660-3.11 SIGNAL SYSTEM TIMING AND ADJUSTMENTS.  The Engineer will use MOA signal maintenance personnel for certain work inside controller cabinets.  Before MOA personnel arrive to terminate conductors, ensure terminal connectors are attached to conductor ends and paired loop detector conductors and cables are labeled as specified in subsection 660-3.05, Wiring.

Controller Cabinet Preparation.  Ship the traffic controller cabinet(s) and equipment to the Municipality of Anchorage Traffic Signal Electronics Shop at 3601 Dr. Martin Luther King Jr. Avenue.  The MOA will inspect cabinet wiring, burn in signal equipment, customize cabinets for desired operation, and test the equipment.  Allow six weeks for testing.

- Loop Detector Wiring.  Municipality of Anchorage Traffic Signal Maintenance (MOA Signal Maintenance) will test and connect paired loop detector conductors to the terminal blocks.

- Control Cable Wiring.  When modifying an operational signal system or controller assembly, MOA Signal Maintenance will connect control cables within the controller cabinet to the terminal blocks.

- Timing Adjustments.  During construction, MOA Signal Maintenance may adjust the system and intersection operational timing to accommodate project conditions.

- Interconnect Wiring.  MOA Signal Maintenance will splice, test and connect copper interconnect wiring to the terminal blocks.

Add the following new subsection:

660-3.16 TRAFFIC SIGNAL MODIFICATIONS.  Required work is detailed in the Plan sheets and notes and the following.  Work related to the Traffic Signal Communications System will be paid for separately.

The Contractor will have 10 hours to "changeover" the new controller assembly. Changeover includes but is not limited to: removing the existing controller assembly, replacing with new controller assembly, landing new and existing wires, programming the new controller unit, and bringing the signal back to full functionality.  The 10 hour window will only occur on the days Monday through Thursday at a time determined by the Engineer.  The Contractor will be assessed a Traffic Price Adjustment for an unauthorized lane closure according to Subsection 643-3.06.

Traffic control during the changeover will be paid for under section 643 Pay Items.  At a minimum, traffic control will include the following:

	A portable changeable message board in advance of each approach with the message "Traffic Signal Work, New Traffic Pattern Ahead, from 00:00 AM/PM mm/dd/yy to 00:00 AM/PM mm/dd/yy

	A flagger for each approach

Traffic signal modifications are subject to the full Standard Specification for Highway Construction, the Special Provisions, and the following:

1.	Traffic Controller Cabinet: When a new traffic controller cabinet is called for, ensure legible labeling of all cabinet cables including but not limited to; control, loop, EVP, UPS, interconnect, and telephone. Label loops and signal heads individually.

2.	Traffic Signal Heads:  When new traffic signal heads are required, provide with new LED units and new mounting hardware. If new heads are not called for, replace any missing visors or backplates subsidiary to the Traffic Signal System Modifications Pay Item.

When replacing traffic signal or pedestrian indications conform to Subsections 740-2.14 and 2.15 and maintain brand consistency throughout intersection. When new heads are provided aim heads according to Table 660-2.

3.	Loops: When shown in the plans, replace inductive loops including homerun cable and required splice. Loop tests are required per 660-3.01.7.

4.	Conduits: Unless new conduits are called for, reuse existing conduits.  When new conductors are being added to existing conduits, conform to Subsections 660-3.03, 3.05, and 3.06.

5.	EVP Components: When called for in the plans provide EVP components including all cables and mounting hardware. Ensure proper operation of EVP system.

6.	UPS: When called for in the plans, provide fully functional UPS system. If no separate UPS item exist, the UPS will be paid for subsidiary to the Traffic Signal System Modifications Pay Item.

7.	Load Center: When called for in the plans provide fully functioning Load Center. If no separate load center item exists, the load center will be paid for subsidiary to the Traffic Signal System Modifications Pay Item.

8.	Conductors: Reuse existing conductors except where the plans call for new conductors.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the local Maintenance & Operations station within 72 hours of removal. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Pay Item 660(7A) Temporary Signal System Complete at Old Seward Highway.  Lump Sum, includes furnish, install, remove, and maintain temporary signal system.  Traffic control for installing, removing, and maintaining is subsidiary to 643(25A).

Pay Item 660(22) Illumination Price Adjustment.  By the mile of roadway with all or part of the existing illumination systems inoperative.  A divided roadway is considered one roadway.  Ramps are considered a separate roadway.  The Engineer will measure each unlit section less than one mile long as one mile.

Pay Item 660(34) Salvage Electrical/Signal Equipment.  Lump Sum, includes removal and delivery to maintenance yard.

660-5.01 BASIS OF PAYMENT.

Payment for Item 660(26), Signal System Timing and Adjustments, will be made based on paid receipts plus 15% for authorized work performed by the Municipality of Anchorage. A directive will not be required to initiate payment for work performed under this item.

All retesting of equipment for failure to comply with the plans and specifications will be at the expense of the Contractor. Invoice cost will be deducted under Item 66(26) and the total value of this Contract will be adjusted accordingly.

Payment Includes labor, equipment, and materials required to provide fully functional traffic signals and lighting systems, permanent and temporary, using new equipment.  Remanufactured or rebuilt equipment will not be permitted.

Subsidiary to each Pay Item including but not limited to (Except when included as a separate Pay Item):

(1)	General construction requirements,

(2)	Bonding and grounding,

(3)	Bored Casings,

(4)	Completing tests,

(5)	Conductors,

(6)	Conduit,

(7)	Dewatering excavations,

(8)	Excavation, trenches in rock or soil, bedding, backfill for foundations, conduits, components,

(9)	Foundations including concrete to complete foundations,

(10)	J-boxes including adjustment to final grade,

(11)	Labeling conductors,

(12)	Maintaining temporary and existing electrical systems,

(13)		Minor routing changes directed by the Engineer

(14)		Preparing as-builts

(15)	Removal and disposal of existing/new unused foundations, conduit, conductors, and J-boxes,

(16)	Removing, repairing and replacing improvements

(17)	Removal of signs and reinstallations required to install foundations, conduits, and J-boxes,

(18)	Repairing damage to finishes on new equipment

(19)	Salvaging reusable equipment and materials and delivering to the local Maintenance and Operations station.

(20)	Wiring

(21)	Maintaining temporary traffic signal system

660 Pay Items do not include:  roadway planing, roadway paving, drainage structures, erosion, sediment and pollution control, signing, striping and pavement markings, traffic control, and components of the traffic signal communication system.

Pay Item 660(1A) Traffic Signal System Complete at C Street and Pay Item 660(1B) Traffic Signal System Modifications at Old Seward Highway.

1.	Signal structures

2.	Traffic controller assemblies including assembly testing and preparation, vehicle and pedestrian indications, video detection systems, inductive loop detection, emergency vehicle preemption systems, auxiliary and test equipment, on-site manufacturer assisted start up, minimum 2 year equipment warranty, and training when called for in the Plans.

3.	Work associated with installing loop detectors and conduit crossings, including:  Except when a separate Pay Item is used, saw cutting, asphalt removal, aggregate base course, tack coating, and installing new hot mix asphalt.

Pay Item 660(22) Illumination Price Adjustment.  Each day the existing illumination system(s) is inoperative, partially or completely, the Engineer will deduct $1,275 per mile from the total value of the Contract.  A mile is measured as noted in 660-4.01 under:  Pay Item 660(22) Illumination Price Adjustment.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

660(1A)		Traffic Signal System Complete at C Street		Lump Sum

660(1B)		Traffic Signal System Modifications at Old Seward Highway		Lump sum

660(7A)		Temporary Signal System Complete at Old Seward Highway		Lump Sum

660(22)		Illumination Price Adjustment		Contingent Sum

660(26)		Signal System Timing and Adjustments		Contingent Sum

660(34)		Salvage Electrical/Signal Equipment		Lump Sum

SECTION 661

ELECTRICAL LOAD CENTERS

Standard Modification

661-2.01 MATERIALS.  Under Item 1. change title by removing:  “Materials on the Approved Products List:” and replace with:  Materials on the Qualified Products List:

Under Item 2. change title by removing:  “Materials Not on the Approved Products List:” and replace with:  Materials Not on the Qualified Products List:

E36(01/27/07)

SECTION 663

Signal interconnect system COMPLETE

- Special Provision

663-1.01 DESCRIPTION.  This item consists of the work required to furnish and install fiber-optic signal interconnect system as shown on the Plans along the route indicated or on a route as directed by the Engineer.

663-1.02 REGULATIONS AND CODE.  Complete the work in accordance with these Specifications.

663-1.03 TRAINING

Before the acceptance of the first shipment of conduit, training shall be provided for DOT and MOA engineering, maintenance and operations staff at the facility required for each participant.

Installation and maintenance training of conduit installation shall be provided for a minimum of 16 hours for at least 10 personnel with a background in conduit and cable installation.  The training shall include installation, preventive maintenance procedures, troubleshooting, and repair of all components.

663-1.04 INSTRUCTIONS AND GUARANTEES

One set of maintenance and repair manual shall be included with each project installation and submitted to MOA personnel through the Engineer.

No changes or substitutions in these requirements will be acceptable unless authorized in writing.

The supplied conduit shall carry a two-year warranty, from the date of project acceptance by MOA, to be free of defects.  The installer shall fully inspect the conduit before installation and within the warranty period.  The installer shall be fully responsible for the installation of defect free conduit and for the replacement of any conduit found to be defective due to improper construction or improper installation for two years after the Engineer’s acceptance of the project.

663-2.01 MATERIALS.  Submit the materials for review and approval per the requirements of item 1, Equipment List and Drawings of subsection 660-2.01, Materials.

663-2.02 POLYETHYLENE DUCT SYSTEM.  Install a polyethylene duct system in which to pull the interconnect cable.  The Department will not permit the installation of the polyethylene conduit in a plowed trench.

Furnish a Type III polyethylene duct made from ultra high molecular weight, high-density, polyethylene (PE) pipe, with a tensile yield strength of 3,200 psi when tested in accordance with ASTM D638.

Furnish fittings used in the duct system such as elbows, etc., made from the same type polyethylene as the duct.  Fuse connections using manufacturer’s recommended procedure and equipment.

Transition from HDPE to RMC before crossing roadways.  When connecting polyethylene conduit to RMC use a UL listed electrofusion coupler rated for direct bury application.  The coupler must be rated for same wall thickness as the adjoining conduits.  Thread the ends of the RMC with the same number of threads as found on the conduit ends cut in the shop or field to remove burrs and sharp edges.

All conduit and fittings shall carry UL label on each segment.

663-2.03 FIBER-OPTIC CABLE

Cable shall be suitable for placement in underground duct and shall conform to:

	United States Department of Agriculture Rural Utilities Service (RUS) standard 7 CFR 1755.900.

	Department of Agriculture Rural Electrification Administration (REA) Bulletin 1753f-601 (PE-90) dated August 4, 1994, and these specifications.

	National Electrical Code (NEC) Article 770; NFPA-National Fire Protection Agency.

	Telecommunications Industry Association/Electronic Industries Association (TIA/EIA) FOTP-Fiber-optic Test Procedures

Fiber-optic cables shall be loose tube and all-dielectric (no metal armor or conductive material) construction.  Optical fibers shall be contained in kink-resistant buffer tubes.  Each cable shall be equipped with up to 12 buffer tubes stranded around an anti-buckling central strength member using a reverse oscillation or “SZ” stranding process.

Each buffer tube shall consist of 6 fibers and shall have an inside diameter much larger than total diameter of the fiber it supports.  Buffer tubes may have up to 12 fibers where specified in the plan.

Fillers are allowed in the cable to achieve cable cross-section symmetry.

All cable fibers shall be usable and shall be sufficiently free of surface imperfections and inclusions to meet or exceed the optical, mechanical, and environmental requirements contained in this specification.

Each optical fiber shall consist of a doped silica core surrounded by a concentric silica cladding.

Fibers shall contain no factory splices.

Fiber coating shall be a dual-layered, UV cured acrylate applied by the fiber manufacturer.  The coating shall be mechanically or chemically strippable without damaging the fiber.

Repairs to fiber coatings are not allowed except as determined by the Municipal Traffic Signal personnel at designated splice locations.

A water-blocking gel shall displace voids between buffer tubes and void areas around individual buffer tubes to prevent water entry.  The gel shall be non-nutritive, electrically non-conductive and homogeneous and shall facilitate free movement of fibers within the tubes such that mechanically or environmentally induced stress on the cable is not induced in optical fibers.  The gel shall be free of dirt or foreign matter and shall be readily removable with nontoxic solvents.

Two (polyester or aramid) yarn binders shall be applied contra-helically with sufficient tension to secure each buffer tube layer to the central strength member without crushing buffer tubes.  The binders shall be non-hygroscopic, non-wicking, and dielectric with low shrinkage.

Tensile strength shall be provided in the cable by a combination of high tensile strength yarns helically stranded around the cable core.  High tensile strength yarns shall be wrapped helically around buffer tubes before application of the outer jacket (sheath).

Individual buffer tubes and optical fibers shall be distinguishable by means of distinct and recognizable color-coding in accordance with TIA/EIA-598-B, “Optical Fiber Cable Color Coding.”  The colors shall be stable during temperature cycling and not subject to fading or smearing onto each other or into the gel filling material.  Ensure colors do not cause fibers to stick together.

Distinguish each fiber and buffer from others by means of color-coding according to the following:

| 1. Blue | 5. Slate | 9. Yellow |
| --- | --- | --- |
| 2. Orange | 6. White | 10. Violet |
| 3. Green | 7. Red | 11. Rose |
| 4. Brown | 8. Black | 12. Aqua |

For cables containing more than 12 buffer tubes, use the color code shown above for tubes 1 through 12, and use stripes or tracers in conjunction with the standard color code for tubes 13 through 24.  Colors shall not fade or smear onto each other or into gel material.  Colors shall not cause fiber to stick together.

The outer jacketing (sheath) material shall be applied directly over high tensile strength yarns.  The minimum nominal jacket thickness shall be 55 mils.

The outer jacket material shall be medium density polyethylene (MDPE) conforming to ASTM D1248, Type II, Class C, Category 4 or 5, Grade J4.  The light absorption coefficient, when measured in accordance with ASTM D3349, shall be a minimum of 400 at a wavelength of 375 nanometers.

The polyethylene jacket (sheath) shall contain carbon black to provide ultra-violet light protection.  The jacket material shall be fungus inert as described in ASTM G21.

The jacket shall be free of any holes, splits, or blisters.

The cable shall contain at least one ripcord under the sheath for easy sheath removal.

The shipping, storage and operating temperature range of the cable shall be –40oF to +160oF.

The fiber-optic cable shall withstand a maximum pulling tension of 600 lbs during installation (short-term loading) with no damage and 200 lbs (long-term loading).  Tensions on the cables shall not be exceeded under any circumstances.

All fiber-optic cable on this project shall be from a current ISO9001 certified manufacturer who is regularly engaged in the production of these specifications for fiber-optic cable.

Fiber-optic cables shall be manufactured, tested, and prepared for shipping all by one single manufacturer; the same manufacturer shall provide for all fiber-optic cable and connectors called for on the project.

Cable slack shall be provided as listed in subsection, Construction Requirements.

All cable markings shall be approximately 1/8-inch (3 mm) nominal height, clearly legible and distinguishable, and made at 2-foot intervals to be used as length markers.  If initial markings fail to meet marking criteria (i.e., non-legible, incorrect spacing, spelling error, etc.), cables may be remarked to meet criteria.  Cable markings shall include:

	Cable ID

	Sequential numbers in whole foot or meter intervals to determine the length of the cable and amount remaining on the reel.

	Number of fibers

	“SM” (for Single Mode Fiber)

	“MOA Fiber”

663-2.04 FIBER-OPTIC DROP CABLE.  Drop cable is defined as the assembly or pigtail consisting of fiber-optic cable, connectors, protective tubing and fan-outs (if required) and all incidental materials used for connectivity between a fiber trunk cable and field devices (i.e., signal controller, modems etc.).

Fiber-optic drop cables shall be a SM 12 fiber Gator Patch Drop Cable with LC Duplex connections manufactured by Fiber Connections Inc. or approved equal.

Cable design and installation shall meet requirements for outdoor use as described in subsection, fiber-optic cable.

Optical jackets (3mm), where used, shall be yellow for single mode fibers.

No splices are allowed within the cable length.

Drop cables shall be factory assembled.

Non-connectorized ends shall be suitable for heat fusion splicing as described in the subsection, Splices.

Factory testing information of each fiber-optic drop cable (fully assembled) shall be provided for each connector/fiber.  The information shall be provided in test tags attached to individual or paired connector/fiber.

Drop cables shall be packaged individually within a plastic back marked clearly with the manufacturer’s part number.

Field testing information of each fiber-optic drop cable (fully assembled) shall be in accordance with subsection, Field Testing and Performance of Fibers.  Documentation of testing shall be in accordance with subsection, Documentation of Testing.

- Fiber-optic drop cables shall be equipped with:

1.	Six (6) optical fibers or number as specified in the plan.

2.	Fiber-optic connectors that are:

a.	compatible with the equipment being used for fiber strands with preset usage.

b.	in accordance with subsection, Connectors.

c.	factory installed unless otherwise allowed by Engineer.

3.	Drop Cable Fan-out Kits:  heavy-duty Spider design.  Install fan-out kits for all connectorized ends to build up to 3 mm jacket.

4.	Tubing that is 900 µm or 3 mm fan-out as required by the application.

5.	Buffer tubes protected by the cable sheath or fan-out kit.  Exposed buffer tubes are not acceptable.

6.	Individual fiber strands protected by aramid fiber tubes.

7.	Minimum tubing length:  (left blank intentionally)

663-2.05 SINGLE MODE OPTICAL FIBERS.  Single mode (SM) fibers utilized in the cable shall be fabricated from 100 kpsi proof stress glass and primarily composed of silica which shall provide a matched clad index of refraction (n) profile and the following physical and performance characteristics:

1.	Core Diameter: 8.3µm

2.	Maximum Attenuation: 0.4/0.25 dB/Km at 1310/1550 nm, respectively

3.	Maximum Dispersion:  < 3.2 psec/nm-km from 1285 nm to 1330 nm; < 17 psec/nm-km at 1550 nm

4.	Dispersion Wavelength (ZWD): 1301.5 to 1321.5 nm

5.	Zero Dispersion Slope:  0.092 ps/nm2-km

6.	Cladding Diameter: 125 +/- 1.0 µm

7.	Core-to-Cladding Offset (concentricity): < 0.8 µm

8.	Cladding Non-Circularity:  < 1.0 percent

9.	Fiber Coating Diameter:  245 +/- 10  µm

10.	Secondary Coating:  900 µm (as specified for breakout cable/kits, distribution cable, pigtails and patch chords only)

11.	Fiber Colored Diameter:  250 +/- 10 µm nominal

12.	Mode-Field Diameter:  9.3 +/- 0.5 µm at 1310 nm; 10.5 +/- 1 µm at 1550 nm

13.	Attenuation Uniformity:  No point discontinuity greater than 0.10 dB at either 1310nm or 1550nm

14.	(Deleted Intentionally)

15.	Cutoff Wavelength:  <1260 nm

16.	Maximum End-to-End Attenuation per cable length:  (left blank intentionally)

17.	Fiber Light loss at 1310 nm and at 1550 (left blank intentionally)

18.	Maximum cable outside diameter:  (left blank intentionally)

19.	Fiber Polarization Mode Dispersion (PMD): 0.5 psec/km1/2

20.	Fiber Curl: (left blank intentionally)

21.	Proof Test:  All Optical fibers shall be proof tested by fiber manufacturer

22.	Attenuation at Water Peak:  The attenuation at 1383 ± 3 nm shall not exceed 2.1 dB/km.

23.	Numerical Aperture:  0.13

24.	Step Index

25.	Index of Refraction:  * at 1310nm, * at 1550 nm (* - left blank intentionally)

***deleted***

Page is Intentionally Blank

Page is Intentionally Blank

- 663-2.07 FIBER-OPTIC MANHOLES

Manholes or vaults shall be spaced at intervals no greater than 2,500 feet (800 to 1,000 feet typical).  In extreme cases where conduit has no bend as permitted by the Engineer, 3,500 feet is allowable (conduit shall be lubricated with no bends).

Fiber-optic manholes shall be installed at locations where the cumulative, conduit bends, measured from the last manhole, exceed 360 degrees.

Manholes are not required for change in conduit installation method.

Manholes shall not be greater than 5 feet in depth as measured from the manhole lid to the base.

Manhole covers shall be heavy duty to bear vehicle loading.

Two knockouts shall be provided on each sidewall of the manhole where the conduit does not enter.  Knockouts shall be sealed with an approved material that can be easily removed.

Manholes shall be located in the field to avoid drainage swells.

Manholes shall be offset a minimum of 2 feet from the conduit trench when communication conduit is located in the same trench as conduit intended for other purposes (i.e., electrical circuits).

- 663-2.08 MANHOLES

All openings in Type 1 manholes shall be cored or blocked out at the time of fabrication, or cored at the time of placement.  Where conduit is terminated in manholes, the coring or shall be no larger than 1/2 inch each side of conduit.

Manholes shall be constructed on top of 12 inches of No. 2 coarse aggregate.

Manholes shall have a 1-inch diameter drain hole in the base.

Proposed manholes shall be fabricated with fiber-optic cable support assemblies in these specifications and as shown on the plans.  The cost to provide the fiber-optic support assemblies shall be incidental to manholes.

Manholes not placed in the roadway shall be placed in a manner that the cover will be flush with the final grass grade.  Manholes placed in the roadway or in a sidewalk shall be placed flush with the pavement.  Type M covers are required for manholes when installed within terrace, median or off-roadway areas.  Type K covers are required for manholes when installed in the roadway.

- 663-2.09 VAULTS

Work under this item shall consist of constructing a communications vault and vault lid in accordance with the details shown on the plans and as hereinafter provided.

The vault shall be 30 x 48 inches and shall have an effective height of 57 inches (one 24-inch tall stackable vault and one 36-inch stackable vault with 3-inch overlap).

Finished grade of vaults shall be in accordance with pertinent sections of section 660-3.04, Junction Boxes.

The vault lid shall have a minimum design load of 15,000 pounds and shall have a permanently recessed logo that reads "TRAFFIC.”  The communications vault lid shall have two 1/2-inch x 4-inch pull slots.  The lid surface shall have a coefficient of friction of 0.50 in accordance with ASTM C1028.

Steel rebar or mesh pieces shall be completely enclosed within the lid such that grounding is not required, locating under heavy snow is easily accomplished with a metal detector, and the steel does not add excess weight to the lid.  A minimum of one inch of cover shall be provided over the steel.

The vault and vault lid should be constructed of the polymer concrete material, "cosmopolite" and be gray in color.

Manufacturer approved gasketing to resist water from entering the communications vault shall be installed between the lid and the top 24-inch-deep stackable vault.

The vault lid shall be secured to the vault with two 3/8-inch 16 UNC stainless steel pentahead bolts to lock the lid and shall also include the appropriate stainless steel washers.

A fiber-optic cable support assembly shall consist of multiple brackets, racks, and/or rails required to suspend the required surplus cabling and any splice enclosures for a single vault.  The support assemblies shall be recommended and approved by the manufacturer of the fiber-optic cable and splice enclosure.  The support assembly shall be made from or coated weather resistant material such that there is no corrosion of the supports.  The support assemblies shall be anchored to the existing vault using stainless steel hardware.  The fiber-optic cable support assemblies shall be incidental to the communications vault.

Void areas between openings and conduit shall be filled with self-curing caulking that will provide a permanent, flexible rubber which is unaffected by sunlight, water, oils, mild acids and alkali.  The caulking shall be mildew resistant and non-flammable.  The material shall provide a permanent bond between the conduit entering the vault and the polymer concrete.  The caulking shall be gray in color.

All openings in vaults shall be machined at the time of fabrication, as shown on the plans, or punch-driven at the time of placement.  Openings shall be sized to facilitate conduit called for in the plan.

Vault walls that receive only one or no conduits shall be provided with at least one 5-3/4 inch diameter knockouts for future multi-duct installation.  The knockouts shall be aligned across from each other to the extent possible.

663-3.01 CONSTRUCTION REQUIREMENTS

- Fiber-optic Cable

All splicing, testing and terminating of optical fibers shall be performed by a technician in accordance with subsection, Certified Fiber-optics Technician.

All fibers should be tested upon receiving cable.  The contractor shall assume full responsibility to cable that is damaged if testing is not performed after receiving cable.

Before installation, all cables shall be inspected to be free of damage (nail or staple holes, jacket tears, kinks, etc.), material, manufacturing defects, and dimensional non-uniformity that would:

1.	Interfere with the cable installation using accepted cable installation practices.

2.	Degrade the transmission performance and environmental resistance after installation.

3.	Inhibit proper connection to interfacing elements.

4.	Otherwise yield an inferior product.

Physical condition of the cable shall be recorded as outlined in subsection, Documentation of Field Testing.

Cable reel shall be inspected for nails, staples and other materials that might otherwise kink or damage the cable when unreeling.

Cable shall only be spliced at designated splice points as specified in the plans.

A detailed construction plan and installation procedure shall be submitted and approved by the engineer before cable installation.

Take all necessary precautions to protect reeled cable from possible damage while unattended.

Cable installation in conduit (duct) systems shall conform to Corning Cable Systems procedure SRP-005-011, “Fiber-optic Cable Placing-Duct,” or manufacturer approved methods of jetting or pulling.

Cable shall not be kinked or forced abruptly against conduit edge when pulling cable from conduit ends.  Cable feed systems (reels, rollers, guide, tubes etc.) shall be used to install or retrieve cable from conduit ends in vaults, manholes, or junction boxes.

When cable is installed by pulling,  a swivel and woven cable grip designed for fiber-optic cable shall be used.  Materials for lubricating shall be utilized when pulling.

Lengthy cables requiring multiple pulls shall be coiled in a “figure-eight” pattern at intermediated access points to avoid twisting of cable unless cable is assisted by jetting or winching.  The figure-eight patterns shall be approximately 15 feet in length.  Cardboard shims shall be installed between cable layers at the crossover of the “figure eight” to relieve pressure on the cable.

Fiber-optic cable lengths greater than 100 ft shall not be coiled in one continuous direction.

Cable shall be pulled in one continuous run.  Splicing is not allowed until the entire length of cable is installed.

Cable shall be pulled in multiple runs when 2 or more 90o bends occur in the run.  One continuous cable pull shall not contain more than one 90o bend.

Equipment shall be provided to monitor tensile forces on long cable runs.  Monitoring equipment shall measure pulling tension as it occurs and record the maximum tension incurred during the pull.

Maximum tension (600 lbs) or minimum bend radii (20 x diameter of the cable with loading, 10 x cable diameter without loading) on the cable shall not be exceeded at any time.

Exposed cable shall be protected at all times from vehicular and public traffic.

If cable ends are exposed and unattended, cable caps shall be taped onto cable ends to prevent ingress of moisture into the cable.  If caps are not available and the duration of the exposed cable end is short, several wraps of tape shall be provided on the cable end.

Temporary aerial installation methods shall be consistent with Corning Cable Systems SRP-005-010, “Fiber-optic Cable Placing-Lashed Aerial” or manufacturer approved methods.

Excess fiber cable slack shall be provided as follows:

1.	Approximately 100 feet per manhole and vaults containing splices

2.	65 feet per splice vault

3.	20 feet per junction box

4.	6 feet per controller cabinet.

Excess fiber cable slack shall be stored in junction boxes, vaults, and manholes on hooks in accordance with the plans.

Cable slack shall be neatly coiled around the inside perimeter of manholes, vaults and junction boxes and shall be supported cable brackets.  Cable slack shall be supported as to not interfere with access into manholes, vaults, or junction boxes.

The fiber-optic cable shall withstand a maximum pulling tension of 600 lbs during installation (short-term loading) with no damage and 200 lbs (long-term loading).  Tensions on the cables shall not be exceeded under any circumstances.

Manufacturer minimum bend radii for loaded and unloaded conditions shall not be exceeded under any circumstance.  If radii information is not available, minimum bend radii shall not exceed 20 times the diameter of the cable when loaded or 10 times the diameter of the cable unloaded (at rest).

All fiber-optic cable shall be installed with marking tape, copper wire tracer and above ground markers as required in subsection, Multi-duct Conduit.

- Vaults

Vaults shall not be placed near drainage collection areas or where vehicle traffic is anticipated.

To the extent possible, vaults shall be placed so that they are accessible by service vehicles driving close to them.

Brackets for splice enclosures shall be mounted as per vault manufacturer recommendations.

Mounting equipment (i.e., bolts) for cable or splice closures shall not fully penetrate vaults in order to prevent water intrusion.

Where multi-duct conduit is terminated at vaults, the opening shall be no larger than 1/2 inch on each side of the conduit (total of one inch).  Void areas shall be caulked from the interior and exterior of the vault.

Where applicable, conduits shall be terminated in vaults to allow for proper grounding and bonding of metallic conduit.  Where possible, multi-duct conduit termination kits shall terminate at vaults inside wall (or slightly into the vaults interior) to the extent possible.

Where applicable, conduit, conduit terminations, and caulking shall be allowed to fully cure as per the manufacturer’s specification before backfilling vault.

Openings required to install special or directional conduit shall be sealed with manufacturer approved termination kit.

Vaults shall be constructed on top of 12 inches of coarse aggregate.

Polyethylene Conduit

Install polyethylene conduits at 36 inches below finished grade in trenches separate from those used to install traffic signal and highway lighting systems.

Keep junction boxes and ends of conduit covered unless pulling conductors.

Backfill requirements shall be in accordance with Section 204.

Conduit shall be installed in one continuous run between access points.

Conduit shall be installed as linear as possible so as to maximize pulling distances dictated by fiber-optic cable tension requirements.  Bends in conduits shall be minimized to the extent possible.

Directional changes in continuous conduit runs shall not exceed 90°.  Manholes, junction boxes, or vaults shall be provided where 90° directional changes are exceeded.

Required bends, sweeps, fittings, and parts necessary to connect the conduit to vaults, manholes, and junction boxes shall be subsidiary and will not be paid for separately.

Flexible bend sections are not allowed.

Conduit bending radii shall not exceed the minimum-bending radius as dictated by fiber-optic cable requirements.

Where lubrication has not been provided in existing conduit, conduits shall be lubricated according to Corning SRP-005-011 or manufacturer recommended procedures.  Lubrication, when required, shall be suitable to avoid long-term cable jacket damage.

Conduit ends shall be protected at all times from migration of foreign materials and rodents during and after shipment and during installation.  Pre-lubricated conduit with exposed ends will be rejected.  Where provided, non-lubricated conduits left unprotected shall be cleaned before cable installation.

Termination kits shall be installed immediately upon conduit installation.

The conduit fill ratio shall not exceed 0.65 where,

Fill Ration = ∑ Cross Sectional Areas of Cable(s) / Inner Conduit Cross Sectional Area

The recommended maximum fill ratios are as follows:

| Fill Ratio | Number of Cables within conduit |
| --- | --- |
| 0.31 | 2 cables |
| 0.40 | 3 cables |

Terminate all conduit entering vaults or manholes 3 inches past the inside walls of vaults or manholes (vendor says to terminate flush with the inside wall).

A detectable polyethylene marking tape with the words “Buried Fiber-optic Cable” (or similar) shall be laid horizontally above the conduit, 12 inches below final grade.  The marking tape shall be at least 6 inches wide, within 2 inches of the trench width, at least 4 mils thick and orange in color.  Two strips shall be laid side by side under all road crossings.

Install above ground markers at 400-foot intervals.  Markers shall be orange flexible delineators reading “Fiber-optic Interconnect System” (or similar).

Use care during compaction operations to prevent damage to junction boxes and conduits.  Remove and replace items damaged during the backfill and compaction operations at no additional cost to the Department.

Special termination kits shall be provided by the conduit manufacturer for terminating the conduit in manholes and vaults.  The kits shall seal ducts from contamination, rodents, and flooding.  Kits shall be designed to fit the number and size of cable(s) within the conduit and shall allow cable entry and exit within vaults or manholes without inducing stress on the fiber-optic cable or damaging cable jacket.

A No. 12-gauge stranded copper locate wire, orange in color, shall be installed in the spare conduit.  The locate wire shall be approximately 4 feet longer than the run of conduit and shall double back at least 2 feet at each raceway access point.  All locate wires entering manholes, vaults, or junction boxes shall be electrically connected together to provide a continuous locate signal throughout the conduit for locating purposes.  All splices shall be sealed with heat shrink tubing (verify with termination kits).

A polyethylene pull rope shall be installed in all empty conduits for future cable installations.  The rope shall be rated for 1,000 lbs or greater and shall not be less than 1/4 inch in diameter.

All sharp objects (rocks, debris, etc.) shall be removed from the conduit trench before backfilling. The first 6 inches of backfill shall be free of rocks exceeding 1 inch maximum dimension.

***deleted***

Page is Intentionally Blank

- 663-3.02 CERTIFIED FIBER-OPTIC TECHNICIAN

The Fiber-Optic Technician shall have attended and successfully completed at least one four-day "Installation of Fiber-optic Products School."  This school shall be conducted by a major manufacturer of fiber-optic products or an MOA approved independent generic four-day school that encompasses all aspects of fiber-optic technician certification.

Employ only technicians demonstrating a minimum of two years work experience with the splicing, termination, and testing of fiber-optic cable.

The approved technician shall provide evidence of completed courses within one week before the beginning of construction.  The Engineer reserves the right to revoke the approval of any technician not demonstrating the skill and knowledge to perform at accepted industry standards or to the quality required in this specification.

- 663-3.03 TESTING AND PERFORMANCE BY MANUFACTURER

All outdoor cable installations shall meet or exceed requirements of the Fiber-optic Test Procedure (FOTP) criteria referenced in RUS 7 CFR 1755.9 and Bulletin 1753f-601 (PE-90) and these specifications.

Following specifications shall apply to the appropriate Fiber-optic Test Procedures (FOTP):

1.	TIA-455-3-A, FOTP-3 “Procedure to Measure Temperature Cycling Effects on Optical Fibers, Optical Cable, and Other Passive Fiver Optic Components”:  The average change in attenuation at extreme operational temperatures (-40° F to +160°F) shall not exceed 0.05 dB/km at 1,550 nm for single-mode fiber.  The magnitude of the maximum attenuation change of each individual fiber shall not be greater than 0.15 dB/km at 1,550 nm.

2.	When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of un-aged cable for 24 hours, no water shall leak through the open cable end.  When a one-meter static head or equivalent continuous pressure is applied at one end of one-meter length of aged cable of one hour, no water shall leak through the open cable end.  The aging cycle is defined as exposing the cable to 85oC for 168 hours and two cycles of –40oC to +70oC with cable held at these temperatures for 24 hours.  At the end of this cycle, the cable will be decreased to +23oC and held for 24 hours.  The water penetration test is completed at the end of the 24 hours hold.  Testing shall be performed in accordance with the industry standard test, TIA-45-82-B, FOTP-82, “Fluid Penetration Test for Fluid-Blocked Fiber-optic Cable.”

3.	TIA/EIA-455-81-B, FOTP-81, “Compound Flow (Drip) Test for Filled Fiber-optic Cable”:  the cable shall exhibit no flow (drip or leak) of filling and/or flooding material at +65o C.

4.	TIA/EIA-455-41-A, FOTP-41, “Compressive Loading Resistance of Fiber-optic Cables”:  Ten percent of the fibers shall not experience a magnitude of attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The magnitude of the attenuation change shall be within the repeatability of the measurement system for the remaining 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  No fibers shall exhibit a measurable change in attenuation after test load is removed.

5.	TIA/EIA-455-104-A, FOTP-104, “Fiber-optic Cable Cyclic Flexing test.”  Change in attenuation shall not exceed 0.1 dB at 1550 nm for single mode fiber.  The magnitude of the attenuation change shall be within the repeatability of the measurement system for 90 percent of the test

fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

6.	TIA/EIA-455-25-C FOTP-25, “Repeated Impact Testing of Fiber-optic Cables and Cable Assemblies.”  The magnitude of the attenuation change shall be within the repeatability of the measurement of 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable jacket shall not exhibit evidence of cracking or splitting at the completion of the test.

7.	TIA-455-33-A FOTP-33, “Fiber-optic Cable Tensile Loading and Bending Test.”  While subjected to a minimum load of 600 lbf, the cable sample shall be able to withstand a twist of 360 degrees in less than 3 meters of length.  The magnitude of the attenuation change shall be within the repeatability for he measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The cable shall not experience a measurable increase in attenuation when subjected to the rated residual tensile load, 200 lbf.

8.	TIA/EIA-455-85-A FOTP-85, “Fiber-optic Cable Twist Test”:  The magnitude of the attenuation change shall be within the repeatability for the measurement system for 90 percent of the test fibers; the repeatability of the measurement system is typically 0.05 dB or less.  The remaining 10 percent of the fibers shall not experience an attenuation change greater than 0.1 dB at 1550 nm (single mode fiber).  The average increase in attenuation for the fibers shall be <0.40 dB at 1300 nm.  The cable jacket will exhibit no cracking or splitting under a 5x magnification after completion of test.

9.	TIA/EIA-455-181 FOTP-181, “Lightning Damage Susceptibility Test for Optic Cables with Metallic Components:  (left blank intentionally)

10.	TIA/EIA-455-37-A FOTP-37, “Low or High Temperature Bend Test for Fiber-optic Cable” (left blank intentionally)

11.	TIA/EIA-455-98, FOTP-98-A, “Fiber-optic Cable External Freezing Test”:  (left blank intentionally)

663-3.04 FIELD TESTING AND PERFORMANCE OF FIBERS.

All testing of optical fibers shall be performed by a Certified Technician as described in subsection, Certified Fiber-optic Technician.

All fibers should be tested upon receiving cable.  The contractor shall assume full responsibility to cable that is damaged if testing is not performed after receiving cable.

Physical condition of the cable shall be recorded as outlined in subsection, Documentation of Field Testing.

The contractor shall schedule the date, time, and location of any tests required by this specification with Engineer and MOA Traffic Personnel (907-343-8355) 72 hours before performing the tests.  MOA Traffic personnel shall be present when the tests are conducted.  The certification technician shall demonstrate clearly how the tests are being performed and shall be made available to discuss testing strategies with MOA personnel.

Tests shall be conducted using standard operating procedures as defined by the manufacturer of the test equipment.

The following tests shall be conducted after the cable has been installed, spliced, and connectorized.  Test results shall be submitted in accordance with subsection Documentation of Field Testing (NCHRP).  Tests shall be preformed before any permanent equipment connections.  All fibers shall be tests for continuity, events above 0.05 dB and total attenuation of the cable.  If the fiber-optic cable installed is connected to an existing fiber-optic cable, perform installation tests on the installed cable and all existing fibers to which it is spliced or connected:

1.	End-to-end OTDR (Optical Time Domain Reflectometer) testing shall be conducted to identify attenuation associated with each fiber.  Traces shall be provided for each operational wavelength for the type of fiber in the system to indicate attenuations and their locations.

A Certified Technician utilizing an OTDR and Optical Source/Power Meter shall conduct the tests after installation.  The Technician shall conduct the test according to the standard operating procedure as defined by the manufacturer of the test equipment.

To eliminate or shift the “dead zone,” either a factory patch chord or “fiber launch box” of length greater than the dead zone shall be used.

Measurement shall be conducted for 1310 and 1550 nm for single mode fiber.

2.	Attenuation Test.  All fiber links shall be tested with a standard power-meter test and all attenuation shall be documented.

For every fiber installed or connected to under this Contract, perform end-to-end attenuation test.  For the test, use a calibrated optical source and power meter using the standard three-stage procedure.  Determine acceptable link attenuation by the cumulative value of standard losses based on length, number, and type of splices and connectors.

Provide test results of the fiber-optic cable that demonstrate the dB/km loss does not exceed +3 percent of the factory test or 1 percent of the cables published production loss.  The Engineer may elect to allow bi-directional averaging of OTDR testing due to splice loss core alignments.  Fiber-optic cable loss limits shall be in accordance with the following.  The Engineer may elect to allow bi-directional averaging of OTDR testing due to splice loss core alignments:

1.	No event shall exceed 0.10 dB.  If any event is above 0.10 dB, repair or replace that event location.

2.	Total dB loss of a cable fiber less events shall not exceed +3 percent of the factory test or 1 percent of the manufacturer’s published production loss at 1310 and 1550 nm.  Cable fiber loss shall not exceed Maximum Attenuation Limits as defined in subsection, “Single Mode Fiber-optic Cable.”

Cable Fiber Loss (dB)  =   Total Loss (dB)  - ∑ events (dB)

Cable Fiber Loss (dB/km) =  Cable Fiber Loss (dB)

Cable Fiber Length (km)

3.	Where total or event losses exceed these specifications, replace or repair that cable run and assume all expenses, both labor and materials.  Elevated attenuation due to exceeding pulling tension during installation will require replacement of cable at the Contractor’s expense.

Fusion splice losses shall not exceed 0.10 dB per fiber.  Mechanical splices, where allowed, shall not exceed 0.30 dB.

Each connector, after factory assembled, shall not exceed the maximum loss of 0.50 dB (typical loss is 0.25dB) and optical return reflective loss of <-0.45dB.

If event losses exceed these specifications, event locations shall be replaced or repaired without additional cost reimbursement for expenses.

If total loss exceeds these specifications, Fiber-optic cable shall be replaced or repaired without reimbursement for expenses.

All fibers within the cable shall be usable.

- 663-3.05 DOCUMENTATION OF TESTING

Upon completion of the field test, the contractor shall provide three copies of all documentation to the Project Engineer.

Except for standard bound materials, documentation shall be neatly bound in 8.5” x 11” (size A4) documentation in logical groupings.  Bindings shall be of either the 3-ring or plastic slide-ring type.  Permanently and appropriately label each such bound grouping of documentation.

Documentation from manufacturer shall include manufacturer data of cable and fiber including:  Optical performance (OTDR) including dB/km loss measured at 1310 and 1550 nm for single mode, manufacturer’s name, date of manufacture, Index of Refraction, cable ID, connector losses and bandwidth/dispersion data.

Documentation of field testing shall include a map of the cable part numbers, manufacturer, cable length markings, as-built cable routing map, location of splice points and hardware at each splice point location (see below under testing also).  Documentation shall include the information below for end-to-end testing, splice loss measurements, OTDR traces.

The documentation shall be neatly tabulated for each field test and shall include the following:

1.	Cable and Fiber Identification:

| Manufacturer | Operator Name |
| --- | --- |
| Cable ID | Date and Time |
| Fiber ID (include tube and fiber color) | Date of installation |
| Cable Location – begin and end point | Fiber Count |
| Cable (i.e., singlemode, loosetube, OSP, OFNG-nonconductive general etc.) |  |

2.	Setup Parameters:

| Wavelength | Range (OTDR) |
| --- | --- |
| Pulse Width (OTDR) | Scale (OTDR) |
| Refractory index (OTDR) |  |
| Jumper and/or Launch Box Length |  |

3.	Test Results:

A.	OTDR Test:

| Total Fiber Trace (mile) | Total Length (OTDR) (mile) |
| --- | --- |
| Splice Loss/Gain | Events > 0.05 dB |
| Measured Length (Cable Marking) | Backscatter |
| Provide traces on Diskette to Engineer |  |

End-to-End Attenuation Test:

| Length, number and type of splices and connectors |  |
| --- | --- |
| Link Attenuation |  |

Fiber-optic cable test results shall demonstrate that dB/km losses do not exceed limits in accordance with subsection, Field Testing and Performance of Fibers.

- 663-3.06 PACKAGING

Fiber-optic cables shall be shipped on wooden reels.  The diameter of the drum shall be a least 20 times the diameter of the cable.  The following information shall be either stenciled on the reel or on a weatherproof tag firmly attached to the reel or a combination of both in order to trace the manufacturing history of the cable:

1.	Optical Cable

2.	Number of Fibers

3.	Date cable was tested

4.	Non-armored

5.	Year of cable manufacture

6.  Name of cable manufacturer

7.  Gross weight

8.  Part Number

9.  Handling Instructions

10.  Arrow indicating cable wind direction

Cable data sheets shall be supplied to MOA Traffic Department containing the following:

1.  Manufacturer Name

2.  Cable ID Number and fiber type

3.  Factory Order Number

4.  Cable Length

5.  Factory measured attenuation (each fiber)

6.  Index of Refraction

7.  Bandwidth Specification (where applicable)

Sufficient cable length, in addition to the quantities shown on the plan, shall be provided for testing.  Both ends of the cable shall be available for testing.  Pack one continuous length of fiber-optic cable per reel; maximum overage shall not exceed 10 percent unless approved by The Engineer.  Compensation will not be granted for overage or excess cable needed for testing and installation methods.

Package the cable for shipping to prevent the cable from coming loose in transit.  Secure the outer and inner end of the cable.  Cover the reel with thermal wrap to protect the cable.  Apply end seals to each end of the cable to prevent moisture from entering the cable.

Include the manufacturer’s test documentation with each reel.  This documentation indicates the attenuation of each cable fiber in dB/km (dB/ft), measured at 1310 and 1550 nm for single mode fiber.

- 663-3.07 CONNECTORIZATION

- Connectors

This subsection shall consist of furnishing and installing connectors (in-line or terminated ends) or attenuators as required in the plans or as required for working fiber-optic system.

Hybrid adaptors shall not be used to connect two different connectors.  Hybrid jumpers with different connectors at each end of cable shall to interface equipment or cables with different connectors where needed.

All connectors shall be installed by a Certified Technician as described in this specification.

Connectors shall be LC connectors for single mode fibers.

Ceramic ferrules shall be provided for all fiber-optic connector applications.  Install connectors per manufacturer application and recommendations, including proper termination to the outer tubing (900 micron, 3 mm fan-out) as required by the application.

Connectors shall be rated for operating temperatures of -40oF to 160oF.

Connectors shall be factory installed for all applications except where approved by the Engineer.

Connectors shall be installed with ceramic ferrules with fibers secured within ferrule with epoxy, heat set or air dried, as specified by the manufacturer; machine polished mating faces shall be provided.

Boots shall be provided for durable cable strain relief.

Dust caps shall be provided and installed at all times when connector is not in use.

If connections are made, connectors shall be cleaned once before the first connection and once every time thereafter before reconnection.  Connectors shall be cleaned according to manufacturer’s recommended practice.

Connector losses shall not exceed limits as described in subsection, Field Testing and Performance of Fibers.

Repeatability of keyed connectors shall not exceed 0.2 dB.

Ceramic ferrule color-coding for SC connectors, when used, shall be used as follows to identify type of connector polish as follows:  (left blank intentionally)

- 663-3.08 ATTENUATORS

Attenuators shall be provided at no extra payment to the contractor to achieve the desirable signal losses at the receiving end equipment (modems, etc.).  Attenuators shall only be installed on the receiving end closest to the originating transmission (typically closest to the Traffic Signal Management Center).

Connecting ends shall be compatible to connectors described in subsection, Connectors.

- 663-3.09 SPLICES

All splicing and termination of optical fibers shall be performed by a Certified Technician as described in this specification.

Two weeks before the start of the fiber-optic cabling installation, the contractor shall submit the following:  proposed locations of the mainline spliced points for review by the Engineer and MOA Traffic Department; the proposed process to be used for splicing including procedure, cleave tool and specific fusion splicer to be used.

Splicing shall only be allowed in areas as designated on the plans or as approved by the Engineer.

All splices and stripped cable shall be housed by a splice closure.

Mainline splices shall consist of end-to-end fusion splices for all fibers (72 fibers typical) within the fiber-optic cable where designated in the plans.

Drop fiber splices (6 fiber typical) and drop cables (6 fibers typical) shall be used for connectivity between a primary mainline fiber-optic cable (72 count typical) and field devices (i.e., traffic signal controller cabinet) as identified in the plans.

Drop fiber splices shall consist of breaking out the required buffer tube(s) from the fiber-optic trunk cable (72 count typical) and fusion splicing the appropriate number of fibers to the fiber-optic drop cable (6 fibers typical).  Remaining undisturbed fibers, if any, shall be protected in the splice tray.  End-to-end fusion splicing shall be conducted for any disturbed fibers within the disturbed buffer tube(s).  Remaining buffer tube(s) that are not required for splicing shall be undisturbed and protected in the Splice Closure.

Splicing (drop splice) shall be performed for each device location at locations shown on the plans.  Splicing shall be performed as per Corning Cabling Systems Recommended Procedure SRP-004-013, Mid-Span Access of Fiber-optic Cable (Cable Slack Present), or an equivalent manufacturer’s recommended procedure approved by Municipality Traffic Department.

Cable ends involved in splicing shall match colors of the fibers and buffer tubes to the extent possible.

Fiber splices shall be contained within fiber splice closures (FSC) in designated locations shown on the plans.

All splices shall be fusion splices protected with a heat shrink sealant (RTV fusion splices) Mechanical splices are not allowed.

Fusion splices shall be made with a portable fusion splicer, capable of AC or internal battery-powered operation.  The unit shall be able to splice fibers specified in these with 250 micrometer coating and 900 micrometer coating with little or no modification in the field.  The fusion splicer shall be capable of full battery recharge in an eight-hour charging period.

End-to-end splicing shall be performed as per manufacturer instructions for the supplied splice closure units.

No stresses shall be placed on the fibers before or after the splice is completed.

Splice loss shall not exceed limits as described in subsection, Field Testing and Performance of Fibers.

Fan-out kits are required for splices to multiple fibers in the buffer tubes for single mode fiber (NCHRP).

Splices shall be located in the center of the slack cable in junction boxes, manholes, or vaults.

- 663-3.10 SPLICE CLOSURES

Fiber-optic splice closures (FSC) shall be installed in the locations on the plan at designated splice locations.  Closures shall contain splice trays or organizers that contain the splices.

Before installation, the contractor shall provide certification from the manufacturer that the splice closures conform to the specifications and test procedures.

Splice closures shall be designed for use under the most severe conditions such as moisture, vibration, impact, cable stress, and flex temperature extremes as demonstrated by successfully passing factory test procedures and these specifications.  The closure shall prevent the intrusion of water without the use of encapsulates.

Closure re-entry and subsequent reassemble shall not require specialized tools or equipment; these operations shall not require the use of additional parts.

Splice closures shall provide housing and storage for all splices, stripped cable, and undisturbed buffer tubes.  All splices enclosures shall provide protection and strain relief to optical fibers.

Splice closures shall be suitable to handle straight, butt or branch splices.

For splice closures requiring greater than 48 splices shall provide for the following requirements:

1.	6-inch diameter by 22-inch length

2.	One, six-cable entry end plate

3.	One blank end plate

4.	All endplates shall be 3-section, pre-molded, and suitable for use with Coyote closures

5.	Required accessories to complete splice

6.	One future cable entry kit for each splice closure

Closures shall be provided with external valve pressurization ports.

Closure shells shall be glass-filled high-density thermoplastic that effectively withstands corrosion; high impact and freeze thaw stresses.

Closure endplates shall be interchangeable with each size of closure available from the closure supplier.

Where additional access is required into an existing splice closure, replace the existing endplate with an endplate suitable for the task.

Splice closures shall accept up to six cables in a butt configuration and 12 for in-line configuration without special adaptors.

Closure shall contain a permanent neoprene gasket seal.

All closures, including closing hardware, shall be from the same supplier.

External Shrader valve pressurization port shall be supplied.

The splice case shall be designed and equipped with the necessary mounting hardware to be attached to the side of the manhole or vault and to be suspended with sufficient clearance at each end for acceptable cable bends.

All cables shall be properly dressed and affixed to rails or racks within the manhole or vault.  No cables or enclosures will be permitted to lie on the floor.

Fiber-optic cables shall be restrained within the splice enclosure such that there is no discernible tensile force on the optical fiber.

The splice closure shall have provisions for storing fiber splices in an orderly manner, mountings for splice organizer assemblies and space for excess or unspliced fiber.  Splice organizers shall be re-enterable and re-sealable.

The closure shall be capable of accommodating splice organizer trays, which accept mechanical, fusion, or multi-fiber array splices.

Splice cases shall hold a minimum of 2 splice trays with a maximum number of splice trays to hold up to 96 splices.

One splice tray shall be designed to hold a minimum of 12 mechanical splices.  A second splice tray (for Fiber-optic Drop Cable splicing) shall be designed to hold a minimum of 12 fusion splices.  All other splice trays provided in the closure shall be designed to hold fusion splices of 12 (typical) up to 36 splices.  Total number of splices supported shall be 96 splices.

Splice trays shall allow for optical fiber storage as recommended by the manufacturer.

The splice closure shall have provisions for controlling the fiber bend radius (1.5 inches typical) to a minimum as required by the manufacturer.

Splice closure shall contain a basket allowing fiber buffer tube storage of exposed buffer tubes.

The splice case shall be UL rated.

The closure shall be installed according to the manufacturer’s recommended guidelines.

663-3.11 SPLICE CLOSURES FACTORY TESTING REQUIREMENTS

The construction and testing of the fiber-optic splices and splice enclosures shall comply with all applicable industry standards including:  Electronic Industry Standards (EIA/TIA), ANSI and ASTM standards.

Splice closures shall meet the following test requirements.

Compression Test:  The closure shall not deform more than 10 percent in its largest cross-sectional dimension when subjected to a uniformly distributed load of 300 lbf (1335 N) at temperatures of 0oF and 100oF (–18oC and +38oC).  The test shall be performed after stabilizing at the required temperature for a minimum of 2 hours.  It shall consist of placing an assembled closure between two flat paralleled surfaces, with the longest closure dimension parallel to the surfaces.  The weight shall be placed on the upper surface for a minimum of 15 minutes.  The measurement shall then be taken with weight in place.

Impact Test:  The assembled closure shall be capable of withstanding an impact of 21 ft-lbf (28 N-m) at temperatures of 10oF and 100oF (-12oC and 38oC).  The test shall be performed after stabilizing the closure at the required temperature for a minimum of 2 hours.  The test fixture shall consist of a 20 lb (9 kg) cylindrical steel impacting head with a 2-inch (5 cm) spherical radius at the point where it contacts the closure.  It shall be dropped from a height of 12 inches (30 cm).  The closure shall not exhibit any cracks or fractures to the housing that would preclude it from passing the water immersion test.  There shall be no permanent deformation to the original diameter or characteristic vertical dimension by more than 5 percent.

Cable Gripping and Sealing Testing:  The cable gripping and sealing hardware shall not cause an increase in fiber attenuation in excess of 0.05 dB/fiber @ 1550 nm when attached to the cables and the closure assembly.  The test shall consist of measurements from six fibers, on from each buffer tube or channel, or randomly selected in the case of a single fiber bundle.  The measurements shall be taken from the test fibers, before and after assembly to determine the effects of the cable gripping and sealing hardware on the optical transmission of the fibers.

Vibrations Test:  The splice organizers shall securely hold the fiber splices and store the excess fiber.  The fiber splice organizers and splice retaining hardware shall be tested per EIA standard FOTP-11, Test condition I.  The individual fibers shall not show an increase in attenuation in excess of 0.1 dB/fiber.

Water Immersion Test:  The closure shall be capable of preventing a 3-meter (10–foot) waterhead from intruding into the splice compartment for a period of 7 days.  Testing of splice closure is to be accomplished by the placing of the closure into a pressure vessel and filling the vessel with tap water to cover the closure.  Apply continuous pressure to the vessel maintain a hydrostatic head equivalent to 10 ft (3 m) on the closure and cable.  This process shall be continued for 7 days.  Remove the closure and open to check for the presence of water.  Any intrusion of water in the compartment containing the splices constitutes a failure.

Certification:  It is the responsibility of the contractor to insure that all of the above tests have been performed by either the manufacturer, or an independent testing laboratory, and the appropriate documentation has been submitted to the Engineer.  Manufacturer certification is necessary for the model of closure supplied.  It is not necessary to subject each supplied closure to the actual tests described herein.

663-3.12 WARRANTY AND MAINTENANCE

Manufacturer’s support (customary warranties) period shall be provided for all equipment and materials furnished and installed as part of the fiber-optic system, including end equipment (modems, panels, switches etc.).  Manufacturer’s and Contractor’s warranties or guarantees shall be continuous throughout their intended duration and state they are subject to transfer.

663-3.13 METHOD OF MEASUREMENT

The Engineer will measure all work required to install a complete signal interconnect system as lump sum.

663-3.14 BASIS OF PAYMENT

The contract price paid per lump sum for signal interconnect system constitutes full compensation for furnishing all work and materials required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under item 660(1B) Traffic Signal System Modifications at Old Seward Highway.

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 663(1) | Fiber Optic Signal Interconnect System Complete | Lump Sum |

Special Provision

Add the following Section:

SECTION 669

AUTOMATED TRAFFIC RECORDERS

669-1.01 DESCRIPTION.  This work shall consist of furnishing and installing traffic count stations for the automated collection of traffic data on an intermittent or permanent basis.  The Automated Traffic Recorder (ATR) station is a vehicle detection system.

The ATR station can be a combination of detection, electronics and software and is defined as a system.  Four types of systems are defined as follows:

1.	An Intermittent ATR station shall consist of the following:

a.	inductive loop detectors for detecting the presence of vehicles, and

b.	underground conduit, junction boxes, cabinet, and wiring as specified on the Plans.

2.	A Traffic Volume Count System shall consist of the following:

a.	inductive loop detectors for detecting the presence of vehicles,

b.	electronics for collecting and storing data obtained from the sensors,

c.	communications capabilities (e.g. modem and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, cabinet, modem, electrical and telephone service as specified.

3.	An Automated Vehicle Classification System (AVC) shall consist of the following:

a.	Piezoelectric sensors for detecting vehicle presence and counting axles and measuring axle spacing,

b.	electronics for collecting, analyzing and temporarily storing the data obtained from the sensors,

c.	communications capabilities (e.g. modem, remotely controllable code operated switch and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel, and

d.	underground conduit, junction boxes, cabinet, electrical and telephone service as specified.

4.	A Weigh In Motion (WIM) System shall consist of the following:

a.	Piezoelectric or bending plate sensors for detecting vehicle presence and counting axles and measuring axle spacing and weight,

b.	electronics for collecting, analyzing and temporarily storing the data obtained from the sensors,

c.	communications capabilities (e.g. modem, remotely controllable code operated switch and cabling) for transmitting the data to IBM PC compatible computers located both in the Highway Data Office in Anchorage, Alaska, and portable laptop computers carried to the equipment site by State personnel,

d.	underground conduit, junction boxes, cabinet, electrical and telephone service as specified,

e.	modification to the pavement section at the WIM installation to provide a smooth approach to and adequate mounting foundation for the axle weight sensors, and

f.	a gravel pad for installation of the equipment cabinet and off-street parking for calibration and service vehicles.

The locations of traffic detection, and cabinets, shown on the Plans are approximate and the Engineer shall establish the exact locations in the field after consultation with the ADOT&PF Highway Data Section.

Concrete pavement work shall consist of furnishing and placing Portland cement concrete for concrete road section at Weigh In Motion (WIM) Installation site in conformance with Section 501 or as established on the plans.

General descriptions of the Automated Traffic Recorders are as follows:

669-1.02 REGULATIONS AND CODE.  Materials and workmanship shall conform to the standards of the Underwriters Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

Electrical equipment shall conform to the standards of the National Electrical Manufacturers Association, where applicable.

669-2.01  MATERIALS.  The materials provided for the work shall be new, unless otherwise stated and must meet the following requirements:

1.	Wiring.  Wiring shall be according to subsection 660-2.09(A), Wiring.  Single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type and letter designation, the conductor size, voltage rating and the number of conductors if a cable.

2.	Conduit.  Conduit shall be according to subsection 660-2.05, Conduit.  Nylon pull cords shall be left in 2-inch conduit.

3.	Junction Boxes.  Junction boxes shall be according to subsection 660-2.06, Junction Boxes.  Junction boxes used for ATR installations shall not contain  conductors carrying a voltage over 50 volts.

4.	Terminal Blocks.  Provide terminal blocks with nickel, silver, or cadmium plated brass binder head screw terminals.  Terminal blocks shall be a barrier type, 600vac at 20amps, capacity for 12 to 18 AWG wire.  Terminal blocks shall have removable shorting bars in each position and have integral type marking strips.  Conductors shall be terminated and labeled to a terminal block.

5.	Inductive Loops.  Inductive loops shall be according to subsection 660-2.08, Conductors.  Conductors used for detector inductive loops shall be UL listed as Type RHW/USE/XLP 12AWG 600V rating.  Multiple pair loop lead-in cable shall consist of 18AWG stranded tinned copper wire with each twisted pair containing a 20AWG tinned copper drain wire, and aluminum shield and overall PVC or PE jacket conforming to IMSA specification 50-2.

6.	Cabinets.  Cabinets shall be unpainted, brushed aluminum and shall have a NEMA 3R rating.

7.	Asphalt Pavement.  Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement for Asphalt Concrete, Type II.

8.	Modem.  The Contractor shall supply and install a high speed modem.  The modems shall meet the following requirements:

a.	300, 1200, 2400 4800, or 9600 baud selectable.

b.	Automatic Answer Mode.

c.	Hayes 2400 compatible.

d.	Pulse or touch-tone dialing.

e.	Full or half-duplex operation.

f.	External switches for COM port 1-4 selection.

g.	Compatible with CCITT V.22, Bell 103, and Bell 212A modem specifications.

h.	Meets FCC Part 15, FCC Part 68 regulations for direct connection to telephone lines.

i.	Hardware flow control.

The modem shall be equal or better to a Multitech 9600.

9.	Remotely Controllable Code Operated Switch.  The Contractor shall supply and install a remotely controllable code operated switch.  The code operated switch shall meet the following requirements:

a.	Minimum 8 addressable ports.

b.	Speed: 110 to 19,200 bps, each port individually settable.

c.	Flow Control:  Hardware X-ON/X-OFF.

d.	Data Format:  7 or 8 data bits; odd, even, or no parity.

e.	Connectors:  DB25s (female); DTE/DCE strap-settable.

f.	Power:  115 VAC, 60 Hz, 5 watts.

Suggested Model GS-SW540A with 4-port expansion board Model GB-SW541-C available from Black Box Corporation or equivalent.

10.	Traffic Volume Counters.  The Contractor shall supply and install traffic volume equipment with the capability of counting traffic in all lanes.  The permanent traffic volume counter(s) shall be GK brand units available from Capital Enterprise & Engineering Corp., P.O. Box 12688, Salem, OR  97309, phone (503) 363-9290.  The permanent traffic volume counters shall include:

a.	GK model 6000 TC.

b.	Loop cards.

c.	Communications card.

d.	Rechargeable battery.

e.	64KB data module.

f.	Battery charger.

g.	Connective cable.

h.	Modem cable.

i.	User manual.

11.	Automated Vehicle Classification (AVC) Counters and Sensors.  The Contractor shall supply and install an automated vehicle classification.  The AVC counters and piezoelectric axle sensors shall be PAT brand C100S available from PAT Equipment Corporation, Inc., 1665 Orchard Drive, Chambersburg, PA  17201, phone (717) 263-7655.  AVC counters and sensors shall include:

a.	PAT model C100S.

b.	Loop card(s).

c.	Communications card.

d.	Loop cable(s).

e.	Power cable.

f.	Axle detector cable.

g.	Modem cable.

h.	User manual.

i.	Rechargeable battery.

j.	Battery charger.

k.	Piezo axle sensor (1 per lane).

l.	Epoxy with hardener for each piezo axle sensor.

12.	Weigh In Motion (WIM) Counters.  The Contractor shall supply and install a weigh in motion system.  The WIM electronics and sensors shall be International Road Dynamics (IRD) brand Piezoelectric WIM equipment available from International Road Dynamics, 702 43rd Street East, Saskatoon, Saskatchewan, Canada S7K 3T9, Phone (306) 653-6600.  WIM electronics and sensors shall include:

a.	IRD Piezoelectric WIM basic units, including 386 computer, 110 volt power supply, monitor, keyboard, 3.5-inch floppy drive, 40Mb hard disk drive, and DOS software.

b.	Loop cards.

c.	Loop cables.

d.	Piezoelectric Sensors Class I AS500 (2 per lane).

e.	Piezoelectric cards, 4 channel.

f.	Modem cable.

g.	User Manuals.

h.	IRD WIM software.

13.	Temperature Probe and Data Logger.  The Contractor shall provide and install a 6-foot temperature probe.  The temperature probe and data logger shall meet the following requirements:

a.	Total of 16 thermistors.

b.	Degree of accuracy + 0.1 degree C.

c.	Thermistor number one on 12 foot wire lead.

d.	Thermistors at 3 inch spacing for first 12 inches.

e.	Thermistors at 6 inch spacing from 12 to 72 inches.

f.	Side mounted 82 foot cable.

g.	Storage capability for 16 thermal readings at one-hour intervals for a minimum of 90 days.

h.	Battery and power supply/charging unit to enable continuous operation from 110 volt service.

i.	Cables and connectors needed to complete the system.

Suggested model TP101 temperature probe and data logger available from Measurement Research Corporation, 4126 4th Street NW, Gig Harbor, WA 98335, Phone (206) 851-3200.

669-3.01 CONSTRUCTION REQUIREMENTS.

1.	Wiring.  Wiring shall be installed according to subsection 660-2.09(A), Wiring.  Unused pairs shall be terminated within splices; at cabinets unused pairs shall be terminated at to a terminal block and labeled "SPARE".

2.	Conduit.  Conduit shall be installed according to subsection 660-2.05, Conduit or as indicated on the Plans.

3.	Junction Boxes.  Junction boxes shall be installed according to subsection 660-2.06, Junction Boxes or as indicated on the Plans.

4.	Terminal Blocks.  Terminal blocks and wire pairs shall be clearly labeled on the block.  Terminal blocks within cabinets shall be permanently mounted so terminals are easily accessible from the front of the cabinet.  By convention, wire pairs shall be labeled such that inductive loops and other sensors in the lane nearest to the cabinet are at the top or left side of the block.

5.	Inductive Loops.  Inductive loops installed through existing asphalt paving shall be installed using full lane width cuts a minimum of 8 feet in length, with the inductive loops centered in the 8 foot cut with a minimum distance of 1 foot to the edge of the cut.  Edges of the cuts shall be tack-coated during patching to ensure full adhesion.  Full width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from 'telegraphing' through the final lift asphalt.  Compaction tests shall be required at the discretion of the Engineer.

Loops installed in new asphalt paving shall be installed immediately before final paving of the particular section of road.  Installation of loops after final lift paving shall not be permitted.

There shall be no transverse seams, joints or roughness within 50 feet of any inductive loops.  The finished surface of the asphalt shall be tested with a straightedge 10 foot long.  The surface shall not vary more than 0.25 inches from the lower edge of the straightedge in an area within 50 feet of the sensors at the ATR installations.  At the discretion of the Engineer, a profilograph equipped with a chart recorder shall be run down each wheel path of each lane for a distance of 50 feet before and after each ATR installation.  The profilograph will be supplied by the Highway Data Section and shall be operated by Contractor personnel.  The asphalt surface as recorded by the chart recorder shall not vary more than 0.25 inches in 10 feet.

Inductive loops shall be formed of four turns of wire, and shall be 0.5 square with + 1-inch tolerance.  Inductive loops in a lane shall be located 16 feet from leading edge to leading edge except for the loops used in the WIM system which shall be 26 feet from leading edge to leading edge, with + 1-inch tolerance.  Inductive loops located in adjacent lanes shall be aligned within + 1-inch tolerance.

Lead-in conduit from edge of pavement to the inductive loops shall be straight and perpendicular to the centerline of the road.

6.	Cabinets.  Style 3 control cabinets shall be installed according to subsection 660-4.01, Installation Details.  Style 1 and 2 cabinets shall be installed as indicated in the Plans.

7.	Piezoelectric Sensors for AVC.  Permanent piezoelectric sensors shall be installed according to AVC equipment manufacturer's recommendations.  Coaxial cables shall be run to the equipment cabinet without splices and terminated on the specified terminal block, with at least 6 foot of slack cable available in the equipment cabinet before the terminal block. Acceptance testing shall be performed by the Contractor to ensure compliance with subsection 669-3.02, Acceptance Testing.

8.	Class I Piezo WIM Sensors and Electronics for WIM.  Permanent Piezo WIM sensors shall be installed according to WIM equipment manufacturer's recommendations.  A manufacturer's representative shall be present to supervise installation of the piezo WIM sensors and to commission the WIM equipment as a complete and fully functioning system.  The Contractor shall make arrangements to schedule delivery of equipment and to schedule the manufacturer's representative.

The piezoelectric WIM sensors will be installed between two inductive loops.  The 6 foot square loops shall be spaced 26 feet from leading edge to leading edge, with 24 feet between the loops as specified in subsection 669-3.01(5).  The piezoelectric sensors shall be installed using epoxy per manufacturer's specification in saw cut slots approximately 1.5 inches wide, 1.5 inches deep, and 12.5 feet long.  The sensors shall be spaced 12 feet apart with + 1 inch tolerance, centered between the loops with + 1 inch tolerance, and spaced 6 feet from each sensor to the edge of the adjacent loop.

Cables shall be run to the equipment cabinet with no more than one splice per cable and terminated on the specified terminal block, with at least 2 feet of slack cable in each junction box and at least 6 feet of slack cable available in the equipment cabinet prior to the terminal block.

Acceptance testing shall be performed by the Contractor to ensure compliance with subsection 669-3.02, Acceptance Testing.

9.	Temperature Probe.  The temperature probe shall be installed vertically in a 7 foot deep by 6 inch diameter hole augured through the asphalt shoulder.  The probe shall be located in the shoulder in front of the cabinet, and placed 2 feet from the edge of the lane.  The 1.5 inch diameter temperature probe shall be placed in the center of the augured hole and backfill the hole with fine sand to the bottom of the asphalt.  The top thermistor on the 1 foot lead shall be placed 1.5 inches below the top surface of the asphalt, and the hole shall be filled with asphalt patch material and compacted.  The 78.7 foot cable shall be brought to the edge of the road in a saw-cut channel, which is then filled with 3-M loop sealant.  The cable shall be run underground to the nearest junction box and then through conduit to the controller cabinet and connected to the data logger.  The data logger shall be connected to the matrix switch to enable remote data retrieval over the telephone line.

10.	Utilities.  The Contractor shall provide and install the load center according to the Plans, Specifications, and the requirements of the appropriate Electrical Utility.  Wiring from the load center to the equipment in the cabinet shall be provided and installed by the Contractor.  The Contractor shall request inspection of the load center by the Department of Labor, Division of Mechanical Inspection (DOL/DMI).  After approval of the load center by the DOL/DMI the Contractor shall inform the Engineer as to when electrical service is needed at the load center, with sufficient time to enable the Engineer to schedule the installation with the Electrical Utility prior to commissioning of the equipment.  The Engineer will make arrangements in writing with the Electrical Utility to connect to the load center.  The Electrical Utility will provide service to the load center upon request of the Engineer.

The Telephone Utility will provide and install a Network Interface Device (NID) on or near the cabinet.  Underground wiring for telephone service will be provided and installed by the Telephone Utility, usually in association with the Electrical Utility when electrical service is installed. The Contractor shall provide and install a RJ-11 telephone jack inside the cabinet, and shall provide and install the wiring to connect the telephone jack with the NID.  The Contractor shall inform the Engineer as to when telephone service is needed at the telephone jack, with sufficient time to enable the Engineer to schedule the installation with the Telephone Utility before commissioning of the equipment.  The Engineer will make arrangements in writing with the Telephone Utility to install and connect the NID.  The Engineer will inform the Contractor of the telephone number at the NID.

669-3.02 ACCEPTANCE TESTING.  The Contractor shall perform acceptance testing on ATR installations.

1.	General Tests.  ATR installations shall be tested according to subsection 660-4.01, Installation Details.

2.	AVC Acceptance Tests.  In addition to the General Tests, perform Acceptance Tests on the automated vehicle classification installations.  Perform acceptance tests to demonstrate that the AVC system performs at or above the required accuracy.

a.	Accuracy Requirements - The accuracy of Automated Vehicle Classifiers is such that, if good lane discipline is maintained:

(1)	not more than plus or minus ten percent of the total vehicles in FHWA class one through class three and

(2)	not more than plus or minus five percent of the total vehicles in FHWA class four through class thirteen are classified in the wrong bin when compared with a concurrent manual classification count.

b.	The AVC Acceptance Test shall consist of an hour by hour and summary comparison of a manual classification count with the output of the permanent AVC.  A manual vehicle classification count shall be performed for sixteen consecutive hours at the AVC site.  During that 16 hour period, a minimum of five vehicles in an individual vehicle type bin is required in order to be included in the final comparison.

c.	The difference between the number of vehicles in each type bin as observed manually and as recorded by the AVC system shall be computed.  If more than the allowed percentages as listed above are classified in the wrong bin when compared with a concurrent manual classification count, the AVC equipment shall be recalibrated and the test performed again until the system meets the required accuracy.

3.	WIM Acceptance Tests.  In addition to the General Tests, perform Acceptance Tests on the weigh in motion installations after Calibration of the WIM system has been performed. Acceptance tests shall be performed to demonstrate that the WIM system performs at or above the required accuracy.

a.	Acceptance Tests shall consist of three vehicles which will make ten passes over the WIM sensors in each lane at speeds varying from 10 to 230 miles per hour.

b.	The three test vehicles shall consist of a five axle, eighteen wheel single trailer vehicle (FHWA Class 9), a three axle, ten wheel single unit vehicle (FHWA Class 6), and a two axle, six wheel single unit vehicle (FHWA Class 5).  The three test vehicles shall be fully loaded with non-shifting material to near legal weight limits.

c.	Test vehicles tires shall be inflated to recommended pressures.

d.	The gross weight of the vehicles and the weight of each axle group shall be determined by weighing on a certified static scale at a scale house operated by the State of Alaska Department of Commerce, Division of Weights and Measures.  An axle group is defined as any two axles whose midpoints are within 8 feet of each other.  For the test vehicles, the Class 9 single trailer vehicle has three axle groups, while the Class 6 and Class 5 each have two axle groups.

e.	The difference in value or error between the weight of each axle group or vehicle gross weight shall be computed as follows:

d = 100 [(W - R) / R]

where:

d =	difference between WIM value and reference value

W =	WIM value, or weight as measured by the WIM system

R =	Reference value, or weight as measured by a static scale

f.	The Accuracy requirements for the WIM equipment consist of a maximum error of plus or minus twelve percent with a 94 percent confidence interval for axle group weights, and a maximum error of plus or minus ten percent with a 94 percent confidence interval for gross vehicle weights.

For each test vehicle, no more than two of the axle group weights measured by the WIM system can differ from the axle group weights as measured at the scale house by more than twelve percent.  Similarly, for each test vehicle, no more than two of the gross vehicle weights measured by the WIM system can differ from the gross vehicle weights as measured at the scale house by more than 10 percent.

g.	Errors or differences between the weights as measured by the WIM and weights as measured at the scale house shall be calculated on ten consecutive passes of each of the three test vehicles at various speeds.  If more than the maximum number of errors is observed, the equipment shall be recalibrated and the Acceptance Test performed again until the system meets the accuracy specifications.

669-3.05 DELIVERABLES.

1.	Equipment List(s) and Drawings.  The Contractor shall submit for review and approval, within 30 days following award of the contract, 9 collated copies of a portfolio of equipment and materials that is proposed to be install.  The portfolio(s) shall consist of a table of contents including each item's intended use(s), and a description that includes product name, manufacturer, model or part number.

The Department will not be liable for materials purchased, labor performed, equipment used, or delay to the work before equipment and materials have been reviewed and approved.

2.	As-Built Plans and Photographs.  The Contractor shall prepare four complete sets of as-built plans that will be kept current with the construction.  These as-built plans shall detail construction changes made to the plans and also include the following information on the appropriate sheets:

a.	the location and depth of the inductive loops and conduit runs, and,

b.	the station and offset of the junction boxes.

Redlines of full size construction plans will be acceptable.

Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed in a waterproof, clear plastic holder to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation.

The Contractor shall present photographs and 35 mm negatives documenting the installation of the inductive loops.  The photos shall show the loops in place before covering with gravel and asphalt pavement.  The photographs shall include at least one view of each loop showing the conduit to the nearest junction box, and at least two overall views of each ATR installation showing placement of the inductive loops.  The photographs shall be 5 x 7 inch color prints, and shall be labeled with the identification of each loop as indicated on the plans (for example; H1 - W1NLA).

3.	Test Results.  Written or printed copies of the final results of the tests, signed by the Contractor, shall be provided to the Engineer before acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted according to subsection subsection 660-3.01, General.  Written (computer printout) results and copies of the electronic data files collected during performance of the WIM System acceptance test shall submitted to the Engineer before acceptance of completion of the WIM system.

669-4.01 METHOD OF MEASUREMENT.  The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder installations as shown on the Plans or as directed by the Engineer.

669-5.01 BASIS OF PAYMENT.  The contract unit bid price for the Automated Traffic Recorder installations will be full compensation for furnishing equipment, labor, and materials necessary to complete the work as specified, with the following exceptions:

1.	Backfill materials required will be paid for under respective pay items.

2.	Asphalt required will be paid for under Item 408(1) Hot Mix Asphalt, Type V.

Excavation, pedestrian gates, load centers, and as-built plans and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder Installations.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1) 	Automated Traffic Recorder 	Each

SECTION 670

TRAFFIC MARKINGS

Special Provision

670-1.01 DESCRIPTION.  Add the following:

Furnish, locate and install Pavement Markings as shown on the Plans and as directed.

Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS.  Replace the material reference,

Methyl Methacrylate Markings			Subsection 712-2.17”, with,

Methyl Methacrylate Pavement Markings		Subsection 712-2.17

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

Replace the last sentence with the following:

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete No. 4 and substitute the following:

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General.  15 days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment.

Use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking:  Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units are not permitted.

(b)	Other Markings:  Use manual or automatic application equipment.  Use stencils or extruders to form sharply defined markings.

f.	Application.  Apply marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate.  During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

SURFACE APPLIED

Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation.  Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings.  Groove the pavement to a depth of 250 mils.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of 250 mils.  Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 250 mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils.  Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste.  Waste material(s) are the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store waste material(s) on State property.  Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling.  On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

The Engineer may elect to use the Contractor’s readings or perform additional sampling.

Add the following:

Refer to the Survey Field Books identifying the no passing zones (see Subsection 642-3.01)

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:

Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Add the following Subsection:

670-3.06 TOLERANCE FOR LANE STRIPING.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width.  ± 4 inches from the width shown on the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within planned alignment.

7.	Double Stripes.  ± 1/4 inch.

8.	Thickness of Surface Applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum specified to a maximum of + 40 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, the beads are not properly placed, the anti-skid aggregate is not visible, or otherwise not to specification, make immediate adjustments to correct the problem.

Pavement markings applied by any method will be unacceptable if:

1.	Marking is not straight or wide enough.

2.	Thickness of line is not uniform.

3.	Thickness of line is less than specified.

4.	Material is uncured.

5.	Material blackens or is inconsistent in color.

6.	Inlay slot is not the specified depth.

7.	Inlay slot is not filled to the specified depth.

8.	Edge of the markings is not clear cut and free of overspray.

9.	Reflective elements are not properly embedded.

10.	Retroreflectivity of the markings is less than specified.

11.	Anti-skid aggregate is not visible in the marking material during application and the dried surface.

12.	Markings exhibit poor adhesion.

13.	Color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch work” manner.  If more than one repair is required in a single 500 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:

Thickness will be measure from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete No. 2.

Delete No. 3 and replace with the following:

3.	Each.  Pavement markings using letters, numbers, and arrows will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Add the following No. 4:

4.	Foot Basis.  Longitudinal pavement markings, transverse, and gore markings, surface applied or inlaid will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:

For all phases of construction:  There will be no separate payment for:

	Over-runs of material caused by the variation of the gradation of the asphalt

	Additional material required to achieve the thickness specified on open graded pavement

All work and materials associated with inlaid markings are subsidiary to 670 items, including but not limited to:

	Milling for installation of the inlaid pavement markings including the removal of millings

	Removal of conflicting markings, including repair of the roadway surface, milled surface or otherwise

	Traffic Control required for the installation of permanent and temporary pavement markings, removal of conflicting markings, and repairs

Traffic Paint is subsidiary to Pay Item 643(2) for the West Dowling Road Phase I project.

Inlaid marking for the stop bar on the Cordova Street Extension project is subsidiary to Pay Item 615(1).

Replace Item 670(10) with the following:

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10)	MMA Pavement Markings	Lump Sum

670(10A)	MMA Pavement Markings, Longitudinal Surface Applied	Linear Foot

670(10B)	MMA Pavement Markings, Symbols and Arrow(s) Surface Applied	Each

670(10C)	MMA Pavement Markings, Transverse and Gore Surface Applied	Linear Foot

670(10D)	MMA Pavement Markings, Longitudinal Inlaid	Linear Foot

670(10E)	MMA Pavement Markings, Symbols and Arrow(s) Inlaid	Each

670(10F)	MMA Pavement Markings, Transverse and Gore Inlaid	Linear Foot

Delete Items 670(11) and 670(12).

CR246-010109

SECTION 682

UTILITY POTHOLING

- Special Provisions

682-1.01 DESCRIPTION.  Determine and record the horizontal and vertical location of subsurface utilities using a vacuum extract truck.

682-2.01 MATERIALS.

Backfill Material: Use aggregate conforming to Aggregate Base Course,      Grading D-1

Asphalt Patch Material:	Use Asphalt Concrete Type II, Class B

682-3.01 CONSTRUCTION.  Submit the utility potholing schedule to the Engineer and utility companies at least 5 days before starting potholing.  Remove materials using a vacuum-extract truck to expose and identify the utilities.  Survey the location and elevation of the utilities using the project horizontal and vertical control.  Log as-built information at each pothole location.

Backfill immediately after the Engineer accepts the logged data.  Backfill and compact the first six vertical inches using the excavated material or other approved materials.  Backfill and compact the remaining pothole void using Aggregate Base Course, Grading D-1.  If the pothole is located in a paved area, provide a pavement patch using Asphalt Concrete material of the thickness equal to the adjacent asphalt concrete.

Immediately contact the Engineer and the affected utility if utility facilities are damaged during the potholing operations.  Costs associated with repairing damaged utilities will be borne by the Contractor.

682-3.02 AS-BUILTS.  Maintain a complete log of pothole information, including station, offset, elevation, utility types/size encountered, date of potholing operation, groundwater elevation, and other pertinent data.  Submit the completed log to the Engineer within two working days following the start of the pothole excavation.

682-4.01 METHOD OF MEASUREMENT.  Measure Vac-Extract Pothole by the total number of locations verified and accepted. Other related work, including but not limited to, removal of pavement, backfilling, pavement patching, shoring, labor, and surveying will not be paid separately, but shall be subsidiary to the Item.  Potholing for the Contractor’s information and not directed by the Engineer will be the Contractors responsibility and will not be paid.

682-5.01 BASIS OF PAYMENT.  Payment for Item 682(1) Vac-Truck Pothole will be paid on a contingent sum basis at the rate of $450/each for the locations directed by the Engineer.  The price for Vac-Truck Potholing includes full compensation for furnishing equipment, labor and materials necessary to complete the work as specified.  Payment will be based on the verified and accepted log.  Payment will not be made for potholing not listed in the verified log, or for exposing utilities during the course of other excavation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

682(1)	Vac-Truck Pothole	Contingent Sum

Special Provision

Add the following Section:

SECTION 690

EROSION, SEDIMENT AND POLLUTION CONTROL - MEASURES

690-1.01 DESCRIPTION.  Furnish, install and maintain measures, countermeasures and associated materials as part of BMP(s) to prevent, control and contain erosion, erosion materials, sediments and pollution contaminates, on and off project site.

Measures:

	Permanent Measures – include, the materials, hardware, equipment and labor required for installation and maintenance of erosion, sediment and pollution control material(s).

	Temporary Measures - include, in addition to the requirements of Permanent Measures, removal and disposal of the erosion, sediment and pollution control material(s).

Related Specifications:

Erosion, Sediment and Pollution Control	Section 641

Silt Fence	Section 633

Seeding	Section 618

Soil Stabilization	Section 619

690-2.01 MATERIALS.

Erosion Sediment and Pollution Control – Materials	Section 744

Others as specified in related Sections.

CONSTRUCTION REQUIREMENTS

690-3.01 GENERAL.  BMP(s) may include individual or a combination of measures and countermeasures, including but not limited to temporary seeding, mulch, matting, staples, stabilizing emulsions, blankets and mats, soil blinders, non-erodible cover, dustless sweeping, dust palliatives.   Refer to Subsection 690-1.01, Related Specifications, for measures not included here.

690-3.02 MATERIAL STORAGE AND PROTECTION.  General:  Store materials elevated off the ground and covered protecting them from construction and or damage from the environment and as follows:

Fiber Rolls.  Additionally, protect fiber rolls from:  precipitation, extended ultraviolet radiant including sunlight, chemicals that are strong acids or other, flames including welding sparks, excess temperatures, and any other environmental conditions that may damage the physical property value of the rolls.

690-3.03 FABRICATION.

Sandbags:  Sand bags shall measure 15 inches by 30 inches.  Use prayer type seams with a minimum of two rows of stitching using a Federal Stitch Type 401 Chain Stitch.  Place approximately 1.0 cubic foot of Select Material, Type B, in each sandbag sack.  Close the open end of the sandbag, after filling, with 2 cinch ties or as recommended by the manufacturer of the sandbag material.

Compost Socks:

a.	Product Data:  Before compost application, furnish a copy of the compost producer's compost technical data sheet and a copy of the compost producers Seal of Testing Assurance certification.  The compost technical data sheet includes:

1.	Laboratory analytical test results.

2.	List of product ingredients.

b.	Certificate of Compliance:  Before compost application, furnish a Certificate of Compliance for the compost under Section 106-1.05, "Certificates of Compliance," of the Standard Specifications.

c.	Quality Control and Assurance:  The compost producer must have the following qualification:

A participant in United States Composting Council’s (USCC) Seal of Testing Assurance (STA) program.

690-3.04 PLACEMENT AND INSTALLATION.  Place and install where shown and detailed in the Plans and Specifications including Section 641, and as recommended by the manufacturer, directed by the Engineer and as follows:

Temporary Seeding.  Annual Ryegrass per Subsection 724-2.02, Table 724-1.  Apply at a rate of 1/2 lb/1000 sq. ft., minimum, on level ground to a maximum of 1 1/2 lb/1000 sq. ft., maximum, on sloping ground and highly erodible soils.  Confirm application of temporary seeding with the Engineer.

Prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetation cover.  Maintain seeded areas.  Refer to Section 620 for further surface/topsoil preparation requirements.

Reseed where water quality standards are being exceeded as a result of insufficient vegetative cover.  Review with Engineer prior to reseeding.

Refer to Section 618 for further information.

690-3.05 MAINTENANCE.  Maintain the integrity of the erosion, sediment and pollution control measures for the duration of the project.  Inspect as required by the NPDES CGP and SWPPP and correct any deficiencies immediately.  Remove and dispose of temporary measures including trapped sediment contaminants off project at approved locations. Materials manufactured as biodegradable may be left in place when approved by the Engineer.

690-4.01 METHOD OF MEASUREMENT.  Section 109 and as follows:

Fiber Rolls: By length, measured along the centerline of the fiber roll, complete in place.

Manufactured Inlet Protection Systems:  By each, complete in place.

Sandbag Inlet Sediment Trap:  By each, complete in place.

Silt Fence:  Section 633.

Seeding:  Section 618.

Stabilization:  Section 619.

690–5.01 BASIS OF PAYMENT.  Section 641.

Except:

Item 690(1) Fiber Rolls, includes materials, hardware, equipment and labor required for installation and maintenance.

Payment will be made under:

| Pay Item No. | Pay Item | Pay Unit |
| --- | --- | --- |
| 690(1) | Fiber Roll | Linear Foot |
| 690(2) | Manufactured Inlet Protection Systems | Each |
| 690(3) | Sandbag Inlet Sediment Trap | Each |

R690(08/12/10)

Replace Section 701 with the following:

SECTION 701

HYDRAULIC CEMENT AND POZZOLAN

701-1.01 GENERAL.  Meet the following general requirements for all cementitious materials furnished:

Provide product from only one mill for each brand and type of cementitious material except to reduce excessive air entrainment when using air-entraining cement.

Cement may be shipped from pretested approved bins.

Before using, retest Portland cement that has been stored longer than 3 months if bagged or 6 months if bulk for compressive strength, time of setting, and loss on ignition according to AASHTO M 85. Store separately different types or brands of cementitious materials, or cementitious materials from different mills.

Protect cementitious materials from dampness during shipment and storage. Do not use partially set cement or cement which contains caked lumps. Do not use cement salvaged from discarded or used bags.

701-2.01 PORTLAND CEMENT. Meet AASHTO M 85, Type I, II, or III, including the low-alkali cement requirement shown in Table 2. Furnish a certificate of compliance meeting AASHTO M 85, Section 15 as required by Subsection 106-1.05.

701-2.02 BLENDED HYDRAULIC CEMENT. Meet AASHTO M 240, Type IP. Furnish a certificate of compliance meeting AASHTO M 240, Section 14 as required by Subsection 106-1.05.

701-2.03 FLY ASH. Class C or Class F meeting AASHTO M 295, including optional chemical requirements as set forth in Table 2 and with the following revisions:

Table 1 Chemical Requirements

Moisture content, max percent	1.0

Table 3 Physical Requirements

Amount retained when wet-sieved on

45-μm (No. 325) sieve, max percent	30

701-2.04 SILICA FUME. Meet AASHTO M 307. Furnish a certificate of compliance meeting AASHTO M 307, Section 23 as required by Subsection 106-1.05.

701-2.05 GROUT. Non-shrink, non-corrosive, non-metallic, cement-based grout meeting ASTM C 1107, except develop a 28-day compressive strength of at least 9,000 psi from specimens made in accordance with ATM 507.

701-2.06 DS GROUT. Use drilled shaft (DS) grout  that conforms to the following requirements:

1.	Portland Cement Type I or Type II cement meeting the requirements of Subsection 701-2.01.

2.	Fine Aggregate: Use fine aggregate meeting Subsection 703-2.01, except 100 percent passing the No. 4 sieve.

3.	Potable Water: Use water meeting the requirements of Subsection 712-2.01.

4.	Proportioning: Mix grout in proportions using at least 564 lbs/yd3 of Portland cement, fine aggregate, and with enough water to produce a flowable mixture.  Do not exceed 67 gal/yd3 of water.

Thoroughly mixed DS grout before injecting into soil surrounding drilled shaft casing and CSL tubes.

701-2.07 POST-TENSION GROUT. Use pre-packaged thixotropic grout formulated specifically for bonded post-tensioned concrete structures in aggressive exposures.

Ship grout in weather proof packages, plainly marked with the name, weight, and volume of the grout, together with the lot number, date of manufacture, mixing instructions, and the name and address of the manufacturer.

Protect grout against dampness. Do not use grout that has become partially set or which contains lumps of caked grout. Do not use grout salvaged from discarded or used bags. Do not use grout with a total time from manufacture to usage in excess of six months unless the manufacturer tests and certifies the product meets the requirements in Table 701-1.

Batch grout using the entire contents of each bag in accordance with all of the manufacturer’s written recommendations and instructions.

1.	Materials. Use grout that conforms to the following requirements:

a.	Portland Cement. Type I or Type II cement meeting the requirements of Subsection 701-2.01.

b.	Potable Water. Use water meeting the requirements of Subsection 712-2.01.

c.	Fly Ash. Class C or Class F fly ash meeting the requirements of Subsection 711-2.03. Limit fly ash content to a maximum of 20% by weight of Portland cement.

d.	Ground Granulated Blast Furnace Slag. Grade 120 slag conforming to ASTM C 989. Limit blast furnace slag content to a maximum of 40% of the weight of Portland cement.

e.	Silica Fume. Silica fume conforming to ASTM C 1240. Limit silica fume content to a maximum of 15% of the weight of Portland cement.

f.	Set Control and Water-Reducing Admixtures. Type D, Type F, and Type G admixtures conforming to AASHTO M 194. Limit Type F and Type G admixtures to 45 oz. per 100 pounds of Portland cement. Consider adding these to Section 711.

g.	Air Entraining Admixtures. Do not use grout with air entraining admixtures.

h.	Expansion Causing Admixtures. Do not use grout with expansive cement or expansion causing admixtures that contain aluminum powder or components that produce hydrogen, carbon dioxide or oxygen gas.

i.	Corrosion Inhibitor Admixtures. Do not use grout with corrosion inhibitor admixtures.

j.	Pumping Aid Admixtures. Do not use pumping aid admixtures.

2.	Physical Properties. Use grout that satisfies the requirements in Table 701-1.

3.	Material Certification. Submit 5 copies of a quality control data sheet covering the chemical and physical tests conducted on the grout for the material in each shipment. Submit 5 copies of a certified test report from an independent laboratory, audited by the Cement Concrete Research Laboratory that shows the material meets all property requirements.

TABLE 701-1

POST TENSION GROUT

| Property | Requirements | Test Method |
| --- | --- | --- |
| Total Chloride Ions | Max. 0.08% by weight of cementitious materials | ASTM C 1152 |
| Setting Time | Min. 3 hours Max. 12 hours | ASTM C 953 |
| Strength | Min 3000 psi after 7 days Min 5000 psi after 28 days | ASTM C 942 |
| Permeability @ 28 days | Max. 2500 Coulombs at 30 V after 6 hours | ASTM C 1202 |
| Volume Change | Maximum 0.0% after 24 hours Maximum +0.2% after 28 days | ASTM C 1090 (modified)* |
| Expansion | ≤ 2.0 % for up to 3 hours | ASTM C 940 |
| Fluidity | - Immediately after mixing: Min. 9 sec. Max. 20 sec. - 30 minutes after mixing: Max. 30 sec. | ASTM C 939 (modified)** |
| Wick Induced Bleed | Max 0.0% | ASTM C 940 (modified)*** |
| Wet Density | Report maximum and minimum obtained test value in pounds per cubic foot | ASTM C 185 |

*	Modify ASTM C1090 to include verification at both 24 hours and 28 days.

**	Modify the ASTM C 939 test by filling the flow cone to the top instead of to the standard level. The efflux time is the time to fill a one liter container placed directly under the flow cone.

***	Modify ASTM C940 to conform with the wick induced bleed test as follows:

(a)	Use a wick made of a 20-inch length of ASTM A416 seven-wire 1/2 inch diameter strand. Wrap the strand with 2-inch wide duct or electrical tape at each end prior to cutting to avoid splaying of the wires when it is cut. Degrease (with acetone or hexane solvent) and wire brush to remove any surface rust on the strand before temperature conditioning.

(b)	Condition the dry ingredients, mixing water, prestressing strand and test apparatus overnight at 65° F to 75° F.

(c)	Mix the conditioned dry ingredients with the conditioned mixing water and place 800 ml of the resulting grout into the 1,000 ml graduate cylinder. Measure and record the level of the top of the grout.

(d)	Completely insert the strand into the graduated cylinder. Center and fasten the strand so it remains essentially parallel to the vertical axis of the cylinder. Measure and record the level of the top of the grout.

(e)	Store the mixed grout at the temperature range listed above in (b).

(f)	Measure the level of the bleed water every 15 minutes for the first hour and hourly for two successive readings thereafter.

(g)	Calculate the bleed water, if any, at the end of the three hour test period and the resulting expansion per the procedures outlined in ASTM C940, with the quantity of bleed water expressed as a percent of the initial grout volume. Note if the bleed water remains above or below the top of the original grout height. Note if any bleed water is absorbed into the specimen during the test.

SECTION 702

ASPHALT MATERIALS

Special Provision

702-2.01 ASPHALT CEMENTS.  Meet AASHTO M 320 and the following:

ADDITIONAL REQUIREMENTS FOR

PERFORMANCE GRADED ASPHALTS

Replace the column heading, PG 64-28, with, PG 58-34.

SECTION 703

AGGREGATES

Special Provision

703-2.03 AGGREGATE FOR BASE.

Delete Table 703-2 and substitute the following:

TABLE 703-2
AGGREGATE FOR UNTREATED BASE

(Percent Passing By Weight)

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 | - | - |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

Replace Subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT.  Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter.  Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Type IV, V and R mixtures.

Coarse Aggregate.  Aggregate retained on the No. 4 Sieve.

Meet the following requirements:

| Description | Specification | Type IIA | Type I, IIB, III | Type IV | Type V, R |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, Min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP 61 | 90, 2 face | 80, 1 face | 90, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % | ATM 306 |  |  |  |  |
| 1:5 |  | 8 | 8 | 8 | 8 |
| 1:3 |  | 20 | - | - | 20 |
| Absorption, max. % | AASHTO T 85 | 2.0 | 2.0 | 2.0 | 2.0 |

Fine Aggregate.  Aggregate passing the No. 4 sieve.

Aggregate shall meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Aggregate for Type IV, V, and R mixes:

	do not blend back natural sand

	shall be non-plastic as determined by WAQTC FOP for AASHTO T 90

	shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%

TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT PAVEMENT AGGREGATE

(Percent Passing by Weight)

| Sieve | Gradation |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V | Type R |
| 1 inch | 100 | - | - | - | - | - |
| 3/4 inch | 80-90 | 100 | - | - | 100 | 100 |
| 1/2 inch | 60-84 | 75-90 | 100 | 100 | 65-90 | 70-100 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | ≤ 45 | 20-32 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | ≤ 35 | 15-25 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | ≤ 25 | 10-20 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | ≤ 20 | 7-15 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | ≤ 12 | 5-12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 4-8 | 3-8 | 4-10 |

Note:

1.	No tolerance is allowed beyond the Broad Band Limits of the No. 200 Sieve.

2.	For Type R, the mix design gradation JMD shall provide a minimum of 8 % difference of percent passing the No. 4 and the No. 8 sieve.

R7031(10/11/10)

Add the following Subsections:

703-2.13 FOUNDATION FILL. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

TABLE 703-9

REQUIREMENTS FOR GRADING FOR FOUNDATION FILL MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3 in. | 100 |
| 3/4 in. | 75-100 |
| No. 4 | 35-65 |
| No. 40 | 0-50 |
| No. 200 | 0-6 |

703-2.14 AGGREGATE FOR ABRASIVE FINISH. Crushed sand consisting of sound, tough, durable rock of uniform quality, oven dried, and stored in moisture-proof bags. Free from clay balls, vegetative matter, or other deleterious matters (AASHTO T 112). Not coated with dirt or other finely divided mineral matter. Meet the grading requirements of Table 703-10 (WAQTC FOP for AASHTO T 27/T 11).

TABLE 703-10

REQUIREMENTS FOR SAND FOR ABRASIVE FINISH

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| No. 8 | 100 |
| No. 20 | 0-5 |

Replace Section 705 with the following:

SECTION 705

JOINT MATERIALS

705-2.01 JOINT FILLERS. Meet AASHTO M 213.

705-2.02 JOINT SEALER.

Silicone Joint Sealer	ASTM D 5893

Hot Pour Joint Sealer (Asphalt)	AASHTO M 324, Type IV

Hot Applied Joint Sealer (Concrete)	AASHTO M 282

Hot Pour Joint Sealant (Concrete, Fuel-Resistant)	ASTM	D 3581

705-2.03 BRIDGE SEAL.

1.	Preformed Strip Seals and Compression Seals. Use preformed seals. Use preformed material meeting ASTM D 3542.

Submit five copies of a certified test report for preformed seal materials.

2.	Silicone Expansion Joint Sealant. Use formed-in-place seals composed of 100 percent silicone meeting the requirements of ASTM D 5893, Type SL (Self-Leveling) for horizontal joints and ASTM D 5893, Type NS (Non-Sag) for curb, rail, and other vertical joints. Do not use acid cure sealants.  Ensure the silicone sealant is compatible with the surface to which it is applied. Use a backer rod meeting ASTM C 578 when the joint width is 1/2 inch or greater.

705-2.04 JOINT MORTAR. Use a mixture of one part portland cement and two parts approved sand with water as necessary to obtain the required consistency. Use mortar within 30 minutes after its preparation.

705-2.05 FLEXIBLE WATERTIGHT GASKETS.

1.	Ring gaskets for rigid pipe and precast manhole sections meeting AASHTO M 198.

2.	Ring gaskets for flexible metal pipe meeting ASTM C 443. Continuous flat gaskets for flexible metal pipe meeting ASTM D 1056, Grade 2B3. Use gaskets with a thickness 1/2 inch greater than the nominal depth of the corrugation for bands with projections or flat bands and 3/8 inch for corrugated bands.

705-2.06 EXPANDED POLYETHYLENE. Use closed-cell expanded polyethylene planks with a density of 2.2 +/- 0.5 lb/ft3 as determined by ASTM D3575 and with a maximum compressive deflection of 50% at 17 psi +/- 5 as determined by ASTM D3575.

SECTION 706

CONCRETE AND PLASTIC PIPE

Special Provisions

706-2.05 PVC PIPE FOR WATER AND SANITARY SEWER SYSTEMS.

Delete the second sentence of the first paragraph and add the following:

Ensure the entire pipe system is made of materials with a 200 psi rated working pressure

706-2.08 HDPE PIPE FOR WATER AND SANITARY SEWER SYSTEMS.

Delete the first paragraph and add the following:

Use high density polyethylene (HDPE) pipe and fittings manufactured from a PE 4710 resin that meets ASTM D3350 with a cell classification of 445574.  Ensure the entire pipe system is made of materials with a 200 psi rated working pressure.  Join all pipe and fittings by either butt fusion of flanges as per manufacturer’s recommendation.  No mechanical joints are allowed.  Pipe shall be ductile iron pipe size.  Meet the following:

HDPE Pipe		AWWA C906, NSF 61

Replace Section 709 with the following:

SECTION 709

REINFORCING STEEL AND WIRE ROPE

709-2.01 REINFORCING STEEL.

1.	Reinforcing Steel Bars. Furnish deformed reinforcing steel bars of the type, grade, and size as specified. For steel reinforcing bars used in bridge structures, use bars meeting ASTM A 706, Grade 60. For all other structures, use bars meeting AASHTO M 31, Grade 60.

2.	Headed Reinforcing Steel Bars. Furnish headed reinforcing steel bars meeting the requirements of ASTM A 970, Class HA. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

3.	Epoxy-Coated Reinforcing Steel Bars. Furnish epoxy-coated steel bars meeting the requirements of AASHTO M 284. Coat epoxy-coated reinforcing steel in an epoxy coating applicator plant certified in accordance with the Concrete Reinforcing Steel Institute (CRSI) Voluntary Certification Program. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

4.	Steel Wire. Furnish plain steel wire of the size specified that meets the requirements of AASHTO M 32.

5.	Steel Bar Mats. Furnish deformed steel bar mats of the type, grade, size, and spacing as specified. Unless otherwise noted, furnish steel bar mats meeting the requirements of AASHTO M 54, Grade 60.

6.	Steel Welded Wire Fabric. Furnish plain steel welded wire fabric of the size and spacing specified that meets the requirements of AASHTO M 55.

7.	Epoxy-Coating Patch Material. Furnish epoxy-coating patch material meeting the requirements of AASHTO M 317.

8.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 709-2.01.8.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

709-2.02 WIRE ROPE OR WIRE CABLE. Meeting AASHTO M 30, 3/4 inch Type 1, Class A.

709-2.03 BAR SUPPORTS.

1.	Precast Mortar Blocks. Provide mortar blocks meeting the following:

a.	Ensure the mortar blocks have compressive strength at least equal to the strength of the concrete in which the mortar blocks are embedded. Sample and test the mortar for compressive strength according to AASHTO T 106. Each test will be considered to represent no more than 2,500 mortar blocks made of the same mortar and cured under the same conditions.

b.	Ensure the bearing area of the mortar block is less than 2 inches in each dimension.

c.	Secure to the reinforcing steel with either a grooved top that will hold the bar in place or a protruding embedded wire that is tied to the reinforcing steel.

2.	Metal Supports. Provide metal supports meeting at least one of the following:

a.	Galvanized after fabrication according to AASHTO M 232 Class D,

b.	Stainless steel meeting the requirements of ASTM A 493, Type 302, or

c.	Plastic coated using coatings that do not react chemically with the concrete, have a minimum thickness of 3/32 inch where the support touches the form, do not crack at or above -5°F, and do not deform enough to expose the metal at or below 200°F.

3.	Plastic Supports. Provide plastic supports meeting the following:

a.	Non-porous.

b.	Chemically inert in concrete.

c.	Have rounded seats.

d.	Do not deform under load during normal temperatures.

e.	Do not shatter or crack under impact loading in cold weather.

f.	Have at least 25 percent of their gross area perforated.

Do not use plastic supports that prevent complete concrete consolidation in and around the support or require supports less than 1 foot apart along the length of the bar.

SECTION 710

FENCE AND GUARDRAIL

Special Provisions

710-2.03 CHAIN LINK FABRIC.

In the 1st sentence between the parenthesis, replace "Class D" with the following:

(Class C or D coating)

CR7101-110410

Standard Modification

Delete Subsection 710-2.04 METAL BEAM RAIL and replace with the following:

710-2.04 METAL BEAM RAIL.  Meet AASHTO M 180-00, Class A, Type II.  Galvanize the rail per ASTM A653 after factory roll formed and punched.

E83-100410

Delete Subsection 710-2.06 GUARDRAIL POSTS AND BLOCKS and replace with the following:

710-2.06 GUARDRAIL POSTS AND BLOCKS.  Furnish posts and blocks, as specified, meeting the following requirements.

1.	Wood Posts and Blocks.  Use timber with a stress grade of 1200 psi or more.  Testing must meet the standards of the West Coast Lumber Inspection Bureau.  Use timber for posts and blocks that is either rough sawn (unplaned) or S4S with nominal dimensions indicated.  Allowable size tolerance of rough sawn blocks in the direction of the bolt holes is  1/4 inch.  Only one combination of post and block finish may be used for any one continuous length of guardrail.  Treat all timber to meet Section 714.

2.	Steel Posts and Blocks.  Meet the section and length specified or shown on the Plans.  Use copper bearing steel when so specified.  Use steel meeting the requirements of ASTM A 36 and galvanized per ASTM A 123.

3.	Synthetic Blocks.  Product made from alternate materials may be used if accepted by the FHWA for use on the National Highway System.

E84-100410

Delete Subsection 710-2.11 GUARDRAIL TERMINALS and replace with the following:

710-2.11 GUARDRAIL TERMINALS.  Meet coating requirements of AASHTO M 180, Class A, Type II.  Galvanize after fabrication.  Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding, and riveting.  Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail.  Provide terminals that pass NCHRP 350 or MASH Test Level 3 and meet the following requirements:

1.	Controlled Release Terminal.	Meet the requirements of Standard Drawing G-25.

2.	Parallel Terminal.

a.	Requirements:

(1)	Crashworthiness:  Provide terminals that pass NCHRP 350 or Mash Test Level 3.

(2)	Length:  50 feet.

(3)	End Offset:  0 to 2 feet (25:1 or flatter straight taper) offset end as shown on the plans.

(4)	Posts:  Use posts that are:

(a)	Steel post with hinge or

(b)	Yielding or breakaway steel post in steel tube

b.	Acceptable models include the following or approved equivalent:

(1)	Sequential Kinking Terminal (SKT) manufactured by Road Systems, Inc., 3616 Old Howard County Airport, Big Spring, Texas 79720, Telephone (432) 263-2435.

(2)	Extruder Terminal (ET-Plus) manufactured by Trinity Highway Products, L.L.C., 950 West 400 South, Centerville, Utah 84014, Telephone (801) 292-4461.

c.	Install AASHTO M 268, Type III, IV, or V retro-reflective sheeting (2.0 square feet, minimum) on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal.

3.	Buried in Backslope Terminal.  Meet the requirements of Standard Drawing G-15.

E85-100410

Replace Section 711 with the following:

SECTION 711

CONCRETE CURING MATERIALS

AND ADMIXTURES

711-2.01 CURING MATERIALS.

Burlap Cloth made from Jute or Kenaf	AASHTO M 182, Class 4

Sheet Materials for Curing Concrete	AASHTO M 171

Liquid Membrane-Forming

Compounds for Curing Concrete	AASHTO M 148, Type I-D Class B, except do not use compounds containing linseed oil.

711-2.02 CHEMICAL ADMIXTURES.

Air-Entraining Admixtures	AASHTO M 154

Water-Reducing Admixtures	AASHTO M 194, Type A

Set-Retarding Admixtures	AASHTO M 194, Type B

Set-Accelerating Admixtures	AASHTO M 194, Type C

Water-Reducing and Set-Retarding Admixtures	AASHTO M 194, Type D

Water-Reducing and Set-Accelerating Admixtures	AASHTO M 194, Type E

Water-Reducing Admixtures	AASHTO M 194, Type F

High Range Water-Reducing and Set-Retarding Admixtures	AASHTO M 194, Type G

Specific Performance Admixtures	ASTM C 494, Type S

SECTION 712

MISCELLANEOUS

Standard Modifications

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS.  In Gray iron castings, delete text and replace with:

AASHTO M 306 and AASHTO M 105, Class 35B.

E46(01/27/07)

Special Provision

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace No. 1. Quality Requirements: with the following:

1.	Quality Requirements:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded or stenciled application:  Material formulated for extruded or direct stenciled application with factory intermix beads, and anti skid aggregate and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:  Add the following:

I.	Color:	Yellow, PR-1 Chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Replace the bead table with the following:

Use the type and quantity of beads specified in writing by the marking material manufacturer required to satisfy the specified performance requirements.  The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads.  Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials.  Marking Material Manufacturer will certify compatibility.

(2)	Lasting retroreflectivity.

CR246(01/01/09)

Add the following:

712-2.19 LOW-VISCOSITY RESIN. Meet AASHTO M 235, Type IV, Grade 1, with the following revisions:

Amend Table 1 as follows:

Replace "2.0[20]" with "0.105[1.05]" in the row labeled "Grade 1, max".

712-2.20 CONCRETE ANCHORS.

1.	Anchor Bolts. Use galvanized anchor bolts meeting ASTM A 307.  Hot-dip galvanize anchor bolts in conformance with AASHTO M 232.

2.	Coil Anchor Inserts. Use 1 inch diameter galvanized inserts with a minimum safe working load of 7,500 pounds.  Hot-dip galvanize anchors according to AASHTO M 111 or AASHTO M 232.

3.	Threaded Anchor Inserts. Use 1 inch diameter galvanized ferrule inserts with a minimum safe working load of 6,500 pounds.  Hot-dip galvanize anchors according to AASHTO M 111 or AASHTO M 232.

712-2.21 EPOXY FOR BONDING DOWELS. Use an epoxy cartridge system appropriate for the service temperature and ambient concrete temperature at the time of installation.

Use epoxy cartridge systems that meet the requirements of the “Acceptance Criteria for Adhesive Anchors in Concrete and Masonry Elements,” AC58, by the International Code Council Evaluation Service (ICC-ES) including the suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic tests.

1.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 712-2.21.1.f;

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Replace Section 715 with the following:

SECTION 715

STEEL FOR PILES

715-2.01 SCOPE. Steel used for Structural Steel Piling and Sheet Piling.

715-2.02 GENERAL REQUIREMENTS. Furnish steel piles of the dimensions, weights, cross-sections, and grades specified. Satisfy the impact test requirements of Subsection 716-2.02. Meet the following:

1.	Structural Steel HP Piling. Furnish "HP" shape piles meeting ASTM A 709, Grade 50T3.

2.	Structural Steel Pipe Piling. Furnish pipe piles meeting one of the following:

a.	American Petroleum Institute (API) 5L X52 PSL2.

b.	ASTM A 709, Grade 50T3 fabricated and monogrammed according to API 2B

3.	Pile Tip Reinforcing. Use pile tip reinforcement conforming to the requirements of ASTM A 27 Grade 65-35 or ASTM A 148 Grade 90-60. Make each pile tip in one piece of cast steel. Weld tip reinforcing to the piles in conformance with the manufacturer's written directions.

4.	Structural Steel Sheet Piling. Furnish sheet piles meeting AASHTO M 202.

715-2.03 CERTIFICATION. Furnish 5 copies of a certified test report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 715-2.03.6; and,

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

For pipe manufactured to API 5L, submit a certified test report according to API 5L SR15.1.

715-2.04 MARKING. Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying certified test report.

Replace Section 716 with the following:

SECTION 716

STRUCTURAL STEEL

716-2.01 SCOPE. Structural steel for highway bridges and other structural purposes.

716-2.02 GENERAL REQUIREMENTS. Meet the following:

1.	General requirements for delivery of rolled steel plates,

shapes, sheet piling, and bars for structural use	ASTM A 6

2.	Structural Steel	ASTM A 709

3.	Filler Metal for Applicable Arc-Welding Electrodes	AWS Specifications

4.	Stud Shear Connectors	ASTM A 108

Gr. 1015, or 1020

5.	Raised Pattern Plate. Where raised pattern plate is shown on the Plans, use plates with a raised pattern surface meeting the following requirements:

a.	Use diagonal type pattern, with the intersecting diagonals at right angles to one another. Use the same material for the raised portions of the pattern as the base metal of the plate. The raised pattern must be an inherent part of the plate. The pattern must be continuous throughout the surface of the plate and the projections along any diagonal must be spaced alternately with the projections along the normal diagonals.

b.	Use plate with projections that are self-draining and self-cleaning and provide a skid-resistant surface from all angles of approach. The projections must have flat tops and be designed not to chip, crack, split, or buckle at their intersection with the base metal.

6.	Impact Test Requirements. Use Structural Steel and Filler Metal for Applicable Arc-Welding Electrodes meeting the following requirements:

a.	For Structural Steel, meet the impact testing requirements and marking requirements of ASTM A 709 for the specified grade, type of component, and impact testing temperature zone.  If the grade is not specified, use Grade 36 steel.  If the type of component is not specified, use steel grades marked with suffix T.  If the impact testing temperature zone is not specified, use steel marked for Zone 3.

b.	For Filler Metal for Applicable Arc-Welding Electrodes, meet the minimum average energy values of the base metals to be joined when tested at or below the temperature corresponding to the specified impact testing temperature zone of the base metal.  Perform impact tests according to ASTM A 370.

716-2.03 FASTENERS. Meet the following:

1.	High Strength Bolts	AASHTO M 164

2.	Nuts	AASHTO M 291

3.	Hardened Steel Washers	AASHTO M 293

4.	Zinc Coated Load Indicating Washers	ASTM F 959 Type 325

716-2.04 Steel Grid Floors. Meet ASTM A 709, Grade 36. If the material is not galvanized, ensure the steel has a copper content of 0.2% minimum.

Unless painting of floors is specified in the Special Provisions, open type floors must be galvanized.

716-2.05 Machine Bolts. Meet ASTM A 307.

716-2.06 STEEL PIPE. Meet ASTM A 53 Grade B.

716-2.07 GALVANIZING. Hot-dip galvanize structural steel shapes, plates, bars and their products according to AASHTO M 111. Galvanize tubes and piles on inside and outside surfaces.

Hot-dip galvanize steel poles, mast arms, pedestals, and posts, according to AASHTO M 111. Submerge each component in the galvanizing kettle in one dip. Use only the dry kettle method of fluxing for high tower poles.

Hot-dip galvanize bolts, nuts, washers, tie-rods, clamps, and other miscellaneous ferrous parts in conformance with AASHTO M 232. After galvanizing, ensure that the bolt threads accept galvanized standard nuts without requiring tools or causing removal of protective coatings.

Galvanize rigid metal conduit in conformance with AASHTO M 232.

For Steel Bridge members, apply 10 mils zinc galvanizing by spray-metalizing process according to Steel Structures Painting Council's  coating system guide SSPC-CS 23.00. Prepare surfaces before galvanizing according to Steel Structures Painting Council's surface preparation guide SSPC-SP 5, White Metal Blast Cleaning.

Repair damaged coatings according to ASTM A 780 annex A1 or annex A3, except as described herein. Clean the damaged area according to SSPC-SP 2, Near-White Blast Cleaning for repairs meeting annex A1 and SSPC-SP 5, White Metal Blast Cleaning for repairs meeting annex A3. Extend the cleaned area 1/2 inch to 3/4 inch into the undamaged section of the coating. Keep the cleaned area dry and free of rust and soiling.  Within 24 hours of cleaning, coat the cleaned section with zinc to a thickness of not less than 10 mils. Taper the thickness of the repair coating to match the original coating thickness at the edges of the cleaned section. Where zinc coating is to be metallized, use zinc wire containing not less than 99.98 percent zinc.

716-2.08 CERTIFICATION. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 716-2.08.6; and,

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

SECTION 719

STEEL, GRAY-IRON ANDMALLEABLE IRON CASTINGS

Standard Modification

719-2.02 GENERAL REQUIREMENTS.  In Gray-Iron Castings, delete text and replace with:

AASHTO M 306 and AASHTO M 105, Class 35B.

E47(01/27/07)

Replace Section 720 with the following:

SECTION 720

BEARINGS

720-2.01 ELASTOMERIC BEARING PADS. Elastomeric bearing pads include plain pads, consisting of elastomer only, and laminated pads with steel laminates.

1.	General. Meet AASHTO M 251, with the following revisions:

4.1 Properties of the Elastomer. Replace the first sentence with the following: Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer. Do not use neoprene. Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) do not apply.

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraph 8.9.

Add the following paragraph:

5.5. Fabricate pads over 3/4 inch thick with alternating laminations of elastomer and metal or fabric reinforcements. The outside laminations must be metal or fabric with a minimum elastomer cover as shown on the Plans.

2.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 720-2.01.2.f; and

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

720-2.02 EPOXY ADHESIVE FOR ELASTOMERIC BEARING PADS. Meet AASHTO M 235, Type IV, Grade 3.

720-2.03 POLYTETRAFLUOROETHYLENE (PTFE) BEARINGS. PTFE bearing assemblies consist of elastomeric bearing pads, polytetrafluoroethylene (PTFE) surfacing, and stainless steel and steel plates.

1.	Materials.

Elastomeric Bearing Pads	Subsection 720-2.01

Stainless Steel Plates	ASTM A 240, Type 304

Steel Plates	ASTM A 709, Grade 36

Use PTFE from virgin material (not reprocessed) meeting the requirements of ASTM D 4894 or D 4895, and Table 720-1.

2.	Fabrication. Fabricate the PTFE sliding surface with lubricant dimples having a maximum diameter of 0.32 inch, a minimum depth of 0.08 inch and a maximum depth of one half of the PTFE sheet thickness. Distribute the dimples uniformly within the area ¼ inch from the edges of the PTFE sheet and occupying between 20 percent and 30 percent of the PTFE sheet area.

For welding of structural steel, conform to the requirements of Section 504.

TABLE 720-1

POLYTETRAFLUOROETHYLENE (PTFE)

| Test | Requirements |
| --- | --- |
| Specific Gravity | 2.13 - 2.19 |
| Peak Melting Temperature | 623oF (2oF) |
| Tensile strength (Minimum) | 2800 psi |
| Elongation (Minimum) | 200% |

Bond the PTFE sheet in the recess of steel plate under controlled factory conditions. Use adhesive material that is an epoxy resin conforming to the requirements of Federal Specification MMM-A-134.

Uniformly roughen the contact surfaces of PTFE sheet and steel plate to be bonded to a minimum roughness height value of 250 micro-inches.

Factory treat the side of the PTFE sheet to be bonded by the sodium naphthalene or sodium ammonia process, after the contact surface is roughened.

Fully bond the PTFE sheet in the recess. Ensure the PTFE surface is smooth and free from bubbles after completion of the bonding operation. PTFE sheets that are delaminated will be rejected.

Perimeter seal weld the stainless steel plate to the steel sole plate. Use stainless steel electrodes in accordance with the requirements of the electrode manufacturer. After the completion of the weld operation, ensure the stainless steel plate is smooth and free from waves.

Control the flatness of the bearing elements such that upon completion of the bearing assembly the PTFE/stainless steel sliding interface is in full bearing.

Provide a mating surface of the stainless steel plate with the PTFE surfacing with a surface finish of less than 8 micro inches root-mean-square (rms), determined according to ANSI Standard B46.1. Do not exceed a first movement static coefficient of friction of 0.05 for the sliding element of the production bearings, when tested without the coating of silicone grease.

Fully vulcanize elastomeric bearing pads to the steel plates under factory controlled conditions. Provide a bond with a peel-strength of at least 30 pounds per inch as determined by AASHTO M 251, appendix X2.

Prepare and paint metal surfaces, except stainless steel surfaces, of bearings exposed to the atmosphere in the completed work. Prepare and paint the surfaces according to Section 504.

After installation of the bottom portion of the bearing assembly, apply a 1/16 inch thick coating of silicone grease to the entire PTFE surface and reassemble the bearing without damage to the mating sliding surfaces. Use silicone grease conforming to Military Specification: MIL-S-8660.

At your expense and without contract extension time return damaged bearings and bearings with scratched mating surfaces to the factory for replacement or resurfacing.

Prior to proof testing, permanent die stamp all individual components on 2 of 4 sides with markings consisting of bearing number and contract number. Provide each bearing with a unique bearing number and match marks on plate edges to insure correct assembly at the job site.

3.	Testing. Proof test and evaluate full sized PTFE bearings for compression and coefficient of friction in the presence of the Engineer, unless otherwise directed. Perform proof tests on samples randomly selected by the Engineer from the production bearings to be used in the work. Perform proof tests at an approved independent laboratory. If proof tests are not performed at the specified load, perform additional physical tests in the presence of the Engineer, unless otherwise directed, to demonstrate that the requirements for proof testing at the specified load are satisfied. Give the Engineer at least 7 working days notice before beginning proof testing.

Proof test one bearing per lot of production PTFE bearings. A lot is defined as 25 PTFE bearings or fraction thereof of the number of PTFE bearings shown on the Project Plans.

Clean the bearing surfaces prior to testing.

Proof test bearings after conditioning specimen for 12 hours at 75o 5oF.

Perform the tests with the dead load as specified in the Contract for the bearing with the test load applied for 12 hours prior to friction measurement and the following:

Arrange the tests to allow measurement of the static coefficient of friction on the first movement of the bearing.

Measure the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

Subject the test bearings to a minimum of 100 movements of at least one inch of relative movement at a sliding speed not exceeding 12 inches per minute. After cycling, measure again the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

The proof tested bearings are to show no visible sign of: (1) bond failure of bearing surfaces, (2) separation or lift-off of plates from each other or from PTFE surfaces, (3) other defects. When a proof tested bearing fails to comply with the Contract Documents, test each bearing in that lot for acceptance.

Proof test results are to be certified correct and signed by the testing laboratory personnel who conducted the test and interpreted the test results. Include the bearing numbers of the bearings tested on the proof test results.

Test a minimum of one pad per lot for bond strength per AASHTO Test M 251. Test specimens are to show no indication of deterioration of elastomer or loss of bond between the elastomer and steel laminates.

Protect all PTFE and stainless steel surfaces from contamination and weather damage.

4.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 720-2.03.4.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

Replace Section 721 with the following:

SECTION 721

PRESTRESSING STEEL AND FITTINGS

721-2.01 SCOPE. Prestressing steel and fittings used in pre-tensioned and post-tensioned concrete construction.

721-2.02 PRESTRESSING STEEL. Meet the following:

Steel Strand	AASHTO M 203

Uncoated Stress-Relieved Steel Wire	AASHTO M 204. Do not use oil-tempered wires.

High Strength Steel Bars	AASHTO M 275

721-2.03 POST-TENSIONING SYSTEM. Use only post-tensioning systems that utilize tendons fully encapsulated in anchorages and ducts. Systems that transfer prestress force by bonding the prestress steel directly to concrete are not allowed. Use only post-tensioning systems that are approved by the Engineer and meet the following requirements:

1.	Anchorage and Distribution. Secure prestressing steel at the ends by means of approved permanent type anchoring assemblies.

Use anchorage devices for post-tensioning that hold the prestressing steel at a load producing a stress of not less than 95 percent of the guaranteed ultimate tensile strength (GUTS) of the prestressing steel, when tested in an unbonded state, without exceeding the anticipated set.

Distribute the load from the anchoring assemblies to the concrete by means of approved devices or bearing plates that will effectively distribute the load to the concrete. Construct the bearing plate and wedge plate from ferrous metal. For bending stresses in the bearing plates or assemblies induced by the pull of the prestressing steel, do not exceed the yield point of the material or cause visible distortion in the bearing plate when 95 percent of the GUTS of the tendons is applied as determined by the Engineer. Do not exceed 3500 psi directly underneath the bearing plate or assembly for the final unit compressive stress on the concrete.

Galvanize the body of the anchorage assembly in accordance with AASHTO M 111. Other components of the anchorage assembly including wedges, wedge plate and local zone reinforcement need not be galvanized.

Construct anchorage assemblies with grout vents suitable for post-grouting inspection access as approved by the Engineer. Equip all anchorages with a grout cap that is vented and bolted to the anchorage.

Recess the anchoring assemblies so that the ends of the prestressing steel and all parts of the anchoring assemblies will be at least 3 inches inside of the end surface of the members, unless shown otherwise on the plans. After post-tensioning all tendons, fill the recesses with concrete conforming to the provisions for the structure and then finished flush with the abutment end diaphragm.

2.	Strand Couplers. Do not use strand couplers.

3.	Enclosures for Post-tensioning. Use rigid ferrous metal duct enclosures for prestressing steel that are galvanized, mortar tight, and capable of withstanding concrete pressures without deforming. Use rigid ducts with smooth inner walls that can be curved to the proper configuration without crimping or flattening and have sufficient strength to maintain their correct alignment during placing of concrete. Do not use semi-rigid ducts. Fabricate ducts with either welded or interlocked seams.

Connect sections of rigid ducts using galvanized ferrous metal couplings that are mortar tight and do not result in angle changes at the joints. Do not use split metal couplings. Use waterproof tape to seal all connections to the duct. Connect ducts to anchoring assemblies using transition couplings that are galvanized ferrous metal or polyethylene, mortar tight, and of sufficient strength to prevent displacement of the ducts during concrete placement.

Use ducts for multi-strand tendons with a minimum diameter that provides an inside area at least 2.5 times the net area of the prestressing steel in the tendon.

Do not use ducts with diameters that exceed 0.4 times the least gross concrete thickness at the duct location.

Use duct enclosures with vents for the injection of grout after post-tensioning.

4.	Grout Vents. Use vents with positive means for allowing the escapement of air, water, grout, and bleed water out of the vents, injecting grout through the vents, and sealing to prevent grout leakage from the vents. Use 3/4 inch minimum diameter standard pipe or suitable plastic pipe vents with positive shut-off designed to withstand the grouting pressure. Do not crimp or bend the vent pipe. Use metallic or plastic structural fasteners to connect the vent with the duct. Do not use plastic components that react with the concrete or enhance corrosion of the prestressing steel, or contain water-soluble chlorides. Make all vents mortar tight, taped as necessary. Make vents with sufficient length out of the concrete member to allow proper closing of the vents. Remove ends of vents at least 1 inch below the roadway surface after grouting has been completed.

Place vents at the following locations:

a.	At anchorages.

b.	At the high points of the duct, when the vertical distance between the highest and lowest point is more than 20 inches.

c.	At a location down flow from all high point vents where the duct is approximately one-half duct diameter lower than the crest, but not to exceed 3 feet downstream.

d.	At the lowest point of the duct.

e.	At major changes in the cross-section of the duct.

f.	At other locations designated by the Engineer.

5.	Grout Caps. Use grout caps that completely cover and seal all exposed ends of prestressing steel at the anchorage. Seal the cap with neoprene “O” ring seals and place a grout vent on the top of the cap. Use caps rated for a minimum pressure of 150 psi.

721-2.04 CERTIFICATION.

1.	Prestressing Steel. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 721-2.04.1.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

2.	Post-Tensioning Systems. Submit certified test reports to the Engineer that shows the post-tensioning system meets all the requirements specified herein. Submit the certified test reports with the shop drawing submittal. If any component of the post-tensioning system is modified or replaced, the entire system must be retested and resubmitted to the Engineer for approval.

Ensure that all components of a system are stamped with the supplier’s name, trademark model number and size corresponding to catalog designation.

Submit certification stating the manufacturer's minimum guaranteed ultimate tensile strength of all prestressing steel used for this project.

Assign an individual lot number for each manufactured reel of prestressing steel to be shipped to the site. Tag each reel in such a manner that each lot can be accurately identified at the site. All unidentified prestressing steel received at the site will be rejected.

Assign and tag each lot of anchorage assemblies to be installed at the site. Tag each anchorage assembly in such a manner it can be accurately identified at the site. All unidentified anchorage assemblies received at the site will be rejected.

SECTION 724

SEED

724-2.02 MATERIALS.  Delete Table 724-1 in its entirety and substitute the following tables:

TABLE 724-1

SEED REQUIREMENTS

Schedule A – No Mow Seed Mix (Application Rate: 3 lbs per 1,000 s.f.)

GERMINATION	GERMINATION    PROPORTION

- NAME	PERIOD	PURITY	RATE	         BY WEIGHT

ArctaRed Fescue

(Festuca rubra ‘Arctared’)	14 days	90%	85%		35%

Nortran Tufted Hairgrass

(Deshampsia caespitosa)	14 days	90%	85%		60%

Annual Ryegrass

(Lolium spp.)	10 days         90%	85%	   5%

TABLE 724-2

SEED REQUIREMENTS

Schedule B –Wildflower Seed Mix (Application Rate: 3.5 lbs per 1,000 s.f)

GERMINATION	GERMINATION   PROPORTION

- NAME	PERIOD	PURITY	RATE	       BY WEIGHT

Annual Ryegrass

(Lolium spp.)	14 days	85%	75%	        5%

Nortran Tufted Hairgrass

(Deschampsia caespitosa)	14 days	95%	85%	      60%

Arctared Red Fescue

(Festuca rubra ‘Arctared’)	14 days	90%	90%	     30%

- Lupine Nootka

(Lupinus nootkatensis)	21 days	85%	85%	      5%

TABLE 724-2

- SEED REQUIREMENTS

Schedule C – Wet Area/No Mow Mix (Application Rate: 2 lbs per 1,000 s.f.)

GERMINATION	GERMINATION      PROPORTION

- NAME	PERIOD	PURITY	RATE                 BY WEIGHT

Arctared Red Fescue

(Festuca rubra ‘Arctared’)	14 days 	90%	85%	     25%

Nortran Tufted Hairgrass

(Deschampsia cespitosa)	14 days	90%	80%	     30%

Alyeska Polargrass

(Arctagrostis latifolia)	14 days 	90%	85%	     20%

Egan American Sloughgrass

(Beckmannia syzigachne)	14 days 	90%	85%	     25%

- SECTION 726

TOPSOIL

Special Provision

Delete Subsection 726-2.01, except for Table 726-1 and replace with the following:

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

CR208-112707

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provision

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

- Virgin/Recycled Wood Fiber, or Blended Wood-Paper Mulch.

Mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors. The mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry. The mulch shall be of a texture such that it can be applied uniformly to the soil surface. Mulch shall not create a hard crust upon drying and it shall have moisture absorption and retention properties as well as the ability to hold grass seed in contact with the soil.

The mulch shall be shipped in packages of uniform weight (plus or minus 5%) bearing the name of the manufacturer and the air-dry weight content.

The mulch shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial tackifier shall be used on all seeded areas where mulch is applied. The amount added will be as recommended by the manufacturer.

3.	Shredded Bark Mulch: Shredded Bark Mulch shall consist of shredded bark and wood.  Maximum length of any individual components shall be two (2) inches and a minimum of 75% of the mulch shall pass through a one (1) inch sieve.  Mulch shall be free of growth or germination-inhibiting ingredients.  The bark mulch shall have the characteristics of retaining moisture, forming a mat not susceptible to spreading by wind or rain, and providing a good growth medium for plants.  Shredded bark may contain up to 50% shredded wood material.  Wood chips are not acceptable.  Bark mulch containing shredded wood shall be aged for one-year minimum prior to installation.  The mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.  Mulch shall be spread evenly in all planting beds as shown on Plans.

Add the following subsection 727-2.04:

727-2.04 Compost Blanket.  Compost blanket media shall be a composted, weed free organic matter source derived from: peat, agricultural, food, or industrial residuals; biosolids (treated sewage sludge); yard trimmings; source-separated or mixed solid waste. Particle size shall be as described below in the product parameters table. The compost shall possess no objectionable odors, will be reasonably free (<1% by dry weight) of man-made foreign matter and will meet the product parameters outlines below. The product shall be certified through the U.S. Composting Council’s (USCC) Seal of Testing Assurance (STA) program. Before delivery of the compost, supplier must provide a copy of the lab analysis, performed by a STA Program certified lab, verifying that the compost meets the product parameters listed below. The lab analysis should not be more than 90 days old.

Compost Blanket Parameters

| Parameters 1,4 | Reported as (units of measure) | Vegetated Compost |
| --- | --- | --- |
| pH2 |  | 5.0 - 8.5 |
| Soluble Salt Concentration2 (electrical conductivity) | dS/m (mmhos/cm) | Maximum 5 |
| Moisture Content | %, wet weight basis | 30 – 60 |
| Organic Matter Content | %, dry weight basis | 25 – 65 |
| Particle Size | % passing a selected mesh size, dry weight basis | - 3”, 100% passing - 1”, 90% to 100% passing - 3/4”, 65% to 100%passing - 1/4”, 0% to 75% passing - 6” maximum particle length |
| Stability3 Carbon Dioxide Evolution Rate | mg CO2-C per g OM per day | < 8 |
| Physical Contaminants (man-made inerts) | %, dry weight basis | < 1 |

- Recommended test methodologies are provided in Test Methods for the Examination of Composting and Compost (TMECC, The US Composting Council)

- Each specific plant species requires a specific pH range.  Each plant also has a salinity tolerance rating; maximum tolerable quantities are known.  When specifying the establishment of any plant or turf species, it is important to understand the pH and soluble salt requirements and how they relate to the compost in use.

- Stability/Maturity rating is an area of compost science that is still evolving and, as such, other various test methods could be considered.  Also, never base compost quality conclusions on the result of a single stability/maturity test.

- Landscape architects and project (field) RCEs may modify the allowable compost specification ranges based on specific field conditions and plant requirements.

The product shall be certified through the U.S. Composting Council’s (USCC) Seal of Testing Assurance (STA) program. Before delivery of the compost, supplier must provide a copy of the lab analysis, performed by a STA Program certified lab, verifying that the compost meets the product parameters listed below. The lab analysis should not be more than 90 days old.

SECTION 730

SIGN MATERIALS

Standard Modification

Delete Subsection 730-2.01 SHEET ALUMINUM and replace with the following:

730-2.01 SHEET ALUMINUM.  Use alloy 6061-T6, 5052-H36, 5052-H38, or recycled aluminum meeting alloy 3105, as specified in ASTM B 209.  Meet the thickness of aluminum sheet designated on the Plans.  Verify alloy and temper designation by mill certification.

Before January 1, 2011, treat the aluminum base metal sheets with chromate conversion coating for aluminum to meet ASTM B449, Class 2.

After January 1, 2011, treat the aluminum base metal sheets with a rinsed non-hexavalent chromium conversion coating for aluminum and aluminum alloys that meets ASTM B 921, class one.  Handle the cleaned and coated base metal only by a mechanical device or by operators wearing clean cotton or rubber gloves.  After cleaning and coating operations, protect the panels at all times from contact or exposure to greases, oils, dust, or other contaminants.

Make each sign panel a continuous sheet for all lengths 72 inches or less in the horizontal direction.  Use no more than one vertical splice for signs up to 144 inches in length and 48 inches or less in height.

Meet the panel dimensions specified with a tolerance of 1/16 inch.  Furnish metal panels that are cut to size and shape and free of buckles, warp, dents, cockles, burrs, and any other defects resulting from fabrication.  Complete all possible fabrication, including shearing, cutting, and punching of holes prior to the base metal preparation.

E86-041210

Special Provision

730-2.04 SIGN POSTS.

Add No. 7:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to ASTM A500, Grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W-shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

CR81-062204

- SECTION 740

- SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace Subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.

- Design.  Design and fabricate highway lighting structures to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans.  Use a wind speed of 100 mph with a gust factor of 1.3.  Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 ft above the pole base.

Design and fabricate traffic signal structures to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category III, with galloping using a basic wind speed of 100 mph and Central Region standard loads.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for the complete-in-place structure including the supported hardware.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section.  Orient handholes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide a minimum overlap of two and one half (2.5) feet or the overlap specified in the Plans, whichever is greater.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to 1/2 inch thick from the prequalified base metals listed in AWS D1.1.  Fabricate elements greater than 1/2 inch thick from steel that conforms to AASHTO M270 and meets the Fracture Critical Impact Test requirements for Zone 3.  The Department will not accept structures that use laminated steel elements.

Fabricate the cross section of each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conform to ASTM A 53 Grade B.

Fabricate breakaway signal poles in accordance with the Pole Sheet in the Plans. Fabricate signal poles 10 to 15 feet long from 7 gage (US Standard) sheet steel.  Fabricate each post with a minimum inside diameter at the base plate as shown in the Plans.  Use 4 inch diameter by 4 inch Schedule 40, ASTM A53, Grade B pipe as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments.  Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot-dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Galvanizing kettles will be large enough to completely submerge each element, the mast arm, and the pole.  Submerge the complete/whole element in the galvanizing process.  An element galvanized in sections will not be accepted.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

(1).	Not fabricated according to these specifications or the approved shop drawings,

(2)	Bowed with sweeps exceeding 3/4 inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

(3)	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to Subsection 504-3.01.8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints for the length of the slip fit joint plus one half the diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

d.	Only visually inspect welds made on luminaire mast arms.

4.	Anchor Rods & Bolts.  Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

5.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified.

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using 1/4 inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms.  If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.  Provide the holes for the blind rivets before galvanizing.

TABLE 740-1

POLE MARKINGS

Note:

Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms.

| POLES (Including Mast Arms ) | MEASUREMENTS | TAG MARKINGS |
| --- | --- | --- |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

740-2.05 CONDUCTORS.  Replace Table 740-2 with the following:

TABLE 740-2

CONDUCTOR TERMINATION TABLE

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG. NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |
| 5 | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Black |  |  |
|  | Spare | Orange |  |  |
| 3 | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |

TABLE 740-2

CONDUCTOR TERMINATION TABLE 

(Continued)

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Preemption per manufacturer installation methods | Yellow | 20 | "PRE" |
|  |  | Orange |  |  |
|  |  | Blue |  |  |
| 3 | Preemption Confirmation | Black | 14 | "PRECON" |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 3 | Service to Controller | Black | 6 or 4 | "SIG" |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |

Replace No. 5. with the following:

5.	Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA 
Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

Replace "6 twisted pairs" in the second sentence of the 4th subparagraph of No. 6. with the following:

"7 twisted pairs"

Replace TABLE 740-3 with the following:

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Pair No. | Tip | Ring | Pair No. | Tip | Ring |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

Replace Subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows conforming to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 80, high-density polyethylene (HDPE) pipe that conforms to UL Standard 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish Type X bodies and, for photoelectric control installation, furnish Types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to 3/4 inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to 3/4 inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Replace Subsection 740-2.09 with the following:

740-2.09 CONTROLLER ASSEMBLIES. Provide solid state, traffic controller assemblies having level 2 conformance to NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements as defined in NTCIP1202.  Traffic Controller Assemblies must meet or exceed the Environmental Requirements of Section 2 of the NEMA TS2-2003 V02.06 document. The Original Equipment Manufacturer (OEM) and its manufacturing and testing facilities shall be ISO 9001:2000 certified for processes involving the Traffic Controller Assemblies.

Use traffic control equipment that is compatible with the existing traffic signal monitoring system.  Compatibility must be 100% at the cabinet level to include inputs, outputs, telemetry protocol, and block upload and download of RAM data.

The existing traffic signal monitoring system is Centracs ATMS by Econolite.

In addition, features of the existing local controllers and controller modules must be functionally duplicated to meet or exceed the performance of the existing equipment.

The existing local controller cabinets at other intersections include the following equipment:

(1)	Econolite ASC/3-2100

	Use LED indicators for all electronic devices covered under Subsections 740-2.09 through 740-2.13.

Replace Subsection 740-2.10 with the following:

740-2.10 CONTROLLER UNIT.

Actuated Controller Unit (CU).

Provide solid state, Type A2N Actuated Controller Units (CU) meeting the requirements of Section 3 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements.

	The CU must meet the referenced National Transportation Communications for ITS Protocol (NTCIP) and comply with publication TS 3.2 the Simple Transportation Management Framework, and shall meet the requirements for Conformance Level 2

	The software shall comply with NEMA TS 3.3, the Class B Profile, and shall include both an EIA/TIA 232-E and an FSK modem interface for NTCIP based communications.

	The CU shall implement conformance groups and optional object groups as defined in NEMA TS 3.4 and TS 3.5 for A2N level 2.

	Provide controllers with display heaters or enhancements to improve viewing in temperatures below 0 F.

	Provide controllers having an interface compatible with SYNCRO-7 traffic modeling software.

Furnish Econolite ASC/3-2100 controller unit or approved equal also meeting the following requirements:

HARDWARE

1.	Enclosure

a.	Compact the controller to fit in limited cabinet space.  It shall rest on a shelf that is not more than 7" deep.  External dimensions no larger than 10 1/4" x 15 1/4" x 9" (H x W x D).

b.	Construct the enclosure of aluminum and finish with an attractive and durable protective coating.  Permanently display model, serial number, and program information on the top surface.

2.	Electronics

a.	Modular electronics with vertical circuit boards.  Horizontal circuit cards are not acceptable.

b.	Use a microprocessor for timing and control functions.  Verify continuing operation of the microprocessor by an independent monitor circuit that is set an output and indicate an error message if a pulse is not received from the microprocessor within a defined period.

c.	In the interest of reliability, do not use sockets for any electronic device.  Devices must be directly solder to the printed circuit board.  Use surface mount parts for the majority of the electronic components in the controller.

d.	Use a built -in, high -efficiency switching power supply to generate required internal voltages as well as 24 VDC for external use.  Regulate voltages and monitor with control signals.  Mount the fuses on the front of the controller for 120 VAC input and 24 VDC output.

e.	Derive timing of the controller from the 120 VAC power line.

f.	Store user -programmed settings and intersection configuration data in Flash Memory. Memory requiring an energy storage device (battery or capacitor) to maintain user data is not acceptable.  To facilitate the transfer of user programmed data from one controller to another, a data transfer module (data key) using a separate serial flash memory device is an option.  This data transfer module shall be easily removable and directly accessible from the front of the controller.  The controller will not require this module to be present for proper operation.

g.	Store controller software in Flash Memory devices.  The controller software shall be easily updated without the removal of any memory device from the controller.  The use of removable PROMS or EPROMS from the controller is not acceptable.  Option to update software on the controller using a Windows based computer.  Allow updating the controller software via a serial or Ethernet port from the front of the controller. Updating the controller software shall require the intersection to be in flash for no more than ten seconds using Ethernet file transfer.

h.	Printed circuit boards shall meet the requirements of the NEMA Standard plus the following requirements to enhance reliability:

(1)	Plated -through holes and exposed circuit traces with solder.

(2)	Solder mask material covering both sides of the printed circuit board.

(3)	Clearly marked circuit reference designation for components and the polarity of capacitors and diodes adjacent to the component.  Designated pin 1 for integrated circuit packages on both sides of printed circuit boards.

(4)	Printed circuit board assemblies, except power supplies, coated with a clear moisture -proof and fungus -proof sealant.

3.	Front Panel

a.	Front of the controller consisting of a panel for the display, keyboard, and connectors for necessary user connections.  Maintenance of the electronic circuits and option installation will be possible by opening the front panel only.

b.	Required 16-line by 40-character/line alphanumeric liquid crystal display (LCD) to show program, and status information with the display area nominal measurements of 2 1/2" x 4 1/2" (H x W), or larger.  Provide, for ease of viewing, backlighting by light emitting diodes and multiple levels of contrast adjustment.  Adjustable display contrast with front panel mounted push buttons.  The use of user potentiometers for display contrast will not be acceptable.

c.	Clearly labeled front -panel operator inputs and environmentally sealed electrometric keys.  Including a 10 digit numeric keypad, nine function keys, an oversize ENTER key, and an oversize four arrow cursor control key.

d.	Required nine function keys, clearly labeled, and providing the following operation:

MAIN MENU - Pressing the Main Menu key displays the main menu.

SUBMENU - Pressing the Sub Menu key from a data screen displays the current submenu.

NEXT DATA - Pressing the Next Data key searches for the first non -zero data field, thus allowing rapid search for valid entries.

NEXT SCREEN - Pressing the Next Screen key l displays the next screen, thus allowing rapid advancement from screen to screen.

HELP - Pressing the Help key at a data entry field displays a help screen about that field.

STATUS DISPLAY - Pressing the Status Display key presents the intersection status display.

NEXT PAGE - Pressing the Next Page key advances to the previous or next group of data entry screens in a submenu.

BACKLIGHT - Pressing up and down arrow -shaped keys adjusts the backlighting of the LCD display screen for brighter or dimmer contrast.

SPECIAL FUNCTION - Pressing the special function key places Pedestrian Calls while viewing the main status display, lock access to controller data until supervisor or data change access codes are entered, and enter hexadecimal values

CLEAR - Pressing the clear key aborts a data entry and restores the current value.

4.	Data Key

a.	A data key available for use as a database storage device (backup) or as a database transfer module capable of storing a minimum 256KB of data.

b.	The data key hot swappable, to be inserted and removed without powering down the controller.

c.	The data key capable of storing the entire controller database and shall retain the information without use of battery or capacitor backup.

d.	This key not required by the controller to be present during normal operation. 2.5. Connectors

e.	Accessible interface connectors from the front of the controller.  Controller models able to accommodate different versions, as follows:

(1)	EMA TS2 Type 1

(2)	NEMA TS2 Type 2

(3)	NEMA TS1

f.	Connectors and signals compatible with the Econolite Model ASC/2, ASC/2S & ASC -8000 25 pin telemetry port and D connector.

g.	Capable of assigning special applications of input or output function to any input or output pin respectively on the interface connectors, with the exception of Flashing Monitor, Controller Voltage Monitor, AC+, AC -, Chassis Ground, 24 VDC, Logic Ground and TS2 Mode bits.

5.	Serviceability

a.	Electronic modules including the power supply easily removable from the front of the controller using a screwdriver as the only tool.  Plug in connector for power and signal connections to the circuit boards.

b.	Allow the removal and replacement of any circuit boards without unplugging or removing other circuit boards, except for the power supply.  No more than two boards attached together to form a circuit assembly.

c.	Designed for one side of any circuit board to be accessible for troubleshooting and testing while the controller is still in operation and accomplished without the use of extender cards or card pullers.

DISPLAY

1.	Dynamic Displays

a.	Provide dynamic displays listed below to show the operational status of the controller and offering additional displays for programming.  Possible to place vehicle, pedestrian, and preemption calls from the keyboard while displaying status information.

b.	Intersection status displaying a summary of ring, phase, coordination, preemption and time-based control status.

c.	Controller status display indicating current interval, pedestrian, density, maximum, and maximum extension timing by phase and ring.  Display the status of vehicle and pedestrian signal outputs in combination with vehicle and pedestrian calls.

d.	Coordinator status display indicating the command source, current coordination pattern information, local and system cycle count, commanded/actual offset, offset correction, time based control status, hold, force off, vehicle permissive, split count down, split extension, offset from ring 1 and green band indications.

e.	Preemptor status display indicating priority (railroad, fire, emergency) preemptors and bus preemptors with calls, preemptor active, inhibit, and delay status.  When a preemptor is active, the display also indicates preemptor interval, timing, duration, and hold status.  A portion of the display indicating the controller status during preemption including current status, interval, and timing by phase and ring and the status of vehicle and pedestrian signals for each phase.

f.	Time base status display indicating the current time and date, the current day and week program, the active program step for both coordination pattern and time of day functions, the start time of the next program step, and the highest step used.  Also displays the programmed selections of the active coordination pattern and time of day pattern.

g.	Communications status displays for Port 1 (SDLC), Port 2 (terminal) Port 3, Ethernet, and NTCIP.

h.	Port 1 (SDLC) status display indicating the frame responses from the MMU, the terminal and facilities BIUs and the detector BIUs.

i.	Ports 2 and 3 status display indicating the interconnect format, transmit, valid data, data error, carrier detect and the last valid command.

j.	An Ethernet status display indicating the line speed, the line status, the total number of transmit and receive counts and transmit and receive error counts.

k.	An NTCIP status display indicating the total number of SNMP and STMP transmit and receive counts.

l.	A detector status display indicating activity for up to 64 detectors.  The display shows the detector calls as processed by the controller.

m.	Flash/malfunction management unit (MMU) status display indicating flash status plus MMU channel, conflict, and monitoring function status.  A separate display indicating the results of the controller’s comparison of its MMU programming to the programming in the controller.

n.	An input and output status display indicating the activity of the logic level inputs and outputs to the controller.

2.	Programming Displays

a.	Programming displays in the form of menus to aid the operator in entering data from the front -panel keyboard.

b.	A main menu allowing the user to select a major function of the controller.  A submenu shall then be displayed to allow the user to select a sub -function within the major function. A four arrow cursor key allows the user to scroll through programmed data.

c.	English language and traffic engineering terminology used throughout to facilitate programming.  The display organization allows traffic personnel to program the controller without using reference cards or manuals.  Data entry and data screens shall be in logical order.

d.	Programming entries consisting of alpha -numerical values, YES/NO and ON/OFF entries.  During program entry, new data is displayed as it is entered. Validated and stored entries only when the consistency check is preformed for entries that are constrained by other programmed data or when the ENTER or cursor key is pressed when they are not.

e.	An example of constrained data is the sequence of the phases within a ring.  Checked with the phase compatibility, phases in the ring and start phases among others.

f.	An example of non-constrained data is the vehicular extension time entry.

g.	The keyboard entry software shall include context sensitive help screens.  Help information accessed by placing the cursor on the data entry in question then pressing the HELP key.  Help screens provided for keyboard entered data and shall include at a minimum range, description, and functional operation information for the data entry.

PROGRAMMING

1.	Programming Methods

a.	Methods listed below shall be available for controller configuration and timing entries. The manufacturer shall be able to provide as off the shelf items firmware and software required to affect the listed methods and to implement network operation with system masters and host PC's.

(1)	Manual data entry from the front panel keyboard

(2)	Downloading from telemetry from a system master connected to a host PC in a closed loop system.

(3)	Downloading from a portable PC -compatible computer via an Ethernet or serial cable.

(4)	Transfer from one controller to another using the Ethernet port on each controller.

(5)	Transfer from one controller to another, or restoring for a back up copy, using a data transfer module (data key).

2.	Programming Security

a.	A minimum of three access levels available to provide programming security.

(1)	The highest or supervisor level shall have access to programming entries including setting access codes.

(2)	The second or data change level shall have access to programming entries except access codes.

(3)	The third or data display level shall only have access to displayed data.  No access code shall be required to display data.

b.	User selectable, four digit access codes provided for the supervisor and data change access levels.  Access codes shall initially be set to provide unrestricted access.

c.	If there has been no keyboard activity the controller shall automatically logoff the user after 30 minutes.

3.	Programming Utility Functions

a.	A copy function shall permit copying timing data from one phase to another.  It shall also permit copying timing plan from one timing plan to another, one detector plan and detector options plan to another, coordination pattern data from one pattern to another and one sequence to another.  This feature will facilitate data entry when programming any two or more phases with the same timing values, or detectors with the same programming, and/or two or more coordination patterns with the same pattern data.

b.	The controller unit shall contain a backup data base with user specified values stored in nonvolatile memory.  A copy function shall permit transferring the backup database to the active database.

c.	A memory clear function shall permit the user to clear data entries for the following controller functions, either individually or all at once:

(1)	Configuration

(2)	Controller

(3)	Coordinator

(4)	Preemptor

(5)	Time base

(6)	Detectors

(7)	Logic Processor

d.	A sign on message shall allow the user to view the controller software version number. This message shall be displayed upon power up until a key is depressed.  It shall also be possible to display the sign on message by keyboard selection.  The sign on display shall allow a user defined message of up to two lines with 38 characters per line.

e.	The controller shall have the capability to output a memory image of the user programmed settings and intersection configuration data in binary format.  This shall allow transferring the memory image data to a data key.

ACTUATED CONTROL FUNCTIONS

The controller shall provide actuated control functions and operations required by the NEMA TS2 Standard.  In addition, it shall provide the features described in the following paragraphs.

1.	Phase Sequence

a.	The phase sequence of the controller shall be programmable in any combination of sixteen phases, eight concurrent groups and four timing rings.

b.	Phase sequence information shall be changeable from the keyboard and stored in EEPROM data memory.

c.	The standard phase sequence of the controller shall also be capable of being altered by coordination, time of day or external alternate sequence command.  The alternate sequence commands shall allow reversing the normal phase sequence of each phase pair as shown below:

Command A - reverses phases 1 and 2

Command B - reverse s phases 3 and 4

Command C - reverses phases 5 and 6

Command D - reverses phases 7 and 8

Command E - reverses phases 9 and 10

Command F - reverses phases 11 and 12

d.	The operator shall be able to select from a library of standard sequences.  As a minimum, the following shall be provided:

(1)	Standard NTCIP sequence

(2)	Two through eight phase controller

(3)	Sixteen phase quad left turn controller

(4)	Four single ring 4 phase controllers

(5)	Dual TS2 eight phase quad controllers

(6)	TXDOT three phase diamond controller

(7)	TXDOT four phase diamond controller

e.	An exclusive pedestrian clearance movement provided that will time and display the pedestrian indications with the vehicle movements remaining in all red.

2.	Timing Intervals

a.	Timing intervals shall be programmable from 0 -255 in one second increments or from 0 -25.5 in one tenth second increments, depending on the function.

b.	Four independent timing plans provided and selectable on a time of day basis or by coordination pattern. Each plan shall contain the following interval timings:

(1)	Minimum Green

(2)	Bike Green

(3)	Delay Green

(4)	Walk

(5)	Walk 2

(6)	Walk Maximum

(7)	Pedestrian Clearance

(8)	Pedestrian Clearance 2

(9)	Pedestrian Clearance Maximum

(10)	Pedestrian Carryover

(11)	Vehicle Extension

(12)	Vehicle Extension 2

(13)	Maximum 1

(14)	Maximum 2

(15)	Maximum 3

(16)	Dynamic Maximum

(17)	Dynamic Maximum Step

(18)	Yellow Clearance

(19)	Red Clearance

(20)	Red Maximum

(21)	Red Revert

(22)	Actuations before Reduction

(23)	Seconds per Actuation

(24)	Maximum Initial

(25)	Time before Reduction

(26)	Cars Waiting

(27)	Time to Reduce

(28)	Min Gap

c.	Guaranteed minimum interval values specified at the time of purchase and shall not be changed or overridden from the keyboard. Values provided for the following intervals:

(1)	Minimum green

(2)	Walk

(3)	Pedestrian clearance

(4)	Yellow clearance

(5)	Red clearance

(6)	Red revert

(7)	Overlap Green

d.	A bike green interval provided that will replace the phase minimum green if the interval time is larger than the min green time and if a detector input designated as a bike detector has been activated.

e.	Two Walk and Pedestrian Clearance intervals provided for each phase per timing plan.  The second Walk and Pedestrian Clearance activated by a time base action plan.

f.	Two vehicle extension intervals provided for each phase per timing plan.  The active vehicle extension interval selected by a time base action plan.

g.	If enabled, a Delay Green timer shall delay the vehicle phase from starting until the timer has expired.  This shall provide an additional all red for the vehicles movement until the timing is complete.

h.	The Pedestrian Walk interval shall extend from Walk to the smaller of the Walk Max time or the phase maximum in effect with a constant input from the "Walk Extension detector".

i.	Volume density intervals shall include actuations before and cars waiting.  Actuations before added shall provide a user specified number of actuations that must occur before adding variable (added) initial time.  Cars waiting shall provide a user specified number of actuations, or cars waiting, that must occur before starting gap reduction. Gap reduction shall be initiated by either; time before reduction or cars waiting, whichever reaches its maximum value first.

j.	Capable of dynamically extending the maximum green time for each phase based on vehicle demand.  Three maximum green intervals shall be selectable per phase based on either time of day, coordination pattern or external input.  The initial interval shall be selectable as Max 1, Max 2, or Max 3.  If the phase terminates due to max out for two successive cycles, then the maximum green time in effect shall automatically be extended by a dynamic max step interval on each successive cycle until it is equal to dynamic maximum.  If the phase gaps out for two successive cycles, then the maximum green time reduces by the dynamic max step time until it reaches to the original max value.

k.	Each phase shall have a red maximum timing interval.  An input (red extension) shall extend the all red period of the assigned phase as long as the detector input is true. This input must be true within the all red time of the assigned phase to be able to extend the all red period.  If this detector fails then the all red extension feature shall be disabled.

3.	Overlaps

a.	The controller shall provide sixteen internally generated overlaps (A - P).  These shall be individually programmable as standard, other (see Section 5.3.2) or minus green / yellow.  The green, yellow and red intervals shall be individually programmable following termination of the parent phase.  The overlaps programmed as minus green / yellow overlaps shall provide overlap green when any of the overlap phases are green or when in transition between overlapped phases and a modifier phase is not green.  The overlap will be yellow when an overlapped phase is yellow and the modifier phase is not yellow and none of the overlapped phases are next.

b.	The other overlap option shall provide for protected, pedestrian protected, not overlap, trailing, leading and advance green programming.

c.	A protected overlap shall be green, yellow, or red like a normal overlap except its outputs shall be blank when the protected phase is green, or the controller is transitioning to a non included phase.

d.	A pedestrian protected overlap shall be green under the following conditions :

(1)	When an included phase is green and the protected pedestrian is NOT in walk or pedestrian clearance

(2)	When the controller is in transition between included phases and a pedestrian protected phase is not next

(3)	After servicing an included phase pedestrian demand if there is enough time before max out to service the overlap minimum green

e.	The controller shall provide the capability of sixteen pedestrian overlaps.  These shall be capable of overlapping the pedestrian displays of any combination of phases with a pedestrian movement.

f.	Overlap functions shall be programmable from the controller keyboard.

g.	The controller shall provide a programmable conditional service feature.  When selected, the controller shall service an odd numbered phase once normal service to that phase has been completed and enough time for additional service exists on the concurrent even phase.

h.	A conditional service minimum green time shall be programmable for each phase. This interval shall ensure a minimum green if the phase is conditionally served.

i.	It shall be possible to program the controller to reservice the even phase after conditionally serving an odd phase.  Once an even phase has been conditionally reserviced, the odd phase shall not be conditionally served again until returning to the concurrent group that is timing.

4.	Additional Features

a.	The following features shall be programmable for each phase in each of four separate detector plans:

(1)	Locking/non -locking detector memory

(2)	Vehicle recall

(3)	Pedestrian recall

(4)	Maximum recall

(5)	Soft recall No-rest phase

(6)	Enable Added Initial

b.	Also programmed by phase shall be:

(1)	Phase in use

(2)	Exclusive Pedestrian phase

c.	Soft recall shall return the controller to the programmed phase in the absence of other calls. 5.5.4.  If a phase is designated as a no rest phase the controller shall not rest in the phase.

d.	The controller shall permit power start and external start to be individually programmed by phase and interval.  Start intervals shall be green, yellow red, or yellow with overlaps forced yellow.

e.	During a power start condition, the controller shall be capable of timing an all red or flash interval before the power start phase (s) and interval are displayed.

f.	The controller shall provide guaranteed passage operation on a per phase basis.  When selected, this feature shall provide a full passage (vehicle extension) interval when a phase gaps out with a gap in effect less than the vehicle extension interval (preset gap).

g.	The controller shall provide both single and dual entry operation.  When selected, dual entry shall cause the controller to ensure that one phase is timing in each ring.

h.	It shall be possible via keyboard selection to inhibit the service of a phase with other phase(s) within the same concurrent group.

i.	The controller shall provide the following additional selectable pedestrian functions:

(1)	Actuated phase rest in WALK

(2)	Flashing WALK output

(3)	Pedestrian clearance protection during manual control

(4)	Pedestrian clearance through yellow

(5)	Pedestrian indications remain dark with no call

(6)	Pedestrian timing shall be capable of being carried over from one phase to another

(7)	Programming shall be provided to inhibit re-service of odd phases (left turns) within the same concurrent group.

j.	The controller shall provide a programmable simultaneous gap termination feature. When programmed, phases in both rings shall gap out together in order to terminate the green interval and cross the barrier.

k.	The controller shall provide automatic flash selection according to the requirements of the MUTCD.  Both the flash entrance and exit phases shall be programmable through the keyboard, and flashing shall be controlled by either setting the fault/voltage monitor output to be FALSE or by flashing through the load switch driver outputs.  If flash desired through the load switches, both the phase and flash overlap outputs either yellow or red as selected by the operator.  Automatic flash will be selectable by external input, system command, or time of day action plan.

l.	The controller provides dimming for selectable load switch outputs.  Dimming will be accomplished by inhibiting the selected outputs for alternate half cycles of the 120 VAC line.  Dimming controllable by time of day and an external input; both functions must be TRUE for dimming to occur.  Programming permits individual dimming of the Green/Walk, Yellow/Ped Clear, Red/Don't Walk outputs for each load switch.

COORDINATION

Coordination functions to control intersection cycle lengths, system offset relationships, and phase split percentages provided as a standard feature, with no need for additional modules or software.

1.	Coordination Patterns

a.	Provide a minimum of 120 coordination patterns.  Each pattern allows selection of an independent cycle length, offset value and split pattern.  The coordination patterns selected using telemetry (system), hardwire, or non-interconnected (time base) coordination commands.

b.	The coordination patterns selected by the coordination command using the following formats:

Pattern.  This format allows selecting the coordination patterns directly, that is, commanding Plan 1 selects Pattern 1.  Pattern command includes 1 -120 patterns, pattern 254 shall select free and pattern 255 shall select flash.

Standard.  This format allows selecting the coordination patterns using a pattern number derived from a cycle offset split command.  Each pattern assignable to a specific cycle offset split combination.  The coordination pattern selected using the formula

(((Cycle – 1) * 20) + ((Split – 1) * 5) + Offset)).

TS2.  This format allows selecting the coordination patterns as a function of Timing Plan and one of three offsets.  With this format a minimum of 20 Timing Plans available for selection of one of sixty coordination patterns.

c.	The following functions programmable in each coordination pattern:

(1)	Cycle length

(2)	Split pattern

(3)	Offset value

(4)	Alternate phase sequence

(5)	Split and offset in seconds or percentage

(6)	Crossing artery pattern

(7)	Permissive timing

(8)	Action plan

(9)	Coordinated phase split extension

(10)	Timing plan

(11)	Actuated rest in walk

(12)	Phase re service

(13)	Ring extension

(14)	Split demand pattern

(15)	Ring displacement

(16)	Directed split preferences

(17)	Special function outputs

d.	The following functions shall be programmable for each of the 120 Split patterns:

(1)	Coordinated phase

(2)	Split value by phase

(3)	Omit by phase

(4)	Min recall by phase

(5)	Max recall by phase

(6)	Pedestrian recall

(7)	Max and Pedestrian recall

2.	Cycle Length

a.	One cycle length provided for each coordination pattern.  The cycle adjustable over a range of 30-255 seconds in 1 -second increments.

b.	The cycle length serves as the reference time for coordination timing. 6.3. Synchronization

c.	For systems with a single system sync pulse, coordination timing synchronized to the leading edge of that pulse that serves as the master zero reference for offset timing.

d.	For hardwire systems with multiple sync pulses, the coordinator locks onto the correct sync by trying different syncs and checking for reoccurrence during successive cycles.

e.	After a valid system sync pulse has been received the coordinator checks for the proper occurrence of the system sync pulse during each subsequent cycle.  If a sync pulse does not occur, the coordinator self syncs and continue to operate with the last set of coordination commands for a programmable number of cycles from 0-255.  If a sync pulse does not occur within the programmed period (or until the first sync pulse is received), the coordinator shall revert to the non -interconnected coordination mode.

3.	Offset

a.	Offset normally defined as the time period from the system sync pulse to the beginning of the leading coordinated phase green (local zero).  The coordinator capable of referencing the offset to the beginning of the lagging coordinated phase green, coordinated phase yield or start o f yellow point.

b.	Offsets shall be programmable using both percent and seconds.  The range is from 0-99% of the cycle length in 1% increments or 0-254 seconds in 1 second increments.  An offset value of 255 results in free.

c.	Offset changes achieved by adding or subtracting cycle time over a maximum of three cycle periods to allow a smooth transition to the new offset.  Other offset change methods may be to add 20% to each cycle or to snap to the sync point once the permissive periods are complete and the coordinated phases are green.  Offset correction using dwell also selectable.

4.	Split

a.	Each split provides a split interval for each of sixteen phases.  The split interval is programmable using percent or seconds.  The range is from 0-99% of the cycle length in 1% increments or 0-255 seconds in 1 second increments.

b.	Split interval settings determine the maximum time, including vehicle clearance (yellow and red), for a noncoordinated phase, or the minimum time for a coordinated phase.  Phase termination controlled by establishing a force off point for each phase within the cycle.  Except for the coordinated phases the force off point is selectable to be a fixed point within the cycle or allowed to float.  If floating force offs are selected each phase shall time no more than its own split interval.

c.	During coordination, it shall be possible to operate a coordinated phase as actuated or nonactuated.  If a coordinated phase is actuated, vehicle detections shall permit the coordinator to extend a phase beyond the normal yield point. Extended coordinated phase green shall be selectable using the same range as split interval settings (percent or seconds). If actuated coordinated phases are used they shall be able to have actuated or non -actuated (walk rest) pedestrian movements.

5.	Permissive Periods

a.	Permissive periods provided to control the time period during coordinated phases released to service calls on noncoordinated phases.

b.	Permissive timing begins at the lead coordinated phase yield point.  A yield point automatically computed for the coordinated phase in each ring.  The coordinated phase yield point allows the coordinated phases to yield independent of each other. The yield point is the point that the coordinated phase is released to allow the controller to service calls on noncoordinated phases.  The computation takes into account the coordinated phase split interval plus pedestrian and vehicle clearance times.

c.	Automatic permissive period operation provided by automatically calculating a permissive period for each noncoordinated phase.  The permissive period shall consist of a separate vehicle and pedestrian period computed from the phase split interval and the vehicle/pedestrian minimum time.  The controller answers a call only during the associated phase permissive period.  However, once the controller has been released to answer a call, remaining phases are served in normal sequence.

d.	Single permissive period operation provided by defining a single time period per cycle beginning with the yield point during which the controller is allowed to answer phase calls for any phase.  The duration of this period will be selectable in each coordination pattern.

e.	Dual permissive period operation provided.  During the first permissive period, the controller answers only vehicle or pedestrian calls on the phases following the coordinated phase.  If the controller yields to a call during this period, calls on the remaining phases are served in normal rotation.  During the second permissive period, the controller shall answer calls on remaining phases except the first permissive phase.  The duration of the two permissive periods, and the time to start the second permissive period (displacement), will be selectable in each coordination pattern.

6.	Phase Reservice

a.	If actuated coordinated phases are in use, it shall be possible to reservice noncoordinated phases within the same cycle if sufficient time remains.  A phase shall be reserviced only if the permissive period for the phase indicates there is sufficient time remaining in the cycle to service the phase.

b.	Phase reservice shall be capable of being enabled/ disabled in each coordination pattern. 6.8. Transition Cycles

c.	The controller provides a smooth and orderly transition when changing from free operation to coordinated operation and from one coordination command to another.

d.	During a free to coordinated transition, the controller shall initiate a pick up cycle beginning upon receipt of a sync pulse and a valid coordination command.  The controller shall then enter coordination mode upon crossing a barrier or if resting in the coordinated phases.

e.	Each coordination command selects a pattern.  A command change implements concurrent with a sync pulse.  Cycle, offset, and split changes does not take effect until local zero.

7.	Crossing Artery Control

a.	The coordinator capable of implementing dual coordination at an intersection where two arterials are under control of separate masters.

b.	An external input enables dual coordination.  Once enabled, the coordinator places a continuous call on the crossing artery phases so as to ensure that these remain green for their full split interval.

c.	The coordinator outputs a crossing artery sync signal to indicate the beginning of the crossing artery phase split interval.

d.	Dual coordination forces a selectable crossing artery split plan to be used so as to allow a particular split to be optimized for dual coordination in each coordination pattern.

8.	Local Split Demand

a.	The coordinator provides a minimum of two split demand detector inputs that allow the selection of a preferred split plan based o n intersection demand.

b.	If the split demand detector indicates continuous vehicle presence during a programmed monitoring period beginning with the onset of a selected phase green, the coordinator forces a selectable split plan to be in effect during the next cycle.  This split plan remains in effect for a selected number of cycles from 0 - 255.  A specific split plan is capable of being selected in each coordination pattern.

9.	Adaptive Split Demand

The coordinator provides a method to select the split using measurement of each phase’s green utilization.  From the measurement, the coordinator determines which phase or phases had excess time that was not used during the last measurement period.  Then the excess time is added to the first set of preferential phases.  If the first set of preferential phases gapped out during the last measurement period, then the excess time will be added to a second set of preferential phases.  If both sets of preferential phases gapped out during the last measurement period then the time shall be added to the beginning of the coordinated phases.

10.	Free Mode

a.	The coordinator provides a free mode of operation, where coordination control is removed.

b.	Free mode operation is selectable by coordination commands, by external input or by keyboard entry.

c.	The coordinator reverts to the free mode when active controller inputs or functions would interfere with coordination.  Such inputs or functions include the following:

(1)	Manual control enable

(2)	Stop time

(3)	Automatic flash

(4)	Preemption

d.	The coordinator provides an active free mode, where coordination control is removed but the coordinator continues to monitor system sync so as to keep its timing in step with the system master.

11.	Manual Control

The controller allows manual override of the current coordination command from the keyboard.  The manual command allows selection of coordination patterns to be in effect.

12.	Interconnect Modes

a.	The coordinator capable of operating with any of the following interconnects types:

(1)	Non-interconnected coordination (time-based)

(2)	Telemetry

(3)	Hardwired

b.	The coordinator is compatible with fixed time interconnect that provides the sync pulse superimposed on the offset lines.  Also operates within an interconnected system using a separate sync line.  The noninterconnected coordination mode serves as a backup when using telemetry or hardwired interconnect.

13.	Master Coordinator

The coordinator shall output the coordination command, including sync pulse. This will permit the controller to be used as a time of day master in a hardwired interconnected system.

PREEMPTION

The controller shall provide a minimum of ten preemption sequences that can be programmed as either railroad-fire emergency or bus vehicle preemption sequences. Preemption capability standard and not requiring additional modules or software:

1.	Railroad-Fire-Emergency Vehicle Preemption

a.	The ten railroad fire emergency vehicle preemptors selectable as a priority or nonpriority Type.  Priority preemptor calls overriding nonpriority preemptor calls.  Low numbered priority preemptors overriding higher numbered priority preemptor calls.  Nonpriority preemptor calls serviced in the order received.

b.	Each preemptor providing a locking and nonlocking memory feature for preemptor calls.  If a preemptor is in the nonlocking mode and a call is received and dropped during the delay time, the preemptor is not serviced.

c.	Preemptor timing intervals programmable from 0 - 255 in one -second increments or 0 -25.5 in one - tenth second increments, depending on function.  Delay, max presence, and duration timing intervals programmed from 0 – 65535 seconds in one -second increments.

d.	A programmable delay time interval shall be provided to inhibit the start of the preemption sequence. This interval shall begin timing upon receipt of a preemption call. This time shall be programmable from 0 - 255 seconds in one second increments.

e.	An inhibit time shall be provided as the last portion of the delay time interval. During this time, phases that are not part of the preempt sequence shall be inhibited from service. This time shall be programmable from 0 - 65535 seconds in one second increments.

f.	A programmable extend input causing the preemptor to remain in the dwell interval following the removal of the preempt call.  If a preempt call is reapplied during this time, the preemptor shall revert to start of dwell interval.  This time is programmable from 0 - 25.5 seconds in one tenth second increments.

g.	A programmable duration time provided to control the minimum time that a preemptor remains active.  This time is programmable from 0 - 65535 seconds in one second increments.

h.	A programmable maximum time provided to control the maximum time that a preemptor input remains active and still be recognized by the controller.  Once failed, the input must return to inactive state to be recognized again.

i.	Phase timing at the beginning of a preemption sequence remains in effect for a minimum time before the controller advances to the next sequential interval.  If the phase has been timing for longer than the programmed preemptor minimum time, the controller shall immediately advance to the next sequential interval.  Minimum times shall be programmable for the following intervals:

(1)	Green/walk/pedestrian clearance

(2)	Yellow

(3)	Red

j.	A phase shall advance immediately to pedestrian clearance if it has been timing a WALK interval at the beginning of a preemption sequence.  It shall be possible to time the minimum pedestrian clearance through the yellow interval, or alternately to advance immediately to yellow.  During preemption, pedestrian indicators is selectable as being a solid DONT WALK, OFF (blank) or fully operational.

k.	If an overlap is in effect when the preemption sequence begins, it shall be possible to terminate the overlap so that it remains red for the remainder of the preemption sequence.  Overlaps terminating or forced to terminate shall time the preemptor minimum yellow and red clearance times.

l.	Each preemptor provides user programmable green, yellow, and red track clearance intervals.  Timing begins immediately after the preemptor minimum red interval.

m.	Up to four permissive phases selectable as track clearance phases.  During the track clearance period, the selected phases times the track clearance green, yellow and red intervals once, and then advance to the hold interval.  If track clearance phases are not selected the track clearance interval omitted from the preempt sequence and is the controller interval timing used if track clearance interval times have been programmed as zero.

n.	The preemption hold interval begins immediately after track clearance.  It remains in effect until the preemptor duration time and minimum hold times have elapsed and the preemptor call has been removed or the preemptor maximum time has been exceeded. During the preemption hold interval, any one of the following conditions shall be selectable:

(1)	Hold phase green

(2)	Limited phase service

(3)	All red

(4)	Flash

o.	Any valid phase, except a track clearance phase, selectable as a hold phase.  If hold phases are not selected, the controller remains in all red during the hold interval.  If flash is selected for the hold interval, up to two permissive phases shall be selectable to flash yellow, and the remaining phases shall flash red.  Overlaps associated with the phases flashing yellow also flashes yellow unless they have been forced to terminate, in which case flashes remain red.

p.	The preemptor shall immediately cause flashing operation if the preemption input and the track interlock input are not in opposite states and the track interlock function is enabled.

q.	Each preemptor provides a user programmable green, yellow, and red hold interval, during which the hold phase(s) shall operate normally, except that the minimum green interval time shall equal the hold green time.  At the completion of the hold green interval, the controller times the hold yellow and red clearance intervals before transfer to the exit phases.

r.	Up to four permissive exit phases will be selectable to time after the preemption sequence is completed serving as transition phases to return the controller to normal operation.  It shall also be possible to place calls on selected phases upon exiting preemption.  The option causes the preemptor to exit preemption to the correct phase to maintain coordination.

s.	Each preemptor provides a user programmable exit maximum time.  Upon exiting the preemption sequence, times shall serve as the maximum green time effective for one controller cycle for all phases except hold phases.

t.	Preemptor linking permits preemption sequences, where lower priority preemptors may call the higher priority preemptors from their preemption sequence.

u.	Preemptor active outputs provided for each of the preemptors.  The output sets to ON when the preemption sequence begins and remains ON for the duration of the sequence.  Possible to program preempt active outputs to be ON only during preempt hold intervals.  Additionally, it shall be possible to program the nonactive, nonpriority preemptor outputs to flash while another preemptor is active.

v.	Preemptors normally override automatic flash.  It will be possible to inhibit this feature for each preemptor.

2.	Bus Preemption

a.	Ten bus preemptors provide control for bus or other low priority vehicles.  Bus preemptors have low priority and are overridden by railroad/fire/emergency vehicle preemptor calls.

b.	The preemptor is programmed to accept either a 6.25 pulse per second signal with a 50% duty cycle or a solid input to identify a bus preemptor call.  Bus preemptor calls shall be capable of preemptor call memory and served in the order received.

c.	Bus preemptor timing intervals programmable from 0 - 255 in one second increments or 0 - 25.5 in one tenth second increments depending on the function.

d.	A reservice time provided to avoid excessive utilization of the same bus preemptor.  If a call is received before the reservice time has elapsed, the bus preemptor shall not be reserviced.  If reservice time has not been entered then all phases with a call when leaving the bus preemption sequence shall be serviced before the bus preemptor may be served again.

e.	Bus preemptors shall provide delay, inhibit, and maximum time functions similar to those for railroad/fire/emergency vehicle preemptors described above.

f.	Bus preemptors shall provide the following entrance intervals:

(1)	Green/walk/pedestrian clearance

(2)	Yellow

(3)	Red

g.	At the completion of the entrance red clearance, the bus preemptor shall advance to the hold green interval.  During this interval, up to four permissive phases shall be selectable to remain green until the minimum hold time has elapsed and the bus preemptor call has been removed or the preemptor maximum time has been exceeded.

h.	It shall be possible to program the controller to allow concurrent phases to be serviced for a bus preemptor with only one phase selected as the hold interval phase.

3.	Preemption Safeguards

a.	If a preemptor call is active when power is restored to a controller, the fault/voltage monitor output shall be set to FALSE, placing the intersection in flash.  Similarly, if external start is applied during a preemption sequence, the intersection shall be set to flash.  Intersection flash shall remain in effect until the preemptor call has been removed and the preemptor duration time has elapsed.

b.	An input provided to stop timing of the current active preemptor under control of the MMU/CMU.

c.	A preemptor safety interlock provided to cause the intersection to go into flash whenever the controller has been removed or has not been programmed for preemption.  This is achieved with an appropriate signal to the MMU/CMU.

4.	Transit Signal Priority

a.	The controller includes a transit signal priority algorithm that provides for transit vehicle movement through the intersection, while not interrupting coordination or skipping phases.

b.	Provide a check in detector input that senses the arrival of the transit vehicle.  When active this input initiates Transit Signal Priority (TSP).

c.	A TSP delay shall delay the beginning of TSP operation until a set interval after check in. 7.4.4. A check out detector input shall determine the departure of the transit vehicle.

d.	Assignment of a single pulse from the check in detector and check out detector to the controller inputs programmable to any controller input.  Including, inputs from devices that continuously pulse (pulsing as long as the vehicle requires TSP) through EVP 1 - 4, for a controller with a C1 connector, or through Preemptor inputs 3 – 6, on a controller with an MSD connector.

e.	When under coordination the TSP sequence shall use alternate split times to accommodate transit vehicles while maintaining coordination.

f.	When under free operation the TSP sequence uses alternate maximum times to accommodate transit vehicle while not skipping phase.

TIME-BASED CONTROL & NON-INTERCONNECTED COORDINATION

The controller shall include time based control.  This capability is a standard feature and shall not require additional modules or software.

1.	Clock/Calendar Functions

a.	The controller shall provide a time of day (TOD) clock that is used for all time based control functions.  The only required clock settings are the current time (hour, minute and second) and date (month, day and year).  Day of week and week of year are automatically computed from the date setting.  Also possible to set the number of hours that the local standard time is ahead or behind Greenwich Mean Time.

b.	During normal operation, the TOD clock shall use the power line frequency as its time base.  When power is removed, a crystal oscillator maintains the time for up to 30 days.  The oscillator has a timing accuracy of +/ - 0.005% over the entire NEMA temperature range as compared to the Universal Coordinated Time Standard.

c.	In addition to entering time and date via the keyboard, it is possible to download the information from another controller, a computer, or a system master.

d.	The controller includes a time reset input.  This feature resets the TOD clock to 03:30 whenever the time reset input is TRUE.

e.	The TOD clock automatically compensates for leap year and shall be programmable to automatically switch to daylight savings time.

2.	Time Based Control

a.	Time based control utilizes a day plan program format.  The month program consists of 200 programmable schedules, each assignable to one of sixteen day programs.  Each day program consists of from 1 to 50 program steps that define a program for the entire day.  Each program step is programmed with a starting time and an action plan number.  The day plans are also assigned to days of the week and days of the month.

b.	Time based control shall use action plans to assign:

(1)	Coordination pattern number

(2)	Vehicle detector plan number

(3)	Controller sequence

(4)	Timing plan

(5)	Vehicle detector diagnostic plan

(6)	Pedestrian detector diagnostic plan

c.	Time based control shall also use action plans to enable:

(1)	Automatic flash

(2)	System override

(3)	Detector log

(4)	Dimming

(5)	Special functions

(6)	Auxiliary functions

(7)	By-Phase functions

(a)	Pedestrian recall - Walk 2 enable

(b)	Vehicle extension 2 enable

(c)	Vehicle recall

(d)	Vehicle max recall

(e)	Max 2 enable - Max 3 enable

(f)	Conditional service inhibit

(g)	Phase omit

d.	A minimum of 36 holiday or exception day programs that override the normal day program.  Holiday programs capable of being set as floating (occurs on a specific day and week of the month) or fixed (occurs on a specific day of the year) and, possible to program a fixed holiday so that it automatically repeats in the following year.

e.	Possible to manually force any of the action plans to override the current action plan. The forced plan entered from the keyboard and remains in effect until removed.

3.	Non-Interconnected Coordination

a.	A minimum of 200 time base schedule programs shall be available for the day-programs.  These shall not have to be entered in any special sequence.  It shall be possible to add and delete steps from a day program without affecting any other day-program.  Each of the program steps shall permit selection of the following functions:

(1)	Day program assignment

(2)	Start time

(3)	Action plan

b.	Selection of system override in an action plan allows the coordination pattern selected by the action plan to override the current telemetry or hardwire system commanded coordination pattern.

c.	When operating in the noninterconnected coordination mode the synchronization point for cycles references to a user selected reference time (sync reference), last event or last sync as selected from the keyboard.  The sync reference time is that time at that cycles are reset to zero.

d.	If the sync reference time is selected, the synchronization point for the cycle selected by the current program step is computed using the present time, sync reference time, and cycle length.  The synchronization point occurs whenever the present time is an even number of cycle length periods has occurred since the sync reference time.

DETECTORS

1.	Detector Functions

The controller provides a minimum of 64 vehicle detector inputs.  Each input is assignable to any phase and programmable as to detector function.  Extend and delay timing is provided for each detector.  Each detector is capable of operating in a lock or nonlock mode.  The controller is capable of providing 16 pedestrian detector inputs. Each pedestrian detector shall be assignable to any phase.

2.	Detector Cross Switching

The controller provides detector cross switching that permits vehicle detectors to alternately place calls on assigned phases and assigned cross switch phases.  If the assigned phase is not green and the cross - switch phase is green, the detector places calls on the cross switch phase. If the assigned phase is omitted, for any reason, the detector places calls on the cross switch phase.

3.	Detector Types

Each vehicle detector is user programmable to operate as one of the following 3 detector types:

Type 0 (zero): supports all NTCIP or standard detector functionality.

Type 1:	(GREEN DELAY) The first detection received when the phase goes green is recognized immediately, whether the detector is active when green starts or is activated after the green is timing.  Detections received before the first timeout of the extension interval are also recognized immediately.  Once the detector extension interval (not the phase extension interval) times out, further detector inputs are recognized only if continuously present for a period equal to the programmed delay time AND the delayed signal is NOT extended.  The first detection received when the phase goes green, whether present when green starts or received later, is recognized immediately. Detections received before the first timeout of the extension interval are also recognized immediately.  Once the detector extension interval (not the phase extension interval) times out, further detector inputs are recognized only if continuously present for a period equal to the programmed delay time AND the delayed signal is NOT extended.

Type 2:	(STOP BAR WITH EXTEND TIME AND RESET) The detector input must be true when assigned phase green starts else the detector is disconnected for the balance of phase green.  If the detector input is true when phase green starts the extension timer is reset while the input remains true.  When the detector input is removed the extension timer begins running.  If another detector input is received before extension time expires, the extension timer is reset for the duration of the input and once again begins timing when the input goes false.  This action is repeated until the extension timer times out, at which time it is disconnected for the balance of phase green.

4.	System Detectors

a.	Each detector input shall be capable of functioning as one of 16 system detectors.

b.	Vehicle detectors shall be capable of being assigned to a minimum of 16 speed detectors.  Speed shall be detected using both one and two detector configurations. Speed shall be computed using a keyboard entered average vehicle length and loop length for a one detector configuration.  When using two detectors, speed shall be calculated using a keyboard entered distance between detectors and travel time between detectors.

SYSTEM COMMUNICATION

1.	On-Street Master Communications

The controller is capable of communicating with an on street system master. This capability provided by a separate telemetry module that is included in the controller when required by the plans and specifications.  The telemetry module receives system master commands and data transmissions.  In addition, it transmits the controller status, data base and system detector information to the system master.

2.	System Commands

a.	The telemetry module allows the controller to receive, as a minimum, the following commands:

(1)	Cycle, offset, and split (coordination pattern)

(2)	System sync

(3)	Special function commands (minimum of four)

(4)	Free and flash mode commands

(5)	Time and date

(6)	Request for local status

(7)	Recall to Max

b.	Commands must occur more than once in any three second period in order to be recognized.

c.	Mode and special function commands cleared after 20 minutes of loss of communication between controller and system master.

d.	Status Data – The status of each of the following functions shall be transmitted to the system master in response to a local status request:

(1)	Green and yellow status for all phases and overlaps

(2)	Walk and pedestrian clearance status for all phases

(3)	Vehicle and pedestrian detector status

(4)	Phase termination status

(5)	Local time

(6)	Coordination status

(7)	Command source

(8)	Sync or transitioning status of coordinator

(9)	Conflict flash status

(10)	Local flash status

(11)	Preempt activity and calls

(12)	Volume and occupancy data from a minimum of 16 system detectors

(13)	Speed data from a minimum of two speed detectors

(14)	Maintenance required (cabinet door open) status

(15)	Status of two user -defined alarms

e.	Split Reporting – The status of each of the following parameters calculated on a per-cycle basis and transmitted to the system master:

(1)	Actual time spent in each phase

(2)	Time of day at end of cycle

(3)	Phases forced off during cycle

(4)	Type of coordination operation

(5)	Whether transitioning to new offset

(6)	Cycle, offset, and split in effect during last cycle

(7)	Flash status if operation is Free

f.	Upload/Download Capability – The telemetry module provides the capability to upload/download the entire intersection database.  Phase assignments for overlaps and preemptors are not to be downloaded to preclude unsafe controller operation.  It is possible to inhibit downloading of phases in use and left turn head control.  Data transfer shall not require the intersection to be in flash.

3.	Telemetry

a.	Telemetry shall utilize TDM/FSK data transmission from 1200 baud to 9600 baud over two pairs of wires. These may be leased lines (Type 3002, voice grade, unconditioned) or dedicated cable. Optional fiber optic communications capability shall also be available.

b.	The nominal transmitter output level shall be 0 dBm into a 600 ohm load.  The receiver sensitivity shall be -34 dBm and adjustable from -40 to +6 dBm.

c.	Parity and error checking employed to assure transmission and reception of valid data.  Indicators provided on the telemetry module to show telemetry activity as follows: transmit, receive carrier, and valid data.

d.	In the event of a telemetry failure, the controller shall revert to the noninterconnected coordination mode after it has self synchronized for a number of cycles, which shall be selectable from 0 -255.

4.	Communications Protocols

The controller has the capability of supporting communications with traffic management systems using industry standard protocols with the installation of appropriate optional software.  At a minimum the controller has optional software to support the following protocols:

(1)	CalTrans AB3418

(2)	ECPIP

(3)	NTCIP

Level 2 as defined by Section 3.3.6 of NEMA TS2 - 2003. NTCIP v02.06 capabilities shall include for NTCIP mandatory and optional objects.  The controller vendor provides access to controller data via vendor specific objects.  These and other objects supported by the controller are defined in a standard MIB file.

5.	Ethernet Communications

The controller has the capability of supporting communications through Ethernet.  This communications uses internal circuitry.  The Ethernet port supports auto sensing of 10/100 Base T and half or full duplex operation.

6.	External Clock

The controller has the capability of communicating with an external clock like a GPS or WWV clock in order to set its internal time of day clock.

7.	Communications Ports

a.	The controller have as a minimum the following internal communications ports:

(1)	Port 1. SDLC for communications to other devices in the cabinet

(2)	Port 2 Terminal port for communications with a computer for the purposes of uploading, downloading or upgrading the controller software

(3)	Port 3 Systems communications port.  This port provides either communicate to an on -street master or a central computer system

(4)	An option circuit board is available to expand communications by adding two additional serial communications ports

b.	Serial communications shall operate at 1200 to 115.2 K baud

DIAGNOSTICS

1.	General Diagnostics Features

a.	The controller includes both automatic and operator initiated diagnostics.  This capability is a standard feature and shall not require additional modules or software.

b.	Automatic diagnostics verifies memory, MMU compatibility programming, and microprocessor operation each time power is reapplied to the controller.  After power has been applied, diagnostics continually verify the operation of essential elements of the controller including at a minimum: PROM, EE PROM, communications, and the microprocessor.

c.	Operator initiated diagnostics allows the operator to verify proper operation of controller input, output, communications, keyboard, and display functions.  Both manual and automatic test modes are provided.

2.	Detector Diagnostics

a.	Time of day controlled detector diagnostics provided to allow testing vehicle and pedestrian detectors for no activity, maximum presence, and erratic output.

b.	A minimum of eight detector diagnostic plans provided.  These plans shall be selectable on a time-of-day basis.  This allows varying the detector diagnostic intervals to correspond with changes in detector activity.

c.	If a detector is diagnosed as failed, the associated phase is placed in one of the following keyboard selectable modes:

(1)	Detector fail recall from 1 to 255 seconds

(2)	Maximum Recall

(3)	Disable the detector from calling or extending.

d.	Diagnostics for NEMA TS2 detectors connected to the controller using a Bus Interface Unit (BIU) shall also include detection of watchdog, open and shorted loop, and excessive inductance change failures.

LOGGING

The controller shall be capable of logging and reporting detector activity, detector failures, and the occurrence of selected events or alarms.  Logs shall be capable of being printed or displayed on the front of the controller.

1.	Detector Logging

a.	The controller includes a detector log buffer capable of logging volume, occupancy and average speed for selected vehicle and speed detectors.

b.	The detector logging interval has keyboard selectable as 5, 15, 30, or 60 minutes.

c.	Detector logging is capable of being enabled or disabled by time of day.

2.	Detector Failure Logging

a.	12.2.1. The controller includes a detector failure log buffer capable of storing a minimum of 100 time and date stamped detector failure events.  Once logged, detector failure events remains in the log until cleared or the log buffer capacity is exceeded at which time the oldest detector failure events shall be overwritten.

b.	12.2.2. Detector diagnostic failures are recorded in the detector failure log including: no activity, maximum presence, erratic output, watchdog failure, open loop, shorted loop, and excessive inductance change.  If a detector recovers after a diagnostic failure, a detector on -line event shall be stored in the detector failure log.

c.	12.2.3. Detector failure logging shall be capable of being disabled.

3.	Event Logging

a.	The controller includes an event log buffer capable of storing a minimum of 200 time and date stamped events or alarms.  Once logged, events remains in the buffer until cleared or the log buffer capacity is exceeded at which time the oldest events shall be overwritten.

b.	At a minimum the following events logged: communication failures, coordination faults, MMU and local flash status, preempt, power ON/OFF, low battery, and status of a minimum of two alarm inputs, and an on line event logged when an event or alarm returns to normal status.

c.	If security is enabled, an event logged when a user enters a data change.  This event includes the user’s ID.  It is necessary to log the first change only and not every change.  Also an entry is recorded when a user logs in and out of the controller.

d.	Event logging shall be capable of being enabled or disabled for each category of event or alarm.

4.	OE logging

a.	The controller accumulates phase utilization data, phase termination data, and detector data for a number of cycles selectable by the operator.

b.	The MOE log includes the number of gap outs, force offs and max outs per phase.

c.	The MOE log includes the mode of operation and phase utilization.  If the controller is operating under coordination, the log shall include the pattern in effect and the average phase split for each period.  If the controller is operating free, the log shall include the timing plan (1 – 4), the maximum in effect and the average phase maximum for each period.

d.	Each logged period includes the volume, number of stops and the delay per phase.

e.	Each log period records the number of times a phase was skipped and the number of times walk was served per phase.

EMULATION

1.	Emulation Software.  With each controller provide software designed to emulate the controller.  The emulation software shall employ the full functionality of the controller including but not limited to;

Configuration, timing, coordination, preemption, time base, detector setup, status display, utilities including special logic and diagnostic information.  The software shall employ a graphical user interface that looks and acts like the controller.  The software shall be designed to operate on the latest Microsoft Windows operating system and be capable of direct interface with the latest version of Transoft Synchro traffic modeling software.

Replace Subsection 740-2.11 with the following:

740-2.11 CONTROLLER CABINET. Provide a controller cabinet that meets the requirements of NEMA Standard TS 2-2003 V02.06 Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2), Section 5 Terminals and Facilities and Section 7 Cabinets. Cabinet enclosure shall be UL listed.

1.	Standard Features. Supply the following standard features:

a.	Materials

Unless otherwise designated in the Plans, provide cabinets constructed of sheet Aluminum.

b.	Cabinet Dimensions

Unless otherwise designated in the Plans, provide a size 6 cabinet as defined in NEMA TS-2 Table 7-1.

c.	Doors

(1)	The cabinet shall be equipped with a universal lock bracket capable of accepting a Best CX series lock. The cabinet shall come equipped with a Best blue construction core lock. Provide two keys for lock.

(2)	Provide a Police Compartment meeting the requirements of NEMA TS-2 Section 7.5.7.  Provide two keys for lock. The Police Compartment shall house the following switches:

(a)	"flash/automatic" switches that when placed in the "flash" position causes the intersection displays to go into the flashing mode.  When placed in the "automatic" position, the signal system must resume normal operation.

(b)	"signals on/off" switch that when placed in the "off" position removes power from the signal bus.  Do not allow power on the bus when either "automatic" or "flash" operation is selected by any means.

(3)	Permanently label switches in the Police Compartment.

d.	Shelves

Provide shelves meeting the requirements of NEMA TS-2 Section 7.6. Provide additional laptop computer shelf mounted approximately 42" above ground level.  The laptop shelf must accommodate a standard 17" computer, be retractable below one of the cabinets’ shelves, and contain a storage drawer.

e.	Finish and Preparation

The cabinet shall be powder-coated grey on the outside and white on the inside. All exterior seams shall be manufactured with a neatly formed continuously weld construction. The weld for the police box door shall be done on the inside of the cabinet door. All welds shall be free from burrs, cracks, blowholes or other irregularities.

f.	Cabinet Mounting

(1)	Provide cabinet mounting features as defined NEMA TS-2 Section 7.8.

(2)	The cabinet manufacturer is responsible for providing a cabinet that will mount without modification on the foundation detailed in Alaska Department of Transportation Central Region, Regional Detail, Controller Cabinet Foundation.

g.	Cabinet Ventilation

Furnish a cabinet that fully meets the requirements of NEMA TS-2 Section 7.9 and the following:

(1)	Furnish the fan and cabinet vent with internally mounted metal covers that are fabricated to close off the flow of air during winter operation.

(2)	Equip the cabinet with a selectable, 600/900/1500 watt cabinet heating device with a 2 speed fan.  The heating device must have a remote air sensing thermostat. The contacts must be rated 20 amps, 120 volts, 60 hertz. Heating device to be mounted on inside of the cabinet door, below the control panel. Heating device shall be a Caframo model 9206CA-BBX or approved equivalent.

(a)	Construct the thermostat so that contacts close on descending temperature and are adjustable between -30 and 110 °F ±5 °F. The contacts must open on rising temperatures of 15 °F above the closing temperature.  The adjustment must have an indicating pointer. Remote bulb type thermostat shall not be used. Thermostat shall be a Johnson Controls model A19BBC-2C or approved equivalent.

(b)	Connect the thermostat in series with an electrical resistance heater and blower fan.  The blower fan must be rated for continuous duty.  The heater and fan must be connected in parallel and rated 120 volts, 60 Hertz.  Mount the unit in the vertical position on the cabinet door beneath the auxiliary "goose neck" cabinet light.  The thermostat shall be mounted immediately to the left of the heating device on the cabinet door.

(c)	Do not block the air intake or outlet.  Provide the unit with a SPST manual override switch that bypasses the thermostat to enable the fan and heater to operate at warmer temperatures.

h.	Auxiliary Cabinet Equipment

(1)	Light fixture.  The cabinet light fixture shall be an incandescent type porcelain lamp holder rated for 660W-250V AC/CA. The lamp shall be 110W.  The lighting fixture “ON-OFF” switch must be a toggle switch mounted on the on the inside control panel.  Include in the circuit a door actuated switch that turns the light ON when the door is open and OFF when the door is closed.

(2)	Provide three (3) paper sets of complete and accurate cabinet drawings with each cabinet.  Make cabinet drawings available electronically in AutoCAD v2004 or later format and deliver with paper set.

(3)	Provide one paper set of manuals for the controller, Malfunction Management Unit and vehicle detector amplifiers with each cabinet. Make said manuals available in electronic Adobe "pdf" format and deliver with paper set.

i.	Cabinet Wiring

Neatly arrange the wiring within controller cabinets to conform to the requirements of Subsections 660-3.05 and 740-2.05.  Furnish controller cabinets wired to accommodate

(1)	Configuration #4 in Table 5-2 of the NEMA Standards Publications No. TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP requirements with four each Type 2 detector racks.

(a)	Equip the cabinet with required control and auxiliary equipment connecting cables to operate the phases and detection indicated on the Plans, including future use with a minimum of 16 load switch positions, 8 flash transfer relay position and 1 flasher socket.

(b)	Size wiring, switches, surge protectors, flash relays, and flashers to handle the necessary amperage required under full cabinet use.  Use orange colored wires to run from the flash transfer relay used for emergency flash programming.

(c)	Wire the cabinet to accommodate 6 unique preempt sequences as defined by NEMA TS-2 Section 3.7 and 2 auxiliary preempt sequences.  Configure each detector rack to accommodate 4 unique sequences.

(d) Wire the cabinet with terminals and wiring to accommodate the full quantity of emergency preemption inputs available with GTT Company’s Opticom Priority Control System 75x series phase selector.

(e) Wire the cabinet so that the control panel’s momentary contact test switches for vehicle calls Phase 1-8 are wired to Detector rack Channels 1-8 respectively.

(f)	Wire the cabinet so that each inductive loop detector channel input termination has three adjacent screw terminal positions provide, so that two loops can be series terminated for each individual detector channel.

j.	Field Terminal Blocks

Provide Terminals and Facilities meeting the requirements of NEMA TS-2 Section 5, Configuration #4 (Table 5-2) and the following:

(1)	Provide 2 or more insulated terminal blocks to terminate field conductors.  Provide each block with 12 poles with 10-32 screw type terminals.  Use a terminal block that is a barrier type with removable shorting bars in each of the 12 positions and with integral type marking strips.  Terminate conductors to a terminal block. The load-bay shall have two rows of field terminals tied together in series. Each channel shall have 6 terminals, two complete rows each consisting of 3 terminations from left to right beginning with phase 1 corresponding to the appropriate vehicle phase Green, Yellow, and Red and following the order of the load switches. Field terminals shall be #10 screw terminal and be rated for 600V.

(2)	Terminate conductors from the controller unit and mmu unit in ring type terminal lugs or solder them to a through panel solder lug on the rear side of the terminal.  Terminate other conductors in spade type terminal lugs.

(3)	Do not bring more than 3 conductors to any one terminal.  Two flat metal jumpers, straight or U shaped, may also be placed under a terminal screw.  Fully engage at least 2 full threads of terminal screws when the screw is tightened.  Do not extend live parts beyond the barrier.

(4)	 A Type 66 B3-50 terminal block shall be installed for telemetry cable terminations.

(5)	On the right side of controller cabinets, install two 16 position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets.  On the left side of the controller cabinets, install two 32 position bus bars, for terminating the equipment grounding and neutral conductors from field wiring.

k.	Cabinet Accessories

See NEMA Standard TS 2-2003 V02.06, Section 5 Terminals and Facilities, Figure 5-4 Cabinet Power Distribution Schematic for Items (1) through (6).

(1)	Disconnecting Means

(a)	Main circuit breaker must be a single pole, 50 ampere, 10,000 amperes interrupting capacity for each cabinet.

(b)	Provide a minimum of 2 Auxiliary circuit breakers, each must be single pole, 20 ampere, 10,000 amperes interrupting capacity to protect fan, heater, light, and convenience outlet(s). One auxiliary circuit breaker shall only service a single outlet receptacle for exclusive use for the cabinet heater.

The rating of the main disconnect means with overcurrent protection must be not less than 125% of the maximum anticipated continuous load.  When using disconnecting circuit breakers, use "trip indicating trip free," Type.

(2)	Signal Bus.  Connect the signal bus to the incoming AC line through a signal bus mercury contactor and an overcurrent protection device.  Energize the signal bus mercury contactor to provide power to the signal bus.  The current rating of the signal bus mercury contactor must be at least the current rating of the main overcurrent protection device.

(3)	AC Service Transient Suppression.  Connect the transient suppression device for the primary feed of the cabinet on the load side of the cabinet overcurrent protection device.  The transient voltage suppression device connected to the controller power circuit must provide protection against voltage abnormalities of 1 cycle or less duration.

(a)	The suppressor must be solid state high energy circuit containing no spark gap, gas tube, or crow bar component.  The current rating of the device must be 15 amps minimum.  The device must provide transient protection between neutral and ground, line and ground, as well as line and neutral.  If the protection circuits fail, they must fail to an open circuit condition.  The device must meet requirements of UL Standard 1449.

(b)	The suppressed voltage rating must be 600 volts or less when subject to an impulse of 6,000 volt, 3,000 amp source impedance, 8.0/20 microsecond waveform as described in UL Standard 1449.  In addition, the device must withstand, without failure or permanent damage, one full cycle at 264 volts RMS.

(c)	The device must contain circuitry to prevent self induced regenerative ringing.  There must be a failure warning indicator light that must illuminate when the device has failed and is no longer operable.  The transient suppression device must withstand a 20,000 ampere surge current with an 8x20 microsecond (time to crest x time to second halfcrest) waveform 20 times at 3 minute intervals between surges without damage or degradation to the suppressor.  Output voltage must not exceed 500 volts at any time during the test.  Use a device that is a solid state, high energy circuit with no spark gap, gas tube, or bar component.

(4)	Radio Interference Suppression.  Equip each traffic cabinet, flasher, and other current interrupting device with a suitable radio interference suppressor installed at the input power point.  Install the radio interference suppressor after the AC service transient suppression unit described in Subsection 740-2.11.1.k (3).  It must provide a minimum attenuation of 50 decibels over a frequency range from 200 kilohertz to 75 megahertz, when used with normal installations.

(a)	The interference suppressor must be hermetically sealed in a substantial metal case filled with suitable insulating compound. Terminals must be nickel plated, 10-24 brass studs of sufficient external length to provide space for connecting two No. 8 conductors and must be so mounted that the terminals cannot be turned in the case.  Ungrounded terminals must be properly insulated from each other and must maintain a surface leakage distance of not less than 1/4 inch between any exposed current conductor and any other metallic part, with an insulation factor of 100 to 200 megohms dependent on external circuit conditions.

(b)	The radio interference suppressor must have a minimum current rating equal to the rating of the main disconnect means as specified in Subsection 740-2.11.1.k (1) (a).  It must be designed for operation on 120 volts, 60 hertz, single phase circuits and be UL and EIA compliant.

(c)	Connect the ground connection of the radio interference suppressor only to AC neutral.  Do not connect to Earth Ground directly.

(5)	Communications Transient Suppression.  Provide a transient suppressor for the system interface communications lines when used.  This suppressor must withstand a 100 ampere 10 x 700 microsecond waveform 20 times at 30 second intervals between surges without damage or degradation to the suppressor.  Apply the transient surge both line to line and line to ground. Output voltage must not exceed 8 volts line to line and line to ground.  Output voltage must not exceed 8 volts line to line or 250 volts line to ground at any time during the test.

(6)	Control Panel.  Provide and label a control panel assembly that is readily accessible from the front of the cabinet. The control panel assembly must consist of:

(a)	"controller power" switch to energize the controller while the signal lights are off or are being operated by the flasher.  Label and rate the switch for load current.

(b)	“cabinet light”  “ON-OFF” switch.

(c)	"auto/flash" switch that when placed in the "flash" position provides flashing operation without interrupting the controller unit power. When the switch is placed in the "auto" position the controller unit must provide normal operation.

(d)	"stop time/off/on" switch that when placed in the "ON" position causes the controller unit to stop time.  In the "off" position, the controller unit must be active regardless of external commands.  In the "AUTO" position, the timing must be normal but subject to external command interruptions.

(e)	"heater by-pass" switch to bypass the remote heater thermostat.

(f)	momentary contact test switches to place calls on each vehicle and pedestrian phase.  Switches must provide tactile feedback and be rated at 1 ampere, minimum, for a resistive load at 120 VAC and at 28 VDC.  Contacts must be coin silver or gold plated and be enclosed and labeled as to their function.

(g) Provide a hinged clear plastic cover over the control panel switches.

(7)	Receptacle Outlets.  The cabinet shall be wired with one duplex outlet with a ground fault interrupter, one convenience duplex outlet without ground fault interrupters and one single outlet, exclusively for the heating device without ground fault interrupter. The ground fault outlet shall be mounted on the right side of the cabinet on or near the power panel.  The one convenience outlet shall be near the top shelf. The heater outlet shall be mounted on the right side of the cabinet on or near the power panel. No outlets shall be mounted on the door.  The GFI power shall be fed through the auxiliary breaker. The convenience outlet shall power shall be fed through an EDCO SHP300-10 transient voltage suppressor located on the cabinet power panel.

2.	Special Features. Provide the following.

Coordination "Remote/Time of Day/Free" Switch.  When the switch is in the "Remote" position, supervisory functions performed on the controller unit from a master coordinator or central computer must operate normally.

When the switch is in the "Time of Day" position, the local controller must use the local coordinators time of day plan.  When the switch is in the "Free" position, it must be possible to remove any or all coordination devices and maintain normal, non-coordinated controller operation without wire jumpers, jumper plugs or other special devices.  Provide this switch if a local coordination or system modem/interface unit is shown on the Plans.

“Force-Off” Switch There shall be 2 momentary test switches tied to ring 1 and ring 2 on the controller. These switches shall have two positions labeled “On” which shall force the controller into the next ring in the phase sequence, “Off” which shall be normal operation. These switches shall be labeled Ring 1 and 2.

Replace Subsection 740-2.12 with the following:

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

1.	Three Circuit Solid State Load Switches.  The cabinet shall come with (16) load switches. All load switches shall be cube type and have LED indications for both the input and output side of the load. The load switches shall be PDC model SSS87I/O or approved equivalent.

2.	Solid State Flasher.  The cabinet shall come with (1) flasher. The flasher shall be cube type and have LED indications. The flasher shall be PDC model SSF87 or approved equivalent.

3.	Malfunction Management Unit (MMU).  The cabinet shall come with a (MMU) that meets all the requirements of NEMA TS2-2003 while remaining downward compatible with NEMA TS1. It shall have (2) high contrast LCD displays and an internal diagnostic wizard. It shall come with a 10/100 ethernet port. It shall come with software to run flashing yellow arrow operation. The MMU shall be an Eberle Design, Inc. model MMU-16LEip or approved equivalent.

4.	Flash Transfer Relay.  The cabinet shall come with (8) heavy duty flash transfer relays. The flash transfer relays. The relays shall be Detrol Controls model 295 or approved equivalent.

Replace Subsection 740-2.13 with the following:

740-2.13 SPECIAL AUXILIARY EQUIPMENT. Provide equipment listed under Items No. 1-5 with all controller cabinets. Provide equipment listed under Item No.6 only when called for in Plans or Special Provisions.

Provide equipment meeting the requirements of the cited Sections of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

1.	Inductive Loop Detectors Units. Provide (16) inductive loop detectors that conform to the requirements of NEMA TS-2, Section 6.5 Inductive Loop Detector Units.  Unless otherwise called for in the Plans provide 4 Channel Inductive Loop Detectors with audible feedback of detection events.  The audible feature must be manually switchable between audible "on" and silent "off."

2.	Local Coordination Units. Provide actuated coordination that conforms to the requirements of NEMA TS-2, Section 3.6 Actuated Coordination.

3.	System Modem/Interface Unit.  The cabinet shall come with an 8 port copper ethernet switch. Four ports of 10/100TX and an optional 1000base SFP port. The ethernet switch shall support all of the following minimum requirements; EFMplus technology, virtual local area networks (VLAN) tagging (IEEE 802.1q) and dynamic bridging (IEEE 802.1). The copper ethernet device shall provide for communication over copper pairs split into two directions and the high speed link shall be over bonded copper pairs (IEEE 802.3ah 2Base-TRL). The copper ethernet switch shall be an Actelis Networks model ML688 or approved equivalent. The following module, cables, and cords shall be supplied with the copper ethernet switch:

- Two quad DSL cables 504R20110

- One AC power adapter 506R00005

- Four Cat6 patch cables five feet

- One 100Base-FX SFP module

- Four LC connector simplex fiber optical cable assemblies.  Length = 2 meters.

4.	Preemption Units. Provide preemption that conforms to the requirements of NEMA TS-2, Section 3.7 Preemption and the following:

Install the following components of the GTT Company’s Opticom Priority Control System according to GTT’s written installation instructions at the signalized intersections listed on the Plans.

a.	The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted "GTT OPTICOM Emitter" has been received and maintained for a period of 1.7 seconds.

b.	Use Opticom Priority Control System Model 792H emitters.

c.	Unless otherwise shown on the Plan use Opticom Traffic Control Systems Opticom Detector Model 721 preemption detectors.

d.	Furnish the appropriate number of Opticom Traffic Control Systems 764 Phase Selectors to meet the number of channels of detection for each intersection.  Use rack mounted phase selectors.

e.	When more than one detector is required per phase, furnish the appropriate number of harnesses for the 764 Phase Selectors to handle the auxiliary detection.

f.	Install Model 138 Optical detector lead in cable between the end of each signal mast arm and the controller cabinet.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

g.	The controller, rather than the phase selector or auxiliary logic, must perform interval timing, signal sequences, and phase skips.

h.	Mount detectors according to manufacturer recommendations or as approved by the Engineer.  Mount and aim detectors to provide maximum emergency vehicle recognition.  Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

i.	When emitters are required, provide GTT Opticom Priority Control System, Model 792H Emitter with 793 in vehicle switch.  The Emitter shall be factory programmed to the class and vehicle identification numbers assigned by jurisdiction as shown in the Plans and the following:

(1)	Class 0 and Vehicle ID. Number 0 (Zero) shall be disabled for Emitters.

(2)	Vehicle Id. Numbers shall be sequential, beginning with the lowest number in the EVP Emitter table for the appropriate class.

(3)	Provide one copy of 790IS Emitter Software Kit including "Y" cable.

(4)	One GTT Opticom Portable Emitter Kit with 792R emitter on a magnetic base, 793R switch and cigarette lighter adapter power cord in a "Camera Bag" case.

5.	Bus Interface Unit (BIU).  Provide six BIU’s that fully meet the requirements of NEMA TS-2 Section 8.  Unless otherwise called for in the Plans provide BIU’s that meet the NEMA designation BIU2.

6.	Video Detection System.

a.	General.

(1)	System Hardware. Use machine vision system hardware consisting of the following components:

(a)	Color Machine Vision Processor (MVP) sensors as shown in the Plans

(b)	Terra Access Point (TAP)

(c)	Communication interface panel

(d)	Personal computer (PC)

The PC shall host the server and client applications that are used to program and monitor the other system components.  The MVP sensor shall be an integrated color zoom camera and processor that perform real-time traffic detection. Each MVP sensor shall be programmable with a minimum of twenty detection zones to satisfy the traffic detection needs of a variety of simple to complex traffic applications.  The detection zones shall be user-defined though interactive graphics software running on a PC.  The detection zones and the associated traffic functions and alarms shall be downloaded to the MVP for operation.  The real-time performance shall be observed by viewing the video output from the sensor with overlaid flashing detector’s to indicate the current detection state (on/off).  Subsequent redefinition of detection zones shall be permitted for rapid reconfiguration of fine-tuning detection performance.  The MVP sensor shall calculate detector states in real-time and communicate the detection information to the TAP that subsequently translates the detection state directly to a traffic signal controller in real time.  The MVP sensor shall optionally store cumulative traffic statistics, internally in non-volatile memory, for later retrieval and analysis.

The MVP shall communicate to the Terra access Point, communications panel and the software applications using the industry standard TCP/IP network protocol.  The MVP shall have a built in Internet Protocol (IP) address and shall be addressable with no plug in devices or converters required.

The Terra Access Point shall communicate directly with up to eight (8) MVP sensors and shall comply with the form factor and electrical characteristics to plug directly into a NEMA Type C or D detector rack providing up to thirty-two (32) inputs and sixty-four (64) outputs directly with a TS2 Type traffic signal controller.

The communication interface panel shall be hardwired into a traffic signal cabinet or junction box.  The communication interface panel shall be a Eight-sensor model and provide the electrical termination of wiring for video, data, and power for the MVP.

The communication interface panel shall provide high-energy transient protection to electrically protect the Terra Access Point and connected MVP sensors.

(2)	System Software. The MVP sensor embedded software suite shall incorporate multiple applications that perform a variety of diagnostic processing.  Its primary function is to detect vehicular traffic approaching or departing the MVP sensor in multiple traffic lanes.  The detection shall be reliable, consistent, and perform under all weather, lighting, and traffic congestion levels.

There shall be a suite of client applications that reside on the host client/server PC.  The applications shall execute under Microsoft Windows 98, 2000, Windows NT, and XP. Available client applications shall include:

(a)	Network Browser:  Learn a network of connected Terra Access Pints and MVP’s then show the topology in a logical hierarchical relationship

(b)	Detector Editor: Create and modify detector configurations to be executed on the MVP sensor

(c)	Operation Log: Extract the MVP run-time operation log of special events that have occurred.

(d)	Data Archive: Extract time interval cumulative traffic statistics in real time (on the same time interval spacing) or after long periods of data accumulation (for instance, once a day or once a week, etc.)

(e)	Software Installer: Reconfigure one or more MVP sensors with a newer release of embedded system software.

b.	Functional Capabilities

(1)	MVP Image Sensor. The MVP image sensor shall be an integrated imaging color CCD array with optics, high-speed image processing hardware and a general purpose CPU bundled into a sealed enclosure.  The MVP Sensor shall be equipped with a sunshield to reflect solar heat and to shield the CCD array from direct exposure to the sun.  The CCD array shall be directly controlled by the general purpose CPU, thus providing high video quality for detection that has virtually no noise to degrade detection performance.  The optics and camera electronics shall be directly controlled for optimal illumination for traffic detection.  The lens shall be pre-focused at the factory, as required for operation.  It shall be possible for the user to zoom the lens, as required for operation.  The MVP sensor shall operate at a maximum rate of 30 frames per second when configured for the NTSC (US) video standard.  The MVP shall process a minimum of twenty detector zones simultaneously placed anywhere in the field of view of the sensor.  The video output shall have the ability to selectively show overlaid graphics indicating the current real-time detection state of each individual detector defined in the video.  The sensor output NTSC video shall be viewed with any compatible video-display device.

(2)	Differential Video. The MVP sensor shall output full motion color video through the means of a differential video port in NTSC format.  The differential video is transmitted over a single twisted pair.

(3)	Power. The MVP sensor shall operate on 24 VAC, 50/60Hz at a maximum of 25 watts.  The camera and the processor electronics shall consume a maximum of 10 watts and the remaining 15 watts shall support an enclosure heater.

(4)	MVP Operations Log. The MVP shall maintain a non-volatile operations log, which minimally contains:

(a)	Revision numbers for the current MVP sensor hardware and software components in operation.

(b)	Title and comments for the specific detector configuration file downloaded to the MVP.

(c)	Date and time the Operations Log was last cleared.

(d)	Date and time communications were opened or closed with the MVP.

(e)	Date and time of last power-up.

(f)	Time stamped MVP self diagnosed hardware and software error to aid in system maintenance and troubleshooting.

(5)	MVP Vehicle Detection. The real time detection performance of the MVP shall be optimized by following the set of guidelines for:

(a)	The traffic application to perform,

(b)	MVP sensor mounting location,

(c)	The number of traffic lanes to monitor,

(d)	The sizing, placement, and orientation of Count and Presence detectors,

(e)	Traffic approaching and/or receding from the sensor’s field of view,

(f)	Minimizing the effects of lane changing maneuvers.

(6)	Detection Zone Placement. The video detection system shall provide flexible detection zone placement anywhere and at any orientation within the field of view of the MVP sensor.  Preferred detector configurations shall be:

(a)	Detection zones placed across lanes of traffic for optimal count accuracy or

(b)	Detection zones placed parallel to lanes of traffic for optimal presence detection accuracy of moving or stopped vehicles.

A single detection zone shall be able to replace one or more conventional detector loops connected in series.  Detection zones shall be able to be overlapped for optimal road coverage.  In addition, selective groups of detectors can be logically combined into a single output by using optional delay and extend timing and signal state information.  Optimal detection shall be achieved when the MVP sensor placement provides an unobstructed view of each traffic lane where vehicle detection is required.  Examples of obstructions are not limited to fixed objects.  Obstruction of the view can also occur when vehicles from a lane nearer to the sensor obscure the view of the roadway of a lane farther away from the sensor.

(7)	Detection Zone Programming. Placement of detection zones shall be by means of a supervisor computer (PC) operating in the Windows 98, 2000 or Windows NT graphical environments, a keyboard, and a mouse.  The monitor shall be able to show the detection zones superimposed on images of traffic scenes.

The detection zones shall be created by using a mouse to draw detection zones on the supervisor computer’s monitor.  Using a mouse and the keyboard it shall be possible to place, size, and orient detection zones to provide optimal road coverage for vehicle detection.  It shall be possible to download detector configurations from the supervisor computer to the MVP, to retrieve the detector configuration that is currently running in the MVP, and to back up detector configurations by saving them to the supervisor computer’s removable or fixed disks.

The supervisor computer’s mouse and keyboard shall be used to edit previously defined detector configurations to permit adjustment of the detection zone size and placement, to add detectors for additional traffic applications, or to reprogram the sensor for different traffic applications or changes in installation site geometry or traffic rerouting.

(8)	Detection Zone Operation. The MVP real time detection operation shall be verifiable through several means.  The primary method shall be to view the video output of the sensor with any standard video display device (monitor).  The video with overlaid detection zones shall display each detector as white, when the state of the detector is ON, or as black, when the state of the detector is OFF.  Each detector shall be selectively assignable to be visible or hidden in the detector flashing video display when the detector configuration file is programmed.

Additional verification of detector operation includes visual observation of the LED’s on the front of the TAP and/or confirmation of detection as recognized by the traffic controller.

(9)	Optimal Detection. The video detection system shall optimally detect vehicle passage and presence when the MVP sensor is mounted 30 ft. or higher above the roadway, when the image sensor is adjacent to the desired coverage area, and when the distance to the farthest detection zone locations are not greater than ten (10) times the mounting heights of the MVP.  The recommended deployment geometry for optimal detection also requires that there be an unobstructed view of each traveled lane where detection is required.  Although optimal detection may be obtained when the MVP is mounted directly above the traveled lanes, the MVP shall not be required to be directly over the roadway.  The MVP shall be able to view either approaching or receding traffic or both in the same field of view.  The preferred image sensor orientation shall be to view approaching traffic since there are high contrast features on vehicles as viewed from the front rather than the rear. The MVP sensor placed at a mounting height that minimizes vehicles image occlusion shall be able to monitor a maximum of six (6) to eight (8) traffic lanes simultaneously.

(10)	Terra Access Point Detector Port Master. The Terra Access Point card shall provide the hardware and software means for up to eight (8) MVP sensors to communicate real time detection states and alarms to a local traffic signal controller.  It shall comply with the electrical and protocol specifications of the detector rack standards.  The card shall have 1500 Vrms isolation between rack logic ground and street wiring.

The Terra Access Point card shall be a simple interface card that plugs directly into a NEMA TS2 Type C or D detector rack.  The TAP TS2 card shall provide 32 phase inputs and 64 detector outputs.

(11)	MVP Input and Output Assignments. Input and Output assignments are programmed into the MVP through the local "Supervisor" port on the detector rack interface card.  The MVP declares which input and output pins are utilized during operation, the card requires no software configuration or setup.  Detector outputs shall be assigned to any detector type that changes on/off state and consecutive pairs of outputs shall emulate the output of two (closely spaced) detectors to report speed of individual vehicles.

(12)	Jumper Configurable TS1 I/O. Two jumpers shall permit the card to be configured so that all inputs and outputs go either to the rear edge connector or the front panel DB 15 connector.

(13)	Terra Interface Panel. The Terra communications interface panel supports one to Eight MVPs.  The communications interface panel consists of a predefined wire termination block for MVP power, data, and video connections, a power transformer for the MVP, electrical surge protectors to isolate the TAP and MVP, and an interface connector to cable directly to the TAP.

(14)	MVP Sensor Power. The interface panel shall provide power for one (1) MVP through a step-down transformer, taking local line voltage and producing 28 VAC, 50/60 Hz, at about 30 watts.  A 1/2 amp slow-blow fuse shall individually protect the step-down transformers.

(15)	High Energy Transient Suppression. The interface panel shall provide termination points for all street wiring of the MVP and high-energy transient protection.  The interface panel shall provide high energy crowbar transient protection, to NEMA TS2 standards.  The transient suppression shall protect all of the interconnected hardware.

(16)	Interface Panel I/O Terminations. The Terra interface panel terminal block includes terminations for one (1) to eight (8) MVPs.  This shall include terminations for:

(a)	3 termination points for power, Communications and Video to and from the MVP sensor

(17)	Supervisor Software Suite. The system software shall support either small or large networks of field hardware of MVP sensors, TAPs, and commercial telecommunications equipment.  The communication of traffic data, alarms, video snapshots, etc. across the network shall use the client server relationship model.  The central communications server, the ComServer, provides local or remote access to all networked field hardware to a variety of client applications that can execute simultaneously on the same host computer as the ComServer or across a local area network.  Local access shall provide direct hook-up/link to field hardware (for field installation and maintenance) even though the field hardware may be communicating to remote client applications.  Remote access shall provide connection to specific field hardware over long distances as part of a larger interconnected network.  The Supervisor Software Suite shall consist of the ComServer and all of the supplied client applications.

The Supervisor Software Suite shall provide an easy to use graphical user interface and support all models/versions of the supplied MVP and Mini–Hub.  The software shall support both still image and real-time viewing of video images within in Windows.  Programming the MVPs and designating inputs and outputs from/to the TAPs shall be performed with detectors overlaid on still images and monitoring the detection performance of the MVPs shall be displayed with "live" video.

The Supervisor Software Suite consists of the:

(a)	ComServer, to provide the network communications services of deployed field hardware to client applications

(b)	Network Browser, to activate selected client applications with associated field hardware in the network

(c)	Detector Editor, to create and modify detector configurations to be executed on the MVPs and TAPs in the field

(d)	Operation Log, to extract the MVP run-time operation log of special vents that have occurred

(e)	Data Archive, to extract time interval cumulative traffic statistics in real time (on the same time interval spacing) or after long periods of data accumulation (for instance, once a day or once a week, etc.) and stored locally to the Supervisor PC

(f)	Installer, to reconfigure one or more MVPs with a newer release of embedded system software.

(18)	Supervisor Computer System. A supervisor computer system is not required.

c.	MVP Hardware

(1)	MVP Image Sensor. The MVP video detection system shall use medium resolution, color image sensor as the video source for real-time vehicle detection.

As a minimum, each image sensor shall provide the following capabilities:

(a)	Images shall be produced with a color CCD sensing element with horizontal resolution of at least 500 lines and vertical resolution of at least 350 lines.

(b)	Images shall be output as a video signal conforming to NTSC specifications.

(c)	Provide software JPEG video compression.

(d)	Useable video and resolvable features in the video image shall be produced when those features have luminance levels as high 10,000 lux during the day.

(e)	Useable video and resolvable features in the video image shall be produced when the ratio of the luminance of the resolved features in any single video frame is 300:1.

(f)	Provide direct real-time iris and shutter speed control.

(g)	Be usable for video surveillance.

(h)	An optical filter and appropriate electronic circuitry shall be included in the image sensor to suppress "blooming" effects at night.

(i)	Gamma for the image sensor shall be preset at the factory to a value of 1.0.

(2)	MVP Optics. The MVP image sensor shall be equipped with an integrated zoom lens that can be changed using either configuration computer software or a hand-held controller.

(3)	MVP Enclosure. The image sensor and lens assembly shall be housed in an environmental enclosure that provides the following capabilities:

(a)	The enclosure shall be waterproof and dust-tight to NEMA-4 specifications, and shall have the option to be pressurized with dry nitrogen to 5  1 psi.

(b)	The enclosure shall allow the MVP image sensor to operate satisfactorily over an ambient temperature range from –29° F to 140° F while exposed to precipitation as well as direct sunlight.

(c)	The enclosure shall allow the image sensor horizon to be rotated during field installation.

(d)	The enclosure shall include a provision at the rear of the enclosure for connection of the factory-fabricated power, communications, and video signal cable.  Input power to the environmental enclosure shall be 110 VAC and either 50 or 60 Hz as an option.

(e)	A heater shall be at the front of the enclosure to prevent the formation of ice and condensation in cold weather, as well as to assure proper operation of the lens’ iris mechanism.  The heater shall not interfere with the operation of the image sensor electronics, and it shall not cause interference with the video signal.

(f)	The enclosure shall be light-colored and shall include a sun shield to minimize solar heating and glare.

(g)	The front edge of the sunshield shall protrude beyond the front edge of the environmental enclosure and shall include provision to divert water flow to the sides of the sunshield.

(h)	The amount of overhang of the sunshield shall be adjustable to prevent direct sunlight from entering the lens or hitting the faceplate.

(i)	The total weight of the image sensor in the environmental enclosure with sunshield shall be less than 6 pounds.

(j)	When operating in the environmental enclosure with the power, communication and video signal cable connected, the image sensor shall meet FCC class B and CE requirement for electromagnetic interference emissions.

(4)	MVP Electrical. Connections for video, communications and power shall be made to the image sensor using a single connector (Easy Lock). The Contractor shall supply the 3 conductor (1175-006) 18 AWG Carolprene flexible cable, which will run from the back of the camera to the signal controller cabinet.

(5)	MVP Field Interface Equipment. An MVP communication interface panel shall be available for installation inside the traffic cabinet.  The panel shall provide twisted-pair connection points with approved transient protection.  Transient protection shall be included for each MVP image sensor.  Additionally, the communication interface panel shall provide 110 VAC for each sensor using transformers that step down the voltage from the existing 110 or higher AC power available in the cabinet.  The interface panel 3-wire input power shall be connected to the transient protected side of the AC power distribution system in the traffic control cabinet in which the panel is installed.

d.	System Installation. The supplier of the video detection system shall supervise the installation and testing of the video detection system and computer equipment.  A factory certified representative from the supplier shall be on-site during installation.  Install all video detection equipment in accordance with the manufacturer’s recommendations.

e.	System Training. Provide a four-hour session of training by a certified instructor to State personnel in the operation, setup and maintenance of the video detection system.  Provide instruction and materials for a maximum of 10 persons and conduct the training at a location determined by the Engineer.

f.	Warranty, Service, and Support. The supplier, for a minimum of two (2) years, shall warrant the video detection system.  Ongoing software support by the supplier shall include software updates of the MVP sensor, Terra Access Point and supervisor computer applications.  These updates shall be provided free of charge during the warranty period.  The supplier shall maintain a program for technical support and software updates following expiration of the warranty period.  This program shall be available to the State in the form of a separate Contract.

740-2.14 VEHICULAR SIGNAL HEADS.  Provide Light Emitting Diode, (LED) Signal Heads that conform to the following publications:

	Circular Indications:  Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) circular Signal Supplement, 6/27/05 (ITE Publication ST-052).  This is hereafter referred to as "VTCSH-Circular-05".

	Arrow Indications:  Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement, 7/1/07 (ITE Publication ST-054).  This is hereafter referred to as "VTCSH-Arrow-07".

"The applicable ITE Specification", as used in this specification, means VTCSH-Circular-05 for circular LED indications and VTCSH-Arrow-07 for arrow LED indications.

1.	Signal Heads.

Use signal heads that:  are the adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; are adjustable through 360 degrees about a vertical axis; and are mounted at the location and in the manner shown on the Plans.  Ensure that all vehicular signal heads at any one intersection are of the same make and type, except for programmed visibility signal heads.

Programmed Visibility Signal Heads.

·	Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

·	Provide each section with a 1 inch cutaway visor.

·	Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

·	The signal must be mountable with ordinary tools and capable of being serviced without tools.  Preset the adjustment at 4 degrees below the horizontal.

·	The visibility of each signal face must be capable of adjustment or programming within the face.  When programmed, each signal face's indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness, a faint glow to each side will be permissible.

·	Program the head as recommended by the manufacturer and as directed by the Engineer.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.

a.	LED Optical Units.  Use Led optical units and lenses meeting the requirement of the applicable ITE specification for all indications.  Also meet the following requirements:

(1)	Gaskets.  Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

(2)	Markings.  Provide LED Signal module with manufacturer applied markings listed in Section 3.6, Module Identification, of the applicable ITE Specification.  For circular indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads:  LED Vehicle Circular Traffic Signal Supplement (June 27, 2005)."  For arrow indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads:  LED Vehicle Arrow Traffic Signal Supplement (July 1, 2007)."

(3)	Compatibility.  Use LED signal modules that are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

(4)	Testing Requirements.

(a)	All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

(b)	Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

(c)	Production Testing and Inspection.  Submit manufacturer's certification that all tests in Section 6.3 of the applicable ITE Specification have been successfully completed on each LED module to be used on the project.

(d)	Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA "Nationally Recognized Testing Laboratory" do the following:

i.	Perform an initial assessment of the manufacturer's factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

ii.	Perform initial Design Qualification Testing as specified in Section 6.4 of the applicable ITE specification.

iii.	Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of the applicable ITE specification:

6.4.2 Conditioning

6.4.4.1 - 6.4.4.4 Luminous Intensity

6.4.4.6 Chromaticity

6.4.6.1 Current Consumption

6.4.6.6 Power Factor

6.4.6.7 Total Harmonic Distortion

iv.	Provide a certification label on each certified LED traffic signal module verifying the manufacturer's factory and modules passed the tests listed in i. through iv. above.

(5)	Warranty.  Provide written warranty by the signal module manufacturer that covers defects in materials, workmanship, and compliance with the applicable ITE specification for a period of 60 months after the manufacture date.  No new LED module will be accepted if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules.

The warranty does not include the cost of removing failed modules or reinstalling new modules.

Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

b.	Lens.  Use only clear lenses for all green signal modules.  Use lenses that meet the requirements of the applicable ITE Specification.

c.	Housing.

(1)	Use die cast aluminum, meeting ASTM B 85, for all parts of the housing, including the doors and end plates.  Ensure all parts are clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

(2)	Use a one-piece housing with integral top, bottom, sides, and with square doors, for each signal section.

(3)	Use stainless steel for all exposed bolts, screws, hinges, pins, and door-locking devices.  Use stainless steel or approved non-ferrous, corrosion-resistant material for all interior screws and fittings.

(4)	Provide an opening in the top and bottom of each housing to accommodate standard 1-1/2 inch pipe fittings and brackets.

(5)	Provide the top and bottom openings of each housing with integral serrated bosses that will provide positive positioning of the signal head in 5-degree increments to eliminate undesirable rotation or misalignment of the signal head as well as between sections.  Provide a total of 72 teeth in the serrated boss.  Ensure teeth are clean and sharp to provide positive position with the grooves of the mating section or framework.

(6)	Fasten individual signal sections together with a cadmium-plated tri-stud connector, lock washers, and nuts with access holes for the passage of electrical conductors form one section to another.

(7)	Provide 2 integral hinge lugs on the left side of each signal housing for mounting the door.

(8)	Provide 2 latches with stainless steel wing nut assemblies on the right side of each signal housing to engage the door latches.

(9)	Provide each signal housing door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal in a NEMA Type 3R enclosure.

(10)	Provide a round opening designed to accommodate any standard traffic signal lens in each signal housing door.

d.	Backplates.  Backplates shall not be louvered.  Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.100 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 3 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

e.	Signal Mounting Hardware:  Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1 1/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Post top adapters without a terminal compartment or compartments - provide manufactured of bronze metal.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish (2) 1/2" x 13 hot dip galvanized bolts that conform to ASTM A325 and (2) 1/2" hot dip galvanized washers that conform to ASTM F 436.

When replacing signal heads include all mounting hardware, backplates and visors.

f.	Finish. Factory finish housing, backplates and visors, each face, with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

CR7401-110410

Delete 740-2.15 PEDESTRIAN SIGNALS and replace with the following:

740-2.15 PEDESTRIAN SIGNALS.  Use LED Pedestrian Countdown modules that use the international "HAND/WALKING PERSON" symbols.  Except for the countdown indication and as otherwise noted in this specification, use modules that conform to "Pedestrian Traffic Control Signal Indications - Part 2:  Light Emitting Diode (LED) Pedestrian Traffic Signal Modules" Institute of Transportation Engineers, 3/19/2004, (hereafter referred to in this document as "PTCSI-04") and to the applicable Sections of the current Alaska Traffic Manual.

1.	Pedestrian Signal Heads.

a.	Signal Modules:  Provide Portland Orange "HAND" and "COUNTDOWN DIGITS" and lunar white "WALKING PERSON."  Locate COUNTDOWN DIGITS adjacent to the associated UPRAISED HAND.  Make "HAND" and "WALKING PERSON" symbols a minimum of 11 inches high and 7 inches wide and COUNTDOWN DIGITS a minimum of 9 inches high and 7 inches wide.  Provide incandescent looking WALKING PERSON, HAND, and COUNTDOWN DIGITS.  Ensure the WALKING PERSON, UPRAISED HAND and COUNTDOWN DIGITS are not readily visible when not illuminated.  Provide "AllnGaP" Portland Orange LEDs or equivalent, rated for 100,000 hours or more at 77˚ F and 20 mA.  Provide "InGaN" White LEDs.

Make all exposed components of modules suitable for prolonged exposure to the environment, without appreciable degradation that would interfere with function or appearance.

Provide modules with an installed gasket to seal the junction with the signal housing.

(1)	Lens.  Use modules with internal masks to prevent the icons and digits from being visible when not in operation.  No external silk-screen is permitted.  Provide smooth or textured lens of transparent polycarbonate material, frosted to prevent sun phantom.  Use lenses that will not crack, craze or yellow due to solar UV exposure typical for a south-facing Arizona desert installation, after a minimum of 60 months in service.

(2)	Retrofit.  When a module will replace an existing module in an existing signal housing, furnish signal modules designed as retrofit replacements for existing neon type pedestrian signals (ICC 4090 and/or 4094).  Provide modules that do not require special tools for installation.  Provide modules that fit securely into existing pedestrian signal housings without any modification to the housing, connect directly to existing electrical wiring, and form a weather-tight seal.  Provide modules and components constructed so each retrofit of existing pedestrian signals only requires the removal of the existing neon message module, gasket, and power supply and installation of the new LED pedestrian countdown module.  Provide all necessary components to complete conversion including a one piece gasket.

(3)	Photometric Requirements.  Meet the following requirements:

·	Minimum Luminance.  Maintain the following minimum luminance values for at least 60 months, under the operating conditions defined in Sections 3.3.1 and 5.2.1 of PTCSI-04 (when measured normal to the plane of the icon surface):

	WALKING PERSON 2,200 cd/m2,

	UPRAISED HAND 1,400 cd/m2,

	DIGITS 1,400 cd/m2 (when "88" is displayed).

·	Maximum Luminance.  Provide modules for which the actual luminance of a module does not exceed three times the minimum maintained luminance, as defined is Section 4.1.1 of PTCSI-04, when operated within the temperature range -40˚ F to +165˚ F.

·	Uniformity.  Provide modules for which the uniformity of the signal output across the emitting section of the module lens (i.e. icons or digits) does not exceed a ratio of 5 to 1 between the maximum and minimum luminance values as measured in 0.5 inch diameter spots.

·	Markings.  Permanently mark the back of each LED signal module with:

Ø	Manufacturer's name, trademark, and other necessary identification

Ø	Warranty information

Ø	Rated voltage and power consumption in volt-amperes

Ø	An up arrow or the word "UP" or "TOP" for orientation within a signal housing.

(4)	Electrical.  Provide LED pedestrian countdown signal modules that:

(a)	are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

(b)	have a maximum of 4 each secured, color coded, 36 inches long, 600V, 18 AWG minimum, jacketed wires, conforming to the National Electrical Code, rated for service at +221˚ F for electrical connection.

(c)	operate from a 60 3 Hz AC line over a voltage range of 80 VAC to 135 VAC. Test voltage for all photometric performance measurements shall be 120 3 volts rms.

(d)	use LED circuitry that prevents perceptible flicker over the voltage range specified above.

(e)	include voltage surge protection against high-repetition noise transients and low-repetition noise transients as stated in Section 2.1.8, NEMA Standard TS-2, 2003.  Module must meet the following test requirements:  Section 8.2 IEC 1000-4-5 & Section 6.1.2 ANSI/IEEE C62.41.2-2002, 3kV, 2 ohm and Section 8.0 IEC 1000-4-12 & Section 6.1.1 ANSI/IEEE C62.41.2-2000, 6kV, 30 ohm.

(f)	have a current draw sufficient to ensure compatibility and proper triggering and operation of load current switches and conflict monitors in signal controller units.  When the module is switched from the On state to the Off state the terminal voltage shall decay to a value less than 10VAC RMS in less than 100 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliamps peak (7.1 milliamps AC).

(g)	have a maximum power consumption at 77˚ F of: Hand 11.0 watts, Walking Person 8.0 watts, Digits 10.0 watts (when display shows "88").

(h)	have waterproof strain relief and anti-capillary wires, or have electrical wires that do not penetrate the LED module housing.  This is intended to prevent water seepage between the back cover and the electrical wires, or between the copper and insulation of the wires (Connection may be made by use of an over molded connector).

(i)	will default to the hand symbol for abnormal conditions when nominal voltage is applied to the unit across the two phase wires (rather than being applied to the phase wire and the neutral wire).

(j)	have three separate power supplies:  one each for the Walking Person, the Upraised Hand and the countdown digits.  Use separate circuitry to power the LED Walking Person icon and the LED Upraised Hand icon, in order to virtually eliminate the risk of displaying the wrong icon.

(5)	Countdown Module Functions.

(a)	General.  Begin the countdown at the beginning of the FLASHING HAND indication.  End the countdown at "0" at the end of the FLASHING HAND indication.  Make the countdown display dark from the end of one FLASHING HAND indication until the beginning of the next.  Display steady, not flashing, countdown digits.  Do not provide user accessible switches, controls, or options that would allow modification of cycle time, icons, digits or that would allow the countdown to operate while the WALKING PERSON or STEADY HAND is displayed.

(b)	Learning Cycle.  At power on, make the countdown display dark for one learning cycle in which it will determine the duration of the FLASHING HAND indication.

(c)	Normal Operation.  Display the countdown/FLASHING HAND for the duration measure in the learning cycle for every cycle until the module measures a different FLASHING HAND duration.

(d)	Countdown Duration Modification.  When a different duration is measured, make the countdown dark for the next cycle, and enter a Learning Cycle as previously described.  Resume Normal Operation with the new FLASHING HAND duration if the measured FLASHING HAND DURATION for the next cycle is the same as for the first cycle when a change was detected.  Continue Learning Cycles, if the duration is different, until the measured FLASHING HAND duration is the same for two cycles.  Resume Normal Operation with new duration when that happens.

(e)	Countdown Truncation.  Make the digits dark if the controller output displays a STEADY HAND or if both the HAND and WALKING PERSON go dark, regardless of whether the countdown to zero has been completed.

(f)	Preemption.  Handle preemption events as described under Countdown Duration Modification and, if necessary, Countdown Truncation.

(g)	Recycling.  Allow for consecutive cycles without display of the STEADY HAND.

(h)	Power Outage.  Maintain an uninterrupted countdown during short power failures (<1.5 seconds).  Make the digits dark after a loss of power of more than 1.5 seconds and enter a Learning Cycle when the power is restored.

(6)	Testing Requirements.

(a)	All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

(b)	Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

(c)	Production Testing and Inspection by Manufacturer.  Submit manufacturer's certification that all tests in Section 6.3 of PTCSI-04 have been successfully completed on each LED module to be used on the project.  Show result of each individual test on the certification.

(d)	Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA "Nationally Recognized Testing Laboratory" do the following:

i.	Perform an initial assessment of the manufacturer's factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

ii.	Perform initial Design Qualification Testing as specified in Section 6.4 of the PTCSI-04.

iii.	Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following section of PTCSI-04.

6.4.2 Conditioning

6.4.4.1 - 6.4.4.4 Luminous Intensity

6.4.4.6 Chromaticity

6.4.6.1 Current Consumption

6.4.6.6 Power Factor

6.4.6.7 Total Harmonic Distortion

iv.	Provide a certification label on each certified LED traffic signal module verifying the manufacturer's factory and modules passed the tests listed in (a) through (c) above.

(7)	Warranty.  Provide a manufacturer's written warranty that covers defects in materials, workmanship, and compliance with PTCSI-04 for a period of 60 months after the manufacture date.  No new LED module will be accepted on a project if its manufacture date is more than 12 months before the date of installation.  Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules.

The warranty does not include the cost of removing failed modules or reinstalling new modules.

Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

b.	Housing:

(1)	Provide signal housings that have maximum overall dimensions of 18-1/2 inches wide, 18-3/4 inches high, and 9 inches deep, including hinges.

(2)	Provide a dustproof and weatherproof housing that allows easy access to and replacement of all components.

(3)	Provide a one-piece, corrosion-resistant, aluminum-alloy die-cast case complete with integrally cast top, bottom, sides and back.  Provide 4 integrally cast hinge lug pairs, 2 at the top and 2 at the bottom of each case, for operation of a swing-down door.

(4)	Provide 1 of the following 3 versions of the case, according to project specifications:

·	Clamshell mount, with hardware, for "pole left of message" installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

·	Clamshell mount, with hardware, for "pole right of message" installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

·	Make suitable for either post top or bracket mounting with upper and lower openings to accommodate standard 1-1/2 inch pipe brackets.  Plug unused openings to be weather-tight.  Integrally cast a shurlock boss into the bottom opening of the signal case.  Make the dimensions of the shurlock boss as follows:  outside diameter, 2-5/8 inch; inside diameter, 1-31/32 inch; number of radial teeth, 72; and depth of teeth, 5/64 inch.  Use clean and sharp teeth that provide full engagement to eliminate rotation or misalignment of the signal.

(5)	Make the door frame a one-piece, corrosion-resistant, aluminum-alloy die-casting, complete with 2 hinge lugs cast at the bottom and 2 latch slots cast at the top of each door.  Attach the door to the case by means of two Type 304 stainless steel spring pins.  Attach 2 stainless steel hinged bolts with captive stainless steel wing nuts and washers to the case with the use of stainless steel spring pins.  Provide a door that will latch and unlatch without the use of tools.

c.	Conductors:  Meet IMSA specifications 20-1 with No. 14 AWG or larger.

d.	Load Switches.  Place all load switches for operation of pedestrian signals in the controller cabinet.

e.	Fasteners.  Use machine screws, studs, and washers that are stainless steel.

f.	Gaskets.  Use gaskets that conform to ASTM D 1056, Grade 2C2.

g.	Terminal Blocks:  Provide a rain tight terminal compartment with a three position terminal block.

h.	Finish.  Factory finish the outside of pedestrian signal head housings and visors and signal visor interiors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363 and ASTM D-522.  Coating to be a Dull Black finish meeting Federal Standard 595-37038.

CR7402-110410

Replace Subsection 740-2.16 with the following:

740-2.16 PEDESTRIAN PUSH BUTTONS.  Push buttons shall be Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch. Furnish Polara model RBDLM2-B-4H or approved equal with the following features.  Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 VAC.  Must have the following characteristics:

1.	Switching unit that is solid state electronic piezo rated for 100 million cycles.

2.	Sealed to prevent ice from impeding function.

3.	Must hold the call for a minimum of 5 seconds.

4.	Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

5.	Provide an LED indication and an audible tone or beep within the button when pushed.

6.	Must have a raised rim or ridges to protect the button from side impacts.

7.	Powder coated cast switch housing of dark olive green or black.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

Replace Subsection 740-2.17 with the following:

740-2.17 FLASHING BEACONS.  Furnish beacons that consist of one or more traffic signal sections meeting the requirements of Subsection 740-2.14 Vehicular Signal Heads. See the Plans for the number, size and color of the signal sections required for each beacon.

Use the flasher in signal controller cabinets to energize beacons that flash continuously and are installed near traffic signals.  Otherwise, each flashing beacon controller assembly consists of the following 120 VAC equipment housed in a NEMA 3R enclosure:  a circuit breaker, a radio interference suppressor, a transient voltage suppressor, a NEMA Type 3 flasher, neutral and ground busses, and terminal blocks.

Controller assemblies for school zone speed limit sign beacons shall also include a time switch and a second 120 VAC circuit breaker that protects a thermostat and heater.

The NEMA 3R enclosure shall feature a single shelf and a hinged door with a hasp and staple for sealing and locking the cabinet door.

The radio interference and transient voltage suppressors shall meet the requirements of Subsections 740-2.11.1.k.(3) and (4), respectively.

Use a solid state NEMA Type 3 flasher meeting the requirements of NEMA Standard TS 1-1989, Traffic Control Systems.

Use 20 ampere, 600 volt barrier type phenolic terminal blocks with plated brass screw type terminals and integral strips can be marked with a pen or pencil.

Furnish an RTC Manufacturing model AP41-L time switch complete with wiring harness, or an approved, calendar programmable, solid state time switch with liquid crystal display, keyboard, input/output port, and wiring harness.  The approved time switch shall:

1.	Operate on line voltages from 95 to 135 VAC, operate in temperatures from -22 F to 165 F, and include a capacitor that provides 48 hours of backup power to retain programming and time when the unit is disconnected from AC voltage.

2.	Include a backlit display and provide 2 lines of alphanumeric legend with 16 characters per line.  The display shall automatically prompt the operator while programming the device through the keyboard for ease of use.

3.	Include an input/output port and keyboard activated special functions that transfer the program to other units and download the program to a printer for a hard copy record of the program.

4.	Automatically compensate for changes in Daylight Savings Time and leap years and include a keyboard activated special function to quickly change the dates for the begin and end of Daylight Savings Time.

5.	Provide at least 10 basic plans for daily and/or weekly use and at least 200 program steps that are equally divided amongst the actual number of basic plans.  Each program step shall be assignable to a single day, weekend, weekday, or every day.  The time switch shall also include 20 plans that activate the basic plans to provide one year of time based control.

6.	Include at least 4 single pole double throw, relay controlled outputs rated for 15 amperes of resistive load at 115 VAC.  Each pole shall be independently activated for steady on or momentary on and be manually switched on through the keyboard.

When a signal controller cabinet flasher is used to energize a beacon, furnish a two pole, fused block with built in fuse pullers to protect the flasher.  Furnish third party certified blocks that hold 13/32" x 1-1/2" midget ferrule fuses, are rated for 30 amperes, and feature tubular screw terminals that accommodate conductors to 8 AWG.  Furnish blocks with two fast acting, 3 ampere (BAF-3) fuses, and flat bases that can be directly mounted on a dead panel.

Replace Subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform to the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

	Meet or exceed the minimum initial light levels indicated.

	Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage.  Furnish lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21.

1.	Luminaries General

Install luminaires that feature:

a.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

b.	Third party certification for use in wet locations.

c.	Glass lenses, unless polycarbonate resin refractors are specified.

d.	Terminal blocks for attaching the illumination tap conductors.

e.	Aluminum reflectors with an ALZAK or ALGLAS finish.

f.	Optical components free of substances that affect photometric performance, paint.

g.	Housings cast with no provision for a photoelectric control receptacle.

h.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

i.	Plug in starting aids in fixtures with lamps through 400 watts.

2.	Luminaries – Cobrahead and Offset

Each cobrahead or offset luminaire shall also include:

a.	An easily removed hinged door used exclusively for mounting the ballast.

b.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

c.	A four bolt mounting brackets that fit 2 inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

3.	LED Luminaire

LED Luminaires shall be UL listed for wet locations and enclosure classified IP66 per IEC 529.  The fixture shall be resistant to corrosion, ultraviolet degradation and abrasion.  Nickel-chrome plated wire guard shall be used for providing anti-fouling protection from leaf/debris and animals nesting to assure cool LED operation.

The luminaire shall have five years warranty on the LED’s and the driver.  Average delivered lumens over 50,000 hours should be a minimum of 85% of initial delivered lumens.

The LEDs shall operate over the temperature range of -40 °F to +165 °F.  The LEDs shall be wired in series parallel strings.  The failure of many one LED, and its associated string of LEDs, shall not cause the loss of more than 20% of the light output of the complete LED module.

4.	Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

Special Provisions

Add the following Section:

SECTION 744

EROSION, SEDIMENT, AND POLLUTION CONTROL - MATERIAL

744-2.01 MATERIAL.

1.	Fiber Roll:  (commonly called straw wattle)

a.	Comprised of UV-degradable plastic netting or 100 percent biodegradable material.

b.	Filled with straw, flax, rice, coconut fiber material or composted material.

c.	Staking shall be made of 100 percent biodegradable materials.

Provide the Engineer certification stating the name of the manufacturer, product name, style number, chemical composition of the fiber, netting and certification of the weed-free status from the manufacturer.  Furnish a sample to the Engineer seven days before the scheduled installation.

2.	Manufactured Inlet Protection System:

a.	Manufacturers:

1)	Ultra Tech International – Ultra-DrainGuard

2)	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

3)	Enpac - Catch Basin Insert, Oil and Sediment or

b.	Approved equal.

3.	Sand Bag Inlet Sediment Trap:

a.	Sandbag sack fabric shall be a nonwoven, needle punched design meeting the following requirements:

Grab Tensile Strength	ASTM D 4632	200 pounds (min.)

Grab Elongation	ASTM D 4632	15 – 70%

Mullen Burst Strength	ASTM D 3786	400 psi. (min.)

Trapezoidal Tear Strength	ASTM D 4533	95 lbs. (min.)

Apparent Opening Size	ASTM D 4751	No. 30 U.S. STD sieve (max)

Permittivity	ASTM D 4491	0.01 sec-1 (min.)

Ultraviolet Light Stability:

Retained Strength	ASTM D 4355	90%

Puncture Strength	ASTM D 4833	120 lbs. (min.)

These requirements are for Minimum Average Roll Values (MARV) verified in accordance with ASTM D 4759.

b.	Seam Thread:  Similar durability to the sandbag sack fabric.

c.	Sandbag Fill Material:

Select Material	703-2.07	Type B

d.	Cinch Ties:  Plastic ties or equivalent tie recommended by the sandbag manufacturer.

CR744-022309

4.	Compost Sock:

a.	Sock must be:

1.	A mesh tube, oval to round in cross section, 12 inches in diameter.  Sock must have a minimum durability of one year after installation.

2.	Composed of UV photodegradable plastic or polyester netting.

3.	Composed of biodegradable jute, sisal, burlap, or coir fiber fabric.  Fabric must be clean, evenly woven, and free of encrusted concrete or other contaminating materials and free from cuts, tears, broken or missing yarns and thin, open, or weak places.

b.	Wood stake must be:

1.	Untreated fir, redwood, cedar, or pine and cut from sound timber

2.	Straight and free of loose or unsound knots and other defects which would render the stakes unfit for use

3.	Pointed on the end to be driven into the ground

4.	At least 1" x 1" x 24" in size for Type 1 installation

5.	At least 1" x 2" x 24" in size for Type 2 installation

c.	Rope must:

1.	Be biodegradable, such as sisal or manila

2.	Have a minimum diameter of 1/4 inch

- INDEX

- Standard Modification

INDEX Remove the text:  “Approved Products List” and replace with:  Qualified Products List

E36(01/27/07)

APPENDIX A

Environmental Permits

APPENDIX B

ROW Permit/Easement Figures

APPENDIX C

Construction Surveying Requirements

APPENDIX D

Materials Certification List

APPENDIX E

Utility Safety Requirements

APPENDIX F

Sign Details