PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

EAGLE RIVER URBAN REHABILITATION

STP-0558(4)/53834

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publication, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction (Metric) 98 M. (Price $25.00)

e.	Phase I Environmental Site Assessment Old Glenn Highway, Right-of-Way Mile 0.0 To Mile 8.1, Old Glenn Highway, August 1998 by AGRA Earth & Environmental

f.	Eagle River Urban Rehabilitation Old Glenn Highway, Artillery Road to North Eagle River Access Road, Phase II Investigations, Alaska; Project 53834, May 22, 2002 by Shannon & Wilson, Inc.

g.	Engineering Geology & Soils Report, Eagle River Urban; Project Number: RS-0558(1), Code Number: B49772, September 1980 by Central Region Materials Section Alaska Department of Transportation and Public Facilities.

3	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

5	New DBE Program Requirements

ADOT&PF has fully implemented the new program elements of its USDOT-approved Disadvantaged Business Enterprise (DBE) Program starting on August 1, 2000.  Key elements of the new DBE Program are:

a.	A newly revised DBE Program Specification, Section 120;

b.	All bidder’s are required to register annually with the ADOT&PF Civil Rights Office;

c.	Apparent low bidder’s will be required to submit a written commitment with each DBE firm proposed for subcontracting; and

d.	Prime Contractors will be required to report to the ADOT&PF Civil Rights Office payments made to DBE firms on a monthly basis.

All information required may be reported on forms available from the ADOT&PF Civil Rights Office or the Regional Contract Compliance Officer.  These forms will also be available soon on the ADOT&PF Civil Rights Office web page in ADOBE Acrobat downloadable format at

www.dot.state.ak.us/external/site_wide/dbe/dbe.html

Any questions about these new provisions may be directed to the Civil Rights Office at 1(800)770-6236 or 269-0851.

6.	The Materials Certification List (MCL) has been included in Appendix D.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for Certification of Compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

Section 101
Definitions and Terms

Standard Modification

101-1.03 DEFINITIONS. Add the following definition:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

(06/25/99)M68

Special Provisions

Add the following definition:

NON-FROST SUSCEPTIBLE MATERIAL.. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material.

(11/29/01)R1M98

Section 102
Bidding Requirements and Conditions

Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.

(2/1/00)R171M98

Section 103
Award and Execution of Contract

Standard Modification

103-1.01 CONSIDERATION OF BIDS.

Add the following after item 9: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.

(10/28/99)M 84

Standard Modification

103-1.02 AWARD OF CONTRACT. In the third paragraph, change “practical” to “practicable”.

(06/25/99)M 69

Section 105
Control of Work

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS. Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the working shop drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area.  Use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Anchorage Water & Wastewater Utility AT&T Alascom, Inc. ENSTAR Natural Gas, Inc. GCI Matanuska Electric Association Matanuska Telephone Association SOA-DOT/PF Anchorage M&O

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

You shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

(05/31/01)R3M98

1.	Anchorage Water and Wastewater Utility.

AWWU has existing water valves and sanitary sewer located within the project limits that will require adjustment as a part of this project.  It shall be the Contractor’s responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.

Prior to the commencement of work by the Contractor, Anchorage Water and Wastewater Utility (AWWU) shall check and correct deficiencies, which may exist in any AWWU facilities.  The Engineer, Contractor, and AWWU representatives shall witness the condition and location of each AWWU facility.  Failure to participate in this inspection shall result in the contractor forfeiting all right to claim that the AWWU facilities were damaged prior to his beginning of work.

Notice that the Contractor is ready for the above walk through inspection shall be given to AWWU field services section in writing, a minimum of two calendar days prior to starting construction.  To obtain a point of contact as well as determine where to send the written notice, contact AWWU by calling 564-2725 or 564-2765.  The Contractor shall furnish a copy of the written notice to the Engineer.

If at any time after the pre-construction inspection, AWWU finds any of their facilities damaged or rendered inoperable by the Contractor, the Contractor shall repair the damage at his expense.

The Contractor shall be responsible for the furnishing of traffic control and personnel to assist AWWU while locating and performing the pre-construction and post-construction inspections.  The Contractor shall schedule a final field review with AWWU and the Engineer upon completion of the valve box adjustments.

2.	ENSTAR Natural Gas Company.

ENSTAR Natural Gas Co. (ENSTAR) owns existing gas transmission, distribution and service facilities throughout the length of the project.  The Contractor shall notify ENSTAR in writing, a minimum of fifteen (15) calendar days prior to starting work on any ENSTAR relocation for this project.  The Contractor shall contact ENSTAR at 907-264-3730 to establish a point of contact and to determine where to send the written notice.  The Contractor shall furnish a copy of the written notice to the Engineer.

ENSTAR’s existing four (4) inch steel transmission between Eagle River Road station 9+900 Lt. and station 9+965 Lt. could potentially conflict with the proposed ditching. ENSTAR shall be provided with a fifteen (15) day written notice when the area will be staked, ENSTAR will then pothole the line and determine whether the line needs to be lowered.  If the line needs to be lowered, ENSTAR shall be allowed an additional four (4) calendar days to complete the lowering.

In the areas that gas lines exist under the roadway or pathway sections where storm drain facilities are to be installed, it shall be the Contractor’s responsibility to physically locate the existing gas lines prior to installation of the storm facilities to determine whether a conflict exists.  If a conflict exists the Engineer shall be notified of the conflict and a determination shall be made of the appropriate solution.  If relocation of the gas line is required the Contractor will allow ENSTAR free access to the area to complete the relocation.

The Contractor shall coordinate with ENSTAR and provide all traffic control, traffic maintenance, flagging, pavement removal and asphalt patching required for ENSTAR’s relocation work described above.

The Contractor shall adhere to ENSTAR’s Excavation Requirements Adjacent to Natural Gas Pipelines attached in Appendix F of these special provisions, when working in the area of these lines.

3.	GCI Cable, Inc.

General Communications Inc. (GCI) has existing aerial and underground facilities located within the project limits.  GCI has facilities that are in conflict with the proposed project improvements and will require adjustment and/or relocation.

The Contractor shall notify GCI in writing, a minimum of fifteen (15) calendar days prior to starting work on any GCI relocation for this project.  The Contractor shall contact GCI at 907-868-8581 to establish a point of contact and to determine where to send the written notice.  The Contractor shall furnish a copy of the written notice to the project Engineer.

The following GCI facilities will require relocation and the appropriate calendar days to complete the work at each location:

| Station/ Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Eagle River Loop Road 13+106, 17m Lt. | One pedestal | 4 |

The Contractor shall all provide assistance or perform work listed below before or in conjunction with the relocation work.

Location No. 1, The Contractor shall coordinate with GCI or their contractor and shall  provide all the traffic control, traffic maintenance and flagging required and all the pavement removal and asphalt patching required accommodating GCI’s relocation in this location.

4.	Matanuska Electric Association.

Matanuska Electric Association Inc. (MEA) has existing aerial and underground facilities located within the projects limits.  No relocation is anticipated due to the proposed project improvements.  MEA will provide new services to the project’s four new load centers.  The Contractor shall notify MEA Eagle River Office by calling 907-689-9621 to establish a point of contact and to have MEA schedule the new services to the load centers.  MEA requires fifteen (15) calendar days notice prior to starting the load center services work for this project.  Below is a list of the locations that MEA load center services are required and the appropriate calendar days to complete the service work at each location.

UNDERGROUND FACILITIES

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Load Center “A1” & “A2” at Old Glenn Highway Sta. 3+304, & 3+300, 28m Rt. | Load Center Service | 6 |
| 2. Load Center “E” Old Glenn Highway Sta. 4+721, 20.6m Rt. | Load Center Service | 7 |
| 3. Load Center “F” Old Glenn Highway Sta. 5+395,25m Lt. | Load Center Service | 3 |

The Contractor shall all provide assistance or perform work listed below before or in conjunction with the relocation work.

Locations 1,2 & 3: Once the Contractor has completed the load center placement and the load centers have been inspected and accepted (tagged) the Contractor shall call MEA to schedule the load center service(s).  Prior to placing top soil and seeding the Contractor shall coordinate with MEA to confirm the service cable conductor routes in the load center locations.

5.	Matanuska Telephone Association.

Matanuska Telephone Association (MTA) has existing aerial and underground facilities located within the project limits.  MTA has facilities that are in conflict with the proposed project improvements and will require adjustment and/or relocation.  The Contractor shall notify MTA at 907-761-2534 to establish a point of contact and to determine where to send the written notice fifteen (15) calendar days prior to starting work on any MTA relocation for this project.  The Contractor shall furnish a copy of the written notice to the project Engineer.  MTA or their contractor crews will only be required to work in one location of the locations listed below at one time.

The following MTA facilities will require relocation and the appropriate calendar days to complete the work at each location.

UNDERGROUND FACILITIES

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Eagle River Road Sta. 9+635 Lt. to Sta. 9+800 Lt. | Place New Direct Buried Cables & Pedestal & Cross Connect Boxes | 10 |
| 2. Eagle River Road Sta. 9+635 Lt, to Sta. 9+800 Lt. | Splicing of the New Buried Cables | 4 |
| 3. Eagle River Loop Road Sta. 13+060 to Sta. 13+120 Lt. | Place New Buried Cable & Pedestal & Splicing | 7 |
| 4. Old Glenn Highway Sta. 4+720, Rt. to Sta. 4+726, Rt. | Place New Buried Cables & Conduit & Adjust Existing Cabinet | 5 |
| 5. Old Glenn Highway Sta. 4+720, Rt. to Sta. 4+726, Rt. | Splicing of the New Buried Cable | 3 |
| 6. Old Glenn Highway Approx. Sta. 4+430, 13m Lt & Sta. 4+420 Lt. | Existing Buried 6-way duct System & Buried Conduit Crossing | Approve Contractors Shoring Plan 3 |

The Contractor shall all provide assistance or perform work listed below before or in conjunction with the relocation work.

Location No. 1: The Contractor shall coordinate with MTA and provide the required slope staking, at approximate Eagle River Road Sta. 19+780, Lt. and all the traffic control, traffic maintenance and flagging required to accommodate MTA’s work in this location.

Location No. 3: The Contractor shall coordinate with MTA and provide all the traffic control, traffic maintenance and flagging required and remove all the pavement required to accommodate MTA’s crossing of Horseshoe Drive. When MTA has completed the cable placement crossing of Horseshoe Drive the Contractor shall coordinate with MTA and provide all the pavement patching required of Horseshoe Drive.

Location No. 4: The Contractor shall coordinate with MTA and provide all the traffic control, traffic maintenance and flagging required and remove all the pavement required to accommodate the MTA work in this location.

Location No. 6: The Contractor shall provide a shoring plan to shore MTA’s existing buried 6-way duct system should shoring be required a minimum of 5 calendar days prior to starting the storm-drain pipe installation in this location.   In the areas that buried phone cables and phone ducts exist under the roadway or pathway sections where storm drain facilities are to be installed it shall be the Contractors responsibility to physically locate the existing buried telephone facilities prior to installation of the storm facilities to determine whether a conflict exists. If a conflict exists the Engineer shall be notified of the conflict and a determination shall be made of the appropriate solution.  If relocation of an existing telephone facility is required the Contractor will allow MTA free access to the area to complete the relocation.  Once MTA has received, reviewed and approved of the Contractor shoring plan the Contractor shall coordinate with MTA and provide MTA with a work schedule for this location.  The Contractor shall allow MTA personal free access to the location listed above to inspect the backfill operation around the MTA facilities.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following project will be under construction concurrently with this project:

Business Boulevard Pedestrian Safety Improvements TEA-0001(130)/52519/96-17

Owner:	 MOA Department of Public Works

Contractor: Wilder Construction

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project so as to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.

(2/1/00)R175M98

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following: Inspect and clean all storm drain sumps and petroleum separator manholes during the construction season and prior to winter shutdowns. This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604.

(2/1/00)R4M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract.

(02/06/02)R237M98

Standard Modification

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

1.	The act, event, or condition the claim is based on.

2.	The Contract provisions which apply to the claim and provide relief.

3.	The item or items of Contract work affected and how they are affected.

4.	The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.

(03/26/01) M 101

Special Provision

Add the following: Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district.

(3/21/01)R93

Section 106
Control of Material

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

(08/31/99)S 13

106-1.02 LOCAL MATERIAL SOURCES. Add the following under Item 2. Inspection and Acceptance:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

a.	Site specific health and safety risks.

b.	Recognition and avoidance of hazards.

c.	Restricted areas.

d.	Warning and evacuation signals.

e.	Other special safety procedures.

f.	Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.

(5/1/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87  (03/08/02)klj

Section 107
Legal Relations and Responsibility to Public

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from the Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

(5/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99)R170M98

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120
Training Program	Section 645
Federal EEO Bid Conditions	Form 25A-301
EEO-1 Certification	Form 25A-304
DBE Subcontractable Items	Form 25A-324
ADOT&PF Training Program Request	Form 25A-310
Training Utilization Report	Form 25A-311
Contact Report	Form 25A-321A
DBE Utilization Report	Form 25A-325C
Summary of Good Faith Effort Documentation	Form 25A-332A
Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

Section 108
Prosecution and Progress

Standard Modification

108-1.01 SUBLETTING OF CONTRACT. Delete the last paragraph under Item 4. and add the following to Item 5:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts.

(10/28/99) M 70

Special Provisions

108-1.03 PROSECUTION AND PROGRESS. Add the following under item no. 1:  Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

(4/22/99)R250M98

Delete Item 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME.  Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

1.	those instances where the Engineer orders suspension of the work for unsafe conditions,

2.	for failure by the Contractor to carry out contractual provisions, or

3.	for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(2/15/01)R242M98

Section 109
Measurement and Payment

Standard Modification

109-1.05 COMPENSATION FOR EXTRA WORK.

Under item 1. Labor:

Delete: “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(5/31/00)M90

1.	Labor. Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

(02/08/01)M71

Special Provision

Under item 3, Equipment, change the first sentence to read: … “Rental Rate Blue Book for Construction Equipment”, published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA, 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

(1/27/00)R14

Standard Modification

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor.

(02/08/01)M71

Special Provision

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(2/4/02)R137A

Add the following Section:

Section 120
Disadvantaged Business Enterprise (DBE) Program

Standard Modification

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

1.	Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer. A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

1)	A description of the work that each DBE will perform;

2)	The dollar amount of participation by the DBE firm;

3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

1.	Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

d.	Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

a.	regular dealer;
b.	manufacturer;
c.	broker; 
d.	subcontractor; 
e.	joint-venture; or
f.	prime contractor.

2.	Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

1)	The work performed will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

6)	All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

7)	The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

1)	increasing the participation of other DBEs on the project;

2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

2)	by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

(11/17/00)S33

Section 202
Removal of Structures and Obstructions

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work also consists of pavement planing as specified in this section.

(2/28/01)R143M98

Add the following: This work also consists of abandoning or removing manholes as designated on the Plans or as directed by the Engineer.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  All existing asphalt pavement and temporary asphalt pavement used in construction shall be removed, processed and sized to 100 percent by weight passing the 37.5mm sieve, and 90-100 percent by weight passing the 25mm sieve.  The processed pavement shall then be reused and paid as 301(1) Aggregate Base Course or hauled to the stockpile location described in Subsection 202-3.06.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

Sawcut and remove existing pavement in areas of distress, cold patches or potholes as directed by the Engineer.  The pavement shall be removed to a distance of 300 mm outside of the described areas. Pavement that is removed shall be replaced with Asphalt Concrete as shown on the plans in accordance with the requirements of Section 401, Asphalt Concrete Pavement.

(2/28/01)R257M98

Add the following Subsections:

202-3.06 PAVEMENT PLANING. Add the following Subsection: Remove existing asphalt concrete pavement by cold planing at locations shown on the Plans. The surface of the pavement after planing shall be uniformly rough grooved or ridged.

Remove all planed material from the project immediately after planing.  Stockpile planed material at the Municipality of Anchorage gravel pit located along the Eagle River Correctional Frontage Road near the Hiland Overpass.  Coordinate with Scott Schnell, MOA Supervisor for Eagle River/Chugiak area @ 694-3487 to coordinate acceptance of material and desired location of stockpile.  Planed material not acceptable to the maintenance chief will be disposed of in an acceptable manner or incorporated into the road structural prism as directed by the Engineer.  Disposal areas shall be outside the project limits and in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks and Curbs.  Obtain written consent from the property owner.  Obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt. ADEC permitting officer in Anchorage may be contacted at 269-7590.

During the planing operation, sweep the streets with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove all loosened material from the planed areas.  The removal operation shall follow within 15 meters of the planing machine.

Do not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 50 millimeters. In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 0.6 meters in width shall be placed adjacent to the edge and to all gutters.

Maintain a tolerance of 3 millimeters between adjacent passes by the planer.

Remove existing asphalt concrete pavement overlay from gutters adjacent to the area being planed.

The existing curb and gutter not designated for removal shall not be damaged or disturbed. Any damage caused by the planing operation shall be removed and replaced by the Contractor at his expense.

The planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 1.5 meters wide and shall be equipped with cutting teeth placed in a variable lacing pattern to produce the desired finish.

The planing machine shall have the following capabilities:

1.	operating speeds from 0 to 12 meters per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the planing operation without leaving the controls,

6.	adjustable as to slope and depth,

7.	longitudinal grade control automatically actuated by the use of a 9-meter ski, and

8.	able to cut up to 76 millimeters without producing fumes or smoke.

Provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, bus pullouts, and intersections.

202-3.07 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the Department of Transportation Maintenance Yard located in Anchorage.  All remaining items removed become the property of the Contractor.

(8/30/00)R258M98

202-3.08 DISPOSAL. A disposal site for trees, brush, outsized boulders, and other objectionable debris shall be Contractor-furnished. Unclassified excavation shall be disposed of at either the municipal sanitary landfill area off Hiland Road, the Anchorage Regional Composting Facility off Point Woronzof Road, or at a Contractor-furnished disposal site.  Unclassified excavation or any material containing stumps, brush, or other construction debris will be charged at the current disposal fee at the municipal sanitary landfill. Contractor-furnished disposal sites shall conform to Appendix Chapter 33 of the 1994 Uniform Building Code (UBC), as adopted and amended by the Municipality of Anchorage.

202-3.09 REMOVAL OF MANHOLES. Add the following: Remove or abandon manholes as designated by the Plans or as directed by the Engineer.

Remove manhole frame and cover, dustpan, adjusting rings and cone section or reducing slab for existing designated for abandonment by the Plans or by the Engineer.  Plug all conduits intersecting the manhole and fill the remaining barrel sections of the abandoned manholes with material meeting the requirements of Selected Material, Type C and compact it to the satisfaction of the Engineer.

Carefully remove and deliver salvaged materials to a site directed by the Engineer.  Provide a disposal site for non-salvageable materials.

All existing manhole frames, covers, dustpans, adjusting rings, cone sections and reducing slabs removed but not reinstalled under these Special Provisions shall become the property of the Contractor.  Materials may be reused if they are undamaged, of satisfactory quality and approved by the Engineer.  No materials are reused for reinstalled until they have been thoroughly cleaned by the Contractor and inspected by the Engineer.

202-5.01 BASIS OF PAYMENT. After the third paragraph, add the following:

Item 202(15) At the contract price per unit specified.  Payment is full compensation for mechanical sweepers during planing operations, removal of pavement from the gutter and stockpile of planed material per Subsection 202-3.06.

(2/28/01)R143M98

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

202(15)	Pavement Planing	Square Meter

Section 203
Excavation and Embankment

Special Provisions

203-1.01 DESCRIPTION. Add the following: Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

(9/1/89)R20

Ditch linear grading shall include installation of insulation board where necessary due to reduced cover over existing utilities.

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

(03/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.

(03/14/02)R193M98

203-3.05 EXCAVATION OF CONTAMINATED MATERIALS: Add the following Subsection: This work shall consist of removing contaminated soils encountered while installing the storm drain system.  Disposal of contaminated soils shall be at a location approved by the Engineer.

1.	Determining Limits of Contaminated Soil. Test soils in accordance with Subsection 644-2.09, Contaminated Material Testing. Verify the contamination levels in the soils and determine if the soils can be disposed of as unclassified excavation or if they will require special handling.

Soils that have a response from photoionizing detector or equivalent instrument above ADEC cleanup level A for petroleum hydrocarbons, are considered to be "contaminated" and will require special handling and shall be disposed of in accordance with this Subsection.

2.	Worker Health and Safety. Prior to removing any soils identified as contaminated, the Contractor shall assure that all personnel working in the area of potential contamination have received the State of Alaska, Department of Labor, Health and Safety Training. The Contractor shall provide the Engineer a list of all personnel and subcontractors that will be working within the area identified as being potentially contaminated.

The Contractor shall notify all personnel and subcontractors prior to their beginning Work at the site that they will be working in an area identified as being potentially contaminated with petroleum fuel.

3.	Contaminated Soil Removal and Segregation. In the event the Contractor must stockpile contaminated soil, a liner, cover and temporary fencing will be required. The size and location of the liner shall be as approved by the Engineer. The Contractor shall cover and secure the stockpile at the end of each work day. The Contractor shall be responsible for removal of the stockpile liner, safety fence and cover once the contaminated soil is removed.

The method of disposal shall be in accordance with Department of Environmental Conservation guidelines for reducing BTEX or TPH in soils. Any additional testing required at the disposal site shall be done in accordance with Subsection 644-2.09, Contaminated Material Testing, unless otherwise directed by the Engineer.

(05/16/97)R149

203-4.01 METHOD OF MEASUREMENT. Add the following: Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the Meter along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

(9/1/89)R20

Installation of insulation board will not be measured.

Item 203(28), Contaminated Soil Special Handling, will be measured for payment on a time and material basis in accordance with subsection 109-1.05, Compensation For Extra Work.

(05/16/97)R149

203-5.01 BASIS OF PAYMENT. Add the following: Payment for ditch linear grading will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

(9/1/89)R20

Installation of insulation board will be subsidiary to Item 203(17) Ditch Linear Grading.

Testing of contaminated soils will be measured for payment under Item 644(8), Contaminated Material Testing.  Excavating, temporary storage and disposing of contaminated soil will be paid under Item 203(28), Contaminated Soil Special Handling.  The Contractor will be paid on a time and materials basis for authorized Work in accordance with Subsection 109-1.05, Compensation for Extra Work.  Backfilling within the limits of other work will be paid for as defined under the other work items.  Backfilling outside plan excavation limits or outside of other work items will be paid for as embankment construction under Item 203(6A) Borrow, Type A.

(05/16/97)R149

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

203(17)	Ditch Linear Grading	Meter

203(28)	Contaminated Soil Special Handling	Contingent Sum

Section 301
Aggregate Base Course

Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1.

(10/1/91)R116

Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.

(9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course,

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons.  Using the test strip, the Engineer will determine the optimum density, known as the density standard.  Minimum compaction shall be 98% of the density standard.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

Add the following: Price adjustment will not be applied to the aggregate base course.

Section 401
Asphalt Concrete Pavement

Special Provisions

401-2.01 Composition Of Mixture - Job Mix Design. Add the following to the first paragraph after ATM T-17:

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03 Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping.  Storage tanks used for the batch shall be noted on the test report.  Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project.  A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket.  The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

1.	Manufacturers certificate of compliance, Subsection 106-1.05

2.	Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

a.	Date and Time of loading

b.	Batch number and storage tank

c.	Type, grade, temperature, and quantity of materials loaded

d.	Type and percent of anti-strip added.

(03/19/02)R199M98

Delete Subsection 401-3.07 and substitute the following:

401-3.07 PREPARATION OF EXISTING SURFACE. Existing paved surfaces shall be cleaned of loose material by vacuum sweeping.

Prior to paving, but after planing, all cracks from 5 mm to 25 mm in width shall be sealed with Roadsaver 231 sealant or approved equivalent.  Cleaning of cracks and application of sealant shall be done according to the manufacturer's recommendations.  Cracks greater than 25 mm (+25 mm) in width shall be cleaned of loose material to full depth then filled using Asphalt Concrete Pavement, Type III, Class B, tamped in place.

After planing the asphalt concrete pavement and crack repair, a leveling course shall be required to fill any remaining ruts or depressions having a depth greater than 12 mm.  Place the leveling course material at the depth required to provide proper grades.  The leveling course material shall be Asphalt Concrete Pavement, Type III, Class B.  Place the leveling course material with an asphalt paver, Layton box, by motorized grader or other approved method.  Compact the leveling course with three passes of a pneumatic tired roller or by vibratory plate/roller equipment.

Planing breakthrough areas shall be cut out and patched to match the planed surface with Asphalt Concrete Pavement, Type II or Type III.  Contractor shall notify the Engineer of any pavement areas that might be considered thin or unstable.

Pavement peeling or layer separation shall be repaired by removing the upper layer to the separation surface by planing or other means approved by the Engineer.  If the separated surface is greater than 12 mm below the existing planed surface, place a leveling course of Asphalt Concrete Pavement, Type II or Type III.  If the separation surface is less than 12 mm below the existing planed surface, proceed with the designed pavement overlay.

Contact surfaces of curbing, gutters, manholes, and other structures shall be coated with a thin , uniform coating of tack coat material conforming to Section 402 prior to the asphalt concrete pavement being placed.

Surfaces which have received a tack coat shall be allowed to cure, prior to placement of asphalt concrete pavement.

(10/2/96)R218M

401-3.09 Preparation Of Aggregates. In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14 Joints. Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one  150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

401-3.15 PATCHING DEFECTIVE AREAS. Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01 Method Of Measurement. Under Asphalt Cement, 1., add to the end of the second sentence: “.. ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints. By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

(03/19/02)R199M98

Add the following: Repair of cracks shall not be measured.  Leveling course material used for repair of cracks, depressions and pavement peeling shall be measured by the megagram of material placed.

(10/2/96)R218M

401-4.02 Acceptance Sampling And Testing. Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken at the end of the auger or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined in accordance with  WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates.  The dry batched aggregate gradation will be determined in accordance with WAQTC FOP FOR AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with  WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One 150 mm diameter core is required for acceptance density testing only.  Acceptance density testing will be in accordance with WAQTC FOP FOR AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

(03/19/02)R199M98

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph: No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Add the following: Crack repair shall be subsidiary to Item 401(1A) Asphalt Concrete Pavement, Type II, Class A.

Add the following: Anti-stripping additives shall be subsidiary to Item 401(2) Asphalt Cement, Grade PG 52-28.

Add the following Section:

Section 407
Stone Mastic Asphalt Concrete Pavement

Special Provisions

407-1.01  DESCRIPTION.  This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the Plans.

407-2.01  COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN.  Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

Provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

Submit the following to the Engineer at least 15 calendar days prior to the production of Stone Mastic Asphalt Concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-9, Stone Mastic Asphalt Concrete Aggregate.  Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended.  Sample sizes:  45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand and/or mineral filler.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature/viscosity curve for the asphalt cement.

4.	A minimum 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 2.5 kilogram sample of the stabilizing additive (cellulose or polyolefin) proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 407-2.05 and manufacturer’s certificate of compliance with Section 407-2.05.

The Engineer will then evaluate the material and the proposed gradation using ATM T-17 (version 01/93) and the mix design requirements of Table 407-1 to establish the Job Mix Design.  Approved Job Mix Designs will become a part of the contract and will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.  Up to10 working days will be required to determine the Job Mix Design after receipt of all items specified above.

TABLE 407-1

STONE MASTIC ASPHALT CONCRETE

MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement |
| --- | --- |
| Stability, newton, min. | 4450 |
| Flow, 0.25 mm | 8-16 |
| Voids in total mix, percent | 3-5 |
| Compaction, number of blows each side of test specimen | 50 |
| Dust-asphalt ratio (the percent of material passing the No. 0.075 mm sieve divided by the percent of asphalt, by weight of mix) | 0.6-1.4 |
| Voids in the mineral aggregate (VMA), min. Voids In Coarse Aggregate (VCA) Of The Mix, % | 17.0 Less Than VCA Of The Coarse Aggregate As Determined By AASHTO T 19 |
| Minimum Asphalt Cement Content % | 6.2 |

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $1,500.00 each.

407-2.02  AGGREGATES.  Aggregates shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.13.

407-2.03  ASPHALT MATERIALS.  Provide the grade of asphalt cement specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  When not specified, the grade of asphalt cement shall be PG 58-28.

Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design is submitted and approved.

407-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05  STABILIZING ADDITIVES.  Use cellulose or polyolefin stabilizing additives.  The dosage rate for cellulose is 0.3 percent by weight of the total mix.  The dosage rate for polyolefin is 0.4 percent by weight of the total mix.  The allowable tolerance per megagram shall not exceed 10 percent of the required weight of the stabilizing additive.

The cellulose stabilizing additive shall conform to the properties shown in Table 407-2. The polyolefin stabilizing additive shall conform to the properties shown in Table 407-3.

TABLE 407-2

CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis(1): Fiber Length Percent passing 0.150 mm sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing 0.850 mm sieve Percent passing 0.425 mm sieve Percent passing 0.106 mm sieve | 6.4 mm (max) 60-80 0.9-1.5 mm (avg) 75-95 55-75 10-30 |
| Ash Content(3) | 20% non-volatiles (max) |
| pH(4) | 7.5 +/-1.0 |
| Oil Absorption(5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content(6) | < 5% |
| Bulk Density(7) | 20.0-40.0 kg/m3 |

Notes:

(1)	Method A - Alpine Sieve Analysis.  This test is performed using an Alpine Air Jet Sieve (Type 200 LS).  A representative five gram sample of fiber is sieved for 14 minutes at a controlled vacuum of 0.56 meters (+/- 75 mm) of water.  The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis.  This test is performed using 0.850, 0.425, 0.250, 0.180, 0.150 and 0.106 mm sieves, nylon brushes and a shaker.  A representative 10 gram sample of fiber is sieved, using a shaker and two nylon brushes on each screen.  The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content.  A representative 2-3 gram sample of fiber is placed in a tared crucible and heated between 593 and 649 C for not less than two hours.  The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test.  Five grams of fiber is added to 100 ml of distilled water, stirred and let sit for 30 minutes.  The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test.  Five grams of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation.  It is then placed in a screen mesh strainer (approximately 0.5 square millimeter hole size) and shaken on a wrist action shaker for ten minutes (approximately 31.75 mm motion at 240 shakes/minute).  The shaken mass is then transferred without touching, to a tared container and weighed.  Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content.  Ten grams of fiber is weighed and placed in a 121 C forced air oven for two hours.  The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density.  Fluff fiber with air or Hobart Mixer, weigh out 25 grams of fiber, place in 100 ml cylinder, tap cylinder and measure volume.

TABLE 407-3

POLYOLEFIN STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Chemical Property | Ethylene, Propylene, Butane 1, Terpolymer, double bond free with no other functional group. |
| Specific Gravity | 0.86 |
| Size | Approx. 3 mm dia. by 3 mm length |
| Softening Point | 93 C |

407-2.06  PROCESS QUALITY CONTROL.  Sample and test materials for process QC of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.03.

Failure to perform process QC forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

CONSTRUCTION REQUIREMENTS

407-3.01 WEATHER LIMITATIONS.  Do not place Stone Mastic Asphalt Concrete mixture when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  Do not place Stone Mastic Asphalt Concrete mixture unless the surface temperature is 10 degrees C or warmer, or after September 10 of any year.

407-3.02 EQUIPMENT.  Use equipment in good working order and free of asphalt concrete mix buildup.  Make all equipment available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

407-3.03 BITUMINOUS MIXING PLANTS.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.    Maintain a current Air Quality Permit issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

407-3.04  HAULING EQUIPMENT.  Haul Stone Mastic Asphalt Concrete mixture in trucks with tight, clean, smooth metal beds thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List.  Do not use any petroleum product (e.g. diesel or fuel oil) as an asphalt release agent.  If truck beds are not satisfactorily cleaned, the Engineer may direct operations to cease.  The Engineer will not allow the operations to resume until measures are in place to insure proper cleaning of hauling units.  Hauling units will be restricted to end dumps only.

Belly dumps will not be allowed as hauling units unless a plan is developed and approved by the Engineer that ensures the following items are satisfactorily adhered to:

- Tracking of asphalt material on the haul route, both on and off the project, shall be eliminated or cleaned.

- Truck beds shall be cleaned and build up of material not allowed.

- Pavement mat temperature behind the screed shall be optimum for compaction.

If the above items are not performed to the Engineer’s satisfaction, the use of belly dumps will be terminated.

Cover the Stone Mastic Asphalt Concrete mixture with a secured watertight canvas cover extending at least 0.3 meters over the sides and end of the truck bed when required by the Engineer.

407-3.05  ASPHALT PAVERS.   Use self-propelled asphalt pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a mobile string-line (ski) at least 9 meters in length, or other approved grade follower to automatically actuate the paver screed control system. Use grade control on either  a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip asphalt pavers with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip receiving hoppers with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Place auger extensions within 0.5 meters of the screed extension on both sides, or per written manufacturer’s recommendations.

The use of a pickup machine to transfer Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collecting the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06  ROLLERS.  Supply a minimum of three rollers weighing a minimum of 11 megagrams each to compact the Stone Mastic Asphalt Concrete mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel or vibratory steel wheel type.  The roller drums shall be a minimum of 2.1 meters wide.  Use self-propelled rollers specifically designed to compact hot asphalt concrete mixtures and capable of reversing without backlash.  The use of equipment that results in crushing of the aggregate, or pick-up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

407-3.07  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces in conformance with the plans and specifications.  Clean existing paved surfaces of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After completion of planing of a section of the roadway, the Engineer shall inspect that section for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  Backfill the excavated area with aggregate base course material in conformance with the requirements of Section 301, asphalt concrete leveling course, or with Stone Mastic Asphalt Concrete as directed by the Engineer.

Prior to placing Stone Mastic Asphalt Concrete mixture, uniformly coat pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures with tack coat material conforming to Section 402.

407-3.08  PREPARATION OF ASPHALT.  Provide a continuous supply of the asphalt cement to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09  PREPARATION OF AGGREGATES.    Provide adequate dry storage for the mineral filler and stabilizing additive.  Dry the aggregate for Stone Mastic Asphalt Concrete so the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled from the windrow, the end of the auger, or from behind the screed prior to compaction, is less than 0.5% (by total weight of mix) as determined by WAQTC TM 6.

Heat the aggregate for Stone Mastic Asphalt Concrete to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Stone Mastic Asphalt Concrete mixture in which soot or fuel is present is considered unacceptable per Subsection 105-1.11.

407-3.10  MIXING.  Uniformly combine the aggregate, asphalt cement, additives, and stabilizing additives in the amounts required by the Job Mix Design.  Mix the materials such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants.  Add the stabilizing additive through a separate inlet directly into the weigh hopper above the pugmill.  Time the addition of the stabilizing additive to occur during the hot aggregate charging of the hopper.  Provide adequate dry mixing time to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants.  Add cellulose stabilizing additive into the drum mixer at the same point the asphalt cement is added.  Add polyolefin-stabilizing additive directly into the drum mixer through the RAP inlet.  Do not use polyolefin stabilizing additive in a drum mix plant without a RAP inlet.  Operate the drum mixer to ensure complete blending of the stabilizing additive into the mix.

Dry mix Stone Mastic Asphalt Concrete with cellulose stabilizing additive a minimum of 15 seconds, and wet mix a minimum of 40 seconds.  Dry mix Stone Mastic Asphalt Concrete with polyolefin a minimum of 4 seconds, and wet mix a minimum of 30 seconds.  In batch plants, place the dry aggregate in motion immediately prior to the addition of asphalt cement.  Use a wet mixing time adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

Mix the Stone Mastic Asphalt Concrete within the temperature range determined by the Job Mix Design.

Proportion the mineral filler into the mixture uniformly and in the desired quantities.  Provide appropriate equipment for accurately proportioning the relatively large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11  TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding Stone Mastic Asphalt Concrete mixture in silo type storage bins is permitted provided that the characteristics of the Stone Mastic Asphalt Concrete mixture are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Dispose of rejected Stone Mastic Asphalt Concrete mixture at no cost to the Department.

407-3.12  SPREADING AND PLACING.  Submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, weight, and operating speed of rollers.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

Place Stone Mastic Asphalt Concrete mixture upon an approved surface, spread and strike off and compact to the required compacted thickness.  Spread and compact in one layer if the total thickness is 75 mm or less.  Use asphalt pavers to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

Use hand tools to spread, rake, and lute the Stone Mastic Asphalt Concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.  In such areas, compact the Stone Mastic Asphalt Concrete mixture to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture that is contaminated or segregated will be rejected.

Pave adjacent traffic lanes to the same elevation within 24 hours when the section of roadway being paved is open to traffic unless prevented by weather or other factors beyond control.  Place approved material against the outside pavement edge when the drop-off exceeds 50 mm.

When multiple lifts are specified in the contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Do not pave against new concrete curb until it has cured for at least 72 hours..

407-3.13 COMPACTION.  Immediately after spreading, thoroughly and uniformly compact the Stone Mastic Asphalt Concrete mixture by rolling.

Roll with a minimum of three steel wheel rollers of a minimum weight of 11 megagrams each.  Adjust rolling procedures to provide the specified pavement density.  Operate rollers at a uniform speed not to exceed 5 kilometers/hour and with the drive roller nearest the paver.  Roll until all roller marks are eliminated and the specified pavement density has been obtained.

Prevent adhesion of mixture to the rollers by moistening the wheels with water mixed with detergent or other approved material.  Replace rollers showing evidence of excessive pick-up.

Stop rolling operations once sufficient in-place density has been achieved.  Where migration of asphalt cement and filler to the compacted pavement surface has occurred, remove and replace with fresh Stone Mastic Asphalt Concrete mixture.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with WAQTC FOP FOR AASHTO T 209.  For the first lot of Stone Mastic Asphalt Concrete, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of the lot.  Acceptance testing for field density will be determined in accordance with WAQTC FOP FOR AASHTO T 166/T 275 except that a 150 mm diameter core is required.  (Acceptance testing for field density of leveling course will not be done.)

Grade with rakes and lutes and compact with mechanical tampers areas not accessible to rollers.  Use a trench roller in depressed areas to achieve the required compaction.

Remove any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective and replace with fresh Stone Mastic Asphalt Concrete mixture and compact to conform with surrounding areas.  Remove and replace any area showing an excess or deficiency of asphalt cement.

Do not leave rollers, other equipment, or vehicles standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14  JOINTS.  Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP FOR AASHTO T 166/T 275.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Remove full depth improperly formed joints resulting in surface irregularities, replace with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compact.  Do not roll joints after the material has cooled below 65 degrees Celsius.  All pavement removal shall be precut to a neat line with a power driven saw.

Apply a tack coat of asphalt cement or asphalt emulsion on all cold joints and allow to break prior to placing any fresh Stone Mastic Asphalt Concrete mixture against the joint.  Apply the tack coat just prior to paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset longitudinal joints in one layer from those in the layer immediately below by at least 150 mm.  Align the joints in the top layer at the centerline or lane lines.  Where pre-formed marking tape striping is required, offset the longitudinal joint in the top layer not more than 150 mm from the edge of the stripe.

407-3.16  PATCHING DEFECTIVE AREAS.  Remove any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective.  Skin patching is not permitted.  Remove defective materials for the full thickness of the course.  Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with tack coat conforming to Section 402 and allow to cure.  Place and compact fresh Stone Mastic Asphalt Concrete mixture in sufficient quantity so that the finished surface conforms to grade and smoothness requirements.  Compact the Stone Mastic Asphalt Concrete mixture to the density specified.  No payment shall be made for material replacing defective material.  All costs associated with patching defective areas shall be borne by the Contractor.

407-3.17  TEST SECTION.  Place a minimum of 270 megagrams of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving.  The test section is used to adjust the Job Mix Design asphalt cement content and also to familiarize the Contractor's personnel with the laydown and compaction of Stone Mastic Asphalt Concrete mixture.

Stone Mastic Asphalt Concrete mixture placed in the test strip that meets specifications will be measured and paid for at contract prices.  No payment will be made for mixture that does not meet specifications.  If the test strip is placed within the project limits and does not meet specifications, it shall be removed at the Contractor's expense.

407-4.01  METHOD OF MEASUREMENT.  Stone Mastic Asphalt Concrete mixture will be measured by the megagram in accordance with Section 109.  The weight used shall be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 407-4.03.

Asphalt cement will be measured by the megagram based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by WAQTC TM 4, or WAQTC FOP FOR AASHTO TP 53.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If the asphalt cement content is determined by WAQTC TM 4, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin.  If the asphalt cement content is determined by WAQTC FOP FOR AASHTO TP 53, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin, and by 0.3 percent for Stone Mastic Asphalt Concrete containing cellulose.

The Engineer may direct at any time that tankers be weighed before and after unloading in his presence.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste, or diversion will be computed in a manner to be determined by the Engineer.  The weight of asphalt cement in waste Stone Mastic Asphalt Concrete will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Longitudinal joints will be measured by the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

407-4.02  ACCEPTANCE SAMPLING AND TESTING.  The quantity of  Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  The Engineer shall perform acceptance sampling and testing.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams.  The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection.  If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot.  The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection.  The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing.  If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed.  If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result.  If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances.  Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees C prior to completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction.  Asphalt cement content will be determined by WAQTC TM 4, or WAQTC FOP FOR AASHTO TP 53 with the exception that the moisture content will be determined by WAQTC TM 6.

Samples taken for the determination of aggregate gradation will be from the same location as samples taken for asphalt cement content.  Aggregate gradation will be determined in accordance with WAQTC FOP FOR AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP FOR AASHTO TP 53) has burned off the asphalt cement.

Cut one full-depth core sample with a  diameter of 150 millimeters from the finished lift from each sublot within 24 hours of final rolling.  The  core sample will be used for density acceptance testing in accordance with WAQTC FOP FOR AASHTO T 166/T 275.  Neatly cut the core sample with a core drill at the randomly selected location marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from Stone Mastic Asphalt Concrete mats on bridge decks.  Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Backfill all voids left by sampling with fresh Stone Mastic Asphalt Concrete mixture and compact within 24 hours of sampling.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Samples will be evaluated for acceptance in accordance with Subsection 407-4.03.

A retest of any sample outside the limits specified in Table 407-4 may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s).  The Engineer will mark the sample location for the retest.  Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s).  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

407-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when the contract quantity equals or exceeds 4,500 megagrams except as defined in Subsection 407-4.02.  The longitudinal joint density price adjustment will apply when Stone Mastic Asphalt Concrete quantities are equal to or greater than 900 megagrams.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis Method as specified in Subsection 106-1.03 to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The Contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lowest of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture that includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material that appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ  =  summation of

x=Σxn

x  =  individual test value to xn

n  =  total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the 0.075 mm sieve.  x is rounded to the nearest hundredth for asphalt content and the 0.075 mm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the 0.075 mm sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the 0.075 mm sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the 0.075 mm sieve.  Use s = 0.020 for the 0.075 mm sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL).  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances  in Table 407-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG). The LSL  for density is 92 percent of MSG and the USL is 96%.

4.	Compute the upper quality index (QU):

QU=USL-xs

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

QL=x-LSLs

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit that corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit that corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

- Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Round the Composite Pay Factor (CPF) to the nearest hundredth.

Table 407-5 is used to determine the weight factor (f) for each sieve size and asphalt  cement content.

Table 407-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 19.0 mm sieve | TV-5.0 | TV+5.0 |
| 12.5 mm sieve | TV-5.0 | TV+5.0 |
| 9.5 mm sieve | TV-5.0 | TV+5.0 |
| 4.75 mm sieve | TV-4.0 | TV+4.0 |
| 2.36 mm sieve | TV-4.0 | TV+4.0 |
| 1.18 mm sieve | TV-4.0 | TV+4.0 |
| 0.600 mm sieve | TV-4.0 | TV+4.0 |
| 0.300 mm sieve | TV-3.0 | TV+3.0 |
| 0.150 mm sieve | TV-3.0 | TV+3.0 |
| 0.075 mm sieve | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.40 | TV+0.40 |
| Density | 92% | 96% |

Table 407-5

WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| 19.0 mm sieve | 3 |
| 12.5 mm sieve | 5 |
| 9.5 mm sieve | 6 |
| 4.75 mm sieve | 10 |
| 2.36 mm sieve | 4 |
| 1.18 mm sieve | 4 |
| 0.600 mm sieve | 4 |
| 0.300 mm sieve | 6 |
| 0.150 mm sieve | 8 |
| 0.075 mm sieve | 10 |
| Asphalt % | 40 |

407-5.01  BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-strip additives will be subsidiary to Item 407(2), Asphalt Cement, Grade PG 58-28.

Stabilizing additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for Anti-Strip Additive or Asphalt Price Adjustment pay items.  The approved Job Mix Design will initiate Item 407(3), Anti-Strip Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(4), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 407-4.02.  The Asphalt Price Adjustment will be algebraically added to the Contractor's payment for Stone Mastic Asphalt Concrete.  Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $64.50  / Megagram

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest    value.

Longitudinal joint densities less than 91 percent of MSG as defined in Subsection 407-3.14 will be measured in accordance with Subsection 407-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 407(1) Stone Mastic Asphalt Concrete | Megagram |
| 407(2) Asphalt Cement, Grade PG 58-28 | Megagram |
| 407(4) Asphalt Price Adjustment | Contingent Sum |

(08/19/02)R163M98

THIS PAGE INTENTIONALLY LEFT BLANK

Add the following Section:

Section 511
Modular Block Retaining Walls

Special Provisions

511-1.01 DESCRIPTION. The Modular Block Retaining Walls shall be constructed at the locations shown on the plans and as provided in these specifications.  The Modular Block Retaining Walls to be constructed shall consist of a precast modular masonry product specifically engineered for the retention of earth.  The modular units shall be a gravity system and shall lock together vertically by pins.  The pins shall also be connected to geogrid reinforcement where indicated in the Plans or working drawings.

The Contractor shall submit a modular block system for approval.  The submittal for the  modular block retaining wall shall include complete working drawings for the wall system in accordance with the provisions in Subsection 105-1.02 of the Standard Specifications.  The Contractor shall verify the existing ground elevations and conditions at the site before preparing the final working drawings.  Said working drawings shall contain all information required for the proper construction of the system and any required revisions or additions to drainage or other facilities.  The working drawings shall be supplemented with calculations for the particular installation.  Said working drawings and calculations shall demonstrate the internal stability as well as the external stability of the modular block retaining wall and shall be signed and sealed by an Engineer who is registered as a Civil Engineer in the State of Alaska.  The Contractor shall allow the Engineer 3 weeks to review the working drawings and calculations after a complete set of working drawings and calculations are submitted by the Contractor.

Heights, lengths, and depths of Modular Block Retaining Wall systems may vary somewhat from the Plans, but begin and end of wall locations and top of wall elevations shall not be less than those shown on the Plans.  Modular Block Retaining Wall shall battered at 1H to 8V.

The height and length to be used for any system shall be the minimum for the system that will effectively retain the earth behind the structure for the loading conditions, profile, or slope lines shown on the plans or on the approved working drawings.  In addition, if the Plans show limiting parameters for the systems, the system selected shall conform to those parameters.

The construction of the Modular Block Retaining Wall system shall conform to the details shown on the plans and shall be constructed in accordance with the manufacturer’s instructions.  The supplier shall provide technical assistance and training to the Contractor.  The Contractor shall provide evidence of prior installation experience with the specific product being used.

511-2.01 MATERIALS. Materials furnished for the Modular Block Retaining Walls shall conform to the following:

GENERAL. The Contractor shall make his own arrangements to purchase and/or manufacture the pre-cast modular block units, attachment devices, and all other necessary components as shown on the Plans.  Materials not conforming to the Plans or specifications, shall not be used without written consent from the Engineer.

1.	Modular Block Units. The units shall be precast in conformance with the manufacturer's requirements and the following additions:

a.	Handling, Storage and Shipping: All units shall be handled, stored, and shipped in such a manner as to protect them from chipping, discoloration, cracks, and fractures.

b.	Rejection: Units shall be rejected because of failure to meet any of the requirements specified above.  In addition, any of the following defects shall be sufficient cause for rejection.

1)	Defects caused by faulty casting.

2)	Defects indicating honeycombed or open texture concrete.

3)	Cracked or severely chipped units.

4)	Unreasonable color variation on front face of unit.

c.	Color: Block color shall be buff. Contractor shall submit samples of colors for approval by the Project Landscape Architect.

2.	Soil Reinforcing and Attachment Devices. All reinforcing and attachment devices shall be carefully inspected to insure they are true to size and free from defects that may impair strength and durability. The geogrid shall meet the requirements of AASHTO Standard Specifications for Highway Bridges, latest Edition, and per the modular block unit suppliers design recommendations.

3.	Backfill Materials. All backfill materials for modular block retaining walls shall conform to requirements for Selected Material, Type A, as set forth in Subsection 703-2.07 Selected Material.

CONSTRUCTION REQUIREMENTS

511-3.01 EXCAVATION AND FOUNDATION. Excavation and preparation of the foundation shall be in conformance with Section 205, Excavation, Backfill and Foundation Fill for Structures.

Foundation Preparation. The foundation for the modular block retaining wall structure shall be graded level for a width as shown on the Plans or shop drawings.  Prior to wall erection, the foundation backfill shall be compacted to meet the requirements of Section 301.  Any foundation soils found to be unsuitable shall be removed and replaced with backfill as per Section 205.

511-3.02 WALL ERECTION. A field representative from the proprietary modular block wall system being used shall be available during the erection of the wall.  The Services of the representative shall be at no additional cost to the Department.

Precast masonry block units shall be placed so that their final position is battered at 1H to 8V.  The masonry block units shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds.  While placing backfill material behind the first course of masonry block units, place backfill material at the front of the units. Remove all excess backfill material from the top surface of all masonry block units prior to placement of the next course of masonry block units.

Backfill Placement. Backfill placement shall closely follow erection of each course of masonry blocks.  Backfill shall be placed in such a manner as to avoid any damage or disturbances of the wall materials or misalignment of the facing panels.  Any wall materials which become damaged during backfill placement shall be removed and replaced at the Contractor's expense.  Any misalignment or distortion of the masonry block units due to placement of backfill outside the limits of this specification shall be corrected by the Contractor .

Backfill shall be compacted to 95 percent of the maximum density as determined by Alaska Test Method T-12 or AASHTO T 180.  The maximum lift thickness after compaction shall not exceed 200mm.  The Contractor shall decrease this lift thickness, if necessary to obtain the specified density.  Field density will be determined using Alaska Test Method T-3 or T-11 by the Engineer.

Ride-on mechanical compaction equipment shall be operated no closer than 900mm from the masonry unit back face.  Compaction within 900mm of the back face of the wall facing may be achieved by using a lightweight mechanical tamper, roller or vibratory system.

A minimum of one density test shall be taken by the Engineer after every three levels of blocks are placed.  Soil tests shall be taken no closer than 900mm from the back surface of the masonry modular block units.

At the end of each day's operation, the Contractor shall slope the last level of backfill away from the wall to rapidly direct water runoff away from the wall face.  In addition, the Contractor shall not allow surface runoff from adjacent areas to enter the wall construction site.

511-401 METHOD OF MEASUREMENT. Modular Block Retaining Walls will be measured by the square meter of wall face measured along the face of the wall, and including that part of wall which is below grade as indicated on the Plans or working drawings.  Measurement shall take place prior to fill of backfill.  Measurement shall be by vertical face, not parallel to batter angle.

511-5.01 BASIS OF PAYMENT. The contract price paid per square meter of wall face for Modular Block Retaining Walls shall include full compensation for furnishing all labor, materials, tools, equipment, and incidentals and for doing all work involved in constructing the earth retaining structure; including precast masonry blocks, random backfill soil, excavation, aggregate base course leveling pad, and all parts of or appurtenances to the modular block earth reinforcement system, complete in place, as shown on the Plans and working drawings, as provided in the Standard Specifications, Standard Modifications and these Special Provisions, and as directed by the Engineer.

Payment will be made under:

Pay Item No.	Pay Item 	Pay Unit

511(3)	Modular Block Retaining Walls	Square Meter

Section 603
Culverts and Storm Drains

Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts.

Installation of storm drain pipe shall include installation of insulation board where necessary due to close proximity of the storm drain to existing water or sanitary sewer facilities.

603-2.01 MATERIALS. Add the following: Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm.

(5/31/96)R42M

Standard Modifications

In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.

(02/08/01)M95

603-3.03 JOINING PIPE.

2. Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.”

(02/08/01)M95

Special Provisions

Add the following Subsection:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

Installation of insulation board will not be measured.

Work and materials required to abandon manholes shall not be measured.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.

(5/31/96)R42M

Installation of insulation board will be subsidiary to pipe items.

Abandoned manholes shall be subsidiary to pipe items.

Section 604
Manholes And Inlets

Special Provisions

604-1.01 DESCRIPTION. Add the following:  This work also includes the repair of cracks in existing storm drain structures including manholes and inlet boxes where described on the Plans.  This work also consists of replacing frames, grates or covers, and grade rings for existing structures where described on the Plans.

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 25 mm concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

6.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the local DOT maintenance station.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 50 mm larger than the outside diameter of the new pipe.  Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 75 mm formed hole approximately 0.6 m below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

Add the following:

Repair Structure Cracks.  Clean of all loose debris from crack for full depth.  Fill cracks full depth with non-shrinking cement mortar joint grout.

Replace Inlet Frame and Grate.  Work will be completed in accordance with the requirements for “Adjust Existing Manhole,” with the exception that new materials shall be provided, and no salvage items will be used.

Replace Manhole Cover, Frame and Grade Ring.  Work will be completed in accordance with the requirements for “Adjust Existing Manhole,” with the exception that new materials shall be provided, and no salvage items will be used.

604-4.01 METHOD OF MEASUREMENT. Add the following: Frames, grates and lids will not be measured for payment.

Repair Structure Cracks shall be measured by each structure repaired.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.

Delete Item 604(1) Storm Sewer Manhole and add the following new pay items:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Drain Manhole, Type I	Each

604(1B)	Storm Drain Manhole, Type II	Each

604(13A)	Replace Inlet Frame and Grate	Each

604(13C)	Replace Manhole Cover, Frame and Grade Ring	Each

604(22)	Repair Structure Cracks	Each

(9/1/00)R43M98

Section 606
Guardrail

Special Provisions

606-3.07 REMOVAL AND DISPOSAL OF GUARDRAIL. Delete the last sentence and substitute the following: Notify the Engineer, five (5) days prior to removing guard rail for disposal.  At that time, the Engineer will physically identify portions of guardrail to be salvaged.  All guardrail and associated hardware so designated will be delivered to the Department of Transportation Maintenance Yard located in Anchorage.  All remaining items removed become the property of the Contractor.

(9/8/00)R259M98

Section 607
Fences

Special Provisions

607-1.01 DESCRIPTION. Add the following after the first paragraph: This work shall also consist of construction of trellis fence, post and rail fence, and rock fence posts.

Trellis fence consists of galvanized tubular steel posts, galvanized flat steel straps and galvanized steel cable and all related fittings and hardware.  The height and location of the trellis fence must conform to the Plans or as designated in the bid schedule.

Post and rail fence consists of split rail cedar posts and rails and related hardware.  The height and location of the split rail fence must conform to the Plans or as designated in the bid schedule.

Rock fence post consists of concrete column base with river rock veneer.  The height and location of the rock fence posts must conform to the Plans or as designated in the bid schedule.

607-2.01 MATERIALS. Add the following:

Rock Fence Post		Subsection 703-2.14

Trellis Fence			Subsection 710-2.12

Posts and Rails		Subsection 710-2.13

607-3.01 CONSTRUCTION REQUIREMENTS.

Standard Modification

In the ninth paragraph, change “minimum” to “maximum”.

(06/25/99) M73

Add the following:

Remove and dispose existing chain link fence where guardrail trellis fence is to be located, including posts, and all related items.  Removal and disposal shall be subsidiary to Item 607(7) Trellis Fence.

Add the following Subsections:

607-4.01 METHOD OF MEASUREMENT. Add the following:

Trellis Fence. By the meter at the base of the lowest rail parallel to the guardrail.

Post and Rail Fence. By the meter at the base of the lowest rail parallel to the guardrail.

Rock Fence Post. Per each as a complete unit in place as shown on plans and details.

607-5.01 BASIS OF PAYMENT. Add the following: Removal and disposal of chain link fence are subsidiary to Item 607(7) Trellis Fence.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

607(7)	Trellis Fence	Meter

607(8)	Post and Rail Fence	Meter

607(9)	Rock Fence Post	Each

Section 608
Sidewalks

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work also consists of constructing asphalt pathway(s) in conformance with the Plans.

This work shall also consist of providing equipment, materials and labor necessary to install cast-in-place Patterned Concrete.  Patterned Concrete shall be imprinted concrete as shown on the Plans.

This work shall also consist of construction curb ramps and retrofitting existing curb ramps with composite detectable warning tiles as shown on the Plans, or as directed by the Engineer.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG52-28	Subsection 702-2.01
Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.	4450
Percent Voids, Total Mix	2-5
Compaction, Blows/side	50

Add the following:

Patterned Concrete shall conform to Section 501, Structural Concrete, Class A, except that Subsection 501-3.02 Batching is modified as follows:

Under item 3. Aggregates, delete the third paragraph.

Add the following: For Patterned Concrete, concrete shall be Class A with the following modification:

1.	Air Entrainment - ***Deleted *** Air entraining agents complying with ASTM C 260 may be used.

2.	Imprint the Patterned Concrete using one of the following imprinting systems and patterns:

a.	“Flagstone” pattern, Bomanite, John-Wayne Construction Co., Anchorage, Alaska; (907-344-3511)

b.	“California Fieldstone” pattern, Stampcrete, Stampcrete International, Ltd. 325 commerce Blvd., Liverpool NY 13088, (800-233-3298); web site: stampcrete.com

c.	“Flagstone” pattern, Design-Crete by Symons Corporation, 200 E. Touhy Avenue, Des Plaines, Il, 60018; (847-298-3200)

608-3.01 CONCRETE SIDEWALKS. Delete the fifth paragraph and substitute the following: Expansion joints shall be placed along all structures and about all features that project into, through., or against the concrete.  An expansion joint shall be constructed at the intersection of the sidewalks; between curbs and sidewalks (except parallel curb); and at the beginning and end of curb returns.  Expansion joint material shall conform to the requirements of AASHTO M-33.  This material shall extend the full width of the structure and shall be cut to such dimensions that the base of the expansion joint shall extend to the subgrade and the top shall be depressed not less than 6 mm nor more than 12 mm below the finished surface of the concrete.  The material shall be of one (1) piece in the vertical dimension and shall be securely  fastened in a vertical position to the existing concrete face against which fresh concrete is to be placed.  After the concrete has set, the expansion joints shall be filled flush to the finish concrete surface with joint sealer.  Before sealing, the joint shall be cleaned of all dirt, gravel, concrete mortar, and other extraneous material.  Sealing shall be done in a neat workmanlike manner.

Contraction joints: Transverse contraction joints, cut to a depth of 25 mm, prior to the final set of the concrete, shall be tooled in the sidewalks at intervals of 1.5 meters, and at 3.0 meter intervals in the curb and gutter.  Where the sidewalk adjoins the curb (parallel to it) contraction joints in the sidewalk and curb shall be made to match where practicable.

Add the following: Contractor shall provide a 1.2 meter by 1.2 meter sample of the proposed finish for approval by the Engineer prior to beginning Patterned Concrete work.  All other Patterned Concrete shall match the approved panel.

Final groove dimensions in the stamped pattern shall be no deeper than 6 mm and no wider than 12 mm.  Patterned Concrete shall be placed in such a fashion that a uniform appearance and texture will be maintained along the length of the sidewalk.  Any significant difference in texture, pattern or appearance between two adjacent concrete panels, or from the sample panel, will result in the removal and replacement of concrete panels by the Contractor at no additional cost.

608-3.03 SIDEWALK RAMPS. Delete this subsection and substitute the following:

608-3.03 CURB RAMPS. Construct curb ramps according to the details and locations shown on the Plans.

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish.

(06/11/02)R256M98

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with Subsection 608-3.02, Asphalt Sidewalks.

608-3.05 PATTERNED CONCRETE. In addition to meeting the requirements of Section 501, the Patterned Concrete shall include all excavation, compaction, steel reinforcement, dowels, construction, and expansion joint materials, patterned concrete and incidental work required to complete work per the plans.  The patterned concrete shall be installed prior to asphalt paving.

Protection of Patterned Concrete. When asphalt paving, observe the following requirements:

Do not place the asphalt pavement until the concrete has cured enough to prevent damage from the paving operation.

When crossing over the concrete surface with vibratory rollers, turn the vibrator off.

Place, spread, and roll the asphalt so that the concrete will not be damaged.

Cover the concrete surface with kraft paper or other approved material, suitable to withstand high asphalt temperatures and vehicle traffic to protect the concrete surface from contaminants.

Prior to final acceptance, the Contractor shall repair all damaged concrete and clean all surface contamination at his expense, to the satisfaction and approval by the Engineer.

608-4.01 METHOD OF MEASUREMENT.

Special Provisions

Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp. By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles, backing curb and landings necessary to provide a single street-level access.

(06/11/02)R256M98

Add the following:

Asphalt Pathway. Will be measured by the megagram in accordance with Section 109, Measurement and Payment.  Asphalt cement and anti-stripping additive will not be measured for payment.

Patterned Concrete. Will be measured by the square meter of finished surface.

608-5.01 BASIS OF PAYMENT. Add the following: Backing curb, will be subsidiary to Item 608(6), Curb Ramp.

The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp.

(06/11/02)R256M98

Asphalt cement and anti-stripping additive for Asphalt Pathway will not be paid for separately, but will be subsidiary to Item 608(7) Asphalt Pathway.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

Payment for Patterned Concrete will be full compensation for all work to complete the item.  No separate payment will be made for surface preparation, or the test panel, these items will be considered subsidiary to Item 608(17B) Patterned Concrete.

Delete Item 608(6), Sidewalk Ramp

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

608(6)	Curb Ramp	Each

608(7)	Asphalt Pathway	Megagram

608(17B)	Patterned Concrete	Square Meter

Section 609
Curbing

Special Provisions

609-1.01 DESCRIPTION. Add the following:  This work shall also include the construction of concrete edging as shown on plans.  Edging shall be cast-in-place concrete as shown on Plans.

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.

(2/1/00)R202M98

609-3.05 CURB RAMPS. Delete this Subsection in its entirety.

(06/11/02)R256M98

609-4.01 METHOD OF MEASUREMENT.

Standard Modification

In the first paragraph, after “drainage structures” insert “or ramps”.

(06/25/99)M 75

Special Provisions

Delete the second paragraph.

(06/11/02)R256M98

Add the following:

Concrete Edging. By the meter along the face of the concrete edging at the finished grade elevation.

609-5.01 BASIS OF PAYMENT. Delete Pay Item 609(3), Curb Ramp.

(06/11/02)R256M98

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

609(8)	Concrete Edging	Meter

Section 615
Standard Signs

Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

7.	Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  The Engineer will contact the Maintenance and Operations Station Foreman, Ira Grindle @ 269-5636 approximately one week before salvage operations begin.  M&O will inspect all salvaged items before they are delivered to the M&O yard and will identify and mark those items which are in good condition and can be re-used.  The remaining salvaged items shall become the property of the Contractor.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer and M&O.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal and relocation of existing signs, removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

Section 616
Thaw Pipe and Thaw Wires

Special Provisions

616-2.02 THAW WIRE. Under Item 3 “Controls,” add the following:

d.	Use a spring wound mechanical line voltage timer.  Contacts close during timer period.  Contact rating 20 amps inductive at 120 volts.  Time period is 12 hours without hold.  Intermatic PFGH or equivalent.

616-3.02 THAW WIRE. Delete the table at the top of page 296 and substitute the following:

| Nominal Voltage/Phase | Grounded | Ungrounded |
| --- | --- | --- |
| ## 120 volt, single phase, 2 wire | ## White | ## Black |
| 120/240 volt, single phase 3 wire | ## White | ## Black/Red |

(8/28/00)R216M98

Standard Modifications

616-3.02 THAW WIRE. In the table under item 5. Color Coding, move “Red” to the Ungrounded column for 3-wire conductors.

(02/08/01)M96

616-3.03 THAW WIRE REMOVAL. Where indicated on the Plans, remove existing thaw wire conduit and thaw wire in its entirety.

616-5.01 BASIS OF PAYMENT. Add the following:  The lump sum price paid for thaw wire installation includes full compensation for all work and materials necessary to install the thaw wire systems as detailed on the Plans.  Materials include all fittings, standpipes, and heat trace load centers.

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

616(4A)	Thaw Wire Installation	Lump Sum

616(7)	Thaw Wire Removal	Lump Sum

Section 618
Seeding

Special Provisions

618-1.01 DESCRIPTION. Delete this Subsection and substitute the following:  All new or disturbed slopes and any other areas directed by the Engineer shall be overlaid with topsoil and seeded with seed mix.  This work shall consist of grading the soil, followed by the application of seed, mulch, fertilizer, and rolling.  It is intended to provide a living ground cover as soon as possible on all slopes.

618-2.01 MATERIALS. Add the following:

Mulch	Subsection 727-2.01.

618-3.01 SOIL PREPARATION. Add the following:  Apply seeding as detailed below immediately after the shaping of the slopes.  Cover all areas to be seeded with topsoil in accordance with Section 620 and grade with a scarifying slope board or rake.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete raking as soon as topsoil is placed.  The Contractor may round the top and bottom of the slopes to create a pleasing appearance, but drainage flow lines shall not be disrupted.  The performance of this work is subsidiary to seeding and will not be paid for separately.

618-3.02 SEEDING SEASONS. Add the following:  If seeding cannot be completed prior to July 15th then a dormant seeding application of the seed mix shall be performed after the first frost or October 1st whichever occurs last.  This dormant seeding application of the seed mix may be performed after the closing of contract time as indicated in subsection 105-1.15, Contract Completion.

618-3.03 APPLICATION. Add the following to the first paragraph:  For Type A seed mix, seed, mulch, and fertilizer shall be applied by the hydraulic method with the application rates as shown in the following table.  Contractor shall take extra precautions when applying seed mixtures, and shall not apply seed mix within planting beds and all shall take care in avoiding water bodies in this project.

Item	Application Rate (per ha)

Seed Mix (Schedule A)	48.8 kg

Mulch	1710 kg

Fertilizer (16-16-16)	586 kg

618-3.04 MAINTENANCE OF SEEDED AREAS. Add the following:  The Maintenance Period for all seeded areas shall be 60 days from the time of the acceptance of the hydroseeding.

A reapplication of fertilizer with water shall be applied between May 1 and September 15 of the following season at a rate of one-half the initial application to all areas that have received Schedule A seed mix, as shown on the Plans.  Contractor shall notify the Engineer in writing two days prior to the application of fertilizer, allowing the Engineer ample time for verification of fertilizer application during the maintenance period.

Contractor shall ensure that the seeded areas stay moist during germination and seedling establishment (as defined by the grass plants attaining a height of approximately 50mm, and showing signs of vigorous growth).  The Contractor shall be prepared to water the seeded areas 4 to 5 times per day until seedlings have become established.

Water should saturate the first 25mm of soil, but should not cause soil erosion or wash seed away.  The Engineer will conduct inspections during the germination period following application of seed, to verify the application of adequate amounts of water.  Should inspections reveal that an adequate amount of moisture is not being applied to the seeded areas, the Engineer will place the Contractor on notice that immediate applications of water be applied and failure to do so will result in a restart of the 60-day maintenance period beginning the day of proper application of moisture.  No additional compensation will be allowed the Contractor for additional applications of water.

If the Contractor fails to apply adequate moisture during the germination period for 5 consecutive days, or after 2 notices of watering requirements without immediate response, the Engineer may declare the seeding unacceptable.  The Contractor will be required to reseed areas that have not been kept moist.  Once adequate water is applied, the Engineer shall restart the 60-day maintenance period beginning the day of proper application of moisture or reseeding.

618-5.01 BASIS OF PAYMENT. Add the following:  Fertilizer, and mulch, as described above, including any required reseeding will not be paid for directly but will be subsidiary to Item 618(2A), Seeding (Schedule A).

The work described under Subsection 618-3.01 Soil Preparation will not be paid for separately but will be subsidiary to seeding.

Water required for the hydraulic method of application will not be paid for separately, but will be subsidiary to seeding.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

618(2A)	Seeding (Schedule A)	Kilogram

Section 620
Topsoil

Special Provisions

620-2.01 MATERIALS. Delete paragraph and substitute the following:  Topsoil shall be as modified in Section 726.

620-3.01 PLACING. Delete paragraph in its entirety and substitute the following:

For all areas shown on the plans, or as directed by the Engineer that are to be seeded with Type A seed mix, (as described in Section 618), topsoil shall be evenly spread on the designated areas to a minimum depth after settlement of 100 mm.  Settlement shall be achieved by rolling the topsoil with a water-filled drum approved by the Engineer.

Grade topsoil with a scarifying slope board or rake.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete the grading as soon as topsoil is placed.   The resultant indentations shall be perpendicular to the fall of the slope.  The Contractor may round the top and bottom of the slopes to facilitate working the slope and to create a pleasing appearance, but drainage flow lines shall not be disrupted.

Do not place topsoil when the site or the topsoil itself is in a condition detrimental to the work.  Keep all roadway surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil, Class .

(9/11/96)R53

Section 621
Planting Trees and Shrubs

Special Provisions

621-1.01 DESCRIPTION. Add the following: This work shall also include installation of willow sprigs, preparation of planting beds, furnishing and installing shredded bark mulch as shown on Plans.

621-2.01 PLANT STOCK. Add the following: Refer to 621-3.03 PLANTING for provision of Certified Arborist.

A Certified Arborist or botanist shall certify plant species, which are scheduled, but not included, in the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature.  Variety and species shall be as scheduled on the Contract Drawings.  Trees and shrubs are not to be bare root.

1.	Nursery Stock.

b.	Delete paragraph in its entirety and substitute the following: Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

Add the following:

c.	Perennials shall have been growing for at least one year and exhibit strong root growth pattern within containers.  Perennial roots shall be visible and thriving when plant is pulled out of its container for inspection.  Weeds, grasses and foreign materials shall be completely removed from the containers of all plants.  Complete removal includes removal of all related roots.  Perennials shall be easily identifiable through thick healthy leaf growth.  Dormant plants will not be accepted.

d.	Coniferous trees shall not come from or have the appearance of trees from Christmas tree farms.  Coniferous trees that appear to be too heavily pruned, sheared, or that have their bottom branches removed, or that do not have acceptable root balls shall be rejected.   The Engineer shall be the sole judge of the plant material.

621-2.02 FERTILIZER. Add the following:  Fertilizer for all trees, shrubs, and groundcovers, and Sod vegetation shall be fertilizer 8-32-16.  Fertilizer shall be applied at a rate determined by the Engineer, as described in Section 726, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.  Where a soil analysis is unavailable, fertilizer 8-32-16 shall be applied at a rate of 34.2 grams per square meter, once approved by the Engineer.

621-2.03 LIMESTONE. Add the following:  Limestone shall be applied at a rate determined by the Engineer, as described in Subsection 726-1, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

Add the following Subsection:

621-2.08 SHREDDED BARK MULCH. Shredded bark mulch shall consist of spruce, Douglas Fir, pine, or hemlock bark shredded with maximum length of 5 cm and no more than 30% of the mix with particles less than 7mm in size.  The shredded mulch shall not contain resin, tannin, non-organic or foreign elements in quantities that could inhibit plant growth.  The mulch shall have the characteristics to be spread evenly so as to form a uniform consistent mat that inhibits weed growth and will not blow or wash away.  The shredded bark mulch shall be aged at least one year and be a deep, dark, brown color.  Chipped wood is not acceptable.

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Prior to final placement of all plant materials, after planting pits have been filled with topsoil, the Contractor shall mark with flags, or by other means, the locations where trees and shrubs are to be installed. The marked locations shall be reviewed and approved by the Engineer prior to planting. The Contractor shall notify the Engineer 4 working days prior to plant location inspection.

621-3.03 PLANTING.

1.	Plant Season.

Delete item 1.  Plant Season, and substitute the following:

1.	Plant Season.

a.	Locally grown:  When native species of locally-grown trees and shrubs are furnished for the project, they shall be planted between June 1 and September 15. Trees and shrubs shall be fully leafed-out prior to planting.

b.	Imported and Nursery Grown: When plants are shipped in from out-of-state, or have been container grown in a nursery for at least one year, handling shall be in accordance with nursery recommendations.  Plants imported from out-of-state shall be planted between May 15 and August 1.

Delete item 2.  Excavation. and substitute the following:

2.	Prepare Planting Bed.

a.	Planting beds must be completely prepared prior to placement of plants.  Planting bed preparation includes excavation, loosening of subgrade soils and placement of edging and topsoil.  Planting beds shall be prepared no more than 5 days prior to planting.

b.	Prior to excavation of planting areas, the Contractor shall ascertain the location of all utilities so that proper precautions may be taken not to disturb or damage any subsurface improvements.  Should obstructions or conflicts be found, the Contractor shall promptly notify the Engineer.  The Contractor shall prepare a revised plan that avoids conflicts with the Utility and meets the intent of the original plan to the extent possible.  The revised plan shall be submitted to and approved by the Engineer prior to construction of the planting bed.

c.	Plant bed size is as shown on plans and generally includes the area within the edging and as per details.  Should placement of individual plants be required due to field changes, the minimum planting bed size shall be no less than three times the size of the plants rootball.

d.	Planting beds with trees and shrubs shall be excavated to a depth of 450 mm.  All excavation is to be removed from the site and disposed according to specifications.

e.	Planting beds with only perennials shall be excavated to a depth of 300 mm.  All excavation is to be removed from the site and disposed according to specifications.

f.	All planting beds are to be tilled to a depth of 300mm below the excavated grade.

g.	Once tilled, subgrade shall not be mechanically compacted.  Heavy equipment shall not be use within planting beds.

h.	Soak planting beds with water.  Allow water to absorb in topsoil throughout planting bed.  Notify Engineer if planting beds are not draining properly.  Topsoil backfill shall be moist but not wet, during planting.  Do not plant until topsoil has no signs of excess water including pools, puddles, inability to compact or muddiness.

i.	Dig planting holes within the planting bed after plant locations have been approved by the Engineer.  Firmly tamp the base of the planting hole to assure plants will not settle to lower than their proper planting depth.  Water planting holes prior to planting if soil appears dry or if planting bed has not been planted within 24 hours of initial watering.

3.	Pruning.  Delete the last two sentences of paragraph (b.) in their entirety.

5.	Placing Plants.  Delete Paragraph (b) and substitute the following:

b.	Balled and burlapped plants, plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the plant itself.  Wire baskets, and burlap shall be clipped and laid flat on the bottom of the planting pit as indicated on the plans.  Containers shall be removed from the site.  The Engineer may reject any plants whose rootballs collapse during planting.

7.	Wrapping.  Delete this paragraph in its entirety, and substitute the following:

Plant materials shall not be wrapped.

8.	Staking and Guying.  Delete Paragraph (a) in its entirety, and substitute the following:

a.	Trees shall not be staked unless the Contractor determines staking to be essential to establishment of trees on the site.   The Contractor shall also be responsible for removing stakes one year after installation.

Add the following:

9.	Certified Arborist.

The Contractor shall retain the services of an arborist certified by the International Society of Arboriculturalists or American Association of Nurserymen whose experience and qualifications are acceptable to the Engineer.  The Certified Arborist shall oversee plant installation and shall inspect plants for health and vigor at least twice during the Plant Establishment Period, once per year.  The Certified Arborist’s resume shall be submitted at least 30 working days before the delivery of plant material.

The Certified Arborist shall inspect plants for health and vigor prior to installation, to assure the requirements of Section 621-2.01 for plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected prior to installation.  The Certified Arborist shall also be responsible for the following:

1.	The Certified Arborist shall oversee and approve plant installation and shall be present on-site for the first day of plant installation and again after 25% of installation is complete. Inspect the tree planting process to assure that planting techniques meet the Contract documents.

2.	The Certified Arborist shall, in written form, verify that plant quality and character, planting depth, pre- and post-water requirements meet specifications.

3.	Inspect plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.

4.	All pruning is to be under the direct on-site supervision of the Certified Arborist.

621-3.04 PERIOD OF ESTABLISHMENT. Delete the last sentence and substitute the following:  The Plant Establishment Period (PEP) shall be one complete growing season.  The growing season is May 1st  to October 15th.  The PEP shall begin when the maintenance schedule is approved by the Engineer and all required planting is complete and accepted for payment by the Engineer.  The PEP applies to all planting beds, trees and shrubs, and ground covers.

Watering is not required between October 15th and May 1st during the PEP.  The Contractor shall deep water all tree root balls and other plant materials as frequently as necessary to keep the immediate root areas moist at all times during the growing season.  The Contractor shall deep water all evergreen plants just prior to freeze-up in order to minimize over-wintering desiccation.  Contractor may also choose to apply anti-desiccants to conifers as approved by the Engineer. Rainfall will not be considered a substitute for deep watering unless permitted by the Engineer.

Trees and shrubs shall be pruned to remove disfigured, damaged, or dead branches.  Damaged trees or those that constitute health or safety hazards shall be pruned at any time of the year as required.  Evergreen trees shall not be pruned without prior approval of the Engineer.

The Contractor shall maintain the planting beds and seeded areas in a weed-free condition.  Weed removal shall be a routine maintenance activity.  Weeds include grasses and other undesirable plants within planting beds.

621-3.05 CLEANUP. Add the following:  Planted and seeded areas shall be kept clean of litter and garbage during the growing season.

621-3.06 PLANT REPLACEMENTS. Add the following:  Plants shall be replaced following the plans and specifications.  Plants which are dead or dying, shall be replaced within 48 hours of notification, June through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

621-3.07 MAINTENANCE. Add the following:  The maintenance period for this project for all plantings, plant materials shall be one year.  The maintenance period for seeding is covered under Section 618 Seeding and shall be 60 days.

The Contractor shall submit a maintenance schedule to the Engineer for approval, ten working days prior to the completion of the planting.

Maintenance includes the care of all trees, shrubs, ground covers, sod plantings, and seeded areas for the duration of the maintenance agreements, including the period of establishment, and the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of planted areas.  At the end of the growing season, and at the end of the maintenance agreement period, the Engineer and the Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of plantings.

a.	Watering.

The Contractor shall deep-water the root balls of all trees, shrubs, and perennials.  Deep watering shall provide water penetration through the root zone to a depth of the planting pits with a minimum of runoff.  Rain will not be considered as a substitute for deep watering unless permitted by the Engineer.

b.	Disease Control.

The Contractor shall apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained prior to the application of any regulated products.

c.	Pruning.

Prune all plant materials, with appropriate pruning techniques, to remove dead or dying wood and to improve the shape and or vigor of the plants.  Cuts shall not be painted. Pruning of flowering trees shall be scheduled to occur right after flowers drop off or decay.  Damaged trees or those that constitute health or safety hazards shall be pruned as directed by the Engineer at any time of the year.  Evergreens are not to be pruned without the approval of the Engineer.

d.	Fertilizer.

Fertilizer shall be applied to all trees, shrubs, and ground covers in the spring of the following year, prior to June 15 at the rates shown in table 621-1.  The fertilizer shall be applied as per manufacturer’s recommendations and thoroughly watered into the ground.   The Contractor shall notify the Engineer in writing 4 working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

TABLE 621-1
MAINTENANCE FERTILIZER SCHEDULE

Plant Type	Fertilizer			Application Rate

Coniferous Trees	8-32-16	34.2 grams per square meter

Deciduous Trees	8-32-16	500 g for each 25 mm of Caliper

Shrubs and Ground Cover	8-32-16	7 grams per  square meter.

621-4.01 METHOD OF MEASUREMENT. Delete this subsection and substitute the following:

The quantity of trees, shrubs and ground covers to be paid for shall be the actual number of plants, alive and healthy at the time of final inspection.

Plant Establishment Period will not be measured.

Upon the written approval of the Engineer for the Landscape Inspection, a 70% payment for installation of all landscape work shall be made upon the Contractor’s application for partial payment.  Final payment shall be made upon the Engineer’s written approval of the Final Maintenance Acceptance Inspection.

Furnishing and installing shredded bark mulch, topsoil backfill mix, fertilizing, disposal of unsuitable and surplus material, the maintenance period, and water for maintenance of plant materials will not be paid for separately, but will be subsidiary to Items 621 (1 - 5).  Water for seeding is measured under Section 618.

621-5.01 BASIS OF PAYMENT.  Add the following:

The accepted quantity of all plant materials planted will be paid for at 70% of the Contract price, per unit of measurement, for the pay items when they are acceptably planted.  Payment of the remaining 30% will be made after the Final Maintenance Acceptance Inspection has been conducted and the Engineer has approved the work.

If damaged plants are not replaced as required within 48 hours of written notice, the Engineer may replace or have replaced the damaged items and deduct the cost of said repair or replacement work from remaining payments.  The cost of said repair or replacement work will be based on paid receipts plus 10% administrative markup.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

621(1A)	Tree, Chokecherry (Prunus maackii), 65 mm cal.	Each

621(1B)	Tree, Birch, clump (Betula papyrifera), 65 mm cal.	Each

621(1C)	Tree, Larch (Larix siberica), 2 m tall	Each

621(1D)	Tree, Pine -Scotch (Pinus sylvestris), 2 m tall	Each

621(1E)	Tree, Spruce- Green (Picea pungens), 2 m tall	Each

621(1F)	Tree, Mountain. Ash (Sorbus aucuparia), 65 mm cal.	Each

621(2A)	Shrub, Currant - Alpine (Ribes alpinum), 600 mm tall	Each

621(2B)	Shrub, Maple - Amur (Acer ginnala), 600 mm tall	Each

621(2C)	Shrub, Highbush Cranberry (Viburnum opulus), 600mm tall	Each

621(5A)	Ground Cover, Iris (Iris setosa), SP 5 cont.	Each

621(5B)	Ground Cover, Lily (Hemerocallis “Enchantment”),	Each
	SP 5 cont.

621(5C)	Ground Cover, Kiwi (Actinidia kolomitka ‘Arctic Beauty’),	Each
	#1 cont.

Section 635
Insulation Board

635-2.01 MATERIALS. Delete this section in its entirety and substitute the following:

Insulation Boards. AASHTO M 230, Type VI, except that the extrusion is not required and the maximum water absorption by weight is 10%, as determined by ASTM C 272.  Meet or exceed an R Value of eighteen (18) with units of (Degrees F x Square Feet x Hour/BTU).

Sand Blanket. Subsection 703-2.12.

Section 639
Approaches

Special Provisions

639-1.01 DESCRIPTION. Add the following: This work also includes the construction of approaches at locations shown on the Plans.

639-3.01 CONSTRUCTION. Delete the first sentence and substitute the following: Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. Delete the first sentence and substitute the following: By the number of driveways and approaches constructed as shown on the Plans or as directed.

639-5.01 BASIS OF PAYMENT. Add the following: The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified.  Excavation in driveways and approaches will not be measured for payment but will be considered subsidiary to 639 items.  Selected Material, Type A, Aggregate Base Course, and Asphalt Concrete required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.  Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

639(6)	Approach	Each

(5/9/02)R58M98

Section 640
Mobilization and Demobilization

Standard Modification

640-2.01 METHOD OF MEASUREMENT. Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M77

Delete Section 641 in its entirety and substitute the following:

Section 641
Erosion, Sediment, and Pollution Control

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

1.	BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

2.	ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

3.	Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

4.	HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

5.	SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days.  Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP.  Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing 2 hectares or less.  The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private.  The plan must also incorporate all the requirements of the Project permits.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities.  Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills.  Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you receive written approval of the SWPPP and HMCP.

Post at the construction site, the

1.	name and phone number of your local contact person, and

2.	location of a SWPPP available for viewing by the public.

Implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

1.	pursue work required by the approved SWPPP,

2.	respond to inspection recommendations and/or deficiencies in the SWPPP, or

3.	implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Item 641(1) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control Administration	Lump Sum

641(2)	Temporary Erosion and Pollution Control	Contingent Sum

641(3)	Temporary Erosion and Pollution Control	Lump Sum

641(4)	Temporary Erosion and Pollution Control Amendments	Contingent Sum

(08/15/01)S81

Section 642
Construction Surveying and Monuments

Special Provisions

642-3.01 GENERAL. Delete the seventh paragraph.

(3/31/00)R252M98

Delete item number 10 after the heading “Perform the following:” and substitute the following:

10.	Necessary cross sections at retaining wall locations.  Cross section data shall be taken at 5.0 meter intervals and given to the Engineer 10 days prior to ordering retaining wall materials.  At that time, the Engineer will verify the plan quantity and make any necessary adjustments to the wall size, design or configuration.

11.	All other surveying and staking necessary to complete the project.

(5/8/00)R255M98

Add the following:

12.	Prior to any work on the project, stake and reference the construction centerline. Reference the existing centerline at 25 meter intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 meters and shall show the offset distance to centerline and the station from the beginning of the project.

Install a reference sign every 150 meters. These reference signs shall meet the following requirements:

1.	mounted a minimum of 1.5 meters above the shoulder,

2.	located a minimum of 3 meters from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 125 mm high black lettering on an orange background.

Reference the beginning and ending points of the no-passing zones in a separate field book.

Provide centerline and shoulder profiles extending 90 meters beyond the limits of the pavement removal and dig-out areas. The Engineer may require such adjustments to the planned roadway grades. This shall not be considered extra work. Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking or blue topping.

(8/29/00)R61M98

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

1.	Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.

(3/31/00)R252M98

Section 643
Traffic Maintenance

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan.  Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

a.	Message sign panel large enough to display 3 lines of 229 mm high characters.

b.	Eight character display per message line.

c.	Fully programmable message module.

d.	The capacity to create, preview, and display new messages and message sequences.

e.	A waterproof, lockable cover for the controller keyboard.

f.	An operator’s manual, a service manual, and a wiring diagram.

g.	Quick release attachments on the display panel cover.

h.	Variable flash and sequence rates.

i.	Manual and automatic dimming capabilities on lamp bulb matrix models.

j.	Locate the bottom of the sign panel at least 2.1 m above the pavement.

k.	Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use reflective sheeting that meets AASHTO M 268 Type II or III.

(09/29/00)M91

Special Provisions

Add the following:

17.	Flexible Markers. Refer to subsection 606-2.01 Materials.

(01/29/02)R222M98

Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed Category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements.  Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://www.fhwa.dot.gov/.)

Submit documentation of compliance to the Engineer before using devices on the project.

(09/29/00)M91

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Standard Modification

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. In the fourth paragraph, third sentence, change “crossings” to “closures”.

(06/25/99)M 80

Special Provisions

643-3.03 PUBLIC NOTICE. Add the following:  The Contractor shall maintain emergency vehicle access to and from the Eagle River Road fire station located near Sta. 9+625 at all times during construction.  Vehicles access the facility from both the east and west side.  Access from the west side leads to VFW Road.  Special care should be taken while working in the area, especially at the fire station driveway and the VFW approach.  The Contractor shall coordinate activities with the on-duty fire station Captain at 694-1413 or 694-26756 a minimum of 48 hours before working in the area.

643-3.04 TRAFFIC CONTROL DEVICES. Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1
ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

Add the following:

1.	Monday through Friday 6:00 am to 8:00 am and 4:00 pm to 6:30pm.

2.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

3.	Bear Paw Festival Parade (tentatively scheduled July 12, 2003).  At least one month prior to this date, the Contractor shall contact the Chugiak-Eagle River Chamber of Commerce at 694-4702 to verify the date and time of the parade.

***Deleted***

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

(01/29/02)R222M98

643-3.10 PUBLIC INFORMATIONAL PROGRAM. Add the following Subsection: Provide a Public Information (PI) professional to accomplish the work outlined in this Subsection. The PI person shall have a minimum of five (5) years demonstrated professional experience in performing similar informational campaigns involving multi-media, ie: television, radio, newspaper and public presentations. S/he shall be responsible for all aspects of this service including coordination; public interaction; preparing graphics; developing mailing lists; supplying updated information; and all labor, equipment, postage, and materials to provide this service. Logos, reports, software, visual aids, graphics and work products developed for this Project shall become the property of the Department, and delivered to the Engineer at the end of the work. The PI professional's office shall be equipped with a facsimile machine.

This professional shall be responsible for the following tasks for the PI Program:

1.	Mail-outs. Design and distribute three informational mail-outs/flyers each construction season, which will be approved by the Engineer. The mail-outs shall contain most or all of the following:

a.	a brief description and map of the Project,

b.	the Contractor's anticipated construction schedule,

c.	a narrative of the possible delays to the traveling public through the Project,

d.	detailed traffic information such as intersection, lane and/or sidewalk closures, their corresponding detours, and their effective dates,

e.	locations of temporary bus stops,

f.	a description of possible impacts to abutting property accessing the Project,

g.	a listing of locations where current Project information may be obtained,

h.	date and times of Open House meeting as required by the Engineer,

i.	the Contractor's 24-hour message number and office telephone number, and

j.	the Engineer's Project office telephone number, e-mail address, and the web site address containing Project updates, schedules and general narrative information.

The last mail-out shall also contain a questionnaire to aid in preparing the final Report required under Item 5 below.

The mail-outs shall be sent to all addresses within one city block on either side of the Project corridor, and shall be addressed to both the owner of record and the current tenant.  It shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction season, and

c.	at the approximate two-thirds point of construction season.

2.	Weekly Notices. Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours.  Areas of potential traffic delay shall be emphasized and alternative routes noted. Coordinate this effort with the Engineer and the Department's NAVIGATOR Informational Program.  Telephone numbers for further information, and the date and time for the next scheduled public open house meeting shall be provided.  The Engineer will approve the Notices. Hand carry or fax the Notices to the local news broadcasting media, emergency services, public service organizations and the major retailers near the Project corridor.

Notices shall also be distributed to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska Trucking Association

Alaska State Troopers

Anchorage Daily News

Anchorage Police Department

Anchorage Fire Department

Anchorage School District

Chugiak-Birchwood-Eagle River Road Service Area Board

Federation of Community Councils

Local Emergency Medical Services

People Mover Transit Authorities

Pulse Publications (East, West & Southside)

US Postal Service

The Notices shall be submitted at the following times:

a.	one week prior to the beginning of construction,

b.	on Wednesday of each week during construction, and

c.	prior to any major change or disruption to traffic or local access.

Additionally, the PI professional shall notify business and residents that front the Project or scheduled road closures or of driveway, curb or sidewalk reconstruction, or any other work affecting them.  Property owners with the work segment shall receive the Notices a minimum of one week prior to the commencement of the work within their segment.  Lastly, provide daily information to those media who do non-paid public service road reports or announcements, and/or "Eye-in-the-Sky" commuter road reporting.

3.	Public Open House Meetings. Prepare presentations for the Engineer's Open House Meetings, and for of each of the Community Councils which represent areas affected the this Project.  The Community Council meetings attended shall be the last regularly scheduled meetings prior to the beginning of construction.  Presentation size graphics shall be used to help explain the Project to the general public.

The PI professional shall be the Contractor's representative and spokesman, able to speak for him.  The PI professional shall be available to attend additional public meetings, up to five, as requested by the Engineer.

4.	Other Agency Coordination. Coordinate with the Anchorage People Mover Transit Department (343-8294) to take advantage of programs which will help decrease traffic through this Project, such as Park-and-Ride with express bus service, Ride Share, and the car pooling program.  Also coordinate any major detours and closures with emergency service providers (police, fire, and ambulance), Anchorage School District bus operators, postal service, and the People Mover.

5.	Final Report. Before Project completion, submit a Report evaluating the Public Informational Program as detailed under this Subsection.  The Report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

6.	Project Progress Meetings. Attend all scheduled or special Project meetings between the Contractor and the Engineer at the field office.

7.	Web Page. Generate an INTERNET web site for the Project containing Project updates, schedules and general narrative information. Add links to the Department's NAVIGATOR Home Page (www.dot.state.ak.us/navigator.html). Update the site weekly.

643-4.01 METHOD OF MEASUREMENT. Add the following: Providing mail-outs, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment.

(8/13/99)R102M98

Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion/ET 2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.

(01/29/02)R222M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

643(31)	Public Information Program	Lump Sum

Section 644
Services to be Furnished by the Contractor

Special Provisions

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

7.	Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

8.	Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

R63M98(09/28/00)

Special Provisions

644-2.09 CONTAMINATED MATERIAL TESTING. Add the following subsection: In accordance with Section 203, and subsection Excavation of Contaminated Material, the Contractor shall retain an independent test laboratory to conduct the following tests:

1.	Field Tests

a.	Organic Vapor Analyzer (OVA) Analysis

b.	Visual Analysis (Petroleum Odor)

2.	Laboratory Tests

a.	Volatile Aromatic Hydrocarbons

b.	Total Petroleum Hydrocarbons

644 3.01 METHOD OF MEASUREMENT. Add the following: Contaminated material testing will be reimbursed based on paid receipts for the authorized tests.

(9/13/93)R115

Standard Modification

644-4.01 BASIS OF PAYMENT. In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Special Provisions

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

(9/28/00)R63M98

Add the following: Payment for contaminated material testing will be made on the receipts for authorized samples plus 15 percent, and shall be considered full compensation for all labor, equipment and materials required to have tests performed.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

644(8)	Contaminated Material Testing	Contingent Sum

(9/13/93)R115

Add the following Section:

Section 645
Training Program

Special Provision

645-1.01 DESCRIPTION. This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective. Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General. The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages. Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts. In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement. The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment. Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program,	Labor Hour
	            1 Trainees/Apprentices

(10/29/91)S 16

Section 646
CPM Scheduling

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.  The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.  60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:

Section 647
Equipment Rental

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(5)	Rubber Tired Backhoe, 34 kW Minimum	Hour

(11/12/98)R15M98

Section 660
Signals and Lighting

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS. Delete item number 1 that follows the first paragraph, and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned in accordance with the following specifications.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When the Contractor begins work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, the Contractor shall inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with the Contractor. If the Contractor begins work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when no damaged or defective equipment in service is found and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with existing equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If repairs are not completed, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due the Contractor. When work is done on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes

1.	The date(s) and time(s) the Contractor began and completed work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to periods during normal working hours as specified in Section 643, Traffic Maintenance. During the shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever the clearance from the traveled was is less than 1.8 meters.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals, maintain 5.3 m to 5.8 m of clearance between the traveled way and the bottom of each signal.

2.	For side mounted signals, maintain 2.7 m to 3.4 m of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	Check the horizontal angle to the side mounted far right signal from the center of the farthest left through lane at the stop bar. When the angle exceeds 20 degrees, move this signal to an overhead location. With two or more through lanes, center one signal head over each lane. With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane, otherwise install the relocated signal 2.4 meters to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 2.1 m to 2.7 m between the traveled way and the bottom of each pedestrian signal.

7.	Aim all signal heads in accordance with subsection 660-3.08, Installation Details.

When no longer required, salvage all original and Department provided equipment in accordance with the plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

Add the following Subsection:

660-1.05(A) TEMPORARY SIGNAL SYSTEMS. Provide temporary traffic signals at the intersections listed in the plans or special provisions. Move traffic through these intersections at all times with fully functional traffic signals, except during shutdowns to change from one system to another. The Engineer will limit temporary signal system shutdowns to periods during normal working hours as specified in Section 643, Traffic Maintenance. During these shutdowns, use flag control to control the flow of traffic.

Submit a plan for each temporary signal system to the Engineer for approval before implementation. Ensure each temporary signal system equals the one being replaced or modified, that is, it includes the same number of signal heads, signal phases, pedestrian pushbuttons, etc.  Include the following details in each temporary signal plan.

1.	A scale drawing of the intersection that includes all lanes, their widths, and auxiliary lane pocket lengths.

2.	The location of all signal poles.

3.	The location, sizes, and type of each signal head.

Temporary signal systems may consist of any combination of the following:

1.	The existing systems

2.	Relocated components of the existing systems

3.	Guyed wood poles

4.	Parts of the permanent signal system.

Furnish and install all materials and miscellaneous hardware required for a functional traffic signal system. All materials shall conform to the requirements of the plans and specifications. Use temporary equipment compatible with existing equipment used in the Central Region. Provide load centers as required in subsection 660-1.05(B), Temporary Illumination Systems.

The Contractor may suspend traffic signals from messenger cables provided the Contractor mounts them with standard span wire hangers and secures them with a second cable to prevent misalignment in a wind. Furnish all signal faces with back plates and visors. Use two circuits to energize the signals of each phase that include two or more signal faces; wire each circuit wired with an IMSA 20-1 signal cable. The Engineer will allow splices only at the terminal blocks in the signal faces. Leave sufficient signal cable slack at each pole to provide for drip loops and to allow realignment of each signal head. The Contractor may install temporary controller assemblies on Type III junction boxes while completing work on the permanent systems.

Whenever temporary signals includes a span wire attached to a permanent signal pole, install a guy on the permanent pole and provide protective collars to prevent chafe damage. Exclude poles with breakaway bases in span wire supported signal systems.

Maintain fully actuated traffic signals during the normal course of construction by installing loop or optical detectors as directed by the Engineer.  During winter shutdown, provide loop detectors in the signal systems according to Section 6.080 of Chapter 6 of the Municipality of Anchorage’s Design Criteria Manual.

Add the following Subsection:

660-1.05(B) TEMPORARY ILLUMINATION SYSTEMS. Provide temporary illumination at all locations with existing lighting, at all temporary traffic signals, and along all roadways that transition from one section to another. Provide this work during the life of the contract on all roadways open to traffic within the project limits.  Make temporary lighting systems operational by sunset on the day you replace or retire a system, or you open a roadway and/or detour to traffic.

Submit a plan for each temporary lighting system to the Engineer for his review and approval prior to implementation.  Ensure the temporary lighting plans equal the systems being replaced or modified.  At intersections, provide electroliers on the far right side of each main street approach, installed near the main street radius returns.  Consider the street with the vehicular right-of-way as the main street; at signalized intersections and four-ways stops, consider both streets as main streets.

Furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including electrical load centers. All materials shall conform to the requirements of the plans and specifications, except branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Install branch conductors in underground electrical conduit when overhead conductor clearances do not conform to the National Electrical Safety Code (NESC).  Size conductors to provide the minimum voltage recommended by the ballast manufacturer at the most remote luminaire. You may use the existing luminaires or new luminaires with a light distribution compatible with the proposed lighting system configuration.

Use any of the following poles that maintain a minimum 12 m difference in elevation between a luminaire and the edge of traveled way beneath it.

1.	Existing poles if they are not owned by a utility.

2.	Poles from the permanent lighting system.

3.	Poles that are part of the temporary signal systems.

4.	ANSI Class 4 wood poles that you furnish.

5.	Steel or aluminum poles that meet design criteria for 130 kilometer per hour wind speeds according to AASHTO Standard Specifications for Structural Supports.

Install all light poles with the ends of the mast arms situated over the edge of the traveled way. Retain the breakaway base features, when you relocate existing electroliers. Provide all other poles installed in the clear zone, except traffic signal poles, with FHWA approved slip bases, transformer bases, or frangible couplings. Install wood poles and all other fixed base poles behind portable concrete barrier; provide a 0.6 meter space between the barrier and the pole.

Use any of the following load centers to energize the temporary lighting and signal systems. Provide all work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

1.	Permanent load centers installed in their plan location.

2.	Existing load centers scheduled to remain intact until completion of the project. You may relocate and reuse existing load centers only if they are approved.

3.	Approved temporary load centers with photoelectric controlled lighting circuits.  Provide a temporary load center when you retire an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

660-2.01 EXCAVATING AND BACKFILLING. In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following after the fourth paragraph: Backfill the first 150 mm lift with material free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS. Delete the Pile Foundations section and substitute the following:

Pile Foundations. Install all light pole foundations according to the following requirements

1.	Materials. Furnish pipe piles that feature the diameter and minimum length and wall thickness as shown on the Plans.  Furnish piles made of material that conforms to ASTM A36/A36M-97, except the mill certificates shall indicate a minimum 290 MPa yield strength.

Furnish pile caps fabricated from 50 mm thick steel plate that conforms to ASTM A36/A36M-97, except the mill certificates shall indicate a minimum 290 MPa yield strength.

Use the number and size of frangible couplings, nuts, and washers as shown on the Lighting Standards detail sheet included in the Plans.

2.	Fabrication Requirements. Fabricate the pile cap to match the base plate shown on the approved light pole shop drawings.  Attach the pile cap to the pipe pile with a fell penetration seam weld.  The Department will not accept socket type joints that are attached to the pile with two fillet welds.

3.	Construction Requirements. Install the steel pipe piles open ended according to Section 505.

Complete all welding shown on the Plans and as specified herein according to the Structural Welding Code – Steel, AWS D1.1-2000.  At least 30 calendar days before you begin welding, submit a welding plan and mill certification reports for the pipe piles and pile caps to the Engineer for approval.  Do not begin welding until the Engineer has returned these items approved in writing.  The welding plan shall consist of the following:

- Welding Procedure Specifications (WPS),

- Procedure Qualification Record (PQR),

- Welder Performance Qualification Record (WPQR),

- Visual Inspection Form,

- Report of Nondestructive Examination (NDE) of Welds, and

- The name of the Contractor’s Quality Control (QC) manager with documentation of qualifications.

Furnish all Quality Control inspection necessary to ensure the materials meet the requirements of the contract documents and workmanship meets the requirements of AWS D1.1.

- Visually inspect (VT) the entire length of each weld.

- Inspect all full penetration welds by ultrasonic NDE (UT) as shown on the Plans.

Correct all deficiencies in materials and workmanship revealed by QC and Quality Assurance (QA) inspections according to AWS D1.1 without additional compensation.

Furnish all completed QC inspection documents to the Quality Assurance representative designated by the State.

Install the frangible couplings according to the manufacturer’s written installation instructions.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Add the following: The minimum design loading for signal mast arm poles is indicated in the Signal Mast Arm/Pole Design Loading Detail found in the Plans.  Should the project plan loading develop shear or moments greater than those related to the Signal Mast Arm/Pole Design Loading Detail, poles shall be designed using the project plan loading.

Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged or destroyed by the Contractor’s operations at the Contractor’s expense. When the Contractor relocates galvanized standards with rusted or scarred surface areas, the Contractor shall repair these areas in accordance with subsection 660-2.15, Galvanizing.

Welding design, fabrication, and inspection shall be in accordance with the latest edition of the AWS D1.1, Structural Welding Code- Steel.

1.	Circumferential Welded Splices

Inspect 100% of CJP welds by ultrasonic examination (UT)

2.	Longitudinal Seam Welds

a.	100% of CJP welds by ultrasonic examination (UT)

b.	25% of all Partial Joint Penetration (PJP) welds of longitudinal seams by magnetic particle examination (MT)

3.	Base Connection Welds

a.	Inspect 100% of all base connection welds shall be inspected

b.	CJP welds shall be inspected by UT

c.	Fillet welds shall be inspected by MT

4.	At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Engineer for approval.  Do not begin welding until these items have been returned approved in writing by the Engineer.  The welding plan shall consist of the following:

a.	Welding Procedure Specification (WPS)

b.	Procedure Qualification Record (PQR)

c.	Welder Performance Qualification Record (WPQR)

d.	Visual Inspection Form

e.	Report of Nondestructive Examination (NDE) of Welds in accordance	with Annex K of the latest edition of AWS D1.1

f.	The Contractor’s Quality Control (QC) manager with documentation of qualifications

g.	NDE personnel qualification records

5.	Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

6.	Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

7.	Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT. Add the following:  The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  After the Contractor paves the final asphalt course, however, the Engineer will not allow trenching. Trenching will not be permitted when bored casing, as indicated on the Plans, is to be installed.

Use Standard Schedule 40 pipe conforming to ASTM A53 to the sizes and at locations shown on the plans for bored casings.  Diameters indicated are DN Designator.

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

Add the following:

Item 660(18), Adjust Junction Box. If conduits enter the existing junction box from the side the junction box shall not be moved vertically.  The junction box shall be extended by means of a cast-in-place concrete extension collar.  The collar shall be attached by drilling the existing junction box for rebar and securing the rebar with epoxy.  Junction box extension shall allow mounting the standard cast iron lid.

660-2.08 CONDUCTORS. Delete the first paragraph of item 2 “Power Conductors and Cables” and add the following: Use power conductors and cables manufactured according to ICEA publication S-66-524 and NEMA Publication No. WC7, and which are UL listed and labeled for direct burial and resistance to sunlight. Furnish conductors insulated with chemically cross-linked polyethylene UL listed and labeled as type XHHW-2. Use cables rated for 600 volts AC operation.

Furnish cables consisting of three #8 AWG conductors with conductor insulation colored black, white, and red. Furnish cables with three conductors larger than #8 AWG with conductor insulation colored black, white, and red, or with all black conductor insulation with printed numbers identifying each conductor per ICEA method 4.

Delete subparagraph “d” of item 2. Power Conductors and Cables and add the following: Furnish highway and sign illumination cables with #8 AWG conductors with a low density, high molecular weight polyethylene jacket.

Delete Item 3 “Detector Loops” and substitute the following:

3.	Loop Detectors. Use No. 14 AWG conductors that conform to IMSA Specification 51-5 for inductive loop detectors.  Furnish the conductor loosely encased within a polyethylene tube.

4.	Loop Lead-in Cables. Add the following to the third paragraph: Furnish cable with colored pairs that match those specified in subsection 660-2.09 Wiring, of these Special Provisions.

660-2.09 WIRING. Delete the first paragraph and add the following: Install signal cables with no splices in them.  Install illumination cables without splices, except when adding an electrolier to the midst of a circuit. In addition, do not splice conductors within cabinets, poles, signal heads, and luminaires.

Crimp spade type terminals onto all conductors that attach to terminal blocks.  When reusing cabinets, replace terminal blocks that lack enough terminals.  Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

Delete the first two sentences of paragraph numbered 7 and add the following: To add an electrolier to a circuit, splice a piece of illumination cable (a tap) into the cable that forms the circuit in the junction box adjacent to the electrolier.  Terminate the two current-carrying tap conductors in the line side half of the fused splice connector.  Pull the tap back into the junction box to position the fused splice connector in the space between the base plate and the hand hole of each pole.  When a circuit branches, complete the splice in a junction box at the location shown in the Plans.

Delete the paragraph numbered 9 and Table 660-3 and add the following: When splicing loop detectors to multi-pair loop lead-in cables, complete the work according to the following

1.	See the plans for the number assigned to each loop detector and the loops assigned to each loop lead-in cable.  Using this information, splice the loop detector tails to the paired conductors found in each lead-in cable, using the following color code:

Loop Detector Number	Colored Pair

The lowest numbered loop detector	Red and Black
The second lowest numbered loop detector	Blue and Black
The third lowest numbered loop detector	White and Black
The fourth lowest numbered loop detector	Green and Black
The fifth lowest numbered loop detector	Brown and Black
Usually a spare pair	Yellow and Black

2.	Remove a short section of cable jacket and only cut the shielded pairs dedicated to the loop detectors being spliced.  Run these pairs, without splices, to the controller cabinet.

3.	Strip the insulation from the ends of the conductors.  With the loop and lead-in conductors parallel to one another, twist the bare ends together and then solder them together.

4.	Insulate and seal each soldered connection with a mastic-lined, heat shrink tubing end cap.

5.	First, crimp and then solder spade terminals to the ends of the shielded pairs in the controller cabinet.  The Department will terminate the pairs on the terminal blocks and make all series and parallel connections.

Delete the last three sentences of paragraph numbered 10.

From the first sentence of the paragraph numbered eleven, delete the phrase "and loop lead-in cable splice (single pair or multiple pair)".

Add the following: Encapsulate all loop lead-in cable splices in rigid, transparent, PVC molds filled with re-enterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide molds that are re-useable and come in four pieces held together with stainless steel hose clamps.  Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full 6 mm of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with re-enterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

Delete paragraph numbered 14 and add the following: Label the cables used in the signal and illumination systems with the following legends:

1.	For the cables listed in Table 660-1, use the legends included in the same Table.

2.	Use the loop number shown on the plans to label each tail of all loop detectors and the paired loop lead-in conductors in the controller cabinet.

3.	For interconnect cables, use the first letter of the direction the cable follows to the adjacent intersection on each cable.  Add a number suffix if more than one cable is routed to the adjacent intersection.

Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer.  Replace at no expense to the State all identification tags the Engineer deems illegible.

1.	Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet.  Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head.  The cable ties shall consist of a single strap with a minimum size tag of 20 mm by 9 mm.

2.	To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear.  Provide tags with a 100 mm by 44 mm minimum size that attach flag style at one corner to a single strap.  Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

660-2.10 FUSED SPLICE CONNECTORS. Delete the 4th paragraph in its entirety and replace with the following:  Use fuses that are 10 ampere, midget (10 mm x 40 mm) ferrule type with fast acting current limiting (KTK type) design.

Add the following: Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING. Add the following after the first paragraph: Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph: All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a mechanically or hot dip galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Where wire is pulled and reinstalled in existing conduits, the bare No. 8 AWG copper wire shall also be installed. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted. (3/30/00)R215M98

660-3.03 STANDARD AUXILIARY EQUIPMENT.

6.	Conflict Monitors. Add the following:

a.	Supply conflict monitors with an RS-232 serial port that allows the monitor to download information through an external dial-up multi-port modem or to a personal computer using the Microsoft Windows NT operating system.

660-3.04 SPECIAL AUXILIARY EQUIPMENT. Add the following:

6.	Opticom Priority Control System.  Install the following components of the 3M Company’s Opticom Priority Control System in accordance with 3M’s written installation instructions at each signalized intersection listed on the plans. During signal preemption, the controller unit rather than the phase selector or auxiliary logic shall perform all interval timings, signal sequences, and phase skips.

a.	Install the quantity of model 711, 721, or 722 Optical Detectors on the traffic signal pole mast arms as shown on the plans.  Before installing the Optical Detectors, gain approval of their final lateral location on the mast arms from the Engineer.  See the plans for installation details.

b.	Install Model 138 Optical detector lead-in cable between each optical detector and the controller cabinet.  Furnish enough slack in these cables for them to extend 0.6 m beyond the end of each signal mast arm and to leave 3.0 m of slack in the controller cabinet.

Before attaching the conductors to the optical detector, strip the insulation from the conductors in the Model 138 cable and attach all four conductors to ground in the controller cabinet.  Attach the signal cable to the confirmation light.  The Municipality of Anchorage’s Signal Maintenance Section will make final terminations of the conductors in the controller cabinet under Item 660(26), Signal System Timing and Adjustments.

c.	Furnish each controller assembly with a Model 754 phase selector, a Model 760 card rack, and an Opticom Panel Assembly, U.S. Traffic Corporation part number 103303, which interfaces the card rack to the controller cabinet.

1.	Furnish new controller cabinets with these parts installed by the controller assembly manufacturer; and

2.	When retrofitting existing controller cabinets, deliver these parts to the Municipality of Anchorage’s Signal Maintenance Section.  They will install these parts under Item 660(26), Signal System Timing and Adjustments.

7.	Traffic Logging System. Furnish, for installation in each traffic signal controller cabinet, a module that collects, time stamps, stores data in an unattended manner, and conforms to the following:

a.	Operation. The unit shall accept a new operating program, operational parameters, and the date and time stamp from a personal computer, downloaded through an RS-232 cable. The use of replaceable proms to change the operational program is unacceptable. Data collection shall be automatic and not require an operator to reset or start operation.

In the event of a power interruption, data collection shall automatically restart at the proper time. Other than the current sample being collected, the unit shall not lose stored data because of the power interruption. At power-up or at the restoration of power after an outage, the unit shall log the date and time at the start of data collection.

The unit shall maintain the operating program, data storage, and date/time for a minimum of 5 years from when power is removed from the unit. The internal program/data size shall be a minimum of 32,000 bytes.

b.	Input Interface. The unit shall have a minimum of 28 inputs.  Furnish a Detector Systems TLS-1-C1 interface cable for each controller cabinet to connect the unit to the output of the loop detector units. The Municipality of Anchorage’s Signal Maintenance Section will install the interface cable in the controller cabinets under Item 660(26), Signal System Timing and Adjustments.

c.	Output Interface. Furnish all units with an RS-232 serial port that allows a user to download and upload directly between the unit and a personal computer using the Microsoft Windows NT operating system or the external dial-up multi-port modem.

d.	Software. Supply Microsoft Windows NT compatible software and user manuals with the unit that provides the operator an interface to the hardware. Furnish menu driven software that allows an operator to: 1) download to initialize the unit with its operating program and data collection parameters, 2) upload information from the unit (both stored data and real-time data) and 3) transfer a data file to a text file.

The operating program shall provide for month, day, day-of-week, hour, minute, and second information and allow sampling periods of 5, 15, 30, and 60 minutes.

8.	Ultrasonic Presence Sensors.  At the locations shown on the plans, install sensors that operate at an ultrasonic frequency and sample for the presence of stationary and moving vehicles at a rate of ten times per second.  Furnish sensor units that:

a.	Feature solid-state circuitry and a high-speed transducer with the sensitivity to detect motorcycles.  The cone of coverage produced by the transducer should measure at least 1.2 m in diameter and 6.6 m from the transducer.  The unit shall provide a continuous call to the controller unit with the presence of a vehicle in its cone of coverage and whenever the unit loses power.

b.	Include an external control to adjust the length of the cone of coverage, an external detection light emitting diode, and mounting brackets suitable to install the units on traffic signal pole mast arms.

c.	Require no external amplifiers, seasonal tuning, or special cabling, and which operate at all temperatures from -35˚C to 75˚C.  Wire each sensor using two pairs of our six pair loop lead-in cable.

d.	Operate on a voltage of 12 to 24 volts AC.  Install a 60-hertz, 40 volt-ampere transformer with 120-volt AC primary and 24-volt AC secondary in the controller cabinet.  Furnish a UL listed, class 2 rated, transformer with built in overload and short circuit protection.

660-3.05 CONTROLLER CABINET.

1.	STANDARD FEATURES

c.	Cabinet Wiring. Add the following to (1): Furnish all controller cabinets wired to accommodate five 4-channel inductive loop detector units and two 2-channel inductive loop detector units.

660-3.09 SIGNAL HEADS. Change the subsection titled “Optical Units.” to:  Incandescent Optical Units

Add the following Subsection at the end of the Incandescent Optical Units subsection:

Light Emitting Diode Modules.

1.	Definition.

a.	Furnish light emitting diode (LED) signal modules for the indications in all 200 mm and 300 mm traffic signals faces on this project.

b.	LED signal modules shall consist of an assembly that utilizes light emitting diodes as the light source in lieu of an incandescent lamp for use in traffic signal sections.

2.	General.

a.	Furnish LED signal modules that fit in the doorframe of a standard traffic signal section.  The lamp socket, reflector, reflector holder, and lens used with an incandescent lamp shall not be used in a signal section in which an LED signal module is installed.

b.	LED signal modules shall be a sealed unit with two conductors for connecting to power, a printed circuit board, power supply, a lens and gasket, and shall be weather proof after installation and connection.  The circuit board and power supply shall be contained inside the module.

c.	Furnish modules with an integral lens that feature a smooth convex outer surface made of ultraviolet stabilized plastic or glass.  The lens shall withstand ultraviolet (direct sunlight) exposure for a minimum period of 5 years without exhibiting evidence of deterioration.

d.	Use a one-piece EPDM (ethylene propylene rubber) gasket to seal the module in the doorframe.

e.	Furnish LED modules that utilize AllnGaP technology and are the ultra bright type rated for 100,000 hours of continuous operation from –40°C to 74°C.  AlGaS LEDs will not be allowed.

f.	The failure of an individual LED in a string shall only result in the loss of that LED, not the entire string or indication.

g.	LED signal modules shall maintain not less than 85 percent of the standard light output values found in the ITE publication ST-008B, "Vehicle Traffic Control Signal Heads" (VTCSH ST-017). LED signal modules shall maintain this light output after 72 months of continuous use in a traffic signal system over the temperature range of -40°C to +74°C.

3.	Physical and Mechanical Requirements.

a.	LED traffic signal modules shall be designed as retrofit replacements for existing optical units of signal lamps and shall not require special tools for installation.  LED signal modules shall fit into existing traffic signal section housings built to the VTCSH without modification to the housing.

b.	Installation of a LED signal module shall only require the removal of the optical unit components, i.e, lens, lamp module, gaskets, and reflector; shall be weather tight and fit securely in the housing; and shall connect directly to electrical wiring.

LED Signal Module Lens.  The LED signal module shall be capable of replacing the optical unit.  The lens may be tinted or may use transparent film or materials with similar characteristics to enhance ON/OFF contrasts.  The use of tinting or other materials to enhance ON/OFF contrasts shall not affect chromaticity and shall be uniform across the face of the lens.

If a polymeric lens is used, a surface coating or chemical surface treatment shall be used to provide front surface abrasion resistance.

Environmental Requirements.  The LED signal module shall operate at all temperatures from -40°C to +74°C.

The LED signal module shall protect all internal components against dust and moisture intrusion according to NEMA Standard 250-1991 for Type 4 enclosures.

Construction.  The LED signal module shall be a single, self-contained device, not requiring on-site assembly for installation into an existing traffic signal housing.  The power supply for the LED signal module shall be integral to the unit.

Module Identification.  Each LED signal module shall have the manufacturer's name, trademark, and other necessary identification permanently marked on the back of the module.  Each individual LED signal module shall be identified for warranty purposes.

The following operating characteristics shall be identified: rated voltage, power consumption, and volt-ampere.

Each LED signal module shall have prominent and permanent vertical marking(s) for correct indexing and orientation within a signal housing.  The markings shall consist of an up arrow, or the word "UP" or "TOP".

4.	Photometric Requirements.

a.	LED traffic signal modules shall meet at least 85 percent of the minimum VTCSH intensity requirements while operating any temperature from        -40°C to +74°C.

b.	The minimum initial luminous intensity values for LED traffic signal modules shall be as defined in Section 11.04 of the VTCSH standard at 25°C.

c.	The measured chromaticity coordinates of LED signal modules shall conform to the chromaticity requirements of Section 8.04 and Figure 1 of the VTCSH standard.

5.	Electrical.

a.	LED signal modules shall operate from a 60 Hz ±3 Hz AC line over a voltage ranging from 80 volts to 135 volts. The LED circuitry shall prevent perceptible flicker over the voltage range specified above.  The fluctuations of line voltage shall have no visible effect on the luminous intensity of the indications.  Rated voltage for all measurements shall be 120 volts. Green and yellow LED signal modules shall not produce light whenever the voltage drops to less than 45 volts AC.

b.	All wiring and terminal blocks shall meet the requirements of Section 13.02 of the VTCSH standard.  Furnish each signal module with two secured, color-coded, 600 V, 20 AWG minimum, jacketed wires that conform to the National Electric Code and are rated for service at +105°C. Furnish 1 m long conductors fitted with fork type terminal connectors.

c.	The signal module on-board circuitry shall include voltage surge protection to withstand high-repetition noise transients as stated in Section 2.1.6 of NEMA Standard TS-2, 1992.

d.	LED signal modules shall be operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

e.	LED signal modules and associated on-board circuitry must meet Federal Communications Commission (FCC) Title 47, Subpart B, Section 15 regulations concerning the emission of electronic noise.

f.	The LED signal module shall provide a power factor of 0.90 or greater.

g.	Total harmonic distortion (current and voltage) induced into an AC power line by a LED signal module shall not exceed 20 percent.

6.	Production Testing Requirements.

a.	To ensure electronic component reliability before shipment, the manufacturer shall energize each new LED signal module for a minimum of 24 hours at operating voltage and at a temperature of 600 C.

b.	After completing the burn-in procedure, the manufacturer shall test each LED traffic signal lamp unit for rated initial intensity at rated operating voltage.

7.	Warranty. Provide the Engineer with all warranty documents before you install the LED modules, including the manufacturer’s toll free telephone number for returning failed LED modules.

a.	The manufacturer shall provide a written warranty that covers defects in materials and workmanship for the LED signal modules for a period of 72 months. The warranty period will begin on the date the traffic signal satisfactorily completes the functional test prescribed in section 660-2.14, Field Tests. The warranty period for modules that replace failed modules will begin on the date they are installed.

b.	The manufacturer shall replace failed LED modules with new LED modules at no cost to the State or Municipality of Anchorage, including the cost of shipping failed modules. The warranty does not include the cost of removing failed modules from or reinstalling new modules in a traffic signal system. Upon notification a module has failed, the manufacturer shall send, via next day delivery, the State or Municipality of Anchorage prepaid authorization to return the failed module.

c.	The manufacturer shall send replacement LED modules within five working days of receiving failed modules.  Deliver the replacement modules to the Municipality of Anchorage, Traffic Signal Electronics Shop.

660-3.11 SIGNAL HEAD MOUNTING. Add the following: Remove all burrs from the inside and outside of all holes made to pass conductors through the walls of posts, poles, and mast arms to prevent scraping of the conductors.

Where 5-section vertical signal heads are side mounted on poles, install a steel conduit hanger on the vertical framework pipe, 150 mm down from the upper horizontal framework pipe.

660-3.13 PEDESTRIAN SIGNALS. Delete the first paragraph and replace it with the following: Provide pedestrian signals with the international “HAND/WALKING PERSON” symbols. Furnish light emitting diode (LED) type pedestrian signal modules as specified in subsection 660-3.13A.  New pedestrian signals shall consist of Pedestrian LED Signal Modules installed in new housings and hardware.

Delete numbered subparagraphs 3. through 9.

Add the following Subsection:

660-3.13a PEDESTRIAN LIGHT EMITTING DIODE PEDESTRIAN SIGNAL MODULES.

1.	General

Furnish pedestrian LED traffic signal modules designed as a retrofit replacement for the message bearing surface of a 400 mm x 400 mm pedestrian traffic signal housing built to the PTCSI Standard.  Supply a message-bearing surface of the module with “HAND” and “WALKING PERSON” symbols that comply with ITE Pedestrian Traffic Control Signal Indications (PTCSI) standard for this symbol for a message-bearing surface of the size specified.  This message-bearing surface shall be designed so that it can be removed from the sealed unit for replacement without further damage to the module.

2.	Installation

a.	Furnish LED pedestrian signal modules designed as retrofit replacements for the existing neon type pedestrian signals (ICC 4090 and/or 4094).

b.	The LED pedestrian signal modules shall not require special tools for installation.

c.	LED pedestrian signal modules shall fit into existing pedestrian signal housings built to the PTCSI standard without modifying the housings.

d.	Furnish LED pedestrian signal modules that fit securely in the housing, connect directly to existing electrical wiring, and form a weather-tight seal.

e.	Retrofitting an existing pedestrian signal shall only require the removal of the existing neon message module, gasket, and power supply and installation of the new LED module.

f.	Each retrofit shall include all necessary components to complete conversion including a one-piece gasket.

g.	Each pedestrian module shall have a sticker attached stating compliance to the ITE Standard for color.

3.	LED Signal Lens

a.	Furnish LED pedestrian signal modules with field replaceable lenses.

b.	Furnish LED pedestrian signal modules with UV stabilized polycarbonate lenses a minimum of 6 mm thick.

c.	The exterior of the lens of the LED pedestrian signal module shall be smooth and frosted to prevent sun phantom.

4.	LED Pedestrian Signal Module Construction

a.	Furnish one piece, self-contained, LED pedestrian signal modules that require no on-site assembly for installation in existing pedestrian signal housings.

b.	All Portland Orange LEDs shall use “AllnGaP” technology or equal, rated for 100,000 hours or more at +25C and 20 mA.  The Department will not accept LEDs that use “AllnGaS” technology.

c.	The manufacturer shall identify each LED pedestrian module for warranty purposes with their trade name, a serial number and operating characteristics, i.e., rated voltage and power consumption in volt-amperes.

5.	Environmental Requirements

a.	Furnish LED pedestrian signal modules that operate in the ambient temperature range of -40C to +60C.

b.	The LED pedestrian signal modules, when properly installed with gasket, shall be protected against dust and moisture intrusion per requirements of NEMA Standard 250-1991, sections 4.7.2.1 and 4.7.3.2., for type 4 enclosures to protect all internal LED, electronic, and electrical components.

6.	Luminous Intensity

- Furnish LED pedestrian signal modules that, when operated over the specified ambient temperature and voltage range, pedestrians can read both day and night at all distances from 3 m to the full width of the area they cross.

b.	The luminous intensity of the LED pedestrian signal module shall not vary more than  10% for voltage range of 80 VAC to 135 VAC.

7.	Chromacity

The measured chromaticity coordinates of the LED signal modules shall conform to the chromaticity requirements of Section 5.3 and Figure C of PTCSI standard.

8.	Electrical

a.	Furnish each LED pedestrian signal module with two secured, color coded, 600V, 20 AWG minimum, jacketed wires that conform to the National Electrical Code and which are rated for service at +105C.  Furnish 1 m long conductors fitted with fork type terminal connectors.

b.	The LED pedestrian signal module shall operate from a 60  3Hz AC line over a voltage range of 80 VAC to 135 VAC.  Rated voltage for all measurements shall be 120  3 volts rms.

c.	The LED circuitry shall prevent perceptible flicker over the voltage range specified above.

d.	The LED pedestrian signal module circuitry shall include voltage surge protection against high-repetition noise transients as stated in Section 2.1.6, NEMA Standard TS-2, 1992.

e.	Catastrophic failure of one LED light source shall not result in the loss of more than the light from that one LED.

f.	The LED pedestrian module shall be operationally compatible with the currently used controller assemblies.  The LED pedestrian module shall be operationally compatible with conflict monitors.

g.	The LED pedestrian module including its circuitry must meet Federal Communications Commission (FCC) Title 47, Subpart B, Section 15 regulations concerning the emission of noise.

h.	The LED pedestrian module shall provide a power factor of .90 or greater over the operating voltage range and temperature range specified above for modules with 6 watts or more.

i.	Total harmonic distortion (current and voltage) induced into an AC power line by an LED pedestrian module shall not exceed 20% over the operating voltage range and temperature range specified above.

9.	Production Testing Requirements

a.	Energize each new LED traffic signal lamp unit for a minimum of 24 hours at operating voltage and at a temperature of 600 C to ensure electronic component reliability before shipment.

b.	After the burn-in procedure is completed, the manufacturer shall test each LED traffic signal lamp unit for rated initial intensity at rated operating voltage.

10.	Warranty Provide the Engineer with all warranty documents before you install the LED modules, including the manufacturer’s toll free telephone number for returning failed LED modules.

a.	The manufacturer shall provide a written warranty that covers defects in materials and workmanship for the LED signal modules for a period of 72 months. The warranty period will begin on the date the traffic signal satisfactorily completes the functional test prescribed in section 660-2.14, Field Tests. The warranty period for modules that replace failed modules will begin on the date they are installed.

b.	The manufacturer shall replace failed LED modules with new LED modules at no cost to the State or Municipality of Anchorage, including the cost of shipping failed modules. The warranty does not include the cost of removing failed modules from or reinstalling new modules in a traffic signal system. Upon notification a module has failed, the manufacturer shall send, via next day delivery, the State or Municipality of Anchorage prepaid authorization to return the failed module.

c.	The manufacturer shall send replacement LED modules within five working days of receiving failed modules. Deliver the replacement modules to the Municipality of Anchorage, Traffic Signal Electronics Shop.

660-3.16 LUMINAIRES. Add the following: Furnish high-pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.

The luminaire manufacturer shall furnish light fixtures free of substances (such as paint) that affect luminaire photometric performance.

The luminaires shall be UL 1572 listed suitable for wet locations.

Furnish luminaires with a wire way that meets National Electrical Code requirements to install three #10 AWG conductors with type XHHW insulation from the pole to a terminal block located in the luminaire.

Furnish luminaires that provide the uniformity specified (or better) in the arrangements listed on the plans.  Use a lighting program that calculates illumination levels according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 1983.  Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.  If electronic data is unavailable, derive the illumination level at the dimmest point by straight-line interpolation between the isolux lines on the manufacturer’s current published photometric data charts. To calculate the uniformity ratio, divide the average illumination level by the illumination at the dimmest point.

Luminaire Type Definitions:

MC-3:	Mast arm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

MS-3:	Mast-arm Mounted Semi Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

Offset:	Pole top mounted luminaires designed to be offset between 6 and 15 meters from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT. Add the following: Transport all signal poles and mast arms to the State.  Deliver controller assemblies and LED modules to the Municipality of Anchorage.  You will provide a one-week notice of your intent to deliver salvaged materials, to coordinate location and time of delivery.  Contact Phil Saunders at 343-4557 for luminaire, metal light standard, service equipment, and related items.  Contact Bill Snyder at 343-8355 for controller assembly, signal equipment, preemption system devices, junction box lids, and other related items.  You will be responsible for disposing of all remaining signal equipment removed.

660-3.24 SIGNAL SYSTEM TIMING AND ADJUSTMENTS. Add the following subsection: The Engineer will use signal maintenance personnel from the Municipality of Anchorage traffic to perform the following functions.

1.	Laboratory Inspection and Tests.  Ship the traffic controller cabinets and equipment to the Municipality of Anchorage Traffic Signal Maintenance lab at 3650 East Tudor Road, Building C.  The Municipality will inspect cabinet wiring, burn in signal equipment, customize cabinets for desired operation and test the cabinets according to Subsection 660-3.07 Shop Tests.

2.	Field Tests and Adjustments. Within the Municipality of Anchorage, Municipal signal maintenance personnel will complete the following work.

a.	Loop Detector Wiring.  Maintenance personnel will test and terminate the paired conductors in the loop lead-in cables. Contractor shall prepare the loop lead-in cables for tie-down, including labeling all paired conductors, stripping insulation and fitting conductor ends with termination connectors.

b.	Control Cable Wiring.  When an actively operating signal system is being modified, maintenance personnel will terminate all control cables within the traffic signal controller cabinet.  It shall be the Contractor’s responsibility to prepare the cables for termination.

c.	Timing Adjustments.  During the project, maintenance personnel may be required to adjust the system and intersection operational timing to accommodate project conditions.

d.	Interconnect Wiring. Maintenance personnel will splice, test and perform tie-down on all interconnect wiring.

660-4.01 METHOD OF MEASUREMENT. Add the following:

Item 660(18), Adjust Junction Box. By each junction box, complete and in place.

Item 660(21), Signal Mast Arm Sign Support.  By each signal mast arm sign support, complete and in place.

Item 660(22), Signal Mast Arm Sign Support with Luminaire.  By each signal mast arm sign support with luminaire, complete and in place, including all conduit, conductors, and other equipment to the nearest junction box.

660-5.01 BASIS OF PAYMENT. Add the following: The lump sum prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans.  This includes: completing all excavation to install foundations, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, adjusting junction boxes, leveling signal poles, retrofitting existing electroliers with new tap wires and fused disconnect kits, and pulling conductors.  The lump sum prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions.  This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

Payment for Item 660(17A), Traffic Signal System Modifications at Artillery Rd/Eagle River Rd will be for all work and materials described on the Plans and Specifications and removing the Type II junction box at approximately Sta. 3+484.9, 1.5 Lt.  The conduit within the junction box shall be connected with flexible conduit to provide a continuous east-west run across Old Glenn Highway between the Type II junction boxes at Sta. 3+482.5, 15.5 Lt and Sta. 3+485.5, 14.8 Rt.  Backfill all excavation associated with the junction box removal and pave.

Payment for Item 660(18), Adjust Junction Box, will be made for each junction box adjusted to finish grade.

Item 660(26), Signal System Timing and Adjustments, will be paid based on paid receipts plus 15 percent for authorized work performed by the Municipality of Anchorage. A directive will not be required to initiate payment for work performed under Item 660(26). The Contractor shall bear all costs of the Municipality re-testing equipment that fails to comply with the Plans and Specifications.

(04-13-01)R65M98

Add the following Pay Items:

Pay Item No.	Pay Item	Pay Unit

660(3)	Highway Lighting System Complete on	Lump Sum

Eagle River Road

660(7A)	Temporary Signal System Complete at	Lump Sum

Artillery Rd / Eagle River Rd

660(7B)	Temporary Signal System Complete at	Lump Sum

Old Glenn Hwy / South Business Blvd

660(7C)	Temporary Signal System Complete at 	Lump Sum

Old Glenn Hwy / Eagle River Loop Rd

660(7D)	Temporary Signal System Complete at	Lump Sum

Old Glenn Hwy / North Eagle River Access Rd

660(17A)	Traffic Signal System Modifications at	Lump Sum

Artillery Rd / Eagle River Rd

660(17B)	Traffic Signal System Modifications at	Lump Sum

Old Glenn Hwy / South Business Blvd

660(17C)	Traffic Signal System Modifications at	Lump Sum

Old Glenn Hwy / Eagle River Loop Rd

660(17D)	Traffic Signal System Modifications at	Lump Sum

Old Glenn Hwy / North Eagle River Access Rd

660(20)	Highway Lighting System Modifications on	Lump Sum

Old Glenn Highway

660(18)	Adjust Junction Box	Each

660(21)	Signal Mast Arm Sign Support	Each

660(22)	Signal Mast Arm Sign Support with Luminaire	Each

660(26)	Signal System Timing and Adjustments	Contingent Sum

Section 661
Electrical Load Centers

661-3.01 CONSTRUCTION REQUIREMENTS.  After the last paragraph, add the following.  Notify Diane Sanders with the State of Alaska, Maintenance & Operations Division, at 269-5700, of all new load center installations.  Provide all pertinent load center information so billing can be coordinated with MEA.

Add the following Subsection:

661-3.02 LOAD CENTER REMOVAL.  Where identified on the Plans, remove existing load centers and deliver those belonging to the Municipality of Anchorage to the MOA signals maintenance yard.  Contractor will provide a one-week notice of intent to deliver salvaged materials, to coordinate location and time of delivery.  Contact Bill Snyder at 343-8355.

For removal of ADOT&PF load centers, the Contractor shall notify the Engineer 5 days prior to removal.  The Engineer will identify those load centers to be salvaged.  The Contractor will deliver the salvaged load centers to the ADOT&PF Maintenance Yard located in Anchorage.

All remaining, removed load centers will become the property of the Contractor.

661-5.01 BASIS OF PAYMENT.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

661(7)	Remove Existing Load Center	Each

Add the following Section:

Section 662
Signal Interconnect

Special Provisions

662-1.01 DESCRIPTION. This item consists of all work required to furnish and install signal interconnect in conduit between the controller assemblies shown on the plans along the route indicated, or on a route as directed by the Engineer.

662-1.02 REGULATIONS AND CODE. Complete all work in accordance with these specifications and Section 660, Signals and Lighting.  The Department requires third-party certification for high-density polyethylene conduit.

662-2.01 MATERIALS. Submit all materials for review and approval per the requirements of subsection 660-1.03, Equipment List and Drawings.

Furnish a 25 pair #19 telephone cable conforming to REA Specification PE-39 for the interconnect cable.  Install the interconnect cable in a 50 millimeter polyethylene conduit.

Encapsulate completed splices in waterproof reenterable type splice kits of the same type used for loop lead-in cable splices. REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers" provides a list of acceptable splice materials.

662-2.02 CONDUIT. Use rigid metal conduit that meets the requirements set forth in Section 660 of the specifications.

662-2.03 JUNCTION BOX. Furnish pre-cast, reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  Install junction box lids made of cast iron.

662-3.01 CONSTRUCTION REQUIREMENTS.  The signal interconnect consists of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.

Install the polyethylene conduits at least 765 mm below finished grade.

Install junction boxes at all abrupt changes in conduit alignment and on 90 meter maximum centers. Angle points and curves with delta angles greater than 45 degrees constitute an abrupt change.  Install Type 1A junction boxes, except when you need to splice interconnect cables together.  Complete all interconnect cable splices in Type II or III junction boxes. Complete all splices in accordance with Rural Electrification Administration (REA) Specification PC-2 for splicing telephone cables.  You may determine the locations for making signal interconnect splices. The Engineer, however, will not allow splices to be made at low points in the terrain or the bottom of sag vertical curves.  Keep splices in the interconnect cable to an absolute minimum, and get the splice locations approved by the Engineer beforehand.

Furnish the controller cabinets with terminal blocks for the interconnect cable.

662-3.02 EXCAVATING AND BACKFILLING. Backfill the excavations according to Section 204.

The Engineer will not allow ripping or plowing for installation of conduit. Backfill around the polyethylene conduit with a 150 mm lift of material free of rocks exceeding a 25 mm maximum dimension.

662-4.01 METHOD OF MEASUREMENT. The Engineer will measure signal interconnect by the meter from the center of junction box to center of the next junction box, following the slopes of the existing ground.

662-5.01 BASIS OF PAYMENT. The contract unit price paid per meter for signal interconnect constitutes full compensation for furnishing all work required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under Item 660(1) Traffic Signal System Complete.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

662(1)	Signal Interconnect	Meter

(6/15/00)R67M98

Add the following Section:

Section 669
Automated Traffic Recorders

Special Provisions

669-1.01 DESCRIPTION. This work shall consist of furnishing and installing four automated traffic recorder stations.

An Automated Traffic Recorder (ATR) station is a vehicle detection system and may contain a traffic volume counter, an Automated Vehicle Classifier (AVC), a Weigh-In-Motion (WIM) system and/or other equipment.  ATRs are operated and maintained by personnel of the Highway Data Section (HDS); main office located at 2200 E. 42nd Ave., Anchorage, phone (907) 269-0876.

The simplest form of ATR is an Intermittent Volume Recorder (IVR), which consists of inductive loop sensors connected to a traffic counter.  In each traffic lane, an inductive loop is buried beneath the pavement.  Lead wires run from the sensors to a type CBA1 cabinet located at the side of the road.  At the type CBA1 cabinet, the lead wires connect to the traffic counter. Traffic volume information is collected by a portable, battery-operated traffic counter that detects passage of vehicles and stores the data for later retrieval.

The locations of traffic detection sensors and cabinets, shown on the plans are approximate and the Engineer shall establish the exact locations in the field.

A general description of the Automated Traffic Recorders on the project is as follows:

H1:	Old Glenn Highway Station 3+250, IVR, 4 lane vehicle sensor array with 1 Presence Loop per lane, 10m right offset CBA1 cabinet without electrical and without telephone service.

The Contractor shall supply and install the CBA1 cabinet, Junction Boxes, Conduit and loop presence sensors as shown on the Plans.  The Contractor shall install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

H2:	Old Glenn Highway Station 3+620, IVR, 4 lane vehicle sensor array with 1 Presence Loop per lane, 10m left offset CBA1 cabinet without electrical and without telephone service.

The Contractor shall supply and install the CBA1 cabinet, Junction Boxes, Conduit and loop presence sensors as shown on the Plans.  The Contractor shall install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

H3:	Old Glenn Highway Station 4+180, IVR, 4 lane vehicle sensor array with 1 Presence Loop per lane, 10m right offset CBA1 cabinet without electrical and without telephone service.

The Contractor shall supply and install the CBA1 cabinet, Junction Boxes, Conduit and loop presence sensors as shown on the Plans.  The Contractor shall install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

H4:	Old Glenn Highway Station 4+970, IVR, 4 lane vehicle sensor array with 1 Presence Loop per lane, 10m right offset CBA1 cabinet without electrical and without telephone service.

The Contractor shall supply and install the CBA1 cabinet, Junction Boxes, Conduit and loop presence sensors as shown on the Plans.  The Contractor shall install Inductive Loop Presence Sensors beneath the new pavement by burial as shown on the Plans.

669-1.02 REGULATIONS AND CODE.  All materials and workmanship shall conform to the standards of the Underwriter's Laboratories, Inc. and the National Electrical Safety Code and local safety code requirements, where applicable.

All electrical equipment shall conform to the standards of the National Electrical Manufacturer's Association, where applicable.

669-2.01 MATERIALS.  All materials provided shall be new, unless otherwise stated, and shall meet the following requirements:

1.	Wiring.  All wiring shall be in accordance with subsection 660-2.09, Wiring.  All single wire conductors and cables shall have clear, distinctive and permanent markings on the outer surface throughout the entire length giving the manufacturer's name or trademark, the insulation type-letter designation, the conductor size, voltage rating and the number of conductors if a cable.  All wires and cables must be home run labeled in each junction box and cabinet; for example, W1SLA (for wire) and GaSLA (for cable) as shown on the plans.

2.	Conduit.  All conduit shall be in accordance with subsection 660-2.05, Conduit. All conduit, except for PVC conduit forming the inductive loops, shall be galvanized rigid metal. All grounding bushings shall be plastic-sleeved to minimize the potential for  insulation damage during wire pulls.

3.	Junction Boxes.  All junction boxes shall be in accordance with subsection 660-2.06, Junction Boxes.  The covers of all junction boxes used for loops or sensor wires shall be labeled 'TRAFFIC'.  The covers of all junction boxes used to provide electrical service to ATR installations shall be labeled 'ELECTRIC’.  Junction boxes for 120V/240V electrical service shall be kept completely separate from junction boxes containing loop or sensor wiring.

4.	Terminal Blocks.  All terminal blocks shall have nickel, silver or cadmium plated brass binder-head screw terminals.  Terminal blocks shall be a barrier type, rated 600 VAC at 20 Amps, sized for 12-18 AWG wire with removable shorting bars in each position and with integral type marking strips.

5.	Presence Loops.  All presence loops shall be in accordance with subsection 660-2.08, Conductors.  Conductors used for detector presence loops shall be UL listed as IMSA specification #51-5-1984 single conductor PVC nylon with tube jacket, type THHN, #14 AWG.

Multiple pair loop lead-in cable shall consist of twisted pairs of 18AWG stranded tinned copper wire.  Each twisted pair shall have its own 20AWG tinned copper drain wire.  An aluminum foil shield shall surround each individual bundle of twisted pair and drain wire.  Multiple pair loop lead-in cable shall have an overall PVC or PE outer jacket.

6.	Style CBA1 Cabinets.  All cabinets shall meet or exceed a NEMA Type 3R rating.  Style CBA1 cabinets shall meet the following requirements:

a.	Cabinet Dimensions. Unless otherwise shown on the plans, the cabinet shall be 518-mm high, 440-mm wide, and 412-mm deep.

b.	Cabinet Construction. The cabinet and hinged door shall be constructed from sheet aluminum alloy, and shall be unpainted with a smooth exterior finish.  All welds shall be neatly formed and free of irregularities.  All inside and outside edges of the cabinet shall be free of burrs.  Cabinet shall be provided with aluminum mounting plate as shown on the plans.

c.	Shelf. An adjustable equipment shelf shall be mounted inside of the cabinet.  The adjustable equipment shelf shall be supported on both sides and located 75 mm upwards from the bottom of the cabinet.  The adjustable equipment shelf shall be constructed from 5052-H32 or better sheet aluminum alloy with a minimum thickness of 3.15 mm.

7.	Pavement. Pavement materials shall meet the following requirements:

a.	Asphalt Pavement. Materials used for asphalt pavement shall conform to Section 401, Asphalt Concrete Pavement for Asphalt Concrete, Type I and shall be approved by the Engineer.

669-3.01 CONSTRUCTION REQUIREMENTS.

1.	Wiring.

a.	Referenced Requirements. All wiring shall be installed in accordance with subsection 660-2.09, Wiring.

b.	Termination. At junction boxes, unused pairs shall be terminated within splices.  At cabinets, unused pairs shall be terminated to a terminal block.  At terminal blocks, all conductors, including unused spares, shall terminate and be soldered to "spade" type terminal lugs.

c.	Relief. All wiring shall have at least 0.6 meters of slack cable in each junction box and at least 1.8 meters of slack cable available in the equipment cabinet prior to the terminal block.

d.	Labeling. All wiring shall be labeled in all junction boxes and at all terminal blocks.

2.	Conduit.

a.	Referenced Requirements. All conduit shall be installed in accordance with subsection 660-2.05, Conduit, or as indicated on the plans.

b.	Pull Cords. Nylon pull cords shall be left in all conduits larger than 25 mm and in all spare conduits.

c.	Bushings. Plastic or plastic-sleeved bushings shall be in place before wire pulls are performed.

3.	Junction Boxes.

a.	Referenced Requirements. All junction boxes shall be installed in accordance with subsection 660-2.06, Junction Boxes, or as indicated on the plans.

b.	Voltage Limitation. Junction boxes used for ATR installations shall not contain any wiring of systems at or greater than 24 V or conduits carrying wiring of systems at or greater than 24 V.

4.	Terminal Blocks.

a.	Terminal Block Placement. Terminal blocks within cabinets shall be mounted so that all terminals are easily accessible from the front of the cabinet.

b.	Labeling. All terminal blocks and wire pairs shall be clearly labeled on the block.

c.	Termination. All conductors, including unused spares, shall terminate and be soldered to “spade” type terminal lugs

5.	Presence Loops.

a.	Referenced Requirements. All presence loops shall be installed and constructed in accordance with subsection 660-3.08, Installation Details, unless otherwise specified on the plans.

b.	Placement Design Adherence. The plans are not schematics; installation of the presence loops shall closely conform to the location and layout of conduit runs shown in the plans.

c.	Presence Loop Dimensions. Unless otherwise noted, presence loops shall be formed of four turns of wire, and shall be 1.83 m square with plus-or-minus 25mm (± 25mm) tolerance.

d.	Lead-in Conduit. All lead-in conduit from edge of pavement to the presence loops shall be straight and perpendicular to the center line of the road.

e.	Presence Loop Alignment. Presence detector loops shall be centered in the traffic lane plus-or-minus 25mm (± 25mm) tolerance.

f.	Presence Loops in Asphalt.

I.	Presence Loops In Existing Asphalt. All presence loops installed through existing asphalt pavement shall be installed using full-lane-width cuts a minimum of 2.43m in length.  Inductive loops shall be centered in the 2.43m cut and spaced a minimum distance of  0.3 m from the edge of the cut.  All edges of the cuts shall be heated and tack-coated during patching to ensure full adhesion.  All full-width patches shall be rolled sufficiently to ensure compaction equal or better than the existing asphalt, and to prevent edge ridges or settling of the patch from 'telegraphing' through the final lift asphalt.  Compaction tests shall be required at the discretion of the Project Engineer.

II.	Presence Loops In New Asphalt. All loops installed in new asphalt paving shall be installed immediately prior to final paving of the particular section of road.  Installation of loops after final lift paving shall not be permitted.

6.	Cabinets.

a.	Cabinet Placement and Orientation. All Cabinets shall be installed out of the clear zone and with the doors facing away from the road.

b.	Conduit Entry. All conduits entries for any above-ground enclosure shall be made through the bottom of the enclosure.  No conduit runs shall be cut through the sides or top of any above-ground enclosure.

c.	Style CBA1 Cabinets.

I.	Mounting. The Style CBA1 cabinets shall be mounted on a 63mm perforated steel tube and supported with a sleeved concrete foundation as shown on the plans.

II.	Terminal Blocks. Terminal blocks in CBA1 cabinets shall be mounted vertically as shown on the plans.

7.	Asphalt Pavement Smoothness: There shall be no transverse seams, joints or roughness within 15.24 m of any inductive loops placed in asphalt pavement section.  The finished surface of the asphalt shall be tested with a straightedge 3 m long.  The surface shall not vary more than 6 mm from the lower edge of the straightedge within 15.24 m of all sensors at the ATR installations. At the discretion of the Engineer, a profilograph equipped with a chart recorder shall be run along each wheelpath of each lane.  The profilograph will be supplied by the Highway Data Section and shall be operated by Contractor personnel.  Each profilogram shall extend 15.24 m beyond either end of the ATR installation.  The asphalt surface as recorded by the chart recorder shall not vary more than 6 mm in 3 m of distance.

8.	Field Inspection. Before installation of conduit, wiring, inductive loops or cabinets, the Contractor shall notify the Engineer.  Notification shall be given in writing, a minimum of 3 working days prior to installation (excluding Saturday, Sunday and State or Federal Holidays).  The Engineer shall be present to approve the installation prior to final burial or encasement.  Any unacceptable installations shall be corrected and re-inspected for completeness prior to burial or encasement.  Any burial or encasment without approval by the Engineer shall be uncovered, removed, and/or replaced at the Contractor's expense.  Any expense or delay in the project scheduling will be the responsibility of the Contractor.

669-3.02 ACCEPTANCE TESTING. The Contractor shall perform acceptance testing on all ATR installations.

1.	General Tests. The contractor shall perform tests for the ATR installations in accordance with subsection 660-3.08, Installation Details.

669-3.05 DELIVERABLES. All deliverables shall be submitted to the Engineer prior to final approval of the work or as otherwise called for herein.

1.	Materials Submittal.

a.	Format and Contents. The Contractor shall provide a Materials Submittal of proposed equipment and materials for the ATR installations.  The Materials Submittal shall consist of three collated copies of an equipment and materials portfolio.  Each identical portfolio shall contain information of sufficient detail to determine the suitability of the equipment and materials proposed.

b.	Table of Contents. Each portfolio shall include a table of contents listing each item's intended uses, item description, product name, manufacturer, model or part number and reference to associated information within the portfolio.

c.	Reference Drawings. The Materials Submittal shall include a detailed shop drawing of each equipment cabinet showing the location of all mounted components.

d.	Delivery Interval. The Materials Submittal shall be delivered for review and approval of the Engineer within thirty days following award of the contract.

e.	Liability. The State of Alaska will not be liable for any materials purchased, labor performed, equipment used or delay to the work before all equipment and materials have been reviewed and approved.

2.	As-Built Plans.

a.	The Contractor shall prepare four complete sets of as-built Plans which will be current with the construction.  These as-built plans shall detail all construction changes made to the ATR design and include the following information on the appropriate sheets:

I.	location and depth of all inductive loops, piezo sensors, conduit runs and scales.

II.	locations of all equipment cabinets and junction boxes.

III.	station and offset of all junction boxes

b.	Three sets of as-built plans shall be presented to the Engineer, and one set shall be affixed to the inside of the cabinet door at the appropriate Automated Traffic Recorder Installation in a waterproof, clear plastic holder.

c.	Redlines of full size construction Plans will be acceptable as-builts.

3.	Photographs.

a.	The Contractor shall provide photographic prints, 35 mm negatives and Kodak PictureCD format CDROMs documenting all sensor installations.

b.	Photographs, negatives and CDROMs shall be delivered organized in one or more white colored, D-ring style, 3 ring binders with clear insert overlays on fronts and spines.  Photographs and negatives will be mounted in archival quality polypropylene pocketed sheets.  CDROMs will be placed in CD storage sheets inside the binders.

c.	The photographs shall be 127 mm x 178 mm color prints.

d.	Each photograph shall be labeled with the identification of its subject. ATR station and device designation as indicated on the plans will be used as identification whenever possible (example: H1 - W1NLA ).  Labels will be photographed with the subject and will be rendered large enough to be read with the unaided eye.

e.	The photographs shall show the inductive loops and conduit in place prior to covering with gravel and pavement for asphalt pavement sites, or prior to covering with epoxy compound for concrete pavement sites. The photographs shall include:

I.	two or more overall views of each ATR installation showing placement of the inductive loops.

II.	one or more views of each loop showing the loop and the conduit to the nearest junction box.

4.	Test Results. Written or printed copies of the final results of all tests, signed by the Contractor, shall be provided to the Engineer prior to acceptance of the Automated Traffic Recorder Installation.  Tests will be conducted in accordance with Subsection 660-3.08, Installation Details.

5.	Manuals. The Contractor shall provide to the Engineer all installation, repair and operation manuals for all Automated Traffic Recording equipment, telemetry equipment, dataloggers, and environmental sensors.

6.	Materials.

a.	The Contractor shall provide to the Engineer any ATR equipment, sensors, and all epoxy grout remaining after installation.

b.	The contractor shall palletize the Deliverable Materials.

c.	The contractor shall group the contents of each pallet by like items.

d.	The contractor shall attatch to each pallet a sealed plastic pouch containing complete copies of all Material Safety Data Sheets that apply to the contents of that pallet.

e.	The contractor shall provide an itemized list of all Deliverable Materials. For each item, the list shall detail:

I.	Item description: including nature of the item, brand name, manufaturer name, model number, type number and serial number.

II.	Item condition

III.	Item quantity

f.	The contractor shall provide complete copies of all Material Safety Data Sheets that apply to the Deliverable Materials. The contractor shall attatch these Material Safety Data Sheets after the last page of the Deliverable Materials list.

669-4.01 METHOD OF MEASUREMENT. The quantity to be paid for will be the actual number of completed and accepted Automated Traffic Recorder Installations as shown on the Plans or as directed by the Engineer.

669-5.01 BASIS OF PAYMENT. The contract unit bid price for all Automated Traffic Recorder installations shall be full compensation for furnishing all equipment, labor and materials necessary to complete the work as specified, with the following exceptions:

1.	Excavation and Backfill materials required will be paid for under their respective pay items.

2.	Asphalt required will be paid for under a separate pay item.

As-built plans and acceptance testing required for these installations will not be paid for separately, but will be subsidiary to the Automated Traffic Recorder Installations.

All Type IA J-Boxes, 27 mm rigid conduit, and 53 mm rigid conduit associated with the Automated Traffic Recorders are subsidiary to the 669 items. Traffic Control required to install Automated Traffic Recorders is paid for under 643 items.

WITHHOLDING.  TO ENSURE FULL COMPLIANCE UNDER THIS SECTION, TWENTY PERCENT (20%) OF THE BILLINGS FOR SECTION 669(1) SHALL BE WITHHELD UNTIL ALL DELIVERABLES HAVE BEEN PROVIDED TO THE ENGINEER AS REQUIRED AND APPROVAL OF THE DELIVERABLES BY THE HIGHWAY DATA SECTION HAS BEEN RECEIVED IN WRITING.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

669(1)	Automated Traffic Recorders H1, H2, H3, H4	Lump Sum

Section 670
Traffic Markings

Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Under item 4 Methyl Methacrylate Pavement Markings, delete the last sentence in the first paragraph and substitute the following: Do not apply striping to the new asphalt until the asphalt has cured for the duration listed below and at the Engineer’s discretion.

Stone Mastic Asphalt Concrete	30 days

All others	15 days

Under item 4 Methyl Methacrylate Pavement Markings. , delete the second paragraph and substitute the following: Apply Methyl Methacrylate marking material with truck mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in litres.

(04/05/02)R246M98

Add the following under item 4. before the third paragraph:  A film test strip will be required at the beginning of each striping shift, and when there is a change in the asphalt type. In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

(09/04/01)R221M98

Under item 4. Methyl Methacrylate Pavement Markings.  delete the first sentence in the fifth paragraph and substitute the following: Apply markings for lane lines, edge lines, and center lines at a yield thickness of 2.3 mm (1 liter will yield a 2.3 mm thick stripe 100 mm wide by 4.348 m in length).

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

2.	Width of Stripe. The width shall not vary more than 6 mm in width in any 15m longitudinal run from the plan quantity.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis: The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.  The Department will limit the final quantity to 115% of the Plan quantity.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B), Methyl Methacrylate Pavement Markings and no separate payment shall be made.

Add the following: The Department will pay the contract unit price for the volume of Methyl Methacrylate accepted by the Engineer up to a maximum of 115% of the quantity shown in the Plans.  All Methyl Methacrylate material over-runs above 115% of the plan quantity shall be paid for by the Contractor at no expense to the Department.

(04/05/02)R246M98

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

670(10B)	Methyl Methacrylate Pavement Markings	Liter

Section 702
Asphalt Materials

Special Provisions.

702-2.01 ASPHALT CEMENTS. Add the following: Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T 53 and ASTM D 5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T 53	(none)	49oC	52oC

Toughness (min)	ASTM D5801	(none)	12.4 N-m	12.4 N-m

Tenacity (min)	ASTM D5801	(none)	8.5 N-m	8.5 N-m

(09/18/00)R244M98

Section 703
Aggregates

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE
Percent Passing By Weight

| Sieve Designation | Grading D-1 |
| --- | --- |
| 37.5 mm |  |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 50-79 |
| 4.75 mm | 35-58 |
| 2.36 mm | 20-47 |
| 0.600 mm | 10-26 |
| 0.300 mm | 6-19 |
| 0.075 mm | 0-6 |

(2/28/00)R117M98

Standard Modification

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.

(06/25/99)M 82

Add the following Subsections:

703-2.13 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT

Coarse Aggregate (retained on the 4.75 mm sieve).  Coarse aggregate shall be free from clay balls, vegetative matter or other deleterious matter and consist of sound, tough, durable rock of uniform quality not coated with dirt or other finely divided mineral matter.  Crush stone or cobbles to such a degree that all faces are fractured and meet the following requirements:

Property				Test Method		Requirement

Percent of Wear			AASHTO T 96	30 max.

Degradation				ATM T-13		30 min.

Percent Sodium Sulfate Loss	AASHTO T 104	9   max. (5 cycles)

Percent Fracture			WAQTC TM 1

All Faces 						75 min.

Thin & Elongated Particles		ATM T-9

3 to 1							20% max.

5 to 1							5%   max.

Absorption				AASHTO T 85	2%   max.

Nordic Abrasion						12.0 max.

Fine Aggregate (passing the 4.75 mm sieve).  Consist entirely of 100 percent crushed aggregate and be non-plastic as determined by WAQTC FOP for AASHTO T 90.  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Mineral Filler.  Meet AASHTO M 17.  Use rock dust from the aggregate crushing operation or crushed limestone free of agglomerations and sufficiently dry to flow freely.

Blended Aggregate.  Blend the aggregate fractions to meet the grading requirements of Table 703-9 as determined by WAQTC FOP for AASHTO T 27/T 11.

TABLE 703-9

STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation			Requirement

19.0 mm			100

12.5 mm 			76-85

9.5 mm			 < 60

4.75 mm			20-27

2.36 mm			14-20

0.075 mm			  8-11

(08/19/02)R164M98

703-2.14 RIVER ROCK VENEER.  For rock fence post.  Rounded river rock, uniformly graded from 100 to 200 mm with all rock faces round and intact, not fractured, cracked or chipped.

Section 706
Concrete and Plastic Pipe

Standard Modifications

706-2.07 CORRUGATED POLYETHYLENE PIPE. Replace “Type S” with “Type S or Type D”.

(02/08/01)M 97

Section 710
Fence and Guardrail

Add the following:

710-2.12 ROCK FENCE POSTS

1.	River Rock Veneer.  Rounded river rock, uniformly graded from 100 to 200 mm with all rock faces round and intact, not fractured, cracked or chipped.

2.	Steel Tabs.  Use 26 gage steel tabs, typical of masonry construction, to anchor rock veneer to rock fence posts.

710-2.13 TRELLIS FENCE.  Furnish metal slats, hardware, and cable, as specified, meeting the following requirements:

1.	Metal Slats. Meet the size and length as shown on plans.  Metal slats shall meet requirements of AASHTO M 180/183 and shall be galvanized meeting AASHTO M 11.

2.	Steel Cables. Meet the size and length as shown on plans.  Meet AASHTO M 30.

3.	Hardware. Provide and install as shown on plans.  Meet AASHTO M 180.  Galvanize after fabrication of all fittings, bolts, washers and accessories meeting AASHTO M 111 or AASHTO M 232, whichever applies.

710-2.14 POST AND RAIL FENCE. Furnish wood posts, as specified, meeting the following requirements:

1.	Wood Posts and Rails.  Use untreated cedar timbers in sizes as shown on Plans.  Wood shall be sound and free of rot, fractures, or chips.

Section 712
Miscellaneous

Special Provisions

712-2.06 FRAMES, GRATES, COVERS AND LADDER RUNGS. Add the following:

Ductile iron castings		ASTM A536 for grade 60-401.

(2/22/00)R78M98

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

2.	Performance Properties: Add the following:

k.      Adhesion:	To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

Section 724
Seed

724-2-02. MATERIALS. Delete this Subsection in its entirety and substitute the following:

Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Delete Table 724-1 in its entirety and substitute the following:

TABLE 724-1
SEED REQUIREMENTS

Seed Mix:  Schedule A

PROPORTION

NAME	BY WEIGHT	PURITY	GERMINATION

Arctared Fescue

(Festuca rubra)	75%	95%	85%

Annual Ryegrass

(Lolium perenne)	25%	85%	80%

Section 726
Topsoil

Special Provisions

726-2.01 TOPSOIL. Delete last sentence in second paragraph and substitute the following:

The Contractor shall submit to the Engineer, 10 working days prior to final placement, a soil analysis for particle size, nutrient content and organic content, before any topsoil shall be accepted for this project.  The Engineer may test the topsoil at any time to verify compliance with the topsoil analysis.  If the supplied topsoil does not meet specifications in this section, the Contractor shall supply new topsoil of a quality required to meet the section standards.

Delete the fertilizer requirements (not the limestone requirements) as stated in this subsection and substitute the following:

Nitrogen	50 – 75 PPM
Phosphoric Acid	112 – 165 PPM
Potassium	121 – 200 PPM

Replace Item No. 3 with the following:

TABLE 726-1
	TOPSOIL REQUIREMENTS

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 12.5 mm | 100 |
| 4.75 mm | 95-100 |
| 1.18 mm | 64-90 |
| .075 mm | 30-60 |
| Organic Content* | 10% - 40% |
| Limestone | 3.4 Mg/hectare |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267ATM T-6.

Add the following:

Limestone shall be incorporated into the topsoil at a sufficient rate to attain a pH of between 6.0 and 7.0.

Section 727
Soil Stabilization Material

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Recycled Paper (“wood cellulose”) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch. Blended mulch may contain up to 50% recycled paper.  The mulch shall meet the following requirements:

a.	Contains no growth or germination inhibiting factors.

b.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry.

c.	Mulch can be applied uniformly on the soil surface.

d.	Will not create a hard crust upon drying and have moisture absorption and retention properties and the ability to hold grass seed in contact with the soil.

e.	Dyed a suitable color to facilitate inspection of its placement.

Ship the mulch material in packages of uniform weight (plus or minus 5%) and bear the name of the manufacturer and the air-dry weight content.

Use a commercial tackifier on all areas steeper than 3:1.  Use the amount recommended by the manufacturer.

(8/19/99)R206M98

Section 729
Geotextiles

Standard Modifications

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT.

1. Separation. Replace “(medium survivability)” with “(Class 3)”.

2. Reinforcement. Replace “Separation (high survivability)” with “Stabilization”.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL.

2. Erosion Control. Replace “Erosion Control” with “Permanent Erosion Control”.

729-2.04 SEDIMENT CONTROL. Replace the first sentence with “Meet AASHTO M 288 for Temporary Silt Fence”.

(02/08/01) M98

Section 730
Sign Materials

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

(2/29/00)R81M

Standard Modification

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

PERMITS / TEMPORARY CONSTRUCTION PERMITS

APPENDIX B

EROSION AND SEDIMENT CONTROL PLAN (ESCP)

APPENDIX C

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX D

MATERIALS CERTIFICATION LIST

APPENDIX E

SIGN DETAILS

APPENDIX F

UTILITY COMPANY REQUIREMENTS