PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

STANDARD SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

2002 (USC)

HUFFMAN ROAD / ELMORE ROAD INTERSECTION IMPROVEMENTS

MGS-0001 (261) / 53934

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	The Standard Specifications for Highway Construction 2002 USC units may be viewed or downloaded at no charge from the Statewide Design and Engineering Service Division’s external website.

e.	Geotechnical Report Titled "Engineering Geology & Soils Report Centerline Soils - Huffman Road Gregory Street to Bragaw Street Project #57426  Central Region March 1988".

3	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix D.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

TABLE OF CONTENTS

Section 101 Definitions and Terms	1

Section 102 Bidding Requirements and Conditions	2

Section 103 Award and Execution of Contract	3

Section 105 Control of Work	6

Section 106 Control of Material	11

Section 107 Legal Relations and Responsibility to Public	14

Section 108 Prosecution and Progress	17

Section 109 Measurement and Payment	18

Section 120 Disadvantaged Business Enterprise (DBE) Program	19

Section 202 Removal of Structures and Obstructions	30

Section 203 Excavation and Embankment	32

Section 301 Aggregate Base Course	34

Section 401 Asphalt Concrete Pavement	36

Section 511 Modular Block Retaining Wall	40

Section 603 Culverts and Storm Drains	44

Section 604 Manholes and Inlets	45

Section 606 Guardrail	47

Section 608 Sidewalks	48

Section 609 Curbing	50

Section 615 Standard Signs	51

Section 618 Seeding	52

Section 619 Soil Stabilization	54

Section 620 Topsoil	56

Section 639 Approaches	57

Section 642 Construction Surveying and Monuments	58

Section 643 Traffic Maintenance	59

Section 644 Services to be Furnished by the Contractor	64

Section 645 Training Program	66

Section 646 CPM Scheduling	70

Section 647 Equipment Rental	71

Section 660 Signals and Lighting	74

Section 670 Traffic Markings	79

Section 703 Aggregates	82

Section 710 Fence and Guardrail	83

Section 712 Miscellaneous	84

Section 724 Seed	85

Section 726 Topsoil	86

Section 730 Sign Materials	87

Appendix A	Permits / Temporary Construction Permits
Appendix B	Erosion and Sediment Control Plan
Appendix C	Construction Surveying Requirements
Appendix D	Materials Certification List
Appendix E	Special Details
Appendix F	Utility Company Requirements

Section 101
Definitions and Terms

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11on minus 3 inch material.

(11/29/01)R1USC

Section 102
Bidding Requirements and Conditions

Special Provisions

102-1.10 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.

(10/23/02)R171USC02

Section 103
Award and Execution of Contract

103-1.06 INSURANCE REQUIREMENTS. Delete this Subsection in its entirety and substitute the following:  The Contractor shall provide evidence of insurance with an insurance carrier or carriers satisfactory to the Department covering injury to persons and property suffered by the State of Alaska or by a third party as a result of operations under this contract by the Contractor or by any subcontractor. The Contractor's insurance shall provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this Contract. All insurance policies (a) shall comply with AS 21 and (b) shall be issued by insurers that (i) are licensed to transact the business of insurance in the State of Alaska under AS 21 and (ii) have a financial rating acceptable to the Department. The Contractor shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.

Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor’s indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

The Contractor shall maintain the following policies of insurance with the specified minimum coverages and limits in force at all times during the performance of the Contract:

1.	Workers' Compensation: as required by AS 23.30.045, for all employees of the Contractor engaged in work under this Contract. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who performs work under this Contract. The coverage shall include:

a.	Waiver of subrogation against the state and Employer's Liability Protection at $500,000 each accident/$500,000 each disease;

b.	“Other States” endorsement if the Contractor directly utilizes labor outside of the State of Alaska;

c.	United States Longshore and Harbor Workers’ Act Endorsement, whenever the work involves activity over or about navigable water; and

d.	Maritime Employer’s Liability (Jones Act) Endorsement with a minimum limit of $1,000,000, whenever the work involves activity form or on a vessel on navigable water.

2.	Commercial General Liability: on an occurrence policy form covering all operations with combined single limits not less than:

a.	$1,000,000 Each Occurrence;

b.	$1,000,000 Personal Injury;

c.	$2,000,000 General Aggregate; and

d.	$2,000,000 Products-Completed Operations Aggregate.

3.	Automobile Liability: covering all vehicles used in Contract work, with combined single limits not less than $1,000,000 each occurrence.

4.	Umbrella Coverage: for Contract amounts over $5,000,000 not less than $5,000,000 umbrella or excess liability. Umbrella or excess policy shall include products liability completed operations coverage and may be subject to $5,000,000 aggregate limits. Further, the umbrella or excess policy shall contain a clause stating that it takes effect (drops down) in the event the primary limits are impaired or exhausted.

The State of Alaska shall be named as an additional insured on policies required by paragraphs 2 thru 4 above. All of the above insurance coverages shall be considered to be primary and non-contributory to any other insurance carried by the State of Alaska, whether through self-insurance or otherwise.

In any contract or agreement with subcontractors performing work, the Contractor shall require that all indemnities and waivers of subrogation it obtains, and any stipulation to be named as an additional insured it obtains, shall also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as an additional named indemnitee and as an additional insured.

The apparent low bidder shall furnish evidence of insurance to the Department before award of the Contract. The evidence shall be issued to the Department and shall be either a certificate of insurance or the policy declaration page with all required endorsements attached and must:

1.	Denote the type, amount, and class of operations covered;

2.	Show the effective (and retroactive) dates of the policy;

3.	Show the expiration date of the policy;

4.	Include all required endorsements; and

5.	Be executed by the carrier's representative.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number). The insurance carrier agrees that it shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.”

The Department’s acceptance of deficient evidence of insurance does not constitute a waiver of Contract requirements.

Failure to maintain the specified insurance or to provide substitute insurance if an insurance carrier becomes insolvent, is placed in receivership, declares bankruptcy, or cancels a policy may be grounds for withholding Contract payments until substitute insurance is obtained, and may, in the Department's discretion, be grounds for declaring the Contractor in default.

(05/06/03)R271USC02

Section 105
Control of Work

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following:

The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital Anchorage Water & Wastewater Utility AT&T Alascom, Inc. Chugach Electric Association Digline - Boise loan to AK ENSTAR Natural Gas, Inc. GCI Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association PTI Communications, Inc. ACS of the Northland Phillips Petroleum Rogers Cable Systems of AK, Inc. Signature Flight Support SOA-DOT/PF Anchorage M&O TelAlaska, Inc. Tesoro Petroleum Co. Unocal Oil & Gas

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the Plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

(05/31/01)R3M98

The Contractor will be required to provide each utility fifteen (15) calendar days advance written notice of any relocation work to begin.

1.	ENSTAR NATURAL GAS COMPANY (ENSTAR)

Contact: Dave Titus (264-3746)

Enstar has existing natural gas distribution lines on the north side of Huffman Road for the entire length of the project.  There are also numerous natural gas crossings for service to Lorraine Street, Elmore Road, and Atherton Road.  This project will result in an impact to Enstar’s facilities from Station 117+50 to 121+50,and at Lorraine Street.  Impact to Enstar’s facilities is mainly due to ditch construction.  The facilities will be adjusted to ensure minimum cover and will remain in the same location.  Enstar will require 12 calendar days to complete this relocation work.

In addition to the natural gas distribution line, Enstar has an existing 12-inch steel transmission line that crosses Huffman at Elmore Road.  Improvements to the Huffman Road/Elmore Road intersection are not anticipated to impact this line.  However, a 16-inch steel casing will be removed at Elmore Road.  Enstar will require 4 calendar days to complete the casing removal.

The Contractor shall allow Enstar 16 calendar days to complete the overall relocation work.

When working near Enstar Natural Gas facilities, the Contractor shall adhere to the requirements set forth in “Safety Requirements for Excavation Adjacent to Natural Gas Pipelines”, attached to these specifications in Appendix F.

Prior to commencement of construction Enstar Natural Gas Company will perform a cathodic protection sweep to verify that the system is in working order. Problems found at that time will be the responsibility of the Utility. A second sweep will be performed after all underground work has been completed, but prior to paving. The Contractor shall, in writing, give the utility four (4) calendar days notice to proceed and shall allow one (1) day for each sweep to be performed. Should either sweep detect a ground fault, the Contractor shall allow the utility time to repair the fault. If the ground fault is determined to be caused by the Contractor’s actions, the cost of repair shall be charged to the Contractor by the Utility.

2.	GCI CABLE, INC. (GCI)

Contact: Kurt Anderson (786-9257)

GCI has existing cable facilities located along the south side of Huffman Road, from Lorraine Street to Elmore Road, that will be relocated due to project impacts.  Work consists of trenching and placing new conduit, fiber optic cable and .875 coax cable.

Specifically, three (3) new 1.25” HDPE ducts, with one duct housing fiber optic cable, will be trenched and placed from the existing vault at Sta. 109+90 RT to the existing vault at Sta. 115+46 RT.  Additionally, a new .875 coax cable will be directly buried in a trench, from the existing pedestal at Sta. 112+72 RT to the existing vault at Sta. 115+46 RT.  From the existing vault at Sta. 115+46 RT, the .875 coax cable will be placed in a new 4” PVC duct running northeast to the existing pedestal at Sta. 115+68 RT.  GCI will require 20 calendar days to complete this relocation work.

Approximately 285-ft of .750 coax cable and 563-ft of (3) 1.25” HDPE ducts will be abandoned in place by GCI. Additionally, GCI will remove approximately 575-ft of fiber optic cable. GCI will require 6 calendar days for this removal and subsequent cutover work.

Incidental to project impacts, betterment work performed by GCI includes the placement of 4” PVC duct from Sta. 109+90 RT to Sta. 110+90 RT and from Sta. 114+46 RT to Sta. 115+46 RT.  GCI will require 3 calendar days for this installation.

The Contractor shall allow GCI 29 calendar days to complete the overall relocation work.

3.	ALASKA COMMUNICATIONS SYSTEMS, INC. (ACS)

Contact: Brad DeMontfort, General Foreman Construction/Splicing (564-1455)

ACS has an existing 100 pair and 200 pair aerial telephone lines that run on the south side of Huffman Road for the extent of the project.  The overhead telephone lines cross Huffman Road at Station 108+30, Station 115+40, Station 120+15, and Station 124+40.  Because of the addition of up to 2.5’ of fill at the Huffman Road/Elmore Road Intersection, clearance requirements for the aerial crossing at Elmore Road and Station 115+40 will not be met.  The 100 pair and 200 pair overhead telephone line crossing at Station 115+40 will be replaced with a single 400 pair underground crossing in the existing road bore.  ACS will require 15 calendar days for this relocation work.

In addition to the overhead telephone lines, ACS has an existing 12-strand fiber optics line that runs underneath Huffman Road at Elmore Road (Station 115+50).  Improvements to the Huffman Road/Elmore Road Intersection are not anticipated to impact this line.

ACS attachments to the utility pole located at Sta. 114+28 RT. will be lowered 1.5’ per a request from Chugach Electric Association.  CEA will be installing a new secondary riser at this location to serve the nearby ADOT load center.  In conjunction, a new riser will be added to the utility pole located at Sta. 115+49 RT.  ACS will require 3 calendar days for this relocation work.

The Contractor shall allow ACS 18 calendar days to complete the overall relocation work.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following projects may be under construction concurrently with this project:

1.	DeArmoun Road Improvements – STP-0510(2) / 53987

Westwind Drive to 140th Ave

Owner: ADOT&PF

Contractor: NorthStar Paving & Construction

2.	South Anchorage Area High School

Owner: Anchorage School District

Contractor: Wilder Construction (site work)

3.	Elmore Road Improvements – Project No. 00-22

DeArmoun Road to Huffman Road

Owner: MOA Department of Public Works

Contractor: Goodfellow Brothers, Inc.

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project so as to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract.

(2/1/00)R175M98

105-1.13 MAINTENANCE DURING CONSTRUCTION. Add the following: Inspect and clean all storm drain sumps and petroleum separator manholes during the construction season and prior to winter shutdowns. This inspection and maintenance of the storm drain system will not be paid for directly but will be subsidiary to work paid for under Sections 603 and 604.

(2/1/00)R4M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract.

(02/06/02)R237M98

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following: Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district.

(3/21/01)R93

Section 106
Control of Material

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.

(08/31/99)S 13

106-1.02 LOCAL MATERIAL SOURCES. Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of the sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) before beginning any operations in your surface mine.  Offer the training at each surface mine that will be used to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

a.	Site specific health and safety risks.

b.	Recognition and avoidance of hazards.

c.	Restricted areas.

d.	Warning and evacuation signals.

e.	Other special safety procedures.

f.	Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.

(05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding test method shown.

| REPLACE TEST METHOD: | WITH TEST METHOD: |
| --- | --- |
| ATM 203 | Alaska FOP for AASHTO T 267 |
| WAQTC FOP for AASHTO T 89/T 90 | WAQTC FOP for AASHTO T 89 WAQTC FOP for AASHTO T 90 |
| WAQTC FOP for AASHTO T 180 | WAQTC FOP for AASHTO T 99/T 180 and WAQTC TM 9 |
| WAQTC FOP for AASHTO T 224 | Same |
| ATM 212 | ATM T-12 |
| WAQTC FOP for AASHTO T 310 | WAQTC TM 7 |
| WAQTC FOP for AASHTO T 27/T 11 | Same |
| WAQTC TM 1 | Same |
| ATM 306 | ATM T-9 |
| ATM 313 | ATM T-13 |
| WAQTC TM 4 | Same |
| WAQTC FOP for AASHTO T 308 | WAQTC FOP for AASHTO TP 53 |
| WAQTC TM 6 | Same |
| WAQTC FOP for AASHTO T 30 | Same |
| WAQTC FOP for AASHTO T 209 | Same |
| WAQTC FOP for AASHTO T 166/T 275 | Same |
| WAQTC TM 8 | Same |
| ATM 412 | None |
| ATM 414 | ATM T-14 |
| ATM 417 | ATM T-17 |
| WAQTC TM 2 | Same |
| WAQTC FOP for AASHTO T 309 | WAQTC TM 10 |
| WAQTC FOP for AASHTO T 119 | Same |
| WAQTC FOP for AASHTO T 121 | Same |
| WAQTC FOP for AASHTO T 152 | Same |
| WAQTC FOP for AASHTO T 23 | Same |
| ATM 520 | ATM T-30 |

(09/04/02)B01

Section 107
Legal Relations and Responsibility to Public

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

A Municipality of Anchorage (MOA) Right-of-Way Use permit will be required.  The Municipality will require a copy of the approved Traffic Control Plan and a copy of the Notice to Proceed from you.

Nighttime construction activities will require a Municipality of Anchorage noise permit which you must obtain.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES. Change the first sentence to the following: When your operation encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, such as shell heaps, land or sea mammal bones or tusks, or other items of historical significance, cease operations immediately and notify the Engineer.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

(05/29/02)R7M98

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. Delete this Subsection in its entirety and substitute the following:   The Contractor shall indemnify, hold harmless and defend the State of Alaska and its agents and employees from any and all claims or actions for injuries or damages whatsoever sustained by any person or property that arise from or relate to, directly or indirectly, the Contractor's performance of the Contract, however, this provision has no effect if, but only if, the sole proximate cause of the injury or damage is the Department’s negligence. This Contract does not create a third party benefit in the public or any member of the public, nor does it authorize any person or entity not a party to this Contract to maintain a suit based on this Contract or any term or provision of the Contract, whether for personal injuries, property damage or any other claim or cause of action.

(05/06/03)R271USC02

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following after the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(10/23/02)R170USC02

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120
Training Program	Section 645
Federal EEO Bid Conditions	Form 25A-301
EEO-1 Certification	Form 25A-304
DBE Subcontractable Items	Form 25A-324
ADOT&PF Training Program Request	Form 25A-310
Training Utilization Report	Form 25A-311
Contact Report	Form 25A-321A
DBE Utilization Report	Form 25A-325C
Summary of Good Faith Effort Documentation	Form 25A-332A
Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

Section 108
Prosecution and Progress

Special Provisions

108-1.03 PROSECUTION AND PROGRESS. Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule.  and substitute the following:

1.  	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order in which the work will be carried out and the contemplated dates on which the Contractor and subcontractors will start and finish each of the salient features of the work, including any scheduled periods of shutdown.  Indicate any anticipated periods of multiple-shift work in the CPM Schedule.  If revisions to the proposed CPM Schedule are required, make them promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to your schedule, or upon request of the Engineer.

(12/13/02)R261M98

Delete Item 5 of the first paragraph and substitute the following:

5.	The submittals identified under subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 3rd paragraph under item 2 “Suspension and Extension of Contract Time,” and substitute the following:

Contract time shall continue through the suspension of work in the following conditions:

●	those instances where the Engineer orders suspension of the work for unsafe conditions,

●	for failure by the Contractor to carry out contractual provisions, or

●	for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(10/23/02)R242USC02

Section 109
Measurement and Payment

Special Provision

109-1.05 COMPENSATION FOR EXTRA WORK.

Delete the first sentence of the second paragraph of sub-item a. of item 3 and substitute the following: The regular hourly rental rate is the adjusted monthly rate for the basic equipment plus the adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the area adjustment factor specified on the adjustment maps for the Alaska - South Region.

(10/23/02)R14USC02

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

Add the following Section:

Section 120
Disadvantaged Business Enterprise (DBE) Program

Standard Modification

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

1.	Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

a.	that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

b.	whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

c.	has been certified by the Department in accordance with 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer. A DBE certified by the Department in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project; and

b.	keeps an inventory in an amount appropriate for the type of work using that product; and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

d.	fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

2.	Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

a.	Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

1)	A description of the work that each DBE will perform;

2)	The dollar amount of participation by the DBE firm;

3)	Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

4)	Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

b.	DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

c.	Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

3.	Phase III - Construction.

a.	Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

b.	DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

c.	DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

1)	The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

2)	If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

d.	DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

1.	Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

a.	Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

b.	If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

c.	Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

d.	Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

e.	Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

f.	Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

g.	Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

h.	Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

i.	Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

a.	The decision on reconsideration will be made by the DBE Liaison Officer.

b.	The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

c.	The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

d.	The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

1.	Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

a.	regular dealer;
b.	manufacturer;
c.	broker; 
d.	subcontractor; 
e.	joint-venture; or
f.	prime contractor.

2.	Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

a.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

b.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

c.	The DBE is certified in the appropriate category at the time of

1)	the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

2)	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

d.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

e.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

f.	The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

1)	The work performed will be necessary and useful work required for the execution of the Contract.

2)	The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

3)	The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

4)	The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

5)	The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

6)	All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

7)	The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

g.	On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

3.	Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

a.	withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

b.	continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

1)	increasing the participation of other DBEs on the project;

2)	documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

3)	by a combination of the above.

4.	DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

2.	The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

3.	It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.

(11/17/00)S33

Section 202
Removal of Structures and Obstructions

Special Provisions

202-1.01 DESCRIPTION. Add the following: This work shall also include relocation of existing cluster mailboxes on concrete pads foundations, as shown on the Plans.

202-2.01 MATERIALS. Add the following after “Item 4. Reflectors”:

5.	Concrete. Class A as described in Section 501.

6.	Reinforcing Steel. Section 503.

7.	Grout. Subsection 705-2.04

Cluster mailbox mounting bolts and template will be provided by the USPS.

202-3.01 GENERAL. Add the following: The construction of mail box installations shall use new posts and mail boxes. Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 21 inches, minimum width of 8 inches and minimum height of 11 inches. Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground.

(4/18/00)R74USC

202-3.02 MAILBOXES. Add the following: Remove existing mailboxes and associated concrete foundations.  If  mailboxes cannot be immediately replaced at the new location Contractor shall provide mailboxes at an approved temporary location.

Contractor shall coordinate temporary location of mailboxes with the United States Postal Service Lake Otis Station.  Contact Deiter Jackson at 563-9578 at least 72 hours prior to removal and replacement of existing mailboxes.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 6 inches.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84USC

Add the following Subsection:

202-3.06 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the Department of Transportation Maintenance Yard located in Anchorage.  All remaining items removed become the property of the Contractor.

(8/30/00)R258M98

202-5.01 BASIS OF PAYMENT. Add the following after the third paragraph:

Item 202(11) Multiple Mailbox Installation.  Payment is full compensation for removal of existing mailboxes, posts and concrete foundation, concrete disposal, temporary mailbox installation, and installation of new concrete pad foundation, reinforcing steel, metal post support and all mounting hardware and installation of relocated mailboxes.

Section 203
Excavation and Embankment

Special Provisions

203-1.01 DESCRIPTION. Add the following: Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.

(2/26/03)R20USC02

203-3.02 EMBANKMENT CONSTRUCTION. On page 63, delete the first sentence of the  tenth paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding  8 inches in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by  1 foot and transversely by 10 feet.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.

The surface of Selected Material, Type D, shall be compacted by coverage of the Contractor's placement equipment to provide a smooth and firm slope. The surface of Selected Material, Type D shall be free of surface irregularities, rutting, slope breaks or unconsolidated material.

(11/05/02)R23USC02

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL. Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP FOR AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the No. 200 sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the No. 4 sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus No. 4 material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the ¾ inch sieve with the plus ¾ inch material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5.

(11/05/02)R193USC02

203-4.01 METHOD OF MEASUREMENT. Delete item 8 and replace with the following:

8.	Item 203(17).  Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the station along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT. Add the following: Payment for ditch linear grading will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

Delete item 203(17), Rockfall Mitigation – Wire Mesh.

Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 203(17) Ditch Linear Grading | Station |

(02/26/03)R20USC02

Section 301
Aggregate Base Course

Special Provisions

301-2.01 MATERIALS. Add the following after the first sentence: If no gradation type is specified in the bid schedule the base course material gradation shall conform to the requirements for Grading D-1.

(11/05/02)R116USC02

Add the following after the first sentence: At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(11/05/02)R176USC02

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.

(9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test s trip using a vibratory compactor with a minimum dynamic force of 40,000 pounds. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to  80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(11/05/02)R176USC02

Section 401
Asphalt Concrete Pavement

Special Provisions

401-2.01  COMPOSITION OF MIXTURE - JOB MIX DESIGN.  Add the following to the third paragraph on page  84: Tolerances will not be applied to the largest sieve specified.

401-2.03  ASPHALT CEMENT. Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

1.	Manufacturers certificate of compliance, Subsection 106-1.05

2.	Conformance test results of the batch, Section 702.

3.	Manufacturer shall also certify:

a.	Date and Time of loading

b.	Batch number and storage tank

c.	Type, grade, temperature, and quantity of materials loaded

d.	Type and percent of anti-strip added.

401-3.13 COMPACTION.  Delete the third paragraph and substitute the following:  Acceptance testing for density will be determined by WAQTC FOP for AASHTO T 166/T 275 except that a 6 inch diameter core is required.  (Acceptance testing for density of leveling course or temporary pavement will not be required.)

401-3.14  JOINTS. Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

Delete the last paragraph.

401-3.15  SURFACE TOLERANCE.  Add the following: The Engineer will measure the smoothness of the asphalt concrete pavement in all driving lanes with a California-type profilograph within 15 days after mainline paving is completed and all defects are corrected.  No measurements will be taken in turn lanes, lane transitions, or within  25 feet of bridge abutments or matches with an existing pavement.  The profilograph results (PrI) will be reduced and a price adjustment calculated in accordance with Subsection 401-5.01.  Furnish required traffic control devices or flagging in accordance with Section 643.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  METHOD OF MEASUREMENT.  Add the following paragraph to this Subsection: Longitudinal joints.  By the linear foot.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02  ACCEPTANCE SAMPLING AND TESTING.  Delete item 1. Asphalt Cement Content. and replace with the following:

1.	Asphalt Cement Content.  Samples taken for the determination of asphalt cement content will be taken at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Delete subitems a. and b. of item 2. Aggregate Gradation. and replace with the following:

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

b.	Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined in accordance with  WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Delete item 3. Density. and substitute the following:

3.	Density.  Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One 6 inch diameter core is required for acceptance density testing only.  Acceptance density testing will be in accordance with WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 1,000 tons.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0 percent and minus 1 percent.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph: No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per yard.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-4 and applied under Item 401(6), Asphalt Price Adjustment.

TABLE 401-4

| Average Profile Index (PrI) ( Inches per Lane Mile) | Adjustment to Item 401(6), Asphalt Price Adjustment, for Pavement Smoothness |
| --- | --- |
| 0 to 3.9 | Add $ 5,000 multiplied by ( 4.0PrI) |
| 4.0 to 6.0 | No Adjustment |
| 6.1 and greater | Deduct $ 5,000 multiplied by (PrI 6.0) but not to exceed $10,000 |

(4/7/03)R199USC02

Add the following Section:

Section 511
Modular Block Retaining Wall

Special Provisions

511-1.01 DESCRIPTION. The modular block retaining walls shall be constructed at the locations shown on the plans and as provided in these specifications.  The modular block retaining walls to be constructed shall consist of a precast modular masonry product specifically engineered for the retention of earth.  The modular units shall lock together vertically by pins.  The pins shall also be connected to geogrid reinforcement where indicated in the Plans or working drawings.

This Work shall also include furnishing all materials and labor necessary to provide shoring to limit retaining wall installation activities to within the available ROW. The shoring may include, but is not limited to, sheet piles, soldier piles and H piles.  It includes cantilevered and anchored systems.

511-1.02 SUBMITTALS.  The Contractor shall submit for approval a design for the modular block retaining wall and any necessary shoring.  The submittal shall include complete working drawings and calculations in accordance with the provisions in Subsection 105-1.02 of the Standard Specifications.  Said working drawings shall contain all information required for the proper construction of the systems and any required revisions or additions to drainage or other facilities.  Said working drawings and calculations shall demonstrate the internal stability as well as the external stability of the retaining wall and shall be signed and sealed by an Engineer who is registered as a Civil Engineer in the State of Alaska.  The Contractor shall allow the Engineer 3 weeks to review the working drawings and calculations.

Heights and lengths of modular block retaining wall systems may vary somewhat from the Plans. The Contractor shall verify the existing ground elevations and conditions at the site before preparing the final working drawings.

511-1.03 REFERENCE STANDARDS. The design of the modular block retaining walls shall be in accordance with the guidelines contained in the latest edition of the American Association of State Highway and Transportation Officials (AASHTO), Standard Specifications for Highway Bridges and the manufacturer's design recommendations.  The height and length to be used for any system shall be the minimum for the system that will effectively retain the earth behind the structure for the loading conditions, profile, or slope lines shown on the plans or on the approved working drawings.  In addition, if the Plans show limiting parameters for the systems, the system selected shall conform to those parameters.

511-2.01 MATERIALS. The Contractor shall furnish all shoring materials necessary including sheet piles, soldier piles, H piles and anchors.  The materials shall be as required by the working drawings submitted to the Engineer.

The Contractor shall make his own arrangements to purchase and/or manufacture the pre-cast modular block units, attachment devices, and all other necessary components as shown on the Plans.  Materials not conforming to the Plans or specifications, shall not be used without written consent from the Engineer.

1.	Modular Block Units. The units shall be precast in conformance with the manufacturer's requirements and the following additions:

a.	General: Precast masonry block units with a sculptured rock face in angular tri-planer configuration.

b.	Handling, Storage and Shipping: All units shall be handled, stored, and shipped in such a manner as to protect them from chipping, discoloration, cracks, and fractures.

c.	Color: Block color shall be buff. Contractor shall submit samples of colors for approval by the Engineer.

d.	Rejection: Units shall be rejected because of failure to meet any of the requirements specified above.  In addition, any of the following defects shall be sufficient cause for rejection.

1)	Defects caused by faulty casting.

2)	Defects indicating honeycombed or open texture concrete.

3)	Cracked or severely chipped units.

4)	Unreasonable color variation on front face of unit.

2.	Geotextile and Attachment Devices. All geotextile shall be as required by the manufacturer of the modular block system.  The geotextile shall be carefully inspected to insure that it is true to size and free from defects that may impair strength and durability. Pins or other devices used to attach the geotextile to the modular blocks shall be as recommended by the manufacturer of the modular block system.

3.	Reinforced Backfill Material. All reinforced backfill materials shall be free of debris or organic material and shall meet the following gradation:

Sieve Size	% Passing

2 inch	100

3/4"	75-100

No. 40	0-60

No. 200	0-10

4.	Core Fill Material. All core fill material shall be clean 1" minus crushed stone or crushed gravel and shall meet the following gradation:

Sieve Size	% Passing

1 inch	100

3/4"	75-100

No. 4	0-10

No. 50	0-5

CONSTRUCTION REQUIREMENTS

511-3.01 EXCAVATION AND FOUNDATION.   Construction of the shoring shall be in conformance with the working drawings submitted to the Engineer.  The shoring shall allow the work to stay within the available ROW.  The Contractor shall avoid conflicts and maintain minimum clearances from existing utilities, especially the adjacent overhead electric and telephone facility.  Special shoring may be necessary near the existing utility pole located just outside the ROW limits near Station 112+60.

Construction of the modular block retaining wall system shall conform to the details shown on the plans and shall be constructed in accordance with the manufacturer’s instructions.  The supplier shall provide technical assistance and training to the Contractor.  The Contractor shall provide evidence of prior installation experience with the specific product being used.

Excavation and preparation of the foundation shall be in conformance with Section 205, Excavation, Backfill and Foundation Fill for Structures.  The foundation for the modular block retaining wall structure shall be graded level for a width as shown on the Plans or shop drawings.  Prior to wall erection, the foundation backfill shall be compacted to meet the requirements of Section 301.  Any foundation soils found to be unsuitable shall be removed and replaced with backfill as per Section 205.

511-3.02 WALL ERECTION. A field representative from the proprietary modular block wall system being used shall be available during the erection of the wall.  The Services of the representative shall be at no additional cost to the Department.

Block units shall be placed so that their final position is battered at least 1H to 8V. An increased batter, up to 1.6:8, will be allowed by sloping the foundation toward the embankment to increase gravity wall overturning stability. The masonry block units shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds.  While placing backfill material behind the first course of masonry block units, place backfill material at the front of the units. Remove all excess backfill material from the top surface of all masonry block units prior to placement of the next course of masonry block units.

Backfill Placement. Backfill placement shall closely follow erection of each course of masonry blocks.  Backfill shall be placed in such a manner as to avoid any damage or disturbances of the wall materials or misalignment of the facing panels.  Any wall materials which become damaged during backfill placement shall be removed and replaced at the Contractor's expense.  Any misalignment or distortion of the masonry block units due to placement of backfill outside the limits of this specification shall be corrected by the Contractor.

Backfill shall be compacted to 95 percent of the maximum density as determined by Alaska Test Method T-12 or AASHTO T 180.  The maximum lift thickness after compaction shall not exceed 8 inches.  The Contractor shall decrease this lift thickness, if necessary to obtain the specified density.  Field density will be determined using Alaska Test Method T-3 or T-11 by the Engineer.  Ride-on mechanical compaction equipment shall be operated no closer than 3 feet from the masonry unit back face.  Compaction within 3 feet of the back face of the wall facing may be achieved by using a lightweight mechanical tamper, roller or vibratory system.  A minimum of one density test shall be taken by the Engineer after every three levels of blocks are placed.

At the end of each day's operation, the Contractor shall slope the last level of backfill away from the wall to rapidly direct water runoff away from the wall face.  In addition, the Contractor shall not allow surface runoff from adjacent areas to enter the wall construction site.

A layer of 4-inch tall solid cap stones shall be placed at the top of the retaining wall.  The cap stones shall be attached securely to the top layer of modular blocks with an adhesive as recommended by the retaining wall manufacturer.

511-4.01 METHOD OF MEASUREMENT. Modular block retaining walls will be measured by the square foot of wall face measured along the face of the wall, and including that part of wall which is below grade as indicated on the Plans or working drawings.  Measurement shall be by vertical face, not parallel to batter angle.

511-5.01 BASIS OF PAYMENT. The contract price paid per square foot of wall face for modular block retaining walls shall include full compensation for furnishing all labor, materials, tools, equipment, and incidentals and for doing all work involved in constructing the earth retaining structure; including excavation, shoring, precast masonry blocks, reinforced backfill material, core fill material, geotextile, aggregate base course leveling pad, and all parts of or appurtenances to the modular block earth reinforcement system, complete in place, as shown on the Plans and working drawings, as provided in the Standard Specifications, Standard Modifications and these Special Provisions, and as directed by the Engineer.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 511(3) Modular Block Retaining Wall | Square Foot |

Section 603
Culverts and Storm Drains

Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts and end section trash guards.

603 2.01 MATERIALS.  Delete the second paragraph and substitute the following:

When Item 603(17), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP), Corrugated Aluminum Pipe or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following: Culvert marker posts shall meet the requirements of Subsection 730-2.05 Flexible Delineator Posts. The color shall be blue with no other markings. The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of a minimum bending radius of 9 inches.

Trash guard shall be constructed of #8 rebar spaced 6 inches on center in a grid pattern, spot welded at each cross joint.  The trash guard shall be hot dip galvanized after fabrication.

603-3.01 GENERAL. Add the following:

The trash guard shall lay on the sloped face of the end section and overlap all portions of the end section opening by a minimum of 6”.   Rebar extending toward the top and the bottom of the end section shall be driven vertically into the soil a minimum of 12 inches.

The Contractor shall submit drawings to the Engineer outlining the proposed trash guard construction plans at least ten days prior to construction and installation.

Add the following Subsection:

603 3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two (42) inches of post shall remain above the ground after driving.

603 4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment. End section trash guards will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items. End section trash guards will not be paid for separately but will be subsidiary to Item 603(20) End Section. (6/24/03)R42 USC

Section 604
Manholes and Inlets

Special Provisions

604-2.01 MATERIALS. Add the following: Grates for curb inlet catch basins shall have “vaned” slots , be certified as bicycle-safe by the manufacturer, and meet the requirements of the applicable standard drawing.

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch of concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

8.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the local DOT maintenance station.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 2 inches larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-4.01 METHOD OF MEASUREMENT. Add the following: Frames, grates and lids will not be measured for payment.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure.

(11/05/02)R43USC02

Delete Item 604(1) Storm Sewer Manhole and add the following new pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 604(1A)Storm Drain Manhole, Type I | Each |

Section 606
Guardrail

Special Provisions

606-2.01 MATERIALS. Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 72 inches. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 20 in2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:		FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

Add the following Subsections:

606 3.09 FLEXIBLE MARKERS. For each extruder terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606 3.10 LENGTH OF NEED VERIFICATION. After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The staked location of the guardrail will be approved by the Engineer prior to installation. The Engineer may determine that additional guardrail is necessary, and you shall comply without delay.

(05/29/02)R45aUSC

Section 608
Sidewalks

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work also consists of constructing asphalt pathway(s) and recycled asphalt material trail(s) in conformance with the Plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG52-28	Subsection 702-2.01
Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, pounds, min.	1000
Percent Voids, Total Mix	2-5
Compaction, Blows/side	50

Add the following:  Materials for Recycled Asphalt Material to be used for trail construction, as indicated on the Plans, shall be in accordance with Special Provisions Subsection 301-2.01, Materials.

608-3.03 CURB RAMPS. Delete the second sentence of this Subsection.

Add the following Subsections:

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with Subsection 608-3.02, Asphalt Sidewalks.

608-4.01 METHOD OF MEASUREMENT. Delete the Curb Ramp item and substitute the following:

Curb Ramp.  By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles and landings necessary to provide a single street-level access.

Add the following:

Asphalt Pathway. Will be measured by the ton in accordance with Section 109, Measurement and Payment.  Asphalt cement and anti-stripping additive will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Add the following:

Backing curb will be subsidiary to Item 608(6), Curb Ramp.

The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp.

(06/11/02)R256USC

Add the following: Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to their respective pay items.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

(2/1/00)R47USC

| Pay Item | Pay Unit |
| --- | --- |
| 608(7) Asphalt Pathway | Ton |

Section 609
Curbing

Special Provisions

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph:  Concrete placed by the extrusion or slip-form process shall have a slump of less than 2 inches.

(2/1/00)R202USC

Section 615
Standard Signs

Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit shop drawings for all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete the sixth sentence of the first paragraph of item 7 and substitute the following:

Deliver sign panels, posts and hardware to the State Maintenance Yard located in Anchorage.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(11/16/02)R50USC02

Section 618
Seeding

Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

Slopes 2:1 or steeper shall be hydromatted with a bonded fiber matrix (BFM) material that acts as a biodegradable, high strength, porous, and erosion resistant mat.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch			Subsection 727-2.01

Add the following:

Bonded fiber matrix shall be comprised of long strand wood fibers held together by a bonding agent which upon drying becomes insoluble and non-dispersible.  BFM shall be EcoAegis® manufactured by Canfor Panel and Fibre Division, 430 Canfor Ave, New Westminster, BC, Canada V3L 5G2, Tel: 1-800-363-8873; Fax: 604-521-3179; or approved equal.  The Contractor shall submit in writing the mulch to be used, ten days prior to its use.

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per acre. Apply seed and mulch in one application if using the hydraulic method.

For slopes 2:1 or steeper, the hydraulic application of seed and mulch shall consist of furnishing and placing a slurry made of seed, fertilizer, bonded fiber matrix, and water.  The mixture shall be prepared as a slurry and applied according to manufacturer’s specifications, using standard hydraulic planting equipment.  When using BFM, the application shall be made in advance of rainfall, so that the matrix has an opportunity to dry for up to 24 hours and adhere to the soil in the form of a continuous biodegradable erosion control blanket.

Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs |
|  | Soil Stabilizer Slope < 2:1 Slope > 2:1 | Mulch Bonded Fiber Matrix (BFM) | 46 lbs. Manufacturer’s Specifications |
|  | Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch, bonded fiber matrix, and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. Add the following: The work described under Subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(11/06/02)R52USC

Section 619
Soil Stabilization

Special Provision

619-1.01 DESCRIPTION. Add the following:

This work also consists of furnishing, placing and maintaining Cellular Slope Protection where shown on the Plans or as directed by the Engineer.

619-1.02 SUBMITTALS. Add the following:

Submit a Manufacturer’s Certificate of compliance as defined in Subsection 106-1.05, Certification of Compliance, for all materials to be placed under Item 619(6) Cellular Slope Protection.  Include the manufacturer’s installation instructions for the application shown on the Plans.

619-2.01 MATERIALS. Add the following:

1.	General. Use cellular slope protection systems pre-manufactured as an assembly of expandable connected cells constructed of high-density polyethylene (HDPE).  Use non-perforated cell walls.  Firmly anchor the slope protection as recommended by the manufacturer.

2.	Cellular Slope Protection System. Use one of the following cellular slope protection systems or an approved equivalent:

a.	“Geoweb 4” Standard Cell”, as manufactured by Presto Products Company, P.O. Box 2399 Appleton, Wisconsin, 54913, (800) 548-3424

b.	“EnviroGrid 4”, as manufactured by AGH Industries, Inc., P.O. Box 1852, Fort Worth, Texas, 76101, (817) 284-1742

c.	“GeoLok 400”, as manufactured by Fluid Systems, Inc., 1245 Corporate Boulevard, Suite 300, Aurora, Illinois, 60504, (800) 346-9107

3.	Prefabricated Slope Protection System Material: Shall meet the following requirements:

Nominal Cell Depth (min.)	4 inches

Sheet Thickness (min.)	50 mil ± 5 mil

Tensile Seam Strength (min.)	225 lbf

Standard Sheet Configuration (typ.)	8 feet x 20 feet

Individual Expanded Cell (max.)	10 inches x 8 inches

Add the following Subsection:

619-3.04 CELLULAR SLOPE PROTECTION. Construct the cellular slope protection according to the details on the approved working drawings and consistent with the manufacturer’s recommendations.

Foundation Preparation. Construct slopes to the lines and grades shown on the Plans prior to construction of the cellular slope protection.  Level or fill localized high or low spots.  Remove all obstructions such as projecting stones.  Remove soft or low-density pockets of material and backfill with selected material.

Construction Requirements. Place the cellular slope protection mats in such a manner as to produce a smooth surface and construct within the specified lines and grades shown on the Plans.  Follow the manufacturer’s recommendations for construction of the cellular slope protection system.

Stretch the mat to the standard nominal expanded dimensions and anchor it according to the manufacturer’s recommendations.  Place the mats side by side so that the mats interlock.  Join or anchor the mats according to the manufacturer’s recommendations.

Infill the cells with topsoil to a depth of 2 inches above the cell walls.  Compact the topsoil with a smooth excavator bucket or with hand equipment.

619-4.01 METHOD OF MEASUREMENT. Add the following:

Item 619(6) Cellular Slope Protection shall be measured by the square yard on the slope of the ground surface.  Payment for seeding Cellular Slope Protection topsoil infill shall be paid for under Item 618(1A) Seeding, Type A.  Payment for infilling Cellular Slope Protection with topsoil shall be paid for under Item 620(1B) Topsoil, Class B.

There will be no separate measurement for hardware and geotextile necessary for Cellular Slope Protection as it will be considered subsidiary to Item 619 (6).

619-5.01 BASIS OF PAYMENT.

Add the following Pay Item:

| Pay Item | Pay Unit |
| --- | --- |
| 619(6) Cellular Slope Protection | Square Yard |

Section 620
Topsoil

Special Provisions

620-2.01 MATERIALS. Add the following:  Topsoil shall conform to the requirements of Section 726.  Topsoil shall be Class B.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(11/06/02)R53USC02

Section 639
Approaches

Delete this Section in its entirety and substitute the following:

Special Provisions

639-1.01 DESCRIPTION. Construct public approaches and residential driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT. At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing  equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

(05/09/02)R58M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(3) Public Approach | Each |

Section 642
Construction Surveying and Monuments

Special Provisions

642-3.01 GENERAL. Add the following item after Item 10:

11.	Measure and document the actual intersection sight distance triangles at all public intersections.  List the actual sight distance available up to 600 feet.  Note locations with greater than 600 feet of sight distance as “600+”.  Measure sight distance triangles are shown in Figure 1190-1 of the Highway Preconstruction Manual by setting up an instrument at the driver’s eye location.  Certify and record the results on standard “letter” size paper and provide it to the Engineer at least 2 weeks prior to submitting shop drawings for permanent signing. Provide an additional copy to the Regional Traffic Engineer.

642-3.03 MONUMENTS. Delete the second sentence of the first paragraph and substitute the following:  Reference all property markers/corners, monuments or accessories which may be disturbed or buried during construction.  Prepare and record Monument Record Forms in the appropriate Recorder’s Office prior to disturbing monuments.  Monument Record Forms may be obtained from the Engineer.  Reestablish monuments in their original position prior to the completion of the Project.

642-5.01 BASIS OF PAYMENT. Add the following after the first paragraph: You will not receive any payment for Item 642(9), Reference Existing Monument until the Monument Record Forms are recorded in the local Recorder’s Office. (3/12/03)R269USC

(3/12/03)R269USC

Section 643
Traffic Maintenance

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: You may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum12 foot lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  You may schedule one weekend closure from Friday, 2000 hour to Sunday, 0500 hour.

Add the following to the second paragraph:  At the end of each shift, the roadbed embankment  shall be smooth and even.  You may run traffic on gravel for no more than 30 consecutive days beginning June 10, 2004.  You may maintain traffic on a continuous gravel surface for the entire length of the project.

643-3.04 TRAFFIC CONTROL DEVICES.  Delete the first sentence of the eighth paragraph and substitute the following:  All items paid under this Section remain your property unless stated otherwise.

Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: Remove all obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Between the hours of 0600 and 0830 and between the hours of 1600 and 1800, Monday through Friday.

Lane restrictions, if allowed shall be conducted so that no more than a 5 minute accumulated stopped delay, 20 vehicles, or 1/8 mile (660 feet) of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 10 minute stopped delay, 40 vehicles, or 1/4 mile (1,320 feet) of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-4.01 METHOD OF MEASUREMENT. Page 281, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $2.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Foot Foot Each Each | $0.30 $0.65 $0.75 $40.00 |

The Engineer will pay for Item 643(15), Flagging on a contingent sum basis at the rate of $36.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices agreed to in the Change Order, or on a time and materials basis in accordance with Subsection 109-1.05. (05/14/03)R222 USC02

Delete Item 643(15) and substitute the following

| Pay Item | Pay Unit |
| --- | --- |
| 643(15)Flagging | Contingent Sum |

Section 644
Services to be Furnished by the Contractor

Special Provisions

644-2.01 FIELD OFFICE. Delete this Subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four (4) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

Add the following Section:

Section 645
Training Program

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless you can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to you where the apprentices/trainees are concurrently employed on the project and you do one or more of the following: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by you, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by you.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in your judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and you employ that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  You must submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event you subcontract a portion of the work, you shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with you; compliance or non-compliance with these provisions rests with you and sanctions and/or damages, if any, shall be applied to you in accordance with Subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  You will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section prior to your submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at your discretion, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, you will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds you may receive, unless such other funding sources specifically prohibit you from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to you if you fail to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A-311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where you have failed, by the end of the project, to provide the required number of hours of training and have failed to submit acceptable good faith efforts documentation which establishes why you were unable to do so, you will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

(10/29/91)S 16

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 1 Trainee/Apprentice | Labor Hour |

Section 646
CPM Scheduling

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this Subsection in its entirety and replace with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer 14 days to review the initial CPM Schedule.  If revisions are required, make them promptly.   The finalized CPM Schedule must be completed and accepted prior to commencement of any work on the Project.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly, or as deemed necessary by the Engineer.

(12/13/02)R261M98

Add the following Section:

Section 647
Equipment Rental

Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 65 HP Minimum will be paid on a contingent sum basis at the rate of $125/hour on a per hour basis at the rate shown on the bid schedule.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation.

(11/12/98)R15USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 65 HP Minimum | Contingent Sum |

Section 660
Signals and Lighting

Special Provisions

660-2.01 MATERIALS. 1. Equipment List(s) and Drawings.  Delete item (a) that follows the first paragraph and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

2. As-Built Plans.  Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.  You will also submit two additional sets of electrical as-built plans to the Engineer.  The Engineer shall deliver one set of electrical as-built plans to MOA Signal Electronics Shop and the other set to MOA Street Light Maintenance.

660-3.01 GENERAL. 6. Salvaging or Reusing Electrical Equipment. Delete the first paragraph and replace with the following:  Salvage and deliver existing electrical equipment undamaged, including signal equipment, luminaires, lighting standards, signal poles and mast arms, service equipment, and junction box lids to the State Maintenance Yard at 5300 east Tudor Road in Anchorage, Alaska. Notify Mike Knowles, Electrician, or Jerry Reed at 338-1466 one-week before your planned delivery date.  All salvaged LED modules and controller assemblies will be delivered to the MOA Signal Electronics Warehouse at 5923 Rowan Street in Anchorage.  Contact MOA Signal Electronics Foreman at 343-8355 one week before anticipated delivery to schedule delivery.

660-3.02 FOUNDATIONS.  1.  Cast-in-Place Foundations.  In subparagraph f, revise the second sentence to read: Before you place the form or reinforcing steel cage, remove all loose material to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of subparagraph i, delete “prior to grouting” and add, ”before you attach the galvanized skirt.”

In the first sentence of subparagraphs j and k, delete “concrete pile caps” and add, ”foundations.”

Add the following new subparagraph l (lowercase L).  Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations. Slide a minimum 6-inch long, non-metallic, protective sleeve over the conductor. Allow one inch of the sleeve and 4 feet of conductor to protrude from the foundations.

2. Pile Foundations. Delete subparagraphs a. through f. and substitute the following:

Pile foundations will not be used.

660-3.03 CONDUIT. Revise subparagraph 6, to read: Install rigid metal conduit under pavements that will not be overlaid by jacking them under pavements up to 30 feet wide and under pavements greater than 30 feet wide by boring or drilling methods.

In subparagraph 8, delete “non-metallic”

Delete subparagraph 9, and add the following: 9.  Position conduit ends in junction boxes to provide clearances of at least 2-1/2 inches around all 2-inch conduits and at least 2-inches around all three inch conduits.

Add the following to subparagraph 11, Provide enough clearance between conduits, including protective sleeves, to ensure you can install grounding bushings on all conduits.

660-3.05 WIRING. Delete subparagraph 11 and add the following: Encapsulate illumination cable splices in rigid 2-piece plastic molds filled with an insulating and sealing epoxy resin. Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin. Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin. Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and which will not sustain combustion.

Delete subparagraph 12 and renumber the paragraph that follows subparagraph 11 to 12.  Also revise the first sentence of new subparagraph 12 to read: Encapsulate all loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with re-enterable polyurethane electrical insulating and sealing compound.

Add the following new subparagraph: 18.  Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

Add the following new subparagraph: 19.  Whenever you can not terminate the conductors specified in the Plans in circuit breakers due to their size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing. Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductor to 5 feet.

660 3.06 BONDING AND GROUNDING. Delete this subsection and add the following: Bond and ground all branch circuits according to the NEC and the following requirements. Make all non-current carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install threaded-type grounding bushings made of malleable iron or steel with a zinc or galvanized finish on the ends of all metallic conduits. Use bushings with an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Install a bare stranded copper wire for the equipment grounding conductor in all conduits, except those conduits you install for future use. Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG. In this case, install a conductor equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit all existing spare conduits that will contain new cables exclusively with new grounding bushings. When the Plans require you to install or remove conductors from existing conduits, retrofit them with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross-sectional area equal to an 8 AWG conductor.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace all missing or damaged conduit and junction box lid bonding jumpers.

When you install signal poles and other poles with fixed bases, attach one grounding conductor to the grounding lug located in the hand hole of each pole.  Join the other required grounding conductors together using irreversible compression type connectors.

When you install lighting standards and other poles with breakaway or slip bases, run a four feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.  With pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector. With concrete foundations, join the equipment grounding conductor from the conduits to the 4 AWG grounding electrode conductor using an irreversible compression connector.

Bond slip-base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

660-3.09 MAINTAINING TEMPORARY AND EXISTING ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of lighting systems and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If you fail to maintain the electrical systems as specified herein, the Engineer will adjust payments to you according to subsection 643-3.06, Traffic Price Adjustment.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, all components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer. If you do not complete the work, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way to less than six feet.

When no longer required, salvage all original and Department provided equipment according to the plans and item 6 Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove all other materials used in the temporary systems from the project.

Section 670
Traffic Markings

Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. 	Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in gallons or liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) gallon of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 1 lb/yd2 (580 g/m2) for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

METHYL METHACRYLATE PAVEMENT MARKING
YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 |
| --- | --- |
| ##### Longitudinal Type2 ##### (Center and Edge lines) | 90 mils (2.3 mm) |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils (3.0 mm) |
| Neutral Area (Diagonals, Chevrons) | 60 mils (1.5 mm) |

1. Measure Type V spray without glass beads.  Tolerance is ±4 mils (±0.1 mm).  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6” x 12” (150 mm x 300 mm) flat sheet of 80 mils (2 mm) thick aluminum placed in the path of the striping guns.

2. Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils (1.5 mm) per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 30 mils (0.75 mm).

Unless directed otherwise by the Engineer, apply the final 60 mils (1.5 mm) of the Longitudinal Type markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

670-3.04 PAINT REMOVAL. Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the removal requirement. Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

2.	Width of Stripe. The width shall not vary more than ¼” (6 mm) in width for any 50’ (15 m) longitudinal run from the width shown in the Plans.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Gallon Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in gallons .

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B).  No separate payment shall be made for furnishing and maintaining the MMAMS.

Payment will be made under:

| #### Pay Item | #### Pay Unit |
| --- | --- |
| 670(10B) Methyl Methacrylate Pavement Markings | Gallon |

Section 703
Aggregates

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| 3/4 inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| ## No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

(2/28/00)R117USC

Section 710
Fence and Guardrail

Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

Drawing	Original	Latest

Number	Date	Revision	Comments

ET-2000 LET	Metric	SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

(01/22/02)R249

Section 712
Miscellaneous

Special Provisions

712-2.06 FRAMES, GRATES, COVERS AND LADDER RUNGS. Add the following:

Ductile iron castings	ASTM A536 for grade 60-401.

(2/22/00)R78M98

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following Subsection:

2.	Performance Properties: Add the following:

k.      Adhesion:	To Portland Cement, minimum 2000 psi. To asphalt, dependent on tensile failure of the substrate.

(12/04/02)R246

Section 724
Seed

Special Provisions

724-2-02. MATERIALS. Delete Table 724-1 and substitute the following:

TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(11/06/02)R52USC

Section 726
Topsoil

Special Provisions

726-2.01 TOPSOIL. Delete item 2 and substitute the following:

- Contain between 10% and 40% organic matter as determined by loss-on-ignition of oven dried samples according to ATM 203.

Delete the table for grading requirements in item 3 and substitute the following:

TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 3 inch | - | 100 |
| ½ inch | 100 | - |
| No. 4 | 95-100 | 75-100 |
| No.16 | 64-90 | 50-95 |
| No. 200 | 30-60 | 20-80 |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267

(6/9/03)R139USC

Section 730
Sign Materials

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

6.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(12/04/02) R81USC

APPENDIX A

PERMITS / TEMPORARY CONSTRUCTION PERMITSAPPENDIX B

EROSION AND SEDIMENT CONTROL PLAN (ESCP)APPENDIX C

CONSTRUCTION SURVEYING REQUIREMENTSAPPENDIX D

MATERIALS CERTIFICATION LISTAPPENDIX E

SPECIAL DETAILSAPPENDIX F

UTILITY COMPANY REQUIREMENTS