PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	State of Alaska Department of Transportation and Public Facilities publication, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Actives

b.	Foundation Geology Report, Montana Creek Pedestrian Bridge, Bridge No. 1984, August 1999.

- Standard Specifications for Highway Construction (Metric) 98M (Price $25.00)

d.	Quantity Computations

2.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

3.	This is to notify all bidders that the contract award process, when the Contractor specifies a DBE Goal, will be modified as explained below.

Prior to award, the Department has been allowing a low bidder who did not submit sufficient good faith efforts (GFE) documentation to submit additional DBE participation to meet the goal stated in the bid documents then. The FHWA has informed us that this practice is not allowable. If the Contractor submits GFE documentation and the documentation is found to be insufficient, the bidder is to be declared nonresponsive.

For contract DBE requirements, refer to Section 120, DBE Program.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

4.	The United States Department of Transportation has recently issued new regulations for the DBE Program (49 CFR Part 26).  New eligibility criteria for DBE firms have been added, including consideration of Personal Net Worth (PNW) of the DBE owner(s).  This new criteria will be used to verify continued certification in the DBE Program.  Contractors are requested to continue to use the same procedure they have been using until the Department can establish the PNW.  If a DBE firm on a Project awarded after March 3, 1999 is decertified for failure to meet the PNW criteria, the Department will deal with the issue on a case by case basis.

SECTION 101

DEFINITIONS AND TERMS

101-1.03.DEFINITIONS. Add the following definition:

Standard Modifications

INTERIM WORK AUTHORIZATION. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

Special Provisions

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 75 Fm  screen as determined by sieve analysis performed on minus 75 mm  material. (01/31/98)R1M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Provisions

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change Apractical@ to Apracticable@.

SECTION 104

SCOPE OF WORK

Special Provisions

104-1.02 CHANGES. Delete the second paragraph.

SECTION 105

CONTROL OF WORK

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate call center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska-DOT/PF Anchorage M&O Alaska Fiberstar AT&T Alascom, Inc. Chugach Electric Association City of Wasilla ENSTAR Natural Gas, Inc. Eyecom TV/Interior Telephone GCI Communications Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association MFS Technologies, Inc. Mukluk Telephone Association PTI Communications, Inc. Phillips Petroleum Rogers Cable Systems of AK, Inc. TelAlaska, Inc. Tesoro / KPL Unocal Oil & Gas

Before the Contractor installs new utilities all existing utilities shall remain in service.

Various utility appurtenances are located within the project limits. The Contractor shall cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor will work around all utility facilities, either existing or relocated, throughout the project. The exceptions are utility facilities that the utility company will abandon.

Do not relocation or adjustment of underground utility appurtenances when the ground is frozen. Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

If scheduling changes occur, the Contractor is still responsible for all conditions of this Contract. This may require additional coordination with the applicable utility.

The Utility may require construction staking before relocation of the utility's facilities.  The Contractor shall give the utility 14 days advance notice when the staking will be available and maintain the stakes until the utility relocation is completed.

Payment for this staking will be as follows:

1.	If, as part of the contract, the Contractor will provide staking in the area needed by the utility, this work will be subsidiary to Item 642(1), Construction Surveying.

2.	If the utility has required construction staking or right-of-way staking in advance of the Contractor's normal schedule, the utility will request the staking, through the Engineer, 14 days prior to the time of the required utility staking. The Department  will pay utility required staking under Item 642(3), Three Person Survey Party.

3.	If the utility requires right-of-way staking, and staking the right-of-way is not a part of the contract, the utility will request the staking, through the Engineer, 14 days prior to the time the Utility requires the staking for the utility to start their relocation. The Department will pay this staking under Item 642(3), Three Person Survey Party.  (8/13/98)R398

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following: The Department shall commence legal actions through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage. (8/5/93)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: Buy America Provision.   The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products that are incorporated into the work shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States: means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy costing, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, palletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-Aid Highway Program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for eac covered product comply with this provision.  Non-conforming products shall be replace at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (8/31/99) S13

The Contractor shall furnish the Engineer acceptable documentation of the quantity and value of any foreign steel and iron prior to incorporating the materials into the work. (6/11/99)S1398M

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: YEAR 2000 WARRANTY: The Contractor warrants that all hardware, software, or firmware product or item delivered or developed under this contract shall accurately process date data (including, but not limited to calculating, comparing, and

sequencing) from, into, during, and between the twentieth and twenty-first century, including leap year calculations, when used in accordance with the documentation provided by the Contractor.

If the contract requires that specific products or items perform as a system, then this Year 2000 Warranty shall also apply to those listed items as a system.

The duration and remedies available to the State for breach of the Year 2000 Warranty shall be as defined in, and subject to, the year 2000 terms and limitations of any general warranty provisions contained in this solicitation. In the absence of any such general warranty provision(s), the remedies available to the State shall include repair or replacement, without any cost to the State, of any noncompliant listed product or item discovered and made known to the Contractor in writing by April 1, 2000 or within one (1) year after acceptance, or within the time limits of the Contractor’s warranty, whichever is longer.

The Contractor shall construe nothing in this Year 2000 Warranty to limit any rights or remedies the State may otherwise have under the Uniform Commercial Code, State or Federal law, or with respect to defects other than Year 2000 performance.

The warranties contained herein are separate and distinct from any other warranties expressed or implied and are not subject to any disclaimer of warranty or limitation of the supplier’s liability.

(3/4/98)S79

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following:

The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If  the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, that will be impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that the Contractor has obtained all necessary permits or clearances. The Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that required no additional action from the Contractor.

Add the following: The following permits have been received on the Contractor’s behalf:

1.	Special Flood Hazard Area - Development Permit, FHDP 9912

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Add the following: Should archaeological, historical, or paleontological resources be discovered during construction, all work which would disturb such resources shall be stopped immediately and the State Historic Preservation Officer contacted at (907) 2169-8715.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following to the sixth paragraph: When working near designated wetlands the Contractor shall place no fill, nor operate equipment outside the slope limits. Refueling and servicing of equipment shall not be performed within 30 meters of wetlands.

Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (7/8/98)R7M

The Contractor shall do no work, stockpiling, staging, parking nor trespassing in or around any watercourses except for that work permitted by the contract.

Standard Modifications

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries". (5/12/89)M9

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES. Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services. (2/7/96)R170M

Add the following subsection:

107-1.22 FEDERAL AFFIRMATIVE ACTION. Requirements applicable to this Contract for the Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements are in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program		Section 120

Training Program						Section 645

Federal EEO Bid Conditions					Form 25A301

EEO-1 Certification						Form 25A304

DBE Subcontractable Items					Form 25A324

ADOT&PF Training Program Request			Form 25A310

Training Utilization Report					Form 25A311

Contact Report						Form 25A321A

DBE Utilization Report					Form 25A325C

Summary of Good Faith Effort Documentation		Form 25A332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, a noncompliance with these requirements is a ground for withholding of progress payments.

In addition to the reports required in the above references, the Contractor shall submit a copy of Form CC-257 to the Department by the 15th of each month of the current construction season.  The form shall reflect the composition of the previous month’s workforce. If requested, the Contractor must also make this information available to the US Department of Labor, Office of Federal Contract Compliance Programs.

(8/13/98)S80

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.03  SCOPE OF PAYMENT.  Delete the last sentence of the fourth paragraph. (05/07/91) M 33

Special Provisions

109-1.04 COMPENSATION FOR ALTERED QUANTITIES. Add the following:  The definition of quantity for items 608(9) Pathway and 514(1) Pedestrian Bridge is the quantity shown in the respective plan sheet schedule of quantities.  The Engineer may adjust the contract quantity for authorized changes that affect those quantities or for errors made in computing those quantities. The Contractor shall request, in writing, that the Engineer adjust the quantity if there is evidence that a quantity specified as a contract quantity is incorrect. The Contractor shall submit such evidence including  calculations, drawings, or other evidence indicating why the quantity is in error.

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1.Labor, delete paragraph f., and substitute the following:

f.	plus 35% of the sum of a, c, d, and e.

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a sub-subcontractor.  (6/25/99) M71

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by K-III Directory Corp., 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (3/24/97)R14

109-1.06 PROGRESS PAYMENTS. Add the following: After the Contractor has received the Notice to Proceed, the Contractor will submit a Schedule of Values, an estimate of unit price corresponding to the quantities shown on the plans  under the Schedule of Quantities.  The Contractor shall submit the Schedule of Values prior to the Preconstruction Meeting.  The Engineer will use the Schedule of Values to determine progress payments during construction.

Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. Upon receipt of current schedules, from the Contractor, the Engineer will release this retainage. (9/21/92)R137

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract. The Contractor shall carry out applicable requirements of 49 CFR part 26 in the award and administration of DOT-assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section shall be considered a material breach of the contract. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04 DEFINITIONS AND TERMS

1.	Broker. A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. Before the Contractor will receive a credit, a broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications.

2.	Commercially Useful Function (CUF). The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with its own equipment and employees within its certified category. The Engineer shall determine the CUF after evaluating the way in which the Contractor performed the work during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE). A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts. The affirmative action measures taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer. A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal. The percent of work that certified DBE=s performs that the Department establishes and specifies in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer. A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver

the product to the general public or construction industry at large. If the DBE rents or leased the distribution equipment, it must be on a repetitive, seasonal basis.

- Revised DBE Utilization Goal. The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C. The Revised DBE Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved. Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01 UTILIZATION GOAL. The Bid Schedule shows the Original DBE Utilization Goal for this as a percentage of the total basic bid amount. In order to get credit toward meeting the Original DBE Utilization Goal for the work of the DBE at time of contract award, the Department must certify the DBE in a category covering the CUF performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid and Award. In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs used to meet the goal.

b.	If the Original DBE Utilization is greater than the DBE utilization submitted by the contractor on Form 25A325C, the Contractor shall submit documentation of Good Faith Effort in the form of the Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and the DBE Contact Reports (25A321A). If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

- Phase II - Construction. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The Contractor shall include the CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) in any subcontract, purchase order or service agreement with that DBE. The Contractor shall submit a written request to obtain prior  approval from the Engineer for the replacement of a DBE for any reason. If the Engineer approves DBE replacement, the Contractor is obligated to replace the DBE with another DBE for the same work in order still to meet the Revised DBE Utilization Goal. If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work performed by the replacing the DBE, reducing the Revised DBE Utilization Goal.

120-3.02 GOOD FAITH EFFORT. The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract. Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The Contractor shall, at a minimum,  seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

- The Contractor has selected the most appropriate items or portions of the item that the DBEs will perform, in order to increase the likelihood of achieving the stated goal.

- The Contractor has notified at least 10 calendar days prior to bid opening all the DBEs listed in the Department’s most current DBE Directory certified to perform those work items identified in Form 25A324 of the

- bidder's/Contractor's interest in securing the DBE's participation in the execution of the work. The Contractor shall log each contact with the DBE on a "Contact Report" (Form 25A321A).

- Requests for DBE participation on specific items of work or services. The Contractor must document allegations of noncompetitive DBE quotes and verifiable. The Contractor shall deem a DBE quote that is more than 10.0% higher than the accepted non-DBE quote noncompetitive, provided the DBE and non-DBE quotes are for the exact same work or service. Where the Contractor rejects a DBE quote as being noncompetitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

- Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding. The Contractor shall log documentation of follow-up contacts on the "Contact Report" (Form 25A321A).

The Department will utilize items 4. through 7. to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF). Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

- regular dealer,

- manufacturer,

- broker,

- subcontractor

- joint-venture, or

- prime contractor.

In order to obtain credit for the CUF work of the DBE toward the goal, the Contractor shall ensure that the DBE meets all of the following requirements:

- The DBE shall have certification in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b.	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Engineer will evaluate the CUF performed by a DBE certified in a supply category to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- The Department restricts a DBE trucking firm certified and performing work in a transportation/hauling category within that category to the CUF of a broker. (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation that could include the hauling of materials for that work.)

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work, or supply of goods or services, regarding CUF and potential DBE credit.

- Should a DBE performing a CUF become decertified, during the term of the subcontract, purchase order, or service agreement for reasons beyond the

- control of and without the fault or negligence of the Contractor, the Contractor may credit the work remaining under the subcontract, purchase order, or service agreement toward the Revised DBE Utilization Goal.

- Should the Department decertify the DBE between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the Contractor shall not credit the work of the decertified firm toward the Revised DBE Utilization Goal. The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01), or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

- The DBE may perform work in categories for which the Department does  not certify it, but the Contractor will only receive credit for the Revised DBE Utilization Goal toward work performed in the DBE's certified category meeting the CUF criteria.

8.	The Engineer shall consider the following criteria when determining what CUF is the DBE is performing:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The Contractor shall perform the work, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below. Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site. All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work. The Department may permit an exception to this requirement where the DBE must perform a specialty task or where the work is in a remote area. In such instances, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the work.  If the Department considers, this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value. Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved. Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control.  The Contractor must document DBE leases and payments for equipment; Contractor withholding or retainage for DBE labor and equipment usage is not permissible. Two-party checks to individuals are not permissible.

e.	The manner in which the Contractor sublets or performs the work shall conform to standard, statewide industry practice within Alaska, as defined by the Department. The work or provision of goods or services shall have a market outside of the DBE program (non-DBE firms must perform the work within the Alaskan construction industry). Otherwise, the Department will deem the work or service a superfluous step in the contracting or purchasing process and the Department will not allow any DBE credit.

No DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal.  Only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications will this be creditable.

g.	Unless the Engineer gives written approval, all subcontract work, with the exception of truck hauling, the Contractor shall sublet by the same unit of measure as shown in the Bid Schedule.

h.	The DBE shall control all business administration, accounting, billing, and payment transactions (this requirement does not preclude the two-party check allowance described under I., below). The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

i.	The Department will not allow credit for payments made by the Contractor to others on behalf of the DBE.

The Contractor may issue two-party checks on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Contractor shall notify the Engineer in writing in advance. The Department will not give DBE credit for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before the Department may credit any DBE credit. The DBE must regularly employ and designate the DBE supervisor as a key employee in the DBE's certification records with the Department prior to a prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identifies payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the Department reduces the quantity of work of a bid item, which involves a DBE, likewise the Department will proportionately reduce the Original and Revised DBE Utilization Goals on Form 25A325C.

120-3.04 DEFAULT OF DBE. In the event that a DBE who has been placed under contract, or to whom the DBE has issued a purchase order, or similar agreement, defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default. The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the

event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, the Contractor has met both of the following criteria:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Department will adjust the Revised DBE Utilization Goal to reflect only that amount of the defaulted DBE's work that the Contractor cannot replace.

120-4.01 METHOD OF MEASUREMENT. The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credits for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credits for the CUF of a subcontractor are 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credits for the CUF of a manufacturer are 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credits for the CUF of a regular dealer of a creditable material, product, or supply are 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credits for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credits for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the premium cost.

8.	Credits for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

Retainage may be withheld from progress payments if the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled. Also retainage may be withheld  if the Contractor fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF. The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, the Engineer will reduce payments as a disincentive. The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after meeting the Original DBE Utilization Goal established on Form 25A325C in terms of dollars, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUF work performed by DBE subcontractors not needed in the calculation to meet the Original DBE

Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

The final estimate will include the payment for the incentive. The disincentive will be withheld in the form of retainage during the course of the project. If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit the same to the Department within 30 days of being billed for the amount due.

The Department does not require a Change Order for DBE Adjustment. The Notice to Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

(6/6/94)S33

SECTION 201

CLEARING AND GRUBBING

Special Provisions

202-3.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

202-4.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

203-3.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 301

AGGREGATE BASE COURSE

Special Provisions

301-2.01 MATERIALS. Replace this subsection with the following: The gradation of base course material shall conform to the requirements of Grading D-1.

301-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

301-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

CONSTRUCTION REQUIREMENTS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.3

401-2.03  Asphalt Materials.  Add the following: Use AC-5 asphalt cement in the construction of the pathway.  Use PG 52-28 asphalt to replace the roadway pavement removed in the construction of the undercrossings.

CONSTRUCTION REQUIREMENTS

401-3.09 PREPARATION OF AGGREGATES. In the first paragraph, delete AASHTO T-110 and substitute the following: ATM T-25.

401-3.11 TEMPORARY STORAGE. Add the following: Rejected asphalt concrete mixture shall be disposed of by the Contractor at no cost to the State.

401-3.14 JOINTS. Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one minimum diameter 150 mm core centered on the longitudinal joint at each location the Contractor cores the mat for acceptance density testing in the panel completing the joint.  Determine density in accordance with ATM T-18.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: The Contractor shall bear all costs associated with the patching of defective areas.

401-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: The Contractor will take samples for the determination of asphalt cement content from the windrow, at the end of the auger, or from two minimum diameter 200 mm core samples cut from each sublot.  Determine asphalt cement content in accordance with ATM T-23, or AASHTO TP 53, however determine the moisture content in accordance with ATM T-25.

Samples taken for the determination of aggregate gradations from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  Determine the aggregate gradation for samples from the conveyor system in accordance with ATM T-7.  For asphalt concrete mixture samples, or cores, determine the gradation in accordance with AASHTO T 30 from the aggregate remaining after the ignition oven (AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradations from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates.  Determine the dry batched aggregate gradation in accordance with ATM T-7.  For asphalt concrete mixture samples, or cores, determine the gradation in accordance with AASHTO T 30 from aggregate remaining after the ignition oven (AASHTO TP 53) has burned off the asphalt cement.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 501

STRUCTURAL CONCRETE

Special Provisions

501-3.07 PLACING CONCRETE. Replace Number Item 15. with the following:

15.	Bridge Decks on Permanent Metal Forms.  Place concrete in accordance with the contract specifications.  Provide special emphasis on the proper vibrations of the concrete to avoid honeycombs and voids especially at construction joints, expansion joints, valleys, and the ends of formed sheets.  Submit the concrete placing procedure for the Engineer’s approval.

The Engineer will carefully observe the concrete placing method during all phases of bridge deck construction.  The Engineer will test the deck for soundness and proper bonds to the forms.  If the Engineer identifies unsatisfactory concrete, the Contractor will repair all areas at no additional cost.  Submit the repair procedure to the Engineer for approval.

Do not remove the permanent metal forms under any circumstances.

Do not use permanent metal forms for the cantilevered deck overhangs.

501-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

501-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

SECTION 503

REINFORCING STEEL

Special Provisions

503-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

503-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

SECTION 504

STEEL STRUCTURES

Special Provisions

504-2.01 MATERIALS. Add the following:

Permanent Metal Forms	716

504-3.01 FABRICATION. Add the following to numbered item 8:

Provide all NDE (nondestructive examination) mandated on the plans and by the relevant welding code.  Perform a NDE in accordance with the mandate of AASHTO/AWS D1.5 even if not explicitly shown on the plans or stated in the project specifications.

Add the following numbered item:

9.	Permanent Metal Forms.  Permanently seal the 10 gauge metal deck forms shown on the plans against the intrusion of water to the interior of the girder.  Submit the method for sealing the forms on the shop drawings for the approval of the Engineer.  Repair all damaged galvanizing on the form surfaces.

504-3.02 PAINTING. Add the following numbered item:

4.	Spray-Metalizing Steel Surfaces. Refer to Section 716-2.07 Galvanized Metal of these specifications.

504-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

504-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

SECTION 505

PILING

Special Provisions

505-1.01  DESCRIPTION. Add the following:   Refer to subsection 505-4.01 Pile Refusal, numbered paragraph 8 of these Special Provisions for the definition of Pile Refusal.

505-3.03  PILE BEARING VALUES.  Delete this section in its entirety and substitute the following:   Drive all piles to the required ultimate bearing capacity.  The required ultimate bearing capacity is the ultimate pile load as indicated on the bridge plans.  The Engineer shall determine the pile driving criteria using a wave equation analysis. Use the wave equation program “GRLWEAP” program using the GRLWEAP industry standard hammer input data on this project. The Department anticipates that over driving will occur during installation of the piles at this bridge site.  The Department anticipates approximately 45 megagrams of excessive over driving resistance.  For hammer approval, perform all Wave Equation analyses for a Rult equal to the specified ultimate capacity plus 45 megagrams.

505-3.05 MINIMUM PENETRATION.  Add the following:   The Contractor shall furnish piles of sufficient length to drive to the minimum tip elevation, to meet the driving criteria from the wave equation analysis and to provide the required cutoff elevation.  Calculate pile lengths from the design cut off elevation to the estimated tip elevation.  The Contractor shall at his own expense, increase the pile lengths given to provide for fresh heading and for such additional pile lengths as may be necessary to suit their method of operation.

505-3.09  DRIVING PILES.  Delete the second paragraph and replace with the following: All pile driving equipment used by the Contractor shall be subject to the approval of the Engineer.  Equip all pile driving systems with an appropriate thickness of hammer cushion to prevent damage to the hammer or pile and to insure uniform driving performance.  Hammer cushions shall consist of durable, manufactured materials, and provided in accordance with the hammer manufacturers guidelines.  Do not use wood, wire rope, and asbestos hammers.  Inspect the hammer cushion in the presence of the Engineer

prior to beginning pile driving and after  each 50 hours of pile driving on this project.  Driving will not continue until the Contractor has replaced any hammer cushion that has lost a thickness exceeding 25% of the original thickness.

Size the pile driving equipment such that the piles can be:

1) 	driven to the required ultimate bearing capacity plus excessive overdrive resistance if specified above,

2) 	without damage to the piles,

3) 	have compressive driving stresses as indicated by the wave equation analysis not exceeding 90% of the pile yield stress and

4) 	with a penetration resistance of 120 blows per foot or less as determined by the wave equation analyses.  Approval of the pile driving equipment will be based on the wave equation analysis and the Engineer's recommendations.

Delete the third paragraph and replace with the following: Drive all piles at least to the minimum tip elevation as shown in the bridge plans or to a tip elevation based on the wave equation and the Engineer's recommendations.  If driving the piles to the limits of the tip elevations shown on the bridge plans cannot achieve the ultimate bearing capacity, the Contractor shall drive the piles to a tip elevation established by the Engineer.

At least thirty calendar days prior to driving the first pile, the Contractor shall submit pile driving equipment information on the "Pile Driving Equipment Data Form" provided by the Engineer.

The Contractor shall use the approved driving system to install the piles.  Variations in the driving system are only permissible with the Engineer’s written approval.  Any change in the driving system will only be considered after the Contractor has submitted a revised Pile Driving Equipment Data Form for a revised wave equation analysis by the Engineer, and the analysis indicates an acceptable result.  The Engineer will notify the Contractor of the acceptance or rejection of the revised driving system, within 7 calendar days of the Engineer's receipt of the requested change.  The time required for submission, review and approval of a revised driving system shall not constitute the basis for a contract time extension.

Add the following to the eleventh paragraph (last paragraph on page 202):

At this bridge site, the Contractor may encounter difficult subsurface soil conditions with cobbles and/or boulders or other obstructions during pile installation.  The Department advises the Contractor to have an  adequate size and type of equipment such as an excavator, pre-drilling equipment, boulder extractor, and/or boulder rooter to assist in advancing the piles down through the extremely difficult subsurface soil conditions, cobbles and/or boulders and other obstructions to the required pile tip elevation without damage to the piles.

505-4.01 METHOD OF MEASUREMENT. Delete the first sentence of numbered item 2 and substitute the following:

There will be no measurement for payment.

Delete numbered paragraph 6 and substitute the following:

6.	Drive piles not achieving the required ultimate bearing capacity within 1.5 meters (below) the estimated pile tip elevation shown on the plans to a penetration depth established by the Engineer.  If the Contractor plans to drive piles more than 1.5 meters deeper than the estimated pile tip elevations shown on the plans, it shall be done under the written direction of the Engineer.  Apply the Contract bid price for depths up to 7.6 meters below the estimated pile tip elevations.  Determine pile unit costs as per subsection 109-1.05 of the Standard Specifications, for depths beyond 7.6 meters below the estimated pile tip elevations.

Add the following:

8.	Special Pile Excavation: Use Special Pile Excavation when the Engineer requires the removal of unusual obstructions causing pile refusal above the specified minimum pile tip elevations.  Measure the work on a time and materials basis in accordance with subsection 109-1.05 of the Standard Specifications.  Pile refusal is the condition reached during pile driving which results in a bearing pile driven by an impact hammer having a negligible rate of penetration per blow (such as when a pile tip reaches an impenetrable bottom such as a rock or bedrock layer), and when the effective transferred energy of the impact hammer blow is no longer sufficient to advance the pile tip.

505-5.01 BASIS OF PAYMENT.  Add the following:

Work required for driven piles will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.  Items 505(5A) and 505(5B) will be paid for in conformance with the bid tabulation, project plans and specifications.

Pay Item No.	Pay Item	Pay Unit

505(5A)	Structural Steel Piles, Furnished (HP360X174)	Meter

505(5B)	Structural Steel Piles, Furnished (HP250X85)	Meter

505 (14)	Special Pile Excavation	Contingent Sum

SECTION 507

BRIDGE RAILING

Special Provisions

507-4.01 METHOD OF MEASUREMENT. Delete the first sentence and substitute the following:

There will be no measurement for payment.

507-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

Add the following Section:

SECTION 514

PEDESTRIAN BRIDGE

514-1.01 DESCRIPTION. This work consists of constructing the proposed  pedestrian bridge across Montana Creek.  This work includes all materials, labor, and equipment to complete the project.  Construct the pedestrian bridge as shown in the plans (plan design) or submit and construct a bridge of an alternate design. The alternate design shall meet AASHTO LRFD Bridge Design Specifications, 1998 Edition, and carry a Live Load of 4.1 kPa or an H-5 truck, whichever produces the maximum effect.

The alternate design shall be equal or superior to the plan design in terms of clear span, walkway width, pedestrian railing height, low steel height, hydraulic capacity, design life, and maintenance cost.  The approach grades for the alternative design shall be no steeper than the plan design.  The alternative design bridge may consist of material different from the plan design.

A professional Civil Engineer shall seal the alternate design licensed to practice in the State of Alaska, who specializes in structural design.  The Contractor must obtain an approved change order prior to fabrication or construction.

514-2.01 MATERIALS. Use materials that conform to the following subsections:

Structural Concrete	Subsection 501-2.01

Reinforcing Steel	Subsection 503-2.01

Structural Steel	Subsection 504-2.01

Piling	Subsection 505-2.01

CONSTRUCTION REQUIREMENTS.

514-3.01 GENERAL

Structural Concrete	Section 501

Reinforcing Steel	Section 503

Structural Steel	Section 504

Piling	Section 505

Bridge Railing	Section 507

Forms and Falsework	Section 512

514-4.01 METHOD OF MEASUREMENT.   Lump sum - no measurement.

The number of piles driven in place is subsidiary, while the length of piles furnished is not.

514-5.01 BASIS OF PAYMENT. Lump Sum. At the contract lump sum price.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

514(1)	Pedestrian Bridge 	Lump Sum

SECTION 602

STRUCTURAL PLATE PIPE

Special Provisions

602-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

602-5.01 BASIS OF PAYMENT. Replace this subsection with the following: At the contract lump sum price.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

602(2A)	Structural Plate Pipe 	Lump Sum

Arch Span 4216, Rise 3708, Gauge 2.77 mm

SECTION 603

CULVERTS AND STORMDRAINS

Special Provisions

603-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 606

GUARDRAIL

Special Provisions

606-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

606-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

# SECTION 608

SIDEWALKS

Special Provisions

608-1.01 DESCRIPTION. Add the following: This work consists of constructing the proposed pathways. This work includes all materials, labor, and equipment to complete the project.

608-2.01 MATERIALS. Add the following:

Embankment	Section 203

Aggregate Base and Surface Course	Section 301

Asphalt Pavements and Surface Treatments	Section 401

Culverts and Storm Drains	Section 603

Standard Signs	Section 615

Seeding	Section 618

Metal Pipe	Section 707

CONSTRUCTION REQUIREMENTS

Add the following subsection:

608-3.04 PATHWAY.  The Department intends this item to be all inclusive of all necessary items required to construct the pedestrian facilities as detailed on the plans.  This item also includes all mobilization and demobilization, temporary erosion and pollution control, construction surveying, traffic control, as well as field facilities, such as field office and laboratory.

608-4.01 METHOD OF MEASUREMENT. Add the following:

Pathway: By the lump sum, will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Item 608(9) Pathway shall be paid at the contract lump sum price.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

608(9)	Pathway	Lump Sum

SECTION 611

RIPRAP

Special Provisions

611-4.01 METHOD OF MEASUREMENT. Replace this subsection with the following: Work required under this section will not be measured for payment.

606-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

SECTION 615

STANDARD SIGNS

Special Provisions

615-2.01 MATERIALS. Under item 1. change the first sentence to the following: Submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

Mark the date of installation on the back of the sign prior to mounting the sign panel. Write the installation dates in the format of a month/day/year, using black permanent marker, with numbers a minimum of 75 mm in height, so as to be readable from the roadside after installation. (1/10/98)R50M98

615-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

615-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION. Delete this subsection and substitute the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. As soon as possible provide a living ground cover on all slopes.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.03 APPLICATION METHOD. In the first sentence of subparagraph b., under numbered paragraph 1. Hydraulic Method, delete the following: "and/or limestone, Item 618(4),".

Add the following: Apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

Add the following: Seed, mulch and fertilizer shall be applied as follows per hectare (ha). If the hydraulic method for seed and mulch is used, it shall be made in one application. All fertilizer shall be applied by the hydraulic method.

| Item | Ingredients | Application Rate (per ha) |
| --- | --- | --- |
| Seed Mix | Alpine Bluegrass Red Fescue (Arctared) Annual Ryegrass (Lolium) | 19.5 kg 24.4 kg 4.9 kg Total=48.8 kg |
| Mulch | -- |  |
| #3:1 |  | 2245 kg |
| >3:1 to 2:1 | add tackifier | 2245-2805 kg |
| Fertilizer | 20-20-10 | 586 kg |

The Contractor shall not remove the required tags from the seed bags.

618-4.01 METHOD OF MEASUREMENT. Replace this subsection with the following: Work required under this section will not be measured for payment.  This includes the following soil preparation, fertilizer, mulch and water for hydraulic seeding.  Reseeding may be required and is also included.

618-5.01 BASIS OF PAYMENT.  Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 620

TOPSOIL

Special Provisions

620-4.01 METHOD OF MEASUREMENT.  Replace the first sentence of this subsection with the following: Work required under this section will not be measured for payment. Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(9/11/96)R53

620-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 631

GEOTEXTILE FOR

SUBSURFACE DRAINAGE AND RIPRAP LINER

Special Provisions

631-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

631-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 514(1) Pedestrian Bridge.

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved. (06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

TEMPORARY EROSION AND POLLUTION

CONTROL

Special Provisions

641-1.01 DESCRIPTION. This work shall consist of temporary control measures as shown on the plans, or ordered during the life of the contract, to control temporary erosion and water pollution. This work shall include preparation of a Temporary Erosion and Pollution Control (TEPC) Plan. The Contractor shall conduct construction activities in accordance with the approved TEPC Plan.

This work shall also include installation of silt fence as shown on the plans or as directed by the Engineer.

641-1.02 TEMPORARY EROSION AND POLLUTION CONTROL PLAN. At least five (5) days prior to the preconstruction conference, the Contractor shall submit for approval by the Department's Environmental Section, a TEPC Plan consisting of the following:

1.	Methods for clearing and grubbing.

2.	Plan for installation of temporary erosion and sediment control measures, in accordance with the Department's Storm Water Manual, including, but not limited to, the following:

a.	Excavation and embankment construction;

b.	Construction of temporary and permanent drainage features;

c.	Construction in and around waterbodies and wetlands; and

d.	Haul roads and material sites.

- List of quantities, types and suppliers of materials.

3.	Disposal of waste material.

4.	Containment, cleanup, and disposal of such substances, as well as the  methods for disposing of, petroleum products or other hazardous substances generated by construction equipment or activities. The plan shall also include a list of the quantities and types of materials available on the site for hazardous substance containment and cleanup activities.

The Department will review the TEPC Plan for approval within five (5) working days. If corrections or modifications are necessary to the plan, the Contractor shall resubmit the corrected plan within five (5) days of receipt of the comments.

641-1.03 EROSION AND SEDIMENT CONTROL PLAN.  The Department’s Erosion and Sediment Control Plan is attached to these specifications in Appendix  B Permits.

641-2.01 MATERIALS. The silt fence filtration material shall meet the requirements of subsection 729-2.04 Sediment Control.

The silt fence support framework shall be finished 50 mm x 50 mm wood, 75 mm diameter wood, #6 rebar with PVC sleeves, iron pipe, or other posts capable of supporting the installation, as approved by the Engineer.

The mesh support shall be WWF 6x6 W1xW1 or as approved by the Engineer.

641-3.01 CONSTRUCTION REQUIREMENTS. The Engineer shall limit the surface area of erodible earth material exposed by clearing and grubbing, excavation, borrow and fill operations.  The Engineer shall direct the Contractor to provide immediate permanent or temporary pollution control measures to prevent contamination of adjacent streams, lakes, ponds or other areas of water impoundment. As necessary such work may involve the construction of temporary berms, dikes, dams, sediment basins, slope drains, and use of temporary mulches, seeding or other control devices or methods as necessary to control erosion. Use temporary pollution control measures to correct conditions that develop during construction that the Department did

not foresee during the design stage.  Conduct these measures  prior to installation of permanent pollution control features, but are not associated with permanent control features on the project.

The Contractor shall incorporate all permanent erosion control features into the project at the earliest practicable time as outlined in his accepted schedule.

Cut slopes shall be seeded and mulched as the excavation proceeds to the extent considered desirable and practicable.

Schedule and perform clearing and grubbing operations, where erosion is likely to be a problem, so that grading operations and permanent erosion control features can follow immediately thereafter if the project conditions permit; otherwise, the Engineer may require temporary erosion control measures between successive construction stages. The surface area of erodible earth material exposed at one time by clearing and grubbing shall not exceed 2.02 hectares without written approval.

The Engineer shall limit the area of excavation, borrow and embankment operations in progress.  This shall be done in commensurate with the Contractor's capability and progress in keeping the finish grading, mulching, seeding and other such permanent pollution control measures current in accordance with the accepted schedule. The Contractor shall take immediate temporary erosion control measures should seasonal limitations make such coordination feasible and justified.

In the event of conflict between these requirements and pollution control laws, rules or regulations of other federal or state or local agencies, the more restrictive laws, rules or regulations shall apply.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

Silt fence shall be installed prior to any work in or near the locations shown on the plans, and in accordance with the provisions of subsection 107-1.11, Protection and Restoration of Property and Landscape. Additional silt fencing may be required at other sites as directed by the Engineer.

The silt fence shall not be removed until slopes are stabilized from further erosion as determined by the Engineer. The silt fence shall be removed and disposed of off the project upon completion of construction at those sites. The fabric shall be cut off at ground level and the wire and posts shall be removed. The silt fence removal shall be performed in such a manner that retained silt is not discharged into wetlands or waterbodies. If a sediment height in excess of 100 mm above ground remains, the sediment shall be spread on the roadway side of the fence location and seeded immediately in accordance with Section 618, Seeding.  (7/23/97)R203M

641-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

641-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 642

CONSTRUCTION SURVEYING

Standard Modification

642-3.01 GENERAL.  Delete the seventh paragraph. (6/25/99)M79

Special Provisions

642-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

642-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  Speeds shall be limited to a minimum of 15 mph and a maximum of 25 mph depending upon the location conditions.  The Traffic Control plan shall specify the traffic control devices required for these operations.

Detours will be permitted to be in existence only one week for each detour.  The Department does not require the Contractor to pave the detours.

643-2.01 MATERIALS. Add the following: Traffic cones, candles, drums, and delineators that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, test level 3. This certification may be a one page affidavit signed by the vendor. Before using devices on the project give the certification to the Engineer. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.

Composition		Weight		Height

Cones		Rubber		 	9 kg		 920 mm

Plastic			9 kg		1220 mm

Candles	Rubber		 	6 kg		920 mm

Plastic			6 kg		920 mm

Drums		Hi Density Plastic	35 kg		920 mm

Lo Density Plastic	35 kg		920 mm

Delineators	Plastic or Fiberglass	 N/A		1220 mm

Provide documentation that certifies truck-mounted attenuators and portable crash cushions purchased after October 1, 1998 are in compliance with National Cooperative Research Program 350, test level 3, crash worthiness requirements.

Before using each of these devices on the project, provide the Engineer with certification, consisting of a letter of NCHRP-350 compliance from the Federal Highway Administration.

Standard Modification

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”. (06/25/99) M 80

Special Provisions

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, washboarding, potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to comply will result in a price adjustment equal to 10 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

643-3.08 CONSTRUCTION SEQUENCING. Add the following:

The Contractor shall not restrict traffic during the following times:

1.	Friday from 3:00 PM to Friday midnight.

2.	Sunday from 12:00 (noon) to Sunday at 6:00 PM.

3.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 3:00 P.M. on the Friday before the holiday to 3:00 A.M. on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 3:00 P.M. on the Tuesday before the holiday to 3:00 A.M. on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 3:00 P.M. on the day before the holiday to 3:00 A.M. on the Monday after the holiday.

The Contractor shall make every effort not to delay school buses through the construction work zone.

Lane restrictions, if allowed, the Contractor shall conduct such restrictions so that a waiting motorist encounters no more than a 10 minute accumulated delay through the entire length of the project.  The exception is during paving operations when the Engineer will allow 20 minute delays for all motorists except school buses. If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the Contractor released the queue.

643-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section, with the exception of Item 643(23) Traffic Price Adjustment, will not be measured for payment.

643-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section, with the exception of Item 643(23) Traffic Price Adjustment, will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

The total of value of this contract will be adjusted using Item 643(23) Traffic Price Adjustment, as determined by the Engineer, for lane restrictions, closures or delays in completing the directed work.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(23)	Traffic Price Adjustment	Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete the third fifth and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 50 square meters of floor area. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of two electrical outlets.

4.	A minimum of 5 square meters of window area and adequate ventilation.

5.	Provide adequate parking for a minimum of 5 vehicles, with one disability parking space. The Engineer's office shall be accessible by the disability parking. The disability parking shall meet the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

7.	Three (3) telephone service lines available at the office location.

8.	Located within 10 kilometers of the project.

9.	Provide one move in and one move out for state office furniture and equipment.  (7/8/98)R63aM

Standard Modifications

644-2.01 FIELD OFFICE.  In the third paragraph, change “the final inspection” to “project completion”. (06/25/99) M 81

Special Provisions

644-4.01 METHOD OF MEASUREMENT.  Replace this subsection with the following: Work required under this section will not be measured for payment.

Standard Modifications

644-4.01 BASIS OF PAYMENT. In the last full paragraph, begining with “Furnishing the following is subsidiary”, after “platform scales,” insert  “scale operators,”. (06/25/99) M 81

Special Provision

644-5.01 BASIS OF PAYMENT. Replace this subsection with the following: Work required under this section will not be paid for directly, but will be subsidiary to Item 608(9) Pathway.

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENT. Add the following: Performance Graded Asphalt Binders PG 52-28, PG 58-28, and PG 64-28 shall conform to the requirements of AASHTO MP1 and in addition shall meet or exceed the softening points  as determined by AASHTO T-53.

Soften Point (min)

PG 52-28		(none)

PG 58-28 		120°F

PG 64-28		125°F

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE AND SURFACE COURSE.  Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading D-1 |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 50-79 |
| 4.75 mm | 35-58 |
| 2.36 mm | 20-47 |
| 600 Fm | 10-26 |
| 300 Fm | 6-19 |
| 75 Fm | 0-6 |

(11/04/94)R117M

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.(06/25/99) M 82

SECTION 716

STRUCTURAL STEEL

Special Provisions

716-2.02 GENERAL REQUIREMENTS. Add the following numbered item:

11.	Permanent Metal Deck Forms.	Meet ASTM A653 AND ASTM A924.

716-2.07 GALVANIZED METAL. Add the following:

Spray metalized specified galvanized or spray-metalized structural steel shapes, plates, bars or their products in accordance with the Structural Steel Painting Council (SSPC) Coating System Guide Number 23.00, Guide for Thermal Spray Metallic Coating Systems. Apply a minimum metal coating thickness of 254 microns on both the interior and exterior girder surfaces.  Prepare the steel surfaces in accordance with SSPC-SP 5, White Metal Blast Cleaning. Apply a sealer coating to exterior girder surfaces. Do not galvanize or apply a sealer coat to the upper surface of the girder top flange.

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Recycled Paper (Awood cellulose@) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch. The mulch shall meet the following requirements:

a.	Contains no growth or germination inhibiting factors.

b.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry.

c.	Mulch can be applied uniformly on the soil surface.

d.	Will not create a hard crust upon drying and have moisture absorption and retention properties and the ability to hold grass seed in contact with the soil.

e.	Dyed a suitable color to facilitate inspection of its placement.

Ship the mulch material in packages of uniform weight (plus or minus 5%) and bear the name of the manufacturer and the air-dry weight content.

Use a commercial tackifier on all areas steeper than 3:1.  Use the amount recommended by the manufacturer.

(8/19/99)R206M98

SECTION 730

SIGN MATERIALS

Standard Modifications

730-2.04 SIGN POSTS.  In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.(6/25/99)M83

Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

6.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeters thick walls. Drill holes to permit mounting of the sign 11 millimeters in diameter.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Repair damaged and abraded tubes and beams in accordance with 1.c. of this subsection.

(1/21/95)R81M

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS (METRIC)

APPENDIX B

PERMITS