PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

1988 STANDARD SPECIFICATIONS FOR HIGHWAY CONSTRUCTION

SPECIAL NOTICE TO BIDDERS

Bidders are hereby notified that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	An environmental document addressing concerns and environmental commitments has been approved and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

2.	Effective January 1, 1998, contract items under Section 643, Traffic Maintenance, will no longer be creditable under the Disadvantaged Business Enterprise Program for DBE credit as subcontractable items. The only current exception is item 643(3), Permanent Construction Signs.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

3.	This is to notify all bidders that the contract award process, when a DBE Goal is specified, will be modified as explained below.

Prior to award, the Department has been allowing a low bidder who did not submit sufficient good faith efforts (GFE) documentation to then submit additional DBE participation to meet the goal stated in the bid documents. The FHWA has informed us that this practice is not allowable. If GFE documentation is submitted and found to be insufficient, the bidder is to be declared nonresponsive.

For contract DBE requirements, refer to Section 120, DBE Program.

For more information, contact the DOT&PF Civil Rights Office at (907) 269-0851 or Toll Free at 1-800-770-6236.

4.	The Department’s procedure for providing for the costs of on-site flagging has changed. In recognition of the benefits derived from a well coordinated flagging operation to both the traveling public and the Contractor’s operation, the Department’s position is that the Contractor is a full partner in this contract and should participate in the cost of flagging. Therefore, the Department has changed the amount paid to provide flagging from a $45.00 / hour to a shared $32.00 / hour. The additional actual cost to provide a flagger will be considered as incidental to other items of work. This change will in no way relieve the Contractor from his responsibility to provide for safety and convenience of the public.

5.	The United States Department of Transportation has recently issued new regulations for the DBE Program (49 CFR Part 26).  New eligibility criteria for DBE firms have been added, including consideration of Personal Net Worth (PNW) of the DBE owner(s).  This new criteria will be used to verify continued certification in the DBE Program.  Contractors are requested to continue to use the same procedure they have been using until the Department can establish the PNW.  If a DBE firm on a Project awarded after March 3, 1999 is decertified for failure to meet the PNW criteria, the Department will deal with the issue on a case by case basis.

6.	This project will require specialized milling equipment to perform the work as specified in Section 406-2.01 of the special provisions.  The Contractor shall submit the following certification prior to award:

A written certification from the manufacturer of the milling equipment to be used that 		addresses the following:

Provide a listing of at least five (5) rumble strip projects of at least 100 miles in length each completed with the proposed milling equipment in the past two years.  Include names, addresses, and phone numbers of agency personnel directly involved in administering the milled-in rumble strip installation contracts.

SECTION 101

DEFINITIONS AND TERMS

Special Provisions

101-1.26 HIGHWAY, STREET OR ROAD. Delete this subsection in its entirety and substitute the following: A general term denoting a public way used by vehicles and pedestrians, including the entire area within the right-of-way.

Standard Modifications

101-1.27 HOLIDAYS. Delete Items 2 and 3 and substitute the following:

2.	Martin Luther King Jr's. Birthday - Third Monday in January

3.	President's Day - Third Monday in February

(5/7/91)M30

Special Provisions

101-1.30 MAJOR CONTRACT ITEM. Replace “10%” with “5%”.

101-1.33 MINOR CONTRACT ITEM. Replace “10%” with “5%”.

Add the following subsections:

101-1.62a SUBSIDIARY. Not paid for directly. Compensation for such work is included in the payment for other items of work and no separate payment will be made. (2/18/99)R230

101-1.73 NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the No. 200 screen as determined by sieve analysis performed on minus 3-inch material. (01/31/94)R1

101-1.74 INTERIM WORK AUTHORIZATION (IWA).  A written order by the Project Engineer initiating changes to the contract, within its general scope, until a subsequent Change Order is executed. (9/2/99)R242

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modifications

102-1.01 QUALIFICATION OF BIDDERS. Delete the second paragraph.  (5/12/89)M1

Special Provisions

Insert the following at the end of this section:

This project will require specialized milling equipment to perform the work as specified in Section 406.2.01 of the Special Provisions.  The Contractor shall submit the following certifications prior to award:

A written certification from the manufacturer of the milling equipment to be used that addresses the following:

Provide a listing of at least five (5) rumble strip projects of at least 100 miles in length each completed with the proposed milling equipment in the past two years.  Include names, addresses, and phone numbers of agency personnel directly involved in administering the milled-in rumble strip installation contracts.

Provides a listing of all rumble strip projects completed with the proposed milling equipment in the past two years.  Include names, addresses and phone numbers for agency personnel directly involved in administering the milled-in rumble strip installation contracts.

102-1.06 PREPARATION OF PROPOSAL. Replace the first sentence with the following: The bidder shall submit his proposal on the forms furnished by the Department, or legible copies thereof.

Standard Modifications

102-1.06 PREPARATION OF PROPOSAL. Replace the second paragraph with the following: The bidder shall specify a unit price, in figures, for each pay item for which a quantity is given and shall also show the products of the respective unit prices and quantities written in figures in the column provided for that purpose and the total amount of the proposal obtained by adding the amounts of the several items. All the figures shall be in ink or typed. In the event of a discrepancy between unit bid prices and extensions, the unit bid price shall govern. Any changes shall be initialed by the person signing the proposal. (7/2/93)M58

Add the following: At certain bid openings a bidder may wish to submit bids on more work than he desires to have awarded to him. The bidder may indicate the total amount desired to be accepted and the Department will determine which of his low bids on these projects, up to the final total indicated, will be accepted. This limitation will only apply when the bidder has added the following statement to the Proposal Form for at least one of the projects being bid:

"We desire to disqualify all of our bids at this letting which exceed the total of $__________ or _____ contracts and hereby authorize the Department to determine which bids shall be disqualified."

Special Provisions

102-1.07 NON-RESPONSIVE PROPOSALS. Replace item 1. with the following:

1.	If the proposal is on a form other than that furnished by the Department, or legible copies thereof; or if the form is altered or any part thereof is detached; or if the proposal is improperly signed.

Standard Modifications

Delete item 3. in its entirety and substitute the following:

3.	If the bidder adds any provisions reserving the right to accept or reject any award, or to enter into a contract pursuant to an award, except for a maximum limit on the total amount of awards acceptable to the bidder at any one bid letting, as provided in Subsection 102-1.06, Preparation of Proposal.  (6/6/94)M31

Add a new item as follows:

7.	If any of the unit prices bid are excessively unbalanced (either above or below the amount of a reasonable bid) to the potential detriment of the Department.  (5/12/89)M2

Special Provisions

102-1.09 DELIVERY OF PROPOSALS. Delete the third paragraph.

102-1.12 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (10/28/96)R171

102-1.16 NON-COLLUSION AFFIDAVIT. Delete this subsection.

(2/18/99)R231

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

103-1.01 CONSIDERATION OF PROPOSALS. Add the following: The apparent low bidder shall submit a completed Subcontractor List, form 25D-5(C), within 5 working days following receipt of written notification by the Department.

If a bidder fails to list a subcontractor or lists more than one subcontractor for a particular portion of work and the value of that work is in excess  of one-half of one percent of the total bid, the bidder agrees to perform that portion of work without the use of a subcontractor and to have represented that he is qualified to perform that work.

A bidder who attempts to circumvent the requirements of this subsection by listing as a subcontractor another Contractor who, in turn, sublets the majority of the work required under the contract, violates this subsection.

If a contract is awarded to a bidder who violates this subsection, the Contracting Officer may:

1.	cancel the contract without any damages accruing to the Department, or,

2.	after notice and a hearing, assess a penalty on the bidder in an amount that does not exceed 10 percent of the value of the subcontract at issue.

A bidder may replace a listed subcontractor who:

1.	fails to comply with AS 08.18,

2.	files for bankruptcy or becomes insolvent,

3.	fails to execute a contract with the bidder involving performance of the work for which the subcontractor was listed and the bidder acted in good faith,

4.	fails to obtain bonding,

5.	fails to obtain insurance acceptable to the Department,

6.	fails to perform the contract with the bidder involving work for which the subcontractor was listed,

7.	must be replaced in order for the prime Contractor to satisfy required State and/or Federal affirmative action requirements,

8.	refuses to agree or abide with the bidder's labor agreement, or,

9.	is determined by the Contracting Officer not to be responsible.

(4/1/93)R82

103-1.04 PERFORMANCE AND PAYMENT BONDS. In the third paragraph, under item 1.delete the first sentence and substitute the following: Escrow account, with a Federally-insured financial institution, in the name of the Department.

103-1.05 INSURANCE REQUIREMENTS. Delete this subsection in its entirety and substitute the following: The Contractor shall provide evidence of insurance with a carrier or carriers satisfactory to the Department covering injury to persons and/or property suffered by the State of Alaska or a third party, as a result of operations under this contract by the Contractor or by any subcontractor. This coverage will also provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this contract. The delivery to the Department of a written 30 day notice is required before cancellation of any coverage or reduction in any limits of liability. Insurance carriers providing coverage shall have an acceptable financial rating.

The Contractor shall maintain in force at all times, during the performance of work under this contract, the following policies of insurance. All insurance policies shall comply with, and be issued by insurers licensed to transact the business of insurance under AS 21. Failure to maintain the specified insurance may, at the option of the Contracting Officer, be deemed as unacceptable work and remedied under Subsection 105-1.11. Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor's indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

1.	Workers' Compensation Insurance: The Contractor shall provide and maintain, for all employees of the Contractor engaged in work under this contract, Workers' Compensation Insurance as required by AS 23.30.045. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who provides services under this contract, to include:

a.	Waiver of subrogation against the State and Employer's Liability Protection in the amount of $500,000 each accident/$500,000 each disease.

b.	If the Contractor directly utilizes labor outside of the State of Alaska in the prosecution of the work, “Other States” endorsement shall be required as a condition of the contract.

c.	Whenever the work involves activity on or about navigable waters, the Workers' Compensation policy shall contain a United States Longshoreman’s and Harbor Worker’s Act endorsement, and when appropriate, a Maritime Employer’s Liability (Jones Act) endorsement with a minimum limit of $1,000,000.

Commercial General Liability Insurance: on an occurrence policy form covering all operations by or on behalf of the Contractor with combined single limits not less than:

$1,000,000 each occurrence

$1,000,000 for Personal Injury Liability

$2,000,000 aggregate for Products-Completed Operations

$2,000,000 general aggregate

The State of Alaska shall be named as additional insured. This insurance shall be considered to be primary and non-contributory to any other insurance carried by the State through self insurance or otherwise.

Automobile Liability Insurance: covering all vehicles used by the Contractor in the performance of services under this agreement with combined single limits not less than $1,000,000 each occurrence.

In addition to providing the above coverages the Contractor shall, in any contract or agreement with subcontractors performing work, require that all indemnities and waivers

of subrogation it obtains, and that any stipulation to be named as an additional insured it obtains, also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as additional named indemnitee and as additional insured.

Evidence of insurance shall be furnished to the Department prior to the award of the contract. Such evidence, executed by the carrier's representative and issued to the Department, shall consist of a certificate of insurance or the policy declaration page with required endorsements attached thereto which denote the type, amount, class of operations covered, effective (and retroactive) dates, and dates of expiration. Acceptance by the Department of deficient evidence does not constitute a waiver of contract requirements.

When a certificate of insurance is furnished, it shall contain the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number).”

(2/18/99)R232

SECTION 104

SCOPE OF WORK

Special Provisions

104-1.02  CHANGES. Add the following after the third paragraph: Before a Change Order or Supplemental Agreement covering work for which there is no established contract price is approved, the Contractor shall submit detailed cost or pricing data regarding the changed or extra work. The cost or pricing data shall include an itemization of all costs including labor, materials, and equipment required for the work. The Contractor shall certify that the data submitted is, to his best knowledge and belief, accurate, complete and current as of a mutually determined specified date and that such data will continue to be accurate and complete during the performance of the changed or extra work. (2/18/99)R233

SECTION 105

CONTROL OF WORK

Standard Modifications

105-1.01 AUTHORITY OF THE ENGINEER. Add the following: The Engineer may, at reasonable times, inspect that part of the plant or place of business of the Contractor or subcontractor that is related to the performance of the contract.

The Engineer may audit the books and records of the Contractor or a subcontractor to the extent that the books and records relate to the performance of the contract or subcontract, including cost or pricing data submitted under subsection 104-1.02, Changes. Books and records that relate to the performance of the contract shall be maintained by the Contractor for a period of three years after the date of final payment under the prime contract and by the subcontractor for a period of three years after the date of final payment under the subcontract, unless a shorter period is authorized in writing by the Contracting Officer.

(5/12/89)M6

Special Provisions

Add the following paragraph:

When, in the opinion of the Engineer, conditions are such that the safety and/or convenience of the traveling public are adversely affected, the Contractor will be immediately notified in writing. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). In no case shall this time exceed 24 hours. In the event that the Contractor fails to take the corrective action within the specified time, the Engineer may direct that the offending operations cease until the defect(s) is (are) corrected. The Engineer reserves the right to have corrective action taken by outside forces. The cost of work by outside forces shall be deducted from any monies due or that may become due under the terms of this Contract.

105-1.02 PLANS AND WORKING DRAWINGS. Replace the second sentence of the second paragraph with the following: No work shall be performed until working drawings for such work, or changes thereto, are approved.

Delete the last two sentences of the second paragraph and substitute the following: All working and detail drawings shall be full size, on white paper, and have dark blue or black lines.

Replace the second sentence of the fourth paragraph with the following: The Contractor shall indicate on the working drawings all deviations from the plans and specifications and shall also itemize and explain all deviations in the letter of transmittal.

(7/2/93)S62

In the next to last paragraph, delete “of the drawings for use by the Engineer” and substitute the following: “or an Autocad drawing interchange file format (.DFX) on 3.5-inch disk.”

105-1.05 COOPERATION BY CONTRACTOR. In the last paragraph, insert the following before the last sentence: The superintendent shall have the authority to sign Directives for the Contractor.

(2/18/99)R234

105-1.06 COOPERATION WITH UTILITIES. Add the following: If necessary, the Contractor shall request locates from all the utilities having facilities in the area. Contractor shall use the locate call center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska-DOT/PF Anchorage M&O Alaska Fiber Star Alaska Native Medical Center Alyeska Cable Anchorage School District Anchorage Telephone Utility Anchorage Water & Wastewater Utility AT&T Alascom, Inc. Chugach Electric Association City of Wasilla ENSTAR Natural Gas, Inc. Eyecom TV/Interior Telephone GCI Communications Homer Electric Association Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association MFS Technologies, Inc. Mukluk Telephone Association Municipality of Anchorage Municipal Light & Power (Anchorage) Phillips Petroleum PTI Communications, Inc. Rogers Cable Systems of AK, Inc. Signature Flight Support Tesoro / KPL United Utilities Inc. Unocal Pipeline

The Contractor shall call the following utilities and agencies directly:

Alaska Railroad Corporation	265-2520

Defense Energy Office Alaska	552-5980

State (DOT & PF) Street Lights & Storm Drains (Anchorage)	333-2411

State (DOT & PF) Street Lights & Storm Drains (Kenai)	269-0783

U. S. Army (Ft. Richardson Utilities)	384-3656

U. S. Air Force Liquid Fuels	552-3334

All existing utilities shall remain in service until the new utilities are installed and put into service.

There are various utility appurtenances located within the project limits. The Contractor is required to cooperate with the utilities and coordinate his work schedule to allow them access to the project for their adjustments and/or relocations.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen. Also, the utilities may prohibit the Contractor, through the Engineer, from working near the utility's facilities when the ground is frozen.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

Right of Way and/or Construction surveying is required of the Contractor prior to utility relocation. Payment to the Contractor will be made as follows:

1.	Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract, and/or;

2.	Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor”s two (2) week work plan, or not required by the contract.

The Utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice of the staking required.

It is the Contractor’s responsibility to schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

The Contractor shall give each utility fifteen (15) calendar days advance written notice that relocation is required. The utility will only be required to work in one location at a time.

Specific coordination requirements for the specific utilities are included below:

(2/17/99)R3

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following:  Six sections of roadway to receive rumble strips will be under construction during the summer of 2000 and will require coordination between other Contractors.  They will not be available for installation of rumble strips until after final paving has occurred.  If the final paving is not complete prior to September 1, 2000, they will be deleted from the rumble strip project without compensation adjustment.  Work will not begin on any of these highway segments until authorized by the Engineer to begin.  Following is a list of those roadway sections and their respective bid item quantities:

| Roadway Section Minnesota Drive - Old Seward Highway to Tudor Road Ocean Dock Road - Whitney Road to Port of Anchorage Sterling Highway - Seward Wye to Cooper Landing Glenn Highway - Moose Creek to Sutton Seward Highway - MP 8 to MP 18 Parks Highway – Glenn Highway to Church Road | Shoulder Rumble Strip Quantity (mi.) 9.27 2.10 16.32 11.90 19.08 10.64 | Lane Line Rumble Strip Quantity (mi.) 15.07 |
| --- | --- | --- |

105-1.12 LOAD RESTRICTIONS. Delete this subsection in its entirety and substitute the following: The Contractor shall comply with all legal size and weight regulations of 17 AAC 25 and all restrictions in the “Administrative Permit Manual”.

The Engineer may waive the permit requirements of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within the project limits when the Contractor submits an acceptable Traffic Control Plan, in accordance with Subsection 643-1.02.

Permits may be obtained from the Department’s Division of Measurement Standards & Commercial Vehicle Enforcement for movements of oversize and overweight equipment outside of the project limits.

(2/18/99)R235

105-1.13 MAINTENANCE DURING CONSTRUCTION. Delete the first paragraph and substitute the following: The Contractor shall maintain the work, and those portions of the project affected by the work, from the date physical construction begins until project completion. This maintenance shall be a continual and effective effort prosecuted day by day, with adequate equipment and forces to the end that the work, and those portions of the project affected by the work, are kept in satisfactory condition at all times.

The Contractor may be relieved of specified portions of this maintenance responsibility during a seasonal suspension of work (Subsection 643-3.07), following partial acceptance (Subsection 105-1.14), or following substantial completion (Subsection 108-1.07). The Department will be responsible for routine snow removal and ice control on only those portions of the project which are open for public use.

(2/18/99)R236

Standard Modifications

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following to the fifth paragraph:

5.	A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the contract adjustment for which the Contractor believes the Department is liable. (7/2/93)M8

Special Provisions

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Delete the ninth paragraph and substitute the following: Any appeal must be in writing, must be limited to the issues that were before the Engineer, and must list the specific exceptions to the Engineer's decision including specific provisions of the Contract which the Contractor intends to rely upon in his appeal. (2/18/99)R237.

Add the following: Legal actions shall be commenced through the Superior Court, Alaska State Courts, Third Judicial District, in Anchorage. (8/5/93)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. Add the following: All steel and iron products that are incorporated into the finished work shall meet the requirements of “Buy America” as defined in Title 23 Code of Federal Regulations Section 635.410.  In order to meet the requirements of “Buy America” all manufacturing processes for steel and iron materials furnished for incorporation into the work on this project shall occur in the United States. Pig iron and processed, pelletized and reduced iron ore manufactured outside of the United States is permissible in the domestic manufacturing process for such steel and iron materials. The definition of “manufacturing process” is smelting, or any subsequent process that alters the material’s physical form, shape, or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, and drilling.  The application of coatings, such as epoxy coating, galvanizing, painting and any other coating that protects or enhances the value of steel or iron materials shall be considered a manufacturing process subject to the "Buy America" requirements.

Prior to using any steel or iron products on the project the Contractor shall furnish a materials certification of the origin of the materials to the Engineer.   This will include the signature of the manufacturer’s representative on all mill test reports stating that all manufacturing processes (from melting to fabrication) occurred in the United States.

The requirements imposed by “Buy America” do not prevent a minimal use of foreign steel and iron materials if the total combined cost of the materials used does not exceed one-tenth of one percent (0.1%) of the total contract cost or $2500, whichever is greater.  For the purposes of this paragraph, the cost is that shown to be the value of the steel or iron products upon delivery to the project.  The Contractor shall furnish the Engineer acceptable documentation of the quantity and value of any foreign steel and iron prior to incorporating the materials into the work.

(6/11/99)S1398M

Add the following: YEAR 2000 WARRANTY: The Contractor warrants that each hardware, software, or firmware product or item delivered or developed under this contract shall accurately process date data (including, but not limited to calculating, comparing, and

sequencing) from, into, during, and between the twentieth and twenty-first centuries, including leap year calculations, when used in accordance with the documentation provided by the Contractor.

If the contract requires that specific products or items perform as a system, then this Year 2000 Warranty shall also apply to those listed items as a system.

The duration and remedies available to the State for breach of the Year 2000 Warranty shall be as defined in, and subject to, the year 2000 terms and limitations of any general warranty provisions contained in this solicitation. In the absence of any such general warranty provision(s), the remedies available to the State shall include repair or replacement, without any cost to the State, of any listed product or item whose noncompliance is discovered and made known to the Contractor in writing by April 1, 2000 or within one (1) year after acceptance, or within the time limits of the Contractor’s warranty, whichever is longer.

Nothing in this Year 2000 Warranty shall be construed to limit any rights or remedies the State may otherwise have under the Uniform Commercial Code, State or Federal law, or with respect to defects other than Year 2000 performance.

The warranties contained herein are separate and distinct from any other warranties expressed or implied and are not subject to any disclaimer of warranty or limitation of the supplier’s liability.

(3/4/98)S79

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Prior to removing, stockpiling, staging or disposing of any material or equipment in, on or from a location not previously permitted by the contract, the Contractor shall obtain all necessary permits and clearances required. These permits and clearances may include, but are not limited to, State Historic Preservation Office clearance, a Division of Governmental Coordination Coastal Consistency Determination, Alaska Department of Natural Resources Mining Reclamation Permit, Alaska Department of Environmental Conservation permits, Alaska Department of Fish and Game Title 16 permit, US Fish and Wildlife endangered species clearance, US Army Corps of Engineers clearances and permits regarding wetlands, City or Borough Flood Hazard permit, local development permits, permission of property owner, etc.

The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. Should cultural resources be discovered during construction activities, work at that site shall be stopped and the Engineer notified.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, that will be impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that all permits or clearances necessary have been obtained. Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action was required on the part of the Contractor.

(7/8/98)R7

107-1.08 RAILWAY-HIGHWAY PROVISIONS. Delete the first paragraph and substitute the following: If the Department determines that the construction of the project will require that materials be hauled across the tracks of any railway, the Department will make arrangements with the railway for the use of such crossings. The Contractor shall obtain permits from the Railroad if additional temporary crossings are needed.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Delete this subsection in its entirety and substitute the following:

The Contractor shall be responsible for and shall protect from disturbance all land monuments and property marks until the Engineer has approved the witnessing or otherwise referenced their location and shall not move them without approval.

The Contractor shall be responsible for all damage or injury to property of any character, resulting from any act, omission, neglect, or misconduct in his manner or method of executing the work, or at any time due to defective work or materials, during the prosecution of the work, and said responsibility will not be released until the project shall have been completed and accepted.

When or where any direct or indirect damage or injury is done to public or private property by or on account of any act, omission, neglect or misconduct in the execution of the work, or in consequence of the non-execution thereof by the Contractor, he shall restore, at his own expense, such property to a condition similar or equal to that existing before such damage or injury, all in an acceptable manner.

The Contractor shall conduct work in a manner that minimizes disturbance to and protects natural resources in compliance with all Federal, State, and local laws and regulations. When working near designated wetlands, as defined by the Corps of Engineers 1987 Manual, the Contractor shall place no fill, nor operate equipment outside the permitted slope limits. When working in or near designated fish streams, as defined by AS 16.05.840 and .870, the Contractor shall not place fill or dredge material, nor operate equipment within or on the banks of the stream (including fording) except as permitted by the Fish Habitat Permit issued for the project. Refueling and servicing of equipment shall not be performed within 100 feet (30 m) of wetlands and/or other water bodies.

The Contractor shall not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels. The Contractor shall not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum. The Contractor shall report immediately to the Engineer any known or suspected hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project. The Contractor shall also report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery. Hazardous materials include, but are not limited to petroleum products, oils, solvents, paints, and chemicals that are toxic, corrosive, explosive, or flammable.

The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, staging activities, equipment or material storage, or for any other purposes unless permitted by the Contract or unless all permits and clearances necessary for such work have been obtained by the Contractor as detailed in Section 107-1.02.

All debris, trash, and other solid waste from project construction shall be removed from the area as soon as possible and in accordance with the Department of Environmental Conservation Solid Waste Program.

(2/18/99)R239

Standard Modifications

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. In the first sentence, change "claims or actions for injuries" to read "claims, actions or liabilities for injuries". (5/12/89)M9

Special Provisions

107-1.15 CONTRACTOR'S RESPONSIBILITY FOR WORK. Add the following to the end of the first paragraph: Damage caused by the public, prior to acceptance (Partial Acceptance or Project Completion), shall be corrected at the Contractor's expense. (5/7/91)S48

Standard Modifications

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICES. In the last sentence of the third paragraph delete: "by the local fire authority." (5/12/89)M10

Special Provisions

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 10 feet of an overhead electrical line.

2.	Operations anticipated to be within 3 feet of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 10 feet of an overhead electrical line.

The notice shall indicate the location and duration of the work to be performed.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 15 feet of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will not be paid for separately, but will be subsidiary to the item(s) of work being performed requiring these services.  (4/21/94)R170

107-1.21 PERMITS. Add the following subsection:

The Contractor shall be responsible for conducting all operations in compliance with Anchorage Municipal Code 15.70 (Noise). If the Contractor can not conform with the restrictions of this Code, it is his responsibility to obtain a Noise Permit authorizing the nonconformance. Application for this permit can be made through the  Municipality of Anchorage, Health and Human Services Division, 825 "L" Street, Anchorage, Alaska, (907)343-4200.

The permits obtained by the Department, if any, are attached to these specifications as Appendix A. The terms, conditions, and stipulations contained in all the permits obtained by either the Department or the Contractor are hereby made a part of these specifications. It is the Contractor's responsibility to abide by the stipulations contained in each permit. If it is determined that an activity cannot be performed as specified in one of the permits, the Contractor shall cease work and immediately notify the Engineer. The Engineer will then decide if a permit modification is necessary. The Engineer will have copies of the permits posted in the project office.

It is the Contractor’s responsibility to obtain all permits required for actions not permitted previously by ADOT&PF.   The Contractor is responsible for complying with all permit stipulations, conditions and/or terms.  Agencies to contact for permit information may include, but are not limited to, the U.S. Army Corps of Engineers, the Environmental Protection Agency, the U.S. Fish and Wildlife Service, the Alaska Department of Fish and Game, the Alaska Department of Environmental Conservation, the Alaska Department of Natural Resources, and local or regional governments.  The Contractor shall provide timely notification of such actions and permit acquisitions as may be required by federal, state, regional, and local authorities.  The Contractor shall provide copies of all permits, and applicable Federal and State notifications to the Project Engineer.

(5/23/96)R9

Add the following subsection:

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A301

EEO-1 Certification							Form 25A304

DBE Subcontractable Items						Form 25A324

ADOT&PF Training Program Request				Form 25A310

Training Utilization Report						Form 25A311

Contact Report							Form 25A321A

DBE Utilization Report						Form 25A325C

Summary of Good Faith Effort Documentation			Form 25A332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

In addition to the reports required in the above references, the Contractor shall submit a copy of Form CC-257 to the Department by the 15th of each month of the current construction season, reflecting the composition of the previous month’s workforce. This information must also be made available, upon request, to the US Department of Labor, Office of Federal Contract Compliance Programs.

(8/13/98)S80

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.01 SUBLETTING OF CONTRACT. Delete the second paragraph. (6/6/94)S68

Standard Modifications

108-1.03 PROSECUTION AND PROGRESS. In Item 1. insert: ", in a format acceptable to the Engineer," immediately after the words: "a progress schedule". (5/12/89)M11

Special Provisions

Delete Item 7, of the first paragraph and substitute the following:

7.	A letter designating the EEO Officer and the DBE Officer and those persons' responsibilities and authority.

(2/18/99)R160

In the first paragraph, delete the words "At this time" and substitute: "Five working days before the preconstruction conference". (5/7/91)S50

Add the following: The construction of this project shall be planned and recorded with a Critical Path Method (CPM) schedule. The schedule shall be used for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.

1.	Preparation of CPM Schedule. At the preconstruction conference, the Contractor shall submit for the Engineer's approval, a detailed initial CPM schedule. The schedule shall meet the requirements set forth below.

The construction time, for the entire project shall not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, the Contractor shall do so promptly. The CPM schedule must be finalized within 60 days of the Notice to Proceed.

2.	Schedule Requirements. All required CPM  schedule submittals shall include 1 hard copy and 1 copy of the same schedule on a 3.5-inch double sided diskette.

The CPM schedule shall be presented as a Precedence Diagram Network developed in the activity-on-node format and shall include:

a.	activity description,

b.	activity duration,

c.	resources required for each of the project activities, including:

(1)	labor, showing:

-work days per week

-holidays

-shifts per day

-hours per shift

(2)	equipment, including the number of units of each type of equipment, and

(3)	materials.

The activity-on-node diagram shall show the sequence and interdependence of all activities required for complete performance of all items of work under this contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration shall be longer than 15 working days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

3.	60-Day Preliminary Schedule. Before proceeding with any work on site, the Contractor shall prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule. The schedule shall provide a detailed breakdown of activities scheduled for the first 60 days of the project and shall include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

4.	Schedule Updates. Job site progress meetings will be held monthly by the Engineer and the Contractor for the purpose of updating the CPM schedule. Progress will be reviewed to verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions. The Contractor shall submit a revised CPM schedule within 7 calendar days after this meeting. The revised schedule shall show finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by contract modification.

The contract completion time will be adjusted only for causes specified in this contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

It is understood by the Engineer and the Contractor that float is a shared commodity.

In addition to the CPM schedule, the Contractor shall, every two weeks during construction, submit a work plan detailing his proposed operations for the forthcoming two weeks. This plan shall detail the following:

1.	work activities,

2.	manpower involved by trade,

3.	work hours,

4.	equipment involved, and

5.	the location of the work to be performed.

After approval of the progress schedule , and during the life of this project, the Contractor shall make available a spokesperson knowledgeable in the proposed construction operation.

Preparation and updating of the CPM schedule and two week work plans will not be paid for directly. Failure to submit the CPM work schedule and two week work plans as specified will result in partial withholding of progress payments in accordance with subsection 109-1.06, Progress Payments.  (12/13/96)R11

108-1.05 CHARACTER OF WORKMEN, METHODS AND EQUIPMENT.  Add the following: The Contractor shall provide the Engineer with make, model, year, capacity, horsepower, and the related information of every piece of powered equipment used on the project. This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)R13

Standard Modifications

108-1.07 FAILURE TO COMPLETE ON TIME. Replace the third sentence of the first paragraph with the following: The amount of these deductions is to reimburse the Department for estimated additional contract administration expenses incurred as a result of the Contractor's failure to complete the work within the time specified.

Replace Table 108-1 with the following:

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  |  |
| --- | --- | --- |
| From More Than | To and Including | Daily Charge |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | - | 3,000 |

(7/2/93)M49

Special Provisions

Add the following after Table 108-1:

The daily charges may be terminated at or following the final inspection, if the Department has determined that the work is substantially complete and is in a condition for safe and convenient use by the traveling public. The work will be considered substantially complete when all necessary signing, striping, guardrail, and other safety appurtenances have been installed. For projects that will not be opened to the traveling public, the work will be considered substantially complete when it is ready for the subsequent project. This shall not be construed as a contractual right and its application will be contingent upon the Contractor's diligence in completing the remaining items of work.

108-1.09 TERMINATION OF WORK FOR DEPARTMENT'S CONVENIENCE. Delete the second sentence of the fourth paragraph and substitute the following: Payment for partially completed work will be made at actual costs incurred plus a reasonable profit.

Delete the fifth and sixth paragraphs and substitute the following:

After receipt of a Notice of Termination, the Contractor shall submit to the Contracting Officer, his claim for additional costs not covered above or elsewhere in these Specifications. Such claim may include such cost items as reasonable idle equipment time, mobilization efforts, bidding and project investigative costs, overhead expenses directly allocable to the project termination and not covered under work paid for in the preceding paragraph, legal and accounting charges and other expenses reasonably necessary in claim preparation, subcontractor costs not otherwise paid for, actual idle labor costs if work is stopped in advance of termination date, guaranteed payments for private land usage as part of the original Contract, and any other costs for which the Contractor feels reimbursement should be made. The intent of negotiating this claim would be to reach an equitable settlement figure with the Contractor for the actual costs incurred. In no event, however, will loss of anticipated profits or consequential damages be considered as part of any settlement.

For any claim related to operating equipment owned by the Contractor, the Contractor is entitled to recover equipment costs based on the Contractor's actual costs for ownership and actual operating expenses. For any claim related to idle equipment time for equipment owned by the Contractor, the Contractor is entitled to recover equipment rates based on the Contractor's internal ownership costs. Recovery for operating equipment or idle equipment time shall not be based on published rental rates. Claims for idle equipment time following termination of the contract are limited to a maximum of 30 days, and may not include any operating expenses. In the case of rented or leased equipment, the Contractor shall recover the lesser of its actual rental costs or fair market rental costs, and the amount paid shall not exceed 30 days rental.

(2/18/99)R241

108-1.05 CHARACTER OF WORKMEN, METHODS AND EQUIPMENT. Add the following: The Contractor shall provide the Engineer with make, model, year, capacity,

horsepower, and the related information of every piece of powered equipment used on the project. This information shall be updated weekly unless otherwise directed by the Engineer. (9/1/89)R13

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME.  Under item number 3. delete the last sentence of the first paragraph and substitute the following:  When a controlling item of work is suspended for one or more calendar days by order of the Engineer, through the use of a Directive, the number of days included in such suspension period shall not be included in the count of contract time except as herein stated.

108-1.07 FAILURE TO COMPLETE ON TIME. Replace the third sentence of the first paragraph with the following: The amount of these deductions is to reimburse the Department for estimated additional contract administration expenses incurred as a result of the Contractor's failure to complete the work within the time specified.

Replace Table 108-1 with the following:

TABLE 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  |  |
| --- | --- | --- |
| From More Than | To and Including | Daily Charge |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | - | 3,000 |

(7/2/93)M49

The daily charges may be terminated at or following the final inspection, if the Department has determined that the work is substantially complete and is in a condition for safe and convenient use by the traveling public. The work will be considered substantially complete when all necessary signing, striping, guardrail, and other safety appurtenances have been installed. For projects that will not be opened to the traveling public, the work will be considered substantially complete when it is ready for the subsequent project. This shall not be construed as a contractual right and its application will be contingent upon the Contractor's diligence in completing the remaining items of work.

108-1.09 TERMINATION OF WORK FOR DEPARTMENT'S CONVENIENCE. Delete the second sentence of the fourth paragraph and substitute the following Payment for partially completed work will be made at actual costs incurred plus a reasonable profit.

Delete the fifth and sixth paragraphs and substitute the following:

After receipt of a Notice of Termination, the Contractor shall submit to the Contracting Officer, his claim for additional costs not covered above or elsewhere in these Specifications. Such claim may include such cost items as reasonable idle equipment time, mobilization efforts, bidding and project investigative costs, overhead expenses directly allocable to the project termination and not covered under work paid for in the preceding paragraph, legal and accounting charges and other expenses reasonably necessary in claim preparation, subcontractor costs not otherwise paid for, actual idle labor costs if work is stopped in advance of termination date, guaranteed payments for private land usage as part of the original Contract, and any other costs for which the Contractor feels reimbursement should be made. The intent of negotiating this claim would be to reach an equitable settlement figure with the Contractor for the actual costs incurred. In no event, however, will loss of anticipated profits or consequential damages be considered as part of any settlement.

For any claim related to operating equipment owned by the Contractor, the Contractor is entitled to recover equipment costs based on the Contractor's actual costs for ownership and actual operating expenses. For any claim related to idle equipment time for equipment owned by the Contractor, the Contractor is entitled to recover equipment rates based on the Contractor's internal ownership costs. Recovery for operating equipment or idle equipment time shall not be based on published rental rates. Claims for idle equipment time following termination of the contract are limited to a maximum of 30 days, and may not include any operating expenses. In the case of rented or leased equipment, the Contractor shall recover the lesser of its actual rental costs or fair market rental costs, and the amount paid shall not exceed 30 days rental.

(2/18/99)R241

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.03 SCOPE OF PAYMENT. Delete the last sentence of the fourth paragraph.  (5/7/91)M33

Special Provisions

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primica, 1735 Technology Drive, Suite 410, San Hosea, CA, 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

(2/18/99)R14

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This retainage will be released by the Engineer upon receipt of current schedules from the Contractor. (9/21/92)R137

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: Materials shall be physically separated from the other materials stored at the storage location. Materials shall be clearly labeled with the project name and number. Materials shall be stored in accordance with the manufacturer's published recommendations. A copy of any such recommendations shall be provided to the Engineer.

Should storage conditions become unsatisfactory, any payments made for the materials will be classified as unearned. If the Contractor has not earned sufficient funds to cover the cost of a deduction on the next progress payment, a request for repayment will be sent

to the Contractor. The Contractor agrees to repay the Department within 30 days from the date of a request to refund payment when the storage conditions have become unsatisfactory. Unsatisfactory storage conditions include, but are not limited to:

1.	Storage not in accordance with the manufacturer's recommendations.

2.	Commingling or storage of other materials where any element of doubt exists as to which materials belong in which lot.

3.	Unsatisfactory labeling of materials.

4.	Any liens filed on the materials for storage or transport, or by the supplier or manufacturer of the material.

5.	Change of the storage locations without obtaining approval of the Engineer prior to the relocation.

6.	Damage to all or part of the materials by fire, theft, or other peril.

Should labor, travel, or any other costs be incurred for inspection off the limits of the project, the Contractor shall reimburse the Department for these costs.

The Contractor releases and discharges the Department from any liability arising out of, or in any way related to, the payment for materials on hand and/or to the storage or transport of these materials. The Contractor is responsible for damages or delays which may relate to the storage or transport of the materials.

(7/2/93)S64

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

Special Provisions

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 23, with the maximum opportunity to participate in the performance of contracts financed in whole or in part with federal funds. The Contractor shall not, nor shall subcontractors or others associated with this contract discriminate on the basis of race, color, national origin, or sex in the award and performance of work under this contract. The Contractor shall carry out applicable requirements of 49 CFR part 26 in the award and administration of DOT-assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 23, in compliance with the Federal Highway Administration's DBE Program guidelines and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section shall be considered a material breach of contract. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS36.30.640(4).

120-1.04 DEFINITIONS AND TERMS

1.	Broker. A DBE that arranges for the delivery or provision of creditable materials, supplies, equipment, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF). The execution of a contract or a distinct element of work or service under a contract by the DBE actually performing, controlling, managing, and supervising the work involved with its own equipment

and employees within its certified category. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the contract.

3.	Disadvantaged Business Enterprise (DBE). A firm certified by the State of Alaska, Department of Transportation and Public Facilities, in accordance with 49 CFR, Part 23, or one granted that status under the Alaska Native Claims Settlement Act, 1991 Amendments and certified by the Department for participation in the Department's DBE program.

4.	Good Faith Efforts. The affirmative action measures that shall be taken by a contractor to meet the DBE Program objectives and goals for this project.

5.	Manufacturer. A DBE certified in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

6.	Original DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the contract bid schedule before approval of the Revised DBE Utilization Goal.

7.	Regular Dealer. A DBE certified in a supply category that

a.	maintains an in-house inventory on a regular basis of the particular product provided to this project,

b.	keeps an inventory in an amount appropriate for the type of work using that product, and

c.	offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the

season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis.

8.	Revised DBE Utilization Goal. The DBE Utilization as submitted by the contractor and approved by the Department for this project on Form 25A325C. The Revised DBE

Utilization Goal may be equal to, greater than, or less than the Original DBE Utilization Goal, if approved. Once approved, this Revised goal becomes the minimum required DBE participation during the execution of the contract.

120-2.01 UTILIZATION GOAL. The Original DBE Utilization Goal for this contract is shown on the Bid Schedule as a percentage of the total basic bid amount. In order for the work of the DBE to be credited towards meeting the Original DBE Utilization Goal at time of contract award, the DBE must be certified by the Department in a category covering the CUF to be performed at the time of listing on the "DBE Utilization Report" (Form 25A325C).

A bidder shall demonstrate the ability to meet the Original DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this contract.

120-3.01 DETERMINATION OF COMPLIANCE

1.	Phase I - Bid and Award. In addition to bid submission requirements, the apparent low bidder shall demonstrate DBE responsibility prior to award of this contract by:

a.	Submitting, within 15 days of receipt of the notice of intent to award, a copy of the DBE Utilization Report (Form 25A325C) listing the certified DBEs to be used to meet the goal.

b.	If the contractor submits less DBE utilization on Form 25A325C than is required to meet the Original DBE Utilization Goal, documentation of Good Faith Effort in the form of the Summary of Good Faith Effort

Documentation (Form 25A332A and attachments) and DBE Contact Reports (25A321A) shall be submitted. If accepted by the Department, this lower DBE utilization becomes the Revised DBE Utilization Goal.

If the bidder cannot demonstrate the ability to meet the Original DBE Utilization Goal, failure to document the minimum required Good Faith Efforts will result in the bid being declared nonresponsive.

c.	Where the bidder submits more DBE utilization on Form 25A325C than is required by the Original DBE Utilization Goal, this higher DBE utilization, if accepted by the Department, becomes the Revised DBE Utilization Goal.

2.	Phase II - Construction. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE officer.

The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE. Prior written request by the Contractor and approval from the Engineer is required for the replacement of a DBE for any reason. If DBE replacement is approved, the Contractor is obligated to replace the DBE with another DBE for the same work in order to still meet the Revised DBE Utilization Goal. If the Contractor cannot find a replacement DBE, the Contractor shall document the required Good Faith Efforts stipulated in Subsection 120-3.02 for the items of work to have been performed by the replaced DBE in order to have the Revised DBE Utilization Goal reduced.

120-3.02 GOOD FAITH EFFORT. The Contracting Officer will use all of the following criteria to judge if the bidder, who has not met the Original DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract. Failure by the Contractor to perform and document any of the following actions 1-7 constitutes insufficient Good Faith Effort.

1.	Consideration of all subcontractable items. The Contractor shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department prior to bid opening (see Form 25A324).

2.	Selection of the most appropriate items or portions of items to be performed by DBEs in order to increase the likelihood of achieving the stated goal.

3.	Notification at least 10 calendar days prior to bid opening to all DBEs listed in the Department's most current DBE Directory certified to perform those work items identified in Form 25A324 of the bidder's/Contractor's interest in securing the DBE's participation in the execution of the work. Each contact with the DBE shall be logged on a "Contact Report" (Form 25A321A).

4.	Request for DBE participation on specific items of work or services. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote shall be deemed non-competitive, provided the DBE and non-DBE quotes are for the exact same work or service. Where the Contractor rejects a DBE quote as being non-competitive under this condition, the work performed and payments received by the non-DBE during the execution of the contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

5.	Provision of assistance to DBEs who need help in obtaining bonding or insurance required by the bidder.

6.	Providing prospective DBEs with adequate information about the requirements of the contract regarding the specific item of work or service sought from the DBE.

7.	Follow-up of initial solicitations for interest by contacting DBEs to determine with certainty whether or not they were interested in bidding. Documentation of follow-up contacts shall be logged on the "Contact Report" (Form 25A321A).

Items 4. through 7. will be utilized to evaluate any request from the Contractor for a reduction in the Revised DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF). Measurement of attainment of the Revised DBE Utilization Goal shall be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section.

CUF is limited to that of a:

a.	regular dealer,

b.	manufacturer,

c.	broker,

d.	subcontractor

e.	joint-venture, or

f.	prime contractor.

In order for the CUF work of the DBE to be credited toward the goal, the Contractor shall ensure that all of the following requirements are met:

1.	The DBE shall be certified in the appropriate category at the time of:

a.	the Engineer's approval of the DBE subcontract; and

b. 	the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

2.	The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

3.	A DBE trucking firm certified and performing work in a transportation/hauling category is restricted within that category to the CUF of a broker. (This does not effect the CUF of that same firm, when performing work as a subcontractor and certified in another category such as embankment or excavation which could include the hauling of materials for that work.)

4.	The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

5.	Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the Revised DBE Utilization Goal.

6.	Should the DBE be decertified between the time of contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm shall not be credited toward the Revised DBE Utilization Goal. The Contractor must still meet the Revised DBE Utilization Goal by either:

a.	Withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, items 4-7) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01, or

b.	Continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out and DBEs in an amount to meet the Revised DBE Utilization Goal through either

1)	subcontractor substitution (Subsection 103-1.01),

2)	increasing the participation of other DBEs on the project,

3)	documenting Good Faith Efforts (Subsection 120-3.02, items 4-7),

4)	or by a combination of the above.

7.	The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the Revised DBE Utilization Goal.

8.	The Engineer shall consider the following criteria when determining what CUF is being performed by the DBE:

a.	The work performed shall be necessary and useful work required for the execution of the contract.

b.	The scope of work shall be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

c.	The work shall be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE, with the exception allowed under (d) below. Either the DBE owner or an on-site DBE representative, DBE superintendent, or DBE foreman shall be responsible for the work at the site. All such DBE representatives must be designated as a key employee in the DBE's certification records with the Department prior to DBE subcontract award.

d.	The DBE shall use their own employees and equipment for the execution of the work. An exception to this requirement may be permitted where the DBE must perform a specialty task or where the work is in a remote area. In such instance, the DBE may temporarily augment its project workforce with another contractor's equipment and employees (not to include supervision) in order to perform the   work, if the Department considers this normal practice performed by non-DBE contractors, within the Alaskan construction industry.

On any project, this practice shall not involve more than 33.3% of the DBE's subcontract value. Also, the Contractor shall submit a request in writing from the DBE and secure the Department's approval for such arrangement prior to commencement of the DBE's subcontract work involved. Exclusive of this arrangement, the DBE's project work force shall be regular DBE employees.

In all instances, the DBE shall be responsible for its payroll and labor compliance requirements concerning all workers under its control. DBE leases and payments for equipment must be documented; Contractor withholding or retainage for DBE labor and equipment usage is not permissible. Two-party checks to individuals are not permissible.

e.	The manner in which the work is sublet or performed shall conform to standard, statewide industry practice within Alaska, as defined by the Department. The work or provision of goods or services shall have a market outside of the DBE program (must be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed a superfluous step in the contracting or purchasing process and no DBE credit will be allowed.

There shall be no DBE credit for lower-tier non-DBE subcontract work, unless the Department defines this lower-tier subcontracting as standard, statewide industry practice within Alaska.

f.	The cost of the goods and services shall be reasonable and competitive with the cost of these goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

g.	All subcontract work, with the exception of truck hauling, shall be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

h.	The prime contractor shall not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

I. 	Credit will not be allowed for payments made by the Contractor to others on behalf of the DBE.

Two-party checks may be issued by the Contractor on an occasional basis to the DBE and another business for work or services performed under the contract; however, the Engineer shall be notified in writing in advance. DBE credit will not be given for these two-party payments, if issued on a routine basis or issued to an extent greater than that offered by the prime to non-DBEs on the project.

j.	A DBE trucking firm certified and performing work in the transportation/hauling category shall have a supervisor on-site at all times in charge of the dispatching of trucks and the hauling of materials before any DBE credit may be credited. The DBE supervisor must be regularly employed by the DBE and designated as a key employee in the DBE's certification records with the Department prior to prime contract award.

9.	The Contractor shall provide proof (canceled checks or bank statements that identify payor, payee, and amount of transfer) of the actual monies paid for the qualifying work, goods and services provided by DBEs.

10.	If the quantity of work of a bid item which involves a DBE is reduced by the Department, the Original and Revised DBE Utilization Goals on Form 25A325C are reduced proportionately.

120-3.04 DEFAULT OF DBE. In the event that a DBE who has been placed under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default. The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the Revised DBE Utilization Goal if, in the opinion of the Engineer, both of the following criteria have been met:

1.	The Contractor had no fault or negligence in the default and that the circumstances surrounding the default were beyond the control of the Contractor.

2.	The Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with items 4 through 7 of Subsection 120-3.02 GOOD FAITH EFFORT for the defaulted work.

The Revised DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor shall be entitled to count toward the Revised DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

1.	Credit for work performed by a DBE prime contractor is 100%, not to exceed the Original DBE Utilization Goal.

2.	Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials.

3.	Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

4.	Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

5.	Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the procurement contract for the creditable item.

6.	Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the cost of the hauling subcontract.

7.	Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee shall not exceed 5% of the premium cost.

8.	Credit for the CUF of a joint venture (JV) (either as the prime contractor or a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner shall be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Meeting the Revised DBE Utilization Goal will be considered subsidiary to other items of work and no separate payment will be made.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, retainage may be withheld from progress payments. The retainage shall be sufficient to assure funds are available to cover the cost of the disincentive or potential disincentive.

If the Contractor fails to meet the Revised DBE Utilization Goal, payments will be reduced as a disincentive. The amount of the disincentive shall be equal to 50% of the difference between the Revised DBE Utilization Goal expressed in dollars and the total creditable DBE participation as determined by the Engineer.

If and only after the Original DBE Utilization Goal established on Form 25A325C in terms of dollars has been met, the Contractor may be eligible for an incentive payment based upon the following calculation:

10% of the total dollar amount of CUT work performed by DBE subcontractors not needed in the calculation to meet the Original DBE Utilization Goal; except that the total incentive paid to the Contractor will not exceed 2% of the total basic bid amount at time of original contract award or $100,000, whichever is less.

Payment of the incentive will be made on the final estimate. The disincentive will be withheld in the form of retainage during the course of the project. If sufficient retainage has not been withheld to cover the cost of the disincentive, the Contractor shall remit same to the Department within 30 days of being billed for the amount due.

A Change Order is not required for DBE Adjustment. The Notice To Proceed shall constitute the notice required to initiate DBE Adjustment.

Payment or Deduction will be made under:

Pay Item No.	Pay Item	Pay Unit

120(1)	DBE Adjustment	Contingent Sum

Add the following special provision:

SECTION 406

RUMBLE STRIPS

406-1.01 DESCRIPTION.  This work includes furnishing and placing milled-in shoulder and center rumble strips, lane line rumble skips, and turn lane rumble strips at the locations indicated in the contract documents and to the width, depth and length required by the contract documents or as directed by the Engineer.

406-2.01 MILLING EQUIPMENT.  The equipment shall consist of a rotary type cutting head, designed specifically for milling in rumble strips, with a maximum outside diameter of 24 inches and will be a minimum of 16 inches long.  The cutting head shall have the cutting tips arranged in such pattern as to provide a relatively smooth cut (approximately 1/16 inch between peaks and valleys).  The equipment shall have a variable length cutting drum to produce 12 inch or 16 inch wide cuts as shown on the plans.

The cutting tool shall be equipped with guides or a guidance system, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

The cutting head(s) shall be on its own suspension system, independent from that of the power unit, to allow the head to align itself with the slope of the shoulder and/or any irregularities in the shoulder surface.

The manufacturer of the milling equipment shall provide training for operators and shall be present on-site during the installation of the four rumble strip test sections specified in Section 406-3.01.

406-3.01 CONSTRUCTION REQUIREMENTS.

Surface Preparation

Roadways receiving rumble strips shall be prepared by sweeping all loose materials from the roadway shoulder and/or centerline prior to milling operations, as directed by the Engineer, to provide a smooth clean surface for the operation of the milling equipment.  This sweeping shall be measured and paid for under Item 643(27) Street Sweeping.

Roadway Striping Re-establishment

Roadway striping location including centerline, shoulder, lane line, and turn lane striping shall be re-established by the Contractor prior to milling, when necessary, to provide guidance for the rumble strip installation operation.  Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping.  Maintain the same lane widths that exist upstream or downstream of the missing striping.  Provide sufficient location marking or “rabbit tracks” to insure an accurate milling operation.  Full restriping of the roadway is not required.  Re-establishing roadway striping location will not be measured or paid for separately but will be subsidiary to the respective rumble strip pay items.

Rumble Strip Test Section

Install an initial 500 foot test section of each of the following rumble strip types:

1.	Shoulder Rumble Strips

2.	Centerline Rumble Strips

3.	Lane Line Rumble Skips

4.	Turn Lane Rumble Strips

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip and surface inside each depression without damaging the remaining asphalt pavement.  If any of the initial 500 foot test sections are not acceptable to the Engineer, provide new equipment, new method, or make necessary adjustments and retest.  These additional test sections will be required before production runs will be allowed to commence.

If during production any of the work becomes unacceptable, the Engineer may require resumption of more test sections.

Rumble Strip Installation

Install the following four types of rumble strips at the locations shown in the contract documents:

1.	Shoulder Rumble Strips

2.	Centerline Rumble Strips

3.	Lane Line Rumble Skips

4.	Turn Lane Rumble Strips

Mill or grind each type of rumble strip to the dimensions shown on the plans.  The alignment of the edge of the ground pattern will be randomly checked.  Locate the inside edge of the rumble strips as shown on the plans.  Pavement surfaces damaged as a result of improper rumble strip installation shall be ground and resurfaced to the satisfaction of the Engineer at the Contractors expense.  Re-cut any rumble strip that is improperly installed.

Tolerances for Rumble Strips

The Contractor shall keep his work within the following allowable tolerances:

Length of Rumble Strip.  The finished rumble strip depression shall not vary in length measured perpendicular to the direction of travel more than plus or minus ½ inch from the plan depression length.

Width of Rumble Strip. The finished rumble strip depression shall not vary in length measured in the direction of travel more than plus or minus ½ inch from the plan depression width.

Depth of Rumble Strip  The finished rumble strip shall depression have a uniform circular concave cross-section and shall not vary in depth from nominal plan depression depth by more than plus or minus 1/8 inch.

Rumble Strip Spacing.  The rumble strip depression spacing shall not vary measured in the direction of travel more than plus of minus ½ inch from the plan depression spacing.

Rumble Strip Alignment.  The rumble strip shall be placed relative to the roadway striping as shown on the plans and shall not vary from this position by more that plus or minus 1 inch for Shoulder and Centerline rumble strips, plus or minus 1 inch for lane line rumble skips, and plus or minus ½ inch for Turn Lane Rumble Strips.

Existing shoulder stripes and lane line strips shall remain in place and shall not be cut.  The rumble strips shall be placed along the roadway centerline according to the patterns shown in the plans.  Existing centerline stripes shall be replaced following the milling operation and shall be paid for under Section 670, Traffic Markings.

Clean Up of Millings

Milled roadway segments shall be returned to a debris-free state prior to re-opening for traffic.  Use a power broom or sweeper/vacuum to continuously remove waste material resulting from the operation.  Equipment for sweeping and disposal of millings shall meet the requirements of Section 643-3.04 Street Sweeping.  Use the following two types of sweeping for removal of millings immediately following rumble strip installation:

1.	Sweeping of Millings.

Millings may be swept off of the roadway and adjacent pathways beyond the shoulder and uniformly spread on the roadway side slopes during each day’s operations. Berming of the millings at the shoulders edge is not allowed.  Use this type of sweeping for shoulder and turn lane rumble strip installations where there is no guardrail or curb and gutter adjacent to the roadway being milled.  Millings shall not be swept across adjacent through traffic lanes.

2.	Sweeping and Disposal of Millings.

Millings shall be swept, picked up and disposed of during each day’s operations. The debris (grindings) generated from the cutting shall be picked up by use of a sweeper/vacuum or other method approved by the Engineer. The debris shall be picked up prior to opening the adjacent lane to traffic.  Use this type of sweeping for shoulder and turn lane rumble strip installations where there is guardrail or curb and gutter adjacent to the roadway being milled and for all areas receiving centerline rumble strips and lane line rumble skips.  Excess material resulting from the operation shall be removed and disposed of in a manner approved by the Engineer.

à$åååååååå35;AGMSY_3a.a.a.a.a.a.a.a.åÆ>ëæñÅc$"ÄSmallßCircle	ñTable_AåÆL!øÅ6PlainßTextPlainßText

"ö