PART 4

STANDARD MODIFICATIONS
AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SECTION 101

DEFINITIONS AND TERMS

## Standard Modification

101-1.03	DEFINITIONS.  Add the following:

Interim Work Authorization.  A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.  (06/25/99)M68

## Special Provisions

101-1.03	DEFINITIONS.  Add the following definition:

NON-FROST SUSCEPTIBLE.  Material that contains 6 percent or less passing the 0.075 mm screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm material.  (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.06	NON-RESPONSIVE BIDS.  Add the following:

8.	Failure to submit Escrow Bid Documents as required by 102-1.17.  (09/21/01)R264M98

102-1.11	ADDENDA REQUIREMENTS.  Delete this Subsection in its entirety and substitute the following:

Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by telephone.  Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents.  It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation for Bids.  No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation for Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening.  If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form.  (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

# Standard Modification

# 103-1.01	CONSIDERATION OF BIDS.  Add the following after Item 9:

In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor.  The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation.  The Contracting Officer will approve the request if it is determined to be in the best interest of the State.  (10/28/99)M84

103-1.02	AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”  (06/25/99)M69

SECTION 105

CONTROL OF WORK

### Standard Modification

105-1.02	PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).  (09/30/99)M 85

Special Provisions

105-1.06	COOPERATION WITH UTILITIES.  Add the following:

The Contractor shall request locates from all the utilities having facilities in the area.  The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital Anchorage School District ACS Alyeska Cable AT&T Alascom, Inc. Anchorage Water & Waste Water Utility Chugach Electric Association City of Wasilla DOT Street Lights, State of Alaska Enstar Natural Gas Eyecom TV/Interior Telephone GCI Communications Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association MFS Technologies, Inc. Mukluk Telephone Association Municipality of Anchorage Municipal Light & Power Phillips Petroleum ACS of the Northland

The Contractor shall call the following utilities and agencies directly for locates:

ADOT&PF Maintenance and Operations	(907) 235-5217

Kodiak Electric Association	(907) 486-7700

City of Kodiak	(907) 486-8065

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation or replacement are addressed in this Subsection.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.  The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract and/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

Shallow utilities, including underground electric, telephone, and coaxial cable, will be relocated through much of the project area.  Relocation will generally occur within the project right-of-way at a specified offset.  Work will be undertaken in phases corresponding to the phases specified in 643-3.08 for roadway reconstruction activities to minimize impacts to local residents.  The Contractor will be required to perform the following work in coordination with utilities:

	provide surveying to establish right-of-way and control for project centerlines, and provide utility staking

	complete clearing in areas requiring utility work before utility relocates begin

	provide traffic control for utility relocation work

	perform final grading and landscaping in areas affected by utility relocation

	perform grading and completion of road crossings and other areas requiring pavement or concrete

	include utility relocation work in the overall project Storm Water Pollution Prevention Plan (SWPPP)

	request and obtain locates for existing utilities

	protect utility facilities throughout the project contract performance period

The Contractor will hold weekly project meetings during construction.  The Contractor will notify each utility and invite a utility representative to attend these weekly meetings.  The Contractor will coordinate with each utility to determine how joint work among utilities affects the overall schedule of utility relocation. The utility contacts include:

UTILITY		CONTACT			TELEPHONE NO.

ACS			Pat Hutson (Kenai)		(907) 335-2328

GCI			John Burnett			(907) 486-3334

KEA			Jim Devlin			(907) 486-7735

City of Kodiak		Howard Weston		(907) 486-8065

The following specific coordination requirements are indicated for each utility:

Alaska Communications Systems (ACS)

ACS has underground facilities along the right side of Selief Lane from Mylark Lane to the end of project near Beaver Lake Parkway and has underground facilities along and crossing Lynden Way, Bonaparte Circle, and Mozart Circle.  The ACS underground facilities are generally located near underground facilities belonging to Kodiak Electric Association (KEA) and GCI. In the interval between Mylark Lane and approximate Station 10+410, only ACS facilities occur.  Most of the relocation work required for ACS will be performed using a joint trench with KEA and GCI.  In some cases ACS will require separate trenching, such as along the interval between Mylark Lane and Station 10+410 and for some crossings of Lynden Way. In all areas of relocation, ACS will have a representative on site providing inspection and field work.  In areas of joint trenching, KEA will perform trenching and conduit installation for all facilities, with individual utilities performing the installation of cable and appurtenances.

All existing facilities will remain in place and protected until cutovers to new facilities have been made.  The new facilities will be installed in phases corresponding to phases of roadway construction and will be activated as completed.  In certain cases temporary facilities such as roadway crossings may be required.  The Contractor will notify ACS 72 hours in advance of working in areas where ACS has facilities to provide ACS the opportunity to have an inspector on site during Contractor work.  Any work by the Contractor within 1 m of ACS facilities requires the Contractor to provide a support/protection plan for work around the facilities to ACS for approval.  The plan will be submitted to ACS at least seven (7) calendar days before beginning the work.

The Contractor will coordinate with ACS to determine the status of facility relocation in each area of work.

General Communications, Inc. (GCI)

GCI has underground facilities along the right side of Selief Lane from approximately Station 10+410 to Beaver Lake Parkway and along and crossing Lynden Way, Bonaparte Circle, and Mozart Circle.  GCI facilities are generally located near underground facilities belonging to ACS and KEA.  One exception is a crossing of Selief Lane near Station 10+698 where an inactive fiber optic cable crosses.  The Contractor will locate this crossing and protect the crossing during roadway construction.

GCI facilities will generally be relocated in a joint trench with KEA and ACS.  GCI will have a representative on site providing inspection and field work.  In areas of joint trenching, KEA will perform trenching and conduit installation with individual utilities performing the installation of cable and appurtenances.

All existing facilities will remain in place and protected until cutovers to new facilities have been made.  The new facilities will be installed in phases corresponding to phases of roadway construction and will be activated as completed.  In certain cases temporary facilities such as roadway crossings may be required.  The Contractor will notify GCI 72 hours in advance of working in areas where GCI has facilities to provide GCI the opportunity to have an inspector on site during Contractor work.  Any work by the Contractor within 1 m of GCI facilities requires the Contractor to provide a support/protection plan for work around the facilities to GCI for approval. The plan will be submitted to GCI at least seven (7) calendar days before beginning the work.

The Contractor will coordinate with GCI to determine the status of facility relocation in each area of work.

Kodiak Electric Association (KEA)

KEA has underground facilities along the right side of Selief Lane from approximately Station 10+410 to the end of project near Beaver Lake Parkway and along and crossing Lynden Way, Bonaparte Circle, and Mozart Circle.  KEA facilities are generally located near underground facilities belonging to ACS and GCI.  One exception is where overhead electric facilities provide lighting along and across Selief Lane.

KEA facilities will generally be relocated in a joint trench with GCI and ACS.  In areas of joint trenching, KEA will perform trenching and conduit installation with individual utilities performing the installation of cable and appurtenances.

All existing underground facilities will remain in place and protected until cutovers to new facilities have been made. The new facilities will be installed in phases corresponding to phases of roadway construction and will be activated as completed.  In certain cases temporary facilities such as roadway crossings may be required.  The Contractor will notify KEA 72 hours in advance of working in areas where KEA has facilities to provide KEA the opportunity to have an inspector on site during Contractor work.  Any work by the Contractor within 1 m of KEA facilities requires the Contractor to provide a support/protection plan for work around the facilities to KEA for approval.  This includes poles that are not designated for removal.  Each pole shall be evaluated in consultation with KEA to determine if shoring or other protection is required during roadway excavation.  The plan will also address the removal of existing lighting and poles, including coordination with KEA for protecting facilities until removal and de-energizing circuits in preparation for removal.  The plan will be submitted to KEA at least seven (7) calendar days before beginning the work.

The Contractor will coordinate with KEA to determine the status of facility relocation in each area of work.  Temporary overhead crossings for side streets will require the installation of conduit for final crossings.  KEA will install this conduit by trenching across the side streets after the Contractor reconstructs the areas.  The Contractor will provide notification to KEA 1 week before each crossing is ready for KEA’s trenching and removal of temporary overhead service.  The estimated time for relocating electric facilities follows:

Phase 1 - No work identified as part of this Subsection.

Phase 2 - Selief Lane from Beaver Lake Parkway to Lynden Way and Cul-de-Sacs: Work including temporary overhead road crossings at side streets and installation of ACS and GCI conduits will take 4 weeks to complete.

Phase 3 - Selief Lane from Lynden Way to Mylark Lane: Work including installation of ACS and GCI conduits will take 3 weeks to complete.

Phase 4 - Lynden Way: Work including installation of ACS and GCI conduits will take 1 week to complete.

City of Kodiak

The Contractor will be responsible for work on sewer and water utilities and shall reference project plans and specifications under the items of work for further requirements. In addition, the contractor shall prepare as-built drawings for all utility work that is performed for utilities.
(05/31/01)R3M98

105-1.15 PROJECT COMPLETION.  Delete the last paragraph and substitute the following: When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract.  (02/06/02)R237M98

Standard Modification

105-1.17	CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within seven (7) days, submit any Intent to Claim, in writing, within the next fourteen (14) days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request. Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.  (03/26/01)M101

Special Provisions

105-1.17	CLAIMS FOR ADJUSTMENT AND DISPUTES.  Add the following:

Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district.  (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01	Source of Supply and Quality Requirements.  Add the following:

Buy America Provision.  The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (08/31/99)S13

106-1.02	LOCAL MATERIAL SOURCES.  Add the following under Item 2, Inspection and Acceptance:

In compliance with 30CFR46.11, have the Operator of the sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) before beginning their operations in your surface mine.  Offer the training at each surface mine that will be used to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (5/1/02)R262M98

106-1.03 TESTING AND ACCEPTANCE.  Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO T 308

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

## (03/08/02) S 87

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02	PERMITS, LICENSES, AND TAXES.  Add the following:

The Contractor is eligible to receive an exemption from the City of Kodiak sales tax for locally purchased materials that will be used on the project.

Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits.  Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained.  Also, provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following:

The Department has received the following permits on the Contractor's behalf:

- Department of the Army Nationwide Permit 23

- State of Alaska Department of Fish and Game Title 16 Fish Habitat Permit

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion and Pollution Control for requirements for this permit.

107-1.11	PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following:  If the Contractor requires water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (5/29/02)R7M98

107-1.16	CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.  Add the following before the last paragraph:

Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.  (7/30/99)R170M98

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S80

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modification

108-1.01	SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4 and add the following to Item 5:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts.  (10/28/99)M70

## Special Provisions

108-1.03	PROSECUTION IN PROGRESS.  Add the following under Item 1:

Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department.  (4/22/99)R250M98

Delete Item 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals.  (01/31/02)R160M98

108-1.06	DETERMINATION AND EXTENSION OF CONTRACT TIME.  Delete the 2nd paragraph under Item 3 “Suspension and Extension of Contract Time” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.  (2/15/01)R242M98

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modification

109-1.05	COMPENSATION FOR EXTRA WORK.  Under Item 1, Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.  (5/31/00)M90

Replace subparagraphs e. and f. with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.  (02/08/01)M71

Delete Item 5. and substitute the following:

5.	Work by a Subcontractor.  The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator.  This markup will be for administrative expenses incurred in connection with the work.  No percentage will be paid on work covered under bid items in the original Contract.  No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor.  (02/08/01)M71

Special Provisions

109-1.05	COMPENSATION FOR EXTRA WORK.  Under Item 3, Equipment, change the first sentence to read:

"Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under Item 3, Equipment, add the following to the second paragraph:

The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  (1/27/00)R14

109-1.06 PROGRESS PAYMENTS.  Add the following:  Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.  (02/04/02)R137A

###### 109-1.07	PAYMENT FOR MATERIALS ON HAND.  Add the following:

The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer.  (9/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

- Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE).  An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- as been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification.  For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer.  A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report.  Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer.  At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement.  If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBEs work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- on-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

- The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06.  (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-3.01	GENERAL.  Add the following:

Cut and dispose of all trees designated for removal on the plans.  Fell trees toward the roadway centerline, in order to minimize damage to the trees that are to be left standing.  Remove and dispose of all remaining stumps, roots, and debris.  Except in areas to be excavated, backfill stump holes and other holes with suitable materials and compact in accordance with the Specifications.  All timber removed under this Section shall become the property of the Contractor.

202-3.02	MAILBOXES.  Delete this Subsection in its entirety and substitute the following:

Construct concrete mailbox unit pads where shown on the Plans.  Coordinate work activities involving existing USPS facilities with the Kodiak Postmaster, (907) 486-4721.  Provide the USPS at least 14 calendar days notice to allow them to notify postal customers, arrange temporary mail service, and remove their mailbox units from the concrete pads.  Accomplish each pad construction within 48 hours after the USPS has removed the mailbox unit and notify the Postmaster no later than 24 hours after each new pad is completed so the USPS can reinstall their mailbox units.

Grout shall conform to Subsection 701-2.03.  Joint Filler shall conform to Subsection 705-2.01.  Concrete shall conform to Section 501.

202-3.03	REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES.  Add the following after the second paragraph:

Any asbestos-containing materials removed from an excavation during performance of the Work shall be considered hazardous waste and disposed of in accordance with 18 AAC 60.450 and other applicable state and federal regulations.

Remove and dispose of inlets and sanitary sewer manholes designated for removal on the plans or as directed by the Engineer.  The Contractor has the option of abandoning in place existing water and sanitary sewer pipes.  If water and sanitary sewer pipes are abandoned in place, there will be no payment.

Remove frame and cover, dustpan, adjusting rings, and cone section or reducing slab from existing sanitary sewer manholes designated for removal on the Plans or by the Engineer.

The Engineer will physically identify items to be salvaged.  All items so designated shall be delivered to the City of Kodiak Public Works yard located in Kodiak, Alaska.  All remaining items removed but not salvaged become the property of the Contractor.  Provide a disposal site for non-salvageable materials.

Materials may be reused if they are undamaged, of satisfactory quality, meet the intent of the Plans, and are approved by the Engineer.  No materials shall be reused or reinstalled until they have been thoroughly cleaned by the Contractor and inspected by the Engineer.  (2/2/00)R18M98

202-3.05	REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:

Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.  (3/29/01)R84M98

    - METHOD OF MEASUREMENT

- Item 202(20).  By the meter, measured before removal.

- Item 202(36).  Each complete pad constructed and installed.

202-5.01	BASIS OF PAYMENT.

Add the following:

Item 202(1).  Payment also includes the removal of trees and existing mailbox pads identified on the Plans.

Item 202(5).  Payment also includes removal of service pipes as indicated on the Plans, and salvage of materials removed, their custody, preservation, storage on the right-of-way and disposal as provided.

Item 202(20).  At the contract price per unit specified.  Payment also includes removal of service pipes and key boxes as indicated on the Plans, and salvage of materials removed, their custody, preservation, storage on the right-of-way and disposal as provided.

Item 202(36).  Payment for the number of mailbox pads constructed and installed, regardless of size, thickness, or weight.  Final grading around the pad is subsidiary.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

202(20)	Removal of Water Pipe	Meter

202(36)	Mailbox Pad	Each	(2/2/00)R17M98

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01	DESCRIPTION.  Add the following:

Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer.  (9/1/89)R20

203-2.07 SHOT ROCK.  Shot rock used in the construction of the embankment shall have at least 80 percent smaller than 600 mm in diameter by weight, with no greater than 10 percent passing the 19 mm sieve by weight.  Shot rock embankment shall be free draining rock material obtained from a rock quarry by means of blasting or ripping.

203-3.01	GENERAL.  Add the following to the sixth paragraph:

Prior to obliterating the existing roadway, remove the existing pavement and dispose in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks and Curbs. (2/28/01)R177M98

Add the following:

Excavation will occur below the ground water table and below the water surface elevation of adjacent lakes.  Contractor shall provide soil stabilization methods, including the adequate control of ground and surface water infiltration during excavation to ensure the stability of soils adjacent to the work area.  This work shall be incidental to Item 203(3).

A portion of Island Lake Creek is being realigned as part of the project.  This realignment is being achieved in part by relocation of an existing 1.2m x 1.8m arch culvert.  Contractor shall have the option of replacing existing culvert identified for relocation.  If culvert is damaged during relocation, replace with new culvert of equal size and material at no additional cost to the Department.

Lateral utility services in areas of geotextile reinforced embankment will require the geotextile be cut to trench in each respective service line.  Excavate to the top of each affected geotextile layer, neatly cut the geotextile to expose a slot no wider than the required trench width, and excavate the service line trench.  Puncturing, tearing, or ripping the geotextile with any equipment will not be permitted.

203-3.02 EMBANKMENT CONSTRUCTION.  On page 88, delete the first sentence of the second paragraph, and substitute the following:  Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following:

Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.  (03/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following:  Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%. Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

    - METHOD OF MEASUREMENT.  Add the following:

- Item 203(11).  By the megagram, measured in final position.

- Item 203(15) will not be measured for payment.

203-5.01	BASIS OF PAYMENT.  Add the following:

Item 203(11).  At the contract price per unit specified, complete and in-place.

Item 203(15).  At the contract price per unit specified.  Payment includes relocating culvert shown on the Plans.  Bedding beneath the culvert, if required, and replacement of culvert are subsidiary.  Streambed realignment of Island Lake Creek and ditch linear grading associated with realignment are subsidiary to 203(3) and 610(1) and no separate payment shall be made in this Subsection.

Soil stabilization during excavation is subsidiary to other items of work.

Add the following pay items:

Pay Item No.	Pay Item	Pay Unit

203(11)	Shot Rock	Megagram

203(15)	Relocate Culvert Pipe	Lump Sum

SECTION 204

STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES

204-1.01	DESCRIPTION.  Add the following to the first paragraph:

The work also includes excavating and backfilling for the construction of sanitary sewer systems and water systems.

    - CONSTRUCTION REQUIREMENTS.  Add the following:

No greater than 100 meters of trench shall be open in advance of pipe or conduit installation unless approved by the Engineer.  There shall be no greater than 30 meters of open trench at the end of the Work day, unless approved by the Engineer.

SECTION 205

EXCAVATION, BACKFILL AND FOUNDATION FILL FOR STRUCTURES

Special Provisions

205-3.03 BACKFILL.  Add the following:  All backfill placed within 0.3 m of a structural unit shall be graded to pass the 75 mm sieve.

205-5.01 BASIS OF PAYMENT.  Add the following:  Grading and placement of material used within 0.3 m of structural units will be subsidiary to Item 203(6A) Borrow, Type A.  (7/24/95)R154M

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01	MATERIALS.  Delete the second sentence of the first paragraph and substitute the following:

The gradation of base course material shall conform to the requirements for Grading D-1.  (10/1/91)R116

301-3.01	PLACING.  Add the following:

Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  (9/1/89)R26

SECTION 401

ASPHALT CONCRETE PAVEMENT

Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials.  Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturer’s certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO
T-110 and substitute the following:  WAQTC TM 6.

401-3.14  Joints.  Delete the first paragraph and substitute the following:  Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

Delete the last paragraph.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following:  All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO T 308.”

Add the following paragraph to this Subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equidistant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, or at the end of the auger, or behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO T 308 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One 150 mm diameter core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under Item 3.:  The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT.  Add the following to the first paragraph:  No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following:  Longitudinal joint densities less than 91 percent of MSG, as defined in Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.  (10/24/02)R199M98

Add the following Section:

SECTION 511

MODULAR BLOCK RETAINING WALL

# Special Provisions

511-1.01	DESCRIPTION.

The Modular Block Retaining Walls shall be constructed at the locations shown on the plans and as provided in these specifications.  The Modular Block Retaining Walls to be constructed shall consist of a precast modular masonry product specifically engineered for the retention of earth.  The modular units shall be a gravity system and shall lock together vertically by pins.  The pins shall also be connected to geogrid reinforcement where indicated in the Plans or working drawings.

The contractor shall submit a modular block system to Engineer for approval.  The submittal for the modular block retaining walls shall include complete working drawings for the wall system in accordance with the provision in Subsection 105-1.02 of the Standard Specifications.  The Contractor shall verify the existing ground elevations and conditions at the site before preparing the final working drawings.  Said working drawings shall contain all information required for the proper construction of the system and any required revisions or additions to drainage or other facilities.  The working drawings shall be supplemented with calculations for the particular installation.  Said working drawings and calculations shall demonstrate the internal stability as well as the external stability of the modular block retaining wall and shall be signed and sealed by an Engineer who is registered as a Civil Engineer in the State of Alaska.  The Contractor shall allow the Engineer three (3) weeks to review the working drawings and calculations after a complete set of working drawings and calculations are submitted by the Contractor.

Heights, lengths, and depths of Modular Block Retaining Wall systems may vary somewhat from the Plans, but begin and end of wall locations and top of wall elevations shall not be less than those shown on the Plans.  Modular Block Retaining Walls shall be battered at 1H to 8V.

The height and length to be used for any system shall be minimum for the system that will effectively retain the earth behind the structure for the loading conditions, profile, or slope lines shown on the plans or on the approved working drawings.  In addition, if the Plans show limiting parameters for the systems, the system selected shall conform to those parameters.

The construction of the Modular Block Retaining Wall system shall conform to the details shown on the plans and shall be constructed in accordance with the manufacturer’s instructions.  The supplier shall provide technical assistance and training to the Contractor.  The Contractor shall provide evidence of prior installation experience with the specific product being used.

511-2.01	MATERIALS.

Materials furnished for the Modular Block Retaining Walls shall conform to the following:

GENERAL.  The Contractor shall make his own arrangements to purchase and/or manufacture the pre-cast modular block units, attachment devices, and all necessary components as shown on the Plans.  Materials not conforming to the Plans or specifications shall not be used without written consent from the Engineer.

- Modular Block Units.  The units shall be precast in conformance with the manufacturer’s requirements and the following additions:

- Handling, Storage and Shipping:  All units shall be handled, stored, and shipped in such a manner as to protect them from chipping, discoloration, cracks, and fractures.

- Rejection:  Units shall be rejected because of failure to meet any of the requirements specified above.  In addition, any of the following defects shall be sufficient cause for rejection.

- Defects caused by faulty casting.

- Defects indicating honeycombed or open texture concrete.

- Cracked or severely chipped units.

- Unreasonable color variation on front face of unit.

- Color:  Block color shall be brick red.  Contractor shall submit samples of colors to Engineer for approval by the Project Landscape Architect.

- Soil Reinforcing and Attachment Devices.  All reinforcing and attachment devices shall be carefully inspected to insure they are true to size and free from defects that may impair strength and durability.  The geogrid shall meet the requirements of AASHTO Standard Specifications for Highway Bridges, latest Edition, and per the modular block unit supplier’s design recommendations.

- Backfill Materials.  All backfill materials for modular block retaining walls shall conform to the requirements for Selected Material, Type A, as set forth in Subsection 703-2.07 Selected Material.

511-3.01	GENERAL REQUIREMENTS.  Excavation and preparation of the foundation shall be in conformance with Section 205, Excavation, Backfill and Foundation Fill for Structures.

Foundation Preparation.  The foundation for the modular block retaining wall structure shall be graded level for a width as shown on the Plans or shop drawings.  Prior to wall erection, the foundation backfill shall be compacted to meet the requirements of Section 301.  Any foundation soils found to be unsuitable shall be removed and replaced with backfill as per Section 205.

511-3.02	WALL ERECTION.  A field representative from the proprietary modular block wall system being used shall be available during the erection of the wall.  The Services of the representative shall be at no additional cost to the Department.

Precast masonry block units shall be placed so that their final position is battered at 1H to 8V. The masonry block units shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds.  While placing backfill material behind the first course of masonry block units, place backfill material at the front of the units.  Remove all excess backfill material from the top surface of all masonry block units prior to placement of the next course of masonry block units.

Backfill Placement.  Backfill placement shall closely follow erection of each course of masonry blocks.  Backfill shall be placed in such a manner as to avoid any damage or disturbances of the wall materials or misalignment of the facing panels.  Any wall materials which become damaged during backfill placement shall be removed and replaced at the Contractor’s expense.  Any misalignment or distortion of the masonry block units due to placement of backfill outside the limits of this specification shall be corrected by the Contractor.

Backfill shall be compacted to 95 percent of the maximum density as determined by ATM T-12 or AASHTO T 180.  The maximum lift thickness after compaction shall not exceed 200mm.  The Contractor shall decrease this lift thickness, if necessary to obtain the specified density.  Field density will be determined using ATM T-3 or T-11 by the Engineer.

Ride-on mechanical compaction equipment shall be operated no closer than 900 mm from the masonry unit back face.  Compaction within 900mm of the back face of the wall facing may be achieved by using a lightweight mechanical tamper, roller, or vibratory system.

A minimum of one density test shall be taken by the Engineer after every three levels of units are placed.  Soil tests shall be taken no closer than 900 mm from the back surface of the masonry modular block units.

At the end of each day’s operation, the Contractor shall slope the last level of backfill away from the wall to rapidly direct water runoff from the wall face.  In addition, the Contractor shall not allow surface runoff from adjacent areas to enter the wall construction site.

511-4.01	METHOD OF MEASUREMENT.  Modular Block Retaining Walls will be measured by the square meter of wall face measured along the face of the wall, and including that part of wall which is below grade as indicated on the Plans or working drawings.  Measurement shall take place prior to fill or backfill.  Measurement shall be vertical face, not parallel to batter angle.

511-5.01	BASIS OF PAYMENT.

The contract price paid per square meter of wall face for Modular Block Retaining Walls shall include full compensation for furnishing all labor, materials, tools, equipment, and incidentals and for doing all work involved in constructing the earth retaining structure; including precast masonry blocks, random backfill soil, excavation, aggregate base course leveling pad, and all parts of or appurtenances to the modular block earth reinforcement system, complete in place, as shown on the Plans and working drawings, as provided in the Standard Specifications, Standard Modifications and these Special Provisions, and as directed by the Engineer.

Payment will be made under:

Pay Item No.		Pay Item	Pay Unit

511 (3)		Modular Block Retaining Wall	Square Meter

# SECTION 603

# CULVERTS AND STORM DRAINS

Standard Modification

603-2.01	MATERIALS.  In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.  (02/08/01)M95

Special Provisions

    - GENERAL.  Add the following:

Trenching shall be used to install culverts and pipes.  Trench depth shall be at least 300 mm greater than the diameter of the pipe being installed and be no wider at the bottom than 900 mm greater than the diameter of the pipe being installed.  Install culverts and pipes in accordance with the pipe manufacturer’s recommendations.  All corrugated polyethylene pipe shall be Type S.

#### Standard Modification

603-3.03	JOINING PIPE.

- Metal Pipe.  Replace the second sentence with the following:  “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.”  (02/08/01)M95

    - METHOD OF MEASUREMENT.

Add the following:

Excavation, bedding, and backfill for culverts and storm drains shall not be measured.

603-5.01	BASIS OF PAYMENT.

Delete the second paragraph and substitute the following:

Excavation, bedding, and backfill for culverts and storm drains are subsidiary to Items 603(1) and 603(21) and no separate payment shall be made.

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-3.01	CONSTRUCTION REQUIREMENTS.  Add the following after the third sentence:

Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 25 mm concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

6.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the City of Kodiak Public Works yard.

Add the following:

When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the plans and 50 mm larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 75 mm formed hole approximately 0.6 m below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  Keep the openings functional.  This may require temporary dikes, RMC extensions, etc., as necessary.  Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-4.01	METHOD OF MEASUREMENT.  Add the following:

Frames, grates, and lids will not be measured for payment.

604-5.01	BASIS OF PAYMENT.  Add the following:  Frames, grates, and lids for Items 604(1A), 604(1B), and 604(9) are subsidiary to the drainage structure.

Delete Item 604(1) Storm Sewer Manhole and Item 604(5) Inlet and add the following new pay items:

Pay Item No.	Pay Item	Pay Unit

604(1A)	Storm Drain Manhole, Type I	Each

604(1B)	Storm Drain Manhole, Type II	Each

604(9)	Pre-cast Catch Basin	Each

604(13A)	Furnish and Install Manhole Frame	Each
and Grate

604(13B)	Furnish and Install Manhole Frame	Each
and Lid	(9/1/00)R43M98

SECTION 607

FENCES

Standard Modification

607-3.01	CONSTRUCTION REQUIREMENTS.  In the ninth paragraph, change “minimum” to “maximum”.  (06/25/99)M 73

SECTION 608

SIDEWALKS

Special Provisions

608-3.03	SIDEWALK RAMPS.  Delete this Subsection and substitute the following:

608-3.03	CURB RAMPS.  Construct curb ramps according to the details and locations shown on the Plans.

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish.  (06/11/02)R256M98

Standard Modification

    - METHOD OF MEASUREMENT.  In both the first and second paragraphs, after “finished surface” insert “, including ramps”. (06/25/99)M 74

Special Provisions

608-4.01	METHOD OF MEASUREMENT. Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp.  By each installation, complete in place, including construction of the ramp runs, flares, composite detectable warning tiles, backing curb, and landings necessary to provide a single street-level access.  (06/11/02)R256M98

608-5.01	BASIS OF PAYMENT.  Add the following:

Backing curb will be subsidiary to Item 608(6), Curb Ramp.

The composite detectable warning tiles are subsidiary to item 608(6) Curb Ramp. (06/11/02)R256M98

Delete Item 608(6), Sidewalk Ramp, and substitute the following pay item:

Pay Item No.	Pay Item	Pay Unit

608(6)	Curb Ramp	Each

SECTION 609

CURBING

Special Provisions

609-3.02	CAST-IN-PLACE CONCRETE CURBING.  Add the following to the fifth paragraph:

Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.  (2/1/00)R202M98

609-3.05	CURB RAMPS.  Delete this Subsection in its entirety.  (06/11/02)R256M98

Standard Modification

609-4.01	METHOD OF MEASUREMENT.  In the first paragraph, after “drainage structures” insert “or ramps”.  (06/25/99)M 75

Special Provisions

609-4.01	METHOD OF MEASUREMENT.  Delete the second paragraph.  (06/11/02)R256M98

609-5.01	BASIS OF PAYMENT.  Delete Pay Item 609(3), Curb Ramp.  (06/11/02)R256M98

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01	MATERIALS.  Under Item 1. delete the first sentence and substitute the following:

Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01	CONSTRUCTION REQUIREMENTS.  Delete Item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. For each sign designated for salvage on the Plans, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the City of Kodiak Public Works yard.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies.  All signs and posts at a single installation shall be considered as one unit.

615-3.02	SIGN PLACEMENT AND INSTALLATION.  Add the following:

Do not remove existing signs without authorization from the Engineer.

615-4.01	METHOD OF MEASUREMENT.  Add the following to the second paragraph:

Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01	BASIS OF PAYMENT.  Add the following:

No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.  (05/16/01)R50M98

# SECTION 618

# SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water.  Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620.  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope.  Complete slope preparation as soon as topsoil is placed on the slopes.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch and fertilizer as follows per hectare (ha).  Apply seed and mulch in one application if using the hydraulic method.  Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg 49.0 kg Total |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 - 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

The Contractor shall not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable. If this substitution is made, apply at the same application rate.

618-4.01 METHOD OF MEASUREMENT.  Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT.  The work described under Subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.  (03/05/02)R52M98

SECTION 620

TOPSOIL

# Special Provisions

620-2.01	MATERIALS.  Delete this Subsection in its entirety and substitute the following:

Topsoil shall conform to the requirements of Subsection 726-2.01.

620-4.01	METHOD OF MEASUREMENT.  Add the following:

Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.  (9/11/96)R53

Delete this Section in its entirety and substitute the following:

# SECTION 626

# SANITARY SEWER SYSTEM

626-1.01	DESCRIPTION.  This work consists of constructing, reconstructing, and testing of sanitary sewers and appurtenances as shown on the Plans or specified in this section.  This section refers to conduit used for sanitary sewers as “sewer conduit.”

626-2.01	GENERAL REQUIREMENTS.  All work in this section shall conform to:

- Specifications for Gray Iron Castings		ASTM A48

- Specification for Ductile Iron Gravity Sewer	ASTM A746

- Specification for Portland Cement		AWWA C-104/ASTM C150

- Specification for Finishing Hydrated Lime	ASTM C206

- Specification for Precast Reinforced Concrete	ASTM 478M

- Manhole Sections

- Sand for Cement Mortar		AASHTO M45

- Polyethylene Encasement for Ductile Iron Piping	AWWA C105/ANSI A21.5
for Water and Other Liquids

- Ductile-Iron and Gray-Iron Fittings for Water and	AWWA C110/ANSI A21.10

- Other Liquids

- Rubber-Gasket Joints for Ductile-Iron Pipe and	AWWA C111/ANSI A21.11
Fittings

- Ductile-Iron Pipe, Centrifugally Cast in Metal Molds	AWWA C151/ANSI A21.51
or Sand-Lined Molds, for Water or Other Liquids

626-2.02	MATERIALS.  Use materials that conform to the following:

- Concrete and Mortar.  All concrete used in the construction of sanitary sewer systems with the exception of precast manholes, manhole risers, and cones, shall conform to Section 501.  The addition of lime to mortar is not permitted.  The use of five (5) minute or fast-cure mortar is prohibited.

- Pipe. All piping shall be in accordance with the Plans conforming to the size and class shown and specified.  The use of pipe containing asbestos materials shall be prohibited.   Fittings shall be ductile iron and all bells conforming to AWWA C-104 except that so called "short body" fittings, otherwise meeting AWWA Specifications may be used. Polyethylene encasement shall be installed on all sanitary sewer mains and shall be 8-mils thick and conform to AWWA C105/ANSI A21.5.

- Joints.  Joints shall conform to the requirements of ASTM C-14 and ASTM C-443. Joints shall be of the "O" Ring type and shall be subject to the approval of the Engineer as to configuration.  All repair clamps shall be approved stainless steel clamps.

- Sanitary Sewer Services.  All sanitary sewer service connects shall be constructed with ductile iron pipe with "Tyton" joints, or approved equal.  All services with less than 1.5 meters of cover shall be insulated with 50mm of rigid board insulation in conformance with Section 635.  Connection to the main shall be made with an Inland Foundry Company IFCO 1068 saddle, or approved equal, and shall be secured with a double strap or a single stainless steel band of 63mm or more in width.  All sanitary sewer service connections 150mm and larger in diameter shall use double strap saddles and all connections 200mm and larger shall connect directly to a sanitary sewer manhole.

## CONSTRUCTION REQUIREMENTS

626-3.01	Required Clearance From Water Mains.

A minimum vertical separation distance (outside to outside of pipe) of 450mm or horizontal distance (outside to outside of pipe) of three meters shall be provided to all water mains.

626-3.02	Pipe Grade and Alignment.

Variance of individual pipe sections from established line and grade shall not be greater than those listed in Table 626-1, providing that such variance does not result in a level or reverse sloping invert.  During the progress of the Work, the Contractor shall provide instruments such as transits, levels, laser devices, and other facilities for transferring grades from offset hubs or for setting of batter boards or other construction guides from the control points and bench marks provided by the Contractor.  The Contractor shall provide qualified personnel to use such instruments and who shall have the duty and responsibility for placing and maintaining such construction guides.  The Contractor shall notify the Engineer 48 hours prior to taking measurements on newly installed sections of line and/or appurtenances for Record Documents.  If the method of transferring grades from the offset hubs to the pipe require batter boards, they shall be at least 25mm x 150mm supported on 50mm x 100mm stakes or approved metal rods and shall be placed every 8 meters.  At least three boards must be in place at any given time to facilitate checking of line and grade. Both line and grade shall be checked and recorded in a field book for each piece of pipe laid. The practice of pushing in uncompacted backfill over a section of pipe to provide a platform for transit and level alignment and grade observations shall be subject to the approval of the Engineer. If intermittent backfilling is allowed, backfilling shall be accomplished in accordance with Section 204.

TABLE 626-1

| Pipe Diameter (mm) | Allowance Tolerance (mm) |
| --- | --- |
| 200 | 9 |
| 250 | 9 |
| 300 | 9 |

626-3.03	furnish and install pipe.

Excavation, backfilling, and compaction for the furnishing and installing of all sanitary sewer conduits shall be in accordance with Section 204.  Notify the City of Kodiak Engineering Department, (907) 486-8065, at least one business day in advance of inspections of pipe bedding and pipe installation prior to backfilling.  Trenching shall be used to install sanitary sewer pipes, which applies to pipes installed in the embankment.  Trench depth shall be at least 300 mm greater than the diameter of the pipe being installed and be no wider at the bottom than 900 mm greater than the diameter of the pipe being installed.  Install pipe in accordance with the pipe manufacturer’s recommendations.  Pipe laying shall in all cases proceed upgrade with the spigot ends of the pipe pointing in the direction of the flow.  Each pipe shall be laid true to line and grade and in such a manner as to form a close concentric joint with the adjoining pipe.  The alignment of the installed pipe shall appear straight to visual observation and shall be such that a full circle of light can be seen between manholes, etc., when sighting along all points of the pipe circumference.  Each section of pipe shall be handled carefully and placed accurately; the spigot end shall be fully inserted.  Each pipe shall be joined in accordance with the pipe manufacturer’s recommended standards.  Care shall be exercised to avoid over-insertion.  Each section of pipe shall be properly supported to ensure true alignment and an invert which is smooth and free from roughness or irregularity.  At all times, when Work is not in progress, open ends of pipe and fittings shall be securely and satisfactorily closed so that no undesirable substance will enter the pipe or fittings.  Where a project outfalls into an existing sanitary sewer, construction of physical connection to the existing line shall be delayed until all upstream underground construction, including exfiltration testing, is complete and accepted unless otherwise directed by the Engineer.  Care shall be exercised during construction, flushing, and testing operations of the connecting link to assure that water or any foreign debris is not diverted into any portion of a sanitary sewer line in service or a sanitary sewer line which is not a portion of the construction project for which the Contractor is responsible.  Pipe shall not be laid when the bottom of the ditch or the sides to within 300mm above the pipe are frozen. Backfill material shall not contain frozen material.  The trench shall not be left open during freezing weather.

626-3.04	POLYETHYLENE ENCASEMENT.

The polyethylene encasement shall be installed on all sanitary sewer mains in strict conformance to the methods described in the most current editions of AWWA C105/ANSI A21.5 and the Ductile Iron Pipe Research Association's "A Guide for the Installation of Ductile Iron Pipe."

626-3.05	TESTING.

- General.  The Contractor shall clean and flush all sanitary sewer pipe installed prior to testing and final inspection.  All sanitary sewer pipe installed shall be subject to either an infiltration test or an exfiltration test.  In those areas where, in the opinion of the Engineer, the water table is high enough to subject the pipe to a satisfactory infiltration test, it is not anticipated that an exfiltration test shall be required.  In checking leakage, there will be no allowance made for external hydrostatic head.  Where in the opinion of the Engineer, the water table is not high enough to provide a satisfactory infiltration test, an exfiltration test shall be required.  The type of test (either infiltration or exfiltration) shall be determined by the Engineer.  The Contractor shall have the option of choosing only one method (air or water) of testing for each section tested.  A City of Kodiak representative shall attend each test.  Schedule each test with the Engineer and the City of Kodiak Engineering Department, (907) 486-8065 at least one business day prior to testing.  All wyes, tees, or ends of side sewer stubs and service connections shall be plugged or capped and the plug or cap shall be securely fastened to withstand the internal test pressures.  Such plugs or caps shall be readily removable and their removal shall provide a socket suitable for extending the lateral connection.  The lengths of service connections shall be included in the computations to determine the allowable leakage for the test section.

- Exfiltration Test (Using Water).  On completion of a section of sanitary sewer between manholes or otherwise, the Engineer shall require that the ends of all pipes be plugged, including service connections, and the pipe subjected to a hydrostatic pressure.  Generally all testing is to be conducted after backfilling, prior to resurfacing and after service connections are made.  A minimum head of 18 kPa above the crown at the upper end of the test section shall be maintained for a period of four (4) hours during which time it will be presumed that full absorption of the pipe body has taken place and thereafter for a further period of one (1) hour for the actual test of leakage.  During this one-hour period, the measured loss shall not exceed the rate of 190 liters per 25mm diameter per 1.6 kilometers per twenty-four (24) hours.  The above listed leakage rate shall also be applied to infiltration from ground water and infiltration or exfiltration in greater amounts will be cause for rejection of the sanitary sewer and all repairs necessary to meet these requirements and retesting shall be at the expense of the Contractor.  The maximum length of sanitary sewer for the above allowable leakage test shall be 300 meters. If it is not apparent that leakage test results between any two (2) manholes is satisfactory, then the Engineer may require subsequent tests to establish the more exact location of the leakage areas.  Any section of sanitary sewer between any two (2) manholes that does not meet the above requirements shall be rejected and the Contractor, at his expense, shall make the necessary repairs to the sanitary sewer to meet the requirements, and shall make subsequent tests after repairs to assure compliance with this Section.

- Exfiltration Test (Using Air).  The Contractor shall furnish all facilities and personnel for conducting the test under the observation of the Engineer.  The equipment and personnel shall be subject to the approval of the Engineer.  Joints only may be tested in pipe 900mm in diameter or larger, at the option of the Contractor.  The Contractor may desire to make an air test prior to backfilling for his own purpose.  However, the acceptance air test shall be made after backfilling has been completed, and compacted.  Immediately following the pipe cleaning, the pipe installation shall be tested with low-pressure air.  Air shall be slowly supplied to the plugged pipe installation until the internal air pressure reaches 27 kPa greater than the average greatest back pressure of any ground water surrounding the pipe.  At least two (2) minutes shall be allowed for temperature stabilization before proceeding further.  The pipeline shall be considered acceptable when tested at an average pressure of 27 kPa greater than the average greatest back pressure of any ground water surrounding the pipe, if:

- The total rate of air loss from any section tested in its entirety between manholes does not exceed 50 liters per minute, or Table 626-2 may be utilized as a guideline for a satisfactory test by air for pipe sizes shown:

TABLE 626-2

| Pipe Diameter (mm) | Allowable Pressure Drop in 10 min. (kPa) |
| --- | --- |
| 200 | 186 |
| 250 | 145 |
| 300 | 124 |

Pressure gauges shall be incremented in not more than 2 kPa increments for accurate tests.  If the pipe installation fails to meet test requirements, the Contractor shall determine at his own expense the source or sources of leakage, and he shall repair (if the extent and type of repairs proposed by the Contractor are acceptable to the Engineer), or replace all defective materials or workmanship.  The completed pipe installation shall meet the requirements of this test or the alternative water exfiltration test before being considered acceptable.  Safety braces shall be required to hold plugs in place and to prevent the sudden release of the compressed air.  Due to the large forces that could be exerted by an escaping plug during the testing of the pipe, workmen shall not be allowed in the manholes in which plugs have been placed while tests are being conducted.  The Contractor's testing equipment shall be arranged in such a manner that a pressure relief device will prohibit the pressure in the pipeline from exceeding 69 kPa.

- Infiltration Test.  Infiltration testing may be allowed at the Engineer's option when the natural ground water table is 1.8 meters above the crown of the higher end of the test section.  The maximum allowable limit for infiltration shall not exceed the rate of 190 liters per 25mm diameter per 1.6 kilometers per twenty-four (24) hours.  The Contractor shall furnish all tools, equipment, and labor necessary to complete the tests and shall verify from his own observations, or preliminary tests, that each line conforms with this Specification before requesting the Engineer to observe and record the actual leakage.  The Engineer may require the Contractor to repair obvious leaks even though the total length of the test section falls within the maximum allowable leakage for the length tested.

- Check of Line and Grade.  After backfilling and cleaning, but before final acceptance, the City of Kodiak shall check all sections of installed conduit for line and grade via in-pipe videocamera surveillance.  Excluding service connections, all size sanitary sewer mains 750 mm and smaller in diameter shall be checked for line and grade by closed circuit television.  A full circle of light must be seen and no pipe misplaced in line or grade.  Any excess deviation in line and grade shall be corrected at the Contractor’s expense prior to Final Acceptance of the Project.  Notify the City of Kodiak Engineering Department (907) 486-8065, a minimum of seven (7) calendar days in advance of requested line and grade check.

626-3.06	CONNECTIONS TO EXISTING SANITARY SEWER MANHOLES.

Excavation, backfilling, and compaction for connections to existing manholes shall be in accordance with Section 204.  Connection to existing manholes shall be made in a workmanlike manner, shall be tight and have smooth flow surfaces and curves. The invert shall be brought into the existing manhole at the elevation shown on the Plans.  An expanding type grout (Jet Set or approved equal) shall be used in connecting sewer pipe to the existing manhole.  The downstream pipe in manholes shall be screened to prevent entry of mortar or other debris from entering the system.  Where a connection is made to an existing sanitary sewer manhole, the base shall be broken out if necessary to form a smooth channel in accordance with Section 604.  Connections to existing sanitary sewer manholes will be allowed only after all portions of the Contractor's Work tributary to the connection point have been cleaned, flushed, inspected and satisfactorily tested.  Under certain conditions, connections prior to the completion of the system may be permitted subject to the Engineer's prior written approval and the provision of suitable and adequate debris sand traps and sumps upstream from the connection.  If the connection to existing manhole occurs near the existing ladder rungs of the existing manhole, the Contractor shall remove the existing ladder rungs and install new ladder rungs so that the ladder rungs are not above a pipe penetration.  Alternatively, the Contractor may rotate the barrel sections and cone section of the manhole rather than removing old ladder rungs and installing new ladder rungs.

626-3.07	SANITARY SEWER SERVICE CONNECTIONS.

Excavation, backfilling, and compaction for furnishing and installing sanitary sewer service connections shall be in accordance with Section 204.  Notify the City of Kodiak Engineering Department, (907) 486-8065, at least one business day in advance of inspections of each sanitary sewer service line and associated appurtenances prior to backfilling.  The service connections shall be bedded with non-frost susceptible material, with a fine granular texture and containing no material larger than 13 mm.  Bedding shall be placed the full extent of ditch and up to the spring line of the service pipe.  Multiple connections shall not be made any closer together than one meter.  Diameter of all sanitary services shall match existing service size or be 100 mm, whichever is greater.  Taps, where allowed for installation of saddles on to sewer pipes, shall be made with a mechanical hole cutter as manufactured by the Pilot Manufacturing Company or approved equal.  Tee and wye saddles will be allowed on mains 300 mm and larger; wye saddles will be the only saddles allowed on mains smaller than 300 mm.  Saddles shall be placed over a circular hole sawed 3 mm larger than the inside diameter of the saddle.  The strap(s) shall be tightened in accordance with the manufacturer's instructions and centered over the hole sawed in the pipe being tapped.  The hole shall be made above the spring line of the main being tapped.  Sanitary sewer service connections to undeveloped parcels shall be installed to the edge of right-of-way or edge of permanent sanitary sewer easement of the lot being served and shall be capped, backfilled, and permanently marked by means of a 50 mm x 100 mm Carsonite (or approved equal) marker extending 600 mm above grade, painted green.  As-built measurements shall be the station of the service connection at the main plus a minimum of two ties to permanent prominent features and, when possible, ties to property corners.  As-built records shall include the pipe station of service connection at the main, service length, service invert elevations at the main and property line and distance to nearest property corner.  Minimum slopes for sanitary sewer services shall conform to Table 626-3.

## TABLE 626-3

| Pipe Diameter (mm) | Maximum Slope (percent) |
| --- | --- |
| 100 | 2.08 |
| 150 | 1.00 |
| 200 | 0.40 |

Upon exposing an existing on-property stub-out for connection, the Contractor is required to insure that the line is free and clear of obstructions prior to connection with the new sanitary sewer service line.  If the new service line is found to be either plugged or to have reverse grade, the Contractor is required to notify the Engineer immediately and be liable for correcting the misalignment or unplugging the line at his expense.  At the point of tie-in if no-hub pipe is exposed, a "Romac repair clamp" SC-1-450 or approved equal shall be used to connect to the on-property service line.  If a "Ty-seal" hub is utilized, the use of a "Romac repair clamp" or equal is not required.  When using a bend at the point of tie-in, two "Romac repair clamps" or approved equal shall be used.  An Inspector for the City of Kodiak shall be present when initial connection or service line installation is made to the main line, without exception.  The Engineer will not approve any installation which is not in accordance with the Uniform Plumbing Code, this Section, and City of Kodiak Standard Specifications.

626-3.08	UNINTERRUPTED SANITARY SEWER SERVICE.

- General.  The Work under this Subsection consists of providing all planning, coordination, and operations pertaining to the bypass pumping of sewer flows around those portions of the sewage facilities to be rehabilitated or replaced.  It shall be the Contractor’s responsibility to maintain uninterrupted sanitary sewer service to all residents within and adjacent to the work area.  Interruptions of up to four hours will be permitted at individual sewer service lines after 48 hours notice has been given to affected residents.  Sanitary service to any given structure shall not be interrupted more than once in a 24 hour period.  Existing flows include those from any upstream collection system components that contribute to the project sewer mains or manhole facilities.

- Performance.  Complete, temporary pumping systems capable of accommodating the peak wastewater flow of 380 liters per minute and able to pass 75mm solids shall be provided to ensure uninterrupted sewer service.  The Contractor is cautioned that the estimated wastewater flows do not include contributions from any infiltration or inflow that may exist at the time of Work.  The Contractor’s pumping system capacity shall make appropriate allowances for such additional flows.  Suction lines and surface bypass piping shall be butt-fused, high density polyethylene (HDPE).

- Requirements.  Prior to any disruptions to sanitary sewer service, the Contractor shall submit a sewage bypass plan to Engineer for approval, detailing the scheduled deployment of pumps, pipes, hoses, and other equipment necessary to maintain continuous sewer service during construction.  At a minimum the bypass plan shall include the proposed pump, pump placement, and layout of suction, surface bypass, and discharge piping.

Prior to construction, and no later than the pre-construction conference, the Contractor shall submit the method to be used in the maintenance of existing sewage flows during construction.  The Engineer shall review and approve, in writing, the method for sewage bypass as submitted by the Contractor.  If, in the opinion of the Engineer, the Contractor’s method does not meet current construction standards and practices, the Contractor shall resubmit his method and receive written approval by the Engineer prior to construction.

The Contractor shall ensure that all flows are properly accommodated.  The pumping system shall be such that the hydraulic gradient both upstream and downstream of the piping being bypassed will not reach elevations that will cause damage to the properties being served.  This will require close attention to the elevation of the upstream head needed to actuate the pumping cycle and the rate of discharge flow from the pumps.  The Contractor shall be liable for all damages which result from sewage flows not being properly maintained during the progress of the work, including all damages to private property which occur as a direct or indirect result of inadequate control of wastewater flows.  The Contractor is reminded that if a noise permit is required for after-hours pumping and the permit is unattainable for certain locations, such lack of attainability shall not be cause for claim for additional compensation or time extension.

Under no circumstances shall the Contractor allow the discharge of sewage into a storm drain facility or directly on or in the ground.  No excavation will be permitted to facilitate this Work except that required by the Plans.  The installation and maintenance of portable sanitary sewer facilities (portable toilets) shall be in place for the duration of service interruptions and shall consist of (1) toilet per two (2) residences (housing units) alternating on each side of the street.  These units shall include hand sanitation devices, shall be properly vented, stocked, cleaned as necessary, or as determined by the Engineer, and overall maintained in a clean working order.

626-4.01	METHOD OF MEASUREMENT.

- Item 626(1).  By the meter, for the diameter specified, along the horizontal projection of the conduit from center to center of manholes.

- Item 626(14).  By each connection to an existing sanitary sewer manhole.

- Item 626(15).  By the number of sewer services installed, for the diameter specified, including connection to the main and reconnection to the existing on-property service line.

- Item 626(16).  Item 626(16) will not be measured for payment.

- Excavation, bedding, backfill, and testing for work required in this Section shall not be measured.

    - BASIS OF PAYMENT.  At the contract unit price per unit of measurement for the pay items listed below that appear on the bid schedule.

- Item 626(1).  Excavation, bedding, polyethylene encasement, backfill, and testing are subsidiary to Item 626(1) and no separate payment shall be made.

- Item 626(15).  All materials, excavation, installation, compaction, backfill, and insulation are subsidiary to this Item.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

626 (1-200) 	Sanitary Sewer Conduit,		Lump Sum
	200 mm Ductile Iron, Class 50

626 (1-250) 	Sanitary Sewer Conduit		Meter
	250 mm Ductile Iron, Class 50

626 (14)	Connection to Existing Sanitary Sewer 	Each
	Manhole

626 (15-100) 	Sanitary Sewer Service Connection,		Each
	100 mm

626 (15-150) 	Sanitary Sewer Service Connection,		Each
	150 mm

626 (15-200) 	Sanitary Sewer Service Connection,		Each
	200 mm

626 (16) 	Uninterrupted Sanitary Sewer Service	Lump Sum

Delete this Section in its entirety and substitute the following:

# SECTION 627

# WATER SYSTEM

627-1.01	DESCRIPTION.  This work consists of furnishing, placing, testing, and disinfecting water mains and appurtenances as shown on the Plans or specified in this Section.  The work also includes furnishing and installing water fittings, straps, restrained joints and/or restraining system for fittings, valves, and piping deflection points and also removing and replacing existing fire hydrants, valves, valve boxes, and water service connections.  Dimensions for fire hydrant fittings shown on the Plans and Specifications and other water system accessories are soft metric conversions.  Submit product data to the Engineer for approval prior to installation.

627-2.01	GENERAL REQUIREMENTS.  All work in this section shall be in accordance with the most recent revision of the following standards of the American Society for Testing and Materials (ASTM) and the American Water Works Association (AWWA):

- Specification for Gray Iron Castings for Valves,	ASTM A126
Flanges, and Pipe Fittings

- Specification for Seamless Copper Water Tubing	ASTM B88M

- Polyethylene Encasement for Ductile Iron Piping	AWWA C105/ANSI A21.5
for Water and Other Liquids

- Ductile-Iron and Gray-Iron Fittings for Water and	AWWA C110/ANSI A21.10
Other Liquids

- Rubber-Gasket Joints for Ductile-Iron Pipe and	AWWA C111/ANSI A21.11
Fittings

- Flanged Ductile-Iron Pipe with Threaded Flanges	AWWA C115/ANSI A21.15

- Ductile-Iron Pipe, Centrifugally Cast in Metal Molds	AWWA C151/ANSI A21.51
or Sand-Lined Molds, for Water or Other Liquids

- Gate Valves for Water and Sewerage Systems 	AWWA C500

- Dry-Barrel Fire Hydrants		ANSI/AWWA C502

- Installation of Ductile-Iron Water Mains and Their	ANSI/AWWA C600
Appurtenances

- Disinfecting Water Mains		AWWA C651

- Underground Service Line Valves and Fittings	ANSI/AWWA C800

- Uniform Fire Code (UBC) latest edition and local amendments.

- National Fire Codes, Volume I and Volume II, 1982 Codes and Standards, National Fire Protection Association.

627-2.02	MATERIALS.  Use materials that conform to the following:

- Pipe.  Class 52 pipe shall be used for all water mains between 75 mm and 500 mm in diameter.  Type K copper shall be used on water service pipe smaller than 75 mm in diameter.  Galvanized pipe, pipe containing asbestos, and the use of lead-tipped gaskets shall not be used.  Polyethylene encasement shall be installed on all water mains and shall be 8-mils thick and conform to AWWA C105/ANSI A21.5.

- Fittings.  Fittings shall be a minimum of 1.7 MPa pressure rating, mechanical joint or all bell, lined or unlined, ductile iron, unless otherwise required by the Contract Documents.

- Continuity Straps.  Continuity straps shall be stranded or solid, rubber or plastic coated, Number 2 copper wire.

- Joint Tie Rods Thrust Restraint System. Tie rods shall be threaded black iron or mild steel and shall be located symmetrically around the perimeter of the pipe, using anchoring lugs of standard manufacture for attachment where required.  Tie rods shall be 19-mm diameter on pipes 600 mm and less in diameter.  There shall be two (2) rods on pipes 300 mm and less in diameter and four (4) rods on pipes 350 mm to 400 mm in diameter.  Tie back rods shall be supported every 8 meters using anchoring lugs of standard manufacture for attachment where required to maintain even tension.  Unless otherwise detailed on the Plans, pipe joints shall be push-on rubber gasket types conforming to AWWA C111.  Restrained joint pipe shall be EBAA Iron MEGALUG, Romac Industries GripRing, U.S. Pipe Field LOK Gasket System, or approved equal.  All restrained joint installation areas shall include joints, fittings, and piping deflection points.  The Contractor shall provide pipe manufacturer submittals, which include thrust restraint calculations prior to construction.

- Gate Valves. Gate valves shall be iron body, fully bronze mounted, double disc, parallel or resilient seat valves as manufactured in accordance with the requirements of AWWA C500 "Gate Valves for Water and Sewer Systems."  All valves shall be non-rising stem type with an O-ring seal and a 50-mm square operating nut, and shall open counterclockwise.  Valves shall be mechanical joint ends.

- Valve Boxes.  Valve boxes shall be cast iron of sliding, adjustable height type with round or oval bottom hood sections to fit over the top of the valve.  The top section shall be recessed to receive a close fitting "eared" lid with the word "water" cast into it.  Internal diameter of the smallest section shall not be less than 125 mm.  Minimum thickness of the metal shall not be less than 8 mm.  Castings shall be smooth and the workmanship shall be acceptable to the Engineer.  Valve boxes shall be of sufficient length for the pipe cover depth on the profile drawings and in accordance with the Plans

- Valve Box Markers.  Valve boxes shall be marked with markers consisting of 63 mm OD galvanized steel pipe sections, 2.1 meters in length, with one meter buried in the ground. Markers shall be shop-painted "Caterpillar Yellow" and painted with stenciled 50 mm black numerals, showing the appropriate references.  Markers shall be located on the nearest property line, due north, south, east or west of the valve at a maximum distance of 15 meters, unless otherwise directed by the Engineer.  Markers shall not be required where valve boxes are located in paved areas.  Markers shall have a notation identifying the direction and horizontal distance to the valve.

- Fire Hydrants. Fire hydrants shall conform to the requirements of ANSI/AWWA C502 for Dry Barrel Fire Hydrants.  Fire hydrants shall be single-pumper Mueller 5-1/4 Centurian (3-port) Model Number A-432, or other pre-approved Mueller model number, and have the following additional requirements:

All fire hydrants shall be supplied with a 133-mm main valve opening.

All fire hydrants shall be furnished with a 150-mm ANSI Class 125 standard mechanical-joint end with two (2) cast-on lugs for tie backs.

All connections shall be mechanical-joint unless otherwise indicated in the Contract Documents.

Single pumper hydrants shall be furnished with two (2) 63-mm hose connections and one (1) 114-mm pumper connection.

Unless otherwise required by the Contract Documents, all hydrants shall be furnished with a barrel length that will allow a minimum of two meters of bury.

The main valves shall be of the compression type, where water pressure holds the main valve closed permitting easy maintenance or repair of the entire barrel assembly from above the ground without the need of a water shutoff.

All fire hydrants shall be furnished with a breakaway flange which allows both barrel and stem to break clean upon impact from any angle.  Traffic flange design must be such that repair and replacement can be accomplished above ground.

Painting and coating shall be in accordance with cited AWWA Specifications.  After installation, the hydrant section from the traffic flange to the top of the operating nut shall be painted "Safety Orange".

Operating and nozzle nuts shall be pentagon shaped with 38 mm point to flat measurements.

Hose nozzle threading shall be in conformance with NFPA #194 for National (America) Standard Fire Hose Coupling Screw Threads.

All working parts shall be bronze or noncorrosive metal in accordance with the requirements of ANSI/AWWA C502.

All hydrants shall be right hand opening (clockwise).

All hydrants shall be self-draining.

All joints shall be restrained.  Unless otherwise detailed on the plans, pipe joints shall be push-on rubber gasket-type conforming to AWWA C111.  Where specified on the plans, restrained joint pipe shall be EBAA Iron MEGALUG, Romac Industries GripRing, U.S. Pipe Field LOK Gasket System, or approved equal.  All restrained joint installation areas shall include joints, fittings, and piping deflection points.

All tie rods must be 19-mm OD black iron or mild steel.

The contractor shall install guard posts at each hydrant where shown on the Plans, in accordance with the standard detail drawings.  If, in the opinion of the Engineer, the guard posts are not to be installed, they shall be delivered to the City of Kodiak storage yard.  Measurement and payment for guard posts shall be incidental to the Bid item "Furnish and Install Fire Hydrant Assembly."

- Water Service Lines.

General.  A service line provides potable water to a building or lot for domestic or commercial use.  Twenty-four (24) hour notification shall be given to the City of Kodiak inspector prior to making the connection available for inspection.

Pipe.  Soft drawn seamless annealed copper type "K" shall be used for all service lines smaller than 75mm in diameter.

Key Box.  The key box shall provide a clear and unobstructed access to a curb stop.  Key boxes shall be installed in the standard location as shown in the Standard Details.  Key boxes shall be of an acceptable construction as outlined in this Section and as shown in the Standard Details.  Key boxes for services stubbed to property lines for future use shall be installed with a standard location marker, which shall be a wood 50 mm x 100 mm x 2.4 meter protruding above the ground one meter, painted blue, and stenciled with the word “water” in white 50 mm high letters.

- Temporary Water System.  Temporary water system consists of the performance of all operations pertaining to the construction, installation, maintenance and removal of temporary water service during construction of this project to current City of Kodiak water utility customers in the area.  The Contractor shall maintain water service during the entire period of construction activities to all current customers in the project area.  The Contractor shall submit a plan for any temporary water systems to the State of Alaska, Department of Environmental Conservation (ADEC) for review and approval prior to beginning Work on such system.  The plan must identify the type of system, the method of construction, and the maintenance and operation procedures to be used.  The plan must identify service to each existing customer except those who agree in writing to have their service temporarily disconnected.  The Contractor shall obtain such agreement.  To be submitted with the plan are any agreements between the Contractor and property owner regarding access and use of private property.  The methods to be employed in maintaining water service are left to the Contractor.  Surface piping, trailer mounted supply systems, and so forth may all be considered as long as they comply with current ADEC health standards and requirements.  A copy of the ADEC approved plan shall be provided to the Engineer, along with copies of any agreements with property owners referenced above.  The Contractor shall also submit the name and phone number of a contact person and at least one alternate who shall be available on a 24-hour basis for repair and/or maintenance of the temporary water system.  In the event that the Contractor fails to repair and/or maintain the temporary system and the City of Kodiak is required to perform repairs and/or maintenance, all costs associated with said repairs and/or maintenance shall be deducted from the contract amount.

The Contractor shall use only those materials and equipment listed in this Subsection to supply temporary water service.  Temporary water service shall be supplied under the service criteria outlined in this Subsection.  All equipment used must be specifically designed and properly disinfected for the storage, handling, and delivery of potable water.  Service shall be supplied to each structure in the project presently served by the City of Kodiak.  The following minimum criteria shall be used for service to each structure:

172 kPa minimum, 586 kPa maximum (or existing system pressure, whichever is greater) delivery pressure measured at the connection to the structure.

Nineteen liters per minute flow at the above delivery pressure measured at the connection to the structure.  Commercial and other business structures may require higher water flows.

Potable water system and water quality shall conform to 18 AAC 80 Alaska Drinking Water Standards.

All temporary services to structures shall be valved to allow individual control of service to each structure.  Materials used for temporary water service shall conform to the requirements of the City of Kodiak standard specifications.  The temporary water service system shall be constructed from one or more of the following materials: polyvinyl chloride (PVC), high-density polyethylene (HDPE), copper, ductile iron, cast iron or galvanized steel.  The primary water feeder pipe shall be a minimum of 75mm in diameter.

## CONSTRUCTION REQUIREMENTS

627-3.01	FURNIsH AND INSTALL PIPE.

- Materials Delivery.  Pipe and appurtenances shall be handled in such a manner as to ensure delivery to the trench in a sound, undamaged condition.  Particular care shall be taken not to injure the pipe, pipe coating, or lining.  Before installation, the pipe and appurtenances shall be examined by the Engineer for defects.  The pipe shall not be strung out along the shoulders of the road for long distances if it causes inconvenience to the public.  The amount of pipe strung at the job site shall be at the discretion of the Engineer.  Rubber gaskets shall be stored in a cool, dark place to prevent damage from the direct rays of the sun and be protected from freezing temperatures or direct sunlight.

- Installation.  Excavation, backfilling, and compaction for the furnishing and installing of all water conduits shall be in accordance with Section 204.  Notify the City of Kodiak Engineering Department, (907) 486-8065, at least one business day in advance of inspections of pipe bedding and pipe installation prior to backfilling.  Installation shall be in accordance with the requirements of ANSI/AWWA C600.  Trenching shall be used to install water pipes, which applies to pipes installed in the embankment.  Trench depth shall be at least 300 mm greater than the diameter of the pipe being installed and be no wider at the bottom than 900 mm greater than the diameter of the pipe being installed.  Install pipe in accordance with the pipe manufacturer’s recommendations.  The interior of the pipe and accessories shall be thoroughly cleaned of foreign matter before being lowered into the trench.  The pipe shall be kept clean and free of debris during laying operations by plugging.  Pipe and appurtenances shall be carefully lowered into the trench by means of derrick, ropes, belt slings, or other suitable equipment.  Under no circumstances shall any of the pipe or appurtenances be dropped or dumped into the trench.  Care shall be taken to avoid abrasion of the pipe coating.  Poles used as levers or skids shall be of wood and shall have broad, flat faces to prevent damage to the pipe and coating.  The trench bottom shall be graded to provide uniform support for the pipe barrel.  Water shall be kept out of the trench by pumping, if necessary, until the jointing is completed.  When Work is not in progress, open ends of the pipe, fittings, and valves shall be securely plugged so that no trench water, earth, or other substances will enter the pipes or fittings.  Where any part of the coating or lining is damaged, the repair shall be made by the Contractor at his expense and in a manner satisfactory to the Engineer.  At a sufficient distance, prior to encountering a known obstacle or tie-in to an existing pipe, the Contractor shall expose and verify the exact location of the obstacle or pipe so that proper alignment and/or grade may be determined before the pipe sections are laid in the trench and backfilled.  The connections shall be made by using case-specific fittings to suit actual conditions.  All connections to active systems shall be made by the Contractor. Existing valves will be operated by the City of Kodiak.  Provide 48 hours notice to the City of Kodiak prior to a valve closure.  Pipe ends left for future connections shall be plugged or capped, and anchored, as shown on the Plans or as directed by the Engineer.  The Contractor shall install vertically a 2.4-meter wood post, directly over the end of pipe.  Cutting of pipe shall be done in a neat and workmanlike manner without damage to the pipe.  Concrete thrust blocks or tie back rods thrust restraint systems of the type shown on the Standard Details shall be installed where the pipeline terminates or changes alignment, utilizes a tee, cross, bend, or similar fitting.  Either poured-in-place or pre-cast thrust blocks are acceptable if the minimum base area is sufficient, as shown in the Standard Details.  Concrete for the thrust blocks shall conform to Section 501.  If the Contractor elects to use poured-in-place thrust blocks, all pipe and fittings exposed to concrete will be double-wrapped with four (4) mil polyethylene film prior to placement of the concrete.

- Alignment and Grade.  The pipe shall be so laid in the trench that after the line is completed, the bottom of the pipe conforms accurately to the grades and alignment shown on the Plans.  A maximum 60 mm deviation from design elevation and alignment will be allowed.  The pipe shall be generally straight to visual observation as determined by the Engineer.  Both line and grade shall be checked and recorded in a field book for each piece of pipe and appurtenances laid.  The Contractor shall have instruments such as a transit and level for transferring alignment and grades from offset hubs.  He also shall have in his employ a person who is qualified to use such instruments and who shall have the responsibility of placing and maintaining such construction guides.  The Contractor will furnish to the Engineer a copy of the surveyor's notes for the newly installed pipe and appurtenances.  The practice of placing backfill over a section of pipe to provide a platform for instruments shall be subject to the approval of the Engineer.   All adjustments to line and grade shall be done by scraping away or filling the earth under the body of the pipe and not by blocking or wedging up.  Deflections from a straight line or grade, as required by vertical curves, horizontal curves, or off-sets shall not exceed eighty percent (80%) of the manufacturer's recommendations.  If the alignment requires deflection in excess of the above limitations, the Contractor shall furnish special bends to provide angular deflections within the limits allowable.  Short-radius curves and closures shall be formed by shorter lengths of pipe, bevels, or fabricated special fittings

- Jointing of Metal Pipe.  The Contractor has the option of using either mechanical or push-on joints.  All joints shall conform to the requirements of ANSI/AWWA C600.  The Contractor will be required to use mechanically restrained joints and fittings on all hydrant leads.  The Engineer has the option of checking any or all mechanical joints to assure proper torque as specified by the manufacturer.  Two electrical continuity straps shall be installed on each side of a joint for pipes less than 300 mm in diameter.  Straps are to be welded to a clean, dry surface.  All welds and uncoated surfaces are to be coated with a coal tar pitch to the satisfaction of the Engineer.  Whenever flange connections are specified, the flange and fittings shall conform to the requirements of AWWA C110/ANSI A21.10 for 1.7 MPa pressure ratings.

- Flushing and Testing. Prior to any tests performed, all newly installed water facilities shall be open-bore flushed.  The Contractor, at his option, shall perform the disinfection and hydrostatic testing in any order of sequence.  The Contractor is made aware that in the event the disinfection has been performed and repairs are made on the system in order to pass the hydrostatic test, then the open-bore flush and the disinfection will be null and void and shall be repeated to the satisfaction of the Engineer after the repairs are made.  Disinfection will not be allowed until all open-bore flush pipes re removed and the water system is sealed.  Continuity tests will not be performed until all excavation has been completed and backfilled.  A City of Kodiak representative must be present for all testing and flushing.

Flushing.  All newly installed water facilities shall be open-bore flushed to remove any foreign matter.  Open-bore flushing shall be accomplished prior to hydrostatic testing and disinfection at each extremity of the main, including all stub-outs and dead ends.  The Contractor shall furnish, install, and remove all fittings and pipes necessary to perform the flushing, at no additional cost to the Department.  Under no circumstances will open-bore flushing through hydrants or reduced outlets be permitted.  It will be the Contractor's responsibility to notify the Engineer and the City of Kodiak forty-eight (48) hours in advance of any flushing operations.  The Contractor shall provide a plan for approval by the Engineer for the disposal of the discharge waters from the open-bore flush.  The governing authority shall approve discharge location.  Flushing of newly-constructed mains may be required between the hours of 1:00 a.m. and 6:00 a.m., depending upon the availability of water, as authorized by the City of Kodiak.  The City of Kodiak and the Department will not be responsible for any cost incurred by the Contractor for flushing.

Hydrostatic Testing.  A hydrostatic test will be conducted on all newly constructed water mains, fire hydrant leads, and stub-outs after open-bore flushing in accordance with the requirements of ANSI/AWWA C600 unless hereinafter modified.  A City of Kodiak representative shall attend each test.  Schedule each test with the Engineer and the City of Kodiak Engineering Department, (907) 486-8065 at least one business day prior to testing.  The Contractor, at his option, can use either a pressure test or a leakage test.  The Contractor shall furnish all necessary assistance, equipment, labor, materials, and supplies necessary to complete the test to the satisfaction of the Engineer.  The Contractor shall suitably valve-off or plug the outlet to the existing or previously-tested water main at his expense, prior to making the required hydrostatic test.  Prior to testing, all air shall be expelled from the pipe.  If permanent air vents are not located at all high points, the Contractor shall, at his expense, install corporation cocks at such points so the air can be expelled as the line is slowly filled with water.  All main valves, fire hydrant auxiliary valves, fire hydrant main valves, and plugs shall be tested.  All intermediate valves within the section being tested will be closed and reopened as directed by the Engineer during the actual test.  Only static pressure will be allowed on the opposite side of the end valves of the section being tested.  All hydrostatic testing will be performed through test copper.  Use of fire hydrant and service connections for testing will not be allowed.  The hydrostatic pressure shall be 1.0 MPa.  The duration of each hydrostatic pressure test shall be thirty (30) minutes.  After the required test pressure has been reached, the pumping will be terminated.  If the pressure remains constant for 30 minutes without the aid of a pump, that section of line will not be subject to any future hydrostatic test.  If a hydrostatic pressure test fails on any section, the Contractor has the option to perform a leakage test on that section.  The Contractor shall furnish all necessary assistance, equipment, labor, tools, materials, and supplies necessary to conduct the test.  Leakage for a newly installed main is determined by the following formula:  L = (ND (P)0.5)/4035, where: L = allowable leakage in liters per hour, N = summation of mechanical and push on joints in length of pipe tested, D = diameter of pipe in millimeters, and P = test pressure in Megapascals.  The duration of each leakage test shall be two (2) hours, and during the test the main shall be subjected to the constant test pressure as defined above.  The test pump shall be valved to ensure that constant test pressure is maintained throughout the test and all excess water returned to the supply tank.  If the pressure decreases below the required test pressure during the two (2) hour period, the preceding portion of that test will be declared void.  Cracked or defective pipe, gaskets, mechanical joints, fittings, valves, or hydrants discovered as a consequence of the hydrostatic tests shall be removed and replaced with sound material at the Contractor's expense.  The test shall then be repeated at the Contractor’s expense until the results are satisfactory.  If a scheduled test must be canceled, the Contractor shall notify the Engineer two (2) hours in advance of the scheduled time.  In the event the Engineer has not been notified of cancellation and the Contractor is not prepared for the test as scheduled, the Contractor shall reimburse the Engineer for all expenses incurred.  These will include, but not be limited to, salaries, transportation, and administrative costs.

Disinfection.  Chlorine shall be used for disinfection.  Chlorine shall be applied by one of the following methods:  (1) liquid chlorine gas-water mixture, (2) direct chlorine gas feed, or (3) calcium hypochlorite and water mixture.  Calcium hypochlorite shall be comparable to commercial products known as HTH, Perchloren, or Machochlor.  The chlorinating agent shall be applied at the beginning of the section through the test copper pipe adjacent to the feeder connection, insuring treatment of the entire line.  Under no conditions shall the chlorinating agent be introduced through a fire hydrant.  Water shall be fed slowly into the new line with chlorine applied in amounts to produce a dosage of forty (40) ppm to fifty (50) ppm.  Application of the chlorine solution shall continue until the required dosage is evident at all extremities of the newly laid line.  Chlorine gas-water mixture shall be applied by means of a solution-feed chlorinating device.  Chlorine gas shall be fed directly from a chlorine cylinder equipped with a suitable device for regulating the rate of flow and the effective diffusion of gas within the pipe.  Calcium hypochloride shall be injected or pumped into the water main.  During the chlorination process, all intermediate valves and accessories shall be operated.  Valves shall be manipulated so that the strong chlorine solution in the line being treated will not flow back into the line supplying the water.  Hydrostatic testing of a water line containing the chlorine mixture will not be allowed.  A residual of not less than five (5) ppm chlorine shall be produced in all parts of the water main and retained for a minimum period of twenty-four (24) hours, after which this residual shall be flushed from the line at its extremities until the replacement water tests are equal chemically and bacteriologically to those of the permanent source of supply.  The Contractor shall provide a plan for approval by the Engineer for disposal of chlorinated waters from the disinfection of the system.  The governing authority shall approve the discharge location.  In no instance shall a water main be chlorinated before open-bore flushing.  Table 627-1 is to be used as a guide for chlorinating mains by the calcium hypochlorite and water mixture method. The given dosage per 30 meters results in a chlorine solution of forty (40) to fifty (50) ppm.  This dosage takes into account that Contractors most frequently use granular HTH, which is sixty-five percent (65%) pure.  If another chlorinating agent is used, the dosage must be adjusted based on the associated purity.  Caution should be exercised against producing too high a concentration of chlorine in the line.

## TABLE 627-1

| Pipe Diameter (mm) | Dosage per 30 meters (g) |
| --- | --- |
| 100 | 17 |
| 150 | 38 |
| 200 | 78 |
| 250 | 122 |
| 300 | 175 |

Test and Air Vent Copper Pipe Removal.  After completion of testing, all test and air vent copper pipe shall be removed and the stop closed at the main, in the presence of the Engineer.

627-3.02	POLYETHYLENE ENCASEMENT.

The polyethylene encasement shall be installed in strict conformance to the methods described in the most current editions of AWWA C105/ANSI A21.5 and the Ductile Iron Pipe Research Association's "A Guide for the Installation of Ductile Iron Pipe."

627-3.03	FURNISH AND INSTALL VALVES.

Excavation, backfilling, and compaction for the furnishing and installing of all water valves shall be in accordance with Section 204.  Valve box components shall be plumb and centered over the operating nut.  The valve operator shall be placed on the side of the water main away from the centerline of the street or easement.  Valves shall have the interiors cleaned of all foreign matter before installation.  If the valve is at the end of the line, it shall be plugged prior to backfilling. The valve shall be inspected by the Engineer in the open and closed positions to insure that all parts are in working condition.  Provisions shall be made to restrict the soils from entering the bottom section to prevent soil infiltration into the valve box.  Wrap burlap inside bottom section under the packing gland and wrap three (3) layers of non-woven geotextile fabric around the outside of the valve and base section of the valve box and secure the fabric at the top and bottom with wire or tape.  Encase the valve box with eight (8) mil polyethylene, taped securely in place.  The Contractor shall expose all valve boxes for prefinal and final inspection.  After final inspection of the valves located in unpaved areas, sawdust shall be poured directly over the valve box lid and covered with gravel to facilitate location in the future.

627-3.04	FURNISH AND INSTALL FIRE HYDRANTS.

- General.  The Work under this Section consists of the performance of all Work required for the furnishing and installation of "L-Base" Fire Hydrant Assemblies, including the fire hydrant leg pipe, auxiliary gate valve, valve box, tie back rods, EBAA Iron MEGALUG, Romac Industries GripRing, U.S. Pipe Field LOK Gasket System, or approved equal, guard rails, and fire hydrants.

- Installation.  Excavation, backfilling, and compaction for the installation of all fire hydrants shall be in accordance with Section 204.  The Contractor shall install the hydrant assemblies in accordance with the Standard Details.  All fire hydrant legs shall be installed level.  The fire hydrant barrel shall be installed plumb.  The Contractor shall adjust fire hydrants to final grade.  The Contractor shall be responsible for access to the hydrant location and all trench excavation, dewatering, and backfill operations prior to, during, and after the fire hydrants are adjusted to final grade. The cost for coordinating and providing trenching operations are incidental to the fire hydrant installation.  Hydrants installed but not available for use shall be covered with burlap and securely tied.  In lieu of valve box markers for the auxiliary gate valves, the Contractor shall paint in 50mm black lettered stencils, the direction and distances to the nearest 30 mm the distance to the valve box on the face of the fire hydrant directly below the bonnet flange.  The method of measurement to furnish and install fire hydrants shall be as follows:

627-3.05	WATER SERVICE LINES.

- Excavation.  Excavation, backfilling, and compaction for the construction of all water service lines shall be in accordance with Section 204. Notify the City of Kodiak Engineering Department, (907) 486-8065, at least one business day in advance of inspections of each water service line and associated appurtenances prior to backfilling. Depth for water service connections will be a minimum of two meters below proposed finished grade.  Variations in depth from the depth stated above will not be grounds for additional payment.  It shall be the Contractor's responsibility to familiarize himself with the depth of water mains for the project.  The portion of the right-of-way that extends from the main to the key box (curb stop) will be excavated in such a manner that will allow the service connection to be installed horizontally (no slope).  The Contractor shall excavate for water connections in such a manner that the excavation is 90 degrees to the street line, whenever possible.  Two services shall not be installed in a single trench when separation between key boxes is greater than 3.6 meters.  The ditch shall be long enough to allow the key box to be set at the property line.  Trenches shall be of sufficient width at the bottom to allow for laying of the particular service (minimum 750 mm for single service).  Excavation of all fill materials to virgin ground is required to provide safety for workmen utilizing the trench.  The Contractor shall expose the mains to be tapped for a distance of 1.2 meters in length.  Excavation on both sides of the pipe shall be carried to the bottom of the pipe. Excess excavation below the required level shall be backfilled and compacted with sand or gravel at the Contractor's expense as directed by the Engineer.  No water service shall be within a horizontal distance of 3 meters from a sanitary sewer service, footing drain, or storm service.  The Contractor shall be responsible for, and shall bear the expenses incurred, in the event that a main should be damaged during excavation or backfilling. New mains which are damaged will be repaired to the satisfaction of the Engineer.  The Contractor shall repair at no cost to the Department any existing mains being tapped which are damaged.

- Service Connections.  A corporation stop shall be installed at a point in the service line as close to the main water supply as possible.  There shall be line pressure in the main at all times connections are being made.  All service lines 50 mm and smaller shall be constructed of seamless, soft drawn, type "K" copper.  A water service line shall not cross property lines of adjoining lots.  The key box shall be installed to the edge of the right-of-way or edge of permanent easement of the lot being served, no closer than 1.5 meters from adjoining property lines.  Most existing water service lines include a water meter.  New water services shall not be metered.  If an existing water service to remain is accidentally damaged by the Contractor, the existing meter shall be taken out of service when the service line is repaired.  Water service stubs for future use shall be marked by means of a Carsonite (or approved equal) marker extended 600 mm above grade, painted blue.  The connection shall be inspected by a City of Kodiak representative at the time the connection is made or the excavation be exposed in its entirety for his inspection.  No unions will be allowed in the right-of-way on newly constructed service lines.  As-built records shall include the pipe station of service connection at the main, service length, and distance to the nearest property corner.

- Backfill.  At such time as the Engineer may direct, but only after the service lines and appurtenances have been properly completed and inspected, the trenches and appurtenant structures shall be backfilled.  The backfilled material, free from large clods, frozen material or stones, shall be placed by the Contractor in conformance with the codes and regulations of the City of Kodiak and the Standard Details.  The Contractor shall exercise due care in backfilling to keep the key box and thaw wire plumb and in place.  In the event that the key box or thaw wire is displaced, the Contractor will be required to excavate and restore the service box and thaw wire to the proper position.  Any work necessary to restore the service box and thaw wire to the proper position will be performed at the Contractor's expense.  A thaw wire constructed to a plastic or rubber coated #2 copper wire shall be attached to the corporation stop on 25 mm connections by an approved method.  On 38 mm and 50 mm connections, the thaw wire shall be attached to the saddle on the main.

- Hydrostatic Testing.  All newly installed water mains and all new services shall be subject to a hydrostatic pressure test of 1.0 MPa pressure.  This pressure test may be performed at the same time that the hydrostatic test is performed on the new water main.  A bleeder will be installed at each service line key box and extended 300 mm above the existing ground.  The bleeder will be capped after testing is complete.  The bleeder may not be used for the on-property system and must be disconnected at the time of the on-property hook-up.

627-3.06	FIRE HYDRANT REMOVAL.

The Contractor shall remove existing fire hydrants and associated equipment at the locations shown on the Plans and deliver them to the City of Kodiak Public Works yard.  Any outage/removal of an existing fire hydrant shall be coordinated with the City of Kodiak Fire Department no less than 24 hours prior to the outage/removal.  Contract Fire Chief Andy Nault, (907) 486-8040.

627-3.07	TEMPORARY WATER SYSTEM.

The Contractor shall submit a temporary water system plan for the City of Kodiak's approval prior to installation of any temporary water facility.  The temporary water system plan shall detail the scheduled deployment of pumps, pipes, tanks, hoses, and other equipment necessary to maintain continuous water service during construction.  The plan shall also include, at a minimum, the proposed layout of temporary water facilities.  All temporary water service equipment shall be disinfected per ANSI/AWWA C652-86 Disinfection of Water Storage Facilities and ANSI/AWWA C651-86 Disinfection of Water Mains.  All bacteriological samples as required under this Section shall be done by a testing laboratory certified by the State of Alaska.  All temporary water service equipment shall be disinfected prior to connecting to a residence or business and shall be disinfected each and every time the equipment is moved or connected to another residence.  The Engineer shall be notified twenty-four (24) hours prior to the installation of any temporary water system.  The Engineer shall be present to inspect the disinfection process of any temporary water service system.  No residence or business presently serviced by the City of Kodiak public water system shall be without water for a period greater than six (6) hours in any twenty-four (24) hour period.  Each residence or business owner shall be notified seventy-two (72) hours before they are transferred on or off the temporary water system and before any other service interruption.  Prior to constructing temporary water services on private property, the contractor shall secure a written “Permission to Enter” from the property owner.  Such permission shall hold the Department, City of Kodiak, and their agents harmless for any claims resulting from damage or harm sustained due to the Contractor’s operation.  The Contractor shall also provide a copy of each “Permission to Enter” form to the Engineer.  Following the successful installation of the temporary water system, the existing water service shall be appropriately disconnected at a main shutoff valve inside the structure, at the Contractor’s expense.  The Contractor shall employ qualified personnel who are familiar with building plumbing systems shall accomplish the disconnection of the existing water service.  This work shall be performed to prevent backfeeding water through the service connection.  Fire hydrants may be used as a water source for a temporary water system subject to approval by the City of Kodiak.  In addition, the Contractor shall provide a gate valve assembly at the fire hydrant as a shutoff valve for the temporary water system.  The Contractor shall be responsible for any damage to the hydrant and temporary service piping and shall repair such damage at his sole expense.

627-4.01	METHOD OF MEASUREMENT.

- Item 627(1).  By the meter, for the diameter specified, along the horizontal projection of the conduit from center to center of valves, fittings, and grade breaks.  No deduction in length will be made for valves and fittings.

- Item 627(3).  By the number of valve boxes installed, including marker posts as required.

- Item 627(5).  By the number of fire hydrants installed, including the tee in the main, auxiliary gate valve and valve box, conduit between the fire hydrant and the main, guard posts, tie rods, thrust restraint system, and all fittings and materials required.

- Item 627(7).  By the number of fire hydrants removed and salvaged, including removal of the tee in the main, auxiliary gate valve and valve box, conduit between the fire hydrant and the main, guard posts, tie rods thrust restraint system, and all other fittings and accessories associated with the hydrant.

- Item 627(8A).  By number of water services installed, for the diameter specified.

- Item 627(8B).  By each connection to an existing water main.

- Item 627(9).  By the number of gate valves installed.

- Item 627(15).  By the number of water main valve and valve box assemblies removed.

- Item 627(27).  Item 626(27) will not be measured for payment.

- Excavation, bedding, backfill, and testing for work required in this Section shall not be measured.

627-5.01	BASIS OF PAYMENT.  At the contract unit price per unit of measurement for the pay items listed below that appear on the bid schedule.

Item 627(1).  Excavation, bedding, polyethylene encasement, backfill, and testing are subsidiary to Item 627(1) and no separate payment shall be made.

Item 627(8A).  Curb stop, key box, service pipe, connection to the main, reconnection to the existing on-property service line, materials, insulation, excavation, installation, backfill, and compaction are subsidiary to this Item.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

627 (1-200)	200-mm Ductile Iron Water Conduit,		Meter
	Class 52

627 (1-300)	300-mm Ductile Iron Water Conduit,		Meter
	Class 52

627 (3)	Install Valve Box		Each

627 (5)	Fire Hydrant Installation		Each

627 (7)	Fire Hydrant Removal		Each

627 (8A)	Water Service Connection		Each

627 (8B)	Connection to Existing Water Main		Each

627 (9-200)	Install 200mm Gate Valve		Each

627 (9-300)	Install 300mm Gate Valve		Each

627 (15)	Removal of Valve Box		Each

627 (27) 	Temporary Water System	Lump Sum

SECTION 635

INSULATION BOARD

635-4.01	METHOD OF MEASUREMENT.  Delete this Subsection in its entirety and substitute the following:

By the square meter of insulation board in its final position, including transitions, regardless of thickness, complete and accepted.

Sand blanket material is subsidiary.

635-5.01	BASIS OF PAYMENT.  Add the following pay item:

# Pay Item No.	Pay Item	Pay Unit

635(2)	Insulation Board	Square Meter

(8/23/00)R57M98

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items. (05/09/02) R58M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

639(3)	Public Approach	Each

639(4)	Driveway	Each

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modification

640-2.01	METHOD OF MEASUREMENT.  Delete Items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.  (06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01	DESCRIPTION.  This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02	DEFINITIONS.

- BMP (Best Management Practices).  A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands.  BMP include temporary or permanent structural and non-structural devices and practices.  The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan).  The general plan for control of project-related erosion and sedimentation.  The ESCP normally consists of a general narrative and a map or site plan.  It is developed by the Department and included in the project plans and specifications.  It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization.  A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional.  The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan).  The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI.  Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT.  Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit.  The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan).  The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit.  The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project.  The approved SWPPP replaces the ESCP.

641-1.03	SUBMITTALS.  Submit three (3) copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days.  Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01	STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.  Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP.  Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares.  The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private.  The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02	HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances.  (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities.  Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01	CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

- NPDES Permit number, if available, and a copy of the NOI,

- name and phone number of your local contact person, and

- location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms.  Perform all fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

- Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

- During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

- Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

- Inspection Reports.  Prepare and submit, within three (3) calendar days of each inspection, a report with the following information:

- A summary of the scope of the inspection.

- Name(s) of personnel making the inspection.

- The date of the inspection.

- Observations relating to the implementation of the SWPPP.

- Any actions taken as the result of the inspection.

- Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI.  Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

- storm event or other circumstance that threatens water quality, and

- inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection.  Detail additional emergency measures required and taken, to include additional or modified measures.  If modifications to existing measures are necessary, complete implementation within seven (7) days.

Stabilize all areas disturbed after the seeding deadline within seven (7) calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer:

- when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

- when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01	METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01	BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

- Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

- Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

- Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

- Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Erosion and Pollution Control 	Lump Sum
	Administration

641(2)	Temporary Erosion and Pollution	Contingent Sum
	Control

(08/15/01)M78

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-3.01	GENERAL.  Add the following after Item 10 on page 355:  Prior to any work on the project, stake and reference the construction centerline. Reference the existing centerline at 25 meter intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 meters and be offset 1.2 to 2.4 m from the shoulder on the right side of the roadway.  They shall show the offset distance to centerline and the station from the beginning of the project.  Ensure that the stakes are visible from the roadway by clearing as necessary.

Provide centerline and shoulder profiles extending 90 meters beyond the limits of the pavement removal and dig-out areas. The Engineer may require such adjustments to the planned roadway grades. This shall not be considered extra work. Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking or blue topping.  (11/29/02)R61M98

Add the following item after Item 10 on page 355:

11.	Measure and document the actual intersection sight distance triangles at all public intersections.  List the actual sight distance available up to 200 m.  Note locations with greater than 200 m of sight distance as “200+”.  Measure sight distance triangles as shown in Figure 1190-1 of the Highway Preconstruction Manual by setting up an instrument at the driver’s eye location.   Certify and record the results on standard “letter” sized paper and provide it to the Engineer at least 2 weeks prior to submitting shop drawings for permanent signing.  Provide an additional copy to the Regional Traffic Engineer.  (11/29/02)R269M98

12.	Necessary cross sections at retaining wall locations.  Cross section data shall be taken at 7.5-meter intervals and given to the Engineer 10 days prior to ordering retaining wall materials.  At that time, the Engineer will verify the plan quantity and make any necessary adjustments to the wall size, design, or configuration.  (05/08/00) R255M98

642-3.02	CROSS-SECTION SURVEYS.  Under the heading “The following shall be required of the Contractor,” delete Item 1 and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.  (3/31/00)R252M98

642-4.01 METHOD OF MEASUREMENT.  Add the following:  Clearing required for stake visibility shall not be measured.

642-5.01 BASIS OF PAYMENT.   Add the following:  Clearing required for stake visibility is subsidiary to Item 642(1) and no separate payment shall be made.  (11/29/02)R61M98

SECTION 643

TRAFFIC MAINTENANCE

#### Special Provisions

    - TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following: You may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6-meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.  (09/10/02) R222M98

#### Standard Modification

643-2.01 MATERIALS.  Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

- Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

- Construction Signs:  Use regulatory, guide, or construction warning signs designated in the ASDS.

- Permanent Construction Signs:  As designated on the Plans or on an approved TCP.

- Special Construction Signs:  All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

- Portable Sign Supports.  Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

- Barricades and Vertical Panels.  Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Portable Concrete Barriers.  Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

- Warning Lights.  Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums.  Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers.  Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings.  Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

- Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

- Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

- Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices.  Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions.  Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels.  Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs.  Use truck or trailer mounted portable changeable message board signs with a self-contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence.  Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

- “Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

- “Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

- “Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing.  Provide temporary sidewalk surfacing as required by an approved TCP and the following:

- Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

- Do not use unsupported 25-mm plywood longer than 750 mm.

- Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

- Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail.  Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

16.	Flagger Paddles.  Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.  (09/29/00)M91

#### Special Provisions

643-2.01	MATERIALS.  Add the following:

- Flexible Markers.  Refer to Subsection 606-2.01 Materials.  (09/10/02)R222M98

#### Standard Modification

Add the following Subsection:

643-2.02	CRASHWORTHINESS.  Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (<http://www.fhwa.dot.gov/>.)

Submit documentation of compliance to the Engineer before using devices on the project.

(09/29/00) M91

Special Provisions

643-3.01	GENERAL CONSTRUCTION REQUIREMENTS.  Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.  (09/10/02)R222M98

#### Standard Modification

643-3.02	ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

#### Special Provisions

643-3.04	TRAFFIC CONTROL DEVICES.  Add the following to 1. Embankments.:  Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.:  Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift.

Delete Item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

- Power Brooming.  The Contractor shall use a power broom capable of ejecting all loose material to the shoulder of the road.  The Contractor shall remove all loose material from all paved portions of the roadway and haul routes open to the public.  This includes sections of roadway off the project where the Contractor’s operations have deposited loose material.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05	AUTHORITY OF THE ENGINEER.  Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06	TRAFFIC PRICE ADJUSTMENT.  Add the following:  Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices.  The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full, unimpeded use by the public.  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

# TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08	CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following:

Construction on this project shall be divided into four phases as described below.  The Contractor shall perform the phases in the order given in this Subsection and shall work down station unless otherwise noted.  With the exception of Phase 1, all excavation, water, sanitary sewer, storm drainage, and embankment construction up to the top of subbase shall be completed in the active phase before beginning work in the next phase.  Permanent or temporary water and sanitary sewer services shall be provided and maintained to each parcel within the project limits at all times per Sections 626 and 627.

- Phase 1 - Selief Lane Water Improvements (“S” 10+039 to “S” 9+997)

Construct the water improvements shown on the Plans and backfill the trench in accordance with the Specifications.  The work area may be closed to through traffic.  Work shall be coordinated to allow continuous local two-way access to residences and businesses along the segment.  The Contractor shall provide no less than 24 hours notice to affected property owners prior to work adjacent to their property.

- Phase 2 - Selief Lane (“S” 11+110 to “S” 10+802), Mozart Circle (“M” 25+000 to “M” 24+904), Bonaparte Circle (“B” 35+000 to “B” 34+914)

Phase 2 limits may be closed to through traffic.  Road closures up to 50 meters in length will be allowed.  Only one road closure will be allowed at any given time per phase. Vehicular access shall be maintained where feasible to each property affected by the road closure at the end of the Work day.  Parcels where vehicular access cannot be maintained as a result of the closure shall be provided temporary parking on either side of the closure and safe pedestrian access to their property for the duration of the closure.  The Contractor shall provide no less than 24 hours notice to affected property owners prior to work adjacent to their property.

- Phase 3 - Selief Lane (“S” 10+802 to “S” 10+332)

Phase 3 limits may be closed to through traffic.  Road closures up to 50 meters in length will be allowed.  Only one road closure will be allowed at any given time per phase. Vehicular access shall be maintained where feasible to each property affected by the road closure at the end of the Work day.  Parcels where vehicular access cannot be maintained as a result of the closure shall be provided temporary parking on either side of the closure and safe pedestrian access to their property for the duration of the closure.  The Contractor shall provide no less than 24 hours notice to affected property owners prior to work adjacent to their property.

- Phase 4 - Selief Lane (“S” 10+332 to “S” 9+995), Lynden Way (“L” 45+000 to “L” 44+722)

Phase 4 limits may be closed to through traffic.  Road closures up to 50 meters in length will be allowed.  Only one road closure will be allowed at any given time per phase. Vehicular access shall be maintained where feasible to each property affected by the road closure at the end of the Work day.  Parcels where vehicular access cannot be maintained as a result of the closure shall be provided temporary parking on either side of the closure and safe pedestrian access to their property for the duration of the closure.  The Contractor shall provide no less than 24 hours notice to affected property owners prior to work adjacent to their property.

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 0.4 kilometers of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 20 minute stopped delay, 80 vehicles, or 0.8 kilometers of traffic detained, will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

The approved Traffic Control Plan shall identify detour routes and road closures.  The construction sequencing shown on the Plans is a suggestion only and is not intended to prevent the use of the Contractor’s ingenuity to arrive at an alternative construction sequencing.

The Contractor shall obtain the local school bus schedule and develop a plan to coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  The Contractor shall make every effort not to delay school buses through the construction work zone.

643-3.09	INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-3.10	PUBLIC INFORMATIONAL PROGRAM.  Add the following Subsection:

Provide a Public Information (PI) professional to accomplish the work outlined in this Subsection.  The PI person shall have a minimum of five (5) years demonstrated professional experience in performing similar informational campaigns involving multi-media, i.e. television, radio, newspaper and public presentations.  S/he shall be responsible for all aspects of this service including coordination; public interaction; preparing graphics; developing mailing lists; supplying updated information; and all labor, equipment, postage, and materials to provide this service.  Logos, reports, software, visual aids, graphics, and work products developed for this Project shall become the property of the Department, and delivered to the Engineer at the end of the work.  The PI professional's office shall be equipped with a facsimile machine.

This professional shall be responsible for the following tasks for the PI Program:

- Mail-outs.  Design and distribute three informational mail-outs/flyers each construction season, which will be approved by the Engineer.  The mail-outs shall contain most or all of the following:

a.	a brief description and map of the Project,

b.	the Contractor's anticipated construction schedule,

c.	a narrative of the possible delays to the traveling public through the Project,

d.	detailed traffic information such as intersection, lane and/or sidewalk closures, their corresponding detours, and their effective dates,

e.	locations of temporary bus stops,

d.	a description of possible impacts to abutting property accessing the Project,

f.	a listing of locations where current Project information may be obtained,

g.	date and times of Open House meeting as required by the Engineer,

h.	the Contractor's 24-hour message number and office telephone number, and

i.	the Engineer's Project office telephone number, e-mail address, and the web site address containing Project updates, schedules and general narrative information.

The last mail-out shall also contain a questionnaire to aid in preparing the final Report required under Item 5 below.

The mail-outs shall be sent to all addresses within one city block on either side of the Project corridor, and shall be addressed to both the owner of record and the current tenant.  It shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction season, and

c.	at the approximate two-thirds point of construction season.

- Weekly Notices.  Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours.  Areas of potential traffic delay shall be emphasized and alternative routes noted.  Coordinate this effort with the Engineer and the Department's NAVIGATOR Informational Program.  Telephone numbers for further information, and the date and time for the next scheduled public open house meeting shall be provided.  The Engineer will approve the Notices.  Hand-carry or fax the Notices to the local news broadcasting media, emergency services, public service organizations, and the major retailers near the Project corridor.

Notices shall also be distributed to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska State Troopers

Kodiak Police Department

Kodiak Fire Department

Kodiak School District

Kodiak Area Transit System (KATS)

Local Emergency Medical Services

US Postal Service

The Notices shall be submitted at the following times:

a.	one week prior to the beginning of construction,

b.	on Wednesday of each week during construction, and

c.	prior to any major change or disruption to traffic or local access.

Additionally, the PI professional shall notify business and residents that front the Project or scheduled road closures or of driveway, curb, or sidewalk reconstruction, or any other work affecting them.  Property owners with the work segment shall receive the Notices a minimum of one week prior to the commencement of the work within their segment. Lastly, provide daily information to those media who do non-paid public service road reports or announcements, and/or "Eye-in-the-Sky" commuter road reporting.

- Public Open House Meetings.  Prepare presentations for the Engineer's Open House Meetings, and for of each of the Community Councils which represent areas affected the this Project.  The Community Council meetings attended shall be the last regularly scheduled meetings prior to the beginning of construction.  Presentation size graphics shall be used to help explain the Project to the general public.

The PI professional shall be the Contractor's representative and spokesman, able to speak for him.  The PI professional shall be available to attend additional public meetings, up to five, as requested by the Engineer.

- Other Agency Coordination.  Coordinate with the Kodiak Area Transit System (KATS) to take advantage of programs which will help decrease traffic through this Project, such as Park-and-Ride with express bus service, Ride Share, and the car pooling program. Also coordinate any major detours and closures with emergency service providers (police, fire, and ambulance), Kodiak School District bus operators, and the U.S. Postal Service.

- Final Report.  Before Project completion, submit a Report evaluating the Public Informational Program as detailed under this Subsection. The Report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

- Project Progress Meetings.  Attend all scheduled or special Project meetings between the Contractor and the Engineer at the field office.

- Web Page.  Generate an INTERNET web site for the Project containing Project updates, schedules and general narrative information.  Add links to the Department's NAVIGATOR Home Page (www.dot.state.ak.us/navigator.html).  Update the site weekly.

643-4.01	METHOD OF MEASUREMENT.  Add the following:

Providing mail-outs, notices, and displays for open house and public meetings and providing weekly notices with updates will not be measured for payment.

Page 376, under Item 6, “Interim Pavement Markings,” delete the second paragraph.

Add the following:

No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01	BASIS OF PAYMENT.  Add the following:

Payment for this work complete and acceptable to the Engineer will be made under:

Pay Item No.	Pay Item	Pay Unit

643(31)	Public Informational Program	Lump Sum  (8/13/99)R102M98

Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET 2000 LET | Each | $3,000 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $36.00/hour.  The Engineer does not require a change order/directive for the flagging pay item.  (09/10/02)R222M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01	FIELD OFFICE.  Delete this Subsection in its entirety and substitute the following:

Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1,600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02	FIELD LABORATORY.  Delete sub-item g. on Page 380 and substitute the following:

- 1900-liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1,900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment. (9/28/00)R63M98

644-2.05 VEHICLES.  Delete first sentence in the first paragraph and substitute the following: Furnish and maintain five (5) full-size four-wheel drive pickups or sport utility vehicles for exclusive use of the Department throughout the project.  If you are working after October 1, provide studded snow tires for all the vehicles you provide for the Department’s use.

Add the following: Equip vehicles used by the Department with CB radios and yellow rotating beacons wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

You are responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The Department is responsible for damage to any vehicle caused by its own negligence during operation.

644-3.01 METHOD OF MEASUREMENT. Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made. (11/26/02)R245M98

#### Standard Modification

644-4.01 BASIS OF PAYMENT.  In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”  (06/25/99)M 81

Special Provisions

Add the following:  Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory. (9/28/00)R63M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(7)	Vehicle	Each

Add the following Section:

SECTION 645

TRAINING PROGRAM

# Special Provisions

645-1.01	DESCRIPTION.

This Training Special Provisions implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, the Contractor shall provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01	Objective.

Training and upgrading of minorities and women toward journey status is the primary objective of this program.  The Contractor shall enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provisions.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01	General.

The Contractor shall determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, the Contractor shall submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

The Contractor shall furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

The Contractor shall periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

The Contractor shall provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02	Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03	Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with Subsection 645-5.01, Basis of Payment.

645-4.01	Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01	Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of Subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

- provide the required hours of training (as shown on the approved Form 25A311),

- train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

- hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

645(1)	Training Program,	Labor Hour
		2 Trainees/Apprentices

(10/29/91)S 16

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01	SUBMITTAL OF SCHEDULE.  Delete this Subsection in its entirety and replace with the following:

Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.  The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01	REQUIREMENTS AND USE OF SCHEDULE.  Delete Item 2.  60-Day Preliminary Schedule.  (3/12/01)R261M98

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following:  The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this Subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If you fail to maintain the electrical systems as specified herein, the Engineer will adjust payments to you according to Subsection 643-3.06, Traffic Price Adjustment.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, all components are located and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you. When you work on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes

- The dates and times you began and completed your work, and the names of the crewmembers completing the work.

- The characteristics of the equipment failure or faulty operation evident before repair.

- The changes made or corrective actions taken.

- The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours when traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing. During the shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way to less than 1.8 meters.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

- For overhead signals, maintain 5.3 m to 5.8 m of clearance between the traveled way and the bottom of each signal.

- For side mounted signals, maintain 2.7 m to 3.4 m of clearance between the traveled way and the bottom of the signal.

- Align overhead signals controlling a single lane with the center of the lane.

- Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

- Check the horizontal angle to the side mounted far right signal from the center of the farthest left through lane at the stop bar. When the angle exceeds 20 degrees, move this signal to an overhead location. With two or more through lanes, center one signal head over each lane. With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane, otherwise install the relocated signal 2.4 meters to the right of the signal centered over the through lane.

- For pedestrian signals, maintain 2.1 m to 2.7 m between the traveled way and the bottom of each pedestrian signal.

- Aim all signal heads in accordance with Subsection 660-3.08, Installation Details.

When no longer required, salvage all original and Department provided equipment in accordance with the plans and Subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

660-2.01 EXCAVATING AND BACKFILLING.  Add the following to the first paragraph: Excavate trenches for installing rigid metal conduit to a depth 150 mm below the bottom of the rigid metal conduit.

In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following to the fourth paragraph:  Embed conduits between two 150 mm lifts of material that are free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS.  Delete the Pile Foundations Subsection and substitute the following:

Pile Foundations.  Install all foundations for light poles with shaft lengths less than 18 meters according to the following requirements

- Materials.  Furnish pipe piles that feature the diameter, minimum length, and wall thickness shown on the Plans.  Furnish piles that conform to ASTM A252, grade 3.  The Department will only accept seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Furnish pile cap adapters fabricated by the pole manufacturer.

- Construction Requirements.  Install the steel pipe piles open ended according to Section 505. Complete all splices and extensions in piles according to Section 505. Attach the pile cap adapter to the pipe pile with a full penetration circumferential weld.

Complete all welding shown on the Plans and as specified herein according to the Structural Welding Code -Steel, AWS D1.1-2000. At least 30 calendar days before you begin welding, submit a welding plan and mill certification reports for the pipe piles and pile caps to the Engineer for approval.  Do not begin welding until the Engineer has returned these items approved in writing.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS),

- Procedure Qualification Record (PQR),

- Welder Performance Qualification Record (WPQR),

- Visual Inspection Form,

- Report of Nondestructive Examination (NDE) of Welds, and

- The name of the Contractor’s Quality Control (QC) manager with documentation of qualifications.

Furnish all Quality Control inspection necessary to ensure the materials meet the requirements of the contract documents and workmanship meets the requirements of AWS D1.1.

- Visually inspect (VT) the entire length of each weld.

- Inspect all full penetration welds by ultrasonic NDE (UT).

Correct all deficiencies in materials and workmanship revealed by QC and Quality Assurance (QA) inspections according to AWS D1.1 without additional compensation.

Furnish all completed QC inspection documents to the Quality Assurance representative designated by the State.

Install the frangible couplings according to the manufacturer’s written installation instructions.

660-2.04 POLES, STEEL PEDESTALS AND POSTS.  Add the following:  Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas according to Subsection 660-2.15, Galvanizing.

Fabricate pile cap adapters from steel piles that conform to ASTM A252 grade 3 and steel plate that conforms to ASTM A709 grade 50.  Only use seamless piles or piles with a single longitudinal seam that is electric resistance welded.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Furnish the adapters hot dip galvanized according to ASTM A123, except leave the beveled edge free of zinc.  Fabricate the anchor plate to match the base plate of the lighting standard.  See the detail sheet in the plans for all dimensional information.

Complete all welding design, fabrication, and inspection according to the latest edition of the AWS D1.1, Structural Welding Code-Steel

- Circumferential Welded Splices

## Inspect 100% of CJP welds by ultrasonic testing (UT)

- Longitudinal Seam Welds

## Inspect 100% of CJP welds by ultrasonic testing (UT)

## Inspect 25% of all PJP welds of longitudinal seams by magnetic particle testing (MT)

- Base Connection Welds

## Inspect 100% of all base connection welds.

## Inspect CJP welds by UT

## Inspect fillet welds by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Quality Assurance (QA) representative for approval.  Do not begin welding until these items have been returned approved in writing by the QA representative.  The welding plan shall consist of the following:

## Welding Procedure Specification (WPS)

## Procedure Qualification Record (PQR)

## Welder Performance Qualification Record (WPQR)

## Visual Inspection Form

## Report of Nondestructive Examination (NDE) of Welds according to Annex K, latest edition of AWS D1.1

## NDE personnel qualification records

## The Contractor’s Quality Control (QC) manager with documentation of qualifications

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT.  Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid and will not allow trenching after you place the final lift of asphalt.

Delete paragraph 17 and add the following: Wherever the plans show reusing existing conduits, clean them using compressed air before pulling in the new cables.  Existing illumination cables that will be reused may be left in the conduits while you clean them.  Use a heavy-duty air compressor that delivers at least 3.540 cubic meters per minute (125 cfm) of air at 0.758 MPa (110 psi).

660-2.06 JUNCTION BOXES.  Delete the second paragraph and substitute the following:  Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS.  Delete item 2.  Power Conductors and Cables and add the following:

- Power Conductors.  For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, ICEA publication S-66-524, and NEMA Publication No. WC7.  Furnish conductors insulated with cross-linked polyethylene, UL listed as type XHHW-2 and rated for 600 volts AC operation.

Provide the following markings on the conductor insulation: manufacturer, conductor size, 600V, the symbol of an Approved Independent Testing Laboratory, and XHHW-2 on intervals of 2 feet or less.

Use size 10 AWG wire for illumination tap conductors.  In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire.  Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors.  Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables.  For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket.  Use conductors UL listed as type XHHW-2.  Furnish these cables with one black, one white, and one red colored conductor and no ground conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors that meet the requirements of ICEA publication S-66-524 and Underwriters Laboratories for Type XHHW.  The jacket shall also meet the requirement of ICEA publication S-66-524.

Provide the following markings on the jacket: manufacturer, conductor size, number of conductors, and 600V on intervals of 2 feet or less.

- Power Cables.  For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene, and a PVC jacket.  Furnish these cables with no ground conductor. Use cables manufactured according to ICEA publication S-95-658 and NEMA Publication No. WC70.  Provide cables UL listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor. Provide conductors UL listed as type XHHW-2.

Provide the following markings on the jacket: manufacturer, number and size of conductors, TYPE TC, 600V, sunlight resistant, 90oC Dry 75oC Wet, and symbol of an Approved Independent Testing Laboratory on intervals of 2 feet or less.

Delete item 4.  Loop Lead-In Cables and add the following:

- Loop Lead-In Cables.  Unless otherwise specified, use a cable that conforms to the following specifications to connect the loop detectors to the terminal blocks in the controller cabinet.  Furnish this cable, also known as Snyder Cable; third party certified for use in underground conduit or as an aerial cable supported by a messenger, and rated for 600 volts AC operation.

Use size 18 AWG, 16 strand, tinned copper conductors per ASTM B-33 insulated with wet-rated, cross-linked polyethylene similar to XHHW.  Furnish conductors with insulation colors that match TABLE 660-1 twisted into pairs.

Provide each twisted pair with an overall aluminum foil coated mylar shield that provides 100% coverage and a 20 AWG tinned copper drain wire that is in constant contact with the foil side of the shield.

Apply a tight fitting polyvinyl chloride jacket over the conductor assembly.  Provide the following markings on the jacket: manufacturer, year of manufacture, TYPE TC, 600V, 6pr#18, sunlight resistant, 90oC Dry 75oC Wet, and name of Approved Independent Testing Laboratory on intervals of 2 feet or less.

Only use the following loop lead-in cable to rewiring existing traffic signals when specified. Use cables that consist of 6 twisted pairs that consist of stranded, size 18 AWG tinned copper wire and polyethylene or polypropylene insulation.  Furnish each pair covered with an aluminum foil shield, stranded copper drain wire, and an overall PVC or PE jacket.  Use cable rated for 300 volts and whose colored pairs match those specified in TABLE 660-1.

660-2.10 FUSED SPLICE CONNECTORS.  Add the following:  Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING.  Add the following after the first paragraph:  Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph:  All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a zinc or galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Retrofit all existing spare conduits that will contain new cables exclusively with new grounding bushings. Whenever you reuse an existing conduit that contains no ground conductor, install a bare No. 8 AWG copper wire as the ground conductor. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted.  (3/30/00)R215M98

660-3.16 LUMINAIRES.  Add the following:  Furnish high-pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.

Furnish luminaires that

- Are UL 1572 listed for use in wet locations.

- Include a terminal block for terminating the illumination tap conductors.

- Feature an easily removed hinged door or tray used exclusively for mounting the ballast.

- Provide the illumination levels and uniformity specified (or better) in the arrangements listed on the plans when calculated according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 1983.

- Include a lamp-starting aid that plugs into a socket for easy replacement.

- Feature a wire way that meets NEC requirements for installing three #10 AWG conductors with type XHHW-2 insulation between the pole and a terminal block located in the luminaire.

- Are free of substances (such as paint) that affect photometric performance.

Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.

Luminaire Type Definitions:

MC-3:	Mast arm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

SC-5:	Short Cutoff, Type 5 as defined by the I.E.S.

Offset:	Pole top mounted luminaires designed to be offset between 6 and 15 meters from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT.  Delete the first paragraph and add the following:  Dispose of all materials removed from the project, except deliver the following materials undamaged to the City of Kodiak maintenance yard in Kodiak, Alaska.  Notify the City of Kodiak representative one week before your planned delivery of salvaged materials.

660-5.01 BASIS OF PAYMENT.  Add the following:  The prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans. This includes: completing all excavation to install foundations, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment. (04/30/02)R65M98

SECTION 670

TRAFFIC MARKINGS

Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 580 g/m2 for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 1.5 mm.

METHYL METHACRYLATE PAVEMENT MARKING
YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| Longitudinal Type3 (Center and Edge lines) | 2.3 mm | 5.8 mm |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 3.0 mm | 5.8 mm |
| Neutral Area (Diagonals, Chevrons) | 1.5 mm | Do not inlay these markings |

1.	Measure Type V spray without glass beads.  Tolerance is ±0.1 mm.  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 150 mm x 300 mm flat sheet of 2 mm thick aluminum placed in the path of the striping guns.

2.	Cut the inlaid slots to a depth of 6.35 mm.  Do not over fill the slots.

3.	Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 1.5 mm per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal and Transverse Type markings at 0.75 mm.

Unless directed otherwise by the Engineer, apply the final 1.5 mm of the Longitudinal Type markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Apply the final Transverse and Neutral Area markings as shown in the application table at this time.  Multiple application passes are required for Transverse Type markings.

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

Inlaid Markings

Apply markings in the milled groves after all millings have been removed. The extruded Methyl Methacrylate may be installed at the final yield thickness at the Engineer’s discretion.

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the removal requirement. Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width for any 15 m longitudinal run from the width shown in the Plans.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B).  No separate payment shall be made for furnishing and maintaining the MMAMS.  (12/04/02)R246

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

670(10B)	Methyl Methacrylate	Liter
	Pavement Markings

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01	ASPHALT CEMENTS.  Add the following:

Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T 53 and ASTM D 5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T 53	(none)	49°C	52°C

Toughness min.	ASTM D 5801 	(none)	12.4 N-m	12.4 N-m

Tenacity min.	ASTM D 5801	(none)	8.5 N-m	8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

Special Provisions

    - AGGREGATE FOR BASE.  Change the Base Degradation Value From “45 min.” to “25 min.”

Delete Table 703-2 and substitute the following:

## TABLE 703-2
AGGREGATE FOR UNTREATED BASE
Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modification

703-2.04	AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute:

“Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."  (06/25/99)M 82

Change the Degradation Value from “30 min.” to “25 min.”

In Table 703-3 on Page 470, revise the Type II gradations to read as follows:

| Sieve, mm | Gradation Type II |
| --- | --- |
| 19.0 | 100 |
| 12.5 | 80-95 |
| 9.5 | 70-90 |
| 4.75 | 50-70 |
| 2.36 | 35-60 |
| 1.18 | 20-40 |
| 0.600 | 13-30 |
| 0.300 | 8-20 |
| 0.150 | 6-12 |
| 0.075 | 3-7 |

703-2.07	SELECTED MATERIAL.  Replace the last sentence in both Items 1 and 2 with the following:

The percent passing the 0.075-mm sieve will be determined on minus 75-mm material.
(06/25/99)M 82

# Special Provisions

    - SELECTED MATERIAL.

- Selected Material, Type A.  In the third sentence, change “20-55%” to “10-55%”.

Add the following:

- Selected material, type D, shall consist of earth, sand, gravel or rock materials obtained from the excavation, and shall contain no wood, concrete or other debris.  (2/22/00)R89M98

SECTION 712

MISCELLANEOUS

## Special Provisions

712-2.06	FRAMES, GRATES, COVERS AND LADDER RUNGS.  Add the following:

Ductile iron castings	ASTM A536 for grade 60-401	(2/22/00)R78M98

712-2.17	METHYL METHACRYLATE PAVEMENT MARKINGS.  Add the following Subsection:

- Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MPa, to asphalt, dependent on tensile failure of the substrate.

(12/04/02)R246

SECTION 724

SEED

Special Provisions

724-2-02. MATERIALS.  Delete this Subsection in its entirety and substitute the following:

Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

TABLE 724-1

Seed Requirements

| # SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 70 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 71 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(03/05/02)R52M98

Delete this Section in its entirety except for Table 726-1 and substitute the following:

SECTION 726

#### TOPSOIL

#### Special Provisions

726-2.01	TOPSOIL.  Furnish topsoil which is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ALASKA FOP for AASHTO T 267, on the soil to determine the organic content of the soil. Supply the results to the Engineer.

Soil with an organic content of 5% or more may be reused and spread on the finished slopes where topsoil is noted on the plans.  Remove roots, stumps, unnatural material, and rocks greater than 75 mm in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less 5% cannot be used as topsoil for the project.  In this case, furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5% or more, as determined by ALASKA FOP for AASHTO T 267.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 75 mm in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free-draining and non-toxic.  Notify the Engineer of the location from which topsoil is to be furnish at least 30 calendar days prior to delivery of topsoil to the project from that location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use.  (12/05/01)R208M98

Replace Item No. 3 with the following:

#### TABLE 726-1

TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 75 mm | - | 100 |
| 12.5 mm | 100 | - |
| 4.75 mm | 95-100 | 75-100 |
| 1.18 mm | 64-90 | 50-95 |
| .075 mm | 30-60 | 20-80 |
| Organic Content* | 10% - 40% | 5% minimum |
| Limestone | 3.4 Mg/hectare | - |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267

(12/05/01)R139M98

SECTION 729

GEOTEXTILES

# Special Provisions

729-2.01	EMBANKMENT SEPARATION AND REINFORCEMENT.  Under 1, Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2, Reinforcement, replace ‘Separation (high survivability)’ with: ‘Stabilization’.

729-2.02	SUBSURFACE DRAINAGE AND EROSION CONTROL.  Under 2, Erosion Control, replace ‘Meet AASHTO M 288 for Erosion Control’ with: ‘Meet AASHTO M 288 for Permanent Erosion Control’.

729-2.04	SEDIMENT CONTROL.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with: ‘Meet AASHTO M 288 for Temporary Silt Fence’.

(2/28/00)R229M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04	SIGN POSTS.  Under Item 1, Metal Pipe Posts, add the following to Paragraph a.:

Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Add the following:

- Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501.  The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls.  Eleven-millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.  (12/04/02)R81M

APPENDIX A

PERMITS

APPENDIX B

EROSION AND SEDIMENT CONROL PLAN