# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	Cross Sections

c.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

d..	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

e.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

f.	Geotechnical Report Titled “Seward Highway MP 96-102”

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix D.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

6.	Changes have been made to Section 670 of the Special Provisions.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

##### PART 4

##### STANDARD MODIFICATIONS

##### AND SPECIAL PROVISIONS

##### to the

##### STATE OF ALASKA

##### SPECIFICATIONS

##### FOR

##### HIGHWAY CONSTRUCTION

##### (METRIC)

##### 98M

#### SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

(06/25/99)M 68

Special Provisions

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material. (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State.(10/28/99)M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”.

(06/25/99)M 69

# Special Provisions

Add the following Subsection:

103-1.10. Escrow of Bid Documentation. Furnish a legible copy of your bid documentation and an affidavit, as instructed in writing by the Contracting Officer. Bid documentation consists of written documentation of all quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and other information used to prepare your bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor with a subcontract exceeding $200,000, regardless of tier.

Meet the following requirements:

- Submitting Bid Documentation. Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number. Deliver the sealed container to the Department-designated document depository for safekeeping.

- Affidavit. Submit directly to the Contracting Officer the completed and certified affidavit located at the end of this Subsection, attesting that:

- the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

- the sealed container contains all bid documentation submitted,

- the escrow materials were relied on to prepare the bid, and

- should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

- Duration and Use. The bid documentation will remain in escrow, without access by either party, until one of the following occurs:

- There is a dispute related to Change Order. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor files a written claim or initiates Contract-related litigation against the Department. With a neutral observer present, both parties will have joint access to review and copy the files.

- The Contractor completes the Contract and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed. Such action is sufficient grounds for the Contractor to obtain the release and custody of the escrow documentation.

- Failure to Provide Bid Documentation. Refusal or failure to provide your bid documentation or affidavit renders your bid nonresponsive. Failure or refusal to provide Subcontractor bid documentation, will result in subcontract disapproval.

- Confidentiality of Bid Documentation. Materials held in escrow are your property. Except as otherwise provided herein, the escrow materials cannot be released without your approval. The original escrow materials are returned to you once any litigation is concluded, outstanding claims are resolved, and the final release is executed.

- Cost and Escrow Instruction. The Department pays to store all escrowed materials and instructs the depository regarding escrow.

- Payment. Include within the overall Contract bid price all costs to comply with this subsection.

# (02/12/02) S 86

SECTION 105

CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area. Use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

##### Alaska Fiber Star ### AT&T Alascom Alaska Communication System (ACS) Chugach Electric Association ENSTAR Natural Gas, Inc. GCI Communications

Call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  You shall bear the expense for any changes or additional relocation requested for your convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

You are responsible for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if you are required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of your two (2) week work plan, or not required by the contract.

The utility shall give you, through the Engineer; fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen  (15) calendar day’s advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit you, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

Alaska Communication System, (ACS): ACS has existing underground facilities located within this project. ACS has existing facilities that are in conflict with the proposed roadway and will require adjustment and/or relocation. Notify ACS at 907-564-1367 to establish a point of contact and to determine were to send the written notice to ACS fifteen (15) calendar days prior to starting work on any ACS relocation for this project.  Provide a copy of the written notice to the Engineer. ACS or their contractor crews will only be required to work in one of the location listed below at one time.

Below is a list of the locations that ACS facilities will require relocation.

UNDERGROUND

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Seward Highway Sta. 36+015, 42m Rt. | Place, One new Vault Type 4878 & Innerduct placement between new Vault and existing Vault #A. | 4 |
| 2. Seward Highway approx. Sta.36+645, 55.9m Lt.& 36+645, 61.9m Lt. | Place Two new, Type 4878 Vaults and Place new Innerduct between new Vaults | 6 |
| 3. Seward Highway Sta. 43+440, 9.1m Rt. to 91.4m Rt. | ### Place 100mm PVC & 31.75mm Innerduct to the Bird Creek CO. | 10 |
| 4. Seward Highway approx. Sta. 35+940 Rt. to Sta. 43+440, Rt. | ### Place New Fiber Optic Cable into Completed & Accepted System | 15 |
| 5. Seward Highway Approx. Sta.36+940 Rt. & Sta. 43+440 Rt. | Fiber Optic Cable Splicing & Bird Creek CO Work | 12 |
| 6. Seward Highway Sta. 36+645, 61.9m Lt. | ### Place new fiber into Innerduct & Splice New Fiber Cable into existing Cell Site Fiber Cable | 5 |
| 7. Seward Highway Sta. 36+015 Rt. to 36+645 Lt. | ### Retire Aerial Fiber | 6 |
| 8. Seward Highway Sta. 44+718 Lt. to 45+596 Lt. | Place Temporary 200 Pair & Two Vaults at each end of Temporary relocation | 10 |
| 9. Seward Highway Sta. 44+718 vault & vault at 45+596, 23.4m Lt. | Temporary Copper Cable Splicing | 7 |
| 10. Seward Highway Sta. 44+718 vault to vault at Sta. 45+596, 23.4 m Lt. | Place new 200 pair copper into completed conduit system and two new vaults | 5 |
| 11. Seward Highway Sta. 44+718 Lt vault & vault at Sta. 45+596, 23.4 Lt. | Final Splicing of 200 pair copper cable. | 7 |

You are required to provide assistance or perform work listed below before ACS and/or in conjunction with relocation work.

Location No. 1: Prior to the placement of the new vault, coordinate with ACS and remove enough of the existing asphalt to accommodate the installation of this ACS vault.  ACS or their contractor will place a new vault at approximate Seward Highway Sta. 36+015, 42.3m Rt. In addition ACS will place a new innerduct from this new vault to an existing vault at approximate Sta. 35+940 Rt. Coordinate with ACS or their contractor to replace all the removed asphalt in and around the new vault.  This work shall be subsidiary to Item 401(1A).

Location No. 2: Coordinate with ACS and stake right of way in the vault locations to facilitate the ACS vault installation.  ACS or their contractor will place two new vaults and install a 31.75mm innerduct between the two new vaults. Coordinate with ACS, or their contractor, to provide all the required traffic control, maintenance and flagging to accommodate the vault installations.  This work shall be paid under the appropriate 643 items.

Location No. 3: Complete the new vault installation approximate Sta. 43+440, 9.1m Rt. prior to ACS or their crews starting the conduit work in this location. Once the vault has been completed and is accepted by ACS, ACS or their contractor will place new 100 mm conduits and three 31.75mm innerduct conduits from the new vault and into the ACS, Bird Creek Central office.

Location No. 4: ACS, or their contractor will place the new fiber cable into the completed duct system once you have completed placing all the required innerduct and vaults, and ACS or their contractor has completed their required innerduct and vault placement and the system has been completed and accepted by ACS.  Coordinate with ACS, or their contractor, to provide all the required traffic control, maintenance flagging to accommodate the fiber cable installation.   This work shall be paid under the appropriate 643 items.

Location No.5: Once ACS, or their contractor, has completed the placement of the new fiber optic cable into the completed duct system from end to end, ACS will test the new fiber cable and begin the required splicing and schedule the splicing cut over. ACS will begin the Bird Creek Central office work.

Location No. 6: When ACS has completed the new fiber optic cable splicing ACS, or their contractor, will place and test the new fiber optic cable between vaults and then cut over the cell site to the new fiber cable.

Location No. 7: Once ACS has completed the Cell Site fiber cable placement, splicing and the cut over, they will retire the aerial fiber cable to the Cell Site.  Coordinate with ACS and provide the required traffic control, maintenance and flagging for the retirement of the aerial cable crossing the Seward Highway, at approximate Pathway or “P” Sta. 60+600 Lt. This work shall be paid under the appropriate 643 items.

Location No. 8:  ACS will schedule the temporary copper cable relocation when you have provided them with the written 15-day advance notice. Provide the Engineer with a copy of the written notice that you send to the utility.  Coordinate with ACS and provide the required traffic control, maintenance, and flagging to accommodate the vault installations.  This work shall be paid under the appropriate 643 items.  Coordinate with ACS and provide the required Pathway or Seward Highway slope stakes and grading information in the vault locations, at approximate Sta. 44+718 to Sta. 45+596 Lt.  This work shall be subsidiary to Item 642(1).

Location No. 9:  When the temporary copper cable placement has been completed, ACS or their contractor will then begin the required splicing for the temporary copper cable.  When the temporary copper cable splicing is completed and working, ACS will abandon the existing buried cable in place. Coordinate with ACS for the abandon cable location.

Location No. 10: When you have completed the placement of innerduct, conduit and vaults from approximate Seward Highway Sta. 44+718 Lt. to Sta. 45+596 Lt. and ACS has accepted the conduit system, ACS, or their contractor, will then schedule the copper cable installation.  Coordinate with ACS and provide all the required traffic control, maintenance, flagging to accommodate the cable installation for this location.  This work shall be paid under the appropriate 643 items.

Location No. 11:   ACS will schedule the required splicing once they have installed the new copper cable placement and testing is complete.

Alaska Fiber Star (AFS):  AFS has an existing buried fiber optic cable located within the project limits that is in conflict with the proposed railroad realignment and will require relocation. Notify AFS at 907-365-7163 to establish a point of contact and to determine were to send the written notice to AFS fifteen (15) calendar days prior to starting work on any AFS relocation for this project. Provide the Engineer with a copy of the written notice to AFS. Listed below are the areas that relocation will be required for the AFS facilities.

UNDERGROUND

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. “R” Alignment Approx. 2+030 to 5+111.1 | Fiber Optic Cable Placement Specification | 7 Days prior to beginning Fiber Cable Placement Operation |
| 2. “R” Alignment 5+111.1 & 37+840, 25 m Rt. | Fiber Optic Cable Splicing | 10 |

You are required to provide assistance or perform work listed below before AFS and/or in conjunction with relocation work.

Location No. 1: When you have completed placing all of the AFS innerduct, handholes and the duct system has been accepted by AFS, or their contract inspector, provide the Fiber Optic Cable Installation Specifications to AFS, or their contract inspector, a minimum of seven (7) calendar days prior to beginning the placement of the new AFS fiber optic cable.  When AFS, or their contract inspector, has reviewed and approved the Fiber Optic Cable Installation Specifications, coordinate and provide a fiber-placing schedule to AFS or their contract inspector. No AFS fiber cable shall be placed with out the AFS inspector or their contract inspector on site to witness the placing operation.

Location No. 2:  When the new fiber optic cable has been installed, tested and excepted, AFS or their contractor will splice the new cable into the existing cable at each end.

Chugah Electric Association Inc., (CEA):  CEA has existing aerial and underground facilities located within the project limits that are in conflict with this proposed project. Notify CEA at 907-762-7656 to establish a point of contact and to determine were to send the written notice to CEA fifteen (15) calendar days prior to starting work on any CEA relocation for this project. Provide the Engineer with a copy of the written notice to CEA. Listed below are the areas that relocation will be required for the CEA facilities.

AERIAL FACILITIES

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. 40+618, 10m Lt. | Pole, Guy and Anchor | 4 |

You are required to provide assistance or perform work listed below before CEA and/or in conjunction with relocation work.

Location No.1:  Coordinate with CEA, or their contractor, and provide the required traffic control, maintenance and flagging to accommodate the retirement of the pole guy and anchor.  This work will be paid under Item 643(25).

General Communications Inc. (GCI) has existing underground fiber optic cable within the project limits and it is in conflict with the proposed excavation and embankment and the realignment of the roadway and railroad and will require relocation. Notify GCI at 907-868-8581 to establish a point of contact and to determine were to send the written notice to GCI fifteen (15) calendar days prior to starting work on any GCI relocation for this project. Provide the Engineer with a copy of the written notice to GCI.  GCI, or their contractor crews, will only be required to work in one of the locations listed below at one time.  Listed below are the locations and time required for GCI, or their contractor, to complete relocation(s) of their facilities.

UNDERGROUND

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Vault #A Rt. (existing) to Vault #D (existing) approx. Sta. 40+791.9 Rt. | Fiber Optic Cable Placement | 7 |
| 2. Vault #D (existing) approx. Sta. 40+791.9 Rt. to Vault # J (existing) approx. Sta. 44+730 Rt. | Fiber Optic Cable Placement | 7 |
| 3. Sta. 44+730, Rt. & Lt. Vault #6 to Vault #9 (270meter past B.O.P.) | Fiber Optic Cable Placement | 10 |
| 4. Vault A and Vault #9 | Fiber Optic Cable Splicing | 10 |

You are required to provide assistance or perform work listed below before GCI and/or in conjunction with relocation work.

Location No. 1, 2, & 3:  When you have completed the placement of the GCI innerducts, vaults and GCI has accepted the entire completed duct system installation for this project, GCI will schedule the fiber optic cable installation. GCI, or their contractor, will place the new fiber optic cable. The Contractor shall coordinate with GCI, or their contractor, and provide the required traffic control, maintenance and flagging for the fiber cable installation.  This work will be paid for under the appropriate 643 items.

Location No. 4:  Once the new fiber optic has been placed into the new GCI innerduct and through the new and existing vaults and has been tested, accepted then GCI or their contractor would begin the required splicing.

TEMPORARY

AERIAL

| Station / Location | Type of Facility | Calendar Days Required |
| --- | --- | --- |
| 1. Sta. 44+720+/- to Vault #9 approx. 270meters out side E.O.P (to the northwest) | Temporary Aerial Fiber Optic Cable Relocation | 30 |
| 2. At GCI Vault #4 Sta. 44+712 to Vault #9 approx. 270meters out side E.O.P (to the northwest) | Splicing of Temporary Fiber Optic Cable | 10 |
| 3. Sta. 44+712 Vault #J to Vault #9 approx. 270meters out side E.O.P (to the northwest) | Retire Temporary Fiber | 15 |

Location No. 1:  GCI will schedule the temporary fiber optic cable relocation when you have provided the GCI inspector, or their contract inspector, with the 15-day written notice.  Provide the Engineer with a copy of the written notice that you send to the utility.  GCI, or their contractor , will place the required new pole and temporary poles etc, and attach the temporary fiber optic cable to all required poles. Coordinate with GCI or their contractor and provide all the required traffic control, maintenance and flagging required for the temporary fiber cable installation.   This work will be paid for under the appropriate 643 items.

Location No. 2:  GCI, or their contractor, will make the necessary splicing for the temporary fiber optic cable once the temporary fiber optic cable has been placed and attached to poles.  GCI will abandon in place a section of the existing buried fiber optic cable once the temporary splicing and cut over has been completed. Coordinate with GCI as to when the temporary fiber cable is up and working and for the limits of the existing abandon in place fiber optic.

Location No. 3:  Once you have completed the new GCI innerducts, vaults,  conduit system and the new fiber is placed, tested and is in working order, GCI (or their contractor) will retire the temporary fiber, poles etc. Coordinate with GCI or their contractor and provide the required traffic control, maintenance and flagging to accommodate the temporary fiber cable retirement work.

(2/1/00)R3M98

105-1.13 MAINTENANCE DURING CONSTRUCTION. Delete the second sentence of the second paragraph.

Add the following: The Department will periodically perform avalanche control work along the mountains above the project.  This work will halt your operations in the avalanche zone.  Remove any avalanches that occur on the project, whether induced by the Department or nature, so your work can continue.  The Department’s control work will be standard avalanche control designed to reduce avalanche hazard to the motoring public, traveling through the avalanche zone.

The Alaska Railroad will be performing snow removal operations from their tracks.  It is possible this snow will interfere with the ability to blast, load, haul or place material.  Remove the snow as necessary for your work to continue.  No separate payment will be made for removal of avalanche debris or snow.  This work is subsidiary to Item 203(3), Unclassified Excavation.

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

### 105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630. (03/26/01) M 101

Special Provisions

-Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials which remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.02  LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY

TO PUBLIC

Special Provisions.

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineation’s in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineation’s of any site outside the project limits or not previously permitted, impacted by your operations. These delineation’s will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Department has received the following permits on your behalf:

- 1. U.S. Army Corps of Engineers Section 404 Permit, Permit No. 2-980650, Turnagain Arm 44, dated August 8, 2001.  This permit is for wetland involvement with the railroad, highway, and pathway construction between Bird Point and the community of Bird.

- State of Alaska Department of Fish and Game Title 16 Permit, Permit No.

FG 01-II-0105, dated May 2, 2001, for culverts at stations 39+007 and 39+840.

- State of Alaska Department of Environmental Conservation Section 401, Amendment to Certificate of Reasonable Assurance, dated April 30, 2001.

- State of Alaska Department of Natural Resources, Special Park Use Permit, Permit Number 01 101, Dated September 4, 2001.

- State of Alaska Department of Environmental Conservation Storm Water Plans Review, letter of non-objection, dated August 16, 2001.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.  (05/29/02)R7M98

# 107-1.08 RAILWAY-HIGHWAY PROVISIONS. Delete this Subsection in its entirety and substitute the following:

# SECTION 1.  DEFINITION OF TERMS

ARRC	Alaska Railroad Corporation, P.O. Box 107500, Anchorage, AK 99510-7500.

ARRC Property	all lands owned or withdrawn for the use of the ARRC, including the ARRC's track right-of-way and communications pole line right-of-way.

Chief Engineer	the person employed by the ARRC as head of its Engineering Department or Branch, or his/her authorized representative.

Contractor	any agent of the Permittee, including Contractors or subcontractors employed to construct, reconstruct, operate and/or maintain the Facility.  The term "Contractor" shall be synonymous with the term "Permittee" when the Permittee performs the construction, reconstruction, operation and/or maintenance of the Facility with its own personnel.

Director, Real Estate	the person authorized by the ARRC to execute contractual real estate agreements on behalf of the ARRC.

Facility	any improvements owned by the Permittee/Contractor which are to be placed on ARRC property in accordance with written permission executed by ARRC and Permittee.

Roadway Worker	any employee of a railroad, or of a contractor to a railroad, whose duties include inspection, construction, maintenance, or repair of railroad track, bridges, roadway, signal and communication systems, electric traction systems, roadway facilities, or roadway machinery on or near track or with the potential of fouling a track.

Telecommunications Supervisor  	the person employed by the ARRC as head of its Telecommunications Department or Branch, or his/her authorized representative.

Permittee/Contractor	the person, company or governmental agency to whom the right to enter upon ARRC Property was given in the form of written permit or contract executed by the ARRC and Permittee/Contractor.

Trackwork	all work on the line from the top of subgrade to the top of rail, including geotextile, when required.

Track Materials	all hardware, excluding signals and controllers, associated with the running of a railroad.

# SECTION 2.  GENERAL REQUIREMENTS

2.1	All construction, reconstruction, operation, and maintenance on ARRC Property shall be performed in compliance with these Standard Specifications for Work on Railroad Property, including all revisions thereto.

2.2	Failure to comply with these Standard Specifications for Work on Railroad Property shall result in the demand of ARRC to suspend all work on ARRC Property.

2.3	All work on or about ARRC Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with approved ARRC practices, and as specified herein.  ARRC traffic and property shall be protected at all times.

2.4	The safety and continuity of the operation of the traffic of ARRC shall be of first importance and shall be at all times protected and safeguarded.  The Permittee/Contractor and its subcontractors shall be required to perform and arrange their work accordingly.  Whenever, in the opinion of the Chief Engineer or his or her representatives, the work or its performance may affect or involve the safety of ARRC's facilities and/or operation of its railroad, the method of doing such work shall first be submitted by the Permittee/Contractor to the Chief Engineer for his/her approval, without which it shall not be commenced or prosecuted.  The approval of the Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which ARRC may suffer, or for which it may be liable, as a result of the acts or omissions of the Permittee/Contractor, its subcontractors or employees.

2.5	Whenever, in the opinion of the Chief Engineer, the construction may cause a hazard to the safe operation of ARRC, ARRC may, in its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Permittee/Contractor and its subcontractors from liability for the payment of damages caused by their operations.  ARRC shall be the sole judge of the necessity for, and as to the number and classification of employees required. The Permittee/Contractor shall reimburse ARRC for the cost and expense incurred in providing such employees.

SECTION 3.  SAFETY REQUIREMENTS

3.1	The safety of personnel, property, rail operations, and the public is of paramount importance in the prosecution of any work on ARRC Property.  The Permittee/Contractor shall comply with all Federal, State and local governmental regulations (e.g. OSHA, NESC, etc.) applicable to the construction, installation, or maintenance of any Facility.   As reinforcement and in furtherance of overall safety measures to be observed by Permittee/Contractor (and not by way of limitation), the following special safety rules shall be followed while working on ARRC Property. Further railroad safety information may be obtained from the ARRC Safety Office at 907-265-2440.  Safety information is also available on the ARRC website at www.akrr.com.

3.2.	ARRC flag protection is required before any activity can occur on or near a railroad operating facility such as a track, yard, bridge or shop building.  For subsidiary work, such as surveying or inspection, an ARRC furnished flagman will provide a safety briefing prior to the commencement of the work   For any activity involving a disturbance or potential disturbance to the track, track embankment, or any railroad facility, ARRC may require the Permittee/Contractor to submit a specific Railroad Safety Plan prior to startup.   Projects that involve activities that cross the tracks or are longitudinal to the tracks will require a specific Railroad Safety Plan and a one-hour ARRC provided training course for Permittee/Contractor’s project supervisors prior to the initiation of work on ARRC Property.  Specific information on Railroad Safety Plans may be obtained from the ARRC Safety Office at 907-265-2440.

3.3	The Permittee/Contractor shall arrange for ARRC flag protection when performing any work within 6 meters (20 feet) of any track.  All work within 6 meters (20 feet) of the track shall cease when a train passes and all Permittee/Contractor employees shall maintain a distance of at least 6 meters (20 feet) from the track until the train has safely passed.  In addition, any work that could come within 6 meters (20 feet) of the track will cease when a train passes.  For example, crane or pile driving activities shall stop when trains pass when the maximum boom and suspended load radius can come within 6 meters (20 feet) of the tracks.  Pile driving shall not be done when trains are passing the work site.  Vehicles and other construction equipment shall not be operated or parked closer than 6 meters (20 feet) from any track without ARRC flag protection.

3.4	In the event Permittee/Contractor will be performing construction or other activities on or in close proximity to a railroad track, the Permittee/Contractor shall be responsible for compliance with applicable Federal Railroad Administration’s Roadway Worker Protection (“RWP”) regulations (49 CFR 214, Subpart C) if its employees qualify as “Roadway Workers”.  Under 49 CFR 214, Subpart C, railroad contractors are responsible for the training of their employees on these regulations.  All RWP related Work shall be conducted in strict compliance with the RWP safety standards set forth in 49 CFR 214, Subpart C and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any RWP related Work.

3.5	In the event Permittee/Contractor will be performing construction or other activities on a railroad bridge, the provisions of 49 CFR 214 regarding bridge worker safety shall apply.  All bridge related work shall be conducted in strict compliance with the bridge worker safety standards set forth in 49 CFR 214 and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any bridge related work.

# SECTION 4.  INSURANCE REQUIREMENTS

4.1 	The Permittee/Contractor shall procure and maintain at all times while performing work on ARRC Property, and be covered by the types of insurance with the minimum limits as specified in Section 4.4.

4.2	Each policy specified in Section 4.4 shall be:  (1) endorsed to include ARRC as an additional named insured with respect to the performance of the work; (2) endorsed whereby the insurance company will notify ARRC of any material change, cancellation, non-renewal or expiration of the insurance policy in writing not less than thirty (30) days prior to the effective date; (3) endorsed with a waiver of subrogation rights in favor of ARRC; and (4) endorsed with the Alaska Suit Endorsement.

Prior to commencement of any work on ARRC Property, the Permittee/Contractor shall deliver to ARRC certificate(s) of insurance showing evidence of the insurance required in Section 4.4.

4.4	Alaska Railroad Corporation Minimum Insurance Requirements.

a.	Commercial General Liability insurance with limits not less than $2,000,000 per occurrence and $6,000,000 aggregate for Bodily Injury and Property Damage, including coverage for Premises and Operations Liability, Products and Completed Operations Liability, Contractual Liability, and Broad Form Property Damage Liability. Coverage shall not contain any exclusions of Explosion, Collapse, Underground, or Rail Operations.

b.	Automobile Liability insurance on all owned, non-owned, hired and rented vehicles with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

c.	Worker's Compensation insurance in accordance with the statutory coverage required by the State of Alaska and, where applicable, insurance in compliance with any other statutory obligations, whether State or Federal, pertaining to the compensation of injured employees assigned to the Work, including but not limited to Voluntary Compensation, Federal Longshoremen and Harbor Workers Act, Maritime and the Outer Continental Shelf's Land Act and the Federal Employers Liability Act.

d.	If any part of the work to be performed on ARRC Property is located in close proximity to a railroad track, then the Permittee/Contractor shall also obtain Railroad Protective Liability insurance (Alaska Railroad Corporation as named insured) with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

# SECTION 5.  NOTICE

5.1	A pre-construction meeting shall be held with ARRC's Chief Engineer and representatives of the Permittee/Contractor and subcontractors prior to the commencement of any work on ARRC Property by the Permittee/Contractor or its subcontractors.

5.2	The Permittee/Contractor shall give written notice to the Chief Engineer not less than ten (10) days in advance of the commencement of any construction, reconstruction or major maintenance activity on ARRC Property, in order that the necessary arrangements may be made for the protection of ARRC's operations.  This notice shall include a description of the proposed work on ARRC Property, schedule of work, and the names of any Permittee/Contractor's subcontractor who may also be working on ARRC Property.

# SECTION 6.  FLAG PROTECTION AND PROTECTION OF ARRC TRAFFIC

6.1	Whenever ARRC flag protection is required, it will be provided by ARRC at Permittee/Contractor's expense.  ARRC flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the ARRC rules on flagging.  A minimum of 48 hours prior notice is required for ARRC to provide flag protection.

6.2	ARRC will, during the progress of the work, utilize as many qualified flag people as in the opinion of the ARRC may be required for the adequate protection of ARRC traffic.  All expense for providing such flagpersons shall be paid by the Permittee/Contractor to ARRC.

6.3	The Permittee/Contractor shall arrange with ARRC to keep itself informed on the time of arrival of all trains and shall stop any of Permittee/Contractor's operations which might be or cause a hazard to the safe passage of the train past the site of the work from ten (10) minutes before the expected arrival of the train until it has safely passed.

6.4	Track outages will only be approved in exceptional cases for limited durations.  Prior to a proposed track outage, the Permittee/Contractor shall submit a closure plan to ARRC.  The plan will describe the work to be accomplished, the equipment, manpower and other resources required, and the work schedule.  Once approved by ARRC, the Permittee/Contractor shall follow the plan.  ARRC reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  Permittee/Contractor shall bear all costs and damages which may result from failure to meet the closure schedule, in addition to the train delay charges provided for herein.

# SECTION 7.  TRAIN DELAYS

7.1	All work on ARRC Property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by ARRC.  The ARRC will provide a weekly forecast of train traffic and the ARRC flagmen will provide daily updates of anticipated train traffic.  Under no circumstances will the ARRC be liable in any way for delays to the Contractor’s work created by any changes or deviations from anticipated train schedules.

- ANTICIPATED WORK WINDOWS DURING CONSTRUCTION

- ARRC Track Maintenance Work Window: Section and summer work crews may need access into the work area to perform routine track maintenance work and scheduled summer major track replacement work.  The routine track work is performed as necessary for the safe passage of trains.  Railroad on-track equipment also travels through the project as needed.

- Train Traffic: The track through the project is very active.  The approximate number of trains in a 24 hour period is as follows:

- Summer Season - (May 6 to September 24) Approximate Daily Trains - 4 to 8 Passenger Trains, ARRC also charters passenger trains, which may run on any day.  Up to 3 Freight Trains, 1 Coal Train and up to 2 Work Trains per day.

- Shoulder - (April 1 to May 5 and September 25 to October 28)  Approximate Daily Trains - Up to 4 Passenger Trains, ARRC also charters passenger trains, which may run on any day.  Up to 3 Freight Trains, 1 Work Train and 1 Coal Train.

- Off Season -  Approximate Daily Trains - Up to 2 Passenger Trains, ARRC also charters passenger trains, which may run on any day.  Up to 3 Freight Trains, 1 Coal Train and 1 Work or Snow Service Train.

- Tracks out of Service: The work shall be planned to minimize track service outages.

- Prior to track outages, the Contractor will submit a closure plan to the Railroad.  The plan shall establish the work to be accomplished, the equipment, manpower and other resources required, and schedule.  Once agreed to by the Railroad, follow the plan.  The Railroad reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  The Contractor will bear all costs and damages, which may result from failure to meet the closure schedule, in addition to the train delay charges provided for in the contract.

- 7.2	Should any of the Permittee/Contractor's or its subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor by ARRC.

- Passenger trains each:		$50 per minute of delay, 60-minute minimum charge.

- All other rail traffic:		$50 per minute for each delay over five minutes, 30

- minute minimum charge.

- Rail barges, or other		No charge for delays of one hour or less; $1,000 per hour

- connecting carrier vessels:	for each hour or any part of an hour thereafter with a

- minimum charge of $6,000.

- 7.3	Delay time will be taken from the train sheet in ARRC’s Dispatcher's Office, Anchorage (907-265-2504) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

# SECTION 8.  PROTECTION OF ARRC COMMUNICATION LINES

- 8.1	All work on ARRC Property shall be conducted in such a manner as to protect ARRC's communication facilities at all times from outages resulting directly or indirectly from the Permittee/Contractor's or its subcontractor's operations.

- 8.2	Should any of the Permittee/Contractor or its subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor:

- Open wire communication circuits:	$1.00 per minute per circuit

##### Communication cable:	$1.00 per minute per cable

- 8.3	A minimum charge of $250.00 will be made for each outage plus the total repair costs.  The outage time shall be that as established by ARRC's Test Board, Anchorage.

- 8.4	There shall be no equipment operated or excavation made within 4.6 meters (15 feet) of any ARRC communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Telecommunications Supervisor.

# SECTION 9.  ROAD CROSSINGS

- 9.1	Whenever automatic railroad crossing signals are in the work area, these signals must remain in operating condition at all times.  If, as a result of the Permittee/Contractor's or subcontractor's activities the signals become inoperable, the crossing shall be continuously flag protected until the signals are again operable.  See Section 6 for flagging specifications.

- 9.2	When regular railroad crossings are used as haul routes inside or outside the work area, flagpersons shall be provided by the Permittee/Contractor for said crossings in all situations at the discretion of the ARRC.

- 9.3	Temporary road crossings may be installed provided the Permittee/Contractor has acquired from ARRC a temporary road crossing permit for said crossing.

- 9.4	The temporary road crossing shall be constructed to the length and the standards specified in the temporary road crossing permit.  All protective signs required by ARRC shall be provided and properly maintained by the Permittee/Contractor.  The temporary road crossing shall be installed under ARRC flag protection in accordance with Section 6 of these specifications.

- 9.5	The flange ways of all road crossings used by the Permittee/Contractor or its subcontractor as haul routes or temporary road crossings shall be kept clean and free of gravel at all times and shall otherwise be maintained to the satisfaction of the Chief Engineer.

- 9.6	When a temporary road crossing is in use, ARRC flag protection shall be provided at all times.  See Section 6 for specifications.

- 9.7	When a temporary or private road crossing is not in use, the Permittee/Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

- 9.8	When not in use during the winter season, the temporary road crossing shall be removed.  Upon completion of the work or termination of the crossing permit, the temporary crossing shall be removed and the area restored to its original condition.

- 9.9	The Permittee/Contractor agrees that all others using the private road crossing, except ARRC and its employees, shall be considered agents of the Permittee/Contractor.

- 9.10	Sight Triangles at road crossings shall be maintained by Permittee/Contractor free of vegetation and other obstructions to vision in accordance with the table entitled "Sight Triangle Distance" attached and as otherwise established and revised from time to time by ARRC.

- 9.11	Temporary public road crossings must be included in a traffic control plan submitted by the Permittee/Contractor to Alaska Department of Transportation (ADOT) for review and approval prior to constructing the crossing.

# SECTION 10.  POWER AND COMMUNICATION LINES

- 10.1	All power and communication lines shall be designed and constructed in accordance with the current edition of the National Electric Safety Code (NESC).

- 10.2	Underground power and communication lines shall be installed in accordance with Section 11 of these specifications.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

- 10.3	The minimum clearance above the top of rail of ARRC track shall be in accordance with the handbook referenced in Section 11.1, plus 0.15 meter (6”) to allow for future grade raises.

- 10.4	The minimum clearance above ARRC communication lines shall be in accordance with the handbook referenced in Section 11.1.

- 10.5	Additional lines may not be added, or the characteristics of the line(s) changed without the prior written approval of ARRC's Director, Real Estate or Chief Engineer.

- 10.6	Wires shall be strung across ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

- 10.7	No wires shall be strung across ARRC's communications lines without first receiving prior written approval from ARRC's Telecommunication Supervisor, and such work must be accomplished only at a time and in a manner prescribed by said Telecommunication Supervisor.

# SECTION 11.  UNDERGROUND UTILITIES

- 11.1	All underground utilities, including culverts, pipelines, and underground power and communication lines, on ARRC Property shall conform to the current American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications.

- 11.2	Unless the Chief Engineer authorizes another method in advance and in writing, all underground utilities shall be installed under tracks and roads by boring, jacking or tunneling.

- 11.3	Boring, jacking or tunneling shall be done under ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

- 11.4	The proposed plan for boring, jacking or tunneling shall be approved by the Chief Engineer prior to commencing the operation.

- 11.5	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring and/or cribbing as necessary.

# SECTION 12.  OPEN TRENCHING

- 12.1	Only when authorized in advance and in writing by ARRC shall any portion of the track be removed to allow trenching for installation of the Facility.

- 12.2	If allowed to open trench, the track may be removed from service only at the time authorized by the Chief Engineer and shall be restored to service within the time period specified by the Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Section 7 of these specifications, whichever is greater, and shall be collected from the Permittee/Contractor.

- 12.3	All track work shall be accomplished by qualified track persons.

- 12.4	Only that portion of the track structure necessary to excavate, stockpile and install the Facility shall be removed.  All track material removed shall be handled, stockpiled and relayed in a manner to avoid damage.  Any material that is damaged shall be replaced by the Permittee/Contractor at its own expense.

- 12.5	The backfill of the trench under the track and in the road bed prism shall be of the same type of material as taken out, except the top 0.6 meters (2 feet) shall be clean pit run gravel.  Backfilling and compaction shall be in 0.3 meter (one foot) lifts with a compaction of 95% of maximum density in the area affecting the road bed prism.

- 12.6	The ballast used in replacing the track shall be equal in depth and quality as that which was removed.  The track shall be relayed and brought to original grade in accordance with standard ARRC practices.  The track shall be resurfaced as often as necessary for a period of 12 months after completion of construction to remove any settlement that may have occurred.

# SECTION 13.  EXCAVATIONS

- 13.1	Unless authorized in advance and in writing by ARRC, the top of any excavation shall not be within 6 meters (20 feet) of the centerline of any track.

- 13.2	No water shall be allowed to stand in open excavations in the track area.

- 13.3	Bridging and shoring shall be adequate to safely carry ARRC traffic and the decision of the Chief Engineer pertaining to same shall be final.

- 13.4	All open excavations shall be continuously protected by flags, flares, barricades or watchpersons, as directed by ARRC.

- 13.5	No excavation shall be left open more than three days, unless authorized by the Chief Engineer.

- 13.6	ARRC embankments and cut slopes shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

- 13.7	ARRC ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

# SECTION 14.  ARRC INSPECTIONS

- 14.1	ARRC may furnish an inspector during the periods of construction on ARRC Property.  The ARRC inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The ARRC inspector will work directly with the representative of the Permittee /Contractor and the decision of the ARRC inspector in matters pertaining to ARRC operations and safety shall be final.  In the event more than one shift is worked, an ARRC inspector will be required for each shift.  Presence or absence of an ARRC inspector shall not relieve the Permittee /Contractor of liability for damage done to property of ARRC, or the property of ARRC lessees or permittees having installations on ARRC Property.  All ARRC cost and expense for furnishing said inspector(s) shall be collected from the Permittee /Contractor.

# SECTION 15.  USE OF EXPLOSIVES

- 15.1	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding same.

- 15.2	No blasting of any kind will be permitted unless the Permittee/Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, ARRC flag protection in accordance with Section 6 of these specifications shall be provided on each side of the blast area by the Permittee/Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

# SECTION 16.  SNOW REMOVAL

- 16.1	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of ARRC; (2) where it interferes with the normal operation of the automatic crossing signals; (3) impairs the visibility of either highway or rail traffic at the crossing.

- 16.2	Snow removal operations shall be conducted in accordance with Section 3 of these specifications.

# SECTION 17.  CLEAN-UP

- 17.1	At all times, all work and activities on ARRC Property shall be accomplished in such a manner as to keep the ARRC Property in a neat, orderly and safe condition satisfactory to ARRC.

- 17.2	Upon completion of Permittee/Contractor’s work, all equipment and unused materials shall be removed and the ARRC Property shall be left in a neat and clean condition satisfactory to ARRC.

- 17.3	Should the Permittee/Contractor or its subcontractor fail to comply with Section 17.1 and 17.2 above, ARRC may perform the required clean-up.  All ARRC costs and expenses for performing this work shall be collected from the Permittee /Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (05/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE. Add the following before the last paragraph: When construction activities meet any of the following conditions, advise the appropriate owning Utility(s) in writing at least 24 hours in advance of work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment that is capable of coming within 3 m of an overhead electrical line.

- The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services. (7/30/99)R170M98

Standard Modifications

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S 80

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

Ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

#### Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1:  Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (04/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals.  (01/31/02)R160M98

108-1.05 CHARACTER OF WORKERS, METHODS AND EQUIPMENT.  Add the following:  Prior to working on the project during periods of avalanche danger, perform the following:

1.	Prepare an avalanche work plan that will address methods to safely operate in the vicinity of known avalanche areas.  This plan shall be submitted to the Engineer a minimum of 14 days prior to beginning work or within 7 days of the Engineer’s request for an update.

2.	Provide a training seminar for all workers on avalanche dangers and rescue methods.

3.	Have avalanche rescue equipment available at the work site.

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (2/15/01)R242M98

***Deleted***

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(05/31/00)M90

1. Labor. Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

(02/08/01)M71

Special Provisions

Under item 3. Equipment, change the first sentence to read … “Rental Rate Blue Book for Construction Equipment”, published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA, 95110-1313.

Under item 3. Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.

(01/27/00)R14

#### Standard Modifications

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor. (02/08/01)M71

#### Special Provisions

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska, at a location acceptable to the Engineer. (09/1/89)R16

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work. Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 201

#### CLEARING AND GRUBBING

Special Provisions

201-2.01 GENERAL.  Add the following:  Timber 125 mm in diameter or larger at breast height shall be cut into 2.4 meter lengths, de-limbed, and stacked at locations approved by the Engineer for public removal.  These locations shall be adjacent to the nearest side street or other approved site which does not create a traffic hazard due to lack of adequate parking for the public.  The Department will notify the public of the availability of the timber once it has been stacked.  Schedule his clearing and grubbing work so as to provide two weeks for the public to access those areas of the project where such timber is available prior to completion of the clearing and grubbing work in those areas.  Dispose of any timber left by the public after the two week time period.

Perform all work necessary to preserve and/or restore land monuments and property corners from damage.  Any land monument or property corner that is disturbed shall be restored in accordance with Section 642  at the Contractor’s expense.  An undisturbed area 1.5 meters in diameter may be left around existing monuments and property corners.

Provide the public two weeks for plant salvage access time after staking the clearing and grubbing limits.

201-2.06 DISPOSAL.  Delete the fifth paragraph.

201-4.01 BASIS OF PAYMENT. Add the following:  All work required to cut, de-limb and stack timber for public removal and to preserve and restore land monuments and property corners will be subsidiary to Item 201(3A), Clearing and Grubbing.

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

Special Provisions

202-1.01 DESCRIPTION.   Add the following:  This work includes the removal and disposal of the existing concrete curbs, steel bridge railing, and steel pedestrian railing on the Bird Creek Bridge No. 643.

# CONSTRUCTION REQUIREMENTS

202-3.01 GENERAL.  Add the following:  When removing existing structures from Bridge No. 643, chip below the top of the concrete deck surface at least 16 mm at all existing reinforcing steel and pedestrian anchor bolt locations.  Cut steel at least 13 mm below the concrete surface then patch with grout meeting Section 701-2.03.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for construction of the embankment. Bury this material so it is not exposed at the completed surface of the embankment.  The maximum dimension of the broken asphalt pieces shall be 150 mm.

For disposal of removed asphalt, obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt. A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

SECTION 203

EXCAVATION AND EMBANKMENT

# Special Provisions

203-1.01 DESCRIPTION.  Delete this Subsection in its entirety and substitute the following:

Excavate, haul, place, install, compact or dispose of specified materials necessary to construct the project. Conform to the lines, grades, depths and typical cross sections shown on the Plans or as established. ***Deleted***

Add the following:  Supply and maintain a certified scale on the Anchorage side of the Bird Creek bridge located within the project limits.  The scale shall be in accordance with Section 644 and operational before you begin hauling material.  The Engineer may require all equipment hauling material to be weighed or only require spot checks of equipment hauling material to ensure that the maximum allowable gross vehicle weight is not exceeded in accordance with Subsection 644-2.06.

Delete Subsections 203-2.01, 2.02, 2.03, 2.04, and 2.05 in their entirety and substitute the following:

203-2.01 MATERIALS.

1.	Unclassified Excavation. All materials of whatever character encountered in the work. May include rock, common, or muck.

2.	Classified Excavation.

- Common Excavation. Silt, sand, gravel, and granular material other than rock or muck.

- Rock Excavation. Rock that cannot be excavated without blasting or ripping.

- Muck Excavation. Soils, organic matter, and other material not suitable for foundation material regardless of moisture content.

3.	Borrow. Approved material required for embankments or for other portions of the work, and obtained from sources outside the right-of-way limits for the project.

4.  Shot Rock Embankment. Free draining rock material removed from the excavation areas by means of blasting or ripping.

5.	Rock Stabilization Materials. As specified in the Plans or Special Provisions.

6.   Rockfall Mitigation Materials.  As specified on the Plans or Special Provisions.

Delete Subsection 203-2.06  CONTROLLED BLASTING in its entirety:

CONSTRUCTION REQUIREMENTS

203-3.01 GENERAL. Delete this Subsection in its entirety and substitute the following:  Perform all necessary clearing and grubbing prior to beginning excavation, grading, and embankment operations in any area.

Keep excavation and embankment areas free draining at all times as the work progresses. Finish the excavation and embankments to reasonably smooth and uniform surfaces.

Excavate and embank material only within the limits on the Plans or as directed. Prevent disturbing material and vegetation outside of the slope limits.

Excavated soils that cannot be properly compacted in embankments may be designated as unsuitable.

When unsuitable material is encountered at the required depth of excavation, remove the unsuitable material to the depth specified or directed. Allow for measurements to be taken before backfill is placed.

Dispose of unsuitable material or excess usable material at locations of your choice outside of the project, with the property owner’s written consent and the approval by the Engineer, or within the project at approved locations.  Ensure that all waste areas are properly graded and drained. Blend the outer limits of waste into surrounding grounds with no noticeable break or variation readily discernible. When existing roadway embankment slopes are used as disposal sites for waste or surplus material, finish the slopes with a motor grader or other approved method.

When the volume of suitable excavation is not sufficient for constructing the fill to the grades indicated, furnish the necessary borrow from approved sources. Borrow may be necessary even though not shown on the Plans. The source and acceptability of the borrow is subject to approval. All test pits and explorations required to evaluate the acceptability of borrow are subsidiary.

Do not place borrow material until after the usable ***DELETED*** excavation has been placed in the fill. If you place more borrow than is required, resulting in or as a result of the unnecessary wasting of usable excavation, the amount of such waste will be deducted from the borrow quantity.

Obliteration of Roadways includes all grading operations necessary to incorporate the existing roadway into the new roadway and surroundings in order to provide a pleasing appearance from the new roadway. Fill ditches not required for drainage and grade to the approximate original ground contour.

Obtain Selected Material, Type A, Type C and Shot Rock from the rock excavation.  Use all excavated material meeting the requirements of Selected Material, Type A or Shot Rock for construction of the Selected Material, Type A or Shot rock portion of the structural section.  Stockpile, double handle, sort and screen the material as required.

Add the following Subsections:

#### EXCAVATION

203-3.01.1 OVERBURDEN LINE DRILLING. Overburden line drilling consists of drilling or probing for the top of the rock surface at the estimated location of the daylight line of rock excavation.  The information obtained from overburden line drilling can be used to help define the slope limits in cut areas prior to beginning excavation in areas where the depth to rock, and therefore, the width of excavation is difficult to estimate.

203-301.2 ROCK EXCAVATION.  This work includes excavation of rock, drilling, blasting and ripping rock, using controlled blasting, production blasting and trim blasting techniques as shown in the plans and specifications or as directed by the Engineer.  The plans and specifications may require blasting techniques where ripping may work or may require ripping techniques where blasting may work.

1.  Blasting Program.  Not later than two weeks prior to the commencement of any drilling and blasting operations, submit to the Engineer for his approval, a tentative Blasting Program for the entire project.  Do not commence any drilling or blasting operations until the Blasting Program is approved by the Engineer.  Include the following in the Blasting Program:

a.   	Description of the overall blasting program, including general sequence of the work and a generalized schedule showing where and when blasting and excavation is expected to be conducted.

b.  	Traffic routes and scheduled closures.

c.  	Blast design details for each cut, rock type and generalized condition indicating hole diameters, spacing, type of explosives and initiators, and delay and firing sequences to be used in the test sections described below.

d.  	Location of explosive storage facilities.

e.  	Description of warning signals and signs and safety procedures.

f.   	Proposed measures for protection of structures, facilities, adjoining work, and sensitive fish and wildlife habitat.

g.  	Number and type of seismographs (if required) proposed for monitoring the blasts.

h.  	Techniques for drilling and loading explosives in wet or water-filled blast holes.

i.	Proposed Rock Bolting Plan

For convenience, the Blasting Program may group together similar cuts with similar rock types, geometry and other characteristics.  Conduct test blasting to establish that the Blasting Program results in acceptable results.  Submit results of the test blasting for evaluation and approval by the Engineer.  The Blasting Program shall be tentative, pending the approval by the Engineer or test blasting conducted as set forth in Subsection 6, below.

Coordinate with the Federal Aviation Administration (FAA).  A 305 m (1000 ft) above ground elevation Controlled Firing Area (CFA) restriction will be in effect for the blast areas.  Accomplish the following:

- Contact the Kenai Flight Service Station at 283-3735 twelve hours prior to blasting.

- Provide an aircraft watch attendant who is in continuous contact with the person in responsible charge for firing.

- Blast faces shall be limited to a maximum height of 76 m (250 ft) above sea level, and no fly rock shall be allowed higher than 152 m (500 ft) above ground elevation.

2.  Blasting Consultant. Employ the services of a Blasting Consultant to design and supervise the Blasting Program as described below.  Provide documentation showing the Blasting Consultant’s has experience and qualifications. Provide documentation showing that the Consultant has not been an employee of the Contractor, the explosives manufacturer or the explosives distributor for the five years prior to the award of the contract.  Provide documentation that the Blasting Consultant derives his primary income from providing specialized blasting or blasting/consulting services in the field of rock excavation for highway construction.

Not later than 5 days prior to the pre-construction conference, submit the resume of the proposed Blasting Consultant for approval by the Engineer.  Demonstrate in the submittal that the Blasting Consultant has been responsible for at least ten highway rock excavation projects for which the Blasting Consultant had primary responsibility for design and which included blasting situations similar to those of this project.  Include in the resume the names and telephone numbers of owners’ representatives with sufficient knowledge of the projects to verify the submitted information.  Do not commence drilling or blasting operations until the Blasting Consultant has been approved by the Engineer.

3.  Blaster in Charge.  Not later than three weeks prior to the commencement of any drilling and blasting operations, employ and designate to the Engineer the Blaster in Charge for the project.  Provide documentation showing that the Blaster in Charge is licensed and authorized under all applicable federal, state and local laws or regulations to possess, transport, store and use explosives of the type to be used on the Project.  Require the Blaster in Charge to be on the site during all loading and blasting operations.  Assign the Blaster in Charge the responsibility for ensuring that the safety procedures set forth below are followed and the record-keeping requirements are met.

4.  Vibration and Noise Consultant.  Where blasting near buildings, structures, utilities, sensitive fish or wildlife habitat, or other facilities for which blasting vibration or noise effects may be detrimental, employ a vibration and noise consultant approved by the Engineer to establish safe vibration and noise limits.  Noise and vibration limits shall be based upon federal, state and local laws and regulations.

5.  Preblast Meeting.  Hold a pre-blasting meeting at the jobsite, prior to commencement of any drilling and blasting operations, with a minimum of the Contractor, Blasting Consultant, Blaster in Charge and representatives of the Engineer.  Discuss the Blasting Program and Blasting Plans and visit such specific sites as are necessary to familiarize the participants with the details of the blasting operations.

6.  Safety.   Submit a safety plan for approval by the Engineer that includes plans for closure of roads and trails, warning signals, notification of affected local, state, and federal agencies.  Include in the plan methods used to protect life and health, public and private property, new work or existing work on the Project, nearby structures, wetlands, waters and wildlife.  Hold a safety meeting shall be held prior to commencement of drilling and blasting work to address safety issues with respect to drilling and blasting.

- Warning Signals. Establish a method of warning all employees on the job site of an impending blast.  The warning signals shall consist of an audible horn or siren signal five minutes prior to the blast and a second signal one minute before the blast.

- Inspection and All Clear Signal.  After the blast, the Blaster shall observe the area of the blast for five minutes to guard against injury or damage due to rockfall.  The Blaster shall then inspect the blast area to determine that all explosive charges were detonated.  After these inspection, the Blaster shall sound an audible horn or siren as an all-clear signal to alert all personnel that the area is safe for entry.

- Misfires.  If a misfire occurs, the Blaster shall follow appropriate procedures to handle the misfire, including, but not limited to, determining why the misfire occurred; excluding all but essential employees from the blast area, closing nearby roads or facilities; repairing the initiation system; correcting the misfire in a safe manner; or, if unable to solve the problem, calling consultants skilled in correcting misfires.

7.  Vibration Monitoring. Wherever vibration damage is possible, monitor blasting with an approved seismograph located between the blast and the structure or facility that may be subject to damage.

a.	Develop a plan for controlling ground vibrations as part of the analysis of test blasts.  Monitor such test blasts as necessary to establish ground vibration levels at structures and facilities that must be protected.  Monitor test blasts to determine the methodology necessary to limit ground vibrations to a level that will not damages structures and facilities.

b. 	Establish a safe limit no higher than 50 mm/second, except as approved by the Engineer. In determining safe limits for noise and vibration, adhere to federal, state and local laws and regulations governing vibration and noise.

c.	Provide a seismograph record of particle velocities in three mutually perpendicular components of vibration in the range generally associated with blasting of the type undertaken.  Do not exceed the safe limits of peak particle velocity of each component as necessary to protect the structure, facility or fish and wildlife.

8.  Noise Monitoring.  When blasting near human habitation, or structures or facilities subject to air blast and noise damage or annoyance, the Engineer may require the installation of an approved air blast monitoring system to measure peak overpressure.  Limit peak overpressure to a maximum of 345 Pa at the nearest structure or other potentially sensitive location.  Make such adjustments as are necessary to assure the air blast and noise levels are minimized.  The Engineer may reduce the overpressure limit if damage or complaints occur.  Furnish the peak overpressure records to the Engineer immediately after each shot.

9.  Use of Explosives.

- Conduct all blasting operations, including storage, transporting and handling of explosives and blasting agents in accordance with all local, State and Federal laws and regulations, including the applicable provisions of the Standard Specifications.  Submit storage plans to the Engineer for approval and confirm the Engineers’ approval prior to ordering and shipping any explosive materials to the jobsite.

- Use caps for a specific period from a single lot number, to help ensure the accuracy of firing times.

- Blast hole conditions may range from dry to wet and filled with water.  Describe in the Blasting Program appropriate techniques for any moisture conditions that are encountered.  Use whatever type of explosives and accessories are necessary to achieve the desired result.

10.  Blasting Test Sections.  Drill, blast, excavate and scale to final finish surface short sections of each rock type on the Project as necessary to determine the appropriate methodology to achieve the desired result prior to commencement of full-scale blasting operations.  The Blasting Program sets the initial methodology for the test sections.  The Blasting Consultant or Blaster in Charge shall prepare the Blasting Plan for each full-scale blast after the results of the test sections are analyzed.

Record each test blast using a video camera, electronic video recording device, or high speed photography.  Provide the video records to the Engineer for approval of the method prior to completion of the test blasting.

Set the controlled blast hole spacing initially to a maximum of 750 mm in 75 mm holes.  After analysis of the initial test blasting results, the Blasting Consultant or the Engineer may adjust the controlled blast hole spacing in additional test sections.

Do not commence work on any test section until the Engineer analyzes the previous test section and approves the next test. The Engineer will complete the analysis of each test section within 48 hours of the test section blast.

The Engineer will analyze the characteristics of the blasts and the final surfaces of the test sections with respect to criteria the Engineer deems necessary.  The Blasting Consultant shall adjust the blasting methods with respect to hole spacing, hole loading, sequencing and other factors that may require adjustment until methods and the final product are acceptable and approved by the Engineer.

Following completion of the test blasting, submit a final Blasting Program to the Engineer for approval.  If at any time during the progress of the work, the approved methods of blasting and drilling fail to produce the desired result (a smooth, stable backslope), the Blasting Consultant shall revise the blasting methodology.  Conduct such additional test blasting as is necessary to determine the appropriate methods to achieve the desired result.

11.  Blasting Plan.  Submit a Blasting Plan to the Engineer for approval at least 24 hours prior to each blast.  Include in the Blasting Plan details of the drilling and blasting pattern including, at a minimum, the following information:

- Station limits, number of blasts, and time of each blast.

- Plan and section view drawings of each blast indicating sizes, depths, angles, patterns and spacing of the holes, burden thickness and expected rock types.

- Drill hole diameters and depths including subdrilling depths.

- Drill steel diameter and bit types.

- Stemming length and type of materials used for stemming.

- Loading details including trade names, types, sizes of explosives.

- Sizes, trade names or primers, initiators and other accessories.

- Proposed initiation and delay sequences of the blast holes.

- Weight of explosives per hole and per delay and powder factors, including weight of explosives per square meter of finished backslope.

- Anticipated peak particle velocities at locations specified by the Engineer.

If a change in drilling or blasting methods is necessary, submit a revised Blasting Plan for the affected work at least 1 week prior to commencing the change of work.

12.	Blasting Records. Maintain a blasting record for each day of blasting work.  Submit the record to the Engineer prior to the next work day.  The record shall include, at a minimum, the following:

- The date of blasting.

- The number of blasts.

- The time of blasts.

- The Station limits of the blasts.

- Plan view and section view of each blast with notes indicating free face, burden, spacing, height of lift, hole diameter, stemming depth, hole angles, hole depths, including subdrill depth.

- Notes regarding conditions encountered in the drill holes, including soft or fractured zones, water table, alignment problems.

- Loading diagram indicating types and amounts of explosive, primers, initiators, stemming depth, powder factors, trade names and sizes of explosives, primers and initiators.

- Sequence plan of the shot, including surface delay times, and initiator delay times.

- Remarks regarding results of the shot including damage, misfires, fly rock and other unusual results or effects.

- Videotapes, electronic videos, or high-speed photographs of each blast, using a method approved by the Engineer in the test blasting program.  The photographs, film, videotape or electronic files recording each blast will become part of the Project records.

- Signature of Blaster.

13.  Unusual Conditions and Methods.  After approval by the Engineer, use angle holes, fan drilling and non-standard loading and spacing and other means in excavating sliver cuts, pioneering to the top of cuts, preparing working benches, and when unexpected or unusual geological conditions are encountered.  The unusual methods must result in the desired result of a stable rock slope.  Describe the methods proposed for use in these situations in the Blasting Program and Blasting Plans.

14.  Controlled Blasting.  Use controlled blasting techniques to produce a stable cut face sheared along the designed neat excavation line.

- Excavate all rock cuts over 3 m in height using controlled blasting methods to protect the backslope.  Controlled blasting holes are closely spaced holes drilled along the plane of the final design slope.  Controlled blasting is either preshear blasting or cushion (trim) blasting.  Where the total burden is greater than 8 m, use preshear blasting.  Where the total burden is less than 8 m, use cushion blasting.  Detonate explosives in the preshear holes before the production hole charges are detonated.  Detonate explosives in cushion blasting holes after the production hole charges are detonated.

- Drill controlled blasting holes between 63 mm and 75 mm in diameter and spaced 600 mm to 750 mm apart.  Do not drill controlled blasting holes deeper than 12 m, unless the Contractor demonstrates that deeper holes can be drilled while maintaining specified tolerances and achieving the desired result.  Determine the optimum spacing for controlled blast holes for each rock type and condition during the test blasting.

- Do not construct benches in finished rock back slopes unless approved by the Engineer or shown in the Plans.  Where more than one lift is required in a cut, the Engineer may allow an offset for drilling equipment clearances.  In order to accommodate any necessary offsets and maintain the desired slope angle in multiple lift cuts, set the controlled blast holes for the upper lift(s) back from the design slope so that the controlled blast holes for the lowest lift are on the designed neat excavation line.

- Lightly load controlled blasting holes with explosives designed for the purpose and no larger than one half the diameter of the hole.  Evenly distribute the explosives throughout the plane of the final slope.  Load all controlled blasting holes.  Do not use ANFO in controlled blasting holes.  Stem controlled blast holes from the top charge to the collar of the drill hole with dry sand or angular granular material passing the 9.5 mm sieve size.

- Drill controlled blasting holes to tolerances of plus or minus 75 mm at the collar and plus or minus 230 mm along the length of the hole.

15.  Production Blasting.  Use methods and materials necessary to fragment and loosen the rock inside the design excavation limits, while leaving a smooth, stable back slope using the controlled blasting methods discussed above.  Use appropriately designed delay sequences and allowable charge weights per delay to minimize ground vibrations and prevent damage to buildings, structures, utilities, sensitive fish or wildlife habitat and other facilities.

- Remove all loose rock, overhanging trees and other loose objects or dangerous conditions in or in close proximity to the cut slope area or rendered the condition safe prior to blasting.  Remove all material loosened or render safe all conditions aggravated by blasting operations as an integral part of the excavation and scaling operations.  Cease further drilling or blasting work until the Engineer approves the resolution of such conditions.

- Strip overburden before drilling blast holes.

- Locate production holes within 2 hole diameters of the staked location and drilled to the required depth.  If more than 5% of production holes are drilled out of tolerance, fill the out of tolerance holes crushed stone and redrilled or, if short, re-drilled to the proper grade.

- Drill production holes no closer than 2 meters to the controlled blasting line.  Drill the last line of production holes (or buffer holes) closest to the controlled blasting line parallel to the controlled blasting line.

- Drill production holes not be greater than 150 mm in diameter, unless approved by the Engineer.

- Drill production holes no deeper than controlled blast holes.

- Detonate production hole charges in a delay sequence toward the free face, with no more than 227 kg of explosive detonated per delay.

- Drill buffer holes, if used from 63 mm to 75 mm in diameter in one line parallel to and not closer than 1 meter from the controlled blasting line.  Load buffer holes to no more than 50% of the charge that would be used in adjoining production blasting holes.  Detonate the buffer hole charges toward the free face on a delay sequence, after the production hole charges are detonated.  Determine the need for buffer holes in the test section blasting.

- Remove material remaining more than 200 mm inside neat line rock slopes by scaling, controlled blasting techniques or other methods approved by the Engineer unless specifically exempted by the Engineer for aesthetic, geological or safety reasons.

- Remove loose material from rock slope failures or slides and disposed of the material at the contract price for unclassified excavation if the Engineer determines the failure did not occur as a result of the Contractor’s methods.

16.  Access for Inspections.  Unless dangerous conditions prevent access, provide continuous access to the excavated rock surfaces for inspections by the Engineer or designated representatives.  Provide all labor and equipment required by the Engineer to access the rock surfaces.  Inspections will be conducted within 48 hours following each blast.

17.  Scaling.  Stabilize new and existing rock slopes following completion of each shot and throughout the Contract period to ensure that rock slopes are stable by removing all loose, hanging, or potentially dangerous rock from the new face and from surrounding existing slopes, as required by the Engineer.

a.	Use hand tools, hydraulic splitters, high pressure water spray or air, light explosive charges or other methods as approved by the Engineer.

b.	Scale following each shot as an integral part of the excavation of each lift.  Do not commence drilling for the next lift until scaling is completed, inspected and approved.

c.	The Engineer may require additional scaling following completion of excavation, due to rebound effects, loosening caused by weather or other reasons.

18.  Ditch Line/Subgrade Blasting.  Where rock is encountered in ditches and below the subgrade, drill and blast to a depth of 2 meters below the profile grade shown on the Plans or as directed by the Engineer to fracture the rock foundation.  Space these holes closer than production holes and load the holes lighter.  Stem appropriately to minimize rifling.  Use this procedure to provide a stable draining interlock between the embankment material and the rock surface.  Provide a backhoe or other equipment to enable the Engineer to verify effectiveness of the blasting.  Adjust the hole pattern and loading if the procedure fails to fracture the underlying rock 1.1 meters below the Selected Material Type A layer.

***Deleted***

***Deleted***

***Deleted***

203-3.01.4 DRAIN HOLES.  Drill drain holes at locations and orientations as directed by the Engineer to relieve water pressure in rock backslopes.  The Engineer will determine the center to center spacing and may require additional drain holes be drilled at specific locations and orientations depending on geologic conditions.  Drill drain holes with a minimum hole diameter of 75 mm to lengths of 7 meters or as directed by the Engineer.  Flush drain holes with water upon completion to remove drill fines.  In weathered or broken rock, install perforated liner pipes as directed by the Engineer.

EMBANKMENT

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.  (03/14/02)R23M98

Add the following to the sixth paragraph:  Embankment may be placed over seasonally frozen mud flats, as long as all ice floes and chunks are removed prior to placement of embankment material.

Delete the 11th paragraph in its entirety and replace with the following:

Place rock embankment in lifts 1 meter or less in height. Restrict maximum rock dimension to 1 m. Distribute spalls and finer rock fragments to level and smooth each lift. Place succeeding lifts without damaging previously completed lifts. Dump rock on the lift being constructed and distribute by blading or dozing to minimize voids, pockets, and bridging and to form a dense, well-compacted embankment. ***Deleted***

In the 12th paragraph, first sentence, delete the words “from excavation”.

In the 12th paragraph, third sentence, insert the words “from excavation” after “wasted rock”.

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

Add the following: Compact all embankment within 6 meters of a bridge abutment full width to not less than 100 percent of the maximum density. All material used within this zone shall be graded to pass the 75-millimeter sieve. (2/1/00)R113M

203-4.01 METHOD OF MEASUREMENT.  Add the following:  Resection areas of instability or potential slides identified by the Engineer will be determined by re-sectioning.

Add the following to the first numbered list:

6.	Item 203(12), Drain Holes.  By the meter drilled and  accepted by the Engineer.

***Deleted***

Add the following to the second numbered list:

5.	water for compaction

6.	placing and removing temporary surcharge material

7.	work required to continually advance the heading on a rolling surcharge

8.	blasting mats

9.	scaling rock slopes

10.	ditch line/subgrade blasting

11.	certified scale

203-5.01 BASIS OF PAYMENT.  Add the following: Grading and placement of material used within 6 meters of bridge abutments will not be paid for directly, but will be subsidiary to Item 203(3) Unclassified Excavation. (2/1/00)R113M98

No additional payment will be made for stockpiling and double handling of material obtained from item 203(3), Unclassified Excavation to use as the Selected Material, Type A or Shot rock portion of the structural section.

Add the following:  Furnishing, maintaining and operating the certified scale on the Anchorage side of Bird Creek bridge is subsidiary to Item 203(3), Unclassified Excavation and no separate payment shall be made.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(12) Drain Holes | Meter |
| ***Deleted*** |  |
| ***Deleted*** |  |
| ***Deleted*** |  |

SECTION 204

STRUCTURE EXCAVATION FOR CONDITS

AND MINOR STRUCTURES

#### Special Provisions

204-3.01 CONSTRUCTION REQUIREMENTS.  Add the following to the third paragraph:  Native material may be utilized for Utility Backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, As specified in Subsection 703-2.07 Selected Material.  Compaction may be as approved by the Engineer.

    - BASIS OF PAYMENT.  Delete the second paragraph and substitute the following:

When item 204(1), Structure Excavation, does not appear in the bid schedule, structure excavation required to complete other items of work will be subsidiary except that excavation and disposal of unsuitable material required from below a plane 450 mm below the invert elevation of conduits and 450 mm below the bottom of structures will be paid for as extra work.

Add the following Section:

SECTION 240

RAILROAD

240-1.01 GENERAL.  The contractor shall be responsible for all railroad trackwork and construction items associated with this project to the limits shown.  All work on ARRC property shall be conducted in strict accordance with the requirements contained in Section 107-1.08 RAILWAY PROVISIONS of these specifications.  Unless otherwise specified, all track materials and work methods shall comply with the applicable standards contained herein.

240-1.02 SUMMARY OF WORK.  The work involved in this project consists of, but is not necessarily limited to, the following activities:

1.	Remove existing track to the excavation limits shown.

2.	Install new track as specified on the Plans for the trackwork area.

3.	Surface main line tracks and raise to design line and grade.

4.	Install temporary and permanent grade crossings.

240-1.03 DEFINITIONS

- ARRC. Alaska Railroad Corporation

- AREA and AREMA.  American Railway Engineering Association and its successor organization,

- American Railway Engineering and  Maintenance-of-way Association.

## W.C.L.I.B. West Coast Lumberman’s Inspection Bureau

## FRA.  Federal Railroad Administration

240-1.04 REFERENCED STANDARDS

- ARRC  Standard Plans, Ballast and Trackwork.

- AREA/AREMA Manual for Railway Engineering–Fixed Properties

- AREA/AREMA Portfolio of Trackwork Plans

- All standards listed in each section of these specifications, but referenced thereafter by a basic designation only i.e. AREA/AREMA, form a part of the specifications to the extent indicated by the reference.  The most recent edition of the standard at the time of advertising shall apply.

240-1.05 REFERENCED DRAWINGS  Alaska Rail Road Standard Drawings list on the title sheet of the Plans.

240-1.06 STORAGE  Storage facilities shall be in areas designated by the Engineer.

240-1.07 CLEAN-UP  At the end of each days work, the job site shall be cleaned up and left in a neat and workman like condition.

Before calling for a final inspection the entire premises shall be cleaned up to the satisfaction of the Engineer.

240-1.08 SURVEYING  All surveying work necessary for the performance of this project shall be furnished by the contractor.

240-1.09 OWNERSHIP  All tracks and crossing materials replaced by new materials will become your property.

Add the following Section:

SECTION 241

RAILROAD BALLAST

241-1.01 DESCRIPTION. This work shall consist of furnishing, placing, tamping and shaping railroad ballast and surfacing and lining new and existing track and turnout, in conformance with the lines, grades and thickness’ shown on the Plans.

241-2.01   MATERIALS.  Subballast shall consist of material meeting the minimum requirements of Section 301, Aggregate Base Course, Type C-1.  Prepared ballast shall be crushed shot rock or crushed pit-run rock, size no. 4A, composed of hard, strong and durable particles, free from injurious amounts of deleterious substances and conforming to the following test standards:

TEST	TEST PROCEDURE	TEST STANDARD

Gradation Tests:

Sampling Aggregates	ASTM D75

ASTM C702

Sieves with Square Openings	ASTM E11

Sieve Analysis	ASTM C136	See table below

Materials Finer Than No. 200	ASTM C117	See table below

Material Quality Tests:

Bulk Specific Gravity	ASTM C127	 2.60 min.

Absorption	ASTM C127	0.5% max.

Magnesium Sulfate Soundness	ASTM C88

(Five Cycles)	1.0% max.

Clay Lumps & Friable Particles	ASTM C142	0.5% max.

Flat and/or Elongated Particles	USACE CRD-C119	5.0% max.

Degradation (LA Abrasion)	ASTM C535	 35% max.

Mill Abrasion	see description below	   9% max.

Abrasion Number	see description below	    55 max.

Fractured Particles	see description below	 80% min.

TYPE 4A

BALLAST GRADATIONS

| Sieve Size | ### Percent Passing |
| --- | --- |
| 63 mm (2-1/2") | 100 |
| 50 mm (2") | 90-100 |
| 37.5 mm (1-1/2") | 60-95 |
| 25 mm (1") | 10-35 |
| 19 mm (3/4") | 0-10 |
| 9.5 mm (3/8") | 0-3 |
| 0.075 mm (No. 200) | 0-0.3 |

MILL ABRASION TEST DESCRIPTION

A representative sample is obtained and sized using the current ASTM Methods of Test.  From the coarse aggregate, split a representative portion into a sample consisting of 1.5 kg (3.3 lb.) passing the 37.5 mm (1-1/2”) sieve and retained on the 25 mm (1”) sieve plus 1.5 kg (3.3 lb.) passing the 25 mm (1”) sieve and retained on the 19 mm (3/4”) sieve.  The sample shall be washed and oven dried in accordance with the Los Angeles abrasion procedure.  The sample will then be placed in a 3.79 liter (1 gallon) 229 mm (9”) external diameter porcelain ball mill pot, along with 2.99 kg (6.6 lb.) of distilled water.  The mill shall be rotated at 33 rpm for a total of 10,000 revolutions (five hours).  The sample shall then be wash-sieved through a 0.075 mm (No. 200) sieve and oven dried before weighing.  Mill abrasion shall be calculated as a percentage loss in weight by the following formula:

Mill Abrasion = (Loss in Weight / Original Weight) x 100

ABRASION NUMBER

The Abrasion Number is a number calculated with the results of the Los Angeles Abrasion Test and the Mill Abrasion Test given in this specification.  The Abrasion Number shall be calculated by the following formula:

Abrasion Number = LA Abrasion Number + (5 x Mill Abrasion Number)

Fractured Particles Test:

A representative sample is obtained and sized using current ASTM methods of Test. From each coarse aggregate fraction representing five percent or more of the submitted sample, split a representative portion into samples of within 10 percent of the weight specified below:

| Sieve Passing | Sieve Passing | Mass in Kilograms (Lbs.) +/- 10 percent |
| --- | --- | --- |
| 63 mm (2 ½") | 50 mm (2") | 5.90 (13.00) |
| 50 mm (2") | 37.5 mm (1 ½") | 5.31 (11.70) |
| 37.5 mm (1 ½") | 25 mm (1") | 2.06 (4.55) |
| 25 mm (1") | 19 mm (3/4") | 0.59 (1.30) |
| 19 mm (3/4") | 12.5 mm (½") | 0.18 (0.39) |
| 9.5 mm (3/8") | 4.75 mm (No. 4) | 0.06 (0.13) |

Each sample shall then be separated into fractured and non-fractured particles according to the following criteria:

A fractured particle shall be a particle with three or more fractured faces.  Each of the fractured faces on the fractured particle must have a freshly exposed rock surface with a maximum dimension of at least one third the maximum particle dimension and a minimum dimension of at least one quarter of the maximum particle dimension.  The included angle formed by the intersection of the average planes of adjoining fractured faces must be less than 135 degrees for each of the faces to be considered as separate fractured faces.

For example, a particle just retained on the 50 mm (2”) screen (i.e. particle size = 50 mm (2”)) must have at a minimum:

1.	a freshly exposed maximum face of between 17 mm (2/3”) and 50 mm (2”) and

2.	a second freshly exposed face with a minimum dimension of 13 mm (1/2”), and

3.	a third freshly exposed face ranging in dimension between the other two.

The angle formed between any two of these faces must not exceed 135 degrees.

Particles which do not meet the above criterion will be classified as non fractured faces.

The fractured particles for each sample will be calculated as a percentage by the following formula:

Fractured Particles = Weight of fractured particles x 100

Original Weight

Engage the service of a qualified Professional Engineer registered in the State of Alaska to oversee performance of the referenced test in the rock source and the processed ballast. All sampling and testing shall be done either by the Professional Engineer himself or by a qualified and experienced technician working under the direction of the Professional Engineer. Samples of processed ballast shall be taken directly off the belt to minimize segregation and contamination. Material quality tests shall be done by a testing laboratory selected by the Contractor and approved by the ARRC.

The frequency of tests shall be as follows:

1.	Pre-Manufacturing Tests: Prior to production of ballast, submit whole and crushed samples of the proposed source rock along with test reports that verify that they conform to the Specifications.

2.	Start-up Manufacturing Test: When ballast manufacturing begins another full battery of tests shall be run to verify that the ballast manufactured conforms to the specifications.

3.	Periodic Full Testing: Whenever the nature of the source rock changes significantly, such that conformance with  specifications is in doubt, above tests shall be redone as appropriate to verify conformance and the results submitted for approval.

4.	Periodic Gradation Testing: The gradation tests and visual monitoring of degree of fracture shall be performed during manufacturing on every 750 cubic meters (1,000 cubic yards) of ballast that is produced, but at least daily. A complete fractured particle test shall be run on every 3,750 cubic meters (5,000 cubic yards) of ballast manufactured.

All test reports shall be submitted to the State for approval. The Professional Engineer shall verify that all test reports are accurate and shall indicate whether or not they conform to these specifications. Any tests that fail to conform shall be brought to the immediate attention of the State's Project Manager and immediate steps shall be taken to bring manufacturing into conformance.

#### CONSTRUCTION REQUIREMENTS

241-3.01   GENERAL. The ballast shall be manufactured, handled, stockpiled and delivered in such a manner that it is kept clean and free from segregation. Stockpiling of ballast will only be allowed over firm stable base areas. In order to minimize segregation, ballast shall be stockpiled in more or less horizontal layers with no dumping over the sides of the stockpile allowed. Travel of construction machinery and other vehicles over the top of the stockpile shall be kept to a minimum. Ballast dumped on subgrade prior to track or turnout construction shall be kept free from material tracked in by construction equipment. Ballast dumped on skeleton track and turnouts shall be distributed uniformly during the dumping operation to minimize the carrying or regulating required to provide the designed ballast section.

241-3.02   BALLAST HANDLING.  Ballast shall be kept clean and free from segregation during handling and placing operations. Contractor shall submit his plan for handling and placing ballast. This plan shall include source, type of equipment to be used, location of stockpiles, and method of distribution.

241-3.03  PLACEMENT OF INITIAL BALLAST.  An initial layer or layers of ballast may be uniformly distributed over the finished sub-ballast and compacted before tie distribution at the option of the Contractor. The initial layer of ballast shall be limited to a total compacted depth that will establish the track surface at least 2 in. below final grade. Subgrade fouled or disturbed by Contractor's operations shall be repaired by Contractor at no additional cost to State.

1.	Each lift of ballast within the initial layers shall be uniformly spread and compacted with not less than two passes of a vibratory compactor with the following characteristics:

Gross weight		2,268 kg (5000 lbs.) minimum

Drum width		1,448 mm (57 in.) minimum

Drum diameter	1,016 mm (40 in.) minimum

Each compacted lift within the initial layers shall not exceed a depth of 100 mm.

2.	The vibratory compactor shall have a weight of not less than 2,268 kg (5000 lbs.) and shall be capable of applying a dynamic load of not less than 8,165 kg (18,000 lbs.) at a frequency between 1,100 to 2,000 vibrations per minute. The compacting equipment selected by Contractor shall be subject to inspection and acceptance by Engineer.

241-3.04   SURFACING OF TRACK  Ballast placed between the limits shown on the Plans shall be placed with equipment that will not damage the cross ties or the spiking and anchoring holding capacity.

1.	Vibratory squeeze-type tampers shall be used to compact ballast after final vertical track alignment has been achieved. Tools shall be maintained to manufacturer's specifications. Ballast shall be packed tightly under and around the tie from a point 457 mm (18 in.) inside each rail on both sides of the tie to the ends of the tie. Ballast around the center of the tie between the above limits shall not be compacted.

2.	Contractor shall prepare for Engineer's review and approval a detailed tamping procedure specification covering tamping equipment methods. The specification shall include a complete description of equipment to be used and variables that can be adjusted such as:

a.	Number of insertions of tamping tools per tie.

b.	Number of passes of tamping machine.

c.	Depth of penetration.

After tamping is complete, ballast shall be regulated to the design ballast section and all ballast removed from the top of cross ties, tie plates and base of rail. Contractor shall prepare for Engineer's review and approval a detailed raising, aligning, tamping and regulating procedure.

241-3.05 TEMPORARY CROSSING.

1.	When regular railroad crossing are used as haul routes inside or outside the permit area, flagmen shall be provided by the Contractor for said crossings in all situations at the discretion of the Railroad.

2.	Temporary road crossings may be installed, provided the Contractor has acquired from the Railroad a temporary road crossing permit for said crossing.

The temporary crossing shall be constructed to the standards specified in the temporary crossing permit.  All protective signs required by the Railroad shall be provided and properly maintained by the Contractor.  When a temporary railroad crossing is in use, Railroad flag protection shall be provided at all times in accordance with Subsection 107-1.08.6. When not in use during the winter season, the temporary crossing shall be removed unless specifically allowed in the temporary crossing permit.  Upon completion of the work or termination of the temporary crossing permit, the temporary railroad crossing shall be removed and the area restored to its original condition.

3.	The flange ways of all road crossing used by the Contractor or subcontractor as haul routes or temporary road crossings shall be kept free of gravel at all times and shall otherwise be maintained to the satisfaction of the Railroad’s Chief Engineer.

4.	When a temporary or private road crossing is not in use, provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

241-4.01  METHOD OF MEASUREMENT. Subballast and ballast placed as shown on the Plans will be measured by the megagram in accordance with Section 109.

241-5.01  BASIS OF PAYMENT.  The accepted quantity of subballast and ballast will be paid for at the contract unit price per megagram for pay item shown in the bid schedule, complete in place.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 241(1) Railroad Ballast | Megagram |
| 241(2) Railroad Subballast | Megagram |

# SECTION 242

# TRACKWORK

242-1.01   DESCRIPTION.   This work consists of furnishing and constructing skeleton track to the alignment and limits shown on the Plans.  This work will also include removal of existing track and crossing materials at the proposed road crossings.

242-2.01   MATERIALS.   Purchase and deliver all track material to construct skeleton track. The material shall conform to the current AREA/AREMA "Manual for Railway Engineering" and as detailed in this specification.

1.	New Standard Carbon Rail: Rail shall be 115# RE Rail Section and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends. Rail shall be end hardened, 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

2.	New High Strength Rail: Rail shall be 115# RE Rail Section and have a Brinell Hardness range of 341-388. Rail may be either head hardened or fully heat treated and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends for 6-hole joint bars. Rail shall be 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

3.	Track Spikes: Use Pandrol screws or approved screws.

4.	Rail Anchors: Use Pandrol clips or approved rail anchors.

5.	Tie Plates: Use Pandrol plates or approved plates.

6.	Angle Joint Bars: Angle joint bars shall be new 900 mm (36") headfree, standard toeless, 6 holes for 115# rail with hole spacing to fit rail drilling per ARRC plan 5.12. Joint bars shall be quenched or medium carbon steel, rolled steel only, heat #16. Hole diameter shall be 31.75 mm (1-1/4").

7.	Track Bolts, Nuts & Washers: Bolts and nuts shall be new and manufactured in accordance with AREA/AREMA Section 4.1.15. Bolts shall be of the appropriate size for the bolt hole of the rail and bar and sufficient length for a full nut, lockwasher and 1 ½ threads exposed after tightening, but not to exceed a 25 mm (1") exposure after tightening. Lockwashers shall be new per ARRC Plan No. 7 and sized for the bolt diameter.

8.	Cross Ties: Cross ties shall be treated 175 mm x 225 mm x 2.59 m (7” x 9” x 8’-6”) per ARRC Standard Plan 1.13.  Cross ties shall be manufactured in accordance with AREA/AREMA Manual for Railway Engineering, Chapter 3; W.C.L.I.B. Grading Rules #17, paragraph 192b; and this specification.  Hardwood ties shall be used.

- Timber: Cross ties shall be sawn from sound, straight live timber, free from any defect that might impair durability and/or strength. Multiples or combinations will not be accepted. Cross ties shall be cut square at the ends and have all bark that impairs treatablility entirely removed.

b.	Stump Pull: Stump pulls will be graded the same as holes or splits in the end of a tie. Cross ties with a stump pull that goes into the interior more than 127 mm (5") will be rejected.

c.	Wane: Cross ties shall have a minimum 203 mm (8 in.) face. Minimum face specifications apply to the entire length of the cross tie. All wane shall be free of bark.

d.	Knots: A knot exceeding in diameter 1/4 of the width of the surface on which it appears will be rejected if it occurs in the rail bearing area. Outside the rail bearing area, knots will be accepted up to a diameter of 1/3 of the surface on which they appear. A cluster of knots will be judged as being a large knot in damaging effect. Rail bearing area shall be defined as 508 mm (20") to 1,016 mm (40") from center of tie.

e.	Cross Grain: Any cross tie with cross grain exceeding one in fifteen will be rejected.

f.	Straightness: A cross tie will be considered straight when (1) a straight line along the top from middle of one end to middle of the other end is not closer than 76 mm (3") from either side of tie, and (2) when a straight line along a side from middle on one end to the middle of the other end is everywhere more than 63.5 mm (2 ½") from top or bottom of the tie.

g.	Bark: Any cross tie containing more than a minimal amount of ingrown bark will be rejected.

h.	Saw Kerf: A saw kerf is not required.

i.	Mill of Manufacture Certification: A mill certification is required indicating that inspections have been performed and that the product is in conformance with specifications. The mill certification must also indicate the species of wood. All ties which pass the inspection will be clearly marked and identified as ARRC ties; unmarked ties will not be accepted.

j.	Treatment: All treatment shall meet the specifications of the American Wood Preservers Association Standards Book C6 ant the following guidelines. A treatment report shall be accurately completed for all charges and at a minimum shall contain the following:

i 	Charge number

ii	Date

iii	Wood species and size

iv	Total retort time in hours

v	Conditioning time in hours

vi	Pressing time in hours

vii	Retention in pounds per cubic meter

viii	Average penetration to be shown for oak

ix	Initial air time, if applicable

x	Gauge readings and times

xi	Treating operator's signature

xii	Seasoned condition (dry or green), if green show moisture content.

xiii	Final Vacuum

xiv	Wright of solution at 38° C (100° F)

xv	Work tank number and cylinder number

The preservative shall consist of a mixture of 50 percent by volume of creosote oil and 50 percent by volume of residuum oil, 50/50 coal tar

solution may also be used. Final readings shall be entered on the treating report. Treating reports and charts shall become a permanent record maintained by the treating company with open access to ARRC personnel.

- Care of Treated Wood: Extreme care shall be used in handling treated cross ties to avoid damage to the edges of the timbers or breaking through the treated portions and exposing untreated wood. The use of peavies, cant hooks, pickaroons, long hooks or pointed tools shall be such as not to break through the treated portion of the wood. If damage during handling which could potentially impair the longevity of material service life, this material shall then be retreated at the vendor's expense. All cost associated with retreatment, including oil, shall be the responsibility of the vendor.

l.	Boring: All cross ties shall be bored and adzed in conformance to the ARRC Standard Tie Boring and Adzing Plan 1.13. Adzing may be deleted if vendor will certify that ties furnished will be flat and provide a uniform bearing surface for the tie plates.

m.	Anti-splitting Devices: All hardwood cross ties shall have steel multi-nail anti-splitting end plates in accordance with AREA/AREMA Manual of Railway Engineering, Chapter 3, Section 1.8 titled "Ties and Wood Preservation", Section 1.9.2.3 titled "Nail Plates", and Section 1.10.3 titled "Nail Plates".

n.	Species:   Acceptable hardwood species are Red Oak, White Oak, Hickory, Black Walnut, Gum, Beech, Ash, White Heart Sycamore, Hackberry and Hard Maple.

242-3.01   CONSTRUCTION REQUIREMENTS .   Track construction shall be performed in accordance with the ARRC Standards, AREA/AREMA Manual for Railway Engineering and as specified in this document. Scope of construction includes but is not limited to, unloading and distribution of track material, distribution and spacing of cross ties, laying, bolting and spiking rail, field welding of joint rail, placing rail anchors, raising, aligning and tamping track, and shaping ballast to the design section.

Construction procedures and methods shall be employed that keep the railroad sub-ballast and ballast sections from becoming rutted or disturbed and any operation that causes damage shall be stopped immediately. Alternate construction methods shall be instituted.

All existing track material removed will become the property of  the Contractor. These materials shall be removed from the ARRC right-of way.

242-3.02   TRACK ALIGNMENT AND GEOMETRY.   The track shall be constructed to the alignment and profile indicated, or as adjusted by Engineer, within the tolerances specified. Contractor shall designate right or left rail, while facing in the direction of increasing stationing, to control the grade of all tangent tracks on a contract-wide basis.  Low rail on curves shall be the profile grade rail.  High rail on curves shall be the line rail.

Track centers between main line and future mainline will be maintained at 4.572 m (15’-0”) within the project area.

242-3.03   TOLERANCES.   Deviations from indicated gauge, cross level, horizontal line, profile grade, and tie spacing shall conform to the following requirements:

1.	Gage: Shall be 1,435 mm (4’-8 ½”) plus or minus 3 mm (1/8”).

2.	Cross Level and Superelevation: Shall be plus or minus 3 mm (1/8”) from level on tangent or design superelevation on curve.

3.	Deviation from Horizontal Alignment: Plus or minus 6 mm (¼”) in a 19 m (62’) chord. Plus or minus 13 mm (½”) total except in road crossings where total deviation shall be plus or minus 6 mm (¼”).

4.	Deviation from Profile Grade: Shall not exceed plus or minus 6 mm (¼”) in 19 m (62’) chord or a total of plus or minus 13 mm (½”).

5.	Tie Spacing: Distance between centerline on adjacent ties shall be 495 mm (19 ½”) and not vary more than plus or minus 25 mm (1”) from the indicated spacing, with the additional requirements that 48 ties shall be installed per 23.8 m (78’) of track.

242-3.04   CROSS TIE DISTRIBUTION.   Contractor shall receive cross ties from supplier and transport them to the work area in accordance with the AREA/AREMA "Handling of Ties from the Tree into the Track". Ties shall be placed on a smooth, compacted surface as specified herein, spaced as shown within specified tolerances, and laid normal to the centerline of track with heartwood face down. Line ends of ties in trackage shall be aligned uniformly on the right side of track when facing increased stationing.

242-3.05  TIE PLATES AND SCREWS.  Tie plates shall be attached to the cross ties with line and hold-down screws to the indicated patterns. Contractor may pre-plate cross ties prior to distribution. If Contractor chooses to pre-plate the cross ties, he shall furnish any additional material required at no added cost to Owner. Contractor shall use a jig to compensate for fabrication tolerances to achieve track gage tolerances.

242-3.06  RAIL LAYING   Standard carbon rail shall be used on all tangent track and curves up to four degrees. High strength rail shall be used on curved track over four degrees and through the crossings. Rail shall be laid in accordance with the details and procedures that follow:

1.	Rail Distribution; Rails shall be distributed along the roadbed with the head of the rail up and in such a manner and using equipment that will prevent damage to them. Dropping rails from the sides of railcars or trucks will not be permitted.

2.	Rail Laying: The base of the rail and surface of the tie and tie plate shall be cleaned prior to laying. Rails shall be laid one at a time without bumping or striking. Rail ends shall be brought squarely together against the expansion shims and completely bolted before spiking. Rails shall be laid so that the joints in opposite rails are staggered not less than 6 m (20’)apart, plus or minus 610 mm (24”), except closer joints may be required at turnouts or roadway crossings. Rails of less than standard length shall be used to space the joints on curves. Rails shorter than 4.6 m (15’) shall not be used. Rail shall be laid or welded so that no joints are in grade crossings.

3.	Rail Cutting and Drilling: Rails shall be cut square and clean by means of rail saws. Holes for complete bolting of cut rail shall be precisely marked, center punched and drilled using an exact template for alignment. In no instance shall marking through, or drilling through joint bars be allowed. Holes shall be deburred. New holes shall not be drilled between two holes already drilled. Burning or cutting of rails or bolt holes by means of an acetylene torch will not be permitted. All cut rail ends shall be beveled at the head and be hardened to conform to AREA/AREMA "Manual Specifications for Steel Rails", Supplementary Requirement S1.

4.	Rail Joints: The fishing surface of the rails and joint-bars shall be wire-brushed to remove rust before assembly. Allowance for rail expansion shall be made at all joints by the use of expansion shims placed between the ends of adjacent rails. The proper expansion allowance shall be determined by the use of the following table refer to AREMA chapter 5, paragraph 5.3.1 for shim thickness to use for 12 m (39’) rail.

| Rail Temperature °C (°F) | Shim Thickness in mm (") for 23.8 m-24.4 m (78’- 80’) rail |
| --- | --- |
| Below 2 (35) | 8 (5/16) |
| 2 to 8 (35-47) | 6.4 (1/4) |
| 9 to 15 (48-60) | 4.8 (3/16) |
| 16 to23 (61-73) | 3.2 (1/8) |
| 24 to 30 (74-85) | 1.6 (1/16) |
| Over 30 (Over 85) | None |

For shorter lengths of rail, proportionate shim thickness’ shall be used. The temperature of the rails shall be determined by the use of an AREA standard rail thermometer, placed on the base of the rails close to the web on the side shaded from the sun. Sufficient time shall be allowed to accurately record the temperature. Care shall be taken to assure that shims are not squeezed or damaged during installation of shims or rails. Shims shall be removed from between rail ends as soon as the bolts have been tightened and the rail anchors applied. All track bolts shall be installed when the rail is laid and tightened before spiking.

Final bolt tension shall be between 89 and 133 kN (20,000 and 30,000 lbs.). Bolts shall be tightened once, at the time of rail installation. Final tension shall be checked and adjusted as necessary just prior to final acceptance per AREMA chapter 5, paragraph 5.5.2.

5.	Rail Anchoring: Use Pandrol clips or approved rail anchors.

242-4.01 METHOD OF MEASUREMENT. Railroad Trackwork will be measured by the meter along the center line of track beginning at the centerline of the first cross ties and ending at the centerline of the last cross tie. Measurement will not include track within the limits of turnouts which begin at the first switch tie and continue to the last long switch tie for each turnout.

Trackwork Removal shall be measured as a Lump Sum for the removal of all trackwork, turnouts and grade crossings.

242-5.01 BASIS OF PAYMENT. If the Contractor calls for flagmen and, through no fault of the Department or the Railroad, the flagmen are not needed, payment shall be deducted from monies due the Contractor. Other flagging, required by the Contractor's operation, shall be paid for by the Contractor.

All traffic control measures required will be paid for separately under their respective pay items.

The accepted quantity of trackwork will be paid for at the contract unit price, per meter for the pay item shown in the bid schedule, complete in place.

The accepted quantity of trackwork removal will be paid for at the contract Lump Sum amount. All required grading and shaping of existing track embankment shall be subsidiary to Item 244(1) Trackwork Removal.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 242(1) Railroad Trackwork | Meter |
| 242(2) Trackwork Removal | Lump Sum |

Delete Section 617 in its entirety and add the following Section:

### SECTION 245

# GRADE CROSSINGS

245-1.01  DESCRIPTION. This work consists of furnishing and constructing permanent wood plank crossings to the alignment and location shown on the Plans.  All trackwork shall be in accordance with Section 242  of the specifications and shall be scheduled with the ARRC through the Engineer.

245-2.01  MATERIALS. Furnish and deliver all material required to construct the grade crossings.  The material shall conform to the current AREA/AREMA specifications and as detailed in this specification.  All standard track material shall conform to Section 242 of these specifications.

1.        Cross Ties:   Cross ties shall be new hardwood as specified in Section 242 except length shall be adjusted to meet installation requirements.

2.	Ballast:   Construction and placement of ballast shall conform to section 241 of these specifications.

3.	Sub-Ballast:   Construction and placement of subballast shall conform to section 241 of these specifications.

4.	Geotextile Fabric:  Geotextile fabric shall be non woven fabric meeting the requirements of AREMA Chapter 1 and shall be heavy class.  Fabric specifications and sample shall be submitted for review prior to purchase and installation.

##### CONSTRUCTION REQUIREMENTS

    - GENERAL. Grade crossing construction shall be performed in accordance with ARRC standards, AREA/AREMA Manual Part 8 and as specified in this document.  Scope of construction includes but is not limited to, unloading and distribution of crossing materials and installation on prepared subgrade and sub-ballast sections.

245-3.02    RAIL.  Rail within the road crossing and for at least 6 m on either side of the crossing shall  be unjointed 52 kg RE as specified in Section 242-2.01.

245-4.01   METHOD OF MEASUREMENT.  Item 245(1), Grade Crossing will not be measured.

245-5.01  BASIS OF PAYMENT.   All excavation and backfill required for this work is subsidiary to Item 245(1), Grade Crossing and no separate payment shall be made.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 245(1) Grade Crossing | Lump Sum |

***Deleted***

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (09/01/89)R26

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/01/91)R116

Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(02/28/01)R176M98

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14  Joints.  Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

***Deleted***

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, ***Deleted*** the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One 150 mm diameter core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-4 and applied under Item 401(6), Asphalt Price Adjustment.

TABLE 401-4

| Average Profile Index (PrI) (Millimeters per 1000 Lane Meters) | Adjustment to Item 401(6), Asphalt Price Adjustment, for Pavement Smoothness |
| --- | --- |
| 0 to 60 | Add $335 multiplied by (61PrI) |
| 61 to 94 | No Adjustment |
| 95 and greater | Deduct $335 multiplied by (PrI94) but not to exceed $10,000 |

(08/19/02)R199M98

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $1,500.00 each.

Add the following Section	SECTION 407

STONE MASTIC ASPHALT CONCRETE

Special Provisions

407-1.01  DESCRIPTION.  This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thickness shown on the Plans.

407-2.01  COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN.  Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

Provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

Submit the following to the Engineer at least 15 working days prior to the production of Stone Mastic Asphalt Concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed Job Mix Design gradation must meet the requirements of Table 703-9, Stone Mastic Asphalt Concrete Aggregate.  Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.  Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended.  Total sample size of 225 kilograms proportioned to the Job Mix Design blend.

3.	A minimum of twenty liters, in four-liter metal containers, of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a recommended mixing temperature.

4.	A minimum 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 2.5 kilogram sample of the cellulose stabilizing additive proposed for use in the mixture, including name of product, manufacture, test results as required in Section 407-2.05 and manufactures certificate of compliance with Section 407-2.05.

The Engineer will then evaluate the material and the proposed gradation using the Superpave Gyratory Compactor, AASHTO PP 41, and the mix design requirements of Table 407-1 to establish the Job Mix Design.  Approved Job Mix Designs will become a part of the contract and will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.  Up to15 working days will be required to determine the Job Mix Design after receipt of all items specified above.

TABLE 407-1

STONE MASTIC ASPHALT CONCRETE

MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement |
| --- | --- |
| Voids in total mix, percent | 4 |
| Compaction Gyrations, NDesign | 100 |
| Dust-asphalt ratio (the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement, by weight of mix) | 0.6-1.6 |
| Voids in the mineral aggregate (VMA), min. Voids In Coarse Aggregate (VCA) Of The Mix, % Rut Index, mm, maximum. Minimum Asphalt Cement Content, % | 18.0 Less Than VCA Of The Coarse Aggregate As Determined By AASHTO T 19 3 6.2 |

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $2,500.00 each.

407-2.02  AGGREGATES.  Aggregates shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.13.  Use a minimum of three stockpiles for crushed Stone Mastic Asphalt Concrete aggregate (coarse, intermediate, and fine).

407-2.03  ASPHALT MATERIALS.  Provide the grade of asphalt cement specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  When not specified, the grade of asphalt cement shall be PG 64-28.

Asphalt cement may be conditionally accepted at the source by providing a manufacture's certificate of compliance in accordance with Subsection 106-1.05, and test results of the applicable quality requirements of Section 702 before the material is shipped.

407-2.04  ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05  STABILIZING ADDITIVES.  Use cellulose stabilizing additive.  The dosage rate for cellulose is 0.3 percent by weight of the total mix.  The allowable tolerance per megagram shall not exceed ± 10 percent of the required weight of the stabilizing additive.

Cellulose stabilizing additive shall conform to the properties shown in Table 407-2.

TABLE 407-2

CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis(1): Fiber Length Percent passing No. 100 sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing No. 20 sieve Percent passing No. 40 sieve Percent passing No. 140 sieve | 0.25 in. (max) 60-80 0.035-0.060 in. (avg.) 75-95 55-75 10-30 |
| Ash Content(3) | 20% non-volatiles (max) |
| pH(4) | 7.5 +/-1.0 |
| Oil Absorption(5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content(6) | < 5% |
| Bulk Density(7) | 1.25-2.50 lbs/ft3 |

Notes:

(1)	Method A - Alpine Sieve Analysis.  This test is performed using an Alpine Air Jet Sieve (Type 200 LS).  A representative 5 gram sample of fiber is sieved for 14 minutes at a controlled vacuum of 22 inches (+/- 3 inches) of water.  The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis.  This test is performed using No. 20, 40, 60, 80, 100, and 140 sieves, nylon brushes and a shaker.  A representative 10 gram sample of fiber is sieved, using a shaker and two nylon brushes on each screen.  The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content.  A representative 2-3 gram sample of fiber is placed in a tared crucible and heated between 1100 and 1200 F for not less than two hours.  The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test.  5 grams of fiber is added to 100 ml of distilled water, stirred and let sit for 30 minutes.  The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test.  5 grams of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation.  It is then placed in a screen mesh strainer (approximately 0.5 square millimeter hole size) and shaken on a wrist action shaker for ten minutes (approximately 1.25inch  motion at 240 shakes/minute).  The shaken mass is then transferred without touching, to a tared container and weighed.  Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content.  10 grams of fiber is weighed and placed in a 250 F forced air oven for two hours.  The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density.  Fluff fiber with air or Hobart Mixer, weigh out 25 grams of fiber, place in 100 ml cylinder, tap cylinder and measure volume.

407-2.06  PROCESS QUALITY CONTROL.  Sample and test materials for process QC of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.03.

Failure to perform process QC forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

CONSTRUCTION REQUIREMENTS

407-3.01  WEATHER LIMITATIONS.  Do not place Stone Mastic Asphalt Concrete mixture when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  Do not place Stone Mastic Asphalt Concrete mixture after August 15 of any year.

407-3.02  EQUIPMENT.  Use equipment in good working order and free of asphalt concrete mix buildup.  Make all equipment available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

407-3.03  BITUMINOUS MIXING PLANTS.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.    Maintain a current Air Quality Permit  issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

407-3.04  HAULING EQUIPMENT.  Haul Stone Mastic Asphalt Concrete mixture in trucks with tight, clean, smooth metal beds thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent.  Do not use any petroleum product (e.g. diesel or fuel oil) as an asphalt release agent.

Cover the Stone Mastic Asphalt Concrete mixture with a secured watertight canvas cover extending at least 0.3 meters over the sides and ends of the truck bed.

407-3.05  ASPHALT PAVERS.   Use self-propelled asphalt pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a mobile string-line (ski) at least 9 meters in length, or other approved grade follower to automatically actuate the paver screed control system. Use grade control on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip asphalt pavers with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip receiving hoppers with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Place auger extensions within 0.3 meters of the screed extension on both sides, or per written manufacturer’s recommendations.

The use of a pickup machine to transfer Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collecting the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06  ROLLERS.  Supply a minimum of three rollers weighing a minimum of 11 megagrams each to compact the Stone Mastic Asphalt Concrete mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel or vibratory steel wheel type.  Use self-propelled rollers specifically designed to compact hot asphalt concrete mixtures and capable of reversing without backlash.  The use of equipment which results in crushing of the aggregate, or pick-up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

Follow the paving plan established for the project.

407-3.07  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces in conformance with the plans and specifications.  Clean existing paved surfaces of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After completion of planing of a section of the roadway, that section shall be inspected by the Engineer for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  Backfill the excavated area with crushed aggregate base course material in conformance with the requirements of Section 301, asphalt concrete leveling course, or with Stone Mastic Asphalt Concrete as directed by the Engineer.

Prior to placing Stone Mastic Asphalt Concrete mixture, uniformly coat pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures with tack coat material conforming to Section 402.

407-3.08  PREPARATION OF ASPHALT.  Provide a continuous supply of the asphalt cement to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09  PREPARATION OF AGGREGATES.    Provide adequate dry storage for the mineral filler and stabilizing additive.  Dry the aggregate for Stone Mastic Asphalt Concrete so the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled from the end of the auger, or from behind the screed prior to compaction, is less than 0.5% (by total weight of mix) as determined by WAQTC TM 6.

Heat the aggregate for Stone Mastic Asphalt Concrete to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Stone Mastic Asphalt Concrete mixture in which soot or fuel is present is considered unacceptable per Subsection 105-1.11.

407-3.10  MIXING.  Uniformly combine the aggregate, asphalt cement, additives, and stabilizing additives in the amounts required by the Job Mix Design.  Mix the materials such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants.  Add the stabilizing additive through a separate inlet directly into the weigh hopper above the pugmill.  Time the addition of the stabilizing additive to occur during the hot aggregate charging of the hopper.  Provide adequate dry mixing time to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants.  Add cellulose stabilizing additive into the drum mixer at the same point the asphalt cement is added.    Operate the drum mixer to ensure complete blending of the stabilizing additive into the mix.

Dry mix Stone Mastic Asphalt Concrete with cellulose stabilizing additive a minimum of 15 seconds, and wet mix a minimum of 40 seconds.  In batch plants, place the dry aggregate in motion immediately prior to the addition of asphalt cement.  Use a wet mixing time adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

Mix the Stone Mastic Asphalt Concrete within the temperature range determined by the Job Mix Design.

Proportion the mineral filler into the mixture uniformly and in the desired quantities.  Provide appropriate equipment for accurately proportioning the relatively large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11  TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding Stone Mastic Asphalt Concrete mixture in silo type storage bins is permitted provided that the characteristics of the Stone Mastic Asphalt Concrete mixture are not altered.  Signs of visible segregation,  heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Dispose of rejected Stone Mastic Asphalt Concrete mixture at no cost to the Department.

407-3.12  SPREADING AND PLACING.  Submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, and weight of rollers, and number of impacts per 0.3 meter.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

Place Stone Mastic Asphalt Concrete mixture upon an approved surface, spread and strike off and compact to the required compacted thickness.  Spread and compact in one layer if the total thickness is 75 mm  or less.  Use asphalt pavers to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

Use hand tools to spread, rake, and lute the Stone Mastic Asphalt Concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.  In such areas, compact the Stone Mastic Asphalt Concrete mixture to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture which is contaminated or segregated will be rejected.

Pave adjacent traffic lanes to the same elevation within 24 hours when the section of roadway being paved is open to traffic unless prevented by weather or other factors beyond control.  Place approved material against the outside pavement edge when the drop-off exceeds 50 mm.

When multiple lifts are specified in the contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Do not pave against new concrete curb until it has cured for at least 72 hours.

407-3.13  COMPACTION.  Immediately after spreading, thoroughly and uniformly compact the Stone Mastic Asphalt Concrete mixture by rolling.

Roll with a minimum of three steel wheel rollers of a minimum weight of 11 megagrams each.  Follow the paving plan established for the project to provide the specified pavement density. Rollers with vibratory engaged may be used for a maximum of three passes.  Operate rollers at a uniform speed to obtain no less than 10-12 impacts per 0.3 meter with the drive roller nearest the paver.  Set rollers for high frequency and low amplitude.  Verify roller settings in the presence of the Engineer.  Roll until all roller marks are eliminated and the specified pavement density has been obtained.  Prevent adhesion of mixture to the rollers by moistening the wheels with water mixed with detergent or other approved material.  Replace rollers showing evidence of excessive pick-up.

Stop rolling operations once sufficient in-place density has been achieved.  Where migration of asphalt cement and filler to the compacted pavement surface has occurred, remove and replace with fresh Stone Mastic Asphalt Concrete mixture.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with WAQTC FOP for AASHTO T 209.  For the first lot of Stone Mastic Asphalt Concrete, the MSG will be determined by the Job Mix Design.  For additional lots, the MSG will be determined by the sample from the first sublot of the lot.  Acceptance testing for field density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.  (Acceptance testing for field density of leveling course will not be done.)

Grade with rakes and lutes and compact with mechanical tampers areas not accessible to rollers.  Use a trench roller in depressed areas to achieve the required compaction.

Remove any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective and replace with fresh Stone Mastic Asphalt Concrete mixture and compact to conform with surrounding areas.  Remove and replace any area showing an excess or deficiency of asphalt cement.

Do not leave rollers, other equipment, or vehicles standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14  JOINTS.  Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Remove full depth improperly formed joints resulting in surface irregularities, replace with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compact.  Do not roll joints after the material has cooled below 65 degrees Celsius.  All pavement removal shall be precut to a neat line with a power driven saw.

Apply a tack coat of asphalt cement or asphalt emulsion on all cold joints and allow to break prior to placing any fresh Stone Mastic Asphalt Concrete mixture against the joint.  Apply the tack coat just prior to paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset longitudinal joints in one layer from those in the layer immediately below by at least 150 mm.  Align the joints in the top layer at the centerline or lane lines.  Where pre-formed marking tape striping is required, offset the longitudinal joint in the top layer not more than  150 mm from the edge of the stripe.

407-3.15 SURFACE TOLERANCE.  The surface of the Stone Mastic Asphalt Concrete  will be measured after final rolling at selected locations using a 4.5meter straightedge.  Correct variations of the surface greater than 5 mm from the testing edge of the straightedge between any two contacts.

The Engineer will measure the surface smoothness of the top lift of the Stone Mastic Asphalt Concrete in all of the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace any portion of the top lift having a smoothness PrI greater than 230 mm/km in a 160 meter segment.

After completion of the corrective work, the Engineer will measure the pavement surface with an inertial profiler for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or matches with an existing pavement.  Smoothness will be measured in the left wheel path of each lane and reported as profilograph results (PrI) filtered with a 5 mm blanking band.  The PrI will be reported as a job average for all measured lanes, calculated to the nearest mm per km.

407-3.16  PATCHING DEFECTIVE AREAS.  Remove any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective.  Skin patching is not permitted.  Remove defective materials for the full thickness of the course.  Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with tack coat conforming to Section 402 and allow to cure.  Place and compact fresh Stone Mastic Asphalt Concrete mixture in sufficient quantity so that the finished surface conforms to grade and smoothness requirements.  Compact the Stone Mastic Asphalt Concrete mixture to the density specified.  No payment shall be made for material replacing defective material.  All costs associated with patching defective areas shall be borne by the Contractor.

407-3.17  TEST SECTION.  Place a minimum of 270 megagrams of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer at least 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving.  Use an underlying grade or pavement structure similar to project conditions for the test section.  Use the test section to verify plant calibration and compaction characteristics of the Stone Mastic Asphalt Concrete mixture.  Use the same equipment that will be used for the project.

Stone Mastic Asphalt Concrete mixture placed in the test strip that duplicates mix design parameters and meets specifications will be measured and paid for at contract prices.  No payment will be made for mixture that does not duplicate the mix design and meet specifications.  If the test section is placed within the project limits and does not duplicate the mix design and meet specifications, it shall be removed at the Contractor's expense.  Additional test sections will continue to be placed until all criteria are meet.

407-4.01  METHOD OF MEASUREMENT.  Stone Mastic Asphalt Concrete mixture will be measured by the megagram in accordance with Section 109.  The weight used shall be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 407-4.03.

Asphalt cement will be measured by the megagram based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by WAQTC TM 4.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.

The Engineer may direct at any time that tankers be weighed before and after unloading in his presence.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste, or diversion will be computed in a manner to be determined by the Engineer.  The weight of asphalt cement in waste Stone Mastic Asphalt Concrete will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Longitudinal joints will be measured by the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

407-4.02  ACCEPTANCE SAMPLING AND TESTING.  The quantity of  Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  Acceptance sampling and testing shall be performed by the Engineer.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams.  The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection.  If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,350 megagrams and 4,499 megagrams, the contract quantity will be considered one lot.  The lot will be divided into 10 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection except that retests will not be allowed.  The lot will be evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 1,350 megagrams, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances.  Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees Celsius prior to completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

Asphalt cement content will be determined from Stone Mastic Asphalt concrete mixture samples in accordance with WAQTC TM 4.  Aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.  Stone Mastic Asphalt Concrete mixture samples will be taken from behind the screed prior to compaction.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if requested.

Cut full depth core samples from the finished lift for density acceptance testing in accordance with WAQTC FOP for AASHTO T 166/T 275 within 24 hours of final rolling.  Neatly cut 150 mm minimum diameter core samples with a core drill at the randomly selected locations marked by the Engineer. Use a core extractor to prevent damage to the cores while removing. Do not cut samples from Stone Mastic Asphalt Concrete mats on bridge decks.  Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 407(5), Asphalt Price Adjustment.

Backfill all voids left by sampling with fresh Stone Mastic Asphalt Concrete mixture and compact within 24 hours of sampling.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day. The accrued amount will be subtracted under Item 407(5), Asphalt Price Adjustment.

Samples will be evaluated for acceptance in accordance with Subsection 407-4.03.

A retest of any sample outside the limits specified in Table 407-4 may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample(s) for density retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s).  The Engineer will mark the sample location for the retest.  Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s).  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

If the retest results for any sublot meets or exceeds any of the rejection limits in Table 407-4, the sublot will be removed and replaced at the Contractor’s expense.  The Engineer will determine the limits of the material represented by the sublot.

407-4.03  EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when  the contract quantity equals or exceeds 4,500 megagrams except as defined in Subsection 407-4.02.  The longitudinal joint density price adjustment will apply when Stone Mastic Asphalt Concrete quantities are equal to or greater than 1,350 megagrams.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis Method as specified in Subsection 106-1.03 to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content  is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean (x) and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lowest of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture which includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material which appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean (x) of the remaining test results:

Where:	Σ  =  summation of

x=Σxn

x  =  individual test value to xn

n  =  total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the 0.075 mm sieve.  x is rounded to the nearest hundredth for asphalt content and the 0.075 mm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

s=nΣ(x2)−(Σx)2n(n-1)

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the 0.075 mm sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the 0.075 mm sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the 0.075 mm sieve.  Use s = 0.020 for the 0.075 mm sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL).  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances  in Table 407-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG).  The LSL  for density is 92 percent of MSG and the USL is 96%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU=USL-xs

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL=x-LSLs

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit which corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit which corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

10.	Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

CPF=[f19mm(PF19mm)+f12.5mm(PF12.5mm)+.......fac(PFac)]Σf

Table 407-5 is used to determine the weight factor (f) for each sieve size and asphalt cement content.

Table 407-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL | Rejection Limits |
| --- | --- | --- | --- |
| 19.0 mm sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| 12.5 mm sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| 9.5 mm sieve | TV-4.0 | TV+4.0 | TV + 6.0 |
| 4.75 mm sieve | TV-4.0 | TV+4.0 | TV + 5.0 |
| 2.36 mm sieve | TV-4.0 | TV+4.0 | TV + 5.0 |
| 0.075 mm sieve | TV-2.0 | TV+2.0 | TV + 3.0 |
| Asphalt % | TV-0.40 | TV+0.40 | TV + 0.5 |
| Density | 92% | 96% | 91% or 98% |

Table 407-5

WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| 19.0 mm sieve | 2 |
| 12.5 mm sieve | 10 |
| 9.5 mm sieve | 10 |
| 4.75 mm sieve | 10 |
| 2.36 mm sieve | 8 |
| 0.075 mm sieve | 20 |
| Asphalt % | 40 |

407-5.01  BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-stripping additives will be subsidiary to Item 407(2), Asphalt Cement, Grade PG 58-28.

Stabilizing additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for anti-stripping additive or Asphalt price adjustment pay items.  The approved Job Mix Design will initiate Item 407(4), Anti-Stripping Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(5), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Subsection 407-4.02.  The Asphalt Price Adjustment will be algebraically added to the Contractor's payment for Stone Mastic Asphalt Concrete.  Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (Megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $46 / Megagrams

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest    value.

Longitudinal joint densities less than 91 percent of MSG as defined in Subsection 407-3.14 will be measured in accordance with Subsection 407-4.01 and assessed a price adjustment of $1.50 per meter.  The accrued amount will be subtracted under Item 407(5), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with subsection 407-3.15 will be calculated and applied.  The adjustment will be applied under Item 407(4) Asphalt Price Adjustment.  Calculate the smoothness price adjustment as follows;

The maximum percent incentive (M) offered for this project is 2.5

SPA% = 3.33  – (0.0266) x PrI

SPA% = Smoothness Price Adjustment Percentage

PrI = measured pavement smoothness (mm/km)

Smoothness Price Adjustment ($) = SPA% x PAB x quantity  									100

PAB = Price Adjustment Base defined above.

quantity = final pay quantity for Item 407(1)

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 407(1) Stone Mastic Asphalt Concrete | Megagram |
| 407(2) Asphalt Cement, Grade PG 58-28 | Megagram |
| 407(4) Asphalt Price Adjustment | Contingent Sum |

This page intentionally left blank.

SECTION 501

STRUCTURAL CONCRETE

# Special Provisions

501-1.01 DESCRIPTION. Add the following:  This work also consists of constructing a “Tombstone” Artillery Gunmount as shown in the Plans.

501-3.01 PROPORTIONING.  Under 1.  Determining Proportions and Batch Weights., delete the first sentence and substitute the following: Submit a mix design developed in accordance with ACI 211 and ACI 301, Section 4 to the Engineer for approval.

(07/06/99)R37M98

501-3.07  PLACING CONCRETE.  Add the following numbered item:

16.  Drill and Bond Reinforcing Steel.   When new concrete is shown on the Plans to be joined to hardened concrete by means of reinforcing steel bonded into holes drilled in the hardened concrete, the holes shall be drilled by methods that will not shatter or damage the concrete adjacent to the holes.  Holes in which longitudinal or transverse reinforcement is encountered during drilling before the specified depth is attained shall be rejected.  A new hole, which does not strike reinforcement, shall be drilled adjacent to the rejected hole to the depth shown on the Plans.  All rejected holes will be filled with epoxy grout.

The bonding agent shall be an epoxy cartridge system consisting of (1) a bonding material that is a two-component epoxy contained in a cartridge having two separate chambers and (2) an applicator that is a special dispensing gun having a replaceable static mixing nozzle.  The epoxy cartridge system used shall be appropriate for the service temperature and ambient concrete temperature at the time of installation.

All epoxy cartridge systems shall be subject to the approval of the Engineer.  Epoxy cartridge systems shall meet the requirements of the “Acceptance Criteria for Adhesive Anchors in Concrete and Masonry Elements,” AC58, dated January 1, 1998, by the ICBO Evaluation Service, Inc.  The suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic qualification of these acceptance criteria shall be met.  Approval of epoxy cartridge systems shall be contingent upon the Contractor submitting to the Engineer one sample of each type of epoxy cartridge system, manufacturer's installation instructions, and certified results of tests, either by a private testing laboratory or the manufacturer, indicating compliance with the above requirements.  Epoxy cartridge systems previously tested and approved by the Engineer need not be re-tested.

The following products have been found to substantially meet these requirements and are conditionally approved for use on this project.

| # Manufacturer | # Model of Conditionally Acceptable Epoxy Cartridge | # Manufacturer’s Phone Number |
| --- | --- | --- |
| ##### Simson Strong-Tie | SET Models SET22 and SET56(Model # designates volume of cartridge in fluid ounces) | 1-510-460-9912 1-630-543-2797 |
| Covert Operations | CIA Gel 7000 | 1-800-827-7229 |
| Adhesives Technology (Div. of US Anchor Corp.) | Anchor-it HS-200 | 1-800-262-4748 |
| ITW Ramset/Redhead | Epcon Ceramic 6 | 1-800-368-9724 |
| Hilti | HSE 2421 | 1-907-344-8351 |

The above conditionally approved products shall not be used when:

- Temperature of concrete will exceed 110 degrees F.

- There is a likelihood of fire.

- The concrete temperature at time of installation is below 40 degrees F.

Each epoxy cartridge shall be clearly and permanently marked with the manufacturer's name, model number of epoxy cartridge system, manufacturing date, and lot number.  Each carton of epoxy cartridges shall contain the manufacturer's recommended installation procedures, minimum cure time, and such warning or precautions concerning the contents as may be required by State or Federal Laws and Regulations.

Each shipment of the epoxy cartridge system, regardless of which epoxy product is furnished, shall be accompanied by a Certificate of Compliance as provided in Section 106-1.05, "Certification of Compliance," of the Standard Specifications.  The certificate shall state that the material complies in all respects to the specifications and data submitted in obtaining acceptance.

The diameters and depths of the drilled holes shall be as recommended by the manufacturer.  The drilled holes shall be clean and dry at the time of placing the bonding material and the reinforcing steel.

After bonding, reinforcing steel shall be supported as necessary to prevent movement during curing and shall remain undisturbed until the epoxy has cured the minimum time specified by the manufacturer.  Reinforcing steel that is improperly bonded, as determined by the Engineer, will be rejected.  New holes shall be drilled, and new reinforcing steel placed and securely bonded to the concrete at the Contractor's expense.

501-4.01 METHOD OF MEASUREMENT. Add the following: The “Tombstone” Artillery Gunmount will not be measured.

501-5.01 BASIS OF PAYMENT. Add the following:  Payment for the concrete required to construct the “Tombstone” Artillery Gunmount will be paid for under Item 501(1).  The schedule 40 steel pipe and all labor required to construct the gunmount as shown in the Plans is subsidiary to Item 501(1) and no separate payment shall be made.

THIS PAGE INTENTIONALLY LEFT BLANK

SECTION 504

STEEL STRUCTURES

## Special Provisions

504-1.01 DESCRIPTION.  Add the following to the first paragraph:  This work includes furnishing, fabricating and installing metal deck drains as shown in the Plans.

504-3.02 ERECTION.  Add the following item:

10.	Installatioin of Deck Drains.  Install the deck drains as shown on the Plans.  Provide holes in the concrete deck and metal deck forms as needed to accommodate the deck drains as shown on the Plans.  Do not damage surrounding concrete when coring, cutting, or drilling hole in deck.

Fill void between deck drain and concrete deck with grout.

504-4.01 METHOD OF MEASUREMENT.

Under Item 2, “Kilogram,” change lettered sub-item designations “4, d, and e” to “d, e, and f” respectively.

(03/31/00)R253M98

SECTION 507

BRIDGE RAILING

# Special Provisions

    - MATERIALS.  Add the following to 3. Concrete Railing:

Grout, 					Subsection 701-2.03.

Drill and Bond Reinforcing Steel,		Subsection 501-3.07, Item 16.

507-4.01 METHOD OF MEASUREMENT.  Add the following items:

4.	Drilling holes in deck and bonding reinforcing steel in accordance with Section 501 and as shown in the Plans.

5.	Drilling holes through the deck and metal deck forms to accommodate anchor bolts as indicated on the Plans.

6.	Roughening the surface under the cast-in-place concrete curb as indicated on the Plans.

7.	Grout under the base plate and between metal deck form and anchor plate.

8.	All other materials, equipment, and labor required to install the Steel Bridge Railing and Pedestrian Railing as shown in the Plans.

Add the following Section:

SECTION 514

ROCKFALL MITIGATION SYSTEMS

514-1.01  DESCRIPTION.  This work consists of constructing and removing temporary and permanent catchment barriers, fences, draped mesh and the installation or use of other mitigation methods as shown in the Plans and specifications or as directed by the Engineer to prevent rockfall from reaching the roadway or other specified areas.

514-4.01 METHOD OF MEASUREMENT.  Items 514(1), (2), and (3) will be measured by the square meter.

514-5.01 BASIS OF PAYMENT.  Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 514(1) Rockfall Mitigation – Rock Fences or Barriers | Square Meter |
| 514(2) Rockfall Mitigation – Wire Mesh | Square Meter |
| 514(3) Rockfall Mitigation – Cable Mesh | Square Meter |

SECTION 603

CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS. Add the following: Culvert marker posts shall meet the requirements of subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm. (05/31/96)R42M

Standard Modifications

In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.

603-3.03 JOINING PIPE.

2. Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.” (02/08/01)M95

#### Special Provisions

603-3.06 CULVERT MARKER POSTS. Add the following Subsection: Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.  (5/31/96)R42M

SECTION 606

GUARDRAIL

#### Special Provisions

606-1.01 DESCRIPTION.  Add the following:  This work also consists of installing Rub Rail.

606-2.01 MATERIALS.  Add the following:

Rub Rail.

1.  Treated Wood				Subsection 650-2.07

2.  Fasteners					Subsection 650-2.08

Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 129 cm2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit the specifications to the Engineer for approval prior to ordering the markers. (05/29/02)R45aM98

Standard Modifications

606-3.01  GENERAL.  Add  the following:   Treat field cuts to timber posts and blocks according to AWPA standard M 4. (10/19/98)M 67

Special Provisions

Replace the second sentence of the first paragraph with the following: Conform with these Specifications and the Standard Drawings with the following exception.  Modify Standard drawing G-20 to only allow an offset of 300 mm (1 foot) for the ET-2000.  (03/22/02)R266M98

606-3.02  POSTS.  Delete the second paragraph and substitute the following:  Use wood posts subject to the following:

Standard Modifications

606-3.05 TERMINAL SECTIONS.  Delete the fourth paragraph (flexible markers) in its entirety and substitute the following:  Attach flexible markers, in a vertical position, to the last post of each guardrail terminal using two pipe bracket holders spaced 300 mm apart. Attach to wooden guardrail posts with wood screws and to steel guardrail posts with hex bolts. (03/14/00) M 88

# Special Provisions

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 15 meters of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed. (05/29/02)R45aM98

606-3.07 REMOVAL AND DISPOSAL OF GUARDRAIL. Delete the last sentence and substitute the following: Notify the Engineer, five (5) days prior to removing guard rail for disposal.  At that time, the Engineer will physically identify portions of guardrail to be salvaged.  All guardrail and associated hardware so designated will be delivered to the Department of Transportation Maintenance Yard located in Girdwood.  All remaining items removed become the property of the Contractor. (09/08/00)R259M98

606-3.09 FLEXIBLE MARKERS. Add the following Subsection: For each rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.10 LENGTH OF NEED VERIFICATION. Add the following Subsection: After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The staked location of the guardrail will be approved by the Engineer prior to installation. The Engineer may determine that additional guardrail is necessary, and comply without delay. (05/29/02)R45aM98

Standard Modifications

606-4.01 METHOD OF MEASUREMENT. Delete the second to the last paragraph and substitute the following:

Guardrail/Bridge Rail Connection. Per each, installed in place. Each connection includes all brackets, beam sections, transition pieces, and all posts and associated hardware required to connect the guardrail section to a bridge rail according to the Plans and the Special Provisions.

(10/19/98)M 66

Special Provisions

Add the following:  Rub Rail will not be measured for payment.

606-5.01 BASIS OF PAYMENT.  Add the following:  All work and materials associated with the installation of Rub Rail are subsidiary to Item 606(1), W-Beam Guardrail and no separate payment shall be made.

SECTION 608

SIDEWALKS

### Special Provisions

608-1.01 description. Add the following: This work also consists of constructing asphalt pathway(s) in conformance with the Plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

###### Asphalt Cement, PG52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.					4450

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

- Add the following subitems:

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with subsection 608-3.02 Asphalt Sidewalks. (2/1/00)R47M98

Standard Modifications

608-4.01 METHOD OF MEASUREMENT.  In both the first and second paragraphs, after “finished surface” insert “, including ramps”. (6/25/99)M74

#### Special Provisions

Add the following:  Asphalt Pathway. By the megagram of asphalt concrete in accordance with Section 109, Measurement and Payment. Asphalt cement will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to Item 608(7), Asphalt Pathway.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively. (2/1/00)R47M98

- Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 608(7) Asphalt Pathway | Megagram |

Delete this Section in its entirety and substitute the following:

SECTION 611

RIPRAP

Special Provisions

611-1.01 DESCRIPTION. This work shall consist of furnishing and placing a protective covering of stone as shown on the Plans.

611-2.01 MATERIALS. Delete the requirements for Class II and add the following: Stone for this work shall meet the requirements of one of the following categories:

A.	Stone from the Bird Creek Cut:

1.	General: Stone shall be hard, angular and durable. Rounded or weathered stones will not be allowed. Stones shall not be elongated or tabular. The longest dimension shall not be greater than three times the least dimension.

2.	Size and Gradation: Prior to placing any stone, develop and maintain a process for sorting stones using a Grizzly or approved equal. This process is subject to approval of the Engineer. Stone shall meet the size and gradation criteria outlined in Table 611-1. Use a stone count method.  Upon approval of the process, riprap produced will be accepted at the stockpile as meeting gradation requirements.

Changes in the size or shape of rock being produced, either before or after processing, ***Deleted*** may require changes to the blasting or sorting process. Changes in the sorting process will be subject to gradation testing prior to the resumption of production. Testing shall be conducted by the Contractor. Results of the testing shall be provided to the Engineer for approval.

3.	Stone Quality: With the exception of gradation conformance testing, stone from within the project limits shall not be subject to the requirements of Section 611-3.01.

Quantity of stone recovered from this source is dependent upon blasting and sorting methods employed. Some or all of the rock in this source may require processing to secure planned quantities of Riprap.

B.	Stone from an Alternate Source: The Contractor may choose to import the stone from an alternate source outside the project limits. The stone shall meet the General, Size and Gradation criteria described for stone produced within project limits and outlined in Table 611-1. In addition, stone from alternate sources shall be subject to all testing and quality compliance standards outlined in Section 611-3.01.

#### Table 611-1

#### STONE CLASSIFICATION

| Designation | Stone Weight | Percent Passing ***Deleted*** | Approximate Stone Dimension * |
| --- | --- | --- | --- |
| R750 | 1250 kg 750 kg 250 kg | 100 0-50 0 | 0.90 m 0.76 m 0.52 m |
| Class II | 250 kg 100 kg 12 kg | 100 0-50 0 | 0.52 m 0.39 m. 0.19 m |

* Note: The dimensions correspond to the size measured by sieve, grizzly, or visual inspection for stone with 2.65 specific gravity.

611-3.01 TESTING AND QUALITY COMPLIANCE.

A.	General: Acceptability of stone quality will be determined by visual inspection and/or laboratory tests, as determined by the Engineer. The tests are listed in Table 611-2. The Engineer may, at any time during performance of the contract, reject materials at the source or job site which do not meet the specified requirements. Materials delivered to the project site and rejected shall be removed from the site unless otherwise directed by the Engineer.

B.	Source Testing: The Contractor shall be responsible for testing necessary to ensure the quality and quantity of proposed stone source(s) prior to proposing them to the Engineer. After identifying the source(s), a 180 to 230 kilogram representative sample shall be selected by the Engineer for quality testing. All tests must be performed by a certified laboratory approved by the Department. If, in the opinion of the Engineer, those tests are representative of the source and show the materials will satisfactorily fulfill the quality requirements, the source may be accepted without further testing. However, if directed by the Engineer, deliver the rock samples to the State of Alaska, Central Region Materials Laboratory, 5750 East Tudor Road, Anchorage, Alaska. The Department will perform the quality tests specified by the Engineer.

Sources whose samples do not meet the specified quality requirements will be rejected for use on this project. Approval of a stone source shall not be construed as approval of all stones from that source. The State reserves the right to reject certain localized areas, strata, or channels within the approved source, when in the opinion of the Engineer, the stone is highly vesicular, fissured, badly weathered, or otherwise unsatisfactory, despite test results.

Table 611-2

QUALITY TEST REQUIREMENTS

| Property | Test Procedure | Limits |
| --- | --- | --- |
| Specific Gravity (SSD) | AASHTO T 85 | Min. 2.65 |
| Soundness (Sodium Sulfate) | AASHTO T 104 | Max. Loss 5% after 5 cycles |
| Abrasive (LA) (Qualitative Test) | AASHTO T 96 | Max. Loss 10% after 200 revs. and 50% after 1000 revs. |
| Degradation | ATM T-13 | Min. 40 |
| Absorption | WAQTC FOP for AASHTO T 85 | Max 2% |
| Solubility & Durability (Ethylene-Glycol) | COE CRD-C-148 | Max. Loss 2% after 15 days |

C.	Acceptance Testing: Only after source testing and approval for use on this project, may stone production begin. Stone material produced for this project shall be visually inspected and tested for quality, weight, gradation, and shape to ensure compliance with the specifications.

Materials that do not meet the specified requirements shall be placed in a separate area of the quarry in a manner to ensure there is no mixing with acceptable materials. Production tests shall be performed at uniform intervals throughout the project at a rate to ensure the minimum number of tests are performed.

The Engineer or his designated representative shall reserve the right to stop production and conduct further testing should the nature of the stone change to such a degree that, in the sole opinion of the Engineer, the quality of the stone becomes questionable. Three consecutive tests failing to pass the specified quality requirements shall be justification for rejecting the source.

Table 611-3 shows the acceptance tests and testing frequency for this project.

Table 611-3

ACCEPTANCE TESTING

| Stone | Type of Test | Minimum Size of Sample | Minimum No. of Tests* |
| --- | --- | --- | --- |
| R750 | Quality | 180 kilograms | 1 @ Start Up 1 @ 50% completion |
| R750 Class II | Gradation Conformance | 3.5 to 5.5 Mg | Each 45,000 Mg |

* Tests which do not pass are not counted toward the number of tests required. Testing shall be increased as necessary to maintain quality control during production. Retesting, as required due to failed tests, shall be at the Contractor's expense.

611-4.01 CONSTRUCTION REQUIREMENTS.

A.	General: Slopes shall be dressed to provide a smooth surface as detailed on the typical drawing prior to the placement of any stone for Riprap. All stone riprap material shall be placed uniformly within the slope lines and grade shown on the drawings or as directed by these specifications.

Prior to placement, establish clear and understandable construction control for riprap placement. The minimum control shall delineate the elevation limits of the different size stones.

Unless otherwise authorized, the riprap protection shall be placed in conjunction with the construction or dressing of the embankment. Any delay in placing the riprap may lead to further slope dressing.

The stones shall be mechanically placed so as to secure a stone mass of the thickness, height, and length shown on the Plans, or as staked. Placing of riprap protection by any method that results in segregation of the different layers will not be permitted.

Final shaping of the slope shall be performed as the stones are placed. A tolerance of plus or minus 300 mm from the slope lines and grades shown on the drawings, measured perpendicular to the theoretical surface, will be permitted. The extreme limits of tolerances shall not be continuous over an area greater than 110 square meters of slope surface in any given area.

Provide a level compact area of sufficient size to dump and sort typical loads of riprap at approved location(s). He shall dump loads specified in this area and assist the Engineer as needed to sort and measure the stones in the load for the purpose of determining if the riprap is within specifications. Mechanical equipment as needed to assist in this sorting shall be provided by the Contractor at no additional cost to the State.

611-5.01 METHOD OF MEASUREMENT. The quantity of riprap to be paid for shall be the number of megagram completed and accepted in place.

Changes to the mechanical sorting process instigated by the Engineer shall be subsidiary to pay items 611(2) and 611(2A).

The delivery of rock samples to the Central Region Materials Laboratory shall be subsidiary to pay items 611(2) and 611(2A).

611-6.01 BASIS OF PAYMENT. The accepted quantity of each type of stone will be paid for at the contract unit price per unit of measurement shown in the bid schedule, complete in place, as shown.

Excavation and backfill required for this work are subsidiary to Items 611(2) and 611(2A).

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 611(2) Riprap, Class II | Megagram |
| 611(2A) Riprap, R750 | Megagram |

SECTION 615

STANDARD SIGNS

#### Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Girdwood.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

As-built the locations of existing railroad signs prior to construction activities disrupt them.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign. (05/16/01)R50M98

# SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

Revegetation of the railroad armor rock on the outside (Lt.) embankment is not necessary.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total = 49.0 kg |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright)  is commercially unavailable.  If this substitution is made, apply at the  same application rate.

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(03/05/02)R52M98

SECTION 620

TOPSOIL

Special Provisions

620-2.01 MATERIALS. Delete this subsection in its entirety and substitute the following: Topsoil shall conform to the requirements of Section 726. Class of topsoil shall be as shown on the Plans.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(09/11/96)R53

SECTION 621

PLANTING TREES AND SHRUBS

#### Special Provisions

621-1.01 DESCRIPTION.  Add the following: Plantings will be staked by the Engineer.  This work shall also include furnishing and installing wood chip mulch as detailed on the Plans.

621-2.01 PLAN STOCK. Add the following after the last paragraph: Plan height will be measured for the top of the root ball.  Caliper will be measured in accordance with ANSI Z60.1-1990.

TABLE 621-1

PLANT STOCK SPECIFICATIONS

| Tree Species | Root Condition | Size | Comments |
| --- | --- | --- | --- |
| White Spruce (Picea Glauca) | Ball & Burlap | 1m-1.2m High | Field Collected or Field Grown |

| Shrub Species | Root Condition | Size | Comments |
| --- | --- | --- | --- |
| Prickly Rose (Rosa Acicularis) | Container | 0.3m-5.4m High | Field Collected or Field Grown |

Field collected plants are local plants harvested in Alaska.  Field grown plants are plants field grown in Alaska nurseries. Nursery grown plants are plants grown in any nursery.

621-2.01 FERTILIZER. Add the following: Fertilize all trees and shrubs with slow release tablet or stake form fertilizers.  Place tablet form fertilizer (20-10-5) near the root zone at the time of planting in accordance with manufacturer’s recommendations.  Place stake form fertilizer (8-16-16) evenly around plant drip line in accordance with manufacturer’s recommendations.

621-2.05 BACKFILL MIX.  Add the following: Prepare mix for planting by mixing in water retention additive at manufacturer’s recommended application rate.

621-2.08 WOOD CHIP MULCH. Wood chip mulch shall consist of spruce, Douglas fir, pine, or hemlock wood or bark and shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.  Approximately 95 percent of the chips by volume shall be 6 mm to 38 mm in length.

621-3.03 PLANTING. Replace item 1. Plant Season with the following:

1.		Plant Season.

a.	Locally Grown: Plant between June 1 and September 15.

Replace paragraph b.,c., and d. under item 2. Excavation with the following:

b.	Planting pits for trees and shrubs shall be as shown on the Plans.

Delete the second, third, and forth sentences of paragraph 3b.

Add the following to item 5. Placing Plants:

d.	Trees and shrubs shall be planted as shown on the Plans.

Replace item 8. Staking and Guying, with the following:

8.		Staking and Guying.  As shown on the Plans.

621-3.04 PERIOD OF ESTABLISHMENT. Replace the last sentence with the following: The Period of Establishment for trees and shrubs shall extend to August 1st of the next growing season following planting.

Add the following: Trees and shrubs shall receive a reapplication of fertilizer of the same chemical proportions as the initial application in accordance with the manufacturer’s instructions.  The reapplication shall be performed between June 1 and August 1 of the growing season following planting.

621-4.01 METHOD OF MEASUREMENT. Replace with the following; The quantity to be paid for shall be the actual number of trees and shrubs furnished, planted and maintained in accordance with the Plans and specifications, and as accepted by the Engineer.

Wood chip mulch will not be measured for payment.

Furnishing and installing wood chip mulch, topsoil backfill, tree wrap, staking and guying will not be paid for separately, but will be subsidiary to Items 621(1) Trees, and 621(2) Shrubs.

621-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 621(1A) Tree, White Spruce | Each |
| 621(2J) Shrub, Prickly Rose | Each |

SECTION 623

#### BLOCK SODDING

Special Provisions

623-1.01 DESCRIPTION. Delete this Subsection in its entirety and substitute the following:  This wetland restoration work consists of two separate items: 1) retrieving, transporting and  installing  living Vegetated Mats which will be produced by the Alaska Department of Natural Resources Plant Materials Center in Palmer, and 2) extract, move, and install Wetland Sod Blocks in the areas designated on the Plans or as directed by the Engineer.  The purpose of this work is to expedite the revegetation of restored wetland areas as required under Special Condition # 8 of the Corps of Engineers Permit 2-980650.

623-1.01 MATERIALS. Delete this Subsection in its entirety and substitute the following:

1. Vegetated Mats.  	Vegetated Mats will be provided by the Plant Materials Center (PMC) in Palmer for installation in Wetland Restoration Area A.

###### a.   	Transportation and Storage: Coordinate the pick up the Vegetated Mats with Nancy Moore, PMC, at (907) 746-7241.  The Vegetated Mats shall be transported from the PMC, in a truck large enough to accommodate the entire 0.9 m X 3 m Mats whole. Insure that the Mats are protected during transport and that they do not dry out.  If the material must be stored on site prior to installation, the storage area shall be shaded and Mats kept moist throughout the root zone.  Installation shall occur within 48 hours of transport from PMC.

2. Wetland Sod Blocks. 	Wetland Sod Blocks shall be harvested from Wetland Restoration Area B, as specified on the Plans. Sod Blocks shall be cut to measure approximately 1.5 m by 1.5 m. Sod Blocks shall be 0.4 meter thick. Sod Blocks shall be removed only from areas approved by the Engineer in and adjacent to Wetland Restoration Area B. Use approved mechanized methods to obtain and place Wetland Sod Blocks.

623-3.01 CONSTRUCTION REQUIREMENTS. Delete this Subsection in its entirety and substitute the following:

Plant Season:  Both the Vegetated Mats and Wetland Sod Blocks shall be planted between May 15 and August 1, 2003.

1.  	Vegetated Mats.

###### a.	Layout. 	Stake all areas to be planted with Vegetated Mats as shown on the Plans prior to installation.  Notify the Engineer of the delineated areas 3 working days prior to installation, and installation shall commence only after approval by the Engineer.

###### b.	Installation.

###### i.	Commencement of work assumes that the Contractor accepts the conditions of the cut and fill grades, of areas in question.  Any discrepancies in work shall be brought to the attention of the Engineer, in written format, immediately.

ii.	Before installing the Vegetated Mats, the Contractor must insure that the embankment is moist. Vegetated Mats shall be placed in position insuring complete contact of root mass to the soil surface. Tamp into place. Staple or stake mats into place as shown on the Plans.

iii.	Water Vegetated Mats  within one hour of placing. Continue to                                                   keep Mats moist until final acceptance of the project.

2.	Wetland Sod Blocks.

###### a.	Removal of Wetland Sod Blocks.

###### The sod blocks shall be harvested from the existing vegetation in and adjacent to Restoration Area B.  Sod Block removal sites shall be approved by the Engineer prior to harvest.  Blocks shall be cut prior to removal from growing site.  The sod blocks shall be stockpiled in a single layer and in the upright position.  Contractor shall remove and transport sod blocks in a manner that allows continued access to the remaining sod blocks and maintains the areas to remain undisturbed without damage.

###### b.	Placement of Wetland Sod Blocks.

###### Final grading of the receiving site shall be completed and approved by the Engineer.   No removal and transport of sod blocks is permitted prior to preparation of the receiving site.  The Wetland Sod Blocks shall be placed within 24 hours of their removal.

###### The Wetland Sod Blocks shall be placed in the upright position in the locations shown on the Plans.

3.	Fertilization.

Apply a slow-release granular fertilizer, 8-32-16, at an application rate of                                           20 grams per square meter between May 1 and June 1 of the growing season following installation.

Add the following Subsection:

623-3.02 MAINTENANCE.  The maintenance period extends from the time of planting to August 1 of the next growing season.  Contractor shall water, repair damaged areas, and replace dead vegetation in the Wetland Sod Blocks as necessary and directed by the Engineer during the maintenance period.

623-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following:

Measurement of Pay Items 623(1) and 623(2) shall be by the square meter installed, per Subsection 109-1.02.  Watering shall be subsidiary to these pay items.

623-5.01 BASIS OF PAYMENT.  Add the following:  All equipment and materials, watering, stapling, fertilizing and labor associated with the work described in this section shall be subsidiary to Pay Items 623(1-2).

Partial payments of up to 80% of full amount may be authorized for installation of Vegetated Mats, Pay Item 623(1) at the time of acceptance.  The balance will be paid with one final payment at the completion of the maintenance period, if at that time 70% of plant materials, by area, are living.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 623(1) Vegetated Mats, Installed | Square Meter |
| 623(2) Wetland Sod Block, Installed | Square Meter |

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.(05/09/02)R58M98

Payment will be made under:

| ## Pay Item | Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modifications

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT. Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Item 641(1) will not be measured for payment.

Item 641(2) will be measured as specified in the Contract or Directive authorizing the work.

Add the following:  Items 641(5) and 641(6) will be measured by the meter installed and accepted by the Engineer.

641-5.01 BASIS OF PAYMENT.

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule. (08/15/01)M78

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |
| 641(5) Silt Fence | #### Meter |
| 641(6) Straw Bale | #### Meter |

#### SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION.  Add the following:  This work also consists of installing “railroad curve tabs”.  The Railroad Curve Tabs shall conform to the Alaska Railroad Standard Drawing “Curve Tab”.

642-3.01 GENERAL.  Add the following:  Supply, stamp and place railroad curve tabs at the TS, SC,CS, and ST points for each curve located within the project limits.

Delete the seventh paragraph.

Delete item number 10 after the heading “Perform the following:” and substitute the following:

- Stake the pathway centerline and mark the cut or fill to finish grade prior to construction.  The Engineer shall be given 10 days to review and realign the pathway if necessary.

- All other surveying and staking necessary to complete the project.

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work.  (03/31/00)R252M98

642-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 642(17), Supply and Set Railroad Curve Tab.  No measurement of quantities will be made.

642-5.01 BASIS OF PAYMENT.  Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 642(17) Supply and Set Railroad Curve Tab | Lump Sum |

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following:  The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (01/29/02)R222M98

Add the following: Your traffic control plan shall also indicate the method of safely stopping and routing the traveling public through the project during periods of possible avalanche danger.

## 643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. (9/29/00)M 91

## Special Provisions

Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

(01/29/02)R222M98

## Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (9/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (01/29/02)R222M98

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES. Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: At the end of each continuous work shift remove all obstructions greater than 100 mm above the nominal foreslope grading.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

# ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and add the following:   The Contractor will be allowed to maintain Seward Highway traffic on the designated detour route show in the Plans from station 44+760 to station 45+675.  The surface of the detour route may initially be gravel; however, the detour route must be paved full width (11 meters) and striped within seven consecutive days of opening the route to traffic.

***Deleted***

Unless otherwise determined by the Engineer and on an approved Traffic Control Plan, do not restrict traffic during the times listed below.

Holidays:

- If a holiday falls on Sunday, Monday or Tuesday, the following stipulations apply from 1200 Hours on the Friday before the holiday to 0300 hours on the day after the holiday.

- If a holiday falls on Wednesday, the following stipulations apply from 1500 Hours on the Tuesday before the holiday to 0300 hours on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the following stipulations apply from 1500 hours on the day before the holiday to 0300 hours on the Monday after the holiday.

May 15 to September 4:

1.	0600 hours to 2000 hours Monday through Thursday.

2.	0600 hours Friday through 2200 hours Sunday.

September 5  to May 14 :***Deleted***

1.	0600 hours to 0800 hours Monday through Friday.

2.	1600 hours to 1800 hours Monday through Friday.

You will be permitted one 30 minute closure per day for blasting Monday through Friday, with no closures allowed during the listed restriction periods.

Clear the queue of traffic if any of the following conditions exist:

- 20 minute accumulated delay

- 80 vehicles stopped in the traffic queue

- 1 kilometer of traffic stopped

Obtain the local school bus schedule and coordinate your efforts to ensure that school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (01/29/02)R222M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions.

644-2.01 FIELD OFFICE. Delete this subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

(9/28/00)R63M98

Standard Modifications

644-4.01 BASIS OF PAYMENT.  In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Special Provisions

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory. (9/28/00)R63M98

Add the following Section:

SECTION 645

TRAINING PROGRAM

#### Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs. (10/29/91)S 16

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 3 Trainees/Apprentices | Labor Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this Subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

##### Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

All equipment shall be fully operated, which shall be understood to include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all subsidiary items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 48 kW Minimum will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all subsidiary costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation. (11/12/98)R15M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 48 kW Minimum | ##### Contingent Sum |

- Add the following Section:

SECTION 650

PARK FACILITIES

650-1.01 DESCRIPTION.  This work shall consist of furnishing, constructing and placing park facilities in conformance with the Plans and Special Provisions.

650-1.02 APPLICABLE ACCESSIBILITY STANDARD.  Americans with Disabilities Act (ADA) Accessibility Guidelines for Buildings and Facilities.

650-1.03 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

MATERIALS

650-2.01 GENERAL.  All materials shall be new and conform to the details shown on the Plans or as specified.

650-2.02	 BACKFILL.  Selected Material, Type A conforming to Subsection 703-2.07.

650-2.03 CONCRETE.  Type “W” and Type “A” Concrete conforming to Section 501.

650-2.04 STRUCTURAL STEEL.  Structural steel shall conform to the requirements of ASTM Specification A 36 (Standard Specification for Carbon Structural Steel).

650-2.05 GALVANIZING.  Conform to AASHTO M 111/ASTM A 123 (Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products), or AASHTO M 232/ASTM A 153 (Standard Specification for Zinc Coating[Hot-Dip] on Iron and Steel Hardware).

650-2.06 WOOD.  Conform to Section 713.  Wood species shall be Douglas Fir, Western Hemlock or Hem-fir unless otherwise specified.

1.	Dimensional.  Dimensional lumber and timbers are shown on the Plans in nominal dimensions, i.e.; 50 mm x 100 mm (2”x4”), indicating surfaced four sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Use classification for structural joists and planks shall be No. 2 Grade or Better.  Manufacturing classification shall be Dressed (Surfaced) Lumber.  Size classification shall be Nominal Size Designations of Boards, Dimension, and Timbers.

2.	Rough Cut.  Unless otherwise indicated, rough cut lumber and timbers are shown on the Plans in actual dimensions, i.e.; 50 mm x 100 mm (2"x4"), indicating rough cut material. Use classification shall be Structural Lumber, No. 2 Grade or Better. Manufacturing classification shall be Rough Lumber.  Size classification shall be Rough Dry Sizes.

650-2.07 TREATED WOOD.  Wood shall conform to Subsection 650-2.06.  Treatment shall be as follows:

1.	Above Ground Applications.  Pressure treat lumber and timber with water borne salts preservative Chromated Copper Arsenate Type C (CCA-C) to a minimum retention of 6.4 kilograms per cubic meter (0.40 pounds per cubic foot) or to refusal. Treated materials shall be pigmented uniformly brown in color by treater and nonincised.  This type of treated wood is commonly used for residential decks for above ground applications.  Incising may be used on 100 mm (4x) and thicker material to obtain minimum retention.

2.	Ground Contact Applications.  Pressure treat lumber and timber with water borne salts preservative to  Chromated Copper Arsenate Type C (CCA-C) to a minimum retention of 9.6 kilograms per cubic meter (0.60 pounds per cubic foot).  Exposed treated materials shall be pigmented uniformly brown in color by treater.

650-2.08 FASTENERS.  Commercial quality and type of nails and screws as required to securely hold all members in place in accordance with National Design Specifications.  Nails shall be hot dipped galvanized.  All other fasteners shall be corrosion resistant.  Fasteners in pressure treated wood shall be hot dipped galvanized.  Nails and wood screws below grade in pressure treated wood shall be stainless steel.

650-2.09 STANDARD PARK PADLOCK.  Master Lock No. 1 with 8 mm (5/16”) shackle diameter, 24 mm (15/16”) vertical clearance, 19 mm (3/4”) horizontal clearance, 44 mm (1 ¾”) case width, and keyed alike to a key number provided by the Engineer specific to the Park area.  Provide two keys with each padlock.

650-2.10 PAINT.  Unless otherwise specified, use the following paint types and colors, or approved equals:

1.	Solid Oil Stain.  Exterior oil/alkyd flat finish stain, color “Russet”. DF7XX as manufactured by Fuller O’Brien / Devoe Products.  Russet as manufactured by Pittsburgh Paint Company, Behr Plus 10 Solid Stain #354 Russet, or Olympic Russet as manufactured by PPG Architectural Finishes, Inc.  Submit color samples of proposed substitutions for approval.

2.	Semi-Transparent Oil Stain.  Exterior alkyd based stain, color to match solid oil stain “Russet”.  Stains for pressure treated wood shall be recommended by manufacturer for use on pressure treated wood.

3.	Clear Oil Stain.  Non-pigmented penetrating exterior alkyd base stain formulated for water repellency.

4.	Metal Primer Paint.  As recommended by enamel paint manufacturer.

5.	Enamel Paint.  Exterior alkyd base gloss enamel.  Color to match solid oil stain color.

6.	Concrete Sealer.  Clear acrylic copolymer conforming to AASHTO M148/ASTM C 309 (Standard Specification for Liquid Membrane-Forming Compounds for Curing Concrete, for Type 1 Compounds).

7.	Above Ground Wood Preservative.  Brown preservative with active ingredient of minimum 9.08 percent copper naphthenate (equivalent to minimum 1 percent metallic copper).  Color to be approved by Engineer.

8.	Below Ground Wood Preservative. Preservative with active ingredient of minimum 16 percent copper naphthenate (equivalent to minimum 2 percent metallic copper).

9.	End Cut Preservative for Treated Wood.  Brown preservative with active ingredient of minimum 16 percent copper naphthenate (equivalent to minimum 2 percent metallic copper).  Color to match preservative pressure treatment color.

- Paint that has been frozen or is out of date shall be replaced at no additional cost to the Department.

650-2.11 SIGNS.  Fabricate sign panels to the dimensions shown on Plans.  Metal sign panels shall be 0.080” thick alloy 6061-T6 aluminum.  Wood sign panels shall be medium density overlay plywood.  Signs shall have Type II (medium intensity) reflective sheeting background with color as specified.  White high intensity sheeting for symbols, letters, and borders shall match 3M Scotchlite Reflective Sheeting #2290.  Brown medium intensity sheeting for background shall match 3M Scotchlite Reflective Sheeting #2279.

650-2.12 SINGLE ENTRANCE GATE.  Conform to Standard Drawing G-1, Single Entrance Gate.  High intensity reflective sheeting for gates shall match 3M Scotchlite Reflective Sheeting #3820 and have alternating red and white 4” wide stripes sloping downward at an angle of 45 degrees.  Provide one standard Park padlock for each gate.

650-2.13 DOUBLE ENTRANCE GATE.  Conform to Standard Drawing G-2, Double Entrance Gate.  High intensity reflective sheeting for gates shall match 3M Scotchlite Reflective Sheeting #3820 and have alternating red and white 4” wide stripes sloping downward at an angle of 45 degrees.  Provide two standard Park padlock for each gate.

650-2.14 CONCRETE PARKING BUMPER.  Conform to Standard Drawing P-6, Parking Bumper.

650-2.15 PARKING BUMPER.  Conform to Standard Drawing P-6, Parking Bumper.  Wood members shall be treated wood surfaced four sides.

650-2.16 BARRIER ROCK.  Barrier rocks shall be a minimum 1 meter (3 feet) diameter when measured in any direction.  Seat rocks are barrier rocks that have one relatively flat surface and can be use for a seat when installed in the ground.  Seat rocks shall be selected by the Engineer from the Contractor's rock source.

650-2.17  INTERPRETIVE KIOSK, TYPE B. Conform to Standard Drawing S-10B, Interpretive Kiosk, Type B.  Interpretive panel frame, bulletin board frame and 50 mm x 150 mm (2x6) concrete column forms shall be surfaced four sides clear cedar.  Column bases shall be painted or corrosion resistant column base for embedment in wet concrete to connect wood post to concrete footing.  Size column base to dimension of post.  Rough cut posts shall have full dimension column bases.  Stirrup shall be provided with holes for two galvanized bolts with washers.  Similar to Simpson CB88R.

| Post Size | Base Plate Thickness & Dimension | Stirrup Material | Post Bolts | Allowable Uplift Load |
| --- | --- | --- | --- | --- |
| 200mmx200mm (8" X 8") | 4.6 mm & 200mmx200mm 7 ga & 8" X 8" | 6.1 mm x 75 mm strap (3 ga x 3" strap) | 2 each 19 mm (2 each 3/4") | 3020kilograms (6,650 pounds) |

650-2.18 ENTRANCE SIGN.  Conform to Standard Drawing S-3, Entrance Sign.  Sign frame shall be surfaced four sides clear cedar.  Column bases shall be painted or corrosion resistant column base for embedment in wet concrete to connect wood post to concrete footing.  Size column base to dimension of post.  Rough cut posts shall have full dimension column bases.  Stirrup shall be provided with holes for two galvanized bolts with washers.  Similar to Simpson CB88R.

| Post Size | Base Plate Thickness & Dimension | Stirrup Material | Post Bolts | Allowable Uplift Load |
| --- | --- | --- | --- | --- |
| 200mmx200mm (8" X 8") | 4.6 mm & 200mmx200mm (7 ga & 8" X 8") | 6.1 mm x 75 mm strap (3 ga x 3" strap) | 2 each 19 mm (2 each 3/4") | 3020kilograms (6,650 pounds) |

- UNIT AND SITE NAMES

Unit Name:				CHUGACH STATE PARK

Site Name:				BIRD CREEK

Site Classification:			ACCESS

650-2.19 DOUBLE TOILET SCREEN.  Conform to Standard Drawing, Double Toilet Screen.

1.	Blockwork.  Reinforcing steel shall conform to Section 503.  Cleaning solution shall be non-acidic, not harmful to masonry work or adjacent materials, recommended by masonry unit manufacturer.  Mortar shall be Type N with liquid polymeric water repellent admixture.

Concrete Masonry Units (CMU) shall conform to the requirements of Subsection 704-2.03 for hollow concrete masonry blocks manufactured with water repellent admixture.  CMU shall have split faces on exposed surfaces.  Blocks shall be colored by adding pigment to the lots during manufacture.  Two shades of gray are required, one medium and one medium to dark.  Submit color samples to the Engineer for approval.

NOMINAL DIMENSIONS OF TYPICAL CONCRETE BLOCK

| Height | Length | Width |
| --- | --- | --- |
| 100 mm (4”) | 200 mm(8”) | 100 mm (4”) |
| 200 mm (8”) | 400 mm (16”) | 200 mm (8”) |

2.	Concrete Cap.  Type A Concrete.

CONSTRUCTION REQUIREMENTS

650-3.01 GENERAL.  Location shown on the drawings of park facilities are approximate.  The Engineer will field locate park facilities at the time of construction.

650-3.02 EXCAVATION AND BACKFILL.  Conform to the requirements of Section 204 and the details on the Plans.

650-3.03 CONCRETE.  Conform to the requirements of Section 501 and the details on the Plans.

650-3.04 STRUCTURAL STEEL.  Welding to conform to American Welding Society D1.1.

650-3.05 WOOD.  Competent carpenters shall be employed and all framing shall be true and exact.  Unless otherwise specified, nails and spikes shall be handdriven with just sufficient force to set the heads flush with the surface of wood.  Power nail guns are prohibited.  All non-removable shipping, storage, weathering and erection marks on fabricated lumber shall be located so as to be hidden from view in the completed work.  Use of damaged lumber shall not be allowed.  Store on-site lumber above the ground and protected from damage and weathering.

Holes for round drift-bolts and dowels shall be bored with a bit 2 mm (1/16”) smaller in diameter than that of the bolt or dowel used.  Holes for machine and carriage bolts shall be bored with a bit of the same diameter as that of the bolt.  Holes for lag screws shall be bored with a bit not larger than the body of the screw at the root of the thread.

Unless otherwise specified, USS flat washers shall be used in contact with all bolt and heads or nuts that would otherwise be in contact with wood.

650-3.06 PAINT.  Deliver in sealed containers with labels legible and intact.  Remove dirt, grease, oil and other construction debris prior to painting.  Insure that surfaces to be painted are even, smooth, sound, clean, dry, and free from defects affecting proper application.  Metal surfaces to receive paint shall be corrosion free.  Apply per manufacturer's recommendations.  Apply paint material evenly without runs, sags, or other defects.  Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer.  Cover surfaces completely to provide uniform color and appearance.  Remove all paint, stain, or other finish material where it has spilled or spattered.

- 1.	General.  Unless otherwise specified, schedule finishes as follows:

a.	Non-Treated Wood, Surfaced.  Finish surfaces not scheduled to receive stain or clear oil stain with wood preservative.

b.	Non-Treated Wood, Rough Cut.  Saturate below and above ground surfaces not scheduled to receive stain with wood preservative.

c.	Treated Wood, Hidden.  Dados, cut ends, drilled holes and field cuts in wood materials shall be brush coated to saturation with end cut preservative.

d.	Treated Wood, Exposed.  Saturate cut surfaces with scheduled finish. Finish surfaces not scheduled to receive stain with wood preservative.

e.	Concrete and Masonry.  Seal exposed surfaces.

f.	Metal.  Prime and paint exposed metal surfaces that are not fabricated of corrosion resistant material or galvanized.

2.	Single Entrance Gate.

- Metal.  Primer and Heavy Duty Aluminum Enamel Paint

3.	Double Entrance Gate.

a.	Metal.  Primer and Heavy Duty Aluminum Enamel Paint

4.	Concrete Parking Bumper.

a.  Concrete.  Sealer

5.	Parking Bumper.

a.	Wood.  Clear Oil Stain

6.	Interpretive Kiosk, Type B.

a.	Interp/Bulletin Board Frame and Exposed T&G Wood.  Clear Oil Stain

b.	Other Wood.  Semi-Transparent Oil Stain

c.	Metal.  Primer and Enamel Paint

d.	Bulletin Board Sound Board.  Off White Flat Latex Paint

7.	Entrance Sign.

a.	Clear Cedar.  Clear Oil Stain

b.	Other Wood.  Semi-Transparent Oil Stain

c.	Metal.  Primer and Enamel Paint

650-3.07 SINGLE ENTRANCE GATE.  Construct in accordance with Standard Drawing G-1, Single Entrance Gate.

650-3.08 DOUBLE ENTRANCE GATE.  Construct in accordance with Standard Drawing G-2, Double Entrance Gate.

650-3.09 CONCRETE PARKING BUMPER.  Construct in accordance with Standard Drawing P-6, Parking Bumper.

650-3.10 PARKING BUMPER.  Construct in accordance with Standard Drawing P-6, Parking Bumper.

650-3.11 BARRIER ROCK. Place barrier rocks 1.2 meters (4 feet) apart, edge to edge, with approximately 20 percent of the height of each rock set below ground level.  When finish surface is pavement, place barrier rocks prior to paving operation.  Cutting pavement to place barrier rocks and then patching is not acceptable.

Place seat rocks with 450 mm to 600 mm (18 to 24”) seat height and a minimum of 20 percent of the height of rock set below ground level.

650-3.12 INTERPRETIVE KIOSK, TYPE B.  Construct in accordance with Standard Drawing S-10B, Interpretive Kiosk, Type B.

650-3.13 ENTRANCE SIGN.  Construct in accordance with Standard Drawing S-3, Entrance Sign.

    - RELOCATE SINGLE ENTRANCE GATE.  The existing single entrance gate including foundation shall be carefully removed.  If gate is damaged during removal it shall be repaired or replaced at no additional cost to the Department.  Existing foundation may be reused if determined acceptable by the engineer.  If a new foundation is needed it shall be constructed in accordance with Standard Drawing G-1, Single Entrance Gate.

650-3.15 DOUBLE TOILET SCREEN.  Construct in accordance with Standard Drawing, Double Toilet Screen.

1.	Blockwork.  Install concrete block columns with random pattern as shown on the Plans.  All exposed faces shall be split face.  Mortar joints shall be 3/8” struck smooth.  Tint the mortar to match the medium gray block.  Custom cut blocks as required to obtain proper course length.  Maintain uniform dimensions for masonry courses.  Vertical and horizontal joints shall be of uniform thickness.  Fill the concrete masonry units and construct concrete cap with Type “A” concrete.  Install wall ties in accordance with the manufactures recommendations.  Concrete cap shall receive a hard trowel finish.

650-4.01 METHOD OF MEASUREMENT.  Park facilities with the unit measure each will be measured by the actual number of facilities completed and accepted.

Excavation and embankment for park facilities outside the limits shown on the Plans will be measured for payment only if said activity is directed by the Engineer.  Excavation and backfill required for facilities paid for under this section will not be measured for payment.

Seat rocks at Interpretive Kiosk, Type B, will be subsidiary to that item and will not be measured separately for payment.

650-5.01 BASIS OF PAYMENT.  The accepted quantity of park facilities will be paid for at the contract unit price per unit of measurement for the type specified completed in place, and listed below excluding all clearing, grubbing, topsoil and crushed aggregate base course, which shall be paid for separately at contract unit prices.

When work consists of relocating a park facility, letter suffix A will be included within the parentheses of the item number and "Relocate" add to the beginning of the pay item name.

Accessible models of a park facility item will be compensated at the same unit price as the standard model.  (4/15/95)PARKS

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 650(8) Single Entrance Gate | Each |
| 650(8A) Relocate Single Entrance Gate | Each |
| 650(9) Double Entrance Gate | Each |
| 650(17) Concrete Parking Bumper | Each |
| 650(18) Parking Bumper | Each |
| 650(21) Barrier Rock | Each |
| 650(30B) Interpretive Kiosk, Type B | Each |
| 650(38) Entrance Sign | Each |
| 650(45) Double Toilet Screen | Each |

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Delete Item 4 in its entirety and substitute the following:

4. Methyl Methacrylate Pavement Markings.  Apply Methyl Methacrylate markings with truck-mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.  Provide the manufacturer’s installation instructions for the Methyl Methacrylate markings at least 15 days prior to application.  Retain a copy of the instructions for use on the project.

A manufacturer’s representative shall be present on the first day of striping and any additional days as required by the Engineer.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Perform a film test strip at the beginning of each striping shift and when there is a change in asphalt type.   In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion.

Apply glass beads as specified in Subsection 712-2.18. Use a minimum drop on rate of 580 g/m2 for transverse type markings.  Apply glass beads for Type V sprayed material by double bead gun, one gun directly in front of the spray unit and another directly behind.

Remove contaminants such as curing agents, surface oils or existing pavement marking materials prior to applying the new pavement markings. Then, thoroughly clean and dry the roadway surface immediately prior to applying Methyl Methacrylate pavement markings.

Apply Methyl Methacrylate pavement markings as shown in the following table.  The table shows final design thickness.  The maximum allowable yield thickness per single-pass of Longitudinal Type markings (non-inlaid) is 60 mils (1.5 mm).

#### METHYL METHACRYLATE PAVEMENT MARKING

#### YIELD THICKNESS TABLE

| Marking Type | Non-Inlaid Markings1 | Inlaid Markings2 |
| --- | --- | --- |
| ##### Longitudinal Type3 ##### (Center and Edge lines) | 90 mils (2.3 mm) | 230 mils (5.8 mm) |
| Transverse Type (Cross Walks, Stop Bars, “Only”s, Arrows and Tracking Lines) | 120 mils (3.0 mm) | 230 mils (5.8 mm) |
| Neutral Area (Diagonals, Chevrons) | 60 mils (1.5 mm) | Do not inlay these markings |

1. Measure Type V spray without glass beads.  Tolerance is ±4 mils (±0.1 mm).  Measure the thickness utilizing a wet film thickness gauge.  Collect a sample on a 6” x 12” (150 mm x 300 mm) flat sheet of 80 mils (2 mm) thick aluminum placed in the path of the striping guns.

2. Cut the inlaid slots to a depth of 250 mils (6.35 mm).  Do not over fill the slots.

3.  Install Non-Inlaid Longitudinal Type markings at a maximum yield thickness of 60 mils (1.5 mm) per application pass.

Non-Inlaid Markings

New asphalt pavement:  Apply interim non-inlaid Longitudinal Type markings at 30 mils (0.75 mm).

Unless directed otherwise by the Engineer, apply the final markings once the asphalt has cured for the duration listed below.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Existing asphalt pavement:  Apply markings according to the Yield Thickness Table.  Longitudinal Type markings will require multiple application passes.

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the removal requirement. Do not use any method utilizing burning with an open flame for removing pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width for any 15 m longitudinal run from the width shown in the Plans.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B).  No separate payment shall be made for furnishing and maintaining the MMAMS.

***Deleted***

(08/21/02)R246

Payment will be made under:

| #### Pay Item | #### Pay Unit |
| --- | --- |
| 670(10B) Methyl Methacrylate Pavement Markings | Liter |

This page intentionally left blank

-

-

Ad

d the following Section:			SECTION 680

## TELEPHONE RELOCATION

# Special Provisions

680-1.01 DESCRIPTION.  This work includes furnishing and installing three complete conduit systems in accordance with these Specifications and the Plans.

The conduit systems include installing innerduct by trenching, trenching with concrete slurry backfill, boring and plowing, prefabricated vaults (handholes), and all appurtenances, materials and devices required to install, support, secure and provide a complete system for supporting and protecting the fiber optic cables.

In order to avoid cumbersome and confusing repetition in this Section, it is provided that when ever “the Inspectors” is used it shall mean “the ACS Inspector and the AFS and GCI contract inspectors”.

680-1.02  CODES AND STANDARDS.  Conduit system materials and devices furnished shall be in accordance with applicable standard of ANSI, ASTM, NEMA,UL, AND ALL LOCAL CODES AND PERMITS. Conduit systems components shall be installed in accordance with applicable requirements of the NEC. In a case of conflict between the requirements of any of the above referenced codes and standards and requirements of these Specifications, the requirements of these Specifications shall govern. All materials, devices, and practices shall be in accordance with the applicable requirements of the Federal “ Occupational Safety and Health Standards.”

680-2.01 MATERIALS.  ACS will furnish the following materials at no cost to you:

- Vaults and lids for 4890 and 3048 Fiberglass

2.	EMS (Electronic marker System)

3.	Ground rods, #6 SDC ground wire, and clamps

# 4.	6-pair Drop Wire (BSW) on 5000 ft. reels

5.	Buried Warning Tape Orange Rolls

6.	PVC Schedule 40 conduit, couplings and solvent

7.	Buried Service Wire Splice kits

ACS MATERIALS

All materials furnished by ACS will be located at ACS’s warehouse. 600 Telephone Avenue, Anchorage, (south yard).

Determine your material take-off requirements and prepare a complete itemized list of materials for submittal to ACS within five (5) days of receiving the Notice-to-proceed.  Deliver a list of required materials to ACS, through the ACS Construction Clerk, at least 24 hours in advance of pickup time. Pick up all the material required to complete the project at one time, not on a “as-needed” or daily basis.

ACS will stage the material for pick up if it is ordered at least 72 hours in advance.  Vaults will be loaded on your vehicle by others at no cost to you.

Sign for the materials at the time of receipt. The ACS warehouse foreman will be available for materials issuance between the hours of 7:30 AM to 12:00 noon and 1:00 PM to 4:30 PM daily except Saturdays, Sundays and ACS holidays. You will be billed for the loaded labor rate time plus a 25 percent handling overhead fee if you require ACS to open the warehouse for your convenience and/or to procure a special issuing of material at times other than normal working hours. You are responsibly for storage and safekeeping of all materials after pickup from ACS.  Return all unused materials to the warehouse upon completion of the project.

You shall furnish the following items:

1.	Visqueen or other covering materials for concrete curing

2.	Separation geotextile

3.	Concrete grout and mortar

4.	Vault lifting slings and lifting eyes

5.	Innerduct Couplers, Fusion type (Approved by ACS)

6.	Fusion Splicer (Central)

8.	Innerduct, Dura-Line Part No. 1215-11, 31.75 mm (1 ¼”) SDR 13.5 Smooth Wall and orange in color

9.	Urethane Foam expanding 32 kg/m3 (2 Lbs/Ft3) (2 part)

10.	Innerduct Plugs (water tight)

11.	Pea Gravel

12.	D-1 Foundation Base

13.	Asphalt Concrete

14.	Pre-measured jet line

15.	Concrete Encasement

16.	Duck spacers, Carlon Spacers Part No.  S289RFN& S288NFN

17.	4878 Base

4878 610 mm (2’) Vault

4878 305 mm (1’) Riser

4878 Lid with a 1,067 mm (42”) Opening

4878 Grade Rings with 1,067 mm (42”) i.d openings

Cast Iron Frame and Access Cover Unit No. 716-4 & 716-5

Boxes of Ram-Nek Sealer

Unit From Pre Cast Concrete Co. Inc. Anchorage, AK.

18.	All miscellaneous tools and hardware, and non-furnished material necessary to construct and install this system.

AFS MATERIALS

AFS will furnish the following materials at no cost to you:

1.	BFO24 (Buried Fiber Optic cable, 24 Fiber on real)

2. 	Warning Maker Tape 3435 m 11,270’ (Has Alaska Fiber Star stenciled on tape).

The AFS furnished materials listed above can be picked up at the AFS warehouse located at 8717 Diamond “D” Circle, Anchorage Alaska, 99515. Call (907-365-7200).  Provide AFS with 72 hours advance notice prior to picking up materials.  The warehouse hours of operation are from 8:AM to noon Monday through Friday. Return all unused materials to the warehouse upon completion of the project.

You shall furnish the following materials:

1.	Dura-line Ribbed Innerduct (Specifications : High Density Polyethylene-PE-3408)1-1/4”, Inside Diameter, Red in color, 3436.3 m (11,274’) in length.

2.	Innerduct Couplers (Approved by AFS)

3.	Electro Fusion System Coupler

4	Innerduct plugs

5.	One HH(4878 Handhole) Unit, consisting of the following:

1-EA. 4878 Base

1-EA. 4878 610 mm (2’) Riser

1-EA 4878 305 mm (1’) Riser

1 EA. 4878 Lid with a 1,067 mm (42”) opening

1-EA. Cast Iron Frame and Access Cover

1-EA. Box of Ram-Nek Sealer 21.3 m (70’)

Unit From Pre Cast Concrete Co. Inc. Anchorage, AK.

6.	One HH (3660 Handhole) Unit consisting of the following:

1-EA 3660 Base

2-EA Lids

7.	Handhole lifting slings and lifting eyes.

8.	All miscellaneous tolls and hardware, and non-furnished material necessary to construct and install these system.

GCI MATERIALS

GCI will furnish the following materials at no cost to you:

1.	Vaults

2.	Vault frame and covers

3.	RAMNECK and gasket sealant materials for handholes

4.	Ground rods, #6 SDC ground wire, and clamps

5.	1-1/4” HDPE Innerduct, black in color

The GCI furnished materials will be located at the GCI warehouse located at 5151 Fairbanks Street, Anchorage, Alaska.   Determine your material take-off requirements and prepare a itemized list of materiasl for submittal to GCI within five (5) days of Notice-to-proceed.  Deliver a list of required materials to GCI, through the GCI Construction Project Manager, at least 24 hours in advance of pickup time. Pick up all the required materials at one time, not on an “as-needed” or daily basis. If you order the materials at least 72 hours in advance, GCI will stage the materials for pick up. Vaults will be loaded on your vehicle by others at no cost to you.

Sign for materials at the time of receipt. The GCI warehouse foreman will be available to issue materials between the hours of 1:00 PM to 4:00 PM daily Monday through Friday and GCI holidays. You are responsibly for storage and safekeeping of all the materials after pickup from GCI.  Return all unused materials to the warehouse upon completion of the project.

You shall furnish the following items:

1. 	Visqueen or other covering materials for curing concrete

2.	Separation geotextile

3.	Concrete grout and mortar

4.	Vault lifting rings and lifting eyes

5.	Marker Tape (Terra tape extra stretch # 540)

6.	Innerduct Plugs

7.	All miscellaneous tools and hardware, and non-furnished material necessary to construct and install these systems.

#### PAY ITEM SPECIFIC DETAILS

Item 680(6):  Furnish and install H-20 vehicle rated Type 4878 telephone handholes and/or vaults with grade ring castings as shown in the Plans.

Item 680(6A): Furnish and install Type 3660 telephone handholes as shown in the Plans.

Item 680(6B): Install Type, 3048 or 4890 Vaults as shown in the Plans and described in the Specifications.

Item 680(10): Furnished and Install one 31.75mm, red in color HDPE innerduct.

The Railroad crossings may be trenched, jacked or bored at your option.

Items 680(11): Furnish and Install two (2) 31.75 mm, orange in color HDPE innerducts into common trench and encase in concrete or bed in sand as per the Plans. Install by trenching.

Item 680(12): Install Three (3) 31.75 mm, black in color HDPE innerducts into a common trench, and encase in concrete or bed in sand as per the Plans. Install by trenching.

Item 680(13): Install three (black) & furnish and install two (orange) HDPE innerducts.  Install the five 31.75 mm HDPE innerducts into a common trench and encase in concrete as per the Plans.  Install by trenching.

Item 680(14): Install two 100 mm PVC conduits into a common trench and concrete encased as per detail. Install by trenching.

Item 680(15): Install the following into a common trench and encase in concrete as shown in the Plans:

Utility furnished:	Two (2) 100 mm PVC conduits

Three (3) 31.75 mm innerducts (black)

Contractor furnished:	Two (2) 31.75 mm innterducts (orange) inside one (1) 100mm PVC Conduit.

Install by trenching.

Item 680(16): Install two (2) 100 mm PVC Conduits and three (3) 31.75 mm HDPE Innerducts in a common trench and encase in concrete as shown in the Plans.

Item 680(17): Furnish Fiber Optic Cable Installation Specifications and install fiber optic cable into the innerduct system.  Install the Utility furnished BFO24 fiber optic cable into the AFS completed innerduct system as per the AFS plans.

680-3.01 GENERAL CONSTURCTION REQUIREMENTS. 	The Inspectors reserve the right to suspend installation of the conduit system, through the Engineer, if at any time you fail to meet the requirements set forth herein.  The suspension will be in effect until you make the necessary corrections. Suspension of work will not entitle you to an extension of time for the completion of the project, and will not entitle you extra payment for costs incurred.

Coordinate your construction operations with the ACS inspector and on site crew foreman.  Allow ACS, and GCI crews access to the job site for the fiber installation and splicing operation with an advance 24-hour notice to you.  Allow AFS crews free access to the job site for the fiber cable splicing operation.

You are responsible for locating, shoring and protecting of all property, (real and personal) in the vicinity of the project. While ACS, AFS and GCI have tried to reflect the location of all sewer, water, storm drains, electric, telephone and gas lines, key boxes, valves and poles on their drawings, it is your responsibility to establish the location of each facility by calling for field locates in accordance with Subsection 105-1.06, Cooperation with Utilities.  The offsets referenced on the ACS plans from project centerline and highway centerline for the ACS relocation designs are for informational purposes only.  Your trench alignment for the ACS relocation shall maintain 1.83 m (5’) of separation from all the existing GCI facilities.

Once the work commences, you, the Engineer, and the Inspectors shall meet once each week to review the work you have done to date.  Your schedule for the following week’s work shall be reviewed as well. Submit your anticipated hourly work shift schedule in writing by noon on the Wednesday prior to the next workweek.

Construct all telephone handholes and vaults within an allowable tolerance of 0.003 m (0.1’) of the plan location and elevation in any phase of the construction. The Inspectors shall field verify the final grade of the telephone vaults prior to backfill. Backfill all vault and trench excavations within 48-hours.  Never leave more than 30.48 m (100’) of trench exposed at the end of any shift.

Do not stage materials, equipment or vehicles on the traveled surface. You may only use wide shoulders and turnouts with the written permission of the Engineer. You may only use private property for this purpose if granted permission in writing by the property owner and the Engineer approves it prior to its use.

Only ACS qualified contractors shall install ACS telephone facilities. A list of qualified contractors may be obtained by contacting the ACS purchasing office at 564-1414.

680-3.02 GENERAL INNERDUCT INSTALLATION REQUIREMENTS.  Lay the innerduct in the center of the trench. Winding, coiling, or snaking of the innerduct in the trench will not be allowed. Remove all rocks, or other materials, which could damage the innerduct, from the trench bottom before placing the innerduct. Grade the trench bottom smooth. Obtain written approval from the Inspectors and the Engineer to vary the depth requirement if the minimum cover of 1.22 m (4’) can not be maintained within the DOT right-of-way.  Supply concrete encasement for protection of the installed ACS facilities when the design depth cannot be obtained.

You may use native material for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material except 100% shall pass the 75 mm (3”) sieve.  Place native backfill material in layers and compacted as directed by the Engineer.

Dispose of waste excavation in accordance with Subsection 680-3.07  Disposal of Waste Excavation.

Sand bedding shall meet the requirements of Subsection 680-3.09 Sand Bedding.

Prior to backfilling rock trench areas, all AFS trench areas, placing vaults and constructing gravel pads as shown on the ACS, AFS and GCI plans, install separation geotextile.  Wrap the separation geotextile completely around the sand bedding for the AFS trench.  Provide a 300 mm overlap on top of the sand bedding and below the marker tape.  Separation geotextile shall meet the requirements of Section 630, Geotextile for Embankment Separation and Reinforcement.   Borrow; Type A shall meet the requirements of Subsection 703-2.07, and shall be constructed in accordance with the requirements of Subsection 203-3.03, Construction of Embankments with Moisture and Density Control.  Provide a temporary access to the pad site at a location approved by the Engineer.

Cut, fusion splice and place the ACS innerduct in accordance with the manufacture requirements, and as detailed on the Plans. Provide cut sheets/information for the type of innerduct fusion splice coupler you propose to use to the ACS Inspector for approved five (5) calendar days prior to beginning the innerduct placement and splicing installations.  Provide a manufacture-approved method for splicing the innerduct to GCI, or their contract inspectors, five (5) calendar days prior to beginning innerduct installation and splicing. Place an EMS marker above every splice in the ACS innerduct and identify all these locations on the ACS As-built.

Complete all splicing of the ACS, AFS and GCI innerduct in the presence of the Inspectors.  Install the service wire and marker tape in accordance with the details shown on the Plans.

Maintain a minimum clearance of 600 mm (24”) from conflicting obstructions where the ACS, AFS and GCI innerduct passes above or below an underground utility line, culvert or other buried facilities. You may be required to over excavate the trench in order to provide adequate cover for the innerduct installation. You may need to over excavate to construct smooth transitions of the trench over abrupt terrain.   Contact the Inspectors and the Engineer prior to starting any over excavation to determine if over excavation is required.

Lay all ACS, AFS and GCI innerduct to the exact grade in the trench as shown in the Plans.  The ends shall enter handholes and/or vaults horizontally as indicated on the Plans.  Use end bells on all vault entries except where another type of termination is specified or detailed on the Plans.

Keep all innerduct protected from sunlight as required to prevent ultraviolet degradation and curvature and deterioration due to thermal expansion.

Do not install defective innerduct.  Immediately remove any innerduct the Engineer deems defective from the worksite.  Take particular care to keep concrete or other substances from the inside of the innerduct during construction. Install all reinforcing materials and other magnetic materials parallel to the lengths of the innerduct, except for the anchoring material. You are responsible for anchoring the installed system to ensure that flotation does not occur. Submit an anchoring design to the Engineer and the Inspectors for approval five (5) calendar days prior to installation.   Use Carlon Plastic spacers in all joint trench areas to maintain separation of utility facilities. Place spacers at 1.5 m (5’) foot intervals.  Adjust plastic bases in lose trench bottoms to provide minimum sag in the innerduct installation. Ensure the trench bottom is smooth and leveled prior to installing the innnerduct.

Clean and test the innerduct prior to ACS or GCI crews, or their contractor, installing the new fiber optic cable in the innerduct.  Plug any innerduct which is not to be immediately used with an airtight seal at each end and mark with an EMS marker.  Remove any and all foreign materials, earth, sand, and gravel from the innerduct.  Pass an ACS provided foam mouse or flexible missile with a Green Lee pre-measured jet line in one of the ACS innerducts as a clearance test.  Pass a missile through the remaining ACS innerduct from access point to access point.  Coordinate and perform all the ACS innerduct testing work addressed above in the presence of the ACS Inspector. The pre-measured jet line for the ACS innerduct shall be measured and recorded by the inspector and verified by your signature in the presence of the Engineer.  The requirements outlined above shall take place prior to the acceptance of the ACS innerduct system.  Identify and expose any innerduct area that a missile cannot pass through. Repair any defects you caused at your expense.

Work to develop and provide the Inspectors a clearance test method and acceptance requirements for the AFS and GCI innerduct system that is acceptable to each utility.  Provide the acceptable clearance test method to the Inspectors five (5) calendar days prior to starting the clearance and acceptance requirements for the AFS and GCI innerduct systems.

You and the Inspectors shall measure and record the wall-to-wall distance of the installed innerduct and record that measurement on the drawings provided by the Engineer.   Proofing of the innerduct shall immediately follow innerduct installation from access point to access point.

Maintain a complete and accurate record of the innerduct offsets and sequential innerduct distances.  Supply the Engineer with a complete sequential distance log on a per reel basis within five (5) days after the installation of each reel of innerduct.

Replace existing asphalt removed with Asphalt Concrete, Type II; Class A in accordance with Section 401 after installation. Temporary asphalt may be replaced if the temperature limitations in Subsection 401-3.01 Weather Limitations cannot be met.  If temporary asphalt is used, remove and replace it with Asphalt Concrete, Type II; Class A as soon as possible once the weather limitations can be met.

Dispose of removed asphalt in accordance with Subsection 202-3.05 Removal of Pavement, Sidewalks, and Curbs.  Dispose waste excavation in accordance with Subsection 680-3.07, Disposal of Waste Excavation.

Concrete Encasement shall meet the requirements of Subsection 680-3.08 Concrete Encasement.

Sand bedding shall meet the requirements of Subsection 680-3.09, Sand Bedding

D-1 material shall meet the requirements of Section 301, Aggregate Base and Surface Course and Subsection 703-2.03 for Type D-1.

You are responsible for all handhole and /or vault required openings.  Using a hacksaw, a hole saw, or a core drill, provide required openings not provided during fabrication.  The method you use is subject to acceptance by the Inspectors.  Finish openings that have been cut through walls of masonry or concrete for the passage of the innerduct by grouting around the innerduct.  Then place expanding urethane foam around the innerduct as shown on the Plans.

AFS INNERDUCT, JOINING AND CONNECTING REQUIREMENTS

Use electro fusion joint couplings (Central Plastics or approved equal) unless specified other wise for all innerduct joints and connectors. Use electro fusion couplings for attaching dissimilar materials (HDPE to galvanized rigid steel).  Use Sherman & Reilly DC-10 or approved equal where HDPE to HDPE split case couplings are necessary.  Couplings shall be resistant to pullout due to expansion and contraction of adjacent piping. All buried split couplings shall be installed and externally protected with heat shrink sleeves where possible, otherwise use cold shrinkable tape wrap.

No internal lips shall be allowed at the joints that will interfere with the blowing of the fiber cable operation into the innerduct. Check all couplings for defects that could damage the cable or reduce the rating of the joint.  Do not use the coupling if deficient in any way. Be careful so that no internal dripping of HDPE occurs at the couplings. Calibrate all electro fusion equipment daily to insure proper fusion.  Provide AFS or their contract inspector with the method and type of equipment that is to use for the electro fusion joint splicing for approval seven (7) calendar days prior to starting any electro fusion joints splicing.   AFS, or their contract inspector may require that they are present for all electro fusion splicing required for this project. If requested, provided a schedule to AFS, or their contract inspector, for electro fusion splicing.

680-3.03 ROAD AND RAILROAD CROSSING INNERDUCT.    The ACS innerduct installation plan calls for crossing the Seward Highway at the following locations: Sta. 36+225, 40+340.  In addition, an ACS crossing will be required for the Bird Point Overlook access road, at approximate Seward Highway Sta. 36+525 Lt. and the ACS relocation plan calls for the innerduct to cross the proposed pathway at approximately Seward Highway Sta. 36+019 Rt.  Construct all ACS road crossings to maintain a minimum of 1.22 m (4’) below the ditch bottom or as directed by the Engineer and the ACS Inspector.

The AFS innerduct installation plan calls for crossing the existing railroad tracks at the following locations: AFS Sta. “R” 1+675 and Sta.”R”5+111.1.  The proposed AFS crossing at approximate AFS Sta. “R” 1+675 will be out side of the new railroad alignment area.  Maintain a minimum of 1.83 m (6’) below finish track grade in the above crossing locations or as approved by the Engineer, the ARRC engineer and the AFS contract inspector.

Trench, bore, or otherwise force the innerduct underneath the railroad at crossing AFS Sta. “R” 1+675.  You may install the innerduct in a casing.  There shall be space between the earth and the outside of the innerduct or casing pipe. Wet bores shall not be permitted.  Only use enough water to lubricate the casing during installation.

If using casing pipe, install it using jacking equipment. Install casing such that the hole is cased as earth is removed through the interior of the casing.  Boring without the concurrent installation of the casing pipe will not be permitted.

Install the innerduct/casing pipe in a manner that will not disrupt traffic or damage the subgrade while maintaining accurate alignment and grade of the pipe.

Use new smooth wall casing pipe fabricated from welded steel. Select the diameter and wall thickness of the casing to allow installation in the type of materials encountered.

Provide casings with welded joints and machine cut ends beveled at 37 ½ degrees.  The beveled ends shall be butted, aligned axially and welded to provide a full strength joint for resisting all stress, including jacking stresses.

Submit complete details of your proposed methods, materials, and time schedule to the Engineer before starting work on the crossing. Do not begin work on the crossing until you receive written notification to proceed from the Engineer.

Use 100 mm (4”) diameter steel bore casing pipe.  Align the bore casing within 0.60 meters (2’) of the staked requirements per 30.48 m (100’) of casing installed.  At no time shall the depth of the bore be less than that indicated on the Plans. Bores shall meet the above requirements and provide 97% utilization of the design bore size to be considered successful. Install an EMS marker and a stake at each end of the innerduct with the station and depth of the innerduct ends of the casing during backfill operations as detailed on the Plans.

The GCI innerduct installation plan calls for the crossing the Seward Highway at Sta. 40+340, Sta. 44+730 and GCI Sta. 45+598. Construct all GCI road crossings to maintain a minimum of 1.22 m (4’) below ditch bottom or as approved by the Engineer and the GCI contract inspector.

Install the ACS and GCI innerduct for the road crossings by trenching. Submit complete details of your proposed methods, traffic maintenance and time schedule to the Engineer before staring any of the ACS and GCI road crossings.  No work shall begin on any crossing until written notification to proceed has been obtained from the Engineer.  Provide a copy of the written notice to the Inspectors.

Replace all existing asphalt removed with Asphalt Concrete, Type II; Class A in accordance with Section 401. You may place temporary asphalt if the temperature limitations in Subsection 401-3.01, Weather Limitations cannot be met. If temporary asphalt is used, remove and replace it with Asphalt Concrete, Type II; Class A as soon as the weather limitations can be met.

Dispose of all asphalt pavement removed in accordance with Subsection 202-3.05, Removal of Pavement, Sidewalks, and Curbs. Dispose waste excavation in accordance with Subsection 680-3.07, Disposal of Waste Excavation.

Concrete Encasement shall meet the requirements of Subsection 680-3.08 Concrete Encasement.

Sand bedding shall meet the requirements of Subsection 680-3.09, Sand Bedding

D-1 material shall meet the requirements of Section 301, Aggregate Base and Surface Course and Subsection 703-2.03 for Type D-1.

680-3.04 INSTALLING INNERDUCT.  Install the innerduct in accordance with the detail sheets for each utility design as shown on the ACS AFS and GCI plans.

Lay the innerduct in the center of the trench. Winding, coiling, or snaking of the innerduct in the trench will not be allowed. Remove all rocks, or other materials, which could damage the innerduct, from the trench bottom before placing the innerduct. Grade the trench bottom smooth. Obtain written approval from the ARRC Engineer and AFS, or their contract inspector to vary the depth requirement if the minimum cover of 1.07 m (42”) can not be maintained within the ARRC embankment.

You may use native material for the trench backfill if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07, Selected Material except 100% shall pass the 75 mm (3”) sieve.  Place native backfill material in layers and compacted as directed by the Engineer.

Dispose of waste excavation in accordance with Subsection 680-3.07  Disposal of Waste Excavation.

Sand bedding shall meet the requirements of Subsection 680-3.09 Sand Bedding.

680-3.05 INSTALLING CONDUIT (100 mm).  Install all ACS 100 mm (4”) PVC conduit in conformance with the lines and grades shown on the ACS plans, or as directed by the Engineer and ACS Inspector.

Paint the inside of all 100 mm (4”) PVC conduit fittings and the ends of all 100 mm (4”) PVC conduit with PVC solvent cement as prescribed by the manufacturer to make a water proof connection.

Install the 100 mm (4”) PVC conduit in open trenchs as per the manufacture’s recommendations, and as depicted in the Plans, with no more than 5 degrees deflection per 3.05 m (10’) of run.  Clean all conduit of dirt and debris.  Pass a rigid mandrill through the 100 mm (4”) PVC as a clearance test.  Use a mandrill that is 300 mm (12”) long with a diameter that is not less than 6.35 mm ( ¼”) of the PVC inside diameter.  Once you have successfully passed the mandrill through the conduit, place an ACS provided pull line in the conduit.

Secure all terminating 100 mm (4”) conduit ends with temporary end caps and mark with an EMS as shown in the Plans at the time the termination is backfilled.  Use duct seal, mortar, or urethane foam as directed by the ACS Inspector for terminations telephone vaults. You may have to furnish expansion couplings as directed by Engineer and the ACS inspector for some 100 mm PVC conduit runs.

You may be required to field bend the 100 mm PVC conduit as set forth on the Plans; however, ACS will provide the standard 5, 45 and 90 degree 100 mm PVC conduit sweeps.  The ACS inspector will inspect all 100mm PVC conduit that you form and bend prior to installation. Bent conduit that is deformed is not unacceptable, and shall be removed and replaced at your expense.

Design and provide all anchor stakes to prevent the 100 mm conduit from floating.  You are responsible for the effectiveness of the anchor stakes.  If flotation or misalignment of the conduit(s) occurs, make the all the necessary repairs at your expense.

All 100 mm Conduit Encasement shall be detailed on the Plans.

680-3.06 PRECAST CONCRETE AND FIBERGLASS HANDHOLES AND / OR VAULTS

Install the ACS, GCI vaults and AFS handholes in accordance with the details shown on the corresponding utility plans.  You are responsible for the cost of transportation, installation, repair and maintenance of ACS, GCI vaults and the AFS handholes until the vaults and /or handholes are accepted by ACS, AFS and GCI.  Remove handholes and/or vaults and re-compact the gravel foundation if, during placement, the gravel foundation proves to be inadequate to support the vault to designed line or grade (elevation).  Provide all vault-required openings not provided during fabrication using a hacksaw, a hole saw or core drill.  The openings are subject to acceptance by the Inspectors.  Finish all openings that have been cut through walls of masonry, concrete or fiberglass for the passage of innerduct by grouting around the innerduct.  Then place expanding urethane foam around the innerduct as shown on the Plans.

Prime and seal the concrete vault sections, frames and covers with primer and gasket sealant ( RAMNEK).  All ACS, AFS and GCI composite or fiberglass vaults do not require ramnek. Install two 2.44 m (8’) ground rods, one on each side of the vault excavation.  Drive from the base level down, or as directed by the ACS Inspector.  Install the AFS ground rods and vault ground wire as per the AFS detail sheet, or as directed by the AFS contract inspector.  Then, connect the ground rods to the vault ground wire leaving a 1.83 m (6’) loop of the same ground wire inside the vault as shown in the ACS plans.  Place the Buried Service Wire (BSW) through the vault as shown on the ACS plans. BSW wire shall be continuous, and all splices shall be encapsulated, and watertight. ACS shall supply all buried closures (KLIK-IT grease kits) for the Buried Service Wire (BSW).

Set the vault frame and cover to the design grade of the proposed paving, roadway finished grade in-slope or existing ground level or as directed by the Engineer, the Inspectors. Place an EMS marker on the floor of the all vaults as well as place a 100 mm x 150 mm (4” x 6”) marker post at all the vault locations as directed by the ACS Inspector.

Excavate all unusable material, as directed by the Inspectors, to a depth of 0.30 m (1’) below designed grade of all vaults and replace the excavated material with Selected Materials, Type A and/or Aggregate Base Course, Type D-1 bedding as required to establish the bottom finish grade of the vaults.  Compact the vault bedding material to 95% of the maximum density.  Although the ACS plans indicate elevations for the vault frames and covers, field verify the exact elevations with the Engineer.

Duct entries into all ACS vaults shall transition gradually from trench centerline into the ACS offset vault as detailed on the plans. Use of sweeps and elbows are at the discretion of the ACS Inspector and approval of the engineer. Approaches into the ACS vaults shall be 9.14 m (30’) on both sides of the vault. Construct pad sites for vault installations as per the ACS, AFS and GCI plan details.  The excavation and selected material placement described within this Subsection is subsidiary to the vault installation items.

680-3.07  DISPOSAL OF WASTE EXCAVATION.    Dispose of waste excavation within the project limits at locations approved by the Engineer. Feather the waste disposal areas into surrounding ground with no noticeable break or variation from the original contour of the area.  Maintain the existing drainage patterns.

680-3.08  CONCRETE ENCASEMENT.    Provide a mixture for the concrete encasement that contains a minimum of 223 kg of cement per cubic meter (four (4) standard 94 lb sacks of cement per cubic yard) of concrete. Place the concrete slurry when the air temperature is 0°C (32° F) or above.  You must propose alternate methods to ensure adequate curing temperatures will be met if the air temperature is below 0° C (32°F).  These may include concrete additives, additional cement, warming blankets, etc. and are subject to the approval of the Engineer.

680-3.09  SAND BEDDING.      Where existing material is unsuitable for the innerduct bedding as determined or as depicted on the corresponding utility detail sheets by the Inspectors, provide bedding sand meeting the following gradation:

| Sieve Size | Present Passing by Weight |
| --- | --- |
| 6.3 mm (¼”) | 100 |
| 0.075 mm (No. 200) | 0-6 |

680-3.10  SURVEYING AND STAKING.    Construct the innerduct alignment as shown in the Plans for the corresponding utility.  Changes to the alignment must be approved by the Engineer and Inspectors.  Locate and stake all handholes, vaults and telephone innerduct at the alignment and elevations shown on the Plans.  You are responsible for physically checking all lines and grades prior to placing any of the handholes, vaults and innerduct. These elevations checks shall include bottom elevations and handhole, vaults top elevations, to assure adequate clearance for the handholes, vaults frame and cover from final grade. Stake ACS vaults with offsets to centerline of the vault. Stake AFS handholes and GCI vaults as shown on the corresponding utilities detail sheets.

680-3.11  AS-BUILT DRAWINGS.  Maintain a complete and accurately dimensioned record of all deviations, deletions, additions, and alterations from and to the contract Plans and Specifications to indicate the work as actually installed. Each utility will provide you with a read-only CD that contains their AutoCAD® design drawing files (.dwg).

Maintain an accurate record of the underground location of all the telephone lines, handholes, vaults, and innerduct installed on the As-built plans and AutoCAD® design drawing files provided by ACS, AFS and GCI.  The ACS, AFS and GCI as-built drawings shall include all references (stationing and offsets) to highway and railroad track centerline at 30.48 m (100’) intervals.  Provide the coordinates of existing landmarks and exact locations of all handholes, vaults, and innerduct splice points in the project coordinate system.  The accuracy in locating the as-built features shall be equal to that required for the surveying and staking of the project (refer to the DOT&PF Construction Surveying Requirements).    Your as-built drawings shall note all obstructions, such as existing utilities, culverts, line and grade changes and elevation changes.  Note and reference the orientation of ACS facilities on the ACS as-built drawings in the joint trench location(s).  A Professional Land Surveyor licensed to practice in the State of Alaska shall stamp and certify the accuracy of the construction survey notes and revisions on the as-built drawings.

Prior to final acceptance of each of the systems by the owning utility, deliver the following to the Engineer:

- Two (2) copies of each utilities’ (ACS, AFS and GCI) final red-lined as-built drawings, signed and stamped by a Professional Land Surveyor licensed t practice in the State of Alaska.

[Total of six (6) final red-lined As-built drawings]

- Two (2) copies of each utilities’ (ACS, AFS and GCI) AutoCAD® design drawing files (.dwg) containing the as-built utility information on read-only CDs.  The files shall be in the owning utilities’ layering scheme. [Total of six (6) read-only CDs]

- A comma delimited ASCII text file containing all recovered, computed, topographic, and points collected during the as-built process.  The data shall be in the sequence:  Point Number, N, E, Z, Description.  Give coordinates to 4 decimal places for the Northings and Eastings, and three decimal places for elevations.  Give points of unknown elevation a placeholder of –9999 in the Z position.  Keep descriptors no longer than 30 characters with no commas, question marks (?), or asterisks (*).  Descriptors are to be case sensitive, e.g.: Rebar5 does not equal REBAR5.

- A comma delimited ASCII text file listing all descriptors used and an expanded description of their meanings.  Do not include descriptors in the list that are not used on this project.  Submit this file with the coordinate file (item 3 above).

- The original field books, signed and stamped by a Professional Land Surveyor licensed t practice in the State of Alaska, containing the survey field notes for staking and as-builting the project.

680-3.12 INSPECTION.   Provide the Inspectors access to the project site for the purpose of inspection at all times. Notify ACS and GCI, or their contract inspectors, at least forty-eight (48) hours prior to the start of this project. Notify AFS, or their contract inspectors, at least seven (7) calendar days prior to the start of this project.  The manner in which you bury the innerduct, 100 mm PVC conduit, materials and equipment used therein shall be subject to inspection and approval by the Inspectors.  The Inspectors shall measure the innerduct conduit prior to your backfilling any of the trenches. ACS, AFS and GCI will conduct a final inspection within ten (10) calendar days of your informing the Inspectors, in writing, that the ACS, AFS, and GCI innerduct, handhole or  vault system is complete.  Complete incomplete items (punch list) as noted in the final inspection report within ten (10) calendar days of the final inspection.

680-3.13 FIBER OPTIC CABLE PLACMENT.  Provide Fiber Optic Cable installation specifications consistent with the cable and innerduct manufacture’s recommendations and the current NESC and applicable Alaskan practices to AFS, or their contract inspector, ten (10) calendar days prior to placing the fiber optic cable.   AFS will test the BFO24 fiber optic cable prior to your taking possession of the cable, when the cable is placed into the innerduct system and when the remaining cable is returned.  You are responsible for any damage to the AFS, fiber optic cable, once you have taken possession and until the fiber optic cable is returned to AFS yard.

The fiber optic cable installation can be scheduled once AFS or their contract inspector has reviewed and approved the Fiber Optic Cable Placement Specifications you provide, and the AFS innerduct and handhole system has been completed and accepted.  No Fiber Optic cable shall be placed without the AFS contract inspector present to wittiness the placement operation.   Place the AFS fiber optic cable into the AFS innterduct system with the amount of slack cable as detailed on the AFS plans.

680-4.01 METHOD OF MEASUREMENT.   All surveying and staking required for the staking of the 680 Items for this project will be measured and paid for under Item 642(1), Construction Surveying.

Items 680(6), 680(6A) and 680(6B) will be measured by each complete unit completed and accepted by the Engineer.

Item 680(9) will not be measured for payment.

Items 680(10) through 680(17) will be measured by the meter, complete and accepted by the Engineer. Measurements will be made from outside of the handhole to the outside of the next handhole.

The slack fiber optic cable installed into the AFS handholes will not be measured.

680-5.01 BASIS OF PAYMENT.  All required trenching to accommodate the vault placement and duct transitions into new or existing vaults described in Subsection 680-3.06 is subsidiary to Items 680(6), 680(6B), 680(10) through 680(16).

The cost of mandrilling and installing the jet line shall be subsidiary to the applicable 100mm PVC Conduit Items.

The cost of field bending the 100mm PVC conduit shall be subsidiary to the applicable 100mm Conduit Items.

The Splicing of the innerducts will be subsidiary to the innerduct items.  If required, all over excavation as noted in Subsection 680-3.02 shall be considered subsidiary to the applicable innerduct items.

Payment for Item 680(6) shall be full compensation for furnishing and installing the ACS vaults and AFS per-cast concrete handholes as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(6) and no separate payment shall be made: Grading excavation, rock excavation, bedding, backfill, ground rods, and ground wire, knockout openings with urethane foam, buried service wire, frame and cover, carsonite signs, 100 mm x 150 mm (4”x 6”) witness posts, EMS makers, conduit sweeps and transitions into handholes or vaults and other items necessary to install complete units.

Payment for Item 680(6A) shall be full compensation for furnishing and installing the AFS handholes as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(6A) and no separate payment will be made for the them:  Grading excavation, rock excavation, bedding, backfill, ground rods and ground wire, knockout openings with urethane foam, buried service wire, frame and cover, crushed stone bedding, carsonite signs, 100 mm x 150 mm (4”x 6”) witness posts, EMS markers, conduit sweeps and transitions into handholes and other items necessary to install complete units.

Payment for item 680(6B) shall be full compensation for installing Utility furnished vaults as described in the Specifications.  In addition, labor and materials for the following are subsidiary to Item 680(6B) and no separate payment shall be made: Grading excavation, rock excavation, bedding, backfill, ground rods and ground wire, knockout openings with urethane foam, tracer wire, frame and cover, bedding, 100 mm x 150 mm (4”x 6”) witness posts, EMS markers, conduit sweeps and transitions into vaults and other items necessary to install complete units.

Payment for Item 680(9) shall be full compensation for providing all the requirements of the Specifications.

Payment for Item 680(10) shall be full compensation for furnishing and installing the HDPE innerduct as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(10) and no separate payment will be made:  Grading excavation, rock excavation, backfill, placement of bedding sand, buried service wire, geotextile fabric, innerduct splicing and marker tape, innerduct acceptance testing, innerduct spacers and any other items necessary for complete installation of this work item.  Jacking or boring in lieu of trenching shall not be a basis for extra payment.

Payment for Item 680(11) shall be full compensation for furnishing and installing two 31.75mm HDPE innerducts as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(11) and no separate payment shall be made:  Grading excavation, rock excavation, concrete encasement, backfill, placement of sand bedding, backfill, buried service wire, geotextile fabric, innerduct splicing and marker tape, innerduct acceptance testing, innerduct spacers and any other items necessary to complete the installation.

Payment for Item 680(12) shall be full compensation for installing three Utility furnished HDPE innerducts as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(12) and no separate payment shall be made: Grading excavation, rock excavation, backfill, placement of sand bedding, buried service wire, geotextile fabric, innerduct splicing, innerduct acceptance testing, innerduct spacers and marker tape, and any other items necessary to complete the installation.

Payment for Item 680(13) shall be full compensation for all labor required for installing three Utility furnished HDPE innerducts along with furnishing and installing two HDPE innerducts as described in the Specifications and Plans. In addition, labor and materials for the following are subsidiary to Item 680(13) and no separate payment shall be made: Grading excavation, rock excavation, backfill, concrete encasement, buried service wire and marker tape, innerduct splicing, innerduct acceptance testing, innerduct spacers and any other items necessary to complete the installation.

Payment for Item 680(14) shall be full compensation for all labor and materials for installing two 100mm (4”) PVC conduits into a common trench and encasing in concrete at the locations shown in the Plans.

Payment for Item 680(15) shall be full compensation for all labor required for installing two Utility furnished 100 mm (4”) PVC conduits and three Utility furnished 31.75 mm (1.25”) HDPE innerducts in addition to all labor and materials required for furnishing and installing two 31.75 mm (1.25”) HDPE innerducts inside one 100 mm (4”) PVC Conduit as described in the Specifications and Plans.  In addition, labor and materials for the following are subsidiary to Item 680(15) and no separate payment shall be made: The grading, excavation, rock excavation, concrete encasement, backfill, buried service wire, marker tape, innerduct splicing, innerduct acceptance testing, innerduct spacers and any other items necessary to complete the installation.

Payment for Item 680(16) shall be full compensation for all labor required for installing two Utility furnished 100 mm (4”) PVC conduits and three Utility furnished 31.75 mm (1.25”) HDPE innerducts. In addition, labor and materials for the following are subsidiary to Item 680(16) and no separate payment shall be made:  Grading, excavation, rock excavation, concrete encasement, backfill, buried service wire, marker tape, innerduct splicing, innerduct acceptance testing, innerduct spacers and any other items necessary to complete the installation.

Payment for Item 680(17) shall be full compensation for all labor required for installing the fiber optic cable, furnishing the Fiber Optic Cable Installation Specifications and transporting the cable from the warehouse to the jobsite and back.  The slack as detailed in the AFS plans will not be paid for directly but will be considered subsidiary to the fiber optic cable installation.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 680(6) Furnish and Install Telephone Handholes and/or Vault | Each |
| 680(6A) Furnish and Install Telephone Handhole | Each |
| 680(6B) Install Telephone Vault | Each |
| 680(9) Telephone System As-Builts | Lump Sum |
| 680(10) Furnish and Install Single Innerduct | Meter |
| 680(11) Furnish and Install Two Innerducts | Meter |
| 680(12) Install Three Innerducts | Meter |
| 680(13) Furnish Two and Install Five Innerducts | Meter |
| 680(14) Install Two Conduits | Meter |
| 680(15) Install 2 Conduits, 3 Innerducts, Furnish & Install 2 Innerducts | Meter |
| 680(16) Install 2 Conduits and 3 innerducts, Concrete Encased | Meter |
| 680(17) Install Fiber Optic Cable | Meter |

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following: Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T-53	(none)	49oC	52oC

Toughness (min)	ASTM D5801	(none)	12.4 N-m	12.4 N-m

Tenacity (min)	ASTM D5801	(none)	8.5 N-m	8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(02/28/00)R117M98

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Delete item 1. and replace with the following:

1.	Selected Material, Type A,  shall contain no muck, frozen material, roots, sod or other deleterious matter.  It shall have a plasticity index not greater than 6 as determined by AASHTO T 90.  It shall have 0-50% by weight of particles passing the 4.75 mm sieve and not more than 6% by weight of particles that pass the 0.075 mm sieve as determined by ATM T-7.

The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.  All material placed in the top 450 mm of the embankment shall have a maximum size of 75 mm.

703-2.13 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT

Coarse Aggregate (retained on the 4.75 mm sieve).  Coarse aggregate shall be free from clay balls, vegetative matter or other deleterious matter and consist of sound, tough, durable rock of uniform quality not coated with dirt or other finely divided mineral matter.  Crush stone or cobbles to such a degree that all faces are fractured and meet the following requirements:

Property				Test Method		Requirement

Percent of Wear			AASHTO T 96	30 max.

Degradation				ATM T-13		30 min.

Percent Sodium Sulfate Loss	AASHTO T 104	9   max. (5 cycles)

Percent Fracture			WAQTC TM 1

All Faces 						75 min.

Thin & Elongated Particles	ATM T-9

3 to 1							20% max.

5 to 1							5%   max.

Absorption				AASHTO T 85	2%   max.

Nordic Abrasion						12.0 max.

Fine Aggregate (passing the 4.75 mm sieve).  Consist entirely of 100 percent crushed aggregate and be non-plastic as determined by WAQTC FOP for AASHTO T 90.  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Mineral Filler.  Meet AASHTO M 17.  Use rock dust from the aggregate crushing operation or crushed limestone free of agglomerations and sufficiently dry to flow freely.

Blended Aggregate.  Blend the aggregate fractions to meet the grading requirements of Table 703-9 as determined by WAQTC FOP for AASHTO T 27/T 11.

TABLE 703-9

STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation			Requirement

19.0 mm			100

12.5 mm 			76-85

9.5 mm			 < 60

4.75 mm			20-27

2.36 mm			14-20

0.075 mm			  8-11

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET  Metric	SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

# English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

# (01/22/02)R249

SECTION 712

MISCELLANEOUS

##### Special Provisions

712-2.14 PREFORMED PAVEMENT MARKINGS. Add the following to paragraph A. under Item 1., General Requirements: The preformed ribbon shall consist of one solid piece of required width and length. In solid stripe areas, the tape length shall, where possible, be a minimum of 30 meters. (7/15/96)R79M

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

SECTION 726

TOPSOIL

#### Special Provisions

726-2.01 TOPSOIL. Replace Item No. 3 with the following:

TABLE 726-1

TOPSOIL REQUIREMENTS

| REQUIREMENT | CLASS A | CLASS B |
| --- | --- | --- |
| Sieve Designation | Percent Passing by Weight |  |
| 75 mm | - | 100 |
| 12.5 mm | 100 | - |
| 4.75 mm | 95-100 | 75-100 |
| 1.18 mm | 64-90 | 50-95 |
| .075 mm | 30-60 | 20-80 |
| Organic Content* | 10% - 40% | 5% minimum |
| Limestone | 3.4 Mg/hectare | - |

*   Determined by loss on ignition of oven dried sample in accordance with ALASKA FOP for AASHTO T 267.

(12/05/01)R139M98

SECTION 727

SOIL STABILIZATION MATERIAL

#### Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

1.	Virgin/Recycled Wood Fiber, Recycled Paper (“wood cellulose”) Mulch, or a Blend of Virgin/Recycled Wood Fiber with Recycled Paper Mulch. Blended mulch may contain up to 50% recycled paper.  The mulch shall meet the following requirements:

a.	Contains no growth or germination inhibiting factors.

b.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry.

c.	Mulch can be applied uniformly on the soil surface.

d.	Will not create a hard crust upon drying and have moisture absorption and retention properties and the ability to hold grass seed in contact with the soil.

e.	Dyed a suitable color to facilitate inspection of its placement.

Ship the mulch material in packages of uniform weight (plus or minus 5%) and bear the name of the manufacturer and the air-dry weight content.

Use a commercial tackifier on all areas steeper than 3:1.  Use the amount recommended by the manufacturer.

(08/19/99)R206M98

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT.  Under 1. Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2. Reinforcement, replace ‘Separation (high survivability)’ with: ‘Stabilization’.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL.  Under 2. Erosion control, replace ‘Meet AASHTO M 288 for Erosion Control’ with: ‘Meet AASHTO M 288 for Permanent Erosion Control’.

729-2.04 SEDIMENT CONTROL.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with: ‘Meet AASHTO M 288 for Temporary Silt Fence’.

(02/28/00)R229M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B.

Standard Modifications

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

Special Provisions

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX B

PERMITS AND

ERROSION AND SEDIMENT CONTROL PLAN

APPENDIX C

ELECTRICAL FACILITY CLEARANCE REQUIREMENTS

FOR

CONSTRUCTION OR MAINTENANCE NEAR ELECTRICAL FACILITIES

APPENDIX D

MATERIALS CERTIFICATION LIST

APPENDIX E

CUSTOM SIGN SHOP DRAWINGS