Glenn Highway Capacity 
Improvements Design Build

- Project 54694

REQUEST FOR PROPOSALS
PART II – CONTRACT REQUIREMENTS

- February 25, 2014

Alaska Department of Transportation and Public Facilities

4111 Aviation Avenue

Anchorage, AK 99502

This page intentionally left blank.

Table of Contents for Part II – Contract Requirements

Section	Page

DIVISION 100 – GENERAL PROVISIONS	1

101	DEFINITIONS AND TERMS	1

102	BIDDING REQUIREMENTS AND CONDITIONS	14

103	AWARD AND EXECUTION OF CONTRACT	17

104	SCOPE OF WORK	23

105	CONTROL OF WORK	26

106	CONTROL OF MATERIAL	38

107	LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC	49

108	PROSECUTION AND PROGRESS	57

109	MEASUREMENT AND PAYMENT	69

DIVISION 200 – EARTHWORK	74

201	CLEARING AND GRUBBING	74

202	REMOVAL OF STRUCTURES AND OBSTRUCTIONS	76

203	EXCAVATION AND EMBANKMENT	78

204	STRUCTURE EXCAVATION FOR CONDUITS AND MINOR STRUCTURES	83

205	EXCAVATION, BACKFILL, AND FOUNDATION FILL FOR MAJOR STRUCTURES	84

206	FILTER BLANKET	87

DIVISION 300 – BASES	88

301	AGGREGATE BASE AND SURFACE COURSE	88

302	SUBGRADE MODIFICATION	90

303	RECONDITIONING	91

304	SUBBASE	92

306	ASPHALT TREATED BASE COURSE	93

307	EMULSIFIED ASPHALT TREATED BASE COURSE	100

308	CRUSHED ASPHALT BASE COURSE	102

DIVISION 400 – ASPHALT PAVEMENTS  AND SURFACE TREATMENTS	103

401	HOT MIX ASPHALT AND SURFACE TREATMENTS	103

402	TACK COAT	118

403	PRIME COAT	119

404	SEAL COAT	120

405	SURFACE TREATMENT	122

406	RUMBLE STRIPS	123

408	HOT MIX ASPHALT AND SURFACE TREATMENTS TYPE V (SUPERPAVE)	126

DIVISION 500 – STRUCTURES	143

501	STRUCTURAL CONCRETE	143

502	PRESTRESSING CONCRETE	175

503	REINFORCING STEEL	181

504	STEEL STRUCTURES	183

505	PILING	195

506	TIMBER STRUCTURES	200

507	BRIDGE RAILING	203

Section	Page

508	WATERPROOFING MEMBRANE	204

509	MICROSILICA MODIFIED CONCRETE OVERLAY	206

510	REMOVAL OF CONCRETE BRIDGE DECK	213

511	MECHANICALLY STABILIZED EARTH (MSE) WALL	215

512	FORMS AND FALSEWORK	220

513	FIELD PAINTING OF STEEL STRUCTURES	229

514	CONCRETE SURFACE TREATMENTS	237

515	DRILLED SHAFTS	238

516	EXPANSION JOINTS AND BEARINGS	248

520	TEMPORARY CROSSINGS	251

DIVISION 600 – MISCELLANEOUS CONSTRUCTION	256

601	METAL FLUME DOWNDRAINS	256

602	STRUCTURAL PLATE PIPE	257

603	CULVERTS AND STORM DRAINS	258

604	MANHOLES AND INLETS	261

605	UNDERDRAINS	263

606	GUARDRAIL	264

607	FENCES	270

608	SIDEWALKS	272

609	CURBING	274

610	DITCH LINING	276

611	RIPRAP	277

614	CONCRETE BARRIER	278

615	STANDARD SIGNS	279

616	THAW PIPE AND THAW WIRES	283

618	SEEDING	288

619	SOIL STABILIZATION	291

620	TOPSOIL	295

621	PLANTING TREES AND SHRUBS	296

623	BLOCK SODDING	302

625	PIPE HAND RAIL	303

626	SANITARY SEWER SYSTEM	304

627	WATER SYSTEM	305

630	GEOTEXTILE FOR EMBANKMENT SEPARATION AND STABILIZATION	309

631	GEOTEXTILE FOR SUBSURFACE DRAINAGE AND EROSION CONTROL	311

632	PAVING FABRIC	313

633	SILT FENCE	314

634	GEOGRID SOIL REINFORCEMENT	315

635	INSULATION BOARD	316

636	GABIONS	317

639	DRIVEWAYS	318

640	MOBILIZATION AND DEMOBILIZATION	319

641	EROSION, SEDIMENT, AND POLLUTION CONTROL	320

642	CONSTRUCTION SURVEYING AND MONUMENTS	343

643	TRAFFIC MAINTENANCE	350

Section	Page

644	SERVICES TO BE FURNISHED BY THE CONTRACTOR	365

646	CPM SCHEDULING	370

660	SIGNALS AND LIGHTING	372

661	ELECTRICAL LOAD CENTERS	403

670	TRAFFIC MARKINGS	408

682	UTILITY POTHOLING	414

DIVISION 700 – MATERIALS	415

701	HYDRAULIC CEMENT AND SUPPLEMENTARY CEMENTITIOUS MATERIALS	415

702	ASPHALT MATERIALS	419

703	AGGREGATES	421

704	MASONRY UNITS	427

705	JOINT MATERIALS	428

706	CONCRETE AND PLASTIC PIPE	430

707	METAL PIPE	431

708	PAINTS	432

709	REINFORCING STEEL AND WIRE ROPE	434

710	FENCE AND GUARDRAIL	436

711	CONCRETE CURING MATERIALS  AND ADMIXTURES	438

712	MISCELLANEOUS	439

713	STRUCTURAL TIMBER, LUMBER, AND PILING	446

714	PRESERVATIVES FOR TIMBER	447

715	STEEL FOR PILES	448

716	STRUCTURAL STEEL	451

718	STEEL FORGINGS	453

719	STEEL, GRAY-IRON AND  MALLEABLE-IRON CASTINGS	454

720	ELASTOMERIC PADS	455

721	PRESTRESSING STEEL AND FITTINGS	459

722	BRIDGE RAILING	462

723	WATER STOPS	463

724	SEED	464

725	FERTILIZER	465

726	TOPSOIL	466

727	SOIL STABILIZATION MATERIAL	467

729	GEOSYNTHETICS	473

730	SIGN MATERIALS	474

740	SIGNALS AND LIGHTING MATERIALS	477

743	FUEL TANK	540

This page intentionally left blank.

- PART II CONTRACT REQUIREMENTS

# DIVISION 100 – GENERAL PROVISIONS

## SECTION 101

## DEFINITIONS AND TERMS

101-1.01 GENERAL. The following terms and definitions apply in these Specifications. If a term is not defined, the ordinary, technical, or trade meanings for that term shall apply, within the context in which it is used.

Titles and headings of sections, subsections, and subparts are intended for convenience of reference and will not govern their interpretation.

Cited publications refer to the most recent issue, including interim publications, in effect on the date of the Invitation To Bid, unless specified by year or date.

These Specifications are written to the Bidder or Contractor. Unless otherwise noted, all actions required by the specifications are to be performed by the Bidder, the Contractor, or the Contractor's agent.

Beginning in Division 200 we use imperative mood and active voice to communicate the Contractor's responsibilities in a direct and concise manner. Omission of words or phrases such as “a,” “an,” “the,” “the Contractor shall,” “unless otherwise specified,” or “unless otherwise directed” is intentional. Interpret the Contract as if they were included.

Beginning in Division 200 whenever anything is, or is to be, done, if, as, or, when, or where “acceptable, accepted, approval, approved, authorized, determined, designated, directed, disapproved, ordered, permitted, rejected, required, satisfactory, specified, submit, sufficient, suitable, suspended, unacceptable, unsatisfactory, or unsuitable,” the expression is to be interpreted as if it were followed by the words “by the Engineer” or “to the Engineer.”

101-1.02 ACRONYMS. Acronyms used in the Contract include the following (publications and plans are italicized):

AAC    	Alaska Administrative Code

AASHTO	American Association of State Highway and Transportation Officials

ACI    	American Concrete Institute

AITC    	American Institute of Timber Construction

ANSI    	American National Standards Institute

AKOSH   Alaska Occupational Safety and Health

AS    	Alaska Statute

ASDS    	Alaska Sign Design Specifications

ASME    	American Society of Mechanical Engineers

ASTM    	American Society for Testing & Materials

ATM    	Alaska Test Method (see Alaska Test Methods Manual)

ATSSA    American Traffic Safety Services Association

AWPA    	American Wood Preservers Association

AWG    	American Wire Gage

AWS    	American Welding Society

AWWA    	American Water Works Association

CFR    	Code of Federal Regulations

CRSI    	Concrete Reinforcing Steel Institute

DOLWD  	Alaska Department of Labor and Workforce Development

DOT&PF	Alaska Department of Transportation and Public Facilities

EEI    	Edison Electrical Institute

EIA    	Electronic Industries Association

FHWA    	Federal Highway Administration

FOP    	Field Operating Procedure (see Alaska Test Methods Manual)

FSS    	Federal Specifications and Standards, General Services Administration

IMSA    	International Municipal Signal Association

ICEA    	Insulated Cable Engineers Association

ITE    	Institute of Transportation Engineers

MRP    	Mining and Reclamation Plan

MUTCD   Manual on Uniform Traffic Control Devices

NEC    	National Electrical Code

NESC    	National Electrical Safety Code

NEMA    	National Electrical Manufacturers Association

SAE    	Society of Automotive Engineers

SSHC    	DOT&PF Standard Specifications for Highway Construction

SSPC    	Steel Structures Painting Council

SWPPP   Storm Water Pollution Prevention Plan

UL    	Underwriters Laboratory

WAQTC   Western Alliance for Quality in Transportation Construction (see ATM Manual)

101-1.03 DEFINITIONS.

ACCEPTANCE. The Contracting Agency’s action in accepting the Work as conforming to the Contract requirements.

ACCEPTANCE TESTING or TESTING FOR ACCEPTANCE. An activity that is carried out by the IQF and consists of a series of material tests of the work in accordance with the Specifications, the materials testing frequency schedule, and the Construction Quality Management Plan. Passing tests will be used to document Project compliance with the Specifications. Failing tests will be cause for rework to achieve a passing test result in accordance with the Construction Quality Management Plan.

ALASKA BIDDER. A Proposer who is eligible for a 5 percent preference in procurement scoring of the Price Proposal according to AAC 12.260(d) and meets the requirements of AS 36.30.170(b).

ALASKA DEPARTMENT OF TRANSPORTATION AND PUBLIC FACILITIES (DOT&PF). The Contracting Agency, also referred to as the Department.

ALASKA OFFEROR. A Proposer who is eligible for a 10 percent preference in procurement scoring of the Technical Proposal according to AAC 12.260(e) and meets the requirements of AS 36.30.170(b).

ALTERNATIVE TECHNICAL CONCEPT (ATC). A technical solution proposed by a Prequalified Proposer during the RFP phase of the Selection Process. An ATC is any proposed change to the Conceptual Design Plan and/or requirements which provides the same or better level of service, quality, and value as the Conceptual Design Plan. ATCs are proposed by the Prequalified Proposers in a pre-Proposal acceptance process, as required in the Instruction to Proposers, during the RFP phase of the Selection Process. The Contracting Agency reserves the sole right to accept and approve or reject a pre-Proposal submittal of an ATC for inclusion with a Proposer’s Proposal. The Design-Builder shall be responsible for all costs associated with the investigation, preparation, submittal, and final implementation of an ATC; this includes but is not limited to design, changes to environmental documents, environmental compliance, and permitting, utilities relocation, ROW acquisition, construction, and warranty.

ADDENDA. Clarifications, corrections, or changes to the Plans, Specifications, or other Contract documents issued graphically or in writing by the Department after the advertisement but prior to bid opening.

ADVERTISEMENT. The public announcement, as required by law, inviting bids for specified work or materials.

AGREED PRICE. An amount negotiated between the Department and the Contractor after Contract award for additional work performed or additional materials supplied under the Contract.

ALASKA TEST METHODS MANUAL. The materials testing manual used by the Department.  Contains Alaska Test Methods, WAQTC Test Methods, WAQTC FOPs for AASHTO Test Methods, and Alaska Standard Practices for evaluating test results and calibrating testing equipment.

AS-BUILT PLAN. Plans that show the final configuration of the work in the field after all approvals by the Department.

AWARD. Acceptance of the successful bid by the Department. The award is effective upon execution of the Contract by the Contracting Officer.

Base Course. One or more layers of specified material placed on a subbase or subgrade to support a surface course.

BEST AND FINAL OFFER (BAFO). A revised Technical and Price Proposal, which may be requested by the Contracting Agency after submittal of the Technical and Price Proposals. The BAFO is optional at the sole discretion of the Contracting Agency.

BETTERMENT. The construction of an additional facility for a utility owner or other third party, or upgrading of a facility being relocated or rearranged for the Project, which is not attributable to construction of the Project or is made solely for the benefit of and at the election of the third party requesting the same.

- BID. Equivalent to Proposal.

- BID BOND. A type of bid guaranty.

- BIDDER. Equivalent to Proposer.

- BID DOCUMENTS. Equivalent to Proposal.

- BID GUARANTY. Equivalent to Proposal Guaranty.

BRIDGE. A structure, including supports, erected over a depression or an obstruction, such as water, highway, or railway; and having a track or passageway for carrying traffic or other moving loads and a length measured along the roadway center of more than 20 feet between undercopings of abutments or spring lines of arches or extreme ends of openings of multiple boxes. The length of a bridge structure is the overall length measured along the line of survey stationing between backs of abutment backwalls or between ends of the bridge floor.

- CALENDAR DAY. Every day shown on the calendar, beginning and ending at midnight.

CHANGE ORDER. A written order by the Department to the Contractor making changes to the Contract, within its general scope, and establishing the basis of payment and time adjustment, if any, for the work affected.

- COMPLETION DATE. The date on which all Contract work is specified to be completed.

CONCEPTUAL DESIGN PLAN (CDP). A Plan that has been developed by the Contracting Agency; is presented in the RFP; and has been used by the Contracting Agency to identify the ROW corridor, slope limits, and environmental impacts. The CDP represents the minimum acceptable requirements. Technical Proposals may modify the CDP to the extent that the modifications exceed the requirements of the CDP.

CONSTRUCTION. Physical activity by the Contractor or any Subcontractor using labor, materials or equipment within the Project, or within material sources planned for use on the Project.

CONSTRUCTION QUALITY ASSURANCE (CQA). The Independent Construction Quality Firm’s program of planned policies, procedures, detailed responsibilities, and systematic actions necessary to provide confidence that the quality management and results meet the Contract requirements related to the final construction elements; includes construction inspection, testing, and audits of the Design-Builder’s Construction Quality Management Plan.

CONSTRUCTION QUALITY CONTROL (CQC). The actions of the Design-Builder in examining, inspecting, checking, and testing in-process work to ensure conformity to Project construction requirements.

CONSTRUCTION QUALITY MANAGEMENT PLAN (CQMP). The Design-Builder’s plan, developed and executed by the IQF, for ensuring construction quality of the Project as further defined in RFP Part III, Scope of Work.

CONTRACT DOCUMENTS. The Contract, including all documents listed in Subsection 105-1.04, Coordination of Contract Documents, as well as all amendments and attachments to the foregoing and all Change Orders issued.

- CONTRACTING AGENCY. DOT&PF, also referred to as the Department.

CONTRACTING OFFICER (PROCUREMENT OFFICER). The person authorized by the Commissioner of the Department to enter into and administer the Contract on behalf of the Department. The Contracting Officer has authority to make findings, determinations, and decisions with respect to the Contract and, when necessary, to modify or terminate the Contract. The Contracting Officer and the COAR are identified in RFP Part I, Instructions to Proposers.

CONTRACTING OFFICER’S AUTHORIZED REPRESENTATIVE (COAR) – The single point of contact designated to receive communications from Prequalified Proposers during the procurement process and from the Design-Builder during execution of the Contract. The COAR is identified in the ITP but may be changed by written notice from the Contracting Agency. The COAR is the authorized representative of the Contracting Officer and is responsible for administration of the Contract.

- CONTRACTOR. Equivalent to the Design-Builder.

CONTRACT PRICE. The lump sum price shown on Form PP-1, as adjusted by Change Order(s), and price adjustments made under the terms of the Contract.

CONTINGENT SUM. A method for paying for a Contract bid item reserved by the Department for specified contingencies. The Contractor shall perform Contingent Sum work only upon the Directive of the Engineer. The basis of payment for Contingent Sum work shall be specified in the Contract or the Directive.

CONTRACT. The written agreement between the Department and the Contractor setting forth the obligations of the parties for the performance and completion of the work.

The Contract includes the Invitation To Bid, Bid Form, Standard Specifications, Standard Modifications, Special Provisions, Plans, Bid Schedule, Contract Forms, Contract Bonds, Addenda, and any Change Orders, Interim Work Authorizations, Directives, or Supplemental Agreements that are required to complete the work in an acceptable manner, all of which constitute one instrument.

CONTRACTING OFFICER (PROCUREMENT OFFICER). The person authorized by the Commissioner of the Department to enter into and administer the Contract on behalf of the Department. The Contracting Officer has authority to make findings, determinations, and decisions with respect to the Contract and, when necessary, to modify or terminate the Contract. The Contracting Officer is identified on the Invitation To Bid.

CONTRACT ITEM (PAY ITEM). A specifically described item of Contract work listed on the Bid Schedule or in a Change Order.

CONTRACTOR. The individual, firm, corporation, joint venture, or any acceptable combination of individuals and entities contracting with the Department for performance of the Contract.

CONTRACT TIME. The time allowed under the Contract, including authorized time extensions, for the completion of all work by the Contractor.  Contract time may be specified either in calendar days or by completion date.

CONTROLLING ITEM. Any feature of the work considered at the time by the Engineer: (1) essential to the orderly completion of the work and (2) a feature which, if delayed, will delay the time of completion of the Contract (such as an item of work on the critical path of a network schedule).

COST.   Amounts actually incurred by the Contractor in the performance of the Contract that are (a) actually reflected in contemporaneously maintained accounting or other financial records and (b) supported by original source documentation. Costs are to be stated in U.S. dollars.

CRITICAL PATH. Each critical path on the Project schedule that ends on a completion deadline (that is, the term shall apply only following consumption of all available float). The lowercase term “critical path” shall mean the activities and durations associated with the longest path(s) through the Project schedule.

- CULVERT. Any structure not classified as a bridge that provides an opening under the embankment.

- DAY. Calendar day unless preceded by the word “working”.

- DEPARTMENT. The State of Alaska Department of Transportation and Public Facilities.

DEPARTMENT-CAUSED DELAYS. Unavoidable delays, to the extent that they affect a Critical Path, arising solely from the following matters:

- A suspension order

Department-Directed Changes

Failure or inability of the Department to provide responses to proposed schedules, Plans, design documents, and other submittals and matters for which response by the Department is required, within the time periods indicated in the Contract Documents

Any lawsuit seeking to restrain, enjoin, challenge, or delay construction of the Project or the granting or renewal of any governmental approval of the Project, except to the extent that the lawsuit is based on improper action by the Design-Builder and except for any lawsuits for which the Design-Builder has accepted the risk under Contract

Uncovering, removing, and restoring work to the extent provided in Subsection 105-1.10, Inspection of Work

Any improper action by the Department’s designated representative with binding authority, as specified in Subsection 107-1.13, Responsibility for Damage Claims, or the Department’s improper failure to act within a reasonable time after delivery of notice by the Design-Builder to the Department requesting such action

DEPARTMENT-DIRECTED CHANGES. Any changes in the work which the Department has directed the Design-Builder to perform in accordance with Subsection 104-1.02, Changes, including changes in the Department standards applicable to the work. Direction by the Department to stop work pending provision of evidence of compliance with applicable requirements of the Contract Documents will not be considered a Department-Directed Change. Direction to modify construction means and methods will not be considered a Department-Directed Change, provided that such direction is an appropriate means of ensuring compliance with applicable requirements of the Contract Documents. The fact that a Directive was issued by the Department shall not be considered evidence that, in fact, a Department-Directed Change occurred.

DESIGN-BUILDER. The individual, firm, corporation, joint venture, or any acceptable combination of individuals and entities contracting with the Department for performance of the Contract; also referred to as the Contractor.

- DESIGN-BUILD TEAM. Equivalent to Project Team.

DESIGN QUALITY ASSURANCE (DQA). The Independent Design Quality Firm’s program of planned policies, procedures, detailed responsibilities, and systematic actions necessary to provide confidence that the quality management and results meet the Contract requirements related to the final design elements; includes calculation checking, Plan review, and audits of the Design-Builder’s Design Quality Management Plan.

DESIGN QUALITY CONTROL (DQC). The actions of the Design-Builder in examining, verifying, and checking in-process design elements and calculations to determine the correctness and accuracy of the Project design.

DESIGN QUALITY MANAGEMENT PLAN (DQMP). The Design-Builder’s plan for ensuring design quality of the Project, as further defined in RFP Part II, Scope of Work.

DIRECTIVE. A written communication to the Contractor from the Engineer enforcing or interpreting a Contract requirement or ordering commencement or suspension of an item of work already established in the Contract.

ENGINEER. The authorized representative of the Department's Contracting Officer, also referred to as the COAR.

- ENTITY. Either the Prospective Proposer or a Major Participant.

ENVIRONMENTAL CLEARANCE. A permit or other clearance that is specific to the Project and is issued by a government, State, or local authority.

ENVIRONMENTAL COMPLIANCE MANAGER (ECM). The individual who ensures that the Project is designed, constructed, and managed with the proper regard to the environmental requirements of the Project. The Design-Builder shall provide an ECM, who shall be an integral part of the Design-Builder’s Quality Program. This person shall have functions that are distinct from other management functions and shall be available on site within one hour notice. The Design-Builder shall not relieve the ECM of any of his or her duties without the express written consent of the Contracting Agency. The ECM’s primary function is to ensure incorporation of environmental commitments into the Project and to monitor, document, and report environmental compliance. This includes, but is not limited to, management, design, and construction with respect to the environmental requirements and commitments.

ENVIRONMENTAL LAWS. All governmental rules now or hereafter in effect relating to the environment or to emissions, discharges, releases, or threatened releases of hazardous substances into the environment, including into the air, surface water or groundwater, or onto land; or relating to the manufacture, processing, distribution, use, treatment, storage, disposal, transport, or handling of hazardous substances; or otherwise relating to the protection of public health, public welfare, or the natural environmental (including protection of nonhuman forms of life, land, surface water, groundwater, and air), including the statutes listed in the definition of Hazardous Substances; NEPA, as amended, 42 U.S.C. §§ 4321 et seq.; the Occupational Safety and Health Act, as amended, 29 U.S.C. §§ 651 et seq.; the Hazardous Materials Transportation Act, as amended, 49 App. U.S.C. §§ 1801; the Endangered Species Act, as amended, 16 U.S.C. §§ 1531 et seq.; the Migratory Bird Treaty Act, 16 U.S.C. §§ 703 et seq.; the Eagle Protection Act, 16 U.S.C. § 668; and applicable State statutes.

EQUIPMENT. All machinery, tools, apparatus, and supplies necessary to preserve, maintain, construct, and complete the work.

Equitable Adjustment. An increase or decrease in Contract price or time calculated according to the terms of this Contract.

ESCROW PROPOSAL DOCUMENT (EPD). The meaning set forth in Subsection 103-1.11, Escrow Proposal Documents.

EVALUATION CRITERIA RESPONSE. The narrative response that is provided in the Proposer’s Technical Proposal.

EXTRA WORK. An item of work not provided for in the Contract as awarded but found essential by the Engineer for the satisfactory completion of the Contract within its intended scope.

FINAL INSPECTION. The date when the Project construction is complete. All punch list items are complete.

FINAL WARRANTY ACCEPTANCE. The date that defines the completion of the warranty period, and the date upon which the warranty bond shall be released by the Department. Acceptance will occur as soon as the Department has determined that the Contract requirements have been met for the warranted work.

FOOTPRINT. The maximum area of ground disturbance as shown in the CDP. This Footprint may be modified at the sole cost and risk of the Design-Builder.

HIGHWAY, STREET, OR ROAD. A general term denoting a public way used by vehicles and pedestrians, including the entire area within the right-of-way.

HOLIDAYS. State of Alaska legal holidays are:

1.	New Year's Day - January 1

2.	Martin Luther King, Jr. Day - Third Monday in January

3.	Presidents' Day - Third Monday in February

4.	Seward's Day - Last Monday in March

5.	Memorial Day - Last Monday in May

6.	Independence Day - July 4

7.	Labor Day - First Monday in September

8.	Alaska Day - October 18

9.	Veteran's Day - November 11

10.	Thanksgiving Day - Fourth Thursday in November

11.	Christmas Day - December 25

12.	Every Sunday

13.	Every day designated by public proclamation by the President of the United States or the governor as a legal holiday.

If a holiday listed above falls on a Saturday, Saturday and the preceding Friday are both legal holidays for officers and employees of the state. If the holiday falls on a Sunday, except (12) above, Sunday and the following Monday are both legal holidays (See  AS 44.12).

INDEPENDENT CONSTRUCTION QUALITY FIRM (ICQF). The Entity that is responsible for developing the Construction Quality Management Program and implementing Construction Quality Control by documenting and reporting on construction quality on the Project, and is responsible for signing quality certifications of construction quality based on observations, reviews, and tests.

INDEPENDENT DESIGN QUALITY FIRM (IDQF). The Entity that is responsible for implementing the Design Quality Management Program by documenting and reporting on design quality on the Project, and is responsible for signing quality certifications of designs based on reviews, analyses, and calculations.

- INDEPENDENT QUALITY FIRM (IQF). Either the ICQF or the IDQF, as appropriate.

INSPECTOR. The ICQF's or the Contracting Agency’s representative who is authorized to make detailed inspections of Contract performance and materials.

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed.

- INVITATION TO BID. The advertisement for bids for all work or materials on which bids are required.

KEY PERSONNEL. The persons assigned to the Project, the loss of whom would, in the judgment of the Contracting Agency, likely have a significant impact on the cost, timeliness, or conformity of the work. The list of persons designated as Key Personnel appears in RFP Part I, Instructions to Proposers.

MAJOR CONTRACT ITEM. A Contract item with a total value of 5 percent or more of the Contract award amount.

MATERIALLY UNBALANCED BID.  A mathematically unbalanced bid that either (a) gives rise to a reasonable doubt that it will ultimately result in the lowest overall cost to the Department, even though it may be the lowest bid or (b) is so unbalanced as to be tantamount to allowing a significant advance payment.

- MATERIALS. Substances specified for use in the construction of the project.

MATERIALS CERTIFICATION LIST (MCL). A list of materials for which certifications must be submitted to the Engineer. The MCL will also designate electrical products requiring listing by an approved independent electrical testing laboratory. The MCL is included in the Contract documents as an appendix.

MATHEMATICALLY UNBALANCED BID.  A bid (a) where each pay item fails to carry its share of the cost of the work plus the bidder’s overhead and profit, or (b) based on nominal prices for some pay items and enhanced prices for other pay items.

- MEDIAN. The portion of a divided highway separating the traveled ways.

MINOR CONTRACT ITEM. A Contract item with a total value of less than 5 percent of the Contract award amount.

NOTICE OF INTENT TO AWARD. The written notice by the Department announcing the apparent successful bidder and establishing the Department's intent to award the Contract when all required conditions are met.

- NOTICE TO PROCEED. Written notice to the Contractor to begin the Contract work.

- ORIGINAL GROUND (OG). The ground surface prior to the start of work.

- OWNER. Equivalent to the Alaska Department of Transportation and Public Facilities.

- PATHWAY. A paved path for multiple uses.

PAVEMENT STRUCTURE. The combination of subbase, base course, and surface course placed on a subgrade to support the traffic load and distribute the traffic load to the roadbed.

PAYMENT BOND. The security furnished by the Contractor and the Contractor’s Surety to guarantee payment of all persons who supply labor and material in prosecution of the work provided for in the contract.

PERFORMANCE BOND. The security furnished by the Contractor and the Contractor’s Surety to guarantee performance and completion of the work provided for in the contract.

PLANS. Drawings, profiles, typical cross sections, Standard Drawings, working drawings, shop drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work as stated in RFP Part II, Subsection 105-1.02, Plans. When used to control the Work, the Plans shall be released for construction by the Department.

PRECONSTRUCTION CONFERENCE. A meeting between the Contractor and the Engineer to discuss the project before the Contractor begins the work.

PREQUALIFIED PROPOSER. An individual, firm, partnership, corporation, joint venture, or combination thereof that submits an SOQ Proposal and is invited to submit a Proposal in response to the RFP. The Prequalified Proposer shall propose to be the Design-Builder for the Project and shall, if its Proposal is selected, execute the Contract.

- PREVAILING TIME. The time on the Contracting Agency’s receiving clerk’s time stamp.

PRICE PROPOSAL. The firm fixed Project price developed by the Prequalified Proposer in response to the RFP and submitted with the Technical Proposal.

PROFILE. The vertical elevation of the surface of the layer at the location indicated. On a roadbed it is typically indicated at the longitudinal centerline of the top layer of pavement. On a material or fabrication it may be used to indicate a thickness of material or thickness of a coating.

- PROJECT. The Glenn Highway Capacity Improvements project.

PROJECT TEAM. The members of the Prequalified Proposer’s or Major Participant’s organizations who have been assigned roles to perform on the Project.

PROPOSAL. A Proposer’s response to the RFP in conformance with RFP Part I, Instructions to Proposers. The Proposal consists of a Technical Proposal and a Price Proposal, including properly completed Proposal forms and all required supporting documentation.

PROPOSAL GUARANTY. The security furnished with a Proposal to guarantee that the Proposer will enter into a Contract if the Contracting Agency accepts the Proposal.

PROPOSAL DEADLINE. The date and time, as listed in RFP Part I, Section 1.6, Proposal Submittal Deadline and Location, by which the Proposals must be submitted to the Contracting Agency.

PROPOSER. An individual, firm, partnership, corporation, joint venture, or combination thereof that prepares and submits a Proposal in response to the RFP. Proposers are those who were notified in writing by the Department that they are eligible to receive the RFP by virtue of the Department’s short listing of their SOQ Proposal submitted in response to the RFQ issued by the Department. The Proposer will propose to be the Design-Builder for the Project and will, if its Proposal is selected, execute the Contract.

QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.

QUALITY CHECKPOINT (QCP). A point in time when construction has proceeded to a defined stage at which representatives of the Design-Builder and the IQF, together with the Department’s oversight representative, determine the progress to date by reviewing appropriate construction documentation for the portions of the Work under review. The parties then judge whether to accept or reject the completed work. No additional work shall take place past the QCP until all parties mutually agree that the work up to that point is acceptable.

QUALITY PROGRAM. The documentation, standards, written Plans, and activities that constitute the design and construction quality efforts on the Project or comparable projects.

RELEASE FOR CONSTRUCTION PLANS. A set of Plans that describes and controls a portion of the Work, and that (a) conforms to the Contract requirements, (b) has been subjected to Quality Control the Design-Builder, (c) has been certified by the IDQF as meeting the Contract requirements and as having been subjected to the proper QA/QC checks, (d) has been duly submitted to the Contracting Agency with the required certification, and (e) has been released for construction by the Contracting Agency in a written transmittal signed by the COAR.

Resources. Labor, equipment, materials, supplies, tools, transportation, and supervision necessary to perform the work.

Responsible Bidder.  A bidder that the Department determines has the skill, ability, financial resources, legal capacity to contract, equipment, required licenses, integrity, satisfactory record of performance and that is otherwise fully capable of performing the Contract.

RESPONSIVE. Determined solely by the Department to conform in all material respects with the requirements of the RFQ and the RFP.

Responsive Bid. A bid that the Department determines conforms in all material respects with the solicitation for bids.

RETAINAGE. A percentage of a payment established in advance under a contract or subcontract to be withheld from a progress payment due on the contract or subcontract. Payment or a percentage of payment withheld for unsatisfactory performance is not retainage.

RIGHT-OF-WAY. Land or property or an interest in property available for a project.  The uses allowed in portions of right-of-way may be restricted.

ROADBED. Graded portion of a highway within top and side slopes, prepared as a foundation for the pavement structure and shoulders.

ROADSIDE. A general term denoting the area adjoining the outer edge of the roadway. Extensive areas between the roadways of a divided highway may also be considered roadside.

- ROADWAY. Portion of a highway including shoulders, for vehicular use.

SCHEDULE OF VALUES. A price breakdown of the lump sum price submitted in the Proposer’s Price Proposal prepared by Design-Builder and acceptable to Owner indicating that portion of the Contract Price to be paid for each major component of the Work.

SELECTION PROCESS. The two-step procurement process used to select a Design-Builder. The Selection Process consists of Step 1, determining the Short List, and Step 2, selecting the Design-Builder. Step 1 has been completed. Step 2 is described in RFP Part I, Section 6, Selection Process.

SHORT LIST. The list of Proposers who have been prequalified by the Department and invited to prepare a Proposal. The Department published the Short List at the end of Step 1 of the Selection Process.

SHOULDER. Portion of the roadway adjacent to the traveled way for accommodation of stopped vehicles for emergency use, and for lateral support of base and surface courses.

- SIDEWALK. Portion of the project constructed for the exclusive use of pedestrians.

SPECIAL PROVISION. Addition or revision that amends or supersedes the Standard Specifications or Standard Modifications, and is applicable to an individual project.

SPECIALTY ITEM. A Contract item identified in the Contract that requires highly specialized knowledge, abilities, or equipment not ordinarily available in the type of contracting organizations qualified and expected to bid on the contract.

SPECIFICATIONS. General term applied to all Contract terms, conditions, directions, provisions, and requirements.

STANDARD DRAWING. Drawing approved by the Department for repetitive use, showing details to be used where appropriate.

STANDARD MODIFICATION. Addition or revision that amends or supersedes the Standard Specification, and is approved by the Department for general application and repetitive use.

STANDARD SPECIFICATIONS. A book or electronic file of specifications approved by the Department for general application and repetitive use.

- STATE. The State of Alaska, acting through its authorized representative.

STATEMENT OF QUALIFICATIONS (SOQ) PROPOSAL. A Prospective Proposer’s proposal submitted in response to the RFQ in Step 1 of the Selection Process.

- STATION. A distance of 100 feet measured horizontally, usually along centerline.

STIPEND. Payment to the unsuccessful Proposers under the terms described in RFP Part II, Subsection 103-1.12, Stipend.

STRUCTURE. Bridge, culvert, catch basin, drop inlet, retaining wall, cribbing, manhole, endwall, building, sewer, service pipe, underdrain, foundation drain, or other similar feature that may be encountered in the work.

- Subbase. Layer of specified material between the subgrade and base course.

SUBCONTRACTOR. Individual or legal entity to whom or to which the Contractor sublets part of the Contract.

- SUBGRADE. The soil or embankment upon which the pavement structure is constructed.

SUBSIDIARY. Work or material not measured or paid for directly. Compensation for such work is included in the payment for other items of work.

SUBSTANTIAL COMPLETION. The point at which the project (1) can be safely and effectively used by the public without further delays, disruption, or other impediments; and (2) pavement structure, shoulder, drainage, sidewalk, permanent signing and markings, guardrail and other traffic barrier, safety appurtenance, utilities, lighting and all bridge deck and parapet work is complete.

For projects that will not be opened to the traveling public or are being built in phases, the work is substantially complete when it is ready for the subsequent project.

SUBSTRUCTURE. All portions of a bridge below the bearings of simple and continuous spans, skewbacks of arches and tops of footings of rigid frames, including backwalls, wingwalls, and wing protection railings.

- SUPERINTENDENT. The Contractor's authorized representative in responsible charge of the work.

- SUPERSTRUCTURE. The entire bridge structure above the substructure.

SUPPLEMENTAL AGREEMENT. Negotiated written agreement between the Department and the Contractor authorizing performance of work beyond the general scope of, but in conjunction with, the original Contract.  Supplemental agreements are new procurements under the State Procurement Code, AS 36.30.

SURETY. Corporation, partnership, or individual, other than the Contractor, executing a bond furnished by the Contractor.

Surface Course. Top homogenous layer of the pavement structure. It is designed to withstand the wear of traffic and the disintegrating effects of climate. Sometimes called the wearing course.

TECHNICAL PROPOSAL. A submittal that is part of the Proposer’s response to the RFP. The required format and contents of the Technical Proposal are described in RFP Part I, Section 7, Proposal Format and Contents.

TRAFFIC CONTROL PLAN (TCP). One or more project-specific plans detailing the routing of vehicular or pedestrian traffic through or around a construction area including the location of all traffic control devices.

- TRAIL. An unpaved path for multiple uses.

- TRAVELED WAY. Portion of the roadway designed for vehicle use, excluding shoulders.

UTILITY. Line, facility, or system for producing, transmitting, or distributing communications, power, electricity, light, heat, gas, oil, crude products, water, steam, waste, storm water not connected with highway drainage, or other similar commodity, including a publicly owned fire or police signal system, street lighting system, or railroad which directly or indirectly serves the public. Also means a utility company, inclusive of any subsidiary.

WARRANTY WORK. Corrective action taken to bring the warranted Work into compliance with the Contract for release of the warranty bond.

WORK. Depending on the context, (a) The act of furnishing all resources for the project and performing all duties and obligations required by the Contract or (b) the physical construction, facility or end–product that is contemplated under the Contract, whether completed or partially completed.

- WORKING DAYS. Calendar days, except Saturdays and state holidays.

WORKING DRAWINGS. Stress sheets, shop drawings, erection plans, falsework plans, framework plans, cofferdam plans, bending diagrams for reinforcing steel, wiring diagrams and schematics, traffic control plans, night work lighting plans, or any other supplementary plans or similar data which the Contractor is required to submit to the Engineer for approval.

## SECTION 102

## BIDDING REQUIREMENTS AND CONDITIONS

102-1.01 QUALIFICATION OF PROPOSERS. In order to propose on this Project prospective Proposers must have been prequalified and have been placed on a Short List by the Department in accordance with the Glenn Highway NB Capacity Improvements Request for Qualifications.

All firms desiring to participate in DOT&PF construction projects must register annually by submitting a completed Bidder Registration (Form 25D-6).

102-1.02 CONTENTS OF REQUEST FOR PROPOSALS PACKAGE. The contents of the RFP package are as stated in RFP Part I, Section 1.1, Introduction. The Standard Specifications,  permits,  forms,  reference  standards,  Standard  Drawings,  and other documents listed in the RFP are considered part of the RFP, whether included or not.

102-1.03 QUANTITIES. The quantities of Work required to produce a complete Project are not defined. The Proposer is required to make its own estimate of quantities based on the Proposer’s own investigations, interpretations, and judgments. The Contractor shall be required to furnish a complete Project in accordance with the requirements, for the lump sum Contract price regardless of the exact quantities necessary to complete the Project, and no relief or equitable adjustment will be made for any claim of increased quantities.

102-1.04 EXAMINATION OF RFP DOCUMENTS AND SITE VISIT. Proposers shall examine the work site and all Contract documents before preparing a Proposal. Submitting a Proposal is a binding representation that the Proposer has examined the work site, is aware of the conditions to be encountered, and has examined and understands all of the Contract documents.

The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a proposal bid package or made accessible to bidders or contractors, are for information purposes only. These records are not part of the Contract. These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated. They do not necessarily reflect variations in soil, rock or groundwater conditions that may exist between or outside such locations. Actual conditions may differ from what is shown in the records. Material sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements. The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project,, except as specifically provided in Subsections 106-1.02.4.b, Mandatory Sources, and 106-1.02.4.c, Designated Sources. The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor. The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Contractors shall examine Subsection 106-1.02 Material Sources for further information about material source development.

Any questions about Proposal procedures, site conditions, or Contract requirements must be submitted in writing to the COAR designated in RFP Part I, Instructions to Proposers. Questions must be submitted in sufficient time to get a reply before submission of Proposals. No oral responses or other oral statements are binding on the Department. Any response to a material question shall be issued by addendum sent to all Proposers.

102-1.05 PREPARATION OF PROPOSAL. Prepare Proposals in accordance with Part I, Instructions to Proposers, and the Contract requirements contained in the RFP.

Forms that are required to be submitted as part of the Proposal shall only be submitted on the forms furnished by the Department or legible copies of the Department's forms. All entries shall be legible and in ink or type. Proposers shall enter the lump sum price required on the Form in figures in accordance with the instructions on the Form

When a bid item contains a choice to be made by the bidder, the bidder shall indicate a choice according to the Specifications for that item. No further choice is permitted.

The necessary copies of the technical and price proposals and forms must be signed in ink by the person or persons authorized to sign the Contract for the Proposer. If a Proposer is a corporation, the bid must be signed by a corporate officer with authority to bind the corporation, or agent. If a Proposer is a partnership, a partner must sign. If the Proposer is a joint venture, each principal member must sign. If a Proposer is a sole proprietorship, the owner must sign. Each person signing the bid must initial any changes made to entries on the forms.

102-1.06 NONRESPONSIVE PROPOSALS.

- A bid shall be rejected as nonresponsive if it:

- Is not properly signed by an authorized representative of the bidder in ink and in a legally binding manner;

- Contains unauthorized additions, conditional or alternative bids, or other irregularities that make the bid incomplete, indefinite, or ambiguous;

- Includes a reservation of the right to accept or reject any award, or to enter into a contract pursuant to an award, except for an award limitation under Subsection 102-1.05;

- Fails to include an acceptable bid guaranty with the bid;

- Is materially unbalanced; or

- Fails to meet any other material requirement of the Invitation To Bid.

- A bid may be rejected as nonresponsive, in the Department's discretion, if it:

- Is not typed or completed in ink;

- Fails to include an acknowledgement of receipt of each addendum by assigned number and date of issue; or

- Is missing a bid price for any pay item, except when alternate pay items are authorized.

102-1.07 PROPOSAL GUARANTY. Proposals shall be accompanied by a Proposal guaranty in the amount specified in RFP Part I, Instructions to Proposers. The guaranty shall be unconditionally payable to the State of Alaska and shall be in the form of an acceptable Proposal Bond (Form 25D-14), or a certified check, cashier's check, or money order.

The surety of a Proposal Bond may be any corporation or partnership authorized to do business in Alaska as an insurer under AS 21.09. A legible power of attorney shall be included with each Proposal Bond.

- An individual surety will not be accepted as a proposal guaranty.

102-1.08 DELIVERY OF PROPOSALS. Delivery of Proposals shall be in accordance with RFP Part I, Instructions to Proposers.

102-1.09 WITHDRAWAL OR REVISION OF PROPOSALS. Proposers may withdraw or revise a Proposal in writing delivered by mail or by fax, in accordance with this section and with RFP Part I, Section 3, Submission, Modification, and Withdrawal of Proposals, provided that the designated office receives the withdrawal or revision prior to the Proposal submittal deadline.

- Revisions to the Technical Proposal shall be as stated in RFP Part I, Instructions to Proposers.

Revisions to the Price Proposal shall include the modification of the lump sum price but shall not reveal the amount of the total original or revised lump sum price.

102-1.10 PROTEST OF INVITATION TO BID. An interested party, as defined in AS 36.30.699, may protest an Invitation to Bid before the bid opening in accordance with AS 36.30.560 and AS 36.30.565. Submit a protest to the Contracting Officer.

102-1.11 ADDENDA REQUIREMENTS. The Department will issue addenda if it determines, in its discretion, that clarifications or changes to the Contract documents or bid opening date are needed. The Department may send addenda by any reasonable method such as mail, courier, fax, or may post the addenda on its web site. Unless picked up in person or included with the bid documents, addenda or notice that an addenda has been issued will be addressed to the individual or company to whom bidding documents were issued and sent to the address or fax number on the plan holders’ list. Notwithstanding the Department’s efforts to distribute addenda, bidders are responsible for ensuring that they have received all addenda affecting the Invitation To Bid. Bidders must acknowledge all addenda received, either on the Bid Form or by fax prior to the scheduled time of bid opening. If a bidder received no addenda, the bidder shall enter “None” on the Bid Form.

102-1.12 RECEIPT AND OPENING OF PROPOSALS. Receipt and opening of Proposals shall be in accordance with RFP Part I, Instructions to Proposers.

102-1.13 RESPONSIBILITY OF BIDDERS. The Department may find a bidder is nonresponsible for any one of the following reasons, but is not limited in its responsibility analysis to the following factors:

1.	Evidence of bid rigging or collusion;

2.	Fraud or dishonesty in the performance of previous contracts;

3.	More than one bid for the same work from an individual, firm, or corporation under the same or different name;

4.	Unsatisfactory performance on previous or current contracts;

5.	Failure to pay, or satisfactorily settle, all bills due for labor and material on previous contracts;

6.	Uncompleted work that, in the judgment of the Department, might hinder or prevent the bidder’s prompt completion of additional work, if awarded;

7.	Failure to reimburse the state for monies owed on any previous contracts;

8.	Default under previous contracts;

9.	Failure to submit evidence of registration and licensing;

10.	Failure to comply with any qualification requirements of the Department;

11.	Engaging in any activity that constitutes a cause for debarment or suspension under the State Procurement Code (AS 36.30) or submitting a bid during a period of debarment;

12.	Failure to satisfy the responsibility standards set out in state regulations;

13.	Lack of skill, ability, financial resources, or equipment required to perform the contract; or

14.	Lack of legal capacity to contract.

Nothing contained in this section deprives the Department of its discretion in determining the best value responsible bidder.

## SECTION 103

## AWARD AND EXECUTION OF CONTRACT

103-1.01 CONSIDERATION OF PROPOSALS. Consideration of Proposals will be in accordance with RFP Part I, Instructions to Proposers.

An interested party, as defined in AS 36.30.699, may protest a proposed Award of contract as per AS 36.30.560 and AS 36.30.565. Submit the protest to the Contracting Officer.

103-1.02 This section is left blank.

103-1.03 AWARD OF CONTRACT. The Department will award the Contract to the best value, responsible, and responsive Proposer in accordance with RFP Part I, Instructions to Proposers, unless it rejects all Proposals. The Department will notify all Proposers in writing of its intent to award.

The Department will notify the apparent successful Proposer in writing of its intent to award the Contract, and will request all required documents to be executed and submitted within the time specified. The apparent successful Proposer’s refusal to sign the contract and provide the requested documents within the time specified may result in cancellation of the notice of intent to award and forfeiture of the Proposal security.

If an award is made, it will be made as soon as practicable and usually within 40 days after the determination of best value. Award may be delayed due to protest or irregularities in the proposals, or if the award date is extended by mutual consent. Proposals shall be valid for 120 days after submittal, and may be extended by mutual consent.

103-1.04 RETURN OF PROPOSAL GUARANTY. Return of Proposal Guaranty shall be in accordance with RFP Part I, Instructions to Proposers.

103-1.05 PERFORMANCE AND PAYMENT BONDS.  The successful bidder shall furnish all required Performance and Payment Bonds on forms provided by the Department for the sums specified in the Contract. If no sum is specified, the successful bidder shall comply with AS 36.25.010. The Surety on each bond may be any corporation or partnership authorized to do business in the state as an insurer under AS 21.09 or two individual sureties approved by the Contracting Officer.

If individual sureties are used, two individual sureties must each provide the Department with security assets located in Alaska equal to the penal amount of each bond. Any costs incurred by the Contractor and the individual Surety are subsidiary and shall be borne by the Contractor or the individual Surety. In no event will the Department be liable for these costs.

Individual sureties shall provide security by one, or a combination, of the following methods:

1.	Escrow Account, with a federally insured financial institution, in the name of the Department. Acceptable securities include, but are not limited to, cash, treasury notes, bearer instruments having a specific value, or money market certificates.

2.  	Irrevocable letters of credit, with a financial institution approved by the Contracting Officer.

3. 	Cashier’s or certified check made payable to the State of Alaska issued by financial institutions approved by the Contracting Officer.

These bonds and security assets, as applicable, shall remain in effect for 12 months after the date of final payment or, if longer, until all obligations and liens under this Contract are satisfied, including, but not limited to, obligations under Subsection 107-1.19.

The Department may, in its discretion, notify the bonding company or Surety of any potential default or liability.

The Contractor shall substitute, within five working days, another bond or surety acceptable to the Department if an individual Surety or the Surety on any bond furnished in connection with the Contract:

- Becomes insolvent or is declared bankrupt;

- Loses its right to do business in any state affecting the work;

- Ceases to meet Contract requirements;

- Fails to furnish reports of financial condition upon request; or

- Otherwise becomes unacceptable to the Department.

When approved by the Contracting Officer, the Contractor may replace:

- An individual surety with a corporate surety; or

- Posted collateral with substitute collateral.

Failure to maintain the specified bonds or to provide substitute bonds when required under this section may be grounds for withholding contract payments until substitute bonding is obtained, and may, in the Department's discretion, be grounds for declaring the Contractor in default.

103-1.06 INSURANCE REQUIREMENTS. The Contractor shall provide evidence of insurance with an insurance carrier or carriers satisfactory to the Department covering injury to persons and property suffered by the State of Alaska or by a third party as a result of operations under this contract by the Contractor or by any subcontractor. The Contractor's insurance shall provide protection against injuries to all employees of the Contractor and the employees of any subcontractor engaged in work under this Contract. All insurance policies shall be issued by insurers that (i) are permitted to transact the business of insurance in the State of Alaska under AS 21 and (ii) have a financial rating acceptable to the Department. The Contractor shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.

Where specific limits and coverages are shown, it is understood that they shall be the minimum acceptable. The requirements of this subsection shall not limit the Contractor’s indemnity responsibility under Subsection 107-1.13. Additional insurance requirements specific to this contract are contained in the Special Provisions, when applicable.

The Contractor shall maintain the following policies of insurance with the specified minimum coverages and limits in force at all times during the performance of the Contract:

- Workers' Compensation: as required by AS 23.30.045, for all employees of the Contractor engaged in work under this Contract. The Contractor shall be responsible for Workers' Compensation Insurance for any subcontractor who performs work under this Contract. The coverage shall include:

- Waiver of subrogation against the state;

- Employer's Liability Protection at $500,000 each accident/each employee and $500,000 policy limit;

- “Other States” endorsement if the Contractor directly utilizes labor outside of the State of Alaska;

- United States Longshore and Harbor Workers’ Act Endorsement, whenever the work involves activity over or about navigable water; and

- Maritime Employer’s Liability (Jones Act) Endorsement with a minimum limit of $1,000,000, whenever the work involves activity from or on a vessel on navigable water.

- Commercial General Liability: on an occurrence policy form covering all operations with combined single limits not less than:

- $1,000,000 Each Occurrence;

- $1,000,000 Personal Injury;

- $2,000,000 General Aggregate; and

- $2,000,000 Products-Completed Operations Aggregate.

- Automobile Liability: covering all vehicles used in Contract work, with combined single limits not less than $1,000,000 each occurrence.

- Umbrella Coverage: for Contract amounts over $5,000,000 not less than $5,000,000 umbrella or excess liability. Umbrella or excess policy shall include products liability completed operations coverage and may be subject to $5,000,000 aggregate limits. Further, the umbrella or excess policy shall contain a clause stating that it takes effect (drops down) in the event the primary limits are impaired or exhausted.

5.	Insurance – Professional and Technical Errors and Omissions and/or Miscellaneous Liability:

- Provide policy coverage for all claims that the Design-Builder will become legally obligated to pay resulting from any actual or alleged negligent act, error, or omission related to the Design- Builder's professional services required under this Contract. On request, the Design-Builder must submit a financial statement that is signed by a certified public accountant and provides evidence that the Design-Builder has adequate assets to cover any deductible amount that applies to this policy.

- The Design-Builder’s professional and technical errors and omissions insurance minimum limits will be as follows:

(1)	$1,000,000 per claim

(2)	$1,000,000 annual aggregate

- Professional liability policy(s) may be provided by the individual professionals as a subcontractor to the General Contractor. Such Professional Liability policy shall provide for an aggregate limit of not less than $1,000,000. The Department shall be listed as the Certificate Holder for this policy whether provided by the Design-Builder or Subcontractor. If a project-specific policy is provided, at the conclusion of the work, and as part of the Certificate of Substantial Completion, the Design-Builder shall transmit to the Owner a certificate of insurance indicating that the policy has been prepaid for 12 months from the date of Substantial Completion.

- The State of Alaska shall be named as an additional insured on policies required by paragraphs 2 through 5 above. All of the above insurance coverages shall be considered to be primary and non-contributory to any other insurance carried by the State of Alaska, whether through self-insurance or otherwise.

In any contract or agreement with subcontractors performing work, the Contractor shall require that all indemnities and waivers of subrogation it obtains, and any stipulation to be named as an additional insured it obtains, shall also be extended to waive rights of subrogation against the State of Alaska and to add the State of Alaska as an additional named indemnitee and as an additional insured.

The apparent low bidder shall furnish evidence of insurance to the Department before award of the Contract. The evidence shall be issued to the Department and shall be either a certificate of insurance or the policy declaration page with all required endorsements attached and must:

- Denote the type, amount, and class of operations covered;

- Show the effective (and retroactive) dates of the policy;

- Show the expiration date of the policy;

- Include all required endorsements;

- Be executed by the carrier's representative; and

- If a certificate of insurance, include the following statement:

“This is to certify that the policies described herein comply with all aspects of the insurance requirements of (Project Name and Number). The insurance carrier agrees that it shall notify the Engineer, in writing, at least 30 days before cancellation of any coverage or reduction in any limits of liability.”

The Department’s acceptance of deficient evidence of insurance does not constitute a waiver of Contract requirements.

Failure to maintain the specified insurance or to provide substitute insurance if an insurance carrier becomes insolvent, is placed in receivership, declares bankruptcy, or cancels a policy may be grounds for withholding Contract payments until substitute insurance is obtained, and may, in the Department's discretion, be sufficient grounds for declaring the Contractor in default.

103-1.07 EXECUTION AND APPROVAL OF CONTRACT. The successful bidder shall execute and return the Contract Form and all other required documents to the Department within the time specified, or within 15 days after receipt by the bidder if no time is specified. A contract is awarded only after it has been signed by the Contracting Officer.

103-1.08 FAILURE TO EXECUTE CONTRACT. If the successful bidder fails to execute and return the Contract Form and other documents within time specified, as required above, the Department may cancel the intent to award and keep the Proposal Guaranty. The Department will then, in its discretion, consider the next highest scoring Proposer for Award of the Contract, cancel the Project or readvertise the Project.

103-1.09 ORAL STATEMENTS. The written terms of the Contract are binding.  No oral statement of any person shall, in any manner or degree, modify or otherwise affect, change, or amend the terms of the Contract.

103-1.10 INTEGRATED CONTRACT.  This Contract is an integrated document and contains the complete agreement and understanding of the parties. There are no unwritten agreements or understandings between the parties.  Changes ordered or agreed upon, Directives given, or Equitable Adjustments issued under this Contract, and all other matters affecting the Contract, must be in writing in order to be binding and effective.

103-1.11 ESCROW PROPOSAL DOCUMENTS. Furnish a legible copy of the Proposal documentation and an affidavit, as instructed in writing by the Contracting Officer. Proposal documentation consists of written documentation of preliminary engineering sketches and calculations, preliminary sizing of structural members or other discrete Project elements, quantity estimates and takeoffs, construction schedules on which the Proposal is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and any other information used to prepare the Proposal for the Project.

Obtain and furnish the same level of Proposal documentation, for each major participant, subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier. Seal each Entity’s documentation in separate envelopes, labeled with the Entity’s name and address, submission date, and Project name and number. Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

- Submitting Proposal Documentation. Place the Proposal documentation in a sealed container clearly marked “Escrow Proposal Documents” and labeled with the Proposer’s name and address, the submission date, and the Project name and number. Deliver the sealed container to the address indicated in RFP, Part I, Instructions to Proposers, for safekeeping.

- Affidavit.     Submit directly to the Contracts Office at the time the Escrow Documents are delivered, a signed and certified affidavit attesting that:

- the affiant has examined the Proposal documentation, and it includes all documents used to prepare the Proposal,

- the sealed container contains all Proposal documentation submitted,

- the escrow materials were relied on to prepare the Proposal, and

- should a dispute arise, the Contractor’s rights to use Proposal preparation documentation other than those in escrow are waived.

- Access and Use of Escrow Documents. The Proposal documentation will remain in escrow, without access by either party, except as otherwise provided herein. In the event the Contractor (1) provides notice of intent to claim, (2) provides a claim, (3) provides a Contract Change Order, or (4) initiates Contract-related litigation, the Department may obtain copies of the Proposal documentation as provided herein.

Both parties will submit to the depository and copy to each other a list of personnel that are authorized to access the escrow documents. Use forms provided by the depository.

Upon request, the depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents. Access to escrow documents shall require at least 5 days’ advance written notice so that the other party has the opportunity to witness the escrow review, examination, and use. There is no requirement that both parties witness the escrow document review, but if one party is absent, then the review must occur in the presence of a neutral third-party observer to be designated by the depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of escrow documentation (whether hard copy, electronic, or otherwise); to use and to provide review copies to consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute. The Department will be allowed to incorporate pertinent copies as supporting documentation in significant Contract Change Orders, contractual disputes, and the settlement of disputed claims.

- The Department is not liable for any Contractor costs associated with escrow review and use.

- Failure to Provide Proposal Documentation. Refusal or failure to provide Proposal documentation or affidavit renders the Proposal not responsive. Failure or refusal to provide subcontractor Proposal documentation will result in subcontract disapproval.

- Confidentiality of Proposal Documentation. Materials held in escrow are the Contractor’s property. Except as otherwise provided herein, the escrow materials cannot be released without the Contractor’s approval.

- Cost and Escrow Instruction. The Department pays to store escrowed materials and instructs the depository regarding escrow.

- Payment. The Contractor shall include within the overall Contract price the cost to comply with this subsection.

- Return of Escrow Documentation. The original escrow documents of unsuccessful Proposers shall be returned within 30 days of either Contract award or cancellation of the Project. The original escrow documents will be returned to the Contractor after Final Completion and after the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

103-1.12 STIPEND. Unsuccessful Proposers who submit a Proposal shall be eligible to receive a stipend in the amount of $100,000 under the following conditions:

- The Proposer has been previously prequalified for participation in the RFP for the Project by the Department.

- The Proposer submits a responsive Proposal.

- The Proposer is not selected to receive the Contract award or been issued Intent to Award.

- The Proposer agrees to allow the Department unconditional use of the ideas contained in its Proposal in connection with the Project or other future projects.

- Any protest of the terms of the RFP by the Proposer has been satisfactorily resolved.

- Any protest of the Contract award by the Proposer has been satisfactorily resolved.

- The Proposer agrees not to further protest the award of the Contract.

- The Proposer indicates its willingness to accept these terms by signing the Stipend Waiver within 30 days of receipt of such waiver from the Department.

If during preparation of the Proposals, the Project is canceled or the RFP is withdrawn, all prequalified Proposers will be eligible to receive a prorated portion of the stipend under the terms described above, which will be adjusted on a prorated basis (based on the percentage of Proposal time elapsed) to a maximum of $100,000, beginning at the date of issuance of the RFP.

No Proposer shall be entitled to reimbursement of any of its costs in connection with preparation of a response to this RFP, except as specified in this section.

By accepting the stipend, each unsuccessful Proposer agrees not to further contest the Department’s award of the Contract.

In consideration for its agreement to pay a stipend, the Department reserves the right to use any ideas or information contained in the unsuccessful Proposals in connection with any Contract awarded for the Project, or in connection with a subsequent procurement, without any obligation to pay any additional compensation to the Proposers.

The Department will transmit the Stipend Waiver to Proposers deemed eligible for the stipend, within 30 days of either Contract award, cancellation of the Project, or withdrawal of the RFP. The Department will pay the stipend or prorated portion of the stipend due within 30 days of receipt of the properly executed Stipend Waiver form.

## SECTION 104

## SCOPE OF WORK

104-1.01 INTENT OF CONTRACT. The intent of the Contract is to provide for the design, construction, and completion of every detail of the Work described and all activities necessary for satisfactory completion of the Project. The Contractor shall furnish all design, labor, material, supervision, equipment, tools, transportation, supplies, and other resources required to complete the work in the time specified and in accordance with the Contract. The Contractor is responsible for the means, methods, techniques, sequence, or procedures of construction, safety, quality control, and to perform or furnish the work in accordance with the Contract documents.

RFP Part III, Scope of Work, describes in detail the performance and prescriptive requirements for the elements required to complete the Project.

104-1.02 CHANGES.

- Within Contract Scope. The Engineer may order changes within the general scope of the Contract at any time, and without notice to sureties, including altering, ordering additions to, or ordering deletions of quantities of any item or portion of the work. These changes shall be made by a written Change Order and shall not invalidate the Contract or release the sureties.

a.	If the change does not materially differ in character or unit cost from specified Contract work, the Contractor shall perform the work at the original contract measurement methods and prices, subject to the provisions of Subsection 109-1.04.

b.	If the change is materially different in character or unit cost from that specified in the Contract, a new Contract Item will be established, and an equitable adjustment to Contract price and Contract time shall be calculated by one of the following methods:

(1)	The Engineer and Contractor agree upon an adjustment to Contract price and Contract time, and the Engineer issues a change order for the described work;

(2)	The Engineer requires the Contractor to proceed with the described work, with an adjustment to contract price and contract time, calculated by time and materials basis under Subsection 109-1.05, and the Engineer issues a change order for the work. The Contractor shall keep complete daily records of the cost of such work; or

(3)	The Engineer may issue a unilateral Change Order requiring the Contractor to proceed with the work with an adjustment to the payment amount or Contract time based on the Engineer's estimate of reasonable value. The Contractor shall keep complete daily records of the cost of such work.

c.	If the Engineer eliminates a Contract item, the Contractor shall accept compensation under Subsection 109-1.09.

- Outside Contract Scope. Changes determined to be outside the general scope of the Contract shall be made only by Supplemental Agreement issued in accordance with AS 36.30 and the State’s procurement regulations. Additional bonding or insurance may be required.

- Cost and Pricing Data. Before a Change Order or Supplemental Agreement covering work for which there is no established Contract price will be approved, the Contractor shall submit detailed cost or pricing data regarding the changed work. The cost or pricing data shall include an itemization of production rates and all costs including labor, materials, and equipment required for the work. The Contractor shall certify that the data submitted are, to the best of its knowledge and belief, accurate, complete, and current as of a mutually agreed date and that the data will continue to be accurate and complete during the performance of the changed work.

- Changes to the Proposed Design. The Technical Proposal is a part of the Contract, and the concepts contained therein shall not be materially changed unless specifically authorized by the Department. Design documents presented to the Department for approval shall modify the concepts presented in the Proposal as necessary to meet the contract requirements or correct deficiencies as determined by the Department. Plans previously approved by the Department and released for construction for any Project element shall not be modified except at the sole discretion of the Department. The Department will normally only allow such changes if there is shown to be a benefit to the Department and not for the convenience of the Contractor. No time or cost adjustment will be allowed for any design changes or field changes required to meet the Contract requirements.

104-1.03 DIFFERING SITE CONDITIONS. The Contractor shall immediately notify the Engineer in writing and specifically describe the alleged differing site condition if the Contractor discovers:

- Subsurface or latent physical conditions at the site, differing materially from those shown in the Contract documents, that could not have been discovered by a careful examination of the site; or

- Unknown physical conditions at the site, of an unusual nature, differing materially from those ordinarily encountered and generally recognized as inherent in work of the character provided for in the Contract.

Failure to give the Engineer immediate written notice of the alleged differing site condition as required under this section constitutes a waiver of any future claim arising from or relating to the alleged differing site condition.

Unless otherwise directed by the Engineer, the Contractor shall leave the affected area undisturbed and suspend work in that area until the Engineer investigates the conditions.

If the Engineer finds that such conditions differ materially and increase or decrease the cost of, or the time required for, performance of the Contract, the Engineer will prepare a Change Order for an Equitable Adjustment to the Contract. The Contractor shall cooperate with the Engineer’s preparation of the Change Order.

If the Contractor and the Engineer are unable to reach an agreement concerning the alleged differing site condition, the Contractor may file a claim under Subsection 105-1.17.

The Contractor shall keep accurate and detailed records of the actual cost of the work done as a result of the alleged differing site condition and shall allow the Engineer access to those records. Failure to keep records, to provide the Engineer with access to those records, or to give the notice required above will bar any recovery for the alleged differing site condition.

104-1.04 USE OF MATERIALS FOUND ON THE WORK. The Design-Builder may use on the Project, with the Engineer's approval, such stone, gravel, sand, or other material determined suitable by the Engineer, as may be found in the excavation. The Contractor shall not excavate or remove any material that is within the right-of-way but outside the slope and grade lines described in the Project permits without written authorization from the Engineer.

In the event the Contractor has processed material from State-furnished sources in excess of the quantities required for performance of the Contract, the Department may retain possession of the surplus processed materials, including any waste material produced as a by-product, without obligation to pay the Contractor for processing costs. When the surplus materials are in a stockpile, the Engineer may direct the Contractor to leave the materials in the stockpile, level the  stockpile(s),  or  remove  the  materials  and  restore  the  premises  to  a satisfactory condition at no additional cost to the Department.

The Contractor may temporarily use material from a structure that is designated to be removed to erect a new structure but shall not cut or otherwise damage such material without the Engineer's approval.

104-1.05 CLEANUP. The Contractor shall remove all rubbish, temporary structures, excess materials, and equipment from the project site, from state owned materials sources, and from all work areas before project completion.

104-1.06 ALTERNATIVE TECHNICAL CONCEPT PROPOSALS BY CONTRACTOR. The Contractor may propose Alternative Technical Concepts in accordance with the RFP Part I, Instructions to Proposers, prior to submission of Proposals only.

## SECTION 105

## CONTROL OF WORK

105-1.01 AUTHORITY OF THE ENGINEER. The Engineer has immediate charge of the engineering details of the project and is responsible for Contract administration. The Engineer has authority to reject defective material and suspend work being performed improperly. The Engineer has authority to accept completed work, issue Directives, issue Interim Work Authorizations, issue Change Orders, and recommend Contract payments.

The Engineer will decide all questions about the quality and acceptability of the materials furnished and the work performed by the Contractor, the Contractor’s rate of progress, Contract interpretation and all other questions relating to Contract performance.

The Engineer has authority to suspend work for reasons listed under Subsection 108-1.06. If the suspension is to protect workers or the public from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions. If the Contractor fails to take the corrective action within the specified time, the Engineer may:

- Suspend the work until it is corrected; and

- Employ others to correct the condition and deduct the cost from the Contract amount.

The Engineer may, at reasonable times, inspect any part of the plant or place of business of the Contractor or any subcontractor that is related to Contract performance, including private or commercial plants, shops, offices, or other places of business.

The Engineer may audit all books and records related to performance of the Contract, whether kept by the Contractor or a subcontractor, including cost or pricing data submitted under Subsection 104-1.02.

Whenever submittals, Plans, mix designs, samples, filings, certificates, or other notifications are indicated as to be made to the Engineer, the Contractor shall submit these items to the Engineer through the Independent Qualify Firm, which shall submit them to the Engineer as part of its program of Project compliance documentation. Time limits for review of submittals or other action begin when the Engineer has received an acceptable complete submittal from the IQF accompanied by the IQF’s statement that the submittal (or proposed activity, if appropriate) meets Contract requirements. Nothing in this statement shall be construed to weaken the authority of the Engineer, or to limit the Engineer’s ability to request and receive any requested Project documentation directly from the Contractor.

Wherever it is indicated that items are to be located, materials delivered, articles for salvage identified, waste areas or stockpiles located, location of samples determined, samples taken, test methods selected, etc. as directed, designated, or selected by the Engineer, the location and/or extent of such activity will be preliminarily designated by the IQF in writing. This information will be submitted to the Engineer and will be subject to approval or acceptance by the Engineer prior to the activity taking place. Nothing in this statement shall be construed to weaken the authority of the Engineer, or to limit the Engineer’s ability to direct the Contractor within the provisions of the Contract.

Wherever the Contractor is required to obtain the Engineer’s approval or acceptance before undertaking or proceeding with a portion of the Work, the IQF shall render his approval and/or acceptance in writing precedent to the Engineer making his determination as to whether approval is to be granted. Nothing in this statement shall be construed to weaken the authority of the Engineer, or limit his ability to request and receive any information about the Project directly from the contractor, that he so requests, nor shall this statement limit the ability of the Engineer to make his own tests or inspections of the Work.

Wherever it is indicated that the Engineer may reject Work, and for all other Project acceptance requirements, the IQF is to inspect and make a determination of the quality and conformance of the Work. If such work is determined to be defective, the IQF shall issue a nonconformance report to both the Contractor and the Engineer, and the work shall be required to be brought into conformance with the Contract (see RFP Part III, Section 16 Quality Program, for requirements). Nothing in this statement shall be construed to weaken the authority of the Engineer, or limit his ability to inspect any Work and to reject Work that does not conform to the Contract requirements.

Wherever it is indicated that the Engineer is to test or accept a portion of the Work, the IQF shall perform such tests and shall certify in writing that the Work conforms to the Contract precedent to the Engineer approving or accepting any portion of the Work. The Department retains the sole authority for acceptance of the Work. Nothing in this statement shall be construed to weaken the authority of the Engineer, or limit his ability to inspect, test and approve Work that conforms to the Contract requirements.

105-1.02 PLANS. The Contractor shall be required to develop Plans to control the work for all Project elements. The Contractor’s Plans shall show lines, grades, typical cross sections, details, location, and design of all structures as well as a summary of items included within the Schedule of Values. The Contractor‘s structure Plans shall include all details that  may  be  required to  adequately control the work, including, but not limited to, bar lists, connection details, and details showing placement of reinforcement.

The Plans shall be prepared in conformance with the Contractor’s approved Design Quality Management Plan, and shall be submitted for approval. The Contractor shall not perform work or order materials until the Plans for such Work, or for changes, are released for construction by the Engineer.

The Engineer will not release Plans for construction unless the Plans:

- conform to the Contract requirements,

- have been QC’ed by the Design-Builder,

- have been certified by the Independent Design Quality Firm as meeting the Contract Requirements and been subject to the proper quality control and quality assurance checks,

- have been duly submitted to the Contracting Agency with the required certification, and

The Contractor shall submit to the Engineer, through the IDQF, three sets of all Plans for all Project elements. The Project name and number shall be stated in the title block for all drawings, as shall the State bridge number, when applicable. The Contractor shall use D-size (22-inch by 34-inch) white paper with dark blue or black lines on all Plans. For each submittal on D-size plans the Contractor shall also submit three ½ size (11 inch by 17 inch) copies. In some instances electronic copies shall be submitted as directed by the Engineer. Where called for or when requested, the Contractor shall also furnish calculations. Calculations including computer print outs, shall be in form and format and content requested by the Engineer, and shall be submitted in triplicate on 8-1/2 inch by 11 inch paper, printed on one side.

The Contractor shall submit all Plans and working drawings to the Engineer in time to allow for review and correction before beginning the work detailed in the drawing. The Engineer will return one set of these Plans, either approved or marked with corrections to be made, and will retain the other sets. The Engineer's approval of Plans does not change the Contract requirements or release the Contractor from the responsibility for successful completion of the work.

The Contractor is responsible for the accuracy of dimensions and details and for conformity of the Plans with the Contract requirements. The Engineer may order the Contractor to comply with the Contract requirements at the Contractor's sole expense if the approved Plans or working drawings deviate from the Contract requirements.

Once the Contractor receives approval of the working drawings, the Contractor shall furnish to the Engineer through the IDQF:

- Sufficient additional copies to provide eight approved sets of prints, which shall be exact photo-replicas of the approved Plans and shall be so certified by the IDQF prior to transmittal to the Engineer;

One set of reproducible transparencies (polyester film); and

If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

The Contractor shall include in the Contract price the cost of designing the Project and furnishing all Plans.

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS. Work performed and materials furnished shall conform to the Plans and Specifications and approved Working Drawings, and be within specified tolerances. When tolerances are not specified, the Engineer will determine the limits allowed in each case.

All work or material not conforming to the Plans and Specifications is considered unacceptable unless the Engineer finds that reasonably acceptable work has been produced. In this event, the Engineer may allow non-conforming work or material to remain in place, but at a reduced price. The Engineer will document the basis of acceptance and payment by Change Order, unless the contract specifies a method to adjust the price of that item.

The failure of the Department to strictly enforce the Contract in one or more instances does not waive its right to do so in other or future instances.

105-1.04 COORDINATION OF CONTRACT DOCUMENTS. These Specifications which include the Standard Specifications and the modifications contained herein, the Plans, the RFP, the Proposal, and all supplementary documents are essential parts of the Contract. They are intended to complement each other and describe and provide for a complete Project. A requirement occurring in one is as binding as if occurring in all.

Should discrepancies appear between any of the following parts of the Contract, a listed part shall take precedence over all those listed below it:

- Change Orders

- The Design-Builder’s Proposal Documents only to the extent that they exceed the requirements of the RFP, as determined solely by the Contracting Agency (see Note below)

- Contract Requirements (RFP Part II)

- The Scope of Work (RFP Part III)

- Appendices to the RFP (Part IV)

- Standard Drawings

- Other Referenced Standards

Note: The Contractor’s Proposal shall take precedence over the RFP only to the extent that it exceeds the requirements of the RFP. (In other words, if the Proposal Documents include statements that can reasonably be interpreted as offers to provide higher-quality items than otherwise required by the Contract Documents or to perform services in addition to those otherwise required, or otherwise contains terms which are more advantageous to the Department than the requirements of the other Contract Documents, the Contractor’s obligations in the Contract shall include compliance with all such statements, offers, and terms.) The determination as to whether a portion of the Proposal exceeds the requirements of the RFP will be made at the sole discretion of the Department.

The Contractor shall not take advantage of any apparent error or omission in the Contract documents. The Contractor may not base a claim for additional compensation or Contract time on a patent error, omission, or conflict in the Contract documents. The Contractor shall notify the Engineer immediately of any apparent errors or omissions in the Contract documents. The Engineer will make any corrections or interpretations necessary to fulfill the intent of the Contract.

105-1.05 COOPERATION BY CONTRACTOR. The Contractor shall give the work the constant attention necessary for its progress, and shall cooperate fully with the Engineer, Department staff, and other contractors in every way possible.

The Contractor shall employ, as its agent, a competent superintendent thoroughly experienced in the type of work being performed and capable of reading and thoroughly understanding the Plans and Specifications. The Contractor shall ensure that the superintendent is available at all times to receive and execute Directives and other instructions from the Engineer, to supervise workers and to coordinate the work of subcontractors. The Contractor shall give the superintendent full authority to supply the resources required. The Contractor shall furnish superintendence regardless of the amount of work sublet.

105-1.06 UTILITIES.

1.	Bid Considerations. Bidders shall include in their bid the cost of:

- All utility work that is specified in the Contract as work to be performed by the Contractor;

- Working around or through all permanent and temporary utilities shown on the Plans, in both their present and adjusted positions;

- Accommodating the removal, adjustment, or relocation of utilities shown on the Plans by entities other than the Contractor;

- Construction and removal of temporary utilities, to provide temporary utility service during the construction or repair of a permanent utility; and

- Other utility work not specifically identified as compensable in Subparagraph 4 Compensation.

The Department will show the approximate locations of utilities it knows to be within the work zone on the Plans. Bidders shall expect that the location, elevation and nature of utilities may vary from what is shown on the Plans and shall factor those contingencies into the bid price. Additional utilities may exist that are not shown on the Plans. Compensation related to utilities not shown on the plans will only be available in accordance with Subparagraph 4 Compensation.

When an entity other than the Contractor is to remove, adjust, or relocate any utility, the applicable completion dates or specific calendar days to complete the removal, adjustment, or relocation may be stated in the Special Provisions. If no date is stated in the Special Provisions, the Contractor shall work cooperatively with the utility owner during the Project.

2.	Cooperation with Utility Owners. The Contractor assumes the obligation of coordinating their activities with utility owners, and shall cooperate with utility owners to facilitate removal, adjustment, or relocation operations, avoid duplication of work, and prevent unnecessary interruption of services. When a utility owner is identified in the Contract as being responsible for removing, adjusting, or relocating a utility, the Contractor shall give the utility owner 15 days advance written notice regarding the dates when the utility owner is required to begin and end operations.

The Contractor shall cooperate with utility owners to determine a utility progress schedule for all parties’ utility work. The Contractor shall submit the schedule to the Engineer before beginning that portion of utility work. The Contractor shall update the utility progress schedule monthly and shall note time delays and their cause.

Utility owners are not required to work in more than one location at a time, and shall be allowed to complete a specific section of work prior to commencing another section. Utility owners will not normally perform adjustment or relocation of underground utilities when the ground is frozen. Utility owners may prohibit the Contractor, through the Engineer, from working near utilities when the ground is frozen.

The Department has sole discretion to grant permits for utility work within the state right-of-way. The Contractor shall allow parties with utility permits to work and make excavations in the project.

If utility owners do not complete their work in a timely manner, the Engineer may direct the Contractor to temporarily relocate the utilities, to construct new utilities, or to make necessary repairs to complete the utility work.

3.	Utility Work. The Contractor shall:

- Make all necessary arrangements with utility owners to locate all utilities that may be within an area of work before excavation in that area, in accordance with AS 42.30.400;

- Provide right-of-way staking and construction staking with lines and grades before excavation in that area;

- Prevent damage to utilities or utility property within or adjacent to the project;

- Carefully uncover utilities where they intersect the work;

- Immediately stop excavating in the vicinity of a utility and notify the Engineer and the utility owner if an underground utility is discovered that was not field marked or was inaccurately field marked;

f.	Promptly notify the utility owner and the Engineer in the event of accidental interruption of utility service, and cooperate with the utility owner and the Engineer until service is restored;

- Take all precautions necessary to protect the safety of workers and the public when performing work involving utilities;

- Follow an approved traffic control plan;

- Keep the length of open trench excavation to a minimum, backfill trenches as work is completed;

- Cover open trenches with metal plates capable of bearing traffic where traffic will cross trenches;

- Maintain continuous utility service and install temporary utility systems where needed;

- Ensure all excavation conforms to AS 42.30.400 – 42.30.490;

- Ensure all excavation and utility work conforms to excavation requirements in 29 CFR 1926, Subpart P, and confined space requirements in 29 CFR 1926.21(b)(6);

- Ensure all work undertaken near energized high voltage overhead electrical lines or conductors conforms to AS 18.60.670, AS 18.60.675, AS 18.60.680 or other applicable law;

- Ensure all work undertaken near energized high voltage underground electric lines or conductors conforms to all applicable laws and safety requirements of the utility owner;

- When required by the utility owner, provide for a cable watch of overhead power, underground power, telephone, and gas;

- Obtain plan approval from the local fire authority, and provide for the continued service of fire hydrants, before working around fire hydrants;

- Do all pressure testing or camera testing required to verify utility acceptance in a timely manner; and

- Coordinate the Storm Water Pollution Prevention Plan (SWPPP) (Section 641) with their work and the utility companies’ work.

4.	Compensation.

a.	Except as otherwise specifically provided in this Subparagraph 4, no equitable adjustment will be paid by the Department:

- Due to any variations in location, elevation, and nature of utilities shown on the Plans, or the operation of removing, adjusting, or relocating them;

- For any delays, inconvenience, or damage sustained as a result of interference from utility owners, interference from utilities, or interference from the operation of removing, adjusting, or relocating utilities; or

- For any adjustments or relocations of utilities requested for the Contractor’s convenience.

- b. Except as otherwise specifically provided in this Subparagraph 4, the Engineer will issue a Change Order with equitable adjustment if:

- Utilities owned by Utility Companies not listed in RFP Part III, Section 10, Utilities, require removal, adjustment, or relocation; or

- Conflicts occur between utilities owned by Utility Companies not listed in RFP Part III, Section 10, Utilities, and other necessary work

- When the Contractor damages utilities, the utility owner may choose to repair the damage or require the Contractor to repair the damage. When the Contractor damages utilities:

(1)	No equitable adjustment will be paid by the Department, and the Contractor shall be solely responsible for repair costs and expenses, when:

(a)	The Contractor failed to obtain field locates before performing the work that resulted in the damage;

(b)	The utility was field located by the utility owner or operator, and the field locate is accurate within 24 horizontal inches if the utility is buried 10 feet deep or less, or the field locate is accurate within 30 horizontal inches if the utility is buried deeper than 10 feet;

(c)	The plan profile supplied by the utility company or the field locate does not indicate or inaccurately indicates the elevation of a buried utility;

(d)	The utility is visible in the field; or

(e)	The Contractor could otherwise reasonably have been aware of the utility.

(2)	The Engineer will issue a Change Order with an equitable adjustment for the cost of repairing damage if:

(a)	The field locate by the owner or operator of a buried utility erred by more than 24 horizontal inches if the utility is buried 10 feet deep or less, or 30 horizontal inches if the utility is buried deeper than 10 feet;

(b)	The utility is owned by a Utility Company not listed in RFP Part III, Section 10, Utilities, or other Contract documents, and the Contractor could not reasonably have been expected to be aware of the utility’s existence; or

(c)	The Contractor made a written request for a field locate in accordance with AS 42.30.400, the utility owner did not locate the utility in accordance with AS 42.30.410, and the Contractor could not reasonably have been expected to be aware of the utility’s existence or location.

- If a delay is caused by a utility owner, is beyond the control of the Contractor, and is not the result of the Contractor’s fault or negligence, the Engineer may issue a Change Order with an equitable adjustment to contract time, but no equitable adjustment will be made for the cost of delay, inconvenience or damage. Additional contract time may be granted if the cause of delay is because a utility owner is to perform utility work:

- By dates stated in the Special Provisions, and the utility work is not completed by the dates stated; or

- In cooperation with the Contractor, and the utility owner does not complete the work in a timely manner, based on a written progress schedule agreed upon by the Contractor and the utility owner.

- If the Engineer orders the Contractor to make necessary construction or repairs due to incomplete utility work by utility owners, the Contractor will be paid as specifically provided for in the Contract, or the Engineer will issue a Change Order with equitable adjustment.

- Request locates from all the utilities having facilities in the area. Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGILINE, INC. Locate Call Center Anchorage Area…………. 287-3121 Statewide 800-478-3121

Who will notify the following:

ACS

Aircraft Service International Group

Alaska Fiberstar

Alaska Native Hospital

Alaska Railroad Corp

Alyeska Cable

Anchorage School District

Anchorage Water & Wastewater

AT&T Alascom, Inc.

Chugach Electric Assoc

DOT Street Lights, State of Alaska

Enstar Natural Gas

Eyecom TV/Interior Telephone

GCI Communications

Matanuska Electric Assoc

Matanuska Telephone Assoc

MOA Street Maintenance Dept MFS

Municipality of Anchorage

Municipal Light & Power

Phillips Petroleum

PTI

Telalaska

Unocal

United Utilities

Call all other utilities and agencies directly. Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent's phone number for this project.

Utilities Relocated by Others. Utilities may be relocated by others concurrently with construction of this project.  For utilities being relocated, the Contractor will:

- include utility work on the Construction Phasing Plan and Progress Schedule;

- provide erosion, sediment, and pollution control including the stabilization of areas disturbed during utility work. Identify all utility companies performing ground disturbing activity in the Storm Water pollution Prevention Plan (SWPPP). Refer to Section 641 for further information;

- clear and grub;

- provide traffic control and flagging;

- provide Construction Surveying before utility relocation, including:

- Control for utility relocation - either ROW or Centerline staking with Station information.

- Slope staking.

- Proposed structures, not including utilities to be relocated by others.

The utility shall give the Contractor, through the Engineer, 15 calendar days advance written notice for required staking.

The Contractor shall coordinate his efforts and access with utility work taking place within the project area.

105-1.07 COOPERATION BETWEEN CONTRACTORS. The Department may, at any time, contract for and perform other or additional work on or near the Project. The Contractor shall allow other contractors reasonable access across or through the Project.

The Contractor shall cooperate with other contractors working on or near the Project, and shall conduct work without interrupting or inhibiting the work of other contractors. All contractors working on or near the Project shall accept all liability, financial or otherwise, in connection with their Contract. No claim shall be made by the Contractor or paid by the Department for any inconvenience, delay, damage or loss of any kind to the Contractor due to the presence or work of other contractors working on or near the Project.

The Contractor shall coordinate and sequence the work with other contractors working within the same project limits. The Contractor shall properly join the work with work performed by other contractors and shall perform the work in the proper sequence to that of the others. The Contractor shall arrange, place, and dispose of materials without interfering with the operations of other contractors on the same project. The Contractor shall defend, indemnify and save harmless the Department from any damages or claims caused by inconvenience, delay, or loss that the Contractor causes to other contractors.

105-1.08 SURVEY CONTROL. The Department will provide sufficient horizontal and vertical control data to establish the planned lines, grades, shapes, and structures. The Contractor shall provide all additional survey work to maintain control during the project.

105-1.09 DUTIES OF THE INSPECTOR. The Department’s inspectors are authorized to examine all work done and materials furnished, but cannot approve work or materials. Only the Engineer can approve work or materials. The inspectors can reject work or materials until any issues can be referred to and decided by the Engineer. The inspectors may not alter or waive any Contract requirements, issue instructions contrary to the Contract or act as foremen for the Contractor.

105-1.10 INSPECTION OF WORK. All materials and each part and detail of the work shall be subject to inspection by the Independent Construction Qualify Firm and the Department. The Contractor shall allow safe access to all parts of the work and shall provide information and assistance to the ICQF and the Engineer to ensure a complete and detailed inspection.

Any work done or materials used without inspection by an authorized ICQF or Department representative may be ordered removed and replaced at the Contractor's expense, unless the Department failed to inspect after being given reasonable written notice that the work was to be performed.

The Contractor shall remove and uncover portions of finished work when directed. After inspection, the Contractor shall restore the work to Contract requirements. The cost to uncover and restore work shall be at the Contractor’s expense, except the Department will pay the cost to uncover and restore work if (1) an authorized Department representative had previously inspected the work or the Contractor had provided reasonable prior written notice that the work was to be performed and (2) the Department finds the uncovered work to be acceptable. If the Department finds the uncovered work to be unacceptable, the cost to correct the work, or remove and replace the work, shall be at the Contractor's expense.

Representatives of Contract funding agencies have the right to inspect the work. This right does not make that entity a party to the Contract and does not interfere with the rights of parties to the Contract.

The Department's observations, inspections, tests and approvals shall not relieve the Contractor from properly fulfilling its Contract obligations and performing the work in accordance with the Contract. Work that has been inspected but contains latent or hidden defects shall not be deemed acceptable even though it has been inspected and found to be in accordance with the Contract.

105-1.11 REMOVAL OF UNACCEPTABLE AND UNAUTHORIZED WORK. All work that does not conform to the requirements of the Contract shall be deemed unacceptable by the Engineer, unless otherwise determined acceptable under Subsection 105–1.03. The Contractor shall correct, or remove and replace, work or material that the Engineer deems unacceptable, as ordered by the Engineer and at no additional cost to the Department.

The Contractor shall establish necessary lines and grades before performing work. Work done before necessary lines and grades are established, work done contrary to the Department's instructions, work done beyond the limits shown in the Contract, or any extra work done without authority, will be considered as unauthorized and shall not be paid for by the Department, and may be ordered removed or replaced at no additional cost to the Department.

If the Contractor fails to promptly correct, remove, or replace unacceptable or unauthorized work as ordered by the Engineer, the Engineer may employ others to remedy or remove and replace the work and will deduct the cost from the Contract payment.

105-1.12 LOAD RESTRICTIONS. The Contractor shall comply with all vehicle legal size and weight regulations of 17 AAC 25 and the Administrative Permit Manual, and shall obtain permits from the DOT&PF Division of Measurement Standards & Commercial Vehicle Enforcement before moving oversize or overweight equipment on a state highway.

The Engineer may permit oversize and overweight vehicle movements within the project limits provided the Contractor submits a written request and an acceptable Traffic Control Plan under Subsection 643-1.03. No overloads will be permitted on a pavement, base or structure that will remain in place in the completed project. The Contractor shall be responsible for all damage done by their equipment due to overloads, and for damage done by a load placed on a material that is curing and has not reached adequate strength to support the load.

The Department requires overload and oversize permits to move pre-stressed concrete girders between the Port of Anchorage or an Anchorage fabricating yard and the job site. Unless permitted by the overload permit officer, permit will be subject to the following limitations:

Maximum Single Axle Load	30,000 lb.

Maximum Tandem Axle Load 	50,000 lb.

Maximum Triple Axle Load	70,000 lb.

Maximum Four Axle Load  	90,000 lb.

Minimum Spacing of Axle Group	20 ft center to center axle groups

Minimum Spacing Within Group	3.9 ft center to center axles

Maximum Vehicle Speed on any Structure	3.0 mph

105-1.13 MAINTENANCE DURING CONSTRUCTION. The Contractor shall maintain the entire highway and related highway facilities located within the project (between the beginning of project and end of project shown on the Plans) from the date construction begins until the Contractor receives a letter of substantial completion. The Contractor shall maintain these areas continually and effectively on a daily basis, with adequate resources to keep them in satisfactory condition at all times.  The Contractor shall maintain those areas outside the project that are affected by the work, such as haul routes, detour routes, structures, material sites, and equipment storage sites during periods of their use.

The Engineer may relieve the Contractor of this maintenance responsibility for specified portions of the project:

- During a seasonal suspension of work (Subsection 643-3.07); or

- Following partial acceptance (Subsection 105-1.14).

The Department is responsible for routine snow removal and ice control only on those portions of the project that the Department accepts for maintenance and that are open for public use.

The Contractor shall maintain previously constructed work until a subsequent course, layer, or structure covers that work. The Contractor shall repair damage done to the work as described in Subsection 107-1.15.

All costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance. The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance. If the Contractor fails to take the corrective action within the specified time, the Engineer may:

1.	Suspend the work until corrective maintenance is completed;

2.	Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

3.	Employ others for corrective maintenance and deduct the cost from the Contract amount.

105-1.14 PARTIAL ACCEPTANCE. The Contractor may submit a written request for partial acceptance of a geographically separate unit of the project. The Engineer will accept the unit in writing before project completion if the Engineer inspects the unit and finds that the unit is substantially complete to Contract requirements, and acceptance is in the best interest of the State.

The Contractor may submit a written request for partial acceptance of a completed portion of the project, when the completed portion is longer than five miles. The Engineer will accept the portion in writing before project completion if the Engineer performs an inspection of the portion and finds that the portion is substantially complete to Contract requirements, and acceptance is in the best interest of the State.

Partial acceptance of the unit or portion neither voids nor alters any Contract terms.  Partial acceptance of a unit or portion of the Work does not establish a separate warranty date for that unit or portion of the Work

105-1.15 PROJECT COMPLETION. The Contractor shall notify the Engineer, in writing, upon substantial completion of all work provided for under the Contract. The Engineer will then schedule and conduct the final inspection. If the inspection discloses that any work is incomplete or unsatisfactory, the Engineer will give the Contractor a list of work items that must be completed or corrected to reach substantial completion and to reach final completion. The Contractor shall promptly complete or correct any work determined unsatisfactory by the final inspection and request a re-inspection.

The Engineer will identify the date of substantial completion in a letter of substantial completion. The letter of substantial completion will relieve the Contractor of further maintenance responsibility except as listed under Subsections 618-3.06 and 621-3.04, Period of Establishment. The letter of substantial completion will not stop Contract time or relieve the Contractor of the obligation to fully complete the work as required by the Contract specifications.

When all physical work and cleanup provided for under the Contract is found to be complete, except for work specified under RFP Part III, Warranties, a letter of Project completion will be issued by the Engineer. Project completion will relieve the Contractor from further maintenance responsibilities and will stop the count of Contract time but will not relieve the Contractor of any other obligations under the Contract.

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION. The Department will issue the letter of Final Acceptance after all of the following:

- Project completion;

- Receipt of all certificates, as-builts, warranties, and other required documents;

- Receipt of the Contractor's Release, with no exceptions;

- Certification of payment of payroll and revenue taxes by DOLWD and State Department of Revenue; and

- Final payment under the Contract.

Final Acceptance will release the Contractor from further Contract obligations, except those:

- Specified under Subsection 107-1.19;

- Required by law or regulation; or

- Continuing obligations established by provisions of this Contract, such as warranty, guaranty, indemnity, insurance, or bond.

The Contractor and the subcontractors shall maintain all books and records relating to performance of the Contract for three years after the date of final payment of the Contract and each subcontract.

105-1.17 CLAIMS. The Contractor shall notify the Engineer as soon as the Contractor becomes aware of any act or occurrence that may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract. The Engineer has no obligation to investigate any fact or occurrence that might form the basis of a claim or to provide any additional compensation or extension of Contract time unless the Contractor notifies the Engineer in a timely manner of all facts the Contractor believes form the basis for the claim.

If the claim or dispute is not resolved by agreement within seven days of the date the Engineer is notified by the Contractor, the Contractor shall within the next fourteen days submit an Intent to Claim in writing to the Engineer.

If the Contractor believes additional compensation or time is warranted, the Contractor shall immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred, and shall give the Engineer access to any such records and furnish the Engineer copies, if requested. Equipment costs must be based on the Contractor's internal rates for ownership, depreciation, and operating expenses and not on published rental rates.

The Contractor shall submit a written claim to the Contracting Officer within 90 days after the date the Contractor became aware of the basis of the claim or should have known of the basis of the claim, whichever is earlier. The Contracting Officer will issue written acknowledgement of the receipt of the claim.

The Contractor waives any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs or if the Claim is not filed on the date required.

- 1.	The written Claim must include all of the following:

- The act, event, or condition giving rise to the claim;

- The Contract provisions that apply to the claim and that provide for the requested relief;

- The item or items of Contract work affected and how they were affected;

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated;

- Revised progress schedules under Subsection 108–1.03; and

- A certification signed by the Contractor that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of the Contractor's knowledge and belief, and that the amount requested accurately reflects the Contract adjustment that the Contractor believes is due.

- 2.	The claim, in order to be considered, must show:

- That the Contractor suffered damages or delay;

- The damages or delay were caused by the act, event, or condition listed in the claim; and

- That the Contract entitled the Contractor for relief due to the act, event, or condition specified in the Claim.

The Department may request the Contractor to provide additional information relating to the claim at any time before issuing a decision. The Contractor shall provide the Department with the requested additional information within 30 days of receiving a request. Failure to furnish the additional information may be regarded as a waiver of the claim.

The Contracting Officer will issue a decision within 90 days of receipt of all information relating to the claim.  The time for the Contracting Officer to issue a decision may be extended in accordance with AS 36.30.620.

The Contracting Officer's decision is final and conclusive unless the Contractor delivers a notice of appeal to the Commissioner within 14 days of receipt of the decision. The Contractor shall also serve a copy of the notice of appeal on the Contracting Officer.

Appeals from a Contracting Officer’s decision shall be decided in accordance with the State Procurement Code’s appeal procedures, including AS 36.30.625, AS 36.30.627, AS 36.30.630, and AS 36.30.631.

Criminal and civil penalties authorized under AS 36.30.687 (including, but not limited to, forfeiture of all claimed amounts) may be imposed on the Contractor if the Contractor makes or uses a misrepresentation in support of a claim, or defrauds or attempts to defraud the Department at any stage of prosecuting a claim under this Contract.

## SECTION 106

## CONTROL OF MATERIAL

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS. The Contractor shall furnish all materials required to complete the work except those specified to be furnished by the Department. The Contractor shall supply materials that are new and that meet Contract requirements.

The Contractor shall notify the Engineer of proposed sources of materials at least 30 days before shipment, and shall submit to the Engineer and to the Department's State Materials Engineer a complete list of materials to be purchased from suppliers sufficiently in advance of fabrication or shipment to permit the Department to inspect the materials. The list of proposed material sources and materials to be purchased from suppliers shall be duly submitted to the Engineer in accordance with the Construction Quality Management Plan (CQMP).

The Department’s inspectors may inspect any materials, including those originating outside Alaska, at the supply source or other locations. Materials may be conditionally approved at the supply source or other location, but are subject to field inspection and may be ordered removed under Subsection 105-1.11 if they do not conform to Contract requirements. Inspectors are  authorized to reject materials that do not conform to specifications. The ICQF’s inspectors shall inspect all materials. The ICQF’s inspectors shall report their actions to the ICQF. Reports of material inspections shall be duly submitted or made available to the Engineer in accordance with the CQMP.

The Contractor shall submit to the ICQF a manufacturer’s certificate of compliance for each item listed on the Material Certification List. The Engineer may authorize the use of materials based on a manufacturer’s certificate of compliance, duly submitted by the ICQF in accordance with the CQMP (see Subsection 106-1.05). Materials incorporated into the project on the basis of a manufacturer’s certificate of compliance may be tested at any time, whether in place or not, and, if they do not conform to Contract specifications, they may be rejected and ordered removed under Subsection 105-1.11.

The Engineer may authorize the use of materials listed in the Department's Qualified Products List. Materials incorporated into the project on the basis of the Qualified Products List may be tested at any time, whether in place or not, and, if they do not conform to Contract specifications, they may be rejected and ordered removed under Subsection 105-1.11. The list of proposed products and materials to be purchased from the Approved Products List shall be duly submitted to the Engineer in accordance with the CQMP.

The Contractor may request substitution of specified materials with equivalent materials. Requests for substitution shall be submitted through the ICQF in accordance with the CQMP to the Engineer, and shall include a manufacturer's statement that certifies, for each lot delivered:

- Conformance to the specified performance, testing, quality or dimensional requirements; and

- Suitability for the use intended in the Contract work.

The Engineer will determine the acceptability of a proposed substitute for use in the project. If a substitute is approved, a Change Order will be executed. The Department is never required to accept substitution. The Contractor shall not incorporate substitute materials into the project without written approval from the Engineer. The Engineer may test substitute materials at any time, whether in place or not, and, if the substitute materials do not meet Contract specifications, they may be rejected and ordered removed under Subsection 105-1.11.

Pursuant to AS 36.15.050 and AS 36.30.322, agricultural/wood products harvested in Alaska shall be used in state funded projects whenever they are priced no more than seven percent above agricultural/wood products harvested outside the state and are of a like quality as compared with agricultural/wood products harvested outside the state.

Maintain records that establish the type and extent of agricultural/wood products utilized. When such products are not utilized, document the efforts he made towards obtaining agricultural/wood products harvested in Alaska and include in this documentation a written statement that he contacted the manufacturers and suppliers identified on the Department of Commerce and Economic Development's list of suppliers of Alaska forest products concerning the availability of agricultural/wood products harvested in Alaska and, if available, the product prices. Complete this documentation at a time determined by the Contracting Officer.

The Contractor's use of agricultural/wood products that fail to meet the requirements of this subsection shall be removed and replaced according to the last paragraph of Subsection 105-1.03, Conformity With Plans and Specifications.

106-1.02 MATERIAL SOURCES.

1.	General. The Contractor shall:

- Utilize Useable Excavation according to Subsection 104-1.04 before using material sources listed in Subsection 106-1.02.4. When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract;

- Produce a sufficient quantity of materials meeting the specifications to complete the project;

- As a subsidiary cost: clear and grub, strip, drill and blast, excavate, crush, sort, blend, screen, wash, stockpile, haul, and rehandle material as needed to produce and deliver the specified product;

- Determine the type of equipment and methods to be used;

- Expect variations in material quality within the deposits, and procure material only from acceptable portions of the deposit, regardless of source ownership; and

- Prevent erosion, sedimentation, and pollution within a materials source.

The Contractor agrees that:

- The costs to explore and develop material sources, including all production effort, are subsidiary to the cost of providing the specified material;

- The Engineer may order the Contractor to procure material only from certain portions of the source and may reject material from other portions of the source that does not conform to the specifications; and.

- All material required may not be procurable from any one source and the Contractor may need to change between sources. That contingency is to be factored into the unit bid price for the Contract Item.

2.	Inspection and Acceptance.  The Contractor shall perform sampling and testing during materials processing and placement in accordance with its Quality Control Plan (Subsection 106-1.03, Testing and Acceptance) and shall obtain acceptable material samples from locations designated within the source.

The ICQF will sample and test materials to determine the quality of the source, at its expense, as part of its Acceptance Testing (106-1.03.2). The Department will reject materials when the samples do not meet specifications. The Department may reject a proposed materials site when samples do not meet specifications.

3.	Awareness Training.  The operator of the Contractor's sand and gravel surface mine or other similar materials source shall provide Site-Specific Hazard Awareness Training in compliance with 30 CFR 46.11 for all the Engineer’s personnel before beginning operations. All other workers shall be given training in compliance with 30 CFR 46 before exposure to mine hazards. The training must be offered at each surface mine that will be used to supply processed aggregates. A qualified person must provide the training.  The training shall be in accordance with the operator’s written training plan approved by the Mine Safety and Health Administration, covering the following items:

- Site-specific health and safety risks;

- Recognition and avoidance of hazards;

- Restricted areas;

- Warning and evacuation signals;

- Evacuation and emergency procedures;

- Other special safety procedures; and

- A site tour.

The Contractor shall require the Engineer’s personnel to sign the Visitor’s Log Book upon completion of the training to indicate that training was provided. Training is a subsidiary cost.

4.	Type of Sources. The Contractor shall utilize Useable Excavation according to Subsection 104-1.04 before using material sources listed in this Subsection. When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

a.	Contractor-Furnished Sources. For a material source that is a commercial plant as defined in Subsection 108-1.01.3.a the Contractor shall:

(1)	Acquire the necessary rights and permits to obtain material from a commercial plant;

(2)	Pay as subsidiary costs all related costs to obtain and use material from the source; and

(3)	Be solely responsible for the quality and quantity of materials.

For all Contractor-Furnished sources that are not a commercial plant, the Contractor shall:

- Acquire the necessary rights and permits to take materials from the sources including state-owned sources that are not under the Department’s control;

- Pay as subsidiary costs all related costs to obtain, develop, and use the sources, including but not limited to permit costs and mineral royalties;

- Be solely responsible for quality and quantity of materials; and

- Obtain all necessary rights, permits, and plan approvals before clearing or disturbing the ground in the material source.

No equitable adjustment or other compensation will be made for any additional costs, including increased length of haul, if the Contractor:

- Chooses to change material sources for any reason;

- Is unable to produce a sufficient quantity or quality of materials from Contractor-Furnished sources; or

- Encounters unexpected, unforeseen, or unusual conditions within Contractor-Furnished sources.

b.	Mandatory Sources. The Department may identify material sources in the Contract from which the Contractor is required to take a specified quantity of material. No other source will be permitted for that portion of material unless prior approval is obtained from the Engineer. The Contract will specifically define these sources as Mandatory Sources and define rights and stipulations for each site. The Department will provide a materials report that estimates quality and quantity of material for these sources.

The Contractor acknowledges that samples from within a source may not be representative of the entire source. The Contractor must expect variations of quality and quantity within the source and shall factor that contingency into the unit bid price for the material. No equitable adjustment will be paid for variations encountered within the source.

If it is subsequently found that the quality or quantity of material producible from a Mandatory Source is not as represented by the materials report, and a change of source is necessary for that reason alone, a Change Order with equitable adjustment will be made.

c.	Designated Sources. The Department may identify material sources in the Contract which are available to the Contractor but which the Contractor is not required to use. The Contract will specifically define these sources as Designated Sources and define rights and stipulations for each site. The Department will provide a materials report that estimates quality and quantity of material for these sources.

The Contractor acknowledges that samples from within a source may not be representative of the entire source. The Contractor must expect variations of quality and quantity within the source and shall factor that contingency into the unit bid price for the material. No equitable adjustment will be paid for variations encountered within the source.

If the Contractor elects to use a Designated Source, and it is subsequently found that the quality and quantity of material producible from that source is not as represented by the materials report, and a change of source is necessary for that reason alone, a Change Order with equitable adjustment will be made. If the Contractor chooses to change between or among sources for any other reason than quantity or quality of material, no equitable adjustment will be paid.

d.	Available Sources. The Department may identify other material sources that are available for use for the project by the Contractor. The Contract will specifically define these sources as Available Sources. The Department makes no guarantee as to quality or quantity of material in Available Sources. The Contractor is responsible for determining the quality and quantity of material, and if additional sources are needed. The Contractor shall be responsible for identifying the rights and stipulations for each site with the owner of the site.

When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for any assumptions the Contractor makes based on this data, and for exploring all Available Sources to the Contractors satisfaction.

The Department makes no representation, guarantees, or warranty whatsoever, expressed or implied, as to:

- The quality or quantity of materials producible from an Available Source, even if such information is indicated in a Materials Report or Soils Investigation Report;

- Whether boring logs, test results or data reliably represent current existing subsurface conditions;

- Whether interpretations of the boring logs, test results, or other data are correct;

- Whether moisture conditions and indicated water tables vary from those found at the time borings were made;

- Whether the ground at the location of the borings was physically disturbed or altered after the boring was made; and

- The condition, materials, or proportions of the materials between borings, regardless of any subsurface information the Department may make available.

The availability of subsurface information from the Department shall not relieve the Contractor from any risks, or of any duty to make on-site examinations and investigations, or of any other responsibility under the Contract or as may be required by law.

No equitable adjustment will be made if the quality and quantity of material available from an Available Source is not as represented in any information provided by the Department, nor if a change of source is necessary for any other reason whatsoever. The use of Available Sources is entirely at the Contractor's option and the Contractor bears all risk associated with their decision to use an Available Source.

e.	Excluded Material Sources. Some material sources may not be considered acceptable regardless of location or ownership. The bid documents may identify some material sources excluded from use. The Department reserves the right to exclude any material source or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.

5.	Rights, Permits and Plan Approvals for Material Sources. Before disturbing the site of a material source, the Contractor shall acquire and pay for all necessary rights, permits and plan approvals indicated in this Subsection and in Subsection 107-1.02. For each material site the Contractor shall:

a.	Acquire approval for a Mining and Reclamation Plan (MRP) or receive an exemption, in accordance with AS 27.19. The MRP shall include:

- Plan and cross-sectional views of the site;

- Applicable boundaries or property lines;

- Areas and depths to be developed;

- Locations of access roads, stripping, sorting, and waste piles, crushing and plant sites, stockpile sites, drainage features, erosion and pollution control features; and

- Condition the Contractor will leave the site after the materials extraction is completed, including reseeding.

- Submit a SWPPP as required by Section 641.

After completing work in a materials source, the Contractor shall finish and grade work areas to a neat, acceptable condition in accordance with the approved MRP. Reclamation of a Contractor-furnished source will be in accord with the Contractor's MRP.

106-1.03 TESTING AND ACCEPTANCE. Materials are subject to inspection and testing by the Department at any time before, during, or after they are incorporated into the project. Use of untested materials is at the Contractor's risk. The Contractor shall remove and replace unacceptable material according to Subsection 105-1.11.

1.	QUALITY CONTROL. The Contractor is responsible for the quality of construction and materials used in the work. Quality control is process control, and includes all activities that ensure that a product meets Contract specifications. Quality control is subsidiary to the applicable items. The Contractor shall perform quality control as follows:

a.	Submit a Quality Control Plan no less than five working days before the preconstruction conference. Include, for each item being produced, the methods to be used for sampling and testing, the proposed testing frequency, personnel qualifications, and equipment descriptions. Include the use of control charts, chart update frequency, chart posting location, and criteria for corrective action.  The Quality Control Plan will become part of the CQMP.

b.	Sample materials during manufacturing or processing and perform quality control tests, as needed, to ensure materials produced conform to the Contract Specifications. Document quality control tests and make them available to the Engineer on a daily basis.

c.	Sample and test according to test methods required in the Specifications.

2.	ACCEPTANCE TESTING. The Department has the exclusive right and responsibility for determining the acceptability of the design, construction, and incorporated materials. The Contractor shall provide and pay for the services of an ICQF and an IDQF, as required by RFP Part III, Section 16, Quality Program. The ICQF is responsible to conduct Acceptance Testing using Department procedures, practices, and approved test methods, in accordance with the CQMP.

The Contractor shall not rely on the Acceptance Testing for its Quality Control. The Acceptance Testing is not a substitute for the Contractor's QC. The Engineer or ICQF may retest materials that have failed the initial acceptance test, but neither is required to do so.

3.	QUALITY LEVEL ANALYSIS (QLA). The basis of payment for production lots of selected Contract items is adjusted through QLA using acceptance test results. Price adjustments are determined by using the method specified under the QLA section of the bid item specification and Tables 106-1 and 106-2. As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained. The maximum pay factor obtainable is 1.05.

QLA is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean () and by the sample standard deviation (s). Analysis of test results will be based on an Accepted Quality Level (AQL) of 95 percent and  Contractor's risk of 5 percent. AQL is the lowest percentage within the specification limits of a material that is acceptable as a process average and receives 100 percent pay. The risk is the probability that when the Contractor is producing material at exactly the AQL, the Contractor will receive less than a 1.00 pay factor.

Table 106-1 gives the Percent within Upper or Lower Specification Limits (PU or PL) for a given number of samples (n), and a given Upper or Lower Quality Index (QU or QL). For negative values of QU or QL, use absolute values of QU or QL. Then PU or PL is equal to 100 minus the table value of PU or PL.

The Upper and Lower Quality Indexes (QU and QL) are determined from the QLA section of the bid item specification.

Table 106-2 gives the Pay Factor (PF) for a given number of samples (n) and a given Quality Level. Quality Level = (PU + PL) – 100.

| PU or PL | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 |
| --- | --- | --- | --- | --- | --- |
|  | Upper or Lower Quality Index (QU or QL) |  |  |  |  |
| 100 | 1.16-50.0 | 1.48-50.0 | 1.68-50.0 | 1.81-50.0 | 1.90-50.0 |
| 99 | - | 1.45-1.47 | 1.61-1.67 | 1.71-1.80 | 1.77-1.89 |
| 98 | 1.15 | 1.42-1.44 | 1.55-1.60 | 1.63-1.70 | 1.68-1.76 |
| 97 | - | 1.39-1.41 | 1.50-1.54 | 1.56-1.62 | 1.60-1.67 |
| 96 | 1.14 | 1.36-1.38 | 1.45-1.49 | 1.50-1.55 | 1.53-1.59 |
| 95 | - | 1.33-1.35 | 1.40-1.44 | 1.44-1.49 | 1.47-1.52 |
| 94 | 1.13 | 1.30-1.32 | 1.36-1.39 | 1.39-1.43 | 1.41-1.46 |
| 93 | - | 1.27-1.29 | 1.32-1.35 | 1.34-1.38 | 1.36-1.40 |
| 92 | 1.12 | 1.24-1.26 | 1.28-1.31 | 1.30-1.33 | 1.31-1.35 |
| 91 | 1.11 | 1.21-1.23 | 1.24-1.27 | 1.25-1.29 | 1.26-1.30 |
| 90 | 1.10 | 1.18-1.20 | 1.20-1.23 | 1.21-1.24 | 1.21-1.25 |
| 89 | 1.08-1.09 | 1.15-1.17 | 1.16-1.19 | 1.17-1.20 | 1.17-1.20 |
| 88 | 1.07 | 1.12-1.14 | 1.13-1.15 | 1.13-1.16 | 1.13-1.16 |
| 87 | 1.05-1.06 | 1.09-1.11 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.04 | 1.06-1.08 | 1.06-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.02-1.03 | 1.03-1.05 | 1.02-1.05 | 1.02-1.04 | 1.01-1.04 |
| 84 | 1.01 | 1.00-1.02 | 0.99-1.01 | 0.98-1.01 | 0.98-1.00 |
| 83 | 0.98-1.00 | 0.97-0.99 | 0.96-0.98 | 0.95-0.97 | 0.94-0.97 |
| 82 | 0.97 | 0.94-0.96 | 0.92-0.95 | 0.91-0.94 | 0.91-0.93 |
| 81 | 0.94-0.96 | 0.91-0.93 | 0.89-0.91 | 0.88-0.90 | 0.87-0.90 |
| 80 | 0.92-0.93 | 0.88-0.90 | 0.86-0.88 | 0.85-0.87 | 0.84-0.86 |
| 79 | 0.90-0.91 | 0.85-0.87 | 0.83-0.85 | 0.81-0.84 | 0.81-0.83 |
| 78 | 0.88-0.89 | 0.82-0.84 | 0.79-0.82 | 0.78-0.80 | 0.77-0.80 |
| 77 | 0.85-0.87 | 0.79-0.81 | 0.76-0.78 | 0.75-0.77 | 0.74-0.76 |
| 76 | 0.83-0.84 | 0.76-0.78 | 0.73-0.75 | 0.72-0.74 | 0.71-0.73 |
| 75 | 0.80-0.82 | 0.73-0.75 | 0.70-0.72 | 0.69-0.71 | 0.68-0.70 |
| 74 | 0.77-0.79 | 0.70-0.72 | 0.67-0.69 | 0.66-0.68 | 0.65-0.67 |
| 73 | 0.75-0.76 | 0.67-0.69 | 0.64-0.66 | 0.63-0.65 | 0.62-0.64 |
| 72 | 0.72-0.74 | 0.64-0.66 | 0.61-0.63 | 0.60-0.62 | 0.59-0.61 |
| 71 | 0.69-0.71 | 0.61-0.63 | 0.58-0.60 | 0.57-0.59 | 0.56-0.58 |
| 70 | 0.66-0.68 | 0.58-0.60 | 0.55-0.57 | 0.54-0.56 | 0.53-0.55 |
| 69 | 0.63-0.65 | 0.55-0.57 | 0.52-0.54 | 0.51-0.53 | 0.50-0.52 |
| 68 | 0.60-0.62 | 0.52-0.54 | 0.48-0.51 | 0.48-0.50 | 0.47-0.49 |
| 67 | 0.57-0.59 | 0.49-0.51 | 0.46-0.47 | 0.45-0.47 | 0.45-0.46 |
| 66 | 0.53-0.56 | 0.46-0.48 | 0.44-0.45 | 0.42-0.44 | 0.42-0.44 |
| 65 | 0.50-0.52 | 0.43-0.45 | 0.41-0.43 | 0.40-0.41 | 0.39-0.41 |
| 64 | 0.47-0.49 | 0.40-0.42 | 0.38-0.40 | 0.37-0.39 | 0.36-0.38 |
| 63 | 0.44-0.46 | 0.37-0.39 | 0.35-0.37 | 0.34-0.36 | 0.33-0.35 |
| 62 | 0.40-0.43 | 0.34-0.36 | 0.32-0.34 | 0.31-0.33 | 0.31-0.32 |
| 61 | 0.37-0.39 | 0.31-0.33 | 0.29-0.31 | 0.28-0.30 | 0.28-0.30 |
| 60 | 0.33-0.36 | 0.28-0.30 | 0.26-0.28 | 0.26-0.27 | 0.25-0.27 |
| 59 | 0.30-0.32 | 0.25-0.27 | 0.24-0.25 | 0.23-0.25 | 0.22-0.24 |
| 58 | 0.26-0.29 | 0.22-0.24 | 0.21-0.23 | 0.20-0.22 | 0.20-0.21 |
| 57 | 0.23-0.25 | 0.19-0.21 | 0.18-0.20 | 0.17-0.19 | 0.17-0.19 |
| 56 | 0.19-0.22 | 0.16-0.18 | 0.15-0.17 | 0.15-0.16 | 0.14-0.16 |
| 55 | 0.15-0.18 | 0.13-0.15 | 0.12-0.14 | 0.12-0.14 | 0.12-0.13 |
| 54 | 0.12-0.14 | 0.10-0.12 | 0.09-0.11 | 0.09-0.11 | 0.09-0.11 |
| 53 | 0.08-0.11 | 0.07-0.09 | 0.07-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.05-0.07 | 0.04-0.06 | 0.04-0.06 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.04 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

| PU or PL | n = 8 | n = 9 | n = 10 to 11 | n = 12 to 14 | n = 15 to 18 |
| --- | --- | --- | --- | --- | --- |
|  | Upper or Lower Quality Index (QU or QL) |  |  |  |  |
| 100 | 1.96-50.0 | 2.01-50.0 | 2.05-50.0 | 2.10-50.0 | 2.15-50.0 |
| 99 | 1.82-1.95 | 1.85-2.00 | 1.87-2.04 | 1.92-2.09 | 1.94-2.14 |
| 98 | 1.71-1.81 | 1.73-1.84 | 1.75-1.86 | 1.78-1.91 | 1.80-1.93 |
| 97 | 1.62-1.70 | 1.64-1.72 | 1.66-1.74 | 1.68-1.77 | 1.69-1.79 |
| 96 | 1.55-1.61 | 1.56-1.63 | 1.57-1.65 | 1.59-1.67 | 1.60-1.68 |
| 95 | 1.48-1.54 | 1.49-1.55 | 1.50-1.56 | 1.51-1.58 | 1.52-1.59 |
| 94 | 1.42-1.47 | 1.43-1.48 | 1.44-1.49 | 1.45-1.50 | 1.45-1.51 |
| 93 | 1.37-1.41 | 1.37-1.42 | 1.38-1.43 | 1.38-1.44 | 1.39-1.44 |
| 92 | 1.31-1.36 | 1.32-1.36 | 1.32-1.37 | 1.33-1.37 | 1.33-1.38 |
| 91 | 1.26-1.30 | 1.27-1.31 | 1.27-1.31 | 1.27-1.32 | 1.28-1.32 |
| 90 | 1.22-1.25 | 1.22-1.26 | 1.22-1.26 | 1.22-1.26 | 1.23-1.27 |
| 89 | 1.17-1.21 | 1.17-1.21 | 1.18-1.21 | 1.18-1.21 | 1.18-1.22 |
| 88 | 1.13-1.16 | 1.13-1.16 | 1.13-1.17 | 1.13-1.17 | 1.13-1.17 |
| 87 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 | 1.09-1.12 |
| 86 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 | 1.05-1.08 |
| 85 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 | 1.01-1.04 |
| 84 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 | 0.97-1.00 |
| 83 | 0.94-0.96 | 0.94-0.96 | 0.93-0.96 | 0.93-0.96 | 0.93-0.96 |
| 82 | 0.90-0.93 | 0.90-0.93 | 0.90-0.92 | 0.90-0.92 | 0.89-0.92 |
| 81 | 0.87-0.89 | 0.87-0.89 | 0.86-0.89 | 0.86-0.89 | 0.86-0.88 |
| 80 | 0.83-0.86 | 0.83-0.86 | 0.83-0.85 | 0.83-0.85 | 0.82-0.85 |
| 79 | 0.80-0.82 | 0.80-0.82 | 0.80-0.82 | 0.79-0.82 | 0.79-0.81 |
| 78 | 0.77-0.79 | 0.77-0.79 | 0.76-0.79 | 0.76-0.78 | 0.76-0.78 |
| 77 | 0.74-0.76 | 0.73-0.76 | 0.73-0.75 | 0.73-0.75 | 0.72-0.75 |
| 76 | 0.71-0.73 | 0.70-0.72 | 0.70-0.72 | 0.70-0.72 | 0.69-0.71 |
| 75 | 0.67-0.70 | 0.67-0.69 | 0.67-0.69 | 0.67-0.69 | 0.66-0.68 |
| 74 | 0.64-0.66 | 0.64-0.66 | 0.64-0.66 | 0.63-0.66 | 0.63-0.65 |
| 73 | 0.61-0.63 | 0.61-0.63 | 0.61-0.63 | 0.60-0.62 | 0.60-0.62 |
| 72 | 0.58-0.60 | 0.58-0.60 | 0.58-0.60 | 0.58-0.59 | 0.57-0.59 |
| 71 | 0.56-0.57 | 0.55-0.57 | 0.55-0.57 | 0.55-0.57 | 0.54-0.56 |
| 70 | 0.53-0.55 | 0.52-0.54 | 0.52-0.54 | 0.52-0.54 | 0.51-0.53 |
| 69 | 0.50-0.52 | 0.49-0.51 | 0.49-0.51 | 0.49-0.51 | 0.49-0.50 |
| 68 | 0.47-0.49 | 0.47-0.48 | 0.46-0.48 | 0.46-0.48 | 0.46-0.48 |
| 67 | 0.44-0.46 | 0.44-0.46 | 0.44-0.45 | 0.43-0.45 | 0.43-0.45 |
| 66 | 0.41-0.43 | 0.41-0.43 | 0.41-0.43 | 0.41-0.42 | 0.40-0.42 |
| 65 | 0.39-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.40 | 0.38-0.39 |
| 64 | 0.36-0.38 | 0.36-0.37 | 0.35-0.37 | 0.35-0.37 | 0.35-0.37 |
| 63 | 0.33-0.35 | 0.33-0.35 | 0.33-0.34 | 0.32-0.34 | 0.32-0.34 |
| 62 | 0.30-0.32 | 0.30-0.32 | 0.30-0.32 | 0.30-0.31 | 0.30-0.31 |
| 61 | 0.28-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 | 0.27-0.29 |
| 60 | 0.25-0.27 | 0.25-0.26 | 0.25-0.26 | 0.24-0.26 | 0.24-0.26 |
| 59 | 0.22-0.24 | 0.22-0.24 | 0.22-0.24 | 0.22-0.23 | 0.22-0.23 |
| 58 | 0.20-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 | 0.19-0.21 |
| 57 | 0.17-0.19 | 0.17-0.18 | 0.17-0.18 | 0.17-0.18 | 0.16-0.18 |
| 56 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.16 | 0.14-0.15 |
| 55 | 0.12-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 | 0.11-0.13 |
| 54 | 0.09-0.11 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 | 0.09-0.10 |
| 53 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 | 0.06-0.08 |
| 52 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 | 0.04-0.05 |
| 51 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 | 0.01-0.03 |
| 50 | 0.00 | 0.00 | 0.00 | 0.00 | 0.00 |

- TABLE 106-2

Determination of Pay Factor (PF)

| Pay Factor | n = 3 | n = 4 | n = 5 | n = 6 | n = 7 | n = 8 | n = 9 | n = 10 to n = 11 | n = 12 to n = 14 | n = 15 to n = 18 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Quality Level (PU + PL) - 100 |  |  |  |  |  |  |  |  |  |
| 1.05 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 1.04 | 90-99 | 91-99 | 92-99 | 93-99 | 93-99 | 93-99 | 94-99 | 94-99 | 95-99 | 95-99 |
| 1.03 | 80-89 | 85-90 | 87-91 | 88-92 | 89-92 | 90-92 | 91-93 | 91-93 | 92-94 | 93-94 |
| 1.02 | 75-79 | 80-84 | 83-86 | 85-87 | 86-88 | 87-89 | 88-90 | 88-90 | 89-91 | 90-92 |
| 1.01 | 71-74 | 77-79 | 80-82 | 82-84 | 84-85 | 85-86 | 85-87 | 86-87 | 87-88 | 88-89 |
| 1.00 | 68-70 | 74-76 | 78-79 | 80-81 | 81-83 | 82-84 | 83-84 | 84-85 | 85-86 | 86-87 |
| 0.99 | 66-67 | 72-73 | 75-77 | 77-79 | 79-80 | 80-81 | 81-82 | 82-83 | 83-84 | 85 |
| 0.98 | 64-65 | 70-71 | 73-74 | 75-76 | 77-78 | 78-79 | 79-80 | 80-81 | 81-82 | 83-84 |
| 0.97 | 62-63 | 68-69 | 71-72 | 74 | 75-76 | 77 | 78 | 78-79 | 80 | 81-82 |
| 0.96 | 60-61 | 66-67 | 69-70 | 72-73 | 73-74 | 75-76 | 76-77 | 77 | 78-79 | 80 |
| 0.95 | 59 | 64-65 | 68 | 70-71 | 72 | 73-74 | 74-75 | 75-76 | 77 | 78-79 |
| 0.94 | 57-58 | 63 | 66-67 | 68-69 | 70-71 | 72 | 73 | 74 | 75-76 | 77 |
| 0.93 | 56 | 61-62 | 65 | 67 | 69 | 70-71 | 71-72 | 72-73 | 74 | 75-76 |
| 0.92 | 55 | 60 | 63-64 | 65-66 | 67-68 | 69 | 70 | 71 | 72-73 | 74 |
| 0.91 | 53-54 | 58-59 | 62 | 64 | 66 | 67-68 | 68-69 | 69-70 | 71 | 73 |
| 0.90 | 52 | 57 | 60-61 | 63 | 64-65 | 66 | 67 | 68 | 70 | 71-72 |
| 0.89 | 51 | 55-56 | 59 | 61-62 | 63 | 64-65 | 66 | 67 | 68-69 | 70 |
| 0.88 | 50 | 54 | 57-58 | 60 | 62 | 63 | 64-65 | 65-66 | 67 | 69 |
| 0.87 | 48-49 | 53 | 56 | 58-59 | 60-61 | 62 | 63 | 64 | 66 | 67-68 |
| 0.86 | 47 | 51-52 | 55 | 57 | 59 | 60-61 | 62 | 63 | 64-65 | 66 |
| 0.85 | 46 | 50 | 53-54 | 56 | 58 | 59 | 60-61 | 61-62 | 63 | 65 |
| 0.84 | 45 | 49 | 52 | 55 | 56-57 | 58 | 59 | 60 | 62 | 64 |
| 0.83 | 44 | 48 | 51 | 53-54 | 55 | 57 | 58 | 59 | 61 | 63 |
| 0.82 | 42-43 | 46-47 | 50 | 52 | 54 | 55-56 | 57 | 58 | 60 | 61-62 |
| 0.81 | 41 | 45 | 48-49 | 51 | 53 | 54 | 56 | 57 | 58-59 | 60 |
| 0.80 | 40 | 44 | 47 | 50 | 52 | 53 | 54-55 | 55-56 | 57 | 59 |
| 0.79 | 38-39 | 43 | 46 | 48-49 | 50-51 | 52 | 53 | 54 | 56 | 58 |
| 0.78 | 37 | 41-42 | 45 | 47 | 49 | 51 | 52 | 53 | 55 | 57 |
| 0.77 | 36 | 40 | 43-44 | 46 | 48 | 50 | 51 | 52 | 54 | 56 |
| 0.76 | 34-35 | 39 | 42 | 45 | 47 | 48-49 | 50 | 51 | 53 | 55 |
| 0.75 | 33 | 38 | 41 | 44 | 46 | 47 | 49 | 50 | 51-52 | 53-54 |
| 0 | 0-32 | 0-37 | 0-40 | 0-43 | 0-45 | 0-46 | 0-48 | 0-49 | 0-50 | 0-52 |

106-1.04 PLANT INSPECTION. The Department may periodically inspect manufacturing methods, manufactured lots and materials at the source of production. The Department may approve, conditionally approve, or reject them.

The Contractor shall:

- Notify the Department of the production and fabrication schedule at least 30 days before beginning work on any item requiring inspection, and notify the Department 48 hours before beginning production or fabrication;

- Give the inspector full and safe access to all parts of the plant used to manufacture or produce materials; and

- Cooperate fully and assist the inspector during the inspection.

Materials may be rejected if the Department requests a plant inspection and the materials are produced or fabricated without a plant inspection. The materials may be tested at any time before final acceptance, whether in place or not, and whether approved at a plant inspection or not. If the materials do not meet Contract specifications, they may be rejected and ordered removed under Subsection 105-1.11. If rejected materials are incorporated into the project, the Department may require those materials to be removed and replaced at the Contractor's expense under Subsection 105-1.11.

106-1.05 CERTIFICATES OF COMPLIANCE. The Engineer may authorize the use of certain materials or assemblies based on a manufacturer's certificate of compliance. The certificate must state that the material or assembly fully complies with Contract requirements, include the project name and number, and be signed by the manufacturer. The certificate must accompany each lot of the materials or assemblies delivered to the project and must clearly identify the lot.

The Contractor shall submit a manufacturer's certificate of compliance, as required, for each item listed on the Materials Certification List (MCL) included in the Contract documents. The Contractor shall submit additional manufacturer’s certificates of compliance if required by the Contract or by the Engineer.

Materials or assemblies incorporated into the project on the basis of a manufacturer’s certificate of compliance may be tested at any time, whether in place or not, and, if they do not meet Contract specifications, they may be rejected and ordered removed under Subsection 105-1.11. The Engineer may refuse permission to incorporate materials or products into the project based on a manufacturer’s certificate of compliance that does not meet specifications.

106-1.06 STORAGE OF MATERIALS. Materials shall be stored to preserve their quality and fitness for the work, and so they can be readily inspected. Materials inspected before storage may be inspected again, before or after being incorporated into the project. The Contractor shall:

- Use only approved portions of the project site for storage of materials and equipment or plant operations;

- Provide any additional space needed for such purposes without extra compensation;

- Restore Department-owned or controlled storage and plant sites to their original condition without extra compensation;

- Obtain the landowner's or lessee’s written permission before storing material on private property, and furnish copies of the permission to the Engineer, if requested; and

- Restore privately owned or leased storage sites, without extra compensation from the Department, to their original condition or as agreed to between the Contractor and the private owner.

106-1.07 DEPARTMENT-FURNISHED MATERIAL. Material furnished by the Department will be made available to the Contractor at a state yard or delivered at the locations specified in the Special Provisions.

The Contractor shall include the cost of handling and placing all materials after they are delivered in the Contract price for the item in connection with which they are used. The Contractor is responsible for all material delivered to the Contractor. Deductions will be made from any monies due the Contractor to make good shortages and deficiencies from any cause whatsoever, for any damage that may occur after delivery, and for demurrage charges.

106-1.08 SUBMITTAL PROCEDURE. The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department. The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents. The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items. The Submittal Register shall list all working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items. If the number of copies of a submittal is not otherwise specified, three copies shall be required. On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet. The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department. The Contractor shall sign submittals and submit them to the Engineer. The Department will review submittals within 30 days after they are received. The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed. The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections. The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department. The Contractor shall be responsible for timely submittals. Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost.

## SECTION 107

## LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

107-1.01 LAWS TO BE OBSERVED. The Contractor shall keep fully informed of, observe, and comply with all federal, state, and local laws, ordinances, and regulations, and all orders and decrees of bodies or tribunals having any jurisdiction or authority, that in any manner affect those engaged or employed on the work or which in any way affect the conduct of the work.

The Contractor and the Surety shall defend, indemnify, and hold harmless the state and its representatives against any claim or liability related to violations of any laws, regulations or decrees by the Contractor, the Contractor's agents, the Contractor's employees, a subcontractor at any tier, or a supplier or service provider.

The Contractor has the affirmative duty to keep informed of and comply with all laws. The Contractor is not entitled to and shall not rely on any Department employee's interpretation, whether oral or written, of any law, ordinance, or regulation.

107-1.02 PERMITS, LICENSES, AND TAXES. The terms, conditions, and stipulations in permits obtained either by the Department or by the Contractor are made a part of this Contract.

The Department will:

1.	The Department has secured some permits and licenses required for the construction of the proposed Project. A list of permits secured, or to be secured by the Department is located in RFP Part III, Section 12, Environmental Compliance.

2.	Modify Department-acquired permits during the performance of the contract, if deemed necessary by the Engineer.

The Contractor shall:

1.	Acquire any permits and licenses required to complete the project that are not acquired by the Department;

2.	Provide qualified professionals to collect data or perform studies necessary to acquire permits for the use of sites not previously permitted;

3.	Give all notices required for the prosecution of the work;

4.	Abide by all permits and licenses whether acquired by the Department or by the Contractor;

5.	Notify the Engineer promptly if any activity cannot be performed as specified in the permits, and cease conducting the activity until permit modifications or any required additional permits are obtained;

6.	Obtain modifications to permits acquired by the Contractor;

7.	Pay all charges, fees and taxes; and

8.	Provide proof of payment of all taxes before the Department makes final payment.

In addition, before using an area not previously permitted for use by the Contract, the Contractor shall:

1.	Contact all government agencies having possible or apparent permit authority over that area;

2.	Obtain all required permits and licenses from those agencies;

3.	Obtain permission from any property owners or lessees with an interest in the property; and

4.	Provide all of the following to the Engineer:

a.	All permits or clearances necessary to use the site for its intended purpose(s);

b.	A written statement that all permits or clearances necessary have been obtained;

c.	Written evidence that the Contractor has contacted all of the relevant agencies and that no additional permits are required on the part of the Contractor, including at a minimum the name of the agency and staff person contacted, the date contacted, and result of coordination; and

d.	A plan that identifies how the site will be finally stabilized and protected.

The Engineer may reject a proposed site if the Contractor fails to provide any of the above information or to demonstrate that a proposed site can be finally stabilized to eliminate future adverse impacts on natural resources and the environment.

107-1.03 PATENTED DEVICES, MATERIALS AND PROCESSES. If the Contractor employs any design, device, material, or process covered by patent, trademark, or copyright, the Contractor shall obtain and provide the Engineer with a copy of a suitable legal agreement with the patentee or owner.

The Contractor and the Surety shall defend, indemnify, and hold harmless the state and its representatives and any affected third party or political subdivision from any claim, cause of action, and damages for infringement arising from or relating to the Contractor's use of a patented design, device, material, process, trademark, or copyright.

107-1.04 WAGE RATES. The Contractor and all subcontractors shall pay the current prevailing rate of wages as per AS 36.05.010 and this Contract. On federally funded projects the Contractor and all subcontractors shall pay the higher of the appropriate wage rates published by the Alaska Department of Labor and the U.S. Department of Labor, for each individual job classification. The Contractor and all subcontractors shall file certified payroll with the Alaska Department of Labor and Workforce Development (DOLWD) and with the Engineer for all work performed on the project.

Before beginning work the Contractor shall file a Notice of Work with DOLWD and pay all required fees. After finishing work the Contractor shall file a Notice of Completion with DOLWD and pay all additional fees required by increases in the Contract amount.

107-1.05 FEDERAL AID PROVISIONS. When the United States government pays all or any portion of the cost of a project, the Contractor shall observe all federal laws, rules, and regulations applicable to the project.

The Contractor shall allow appropriate federal officials access to inspect the work. The federal government is not a party to the Contract.  Federal inspections will not form the basis for any claim for interference with the rights of the Contract parties.

Form 25D-55 H Required Contract Provisions for Federal-Aid (FHWA) Construction Contracts. The FHWA no longer requires the contractor to fill out FHWA Form 47, Statement of Materials and Labor Used By Contractors on Highway Construction Involving Federal Funds. Section VI Records of Materials, Supplies and Labor of Form 25D-55H is no longer applicable to highway construction contracts.

Title VI Requirements. During the performance of this contract, the contractor, for itself, its assignees and successors in interest (hereinafter referred to as the "contractor") agrees as follows:

- Compliance with Regulations: The contractor shall comply with the Regulation relative to nondiscrimination in Federally-assisted programs of the Department of Transportation (hereinafter, "DOT") Title 49, Code of Federal Regulations, Part 21, and the Federal Highway Administration (hereinafter "FHWA") Title 23, Code of Federal Regulations, Part 200 as they may be amended from time to time, (hereinafter referred to as the Regulations), which are herein incorporated by reference and made a part of this contract.

- Nondiscrimination: The Contractor, with regard to the work performed by it during the contract, shall not discriminate on the grounds of race, color, or national origin, sex, age, and disability/handicap in the selection and retention of subcontractors, including procurements of materials and leases of equipment. The contractor shall not participate either directly or indirectly in the discrimination prohibited by 49 CFR, section 21.5 of the Regulations, including employment practices when the contract covers a program set forth in Appendix B of the Regulations.

- Solicitations for Subcontractors, Including Procurements of Materials and Equipment: In all solicitations either by competitive bidding or negotiation made by the contractor for work to be performed under a subcontract, including procurements of materials or leases of equipment, each potential subcontractor or supplier shall be notified by the contractor of the contractor's obligations under this contract and the Regulations relative to nondiscrimination on the grounds of race, color, or national origin, sex, age, and disability/handicap.

- Information and Reports: The contractor shall provide all information and reports required by the Regulations or directives issued pursuant thereto, and shall permit access to its books, records, accounts, other sources of information, and its facilities as may be determined by the DOT&PF or the FHWA to be pertinent to ascertain compliance with such Regulations, orders and instructions. Where any information required of a contractor is in the exclusive possession of another who fails or refuses to furnish this information the contractor shall so certify to the DOT&PF, or the FHWA as appropriate, and shall set forth what efforts it has made to obtain the information.

- Sanctions for Noncompliance: In the event of the contractor's noncompliance with the nondiscrimination provisions of this contract, the DOT&PF shall impose such contract sanctions as it or the FHWA may determine to be appropriate, including, but not limited to:

- withholding of payments to the contractor under the contract until the contractor complies, and/or

- cancellation, termination or suspension of the contract, in whole or in part.

- Incorporation of Provisions: The contractor shall include the provisions of paragraphs (1) through (6) in every subcontract, including procurements of materials and leases of equipment, unless exempt by the Regulations, or directives issued pursuant thereto.

The contractor shall take such action with respect to any subcontract or procurement as the DOT&PF or the FHWA may direct as a means of enforcing such provisions including sanctions for non-compliance: Provided, however, that, in the event a contractor becomes involved in, or is threatened with, litigation with a subcontractor or supplier as a result of such direction, the contractor may request the DOT&PF to enter into such litigation to protect the interests of the DOT&PF, and, in addition, the contractor may request the United States to enter into such litigation to protect the interests of the United States.

107-1.06 SANITARY, HEALTH, AND SAFETY PROVISIONS. The Contractor shall provide and maintain neat and sanitary accommodations for employees that meet all federal, state and local requirements.

The Contractor shall comply with federal, state, and local laws, rules, and regulations concerning construction safety and health standards, including U.S. Mine Safety and Health Administration rules when the project includes pit or quarry operations.

The Contractor shall not expose the public to, or require any workers to work under, conditions that are unsanitary, hazardous, or dangerous to health or safety.

The Contractor is responsible for ensuring all workers are adequately protected. The Contractor shall have a safety and health management program that complies with AKOSH requirements, and includes:

- A worksite hazard analysis;

- A hazard prevention and control plan including personal protective equipment and safe work procedures required for specific tasks;

- New employee training and periodic worker training regarding safety and health;

- Regular safety meetings with written documentation of attendance, safety topics discussed, worker safety complaints, and corrective actions taken; and

5.	A designated safety officer, employed by the Contractor, who monitors the construction site and is responsible for implementing the safety and health management program.

The Contractor shall defend, indemnify and hold harmless the State of Alaska from all claims, causes of action and judgments arising from or relating to the Contractor’s failure to comply with any applicable federal, state or local safety requirement, regulation or practice, whether or not listed above.

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES. When the Contractor's operation encounters prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, shell heaps, land or sea mammal bones, tusks, or other items of historical significance, the Contractor shall:

1.	Immediately cease operations at the site of the find;

2.	Immediately notify the Engineer of the find; and

3.	Not disturb or remove the finds or perform further operations at the site of the finds until directed by the Engineer.

The Engineer will issue an appropriate Change Order if the Engineer orders suspension of the Contractor's operations or orders the Contractor to perform extra work in order to protect an archaeological or historical find.

107-1.08 RAILWAY-HIGHWAY PROVISIONS. The Contractor shall conduct all operations on or near a railroad according to the Contract, any contract between the Department and the railroad, and any permits issued by the railroad. The Department shall obtain permits for hauling materials across railroad tracks at locations specified in the Contract. If the Contractor desires additional crossings, the Contractor shall obtain any required permits at the Contractor's expense.

107-1.09 CONSTRUCTION OVER OR ADJACENT TO WATERS. The Contractor shall fully comply with all laws, regulations and permits issued by agencies of the United States and the State of Alaska when working in, over or adjacent to wetlands, tidelands, anadromous fish streams, eagle nests, navigable waters, or coastal waters.

The Contractor shall ensure that all work in, over or adjacent to navigable waters is conducted so that free navigation of the waterways is not obstructed and that existing navigable depths are not impaired, except as allowed by the U.S. Coast Guard and the U.S. Army Corps of Engineers.

107-1.10 USE OF EXPLOSIVES. The Contractor shall obey all laws, regulations and permits applicable to using, handling, loading, transporting, or storing explosives. When using explosives, the Contractor shall take utmost care not to endanger life, property, new construction, or existing portions of the project and facilities that are to remain in place after the project is complete.

The Contractor shall provide notice to property owners, the traveling public, and utility companies in the vicinity before using explosives. The Contractor shall provide notice to the Federal Aviation Administration when required by law. The Contractor shall notify police and fire authorities in the vicinity before transporting or using explosives. The Contractor shall provide notice sufficiently in advance to enable all potentially affected parties to take whatever steps they may deem necessary to protect themselves and their property from injury or damage.

The Contractor is liable for all property damage, injury, or death resulting from the use of explosives on the project. The Contractor shall indemnify, hold harmless, and defend the State of Alaska from all claims related to the use of explosives on the project, including claims from government agencies alleging that explosives were handled, loaded, transported, used, or stored improperly.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

  - Restoring Areas. Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed. The original condition of an area shall be determined as follows: Prior to commencement of operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition. After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs. Prior to demobilization the Contractor shall repair damages attributed to its operations. The Contractor agrees that all costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

  - Material Disposal Sites. Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result therefrom, together with all permits required by law for such dumping. A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before commencing work on private property. The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer prior to use of the sites.

  - Property marks.  The Contractor shall:

- Be responsible for and protect from disturbance all land monuments and property marks until the Engineer has approved the witnessing or otherwise referenced their locations; and

- Not move such monuments or marks without the Engineer's approval.

  - Damage to property.  The Contractor shall:

  - Be responsible for all damage to public or private property resulting from any act, omission, neglect, or misconduct in the manner or method of executing the work;

  - Be responsible for all damage to public or private property resulting from defective work or materials at any time, before, during, or after project completion; and

  - Restore all such damaged property to a condition similar or equal to that existing before the damage occurred, at no additional cost to the Department.

  - Protection of natural resources. The Contractor shall:

- Conduct work in a manner that minimizes disturbance to and protects natural resources in compliance with all federal, state, and local laws and regulations;

- When working near designated wetlands, as defined by the Corps of Engineers, place no fill, nor operate equipment outside the permitted area;

- When working in or near designated anadromous fish streams, as defined by AS 41.14.840 and .870, place no fill or dredge material, nor operate equipment, within or on the banks of the stream (including fording) except as permitted by the State Fish Habitat Permit issued for the project; and

- Not refuel and service equipment within 100 feet of wetlands and/or other water bodies.

- If water from a non-municipal water source is required for construction purposes, obtain

a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.

- Bald Eagles are protected under the Bald Eagle Protection Act (16 U.S.C. 668-668c)

which prohibits “takes” of bald eagles, their eggs, nests, or any part of the bird. The Act defines “taking” as “to pursue, shoot, shoot at, poison, wound, kill, capture, trap, collect, molest, or disturb.”

Maintain a Primary Zone of a minimum 330 feet as an undisturbed habitat buffer around nesting bald eagles. If topography or vegetation does not provide an adequate screen or separation, extend this buffer to 0.25 miles, or a sufficient distance to screen the nest from human activities. The actual distance will depend on site conditions and the individual eagle’s tolerance for human activity. Within the Secondary Zone, between 330 feet and 660 feet from eagles nest tree no obtrusive facilities or major habitat modifications shall occur. If nesting occurs in sparse stands of trees, treeless areas, or where activities would occur within line-of-site of the nest, this buffer shall extend up to 0.5 miles. No blasting, logging and other noisy, disturbing activities should occur during the nesting period (March 1 – August 31) within the primary or secondary zones.

Extremely noisy activities such as road construction or other activities that occur within the Secondary Zone shall be conducted outside the nesting period to avoid disturbance to eagles. If activities occur in proximity to a nest site, employ an individual qualified to observe and assess the impact of such activities on nesting eagles. Behavior generally associated with disturbed eagles includes alarm calls, birds flushed from their nest or perch, and aggressiveness.

If nest trees are discovered within the vicinity of the project site, the U.S. Fish and Wildlife Service must be notified immediately by calling (907) 786-3503 or (907) 271 – 2772, before starting construction activities, for further site evaluation. This is an advisory. Do what is required to keep from disturbing a nesting eagle.

  - Hazardous materials. Hazardous materials include but are not limited to petroleum products, oils, solvents, paints, lead based paints, asbestos, and chemicals that are toxic, corrosive, explosive, or flammable. Except as otherwise specified in this Contract, the Contractor shall:

  - Not excavate, nor use for fill, any material at any site suspected of or found to contain hazardous materials or petroleum fuels;

  - Not raze and remove, or dispose of structures that contain asbestos or lead-based paints;

  - Not stockpile, nor dispose of, any material at any site suspected of or found to contain hazardous materials or petroleum;

  - Report immediately to the Engineer any known or suspected hazardous material discovered, exposed, or released into the air, ground, or water during construction of the project;

  - Report any containment, cleanup, or restoration activities anticipated or performed as a result of such release or discovery;

  - Handle and dispose of hazardous material with properly trained and licensed personnel who follow an approved Hazardous Material Control Plan as per Section 641.

  - Protected areas. The Contractor shall not use land from any park, recreation area, wildlife or waterfowl refuge, or any historical site located inside or outside of the project limits for excess fill disposal, staging activities, equipment or material storage, or for any other purposes unless permitted by the Contract or unless all permits and clearances necessary for such work have been obtained by the Contractor as detailed in Subsection 107-1.02.

  - Solid waste. The Contractor shall remove all debris, trash, and other solid waste from the project site as soon as possible and in accordance with the Alaska Department of Environmental Conservation Solid Waste Program.

107-1.12 FOREST PROTECTION. The Contractor shall:

1.  	Comply with all laws and regulations of the United States and the State of Alaska, local governments, or other authorities governing the protection of forests and the carrying out of work within forests;

2.  	Keep forest areas in an orderly condition;

3.	Dispose of all refuse and obtain permits for the construction and maintenance of all construction camps, stores, warehouses, residences, latrines, cesspools, septic tanks, and other structures in accordance with the requirements of the supervising authorities;

4.	Take all reasonable precautions to prevent and suppress forest fires;

5. 	Require workers and subcontractors, both independently and at the request of officials, to do all reasonably within their power to prevent and suppress and to assist in preventing and suppressing forest fires; and

6. 	Make every possible effort to notify the appropriate forestry agency at the earliest moment of the location and extent of any forest fire.

107-1.13 RESPONSIBILITY FOR DAMAGE CLAIMS. The Contractor shall indemnify, hold harmless, and defend the State of Alaska and its agents and employees from any and all claims or actions for injuries or damages whatsoever sustained by any person or property that arise from or relate to, directly or indirectly, the Contractor's performance of the Contract; however, this provision has no effect if, but only if, the sole proximate cause of the injury or damage is the Department’s negligence.

This Contract does not create a third party benefit to the public or any member of the public, nor does it authorize any person or entity not a party to this Contract to maintain a suit based on this Contract or any term or provision of the Contract, whether for personal injuries, property damage, or any other claim or cause of action.

107-1.14 OPENING SECTIONS OF THE PROJECT TO TRAFFIC. The Engineer may, at their discretion, order the Contractor to open sections of the work to traffic prior to completion of the entire project. Openings under this section shall not constitute (a) acceptance of the opened sections or any other part of the work or (b) a waiver of any other provision of the Contract.

The Engineer may establish a time period for completing any features of the opened section of work that are behind schedule.

The Contractor shall:

1.	Maintain the opened portions of the work without additional compensation;

2.	Perform all necessary repairs or renewals on the opened sections of the work without additional compensation; and

3.	Conduct the remainder of the work with minimum interference to traffic.

107-1.15 CONTRACTOR'S RESPONSIBILITY FOR WORK. The Contractor shall be responsible for implementing all preventative measures necessary to protect, prevent damage, and repair damage to the work from all causes at no additional cost to the Department. This duty continues from the date construction begins until the date specified in a letter of Substantial Completion or Partial Acceptance of a specific section of the project. Where there is a Partial Acceptance, the duty ends only as to the accepted portion of the work. This duty continues during periods of suspended work, except in specific sections the Department has agreed to maintain under Subsection 643-3.07.

The Contractor shall rebuild, repair, restore, and make good all losses or damages to any portion of the work including that caused by vandalism, theft, accommodation of public traffic, and weather. The Department will only be responsible for loss or damage due to unforeseeable causes beyond the control of and without the Contractor’s fault or negligence, such as Acts of God, the public enemy, and governmental authorities.

In case of suspension of work from any cause, the Contractor shall take such precautions as may be necessary to prevent damage to the work or facilities affected by the work. This will include providing for drainage and erecting any necessary temporary structures, signs, or other facilities and maintaining all living material such as plantings, seedings, and soddings.

107-1.16 RESERVED.

107-1.17 FURNISHING RIGHT-OF-WAY. The Department will secure all necessary right-of-way or property in advance of construction. Any exceptions will be indicated in the Contract.

107-1.18 PERSONAL LIABILITY OF PUBLIC OFFICIALS. There shall be no liability upon the Engineer and their authorized representatives, either personally or as officials of the state, in carrying out any of the provisions of this Contract, or in exercising any power or authority granted to them by or within the scope of the Contract, it being understood that in all such matters the Engineer and their authorized representatives act solely as agents and representatives of the State. The Contractor shall bring no suit related to or arising under this Contract naming as defendants any State officer, employee or representative in either their personal or official capacities, and shall include a prohibition to that effect in all subcontracts entered into for this Project.

107-1.19 NO WAIVER OF LEGAL RIGHTS. The Department shall not be precluded nor estopped by any measurement, estimate, or certificate made either before or after the completion and acceptance of the work and payment, from showing the true amount and character of the work performed and materials furnished by the Contractor, nor from showing that any measurement, estimate, or certificate is untrue or is incorrectly made, nor that the work or materials do not in fact conform to the Contract.

The Department shall not be precluded nor estopped, notwithstanding any measurement, estimate, or certificate and payment, from recovering from the Contractor or the Contractor’s Sureties, or both, such damages as it may sustain by reason of the Contractor's failure to comply with the terms of the Contract.

Neither the acceptance by the Department, or by any representative of the Department, nor any payment for or acceptance of the whole or any part of the work, nor any extension of time, nor any possession taken by the Department, shall operate as a waiver by the Department of any portion of the Contract or of any right of the Department to damages. A waiver by the Department of any breach of the Contract shall not be held to be a waiver of any other subsequent breach.

107-1.20 GRATUITY AND CONFLICT OF INTEREST. The Contractor shall not extend any loan, gratuity, or gift of money of any form whatsoever to any employee of the Department, nor will the Contractor rent or purchase any equipment or materials from any employee of the Department or to the best of the Contractor’s knowledge from any agent of any employee of the Department. The Contractor shall execute and furnish the Department an affidavit certifying that the Contractor has complied with this section before final acceptance.

## SECTION 108

## PROSECUTION AND PROGRESS

108-1.01 SUBCONTRACTING OF CONTRACT. The Contractor shall submit a Contractor Self Certification for Subcontractors and Lower Tier Subcontractors, Form 25D-042, before the Contractor or any subcontractor subcontracts, sells, transfers, assigns, or otherwise disposes of the Contract or any portion of the Contract. The Department has authority to review subcontracts and to deny permission to subcontract work. The Department may penalize the Contractor for false statements or omissions made in connection with Form 25D-042.

The Contractor shall perform, with the Contractor's own organization, work amounting to at least 30 percent of the difference between the original Contract price and the price of designated Specialty Items. For the purpose of this Subsection, work is defined as the dollar value of the services, equipment, materials, and manufactured products furnished under the Contract. The Engineer will determine the value of the subcontracts based on the approved Schedule of Values or upon reasonable value, if entire items are not subcontracted.

The Department’s consent to the subcontracting, sale, transfer, assignment, or disposal of all or a part of the Contract shall not relieve the Contractor and the Surety of responsibility for fulfillment of the Contract or for liability under the bonds regardless of the terms of the transfer or sublet approvals.

- The Contractor shall ensure that for all subcontracts (agreements):

- The Department is furnished with one completed Contractor Self Certification, Form 25D-042, for each subcontract;

- The subcontractors have submitted a Bidder Registration, Form 25D-6;

- The required prompt payment provisions of AS 36.90.210 are included in all subcontracts:

- A clause is included requiring the Contractor to pay the subcontractor for satisfactory performance according to AS 36.90.210 and within eight (8) working days after receiving payment from which the subcontractor is to be paid;

- A clause is included requiring the Contractor to pay the subcontractor interest, according to AS 45.45.010(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made:

- A clause is included requiring the Contractor to pay the subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received from the Department, or after the notice period under AS 36.25.020(b) expires, whichever is later;

- A clause is included requiring the Contractor to pay interest on retainage, according to AS 36.90.250 and AS 45.45.101(a):

- Other required items listed in Form 25D-042 are included in the subcontracts;

- The subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

- Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

- The Contractor shall ensure that for all lower tier subcontracts (agreements between subcontractors and lower tier subcontractors):

- The required prompt payment provisions of AS 36.90.210 are included in all lower tier subcontracts;

- A clause is included requiring the subcontractor to pay the lower tier subcontractor for satisfactory performance according to AS 36.90.210, and within eight (8) working days after receiving payment from which the subcontractor is to be paid;

- A clause is included requiring the subcontractor to pay the lower tier subcontractor interest, according to AS 45.45.010(a), for the period beginning the day after the required payment date and ending on the day payment of the amount due is made;

- A clause is included requiring the subcontractor to pay the lower tier subcontractor all retainage due under the subcontract, within eight (8) working days after final payment is received, or after the notice period under AS 36.25.020(b) expires, whichever is later;

- A clause is included requiring the subcontractor to pay the lower tier subcontractor interest on retainage, according to AS 36.90.250 and AS 45.45.101(a);

- Other required items listed in Form 25D-042 are included in the lower tier subcontracts;

- The lower tier subcontractors pay current prevailing rate of wages as per Subsection 107-1.04 and file certified payrolls with the Engineer and DOLWD for all work performed on the project; and

- Upon receipt of a request for more information regarding subcontracts, the requested information is provided to the Department within 5 calendar days.

- The following will be considered as subcontracting, unless performed by the Contractor:

- Roadside Production. Roadside production of crushed stone, gravel, and other materials with portable or semi-portable crushing, screening, or washing plants set up or reopened in the vicinity of the project to supply materials for the project, including borrow pits used exclusively or nearly exclusively for the project.

- Temporary Plants.  Production of aggregate mix, concrete mix, asphalt mix, other materials, or fabricated items from temporary batching plants, temporary mixing plants, or temporary factories that are set up or reopened in the vicinity of the project to supply materials exclusively or nearly exclusively for the project.

- Hauling. Hauling from the project to roadside production, temporary plants, or commercial plants, from roadside production or temporary plants to the project, from roadside production or temporary plants to commercial plants, and all other hauling not specifically excluded in this subsection.

- Other Contractors. All other contractors working on the project site under contract with the Contractor are considered subcontractors unless specifically excluded in this subsection.

- The following will not be considered as subcontracting, but the Contractor shall comply with the prompt payment provisions of AS 36.90:

- Commercial Plants. The purchase of sand, gravel, crushed stone, crushed slag, batched concrete aggregates, ready-mixed concrete, asphalt paving mix, and any other material or fabrication produced at and furnished from established and recognized commercial plants that sell to both public and private purchasers.

- Hauling.  Delivery of materials from a commercial plant to a different commercial plant, and delivery from a commercial plant to the project site by vehicles owned and operated by the commercial plants or by commercial freight companies that have a contract with the commercial plant. Commercial freight companies are trucking or hauling companies that deliver multiple types of materials to multiple clients, both public and private, on an established route and on a recurrent basis.

- Contractors' General Business.  Work within permanent home offices, branch plants, fabrication plants, tool yards, and other establishments that are part of a contractor's or subcontractor's general business operations.

- Owner-Operators. Hauling of materials for the project by bona fide truck owner-operators who are listed as such on the certified payroll of the Contractor or approved subcontractor is not considered subcontracting for purposes of AS 36.30.115.

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in contracts with owner-operators.

The Contractor shall collect and maintain at the project site current and valid copies of the following to prove that each trucker listed is a bona fide owner-operator:

- Alaska Driver's License with appropriate CDL class and endorsements;

- Business license for trucking with supporting documents that list the driver as the business owner or corporate officer;

- Documents showing the driver's ownership interest in the truck, including copies of:

- Truck registration; and

- Lease (if truck is not registered in driver's name or in the name of the driver's company).

The Contractor shall maintain legible copies of these records for a period of at least three years after final acceptance of the project.

Owner-operators must qualify as independent contractors under the current Alaska Department of Labor’s criteria. Owner-operators may be required to show:

- The owner-operator’s right to control the manner in which the work is to be performed;

- The owner-operator’s opportunity for profit or loss depending upon their managerial skill;

- The owner-operator’s investment in equipment or materials required for their task, or the employment of helpers;

- Whether the service rendered requires a special skill;

- The degree of permanence of the working relationship; and

- Whether the service rendered is an integral part of the owner-operator’s business.

The status of owner-operators is subject to evaluation throughout the project period. If the criteria for an independent contractor are not met, the Contractor shall submit amended payrolls listing the driver as an employee subject to all labor provisions of the Contract.

The Contractor shall issue each owner-operator a placard in a form approved by the Engineer that identifies both the truck driver and the vehicle. The placard shall be prominently displayed on the vehicle so that it is visible to scale operators and inspectors.

Notwithstanding the Department’s definitions of contracting and subcontracting, the Contractor shall be responsible for determining and complying with all federal and state laws and regulations regarding contracting, subcontracting, and payment of wages. The Contractor shall promptly pay any fines or penalties assessed for violations of those laws and regulations, and shall promptly comply with the directives of any government agency having jurisdiction over those matters.

108-1.02 NOTICE TO PROCEED. The Department will issue a Notice to Proceed authorizing construction to begin and indicating the date when Contract time will begin. The Contractor shall not begin construction before the effective date of the Notice to Proceed. The Department will, in its sole discretion, refuse to pay for construction begun before the effective date of the Notice to Proceed. The Contractor shall notify the Engineer at least 48 hours before construction begins at the project site.

108-1.03 PROSECUTION AND PROGRESS.  The Contractor shall meet with the Engineer at the regional construction office for a preconstruction conference before beginning construction. Submit the following at the Preconstruction Conference:

- A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subcontractors will start and finish each of the salient features of the work, including scheduled periods of shutdown. Indicate anticipated periods of multiple shift work in the CPM Schedule. Revise to the proposed CPM Schedule promptly. Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.

- A list showing anticipated dates for procurement of materials and equipment, ordering of articles of special manufacture, furnishing of plans, drawings and other data required under Subsection 105-1.02 and for other events such as inspection of structural steel fabrication.

- A list showing all proposed subcontractors and material suppliers.

- A Construction Phasing plan, as required under Subsection 643-1.05.

- A Storm Water Pollution Prevention Plan, Erosion and Sediment Control Plan, and a Hazardous Material Control Plan, with the line of authority and designated field representatives, as required under Section 641.

- A letter designating the Contractor's Project Superintendent, defining that person's responsibility and authority, and providing a specimen signature.

- A letter designating the Environmental Compliance Officer, and designating that person’s responsibilities and authority

- A letter designating an Equal Employment Opportunity Officer and a Disadvantaged Business Enterprise Officer, and designating those person’s  responsibilities and authority.

- A Design Quality Management Plan, Construction Quality Management Plan, and a Quality Control Plan, as required under Subsection 106-1.03, Testing and Acceptance, and Part III, Section 16, Quality Program.

- A letter designating a Safety Officer, and designating that person’s responsibilities and authority.

- A letter designating the Environmental Compliance Officer, and designating that person’s responsibilities and authority.

- A proposed Schedule of Values submitted on a state contract form for approval. The Contractor shall break down all Contract work into measurable work items, in sufficient detail to serve as a basis of progress payments. Any stockpiled materials for which interim payment is proposed shall be included. The Schedule of Values must indicate a quantity and unit cost including overhead and profit for each work item, the total cost for each work item, and the total cost for all work items. The total cost for all work items must equal the total Contract price.

The Contractor shall provide adequate materials, labor and equipment to ensure the completion of the project according to the Plans and Specifications. The work shall be performed as vigorously and as continuously as weather conditions or other interferences may permit. The Contractor shall take into consideration and make due allowances at the Contractor’s expense for foreseeable delays and interruptions to the work such as unfavorable weather, frozen ground, equipment breakdowns, shipping delays, quantity overruns, utility work, permit restrictions, and other foreseeable delays and interruptions.  The Contractor shall identify these allowances on the progress schedule.

The Contractor shall adjust forces, equipment and work schedules as necessary to ensure completion of the work within the Contract time, and shall notify the Engineer at least 24 hours before resuming suspended operations.  Upon a substantial change to the work schedule or when directed by the Engineer, the Contractor shall submit a revised progress schedule in the form required, including a written explanation for each revision made in the schedule or methods of operation.

The Engineer's review or approval of the documents, plans, and schedules provided by the Contractor under this section shall not change the Contract requirements, release the Contractor of the responsibility for successful completion of the work or relieve the Contractor of the duty to comply with applicable laws. The Engineer’s review or approval of schedules shall not indicate agreement with any assertions of delay or claims by the Contractor.

It is the Contractor's responsibility to prepare and submit documents that satisfy all applicable contract requirements.  By reviewing and approving the Contractor’s documents, the Department does not warrant that following the Contractor’s documents will result in successful performance of the work. The Department's failure to discover defects in the Contractor's documents, the assumptions upon which they are based or conditions that prevent the Contractor from performing the work as indicated in the documents will not entitle the Contractor to additional compensation or time. If the Contractor becomes aware of any act or occurrence that may form the basis of a claim for additional compensation or an extension of time, it must specifically advise the Engineer of these conditions in accordance with Subsection 105-1.17.

108-1.04 LIMITATION OF OPERATIONS. The Contractor shall not open up work to the detriment of work already started. The Contractor shall minimize interference with traffic within the project.  The Contractor shall not stop or otherwise impede traffic outside the project limits without the Engineer's prior written permission. The Engineer may require the Contractor to finish a section of work in progress before starting additional sections if the Engineer determines it is necessary for the convenience of the public or the Department.

108-1.05 CHARACTER OF WORKERS, METHODS, AND EQUIPMENT.  The Contractor shall employ sufficient labor and equipment to complete the work required under the Contract and to complete it on time.

The Contractor shall ensure that all workers on the project have the skills and experience necessary to properly perform their assigned work. Workers engaged in special work or skilled work shall have sufficient experience in that work and in the operation of the equipment required to properly perform that work.

The Contractor shall comply with any written order by the Engineer to remove workers, who, in the opinion of the Engineer, perform the work in an unskilled manner, who are intemperate or disorderly, or who jeopardize the safety of the public, other workers or Engineer’s personnel.  The Contractor shall allow removed workers to return to the project only with the Engineer’s written permission. The Engineer may suspend the work if the Contractor fails to furnish suitable and sufficient personnel necessary to perform the work, or fails to remove any worker at the Engineer's order.

- The Contractor shall not use prisoner labor on the project.

The Contractor shall use equipment of the appropriate size and mechanical condition to produce the specified quality and quantity of work by the means specified in the Contract, if any, and shall ensure that the equipment does not damage roadways or property.

The Contractor shall ensure all equipment, materials, and articles incorporated into the work are new and of the specified quality, unless the Contract specifically permits otherwise.

The Contractor shall provide the Engineer with a list of all powered equipment that will be used on the project, showing the make, model, year, capacity, horsepower, and related information. The Contractor shall update this list when equipment is added or removed from the work site, but need not update more frequently than weekly.

When the methods and equipment to be used by the Contractor are not prescribed by the contract, the Contractor is free to use any method, means or equipment that is satisfactory to produce the specified work in conformity with the Contract, except as provided above.  At the request of the Engineer, the Contractor shall demonstrate that the method, means and equipment chosen will produce the work specified in the Contract in the time allowed under the Contract.  The Contractor shall bear all costs and impacts associated with any means, methods and equipment chosen by the Contractor.  No suggestion, statement or observation from the Engineer or other Department representatives shall alter this responsibility.

If the Contract specifies a particular method, means or type of equipment for performance of the work, the Contractor must use that method, means or equipment unless the Contractor first requests, in writing, permission to alter the Contract requirement and receives prior written approval from the Engineer.

108-1.06 CONTRACT TIME, EXTENSION OF CONTRACT TIME AND SUSPENSION OF WORK. Contract time will be by specific Completion Date.

1.	Completion Date. When the contract time is specified on a completion date basis, All work under the Contract shall be completed by the specified completion date.

2.	Reasons for Suspension of Work and Extension of Contract Time. The Department may order a suspension of work for any reason listed in Items 3a through 3p.

The Department shall not pay additional compensation, but may extend Contract time only, if there are delays in the completion of controlling items of work from unforeseeable causes that are beyond the Contractor's control and are not the result of the Contractor's fault or negligence, including:

- Acts of God;

- Acts of the public enemy;

- Fires;

- Floods;

- Epidemics;

- Quarantine restrictions;

- Strikes;

- Freight embargoes;

- Unusually severe weather;

- In accordance with Subsection 105-1.06.4.d, delays by utility owners beyond completion dates specified in the RFP Part III, Section 10, Utilities for relocating or adjusting utilities and related facilities; or

- Delays of subcontractors, suppliers and fabricators from unforeseeable causes beyond the control of the subcontractors, suppliers or fabricators and that are not the fault of the subcontractors, suppliers or fabricators, including those causes listed in this Subparagraph 3, Items a through j.

No additional Contract time or additional compensation will be allowed due to delays caused by or suspensions ordered due to:

  - Failure to correct unsafe conditions for the workers or the public;

  - Adverse weather that is not unusually severe;

  - Failure to carry out Contract provisions;

  - Failure to carry out orders given by the Engineer; or

  - Failure to timely obtain materials, equipment, or services.

The Contractor shall notify the Engineer as soon as the Contractor becomes aware of any act or occurrence that may form the basis of a request for a time extension under this section. The Contractor shall submit a request for a time extension to the Engineer within 10 days of the act or occurrence, and if an agreement is not reached, the Contractor may submit a Claim under Subsection 105-1.17.

The time allowed in the Contract, as awarded, is based on performing the original estimated quantities of work set out in the bid schedule. An assertion that insufficient time was originally specified shall not constitute a valid reason for extension of contract time. If satisfactory fulfillment of the Contract requires extra work, the Department may extend Contract time on a basis commensurate with the amount and difficulty of the extra work, provided that the extra work is for a controlling item.

4.	Suspension of Work.  The Engineer will suspend work on the project, in whole or in part, for such periods and for such reasons as the Engineer determines to be reasonable, necessary, in the public interest, or for the convenience of the Department.

a.	The Engineer will issue a written order to suspend, delay, or interrupt all or any part of the work.  The Contractor shall not be compensated for the suspension, delay, or interruption if it is imposed for a reasonable time under the circumstances.

b.	Unless another Contract section specifically provides otherwise, the Contractor will be compensated by equitable adjustment for a suspension, delay, or interruption of the work only if:

(1)	The period of suspension, delay, or interruption is for an unreasonable time under the circumstances and another Contract section allows compensation in the event of a suspension, delay, or interruption of the work under the circumstances that actually caused the suspension, delay, or interruption; or

(2)	The delay, suspension, or interruption results from the Department’s failure to fulfill a contractual obligation to the Contractor within the time period specified in the Contract or, if no time period is specified, within a reasonable time.

c.	No equitable adjustment will be made under this subsection for any suspension, delay, or interruption of the work if the Contractor's performance would have been suspended, delayed, or interrupted by any other cause for which:

(1)	The Department is not responsible under the Contract, including the Contractor's fault or negligence; or

(2)	An equitable adjustment is either provided for or excluded under any other section of this Contract.

- Claims for equitable adjustments under this section shall be filed under Subsection 105-1.17 except that:

(1)	The Contractor must give written notice of intent to claim no later than 20 days after the event giving rise to the delay, suspension, or interruption; and

(2)	The claim may not include any costs incurred more than 20 days before the Contractor files the Contractor's written notice of intent to claim.

108-1.07 FAILURE TO COMPLETE ON TIME. For each calendar day that the work is not substantially complete after the expiration of the Contract time or the completion date has passed, the Engineer shall deduct the full daily charge corresponding to the original Contract amount shown in Table 108-1 from progress payments.

For each calendar day that the work is substantially complete but the project is not complete, after the expiration of the Contract time or the completion date has passed, the Engineer shall deduct 20 percent of the daily charge corresponding to the original Contract amount shown in Table 108-1 from progress payments.

If no money is due the Contractor, the Department may recover these sums from the Contractor, from the Surety, or from both. These are liquidated damages and not penalties.  These charges shall reimburse the Department for its additional administrative expenses incurred due to the Contractor's failure to complete the work within the time specified.

- Table 108-1

DAILY CHARGE FOR LIQUIDATED DAMAGES

FOR EACH CALENDAR DAY OF DELAY

| Original Contract Amount |  | Daily Charge |
| --- | --- | --- |
| From More Than | To and Including |  |
| $ 0 | $ 100,000 | $ 300 |
| 100,000 | 500,000 | 550 |
| 500,000 | 1,000,000 | 750 |
| 1,000,000 | 2,000,000 | 1,000 |
| 2,000,000 | 5,000,000 | 1,500 |
| 5,000,000 | 10,000,000 | 2,500 |
| 10,000,000 | -------------- | 3,000 |

Permitting the Contractor to continue work after the Contract time has elapsed or the completion date has passed does not waive the Department’s rights to collect liquidated damages under this section.

108-1.08 DEFAULT OF CONTRACT. The Contracting Officer will give a written Notice of Default to the Contractor and the Surety if the Contractor:

1.	Fails to begin work under the Contract within the time specified;

2.	Fails to perform the work with sufficient workers, equipment, or materials to ensure the prompt completion of the work;

3.	Performs the work unsuitably or neglects or refuses to remove materials or to replace rejected work;

4.	Discontinues the prosecution of the work;

5.	Fails to resume work that has been discontinued within a reasonable time after notice to do so;

6.	Becomes insolvent except that if the Contractor declares bankruptcy, termination shall be in accordance with the Federal Bankruptcy Code. In the event that the Contractor declares bankruptcy, the Contractor agrees that the Contract will be assumed by the Surety in a timely manner so as to complete the Contract by the date specified in the Contract;

7.	Allows any final judgment to stand against the Contractor unsatisfied for a period of 60 days;

8.	Makes an assignment for the benefit of creditors, without the consent of the Engineer;

9.	Fails to comply with applicable minimum wage or civil rights requirements;

10.	Is a party to fraud, deceit, misrepresentation, or malfeasance in connection with the Contract; or

11.	Fails to perform the work in an acceptable manner for any other cause whatsoever.

The written Notice of Default will include a notice to cure and will establish a date by which the cure must be completed. The Contracting Officer may allow more time to cure than originally stated in the Notice to Default if the Contracting Officer deems it to be in the best interests of the Department.  Failure to cure the delay, neglect, or default within the time specified in the Contracting Officer’s Notice of Default authorizes the Department to terminate the contract.  The Department will provide the Contractor and the Contractor's Surety with a written Notice of Termination.

After the Notice of Termination is issued, the Department may take over the work without further notice; may complete it by itself, by contract or otherwise; and may take possession of and use materials, appliances, equipment, or plant on the work site necessary for completing the work.

The Department may transfer the obligation to perform the work from the Contractor to the Surety. In that event, the Surety shall submit its plan for completion of the work, including any contracts or agreements with third parties for completion, to the Department for approval before beginning work. The Surety must follow the Contract requirements for approval of subcontracts, except that the limitation on percent of work subcontracted will not apply. On receipt of the transfer notice, the Surety shall take possession of all materials, tools, equipment, and appliances at the work site, employ an appropriate work force, and complete the Contract work as specified. The Contract specifications and requirements shall remain in effect, except that the Department will make subsequent Contract payments directly to the Surety. The Contractor forfeits any right to claim for the work and is not entitled to receive any further balance of the amount to be paid under the Contract.

The Contractor and the Contractor's Surety are jointly and severally liable for any damage to the Department resulting from the Contractor's delay, neglect, or default, whether or not the Department terminates the Contractor's right to prosecute the work. The Department's damages include any increased costs incurred by the Department in completing the work or paying for the work to be completed. The Department's rights and remedies are in addition to any other rights and remedies provided by law or under the Contract.

If, after notice of termination of the Contractor's right to proceed under this clause, it is determined that the Contractor was not in default, or that the default was excusable, the rights and obligations of the parties will be determined under Subsection 108-1.09, Termination for Convenience.

108-1.09 TERMINATION FOR CONVENIENCE.

- Notice. The Contracting Officer may terminate the Contract in whole or in part due to:

- Executive Orders of the President of the United States or the Governor of the State of Alaska with respect to the prosecution of war or the interest of national defense, or any disaster declaration.

- Restraining orders or injunctions by a court of competent jurisdiction affecting prosecution of the work based on acts or omissions of persons or agencies other than the Contractor.

- Any reason determined by the Contracting Officer to be in the best interest of the Department.

The Contracting Officer will issue a written Notice of Termination to the Contractor. The Notice of Termination shall state the extent to which performance of work under the Contract is terminated, the effective date of the termination, and for which of the above-listed reasons the Contract is terminated.

- Required Actions. Unless otherwise directed by the Contracting Officer, upon receipt of a Notice of Termination the Contractor shall immediately:

- Stop work as directed in the Notice.

- Place no further orders or subcontracts for materials, services, or facilities except as approved to complete work not terminated.

- Terminate all orders and subcontracts for the terminated work.

- Accomplish either (1) or (2) below as directed by the Contracting Officer:

- Assign to the Department all right, title and interest in any terminated orders or subcontracts. The Contracting Officer will settle all claims on the terminated orders or subcontracts.

- Settle any outstanding liabilities and claims arising from termination of orders and subcontracts. Settlements must be limited to costs allowed under this Section.

- Submit to the Contracting Officer a list, certified as to quantity and quality, of all materials acquired or produced for incorporation into the project and that are properly allocable to the terminated portion of the project, exclusive of items disposed of under Subsection 108-1.09.2.f., below.

- Dispose of materials in the Contractor’s possession or control that were acquired or produced but not incorporated into the project as of the termination date as directed by the Contracting Officer under either (1) or (2) below:

- Transfer title and deliver the materials to the Department. The Department will pay for the materials at the actual cost delivered to the project or storage site, including transportation charges, to which cost 15% will be added.

- Sell the materials. Credit will not have to be extended to prospective purchasers.

The Contractor may acquire the materials if the Contracting Officer approves the sale price and the Contractor meets any other conditions prescribed by the Contracting Officer.

At the sole discretion of the Contracting Officer, the proceeds of any sale, transfer, or disposition of materials may be:

- applied to reduce any payments to be made by the Department under the Contract,

- credited to the cost of the work, or

- paid in any other manner as directed.

- Deliver to the Department completed or partially completed plans, drawings, information, and other property required to be furnished under the Contract.

- Take all necessary actions and comply with all directives to protect contract-related property in which the Department has or may acquire an interest.

- Complete work not terminated.

The Contractor shall proceed immediately with performance of the above obligations notwithstanding any delay in determining or adjusting the amount of any item or reimbursable cost under this clause.

- Claim. The Contractor shall submit any termination claim to the Contracting Officer within 90 days after the effective date of termination, unless the date for submitting a claim is extended in writing by the Contracting Officer.

- Without duplication of any amount paid for under Subsection 108-1.09.2., the claim may be for the total of:

- costs incurred in performing the terminated work from the date of Contract award to the effective date of the termination subject to the provisions of Subsection 108-1.09.3.b. regarding reimbursement of equipment costs and Subsection 108-1.09.3.c. regarding unallowable items.

- payments approved by the Contracting Officer under Subsection 108-1.09.2.d.(2) to settle the termination claims of suppliers and subcontractors to the extent not covered under Subsection 108-1.09.3.a.(1).

- reasonably incurred costs for:

(a)	accounting, legal, clerical, and other costs reasonably necessary for preparation of the termination claim and settlement negotiations, excluding costs incurred after the date an appeal is filed with the Appeals Officer under Subsection 108-1.09.8.

(b)	settling subcontractor and supplier claims, excluding the amounts of those settlements paid under Subsection 108-1.09.3.a.(2).

- reasonable profit on the costs included in Subsection 108-1.09.3.a(1) based on the Contractor’s bid rate for profit or as determined under any other reasonable accounting method. However, if it appears that the Contractor would have sustained a loss on the entire Contract had it been completed, the Contracting Officer will allow no profit and will reduce the settlement to reflect the indicated rate of loss under Subsection 108-1.09.4. The Department will not pay profit on costs included in Subsections 108-1.09.3.a.(2) and 108-1.09.3.a.(3).

- Equipment claims will be reimbursed as follows:

- Contractor-owned equipment usage, based on the Contractor’s ownership and operating costs for each piece of equipment as determined from the Contractor’s accounting records. Do not base equipment claims on published rental rates.

- Idle time for Contractor-owned equipment, based on the Contractor’s internal ownership and depreciation costs. Idle equipment time is limited to the actual period of time equipment is idle as a direct result of the termination, not to exceed 30 days. Operating expenses will not be included for payment of idle equipment time.

- Rented equipment, based on reasonable, actual rental costs. Equipment leased under “capital leases” as defined in Financial Accounting Standard No. 13 will be considered Contractor-owned equipment. Equipment leased from an affiliate, division, subsidiary or other organization under common control with the Contractor will be considered Contractor-owned equipment, unless the affiliate, division, subsidiary or other organization has an established practice of leasing to unaffiliated lessees.

- The following costs are not payable under a termination settlement agreement or Contracting Officer’s determination of the termination claim, or on appeal:

- Loss of anticipated profits or consequential or compensatory damages

- Unabsorbed home office overhead (also termed “General & Administrative Expense”) related to ongoing business operations

- Bidding and project investigative costs

- Direct costs of repairing equipment to render it operable for use on the terminated work

- Adjustment for Loss. If the Contractor would have sustained a loss on the entire Contract had it been completed, the Department will not pay the Contractor more than the total of:

- The amount due for termination claim costs under Subsection 108-1.09.3.a.(3); plus

- The remainder of the total allowable claim amount due reduced by multiplying the remainder by the ratio of (1) the total contract price to (2) the remainder plus the estimated cost to complete the entire Contract; minus

- all disposal and other credits, all advance and progress payments and all other amounts previously paid under the Contract.

- Deductions. In arriving at the amount due under this Subsection, the Department will deduct:

- All previous payments made before termination;

- Any claim which the Department may have against the Contractor;

- The proceeds of the sale or transfer of any materials, supplies, or other items acquired for the terminated work and not otherwise recovered by or credited to the Department;

- All partial payments made under this Section; and

- Any adjustment for loss determined under Subsection 108-1.09.4.

- Agreed Settlement. The Contractor shall make every effort to arrive at a claim settlement with the Contracting Officer that is fair to both parties, that reflects the reasonable and allocable incurred costs allowable under Subsection 108-1.09.3, that includes a profit under Subsection 108-1.09.3.a.(4) or, where appropriate, a loss adjustment under Subsection 108-1.09.4, and that takes into account the Contractor’s reasonable business judgment in performing the work.

The total settlement, whether determined under this Subsection 108-1.09.6 or under Subsection 108-1.09.7, exclusive of the costs listed in Subsection 108-1.09.3.a.(3), may not exceed the total contract price as reduced by previous payments made and the value of the work not terminated, as determined from the approved Schedule of Values.

If an agreement is reached in whole or in part, the Department will amend the contract and will pay the agreed amount.

- Determined Settlement. If the Contractor fails to submit a termination claim within the time allowed, or if an agreement is not reached on the amount due, the Contracting Officer may determine in a Contracting Officer’s Decision, the amount due under Subsection 108-1.09 on the basis of information available to the Department.

- Right of Appeal. The Contractor may appeal a Contracting Officer’s Decision within the time and in the manner specified in Subsection 105-1.17.

- Partial Payments. In the sole discretion of the Contracting Officer, the Department may make partial payments against costs incurred by the Contractor in connection with the terminated portion of the Contract. The sum of these partial payments will not exceed the Contracting Officer’s estimate of the total amount that will be due as a result of the termination. The estimate will be based on available information. The Contracting Officer may adjust the estimate as additional information becomes available. If the Contracting Officer orders an audit of the Contractor’s financial or project records, the Contracting Officer may decline to make partial payments until the audit is completed.

- No Waiver of Rights. The termination of work by the Department does not affect or extinguish any of the rights of the Department against the Contractor or the Contractor’s Surety then existing or which may thereafter accrue. Any retention or payment of monies by the Department due under the terms of the Contract will not release the Contractor or the Contractor’s Surety from the contractual obligations or warranties made under Subsection 107-1.19 or elsewhere in the Contract.

- Retaining Records. The Contractor shall unless otherwise provided for in the Contract or by applicable statute, keep all books, records, documents, and other evidence bearing on the Contractor’s cost and expenses under the Contract and relating to the work terminated for a period of 3 years after final settlement under this Contract. Records must be made available to the Department at the Contractor’s office and at all reasonable times.

- Definitions. In this Subsection 108-1.09, the term “cost” and the term “expense” mean a monetary amount in U.S. Dollars actually incurred by the Contractor, actually reflected in the Contractor’s contemporaneously maintained accounting or other financial records and supported by original source documentation.

- Cost Principles. The Department may use the federal cost principles at 48 CFR §§ 31.201-1 to 31.205-52 (or succeeding cost principles for fixed price contracts) as guidelines in determining allowable costs under this Subsection to the extent they are applicable to highway construction contracts and consistent with the specifications of this Contract. The provisions of this contract control where they are more restrictive than, or inconsistent with, these federal cost principles.

## SECTION 109

## MEASUREMENT AND PAYMENT

109-1.01 GENERAL. The lump sum price indicated on Form PP-1 of RFP Part I, Instructions to Proposers, Section 9, RFP Proposal Forms (which is known as the Contract Price), shall be full compensation for design, construction, and warranty of the Project in its entirety. No adjustment of the Contract Price will be made except in the case of:

    - Adjustments for incentives or disincentives, or other reductions described in the Contract.

    - Owner directed changes in the Work in accordance with Subsection 104-1.02, Changes.

    - Differing Site Conditions in accordance with Section 104-1.03, Differing Site Conditions

All requirements specified or necessary for a complete Project are to be furnished for the Contract Price indicated in the Design-Builder’s Proposal in accordance with the accepted Release for Construction Plans, regardless of the presence or absence of any statements that any Work is to be paid for as extra work, or of the presence or absence of any statements that any Work is subsidiary to another item.

The above statement does not nullify Specifications that refer to price adjustments for quality of materials and/or workmanship, such as for asphalt cement concrete, Portland cement concrete, traffic price, schedule submittal adjustments or similar price adjustments, which shall remain in full force and effect.

109-1.02 MEASUREMENT OF QUANTITIES. The Contractor shall determine the quantities of work completed during each Contract pay period. The Contractor shall maintain current records of measurements, invoices, estimates, and computations for each pay request and make them available to the Engineer for inspection through Final Acceptance.

When the Contract specifies Quality Control and/or Acceptance testing frequencies, the Contractor shall provide timely measurements of material production and application rates to the Engineer to allow proper sampling and testing.

109-1.03 SCOPE OF PAYMENT. The Contractor shall accept the Contract Price as full payment for furnishing all resources necessary to complete all work under the Contract in a complete and acceptable manner. The Contractor shall assume all liability for risk, loss, damage, or expense resulting from the work, subject to Subsection 107-1.18.

109-1.04 COMPENSATION FOR ALTERED QUANTITIES.  No allowance shall be made to the Contractor for any increased expenses, loss of expected reimbursement or loss of anticipated profits suffered or claimed, from alterations in quantities.

109-1.05 COMPENSATION FOR EXTRA WORK ON TIME AND MATERIALS BASIS. When the Engineer orders extra work to be performed on a time and materials basis, compensation will be computed as follows:

1.	Labor. Based on the sum of a. through f.

a.	Total hours worked times the straight time rate of pay. The rates of pay are those indicated on the certified payroll for all labor and foremen in direct charge of the specific operations. Rates shall not exceed those for comparable labor currently employed on the project, and shall not include general superintendence.

b.	Overtime hours worked times the difference between the overtime rate and the straight time rate. No markup is allowed.

c.	Fringe benefit rate times the total hours worked. Fringe benefits include Health and Welfare, Pension Fund, etc., when such amounts are required by collective bargaining agreement or other employment contracts generally applicable to the classes of labor employed on the project.

d.	Workers’ Compensation Insurance at 8 percent of a. The actual net rate may be used if it exceeds 10 percent and if proof of rates is furnished within 30 days of the completion of the extra work.

e.	Either subsistence and travel allowances or prorated camp costs. If an employee is due and receives subsistence or camp privileges on their days off, divide that cost by the number of days worked that week and add to their daily subsistence entitlement. If the employee did not work an entire day on time and materials work, prorate the entitlement for the hours worked on time and materials.

- Markup at 35 percent of the sum of a., c., d., and e. This includes and shall fully compensate the Contractor for all overhead and profit, including general superintendence, additional bond, property damage liability insurance, unemployment insurance contributions, social security and other taxes, administrative overhead costs, and profit.

- Compensation for extra design work and administration will be computed by multiplying all direct labor costs by 2.60.

2.	Materials. Actual invoiced material and delivery costs plus 15 percent markup. The material must be approved and incorporated into the work. The Contractor shall furnish to the Engineer proof of payment for materials used in the work plus applicable transportation charges. For Contractor-produced materials, certify in writing the Contractor's actual direct costs, the quantities used, and attach cost spreadsheets and production documentation to verify the costs.

3.	Equipment. Includes machinery and special equipment (other than small tools) necessary for the work and authorized by the Engineer. No additional compensation will be made for overhead, profit, maintenance, service, repairs, fuels, lubricants, or replacement parts.

a.	Hourly Rental Rate. Based on rental rates in the current edition and appropriate volume of the Rental Rate Blue Book for Construction Equipment, published by PRIMEDIA Information, Inc., 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

The regular hourly rental rate is equal to the equipment rate plus the estimated hourly operating cost. These rates apply for equipment used during the Contractor's regular shift of 10 hours per day. No markup is allowed.

The equipment rate is equal to the age adjusted monthly rate for the basic equipment plus the age adjusted monthly rate for applicable attachments, both divided by 176, and multiplied by the regional adjustment factor for Alaska – South Region. The equipment rate is per hour.

The age adjusted monthly rate is that resulting from application of the age adjustment formula, to eliminate replacement cost allowances in machine depreciation and contingency cost allowances.

- Only the attachments required for the time and materials work will be included.

b.	Hourly Overtime Rate. Half of the equipment rate plus the full estimated hourly operating cost. The overtime rate will apply to hours the equipment is used in excess of 10 hours per day, either on the Contractor's normal work or on time and materials, and either on single or multiple shifts. No markup is allowed.

c.	Hourly Stand-by Rate. Half of the equipment rate, for equipment ordered on stand-by during the Contractor's normal work shift, not to exceed eight hours per day. No operating costs or markup is allowed.

d.	Unlisted Equipment. For equipment not listed in The Blue Book, the Contractor and the Engineer may agree to a rate before extra work is begun. If agreement is not reached, the Engineer has authority to establish a rate based on similar equipment in the Blue Book or prevailing commercial rates. No markup is allowed.

e.	Leased or Rented Equipment. Equipment that must be rented or leased specifically for work required under this section and authorized in writing by the Engineer shall be paid at invoice price plus 15 percent markup.

Equipment rented or leased for other work under the Contract and used for work under this section shall be paid based on 3.a., b., and c. (above) with no markup, except that the adjusted monthly rate is the monthly rate determined directly from the submitted rental or lease agreement.

f.	Transportation of Equipment. The actual cost of moving equipment to and from the work site. To receive reimbursement for transportation of equipment, the Contractor shall obtain the equipment from the nearest approved source and use the equipment exclusively for time and materials work. Payment for move-out will not exceed the amount of the move-in. No markup is allowed, except on operator’s wages.

Basis of payment:

- If by common carrier: paid freight bill or invoice.

- If hauled with the Contractor's own resources: hourly rental rate for hauling unit plus operator wages.

- If equipment must be moved under its own power: half of the normal hourly rental rate plus operator's wages.

4.	Work by a Subcontractor or Owner-Operator. For time and materials work performed by an approved subcontractor or owner-operator under items 1 through 3 above, the Contractor will receive a 5 percent markup for administrative costs. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid for work done by a lower tier subcontractor.

5.	Work by a Specialty Subcontractor. The Contractor shall obtain the Engineer’s advance agreement that the specialty item needed is beyond the Contractor's ability or expertise or that of the Contractor's other subcontractors. For work on a specialty item performed by an approved specialty subcontractor, the Contractor will receive the approved invoice cost of work or service plus a 15 percent markup for administrative costs.

6.	Records. The Engineer will maintain a daily record of labor, equipment and materials utilized in the extra work. The Engineer will present this record to the Contractor at the end of each day's work for verification and signature.

7.	Compensation. Payment for time and materials work will be made in the progress estimate following receipt of the verified daily records and all required supporting information from the Contractor. If, at any time, a unit price or lump sum basis of compensation is agreed to for work being performed under this subsection, that compensation will be set forth in writing as a Change Order.

109-1.06 PROGRESS PAYMENTS. The Department will make monthly progress payments to the Contractor based on estimates of the value of work performed and materials on hand under Subsection 109-1.07. At the Departments discretion, a progress payment may be made twice monthly if the value of the estimate exceeds $10,000 and the Contractor makes the request.

The Contractor shall submit an estimate of work completed based on the approved Schedule of Values. The Contractor shall include supporting documentation as required by the Engineer.

The Contractor shall submit Progress payment requests to the ICQF, which shall review each progress payment request. The ICQF shall verify that the acceptable quality documentation is on file for all items for which progress payment is requested and that the following information is correct:

1.	Percent complete of all payment items

2.	Quality-based price adjustments

3.	Value of materials on hand (in accordance with Subsection 109-1.07, Payment for Material on Hand)

The payment items are the items listed in the Design-Builder-provided and Department-approved Schedule of Values. The Contractor shall submit a proposed Schedule of Values at the Preconstruction Conference for approval. Once approved, the Schedule of Values shall be used as the basis for progress estimates. After the ICQF has reviewed the progress payment request and verified that it is correct, the ICQF shall so certify, and shall submit the progress payment request with the accompanying certification to the Engineer for payment. The progress payment requests shall not include any payment for work documented as deficient by the IQF.

Contractor’s failure to pay subcontractors, or subcontractor’s failure to pay lower tier subcontractors, according to prompt payment provisions required under Subsection 108-1.01 is considered unsatisfactory performance.

The Department will not withhold payment as retainage but may withhold payment for unsatisfactory performance. If satisfactory progress is being made and subcontractors are paid according to Subsection 108-1.01 and AS 36.90.210, the Engineer will authorize 100 percent payment for the estimated value of work accomplished, less any authorized deductions.

If the Engineer finds that satisfactory progress is not being made or payment for satisfactory work by a subcontractor or lower tier subcontractor is not paid according to Subsection 108-1.01, the Engineer may withhold up to 100 percent of the total amount earned from subsequent progress payments. The Engineer may withhold up to 200 percent of the estimated cost to complete final punch list items for unsatisfactory performance until those items are complete. The Engineer will notify the Contractor in writing within eight (8) working days of a request for a progress payment of the reasons why part or all of the payment is being withheld for unsatisfactory performance and what actions may be taken by the Contractor to receive full payment.

Payments of withheld amounts will be made in accordance with AS 36.90.200. No interest will be paid to the Contractor for amounts withheld for unsatisfactory performance except if the Department fails to pay the amount withheld within twenty one (21) calendar days after the Contractor satisfactorily completes the remedial actions identified by the Engineer, as provided in AS 36.90.200(e).

The Contractor shall pay interest on retainage withheld from subcontractors, and at an interest rate according to AS 36.90.250 and AS 45.45.010(a).

109-1.08 FINAL PAYMENT. When the project has been completed as provided in Subsection 105-1.15, the Engineer will prepare the final estimate of the quantities of the various classes of work performed. All prior progress estimates and payments shall be subject to correction in the final estimate and payment. The final estimate will not be processed until the Alaska Department of Labor and Workforce Development has verified that final payment can be released.  The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of Subsection 105-1.16.

If the Contractor approves the final estimate, or does not file a claim within 90 days of receiving the final estimate, the estimate shall be processed for final payment. Final payment shall consist of the entire sum found to be due after deducting all previous payments and all amounts to be retained or deducted under the provisions of the Contract.  Failure to file a claim within 90 days of receiving the final estimate is a waiver of any and all claims relating to or arising from the final estimate.

When the Contractor approves the final estimate and executes the Contractor’s Release form, final payment will be processed.

The Contractor may reserve any unresolved claims that were timely filed in accordance with Subsection 105-1.17 by listing those claims as exceptions on the Contractor’s Release. Any claims listed as exceptions that were not filed before the Contractor executes the final estimate will be considered null and void. Any claims filed in a timely manner but not listed on the Contractor’s Release are waived and deemed released.

If the Contractor fails or declines to approve the final estimate within 90 days but does not file any claims, the Department will consider the estimate approved and process the estimate for final payment.  Any subsequently raised claims will be considered null and void.

# DIVISION 200 – EARTHWORK

## SECTION 201

## CLEARING AND GRUBBING

201-1.01 DESCRIPTION. Clear, grub, remove, and dispose of all vegetation and debris within designated areas of the project, except such objects as are designated to remain or are to be removed under other sections of these Specifications. Preserve from injury or defacement all vegetation and objects designated to remain.

201-2.01 MATERIALS. None.

- CONSTRUCTION REQUIREMENTS

201-3.01 GENERAL. The limits of work and all trees, shrubs, plants and other things to remain shall be shown on the plans. Preserve all things designated to remain. Keep erosion potential to a minimum. Preserve survey stakes, boundary markers, bench marks, and tie points until such time as their usefulness has ceased and the work has been accepted.

Cut timber, with a 5 inch diameter or larger at breast height, into 8 foot lengths, de-limbed, and stacked to a height no greater than 6 feet at locations readily available for public removal. Make locations at an approved site that does not create a traffic hazard due to lack of adequate parking for the public. Access to the site(s) shall be maintained and controlled by flaggers, in accordance with Subsection 643-3.04. The Contractor shall provide and maintain a separate firewood telephone hotline that details when and where the wood is available to the public. Special Construction signs, in accordance with Subsection 643-2.01, shall be used to advertise the firewood telephone hotline. Provide at least two weeks for the public to access the site where timber is made available. Dispose of the remaining timber left after the public access time period. Mechanical loading by the public is not permitted.

Clearing and grubbing is not permitted within the migratory bird window of May 1 to July 15; except as permitted by Federal, State and local laws approved by the Engineer.

201-3.02 CLEARING. Cut and dispose of all trees, down timber, stubs, brush, bushes and debris from all areas designated.

Fell trees toward the center of the area to be cleared, in order to minimize damage to the trees that are to be left standing. Remove and dispose of trees unavoidably falling outside the specified limits. Cut trees and brush to a height of not more than 6 inches above the surrounding ground.

201-3.03 GRUBBING. Remove and dispose of all stumps, roots, moss, grass, turf, debris or other objectionable material within excavation limits, and within fill limits where the embankments are to be made to a depth less than 4 feet below subgrade. Grub any other areas designated on the Plans or in the Special Provisions.

Except in areas to be excavated, backfill stump holes and other holes with suitable materials and compact according to the Specifications.

201-3.04 HAND CLEARING. Cut and dispose of all trees, down timber, stubs, brush, bushes and debris from all areas designated, with minimal disturbance to grass and/or moss cover. Do not use equipment on wheels or tracks in areas designated as hand clearing, except as stated below.

Cut stumps flush with the ground. In areas to be covered by least 4 feet of subgrade material, stumps may extend up to 12 inches above natural ground, except where geotextile is specified.

201-3.05 SELECTIVE TREE REMOVAL. Remove and dispose of selected trees, as designated by the Engineer, and which are located outside the normal clearing and grubbing limits. The Engineer may designate the trees to be removed under this item at any time during the Contract life, subject to conditions in Subsection 201-3.04, Hand Clearing. Cut off designated trees no more than 12 inches above the ground surface.

201-3.06 DISPOSAL. Dispose of all vegetation, debris and timber less than 5 inch in diameter at breast height removed by clearing or grubbing using approved methods at approved off-site locations.

Obtain the property owner’s written permission to dispose of vegetation and debris at locations outside the right-of-way limits and a waiver of all claims against the State for any damage to such land which may result. Obtain all permits required by law for such disposal. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work.

Burning will only be allowed with permission of the Department. Do not burn when prevailing winds would produce a smoke hazard to traffic or disturb local communities. Place piles for burning in open spaces within the Project, or in other spaces shown on the Plans where no damage to trees, other vegetation or embankment stability will occur.

## SECTION 202

## REMOVAL OF STRUCTURES AND OBSTRUCTIONS

202-1.01 DESCRIPTION. Remove and dispose or salvage all buildings, fences, guardrail, structures, old pavements, abandoned utilities and any other obstructions which are not designated or permitted to remain, except for the obstructions to be removed and disposed of under other items in the Contract. Backfill the resulting trenches, holes and pits. When the bid does not include pay items for removal of structures and obstructions as set out in this Section, perform such work under Section 203 or as specified. Remove and reset mailboxes and newspaper delivery tubes and the preserve from injury and defacement all vegetation and objects not scheduled to be removed.

202-2.01 MATERIALS. Use materials that conform to the following:

Timber	AASHTO M 168 (Hemlock, Douglas fir, Western Pine, or Sitka Spruce). Pressure treated per AASHTO M 133.

Steel Pipe	Standard Weight Steel Pipe, 2-inch (max.) diameter. Galvanized per AASHTO M 111.

Steel Fasteners	ASTM A 307, Grade A. Galvanized per AASHTO M 232.

Reflectors	Yellow acrylic prismatic type meeting AASHTO M 290 or reflective sheeting meeting AASHTO M 268, Type III, IV, or V.

- CONSTRUCTION REQUIREMENTS

202-3.01 GENERAL. Raze, remove, and dispose of, or salvage all buildings and foundations, structures, fences, and other obstructions, any portions of which are within the right-of-way, except utilities and those for which other provisions have been made for removal.

Fill basements, or cavities left by structure removal, to the level of the surrounding ground and, if within the prism of construction, compact backfill as specified under Section 203.

- Stockpile all materials which are designated for use on the project at approved locations.

- Burn or otherwise dispose of combustible debris as approved.

Non-combustible debris or materials may be:

1.	placed in embankments under the provisions of Subsection 203-3.03 for placing rock in embankments (No metal pipes, wires, or cables may be placed in any embankment),

2.	buried on the project, outside the embankment at approved locations, under a minimum covering of 2 feet of earth, or

3.	disposed of outside the right-of-way limits, provided that before dumping such materials or debris on private or public lands, obtain from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result, together with all permits required by law for such dumping. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work. Grade waste areas to drain.

Remove septic or fuel tanks according to the Department of Environmental Conservation (DEC) regulation. Remove or abandon wells according to DEC regulations.

202-3.02 MAIL BOXES. Remove existing mail boxes and newspaper delivery tubes within the project limits and temporarily reset them at approved locations. Install the boxes and tubes in such a position that their usefulness will not be impaired.

After construction has been completed, install mail boxes and tubes to meet Standard Drawings M-20 and M-23. Repair or replace any posts, boxes, tubes or other material broken or damaged by the Contractor.

202-3.03 REMOVAL OF BRIDGES, CULVERTS, AND OTHER DRAINAGE STRUCTURES. Do not remove bridges, culverts and other drainage structures in use by traffic until satisfactory arrangements have been made to accommodate traffic.

Do not remove manholes, inlets, valves or any other portion or portions of the sewer or water systems until the new systems are in operation or suitable arrangements have been made for the diversion, interruption, or a temporary system has been installed.

When flexible pipe is designated on the Plans to be abandoned in place, crush and flatten the ends before covering. Securely plug other conduits by an approved method.

Remove the substructures of existing structures down to the natural stream bottom and remove those parts outside of the stream down 12 inches below natural ground surface. Where such existing structures lie wholly or in part within the limits for a new structure, remove such portions as necessary to accommodate the new structure.

Upon removal of existing bridges, dress all slopes or embankments according to the plan details. Dress slopes not designated in the Plans to conform to the natural ground surface or blend as directed. Fill all excavations and depressions.

Complete blasting or other operations necessary for the removal of an existing structure or obstruction, which may damage new construction, prior to placing the new work.

202-3.04 REMOVAL OF PIPE. Any pipe required to be removed to construct the work becomes the Design-Builder’s property.

During project construction, ENSTAR Natural Gas Company and AWWU may abandon existing pipelines. Follow the procedures given in Subsection 105-1.06, Utilities, when working around pipelines until they have been abandoned. Once the pipelines are abandoned, remove abandoned pipes within the right-of-way that are in conflict with the Work and dispose of off the Project limits. If in the opinion of the Department, the abandoned pipeline would not adversely affect future plans, the pipeline may be abandoned in place if properly filled with inert material such as grout.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS. Dispose of all concrete pavement, base course, sidewalks, curbs, gutters, etc., designated for removal, in an acceptable manner.

In removing pavements, curbs, walks, driveways and similar structures, make all cuts clean, vertical, and true to designated lines where an abutting structure or a part of a structure is to be left in place.

## SECTION 203

## EXCAVATION AND EMBANKMENT

203-1.01 DESCRIPTION. Excavate, haul, place, and compact or dispose of specified materials necessary to construct the project. Conform to the lines, grades, depths and typical cross sections shown on the Plans or as established. The Plans will designate material to be removed within the excavation limits as classified or unclassified excavation.

203-2.01 MATERIALS.

- Unclassified Excavation. All materials of whatever character encountered in the work. May include rock, common, or muck.

- Classified Excavation.

- Common Excavation. Silt, sand, gravel, and granular material other than rock or muck.

- Rock Excavation. Rock that cannot be excavated without blasting or ripping.

- Muck Excavation. Soils, organic matter, and other material not suitable for foundation material regardless of moisture content.

- Borrow. Approved material required for embankments or for other portions of the work, and obtained from sources outside the right-of-way limits for the project.

- Rock Stabilization Materials. As specified on the Plans or Special Provisions.

- Rockfall Mitigation Materials. As specified on the Plans or Special Provisions.

- Crushed Glass: May be combined with soil-aggregate material to be used in embankment construction. Meet 703-2.15 requirements.

- CONSTRUCTION REQUIREMENTS

203-3.01 GENERAL. Perform all necessary clearing and grubbing prior to beginning excavation, grading, and embankment operations in any area.

Keep excavation and embankment areas free draining at all times as the work progresses. Finish the excavation and embankments to reasonably smooth and uniform surfaces.

Excavate and embank material only within the limits on the Plans or as directed. Prevent disturbing material and vegetation outside of the slope limits.

The Engineer may designate excavated soils, that cannot be properly compacted in embankments, as unsuitable.

When unsuitable material is encountered at the required depth of excavation, remove the unsuitable material to the depth specified or directed. Allow for measurements to be taken before backfill is placed.

- Dispose of unsuitable material or excess usable material at approved locations.

Obtain the property owner’s written permission to dispose of unsuitable material or excess usable material at locations outside the right-of-way limits and a waiver of all claims against the State for any damage to such land which may result. Obtain all permits required by law for such disposal. Furnish a copy of such permission, waiver of claims, and permits to the Engineer before commencing work.

The Anchorage Regional Landfill at Hiland Road may allow disposal of unsuitable material or excess usable material at no cost to the Design-Builder.

Ensure that all waste areas are properly graded and drained. Blend the outer limits of waste into surrounding grounds with no noticeable break or variation readily discernible. When existing roadway embankment slopes are used as disposal sites for waste or surplus material, finish the slopes with a motor grader or other approved method.

When the volume of suitable excavation is not sufficient for constructing the fill to the grades indicated, furnish the necessary borrow from approved sources. Borrow may be necessary even though not shown on the Plans. The source and acceptability of the borrow is subject to approval.

Do not place borrow material until after the usable roadway excavation has been placed in the fill. If you place more borrow than is required, resulting in or as a result of the unnecessary wasting of usable excavation, the amount of such waste will be deducted from the borrow quantity.

Obliteration of Roadways includes all grading operations necessary to incorporate the existing roadway into the new roadway and surroundings in order to provide a pleasing appearance from the new roadway. Fill ditches not required for drainage and grade to the approximate original ground contour.

Do not place soil-aggregate containing glass cullet:

- Within four feet from the face of any embankment slope,

- Within 150 feet from any surface water body,

- In embankment areas where culvert placement is required,

- In contact with any geosynthetic material.

203-3.02 ROCK EXCAVATION. Excavate rock by blasting, ripping, or both.

Unless Subgrade Blasting is specified, excavate material which would classify as rock within the limits of the roadbed to a minimum depth of 6 inches below subgrade.

1.	Blasting.

a.	Blasting Plan. Prior to commencement of drilling, submit a Blasting Plan prepared by a qualified Blaster. Include the details of test blasting, controlled blasting and production blasting. Include station limits, date and time of each blast, layout details of each blast, trade names, types and sizes of explosives and accessories, delay sequences of the blast holes, and powder factors. Submit a revised Blasting Plan any time there is a change in the drilling or blasting methods.

b.	Blaster. Use a qualified blaster licensed or otherwise authorized under all applicable federal, state and local laws or regulations to possess, transport, store and use explosives of the type used on the Project. Provide the Blaster’s resume and copies of all applicable licenses to the Engineer with the Blasting Plan. Have the Blaster on site during all loading and blasting operations. Require the Blaster to take responsible charge for safety procedures as set forth below and to maintain a detailed record for each day of blasting work.

c.	Pre-Blast Conference. Hold a pre-blasting meeting at the jobsite prior to commencement of any drilling and blasting operations with the Contractor, the Blaster and representatives of the Engineer. Discuss the Blasting Plan and visit such specific sites as are necessary to familiarize the participants with the details of the blasting operations.

d.	Safety. Submit a Safety Plan that includes descriptions of road closures, warning signals, and plans for notification of affected local, state, and federal agencies. Discuss in the Safety Plan methods for protection of life and health, public and private property, new work or existing work on the project, nearby structures, wetlands, waters and wildlife. Hold a safety meeting prior to commencement of blasting operations to address safety issues.

e.	Controlled Blasting. Controlled blasting holes are closely spaced, lightly loaded holes drilled along the plane of the final design slope. Controlled blasting is either preshear blasting with holes detonated before the production blasting or cushion (trim) blasting with holes detonated after the production blasting. Drill holes parallel to each other and within 12 inches of the staked slope plane. Use controlled blasting techniques for all rock slopes higher than 10 feet to produce a stable cut face sheared along the designed neat excavation line. If at any time during the progress of the work, the approved methods of blasting and drilling fail to produce the desired result of a smooth, stable backslope, modify the blasting method to achieve the desired result. Do not construct benches in finished rock back slopes unless approved by the Engineer. The Engineer may permit an offset for drilling equipment clearances. Do not use ANFO in controlled blasting holes.

f.	Production Blasting. Use materials and methods as necessary to fragment and loosen the rock inside the design excavation limits, while leaving a smooth, stable back slope using the controlled blasting methods set forth above. Use appropriately designed delay sequences and charge weights per delay to minimize ground vibrations and prevent damage to buildings, structures, utilities, sensitive fish or wildlife habitat and other facilities. Prior to blasting, remove all loose objects, and render safe all dangerous conditions, in or near the cut slope area. Detonate production hole charges in a delay sequence toward the free face. Remove and dispose of loose material from rock slope failures or slides at the contract price for unclassified excavation if the Engineer determines the failure did not occur as a result of the Contractor’s methods. The Engineer will determine the amount of loose material at the time of removal.

g.	Scaling. Remove all loose, hanging, or potentially dangerous rock from newly excavated slopes and from surrounding existing slopes as the excavation progresses to ensure the rock slopes are stable. Do not commence work on subsequent lifts or shots until scaling is complete. Accomplish scaling with hand tools, hydraulic splitters, machine scaling with excavators or other equipment, high pressure water spray, light explosive charges, or other approved methods.

h.	 Ditch Line/Subgrade Blasting. Construct a free-draining fractured rock zone below the ditch line and the bottom of the structural section as shown on the Plans and Specifications or as directed. Blast or rip rock below the bottom profile of the ditch line and below the bottom of the structural section to depths as indicated or directed.

2.	Stabilization. Stabilize excavated or existing rock surfaces with rock bolts, rock dowels, shotcrete, or other techniques, as indicated in the Plans and Specifications or as directed. The Engineer may increase or decrease the extent and type of stabilization methods depending on the geologic conditions encountered during the work. Obtain approval from the Engineer for rock bolts, dowels, shotcrete, resin grout, cement grout, mortar, and other stabilization accessories prior to ordering the items. Conduct performance testing as required by the Engineer to confirm the stabilization methods and equipment produce the required capacities and functions.

3.	Rockfall Mitigation. Use rockfall mitigation methods such as rock catchment fences, wire mesh draping, flexible or rigid barriers, ditch width modification, and other techniques to intercept rockfall and control it before it reaches the roadway or other facilities. Construct according to the Plans and Specifications or as required by the Engineer. The Engineer may increase or decrease the extent and type of mitigation methods depending on the geologic conditions encountered during the work. Obtain approval from the Engineer for fence material, wire mesh, barrier design and accessories prior to ordering the items. Conduct performance testing as required by the Engineer to confirm the methods and equipment produce the required capacities and functions.

4.	Drain Holes. Drill drain holes in rock slopes to relieve excess water pressure as specified or directed. The Engineer will determine the location and construction details of the drain holes, depending on the conditions encountered in each slope.

203-3.03 EMBANKMENT CONSTRUCTION. Prepare the areas upon which embankments are to be placed, construct dikes within or outside the right-of-way when required, place and compact approved material within the roadway areas where unsuitable material has been removed, and place and compact embankment material in holes, pits, and other depressions within the roadway area. Use only approved materials in the construction of embankments and backfills. Embankment material will be approved for gradation following placement but prior to compaction.

Construct the embankment with selected material meeting the requirements of Subsection 703-2.07. Selected material may be obtained from unclassified excavation, rock excavation, common excavation or borrow.

Do not place rocks, broken concrete or other solid materials in embankment areas where piling is to be placed or driven, or where culvert placement is required.

Bench slopes that are steeper than 4:1, when measured at right angles to the roadway, when embankment is to be placed and compacted on hillsides, or when new embankment is to be compacted against existing embankments, or when embankment is built half-width at a time. Continuously bench over those areas as the work is brought up in layers. Make benches wide enough to permit placing and compacting operations. Begin each horizontal cut at the intersection of the original ground and the vertical side of the previous bench. Incorporate material cut out, and deemed suitable, into the new embankment and recompact along with the new material.

Scarify existing roadways, lying within 3 feet of subgrade, to a depth of 6 inches and recompact to meet Subsection 203-3.04 or 203-3.05.

When permanently frozen soils are encountered, place backfill or embankment materials in a timely manner, as directed, to minimize degradation of the foundation material. Do not place embankment over seasonally frozen ground unless authorized in writing.

Thaw and drain frozen material deemed acceptable for fill before placing in the embankment. Frozen cuts may require stage excavation: remove thawed material and allow the cut to thaw while work continues on some other portions of the project. After the material in the cut has thawed to a sufficient depth, remove the thawed material. Repeat this operation until all frozen material is removed or the cut is excavated to grade.

When excavation is performed when freezing weather is imminent, place the specified backfill promptly, following the excavation work, at least up to a level which will allow the surface to adequately drain. Make arrangements for the timely availability of such embankment or backfill materials prior to commencement of the stripping or excavation operations, when required.

If embankment can be deposited on one side only of abutments, wing walls, piers or culvert headwalls, prevent the overturning of or excessive pressure against the structure. Do not place the fill adjacent to the abutment of a bridge higher than the bottom of the backwall of the abutment until the superstructure is in place. When embankment is to be placed on both sides of a concrete wall or box type structure, keep the embankment at approximately the same elevation on both sides of the structure.

Place roadway embankment of earth materials in horizontal layers not to exceed 8 inches (uncompacted) for the full width of the embankment, except as required for traffic, and compact as specified before the next layer is placed. Use spreading equipment on each lift to obtain uniform thickness prior to compacting. Maintain uniform density, during compaction. Add or remove water, as necessary, to obtain the required density. Route compaction equipment uniformly over the entire surface of each layer.

Place rock embankment in lifts not thinner than the thickness of the largest rocks. Restrict maximum rock dimension to 3 feet. Distribute spalls and finer rock fragments to level and smooth each lift. Place succeeding lifts without damaging previously completed lifts. Dump rock on the lift being constructed and distribute by blading or dozing to fill voids and to form a dense, well-compacted embankment. Do not place rocks over 8 inches within 2 feet of finished subgrade.

Rock is considered usable material, regardless of size. Rocks too large to be embanked, as specified above, may either be reduced to a suitable size for incorporation into the embankment or disposed of in approved areas, at your option. Replace all wasted rock from excavation with borrow at no additional cost to the Department, unless such rock is excess to project embankment requirements.

Finish the subgrade surface so it will not vary more than 0.10 foot when tested using a 10-foot straightedge nor vary more than 0.10 ft from the established grade.

When embankment is to be placed over swampy or saturated ground, end dump an initial lift of material of sufficient depth to support hauling equipment, as directed.

- Repair damage to embankment caused by hauling equipment.

Construct all embankments with moisture and density control unless the Engineer determines that such controls are not feasible.

Temporary surcharging consists of two methods:

- Static Surcharge. Leave surcharge in place until the foundation material has reached stability or the required settlement has taken place.

- Rolling Surcharge. Construct a surcharge on top of the embankment to the specified elevation and continually advance the surcharge as the embankment is constructed ahead.

Use material removed from the temporary surcharge in areas indicated on the Plans. Do not waste temporary surcharge material without written approval. Compaction is not required for material placed in a temporary surcharge.

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL. The maximum density and optimum moisture will be determined by WAQTC FOP for AASHTO T 180 or ATM 212.

Adjust the moisture content of the embankment material to within 2% of the optimum moisture content and compact each layer to not less than 95% of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

Compact embankment within 20 feet of a bridge abutment full width to not less than 100 percent of the maximum density. Material used within this zone shall be graded to pass the 3 inch sieve.

203-3.05 COMPACTION WITHOUT MOISTURE AND DENSITY CONTROL. Except for rock fills and the first layer of fills over swampy ground, deposit embankment materials in layers not exceeding 8 inches in thickness before compaction.

Compact by routing construction equipment and/or rollers uniformly over the entire surface of each layer before the next layer is placed. Compact until embankment does not rut under the loaded hauling equipment.

Keep dumping and rolling areas separate. Do not cover any lift by another until the required compaction has been completed.

## SECTION 204

## STRUCTURE EXCAVATION FOR CONDUITS 
AND MINOR STRUCTURES

204-1.01 DESCRIPTION. Excavate and backfill for pipe culverts, storm drains, manholes, inlets and other minor structures.

Perform all pumping, bailing, draining, sheeting, bracing, and incidentals required for proper execution of the work.

204-2.01 MATERIALS. Use selected material, Type A (Subsection 703-2.07) passing the 3-inch sieve for bedding material, and for backfill material to 12 inches above the pipe.

Use excavated native material for the remainder of the backfill if it meets the requirements of Selected Material, Type C.

Use bedding material, and backfill material within the roadbed structure, meeting the requirements for the applicable lift of material.

Use all suitable material from structure excavation for bedding and backfill prior to using material from another source.

204-3.01 CONSTRUCTION REQUIREMENTS. Remove and dispose of unsuitable foundation material below the designed elevation, as shown on the Plans or as necessary to obtain a firm, unyielding foundation. Replace with approved material.

Remove rock or other unyielding material, when encountered, to the depth shown on the Plans or as directed and replace with approved material.

Place bedding and backfill in uniform layers not more than 6 inches deep and compact to meet Subsection 203-3.04. Ponding or jetting is not permitted.

Excavation, bedding, backfill, and compaction for culverts outside the roadbed may be visually inspected and approved by the Engineer.

Native material may be utilized for electrical conduit backfill outside the pavement structure if it meets the minimum requirements of Selected Material, Type C, as specified in Subsection 703-2.07. Compaction may be as approved by the Engineer.

Do not place backfill against newly constructed masonry or concrete structures for a period of 14 days or until concrete achieves at least 80% of the design strength (f 'c).

Support and protect existing conduits or utilities, which are not scheduled for removal or abandonment, when encountered in the excavation.

- Remove all sheeting and bracing used in structure excavation upon completion of the work.

## SECTION 205

## EXCAVATION, BACKFILL, AND 
FOUNDATION FILL FOR MAJOR STRUCTURES

205-1.01 DESCRIPTION. Excavate and backfill for the foundations of bridges, retaining walls, concrete box culverts, and other major structures.

Furnish all resources to place and remove cribbing or cofferdams. Perform all required sheeting, bracing, bailing, pumping, draining, and grouting.

- Replace unsuitable material encountered below the elevation of the bottom of footings.

205-2.01 MATERIALS. Use materials that conform to the following:

Backfill and Foundation Fill	Subsection 703-2.07, Selected Material, Type A

Porous Backfill Material	Subsection 703-2.10

- CONSTRUCTION REQUIREMENTS

205-3.01 EXCAVATION.

1.	General. Clear and grub prior to starting excavation.

Cut all rock or other hard foundation material to a firm surface, either level, stepped, or serrated, as directed, and remove all loose material.

Excavate to the bottom of footing prior to driving piles.  Do not excavate below the footing elevation unless otherwise noted in the Contract.

When swell or subsidence results from driving piles, excavate the footing area or backfill with foundation fill material, to the grade of the bottom of the footing, as shown on the Plans. This work is subsidiary.

- Do not disturb material below the bottom of footings.

Utilize all excavated material for backfill or embankment when approved as suitable and dispose of any unsuitable or surplus excavated material as directed.

Do not alter streambed channel and do not place excavated materials in natural stream channels, unless shown on the Plans or approved in writing.

Give the Engineer in writing no less than 15 days advance notice prior to beginning excavation for spread footings to allow for inspection of the excavated surface. With this notification, identify the location and specify a time period of no less than two days for the Department to inspect the excavated surface. Dewater and remove all debris from the surface prior to the Department's inspection. Obtain the Engineer’s approval of the excavated surface prior to the placement of any formwork or foundation materials. Account for the time required by the Department to perform the inspection in the progress schedule submitted under Subsection 108-1.03. Suspension of work to allow for inspection is not a suspension of work per Subsection 108-1.06 and additional contract time will not be allowed.

2.	Foundations on Bedrock. Excavate for footings founded on bedrock, to the neat lines of the footings. Fill overbreak areas outside the neat lines of footings, with Class A concrete, without extra compensation.

3.	Cofferdams. Use suitable cofferdams as necessary wherever water-bearing strata are encountered above the elevation of the excavation. Construct foundation seals according to the requirements of Subsection 501-3.08.

Submit detailed working drawings showing proposed method of cofferdam construction, designed by a person proficient in cofferdam design. The working drawings must be stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska. The details and clearance of cofferdams, which affect the character of the finished work, is subject to approval but other details of the design are your responsibility. Submit drawings at least 3 weeks in advance of cofferdam construction.

Extend cofferdams to the required depth or to bedrock. Adequately brace cofferdams and make them as watertight as practical. Provide sufficient clearance inside cofferdams to permit construction of forms and permit pumping outside of the forms.

Right or enlarge cofferdams which are tilted or moved out of position by any cause during the sinking process, to provide the necessary clearance and proper pier location.

When no foundation seal is shown on the Plans and the cofferdam cannot be dewatered, place a seal if permitted in writing.

Foundation seals, when shown on the Plans, may be eliminated as directed if the cofferdams can be dewatered without the seals when the excavation has been carried to the elevation of the bottom of the footing, unless the Plans or Special Provisions specifically note that seals may not be eliminated.

Vent cofferdams at low water, if foundation seals are required, in order to prevent damage to green concrete from differential hydrostatic head.

- No timber may extend into the completed substructure.

After substructure completion, remove sheet piling and other temporary structural materials in such a manner as to avoid disturbing the finished structure. Steel or concrete sheeting or bracing may be permitted to remain in the completed structure, subject to approval.

205-3.02 FOUNDATION FILL. Remove material that is unsuitable for foundations, to the depth below the bottom of the footing as shown on the Plans. Remove material that is unsuitable for approach slabs shown on the Plans.

Place Structural Fill in 8-inch layers, compacted to meet Subsection 203-3.04. Place Structural Fill as uniformly as possible on all sides of structural units as shown on the Plans. Avoid unbalanced loading of Structural Fill material which could damage the structure. When placed against concrete, place Structural Fill in accordance with Section 501.

Controlled Low-Strength Material may be used as an alternative source for Structural Fill if approved by the Engineer.

205-3.03 BACKFILL. Place backfill materials in 8-inch layers, compacted to meet Subsection 203-3.04.  Bench slopes within the area to be filled.

- Place underwater backfill in natural stream channels without compaction or layer requirements.

Place backfill as uniformly as possible on all sides of structural units. Avoid unbalanced loading of backfill which could damage the structure. When placed against green concrete or retaining type walls, prevent pressures which would damage the structure.

- No ponding or jetting of backfill is allowed.

205-3.04 POROUS BACKFILL. Place porous backfill material continuously within a vertical plane 1 foot behind retaining walls and abutments, unless otherwise shown on the Plans.

Where weep holes are shown on the Plans or required by the Specifications, place not less than 1 cubic foot of Porous Backfill material in the fill at each hole, securely tied in a burlap bag, or wrapped with an acceptable geotextile fabric. Extend the wrapped Porous Backfill material at least 6 inches above the hole.

205-3.06 CONTROLLED LOW-STRENGTH MATERIAL. Provide Controlled Low-Strength Material (CLSM) that is self compacting, cementitious, flowable material requiring no subsequent vibration or tamping to achieve consolidation.

Design CLSM to have 28-day compressive strength between 100 psi minimum to 300 psi maximum as determined by ASTM D 4832 and a flowable consistency within a slump range of 3 to 10 inches as determined by WAQTC FOP for AASHTO T 119.

Calculate the water-cement ratio on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, and silica fume. Use admixtures in accordance with the manufacturer’s recommendations. Do not use admixtures containing calcium chloride.

- Mix and batch CLSM in accordance with Subsection 501-3.01 to Subsection 501-3.03.

Do not place CLSM on frozen ground, in standing water, or during wet weather conditions. Place CLSM only if the air temperature is 40 °F minimum and rising. Ensure the material temperature is at least 50 °F while being placed.

- Do not apply loads to the CLSM until the compressive strength reaches 50 psi.

Acceptance will be based on a Certificate of Compliance. Provide a Certificate of Compliance for each batch of CLSM in accordance with Subsection 106-1.05.

## SECTION 206

## FILTER BLANKET

206-1.01 DESCRIPTION. Construct a layer of specified material in conformance to the plan dimensions and elevations.

206-2.01 MATERIALS. Use materials that conform to the following:

Filter Blanket	Subsection 703-2.08

206-3.01 CONSTRUCTION REQUIREMENTS. Construct Filter Blanket in an even, homogeneous layer, avoiding contamination by the underlying material. Place the layer to full thickness in one application or end-dump and spread by tracked equipment.

# DIVISION 300 – BASES

## SECTION 301

## AGGREGATE BASE AND SURFACE COURSE

301-1.01 DESCRIPTION. Construct an aggregate base course or aggregate surface course on an approved foundation, as shown on the Plans.

301-2.01 MATERIALS. Use aggregate conforming to Subsection 703-2.03.  Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5 inch sieve and 95-100 percent by weight passing the 1 inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

Crushed Glass: May be combined with soil-aggregate material to be used in base course construction. Meet 703-2.15 requirements.

- CONSTRUCTION REQUIREMENTS

301-3.01 PLACING. Place material in layers not exceeding 8 inches in depth.

- Maintain the roadway surface to drain freely at all times.

When paving is specified in the Contract, schedule the work so that any base course placed will be covered prior to winter shutdown.

Base course material used for the sidewalk and pathway foundation shall be placed with a “Layton box” or similar equipment capable of providing a specified depth with a uniform surface.

- Place surfacing material over all soil-aggregate bases containing glass cullet.

Do not place base course soil-aggregate containing glass cullet:

- Within four feet from the face of any embankment slope,

- Within 150 feet from any surface water body,

- In embankment areas where culvert placement is required,

- In contact with any geosynthetic material.

301-3.02 MIXING. Mix the aggregate, incorporating any specified additives. Add water, as needed, to provide the approximate optimum moisture content for compaction.

Mix the aggregate by one of the following methods:

1.	Stationary Plant Method

2.	Travel Plant Method

3.	Road Mix Method

The aggregate will be accepted for gradation based on random samples taken for each lift from the roadway after spreading but prior to compaction.

301-3.03 SHAPING AND COMPACTION. The maximum density and optimum moisture will be determined by WAQTC FOP for AASHTO T 180 or ATM 212.

Spread and shape the material to the required grade and section. Water or aerate as necessary to provide the approximate optimum moisture content for compaction. Compact each layer to a density of not less than 98% of the maximum density. Acceptance densities will be determined by WAQTC FOPs for AASHTO T 310 and T 224.

Maintain the surface of each layer during the compaction operations in such manner that a uniform texture is produced and the aggregates firmly keyed.

The finished surface will be tested using a 10-foot straightedge at selected locations. Limit surface deviations to 3/8 inch, as measured from the testing edge of the straightedge between two contacts with the surface.

If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. Use a test strip with a vibratory compactor with a minimum dynamic force of 40,000 pounds. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

## SECTION 302

## SUBGRADE MODIFICATION

302-1.01 DESCRIPTION. Scarify the existing road surface, incorporate aggregate and additives, if required, and grade and compact the material to the typical section shown on the Plans. Realign the shoulders and clean and reshape the ditches, if required on the Plans.

302-2.01 MATERIALS. As shown on the Plans.

- CONSTRUCTION REQUIREMENTS

302-3.01 PROCESSING. Blade the shoulder slopes and ditches to form a uniform shoulder line. First remove and dispose of weeds, sod, grass, roots, or other objectionable material from the surface. Spread the useable material obtained from the shoulder slopes and ditches and the surfacing material existing on the road surface uniformly over the roadbed.

Scarify the road surface to the depth specified. Pulverize lumps as needed so that not more than 5% of the material exclusive of gravel or stone is retained on a 2-inch sieve. Mix material thoroughly. Form the mixed material into a uniform windrow.

Place the quantity of aggregate for subgrade modification, as designated on the Plans, in a uniform windrow. Blend the windrowed materials together until all materials are uniformly distributed throughout the combined windrow.

- Aggregate will be accepted at the point of production based on periodic samples.

- Spread the material uniformly to the required cross section and compact to meet Subsection 203-3.04.

When the material being compacted contains a significant quantity of pulverized asphalt, adequacy of compaction will be determined by alternative methods acceptable to the Engineer.

302-3.02 FINISHING. The finished surface will be tested using a 10-foot straightedge at selected locations. Limit surface deviations to 1-1/4 inches, as measured from the testing edge of the straightedge between two contacts with the surface.

If a base or surface course is included in the Plans, maintain the surface of the completed subgrade until the base or surface course has been placed.

## SECTION 303

## RECONDITIONING

303-1.01 DESCRIPTION. Recondition the surface of an existing roadbed, clean and recondition the ditches, and shape the shoulders.

303-2.01 MATERIALS. None.

303-3.01 CONSTRUCTION REQUIREMENTS. Scarify the existing surface to the depth shown on the Plans. Pulverize material to 2 inches or smaller.

- Clean and recondition the ditches and shape the shoulders as shown on the Plans.

Spread surface material to line and grade and compact uniformly as specified in Subsection 203-3.04. Compact pulverized asphalt using alternate method acceptable to the Engineer.

The reconditioned surface will be tested using a 10-foot straightedge at selected locations. Limit surface deviations to 1 inch prior to placement of a base course or 3/8 inch prior to placement of a surface course, as measured from the testing edge of the straightedge between two contacts with the surface.

Maintain the surface satisfactorily until the base or surface course has been placed. Apply additional water, as required.

## SECTION 304

## SUBBASE

304-1.01 DESCRIPTION. Construct a subbase course on an approved foundation, as shown on the Plans.

304-2.01 MATERIALS. Use materials that conform to the following, for the grading specified:

Aggregate	Subsection 703-2.09

Crushed glass may be combined with soil-aggregate material to be used in subbase construction. Meet 703-2.15 requirements.

304-3.01 CONSTRUCTION REQUIREMENTS. Place and compact subbase material to meet the requirements of Subsections 203-3.01, 203-3.03, and 203-3.04.

The material will be accepted for gradation based on random samples taken from the roadway after spreading but prior to compaction.

When subbase material is utilized as the finished wearing course, place and compact to meet Subsection 301-3.01 through 301-3.03.

Do not place subbase soil-aggregate containing glass cullet:

- Within four feet from the face of any embankment slope,

- Within 150 feet from any surface water body,

- In embankment areas where culvert placement is required,

- In contact with any geosynthetic material.

## SECTION 306

## ASPHALT TREATED BASE COURSE

306-1.01 DESCRIPTION. Construct a plant-mixed asphalt treated base (ATB) course on an approved foundation to the lines, grades, and depths shown on the Plans.  Recycled asphalt pavement (RAP) may be used in the mix as specified herein.

306-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.

- MATERIALS

306-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 306-1 and as specified herein. Recycled Asphalt Pavement may be used to supplement the aggregate and asphalt cement in the ATB.

- TABLE 306-1

ATB Design Requirements

| DESIGN PARAMETERS | CLASS “B” |
| --- | --- |
| ATB (Including Asphalt Cement) |  |
| Stability, Pounds | 1200 min. |
| Flow, 0.01 Inch | 8 - 16 |
| Voids in Total Mix, % | 3 – 5 |
| Compaction, Number of Blows Each Side of Test Specimen | 50 |
| Asphalt Cement |  |
| Percent Voids Filled with Asphalt Cement (VFA) | 65 - 78 |
| Asphalt Cement Content, Min. % @ 4% VTM | 5.0 |
| Dust-Asphalt Ratio* | 0.6 - 1.4 |
| Voids in the Mineral Aggregate (VMA), %, Min. |  |
| Type II | 12.0 |
| *Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt cement. |  |

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the ATB, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3. For acceptance testing, ATB mixture will have the full tolerances in Table 306-2 applied. The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits. Tolerance limits will not be applied to the largest sieve specified.

Do not mix ATB produced from different plants for testing or production paving.  ATB from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of ATB:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD including gradations for individual virgin aggregate (aggregate) stockpiles and the RAP stockpile. Provide supporting process quality control information; including the blend ratio of each aggregate stockpile, the RAP stockpile and the RAP asphalt cement content. For mixes with RAP, provide JMD gradation with and without RAP. Provide calibration data if WAQTC FOP for AASHTO T308 is used for RAP process control.

2 	Representative samples of each aggregate (coarse, intermediate, fine, blend material and mineral filler, if any) and RAP required for the proposed JMD. Furnish 100 lbs of each intermediate and/or coarse aggregate, 200 lbs of fine aggregate, 25 lbs of blend sand, and 200 lbs of RAP.

3.	Three separate 1-gallon samples, minimum, of the asphalt cement proposed for use in the ATB. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet (MSDS).

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current MSDS.

The Engineer will evaluate the material and the proposed gradation using ATM 417 and Table 306-1 ATB Design Requirements.

The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

- FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 306-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The source of RAP is changed

Do not produce ATB for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD.

Payment for ATB will not be made until the new JMD is approved. Approved changes apply only to ATB produced after the submittal of changes.

- The Engineer will assess a fee for each mix design subsequent to the approved Job Mix.

306-2.02 AGGREGATES. Conform to Subsection 703-2.04. Type II, Class B (IIB) total combined aggregates.

Use a minimum of three stockpiles for crushed ATB aggregate (coarse, intermediate, and fine).  Place RAP, blend material and mineral filler in separate piles.

306-2.03 ASPHALT CEMENT. Conform to Subsection 702-2.01 and the following:

The total asphalt cement content may be a combination of PG 52-28 and the residual asphalt cement/binder in the RAP, or only PG 52-28. Documentation and conformance is required for the PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702, before delivery to the project. Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (Subsection 106-1.05).

2.	Conformance test reports for the batch (provide prior to delivery as noted above).

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

306-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD. At least 70% of the aggregate must remain coated when tested according to ATM 414. A minimum of 0.25% by weight of asphalt cement is required.

306-2.05 PROCESS QUALITY CONTROL. Sample and test materials for quality control of the ATB according to Subsection 106-1.03. Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results. When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 7 days before initiating pre-paving operations. Address the sequence of operations. Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the ATB, and to provide the mat density required by these specifications. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

- Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 306-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

306-2.06 RECYCLED ASPHALT PAVEMENT (RAP). Process existing pavement removed under Subsection 202-3.05 and 3.06 so material passes the 1-1/2 inch sieve. Stockpile the material separately from the crushed aggregates. Perform one gradation and one asphalt cement content test for every 1000 tons of RAP or a minimum of 10 sets of tests whichever is greater.

- CONSTRUCTION REQUIREMENTS

306-3.01 WEATHER LIMITATIONS. Do not place ATB on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix. Do not place ATB unless the roadway surface temperature is 40F or warmer.

306-3.02 EQUIPMENT, GENERAL. Use equipment in good working order and free of ATB buildup. Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production ATB.

306-3.03 ASPHALT MIXING PLANTS. Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before ATB production.

When using recycled asphalt pavement material, mix the RAP with the aggregate before the aggregate enters the plant thereby adding the RAP combined with the aggregate to the asphalt treated base mixture at one time.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the ATB.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

- Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

306-3.04 HAULING EQUIPMENT. Costs associated with meeting the requirements of Subsection 306-3.04 are subsidiary to Section 306 Pay Items.

Vehicles/Equipment. Haul ATB in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent. Do not use petroleum fuel as an asphalt release agent.

During ATB hauling activities, the hauling vehicle will have covers attached and available for use. Be prepared to demonstrate deployment of the cover when hauling material or empty. Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials. When directed by the Engineer, cover the ATB in the hauling vehicle(s).

Roadway Maintenance. Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surface(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 7 days before initiating paving operations. Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options. At a minimum, the cleaning station will include the materials and means to:

1.	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paving equipment.

2.	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

3.	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris. The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material, the users and others) and the damage to the roadway materials from the removal method(s). Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage, as specified in Subsection 306-3.16 Patching Defective Areas, to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal.  Use repair materials of similar type to the damaged material. Attain written approval from the Engineer for the proposed material.

306-3.05 PAVING EQUIPMENT. Use self-propelled asphalt pavers with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices. Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the screed or blade control system. Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Use a paver screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the ATB.

Equip pavers with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the ATB uniformly in front of screed.

Prevent segregation of the coarse aggregate particles from the remainder of the ATB during paving operations. Specifically equip pavers to prevent segregation between the hopper and augers. Use means and methods approved by the paver manufacturer. Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices. When required by the Engineer, provide a Certificate of Compliance verifying use of the means and methods required to prevent segregation.

306-3.06 ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact ATB asphalt mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

- Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

306-3.07 PREPARATION OF EXISTING SURFACE. Prepare base surface conforming to the Plans and Specifications.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402. Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material. Allow tack coat to break before placement of ATB on these surfaces.

306-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

306-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the ATB, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the ATB, and the RAP when being used in the mix, to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate. ATB containing soot or fuel is unacceptable (Subsection 105-1.11).

306-3.10 MIXING. Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T 195.

306-3.11 TEMPORARY STORAGE. Silo type storage bins may be used, provided the characteristics of the ATB remain unaltered. Changes in the JMD, visible or otherwise, are cause for rejection. Changes may include: visible segregation, heat loss; and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the ATB or similar.

306-3.12 PLACING AND SPREADING. Use asphalt pavers to distribute ATB. Place the ATB upon the approved surface, spread, strike off, and adjust surface irregularities.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the ATB surface immediately behind the paver for temperature uniformity. Areas with temperature differences more than 25o F lower than the surrounding ATB may produce areas of low density. Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less. Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the ATB in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours. Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

Do not the cover/place over the asphalt treated base material until the ATB material throughout that section, as defined by the Paving Plan, is placed and accepted.

- Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

- Do not place ATB over bridge deck membranes, except as directed by the Engineer.

306-3.13 COMPACTION. Compact the ATB by rolling thoroughly and uniformly. In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Prevent indentation of ATB. Do not leave rollers or other equipment standing on ATB that is not sufficiently cooled to prevent indentation.

A mat area with density lower than 92% MSG is considered segregated and not in conformance with the requirements of the Contract. The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 95% of the MSG, as determined by WAQTC FOP for AASHTO T 209.  The MSG of the JMD will be used for the first lot of ATB. The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

306-3.14 JOINTS. Minimize the number of joints. Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting. Place and compact the ATB to provide a continuous bond, texture, and smoothness between adjacent sections of the ATB.

Coordinate the joints in the ATB pavement layer with the layer of HMA pavement above.  Offset the longitudinal joints in the HMA pavement layer above from the joint in the ATB asphalt pavement layer immediately below by at least 6 inches.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer. Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Remove to full depth improperly formed joints resulting in surface irregularities. Before removing pavement, cut a neat straight line along the pavement to be removed and the pavement to remain. Use a power saw or other method approved by the Engineer. Replace the removed asphalt with new ATB and thoroughly compact.

306-3.15 SURFACE TOLERANCE. Costs associated with meeting surface tolerances are subsidiary to the ATB Pay Items.

The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge. Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

306-3.16 PATCHING DEFECTIVE AREAS. Costs associated with patching defective areas are subsidiary to the ATB Pay Items.

Remove defective ATB for the full thickness of the course, do not skin patch. Cut the pavement so that edges are vertical and the sides are parallel to the direction of traffic. Coat edges with a tack coat meeting Section 402 and allow to cure. Place and compact fresh ATB to grade (Subsection 306-3.13) and surface tolerance requirements (Subsection 306-3.15).

## SECTION 307

## EMULSIFIED ASPHALT TREATED BASE COURSE

307-1.01 DESCRIPTION. Construct an emulsified asphalt treated base (EATB) course on a prepared foundation to the lines, grades, and depths shown on the Plans.

307-2.01 MATERIALS. Use materials that conform to the following:

Aggregate	Subsection 703-2.03

Asphalt	Section 702, for the type and grade shown on the bid schedule

Anti-Strip	As required by the approved Job Mix Design

Portland Cement	Section 701 (Type I)

307-2.02 COMPOSITION OF MIXES. At least 15 days in advance of the production of EATB material, furnish a representative 300-pound sample of the base aggregate proposed for the project, and a representative 3-gallon sample of the asphalt material.

The Engineer will determine the job mix design. Changes in aggregate gradation or aggregate sources will require a new job mix design. Submit samples in the same manner as the original submittal.

Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design. At least 70% of the aggregate must remain coated when tested by ATM 414.

- CONSTRUCTION REQUIREMENTS

307-3.01 MIXING.

1.	Mix EATB material either

a.	at an approved central mixing plant,

b.	in place, on an approved subgrade, or

c.	on an approved mixing area.

If method b. or c. above is used, prevent contamination of the base course material by the underlying material.

Adjust aggregate moisture content prior to asphalt application. Apply Portland cement, if required, to the aggregate immediately prior to mixing.

Acceptance of aggregates will be based upon representative samples taken just prior to the addition of the emulsified asphalt.

2.	Central plants may be either batch or continuous twin-shaft pugmill units equipped with adequate proportioning devices to control aggregate, asphalt, water and Portland cement.

Combine the aggregate, emulsified asphalt, Portland cement, and water, in the mixing plant in the specified proportions. Adjust the mixing time to the minimum time which will provide a complete coating of the aggregate particles.

3.	Perform in-place mixing with single or double pugmill travel plants, rotary cross-shaft mixers, or motor grader (blade). Equip travel plants and cross-shaft mixers with adequate proportioning devices to control asphalt. Use distributors for applying asphalt for in-place blade mixing which conform to Subsection 402-3.02.

Mix aggregates, asphalt material and additives until a uniform coating of aggregate particles is attained.

307-3.02 WEATHER LIMITATIONS. Do not mix or place EATB material until the aggregate temperature is above 40 °F and the air temperature as measured in the shade and away from any heat source is 45 °F and rising. Do not place the EATB material on a wet or frozen surface, or when weather conditions will prevent proper handling, compacting, finishing, or curing of the mixture.

307-3.03 OPERATIONAL LIMITATIONS. Coordinate the various portions of the work to conform to the traffic maintenance requirements of Section 643.

Place EATB materials only on an accepted subgrade. Ensure that the subgrade surface is substantially true to line and grade, firm and reasonably smooth, and free of loose or objectionable material, before placement of EATB materials.

307-3.04 EQUIPMENT.

1.	Mixing Plant. Conform to Subsection 401-3.03.

2.	Hauling Equipment. Conform to Subsection 401-3.04.

3.	Spreading Equipment. Self-propelled paving machine or motor grader.

4.	Rollers. Conform to Subsection 401-3.06.

307-3.05 SPREADING AND FINISHING. Spread EATB material in single lifts not to exceed 6 inches. If the single lift cannot be compacted sufficiently to conform to Subsection 307-3.06, spread and compact in multiple lifts of equal thickness.

307-3.06 COMPACTION. The Engineer will use ATM 412 to determine the density standard. Make each control strip at least 12 feet by 300 feet. Compact the remainder of the project to not less than 98% of the density standard, in accordance with WAQTC TM 8. The Engineer will designate the location of test strips.

Compact the EATB using at least one pneumatic roller and one vibratory roller. Use vibratory compactors, applying a minimum dynamic force of 50,000 pounds per vibration at a minimum frequency of 1,000 vibrations per minute. Adjust working speed in order to apply 8 to 12 impacts per foot. In areas inaccessible to rollers, use mechanical tampers until thoroughly compacted.

307-3.07 SURFACE TEST. After rolling has been completed, the surface will be tested for smoothness and accuracy of grade, crown, superelevation, and width.

Limit surface deviations to 3/8 inch, as measured from the testing edge of a 10-foot straightedge between two contacts with the surface parallel with, and at right angles to, the centerline.

307-3.08 THICKNESS REQUIREMENTS. Limit deviations in thickness to 1/2 inch.

## SECTION 308

## CRUSHED ASPHALT BASE COURSE

308-1.01 DESCRIPTION. Construct a base course, using pulverized asphalt pavement, to the grades shown on the Plans.

- When item 308(2) is listed in the bid schedule, add emulsified asphalt to the base course mixture.

308-2.01 MATERIALS. Use materials that conform to the following:

Asphalt Concrete	Existing asphalt pavement material

Aggregate Base Course	Subsection 703-2.03

Emulsified Asphalt	Section 702 (CSS-1)

- CONSTRUCTION REQUIREMENTS

308-3.01 pulverizing and mixing. Crush or process the existing asphalt pavement so that 100% by weight passes the 2-inch sieve and 95-100% by weight passes the 1-1/2-inch sieve.

Use self-propelled pulverizing and mixing equipment capable of processing to full depth in a single pass. If emulsified asphalt is called for on the Plans, the mixing equipment must also be capable of adding the emulsion, through a metered system during mixing.

Add crushed aggregate base course to the base course mixture as needed to conform to the design grade.

308-3.02 WEATHER LIMITATIONS. Do not use any frozen material or compact on a frozen base.

308-3.03 SHAPING AND GRADING. Use a finish grader that is equipped with an automatic grade and cross slope control system. Maintain longitudinal grade control, based on either string line or the existing roadway surface, as determined by the Engineer.

308-3.04 COMPACTION AND COMPACTION EQUIPMENT. The Engineer will use ATM 412 to determine the density standard. Make each control strip at least 12 feet by 300 feet. Compact the remainder of the project to not less than 98% of the density standard, in accordance with WAQTC TM 8. The Engineer will designate the location of test strips.

Compact the base course using vibratory compactors, applying a minimum dynamic force of 50,000 pounds per vibration at a minimum frequency of 1,000 vibrations per minute. Adjust working speed in order to apply 8 to 12 impacts per foot. In areas inaccessible to rollers, use mechanical tampers until thoroughly compacted.

308-3.05 SURFACE TEST. The finished surface will be tested for smoothness and accuracy of grade, crown, superelevation, and width.

Limit surface deviations to 3/8 inch, as measured from the testing edge of a 10-foot straightedge between two contacts with the surface parallel with, and at right angles to, the centerline.

# DIVISION 400 – ASPHALT PAVEMENTS 
AND SURFACE TREATMENTS

## SECTION 401

## HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed hot mix asphalt on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section, HMA refers to Type I, II, III and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

c.	Use of Recycled Asphalt Pavement (RAP) is not permitted in HMA, except RAP may be used in HMA, Type II, Class B.

d.	Warm Mix Asphalt (WMA) is not permitted in HMA.

- MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to the Alaska Test Manual (ATM) 417 using the design requirements of Table 401-1.

- TABLE 401-1

HOT MIX ASPHALT MIX DESIGN REQUIREMENTS

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| Stability, pounds | 1800 min. | 1200 min. |
| Flow, 0.01 inch | 8-14 | 8-16 |
| Voids in Total Mix, % | 3-5 | 3-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 |
| Percent Voids Filled with Asphalt (VFA) | 65-75 | 65-78 |
| Minimum Asphalt Cement Content, ( % ) | 5.0 | 5.0 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |
| Type I Type II Type III, IV | 12.0 13.0 14.0 | 11.0 12.0 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt (calculated by weight of mix).

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broad band limits shown in Table 703-3, for the type of hot mix asphalt specified. For acceptance testing, hot mix asphalt will have the full tolerance limits in Table 401-2 applied. Except for the No. 200 sieve, the tolerance limits will apply even if they fall outside the broad band shown in Table 703-3. The tolerance limits for the No. 200 sieve will be confined by the broad band shown in Table 703-3. Tolerance limits will not be applied to the largest sieve specified.

- Do not produce hot mix asphalt for payment until the Engineer approves the Job

Mix Design. Do not mix hot mix asphalt produced from different plants. Use Hot Mix Asphalt Type II, Class B, minimum, for temporary pavement.

Submit the following to the Engineer at least 15 days before the production of hot mix asphalt:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the  blend ratio of each aggregate stockpile. The proposed gradation must meet the requirements of Table 703-3 for each type of hot mix asphalt specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the hot mix asphalt. Include name of product, manufacturer, test results of the applicable quality of Subsection 702-2.01, manufacturer's certificate of compliance per Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate type and class of hot mix asphalt specified, and establish the approved Job Mix Design which will become a part of the Contract.

The Engineer will assess a fee of $2,500 as a part of the Asphalt Price Adjustment, for each mix design subsequent to the approved Job Mix Design for each Type and Class of Hot Mix Asphalt specified.

No payment for hot mix asphalt for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved. Approved changes apply only to hot mix asphalt produced after the submittal of the changes.

Changes. Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design. Submit changes and new samples in the same manner as the original submittal.

401-2.02 AGGREGATES. Conform to Subsection 703-2.04, Aggregate for Hot Mix Asphalt.

Use a minimum of three stockpiles for crushed hot mix asphalt aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in separate piles.

401-2.03 ASPHALT CEMENT. Provide the grade of asphalt cement specified in the Contract meeting the applicable requirements of Section 702, Asphalt Materials. If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 prior to delivery to the project. Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturer’s certificate of compliance (106-1.05).

2.	Conformance test reports for the batch (Section 702).

3.	Batch number and storage tanks used.

3.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of asphalt cement loaded.

6.	Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design. At least 70% of the aggregate must remain coated when tested according to ATM 414.

401-2.05 PROCESS QUALITY CONTROL. Sample and test materials for quality control of the hot mix asphalt according to Subsection 106-1.03, Testing and Acceptance. Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits your right to a retest under Subsection 401-4.02, Acceptance Sampling and Testing.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations. Address the sequence of operations and joint construction. Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the hot mix asphalt. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

- CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS. Do not place the hot mix asphalt on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix. Do not place  hot  mix  asphalt  unless  the  roadway  surface  temperature  is  40  °F  or warmer.

401-3.02 EQUIPMENT, GENERAL. Use equipment in good working order and free of hot mix asphalt buildup. Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of hot mix asphalt.

401-3.03 ASPHALT MIXING PLANT. Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before hot mix asphalt production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the hot mix asphalt.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

- Provide aggregate and asphalt cement sampling conditions meeting OSHA

safety requirements.

401-3.04 HAULING EQUIPMENT. Haul hot mix asphalt in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent. Do not use petroleum fuel as an asphalt release agent.

- Cover the hot mix asphalt in the hauling vehicle, when directed.

401-3.05 ASPHALT PAVERS. Use self-propelled units equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices. Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system. Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation. Equip the hopper with a distribution system to place the hot mix asphalt uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the hot mix asphalt.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous plant mix when that mix is carried from the paver hopper back to the paver augers. The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified bituminous pavers:

1.	Blaw-Knox bituminous pavers shall be equipped with the Blaw-Knox Materials Management Kit (MMK).

2.	Cedarapids bituminous pavers must have been manufactured in 1989 or later.

3.	Caterpillar bituminous  pavers shall be equipped with deflector plates.

- The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Operate rollers according to manufacturer's instructions. Avoid crushing or fracturing of aggregate. Use rollers designed to compact hot mix asphalt and reverse without backlash.

- Use fully-skirted pneumatic-tire rollers with a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE. Prepare existing surfaces in conformance with the Plans and Specifications. Prior to applying tack coat to the existing surface, clean out loose material from cracks in existing pavement wider than 1 inch in width full depth then fill using asphalt concrete tamp in place. Clean, wash, and sweep existing paved surfaces of loose material.

- Preparation of a milled surface,

•	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than ½-inch with Asphalt Concrete, Type IV.

No density testing is required for the leveling course material. The Engineer will inspect and accept this material.

•	If planing breaks through existing pavement remove 2 inches of existing base and fill with Asphalt Concrete, Type II, Class B. Notify the Engineer of pavement areas that might be considered thin or unstable during pavement removal.

Existing surface must be approved by the Engineer before applying tack coat. Clean existing paved surfaces of loose material.

Prior to placing the hot mix asphalt, uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material meeting Section 402.

Allow prime coat to cure and emulsion tack coat to break before placement of hot mix asphalt on these surfaces.

401-3.08 PREPARATION OF ASPHALT CEMENT. Provide a continuous supply of asphalt cement to the asphalt plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the hot mix asphalt, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the hot mix asphalt to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate. Hot mix asphalt containing soot or fuel is considered unacceptable per Subsection 105-1.11, Removal of Unacceptable and Unauthorized Work.

401-3.10 MIXING. Combine the aggregate, asphalt cement and additives in the mixer in the amounts required by the Job Mix Design. Mix to obtain 98% coated particles when tested according to AASHTO T 195.

- For batch plants, put the dry aggregate in motion before addition of asphalt cement.

- Mix the hot mix asphalt within the temperature range determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE. Silo type storage bins may be used, provided that the characteristics of the hot mix asphalt are not altered. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the hot mix asphalt are causes for rejection.

401-3.12 PLACING AND SPREADING. Place the hot mix asphalt upon the approved surface, spread, strike off, and adjust surface irregularities. Use asphalt pavers to distribute hot mix asphalt, including leveling courses.

During placement, the Engineer may evaluate the hot mix asphalt immediately behind the paver for temperature uniformity. Areas with temperature differences more than 25oF lower than the surrounding hot mix asphalt are likely to produce areas of low density. Any thermal images and/or thermal profile data will become part of the project record and shared with the Contractor.

- The Contractor shall immediately adjust his laydown procedures to correct the problem.

Use hand tools to spread, rake, and lute the hot mix asphalt in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours. Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

- Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Place hot mix asphalt over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly compact the hot mix asphalt by rolling. In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

The target value for density is 95% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209. For the first lot of each type of hot mix asphalt, the MSG will be determined by the Job Mix Design. For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed in accordance with WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core. (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on hot mix asphalt that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Minimize the number of joints. Place and compact the hot mix asphalt to ensure a continuous bond, texture, and smoothness between adjacent panels of hot mix asphalt.

Remove full depth improperly formed joints resulting in surface irregularities, replace with new hot mix asphalt, and thoroughly compact. Precut all pavement removal to a neat line with a power saw, or other method approved by the Engineer.

Form transverse joints by saw-cutting back on the previous run to expose the full depth of the layer with a power saw or other method approved by the Engineer, or use a removable bulkhead.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches. Align the joints of the top layer at the centerline or lane lines. Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 12 inches from the edge of the stripe.

Uniformly coat all joint surfaces below the final lift with tack coat conforming to Section 703, Aggregates, prior to placing any fresh HMA against the joint.

Before placing an adjacent panel of hot mix asphalt to form a joint in the top layer, apply Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal, to the edge of the existing panel. Edge surface preparation, application temperature, thickness, and method shall be per manufacturer’s recommendations.

For the top layer of hot mix asphalt, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint. Cut one 6-inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing. Density will be determined in accordance with WAQTC FOP for AASHTO T 166/T 275.

In the top layer, seal the longitudinal joints with Asphalt Systems GSB-78, or approved equal, while the hot mix asphalt is clean, free of moisture, and before traffic marking. Longitudinal joint sealing shall be per the manufacturer’s recommendations and an application rate of 0.15 gallons per square yard. Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150° F. These joints do not need to be tacked and will be measured and evaluated for joint density.

- Longitudinal joints will be evaluated for acceptance in accordance with 401-4.05.

401-3.15 SURFACE TOLERANCE. The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge. Correct variations from the testing edge, between any two contacts, of more than 1/4 inch.

The Engineer will measure the surface smoothness of the top layer of asphalt concrete pavement in the driving lanes with an inertial profiler before final acceptance of the project. Remove and replace, or grind smooth any area of final pavement surface that does not meet straight edge tolerances. All costs associated with meeting surface tolerances are subsidiary to the Asphalt Concrete pay item.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment. No measurements will be taken in turn lanes, lane transitions, or within 25 feet of the existing pavement at the project beginning and end.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph results (PrI) filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

401-3.16 PATCHING DEFECTIVE AREAS. Remove any hot mix asphalt that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective. Do not skin patch. Remove defective hot mix asphalt for the full thickness of the course. Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic. Coat edges with a tack coat meeting Section 402 and allow to cure. Place and compact fresh hot mix asphalt per Subsection 401-3.13 to grade and smoothness requirements.

- All costs associated with patching defective areas are subsidiary to the Hot Mix Asphalt pay item.

401-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of each class and type of hot mix asphalt produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons. The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation according to this Subsection. If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot. The price adjustment computed, according to Subsection

401-4.03, Evaluation of Materials for Acceptance, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be  based on  the  actual number of test results (excluding outliers) in the shortened lot.

If the Plan quantity is between 1,500 tons and 4,999 tons, the Plan quantity will be considered one lot. The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this Subsection except that a determination for outliers will not be performed. Hot mix asphalt quantities of less than 300 tons remaining after dividing the Plan quantity into sublots will be included in the last sublot. Hot mix asphalt quantities of 300 tons or greater will be treated as an individual sublot. The lot will be evaluated for price adjustment according to Subsection 401-4.03 except as noted.

For Plan quantity of less than 1,500 tons (and for temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance. Remove and replace any hot mix asphalt that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer. The Engineer will take immediate possession of the samples.

1.	Asphalt Cement Content. Hot mix asphalt samples taken solely for the determination of asphalt cement content will be taken randomly from behind the screed prior to initial compaction, at the end of the auger, or from the windrow according to WAQTC FOP for AASHTO T 168, as directed by the Engineer. Hot mix asphalt samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed prior to initial compaction according to WAQTC FOP for AASHTO T 168.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. At the discretion of the Engineer, asphalt cement content will be determined in accordance with ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants. Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2, or from the same location as samples for the determination of asphalt cement content. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11. For hot mix asphalt samples, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum. Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the hot mix asphalt.

b.	Batch Plants. Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates in accordance with WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. Dry batched aggregate gradations will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11. For hot mix asphalt samples, the aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density. Cut full depth core samples from the finished hot mix asphalt within 24 hours after final rolling. Neatly cut one 6-inch diameter core sample with a core drill at each location marked by the Engineer. Cut six- inch diameter core samples for assurance testing as directed by the Engineer. Use a core extractor to prevent damage to the core. The Engineer will determine the density of the core samples in accordance with WAQTC FOP for AASHTO T 166/T 275. Do not core hot mix asphalt on bridge decks. Backfill and compact all voids left by coring with new hot mix asphalt within 24 hours.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day. Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day. The accrued amount will be subtracted as part of the Asphalt Price Adjustment.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location the panel completing the joint is cored for mat density acceptance testing.

4.	Retesting. A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result. The Engineer will mark the sample location for the density retest within a two-foot radius of the original core. The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample is allowed. Except for the first lot, when gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement content from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for the MSG.

5.	Asphalt Cement. The lot size for asphalt cement will normally be 200 tons. If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot. If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 199 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated in accordance with this subsection. Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled in accordance with WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, Asphalt Materials, and evaluated for price adjustment in accordance with Subsection 401-4.03, Evaluation of Materials for Acceptance. Asphalt cement pay reduction factors for each sample will be determined from Table 401-4. Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

The total asphalt cement price adjustment is the sum of the individual lot price adjustments and will be subtracted as part of the Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. The following method of price adjustment will be applied to each type of Hot Mix Asphalt for which the contract quantity equals or exceeds 1,500 tons, except as specified in Subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03, Testing and Acceptance, to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lowest of two pay factors. The first factor is a  composite  pay  factor  for  hot  mix  asphalt  which  includes  gradation  and asphalt cement content. The second factor is for density.

A lot containing hot mix asphalt with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer. A lot containing hot mix asphalt that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject hot mix asphalt which appears to be defective based on visual inspection. A minimum of two samples will be collected from the rejected hot mix asphalt and tested if requested. If all test results are within specification limits, payment will be made for the hot mix asphalt. If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as part of the Asphalt Price Adjustment. All costs associated with removal and disposal of the rejected hot mix asphalt are subsidiary to the Hot Mix Asphalt pay item.

Outlier Test. Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any sieve size on the gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier also. If  the  density test result is an outlier, the density test result will not be included in the price adjustment, however, the gradation and asphalt cement content results for the sublot will be included provided neither is an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment. The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier. If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier. If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean (x) of the remaining test results is determined:

Σ x

x  =

n

Where:	Σ 	= 	summation of

x	= 	individual test value to x n

n 	= 	total number of test values

x is rounded to the nearest tenth for density and all sieve sizes except the No. 200 sieve. x is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:	(x2)	=	sum of the squares of individual test values.

(x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed. For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2. The TV is the specification value specified in the approved Job Mix Design. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing PWL calculations. The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 100%.

- TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV-6.0 | TV+6.0 |
| 1/2 inch sieve | TV-6.0 | TV+6.0 |
| 3/8 inch sieve | TV-6.0 | TV+6.0 |
| No. 4 sieve | TV-6.0 | TV+6.0 |
| No. 8 sieve | TV-6.0 | TV+6.0 |
| No. 16 sieve | TV-5.0 | TV+5.0 |
| No. 30 sieve | TV-4.0 | TV+4.0 |
| No. 50 sieve | TV-4.0 | TV+4.0 |
| No. 100 sieve | TV-3.0 | TV+3.0 |
| No. 200 sieve1 | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.4 | TV+0.4 |
| Mat Density % | 92 | 100 |

Note 1. Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:	 QU

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:	 QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined. See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined. See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor is determined for Density (DPF) and gradation and asphalt cement content pay factors (PF) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

- The CPF is rounded to the nearest hundredth.

- Table 401-3 gives the weight factor (f) for each sieve size and asphalt cement content.

- TABLE 401-3

WEIGHT FACTORS

| Sieve Size | Type I | Type II | Type III |
| --- | --- | --- | --- |
|  | Factor “f” | Factor “f” | Factor “f” |
| 1 inch sieve | 4 |  |  |
| 3/4 inch sieve | 4 | 4 |  |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value. The price adjustment for each individual lot will be calculated as follows:

- Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower.

- PAB = Price Adjustment Base = $110 per ton

- TABLE 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  | Spec | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | <3 Pa-s | <3 |  | >3 |  |  |  |  |  |  |
| Dynamic Shear | >1.00 kPa | >1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.87 | 0.50-0.70 | <0.50 |
| Toughness | >110 in-lbs | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | <70.0 |
| Tenacity | >75 in-lbs | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | <48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | <1.00 % | <1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | >1.276 |
| Dynamic Shear | >2.20 kPa | >2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | <1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | <5000 kPa | <5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | >5867 |
| Creep Stiffness, S | <300 MPa | <300 |  | 301-338 |  |  |  | 339-388 | 389-450 | >450 |
| Creep Stiffness, m-value | >0.300 | >0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | <0.261 |
| Direct Tension | >1.0 % | >1.0 |  | 0.86-0.99 |  |  |  | 0.71-0.85 | 0.56-0.70 | <0.56 |

- Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty X PRF

- PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure. Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal. The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question). The Engineer will review these test results and using ASTM D3244 determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing. This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction. If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot and will be subcontracted from the Contract price.

401-4.05 EVALUATION OF LONGITUDINAL JOINTS FOR ACCEPTANCE. Longitudinal joint density price adjustments apply when hot mix asphalt quantities are equal to or greater than 1,500 tons.

A longitudinal joint density price adjustment for the top layer will be based on the average of the joint densities for the project and determined as follows:

1.	If the project average joint density is less than 91% of MSG, the following disincentives apply:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted from the Contract price.

## SECTION 402

## TACK COAT

402-1.01 DESCRIPTION. Apply an asphalt tack coat on an approved surface.

402-2.01 MATERIALS. Use materials that conform to the following:

Asphalt	Section 702 (STE-1)

- CONSTRUCTION REQUIREMENTS

402-3.01 WEATHER LIMITATIONS. Do not apply tack coat to a wet surface or when the roadway surface temperature is below 40 F.

402-3.02 EQUIPMENT. Furnish, maintain, and operate asphalt distributor to apply asphalt material uniformly at even heat on variable widths of surface up to 15 feet at readily determined and controlled rates from 0.01 to 0.11 gallon per square yard, with uniform pressure, and with an allowable variation from any specified application rate not to exceed 0.02 gallon per square yard. Equip with a heater, tachometer, pressure gauges, calibrated tank, thermometer for measuring temperatures of tank contents, power unit for the pump and full circulation spray bars adjustable laterally and vertically.

402-3.03 PREPARATION OF SURFACE TO BE TREATED. Clean and patch the existing surface to receive the treatment. Remove irregularities to provide a reasonably smooth and uniform surface. Remove and replace unstable corrugated areas with suitable patching materials. Clean the edges of existing pavements, which are to be adjacent to new pavement, to permit the adhesion of asphalt materials.

402-3.04 APPLICATION OF ASPHALT MATERIAL. Apply tack coat uniformly with a pressure distributor at a rate of 0.04 to 0.10 gallon per square yard, as directed.

Apply the tack coat in such a manner as to offer the least inconvenience to traffic and to permit one-way traffic without pickup or tracking of the asphalt material.

- Limit application of tack coat so it will be covered by paving within one day.

## SECTION 403

## PRIME COAT

403-1.01 DESCRIPTION. Construct an asphalt prime coat on an approved surface. Apply blotter material, if required.

403-2.01 MATERIALS. Use materials that conform to the following:

Asphalt	Section 702 (MC-30, CSS-1)

Blotter Material	Suitable clean sand

- CONSTRUCTION REQUIREMENTS

403-3.01 WEATHER LIMITATIONS. Do not apply asphalt material to a wet surface, or when the surface temperature is below 45 F, or when weather conditions would prevent the proper penetration of the prime coat.

403-3.02 EQUIPMENT. A distributor meeting Subsection 402-3.02. An approved self-propelled aggregate spreader and rotary paver broom.

403-3.03 PREPARATION OF SURFACE. Ensure that surface to be primed is shaped to the required grade and section, free of ruts, corrugations, segregated material or other irregularities, and uniformly compacted.

403-3.04 APPLICATION OF ASPHALT MATERIAL. Before prime coat application, obtain approval of rate of application, temperature, and areas to be treated, from the Engineer.

When CSS-1 Emulsified Asphalt is specified, dilute with an equal amount of potable water at a temperature between 50 and 120 F and mix for a minimum of 15 minutes before using.

Apply asphalt material to the width of the section to be primed by means of a pressure distributor in a uniform, continuous spread. Do not exceed maximum application rate at overlaps. Squeegee excess asphalt material from the surface. Correct any skipped areas or deficiencies. Place building paper over the end of the previous applications and start the joining application on the building paper. Remove and dispose of used building paper.

When road is open to traffic, treat not more than 1/2 of the width of the section in one application. Maintain traffic on the untreated portion of the roadbed. As soon as the asphalt material has been absorbed by the surface and will not pick up, traffic may be transferred to the treated portion and the remaining width of the section primed.

- Maintain the surface until the next course has been placed. Protect the surface against damage.

403-3.05 APPLICATION OF BLOTTER MATERIAL. If, after the application of the prime coat, the asphalt material fails to penetrate and dry, and traffic must be routed over the primed surface, or rain is imminent, apply blotter material as directed.

- Do not apply blotter material sooner than 4 hours after application of the asphalt material.

## SECTION 404

## SEAL COAT

404-1.01 DESCRIPTION. Construct a seal coat on an approved surface, with or without cover coat material, as specified.

404-2.01 MATERIALS. Use materials that conform to the following, for the type and grade specified:

Asphalt	Section 702

Cover Coat Aggregate	Subsection 703-2.05

- CONSTRUCTION REQUIREMENTS

404-3.01 WEATHER LIMITATIONS. Do not apply asphalt material to a wet surface, or when the surface temperature is below 60 °F, or when weather conditions would prevent the proper penetration and adhesion of the cover aggregate.

404-3.02 EQUIPMENT. Use the following equipment, or its approved equivalent:

1.	Distributor. Conform to Subsection 402-3.02.

2.	Broom. A rotary power broom or power vacuum sweeper.

3.	Rollers. A minimum of two self-propelled pneumatic tired rollers having gross loads adjustable to apply 200 to 350 pounds per inch of rolling width as directed. Tire pressure or contact pressure may be specified for pneumatic tire rollers. Operate pneumatic tire rollers at a maximum speed of 5 mph.

4.	Spreader. One self-propelled aggregate spreader of approved design supported by at least 4 wheels equipped with pneumatic tires on two axles.

404-3.03 PREPARATION OF SURFACE. Clean the roadway surface of all loose material immediately before applying asphalt.

404-3.04 APPLYING ASPHALT MATERIAL. Apply asphalt material to an approved surface by means of a pressure distributor in a uniform, continuous spread and within the temperature range specified.

Apply asphalt material at the rate specified. If the surface texture is such that asphalt material penetrates the surface, a preliminary application of 0.05 to 0.10 gallon per square yard of surface may be required.

Use building paper at the beginning of each spread. Remove and dispose of used building paper. Open the spray bar only when the distributor is moving forward at proper application speed. Correct any skipped areas or deficiencies. Do not exceed maximum application rate at overlaps.

Suspend spreading asphalt material early enough in the day to permit the termination of traffic control prior to darkness. Apply asphalt material to only one designated traffic lane at a time. Cover the entire width of the lane in one operation.

Spread the asphalt material not more than 6 inches wider than the width covered by the cover coat material. Do not allow asphalt material to chill, set up, or dry.

- Do not allow the distributor to drip on the surface of the traveled way.

404-3.05 APPLICATION OF COVER COAT MATERIAL. Moisten the cover coat material with water the day before the aggregate is to be used. Spread the aggregate at a surface dry or slightly damp condition.

Aggregate may be accepted in the stockpile at the source. Gradation will be determined by WAQTC FOP for AASHTO T 27/T 11.

Immediately following asphalt material application, spread the specified quantity of cover coat material. Do not allow truck or aggregate spreader tires to contact the wet asphalt material.

Cover any deficient areas with additional material immediately after the cover coat material is spread. Begin rolling immediately for the full width of the aggregates, and continue until 3 complete coverages are obtained. Complete pneumatic tire rolling the same day the asphalt and cover coat materials are applied.

After the application of the cover coat material, lightly broom the surface and maintain for a period of 4 days or as directed. Maintenance of the surface includes the distribution of cover coat material over the surface to absorb any free asphalt material. Do not displace imbedded material. Sweep excess material from the entire surface by means of rotary brooms at the time directed.

When applying asphalt material without a cover coat, begin rolling the asphalt material immediately upon application and continue until there is no evidence of kneading action. Make at least one complete roller coverage of the road surface.

Do not permit traffic on the seal coat until rolling is completed. Control traffic on seal coats by pilot cars at a speed not to exceed 15 mph for a period of 2 to 24 hours, as directed.

## SECTION 405

## SURFACE TREATMENT

405-1.01 DESCRIPTION. Construct a single or multiple course asphalt surface treatment.

405-2.01 MATERIALS. Use materials that conform to the following:

Asphalt		Section 702, for the type and grade specified

Surface Treatment Aggregate	Subsection 703-2.05, for the grading specified

Blotter Material		Suitable clean sand

- CONSTRUCTION REQUIREMENTS

405-3.01 PRIME COAT. Apply prime coat, when specified, per Section 403, Prime Coat.

Allow a curing period of up to 4 days between the application of the prime coat and the next application of asphalt material, as directed.

Maintain the primed surface during the curing period. Repair all holes, ravels and areas deficient in prime with asphalt treated materials, by penetration methods, or other approved procedures.

405-3.02 SURFACE TREATMENT. Apply each course (asphalt and surface treatment aggregate per Section 404, Seal Coat. Allow each course to cure for a period of 4 days before applying additional courses.

Surface treatment aggregate may be accepted in stockpile at the source. Gradation will be determined by WAQTC FOP for AASHTO T 27/T 11.

405-3.03 OPENING TO TRAFFIC. Keep the highway open to traffic at all times. As soon as the final layer is rolled, controlled traffic may be permitted as specified under Subsection 404-3.05.

## SECTION 406

## RUMBLE STRIPS

406-1.01 DESCRIPTION. Form a series of indentations (rumble strips) into the roadway pavement. Place rumble strips in each shoulder and the roadway centerline to the width, depth and length as indicated in the Contract documents.

406-1.02 RUMBLE STRIP. A single uniform circular concave (cross section) indentation/depression milled into the pavement surface having a length measured perpendicular to the direction of travel, a width measured in the direction of travel and a depth measured from the surface of the pavement to the bottom of the indentation.

406-2.01 MATERIALS. None.

406-2.02 MILLING EQUIPMENT. Use equipment designed specifically for milling rumble strips into asphalt pavement. Equip milling machine with a rotary type cutting head with a maximum outside diameter of 24 inches and a minimum length of 16 inches capable of producing a depression both 12 inches and 16 inches in length by 7-1/2 inches in width to a depth shown in the Plans. Arrange the cutting tips to provide a smooth cut (approximately 1/16 inch between peaks and valleys).

Furnish the milling equipment with a guidance system, including a guide, clearly visible to the operator, to provide for consistent alignment of each rumble strip cut at the offsets from traveled way indicated on the Plans and to provide uniformity and consistency throughout the project.  The equipment shall incorporate water into the cutting head to minimize dust caused by the milling operation.

Equipment Manufacture: provide training for the operators and a representative onsite during installation of the rumble strip test section(s) (Subsection 406-3.03). Representative: remain onsite until test specimen(s) satisfy the Plans and Specifications as determined by the Engineer.

406-3.01 PAVEMENT SURFACE PREPARATION. Inspect roadway to receive rumble strips for acceptable pavement condition and stake locations to receive rumble strips prior to installation. Prepare the roadway for the milling operation by providing a smooth clean surface. Sweep all loose material from the roadway surface in line with the planned rumble strips and to each side of the strips for the width of the milling machine plus an additional 12 inches minimum per side or edge of pavement whichever is smaller, and as directed by the Engineer.

406-3.02 TOLERANCES FOR RUMBLE STRIPS.

1.	Length:   1/2 inch.

2.	Width:  1/2 inch.

3.	Depth:  1/16 inch.

4.	Spacing:   1/2 inch.

5.	Alignment:  1 inch from the striping layout in the Plans; existing striping and re-established striping.

If it is determined that the rumble strips are not being placed to specification, make immediate adjustments to correct the problem.

Rumble strips are unacceptable if:

1.	The strips are not straight.

2.	The length or width does not meet tolerance.

3.	The depth of the depression does not meet tolerance.

4.	The depression/indentation concave surface is not smooth, does not meet tolerance.

5.	The edge of the indentation/depression is not straight, smooth, and free of spalling.

6.	Pavement surface is damaged as a result of improper rumble strip installation.

Unacceptable rumble strip installation, dimensional, alignment, surface irregularities, and surface damage shall be ground, resurfaced and the rumble strip reinstalled to the satisfaction of the Engineer and at the Contractor’s expense. Perform repairs using equipment similar to the equipment initially used to mill the rumble strip. Do not perform repairs in a “patch work” manner. If more than one repair is required; in a group of rumble strips repair the entire group. Where a repair is required in a continuous run, repair the unacceptable rumble strip(s) and repair or replace the rumble strip to each side of the unacceptable rumble strip as required to provide continuity between rumble strips as originally intended. The Engineer will confirm the extent of the repair(s) required.

If during production the work becomes unacceptable the Engineer may require resumption of testing, Subsection 406-3.03. Testing in addition to the initial test for each rumble strip type will be at the Contractor’s expense.

406-3.03 RUMBLE STRIP TEST SECTION. Install an initial 1/4 mile test section for each of the following rumble strip type(s):

1.	Shoulder.

2.	Centerline.

Demonstrate for each type of rumble strip that the equipment and method will provide the desired milled-in rumble strip, including the surface inside each depression, without damaging the surrounding asphalt pavement.  If any of the initial test sections do not meet tolerances, provide new equipment, new method, or make necessary adjustments and retest. These additional test sections will be required before production runs will be allowed to begin.

Testing in addition to the initial test sections, one for the shoulder type and one for the centerline type, will be at the Contractor’s expense.

Additionally, demonstrate the means and methods, including the equipment, for containing dust and waste material.

406-3.04 TRAFFIC STRIPING RE-ESTABLISHMENT. Traffic striping is required to provide guidance for the rumble strip installation operation. Contractor, where shoulder and/or centerline striping is missing to the extent that rumble strip location cannot be determined by the Engineer, re-establish the striping location prior to the milling operation. Re-establish missing striping location by measuring laterally across the roadway from adjacent visible striping. Maintain the same lane widths that exist at each end of the missing striping. Provide sufficient location marking or “rabbit tracks” to ensure an accurate milling operation. Shoulder re-striping is not required.

406-3.05 RUMBLE STRIP INSTALLATION. Install the following types of rumble strip at the locations shown in the Plans:

1.	Shoulder. Do not disturb existing shoulder striping.

2.	Centerline. Place along the roadway centerline according to the patterns shown in the Plans. Replace existing centerline stripe(s) after milling the pavement.

In compacted pavement with a temperature below 80˚ F, mill each type of rumble strip to the dimensions shown in the Plans. Locate the inside edge of the rumble strip as shown in the Plans. The Engineer will randomly check the edge alignment of the milled pattern.

406-3.06 CLEAN UP OF MILLINGS. Handle, transport, and store, or dispose of material according to the Alaska Department of Environmental Conservation (DEC) regulations. Remove off the project, on a daily basis, waste material (millings) resulting from the operation.

Disposal: Dispose waste material outside the project limits, unless directed otherwise, in writing, by the Engineer. Obtain written consent from the property owner. Milled material not being spread on the roadway side slopes requires a Solid Waste Disposal Permit from the DEC. Obtain a permit for disposal of milled material or dispose the material in a site previously approved.

Remove millings immediately following rumble strip installation. Maintain the removal operation within 50 feet of the milling machine. Dry power brooming and power brooming without direct immediate means of collection/pickup is not permitted.

During milling operations keep the travel lanes free of milling debris. Do not berm the millings at the shoulder edge, do not allow milling debris to impede roadway drainage or enter waterways. Use a sweeper, sweeper/vacuum, (Subsection 643-3.04 No. 6, Street Sweeping, and Power Brooming), continuously removing waste material, including dust from the operation. Keep millings damp to help control airborne dust. Millings shall not enter adjacent lanes open to traffic.

Remove the waste material from the roadway surface and any adjacent pathway beyond the shoulder. Shoulder millings may be placed off of the road or pathway beyond the shoulder on the side slopes, except in areas where guardrail is present. Uniformly spread shoulder millings on the roadway side slopes; alternatively, it may become property of the Contractor and disposed of off the project as indicated above.

- Milled roadway segments shall be returned to debris-free state prior to re-opening for traffic.

## SECTION 408

## HOT MIX ASPHALT AND SURFACE TREATMENTS TYPE V (SUPERPAVE)

408-1.01 DESCRIPTION. Construct one or more layers of plant-mixed hot mix asphalt (HMA) on an approved surface, to the lines, grades, and depths shown on the Plans.

1.	In this Section HMA refers to Type V, except where noted otherwise.

a.	Use of Recycled Asphalt Pavement (RAP) is not permitted in HMA.

b.	Warm Mix Asphalt (WMA) is not permitted in HMA.

408-1.02 REFERENCE.

1.	Section 401, Hot Mix Asphalt and Surface Treatments.  HMA, Type I, II, III, and IV.

a.	Temporary Asphalt Pavement:  HMA, Type II, Class B, minimum.

b.	Preleveling/Leveling Course:  HMA, Type IV, Class B.

- MATERIALS

408-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN (JMD). Design the JMD according to AASHTO R35 using the design requirements of Table 408-1, except evaluate the moisture sensitivity using the Alaska Test Manual (ATM) 414 and not AASHTO T 283.

- TABLE 408-1

HMA Design Requirements

| DESIGN PARAMETERS |  |
| --- | --- |
| Design ESALs, Millions | 0.3 to < 3 |
| Rut Index, Max., ATM 419 | 3 |
| Asphalt Cement Content, Min. % | 5.0 |

The JMD will specify the Target Values (TV) for gradation, the TV for asphalt cement content, the Maximum Specific Gravity (MSG) of the HMA, the additives, and the allowable mixing temperature range.

Target values for gradation in the JMD must be within the broad band limits shown in Table 703-3, for the Type of HMA specified. For acceptance testing, HMA mixture will have the full tolerances in Table 408-2 applied. The tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3, except the tolerance limit of the No. 200 sieve is restricted by the broad band limits. Tolerance limits will not be applied to the largest sieve specified.

Do not mix HMA produced from different plants for testing or production paving. HMA from different plants will be rejected.

Submit the following to the Engineer at least 15 days before the production of HMA:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the JMD, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile. The proposed gradation must meet the requirements of Table 703-3 for each type of HMA specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1 gallon samples of the asphalt cement proposed for use in the HMA. Include name of product, manufacturer, test results of the applicable quality requirements of Subsection 702-2.01, manufacturer's certificate of compliance according to Subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will evaluate the material and the proposed gradation using the requirements of Table 408-1 for Type V Hot Mix Asphalt. The mix, the materials and proposed gradation meeting the specification requirements will become part of the Contract when approved, in writing, by the Engineer.

The Engineer has the option to require further verification of the JMD. Evaluation of the JMD may be included in the Process Quality Controls, Supplemental Process Quality Controls, Subsection 408-2.05, Test Strip construction.

- FAILURE TO MEET SPECIFICATION REQUIREMENTS

Submit a new JMD with changes noted and new samples in the same manner as the original JMD when:

	The results do not achieve the requirements specified in Table 408-1

	The asphalt cement source is changed

	The source of aggregate, aggregate quality, gradation, or blend ratio is changed

	The results of a Test Strip do not meet the requirements of the specification – the Engineer may require a new JMD.

Do not produce HMA for production paving and payment before the Engineer provides written approval of the JMD, the original or a new replacement JMD. If a Test Strip(s) is required, do not produce HMA for production paving and payment before the Engineer provides written approval of the Test Strip construction, construction process, the materials, and the JMD, Subsection 408-2.05.

Payment for HMA will not be made until the new JMD and the Test Strip, when required, is approved. Approved changes apply only to HMA produced after the submittal of changes.

The Engineer will assess a fee for each mix design subsequent to the approved Job Mix Design. The fee will be included under Item 408(6) Asphalt Price Adjustment – Quality.

408-2.02 AGGREGATES.  Conform to Subsection 703-2.04.

- Use a minimum of 3 stockpiles for crushed HMA aggregate (coarse, intermediate, and fine).

408-2.03 ASPHALT CEMENT.  Conform to 702-2.01.  If not specified, use PG 58-34.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project. Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket. The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.	Manufacturers certificate of compliance (Subsection 106-1.05).

2.	Conformance test results of the batch (provide prior to delivery as noted above)

3.	Batch number and storage tanks used.

4.	Date and time of load out for delivery.

5.	Type, grade, temperature, and quantity of materials loaded.

6.	Type and percent of anti-strip added.

408-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM 414 and included in the approved JMD. At least 70% of the aggregate shall remain coated when tested according to ATM 414. A minimum of 0.25% by weight of asphalt cement is required.

408-2.05 PROCESS QUALITY CONTROL. Sample and test materials for quality control of the HMA according to Subsection 106-1.03. Submit to the Engineer, with the JMD, a documentation plan that will provide a complete, accurate, and clear record of the sampling and testing results. When directed by the Engineer, make adjustments to the plan and resubmit.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations. Address the sequence of operations and joint construction.  Outline steps to provide product consistency, to minimize segregation, to prevent premature cooling of the HMA and to provide the mat and longitudinal density required by these specifications.  Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

- Failure to perform quality control forfeits the Contractor’s right to a retest under Subsection 408-4.02.

Provide copies of the documented sampling and testing results no more than 24 hours from the time taken.

- SUPPLEMENTAL PROCESS QUALITY CONTROL

The Engineer has the option to require supplemental process quality controls including additional sampling and testing. Include the supplemental process quality controls in the documentation plan.

- When directed by the Engineer; provide “Density Profiles” and or “Test Strips.”

1.	Density Profiles. Provide density profile testing, with a nuclear density gauge, of the mat and longitudinal joints. Include the frequency of the test groups, configuration of the test groups for mat density and joint density individually or combined. Indicate the number of tests in a test group intended to confirm the density of the mat and joints.

Locations that may require testing include: all lanes on bridge decks, adjacent to longitudinal joints, areas where segregation is visible, thermal segregation potential exists, where mat density is lower than the minimum (considered segregated), and the paver starts/stops. The Engineer will identify these and other areas that require density testing.

2.	Test Strips. Construct test strips (ATM 412) using the approved job mix HMA a minimum of 5 working days prior to planned production paving, except use the proposed JMD when the test strip is being constructed to help evaluate the JMD as part of the mix performance analysis. Submit a proposed test strip location to the Engineer for coordination, and approval; include in the process control documentation plan. The Engineers approval and written authorization of the location, date, and time, is required before construction of a test strip.

Establish roller patterns and the number of passes required to assure that proper placement and compaction is achieved. The test strip shall include no less than 300 tons and no more than 1000 tons, except as may be authorized, in writing, by the Engineer. The full complement of the paving train will be on site to receive instructions from the Engineer as needed to complete the mix performance analysis. Make the equipment available for inspection as required by Subsection 408-3.02. Provide an onsite process control representative with authority to modify mix components as instructed by the Engineer.

Only after the Engineer approves the test strip may HMA be produced for production paving and payment.

- CONSTRUCTION REQUIREMENTS

408-3.01 WEATHER LIMITATIONS. Do not place HMA on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix. Do not place HMA unless the roadway surface temperature is 40F or warmer. Do not place mix after September 15 unless approved by the Engineer in writing.

408-3.02 EQUIPMENT, GENERAL. Use equipment in good working order and free of HMA buildup. Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of production HMA, except when a test strip is required, 24 hours before placement of the test strip HMA.

408-3.03 ASPHALT MIXING PLANTS. Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates. Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before HMA production. Provide daily burner charts to the Engineer showing start/stop times and temperatures.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the HMA.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

- Provide aggregate and asphalt cement sampling equipment meeting OSHA safety requirements.

408-3.04 HAULING EQUIPMENT.

Vehicles/Equipment. Haul HMA in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

During HMA hauling activities, the hauling vehicle will have covers attached and available for use. Be prepared to demonstrate deployment of the cover when hauling material or empty. Illustrate the efficiency of deployment and how the materials are protected from the environment and the environment is protected from the materials. When directed by the Engineer cover the HMA in the hauling vehicle(s).

Roadway Maintenance. Daily inspect, remove/clean, and dispose of project materials deposited on existing and new pavement surfaces(s) inside and outside the project area including haul routes.

The inspection plan and method of removal/cleaning and disposal shall be submitted in writing to the Engineer and approved by the Engineer 5 days before initiating paving operations. Include alternatives, options to immediately correct deficiencies in the inspection plan and methods of removal/cleaning and disposal that may be discovered as the work is being performed.

The Engineer may require the Contractor to include a vehicle/equipment cleaning station(s), to be added at the project site and or at the plant, in the basic plan or as one of the corrective alternatives/options. At a minimum, the cleaning station will include the materials and means to:

1.	Spray truck tires with an environmental degradable release agent if mix adheres to tires before dumping in front of the paver.

2.	Clean off loose mix from gates, chains, and tires that might fall on the pavement of the haul route.

3.	Contain, collect and disposal of (1) and (2).

The Contractor is responsible for the inspection plan, the means, and methods used for removal/cleaning and disposal of fugitive materials/debris. The Contractor is responsible for the damage as a result of not removing these materials (to the roadway material and the users and others) and the damage to the roadway materials from the removal method(s). Approval does not change the Contractor's responsibility, nor add responsibility to the Department for this work.

Repair damage to the existing roadway materials (asphalt type) as a result of the fugitive materials or their removal as specified in Subsection 408-3.16 Patching Defective Areas.

408-3.05 ASPHALT PAVERS. Use self-propelled asphalt pavers having a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices. Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation and a distribution system to place the HMA uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving, or displacing the HMA.

Equip the paver with a means of preventing segregation of the coarse aggregate particles from the remainder of the HMA when carried from the paver hopper back to the augers. Use means and methods approved by the paver manufacturer. Means and methods may include chain curtains, deflector plates, or other similar devices or combination of devices. When required by the Engineer, provide a Certificate of Compliance that verifies the means and methods required to prevent segregation are being used.

408-3.06 ROLLERS. Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Avoid crushing or fracturing of aggregate. Use rollers designed to compact HMA mixtures and reverse without backlash.

All rollers shall have an attached infrared thermometer that measures and displays the surface temperature to the operator.

- Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

408-3.07 PREPARATION OF EXISTING SURFACE. Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to an existing paved surface, clean loose material from cracks for the depth of the cracks. Fill the cleaned cracks, wider than 1 inch, with an approved HMA tamped in place. Wash and or sweep the paved surface clean and free of loose materials.

Preparation of a milled surface:

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than 1/2 inch with HMA, Type IV. Compact the prelevel/leveling course using pneumatic-tire rollers. The Engineer’s approval of the material and material installation is required. The Engineer will inspect the material and material installation. Correct material and material installations identified by the Engineer as required by the Engineer for approval. Density testing is not required for the leveling course (prelevel) material, material installation.

	Where the planing equipment breaks through the existing pavement, remove 2 inches of existing base material depth and replace with Section 401 HMA; Type II, Class B. If Section 401 is not included in the project special provisions use the HMA Type specified for the immediate layer of HMA to be placed over the planed surface. Cold mix HMA prohibited. Repair work and materials are subsidiary to the HMA Pay Items.

- During the planing operation, notify the Engineer of pavement areas that may be thin or unstable.

Do not apply the tack coat material until the Engineer approves the existing surface including, not limited to; the existing paved surface, the milled surface, and a prior layer of HMA pavement.

Before placing the hot asphalt mix, apply tack coat material (Section 702) as specified here and in Section 402. Uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material. Allow tack coat to break before placement of HMA on these surfaces.

408-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

408-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the HMA, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

- Heat the aggregate for the HMA to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate. HMA containing soot or fuel is unacceptable (Subsection 105-1.11).

408-3.10 MIXING. Combine the aggregate, asphalt cement, and additives in the mixer in the amounts required by the JMD. Mix to obtain 98% coated particles when tested according to AASHTO T 195.

- For batch plants, put the dry aggregate in motion before addition of asphalt cement.

408-3.11 TEMPORARY STORAGE. Silo type storage bins may be used, provided the characteristics of the HMA remain unaltered. Changes in the JMD, visible or otherwise, are cause for rejection. Changes may include: visible segregation, heat loss, and the physical characteristics of the asphalt cement, lumpiness, or stiffness of the HMA or similar.

408-3.12 PLACING AND SPREADING. Use asphalt pavers to distribute HMA.  Place the HMA upon the approved surface, spread, strike off, and adjust surface irregularities. The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer, using an infrared camera, may evaluate the HMA surface immediately behind the paver for temperature uniformity. Areas with temperature differences more than 25o F lower than the surrounding HMA may produce areas of low density. Contractor shall immediately adjust laydown procedure to maintain a temperature differential of 25o F or less. Thermal images and thermal profile data will become part of the project record and shared with the Contractor.

Use hand tools to spread, rake, and lute the HMA in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours. Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

- Do not pave against new Portland cement concrete curbing until it has cured for at least 72 hours.

Do not place the final lift until curb and gutter, all types, are installed complete, except as approved by the Engineer.

- Place HMA over bridge deck membranes according to Section 508 and the manufacturer's specifications.

408-3.13 COMPACTION. Thoroughly and uniformly, compact the HMA by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers. Do not leave rollers or other equipment standing on HMA that has not sufficiently cooled to prevent indentation.

A mat area with density lower than 93% MSG is considered segregated and not in conformance with the requirements of the Contract. The work shall be deemed unacceptable by the Engineer according to Subsection 105-1.11 unless, the Engineer determines that reasonably acceptable work has been produced as permitted in Subsection 105-1.03.

The density TV is 96% of the MSG, as determined by WAQTC FOP for AASHTO T 209. The MSG of the JMD will be used for the first lot of each type of HMA. The MSG for additional lots will be determined from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core.

When directed by the Engineer, provide density profiles of the mat and longitudinal joints with a nuclear density gauge. Deliver the results of density tests to the Engineer at the time of the testing, in writing in the format detailed in the Quality Control Plan Subsection 408-2.05.

408-3.14 JOINTS. Minimize the number of joints.  Do not construct longitudinal joints in the driving lanes unless approved by the Engineer in writing at the Pre-paving meeting. Place and compact the HMA to provide a continuous bond, texture, and smoothness between adjacent sections of the HMA.

Remove to full depth improperly formed joints resulting in surface irregularities. Before removing pavement, cut a neat, straight line along the pavement to be removed and the pavement to remain. Use a power saw or other method approved by the Engineer. Replace the removed asphalt with new HMA and thoroughly compact.

Form transverse joints by cutting back on the previous run to expose the full depth of the layer. Saw cut the joint, use a removable bulkhead or other method approved by the Engineer.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches. Align the joints of the top layer at the centerline or lane lines. Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

On the final lift, before paving against the longitudinal joint (completing the joint) uniformly coat the surface below the final lift with tack coat material conforming to Section 702. Coat the vertical edge of pavement (including milled edges) with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal. Apply a 1/8 inch thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

The Engineer shall evaluate the difference in elevation of the final surface of adjacent mats each side of the longitudinal joint, at the joint, with a straight edge and by requiring the Contractor to flood the joint surface with water. The Engineer will determine where and how often to evaluate the joint. All differences in the surface elevations greater than 1/8 inch or that pond water shall be repaired at no cost to the Department. Heat the HMA pavement to be repaired with an infrared heater (310˚ F max) and roll flat or add HMA until the joint differential is within tolerance.

For the top layer of HMA, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint. Cut one 6 inch diameter core centered on the longitudinal joint at each location that the panel completing the joint is cored for acceptance density testing. Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-88 or approved equal, while the HMA is clean, free of moisture, and before traffic marking. Longitudinal joint sealing shall be according to the manufacturer’s recommendations and a maximum application rate of 0.15 gallons per square yard. Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150°F. These joints do not need to be tacked and will not be measured or evaluated for joint density.

- Longitudinal joints will be evaluated for acceptance according to Subsection 408-4.03.

408-3.15 SURFACE TOLERANCE. The Engineer will test the finished surface after final rolling at selected locations using a 10-foot straightedge. Correct variations from the testing edge, between any two contacts, greater than 1/4 inch.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment. No measurements will be taken in turn lanes, intersections, ramps, and lane transitions, within 25 feet of the existing pavement or in areas where curb and gutter is left in place.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph (Prl) results filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

- Costs associated with meeting surface tolerances are subsidiary to the HMA pay item.

408-3.16 PATCHING DEFECTIVE AREAS. Remove HMA that is contaminated with foreign material, is segregated (determined visually or by testing), flushing or bleeding asphalt after compaction is completed or is in any way determined to be defective. Do not skin patch. Remove defective HMA for the full thickness of the course. Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic. Coat edges with a tack coat meeting Section 402 and allow to cure. Place and compact fresh HMA according to Subsection 408-3.13 to grade and smoothness requirements.

408-4.02 ACCEPTANCE SAMPLING AND TESTING. The total price adjustment is the sum of the individual lot price adjustments as determined in Subsection 408-4.03 Evaluation of Materials for Acceptance and is included in Item 408(6) Asphalt Price Adjustment-Quality. Penalties assessed are also included in Item 408(6).

A mat area of finished surfacing that is visibly segregated, has a lower density than specified (Subsection 408-3.13), fails to meet surface tolerance requirements, or is flushing asphalt cement is considered unacceptable according to Subsection 105-1.11.

- HOT MIX ASPHALT

The quantity of each class and type of HMA produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons. The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection. If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot. The price adjustment computed, according to Subsection 408-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5000 tons, the Contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed. HMA quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot. HMA quantities of 300 tons or greater will be treated as an individual sublot. The lot will be evaluated for price adjustment according to Subsection 408-4.03 except as noted.

For Contract quantity of less than 1,500 tons, (also for approaches) HMA will be accepted for payment based on the Engineer's approval of a JMD and the placement and compaction of the HMA to the specified depth and finished surface requirements and tolerances. The Engineer reserves the right to perform any testing required in order to determine acceptance. Remove and replace any HMA that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer. The Engineer will take immediate possession of the samples.

- The Engineer will determine where samples are taken.

1.	Asphalt Cement Content. Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403 as directed by the Engineer. HMA samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants. Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AASHTO T 2, or from the same location as samples for the determination of asphalt cement content. Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum. Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the HMA. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11. For HMA samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

b.	Batch Plants. Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable. Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11. For HMA samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.

a.	Acceptance Testing. The Engineer will determine and mark the location(s) where the Contractor will take each core sample. Core samples will not be taken at bridge decks or the milled edge of existing pavement.

1)	Mat Cores: The location(s) for taking core samples will be determined using a set of random numbers and the Engineer's judgment.

2)	Longitudinal Joint Cores: The Engineer will mark the location(s) to take the core sample, centered on the visible surface joint, and adjacent to the mat core sample taken in the panel completing the joint. Take joint core samples in the presence of the Engineer.

Cut full depth core samples, centered on the marks and as noted above, from the finished HMA within 24 hours after final rolling. Neatly core drill one six inch diameter sample at each marked location. Use a core extractor to remove the core - do not damage the core. Backfill and compact voids left by coring with new HMA within 24 hours.

The Engineer will immediately take possession of the samples. Density of the samples will be determined, by the Engineer, according to WAQTC FOP for AASHTO T 166/T 275.

A penalty will be assessed for each failure to take core samples or backfill core sample voids within the specified period, or take core samples at the location marked by the Engineer.

4.	Retesting. A retest of any sample outside the limits specified in Table 408-2 may be requested provided the quality control requirements of 408-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the final test of the lot. The Engineer will mark the sample for the density retest within a 2 foot radius of the original core. The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample is allowed. Except for the first lot, when gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

- ASPHALT CEMENT.

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot. If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the Contract quantity of asphalt cement is between 85 – 200 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection. Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 408-4.03. Asphalt cement pay reduction factors for each sample will be determined from Table 408-4. Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.

- HOT MIX ASPHALT

- The total Hot Mix Asphalt price adjustment is the sum of all price adjustments for each lot.

The following method of price adjustment will be applied to each type of HMA when the contract quantity equals or exceeds 1,500 tons, except as defined in Subsection 408-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in Subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors. The first factor is a composite pay factor for HMA that includes gradation and asphalt cement content. The second factor is for density.

A lot containing HMA with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer. A lot containing HMA that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under Subsection 105-1.11.

The Engineer will reject HMA that appears to be defective based on visual inspection. A minimum of two samples will be collected from the rejected HMA and tested if requested. If test results are within specification limits, payment will be made for the HMA. If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted as a price adjustment. Costs associated with removal and disposal of the rejected HMA are subsidiary to the Hot Mix Asphalt Pay Item.

Outlier Test. Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if a sieve size on the gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment. The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier. If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean () of the remaining test results is determined:

Where:	= summation of

x = individual test value to xn

n = total number of test values

is rounded to the nearest tenth for density and all sieve sizes except the No. 200 sieve.  is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:	(x2)	=	sum of the squares of individual test values.

(x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve. The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed. For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2. The TV is the specified value in the approved JMD. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing Percent Within Limits (PWL) calculations. The TV for density is 96% of the MSG and the LSL is 93% of MSG.

- TABLE 408-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV -6.0 | TV + 6.0 |
| 1/2 inch sieve | TV -6.0 | TV + 6.0 |
| 3/8 inch sieve | TV -6.0 | TV + 6.0 |
| No. 4 sieve | TV -6.0 | TV + 6.0 |
| No. 8 sieve | TV -6.0 | TV + 6.0 |
| No. 16 sieve | TV -5.0 | TV + 5.0 |
| No. 30 sieve | TV -4.0 | TV + 4.0 |
| No. 50 sieve | TV -4.0 | TV + 4.0 |
| No. 100 sieve | TV -3.0 | TV + 3.0 |
| No. 200 sieve* | TV -2.0 | TV + 2.0 |
| Asphalt Cement % | TV -0.4 | TV + 0.4 |
| Mat Density % | 93 | 100 |
| *Tolerances for the No. 200 sieve may not exceed the broadband limits in Table 703-3. |  |  |

4.	The Upper Quality Index (QU) is computed:	 QU

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:	 QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined. See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined. See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor (PF) is determined for Density (DPF) and gradation and asphalt cement content pay factors from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

- The CPF is rounded to the nearest hundredth.

- Table 408-3 gives the weight factor (f), for each sieve size and asphalt cement content.

- TABLE 408-3

WEIGHT FACTORS

| Sieve Size | Type V Factor “f” |
| --- | --- |
| 3/4 inch sieve | 4 |
| 1/2 inch sieve | 5 |
| 3/8 inch sieve | 5 |
| No. 4 sieve | 4 |
| No. 8 sieve | 4 |
| No. 16 sieve | 4 |
| No. 30 sieve | 5 |
| No. 50 sieve | 5 |
| No. 100 sieve | 4 |
| No. 200 sieve | 20 |
| Asphalt Cement Content, % | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

- Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

*CPF or DPF, whichever is lower.

- PAB = Price Adjustment Base = $140 per ton

- ASPHALT CEMENT

- The total asphalt cement price adjustment is the sum of all price adjustments for each lot.

Asphalt cement will be randomly sampled and tested in accordance with Subsection 408-4.02. Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.

- Table 408-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  |  | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Test | Spec | 0.00 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.10 | 0.25 | Reject or Engr Eval |
| Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | < 3 Pa-s | < 3 |  | > 3 |  |  |  |  |  |  |
| Dynamic Shear | > 1.00 kPa | > 1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | < 0.50 |
| Toughness | > 110 in-lbs | > 93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | < 70.0 |
| Tenacity | > 75 in-lbs | > 63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | < 48.0 |
| Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | < 1.00 % | < 1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | > 1.276 |
| Dynamic Shear | > 2.20 kPa | > 2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | < 1.048 |
| Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | < 5000 kPa | < 5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | > 5867 |
| Creep Stiffness, S | < 300 MPa | < 300 |  | 301-338 |  |  |  | 339- 388 | 389- 450 | > 450 |
| Creep Stiffness, m-value | > 0.300 | > 0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | < 0.261 |

Asphalt Cement Price Adjustment = 5 x PAB x Qty x PRF (for each sample)

PAB 		= Price Adjustment Base

Qty 		= Quantity of asphalt cement represented by asphalt cement sample

PRF	 	= Pay Reduction Factor from Table 408-4

Asphalt Cement Appeal Procedure. Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal. The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question). The Engineer will review these test results using ASTM D3244 to determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing. This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction. If this final value incurs a price adjustment, the Contractor shall pay the cost of testing the referee sample.

- PAVEMENT SMOOTHNESS

The top layer of HMA will be measured according to 408-3.15 and evaluated for a smoothness price adjustment. The Engineer will calculate the smoothness price adjustment as follows:

- Smoothness Price Adjustment = PAB x PQ x SF

PAB 	= 	Price Adjustment Base

PQ 		= 	Final quantity of HMA, tons

PrI		= 	Final measured hot mix smoothness, inches/mile

SF 		= 	Smoothness Factor

- If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

- LONGITUDINAL JOINT DENSITY

Longitudinal joint density price adjustments apply when HMA quantities are equal to or greater than 1,500 tons. A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

a.	Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted.

Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to Subsection 408-3.14.

408-4.04 ASPHALT MATERIAL PRICE ADJUSTMENT – UNIT PRICE.

This subsection provides a price adjustment for asphalt material by:

(a) 	additional compensation to the Contractor or

(b) 	a deduction from the Contract amount.

1.	This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 318 and 401 through 409, except Section 402. Also included is the asphalt material in the Approach HMA as included in 408 or 639 and Pathway HMA as part of 608.

2.	This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

3.	The asphalt material price adjustment will only apply when:

a.	More than a 7.5% increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

4.	The Alaska Asphalt Material Price Index (AAMPI) is posted on the Department’s Materials website along with the formula used to calculate the Index. The AAMPI as used in the determination of the “Asphalt Material Price Adjustment – Unit Price” is calculated for the first and third Friday of each month. The index applies from the beginning of the period start day 00:00 hours, and ends 00:00 hours the start of the next period. Other calculation and or period start/end days, including the post day (except as fall on the 1st and 3rd Friday) are not permitted.

5.	Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this Contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%,

additional compensation 	= [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%,

deduction from contract = [(IB – IPP) – (0.075 x IB)] x Q

Where:	Q	=	Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB	=	Index at Bid: the bimonthly Alaska Asphalt Material Price Index in effect on date of bid, in dollars per ton

IPP	=	Index at Pay Period: the bimonthly Alaska Asphalt Material Price Index in effect on the last day of the pay period, in dollars per ton

Method of measurement for determining Q (quantity) is the weight of asphalt material meeting the criteria of this subsection and is incorporated into the project.  The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

# DIVISION 500 – STRUCTURES

## SECTION 501

## STRUCTURAL CONCRETE

501-1.01 DESCRIPTION. Furnish, place, finish, and cure Portland cement concrete for structure construction. Use the class of concrete noted on the Plans unless otherwise specified.

- classes of concrete

- Class A:	General use concrete

Class A-A:	Concrete where improved strength and durability is required

Class P:	Concrete where strength in excess of 5000 psi is required

Class DS:	Concrete for drilled shaft foundations

501-1.02 DEFINITIONS.

ADMIXTURE. A material other than water, aggregate, hydraulic cement, pozzolan, and fiber reinforcement, added to the batch before or during mixing, used as an ingredient of a cementitious mixture to modify its freshly mixed, setting, or hardened properties.

AIR-ENTRAINING ADMIXTURE. An admixture causing the development of a system of microscopic air bubbles in concrete, mortar, or cementitious material paste during mixing, usually to improve its workability and resistance to damage by freezing and thawing.

SET-ACCELERATING ADMIXTURE. An admixture causing an increase in the rate of hydration of the hydraulic cement and shortens the time of setting, increases the rate of strength development, or both.

SET-RETARDING ADMIXTURE. An admixture causing a decrease in the rate of hydration of the hydraulic cement and lengthens the time of setting, decreases the rate of strength development, or both.

WATER-REDUCING ADMIXTURE. An admixture either increasing slump of freshly mixed mortar or concrete without increasing water content or maintaining slump with a reduced amount of water, due to factors other than air entrainment.

AGITATION. The process of providing motion in mixed concrete just sufficient to prevent segregation or loss of plasticity.

BLEED WATER. The autogenous flow of water emerging from newly placed concrete, and caused by the settlement of the solid materials within the mass. The relative quantity of mix water that will bleed can be estimated by AASHTO T 158.

CAMBER. For prestressed concrete members, camber is the net upward deflection of an eccentrically prestressed concrete member due to the combined loads, shrinkage, creep, and eccentricity of the prestress force. For non-prestressed members, camber is a deflection intentionally built into a structural element or form to improve appearance or to nullify the deflection of the element under the effects of loads, shrinkage, and creep.

CEMENT. A binding material that sets and hardens by hydration and is capable of doing so underwater, sometimes called hydraulic cements

- CEMENTITIOUS MATERIAL. Hydraulic cements and pozzolans with cementing properties.

- CHAMFER. A beveled edge or corner formed into finished concrete.

COMPRESSIVE STRENGTH, (fc). The measured maximum resistance of a concrete or mortar specimen to axial compressive loading; expressed as force per unit cross-sectional area; or the specified resistance used in design calculations.

SPECIFIED COMPRESSIVE STRENGTH, (f’c). The 28-day compressive strength used in structural design and specified in the Contract documents.

REQUIRED AVERAGE COMPRESSIVE STRENGTH, (f’cr). The 28-day compressive strength, used as the basis for selection of concrete proportions in the mix design process, sufficiently greater than the Specified Compressive Strength to ensure the acceptance criteria are met.

COMPRESSIVE STRENGTH TEST. The average strength test of concrete, from at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders sampled according to AASHTO T 141, cured according to AASHTO R 39 or WAQTC FOP for AASHTO T 23, and tested according to AASHTO T 22 or sampled, cured, and tested to equivalent ASTM test methods. Unless otherwise noted, tested at an age of 28 days.

The average strength test of grout, from at least three specimens from a batch and tested according to WAQTC TM 12, AASHTO T 106, or ASTM C 109.

CONCRETE ANCHOR. Cast-in-place or post-installed fastening device installed in the concrete for the purpose of transferring loads to the concrete. See ASTM E 2265 for standard terminology.

CONSOLIDATION. The process of inducing a closer arrangement of the solid particles in freshly mixed concrete during placement by the reduction of voids, usually by vibration, rodding, tamping, or some combination of these actions.

- CONSTRUCTION JOINT. The surface where two successive placements of concrete meet.

CURING. Action taken to maintain moisture and temperature conditions in a freshly placed cementitious mixture to allow hydraulic cement hydration and (if applicable) pozzolanic reactions to occur so the desired properties of the mixture develop.

CURING PERIOD. The length of time in which continuous curing operations are maintained thereby allowing the concrete to properly hydrate and develop its required strength and durability.

INITIAL CURING PERIOD. The time period between placement and implementation of final curing methods in which deliberate action is taken to reduce the loss of moisture from the surface of the concrete.

FINAL CURING PERIOD. The time period after the concrete achieves final set in which deliberate action is taken, without damaging or marring the concrete surface, to maintain satisfactory moisture content and temperature in concrete.

CURING COMPOUND. A liquid applied as a coating to the surface of newly placed concrete to retard the loss of water and, in the case of pigmented compounds, reflects heat to provide an opportunity for the concrete to develop its properties in a favorable temperature and moisture environment.

DURABILITY. The ability of concrete to resist weathering action, chemical attack, abrasion, and other conditions of service.

EVAPORATION RATE REDUCER. A material generating a continuous thin film when spread over water on the surface of fresh concrete to retard the evaporation of bleed water.

FIELD TEST RECORD. A record of compressive strength test results from concrete used on prior projects and produced by the concrete production facility.

INFORMATIONAL FIELD TEST. A compressive strength test, determined by the Engineer, from field test cylinders cured on the site under temperature and moisture conditions similar to the concrete in the structure; except, the compressive strength test may consist of one 6.0 x 12.0 inch or one 4.0 x 8.0 inch compressive strength test cylinder.

KEYWAY. A recess or groove in one lift or placement of concrete and filled with concrete of the next lift or grout, giving shear strength to the joint.

LAITANCE. A layer of weak material derived from cementitious material and aggregate fines either: 1) carried by bleeding to the surface or to internal cavities of freshly placed concrete; or 2) separated from the concrete and deposited on the concrete surface or internal cavities during placement of concrete underwater.

MORTAR. A mixture of cementitious material paste and fine aggregate occupying the space between particles of coarse aggregate.

RETEMPER. To add water and remix concrete or mortar to restore workability to a condition in which the mixture is placeable or usable.

ROCK POCKET. A porous, mortar-deficient portion of hardened concrete consisting primarily of coarse aggregate and open voids.

SCREED. To strike off concrete lying beyond the desired plane or shape. A tool for striking off the concrete surface, sometimes referred to as a strikeoff.

SET. The condition reached by a cementitious material paste, mortar, or concrete that has lost plasticity to a degree of stiffening generally stated as the time in hours and minutes required for cementitious material paste to stiffen sufficiently to resist the penetration of a weighted test needle as prescribed by AASHTO T 197,

- INITIAL SET. The first stiffening of concrete.

- FINAL SET. Attainment of significant rigidity in which rainfall, foot traffic, and curing materials contacting the concrete surface do not damage or mare the concrete surface and do not alter the properties of the finished surface.

- TREMIE. A pipe or tube with a hopper for filling at its upper end through which concrete is deposited.

501-2.01 MATERIALS. Use materials conforming to the following:

- 1.	Cementitious Materials

Portland Cement	Section 701

Blended Hydraulic Cement	Section 701

Fly Ash	Section 701

Ground Granulated Blast-Furnace Slag	Section 701

Silica Fume	Section 701

- 2.	Aggregate Materials

Fine Aggregate	Subsection 703-2.01

Coarse Aggregate	Subsection 703-2.02

Aggregate for Abrasive Finish	Subsection 703-2.14

- 3.	Water, Admixtures and Curing Materials

Curing Materials	Subsection 711-2.01

Chemical Admixtures	Subsection 711-2.02

Water and Ice	Subsection 712-2.01

- 4.	Anchors and Inserts

Concrete Anchor Inserts and Bolts	Subsection 712-2.20

Utiliduct, HDPE	Subsection 706-2.08

Utiliduct, Steel	Section 716

Structural Steel	Section 716

Asphalt Felt	ASTM D 226, Type I (No. 15 Asphalt Felt)

- 5.	Grout and Epoxy

Grout	Subsection 701-2.03

Epoxy Adhesive for Crack Sealing	AASHTO M 235, Type IV, Grade 3

Epoxy Adhesive for Crack Injection	AASHTO M 235, Type IV, Grade 1

Low-Viscosity Resin	Subsection 712-2.19

Epoxy Bonding Agents	AASHTO M 235, Type V

501-2.02 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Provide a Job Mix Design, for each required class of concrete and Specified Compressive Strength (f'c), which meets the requirements of this Subsection and provides workability and consistency so the concrete can be worked readily into the forms and around reinforcement without segregation or bleeding. Determine proportions using the absolute volume method according to ACI 211.1.

1.	Water-Cement Ratio and Cementitious Materials. Provide a Job Mix Design meeting the water-cement ratio requirements in Table 501-1.

Calculate the water-cement ratio based on the total weight of cementitious material. The following are considered cementitious materials: Portland cement, blended hydraulic cement, fly ash, ground granulated blast-furnace slag, and silica fume.

Fly ash, ground granulated blast-furnace slag, silica fume, and combinations of these materials may be used as a substitute for Type I and II Portland cement provided the quantity meets the limits of Table 501-2 and the total quantity of combined fly ash, ground granulated blast-furnace slag, and silica fume does not exceed 40 percent of the total cementitious material by weight. Do not use fly ash with Type III Portland cement.

- TABLE 501-1

WATER-CEMENT RATIO REQUIREMENTS

| Class of Concrete | Water-Cement Ratio, maximum |
| --- | --- |
|  | lbs/lbs |
| A | 0.45 |
| A-A | 0.40 |
| P | 0.35 |
| DS | 0.45 |

- TABLE 501-2

SUPPLEMENTARY CEMENTITIOUS MATERIAL LIMITS

| Cementitious Material | Percent of Total Cementitious Material by Weight1 |
| --- | --- |
|  | Maximum |
| Fly Ash | 35% |
| Ground Granulated Blast-Furnace Slag | 40% |
| Silica Fume | 10% |
| 1 The maximum percent includes initial quantities in blended hydraulic cement plus additional supplementary cementations materials. |  |

2.	Aggregate Gradations. Provide a Job Mix Design meeting the fine aggregate gradation requirements in Subsection 703-2.01 and the coarse aggregate gradation requirements in Table 501-3.

- TABLE 501-3

COARSE AGGREGATE GRADATION REQUIREMENTS

| Class of Concrete | Coarse Aggregate Size Number |
| --- | --- |
|  | AASHTO M 43 |
| A | No. 57 or 67 |
| A-A | No. 57 or 67 |
| P | No. 67 |
| DS | No. 7 or 8 |

3.	Air Content. Provide a Job Mix Design with a total air content of 6.0 percent. The total air content for Class P concrete having a water/cement ratio less than 0.33 may be reduced 3.0 percent. Air-entrained concrete is required only for the deck portion of prestressed precast concrete members. Air-entrained concrete is not required for Class DS concrete.

4.	Slump. Provide a Job Mix Design meeting the slump requirements in Table 501-4.

- TABLE 501-4

SLUMP REQUIREMENTS

| Condition | Slump |
| --- | --- |
| Concrete without a water-reducing admixture | 4" max. |
| Concrete with a Type A, D, or E water-reducing admixture | 6" max. |
| Concrete with a Type F or G high-range water-reducing admixture | 9" max. |
| Class DS concrete, wet-shaft process | 7" min. 9" max. |
| Class DS concrete, dry-shaft process | 6" min. 9" max. |

5.	Chloride Ion Content. For Class A-A and P Concrete, provide a Job Mix Design with a total water soluble chloride ion content of the concrete that does not exceed 0.06 percent by weight of cementitious material for precast concrete members or 0.08 percent by weight of cementitious material for other concrete, tested according to ASTM C 1218.

6.	Required Averaged Compressive Strength. Provide a Job Mix Design meeting a Required Average Compressive Strength (f'cr) established from either the Empirical Method or the Statistical Method.

If the Specified Compressive Strength (f'c) is not designated on the Plans, use a Specified Compressive Strength listed in Table 501-5.

- TABLE 501-5

COMPRESSIVE STRENGTH REQUIREMENTS

| Class of Concrete | Specified Compressive Strength (f'c) |
| --- | --- |
|  | (psi) |
| A | 4000 |
| A-A | 5000 |
| P | 8000 |
| DS | 4000 |

a.	Empirical Method. Establish the Required Average Compressive Strength from the following equations:

f'cr = f'c + 1200	for f'c ≤ 5000 psi

f'cr = 1.1f'c + 700	for f'c > 5000 psi

Where:		f'cr = Required Average Compressive Strength, psi

f'c = Specified Compressive Strength, psi

b.	Statistical Method. If the production facility has field test records of compressive strength tests, establish the Required Average Compressive Strength based on the calculated standard deviation of the field test records and using the largest result of the following the equations:

f'cr = f'c + 1.34ks	for all f'c

or,

f'cr = f'c + 2.33ks – 500	for f'c ≤ 5000 psi,

f'cr = 0.90f'c + 2.33ks	for f'c > 5000 psi,

Where:		f'cr	=	Required Average Compressive Strength, psi

f'c	=	Specified Compressive Strength, psi

k	=	1.16 if 15 total tests are considered

1.08 if 20 total tests are considered

1.03 if 25 total tests are considered

1.00 if 30 or more total tests are considered

S	=	standard deviation, psi

Linear interpolation to determine k for intermediate number of tests is acceptable.

Use field test records performed within the past 12 months and spanning a period of more than 60 days for a class of concrete within 1000 psi of the Specified Compressive Strength. Use field test records from concrete produced at the production facility, which represent materials, quality-control procedures, and climatic conditions similar to those expected in the work. Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work. Use field test records meeting one of the following:

(1)	One Group of Field Test Records. Use field test records representing a group of at least 15 consecutive compressive strength tests in which all concrete was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation, psi

- n	=	number of compressive strength test results considered

Xi	=	individual compressive strength test result, psi

=	average of n compressive strength test results, psi

(2)	Two Groups of Field Test Records. Use field test records representing two groups of consecutive compressive strength tests totaling at least 30 tests. Ensure each group is comprised of at least 10 consecutive compressive strength tests, and all concrete in each group was produced using the same mixture proportions. Calculate the standard deviation using the following equation:

- Where:	s	=	standard deviation for the two groups combined, psi

s1, s2	=	standard deviation for groups 1 and 2, respectively, calculated according to Subsection 501-2.02.6.b.(1), psi

n1, n2	=	number of test results in groups 1 and 2, respectively

7.	Job Mix Design Verification.

a.	Required Average Compressive Strength. Verify the Job Mix Design satisfies the Required Average Compressive Strength by meeting at least one of the following requirements:

(1)	Field Test Records. Use field test records that:

(a)	use materials of the same brand and type and from the same manufacturer as the materials used in the work;

(b)	were from concrete produced at the production facility;

(c)	use quality-control procedures, and had climatic conditions similar to those expected in the work; and

(d)	encompass a period of not less than 60 days.

Do not use field test records from concrete in which acceptance requirements for materials or concrete proportions were more closely restricted than those in the proposed work.

For a single group of at least 10 consecutive compressive strength tests for one mixture, verify the average of the compressive strength tests equals or exceeds the Required Average Compressive Strength.

For two groups, each having at least 10 consecutive compressive strength tests, for two mixtures representing classes of concrete within 1000 psi of the Specified Compressive Strength, plot the average strength of each group versus the water-cementitious material ratio of the corresponding mixture proportions and interpolate between them to determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the interpolated compressive strength equals or exceeds the Required Average Compressive Strength.

(2)	Laboratory Trial Mixtures. Use materials and material combinations for trial mixtures of the same brand and type and from the same manufacturer as the materials used in the work.

Record the temperature of the freshly mixed concrete according to AASHTO T 309 and ensure the temperature is within 10°F of the intended maximum temperature of the concrete as mixed and delivered.

For each trial mixture, make and cure at least two 6.0 x 12.0 inch or at least three 4.0 x 8.0 inch compressive strength test cylinders for each test age according to AASHTO R 39. Test for compressive strength according to AASHTO T 22 at test ages of 7, 14 and 28 days.

For a single trial mixture, verify the compressive strength test equals or exceeds the Required Average Compressive Strength.

For a group of trial mixtures, make at least three trial mixtures with each mixture having a different cementitious material content. Select water-cement ratios producing a range of compressive strengths encompassing the Required Average Compressive Strength. From the results of the 28-day compressive strength tests, plot a curve showing the relationship between water-cement ratio and compressive strength. From the curve of water-cement ratio versus compressive strength, determine the compressive strength corresponding to the water-cementitious material ratio of the Job Mix Design. Verify the compressive strength equals or exceeds the Required Average Compressive Strength.

b.	Flowability Requirements for Class DS Concrete (Wet-Shaft Process). Verify the Job Mix Design satisfies the concrete flowability requirements of Subsection 501-3.05.6.a.1. Develop a slump loss table showing the slump at 1 hour intervals since batching until the concrete takes initial set.

c.	Plasticity Requirements for Class DS Concrete (Dry-Shaft Process). Verify the Job Mix Design satisfies the concrete plasticity requirements of Subsection 501-3.05.6.b.1. Ensure initial set occurs after placement operations are complete.

8.	Job Mix Design Submittal. Submit a written mix design, signed and sealed by a Professional Engineer registered in the State of Alaska, for each specified class of concrete and for each Specified Compressive Strength, to the Engineer at least 45 days prior to scheduled production. Submit the mix design on Form 25D-203. Include the following:

a.	Job Mix Design Proportions and Test Results. Submit concrete mixture proportions per cubic yard and test results for the proposed Job Mix Design. Include the following information:

- (1)	Weights of cementitious materials

- (2)	Weights of aggregates in saturated surface dry condition

- (3)	Volume or weight of each admixture.

- (4)	Weight of water

- (5)	Water-cement ratio

- (6)	Percentage of air by volume

- (7)	Total water soluble chloride ion content

- (8)	Wet unit weight

- (9)	Expected slump

- (10)	Expected 7, 14, and 28 day compressive strength

- (11)	Slump loss table for flowability requirements of Class DS concrete (if applicable)

- (12)	Time of initial set for plasticity requirements of Class DS concrete (if applicable)

b.	Materials Documentation. Submit the following:

(1)	For each cementitious material, include:

(a)	Type/Class

(b)	Brand

(c)	Producer

(d)	Plant location

(e)	Certified test reports confirming the cementitious material meets these Specifications.

(2)	For aggregates, include:

(a)	Pit or quarry location(s)

(b)	Bulk dry specific gravity, bulk saturated surface dry specific gravity, and apparent specific gravity

(c)	Absorption values

(d)	AASHTO size number for coarse aggregates

(e)	Gradations for aggregates

(3)	For each admixture, include:

(a)	Type

(b)	Manufacturer

(c)	Manufacturer's product data sheet giving the procedure for admixture use and confirming the admixture meets these Specifications.

(d)	The batching process step and mixing instructions when each admixture is added.

(e)	When using two or more admixtures in the same Job Mix Design, provide manufacturer’s certifications showing the admixtures are compatible and if they can be added simultaneously.

(4)	Include the source of supply for water and ice.

c.	Materials Samples. The Engineer may require samples of aggregate, cementitious materials, and admixtures to verify the mix design. If requested, furnish representative samples (330 pounds each) of both coarse and fine aggregates, 94 pounds of each cementitious material, and enough admixture to allow for Job Mix Design verification testing. Ensure the Department receives these samples at least 45 days before the mixture’s scheduled production for the project.

d.	Basis of Required Average Compressive Strength. If the Statistical Method is used, submit the following for each field test record:

(1)	Compressive strength test results of the tested concrete.

(2)	Standard test method used for determining compressive strength.

(3)	Date the compressive strength tests were performed

(4)	Aggregate source used for the tested concrete.

(5)	Specified strength of the tested concrete.

(6)	Batched weights of constituent materials for the concrete used for each compressive strength test.

e.	Documentation of Required Average Compressive Strength. Submit documentation indicating the proposed concrete proportions will produce an average compressive strength equal to or greater than the Required Average Compressive Strength meeting one of the following requirements:

(1)	Field Test Records. If field test records were used to verify the Required Average Compressive Strength, submit the following for each field test record:

(a)	Compressive strength test results of the tested concrete.

(b)	Standard test method used for determining compressive strength.

(c)	Date the compressive strength tests were performed

(d)	Aggregate source used for the tested concrete.

(e)	Specified strength of the tested concrete.

(f)	Batched weights of constituent materials for the concrete used for each compressive strength test.

(2)	Trial Mixtures. If a single or group of trial mixtures were used to verify the Required Average Compressive Strength, submit concrete mixture proportions per cubic yard and test results for each trial mixture. Include the following information:

(a)	Weights of cementitious materials

(b)	Weight of aggregates in saturated surface dry condition

(c)	Volume or weight of each admixture

(d)	Weight of water

(e)	Water-cement ratio

(f)	7-day, 14-day, and 28-day compressive strength test results

(g)	Percentage of air by volume

(h)	Wet unit weight

9.	Changes. A change in the approved Job Mix Design proportions, materials, aggregate gradation, or aggregate quality requires a new Job Mix Design; except, a change in Type A, D, E, F, and G admixture proportions, or the addition of a Type A, D, E, F, and G admixture, does not require a new Job Mix Design.

10.	Approval. Obtain the Engineer’s approval of each mix design prior to use. Approval of the Job Mix Design does not constitute acceptance of produced concrete and will not obligate the Department to accept or pay for concrete that does not meet the mix acceptance requirements of Subsection 501-3.03.

- CONSTRUCTION REQUIREMENTS

501-3.01 BATCHING. Batch concrete, in proportioned amounts, according to the approved Job Mix Design.

1.	Certification and Calibration. Batch concrete using a certified batch plant. Obtain plant certification meeting the requirements in this Subsection. Use and maintain calibrated weighing and measuring devices for concrete batching equipment, including measuring devices for adding material on-site, meeting the requirements of this Subsection. Submit documentation required for plant certification and weighing and measuring device calibration meeting the requirements of this Subsection before commencing concrete work.

a.	Plant Certification by the National Ready Mix Concrete Association. Certification may be obtained from the National Ready Mix Concrete Association (NRMCA). Information concerning NRMCA certification may be obtained from the NRMCA at 900 Spring Street, Silver Springs, MD 20910 or online at www.nrmca.org. The NRMCA certification is valid for 2 years from the date of inspection.

b.	Plant Certification by a Professional Engineer. Certification may be obtained by an independent inspection and evaluation by a Professional Engineer registered in the State of Alaska using and completing the NRMCA Plant Certification Check List. Correct deficiencies to the satisfaction of the Professional Engineer. The Professional Engineer must sign and seal the completed NRMCA Plant Certification Check List certifying all applicable items have been met. The certification by a Professional Engineer is valid for 2 years from the date of inspection.

c.	Calibration of Weighing and Measuring Devices. Use weighing and measuring devices meeting the requirements of the National Institute of Standards and Technology Handbook 44: Specifications, Tolerances, and other Technical Requirements for Weighing and Measuring Devices, and are calibrated by a commercial scale service or certified by the DOT&PF Division of Measurement Standards & Commercial Vehicle Enforcement. Calibrate weighing and measuring devices using equipment traceable to the Alaska State Standards of Weight and Measure as adopted by AS 45.75.020.

Calibrate weighing and measuring devices:

(1)	no more than 12 months before commencing concrete work,

(2)	after each relocation,

(3)	at least once every 12 months until the work is completed, and

(4)	when, in the opinion of the Engineer, there is a question as to the accuracy or adequacy of the device.

d.	Certification and Calibration Submittals. If the Plant Certification is by the NRMCA, submit a copy of the NRMCA Certificate of Conformance. If the Plant Certification is by a Professional Engineer, submit a copy of the completed NRMCA Plant Certification Check List and associated Fleet Inspection Reporting Spreadsheet.

Submit copies of the calibration worksheets for weighing and measuring devices including the most recent date of inspection and the calibrated accuracy for each weighing and measuring device.  Submit copies of updated calibration worksheets for each additional calibration required according to 501-3.01.1.c.

2.	Measuring Materials.

a.	Cementitious Materials. Use cementitious materials of the same brand, type, and from the same plant of manufacture as the cementitious materials used to verify the approved Job Mix Design according to Subsection 501-2.02.7. Ensure the quantity of the Portland cement and the cumulative quantity of Portland cement plus other cementitious materials is proportioned in amounts required by the Job Mix Design and meets the mix acceptance requirements.

Measure cementitious materials by weight. When other cementitious materials, including fly ash, ground granulated blast-furnace slag, or silica fume, are specified in the concrete proportions, the material may be cumulatively weighed with the Portland cement. Weigh cementitious materials on a weighing device that is separate and distinct from those used for other materials. Weigh the Portland cement before other cementitious materials.

Portland cement is permitted to be measured in bags of standard weight (94 pounds). Do not use a fraction of a bag of cementitious materials unless its weight has been determined by calibrated weighting devices.

b.	Aggregates. Use aggregates from the same sources and having the same size ranges as the aggregates used in the trial mixtures or field test records used to verify the required average compressive strength. Ensure the quantity of the aggregates is proportioned in amounts required by the Job Mix Design.

Measure aggregates by weight. Establish batch weight measurements on dry materials and adjust the actual scaled weight for the required dry materials weight plus the total weight of moisture, both absorbed and surface, contained in the aggregate.

c.	Water. The total quantity of mixing water includes water added to the batch, ice added to the batch, and water occurring as surface moisture on the aggregates. Measure the added water by weight or volume. Measure added ice by weight. Discharge the flush water (wash water) prior to loading the next batch of concrete. Do not use flush water (wash water) as a portion of the mixing water.

d.	Admixtures. Use concrete admixtures according to the manufacturer's instructions and the approved Job Mix Design. Type A, D, E, F, and G admixtures not included in the approved Job Mix Design may be added according to Subsection 501-2.02.9.

Measure powdered admixtures by weight. Measure paste or liquid admixtures by weight or volume.

3.	Materials Storage and Handling.

a.	Cementitious Materials. Keep cementitious materials dry and free from contaminants. Do not use cementitious materials which have become partially hydrated or which contain lumps of caked cementitious material.

b.	Aggregates. Do not allow segregation of the aggregates or contamination with foreign materials. Separate aggregate to prevent intermixing of specified gradations.

Drain aggregate so the moisture content is uniform and is accounted for during the batching process.

Do not use aggregates that contain ice, are frozen, or have been heated directly by combustible materials. Use direct steam, steam-coil, or water-coil heating when heating aggregates. When direct steam is used to thaw aggregate piles, drain aggregates to uniform moisture content before batching.

c.	Admixtures. Protect admixtures from contamination, evaporation, or damage. Store admixtures according to the manufacturer’s instructions. Protect liquid admixtures from freezing and from temperature changes affecting the admixture’s performance.

501-3.02 MIXING AND DELIVERY. Mix concrete, in proportioned amounts, according to the approved Job Mix Design. Mix ingredients into a thoroughly intermingled uniform mixture. Do not retemper concrete mixtures. Do not use concrete that has developed initial set prior to placement.

- 1.	Addition of Water. Additional water may be added on-site provided the following are met:

a.	The volume of concrete in the mixer after the additional water is added does not exceed the maximum mixing capacity.

b.	The water measuring device is calibrated according to Subsection 501-3.01.1.c.

c.	The Water-cement ratio for the batch as established by the approved Job Mix Design is not exceeded. Account for the actual volume of concrete remaining in the mixer.

d.	Water additions are completed within 30 minutes after the introduction of the mixing water to the cementitious materials.

The addition of water is not prohibited from being several distinct additions of water. Inject additional water into the mixer under pressure and direction of flow to allow for proper distribution within the mixer. Provide additional mixing to ensure a thoroughly intermingled uniform mixture is attained.

- 2.	Time for Placement. Discharge the concrete within 1.5 hours of the following:

a.	after adding the mixing water to the cementitious materials, and

b.	after adding the cementitious materials to the aggregates.

The time to complete discharging the concrete may be extended 2 minutes for every degree of temperature at which the concrete is discharged below 70°F, to a maximum total time of 2 hours. The Engineer may increase the time to discharge requirement provided the concrete can be placed before initial set occurs and without the addition of water.

501-3.03 EVALUATION OF MATERIAL FOR ACCEPTANCE. All concrete in the work will be evaluated for acceptance.

The Engineer may reject a batch or load of concrete failing to meet the requirements for proportions, slump, total air content, or temperature. Prior to sampling, the Engineer may reject a batch or load of concrete that appears defective in composition.

1.	Sampling. The Department will take samples at the discharge point of the placement system, except Class DS concrete will be sampled at the truck discharge.

Provide adequate and representative fresh concrete for sampling and testing as directed by the Engineer. The Engineer will sample the concrete after a minimum of 1/2 cubic yard of concrete has discharged from the placement system. Do not add water or admixtures to the mix after the concrete has been sampled for acceptance testing.

The Engineer will determine aggregate gradation for acceptance based on random samples taken at the plant.

2.	Sampling and Test Methods. The Department will sample and test according to the following:

WAQTC TM 2	Sampling Freshly Mixed Concrete

WAQTC FOP for AASHTO T 309	Temperature of Freshly Mixed Portland Cement Concrete

AASHTO T 22	Compressive Strength of Cylindrical Concrete Specimens

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse Aggregates, and Materials Finer Than No. 200 Sieve in Mineral Aggregate by Washing

WAQTC FOP for AASHTO T 23	Method of Making and Curing Concrete Test Specimens in the Field

WAQTC FOP for AASHTO T 119	Slump of Hydraulic Cement Concrete

WAQTC FOP for AASHTO T 121	Density (Unit Weight), Yield, and Air Content (Gravimetric) of Concrete

WAQTC FOP for AASHTO T 152	Air Content of Freshly Mixed Concrete by the Pressure Method

AASHTO T 231	Capping Cylindrical Concrete Specimens

WAQTC FOP for AASHTO TP 83	Field Sampling and Fabrication of 50-mm (2-in) Cube Specimens using Grout (Non-Shrink) and or Mortar

3.	Batch Tickets. Provide a ticket with each batch of concrete delivered to the project.  Include the following information:

a.	Manufacturer plant (batching facility)

b.	Department contract number

c.	Date

d.	Time cementitious material added to batch

e.	Truck number

f.	Quantity (quantity batched this load)

g.	Batch facility mix identification number

h.	Weights of every type of cementitious material

i.	Weights of each aggregate

j.	Weight or volume of each admixture

k.	Weight or volume of water added at the plant

l.	Total moisture and absorption percentage for each aggregate

m.	Maximum weight or volume of water that may be added in the field

n.	Weight or volume of water added in the field

o.	Time discharge completed

p.	Signature of Contractor’s representative, affirming the accuracy of the information provided

4.	Proportion Requirements. Meet the proportion requirements of the approved Job Mix Design within the following proportion tolerances:

a.	Total Cementitious Material, weight 	±1%

b.	Aggregates, weight	±2%

c.	Total Water, weight or volume	±3%

d.	Air-Entraining Admixtures, weight or volume	manufacturer's limits

e.	Type S Admixture, weight or volume	±3%

f.	Type A, B, C, D, E, F, G Admixtures, weight or volume	manufacturer's limits

If the total cementitious material weight is made up of different components, keep the component weights within the following tolerances:

(1)	Portland Cement	±1%

(2)	Fly Ash	±5%

(3)	Ground Granulated Blast-Furnace Slag	±5%

(4)	Silica Fume	±10%

Proportion tolerance will be calculated using consistent units for MJMD and MA as follows:

- Where:	P	=	Proportion tolerance, percentage

- MJMD	=	Weight or Volume of component according the approved Job Mix Design

MA	=	Weight or Volume of actual batched component

5.	Slump Requirements. Do not exceed 9” slump for Class A, A-A, P, and DS concrete. For Class DS concrete, meet the following slump tolerances:

a.	Using the wet-shaft process: 7 inches minimum, 9 inches maximum

b.	Using the dry-shaft process: 6 inches minimum, 9 inches maximum

6.	Total Air Content Requirements. Meet the total air content percentage within a tolerance of ±1.5 of the approved Job Mix Design percentage.

7.	Temperature Requirements. Unless otherwise noted, ensure the concrete temperature is between 50°F and 90°F when placed in the forms.

8.	Compressive Strength Requirements. Meet the strength requirements for the Specified Compressive Strength. Concrete of the approved Job Mix Design will be considered to meet the Specified Compressive Strength requirements when both of the following conditions are met:

a.	The lowest individual compressive strength test result is not less than the Specified Compressive Strength minus 500 psi, or 90.0 percent of the Specified Compressive Strength, whichever is lower.

b.	The lowest averaged result of three consecutive individual compressive strength tests meets or exceeds the Specified Compressive Strength.

501-3.04 PREPARATION FOR CONCRETE PLACEMENT. Allow time for inspection prior to concrete placement.

Remove debris, concrete splatter, oil, paint, and other foreign substances from the surfaces of forms and reinforcing steel, against which the concrete is to be placed.

- Remove soil and other debris from pipe piles to the bottom of concrete elevation shown on the Plan.

- Prepare foundations according to Section 205.

Moisten foundations and forms with water before the concrete is placed. Remove standing water on the foundation, in the pile, and in the forms before placing concrete.

501-3.05 PLACING CONCRETE. Do not begin concrete placement without the Engineer's authorization. Place concrete conforming to the approved Job Mix Design. Place and consolidate each layer within 30 minutes and before the preceding layer takes initial set.

If concrete placement operations are delayed so initial set occurs before placement of the succeeding section or layer, place a joint according to Subsection 501-3.11. The resulting joint will be considered a construction joint. If, in the opinion of the Engineer, the location of the construction joint will affect the strength or durability of the concrete, the Engineer may reject the concrete, the structure, or a portion of the structure.

Place concrete in a sequence to obtain a well-consolidated concrete and to prevent cracks. Place concrete as near as possible to final position. Prevent segregation of the mix, displacement of reinforcing steel, and spattering of mortar on the reinforcing steel and forms above the elevation of the layer being placed. Do not deposit a large quantity of concrete at any point and run or work the concrete along the forms. Do not allow concrete to slide down the sides of the forms.

Regulate concrete placement so the pressures do not exceed the load capacity of the forms. Limit layer thickness to no more than 2.5 feet, or the capacity of the vibrators to consolidate and merge the concrete with the previous layer, whichever is less.

Unless otherwise specified, use a tremie, tube, or other such device to limit the free-fall height to less than 5.0 feet when placing operations would otherwise allow concrete to drop more than 5.0 feet. When using a tremie to place concrete, use a watertight tremie with an inside diameter of at least 10 inches.  When using a concrete pump to place concrete, use concrete pump lines that are watertight with an inside diameter of at least 5 inches.

Concrete placed in piles or in dry-shaft process may free-fall more than 5 feet without use of tremie, tube or other such device, provided the falling concrete does not contact rebar or other objects before reaching the top surface of the placed concrete. When free-falling concrete more than 5 feet, use a drop chute at least 3 feet long.

After initial set, prevent movement of forms, projecting ends of reinforcing steel, and other embedded items.

- Do not use aluminum components in contact with fresh concrete.

Place concrete in the superstructure only after substructure forms are removed and the substructure has been inspected.

1.	Concrete Placement Plan.  Submit a concrete placement plan to the Engineer, for concrete decks and drilled shafts.  Submit each concrete placement plan to the Engineer, at least 30 days before placing concrete. Do not place concrete until after the Engineer has approved the plan. Include the following in each concrete placement plan:

  - concrete placement sequence,

  - schedule of concrete placement and curing,

- estimated concrete volume of each section,

- placement rate and duration,

- description of finishing equipment,

- placement procedure,

- name of the concrete foreman,

- curing materials, equipment, and procedure.

2.	Pre-concreting Conference. Hold a pre-concreting conference for concrete decks and Drilled Shafts, at least 5 working days before placing concrete. Include the Engineer, the Superintendent and foremen in charge of placing reinforcing steel, placing concrete, finishing concrete, and curing operations. Discuss construction procedures, personnel, and equipment to be used.

If the project includes more than one concrete placement operation, and if key personnel change between concreting operations, hold additional conferences to include replacement personnel before placing successive concrete sections.

3.	Pumping Concrete. Use a pump producing a continuous stream of concrete without air pockets. When pumping is completed, the concrete remaining in the pipeline, if used, must eject without contaminating the concrete or separating the ingredients. Discard concrete contaminated by priming or cleaning the pump.

4.	Conveying Concrete. Concrete may be conveyed if the equipment will handle the class of concrete, with the slump and air content specified and without segregation of the aggregate, and no equipment vibrations will damage freshly placed concrete or reinforcing steel. Limit the length of conveyor belts to prevent aggregate segregation or 300 feet, whichever is less. Cover the belt to protect the concrete from heat, evaporation, precipitation, or when the Engineer determines precipitation is likely.

5.	Piles. Do not place concrete underwater in piles.

6.	Drilled Shaft Foundations. Place concrete following either the wet-shaft process or dry-shaft process, as applicable.

The dry-shaft process may be used where the ground water level and soil and rock conditions are suitable to permit construction of the shaft in a relatively dry excavation, and where the sides and bottom of the shaft can be visually inspected by the Engineer prior to placing the concrete. Relatively dry excavation conditions exist when excavation fluids have been removed from the shaft and the rate of water intrusion is less than 6 inches of water accumulating above the base in a 1-hour period without pumping or other methods to drain or remove water. Suitable soil and rock conditions exist when the sides and bottom of the hole remain stable without caving, sloughing, or swelling between completion of excavation and concrete placement; and loose material and water can be satisfactorily removed prior to inspection and concrete placement. Do not begin concrete placement if there is more than 1 inch of water in the bottom of the shaft excavation. Use wet-shaft process if the requirements for dry-shaft process cannot be satisfied.

Provide process control testing during concrete placement. Test total air content and slump before placing each batch of concrete in the drilled shaft. Perform sampling and testing according to Subsection 501-3.03.2 using a WAQTC qualified concrete testing technician or ACI certified concrete field testing technician. Test every batch of concrete before placement. Record the time when each sample is collected. Submit test results to the Engineer within 72 hours of completing each test.

a.	Wet-Shaft Process. Place concrete using a tremie or concrete pump. Place concrete continuously until good quality concrete, as determined by the Engineer, is evident at top of the shaft or nearest construction joint. Good quality concrete is considered concrete of the same consistency, appearance, and quality as the concrete being delivered and meeting the applicable mix acceptance requirements. Remove a sufficient volume of concrete to ensure elimination of contaminated concrete at the top of shaft before continuing with subsequent construction operations.

Remove concrete laitance during or immediately after concrete placement operations have ended.

Do not allow water, fluids, drilling aids, or concrete from the top of the shaft to enter streams or other waterways.

Construct the discharge end of the tremie or pump line to prevent water intrusion and permit the free flow of concrete during concrete placement. Use caps, bottom plates, pigs, or other such devices inserted into or attached to discharge pipe to separate the concrete from the excavation fluid during initial charging of the discharge pipe. Ensure the discharge pipe has sufficient length and weight to rest on the shaft base before starting concrete placement.

When using a tremie, provide adequate support so the tremie can be raised to increase the discharge of concrete and lowered to reduce the discharge of concrete. Do not shake, vibrate, or rapidly raise or lower the tremie to increase the discharge of the concrete.

Maintain a positive head of concrete inside the tremie or pump line relative to the excavation fluid level. Position the discharge orifice within one pipe diameter of the shaft base. Do not re-position the discharge pipe until the orifice is at least 8 feet below the concrete surface. Maintain at least 8 feet of concrete above the discharge orifice during concrete placement. Monitor the concrete level during placement to ensure the tremie or pump line discharge orifice remains at least 8 feet below the concrete surface throughout placement.

If the discharge orifice rises above the concrete surface before concrete placement is complete, the shaft will be considered defective. Immediately terminate concrete placement operations and notify the Engineer.

(1)	Concrete Flowability Requirements. Ensure concrete placed in the shaft remains flowable throughout placement operations by maintaining a slump of at least 6 inches until placement is completed. Collect samples from the first batch of concrete. Test slump from the first batch of concrete at the beginning of the concrete placement operations and immediately after concrete placement operations are complete. Record the time when samples are collected and when tests are performed. Submit test results to the Engineer within 72 hours of completing each test.

b.	Dry-Shaft Process. Place concrete continuously until concrete is evident at top of the shaft or nearest construction joint. Concrete may be permitted to free-fall into place if the concrete does not contact the sides of the shaft, reinforcing steel, or other objects while free falling.

Remove concrete laitance during or immediately after concrete placement operations have ended.

(1)	Concrete Plasticity Requirements. Ensure concrete placed in the shaft remains plastic throughout placement operations by completing placement operations before initial set occurs.

7.	Concrete Decks and Approach Slabs. Before placing concrete, operate the finishing machine over the entire length of the deck to check screed deflection, reinforcing steel clearance, and concrete thickness.

- Limit the rate of placing concrete to what can be finished before initial set.

a.	Placement Sequence. Place the concrete deck in the sequence shown on the Plans. The Engineer may approve a revised placement sequence for casting the concrete deck continuously from one end to the other provided the following:

(1)	Do not use Type III Portland cement.

(2)	Stockpile the materials necessary to complete the placement and have the equipment, incidentals, and workers on the site before beginning concrete placement operations.

(3)	Ensure the continuous concrete placement and finishing operation proceeds at a minimum rate of 30 feet per hour, measured longitudinally along the axis of the span.

(4)	The Engineer determines the revised placement sequence will not reduce the stability during construction and will not reduce the quality, capacity, or durability of the completed structure.

If the Engineer approves the proposal for a continuous concrete placement operation, the Department will observe and evaluate performance to the first planned construction joint in the sequence. At this point, the Engineer may authorize you to proceed with the continuous concrete placement operation or suspend the placement and install a construction joint. The Engineer's decision will be based on whether the concrete can be produced, delivered, and finished at a continuous rate permitting the structure to accommodate final dead load deflections while the concrete is plastic.

If the Engineer suspends the continuous concrete placement operations after the first sequential placement, submit modifications for improving the continuous concrete placement operations, beginning at the other end of the deck. If a second attempt at continuous concrete placement is authorized, the placement will be evaluated and allowed or terminated based on the same criteria as the first sequential placement.

If the Engineer suspends the continuous concrete placement operation after the second attempt, additional attempts will not be permitted. Follow the deck placing sequence shown on the Plans.

501-3.06 CONSOLIDATION OF CONCRETE. Consolidate concrete to make a dense homogeneous mass free of voids and rock pockets. Consolidate each layer to leave a compact, dense, and impervious concrete with smooth faces on exposed surfaces with no visible line of separation between adjoining layers.

Consolidate concrete, except underwater or other exempted placements, by mechanical vibration at the point of deposit. Use vibrators capable of visibly affecting concrete with a 1-inch slump for a distance of at least 18 inches from the vibrator.

Use vibrators and regulate placement in order to consolidate the fresh concrete within 15 minutes of placement and before initial set. Effectively vibrate the full depth of each layer.

For immersion-type vibrators, insert vibrators vertically to a depth penetrating into the previous layer. Withdraw vibrators slowly to avoid segregation or grout pockets. Vibrate in a uniform pattern spaced less than 1.5 times the radius of visible effectiveness.

Avoid vibration of initially set layers and reinforcing steel below the succeeding placement. Do not hold vibrators against reinforcing steel or use them to flow or spread the concrete into place. Manipulate vibrators to produce concrete free of voids, with proper texture on exposed faces, and maximum consolidation. Do not allow the concrete to segregate, form pools of mortar, or form laitance on the surface.

When immersion-type vibrators are used to consolidate concrete around epoxy-coated reinforcing steel, use rubber or nonmetallic vibrator heads that will not damage epoxy coatings.

Concrete may be placed directly into drilled shaft foundations and piles without mechanical vibration; except, vibrate the top 5 feet of concrete. For drilled shaft foundations, consolidate the top 5 feet of concrete after good quality concrete is evident at the top of the shaft and after water, slurry, drilling aids, and other materials other than concrete have been removed.

501-3.07 FINISHING CONCRETE SURFACES. After the concrete is consolidated and prior to the application of curing materials, strike-off unformed concrete surfaces to the required elevation and slope. Finish the surface by floating the surface to remove local irregularities and leave sufficient mortar to seal the concrete surface. Do not use mortar topping for concrete surfaces. Do not use aluminum finishing equipment.

Complete initial floating operations before bleed water or excess moisture is present on the surface and before the concrete takes initial set. Complete final finishing before final set occurs. Do not use finishing aids or additional water to assist in finishing concrete surfaces. Do not finish concrete surfaces if bleed water, excess moisture, or curing materials are present.

- Provide formed concrete surfaces with an ordinary finish unless otherwise noted.

1.	Ordinary Finish. An ordinary finish is the finish left on a surface after removing the forms, filling the holes left by the form ties, and repairing defects. Ensure the surface is true and even and free from rock pockets and depressions or projections.

Immediately after removing the forms, remove the metal devices holding the forms in place and passing through the body of the concrete, or cut them back at least 1 inch beneath the surface of the concrete. Remove fins of mortar and irregularities caused by form joints.

Patch cavities produced by form ties, depressions, holes, and voids greater than 1/4 inch. Fill the cavity with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand. Clean the cavity and saturate the concrete with water before filling the cavity. Thoroughly tamp the mixture into place. Float the surface of the mortar before initial set to make the surface neat in appearance. Cure the patch according to Subsection 501-3.08.

Do not repair concrete with rock pockets, cracks, or other defects until the concrete is inspected by the Engineer. Concrete repaired prior to inspection by the Engineer may be rejected. If, in the opinion of the Engineer, the defect will affect the strength or durability of the concrete, the Engineer may reject the concrete, the structure, or portion of the structure. If the defect is greater than 3/4 inch in depth, submit a repair plan including complete details of the method, materials, and equipment proposed for use in repairing the concrete. Obtain the Engineer's approval of the repair plan before repairing the defect. A repair plan is not required if the defect is 3/4 inch or less in depth.

Repair broken corners and edges, rock pockets, and other defects. If the defect is greater than 3/4 inch in depth, repair the defect according to the approved repair plan. If the defect is 3/4 inch or less in depth, chip away coarse or broken material according to Subsection 501-3.16 to obtain a dense, uniform surface of concrete exposing solid coarse aggregate. Cut feathered edges to form faces perpendicular to the surface. Apply an epoxy bonding agent to the concrete mating surfaces according the manufacturer's instructions. Patch the repaired area with stiff mortar composed of one part of Portland cement to two parts of fine aggregate. Proportion the mortar by loose volume with only enough water to form a small ball when squeezed gently by hand.

- Perform repairs prior to releasing falsework, prestressing, or applying additional loads to the concrete.

2.	Rubbed Finish. Provide a rubbed finish at locations shown on the Plans. When forms can be removed, wet the surface and then rub with a wooden float until irregularities and form marks are removed and the surface is covered with a lather composed of cement and water. A thin grout composed of one part Portland cement and one part fine aggregate may be used. Allow this lather to set for at least 5 days. Then, smooth the surface by lightly rubbing with a fine carborundum stone.

If the concrete has hardened before being rubbed, use a medium coarse carborundum stone to finish the surface at least 4 days after placing the concrete. Spread a thin grout composed of one part Portland cement and one part fine aggregate over a small area of the surface. Immediately rub the surface with the stone until form marks and irregularities are removed and the surface is covered with a lather. Allow this lather to set for at least 5 days. Then, smooth the surface by rubbing lightly with a fine carborundum stone.

- Complete ordinary finish work before applying the rubbed finish.

3.	Concrete Decks and Approach Slabs. Obtain a smooth riding surface of uniform texture, true to the required grade and cross section.

Use a self-propelled mechanical finishing machine:

a.	capable of forward and reverse movement,

b.	with a rotating cylindrical single or double drum screed,

c.	with necessary adjustments to produce the required cross-section, line, and grade,

d.	allowing screeds to be raised and lowered, and

e.	with an upper vertical limit of screed travel permitting the screed to clear the finished concrete surface.

When placing concrete abutting previously placed concrete, equip the finishing machine to travel on the existing concrete.

The Engineer may approve hand-operated motorized roller screeds (friction screeds) where jobsite conditions prohibit the use of conventional configuration finishing machines described above, for small areas less than 12 feet wide, and on approach slabs in which conventional configuration finishing machines are not used to finish the concrete deck. Do not use vibratory screeds.

Use equipment capable of striking off the full placement width without intermediate supports or rails. Use rails resting on adjustable supports that can be removed with the least disturbance to the concrete. Place the supports on structural members or on forms rigid enough to resist deflection. Use supports that are removable to at least 2 inches below the finished surface. If possible, place rails outside the finishing area. If not possible, place them above the finished surface.

Use rails (with their supports) that are strong and stiff enough for operation of the equipment without excessive deflection. Place and secure rails for the full length of the deck before placing concrete. Set the rails to the proper grade and elevations to ensure the required profile is provided.

- After placing and consolidating the concrete, carefully strike off the concrete surface. Correct imperfections left on the deck. Provide a float finish to surfaces receiving a waterproof membrane. Texture other surfaces with a heavy-broom finish perpendicular to the direction of traffic.

Do not place finishing machines or other loads on the screed rail supports or on features supporting fresh concrete after the concrete has initially set and before the concrete attains at least 80 percent of the Specified Compressive Strength.

Do not release falsework or wedges supporting concrete on either side of a joint until each side has cured as specified.

4.	Curb, Sidewalk, and Concrete Barrier Surfaces. Finish exposed faces of curbs, sidewalks, and concrete barriers to true surfaces and provide a broom finish. Broom finish sidewalks perpendicular to the direction of traffic.

5.	Sandblasted Finish. Sandblast the cured concrete surface with hard, sharp abrasive media to produce an even fine-grained surface in which the mortar has been cut away, leaving the aggregate exposed.

6.	Trowel Finish. Trowel the surface smooth and free of trowel marks.

501-3.08 CURING CONCRETE. Maintain a satisfactory moisture content and temperature in the concrete immediately after finishing operations are completed.

1.	Initial Curing Period. Before final curing, ensure the surface of the concrete is kept moist.  Concrete surface is beginning to dry when no bleed water is present and the surface color changes.  If the concrete surface begins to dry before the final curing method can be applied, prevent further loss of moisture by one or more of the following methods:

a.	Fog Spray. Use equipment producing a fog spray from an atomizing nozzle with sufficient velocity to cover the entire concrete surface. Direct the atomized water spray above the concrete surface to allow the fog to drift down to the concrete surface. Do not apply the discharge of the atomized water spray directly at the concrete surface. Continue fogging to maintain the reflective appearance of the damp concrete. Do not allow the surface to dry, or to undergo cycles of drying and wetting. Keep the concrete surface damp, but do not accumulate water until after final set has occurred. Use water meeting the requirements of Subsection 712-2.01.

b.	Evaporation Rate Reducer. Apply a monomolecular film intended specifically as an evaporation rate reducer to entrap bleed water or excess moisture on the concrete surface. Apply the evaporation rate reducer according to the manufacturer’s written instructions. Do not use the evaporation rate reducer during finishing operations or as a finishing aid. Do not use evaporation rate reducers on concrete surfaces receiving a waterproofing membrane such as concrete decks, approach slabs, end diaphragms and decked precast concrete members.

2.	Final Curing Period. Unless otherwise noted, employ the final curing method immediately following finishing operations.

Use wet curing on construction joints, concrete with a mix design water-cement ratio less than 0.40, and concrete decks, approach slabs, and concrete surfaces subject to tire contact in the completed structure. For other concrete, use wet curing, liquid membrane-forming curing, forms-in-place curing, or a combination of these curing methods.

Do not use liquid membrane-forming curing compounds on concrete surfaces to which other materials will be cast against or bonded such as concrete and waterproofing membranes.

In addition to the requirements in this section, precast concrete members may use accelerated curing.

a.	Wet Curing. Until the end of the curing period, provide continuous moisture by:

(1)	watering a covering of heavy burlap blankets or quilted cotton mats,

(2)	keeping concrete surfaces wet with water continuously,

(3)	wetting the outside surfaces of wood forms.

Wait to install curing materials until the concrete has sufficiently hardened to permit such operations without damaging the concrete or marring the finish. While waiting to employ curing materials, maintain the concrete surface moisture as specified for the initial curing period.

Uniformly distribute absorbent materials across the entire concrete surface. Apply water in a manner that will not displace the curing materials or erode the concrete surface. Keep the concrete surfaces continuously wet. Do not allow concrete surfaces to dry or alternate with wetting and drying cycles. Cover the concrete, wooden forms and absorbent material with impermeable sheeting. Use white reflective impermeable sheeting if direct sunlight is present, or if the Engineer determines direct sunlight may be present during the curing period.

Do not use absorbent materials containing harmful substances such as sugar or fertilizer, or materials that may discolor the concrete.

b.	Liquid Membrane-Forming Curing Compounds. Apply liquid membrane-forming compounds immediately after final finishing and as soon as the free water has disappeared, no water sheen is visible, and bleeding has essentially ceased. Apply two coats of liquid membrane-forming compound with the second coat at right angles to the first. Apply both coats of liquid membrane-forming compounds uniformly until the original color of the concrete is obscured. Apply liquid membrane-forming compound according to the manufacturer’s instructions.

Do not apply the liquid membrane-forming compound to dry concrete surfaces. Moisten the concrete surface, without standing water, before applying the liquid membrane-forming compound. Protect the membrane from damage for the duration of the curing period. Re-apply the liquid membrane-forming compound if the membrane is cracked or damaged during the curing period.

c.	Forms-In-Place Curing. Formed concrete surfaces may be cured by retaining the forms in place for the entire curing period. Keep the forms moisture tight. Do not loosen forms. For wooden forms, keep the forms wet as required for wet curing. If gaps develop between the forms or between the forms and concrete:

(1)	remove the forms and implement another curing method

(2)	keep the gaps continuously filled with water for the remainder of the curing period.

d.	Accelerated Curing. Accelerated curing may be used only on Class P Concrete with a water-cement ratio of less than 0.35.

During the curing period, keep the concrete in a saturated curing atmosphere until the concrete achieves the required release strength.

The curing period may be accelerated by using saturated low-pressure steam, convection-heat, or radiant-heat in a suitable curing chamber to contain the live steam or heat. Provide at least 3 inches of clearance between the enclosure and forms to allow adequate circulation.

If accelerated curing methods are used, embed at least one temperature-recording device in the concrete to verify concrete temperatures are within the specified limits. Install one temperature-recording device, accurate to ±5°F, near the member’s midpoint, 6 to 8 inches from the top or bottom, and along the member’s centerline. Monitor the concrete temperature with the temperature-recording device sensor arranged and calibrated to continuously record, date, and identify the concrete temperature throughout the heating cycle. Begin recording temperatures once concrete is placed in the forms. Stop recording temperatures after the heating cycle is complete and when the concrete temperature is within 20°F of the air temperature to which the concrete will be exposed. Upon request, submit the temperature record to the Engineer for each precast concrete member.

While waiting to begin the heating cycle, maintain the concrete temperature between 50°F and 90°F and maintain concrete surface moisture as specified for the initial curing period. Do not apply steam, convection-heat or radiant-heat prior to initial set except to maintain the concrete temperature. Determine the time of initial set according to AASHTO T 197.

Begin the heating cycle immediately after the initial set. Prevent hot air and steam from blowing directly onto the concrete or forms. Increase the concrete temperature at an average rate not exceeding 40°F per hour until the curing temperature is reached. Limit curing temperature within the concrete to 175°F maximum. Decrease the concrete temperature not more than 40°F per hour until reaching a temperature 20°F above the temperature of the air to which the concrete will be exposed.

Apply radiant heat by pipes circulating steam, hot oil, or hot water, or by electric heating elements.

3.	Curing Temperature. To achieve adequate curing, maintain the concrete temperature at or above 50°F during the curing period. Add one additional day of curing for each day or portion of a day the concrete temperature falls below 50°F during the curing period.

4.	Ending Curing Operations. Continue curing operations uninterrupted until the required concrete properties, strength, and durability have developed or until there is reasonable assurance these properties will be achieved after the curing operations have been terminated.

Curing operations may be terminated after both of the following are satisfied:

a.	The concrete has cured for:

(1)	at least 7 days.

(2)	at least 10 days when fly ash or ground granulated blast furnace slag in excess of 10 percent by weight of the Portland cement are used in the mix.

b.	The compressive strength from informational field tests reaches the following:

(1)	70 percent of the Specified Compressive Strength if post curing concrete temperature is expected to remain at or above 50°F until 100 percent of the Specified Compressive Strength is attained.

(2)	100 percent of the Specified Compressive Strength, if post curing conditions are expected to allow the concrete temperature to fall below 50°F before 100 percent of the Specified Compressive Strength is attained.

501-3.09 PROTECTION OF CONCRETE. Protect concrete from damage. Do not apply loads to the concrete for at least 7 days, until curing operations are completed, and until the Engineer determines the concrete has attained sufficient strength to safely carry the applied loads without damage. Unless otherwise noted, sufficient strength is attained when the concrete has a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

- Release forms and falsework according to Section 512.

During the curing period, protect concrete from damaging mechanical disturbances. Protect concrete surfaces from damage by construction traffic, equipment, materials, rain or running water, and other adverse weather conditions. Meet the vibration limits during pile driving of Section 505.

Do not backfill against concrete structures until the end of the curing period and until the concrete has attained a compressive strength, determined from informational field tests, of at least 80 percent of the Specified Compressive Strength.

Obtain authorization from the Engineer before driving vehicles or equipment, or storing materials on the structure. Keep the structure closed to traffic until the concrete has been accepted. Obtain authorization from the Engineer before opening the structure to traffic.

1.	Rain Protection. Provide materials and equipment on site to protect concrete until final set.  During precipitation, or when the Engineer determines precipitation is likely before final set, employ materials and equipment to protect the concrete until final set occurs. Do not expose the concrete to rain or flowing water before final set occurs.

2.	Cold Temperature Protection. When air temperatures are expected to be below 35°F during concrete placement or the curing period, have materials and equipment in place to prevent the concrete temperature from falling below 35°F. Implement the cold temperature concreting plan when the air temperature in the shade, away from artificial heat, is less than 35°F or, in the opinion of the Engineer, is likely within 24 hours.

a.	Submittals. Submit a cold temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to be below 35°F during the concrete placement or during the curing period. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during cold weather for each concrete placement. Include procedures for abrupt changes in weather conditions and equipment failures.

b.	Preparation. Remove snow, ice, and frost from surfaces that will touch the concrete. Before beginning concrete placement, thaw the subgrade to at least 2 feet below the concrete to be placed. Do not place concrete around or adjacent to forms, embedded items, concrete, steel, or other materials unless such items are preheated and maintained at a temperature above 35°F.

c.	Temperature of Concrete Before Placement. Ensure concrete is between 50°F and 70°F during placement. Obtain these temperatures by heating the mixing water and/or aggregate. Heat mixing water to no more than 150°F.

When the temperature of the water or aggregate exceeds 100°F, mix them together so temperature of the combined ingredients does not exceed 80°F when the cementitious materials are added.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to cold weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

If the minimum curing temperature cannot be maintained, do not allow the concrete temperature to drop below 35°F. Provide extra protection in areas especially vulnerable to temperatures below 35°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Maintain the concrete temperature using methods such as insulated forms, enclosures, and indirect heat. When using combustion heaters, vent flue gases to the outside of the enclosure. Prevent overheating areas of concrete or drying during the curing period by directing heaters and ducts away from the concrete surface. Do not expose the concrete surface to air with a temperature more than 90°F, unless higher values are allowed according to the curing method.

Protection may be terminated when the air temperature in the shade, away from artificial heat is rising, above 35°F, and is expected to remain above 35°F until the end of the curing period. At the end of the protection period, remove the protection so the concrete surface drops in temperature gradually at a rate not more than 1.25°F per hour until the concrete temperature is within 20°F of the air temperature in the shade, away from artificial heat. If water curing is used, terminate the addition of water to the surface and allow the concrete surface to dry prior to exposure of the concrete to freezing temperatures.

3.	Hot Temperature Protection. When air temperatures are expected to exceed 90°F during concrete placement, have materials and equipment in place to prevent the concrete temperature from exceeding 90°F before final set and exceeding 150°F during the final curing period. Implement the hot temperature concreting plan when the air temperature in direct sunlight is greater than 90°F.

a.	Submittals. Submit a hot temperature concreting plan at least 5 days before placing concrete when the air temperature is expected to exceed 90°F during the concrete placement. Submit detailed procedures for the production, transport, placement, protection, curing, and temperature monitoring of concrete during hot temperature for each concrete placement. Include procedures for abrupt changes in temperature conditions or equipment failures.

b.	Preparation. Prior to placing concrete, plan to minimize the exposure of the concrete to hot temperatures and direct sunlight. Cool surfaces that will touch the concrete to less than 90°F.

Do not sprinkle fine aggregate piles with water. If sprinkling coarse aggregates, monitor the moisture content and adjust the mixing water for the free water in the aggregate.

If replacing all or part of the mixing water with crushed ice, then ensure the ice is completely melted and thoroughly mixed with the other concrete materials before concrete placement commences.

c.	Temperature of Concrete Before Placement. Ensure concrete being placed in forms is between 50°F and 90°F. Obtain these temperatures by cooling the mixing water and/or aggregate.

d.	Temperature of In-place Concrete. Protect the concrete from damage due to hot weather immediately after concrete placement and ensure adequate curing conditions are maintained as required in Subsection 501-3.08.

Provide extra protection in areas especially vulnerable to temperatures above 90°F such as exposed top surfaces, corners and edges, thin sections, and concrete placed against steel.

Protection may be terminated when the air temperature in direct sunlight drops below 90°F and is expected to remain below 90°F for at least 24 hours.

501-3.10 TOLERANCES. Produce concrete elements conforming to the following tolerances:

1.	Length: ±3/4 inch for members 100’ and shorter.   ±1 inch for members longer than 100’

2.	Cross-sectional Dimensions:

a.	For dimensions 6 inches or less: -1/8 inch to +1/4 inch.

b.	For dimensions over 6 inches but not over 18 inches: -1/8 inch to +3/8 inch.

c.	For dimensions over 18 inches: -1/4 inch to +3/8 inch.

3.	Distortion of Cross-section: Limit the slope with respect to the specified surface, plane, or line to less than ±1/16 inch per foot, but not to exceed ±1/4 inch measured perpendicular to the long axis of member.

4.	Surface Irregularities (deviation from a 10-foot straight edge):

a.	For surfaces receiving a topping or are buried: ±1/4 inch.

b.	For surfaces not receiving a topping or are visible in the completed work: ±1/8 inch.

5.	Camber: Do not vary from the approved camber more than ±1/8 inch per 10 feet of length, but not to exceed 1 inch. In addition, the camber of each girder may not differ from the camber or the other girders by more than 1 inch.

6.	Lateral Sweep (deviation from a straight line parallel to centerline of member):

a.	For member length 40 feet or less: ±1/4 inch.

b.	For member length over 40 feet but not over 60 feet: ±3/8 inch.

c.	For member length over 60 feet: ±1/2 inch.

7.	Deck Width (measured out-to-out): Zero to +2 inches, except not more than +1/2 inch where more precision is dictated by the substructure details such as anchor bolts, parallel wing walls, etc.

8.	Position and Alignment:

a.	Bottom of footing elevation: ±0.1 feet.

b.	Profile grade: ±0.05 feet.

c.	Lateral position: ±0.1 feet.

d.	Skew: ±0.05 degrees.

9.	Bearing Seats:

a.	Elevation: ±0.01 feet

b.	Variation between bearing seats: Do not vary from a straight line coincident with the centerline of bearings and parallel to the surface of the bottom flanges more than 0.01 feet.

c.	Grade and cross slope: ±0.005 feet per foot.

10.	Openings:

a.	Size of opening: ±1/4 inch.

b.	Location of centerline of opening: ±1/2 inch.

11.	Embedded Items:

a.	Bolts: ±1/4 inch.

b.	Utility hangers: ±1/2 inch.

c.	Weld Plates: ±1/2 inch measured along the length of the member, ±1/8 inch measured perpendicular to the length of the member.

d.	Inserts: ±1 inch.

e.	Rail post anchor plates: ±1/4 inch.

f.	Expansion joints: ±1/8 inch.

g.	Electrical conduits: ±1/2 inch.

h.	Deck drains: ±1/2 inch.

i.	Other embedded items: ±1/2 inch.

501-3.11 CONSTRUCTION JOINTS. Unless otherwise noted, locate construction joints where specified in the Contract documents. Obtain approval before adding, deleting, or relocating construction joints specified in the Contract documents. Make requests for such changes in writing, accompanied by a drawing depicting the joint. The Engineer will evaluate the proposed construction joint to determine if the joint will affect the strength or durability of the concrete. Joints noted as "permissible" do not need the Engineer's approval before deleting. When permitted, place the joints where they will not be exposed to view in the finished structure.

At horizontal construction joints, place gage strips 1-1/2 inches thick inside the forms along exposed faces to give the joints straight lines.

- Do not use wire mesh forming material.

If the Plans require a roughened surface on the joint, create grooves at right angles to the length of the member. Make grooves that are 1/2 to 1 inch wide, 1/4 to 1/2 inch deep, and spaced equally at twice the width of the groove. Terminate the grooves within 1-1/2 to 2 inches from the edges of the joint.

- If the Plans require a smooth surface on the joint, provide a trowel finish.

Include shear keys at the joint when the Contract documents do not require a roughened surface or a smooth surface. Make shear keys of formed depressions with slight beveling to ensure ready form removal. Do not use raised shear keys. Make shear keys that meet the following:

1.	For tops of beams, at the tops and bottoms of boxed girder webs, in diaphragms, and in crossbeams, use shear keys 1-1/2 inches deep, 8 inches long, and spaced at 16 inches.

2.	In other locations, use shear keys at least 1-1/2 inches deep and 1/3 of the joint width.

- Terminate the shear keys within 1-1/2 to 2 inches of the joint edge.

Clean construction joints of surface laitance and other foreign materials before fresh concrete is placed against the surface of the joint. Flush construction joints with water and allow the joint to dry to a surface-dry condition immediately prior to placing concrete.

501-3.12 FORMS AND FALSEWORK. Use forms and falsework designed and constructed according to Section 512.

501-3.13 PRECAST CONCRETE MEMBERS. In addition to the requirements listed in this Section, conform to Section 502 when fabricating prestressed concrete members.

1.	Shop Drawings. Provide shop drawings for precast concrete members. Include details not provided in the Plans for the construction and erection of the members. Cast members only after shop drawings are approved. Use precast methods for cast-in-place elements when approved. Submit shop drawings, showing construction joint details and other required information.

2.	Manufacture. Prestress concrete according to Section 502. Fabricate and install reinforcing steel according to Section 503.

Unless otherwise noted, use Class P concrete for precast concrete members meeting the Specified Compressive Strength noted on the Plans.

3.	Storage and Handling. Handle and move precast concrete members without damage. Store and transport precast concrete members in an upright position with the directions of the support reactions on the member during storage or transport as if in the final position. Locate support points during transport and storage within 30 inches of their final position, or as shown on approved shop drawings. Ship only after the member has cured at least 7 days and has a compressive strength not less than 100 percent of the Specified Compressive Strength.

4.	Erection. Maintain member stability during transport, lifting, and erection operations. Limit concrete tension stresses due to transport, lifting, and erection operations to less than 500 psi.

Set interchangeable precast concrete members so the initial difference between the top surfaces of the edges of adjacent precast concrete members is no more than 1/2 inch at midspan and no more than 1/4 inch at the bearings.

Set and securely brace precast concrete members within a span before making shear connections. Secure the member to the structure, and provide temporary braces necessary to resist wind or other loads immediately after erecting each precast concrete member.

Provide and use forcing devices as shown in the Plans or as recommended by the precast concrete member manufacturer. Use devices maintaining the top edges of adjacent members at the same elevation while casting or welding diaphragms, welding shear connector plates, and while placing and curing grout in the shear keys.

- Make field welds according to Section 503 and Section 504.

Install cast-in-place diaphragms within 2 weeks after setting precast concrete members on their bearings.

If cast-in-place diaphragms cannot be placed within the prescribed time limit, ensure the members are adequately braced to resist movement and rotation. Submit a bracing plan including complete details and substantiating calculations, sealed by a Professional Engineer registered in the State of Alaska.

Erect and place precast deck panels so the mating surfaces do not allow grout leakage. Seal joints where grout leakage may occur.

When the Plans require filling keyways between adjacent concrete members with grout, place grout according to the manufacturer's written instructions. Clean joints of surface laitance and other foreign material before placing grout. Do not place loads on the grouted members until the grout compressive strength has reached 5000 psi.

Tightly pack and rod the grout in the keys and spaces. Keep the grout surface smooth and neat. Ensure the grout surface meets the member edges throughout their lengths and matches the surface elevation of the members with a tolerance of ±1/8 inch.

501-3.14 PLACING ANCHOR BOLTS. Secure anchor bolt assemblies where shown on the Plans.

When casting anchor bolts in concrete, secure anchor bolts before placing concrete in the forms. Do not disturb anchor bolts after concrete has been placed.

When installing anchor bolts in pipe sleeves, pre-cast holes, cored holes, or drilled holes, completely fill the cavity with grout. Do not allow water to freeze in the cavity. Do not allow foreign material in the cavity.

501-3.15 UTILIDUCTS, PIPES, CONDUITS, DUCTS, AND UTILITY HOLES. When utiliducts, pipes, conduits, and ducts will be encased in concrete, install them in the forms before placing the concrete. Support the utiliducts, pipes, conduits, and ducts to prevent displacement during concrete placement.

Install utiliducts and utility holes parallel to the roadway centerline unless noted otherwise. Prevent bond between the utiliducts and concrete by tightly wrapping the utiliducts with at least two layers of asphalt felt.

501-3.16 REMOVING CONCRETE. Do not damage other portions of the structure remaining in place when removing concrete.

Determine and delineate the extent of removal area. Outline the area with a 3/4-inch deep saw cut to form faces perpendicular to the surface prior to the removal of concrete. Do not cut or damage existing reinforcing steel or prestressing steel. During the course of removal, the Engineer may suspend removal or may require additional removal and outline saw cut.

Use any combination of mechanical methods, water-blast cleaning, or abrasive-blast cleaning to remove coarse or broken concrete until a dense, uniform surface of concrete exposing solid coarse aggregate is obtained. When using mechanical methods for removal of concrete, meet the following:

1.	Use impact tools weighing less than 15 lbs.

2.	Operate impact tools at an angle less than 45 degrees relative to the surface of the concrete being removed.

3.	Use hand tools such as hammers and chisels or small air chisels, water blast cleaning, or abrasive blast cleaning to remove final particles of unsound concrete.

During the removal operation do not damage existing reinforcing steel, prestressing steel, or concrete to remain in place.

- Before applying the repair material, clean the surface according to ASTM D 4258 within 24 hours of applying the repair material.

- Use water meeting the requirements of Subsection 712-2.01 for removal operations.

501-3.17 CRACK EVALUATION. The Engineer will evaluate concrete that is cracked during execution of the Contract. Measure cracks at their widest point.

For concrete decks and approach slabs, allow the Engineer to inspect any surface cracking immediately after termination of concrete curing operations, before prestressing (if applicable), and before releasing falsework. If any 500 square foot portion of the concrete deck or approach slab has cracks, whose width exceeds 0.020 inches and combined lengths total more than 16 feet, treat the surface by performing low-viscosity resin crack repair.

- For other concrete, cracks will be evaluated based on the crack width.

1.	For crack widths equal to and greater than 0.060 inches, the concrete will be considered unacceptable.

2.	For cracks widths equal to and greater than 0.013 inches but less than 0.060 inches, the Engineer will evaluate the cracked concrete for structural adequacy and durability. If the Engineer determines the crack may affect structural adequacy or durability, the Engineer may reject the concrete, the structure, or a portion of the structure. If the Engineer determines the cracked concrete is acceptable, repair the crack by performing low-pressure crack repair according to 501-3.18.

3.	For cracks widths less than 0.013 inches wide, the crack will be considered acceptable with no additional evaluation or repairs required.

501-3.18 CRACK REPAIR. Perform crack repairs and replace unacceptable concrete at no cost to the Department. No contract time extension will be given for repairing, removing, and replacing unacceptable material.

- 1.	Low-Pressure Crack Repair. Repair cracked concrete according to the following requirements:

a.	Crack Repair Plan. Submit a crack repair plan to the Engineer. Do not repair the crack until the Engineer has approved the crack repair plan. Include the following in the crack repair plan:

(1)	Experience of the injection equipment technicians

(2)	Evaluation of the crack width and the recommended epoxy viscosity allowing the epoxy to achieve and maintain the penetration requirements

(3)	Material information including manufacturer's product data sheets

(4)	Equipment

(5)	Crack preparation, injection procedures, and injection sequence

(6)	Cleanup procedures

b.	Experience. Provide epoxy injection technicians who have a minimum of 2 years experience in performing repairs using the methods and materials of the selected system.

c.	Materials. Use epoxy adhesive for crack sealing meeting the requirements of Subsection 501-2.01.5 and capable of containing the crack injection epoxy. Use epoxy adhesive for crack injection meeting the requirements of Subsection 501-2.01.5 and of viscosity capable of filling at least 90 percent of the crack volume.

d.	Equipment. Use positive displacement plural component pumps, specifically designed to meter, mix, and to inject epoxy, and capable of filling at least 90 percent of the crack volume.

e.	Surface and Crack Preparation. Remove contaminants and other foreign material reducing the effectiveness of the surface seal and repaired crack. Allow adequate time for drying. If cleaning solutions are used, perform trial tests to verify the contaminants can be removed. Prepare the surface and crack according to the epoxy manufacturer’s instructions.

f.	Entry and Venting Ports. Install entry/venting ports spaced equal to the thickness of the concrete member along one face of the crack. Acceptable types of entry/venting ports are fittings inserted into drilled holes, bonded flush fittings, and gasket devices covering unsealed portions of interrupted seals, allowing injection of epoxy directly into the crack without leaking epoxy.

g.	Mixing Epoxy for Crack Sealing. Mix the epoxy adhesive for crack sealing to the volume ratio prescribed by the manufacturer.

h.	Surface Sealing. Seal the surface of the crack with epoxy adhesive for crack sealing.

i.	Mixing Epoxy for Crack Injection. Mix the epoxy adhesive for crack injection to the volume ratio prescribed by the manufacturer.

j.	Epoxy Injection. Assure the crack seal is cured and capable of containing the crack injection epoxy. Inject the epoxy according to the epoxy manufacturer’s instructions. Do not inject epoxy until the air, substrate, and epoxy are within the manufacturer's application temperature range. Limit injection pressure to prevent propagation of the crack, prevent additional damage, and injection pressure in excess of 50 psi.

Inject the epoxy in the sequence noted in the approved crack repair plan. Ensure at least 90 percent of the crack volume is filled.

Maintain the epoxy temperature within the manufacturer's application temperature range during injection operations and until the epoxy is cured.

k.	Finishing and Cleanup. After the injected epoxy is cured, remove ports and surface seal flush with the concrete surface. Do not damage the injected epoxy and do not heat the surface seal to aid in removal.

- 2.	Low-Viscosity Resin Crack Repair. When concrete deck or approach slab crack repair is required, the Engineer will define the repair area with the following boundary limits:

a.	Beginning and ending on straight lines perpendicular to the direction of traffic and extending across the entire width of the concrete deck or approach slab, between the concrete barriers or curbs.

b.	Beginning and ending at least 5 feet beyond the furthest opposing cracks, measured from where the crack widths exceeds 0.020 inches

- If grinding is required, treat the concrete before grinding.

Before treatment, ensure the concrete surface is clean, sound and free of foreign materials that may reduce the effectiveness of the repaired cracks. If the concrete surface becomes contaminated before placing the resin, repeat the cleaning process.

Apply low-viscosity resin to the repair area. Protect barriers, railing, joints, and drainage facilities to prevent contamination by the treatment material.

Completely cover the deck surface with resin so the resin penetrates and fills cracks. Ensure the relative humidity is less than 80 percent, the prepared area is dry, and the surface temperature is at least 50°F and not more than 90°F when the resin is applied. Apply the resin and distribute excess material within the manufacturer's listed pot life. For textured surfaces, including grooved surfaces, remove excess material from the texture indentations.

For concrete decks and approach slabs not receiving a waterproofing membrane, apply aggregate for abrasive finish within 20 minutes of resin application and before setting occurs. Broadcast the aggregate for abrasive finish evenly over the entire treated area at a rate of 1.5 to 2.5 pounds per square yard.

501-3.19 CLEANUP. Remove concrete splatter, paint marks, laitance, rust staining, chamfer strips, and other material not providing a uniform texture and color to the concrete surface.

## SECTION 502

## PRESTRESSING CONCRETE

502-1.01 DESCRIPTION. Furnish, place, and tension prestressing steel for pretensioning precast concrete or post-tensioning cast-in-place concrete.

502-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501

Reinforcing steel 	Section 503

Portland Cement	Section 701

Grout	Section 701

Prestressing Steel and Fittings	Section 721

Corrosion inhibitor 	Federal Specification MIL-P-3420F-87

Approved Ducts	AASHTO LRFD Bridge Design Specifications

Expanded polyethylene material: Closed-cell expanded polyethylene planks with a density of 2.2 (±0.2) lb/ft3 as determined by ASTM C 271. Use planks that have a maximum compressive deflection of 50% at 15 (±3) psi, and that do not retain a compression set of more than 15% of the plank thickness after maintaining 50% compression deflection for 22 hours with a following 24-hour recovery period, as determined by ASTM D 1056. Use planks that have a maximum water absorption by weight of 10% as determined by ASTM C 272.

- CONSTRUCTION REQUIREMENTS

502-3.01 PRESTRESSING METHODS. Select a prestressing method that provides the magnitude and distribution of prestressing force and ultimate strength without exceeding allowable temporary stresses, subject to the requirements in this specification.

Perform the prestressing by either pretensioning or post-tensioning methods, or a combination of the two methods.

- 1.	Submittals.

a.	Working Drawings. Before casting members to be prestressed, submit for approval working drawings including complete details and substantiating calculations of the method, materials, and equipment proposed for use in the prestressing operations, any additions or rearrangement of reinforcing steel, and any revision in concrete dimensions.

Include an outline of the method and sequence of stressing, complete specifications and details of the prestressing steel and anchoring devices to be used, anchoring stresses, strand release sequence, type of enclosures, and other data pertaining to the prestressing operations, including the proposed arrangement of the prestressing units in the members. Include conformance test data for the post-tensioning system, conforming with Subsection 721-2.05.

Compute the anticipated camber at the time of prestressing force transfer and at other significant times. Show the values on the shop drawings as a time/deflection curve, subject to approval.

Include on working drawings embedded items such as the post-tensioning ducts, vents, anchorage reinforcement and hardware, reinforcing steel, anchor bolts, earthquake restrainers, deck joint seal assemblies, drainage systems, utility conduits and other such items. Ensure there will be no conflict between the planned positions of any embedded items and that concrete cover will be adequate.

b.	Quality Control Program. Submit for approval a quality control program that verifies that all materials and workmanship incorporated into the precast prestressed concrete members conform with the requirements.

502-3.02 Fabrication.

1.	General. Place reinforcing steel according to the requirements of Section 503. Produce and place concrete for prestressed concrete structural members according to the requirements of Section 501. Both are subject to the modifications and amendments contained in this specification.

Before depositing concrete in the forms, obtain an inspection and approval of the placement of the reinforcing, enclosures, anchorages, and prestressing steel.

Provide a technician, skilled in the prestressing method, to aid and instruct in using the prestressing equipment and in installing the materials to obtain required results.

2.	Placing Ducts, Prestressing Steel, and Anchorage Hardware. Rigidly support ducts in the forms by ties, supplementary support bars, and hold-down ties to prevent displacement during concrete placement and to maintain proper alignment of the duct.

Couple joints between sections of duct with positive connections that do not result in angle changes at the joints and that will prevent the intrusion of cement paste.

Vent all ducts for continuous structures at the high points of the duct profile, except where the curvature is small. Install drains at low point in ducts.

Remove the ends of vents and drains 1 inch below the surface of the concrete after grouting is completed. Fill the void with mortar.

Install prestressing steel accurately in the forms and hold in place by the stressing jack or temporary anchors and, when tendons are to be draped, by hold-down devices.

Set and hold anchorage devices or block-out templates for anchorages with their axes parallel to the axis of the tendon, and anchor plates perpendicular to the tendon.

Ensure prestressing steel installed in members or ducts, but not grouted within 10 days, is continuously protected against rust or other corrosion by means of a corrosion inhibitor placed in the ducts or directly applied to the steel. Protect the prestressing steel until grouted or encased in concrete.

Seal the openings at the ends of the ducts to prevent entry of moisture after tendons are placed in ducts. Install steel for post-tensioning until after steam curing is completed.

3.	Tensioning. Tension prestressing steel using hydraulic jacks to produce the forces on the approved working drawing with appropriate allowances for all losses. For post-tensioned work, the losses must also include the anchor set loss appropriate for the anchorage system employed.

You may use the following formula to estimate the stress losses due to friction between the duct and prestressing steel:

- To = Tx e(KL+ua)

- Where: 	To = Steel stress at jacking end

Tx = Steel stress at any point x

e = Base of Naperian logarithms

u = Friction curvature coefficient

a = Total angular change of prestressing steel profile in radians from jacking end to point x

L = Length of prestressing steel element from jacking end to point x

K = Friction wobble coefficient per foot of prestressing steel

Values of K and u to be applied in the preceding formula are listed in Table 502-1.

- TABLE 502-1

| Type of Steel | Type of Duct | K | u |
| --- | --- | --- | --- |
|  | Bright metal sheathing | 0.0020 | 0.30 |
| Wire cables | Galvanized metal sheathing | 0.0015 | 0.25 |
|  | Greased or asphalt- coated |  |  |
|  | and wrapped | 0.0020 | 0.30 |
|  | Direct contact with concrete | 0.0015 | 0.45 |
|  | Bright metal sheathing | 0.0003 | 0.20 |
| High-strength | Galvanized metal sheathing | 0.0002 | 0.15 |
| bars | Direct contact with concrete | 0.0005 | 0.40 |
|  | Bright metal sheathing | 0.0015 | 0.25 |
| Galvanized | Galvanized metal sheathing | 0.0010 | 0.20 |
| strand | Direct contact with concrete | 0.0015 | 0.50 |

Use jacks equipped with pressure gauges or other devices for measuring jacking force. Calibrate all devices, whether hydraulic jack gauges or otherwise. If necessary, recalibrate the devices to permit the stress in the prestressing steel to be computed at all times. Include a certified calibration curve with each device.

Ensure that the tension load indicated by the gauge(s) is within 5% of the calculated tension load based on elongation measurements for each tendon.

Limit the strand stress in pretensioned members before seating (jacking stress) to 80 percent of the minimum ultimate tensile strength (0.80 f ′s) of the prestressing steel.

Limit the standard stress in post-tensioned members prior to seating (jacking stress) and the stress in the steel immediately after seating to the values allowed in AASHTO LRFD Bridge Design Specifications.

Apply or transfer prestressing forces to the concrete after the concrete has attained the strength specified for initial stressing.

- Provide a record of gauge pressures and tendon elongations for each tendon for review.

Determine the stress in tendons during tensioning by the gauge or load cell readings and verify with the measured elongations using the modulus of elasticity, based on nominal area, as furnished by the manufacturer for the lot of steel being tensioned, or as determined by a bench test of strands used in the work.

Use a dynamometer or other approved method to measure the initial force so that its amount can be used as a check against elongation computed and measured. Mark each strand prior to final stressing to permit measurement of elongation and to ensure all anchor wedges set properly.

- Pretensioning. Stress strands by either single strand stressing or multiple strand stressing.

Bring all strands to be stressed in a group (multiple strand stressing) to a uniform initial tension, prior to being given their full pretensioning, that is within the range specified and sufficient to eliminate all slack and equalize the stresses in the tendons.

Use approved low-friction devices at all points of change in slope of tendon trajectory when tensioning draped pretensioned strands, regardless of the tensioning method used.

Tension draped strand from both ends of the bed if the load, as determined by elongation measurements, is more than 5 percent less than that indicated by the jack gages. Ensure the computed load from the sum of elongation at both ends is within 5 percent of that indicated by the jack gages.

Permit only one splice per strand when using single strand jacking. Splice all strands or splice no more than 10 percent of the strands when multistrand jacking is used. Splice strands with similar physical properties, from the same source, and with the same “twist” or “lay.” Locate all splices outside of the prestressed units.

Keep the temperature of the strands during tensioning and concrete placement within 25 °F of the concrete temperature. During the interval between tensioning and concrete placement, do not let a temperature drop increase the stress level in the strands more than 0.05 GUTS (guaranteed ultimate tensile strength), nor cause the stress in the strand to exceed 0.75 GUTS.

Cut all pretensioned-prestressing strands flush with the end of the member. Cut or release the elements in an order that minimizes the lateral eccentricity of the pre-stress. Clean and paint the exposed ends of the strand and a 1-inch strip of adjoining concrete.

- Post-Tensioning. Stress all strands in each tendon simultaneously with a multi-strand jack, except for those in flat ducts with not more than four strands. Tension tendons in continuous post-tensioned members by jacking at each end of the tendon. Provide the prestressing steel with permanent protection and bond to the concrete by completely filling the void space between the duct and the tendon with grout.

4.	Grouting. Flush ducts with concrete walls (cored ducts) to ensure that the concrete is thoroughly wetted. Remove water from ducts with oil-free compressed air.

Add water to the mixer first, followed by Portland cement and admixture, or as required by the admixture manufacturer. Mix to obtain a uniform, thoroughly blended grout, without excessive temperature increase or loss of expansive properties of the admixture. Agitate grout continuously until it is pumped. Limit the water content to the minimum necessary for proper placement, and when Type I or II cement is used, to a water-cement ratio of 0.45.

Open all grout and high-point vent openings when grouting starts. Allow grout to flow from the vent nearest the inlet pipe until any residual flushing water or entrapped air has been removed. Cap or otherwise close the vent.

Inject grout at any vent that has been, or is ready to be, capped if the grouting pressure exceeds the maximum recommended pumping pressure to maintain a one-way flow of grout.

Pump grout through the duct and continuously waste at the outlet pipe until no visible slugs of water or air are ejected and the efflux time of the ejected grout, as measured by a flow cone test, if used, is not less than that of the injected grout. Close the outlet and build the pumping pressure to a minimum of 75 psi before the inlet vent is closed.

Ensure the temperature of the concrete is 35 °F or higher from the time of grouting until job-cured 2-inch cubes of grout reach a minimum compressive strength of 800 psi. Ensure the temperature of the grout is below 90 °F during mixing or pumping.

5.	Camber. Camber is the upward deflection which occurs in prestressed concrete flexural members due to the combination of stressing forces and dead load. It does not include dimensional inaccuracies from manufacturing errors.

Form girders so the roadway surface conforms to the indicated grade line with an allowance for 1/2 inch of positive camber at midspan. Form girders to adjust for the predicted long-term camber from loss of prestress and from dead load deflection. When estimating this adjustment, assume that future paving will be applied 3 years after erection.

Control the concrete properties and the placing, curing, curing times, tensioning procedures, and the storage of precast prestressed beam sections. Control these elements so that the shape and amplitude of the deflection curves for all girders will be within specified tolerances and as nearly alike as possible.

Measure camber with the girder supported at bearing points only. When it is impractical to support the girder on its bearing points, you may use alternative support points. Obtain approval of the alternative supports and submit calculations of the effects of the supports on girder camber. Measure actual camber during prestressing force transfer and compare it with computed values and tolerance.

502-3.03 TOLERANCES. Precast prestressed concrete members must conform to the following dimensional tolerances:

- Length: ±3/4 inch (±1 inch for girders longer than 100 feet).

- Girder Width (overall): ±1/4 inch, subject to item 11 below.

- Depth: ±1/4 inch.

- Width of Webs, Stems, and Bottom Flanges: -1/8 inch to +3/8 inch.

- Flange Thickness: +1/4 inch, -1/8 inch.

- Horizontal Alignment (deviation from straight line parallel to centerline of member): 1/2 inch, subject to item 11 below.

- Camber: Do not vary from approved camber more than ±1/8 inch per 10 feet of length with a maximum of 1 inch. In addition, the camber of any girder may not differ from that of any other girder by more than 1 inch.

- Position of Tendons: ±1/4 inch (±1/2 inch where harped strands exit the member).

- Longitudinal Position of Deflection Point for Deflected Strands: ±12 inches.

- Position of Weld Plates: ±1 inch measured along joint. ±1/8 inch transverse to joint.

- Deck Width (measured out-to-out of all girders in the span): +2 inches, except not more than +1/2 inch where more precision is dictated by substructure details such as anchor bolts, parallel wing walls, etc.

- Parallelism of Top and Bottom Flanges: Do not vary the depth of any deck type girder at any transverse cross section more than 1/4 inch, when measured perpendicular from a line coincident with the surface of the bottom flange(s) to the deck surface at the edges of the girder.

## SECTION 503

## REINFORCING STEEL

503-1.01 DESCRIPTION. Furnish and place reinforcing steel according to the Plans.

503-2.01 MATERIALS.

Reinforcing Steel	Subsection 709-2.01

Substitute different reinforcing bars only when authorized. Ensure substitute bars have an area equivalent to the design area, or larger, and meet AASHTO LRFD Bridge Design Specifications.

- CONSTRUCTION REQUIREMENTS

503-3.01 BAR LIST. When the Contract documents include bar lists and/or bending schedules, verify the quantity, size, and shape of all bar reinforcement against the structure drawings and make any corrections before ordering.

Where bar lists and bending schedules do not appear on the Plans, furnish order lists and bending diagrams for approval according to Subsection 105-1.02. Despite approval of the order lists and bending diagrams, be responsible for their accuracy. Bear any expenses for revising material furnished according to lists and diagrams to make the material comply with the design drawings.

503-3.02 PROTECTION OF MATERIALS. Protect reinforcing steel from damage at all times. Before placing it in the work, ensure that the reinforcing steel is free of dirt, loose rust or scale, paint, oil, or other foreign substance.

Handle epoxy-coated bars using systems with padded contact areas for the bars, wherever possible. Use padded bundling bands. Lift bundles with a strongback, multiple supports, or a platform bridge to prevent bar-to-bar abrasion from sags in the bar bundle. Do not drop or drag the bars or bundles. Protect epoxy-coated bars from sunlight, salt spray, and weather exposure.

503-3.03 BENDING. Cut and bend reinforcing bars to the shapes shown in the Contract documents. Reinforcing steel dimensions shown are out-to-out of bar, unless otherwise noted. Meet fabrication tolerances in ACI 315, Detailing Manual. Bend bars when they are cold. Do not field bend bars that are partially embedded in concrete except as shown on the Plans. If the Engineer approves applying heat for field bending reinforcing bars, take precautions to avoid materially altering the physical properties of the steel. Use hooks and bends that conform to the current CRSI Manual of Standard Practice.

503-3.04 PLACING AND FASTENING. Place reinforcing bars as shown on the Plans and securely hold them in position during concrete placing and setting. Tie the bars with No. 14 or No. 16 steel wire. Tie the bars at all intersections around the perimeter of each mat. Elsewhere, tie the bars at not less than 2-foot centers or at every intersection, whichever is greater. Obtain written authorization before welding reinforcing steel.

Maintain distances from the forms using approved precast mortar blocks, metal or plastic chairs, spacers, metal hangers, or supporting wire strong enough to resist movement under construction loads. Use stainless steel metal supports if they extend to the surface of the concrete, or protect them with a plastic coating to prevent corrosion. Do not use wooden supports. Space supports under deck slab reinforcement not more than 4 feet apart in each direction.

Use coated hardware or plastic supports to support and fasten epoxy-coated reinforcing steel. Use hardware coated with plastic, epoxy, or similar material.

As the work progresses, do not place bars on layers of fresh concrete or adjust bars while placing concrete. Securely fasten dowels in position before placing the concrete that will contain the dowels into the form. You may place curb or sidewalk dowels after the deck concrete has received the preliminary finish.

Cover reinforcing steel, other than stirrups or spacers, with 2 inches of concrete, measured from the surface of the concrete to the outside of the bar, unless otherwise shown. Embed stirrups and spacers at least 1 inch clear, except when exposed to earth. The minimum embedment is 1-1/2 inches.

Repair detectable coating damage on epoxy-coated reinforcing steel using patching material that is comparable to the coating material and inert in concrete. Apply according to the patching material manufacturer's recommendation.

503-3.05 SPLICING. Furnish all reinforcement in the full lengths specified. Obtain the Engineer’s written approval before splicing, except for splices shown on the Plans and splices for No. 16 or smaller bars. Stagger splices as far as possible.

1.	Lap Splice. Lap bars to be spliced at least 50 bar diameters, unless otherwise shown on the Plans. If bars are near the top of the beams and girders and have more than 12 inches of fresh concrete below them, lap them at least 70 bar diameters.

2.	Welded Splice. Use welded splices only where shown on the Plans or authorized in writing. Apply radiographic testing to all welded splices. Meet ANSI/AWS D1.4.

3.	Mechanical Splice. Use mechanical splices only where shown on the Plans or authorized in writing. Ensure that such mechanical splices develop at least 1.5 times the specified yield strength of the spliced bar. The Engineer may randomly sample and test mechanical splices.

## SECTION 504

## STEEL STRUCTURES

504-1.01 DESCRIPTION. Construct steel structures and the structural metal portions of composite structures according to the Plans.

Furnish, fabricate, erect, and coat structural metals shown on the Plans, including structural steel of all grades, bolts and fasteners, stud shear connectors, welding, special and alloy steels, metallic electrodes, steel forgings and castings, and iron castings. Furnish, fabricate, and install incidental metal construction and elastomeric material not otherwise provided for, according to the Contract.

504-2.01 MATERIALS. Use materials that conform to the following:

Paint	Subsection 708-2.01

Structural Steel	Section 716

Arc Welding Electrodes	Section 716

Bolts	Section 716

Steel Grid Floors	Section 716

Steel Pipe	Section 716

Galvanized Metal	Section 716

Steel Forgings	Section 718

Steel Pins & Rollers	Section 718

Castings	Section 719

Elastomeric Pads	Section 720

With written approval, substitute a grade of steel, for that specified, for a particular application where it is desired. Substituted steel must be equal or superior in both physical and chemical properties.

504-2.02 TEFLON COATED BEARINGS. When shown on the Plans, furnish bearings with a 3/32 inch thick pad of filled Poly Tetrafluoroethylene (TFE), bonded to the sliding surfaces of the sliding plates, by the manufacturer.

Use a TFE pad meeting the following requirements:

- TFE PAD REQUIREMENTS

| Tensile Strength, minimum | 2000 psi |
| --- | --- |
| Tensile Elongation, minimum | 200% |
| Hardness | 55-65 Shore D |
| Coefficient of Friction (TFE against Stainless Steel), maximum | 0.08 (for loads greater than 1000 psi and speeds less than 1 inch/min.) |
| Compressive Strength (0.2% offset), minimum | 1800 psi |
| Shear Strength (between TFE and steel plate), minimum | 100 psi |

- CONSTRUCTION REQUIREMENTS

504-3.01 FABRICATION.

1.	Shop Inspection. Furnish 30 days notice of when work will begin at the fabrication shop to allow for an inspection.

- Furnish 4 signed copies of mill reports covering all steel used on the project.

2.	General. Fabricate steel main members subject to tensile stress and fracture critical members, except for rolled shapes, at a plant certified under the American Institute of Steel Construction (AISC) Quality Certification Program as “Major Steel Bridge,” with endorsement “F.”

Provide workmanship and finish that equal the best general practice in modern bridge shops. Neatly finish portions of the work exposed to view. Carefully and accurately perform shearing, flame cutting, and chipping.

Store plain or fabricated structural material at the fabricating shop above the ground on platforms, skids, or other supports. Keep it free from dirt, grease, or other foreign matter. Protect it from corrosion.

Ensure that rolled material is straight before being laid off or worked. If straightening is necessary, use methods that will not injure the metal. Do not use material with sharp kinks or bends.

Steel or wrought iron may be flame cut provided a mechanical guide is used to secure a smooth surface. Flame cut by hand only where approved, and smooth the surface by planing, chipping, or grinding. Manipulate the cutting flame to avoid cutting beyond the prescribed lines. Fillet re-entrant cuts to a radius of at least 3/4 inch.

- Ensure that finished members are true to line and free from twists, bends, and open joints.

Plane sheared edges of plates more than 5/8 inch thick and carrying calculated stresses to a depth of 1/4 inch deep. Fillet re-entrant cuts before cutting.

Make sure the surface finish of bearing and base plates and other bearing surfaces that will contact each other or concrete meets the surface roughness requirements as defined in ANSI/ASME B-46.1, surface roughness, waviness and lay, Part I:

Steel slabs	ANSI 2,000

- Heavy plates in contact

in shoes to be welded	ANSI 1,000

- Milled ends of compression

members, stiffeners, and fillers	ANSI 500

Bridge rollers and rockers	ANSI 250

Pins and pin rockers	ANSI 125

Slide bearings	ANSI 125

Face and bring to an even bearing abutting joints in compression members and girder flanges, and in tension members where specified on the drawings. Where joints are not faced, keep the opening at 1/4 inch or less.

Build floor beams, stringers, and girders with end construction angles to the exact length shown on the Plans, as measured between the heels of the connection angles. The permissible tolerance is plus 0 inch to minus 1/16 inch. Where continuity is required, face end connections.

Cold bend load-carrying rolled-steel plates as follows:

Take the rolled-steel plates from the stock plates so that the bendline is at right angles to the direction of rolling.

Bend until the radius of the bends, measured to the concave face of the metal, is not less, and preferably more, than shown in the following table, where T is the thickness of the plate.

| Angle Through Which Plate is Bent | Minimum Radius |
| --- | --- |
| 61-90 degrees | 1.0 T |
| 91-120 degrees | 1.5 T |
| 121-150 degrees | 2.0 T |

- If a shorter radius is essential, bend the plates when hot, but not shorter than a radius of 1.0 T.

Before bending, round the edges of the plate to a radius of 1/16 inch throughout the portion of the plate to be bent.

Fit up and attach end and intermediate stiffeners as shown on the Plans. Do not weld ends of stiffeners and other attachments to flanges unless shown on the Plans.

Where called for on the Plans, stress relieve welded members according to the requirements of the AWS specifications.

3.	Shop Splices. In addition to those shown on the Plans, girder webs and flanges may contain a maximum of 2 shop splices per plate per span. Indicate all splices on the shop drawings. These splices are subject to approval and are subject to the following limitations:

Make splices complete penetration butt welds. Grind flange splices flush. Grind web splices flush on the outside face of exterior girders only. Grind parallel to the longitudinal axis of the girder.

Do not place a bottom flange splice within the middle third of any span. Use tension flange splices only as shown on the Plans or as approved.

Completely weld each element of a girder, such as flange or web, before attaching it to another element.

Make all splices at least 6 inches from the nearest stiffener plate. Offset web and flange splices at least 6 inches.

4.	Pins and Rollers. Turn pins and rollers to the dimensions shown on the drawings. Keep them straight, smooth, and free from flaws.

In pins larger than 9 inches in diameter, bore a hole at least 2 inches in diameter full length along the axis. Bore the hole after the forging has cooled to a temperature below the critical range and before it is annealed. Bore under conditions that prevent injury from too rapid cooling.

Bore pin holes true to the specified diameter, smooth and straight, at right angles with the axis of the member, and parallel with each other. Finish cut the final surface.

Do not vary the distance outside to outside of holes in tension members and inside to inside of holes in compression members more than 1/32 inch from that specified. Bore the holes in built-up members after completing the assembly.

The diameter of the pin hole must not exceed that of the pin by more than 1/50 inch, for pins 5 inches or less in diameter, or 1/32 inch for larger pins.

- Furnish 2 pilot nuts and 2 driving nuts for each size of pin.

5.	Bolt Holes. Either drill or punch bolt holes. Make finished bolt holes 1/16 inch larger than the nominal diameter of the bolt. Ensure holes are clean cut and without burrs or ragged edges. Material with poorly matched holes will be rejected.

When material forming parts of a member is composed of not more than 5 thicknesses of metal, and whenever the thickness of the metal is not greater than 3/4 inch for structural carbon steel or 5/8 inch for alloy steel, either punch or drill the holes to full size.

When there are more than 5 thicknesses or when any of the main material is thicker than 3/4 inch in carbon steel, or 5/8 inch in alloy steel, or when required under paragraph 5 below, subpunch or subdrill the holes 3/16 inch smaller. After assembling, ream them to size or drill them from the solid to full size.

For punched holes, the diameter of the die must not exceed the diameter of the punch by more than 1/16 inch. Ream any holes that must be enlarged to admit bolts.

Ream holes cylindrical and perpendicular to the member. Direct reamers mechanically, where practicable.

Ream and drill using twist drills. Assemble connecting parts requiring reamed or drilled holes and securely hold them while reaming or drilling them. Match mark them before disassembling.

Subpunch (or subdrill if required) holes for field connections and field splices of main truss or arch members, continuous beams, towers (each face), bents, plate girders, and rigid frames while assembled in the shop according to paragraph 9 of this Subsection. Obtain approval of the assembly, including camber, alignment, and accuracy of holes and milled joints before beginning reaming.

Subpunch and ream holes for floor beam and stringer field end connections to a steel template, or ream them while assembled. When partial assembly is permitted, as provided in paragraph 9 of this Subsection, ream holes for web member connections to steel templates.

When using templates to ream field connections of web members of a truss, arch, bent or tower, mill or scribe at least one end of each web member normal to the long axis of the member. Accurately set the templates at both ends from this milled or scribed end. Accurately set and locate templates for reaming gussets of a truss before reaming or drilling them to their true geometric dimensions, as shown on the shop plans.

Ream or drill the full size of the field connection through templates after carefully locating the templates as to position and angle and firmly bolting them. Use exact duplicate templates used to ream matching members or the opposite faces of one member. Accurately locate templates for connections that duplicate so that like members are duplicates and require no matchmarking.

Accurately punch holes full-size, subpunch them, or subdrill them so that after assembling (before reaming), a cylindrical pin 1/8 inch smaller in diameter than the nominal size of the punched hole may be entered perpendicular to the face of the member, without drifting, in at least 75% of the contiguous holes in the same plane. If the requirement is not fulfilled, the badly punched pieces will be rejected. If any hole will not pass a pin 3/16 inch smaller in diameter than the nominal size of the punched hole, the material will be rejected.

Ream or drill holes so that 85% of the holes in any contiguous group after being reamed or drilled show no offset greater than 1/32 inch between adjacent thicknesses of metal.

Provide in steel templates hardened steel bushings in holes accurately dimensioned from the center lines of the connection as inscribed on the template. Use the center lines to locate accurately the template from the milled or scribed ends of the members.

6.	Shop Assembling. Except as modified below, assemble in the shop each main truss, arch member, continuous beam, tower (each face), bent plate girder, and rigid frame. Make milled ends of compression members in full bearing before starting reaming. Completely shop assemble an entire structure, including floor system, when indicated on the Plans or in the Special Provisions. When the Plans or Special Provisions indicate “partial assembly,” assemble trusses, continuous beams, plate girders, and open spandrel arches in lengths of 3 or more abutting panels. The assembled length must be at least 150 feet.

Clean metal surfaces in contact before assembling them. Assemble, pin well, and firmly draw together the parts of a member with bolts before beginning reaming. Take apart assembled pieces, if necessary, to remove burrs and shavings produced by reaming. Keep the members free of twists, bends, and other deformities.

To prepare to shop bolt material punched full-size, spear-ream the bolt holes, if necessary, to admit the bolts. Make the reamed holes no more than 1/16 inch larger than the nominal diameter of the bolts.

Secure end connection angles, stiffeners, and similar parts using shipping bolts to prevent damage in shipment and handling.

Furnish a camber diagram showing the camber at each panel for each truss. Take the camber from actual measurement while the truss is assembled, or base it on calculated values when full assembly is not required.

Allow holes to drift during assembly only as needed to position the parts, and not enough to enlarge the holes or distort the metal. To enlarge holes to admit the bolts, ream them.

Match mark connecting parts assembled in the shop to allow for reaming holes in field connections. Furnish to the Engineer a diagram showing the marks.

- Bolted Connections, High-Strength Bolts. Determine bolt lengths by adding the values given in Table 504-1 to the total thickness of connected material. These values compensate for thickness of nut, bolt point, and washers. Add 5/32 inch to the grip length per each additional flat washer. Adjust the total length to the next longer 1/4 inch increment up to a 5 inch length and to the next longer 1/2 inch increment for lengths over 5 inches.

Fit bolted parts solidly together when assembling them and do not separate them by gaskets or other interposed compressible material. Place hardened washers under the turned element.

- TABLE 504-1

BOLT LENGTH DETERMINATION

| Bolt Diameter (inches) | Added Length (inches) |
| --- | --- |
| 1/2 | 11/16 |
| 5/8 | 7/8 |
| 3/4 | 1 |
| 7/8 | 1-1/8 |
| 1 | 1-1/4 |
| 1-1/8 | 1-1/2 |
| 1-1/4 | 1-5/8 |

Keep assembled joint surfaces, including those adjacent to washers, free of scale except tight mill scale. Clean off dirt, loose rust, burrs, and other defects that would prevent the parts from seating. Keep contact surfaces free of oil, paint, or lacquer.

When the outer face of the bolted parts has a slope of more than 1:20, use a smooth beveled washer in contact with the sloped surface.

Tighten fasteners to give at least the required minimum tension values shown in Table 504-2 when the joint is completed. Use bolts and nuts made by the same manufacturer in a connection.

- TABLE 504-2

REQUIRED BOLT TENSION

| Bolt Size (inches) | Required Minimum Tension (pounds) |
| --- | --- |
| 3/4 | 28,400 |
| 7/8 | 39,250 |
| 1 | 51,500 |

To achieve the minimum tension values shown in Table 504-2, use direct load indicating washers that conform to ASTM F 959. Demonstrate the suitability of the device by testing a representative sample of at least three devices for each diameter and grade of fastener used in the structure. Test with a calibration device capable of indicating bolt tension. Include in the test assembly flat, hardened washers, if required in the actual connection, arranged as those in the actual connection to be tensioned. Demonstrate with the calibration test that the device indicates a tension at least 5% greater than that required by Table 504-2. Follow manufacturer's installation procedures when installing bolts in the calibration device and in all connections. Be careful to properly install flat, hardened washers when using load indicating devices with bolts installed in oversized or slotted holes and when using the load indicating devices under the turned element. The load indicating device will count as one washer for the purpose of determining bolt length.

Place the load indicating device under the bolt head and turn only the nut when tightening the bolt. The device must indicate full tensioning of the bolt when the opening reaches zero.

Install bolts in all holes of the connection and bring them to a snug tight condition. Then, tighten fasteners, progressing systematically from the most rigid part (usually near the center) of the connection to the free edges, or as directed. Keep previously tightened fasteners from relaxing. Multiple systematic tightening cycles may be required.

Do not reuse high-strength bolts. Remove previously fully tightened bolts that were loosened by tightening adjacent bolts. Replace them with new bolts, nuts, and load indicating devices.

- Welding. Perform all welding and Nondestructive Examination (NDE) as specified or shown on the Plans. Conform to the ANSI/AASHTO/AWS Bridge Welding Code D1.5 when welding new steel bridge girders, beams and stringers. Conform to the Structural Welding Code AWS D1.1 when welding all other steel structures.

At least 30 days prior to welding, submit for approval a welding plan that has been signed and stamped by a Certified Welding Inspector (CWI) responsible for Quality Control (QC) and consisting of the following documents:

a.	Quality Control personnel qualifications listing CWI number;

b.	Welding Procedure Specifications (WPS) using forms in AWS D1.1, Sample Welding Forms;

c.	Procedure Qualification Records (PQR) when applicable, using forms in AWS D1.1, Sample Welding Forms;

d.	Welder Performance Qualification Records (WPQR) using forms in AWS D1.1, Sample Welding Forms with the documentation of current welder certification;

e.	Sample daily inspection sheet; and

f.	Type and extent of NDE to be conducted, as required in the specifications.

Perform all Quality Control inspection necessary to ensure the materials and workmanship meet the requirements of the contract documents. Use a CWI for welding inspection.

Correct all deficiencies in materials and workmanship revealed by Quality Control and Quality Assurance inspections without additional compensation.

Furnish all completed Quality Control inspection documents to the Engineer and to the Quality Assurance representative designated by the State (when designated).

Meet Charpy V-notch impact test requirements as shown on the Plans and according to Sections 715 and 716; except that the impact energy values for filler metals must not be less than that of the base metals to be joined, when tested at the same temperature as the base metal.

504-3.02 ERECTION.

1.	General. Provide the falsework and all tools, machinery, and appliances, including driftpins and fitting-up bolts, needed to perform the work efficiently. Erect the structural steel, remove the temporary construction, and do the work to complete the structure, as required by the Contract and according to these Plans and Specifications. Make temporary field welds to structural steel according to the procedures required by these Specifications. Steel with sharp kinks or bends will be rejected. Heat straightening of A 514 or A 517 steel will be governed by special provision when used.

Install stud shear connectors on beams, stringers, girders, diaphragms, and other surfaces that may be used as walkways. Install stud shear connectors after erecting the structural steel and placing the concrete deck forms and before placing the deck reinforcing steel.

2.	Handling and Storing Materials. Store material on skids above the ground. Keep it clean and properly drained. Place girders and beams upright and shore them. Adequately support long members, such as columns and chords, on skids to prevent injury from deflection.

3.	Falsework. Use falsework according to Section 512.

4.	Method and Equipment. Before starting erection work, inform the Engineer of the proposed erection method and the proposed amount and character of the equipment.

Follow handling and erection procedures so as to avoid inducing critical buckling stresses in the girders.

Submit plans for approval showing the erection method. For trusses, except for simple span trusses supported throughout by falsework during erection, submit stress sheets showing the calculated stresses and deflections resulting from the planned erection sequence. Revise the truss as necessary to suit this erection method. Furnish stress sheets and deflection diagrams for any other unusual design or erection method.

The above methods and equipment are subject to the Engineer’s approval. However, even with this approval, maintain responsibility for the safety of the method or equipment and complete the work according to the Plans and Specifications. Obtain approval before doing any work.

5.	Straightening Bent Material. Straighten plates and angles or other shapes using methods not likely to fracture or injure the material. Heat the metal only when the Engineer permits. Do not heat to a higher temperature than what produces a “dark, cherry-red” color.

After heating, cool the metal as slowly as possible. After straightening a bend or buckle, carefully inspect the metal surface for fractures.

6.	Assembling Steel. Accurately assemble the parts as shown on the Plans and follow match-marks. Handle the material carefully to avoid bending, breaking, or otherwise damaging the parts. Do not hammer if doing so will injure or distort the members. Clean bearing surfaces and surfaces to be in permanent contact before assembling the members. Unless erecting by the cantilever method, erect truss spans on blocking placed to give the trusses proper camber. Leave the blocking in place until the tension chord splices have been fully bolted and pinned and all other truss connections have been bolted. Wait to tighten the bolts in splices of butt joints of compression members and bolts in railing until the span has been swung. Fit up and tighten bolted joints as specified in Subsection 504-3.01.7.

7.	Pin Connections. Furnish pilot and driving nuts for use in driving pins. Drive pins so that the members will take full bearing on them. Screw up tight and secure pin nuts as shown on the Plans.

8.	Setting Shoes and Bearings. Place shoes, bearing plates, and elastomeric bearing pads set directly on concrete surfaces on properly finished bearing areas. Float the concrete surfaces on a level plane that varies no more than 1/16 inch from a straightedge placed in any direction across the area. Limit the variation of the finished surface to 1/8 inch from the elevation shown on the Plans. Set the shoes, elastomeric bearing pads, and bearing plates as shown on the Plans in exact position with full and even bearing.

Place under masonry plates grout that meets Subsection 701-2.03. Mix and place grout according to the manufacturer’s written recommendations. Clean concrete areas that will contact the grout. Remove loose or foreign matter that would prevent the bond between the mortar and the concrete surfaces.

Tightly pack the grout under the masonry plates to provide full bearing. After placing, cover exposed surfaces of grout pads with a heavy thickness of burlap saturated with water for 3 days. Do not place a load on the grout until it has attained a compressive strength of 5000 psi.

Locate the anchor bolts in relation to the slotted holes in the expansion shoes to correspond with the temperature during erection. Adjust the nuts on anchor bolts at the expansion ends of spans to permit the span to move freely.

Apply epoxy adhesive, meeting AASHTO M 235, to the bottom surface of the elastomeric bearing pads before placing them. Do not move the pad until the epoxy has cured and full adhesion is achieved.

9.	Attachment of Formwork. When approved, use 1-inch maximum diameter holes in steel girder webs for attaching formwork. Place holes 6 inches minimum clear distance from all horizontal or vertical welds and space them at least 4 feet center to center. Drill or subpunch and ream holes. They may be left open.

Include in the request enough detail of the formwork for determining the stresses that will be imposed on the girder.

504-3.03 PAINTING.

1.	Preparing Metal Surfaces for Painting. Prepare metal surfaces according to Specification SSPC-SP 10, Near White Blast Cleaning to a profile depth of 1 to 3 mils. Use a profile comparator to ensure minimum profile depth. Do not reuse sand or flint abrasives.

Clean grit or shot of contamination before reusing it. Blow dust and grit from the surface with clean dry air. Remove weld spatter and round sharp edges to a smooth curve. To remove contamination, jet wash or scrub with a stiff brush and clear water or brush blast. Remove light rust with a steel brush or mechanical tool.

2.	Schedule of Paint Coats for Metals. Unless otherwise specified, if structural steel will be exposed to weathering, shop-paint it at least 3 coats: prime coat, intermediate coat, and finish coat.

3.	Painting Metal Surfaces.

a.	Time of Application. Apply 1 or more applications of prime coat. Apply the initial application within 4 hours after blast cleaning. Allow at least 30 minutes of drying time between primer applications. Before painting and after preparing the surface, remove any oil, grease, soil, dust, or foreign matter on the surface. If rusting occurs after the surface is prepared, clean the surface again.

Avoid contaminating cleaned surfaces with salts, acids, alkali, or other corrosive chemicals before applying the prime coat and between applications of the remaining coats of paint. Remove any contamination from the surface.

b.	Storage of Paint and Thinner. Store paint and thinner in a separate building or in a room that is well ventilated and free from excessive heat, sparks, flame, or direct sun rays. Keep paints susceptible to damage from freezing in a heated storage space when necessary.

Leave paint containers unopened until required for use. Use open containers first. Seal left-over, partial containers.

- Do not use paint that has begun to polymerize, solidify, gel, or deteriorate.

c.	Mixing and Thinning. Mix paint thoroughly before use and agitate often during application.

Do not transfer paint mixed in the original container until all settled pigment is incorporated into the vehicle. Pouring off part of the vehicle temporarily to simplify mixing, is permitted.

- Mix by mechanical methods, except use hand mixing for containers up to 5 gallons.

Do not use an air stream bubbling under the paint surface to mix paint or keep it in suspension. Remove and discard any skin that has formed in the container. Do not use the paint if the skin exceeds 2% of the paint volume.

When mixing paint, break up all lumps, completely disperse settled pigment, and create a uniform composition. If mixing by hand, pour off most of the vehicle into a clean container.

Lift the pigment in the paint from the bottom of the container using a broad, flat paddle. Break up lumps and thoroughly mix the pigment with the vehicle. Return the poured-off vehicle to the paint by simultaneously stirring or pouring repeatedly from one container to another until the composition is uniform. Inspect the bottom of the container for unmixed pigment.

Wet tinting pastes or colors with a small amount of thinner, vehicle, or paint and thoroughly mix them. Add the thinned mixture to the large container of paint and mix until the color is uniform.

If paint does not have a limited pot life, or does not deteriorate on standing, mix it at any time before use. However, if it has settled, remix it immediately before use. Do not keep paint in spray pots, painters' buckets, etc., overnight. Gather it into a container and remix it before use.

When the engineer deems it necessary to obtain satisfactory application, add paint thinner according to the manufacturer's instructions.

d.	Application of Paint. Use the oldest of each kind of paint first. Apply paint by spraying. Use brushes, daubers, or sheepskins when no other method can properly apply paint in difficult access areas. Use dipping, roller coating, or flow coating only when authorized.

Blast clean all areas with mudcracking in the zinc-rich primer and then paint them with primer to the specified thickness.

After applying the prime coat, apply the intermediate and finish coats to exposed surfaces according to the manufacturer's recommendations.

Apply the intermediate coat in 2 applications. Apply the first application as a mist coat. Apply the second application after the mist coat has dried to a set-to-touch condition.

- Apply the finish coat in 1 application.

Apply paint within the environmental limitations specified by the coating manufacturer. Do not apply paint when the temperature of the steel surface is less than 40 °F or more than 125 °F.

Do not apply paint in fog or mist, when it is raining or snowing, or when the relative humidity exceeds the manufacturer’s recommendations. Do not apply paint to wet or damp surfaces. Do not apply paint on frosted or ice-coated surfaces.

With approval, apply paint in damp or cold weather, and only under the following conditions. Paint the steel under cover and protect and shelter it, or heat the surrounding air and the steel to a satisfactory temperature. Meet the above temperature and humidity conditions. Keep the steel under cover or protected until it is dry or until weather conditions permit its exposure.

Allow to dry any applied paint exposed to freezing, excess humidity, rain, snow, or condensation. Then, remove damaged areas of paint, prepare the surface again, and repaint it with the same kind as the undamaged areas.

Stripe paint before applying each coat of paint. Spot paint edges, corners, crevices, rivets, bolts, welds, and sharp edges before applying the full coat of paint on the steel. Extend striping for at least 1 inch from the edge. Let this stripe coat dry before applying the full coat, if possible. Otherwise, set-to-touch the stripe coat before applying the full coat. However, do not permit the stripe coat to dry long enough to allow the unprimed steel to rust.

Apply each coat of paint as a continuous film of uniform thickness, free of pores. Repaint any thin spots or areas missed in the application. Allow them to dry before applying the next coat.

Wait until each coat of paint is in the proper state of cure or dryness before applying the next coat.

Ensure a minimum dry film thickness of 3 mils and a maximum dry film thickness of 5 mils for each coat of paint. The dry film thickness of the paint will be measured in place with a calibrated magnetic film thickness gauge. If any coat of paint is thinner than specified, obtain the minimum dry film thickness by applying additional coats of paint.

A Tooke gauge may be used to perform destructive testing of each coat’s dry film thickness. Repair damaged areas.

e.	Brush Application. Brush paint areas inaccessible to a spray gun. Work paint into crevices and corners. Paint surfaces not accessible to brushes using daubers or sheepskins. Brush out runs or sags. Leave a minimum of brush marks in the applied paint.

f.	Spray Application of Paint. To apply paint by spraying, use equipment capable of properly atomizing the paint to be applied. Use equipment with pressure regulators and gauges and use air caps, nozzles, and needles recommended by the equipment manufacturer for the material being sprayed. Keep the equipment in satisfactory condition to permit proper paint application. In closed or recirculating paint spray systems, where gas is used under pressure over the liquid, use an inert gas, such as nitrogen.

Provide adequately sized traps or separators to remove oil and water from the compressed air. Drain them periodically during operations. Ensure that the air from the spray gun impinging against the surface shows no water or oil.

Keep paint ingredients properly mixed in the spray pots or containers while applying the paint. Use either continuous mechanical agitation or frequent intermittent agitation.

Adjust the pressure on the material in the pot and adjust the air pressure at the gun for optimum spraying effectiveness. Adjust the pressure on the material in the pot when changing the elevation of the gun above the pot. Keep the atomizing air pressure at the gun high enough to atomize the paint properly but not so high as to cause the paint to fog or the solvent to evaporate, or to cause loss by overspray.

Keep spray equipment clean to avoid depositing dirt, dried paint, and other foreign materials in the paint film. Remove any solvents left in the equipment before applying paint to the surface.

Apply paint in a uniform layer, overlapping at the edge of the spray pattern. During application, hold the gun perpendicular to the surface and at a distance that will deposit a wet layer of paint on the surface. Release the gun’s trigger at the end of each stroke.

- Apply coats free of runs, sags, and dry spray.

g.	Shop Painting. Perform shop painting after fabrication and before the surface is damaged from weather or other exposure.

- Do not paint shop contact surfaces. Paint surfaces to be in contact after field erection.

Apply only a mist coat (0.5 to 0.8 mil dry film thickness) of inorganic zinc-rich primer, meeting SSPC Paint Specification No. 30, Weld-Through Inorganic Zinc Primer, Class 5, on the following surfaces:

- High strength bolted connection contact surfaces

- Top flange steel surfaces

- Areas within 2 inches from the edges to be welded

- Areas where the full 3 coats of paint will interfere with field assembly

- Apply the full paint coats specified to steel surfaces that will contact wood.

- Remove anti-weld spatter coatings before painting.

Before abrasive blasting, grind smooth all metal defects, fins, slivers, burrs, weld spatter, and sharp edges from shearing or similar operations, including flame hardened edges from cutting or burning. Grind flame hardened edges to a 1/16 inch minimum radius. Repair defects that become evident after abrasive blasting or prime coat application. Retexture the surface to match the blasted profile.

Copy erection marks and weight marks on areas that have been previously painted with the shop coat.

h.	Field Painting. If steel surfaces have not received the full paint coats, paint them as soon as possible after erection.

Touch up metal that has been shop coated with the same type of paint as the shop coat. Touch up by cleaning and painting field connections, welds, bolts and all damaged or defective paint and rusted areas.

If concreting or other operations damage any paint, clean the surface and repaint it. Remove concrete spatter and drippings before applying paint.

- Protect wet paint against damage from dust or other detrimental foreign matter.

i.	Drying of Painted Metal. Allow the paint to dry before recoating or exposing it. Do not add a dryer to paint on the job unless the paint specification calls for one. Do not immerse painted metal until the paint has dried. Protect paint from rain, condensation, contamination, snow, and freezing until dry.

j.	Handling of Painted Steel. Do not handle painted steel until the paint has dried except for turning it for painting or stacking it for drying. Minimize damage to paint films from stacking steel members.

Remove paint that is damaged during handling and touch it up with the same number of coats and kinds of paint previously applied.

- Wait until painted steel is dry before loading it for shipment.

Repair damaged galvanized coating per AASHTO M 36, Section 11. Use inorganic zinc rich primer meeting Subsection 708-2.01.

k.	System Durability and Certification. Have the coating manufacturer review the project and the proposed service environment and issue you written recommendations and instructions to properly prepare the surface, apply the coating, and achieve maximum durability on this project.

Certify to the Department that the system was applied according to the manufacturer’s recommendations and instructions. Enclose a copy of the recommendations and instructions with the certificate.

504-3.04 CLEANUP. Upon completion and before final acceptance of the structure, remove falsework and falsework piling down to 2 feet below the finished ground line.

## SECTION 505

## PILING

505-1.01 DESCRIPTION. Furnish and drive piles, including test piles, as specified.  Assist in pile testing

Furnish piles sufficient in length to obtain the required ultimate bearing capacity and to extend to the minimum tip elevation shown on the Plans.

Drive additional test piles, make borings, or make other investigations needed to determine pile lengths required, without extra compensation.

505-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501

Reinforcing Steel	Section 709

Timber Piles	Section 713

Preservatives for Timber	Section 714

Steel Shell	Section 715

Steel Pipe	Section 715

Structural Steel Piles	Section 715

Sheet Piles	Section 715

- CONSTRUCTION REQUIREMENTS

505-3.01 TEST PILES. When called for in the bid schedule, furnish and drive test piles at the locations designated.

Drive test piles to the specified tip elevation or bearing value, as directed, and as follows:

- Before driving the pile, excavate the ground at the test piles to the elevation of the bottom of the footing.

- Drive test piles using the same hammer you will use for service piles.

- Drive required test piles before beginning any other pile driving work on the structure.

Test piles may be included as part of the completed structure if they conform to the requirements for service piles. Cut off test piles not included in the completed structure as directed.

505-3.02 LOAD TESTS. When called for on the Plans, perform pile load tests according to the Special Provisions.

505-3.03 PILE BEARING VALUES. Drive piles to the required ultimate bearing capacity. The required ultimate bearing capacity is the design pile load as indicated on the Plans multiplied by a factor of safety.

The Engineer will determine the pile driving criteria using wave equation analysis. When the wave equation is not used, drive all piles to a bearing value not less than the design load, as shown on the Plans.

When called for in the bid schedule, check bearing values using load tests as specified above. Determine the safe bearing value of each pile using the applicable dynamic formula from those listed below.

1.	Gravity hammers:	P =	2WH

- S+1

- 2.	Single-acting hammers with unrestricted rebound of ram:

P =	2WH

- S+0.1

- 3.	Double-acting hammers with enclosed rams:

P =	2E

- S+0.1

Where:	P	=	Safe bearing value, in pounds

W	=	Weight of the striking parts of the hammer, in pounds

H	=	Effective height or fall of the ram, in feet

S	=	Average penetration per blow, in inches, for the last 5 to 10 blows for gravity hammers and the last 10 to 20 blows for steam, air, or diesel hammers

E	=	The actual energy delivery by the hammer per blow, in foot-pounds

The above formulas are applicable only when

- the hammer has free fall,

- the head of the pile is square and in good condition,

- the penetration rate is reasonably quick and uniform,

- there is no appreciable bounce of gravity hammers after the blow, and

- a follower is not used.

If there is appreciable bounce for gravity hammers, deduct twice the height of bounce from H to determine its value in the formula.

505-3.04 JETTED PILES. Do not use jets during the test blows when determining the safe bearing values of jetted piles.

505-3.05 MINIMUM PENETRATION. Make all efforts to drive each pile to the minimum desirable tip elevation and to the desired bearing, as shown on the Plans.

505-3.06 CAST-IN-PLACE CONCRETE PILES. Build cast-in-place concrete piles to the design shown on the Plans. Drive steel shells or pipes and fill with Class A Concrete.

Use the type of steel shell or closed-end pipe and the minimum thicknesses of material shown on the Plans.

- Do not allow water to freeze in cylinder-type piles.

Before placing concrete, inspect the shells for damage or distortion. Furnish a suitable light for this purpose.

Do not fill shells or pipe with concrete until all adjacent shells, pipes, or piles within a radius of 5 feet or 4.5 times the average pile diameter, whichever is greater, have been driven to the required resistance.

Place concrete as follows:

- Remove all water and foreign material from shells and pipes.

- Place the concrete in one continuous operation from bottom to top. Concrete may be discharged directly into the pile and permitted to free-fall into place.

- Use interior reinforcement where shown on the Plans.

- Vibrate the top 20 feet of concrete.

- After filling a shell or pipe with concrete, do not drive any shell, pipe, or pile within 20 feet for at least 7 days after filling.

505-3.07 EXTENSIONS, SPLICES, AND BUILD-UPS. When necessary, make extensions, splices, and build-ups as shown on the Plans and according to the following:

- Steel Piles. If the length of a steel pile is not sufficient to obtain the required bearing capacity, splice an additional length to it. Use additions with cross sections identical to the pile cross sections.

- Make splices with complete penetration butt welds over the entire cross section. If approved, piles may be spliced using pile cut-offs and short pieces if no piece used is less than 10 feet long.

- Shell or Pipe for Cast-in-Place Piles. If pile shell or pipe must be extended to reach desired penetration or required bearing capacity, splice additional lengths to the shell or pipe using complete penetration butt welds over the entire cross section or other splice details recommended by the manufacturer and approved.

- Meet the welding requirements of Subsection 504-3.01.8.

505-3.08 TIMBER PILE BENTS. Distribute piles of various sizes within each bent to obtain uniform strength and rigidity in the bents of each structure and to avoid undue bending or distortion of the sway bracing.

- Make accurate cut-offs to ensure full bearing between the caps and piles.

505-3.09 DRIVING PILES. Size the pile driving equipment to drive the piles to the required minimum depth and ultimate bearing capacity without damage. Use the approved hammer and pile cushions recommended in the hammer manufacturer’s guidelines. Limit the compressive driving stresses as indicated by a wave equation analysis to 90% of the pile yield stress.

Submit a pile driving plan at least 15 days before driving piles. Include a completed Pile Driving Equipment Data (Form 25D-098) and any attachments necessary to describe all pile driving equipment and techniques to be used. The Department will base approval of the pile driving equipment on a wave equation analysis and the Engineer’s recommendations. Submit changes to the approved pile driving plan on a revised Pile Driving Equipment Data form with necessary attachments. Allow at least 5 working days for the Engineer’s approval.

Steel piles when placed in the leads must not exceed the camber and sweep permitted by allowable mill tolerance. Piles bent or otherwise injured will be rejected.

Drive all piles as shown on the Plans or as ordered in writing. Drive abutment piles and pier piles in footings within an allowed variation as to direction of pile of not more than 1/4 inch per foot. Position the piles at the bottom of the footing within 6 inches of the position shown on the Plans. Do not vary the distance between any 2 piles more than 6 inches from that shown on the Plans, and keep the clear distance from the edge of pile to the edge of footing to at least 9 inches. Place exposed pile bents within 1/2 inch of the plan position at cut-off elevation and within 3 inches of the plan position at the original ground line elevation. Limit the rotation of such steel piles about their longitudinal axis to 15 degrees from the plan position.

- Install piles in groups starting from the center of the group and proceed outward in either direction.

Use a metal collar on every timber pile, except when the head is fitted into a steel head block. Protect the heads of the piles with caps of approved design, when needed.

Provide driving heads, mandrels, or other devices according to the manufacturer’s recommendations so that the pile may be driven without damage. Use cast steel combination driving heads and pilots with suitable cushion blocks. Ensure that the driving heads closely fit the top of a steel H-pile or steel pipe pile, and cut the steel piles squarely. Provide a driving cap to hold the axis of the pile in line with the axis of the hammer.

Use full-length piles where practical. Where splices are required, follow the provisions of Subsection 505-3.07.

- Use metal shoes or reinforced tips of the design shown on the Plans or as ordered in writing.

Use impact hammers or a combination of hammers to drive piles. However, with written permission, use gravity hammers to drive timber piles. The Department will consider the use of vibratory hammers when requested by the Contractor and when circumstances permit the determination of bearing capacity and required penetration by means other than a dynamic driving formula. Remove inefficient hammers from the work. Do not use followers to drive piles.

Use pile driver leads that allow the hammer to move freely. To ensure rigid lateral support to the pile during driving, hold the pile driver leads in position at the top and bottom by using guys or steel braces or by securely fastening them to the ground. Except where piles are driven through water, use leads that are long enough to avoid using a follower. The design of the leads must permit proper placing of batter piles.

If you cannot obtain the desirable penetration shown on the Plans by using the specified driving methods and equipment, or if the Engineer believes structural damage to the piling is likely to result from continuing these methods, attempt other methods (as approved in writing) to obtain penetration. These methods may include, but are not necessarily limited to:

- Pre-boring

- Blasting

- Spudding

- Jetting

- Using a heavier or faster striking hammer

Attempt all approved methods before starting work on more than 5 piles or 50% of the piles, whichever is lesser, in any one substructure unit (such as pier or abutment), or within a 30 foot length of retaining wall.

After exhausting all practicable means to obtain the desired penetration but without success, the Engineer may consider accepting the piling at a lesser penetration if the Engineer believes the adequacy and safety of the resulting structure will not be jeopardized by such acceptance.

Obtain written approval before employing any alternative methods of pile driving or variations from the desirable tip elevation accepted.

When driving piles through new embankment and the depth of the embankment at the pile location is in excess of 5 feet, drive the pile in a hole made through the embankment. Make the hole diameter not less than the nominal size of the pile plus 6 inches. After driving the pile, fill the annular space around the pile with dry sand or pea gravel. Dispose of excess excavated material as provided in Subsection 203-3.01.

505-3.10 DEFECTIVE PILES. Use a pile driving method which does not subject the piles to excessive and undue abuse producing crushing and spalling of the concrete, injurious splitting, splintering, and brooming of the wood or deformation of the steel. Do not manipulate the piles to force them into proper position. Correct damaged or improperly driven piles by one of the following approved methods:

- Withdraw and replace the pile with a new and, when necessary, longer pile.

- Drive a second pile adjacent to the defective pile.

- Splice or build up the pile as provided in Subsection 505-3.07, or extend a sufficient portion of the footing to properly imbed the pile. Do not splice timber piles without specific permission. Drive down all piles pushed up by driving adjacent piles or by any other cause.

505-3.11 CUTTING OFF PILES. Cut off the piles at the elevations indicated on the Plans. Ensure that all injured material is removed.

505-3.12 PROTECTING TREATED TIMBER PILES. Carefully handle the treated piles. Do not drop the piles, break the outer fibers, bruise the surface, or penetrate the piles with tools.

Carefully trim all cuts and abrasions in treated piles and coat with at least 3 applications of hot creosote oil and cover with hot roofing pitch. Treat all bolt holes according to AWPA standards before driving bolts. After treating the holes, plug all unfilled holes with treated plugs.

After cutting each treated pile to receive the cap, give the sawed surface 3 coats of hot creosote oil. Cover it with hot tar pitch and place 2 layers of 20 inches x 20 inches heavy canvas saturated with hot pitch over the surface. Place a 28 gage galvanized metal cover which overlaps the pile at least 6 inches in each direction. Bend the metal cover down over the edges and secure it with galvanized roofing nails.

505-3.13 COATING OF STEEL PILES AND SHELLS. Galvanize steel piles and steel pile shells from the top to a distance not less than 10 feet below the ground line. Galvanize according to AASHTO M 111 and to a thickness of 4 mils. Steel piles and pile shells that do not protrude above the final ground line do not require galvanizing.

## SECTION 506

## TIMBER STRUCTURES

506-1.01 DESCRIPTION. Construct timber structures and the timber portions of composite structures. Furnish, prepare, fabricate, erect, treat and/or paint timber and hardware, as specified.

506-2.01 MATERIALS. Use materials that conform to the following:

Timber	Section 713

Preservatives for Timber	Section 714

Structural Shapes, Rods, and Plates	Section 716

Glued-Laminated Timber Members. Construct of Douglas Fir produced and inspected in conformance with the requirements of ANSI/AITC A 190.1. Use laminating adhesives for timber to be used in wet conditions. Use Industrial-Grade glued-laminated members that have been treated with pressure preservative.

Bolts, Screws and Drive Spikes. Conform to ASTM A 307 (ANSI/ASME B 18.2.1). Galvanize meeting AASHTO M 232. Use standard timber fasteners manufactured with economy heads and spiral threads as drive spikes for fastening glued-laminated deck panels.

- Preservatives. Use pressure treatment preservatives for timber bridges as specified.

Mastic Sealer. Use Koppers Bitumastic Super Service Black, Chevron Wet Plastic Cement, ATCO 1714 Plastic Fibre Seal, Seal Tight 158 Rubber Asphalt Sealer, or approved equal.

Steel Dowels. Use uncoated steel dowels with a minimum yield strength of 36,000 psi on glued-laminated deck panels.

Timber Connectors. Conform to the requirements of the AASHTO Standard Specifications for Highway Bridges, Division II, Section 16.2.6, Timber Connectors.

- CONSTRUCTION REQUIREMENTS

506-3.01 GENERAL. Employ competent bridge carpenters. Framing must be true and exact. Set the heads of nails and spikes flush with the wood surface. Workmanship on all metal parts must conform to specified requirements.

Stack all lumber and timber at the worksite to prevent warping. Open-stack untreated material at least 12 inches above the ground surface so that the pile will shed water. When required, cover untreated timber to protect it from the weather. Close-stack treated timber above the ground on blocks or lagging. Clear weeds and rubbish underneath and around all stacks.

Locate all non-removable erection marks on fabricated timber so they are hidden from view in the completed work.

Do not drag or drop timber members. Use web-belting slings and chokers to handle timber members. Protect corners with protection angles or blocking at pickup points.

The estimated quantity of treated timber shown on the Plans is approximate only and no guarantee is made that it is the exact quantity to be furnished. Glued-laminated timber quantities shown on the Plans indicate gross quantities of timber, based on nominal dimensions and actual lengths before final planing of the laminated member.

506-3.02 TREATED TIMBER. Fabricate timber (including all cutting, shaping, and boring) before treatment. Handle timber carefully without dropping, breaking the outer fibers, or bruising or penetrating the surface with tools. In coastal waters, avoid cutting and boring below the high-water mark. Carefully trim all abrasions and treat all cuts in treated piles according to AWPA standard M 4.

Before driving bolts, treat all holes bored after treatment according to the applicable AWPA standards. Plug remaining holes with treated plugs.

506-3.03 UNTREATED TIMBER. In structures of untreated timber, thoroughly coat the following surfaces with an AWPA-approved preservative before the timbers are assembled:

- Ends, tops, and all contact surfaces of posts, sills, caps, floor beams, and stringers

- All ends, joints, and contact surfaces of bracing and truss members

- All surfaces of timber bumpers

- The back faces of bulkheads

- All other timber that will come in contact with earth

506-3.04 HOLES FOR BOLTS, DOWELS, RODS, AND LAG SCREWS. Bore holes for round drift-bolts and dowels with a bit 1/16 inch smaller in diameter than the bolt or dowel to be used. Bore holes for square drift-bolts or dowels equal to one side of the bolt or dowel. Bore holes for machine bolts 1/16 inch wider than the bolt. Bore holes for lag screws with a bit not larger than the body of the screw at the root of the thread. Bore holes for deck dowels in glued-laminated timber deck panels 1/2 inch deeper than the dowel embedment and no more than 1/16 inch oversize.

506-3.05 BOLTS AND WASHERS. Use washers of the type and size specified to protect wood from bolt heads and nuts. Use cast-iron washers with a thickness equal to the diameter of the bolt and with a diameter 4 times its thickness. Use malleable or plate washers with diameter or side dimensions of the square equal to 4 times the diameter of the bolt, and thickness equal to 1/2 the diameter of the bolt. Use cast-iron washers when the timber is in contact with the earth. Check or burr all nuts with a pointed tool after final tightening to prevent turning.

506-3.06 COUNTERSINKING. Countersink bolts where smooth faces are required. Paint recesses formed for countersinking, except in railing, with pentachlorophenol or creosote oil. After bolts or screws are in place, fill the recesses with hot pitch or mastic sealer. Countersink fasteners for attaching glu-lam deck panels to their supporting members below the top surface of the deck. After installation, fill all fastener recesses in the top surface of the deck with mastic sealer.

506-3.07 FRAMING. Cut all lumber and timber accurately and frame to a close fit so that the joints bear weight evenly over all contact surfaces without shimming.

506-3.08 FRAMING BENTS. Bed mud sills firmly and evenly to solid bearing. Tamp them in place.

Carefully finish concrete pedestals for supporting framed bents so that posts will bear evenly on them. Set dowels for anchoring posts when the concrete is cast.

506-3.09 STRINGERS. Size stringers at bearings and place them in position so that knots near edges are in the top portions of the stringer.

Separate the lapped ends of untreated stringers by at least 1/2 inch for air circulation. Securely fasten the lapped ends by drift-bolting where specified. Stagger the joints when stringers are two panels in length.

Securely toe-nail cross-bridging between stringers with at least two nails in each end. Place cross-bridging at the center of each span.

506-3.10 PLANK FLOORS. Lay the planks heart side down. For seasoned material, use 1/4 inch openings between planks. For unseasoned material, use tight joints. Securely spike each plank to each stringer. Carefully grade the planks for thickness and lay them so that adjacent planks vary in thickness by no more than 1/16 inch.

506-3.11 LAMINATED OR STRIP FLOORS. Lay each piece vertically and tightly against the preceding piece. Each piece must bear evenly on all the stringers.

Use pieces long enough to bear on at least four stringers. Make end joints on any one stringer no closer than every third piece. Place end joints in adjoining pieces no closer than every second stringer.

Coat joints between adjacent glu-lam timber deck panels with mastic sealer before drawing the panels together.

506-3.12 TRUSSES. Check completed trusses to ensure that they show no irregularities of line. Chords must be straight and true from end to end in horizontal projection. Ensure that chords show a smooth curve through panel points conforming to the correct camber in vertical projection. Accurately fit all bearing surfaces and joints. The Engineer will reject pieces with uneven or rough cuts at the points of bearing.

506-3.13 PAINTING. Paint the structure only when specified.

## SECTION 507

## BRIDGE RAILING

507-1.01 DESCRIPTION. Construct concrete, timber, or steel bridge railing and pedestrian railing as shown on the Plans. Furnish and install bridge number plates as shown on the Plans.

507-2.01 MATERIALS. Use materials that conform to the following:

Steel Railing	Section 722

Timber Railing	Section 506

Concrete	Section 501

Reinforcing steel	Subsection 709.-2.01 (Epoxy-Coated)

Grout	Section 701-2.03

507-3.01 CONSTRUCTION REQUIREMENTS.

1.	General. Construct railing to the line and grade shown on the Plans. Ensure that the rail does not reflect any unevenness of the bridge structure. Set rail posts normal to the grade. Place railing after all falsework is removed and the span is self-supporting. Do not paint bridge railing.

Furnish and install concrete curbing, associated reinforcing steel, and the approach rail transition bracket for steel bridge railing.

2.	Steel. Erect steel railing in conformance with Subsection 504-3.02. Weld in conformance with Subsection 504-3.01.8. Complete welding before galvanizing the railing.

3.	Timber. Fabricate and install timber railing in conformance with Section 506.

4.	Concrete. Construct concrete railing to meet applicable requirements of Sections 501 and 503. Base concrete mix design on Class A. Apply a rubbed finish to exposed surfaces of concrete.

## SECTION 508

## WATERPROOFING MEMBRANE

508-1.01 DESCRIPTION. Furnish and install preformed waterproofing membrane on concrete bridge decks, as specified.

508-2.01 MATERIALS. Use materials that conform to the following:

Membrane Material	Manufactured type single or multiple component elastomeric material from the Department's Qualified Products List.

- CONSTRUCTION REQUIREMENTS

508-3.01 APPLICATION OF MEMBRANE WATERPROOFING.

- General. Install membranes under the on-site supervision of a representative from the membrane manufacturing company and according to the manufacturer's published instructions. Achieve the following results:

- Complete bond between the membrane and the concrete surface of deck and curb face

- Unbroken waterproof membrane in place between the concrete deck surface and the asphalt overlay

- Complete bond between the membrane and the asphalt overlay

- Preparation of Concrete Deck. Before applying membrane:

- Ensure that all concrete to receive membranes has achieved at least 80% of the 28 day ultimate strength (f ’c) indicated on the Plans.

- Ensure that grout in keyways between precast concrete deck components has cured at least 5 days.

- Remove any contaminants such as grease, oil, or paint with solvents, detergents, or by sand blasting.

- Correct any sharp concrete edges on the deck surface that may puncture the membrane.

- Power sweep the deck to remove all foreign materials such as dirt, dust, moisture, and loose concrete.

- Before applying the tack coat, primer, or emulsion, thoroughly clean the deck with compressed air.

- Weather and Moisture Limitations. Apply membrane only when:

- The deck is completely dry

- The temperature of the deck and ambient air is above 40 °F

- Overlaying and Protection of Membrane. When overlaying membrane, observe the following requirements:

- Do not place the asphalt overlay until the membrane has cured enough to prevent damage from the overlaying operation.

- Do not operate vehicles, except the asphalt paver and trucks used for hauling the asphalt overlay mix, on the membrane.

- Use only rubber-tired or rubber-tracked paving machines over the membrane.

- Use only steel-wheeled rollers to compact the asphalt paving on the bridge decks.

- Do not use vibratory rollers with vibrator turned on.

- Place, spread, and roll the asphalt so that the membrane will not be damaged.

- Adhere to the manufacturer’s published minimum and maximum temperature limitations for asphalt overlay material.

## SECTION 509

## MICROSILICA MODIFIED CONCRETE OVERLAY

509-1.01 DESCRIPTION. Furnish and install microsilica modified concrete (MMC) overlay, as specified, at the location(s) shown in the Plans.

509-2.01 MATERIALS. Use materials that conform to the following:

Portland Cement	Section 701 (Type I or Type IA)

Fine Aggregate	Subsection 703-2.01

Coarse Aggregate	Quality: Subsection 703-2.02

Gradation: AASHTO M 43 (Gradation No. 7)

Sand For Abrasive Finish	Crushed sand, oven dried, and stored in moisture-proof bags. Meet the following gradation requirements when tested according to WAQTC FOP for AASHTO T 27/T 11:

| Sieve | Percent Passing |
| --- | --- |
| No. 8 | 100 |
| No. 30 | 97-100 |
| No. 200 | 0-5 |

High Molecular Weight 	Subsection 705-2.07

Methacrylate (HMWM) Resin

Microsilica Admixture	Subsection 711-2.04

Epoxy Resin Mortar	AASHTO M 235, Type I, Grade 3

- CONSTRUCTION REQUIREMENTS

509-3.01 QUALITY CONTROL AND TESTING.

1.	Technical Representative. Have a technical representative from the microsilica admixture manufacturer present during initial proportioning, mixing, placing and finishing operations. The technical representative must:

  - Remain on site for at least the first 2 days of placement.

- Be able to perform, demonstrate, inspect and test all of the functions required for placing the MMC as specified and approved by the Engineer.

- Aid in properly installing the MMC.

- Adhere to recommendations made by the technical representative as approved by the Engineer.

2.	Test Slab. Make a trial batch of the MMC which meets the Specifications at least 4 days before placing the first section of the overlay. Make the trial batch the same size to be batched per truck. Place a test slab at a location approved by the Engineer. Cast the slab 12 feet wide, the same thickness of the overlay, and long enough to place the trial batch. Furnish individual batch weights to the Engineer. Finish and cure the test slab according to all the requirements of these Specifications.

Notify the Engineer 7 days before preparing the test batch. The Engineer will sample for slump, air entrainment and unit weight and conduct all the required tests to determine if the MMC meets specifications before field placement.

The test slab remains the Contractor’s property. Remove and dispose of the test slab after testing is complete.

3.	Production Testing. The Engineer will perform the following tests:

a.	Daily Start-up Tests. Slump and entrained air tests according to WAQTC FOPs for AASHTO T 119 and T 152, respectively, on each of the first two loads of each day before the concrete is placed. Discharge and set aside a wheelbarrow load of concrete for this purpose.

b.	Operational Control Tests. Slump and entrained air tests for concrete on random samples, selected according to AASHTO T 141, with at least one set of tests for every 20 cubic yards.

c.	Quality Assurance Tests. Compressive strength and permeability tests. The Engineer will select the concrete specimens and perform permeability tests according to AASHTO T 277 for concrete samples aged to 28 days. The charge passed through the sample must not exceed 1000 coulombs.

- Remove and dispose of test samples when testing is complete.

509-3.02 SUBMITTALS. Submit a list of proposed materials to be used in the mix, 20 days before placement. Do not begin placing concrete without written approval. Use a mix design according to Subsection 509-3.03.

509-3.03 PROPORTIONING MATERIALS. Mix the concrete into a workable mix that is uniform in composition and consistency and within the proportioning tolerances in Subsection 501-3.01. Use the following mix proportions per cubic yard:

Portland cement	660 lb.

Microsilica Fume	52 lb.

Fine aggregate	(determined from mix design)

Coarse aggregate	(determined from mix design)

Air	6% ±1.5%

Water/cement ratio	0.33 lb./lb. max.

Calculate the water/cement ratio using all of the available mix water, including the free water in both the coarse and fine aggregate and in the microsilica slurry, if a slurry is used.

Mix the concrete to a maximum slump of 7 inches. Adjust the slump to accommodate the gradient of the deck. Add water-reducing admixtures, air-entraining admixtures, and superplasticizers according to the microsilica admixture supplier’s recommendations.

509-3.04 STORAGE OF MATERIALS. Store materials per Subsection 106-1.06 and the following:

- Aggregate. Prevent variations of more than 1.0% in the stockpile moisture content.

- High Molecular Weight Methacrylate (HMWM) Resin. Store the HMWM resin in a cool, dry place. Protect resin from freezing and exposure to temperatures greater than 100 °F. If the promoter and initiator are supplied separately from the resin, store them so that they do not contact each other directly. Do not store containers of promoters and initiators together in a way that allows leakage or spillage from one to contact containers or materials of the other.

509-3.05 EQUIPMENT. Use equipment that complies with the applicable requirements of Section 510 and the following:

- Air Compressor. Equipped with oil traps to eliminate oil from being blown onto the roadway deck during sandblasting and air-cleaning.

- Vacuum Machine. Capable of collecting all dust, concrete chips, free-standing water and other debris encountered during deck cleaning and preparation. Equipped with collection systems that can operate in air pollution sensitive areas and will not contaminate the deck during final preparation for concrete placement.

- Water Blast Equipment. High-pressure water blasting equipment capable of removing dust, debris, and loose, disintegrated concrete. Must produce a minimum pressure of 5000 psi.

- Water Spraying System. A portable high-pressure sprayer with a separate water supply. Make the sprayer readily available to all parts of the deck being overlaid. The sprayer must discharge water in a fine mist to prevent accumulation of free water on the deck. Make sure enough water is available to thoroughly soak the deck being overlaid and keep the deck wet until concrete is placed.

- Certify that the water spraying system meets the following minimum requirements:

- Pressure	2200 psi

- Flow Rate	5 gallons per minute

- Fan Tip	15 to 25 degree range

- Fogging Equipment. Water fogging equipment capable of increasing humidity in the area of placement. Use nozzles that produce a fine fog mist to maintain a sheen of moisture on the overlay surface without ponding. Limit flow rate to approximately 1 gallon per minute. Use “Fog-it” triple head nozzle by the Fogg-it Nozzle Co., San Francisco, CA, or approved equal.

- Finishing Machine. A self-propelled finishing machine that:

- Can move forward and in reverse under positive control.

- Provide for raising and lowering all screeds under positive control. Ensure the upper vertical limit of screed travel permits the screed to clear the finished concrete surface.

- Is adjustable to produce the required cross-section, line, and grade. When placing concrete abutting a previously placed lane or strip, ensure the side of the finishing machine is equipped to travel on the completed lane or strip.

- Is equipped with a rotating cylindrical double-drum screed not more than 5 feet long, preceded by a vibrating pan. Use a finishing machine with a metal vibrating pan long and wide enough to consolidate the mixture properly. The vibrating frequency of the vibrating pan must be variable with positive control between 3,000 and 6,000 rpm. The Engineer will consider approving a machine with a vibrating pan as an integral part, if it is proposed.

509-3.06 DECK PREPARATION.

1.	Clean. Thoroughly clean the lane or strip being overlaid of all loose particles, dust, oil, grease, rust, or other foreign materials that may reduce the bond of new concrete to old concrete.

- Use detergent cleaning, water blast, sandblast or another approved method.

2.	Protect. Prevent equipment from contaminating the surface with oil or grease before placing the overlay. When using an air supply system for blast cleaning and blowing, ensure there is an oil trap in the air line.

Confine hydrodemolition to areas at least 100 feet from the defined limits of any final cleaning or overlay placement in progress. If the Engineer determines that hydrodemolition is impeding or interfering in any way with final cleaning or overlay placement, stop the hydrodemolition work immediately and move hydrodemolition equipment far enough from the area being prepared or overlaid.

If the water and contaminates from hydrodemolition could flow into the area being prepared or overlaid because of the grade, suspend the hydrodemolition for the first 24 hours of curing time after the concrete is placed.

When final preparation begins, stop removing concrete by mechanical methods and stop cleaning in areas adjacent to a lane or strip being cleaned. Do not resume removing concrete by mechanical methods until placing the concrete and satisfying the curing-time requirement. Suspend sandblasting and cleaning for the first 24 hours of curing time after the concrete is placed.

If the lane or strip being overlaid becomes contaminated after final cleaning, flush the surface with high-pressure water or sandblast (shotblast) the surface before placing the overlay. Begin concrete placement within 24 hours of completing deck preparation for the portion of the deck to be overlaid.

Do not permit traffic (other than required construction equipment) on any portion of the lane or strip prepared for concrete placement, without approval. To prevent contamination from equipment after final cleaning, place polyethylene sheeting over prepared lanes or strips.

3.	Keep Wet. After cleaning the lane or strip to be overlaid, and at least 6 hours before placing concrete, thoroughly soak the lane or strip with water. Remove all free-standing water. Keep the lane or strip moist until concrete is placed.

509-3.07 BATCHING AND MIXING CONCRETE.

- Batch concrete to conform with Subsection 501-3.03.

Mix concrete to conform with Subsection 501-3.04, but do not use a truckload that contains more than 4 cubic yards of concrete without approval.

509-3.08 FORMS. Conform with Section 512.

509-3.09 PLACING CONCRETE. Before placing concrete, review equipment, procedures, personnel, previous results, and inspection procedures with the Engineer.

Place concrete according to Subsection 501-3.08 and the following:

- Do not place concrete under the following conditions:

- When the concrete surface temperature is less than 45 °F or greater than 80 °F.

- When the combination of air temperature, relative humidity, fresh concrete temperature, and wind velocity at the construction site produces an evaporation rate of 0.15 lb/ft2 per hour as determined from Table 501-2.

- When rain is expected. Protect freshly placed concrete in case rain begins during placement. Remove and replace rain-damaged concrete to the satisfaction of the Engineer.

- Use enough concrete delivery trucks to deliver and place concrete consistently and continuously throughout the pour.

- Use bulkheads for all joints. Before placing concrete against previously placed concrete, check the joint for bond. Remove and replace unbonded concrete as specified in Subsection 509-3.13.

- If concrete placement is stopped for one half hour or more, install a bulkhead transverse to the direction of placement at a position where the overlay can be finished full width up to the bulkhead. Install the bulkhead at full depth of the overlay and to grade. Finish and cure concrete according to these Specifications.

Wait at least 12 hours before placing more concrete, unless there is a gap in the lane or strip. The gap must be wide enough for the finishing machine to clear the transverse bulkhead installed where concrete placement was stopped. Saw back the previously placed concrete from the bulkhead to straight and vertical edges as designated by the Engineer. Sandblast or water-blast the previously placed concrete before placing new concrete.

- Do not place concrete against the edge of an adjacent lane or strip less than 36 hours old.

- Use epoxy resin mortar to patch overhead blow-throughs after placing the overlay.

509-3.10 FINISHING CONCRETE. Finish the concrete according to Subsection 501-3.09.3 and the following requirements:

Place rails on which the finishing machine travels outside the area to be overlaid. Use interlocking rail sections or other approved methods of providing rail continuity. Submit plans for anchoring rails for approval according to Subsection 105-1.02. Do not shoot hold-down devices into the concrete unless the concrete is to be subsequently overlaid. Do not penetrate the existing deck with hold-down devices by more than 3/4 inch. Remove rails any time after the concrete has taken an initial set. Protect the new surface edges when removing the finishing machine and rails.

Set screed control to obtain the nominal overlay thickness or specified profile grade and meet finished surface smoothness requirements. The Engineer will verify or adjust the overlay profile before concrete placement. After verifying the profile, the Engineer will not permit changes in the finishing machine elevation controls.

Place and strike off concrete approximately 1/2 inch above the final grade. Consolidate and finish the concrete to final grade with a single pass of the finishing machine to provide a dense, uniform surface. Hand finish concrete to close up or seal off the surface, when required.

Do not allow the concrete surface to dry out. Throughout the finishing process, fog the air over the concrete as needed to maintain a visible moisture sheen on the surface. Use an evaporation reducer, such as “Confilm” by Master Builders, Inc., Seattle, WA, if desired, until the wet burlap is applied.

Separate construction bulkheads from the newly placed concrete, as follows: Pass a pointing trowel along the inside surfaces of the bulkheads. After the concrete has stiffened enough so it does not flow back, carefully make the trowel cut for the entire depth and length of bulkheads.

509-3.11 CURING CONCRETE. As the finishing operation progresses, immediately cover the concrete with a single layer of clean, wet burlap. Use burlap cloth that meets the requirements of AASHTO M 182, Class 4 and is no wider than 6 feet. The Engineer will determine if the burlap can be reused, based on its cleanliness and absorption ability.

Make sure the burlap is well drained and laid flat with no wrinkles on the deck surface. Place adjacent strips of burlap with a minimum overlap of 6 inches. Once the burlap is in place, apply a light fog mist of water. Immediately place a separate layer of white, reflective-type polyethylene sheeting over the wet burlap.

Wet cure the concrete by leaving the polyethylene sheeting and burlap in place for at least 72 hours, keeping the burlap wet.

After the polyethylene sheeting and burlap are removed and the concrete surface has dried, fill and seal all joints and visible cracks with a high-molecular-weight methacrylate (HMWM) resin. Use two applications of HMWM in cracks 1/16 inch and wider. Immediately after applying HMWM, coat the wetted surface with sand for an abrasive finish.

After meeting the curing requirements, use compressed air to accelerate deck-surface drying, crack identification, and sealing.

Do not permit traffic on the finished concrete until the specified curing time is satisfied and the concrete reaches a minimum compressive strength of 3000 psi. Determine compressive strength from informational test cylinders cured on site under temperature and moisture conditions similar to those of the concrete in the structure.

509-3.12 PROTECTING CONCRETE. Protect microsilica concrete when placing it in cold weather. Cold weather is defined as when the average daily air temperature for 3 consecutive days is less than 45 °F. The average daily air temperature is the average of the highest and lowest temperatures from midnight to midnight.

- After placing MMC, maintain it at a temperature above 50 °F for at least 3 days.

If the air temperature drops below 35 °F while curing, place insulating blankets over the curing materials. Use insulating blankets 2 inches thick with tough, impermeable cover material.

When the deck temperature is lower than 45 °F, pour microsilica concrete only under the following conditions:

- Use a concrete mixture between 55 °F and 75 °F at the time of placement.

- If using heated water to obtain proper placement temperatures, add air-entraining agents after the last heated water.

- Clear the deck of snow, ice, or frost.

- Maintain the temperature of the deck receiving concrete at 35 °F, minimum.

- Maintain the temperature of the rebar at 35 °F, minimum.

- Cover placed concrete with burlap, plastic sheeting and insulated mats immediately after finishing of the surface. Keep the covering in place for 3 days. Monitor concrete temperature hourly for 3 days. Add 1 day to the covered time for any day in which the recorded surface temperature of the concrete is less than 50 °F.

- If heated enclosures are used, vent combustion heaters to the outside of the enclosure. Locate heaters and ducts to avoid overheating or drying areas of the concrete surface.

- As an alternative to the requirements of step 6, monitor the slab’s compressive strength. Use in-place, non-destructive testing. After 3 days, uncover the concrete, regardless of temperature, when the concrete reaches a compressive strength of 3000 psi.

- If any freezing temperature is recorded during the first 24 hours that it is covered, promptly remove concrete.

To pour concrete when rain is predicted, observe the following conditions:

- Have materials on hand to cover the work in case of rain.

- Halt the pour and immediately cover all work when rain drops affect the slab finish.

509-3.13 CHECKING FOR BOND. After deck curing is complete, the Engineer will test the entire overlaid surface for total bonding of concrete to the bridge deck. Remove concrete from unbonded areas and replace it with MMC without extra compensation.

## SECTION 510

## REMOVAL OF CONCRETE BRIDGE DECK

510-1.01 DESCRIPTION. Remove, wholly or in part, and satisfactory dispose of bridge deck concrete to the depth and limits shown on the Plans and/or as directed. Remove all unsound (spalled, cracked and/or delaminated) concrete.

510-2.01 MATERIALS. Use falsework meeting Section 512.

- CONSTRUCTION REQUIREMENTS

510-3.01 GENERAL. Perform work to meet the applicable requirements of Section 202.

- Prevent damage to reinforcing steel designated to remain in place.

Following the concrete removal, the Engineer will inspect any exposed reinforcing steel. Remove and replace bars or sections of bars that are damaged or deteriorated at any point to less than 80% of their original cross section, including cracked or broken bars.

Remove sufficient concrete to allow for splicing of a new piece of reinforcing steel. Extend the spliced reinforcing steel 32 inches beyond each end of the damage or deterioration.

- Replace damaged or deteriorated steel reinforcing bars under Subsection 109-1.05, if

1.	not damaged by Contractor operations, or

2.	damage from milling is a result of the concrete cover being 1 inch or less.

510-3.02 METHOD OF REMOVAL. Remove concrete to specified depth using hydrodemolition equipment. For areas of the deck not accessible to hydrodemolition, use mechanical impact methods. You may use power operated rotary milling machines to scarify the upper deck to a nominal depth of 3/4 inch.

510-3.03 MILLING. Use rotary type milling machines, capable of scarifying a minimum width of 4 feet per pass.

510-3.04 HYDRODEMOLITION.

1.	Equipment. Use high-pressure water pumping system, low-pressure water filtration and feed systems, and remote-control stations for two remote-controlled demolishing units. Ensure a nozzle pressure of 25,000 psi.

Employ qualified personnel, certified by the equipment manufacturer, to operate the equipment. Submit operator certification(s) to the Engineer for approval before beginning concrete removal operation.

2.	Concrete Removal. Perform concrete deck removal as shown on the Plans. Perform hydrodemolition removal resulting in a rough finished surface, free of debris.

Before concrete removal begins, the Engineer will select a trial area of sound concrete of the deck approximately 30 ft2 in size. Advance the demolishing unit over this area and establish the operating parameters to achieve the depth of removal called for on the Plans. Submit a list of operating parameters to be used for production work to the Engineer for approval.

During production work, the Engineer may require recalibration of the equipment if, in the Engineer’s opinion, satisfactory concrete removal is not being obtained.

Remove debris immediately after demolition operation to prevent rebonding to the surface of sound concrete. Remove any material which is allowed to rebond without extra compensation and with no contract time extension. Avoid damage to remaining sound concrete and reinforcing steel.

Furnish and erect rigid safety shields adjacent to hydrodemolition equipment, or otherwise protect adjacent traffic and property from flying debris.

- Protect traffic from hazardous glare of work lights during nighttime operations.

- Furnish water to operate the hydrodemolition equipment.

3.	Controlling Wastewater and Debris. Submit a Wastewater Treatment Plan no less than 5 working days prior to the preconstruction conference. Include methods for containment, collection, filtration, storage, and disposal of wastewater and debris. The plan must be stamped by an Engineer registered in the State of Alaska and must be acceptable to the Alaska Department of Environmental Conservation.

Perform the following:

a.	Capture and contain all wastewater and debris within the work area.

b.	Filter wastewater to ensure that it is free of concrete particles and sediment before being discharged.

4.	Reinforcing Steel. Clean all reinforcing steel that is to remain in place and has been exposed by removal operations. Remove all rust and corrosive products immediately prior to concrete placement. Remove oil, dirt, concrete fragments, laitance, loose scale, and other coating that would destroy or inhibit the bond with the new concrete.

Protect cleaned reinforcing steel from the elements and from contamination. Sandblast reinforcing steel contaminated as a result of your failure to provide adequate protection, at your expense.

510-3.05 MECHANICAL METHODS. In areas not accessible to hydrodemolition remove concrete by mechanical impact methods to the same depth as adjacent areas. Avoid damage to sound concrete structures by the improper use of mechanical tools. Repair, cracked or damaged structures, as required.

Also use mechanical methods if either of the following conditions exists:

1.	There is unsound concrete remaining after the hydrodemolition is done in an area

2.	There is a lack of bond between the existing concrete and the reinforcing steel

If unsound concrete exists or if the bond is broken around existing reinforcing steel, remove concrete to provide a 3/4 inch minimum clearance around the reinforcing steel. Do not damage any of the existing reinforcing steel that is to remain in place.

Operate the mechanical impact tool at angles less than 45 degrees as measured from the deck surface to the tool. Do not use jack hammers heavier than the nominal 30 lb class or chipping hammers heavier than the nominal 15 lb class.

510-3.06 Cleanup. Following concrete removal, clean the job site and remove debris. Dispose of debris at a Department of Environmental Conservation approved landfill. Remove dust and loose particles by flushing with water and/or vacuum cleaning.

## SECTION 511

## MECHANICALLY STABILIZED EARTH (MSE) WALL

511-1.01 DESCRIPTION. Furnish and install mechanically stabilized earth wall. Construct the Mechanically Stabilized Embankment (MSE) Retaining Walls at the locations shown on the Plans and as provided in these specifications. Constructing the MSE retaining walls shall consist of precast concrete facing panels connected to a metallic strip or grid reinforcement. The MSE wall shall be an acceptable wall system as listed in RFP Part III, Section 4, Bridges and Structures.

The construction of the MSE wall system shall conform to the Release for Construction Plans, the details on the approved working drawings and to the details of the acceptable wall system.

511-2.01 MATERIALS. Meet the following:

Class A Concrete 	Section 501

Precast and Cast-in-Place Concrete Panels 	Section 501

Reinforcing Steel 	Section 503

Structural Steel 	AASHTO M 270

Pipe and Perforated Pipe 	Section 706

Geotextile for Drainage	Subsection 729-2.02

Geogrid	Subsection 729-2.05

Geocomposite Drainage System	As Specified

Porous Backfill Material 	Subsection 703-2.10

1.	Structure Backfill and Foundation Fill. Meet Subsection 703-2.07, Selected Material, Type A. Use materials with a sodium sulfate soundness loss less than 30% after four cycles as determined by AASHTO T 104 and free of shale or other particles of low durability.

When using backfill material with 80% passing the 3/4 inch sieve, the minimum angle of internal friction on the portion of the material finer than the No. 10 sieve must be 34 degrees, as tested by AASHTO T 236.

When using steel soil reinforcement, use backfill material meeting the following electrochemical requirements:

- pH of 5 to 10 (AASHTO T 289)

- Resistivity not less than 30 ohmmeters (AASHTO T 288)

- Chlorides not greater than 100 ppm (AASHTO T 291)

- Sulfates not greater than 200 ppm (AASHTO T 290)

The IQF shall perform and report corrosion tests. Notify the IQF and the Engineer of the MSE backfill source at least 21 days before wall construction for corrosion testing of the backfill materials.

2.	Wall Members. Provide facing consisting of precast concrete panels, modular units, cast-in-place concrete, or welded wire fabric, as specified.

Manufacture concrete panels with a minimum concrete compressive strength of 4,000 psi. Finish the exposed face with ordinary finish. For the face not exposed to view, provide a uniform surface finish free of open pockets of aggregate or surface distortions in excess of 1/4 inch. Locate soil reinforcement connection hardware during concrete placement to avoid contact with the panel reinforcing steel. Shop-fabricate welded wire fabric reinforcement from cold-drawn wire meeting AASHTO M 32, and the finished fabric meeting AASHTO M 55.

a.	Concrete Face  Panels. Fabricate panels  conforming to  Section 501, with the following exceptions and additions:

1)	Do not strip the units until the concrete reaches a minimum compressive strength of 1000 psi. Ship the units after reaching a minimum compressive strength of 3300 psi. The Engineer will not accept panels with hairline cracks in them.

2)	Angle Points: Changes in the wall alignment shall be accomplished using prefabricated angled corner panels or special columns of the same texture and size as the flat panels, such that a continuous panel is traversing the angle point without a break in the normal horizontal and vertical joint pattern unless directed otherwise by the Engineer. Bevel panels or field outs that disrupt the normal joint pattern and/or result in a single vertical line are not permissible.

3)	Marking: Clearly scribe the date of manufacture, the production lot number, and the piece mark, on the unexposed face of each panel.

4)	Handling, Storage and Shipping: Handle, store, and ship all panels in such a manner as to protect them from chipping, discoloration, cracks, fractures, and excessive bending stresses.  Support  panels  in  storage  on  firm  blocking  to protect the panel connection devices and the exposed exterior finish.

5)	Tolerances:  Manufacture all panels within the following tolerances:

a)	Panel Dimensions: Position of panel strap connection devices within 1 inch. All other dimensions within 3/16 inch.

b)	Panel Squareness: Squareness as determined by the difference between the two diagonals, shall not exceed ½ inch.

c)	Panel Surface Finish: Surface defects on smooth formed surfaces measured on a length of 5 feet shall not exceed 0.1 inch. Surface defects on the textured- finished surfaces measured over a length of 5 feet shall not exceed 3/16 inch.

6)	Testing:

Compressive Strength: Production lots shall determine the acceptance of concrete panels with respect to compressive strength. A single compressive strength sample will represent a production lot of a group of panels. A production lot will consist of either 10 panels or a single day's production, whichever is less.

During the production of the concrete panels, the manufacturer will randomly sample the concrete in accordance with WAQTC TM 2. A single compressive strength sample, consisting of a minimum of four cylinders, will be randomly selected for every production lot.

Perform compression tests on a standard 6 inches by 12 inches test specimen in accordance with WAQTC FOP for AASHTO T 23. Conduct compressive strength testing in accordance with AASHTO T-22.

For every compressive strength sample, cure a minimum of two cylinders in accordance with WAQTC FOP for AASHTO T-23 and test at 28 days. The average compressive strength of these cylinders, when tested in accordance with AASHTO T-22, will provide a compressive strength test result that will determine the compressive strength of the production lot.

If the compressive strength test result is greater than or equal to 4000 psi the Engineer will accept the production lot. If the compressive test result is less than 4000 psi, then the acceptance of the production lot will be based on its meeting the following acceptance criteria in their entirety:

a) 	Ninety percent of the compressive strength test results for the overall production shall exceed 4060 psi.

b) 	The average of any six consecutive compressive test results shall exceed 4200 psi.

c) 	No individual compressive strength test result shall fall below 3600 psi.

Air Content: Perform air content tests in accordance with WAQTC FOP for AASHTO T 152 or AASHTO T-196. Take air content samples at the beginning of each day's production and take compressive samples at the same time to insure compliance.

Slump Test: Perform the slump test in accordance with WAQTC FOP for AASHTO T-119. Determine the slump at the beginning of each day's production and take the compressive samples at the same time.

Rejection: Rejection of units shall be because of failure to meet any of the requirements specified above. In addition, any of the following defects shall be sufficient cause for rejection.

a)	Faulty casting causing defects.

b)	Defects indicating honeycombed or open texture concrete.

c)	Cracked or severely chipped panels.

d)	Unreasonable color variation on front face of panels.

Joint Materials: Bearing pads, joint filler, and joint cover materials shall be according to the MSE wall supplier's recommendations.

b.	Concrete Leveling Pad. The concrete leveling pad shall be cast in place Class A and conform to Section 501. The concrete for the pad shall be placed at least 24 hours prior to erecting the face panels.

3.	Soil Reinforcement. Use approved geogrid reinforcement.

Galvanize all steel soil reinforcement and any steel connection hardware to meet AASHTO M 111. Manufacture steel strip reinforcement by hot rolling to meet ASTM A 572, Grade 450, or approved alternate.

4.	Working Drawings. Submit all working drawings and design calculations, including:

- Earthwork requirements including specifications for material and compaction of backfill.

- Details of revisions or additions to drainage systems or other facilities required to accommodate the system.

- Existing ground elevations verified by the Contractor for each location involving construction wholly or partially in original ground.

- Complete design calculations substantiating that all proposed designs satisfy the design parameters in the Contract documents.

- Complete details of all elements required for the proper construction of the system, including complete material specifications.

Prohibit work on earth retaining systems for which working drawings are required until such drawings have been approved.

511-3.01 CONSTRUCTION.

1.	Excavation and Backfill. Excavate and backfill earth retaining systems to meet Section 205. Replace excavated material with structure backfill material meeting Section 205. Compact the material as specified under Subsection 203-3.04.

2.	Drainage. Provide outlet works at sags in the profile and at the low ends of the gutter.

- Weep Holes. Place a minimum of 2 cubic feet of porous backfill material encapsulated with geotextile at each weep hole. Cover joints between retaining wall panels, which function as weep holes, with geotextile. Dry and thoroughly clean the face panels that are to receive the geotextile.

- Drainage Blankets. Construct drainage blankets consisting of porous backfill material encapsulated in geotextile, collector pipes, outlet pipes, and cleanout pipes. Construct and compact the subgrade to receive the geotextile so it is free of loose or extraneous material and sharp objects that may damage the geotextile. Stretch, align, and place the fabric in a wrinkle-free manner. Overlap adjacent borders of the fabric from 12 to 18 inches. Repair torn or punctured fabric by covering the damaged area with a piece of fabric large enough to cover the damaged area and meet the overlap requirement.

Place the porous backfill material in horizontal layers and thoroughly consolidate by the same methods specified for structure backfill. Prohibit ponding or jetting of porous backfill material or structure backfill material. Maintain a minimum of 6 inches of porous backfill material, structure backfill, or embankment material between the fabric and the equipment during spreading and compaction of the porous backfill material.

Place perforated collector pipe, when required, within the porous backfill material to the flow line elevations shown. Place outlet pipes at sags in the flow line and at the low end of the collector pipe. Construct rock slope protection, when required, at the end of outlet pipes, as shown on the Plans. Place cleanout pipes at the high ends of collector pipes.

- Geocomposite Drainage Systems. Place and secure the geocomposite drainage material tightly against the excavated face, lagging or back of wall. Protect the drainage material against physical damage and grout leakage when concrete is to be placed against geocomposite drainage material.

3.	Retaining Wall Construction. Construct mechanically stabilized earth walls consisting of a facing system to which steel or polymeric soil reinforcement is connected. Provide facing of precast concrete panels, cast-in-place concrete.

- Install polymeric soil reinforcement under Section 634.

When constructing cast-in-place concrete facing, embed soil reinforcement which extends beyond the temporary facing into the facing concrete.

Form welded wire facing by bending the horizontal soil reinforcement 90 degrees upward to form the wire face. Connect the vertical portion of the welded fabric forming the face to the next upper level of soil reinforcement. Place a separate backing mat and hardware cloth immediately behind the vertical portion of soil reinforcement.

Provide a precast reinforced or cast-in-place concrete leveling pad at each panel foundation level. Place panels or wire fabric and support to achieve the final position.

Place and compact structure backfill material at the same time as placement of facing and soil reinforcement, without distortion, damage, or displacement of the facing or soil reinforcement. Backfill to an elevation approximately 1-1/4 inch above the facing connection level before placing the next level of soil reinforcement. Roughly level the backfill material before placing the soil reinforcement. Uniformly tension all soil reinforcement to remove any slack in the connection or material.

- Install joint filler, bearing pads, and joint-covering material concurrently with face panel placement.

- Furnish and install instrumentation for monitoring corrosion, where specified.

- Tolerances. Precast concrete panels shall be placed so that their final position is vertical, or battered as shown in the Plans. Handle panels for erection by means of lifting devices connected to the upper edge of the panel or as per the MSE wall suppliers recommendations. Panels shall be placed in successive horizontal lifts in the sequence shown on the working drawings as backfill placement proceeds. As backfill material is placed behind the panels, maintain the panels in a vertical position by means of temporary wedges or bracing according to the wall supplier’s recommendation. For structures with precast facing panels, concrete vertical tolerances and horizontal alignment tolerances shall not exceed ¾ inch when measured with a 10 foot straight edge. During construction, the maximum allowable offset in any panel joint shall be ¾ inch. The overall vertical tolerance of the wall (top to bottom) shall not exceed ½ inch per 10 foot of wall height. The plumb and tolerances of each panel row at the face shall be checked before erection of the next panel row. Should panels be out of tolerance, remove the fill, and reset panels to proper tolerances. Horizontal, vertical and slope joint openings between panels shall be uniform and no larger than 1 ¼ inch and no smaller than ½ inch.

5.  	Reinforcement. Reinforcement elements shall be placed normal to the face of the wall, unless otherwise shown on the Plans. Before placement of the reinforcing elements, backfill shall be compacted according to Section 205.

6.  	Backfill Placement. Backfill placement shall closely follow erection of each course of panels. Backfill shall be placed in such a manner as to avoid damage or disturbances of the wall materials or misalignment of the facing panels. Remove and replace wall materials that become damaged during backfill placement at the Contractor's expense. Correct misalignment or distortion of the wall facing panels due to placement of backfill outside the limits of this specification.

Backfill shall be compacted to 95 percent of the maximum density as determined by AASHTO T99/T180 or ATM 212. Where spread footings support bridge or other structural loads, the top 5 feet below the bottom of the footing elevation shall be compacted to 98 percent as determined by AASHTO T99/T180 or ATM 212. The maximum lift thickness after compaction shall not exceed 8 inches. Decrease this lift thickness, if necessary to obtain the specified density. The Engineer will determine field density using ALASKA FOP for AASHTO T 205 or WAQTC FOP for AASHTO T 310 AND WAQTC FOP for AASHTO T 224.

Use a lightweight mechanical tamper, roller, or vibratory system with at least three passes to achieve compaction within 3 feet of the back face of the wall facing. Obtain a minimum of one density test at each level of soil reinforcement material. Slope the last level of backfill away from the wall facing to permit rapid water runoff away from the wall face at the end of operations each day. Do not allow surface runoff from adjacent areas to enter the wall construction site.

## SECTION 512

## FORMS AND FALSEWORK

512-1.01 Description. Design, construct, and remove forms and falsework to temporarily support structural concrete, girders, and other major structural elements.

512-2.01 MATERIALS. As specified or approved.

- design and construction requirements

512-3.01 Drawings. When complete details for forms and falsework are not shown, prepare and submit drawings according to Subsection 105-1.02. Include the following, as applicable:

- Design and show the details for constructing safe and adequate forms and falsework that provide the necessary rigidity, support the loads imposed, and produce in the finished structure the required lines and grades. See Subsection 512-3.02 for design loads. See Subsection 512-3.03 for design stresses, loadings, and deflections. See Subsection 512-3.04 for manufactured assemblies.

- Show the maximum applied structural load on the foundation material. Include a drainage plan or description of how foundations will be protected from saturation, erosion, and/or scour. See Subsection 512-3.05.

- Precisely describe all proposed material. Describe the material that is not describable by standard nomenclature (such as AASHTO or ASTM specifications) based on manufacturer's tests and recommended working loads. Evaluate falsework material and ascertain whether the physical properties and conditions of the material is such that it can support the loads assumed in the design.

- Furnish design calculations and material specifications showing that the proposed system will support the imposed concrete pressures and other loads. Provide an outline of the proposed concrete placement operation listing the equipment, labor, and procedures to be used for the duration of each operation. Include proposed placement rates and design pressures for each pour. Include a superstructure placing diagram showing the concrete placing sequence and construction joint locations.

- Provide design calculations and working drawings for proposed bridge falsework.  Show the stresses and deflections in load supporting members in the falsework design calculations. Use a person proficient in falsework design to perform the work. The design calculations and working drawings must be stamped with the seal of, dated by, and signed by a Professional Engineer registered in the State of Alaska.

- Show anticipated total settlements of falsework and forms. Include falsework footing settlement and joint take-up. Design for anticipated settlements not to exceed 1 inch. Design and detail falsework supporting deck slabs and overhangs on girder bridges so there is no differential settlement between the girders and the deck forms during placement of deck concrete. Design and construct the falsework to elevations that include anticipated settlement during concrete placement and required camber to compensate for member deflections during construction.

- Show the support systems for form panels supporting concrete deck slabs and overhangs on girder bridges.

- Show details for strengthening and protecting falsework over or adjacent to roadways and railroads during each phase of erection and removal. See Subsection 512-3.06.

- Include intended steel erection procedures with calculations in sufficient detail to substantiate that the girder geometry will be correct. See Subsection 512-3.07.

- Submit details of proposed anchorage and ties for void forms. See Subsection 512-3.09 for void form requirements.

Submit separate falsework drawings for each structure, except for identical structures with identical falsework design and details. Do not start construction of any unit of falsework until the drawings for that unit are reviewed and approved.

512-3.02 Design Loads.

1.	Vertical Design Loads. Dead loads include the weight of concrete reinforcing steel, forms, and falsework. Consider the entire superstructure, or any concrete mass being supported by falsework to be a fluid dead load with no ability to support itself. If the concrete is to be prestressed, design the falsework to support any increased or readjusted loads caused by the prestressing forces.

Assume the density of concrete, reinforcing steel, and forms to be not less than 160 lb/ft3 for normal concrete and not less than 130 lb/ft3 for lightweight concrete.

Consider live loads to be the actual weight of equipment to be supported by falsework applied as concentrated loads at the point of contact plus a uniform load of not less than 20 lb/ft2 applied over the area supported, plus 75 lb/ft applied at the outside edge of deck falsework overhangs.

The total vertical design load for falsework is the sum of vertical dead and live loads. Use a total vertical design load of not less than 100 lbs/ft2.

2.	Horizontal Design Loads. Use an assumed horizontal design load on falsework towers, bents, frames, and other falsework structures to verify lateral stability. The assumed horizontal load is the sum of the actual horizontal loads due to equipment, construction sequence, or other causes and an allowance for wind. However, in no case is the assumed horizontal load to be less than 2% of the total supported dead load at the location under consideration.

The minimum wind allowance for each heavy-duty steel shoring having a vertical load-carrying capacity exceeding 30,000 pounds per leg is the sum of the products of the wind impact area, shape factor, and the applicable wind pressure value for each height zone. The wind impact area is the total projected area of all the elements in the tower face normal to the applied wind. Assume the shape factor for heavy-duty shoring to be 2.2. Determine wind pressure values from Table 512-1.

- Table 512-1

Design Wind Pressure - heavy-duty Steel Shoring

| Height Zone (ft) | Wind Pressure Value (lb/ft2) |  |
| --- | --- | --- |
| Above Ground | Adjacent to Traffic | At Other Locations |
| 0 30 - 50 50 - 100 Over 100 | 20 25 30 35 | 15 20 25 30 |

The minimum wind allowance on all other types of falsework, including falsework supported on heavy-duty shoring, is the sum of the products of the wind impact area and the applicable wind pressure value for each height zone. The wind impact area is the gross projected area of the falsework and unrestrained portion of the permanent structure, excluding the areas between falsework posts or towers where diagonal bracing is not used. Use design wind pressures from Table 512-2.

- Table 512-2

Design Wind Pressure - Other Types of Falsework

| Height Zone (ft) | Wind Pressure Value (lb/ft2) |  |
| --- | --- | --- |
| Above Ground | For Members Over and Bents Adjacent to Traffic Openings | At Other Locations |
| 0 30 - 50 50 - 100 Over 100 | 2.0 Q 2.5 Q 3.0 Q 3.5 Q | 1.5 Q 2.0 Q 2.5 Q 3.0 Q |

NOTE: Determine the value of Q, if applicable, in the above table as follows:

Q = 1 + 0.2W, but not more than 10. W is the width of the falsework system in feet measured in the direction of the wind force being considered.

Design the falsework so the falsework has sufficient rigidity to resist the assumed horizontal load without vertical dead load. Neglect the effects of frictional resistance.

3.	Lateral Fluid Pressure. Design forms, form ties, and bracing for concrete with retarding admixture, fly ash, or other pozzolan replacement for cement, for a lateral fluid pressure based on concrete with a density of 150 lb/ft3. Determine the lateral fluid pressure for concrete containing no pozzolans or admixtures, which affect the time to initial set, based on concrete temperature and rate of placement according to ACI standard 347, Formwork for Concrete.

512-3.03 Design Stresses, Loads, and Deflections. The allowable maximum design stresses and loads listed in this Section are based on the use of undamaged, high-quality material. Reduce the allowable stresses and loads if lesser quality material is used. Do not exceed the following maximum stresses, loads, and deflections in the falsework design:

- 1.	Timber.

- Compression perpendicular to the grain = 450 psi

Compression parallel to the grain =    480,000 psi

(Not to exceed 1600 psi)	(L/d)2

Where:

L = The unsupported length

d = The least dimension of a square or rectangular column or the width of a square of equivalent cross-sectional area for round columns

- Flexural stress = 1800 psi

(Reduced to 1450 psi for members with a nominal depth of 8 inches or less.)

- Horizontal shear = 190 psi

- Axial tension = 1200 psi

Deflection due to the weight of concrete may not exceed 1/500 of the span even if camber strips compensate for the deflection.

- The modulus of elasticity (E) for timber = 1.6 x 106 psi

- Maximum axial loading on timber piles = 45 tons

Design timber connections according to the stresses and loads allowed in the National Design Specification for Wood Construction, published by the National Forest Products Association except:

(1) Reductions in allowable loads required therein for high moisture condition of the lumber and service conditions do not apply.

(2) Use 75% of the tabulated design value as the design value of bolts in two member connections (single shear).

- 2.	Steel. For identified grades of steel, do not exceed the design stresses (other than stresses due to flexural compression) specified in the AISC Manual of Steel Construction.

When the grade of steel cannot be positively identified, do not exceed the design stresses, other than stresses due to flexural compression, either specified in the AISC Manual of Steel Construction for ASTM A 709, Grade 36 steel or the following:

- Tension, axial and flexural = 22,000 psi

- Compression, axial = 16,000 - 0.38(L/r)2 psi (except that L/r may not exceed 120)

- Shear on the web gross section of rolled shapes = 14,500 psi

- Web crippling for rolled shapes = 27,000 psi

For all grades of steel, do not exceed the following design stresses and deflection:

Compression, flexural* =    12x106 psi

Ld/bt

(*Not to exceed 22,000 psi for unidentified steel or steel meeting ASTM A 709. Not to exceed 0.6 Fy for other identified steel.)

Where:

L = The unsupported length, inches

d = The least dimension of a square or rectangular column or the width of a square of equivalent cross-sectional area for round columns or the depth of beams, inches

b = The width of the compression flange, inches

t = The thickness of the compression flange, inches

r = The radius of gyration of the member

Fy = The specified minimum yield stress for the grade of steel used

Deflection due to the weight of concrete may not exceed 1/500 of the span even if camber strips compensate for the deflection.

- The modulus of elasticity (E) for steel = 30x106 psi

- 3.	Other Requirements. Limit falsework spans supporting T-beam girder bridges to 14 feet plus 8.5 times the overall depth of T-beam girder.

512-3.04 Manufactured Assemblies. For jacks, brackets, columns, joists and other manufactured devices, do not exceed the manufacturer's recommendations or 40% of the ultimate load carrying capacity of the assembly based on the manufacturer's tests or additional tests ordered. Limit the maximum allowable dead load deflection of joists to 1/500 of their spans.

Furnish catalog or equivalent data showing the manufacturer's recommendations or perform tests, as necessary, to demonstrate the adequacy of any manufactured device proposed for use. Do not substitute other manufacturer's components unless the manufacturer's data encompasses such substitutions or field tests reaffirm the integrity of the system.

If a component of the falsework system consists of a steel frame tower exceeding 2 or more tiers high, do not exceed a differential leg loading within the steel tower unit of 4 to 1. An exception may be approved if the manufacturer of the steel frame certifies, based on manufacturer's tests, that the proposed differential loadings are not detrimental to the safe load carrying capacity of the steel frame.

512-3.05 Falsework Foundations. Field verify all ground elevations at proposed foundation locations before design.

Where spread footing type foundations are used, determine the bearing capacity of the soil. The maximum allowable bearing capacity for foundation material, other than rock, is 4000 lb/ft2.

Do not locate the edge of footings closer than 12 inches from the intersection of the bench and the top of the slope. Unless shoring adequately supports the excavation for footings, do not locate the edge of the footings closer than 4 feet or the depth of excavation, whichever is greater, from the edge of the excavation.

When a pile type foundation is used, use according to Section 505. When falsework is supported by footings placed on paved, well-compacted slopes of berm fills, do not strut the falsework to columns unless the column is founded on rock or supported by piling.

Size spread footings to support the footing design load at the assumed bearing capacity of the soil without exceeding anticipated settlements. Provide steel reinforcement in concrete footings.

When individual steel towers have maximum leg loads exceeding 30,000 pounds, provide for uniform settlement under all legs or each tower under all loading conditions.

Protect the foundation from adverse effects for the duration of its use. Advise the Engineer of actions that will be taken to protect the foundation.

512-3.06 Falsework Over or Adjacent to Roadways and Railroads. Design and construct the falsework to be protected from vehicle impact. This includes falsework posts that support members crossing over a roadway or railroad and other falsework posts if they are located in the row of falsework posts nearest to the roadway or railroad and if the horizontal distance from the traffic side of the falsework to the edge of pavement or to a point 10 feet from the centerline of track is less than the total height of the falsework.

Provide additional features to ensure that this falsework will remain stable if subjected to impact by vehicles. Use vertical design loads for these falsework posts, columns, and towers (but not footings) that are not less than either:

1.	150% of the design load calculated according to Subsection 512-3.02, but not including any increased or readjusted loads caused by prestressing forces, or

2.	the increased or readjusted loads caused by prestressing forces.

Install temporary traffic barriers before erecting falsework towers or columns adjacent to an open public roadway. Locate barriers so that falsework footings or pile caps are at least 3 inches clear of concrete traffic barriers and all other falsework members are at least 12 inches clear. Do not remove barriers until approved.

Use falsework columns that are steel with a minimum section modulus about each axis of 9.5 in3) or sound timbers with a minimum section modulus about each axis of 250 in3.

Mechanically connect the base of each column or tower frame supporting falsework over or immediately adjacent to an open public road to its supporting footing or provide other lateral restraint to withstand a force of not less than 2000 pounds applied to the base of the column in any direction. Mechanically connect such columns or frames to the falsework cap or stringer to resist a horizontal force of not less than 1000 pounds in any direction. Neglect the effects of frictional resistance.

Brace or tie exterior girders, upon which overhanging bridge deck falsework brackets are hung, to the adjacent interior girders as necessary to prevent rotation of the exterior girders or overstressing the exterior girder web.

Mechanically connect all exterior falsework stringers and stringers adjacent to the end of discontinuous caps, the stringer or stringers over points of minimum vertical clearance and every fifth remaining stringer, to the falsework cap or framing. Provide mechanical connections capable of resisting a load in any direction, including uplift on the stringer, of not less than 500 pounds. Install connections before traffic is allowed to pass beneath the span.

Use 5/8 inch diameter or larger bolts to connect timber members used to brace falsework bents located adjacent to roadways or railroads.

Sheath falsework bents within 20 feet of the centerline of a railroad track solid in the area between 3 and 17 feet above the track on the side facing the track. Construct sheathing of plywood not less than 5/8 inch thick or lumber not less than 1 inch nominal thickness. Provide adequate bracing on such bents so that the bent resists the required assumed horizontal load or 5000 pounds, whichever is greater, without the aid of sheathing.

Provide at least the minimum required vertical and horizontal clearances through falsework for roadways, pedestrians, and boats.

512-3.07 Falsework for Steel Structures.

1.	Use falsework design loads consisting of the weight of structural steel, the load of supported erection equipment, and all other loads supported by the falsework.

2.	Design falsework and forms for concrete supported on steel structures so that loads are applied to girder webs within 6 inches of a flange or stiffener. Distribute the loads in a manner that does not produce local distortion of the web.

3.	Strut and tie exterior girders supporting overhanging deck falsework brackets to adjacent interior girders to prevent distortion and overstressing of the exterior girder web.

4.	Do not apply loads to existing, new, or partially completed structures that exceed the load carrying capacity of any part of the structure according to the Load Factor Design methods of the AASHTO Bridge Design Specifications using Load Group IB.

5.	Build supporting falsework that will accommodate the proposed method of erection without overstressing the structural steel, as required, and will produce the required final structural geometry, intended continuity, and structural action.

512-3.08 Falsework Construction. Construct falsework to conform to the approved drawings.

Build camber into the falsework to compensate for falsework deflection and anticipated structure deflection. Camber shown on the Plans or specified by the Engineer is for anticipated structure deflection only.

Attach tell-tales to soffit of concrete forms in enough systematically placed locations to be able to determine from the ground the total settlement of the structure while concrete is placed.

- Do not apply dead loads, other than forms and reinforcing steel, to any falsework until authorized.

Discontinue concrete placement and take corrective action, if unanticipated events occur, including settlements that cause a deviation of more than 0.325 inches from those shown on the falsework drawings. If satisfactory corrective action is not taken before initial set, remove all unacceptable concrete.

512-3.09 Forms. For exposed concrete surfaces, use U.S. Product Standard PS 1 for Exterior B-B (Concrete Form) Class I Plywood or other approved material that will produce a smooth and uniform concrete surface. Use only form panels in good condition free of defects on exposed surfaces. If form panel material other than plywood is used, it must have flexural strength, modulus of elasticity, and other physical properties equal to or greater than the physical properties for the type of plywood specified.

Furnish and place form panels for exposed surfaces in uniform widths of not less than 2 feet and in uniform lengths of not less than 4 feet except where the width of the member formed is less than 2 feet.

Arrange panels in symmetrical patterns conforming to the general lines of the structure. Place panels for vertical surfaces with the long dimension horizontal and with horizontal joints level and continuous. For walls with sloping footings which do not abut other walls, placement of panels with the long dimension parallel to the footing is permitted.

Increase the thickness of concrete members that receive an architectural finish to maintain the specified minimum cover to reinforcing steel.

Precisely align form panels on each side of the panel joint by means of supports or fasteners common to both panels. Provide 3/4 inch triangular filets at all sharp edges of the concrete.

Devices may be cast into the concrete for later use in supporting forms or for lifting precast members. Do not use driven devices for fastening forms or form supports to concrete. Use form ties consisting of form bolts, clamps, or other devices necessary to prevent spreading of the forms during concrete placement.

Do not use form ties consisting of twisted wire loops. Use form ties and anchors that can be removed without damaging the concrete surface. Construct metal ties or anchorages within the forms to permit their removal to a depth of at least 1 inch from the face without damage to the concrete. Fill cavities with cement mortar and finish to a sound, smooth, uniform colored surface.

Construct all exposed concrete surfaces that will not be completely enclosed or hidden below the permanent ground surface so the formed surface of the concrete does not undulate more than 0.1 inch or 1/360 of the center to center distance between studs, joists, form stiffeners, form fasteners, or wales. Interior surfaces of underground drainage structures are considered to be completely enclosed surfaces. Form all exposed surfaces for each element of a concrete structure with the same forming material or with materials that produce similar surface textures, color, and appearance.

Support roadway slab forms of box girder type structures on wales or similar supports fastened, as nearly as possible, to the top of the web walls.

Construct concrete forms mortar-tight, true to the dimensions, lines, and grades of the structure, and of sufficient strength to prevent appreciable deflection during placement of concrete. Place all material required to be embedded in the concrete before concrete placement. Clean inside surfaces of forms of all dirt, mortar and foreign material. Remove all loose material before the completion of forming for the roadway deck slab of cast-in-place box girders or cells or voids of other members in which the forms are to either remain in place or be removed.

Coat forms to be removed with form oil. Use commercial quality form oil or an equivalent coating that permits release of the forms and does not discolor the concrete. Do not place concrete in forms until the forms have been inspected and approved.

Store void forms in a dry location to prevent distortion. Secure the forms using anchors and ties which leave a minimum of metal or other supporting material exposed at the bottom of finished slab.

Make the outside surface of void forms waterproof. Cover the ends with waterproof mortar tight caps. Use a premolded 1/4 inch thick rubber joint filler around the perimeter of the caps to permit expansion.

Provide a PVC vent near each end of each void form. Construct vents so the vent tubes do not extend more than 1/2 inch below the bottom surface of the finished concrete after form removal. Protect void forms from the weather until concrete is placed.

512-3.10 Removal of Forms and Falsework. Remove all forms except as follows:

1.	Interior soffit forms for roadway deck slabs of cast-in-place box girders.

2.	Forms for the interior voids of precast members.

3.	Forms for abutments or piers when no permanent access is available into the cells or voids.

Remove forms that do not support the dead load of concrete members, other than railings and barriers, only after the concrete for the member has been in place for at least 24 hours and the concrete has sufficient strength to resist damage to the surface. Protect exposed concrete surfaces from damage.

Do not begin the removal of forms and falsework until the requirements specified in Table 512-3 for concrete strength or minimum time in the forms, when applicable, have been met.

Remove falsework for arch bridges uniformly and gradually, beginning at the crown and working toward the springing. Remove falsework for adjacent arch spans simultaneously.

Do not release falsework for cast-in-place prestressed portions of structures until after the prestressing steel has been tensioned.

Do not remove falsework supporting the deck of rigid frame structures excluding box culverts, until compacted backfill material has been placed against vertical legs of the frame.

Falsework supporting the sides of girder stems with slopes steeper than 1:1 may be removed before placing deck slab concrete, providing a reshoring system is installed. Design the lateral supports of the reshoring system to resist all rotational forces acting on the stem, including those caused by the placement of deck slab concrete. Install the lateral supports immediately after each form panel is removed and before release of supports for the adjacent form panel.

- Table 512-3

Form/Support Release Criteria

| Structural Element | Percent of Specified 28-Day Strength (f ’c), min. | Days Since Last Pour, min. |
| --- | --- | --- |
| (a) Columns and wall faces (not yet supporting loads) | 50 | 3 |
| (b) Mass piers and mass abutments not yet supporting loads (except pier caps) | 50 | 3 |
| (c) Box girders | 80 | 14 |
| (d) Simple span girders, T-beam girders, slab bridges, cross beams, caps, pier caps not continuously supported, struts, and top slabs of concrete box culverts | 80 | 14 |
| (e) Trestle slabs where supported on wood stringers | 70 | 10 |
| (f) Slabs and overhangs where supported on steel stringers or prestressed concrete girders | 70 | 10 |
| (g) Pier caps continuously supported | 60 | 7 |
| (h) Arches, continuous span bridges, rigid frames | 90 | 21 |

Completely remove falsework material. Remove falsework piling at least 2 feet below the surface of the original ground or original stream bed. Where falsework piling is driven within the limits of ditch or channel excavation, remove the piling to at least 2 feet below the bottom and side slopes of the excavated areas.

Leave the forms for footings constructed within a cofferdam or crib in place when their removal would endanger the safety of the cofferdam or crib, and where the forms will not be exposed to view in the finished structure.

- Remove all other forms whether above or below groundline or water level.

## SECTION 513

## FIELD PAINTING OF STEEL STRUCTURES

513-1.01 DESCRIPTION. Clean and paint the structural steel on existing bridges. Contain, collect, and dispose of waste materials and protect existing facilities, vehicles, the environment, and the public from damage due to this work.

513-2.01 MATERIALS. Use materials that conform to the following:

- Paint. Section 708. Use approved contrasting colors for each coat.

- Abrasives. Use an abrasive that is free of oil, moisture, and salts and will produce a minimum profile of 1.5 mils on the surface of the cleaned steel.

a.	Non-Steel Abrasives. Meet SSPC-AB1 (Abrasive Specification No. 1), Mineral and Slag abrasives. Do not use abrasives containing more than 1% “free” silica.

b.	Steel Abrasives. Recycle and reclean after each use. Must produce a profile approved by the coating's manufacturer.

513-2.02 COMPONENT ORIGIN. Use only components that are the standard, regularly produced product of a single manufacturer and meet or exceed the requirements in this Section.

Paint systems must be the same generic type, be field applicable under the environmental constrictions of the site and structure, and have been used successfully in the field for at least 2 years on similar structures in a similar environment as this project.

Submit the following information on paint systems for approval:

- Description of product

- Intended uses and exposures of the product

- Technical data on the formulation and components

- Description of surface preparation required

- Application information, including written recommendations and instructions for this project

- Safety information and precautions, including Material Safety Data Sheets

- List of references of previous bridge projects that used the proposed system, including applicator and owner contacts

If the proposed equivalent system literature requires a higher degree of surface preparation/profile or greater film thickness than specified in this Section, follow the submittal requirements, with no additional compensation.

- CONSTRUCTION REQUIREMENTS

513-3.01 SYSTEM DURABILITY AND CERTIFICATION. Require the coating manufacturer to review the project and the proposed service environment and issue written recommendations and instructions to the applicator to ensure maximum durability, proper surface preparation, and proper coating application. Make these documents available at the prepainting conference.

Require the coating system manufacturer to have a technical representative on the job site during the prepainting conference and also be available and on-call during construction.

Do not deviate from the coating manufacturer's written recommendations and instructions unless the manufacturer’s technical representative authorizes the change in writing, and the Engineer approves.

After the project is completed, certify to the Department that the system was applied according to the manufacturer's recommendations and instructions.

513-3.02 PAINT APPLICATOR'S CERTIFICATIONS. Hire only paint crew members that are certified by the Alaska Department of Labor for completing the Alaska Hazardous Painting Certificate Course within the last 3 years. Contact the Alaska Department of Labor for certification information.

Crew members must provide either a resume showing experience with the paint system components specified in this Section or a letter of acceptance of experience from the paint system manufacturer.

- Provide copies of certificates, resumes or letters to the Engineer at the prepainting conference.

513-3.03 REQUIRED CONTRACTOR EXPERIENCE. Hire a paint superintendent with experience with the coating system. Submit a list of the paint superintendent’s projects and references at least 7 days before the prepainting conference.

For projects requiring removal of paint containing lead and/or chromium, hire a paint superintendent with experience in removing lead and/or chromium from steel structures. Include these references in the paint superintendent’s list of references described above. The paint superintendent must know all current standards and regulations about containing hazardous debris generated during paint removal operations and disposing of contaminated surface preparation debris.

513-3.04 PREPAINTING CONFERENCE. Attend a prepainting conference at the Engineer’s office after the preconstruction conference and before mobilizing on the site and beginning any work under this Section.

Submit a Containment and Disposal Plan to the Engineer for approval 30 days before the prepainting conference. Include plans and written guidelines for the following:

- Containment structures and attachments to the bridge

- Ventilation

- Rigging

- Handling and disposing of hazardous and non-hazardous waste

An Engineer registered in the State of Alaska must stamp all containment and rigging plans. The engineer must design the containment structures and rigging to include attachments to the bridge and to accommodate maximum high wind loads and maximum daily weight loads of abrasive blast grit, dry or wet.

Include in the Containment and Disposal Plan all measures necessary to contain paint during painting operations.

Require the following personnel to attend the prepainting conference:

- Site Superintendent and/or Applicator Foreman

- Quality Control Inspector

- Chief Blast Cleaner

- Chief Paint Applicator

- Technical representative of the coating system manufacturer for this project

At the prepainting conference, submit the following in writing and discuss in detail:

- Work plan for safety, health, containment, ventilation, pressure washing, rigging, lighting, abrasive blast cleaning, coating application, curing all coats, and quality control

- Work plan for handling hazardous and non-hazardous waste, including but not limited to testing, handling, treatment, temporary storage, transportation, disposal, and applicable regulations and laws governing hazardous waste

- Plans for record keeping for all work performed

- Work schedule, including hours per shift, number of shifts and all manpower

- List of all equipment in detail, including compressor sizes, number of blast personnel per shift, and coating applicators

Immediately after the prepainting conference, all parties must visit the project site. On site, explain the proposed methods of cleaning, coating, containing hazardous waste, and making attachments to the bridge. Submit the planned schedule of work typical of all sequences.

Submit all required certificates and resumes/letters for approval, including the paint manufacturer’s written recommendations and instructions.

Following receipt of written final approval of all submittals, notify the Engineer in writing of the actual project mobilization or start up. The Engineer will determine the minimum notification time at the end of the prepainting conference.

513-3.05 QUALITY CONTROL AND QUALITY ASSURANCE. Comply with the following quality control and quality assurance rules:

- Use the best practices of the trade.

- Use applicable portions of the SSPC-PA Volume 1, Shop, Field and Maintenance Painting when they do not conflict with contract Specifications.

- Have current copies of SSPC-PA Volumes 1, 2, and 3 on site at all times. Supply them to your crew and Department personnel for reference.

- Require your Quality Control Inspector to monitor and document daily all equipment, manpower, materials, surface preparation, ambient conditions, paint application and product millage to conform with the Specifications and with the coating system manufacturer's written recommendations and instructions given at the prepainting conference. Deliver a copy of each daily report to the Engineer on the following morning.

- Prior to requesting an inspection by the Engineer, submit a report signed by the Quality Control Inspector, certifying that all work complies with the Plans and Specifications.

Correct the following defects without additional compensation or contract time:

- Coats thinner than minimum dry film thickness specified

- Coats with excessive millage (Remove coats with excessive millage according to the coating manufacturer's written instructions and recoat to Specifications.)

- Unauthorized paint application (Remove and reclean the underlying surface.)

- Incomplete stripe coat

- Overspray, spatter, runs, and sags

- Defects in the top coat, including abrasives or dust

Provide equipment and an operator for safe access to all areas of the work for quality assurance inspections by the State, as necessary.

The Engineer may hire a National Association of Corrosion Engineers (NACE) Certified Coating Inspector to inspect the work. Results of all such inspections will be documented. As a minimum, the following points will be inspected:

- After pressure washing

- After abrasive blast surface preparation and blowing all surfaces clean

- After applying and curing the prime coat

- After applying and curing the intermediate coat.

- After applying and curing the finish coat

- During final inspection of all work at the end of the project

513-3.06 MEASUREMENT OF DRY FILM THICKNESS. Measure and completely document coating thickness by calibrated magnetic film thickness gauge according to the requirements of SSPC-PA Volume 2, Method for Measurement of Dry Paint Thickness with Magnetic Gauges.

Destructive testing of the dry film thickness of each coat may be performed with a Tooke gauge. Repair damaged areas.

513-3.07 TRAINING. Train all crafts personnel, including three Department Inspectors, to comply fully with the General Industry Lead Standard 29 CFR 1910.1025. Furnish the necessary supplies, equipment, instruments, and facilities. Include the following subjects in the training:

- Action Level

- Permissible Exposure Limit

- Exposure Monitoring

- Compliance Plan

- Respiratory Protection

- Protective Work Clothing and Equipment

- Housekeeping

- Hygiene Facilities and Practices

- Medical Surveillance

- Medical Removal Protection

- Employee Information and Training

- Signs

- Record Keeping

- Observation of Monitoring

513-3.08 HEALTH AND SAFETY. Follow and enforce safety rules and requirements of the State, Resource Conservation and Recovery Act (RCRA), Federal codes, EPA, local laws, and SSPC-PA Guide 3, A Guide to Safety in Paint Application.

- Equipment. Use explosion-proof lighting and electrical equipment in cleaning and applying coatings.

- Use compressors with in-line dryers that are rated to match the compressor's rated capacity. Regularly test the compressor's discharge air to make sure it is oil-free.

- Air Alert. Notify all personnel and the Engineer when work on painted surfaces may contaminate the air above the action level, including, but not limited to, the following:

- Rivet busting

- Power tool cleaning without a vacuum system

- Welding

- Cutting or torch burning

- Abrasive blasting

- Clean-up activities, including containment structure movement

- Data Sheets. Conspicuously post Material Safety Data Sheets at the work site.

- Overspray. Take all necessary measures to contain paint during painting operations. Take appropriate action to prevent overspray paint or coating damage to adjacent property. Take remedial action for all overspray.

- Sampling and Testing. Conduct an acceptable abrasive blast test before startup.

Take a sample of blast abrasives from the accumulation of the first day's blast. Send the sample to an independent testing laboratory to determine contaminant levels. Deliver the report immediately to the Engineer. Take additional samples when the project is 25% and 75% complete or as the Engineer directs.

Test with the Toxicity Characteristic Leaching Procedure (TCLP). Classify levels at or above 5 ppm of leachable lead as hazardous waste and levels below 5 ppm as non-hazardous. Until the lab confirms test results, consider all debris hazardous and implement all safety precautions.

Take soil, water, and sediment samples at approved locations at the bridge site before beginning work and after completing the project. Send these samples to an independent testing lab for analysis. Submit the results to the Engineer. If the samples taken at the end of the project contain higher lead concentrations than the samples taken before beginning work, clean up the area to reduce the lead concentration to or below the level found before work began.

- Perform additional sampling and testing as results dictate, including tests for plant and aquatic life.

- Adjacent Property. Coordinate bridge cleaning and painting operations with adjacent property owners before beginning.

- Confined Spaces. At a minimum, whenever sandblasting and/or painting in confined area, ventilate area and furnish positive pressure respirators. Use the positive pressure respirators according to the coating manufacturer's written instructions.

- Housekeeping. Maintain good housekeeping practices. Keep the work area, including the work platform, roadway, and adjacent areas, clean and uncluttered. Deposit all debris and rubbish in suitable containers at the end of each work day or as directed.

- Final Clean Up. At the end of the project, clean all areas, including adjacent areas, and remove all debris. Ensure that the top coat on the complete bridge is free from abrasives and dust generated from the project.

513-3.09 CONTAINMENT AND DISPOSAL. Ensure that surface preparation debris test results fall below RCRA regulatory levels. Treat debris on-site using blast media additives that react with the lead to make it non-leachable in the abrasive blast media.

Obtain a site-specific EPA identification number for transporting and disposing of hazardous waste. List the Department as the waste generator for the project.

Use containment for all other structural steel work involving grinding, welding, or burning of the existing lead-based paint.

Provide all labor, equipment, and material for compliance with Specifications and regulations of RCRA, State, Federal, EPA, Local Laws, SSPC-Guide 6 (CON) Guide for Containing Debris Generated During Paint Removal Operations, and SSPC-Guide 7 (DIS) Guide for Disposal of Lead-Contaminated Surface Preparation Debris. Use SSPC Guides when they do not conflict with these Specifications. These regulations apply to sampling, testing, storing, containing, treating on site, transporting and disposing of all hazardous and non-hazardous waste.

Use filter fabric, drapes, or other appropriate methods to recover and contain loose paint and other debris generated during pressure washing.

Maintain liners, tarps, and drapes used to contain debris in good condition. If they are punctured, stop the work, repair the puncture, and capture the debris.

Stop abrasive blast cleaning and coating during high wind or precipitation, when containment is not in compliance, and when otherwise directed.

Use containment procedures meeting the following subsections of SSPC-Guide 6 (CON):

5.3	containment structures for abrasive blasting

5.3.1	Containment Materials, Type A1 (Rigid)

5.3.2	Air Impenetrable, Type B1

5.3.3	Support Structure, Type C1 (Rigid)

5.3.4	Joints, Type D1 (Full Seal)

5.3.5	Entryway, Type E3 (Overlapping)

5.4	Ventilation System Components

5.4.1	Input Air Flow, Type G1 (Forced)

5.4.2	Air Pressure, Type H2 (Visual)

5.4.3	Air Movement, Type I1 (Minimum Specified)

5.4.4	Exhaust Air Flow/Dust Collection, Type J1 (Air Filtration Required)

5.5	Methods for Assessing Quantity of Emissions

5.5.1	Visible Emissions, General Surveillance, 200 feet from containment structure and Level 2 Emissions

5.5.5	Soil Analysis for Toxic Metals

5.6	METHOD OF ASSESSING EFFICIENCY OF DEBRIS COLLECTION AND BULK ABRASIVE RECOVERY

5.6.1	Weight In/Weight Out Method

- Dispose of waste according to Sections 5, 6 and 7 of SSPC-Guide 7 (DIS).

513-3.10 SURFACE PREPARATION. Before beginning any other cleaning, pressure wash all surfaces scheduled for painting. Remove all dirt, grease, loose chalky paint, salts, or other foreign material.

- Do not pressure wash surfaces more than 2 weeks before painting or cleaning.

Use a pressure washer with at least 3000 psi at all elevations. Keep the nozzle tip no more than 12 inches from the surface during all phases of power washing.

Perform pressure washing with potable water. If needed, add a biodegradable detergent to the pressure washer feed water or apply it directly to the surface to be cleaned. Apply the detergent using methods that remove all surface contaminants.

Before abrasive blasting, grind smooth all metal defects, fins, slivers, burrs, weld spatter, and sharp edges resulting from shearing or similar operations, including flame-hardened edges resulting from cutting or burning. Grind flame-hardened edges a minimum of 1/16 inch. Document all weld defects and report them to the Engineer immediately.

Abrasive blast clean all metal to be coated to SSPC-SP10/NACE #2, Near-white Blast Cleaning. Remove all mill scale. Match the appearance of the abrasive blast cleaned area to Pictorial Standard SSPC-VIS-1-89 and NACE TMO170/NACE #2. Produce a surface profile neither detrimental to the coating performance nor contrary to the coating manufacturer's written instructions.

Repair all defects that become evident after abrasive blasting or applying a prime coat. Retexture the surface to match the blasted profile.

Clean all abrasive-blast-cleaned surfaces and staging surfaces by brushing, vacuum cleaning, or blowing with dry, oil-free compressed air. Do not wipe down surfaces with rags. Remove all loose blast material from the work area. Make sure all surfaces to be coated are free of contaminants and moisture.

Coat all abrasive blast cleaned surfaces in the same working shift. Reclean and inspect all surfaces not coated within 12 hours or if they show contamination or rust bloom. The Engineer may approve additional time between abrasive blast cleaning and coating under controlled humidity conditions.

To prevent contaminating cleaned or coated surfaces, do not pressure wash or abrasive blast clean in adjacent areas when also applying coatings or drying coated surfaces.

Prevent contaminating the cleaned surfaces with any oil, grease, soil, dust, foreign matter, salts, acids, alkali, or other corrosive chemicals before applying the prime coat and remaining coats. Remove any contamination from the surface before applying other coats.

513-3.11 Weather Limitations. Apply coatings within the environmental limitations recommended by the coating manufacturer. Do not apply coatings:

- where dust is generated;

- in fog, snow, or rain;

- on surfaces that are wet or damp; or

- when surface temperature is below 35 °F or above 120 °F.

When necessary, control the containment environment to comply with material specifications and meet the completion date.

513-3.12 PAINTING METAL SURFACES.

- Supply enough materials on the job site to satisfy all coat time windows and recoating requirements.

- Do not open paint containers until ready to use. Keep partial containers sealed.

- Do not use paints that have begun to polymerize, solidify, gel or deteriorate.

Remove and discard paint skin before mixing. Do not use paint if the volume of skin on the surface or sides of the container exceeds 2%.

Use the oldest paint or component first. Apply coating by spraying. Use daubers or sheepskins when no other application method is practical in places that are difficult to access. Use dipping, roller coating, or flow coating only when specifically authorized.

Apply stripe coating before applying each coat. Spot paint or stripe all edges, corner crevices, rivets, bolts, welds, and sharp edges before fully coating the steel. Make sure that striping extends at least 2 inches from the edge. Evenly distribute the stripe coat and work it well into joints, corners, and crevices. Use coating techniques that result in a uniform wet pattern or that comply with the coating manufacturer's written instructions.

Apply paint to the following dry film thickness(DFT):

- Prime Coat: 	3 to 5 mils

Intermediate Coat: 	3 to 5 mils

Top Coat: 	3 to 5 mils

If necessary, apply several coats to achieve the proper thickness. Apply each coat as a continuous film of uniform thickness, free of pores. Make sure all coats are free of runs, sags, and dry spray. Repaint any thin spots or areas missed in the application.

- Make sure each coat is properly cured or dried before applying the next coat.

If any applied coating is damaged, mud cracked, bubbling or blistering, permit it to dry first. Remove damaged areas of paint and prepare the surface again. Feather the edges of existing paint out to 1/2 inch surrounding the spot-cleaned area. Make sure no loose or abrupt edges of paint remain. Repaint the area with the same kind and number of coats as the undamaged area according to the manufacturer's written recommendations. Evenly blend the final spot coat of repair with the surrounding coating.

For final inspection, make sure the top coat is uniform and complete in coverage and appearance. The Engineer will visually inspect the top coat and determine acceptance by total DFT.

## SECTION 514

## CONCRETE SURFACE TREATMENTS

514-1.01  DESCRIPTION. This work consists of providing an aesthetic fascia and anti-graffiti protection on exposed faces of precast and cast-in-place concrete.  Use form liners where designated on the Plans.  Apply anti-graffiti protection where designated on the Plans.

514-2.01 MATERIALS.

1.	Aesthetic Fascia. Provide standard reusable, non-porous form liners conforming to the pattern as specified on the Plans; or approved equal.

2.	Anti-graffiti Protection. Use a two-step graffiti protection system designed specifically for this use.  The system shall consist of a single component clear acrylic base coat covered by a clear urethane finish coat.  This material is not a sealer or vapor barrier and no appreciable discoloration is allowed.

514-3.01  AESTHETIC FASCIA. The wall dimensions and concrete quantities provided on the Plans are minimum and do not include allowances for the thickness of the form liners. Account for the thickness of the form liners. Do not decrease the required minimum clear cover when using aesthetic fascia. Measure provided clear cover at the point where it is a minimum due to the aesthetic fascia.

Cover the form, leaving 6 inches between the edge of liner and the finished top of the wall, pathway or ground grade at the bottom, and edge or expansion joints on the sides. The Engineer shall approve the liner placement on the form prior to the concrete placement.

514-3.02 ANTI-GRAFFITI PROTECTION. Let all concrete surfaces set at least 28 days before applying any coatings. Apply the base coat with a roller or sprayer in accordance with the manufacturer’s recommendations. Apply two coats of the finish coat after the base coat has cured for 72 hours. Apply appropriate masking as required. Exposed faces of wall extend 1 foot below finished grade.

## SECTION 515

## DRILLED SHAFTS

515-1.01 DESCRIPTION. Construct drilled shaft foundations where indicated in the plans. This work includes all labor, materials, equipment, incidentals and services necessary to perform all operations to complete drilled shaft installation.

515-1.02 QUALITY CONTROL. Provide a Quality Control Inspector to ensure that all materials, techniques and methods are suitable to meet or exceed the minimum requirements of the contract.

The Quality Control Inspector shall submit daily reports during drilled shaft installation and testing operations verifying the Contractor’s compliance with requirements of the contract. Include field measurement data, procedural discrepancies, installation problems, names of personnel, equipment usage data, and all other significant information in the daily reports.

515-1.03 PERMITS. Conform to the requirements of the Department obtained permits when constructing drilled shafts and disposing of excavated materials. Obtain all other permits not obtained by the Department required to construct the drilled shafts and dispose of excavation materials.

515-1.04 QUALIFICATIONS. Experience is required for constructing drilled shafts of at least 8 feet in diameter and lengths similar to those indicated on the plans for three separate projects during the previous five years. Experience must include drilling in deep water (greater than 30 feet), drilling in soils with ground water, in soils with large boulders, and in rock.

515-1.05 GENERAL REQUIREMENTS AND SUBMITTALS. Submit the following documents for review and approval no more than one week after the Notice to Proceed:

1.	Project Experience. Provide a list of three drilled shaft projects performed by the Drilled Shaft Contractor that involved drilling in sand, gravel, large boulders and rock similar to those conditions expected at this project location. Provide the drilled shaft plans, logs of test holes, dates of work, type of work, description of work, and amount of work performed. Provide the name and telephone number of a contact person at the agency or company for which the work was completed.

2.	Personnel Experience. Provide a list of the key personnel involved in the drilled shaft construction. Include the name of the superintendent and of the superintendent’s assistants who will be performing and directing the actual drilling operations. Include a resume of each superintendent and assistant involved in drilled shaft construction indicating:

a.	A minimum of five years experience in directing drilled shaft construction of which two years being in responsible charge or operating equipment proposed for this project.

b.	The number of years of recent continuous relevant experience in performing similar drilling operations and operating the contractor proposed equipment for this job.

c.	Detailed recent relevant experience (3 project minimum) including project description, date of work, actual work performed by individual, and a reference for each project including telephone number.

d.	A list of relevant equipment operated including type of equipment and amount and nature of experience.

Only those personnel approved by the Engineer may work on the drilled shaft construction. The Engineer may suspend the drilled shaft work if the Contractor substitutes unauthorized personnel for authorized personnel during construction. If work is suspended due to unauthorized substitution of personnel, the Contractor shall be fully liable for all additional costs resulting from the suspension of work and no adjustment in contract time will be allowed.

Submit the following for review and approval no less than 45 days prior to the anticipated start of drilled shaft construction:

1.	Drilled Shaft Installation Plan. Provide the installation plan for the drilled shaft foundations. Include the following:

a.	Personnel Experience information identified in item number 1.

b.	List the type, number and size of all proposed equipment, including cranes, barges, drills, augers, bailing buckets, final cleaning equipment, desanding equipment, slurry pumps, tremies, concrete pumps, casings, grout pumps, etc. Include manufacturer’s recommended capacities for each piece of equipment.

c.	Details and methods required for construction including temporary work structures and access roads.

d.	Details of sequence of construction operations and sequence of shaft construction including dates and anticipated duration of work.

e.	Details of shaft excavation methods.

f.	Procedure for maintaining correct horizontal and vertical alignment during shaft installation.

g.	Casing diameter and thickness required but not less than that indicated on the plans.

h.	Method to advance casing.

i.	Methods and equipment proposed to prevent displacement of casing and/or shafts throughout shaft construction.

j.	Details for obstruction removal.

k.	The casing grouting plan and procedure if required.

l.	Details of proposed methods to clean shaft after initial excavation.

m.	Details of shaft reinforcement, including methods to ensure centering/required cover, reinforcement cage integrity during placement, placement procedures, cage support, tie downs, etc.

n.	Details of concrete placement, including proposed operational procedures for concrete tremie or pump, concrete placement rates, initial concrete placement procedure, method for raising tremie during concrete placement, and overfilling of the shaft concrete. Also provide provisions to ensure proper final shaft cutoff elevation.

o.	Action plan for correcting defects in the shaft. Defects include but are not limited to the following: tilted casing, partially or completely collapsed casing, partially or completely collapsed reinforcement cage, improper concrete placement, and equipment failure.

p.	Required submittals, including shop drawing, mill certification and concrete mix designs.

q.	Welding Quality Control plan conforming to the requirements of AWS D1.1:2002.

r.	Details for CSL testing procedure including testing schedule, inspector’s name, inspector’s qualifications, required instrumentation and power sources.

s.	Safety plan to be implemented to ensure employee safety. Provide worker safety procedures around the shaft excavation and in the shaft when personnel descend for inspection.

t.	Details of environmental control procedures used to prevent loss of slurry, concrete or other shaft materials into waterways or other protected areas.

u.	Wastewater and concrete disposal procedures.

v.	Other information shown in the Plans, requested by the Engineer or deemed necessary by the Contractor.

The Engineer will evaluate the drilled shaft installation plan for conformance with the Contract Documents and will reject any portion of the plan that is unacceptable.  Partial submittals will not be accepted for approval.  Within 20 days after receipt of the complete plan, the Engineer will notify the Contractor of any additional information required and/or changes that may be necessary in the opinion of the Engineer to satisfy the Contract Documents. Submit agreed upon changes for reevaluation. The Engineer will notify the Contractor within 10 days after receipt of proposed changes of their acceptance or rejection. All approvals given by the Engineer are subject to trial and satisfactory performance in the field.  Do not begin any drilled shaft work without an approved Drilled Shaft Installation Plan.  Do not begin any drilled shaft work without the written approval of the Engineer.

Identify all Critical Path Schedule Items in the drilled shaft installation plan. Provide adequate lead time to obtain concrete mix design approval and permanent metal casing delivery.

Submit the Crosshole Sonic Logging (CSL) results within 5 days of testing. Provide the following:

1.	Crosshole Sonic Testing Report. A report that contains the following:

a.	The CSL logs for all tested tube pairs. Identify the CSL log for each test tube pair indicating the orientation relative to the structure.

b.	The traditional signal peak diagram (time versus depth).

c.	The computer first pulse arrival time verses depth.

d.	The computed pulse wave speed versus depth.

e.	The computed relative pulse energy or amplitude versus depth.

f.	Identification of defect zones, if any, on the CSL logs. Defect zones are defined by an increase in arrival time of more than 20% relative to arrival time in a nearby zone of good concrete.

515-1.06 CERTIFICATIONS. Provide certification that all available geotechnical information provided by the Department has been reviewed and considered in the bid preparation.

515-2.01 MATERIALS. Use materials that conform to the following:

DS Concrete	Section 501

DS Grout	Subsection 701-2.04

Reinforcing Steel	Section 503

Steel for Casing	ASTM A709, Grade 50 or higher

CSL Tubes	ASTM A53

- CONSTRUCTION REQUIREMENTS

515-3.01 GENERAL METHODS AND EQUIPMENT.  Perform the excavations required for the shafts through all materials encountered to the dimensions and elevations shown in the Contract Documents. Use methods and equipment suitable for the intended purpose and the materials encountered. Provide equipment capable of constructing shafts to a depth equal to the deepest shaft shown in the plans plus three times the shaft diameter.

Construct drilled shafts according to the Contract Documents except when permitted otherwise by the Engineer. An alternate method of shaft construction may be proposed. Acceptance for other proposed shaft installation methods will be based upon the suitability of the method to the site conditions and the effect of the method on the structural system.   Submit alternate methods of shaft construction for approval.

Maintain a construction method and soil log during shaft excavation. Submit copies of the log daily. Resolve all differences in the production logs between the Engineer and the Contractor within 24 hours of submittal to the Engineer. Provide at least the following items in the log:

1.	Description and approximate top and bottom elevation of each soil or rock material encountered

2.	Location of all obstructions and time spent removing the obstruction

3.	Drilling rate, down thrust, and torque

4.	Seepage or groundwater

5.	Remarks and comments

Barges, temporary work structures and roads may be required to install the drilled shaft foundation, piers, and bridge superstructure.

515-3.02 CONSTRUCTION METHOD.  Use the permanent casing method.

Permanent Casing Method: Excavate through the casing and advance the casing until reaching the desired penetration. Overreaming the outside diameter of the casing before placing the casing may be necessary.

Casing may be placed in oversized holes and grouted in place using the pre-approved grouting procedure identified in Subsection 515-1.05.

Vibratory and impact hammers may be used to install casing. Casing that is driven or vibrated into place need not be grouted.

Oscillating and rotary type casing installation devices may be used with the Engineer’s approval. Casing that is driven or vibrated into place need not be grouted.

After the concrete has cured according to Section 501, cut the casing off at the prescribed elevation and leave the remainder of the casing in place.

515-3.03 POSITION AND ALIGNMENT. When drilling from a barge, provide a fixed template, adequate to maintain shaft position and alignment during all excavation and concreting operations. Do not use floating templates (attached to a barge). A fixed template for shafts drilled on land will not be required if the Contractor demonstrates satisfactorily to the Engineer that shaft position and alignment can be properly maintained. The Engineer will require a fixed template adequate to maintain shaft position and alignment during all excavation and concreting operations for shafts drilled on land when the Contractor fails to demonstrate to the Engineer’s satisfaction that he can properly maintain shaft position and alignment without use of a template.

515-3.04 EXCAVATIONS AND EQUIPMENT. All shaft excavation from the mudline to the top of bedrock, including the rubble layer, is Unclassified Shaft Excavation. All shaft excavation from the top of bedrock to the bottom of the shaft is Special Shaft Excavation. Mudline, top of bedrock, and bottom of shaft elevations are shown on the Plans. The Engineer will require Drilled Shaft Sidewall Overreaming when necessary.

1.	Unclassified Shaft Excavation. All processes required to excavate a drilled shaft of the dimensions shown in the Contract Documents, completed and accepted. Include in the work all shaft excavation, whether the material encountered is soil, rock, boulders, weathered rock, stone, natural or man-made obstructions, or any other materials.  Special Shaft Excavation begins either when top of bedrock elevation is reached or when drilling operations using conventional equipment reach practical refusal.  Practical refusal is defined as the point where the rate of hole advancement using earth augers with soil or rock teeth, drill buckets, and/or under reaming tools with the drilling equipment operating at maximum power, torque and downthrust, is less than 1 foot after 15 minutes of continuous drilling.

2.	Special Shaft Excavation. All processes required to excavate a drilled shaft of the dimensions shown in the Contract Documents, completed and accepted. Include in the work all shaft excavation, whether the material encountered is soil, rock, boulders, weathered rock, stone, natural or man-made obstructions, or any other materials.  Payment for excavation below the point where Special Shaft Excavation has been authorized will be for Special Shaft Excavation only and will not include payment for Unclassified Shaft Excavation.

3.	Drilled Shaft Sidewall Overreaming. The unclassified excavation required to enlarge the drilled shaft diameter to accommodate the installation of the permanent metal casing. Increase the shaft radius a maximum of 6 inches by overreaming.

If the Engineer determines that the material encountered while drilling the shaft excavation is unsuitable and/or is not the same as anticipated in the design of the drilled shaft, extend the drilled shaft excavations as required by the Engineer.

Provide areas for the disposal of unsuitable materials and excess materials that are removed from shaft excavations, and dispose of them subject to permit requirements and in a manner meeting all requirements pertaining to the approved storm water pollution prevention (SWPP) plan.

Use excavation and drilling equipment having adequate capacity, power, torque, and downthrust to perform the work. Use excavation and overreaming tools of adequate design, size, and strength to perform the work. If the material encountered cannot be drilled using conventional earth augers and/or underreaming tools, provide special drilling equipment, including but not limited to rock augers, core barrels, rock tools, air tools, blasting materials, and other equipment as necessary to continue the shaft excavation to the size and depth required.

515-3.05 CASINGS. Use casings that are of ample strength to withstand handling and driving stresses and the pressure of concrete and surrounding earth materials. Casing may be thickened or reinforced to withstand applied stresses. Internally brace casing during shipping.

Use casings that are smooth and water tight. Provide a casing that is continuous along the entire length of the shaft.

Ensure that the inside diameter of casing is not less than the specified size of shaft. Oversized casing may be used with the Engineer’s approval. The Department will not provide extra compensation for excess concrete required to fill an oversize casing.

If the installed casing does not satisfy the requirements of Subsection 515-3.10, submit casing repair procedure for approval.

Special casing systems may be used with the Engineer’s written approval. Design special casings so that no damage occurs to the drilled shaft foundation.

1.	Grouting. For drilled shaft foundation casings installed in oversized holes or where gaps exist between the shaft excavation and the casing, grout the zone between the casing and the soil with DS Grout. Grout the casing the full depth of the shaft. Use at least six grout placement tubes placed uniformly around the perimeter the full length of the casing. Grout the casing in one continuous operation. Withdraw the grout tubes vertically during grout placement operations. Provide at least two water relief/release pipes on opposite sides of the casing. Withdraw the water relief/release pipes vertically during the grout placement operations.

- Submit the grout placement procedure for approval.

515-3.06 INSPECTION OF EXCAVATIONS.  Do not enter the shaft unless the casing is installed and adequate safety equipment and procedures have been provided.

Inspect the excavations for the following:

1. 	Dimensions and Alignment. Provide equipment for checking the dimensions and alignment of each shaft excavation. Verify the dimensions and alignment of the shaft excavation under the observation and direction of the Engineer. Check the following:

a.	Shaft excavation dimensions and alignment.

b.	Casing dimensions and alignment periodically throughout the installation process.

c.	Casing dimension and alignment in final position.

2. 	Depth. Reference the depth of the shaft during drilling using marks on the Kelly bar or other suitable methods. Measure final shaft depths with a suitable weighted tape or other approved methods after final cleaning.

3. 	Shaft Cleanliness Requirements. Clean the shaft so that at least 50 percent of the base of each shaft has less than 3/4 inch of sediment at the time of concrete placement. Ensure that the maximum depth of sedimentary deposits or other debris does not exceed 1½ inches at any location on the bottom of the excavation. The Engineer will approve shaft cleanliness based on visual inspection for dry shafts. The Engineer will approve shaft cleanliness using divers, Shaft Inspection Device (SID) or other appropriate methods for wet shafts.

- Refer to Subsection 515-3.15 for SID requirements.

4.	Casing. Visually inspect casings above water. Use a Shaft Inspection Device (SID), diver, or other methods as directed by the Engineer to examine the casings below water for defects.

- Refer to Section 515-3.15 for SID requirements.

515-3.07 REINFORCING STEEL CONSTRUCTION AND PLACEMENT.

1. 	Reinforcement Cage Construction and Placement. Tie all intersections of drilled shaft reinforcing steel with cross ties or "figure 8" ties. Use double strand ties or ties with larger tie wire when necessary. The Engineer will give final approval of the cage construction subject to satisfactory performance in the field.

Assemble and place as a single unit the cage of reinforcing steel consisting of; longitudinal bars, ties, spirals, cage stiffener bars, crosshole sonic logging (CSL) tubes and all other components. Place the cage immediately after the Engineer inspects and accepts the shaft excavation and immediately prior to placing concrete. The Engineer will give final approval of the placement subject to satisfactory performance in the field.

2. 	Splicing Reinforcement Cage. If the bottom of the constructed shaft elevation is lower than the bottom of the shaft elevation in the plans, extend a minimum of one half of the longitudinal bars required in the lower portion of the shaft the additional length. Continue the tie bars throughout the extra depth and extend the stiffener bars to the final depth. Splice the longitudinal bar extensions as required.

3. 	Support, Alignment, and Tolerance. Tie and support the reinforcing steel in the shaft so that the reinforcing steel will remain within allowable tolerances as specified in Section 515-3.10.

Use concrete wheels or other approved, non-corrosive spacing devices near the bottom and at intervals not exceeding 15 feet up the shaft to ensure concentric spacing for the entire length of the cage. Do not use block or wire type spacers. Use a minimum of one spacer for each 30 inches of cage circumference.

Provide concrete or other Engineer-approved spacers at the bottom of the drilled shaft reinforcing cage. Maintain the specified distance between the bottom of the cage and the bottom of the shaft. Use one spacer per longitudinal bar unless directed otherwise by the Engineer. Use spacers sized to prevent vertical movement of the cage. Use spacers constructed of material equal in quality and durability to the shaft concrete. Submit spacer information for approval.

Check the elevation of the top of the steel cage before and after placing the concrete. If the cage is not maintained within the specified tolerances, correct it as approved by the Engineer. Do not construct additional shafts until modifying the reinforcement cage support in a manner satisfactory to the Engineer.

515-3.08 FLUID IN EXCAVATION AT TIME OF CONCRETE PLACEMENT.  Prior to placing concrete in any shaft excavation, ensure that contaminated suspensions, which could impair the free flow of concrete from the tremie pipe, have not accumulated in the bottom of the shaft. Take samples of the fluid in the shaft starting 1 foot from the base of the shaft and at intervals not exceeding 10 feet up the shaft, using an approved sampling tool.  Ensure that the density of the fluid in the shaft excavation prior to concreting is less than 70 lb/ft3 for mineral slurries including bentonite and attapulgite and less than 54 lb/ft3 for polymer slurries according to ASTM D 4380. If desanding equipment is required, ensure that the sand content does not exceed 4 percent. Take whatever action is necessary to modify the fluid in the shaft excavation prior to placing the concrete to bring the fluid within the contract requirements.

515-3.09 CONCRETE PLACEMENT.  Place concrete in accordance with Section 501 and the requirements herein.

At no expense to the Department, furnish the additional drilled shaft concrete (over the theoretical amount required to fill the shaft as shown in the Plans) required to complete filling shafts larger than required by the Plans or authorized by the Engineer.

If the pressure head is lost during concrete placement for any reason, the Engineer may direct the Contractor to perform integrity testing at no expense to the Department.

- Cure the top surface of the shaft in accordance with Section 501.

Install grout in all voids between the casing and shaft excavation after placing shaft concrete. Grout permanent metal casing in conformance with the requirements of Section 501.

Pressure wash all concrete overflow from the outside surface of the shaft casing.  Do not allow loose concrete and other debris generated during pressure washing the casing to flow into adjoining bodies of water.

515-3.10 CONSTRUCTION TOLERANCES.  Conform to the following:

1.	Ensure that the top of the drilled shaft is no more than 3 inches laterally from the position indicated in the plans.

2.	Ensure that the vertical alignment of the shaft excavation does not vary by more than ¼ inch horizontally for each foot of depth.

3.	After placing all the concrete, ensure that the top of the reinforcement cage is no more than 2 inches above and no more than 3 inches below plan position.

4.	Ensure that the column and shaft reinforcement cages are concentric with the shaft within a tolerance of 1 inch. Ensure that concrete cover is within 1½ inches of the plan dimension.

5.	Ensure that the top elevation of the drilled shaft concrete is within 6 inches of the top of shaft elevation shown in the plans.

6.	Do not exceed a difference between the major and minor outside diameters at any point along the length of the permanent metal casing (out-of-roundness) of 1 percent of the nominal diameter. The circumference of the permanent metal casing shall not vary more than 3/16 inch from the nominal circumference.

7.	Ensure that the cutting edges of excavation equipment are normal to the vertical axis of the equipment within a tolerance of ±3/8 inch per foot of shaft diameter.

8.	The completed shaft excavation shall have a flat bottom as shown on the plans. The flat bottom of the shaft excavation shall be fully founded on rock and be level within ±3/8 inch per foot of shaft diameter.

9.	Provide a solid concrete shaft without voids or sections of unsound concrete as determined by Crosshole Sonic Logging.

515-3.11 INSTRUMENTATION AND DATA COLLECTION.

1. 	Shaft Inspection Device. The Engineer may use a Shaft Inspection Device (SID) comprised of a television camera sealed inside a watertight jacket to inspect the bottoms of the shafts. Cooperate with the Engineer in using this device. Place the device in position for inspection and removing it after the inspection. Furnish 110 V single-phase current (minimum 30 A service), 220 V single- phase current (minimum 15 A service), and a 150 psi compressor (230 in3/s minimum) to operate the SID.

Notify the Department at least ten days prior to the desired pick-up date. Notify the Department at least ten working days prior to returning the SID.

The Contractor is responsible for the device from the time it leaves its storage area until the time it is returned. During this time, insure the device against loss or damage for the replacement cost ($500,000 minimum) or for the full insurable value if replacement cost insurance is not available. Return the device in good working condition to its proper location within 30 days after completing drilled shaft installation.

2.	Crosshole Sonic Logging. Provide crosshole sonic logging (CSL) inspection of all drilled shaft foundations along their entire lengths in accordance with Subsection 515-1.05. Provide an independent CSL inspector with at least three years experience in CSL testing to inspect the drilled shaft and prepare the CSL report.

Secure CSL tubes (steel pipes) to the inside of the reinforcing steel cage on regular intervals not exceeding 3 feet. Place CSL tubes as near parallel and plumb as possible and around the reinforcement cage perimeter as indicated on the plans. Extend the CSL tube from the bottom of the shaft to at least three feet above the top of the shaft or as directed by the Engineer.

Do not damage CSL tubes. Prior to beginning CSL testing, assure that the test probes can pass through every tube to the bottom. If a tube is obstructed, at your expense core a hole that is near to the obstructed tube and extends to its full depth. The corehole should be large enough to accommodate the CSL probe.

Prior to coring, submit for approval a coring plan including corehole locations and coring equipment and procedures. Provide for complete core recovery and minimize abrasion and erosion of the core. Place the core hole at a position in the shaft that will not produce damage to the reinforcing steel in the shaft.  Log the corehole and submit the log.  Indicate in the log voids and defects located in the core hole. Preserve the cores and make them available for inspection by the Engineer. Commence downhole testing with the corehole treated as an access tube.

CSL tubes shall be schedule 40 pipes that provide an inside diameter of at least 2 inches. Provide CSL tubes with smooth, regular inside surface free of defects and obstructions (including pipe joints) to permit the free movement of a 1¼ inch diameter probe over the entire length of the tube.

- Use mechanical couplers to extend CSL tubes. Seal all CSL tube joints. Do not weld CSL tube joints.

CSL tubes must be watertight. Provide a watertight cap at the bottom of the CSL tube. Provide a watertight, removable cap at the top of the CSL tube. Fill CSL tubes with potable water prior to or within 1 hour after placement of shaft concrete.

The exterior surface of CSL tubes must be free from corrosion, oil, and coatings so that a good bond is provided between the concrete and the tube.

Test the drilled shaft no sooner than 3 days and no later than 10 days after placement of drilled shaft concrete.

Provide the shaft installation and drilling record to the Engineer and CSL Inspector within 3 days of placing shaft concrete.

Perform CSL testing between all adjacent tube pairs and across at least two major diagonals. Perform additional diagonal testing if shaft defects are identified. At your expense, perform as many additional diagonal tests as needed to determine the extent of the shaft defect.

If the CSL results indicate a potential defect, the core the location of the defect as described above for blocked CSL tubes.

If the cores indicate the presence of a defect, repair the shaft at your expense and at no extra cost to the Department.  If a defect is not observed in the cores, the Department will pay for all coring costs and compensation for the delay will be granted by an appropriate time extension. "

After CSL testing has been completed and accepted by the Engineer, remove water from the CSL tube, cut the tube flush with the top of the shaft, and fill the tube with DS Grout.

515-3.12 DRILLED SHAFT EXCAVATIONS CONSTRUCTED OUT OF TOLERANCE.  Do not construct drilled shaft foundations in such a manner that the concrete shaft cannot be completed within the required tolerances. If the contract tolerances are not met, the Contractor may request design changes in the pier to incorporate shafts installed out of tolerance. The Contractor shall bear the costs of redesign and all related costs resulting from approved design changes to incorporate shafts installed out of tolerance. Furnish additional materials and work necessary, including engineering analysis and redesign, to implement corrections of out of tolerance drilled shafts at no expense to the Department.

Provide a proposal on correcting out of tolerance shafts. Do not begin any redesign until the proposal has been reviewed for acceptability and approved by the Engineer in writing.

A Professional Engineer registered in the State of Alaska must perform all redesign to correct for out of tolerance shafts. The Registered Professional Engineer performing the redesign is subject to the approval of the Engineer.

Repair all defects in the shaft identified by Crosshole Sonic Testing. Submit repair procedure for review and approval.

## SECTION 516

## EXPANSION JOINTS AND BEARINGS

516-1.01 DESCRIPTION. Furnish and install expansion joints and bearings according to the Plans.

516-2.01 MATERIALS. Use materials that conform to the following:

Grout	Subsection 701-2.03

Bridge Seals	Subsection 705-2.03

Expanded Polyethylene	Subsection 705-2.06

Structural Steel	Section 716

Elastomeric Bearing Pads	Subsection 720-2.01

Epoxy Adhesive for Elastomeric Bearing Pads	Subsection 720-2.02

Polytetrafluoroethylene (PTFE) Bearings 	Subsection 720-2.03

Water Stops	Section 723

- CONSTRUCTION REQUIREMENTS

516-3.01 EXPANSION JOINTS. Locate and form expansion joints as shown on the Plans.

1.	Shop Drawings. Provide shop drawings for expansion joints having a total movement of more than 1.75 inches. Submit drawings showing installation procedures and joint assembly details. Install joints only after shop drawings are approved.

2.	Manufacture and Fabrication.

a.	Open Joints. Place open joints where shown on the Plans. Remove forms without chipping or breaking the corners of the concrete. Do not extend reinforcement across an open joint, unless shown on the Plans.

b.	Filled Joints. Construct expansion joints with expanded polyethylene joint filler as thick as the width of the joint.

Cut the joint filler to the same shape and size as the adjoining surfaces. Fix the joint filler against the concrete surfaces in place to keep the joint filler from displacing when concrete is placed.

Immediately after removing the forms, inspect the expansion joints. Remove concrete or mortar that has sealed across the joint.

c.	Compression Seals. Shape the joint as shown on the Plans. Install the seal according to the manufacturer’s instructions.

Install the seal in one piece for the full width of the roadway joint. Install the seal immediately after the curing period of the concrete.

d.	Strip Seals. Use expansion joint strip seals in one piece for the length of the joint. Shape the steel components to conform to the section of the concrete. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

e.	Steel Joints. At the shop, shape the plates, angles, or other structural components to conform to the section of the concrete. Fabricate and paint structural shapes to meet the specifications covering those items. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint. Meet the joint opening dimension shown on the Plans.

f.	Modular Seals. Shape the joint as shown on the Plans. Use expansion joint modular seals in one piece for the length of the joint. Ensure that the surface in the finished plane is true and free of warping. When placing the joints, use methods to keep them in correct position during concrete placement that do not affect or modify the structure or joint.

Install the expansion joints according to the manufacturer's recommendations. Adjust the joint opening for the dimensions indicated on the Plans.

g.	Silicone Expansion Joint Seals.  Prepare concrete surface by sandblasting each face until the surface is roughened and all contaminants are removed.  Ensure all joint faces are sound, clean, dry, and free of frost immediately prior to sealant application.  Install a bond breaking backing material that is configured per the sealant manufacturer’s specifications.  Install the sealant according to the manufacturer’s recommendations.

3.	Tolerances. Install expansion joints conforming to the following tolerances:

a.	Top Surface Profile: 1/4 to 5/8 inch recessed from the finished roadway profile.

b.	Surface Irregularities (deviation from a 10-foot straight edge): ±1/8 inch.

c.	Gap Width: ±1/4 inch.

516-3.02 BEARINGS. Install bearing at locations shown on the Plans.

1.	Shop Drawings. Provide shop drawings showing all details of the bearings and of the materials proposed for use. Fabricate bearings only after shop drawings are approved.

2.	Packaging, Handling, and Storage. Prior to shipment from the point of manufacture, package the bearings in a manner to ensure that each bearing will be protected from damage during shipment, handling, and storage. Store the bearings in an area that provides protection from environmental and physical damage. Prior to installation, clean the bearings of all foreign substances.

3.	Construction and Installation. Set the bearing plates, sole plates and elastomeric bearing pads as shown on the Plans in the exact position with full and even bearing on properly finished bearing seats.

Finish bearing areas or grind them to elevation and parallel to the roadway grade and parallel to the roadway cross slope or crown, unless otherwise shown on the Plans.

When shown on the plans, place grout under masonry plates. Mix and place grout according to the manufacturer’s written recommendations. Clean concrete areas that will contact the grout. Remove loose or foreign matter that would prevent the bond between the mortar and the concrete surfaces.

Tightly pack the grout under the masonry plates to provide full bearing. After placing, cover exposed surfaces of grout pads with a heavy thickness of burlap saturated with water for 3 days. Do not place a load on the grout until the grout has attained a compressive strength of 5000 psi as determined by field specimen.

Locate sole plates to correspond with the temperature during erection. Anchor bearing securely. Adjust the nuts on anchor bolts at the expansion ends of spans to permit the span to move freely. Burr threads sufficiently to prevent removal of nuts.

Apply epoxy adhesive to the bottom surface of the elastomeric bearing pads before placing them. Do not move the pad until the epoxy has cured and full adhesion is achieved. Do not apply epoxy adhesive to elastomeric bearings used in PTFE bearing assemblies.

4.	Tolerances. Install bearings conforming to the following tolerances:

a.	Horizontal Position: ±1/8 inch

b.	Elevation: ±1/8 inch

c.	Grade and cross slope: ±1/16 inch per foot.

516-3.03 WATER STOPS. Furnish water stops in continuous, full-length segments without field splices. Do not field splice water stops. Ensure all spliced performed by the Manufacturer are fully vulcanized.

Use spacers, supporting wires, or other approved devices to secure the water stop in the position shown on the plans.

- Remove and replace water stops that are out of position or shape at no expense to the Department.

## SECTION 520

## TEMPORARY CROSSINGS

520-1.01 DESCRIPTION.  For each site where public traffic uses a temporary crossing or a Contractor uses a temporary crossing that is elevated over a public route, construct and maintain the temporary crossing. Remove temporary crossings after use and cleanup the site.

Design temporary bridges, change the preliminary design of approach roads to accommodate temporary bridges, and have an independent design check performed. Inspect and perform quality acceptance on temporary bridges.

520-1.02 DEFINITIONS.

Designer of Record (DOR). A civil engineer registered as a Professional Engineer in the State of Alaska, and in responsible charge of the work described. The DOR must have adequate and relevant prior bridge design and inspection experience. The DOR may delegate portions of design, quality acceptance, and inspection work, to qualified technicians. The DOR and qualified technicians must not be supervised by, or under the direction of the Contractor’s temporary crossing superintendent and work crew.

Independent Engineer (IE). An engineer registered as a Professional Engineer in the State of Alaska, and in responsible charge of the independent design check. The engineer responsible for the check must have adequate and relevant prior bridge design experience. The engineer responsible for the check shall not be employed by the Contractor or the same firm as the Designer of Record; or employed by a firm managed or owned by the Contractor or the Designer of Record; nor shall the engineer performing the work manage or own the Contractor or the firm employing the Designer of Record.

Independent Design Check (IDC). An independent design check of the temporary bridge package including but not limited to: design, location and dimensions of the foundation, structural members, connections, erection plan and temporary bracing (when required), safety barrier, and independent calculations of design loads, member stress, material properties, hydraulic capacity and scour protection.

### Temporary Bridge. A temporary bridge used by the public or over a public route, including abutments, piers, safety barrier and railing, foundation scour protection, and other incidentals.

### Temporary Bridge Package (TBP). Design calculations, working drawings, specifications, and all items identified on Form 25D-080, for a temporary bridge.

Temporary Crossings. A detour route that includes temporary bridges, approach roads and other incidentals.

MATERIALS AND DESIGN

520-2.01 MATERIALS. New or used materials must meet the requirements of the design and the Contract. The DOR must verify the quality of temporary bridge materials before incorporation into the project.

520-2.02 GEOTECHNICAL DATA AND HYDROLOGY REPORT. The Department may provide records of geotechnical investigations.  The Contractor is responsible for obtaining all additional geotechnical data necessary for design and construction of the temporary crossings.

The Department may provide a preliminary hydrology and hydraulics report. The Contractor is responsible for obtaining all additional hydrology and hydraulics data necessary for design and construction of the temporary crossings.

520-2.03 TRAFFIC CONTROL PLAN. Submit a traffic control plan for temporary crossing according to the Plans and Section 643.

520-2.04 DESIGN REQUIREMENTS. Retain the services of a DOR to design temporary bridges, and to provide a TBP. When the temporary bridges are used as a construction platform for the Contractor’s equipment or workers, then design and construct temporary bridges that are wide enough for traffic lanes and construction areas, and strong enough to support design traffic and construction loads.

The Department will provide preliminary designs for approach roads.  The DOR may change the design of approach roads to accommodate temporary bridges.

- 1.	Design temporary crossings according to the following documents:

- DOT&PF Standard Specifications for Highway Construction for recommended material properties, and sampling and testing frequencies and methods.

- AASHTO LRFD Bridge Design Specifications for temporary bridge design criteria, as modified by Subsection 520-2.04; and

- DOT&PF Preconstruction Manual for design criteria for changes to approach roads.

- 2.	Provide working drawings for temporary bridges including:

- All information and details necessary to construct temporary bridges including all items listed in Form 25D-080;

- All dimensions controlling the temporary bridge design and erection, including beam length and spacing, post location and spacing, vertical distance between connections in diagonal bracing, height of bents, and similar design controlling dimensions;

- All design loads and material properties;

- The soil bearing values;

- The openings required to allow the passage of traffic, including horizontal and vertical clearances, and the location of railing or barrier;

- Water design flow, opening size and elevations under superstructure, the high water elevation, and the maximum water flow elevation, and vertical clearances; and

- When a bridge is built over a traveled way show where temporary bracing is used during erection or removal of the bridge, show the sequence of erection and removal, and show details of the temporary bracing used.

- 3.	Design temporary bridges to conform to the following requirements:

- To support 100% of HL-93 live loads or the Contractor’s maximum construction load whichever is greater, without overstress. Follow the most recent version, including interim version, of AASHTO LRFD Bridge Design Specifications. Indicate governing live load on working drawings;

- Design for half the seismic acceleration value of the permanent bridge shown on the Plans;

- Include the capacities and demands of load-supporting members in the design calculations;

- Provide a clear roadway and clear pathway widths equal to or greater than the widths indicated on the plans. Construct the temporary bridge and approach embankments wide enough to provide the widths indicated on the plans, and to safely pass contractor’s equipment during all phases of constructing the new bridge. Provide additional width for construction equipment if the temporary bridge will be used as a work platform during the same time that the roadway and pathway are open to the public;

- Design vertical clearance for the life of the temporary structure. A minimum vertical clearance of 16.5 feet is required above a state highway, local road, or street open to the public. A minimum vertical clearance of 23 feet is required above the Alaska Railroad. A minimum vertical clearance of 17 feet is required between the low elevation of the superstructure and (1) the ordinary high fresh water or (2) mean high salt water elevation of navigable waters;

- Minimum clearance of one foot between the low elevation of the superstructure and the maximum water flow elevation within your proposed construction opening. Calculate the design water discharge for each temporary bridge;

- To support equipment used to install and remove the temporary bridge, and construct or renovate the existing bridge. List equipment type, size, capacity, lifting locations, and traffic patterns during lift on the working drawings. Indicate maximum construction loads and locations of applied construction loads;

- Provide a concrete f shape barrier system on the bridge and bridge approaches.  Anchor barrier system to prevent deflection when impacted. Locate barrier so outside edge is setback a minimum of 12 horizontal inches from outside edge of bridge deck;

- Construct roadway surface of concrete or asphalt.  Construct bridge deck surface of concrete, asphalt, timber or steel;

- Design to comply with the requirements of all permits and environmental commitments, including time windows during which work may occur. Apply for and obtain additional permits or modifications to existing permits as needed;

- Do not use existing bridge components on the project site for temporary bridge construction;

- To support loads from utilities identified in the Contract.

- 4.	Design changes to approach roads must conform to permit requirements, and Department design standards applicable to the design criteria listed on the plans.

520-2.05 DESIGN SUBMITTAL AND REVIEW. Comply with the following:

- Retain a DOR to design temporary bridges and design changes to the approach roads. The design drawings in the TBP must be stamped with the seal of, dated by, and signed by the DOR;

- Retain an IE to perform an IDC; and to stamp with their seal, date, and sign an IDC letter certifying: “The TBP meets the AASHTO LRFD Bridge Design Specifications and the Contract requirements”; and

- Submit the IDC letter with three sets of the TBP (except calculations may be one set), and with three sets of design changes to the approach roads, to the Engineer for review and approval at least 30 days prior to anticipated date of beginning construction of the temporary bridge.

520-2.06 VALUE ENGINEERING. Base your bid on supplying temporary bridge structures according to the Contract documents. After Award you may submit construction value engineering proposals to the Engineer. Proposals must include permitting requirements and timelines for construction. The Department will consider value engineering proposals in accordance with Subsection 104-1.06.

CONSTRUCTION

520-3.01 TRAFFIC MAINTENANCE. Protect and control traffic according to Section 643 and the approved traffic control plan.

520-3.02 CONSTRUCTION REQUIREMENTS. Construct temporary crossings entirely within the right-of-way and within permitted areas. Construct according to the approved TBP. Construct according to the Standard Specifications for Highway Construction with exceptions noted by the DOR and this Section 520.

Bolted steel connections must use load indicating washers. Weld according to Subsection 504-3.01.8 Welding.

Maintain structure and wearing surface of temporary crossings until substantial completion. Maintain temporary bridges in a safe and functional condition. Keep bracing and connections tight, and immediately replace any damaged members or damaged connections. Promptly remove debris caught against, under or inside, temporary bridges.

Limit surface deviations to 3/8 inch, as measured from the testing edge of a 10-foot straightedge, between two contacts on the driving surface of the temporary crossings.

520-3.03 WINTER MAINTENANCE. The Department may accept the maintenance responsibility for winter snow and ice removal only.  The Contractor is responsible for repairs and maintenance for damage resulting from the Department’s action to remove snow and ice, or as required for any other reason.

520-3.04 INSPECTION. The Contractor is responsible for Quality Control, and the construction of temporary crossings, including temporary bridges and approach roads, to conform to the working drawings, specifications and the Contract requirements.

The DOR is in responsible charge of Quality Acceptance and inspection, of temporary bridge materials and construction work. The DOR must verify in writing that the quality of bridge materials meet the design and Contract requirements. The DOR or qualified technician, is required to be on-site and to inspect critical work including but not limited to abutments, piers, pile driving, welding, structural elements, fastening of structural elements, reinforcing steel placement, concrete pours, and foundation scour protection.

The Engineer may sample and test materials, and may reject materials that do not meet the requirements of the design. The Engineer may inspect the construction of temporary crossings at any phase of construction and reject unacceptable work. The Engineer will inspect the finished construction of temporary crossings before public use; however, inspection by the Engineer will not relieve the Contractor from any responsibility for defective work.

520-3.05 APPROVALS. Obtain the following written approvals from the Engineer:

  - TBP prior to beginning temporary bridge construction;

  - Design changes to temporary approach roads prior to construction of approach roads;

  - Temporary bridge construction prior to opening the bridge to traffic; and

  - Approach road construction prior to opening the road to traffic.

Such approvals will not relieve the Contractor of the responsibility for defective work.  The Contractor shall remain responsible for all aspects of the design, location and dimensions of the temporary crossing, including but not limited to materials, foundation, structural members, connections, safety barrier, and for satisfactory and safe construction of all work.

The Engineer’s review and approval of the TBP shall not be construed as a complete review, but will indicate only that the general method of construction and working drawings are acceptable to the Department, that the TBP appears complete, and that a certification of an IDC was provided.

The request to open the temporary bridge to traffic must be supported by a final inspection report that is stamped with the seal of, dated by, and signed by the DOR; and that certifies: “The temporary bridge has reached Substantial Completion as defined in Subsection 101-1.03, conforms to the requirements of the TBP and the Contract, and can support design traffic loads and construction loads, and is suitable for public use.”

520-3.06 CLEANUP. Remove temporary crossings, cleanup site, and stabilize site from erosive forces before final completion. Return the site substantially to its original condition. Additional cleanup conditions may be listed in the permits. Remove piling to one foot below ground level.

# DIVISION 600 – MISCELLANEOUS CONSTRUCTION

## SECTION 601

## METAL FLUME DOWNDRAINS

601-1.01 DESCRIPTION. Furnish and install tapered inlet assemblies, metal flume downdrains, and anchor assemblies, at the locations shown on the Plans.

601-2.01 MATERIALS. Fabricate tapered inlets and flume downdrains using any one of the base metals listed in AASHTO M 36 or AASHTO M 196. Use a minimum sheet thickness of 0.060 inches. Use steel nuts and bolts, galvanized according to AASHTO M 232.

601-3.01 CONSTRUCTION REQUIREMENTS. Fabricate downdrains according to the details and dimensions shown on the Plans. Weld bulkheads and flume pieces to the inlet assembly to form watertight connections.

Do not use dissimilar metal at any one installation. Anchor assemblies shown on the Plans may be used with an aluminum installation if the anchor assemblies are electrically insulated.

Connect flume downdrain sections together and to the inlet assembly using galvanized bolts as shown on the Plans.

## SECTION 602

## STRUCTURAL PLATE PIPE

602-1.01 DESCRIPTION. Construct galvanized corrugated steel plate or aluminum alloy plate pipes, at the locations shown on the Plans.

602-2.01 MATERIALS. Use materials that conform to the following:

Pipe 	Subsection 707-2.04

Bedding and backfill 	Subsection 204-2.01

602-3.01 CONSTRUCTION REQUIREMENTS. Lay field-assembled plate pipes in conformance to the lines and grades approved by the Engineer. Excavation, grading, and backfill must conform to Subsection 204-3.01.

- Repair damage to the zinc coating according to AASHTO M 36.

Pre-shape bedding material to fit the lower portion of the pipe. Pre-shape to a depth of one-tenth of the pipe height and wide enough to permit compaction under the haunches. Strutting is not permitted.

When elongated pipes are specified, form the plate sections at the factory so that the pipe’s vertical dimension is increased by 5% of the specified diameter.

Provide the Engineer with a copy of the manufacturer's recommendations and instructions and comply with them.

## SECTION 603

## CULVERTS AND STORM DRAINS

603-1.01 DESCRIPTION. Construct or reconstruct culverts and storm drains (pipe), to the lines and grades shown on the Plans.  Install culvert marker posts.

603-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

Joint Mortar	Subsection 705-2.04

Flexible Watertight Gaskets	Subsection 705-2.05

Non-Reinforced Concrete Pipe	Subsection 706-2.01

Reinforced Concrete Pipe 	Subsection 706-2.02

Corrugated Steel Pipe and Pipe Arches	Subsection 707-2.01

Bituminous Coated Corrugated 
 Steel Pipe and Pipe Arches	Subsection 707-2.02

Corrugated Aluminum Pipe 	Subsection 707-2.03

When Item 603(17), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP), Corrugated Aluminum Pipe,  or Reinforced Concrete Pipe. End Sections for Metal Pipe must be of the same material as the pipe.

When extending in-place metal culverts and/or reattaching end sections with dissimilar metal, provide an electrical insulating material to separate the dissimilar materials. The insulating material must be at least 1/16 inch thick and be approved by the Engineer.

Select pipe for each installation which meets or exceeds the requirements shown on the Plans for height of cover.

Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts. The color shall be blue with no other markings. The 2.5 inch by 6 foot post shall be rectangular in cross section with reinforcing ribs capable of withstanding a bending radius of 9 inches.

- CONSTRUCTION REQUIREMENTS

603-3.01 GENERAL. Excavation, bedding, and backfill must conform to the requirements of Subsections 204-2.01 and 204-3.01, and the details on the Plans.

603-3.02. LAYING PIPE. Begin the pipe laying at the downstream end of the pipe. Keep the lower segment of the pipe in contact with the shaped bedding throughout its full length. Place bell or groove ends of rigid pipe and outside circumferential laps of flexible pipe facing upstream.

Lay paved or partially lined pipe so that the longitudinal center line of the paved segment coincides with the flow line. Install elliptical conduit and circular conduit reinforced with other than a full circular cage or cages so the orientation of a vertical plane through the longitudinal axis of the conduit does not vary more than 5 degrees from the design orientation.

- Repair damaged metallic coating on metal pipe according to AASHTO M 36.

603-3.03 JOINING PIPE.

1.	Rigid Pipe. Use either bell and spigot or tongue and groove joints. Join pipe sections so that the ends are fully entered and the inner surfaces are reasonably flush and even.

Use one or more of the following joint materials, or any other if approved:

- Portland cement mortar

- Portland cement grout

- Rubber gaskets

- Oakum and mortar

- Oakum and joint compound

- Coupling bands

- Preformed plastic sealing compound

Make mortar joints using an excess of mortar to form a bead around the outside of the pipe. Finish the joint smooth on the inside.

For grouted joints, use molds or runners to retain the poured grout. Install rubber ring gaskets to form a flexible, watertight seal. When using oakum, caulk the joint and then seal it with the specified material.

When using Portland cement mixtures, protect the completed joints against rapid drying using suitable covering material.

2.	Metal Pipe. Join metal pipe firmly using one of the following types of coupling bands. Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case more than 0.052 inches lighter.  Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe of similar or dissimilar materials, regardless of the type of coupling band. Except, the end section joint does not require a gasket. Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

- Primary Band. Furnish and install corrugated bands so that the band corrugations match and conform to the corrugations of the pipe. Conform to the following guidelines:

- The gap between the pipe being joined is in the center of the band and is no wider than one corrugation width.

- Bands for 12-inch through 30 inch diameter pipe are at least 12 inches wide.

- Bands for pipe with diameters greater than 30 inches are at least 22 inches wide.

- Secondary Band. Use this band only where it is not physically possible to use primary bands, such as on field-cut pipe ends, joining new pipe to existing pipe, etc. Furnish and install deformed metal sheet bands (dimple bands) so that the projections match and are the same depth as the pipe corrugations. Form these projections in circumferential rows with one projection for each corrugation of the helical pipe.  Use of dimpled bands is restricted to extending culverts or storm drains that are encountered on the Project. Use of dimpled bands shall not be allowed for culverts and storm drains constructed as part of the Project.

Conform to the following guidelines:

- The gap between the pipe being joined is in the center of the band and is no wider than 2 inches.

- Bands for 12-inch diameter pipe are at least 12 inches wide and have one circumferential row of projections for each pipe end being joined.

- Bands for pipe with diameters greater than 12 inches are at least 24 inches wide and have two circumferential rows of projections for each pipe end being joined.

- Furnish and install these bands with a gasket that resists infiltration and leakage.

3.	Polyethylene Pipe. Ensure that polyethylene pipe couplings are corrugated to match the pipe corrugations and that their width is not less than one half the nominal pipe diameter.  Install a gasket in all pipe joints; joints between new sections of pipe and joints between new and existing sections of pipe. Except, the end section joint, and where the pipe is manufactured with a locking joint such that the joint seals watertight, a gasket is not required. Use flexible watertight gaskets (ASTM D 1056 2B3) as specified in Subsection 705-2.05.

Furnish all bolted connections on coupling bands with cutwashers placed between the nut and the angle bracket or use nuts with integral washers.

- Take up any pipe that is out of alignment, unduly settled, or damaged and re-lay or replace it.

603-3.04 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. Forty two inches of post shall remain above the ground after driving.

## SECTION 604

## MANHOLES AND INLETS

604-1.01 DESCRIPTION. Inspect existing, construct, reconstruct, relocate, or adjust manholes and inlets.

Sanitary Sewer Facilities:

Coordinate with the Engineer and AWWU; and participate in a pre-construction condition inspection, and a post-construction condition inspection of the sanitary sewer facilities.

Storm Drain Facilities:

Coordinate with the Engineer and participate in a pre-construction condition inspection of the storm drain facilities.

The pre-construction inspections may identify additional items, manhole metal frames, covers, lids, catch basin inlets and grates, to be repaired and or replaced. Make repairs and or replace additional facility items as directed by the Engineer.

604-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501

Clay or Shale Brick	Subsection 704-2.01

Concrete Brick	Subsection 704-2.02

Concrete Masonry Block	Subsection 704-2.03

Joint Mortar	Subsection 705-2.04

Flexible Watertight Gaskets	Subsection 705-2.05

Reinforcing Steel	Subsection 709-2.01

Precast Concrete Manhole Sections	Subsection 712-2.05

Frames, Grates, Covers,

& Ladder Rungs	Subsection 712-2.06

Corrugated Metal Units	Subsection 712-2.07

604-3.01 CONSTRUCTION REQUIREMENTS. Install precast concrete manholes consisting of a base, risers, cone or flat top; with ladder rungs, pipe boots, frame and cover as shown on the Plans. Use flexible watertight gaskets between concrete sections. Tighten watertight boots over all pipes, then grout pipes in place.

Install inlets consisting of a precast concrete catch basin box, risers, metal frame and grate as shown on the Plans. Grout pipes into place.

Construct poured concrete manholes and inlets to conform to the requirements of Section 501 and the details shown on the Plans.

- Use full mortar joints no more than 1/2 inch wide.

- Set metal frames in full mortar bed.

When specified, plaster the outside face of concrete structures with a 1/2 inch thick cement-sand mortar coat.

- Cure exposed surfaces of concrete and masonry with wet burlap for at least 48 hours.

Fit each pipe section flush on the inside of the structure wall and to project far enough outside to connect properly with the next pipe section.

- Fit masonry neatly and tightly around the pipe.

Construct invert channels in all manholes used for sanitary or combined sanitary and storm sewers. Construct channels to be smooth and semicircular to conform to the inside of the adjacent sewer sections. Make changes in flow direction along a smooth curve with as large a radius as the manhole size permits. Make gradual and even changes in channel size and grade.

Form invert channels by using any of the following methods:

1.	Directly in manhole concrete base

2.	Built up with brick and mortar

3.	Laying half tile in concrete

4.	Breaking out the top one-half of full sections of pipe, laid through the manhole, after the surrounding concrete has hardened

Construct smooth floor outside the invert channel so that it slopes towards the channel not less than 1 inch or more than 2 inches per foot.

Adjust existing manhole or inlet by raising or lowering the frame or ring casting 12 inches or less, without reconstructing the cone section.

Reconstruct existing manhole by using one or more of the following methods:

1.	Bring the manhole frame and cover to grade if you remove the cone for lowering.

2.	Raise the manhole frame and cover more than 12 inches.

3.	Reconstruct a portion of the manhole with no change in line or grade.

4.	Tap one or more additional pipes into an existing manhole.

5.	Rotate the manhole cone to align the lid to the shoulder, lane line, or middle of driving lane.

6.	Rotate the manhole cone to align the inlet casting to the curb line.

7.	Align the access stairs by rotating the barrel sections or install new steps.

Reconstruct the manhole to the required elevation so that it conforms to plan details. Complete this work according to the requirements for new construction. Reuse material only if the Engineer approves.

Align manholes designed to fall within the paved roadway surface so that the casting is not in the driving lane wheel path or in the gutter pan flow line.

In roadways, set the manhole frame and cover flush with or no more than 3/8 inch below the finished pavement surface. In walkways and bike paths, set the manhole frame flush with the surface.

- Do not impede existing sewer flow during construction.

- Relocate inlet by removing and reinstalling inlet box, frame, and grate at new location.

- Relocate manhole by removing and reinstalling manhole barrel, cone, frame, and cover at new location.

## SECTION 605

## UNDERDRAINS

605-1.01 DESCRIPTION. Construct underdrains and blind drains, underdrain outlets, cleanouts, and marker posts.

605-2.01 MATERIALS. Use materials that conform to the following:

Porous Backfill Material 	Subsection 703-2.10

Perforated Concrete Pipe 	Subsection 706-2.03

Perforated PVC Pipe	Subsection 706-2.06

Perforated Corrugated Polyethylene Pipe	Subsection 706-2.07

Corrugated Steel Pipe	Subsection 707-2.01

Bituminous Coated Corrugated Steel Pipe	Subsection 707-2.02

Corrugated Aluminum Pipe	Subsection 707-2.03

Gray Iron Casting	Subsection 719-2.02

Marker Post	Subsection 730-2.05

- CONSTRUCTION REQUIREMENTS

605-3.01 PIPE INSTALLATION. Excavate trenches to the dimensions and grade required by the Plans or as directed. Place and compact a 3-inch minimum bedding layer of porous backfill material in the bottom of the trench for its full width and length.

Use coupling bands for 6 inch, 8 inch, and 10 inch diameter corrugated underdrain that are 2 piece, 7 inch minimum width and corrugated to match the corrugations of the pipe.

Place perforated pipe with the perforations down. Join pipe end sections securely with the appropriate coupling fittings or bands. Plug or cap up-grade ends of subdrain pipe to prevent entry of soil materials.

After the pipe installation has been inspected and approved, place porous backfill material to a height of 12 inches above the top of pipe. Place and compact the remainder of the porous backfill material as specified in Section 204, to the required height. Fill trench above the porous backfill with specified material.

605-3.02 UNDERDRAIN OUTLETS. Excavate trenches for underdrain outlets to the width and depth shown on the Plans. Lay pipe in the trench with ends firmly joined. Backfill the trench after inspection and approval of the pipe installation.

605-3.03 BLIND DRAINS. Excavate trenches for blind drains to the width and depth shown on the Plans. Fill the trench with specified backfill materials to the depths required by the Plans. Compact all backfill material.

## SECTION 606

## GUARDRAIL

606-1.01 DESCRIPTION. Construct new guardrail, terminal sections, and guardrail/bridge rail connections of the kind and type specified.

Remove and reconstruct or remove and dispose of existing guardrail, terminal sections, and guardrail/bridge rail connections.

- Furnish and install bollard(s) included in the Plans and Specifications.

Construct all new permanent crash cushions to shield the hazard width and travel direction shown in the plans.

606-1.02 SUBMITTALS. Submit the following for crash cushions:

1.	A letter from the Manufacturer or their approved representative with the name of their representative, certification of their installation contractor, and their recommendations for the crash cushions shown on the plans, including product information, foundations, and rigid backup or transition connection type.

2.	A copy of the manufacture's installation requirements and recommendations. Provide detailed assembly instructions and shop drawings for the crash cushion, foundation, and rigid backup anchorage, or transition connection before beginning installation.

3.	FHWA Acceptance Letters(s) for the crash cushion submitted to support either AASHTO Manual for Assessing Safety Hardware (MASH) Test Level 3 or NCHRP 350 Test Level 3. Acceptance must include the shielding typical hazard widths and travel directions shown in the plans.

4.	AASHTO acceptance or written updates for the crash cushion classification as noted in the 2011 AASHTO Roadside Design Guide, Section 8.4.

5.	Manufacturer Certified Installers: Submit the installer certification to the Engineer at the Preconstruction Conference.

606-2.01 MATERIALS. Use materials that conform to the following:

- Concrete, Class A

(or an approved, pre-mixed, sacked concrete)	Subsection 501-3.01

Wire Cable 	Subsection 709-2.02

Metal Beam Rail	Subsection 710-2.04

Guardrail Posts and Blocks	Subsection 710-2.06

Guardrail Hardware	Subsection 710-2.07

Terminals	Subsection 710-2.11

Terminal  Markers. Single piece marker, constructed of a durable UV resistant, continuous glass fiber and marble reinforced, thermosetting composite material.

1.	designed for use as road markers

2.	impact-resistant temperature range, -40°F to +140°F

3.	0.125 by 3.75 inches by 66 inches long, 18 inch burial depth

Furnish white flexible markers with a 3 inch by 12 inch retroreflective sheeting, color orange, shall meet AASHTO M 268-08 requirements for Type VIII or IX. Alternately, use 3M Diamond Grade DG3 or approved equivalent.

Fabricate guardrail reflector assembly brackets from aluminum alloy, galvanized steel, or polycarbonate. Use reflective sheeting meeting AASHTO M 268-08 requirements for Type VIII or IX.  Alternately, use 3M Diamond Grade DG3 or approved equivalent.

- Bollards.

Concrete; Class A	Subsection 501-3.01

Shapes, Plates and Bars		ASTM A 36

Bollard Pipe	Subsection 716-2.06

Bollard Tube	ASTM A 500, Grade B

Welding	Subsection 716-2.02

Galvanizing	Subsection 716-2.07

Galvanizing Repair	ASTM A 780

Paint (Paint for Steel Structures/
   Paint of Timber)	Subsection 708-2.01/2.02

Bollard Post (WCLIB; Posts and Timbers, 
Douglas Fir-Larch No. 1)	Subsection 713-2.01

Preservatives and Pressure Treatment 
Process for Timber	Subsection 714-2.01

Backfill Material (Selected Material, 
   Type A)	Subsection 703-2.07

Retroreflective Bands (6 inch wide 
   reflector, smooth surface bands)	AASHTO M 268, Type III-A

- Crash Cushion.

Generally acceptable crash cushion classifications are listed in the AASHTO Roadside Design Guide. The Engineer will determine the final classification of each materials submittal. Each crash cushion in the plans is specified as one of the following:

1.	Sacrificial: These are demonstrated to be designed for a single impact. These may also be "narrow" crash cushions or "median barrier" crash cushions as defined by the FHWA Office of Safety.

2.	Reusable Crash Cushion. These are demonstrated to have some major components that survive most impacts intact and can be salvaged when the unit is being repaired.  Some components need to be replaced after a crash.

3.	Low-maintenance or Self-restorable Crash Cushion. These are demonstrated to suffer very little, if any damage, upon impact and are easily pulled back into their full operating condition. They may partially rebound after an impact and may only need an inspection to ensure that no parts have been damaged or misaligned.

Crash Cushion – Flexible Marker Post: Provide Carsonite CIB-380, TAPCO Curve-Flex, TrafficWorks Guardian TW-375, or approved equal.

- CONSTRUCTION REQUIREMENTS

606-3.01 GENERAL. Install guardrail and terminals at the locations shown on the Plans. Conform to these Specifications and the Standard Drawings with the following exception. Modify Standard Drawing G-20.10 to only allow an offset of 1.5 feet for the ET-2000.

At locations where public traffic is adjacent to guardrail work, have all materials on site, including crashworthy terminals, that are required to completely install a segment of guardrail before beginning work on that segment.

Start guardrail installation at the “upstream” end (the end adjacent traffic will encounter first) by either installing a crashworthy terminal or connecting to an existing barrier. Continue installation in the direction of traffic. Exception: if the guardrail run will connect to existing barrier, buried in the backslope, or guardrail, existing or new bridge railing, or other existing structure at the “downstream” end, guardrail installation may be started at the point of connection.

Do not leave posts installed for guardrail within the clear zone for more than 48 hours before installing the rail. At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

If guardrail runs are not completed within 10 calendar days after beginning installation, install temporary crash cushions meeting NCHRP 350 or MASH test level 3 at all non-crashworthy guardrail ends within the clear zone. Apply Traffic Price Adjustment if the Contractor does not comply with the crash cushion requirement.

- When possible, proceed with construction of guardrails with the direction of traffic.

- Where necessary, adjust the height of existing guardrail to provide a smooth transition to new guardrail.

After shaping the slopes and staking proposed guardrail terminal section locations, request the Engineer to field verify their locations. Receive approval of the staked locations before installing terminal sections.

- Treat field cuts to timber posts and blocks according to AWPA standard M 4.

- Install synthetic blocks according to manufacturer’s recommendations.

Install side-mounted guardrail reflectors as follows:

- At intervals noted on the Standard Drawings, starting with the first standard guardrail post

- With the reflective sheeting facing approaching traffic

- With both faces reflectorized, on two-way roadways

- Not on the terminal sections

At the end of each work shift, install drums or Type II barricades with flashing warning lights to delineate incomplete sections of guardrail and terminal sections.

606-3.02 POSTS. Set posts to accommodate the line, grade, and curvature shown on the Plans.

Use either wood or steel posts when allowed by the type of guardrail specified, subject to the following:

- Exclusive of end treatments, use one type of post material on the project unless extending an existing run of guardrail.

- Match existing post material to extend an existing run of guardrail.

Set posts as follows:

- Set posts plumb, in the location and to the depth shown on the Plans or Standard Drawings.

- Choose an installation method that does not damage the post, adjacent pavement, structures, utility conduits, and final slopes. Repair all damage to the satisfaction of the Engineer, or replace the damaged item, as per subsection 105-1.11.

- Set wood or steel posts in dug, drilled, or pre-punched holes. Steel posts may also be set by ramming or driving if:

- The underlying material is no larger than six inch; and

- The posts are not damaged during installation.

  - Backfill and compact around posts with material as specified in the typical section to firmly support the post laterally and vertically. Compact under and around posts to the Engineer’s satisfaction.

  - In solid rock or in broken rock embankment, construct holes for posts, no ramming or driving in the rock will be allowed.

  - In new roads, install posts before final shoulder or median compaction, surfacing, and paving.

606-3.03 BEAM RAIL. Fabricate metal work in the fabricator’s shop. Bend curved guardrail elements with radii less than or equal to 100 feet in the fabricator’s shop or with an approved bending apparatus.

Receive approval before field punching, cutting, or welding. Repair damaged spelter coat areas on galvanized rail elements according to AASHTO M 36.

- Lap rail elements so that the exposed ends face away from approaching traffic.

Use bolts long enough to extend at least 1/4 inch beyond the nuts. Except where required for adjustments, do not extend bolts more than 1 inch beyond the nuts.

- Locate bolts at expansion joints at the center of the slotted holes.

- Tighten bolts at expansion joints to snug-tight. Make all other bolts fully-tight.

606-3.04 CABLE RAIL. Install cable guardrail according to the Plans and Specifications. Install at the locations shown on the Plans.

606-3.05 TERMINAL SECTIONS. Install terminal sections according to the manufacturer’s recommendations. Install where shown on the Plans.

- Follow Section 203 for excavation and embankment requirements.

Attach flexible markers, in a vertical position, to the first post of each parallel guardrail terminal using two pipe bracket holders spaced 24 inches apart. Attach to wooden guardrail posts with wood screws and to steel guardrail posts with hex bolts.  Attach flexible markers in the same manner to the “P.T.” post of Controlled Release Terminals.

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Remove and reconstruct guardrail as specified. Replace lost or damaged materials without extra compensation.

Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 14 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL. Remove the existing guardrail shown on the Plans, including the rail, cable elements, terminal sections, hardware, posts, concrete bases, and steel tubes. Backfill resulting holes with material in 6-inch layers that is similar to the existing embankment and compact to the same approximate density. Removed items become your property.

- Guardrail.

Notify the Engineer a minimum of 5 days before removing guardrail. The Engineer will notify the ADOT&PF, M&O, and have an M&O representative designate portions of guardrail for salvage. Deliver salvaged guardrail and associated hardware to the M&O yard located on Tudor Road. Remaining items removed become the Contractor's property.

- Crash Cushion.

Notify the Engineer a minimum of 5 days before removing crash cushions. The Engineer will notify the ADOT&PF, M&O, and have an M&O representative designate portions of the crash cushion for salvage. Deliver salvaged crash cushion and associated hardware to the M&O yard located on Tudor Road. Remaining items removed become the Contractor's property.

606-3.08 ADJUST EXISTING GUARDRAIL. When called for on the Plans, reset existing guardrail to the height shown on the applicable Standard Drawing, measured from the top of the rail to the finished shoulder surface below the rail. Raise and lower the posts several times to prevent settlement and then re-drive them to the height shown on the Plans. Use other methods if approved.

606-3.09 FLEXIBLE MARKERS. For each rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

606-3.11 LENGTH OF NEED VERIFICATION. After shaping the slopes and staking the proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine additional guardrail is necessary and the Contractor shall comply without delay.

606-3.12 BOLLARDS.

- Steel Bollards. Galvanize all steel members and hardware.

a.	Perform all welding according to AWS D1.1.

b.	Shop galvanize steel bollards and associated hardware, after fabrication.  Repair damage to galvanizing after installation.

- Wood Bollards. Preservative treat all wood material.

a.	Treat field cuts, bolt holes and similar according to AWPA Standard M4.

Installation. Install bollards in concrete, plumb, back fill with specified material, and compact to the satisfaction of the Engineer. Padlock keys shall be given to the Engineer.

Paint. Shop paint steel bollards with one coat of primer and two top coats of safety yellow. At the site repair nicks, scratches, and other damage.  In the shop and field, clean, prepare the surface and apply the materials as recommended by the manufacturer.

Retroreflective Bands. Apply two white retroreflective bands placed 3-4 inches from the top with a maximum of 6 inches between the bands.

606-3.13 CRASH CUSHION. Install crash cushions according to the manufacturer's recommendations.

Manufacturer's Representative. Provide the services of a manufacturer's representative to review both the initial planned installation and the final installation. Pre-installation inspection and observation of the installation onsite is not required. Cooperate with the Manufacturer's Representative and the Engineer to ensure the materials are placed according to these specifications and the manufacturer's recommended procedures.

Manufacturer Certified Installers. Install crash cushions using installers certified by the materials manufacturer. Install Crash cushions as follows:

1.	Parallel to the approach traveled way or as shown on the plans.

2.	Follow Section 203 for the excavation and embankment requirements of the concrete base component of the crash cushion.

3.	Follow Section 501 for a concrete pad, sized according to the manufacturer's recommendations, constructed on a minimum of 12 inches of Selected Material, Type B.

4.	Cut or fill to the top of the concrete pad with Selected Material, Type B at 12:1 or shallower on installations in grass median.

5.	Install top elevation of concrete pad flush to pavement edge when adjacent to or within asphalt pavement.

6.	Bolt crash cushion to median barrier with manufacturer approved barrier to crash cushion connector when attached to median barrier.

7.	Install a flexible marker post on the nose of each crash cushion, Use a yellow post 3-inch to 4-inch wide by 78-inch long. Attach the marker post to the inside of the crash cushion nose piece with two 3/8-inch stainless steel bolts, nylon lock nuts, and 1 1/2-inch fender washers (two per each bolt), spaced 10-inch apart. The marker post is in addition to, not a substitute for, the reflective tape delineation installed on the crash cushion nose.

Provide permanent crash cushions with performance features designed to minimize the impacts of snow and ice buildup due to frequent freeze and thaw cycles. Crash cushions using supports which interlock and travel within fixed tracks at or below the first six inches from ground level are not accepted for permanent winter use. Crash cushion covers must be provided when available from the manufacturer.

## SECTION 607

## FENCES

607-1.01 DESCRIPTION. Construct fence and gates. Reconstruct fences previously removed. Include barbed wire, where shown on the Plans.

Woven wire fence consists of galvanized woven wire fence fabric, metal posts, and all fittings and hardware.

Chain link fence consists of chain link fence fabric, metal posts, and all fittings and hardware. The height of chain link fences must conform to the Plans.

Barbed wire consists of galvanized barbed wire and all fittings and hardware required for fastening to either a woven wire fence or a chain link fence, as shown on the Plans.

607-2.01 MATERIALS. Use materials that conform to the following:

Concrete (or an approved, pre-mixed,

sacked concrete)	Subsection 501-3.01

Barbed Wire	Subsection 710-2.01

Woven Wire	Subsection 710-2.02

Chain link Fabric	Subsection 710-2.03

Fence Posts	Subsection 710-2.05

Any one of the types of chain link fabric specified in Section 710 may be furnished under Item 607(3), Chain link Fence. Intermixing fabric types is not allowed.

607-3.01 CONSTRUCTION REQUIREMENTS. Clear and grub as necessary to construct the fence to the required grade and alignment.

Before installing fence, grade the existing ground along the fence line to a smooth, uniform surface so there are no abrupt grade changes between adjacent fence posts.

At locations where breaks in a run of fencing are required, or at intersections with existing fences, adjust post spacing to conform to the requirements for the type of closure indicated.

When the Plans require that posts, braces, or anchors be imbedded in concrete, install temporary guys or braces as required to hold the posts in proper position until the concrete has set sufficiently to hold the posts. Do not install any materials on posts or place strain on guys and bracing set in concrete until 7 days after placing the concrete.

- Set the tops of all posts to the required grade and alignment. Do not cut the tops of the posts.

In areas where muck excavation is designated on the Plans or in unstable areas as determined by the Engineer, drive fence posts as shown on the Plans or as directed.

Attach the required size and type of wire or fencing firmly to the posts and braces in the manner indicated. Stretch all wire taut and install it to the required elevations.

At each location where an electric transmission, distribution, or secondary line crosses any of the types of fences covered by these Specifications, furnish and install a ground rod and connection to the fence meeting the requirements of Section 9 of the NESC.

Place ground rods and connectors at maximum intervals of 400 feet along the fence. When fence runs are less than 400 feet long, place one ground rod with connection to the fence.

Coordinate fence construction operations so that livestock do not escape. Connect existing cross fences to the new posts. Place braces for every direction of strain at the junction with existing fences. Fasten the wire in both fences properly to the posts. At bridges, cattle passes, and at culverts if shown on the Plans, connect the new fence to the structure so that livestock can pass freely through or under the structure.

- Fasten fence fabric and wire to the highway side of the posts.

Treat changes in line where the angle of deflection is 30 degrees or more as a corner. Install corner posts.

Treat changes in line where the angle deflection is between 15 and 30 degrees as alignment angles. Fasten adjacent posts to the angle posts using wire. If using wire is impracticable, brace the posts as detailed on the Plans for gate, end, and center posts.

At all grade deflections and alignment angles where stresses tend to pull the posts from the ground, snub or guy the fencing at the critical point using a double strand of 9 gage galvanized wire. Connect the wire to each horizontal line of barbed wire, or to the top and bottom of wire mesh fabric, and to a deadman weighing approximately 100 pounds, buried in the ground not less than 2 feet. Pull the fencing snug to the ground before snubbing or guying.

Erect reconstructed fences carefully using approved salvaged materials. Match any new materials required for reconstructed fence with the existing materials as closely as possible.

## SECTION 608

## SIDEWALKS

608-1.01 DESCRIPTION. Construct asphalt (HMA) or concrete sidewalks, pathways, medians and curb ramps.

608-2.01 MATERIALS. Use materials that conform to the following:

- Concrete Sidewalk

Bed Course Material 	Subsection 703-2.03

Joint Fillers	Subsection 705-2.01

Joint Sealer	Subsection 705-2.02

Concrete, Class A	Section 501*

* Except that in Subsection 501-3.02.3, delete a., b., and c.

- Asphalt Sidewalk

Bed Course Material 	Subsection 703-2.03

Asphalt Cement, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix design Requirements (ATM 417):

Marshall Stability, lb., min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

- CONSTRUCTION REQUIREMENTS

608-3.01 CONCRETE SIDEWALKS. Excavate to the required depth and to a width necessary to install and brace the forms. Shape and compact the foundation to a firm, even surface conforming to the section shown on the Plans. Replace soft and yielding material with approved material. Compact bed course material according to Subsection 203-3.04.

Use full depth forms made of wood or metal. Use forms that are straight, free from warp, and strong enough to resist the pressure of the concrete without springing. Coat forms with an approved form-release agent. Brace and stake the forms so that they maintain their position until their removal.

- Thoroughly moisten the foundation immediately before placing the concrete.

Finish the surface under Subsection 501-3.09.4. Do not plaster the surface. Edge all outside slab edges and all joints to a 1/4 inch radius.

Make expansion joints to the dimensions and spacing shown on the Plans and fill with the type of preformed expansion joint filler specified.

Divide the sidewalk into specified sections using dummy joints formed by a jointing tool or other acceptable means. Make dummy joints 1/3 the depth of the concrete and approximately 1/8 inch wide.

Form construction joints around all appurtenances such as manholes, utility poles, buildings, or bridges, extending into and through the sidewalk. Install preformed expansion joint filler 1/2 inch thick in construction joints. Extend the expansion joint material the full depth of the walk.

- Apply joint sealer evenly to completely seal all joints.

Cure concrete under Subsection 501-3.10 for at least 72 hours. During the curing period, exclude all pedestrian and vehicular traffic. Exclude vehicular traffic for additional time as directed.

608-3.02 ASPHALT SIDEWALKS. Place bed course material in layers. Compact it according to Subsection 203-3.04.

Place asphalt material on the compacted bed course in one or more courses as indicated on the Plans. Compact it uniformly to the required depth. Use a power roller of an acceptable type and weight. In areas inaccessible to the roller, use other approved methods.

608-3.03 CURB RAMPS. Construct curb ramps according to the details and the locations shown on the Plans. Follow the construction requirements of Subsection 608-3.01. Give the exposed concrete surface a coarse broom finish. Install detectable warnings.

608-3.04 DETECTABLE WARNINGS. Construct detectable warnings according to the details and the locations shown on the Plans. Install detectable warning tile by embedding tile flanges into cast in place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch. Align pattern on a square grid in the predominant direction of travel. Install the same type of detectable warning tile throughout the project.

Install cast iron, yellow polymer soaked or black asphalt dip finish, with slip resistant surface, with handle or flange on bottom, and with truncated dome pattern; or approved equal.

Detectable warnings shall be manufactured and installed according to the Americans with Disabilities Act Accessibility Guidelines.

## SECTION 609

## CURBING

609-1.01 DESCRIPTION. Construct curb, gutter, or combination curb and gutter. The types of curbing are designated as follows:

- Type 1: Cast-in-place concrete curb

Type 2: Precast concrete curb

Type 3: Asphalt curb

609-2.01 MATERIALS. Use materials that conform to the following:

Concrete, Class A	Section 501*

Bed Course Material 	Subsection 703-2.03

Joint Filler	Subsection 705-2.01

Joint Sealer	Subsection 705-2.02

Joint Mortar	Subsection 705-2.04

Precast Concrete Curb	Subsection 712-2.04

* Except that in Subsection 501-3.02.3, delete a., b., and c.

Asphalt material for curbing must conform to the following requirements:

Asphalt Cement, PG 52-28	Subsection 702-2.01

Aggregate, Type II or III	Subsection 703-2.04

Mix design Requirements (ATM 417):

Marshall Stability, lb., min.	1000

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

- CONSTRUCTION REQUIREMENTS

609-3.01 GENERAL. Excavate to the required depth. Compact the base upon which curbs, gutters, and ramps are to be set to a firm, even surface according to Subsection 203-3.04.

Make expansion joints in concrete units that comply with the dimensions and spacing shown on the Plans. Fill expansion joints with the type of preformed expansion joint filler specified.

Make repairs to concrete units by removing and replacing the entire unit between scoring lines or joints. Clean all discolored concrete.

The Engineer will test the finished surface with a 10-foot straightedge. Variations of more than 1/4 inch from the edge of the straightedge to the top or face of the curb or the surface of gutters and ramps, except at grade changes or curves, are unacceptable.

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Use full-depth forms made of wood or metal that are straight, free from warp, and constructed so that they will not interfere with the inspection of grade or alignment. Brace and secure forms to prevent deflection from alignment or grade during concrete placement. Coat forms with an approved form-release agent.

- Thoroughly moisten the foundation immediately before placing the concrete.

Compact concrete in the forms by vibration or other acceptable methods. Leave forms in place until the concrete sets sufficiently so that the forms can be removed without damaging the concrete.

Finish the surface under Subsection 501-3.09.4. Immediately upon removing the forms, rub the exposed face to a uniform surface. Do not plaster the surface.

Make weakened plane contraction joints, spaced at 13 feet maximum intervals. Form each joint as a minimum 1/8 inch wide by 1/2 inch deep slot, continuous across the top and down the sides of the section. Make this slot either by sawing or scoring with a tool that will leave the corners rounded.

- If approved, construct the curb using a curb forming or slip-form machine.

Cure concrete under Subsection 501-3.10 for at least 72 hours. During the curing period, exclude all pedestrian and vehicular traffic. Exclude vehicular traffic for additional time as directed.

After the concrete sets sufficiently, refill the spaces in front and back of the curb to the required elevation with the specified material and thoroughly compact it.

609-3.03 PRECAST CONCRETE CURB. Set the curb so that the front, top line conforms to the line and grade required.

- Lay curb with joints 3/8 inch to 1 inch wide. Fill the joints with joint mortar.

After the mortar has set, backfill any remaining excavated areas with the specified material and thoroughly compact it.

609-3.04 ASPHALT CURB. When the curb is to be constructed on a cured or aged Portland cement concrete base, asphalt pavement, or asphalt treated base, thoroughly sweep and clean the bed using compressed air. Thoroughly dry the surface and, immediately before placing the asphalt mixture, place a tack coat of asphalt material of the approved type and grade onto the surface.

Construct asphalt curb using an approved, self-propelled automatic curb machine or a paver with curbing attachments that is heavy enough to compact the curb without riding above the foundation. For short sections or sections with short radii, use other approved means.

- Make the curb uniform in texture, shape, and density.

- If painting or sealing is required, curb must be clean, dry, and at ambient temperature.

609-3.05 BACKING CURB. Construct backing curb at curb ramp locations, according to the details and the locations shown on the Plans.

609-3.06 BUMPER CURBS. Concrete Parking Bumper shall conform to Subsection 609-3.03, Precast Concrete Curb, and the Plans.

## SECTION 610

## DITCH LINING

610-1.01 DESCRIPTION. Construct ditch lining at the locations on the Plans or as staked.

610-2.01 MATERIALS. Use stones that are sound and durable, are no larger than 8 inches in greatest dimension, and not more than 50% by weight passing a 3-inch sieve as determined by WAQTC FOP for AASHTO T 27/T 11.

610-3.01 CONSTRUCTION REQUIREMENTS. Excavate to the dimensions shown on the Plans. Place and spread ditch lining materials so that the finished face is reasonably uniform and conforms with the lines and slope shown on the Plans or as directed.

## SECTION 611

## RIPRAP

611-1.01 DESCRIPTION. Construct riprap bank and slope protection.

611-2.01 MATERIALS. Evenly graded stones that are hard, angular, and have no more than 50% wear at 500 revolutions as determined by AASHTO T 96. Apparent specific gravity will be determined by WAQTC FOP for AASHTO T85.  Use stones with breadth and thickness at least 1/4 of its length. Do not use rounded boulders or cobbles on slopes steeper than 2:1.

Meet the following gradation for the class specified. Percents are by total weight, weights are for each stone:

1.	Class I 	0-50% weighing up to 25 pounds

0-10% weighing more than 50 pounds

2.	Class II 	50-100% weighing 200 pounds or more

0-15% weighing up to 25 pounds

0-10% weighing more than 400 pounds

3.	Class III 	50-100% weighing 700 pounds or more

0-15% weighing up to 25 pounds

0-10% weighing more than 1400 pounds

4.	Class IV 	50-100% weighing 2000 pounds or more

0-15% weighing up to 400 pounds

0-10% weighing more than 5400 pounds

611-3.01 CONSTRUCTION REQUIREMENTS. Provide a level, compact area large enough to dump and sort typical loads of riprap at approved location(s). Dump the loads specified in this area and assist the Engineer as needed to sort and measure the stones in the load to determine if the riprap is within specifications. Provide the equipment needed to assist in this sorting.

Excavate a footing trench along the toe of the slope as shown on the Plans.

Place stones to the thickness, height, and length shown on the Plans, or as staked, in a well-graded mass with a minimum of voids. Fill in unacceptable voids with smaller stones. Place riprap to its full course thickness in one operation. Avoid displacing the underlying material. Do not place riprap in layers or use methods likely to cause segregation.

Manipulate the rock sufficiently using a backhoe, rock tongs, or other suitable equipment to secure a reasonably regular surface and stability.

## SECTION 614

## CONCRETE BARRIER

614-1.01 DESCRIPTION. Furnish and install concrete barrier.

614-2.01 MATERIALS. Use materials that conform to the following:

Concrete, Class A	Subsection 501-3.01

Reinforcing Steel and Wire Rope	Subsection 709-2.01

Reflective Sheeting Material	AASHTO M 268, Type III, IV, or V

Reflector Assemblies	Side-mounted or top-mounted as shown in the Plans.

614-3.01 CONSTRUCTION REQUIREMENTS. Use precast or cast-in-place concrete barrier meeting the lines, dimensions, and requirements shown on the Plans.

- Give all exposed surfaces a smooth finish.

Where the concrete barrier is not placed on pavement, shape, compact, and finish the supporting material to the lines and grades shown on the Plans or as directed.

Attach reflector assemblies to concrete barriers according to the manufacturer’s recommendations at 50-foot intervals on the side(s) and top as shown in the Plans. Reflector assemblies are required on both sides of median barriers.

## SECTION 615

## STANDARD SIGNS

615-1.01 DESCRIPTION. Furnish and install standard signs and delineators. Remove and relocate or remove and dispose of existing signs and markers, as specified.

615-2.01 MATERIALS. Use materials that conform to the following Subsections:

Sheet Aluminum 	730-2.01

High Density Overlaid Plywood	730-2.02

Reflective Sheeting 	730-2.03

Sign Posts	730-2.04

Delineator Posts	730-2.05

Acrylic Prismatic Reflectors	730-2.06

- Shop Drawings. Submit shop drawings, for all signs that must meet the ASDS letter width and spacing charts, for approval before fabrication. Submit 4 sets of collated shop drawings prepared according to Subsection 105-1.02. Show the following on each sign drawing:

- Dimensions of all horizontal and vertical characters and spaces

- Overall dimensions

- Sign material and sheeting material type

- Panel thickness

- Legend and letter series

- Whether the sign will be framed

- Sign Fabrication. Use Type IV reflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for all signs except the following:

- Orange Background Signs:

Use Type IX fluorescent orange reflective sheeting. For temporary installations place reflective sheeting on sheet aluminum, plastic, or plywood panels.

b. 	Railroad Crossbucks and Vertical Crossbuck Supports: Use white Type VIII or Type IX reflective sheeting for background of sign and all strips.

- Non-Illuminated Overhead Signs with White Legends on Green Backgrounds: Use Type IX reflective sheeting for legends and background. Create the legend in one of the following ways:

  - Cut border and legend from white Type IX reflective sheeting and adhere them to a green Type IX background, or

  - Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

- Fluorescent Yellow-Green School Area Signs: Use Type VIII or Type IX reflective sheeting for background.

Reflective Sheeting Warranty. Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured in accordance with ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor	YF: 20%

Minimum Total Luminance Factor	YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness. If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.

- Use a manufacturer-recommended clear coat on all screened signs.

- Use sign layouts (including characters, symbols, corner radii, and borders) that conform to the ASDS.

Frame all rectangular signs over 53 inches (measured along the horizontal axis) and all diamond shape signs 60 x 60 inches and larger. Construct the frames of aluminum as indicated on the Plans.

- Sign Posts and Bases. Use sign posts and bases of the types specified. The structural aspects of design and materials for sign supports must comply with the AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals. Do not splice sign posts.

Use Class A concrete for steel-reinforced slip base and breakaway base foundations meeting the requirements of Section 501. Concrete for other sign foundations may be any commercially available concrete with psi greater than 2000 psi.

- Delineators. Use delineator assemblies that conform to the requirements shown on the Plans. Fabricate flexible delineators using Type III, IV, or V Reflective Sheeting.

615-3.01 CONSTRUCTION REQUIREMENTS.

- Place wooden posts in excavated holes to the depth shown on the Standard Drawings.

- Backfill the space around the posts in the holes to finish ground with selected earth or sand, free of rocks or deleterious material. Place backfill in layers approximately 6 to 12 inches thick and thoroughly compact it.

- Dispose of surplus excavated material neatly along the adjacent roadway as directed.

- Install flexible delineator posts according to the manufacturer's recommendations.

- Attach sign panels to posts, electroliers, traffic signal standards, bridge rails, piers, and abutments using the types and sizes of fastening hardware shown on the Plans.

- If using existing signs and mileposts that are removed and relocated, ensure they conform to the details shown on the Plans or as directed.

- Notify the Engineer 5 working days prior to beginning sign salvage activities. The Engineer will physically identify those signs to be salvaged. Protect all items from damage during salvaging and delivery. For each sign so designated, disconnect sign post from panel and group the panels together. Group posts together with their hardware. Deliver sign panels, posts and hardware to the State Maintenance Yard on Tudor Road near Boniface Parkway in Anchorage, Alaska. Do not deliver salvaged materials until they have been inspected and approved by the Engineer. Replace any items damaged by you at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise). If they are abandoned in place, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to a depth of not less than 12 inches below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation will be considered as one unit.

- All materials and finished signs are subject to inspection and acceptance in place.

- Surfaces exposed to weathering must be free of defects in the coating that impair serviceability or detract from general appearance or color match.

- Finished signs must be clean and have no chatter marks, burrs, sharp edges, loose rivets, delaminated reflective sheeting, or aluminum marks. Do not make repairs to the face sheet.

- Install the various breakaway assemblies according to the manufacturer’s written instructions.

- Secure the anchors in templates and install them according to the manufacturer’s written instructions.

- Finish the foundation according to these tolerances:

- Do not use more than two shims per coupling.

- Do not use more than three shims to plumb each post.

- Remove and replace all foundations requiring more than three shims to plumb a post without extra compensation.

- Construct the top of any foundation located on a slope so that the finished slope passes through the top center of the foundation. Grade the area 24 inches up and down slope of the foundation edge so that no portion of the foundation projects above the surrounding slope and water will drain away from the foundation.

- Attach a label to the back of all standard signs in the lower right corner. Make the label at least 15 square inches and show the year the sign was purchased from the manufacturer. Show the last two digits of the year in clear and bold numbers. Make the label from Type I or brighter reflective sheeting. Use background and legend colors meeting Table 615-1.

Table 615-1

DECAL COLORS

| YEAR | BACKGROUND COLOR | LEGEND COLOR |
| --- | --- | --- |
| XXX1 | Yellow | Black |
| XXX2 | Red | White |
| XXX3 | Blue | White |
| XXX4 | Green | White |
| XXX5 | Brown | White |
| XXX6 | Orange | Black |
| XXX7 | Black | White |
| XXX8 | White | Black |
| XXX9 | Purple | White |
| XXX0 | Strong Yellow-Green | Black |

Central values and tolerance limits for each color, as referenced in the MUTCD, are available from the Federal Highway Administration, (HHS-30), 400 7th St. SW, Washington, D.C. 20590

615-3.02 SIGN PLACEMENT AND INSTALLATION. The location and type of installation will be as shown on the Plans. Sign locations are approximate and subject to field adjustment by the Engineer.

Do not allow the top of the embedded steel tube to extend more than 2 inches above the surrounding ground and concrete foundation.

On all signs, install 2-inch diameter wind washers, colored to match the sign face, between the fastener head and the sign. Use rust-resistant washers fabricated from a material equal in strength to the sign blank.

- Mount signs on mast arms level.

Bring existing signs that are to remain, into conformance with Standard Drawing S-05. Keep existing signs in service until they are no longer needed.

## SECTION 616

## THAW PIPE AND THAW WIRES

616-1.01 DESCRIPTION. Furnish, fabricate, and install thaw pipes or electric thaw wire.

- MATERIALS

616-2.01 THAW PIPE. Use materials that conform to the following:

Pipe	ASTM A 53, galvanized per AASHTO M 111

Fittings	ASTM A 234 galvanized per AASHTO M 111

Pipe Hangers	ASTM A 47, galvanized per AASHTO M 111

Braces for Standpipe	ASTM A 36, galvanized per AASHTO M 111

Bolts and Nuts	ASTM A 307, galvanized per AASHTO M 232

616-2.02 THAW WIRE. Provide materials, devices, fittings, and hardware meeting NEMA standards and bearing the approval of a third party certification, meeting ANSI Z 34.1.

Deliver all warranties and guarantees provided by the manufacturer to the Engineer before acceptance of this work.

1.	Conduit and Fittings.

a.	Use conduit, couplings, elbows, and nipples that are rigid, hot-dip galvanized steel meeting ANSI C80.1. Install them as indicated on the applicable drawings. Use threaded type couplings, elbows, and nipples.

b.	Use fittings and miscellaneous conduit hardware that are vapor-proof, galvanized cast iron or steel meeting ANSI/NEMA FB-1 and are compatible with the rigid conduit furnished and installed. Use threaded type fittings.

2.	Heat Cable.

- Use heat cable that meets the following standards:

- Parallel-circuit, 120 or 240 VAC, 16 AWG minimum copper bus wire, with self-limiting conductive core

- Modified polyolefin inner jacket, tinned copper or nickel-clad metallic braid, and fluoropolymer overjacket

- Rated in conduit at 8 W/ft. at 50 F

- UL Listed or FM approved specifically as a culvert deicing system in conduit

- Use connection components that are rated at NEMA 4X. Use power connections and seals specifically designed for use with the particular type and size of heat cable.

3.	Controls.

a.	Use a thermostat that is heavy duty, single stage, line voltage type. Operating temperature range: 25 to +125 F. Provide with NEMA 1 enclosure and capillary bulb for remote sensing.

b.	Use a contactor that is electrically held, 30 amp rated, lighting type, with NEMA 1 enclosure.

c.	Use a switch that is heavy duty hand-off-auto type with a gloved hand selector switch knob and NEMA 1 enclosure.

4.	Conductors. Use copper conductors with insulation rated for 300 volt minimum where the impressed voltage is 100 volts or less and 600 volt where the impressed voltage is between 100 and 600 volts.

a.	Service and Feeder Cables. Use No. 8 AWG, or larger, with type USE, THWN, THHN, or XHHW insulation.

b.	Underground Wire. Use No. 6 AWG with type XHHW or USE insulation where buried in conduit.

c.	Branch Circuit Wire. Use No. 12 AWG with type USE or XHHW insulation.

d.	Control Wire. Use No. 16 AWG with stranded conductor with type SIS insulation within control panels.

e.	Splices for Copper Conductors. Use solderless, preinsulated, compression set type only with heat-shrink tubing jacket. When making splices between power leads and heat cable cold leads, use splicing kits designed specifically for that purpose.

f.	Terminations. Use compression set or bolted type.

5.	Device, Junction, and Pull Boxes.

a.	Boxes Installed Above Grade. Use boxes that are hot dipped galvanized cast iron or corrosion resistant alloy complete with conduit hubs. Use boxes designed for damp or wet locations.

b.	Boxes Installed Below Grade (exposed to earth). Use concrete boxes as required or shown in the drawings. Provide covers constructed of ribbed cast metal alloy.

c.	Cast Thermoplastic or Fiberglass Boxes. Use where indicated in the drawings.

6.	Receptacles, Remote Power. Use remote power receptacles that are 2-pole, 3-wire grounding, male, 30 amp, 120 or 240 VAC, NEMA L6-30.

7.	Circuit Breakers.

a.	Provide 1- or 2-pole circuit breakers as scheduled in the drawings. Multiple breakers must operate all poles simultaneously. Use circuit breakers that operate manually for normal ON-OFF switching and automatically for overload and short-circuit conditions. Ensure that the operating mechanism will not prevent trip action when held in the ON position. Provide 10,000-ampere symmetrical interrupting capacity minimum. Provide bolt-in type with a molded case.

b.	Use Ground Fault Interrupter (GFI) circuit breakers that sense ground fault current, that trip at 30±1 milliamperes within 2 cycles, and that have the following:

- Internal circuitry to prevent nuisance tripping caused by voltage spikes, radio frequency interference, and electromagnetic interference.

- A 'TEST' button that provides approximately 30 milliamperes of simulated ground fault current to verify the operation of the sensing and tripping devices. The button must reset the trip unit within the circuit breaker.

- Type b auxiliary contacts to close when the circuit breaker is tripped or shutoff.

8.	Grounding.

a.	Electrodes. Use electrodes that are copper-clad steel rods with a minimum diameter of 5/8 inch Increase diameter as required to drive to the necessary depth without being damaged.

b.	Splices and Connections. Use an exothermic weld for all connections and joints in inaccessible locations. Use standard clamps and connectors in accessible locations.

9.	Terminal Posts. Use terminal posts that are 6 X 8-inch treated wood posts 8 feet long.

10.	Branch Circuit Panelboard. Use panelboards that meet the following:

- Sized and rated according to the panel schedules in the drawings

- Have multiple lugs (as required), a neutral terminal bar, and a ground terminal bar if ground conductors are terminated in the panelboard

- Use panelboards that are braced for 10,000 symmetrical RMS amperes

- With copper or aluminum bus bars

- CONSTRUCTION REQUIREMENTS

616-3.01 THAW PIPE.

1.	Pipe Hangers. Drill or field punch the bolt holes and then ream them. Ensure that the diameter of the hole does not exceed the diameter of the bolt by more than 1/8 inch. Draw the bolt heads and nuts tightly against the pipe.

2.	Pipe Jointing. Remove all scale from the pipe. After cutting, ream all pipe. Assemble all pipe and fittings using an application of pipe compound.

3.	Installation. Prevent dirt or other foreign matter from entering the pipe. After the thaw pipe is fully assembled and installed, flush it thoroughly with water.

- Repair damage to galvanized coatings per AASHTO M 36.

616-3.02 THAW WIRE. Meet all applicable requirements and recommendations of the NEC and the NESC.

- Furnish the Engineer with circuit and wiring diagrams.

When required on the Plans, install a post and meter combination for each individual thaw wire or a single post and meter combination for any group of thaw wires as specified and paid for under Section 661.

1.	Conduit and Fittings.

a.	Use galvanized rigid steel (GRS) conduit for direct burial at depths required by NEC Articles 300 and 710, unless noted otherwise. Repair damage to galvanized coatings per AASHTO M 36.

b.	Provide bituminous asphalt coating for all ferrous conduit installed directly in earth. Apply 2 coats after conduit is completely assembled. Use conduit with factory-applied protective coating in lieu of asphalt if suitable touch-up materials are used to seal couplings and repair injuries to the factory-applied coat.

c.	Cut and ream all conduit squarely at the ends. Make fittings tight.

d.	Route concealed conduit in a direct path with a minimum number of bends. Use bends of long radii where possible.

e.	Keep all bends free from dents or flattening.

f.	Install conduit mechanically and electrically continuous from termination to termination. Connect securely to cabinets, junction boxes, and device boxes using a locknut on the outside and a grounding bushing on the inside. Bushings and locknuts are not required where conduits are screwed into threaded connections.

g.	Before the installation of conductors, use caps or corks to keep foreign material out of open conduits.

2.	Heat Cable. Install per manufacturer’s instructions and as indicated on the electrical plans. Install in 1-1/2 inch GRS conduit as indicated on the electrical plans. Do not splice heat cable.

3.	Controls. Install the controls in the load center along with the panelboard as indicated on the electrical plans. Refer to the detail drawings.

4.	Conductors.

a.	Install all conductors in conduit.

b.	Clean all conduit before installing conductors.

c.	Install conductors continuously from box to box. Splice only at device or junction boxes.

d.	Circuit all feeder and branch circuits as shown in the drawings.

e.	Install all conductors in a single raceway at one time so that conductors do not cross one another while being pulled into place. Leave sufficient conductor length at all fittings and boxes.

f.	Stay within the pulling tensions specified by the manufacturer or as noted elsewhere in this division.

g.	Maintain bending radii in excess of those allowed by the manufacturer.

h.	Use lubricants according to UL, the conductor, and raceway manufacturers’ requirements.

i.	Neatly bundle and form conductors to fan into terminals at regular intervals inside panels.

j.	Coordinate conductor insulation temperature rating and ampacity rating with the temperature and ampacity rating of the circuit protection devices.

5.	Color Coding.

a.	Color all conductors #6 AWG and smaller continuously. Conductors larger than #6 may be either continuously colored or marked at each end and at every accessible point with appropriately colored paint, tape, or adhesive labels.

b.	Mark or color grounding conductors according to the NEC.

c.	Mark or color grounded conductors according to paragraph d. and according to the NEC.

d.	Mark or color ungrounded conductors according to the following convention:

| Nominal Voltage/Phase | Grounded | Ungrounded |
| --- | --- | --- |
| 120 volt, single phase, 2 wire | White | Black |
| 120/240 volt, single phase, 3 wire | White | Black |
|  |  | Red |

6.	Device, Junction, and Pull Boxes.

a.	Anchor device boxes to structural members so there is no apparent movement when the device is operated.

b.	Install junction and pull boxes in permanently accessible locations only. Size boxes according to NEC, Article 370.

c.	Mount all boxes square and plumb.

7.	Grounding.

a.	General. Create an equipotential ground plane for the installation as shown on the drawing and as required at the service meter/disconnect cabinet. Connect the following items to the service entrance ground bar:

(1)	The grounded neutral conductor for the utility service.

(2)	Ground electrode(s).

(3)	All non-current-carrying electrical equipment, conduit, and enclosures.

(4)	Metal culvert and/or end sections.

(5)	Heat cable metal sheath.

b.	Resistance. Ensure that the resistance between the service entrance ground electrode and earth ground, as measured using a multiple ground rod method and a Biddle 250220-1 Megger Null Balance Earth Tester or a Biddle 250260 Megger Direct Reading Earth Tester or approved equal, is as close to zero as possible with the design shown in the drawings. Give the resistance measurement to the Engineer in writing. Include the environmental conditions during testing.

c.	Conductors. Size conductors according to the drawings or, if not shown on drawings, as required by Tables 250-94 and 250-95 of the NEC. Protect conductors from physical damage.

d.	Electrodes. Drive ground rods at least 8 feet deep.

8.	Controls. Install the controls in the load center along with the panelboard as indicated on the electrical plans. Refer to the detail drawings.

9.	Branch Circuit Panelboard.

a.	Mounting. Mount panelboard interiors inside load center cabinet after the enclosure has been installed as shown on the Plans and as described under Section 661.

b.	Circuit Breakers. Install circuit breakers in the order specified in the drawing panelboard schedules. Type the circuit directory with circuit descriptions as they are shown in the drawing panelboard schedules. Make the directory configuration identical to the circuit breaker configuration.

## SECTION 618

## SEEDING

618-1.01 DESCRIPTION.  Establish a perennial stand of grass or other specified living vegetative cover, by clearing, applying topsoil, soil stabilization material(s), and seeding the area(s) shown in the Plans, including new and disturbed area(s), and other area(s) identified by the Engineer. Track the soil and apply seed, mulch, fertilizer, and water. Provide a living ground cover on slopes as soon as possible.  Maintain the cover for the term of the Contract.

618-2.01 MATERIALS. Use materials that conform to the Special Provisions and the following:

Seed 	Section 724

Fertilizer (20-20-10)	Section 725

Water	Subsection 712-2.01

Soil Stabilization Material	Section 727 (Stabilization Material)

Topsoil	Section 726

- CONSTRUCTION REQUIREMENTS

618-3.01 SURFACE PREPARATION. Clear all areas to be seeded of stones 4 inches in diameter and larger and of all weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the seeding operation, growth of grass, or subsequent maintenance of the grass-covered areas.

- Make areas to be seeded reasonably free of ruts, holes, and humps.

- When specified, apply topsoil according to Section 620.

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope. Use one or more of the following grooving methods prior to the application of seed:

- Manual raking with landscaping rakes;

- Mechanical track walking with track equipment; or

- Mechanical raking with a scarifying slope board. Form one inch wide grooves spaced no more than six inches apart.

You may round the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance, but you may not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS. Seed and fertilize during the local growing season.

Do not seed during windy conditions or when climatic conditions or ground conditions would hinder placement or proper growth.

Seed disturbed areas that require seeding within fourteen days of the permanent cessation of ground-disturbing activities in that area.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.

618-3.03 APPLICATION. Apply seed mix, fertilizer, and mulch (if required) at the rate specified in the Special Provisions. If no seed mix, seed mix application rate, or fertilizer rate are specified in the special provisions, use the recommendations of the Alaska Department of Natural Resources (ADNR) and the Revegetation Manual for Alaska.

- Do not seed areas of bedrock, plant beds, and areas indicated on the plans as “no seeding”.

- Water and fertilizer required for application are subsidiary to the Seeding bid item.

Apply seed and stabilization material in one application when using the hydraulic method. Apply fertilizer with the hydraulic method. Include the fertilizer with the seed and stabilization material or apply separately.

- TABLE 618-1

APPLICATION RATES

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 0.50 lbs. 0.40 lbs. 0.10 lbs. Total = 1.00 lbs. |
| Soil Stabilizera. |  |  |
| Slope ≤ 3:1 | Mulch | 46 lbs. |
| Slope >3:1 | Mulch with tackifier | 45-58 lbs. |
| Fertilizer | 20-20-10 | 12 lbs. |

a Soil Stabilizer/Stabilization Material. Refer to Section 619 and 727 for additional soil stabilization and soil stabilization materials.

- Do not remove required tags from seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable. If this substitution is made, apply at the same application rate.

Use any of the following methods:

- 1.	Hydraulic Method.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other components as required by the Special Provisions.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

- 2.	Dry Methods.

a.	Use mechanical spreaders, seed drills, landscape seeders, aircraft, cultipacker seeders, fertilizer spreaders, or other approved mechanical spreading equipment when seed and fertilizer are to be applied in dry form.

b.	Spread fertilizer separately at the specified rate.

618-3.04 MAINTENANCE AND WATERING. Protect seeded areas against traffic by approved warning signs or barricades. Repair surfaces gullied or otherwise damaged following seeding. Maintain seeded areas in a satisfactory condition until final acceptance of work.

Maintenance includes but is not limited to:

1.	Protecting seeded areas against traffic by approved warning signs or barricades and against erosion.

2.	Repairing surfaces gullied or otherwise damaged following seeding.  Fill erosion gullies 4 inches deep and greater filling the gully to surrounding grade including the portions less than 4 inches deep. Apply and prepare the stabilization material for seeding.  Seed repaired area(s). Refer to Subsections 618-3.01 & 3.03.

3.	Reseeding areas not showing evidence of satisfactory growth within 3 weeks of seeding and after repairs are complete. Reseed bare patches of soil more than 10 square feet in area. Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.

4.	Watering seeded areas for growth of vegetative cover. If in the opinion of the Engineer, too little or too much water is being applied, adjust the amount of water as directed.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth. You are responsible for retracking, reseeding, refertilizing and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE. The Engineer will perform a visual inspection of seeding to determine final stabilization. During the visual inspection each station and each side of the road will be considered a separate area. The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

- Reseed areas that are not accepted.

618-3.06 PERIOD OF ESTABLISHMENT. For each area accepted, the establishment period extends one complete growing season following the date of acceptance.  Employ all possible means to preserve/maintain the new vegetative mat in a healthy and vigorous condition to ensure successful establishment. Maintain the vegetative mat, according to Subsection 618-3.04, to not less than the requirements for acceptance, Subsection 618-3.05.

## SECTION 619

## SOIL STABILIZATION

619-1.01 DESCRIPTION. Furnish, install, and maintain materials to stabilize the soil. Control erosion, sediment, and pollution.

619-1.02 RELATED SECTIONS, REFERENCE ORGANIZATIONS, AND STANDARD DOCUMENTS.

1.	Seeding						Section 618

Topsoil	Section 620

Planting Trees and Shrubs	Section 621

Silt Fence	Section 633

Erosion, Sediment, and Pollution Control	Section 641

Soil Stabilization Material	Section 727

2.	United States Composting Council (USCC):

  Testing Methods for the Examination of Compost and Composting (TMECC)

  Seal of Testing Assurance Program (STA) documents

3.	Erosion Control Technology Council (ECTC)

  Hydraulic Erosion Control Products (HECPs) Specification Chart

Table 1, Performance Chart for Standard HECPs

  Rolled Erosion Control Products (RECPs) Specification Chart

Table 1, Rolled Erosion Control - Temporary

Table 2, Rolled Erosion Control - Permanent

4.	National Transportation Product Evaluation Program (NTPEP)

  Testing and Evaluation of Products Materials and/or Devices

619-1.03 SUBMITTALS. Submit stabilization and erosion, sediment and pollution control performance testing results with certifications for each material, Section 619-2.01 Materials.

1)	Test compost, all applications, no more than 30 days before installation.

2)	At a minimum, certificate will include the name of the manufacturer, product name, style number or similar, chemical composition of the material, the fibers, netting, yarn and similar and the weed free status of the material.

3)	Organic materials shall be accompanied with all applicable health certificates and permits.

4)	Furnish a Material Safety Data Sheet (MSDS) that demonstrates the product is not harmful to plants, animals, and aquatic life.

619-2.01 MATERIALS. Select stabilization materials, individually or a combination of, matched to the project applications/conditions (sheet flow, concentrated flow, slope, length of slope, access, etc.) providing performance and functional longevity meeting the most restrictive requirements of the Construction General Permit (CGP), the approved Stormwater Pollution Prevention Plan (SWPPP) and Section 641 Erosion, Sediment and Pollution Control.

1)	Mulch						Subsection 727-2.01

  Dry Erosion Control, Stabilization Products

  Hydraulic Erosion Control Products (HECPs)

- 2)	Matting						Subsection 727-2.02

  Rolled Erosion Control Products (RECPs)

- 3)	Sediment Retention Fiber Rolls (SRFRs)		Subsection 727-2.03

  Filter Socks

  Compost Socks

  Coir Logs

4)	Compost						Subsection 727-2.04

5)	Tackifier						Subsection 727-2.05

6)	Soil Binders (Polyacrylamide (PAM))		Subsection 727-2.06

7)	Geotextile-Encased Check Dams and 		Subsection 727-2.07

Sediment Barriers

8)	Sandbag						Subsection 727-2.08

9)	Manufactured Inlet Protection System		Subsection 727-2.09

10)	Clear Plastic Covering				Subsection 727-2.10

11)	Staples						Subsection 727-2.11

12)	Other stabilization materials submitted to and approved by the Engineer.

Include on the packaging the manufacturer's name, the content, the air dry-weight and the guaranteed chemical analysis of the contents.  Ship and deliver to the site in the original, unopened containers.

- CONSTRUCTION REQUIREMENTS

619-3.01 GENERAL. Stabilization may include individual or a combination of materials, including but not limited to temporary seeding, mulch, tackifier, staples, matting, stabilizing emulsions, soil binders, dustless sweeping, dust palliatives, and others.

- 1.	Material Storage and Protection. Store materials elevated off the ground and covered protecting them from construction and or damage from the environment including but not limited to:

  Precipitation

  Extended ultraviolet radiant including sunlight

  Chemicals that are strong acids or other

  Flames and welding sparks

  Excess temperatures

  Other environmental conditions that may damage the materials

- 2.	Fabrication.

a.	Sandbags. Sand bags shall measure 15 inches by 30 inches. Place approximately 1.0 cubic foot of select Material, Type B, in each sandbag sack. Close the open end of the sandbag as recommended by the fabric manufacturer.

619-3.02 SURFACE PREPARATION. Clear all areas to be stabilized of stones 4 inches in diameter and larger and of weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the stabilization operation, growth of cover (where vegetative cover is part of the stabilization operation) or subsequent maintenance of the vegetative-covered area(s).

Smooth the surface of the area(s) to be stabilized; make the areas reasonably free of ruts, holes, and humps; trackwalk if required by the manufacturer; apply the stabilization material to each area.

If specified, apply topsoil to the area to be stabilized before application of the stabilizing material. Section 618 and 620.

619-3.03 APPLICATION. Apply stabilization material, including rate of application, according to the specifications. If not specified, apply according to the manufacturer's requirements. Where manufacturer requirements conflict with the specification, except where the Engineer directs otherwise, apply the material according to the requirements of the manufacturer.

If seeding is specified, except where seed is included in the stabilization material, complete the application of stabilization materials within 24 hours after seed is placed.

- Do not use vehicles or equipment which cause rutting or displacement of the subgrade or topsoil.

1.	Temporary Seeding. Annual Ryegrass per Subsection 724-2.02, Table 724-1. Apply at a rate of 1/2 lb/1000 SF, minimum, on level ground to a maximum of 1-1/2 lb/1000 SF, maximum, on sloping ground and highly erodible soils. Prepare surface and place seed as noted under Subsection 619-3.02 Surface Preparation and Section 618 Seeding. Confirm application of temporary seeding with the Engineer.

2.	Tacking Agents - Tackifiers. Apply tacking agents according to the manufacturer's installation instructions matched to the application providing functional longevity, erosion control effectiveness, and vegetative establishment.

3.	Soil Binders. Apply soil binders according to the manufacturer's installation instructions.

a.	Using Polyacrylamide (PAM) and PAM with Short-Term Mulch:

Apply PAM on bare soils.

Apply PAM and PAM with short-term mulch only where sediment control is in place and complete.

- Do not apply PAM and PAM with short-term mulch on saturated ground during rainfall.

b.	Using Moderate-Term Mulch:

Apply moderate-term mulch according to manufacturer's installation instructions.  If the curing period to achieve maximum performance is greater than the time period before precipitation is predicted, or the soil is saturated, do not apply the moderate-term mulch except as approved by the Engineer.

c.	Using Long-Term Mulch:

Apply long-term mulch according to the manufactures installation instructions.

4.	Erosion Control Blankets (ECBs).  Select blankets, as specified by the manufacturer, to match the slope; and installed according to the manufacturer's instructions rolled out on well prepared soils to assure intimate contact and anchored with staples, stakes and or anchor trenches.  Temporary erosion control blankets with 60 percent or greater open area may be installed prior to seeding.  Place blankets with less than 60 percent open area immediately after the seeding operation.

Staple matting/ECBs as recommended by the manufacturer for the application.

5.	Compost Blankets. Construct compost blankets according to AASHTO R 52-10 and as specified. Use coarse compost and place over bare soil a blanket of 2 inch minimum thickness, except as otherwise specified. Apply material either by hand spreading and or pneumatically. Compost will have no free water visible or produce dust when handled. Place compost before seeding or mix seed with compost.

6.	Check Dams. Place check dams as soon as possible and practicable or when and where if directed by the Engineer. Place the check dams perpendicular to channels and construct of a height sufficient to maximize detention while keeping the water in the channel. Place and install check dams according to the Plans and anchor to maintain in effective position.

a.	Sandbag. Place the initial row in tight contact with the ditchline for the length of the dam. Place each following row centered across the joint between the bags of the lift/row below.

7.	Stabilized Construction Entrance. Temporary stabilized construction entrance shall be constructed according to the Plans, prior to beginning any clearing, grubbing, earthwork, or excavation.

When the stabilized entrance no longer prevents track out of sediment or debris, the Contractor shall either rehabilitate the existing entrance to original condition, or construct a new entrance.

When the Plans require a tire wash in conjunction with the stabilized entrance, the Contractor shall include details for the tire wash and the method for containing and treating the sediment-laden runoff as part of the SWPPP. All vehicles leaving the site shall stop and wash sediment from their tires.

8.	Sediment Control Barriers.  Sediment control barriers shall be installed according to the Plans or manufacturer's recommendations in the areas of clearing, grubbing, earthwork, or drainage prior to starting those activities.

a.	Sandbag. Place the initial row in tight contact with the surface perpendicular to the slope. Place each following row centered across the joint between the bags of the lift/row below.

b.	Sediment Retention Fiber Rolls.

c.	Silt Fence.

d.	Compost Berm.  Construct compost berms according to AASHTO R 51-10.  Use coarse compost.

9.	Turf Reinforcement Mats. According to manufacturers installation instructions.

619-3.04 MAINTENANCE. Maintain stabilized areas in a satisfactory condition for the term of the Contract, including warranty obligations.  Inspect as required by the CGP, approved SWPPP, and Section 641 Erosion, Sediment and Pollution Control and correct any deficiencies immediately. Remove and dispose of temporary measures, including trapped sediment and contaminants, off project at approved locations. Materials manufactured as degradable may be left in place when approved by the Engineer.

Maintenance includes but is not limited to:

1.	Protecting stabilized areas against traffic by approved warning signs or barricades.

2.	Repairing surfaces gullied or otherwise damaged following application of stabilization material(s).

Where seeding is included as a part of the soil stabilization:

3.	Reseeding, as required by Section 618 Seeding.  Reapply the stabilization materials correcting the problems of the initial application.

4.	Watering, where vegetative growth is part of the soil stabilization, according to Section 618 Seeding.

The Engineer will perform inspection of the stabilization as required in the CGP, Section 641, and the SWPPP. Make repairs as required by same and as directed.

## SECTION 620

## TOPSOIL

620-1.01 DESCRIPTION. Furnish and spread topsoil where shown on the Plans.

620-2.01 MATERIALS. Use materials that conform to the following:

Topsoil	Section 726

620-3.01 PLACING. Spread the topsoil evenly on the designated areas to the depth (after settlement) shown on the Plans. Do not place when the ground or topsoil is frozen, excessively wet, or in a condition detrimental to the work. Keep the roadway surfaces clean of topsoil during hauling and spreading operations.

620-3.02 MAINTENANCE AND REPAIR. Maintain the areas covered by topsoil until subsequent seeding or landscaping is accomplished. Complete any repairs or topsoil replacement, including damage or loss resulting from winter shutdown, without extra compensation.

## SECTION 621

## PLANTING TREES AND SHRUBS

621-1.01 DESCRIPTION. This work shall consist of furnishing, planting and maintaining seedlings, shrubs, and willow bundles as shown in the Plans. Seedlings shall consist of tree and shrub species shown in the Plans and shall be 18 to 24 inches in height above the ground at time of planting.

- MATERIALS

621-2.01 PLANT STOCK. Use plants that are true to type and name according to the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature. Label each bundle, or each plant if not bundled, with scientific name and size.

Use the variety and species specified in the Special Provisions. Use plants that are typical of the species or variety and that conform to ANSI-Z 60.1 of the American Nursery and Landscape Association of (ANLA) for type and grade. Use plants free from disease, injurious insects, mechanical wounds, broken branches, decay, or other defects.

1.	Nursery Stock.

a.	Use trees and shrubs furnished from a nursery that have been root pruned during their growing period in the nursery according to standard nursery practice to produce a fibrous compact root system suitable for the various species and sizes called for on the Plans. Use nursery stock that has been growing for at least 2 full growing seasons.

b.	Use container grown plants that have been growing for at least 1 year but no more than 2 years in the same container. Only ground cover plants may exhibit a “pot-bound” condition.

2.	Collected Stock. Follow ANLA Handbook collection procedures. Collect healthy plants growing under natural conditions in soils and in locations which lend themselves to proper collecting practices. Ensure that the root systems or balls for collected stock is at least 25% larger than those specified for nursery-grown material.

3.	Balled and Burlapped Plants.

a.	Meet the ball diameters and depths specified in the American Standard for Nursery Stock of the ANLA.

b.	Furnish plants with a firm ball of earth from the original and undisturbed soil in which the plant was growing. Wrap the ball with burlap or similar approved material and lace it tightly to hold the ball firm and intact. Plant material that arrives at the planting site with broken or loose balls or with manufactured earth, are unacceptable.

4.	Substitutions. No substitutions are permitted without written approval.

5.	Storage and Packing. Handle and pack all plant material according to good nursery practices as required by soil and climatic conditions. Plants that show signs of improper storage or handling are unacceptable.

6.	Inspection.

a.	Make all planting stock available for inspection in the nursery or collecting field before it is dug. At least 10 working days before digging operations, furnish complete and detailed information about the supply source for each item of plant materials.

b.	Final inspection and acceptance for size of ball or roots, color, absence of defects, and for other requirements will be made at the planting site before placing the plants in their permanent positions.

621-2.02 Fertilizer. Use a regular release, 8-32-16 (nitrogen-phosphoric acid-potassium) fertilizer in granular form with seedlings, shrubs, and Willow bundles. The fertilizer shall be mixed with soil at the manufacturer’s recommended application rate.

621-2.03 LIMESTONE. Use limestone that meets Subsection 712-2.03.

621-2.04 MULCH. For use as a ground cover in landscape beds as shown on Plans. It shall consist of shredded wood fibers with the characteristics of retaining moisture and forming a mat so as not to be disturbed by wind or rain. Mulch shall not contain individual components greater than 2 inches in length with a minimum of 75 percent of the total mulch component passing through a 1 inch screen. Mulch shall contain no growth or germinating inhibiting ingredients.  Locally harvested shredded wood fibers shall be aged for one-year minimum prior to installation. Commercially available shredded wood fiber landscape mulch may be used, provided any added color shall be a natural dark brown. “Green” or “Fresh” wood chips are not acceptable. It shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.

621-2.05 BACKFILL MIX. Topsoil used for backfill in planting beds shall consist of a natural friable surface soil without admixtures of undesirable refuse or foreign materials. It shall be free from roots, hard clay, noxious weeds, tall grasses, brush, sticks, stubble, or other liter, and shall be free draining and non-toxic. Local red loam or imported peat mix having nutritional and gradation requirements may be used. Topsoil backfill shall have 10-15 percent organic matter as determined by loss-on-ignition of oven dried samples according to ASTM 203, and shall meet the following:

| Sieve Designation | Percent Passing by Weight |
| --- | --- |
| 3/4 Inch | 100 |
| No. 4 | 95 – 100 |
| No. 16 | 30 – 55 |
| No. 200 | 25 – 55 |

621-2.06 STAKES. Use stakes that are strong and fit for the purpose intended.

621-2.07 TREE WOUND DRESSING. Use tree wound dressing that is antiseptic, waterproof, and contains no materials harmful to the living tissue of trees.

621-2.08 EDGING. Plastic edging shall be pure polyethylene with 3 1/2 to 4 percent carbon black concentrate added for ultraviolet stabilization, medium density with a melt factor under 2. Average wall thickness shall be 95/1000 to 105/1000 inch, height of 4 inches, with a 1 inch round top and 4 groove base. Install per manufacturer's specifications, straight, level and secure.

- CONSTRUCTION REQUIREMENTS

621-3.01 TEMPORARY STORAGE. Where temporary storage or heeling-in of plants is required, provide and prepare a suitable heeling-in ground or a well-ventilated and cool storage shed, located near the planting site, before shipping planting stock.

Heel-in or properly store all acceptable planting stock if not planted within 24 hours, as follows:

1.	Balled and Burlapped Plants. Temporarily store in a protected area with balls 6 inches apart. Fill voids with moist mulch up to and including the top of the ball.

2.	Bare-Rooted Plants. Puddle immediately, then heel-in by placing the plants, properly spread, in a trench and covering the roots with moist topsoil.

Protect bare root plants adequately at all times. Plants left out of the ground unprotected overnight, left with roots exposed to the sun, or improperly protected during transit, unloading, heeling-in, or during the planting operation, are unacceptable.

Protect the roots of plants stored in a shed at all times using moist straw or other approved material. Water as required.

621-3.02 ADVANCE PREPARATION AND CLEANUP. After clearing and grubbing of the area is complete, remove any stones, sticks, stumps, clods, and other debris which might interfere with growth or maintenance. Repair any subsequent damage from erosion or other causes.

- Prepare areas which will receive group plantings with generally curving outlines.

621-3.03 PLANTING. Perform all planting work using good horticultural practices.

1.	Plant Season.

a.	Locally Grown:  When locally grown seedlings and shrubs are furnished for the project, plant them between June 1 and September 15.

b.	Imported:  Handle plants shipped in from out-of-state according to the nursery recommendations.  Place plants imported from out-of-state between June 1 and August 15.

c.	Willow Bundles.  Plant Willow bundles between May 1 and June 15.

2.	Excavation.

a.	Keep topsoil separate from underlying layers and render it loose and friable. Remove any material detrimental to plant growth and waste it at approved locations.

b.	Make pits for trees at least 2-5 times the diameter of the root ball or the spread root system of bare-root trees. Make the depths of pits for trees at least 2 feet and as much deeper as may be necessary to provide a minimum depth of 9 inches below the bottom of the ball or spread root system of the tree when placed at the proper elevation.

c.	Construct planting pits for seedlings and shrubs and trenches for Willow bundles as shown on the Plans.

d.	Ensure that the dimensions of pits, pockets, or trenches for vines, ground covers, and similar types of plants will provide space for the spread root system. Keep the depth and width at least 6 inches below and around the root system.

3.	Pruning.

a.	Roots. Prune all damaged or broken main roots with a clean, oblique cut immediately above the point of damage.

b.	Branches. Use pruning techniques that conform to the best horticultural practices with due regard to natural or desired form and growth characteristics of the individual species. Preserve a single terminal leader when pruning. On all deciduous plants, remove 1/3 to 1/2 of the potential leaf-bearing surface. Treat all cut surfaces that are 3/4 inch or more in diameter with tree wound dressing.

4.	Transplanting. Relocate plant material, within the limits of the project, designated for transplanting to areas shown on the drawings or as specified. Dig this material with root systems or balls as specified for collected stock and replant it the same way as new stock.

5.	Placing Plants.

a.	Set plants plumb on lightly tamped backfill mix and at a level so that the root collar will bear the same relation to the planting site as it bore to the ground from which it was dug.

b.	Handle balled and burlapped plants by the earth ball and not by the plant itself. Place the plants in holes without removing the burlap.

c.	Fill the hole with water before placing the plant. Place the backfill gradually, allowing the soil to soak up the water.

6.	Backfilling. Work backfill mix around the roots and firmly tamp it as it is filled into the holes to eliminate air pockets. Avoid bruising or breaking the roots while tamping or firming the backfill mix about them. Hold upright plants plumb during the backfilling operation. When the backfilling is 2/3 completed, loosen the exposed burlap and lay it back from the ball or cut off excess. After thorough watering, complete the backfilling. During backfilling, remove stocks, sod, clods, or other material that tend to form air pockets. Except in areas for shrub beds, construct a shallow basin of backfill mix approximately 3 inches deep and as wide as the diameter of the hole around each plant. On steep slopes, pull enough soil to the lower side of the plants to form shallow basins to catch and hold water. After the backfilling is completed, water the plant basins thoroughly.  Backfill seedlings, shrubs, and willow bundles with topsoil mixed with fertilizer at the manufacturer’s recommended application rate.

7.	Wrapping. When specified, wrap the trunks of all deciduous shade and flowering trees with 4-inch-wide waterproof paper, overlapping 1-1/2 inches, between the lowest main branches to the ground line. Tie the wrapping in at least 5 places, including top, middle, and bottom. Complete these protective measures within 4 days after planting.

8.	Staking and Guying.

a.	Immediately after planting, brace all evergreen trees 4 to 6 feet high and all deciduous trees 6 feet and over in height and less than 1-1/2 inch in diameter. Use a single stake measuring at least 2 inches by 2 inches by 6 feet and place it 2 feet deep into the ground on the windward side to avoid injury to the root system. Connect the stake to the tree using approved binding straps.

b.	Immediately guy all deciduous trees 1-1/2 inches and over in diameter, and all evergreen trees 6 feet and over in height using 3 cables spaced approximately 120 degrees apart around the tree. Use cables each made of 2 No. 12 galvanized steel wires, free from bends and kinks, twisted into a strand. Fasten cables around the trunk immediately above a substantial limb wherever possible. Fasten cables around the trunk at a distance from the ground equal to 1/2 to 2/3 of the total height of the tree. Anchor cables to the ground at an equal distance away from the trunk. Protect the tree from damage caused by the cable using an approved method.

c.	Use other anchor stakes that are at least 2 inches x 2 inches x 2 feet. Drive the stakes at right angles to the guy wire. Ensure that the stakes do not extend more than 3 inches above the ground. Notch or drill the stakes to prevent cables from slipping.

621-3.04 PERIOD OF ESTABLISHMENT. Establishment periods extend for one complete growing season (May 1 to September 30) following acceptable planting. Employ all possible means to preserve the plants in a healthy and vigorous condition to ensure successful establishment. During this period, perform the necessary weeding, spraying (with approved insecticides or fungicides), cultivating, remulching, and tightening or replacing guy wires and stakes as may be required. Water all shade, evergreen, and flowering trees as frequently as necessary to keep the immediate root areas moist at all times.

Provide a reapplication of fertilizer to seedlings and shrubs by driving a 1-1/2 ounce fertilizer spike of the same chemical proportions as the initial application into the ground at the drip line of each plant. Perform the reapplication between May 15 and May 31.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance. After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with Subsection 105-1.16.

621-3.05 CLEANUP. Remove from planting sites any quantities of subsoil, rock, and other spoils resulting from excavation after planting. Dispose of them as directed. On slopes 3:1 and steeper, you may scatter or waste material other than rock and coarse debris. Leave all planting sites in an acceptable condition.

621-3.06 PLANT REPLACEMENTS. In the Spring, before June 30, the Engineer and the Contractor’s representative shall inventory seedlings and shrubs planted on the project to determine the number of dead or unhealthy plants. If the number of dead or unhealthy seedlings and shrubs is lower than 25 percent of the quantities originally planted, then no plant replacements shall be required.

If the number of dead or unhealthy seedlings and shrubs is higher than 25 percent of the quantities originally planted, replace a sufficient number of plants to increase the number of healthy seedlings and shrubs to 75 percent of the quantities originally planted.

Provide healthy replacement seedlings and shrubs of the same species and size as the original plantings. Perform replacement planting between July 1 and July 15, according to the original planting procedures. The Engineer will select which of the dead or unhealthy plants to be replaced.

The Contractor shall reset seedlings or shrubs to an upright position, or to the proper grade, and remove dead seedlings or shrubs.

621-3.07 MAINTENANCE. Protect the planted areas using signs, barricades, or other approved means. Keep the planted areas watered. Deep water the seedlings and shrubs immediately after planting. Deep watering shall provide water penetration throughout the entire root zone to the total depth of the planting pits with a minimum of runoff. Rain will not be considered a substitute for deep watering unless permitted by the Engineer.

Deep water seedlings and shrubs according to the following maintenance schedule:

1.	Deep water seedlings and shrubs at least twice a week during the first 45 days after planting.  If these 45 days extend past September 30, cease the twice weekly deep watering after that date and resume on May 1 of the following calendar year.  If the 45 days does not extend past September 30, additional deep watering in the planting year after the 45 days expire shall be as follows:

a.	Once a week in June and July.

b.	Once between August 10 and August 20.

c.	Once during the last week in September.

2.	Deep water seedlings and shrubs during the Period of Establishment as follows:

a.	Once a week during May, June, and July.

b.	Once between August 10 and August 20.

c.	Once during the last week in September.

3.	The Engineer may direct the Contractor to deep water seedlings and shrubs past September 30 or provide supplemental watering any time during the life of the project if weather conditions are excessively warm or dry.

4.	The Engineer may direct the Contractor to deep water conifer tree seedlings and shrubs before freeze-up in order to minimize over-wintering desiccation.

## SECTION 623

## BLOCK SODDING

623-1.01 DESCRIPTION. Establish a perennial stand of grass or other specified living vegetative cover, by sodding, in areas shown on the Plans. Maintain the cover for the term of the Contract.

623-2.01 MATERIALS.

Sod. Use living native plants and grasses that grow in the more fertile soils near the project. Preferred plants include willow, alder, fireweed, calamagrostis, bearberry, red top, and other natural species. Establish fertility by observing the quality and quantity of the plants and grasses in their natural location.

Collect sod out of sight of the roadway and within the right-of-way if possible. Obtain authority to remove sod from areas outside the right-of-way. Obtain approval of the sod in its original position before cutting.

Cut sod in blocks of at least 6 ft2. Obtain approval to use different dimensions. Include an intact root system with natural soil at least 4 inches thick.

- Fertilizer. Use a 28-8-4 mixture in 300-grain pellets, meeting the requirements of Section 725.

623-3.01 CONSTRUCTION REQUIREMENTS. Prepare the area to be sodded by removing oversize rocks, logs, wood, soil clods, paper, and other debris. Dispose of debris out of sight of the roadway. Smooth any rivulets eroded into the face of the slope, by tapering the edges into the depressions. Smooth the area enough to allow planting sod.

1.	Keep sod moist at all times. Water sod if necessary prior to cutting. Keep as much soil as possible in the natural state around the roots during digging, hauling and planting.

2.	Use approved mechanized methods wherever possible to obtain and place sod.

3.	Place sod on the designated slopes without excavating holes and within 6 inches of the locations specified on the Plans. Place each piece tightly against adjoining pieces. On slopes steeper than 3:1, peg sod pieces as directed.

4.	Fill and pack voids with suitable soil from the sod source. Tamp or roll sod firmly in place, to eliminate air pockets provide a smooth plane, level with the adjacent slope.

5.	Fertilize the sod using 2 pellets per sod block. Water sod within one hour of placing. Continue watering sod blocks until project completion.

## SECTION 625

## PIPE HAND RAIL

625-1.01 DESCRIPTION. Furnish and place pipe handrail with galvanized steel pipe members, concrete bases, and other required materials in conformance with the Plans.

625-2.01 MATERIALS. Use materials that conform to the following:

Concrete	Section 501 (Class W)

Pipe	ASTM A 53, Schedule 40, galvanized per AASHTO M 111

625-3.01 CONSTRUCTION REQUIREMENTS. Set posts plumb in concrete base. Weld galvanized steel pipe members at rail-to-post connections and intermediate rail connections, as shown on the Plans. Erect railing smoothly and continuously so that it is parallel to the sidewalk grade.

- Repair all welds and damaged galvanizing to conform to AASHTO M 36.

## SECTION 626

## SANITARY SEWER SYSTEM

626-1.01 DESCRIPTION. Construct or reconstruct sanitary sewers and appurtenances to conform to the Plans. This Section refers to conduit used for sanitary sewers as “sewer conduit.”

626-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

PVC Pipe 	Subsection 706-2.05

HDPE Pipe	Subsection 706-2.08

Ductile Iron Pipe	Subsection 707-2.05

626-3.01 CONSTRUCTION REQUIREMENTS. Complete the sanitary sewer system and make sure it operates properly at the time of acceptance of the work. Furnish and install all incidental parts not shown on the Plans or specified in this Section that are necessary to complete the sanitary sewer system.

Meet the applicable provisions of Sections 201, 204, and 603 for all clearing and grubbing, excavation, bedding, backfill, conduit, and appurtenances.

If sewer conduit is directly connected to or supported by rigid structures such as manholes, it must have a joint or flexible connection located 5 feet or less from the point of connection or support.

Lay sewer conduit accurately to the staked line and grade. Install all service connections as indicated on the Plans. Provide suitable fittings and adapters when connecting existing service sewers.

Clean all foreign matter from sewer conduit. Keep water out of trenches until joints are completed. Plug or cover open ends of conduit and fittings when work is not in progress to keep out foreign matter and rodents.

- Join pipe according to manufacturer’s recommendations, or as detailed on the Plans.

When sewer conduit is laid within a 10-foot horizontal radius of an existing or a new water main, and is above or 3 feet below the water main, use cast-iron pipe.

Remove trench sheeting and bracing above the elevation of the conduit. Do not pull, remove, or disturb sheeting below the conduit.

626-3.02 TESTING. With the Engineer present, test the sewer for grade, alignment, and leakage. Grade and alignment must conform to staking with no deviation allowed that would inhibit flow.

Test for infiltration if the normal groundwater table lies above the invert of the sewer conduit. Infiltration must not exceed 4 gallons per inch of conduit diameter per 1000 feet of pipe per day.

Test for exfiltration when no groundwater exists above the conduit invert. Leakage must not exceed 5 gallons per inch of conduit diameter per 1000 feet of pipe per day. Use minimum test pressure of 4 feet of water column above the crown at the upper end of the conduit.

- Correct all leakage before backfilling.

After backfilling, test each run of conduit for obstructions and alignment by placing a light at one end. The light must be visible through the sewer conduit at the next manhole.

## SECTION 627

## WATER SYSTEM

627-1.01 DESCRIPTION. Furnish and place water main improvements and replacements, including all appurtenances, as shown on the Plans or specified in this Section. Remove, salvage and reinstall or abandon existing fire hydrants, valve boxes, and water meters, as specified.

The term “water conduit” refers to all conduits used for water mains. The term “service pipe” refers to service lines.

Coordinate with the Engineer and AWWU; and participate in a pre-construction condition inspection, and a post-construction condition inspection of the water system facilities.

The inspections may identify main valve boxes, the top section, the lid and additional items, to be replaced. Replace additional facility items as directed by the Engineer.

627-2.01 MATERIALS. Use materials that conform to the following:

Bedding and Backfill	Subsection 204-2.01

HDPE Pipe	Subsection 706-2.08

Ductile Iron Pipe 	Subsection 707-2.05

Service Pipe 	Subsection 707-2.06

Corporation Stops	Subsection 712-2.09

Gate Valves	Subsection 712-2.10

Valve Boxes	Subsection 712-2.11

Hydrants	Subsection 712-2.12

- CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL. Complete the water system and make sure it operates properly at the time of acceptance of the work. Furnish and install all incidental parts not shown on the Plans or specified in this Section that are necessary to complete the water system.

Meet the applicable provisions of Sections 201, 204, and 603 for all clearing and grubbing, excavation, bedding, backfill, conduit, and appurtenances.

It is the Contractor’s responsibility to preserve, protect, and relocate as necessary all utilities encountered in the course of the work, unless the applicable utility agreement specifies that the specific pipe in question is to be abandoned or taken out of service. Confirm and mark the exact locations of all existing utilities before starting work.

Excavate, bore, or probe by hand ahead of your work where necessary to determine the exact location of underground conduit or other features that might interfere with construction. Support and protect conduits or other services that cross the trench. Immediately repair or replace any existing utilities that you break or damage. Immediately replace any existing valves, valve boxes, or water lines that you break or damage.

- Notify the local Fire Department at least 24 hours before removing or interrupting service to fire hydrants.

Give at least 24 hours’ notice before interrupting water service to any area. Restore disrupted water service as soon as possible, or make temporary service connections. Use hoses or other suitable methods.

- If your operations cause service interruptions, you are responsible for all damages.

Furnish and install concrete thrust blocks as shown on the Plans or specified in this Section. Place blocks against firm natural ground at the trench site. When the trench is in soft, unstable soil, remove the soft soil and replace it with a ballast backing large and heavy enough to resist the thrust.

- Connect to existing water lines and structures, avoiding contamination of water in lines that are in use.

Where water mains under this contract approach within 10 feet horizontal clearance and are below or less than 3 feet above existing sanitary sewers, encase the sanitary sewer with a jacket of Class A concrete 3 inches thick for 10 feet on each side of the crossings.

Concrete encasement is not required if the existing sewer is constructed of ductile iron pipe with joints at least 8 feet from the water main, or if you replace the existing sewer with such ductile iron pipe.

Contractor furnishes the required traffic control, including personnel to assist, while performing inspections.

The Contractor forfeits all right to deny pre-existing damage if the Contractor fails to participate in the inspections.

- Install the replacement facility items as shown in the Plans.

During inspections the AWWU representative, the Engineer and the Contractor will observe each facility's location and condition. The Engineer will indicate the additional facility items to be replaced.

Provide 3 days advance written notice to AWWU scheduling a pre-construction inspection of the facilities. Conduct this inspection before pavement removal begins. Contact the AWWU Project Manager to determine where to send the written notice, (907) 564-2763.  Provide the Engineer a copy of the written notice.

AWWU furnishes the valve box top sections and lids. Contact the AWWU Project Manager to schedule the pick-up of the furnished materials. Allow 3 working days from the time contact is made to pick-up of the materials.

If service connection locates are required, contact AWWU Field Services at (907) 564-2762. Allow 3 working days from the time of the request to the time of locate.

Salvage the replaced valve box top sections and lids. Coordinate with, and deliver to AWWU the salvaged materials. Dispose of water system facility materials not wanted by AWWU, according to the Municipality of Anchorage rules and regulations.

Provide a written notice to AWWU scheduling a post-construction inspection of the facilities, after the paving operations are complete and 3 days in advance of the inspection.

627-3.02 INSTALLATION OF CONDUIT. Install conduit and fittings according to these Specifications or the manufacturer's recommendations. Lay conduit to the grades and lines shown on the Plans.

Remove all foreign matter from conduit interiors before lowering conduit into the trench. When work is not in progress, securely close all open ends of conduit and fittings to keep out trench water, earth, rodents or other substances.

Keep trenches dry to avoid laying conduit in water. Do not lay conduit when weather or trench conditions are unsuitable. Keep water away from new joints, until the joint materials have hardened.

- Use methods to cut conduit that will produce tight joints and will not damage the conduit.

- Inspect conduit before lowering it into the trench. Replace defective, damaged, or unsound conduit.

Place conduit bedding to conform to plan details. Place bedding, if required, to give conduit a uniform bearing for its full length. Do not permit couplings to rest on solid or original trench bottoms.

Conduit bends must not exceed the manufacturer’s recommended limits. If the specified or required alignment requires deflections beyond the limits, furnish special bends or enough shorter lengths of conduit to provide angular deflection within the limits.

Use standard lengths of conduit except where fittings require short lengths, or where conduit passes through a rigid structure.

Make service and other connections to conform to the Plans. Valve, plug or cap conduit ends for future connections as shown on the Plans and provide thrust blocks.

627-3.03 FIRE HYDRANTS. Install, relocate, or adjust fire hydrants to the locations and grades shown on the Plans. Where required, furnish and install new fire hydrant extensions and any required conduit.

- Clean all foreign matter from inside hydrants before installation.

Connect the hydrant to the main with 6-inch ductile iron conduit or the same size as the main, whichever is smaller. Provide with an auxiliary valve and cast iron valve box of the same size as the connecting conduit. Use a mechanical connection between the hydrant and the auxiliary valve.

Set hydrants at elevations that drain the connecting conduit to the main. Set the hydrant on a slab of stone or concrete at least 4 inches thick and 15 inches square. Firmly block the back of the hydrant with concrete at least 1 square foot in area against the vertical face of the trench. If the character of the soil does not allow the hydrant to be securely wedged, use bridle rods and rod collars of at least 3/4 inch stock and coated with acid-resisting paint.

Place at least 7 cubic feet of approved broken stone or clean gravel around the base of the hydrant to ensure drainage. Thoroughly compact the backfill around hydrant to the grade line in a satisfactory manner.

Tighten stuffing boxes and inspect the hydrants in opened and closed positions to make sure that all parts are in working condition.

When removing a fire hydrant from an existing main, plug the tee in the main and test for leakage according to Subsection 627-3.06.

Adjust existing fire hydrants for grade, using barrel extensions according to the hydrant manufacturer's recommendations.

627-3.04 VALVES. Install gate valves as shown on the Plans, on a firm base, and plumb. Remove all foreign matter from the interior before installation.

627-3.05 VALVE BOXES. Install valve boxes over the gate valves as shown on the Plans. Center box over valve and rest base section on well-compacted backfill. Set top section to allow equal movement above and below finished grade, with final elevation 1 inch below finished grade. Set top of base section approximately on line with nut at top of valve stem. The entire assembly must be plumb.

- Place a concrete collar on valve boxes installed in pavement, as shown on the Plans.

Adjust existing valve boxes by raising or lowering to conform to the final grade and the details shown on the Plans. Salvage and reuse the existing cast iron valve box and cover. If the valve box is adjustable, adjust it with adaptable extension pieces. If the valve box is constructed with steel conduit, weld additional steel conduit to raise the cover. Lower by cutting the existing valve box pipe.

627-3.06 TESTING WATER SYSTEM. Test all water main and service connection work for both pressure and leakage after laying. Leave conduit joints fully exposed. Place only enough backfill between joints to hold the conduit in place during testing. Test services before insulation. Open corporation stops after successful tests. Conduct all tests with the Engineer present.

Furnish all testing equipment, labor, materials, and supplies. The Engineer has the right to test and approve all gauges used.

Where connection is made to an existing main with no valve present, blank off or plug the outlet leading to the existing main before testing.

Conduct tests after completing installation of the system or any portion thereof, before backfilling and after thoroughly flushing the test portion. Fill all lines with water and eliminate all air.

Use test pressure equal to the strength classification of the pipe. Use either pneumatic or hydraulic pressure. Maintain pressure on the tested portion for at least 2 hours. Allowable leakage during the test must not exceed the amount established by the AWWA. If visible leakage other than minor sweating occurs, immediately stop the test and tighten the joint to eliminate leakage when pressure is resumed. Replace leaking fittings, nipples, or lengths of conduit. Do not caulk or use paints, asphalts, enamels or other types of compounds to eliminate leaks.

- Complete backfilling after acceptance of the tests.

627-3.07 DISINFECTION. After acceptance of pressure and leakage tests, disinfect all portions of the water system, including valves and stops and any portion of the existing connecting system that may have been contaminated during construction.

Use calcium hypochlorite as the disinfecting medium. Use “HTH,” Perchloron, or a similar commercial product with approximately 70% available chlorine. Make a 5% solution by mixing 5% of powder with 95% water (by weight). Mix the solution into a paste, thin it to slurry by adding water, and add it to the system. Place enough disinfecting material in the system to ensure a chlorine dosage of 50 ppm. This dosage is equivalent to 10 ounces of commercial hypochlorite powder to each 1,000 gallons of water.

After adding the chlorine solution, open and leave open all taps, valves, etc., until you notice a strong chlorine odor in the water coming from the outlets; then close the taps, valves, etc. Keep chlorinated water in the system for at least 24 hours; then thoroughly flush the system. During the retention period, operate all valves, stops, and other appurtenances to assist disinfection.

After treating the system, thoroughly flush. Then take samples from representative points in the system. Place samples in sterile bottles and submit them to proper authorities as directed for bacteriological examination. If the bacteriological examination report is unsatisfactory, repeat disinfection until you obtain satisfactory results.

## SECTION 630

## GEOTEXTILE FOR EMBANKMENT
SEPARATION AND STABILIZATION

630-1.01 Description. Prepare surfaces and furnish and place geotextiles for embankment separation and/or stabilization as shown in the Plans.

630-2.01 MATERIALS. Use materials that conform to the following:

Geotextiles and Sewing Thread	Subsection 729-2.01

630-3.01 Construction.

1.	Surface Preparation. Prepare surface by removal of stumps, brush, boulders, and sharp objects. Fill holes and large ruts with material shown on the Plans or as approved.

2.	Geotextile Placement. Unroll geotextile directly onto the prepared surface. Stretch geotextile to remove any creases or wrinkles. Do not expose geotextiles to the elements for longer than 5 days after removal of protective covering.

a.	Separation. Lay geotextile for embankment separation parallel to roadway centerline. On horizontal curves, place in segment lengths not exceeding those listed in Table 630-1, with butt ends cut to match and sewn or overlapped. On tangents, straighten the geotextile and sew or overlap butt ends.

b.	Stabilization. Lay geotextile for embankment stabilization perpendicular to the roadway centerline. Join segments by sewing or an approved bonding or attachment process.

- TABLE 630-1

GEOTEXTILE PLACEMENT ON CURVES

| Degree of Curve | Maximum Segment Length (ft.) |
| --- | --- |
| 1 | 125 |
| 2 | 90 |
| 3 | 75 |
| 4 | 65 |
| 5 | 55 |
| 6 | 50 |

3.	Joining. Join geotextile for embankment separation by sewing or overlapping. Join geotextile for stabilization by sewing. Use other attachment methods, if approved.

a.	Sew seams with a butterfly or J-Seam. Use a double-thread chain stitch (lock stitch) Bring adjacent sections of geotextile together and fold so that the stitching penetrates four layers of geotextile for the full seam length. Make the stitching line 1-1/4 inches (± 1/4 inch) from the folded edge of the seam and at least 1/2 inch from the free edge of the geotextile. Illustrations showing correct stitch formation and seam configurations are provided in Figure 1.2 (page 21) of the FHWA publication, Geosynthetic Design & Construction Guidelines, FHWA-HI-95-038, May 1995.

b.	Overlapped sections must overlap a minimum of 3 feet.

4.	Material Placing and Spreading. During placing and spreading, maintain a minimum depth of 12 inches of cover material at all times between the fabric and the wheels or tracks of the construction equipment.

Spread the material in the direction of the fabric overlap. Maintain proper overlap and fabric continuity. If sewn or bonded seams are used, place the cover material and spread in only one direction for the entire length of the geotextile. On weak subgrades spread the cover material simultaneously with dumping to minimize the potential of a localized subgrade failure.

Compact using a smooth drum roller. Do not allow construction equipment to make sudden stops, starts, or turns on the cover material.

5.	Geotextile Repair.

a.	Separation. Overlay torn area with geotextile with a minimum 3 foot overlap around the edges of the torn area. Ensure that the patch remains in place when material is placed over the affected area.

b.	Stabilization. Sew or bond according to Subsection 630-3.01.3.

## SECTION 631

## GEOTEXTILE FOR SUBSURFACE
DRAINAGE AND EROSION CONTROL

631-1.01 DESCRIPTION. Prepare surfaces and furnish and place geotextiles for subsurface drainage and erosion control as shown in the Plans.

631-2.01 MATERIALS. Use materials that conform to the following, for the class specified in the bid schedule:

Geotextiles and Sewing Thread	Subsection 729-2.02

631-3.01 CONSTRUCTION.

1.	Surface Preparation. Prepare surface by removing stumps, brush, boulders, and sharp objects. Fill holes and large ruts with material shown on the Plans or as approved.

2.	Geotextile Placement. Unroll geotextile directly onto the prepared surface. Stretch geotextile to remove any creases or wrinkles. Do not expose geotextiles to the elements for longer than 5 days after removal of protective covering.

a.	Subsurface Drainage. In trenches, after placing the drain aggregate, fold the geotextile over the top of the aggregate to produce a minimum overlap of 12 inches, for trenches greater than 12 inches wide. In trenches less than 12 inches wide, make the overlap equal to the width of the trench. Then cover the geotextile with the subsequent course of material.

b.	Erosion Control. Place and anchor geotextile on the approved surface so it will not be torn or excessively stretched by placement of the overlying materials. Anchor the terminal ends of the geotextile using key trenches or aprons at the crest and toe of slope, as shown on the Plans. Other temporary or permanent anchoring methods may be used, subject to approval.

3.	Joining. Join geotextile by sewing or overlapping. Joining by bonding or other attachment methods may be used, subject to approval.

a.	Sew seams with a Butterfly or J-Seam. Use a double thread chain stitch (lock stitch). Bring adjacent sections of geotextile together and fold so that the stitching penetrates four layers of geotextile for the full seam length. Make the stitching line 1-1/4 inches (±1/4 inch) from the folded edge of the seam and at least 1/2 inch from the free edge of the geotextile. Illustrations showing correct stitch formation and seam configurations are provided in Figure 1.2 (page 21) of the FHWA publication, Geosynthetic Design & Construction Guidelines, FHWA-HI-95-038, May 1995.

b.	Overlapped sections must overlap a minimum of 3 feet. Overlap successive geotextile sheets in the direction of flow so that the upstream sheet is placed over the downstream sheet and/or upslope over downslope. In trenches, where overlapped seams are constructed in the longitudinal trench direction, make the overlap equal to the width of the trench.

4.	Material Placing and Spreading. Following placement of the geotextile on the prepared surface, place cover material of the type shown on the Plans. Use methods for placing cover material which minimize tearing and/or excessive stretching of the geotextile. In underwater applications, place the geotextile and the required thickness of cover material in the same day. Maintain proper overlap and geotextile continuity. Do not exceed the allowable drop heights for cover material shown in Table 631-1.

- TABLE 631-1

|  | ALLOWABLE DROP HEIGHT (ft) |  |
| --- | --- | --- |
| INDIVIDUAL STONE |  |  |
| Max. Weight (lbs) | UNPROTECTED | PROTECTED |
|  | GEOTEXTILE | GEOTEXTILE * |
| < 5 | 3 | 3 |
| 5-250 | 0 | 3 |
| > 250 | 0 | 0 ** |

*Protected geotextile is defined as having a gravelly covering (cushion layer) of 4 inches minimum thickness.

**If stones greater than 250 pounds must be dropped or if a height of drop greater than 3 feet is required, then perform field trials to determine the maximum height of safe drop without damaging the geotextile.

Maintain a minimum depth of 12 inches of cover material between the geotextile and the wheels or tracks of the construction equipment.

5.	Geotextile Repair. Overlay torn area with geotextile with a minimum 3 foot overlap around the edges of the torn area. Ensure that the patch remains in place when material is placed over the affected area.

## SECTION 632

## PAVING FABRIC

632-1.01 DESCRIPTION. Furnish and install geotextile paving fabric where shown on the Plans.

632-2.01 MATERIALS. Use materials that conform to the following:

Paving Fabric	Subsection 729-2.03

Asphalt Cement	Subsection 702-2.01 (for grade of asphalt used in the overlay)

632-3.01 CONSTRUCTION.

1.	Surface Preparation. Prepare the surface on which the fabric is to be placed as follows:

a.	Fill all potholes and cracks wider than 1/4 inch with an approved asphalt emulsion and sand slurry.

b.	Remove excess asphalt material, loose aggregate, and other foreign materials from the surface.

2.	Application of Sealant. Apply asphalt sealant by distributor meeting all requirements set forth under Subsection 402-3.02. Apply the asphalt sealant uniformly at 0.20 to 0.30 gallons per square yard and at a temperature of between 295 °F min. and 325 °F.

Do not apply asphalt material on a wet surface or when the ambient air temperature is below 45 °F or when other conditions would prevent proper application.

3.	Fabric Laydown Equipment. Use approved mechanical laydown equipment to place fabric.

4.	Fabric Placement. Place fabric directly on top of the asphalt sealant (tack coat) before the sealant has cooled and lost its tackiness. Lay fabric in full rolls without wrinkles and/or folds. Place the fabric per the manufacturer’s recommendations. Overlap transverse joints in the direction of paving. Apply 0.20 gallons per square yard of additional asphalt sealant beneath all fabric joints.

5.	Bituminous Surface Course Overlay. Place the bituminous surface course closely following the fabric laydown to avoid exposure of uncovered fabric overnight or to traffic or inclement weather. If asphalt sealant bleeds through the fabric before the placement of the overlay, apply sand or bituminous surface course evenly over the affected area to prevent fabric pick-up by construction equipment. Prevent paver or other construction equipment from turning and/or pivoting on the fabric.

## SECTION 633

## SILT FENCE

633-1.01 DESCRIPTION. Furnish, place, maintain, and remove temporary silt fence as shown in the Plans or as directed.

633-2.01 MATERIALS. Use materials that conform to the following:

Geotextile	Subsection 729-2.04

Posts	Wood, steel, or approved synthetic material.

633-3.01 CONSTRUCTION.

1.	Post Installation. Place posts a maximum of 8 feet apart and drive a minimum of 18 inches into the ground.

2.	Geotextile Placement. Install geotextile on posts in a vertical position and support by a wire mesh fence or self-support system. Set at the height specified in the Contract. Secure the bottom 18 inches of the geotextile on the upslope side of the fence as shown on the Plans. Backfill trench with tamped soil. Join adjacent sections of geotextile only at posts with a minimum of 6 inches overlap.

633-3.02 MAINTENANCE. Maintain the integrity of the fence as long as it is necessary to contain sediment runoff. Inspect daily and correct any deficiencies immediately. Remove and dispose of fence when adequate vegetative growth insures no further erosion of the slopes. Cut off the fabric at ground level and remove the wire and posts. When thickness of trapped sediment is in excess of 4 inches above the ground, either remove sediment from the site or spread sediment uphill of the fence and seed all exposed soil immediately, following the requirements of Section 618.

## SECTION 634

## GEOGRID SOIL REINFORCEMENT

634-1.01 DESCRIPTION. Furnish and install geogrid material at locations shown on the Plans.

634-2.01 MATERIALS. Use materials that conform to the following:

Geogrid	Subsection 729-2.05

CONSTRUCTION REQUIREMENTS

634-3.01 WEATHER LIMITATIONS. Do not expose geogrid to the elements for longer than 14 days after removal of protective covering.

634-3.02 Surface Preparation.

1.	Soft Ground (CBR 1-3). Prepare surface by removal of stumps, brush, boulders, and sharp objects. Fill holes and large ruts with material shown on the Plans or as approved.

2.	Firm Ground (CBR >3). Compact and finish subgrade or subbase prior to placement of the geogrid.

634-3.03 Geogrid Placement. Unroll geogrid directly onto the prepared surface.

1.	Soft Ground. Overlap geogrid panels a minimum of 24 inches at all joints, in the direction that fill will be placed. Tie panels together securely with cable ties or hog rings at 20 foot intervals.

2.	Firm Ground. Overlap geogrid panels at all joints a minimum of 12 inches, in the direction that fill will be placed. Tie panels together securely with manufacturer-recommended pins or bars. Hand-tension geogrid and stake to the ground at the edges, overlaps, and in the center of each roll, at 30 foot intervals.

634-3.04 Placing and Spreading Cover Material. Do not operate equipment on the unprotected geogrid. Spread fill material in the direction of the fabric overlap.

1.	Soft Ground. Back dump material onto the geogrid. Spread material ahead with a low ground pressure dozer to the depth permitted.

2.	Firm Ground. Maintain a minimum depth of 6 inches of cover material at all times between the fabric and the wheels or tracks of the construction equipment.

Compact using a smooth drum roller. Do not allow construction equipment to make sudden stops, starts, or turns on the cover material.

634-3.05 Geogrid Repair. Overlay torn area with geogrid with a minimum 3 foot overlap around the edges of the torn area and secure as recommended by the geogrid manufacturer.

## SECTION 635

## INSULATION BOARD

635-1.01 DESCRIPTION. Furnish and install polystyrene insulation board where shown on the Plans.

635-2.01 MATERIALS. Use materials that conform to the following:

Insulation Board. AASHTO M 230, Type VI, except that extrusion is not required and the maximum water absorption by weight is 10%, as determined by ASTM C 272. Meet or exceed the specified R value.

- Sand Blanket. Subsection 703-2.12.

635-3.01 CONSTRUCTION REQUIREMENTS. Prior to placing the insulation board, blade, shape, and compact the area per Section 203. Place a sand blanket leveling course at least 2 inches thick.

Set each board accurately to the line and grade established and anchor firmly in place by driving a minimum of 2 wood dowels per panel. Place insulation to the required thickness, using a minimum of two layers. Stagger all joints between layers.

Cover the insulation board with 4 inches of sand blanket material prior to placing subsequent lifts. Use approved spreading and compacting equipment.

## SECTION 636

## GABIONS

636-1.01 DESCRIPTION. Construct wire gabion bank protection at locations shown on the Plans.

636-2.01 MATERIALS. Use materials that conform to the following:

Wire	Subsection 712-2.13

Gabion Backfill	Subsection 703-2.11

636-3.01 CONSTRUCTION REQUIREMENTS. Construct gabions to the lines and grades as staked. Meet the details shown on the Plans.

Assemble gabion baskets per the manufacturer's recommended procedures. Align each row or tier of gabion baskets before filling the baskets. Install tie wires in both directions horizontally so that layers between ties are not more than 14 inches thick. Space tie wires not more than 14 inches apart horizontally within any gabion basket cell. Loop tie wires around at least 3 meshes of the gabion basket and tie or twist securely. Fill each gabion basket so the lid, when secure, will bear on the gabion filler. Securely fasten gabion baskets to all adjacent baskets, using sufficient wire to provide the same strength as the body of the mesh.

- Meet Section 204 for all excavation and backfill for gabions.

## SECTION 639

## DRIVEWAYS

639-1.01 DESCRIPTION. Construct residential or commercial driveways at the locations shown on the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 Construction. Construct driveways to the dimensions shown on the Plans.

## SECTION 640

## MOBILIZATION AND DEMOBILIZATION

640-1.01 DESCRIPTION. Perform work and operations necessary to

- move personnel, equipment, supplies, and incidentals to the project site;

- establish offices, buildings, and other facilities, except as provided under Section 644;

- perform other work and operations and pay costs incurred, before beginning construction;

- complete similar demobilization activities; and

- furnish required submittals such as as-builts, certificates, payrolls, civil rights reports, and equipment warranties.

- Comply with the Alaska Department of Labor and Workforce Development (DOLWD) requirements for Worker Meals and Lodging, or Per Diem; as described in their July 25, 2005 memo WHPL #197 (A2) and the State Laborer’s and Mechanic’s Minimum Rates of Pay (current issue). On Federal-aid projects, PL 109-59, 119 STAT. 1233, Sec. 1409(c) also applies.

- Ensure subcontractors comply with the Federal and State DOLWD requirements.

Ensure facilities meet the Alaska Administrative Code 8 AAC 61.1010 and 8 AAC 61.1040 Occupational Safety and Health Standards, 18 AAC 31 Alaska Food Code, and U. S. Code of Federal Regulations 29 CFR Section 1910.142 Temporary Labor Camps.

Do not consider the cost of Meals and Lodging, or Per Diem in setting wages for the worker or in meeting wage requirements under AS 23.10.065 or AS 36.05.

640-2.01 MATERIALS. None.

640-3.01 CONSTRUCTION REQUIREMENTS. None.

640-4.01 EARNED VALUE.

1.	When you earn 4% of the original contract amount from other Work elements indicated on the approved Schedule of Values, 40% of the amount indicated for the mobilization and demobilization element on the approved Schedule of Values, or 4% of the original contract amount, whichever is less, will be paid.

2.	When you earn a total of 8% of the original contract amount from other Work elements indicated on the approved Schedule of Values, an additional 40% of the amount shown on the approved Schedule of Values for mobilization and demobilization, or an additional 4% of the original contract amount, whichever is less, will be paid.

3.	The remaining balance of the amount indicated for the mobilization and demobilization element shown on the approved Schedule of Values will be paid after all submittals, including all closeout submittals, required under the Contract are received and approved.

## SECTION 641

## EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. Plan, provide, inspect, and maintain control of erosion, sedimentation, water pollution, and hazardous materials contamination.

Provide project administration and Work relating to control of erosion, sedimentation, and discharge of pollutants, according to this section and applicable local, state, and federal requirements, including the Construction General Permit.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMPs in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit. Use EPA Form 3510-9.

- NOT. Notice of Termination of coverage under the NPDES General Permit. Use EPA Form 3510-713.

- NPDES General Permit. The Storm Water General Permit for Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires an approved SWPPP and NOIs listed as active status by the EPA prior to ground-disturbing activities for the project.

- SPCC Plan (Spill Prevention, Control and Countermeasure). The Contractor’s detailed plan for oil spill prevention and control measures, that meets the requirements of 40 CFR 112.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

- These definitions apply only to Section 641.

Active Treatment System Operator. The Contractor’s qualified representative who is responsible for maintaining and operating an active treatment system (as defined in the CGP) for storm water runoff.

Alaska Certified Erosion and Sediment Control Lead (AK-CESCL). A person who has completed training, testing, and other requirements of, and is currently certified as, an AK-CESCL from an AK-CESCL Training Program (a program developed under a Memorandum of Understanding between the Department and others). The Department recognizes AK-CESCLs as “qualified personnel” required by the CGP. An AK-CESCL must be recertified every three years.

Alaska Department of Environmental Conservation (ADEC).  The state agency authorized by EPA to administer the Clean Water Act’s National Pollutant Discharge Elimination System.

Alaska Pollutant Discharge Elimination System (APDES). A system administered by ADEC that issues and tracks permits for storm water discharges.

Best Management Practices (BMPs).  Temporary or permanent structural and non-structural devices, schedules of activities, prohibition of practices, maintenance procedures, and other management practices to prevent or minimize the discharge of pollutants to waters of the United States. BMPs also include, but are not limited to, treatment requirements, operating procedures, and practices to control plant site runoff, spillage or leaks, sludge or waste disposal, or drainage from material storage.

Clean Water Act (CWA).  Federal Water Pollution Control Amendments of 1972, as amended (33 U.S.C. 1251 et seq.).

Consent Decree. The decree entered by the United States District Court for the District of Alaska on September 21, 2010, regarding compliance with the CWA and implementation of the CGP, to which the United States and the Department are parties.

Construction Activity. Physical activity by the Contractor, Subcontractor or utility company; that may result in erosion, sedimentation, or a discharge of pollutants into storm water. Construction Activity includes soil disturbing activities (e.g. clearing, grubbing, grading, excavating); and establishment of construction materials or equipment storage or maintenance areas (e.g. material piles, borrow area, concrete truck chute washdown, fueling); and industrial activities that may discharge storm water and are directly related to the construction process (e.g. concrete or asphalt batch plants).

Construction General Permit (CGP). The permit authorizing storm water discharges from Construction Activities, issued and enforced by ADEC. It authorizes stormwater discharges provided permit conditions and water quality standards are met.

Corp of Engineers Permit (COE Permit). A U.S. Army Corp of Engineers Permit for construction in waters of the US. Such permit may be issued under Section 10 of the Rivers and Harbors Act of 1899, or Section 404 of the Clean Water Act.

Electronic Notice of Intent (eNOI). The electronic Notice of Intent submitted to ADEC, to obtain coverage under the CGP.

Electronic Notice of Termination (eNOT). The electronic Notice of Termination submitted to ADEC, to end coverage under the CGP.

Environmental Protection Agency (EPA). A federal agency charged to protect human health and the environment.

Erosion and Sediment Control Plan (ESCP). The Department’s project specific document that illustrates measures to control erosion and sediment on the project. The ESCP provides bidders with the basis for cost estimating and guidance for developing an acceptable Storm Water Pollutant Prevention Plan (SWPPP).

- Final Stabilization. Is defined in this section as it is defined in the CGP.

Hazardous Material Control Plan (HMCP).  The Contractor's detailed project specific plan for prevention of pollution from storage, use, transfer, containment, cleanup, and disposal of hazardous material (including, but are not limited to, petroleum products related to construction activities and equipment).  The HMCP is included as an appendix to the SWPPP.

Inspection.  An inspection required by the CGP or the SWPPP, usually performed together by the Contractor’s SWPPP Manager and Department’s Stormwater Inspector.

Municipal Separate Storm Sewer System (MS4) Permit.  An ADEC storm water discharge permit issued to certain local governments and other public bodies, for operation of storm water conveyances and drainage systems. See CGP for further definition.

Multi-Sector General Permit (MSGP). The Alaska Pollutant Discharge Elimination System General Permit for storm water discharges associated with industrial activity.

Operator(s). The party or co-parties associated with a regulated activity that has responsibility to obtain permit coverage under the CGP.  ”Operator” for the purpose of the CGP and in the context of storm water associated with construction activity, means any party associated with a construction project that meets either of the following two criteria:

- The party has operational control over construction plans and specifications, including the ability to make modifications to those plans and specifications; or

- The party has day to day operational control of those activities at a project which are necessary to ensure compliance with a SWPPP for the site or other permit conditions (e.g. they are authorized to direct workers at a site to carry out activities required by the SWPPP or comply with other permit conditions).

Pollutant. Any substance or item meeting the definition of pollutant contained in 40 CFR § 122.2. A partial listing from this definition includes: dredged spoil, solid waste, sewage, garbage, sewage sludge, chemical wastes, biological materials, wrecked or discarded equipment, rock, sand, cellar dirt and industrial or municipal waste.

Project Zone. The physical area provided by the Department for Construction. The Project Zone includes the area of highway or facility under construction, project staging and equipment areas, and material and disposal sites; when those areas, routes and sites, are provided by the Department by the Contract and are directly related to the Contract.

Material sites, material processing sites, disposal sites, haul routes, staging and equipment storage areas; that are furnished by the Contractor or a commercial operator, are not included in the Project Zone.

Records. Any record, report, information, document or photograph required to be created or maintained pursuant to the requirements of the Consent Decree, the CGP, the CGP storm water requirements of the Clean Water Act; and applicable local, state, and federal laws and regulations regarding document preservation.

Spill Prevention, Control and Countermeasure Plan (SPCC Plan). The Contractor’s detailed plan for petroleum spill prevention and control measures, that meet the requirements of 40 CFR 112.

Spill Response Field Representative. The Contractor’s representative with authority and responsibility for managing, implementing, and executing the HMCP and SPCC Plan.

Storm Event. A rainfall event that produces more than 0.5 inch of precipitation in 24 hours and that is separated from the previous storm event by at least 3 days of dry weather.

Storm Water Pollution Prevention Plan (SWPPP). The Contractor’s detailed project specific plan to minimize erosion and contain sediment within the Project Zone, and to prevent discharge of pollutants that exceed applicable water quality standards. The SWPPP includes, but is not limited to, amendments, records of activities, inspection schedules and reports, qualifications of key personnel, and all other documentation, required by the CGP and this specification, and other applicable local, state, and federal laws and regulations.

Storm Water Pollution Prevention Plan Two (SWPPP2). The Contractor’s detailed project specific plan to comply with CGP or MSGP requirements, for Contractor construction-related activities outside the Project Zone.

Subcontractor Spill Response Coordinator. The subcontractor’s representative with authority and responsibility for coordinating the subcontractor’s activities in compliance with the HMCP and SPCC Plan.

Subcontractor SWPPP Coordinator. The subcontractor’s representative with authority to direct the subcontractor’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the subcontractor’s compliance with the SWPPP.

Superintendent. The Contractor’s duly authorized representative in responsible charge of the work.  The Superintendent has responsibility and authority for the overall operation of the Project and for Contractor furnished sites and facilities directly related to the Project.

- SWPPP Amendment. A revision or document that adds to, deletes from, or modifies the SWPPP.

SWPPP Manager. The Contractor’s qualified representative who conducts Inspections, updates SWPPP records, and has authority to suspend work and to implement corrective actions required for CGP compliance.

SWPPP Preparer. The Contractor’s qualified representative who is responsible for developing the initial SWPPP.

Utility Spill Response Coordinator. The Utility’s representative with authority and responsibility for coordinating the Utility’s activities in compliance with the HMCP and SPCC Plan.

Utility SWPPP Coordinator. The Utility’s representative with authority to direct the Utility’s work, and who is responsible for coordination with the Superintendent and SWPPP Manager, and for the Utility’s compliance with the SWPPP.

641-1.03 PLAN AND PERMIT SUBMITTALS.  For plans listed in Subsection 108-1.03.5 (SWPPP and HMCP) use the Contractor submission and Department review deadlines identified in Subsection 641-1.03.

Partial and incomplete submittals will not be accepted for review.  Any submittal that is re-submitted or revised after submission, but before the review is completed, will restart the submittal review timeline. No additional Contract time or additional compensation will be allowed due to delays caused by partial or incomplete submittals, or required re-submittals.

- Storm Water Pollution Prevention Plan. Submit an electronic copy and three hard copies of the SWPPP to the Engineer for approval. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. Organize and bind the SWPPP and related documents for submittal according to the requirements of Subsection 641-2.01.2.

The Department will review the SWPPP submittals within 14 days after they are received. Submittals will be returned to the Contractor, and marked as either “rejected” with reasons listed or as “approved” by the Department. When the submittal is rejected, the Contractor must revise and resubmit the SWPPP. The 14 day review period will restart when the contractor submits an electronic copy and three hard copies of the revised SWPPP to the Engineer for approval.

After the SWPPP is approved by the Department, the Contractor must sign and certify the approved SWPPP. See Item 4 for further SWPPP submittal requirements.

- Hazardous Material Control Plan.  Submit an electronic copy and three hard copies of the HMCP, as an appendix to the SWPPP, to the Engineer for approval. The HMCP submittal and review timeline, and signature requirements are the same as the SWPPP.

- Spill Prevention, Control and Countermeasure Plan. When a SPCC Plan is required under Subsection 641-2.03, submit an electronic copy and three signed hard copies of the SPCC Plan to the Engineer. Deliver these documents to the Engineer at least 21 days before beginning Construction Activity. The Department reserves the right to review the SPCC Plan and require modifications.

- CGP Coverage. The Contractor is responsible for permitting of Contractor and subcontractor Construction Activities related to the Project. Do not use the SWPPP for Construction Activities outside the Project Zone where the Department is not an operator.  Use a SWPPP2 for Construction Activities outside the Project Zone.

After Department approval of the SWPPP and prior to beginning Construction Activity, submit an eNOI with the required fee to ADEC for coverage under the Construction General Permit (CGP). Submit a copy of the signed eNOI and ADEC’s written acknowledgement (by letter or other document), to the Engineer as soon as practicable and no later than three days after filing eNOI or receiving a written response.

- Do not begin Construction Activity until the conditions listed in Subsection 641-3.01.1 are completed.

The Department will submit an eNOI to ADEC for Construction Activities inside the Project Zone. The Engineer will provide the Contractor with a copy of the Department’s eNOI and ADEC’s written acknowledgment (by letter or other document), for inclusion in the SWPPP.

Before Construction Activities occur transmit to the Engineer an electronic copy of the approved and certified SWPPP, with signed Delegations of Signature Authorities, SWPPP Certifications, both permittee’s signed eNOIs and ADEC’s written acknowledgement.

- Ending CGP Coverage. Submit an eNOT to ADEC within 30 days after the Engineer has determined the conditions listed in Subsection 641-3.01.6 have been met. Submit a copy of the signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

- ADEC SWPPP Review.  When CGP Part 2.1.3, requires ADEC SWPPP review:

- Transmit a copy of the Department-approved SWPPP to ADEC using delivery receipt confirmation;

- Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation; and

- Retain a copy of delivery receipt confirmation in the SWPPP.

7.	Local Government SWPPP Review.  When local government or the CGP Part 2.1.4, requires local government review:

- Transmit a copy of the Department-approved SWPPP and other information as required to local government, with the required fee.  Use delivery receipt confirmation;

- Transmit a copy of the delivery receipt confirmation to the Engineer within seven days of receiving the confirmation;

- Transmit a copy of any comments by the local government to the Engineer within seven days of receipt;

- Amend the SWPPP as necessary to address local government comments and transmit SWPPP Amendments to the Engineer within seven days of receipt of the comments;

- Include a copy of local government SWPPP review letter in the SWPPP; and

- File a notification with local government that the project is ending.

8.	Modifying Contractor’s eNOI.  When required by The CGP Part 2.7, modify your eNOI to update or correct information. Reasons for modification include a change in start or end dates, small changes in number of acres to be disturbed, change in decision to use or not use treatment chemicals, or change in location of SWPPP Records.

The Contractor must submit an eNOT and then submit a new eNOI instead of an eNOI modification when: the operator has changed, the original eNOI indicates disturbed area less than five acres and the project will disturb more than five acres, or a project over five disturbed acres grows by more than 50%.

641-1.04 PERSONNEL QUALIFICATIONS. Provide documentation in the SWPPP that the individuals serving in these positions meet the personnel qualifications.

The SWPPP Preparer must meet at least one of the following qualifications:

- Current certification as a Certified Professional in Erosion and Sediment Control (CPESC);

- Current certification as AK-CESCL, and at least two years experience in erosion and sediment control, as a SWPPP Manager or SWPPP writer, or equivalent. Provide documentation including project names, project timelines, and work responsibilities demonstrating the experience requirement; or

- Professional Engineer registered in the State of Alaska with current certification as AK-CESCL.

For Projects disturbing more than 20 acres, the SWPPP Preparer must also have completed a SWPPP Preparation course.

The Superintendent must meet the following qualifications:

- Current certification as AK-CESCL; and

- Duly authorized representative, as defined in the CGP, Appendix A, Part 1.12.3.

The SWPPP Manager must have current certification as AK-CESCL and must meet the CGP experience, training, and authority requirements identified for the Storm Water Lead and Storm Water Inspector positions as defined in the CGP, Appendix C, Qualified Person.

The Active Treatment System (ATS) operator must have current certification as AK-CESCL, and be knowledgeable in the principals and practices of treatment systems in general, and the operation of the project-specific ATS. The ATS operator must have at least three months field experience with ATS, or completion of an ATS manufacturer’s training course, or completion of system operators certification course.

The Department accepts people having any of the following certificates as equivalent to AK-CESCL, if the certificates are current according to the sponsoring organization’s policies:

- CPESC, Certified Professional in Erosion and Sediment Control; or

- CISEC, Certified Inspector in Sediment and Erosion Control.

641-1.05 SIGNATURE/CERTIFICATION REQUIREMENTS AND DELEGATIONS.

- eNOI and eNOT. The eNOI and eNOT must be signed and certified by a responsible corporate officer according to CGP Appendix A, Part 1.12.2. Signature and certification authority for the eNOI and eNOT cannot be delegated.

- Delegation of Signature Authority for Other SWPPP Documents and Reports.  Use Form 25D-108 to delegate signature authority and certification authority to the Superintendent position, according to CGP Appendix A, Part 1.12.3, for the SWPPP, Inspection Reports and other reports required by the CGP. The Superintendent position is responsible for signing and certifying the SWPPP, Inspection Reports, and other reports required by the CGP, except the eNOI and eNOT.

The Engineer will provide the Department’s delegation Form 25D-107, which the Contractor must include in the SWPPP.

- Subcontractor Certification. Subcontractors must certify that they have read and will abide by the CGP and the conditions of the project SWPPP.

- Signatures and Initials.  Handwrite signatures or initials on CGP documents and SWPPP forms, wherever a signature or initial is required.

641-1.06 RESPONSIBILITY FOR STORM WATER PERMIT COVERAGE.

- The Department and the Contractor are jointly responsible for permitting and permit compliance within the Project Zone.

- The Contractor is responsible for permitting and permit compliance outside the Project Zone. The Contractor has sole responsibility for compliance with ADEC, COE and other applicable federal, state, and local requirements, and for securing all necessary clearances, rights, and permits. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

- An entity that owns or operates, a commercial plant (as defined in Subsection 108-1.01.3) or material source or disposal site outside the Project Zone, is responsible for permitting and permit compliance. The Contractor has sole responsibility to verify that the entity has appropriate permit coverage. Subsection 107-1.02 describes the requirement to obtain permits, and to provide permit documents to the Engineer.

- The Department is not responsible for permitting or permit compliance, and is not liable for fines resulting from noncompliance with permit conditions:

a.	For areas outside the Project Zone;

b.	For Construction Activity and Support Activities outside the Project Zone; and

c.	For commercial plants, commercial material sources, and commercial disposal sites.

641-1.07 UTILITY. Relocation Coverage. A Utility company is not an Operator when utility relocation is performed concurrently with the Project, as outlined in Section 105-1.06. The Department maintains operational control over the Utility’s plans and specifications for coordination with project construction elements, and the Contractor has day-to-day control over the various utility construction activities that occur in support of the Project. A Utility company is considered a subcontractor for concurrent relocation.

After the Contractor has an active NOI for the Project, a Utility Company performing advance relocation work under a separate SWPPP no longer has Operator status and files the NOT for the Utility Company’s SWPPP covering only the completed utility work. Remaining utility relocation work is included in and performed under the Project SWPPP.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS.

- 1.	SWPPP Preparer and Pre-Construction Site Visit.

Use a SWPPP Preparer to develop the SWPPP and associated documents, according to the requirements of the CGP and COE permit. The SWPPP Preparer must put their name, qualifications (including the expiration date of any certifications), title and company name in the SWPPP.

The SWPPP Preparer must conduct a pre-construction inspection at the Project site before construction activity begins. If the SWPPP Preparer is not a Contractor employee, the SWPPP Preparer must visit the site accompanied by the Contractor. Give the Department at least seven days notice of the site visit, so that the Department may participate.

During the pre-construction inspection, the SWPPP Preparer must identify, or if a draft of the SWPPP has already been prepared verify that the SWPPP fully addresses and describes:

- Opportunities to phase construction activities;

- Appropriate BMPs and their sequencing; and

- Sediment controls that must be installed prior to beginning Construction Activities.

Document the SWPPP Preparer’s pre-construction inspection in the SWPPP on Form 25D-106, SWPPP Pre-Construction Site Visit, including the names of attendees and the date.

- 2.	Developing the SWPPP.

Use the Department’s ESCP, Environmental commitments, and other Contract documents as a starting point for developing the SWPPP. The approved SWPPP replaces the ESCP.

Develop the SWPPP with sections and appendices, according to the current DOT&PF SWPPP template. Include information required by the Contract and the CGP.

Obtain the following forms after they have been completed by the Department and include them in the SWPPP:

    - SWPPP Delegation of Signature Authority – DOT&PF (25D-107)

    - SWPPP Certification for DOT&PF (25D-109)

    - SWPPP Delayed Action Item Report (25D-113)

Use the following Department forms for recording information in the SWPPP:

  - SWPPP Amendment Log (25D-114)

  - SWPPP Certification for Contractor (25D-111)

  - SWPPP Construction Site Inspection Report (25D-100)

  - SWPPP Corrective Action Log (25D-112)

  - SWPPP Daily Record of Rainfall (25D-115)

  - SWPPP Delegation of Signature Authority – Contractor (25D-108)

  - SWPPP Grading and Stabilization Activities Log (25D-110)

  - SWPPP Pre-Construction Site Visit (25D-106)

  - SWPPP Project Staff Tracking (25D-127)

  - SWPPP Subcontractor Certification (25D-105)

  - SWPPP Training Log (25D-125)

SWPPP Template and Forms are available online at:  http://www.dot.state.ak.us/stwddes/dcsconst/pop_constforms.shtml

Compile the SWPPP in three ring binders with tabbed and labeled dividers for each section and appendix.

- 3.	 SWPPP Considerations and Contents.

The SWPPP must provide erosion and sediment control measures for all Construction Activity within the Project Zone. Construction activity outside the Project Zone must have permit coverage, using a separate SWPPP2, and separate Contractor Inspections.

The SWPPP must consider the activities of the Contractor and all subcontractors and utility companies performing work in the Project Zone. The SWPPP must describe the roles and responsibilities of the Contractor, subcontractors, utility companies, and the Department with regard to implementation of the SWPPP.  The SWPPP must identify all operators for the Project, including utility companies performing Construction Activity, and identify the areas:

- Over which each operator has operational control; and

b.	Where the Department and Contractor are co-operators.

For work outside the Project Zone the SWPPP must identify the entity that has stormwater permit coverage, the operator, and the areas that are:

- Dedicated to the Project and where the Department is not an operator; and

- Not dedicated to the project, but used for the project.

Develop the SWPPP according to the requirements of the CGP and this specification.   Account for the Contractor’s construction methods and phasing. Identify the amount of mean annual precipitation.

Comply with the CGP Part 1.4 .2 Allowable Non-Storm Water Discharges. List locations where authorized non-storm water will be used, including the types of water that will be used on-site.

Include the Department’s Antidegredation Analysis in the SWPPP if storm water from the Project Zone discharges into receiving water that is considered a high quality water and that constitutes an outstanding national resource, according to CGP Part 2.1.5.

There are special requirements in the CGP Part 3.2, for storm water discharges into an impaired water body, and they may include monitoring of storm water discharges. For Projects meeting the permit criteria, the Department will initiate a monitoring program for the storm water within the Project Zone, and will provide the required information and reports for inclusion in the SWPPP. The Contractor is responsible for monitoring and reporting outside the Project Zone.

Preserve natural topsoil unless infeasible. Delineate the site according to CGP Part 4.1.  Use stakes, flags, or silt fence, etc. to identifying areas where land disturbing activities will occur and areas that will be left undisturbed. Minimize the amount of soil exposed during Construction activity according to CGP Part 4.1.2.

Comply with CGP Part 4.3, requirements for dewatering for trenches and excavations.

The SWPPP must identify specific areas where potential erosion, sedimentation, or pollution may occur.  The potential for wind erosion must be addressed.  The potential for erosion at drainage structures must be addressed.

Describe methods and time limits, to initiate temporary or permanent soil stabilization. For areas with mean annual precipitation of:

- 40 inches or less, initiate stabilization as soon as practicable and within 14 days; or

- Greater than 40 inches, initiate stabilization as soon as practicable and within seven days.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

Include in the “Stabilize Soils” section of the SWPPP, a description of how you will minimize the amount of disturbed and unstabilized ground in the fall season. Identify anticipated dates of fall freeze-up and spring thaw. Describe how you will stabilize areas when it is close to or past the seasonal time of snow cover or frozen conditions, and before the first seasonal thaw. Include a plan for final stabilization.

Plans for Active Treatment Systems must be submitted to DEC for review at least 14 days prior to their use and the Operator of the ATS identified in the SWPPP. Any use of treatment chemicals must be identified on the NOI.

The SWPPP must provide designated areas for equipment and wheel washing, equipment fueling and maintenance, chemical storage, staging or material storage, waste or disposal sites, concrete washouts, paint and stucco washouts, and sanitary toilets. These activities must be done in designated areas that are located, to the extent practicable, away from drain inlets, conveyance channels, and waters of the US. No discharges are allowed from concrete washout, paint and stucco washout; or from release oils, curing compounds, fuels, oils, soaps, and solvents. Equipment and wheel washing water that doesn’t contain detergent may be discharged on-site if it is treated before discharge.

Design temporary BMPs for a 2 year 24 hour precipitation amount. Describe BMPs in the SWPPP and in SWPPP Amendments, including source controls, sediment controls, discharge points, and temporary and permanent stabilization measures. Describe the design, placement, installation, and maintenance of each BMP, using words and drawings as appropriate. Describe the design capacity of sediment basins (including sediment ponds and traps). Provide a citation to the BMP Manual or publication used as a source for the BMP, including the title of the BMP Manual or publication, the author (individual or agency), and date of publication. If no published source was used to select or design a BMP, then the SWPPP or SWPPP amendment must state that “No BMP manual or publication was used for this design.”

Describe the sequence and timing of activities that disturb soils and of BMP implementation and removal. Phase earth disturbing activities to minimize unstabilized areas, and to achieve temporary or final stabilization quickly. Whenever practicable incorporate final stabilization work into excavation, embankment and grading activities.

Identify the inspection frequency in the SWPPP:

- For areas where the mean annual precipitation is 15 inches or less, inspect at least once every 14 days during construction and within 24 hours of the end of a storm event ) that resulted in a discharge from the site;

- For areas where the mean annual precipitation is between 15 to 40 inches, inspect either once seven days or according to item a;

- For areas where the mean annual precipitation is 40 inches or greater, inspect once every seven days, and at least twice every seven days during periods of relatively continuous precipitation or sequential storm events.

Linear Project Inspections, described in CGP Part 6.5, are not applicable to this project.

The SWPPP must cite and incorporate applicable requirements of the Project permits, environmental commitments, COE permit, and commitments related to historic preservation. Make additional consultations or obtain permits as necessary for Contractor specific activities which were not included in the Department’s permitting and consultation.

The SWPPP is a dynamic document. Keep the SWPPP current by noting installation, modification, and removal of BMPs, and by using amendments, SWPPP amendment logs, Inspection Reports, corrective action logs, records of land disturbance and stabilization, and any other records necessary to document storm water pollution prevention activities and to satisfy the requirements of the Consent Decree, CGP and this specification. See Subsection 641-3.03 for more information.

- 4.	Recording Personnel and Contact Information in the SWPPP.

Identify the SWPPP Manager as the Storm Water Lead and Storm Water Inspector positions in the SWPPP. Document the SWPPP Manager’s responsibilities in Section 2.0 Storm Water Contacts, of the SWPPP template and:

- Identify that the SWPPP Manager does not have authority to sign inspection reports (unless the SWPPP Manager is also the designated project Superintendent).

- Identify that the SWPPP Manager cannot prepare the SWPPP unless the SWPPP Manager meets the Contract requirements for the SWPPP Preparer.

Include in the SWPPP, Records of the AK-CESCL cards or certificates for the Superintendent and SWPPP Manager, and for any acting Superintendent and acting SWPPP Managers.  If the Superintendent or SWPPP Manager is replaced permanently or temporarily, by an acting Superintendent or acting SWPPP Manager; record in the SWPPP (use Form 25D-127) the names of the replacement personnel, the date of the replacement. For temporary personnel record their beginning and ending dates.

Provide 24 hour contact information for the Superintendent and SWPPP Manager. The Superintendent and SWPPP Manager must have 24 hour contact information for all Subcontractor SWPPP Coordinators and Utility SWPPP Coordinators.

Include in the SWPPP, Records of the AK-CESCL cards or certificates of ATS operators. Record names of ATS operators and their beginning and ending dates, on Form 25D-127.

The Department will provide Records of AK-CESCL cards or certificates for the Project Engineer, Stormwater Inspectors, and Monitoring Person (if applicable), and names and dates they are acting in that position. Include the Department’s Records in the SWPPP Appendix.   Include the department’s Storm Water Inspector and Storm Water Monitoring Person (if applicable) in section 2.0 of the SWPPP.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS.

Prepare the HMCP for prevention of pollution from storage, use, containment, cleanup, and disposal of all hazardous material, including petroleum products related to construction activities and equipment. Include the HMCP as an appendix to the SWPPP. Compile Material Safety Data Sheets in one location and reference that location in the HMCP.

Designate a Contractor’s Spill Response Field Representative with 24 hour contact information. Designate a Subcontractor Spill Response Coordinator for each subcontractor. The Superintendent and Contractor’s Spill Response Field Representative must have 24 hour contact information for each Subcontractor Spill Response Coordinator and the Utility Spill Response Coordinator.

List and give the location and estimated quantities of hazardous materials (Including materials or substances listed in 40 CFR 117 and 302, and petroleum products) to be used or stored on the Project. Hazardous materials must be stored in covered storage areas.  Include secondary containment for all hazardous material storage areas.

Identify the locations where fueling and maintenance activities will take place, describe the activities, and list controls to prevent the accidental spillage of petroleum products and other hazardous materials. Controls include placing absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

List the types and approximate quantities of response equipment and cleanup materials available on the Project. Include a list and location map of cleanup materials, at each different work site and readily available off site (materials sources, material processing sites, disposal sites, staging areas, etc). Spill response materials must be stored in sufficient quantity at each work location, appropriate to the hazards associated with that site.

Describe procedures for containment and cleanup of hazardous materials.  Describe a plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by spills.  Describe a plan for dealing with contaminated soil and water encountered during construction. Clean up spills or contaminated surfaces immediately.

Describe methods of disposing of waste petroleum products and other hazardous materials generated by the Project, including routine maintenance.  Identify haul methods and final disposal areas.  Assure final disposal areas are permitted for hazardous material disposal.

Describe methods of complying with the requirements of AS 46.04.010-900, Oil and Hazardous Substances Pollution Control, and 18 AAC 75. Include contact information for reporting hazardous materials and petroleum product spills to the Project Engineer and reporting to federal, state and local agencies.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC Plan) REQUIREMENTS.   Prepare and implement an SPCC Plan when required by 40 CFR 112; when both of the following conditions are present on the Project:

- Oil or petroleum products from a spill may reach navigable waters (as defined in 40 CFR 112); and

- Total above ground storage capacity for oil and any petroleum products is greater than 1,320 gallons (not including onboard tanks for fuel or hydraulic fluid used primarily to power the movement of a motor vehicle or ancillary onboard oil-filled operational equipment, and not including containers with a storage capacity of less than 55 gallons)

Reference the SPCC Plan in the HMCP and SWPPP.

641-2.04 RESPONSIBILITY AND AUTHORITY OF THE SUPERINTENDENT AND SWPPP MANAGER.

The Superintendent is responsible for the overall operation of the Project and all Contractor furnished sites and facilities directly related to the Project. The Superintendent shall sign and certify the SWPPP, Inspection Reports, and other reports required by the CGP, except the NOI and NOT. The Superintendent may not delegate the task or responsibility of signing and certifying the SWPPP submitted under Subsection 641-1.03.1, Inspection Reports, and other reports required by the CGP.

The Superintendent may assign certain duties to the SWPPP Manager those duties may include:

- Ensuring Contractor’s and subcontractor’s compliance with the SWPPP and CGP;

- Ensuring the control of erosion, sedimentation, or discharge of pollutants;

- Directing and overseeing installation, maintenance, and removal of BMPs;

- Performing Inspections; and

- Updating the SWPPP including adding amendments and forms.

When Bid Item 641(7) is part of the Contract, the SWPPP Manager must be available at all times to administer SWPPP requirements, and be physically present within the Project Zone or the project office, for at least eight hours per day when construction activities are occurring.

The Superintendent and SWPPP Manager shall be knowledgeable in the requirements of this Section 641, the SWPPP, CGP, BMPs, HMCP, SPCC Plan, environmental permits, environmental commitments, and historic preservation commitments.

The Superintendent and SWPPP Manager shall have the Contractor’s complete authority and be responsible for suspending construction activities that do not conform to the SWPPP or CGP.

641-2.05 MATERIALS.

Use materials suitable to withstand hydraulic, wind, and soil forces, and to control erosion and trap sediments according to the requirements of the CGP and the Specifications.

Use the temporary seed mixture specified by special provision, or use annual rye grass if no temporary seed mix is specified.

- Use soil stabilization material as specified in Section 727.

- Use silt fences as specified in Section 729.

Use straw that is certified as free of noxious weed by the United States Department of Agriculture, Natural Resources Conservation Service, Local Soil and Water Conservative District. Alaska Weed Free Forage Certification Program must be used when available. Hay may not be substituted for straw.

Use Oregon Scientific RGR126 wireless rain gauge with temperature, or Taylor 2751 Digital Wireless Rain Gauge with Thermometer, or approved equivalent.

641-2.06 CONTRACTOR REQUIREMENTS.

The Contractor must be familiar with the requirements of the CGP and Consent Decree because Contractor’s employees will be conducting duties that relate to compliance with the CGP and the Consent Decree. A copy of the Consent Decree is available on the Department’s Statewide Environmental Office web page.

641-3.01 CONSTRUCTION REQUIREMENTS.

- Comply with the SWPPP and the requirements of the CGP.

- Before Construction Activity May Begin.

The following actions must be completed before Construction Activity begins:

- The SWPPP Preparer must visit the Project, the visit must be documented in the SWPPP, and the SWPPP must be developed (or amended) with findings from the visit;

- The SWPPP must be approved by the Engineer;

- The Contractor must be authorized to begin by the Engineer;

- The Project eNOIs for the Department and for the Contractor, as well as any other eNOIs if there are additional operators, must be listed as Active Status on the ADEC website;

- The Department approved SWPPP must be submitted to ADEC and Local Government (when required); and

- The Contractor has transmitted to the Engineer an electronic copy of the approved SWPPP.

You may begin Winter Construction activity according to CGP Part 4.10.3, provided actions a through c above are completed before winter construction activity begins.

Post notices containing the following information:

- Copy of all eNOIs related to this project;

- Name and 24 hour phone number of SWPPP Manager; and

- Location of the SWPPP.

Post notices on the outside wall of the Contractor’s project office, and near the main entrances of the construction project. Protect postings from the weather. Locate postings so the public can read them without obstructing construction activities or the traveling public (for example, at an existing pullout).  Do not use retroreflective signs for the SWPPP posting. Do not locate SWPPP signs in locations where the signs may be confused with traffic control signs or devices. Update the notices if the listed information changes.

Install an outdoor rain gauge in per manufacturer’s guidance in a readily accessible location on the Project.

Delineate the site for both land disturbing activities and areas that will be left undisturbed. Install sediment controls and other BMPs that must be placed prior to the initiation of Construction Activity.

- During Construction.

Before subcontractors or utility companies begin soil disturbing activities, provide to them copies of applicable portions of the SWPPP, and require them to sign a SWPPP Subcontractor Certification, Form 25D-105. Include SWPPP Subcontractor Certifications as an appendix to the SWPPP. Ensure subcontractors and utility companies understand and comply with the SWPPP and the CGP. Inform subcontractors and utility companies of SWPPP amendments that affect them in a timely manner. Coordinate with subcontractors and utility companies doing work in the Project Zone so BMPs, including temporary and permanent stabilization are installed, maintained, and protected from damage.

Provide on-going training to employees and subcontractors, on control measures at the site and applicable storm water pollution prevention procedures. Training must be specific to the installation, maintenance, protection, and removal of control measures. Training must be given at a frequency that will be adequate to ensure proper implementation and protection of control measures, and no less frequently than once a month during construction activity. Document on the SWPPP Training Log. Form 25D-125, the dates and attendees to these trainings. Include the SWPPP Training Log as an appendix to the SWPPP.

Notify the Engineer immediately if the actions of any utility company or subcontractor do not comply with the SWPPP and the CGP.

Comply with Subsection 107-1.11 Protection and Restoration of Property and Landscape. Concrete washout must be fully contained.

Fuel in designated areas. Place absorbent pads or other suitable containment under fill ports while fueling, under equipment during maintenance or repairs, and under leaky equipment.

Comply with requirements of the HMCP and SPCC Plan, and all local, state and federal regulations that pertain to the handling, storage, containment, cleanup, and disposal of petroleum products or other hazardous materials.

Keep the SWPPP and HMCP current (refer to Subsection 641-2.01.3, SWPPP Considerations and Contents)

- Pollutant and Hazardous Materials Reporting Requirements.

If there has been an incident of non-compliance with the CGP that may endanger health or the environment, immediately report the incident to ADEC according to the CGP, Appendix A, Part 3.0. Notify the Engineer immediately and to the extent possible coordinate reports to ADEC with the Engineer. The report must include:

- A description of the noncompliance and its causes;

- The exact dates and times of noncompliance ;

- If not yet corrected the anticipated time the project will be brought back into compliance; and

- The corrective action taken or planned to reduce, eliminate and prevent reoccurrence.

If there has been an incident of non-compliance with COE Permits, then notify the Engineer immediately of the non-compliance.

Report spills of petroleum products or other hazardous materials to the Engineer and other agencies as required by law. Use the HMCP and SPCC Plan (if available) for contact information to report spills to regulatory agencies.

- Corrective Action and Maintenance of BMPs.

Implement maintenance as required by the CGP, SWPPP, and manufacturer’s specifications, whichever is more restrictive.

Implement corrective action:

- If an incident of non-compliance with the SWPPP, or CGP is identified;

- If an Inspection or the Engineer identifies the SWPPP or any part of the SWPPP is ineffective in preventing erosion, sedimentation or the discharge of pollutants;

- If a required BMP was not installed according to the SWPPP schedule or phasing, or was installed incorrectly, or was not installed according to the CGP Part 4.0;

- If a BMP is not operating as intended, has not been maintained in an effective operation condition, or is unable to effectively perform the intended function;

- If a prohibited discharge of pollutants, as specified in CGP Part 4.6, is occurring or will occur; or

- If there is accumulation of sediment or other pollutants, that is in or near any storm water conveyance channels, or that may enter a discharge point or storm sewer system. If there is accumulation of sediment or other pollutants that is being tracked outside the project zone.

Implement corrective actions so that they comply with the following time requirements:

- For conditions that are easily remedied (i.e. removal of tracked sediment, maintenance of control measure, or spill clean-up), initiate corrective action within 24 hours and complete as soon as possible;

- For all other conditions meet both requirements:

- Corrective action is completed in time to protect water quality; and

- Corrective action is completed no later than the Complete-by-Date that was entered in an Inspection Report (see Subsection 641-3.03.2 for more information).

If a corrective action is not implemented within the time requirements of this section, document the situation in the SWPPP, notify the Engineer and implement corrective action as soon as possible.

If a corrective action could affect a subcontractor, notify the subcontractor within three days of taking the corrective action. Require in your written subcontract, that subcontractors must notify the Contractor within 24 hours of becoming aware of a condition that requires a corrective action.

- Stabilization.

Stabilization may be accomplished using temporary or permanent measures.  Initiate stabilization of disturbed soils, erodible stockpiles, disposal sites, and of erodible aggregate layers so that all of the following conditions are satisfied:

- As soon as practicable;

- As soon as necessary to avoid erosion, sedimentation, or the discharge of pollutants; and

- As identified in the SWPPP.

Land may be disturbed and stabilized multiple times during a project. Coordinate work to minimize the amount of disturbed soil at any one time. Do not disturb more soil than you can stabilize with the resources available.

Temporarily stabilize from wind and water erosion portions of disturbed soils, portions of stockpiles, and portions of disposal sites, that are not in active construction. Temporary stabilization measures may require a combination of measures including but not limited to vegetative cover, mulch, stabilizing emulsions, blankets, mats, soil binders, non-erodible cover,  dust palliatives, or other approved methods.

When temporary or permanent seeding is required, provide a working hydro seeding equipment located within 100 miles of the project by road; with 1,000 gallon or more tank capacity, paddle agitation of tank, and the capability to reach the seed areas with an uniform mixture of water, seed, mulch and tackifier. If the project is located in an isolated community the hydro-seeder must be located at the project.

Before applying temporary or permanent seeding, prepare the surface to be seeded to reduce erosion potential and to facilitate germination and growth of vegetative cover. Apply seed and maintain seeded areas. Reseed areas where growth of temporary vegetative cover is inadequate to stabilize disturbed ground.

Apply permanent seed according to Sections 618 and 724, within the time periods allowed by the CGP and the contract, at locations where seeding is indicated on the plans and after land-disturbing activity is permanently ceased.

When installing a culvert or other drainage structure where stream bypass is not used, install temporary or permanent stabilization concurrently or immediately after placing the culvert or drainage structure in a manner that complies with the SWPPP, applicable project permits and prevents discharge of pollutants. Install temporary and permanent stabilization:

- At the culvert or drainage structure inlet and outlet; and

- In the areas upstream and downstream that may be disturbed by the process of installing the culvert, culvert end walls, culvert end sections, or drainage structure.

Before deactivating a stream bypass or stream diversion used for construction of a bridge, culvert, or drainage structure, install permanent stabilization:

- At the inlet and outlet of the culvert, drainage structure, or bridge;

- In the area upstream and downstream of the culvert, drainage structure, or bridge, that is disturbed during installation or construction of the culvert, drainage structure, or bridge; and

- Under the bridge.

Within seven days of initiating final stabilization, either complete final stabilization or continue maintenance of work until final stabilization is complete.

- Ending CGP Coverage and BMP Maintenance.

The Engineer will determine the date that all the following conditions for ending CGP coverage have been met within the Project Zone:

- Land disturbing activities have ceased;

- Final Stabilization has been achieved (including at Department furnished material sources, disposal sites, staging areas, equipment areas, etc.); and

- Temporary BMPs have been removed.

After the Engineer has determined the conditions for ending CGP coverage have been met, the Department will:

- Send written notice to the Contractor with the date that the conditions were met;

- Submit an eNOT to ADEC; and

- Provide a copy of the eNOT and ADEC’s acknowledgement letter to the Contractor.

The Contractor is responsible for ending permit coverage within the Project Zone, by submitting an eNOT to ADEC within 30 days of meeting the conditions for ending CGP coverage. The Contractor is responsible for BMP maintenance and SWPPP updates until permit coverage is ended.

If the Contractor’s CGP eNOI acreage includes Support Activities and any other areas where the Department is not an Operator, the Contractor may not be able to file an eNOT at the same time as the Department.  In this case, the Contractor must amend the SWPPP and separate SWPPP2(s), to indicate the Department’s CGP coverage has ended, and the Department is no longer an Operator within the Project Zone.

The Contractor must indicate in the SWPPP the areas that have reached Final Stabilization, and the dates land disturbing activities ended and Final Stabilization was achieved. The Contractor must submit an eNOT to ADEC, and insert copies of the Department’s and the Contractor’s eNOTs with ADEC’s acknowledgement letters in the appendix of the SWPPP.

The Contractor must submit a copy of each signed eNOT and ADEC’s acknowledgement letter to the Department within three days of filing the eNOT or receiving a written response.

The Contractor is responsible for coordinating local government inspections of work and ending permit coverage with local government. See Subsection 641-1.03.5 for more information.

7.	Transmit final SWPPP.

Transmit one copy of the final SWPPP, including all amendments, appendices and maps, to the Engineer; when the project eNOTs are filed, or within 30 days of the Department’s eNOT being filed, whichever is sooner. Transmittal must be by both electronic and hard copy.

641-3.02 SWPPP DOCUMENTS, LOCATION ON-SITE, AVAILABILITY, AND RECORD RETENTION.

The SWPPP and related documents maintained by the Contractor are the Record for demonstrating compliance with the CGP and the Consent Decree. Copies of SWPPP documents transmitted to the Engineer under the requirements of this specification are informational and do not relieve the Contractor’s responsibility to maintain complete records as required by the CGP and this specification.

Keep the SWPPP, HMCP and SPCC Plan at the on-site project office. If there is not an on-site project office, keep the documents at a locally available location that meets CGP requirements and is approved by the Engineer. Records may be moved to another office for record retention after the eNOTs are filed. Records may be moved to another office during winter shutdown.  Update on-site postings if records are relocated during winter shutdown. Provide the Department with copies of all Records.

Retain Records and a copy of the SWPPP, for at least three years after the date of eNOT. If EPA or ADEC inspects the project,  issues a Notice of Violation (NOV), or begins investigation for a potential NOV before the retention period expires, retain the SWPPP and all Records related to the SWPPP and CGP until at least three years after EPA and/or ADEC has determined all issues related to the investigation  are settled.

The SWPPP and related documents must be made available for review and copy, to the Department and other regulatory agencies that request them.  See CGP Parts 5.10, 6.6 and 9.4.

641-3.03 SWPPP INSPECTIONS, AMENDMENTS, REPORTS, AND LOGS.

Perform Inspections, prepare Inspection Reports, and prepare SWPPP Amendments in compliance with the SWPPP and the CGP.  Update SWPPP Corrective Action Log, SWPPP Amendment Log, SWPPP Grading and Stabilization Activities Log, and SWPPP Daily Record of Rainfall forms. For active projects update the Records daily.

- Inspection during Construction.

Conduct Inspections according to the schedule and requirements of the SWPPP and CGP.

Inspections required by the CGP and SWPPP must be performed by the Contractor’s SWPPP Manager and the Department’s Stormwater Inspector jointly, unless impracticable. For this paragraph, “impracticable” means when both inspectors must fly to a remote area in the winter or when one inspector is sick or unable to travel to the site due to weather.  When this is the case, the Operator who conducts the Inspection must provide a copy of the Inspection Report to the other Operator within three days of the Inspection date and document the date of the report transmittal.

- Inspection Reports.

Use only the DOT&PF SWPPP Construction Site Inspection Report, Form 25D-100 to record Inspections. Changes or revisions to Form 25D-100 are not permitted; except for adding or deleting data fields that list: Location of Discharge Points, and Site Specific BMPs. Complete all fields included on the Inspection Report form; do not leave any field blank.

Unless otherwise directed by the Engineer, insert a Complete-by-Date for each corrective action listed that complies with:

a.	In time to protect water quality;

b.	less than seven calendar days after the date the inspection was performed; and

c.	before the next scheduled inspection.

Provide a copy of the completed, unsigned Inspection Report to the Engineer by noon on the day following the inspection.

The Superintendent must review, correct errors, and sign and certify the Inspection Report, within three days of the date of Inspection. The Engineer may coordinate with the Superintendent to review and correct any errors or omissions before the Superintendent signs the report. Corrections are limited to adding missing information or correcting entries to match field notes and conditions present at the time the Inspection was performed. Deliver the signed and certified Inspection Report to the Engineer on the same day the Superintendent signs it.

The Engineer will sign and certify the Inspection Report and will return the original to the Contractor within three working days.

The Engineer may make corrections after the Superintendent has signed and certified the Inspection Report. The Engineer will initial and date each correction. If the Engineer makes corrections, the Superintendent must recertify the Inspection Report by entering a new signature and date in the white space below the original signature and date lines. Send a copy of the recertified Inspection Report to the Engineer on the day it is recertified.

If subsequent corrections to the certified Inspection Report are needed, document the corrections in an addendum that addresses only the omitted or erroneous portions of the original Inspection Report. The Superintendent and the Engineer must both sign and certify the addendum.

- Inspection before Seasonal Suspension of Work.

Conduct an Inspection before seasonal suspension of work to confirm BMPs are installed and functioning according to the requirements of the SWPPP and CGP.

- Reduced Inspection Frequencies.

Conduct Inspections according to the inspection schedule indicated in the approved SWPPP.  Any change in inspection frequency must be approved by the Engineer, and beginning and ending dates documented as an amendment to the SWPPP.

Inspection frequency may be reduced to at least one Inspection every 30 days if approved by the Engineer and the entire site is temporarily stabilized.

When work is suspended due to freezing conditions, the Engineer may suspend inspection requirements after fourteen days of freezing conditions if:

a.	Soil disturbing activities are suspended; and

b.	Soil stabilizing activities are suspended.

Inspections must resume according to the normal inspection schedule identified in the SWPPP, at least 21 days before anticipated spring thaw.

The Engineer may waive requirements for updating the Grading and Stabilization Activities Log and Daily Record of Rainfall during seasonal suspension of work.  If so, resume collecting and recording weather data on the Daily Record of Rainfall form one month before thawing conditions are expected to result in runoff.  Resume recording land disturbance and stabilization activities on the Grading and Stabilization Activities Log when Construction Activity resumes.

- Stabilization before Seasonal Thaw.

Construction Activities within the Project Zone must be stabilized with appropriate BMPs prior to seasonal thaw. Seasonal thaw is the annual (first) recurrence of snow and ice melting after a prolonged period of freezing conditions.

- Inspection before Project Completion.

Conduct Inspection to ensure Final Stabilization is complete throughout the Project, and temporary BMPs that are required to be removed are removed. Temporary BMPs that are biodegradable and are specifically designed and installed with the intent of remaining in place until they degrade, may remain in place after project completion.

- Items and Areas to Inspect.

Conduct Inspections of the areas required by the CGP and SWPPP.

- SWPPP Amendments and SWPPP Amendment Log.

The Superintendent and the SWPPP Manager are the only persons authorized to amend the SWPPP and update the SWPPP Amendment Log, Form 25D-114. The Superintendent or the SWPPP Manager must sign and date amendments to the SWPPP and updates to the SWPPP Amendment Log.

SWPPP Amendments must be approved by the Engineer.

Amendments must occur:

- Whenever there is a change in design, construction operation, or maintenance at the construction site that has or could cause erosion, sedimentation or the discharge of pollutants that has not been previously addressed in the SWPPP;

- If an Inspection identifies that any portion of the SWPPP is ineffective in preventing erosion, sedimentation, or the discharge of pollutants;

- Whenever an Inspection identifies a problem that requires additional or modified BMPs

- Whenever a BMP is modified during construction, or a BMP not shown in the original SWPPP is added;

- If the Inspection frequency is modified (note beginning and ending dates); or

- When there is a change in personnel who are named in the SWPPP, according to Subsection 641-2.01.4.

Do not record removal of BMPs as amendments to the SWPPP. See Subsection 641-3.03.9 for documenting removal of BMPs.

Amend the SWPPP narrative as soon as practicable after any change or modification, but in no case, later than seven days following identification of the need for an amendment.  Every SWPPP Amendment must be signed and dated. Cross-reference the amendment number with the Corrective Action Log or SWPPP page number, as applicable. When a BMP is modified or added, describe the BMP according to Subsection 641-2.01.3.

Keep the SWPPP Amendment Log current. Prior to performing each scheduled Inspection, submit to the Engineer a copy of the pages of the Amendment Log that contain new entries since the last submittal. Include copies of any documents amending the SWPPP.

Keep the SWPPP Amendment Log as an appendix to the SWPPP.

9.	Site Maps.

Document installation, routine maintenance, and removal of BMPs by making notes on the SWPPP Site Maps. Include the date and the recording person’s initials by these notes. Identify areas where Construction Activities begin, areas where Construction Activities temporarily or permanently cease, and areas that are temporarily or permanently stabilized.

10. Corrective Action Log.

The Superintendent and SWPPP Manager are the only persons authorized to make entries on the SWPPP Corrective Action Log, Form 25D-112. Document the need for corrective action within 24 hours of either:

- Identification during an inspection; or

- Discovery by the Department’s or Contractor’s staff, a subcontractor, or a regulatory agency inspector.

Modification or replacement of a BMP, installation of a new BMP not shown in the original SWPPP, or overdue maintenance (after sediment accumulated in sediment basins (including sediment traps and ponds) exceeds 50% of design capacity; or after sediment accumulates to more than half the above ground height on silt fences, check dams, or berms) is a corrective action and must be documented on the Corrective Action Log. Do not record removal of BMPs on the Corrective Action Log.

Within 24 hours of discovery, update the Corrective Action Log with the date of discovery and proposed corrective action. If discovered during an inspection, update log with inspection date and proposed corrective actions noted on the Inspection Report.

After the corrective action has been accomplished, note in the Corrective Action Log the action taken and if a SWPPP amendment was needed. Date and initial the entry.

Keep the Corrective Action Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection.

Keep the Corrective Action Log as an appendix to the SWPPP.

11. Grading and Stabilization Activities Log.

The Superintendent and SWPPP Manager are the only persons authorized to date and initial entries on the SWPPP Grading and Stabilization Activities Log, Form 25D-110. Use the SWPPP Grading and Stabilization Activities Log, to record land disturbance and stabilization activities.

Keep the Grading and Stabilization Activities Log current and submit a copy to the Engineer prior to performing each scheduled SWPPP Inspection. Keep the Grading and Stabilization Activities Log organized and completed to demonstrate compliance with the CGP Part 4.4.

Keep the Grading and Stabilization Activities Log as an appendix to the SWPPP.

12. Daily Record of Rainfall.

Use SWPPP Daily Record of Rainfall, Form 25D-115, to record weather conditions at the Project.  Update the form daily and include the initials of the person recording each day’s entry.  Submit a copy to the Engineer prior to performing each scheduled Inspection.  Keep the Daily Record of Rainfall as an appendix to the SWPPP.

641-3.04 FAILURE TO PERFORM WORK.

The Engineer has authority to suspend work and withhold monies, for an incident of non-compliance with the CGP, Consent Decree or SWPPP, that may endanger health or the environment or for failure to perform work related to this Section 641. If the suspension is to protect workers, the public, or the environment from imminent harm, the Engineer may orally order the suspension of work. Following an oral order of suspension, the Engineer will promptly give written notice of suspension. In other circumstances, the Engineer will give the Contractor written notice of suspension before suspension of work. A notice of suspension will state the defects or reasons for a suspension, the corrective actions required to stop suspension, and the time allowed to complete corrective actions. If the Contractor fails to take the corrective action within the specified time, the Engineer may:

- Suspend the work until corrective action is completed;

- Withhold monies due the Contractor until corrective action is completed;

- Assess damages or equitable adjustments against the Contract Amount; and

- Employ others to perform the corrective action and deduct the cost from the Contract amount.

Reasons for the Engineer to take action under this section include, but are not limited to, the Contractor’s failure to:

- Obtain appropriate permits before Construction Activities occur;

- Perform SWPPP Administration;

- Perform timely Inspections;

- Update the SWPPP;

- Transmit updated SWPPP, Inspection Reports, and other updated SWPPP forms  to the Engineer;

- Maintain effective BMPs to control erosion, sedimentation, and pollution in accordance with the SWPPP, the CGP, and applicable local, state, and federal requirements;

- Perform duties according to the requirements of this Section 641; or

- Meet requirements of the CGP, SWPPP, or other permits, laws, and regulations related to erosion, sediment, or pollution control.

No additional Contract time or additional compensation will be allowed due to delays caused by the Engineer’s suspension of work under this subsection.

641-3.05 ACCESS TO WORK.

The Project, including any related off-site areas or support activities, must be made available for inspection, or sampling and monitoring, by the Department and other regulatory agencies. See CGP Part 6.6.

641-4.01 METHOD OF MEASUREMENT.

Item 641(6) will be measured on a contingent sum basis with withholding determined by the Department.

- ABLE 641-1 BMP VALUES

Liquidated Damages assessed according to Table 641-2 are not an adjustment to the Contract amount. These damages charges are related to Contract performance but are billed by the Department independent of the Contract amount. An amount equal to the Liquidated Damages may be withheld for unsatisfactory performance, from payment due under the Contract, until the Contractor remits payment for billed Liquidated Damages.

- TABLE 641-2 Version B

EROSION, SEDIMENT AND POLLUTION CONTROL – LIQUIDATED DAMAGES

| Code | Specification Subsection Number and Description | Deductable Amount in Dollars | Cumulative Deductable Amounts in Dollars |
| --- | --- | --- | --- |
| A | 641-1.04 Failure to have a qualified (AK-CESCL or equivalent) Superintendent or SWPPP Manager | Calculated in Code B or F |  |
| B | Failure to meet SWPPP requirements of: - 641-2.01.1 Name of SWPPP Preparer and Date of Pre-Construction Inspection - Not Applicable - 641-3.03.8 Sign and Date SWPPP amendments with qualified person. 641-2.01.4 SWPPP Include approving person’s name and AK-CESCL expiration date. (4) 641-3.02 Records maintained at project and made available for review | $750 per omission |  |
| C | 641-2.01.3 and 641-303.8 Failure to either reference a BMP manual or publication, or state that no BMP manual or publication was used | $250 per omission |  |
| D | 641-3.03.5 Failure to stabilize a Project prior to Seasonal Thaw | $5,000 per Project per year |  |
| E | 641-2.01.1 Failure to conduct pre-construction inspections before Construction Activities | $2,000 per Project |  |
| F | 641-3.03. Failure to conduct and record CGP Inspections 641-3.03.1 Personnel conducting Inspections and Frequency 641-3.03.2 Inspection Reports, use Form 25D-100, completed with all required information according to the Consent Decree paragraph 7.c, parts (1) through (11) | $750 per Inspection |  |
| G | 641-3.01.4 Failure to timely accomplish BMP maintenance and/or repairs, In effect until BMP maintenance and/or repairs is completed. | $500 per Project per day | Not to exceed $250,000 per year for all projects |
| H | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely oral endangerment report of violations or for a deficient oral endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |
| I | 641-3.01.3 Failure to provide to the Engineer and ADEC a timely written endangerment report of violations or for a deficient written endangerment report | $750 for the first day the report is late or deficient | Additional $750 for every 14 day period without the required information |

641-5.01 BASIS OF PAYMENT. See Subsection 641-3.04 Failure to Perform Work, for additional work and payment requirements.

Item 641(6) Withholding. The Engineer may withhold an amount equal to Liquidated Damages, assessed according to Section 641, from payment due the Contractor. Liquidated Damages for violations of the Contract, CWA, CGP, or Consent Decree are determined by the Engineer according to Table 641-2. The Engineer may withhold payment due the Contractors until the Contractor pays the Liquidated Damages to the Department.

The Department will not release performance bonds until Liquidated Damages assessed according to Section 641 are paid to the Department, and all requirements according to Subsection 103-1.05 are satisfied.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(6) Withholding | Contingent Sum |

## SECTION 642

## CONSTRUCTION SURVEYING AND MONUMENTS

642-1.01 DESCRIPTION. Perform surveying and staking essential for the completion of the project and perform the necessary calculations required to accomplish the work in conformance with the Plans and Specifications and standard engineering and survey practice.

Furnish and install survey monuments and monument cases in conformance with the Plans or as directed.

- Adjust existing monuments and monument cases to conform to the new elevations.

642-1.02 DEFINITIONS.

1.	Monument: A fixed physical object marking a point on the surface of the earth; used to commence or control a survey; mark the boundaries of a parcel of land; or the centerline of a right-of-way corridor. Monuments will be Primary or Secondary, as shown on the Plans.

2.	Point: An identified spot located on the surface of the earth. For purposes of this definition, a point can be a PK nail, wooden hub, rebar, large nail or other structure capable of being utilized as a marker.

3.	Witness Corner: A material mark or point usually placed on a property or survey line, at a known distance from a property corner or other survey point. A witness corner is employed to witness the location of a corner/point that cannot be monumented at its true location.

4.	Reference Monument: A material mark or point placed at a known distance and direction from a property corner or other survey point, usually not on a property or survey line. A reference monument is employed to perpetuate a corner/point that cannot be monumented at its true location or where the corner monument is subject to destruction.

5.	Surveyor: The Contractor’s Professional Land Surveyor, currently registered in the State of Alaska.

642-2.01 MATERIALS.

1.	Monument Cases: Use castings meeting AASHTO M 105, Class No. 30A. Coat castings with a bituminous damp-proof coating. Use tops that bear evenly on the frames.

- Primary Monument: A minimum 2-inch diameter nonferrous pipe at least 30 inches long, with a minimum 4-inch flange at the bottom and having magnets attached at the top and bottom. A minimum 2-3/8 inch diameter nonferrous metal cap must be permanently attached to the top. Mark the cap around the outside edge with the words “STATE OF ALASKA DOT&PF". Permanently stamp every monument with the Surveyor’s registration number, the year set, and the point/corner identification. Orient cap so that the data may be read when the reader is facing north, except for centerline monuments that will be oriented to be read facing up-station.

- Secondary Monument: A minimum 5/8 inch x 30 inches rebar with a 2-inch aluminum cap attached to the top. Permanently stamp every secondary monument with the Surveyor’s registration number, the point/corner identification, and the year set.

4.	Digital Measuring Instrument: Nu-metrics, Nitestar DMI (www.ae-traffic.com)

- CONSTRUCTION REQUIREMENTS

642-3.01 GENERAL. Use competent, qualified personnel and suitable equipment for the layout work required and furnish traffic control, stakes, templates, straight-edges and other devices necessary for establishing, checking and maintaining the required points, lines and grades.

Furnish computer services to accomplish the work. Check data received from the computer for completeness and accuracy. As soon as practical after completion of the work, and in no case later than acceptance of the project, deliver field books, computer forms and computer output data to the Engineer. This data becomes the property of the Department.

Supervise construction surveying personnel. Correct errors resulting from the operations of said personnel at your expense. The Contractor is responsible for the accuracy of the work.

Work classified as Land Surveying under AS 08.48, and work involving the location, control, and monumentation of construction centerline and right-of-way, must be performed by or under the responsible charge of a Professional Land Surveyor.

- Follow the Department’s Construction Surveying Requirements.

The Department will provide sufficient centerline or reference thereto, and at least 2 benchmarks per mile to enable the establishment of planned elevations and centerline.

Keep field notes in standard hardbound notebooks in a clear, orderly, and neat manner consistent with Departmental procedures, including titles, numbering, and indexing. Make field books available for inspection by the Engineer’s project personnel at any time. Store the field books in the Engineer’s Project Office during periods of non-use.

Perform the following:

1.	Staking necessary to delineate clearing and/or grubbing limits.

2.	Cross sections necessary for determination of excavation and embankment quantities, including intermediate and/or remeasure cross sections as needed. Take cross sections after clearing and grubbing has been completed.

3.	Slope staking.

4.	Staking of signs, culverts, minor drainage structures and other appurtenances, including the necessary checking to establish the proper location and grade to best fit the conditions on site.

5.	Bridge staking.

6.	Setting finishing stakes.

7.	Measurement of pay quantities that require measurement.

8.	Staking of right-of-way and material source limits.

9.	Staking, referencing and other actions required to preserve or restore land monuments and property corners.

- Other surveying and staking necessary to complete the project.

- Before work on the Project starts, stake and reference the existing centerline on both sides of the roadway alignment. Stake the existing centerline on tangents at 100 foot, and 50 foot intervals on curves from the beginning and ending of super-elevation changes when the roadway is no longer at normal crown. Stake sign locations at proper offset. Stakes shall be a minimum of 1 inch x 2 inch x 2 feet and be offset 4 to 8 feet from the shoulder on both sides of the roadway. Extend lath stakes a minimum of 2 feet above ground. Show the offset distance to centerline and the station from the beginning of the project. Maintain staking until the final roadway striping is completed. Staking accuracy work requires an electronic distance measuring instrument (DMI) be installed in the Contractor's vehicle. Calibrate the DMI to roadway alignments as stationed in the Plans before beginning work. Record the calibration and staking information in the field book.

Install a reference sign every 500 feet. These reference signs shall meet the following requirements:

- mounted with the base a minimum of 5 feet above the shoulder,

- located a minimum of 10 feet from the edge of shoulder,

- marked with the station from the beginning of the project, in 6 inch high permanent black lettering with a letter proportion height to width ration of 1:0.6 and a stroke width to height ratio of 1:6, on an orange background.

12.	Document the Station at the beginning and ending of existing passing zones before work that will remove or obliterate the existing striping. Measure, as outlined below, sight distance for passing zones after the base course layer or pavement milling has been accepted. Use Table 642-1 to establish Minimum Passing Sight Distance. Move forward alongside the centerline or edge of traveled way in order to spot check and discover locations where the Minimum Passing Sight Distance drops below what is required for 10 MPH over the posted speed limit. Record the sight distance for each station location that falls below the posted speed limit plus 10 MPH. Continue to record the sight distance for each station location until the sight distance drops below what is required for the posted speed limit.  Stations observed to exceed the values required for posted speed limit plus 10 MPH are not required to be recorded.  If recorded mark them as "Pass" or "+." Mark stations observed to fall below the values required for the posted speed limit as “Fail” or “-.”

Measure from the roadway edge of traveled way, using a 3.5 feet object height (or “instrument height”) at 100 foot station marks looking ahead to a 3.5 foot target height at the edge of traveled way for opposing traffic. Provide a list of each station result for each direction of travel along the roadway edge of traveled way. Certify and record the results on standard “letter” sized paper and provide a copy to the Engineer at least 14 days before laying out final pavement markings.

The Engineer will forward one copy of the existing and proposed sight distance measurements on the form provided herein, to the Regional Traffic Engineer. Table 642-1 does not automatically ensure passing striping will be provided. The Regional Traffic Engineer’s office will take up to 14 days to review and approve pass/no pass striping against operating speeds for the roadway before installation, using Table 642-1 and the Alaska Traffic Manual as a guide. No passing striping zones shall be at least 500 feet in length. Passing striping shall be no less than 400 feet minimum and long enough to meet the distances in Table 642-1. Establish no passing zones at all at-grade railroad crossings. Passing striping will not extend into a segment of road without minimum sight distance.

- TABLE 642-1

PASSING SIGHT DISTANCE

| Operating Speed (mph) | Minimum Passing Sight Distance (ft) |
| --- | --- |
| 25 | 450 |
| 30 | 500 |
| 35 | 550 |
| 40 | 600 |
| 45 | 700 |
| 50 | 800 |
| 55 | 900 |
| 60 | 1000 |
| 65 | 1100 |
| 70 | 1200 |

- Passing Sight Distance Survey Table.

- ROAD NAME:

Stationing:  From  	  	To

Surveyor:  			Date:

| Project Station | Posted Speed Limit | Direction of Travel | Sight Distance Ahead | Existing Striping: Pass or No-Pass | Engineer's Striping Requirement |
| --- | --- | --- | --- | --- | --- |

Other Notes:

1.

2.

3.

4.

5.

Accepted By:  				  Date:

DOT/PF Project Engineer

When the Department has not established the project centerline points but the survey control points were established as a part of the Department’s Preconstruction surveys (as detailed on the project Survey Control Sheet) recover these points and use them as the basis for establishing the project centerline. Verify the position of these points and establish new points where required to replace missing points, before clearing, grubbing, or excavation.

Notify the Engineer immediately if a Department-established reference point is discovered to be in error or a reset point is not in harmonious relationship to the adjacent centerline points.

Furnish a notekeeper to record field survey notes, including  documentation for quantity computations for payment.  Ensure that the notekeeper is thoroughly familiar with generally accepted standards of good survey notekeeping practice and the Department’s Construction Surveying Requirements.

The Engineer may randomly spot check surveying, staking and computations. After the survey or staking has been completed, provide the Engineer with a minimum of 72 hours notice before performing work, and furnish the appropriate data, to allow for random spot checking.  The Department assumes no responsibility for the accuracy of the work.

642-3.02 CROSS-SECTION SURVEYS. When required, obtain right-angle cross sections to the construction centerline at the interval detailed in the Department’s Construction Surveying Requirements.

The Department will supply following:

1.	Construction Plans and Specifications

2.	Design Cross Sections, if any

3.	State of Alaska Land Survey Monument Record forms

4.	Department’s Construction Surveying Requirements (one copy)

5.	Design centerline grades, unless Item 642(2), Office Engineering is used

Perform the following:

- Furnish hardbound field books (Level, Cross-Section, Slope Stake, etc. ). Use “Rite-in-the-Rain” or similar weather resistant books. Field books become the property of the Department upon completion of the work.

- Label the books and number the pages. Make a heading in the appropriate book (date, weather, names and duties of crew members) at the beginning of each day's work.

- Update the index of the appropriate book at the end of each day's work.

- Reduce, check, and adjust level notes.

- The notekeeper shall compute the cross-section level notes and slope stake catches and a different crew member shall check the computation on a continual basis in the field.

- Enter the grade data, shoulder width and/or ditch distance, stationing, slope, etc., in the slope stake books.

- Maintain the position and identifying marks of slope stakes and reference points until used for their intended purpose.

- Correct errors by drawing a line through them and writing the correct entry directly above. Erasures are not allowed.

- Return field books or copies of the field books to the Project office at the end of each work day or as directed.

- Provide copies of grade sheets and temporary bench mark elevations to the Engineer 48 hours before beginning work on unclassified excavation or embankment.

- Ensure that survey crews comply with approved traffic control plans. Coordinate crews activities with the Worksite Traffic Supervisor.

- Keep a daily survey Party Chief diary, and give a copy of the diary to the Engineer each day. The diary shall contain the following information:

a.	Date

b	Weather

c.	Crew members’ names and duties

d. 	Type and location of work performed

e. 	Hours worked

f. 	Type of equipment used (brand) and date equipment was double centered or “peg” test was performed

g. 	Signature of person in responsible charge

- Submit the survey field notes for the specific area, relating to monument referencing, before beginning clearing, grubbing, or excavation.

642-3.03 MONUMENTS. Install primary and secondary monuments, as called for in the Plans, at the positions determined by the Department. Reference property markers/corners, monuments, or accessories that may be disturbed or buried during construction. Prepare and record Monument Record Forms in the appropriate Recorder’s Office before disturbing monuments. Monument Record Forms may be obtained from the Engineer. Reestablish monuments in their original position before completion of the project. Prepare and file a Monument Record Form for each reestablished monument.

Keep records and report to the Engineer evidence that a monument has been disturbed and is no longer reliable or cannot be located and is presumed to be lost or obliterated. Establish a minimum of two in-line reference points, or three swing-tie reference points in situations where in-line referencing is not desirable.  Set reference points outside of the construction limits. Measure distances from the monument to the nearest 0.01 foot. Record referencing of monuments in a separate field book stamped by the Surveyor.

Replace existing monuments disturbed by construction with Primary or Secondary Monuments meeting the requirements of subsection 642-2.01. When it is impractical to establish a monument in its original position, install a witness corner (WC). Place the WC to a property corner on the property line when the other property corner that defines said line is existing or there has been sufficient retracement to define said line. In other cases, place a reference monument (RM) perpendicular to the centerline at the station of the original position and at a distance from the original position measured in whole feet.

Replacing monuments not shown on the Plans will be considered additional work and paid by 642(3), Three Person Survey Party. Those monuments found that are not shown on the Plans will be recognized by the Department when the Surveyor provides timely field notes identifying type and location of the monument, and a description of the point the monument marks, with the reason to preserve its location.

The Surveyor must complete and stamp a State of Alaska Land Survey Monument Record form for each primary and secondary monument removed, installed, relocated, or replaced. Provide the required survey information on the form in accordance with statutory requirements, including section, township, and range. Meet requirements for recording at the District Recorder’s Office in which the project is located for each monument record. Deliver conforming copies of the recorded forms to the Engineer before monument removal or disturbance and after setting any final monuments requiring monument records.

Set each monument and monument case accurately to lines established at the required location and in a manner as to ensure being held firmly in place. Set existing monuments and monument cases to be adjusted to new elevations in the manner and at the elevations directed.

642-3.04 OFFICE ENGINEERING. Calculate finish grades for the roadway as specified according to Plans and/or Specifications. Use information available in the field, on as-builts, or as provided by the Engineer. Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.

642-3.05 FINAL TRAVERSE. Within 30 days after the Engineer receives a letter stating that construction activities that may disturb the monuments have ceased, the Surveyor shall run a final closed traverse to verify the positional accuracy of installed survey monuments. Begin and end this traverse at different Department-provided control points. Tie into the traverse the primary and secondary monuments placed or replaced and undisturbed Department-provided control points. Do not run the final traverse more than 2.5 miles without a tie to a Department-provided monument/control point. Meet the requirements of a secondary monument for traverse points established during this work. Have the Surveyor sign and stamp a letter that lists each monument and its coordinates and certify that the monuments are each located within 0.2 feet of their proposed position based on the project survey control points provided by the Department. Deliver the certification letter and field notes for this work to the Engineer.

## SECTION 643

## TRAFFIC MAINTENANCE

643-1.01 DESCRIPTION. Protect and control traffic during the contract. Furnish, erect, maintain, replace, clean, move and remove the traffic control devices required to ensure the traveling public’s safety. Perform all administrative responsibilities necessary to implement this work.

Maintain all roadways and pedestrian and bicycle facilities affected by the work in a smooth and passable condition. Construct and maintain approaches, crossings, intersections, and other necessary features throughout the project for the life of the contract.

Illuminate construction activities listed in Table 643-2 during hours of night work on roads open to the public within project limits.

643-1.02 DEFINITIONS.

ATM. When used in this Section, ATM stands for the Alaska Traffic Manual, which is the MUTCD with Alaska Supplement.

Balloon Light: Light surrounding by a balloon-like enclosure kept inflated by pressurized air or helium, and producing uniform light through 360 horizontal degrees.  The  top  half  of  the  balloon  enclosure  shall  be  constructed  of  an opaque material.

Construction Phasing Plan. A plan for each phase of the project showing how you will accommodate traffic. Show the sequence of work by segment or phase, if required.

- Night Work: Work occurring between sunset and sunrise on all days except the

“No Lighting Required” period shown in the table below:

- TABLE 643-1

LIGHTING REQUIREMENTS

| Latitude (degrees) | No Lighting Required |  | Cities |
| --- | --- | --- | --- |
|  | Start | End |  |
| 61 | June 11 | July 1 | Anchorage, Valdez, Girdwood |

Traffic. The movement of vehicles, pedestrians, and bicyclists through road construction, maintenance operations, utility work, or similar operations.

Traffic Control Plan (TCP). A drawing or drawings indicating the method or scheme for safely guiding and protecting motorists, pedestrians, bicyclists, and workers in a traffic control zone. The TCP depicts the traffic control devices and their placement and times of use.

Traffic Control Zone. A portion of a road construction project, maintenance operation, utility work or similar operation that affects traffic and requires traffic control to safely guide and protect motorists, pedestrians, bicyclists, or workers.

643-1.03 TRAFFIC CONTROL PLAN. Implement an approved TCP before beginning work within the project limits.

The TCP includes, but is not limited to, signs, barricades, traffic cones, plastic safety fence, sequential arrow panels, portable changeable message board signs, special signs, warning lights, portable concrete barriers, crash cushions, flaggers, pilot cars, interim pavement markings, temporary lighting, temporary roadways and all other items required to direct traffic through or around the traffic control zone according to these Specifications and the ATM. Address in the TCPs placement of traffic control devices, including location, spacing, size, mounting height and type. Include code designation, size, and legend per the ATM and the ASDS.

When a TCP is included in the Plans, use it, modify it, or design an alternative TCP. When a TCP is omitted from the Plans, provide one according to this Section and the ATM.

Submit new or modified TCPs to the Engineer for approval. Allow 1 week for the Engineer to review any TCP or each subsequent correction. You may change an approved TCP during construction provided you allow 48 hours for review and the Engineer approves the changes.

Certify by signature of the Worksite Traffic Supervisor that all TCPs conform with the ATM and Specifications. The Engineer will not accept the TCP without Worksite Traffic Supervisor’s certification. Have your superintendent review and sign all TCPs before you submit them.

In all TCPs you submit, include the periods for which the TCP will be in effect. Provide the name and 24-hour telephone number of the Worksite Traffic Supervisor.

The TCPs, Plans, and Standard Drawings show the minimum required number of traffic control devices. If unsafe conditions occur, the Engineer may require additional traffic control devices.

A waiver may be requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing. If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan. Maintain a minimum12 foot lateral separation between the nonstreet legal vehicles and the motoring public. The Traffic Control plan shall specify the traffic control devices required for these operations.

Road Closures and Major Traffic Sequencing (events). Submit a written request to the Engineer for review and approval of each proposed event and event date. Allow 7 days for the Engineer to review any proposed event or subsequent changes/corrections. The proposed event date will be no less than 14 days from the date of written approval.

643-1.04 WORKSITE TRAFFIC SUPERVISOR. Provide a Worksite Traffic Supervisor responsible for maintaining 24-hour traffic operations.

- Qualifications. The Worksite Traffic Supervisor shall be knowledgeable and experienced regarding the requirements of the ATM and the implementation of those requirements. The Worksite Traffic Supervisor shall be familiar with the Plans, the Specifications, your proposed operations, and  certified as one of the following:

a.	Traffic Control Supervisor, American Traffic Safety Services Association (ATSSA)

b.	Work Zone Safety Specialist, International Municipal Signal Association (IMSA)

Certify according to Form 25D-105 that the Worksite Traffic Supervisor is competent and capable, and has the authority to perform the duties and responsibilities in accordance with this section.

Worksite Traffic Supervisors shall maintain current certification and be able to show their certification anytime they are on the project.

- Duties.

a.	Prepare the TCPs and public notices and coordinate traffic control operations between the Project Superintendent and the Engineer.

b.	Physically inspect the condition and position of all traffic control devices used on the project at least once each day and once each night.  Ensure that traffic control devices work properly, are clean and visible, and conform to the approved TCP.  Complete and sign a detailed written report of each inspection on the form provided by the Engineer within 24 hours.

c.	Supervise the repair or replacement of damaged or missing traffic control devices.

d.	Review and anticipate traffic control needs. Make available proper traffic control devices necessary for safe and efficient traffic movement.

e.	Review work areas, equipment storage, and traffic-safety material handling and storage.

f.	Hold traffic safety meetings with superintendents, foremen, subcontractors, and others as appropriate before beginning construction, prior to implementing a new TCP, and as directed. Invite the Engineer to these meetings.

g.	Supervise all traffic control workers, flaggers, and pilot car drivers.

h.	Certify that all flaggers are certified as required by Subsection 643-3.04.4.  Submit a copy of all flagger certifications to the Engineer.

- Authority. The Worksite Traffic Supervisor shall have the Contractor’s authority to stop work and implement immediate corrective action to unsafe traffic control, in locations where unsafe traffic control is present.

643-1.05 CONSTRUCTION PHASING PLAN. Submit a Construction Phasing Plan for approval no less than 5 working days prior to the preconstruction conference. Include the following:

1.	Name and 24-hour telephone numbers of the Worksite Traffic Supervisor. Also include their resume and written verification of their credentials.

2.	A plan for each phase or segment of the project.

3.	TCPs for the first phase of the project. Show permanent and temporary traffic control measures, including the times each TCP will be used.

- Submit any changes to the Engineer for approval 7 days before proposed implementation.

643-1.06 TRAFFIC MAINTENANCE SETUP. When shown on the bid schedule, Traffic Maintenance Setup items are site specific and are detailed as individual TCPs on the plan sheets. They depict the method or scheme required to route traffic safely and efficiently when any of the following restrictions occur:

1.	Lane Closure. The closure of one or more lanes on a roadway.

2.	Detour. The redirection of traffic through or around a traffic control zone.

3.	Road Closure. The closure of a roadway with or without a specified detour route.

4.	One Lane Road. A two-way roadway reduced to a single-lane roadway with flaggers, pilot cars, traffic signals, stop signs, or yield signs.

643-2.01 MATERIALS. Provide traffic control devices meeting the following requirements:

- Signs. Use signs, including sign supports, that conform to Section 615, the ATM, and ASDS.

  - Construction Signs: Regulatory, guide, or construction warning signs designated in the ASDS.

  - Permanent Construction Signs: As designated on the Plans or an approved TCP.

  - Special Construction Signs: All other signs are Special Construction Signs. Neatly mark the size of each sign on its back in 3-inch black numerals.

- Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 48 X 48 inch traffic control sign at the height above the adjacent roadway surface required by the ATM.

- Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 8 feet long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip each 10-foot section of barrier with at least two side-mounted retroreflective reflectors or a continuous 4-inch wide horizontal retroreflective stripe mounted 6 inches below the top of the barrier. Use yellow reflectors or stripe if you use barriers at centerline. Use white reflectors or stripe if you use barriers on the roadway shoulder. Use reflective sheeting that meets AASHTO M 268 Type III, IV or V.

- Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

- Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 28 inches high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

- Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

  - Paint meeting Subsection 708-2.03 with glass beads meeting Subsection 712-2.08,

  - Preformed Marking Tape (removable or non-removable) meeting Subsection 712-2.14, or

  - Temporary Raised Pavement Markers meeting Subsection 712-2.15 or 712-2.16, as appropriate.

- High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

- Temporary Crash Cushions. Must have FHWA Acceptance letter for NCHRP 350 or MASH Test Level 3. Use reflective sheeting that meets AASHTO M 268 Type III, IV or V. Application of crash cushion must be appropriate for the intended use and be installed per manufacturer’s recommendation. Temporary crash cushions used as rail or barrier end treatments must be redirective. Temporary crash cushions that are barrels or barricade filled with sand or water are considered nonredirective and may only be used when the forecasted temperature during their use is above 32 degrees Fahrenheit.

- Sequential Arrow Panels. Use Type A (24 X 48 inch), Type B (30 X 60 inch) or Type C (48 X 96 inch) panels that conform to the ATM.

- Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self-contained power supply for the sign and with the following features:

  - Message sign panel large enough to display 3 lines of 9 inch high characters

  - Eight character display per message line

  - Fully programmable message module

  - The capacity to create, preview, and display new messages and message sequences

  - A waterproof, lockable cover for the controller keyboard

  - An operator’s manual, a service manual, and a wiring diagram

  - Quick release attachments on the display panel cover

  - Variable flash and sequence rates

  - Manual and automatic dimming capabilities on lamp bulb matrix models

  - Locate the bottom of the sign panel at least 7 feet above the pavement

  - Operate with a battery pack a minimum of 2 hours under full load

- Plastic Safety Fence. Use 4 foot high construction orange fence manufactured by one of the following companies, or an approved equal:

- “Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

- “Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

- “Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

- Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

- Use plywood at least 1/2 inch thick for areas continuously supported by subgrade. Use plywood at least 1 inch thick for areas that are not continuously supported.

- Do not use unsupported 1-inch plywood longer than 30 inches.

- Use plywood with regular surfaces. Do not overlap plywood joints higher than 1 inch.

- Use a method that will withstand 25 mph wind velocities to hold temporary surfacing in place.

- Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 24 inches wide by 24 inches high sign panels, 8 inch Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM.  Use reflective sheeting that meets AASHTO M 268 Type VIII or IX. Use background colors of fluorescent orange on one side and red on the other side.

- Truck Mounted Attenuator, TMA. The TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight per the manufacturer’s recommendations. The TMA complies with NCHRP 350 Test Level 3 requirements.

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of National Cooperative Highway Research Program (NCHRP) Report 350 or the Manual for Assessing Safety Hardware (MASH) (Test Level 3) on the given schedule. Submit documentation of compliance to the Engineer before installing devices on the project.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |
| --- | --- | --- | --- |
| Category | Devices |  | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | Manufacturer's Certification for devices exceeding height and weight limits |  |
| 2 | Barricades, portable sign supports, drums w/lights, other devices weighing less than 100 pounds but not included in category 1 | FHWA acceptance letter indicating acceptance at Test Level 3 (when not test level is specified in the letter; it is implied that the tests were run for Test Level 3), |  |
| 3 | Truck mounted attenuators, redirective and nondirective temporary crash cushions | FHWA acceptance letter indicating acceptance at Test Level 3 (when no test level is specified in the letter; it is implied that the tests were run for Test Level 3), |  |
|  | Portable concrete barriers | FHWA acceptance letter specifying the Test Level required in the Plans or Specifications. |  |

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350 or MASH, Test Level 3. This certification may be a one-page affidavit signed by the vendor. Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization. No certification is required for devices within the weight and height limitations.

Device	Composition		Weight	Height

Cones	Rubber		20 lb.	36 in.

Plastic		20 lb.	48 in.

Candles	Rubber		13 lb.	36 in.

Plastic 		13 lb.	36 in.

Drums	Hi Density Plastic		77 lb.	36 in.

Lo Density Plastic		77 lb.	36 in.

Delineators	Plastic or Fiberglass	N/A	48 in.

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Keep the work, and portions of the project affected by the work, in good condition to accommodate traffic safely. Provide and maintain traffic control devices and services inside and outside the project limits, day and night, to guide traffic safely.

Unless otherwise provided in this Section, keep all roadways, business accesses, and pedestrian facilities within the project limits open to traffic. Obtain the Engineer’s approval before temporarily closing residential, commercial, or street approaches. Provide access through the project for emergency vehicles and school and transit buses. Properly sign and/or flag all locations where you must redirect or stop the traveling public.

Stop your equipment at all points of intersection with the traveling public unless an approved TCP shows otherwise.

Continue to operate all illumination and signalization according to the requirements of Subsection 660-3.09. When moving approach lanes, realign signal heads as necessary according to the ATM. Coordinate any modifications to existing traffic signals with the agency that maintains and operates them. Operate flood lighting at night according to the ATM. Adjust flood lighting so that it does not shine into oncoming traffic.

Provide and maintain safe routes for pedestrians and bicyclists through or around traffic control zones at all times, except when regulations prohibit pedestrians or bicyclists.

Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. Maintain business accesses during flagging operations.

Immediately notify the Engineer of any traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor becomes aware of the accident.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION. Obtain an approved TCP before reducing existing roadway lane and shoulder widths before starting construction. Maintain a clear area with at least 2 feet between the edge of traveled way and the work area. Use barricades, traffic cones, or drums to delineate this area. Place traffic control devices on the work side of the clear area. Space them according to the ATM.

If you are allowed to maintain traffic on an unpaved surface, conduct construction to provide a smooth and even surface that public traffic can use at all times. Properly crown the roadbed surface for drainage. Before beginning other grading operations, place sufficient fill at culverts and bridges to permit traffic to cross smoothly and unimpeded. Use part-width construction techniques when routing traffic through roadway cuts or over embankments under construction. Excavate the material or place it in layers. Alternate construction activities from one side to the other. Route traffic over the side opposite the one under construction.

You may detour traffic when the Plans or an approved TCP allows it. Maintain detour routes so that traffic can proceed safely. When detours are no longer required, obliterate the detour. Topsoil and seed appropriate areas.

If you cannot maintain two-way traffic on the existing roadway or detour, you may use half-width construction or a road closure if it is shown on an approved TCP. Make sure the TCP indicates closure duration and conditions. Schedule roadway closures so you do not delay school buses and peak-hour traffic. For road closures, post closure-start and road-reopen times at the closure site, within view of waiting traffic.

Pave lanes next to the median first. Pave lanes next to exit and entrance ramps last. Place a temporary 12:1 sloped wedge of asphalt concrete against the abrupt pavement edge on lanes next to exit and entrance ramps. Do not open the roadway to traffic until slope wedges are in place.

643-3.03 PUBLIC NOTICE. Make sure the Worksite Traffic Supervisor gives a minimum of 3 days notice before major changes, delays, lane restrictions, or road closures to local officials and transportation organizations, including but not necessarily limited to:

- Alaska Carriers Association

- Alaska Trucking Association

- Alaska State Troopers

- Division of Measurement Standards

- Local Police Department

- Local Fire Department

- Local Government Traffic Engineer

- School and Transit Authorities

- Local Emergency Medical Services

- Local Media (newspapers, radio, television)

- Railroads (where applicable)

- U.S. Postal Service

- Major Tour Operators

Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system. Provide notice as required by utility companies before repairing or replacing a utility.

Provide the Alaska State Troopers, local police and fire department with the radio frequencies used on the project and the 24-hour telephone numbers of the Worksite Traffic Supervisor and the Project Superintendent. Tell them to use these numbers to alert you when emergency vehicles must pass through the project. When notified of emergencies, use all equipment and make every necessary effort to expedite rapid passage.

Additional notices may be given through the Navigator System for selected projects. Check the special provisions for those requirements.

643-3.04 TRAFFIC CONTROL DEVICES. Before starting construction, erect permanent and temporary traffic control devices required by the approved TCPs. Use traffic control devices only when they are needed. The Engineer will determine advisory speeds when necessary.

For lane closures on multilane roadways, use sequential arrow panels. During hours of darkness when required by the approved TCP use flashing warning lights to mark obstructions or hazards and steady-burn lights for channelization.

Use only one type of traffic control device in a continuous line of delineating devices, unless otherwise noted on an approved TCP. Use drums or Type II barricades for lane drop tapers.

During non-working hours and after completing a particular construction operation, remove all unnecessary traffic control devices. Store all unused traffic control devices in a designated storage area which does not present a nuisance or visual distraction to traffic. If sign panels are post mounted and cannot be readily removed, cover them entirely with either metal or plywood sheeting. Completely cover signal heads with bags.

- Keep signs, drums, barricades, and other devices clean at all times.

Use only traffic control devices that meet the requirements of the “Acceptable” category in ATSSA (American Traffic Safety Services Association) “Quality Guidelines for Temporary Traffic Control Devices” and meet crashworthiness requirements per Section 643-2.02.

Immediately replace any devices provided under this Section that are lost, stolen, destroyed, inoperable or deemed unacceptable while used on the project. Stock repair parts for each Temporary Crash Cushion used on the project. Repair damaged crash cushions within 24 hours.

Maintain pre-existing roadside safety hardware at an equivalent or better level than existed prior to project implementation until the progress of construction necessitates removing the hardware. All existing hazards that are currently protected with roadside safety hardware or new hazards which result from project improvements shall be protected or delineated as required in the plans, specifications, and approved TCPs until permanent roadside safety hardware is installed. All temporary roadside safety hardware shall meet NCHRP 350 or MASH Test Level 3 unless otherwise noted.

- All items paid under this Section remain your property. Remove them after completing the project.

- Embankments. Install portable concrete barrier, plastic drums, barricades, tubular markers, plastic safety fence, and cones as specified on the Plans or TCPs to delineate open trenches, ditches, other excavations and hazardous areas when they exist along the roadway for more than one continuous work shift.

- Adjacent Travel Lane Paving. Limit pavement-edge and lane-edge drop-offs as specified in Section 401. When paving is deeper than 2 inches and you cannot finish paving adjacent travel lanes or paved shoulders to the same elevation before the end of the paving shift, install one of the following, as appropriate: CW24-1 (Uneven Lanes), CW8-9A (Low Shoulder), CW14-3 (No Passing Zone), R4-1 (Do Not Pass), and R4-2 (Pass with Care). If the section is longer than 1/2 mile, place additional signs every 1500 feet.

- Fixed Objects. Use flashing warning lights on all vehicles when they are working within 15 feet of the edge of traveled way. Use emergency flashers, flashing strobes or rotating beacons.

Locate private vehicles, idle construction equipment, construction material stockpiles and other items deemed by the Engineer to be fixed objects at least 30 feet from the edge of traveled way at all times. Do not park equipment in medians adjacent to active travelled way.

Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

If you cannot meet the preceding restrictions because of land features or lack of right-of-way, park equipment as far away as practical but at least 15 feet from the edge of traveled way, as approved by the Engineer. Use drums or Type II barricades with flashing warning lights to delineate parked equipment. These traffic control devices are subsidiary.

- Flagging. Furnish trained and competent flaggers and all necessary equipment, including lighting of the flagging position during nighttime operations, to control traffic through the traffic control zone. The Engineer will approve each flagging operation before it begins and direct adjustments as conditions change.

Flaggers must be certified as one of the following:

- Flagging Level I Certification by IMSA (International Municipal Signal Association)

- Flagger Certification by ATSSA (American  Traffic Safety Services Association)

- Traffic Control Supervisor, ATSSA

- Work Zone Safety Specialist, IMSA

- ATSSA Flagging Instructor

Flaggers shall maintain current flagger certification.  Flaggers must be able to show their flagger certification anytime they are on the project.

Flaggers must maintain their assigned posts at all times, unless another qualified flagger relieves them, or the approved traffic control plan terminates the flagging requirements. Remove, fully cover, or lay down flagger signs when no flagger is present. Keep the flaggers’ area free of encumbrances, such as parked vehicles, so that flaggers can be seen easily.

Provide approved equipment for two-way radio communications between flaggers when flaggers are not in plain, unobstructed view of each other.

Obtain the Engineer’s written approval before flagging signalized intersections. When you flag a signalized intersection, either turn off and cover the traffic signal or place it in the All-Red Flash mode. Coordinate changing traffic signal modes and turning off or turning on traffic signals with the agency responsible for signal maintenance and operation and the Engineer. Get their written approval in advance. Only uniformed police officers are permitted to direct traffic in an intersection with an operating traffic signal.

- Pilot Cars. You may use pilot cars if the route through a traffic control zone which is particularly hazardous, involved, or frequently altered to preclude adequate signing, or if the Engineer deems one-way traffic necessary. Do not use pilot cars to avoid localized traffic control at several locations.

Organize construction operations so the total of all stoppages experienced by a vehicle traveling through a project does not exceed 20 minutes. However, this does not imply that you may allow 20 minutes in all cases. Coordinate multiple pilot-car operations within a project or adjoining projects to minimize inconvenience to the traveling public. You may use two or more pilot cars to provide two-way traffic through the traffic control zone to reduce the waiting period. The flagger or pilot car operator must record each pilot car’s departure time in a bound field book furnished by the Engineer. Whenever practical, the flagger should tell the motorist the reason for and approximate length of the delay. Make every reasonable effort to yield right-of-way to the public and prevent excessive delay.

Use an automobile or pickup as the pilot car, with your company logo prominently displayed. Equip the pilot car with a two-way radio for contact with flaggers and other pilot cars. Mount a G20-4 sign (Pilot Car Follow Me) on the rear at least 5 feet above the driving surface. Identify the last vehicle in the column.

When pilot cars are authorized, use them before beginning work and continue until no longer necessary or until you have properly placed and checked functioning of all traffic control devices required for non-working hours.

- Street Sweeping and Power Brooming. Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material. Use a power broom that can eject the material outside the traveled way. Use a street sweeper that can collect the material.

- Watering. Furnish, haul, and place water for dust control and pavement flushing, as directed. Use water trucks that can provide a high-pressure water stream to flush the pavement and a light-water spray to control dust. If the flushing operations contaminate or fill adjacent catch basins, clean and restore them to their original condition. This requirement includes sections of roadway off the project where flushing is required. The Engineer will control water application.

If you take water from a lake, stream, or other natural water body, first obtain a water removal permit from the Alaska Department of Natural Resources. Comply with the Alaska Department of Fish and Game screening requirements for all water removal operations.

- Portable Changeable Message Board Signs. Furnish Changeable Message Signs when approved on a TCP. Display only messages approved on the TCP. Follow application guidelines in the ATM.

- Truck Mounted Attenuator, TMA. TMAs are mounted on the rear of work vehicles. Impact attenuators are defined by NCHRP  350 as a category III device. TMA shall be mounted on a vehicle with a minimum weight of 15,000 pounds and a maximum weight in accordance with the manufacturer’s recommendations. TMA shall have an adjustable height  so that it can be placed at the correct elevation during usage and to a safe height for transporting. Approach ends of TMAs shall have impact attenuator markings in accordance with the MUTCD. Do not use a damaged attenuator in the work. Replace at your expense, an attenuator damaged from an impact during work.

643-3.05 AUTHORITY OF THE ENGINEER. When the Engineer believes existing conditions may adversely affect the traveling public’s safety and/or convenience, you will receive a written notice. The notice will state the defect(s), the corrective action(s) required, and the time required to complete such action(s). If you fail to take corrective action(s) within the specified time, the Engineer will immediately close down the offending operations until you correct the defect(s). The Engineer may require outside forces to correct unsafe conditions. The cost of work by outside forces will be deducted from any monies due under the terms of this Contract.

643-3.06 TRAFFIC PRICE ADJUSTMENT. A Traffic Price Adjustment, under Item 643(23), will be assessed for unauthorized lane closures or reductions.

Authorized lane closures and/or lane reductions are those shown in the Contract, an approved TCP, or authorized in writing. Unauthorized lane reductions include unacceptable driving surfaces, such as severe bumps, ruts, washboarding, potholes, excessive dust or mud, and non-conforming or out of place traffic control devices. They shall include when temporary crash cushions required to protect motorists from incomplete guardrail installations, as described in Section 606-5.01 are not installed. The Engineer will make the sole determination as to whether the roadway is acceptable for full unimpeded use by the public.

Adjustment Rates are listed in Table 643-1. These rates are liquidated damages which represent highway user costs, based on Average Daily Traffic (ADT). The Engineer will use the rate shown for the current ADT for this project, as published in the Regional Traffic Volume Report prepared by the Department's Planning Section.

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| Less than 1,000 | $2 |
| 1,000-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.07 MAINTENANCE OF TRAFFIC DURING SUSPENSION OF WORK. Approximately one month before you suspend work for the season, schedule a preliminary meeting with the Engineer and Maintenance & Operations to outline the work you expect to complete before shutdown and the anticipated roadway condition. Schedule a field review with the Department for winter maintenance acceptance. At the field review the Engineer will prepare a punch list for implementation before acceptance.

To be relieved of winter maintenance responsibility, leave all roads with a smooth and even surface for public use at all times. Properly crown the roadbed surface for drainage and install adequate safety facilities. Make sure all illumination and signals, including vehicle detectors, are in good working order.

After the project is accepted for winter maintenance and until you are ordered to resume construction operations, the Department is responsible for maintaining the facility. The Department will accept maintenance responsibility only for portions of the work that are open to the public, as determined by the Engineer. The Department will not accept maintenance responsibility for incomplete work adjacent to accepted roads. You are responsible for maintaining all other portions of the work. The Engineer will issue a letter of “Acceptance for Winter Maintenance” that lists all portions of the work that the Department will maintain during a seasonal work suspension. You retain all contractually required maintenance responsibilities until you receive this letter.

If you suspend work due to unfavorable weather (other than seasonal) or due to your failure to correct unsafe conditions, carry out Contract provisions, or carry out the Engineer’s orders, you must bear all costs for traffic maintenance during the suspended period.

When you resume work, replace or renew any work or materials lost or damaged during temporary use. If the Department caused damage during winter suspension, payment will be made for repairs by unit pay item or in accord with Subsection 109-1.05, Compensation for Extra Work. When the Engineer directs, remove any work or materials used in the temporary maintenance. Complete the project as though work has been continuous.

643-3.08 CONSTRUCTION SEQUENCING. Refer to RFP Part III Section 6, Maintenance of Traffic for requirements affecting construction sequencing.

643-3.09 INTERIM PAVEMENT MARKINGS. Place permanent or interim pavement markings according to this Subsection, details shown on the Plans, approved TCPs, and Parts III and VI of the ATM before opening existing paved roadways, temporary paved roadways, detours, interim paving lifts, and roadways with seal coats and surface treatments for more than one continuous work shift. This work may include restriping the existing roadway before beginning construction, before seasonal suspension, and/or after seasonal suspension.

- Remove conflicting pavement markings according to Subsection 670-3.04, Paint Removal.

Mark existing roadway sections that will be opened to traffic during the winter. Mark over the existing lines and markings, unless shown otherwise on the Plans or an approved TCP.

Maintain all interim pavement markings for their intended life including reapplication when necessary. There will be no compensation to upgrade interim pavement markings required for work operations lasting up to 2 weeks.

Use only temporary raised pavement markers or removable preformed retroreflective marking tape as interim pavement markings on final pavement surfaces. Completely remove and dispose of them when you place the final markings. Completely remove any residual adhesive that might misguide motorists. Place final pavement markings on finished pavement surfaces and interim pavement surfaces before suspending work for the winter.

Stage construction to avoid routing traffic over conflicting markings for more than one continuous workshift. If you route traffic over conflicting markings during a workshift, delineate the roadway with a complement of warning signs, channelizing devices, and flaggers as required by the ATM.

Use only temporary raised pavement markers meeting Subsection 712-2.16 as interim markings on seal coat and surface treatment pavements. Install the markers according to the manufacturer’s instructions before applying the asphalt surface material and cover coat. Remove the vinyl protective covers after applying the asphalt pavement.

On multicourse surface treatments, install the temporary raised pavement markers after applying the full width of the first layer of cover coat. Install the markers on each day's completed surface before removing the pilot car operations and allowing unescorted traffic on the surface treatment.

Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 14 days. Apply final pavement markings within 10 days of completing the final sweeping or brooming of the mainline seal coat or surface treatment.

643-3.10 LIGHTING OF NIGHT WORK

- Illuminate the night work areas specified in Table 643-3 to the light levels specified.

Table 643-3 does not provide a comprehensive list of operations that require lighting. Provide lighting for other operations when necessary.

- TABLE 643-3

NIGHT WORK ILLUMINATION LEVEL AND AREA OF COVERAGE

| Type of Work or Equipment | Lighting Configuration |
| --- | --- |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine-mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) with roads with ADTs over 10,000 or 2) that are controlled by portable traffic signals or flaggers | Two balloon lights of at least 2000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources. Do not use floodlights without prior approval by the Engineer. When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway. Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences. When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operation that requires illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and in compliance with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment. Design mountings so lights can be aimed and positioned as necessary to reduce glare. Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures. Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment-mounted light towers or poles are sturdy and freestanding without the aid of guy wires. Towers shall be capable of being moved as necessary to keep pace with the construction operation. Position ground and trailer-mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges. Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers. Illuminate the operator’s controls on all machines uniformly.

Furnish each side of non-street legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction. Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-3.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that all required lights operate continuously during nighttime operations. Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours. In the event of any failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations. Comply with local noise ordinances.

Install all post-mounted electroliers located within the clear zone, on NCHRP 350- compliant breakaway bases.

643-3.11 HIGH VISIBILITY GARMENTS. Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

- Standards.

Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

- Labeling.

Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004; except you may use previously purchased garments labeled in conformance with ANSI/ISEA 107-1999 until 1/1/08.

- Tops.

Wear high visibility vests, jackets, or coverall tops at all times.

- Bottoms.

Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

- Outer Raingear.

Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

- Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

- Condition.

Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

- Payment for high visibility garments for workers is subsidiary to other traffic contract items.

643-4.01 METHOD OF MEASUREMENT.

- Traffic Price Adjustment. By each minute that any lane of traffic is not open to full use by the traveling public, measured to the nearest minute. The Engineer will determine whether the roadway is opened to full use.

643-5.01 BASIS OF PAYMENT.

- Traffic Price Adjustment. If Item 643(23), Traffic Price Adjustment, is shown on the bid schedule, the total value of this contract will be adjusted, for lane closures or delays at the rates listed in Table 643-1.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(23) Traffic Price Adjustment | Contingent Sum |

## SECTION 644

## SERVICES TO BE FURNISHED BY THE CONTRACTOR

644-1.01 DESCRIPTION. Furnish and maintain facilities and services specified in the Contract for the Department’s project administrative personnel to use during the project. Services include heat, electrical power (NEC compliant), water and any others required to operate the facilities. All furnished facilities remain your property when you complete the work.

644-2.01 FIELD OFFICE. Subsection intentionally left blank.

644-2.02 IMAGE DOCUMENTATION. Provide secure "digital image" (image) documentation of the construction of the Eagle River bridge(s); inclusive of an integrated, professional-grade, high resolution digital webcam image system designed for the construction industry with camera(s) and related hardware, mounting equipment, software, data transmission service, website hosting, image hosting, storage/archiving and online interface for the system with technical support and as further defined herein.

1. 	Period of Service. Begin Image Documentation one week before construction begins through one week after project completion.

2. 	Ownership of Image Documentation. All images are the copyright of the Department including still images and time-lapse movies. The Contractor and Vendor may not use the image documentation without the written approval of the Department.

3. 	Ownership of Camera(s) and Accessories. The camera(s) is the property of the Contractor.

4. 	Submittals. Provide complete submittals (3 printed copies), to the Engineer for review and approval, 21 days before beginning Construction activity. Submittals will be returned to the Contractor, within 14 days from the date submitted, marked as approved by the Department, or requiring revisions. Amend and resubmit the documents for review until approved by the Engineer. Include the following:

a.	Shop Drawings. Submit a key plan of the project site and construction to be documented with vantage points marked for location and direction of each camera. Coordinate layout and installation of cameras to avoid interference from trees and to prevent sunlight and light from fixtures entering directly into the camera lens. Indicate camera mounting heights relative to ground and the construction being documented. Include mounting structure, if required, and mount.

Coordinate with the Engineer the location(s) (plan and elevation) to capture the specified activity.

b. 	Data Sheets and Certificates: Submit the technical data sheets and certificates for materials including equipment and software.

c. 		Maintenance: Submit maintenance requirements with a schedule and service instructions.

d. 	Qualifications: Submit:

- Technical Representative’s Resume: name, education, training and two years minimum experience providing same or similar service. Include names of individuals and contact information for verification of service.

- Vendor Qualifications: Name and qualifications including five years minimum experience providing completed successful same service. Include names of projects, project descriptions and contact information for individuals able to verify service.

5. 	Materials.

a. 	Camera. Provide 3 camera(s) with specifications similar to those listed below with equivalent to or better performance.

- CAMERA SPECIFICATIONS

- Features

- Imager: 6 Megapixels, minimum

- Lens: F-Stop f/3.5 - f/5.6

- Zoom: 18 mm - 55 mm

- Optical: 3x min.

- Resolution: (minimum)

- Stills: 3088 x 2056

- Angle of View: Cover intended site area

- Auto Features: ISO, shutter, white balance, and focus

- Compression: JPEG, Motion JPEG

- Communication:

- IP Addressing: Dynamic or Static

- Types: Provide stable communication, by one or more of the following types, dependant on the availability with the order of precedence as follows:

- Wired Broadband (10Base-T/100Base-TX)

- Wireless (802.11n)

- Cellular (3G min)

- Satellite Broadband

Fixed Position: Yes

b.	Online Access, Interface and Online Software. Contractor's System Vendor shall provide an online based interface and online software as managed service to allow the viewing of all still images captured and stored/archived during construction, from any location with internet access using a PC computer and/or cellular device. The Department will not be required to own specific software or operating equipment proprietary to the system vendor to utilize any part of the Vendors service.

- Solution Service: provide solution service, including technical corrective service, continuous 24 hrs, 7 days a week during period of service.

- Machine to machine automated maintenance of the camera system providing continual operation without interruption.

- Communication:

- Broadband/High-Speed connection (1.5 Mbps)

- WiFi G or N // 3G cellular connection

- Accessibility: The Engineer will coordinate with the Central Region Web Manager to provide a link to the vendors site for this project on the Department's Navigator Construction Project Site and the Central Region web page.

- Public: Provide the public with viewing access of still image documentation.

- Department: Provide the Department with viewing access of the still images and live video as specified in 6) User Screen Viewing.

- System Navigation: Calendar based.

- User Screen Viewing: Display the Project Name and Number; Owner and Contractor Logo. Multifunction image browsing (still images, multiple images, online time-lapse movies) per individual camera and between multiple cameras. Additional viewing requirements include:

(a)	Public and Department.

- Images: include time and date.

- Navigation: calendar to navigate between documentation.

- Weather Data: graphical display of local weather data including long term forecast (4-7 day forecast including, sun, overcast, rain, snow, wind speed, temperature, high and low pressure systems and others).

- Multiview Screen: instant view/image of past days, weeks, months, or years at one time.

- Time-lapse movies: not real-time video.

- Split Screen: Instant play back, two or more discreet images side by side from one or more cameras.

- Full-Screen: screen maximizing view of images on users monitor.

- Share Image Tools: save, print, email, and post to message board or, mobile devices.

- Map: aerial and satellite view by Google or other.

(b)	Department Only. Provide password protection for Department only viewing.

- Pan-tilt-zoom control within a high-definition image and by operable motorized/robotic base when included in camera types specified.

- Real-Time Image Browsing/Viewing: view images and video from all cameras in the same display at the same time by day, week, year, and event.

- Overlays: graphical mark-up tools for detailing and creating overlays from multiple discrete images.

- Automated progress reports: Power Point, Open Office and PDF formats.

c.	Environmental. Camera and supporting equipment shall be designed for continual operation in all weather conditions relative to the project site, 24 hrs each day, each day of the week. Weather conditions including but not limited to:

(1)	Wet: water proof.

(2)	Operational Temperatures: -50°F to +120°F (thermostatically controlled heater and blower or other as required).

(3)	Winds: 110 mph (3sec gust)

(4)	Fugitive Materials: Dust, rain, snow and similar.

d.	Physical. Designed and constructed for the conditions existing at the project site.

(1)	Housing: impact resistant, water proof enclosure constructed of aluminum with stainless steel fittings and UL rated compression glands.

(a)	Adjustability: adjustable camera sled.

(b)	Operational Options: (See camera specifications for actual)

• Fixed (pan-tilt-zoom in high-definition image provided by software interface)

• Operable remotely controlled (pan-tilt-zoom)

(2)	Viewing Window: impact resistant with remotely controlled washer/wiper.

(3)	Security: Protect against vandalism. Lockable housing secured in-place to prevent unauthorized removal from project site.

e.	Power. Provide continuous uninterrupted power as required by the Vendor to operate and maintain the image documentation system.

6.	Vendors.

| EarthCam, Inc. | OnsiteView, Inc. | OxBlue Corporation | Work Zone CAM, LLC |
| --- | --- | --- | --- |
| 84 Kennedy Street, | Shipping: | 814 Bellemeade Ave. NW | 331 W 57th St, Suite 310 |
| Hackensack, NJ 07601 | 7901 Cameron Rd | Atlanta, GA 30318 | New York, NY 10019 |
| Ph: 800.327.8422 | Bldg. 3, Suite 301 | Ph: 888.849.2583 | Ph: 877.966.3101 |
| Ph: 201.488.1111 | Austin, TX 78754 | Ph: 404.917.0200 | www.Workzonecam.com |
| Fax: 201.488.1119 | Mail: | Fax: 404.917.0201 |  |
| www.EarthCam.net | P.O. Box 190139 | www.OxBlue.com |  |
|  | Dallas, Texas 75219 |  |  |
|  | Ph: 866.701.2020 |  |  |
|  | Ph: 512.301.2848 |  |  |
|  | www.OnsiteView.com |  |  |

7.	Security. Provide security for the image documentation and documentation system. Prevent; interruption of the continuous documentation, damage to the documentation (data corruption, theft, or loss of the data), and damage to the system (the physical equipment, interface, software, data collection, and storage).

Maintain all images on System Vendor owned and operated secure and redundant servers, in a secure area at a location owned by the Vendor. Minimum levels of security include multiple levels of password protection, IP address block/permission and SSL protection of the user login password.

8.	Installation and Maintenance. Provide initial installation by the Vendor, or other as approved by the Vendor, with the option to move the camera(s) 4 times(s); and maintain the system through project completion without interruption except as may be specified in this specification. Damaged or failed parts and service complications, resulting in documentation interruption, are to be repaired, replaced, and resolved within 48 hrs from the time of interruption.

9.	Documentation. During a 24 hr period, during the day and/or night, document the construction activity. Approximate times are included herein; the approximate location of the camera(s) is provided in the Plans (plan and profile sheets coordinated with the summary sheets). Coordinate with the Engineer, adjusting the times of documentation and actual location(s) (plan and elevation) to capture the specified activity.

Make time-lapse movies at regular intervals from the beginning of service until project completion, season changes, specific construction milestones and other events as noted in these specifications and indicated by the Engineer. Create a final time-lapse movie of construction from beginning of service through project completion combining the time-lapse movies created previously into this final movie.

For all image documentation include the project name and number with the date and time. The date and time for a still image would be at the time of capture and for a time-lapse movie the time from start to finish of the movie.

- Type.

(1)	Still Image Capture. Capture still image at regular intervals. Intervals = 15 minutes.

(2)	Pan-Tilt-Zoom. Real-time video and stills with high-definition image. Available on an as needed basis, except restricted to periods each side of the scheduled still image capture and timed out after a predetermined set time coordinated with the Engineer.

(3)	Time-Lapse. Time-lapse movie from start of service period through the project completion and at the regular interval, change of seasons, construction milestones, and events; include as follows:

Regular Interval. Time-Lapse Movie Interval = End of Each Month.

Seasons.

• Construction season

• Winter shut-down

Milestones and Events.

• Bridge Work

• Bridge abutments

• Bridge substructure or superstructure

10.	Period of Service. At the end of the Period of Service, create a time-lapse movie of the construction activity(s) from the beginning of service to the end of service.

11.	Removal. Remove the complete system after project completion. The Engineer may direct the system to be removed prior to project completion.

12.	Deliverables. Provide the Engineer with (2) DVDs (2 copies) of:

a.	Stills: as originally recorded in the digital camera, without alteration, manipulation, editing, or modifications, in compressed JPEG format, no more than 72 hrs after project completion.

b.	Time lapse movies, compressed motion JPEG format, no more than 72 hrs after each interval, season change, construction milestone, other event specified in 9) "Documentation," and project completion.

## SECTION 646

## CPM SCHEDULING

646-1.01 DESCRIPTION. Provide and maintain a Critical Path Method (CPM) progress schedule for the project. Use the schedule in coordinating and monitoring of all work under the Contract including activity of subcontractors, manufacturers, suppliers, and utility companies, and reviews by the Department. Update CPM, as required.

- Provide work plans.

646-2.01 SUBMITTAL OF SCHEDULE.

Submit a detailed initial CPM schedule at least 5 working days prior to the preconstruction conference, for the Engineer's approval. Meet the requirements set forth below.

- The construction schedule, for the entire project, may not exceed the specified contract time.

Following the Engineer's review, if revisions to the proposed CPM schedule are required, do so promptly. The CPM schedule must be finalized within 60 days of the Notice to Proceed.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

1.	Schedule Requirements. Prepare the CPM schedule as a Precedence Diagram Network developed in the activity-on-node format which includes:

a.	Activity description

b.	Activity duration

c.	Resources required for each of the project activities, including:

(1)	Labor (showing work days per week, holidays, shifts per day, and hours per shift)

(2)	Equipment (including the number of units of each type of equipment)

(3)	Materials

Show on the activity-on-node diagram the sequence and interdependence of all activities required for complete performance of all items of work under this Contract, including shop drawing submittals and reviews and fabrication and delivery activities.

No activity duration may be longer than 15 work days without the Engineer's approval.

The Engineer reserves the right to limit the number of activities on the schedule.

Consider that schedule float time is shared equally with the Department.

The contract completion time will be adjusted only for causes specified in this Contract.

As determined by CPM analysis, only delays in activities which affect milestone dates or contract completion dates will be considered for a time extension.

2.	60-Day Preliminary Schedule. Before proceeding with any work on site, prepare, submit, and receive the Engineer's approval of a 60-Day Preliminary Schedule. Provide a detailed breakdown of activities scheduled for the first 60 days of the project and include mobilization, submittals, procurement, and construction.

No contract work may be pursued at the site without an approved 60-Day Preliminary Schedule or an approved CPM schedule.

3.	Schedule Updates. Hold monthly job site progress meetings with the Engineer for the purpose of updating the CPM schedule. Review progress and verify finish dates of completed activities, remaining duration of uncompleted activities, and any proposed logic and/or time estimate revisions. Submit a revised CPM schedule, within 5 working days after this meeting, showing the finish dates of completed activities and updated times for the remaining work, including any addition, deletion, or revision of activities required by Contract modification.

4.	Work Plans. In addition to the CPM schedule, submit a work plan every two weeks during construction detailing your proposed operations for the forthcoming two weeks. Include:

a.	work activities

b.	manpower involved by trade

c.	work hours

d.	equipment involved

e.	location of the work to be performed

646-3.02 SCHEDULE SUBMITTAL PAY ADJUSTMENT.

A schedule submittal pay adjustment will be assessed for each Day that the Contractor fails to

- Submit an approvable CPM Schedule

- Submit an approvable CPM Schedule update when required by the Contract.

- The Schedule Submittal Pay Adjustment Rates are shown in Table 646-1.

- Table 646-1

Schedule Submittal Pay Adjustment Rates

| Submittal | Pay Adjustment |
| --- | --- |
| CPM Schedule | $650.00 |
| CPM Schedule Update | $120.00 |

Schedule submittal pay adjustments will be deducted from the amount(s) due or to become due the Contractor; and shall be reflected on the next progress payment or final payment that is processed.

## SECTION 660

## SIGNALS AND LIGHTING

660-1.01 DESCRIPTION. Furnish and install, modify, remove, or salvage one or more traffic signal systems, flashing beacon systems, highway lighting systems, sign illumination systems, traffic count systems, electrical equipment on structures, falsework lighting, partial installations for future systems, or combinations thereof, as specified.

Where an existing system is to be modified, reuse the existing material in the revised system as shown on the Plans or specified in the Special Provisions, and salvage or dispose of all other materials.

When required by the Special Provisions, provide an on-site manufacturer’s representative to:

1.	Turn on and adjust the electrical system.

2.	Provide acceptable instruction for the operation and maintenance of the electrical system.

660-1.02 DEFINITIONS. Use the definitions in NEMA TS 2-2003, Traffic Controller Assemblies with NTCIP Requirements, Section 1, Definitions, along with the following:

- Electrolier. The complete assembly of pole, mast arm, luminaire, ballast, and lamp.

- Luminaire. The assembly which houses the light source and controls the light emitted from the light source. Luminaires consist of hood (including socket), reflector, and glass globe or refractor.

- Lighting Standard. The pole and mast arm which supports the luminaire.

- Vehicle. Any motor vehicle licensed for highway use by the State of Alaska.

660-2.01 MATERIALS. Use materials that conform to Section 740, the Materials Certification List, the Plans, specifications, and the following:

Concrete	Section 501 (Class A)

Grout	Subsection 701-2.03

Reinforcing Steel	Section 503

Paint	Subsection 708-2.01

Steel Pipe Pile	Section 715

Anchor Plate	ASTM A 709

Galvanizing	Subsection 716-2.07

1.	Equipment List(s) and Drawings. Within 30 days after the Contract award, submit 8 collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval. Include a table of contents in the portfolio(s) that includes each item’s intended use(s) and the following:

- Materials on the Qualified Products List: A description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

- Materials Not on the Qualified Products List: Catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

- Pole Package. A complete set of design, fabrication, and installation proposals for each signal and lighting pole. Include stamped engineering calculations, shop drawings, welding plans, equipment lists, and pole installation plans.

- Materials Not Requiring Certification: Incidental materials incorporated into the work (such as nuts, ties, bolts, washers, etc.) must meet all applicable Specifications and be installed per all manufacturer’s recommendations. Certification is not needed unless required by the Special Provisions or requested by the Engineer.

2.	As-Built Plans. Prepare 3 complete sets of red lined as-built plans and keep them current with the construction. Detail in the as-built plans all construction changes made to the Plans. Include the following information on the appropriate sheets:

- Location and depth of conduit runs

- Station and offset of all junction boxes

- Heights of signal faces and overhead signs

- A list of equipment, including manufacturer, brand, and model number installed in each controller cabinet

Furnish copies of the as-built plans at least twice a month during construction so that they may be reviewed for accuracy and completeness. Furnish any additional information required to clarify the as-built plans and correct all discrepancies. The Department will not make progress payments for the signal and illumination work completed until reviewing accurate as-built plans reflecting the construction progress. Correct any deficiencies before payment.

Before final inspection of the work, submit 3 complete sets of as-built plans to the Engineer. You may substitute 2 colored copies of the as-built plans in lieu of keeping the 3 separate original copies. If you elect to do this, a sample of the method of copying must be approved before starting any work on the signal and lighting items.

The Contractor will attach the appropriate sheets of the appropriate sheets of the as-built plan set in clear plastic envelopes to the inside of each controller assembly and load center.

3.	Warranties, Guarantees, and Instruction Sheets. Deliver to the Engineer all manufacturers’ warranties, guaranties, instruction sheets, and parts furnished with materials used in the work before the Department assumes maintenance responsibilities.

CONSTRUCTION REQUIREMENTS

660-3.01 GENERAL.

1.	Scheduling of Work. Complete each new traffic signal system, highway lighting system, and sign illumination system and ensure it is ready for operation before opening to traffic the corresponding section of new alignment.  After staking pole foundations, verify there will be no overhead or underground utility conflicts with foundations, poles, mast arms, or conduits.  Locate and protect existing underground and overhead utilities.  The location of cables, conduits, J-boxes, foundations and poles that are shown on the Plan sheets are approximate and it is the Contractor’s responsibility to verify the actual location when working in the area.  See Subsection 105-1.06.

Existing signing and traffic markings shall not be allowed to conflict with new signal modifications.  New signing and traffic marking modifications shall not conflict with existing signals and shall be kept current with signal modifications.

Conduct work with the existing traffic signal systems remaining in operation unless authorized otherwise by the Engineer.

Incidental materials and other items that are not shown on the Plans, assembly drawings, or specified herein, that are necessary to complete the system, must be furnished and installed as though such materials and other items were shown on the Plans, assembly drawings, or specified herein.

Protect metallic materials against corrosion.  Hot-dip galvanize ferrous metals such as bolts, braces, bodies, clamps, fittings, guards, nuts, pins, rods, shims, thimbles, washers, and miscellaneous parts not of corrosion resistant steel, according to ASTM A 123 or A 153, except where other equivalent protection treatment is specifically approved in writing by the Engineer.

Asphalt Patches placed in existing asphalt for loops and conduit crossings must be placed prior to the end of shift in which the loops and crossings are placed. Asphalt patches will match the thickness of the existing asphalt to a maximum of 3 inches thick. Where the existing asphalt is thicker than 3 inches, use compacted crushed aggregate base course to make up the difference.

Do not place traffic signal systems in operation until the street lighting is energized at controlled intersections.

Install detector loops and underground conduit before applying new pavement.

Do not pull conductors into conduit until the junction boxes are set to grade, crushed rock sumps are installed, grout is placed around the conduit, and metallic conduit is bonded.

In vehicular undercrossings, place soffit lights in operation as soon as practicable after removing falsework from the structure. Place lighting for pedestrian structures in operation before opening the structure to pedestrian traffic.

2.	Safety Precautions. Before starting work on existing street lighting circuits, de-energize the system by opening disconnect switches, and/or opening bypass switch plugs, and tagging each opened device as detailed in Part 4, Section 44, Article 440 of NESC. Where said circuits are under the control of an electric utility, obtain written assurance daily from the utility that the circuit being worked on has been de-energized.

Post suitable signs at load centers when any of the circuits from that load center are being worked on.

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

3.	Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors. Provide traffic control to complete this work according to the requirements of Section 643. Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified side by side, to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches, and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit. Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

Dispose of, according to subsection 203-3.01, excavated materials that remains after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in subsection 703-2.07.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations. Backfill excavations with materials that meet the following requirements:

a.	Backfill foundations with material that meets the requirements of

Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift,

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material gleaned free of rocks exceeding a 1 inch maximum dimension. Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to Subsection 203-3.04. In other locations, compaction may be as approved by the Engineer.

4.	Welding. Complete welding according to subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval. The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes, which were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface. For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole. Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole. Grind the welds smooth and flush with the adjoining pole and disk surfaces. Repair the damaged finish according to Subsection 660-3.01.8.

5.	Removing and Replacing Improvements. The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the nonreusable improvements the Contractor removed to complete the work, unless other items in the contract cover the improvements.

c. 	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements that the Contractor damaged or removed, that do not conflict with the work and are not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings. Reusable improvements include the items that were made before installation. Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition. In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material,  cut  completely  through  the  material  with  a  saw  along  the outline of the area to be removed. Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil. Match the top of the topsoil with the bottom of the vegetative mat. Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621. Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment. When the Plans include existing electrical equipment scheduled for removal or relocation, remove and store the equipment listed in the following paragraph without damaging it. Deliver removed equipment not scheduled for reuse to the nearest District Maintenance Station. Notify the district superintendent or person specified by telephone one-week before planned delivery date.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation. The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations. Raze the tops of foundations abandoned in place according to subsection 660-3.02. Fill the holes left by removing junction boxes and foundations with selected material type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place with a credit taken by the Department. Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer. Note the location and condition of the materials. When material specified for reuse is found  in  an  unserviceable  condition,  the  Engineer  will  determine whether to repair it or replace it with new material, which will be paid for as extra work under Subsection 109-1.05. Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

a.	For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

b.	For lighting poles, install new illumination tap wires and fused disconnect kits.

c.	For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

d.	For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

e.	For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to Subsection 660-3.01.4. Welding and repair the finishes according to Subsection 660-3.01.8.

When ordered, the Engineer will pay for repairing damaged finishes on existing equipment according to Subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to Subsection 660-2.01.1.

7.	Field Tests. Before acceptance of the work, perform the following tests on all electrical systems under this Section, in the presence of the Engineer. Furnish the necessary equipment needed to perform these tests. The Department reserves the right to retest, and the test results will govern the acceptance or rejection of the installation. Replace or repair at your expense, and in an approved manner, any faults in material or any part of the installation revealed by these tests. Repeat the same test until no fault appears.

- Continuity. Test each circuit for continuity.

Test each loop detector circuit for continuity at two locations:

- Loop detector at the junction box before splicing with the loop detector lead-in cable must have a value less than 0.5 ohms.

- Loop detector and lead-in cable system at the traffic signal controller cabinet or detector cabinet after splicing in the junction box must have a value less than 5 ohms for single pair lead-in cable and 10 ohms for multi-pair lead-in cable. The continuity test ohm reading at the traffic signal controller cabinet or detector cabinet must be greater than the ohm reading measured at the loop detector at the junction box.

- Grounds. Test for grounds in each circuit by physically examining the installation to ensure that all required grounding bushings, bonding jumpers, and ground rods have been installed and are mechanically firm.

- Insulation Resistance Test. Perform a megohm test on each circuit, between circuits, and between the circuit and a ground. Measure each detector loop and lead-in cable system at the traffic signal controller cabinet or at the detector cabinet between one loop detector lead-in conductor and the cabinet ground rod. Ensure the insulation resistance is not less than 100 megohms or the minimum specified by the manufacturer, measured at 500 volts DC. Disconnect all lamps and magnetometer sensing probes prior to the megger test. Document these tests in writing, for each circuit, and submit to the Engineer prior to acceptance of the system.

- Inductance Test. Measure each detector loop and lead-in cable system at the traffic signal controller cabinet or detector cabinet. The inductance must be in the range of 50 to 500 microhenries.

- Circuit. Energize every signal indication circuit with lamps installed before installing the load switches.

- Functional. Perform the following tests on each signal and lighting system after all of the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity and circuitry.

  - Perform the functional test for each new traffic signal system by running at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation. You may omit the flashing portion of the test for a modified signal system or if there was an existing signal maintained at this location during the construction activity.

The Engineer and the final owner of the signal system will determine if the flashing operation will be required. If the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for 5 days with continuous satisfactory operation.

Do not start signal functional tests on a Friday, Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Initially turn on the system between 9:00 a.m. and 2:00 p.m. Before turning it on, ensure all equipment is installed and operable. This includes, but is not limited to, pedestrian signals and push buttons; signal face backplates and visors; vehicle detectors; highway lighting; and all regulatory, warning, and guide signs. Aim all signal faces as required by Subsection 660-3.08.

  - Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5-day operational test using the photocell.

  - Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

  - Perform a continuous 5-day burning test on each pedestrian overcrossing and undercrossing lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system is functional when the power is returned.

8.	Repairing Damaged Finishes. Examine all exterior surfaces for damage in the field, including new, reused, and State-furnished equipment. Repair damaged finishes as follows:

a.	Galvanized. Repair damage to galvanized coatings in conformance with AASHTO M 36.

b.	Painted.

- Wash the equipment with a stiff bristle brush using a solution of water containing 2 tablespoons of heavy-duty detergent powder per gallon. After rinsing, wire brush all surfaces to remove all poorly bonded paint, rust, scale, corrosion, grease, or dirt. Remove any dust or residue remaining after wire brushing before priming.

- You may use factory or shop cleaning methods for metals if equal to the methods specified herein.

- Immediately after cleaning, coat all bare metal with pre-treatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

- Give signal equipment, excluding standards, a spot-finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

- Give ungalvanized standards 2 spot-finish coats on newly primed areas.

You may apply all paint coats either by hand brushing or by approved spraying machines. Perform the work in a neat and workmanlike manner. The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint spraying machine prove unacceptable.

9.	Regulations and Code. Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

660-3.02 FOUNDATIONS.

- Cast-in-Place Foundations. Cast-in-place foundations for posts and poles in drilled holes. Use either precast or cast-in-place foundations for cabinets.

- Form the entire controller foundation and the top 12 inches of pole or post foundations and give the top a smooth steel trowel finish. Locate the tops of traffic signal post and pole foundations flush with the adjacent finished: walkway, shoulder, or surrounding ground.

- Place conduits in the center of the pole-post foundations with clearance allowed for bushings. If subsurface conditions prevent completing a drilled hole, and when approved, use a corrugated metal pipe (CMP) form as a substitute for the drilled hole. Consider the savings in concrete to offset the cost of supplying and installing the CMP form. No additional payment will be made for the CMP formed foundation.

- When a CMP is used, over-excavate the area around the form enough to allow for proper compaction around the form. Perform backfill operations according to Section 204. Do not use water for drilling operations or for any other purpose where it may enter the hole.

- Use controller cabinet anchor bolts as recommended by cabinet manufacturer and set with a template.

- Place Class A concrete meeting Section 501. Place reinforcing steel meeting Section 503. If required, use corrugated steel pipe that is at least 14 gage, meeting Subsection 707-2.01.

- Drill holes or use forms that are vertical and true to the locations shown in the Plans. When foundation excavation is complete, but before placing the concrete, remove all loose material to ensure that the foundation rests on firm, undisturbed ground.

- If a reinforcing steel cage is required, place and secure it symmetrically about the vertical axis and securely block it to clear the sides of the foundation. Use a template to securely support all anchor bolt assemblies and conduit ends so they do not move during concrete placement.

- Do not permit surface water to enter the hole. Before placing concrete, remove all water that may have infiltrated in the hole. Thoroughly moisten both the forms and the ground before placing concrete. Pour each foundation in one continuous pour.

- Do not erect or place posts, poles, and pedestals on the foundation until 7 days after placing the concrete. Plumb the assembly by adjusting the nuts on the anchor bolts prior to attaching the skirt.

- Replace, with no additional compensation, all finished foundations with anchor bolts that do not match the base plate of the pole or are out of plumb. Do not modify the anchor bolts or base plate to get the base plate set on the leveling nuts.

- Install the bottoms of the bottom leveling nuts in a level plane within 1 inch of the top of foundations. Adjust all nuts until their tops form a level plane. Install one washer on top of all leveling nuts and, after setting the pole on these washers, install one washer under all top nuts.

- Bring all leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax. Tighten all top nuts to a “snug” condition.

- Use a click-type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts.

After torquing the top nuts, use a hydraulic wrench to rotate all top nuts an additional one sixth (60o) turn, while preventing the leveling nuts from turning.

l.	Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage. Use an irreversible compression connector or cadweld to make the attachment. Protect the attachment during concrete placement. In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode. Route the conductor to protrude near the top, center of the foundations. Slide a minimum 6 inch long, nonmetallic, protective sleeve over the conductor. Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

- Pile Foundations.

  - Install pipe piles according to Section 505.

  - Install pipe piles open-ended and to a minimum depth of 15 feet (less top projection).

  - Use CJP groove welds for all circumferential welds.

  - Inspect 100% of CJP welds using UT or RT.

  - Backfill and compact the work hole around upper portion of each pile in 8-inch lifts with a soil-cement mixture. (minimum of 3 sacks of cement per cubic yard of soil).

  - Certify steel pipe piles by matching the stencils on the pipe piles (by 300 foot lots) to the physical and chemical tests for the applicable lot.

  - Use no more than one splice per foundation. Locate the splice at least 7 feet from the top of pile.

    - All Foundations.

- Install frangible couplings according to the manufacturers written installation instructions. Use shims furnished by the coupling manufacturer.

- Provide new foundations and anchor bolts of the proper type and size for standards that are to be relocated. Install the anchor bolts on a bolt circle that matches the base plate.

- Install a raised Type III junction box on the door side of the controller cabinet, and butt it against the cabinet’s foundation unless installing a one-piece cabinet/junction box foundation. Extend the top of the controller cabinet foundation 18 inches above the junction box and provide it with a 1-inch diameter drain. The drain connected to the cabinet interior must empty to the rear and above the ground. Place all conduits in the door side half of the foundation to provide adequate terminal block clearance.

- Existing foundations may be abandoned-in-place. However, remove the tops of the foundations, reinforcing steel, anchor bolts, and conduits to at least 12 inches below the roadway subgrade, sidewalk, or unimproved ground. Backfill the resulting hole with material equivalent to and compacted to the density of the surrounding ground.

    - High Tower Foundations. Furnish pipe piles that conform to API 5L X 52 and feature the diameter, minimum length and wall thickness shown on the Plans. Furnish seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Complete welding according to Subsection 504-3.01.8 Welding. Submit a shop drawing of the work with the welding plan. Furnish Quality Control inspection to ensure materials and workmanship meet contract requirements. Visually inspect (VT) 100% of each weld and inspect 100% of full penetration welds by ultrasonic NDE (UT).

Furnish anchor bolts that conform to ASTM F1554, grade 55, and meet the supplementary Charpy V-Notch requirements listed in subsection S4 of the specification. Furnish each anchor bolt with three nuts and two washers.

Secure the anchor bolts to ensure they do not move during concrete placement. Replace, with no additional compensation, concrete pile caps with anchor bolts that do not match the base plate of the pole or are out of plumb. The Department will not allow modification of the anchor bolts or base plate to get the base plate set on the leveling nuts.

660-3.03 CONDUIT. Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified. Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits. Install conduits of the sizes specified along the routes detailed on the Plans.

1.	Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

2.	Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches. Excavate, bed conduits, and backfill trenches according to subsection 660-3.01.3, Excavating and Backfilling.

3.	Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods. Jacking conduits into position is allowed. However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

4.	Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90 degree rigid metal elbows on the ends of conduit runs. To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

5.	Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box. Extend the ends a minimum of 2 inches beyond the inside wall of the box.

6.	Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs. Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors. Cover the holes with a wrap of approved filter cloth secured with 2 self-clinching nylon cable ties.

7.	Keep conduits clean. Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

8.	At the low points of conduit runs, install sumps containing a minimum 2 cubic-feet of coarse concrete aggregate material that conforms to subsection 703-2.02. Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

9.	Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary. Install additional drains and aggregate sumps at the low spots, if any.

10.	Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

11.	Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit. Cut conduits squarely to ensure the threading die starts squarely on the conduit. Cut the same number of threads as found on the factory threaded ends. Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges. Do not use slip joints or pieces of running thread pipe.

12.	Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

13.	When standard couplings cannot be used to join conduit components, use approved threaded unions.

14.	Bury a continuous strip of 4 mils thick, 6 inch wide polyethylene marker tape above underground conduit runs. Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings. Furnish tapes with a black legend on a red background.

15.	If encountering obstructions during jacking or drilling operations, obtain approval and cut small holes in the pavement to clear the obstruction. Locate the bottom inside face of the bore pit no closer than the catch point of a 1¼ to 1 slope (a horizontal to vertical ratio) from the edge of pavement. Do not leave these pits unattended until installing an approved means of protection.

16.	When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

17.	In foundations, install 90 degree elbows and conduits of the size and quantity shown on the Plans. Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

18. 	Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct sealing compound.

19.	Install expansion fittings in conduits that cross expansion joints.

20.	Install a polypropylene pull rope with a minimum 200 pound tensile strength in future use or spare conduits, and reinstall the plugs. Double back at least two feet of pull rope into both ends of each conduit.

21.	The Contractor may install conduits larger than the sizes specified. If used, it must be for the entire length of the run. Reducing couplings or bushings are not allowed. Complete work associated with installing conduits larger than specified without extra compensation.

22.	Clean existing conduits that will remain in service using a heavy duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch. Clean the conduits before pulling in new cables and after removing cables specified to be removed or replaced as follows:

a.	When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

b.	Ream empty conduits with a mandrel or cylindrical wire  brush before blowing them out with compressed air.

23.	When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit. When extending existing conduits, add no more than 90 degrees of horizontal bend to the extension.

24.	When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

25.	When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

26.	Remove the ends of abandoned conduits from junction boxes that will remain in service.

27.	When Plans call for connecting polyethylene conduit to RMC use an electrofusion coupler rated for direct bury application. The coupler must be rated for same wall thickness as the adjoining conduits. Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC. Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

660-3.04 JUNCTION BOXES. Install precast reinforced concrete junction boxes of the types specified. For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them. For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

- Junction Box Location

When shown, install junction boxes at the station and offset locations specified. When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement. If the 8 feet offset falls:

1.	In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility. When lacking the right-of-way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

2.	In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

3. 	Outside the right-of-way, install the boxes just inside the right of way line.

4.	In a raised median, install junction boxes near the center of the median.

5.	In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

6.	Behind  guardrails  that  shield  slopes  steeper  than  3:1  (a  horizontal  to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

7.	On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing type 1A junction boxes in driveways and in locations subject to use by heavy trucks. When shown near the ends of medians, install junction boxes at least 10 feet from the median end. When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.

- Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2. 	300 feet for conduits that exclusively contain two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work, otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria. In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade. In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to Subsection 660-3.06. Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box. Drains shall consist of coarse aggregate for concrete that conforms to Subsection 703-2.02. Minimum drain dimensions include an 18 inch depth and a length and width equal to those of the junction box it drains. Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker that consists of an antenna encapsulated in a 4 inch diameter red polyethylene ball. Furnish markers that conform to the American Public Works Association standards for locating power. Markers shall respond to locator devices up to 5 feet away, work at all temperatures, and contain no internal power source.

660-3.05 WIRING. Wire all cabinets with conductors sized to handle the amperage drawn under full cabinet use. Make wiring neat in cabinets by cabling wires together with self-clinching nylon ties. Terminate all spare conductors on terminal blocks. Attach all conductors, including spares, to terminal blocks with “spade” type terminal lugs. Furnish additional terminal blocks if enough locations are unavailable in existing terminal blocks. Do not splice conductors within cabinets, poles, signal heads, and luminaires.

Do not pull conductors into conduits until the following conditions are met:

a.	 The prescribed clearances around conduit ends are provided,

b.	Crushed rock sumps are installed under junction boxes,

c.	Conduit ends protrude above the bottom of junction boxes within the prescribed range,

d.	New conduits are free of material that became lodged in them during the completion of the work,

e.	Reused conduits are cleaned according to Subsection 660-3.03,

f.	Junction boxes are set to grade, and

g.	Grounding bushings are installed on the ends of metallic conduits.

- Pull conductors by hand or by approved commercially built cable-pulling equipment that is specially designed for that purpose. Do not pull cable by any other means. Equip the cable pulling device with a force limiting circuit and force gauge.

- Use wire-pulling lubricant when placing the cables and conductors in conduit. Do not allow the tension of the wire or cable to exceed the manufacturer’s recommend allowable tension for the conductor or cable.

- When adding new conductors to a conduit with existing conductors, remove all conductors and clean the conduit with a mandrel or brush. Pull both old and new conductors through as a unit. In a new installation, pull all conductors through the conduit as a unit.

- Leave at least 1 foot of slack in the bottom of each signal or combination signal and lighting pole of each signal conductor or cable. Neatly leave at least 3 feet of slack illumination and signal conductor or cable curled up in the bottom of each junction box or splice location.

- Separate the neutral for pedestrian push button circuits from the signal light circuit neutral.

- Run all signal and feeder conductors continuously without splices from a terminal block located in a cabinet, compartment, or signal head, to a similarly located terminal block. When modifying an existing signal system, splice existing conductors (cables) to new conductors (cables) as required to complete the signal, opticom, and interconnect systems. Make these splices only in pole bases, signal terminal compartments, or the controller cabinet.

- Route highway illumination cable through each lighting pole designated for connection to that cable’s circuit. Do not splice illumination cable between a load center and a pole or between poles. Join the individual conductors by using non-insulated, overlap type pressure connectors. Insulate with mastic-lined heat shrink tubing or 2 layers of one-half lapped UL listed electrical tape. Do not use wire binding screws, studs, or nuts. Stagger splices to minimize the overall diameter.

- Install all loops in 1-inch rigid schedule 80 PVC conduit in the roadway and to the nearest junction box. Run loop lead-in cable continuously without splices from the controller cabinet to the curbside detection junction box nearest the loop being spliced to the lead-in cable. Splice the loop(s) to the lead-in cable by soldering at the junction box and encapsulating in a waterproof splice kit.

Multiple loop configurations must have the individual lead-ins, multiple pair, or single pair brought to the controller cabinet for termination. Make series connection of loop lead-ins in the controller cabinet only. Wind all loops in the same direction with the starting lead marked with an “S.” Connect the black conductor of the pair shown in Table 660-1 to the “S” designated conductor of the loop. Connect multiple loop detectors in the same lane so that the adjacent loops are in alternating directions clock wise (CW), counter clock wise (CCW), etc.

- When splicing loop detectors to multi-pair loop lead-in cables, complete the work according to the following.

a.	See the Plans for the identifying number assigned to each loop detector and the loops assigned to each loop lead-in cable. Using this information, splice the loop detector tails to the paired conductors found in each lead-in cable, using the color code in Table 660-1.

- TABLE 660-1

MULTIPLE PAIR LOOP LEAD-IN COLOR CONNECTION SCHEDULE

| Loop Detector Number | Colored Pair |
| --- | --- |
| The lowest numbered loop detector | Red and Black |
| The second lowest numbered loop detector | Blue and Black |
| The third lowest numbered loop detector | White and Black |
| The fourth lowest numbered loop detector | Green and Black |
| The fifth lowest numbered loop detector | Brown and Black |
| Usually a spare pair | Yellow and Black |
| Usually a spare pair | Orange and Black |

b.	Remove a short section of cable jacket and only cut the shielded pairs dedicated to loop detectors being spliced. Run these pairs, without splices, to the controller cabinet.

c.	Strip the insulation from the ends of the conductors. With the loop and lead-in conductors parallel to one another, twist the bare ends together and then solder them together.

d.	Insulate and seal each soldered connection with a mastic lined heat shrink tubing; crimp the ends of the heat shrink tubing with a pair of needle nose pliers.

e.	First, crimp and then solder spade terminals to the ends of the shielded pairs in the controller cabinet.

- Maintain the electrical isolation between shields and do not allow the drain wires to come in contact at any point other than the ground bus in the cabinet. Tie all drain wires to the ground bus at the controller cabinet.

- Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin. Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin. Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin. Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, 1 splice may be used in the following cases:

a.	An in-line splice may be used when a planned cable run exceeds the length available from the manufacturer on a single spool of cable.

b.	In a run of 1,000 linear feet or more.

When a cable is spliced it shall occur within an appropriately sized j-box or in the base of an electrolier designed for said splice.

- Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with reenterable polyurethane electrical insulating and sealing compound. Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide reuseable four piece molds that are held together with stainless steel hose clamps. Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry. Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full ¼ inch of insulating compound to flow between the splice and the inside of the mold. Fill the PVC molds with reenterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is noncorrosive to copper, and does not support fungi or mold growth.

- Permanently identify all cables and single wire conductors by labeling all pole bases and cabinets, at each detector loop tail/lead-in cable and illumination cable splices, and in junction boxes adjacent to lighting and signal poles. When modifying an existing system, label all new and existing lighting cables/conductors with circuit numbers at locations noted above. If the existing circuits are not identified, the Engineer will provide the required circuit numbers.

- Label the cables used in the signal and illumination systems with the following legends:

  - Use the legends included in Table 740-2, for the cables listed.

  - Use the loop number shown on the Plans to label each tail of all loop detectors and the paired loop lead-in conductors in the controller cabinet.

  - For interconnect cables, use the first letter of the direction the cable follows to the adjacent intersection on each cable. Add a number suffix if more than one cable is routed to the adjacent intersection.

Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer. Replace at no expense to the State all identification tags the Engineer deems illegible.

- Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet. Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head. Use cable ties consisting of a single strap with a minimum size tag of 3/4 inch by 3/8 inch.

- To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear. Provide tags with a 4 inch by 1-3/4 inch minimum size that attach flag style at one corner to a single strap. Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

- Terminate the control and power cables as shown in Table 740-2.

- Connect telemetry cable to a Type No. 66B3-50 terminal block. Start the wiring at the top with Pair No. 1. Connect the incoming cable from the computer to the left side of the terminal block, and connect the outgoing cable to the next intersection to the right side.

- Wire luminaires using No. 10 AWG illumination tap conductors that run from the fused disconnect kit in the pole base.

Install a fused splice connector between the line and luminaire ballast tap conductors in the base of every pole equipped with a luminaire.

Attach the conductors to the connector halves with setscrew type pressure connectors. Provide the plug and socket assembly so that the fuse remains in the load side plug without exposing live metal parts when the connector separates and the coil springs are not included in the current carrying circuit.

Make the fused connectors readily accessible from the handhole. Install tap conductors to prevent slack when their ends touch the top of the foundation.

- Retrofit reused poles with new tap wires, fused disconnect kits, and fuses.

19.	Whenever conductors cannot be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector. Insulate the splice with heat shrink tubing. Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductor to 5 feet.

20.	Spare lighting conductors shall be capped in the pole bases and load centers by cutting the wire flush with the end of the insulation and bending the conductor back against itself and securing with three layers of electrical tape to prevent any possibility of making contact with ground or current carrying conductors.

660-3.06 BONDING AND GROUNDING. Bond and ground branch circuits according to the NEC and the following requirements. Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor. Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits. Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use. Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG. In this case, install a wire equal in size to the largest circuit conductor. Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing. Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings. When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to an 8 AWG conductor and eyelets spaced at 6 inch intervals. Connect bonding jumpers to the grounding conductors using irreversible compression type connectors. Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the 4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations. For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 4 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES. Prepare each solid-state, traffic controller assembly to operate various traffic signal devices as shown on the Plans. The controller must provide right-of-way, clearance, and other indications using duration and sequence as determined by preset programming.

Details of operation for the complete controller assembly must be according to the traffic phases; preferential phase sequence and concurrence; signal indications; signal indication sequence; detection requirements; and other details shown on the Plans or as specified herein.

At the time the controller assembly is delivered, submit the following for each assembly called for in the Plans:

- Two blackline sets of controller cabinet schematic wiring diagrams

- Two copies of the manufacturer’s maintenance and operations manuals for the equipment in the cabinet (1 paper copy and 1 electronic copy on Adobe PDF format).

The schematic wiring diagrams must show all circuits and parts in detail. Clearly identify all parts by name or number. Submit the final wiring diagrams for each controller assembly in an AutoCAD Drawing Interchange File format (DXF, DWG, etc.) on compact disk. Use only the default font style and line type distributed with a basic AutoCAD package.

1.	Shop Tests. The Controller Assembly manufacturer shall conduct a pretest of the cabinet and controller assembly. The pretest includes but is not limited to:

a.	Ensure the cabinet is free of paint scratches, dents, sharp edges, and other physical defect.

b.	Ensure cabinet hinges, heater, ventilation system, lighting, and door locking mechanism function properly.

c.	Ensure that there are no shorts between AC+, AC-, and GND anywhere in the cabinet.

d.	Check that there is no continuity between AC+ and DC+.

e.	Check for continuity between any green wire connection point and GND.

f.	Ensure devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly. Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of; flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation, and proper police and auxiliary panel operation.

Upon completing the final test the cabinet shall be run, "burned in," under full loads for a period of not less than 48 hours with a test timing plan in effect which utilizes full cabinet phases and functionality.

In the course of testing, a component found to function incorrectly or exhibit physical damage must be replaced with an equivalent new component before delivery.  Should the cabinet fail during burn in, the cause of the failure must be remedied and the test restarted with another 48 hours of burn in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pretest, final test, and burn in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note defects found and the remedial action taken.  Further, the certification shall state the assembly conforms to the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements. Submit the certification letter and copies of the test results to the Engineer.

2.	Controller Cabinet Installation.

- Where the cabinet is mounted on a concrete pedestal foundation, place a 1-inch drain hole or pipe with screen in the foundation, connecting to the cabinet and emptying above the ground line.

- Place a 3/8-inch fillet of silicone caulking between each controller cabinet and the concrete slab foundation to prevent dust and dirt from entering the cabinet.

- When called for in the Plans or Special Provisions, add 2 inches of approved foam insulation within the bottom of the cabinet between the control equipment and the concrete base. Design all wiring, terminals, and other items to allow sufficient room for the insulation.

- On Precast Controller Foundations. When called for in the Plans or Special Provisions, place a 3/8-inch thick, 2-piece exterior grade plywood board on the bottom of the cabinet and under the foam insulation. Place the plywood within the controller cabinet, and do not extend under it. Make holes to allow for the conduits entering the cabinet. Place a pliable sealant composed of a silicon caulking compound between the plywood board and the cabinet and between the plywood board and all the conduits.

- Place a ground rod in the Type III junction box next to the cabinet or in the foundation of the cabinet if it is precast foundation.

- See Subsection 660-3.05 and Section 740 for wiring requirements.

3.	Controller Operation. Provide the following operations.

- Wire the controller cabinet to flash the yellow signals on the main street or highway, and the red signals on the cross streets and left turn lanes.

- Make the flashing circuit independent of the controller unit. They must remain in operation upon shutdown of the controller or removal of the controller from the cabinet.

- Wire the controller cabinet so that removal of the conflict monitor causes the intersection to go into flashing operation.

- Accomplish transfer to flashing operation by relays between the normal load switching device and the field terminals.

- Do not operate pedestrian pushbuttons at more than 24 volts.

- Controller Priorities. Prioritize the drives, controls and equipment so that each device, control, or item of equipment overrides the operation of those items listed below it:

- Power failure

- Power restart

- Flashing

- Emergency vehicle preemptor

- Phase selector

- Interconnect

- Time switch

- Normal controller unit operation

Provide the following preemption operations when called for on the Plans or as specified in the Special Provisions.

- General. Preemption units must use the controller unit functional inputs and timings to the largest extent possible. Signal load switching control must remain with the controller unit.

b.	Emergency Equipment Preemption. The Emergency Equipment Preemption Routine must consist of 3 functional intervals in the order listed below:

(1)	Enter Preemption Interval.

(a)	Energize a 120 VAC alarm circuit which may be used for a sign, bell, or beacon.

(b)	Immediately advance to the pedestrian clearance interval of any walk that is being displayed. On any phase other than the track clearance phase(s), abbreviate the pedestrian clearance interval by a timer with a minimum range of 0-30 seconds.

(c)	Following the pedestrian clearance period, the controller must advance into and time normally the vehicle clearance intervals.

(d)	If the preemption call is received while in the preempt phase(s), skip step (b) and (c) above.

- Preempt Phase Interval. Hold the controller in the preempt phase(s) until the call is removed.

- Leaving Preemption Interval. When the preemption call is removed, the controller unit must immediately revert to normal operation.

660-3.08 SIGNAL AND LIGHTING STRUCTURES. Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply antiseizing compound to the following fasteners: frangible couplings, mechanical grounding connectors, bolts that secure hand hole covers and signal mounting hardware to poles and mast arms. Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces which secure the visors, and apply antiseizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans. Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal. Provide shirts with a legend that reads “out of service” and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation. Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm. After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Signal Pole Installation. Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate. Tighten the nuts on the anchor bolts as described in subsection 660-3.02k.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

3.	Vehicular Signal Head Installation. With two piece mast arms, do not install signal heads within 12 inches on either side of the slip type field splice.

Attach each side mounted terminal compartment with two ½” x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on Standard Drawing T-30. Install the vertical pipe members plumb.

When installing 5 section vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2. If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

- TABLE 660-2

THROUGH-SIGNAL AIMING POINT

| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| --- | --- |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

4.	Pedestrian Signal and Push Button Installation. Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street. Attach each clamshell bracket with two ½ inch x 13 bolts threaded into holes tapped into the side of the pole. Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole. Install R10-4B (R or L) push button signs above each push button. Furnish signs with the arrow pointing in the direction of the appropriate crosswalk. When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

Install an R10-101 sticker, The Meaning of Pedestrian Signals, on each pole with one or two pedestrian push buttons. With two pedestrian push buttons on a pole, install the sticker between and above the R10-4B signs. With one pedestrian push button, install the sticker directly above the R10-4B sign.

5.	High Tower Lighting System Installation. Assemble and install high tower poles according to the written instructions furnished by the manufacturer. To assemble and install poles other than as recommended, furnish a plan stamped by a registered professional engineer to the Engineer for approval. Furnish timbers required to assemble the pole, regardless of the method of assembly.

Position the pole during assembly to avoid moving the pole on the ground when lifting the pole to install it on its foundation. When conditions around a foundation preclude assembling the pole on site, assemble the pole as close as possible to the foundation and move the pole into position for installation on its foundation. Before moving a pole, submit a plan stamped by a register professional engineer for moving poles without damage to the Engineer for approval.

Install the lowering system including masthead assembly, luminaire ring, winch assembly, cables, and permanent integral electric motor as instructed by the manufacturer’s on site representative.

Install and level the luminaires according to the manufacturer’s written installation instructions.

Furnish the Engineer an instruction sheet from the manufacturer for orienting reflectors in luminaires that provide an asymmetrical light distribution. Adjust the luminaire reflectors on each pole according to this sheet until they are oriented in the same direction and distribute light according to the pattern shown on the illumination sheets.

Use steel templates to accurately locate and hold the anchor rods plumb and in proper alignment during concrete placement. Leave this template in place for at least 24 hours after completing concrete placement. The Engineer will reject foundations with anchor rods that are out of position or more than 1:40 out of plumb. The Department does not allow bending of anchor rods to plumb the ends or to move them into position, or altering a pole’s base plate to match the anchor bolts.

Tighten the nuts that secure high tower lighting poles to concrete foundations according to the following procedure. Use nuts that conform to ASTM Specification A 194 or A 563 of the grade, surface finish, and style for 2 inch diameter anchor rods that conform to ASTM F 1554, Grade 55. Washers shall conform to ASTM F 436 Type 1.

Thread nuts onto the anchor rods to within 1 inch above the top of the concrete base and adjust them downward, if necessary, to provide a minimum ¼ inch projection of the rod above the top of the top nut in the tightened position. Adjust nuts until their tops form a level plane. Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Apply beeswax to the top nut bearing face and top nut internal threads before threading it onto the anchor rod. Tighten top nuts to a “snug” condition. Use a click type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts. Torque the top nuts in the following crisscross pattern.

After torquing the top nuts, use a hydraulic wrench to rotate top nuts an additional one sixth (60o) turn, while preventing the leveling nuts from turning. Use the crisscross pattern shown above.

6.	Underpass Lighting System Installation. Mount the luminaires as detailed on the drawings to orient the axis of the lamp perpendicular to the axis of the underpass.

7.	Flashing Beacon Installation. When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher. Furnish and leave 5 feet of cable in the cabinet. Others will install the fused block and terminate the beacon cables.

8.	Wood Pole Installation. Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material. Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

660-3.09 MAINTAINING TEMPORARY AND EXISTING ELECTRICAL SYSTEMS. This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If the existing lighting systems is not kept fully operational as specified herein, the Engineer will reduce the payments under the Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference. Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility. Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment. If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer. If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records. When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet. Make sure each entry includes:

1.	The dates and times beginning and completing work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions allowed in Subsection 643-3.08, Construction Sequencing. During shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 15.0 feet.

Alignment. During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 18.0 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal. For closer signals refer to the MUTCD for maximum clearances.

2.	For side-mounted signals, maintain 9 feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5. 	When the horizontal angle to the side mounted far right signal exceeds 20o, relocate this signal to an overhead location. Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

- With two or more through lanes, center one signal head over each lane.

- With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

- Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in Subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and item 6. Salvaging or Reusing Electrical Equipment found in Subsection 660-3.01, and remove other materials used in the temporary systems from the project.

660-3.10 FALSEWORK LIGHTING. When required by the Plans, install falsework lighting where vehicular traffic with or without pedestrian traffic crosses through or under structure falsework.

Provide illumination of the portal faces of falsework during the hours from dusk to dawn. Provide illumination of the pavement and pedestrian openings through or under falsework 24 hours a day.

Submit a plan for the proposed lighting installations and do not commence falsework construction until the Engineer has reviewed such plans. The Engineer will make a subsequent review after you place falsework lights in operation.

Falsework lighting equipment remains your property and must be removed from the site of the work upon completion of the project or when directed.

660-3.11 SIGNAL SYSTEM TIMING AND ADJUSTMENTS. The Contractor will use Municipality of Anchorage (MOA) signal maintenance personnel for certain work inside controller cabinets. Before MOA personnel arrive to terminate conductors, ensure terminal connectors are attached to conductor ends and paired loop detector conductors and cables are labeled as specified in subsection 660-3.05, Wiring. On projects outside the MOA, send controller equipment to the MOA for testing and complete work specified inside controller cabinets.

Controller Cabinet Preparation. Ship the traffic controller cabinet(s) and equipment to the Municipality of Anchorage Traffic Signal Electronics Shop at 3650 E. Tudor Road, Building C. MOA will inspect cabinet wiring, burn in signal equipment, customize cabinets for desired operation, and test the equipment according to subsection 660-3.07, Shop Tests.

1.	Loop Detector Wiring. Municipality of Anchorage Traffic Signal Maintenance (MOA Signal Maintenance) will test and connect paired loop detector conductors to the terminal blocks.

2.	Control Cable Wiring. When modifying an operational signal system or controller assembly, MOA Signal Maintenance will connect control cables within the controller cabinet to the terminal blocks.

3.	Timing Adjustments. During construction, MOA Signal Maintenance may adjust the system and intersection operational timing to accommodate project conditions.

4.	Interconnect Wiring.  MOA  Signal  Maintenance  will  test  and  connect interconnect wiring to the terminal blocks.

660-3.12 TRAFFIC SIGNAL MODIFICATIONS. Required work is detailed in the Plans.

The Contractor will have 10 hours to "changeover" the new controller assembly. Changeover includes but is not limited to: removing the existing controller assembly, replacing with new controller assembly, landing new and existing wires, programming the new controller unit, and bringing the signal back to full functionality. The 10 hour window will only occur on the days Monday through Thursday at a time determined by the Engineer. The Contractor will be assessed a Traffic Price Adjustment for an unauthorized lane closure according to Subsection 643-3.06.

Traffic control during the changeover will be paid for under section 643 Pay Items. At a minimum, traffic control will include the following:

•	A portable changeable message board in advance of each approach with the message "Traffic Signal Work, New Traffic Pattern Ahead, from 00:00 AM/PM mm/dd/yy to 00:00 AM/PM mm/dd/yy.

•	A flagger for each approach.

Traffic signal modifications are subject to the full Standard Specification for Highway Construction, the Special Provisions and the following:

1.	Traffic Controller Cabinet: When a new traffic controller cabinet is called for, ensure legible labeling of all cabinet cables including but not limited to; control, loop, EVP, UPS, interconnect, and telephone. Label loops and signal heads individually.

2.	Traffic Signal Heads: When new traffic signal heads are required, provide with new LED units and new mounting hardware. If new heads are not called for, replace any missing visors or backplates.

When replacing traffic signal or pedestrian indications conform to Subsections 740-2.14 and 2.15 and maintain brand consistency throughout intersection. When new heads are provided aim heads according to Table 660-2.

3.	Loops: When shown in the plans, replace inductive loops including homerun cable and required splice. Loop tests are required per Subsection 660-3.01.7.

4.	Conduits: Unless new conduits are called for reuse existing conduits. When new conductors are being added to existing conduits, conform to Subsections 660-3.03, 3.05, and 3.06.

5.	EVP Components: When called for in the plans provide EVP components including all cables and mounting hardware. Ensure proper operation of EVP system.

6.	UPS: When called for in the plans provide fully function UPS system.

7.	Load Center: When called for in the plans provide fully functioning Load Center.

8.	Conductors: Reuse existing conductors except where the plans call for new conductors.

Salvage decommissioned reusable traffic signal equipment, components/materials and deliver to the M&O Yard on Tudor Road within 72 hours of removal. Decommissioned components damaged as part of the salvage effort must be replaced with new components at no additional cost.

660-3.13 MANUFACTURER ASSISTED START UP. The Contractor shall retain the services of a representative from the controller equipment manufacturer (Manufacturer’s Representative), subject to the approval of the Engineer.  The Manufacturer’s Representative shall have previous experience with either the Central Region DOT&PF or Northern Region DOT&PF in assisting with traffic signal controller testing, field testing and turn on. Submit name(s) and professional credentials at least 30 days before beginning this work. When required, work on, and connections to, the controller unit, amplifiers, and related equipment shall be performed by or directly supervised by a qualified person serving as the Manufacturer’s Representative.

- On-Site manufacturer assisted start up may be required when indicated in the Plans.

Telephonic manufacturer assisted start-up required for all intersections that do not require on-site manufacturer assisted start up as indicated above.

1.	Required Credentials of Manufacturer’s Representative

a.	10 years experience working in the traffic controller industry, 5 years of that must have been as a signal technician.

b.	Must have IMSA Traffic Signal Technician, Level II certification

c.	Experience assisting with traffic signal controller testing and start-up with the Northern Region ADOT, or the Central Region ADOT

d.	Familiarity with both the NEMA TS1 and TS2 specifications

e.	Experience setting up video detection

f.	Competent to program the Controller Unit

g.	Competent to program the MMU permissive card

h.	Competent to implement and adjust timing plans

i.	Competent to implement coordinated timing plans

j.	Competent to read cabinet wiring diagrams and troubleshoot cabinet components

k.	Competent to troubleshoot interconnect cable

l.	Competent to test inductive loop detectors and setup detector amplifiers

m.	Competent to conduct training on installed components

2.	Cabinet Preparation. The Manufacturer’s Representative shall provide oversight and supervision of the controller cabinet preparation. The Manufacturer’s Representative shall be on-site for the duration of this work. Cabinet Preparation, includes, but is not limited to:

a.	Field Test: Conduct field test including needed adjustments and repairs as described in Subsection 660-3.01.7.

b.	Control Cable Wiring. The Manufacturer’s Representative will oversee the connection of control cables within the controller cabinet to the terminal blocks.

c.	Interconnect Wiring. The Manufacturer’s Representative will oversee and test connect wiring to the terminal blocks.

d.	Labeling. The Manufacturer’s Representative will check labeling of traffic signal components and correct or cause to be corrected deficiencies. Labeling will be done according to 660-3.05.14. Labeling occurs in both the traffic signal cabinet and j boxes associated with the traffic signal. Complete this work before any functional testing of the signal heads.

e.	Schedule. Upon completion of the controller cabinet preparation the Contractor and Manufacturer’s Representative shall submit a schedule for controller programming, detector testing, installation field-testing, signal start-up and training of Department personnel to the Engineer for approval. Once the schedule is approved the Manufacturer's Representative shall:

(1)	Review timing plans provided by the Engineer. The Manufacturer’s Representative may recommend adjustments to timing to be considered and accepted by the Engineer.

(2)	Program the controller unit based upon the accepted timing plan.

(3)	Connect the programmed controller unit and electronics accessories in the cabinet as required to make the signal fully operational.

(4)	Oversee field testing. Coordinate field testing with the Engineer to allow participation by Department staff. Schedule the start-up day following successful field testing and 1 to 5 days of flashing operations. Flashing operations can immediately follow acceptable field testing.

(5)	Oversee the change of the signal from flashing operations to fully actuated operations

(6)	Place current timing plans in the controller cabinet by the close of business the day the signal is turned on.

(7)	Provide intersection diagrams compatible with the Aries software.

(8)	Be available for onsite timing adjustments for a minimum of 24 hours after signal turn-on.

3.	Test Reports.

a.	Contractor and the Manufacturer’s Representative will provide the Engineer with reports detailing test procedures and results of test.

The report will include at a minimum:

(1)	Inductive Loop Test including measured values of Inductance, quality factor, continuity and insulation resistance.

(2)	Proper signal display illumination

(3)	Proper pedestrian display illumination

(4)	Correct number of signal faces per phase

(5)	Proper signal head alignment

(6)	Proper functioning of pedestrian buttons

(7)	Proper functioning of EVP system

(8)	Flash programming correct

(9)	Ensure ped indication is black during flash

(10)	Conflicting traffic control signs removed

660-3.14 HIGH TOWER LOWERING AND LIFTING PLAN SUBMITTAL, REQUIREMENTS AND REVIEW.

1.	Submit a High Tower Lowering and Lifting Plan as developed by a Consultant at the preconstruction conference. Attach a resume and a description of the required Consultant qualifications to the Plan. Submit the Plan to the Division of Labor Standards and Safety, Occupation Safety and Health, of the Alaska Department of Labor for comments.

The Department will have 10 days to review, comment, and accept the first Plan submittal, and 5 days on each subsequent submittal, until the Plan is found to be acceptable. The Department’s allotted time to review the Plan starts when both the Plan and the Traffic Control Plan have been submitted; refer to Section 643 Traffic Maintenance.

2.	The Consultant’s Plan, services, and activities shall follow the guidelines and requirements of ANSI A10.33-1992, American National Standard Construction and Demolition Operations – Safety and Health Program Requirements for Multi-Employer Projects, approved February 6, 1992 and published by the National Safety Council. This specification does not modify Section 107 of the Standard Specifications for Highway Construction. The Consultant shall use ANSI A10.33 for performance of the required tasks. The Contractor is not required to use or follow ANSI A10.33 for construction operations.

3.	The scope of work for the application of ANSI A10.33 is the lowering and lifting of the high tower structures. The Consultant will follow the guidelines of the following sections as found in ANSI A10.33:

3.4.1	Evaluation of Contractor Safety and Health Programs to determine their appropriateness to the specific job site and work to be performed;

3.4.2	Monitoring and documenting the implementation of Safety and Health Programs;

3.7	Special Safety and Health Plan.

5.3	Corrective Action.

7.	Construction Process Plan

8.	Pre-Work Planning

The Project Safety and Health Program and Construction Process Plan as described within ANSI A10.33 as applied to the lowering and lifting of the high tower structure should be considered the same as the Plan. The Consultant is not the same as the Senior Contractor Supervisor as defined within ANSI A10.33. The Contractor will provide the Consultant access to the construction sites.

4.	At a minimum, the information included in the Plan provided shall include:

a.	a list and the configuration of equipment, tools and material to be used;

b.	a sketch of each site or the crane set-up where one sketch may represent multiple sites that are similar;

c.	manpower and manpower qualifications;

d.	a description of the method and sequencing of the lowering and lifting procedure;

e.	documentation of crane certification as required by law;

f.	the necessary equipment and work force to provide a backup system to prevent the fall of a high tower structure should there be a failure of primary lowering and lifting equipment.

5.	More than one process Plan may be necessary to address differing site conditions from site to site. Possible Plan differences may include differing site restrictions such as the available working area, differing terrain, highway and ramp slopes, guardrail, highway traffic and nearby private development.

6.	The high tower pole sections shall be manufactured without picking holes. Coordinate with the pole manufacturer for load picking points.

7.	The Plan will need to be coordinated with the Traffic Control Plan at high tower pole sites. The final Traffic Control Plan approved by the Engineer may have an impact on the Plan.

660-3.15 HIGH TOWER LOWERING AND LIFTING PLAN CONSULTANT QUALIFICATIONS. The Consultant is to be a Certified Safety Professional (CSP) as certified by the Board of Certified Safety Professionals, with specific knowledge and experience in the lowering and lifting industry, crane and sling operations and safety, fall protection, and knowledge of State and Federal Occupational Safety and Health Standards and applicable regulations. The Consultant will also demonstrate education in the field of safety, a minimum of 4 years of experience and practice in crane lowering and lifting in cold regions, and a list of 5 previous and similar projects. The Plan may require the services and certification of a Professional Engineer registered to practice in the State of Alaska, as per ANSI A10.33 Section 3.9 Critical Structures and Complex Processes, and will be dependent on the scope of the lift and weights involved.

660-3.16 IMPLEMENTATION OF THE HIGH TOWER LOWERING AND LIFTING PLAN.

1.	Ten days before the first lowering event, the Contractor will schedule a meeting and have the Consultant conduct a training session with the Contractor and the Engineer present, to review and explain the accepted Plan. The Contractor’s and subcontractor’s construction personnel that will be in the field performing the work are also to be present. The approved Traffic Control Plan will also be reviewed.

2.	During the first lowering event and again with the first lifting event, the Consultant shall conduct a field inspection of the operation and procedure being used by the Contractor, establish compliance with the Plan, to be followed within 3 days by a written report, and certify that the Plan is being incorporated. The report will indicate discrepancies and deviations from the Plan that were found, and the corrective action to be incorporated. This is the same as ANSI A10.33, Section 3.7, Special Safety and Health Plan and Section 5.3 Corrective Action.

3.	There are to be four additional field inspections and reports by the Consultant during the progress of the work:  two of a lowering activity and two of a lifting activity.  These inspections and reports are the same as ANSI A10.33, Section 3.8 Monthly Status Reports, and replace the monthly requirement. This brings the total required field inspections to three each of lowering and lifting, for a total of six inspections and reports. Fifth and sixth inspection will be considered the last and final inspections and reports.

660-3.17 HIGH TOWER LOWERING AND LIFTING CORRECTIVE MEASURES BY THE CONTRACTOR. The Contractor will implement corrective measures. The Consultant will conduct a follow up inspection and provide a written report on how discrepancies were corrected.

## SECTION 661

## ELECTRICAL LOAD CENTERS

661-1.01 DESCRIPTION. Furnish and install load center assemblies at the locations indicated in the Plans. Modify existing load centers when indicated.

Furnish and install load center assembly Type 1A with an integral uninterruptible power supply (secondary power source) to power intersection traffic and pedestrian signals (no lighting) and control equipment during interruptions to the utility power (primary power source).

Use load centers of the following types as shown on the load center detail sheets:

Type 1:		Pad mounted with underground service (large)

Type 1A:		Pad mounted with underground service (small)

Type 1A with UPS:	Pad mounted with underground service (large)

Type 2:		Post mounted with underground service

Type 3:		Pole mounted with overhead service

661-1.02 ACRONYMS.

BBS	Battery Backup System

LC	Load Center

LCD	Liquid Crystal Display

LED	Light Emitting Diode

LC/UPS	Load Center with Integral Uninterruptible Power Supply

MBPS	Power Transfer Switch

MMU	Malfunction Management Unit

PLC	Powerline Communications

PTS	Power Transfer Switch

THD	Total Harmonic Distortion

UPS	Uninterruptible Power Supply

661-1.03 DEFINITIONS.

- BUCK-BOOST. Switch-mode voltage regulator in which voltage can be above or below the input voltage.

661-2.01 MATERIALS. Use materials that conform to Section 740, the Materials Certification List, the Plans, specifications, and the following.

Concrete	Section 501 (Class A)

Grout	Subsection 701-2.03

Reinforcing Steel	Section 503

Anchor Bolts	Section 740-2.02

- Load Center. NEMA 3R enclosure constructed of .125” aluminum with no external screws, bolts, or nuts.

Shop coat cabinet components with a 2-part urethane paint undercoat and 2-part urethane finish coats. Finish coats must be standard white for removable panels and non-gloss silver-gray, closely matching FSS No. 5950 Color No. 36622, for the enclosure.

The load center must be labeled as a unit by an approved independent electrical testing laboratory (such as UL, ETL, CSA, etc.) defined by ANSI Standard Z34.1 Third-Party Certification Programs for Products Processes and Services and conform to applicable published standards noted herein, the Plans, and Special Provisions. The load center must be labeled as service entrance equipment and labeled UL 508A or equivalent.

Panelboards. Load panels in load centers must conform to FSS W-P-115C, Type 1 - Circuit Breaker Panelboards; UL 67 - Panelboards; and NEMA PB1 - Panelboards with Molded Case Circuit Breakers. The rated voltage of the panels must be as noted on the load center summary in the Plans, 120/240 volts or 240/480 volt single phase or 120/208 volt or 277/480 volt three-phase. The ampacity rating of panels must not be less than the ampacity noted on the load center summary, 100 amps minimum, at rated voltage.

Circuit Breakers. Use bolt-in type circuit breakers with a copper bus. Provide separate neutral and ground busses. The series rated interrupting capacity of the circuit breakers in the panels must not be less than shown on the load center summary, or 10,000 AIC minimum, at rated voltage.

Use circuit breakers that are molded-case thermal-magnetic types with single-trip indicating switch handle. They must have an enclosed toggle type operating mechanism with quick-make/quick-break action and have a trip-free disconnect from the switch handle that will prevent the contacts from being held in the closed position. The circuit breakers must have the frame size, interrupting capacities, and trip rating clearly marked on the breaker. Multi-pole circuit breakers must have a common trip mechanism. Contacts must be silver alloy enclosed in an arc quenching chamber. Overload trip ratings must be self-compensating for ambient temperatures from 14 °F to 140 °F. Circuit breakers must be 240 or 277 volt maximum rated for 120/240/277 volt circuits, whichever is applicable, and have an interrupting capacity (RMS - symmetrical) of not less than 10,000 amperes. They must have not less than 480 volt rated for circuits above 277 volts and have an interrupting capacity (R.M.S.- symmetrical) of not less than 14,000 amperes.

Contactor. Electrically-held type consisting of an operating coil, a laminated armature, contacts, and terminals. Contacts must be fine silver, silver alloy, or superior alternative material rated to switch the specified load, 30 ampere minimum at rated voltage, and be normally open, unless otherwise noted. Contactor coils must be rated for operation at 240 VAC.

Meters. Equip all meter sockets mounted in Type-1 load centers with internal mounted meters with manual circuit closing devices. The devices may be either the link or lever type. Do not use the horn and sliding types. Equip all load centers with internal mounted meters with safety sockets (that is, provisions for de-energizing the meter jaws). The test section cover must be sealable with a 0.047-inch stainless steel bail.  Furnish meter sockets and landing pads rated for 200 Ampere Service.

Transformers. Transformers in load centers containing load panels of different nominal voltages must be isolated winding type with primary and secondary voltages and KVA ratings as noted on the Plans. Transformers must carry rated volt amperes continuously without exceeding a 240 °F temperature rise above a 100 °F ambient temperature.

Where installed outside of the load center enclosure, use a non-ventilated transformer fabricated from aluminum, stainless steel, or galvanized steel and filled with high-melting point, thermal setting, or epoxy insulating compounds to prevent moisture from entering the winding enclosure. Coat enclosures fabricated from sheet metal with moisture-resistant paint. Insulate transformer leads with non-hygroscopic material and extend them 9 inches beyond the winding chamber seal.

- Conductors. Stranded copper with either type XHHW-2 or RHW insulation.

- Conduit. Galvanized rigid conduit made of mild steel meeting UL standard UL-6.

Terminals. Size all terminals according to the amperage ratings of the conductor used. They must be suitable for termination of copper and aluminum conductors.

- Ground Rods. Furnish one piece ¾ inch diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps. Furnish one piece bronze clamps with a hex head setscrew that are suitable for direct burial and for use with copper clad ground rods.

- Meters. Furnish meter sockets and landing pads rated for 200 Ampere Service.

- Photoelectric Controls. Use photoelectric controls rated for operation at 240 VAC.

Galvanizing. Galvanize steel materials according to Subsection 716-2.07. Repair damage to galvanized coatings per AASHTO M 36.

- Welding. Perform welding according to Subsection 504-3.01, and the requirements of the individual items.

Photoelectric Controls. Use three wire photoelectric controls that directly switch a circuit from one conductor to another. Furnish two piece photoelectric controls that consist of a plug-in control unit and a locking type receptacle set in a cast aluminum adapter.

- 1.	Plug-in Control Unit.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, and control relay free of intermediate amplifications.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 VAC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes,

c.	Operate at temperatures from -40 °F to +150 °F,

d.	Consumes less than 10 watts of power,

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug,

f.	Turn-on between 1.0 and 5.0 foot-candles and turn-off at light levels between 1.5 and 5.0 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices used in the Control of Roadway Lighting.

Screen the photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation. Extend screens to the top of the control units. Use 3 inch wide x 0.063 inch thick (min) aluminum meeting ASTM B209, Alloy 3003-H14.

- 2.	Locking Receptacles.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for 1/2 inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms,) furnish a pole top adapter: equipped with a terminal block, made to slip over the ends of poles 3-1/2 to 4-1/2 inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

Equipment List(s) and Drawings. Within 30 days after the Contract award, submit 8 collated copies of a portfolio of equipment and materials proposed for installation to the Department for review and approval. Include a table of contents in the portfolio(s) that includes each item’s intended use(s) and the following:

- Materials on the “Qualified Products List”: The Qualified Products List does not apply to the 661 Pay Items. Provide catalog cuts of materials to the Engineer for review and approval.

- Materials Not on the Qualified Products List: Catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

- Materials Not Requiring Certification: Incidental materials incorporated into the work (such as nuts, ties, bolts, washers, etc.) must meet all applicable Specifications and be installed per all manufacturer’s recommendations.

661-3.01 CONSTRUCTION REQUIREMENTS. Install load centers at the location and position shown on the Plans. Any deviation from the plan location must be coordinated with and approved by the serving utility and the Engineer.

Furnish conduit, conductors, contactors, breakers, transformers, and all other necessary materials at all new and modified load centers to complete the installation.

Install a rigid metal conduit of the size shown in the Plans at a 30-inch depth from the load center and extend it to a location 2 feet from the power source. Install a pull rope in the conduit, cap the end, and mark the terminus with a 2- x 4-inch stake or 1-inch rebar, 3 feet long. Extend the end of the stake or bar 1 inch above the ground. When the servicing utility requires the complete conduit and weather head to be in place on the designated service pole, furnish and install all materials required by the utility. The additional work and materials are subsidiary to the load center bid item.

Where the service is to be installed on a utility-owned pole, coordinate the positioning of the riser and service equipment with the service utility.

House circuit breakers, switches, and contactors in a NEMA 3R type enclosure listed by an approved independent electrical testing laboratory as service equipment with a hinged and locking front cover. Indelibly label panel covers with the circuit number. Legend plates, labels, and signs must be engraved plastic or metal fastened with screws, non-cold-susceptible adhesive, or component mounting hardware.

Size and wire load center cabinets to serve the combination of highway lighting, traffic signal, and thaw wire circuits shown in the Plans. Each cabinet must be a single box subdivided to form compartments as required. Include hinged lockable door(s) or panel cover(s) with provision for a padlock with a 5/16 inch diameter shackle for each compartment. Circuit breaker ratings must be as shown in the load center summary for each location.

Wire and equip load centers with commonly metered thaw wire and lighting circuits with separate contactors, selector switches, and terminal blocks for lighting and thaw wire circuits. Control the thaw wires as described in Section 616.

Where a meter is required, furnish and install a meter socket that is acceptable to the serving utility, complete with sealing rings. Do not mount the meter socket on doors or removable panels.

Load centers containing contactors must have contactor control switches mounted in the load distribution section. Control switches for systems having automatic controls (for example, photo cell, thermostats, or time controls) must be 3-position types with the positions labeled “On”, “Off” and “Auto”. Control switches for manual control only must be a 2-position type with positions labeled “On” and “Off”. Label each switch to identify function being controlled.

Mount transformer fuses in dead-front fuse holders with lighted blown fuse indicators, where required. Label them to indicate function and fuse amp rating.

Install two ground rods at least 6 feet apart at each load center. Connect the neutral bus to the ground rods with a soft drawn bare copper conductor sized per the NEC, 6 AWG minimum. Bond non-current carrying metal parts in each load center to the ground bus. At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base. Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky. Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic. To the hub, attach an assembly that consists of a Type LB conduit body, a length of conduit, and a Type C conduit body. Fabricate the conduit at least 3 feet long and locate the photoelectric control 1 ft above the top of the load center. Mount the photoelectric control adapter on the Type C conduit body. Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a Type C conduit body to the hub with a close nipple. Mount the photoelectric control adapter on the conduit body. Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard. Restrain the cable in a similar manner as the illumination cable in the pole base. Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

Provide a typed circuit directory for each load panel inside of the load center door, protected with a plastic cover, describing each circuit, with even and odd numbered circuit breaker positions shown on separate parts of the directory. Provide a power and control one-line diagram protected by a laminated plastic cover inside the load center. Include the following information on the directory and one-line diagram: Load center identification (A, B, etc.), Project Name, Project number (Federal/State) and Service Voltage.

- Coordinate new load centers with existing and or new service utilities.

## SECTION 670

## TRAFFIC MARKINGS

670-1.01 DESCRIPTION. Furnish and place traffic markings of the type, color, dimensions, and at the locations shown on the Plans. Meet these specifications and the applicable portions of the Alaska Traffic Manual.

- Pavement Marking Type:  Methyl Methacrylate (MMA)

670-2.01 MATERIALS. Use materials that conform to the following:

Traffic Paint 	Subsection 708-2.03

Glass Beads 	Subsection 712-2.08

Preformed Pavement Markings 	Subsection 712-2.14

Raised and Recessed Pavement Markers	Subsection 712-2.15

Methyl Methacrylate Pavement Markings	Subsection 712-2.17

Glass Beads for Methyl Methacrylate Markings	Subsection 712-2.18

Methyl Methacrylate Pavement Markings are a combination of methyl methacrylate, glass beads and anti-skid aggregate.

- Construct the iron casting for the raised pavement markers of modular iron meeting ASTM A 536.

Submit a single certification from the manufacturer of the marking material, for each material combination, certifying the combination of marking material, glass beads and anti-skid aggregate, as furnished, provides the durability, retroreflectivity, and skid resistance specified.

670-3.01 CONSTRUCTION REQUIREMENTS. Install interim pavement markings meeting Section 643 if permanent markings are not installed prior to opening the roadway to traffic.

- Paint.

- Apply paint only to pavements that are clean, dry, and warmer than 40 °F.

- Remove all dirt, oil, grease, and other foreign matter from the surfaces to be painted in a satisfactory manner.

- Apply the paint at the rate of 80 ft2/gal (approximately 20 mils wet film thickness). This rate is effectively 22 gallons of paint per mile of solid 4-inch stripe. A tolerance not to exceed 10% is allowed for film thickness or yield.

- Apply glass beads over the wet painted stripes in a uniform pattern at the rate of 6 pounds (± 0.1 pound) of beads per gallon of paint. Pressure-apply the beads using a mechanical dispenser mounted not more than 12 inches behind the paint dispenser.

- Use approved equipment for highway lane striping that is specifically designed and manufactured for that purpose by a company experienced in the design and manufacture of such equipment. Minimum requirements include the capability of striping two 4-inch yellow centerlines and one 4-inch white edge line simultaneously. Apply markings with clear-cut edges, true and smooth alignment, and uniform film thickness.

2.	Preformed Marking Tapes (PMT). Apply the PMT material as directed by the manufacturer by either the inlay or overlay method. Use the inlay method whenever new asphalt concrete is placed. Use the overlay method to apply markings to existing pavement.

Store all PMT materials between 60 °F and 85 °F for at least 24 hours prior to installation. During installation, maintain field stockpiles at the required storage temperature.

For the inlay method, embed the pavement markings in the asphalt concrete surface with a conventional steel wheeled roller. Apply when the surface temperature of the mat is the warmest possible without deforming the marking. The minimum allowable surface temperature, taken within 3/8 inch of the top of the mat, is 140 °F.

If the application of the PMT materials falls behind the paving operation to the extent that the markings are not being applied at the minimum acceptable temperature, slow the paving operation to match the rate of the marking laydown. Resume full paving operations after demonstrating that you have sufficiently skilled personnel to install the markings within the required temperature limits.

When applying pavement markings by the overlay method, ensure the surface is clean and dry and is at least 60 °F and rising. Broom the surface clean. Remove any dust using compressed air. Apply a coat of primer/adhesive activator according to the manufacturer’s recommendations. Install and roll the markings with a minimum 200-pound pneumatic roller.

3.	Raised and Recessed Pavement Markers. Install raised and recessed pavement markers per the manufacturer’s instructions.

Cut or dado the finished pavement surface with a concrete saw to produce a slot with dimensions as shown on the Plans or recommended by the manufacturer. Clean and dry the slots using compressed air. Install a reflective marker of the color indicated with an epoxy adhesive recommended by the marker manufacturer.

4.	Methyl Methacrylate Pavement Markings (MMA).

a.	General. 15 days before starting work meet with the Engineer for a prestriping meeting. At this meeting, do the following:

(1)	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

(2)	Discuss placement of materials, potential problems.

(3)	Discuss work plan at off ramps, on ramps and intersections.

(4)	Discuss material handling procedures.

(5)	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative. Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”). Ensure the Manufacturer’s Representative observes the application of the pavement marking materials. Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers. Install pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method. Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation. Prepare the roadway surface to receive pavement markings according to these Specifications and the manufacturer’s recommendations. Clean and dry the roadway surface. Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Equipment.

(1)	Grooving Equipment. Use grooving equipment that produces a dry cut. Use vacuum shrouded equipment or other equally effective containment procedures.

(2)	Marking Equipment.

(a)	Longitudinal Marking: Use truck mounted application equipment capable of installing a double centerline and a single shoulder line in a single pass. Use automatic bead applicators that place a uniform layer of beads on the lines. Hand units are not permitted.

(b)	Other Markings: Use manual or automatic application equipment. Use stencils or extruders to form sharply defined markings.

f.	Application. Apply marking material according to these Specifications and the manufacturer’s recommendations. Use equipment designed and capable of properly mixing at the place and time of application and approved by the manufacturer for the type of product being installed.

Anti-skid Aggregate. During marking material application, anti-skid aggregate will be evenly distributed and visible throughout the top 20 mils of the marking material mixture, and after the application, in the surface of the cured material.

- SURFACE APPLIED

- Marking thickness will be measured from the pavement surface.

(1)	Longitudinal Markings. Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 60 mils.

(b)	Gore Markings:

Apply diagonal gore markings to yield a thickness of 60 mils.

- INLAID

Groove the area(s) designated in the Plans.  Install markings in the same work shift as the grooving operation. Markings will be measured flush with the pavement surface.

(1)	Longitudinal Markings. Groove the pavement to a depth of 60 mils. Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 60 mils.

(2)	Other Markings.

(a)	Transverse and Symbol Markings:

Groove the area for inlaid markings to a depth of 500 mils. Apply marking for symbols, arrows, stop bars, railroad symbols, and cross walks to yield a thickness of 500 mils.

(b)	Roundabouts:

As designated on the plans, groove the area for inlaid markings in roundabouts to a depth of 500 mils. Apply markings to yield a thickness of 500 mils.

(c)	Gore Markings:

Diagonal gore markings will not be inlaid unless shown in the Plans.

g.	Disposal of Waste. Waste material(s) are the Contractor’s property. This includes grindings and removed marking material. Do not dispose of or store waste material(s) on State property. Dispose of waste material(s) according to applicable Federal, State, and local regulations.

h.	Sampling. On the form provided by the Engineer, record the following readings and locations where they were taken using project stationing, and submit them to the Engineer with 24 hours for evaluation. Thickness of material and depth of slot are measured from the surface of the pavement.

- SURFACE APPLIED

(1)	For surface applied longitudinal applications, measure the thickness of the lines (above the pavement surface) at the time of application, every 500 feet.

(2)	For surface applied other markings measure the thickness in three locations for each marking.

- INLAID

(1)	For inlay longitudinal applications, record the depth of the slot every 500 feet during the grinding operation.

(2)	For inlay other markings measure the thickness in three locations for each marking.

Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly. Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

- The Engineer may elect to use the Contractor’s readings or perform additional sampling.

670-3.04 PAVEMENT MARKING REMOVAL. Remove all existing traffic markings that are in conflict with the striping details shown on the Plans, an approved TCP, or any temporary striping as directed. Do not paint over existing markings. Do not use open flame on the final paving lift.

Remove pavement markings to the fullest extent possible without materially damaging the pavement surface, color, or texture. As the work progresses, remove sand or other material deposited on the pavement as a result of removing markings. Remove accumulations of sand or other material that might interfere with drainage or constitute a hazard to traffic.

Coordinate removal work with construction activity. Remove pavement markings the same day permanent markings are applied, unless otherwise directed. Use vacuum shrouded equipment or other equally effective containment procedures.

Before making any change in the traffic pattern, remove or obliterate pavement markings that may create confusion to motorists.

Where using blast cleaning to remove pavement markings or objectionable material within 10 feet of a lane occupied by public traffic, immediately remove the residue (including dust) after contact between the sand and the surface being treated. For such removal, use a vacuum attachment operating concurrently with the blast cleaning operation or by other approved methods.

- Repair any damaged pavement or surfacing caused by the pavement marking removal operation.

670-3.05 PRELIMINARY SPOTTING. Provide the necessary control points at intervals including all changes of direction and changes in the basic configuration of striping, such as at the beginning and ending of no-passing zones on a 2-way, 2-lane roadway. Use these points in preliminary spotting of lines before striping is commenced. Perform preliminary spotting of the lines to be painted and obtain approval for all spotting before striping begins. Preliminary spotting is required for all longitudinal striping, with spacing of spots not to exceed 50 feet.

Reference the lines and markings to be replaced at their existing locations prior to performing any work that may disturb them.

670-3.06 TOLERANCES FOR METHYL METHACRYLATE PAVEMENT MARKINGS.

1.	Length of Stripe. ± 2 inches.

2.	Width of Stripe. ± 1/8 inch.

3.	Lane Width. ± 4 inches from the width shown in the Plans.

4.	Stripes on Tangent. Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves. Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes. Keep the center of the stripe within 4 inches from the planed alignment.

7.	Double Stripes. ± ¼ inches

8.	Thickness of surface applied. Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot. Minimum 250 mils to a maximum of 290 mils.

10.	Thickness of Inlaid Marking Material. Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, or otherwise not to specification, make immediate adjustments to correct the problem.

Methyl methacrylate pavement markings applied by any method will be unacceptable if:

1.	The marking is not straight or wide enough.

2.	The thickness of the line is not uniform or less than specified.

3.	The top of the line is not smooth and uniform.

4.	The material is uncured.

5.	The material blackens or is inconsistent in color.

6.	The inlay slot is not ground to the specified depth.

7.	The inlay slot is not filled to the specified depth.

8.	The edge of the markings are not clear cut and free from overspray.

9.	The reflective elements are not properly embedded.

10.	The markings exhibit poor adhesion.

11.	The retro-reflectivity of the markings is less than specified.

12.	The color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials. Do not perform repairs in a “patch-work” manner. If more than one repair is required in a single 500 foot section, grind and repair the entire section.

## SECTION 682

## UTILITY POTHOLING

682-1.01 DESCRIPTION. Expose subsurface utilities using a vacuum-extract truck. Record the location of the utility(s). Backfill the pothole and dispose of waste materials.

682-2.01 MATERIALS.

Backfill Material:	Aggregate Base Course, Grading D-1	Section 703

Asphalt Patch Material:	Hot Mix Asphalt Type II, Class B		Section 401

682-3.01 CONSTRUCTION. Submit the utility potholing schedule to the Engineer and utility companies not less than 7 days before starting potholing.

- Deliver the vacuum-extract truck to the job-site with the debris tank empty.

Expose the subsurface utilities.  Log the as-built information, Subsection 682-3.02. Backfill the pothole immediately after the Engineer accepts the logged data. Backfill the first 6 inch lift using the excavated material, compact the material. Backfill the balance of the pothole using Aggregate Base Course, Grading D-1, compact the material. In paved areas, use Hot Mix Asphalt Type II, Class B to patch over the pothole, match the thickness of the surrounding pavement.

Dispose of excavations off-site. Before beginning potholing, provide to the Engineer a certificate, signed by the owner or owner's representative, identifying the disposal site and acceptance of the project potholing excavations.

Utilities damaged by the potholing operation require the Engineer to be immediately notified. The Contractor is responsible for the repairs and the associated costs.  Contact and coordinate repairs with the utility owner.

682-3.02 AS-BUILTS. Create a utility pothole log, as-built, recording for each pothole: the date of potholing operation, utility type and size, station, offset, elevation, groundwater, and other pertinent data. Survey the utility location using the project horizontal and vertical control; comply with the requirements of Section 642. Submit the completed log to the Engineer within two working days following the completion of the pothole excavation.

# DIVISION 700 – MATERIALS

## SECTION 701

## HYDRAULIC CEMENT AND SUPPLEMENTARY CEMENTITIOUS MATERIALS

701-1.01 GENERAL. Meet the following general requirements for all cementitious materials furnished:

Before using, retest Portland cement stored longer than 3 months in bags or 6 months in bulk for compressive strength, time of setting, and loss on ignition according to AASHTO M 85. Store separately different types or brands of cementitious materials, or cementitious materials from different mills.

Protect cementitious materials from dampness during shipment and storage. Do not use partially set cement or cement which contains caked lumps. Do not use cement salvaged from discarded or used bags.

701-2.01 PORTLAND CEMENT. Meet AASHTO M 85, Type I, II, or III including the low-alkali cement requirement shown in Table 2.

701-2.02 BLENDED HYDRAULIC CEMENT. Meet AASHTO M 240, Type IP, or Type IS. Report the weight of pozzolan and ground granulated blast furnace slag as percent of weight of the total cementitious material.  Do not vary the pozzolan and ground granulated blast furnace slag constituent content from the certified value more than ±5 percent by weight of the total cementitious material. Limit pozzolan in Type IP to fly ash.  Meet the replacement limits in Table 701-1

- TABLE 701-1

BLENDED HYDRAULIC CEMENT LIMITS

| Cement Type | Constituent | Percent of Total Cementitious Material by Weight |
| --- | --- | --- |
|  |  | Maximum |
| Type IP | Fly Ash | 35% |
| Type IS | Slag cement | 40% |

701-2.03 GROUT. Non-shrink, non-corrosive, non-metallic, cement-based grout meeting ASTM C 1107, except develop a 28-day compressive strength of at least 9,000 psi when tested according to AASHTO T 106 or ASTM C 109.

701-2.04 FLY ASH. Meet AASHTO M 295, Class C or Class F, including optional chemical requirements as set forth in Table 2.

701-2.05 GROUND GRANULATED BLAST-FURNACE SLAG. Meet AASHTO M 302, Grade 100 or Grade 120.

701-2.06 SILICA FUME. Meet AASHTO M 307.

701-2.07 DS GROUT. Use drilled shaft (DS) grout conforming to the following requirements:

1.	Portland Cement Type I or Type II cement meeting the requirements of Subsection 701-2.01.

2.	Fine Aggregate: Use fine aggregate meeting Subsection 703-2.01, except 100 percent passing the No. 4 sieve.

3.	Potable Water: Use water meeting the requirements of Subsection 712-2.01.

4.	Proportioning: Mix grout in proportions using at least 564 lbs/yd3 of Portland cement, fine aggregate, and with enough water to produce a flowable mixture.  Do not exceed 67 gal/yd3 of water.

Thoroughly mix DS grout to a uniform consistency before injecting into soil surrounding drilled shaft casing and filling CSL tubes.

701-2.08 POST-TENSION GROUT. Use pre-packaged thixotropic grout formulated specifically for bonded post-tensioned concrete structures in aggressive exposures.

Ship grout in weather proof packages, plainly marked with the name, weight, and volume of the grout, together with the lot number, date of manufacture, mixing instructions, and the name and address of the manufacturer.

Protect grout against dampness. Do not use grout that has become partially set or which contains lumps of caked grout. Do not use grout salvaged from discarded or used bags. Do not use grout with a total time from manufacture to usage in excess of 6 months unless the manufacturer tests and certifies the product meets the requirements in Table 701-2.

Batch grout using the entire contents of each bag in accordance with all of the manufacturer’s written recommendations and instructions.

- 1.	Materials. Use grout that conforms to the following requirements:

a.	Portland Cement. Type I or Type II cement meeting the requirements of Subsection 701-2.01.

b.	Potable Water. Use water meeting the requirements of Subsection 712-2.01.

c.	Fly Ash. Class C or Class F fly ash meeting the requirements of Subsection 711-2.03. Limit fly ash content to a maximum of 20% by weight of Portland cement.

d.	Ground Granulated Blast Furnace Slag. Grade 120 slag conforming to Subsection 701-2.05. Limit blast furnace slag content to a maximum of 40% of the weight of Portland cement.

e.	Silica Fume. Silica fume conforming to Subsection 701-2.06. Limit silica fume content to a maximum of 15% of the weight of Portland cement.

f.	Set Control and Water-Reducing Admixtures. Type D, Type F, and Type G admixtures conforming to AASHTO M 194. Limit Type F and Type G admixtures to 45 oz. per 100 pounds of Portland cement.

g.	Air Entraining Admixtures. Do not use grout with air entraining admixtures.

h.	Expansion Causing Admixtures. Do not use grout with expansive cement or expansion causing admixtures that contain aluminum powder or components that produce hydrogen, carbon dioxide or oxygen gas.

i.	Corrosion Inhibitor Admixtures. Do not use grout with corrosion inhibitor admixtures.

j.	Pumping Aid Admixtures. Do not use pumping aid admixtures.

- 2.	Physical Properties. Use grout that satisfies the requirements in Table 701-2.

- TABLE 701-2

POST TENSION GROUT

| Property | Requirements | Test Method |
| --- | --- | --- |
| Total Chloride Ions | Max. 0.08% by weight of cementitious materials | ASTM C 1152 |
| Setting Time | Min. 3 hours Max. 12 hours | ASTM C 953 |
| Strength | Min 3000 psi after 7 days Min 5000 psi after 28 days | ASTM C 942 |
| Permeability @ 28 days | Max. 2500 Coulombs at 30 V after 6 hours | ASTM C 1202 |
| Volume Change | Maximum 0.0% after 24 hours Maximum +0.2% after 28 days | ASTM C 1090 (modified)* |
| Expansion | ≤ 2.0 % for up to 3 hours | ASTM C 940 |
| Fluidity | - Immediately after mixing: Min. 9 sec. Max. 20 sec. - 30 minutes after mixing: Max. 30 sec. | ASTM C 939 (modified)** |
| Wick Induced Bleed | Max 0.0% | ASTM C 940 (modified)*** |
| Wet Density | Report maximum and minimum obtained test value in pounds per cubic foot | ASTM C 185 |

*	Modify ASTM C1090 to include verification at both 24 hours and 28 days.

**	Modify the ASTM C 939 test by filling the flow cone to the top instead of to the standard level. The efflux time is the time to fill a one liter container placed directly under the flow cone.

***	Modify ASTM C940 to conform with the wick induced bleed test as follows:

(a)	Use a wick made of a 20-inch length of ASTM A416 seven-wire 1/2 inch diameter strand. Wrap the strand with 2-inch wide duct or electrical tape at each end prior to cutting to avoid splaying of the wires when it is cut. Degrease (with acetone or hexane solvent) and wire brush to remove any surface rust on the strand before temperature conditioning.

(b)	Condition the dry ingredients, mixing water, prestressing strand and test apparatus overnight at 65° F to 75° F.

(c)	Mix the conditioned dry ingredients with the conditioned mixing water and place 800 ml of the resulting grout into the 1,000 ml graduate cylinder. Measure and record the level of the top of the grout.

(d)	Completely insert the strand into the graduated cylinder. Center and fasten the strand so it remains essentially parallel to the vertical axis of the cylinder. Measure and record the level of the top of the grout.

(e)	Store the mixed grout at the temperature range listed above in (b).

(f)	Measure the level of the bleed water every 15 minutes for the first hour and hourly for two successive readings thereafter.

(g)	Calculate the bleed water, if any, at the end of the three hour test period and the resulting expansion per the procedures outlined in ASTM C940, with the quantity of bleed water expressed as a percent of the initial grout volume. Note if the bleed water remains above or below the top of the original grout height. Note if any bleed water is absorbed into the specimen during the test.

701-2.09 CERTIFICATION. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 701-2.09.6;

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

## SECTION 702

## ASPHALT MATERIALS

702-2.01 ASPHALT CEMENTS. Meet AASHTO M 320 and the following:

- ADDITIONAL REQUIREMENTS FOR

Performance Graded AsphaltS

PG 58-28	PG 58-34

Softening Point, min. (AASHTO T 53)	120 oF	125 oF

Toughness, min.       (ASTM D 5801)	110 in-lbs.	110 in-lbs.

Tenacity, min.           (ASTM D 5801)	75 in-lbs.	75 in-lbs.

702-2.02 CUT-BACK ASPHALTS. Meet AASHTO M 81 and M 82 except as follows:

In Table 1 of M 82, reduce the minimum absolute viscosity on residue from distillation at 60 °C to 100, in the MC-30 and MC-250 columns, and revise the maximum distillate percentage by volume of total distillate at 225 °C for MC-30 to read: 35%.

702-2.03 EMULSIFIED ASPHALTS. Meet AASHTO M 140 and the following:

- Cationic Emulsified Asphalt. Meet AASHTO M 208.

Special Tack Emulsion, STE-1. Meet the following, when tested using ASTM D 244:

- TESTS ON EMULSION

Viscosity @ 77 °F, SSF	30, max.

Storage Stability, I day, %	1, max.

Demulsibility, 35 mL 0.8% SDS, %	25, min.

Particle Charge	Positive*

Sieve Test, % Retained	0.10, max.

Distillation Oil by Vol. of Emulsion, %	5, max.

Distillation Residue by Wt. of Emulsion, %	45, min.

- TESTS ON RESIDUE

Penetration @ 77 °F	100-200

Ductility @ 77 °F, 5 cm/min., cm	40, min.

Solubility in TCE, %	97.5, min.

* If particle charge test is inconclusive, material having a max. pH value of 6.7 is acceptable.

702-2.04 STORAGE AND APPLICATION TEMPERATURES. Store, mix, and apply asphalt materials within the following temperature ranges:

- TABLE 702-1

STORAGE AND APPLICATION TEMPERATURES

| Type and Grade of Material | Spray °F | Mix °F | Storage °F |
| --- | --- | --- | --- |
| MC-30 | 85+ |  | 140, max. |
| MC-250 | 165+ | 165-220 | 240, max. |
| RC-800 | 200+ |  | 200, max. |
| CRS-2 | 125-175 |  | 100-175 |
| CMS-2 | 125-175 | 120-160* | 100-175 |
| Type and Grade of Material | Spray °F | Mix °F | Storage °F |
| CSS-1 | 90-120 | 90-160* | 50-125 |
| STE-1 | 70-140 | 70-150 | 50-125 |

*	Temperature of the emulsified asphalt in the pugmill mixture.

** As required to achieve Kinematic viscosity of 150-300 centistokes.

Store, mix, and apply Performance-Graded Asphalt within the temperature ranges recommended by the manufacturer or shown on the approved Job Mix Design.

## SECTION 703

## AGGREGATES

703-2.01 FINE AGGREGATE FOR CONCRETE. Meet AASHTO M 6, Class A, except as follows:

- Delete paragraph 8.2 of AASHTO M 6.

- Delete the following methods of sampling and testing:

AASHTO T 11	Amount of Material Finer than No. 200 Sieve

AASHTO T 27	Sieve Analysis

AASHTO T 103	Soundness (freezing and thawing)

- And substitute the following:

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse Aggregates and Material Finer Than No. 200 Sieve in Mineral Aggregates by Washing

- Add the following: Meet AASHTO T 104 using sodium sulfate solution.

In AASHTO M 6, Section 7.1, table entitled “Deleterious Substances Limits”, change the maximum percent of material by mass finer than No. 200 Sieve in a. (concrete subject to surface abrasion), from 2.0 to 3.0.

703-2.02 COARSE AGGREGATE FOR CONCRETE. AASHTO M 80, class B, except as follows:

- Delete the following methods of sampling and testing:

AASHTO T 11	Amount of Material Finer than No. 200 Sieve

AASHTO T 27	Sieve Analysis

- And substitute the following:

WAQTC FOP for AASHTO T 27/T 11	Sieve Analysis of Fine and Coarse Aggregates and Material Finer Than No. 200 Sieve in Mineral Aggregates by Washing

- Add the following: Meet AASHTO T 104 using sodium sulfate solution.

703-2.03 AGGREGATE FOR BASE AND SURFACE COURSE. Crushed stone or crushed gravel, consisting of sound, tough, durable pebbles or rock fragments of uniform quality. Free from clay balls, vegetable matter, or other deleterious matters. Meet the following requirements:

- TABLE 703-1

| PROPERTY | base COURSE | SURFACE COURSE | TEST METHOD |
| --- | --- | --- | --- |
| L.A. Wear,% | 50, max. | 45, max. | AASHTO T 96 |
| Degradation Value | 45, min. | 45, min. | ATM 313 |
| Fracture,% | 70, min. | 70, min. | WAQTC FOP for AASHTO TP 61 |
| Liquid Limit | --- | 35, max. | WAQTC FOP for AASHTO T 89 |
| Plastic Index | 6, max. | 10, max. | WAQTC FOP for AASHTO T 90 |
| Sodium Sulfate Loss,% | 9, max. (5 cycles) | 9, max. (5 cycles) | AASHTO T 104 |

Meet the following gradations, as determined by WAQTC FOP for AASHTO T 27/T 11:

- TABLE 703-2

AGGREGATE FOR BASE AND SURFACE COURSE

Percent Passing By Weight

| SIEVE | GRADATION |  |  |  |
| --- | --- | --- | --- | --- |
|  | BASE COURSE |  | SURFACE COURSE |  |
|  | C-1 | D-1 | E-1 | F-1 |
| 1-1/2 in. | 100 |  |  |  |
| 1 in. | 70-100 | 100 | 100 | 100 |
| 3/4 in. | 60-90 | 70-100 | 70-100 | 85-100 |
| 3/8 in. | 45-75 | 50-79 | 50-85 | 60-100 |
| No. 4 | 30-60 | 35-58 | 35-65 | 50-85 |
| No. 8 | 22-52 | 20-47 | 23-50 | 40-70 |
| No. 30 | 10-33 | 10-26 | 13-31 |  |
| No. 50 | 6-23 | 6-19 | 10-26 | 25-45 |
| No. 200 | 0-6 | 0-6 | 8-15 | 8-20 |

703-2.04 AGGREGATE FOR HOT MIX ASPHALT PAVEMENT. Process and crush aggregate that is free from clay balls, organic matter, other deleterious material, and not coated with dirt or other finely divided mineral matter. Aggregate used must consist of sound, tough, durable rock of uniform quality.

Remove all natural fines passing a No. 4 sieve before crushing aggregates for Types IV, V, and R mixtures.

Coarse Aggregate (retained on the No. 4 sieve). Meet the following requirements:

| L.A. Wear, % | AASHTO T 96 | 45, max. |
| --- | --- | --- |
| Degradation Value | ATM 313 | 30, min. |
| Sodium Sulfate Loss,% | AASHTO T 104 | 9, max. (5 cycles) |
| Fracture,% | WAQTC FOP for AASHTO TP 61 | 80, min. (single face) |
| Flat - Elongated Pieces,% | ATM 306 | 8, max. |
| Nordic Abrasion, % | ATM 312 | 8.0, max. |
| Absorption, % | AASHTO T 85 | 2.0, max. |

Fine Aggregate (passing the No. 4 sieve). Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

Blended Aggregate. Blend the aggregate fractions to meet the grading requirements of Table 703-3, as determined by WAQTC FOP for AASHTO T 27/T 11. Ensure that the fraction actually retained between any two consecutive sieves larger than the No. 100 sieve is not less than 2% of the total.

Aggregate for Type II, Class A, mix shall not contain more than 10% natural fines (blend sand and mineral filler) added to the crushed aggregate. Aggregate for Types IV, V, and R mixes will not blend back natural sand; shall be non-plastic as determined by WAQTC FOP for AASHTO T 90; shall have a minimum uncompacted void content (Fine Aggregate Angularity) determined by AASHTO T 304, Method A, of 45%.

- TABLE 703-3

BROAD BAND GRADATIONS FOR HOT MIX ASPHALT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V | Type R |
| 1 in. | 100 | - | - | - | - | - |
| 3/4 in. | 80-90 | 100 | - | - | 100 | 100 |
| 1/2 in. | 60-84 | 75-90 | 100 | 100 | 65-90 | 70-100 |
| 3/8 in. | 48-78 | 60-84 | 80-90 | 80-95 | 55-80 | 50-70 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 40-60 | 30-42 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | < 45 | 20-32 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | < 35 | 15-25 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | < 25 | 10-20 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | < 20 | 7-15 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | < 12 | 5-12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 4-8 | 3-8 | 4-10 |

Notes:

1. No tolerance is allowed beyond the Broad Band Limits of No. 200 Sieve

2. For Type R, the mix design gradation JMD shall provide a minimum of 8% difference passing the No.4 and No.8 sieve.

703-2.05 AGGREGATE FOR COVER COAT AND SURFACE TREATMENT. Crushed stone or crushed gravel, consisting of sound, tough, durable pebbles or rock fragments of uniform quality. Free from clay balls, vegetable matter, or other deleterious matters, and with no adherent films or coatings of dirt, clay, dust or other deleterious matter that could impede adherence of the bituminous material. Wash the aggregate if necessary. Meet the following requirements:

| L.A. Wear,% | AASHTO T 96 | 45, max. |
| --- | --- | --- |
| Degradation Value | ATM 313 | 50, min. |
| Sodium Sulfate loss,% | AASHTO T 104 | 9, max. (5 cycles) |
| Fracture,% | WAQTC FOP for AASHTO TP 61 | 90, min. (single face) |

At least 15 days before beginning work, submit a representative 30-pound sample of the aggregate and 1-quart sample of the bituminous material proposed for use in the work. The Department will test the materials using ATM 414 as submitted (that is, without addition of anti-stripping additives). The Department will reject materials failing to meet or exceed 70% retention of the asphalt, unless you provide approved anti-stripping additives or employ other approved measures which correct this deficiency.

Cover Coat Material. Meet the gradation requirements of Table 703-4, as determined by WAQTC FOP for AASHTO T 27/T 11.

- TABLE 703-4

REQUIREMENTS FOR GRADING OF COVER COAT MATERIAL

Percent Passing By Weight

| SIEVE | TYPE 2 COVER | TYPE 3 COVER AGGREGATE |  |  |
| --- | --- | --- | --- | --- |
|  | AGGREGATE | Grading A | Grading B | Grading C |
| 1/2 in. | -- | -- | -- | 100 |
| 3/8 in. | 100 | 100 | 100 | 90-100 |
| No. 4 | 85-100 | 85-100 | 60-100 | 10-30 |
| No. 8 | -- | 0-25 | 0-10 | 0-8 |
| No. 50 | 0-20 | -- | -- | -- |
| No. 200 | 0-1 | 0-1 | 0-1 | 0-1 |

Surface Treatment Material. Meet the gradation requirements of Table 703-5, as determined by WAQTC FOP for AASHTO T 27/T 11.

- TABLE 703-5

REQUIREMENTS FOR GRADING OF AGGREGATE FOR ASPHALT SURFACE TREATMENT

| SIEVE | GRADING Percent Passing by Weight |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | A | B | C | D | E | F | G |
| 1-1/2 in. | 100 | -- | -- | -- | -- | -- | -- |
| 1 in. | 90-100 | 100 | -- | -- | -- | -- | -- |
| 3/4 in. | -- | 90-100 | 100 | -- | -- | -- | -- |
| 1/2 in. | 0-15 | 20-55 | 90-100 | 100 | 100 | -- | -- |
| 3/8 in. | -- | 0-15 | 40-75 | 90-100 | 90-100 | 100 | 100 |
| No. 4 | -- | -- | 0-15 | 0-10 | 10-30 | 75-100 | 85-100 |
| No. 8 | -- | -- | 0-5 | 0-5 | 0-8 | 0-10 | 60-100 |
| No. 200 | 0-1 | 0-1 | 0-1 | 0-1 | 0-1 | 0-1 | 0-10 |

703-2.06 MINERAL FILLER. Meet AASHTO M 17.

703-2.07 SELECTED MATERIAL. Meet the following requirements for the type specified. Obtain the Engineer’s approval for the intended purpose, prior to use on the project.

1.	Type A. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

Sieve	Percent Passing by Weight

No. 4	20-55%

No. 200	0-6%, determined on the minus 3-inch portion of the sample

2.	Type B. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

Sieve	Percent Passing by Weight

No. 200	0-10% determined on the minus 3-inch portion of the sample

3.	Type C. Earth, sand, gravel, rock, or combinations thereof containing no muck, peat, frozen material, roots, sod, or other deleterious matter and is compactable under the provisions of Subsections 203-3.04 or 203-3.05.

703-2.08 FILTER BLANKET. Meet AASHTO M 80, Class A. Meet the following gradation: AASHTO M 43, size No. 467.

703-2.09 SUBBASE. Hard, durable particles or fragments of stone or gravel. Do not use materials that break up when alternately frozen and thawed or wetted and dried. Do not include muck, frozen material, roots, sod, or other deleterious matter. Meet the following requirements:

L.A. Wear,%	AASHTO T 96	50 max.

Liquid Limit	WAQTC FOP for AASHTO T 89	25 max.

Plasticity Index	WAQTC FOP for AASHTO T 90	6 max.

Degradation	ATM 313	40 min.

- Meet the grading requirements of Table 703-6 (WAQTC FOP for AASHTO T 27/T 11).

Grading C and Grading D: Crushed aggregate with at least 50% by weight of the particles retained on the No. 4 sieve having at least one fractured face as tested by WAQTC FOP for AASHTO TP 61.

- TABLE 703-6

REQUIREMENTS FOR GRADING FOR SUBBASE

Percent Passing by Weight

| SIEVE | GRADING |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | A | B | C | D | E |
| 4 in. | 100 | -- | -- | -- | -- |
| 2 in. | 85-100 | 100 | -- | -- | -- |
| 1 in. | -- | -- | 100 | -- | -- |
| 3/4 in. | -- | -- | -- | 100 | -- |
| No. 4 | 20-55 | 20-55 | 40-75 | 45-80 | -- |
| No. 16 | -- | -- | 20-43 | 23-50 | -- |
| No. 200 * | 10 Max. | 0-6 | 4-10 | 4-12 | 0-6 |

* Gradation shall be determined on that portion passing the 3-inch screen.

703-2.10 POROUS BACKFILL MATERIAL. Gravel consisting of crushed or naturally occurring granular material containing not more than 1% clay lumps or other readily decomposed material (AASHTO T 112). Meet the grading requirements of Table 703-7 (WAQTC FOP for AASHTO T 27/T 11).

- TABLE 703-7

REQUIREMENTS FOR GRADING FOR POROUS BACKFILL MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3 in. | 100 |
| 1 in. | 0-10 |
| No. 200 | 0-5 |

703-2.11 GABION BACKFILL. Stone and gravel, uniformly graded from 4 to 12 inches in least dimension and having no more than 60% wear (AASHTO T 96).

703-2.12 SAND BLANKET. Sand containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as determined by WAQTC FOPs for AASHTO T 89 and T 90. Meet the grading requirements of Table 703-8 as determined by WAQTC FOP for AASHTO T 27/T 11:

- TABLE 703-8

REQUIREMENTS FOR GRADING FOR SAND BLANKET MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3/8 in. | 100 |
| No. 4 | 95-100 |
| No. 200 | 0-6 |

703-2.13 STRUCTURAL FILL. Aggregate containing no muck, frozen material, roots, sod or other deleterious matter and with a plasticity index not greater than 6 as tested by WAQTC FOPs for AASHTO T 89 and T 90. Meet the following gradation as tested by WAQTC FOP for AASHTO T 27/T 11:

- TABLE 703-9

REQUIREMENTS FOR GRADING FOR STRUCTURAL FILL MATERIAL

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| 3 in. | 100 |
| 3/4 in. | 75-100 |
| No. 4 | 35-65 |
| No. 50 | 0-30 |
| No. 200 | 0-6 |

703-2.14 AGGREGATE FOR ABRASIVE FINISH. Crushed silica sand, oven dried, and stored in moisture-proof bags. Free from clay balls, vegetative matter, or other deleterious matters (AASHTO T 112). Not coated with dirt or other finely divided mineral matter. Meet the grading requirements of Table 703-10 (WAQTC FOP for AASHTO T 27/T 11).

- TABLE 703-10

REQUIREMENTS FOR AGGREGATE FOR ABRASIVE FINISH

| SIEVE | PERCENT PASSING BY WEIGHT |
| --- | --- |
| No. 12 | 100 |
| No. 50 | 0-5 |

703-2.15 CRUSHED GLASS. Up to 10% by weight crushed glass (cullet) smaller than 3/8-inch may be uniformly blended with natural soil-aggregate material prior to project delivery and placement. Glass cullet must be free of soil, paper, plastic, metals, organic material and other deleterious and hazardous substances. No more than 2.0% debris should be present as determined by Section X3 of AASHTO M318.

Eligible glass products from which glass cullet might be produced include: food and beverage container glass; plain ceramic or china dinnerware; or building window glass.

Prohibited glass products include: automobile windshields or other glass from automobiles; light bulbs of any type; porcelain products; laboratory glass; television, computer or other cathode ray monitor tubes.

Provide documentation certifying that the glass cullet:

- Showing the origin of the glass products,

- Does not contain prohibited materials,

- Meets debris content requirement.

Uniformly blend glass cullet and natural soil-aggregate and meet the following gradation requirements for the type specified:

- TABLE 703-13

| Type (Section) | Section/Table |
| --- | --- |
| Selected material (203-3.03) | Section 703-2.07 |
| Base course (301) | Table 703-2 |
| Subbase (304) | Table 703-8 |

For the natural soil-aggregate used in the blend, meet quality requirements as shown in Table 703-1, Section 703-2.07, or Section 703-2.09 for the type specified.

## SECTION 704

## MASONRY UNITS

704-2.01 CLAY OR SHALE BRICK. Meet one of the following specifications:

Sewer Brick	AASHTO M 91, Grade SM or SS

Building Brick 	AASHTO M 114, Grade MW

704-2.02 CONCRETE BRICK. Meet ASTM C 55, Grade N.

704-2.03 CONCRETE MASONRY BLOCK. Meet ASTM C 90. Use rectangular or segmented block, When shown on the Plans, shape ends to provide interlock at vertical joints. Meet the dimensions and tolerances shown on the Plans.

## SECTION 705

## JOINT MATERIALS

705-2.01 JOINT FILLERS. Meet AASHTO M 213.

705-2.02 JOINT SEALER.

Silicone Joint Sealer	ASTM D 5893

Hot Pour Joint Sealer (Asphalt)	AASHTO M 324, Type IV

Hot Applied Joint Sealer (Concrete)	AASHTO M 282

Hot Pour Joint Sealant (Concrete, Fuel-Resistant)	ASTM	D 3581

705-2.03 BRIDGE SEALS.

1.	Preformed Strip Seals and Compression Seals. Use preformed seals constructed with only virgin natural polyisoprene (natural rubber) as the raw polymer in the elastomeric compound. Do not use polychloroprene (neoprene). Use steel extrusions meeting ASTM A 709 Grade 36. Galvanize steel extrusions in accordance with Subsection 716-2.07. Use preformed material meeting the following requirements of ASTM D 2000:

- M4AA 514 A13b13c12f17

Use a lubricant-adhesive for installing preformed strip seals and compression seals meeting ASTM D4070.

a.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

(1)	the project name and number;

(2)	the manufacturer's name;

(3)	the name of the product or assembly;

(4)	a complete description of the material;

(5)	country of origin;

(6)	the lot, heat, or batch number that identifies the material;

(7)	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 705-2.03.1.a.(6);

(8)	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

2.	Silicone Expansion Joint Seals. Use materials that conform to the following:

a.	Silicone Joint Sealants.

(1)	Horizontal Joints.  Use formed-in-place sealant composed of 100 percent silicone that is self-leveling, cold applied, and two-part formulation meeting the requirements in Table 705-1.

(2)	Vertical Joints.  Use formed-in-place sealant composed of 100 percent silicone meeting the requirements of ASTM D 5893, Type NS (Non-Sag). Do not use acid cure sealants.  Ensure the silicone sealant is compatible with the surface to which it is applied.

b.	Bond Breaking Backing Material. Use closed-cell expanded polyethylene foam backer rod meeting the requirements of ASTM D 5249.

- TABLE 705-1

SELF-LEVELING SEALANT REQUIREMENTS

| PROPERTY | REQUIREMENTS | TEST METHOD |
| --- | --- | --- |
| Extrusion Rate | Min, 50 mL/minute | ASTM C 1183 (type S) |
| Specific Gravity | Min. 1.25 Max. 1.35 | ASTM D 1475 |
| Joint Elongation | Min. 600% | ASTM D 5329 (modified)* |
| Joint Modulus (at 100% elongation) | Min. 3 psi Max. 12 psi | ASTM D 5329 (modified)* |

*	Modify the ASTM D5329 test by using a pull rate of 2 inches per minute and a joint size of 1/2 inch x 1/2 inch x 2 inch.

705-2.04 JOINT MORTAR. Use a mixture of one part Portland cement and two parts approved sand with water as necessary to obtain the required consistency. Use mortar within 30 minutes after its preparation.

705-2.05 FLEXIBLE WATERTIGHT GASKETS.

1.	Ring gaskets for rigid pipe and precast manhole sections meeting AASHTO M 198.

2.	Ring gaskets for flexible metal pipe meeting ASTM C 443. Continuous flat gaskets for flexible metal pipe meeting ASTM D 1056, Grade 2B3. Use gaskets with a thickness 1/2 inch greater than the nominal depth of the corrugation for bands with projections or flat bands and 3/8 inch for corrugated bands.

705-2.06 EXPANDED POLYETHYLENE. Use closed-cell expanded polyethylene with a density of at least 2.1 lb/ft3 as determined by ASTM D3575 and with a minimum compressive stress of 9 psi at 25% deflection as determined by ASTM D3575.

705-2.07 High Molecular Weight Methacrylate (HMWM) Resin. Meet the following:

Viscosity, min.:	25 cps (Brookfield RVT w/UL adapter, 50 rpm at 75 °F (CA Test 434)

Density:	8.5 to 8.75 lb/gal at 75 °F (ASTM D 1475)

Flash Point, min.:	200 °F PMCC (Pinsky-Martens CC)

Vapor Pressure, max.:	0.04 in. Hg at 75 °F (ASTM D 323)

Tg (DSC), min.:	135 °F (ASTM D 3418)

Gel Time, min.:	60 minutes

- Use a promoter/initiator system for the HMWM resin consisting of a metal dryer and peroxide.

## SECTION 706

## CONCRETE AND PLASTIC PIPE

706-2.01 NON-REINFORCED CONCRETE PIPE. Meet AASHTO M 86.

706-2.02 REINFORCED CONCRETE PIPE. Meet the following:

Round Pipe	AASHTO M 170, “Wall B”

Elliptical Pipe	AASHTO M 207

706-2.03 PERFORATED CONCRETE PIPE. Meet AASHTO M 175.

706-2.04 DRAIN TILE. Meet AASHTO M 178. When specified, provide integral spacer lugs in the pipe spigot to provide for an annular opening and self-centering feature.

706-2.05  PVC PIPE FOR WATER AND SANITARY SEWER SYSTEMS. Use Polyvinyl Choloride (PVC) pipe systems manufactured from a compound that meets ASTM 1784 with a cell classification of 12454B. Ensure the entire pipe system is made of materials with a 150 psi rated working pressure. Use pipe with push on type joints and an exterior size compatible with ductile iron fittings. Meet the following:

PVC Pipe	ANSI/AWWA	C 900 or C905

PVC Fittings	ANSI/AWWA	C 907

Rubber Gasket	ASTM		F477

Joints	ASTM 		D3139

706-2.06 PLASTIC PIPE. Semi-rigid, smooth-wall pipe meeting the following:

Polyethylene (PE)	AASHTO M 294, Type S or Type D

Polyvinyl Chloride (PVC)	AASHTO M 264 or M 278

Acrylonitrile-Butadine-Styrene (ABS)	AASHTO M 264

706-2.07 GALVANIZED STEEL WATER CONDUIT. Meet the following:

Galvanized Pipe	ASTM A 53 or ASTM A 120, galvanized per AASHTO M 111

Galvanized Fittings 	ASTM A 234 galvanized per AASHTO M 232

706-2.08 HDPE PIPE FOR WATER AND SANITARY SEWER SYSTEMS. Use high density polyethylene (HDPE) pipe and fittings manufactured from a PE 3408 resin that meets ASTM D3350 with a cell classification of 345464C. Ensure the entire system is made of materials with a 150 psi rated working pressure, except material two inch or less in diameter shall have a 200 psi rated working pressure. Join all pipe and fittings by either butt fusion or flanges as per manufacturers recommendation. No mechanical joints are allowed. Meet the following:

HDPE Pipe 2” or less	ASTM	D2737

HDPE Pipe over 2”	ASTM 	F714

Butt Fusion Fittings 	ASTM 	D3261

Flanged joints 		ASTM 	D3261

When HDPE pipe is used in arctic applications:

1.	Protect by using a thaw wire, control system, and power supply designed by an Electrical Engineer, and meeting the requirements of Section 616; except use heating cable consisting of 10 AWG nickel-plated copper bus wires in a self-regulated polymeric core, with a continuous exposure capability of 150F;

2.	Surround with a minimum of three inch thick polyurethane insulation; and

3.	Provide an outer surfacing of 24 gauge galvanized steel or 16 gauge aluminum.

## SECTION 707

## METAL PIPE

707-2.01 CORRUGATED STEEL PIPE, PIPE ARCHES, AND UNDERDRAINS. Meet AASHTO M 36 for conduits and coupling bands including special sections such as elbows and flared end sections. Meet the specified sectional dimensions and gages. Furnish shop-formed elliptical pipe where specified. Fabricate pipe using one of the following:

1.	Zinc-coated steel meeting AASHTO M 218

2.	Aluminum-coated steel meeting AASHTO M 274

3.	Aluminum-zinc alloy coated steel meeting AASHTO M 289

707-2.02 BITUMINOUS COATED CORRUGATED STEEL PIPE, PIPE ARCHES, AND UNDERDRAINS. Meet AASHTO M 190 for conduits and coupling bands. Meet the specified sectional dimensions, gages, and type of bituminous coating. Fully coat coupling bands with bituminous material. Furnish shop-formed elliptical pipe where specified.

Use the same gage of steel for special sections, such as elbows and flared end sections, as the conduit to which they are joined. Meet the requirements of AASHTO M 190. Use the type of coating and invert paving specified.

Meet the specified minimum size of perforations after coating.

707-2.03 CORRUGATED ALUMINUM ALLOY CULVERT PIPE AND UNDERDRAINS. Meet AASHTO M 196.

707-2.04 STRUCTURAL PLATE CULVERTS. Meet the following:

Steel or iron plates	AASHTO M 167

Aluminum alloy 	AASHTO M 219

707-2.05 DUCTILE IRON PIPE FOR WATER AND SANITARY SEWER. Use ductile iron pipe and fittings that are bituminous coated, cement mortar lined, have push on type joints, and a 150 psi working pressure. Meet the following:

Cement mortar lining			ANSI/AWWA	C104

Loose Polyethylene Encasement 	ANSI/AWWA	C105	(8 mil when required)

Ductile Iron Fittings			ANSI/AWWA	C110 or C153, and C104

SBR Rubber Gaskets			ANSI/AWWA	C111	(Push on or mech. joint)

Threaded Flange Joints			ANSI/AWWA	C115

Ductile Iron Pipe			ANSI/AWWA	C150 and C151 and C104

707-2.06 SERVICE PIPE. Meet the following:

1.	Copper Pipe. Cold drawn, seamless, annealed Type “K” with flare fittings meeting ASTM B 88.

2.	Steel Pipe. Standard weight, Grade B, galvanized, welded or seamless pipe meeting ASTM A 53.

707-2.07 GALVANIZED STEEL WATER CONDUIT. Meet the following:

Galvanized Pipe	ASTM A 53 or ASTM A 120, galvanized per AASHTO M 111

Galvanized Fittings 	ASTM A 234 galvanized per AASHTO M 232

## SECTION 708

## PAINTS

708-1.01 General Requirements. Ship paint in strong, substantial containers, plainly marked with the name, weight, and volume of the paint content, together with the color formula, batch number, and the name and address of the manufacturer.

- Store materials in a closed weather proof, dry shelter at all times.

Have the paint manufacturer furnish samples of the actual batches of paint supplied for the project for independent laboratory testing of chemical composition.

Use reduction and clean up thinners approved by the coating manufacturer. Measure and document all thinner reduction with records provided to the Engineer. Ship all thinners in their manufacturer’s original containers.

708-2.01 PAINT FOR STEEL STRUCTURES.

1.	Prime Coat. A single component, moisture cure, polyurethane (SC-MC-U) using zinc dust pigment, meeting the following:

zinc powder	78% by weight, min.

volume of solids	60% min.

zinc in dry film	83% minimum, by weight (ASTM D 521)

weight per gallon	23 pounds, min.

VOCs	3.75 pounds per gallon, max.

2.	Intermediate Coat. A single component, moisture cure, polyurethane (SC-MC-U). Pigment color must contrast with the prime coat and the top coat. Meet the following:

micaceous iron oxide (MIO)	3.3 pounds per gallon, min. (ASTM D 5532, Type I)

volume of solids	60% min.

weight per gallon	12.5 pounds min.

VOCs	3.75 pounds per gallon, max.

3.	Top Coat. A single component, moisture cure, aliphatic polyurethane (SC-MC-ALIP-U). Pigment color FSS FED-STD-595B, color number 26492. Evaluate the color match as a general match under a daylight source using ASTM D 1729. Meet the following:

micaceous iron oxide (MIO)	3.3 pounds per gallon, min. (ASTM D 5532, Type I)

Volume of solids	60% min.

Weight per gallon	12 pounds min.

VOCs	3.75 pounds per gallon, max.

All coatings must pass the following tests:

Corrosion Resistance, ASTM B 117, Salt Spray Test. Minimum of 5000 hours with less than 1/16 inch creep from scribe. Use 1/8 inch minimum thickness ASTM A 36 steel panels, having SSPC-SP 10 Near White Blast with 1 to 2 mils angular profile.

Accelerated Weathering, ASTM G 53. Minimum 400 hours QUV B bulb with no chalking, cracking, or gloss loss greater than 20%.

- Forward Impact, ASTM D 2794. Minimum 150 in-lb impact.

- Abrasion Resistance, ASTM D 4060. Less than 90 mg loss on CS-17 wheel, 1 kg/load, 1000 cycles.

- Moisture Resistance, ASTM D 4585. Minimum 1000 hours at 100 °F with no change in appearance.

Flexibility, ASTM D 522, Cylindrical Mandrel Bend Test. Bend around 1/2 inch diameter mandrel with no cracking.

- Adhesion, ASTM D 4541. Minimum 500 psi on a certified pull test.

Cyclic Weathering, ASTM D 5894. Minimum 5000 hours, 15 cycles with less than 1/16 inch creep from scribe. Use 1/8 inch minimum thickness ASTM A 36 steel panels, having SSPC-SP 10 Near White Blast with 1 to 2 mils angular profile.

708-2.02 PAINT FOR TIMBER. Meet FSS TT-P-19D(1), Paint, Latex (Acrylic Emulsion, Exterior).

708-2.03 PAINT FOR TRAFFIC MARKINGS. Use one of the following:

1.	AASHTO M 248, Type F (Alkyd Resin), or

2.	FSS TT-P-19D(1) Paint, Latex (Acrylic Emulsion, Exterior), or

3.	The current State of Alaska DOT&PF maintenance specification for pavement marking paint.

708-2.04 PAINT FOR CONCRETE. Meet FSS TT-P-19D(1), Paint, Latex (Acrylic Emulsion, Exterior).

## SECTION 709

## REINFORCING STEEL AND WIRE ROPE

709-2.01 REINFORCING STEEL.

1.	Reinforcing Steel Bars. Furnish deformed reinforcing steel bars of the type, grade, and size as specified. For steel reinforcing bars used in bridge structures, use bars meeting ASTM A 706, Grade 60. For all other structures, use bars meeting AASHTO M 31, Grade 60.

2.	Headed Reinforcing Steel Bars. Furnish headed reinforcing steel bars meeting the requirements of ASTM A 970, Class HA. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

3.	Epoxy-Coated Reinforcing Steel Bars. Furnish epoxy-coated steel bars meeting the requirements of ASTM 775. Coat epoxy-coated reinforcing steel in an epoxy coating applicator plant certified in accordance with the Concrete Reinforcing Steel Institute (CRSI) Voluntary Certification Program. Use reinforcing steel meeting Section 709-2.01.1 unless otherwise noted.

4.	Steel Wire. Furnish plain steel wire of the size specified that meets the requirements of AASHTO M 32.

5.	Steel Bar Mats. Furnish deformed steel bar mats of the type, grade, size, and spacing as specified. Unless otherwise noted, furnish steel bar mats meeting the requirements of AASHTO M 54, Grade 60.

6.	Steel Welded Wire Fabric. Furnish plain steel welded wire fabric of the size and spacing specified that meets the requirements of AASHTO M 55.

7.	Epoxy-Coating Patch Material. Furnish epoxy-coating patch material meeting the requirements of ASTM D 3963.

8.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 709-2.01.8.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

709-2.02 WIRE ROPE OR WIRE CABLE. Meeting AASHTO M 30, 3/4 inch Type 1, Class A.

709-2.03 BAR SUPPORTS.

1.	Precast Mortar Blocks. Provide mortar blocks meeting the following:

a.	Ensure the mortar blocks have compressive strength at least equal to the strength of the concrete in which the mortar blocks are embedded. Sample and test the mortar for compressive strength according to AASHTO T 106. Each test will be considered to represent no more than 2,500 mortar blocks made of the same mortar and cured under the same conditions.

b.	Ensure the bearing area of the mortar block is less than 2 inches in each dimension.

c.	Secure to the reinforcing steel with either a grooved top that will hold the bar in place or a protruding embedded wire that is tied to the reinforcing steel.

2.	Metal Supports. Provide metal supports meeting at least one of the following:

a.	Galvanized after fabrication according to AASHTO M 232 Class D,

b.	Stainless steel meeting the requirements of ASTM A 493, Type 302, or

c.	Plastic coated using coatings that do not react chemically with the concrete, have a minimum thickness of 3/32 inch where the support touches the form, do not crack at or above -5°F, and do not deform enough to expose the metal at or below 200°F.

3.	Plastic Supports. Provide plastic supports meeting the following:

a.	Non-porous.

b.	Chemically inert in concrete.

c.	Have rounded seats.

d.	Do not deform under load during normal temperatures.

e.	Do not shatter or crack under impact loading in cold weather.

f.	Have at least 25 percent of their gross area perforated.

Do not use plastic supports that prevent complete concrete consolidation in and around the support or require supports less than 1 foot apart along the length of the bar.

## SECTION 710

## FENCE AND GUARDRAIL

710-2.01 BARBED WIRE. Meet AASHTO M 280, 12.5 gage wire, with 4-point round 14-gage barbs, spaced at 5 inches, Class 1 coating.

710-2.02 WOVEN WIRE. Meet AASHTO M 279, Grade 60, Class 1 coating.

710-2.03 CHAIN LINK FABRIC. Meet AASHTO M 181, Type I (Class C or D coating), Type II, or Type III, including fittings and hardware. Use 9-gage fabric wire, 2-inch mesh.

710-2.04 METAL BEAM RAIL. Meet AASHTO M 180-00, Class A, Type II. Galvanize the rail per ASTM A653 after factory roll formed and punched.

710-2.05 FENCE POSTS. Meet AASHTO M 181, Grade 1 or Grade 2, including rails and braces.

710-2.06 GUARDRAIL POSTS AND BLOCKS. Furnish posts and blocks, as specified, meeting the following requirements.

- Wood Posts and Blocks. Use timber with a stress grade of 1200 psi or more. Testing must meet the standards of the West Coast Lumber Inspection Bureau. Use timber for posts and blocks that is either rough sawn (unplaned) or S4S with nominal dimensions indicated. Allowable size tolerance of rough sawn blocks in the direction of the bolt holes is ±1/4 inch. Only one combination of post and block finish may be used for any one continuous length of guardrail. Treat all timber to meet Section 714.

- Steel Posts and Blocks. Meet the section and length specified or shown on the Plans. Use copper bearing steel when so specified. Use steel meeting the requirements of ASTM A 36 and galvanized per ASTM A 123/A.

- Synthetic Blocks. Products made from alternate materials may be used if accepted by the FHWA for use on the National Highway System.

710-2.07 GUARDRAIL HARDWARE. Meet AASHTO M 180. Galvanize after fabrication fittings, bolts, washers, and accessories meeting AASHTO M 111 or AASHTO M 232, whichever applies.

710-2.08 WIRE MESH. Galvanized 2-inch mesh (poultry netting), 20 gage wire.

710-2.09 ANCHOR WIRE. Galvanized 9 gage steel wire.

710-2.10 PIPE COUPLINGS. Galvanized nonrecessed, taper tapped, extra heavy couplings.

710-2.11 GUARDRAIL TERMINALS. Meet coating requirements of AASHTO M 180, Class A, Type II. Galvanize after fabrication. Fabrication includes forming, cutting, shearing, punching, drilling, bending, welding and riveting. Provide one of the following terminal types, as shown on the plans, for single-rail W-beam guardrail. Provide terminals that pass NCHRP 350 or MASH Test Level 3 and meet the following requirements:

- Controlled Release Terminal. Meet the requirements of Standard Drawing G-25.

- Parallel Terminal.

  - Requirements:

    - Crashworthiness: Provide terminals that pass NCHRP 350 or MASH Test Level 3.

    - Length: 50 feet.

    - End Offset: 0 to 2 feet (25:1 or flatter straight taper) Offset end as shown on the plans.

    - Posts: Use posts that are:

          - Steel post with hinge or

          - Yielding or breakaway steel post in steel tube

  - Acceptable models include the following or approved equivalent:

    - Sequential Kinking Terminal (SKT) manufactured by Road Systems, Inc., 3616 Old Howard County Airport, Big Spring, Texas 79720, Telephone 432-263-2435.

    - Extruder Terminal (ET-Plus) manufactured by Trinity Highway Products, L.L.C., 950 West 400 South, Centerville, Utah 84014, Telephone 801-292-4461.

  - Install AASHTO M 268, Type III, IV, or V retro-reflective sheeting (2.0 square feet, minimum) on the end section of parallel terminals consisting of yellow and black bars sloping 45 degrees downward toward the traffic side of the terminal.

- Buried in Backslope Terminal: Meet the requirements of Standard Drawing G-15.

## SECTION 711

## CONCRETE CURING MATERIALS 
AND ADMIXTURES

711-2.01 CURING MATERIALS.

Burlap Cloth made from Jute or Kenaf	AASHTO M 182

Sheet Materials for Curing Concrete	AASHTO M 171

Liquid Membrane-Forming

Compounds for Curing Concrete	AASHTO M 148, Type I, except do not use compounds containing linseed oil.

711-2.02 CHEMICAL ADMIXTURES.

Air-Entraining Admixtures	AASHTO M 154

Water-Reducing Admixtures	AASHTO M 194

Set-Retarding Admixtures	AASHTO M 194

Set-Accelerating Admixtures	AASHTO M 194

711-2.03 FLY ASH. Class C or Class F meeting AASHTO M 295, including optional requirements, except change:

1.	Moisture content to 1% maximum.

2.	Amount retained on the No. 325 sieve to 30% maximum.

711-2.04 MICROSILICA ADMIXTURE. Meet AASHTO M 307, as modified below:

- Table 1 Chemical Requirements

Loss on Ignition, max., %	4.0

Add the following:

Other compounds, total*, max., %	7.0

* Includes aluminum, ferric, magnesium, and calcium oxides

- Table 3 Physical Requirements

Add the following:

Specific Surface Area, min.	15 m2/g

(ASTM C 1069)

## SECTION 712

## MISCELLANEOUS

712-2.01 WATER. Use water in mixing or curing concrete that is clean and free of oil, salt, acid, alkali, sugar, vegetable or other substances injurious to the finished product. Meet the suggested requirements of AASHTO T 26. Use mix water that contains less than 500 parts per million of chlorides as CI or of sulphates as SO4. Water known to be of potable quality will not require testing. Where the source of water is relatively shallow, enclose the intake to exclude silt, mud, grass, or other foreign materials.

- Use water for irrigating trees, plants, and seeded areas that is free of elements harmful to plant growth.

712-2.02 CALCIUM CHLORIDE. AASHTO M 144.

712-2.03 LIMESTONE. Use limestone containing not less than 85% of calcium and magnesium carbonates. Meet the standards of the Association of Official Agricultural Chemists. Meet the following gradation for agricultural ground limestone suitable for application by a fertilizer spreader:

| Sieve | Percent Passing, by Weight, Min. |
| --- | --- |
| No. 10 | 100 |
| No. 20 | 90 |
| No. 100 | 50 |

Use soluble or ground limestone in a hydraulic sprayer. Ground limestone must permit complete suspension of insoluble particles in water.

712-2.04 PRECAST CONCRETE CURBING. Portland cement concrete curb units conforming to the lengths, shapes, and other details of the Plans. Use steel reinforcement, where shown on the Plans, meeting Subsection 709-2.01.

Furnish a depressed or modified section of curb, when shown on the Plans, for driveways, crossing, closures, or for other reasons.

712-2.05 PRECAST CONCRETE MANHOLE SECTIONS. Meet AASHTO M 199, except that the absorption test will not be required. Reject units with cracks and honeycombed or patched areas in excess of 30 square inches.

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS. Conform to the plan dimensions and to the following materials requirements.

Gray iron castings	AASHTO M 306 and AASHTO M 105, Class 35B.

Carbon-steel castings 	AASHTO M 103. Grade is optional.

Structural steel 	ASTM A 709

Galvanizing	AASHTO M 111

Malleable iron castings 	ASTM A 47. Grade is optional.

712-2.07 CORRUGATED METAL UNITS. Meet AASHTO M 36. When bituminous coating is specified, meet AASHTO M 190, Type A.

712-2.08 GLASS BEADS. Meet AASHTO M 247 Type I, with a moisture resistant coating.

712-2.09 CORPORATION STOPS AND CURB STOPS. Use threaded corporation stops meeting AWWA C800. Use tapped couplings and service saddles as detailed on the Plans and per the manufacturer's recommendations.

712-210 GATE VALVES. All valves must open counter-clockwise, and have ends corresponding to the type of conduit being used.

Valves Larger than 3-inch. Iron body, fully bronze mounted, double disc, parallel seat valves, as manufactured to meet AWWA Specifications C500.

Valves 3-inch and Smaller. Meet ASTM B 62. Solid bronze, wedge disc, non-rising stem, Class 125, with threaded ends.

712-2.11 VALVE SERVICE BOXES. Furnish the specific style box, stem, and cover shown on the Plans. Inscribe cover with “water” or “W”. Furnish service box of sufficient length to be adjusted an equal amount above and below the final ground surface. Dip boxes in coal tar pitch.

Furnish special wrenches, keys, or other tools needed to operate valve and to open valve box lid. Furnish a minimum of one of each type for each style and size of box and lid.

Boxes for Valves Larger than 3-inch. Cast iron, not less than 5-1/4 inch shaft, with extension stem adjustable for elevation.

Boxes for Valves, 3-inch and Smaller. Cast iron, not less than 4-1/4 inch shaft, with screw type extension stem.

712-2.12 HYDRANTS. Meet AWWA Specifications C-502, “Dry-Barrel Fire Hydrants”. Equip hydrants with 5-inch main valve openings and 6-inch standard mechanical joint hub ends for connection to the auxiliary gate valve. Equip hydrants with an auxiliary gate valve and valve box as shown on the standard details. Use mechanical joints for all connections. Furnish the following types of hose connections, as indicated on the drawings and bid schedule:

- Single Pumper Hydrants. Two 2-1/2 inch hose connections and one 4-1/2 inch pumper connection.

- Double Pumper Hydrants. One 2-1/2 inch hose connection and two 4-1/2 inch pumper connections.

Furnish hydrants in lengths indicated on the drawings. Furnish hydrants with working parts made of bronze or non-corrodible metal. Paint and coat to meet the cited AWWA Specifications.

712-2.13 GABIONS.

Wire Mesh: Use 11 gage minimum wire, except that the selvedge may be heavier. Meet or exceed ASTM A 641 medium hardness and tensile strength; Class 3 coating. Furnish at least one sample of each component of the mesh for testing.

- Use mesh with 4-inch openings in the longest dimension.

Use wire mesh that is designed to be nonraveling. It must resist pulling apart at any of the connections forming the mesh when a single wire strand in a section of mesh is cut.

Tie and Connecting Wire: Conform to the same specifications as wire used in the mesh except that it may be not more than 2 gauges smaller. Supply sufficient quantity for securing and fastening all edges of the gabion baskets and diaphragms, for fastening adjacent gabion baskets together, and to provide cross connecting wires in each gabion cell as specified below.

Gabion Baskets. Supply baskets, as specified, in various lengths and heights. Make the lengths multiples (2, 3, or more) of the horizontal width. Furnish all gabion baskets in uniform width of not less than 24 inches or more than 48 inches.

Fabricate the sides, ends, lid, and diaphragms for field assembly into a rectangular basket of the required size. Construct gabions as a unit. The base, ends and sides are either to be woven into a single unit or one edge of these members connected to the base so that strength and flexibility at the point of connection is at least equal to that of the mesh.

Diaphragms. Where the length of the gabion exceeds its horizontal width, divide the gabion equally with diaphragms of the same mesh and gage as the gabion basket and make compartments of a length approximately equal to horizontal width. Furnish the gabion with the necessary diaphragms secured in proper position on the base section so that no additional tying at this juncture is necessary.

Securely selvedge or bind all perimeter edges so that the joints formed by tying the selvedges have approximately the same strength as the body of the mesh.

712-2.14 PREFORMED PAVEMENT MARKING tape.

1.	General Requirements:

a.	Reflectorized plastic pavement markings and legends. Furnish a pliant polymer or homogenous preformed ribbon, 60 mils thick and of specified width, containing glass spheres uniformly distributed throughout the entire cross section. Furnish type that is designed to be inlayed on hot asphalt pavement or attached to existing bituminous pavement with a precoated pressure adhesive or liquid contact cement as herein specified.

b.	Use legends and symbols meeting the applicable shapes and sizes in the Alaska Traffic Manual and the Plans.

c.	Ensure that the plastic marker will mold itself to pavement contours, breaks, faults, etc. at normal pavement temperatures and fuse with itself and with previously applied markings of the same composition under normal conditions of use.

2.	Composition Requirements: Furnish marker with the following materials uniformly distributed throughout its cross-sectional area, and with a reflective layer of beads bonded to the top surface:

Material	(Composition by Weight, min.)

Resins & Plasticizers	20%

Pigments	30%

Graded Glass Beads	25%

3.	Physical Requirements:

a.	Tensile Strength. Minimum tensile strength of 100 psi when tested according to ASTM D 638.

b.	Plastic Pull Test. A test specimen made by cutting two 1-inch by 3-inch pieces of the plastic and attaching a 1-inch by 1-inch area at the end of each piece to the other, must support a dead weight of 4 pounds for not less than 5 minutes at a temperature between 70 °F and 80 °F.

c.	Pigmentation. Select and blend the pigments to provide a marking film which includes titanium dioxide for white markers and medium chrome yellow for yellow markers meeting standard highway colors through the expected life of the film.

d.	Glass Beads. Colorless glass with a minimum index of refraction of 1.50 when tested using the liquid oil immersion method. Use beads of size and quality to meet the performance requirements for the plastic.

e.	Skid Resistance. Meet a minimum skid resistance value of 40 BPN for the surface of the plastic using ASTM E 303.

f.	Reflectance. Meet the following initial minimum reflectance values for white and yellow films at 0.2° and 0.5° observation angles and 86.0° entrance angle using FSS FED-STD-370. Use a test distance of 50 feet and a 2-foot x 2.5-foot rectangular sample. Express specific luminance (SL) as millicandelas per ft2 per foot candle.

Use an angular aperture of both the photoreceptor and light projector of 6 minutes of arc. Use the geometric center of the sample as the reference center and the reference axis perpendicular to the test sample.

White	Yellow

Observation Angle	0.2°	0.5°	0.2°	0.5°

Specific Luminance	550	380	410	250

g.	Reflectivity Retention Tests. Meet the following test requirements:

(1)	Taber Abraser Simulation Test. Using a taber abraser with an H-18 wheel and a 125-gram load, inspect the sample at 50, 100 and 200 cycles, under a microscope, to observe the extent and type of bead failure.

No more than 10% of the beads may be lost due to popout and the predominant mode of failure must be “wear down” of the beads.

(2)	Qualitative Test. Judge bead bond strengths under a microscope with a magnification of 5X. The beads when removed must show a portion of the polymer bead bond retained with the beads.

h.	Certification. In lieu of running the tests required by this Subsection, provide a certification from the manufacturer stating the product conforms to these requirements.

i.	Effective Performance Life. Provide a neat, durable marking that will not flow or distort due to temperature if the pavement surface remains stable.

The plastic must be weather resistant and through normal traffic wear, show no appreciable fading, lifting or shrinkage and show no significant tearing, roll back, or other signs of poor adhesion.

4.	Application. Use a vendor-furnished mechanical applicator for the installation of a 4-inch wide pressure sensitive adhesive coated material. Provide the mechanical applicator on location for the duration of the installation period. Ensure that a manufacturer's representative is present during the time of the installation to provide technical assistance.

712-2.15 RAISED AND RECESSED PAVEMENT MARKERS. Use reflectors for both raised and recessed pavement markers consisting of an acrylic plastic shell filled with tightly adherent potting compound. Use shells containing one or two glass-covered prismatic reflective faces as called for on the Plans to reflect incidental light from a single or opposite directions.

1.	Shell. Molded Methyl Methacrylate meeting ASTM D 788, Gr. 8.

2.	Overall Dimensions. 4 x 2 x 3/8 inches.

3.	Reflective Surface. Each reflective surface must have a minimum area of 3-1/4 in2 and be located on a 30-degree angle from a horizontal plane.

4.	Optical Requirements. Meet the following minimum optical requirements of the reflective faces for an observation angle of 0.2 degrees, with the incident light parallel to the base of the reflector:

| Horizontal Entrance Angle | Specific Intensity* White Yellow Red |
| --- | --- |
| 0 degrees | 3 1.8 0.75 |
| 20 degrees | 1.2 0.72 0.30 |

*Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

5.	Adhesive. Install pavement markers with an epoxy adhesive recommended by the marker manufacturer and approved by the Engineer.

6.	Color. Match the color of the raised pavement markers to the color of the marking for which they supplement, substitute, or serve as a positioning guide.

7.	Filler. Use a potting compound filler selected for strength, resilience, and adhesion.

Bond thin, smooth, untempered glass to the prismatic reflective faces to provide an extremely hard and durable abrasion resistant surface.

712-2.16 TEMPORARY RAISED PAVEMENT MARKERS FOR SHORT-TERM OPERATIONS, SEAL COATS, AND SURFACE TREATMENTS.

1.	Marker. L-shaped polyurethane body with retroreflective tape on the top vertical section, with a self-adhesive base. Reflectorize both faces of the yellow marker and one face of the white marker. Make the marker body of 60 mil minimum thickness polyurethane meeting Table 712-1 with vertical leg approximately 2 inches high by 4 inches wide and base approximately 1-1/4 inch wide.

- TABLE 712-1

| PROPERTY | RESULT | ASTM TEST METHOD |
| --- | --- | --- |
| Specific Gravity (min.) | 1.19 | D 792 |
| Hardness | 80A | D 2240 |
| Tensile Strength (psi, min.) | 4600 | D 412 |
| Ultimate Elongation (%, min.) | 330 | D 412 |
| Modulus @ 300% (psi, min.) | 1000 | D 412 |
| Stiffness @ -20 °F (psi, min.) @ 72 °F (psi, min.) | 1700 900 | D 1053 D 1053 |
| Compression Set 22 hrs @ 160 °F max. % | 65 | D 395 |
| Taber Abrasion CS17 wheel wt loss mg/1000 cycles | 3 | ---- |

2.	Reflective Tape. Metalized polycarbonate microprism retroreflective material with acrylic backing or equal, a minimum 1/4-inch wide by 4 inches long. Provide the minimum optical performance shown in Table 712-2, for an observation angle of 0.2 degrees.

- TABLE 712-2

| Horizontal | Specific Intensity * |  |
| --- | --- | --- |
| Entrance Angle | White | Yellow |
| 0 degrees | 3.5 | 3.0 |
| 30 degrees | 2.7 | 1.7 |

*Candelas per footcandle of illumination at the reflector on a plane perpendicular to the incident light.

3.	Protective Cover. Where chip seals, slurry seals or tack coats are to be utilized after placement of the temporary raised pavement markers, furnish markers with a protective cover made of clear flexible polyvinyl chloride.

4.	Adhesive. Pressure-sensitive material, a minimum of 1/8 inch thick and 3/4 inch wide, factory-applied to the marker base with release paper.

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.

1.	Quality Requirements: Use a marking material formulated for the application type specified. Use a marking material manufactured from new materials and free from dirt and other foreign material. Use a methyl methacrylate based resin system for part “A”. Use benzoyl peroxide system for part “B”.

Extruded or Stenciled Application: Material formulated for extruded or direct stenciled application with factory intermix beads and anti skid aggregate, and the application of additional surface applied beads.

Submit a manufacturer certification for both the methyl methacrylate material, glass beads and anti-skid aggregate to ensure that the materials furnished conform to these Specifications.

2.	Performance Properties:

a.	No Track Time: Material must be track free after 15 minutes when applied at 40 mils (ASTM D 711).

b.	Hardness: Shore Durometer, A-1, 80 minimum after 24 hours.

c.	Tensile Strength: At break, minimum 125 psi (ASTM D 638).

d.	Percent Elongation: Minimum 20% (ASTM D 638).

e.	Water Absorption: Maximum 0.5% (ASTM D 570).

f.	Chemical Resistance: The material must show no effect after 7-day immersion in anti-freeze, motor oil, diesel fuel, gasoline, calcium chloride, sodium chloride or transmission fluid.

g.	Ultra-violet Light: Ultra-violet light must have no effect.

h.	Skid Resistance: Minimum 45 units, British pendulum (ASTM E 303).

i.	Reflectivity: 200 millicandelas, minimum initial

j.	Viscosity: Spray Material: 5 - 12 Pa•s (ASTM D 2196 Method B, LV Model, Spindle #4 at 60 RPM).

k.	Color:	Yellow, PR-1 chart, 33538 Federal Yellow.

White, minimum daylight reflectance of 84.

3.	Composition: The composition is at the discretion of the manufacturer, but must be essentially comprised of resins, reactive monomers, pigments, plasticizer, benzoyl peroxide, aggregate and glass beads. When mixed in the stated ratio, the material must cure to 99% minimum by weight and volume solids.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS. Use the type and amount of beads specified in writing by the marking material manufacturer necessary to meet the specified performance requirements. The written certification will note the bead coating is compatible with the marking material binder.

1.	Bead Manufacturer and Type.

a.	Swarco, Megalux-Beads or

b.	Approved equal beads

Approved Equal Beads. Equal beads will demonstrate:

(1)	Bead coatings compatible with marking materials. Marking Material Manufacturer will certify compatibility.

(2)	Lasting retro reflectivity.

712-2.19 LOW-VISCOSITY RESIN. Meet AASHTO M 235, Type IV, Grade 1, with the following revisions:

- Amend Table 1 as follows:

- Replace "2.0[20]" with "0.105[1.05]" in the row labeled "Grade 1, max".

712-2.20 CONCRETE ANCHORS.

1.	Anchor Bolts. Use galvanized anchor bolts meeting ASTM A 307, Grade A or ASTM F1554, Grade 36.  Hot-dip galvanize anchor bolts in conformance with AASHTO M 232.

2.	Coil Anchor Inserts. Use 1-inch diameter galvanized inserts with a minimum safe working load of 7,500 pounds.  Hot-dip galvanize anchors according to AASHTO M 111 or AASHTO M 232.

3.	Threaded Anchor Inserts. Use 1-inch diameter galvanized ferrule inserts with a minimum safe working load of 6,500 pounds.  Hot-dip galvanize anchors according to AASHTO M 111 or AASHTO M 232.

712-2.21 EPOXY FOR BONDING DOWELS. Use an epoxy cartridge system appropriate for the service temperature and ambient concrete temperature at the time of installation.

Use epoxy cartridge systems that meet the requirements of the “Acceptance Criteria for Adhesive Anchors in Masonry Elements,” AC58, by the International Code Council Evaluation Service (ICC-ES) including the suitability requirements for creep, in-service temperature, dampness, freezing and thawing, and seismic tests.

## SECTION 713

## STRUCTURAL TIMBER, LUMBER, AND PILING

713-.201 GENERAL REQUIREMENTS. Furnish structural timber manufactured according to the Voluntary Product Standard PS 20 as published by the United States Department of Commerce.

- Use timber free of heart center or pith of the log.

713-2.02 SPECIES REQUIREMENTS. Furnish Douglas Fir-Larch as described in ASTM D 1165, unless otherwise noted.

713-2.03 GRADE REQUIREMENTS. Furnish timber graded according to the West Coast Lumber Inspection Bureau (WCLIB) grading rules or the Western Wood Products Association (WWPA) grading rules. Meet the following minimum grade requirements, unless otherwise noted:

Dimension Lumber	No. 2 (WCLIB & WWPA)

Beams and Stringers	No. 1 (WCLIB & WWPA)

Posts and Timbers	No. 1 (WCLIB & WWPA)

713-2.04 SURFACING AND SEASONING REQUIREMENTS. Furnish timber surfaced on four sides (S4S) when the wood moisture content is less than 19%, unless otherwise noted.

713-2.05 INSPECTION, GRADE STAMPING, AND CERTIFICATION. Furnish timber inspected by the West Coast Lumber Inspection Bureau (WCLIB), Western Wood Products Association (WWPA), or the Pacific Lumber Inspection Bureau (PLIB). Ensure timber delivered to the project bears the certified lumber grade stamp provided by the inspecting agency. Provide grading certificates issued by either the inspecting agency whose stamp is shown on the timber, or by the lumber mill supervised by the inspecting agency including the following:

1.	Name of the mill performing the grading

2.	The grading rules being used

3.	The name and certification of the person doing the grading

4.	Signature of a responsible representative of the mill

5.	Date the timber was graded

6.	Grade, dimension, and quantity of timber

## SECTION 714

## PRESERVATIVES FOR TIMBER

714-2.01 GENERAL REQUIREMENTS.  Treat timber according to AASHTO M 133 and Best Management Practices for the Use of Treated Wood in Aquatic Environments as published by the Western Wood Preservers Institute. Use pentachlorophenol preservative, meeting the American Wood Protection Association (AWPA) Standard P8, in Type A solvent according to the AWPA Standard P9. Provide a preservative retention conforming to UC4C of the AWPA Standard U1.

## SECTION 715

## STEEL FOR PILES

715-2.01 SCOPE. Steel used for Structural Steel Piling and Sheet Piling.

715-2.02 GENERAL REQUIREMENTS. Furnish steel piles of the dimensions, weights, cross-sections, and grades specified. Satisfy the impact test requirements of Subsection 716-2.02. Meet the following:

1.	Structural Steel HP Piling. Furnish "HP" shape piles meeting ASTM A 709, Grade 50T3.

2.	Structural Steel Pipe Piling. Furnish pipe piles meeting one of the following:

a.	American Petroleum Institute (API) 5L X52 PSL2.

b.	ASTM A 709, Grade 50T3 fabricated and monogrammed according to API 2B

c.	ASTM A 709, Grade 50T3 fabricated according to the following:

(1)	General. Fabricate pipe piling using coiled steel with one helical seam weld. Use skelp material that does not contain repair welds. Use skelp having a width not less than 0.8 times the outside diameter of the pipe and not greater than 3.0 times the outside diameter of the pipe. Form pipe when the steel temperature is below 400°F. Locate junctions of skelp end welds and the helical seam welds at distances greater than 1.0 times the outside diameter of the pipe from the pipe ends and at distances greater than 5.0 times the outside diameter of the pipe from other junctions of skelp end welds and helical seam welds.

(2)	Welding. Use complete joint penetration welds produced by the automatic submerged–arc welding process, the automatic gas metal-arc welding process, or a combination of both processes. Perform welding according to Section 504.

(3)	Welding Inspection. Perform welding inspection according to AWS D1.1. Provide visual inspection of welds on the inside surfaces and outside surfaces of the pipe.

(4)	Non-Destructive Examination. Randomly examine 10% of the total length of helical seam welds and skelp end welds. Examine welds by performing one or more of the following tests:

(a)	Radiographic testing according to the requirements of AWS D1.1 Section 6, Part E with Subsection 6.12.3 of AWS D1.1.

(b)	Ultrasonic testing according to the requirements of AWS D1.1 Section 6, Part F with Subsection 6.13.3.1 of AWS D1.1.

If more than 10% of the welds examined are defective, examine a second random sample of 25% of the total length of welds. If more than 10% of the welds examined in the second sample are defective, examine 100% of the total length of welds.

- Repair all weld defects.

(5)	Destructive Examination. Perform destructive examination on specimens from finished pipe of each specified outside diameter, wall thickness, steel type, and grade. Examine specimens at a frequency of at least one set of tests for each lot representing 2000 linear feet of finished pipe or once per week during each production run, whichever occurs first. Do not use specimens containing repaired welds.

(a)	Tensile Tests. Meet the specified tensile requirements for yield strength, tensile strength, and elongation. Perform tension tests according to ASTM A 307 using one base metal specimen and two weld specimens taken at 90° to the length of the weld with the weld across the center of the sample. For base metal specimen, determine and report yield point, yield strength, tensile strength, and elongation. For weld test specimens, determine and report tensile strength.

Each lot of pipe will be considered to meet the tensile requirements if the base metal test results exceed the specified yield strength, tensile strength, and elongation and the weld test results exceed the specified tensile strength result.

(b)	Bend Tests. Perform transverse side bend tests according to ASTM E 190. Each lot of pipe will be considered to meet the bend test requirements if the no cracks occur in the specimen.

(6)	Tolerances. Meet the following tolerances:

(a)	Roundness. Limit the difference between the major and minor outside diameter to 1% of the specified outside diameter of the pipe or 1/4 inch, whichever is less.

(b)	Circumference. Limit the outside circumference to 1% of the nominal outside circumference of the pipe or 1/2 inch, whichever is less.

(c)	Straightness. Do not deviation from a straight line parallel to centerline of the pile more than ±1/8 inch per 10 feet of length, but not to exceed 3/8 inch.

(d)	Length. ±1-1/2 inch per 10 feet of length.

(7)	Defects. The Engineer may reject piles containing surface defects. The depth of the surface defect will be measured as the gap between the lowest point of the defect and a prolongation of the original contour of the pipe. Use of piles containing surface defects may be authorized according to the following requirements based on the depth of the surface defect:

(a)	If the surface defect is not greater than 5% of the wall thickness in depth, the defect need not be repaired.

(b)	If the surface defect is deeper than 5%, but not greater than 7%, of the specified wall thickness, grind smooth the surface defect. Remove abrupt changes in contour, but do not reduce the thickness in the ground area more than 7% of the specified wall thickness.

(c)	If the surface defect is deeper than 7%, but not greater than 20%, of the specified wall thickness, repair the defect by welding according to Section 504.

(d)	If the surface defect is deeper than 20% of the specified wall thickness, repairs will not be permitted and the pile will be rejected.

3.	Pile Tip Reinforcing. Use pile tip reinforcement conforming to the requirements of ASTM A 27 Grade 65-35 or ASTM A 148 Grade 90-60. Make each pile tip in one piece of cast steel. Weld tip reinforcing to the piles in conformance with the manufacturer's written directions.

4.	Structural Steel Sheet Piling. Furnish sheet piles meeting AASHTO M 202.

715-2.03 CERTIFICATION. Furnish 5 copies of a certified test report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number;

2.	the manufacturer's name;

3.	the name of the product or assembly;

4.	a complete description of the material;

5.	country of origin;

6.	the lot, heat, or batch number that identifies the material;

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 715-2.03.6; and,

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

For pipe manufactured to API 5L, submit an inspection certificate with test results according to API 5L 10.1.3.

715-2.04 MARKING. Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying certified test report.

For helical welded pipe piles, mark each pipe on the inside surface and outside surface of both ends indicating: the fabricators name, type of steel, grade of steel, steel heat number, welding process, total pipe weight or weight per lineal foot of pipe, length, nominal outside diameter, and nominal wall thickness.

## SECTION 716

## STRUCTURAL STEEL

716-2.01 SCOPE. Structural steel for highway bridges and other structural purposes.

716-2.02 GENERAL REQUIREMENTS. Meet the following:

- 1.	General requirements for delivery of rolled steel plates,

shapes, sheet piling, and bars for structural use	ASTM A 6

2.	Structural Steel	ASTM A 709

- 3.	High Strength Low-Alloy Columbium

Vanadium Steels of Structural Quality	ASTM A 709

- 4.	High Strength Low-Alloy Steel with 50,000 psi

minimum yield point to 4 inches thick	ASTM A 709

- 5.	High Yield Strength, Quenched and Tempered

Alloy Steel Plate Suitable for Welding	ASTM A 709

6.	Welded and Seamless, High Strength, Low-Alloy Tubing 	ASTM A 618

7.	Filler Metal for Applicable Arc-Welding Electrodes	AWS Specifications

8.	Stud Shear Connectors	ASTM A 108

Gr. 1015, or 1020

9.	Raised Pattern Plate. Where shown on the Plans, use plates for steel expansion joints fabricated from steel plate, with a raised pattern surface meeting the following requirements:

a.	Use diagonal type pattern, with the intersecting diagonals at right angles to one another. Use the same material for the raised portions of the pattern as the base metal of the plate. The raised pattern must be an inherent part of the plate. The pattern must be continuous throughout the surface of the plate and the projections along any diagonal must be spaced alternately with the projections along the normal diagonals.

b.	Use plate with projections that are self-draining and self-cleaning and provide a skid-resistant surface from all angles of approach. The projections must have flat tops and be designed not to chip, crack, split, or buckle at their intersection with the base metal.

10.	Impact Test Requirements.

a.	Meet the supplemental requirements for impact toughness testing (Charpy V-Notch) and marking under ASTM A 709, Zone 3. These supplemental requirements are mandatory for material designated on the Plans as fracture critical (F) or as main members subject to tensile stress (T).

b.	Submit impact test reports to the Engineer.

716-2.03 HIGH TENSILE STRENGTH BOLTS. Meet the following:

High Strength Bolts for Structural Steel Joints 	AASHTO M 164

Nuts for AASHTO M 164 bolts	AASHTO M 292

Hardened Steel Washers	AASHTO M 293

716-2.04 Steel Grid Floors. Meet ASTM A 709, Grade 36. Unless the material is galvanized, it must have a copper content of 0.2% minimum.

- Unless painting of floors is specified in the Special Provisions, open type floors must be galvanized.

716-2.05 Machine Bolts. Meet ASTM A 307.

716-2.06 STEEL PIPE. Meet ASTM A 53 Grade B.

716-2.07 GALVANIZING. Hot-dip galvanize structural steel shapes, plates, bars and their products according to AASHTO M 111. Galvanize tubes and piles on inside and outside surfaces.

Hot-dip galvanize steel poles, mast arms, pedestals, and posts, according to AASHTO M 111. Submerge each component in the galvanizing kettle in one dip. Use only the dry kettle method of fluxing for high tower poles.

Hot-dip galvanize all anchor bolts, nuts, washers, tie-rods, clamps, and other miscellaneous ferrous parts in conformance with AASHTO M 232. After galvanizing, ensure that the bolt threads accept galvanized standard nuts without requiring tools or causing removal of protective coatings.

- Galvanize rigid metal conduit in conformance with AASHTO M 232.

For steel bridge members, apply 10 mils zinc galvanizing by spray-metalizing process according to Steel Structures Painting Council’s coating system guide SSPC-CS 23.00. Prepare surfaces before galvanizing according to Steel Structures Painting Council's surface preparation guide SSPC-SP 5, White Metal Blast Cleaning.

Repair damaged coatings according to ASTM A 780 Annex A1 or Annex A3, except as described herein. Clean the damaged area according to SSPC-SP 2, Near-White Blast Cleaning for repairs meeting Annex A1 and SSPC-SP 5, White Metal Blast Cleaning for repairs meeting Annex A3. Extend the cleaned area 1/2 inch to 3/4 inch into the undamaged section of the coating. Keep the cleaned area dry and free of rust and soiling.  Within 24 hours of cleaning, coat the cleaned section with zinc to a thickness of not less than 10 mils. Taper the thickness of the repair coating to match the original coating thickness at the edges of the cleaned section. Where zinc coating is to be metallized, use zinc wire containing not less than 99.98 percent zinc.

716-2.08 CERTIFICATION. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number

2.	the manufacturer's name

3.	the name of the product or assembly

4.	a complete description of the material

5.	country of origin

6.	the lot, heat, or batch number that identifies the material

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 716-2.08.6

8.	an affidavit, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

## SECTION 718

## STEEL FORGINGS

718-2.01 SCOPE. Steel forgings from which pins, rollers, trunnions or other forged parts are to be fabricated.

718-2.02 GENERAL REQUIREMENTS. Meet the dimensions shown on the Plans and the following specifications.

1.	Alloy Steel Forgings (general industrial use): AASHTO M 102, Class G.

2.	Carbon Steel Forgings (general industrial use): AASHTO M 102, Class C.

3.	Pins and Rollers

a.	More than 7 inches in Diameter: Annealed carbon-steel forgings meeting AASHTO M 102, Class C.

b.	7 inches or Less in Diameter: Either annealed carbon-steel forgings meeting AASHTO M 102, Class C or cold finished carbon-steel shafting meeting AASHTO M 169, Grade 1016 to 1030, inclusive, with a minimum Rockwell Scale B hardness of 80. Material not meeting the specifications for hardness may be accepted provided it develops a minimum tensile strength of 66,000 psi and a minimum yield point of 33,000 psi.

4.	Threads for Pins: ANSI B 1.1, Class 2A coarse thread series. Thread pin ends, having a diameter of 1-3/8 inch or more, 6 threads to the inch.

718-2.03 CERTIFICATION. Submit 5 copies of a certified mill test report covering chemical and physical tests for the material in each shipment.

## SECTION 719

## STEEL, GRAY-IRON AND 
MALLEABLE-IRON CASTINGS

719-2.01 SCOPE. Steel, gray-iron and malleable-iron castings intended for various uses as shown on the Plans.

719-2.02 GENERAL REQUIREMENTS. Meet the size and dimensions shown on the Plans, be true to pattern in form, and conform to the following specifications.

Carbon Steel Castings	AASHTO M 103, Grade 65-35

Chromium Alloy Steel Castings	AASHTO M 163, Grade CA-15

Gray-Iron Castings	AASHTO M 306 and AASHTO M 105, Class 35B

Malleable-Iron Castings	ASTM A 47, Grade 24018

## SECTION 720

## ELASTOMERIC PADS

720-2.01 ELASTOMERIC BEARING PADS. Elastomeric bearing pads include plain pads, consisting of elastomer only, and laminated pads with steel laminates.

1.	General. Meet AASHTO M 251, with the following revisions:

4.1. Properties of the Elastomer. Replace the first sentence with the following: Use elastomeric compound in the construction of the bearings containing only virgin natural polyisoprene (natural rubber) as the raw polymer. Do not use neoprene. Properties and requirements elsewhere in AASHTO M 251 pertaining solely to polychloroprene (neoprene) do not apply.

Use elastomer compound classified as low temperature Grade 5 and meeting the requirements of paragraph 8.9.

- Add the following paragraph:

5.5. Fabricate pads over 3/4 inch thick with alternating laminations of elastomer and metal or fabric reinforcements. The outside laminations must be metal or fabric with a minimum elastomer cover as shown on the Plans.

- Table 2—Tolerances. Replace Item 6. with the following:

6. Edge cover of embedded laminates or connection members		-0, 1/16 inch

A3.4.3. Replace the second sentence with the following:  Condition the specimens at the specified test temperature for 96 hours.

2.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 720-2.01.2.f; and

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

720-2.02 EPOXY ADHESIVE FOR ELASTOMERIC BEARING PADS. Meet AASHTO M 235, Type IV, Grade 3.

720-2.03 POLYTETRAFLUOROETHYLENE (PTFE) BEARINGS. PTFE bearing assemblies consist of elastomeric bearing pads, polytetrafluoroethylene (PTFE) surfacing, and stainless steel and steel plates.

1.	Materials.

Elastomeric Bearing Pads	Subsection 720-2.01

Stainless Steel Plates	ASTM A 240, Type 304

Steel Plates	ASTM A 709, Grade 36

Use PTFE from virgin material (not reprocessed) meeting the requirements of ASTM D 4894 or D 4895, and Table 720-1.

2.	Fabrication. Fabricate the PTFE sliding surface with lubricant dimples having a maximum diameter of 0.32 inch, a minimum depth of 0.08 inch and a maximum depth of one half of the PTFE sheet thickness. Distribute the dimples uniformly within the area ¼ inch from the edges of the PTFE sheet and occupying between 20 percent and 30 percent of the PTFE sheet area.

- For welding of structural steel, conform to the requirements of Section 504.

- TABLE 720-1

POLYTETRAFLUOROETHYLENE (PTFE)

| TEST | REQUIREMENTS |
| --- | --- |
| Specific Gravity | 2.13 - 2.19 |
| Peak Melting Temperature | 623oF (2oF) |
| Tensile strength (Minimum) | 2800 psi |
| Elongation (Minimum) | 200% |

Bond the PTFE sheet in the recess of steel plate under controlled factory conditions. Use adhesive material that is an epoxy resin conforming to the requirements of Federal Specification MMM-A-134.

Uniformly roughen the contact surfaces of PTFE sheet and steel plate to be bonded to a minimum roughness height value of 250 micro-inches.

Factory treat the side of the PTFE sheet to be bonded by the sodium naphthalene or sodium ammonia process, after the contact surface is roughened.

Fully bond the PTFE sheet in the recess. Ensure the PTFE surface is smooth and free from bubbles after completion of the bonding operation. PTFE sheets that are delaminated will be rejected.

Perimeter seal weld the stainless steel plate to the steel sole plate. Use stainless steel electrodes in accordance with the requirements of the electrode manufacturer. After the completion of the weld operation, ensure the stainless steel plate is smooth and free from waves.

Control the flatness of the bearing elements such that upon completion of the bearing assembly the PTFE/stainless steel sliding interface is in full bearing.

Provide a mating surface of the stainless steel plate with the PTFE surfacing with a surface finish of less than 8 micro inches root-mean-square (rms), determined according to ANSI Standard B46.1. Do not exceed a first movement static coefficient of friction of 0.05 for the sliding element of the production bearings, when tested without the coating of silicone grease.

Fully vulcanize elastomeric bearing pads to the steel plates under factory controlled conditions. Provide a bond with a peel-strength of at least 30 pounds per inch as determined by AASHTO M 251, appendix X2.

Prepare and paint metal surfaces, except stainless steel surfaces, of bearings exposed to the atmosphere in the completed work. Prepare and paint the surfaces according to Section 504.

After installation of the bottom portion of the bearing assembly, apply a 1/16 inch thick coating of silicone grease to the entire PTFE surface and reassemble the bearing without damage to the mating sliding surfaces. Use silicone grease conforming to Military Specification: MIL-S-8660.

At your expense and without contract extension time return damaged bearings and bearings with scratched mating surfaces to the factory for replacement or resurfacing.

Prior to proof testing, permanent die stamp all individual components on 2 of 4 sides with markings consisting of bearing number and contract number. Provide each bearing with a unique bearing number and match marks on plate edges to insure correct assembly at the job site.

3.	Testing. Proof test and evaluate full sized PTFE bearings for compression and coefficient of friction in the presence of the Engineer, unless otherwise directed. Perform proof tests on samples randomly selected by the Engineer from the production bearings to be used in the work. Perform proof tests at an approved independent laboratory. If proof tests are not performed at the specified load, perform additional physical tests in the presence of the Engineer, unless otherwise directed, to demonstrate that the requirements for proof testing at the specified load are satisfied. Give the Engineer at least 7 working days notice before beginning proof testing.

Proof test one bearing per lot of production PTFE bearings. A lot is defined as 25 PTFE bearings or fraction thereof of the number of PTFE bearings shown on the Project Plans.

- Clean the bearing surfaces prior to testing.

- Proof test bearings after conditioning specimen for 12 hours at 75o 5oF.

Perform the tests with the dead load as specified in the Contract for the bearing with the test load applied for 12 hours prior to friction measurement and the following:

Arrange the tests to allow measurement of the static coefficient of friction on the first movement of the bearing.

Measure the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

Subject the test bearings to a minimum of 100 movements of at least one inch of relative movement at a sliding speed not exceeding 12 inches per minute. After cycling, measure again the first movement static and dynamic coefficients of friction at a sliding speed not exceeding one inch per minute and do not exceed the specified coefficient of initial static friction.

The proof tested bearings are to show no visible sign of: (1) bond failure of bearing surfaces, (2) separation or lift-off of plates from each other or from PTFE surfaces, (3) other defects. When a proof tested bearing fails to comply with the Contract Documents, test each bearing in that lot for acceptance.

Proof test results are to be certified correct and signed by the testing laboratory personnel who conducted the test and interpreted the test results. Include the bearing numbers of the bearings tested on the proof test results.

Test a minimum of one pad per lot for bond strength per AASHTO Test M 251. Test specimens are to show no indication of deterioration of elastomer or loss of bond between the elastomer and steel laminates.

- Protect all PTFE and stainless steel surfaces from contamination and weather damage.

4.	Certification. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 720-2.03.4.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

## SECTION 721

## PRESTRESSING STEEL AND FITTINGS

721-2.01 SCOPE. Prestressing steel and fittings used in pre-tensioned and post-tensioned concrete construction.

721-2.02 PRESTRESSING STEEL. Meet the following:

Strand	AASHTO M 203

Wire	AASHTO M 204. Do not use oil-tempered wires.

High Strength Alloy Steel Bars	AASHTO M 275

721-2.03 POST-TENSIONING SYSTEM. Use only post-tensioning systems that utilize tendons fully encapsulated in anchorages and ducts. Systems that transfer prestress force by bonding the prestress steel directly to concrete are not allowed. Use only post-tensioning systems that are approved by the Engineer and meet the following requirements:

1.	Anchorage and Distribution. Secure prestressing steel at the ends by means of approved permanent type anchoring assemblies.

Use anchorage devices for post-tensioning that hold the prestressing steel at a load producing a stress of not less than 95 percent of the guaranteed ultimate tensile strength (GUTS) of the prestressing steel, when tested in an unbonded state, without exceeding the anticipated set.

Distribute the load from the anchoring assemblies to the concrete by means of approved devices or bearing plates that will effectively distribute the load to the concrete. Construct the bearing plate and wedge plate from ferrous metal. For bending stresses in the bearing plates or assemblies induced by the pull of the prestressing steel, do not exceed the yield point of the material or cause visible distortion in the bearing plate when 95 percent of the GUTS of the tendons is applied as determined by the Engineer. Do not exceed 3500 psi directly underneath the bearing plate or assembly for the final unit compressive stress on the concrete.

Galvanize the body of the anchorage assembly in accordance with AASHTO M 111. Other components of the anchorage assembly including wedges, wedge plate and local zone reinforcement need not be galvanized.

Construct anchorage assemblies with grout vents suitable for post-grouting inspection access as approved by the Engineer. Equip all anchorages with a grout cap that is vented and bolted to the anchorage.

Recess the anchoring assemblies so that the ends of the prestressing steel and all parts of the anchoring assemblies will be at least 3 inches inside of the end surface of the members, unless shown otherwise on the plans. After post-tensioning all tendons, fill the recesses with concrete conforming to the provisions for the structure and then finished flush with the abutment end diaphragm.

2.	Strand Couplers. Do not use strand couplers.

3.	Enclosures for Post-tensioning. Use rigid ferrous metal duct enclosures for prestressing steel that are galvanized, mortar tight, and capable of withstanding concrete pressures without deforming. Use rigid ducts with smooth inner walls that can be curved to the proper configuration without crimping or flattening and have sufficient strength to maintain their correct alignment during placing of concrete. Do not use semi-rigid ducts. Fabricate ducts with either welded or interlocked seams.

Connect sections of rigid ducts using galvanized ferrous metal couplings that are mortar tight and do not result in angle changes at the joints. Do not use split metal couplings. Use waterproof tape to seal all connections to the duct. Connect ducts to anchoring assemblies using transition couplings that are galvanized ferrous metal or polyethylene, mortar tight, and of sufficient strength to prevent displacement of the ducts during concrete placement.

Use ducts for multi-strand tendons with a minimum diameter that provides an inside area at least 2.5 times the net area of the prestressing steel in the tendon.

Do not use ducts with diameters that exceed 0.4 times the least gross concrete thickness at the duct location.

- Use duct enclosures with vents for the injection of grout after post-tensioning.

4.	Grout Vents. Use vents with positive means for allowing the escapement of air, water, grout, and bleed water out of the vents, injecting grout through the vents, and sealing to prevent grout leakage from the vents. Use 3/4 inch minimum diameter standard pipe or suitable plastic pipe vents with positive shut-off designed to withstand the grouting pressure. Do not crimp or bend the vent pipe. Use metallic or plastic structural fasteners to connect the vent with the duct. Do not use plastic components that react with the concrete or enhance corrosion of the prestressing steel, or contain water-soluble chlorides. Make all vents mortar tight, taped as necessary. Make vents with sufficient length out of the concrete member to allow proper closing of the vents. Remove ends of vents at least 1 inch below the roadway surface after grouting has been completed.

Place vents at the following locations:

a.	At anchorages.

b.	At the high points of the duct, when the vertical distance between the highest and lowest point is more than 20 inches.

c.	At a location down flow from all high point vents where the duct is approximately one-half duct diameter lower than the crest, but not to exceed 3 feet downstream.

d.	At the lowest point of the duct.

e.	At major changes in the cross-section of the duct.

f.	At other locations designated by the Engineer.

5.	Grout Caps. Use grout caps that completely cover and seal all exposed ends of prestressing steel at the anchorage. Seal the cap with neoprene “O” ring seals and place a grout vent on the top of the cap. Use caps rated for a minimum pressure of 150 psi.

721-2.04 CERTIFICATION.

1.	Prestressing Steel. Furnish 5 copies of a Certified Test Report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

a.	the project name and number;

b.	the manufacturer's name;

c.	the name of the product or assembly;

d.	a complete description of the material;

e.	country of origin;

f.	the lot, heat, or batch number that identifies the material;

g.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 721-2.04.1.f; and,

h.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying Certified Test Report.

2.	Post-Tensioning Systems. Submit certified test reports to the Engineer that shows the post-tensioning system meets all the requirements specified herein. Submit the certified test reports with the shop drawing submittal. If any component of the post-tensioning system is modified or replaced, the entire system must be retested and resubmitted to the Engineer for approval.

Ensure that all components of a system are stamped with the supplier’s name, trademark model number and size corresponding to catalog designation.

Submit certification stating the manufacturer's minimum guaranteed ultimate tensile strength of all prestressing steel used for this project.

Assign an individual lot number for each manufactured reel of prestressing steel to be shipped to the site. Tag each reel in such a manner that each lot can be accurately identified at the site. All unidentified prestressing steel received at the site will be rejected.

Assign and tag each lot of anchorage assemblies to be installed at the site. Tag each anchorage assembly in such a manner it can be accurately identified at the site. All unidentified anchorage assemblies received at the site will be rejected.

## SECTION 722

## BRIDGE RAILING

722-2.01 BRIDGE RAILING.

Steel tube rail elements	ASTM A 500, Grade B

Steel Thrie Beam elements	AASHTO M 180, Class B, Type II

Posts	ASTM A 709, Grade 36

- Machine bolts, cap screws, nuts

and washers	ASTM A 307

High strength bolts, nuts and washers	ASTM A 325 and Subsection 716-2.03

Anchor bolts	AASHTO M 314, Grade 105; ASTM F 1554,

Grade 105; or ASTM A 449, Type 1

Shims, plates and sleeves 	ASTM A 709, Grade 36

Galvanize steel portions of railing 	Meet AASHTO M 111 or M 232,

after fabrication. 	whichever is applicable.

722-2.02 CERTIFICATION. Furnish 5 copies of a certified test report from the manufacturer or an independent testing laboratory containing a list of dimensional, chemical, metallurgical, electrical, physical, and other required test results of the specified material certifying that the product or assembly has passed all specified tests. Include the following:

1.	the project name and number

2.	the manufacturer's name

3.	the name of the product or assembly

4.	a complete description of the material

5.	country of origin

6.	the lot, heat, or batch number that identifies the material

7.	all required test results for the specified material from the same lot, heat, or batch defined in Subsection 722-2.02.6

8.	a statement, signed by a person having legal authority to act for the manufacturer or the independent testing laboratory, that the test results show that the product or assembly to be incorporated into the project has been sampled and tested and the samples have passed all specified tests.

Tag, stencil, stamp, or otherwise mark all materials or assemblies furnished under certification to the project with the lot number, heat number, batch number, or other appropriate identification, which can be readily recognized and legible, and is identical to the accompanying certified test report.

## SECTION 723

## WATER STOPS

723-2.01 WATER STOPS.

1.	Rubber water stops, either molded or extruded from plain rubber or synthetic rubber. Meet the requirements of ASTM D 2000.

2.	Use water stops formed with an integral cross section. No splices are permitted in straight strips. Strips and special connection pieces must be free from all porosity. All junctions in the special connection pieces must be full molded. During the vulcanizing period securely hold the joints with suitable clamps. The material at the splices must be dense and homogeneous throughout the cross section.

3.	Full mold all field splices and bevel splice faces at an angle of 45 degrees or flatter. All finished splices must have a tensile strength of not less than 50% of the unspliced material.

4.	Obtain the Engineer’s approval to use water stops of materials other than those specified.

## SECTION 724

## SEED

724-2.01 DESCRIPTION. Grass seed to provide a living vegetative cover.

724-2.02 MATERIALS. Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished. Meet or exceed the percentages of sproutable seed specified in Table 724-1.

- TABLE 724-1

SEED REQUIREMENTS

| SPECIES | SPROUTABLE SEED*, %, MIN. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

## SECTION 725

## FERTILIZER

725-2.01 DESCRIPTION. Standard commercial fertilizer supplied separately or in mixtures, and furnished in moisture proof containers. Mark each container with the weight and with the manufacturer's guaranteed analysis of the contents showing the percentage for each ingredient contained therein.

725-2.02 MATERIALS. Furnish a mixture of chemical ingredients providing the total available nitrogen, phosphoric acid, and potassium required by the soil analysis or as specified in the Special Provisions. Tolerances of the chemical ingredients are plus or minus 2%.

No cyanamid compounds or hydrated lime are permitted in mixed fertilizers.

## SECTION 726

## TOPSOIL

726-2.01 TOPSOIL. Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 203, on the soil to determine the organic content of the soil. Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the plans. Remove roots, stumps, unnatural material, and rocks greater than 3 inch in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project. In this case furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse or foreign materials having an organic content of 5 percent or more, as determined by ATM 203. The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic. Notify the Engineer of the topsoil source location at least 30 calendar days before delivery of topsoil to the project from the identified location. The Engineer will inspect the topsoil and its sources before approval will be granted for its use.

- TABLE 726-1

Limestone Requirements

| Soil pH | Limestone, tons/acre |
| --- | --- |
| Above 6.0 | 0 |
| 5.0-6.0 | 1.5 |
| Below 5.0 | 3.0 |

## SECTION 727

## SOIL STABILIZATION MATERIAL

727-2.00 GENERAL. Free of noxious weeds, seeds, chemical printing ink, germination and growth inhibitors, herbicide residue, chlorine bleach, (except where specified: rock, metal, plastics) and other deleterious materials and not harmful to plants, animals and aquatic life. Wood cellulose "paper" fiber, wood chips, sawdust, and hay are not permitted as stabilization materials.

727-2.01 MULCH. Flexible blanket/covering, temporary degradable (bio/photo) form of erosion control. Use one of the following:

- Dry Erosion Control, Stabilization Products. Hand applied or spread with mulch blower equipment.

1.	Straw. Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. Straw material shall be certified weed-free straw using North American Weed Management Association (NAWMA) Standards. In-lieu of certified weed-free straw provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

2.	Shredded Bark Mulch. Shredded bark and wood with the following characteristics:

a.	Not containing resin, tannin, or other compounds in quantities harmful to plant life.

b.	Maximum length of individual pieces is 2 inches with 75% passing through a 1 inch sieve.

c.	Will form a uniform ground cover/mat, have moisture absorption, retention, and percolation properties, not be susceptible to spreading by wind or rain providing a good growth medium.

d.	May contain up to 50% shredded wood material.

e.	Shredded wood material aged 1 year minimum prior to use.

- Hydraulic Erosion Control Products (HECPs). Applied hydraulically.

A fiber mulch matrix:  biodegradable and composed of wood, straw, coconut and other fibers natural and man-made. When applied, create a continuous, porous, absorbent high water holding, flexible blanket/mat/mulch/covering making intimate contact with, and adhering to sloped soil surface; permitting water infiltration; resists erosion and promotes rapid germination and accelerated plant growth. The fibers may be thermally processed, and cross-linked with a hydro-colloidal or linear anionic tackifier (curing period 24-48 hours) or mechanically-bonded (no curing period). When agitated in slurry tanks with water the fibers will become uniformly suspended, without clumping to form homogeneous slurry.

The HECPs shall be delivered premixed by the manufacturer. The HECP will contain only the materials provided in the sealed containers from the manufacturer.  No added components are permitted after the manufacturer seals the product container, before application, during application or otherwise. Submit documentation dated within 3 years of application, from an independent accredited laboratory as approved by the Engineer, showing that the product's testing performance meets the requirements for the slope(s) to be protected on the project, according to the National Transportation Product Evaluation Program (NTPEP), Erosion Control Technology Council (ECTC) and or the Texas DOT/Texas Transportation Institute (TTI) Laboratory.

If the HECP contains cotton or straw provide documentation that the material is certified weed free using NAWMA Standards. In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

- The HECP shall contain a dye to facilitate placement and inspection of the material.

- 1.	Wood Strand, Fiber.

A blend of angular, loose, long thin wood pieces with a high length to width ratio and that are frayed. Minimum 95% of strands between 2 inches and 10 inches, at least 50% of the length shall have a width thickness between 1/16 and 1/8 inch. No single strand shall have a width or thickness greater than 1/2 inch.  Processed wood fiber with the following characteristics:

a.	Will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form homogeneous slurry.

b.	Will form a blotter-like uniform ground cover on application, have moisture absorption, retention and percolation properties, the ability to cover, and hold grass seed in contact with soil, and not create a hard crust upon drying providing a good growth medium.

- 2.	Dried Peat Moss. Partially decomposed fibrous or cellular stems and leaves of any of several species of Sphagnum mosses with the following characteristics:

a.	Chopped or shredded to allow distribution through normal hydraulic type seeding equipment and capable of being suspended in water to form part of a homogeneous slurry.

b.	Free from woody substances and mineral matter such as sulfur or iron and with a pH value of between 4.0 and 6.5.

c.	Furnished in an air dry condition and containing less than 35% moisture by weight.  Have a water holding capacity of not less than 800% by weight on an oven dry basis.

- 3.	Fiber Matrix (FM) Mulch - Types.

a.	Stabilized Mulch Matrices (SMMs)

b.	Bonded Fiber Matrices (BFMs)

c.	Mechanical Bonded Fiber Matrix (MBFM)

d.	Polymer Stabilized Fiber Matrix (PSFM)

e.	Fiber Reinforced Matrices (FRMs)

	Flexible Growth Medium (FGM)

	Extended-Term Flexible Growth Medium (ET-FGM)

727-2.02 MATTING. Fiber mulches, mulch matrices, nets and turf reinforcement mats manufactured from wood fibers, straw, jute, coir, polyolefins, PVC, nylon and others creating dimensionally stable nets, meshes, geotextiles and blankets; creating a continuous, porous, absorbent, flexible blanket/mat/mulch/covering making intimate contact with and adhering to sloped soil surface, resisting erosion and promoting rapid germination and accelerated plant growth.

- Rolled Erosion Control Products (RECPs) (Temporary Degradable and Permanent Erosion Control)

Use RECPs that bear the Quality and Date Oversight and Review (QDOR) Seal from the ECTC. Independent test results from the NTPEP, that the mulch, when tested according to ASTM 6459 Standard Test Method for Determination of Rolled Erosion Control Products (RECP), Performance in Protecting Hillslopes from Rainfall-Induced Erosion, meets the performance requirement using the Revised Universal Soil Loss Equation (RUSL).

- Functional Longevity.

- 1.	Temporary Degradable.

a.	Duration.

1)	Short-Term RECPs. (RECPs 3 - 12 months)

C Factor = .15 maximum

Test Soil Type = Sandy Loam

(National Resources Conservation Service (NCRS) Soil Texture Triangle)

2)	Moderate (Extended) -Term RECPs. (RECPs 24 months)

C Factor = .05 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

3)	Long-Term RECPs. (RECPs 36 months)

C Factor = .01 maximum

Test Soil Type = Sandy Loam (NCRS Soil Texture Triangle)

b.	Product types.

1)	Mulch-Control Nets (MCNs). Planar woven natural fiber or extruded geosynthetic mesh used to anchor loose fiber matting/mulches.

2)	Erosion Control Blankets (ECBs). Processed natural and/or polymer fibers, yarns or twines mechanically, structurally, or chemically bound together to form a continuous matrix with a minimum weight of 8 oz/yd2 and a limiting shear stress of 0.45 lb/ft2.

3)	Netless. Fibers mechanically interlocked and/or chemically adhered together.

4)	Single-net and Double-net. Fibers mechanically bound together by single or double netting.

5)	Open Weave Textiles (OWTs). Fibers woven into a continuous matrix.

c.	Materials.

1)	Burlap. Standard weave with a weight of 3.5 to 10 oz/yd2.

2)	Jute Mesh Fabric. Cloth of a uniform, open, plain weave of undyed and unbleached single jute yarn. Use yarn that is loosely twisted and not varying in thickness more than one-half its normal diameter. Furnish jute mesh in rolled strips meeting the following requirements:

a)	Width: 45 to 48 inches,  1 inch

b)	78 warp-ends per width of cloth (minimum)

c)	41 weft-ends per yard (minimum)

d)	Weight: 20 ounces per linear yard,  5%

3)	Woven Paper or Sisal Mesh Netting. Woven from twisted yarns available in rolls 45 to 48 inches wide. Mesh may vary from closed to open weave, ranging from 1/8 to 1/4 inch openings. Shrinkage after wetting may not exceed 20% of the surface area.

4)	Knitted Straw Mat. Commercially manufactured ECB. Use photodegradable netting and biodegradable thread. Use straw, in an air-dried condition, from oats, wheat, rye, or other approved grain crops that are free from noxious weeds, seeds, mold, or other materials detrimental to plant life. ECB may contain coconut or fiber to reinforce the straw. Straw material shall be certified weed-free straw using NAWMA Standards. In-lieu of certified weed-free straw, provide documentation that the material is steam or heat treated to kill seeds or provide U.S. or state's department of agriculture laboratory test reports, dated within 90 days prior to the date of application showing that there are no viable seeds in the straw.

5)	Woven/Curled Wood blanket. Machine produced mat of curled wood shavings with a minimum of 80% 6 inch or longer fibers, with consistent thickness and the fibers evenly distributed over the entire area of the blanket. Smolder resistant without the use of chemical additives. Cover the top side of the blanket with biodegradable extruded plastic mesh.

6)	Coconut (Coir Fiber). Machine produced mat, ECB of consistent thickness and coir fiber evenly distributed over the area of the mat. Use bio/photo degradable netting and thread.

- 2.	Permanent.

a.	Product Types and Materials.

1)	Turf Reinforcement Mats (TRMs). A rolled erosion control product composed of non-degradable synthetic fibers, filaments, nets, wire mesh, and/or other elements, processed into a permanent, three-dimensional matrix of sufficient thickness with a minimum weight of 8 oz/yd2 and a minimum limiting shear stress of 1.5 lb/ft2. TRMs (may be supplemented with degradable components) shall impart immediate erosion protection, enhance vegetation establishment during and after maturation and permanent vegetation reinforcement providing long-term functionality.

727-2.03 SEDIMENT RETENTION FIBER ROLLS (SRFRs). Fiber rolls also referred to as wattles. Manufacture of photodegradable or biodegradable fabric netting without preservative treatment, evenly woven, free of crusted material, cuts, and tears. Manufacture stakes of photodegradable or biodegradable material (wood stakes, except as approved by the Engineer).

- 1.	Filter Sock (Wattle)

a.	Fabric netting.

b.	Filled with wood fiber, straw, flax, rice, coconut fiber material.

c.	Minimum diameter 5 inches.

- 2.	Compost Sock.

a.	Extra Heavy weight fabric netting with a minimum strand width of 5 mils.

b.	Filled with coarse compost.

c.	Minimum diameter 8 inches.

- 3.	Coir Log.

a.	Woven wrap bristle coir twine netting.

b.	Filled with 100% coconut (coir) fiber uniformly compacted.

c.	Segments maximum length 20 foot, diameter as suited to the application and a density of 7 lbs/pcf or greater.

d.	Coir twine strength equal to 80 lb minimum weaved to a 2 inch x 2 inch opening pattern.

e.	Ties made of hemp rope by 1/4 inch diameter.

727-2.04 COMPOST. Suitable for serving as a soil amendment or an erosion control material. Sanitized, mature compost meeting local, state, and Federal quality requirements tested and certified by the U.S. Composting Council (USCC) under the Seal of Testing Assurance (STA) Program. Biosolids compost must meet the Standards for Class A biosolids outlined in 40 Code of Federal Regulations (CFR) Part 503. Additionally, meet the requirements of the AASHTO specifications:

- 1.	Compost Blankets. Standard Practice for Compost for Erosion/Sediment Control (Compost Blankets) R 52-10.

- 2.	Compost Filter Berms and Filter Socks. Standard Practice for Compost for Erosion/Sediment Control (Filter Berms and Filter socks) R 51-10.

727-2.05 TACKIFIER. Tackifier, viscous overspray, generally composed of dry powered vegetable gums derived from guar gum, psyllium and sodium alginase; asphaltic emulsions; petroleum distillates; co-polymer emulsions; and lignosulfonates and used to anchor soil, compost, seed, the mulch fibers to one another, and the ground. Contain no growth or germination inhibiting materials nor significantly reduce infiltration rates. Tackifier shall hydrate in water and readily blend with other slurry material. Tackifier options include:

- 1.	Type A. Organic tackifier with certification of plant sources; or

2.	Type B. Synthetic tackifier with certification confirming product is not harmful to plants, animals, or aquatic life.

727-2.06 POLYACRYLAMIDE (PAM). Use as a tie-down for soil, compost, seed and as a flocculent. Polyacrylamide (PAM) products shall meet the requirements of American National Standards Institute (ANSI)/National Sanitation Foundation International (NSF) Standard 60 for drinking water treatment, be anionic (not cationic), linear and not cross-linked with an average molecular weight greater than 5 Mg/mole, minimum 30 percent charge density; contain at least 80% active ingredients and a moisture content not exceeding 10% by weight.

- Deliver PAM in a dry granular powder or liquid form.

727-2.07 GEOTEXTILE-ENCASED CHECK DAM AND SEDIMENT BARRIER. Urethane foam core encased in geotextile material (silt fence material Section 633), minimum 8 inches height by minimum base width of 16 inches by minimum 7 foot length.  Overhang the geotextile 6 inch minimum each end with apron type ties by 24 inches each side of the foam core.

727-2.08 SANDBAG.

1.	Sandbag Sack Fabric. Fabric shall be a nonwoven, needle punched design meeting the Minimum Average Roll Values (MARV) verified in accordance with ASTM D4759.

- 2.	Seam Thread. Similar durability to the sandbag sack fabric.

- 3.	Sandbag Fill Material.

a.	Selected Material	Subsection 703-2.07		Type B

4.	Cinch Ties. Plastic ties or equivalent tie recommended by the sandbag manufacturer.

727-2.09 MANUFACTURED INLET PROTECTION SYSTEM.

- 1.	Manufacturers:

a.	Ultra Tech International – Ultra-DrainGuard

b.	Bowhead Environmental and Safety - StreamGuard Exert II Sediment Insert

c.	Enpac - Catch Basin Insert, Oil and Sediment or

d.	Approved equal.

727-2.10 CLEAR PLASTIC COVERING. A clear plastic covering meeting the requirements of the National Institute of Standards and Technology (NIST) voluntary Product Standard PS 17 - 69 for polyethylene sheeting having a minimum thickness of 6 mils.

727-2.11 STAPLES. U-shaped staples for anchoring matting, approximately 6 inches long and 1 inch wide. Machine-made: No. 11 gage or heavier steel wire.  Hand-made: 12-inch lengths of No. 9 gage or heavier steel wire.

## SECTION 729

## GEOSYNTHETICS

729-2.01 GEOTEXTILE, SEPARATION AND STABILIZATION.

1.	Separation. Meet AASHTO M 288 for Separation, except provide a minimum permittivity of 0.05 sec-1

2.	Stabilization. Meet AASHTO M 288 for Stabilization, except provide a minimum permittivity of 0.08 sec-1

729-2.02 GEOTEXTILE, SUBSURFACE DRAINAGE AND EROSION CONTROL.

1.	Subsurface Drainage. Meet AASHTO M 288 for Subsurface Drainage.

2.	Erosion Control. Meet AASHTO M 288 for Permanent Erosion Control.

729-2.03 PAVING FABRIC. Meet AASHTO M 288 for Paving Fabric.

729-2.04 SILT FENCE. Meet AASHTO M 288 for Temporary Silt Fence.

729-2.05 GEOGRID. Biaxial polymer grid, specifically fabricated for use as a soil reinforcement, having high tensile strength, modulus, and stiffness in both principal directions. Use a single-layered, integrally-formed grid structure. Use either extruded or punched and drawn polypropylene or high density polyethylene. Geogrid must be UV-stabilized, chemically inert, and meet the physical requirements in Table 729-1.

- Package, label, handle, and store geogrid material according to ASTM D 4873.

- TABLE 729-1

GEOGRID PHYSICAL REQUIREMENTS

| PROPERTY | REQUIREMENT | TEST METHOD |
| --- | --- | --- |
| Average Aperture Size, MD(1) XD(2) | 0.8-2.0 in. 0.8-2.0 in. | I.D Calipered Maximum Inside Dimension |
| Installation Damage Resistance | 80% (3) | Sample per D5818 Test per D6637 |
| Rib Thickness, min. (Nominal) | 40 mils | Rib Thickness Calipered Minimum |
| Tensile Strength, min. At 2% Strain At 5% Strain | MD & XD 400 lb/ft 800 lb/ft | ASTM D6637 |
| Junction Strength, min. | 90%(4) | GRI GG-GG2 |
| (1) MD: Machine Direction which is along roll length. (2) XD: Cross machine direction which is across roll width. (3) 80% relative to pre-installation Tensile Strength values. Perform Test install using GP or GW Class soil. (4) 90% relative to Ultimate Tensile Strength as determined by ASTM D6637 |  |  |

## SECTION 730

## SIGN MATERIALS

730-2.01 SHEET ALUMINUM. Use alloy 6061-T6, 5052-H36, 5052-H38, or recycled aluminum meeting alloy 3105, as specified in ASTM B 209. Meet the thickness of aluminum sheet designated on the Plans. Verify alloy and temper designations by mill certification.

Before January 1, 2011, treat the aluminum base metal sheets with chromate conversion coating for aluminum to meet ASTM B 449, Class 2.

After January 1, 2011, treat the aluminum base metal sheets with a rinsed non-hexavalent chromium conversion coating for aluminum and aluminum alloys that meets ASTM B 921, class one. Handle the cleaned and coated base metal only by a mechanical device or by operators wearing clean cotton or rubber gloves. After cleaning and coating operations, protect the panels at all times from contact or exposure to greases, oils, dust or other contaminants.

Make each sign panel a continuous sheet for all lengths 72 inches or less in the horizontal direction. Use no more than one vertical splice for signs up to 144 inches in length and 48 inches or less in height.

Meet the panel dimensions specified with a tolerance of 1/16 inch. Furnish metal panels that are cut to size and shape and free of buckles, warp, dents, cockles, burrs and any other defects resulting from fabrication. Complete all possible fabrication, including shearing, cutting and punching of holes prior to the base metal preparation.

730-2.02 HIGH DENSITY OVERLAID PLYWOOD. Construct plywood sign panels, for Construction and Maintenance Signs, of high density plywood, exterior type Grade B-C or better. Meet the requirements in PS 1-66 Products Standard for Softwood Plywood, Construction and Industrial published by the Products Standards Section of the U.S. Department of Commerce.

Use high density type overlay, with the following properties:

1.	Minimum weight of 60 pounds per thousand square feet of surface

2.	Minimum thickness of 0.012 inch before pressing

3.	Contain a minimum resin content of 45% based on the dry weight of the impregnated fiber

4.	Contain sufficient resin content to bond itself to the plywood

| Single Panel Signs | Thickness, inches, Minimum |
| --- | --- |
| Up to and including 18 inches wide | 3/8 |
| Over 18 inches wide | 1/2 |
| Plywood shields on destinations signs | 3/8 |
| Multiple Panel Signs | 5/8 |

Prime the sign back with one coat of white exterior enamel undercoat and finish with one coat of white exterior enamel. Use primer recommended by the supplier of the finish coat which is completely compatible.

Before applying reflective sheeting:

1.	Clean the surface thoroughly with lacquer thinner, heptane, benzene, or solvent recommended by sheeting manufacturer.

2.	Sand the surface with light sandpaper or steel wool and wipe dry and clean with clean cloth.

730-2.03 REFLECTIVE SHEETING. Meet AASHTO M 268, for the type specified.

730-2.04 SIGN POSTS. Use the type and size of posts designated on the Plans.

- 1.	Metal Pipe Posts.

a.	Fabricate from steel pipe to meet ASTM A 53 Standard Weight (Schedule 40), Type E or S, Grade B. Furnish square posts with 7/16 inch diameter holes drilled or punched as necessary to permit mounting of the sign.

b.	Hot dip galvanize to meet AASHTO M 111 after fabrication. When cutting metal posts after hot dip galvanizing, minimize damage to the zinc coating and protect all exposed surfaces by treating the exposed area.

c.	Repair galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating to meet the applicable provisions of AASHTO M 36.

- 2.	Perforated Steel Posts.

a.	Fabricate posts from 0.105-inch (12 gauge) thick cold-rolled carbon steel sheets, commercial quality, to meet ASTM A 653 and ASTM A 924. Zinc coat, both sides, to meet coating designation G90. Form posts into a steel tube, roll to size, and weld in the corner.

b.	Perforate all members for their entire length with 7/16 inch diameter holes on 1 inch centers.

c.	Furnish members that are straight and with a smooth, uniform finish, with no splices.

d.	Ensure that all perforations and cut off ends are free from burrs.

e.	Ensure that consecutive sizes will telescope freely with a minimum of play.

- 3.	Finished Wooden Posts.

a.	Meet AASHTO M 168, except limit the sweep (circular deviation from a straight line) to 0.08 foot in 10 feet.

b.	Pressure treat wooden posts with one of the following:

- Pentachlorophenol in light oil solvent

- Acid Copper Chromite

- Ammoniacal Copper Arsenate

- Chromated Copper Arsenate

- Chromated Zinc Arsenate

- Chromated Zinc Chloride

- Copperized Chromated Zinc Chloride

Use the methods specified in Section 714, except do not incise lumber posts for signs. Meet the minimum retention of preservative specified for “Posts.”

c.	Treat all field cuts and holes in wooden posts by thoroughly swabbing, spraying or brushing with two coats of the same type of preservative as initially used. Apply wood preservative when the moisture content of the wood is less than 25% and there is no free moisture on the surface. Protect posts treated during wet weather from moisture. Apply wood preservative with suitable brush or other means that will result in adequate penetration.

- 4.	Wide Flange Posts.

a.	Steel. Meet ASTM A 36.

b.	Hot dip galvanize to meet AASHTO M 111 after fabrication. When cutting galvanized metal posts, minimize damage to the zinc coating and treat the exposed area as follows.

c.	Repair galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating to meet the applicable provisions of AASHTO M 36.

- 5.	Flanged Channel Posts. Use either of the following:

a.	Aluminum meeting ASTM B 221, alloy 6061-T6.

b.	Steel meeting ASTM A 36. Galvanize steel posts per AASHTO M 111.

- 6.	Square Non-Perforated Steel Tubes.

a.	Fabricate from 3/16 inch thick cold-rolled carbon steel sheets, commercial quality, to meet ASTM A 500, Grade B. Form posts into a steel tube, roll to size, and weld in the corner. Furnish with 7/16-inch diameter holes drilled or punched as necessary to permit mounting of the sign.

b.	Hot dip galvanize to meet AASHTO M 111 after fabrication. When cutting metal posts after hot dip galvanizing, minimize damage to the zinc coating and protect all exposed surfaces by treating the exposed area.

- Repair galvanized surfaces that are abraded or damaged at any time after the application of the zinc coating to meet the applicable provisions of AASHTO M 36.

- 7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM  A501.  The  tubing  shall  be  square  and  of  the  dimensions called for in the Plans with 0.2 inch thick walls. 0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized according to 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

730-2.05 Flexible Delineator Posts. Durable plastic material meeting the dimensions and colors shown on the Plans. Resistant to ultraviolet light, ozone and hydrocarbon damage and remain flexible at a temperature of minus 40 °F. Provide posts with reflectors that are capable of self-erecting and remaining serviceable after 5 head-on impacts at 55 mph and 10 impacts at 35 mph with an automobile at an air temperature of plus 40 °F.

730-2.06 ACRYLIC PRISMATIC REFLECTORS. Meet AASHTO M 290 and the dimensions and colors shown on the Plans.

## SECTION 740

## SIGNALS AND LIGHTING MATERIALS

740-2.01 GENERAL. Use electrical materials, devices, fittings, and hardware that conform to applicable NEMA and ANSI standards.

Use electrical products that are Third Party Labeled or Listed (by an approved independent electrical testing laboratory such as UL, ETL, CSA, etc.), unless otherwise indicated on the Materials Certification List (MCL).

Ensure that all material and workmanship, as determined by the Department, conform to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design.

Design and fabricate highway lighting structures to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions and the highway lighting sheets in the Plans. Use a wind speed of 100 mph with a gust factor of 1.3. Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 feet above the pole base.

Design and fabricate traffic signal structures to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions and Central Region Traffic Signal Details.  Design must meet Fatigue Category III, with galloping using a basic wind speed of 100 mph and Central Region standard loads.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations. Submit the stamped drawings and calculations for each pole to the Engineer for approval. Design for the complete-in-place structure including the supported hardware.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole and mast arm, including: design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including: materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

2.	Fabrication. Fabricate signal and lighting structures from tapered steel tubes with a round or 16 sided cross section. Orient hand holes located near the base of poles to face downstream of traffic flow.

- Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece. Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice. For slip type joints, provide a minimum overlap of two feet or 1.5 times the inside diameter of the female section whichever is larger. In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs. In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1 and which feature maximum yield strengths of 70,000 psi. Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3. The Department will not accept structures that contain or are made with laminated steel elements.

Fabricate each tube from no more than 2 pieces of steel. When using 2 pieces, place the longitudinal welded seams directly opposite one another. Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B.

Fabricate 10 to 15 feet long signal poles from 7 US Standard Gage sheet steel. Fabricate each post with a minimum inside diameter of 5 inches at the base plate. Use a 4 inch long piece of 4 inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms. To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments. Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a. Lift points added to the inside of tubes in place may be left in place.

Hot dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications. Completely submerge pole and mast arm segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF. Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding ¾ inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

c.	Out of round. Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from Grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding. Perform welding to conform to Subsection 504-3.01 8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous. Grind exposed welds flush with the base metal at slip fit joints for the length of the slip fit joint plus one half the diameter of the female section.

b.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

c.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT). If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order. In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

4.	Anchor Rods and Bolts. Furnish 2 inch diameter (nominal) anchor rods for signal poles that meet ASTM F1554 Grade 105, are 96 inch minimum length and conform to Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification and S-5 Charpy Impact Requirements. Hot dip galvanize according to AASHTO M232. Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods. Washers shall conform to AASHTO M293.

5.	Miscellaneous. Finish the edges of poles and mast arms to conform to the following requirements. Before hot dip galvanizing, neatly round the following features to the radius specified

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another. First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively. Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

d.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms. Grinding seam welds on multisided poles is not required, except in slip type joints.

- Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1. The measurements shown are for illustration purposes only. Use tags large enough to include required information using ¼ inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text. Secure the tags with two 1/8 inch blind rivets at the base of poles and the underside of mast arms. If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message. Provide the holes for the blind rivets before galvanizing.

- TABLE 740-1

POLE MARKINGS

Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms.

| POLES (including Mast Arms) | MEASUREMENTS | TAG MARKINGS |
| --- | --- | --- |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

740-2.03 WOOD POLES. Use wood poles for service or temporary installations of the class shown on the Plans or as specified in the Special Provisions.

- Use 35-foot poles, except for service poles use 25-foot poles.

Use mastarms and tie rods for wood pole installations that conform to Subsection 740-2.02, and to the details shown on the Plans. Provide each mastarm with an insulated wire inlet and wood pole-mounting bracket for mastarm and tie rod crossarm.

Use structural timber meeting Section 713. Do not use poles that have more than 180 degrees twist in grain over the full length. Ensure that the sweep is no more than 4 inches. Pressure-treat wood poles, that are not to be painted, after fabrication. Meet Section 714.

740-2.04 HIGH TOWER POLES.

1.	Design. Design and fabricate high tower lighting poles to conform to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations. Submit the stamped drawings and calculations for each pole to the Engineer for approval. Design for stresses on the completed structure with hardware in place.

a.	In the stamped calculations, indicate the edition of Standard Specifications to which the poles are being designed and provide the input data used to design each pole, including: design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide the criteria to which the poles are designed and the details for building the poles, including: materials specifications, slip fit joint dimensions, dimensions of the tube segments and other components, the total weight of each segment, the welds that will be made, and the welding inspection that will be done.

The pole manufacturer shall submit a pole installation plan that details the work required to assemble each pole, the locations of timber supports during and after pole assembly. Submit this plan with the stamped plans and calculations.

Submit the mill certifications for steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design high tower poles for a 50 year design life and the basic wind speed shown in the 2001 AASHTO Standard Specifications for Structural Supports or for 100 mph, whichever is greater. Use a gust effect factor of 1.14.

For fatigue design, use fatigue category I importance factors for lighting poles, and design poles that taper less than 0.14 inches of diameter per foot to resist the effects of vortex shedding.

Furnish poles fabricated from tapered steel tubes with a round, 16 sided cross section. Use no more than four tapered tube segments with slip type field splices to form each pole. For the slip type joints, provide a minimum overlap of 24 inches or 2 times the inside diameter of the female section whichever is larger.

- Furnish poles that allow the luminaire ring to descend within five feet of the base plate.

Design poles to support a load that consists of the lowering device and ten luminaires equipped with light shields. Use the following values for these components.

Component	 Projected Area	Weight

One lowering device	8.6 ft2	309 lbs

Ten luminaires	21.5 ft2	617 lbs

Ten light shields	30.0 ft2	22 lbs

2.	Fabrication. Provide a reinforced rectangular hand hole that provides an opening large enough to install the winch assembly.

Provide a detachable door over the handhole frame including hinges, nuts to fasten the door to the frame, and a neoprene gasket to provide a watertight seal around the frame. Provide for a locking mechanism for the handhole door.

Fabricate the reinforced rectangular hand hole to provide maintenance access to the integral luminaire lowering device with a minimum clearance of 12 inches and a maximum clearance of 13 inches between the top of the base plate and the bottom of the hand hole opening.

Fabricate the base plate to match the bolt circle diameter and the quantity and size of anchor bolts of the foundation detailed on the Plans.  Ensure the 2 inch anchor bolts conform to ASTM F 1554, Grade 105 with Supplemental Requirements; S2, Permanent Manufacturer’s Identification, S3, Permanent Grade Identification, and S-5 Charpy Impact Requirements.  Hot dip galvanize according to AASHTO M232.  Use nuts that conform to AASHTO Specification M292 of the grade, surface finish, and style for 2 inch diameter anchor rods.  Washers shall conform to AASHTO M293.

The distance from bottom of the leveling nut to the top of the concrete of the anchor bolts will not exceed one inch.

Install a hook to the left of the handhole for storing the winch control cable away from the top of the foundation. Provide a 1 inch wide hook that features rounded edges, a 1½ inch radius, and 3 inches between the low point and free end of the hook.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1. Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3.

Fabricate each tube from no more than 2 pieces of steel. When using 2 pieces, place the longitudinal welded seams directly opposite one another. Place the welded seams on adjacent segments to form continuous straight seams from the base to the top of the pole. The Department will not accept poles and mast arms made with laminated steel elements.

The Department does not allow holes made for lifting purposes in the ends of tubular segments. To add lift points, weld them at least 12 inches away from welds on the outside of female segments and on the inside of male segments. Before shipment, remove added lift points, grind the area smooth with the base metal, and hot stick repair the finish according to Subsection 660-3.01.8.a.

Provide the mounting brackets needed to install the luminaire ring lowering device, including the winch assembly, associated hardware, and the masthead assembly.

Around the top of each pole, provide a stabilizer system that prevents the luminaire ring from swinging freely when the top of the ring is within 24 inches of being fully docked in the masthead fitting. The stabilizer system shall consist of at least three crooked F shaped brackets located symmetrically around each pole. The brackets shall form a tapered bottom section and a parallel top section that restricts ring movement. Bolt each bracket to two channels welded to the pole shaft. With the Eagle lowering device, locate the brackets between the wheels that line the luminaire ring. Design and fabricate the brackets from stainless steel tubing to withstand the load and wind speed used to design the poles. The installed brackets shall just fit through a circle two inches smaller in diameter than the inside diameter of the luminaire ring.

- Notify the Central Region Traffic Design Engineer, five calendar days, before starting pole fabrication.

3.	Welding. Perform welding to conform to Subsection 504-3.01 8. Welding and the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals with interim revisions, the Central Region Traffic Signal Details, and the following:

a.	Make welds continuous. Grind exposed welds flush with the base metal at slip joints, the length of the slip fit joint plus on half diameter of the female section.

b.	Use CJP groove welds on longitudinal seams within six inches of CJP circumferential welds.

c.	In the ends of those segments that form a slip type joint, provide CJP longitudinal seam welds at least the length of the slip joint plus one half times the diameter of the female section.

d.	Use PJP and fillet welds to attach hand-hole frames to the tube.

e.	On steels 5/16 inch thick and thicker, inspect 100 percent of CJP welds by either radiography (RT) or ultrasound (UT).

f.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order. In steels less than 1/8 inch thick, complete the tests according to AWS D1.1.

Weld tags on the ends of segments that form slip type joints to facilitate field assembly. Locate the tags to ensure segment alignment when the tags are aligned. Attach the tags at least 12 inches away from the slip type joint. Include the shop drawing number to which the poles are fabricated and pole length on the tag.

4.	Miscellaneous. Finish poles to meet the following requirements. Before they are galvanized, neatly round the following features to the radius specified.

a.	On holes through which electrical conductors pass, provide a 1/16- inch radius on both edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another. First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively. Then for the length of the joint plus one half times the diameter of the female section do two things: grind down welds until a radius concentric is feature with the mating surface and remove material protruding from the two surfaces, and

d.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms. Grinding seam welds on multisided poles is not required, except in slip type joints.

5.	Rejection. The Department will reject poles containing segments that

a.	Are not fabricated according to these specifications and the approved shop drawings,

b.	Are bowed with sweeps exceeding ¾ inch throughout the length of the segment,

c.	Are out of round. Segments are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

d.	Do not provide the minimum overlap of 24 inches or 2 times the inside diameter of the female section, whichever is larger, in the slip type field splices when the pole is assembled.

6.	Galvanization. Hot dip galvanize pole segments and attachments to meet AASHTO M 111 and these specifications. Completely submerge pole segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, and then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF. Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove excess zinc from drip lines and points and the surfaces of tube ends that form slip type joints to provide a smooth finish.

740-2.05 CONDUCTORS. Use conductor sizes based on the American Wire Gage (AWG). Use sizes that conform to the Plans or, when not shown, to this subsection.

Use insulated conductors made of uncoated, stranded copper that conforms to the specifications of ASTM B 8. Use grounding conductors that are bare copper of the gage required by the NEC. They may be stranded, solid, or braided.

Provide the following markings on the outer coverings of conductors and cables on intervals of 2 feet or less: manufacturer, the number of conductors or pairs in cables, conductor size, 600V, the conductor or cable type and environmental conditions for which the conductor or cables are listed, and the symbol of an approved independent testing laboratory.

Use conductors meeting the referenced specifications for the following purposes:

- Power Conductors. For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, ICEA S-66-524, and NEMA No. WC7. Furnish conductors insulated with cross-linked polyethylene listed as type XHHW-2 and rated for 600 volts AC operation.

- TABLE 740-2

CONDUCTOR TERMINATION TABLE

| CONDUCTORS PER CABLE | CIRCUIT | WIRE COLOR | AWG. NO. | BAND LEGEND |
| --- | --- | --- | --- | --- |
| 7 | Vehicle Red Vehicle Yellow Vehicle Green Common Neutral Spare Spare Spare | Red Orange Green White White/Black Black Blue | 14 | Head No. |
| 7 | Vehicle Red Arrow Vehicle Yellow Arrow Vehicle Green Arrow Common Neutral Spare Spare Spare | Red Orange Green White White/Black Black Blue | 14 | Head No. |
| 7 | Vehicle Red Vehicle Yellow Vehicle Green Common Neutral Spare Vehicle Yellow Arrow Vehicle Green Arrow | Red Orange Green White White/Black Black Blue | 14 | Head No. |
| 4 | Pedestrian Don’t Walk Pedestrian Walk Common Neutral Spare | Red Green White Black | 14 | Head No. |
| 4 | Pedestrian Pushbutton Neutral Spare Spare | Black White Red Green | 14 | Head No. |
| 5 | Photo Electric Control Load to Contactor Neutral Spare Spare | Black Red White Orange Green | 14 | PEC |
| 3 | Flashing Beacon Neutral Spare | Black White Red | 14 | Head No. |
| 3 | Preemption Neutral Spare | Black White Red | 20 | “PRE” |
| 3 | Preemption Confirmation Neutral Spare | Black White Red | 14 | “PRECON” |
| 3 | Highway Luminaire Highway Luminaire Highway Luminaire Spare | Black Red White | 8 or 6 | Circuit No. Circuit No. |
| 3 | Service to Controller Neutral Spare | Black White Red | 6 or 4 | “SIG” No Band No Band |
| 3 | Sign Luminaire Sign Luminaire Sign Spare | Black Red White | 8 | SIGN SIGN |

Use size 10 AWG wire for illumination tap conductors. In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors. Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables. For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket. Use insulated conductors listed as type XHHW-2. Furnish these cables with one black, one white, and one red colored conductor and no grounding conductor. Use cables rated for 600 volts AC operation.

Use insulated conductors meeting ICEA S-66-524 and UL Standard 44. The jacket must also meet ICEA S-66-524.

- Power Cables. For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene that meets the requirements of XHHW-2, and a PVC jacket. Furnish these cables without an integral grounding conductor. Use cables manufactured according to UL Standard 1277, ICEA S-95-658, and NEMA No. WC70. Provide cables listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor.

- Control Cables. Wire with signal cable meeting IMSA 20-1 all vehicular signal heads, pedestrian signal heads, pedestrian push button detectors, flashing beacons, hardwired local coordination and preemption devices, and photoelectric controls.

- Detector Loops. Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

- Loop Lead-In Cables. Unless otherwise specified, use a tray cable that conforms to the following specifications to connect the loop detectors to the terminal blocks in the controller cabinet. Furnish this cable, also known as Snyder Cable; manufactured according to UL Standard 1277. Supply these cables third party certified as Type TC and certified for use in underground conduit or as an aerial cable supported by a messenger, and rated for 600 volts AC operation.

Use size 18 AWG, 16 strand, tinned copper conductors per ASTM B-33 insulated with wet-rated, cross-linked polyethylene similar to XHHW. Furnish conductors with insulation colors that match Table 660-1 twisted into pairs.

Provide each twisted pair with an overall aluminum foil coated mylar shield that provides 100% coverage and a 20 AWG tinned copper drain wire that is in constant contact with the foil side of the shield. Apply a tight fitting polyvinyl chloride jacket over the conductor assembly.

Only use the following loop lead-in cable, also known as shielded data cable, to rewire existing traffic signals when specified. Use cables that consist of 7 twisted pairs that consist of stranded, size 18 AWG tinned copper wire and polyethylene or polypropylene insulation. Furnish each pair covered with an aluminum foil shield, stranded copper drain wire, and an overall PVC or PE jacket. Use cable rated for 300 volts and whose colored pairs match those specified in Table 660-1.

- Detector Loops. Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans.

TABLE 740-3

INTERCONNECT TERMINATION TABLE

| 740-2.06 ELECTRICAL CONDUIT AND FITTINGS. Unless specified otherwise, use rigid metal conduit and fittings for raceways. Furnish galvanized rigid type conduit and elbows that conform to UL Standard 6 and are manufactured of mild steel according to ANSI C80.1. Furnish third party certified fittings designed for rigid metal conduit. TELEMETRY CABLE: Type PE-39, No. 19 AWG, Solid Copper, as noted on the Plans or in the Special Provisions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PAIR NO. | TIP | RING | PAIR NO. | TIP | RING |
| 1 | White | Blue | 14 | Black | Brown |
| 2 | White | Orange | 15 | Black | Slate |
| 3 | White | Green | 16 | Yellow | Blue |
| 4 | White | Brown | 17 | Yellow | Orange |
| 5 | White | Slate | 18 | Yellow | Green |
| 6 | Red | Blue | 19 | Yellow | Brown |
| 7 | Red | Orange | 20 | Yellow | Slate |
| 8 | Red | Green | 21 | Violet | Blue |
| 9 | Red | Brown | 22 | Violet | Orange |
| 10 | Red | Slate | 23 | Violet | Green |
| 11 | Black | Blue | 24 | Violet | Brown |
| 12 | Black | Orange | 25 | Violet | Slate |
| 13 | Black | Green |  |  |  |

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL Standard 651. Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL 651 B and NEMA TC-7-2000.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish. Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle. Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline. The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws. For loop detectors, furnish type X bodies and, for photoelectric control installation, furnish types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it. The movements include: axial expansion or contraction to ¾ inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to ¾ inch. The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

740-2.07 FUSED SPLICE CONNECTORS. Use fused, quick disconnect, splice connector that is weather tight and has two halves: a single-unit line side socket and a load-side plug. Use fuses that are 10 ampere, midget (13/32” x 1-1/2“) ferrule type with a fast acting current limiting (KTK type) design.

740-2.08 SIGN SWITCHES. Provide a NEMA 3R non-fused disconnect switch as shown on the Plans for each sign illumination installation.

740-2.09 CONTROLLER ASSEMBLIES. Provide solid state, traffic controller assemblies having level 2 conformance to NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements as defined in NTCIP1202.  Traffic Controller Assemblies must meet or exceed the Environmental Requirements of Section 2 of the NEMA TS2-2003 V02.06 document. The Original Equipment Manufacturer (OEM) and its manufacturing and testing facilities shall be ISO 9001:2000 certified for processes involving the Traffic Controller Assemblies.

Use traffic control equipment that is compatible with the existing traffic signal monitoring system. Compatibility must be 100% at the cabinet level to include inputs, outputs, telemetry protocol, and block upload and download of RAM data.

The existing traffic signal monitoring system includes the following equipment:

- Econolite ASC/2M-1000 Master Controller

- Aries Zone Manager (version 3.31) by Econolite

In addition, features of the existing local controllers and controller modules must be functionally duplicated to meet or exceed the performance of the existing equipment.

The existing local controller cabinets at other intersections include the following equipment:

- Econolite ASC/3-2100

	Use LED indicators for all electronic devices covered under Subsections 740-2.09 through 740-2.13.

740-2.10 CONTROLLER UNIT.

- Actuated Controller Unit (CU).

Provide solid state, Type A2N Actuated Controller Units (CU) meeting the requirements of Section 3 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements.

	The CU must meet the referenced National Transportation Communications for ITS Protocol (NTCIP) and comply with publication TS 3.2 the Simple Transportation Management Framework, and shall meet the requirements for Conformance Level 2

	The software shall comply with NEMA TS 3.3, the Class B Profile, and shall include both an EIA/TIA 232-E and an FSK modem interface for NTCIP based communications.

	The CU shall implement conformance groups and optional object groups as defined in NEMA TS 3.4 and TS 3.5 for A2N level 2.

	Provide controllers with display heaters or enhancements to improve viewing in temperatures below 0 F.

	Provide controllers having an interface compatible with SYNCRO-7 traffic modeling software.

Furnish Econolite ASC/3-2100 controller unit or approved equal also meeting the following requirements:

- HARDWARE

- 1.	Enclosure

a.	Compact the controller to fit in limited cabinet space. It shall rest on a shelf that is not more than 7" deep. External dimensions no larger than 10 1/4" x 15 1/4" x 9" (H x W x D).

b.	Construct the enclosure of aluminum and finish with an attractive and durable protective coating. Permanently display model, serial number, and program information on the top surface.

- 2.	Electronics

a.	Modular electronics with vertical circuit boards. Horizontal circuit cards are not acceptable.

b.	Use a microprocessor for timing and control functions. Verify continuing operation of the microprocessor by an independent monitor circuit that is set an output and indicate an error message if a pulse is not received from the microprocessor within a defined period.

c.	In the interest of reliability, do not use sockets for any electronic device.  Devices must be directly solder to the printed circuit board. Use surface mount parts for the majority of the electronic components in the controller.

d.	Use a built -in, high -efficiency switching power supply to generate required internal voltages as well as 24 VDC for external use. Regulate voltages and monitor with control signals. Mount the fuses on the front of the controller for 120 VAC input and 24 VDC output.

e.	Derive timing of the controller from the 120 VAC power line.

f.	Store user -programmed settings and intersection configuration data in Flash Memory. Memory requiring an energy storage device (battery or capacitor) to maintain user data is not acceptable. To facilitate the transfer of user programmed data from one controller to another, a data transfer module (data key) using a separate serial flash memory device is an option. This data transfer module shall be easily removable and directly accessible from the front of the controller. The controller will not require this module to be present for proper operation.

g.	Store controller software in Flash Memory devices. The controller software shall be easily updated without the removal of any memory device from the controller. The use of removable PROMS or EPROMS from the controller is not acceptable.  Option to update software on the controller using a Windows based computer. Allow updating the controller software via a serial or Ethernet port from the front of the controller. Updating the controller software shall require the intersection to be in flash for no more than ten seconds using Ethernet file transfer.

h.	Printed circuit boards shall meet the requirements of the NEMA Standard plus the following requirements to enhance reliability:

(1)	Plated -through holes and exposed circuit traces with solder.

(2)	Solder mask material covering both sides of the printed circuit board.

(3)	Clearly marked circuit reference designation for components and the polarity of capacitors and diodes adjacent to the component. Designated pin 1 for integrated circuit packages on both sides of printed circuit boards.

(4)	Printed circuit board assemblies, except power supplies, coated with a clear moisture -proof and fungus -proof sealant.

- 3.	Front Panel

a.	Front of the controller consisting of a panel for the display, keyboard, and connectors for necessary user connections. Maintenance of the electronic circuits and option installation will be possible by opening the front panel only.

b.	Required 16-line by 40-character/line alphanumeric liquid crystal display (LCD) to show program, and status information with the display area nominal measurements of 2½ inches x 4½ inches (H x W), or larger. Provide, for ease of viewing, backlighting by light emitting diodes and multiple levels of contrast adjustment. Adjustable display contrast with front panel mounted push buttons. The use of user potentiometers for display contrast will not be acceptable.

c.	Clearly labeled front -panel operator inputs and environmentally sealed electrometric keys. Including a 10 digit numeric keypad, nine function keys, an oversize ENTER key, and an oversize four arrow cursor control key.

d.	Required nine function keys, clearly labeled, and providing the following operation:

MAIN MENU - Pressing the Main Menu key displays the main menu.

- SUBMENU - Pressing the Sub Menu key from a data screen displays the current submenu.

NEXT DATA - Pressing the Next Data key searches for the first non -zero data field, thus allowing rapid search for valid entries.

NEXT SCREEN - Pressing the Next Screen key l displays the next screen, thus allowing rapid advancement from screen to screen.

- HELP - Pressing the Help key at a data entry field displays a help screen about that field.

- STATUS DISPLAY - Pressing the Status Display key presents the intersection status display.

NEXT PAGE - Pressing the Next Page key advances to the previous or next group of data entry screens in a submenu.

BACKLIGHT - Pressing up and down arrow -shaped keys adjusts the backlighting of the LCD display screen for brighter or dimmer contrast.

SPECIAL FUNCTION - Pressing the special function key places Pedestrian Calls while viewing the main status display, lock access to controller data until supervisor or data change access codes are entered, and enter hexadecimal values.

- CLEAR - Pressing the clear key aborts a data entry and restores the current value.

- 4.	Data Key

a.	A data key available for use as a database storage device (backup) or as a database transfer module capable of storing a minimum 256KB of data.

b.	The data key hot swappable, to be inserted and removed without powering down the controller.

c.	The data key capable of storing the entire controller database and shall retain the information without use of battery or capacitor backup.

d.	This key not required by the controller to be present during normal operation. 2.5. Connectors

e.	Accessible interface connectors from the front of the controller. Controller models able to accommodate different versions, as follows:

(1)	EMA TS2 Type 1

(2)	NEMA TS2 Type 2

(3)	NEMA TS1

f.	Connectors and signals compatible with the Econolite Model ASC/2, ASC/2S & ASC -8000 25 pin telemetry port and D connector.

g.	Capable of assigning special applications of input or output function to any input or output pin respectively on the interface connectors, with the exception of Flashing Monitor, Controller Voltage Monitor, AC+, AC -, Chassis Ground, 24 VDC, Logic Ground and TS2 Mode bits.

- 5.	Serviceability

a.	Electronic modules including the power supply easily removable from the front of the controller using a screwdriver as the only tool. Plug in connector for power and signal connections to the circuit boards.

b.	Allow the removal and replacement of any circuit boards without unplugging or removing other circuit boards, except for the power supply. No more than two boards attached together to form a circuit assembly.

c.	Designed for one side of any circuit board to be accessible for troubleshooting and testing while the controller is still in operation and accomplished without the use of extender cards or card pullers.

- DISPLAY

- 1.	Dynamic Displays

a.	Provide dynamic displays listed below to show the operational status of the controller and offering additional displays for programming. Possible to place vehicle, pedestrian, and preemption calls from the keyboard while displaying status information.

b.	Intersection status displaying a summary of ring, phase, coordination, preemption and time-based control status.

c.	Controller status display indicating current interval, pedestrian, density, maximum, and maximum extension timing by phase and ring. Display the status of vehicle and pedestrian signal outputs in combination with vehicle and pedestrian calls.

d.	Coordinator status display indicating the command source, current coordination pattern information, local and system cycle count, commanded/actual offset, offset correction, time based control status, hold, force off, vehicle permissive, split count down, split extension, offset from ring 1 and green band indications.

e.	Preemptor status display indicating priority (railroad, fire, emergency) preemptors and bus preemptors with calls, preemptor active, inhibit, and delay status. When a preemptor is active, the display also indicates preemptor interval, timing, duration, and hold status. A portion of the display indicating the controller status during preemption including current status, interval, and timing by phase and ring and the status of vehicle and pedestrian signals for each phase.

f.	Time base status display indicating the current time and date, the current day and week program, the active program step for both coordination pattern and time of day functions, the start time of the next program step, and the highest step used. Also displays the programmed selections of the active coordination pattern and time of day pattern.

g.	Communications status displays for Port 1 (SDLC), Port 2 (terminal) Port 3, Ethernet, and NTCIP.

h.	Port 1 (SDLC) status display indicating the frame responses from the MMU, the terminal and facilities BIUs and the detector BIUs.

i.	Ports 2 and 3 status display indicating the interconnect format, transmit, valid data, data error, carrier detect and the last valid command.

j.	An Ethernet status display indicating the line speed, the line status, the total number of transmit and receive counts and transmit and receive error counts.

k.	An NTCIP status display indicating the total number of SNMP and STMP transmit and receive counts.

l.	A detector status display indicating activity for up to 64 detectors. The display shows the detector calls as processed by the controller.

m.	Flash/malfunction management unit (MMU) status display indicating flash status plus MMU channel, conflict, and monitoring function status. A separate display indicating the results of the controller’s comparison of its MMU programming to the programming in the controller.

n.	An input and output status display indicating the activity of the logic level inputs and outputs to the controller.

- 2.	Programming Displays

a.	Programming displays in the form of menus to aid the operator in entering data from the front -panel keyboard.

b.	A main menu allowing the user to select a major function of the controller. A submenu shall then be displayed to allow the user to select a sub -function within the major function. A four arrow cursor key allows the user to scroll through programmed data.

c.	English language and traffic engineering terminology used throughout to facilitate programming. The display organization allows traffic personnel to program the controller without using reference cards or manuals.  Data entry and data screens shall be in logical order.

d.	Programming entries consisting of alpha -numerical values, YES/NO and ON/OFF entries. During program entry, new data is displayed as it is entered. Validated and stored entries only when the consistency check is preformed for entries that are constrained by other programmed data or when the ENTER or cursor key is pressed when they are not.

e.	An example of constrained data is the sequence of the phases within a ring. Checked with the phase compatibility, phases in the ring and start phases among others.

f.	An example of non-constrained data is the vehicular extension time entry.

g.	The keyboard entry software shall include context sensitive help screens. Help information accessed by placing the cursor on the data entry in question then pressing the HELP key. Help screens provided for keyboard entered data and shall include at a minimum range, description, and functional operation information for the data entry.

- PROGRAMMING

- 1.	Programming Methods

a.	Methods listed below shall be available for controller configuration and timing entries. The manufacturer shall be able to provide as off the shelf items firmware and software required to affect the listed methods and to implement network operation with system masters and host PC's.

(1)	Manual data entry from the front panel keyboard

(2)	Downloading from telemetry from a system master connected to a host PC in a closed loop system.

(3)	Downloading from a portable PC -compatible computer via an Ethernet or serial cable.

(4)	Transfer from one controller to another using the Ethernet port on each controller.

(5)	Transfer from one controller to another, or restoring for a back up copy, using a data transfer module (data key).

- 2.	Programming Security

a.	A minimum of three access levels available to provide programming security.

(1)	The highest or supervisor level shall have access to programming entries including setting access codes.

(2)	The second or data change level shall have access to programming entries except access codes.

(3)	The third or data display level shall only have access to displayed data. No access code shall be required to display data.

b.	User selectable, four digit access codes provided for the supervisor and data change access levels. Access codes shall initially be set to provide unrestricted access.

c.	If there has been no keyboard activity the controller shall automatically logoff the user after 30 minutes.

- 3.	Programming Utility Functions

a.	A copy function shall permit copying timing data from one phase to another. It shall also permit copying timing plan from one timing plan to another, one detector plan and detector options plan to another, coordination pattern data from one pattern to another and one sequence to another. This feature will facilitate data entry when programming any two or more phases with the same timing values, or detectors with the same programming, and/or two or more coordination patterns with the same pattern data.

b.	The controller unit shall contain a backup data base with user specified values stored in nonvolatile memory. A copy function shall permit transferring the backup database to the active database.

c.	A memory clear function shall permit the user to clear data entries for the following controller functions, either individually or all at once:

(1)	Configuration

(2)	Controller

(3)	Coordinator

(4)	Preemptor

(5)	Time base

(6)	Detectors

(7)	Logic Processor

d.	A sign on message shall allow the user to view the controller software version number. This message shall be displayed upon power up until a key is depressed. It shall also be possible to display the sign on message by keyboard selection. The sign on display shall allow a user defined message of up to two lines with 38 characters per line.

e.	The controller shall have the capability to output a memory image of the user programmed settings and intersection configuration data in binary format. This shall allow transferring the memory image data to a data key.

- ACTUATED CONTROL FUNCTIONS

The controller shall provide actuated control functions and operations required by the NEMA TS2 Standard.  In addition, it shall provide the features described in the following paragraphs.

- 1.	Phase Sequence

a.	The phase sequence of the controller shall be programmable in any combination of sixteen phases, eight concurrent groups and four timing rings.

b.	Phase sequence information shall be changeable from the keyboard and stored in EEPROM data memory.

c.	The standard phase sequence of the controller shall also be capable of being altered by coordination, time of day or external alternate sequence command.  The alternate sequence commands shall allow reversing the normal phase sequence of each phase pair as shown below:

Command A - reverses phases 1 and 2

Command B - reverse s phases 3 and 4

Command C - reverses phases 5 and 6

Command D - reverses phases 7 and 8

Command E - reverses phases 9 and 10

Command F - reverses phases 11 and 12

d.	The operator shall be able to select from a library of standard sequences.  As a minimum, the following shall be provided:

(1)	Standard NTCIP sequence

(2)	Two through eight phase controller

(3)	Sixteen phase quad left turn controller

(4)	Four single ring 4 phase controllers

(5)	Dual TS2 eight phase quad controllers

(6)	TXDOT three phase diamond controller

(7)	TXDOT four phase diamond controller

e.	An exclusive pedestrian clearance movement provided that will time and display the pedestrian indications with the vehicle movements remaining in all red.

- 2.	Timing Intervals

a.	Timing intervals shall be programmable from 0 -255 in one second increments or from 0 -25.5 in one tenth second increments, depending on the function.

b.	Four independent timing plans provided and selectable on a time of day basis or by coordination pattern. Each plan shall contain the following interval timings:

(1)	Minimum Green

(2)	Bike Green

(3)	Delay Green

(4)	Walk

(5)	Walk 2

(6)	Walk Maximum

(7)	Pedestrian Clearance

(8)	Pedestrian Clearance 2

(9)	Pedestrian Clearance Maximum

(10)	Pedestrian Carryover

(11)	Vehicle Extension

(12)	Vehicle Extension 2

(13)	Maximum 1

(14)	Maximum 2

(15)	Maximum 3

(16)	Dynamic Maximum

(17)	Dynamic Maximum Step

(18)	Yellow Clearance

(19)	Red Clearance

(20)	Red Maximum

(21)	Red Revert

(22)	Actuations before Reduction

(23)	Seconds per Actuation

(24)	Maximum Initial

(25)	Time before Reduction

(26)	Cars Waiting

(27)	Time to Reduce

(28)		Min Gap

c.	Guaranteed minimum interval values specified at the time of purchase and shall not be changed or overridden from the keyboard. Values provided for the following intervals:

(1)	Minimum green

(2)	Walk

(3)	Pedestrian clearance

(4)	Yellow clearance

(5)	Red clearance

(6)	Red revert

(7)		Overlap Green

d.	A bike green interval provided that will replace the phase minimum green if the interval time is larger than the min green time and if a detector input designated as a bike detector has been activated.

e.	Two Walk and Pedestrian Clearance intervals provided for each phase per timing plan. The second Walk and Pedestrian Clearance activated by a time base action plan.

f.	Two vehicle extension intervals provided for each phase per timing plan. The active vehicle extension interval selected by a time base action plan.

g.	If enabled, a Delay Green timer shall delay the vehicle phase from starting until the timer has expired. This shall provide an additional all red for the vehicles movement until the timing is complete.

h.	The Pedestrian Walk interval shall extend from Walk to the smaller of the Walk Max time or the phase maximum in effect with a constant input from the "Walk Extension detector".

i.	Volume density intervals shall include actuations before and cars waiting. Actuations before added shall provide a user specified number of actuations that must occur before adding variable (added) initial time. Cars waiting shall provide a user specified number of actuations, or cars waiting, that must occur before starting gap reduction. Gap reduction shall be initiated by either; time before reduction or cars waiting, whichever reaches its maximum value first.

j.	Capable of dynamically extending the maximum green time for each phase based on vehicle demand.  Three maximum green intervals shall be selectable per phase based on either time of day, coordination pattern or external input.  The initial interval shall be selectable as Max 1, Max 2, or Max 3. If the phase terminates due to max out for two successive cycles, then the maximum green time in effect shall automatically be extended by a dynamic max step interval on each successive cycle until it is equal to dynamic maximum. If the phase gaps out for two successive cycles, then the maximum green time reduces by the dynamic max step time until it reaches to the original max value.

k.	Each phase shall have a red maximum timing interval. An input (red extension) shall extend the all red period of the assigned phase as long as the detector input is true. This input must be true within the all red time of the assigned phase to be able to extend the all red period. If this detector fails then the all red extension feature shall be disabled.

- 3.	Overlaps

a.	The controller shall provide sixteen internally generated overlaps (A - P). These shall be individually programmable as standard, other (see Section 5.3.2) or minus green / yellow. The green, yellow and red intervals shall be individually programmable following termination of the parent phase.  The overlaps programmed as minus green / yellow overlaps shall provide overlap green when any of the overlap phases are green or when in transition between overlapped phases and a modifier phase is not green. The overlap will be yellow when an overlapped phase is yellow and the modifier phase is not yellow and none of the overlapped phases are next.

b.	The other overlap option shall provide for protected, pedestrian protected, not overlap, trailing, leading and advance green programming.

c.	A protected overlap shall be green, yellow, or red like a normal overlap except its outputs shall be blank when the protected phase is green, or the controller is transitioning to a non included phase.

d.	A pedestrian protected overlap shall be green under the following conditions :

(1)	When an included phase is green and the protected pedestrian is NOT in walk or pedestrian clearance

(2)	When the controller is in transition between included phases and a pedestrian protected phase is not next

(3)	After servicing an included phase pedestrian demand if there is enough time before max out to service the overlap minimum green

e.	The controller shall provide the capability of sixteen pedestrian overlaps. These shall be capable of overlapping the pedestrian displays of any combination of phases with a pedestrian movement.

f.	Overlap functions shall be programmable from the controller keyboard.

g.	The controller shall provide a programmable conditional service feature. When selected, the controller shall service an odd numbered phase once normal service to that phase has been completed and enough time for additional service exists on the concurrent even phase.

h.	A conditional service minimum green time shall be programmable for each phase. This interval shall ensure a minimum green if the phase is conditionally served.

i.	It shall be possible to program the controller to reservice the even phase after conditionally serving an odd phase. Once an even phase has been conditionally reserviced, the odd phase shall not be conditionally served again until returning to the concurrent group that is timing.

- 4.	Additional Features

a.	The following features shall be programmable for each phase in each of four separate detector plans:

(1)	Locking/non -locking detector memory

(2)	Vehicle recall

(3)	Pedestrian recall

(4)	Maximum recall

(5)	Soft recall No-rest phase

(6)	Enable Added Initial

b.	Also programmed by phase shall be:

(1)	Phase in use

(2)	Exclusive Pedestrian phase

c.	Soft recall shall return the controller to the programmed phase in the absence of other calls. 5.5.4.  If a phase is designated as a no rest phase the controller shall not rest in the phase.

d.	The controller shall permit power start and external start to be individually programmed by phase and interval.  Start intervals shall be green, yellow red, or yellow with overlaps forced yellow.

e.	During a power start condition, the controller shall be capable of timing an all red or flash interval before the power start phase (s) and interval are displayed.

f.	The controller shall provide guaranteed passage operation on a per phase basis.  When selected, this feature shall provide a full passage (vehicle extension) interval when a phase gaps out with a gap in effect less than the vehicle extension interval (preset gap).

g.	The controller shall provide both single and dual entry operation.  When selected, dual entry shall cause the controller to ensure that one phase is timing in each ring.

h.	It shall be possible via keyboard selection to inhibit the service of a phase with other phase(s) within the same concurrent group.

i.	The controller shall provide the following additional selectable pedestrian functions:

(1)	Actuated phase rest in WALK

(2)	Flashing WALK output

(3)	Pedestrian clearance protection during manual control

(4)	Pedestrian clearance through yellow

(5)	Pedestrian indications remain dark with no call

(6)	Pedestrian timing shall be capable of being carried over from one phase to another

(7)	Programming shall be provided to inhibit re-service of odd phases (left turns) within the same concurrent group.

j.	The controller shall provide a programmable simultaneous gap termination feature. When programmed, phases in both rings shall gap out together in order to terminate the green interval and cross the barrier.

k.	The controller shall provide automatic flash selection according to the requirements of the MUTCD.  Both the flash entrance and exit phases shall be programmable through the keyboard, and flashing shall be controlled by either setting the fault/voltage monitor output to be FALSE or by flashing through the load switch driver outputs.  If flash desired through the load switches, both the phase and flash overlap outputs either yellow or red as selected by the operator.  Automatic flash will be selectable by external input, system command, or time of day action plan.

l.	The controller provides dimming for selectable load switch outputs.  Dimming will be accomplished by inhibiting the selected outputs for alternate half cycles of the 120 VAC line.  Dimming controllable by time of day and an external input; both functions must be TRUE for dimming to occur.  Programming permits individual dimming of the Green/Walk, Yellow/Ped Clear, Red/Don't Walk outputs for each load switch.

- COORDINATION

Coordination functions to control intersection cycle lengths, system offset relationships, and phase split percentages provided as a standard feature, with no need for additional modules or software.

- 1.	Coordination Patterns

a.	Provide a minimum of 120 coordination patterns. Each pattern allows selection of an independent cycle length, offset value and split pattern. The coordination patterns selected using telemetry (system), hardwire, or non-interconnected (time base) coordination commands.

b.	The coordination patterns selected by the coordination command using the following formats:

Pattern. This format allows selecting the coordination patterns directly, that is, commanding Plan 1 selects Pattern 1. Pattern command includes 1 -120 patterns, pattern 254 shall select free and pattern 255 shall select flash.

Standard. This format allows selecting the coordination patterns using a pattern number derived from a cycle offset split command. Each pattern assignable to a specific cycle offset split combination. The coordination pattern selected using the formula:

(((Cycle – 1) * 20) + ((Split – 1) * 5) + Offset)).

TS2. This format allows selecting the coordination patterns as a function of Timing Plan and one of three offsets. With this format a minimum of 20 Timing Plans available for selection of one of sixty coordination patterns.

c.	The following functions programmable in each coordination pattern:

(1)	Cycle length

(2)	Split pattern

(3)	Offset value

(4)	Alternate phase sequence

(5)	Split and offset in seconds or percentage

(6)	Crossing artery pattern

(7)	Permissive timing

(8)	Action plan

(9)	Coordinated phase split extension

(10)	Timing plan

(11)	Actuated rest in walk

(12)	Phase re service

(13)	Ring extension

(14)	Split demand pattern

(15)	Ring displacement

(16)	Directed split preferences

(17)	Special function outputs

d.	The following functions shall be programmable for each of the 120 Split patterns:

(1)	Coordinated phase

(2)	Split value by phase

(3)	Omit by phase

(4)	Min recall by phase

(5)	Max recall by phase

(6)	Pedestrian recall

(7)	Max and Pedestrian recall

- 2.	Cycle Length

a.	One cycle length provided for each coordination pattern. The cycle adjustable over a range of 30-255 seconds in 1 -second increments.

b.	The cycle length serves as the reference time for coordination timing.

c.	For systems with a single system sync pulse, coordination timing synchronized to the leading edge of that pulse that serves as the master zero reference for offset timing.

d.	For hardwire systems with multiple sync pulses, the coordinator locks onto the correct sync by trying different syncs and checking for reoccurrence during successive cycles.

e.	After a valid system sync pulse has been received the coordinator checks for the proper occurrence of the system sync pulse during each subsequent cycle. If a sync pulse does not occur, the coordinator self syncs and continue to operate with the last set of coordination commands for a programmable number of cycles from 0-255. If a sync pulse does not occur within the programmed period (or until the first sync pulse is received), the coordinator shall revert to the non -interconnected coordination mode.

- 3.	Offset

a.	Offset normally defined as the time period from the system sync pulse to the beginning of the leading coordinated phase green (local zero). The coordinator capable of referencing the offset to the beginning of the lagging coordinated phase green, coordinated phase yield or start of yellow point.

b.	Offsets shall be programmable using both percent and seconds. The range is from 0-99% of the cycle length in 1% increments or 0-254 seconds in 1 second increments. An offset value of 255 results in free.

c.	Offset changes achieved by adding or subtracting cycle time over a maximum of three cycle periods to allow a smooth transition to the new offset. Other offset change methods may be to add 20% to each cycle or to snap to the sync point once the permissive periods are complete and the coordinated phases are green. Offset correction using dwell also selectable.

- 4.	Split

a.	Each split provides a split interval for each of sixteen phases. The split interval is programmable using percent or seconds. The range is from 0-99% of the cycle length in 1% increments or 0-255 seconds in 1 second increments.

b.	Split interval settings determine the maximum time, including vehicle clearance (yellow and red), for a noncoordinated phase, or the minimum time for a coordinated phase. Phase termination controlled by establishing a force off point for each phase within the cycle. Except for the coordinated phases the force off point is selectable to be a fixed point within the cycle or allowed to float. If floating force offs are selected each phase shall time no more than its own split interval.

c.	During coordination, it shall be possible to operate a coordinated phase as actuated or nonactuated.  If a coordinated phase is actuated, vehicle detections shall permit the coordinator to extend a phase beyond the normal yield point. Extended coordinated phase green shall be selectable using the same range as split interval settings (percent or seconds). If actuated coordinated phases are used they shall be able to have actuated or non -actuated (walk rest) pedestrian movements.

- 5.	Permissive Periods

a.	Permissive periods provided to control the time period during coordinated phases released to service calls on noncoordinated phases.

b.	Permissive timing begins at the lead coordinated phase yield point. A yield point automatically computed for the coordinated phase in each ring.  The coordinated phase yield point allows the coordinated phases to yield independent of each other. The yield point is the point that the coordinated phase is released to allow the controller to service calls on noncoordinated phases. The computation takes into account the coordinated phase split interval plus pedestrian and vehicle clearance times.

c.	Automatic permissive period operation provided by automatically calculating a permissive period for each noncoordinated phase. The permissive period shall consist of a separate vehicle and pedestrian period computed from the phase split interval and the vehicle/pedestrian minimum time. The controller answers a call only during the associated phase permissive period. However, once the controller has been released to answer a call, remaining phases are served in normal sequence.

d.	Single permissive period operation provided by defining a single time period per cycle beginning with the yield point during which the controller is allowed to answer phase calls for any phase. The duration of this period will be selectable in each coordination pattern.

e.	Dual permissive period operation provided. During the first permissive period, the controller answers only vehicle or pedestrian calls on the phases following the coordinated phase. If the controller yields to a call during this period, calls on the remaining phases are served in normal rotation. During the second permissive period, the controller shall answer calls on remaining phases except the first permissive phase. The duration of the two permissive periods, and the time to start the second permissive period (displacement), will be selectable in each coordination pattern.

- 6.	Phase Reservice

a.	If actuated coordinated phases are in use, it shall be possible to reservice noncoordinated phases within the same cycle if sufficient time remains. A phase shall be reserviced only if the permissive period for the phase indicates there is sufficient time remaining in the cycle to service the phase.

b.	Phase reservice shall be capable of being enabled/disabled in each coordination pattern. 6.8. Transition Cycles

c.	The controller provides a smooth and orderly transition when changing from free operation to coordinated operation and from one coordination command to another.

d.	During a free to coordinated transition, the controller shall initiate a pick up cycle beginning upon receipt of a sync pulse and a valid coordination command. The controller shall then enter coordination mode upon crossing a barrier or if resting in the coordinated phases.

e.	Each coordination command selects a pattern.  A command change implements concurrent with a sync pulse. Cycle, offset, and split changes does not take effect until local zero.

- 7.	Crossing Artery Control

a.	The coordinator capable of implementing dual coordination at an intersection where two arterials are under control of separate masters.

b.	An external input enables dual coordination. Once enabled, the coordinator places a continuous call on the crossing artery phases so as to ensure that these remain green for their full split interval.

c.	The coordinator outputs a crossing artery sync signal to indicate the beginning of the crossing artery phase split interval.

d.	Dual coordination forces a selectable crossing artery split plan to be used so as to allow a particular split to be optimized for dual coordination in each coordination pattern.

- 8.	Local Split Demand

a.	The coordinator provides a minimum of two split demand detector inputs that allow the selection of a preferred split plan based on intersection demand.

b.	If the split demand detector indicates continuous vehicle presence during a programmed monitoring period beginning with the onset of a selected phase green, the coordinator forces a selectable split plan to be in effect during the next cycle. This split plan remains in effect for a selected number of cycles from 0 - 255. A specific split plan is capable of being selected in each coordination pattern.

- 9.	Adaptive Split Demand

The coordinator provides a method to select the split using measurement of each phase’s green utilization. From the measurement, the coordinator determines which phase or phases had excess time that was not used during the last measurement period. Then the excess time is added to the first set of preferential phases. If the first set of preferential phases gapped out during the last measurement period, then the excess time will be added to a second set of preferential phases. If both sets of preferential phases gapped out during the last measurement period then the time shall be added to the beginning of the coordinated phases.

- 10.	Free Mode

a.	The coordinator provides a free mode of operation, where coordination control is removed.

b.	Free mode operation is selectable by coordination commands, by external input or by keyboard entry.

c.	The coordinator reverts to the free mode when active controller inputs or functions would interfere with coordination. Such inputs or functions include the following:

(1)		Manual control enable

(2)		Stop time

(3)		Automatic flash

(4)		Preemption

d.	The coordinator provides an active free mode, where coordination control is removed but the coordinator continues to monitor system sync so as to keep its timing in step with the system master.

- 11.	Manual Control

The controller allows manual override of the current coordination command from the keyboard. The manual command allows selection of coordination patterns to be in effect.

- 12.	Interconnect Modes

a.	The coordinator capable of operating with any of the following interconnects types:

(1)		Non-interconnected coordination (time-based)

(2)		Telemetry

(3)		Hardwired

b.	The coordinator is compatible with fixed time interconnect that provides the sync pulse superimposed on the offset lines. Also operates within an interconnected system using a separate sync line. The noninterconnected coordination mode serves as a backup when using telemetry or hardwired interconnect.

- 13.	Master Coordinator

The coordinator shall output the coordination command, including sync pulse. This will permit the controller to be used as a time of day master in a hardwired interconnected system.

- PREEMPTION

The controller shall provide a minimum of ten preemption sequences that can be programmed as either railroad-fire emergency or bus vehicle preemption sequences. Preemption capability standard and not requiring additional modules or software:

- 1.	Railroad-Fire-Emergency Vehicle Preemption

a.	The ten railroad fire emergency vehicle preemptors selectable as a priority or nonpriority Type. Priority preemptor calls overriding nonpriority preemptor calls. Low numbered priority preemptors overriding higher numbered priority preemptor calls. Nonpriority preemptor calls serviced in the order received.

b.	Each preemptor providing a locking and nonlocking memory feature for preemptor calls. If a preemptor is in the nonlocking mode and a call is received and dropped during the delay time, the preemptor is not serviced.

c.	Preemptor timing intervals programmable from 0 - 255 in one -second increments or 0 -25.5 in one - tenth second increments, depending on function. Delay, max presence, and duration timing intervals programmed from 0 – 65535 seconds in one -second increments.

d.	A programmable delay time interval shall be provided to inhibit the start of the preemption sequence. This interval shall begin timing upon receipt of a preemption call. This time shall be programmable from 0 - 255 seconds in one second increments.

e.	An inhibit time shall be provided as the last portion of the delay time interval. During this time, phases that are not part of the preempt sequence shall be inhibited from service. This time shall be programmable from 0 - 65535 seconds in one second increments.

f.	A programmable extend input causing the preemptor to remain in the dwell interval following the removal of the preempt call. If a preempt call is reapplied during this time, the preemptor shall revert to start of dwell interval. This time is programmable from 0 - 25.5 seconds in one tenth second increments.

g.	A programmable duration time provided to control the minimum time that a preemptor remains active. This time is programmable from 0 - 65535 seconds in one second increments.

h.	A programmable maximum time provided to control the maximum time that a preemptor input remains active and still be recognized by the controller. Once failed, the input must return to inactive state to be recognized again.

i.	Phase timing at the beginning of a preemption sequence remains in effect for a minimum time before the controller advances to the next sequential interval. If the phase has been timing for longer than the programmed preemptor minimum time, the controller shall immediately advance to the next sequential interval. Minimum times shall be programmable for the following intervals:

(1)	Green/walk/pedestrian clearance

(2)	Yellow

(3)	Red

j.	A phase shall advance immediately to pedestrian clearance if it has been timing a WALK interval at the beginning of a preemption sequence. It shall be possible to time the minimum pedestrian clearance through the yellow interval, or alternately to advance immediately to yellow. During preemption, pedestrian indicators is selectable as being a solid DONT WALK, OFF (blank) or fully operational.

k.	If an overlap is in effect when the preemption sequence begins, it shall be possible to terminate the overlap so that it remains red for the remainder of the preemption sequence. Overlaps terminating or forced to terminate shall time the preemptor minimum yellow and red clearance times.

l.	Each preemptor provides user programmable green, yellow, and red track clearance intervals. Timing begins immediately after the preemptor minimum red interval.

m.	Up to four permissive phases selectable as track clearance phases.  During the track clearance period, the selected phases times the track clearance green, yellow and red intervals once, and then advance to the hold interval. If track clearance phases are not selected the track clearance interval omitted from the preempt sequence and is the controller interval timing used if track clearance interval times have been programmed as zero.

n.	The preemption hold interval begins immediately after track clearance. It remains in effect until the preemptor duration time and minimum hold times have elapsed and the preemptor call has been removed or the preemptor maximum time has been exceeded. During the preemption hold interval, any one of the following conditions shall be selectable:

(1)	Hold phase green

(2)	Limited phase service

(3)	All red

(4)	Flash

o.	Any valid phase, except a track clearance phase, selectable as a hold phase. If hold phases are not selected, the controller remains in all red during the hold interval. If flash is selected for the hold interval, up to two permissive phases shall be selectable to flash yellow, and the remaining phases shall flash red. Overlaps associated with the phases flashing yellow also flashes yellow unless they have been forced to terminate, in which case flashes remain red.

p.	The preemptor shall immediately cause flashing operation if the preemption input and the track interlock input are not in opposite states and the track interlock function is enabled.

q.	Each preemptor provides a user programmable green, yellow, and red hold interval, during which the hold phase(s) shall operate normally, except that the minimum green interval time shall equal the hold green time. At the completion of the hold green interval, the controller times the hold yellow and red clearance intervals before transfer to the exit phases.

r.	Up to four permissive exit phases will be selectable to time after the preemption sequence is completed serving as transition phases to return the controller to normal operation. It shall also be possible to place calls on selected phases upon exiting preemption. The option causes the preemptor to exit preemption to the correct phase to maintain coordination.

s.	Each preemptor provides a user programmable exit maximum time.  Upon exiting the preemption sequence, times shall serve as the maximum green time effective for one controller cycle for all phases except hold phases.

t.	Preemptor linking permits preemption sequences, where lower priority preemptors may call the higher priority preemptors from their preemption sequence.

u.	Preemptor active outputs provided for each of the preemptors. The output sets to ON when the preemption sequence begins and remains ON for the duration of the sequence. Possible to program preempt active outputs to be ON only during preempt hold intervals. Additionally, it shall be possible to program the nonactive, nonpriority preemptor outputs to flash while another preemptor is active.

v.	Preemptors normally override automatic flash. It will be possible to inhibit this feature for each preemptor.

- 2.	Bus Preemption

a.	Ten bus preemptors provide control for bus or other low priority vehicles. Bus preemptors have low priority and are overridden by railroad/fire/emergency vehicle preemptor calls.

b.	The preemptor is programmed to accept either a 6.25 pulse per second signal with a 50% duty cycle or a solid input to identify a bus preemptor call. Bus preemptor calls shall be capable of preemptor call memory and served in the order received.

c.	Bus preemptor timing intervals programmable from 0 - 255 in one second increments or 0 - 25.5 in one tenth second increments depending on the function.

d.	A reservice time provided to avoid excessive utilization of the same bus preemptor. If a call is received before the reservice time has elapsed, the bus preemptor shall not be reserviced. If reservice time has not been entered then all phases with a call when leaving the bus preemption sequence shall be serviced before the bus preemptor may be served again.

e.	Bus preemptors shall provide delay, inhibit, and maximum time functions similar to those for railroad/fire/emergency vehicle preemptors described above.

f.	Bus preemptors shall provide the following entrance intervals:

(1)	Green/walk/pedestrian clearance

(2)	Yellow

(3)	Red

g.	At the completion of the entrance red clearance, the bus preemptor shall advance to the hold green interval. During this interval, up to four permissive phases shall be selectable to remain green until the minimum hold time has elapsed and the bus preemptor call has been removed or the preemptor maximum time has been exceeded.

h.	It shall be possible to program the controller to allow concurrent phases to be serviced for a bus preemptor with only one phase selected as the hold interval phase.

- 3.	Preemption Safeguards

a.	If a preemptor call is active when power is restored to a controller, the fault/voltage monitor output shall be set to FALSE, placing the intersection in flash. Similarly, if external start is applied during a preemption sequence, the intersection shall be set to flash. Intersection flash shall remain in effect until the preemptor call has been removed and the preemptor duration time has elapsed.

b.	An input provided to stop timing of the current active preemptor under control of the MMU/CMU.

c.	A preemptor safety interlock provided to cause the intersection to go into flash whenever the controller has been removed or has not been programmed for preemption. This is achieved with an appropriate signal to the MMU/CMU.

- 4.	Transit Signal Priority

a.	The controller includes a transit signal priority algorithm that provides for transit vehicle movement through the intersection, while not interrupting coordination or skipping phases.

b.	Provide a check in detector input that senses the arrival of the transit vehicle. When active this input initiates Transit Signal Priority (TSP).

c.	A TSP delay shall delay the beginning of TSP operation until a set interval after check in. 7.4.4. A check out detector input shall determine the departure of the transit vehicle.

d.	Assignment of a single pulse from the check in detector and check out detector to the controller inputs programmable to any controller input. Including, inputs from devices that continuously pulse (pulsing as long as the vehicle requires TSP) through EVP 1 - 4, for a controller with a C1 connector, or through Preemptor inputs 3 – 6, on a controller with an MSD connector.

e.	When under coordination the TSP sequence shall use alternate split times to accommodate transit vehicles while maintaining coordination.

f.	When under free operation the TSP sequence uses alternate maximum times to accommodate transit vehicle while not skipping phase.

- TIME-BASED CONTROL & NON-INTERCONNECTED COORDINATION

The controller shall include time based control. This capability is a standard feature and shall not require additional modules or software.

- 1.	Clock/Calendar Functions

a.	The controller shall provide a time of day (TOD) clock that is used for all time based control functions. The only required clock settings are the current time (hour, minute and second) and date (month, day and year). Day of week and week of year are automatically computed from the date setting. Also possible to set the number of hours that the local standard time is ahead or behind Greenwich Mean Time.

b.	During normal operation, the TOD clock shall use the power line frequency as its time base. When power is removed, a crystal oscillator maintains the time for up to 30 days. The oscillator has a timing accuracy of +/ - 0.005% over the entire NEMA temperature range as compared to the Universal Coordinated Time Standard.

c.	In addition to entering time and date via the keyboard, it is possible to download the information from another controller, a computer, or a system master.

d.	The controller includes a time reset input. This feature resets the TOD clock to 03:30 whenever the time reset input is TRUE.

e.	The TOD clock automatically compensates for leap year and shall be programmable to automatically switch to daylight savings time.

- 2.	Time Based Control

a.	Time based control utilizes a day plan program format.  The month program consists of 200 programmable schedules, each assignable to one of sixteen day programs.  Each day program consists of from 1 to 50 program steps that define a program for the entire day.  Each program step is programmed with a starting time and an action plan number.  The day plans are also assigned to days of the week and days of the month.

b.	Time based control shall use action plans to assign:

(1)	Coordination pattern number

(2)	Vehicle detector plan number

(3)	Controller sequence

(4)	Timing plan

(5)	Vehicle detector diagnostic plan

(6)	Pedestrian detector diagnostic plan

c.	Time based control shall also use action plans to enable:

(1)	Automatic flash

(2)	System override

(3)	Detector log

(4)	Dimming

(5)	Special functions

(6)	Auxiliary functions

(7)	By-Phase functions

(a)	Pedestrian recall - Walk 2 enable

(b)	Vehicle extension 2 enable

(c)	Vehicle recall

(d)	Vehicle max recall

(e)	Max 2 enable - Max 3 enable

(f)	Conditional service inhibit

(g)	Phase omit

d.	A minimum of 36 holiday or exception day programs that override the normal day program. Holiday programs capable of being set as floating (occurs on a specific day and week of the month) or fixed (occurs on a specific day of the year) and, possible to program a fixed holiday so that it automatically repeats in the following year.

e.	Possible to manually force any of the action plans to override the current action plan. The forced plan entered from the keyboard and remains in effect until removed.

- 3.	Non-Interconnected Coordination

a.	A minimum of 200 time base schedule programs shall be available for the day-programs. These shall not have to be entered in any special sequence. It shall be possible to add and delete steps from a day program without affecting any other day-program. Each of the program steps shall permit selection of the following functions:

(1)	Day program assignment

(2)	Start time

(3)	Action plan

b.	Selection of system override in an action plan allows the coordination pattern selected by the action plan to override the current telemetry or hardwire system commanded coordination pattern.

c.	When operating in the noninterconnected coordination mode the synchronization point for cycles references to a user selected reference time (sync reference), last event or last sync as selected from the keyboard. The sync reference time is that time at that cycles are reset to zero.

d.	If the sync reference time is selected, the synchronization point for the cycle selected by the current program step is computed using the present time, sync reference time, and cycle length. The synchronization point occurs whenever the present time is an even number of cycle length periods has occurred since the sync reference time.

- DETECTORS

- 1.	Detector Functions

The controller provides a minimum of 64 vehicle detector inputs. Each input is assignable to any phase and programmable as to detector function. Extend and delay timing is provided for each detector. Each detector is capable of operating in a lock or nonlock mode. The controller is capable of providing 16 pedestrian detector inputs. Each pedestrian detector shall be assignable to any phase.

- 2.	Detector Cross Switching

The controller provides detector cross switching that permits vehicle detectors to alternately place calls on assigned phases and assigned cross switch phases. If the assigned phase is not green and the cross - switch phase is green, the detector places calls on the cross switch phase. If the assigned phase is omitted, for any reason, the detector places calls on the cross switch phase.

- 3.	Detector Types

Each vehicle detector is user programmable to operate as one of the following 3 detector types:

- Type 0 (zero):		Supports all NTCIP or standard detector functionality.

Type 1:		(GREEN DELAY) The first detection received when the phase goes green is recognized immediately, whether the detector is active when green starts or is activated after the green is timing.  Detections received before the first timeout of the extension interval are also recognized immediately. Once the detector extension interval (not the phase extension interval) times out, further detector inputs are recognized only if continuously present for a period equal to the programmed delay time AND the delayed signal is NOT extended. The first detection received when the phase goes green, whether present when green starts or received later, is recognized immediately. Detections received before the first timeout of the extension interval are also recognized immediately. Once the detector extension interval (not the phase extension interval) times out, further detector inputs are recognized only if continuously present for a period equal to the programmed delay time AND the delayed signal is NOT extended.

Type 2:		(STOP BAR WITH EXTEND TIME AND RESET) The detector input must be true when assigned phase green starts else the detector is disconnected for the balance of phase green. If the detector input is true when phase green starts the extension timer is reset while the input remains true. When the detector input is removed the extension timer begins running. If another detector input is received before extension time expires, the extension timer is reset for the duration of the input and once again begins timing when the input goes false. This action is repeated until the extension timer times out, at which time it is disconnected for the balance of phase green.

- 4.	System Detectors

a.	Each detector input shall be capable of functioning as one of 16 system detectors.

b.	Vehicle detectors shall be capable of being assigned to a minimum of 16 speed detectors. Speed shall be detected using both one and two detector configurations. Speed shall be computed using a keyboard entered average vehicle length and loop length for a one detector configuration. When using two detectors, speed shall be calculated using a keyboard entered distance between detectors and travel time between detectors.

- SYSTEM COMMUNICATION

- 1.	On-Street Master Communications

The controller is capable of communicating with an on street system master. This capability provided by a separate telemetry module that is included in the controller when required by the plans and specifications. The telemetry module receives system master commands and data transmissions. In addition, it transmits the controller status, data base and system detector information to the system master.

- 2.	System Commands

a.	The telemetry module allows the controller to receive, as a minimum, the following commands:

(1)	Cycle, offset, and split (coordination pattern)

(2)	System sync

(3)	Special function commands (minimum of four)

(4)	Free and flash mode commands

(5)	Time and date

(6)	Request for local status

(7)		Recall to Max

b.	Commands must occur more than once in any three second period in order to be recognized.

c.	Mode and special function commands cleared after 20 minutes of loss of communication between controller and system master.

d.	Status Data – The status of each of the following functions shall be transmitted to the system master in response to a local status request:

(1)	Green and yellow status for all phases and overlaps

(2)	Walk and pedestrian clearance status for all phases

(3)	Vehicle and pedestrian detector status

(4)	Phase termination status

(5)	Local time

(6)	Coordination status

(7)	Command source

(8)	Sync or transitioning status of coordinator

(9)	Conflict flash status

(10)	Local flash status

(11)	Preempt activity and calls

(12)	Volume and occupancy data from a minimum of 16 system detectors

(13)	Speed data from a minimum of two speed detectors

(14)	Maintenance required (cabinet door open) status

(15)	Status of two user -defined alarms

e.	Split Reporting – The status of each of the following parameters calculated on a per-cycle basis and transmitted to the system master:

(1)	Actual time spent in each phase

(2)	Time of day at end of cycle

(3)	Phases forced off during cycle

(4)	Type of coordination operation

(5)	Whether transitioning to new offset

(6)	Cycle, offset, and split in effect during last cycle

(7)		Flash status if operation is Free

f.	Upload/Download Capability – The telemetry module provides the capability to upload/download the entire intersection database. Phase assignments for overlaps and preemptors are not to be downloaded to preclude unsafe controller operation. It is possible to inhibit downloading of phases in use and left turn head control. Data transfer shall not require the intersection to be in flash.

- 3.	Telemetry

a.	Telemetry shall utilize TDM/FSK data transmission from 1200 baud to 9600 baud over two pairs of wires. These may be leased lines (Type 3002, voice grade, unconditioned) or dedicated cable. Optional fiber optic communications capability shall also be available.

b.	The nominal transmitter output level shall be 0 dBm into a 600 ohm load.  The receiver sensitivity shall be -34 dBm and adjustable from -40 to +6 dBm.

c.	Parity and error checking employed to assure transmission and reception of valid data.  Indicators provided on the telemetry module to show telemetry activity as follows: transmit, receive carrier, and valid data.

d.	In the event of a telemetry failure, the controller shall revert to the noninterconnected coordination mode after it has self-synchronized for a number of cycles, which shall be selectable from 0 -255.

- 4.	Communications Protocols

The controller has the capability of supporting communications with traffic management systems using industry standard protocols with the installation of appropriate optional software. At a minimum the controller has optional software to support the following protocols:

- CalTrans AB3418

- ECPIP

- NTCIP

Level 2 as defined by Section 3.3.6 of NEMA TS2 - 2003. NTCIP v02.06 capabilities shall include for NTCIP mandatory and optional objects. The controller vendor provides access to controller data via vendor specific objects. These and other objects supported by the controller are defined in a standard MIB file.

- 5.	Ethernet Communications

The controller has the capability of supporting communications through Ethernet.  This communications uses internal circuitry. The Ethernet port supports auto sensing of 10/100 Base T and half or full duplex operation.

- 6.	External Clock

The controller has the capability of communicating with an external clock like a GPS or WWV clock in order to set its internal time of day clock.

- 7.	Communications Ports

a.	The controller have as a minimum the following internal communications ports:

(1)	Port 1. SDLC for communications to other devices in the cabinet

(2)	Port 2 Terminal port for communications with a computer for the purposes of uploading, downloading or upgrading the controller software

(3)	Port 3 Systems communications port. This port provides either communicate to an on -street master or a central computer system

(4)	An option circuit board is available to expand communications by adding two additional serial communications ports

b.	Serial communications shall operate at 1200 to 115.2 K baud

- DIAGNOSTICS

- 1.	General Diagnostics Features

a.	The controller includes both automatic and operator initiated diagnostics. This capability is a standard feature and shall not require additional modules or software.

b.	Automatic diagnostics verifies memory, MMU compatibility programming, and microprocessor operation each time power is reapplied to the controller. After power has been applied, diagnostics continually verify the operation of essential elements of the controller including at a minimum: PROM, EE PROM, communications, and the microprocessor.

c.	Operator initiated diagnostics allows the operator to verify proper operation of controller input, output, communications, keyboard, and display functions.  Both manual and automatic test modes are provided.

- 2.	Detector Diagnostics

a.	Time of day controlled detector diagnostics provided to allow testing vehicle and pedestrian detectors for no activity, maximum presence, and erratic output.

b.	A minimum of eight detector diagnostic plans provided. These plans shall be selectable on a time-of-day basis. This allows varying the detector diagnostic intervals to correspond with changes in detector activity.

c.	If a detector is diagnosed as failed, the associated phase is placed in one of the following keyboard selectable modes:

(1)	Detector fail recall from 1 to 255 seconds

(2)	Maximum Recall

(3)	Disable the detector from calling or extending.

d.	Diagnostics for NEMA TS2 detectors connected to the controller using a Bus Interface Unit (BIU) shall also include detection of watchdog, open and shorted loop, and excessive inductance change failures.

- LOGGING

The controller shall be capable of logging and reporting detector activity, detector failures, and the occurrence of selected events or alarms.  Logs shall be capable of being printed or displayed on the front of the controller.

- 1.	Detector Logging

a.	The controller includes a detector log buffer capable of logging volume, occupancy and average speed for selected vehicle and speed detectors.

b.	The detector logging interval has keyboard selectable as 5, 15, 30, or 60 minutes.

c.	Detector logging is capable of being enabled or disabled by time of day.

- 2.	Detector Failure Logging

a.	12.2.1. The controller includes a detector failure log buffer capable of storing a minimum of 100 time and date stamped detector failure events. Once logged, detector failure events remains in the log until cleared or the log buffer capacity is exceeded at which time the oldest detector failure events shall be overwritten.

b.	12.2.2. Detector diagnostic failures are recorded in the detector failure log including: no activity, maximum presence, erratic output, watchdog failure, open loop, shorted loop, and excessive inductance change. If a detector recovers after a diagnostic failure, a detector on -line event shall be stored in the detector failure log.

c.	12.2.3. Detector failure logging shall be capable of being disabled.

- 3.	Event Logging

a.	The controller includes an event log buffer capable of storing a minimum of 200 time and date stamped events or alarms. Once logged, events remains in the buffer until cleared or the log buffer capacity is exceeded at which time the oldest events shall be overwritten.

b.	At a minimum the following events logged: communication failures, coordination faults, MMU and local flash status, preempt, power ON/OFF, low battery, and status of a minimum of two alarm inputs, and an on line event logged when an event or alarm returns to normal status.

c.	If security is enabled, an event logged when a user enters a data change.  This event includes the user’s ID. It is necessary to log the first change only and not every change. Also an entry is recorded when a user logs in and out of the controller.

d.	Event logging shall be capable of being enabled or disabled for each category of event or alarm.

- 4.	OE logging

a.	The controller accumulates phase utilization data, phase termination data, and detector data for a number of cycles selectable by the operator.

b.	The MOE log includes the number of gap outs, force offs and max outs per phase.

c.	The MOE log includes the mode of operation and phase utilization. If the controller is operating under coordination, the log shall include the pattern in effect and the average phase split for each period. If the controller is operating free, the log shall include the timing plan (1 – 4), the maximum in effect and the average phase maximum for each period.

d.	Each logged period includes the volume, number of stops and the delay per phase.

e.	Each log period records the number of times a phase was skipped and the number of times walk was served per phase.

- EMULATION

1.	Emulation Software.  With each controller provide software designed to emulate the controller.  The emulation software shall employ the full functionality of the controller including but not limited to, Configuration, timing, coordination, preemption, time base, detector setup, status display, utilities including special logic and diagnostic information. The software shall employ a graphical user interface that looks and acts like the controller. The software shall be designed to operate on the latest Microsoft Windows operating system and be capable of direct interface with the latest version of Transoft Synchro traffic modeling software.

740-2.11 CONTROLLER CABINET.

Provide a controller cabinet that meets the requirements of NEMA Standard TS 2-2003 V02.06 Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2), Section 5 Terminals and Facilities and Section 7 Cabinets.

- 1.	Standard Features. Supply the following standard features:

a.	Materials

Unless otherwise designated in the Plans, provide cabinets constructed of sheet Aluminum.

b.	Cabinet Dimensions

Unless otherwise designated in the Plans, provide a size 6 cabinet as defined in NEMA TS-2 Table 7-1.

c.	Doors

(1)	Provide doors meeting the requirements of NEMA TS-2 Section 7.5.  The lock must accept a Best CX series core that will be installed by the Department after the Contract is complete.

(2)	Provide a Police Compartment meeting the requirements of NEMA TS-2 Section 7.5.7. The Police Compartment shall house the following switches:

(a)	"flash/automatic" switches that when placed in the "flash" position causes the intersection displays to go into the flashing mode.  When placed in the "automatic" position, the signal system must resume normal operation.

(b)	"signals on/off" switch that when placed in the "off" position removes power from the signal bus. Do not allow power on the bus when either "automatic" or "flash" operation is selected by any means.

(3)	Permanently label switches in the Police Compartment.

d.	Shelves

Provide shelves meeting the requirements of NEMA TS-2 Section 7.6. Provide additional laptop computer shelf mounted approximately 42 inches above ground level. The laptop shelf must accommodate a standard 17 inch computer and be retractable below one of the cabinets’ shelves.

e.	Finish and Preparation

Unless otherwise designated in the Plans, provide unpainted Aluminum Cabinets with a "natural" brushed appearance.

f.	Cabinet Mounting

(1)	Provide cabinet mounting features as defined NEMA TS-2 Section 7.8.

(2)	The cabinet manufacturer is responsible for providing a cabinet that will mount without modification on the foundation detailed in Alaska Department of Transportation Central Region, Regional Detail, Controller Cabinet Foundation.

g.	Cabinet Ventilation

Furnish a cabinet that fully meets the requirements of NEMA TS-2 Section 7.9 and the following:

(1)	Furnish the fan and cabinet vent with internally mounted metal covers that are fabricated to close off the flow of air during winter operation.

(2)	Equip the cabinet with a selectable, 600/900/1500 watt cabinet heating device. The heating device must have a remote air sensing thermostat. The contacts must be rated 20 amps, 120 volts, 60 hertz.

(a)	Construct the thermostat so that contacts close on descending temperature and are adjustable between 0 and 30 °F ±5 °F. The contacts must open on rising temperatures of 15 °F above the closing temperature. The adjustment must have an indicating pointer.

(b)	Connect the thermostat in series with an electrical resistance heater and blower fan. The blower fan must be rated for continuous duty. The heater and fan must be connected in parallel and rated 120 volts, 60 Hertz. Mount the unit in the vertical position on the cabinet door beneath the auxiliary "goose neck" cabinet light.  The thermostat shall be mounted immediately to the left of the heating device on the cabinet door.

(c)	Do not block the air intake or outlet.  Provide the unit with a SPST manual override switch that bypasses the thermostat to enable the fan and heater to operate at warmer temperatures.

h.	Auxiliary Cabinet Equipment

(1)	Mount a hooded incandescent light fixture with a 15 inch flexible "goose neck" from the cabinet door. Use a fixture UL rated to accommodate a 25 watt lamp with an integral "ON-OFF" rotary switch mounted on the lamp hood. Mount a fluorescent lighting fixture on the inside of the cabinet near the front edge. Use a fixture rated to accommodate an F15T8 lamp operated from a high power factor UL or ETL listed ballast.  The lamp must be included. The lighting fixture "ON-Off" switch must be a toggle switch mounted on an inside control panel. Include in the circuit a door actuated switch that turns the light ON when the door is open and OFF when the door is closed.

(2)	Provide three (3) paper sets of complete and accurate cabinet drawings with each cabinet. Make cabinet drawings available electronically in AutoCAD v2004 or later format and deliver with paper set.

(3)	Provide one paper set of manuals for the controller, Malfunction Management Unit and vehicle detector amplifiers with each cabinet. Make said manuals available in electronic Adobe "pdf" format and deliver with paper set.

i.	Cabinet Wiring

Neatly arrange the wiring within controller cabinets to conform to the requirements of Subsections 660-3.05 and 740-2.05. Furnish controller cabinets wired to accommodate

(1)	Configuration #4 in Table 5-2 of the NEMA Standards Publications No. TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP requirements with two each Type 2 detector racks.

(a)	Equip the cabinet with required control and auxiliary equipment connecting cables to operate the phases and detection indicated on the Plans, including future use.

(b)	Size wiring, switches, surge protectors, flash relays, and flashers to handle the necessary amperage required under full cabinet use.  Use orange colored wires to run from the flash transfer relay used for emergency flash programming.

(c)	Wire the cabinet to accommodate 6 unique preempt sequences as defined by NEMA TS-2 Section 3.7 and 2 auxiliary preempt sequences. Configure each detector rack to accommodate 4 unique sequences.

j.	Field Terminal Blocks

Provide Terminals and Facilities meeting the requirements of NEMA TS-2 Section 5, Configuration #4 (Table 5-2) and the following:

(1)	Provide 2 or more insulated terminal blocks to terminate field conductors. Provide each block with 12 poles with 10-32 screw type terminals. Use a terminal block that is a barrier type with removable shorting bars in each of the 12 positions and with integral type marking strips. Terminate conductors to a terminal block.

(2)	Terminate conductors from the controller unit in ring type terminal lugs or solder them to a through panel solder lug on the rear side of the terminal. Terminate other conductors in spade type terminal lugs.

(3)	Do not bring more than 3 conductors to any one terminal. Two flat metal jumpers, straight or U shaped, may also be placed under a terminal screw. Fully engage at least 2 full threads of terminal screws when the screw is tightened. Do not extend live parts beyond the barrier.

(4)	Terminals must be provided to terminate a future 25 pair interconnect cable with each conductor terminated on individual terminals. Terminate interconnect cable conductors on individual terminals.

(5)	On the right side of controller cabinets, install two 16 position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets. On the left side of the controller cabinets, install two 32 position bus bars, for terminating the equipment grounding and neutral conductors from field wiring.

k.	Cabinet Accessories

See NEMA Standard TS 2-2003 V02.06, Section 5 Terminals and Facilities, Figure 5-4 Cabinet Power Distribution Schematic for Items (1) through (6).

(1)	Disconnecting Means

(a)	Main circuit breaker must be a single pole, 30 ampere, 10,000 amperes interrupting capacity for each cabinet.

(b)	Auxiliary circuit breaker(s) must be single pole, 20 ampere, 10,000 amperes interrupting capacity to protect fan, heater, light, and convenience outlet(s).

The rating of the main disconnect means with overcurrent protection must be not less than 125% of the maximum anticipated continuous load. When using disconnecting circuit breakers, use "trip indicating trip free," Type.

(2)	Signal Bus. Connect the signal bus to the incoming AC line through a signal bus mercury contactor and an overcurrent protection device. Energize the signal bus mercury contactor to provide power to the signal bus. The current rating of the signal bus mercury contactor must be at least the current rating of the main overcurrent protection device.

(3)	AC Service Transient Suppression.  Connect the transient suppression device for the primary feed of the cabinet on the load side of the cabinet overcurrent protection device. The transient voltage suppression device connected to the controller power circuit must provide protection against voltage abnormalities of 1 cycle or less duration.

(a)	The suppressor must be solid state high energy circuit containing no spark gap, gas tube, or crow bar component. The current rating of the device must be 15 amps minimum. The device must provide transient protection between neutral and ground, line and ground, as well as line and neutral. If the protection circuits fail, they must fail to an open circuit condition. The device must meet requirements of UL Standard 1449.

(b)	The suppressed voltage rating must be 600 volts or less when subject to an impulse of 6,000 volt, 3,000 amp source impedance, 8.0/20 microsecond waveform as described in UL Standard 1449. In addition, the device must withstand, without failure or permanent damage, one full cycle at 264 volts RMS.

(c)	The device must contain circuitry to prevent self induced regenerative ringing. There must be a failure warning indicator light that must illuminate when the device has failed and is no longer operable. The transient suppression device must withstand a 20,000 ampere surge current with an 8x20 microsecond (time to crest x time to second halfcrest) waveform 20 times at 3 minute intervals between surges without damage or degradation to the suppressor. Output voltage must not exceed 500 volts at any time during the test. Use a device that is a solid state, high energy circuit with no spark gap, gas tube, or bar component.

(4)	Radio Interference Suppression. Equip each traffic cabinet, flasher, and other current interrupting device with a suitable radio interference suppressor installed at the input power point. Install the radio interference suppressor after the AC service transient suppression unit described in Subsection 740-2.11.1.k (3). It must provide a minimum attenuation of 50 decibels over a frequency range from 200 kilohertz to 75 megahertz, when used with normal installations.

(a)	The interference suppressor must be hermetically sealed in a substantial metal case filled with suitable insulating compound. Terminals must be nickel plated, 10-24 brass studs of sufficient external length to provide space for connecting two No. 8 conductors and must be so mounted that the terminals cannot be turned in the case. Ungrounded terminals must be properly insulated from each other and must maintain a surface leakage distance of not less than 1/4 inch between any exposed current conductor and any other metallic part, with an insulation factor of 100 to 200 megohms dependent on external circuit conditions.

(b)	The radio interference suppressor must have a minimum current rating equal to the rating of the main disconnect means as specified in Subsection 740-2.11.1.k (1) (a). It must be designed for operation on 120 volts, 60 hertz, single phase circuits and be UL and EIA compliant.

(c)	Connect the ground connection of the radio interference suppressor only to AC neutral. Do not connect to Earth Ground directly.

(5)	Communications Transient Suppression. Provide a transient suppressor for the system interface communications lines when used. This suppressor must withstand a 100 ampere 10 x 700 microsecond waveform 20 times at 30 second intervals between surges without damage or degradation to the suppressor. Apply the transient surge both line to line and line to ground. Output voltage must not exceed 8 volts line to line and line to ground. Output voltage must not exceed 8 volts line to line or 250 volts line to ground at any time during the test.

(6)	Control Panel. Provide and label a control panel assembly that is readily accessible from the front of the cabinet. The control panel assembly must consist of:

(a)	"controller power" switch to energize the controller while the signal lights are off or are being operated by the flasher. Label and rate the switch for load current.

(b)	An electrical outlet.  It must be a duplex, 3 prong, NEMA Type 5-20R grounding type outlet with independent ground fault circuit protection.

(c)	"auto/flash" switch that when placed in the "flash" position provides flashing operation without interrupting the controller unit power. When the switch is placed in the "auto" position the controller unit must provide normal operation.

(d)	"stop time/off/on" switch that when placed in the "stop time" position causes the controller unit to stop time. In the "off" position, the controller unit must be active regardless of external commands.  In the "on" position, the timing must be normal but subject to external command interruptions.

(e)	"heater by-pass" switch to bypass the remote heater thermostat.

(f)	momentary contact test switches to place calls on each vehicle and pedestrian phase. Switches must provide tactile feedback and be rated at 1 ampere, minimum, for a resistive load at 120 VAC and at 28 VDC.  Contacts must be coin silver or gold plated and be enclosed and labeled as to their function.

- 2.	Special Features. Provide special features if called for in the Plans or as specified in the Special Provisions.

Coordination "Remote/Time of Day/Free" Switch. When the switch is in the "Remote" position, supervisory functions performed on the controller unit from a master coordinator or central computer must operate normally.

When the switch is in the "Time of Day" position, the local controller must use the local coordinators time of day plan. When the switch is in the "Free" position, it must be possible to remove any or all coordination devices and maintain normal, non-coordinated controller operation without wire jumpers, jumper plugs or other special devices. Provide this switch if a local coordination or system modem/interface unit is shown on the Plans.

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

1.	Three Circuit Solid State Load Switches. Use load switches conforming to NEMA TS-2, Section 6.2 Three Circuit Solid State Load Switches and as a minimum include Light Emitting Diode indicators on the DC input circuitry. The load switch must have three independent switching circuits, each being an individually replaceable solid state module.

2.	Solid State Flasher. Use a NEMA Type III flasher unit that conforms to NEMA TS-2, Section 6.3 Solid State Flashers.

3.	Malfunction Management Unit (MMU). Provide Type 16 MMU to be fully compliant with the requirements of NEMA TS-2, Section 4. In addition, the MMU shall have a full intersection LCD back lighted signal on the front panel and shall be downward compatible with TS-1 CMUs.

4.	Flash Transfer Relay. Use flash transfer relays that meet the requirements of NEMA TS-2, Section 6.4 Flash Transfer Relays.

740-2.13 SPECIAL AUXILIARY EQUIPMENT.

Use the following special auxiliary equipment when called for on the Plans and/or Special Provisions:

Provide equipment meeting the requirements of the cited Sections of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

1.	Inductive Loop Detectors Units. Provide inductive loop detectors that conform to the requirements of NEMA TS-2, Section 6.5 Inductive Loop Detector Units.  Unless otherwise called for in the Plans provide 2 Channel Inductive Loop Detectors with audible feedback of detection events. The audible feature must be manually switchable between audible "on" and silent "off."

2.	Local Coordination Units. Provide actuated coordination that conforms to the requirements of NEMA TS-2, Section 3.6 Actuated Coordination.

3.	System Modem/Interface Unit. Supply a system modem/interface unit assembly that is compatible with the existing computerized traffic control system.

4.	Preemption Units. Provide preemption that conforms to the requirements of NEMA TS-2, Section 3.7 Preemption and the following:

Install the following components of the GTT Company’s Opticom Priority Control System according to GTT’s written installation instructions at the signalized intersections listed on the Plans.

a.	The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted "GTT OPTICOM Emitter" has been received and maintained for a period of 1.7 seconds.

b.	Use Opticom Priority Control System Model 792H emitters.

c.	Unless otherwise shown on the Plan use Opticom Traffic Control Systems Opticom Detector Model 721 preemption detectors.

d.	Furnish the appropriate number of Opticom Traffic Control Systems 754 Phase Selectors to meet the number of channels of detection for each intersection.  Use rack mounted phase selectors.

e.	When more than one detector is required per phase, furnish the appropriate number of harnesses for the 754 Phase Selectors to handle the auxiliary detection.

f.	Install Model 138 Optical detector lead in cable between the end of each signal mast arm and the controller cabinet.  Furnish enough slack in these cables for them to extend 2 feet beyond the end of each signal mast arm and to leave 10 feet of slack in the controller cabinet.  Seal both ends of each lead in cable with mastic lined, heat shrink tubing end caps.

g.	The controller, rather than the phase selector or auxiliary logic, must perform interval timing, signal sequences, and phase skips.

h.	Mount detectors according to manufacturer recommendations or as approved by the Engineer. Mount and aim detectors to provide maximum emergency vehicle recognition. Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

i.	When emitters are required, provide GTT Opticom Priority Control System, Model 792H Emitter with 793 in vehicle switch. The Emitter shall be factory programmed to the class and vehicle identification numbers assigned by jurisdiction as shown in the Plans and the following:

(1)	Class 0 and Vehicle ID. Number 0 (Zero) shall be disabled for Emitters.

(2)	Vehicle Id. Numbers shall be sequential, beginning with the lowest number in the EVP Emitter table for the appropriate class.

(3)	Provide one copy of 790IS Emitter Software Kit including "Y" cable.

(4)	One GTT Opticom Portable Emitter Kit with 792R emitter on a magnetic base, 793R switch and cigarette lighter adapter power cord in a "Camera Bag" case.

5.	Bus Interface Unit (BIU).  Provide BIU’s that fully meet the requirements of NEMA TS-2 Section 8. Unless otherwise called for in the Plans provide BIU’s that meet the NEMA designation BIU2.

6.	Traffic Logging System.  If called for in the Plans, furnish, and install in the controller cabinet, a stand-alone unit that collects, time stamps, and stores data in an unattended manner.

- Video Detection System.

a.	General.

(1)	System Hardware. Use machine vision system hardware consisting of the following components:

(a)	Color Machine Vision Processor (MVP) sensors as shown in the Plans

(b)	Terra Access Point (TAP)

(c)	Communication interface panel

(d)	Personal computer (PC)

The PC shall host the server and client applications that are used to program and monitor the other system components. The MVP sensor shall be an integrated color zoom camera and processor that perform real-time traffic detection. Each MVP sensor shall be programmable with a minimum of twenty detection zones to satisfy the traffic detection needs of a variety of simple to complex traffic applications. The detection zones shall be user-defined though interactive graphics software running on a PC. The detection zones and the associated traffic functions and alarms shall be downloaded to the MVP for operation. The real-time performance shall be observed by viewing the video output from the sensor with overlaid flashing detector’s to indicate the current detection state (on/off). Subsequent redefinition of detection zones shall be permitted for rapid reconfiguration of fine-tuning detection performance. The MVP sensor shall calculate detector states in real-time and communicate the detection information to the TAP that subsequently translates the detection state directly to a traffic signal controller in real time. The MVP sensor shall optionally store cumulative traffic statistics, internally in non-volatile memory, for later retrieval and analysis.

The MVP shall communicate to the Terra access Point, communications panel and the software applications using the industry standard TCP/IP network protocol. The MVP shall have a built in Internet Protocol (IP) address and shall be addressable with no plug in devices or converters required.

The Terra Access Point shall communicate directly with up to eight (8) MVP sensors and shall comply with the form factor and electrical characteristics to plug directly into a NEMA Type C or D detector rack providing up to thirty-two (32) inputs and sixty-four (64) outputs directly with a TS2 Type traffic signal controller.

The communication interface panel shall be hardwired into a traffic signal cabinet or junction box. The communication interface panel shall be a Eight-sensor model and provide the electrical termination of wiring for video, data, and power for the MVP.

The communication interface panel shall provide high-energy transient protection to electrically protect the Terra Access Point and connected MVP sensors.

(2)	System Software. The MVP sensor embedded software suite shall incorporate multiple applications that perform a variety of diagnostic processing. Its primary function is to detect vehicular traffic approaching or departing the MVP sensor in multiple traffic lanes. The detection shall be reliable, consistent, and perform under all weather, lighting, and traffic congestion levels.

There shall be a suite of client applications that reside on the host client/server PC. The applications shall execute under Microsoft Windows 98, 2000, Windows NT, and XP. Available client applications shall include:

(a)	Network Browser:  Learn a network of connected Terra Access Pints and MVP’s then show the topology in a logical hierarchical relationship

(b)	Detector Editor: Create and modify detector configurations to be executed on the MVP sensor

(c)	Operation Log: Extract the MVP run-time operation log of special events that have occurred.

(d)	Data Archive: Extract time interval cumulative traffic statistics in real time (on the same time interval spacing) or after long periods of data accumulation (for instance, once a day or once a week, etc.)

(e)	Software Installer: Reconfigure one or more MVP sensors with a newer release of embedded system software.

b.	Functional Capabilities

(1)	MVP Image Sensor. The MVP image sensor shall be an integrated imaging color CCD array with optics, high-speed image processing hardware and a general purpose CPU bundled into a sealed enclosure.  The MVP Sensor shall be equipped with a sunshield to reflect solar heat and to shield the CCD array from direct exposure to the sun. The CCD array shall be directly controlled by the general purpose CPU, thus providing high video quality for detection that has virtually no noise to degrade detection performance. The optics and camera electronics shall be directly controlled for optimal illumination for traffic detection. The lens shall be pre-focused at the factory, as required for operation. It shall be possible for the user to zoom the lens, as required for operation. The MVP sensor shall operate at a maximum rate of 30 frames per second when configured for the NTSC (US) video standard. The MVP shall process a minimum of twenty detector zones simultaneously placed anywhere in the field of view of the sensor.  The video output shall have the ability to selectively show overlaid graphics indicating the current real-time detection state of each individual detector defined in the video. The sensor output NTSC video shall be viewed with any compatible video-display device.

(2)	Differential Video. The MVP sensor shall output full motion color video through the means of a differential video port in NTSC format. The differential video is transmitted over a single twisted pair.

(3)	Power. The MVP sensor shall operate on 24 VAC, 50/60Hz at a maximum of 25 watts. The camera and the processor electronics shall consume a maximum of 10 watts and the remaining 15 watts shall support an enclosure heater.

(4)	MVP Operations Log. The MVP shall maintain a non-volatile operations log, which minimally contains:

(a)	Revision numbers for the current MVP sensor hardware and software components in operation.

(b)	Title and comments for the specific detector configuration file downloaded to the MVP.

(c)	Date and time the Operations Log was last cleared.

(d)	Date and time communications were opened or closed with the MVP.

(e)	Date and time of last power-up.

(f)	Time stamped MVP self diagnosed hardware and software error to aid in system maintenance and troubleshooting.

(5)	MVP Vehicle Detection. The real time detection performance of the MVP shall be optimized by following the set of guidelines for:

(a)	The traffic application to perform,

(b)	MVP sensor mounting location,

(c)	The number of traffic lanes to monitor,

(d)	The sizing, placement, and orientation of Count and Presence detectors,

(e)	Traffic approaching and/or receding from the sensor’s field of view,

(f)	Minimizing the effects of lane changing maneuvers.

(6)	Detection Zone Placement. The video detection system shall provide flexible detection zone placement anywhere and at any orientation within the field of view of the MVP sensor. Preferred detector configurations shall be:

(a)	Detection zones placed across lanes of traffic for optimal count accuracy or

(b)	Detection zones placed parallel to lanes of traffic for optimal presence detection accuracy of moving or stopped vehicles.

A single detection zone shall be able to replace one or more conventional detector loops connected in series. Detection zones shall be able to be overlapped for optimal road coverage. In addition, selective groups of detectors can be logically combined into a single output by using optional delay and extend timing and signal state information. Optimal detection shall be achieved when the MVP sensor placement provides an unobstructed view of each traffic lane where vehicle detection is required. Examples of obstructions are not limited to fixed objects. Obstruction of the view can also occur when vehicles from a lane nearer to the sensor obscure the view of the roadway of a lane farther away from the sensor.

(7)	Detection Zone Programming. Placement of detection zones shall be by means of a supervisor computer (PC) operating in the Windows 98, 2000 or Windows NT graphical environments, a keyboard, and a mouse. The monitor shall be able to show the detection zones superimposed on images of traffic scenes.

The detection zones shall be created by using a mouse to draw detection zones on the supervisor computer’s monitor.  Using a mouse and the keyboard it shall be possible to place, size, and orient detection zones to provide optimal road coverage for vehicle detection.  It shall be possible to download detector configurations from the supervisor computer to the MVP, to retrieve the detector configuration that is currently running in the MVP, and to back up detector configurations by saving them to the supervisor computer’s removable or fixed disks.

The supervisor computer’s mouse and keyboard shall be used to edit previously defined detector configurations to permit adjustment of the detection zone size and placement, to add detectors for additional traffic applications, or to reprogram the sensor for different traffic applications or changes in installation site geometry or traffic rerouting.

(8)	Detection Zone Operation. The MVP real time detection operation shall be verifiable through several means. The primary method shall be to view the video output of the sensor with any standard video display device (monitor).  The video with overlaid detection zones shall display each detector as white, when the state of the detector is ON, or as black, when the state of the detector is OFF. Each detector shall be selectively assignable to be visible or hidden in the detector flashing video display when the detector configuration file is programmed.

Additional verification of detector operation includes visual observation of the LED’s on the front of the TAP and/or confirmation of detection as recognized by the traffic controller.

(9)	Optimal Detection. The video detection system shall optimally detect vehicle passage and presence when the MVP sensor is mounted 30 ft. or higher above the roadway, when the image sensor is adjacent to the desired coverage area, and when the distance to the farthest detection zone locations are not greater than ten (10) times the mounting heights of the MVP. The recommended deployment geometry for optimal detection also requires that there be an unobstructed view of each traveled lane where detection is required. Although optimal detection may be obtained when the MVP is mounted directly above the traveled lanes, the MVP shall not be required to be directly over the roadway. The MVP shall be able to view either approaching or receding traffic or both in the same field of view. The preferred image sensor orientation shall be to view approaching traffic since there are high contrast features on vehicles as viewed from the front rather than the rear. The MVP sensor placed at a mounting height that minimizes vehicles image occlusion shall be able to monitor a maximum of six (6) to eight (8) traffic lanes simultaneously.

(10)	Terra Access Point Detector Port Master. The Terra Access Point card shall provide the hardware and software means for up to eight (8) MVP sensors to communicate real time detection states and alarms to a local traffic signal controller. It shall comply with the electrical and protocol specifications of the detector rack standards. The card shall have 1500 Vrms isolation between rack logic ground and street wiring.

The Terra Access Point card shall be a simple interface card that plugs directly into a NEMA TS2 Type C or D detector rack. The TAP TS2 card shall provide 32 phase inputs and 64 detector outputs.

(11)	MVP Input and Output Assignments. Input and Output assignments are programmed into the MVP through the local "Supervisor" port on the detector rack interface card. The MVP declares which input and output pins are utilized during operation, the card requires no software configuration or setup. Detector outputs shall be assigned to any detector type that changes on/off state and consecutive pairs of outputs shall emulate the output of two (closely spaced) detectors to report speed of individual vehicles.

(12)	Jumper Configurable TS1 I/O. Two jumpers shall permit the card to be configured so that all inputs and outputs go either to the rear edge connector or the front panel DB 15 connector.

(13)	Terra Interface Panel. The Terra communications interface panel supports one to Eight MVPs. The communications interface panel consists of a predefined wire termination block for MVP power, data, and video connections, a power transformer for the MVP, electrical surge protectors to isolate the TAP and MVP, and an interface connector to cable directly to the TAP.

(14)	MVP Sensor Power. The interface panel shall provide power for one (1) MVP through a step-down transformer, taking local line voltage and producing 28 VAC, 50/60 Hz, at about 30 watts. A 1/2 amp slow-blow fuse shall individually protect the step-down transformers.

(15)	High Energy Transient Suppression. The interface panel shall provide termination points for all street wiring of the MVP and high-energy transient protection. The interface panel shall provide high energy crowbar transient protection, to NEMA TS2 standards. The transient suppression shall protect all of the interconnected hardware.

(16)	Interface Panel I/O Terminations. The Terra interface panel terminal block includes terminations for one (1) to eight (8) MVPs.  This shall include terminations for:

(a)	3 termination points for power, Communications and Video to and from the MVP sensor

(17)	Supervisor Software Suite. The system software shall support either small or large networks of field hardware of MVP sensors, TAPs, and commercial telecommunications equipment. The communication of traffic data, alarms, video snapshots, etc. across the network shall use the client server relationship model. The central communications server, the ComServer, provides local or remote access to all networked field hardware to a variety of client applications that can execute simultaneously on the same host computer as the ComServer or across a local area network.  Local access shall provide direct hook-up/link to field hardware (for field installation and maintenance) even though the field hardware may be communicating to remote client applications. Remote access shall provide connection to specific field hardware over long distances as part of a larger interconnected network.  The Supervisor Software Suite shall consist of the ComServer and all of the supplied client applications.

The Supervisor Software Suite shall provide an easy to use graphical user interface and support all models/versions of the supplied MVP and Mini–Hub. The software shall support both still image and real-time viewing of video images within in Windows. Programming the MVPs and designating inputs and outputs from/to the TAPs shall be performed with detectors overlaid on still images and monitoring the detection performance of the MVPs shall be displayed with "live" video.

The Supervisor Software Suite consists of the:

(a)	ComServer, to provide the network communications services of deployed field hardware to client applications

(b)	Network Browser, to activate selected client applications with associated field hardware in the network

(c)	Detector Editor, to create and modify detector configurations to be executed on the MVPs and TAPs in the field

(d)	Operation Log, to extract the MVP run-time operation log of special vents that have occurred

(e)	Data Archive, to extract time interval cumulative traffic statistics in real time (on the same time interval spacing) or after long periods of data accumulation (for instance, once a day or once a week, etc.) and stored locally to the Supervisor PC

(f)	Installer, to reconfigure one or more MVPs with a newer release of embedded system software.

(18)	Supervisor Computer System. A supervisor computer system is not required.

c.	MVP Hardware

(1)	MVP Image Sensor. The MVP video detection system shall use medium resolution, color image sensor as the video source for real-time vehicle detection.

As a minimum, each image sensor shall provide the following capabilities:

(a)	Images shall be produced with a color CCD sensing element with horizontal resolution of at least 500 lines and vertical resolution of at least 350 lines.

(b)	Images shall be output as a video signal conforming to NTSC specifications.

(c)	Provide software JPEG video compression.

(d)	Useable video and resolvable features in the video image shall be produced when those features have luminance levels as high 10,000 lux during the day.

(e)	Useable video and resolvable features in the video image shall be produced when the ratio of the luminance of the resolved features in any single video frame is 300:1.

(f)	Provide direct real-time iris and shutter speed control.

(g)	Be usable for video surveillance.

(h)	An optical filter and appropriate electronic circuitry shall be included in the image sensor to suppress "blooming" effects at night.

(i)	Gamma for the image sensor shall be preset at the factory to a value of 1.0.

(2)	MVP Optics. The MVP image sensor shall be equipped with an integrated zoom lens that can be changed using either configuration computer software or a hand-held controller.

(3)	MVP Enclosure. The image sensor and lens assembly shall be housed in an environmental enclosure that provides the following capabilities:

(a)	The enclosure shall be waterproof and dust-tight to NEMA-4 specifications, and shall have the option to be pressurized with dry nitrogen to 5  1 psi.

(b)	The enclosure shall allow the MVP image sensor to operate satisfactorily over an ambient temperature range from –29° F to 140° F while exposed to precipitation as well as direct sunlight.

(c)	The enclosure shall allow the image sensor horizon to be rotated during field installation.

(d)	The enclosure shall include a provision at the rear of the enclosure for connection of the factory-fabricated power, communications, and video signal cable. Input power to the environmental enclosure shall be 110 VAC and either 50 or 60 Hz as an option.

(e)	A heater shall be at the front of the enclosure to prevent the formation of ice and condensation in cold weather, as well as to assure proper operation of the lens’ iris mechanism. The heater shall not interfere with the operation of the image sensor electronics, and it shall not cause interference with the video signal.

(f)	The enclosure shall be light-colored and shall include a sun shield to minimize solar heating and glare.

(g)	The front edge of the sunshield shall protrude beyond the front edge of the environmental enclosure and shall include provision to divert water flow to the sides of the sunshield.

(h)	The amount of overhang of the sunshield shall be adjustable to prevent direct sunlight from entering the lens or hitting the faceplate.

(i)	The total weight of the image sensor in the environmental enclosure with sunshield shall be less than 6 pounds.

(j)	When operating in the environmental enclosure with the power, communication and video signal cable connected, the image sensor shall meet FCC class B and CE requirement for electromagnetic interference emissions.

(4)	MVP Electrical. Connections for video, communications and power shall be made to the image sensor using a single connector (Easy Lock). The Contractor shall supply the 3 conductor (1175-006) 18 AWG Carolprene flexible cable, which will run from the back of the camera to the signal controller cabinet.

(5)	MVP Field Interface Equipment. An MVP communication interface panel shall be available for installation inside the traffic cabinet. The panel shall provide twisted-pair connection points with approved transient protection. Transient protection shall be included for each MVP image sensor. Additionally, the communication interface panel shall provide 110 VAC for each sensor using transformers that step down the voltage from the existing 110 or higher AC power available in the cabinet. The interface panel 3-wire input power shall be connected to the transient protected side of the AC power distribution system in the traffic control cabinet in which the panel is installed.

d.	System Installation. The supplier of the video detection system shall supervise the installation and testing of the video detection system and computer equipment. A factory certified representative from the supplier shall be on-site during installation. Install all video detection equipment in accordance with the manufacturer’s recommendations.

e.	System Training. Provide a four-hour session of training by a certified instructor to State personnel in the operation, setup and maintenance of the video detection system. Provide instruction and materials for a maximum of 10 persons and conduct the training at a location determined by the Engineer.

f.	Warranty, Service, and Support. The supplier, for a minimum of two (2) years, shall warrant the video detection system. Ongoing software support by the supplier shall include software updates of the MVP sensor, Terra Access Point and supervisor computer applications. These updates shall be provided free of charge during the warranty period. The supplier shall maintain a program for technical support and software updates following expiration of the warranty period. This program shall be available to the State in the form of a separate Contract.

740-2.14 VEHICULAR SIGNAL HEADS.

Provide Light Emitting Diode, (LED) Signal Heads that conform to the following publications:

	Circular Indications: Vehicle Traffic Control Signal Heads:  Light Emitting Diode (LED) circular Signal Supplement, 6/27/05 (ITE Publication ST-052). This is hereafter referred to as "VTCSH-Circular-05".

	Arrow Indications: Vehicle Traffic Control Signal Heads: Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement, 7/1/07 (ITE Publication ST-054).  This is hereafter referred to as "VTCSH-Arrow-07".

"The applicable ITE Specification", as used in this specification, means VTCSH-Circular-05 for circular LED indications and VTCSH-Arrow-07 for arrow LED indications.

1.	Signal Heads.

Use signal heads that: are the adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; are adjustable through 360 degrees about a vertical axis; and are mounted at the location and in the manner shown on the Plans. Ensure that all vehicular signal heads at any one intersection are of the same make and type, except for programmed visibility signal heads.

- Programmed Visibility Signal Heads.

	Indications provide a nominal 12 inch diameter circular or arrow indication.  Meet the VTCSH requirements for color and arrow configuration.

	Provide each section with a 1 inch cutaway visor.

	Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5 degree increments.

	The signal must be mountable with ordinary tools and capable of being serviced without tools. Preset the adjustment at 4 degrees below the horizontal.

	The visibility of each signal face must be capable of adjustment or programming within the face. When programmed, each signal face's indication must be visible only in those areas or lanes to be controlled.  During dusk and darkness, a faint glow to each side will be permissible.

	Program the head as recommended by the manufacturer and as directed by the Engineer.

- Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit.

a.	LED Optical Units.  Use Led optical units and lenses meeting the requirement of the applicable ITE specification for all indications.  Also meet the following requirements:

(1)	Gaskets. Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

(2)	Markings.  Provide LED Signal module with manufacturer applied markings listed in Section 3.6, Module Identification, of the applicable ITE Specification. For circular indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Circular Traffic Signal Supplement (June 27, 2005)." For arrow indications marking shall include: "Manufactured in conformance with the ITE Vehicle Traffic Control Signal Heads: LED Vehicle Arrow Traffic Signal Supplement (July 1, 2007)."

(3)	Compatibility. Use LED signal modules that are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

(4)	Testing Requirements.

(a)	All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

(b)	Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

(c)	Production Testing and Inspection.  Submit manufacturer's certification that all tests in Section 6.3 of the applicable ITE Specification have been successfully completed on each LED module to be used on the project.

(d)	Design Qualification and Quality Assurance Testing by an Independent Lab. Have ETL/Intertek or other approved OSHA "Nationally Recognized Testing Laboratory" do the following:

i.	Perform an initial assessment of the manufacturer's factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

ii.	Perform initial Design Qualification Testing as specified in Section 6.4 of the applicable ITE specification.

iii.	Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of the applicable ITE specification:

6.4.2 Conditioning

6.4.4.1 - 6.4.4.4 Luminous Intensity

6.4.4.6 Chromaticity

6.4.6.1 Current Consumption

6.4.6.6 Power Factor

6.4.6.7 Total Harmonic Distortion

iv.	Provide a certification label on each certified LED traffic signal module verifying the manufacturer's factory and modules passed the tests listed in i. through iv. above.

(5)	Warranty. Provide written warranty by the signal module manufacturer that covers defects in materials, workmanship, and compliance with the applicable ITE specification for a period of 60 months after the manufacture date. No new LED module will be accepted if its manufacture date is more than 12 months before the date of installation. Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules.

The warranty does not include the cost of removing failed modules or reinstalling new modules.

Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

b.	Lens. Use only clear lenses for all green signal modules.  Use lenses that meet the requirements of the applicable ITE Specification.

c.	Housing.

(1)	Use die cast aluminum, meeting ASTM B 85, for all parts of the housing, including the doors and end plates. Ensure all parts are clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

(2)	Use a one-piece housing with integral top, bottom, sides, and with square doors, for each signal section.

(3)	Use stainless steel for all exposed bolts, screws, hinges, pins, and door-locking devices. Use stainless steel or approved non-ferrous, corrosion-resistant material for all interior screws and fittings.

(4)	Provide an opening in the top and bottom of each housing to accommodate standard 1-1/2 inch pipe fittings and brackets.

(5)	Provide the top and bottom openings of each housing with integral serrated bosses that will provide positive positioning of the signal head in 5-degree increments to eliminate undesirable rotation or misalignment of the signal head as well as between sections. Provide a total of 72 teeth in the serrated boss. Ensure teeth are clean and sharp to provide positive position with the grooves of the mating section or framework.

(6)	Fasten individual signal sections together with a cadmium-plated tri-stud connector, lock washers, and nuts with access holes for the passage of electrical conductors form one section to another.

(7)	Provide 2 integral hinge lugs on the left side of each signal housing for mounting the door.

(8)	Provide 2 latches with stainless steel wing nut assemblies on the right side of each signal housing to engage the door latches.

(9)	Provide each signal housing door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal in a NEMA Type 3R enclosure.

(10)	Provide a round opening designed to accommodate any standard traffic signal lens in each signal housing door.

d.	Backplates. Backplates shall not be louvered. Install backplates around vehicular signal faces except post mounted flashers.  Furnish backplates constructed of 0.100 inch minimum thickness aluminum alloy sheet meeting ASTM B209, alloy 3003-H14. For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16" aluminum rivets or bolts peened after assembly.

Furnish 3 inch wide backplates regardless of where the signals are installed, on mast arms, on top of posts, or on the sides of poles.

e.	Signal Mounting Hardware: Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1-1/2 inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments. The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews. Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings. Post top adapters without a terminal compartment or compartments - provide manufactured of bronze metal.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals. Each terminal must accommodate at least three 14 AWG conductors. Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish (2) ½ inch x 13 hot dip galvanized bolts that conform to ASTM A325 and (2) ½ inch hot dip galvanized washers that conform to ASTM F 436.

- When replacing signal heads include all mounting hardware, backplates and visors.

f.	Finish. Factory finish housing, backplates and visors, each face, with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363, and ASTM D-522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.15 PEDESTRIAN SIGNALS. Use LED Pedestrian Countdown modules that use the international "HAND/WALKING PERSON" symbols.  Except for the countdown indication and as otherwise noted in this specification, use modules that conform to “Pedestrian Traffic Control Signal Indications - Part 2: Light Emitting Diode (LED) Pedestrian Traffic Signal Modules” Institute of Transportation Engineers, 3/19/2004, (hereafter referred to in this document as “PTCSI-04”) and to the applicable Sections of the current Alaska Traffic Manual.

- Pedestrian Signal Modules: Provide Portland Orange “HAND” and “COUNTDOWN DIGITS” and lunar white “WALKING PERSON.”   Locate COUNTDOWN DIGITS adjacent to the associated UPRAISED HAND.    Make “HAND” and “WALKING PERSON” symbols a minimum of 11 inches high and 7 inches wide and COUNTDOWN DIGITS a minimum of 9 inches high and 7 inches wide.  Provide incandescent looking WALKING PERSON, HAND and COUNTDOWN DIGITS.  Ensure the WALKING PERSON, UPRAISED HAND and COUNTDOWN DIGITS are not readily visible when not illuminated.  Provide “AlInGaP” Portland Orange LEDs or equivalent, rated for 100,000 hours or more at 77ºF and 20 mA. Provide “InGaN” White LEDs.

Make all exposed components of modules suitable for prolonged exposure to the environment, without appreciable degradation that would interfere with function or appearance.

- Provide modules with an installed gasket to seal the junction with the signal housing.

- Lens.  Use modules with internal masks to prevent the icons and digits from being visible when not in operation. No external silk-screen is permitted. Provide a smooth or textured lens of transparent polycarbonate material, frosted to prevent sun phantom. Use lenses that will not crack, craze or yellow due to solar UV exposure typical for a south-facing Arizona desert installation, after a minimum of 60 months in service.

- Retrofit.  When a module will replace an existing module in an existing signal housing, furnish signal modules designed as retrofit replacements for existing neon type pedestrian signals (ICC 4090 and/or 4094).  Provide modules that do not require special tools for installation. Provide modules that fit securely into existing pedestrian signal housings without any modification to the housing, connect directly to existing electrical wiring, and form a weather-tight seal. Provide modules and components constructed so each retrofit of existing pedestrian signals only requires the removal of the existing neon message module, gasket, and power supply and installation of the new LED pedestrian countdown module. Provide all necessary components to complete conversion including a one piece gasket.

- Photometric Requirements.  Meet the following requirements:

- Minimum Luminance.  Maintain the following minimum luminance values for at least 60 months, under the operating conditions defined in Sections 3.3.1 and 5.2.1 of PTCSI-04 (when measured normal to the plane of the icon surface):

- WALKING PERSON 2,200 cd/m2,

- UPRAISED HAND 1,400 cd/m2,

- DIGITS 1,400 cd/m2 (when “88” is displayed).

- Maximum Luminance.  Provide modules for which the actual luminance of a module does not exceed three times the minimum maintained luminance, as defined in Section 4.1.1 of PTCSI-04,  when operated within the temperature range -40°F to +165°F

- Uniformity:  Provide modules for which the uniformity of the signal output across the emitting section of the module lens (i.e. icons or digits) does not exceed a ratio of 5 to 1 between the maximum and minimum luminance values as measured in 0.5 in. diameter spots.

- Markings. Permanently mark the back of each LED signal module with:

- Manufacturer’s name, trademark, and other necessary identification

- Warranty information

- Rated voltage and power consumption in volt-amperes

- An up arrow or the word “UP” or “TOP” for orientation within a signal housing.

- Electrical. Provide LED pedestrian countdown signal modules that:

- are operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

- have a maximum of 4 each secured, color coded, 36 inches long, 600V, 18 AWG minimum, jacketed wires, conforming to the National Electrical Code, rated for service at +221ºF for electrical connection.

- operate from a 60 ±3 Hz AC line over a voltage range of 80 VAC to 135 VAC. Test voltage for all photometric performance measurements shall be 120 ±3 volts rms.

- use LED circuitry that prevents perceptible flicker over the voltage range specified above.

- include voltage surge protection against high-repetition noise transients and low-repetition noise transients as stated in Section 2.1.8, NEMA Standard TS-2, 2003.  Module must meet the following test requirements:  Section 8.2 IEC 1000-4-5 & Section 6.1.2 ANSI/IEEE C62.41.2-2002, 3kV, 2 ohm and Section 8.0 IEC 1000-4-12 & Section 6.1.1 ANSI/IEEE C62.41.2-2002, 6kV, 30 ohm.

- have a current draw sufficient to ensure compatibility and proper triggering and operation of load current switches and conflict monitors in signal controller units. When the module is switched from the On state to the Off state the terminal voltage shall decay to a value less than 10VAC RMS in less than 100 milliseconds when driven by a maximum allowed load switch leakage current of 10 milliamps peak (7.1 milliamps AC).

- have a maximum power consumption at 77°F of:  Hand 11.0 watts, Walking Person 8.0 watts, Digits 10.0 watts (when display shows “88”)

- have waterproof strain relief and anti-capillary wires, or have electrical wires that do not penetrate the LED module housing.  This is intended to prevent water seepage between the back cover and the electrical wires, or between the copper and insulation of the wires (Connection may be made by use of an over molded connector).

- will default to the hand symbol for abnormal conditions when nominal voltage is applied to the unit across the two phase wires (rather than being applied to the phase wire and the neutral wire).

- have three separate power supplies: one each for the Walking Person, the Upraised Hand and the countdown digits.  Use separate circuitry to power the LED Walking Person icon and the LED Upraised Hand icon, in order to virtually eliminate the risk of displaying the wrong icon.

- Testing Requirements.

- All LEDs Functional.  LED modules with any non-functioning individual LEDs at the final inspection will be rejected.

- Burn-in.  Manufacturer shall energize each new LED module for a minimum of 24 hours at operating voltage before shipment to ensure electronic component reliability.

- Production Testing and Inspection by Manufacturer.  Submit manufacturer’s certification that all tests in Section 6.3 of PTCSI-04 have been successfully completed on each LED module to be used on the project.  Show result of each individual test on the certification.

- Design Qualification and Quality Assurance Testing by an Independent Lab.  Have ETL/Intertek or other approved OSHA “Nationally Recognized Testing Laboratory” do the following:

  - Perform an initial assessment of the manufacturer’s factory, engineering and manufacturing systems, and procedures to confirm compliance with ISO 9000.

  - Perform initial Design Qualification Testing as specified in Section 6.4 of the PTCSI-04.

  - Every 6 months, conduct a factory inspection and perform Quality Assurance Tests on two samples of each certified LED module in accordance with the following sections of PTCSI-04:

6.4.2 	Conditioning

6.4.4.1 - 6.4.4.4 	Luminous Intensity

6.4.4.6 	Chromaticity

6.4.6.1 	Current Consumption

6.4.6.6 	Power Factor

6.4.6.7 	Total Harmonic Distortion

  - Provide a certification label on each certified LED traffic signal module verifying the manufacturer’s factory and modules passed the tests listed in a. through c. above.

- Warranty. Provide a manufacturer’s written warranty that covers defects in materials, workmanship, and compliance with PTCSI-04 for a period of 60 months after the manufacture date.  No new LED module will be accepted on a project if its manufacture date is more than 12 months before the date of installation. Begin warranty period for modules that replace failed modules on the date of installation.

The warranty shall require the manufacturer to replace LED modules that fail within the warranty period with new LED modules at no cost to the Department, and to cover the cost of shipping failed modules. The warranty does not include the cost of removing failed modules or reinstalling new modules. Warranty shall require the manufacturer to send the Department prepaid authorization to return the failed module and provide a toll free telephone number for notifying them when it becomes necessary to return failed LED modules.

The warranty shall require the manufacturer to deliver replacement LED modules within 5 working days of receiving failed modules to the location specified by the Department.

- Countdown Module Functions.

- General. Begin the countdown at the beginning of the FLASHING HAND indication.  End the countdown at “0” at the end of the FLASHING HAND indication.  Make the countdown display dark from the end of one FLASHING HAND indication until the beginning of the next. Display steady, not flashing, countdown digits.  Do not provide user accessible switches, controls, or options that would allow modification of cycle time, icons, digits or that would allow the countdown to operate while the WALKING PERSON or STEADY HAND is displayed.

- Learning Cycle.  At power on, make the countdown display dark for one learning cycle in which it will determine the duration of the FLASHING HAND indication.

- Normal Operation.  Display the countdown/FLASHING HAND for the duration measured in the learning cycle for every cycle until the module measures a different FLASHING HAND duration.

- Countdown Duration Modification.  When a different duration is measured, make the countdown dark for the next cycle, and enter a Learning Cycle as previously described. Resume Normal Operation with the new FLASHING HAND duration if the measured FLASHING HAND duration for the next cycle is the same as for the first cycle when a change was detected. Continue Learning Cycles, if the duration is different, until the measured FLASHING HAND duration is the same for two cycles. Resume Normal Operation with the new duration when that happens.

- Countdown Truncation.  Make the digits dark if the controller output displays a STEADY HAND or if both the HAND and WALKING PERSON go dark, regardless of whether the countdown to zero has been completed.

- Preemption.  Handle preemption events as described under Countdown Duration Modification and, if necessary, Countdown Truncation.

- Recycling.  Allow for consecutive cycles without display of the STEADY HAND .

- Power Outage.  Maintain an uninterrupted countdown during short power failures (<1.5 seconds).  Make the digits dark after a loss of power of more than 1.5 seconds and enter a Learning Cycle when the power is restored.

- Housing:

- Provide signal housings that have maximum overall dimensions of 18-1/2 inches wide, 18-3/4 inches high, and 9 inches deep, including Z-crate-type visor and hinges.

- Provide a dustproof and weatherproof housing that allows easy access to and replacement of all components.

- Provide a one-piece, corrosion-resistant, aluminum-alloy die-cast case complete with integrally

cast top, bottom, sides and back. Provide 4 integrally cast hinge lug pairs, 2 at the top and 2 at the bottom of each case, for operation of a swing-down door.

- Provide 1 of the following 3 versions of the case, according to project specifications:

- Clamshell mount, with hardware, for “pole left of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

- Clamshell mount, with hardware, for “pole right of message” installation.  These need not include upper and lower openings, but when provided the openings must be plugged to be weather-tight.

- Make suitable for either post top or bracket mounting with upper and lower openings to accommodate standard 1-1/2 inch pipe brackets.  Plug unused openings to be weathertight.  Integrally cast a shurlock boss into the bottom opening of the signal case. Make the dimensions of the shurlock boss as follows: outside diameter, 2-5/8 inch; inside diameter, 1-31/32 inch; number of radial teeth, 72; and depth of teeth, 5/64 inch. Use clean and sharp teeth that provide full engagement to eliminate rotation or misalignment of the signal.

- Make the door frame a one-piece, corrosion-resistant, aluminum-alloy die-casting, complete with 2 hinge lugs cast at the bottom and 2 latch slots cast at the top of each door. Attach the door to the case by means of two Type 304 stainless steel spring pins. Attach 2 stainless steel hinged bolts with captive stainless steel wing nuts and washers to the case with the use of stainless steel spring pins. Provide a door that will latch and unlatch without the use of tools.

- Conductors:  Meet IMSA specifications 20-1 with No. 14 AWG or larger.

- Load Switches: Place all load switches for operation of pedestrian signals in the controller cabinet.

- Fasteners. Use machine screws, studs, and washers that are stainless steel.

- Gaskets: Use gaskets that conform to ASTM D 1056, Grade 2C2.

- Terminal Blocks: Mount a terminal block in the unit for field wiring, as specified in Subsection 740-2.14.

- Finish. Factory finish the outside of pedestrian signal head housings and visors and signal visor interiors with a single coat of environmentally safe, ultraviolet-resistant, polyester powder coating that is applied electrostatically at 90kV and baked for 20 minutes at 400 degrees Fahrenheit per ASTM D-3359, ASTM D-3363 and ASTM D-522. Coating to be a Dull Black finish meeting Federal Standard 595b-37038.

740-2.16 PEDESTRIAN PUSH BUTTONS. Push buttons shall be Tamper proof with a 2 inch minimum diameter convex 316 stainless steel actuator button.

Construct a weatherproof assembly designed to prevent an electrical shock under any weather condition and grounded per the NEC.

Push Button Switch. Furnish Polara model RBDLM2-B-4H or approved equal with the following features. Provide a solid state electronic piezo type, switching unit, with screw type terminals, rated 15 amperes at 125 VAC. Must have the following characteristics:

1.	Switching unit that is solid state electronic piezo rated for 100 million cycles.

2.	Sealed to prevent ice from impeding function.

3.	Must hold the call for a minimum of 5 seconds.

4.	Switch operating force of 3 pounds or less with no moving plunger or moving electrical contacts.

5.	Provide an LED indication and an audible tone or beep within the button when pushed.

6.	Must have a raised rim or ridges to protect the button from side impacts.

7.	Powder coated cast switch housing of dark olive green or black.

Where a pedestrian push button is to be mounted on top of a 2-1/2 inch diameter post, provide the housing with a slip-fitter with screws for securing to the post.

Factory finish pedestrian push button housings, mountings, brackets, and fittings with 2 coats of dull black enamel or powder coat.  Painting/powder coating is not required where the color is an integral part of the component material.

740-2.17 FLASHING BEACONS. Each beacon consists of a single section traffic signal head, meeting the provisions in Subsection 740-2.14 with yellow or red lens as shown on the Plans.

Each flashing beacon control unit consists of a circuit breaker, flasher, and terminal block housed in a single enclosure. Provide a NEMA Type 3R enclosure with top-hinged cover, hasp for sealing cover, and provisions for locking.

Furnish and install a radio interference and transient suppressor in the enclosure, meeting the requirements of Subsection 740-2.11.1.d.(3) and (4).

- Mount 20 amp, single-pole, 120 volt AC switches at the top and center of the dead front panel.

Use a solid state NEMA Type 3 flasher meeting the requirements of NEMA Standard TS 1-1989, Traffic Control Systems.

Use 20 amp, 600 volt barrier-type terminal blocks, molded from phenolic material, with plated brass screw-type terminals and integral-type marking strips.

740-2.18 ROADWAY LUMINAIRES. Furnish luminaires that conform the following specifications and provide the light distributions specified. When luminaire performance criteria are specified, luminaires shall also:

•	Meet or exceed the minimum initial light levels indicated.

•	Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified: luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic  photometric  data to the Engineer for approval. Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format. The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage. Furnish lamps that feature a rated life of 40,000 hours based on 10 hours per start and ballasts that conform to Subsection 740-2.21.

- 1.	Luminaries General

Install luminaires that feature:

a.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

b.	Third party certification for use in wet locations.

c.	Glass lenses, unless polycarbonate resin refractors are specified.

d.	Terminal blocks for attaching the illumination tap conductors.

e.	Aluminum reflectors with an ALZAK or ALGLAS finish.

f.	Optical components free of substances that affect photometric performance, paint.

g.	Housings cast with no provision for a photoelectric control receptacle.

h.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

i.	Plug in starting aids in fixtures with lamps through 400 watts.

- 2.	Luminaries – Cobrahead and Offset

Each cobrahead or offset luminaire shall also include:

a.	An easily removed hinged door used exclusively for mounting the ballast.

b.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

c.	A four bolt mounting brackets that fit 2 inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

- 3.	LED Luminaire

LED Luminaires shall be UL listed for wet locations and enclosure classified IP66 per IEC 529. The fixture shall be resistant to corrosion, ultraviolet degradation and abrasion. Nickel-chrome plated wire guard shall be used for providing anti-fouling protection from leaf/debris and animals nesting to assure cool LED operation.

The luminaire shall have five years warranty on the LED’s and the driver.  Average delivered lumens over 50,000 hours should be a minimum of 85% of initial delivered lumens.

The LEDs shall operate over the temperature range of -40 °F to +165 °F.  The LEDs shall be wired in series parallel strings.  The failure of many one LED, and its associated string of LEDs, shall not cause the loss of more than 20% of the light output of the complete LED module.

- 4.	High Tower Luminaire

a.	A 1,000 watt, high pressure sodium lamp that provide 140,000 minimum initial lumens, or as otherwise stated in the Plans.

b.	A side entry 4 bolt mounting bracket designed for 2 inch nominal diameter pipe with provision for leveling the luminaire.

c.	A die cast aluminum housing attached to the mounting bracket that provides a weather tight enclosure for the ballast and terminal block and is readily removable without removing the luminaire from the bracket arm.

d.	A cover and reflector that readily detaches from the mounting bracket without removing the luminaire from the bracket arm.

e.	A double fused 480 volt ballast with fuses sized by the luminaire manufacturer.

f.	A hinged lens compatible with add on light shields.

g.	A stainless steel lamp clamp to prevent lamps from loosening, which is separate from the socket.

When the Plans specify shielding areas from illumination, install light shields on luminaires on hightower poles whose templates touch the shielded areas. Provide shields that limit light levels to 0.1 foot-candle or less at the right of way line. Whenever stock shields fail to limit light levels to the 0.1 foot-candle level, hire the luminaire manufacturer to custom design, and fabricate shields.  If the first generation of custom fabricated shields fails to limit light levels to the 0.1 foot-candle level, the Engineer may waive the 0.1 foot-candle requirement.

- 5.	Lenses

When polycarbonate resin lenses are specified, the fabricator shall furnish certified lenses conforming to the following criteria:

a.	The lenses are molded in a single piece from virgin polycarbonate resin.

b.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

c.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

d.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

e.	The resins used meet the requirements for the self extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by 1/2 inch bar molded according to ASTM recommended practice.

740-2.19 SIGN LIGHTING FIXTURES.

1.	Incandescent Down Light. Provide the type of sign lighting fixture, with incandescent lamp, shown on the Plans or as specified in the Special Provisions.

- Hood. Cadmium plated, finished with aluminum paint, and side outlet tapped for conduit.

- Reflector. Symmetrical 8-inch steel. Porcelain enameled green finish on the outside and white on the inside.

- Lamp. Provide 2,900 lumen.

2.	Mercury Vapor. Fully enclosed, rain-tight, dust-tight, and corrosion-resistant. Design each fixture for mounting at the bottom of the sign on an overhead sign structure as shown on the Plans. Painting of fixture is not required.

- Housing. Cast aluminum alloy or other non-corrosive material conforming to the Plans. Finish all housings in a workmanlike manner with no exposed burrs or sharp edges.

- Refractor. Glass having inner prisms with a smooth exposed face. Mount the refractor in a door frame assembly which is hinged to the body of the fixture and fastened with an automatic type latch.

- Gaskets. Made of a material capable of withstanding the temperatures involved, and securely held in place.

- Light Distribution. Light distribution over the sign face must conform to the isolux distribution patterns shown in the Plans. Accomplish light distribution entirely by refraction through the lens with no additional refractors or reflectors.

- Miscellaneous. All ballasts, lampholders, lamps, terminal blocks, and necessary fuses must conform to applicable requirements of Subsection 740-2.21 or to the Plans.

- Lamps. Color-improved to provide good color rendition of signs.

740-2.20 This subsection left intentionally blank.

740-2.21 BALLASTS. Include ballasts for high intensity discharge lamps as an integral part of each luminaire and design for the voltages and lamp types specified in the Plans or Special Provisions. Ensure that the current needed to start the lamps is less than the operating current.

Furnish regulator-type ballasts with copper windings electrically isolated from each other, which will start and operate the lamps in temperatures down to -40 °F. The allowable line voltage variation is plus and minus 10%.

Equip high-pressure sodium luminaires, except those with 1000 watt lamps, with magnetic regulator ballasts with the following additional operating characteristics:

- The lamp wattage regulation spread at any time over the life of the lamp must not exceed 18% of nominal lamp watts at plus and minus 10% line voltage variations.

- With nominal line and lamp voltages, the ballast must regulate the lamp output to within 5% of the ballast design center, and sustain lamp operation with a minimum 60% voltage drop lasting 4 seconds or less.

Equip luminaires with 1000 watt high pressure sodium lamps with auto-regulator ballasts that provide a maximum 30% lamp regulation spread, a minimum 35% voltage dip tolerance, and with nominal line and lamp voltages regulate lamp output to within 5% of the ballast design center.

Furnish ballasts, for soffit luminaires, with mounting brackets attached and equip with terminal blocks for primary connections and lamp socket preconnected to the secondary for flush mounted luminaires and with terminal blocks for both primary and secondary connections for use with suspended luminaires.

- Submit the ballast manufacturer’s specification sheets for review and approval.

740-2.22 HIGH TOWER LUMINAIRE LOWERING SYSTEM. Furnish an integral luminaire lowering device that is compatible with the high tower design and consists of a head frame assembly, luminaire ring assembly, and winch assembly complete with electric motor.

Provide a technician employed by the lowering device manufacturer, who has a minimum three years experience installing the lowering device, to

1.	Teach each crew that assembles the lowering device how to complete the work on the first pole,

2.	Oversee the assembly work on the next three poles or until the technician can assure the Engineer the crew can correctly assemble the lowering devices,

3.	Teach each crew how to initially adjust each lowering device on the first pole installed,

4.	Oversee the adjustment work on the next three installed poles or until the technician can assure the Engineer the crew can correctly adjust the lowering devices,

5.	Come back to teach each new crew how to assemble and adjust the lowering system components, if the installation crews change, and

6.	Make intermediate and final adjustments to all lowering devices installed under the contract at three, six, and twelve month intervals after the State has accepted the high tower poles.

Furnish a complete service manual with instructions on installation, operation, and maintenance for each lowering device, winch assembly, and power drive system furnished on the project.

Install one of the following high mast lowering devices wired for a single circuit, rated 480 VAC single phase, on each high tower pole shown on the Plans. Furnish all power cords with four #8 AWG conductors.

Furnish each luminaire ring assembly with guide cones (Millerbernd) or tapered positioning pins (Eagle) painted a safety orange color for their full length. Use a 2 component, waterborne epoxy paint with gloss finish that can be applied to galvanized steel and provides a tough, abrasion resistant coating rated for exterior use. Complete work according to the paint manufacturer’s written instructions, including: preparing the surfaces and tinting, mixing, and applying the paint.

| Manufacturer | Model No. | Options to be Furnished |
| --- | --- | --- |
| Millerbernd Manufacturing | SSLD-2 | Integral winch and motor assembly |
| Stratus | 2070 | Centering Ring Per Stratus Drawing 50193, 1/4" Stainless Steel Cables and lighting Rod. |

- High Tower luminaire lowering systems shall meet third party certification.

The Plans will indicate the number of luminaires on each pole, each pole’s height, and whether FAA approved obstruction lights are required.

The Plans will indicate the number of luminaires on each pole, each pole’s height, and whether FAA approved obstruction lights are required.

740-2.23 UNDERPASS LIGHTING SYSTEM. Use underpass luminaires that have vandal-resistant surface-mounted fixtures installed in a galvanized welded steel enclosure as detailed on the Plans. The lamp must be a mogul based 150-watt, clear, ANSI/NEMA C78.1355, horizontal mount, high pressure sodium type. The lamp must provide a minimum of 15,000 initial lumens with a rated life of 24,000+ hours based on a minimum burn period of 3 hours.

Mount the ballast within the body of the fixture with a constant wattage autoregulator CWA type meeting ANSI/NEMA C78.1355 operating characteristics. See Plans for input voltage.

Provide a square lens that is semi-recessed, extra thick, injection molded polycarbonate prismatic type, with internal specular aluminum reflector. The lens must provide the uniformity specified in the Plans or Specifications with a minimum spacing to mounting height ratio (S/MH) of 3.5:1, in the plane defined by the axis of the lamp, and a minimum S/MH ratio of 1:1 in the plane passing vertically through the length of the lamp axis.

Provide a lens frame and side housing made of ASTM B 209, alloy 6061-T6 tempered aluminum a minimum of 0.177 inch thick, or equivalent stainless steel, secured with tamper proof screws requiring a special manufacturer’s tool to remove.

Provide fixtures that are Third Party listed for wet, damp, and dry locations. Fasten the fixture into the mounting enclosure with stainless steel screws accessible only from within the fixture housing.

Fabricate the mounting enclosure from 0.138 inch thick mild steel with continuous welded seams and hot-dipped galvanized, as detailed on the Plans. Use wiring within the enclosure that might come in contact with the ballast rated at 390 F [type SR-2]. Provide a grounding screw or lug within the enclosure for a maximum No. 8 AWG ground conductor.

Submit the manufacture’s fixture specifications, photometric data, and a computer-generated lighting layout for approval prior to ordering. Calculate, by the point-to-point method, the light level on the walkway surface through the underpass with no wall, ceiling, or walkway reflectances. The calculated light level on the walking surface and the calculated average-to-minimum uniformity ratio may not be worse than the light level and uniformity ratio noted on the drawings. Center the calculation area on the light fixtures and base it on the width of the walkway less 12 inches, and the length of the walkway equal to the distance between the first and last fixtures plus a distance equal to 50% of the spacing between the fixtures added to each end of the walkway. You may substitute fixtures having similar construction, electrical, and light distribution characteristics, if approved. In the case of a substitution, construct the enclosure shown on the drawing to match the mounting requirements of the submitted fixture. Submit shop drawings for the enclosure for approval along with the fixture shop drawings.

## SECTION 743

## FUEL TANK

743-1.01 DESCRIPTION. This item consists of furnishing and installing a protected aboveground motor vehicle fuel or heating oil tank complete with fuel and accessories as specified. Prepare for Department use, an Environmental Protection Agency (EPA) approved Spill Prevention, Control and Countermeasure Plan (SPCC plan).

- MATERIALS

743-2.01 TANK. Provide skid-mounted, doublewall, aboveground steel tank. The tank shall be of the type and capacity shown in the bid schedule. Equip tank with accessories as shown on the Plans and as follows:

1.	Overfill Alarm. Provide a mechanical, audible overfill alarm, Ventalarm Signal as manufactured by Scully Signal Company, 70 Industrial Way, Wilmington, MA 01887 or approved equal.

2.	Automatic Shut-Off Device. Provide a positive closing, mechanical, automatic shut-off device. Clay & Bailey model F-30 as manufactured by Clay and Bailey Manufacturing Co., 6401 East 40th Street, Kansas City, MO 64129 or approved equal.

3.	Tank-Mounted Mechanical Fuel Gauge. Provide mechanical gauge with 12-hour clock face in feet and inches readout, activated by a stainless steel float connected to a stainless steel cable. Morrison Model 818 as manufactured by Morrison Bros. Co., P.O. Box 238, Dubuque, Iowa 52004 or approved equal.

4.	Openings. Provide the following threaded openings and accessories on tank top:

- One 2-inch Interstitial Monitoring with plug

- One 2-inch Normal Vent with screen

- One 2-inch Product fill opening with locking cap

- One 2-inch Product pump opening with plug

- One 2 to 4-inch Liquid level gauge

- One 4 to 8-inch Emergency vent with plug, primary tank

- One 4 to 8-inch Emergency vent with plug, secondary tank

- No Drain Opening at bottom

5.	Exterior Coating. Abrasive blast the exterior surface of the outer tank according to SSPC-SP 6. Coat the exterior surface with 8 mils total thickness of epoxy paint base and urethane paint finish.

6.	UL Labeling. Heating oil tanks shall be manufactured and labeled according to UL 142. Motor vehicle fuel tanks shall be manufactured and labeled according to UL 142 and UL 2085.

7.	Insulation. For motor vehicle fuel tanks install 3-inch thickness of insulation according to ASTM C-332 and ASTM C-495.

When a motor vehicle fuel-dispensing tank is specified, it shall meet or exceed the requirements of UL 2085, Underwriters Laboratories Standard for Safety for Protected Aboveground Tanks for Flammable and Combustible Liquids. Equip with a threaded opening for the specified fuel pump.

- Tanks larger than 2,500 gallons require additional openings and accessories for UL rating.

743-2.02 MANUAL DISPENSING SYSTEM. Provide a double-action pump, equipped with detachable, self-venting bung adapter, set screws and strainer screen. Provide a dispensing system that is not gravity fed. The pump shall have 16 feet of ¾-inch diameter arctic service fuel hose with shut-off nozzle and deliver a minimum of 20 gallons/100 strokes. The pump supplied shall be a Gasboy, Model 1720, or approved equal.

743-2.03 ELECTRIC DISPENSING SYSTEM. Provide an electric suction or submerged turbine pump with a delivery rate up to 18 gpm, 3-wheel, meter-register with reset and non-resettable 6 digit master totalizer in a cabinet, anti-siphon valve with internal pressure relief, gate valve, canister style fuel filter, flow meter, 20 ft arctic service fuel hose with swivel and breakaway coupling, hose retractor, OPW 11-A automatic nozzle with lockable nozzle holder, explosion proof pump activation switch, emergency pump shutoff switch mounted on the SRE building, warning signs, and BC fire extinguisher per International Fire Code (IFC) chapter 2201 – 2206.

743-2.04 FUEL. No. 1 diesel or No. 1 heating oil, depending on tank use.

- CONSTRUCTION REQUIREMENTS

743-3.01 INSTALLATION. Install according to the International Fire Code (IFC) chapters 22 and 34 for the type of tank specified. Mount and secure the tank on the skid base. Install dispensing system to include all fittings and hose. Install wiring of the pump and emergency shut off according to National Fire Protection Association (NFPA) 30 and the current edition of the National Electrical Code (NEC) for hazardous locations. Place tank at the location shown on the Plans, or as directed. Set automatic shut-off device to 90% capacity. Fill to 90% capacity with specified fuel.

743-3.02 SPILL PREVENTION, CONTROL AND COUNTERMEASURE PLAN (SPCC). Provide for Department use after tank installation, an EPA approved SPCC plan for the motor vehicle fuel or heating oil tank, that is certified by a licensed professional engineer. (See http://www.epa.gov/oilspill/lawsregs.htm for SPCC plan requirements).

Comply with 40 CFR 112 and address the following issues in the SPCC Plan:

1.	Operating procedures that prevent oil spills;

2.	Control measures installed to prevent a spill from reaching navigable waters; and

3.	Countermeasures to contain, clean up, and mitigate the effects of an oil spill.

The Contractor shall coordinate with the Department to identify oil spill response resources. The SPCC Plan shall take into account the Department’s on-site equipment, oil spill containment material, cleanup material, and personnel; and shall make recommendations for future improvements in these areas.

Provide two (2) copies of the SPCC Plan; deliver one to the Engineer to be retained at the site and deliver the other to the Department’s Statewide Safety Officer at 5300 E. Tudor Drive, Anchorage, AK, 99507.

This page intentionally left blank.