- PART 4

- STANDARD MODIFICATIONS

- AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

- STANDARD SPECIFICATIONS

- FOR

- HIGHWAY CONSTRUCTION

2004

ESCROW OF PROPOSAL DOCUMENTATION AFFIDAVIT

THE UNDERSIGNED HEREBY CERTIFIES THAT THE ESCROW OF PROPOSAL DOCUMENTATION CONTAINS ALL OF THE INFORMATION THAT WAS USED TO DEVELOP THE PROPOSAL AND THAT I HAVE PERSONALLY EXAMINED THESE CONTENTS AND THAT THE DOCUMENTATION IS CORRECT AND COMPLETE IN ACCORDANCE WITH SUBSECTION 102-1.17. SUBMITTAL BY THE CONTRACTOR OF A CLAIM, WHICH IS NOT CONSISTENT WITH THE CONTENTS OF THESE PROPOSAL PREPARATION DOCUMENTS, SHALL RESULT IN DENIAL OF THE CLAIM.

By:

Title:

Firm:

Date of Submission:

Project Number:		___

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room, or at the Central Region Materials Laboratory:

- Quantity Computations

- Cross Sections

- Parks Highway MP 39 – 42 Geology Report, Dated January 2004.

- Crusey Street Improvements Hydrologic and Hydraulics Report, Dated March 2006.

e.	State of Alaska Department of Transportation and Public Facilities publication, Alaska Storm Water Pollution Prevention Plan Guide, January 14, 2005.

f.	Standard Specifications for Highway Construction 2004.  ($25.00)

g.	Alaska Test Methods Manual (Lab & Field), 2004 Edition. ($25.00)

2.	The Department has an approved environmental document addressing concerns and environmental commitments and it is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0534.

3.	The Materials Certification List (MCL) has been included in Appendix F.  This list is provided for the Contractor to determine materials that will require submittal to the project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

4.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

5.	Asphalt laydown temperatures may be monitored with a thermal imaging camera.  Unsatisfactory areas will be subject to additional testing and/or replacement at the Contractor’s expense under Division 400.

6.	A new asphalt specification is contained in the special provisions that changes the name of the asphalt concrete pavement to hot mix asphalt.   If the name asphalt concrete pavement appears in the contract, it should be assumed to be hot mix asphalt.

7.	The Department requires all workers within the project limits to wear an outer visible surface or layer of high visibility color and retro reflectivity.  See subsection 643-3.11, High Visibility Clothing for requirements.

8.	Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically, Contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A-336. This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit and airport projects as appropriate.  A 0% DBE participation goal does not relieve the Contractor of the requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, jon_dunham@dot.state.ak.us

9.	Contractors must comply with Administrative Order 226, which establishes a 15% goal for hiring apprentices in certain job categories; on highway, airport, harbor, dam, tunnel, utility or dredging projects awarded by the Alaska Department of Transportation and Public Facilities.  This Administrative Order will apply to all such projects advertised after September 1, 2005, where the project construction cost exceeds 2.5 million dollars.

For additional details, please visit: http://labor.state.ak.us/lss/forms/ApprenHireReq.pdf

10.	Based on guidance from the US Department of Transportation’s General Counsel, effective January 10, 2006 the Alaska Department of Transportation and Public Facilities implemented a Race Neutral Disadvantaged Business Enterprise (DBE) program by setting 0% project goals on all highway, mass transit and airport projects.  All forms and reports required under the existing DBE program will continue to be required under these 0% goal contracts.

Specifically, contractors must continue to report creditable DBE participation/payments on the Monthly Summary of Disadvantaged Business Enterprise Participation Form 25A-336. This will allow the Department to continue to accurately report DBE participation to the Federal Highway Administration, Federal Transit Administration and Federal Aviation Administration.

Contractors must also continue to provide opportunities for DBE firms to participate on highway, mass transit and airport projects as appropriate.  A 0% DBE participation goal does not relieve the contractor of the requirement to provide equal opportunity in subcontracting, supplies or other services offered by DBE firms.

Any questions about this notice may directed to Jon Dunham, Manager of the Civil Rights Office, (907) 269-0850, or email jon_dunham@dot.state.ak.us

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS.  Replace the definitions of SUBGRADE with the following:

SUBGRADE.  The soil or embankment upon which the pavement structure is constructed.

E22 (1/1/06)

Delete text of PLANS and replace with:  The Department’s Contract drawings, profiles, typical cross sections, standard drawings, and supplemental drawings or reproductions showing the location, character, dimensions, and details of the work.

E32(01/27/07)

Add the following definition:  QUALIFIED PRODUCTS LIST. A list of companies and products that the Department has found conforms to the SSHC.  E36(01/27/07)

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

Standard Modification

102-1.04 EXAMINATION OF PLANS, SPECIFICATIONS, SPECIAL PROVISIONS, AND WORK SITE.  Replace the second paragraph with the following:  The records of geotechnical investigations including boring logs, test results, geology data reports, soil reports, material site reports, and geotechnical reports included in a bid package or made accessible to bidders or Contractors, are for information purposes only.  These records are not part of the Contract.  These records indicate subsurface conditions only at specific locations and times, and only to the depths penetrated.  They do not necessarily reflect variations in soil, rock, or groundwater conditions that may exist between or outside such locations.  Actual conditions may differ from what is shown in the records.  Material Sources referenced in these records may not contain materials of sufficient quantity or quality to meet project requirements.  The accessibility of these records does not constitute approval, nor guarantee suitability of soils or sources, or the rights to use sources for this project, except as specifically provided in subsections 106-1.02.4.b Mandatory Sources and 106-1.02.4.c Designated Sources.  The records shall not substitute for independent investigation, interpretation, or judgment of the bidder or Contractor.  The Department is not responsible for any interpretation or conclusion drawn from its records by the bidder or Contractor.

Bidders and Contractors shall examine subsection 106-1.02 Material Sources for further information about material source development. E23 (1/1/06)

Standard Modification

102-1.05 PREPARATION OF BID.  Modify the second sentence in the third paragraph, after: “If a bidder is a corporation, the bid must be signed by a corporate officer,” add: or agent.

E18 (6/30/04)

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Special Provisions

Add the following subsection:

103-1.11 ESCROW OF BID DOCUMENTATION.  Furnish a legible copy of the Bid documentation and an affidavit, as instructed in writing by the Contracting Officer.  Bid documentation consists of written documentation of quantity takeoffs, construction schedules on which the bid is based, cost estimates, rates of production and progress, assumptions, calculations, quotes from subcontractors and suppliers, and information used to prepare the Bid for this project.

Obtain and furnish the same level of bid documentation, for each subcontractor, supplier or fabricator with a subcontract or agreement exceeding $200,000, regardless of tier.  Seal each entity’s documentation in separate envelopes, labeled with the entity’s name and address, submission date, and project name and number.  Include a cover letter or quote signed by a responsible party.

Meet the following requirements:

1.	Submitting Bid Documentation.  Place bid documentation in a sealed container clearly marked “Bid Documentation” and labeled with the bidder’s name and address, submission date, and project name and number.  Deliver the sealed container to the Department designated document depository for safekeeping.

2.	Affidavit.  Submit directly to the Contracting Officer a signed and certified affidavit attesting that

- the affiant has examined the bid documentation and that it includes all documents used to prepare the bid,

b.	the sealed container contains all bid documentation submitted,

c.	the escrow materials were relied on to prepare the bid, and

d.	should a dispute arise, the Contractor’s rights to use bid preparation documentation other than those in escrow are waived.

3.	Access and Use of Escrow Documents. The bid documentation will remain in escrow, without access by either party, except as otherwise provided herein.  In the event the Contractor (1) provides notice of intent to claim, (2) a claim, (3) a contract change order, or (4) initiates contract related litigation, the Department may obtain copies of the bid documentation as provided herein.

Both parties will submit to the Depository and copy to each other a list of personnel that are authorized to access the escrow documents.  Use forms provided by the Depository.

Upon request the Depository will set the time and place for access to escrow documents, will monitor the escrow documents review, and will arrange for a method of copying escrow documents.  Access to escrow documents shall require at least 5 days advance written notice so that the other party has the opportunity to witness the escrow review, examination and use.  There is no requirement that both parties witness the escrow document review, but if one party is absent then the review must occur in the presence of a neutral third party observer to be designated by the Depository.

Notwithstanding paragraph five below, the Department will be allowed: to make copies of escrow documentation (whether hard copy, electronic, or otherwise); to use and review copies consultants directly involved in the subject dispute.

Distribution is not authorized except as related to resolution of a dispute.  The Department will be allowed to incorporate pertinent copies as supporting documentation in significant contract change orders, contractual disputes, and the settlement of disputed claims.

The Department is not liable for any Contractor costs associated with escrow review and use.

4.	Failure to Provide Bid Documentation.  Refusal or failure to provide bid documentation or affidavit renders the bid nonresponsive.  Failure or refusal to provide subcontractor bid documentation will result in subcontract disapproval.

5.	Confidentiality of Bid Documentation.  Materials held in escrow are the Contractor’s property.  Except as otherwise provided herein, the escrow materials cannot be released without the Contractor’s approval.

6.	Cost and Escrow Instruction.  The Department pays to store escrowed materials and instructs the depository regarding escrow.

7.	Payment.  Include within the overall Contract bid price costs to comply with this subsection.

8.	Return of Escrow Documentation.  The original escrow documents will be returned to the Contractor once litigation is concluded, outstanding claims are resolved, the Contractor has completed the Contract, and the Department receives an executed Contractor’s Release (Form 25D-117) with no exceptions listed.

ES11(1/01/06)

SECTION 105

# CONTROL OF WORK

Standard Modification

105-1.02 PLANS AND WORKING DRAWINGS.  In the third paragraph delete: “(24”x36”)” and replace with: (22”x34”)

105-1.03 CONFORMITY WITH PLANS AND SPECIFICATIONS.  In the first sentence of the first paragraph after: “Work performed and materials furnished shall conform to the Plans and Specifications” add: and approved Working Drawings,

In the first sentence of the second paragraph after: “Work or material not conforming to the Plans and Specifications” add: and approved Working Drawings,  E33(01/27/07)

Special Provisions

105-1.06 COOPERATION WITH UTILITIES.  Add the following:  Request locates from all the utilities having facilities in the area.  Use the Alaska Digline, Inc. Locate Call Center for the following utilities:

ALASKA DIGLINE, INC. Anchorage: 907-278-3121 Statewide: 800-478-3121 who will notify the following:

Alaska Railroad Corp City of Wasilla DOT Street Lights, State of Alaska ENSTAR Natural Gas Matanuska Electric Association Matanuska Telephone Association General Communications Inc. (GCI)

Call the following utilities and agencies directly:

DOT/PF Maintenance and Operations……………………………………..	338-1475

Contact the Central Region Maintenance & Operations Office at (907) 269-0760 to obtain the appropriate District Superintendent’s phone number for this project.

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the Plans and the following utility specific coordination.  The Contractor shall bear the expense for changes or additional relocation requested for the Contractor’s convenience.

Work around utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right-of-Way and/or Construction surveying is required before utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is  required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right-of-Way staking required by the utility is either in advance of the two (2) week work Plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin, provide a copy of the notice to the Project Engineer.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work before beginning work with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Before any of the relocations listed below, the identified areas will be slope staked, along with pipe locations and grading information.  During relocation work, provide all required traffic control and flagging for the Utilities, this work will be paid under the applicable 643 items.

Specific coordination requirements for the specific utilities impacted by the Parks Hwy MP 42.1 – MP 44 Rehabilitation:  Crusey Street to Lucus Road and Lucille Street at Fred Nelson Avenue Safety Improvements are included below for the:

The City Of Wasilla (C.O.W.) (907) 373-9010 has existing water valves, sanitary sewer and storm drain manholes located within the project limits that as a part of this project will require adjustment.  The State of Alaska (S.O.A.) also owns storm drain manholes within the project limits that as a part of this project will require adjustment. It shall be the Contractor responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction.

Before the beginning of work by the Contractor, C.O.W. and the S.O.A. shall check and correct all deficiencies that may exist in any C.O.W. facilities.  The Engineer, Contractor, C.O.W. and the S.O.A. representatives shall witness the condition and location of each C.O.W. and S.O.A. facility.  Failure to participate in this inspection shall result in the Contractor forfeiting all right to claim that the C.O.W. or S.O.A. facilities were damaged before his beginning of work.

Notice that the Contractor is ready for the above walk through inspection shall be given to C.O.W. and the S.O.A. field services section in writing, a minimum of two calendar days before staring construction.  To obtain a point of contact as well as determine where to send the written notice to, contact C.O.W. by calling 373-9010 and the S.O.A. by calling 745-2159.  The Contractor shall furnish a copy of the written notice to the Engineer.

If at any time after the pre-construction inspection C.O.W. or the S.O.A. finds any of their facilities damaged or rendered inoperable by the Contractor, the Contractor shall repair the damage at his expense.

The Contractor shall be responsible for the furnishing of traffic control and personal to assist C.O.W. and S.O.A. while locating and performing the post and pre-construction inspections.  The Contractor shall schedule the final field review with C.O.W., S.O.A. and Engineer upon completion of the valve box adjustments.

Enstar Natural Gas Company (ENSTAR), ENSTAR owns and operates existing transmission and distribution natural gas mains at various locations throughout the project area.  ENSTAR’s existing four (4) inch plastic gas line that parallels the east side of Lucille Street may require adjustment to avoid conflict with the proposed signal bases at the Nelson Road and Lucille Street Intersection. The proposed signal locations will require staking. Once the bases have been staked the Project Engineer, the Departments Utility Inspector and ENSTAR will make a joint determination of the conflict. If a conflict exists the line will be adjusted or relocated to avoid the conflict. Allow ENSTAR four (4) calendar days to complete the adjustment or relocation required.

A copy of Enstar’s Safety Requirements for Excavation Adjacent to Natural Gas Pipelines is included in Appendix E to the Special Provisions to familiarize Contractors with safe excavation methods while working close to gas pipelines.

Matanuska Telephone Association (MTA). MTA owns and operates existing overhead and underground telecommunications facilities at various locations throughout the project area. MTA’s existing fiber optic that parallels the east side of Lucille Street may require adjustment to avoid conflict with the proposed signal bases at the Nelson Road and Lucille Street Intersection. The proposed signal locations will require staking. Once the bases have been staked the Project Engineer, the Departments Utility Inspector and MTA will make a joint determination of the conflict. If a conflict exists the line will be adjusted or relocated to avoid the conflict. Allow MTA five (5) calendar days to complete the adjustments or relocation required.

Matanuska Electric Association (MEA), MEA owns and operates existing overhead and underground electrical distribution facilities at various locations throughout the project area. MEA will be supplying service to the proposed load centers for the project. Once the new load centers have been installed, inspected and green tagged for service MEA will be notified and work will be scheduled by MEA. Before installation of the service extension for Load Center C, located at the NW quadrant of the Parks Highway and Lucille Street the concrete sidewalk will be removed along Lucille Streets west side to the serving pole to the north.

Specific coordination requirements for the specific utilities impacted by the Crusey Street Improvements Project are included below:

ENSTAR Natural Gas Company (ENSTAR) owns and operates existing underground transmission and distribution natural gas mains at various locations throughout the project area that will require relocation and/or adjustment.  Notify ENSTAR by calling 907-264-3712 to establish a point of contact and to determine where to send the written notice. The following existing facilities have been identified as potential conflicts:

- At Station 11+15, RT:  the existing 2” plastic gas line crossing may require adjustment horizontally and/or vertically to avoid conflict with the proposed storm drain pipe.  Coordinate with ENSTAR to expose the facilities before the storm drain pipe installation.  Allowed ENSTAR three (3) calendar days to complete the adjustment.

- At Station 14+00, LT:  the existing 2” plastic gas line may require adjustment to avoid conflict with the proposed storm drain pipe.  Coordinate with ENSTAR to expose the facilities before the storm drain pipe installation.  Allowed ENSTAR three (3) calendar days to complete the adjustment.

- At Station 17+10:  the existing 2” plastic gas line crossing of Crusey Street will require relocation or adjustment to avoid conflict with the proposed storm drain pipe and/or rigid insulation.  Coordinate with ENSTAR to expose the facilities before the storm drain pipe installation.  The 2” gas line will be adjusted to avoid the conflict, if adjustment is not possible, ENSTAR will abandon the existing 2” plastic line in-place and bore a new 2” plastic line to an extra depth to avoid the storm drain pipe.  Allowed ENSTAR five (5) calendar days to complete the relocation.

- At Station 20+45:  the existing 2” plastic gas line crossing of Crusey Street will require relocation to avoid conflict with the proposed storm drain pipe.  Coordinate with ENSTAR to expose the facilities before the storm drain pipe installation.  After the installation of the storm drain pipe, allow ENSTAR to install the 2” plastic gas line crossing over the pipe.  Allow ENSTAR five (5) calendar days to complete the adjustment and/or relocation.

- At Station 20+55, RT:  the 2” plastic gas line may require adjustment to avoid conflict with the proposed Special Ditch and/or storm drain inlet.  Stake the Special Ditch and storm drain inlet.  Coordinate with ENSTAR to pothole the facilities to determine the extent of the conflict.  Allow ENSTAR two (2) calendar days to complete the adjustment.

- At Station 27+50, LT:  the 2” plastic gas line will require relocation to avoid conflict with the proposed storm drain pipe & sidewalk excavation.  From Station 26+50 LT to 28+40 LT, the 2”PL gas line will be abandoned in place.  The new 2” plastic line will be installed 25ft to the west of the existing line.  The new 2” gas line will tie into the 6” main at Station 28+40 LT and connect with the existing 2” plastic line at Station 26+50 LT on Crusey St.  Coordinate with ENSTAR to expose the facility before the storm drain inlet installation and sidewalk excavation.  Allow ENSTAR five (5) calendar days to complete the relocation.

- Crusey St:  at Station 28+40, the 6” plastic gas line will require relocation to avoid conflict with the proposed storm drain pipe, signal pole foundation and/or roadway excavation.  Along the north side of Bogard Rd, from Station 121+50 LT to Station 124+50 LT, the 6” plastic line shall be abandoned in place and the new 6” plastic shall be installed approximately 35ft to the north.  The new 6” plastic line will splice into the existing 6” line at Station 121+50 LT & Station 124+50 LT.  Coordinate with ENSTAR to expose the facility before the storm drain pipe and signal pole foundation installation and roadway excavation.  ENSTAR shall be allowed five (5) calendar days to complete the relocation.

A copy of Enstar’s Safety Requirements for Excavation Adjacent to Natural Gas Pipelines is included in Appendix E to the Special Provisions to familiarize Contractors with safe excavation methods while working close to gas pipelines.

General Communication Inc. (GCI) has existing underground facilities located within this project that will require adjustment.  Notify GCI by calling 907-229-9176 to establish a point of contact and to determine where to send the written notice. The following existing facilities have been identified as potential conflict.

- The .750 coax cable along the north side of Bogard Rd will require relocation to avoid conflict with the proposed approach to the school and storm drain pipes.  GCI will install two (2) new pedestals, one at Station121+25 LT & one at Station 124+75 LT.  GCI will trench new .750 coax cable between the pedestals and splice the new and existing cable together in each pedestal.  From Station 28+60 RT to Station 30+00 LT, the .500 coax cable that services Wasilla High School will require relocation to avoid conflict with the proposed roadway excavation.  The existing .500 coax cable will be abandoned in place and a new .500 coax cable will be installed from the pedestal (Station 28+60 RT) to Wasilla High School.  Allow GCI six (6) calendar days to complete the relocation.

- GCI has two (2) fiber optic cables and spare ducts that run along the north side of Bogard Rd that will require relocation to avoid conflict with the proposed approach  to the school and storm drain pipes.  The F/O cables and ducts will be lowered in place from Station 119+50 LT to Station 126+50 LT along Bogard Rd.  Allow GCI seven (7) calendar days to complete the relocation.

Matanuska Electric Association, Inc (MEA).  MEA owns and operates existing aerial and underground electrical distribution facilities located within the project area that will require adjustment.  Notify MEA by calling 907-761-9283 to establish a point of contact and to determine where to send the written notice.  The following existing facilities have been identified as potential conflicts:

From Station 25+00 LT to Station 28+60 RT, the existing 3-phase aerial conductors at the Crusey St & Bogard Rd intersection will require relocation.

- MEA will install new poles, down guys and anchors at Station 26+30, 45LT (WE19A-1A) and 26+70, 90 LT (WE19A-1).  New conductors will be installed from existing Pole WE19 (Bogard Rd Station 120+45, 50 LT) to the two (2) new poles and then south to Pole WE19A-2(Station 25+05, 45 LT).

MEA will retire the existing intersection crossing from Pole WE19 to WE19A-1.  MEA will also retire the existing Pole WE19A-1(Station 27+25, 50 LT).  Allow MEA six (6) calendar days to complete the relocation and retirement.

- A section of the underground electrical service to Wasilla High School (WHS) is in conflict with the Crusey St extension and will require relocation.  From Pole WE20 to Station 29+75, 40ft LT, the existing electrical service to WHS will be abandoned in place.  A new J-Box(WE20-AU) will be installed at Station 29+75, 40ft LT.  A 4” conduit  and cable will be installed from Pole WE20 to J-Box WE20-AU.  The existing and new cable will be spliced together at J-Box WE20-AU to complete the electrical service to WHS.  Allow MEA four (4) calendar days to complete the relocation.

- MEA will replace the aerial transformer at Pole WE19A-4 (Station 20+65 LT).  MEA will install conduit and cable from Pole WE19A-4 to Load Center A, at Station 26+70 LT.  MEA will install an aerial transformer at Pole WE19A, install conduit and cable from the pole to the relocated Load Center B at Station 28+45, RT.  Allow MEA four (4) calendar days to complete the relocation.

Matanuska Telephone Association Inc. (MTA).  MTA owns and operates existing overhead and underground telecommunications facilities at various locations throughout the project area that will require adjustment.  Notify MTA by calling 907-761-2544 to establish a point of contact and to determine where to send the written notice. The following existing facilities have been identified as potential conflict:

- A new fiber optic handhole will be installed at Station 28+60, 60ft RT.  A 2” conduit will be buried from the existing fiber optic handhole at Station 28+40, 10ft LT, to the new F/O handhole at Station 28+60, 60ft RT.  A new innerduct with fiber optic cable (BFO) will be buried from the new F/O handhole to Wasilla High School.  At Station 30+00, a 4” conduit will be buried across the roadway for the fiber optic and telephone cable crossing.  Two (2) fiber optic cables along the north side of Bogard Road will be lowered in place to avoid roadway excavation.  The cables will be lowered in-place from the existing fiber optic hand hole (Station 28+40, 10ft LT) to 100ft east.  The buried fiber optic cable from Station 111+50, 40ft LT to Station 123+40, 40ft LT will be abandoned in place.  The new innerduct with fiber optic cable will be buried from Station 111+50, 50ft LT (handhole XF4002) to Station 123+70, 50ft LT (handhole XF5511).  The new innerduct and cable will be 4ft north of the right-of-way along the north side of Bogard Rd.  Once this work is complete, the existing fiber optic handhole and fiber optic cable service to WHS will be abandon in place.  Allow MTA twenty seven (27) days to complete the relocation and retirement.

- A new buried telephone cable will be installed from pedestal XF5611 to Station 30+00, 60ft LT.  At Station 30+00,60ft LT, the new and existing telephone cable will be spliced together to complete the telephone service to the school.  From pedestal XF5611 to Station 30+00, 60ft LT, the existing cable will be abandoned in place.  Allow MTA four (4) calendar days to complete the work.

- Two (2) existing buried telephone cables will be extended 60ft south, from a splice point at Station 27+35, 65’ LT, to a new pedestal at Station 26+95, 60’ LT.  Allow MTA three (3) calendar days to complete the work.

- A buried telephone cable along the south of Bogard Rd, from Station 118+00, 40ft RT (Bogard Rd) to Station 27+35, 65ft LT (Crusey St), will be abandoned in place.  A new buried telephone cable will be installed from a splice point at Station 118+00, 55ft RT (Bogard Rd) to the new pedestal at Station 26+95, 60ft LT on Crusey St.  The new cable will be 4ft south of the new right-of-way along the south side of Bogard Road.  Allow MTA four (4) days to complete the work.

- Crusey St: From Station 20+75 RT to Station 21+10 RT, the buried telephone cable may require adjustment horizontally and/or vertically to accommodate the installation of the storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  If adjustment of the telephone line is necessary, allow MTA four (4) calendar days to complete the work.

- Crusey St: From Station 19+00 LT to Station 20+75 LT, MTA will relocate two (2) buried telephone cables and one (1) pedestal 5 ft to the west, from underneath the proposed pathway.  Allow MTA four (4) calendar days to complete the work.

- Crusey St: At Station 17+80, 75ft RT, the buried telephone cable may require adjustment horizontally and/or vertically to accommodate the installation of the storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  If adjustment of the telephone cable is necessary, allow MTA two (2) calendar days to complete the work.

- Crusey St: At Station 14+50,50ft LT: MTA will raise an existing manhole.  Allow MTA four (4) calendar days to complete the work.

- Crusey St crossing at Station 14+85:  MTA will install 2 – 4” ridge metal conduits across the roadway.  Coordinate with MTA to install the conduits after the storm drain pipe installation.  After compaction and before paving, MTA will inspect the conduits for damage and make any repairs, if necessary.  Allow MTA three (3) calendar days to complete the work.

- Crusey St: at Station 11+20 RT:  the buried telephone cable may require adjustment horizontally and/or vertically to accommodate the installation of the storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  If adjustment of the telephone cable is necessary, allow MTA two (2) calendar days to complete the work.

- Crusey St: at Station 16+95 RT:  the fiber optic cable may require adjustment horizontally and/or vertically to accommodate the installation of a storm drain pipe/inlet.  Coordinate with MTA to expose the facilities before the storm drain pipe/inlet installation.  If adjustment of the BFO is necessary, allow MTA six  (6) calendar days to complete the work.

- At Station 14+00 LT:  the existing buried telephone cable may require adjustment to avoid conflict with the proposed storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  Allow MTA three (3) calendar days to complete the adjustment.

- At Station 11+25 RT:  the existing buried telephone cable may require adjustment to avoid conflict with the proposed storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  Allow MTA three (3) calendar days to complete the adjustment.

- From Station 10+80 RT to 11+20 RT:  the existing buried telephone cable may require adjustment to avoid conflict with the proposed storm drain pipe.  Coordinate with MTA to expose the facilities before the storm drain pipe installation.  Allow MTA three (3) calendar days to complete the adjustment.

- At Station 6+90, 60ft RT:  the existing pedestal may require adjustment to avoid conflict with road excavation.  Coordinate with MTA to expose the facilities before the road excavation.  Allow MTA three (3) calendar days to complete the adjustment.

- Crusey St: MTA will abandon an existing telephone cable, within the roadway, from Station 14+50 LT to Station 28+50 LT.  Allow MTA one (1) calendar day to complete the work.

105-1.07 COOPERATION BETWEEN CONTRACTORS.  Add the following: The following projects may be under construction concurrently with this project:

| Project | Fed # | Contact | Phone |
| --- | --- | --- | --- |
| Wasilla Fishhook Road | STP-0525(13)/56912 | TNH | 279-0543 |
| Palmer-Wasilla Hwy Intersection Improvements | State Project No. 59981 | ADOT&PF | 569-0589 |
| Mat-Su Pavement Rehabilitation Program 2007 | IM-0525(15)/60008 | ADOT&PF | 269-0450 |

Coordinate traffic control, construction, and material hauling operations with the prime contractor of the above project to minimize impact on the traveling public, and to minimize conflicts with the work being performed under the other contract. (02/01/00)R175M98

Standard Modification

105-1.13 MAINTENANCE DURING CONSTRUCTION.  Add the following at the end of this subsection:  Costs of maintenance work during construction and before the project is accepted as substantially complete shall be subsidiary to the prices bid on the various Contract items, and the Contractor will not be paid an additional amount for such work.

If in the Engineer’s opinion, the Contractor at any time fails to provide adequate maintenance, the Engineer will notify the Contractor of such noncompliance.  The notification will specify the areas or structures for which there is inadequate maintenance, the corrective maintenance required, and the time allowed to complete corrective maintenance.  If the Contractor fails to take the corrective action within the specified time, the Engineer may:

- Suspend the work until corrective maintenance is completed;

- Assess a traffic price adjustment against the Contract Amount when an adjustment rate is specified in the Contract; and

- Employ others for corrective maintenance and deduct the cost from the Contract amount.

E33(01/27/07)

Standard Modification

105-1.16 FINAL ACCEPTANCE AND RECORD RETENTION.  Modify the first paragraph, Item 4., after: “DOLWD” add: and State Department of Revenue. (6/30/04)E19

Special Provisions

105-1.17 CLAIMS.  Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

# SECTION 106

CONTROL OF MATERIAL

## Standard Modification

106-1.01 SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  In fifth paragraph, in two places remove the text: “Approved Products List” and replace with:  Qualified Products List E36(01/27/07)

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision.  Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, before award of the contract.

Steel and iron products that are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater.  For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States.  The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition.  These processes include rolling, extruding, machining, bending, grinding, drilling, etc.  The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), scrap, pig iron, and processed, pelletized and reduced iron ore.  It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework).  Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement.  There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non-steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that manufacturing processes for each covered product comply with this provision.  Non-conforming products shall be replaced at no expense to the State.  Failure to comply may also subject the Contractor to default and/or debarment.  False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020.  (02/07/05)S13

Standard Modification

106-1.02 MATERIAL SOURCES.

1.	a.	General.  Within Item a. delete text and replace with:  Utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in subsection 106-1.02.4.  When there is insufficient useable excavation furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

4.	Type of Sources.  Replace the first paragraph with the following:  The Contractor shall utilize Useable Excavation according to subsection 104-1.04 before using material sources listed in this subsection.  When there is insufficient Useable Excavation, the Contractor shall furnish additional required materials from sources of the Contractor’s choice, except that the Contractor shall use a mandatory source when identified in the Contract.

When there is insufficient Useable Excavation, the Contractor shall supply additional required material from the following sources:

4.	d.	Available Sources.  Replace the second paragraph with the following:  When the Department furnishes copies of existing boring logs, test results, or other data in its possession concerning Available Sources, the Contractor is responsible for determining the accuracy and completeness of this data, for assumptions the Contractor makes based on this data, and for exploring Available Sources to the Contractor’s satisfaction.

4.	e.	Excluded Material Sources.  Replace the paragraph with the following:  Some material sources may not be considered acceptable regardless of location or ownership.  The bid documents may identify some material sources excluded from use.  The Department reserves the right to exclude a material sources or any portion of a material source, at any time after Contract award, that is determined by material testing to be unsuitable for use on the project.  (1/1/06)E24

Standard Modification

Add new subsection 106-1.08:

106-1.08 SUBMITTAL PROCEDURE.  The Contractor shall complete a Submittal Register, and shall submit it to the Engineer on forms provided by the Department.  The intent of the Submittal Register is to provide a blueprint for the smooth flow of specified project documents.  The Contractor shall fill it out sequentially by bid item and allow at least three spaces between bid items.  The Submittal Register shall list working drawings, schedules of work, and other items required to be submitted to the Department by the Contractor including but not limited to: Progress Schedule, anticipated dates of material procurement, Construction Phasing Plan, Traffic Control Plan, Storm Water Pollution Prevention Plan, Quality Control Program, Utility Progress Schedule, Blasting Plan, Mining Plan, annual EEO reports, DBE payment documentation and subcontracts.

The Contractor shall submit materials (product) information to the Engineer for review, as required by the Materials Certification List and the Contract.

The number of copies required for submittals may be included in the specifications for individual bid items.  If the number of copies of a submittal is not otherwise specified, three copies shall be required.  On each sheet submitted to the Department, including working drawings, catalog cuts, manufacturer’s certifications, etc., space shall be provided for Contractor and Department review stamps.

Each copy of each submittal shall include a Submittal Summary sheet.  The Contractor may use forms provided by the Department or a similar form of the Contractor’s choice as approved by the Department.  The Contractor shall sign submittals and submit them to the Engineer.  The Department will review submittals within 30 days after they are received.  The Department will return submittals to the Contractor as either: approved, conditionally approved with the conditions listed, or rejected with the reasons listed.  The Contractor may resubmit a rejected submittal to the Engineer with more information or corrections.  The Department will review resubmittals within 30 days after they are received.

The Contractor shall not order material or use working drawings that have not been approved by the Department.  The Contractor shall be responsible for timely submittals.  Failure by the Department to review submittals within the time given may be the basis for a request for extension of Contract time but not for additional compensation.

Payment for a specific Contract item will not be made until the Department has received the Submittal Register for all items and approved all required submittals for that specific Contract item.

When material invoices, freight bills and mill certificates are submitted, they shall provide sufficient information for the Engineer to identify the date, company and location of invoice (bill, certificate); project name and number where material will be incorporated; manufacturer, product number, quantity and cost. E34(01/27/07)

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES, AND TAXES.  Add the following after the first sentence:  For the purposes of this subsection, the term “permits” will include but not be limited to Memorandum of Agreements (MOA’s) and Temporary Construction Easements (TCE’s).

Add the following:  Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on off project site, is not expected to impact cultural resources.  The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715.  If cultural resources are discovered during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations according to the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of sites outside the project limits or not previously permitted, impacted by the Contractor's operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of permits or clearances received before using sites outside the project limits.  Additionally, provide the Engineer a written statement that permits or clearances have been obtained.  Also provide a written statement to the Engineer listing agencies or offices contacted that responded that no additional action is required.

Add the following:  The Department has received the following permits on Contractor’s behalf:

- Alaska Department of Environmental Conservation (ADEC) Stormwater Review, Letter of Non-Objection, Stormwater Project No. 05-WW-353-021, dated December 29, 2004.

- ADEC Stormwater Plan Review, 06-WW-170-053

- Coastal Consistency determination from DNR, OPMP, ID2006-0450AA

Copies of the permits/clearances are contained in Appendix F.

Provide information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site.  Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.  (05/29/02)R7M98

107-1.07 ARCHAEOLOGICAL OR HISTORICAL DISCOVERIES.  Change the first sentence to the following:  When operations encounters historic or prehistoric artifacts, burials, remains of dwelling sites, paleontological remains, (shell heaps, land or sea mammal bones or tusks, or other items of historical significance), cease operations immediately and notify the Engineer. (05/29/02)R7M98

# 107-1.08 RAILWAY-HIGHWAY PROVISIONS.  Delete this subsection in its entirety and substitute the following:

# 107-1.08 SECTION 1 - DEFINITION OF TERMS

ARRC	Alaska Railroad Corporation, P.O. Box 107500, Anchorage, AK 99510-7500.

ARRC Property	lands owned or withdrawn for the use of the ARRC, including the ARRC's track right-of-way and communications pole line right-of-way.

Chief Engineer	the head of the Engineering Department or Branch of the ARRC, or authorized representative.

Contractor	an agent of the Permittee, including Contractors or subcontractors employed to construct, reconstruct, operate and/or maintain the Facility.  The term "Contractor" shall be synonymous with the term "Permittee" when the Permittee performs the construction, reconstruction, operation, and/or maintenance of the Facility with its personnel.

Facility	improvements, owned by the Permittee, that are to be placed on ARRC property according to written permission of the ARRC and executed by Permittee.

Roadway Worker	employee of a railroad, or of a contractor to a railroad, whose duties include inspection, construction, maintenance, or repair of railroad track, bridges, roadway, signal and communication systems, electric traction systems, roadway facilities, or roadway machinery on or near track or with the potential of fouling a track.

Telecommunications Supervisor  	the person employed by the ARRC as head of its Telecommunications Department or Branch, or authorized representative.

Permittee	the Department of the governmental agency to whom the right to enter upon ARRC Property was given in the form of written permit or contract executed by the ARRC.

Trackwork	work on the line from the top of subgrade to the top of rail, including geotextile, when required.

Track Materials	hardware, excluding signals and controllers, associated with the running of a railroad.

# 107-1.08 SECTION 2 - GENERAL REQUIREMENTS

Construction, reconstruction, operation, and maintenance on ARRC Property shall be performed in compliance with these Standard Specifications for Work on Railroad Property, including revisions thereto.

Failure to comply with these Standard Specifications for Work on Railroad Property shall result in the demand of ARRC to suspend work on ARRC Property.

Experienced personnel shall perform work on or about ARRC Property in a safe and competent manner in keeping with approved ARRC practices, and as specified herein.  ARRC traffic and property shall be protected.

The safety and continuity of the operation of the traffic of ARRC shall be of first importance and shall be protected and safeguarded.  The Contractor and subcontractors shall be required to perform and arrange work accordingly.  Whenever, in the opinion of the Chief Engineer or representatives, the work or its performance may affect or involve the safety of ARRC's facilities and/or operation of its railroad, the method of doing work shall first be submitted by the Contractor to the Chief Engineer for approval, without which it shall not be commenced or prosecuted.  The approval of the Chief Engineer, when given, shall not be considered as a release from responsibility or liability for damage that ARRC may suffer, or for which it may be liable, because of the acts or omissions of the Contractor, its subcontractors or employees.

Whenever, in the opinion of the Chief Engineer, the construction may cause a hazard to the safe operation of ARRC, ARRC may, in its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and other precautions as may be taken shall not relieve the Contractor and subcontractors from liability for the payment of damages caused by their operations.  ARRC shall be the sole judge of the necessity for, and as to the number and classification of employees required. The Contractor shall reimburse ARRC for the cost and expense incurred in providing such employees.

# 107-1.08 SECTION 3 - SAFETY REQUIREMENTS

The safety of personnel, property, rail operations, and the public is of paramount importance in the prosecution of work on ARRC Property.  The Contractor shall comply with Federal, State, and local governmental regulations (e.g. OSHA, NESC, etc.) applicable to the construction, installation, or maintenance of any Facility.  As reinforcement and in furtherance of overall safety measures to be observed by the Contractor (and not by way of limitation), the following special safety rules set forth in this subsection shall be followed while working on ARRC Property.  Further railroad safety information may be obtained from the ARRC Safety Office at 907-265-2440.  Safety information is also available on the ARRC website at www.akrr.com.

ARRC flag protection is required before activity can occur on or near a railroad operating facility such as a track, yard, bridge, or shop building.  For subsidiary work, such as surveying or inspection, an ARRC furnished flagman will provide a safety briefing before beginning work.  For activities involving a disturbance or potential disturbance to the track, track embankment, or railroad facility, ARRC may require the Contractor to submit a specific Railroad Safety Plan before startup.  Projects that involve activities that cross the tracks or are longitudinal to the tracks will require a specific Railroad Safety Plan and a one-hour ARRC provided training course for the Contractor’s project supervisors before the initiation of work on ARRC Property.  Specific information on Railroad Safety Plans may be obtained from the ARRC Safety Office at 907-265-2440.

The Contractor shall arrange for ARRC flag protection when performing work within 20 feet of any track.  Work within 20 feet of the track shall cease when a train passes and the Contractor employees shall maintain a distance of at least 20 feet from the track until the train has safely passed.  (See Section 6.3 for definition of when train is “passing” the work site).  Work that could come within 20 feet of the track will cease when a train passes.  For example, crane or pile driving activities shall stop when trains pass when the maximum boom and suspended load radius can come within 20 feet of the tracks.  Pile driving shall not be done when trains are passing the work site.  Vehicles and other construction equipment shall not be operated or parked closer than 20 feet from any track without ARRC flag protection.  For this Contract, the requirement for ARRC flag protection is reduced to 12 feet provided:

The Contractor must designate a person in charge of safety whenever work occurs within 20 feet of a railroad crossing.  With ARRC assistance, this person must have passed the Railroad Worker Protection (RWP) training module for the Alaska Railroad found at www.contractororientation.com.   No work can occur within 50 feet of a crossing without an RWP trained person on site.

The trained person will brief the work crew daily on subjects related to safety at railroad crossings.  This person will also be in touch daily with ARRC Maintenance personnel regarding train traffic and the location of the Contractor’s work crew.

Whenever work occurs within 50 feet of the tracks, a watchman will be used.  This watchman will:

Be solely dedicated to watching for trains and related duties.

Take up a position on the track side of the employees working on the project.

Will wear and orange hard hat with yellow reflectors and a reflective orange vest.

Ensure that no employees or equipment come closer than 12 feet from the nearest rail at any time.

When a train approaches, immediately notify workers within the area to stop work and move any tools and themselves at least 25 feet from the tracks.  A hand held air horn or similar device will be used for this notification.  If noisy equipment is in use, the watchman must have a positive means of notification to the crew.  Work may resume after the passage of the train.

Failure to provide proper railroad watchman protection to the Contractor’s crew will result in the shutdown of all work within 100’ of the tracks.  Work can only resume when the ARRC provides ARRC Railroad Flag Protection.  To arrange flag protection, the Contractor will establish a purchase order with the ARRC for $70/hour and pay in advance or arrange for bonding.

In the event Contractor will be performing construction or other activities on or within 20 feet of a railroad track, the Contractor shall be responsible for compliance with applicable Federal Railroad Administration’s Roadway Worker Protection (“RWP”) regulations (49 CFR 214, Subpart C) if its employees qualify as “Roadway Workers”.  Under 49 CFR 214, Subpart C, railroad contractors are responsible for the training of their employees on these regulations.  RWP related Work shall be conducted in strict compliance with the RWP safety standards set forth in 49 CFR 214, Subpart C and the Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards before beginning RWP related Work.

In the event Contractor will be performing construction or other activities on a railroad bridge, the provisions of 49 CFR 214 regarding bridge worker safety shall apply.  Bridge related work shall be conducted in strict compliance with the bridge worker safety standards set forth in 49 CFR 214 and the Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards before beginning bridge related work.

# 107-1.08 SECTION 4 - INSURANCE REQUIREMENTS

While performing work on the ARRC Property, the Contractor shall procure and maintain the ARRC Property.  The Contractor shall be covered by the appropriate insurance with the minimum limits as specified in this subsection.

Each policy specified shall be:

(1) 	endorsed to include ARRC as an additional named insured with respect to the performance of the work;

(2) 	endorsed whereby the insurance company will notify ARRC of material change, cancellation, non-renewal or expiration of the insurance policy in writing not less than 30 days before the effective date;

(3) 	endorsed with a waiver of subrogation rights in favor of ARRC; and

(4) 	endorsed with the Alaska Suit Endorsement.

Before beginning work on ARRC Property, the Contractor shall deliver to ARRC certificate(s) of insurance showing evidence of the insurance required from the following:

Alaska Railroad Corporation Minimum Insurance Requirements.

a.	Commercial General Liability insurance with limits not less than 5,000,000/$10,000,000 Combined Single Limit for Bodily Injury and Property Damage, including coverage for Premises and Operations Liability, Products and Completed Operations Liability, Contractual Liability, and Broad Form Property Damage Liability.  Coverage shall not contain any exclusions of Explosion, Collapse, Underground, or Rail Operations.

b.	Automobile Liability insurance on owned, non-owned, hired and rented vehicles with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

c.	Worker's Compensation insurance according to the statutory coverage required by the State of Alaska and, where applicable, insurance in compliance with other statutory obligations, whether State or Federal, pertaining to the compensation of injured employees assigned to the Work, including but not limited to Voluntary Compensation, Federal Longshoremen and Harbor Workers Act, Maritime and the Outer Continental Shelf's Land Act and the Federal Employers Liability Act.

d.	If a part of the work to be performed on ARRC Property is located within 100 feet of a railroad track, then the Contractor shall also obtain Railroad Protective Liability insurance (Alaska Railroad Corporation as named insured) with limits of liability of not less than $1,000,000/$1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.  Railroad Protective Liability Insurance is waived for this project provided only light equipment is used within 30 feet of the tracks.  Light equipment is equipment that does not come closer than 12 feet to the crossing when working, and can easily be moved to 25 feet from the crossing within 10 seconds.

# 107-1.08 SECTION 5 - NOTICE

A pre-construction meeting shall be held with ARRC's Chief Engineer and representatives of the Department, the Contractor, and subcontractors before beginning work on ARRC Property by the Contractor or its subcontractors.  Contact Brandon Frazier at (907) 265-2353 to schedule meeting.  At Department’s request, ARRC representatives will attend a designated time within the Department’s project preconstruction meeting in order to afford Contractor and Department a convenient method of satisfying the foregoing requirement.

The Contractor shall give written notice to the Chief Engineer not less than ten (10) days in advance of beginning construction, reconstruction or major maintenance activity on ARRC Property, in order that arrangements may be made for the protection of ARRC's operations.  This notice shall include a description of the proposed work on ARRC Property, schedule of work, and the names of any Department, Contractor, and/or subcontractor personnel who may also be working on ARRC Property.

107-1.08 SECTION 6 - FLAG PROTECTION AND PROTECTION OF ARRC TRAFFIC.

ARRC flag protection for the temporary road detour will be provided by ARRC AT THE Department’s expense.  For other instances, unless otherwise noted, flag protection will be provided by ARRC AT THE Contractor’s expense.  ARRC flag protection is to ensure the safe movement of trains and other rail traffic shall be done according to the ARRC rules on flagging.  A minimum of 3 business days before notice is require for ARRC to provide flag protection.  Contact Crystal Wilson at (907) 265-2490.

ARRC will, during the progress of the work, utilize as many qualified flag people as in the opinion of the ARRC may be required for the adequate protection of ARRC traffic.  The Contractor shall pay expense for providing flagperson to ARRC.

Arrange with ARRC to keep informed on the time of arrival of trains and stop any operation that might be or cause a hazard to safe passage of the train past the site of the work 10 minutes before the expected arrival of the train until the last car of the train has safely passed, unless otherwise determined by the Railroad flag person onsite, if any.

Track outages will only be approved in exception cases for durations.  Refer to Tracks out of Service.

107-1.08 SECTION 7 - TRAIN DELAYS; ANTICIPATED WORK WINDOWS DURING CONSTRUCTION.

Conduit work on ARRC Property to prevent delays to trains or other train traffic operated by ARRC.  The ARRC will provide a weekly forecast of train traffic and the ARRC flag persons will provide daily updates of anticipated train traffic.

a.	ARRC Track Maintenance Work Window:  Railroad section and summer work crews may need access into the work area to perform routine track maintenance  work and scheduled summer major track replacement work.   The routine track work is performed as necessary for the safe passage of trains.  Railroad on-track equipment also travels through the project as needed.

b.	Train Traffic:  The track through the project is very active.  The approximate number of trains in a 24 hour period is given below as a planning tool for Contractor and cannot be relied upon to assume times are available for track outage.  Contractor must obtain prior approval of any period of track outage from ARRC below.

Summer Season – (May 6 to September 24)  Approximate Daily Trains:  2 to 4 scheduled Passenger Trains; ARRC also charters passenger trains, that may run on any day; Up to 8 Freight Trains, 1 Coal Train and up to 2 Work Trains per day.

Shoulder – (April 1  to May 5 and September 25 to October 28) Approximate Daily Trains:  Up to 2 scheduled passenger trains; ARRC also charters passenger trains, that may run on any day, up to 8 Freight Trains, 2 Work Trains, and 1 Coal Train.

Off Season – Approximate Daily Trains:  Up to 2 scheduled Passenger Trains;  ARRC also charters passenger trains, that may run on any day, up to 6 Freight Trains, 1  Coal Train, and 1 Work or Snow Service Train.

c.	Tracks out of Service (Track Outages):  This work shall be planned so as to minimize track service outages.  The Contractor shall submit to ARRC a closure plan and request the track outage no less than 10 business days before the proposed date.  The plan will describe the work to be accomplished, the equipment, manpower, and other resources required, and the work schedule, specifying dates and times.  Once approved by ARRC, the Contractor shall follow the plan without any variation whatsoever unless a modification is approved by the Chief Engineer.  ARRC reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  The Contractor shall bear all costs and damages that may result from failure to meet the closure schedule, in addition to the train delay charges provided for in the Contract.  No track outages will be granted for this project.

Should the Contractor or subcontractors actions or activities course delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor by ARRC.

Passenger trains each:	$50 per minute of delay, 60 minute minimum charge.

Other rail traffic:	$50 per minute for each delay over 5 minutes, 30 minute minimum charge.

Rail barges, or other connecting carrier vessels:	No charge for delays of one hour or less; $1,000 per hour for each hour or any part of an hour thereafter with a minimum charge of $6,000.

Delay time will be taken from the train sheet in ARRC’s Dispatch Office, Anchorage (907) 265-2421 for delays and train sheet shall be the official document that length of time a train is delayed will be determined.  If another crew is needed to relieve the original crews, the charge shall also apply to the second crews.  If delays cause a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by the train sheet.

107-1.08 SECTION 8 - PROTECTION OF ARRC COMMUNICATION LINES

Work on ARRC Property shall be conducted to protect ARRC's communication facilities from outages resulting directly or indirectly from the Contractor's or its subcontractor's operations.

Should the Contractor or subcontractor's operations cause outages to communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Contractor:

Open wire communication circuits:	$1.00 per minute per circuit

Communication cable:	$1.00 per minute per cable

A minimum charge of $250.00 will be made for each outage plus the total repair costs.  The outage time shall be that as established by ARRC's Test Board, Anchorage.

There shall be no equipment operated or excavation made within 15 feet of ARRC communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Telecommunications Supervisor.

107-1.08 SECTION 9 - ROAD CROSSINGS

Whenever automatic railroad crossing signals are in the work area, these signals must remain in operating condition.  If, because of the Contractor's or subcontractor's activities the signals become inoperable, the crossing shall be continuously flag protected until the signals are again operable.  See subsection 643-3.04 item 4.for flagging specifications.

When regular railroad crossings are used as haul routes inside or outside the work area, flag persons shall be provided by the Contractor for said crossings in all situations at the discretion of the ARRC.

Temporary road crossings may be installed provided the Contractor has acquired from ARRC a temporary road crossing permit for said crossing.  If a requested crossing is not shown on the project plans as approved by ARRC, then it will be at ARRC’s sole discretion whether to allow the crossing.

The temporary road crossing shall be constructed to the length and the standards specified in the temporary road crossing permit.  Protective signs required by ARRC shall be provided and properly maintained by the Contractor.  The temporary road crossing shall be installed under ARRC flag protection according to subsection 643-3.04 item 4.

The flange ways of road crossings used by the Contractor or its subcontractor as haul routes or temporary road crossings shall be kept clean and free of gravel and shall be maintained to the satisfaction of the Chief Engineer.

When a temporary road crossing is in use, ARRC flag protection shall be provided.  See subsection 643-3.04 item 4.

When a temporary or private road crossing is not in use, the Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

When not in use during the winter season, the temporary road crossing shall be removed.  Upon completion of the work or termination of the crossing permit, the temporary crossing shall be removed and the area restored to its original condition.

The Contractor agrees that others using the private road crossing, except ARRC and its employees, shall be considered agents of the Contractor.

Sight Triangles at road crossings shall be maintained by Contractor free of vegetation and other obstructions to vision according to the table entitled "Sight Triangle Distance" attached and as otherwise established and revised from time to time by ARRC.

Temporary public road crossings must be included in a traffic control plan submitted by the Contractor to the Department for review and approval before constructing the crossing.

107-1.08 SECTION 10 - POWER AND COMMUNICATION LINES

Power and communication lines shall be designed and constructed according to the current edition of the National Electric Safety Code (NESC).

Underground power and communication lines shall be installed in according to this subsection.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

The minimum clearance above the top of rail of ARRC track shall be done according to the American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications, plus 6” to allow for future grade raises.

The minimum clearance above ARRC communication lines shall be done according to the American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications.

Additional lines may not be added, or the characteristics of the line(s) changed without the prior written approval of ARRC's Chief Engineer.

Wires shall be strung across ARRC tracks only when ARRC flag protection is provided in accordance with subsection 643-3.04 Item 4.

No wires shall be strung across ARRC's communications lines without first receiving prior written approval from ARRC's Telecommunication Supervisor, and such work must be accomplished only at a time and in a manner prescribed by said Telecommunication Supervisor.

107-1.08 SECTION 11 - UNDERGROUND UTILITIES

Underground utilities, including culverts, pipelines, and underground power and communication lines, on ARRC Property shall conform to the current American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications.

Unless the Chief Engineer authorizes another method in advance and in writing, underground utilities shall be installed under tracks and roads by boring, jacking, or tunneling.

Boring, jacking, or tunneling shall be done under ARRC tracks only when ARRC flag protection is provided in according to subsection 643-3.04 item 4.

The proposed plan for boring, jacking, or tunneling shall be approved by the Chief Engineer before beginning the operation.

Boring, jacking, or tunneling headings shall be continuously protected against loss of ground material by shoring and/or cribbing as necessary.

107-1.08 SECTION 12 - OPEN TRENCHING

Only when authorized in advance and in writing by ARRC shall a portion of the track be removed to allow trenching for installation of the Facility.

If allowed to open trench, the track may be removed from service only at the time authorized by the Chief Engineer and shall be restored to service within the time period specified by the Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in according to subsection 643-3.06, whichever is greater, and shall be collected from the Contractor.

Track work shall be accomplished by qualified track persons.

Only that portion of the track structure necessary to excavate, stockpile, and install the Facility shall be removed.  Track material removed shall be handled, stockpiled, and relayed in a manner to avoid damage.  Material that is damaged shall be replaced by the Contractor at the Contractor’s expense.

The backfill of the trench under the track and in the road bed prism shall be of the same type of material as taken out, except the top 2 feet shall be clean pit run gravel.  Backfilling and compaction shall be in one foot lifts with a compaction of 95% of maximum density in the area affecting the road bed prism.

The ballast used in replacing the track shall be equal in depth and quality as that which was removed.  The track shall be relayed and brought to original grade in according to standard ARRC practices.  The track shall be resurfaced as often as necessary for a period of 12 months after completion of construction to remove any settlement that may have occurred.

107-1.08 SECTION 13 - EXCAVATIONS

Unless authorized in advance and in writing by ARRC, the top of excavation shall not be within 20 feet of the centerline of tracks, nor shall any excavation exceed 10 feet in depth regardless of its proximity to track.

No water shall be allowed to stand in open excavations in the track area.

Bridging and shoring shall be adequate to safely carry ARRC traffic and the decision of the Chief Engineer pertaining to it shall be final.

Flags, flares, barricades, or watchpersons, as directed by ARRC, shall continuously protect open excavations.

No excavation shall be left open more than three days, unless authorized by the Chief Engineer.

ARRC embankments and cut slopes shall not be disturbed more than necessary to accommodate the construction and shall be left in a stabilized condition.

ARRC ditches, culverts, and roadways shall be kept clean and free of rock, gravel, construction debris, and equipment at all times.

107-1.08 SECTION 14 - ARRC INSPECTIONS

ARRC may furnish an inspector during the periods of construction on ARRC Property.  The ARRC inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The ARRC inspector will work directly with the representatives of the Department and Contractor and the decision of the ARRC inspector in matters pertaining to ARRC operations and safety shall be final.  In the event more than one shift is worked, an ARRC inspector will be required for each shift.  Presence or absence of an ARRC inspector shall not relieve the Contractor of liability for damage done to property of ARRC, or the property of ARRC lessees or permittees having installations on ARRC Property.  ARRC cost and expense for furnishing said inspector(s) shall be collected from the Contractor.

107-1.08 SECTION 15 - USE OF EXPLOSIVES

The use of explosives shall be done in compliance with applicable Federal, State and local laws and ordinances.

No blasting will be permitted unless the Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, ARRC flag protection in according to subsection 643-3.04 item 4 shall be provided on each side of the blast area by the Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

107-1.08 SECTION 16 - SNOW REMOVAL

Snow removal operations shall be conducted in such a manner as to not place snow

(1)	upon the tracks of ARRC;

(2)	where it interferes with the normal operation of the automatic crossing signals; or

(3) 	where it impairs the visibility of either highway or rail traffic at the crossing.

Snow removal operations shall be conducted in accordance with 107-1.08-SAFETY REQUIREMENTS.

107-1.08 SECTION 17 - CLEAN-UP

Work and activities on ARRC Property shall be accomplished to keep the ARRC Property in a neat, orderly, and safe condition satisfactory to ARRC.

Upon completion of the Contractor’s work, equipment and unused materials shall be removed and the ARRC Property shall be left in a neat and clean condition satisfactory to ARRC.

Should the Contractor or its subcontractor fail to comply, ARRC may perform the required clean-up.  ARRC costs and expenses for performing this work shall be collected from the Contractor.  (07/20/04)R268

Standard Modification

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  Add the following paragraphs:

7.	Restoring Areas.  Areas used by the Contractor, including haul routes, shall be restored to their original condition after the Contractor’s operations are completed.  The original condition of an area shall be determined as follows:  Before commencement of operations, the Engineer and the Contractor shall inspect each area and haul route that will be used by the Contractor and take photographs to document their condition.  After construction operations are completed, the condition of each area and haul route will be compared to the earlier photographs.  Prior to demobilization the Contractor shall repair damages attributed to its operations.  The Contractor agrees that all costs associated with repairs shall be subsidiary to other items of work and will not be paid for directly.

8.	Material Disposal Sites.  Offsite disposal areas may be at locations of the Contractor’s choice, provided the Contractor obtains from the owner of such land written permission for such dumping and a waiver of all claims against the State for any damage to such land which may result therefrom, together with all permits required buy law for such dumping.  A copy of such permission, waiver of claims, and permits shall be filed with the Engineer before commencing work on private property.  The Contractor’s selected disposal sites shall also be inspected and approved by the Engineer before use of the sites.  E35(1/27/07)

Add the following:  If water is required for construction purposes from a nonmunicipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624.  R7M98(05/29/02)

Add the following subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION.  The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

Training Utilization Report	Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S80

SECTION 108

PROSECUTION AND PROGRESS

Special Provisions

108-1.03 PROSECUTION AND PROGRESS.  Delete the last sentence of the first paragraph and substitute the following:  Submit the following at the Preconstruction Conference:

Delete item 1. A progress schedule. and substitute the following:

1.	A Critical Path Method (CPM) Schedule is required, in a format acceptable to the Engineer, showing the order the work will be carried out and the contemplated dates the Contractor and subContractors will start and finish each of the salient features of the work, including scheduled periods of shutdown.  Indicate anticipated periods of multiple shift work in the CPM Schedule.  Revise to the proposed CPM Schedule promptly.  Promptly submit a revised CPM Schedule if there are substantial changes to the schedule, or upon request of the Engineer.  (12/13/02)R261M98

Add the following:

Interim completion dates.  All Planing and paving shall be started and completed in the same calendar year with completion before September 15th.

All digouts completed with paving constructed in 2007 and completion before October 15th.

Storm drain cleaned out before October 15th, 2007.

108-1.06 CONTRACT TIME, EXTENSION OF CONTRACT TIME AND SUSPENSION OF WORK.  Add the following:

5.	Long Lead Items.  The Contractor shall provide the Engineer with copies of purchase orders for electrical items (poles, mast arms, and load centers) within 20 calendar days after the receipt of Notice to Proceed.  Include the estimated delivery date to Anchorage, Alaska for electrical items in the Purchase Order.

Upon delivery of electrical items, the Contractor shall provide a copy of the delivery order to the Engineer.  The Contractor has 45 days from delivery of electrical items to complete associated work.  If the project is not completed within the 45 days liquidated damages will be assessed at 25% of values according to subsection 108-1.07 Failure to Complete on Time.

# The Contractor is responsible for maintenance of the project until Contract Time is suspended or the project is completed.

All work within a single intersection, including but not limited to illumination, curb ramps, approach paving, pavement removal and landscaping, shall be completed within 15 calendar days.

All Planing and paving of the Parks Highway shall be started and completed in the same calendar year with completion before Sept 15.  The digout section from station 401+50 to 408+00 shall be constructed in 2007 with completion before Oct 15.

6.	Final Completion Date:  Complete all work by August 15, 2008.

The Engineer will assess liquidated damages according to subsection 108-1.07, Failure to Complete on Time, for failure to complete the work specified above for the work zone duration limits, and interim and final completion dates.

# SECTION 109

MEASUREMENT AND PAYMENT

Special Provisions

109-1.02 MEASUREMENT OF QUANTITIES.  Under subtitle Electronic Computerized Weighing System item (1) add the following to the end of the first sentence:  “, CD, or a USB device.”

109-1.05 COMPENSATION FOR EXTRA WORK.  Under item 3.  Equipment, item a. add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region.  (4/31/05)R14

109-1.07 PAYMENT FOR MATERIALS ON HAND. Add the following: The location of stockpiled materials for payment in acceptable storage facilities off the project will be in Alaska at a location acceptable to the Engineer. (9/1/89)R16

Standard Modification

109-1.08 FINAL PAYMENT.  Add the following sentence to the first paragraph:  The Department will not process the final estimate until the Contractor completes Items 1 through 4 in the first paragraph of subsection 105-1.16. (6/30/04)E11

Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION.  The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other Contractors in the performance of contracts financed in whole, or in part, with federal funds.  The Contractor or subContractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract.  Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION.  It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION.  Failure to comply with the provisions of this section will be considered a material breach of contract, that may result in the termination of this contract or such other remedy as the Department deems appropriate.  The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS.  The following definitions will apply.

1.	Broker.  A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project.  A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

2.	Commercially Useful Function (CUF).  The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment.  The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself.  To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered.  The determination of CUF is made by the Engineer after evaluating the way that the work was performed during the execution of the Contract.

3.	Disadvantaged Business Enterprise (DBE).  An enterprise that is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, that 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department according to 49 CFR, Part 26.

4.	DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

5.	DBE Utilization Goal.  The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

6.	Good Faith Efforts.  Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

7.	Manufacturer.  A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

8.	Notification.  For purposes of soliciting DBE participation on a project and to count toward a Contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

9.	Regular Dealer.  A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large.  If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL.  The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount.  A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE.

- Phase I - Bid.  Each bidder must register with the Civil Rights Office annually according to §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award.  The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment.  Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subContractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report.  Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation.  Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal.  If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and cannot document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer.  At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work.  The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement.  If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal.  In the event the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended according to subsection 120-3.02.

- DBE Utilization Goal.  The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that cannot be replaced.

120-3.02 GOOD FAITH EFFORT.

- Good Faith Effort Criteria.  The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items.  The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) before bid opening.  It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder cannot achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least seven calendar days before bid opening.  The bidder must give the DBEs no less than five (5) days to respond.  The bidder may reject DBE quotes received after the deadline.  Such a deadline for bid submission by DBEs will be consistently applied.  DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor.  Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder.  Allegations of non-competitive DBE quotes must be documented and verifiable.  A DBE quote that is more than 10 percent higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subContractor quotes are for the exact same work or service.  Bidders must have a non-DBE subContractor quote for comparison purposes.  Such evidence shall be provided in support of the bidder’s allegation.  Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subContractor and payments received by the non-DBE subContractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding.  Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding.  Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration.  Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration.  Such an opportunity must be exercised by the bidder within three (3) calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so.  If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within four (4) days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder.  The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work.  Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer according to this Section.  CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subContractor;

- joint-venture; or

- prime Contractor.

- Determination of Commercially Useful Function.  In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO before submitting a bid to a Contractor for DBE trucking.  The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm.  A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker.  (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section.  Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories that it is not certified for, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE.  The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner that the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department.  The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry).  Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska.  Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subContractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- Subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions.  The prime Contractor will not perform the business, accounting, billing, and similar functions of the DBE.  The Engineer may, according to AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE.  Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal.  The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (subsection 120-3.02, items c through h) to replace it with one from a currently certified DBE for that same work or service through subContractor substitution (subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of No CUF.  Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination.  The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE.  In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work.  In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended according to items c through h of subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that cannot be replaced.

120-4.01 METHOD OF MEASUREMENT.  The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer.  The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime Contractor is 100 percent of the monies actually paid to the DBE under the contract for creditable work and materials according to 49 CFR 26.55.

- Credit for the CUF of a subContractor is 100 percent of the monies actually paid to the DBE under the subcontract for creditable work and materials.  This shall include DBE trucking firms certified as a subContractor and not a broker.  Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100 percent of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60 percent of its value.  The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee.  The brokerage fee will not exceed 5 percent of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime Contractor or as a subContractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department.  The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT.  Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work.  If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.  Unsatisfactory work may result in disqualification of the Contractor from future bidding under subsection 102-1.13 and withholding of progress payments consistent with subsection 109-1.06.  (11/17/00)S33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

## Special Provisions

202-1.01 DESCRIPTION.  Add the following:  This work also consists of pavement Planing as specified in this section.  (02/28/01)R143USC

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS, AND CURBS.  Add the following:  Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 6 inches.

Obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at (907) 269-7590.  (03/29/01)R84USC

Add the following subsection:

202-3.06 PAVEMENT PLANING.  Remove existing asphalt concrete pavement by cold Planing at locations shown on the Plans.  The surface of the pavement after Planing on  the Parks Highway shall be uniformly rough grooved or ridged.

If the pavement removed from the existing roadway is not to be used as Item 301 Base Course then the Planed material shall be removed and stockpile at the DOT&PF pit located on Endeavour Street, about 2 miles south of the Parks Highway off the Knik Goose Bay Road. Coordinate with Kurt Devon, Maintenance Chief, 745-2102, for acceptance of material and desired location of stockpile.

Planed material not acceptable to the maintenance chief will be disposed of in an acceptable manner or incorporated into the road structural prism as directed by the Engineer.  Disposal areas shall be outside the project limits and according to subsection 202-3.05, Removal of Pavement, Sidewalks, and Curbs.  For disposal of waste asphalt pavement, the Contractor shall obtain a solid waste disposal permit from the Department of Environmental Conservation (DEC) or use a site previously approved by DEC for disposal of removed asphalt.  ADEC permitting officer in Anchorage may be contacted at (907) 269-7590.  Obtain written permission of the property owner before disposal.

Keep the rotomilled material free from base course and other deleterious material.

During the Planing operation, the Contractor shall concurrently sweep the highway with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove all loosened material from the Planed areas.  The removal operation shall follow within  50 feet of the Planing machine.

The Contractor shall not allow traffic to travel on surfaces that have an abrupt longitudinal Planed edge greater than 2 inches.  In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 2 feet wide shall be placed adjacent to the edge and to all gutters.

Maintain a vertical tolerance of 1/8 inch between adjacent passes by the Planer.

Remove existing asphalt concrete pavement overlay from gutters adjacent to the area being Planed.

The existing curb and gutter not designated for removal shall not be damaged or disturbed.  Damage caused by the Planing operation shall be removed and replaced by the Contractor at the Contractor’s expense.

The Planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 5 feet wide and shall be equipped with cutting teeth placed in a variable lacing pattern to produce the desired finish.

The Planing machine shall have the following capabilities:

1.	operating speeds from 0 to 40 feet per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the Planing operation without leaving the controls,

6.	adjustable as to slope and depth,

7.	a) 	in areas of no curbed shoulders use a longitudinal grade control automatically actuated by the use of two 30 foot skis, (use on both sides of the machine)

b) 	in areas of curbed shoulders use a curb ski to control grade

8.	able to cut up to 3 inches without producing fumes or smoke.

The Contractor shall provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections.  (7/30/99)R143M

202-5.01 BASIS OF PAYMENT.  Add the following:

Item 202(15) At the contract price per unit specified.  Payment is full compensation for mechanical sweepers during Planing operations, removal of pavement from the gutter and stockpile of Planed material according to subsection 202-3.06.

Replace Loop detectors damaged by the Planing operation according to Section 660.  Replace damaged loop detectors at no additional expense to the Department.  If loops are encountered within the Planing depth specified in the Plans, replacement will be measured and paid as Item 660(11) Traffic Loop (or under subsection 109-1.05, Compensation For Extra Work).  (02/28/01) R143

Add the following pay item:

| Pay Item | Pay Unit |
| --- | --- |
| 202(15) Pavement Planing | Square Yard |
| 202(16) Pavement Planing | Square Foot |

SECTION 203

EXCAVATION AND EMBANKMENT

# Special Provisions

203-3.01 GENERAL.  Add the following:  Wait a minimum of 48 hours after staking is complete before commencing excavation activities.  The Engineer, after staking by the Contractor, may adjust stationing of sections for best fit without additional compensation to the Contractor.

203-3.03  EMBANKMENT CONSTRUCTION.  Delete the first sentence of the tenth paragraph and substitute the following:  Place roadway embankment of earth materials in horizontal layers not exceeding 8 inches in thickness measured before compaction.  Each layer of classified material shall have its joint offset from the joint below, longitudinally by 1 foot and transversely by 10 feet.

Add the following:  Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements.  Reduction in excavation or Borrow quantities because of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104, Scope of Work.

203-3.04 COMPACTION WITH MOISTURE AND DENSITY CONTROL. Delete this section in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately optimum moisture content. Dry or moisten material as required.

Compact embankment material to not less than 95 percent of the maximum dry density as determined by WAQTC FOP for AASHTO T 99 / T 180 or ATM 212. The Engineer will determine in-place field densities using WAQTC FOP for AASHTO T 310 and WAQTC FOP for AASHTO T 224. (matls 2/05)

    - BASIS OF PAYMENT.  Add the following:

Obliteration of roadway and pathway includes all grading operations necessary to remove the existing roadway and pathway outside of the new roadway and pathway improvements.  It shall be graded to provide a pleasing appearance, and restore drainage.  Grading and compacting the existing base course material to form a gravel path at the existing Wasilla High School entrance will be subsidiary to the work.

Add the Following Pay Item:

| Pay Item | Pay Unit |
| --- | --- |
| 203(19) Obliteration of Roadway and Pathway | Lump Sum |

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS.  Add the following after the first sentence:  Recycled asphalt material (RAM) may be substituted for aggregate base course, inch for inch, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 1.5-inch sieve and 95-100 percent by weight passing the 1-inch sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| Sieve | Percent Passing by Weight |
| --- | --- |
| 1 inch | 100 |
| 3/4 inch | 70-100 |
| 3/8 inch | 42-90 |
| No. 4 | 28-78 |
| No. 16 | 11-54 |
| No. 50 | 5-34 |
| No. 100 | 3-22 |
| No. 200 | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM. (11/05/02) R176USC02

301-3.01 PLACING.  Add the following:  Base course material used for a separated or detached sidewalk or pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface.  (09/01/89)R26modified

301-3.03 SHAPING AND COMPACTION.  Add the following:  If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern.  The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 40,000 pounds.  The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip according to ATM 412.  Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed.  Tires shall be inflated to 80 psi (± 5 psi), and the roller shall have a minimum operating weight per tire of 3,000 pounds.

301-5.01 BASIS OF PAYMENT.  Add the following:  If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule.  (11/05/02)R176USC02

Replace Section 401 with the following:

SECTION 401

HOT MIX ASPHALT AND SURFACE TREATMENTS

401-1.01 DESCRIPTION. Construct one or more layers of plant-mixed hot asphalt concrete pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

###### MATERIALS

401-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN. Meet the requirements of Table 401-1 for the Job Mix Design performed according to ATM 417.

TABLE 401-1

hOT MIX Asphalt Design Requirements

| DESIGN PARAMETERS | CLASS “A” | CLASS “B” |
| --- | --- | --- |
| Stability, pounds | 1800 min. | 1200 min. |
| Flow, 0.01 inch | 8-14 | 8-16 |
| Voids in Total Mix, % | 3-5 | 3-5 |
| Compaction, number of blows each side of test specimen | 75 | 50 |
| Percent Voids Filled with Asphalt (VFA) | 65-75 | 65-78 |
| Asphalt Content, min. % | 5.0 | 5.0 |
| Dust-asphalt ratio* | 0.6-1.4 | 0.6-1.4 |
| Voids in the Mineral Aggregate (VMA), %, min. |  |  |
| Type I Type II Type III, IV | 12.0 13.0 14.0 | 11.0 12.0 13.0 |

*Dust-asphalt ratio is the percent of material passing the No. 200 sieve divided by the percent of effective asphalt (calculated by weight of mix).

The approved Job Mix Design will specify the target values for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the hot mix asphalt, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broad band limits shown in Table 703-3, for the type of hot mix asphalt specified.  For acceptance testing, hot mix asphalt concrete mixture will have the full tolerances in Table 401-2 applied.  Except the tolerances for the No. 200 sieve, the tolerance limits will apply even if they fall outside the broad band limits shown in Table 703-3.  The tolerance limits for the No. 200 sieve will be confined by the broad band shown in Table 703-3.  Tolerance limits will not be applied to the largest sieve specified.

Do not produce hot mix asphalt for payment until the Engineer approves the Job Mix Design.  Do not mix asphalt produced from different plants.

Use Hot Mix Asphalt Type II, Class B, minimum, for temporary pavement.

Submit the following to the Engineer at least 15 days before the production of hot mix asphalt:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-3 for each type of hot mix asphalt specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and  blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the hot mix asphalt.  Include name of product, manufacturer, test results of the applicable quality requirements of subsection 702-2.01, manufacturer's certificate of compliance according to subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

4.	One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation using ATM 417 and the requirements of Table 401-1 for the appropriate type and class of hot mix asphalt specified and establish the approved Job Mix Design that will become a part of the Contract.

No payment for hot mix asphalt for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved.  Approved changes apply only to hot mix asphalt produced after the submittal of the changes.

Changes. Failure to achieve results conforming to Table 401-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design. Submit changes and new samples in the same manner as the original submittal.

401-2.02 AGGREGATES. Conform to subsection 703-2.04.

Use a minimum of three stockpiles for crushed hot mix asphalt aggregate (coarse, intermediate, and fine). Place blend material or mineral filler, if any, in a separate pile.

401-2.03 ASPHALT CEMENT. Provide the grade of asphalt cement specified in the Contract meeting the applicable requirements of Section 702.  If not specified, use PG 52-28.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Require that the storage tanks used for each batch be noted on the test report, the anti-strip additives required by the mix design be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the written approval of the Engineer.

Furnish the following documents at delivery:

1.                  Manufacturer’s certificate of compliance (106-1.05).

2.                  Conformance test reports for the batch (Section 702).

3.                  Batch number and storage tanks used.

4.                  Date and time of load out for delivery.

5.                  Type, grade, temperature, and quantity of asphalt cement loaded.

6.                  Type and percent of anti-strip added.

401-2.04 ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM 414 and included in the approved Job Mix Design.  At least 70% of the aggregate must remain coated when tested according to ATM 414.

401-2.05 PROCESS QUALITY CONTROL.  Sample and test materials for quality control of the hot mix asphalt according to subsection 106-1.03.  Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits the Contractor’s right to a retest under subsection 401-4.02.

Submit a paving and plant control plan at the pre-paving meeting to be held a minimum of 5 working days before initiating paving operations.  Address the sequence of operations and joint construction.  Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the hot mix asphalt. Include a proposed quality control testing frequency for gradation, asphalt cement content, and compaction.

CONSTRUCTION REQUIREMENTS

401-3.01 WEATHER LIMITATIONS.  Do not place the hot mix asphalt on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix.  Do not place hot mix asphalt unless the roadway surface temperature is 40 °F or warmer.

401-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of hot mix asphalt buildup.  Make equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of hot mix asphalt.

401-3.03 ASPHALT MIXING PLANT.  Meet AASHTO M 156. Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the calibration data to the Engineer at least 4 hours before hot mix asphalt production.

Provide a scalping screen at the asphalt plant to prevent oversize material or debris from being incorporated into the hot mix asphalt.

Provide a tap on the asphalt cement supply line just before it enters the plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling conditions meeting OSHA safety requirements.

401-3.04 HAULING EQUIPMENT. Haul hot mix asphalt in trucks with tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution, or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

Cover the hot mix asphalt in the hauling vehicle, when directed.

401-3.05 ASPHALT PAVERS.  Use self-propelled pavers equipped with a heated vibratory screed.  Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a 30-foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system.  Use grade control on either (a) both the high and low sides or (b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip the hopper with a distribution system to place the hot mix asphalt uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the hot mix asphalt.  Heat and vibrate screed extensions.  Place auger extensions within 20 inches of the screed extensions or according to written manufacturer’s recommendations.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous plant mix when that mix is carried from the paver hopper back to the paver augers.  The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified bituminous pavers:

(1)              Blaw-Knox bituminous pavers shall be equipped with the Blaw-Knox   Materials Management Kit (MMK).

(2)              Cedarapids bituminous pavers must have been manufactured in 1989 or later.

(3)              Caterpillar bituminous pavers shall be equipped with deflector plates.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

401-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers.  Operate rollers according to manufacturer's instructions.  Avoid crushing or fracturing of aggregate.  Use rollers designed to compact hot mix asphalt and reverse without backlash.

Use fully skirted pneumatic-tire rollers with a minimum operating weight of 3000 pounds per tire.

401-3.07 PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces conforming to the Plans and Specifications. Before applying tack coat to the existing surface, clean out loose material from cracks in existing pavement wider than 1 inch in width full depth then fill using asphalt concrete tamped in place.  Clean, wash, and sweep existing paved surfaces of loose material.

Preparation of a milled surface,

        Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than ½-inch with Asphalt Concrete, Type IV.  No density testing is required for the leveling course material.  The Engineer will inspect and accept this material.

        If planing breaks through existing pavement remove 2 inches of existing base and fill with Asphalt Concrete, Type II.  Notify the Engineer of pavement areas that might be considered thin or unstable during pavement removal.

Existing surface must be approved by the Engineer before applying tack coat.  Clean existing pave surfaces of loose material.

Before placing the hot asphalt mix, uniformly coat contact surfaces of curbing, gutters, sawcut pavement, cold joints, manholes, and other structures with tack coat material meeting Section 402.

Allow prime coat to cure and emulsion tack coat to break before placement of hot mix asphalt on these surfaces.

401-3.08 PREPARATION OF ASPHALT. Provide a continuous supply of asphalt cement to the asphalt mixing plant at a uniform temperature, within the allowable mixing temperature range.

401-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the hot mix asphalt, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the hot mix asphalt to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Hot mix asphalt concrete containing soot or fuel is considered unacceptable according to subsection 105-1.11.

401-3.10 MIXING.  Combine the aggregate, asphalt cement and additives in the mixer in the amounts required by the Job Mix Design. Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch plants, put the dry aggregate in motion before addition of asphalt cement.

Mix the hot mix asphalt within the temperature range determined by the Job Mix Design.

401-3.11 TEMPORARY STORAGE.  Silo type storage bins may be used, provided that the characteristics of the hot mix asphalt are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the hot mix asphalt are causes for rejection.

401-3.12 PLACING AND SPREADING.  Place the hot mix asphalt upon the approved surface, spread, strike off, and adjust surface irregularities.  Use asphalt pavers to distribute hot mix asphalt, including leveling courses.  The maximum compacted lift thickness allowed is 3 inches.

During placement, the Engineer may evaluate the hot mix asphalt immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25oF lower than the surrounding hot mix asphalt are likely to produce areas of low density.  Any thermal images and/or thermal profile data will become part of the project record and shared with the Contractor.  The Contractor shall immediately adjust laydown procedures to correct the problem.

Use hand tools to spread, rake, and lute the hot mix asphalt in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours.  Place approved material against the outside pavement edge when the drop off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland concrete curbing until it has cured for at least 72 hours.

Place hot mix asphalt over bridge deck membranes according to Section 508 and the manufacturer's specifications.

401-3.13 COMPACTION. Thoroughly and uniformly compact the hot mix asphalt by rolling.  In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each type of hot mix asphalt, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed in according to WAQTC FOP for AASHTO T 166/T 275 using a 6-inch diameter core.  (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on hot mix asphalt that has not cooled sufficiently to prevent indentation.

401-3.14 JOINTS. Minimize the number of joints.  Place and compact the hot mix asphalt to ensure a continuous bond, texture, and smoothness between adjacent sections of the hot mix asphalt.

Remove to full depth improperly formed joints resulting in surface irregularities, replace with new hot mix asphalt, and thoroughly compact.

Precut pavement removal to a neat line with a power saw or by other method approved by the Engineer.

Form transverse joints by saw cutting back on the previous run to expose the full depth of layer with a power saw or other method approved by the Engineer or use a removable bulkhead. Skew transverse joints between 15-25 degrees.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 12 inches from the edge of the stripe.

Uniformly coat joint surfaces below the final lift with tack coat conforming to Section 703 before placing any fresh HMA against the joint.

Before placing an adjacent panel of hot mix asphalt to form a joint in the top layer, apply Crafco Pavement Joint Adhesive No. 34524 Deery Cold Joint Adhesive or approved equal, to the edge of the existing panel.  Edge surface preparation, application temperature, thickness, and method shall be according to manufacturer’s recommendations.

For the top layer of hot mix asphalt, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch diameter core centered on the longitudinal joint at each location the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

For areas that fail to achieve the prescribed joint density seal the surface of the longitudinal joints with Asphalt Systems GSB-78 or approved equal, while the hot mix asphalt is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be according to the manufacturer’s recommendations and an application rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150F.  These joints do not need to be tacked and will be measured but not evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to subsection 401-4.05.

401-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10 foot straightedge.  Correct variations from the testing edge, between any two contacts of more than 1/4 inch.

The Engineer will measure the surface smoothness of the top layer of asphalt concrete pavement in the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace, or grind smooth any area of final pavement surface that does not meet straight edge tolerances.  Costs associated with meeting surface tolerances are subsidiary to the Hot Mix Asphalt pay item.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 25 feet of the existing pavement at the project beginning and end.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph results (PrI) filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

401-3.16 PATCHING DEFECTIVE AREAS.  Remove hot mix asphalt that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch. Remove defective hot mix asphalt for the full thickness of the course.  Cut the pavement so that edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with a tack coat meeting Section 402 and allow to cure.  Place and compact fresh hot mix asphalt according to subsection 401-3.13 to grade and smoothness requirements.

Costs associated with patching defective areas are subsidiary to the Hot Mix Asphalt pay item.

401-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Hot Mix Asphalt.

a)	By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

b)	By the area of final hot mix asphalt surface.

Asphalt Price Adjustment.  Calculated by quality level analysis under subsection 401-4.03.

Asphalt Cement.  By the ton, as follows.

1.	Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASTHO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the Job Mix Design.

2.	Supplier's invoices minus waste, diversion and remnant.  This procedure may be used on projects where deliveries are made in tankers and the asphalt plant is producing hot mix asphalt for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineers presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Any remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement. The Engineer will determine the method. The weight of asphalt cement in waste hot mix asphalt will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Method 1 will be used for determining asphalt quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt content specified in the Job Mix Design.

Job Mix Design. When specified, Contractor furnished Job Mix Designs will be measured at one according to the hot mix asphalt class and type.

Temporary Pavement.  By weighing.  No deduction will be made for the weight of asphalt cement or anti-stripping additive.

Longitudinal Joint Adhesive and Sealing.  By the linear foot of longitudinal joint.

Preleveling.  By weighing.  No deduction will be made for the weight of asphalt cement or anti stripping additive.

401-4.02 ACCEPTANCE SAMPLING AND TESTING.  The quantity of each class and type of hot mix asphalt produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons, each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot.  The price adjustment computed, according to subsection 401-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 4,999 tons, the contract quantity will be considered one lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  Hot mix asphalt quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  Hot mix asphalt quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to subsection 401-4.03 except as noted.

For Contract quantity of less than 1,500 tons (and for temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any hot mix asphalt that does not conform to the approved JMD.

Samples collected at the plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

1. 	Asphalt Cement.  Hot mix samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, at the end of the auger, or from the windrow according to WATC FOP for AASHTO T 168 and ATM 403, as directed by the Engineer.  Hot mix asphalt samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 168 and ATM 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP for AAHSTO T2, or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the hot mix asphalt.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

- Batch Plants.  Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2. Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density.  Cut full depth core samples from the finished hot mix asphalt within 24 hours after final rolling. Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples in accordance with WAQTC FOP for AASHTO T 166/T 275.  Do not core hot mix asphalt on bridge decks. Backfill and compact voids left by coring with new hot mix asphalt within 24 hours.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location the panel completing the joint is cored for mat density acceptance testing.

4.	Retesting.  A retest of any sample outside the limits specified in Table 401-2 may be requested provided the quality control requirements of 401-2.05 are met. Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample is allowed.  Except for the first lot, gradation and asphalt cement content are determined from the same sample, retesting for gradation or asphalt cement from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for MSG.

5.	Asphalt Cement.

The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the contract quantity of asphalt cement is between 85 – 199 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated in accordance with this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment in accordance with 401-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

The total asphalt cement price adjustment is the sum of the individual lot price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to each type of Hot Mix Asphalt for which the contract quantity equals or exceeds 1,500 tons, except as specified in subsection 401-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors.  The first factor is a composite pay factor for hot mix asphalt that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing hot mix asphalt with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing hot mix asphalt that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under subsection 105-1.11.

The Engineer will reject hot mix asphalt that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected hot mix asphalt and tested if requested.  If test results are within specification limits, payment will be made for the hot mix asphalt.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted under Item 401(6) Asphalt Price Adjustment.  Costs associated with removal and disposal of the rejected hot mix asphalt are subsidiary to the Hot Mix Asphalt pay item.

Outlier Test.  Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if any size on the gradations test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment.  The density test result for that sublot will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment, however, the gradation and asphalt cement content results for that sublot will be included provided neither is an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean () of the remaining test results is determined:

Where:	= summation of

x = individual test value to xn

n = total number of test values

is rounded to the nearest tenth for density and sieve sizes except the No. 200 sieve.  is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:	(x2)	=	sum of the squares of individual test values.

(x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200. Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 401-2.  The TV is the specification value specified in the approved Job Mix Design. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing PWL calculations.  The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

TABLE 401-2

LOWER SPECIFICATION LIMIT (LSL) & UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV-6.0 | TV+6.0 |
| 1/2 inch sieve | TV-6.0 | TV+6.0 |
| 3/8 inch sieve | TV-6.0 | TV+6.0 |
| No. 4 sieve | TV-6.0 | TV+6.0 |
| No. 8 sieve | TV-6.0 | TV+6.0 |
| No. 16 sieve | TV-5.0 | TV+5.0 |
| No. 30 sieve | TV-4.0 | TV+4.0 |
| No. 50 sieve | TV-4.0 | TV+4.0 |
| No. 100 sieve | TV-3.0 | TV+3.0 |
| No. 200 sieve1 | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.4 | TV+0.4 |
| Mat Density % | 92 | 98 |

Note 1.Tolerances for the No. 200 sieve may not exceed the broad band limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:	QU

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:	QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit which corresponds to a given QU) is determined. See Subsection 106-1.03.

7.	PL (percent within the lower specification limit which corresponds to a given QL) is determined. See Subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor is determined for Density (DPF) and gradation and asphalt cement content pay factors (PF) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

Sf

The CPF is rounded to the nearest hundredth.

Table 401-3 gives the weight factor (f) for each sieve size and asphalt cement content.

TABLE 401-3

WEIGHT FACTORS

| ###### Sieve Size | Type I | Type II | Type III |
| --- | --- | --- | --- |
|  | ###### Factor “f” | Factor “f” | ###### Factor “f” |
| 1 inch sieve | 4 |  |  |
| 3/4 inch sieve | 4 | 4 |  |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower.

## PAB = Price Adjustment Base  = $72 per ton  for the Parks Highway MP 42.1 to MP 44 Rehabilitation:  Crusey Street to Lucas Road and the HSIP:  Lucille Street at Fred Nelson Avenue Safety Improvements projects.

PAB = Price Adjustment Base  = $55 per ton  for the Crusey Street Improvements project.

The total asphalt concrete price adjustment is the sum of all price adjustments for each lot and will be adjusted under Item 401(6) Asphalt Price Adjustment.

EVALUATION OF ASPHALT CEMENT

Asphalt cement will be randomly sampled and tested every 200 tons and evaluated for price adjustment.  If the last sample increment is 100 tons or less, that quantity of asphalt cement will be added to the quantity represented by the previous sample and the total quantity will be evaluated for price adjustment.  If the last sample increment is greater than 100 tons, it will be sampled, tested and evaluated separately.  Asphalt cement pay reduction factors for each sample will be determined from Table 401-4.

The total asphalt cement price adjustment is the sum of the individual sample price adjustments and will be subtracted under Item 401(6) Asphalt Price Adjustment.

Table 401-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  | #### Spec | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval |
| ##### Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | <3 Pa-s | <3 |  | >3 |  |  |  |  |  |  |
| Dynamic Shear | >1.00 kPa | >1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.89 | 0.50-0.70 | <0.50 |
| Toughness | >110 in-lbs | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | <70.0 |
| Tenacity | >75 in-lbs | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | <48.0 |
| ##### Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | <1.00 % | <1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | >1.276 |
| Dynamic Shear | >2.20 kPa | >2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | <1.048 |
| ##### Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | <5000 kPa | <5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | >5867 |
| Creep Stiffness, S | <300 MPa | <300 |  | 301-338 |  |  |  | 339-388 | 389-450 | >450 |
| Creep Stiffness, m-value | >0.300 | >0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | <0.261 |
| Direct Tension | >1.0 % | >1.0 |  | 0.86-0.99 |  |  |  | 0.71-0.85 | 0.56-0.70 | <0.56 |

# Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty X PRF

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results and using ASTM D3244 determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction.  If this final value incurs a price adjustment, the Contractor under Item 408(3) Asphalt Price Adjustment, shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot and will be included in 401(6) Asphalt Price Adjustment.

EVALUATION OF PAVEMENT SMOOTHNESS.

The top layer of hot mix asphalt will be measured according to 401-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

# Smoothness Price Adjustment = PAB x PQ x SF

PAB = Price Adjustment Base (401-4.03)

PQ = Final quantity of Hot Mix Asphalt, tons

PrI = Final measured hot mix smoothness, inches/mile

SF = Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

The smoothness price adjustment will be applied under Item 401(6) Asphalt Price Adjustment.

EVALUATION OF LONGITUDINAL JOINT DENSITY.  Longitudinal joint density price adjustments apply when hot mix asphalt quantities are equal to or greater than 1,500 tons.  A longitudinal joint density price adjustment for the top layer will be based on the average of all the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, apply the following disincentive:

- Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted under Item 401(6) Asphalt Price Adjustment.

- Sections of longitudinal joint represented by cores with less than 91% density shall be surface sealed according to subsection 401-3.14.

2.	If project average joint density is greater than 92% MSG apply the following incentive:

Longitudinal joint density price adjustment equal to $1.50 per linear foot is added under Item 401(6) Asphalt Price Adjustment.

The longitudinal joint price adjustment will be included in Item 401(6) Asphalt Price Adjustment.

401-5.01 BASIS OF PAYMENT.

Asphalt cement, anti-strip additives for Item 401(3) Temporary Hot Mix Asphalt, or for hot mix asphalt for leveling course is subsidiary to item 401(3).

Sealing the surface of longitudinal joints according to subsection 401-3.12 will be subsidiary to 401 items.

Asphalt cement, anti stripping additives, tack coat, and crack sealing (401-3.07) are subsidiary to the hot mix asphalt unless specified as pay items.

Price adjustments will not apply to:

1.	Hot Mix Asphalt for leveling course

2.	Temporary Hot Mix Asphalt

Payment for furnishing and installing joint adhesive will be paid as 401(9) Longitudinal Joint Adhesive and Sealing.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6) Asphalt Price Adjustment.

The Engineer will assess a fee of $2,500.00 under Item 401(6) Asphalt Price Adjustment, for each mix design subsequent to the approved Job Mix Design for each Type and Class of Hot Mix Asphalt specified.Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 401(1A) Hot Mix Asphalt, Type II; Class B | Ton |
| 401(1B) Hot Mix Asphalt, Type IV; Class B | Lane Station |
| 401(2) Asphalt Cement, Grade PG 52-28 | Ton |
| 401(3) Temporary Hot Mix Asphalt | Ton |
| 401(6) Asphalt Price Adjustment | Contingent Sum |
| 401(9) Logitudinal Joint Adhesive and Sealing | Linear Foot |

(06/07/06) R199USC04

Standard Modification

Add the following:

401-5.02 ASPHALT MATERIAL PRICE ADJUSTMENT.

Asphalt Material Price Adjustment. This subsection provides a price adjustment for asphalt material by: (1) additional compensation to the contractor or (2) a deduction from the contract amount.

- This provision shall apply to asphalt material meeting the criteria of Section 702, and is included in items listed in the bid schedule of Sections 306, 307, 308, 401 thru 405, 608, and 609.

- This provision shall only apply to cost changes in asphalt material that occur between the date of bid opening and the date the asphalt material is incorporated into the project.

- The asphalt material price adjustment will only apply when:

  - There is more than 500 tons of asphalt material in the bid schedule of Sections described in Item 1; and

  - There is more than a seven and one half percent (7.5%) increase or decrease in the Alaska Asphalt Material Price Index, from the date of bid opening to the date the asphalt material is incorporated into the project.

- As used in this Subsection, the Alaska asphalt material price index is calculated bi-monthly on the first and third Friday of each month, and will remain in effect from the day of calculation until the next bi-monthly calculation. The Alaska asphalt material price index is posted on the Department’s Statewide Materials website, and calculated according to the formula posted there.

- Price adjustment will be cumulative and calculated with each progress payment. Use the price index in effect on the last day of the pay period, to calculate the price adjustment for asphalt material incorporated into the project during that pay period. The Department will increase or decrease payment under this contract by the amount determined with the following asphalt material price adjustment formula:

For an increase exceeding 7.5%, additional compensation = [(IPP – IB) – (0.075 x IB)] x Q

For a decrease exceeding 7.5%, deduction from contract     = [(IB – IPP) – (0.075 x IB)] x Q

Where:

Q	=  Quantity of Asphalt Material incorporated into project during the pay period, in tons

IB 	=	Index at Bid: the Bi-monthly Alaska asphalt material price index in effect on date of bid, in dollars per ton

IPP 	=	Index at Pay Period: the Bi-monthly Alaska asphalt material price index in effect on the last day of the pay period, in dollars per ton

- Method of measurement for determining Q (quantity) is the weight of asphalt material that meets the criteria of this subsection and is incorporated into the project. The quantity does not include aggregate, mineral filler, blotter material, thinning agents added after material qualification, or water for emulsified asphalt.

- Basis of payment is:

| Pay Item | Pay Unit |
| --- | --- |
| 401(10) Asphalt Material Price Adjustment | Contingent Sum |

E55(5/01/07)

Add the following Section:

SECTION 408

HOT MIX ASPHALT (SUPERPAVE)

408-1.01 DESCRIPTION.  Construct one or more layers of Plant-mixed hot asphalt concrete pavement on an approved surface, to the lines, grades, and depths shown on the Plans.

CONSTRUCTION REQUIREMENTS

408-2.01 COMPOSITION OF MIXTURE - JOB MIX DESIGN.  Meet the requirements of Table 408-1 for the Job Mix Design performed according to AASHTO R35 except evaluation of moisture sensitivity will determined by ATM 414 and not AASHTO T283.

TABLE 408-1

Hot Mix Asphalt Design Requirements

| Design ESALs, millions | 0.3 to < 3 |
| --- | --- |
| Rut Index, max. ATM 419 | 3 |

The approved Job Mix Design will specify the target values for gradation, the target value for asphalt cement content, the Maximum Specific Gravity (MSG) of the hot mix asphalt, the additives, and the allowable mixing temperature range.

Target values for gradation in the Job Mix Design must be within the broadband limits shown in Table 703-3, for the type of hot mix asphalt specified.  For acceptance testing, hot mix asphalt will have the full tolerances in Table 408-2 applied.  Except for the No. 200 sieve, the tolerance limit will apply even if falling outside the broad band shown in Table 703-3.  Tolerance limits will not be applied to the largest sieve specified.

Do not produce hot mix asphalt for payment until the Engineer approves the Job Mix Design.  Do not mix hot asphalt produced from different Plants.

Submit the following to the Engineer at least 15 days before the production of hot mix asphalt:

1.	A letter stating the location, size, and type of mixing Plant, the proposed gradation for the Job Mix Design, gradations for individual stockpiles with supporting process quality control information, and the blend ratio of each aggregate stockpile. The proposed gradation must meet the requirements of Table 703-3 for each type of hot mix asphalt specified in the Contract.

2.	Representative samples of each aggregate (coarse, intermediate, fine, and blend material and/or mineral filler, if any) in the proportions required for the proposed mix design. Furnish a total of 500 pounds of material.

3.	Five separate 1-gallon samples of the asphalt cement proposed for use in the hot mix asphalt.  Include name of product, manufacturer, test results of the applicable quality requirements of subsection 702-2.01, manufacturer's certificate of compliance according to subsection 106-1.05, a temperature viscosity curve for the asphalt cement or manufacturer's recommended mixing and compaction temperatures, and current Material Safety Data Sheet.

- One sample, of at least 1/2 pint, of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Material Safety Data Sheet.

The Engineer will then evaluate the material and the proposed gradation and the requirements of Table 408-1 for the appropriate type and class of hot mix asphalt specified, and establish the approved Job Mix Design that will become a part of the Contract.

For the Parks Highway Rehabilitation and Lucille/Nelson Street Intersection Improvements projects the Engineer will assess a fee of $2,500 under Item 408(3), Asphalt Price Adjustment, for each mix design subsequent to the approved Job Mix Design for each Type and Class of Hot Mix Asphalt specified.

No payment for hot mix asphalt for which a new Job Mix Design is required, will be made until the new Job Mix Design is approved.  Approved changes apply only to hot mix asphalt produced after the submittal of the changes.

Changes.  Failure to achieve results conforming to Table 408-1 or changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio, will require a new Job Mix Design.  Submit changes and new samples in the same manner as the original submittal.

408-2.02 AGGREGATES.  Conform to subsection 703-2.04.

Use a minimum of 3 stockpiles for crushed hot mix asphalt aggregate (coarse, intermediate, and fine).  Place blend material or mineral filler, if any, in separate piles.  Additional stockpiles may be required for some material sources to create a Design Aggregate Structure that meets the volumetric requirements of the mix design procedures.

408-2.03 ASPHALT MATERIALS.  Conform to subsection 702-2.01, if not specified use PG 64-28.   Table 1 of AASHTO M 232 will not apply.

Provide test reports for each batch of asphalt cement showing conformance to the specifications in Section 702 before delivery to the project.  Storage tanks used for the batch shall be noted on the test report, the anti-strip additives required by the mix design shall be added during load out for delivery to the project, and a printed weight ticket for anti-strip is included with the asphalt cement weight ticket.  The location where anti-strip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Batch number and storage tanks used.

- Date and Time of load out for delivery.

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

408-2.04 ANTI-STRIP ADDITIVES. Use anti-strip agents in the proportions determined by ATM T-414 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested according to ATM T-414.

408-2.05 QUALITY CONTROL. Sample and test materials for quality control of the hot mix asphalt according to subsection 106-1.03.  Provide copies of these test results to the Engineer within 24 hours.

Failure to perform quality control forfeits the Contractor's right to retest under subsection 408-4.02.

Submit a paving and Plant control Plan at the pre paving meeting to be held a minimum of 5 working days before beginning the paving operations.  Address the sequence of operations and joint construction.  Outline steps to assure product consistency, to minimize segregation, and to prevent premature cooling of the hot mix asphalt.  Include a proposed quality control testing frequency for gradation, asphalt cement content and compaction.

## CONSTRUCTION REQUIREMENTS

408-3.01 WEATHER LIMITATIONS. Do not place hot mix asphalt on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mix. Do not place hot mix asphalt unless the roadway surface temperature is 40F or warmer.  Do not place mix after September 15 unless approved by the Engineer in writing.

408-3.02 EQUIPMENT, GENERAL.  Use equipment in good working order and free of hot mix asphalt buildup.  Make all equipment available for inspection and demonstration of operation a minimum of 24 hours before placement of hot mix asphalt.

408-3.03 BITUMINOUS MIXING PLANTS. Meet AASHTO M156. Use an asphalt Plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt Plant and furnish copies of the calibration data to the Engineer at least 4 hours before hot mix asphalt production.

Provide a scalping screen at the asphalt Plant to prevent oversize material or debris from being incorporated into the hot mix asphalt.

Provide a tap on the asphalt cement supply line just before it enters the Plant (after the 3-way valve) for sampling asphalt cement.

Provide aggregate and asphalt cement sampling conditions meeting OSHA safety requirements.

408-3.04 HAULING EQUIPMENT.  Haul hot mix asphalt in trucks having tight, clean, smooth metal beds, thinly coated with a minimum amount of paraffin oil, lime water solution or an approved manufactured asphalt release agent.  Do not use petroleum fuel as an asphalt release agent.

Cover the hot mix asphalt in the haul vehicle, when directed.

408-3.05 ASPHALT PAVERS.   Use self-propelled asphalt pavers having a heated vibratory screed.  Control with grade and cross slope using automatic grade and slope control devices.  Use an erected string line, a 30 foot minimum mobile stringline (ski), or other approved grade follower, to automatically actuate the paver screed control system. Use grade control on either a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip the paver with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip the hopper with a distribution system to place the hot mix asphalt uniformly in front of screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness, and texture without tearing, shoving or displacing the hot mix asphalt.

Equip the paver with a means of preventing the segregation of the coarse aggregate particles from the remainder of the bituminous Plant mix when the mix is carried from the paver hopper back to the paver augers.  The means and methods used shall be approved by the paver manufacturer and may consist of chain curtains, deflector plates, or other such devices and any combination of these.

The following specific requirements apply to the identified bituminous pavers:

- Blaw-Knox bituminous pavers shall be equipped with the Blaw-Knox Materials Management Kit (MMK).

- Cedarapids bituminous pavers must have been manufactured in 1989 or later.

- Caterpillar bituminous pavers shall be equipped with deflector plates.

The use of a “Layton Box” or equivalent towed paver is allowed on bike paths, sidewalks, and driveways.

408-3.06 ROLLERS.  Use both steel-wheel (static or vibratory) and pneumatic-tire rollers. Operate rollers according to manufacturer's instructions. Avoid crushing or fracturing of aggregate. Use rollers designed to compact hot asphalt concrete mixtures and reverse without backlash.

Use fully skirted pneumatic-tire rollers having a minimum operating weight of 3000 pounds per tire.

408-3.07 PREPARATION OF EXISTING SURFACE.  Prepare the existing surfaces in conformance with the Plans and Specifications.  Before applying tack coat to the existing surface, clean out loose material from cracks in existing pavement wider than 1 inch in width full depth then fill using asphalt concrete tamp in place.  Clean, wash, and sweep existing paved surfaces of loose material.

Preparation of milled surface.

	Prelevel remaining ruts, pavement delaminations, or depressions having a depth greater than ½ inch with Asphalt Concrete, Type IV (Section 401).  No density testing is required for the leveling course material.  The Engineer will inspect and accept this material.

	If Planing breaks through existing pavement remove 2 inches of existing base and fill with Asphalt Concrete, Type II, Class B (Section 401).  Notify the Engineer of pavement areas that might be considered thin or unstable during pavement

The Engineer must approve existing paved surfaces before tack coat is applied.  Clean existing paved surfaces of loose material

Before placing the hot mix asphalt, uniformly coat contact surfaces of curbing, gutters, saw cut pavement, cold joints, manholes, and other structures with tack coat material meeting Section 402.  Allow tack coat to break before placement of hot mix asphalt on these surfaces.

408-3.08 PREPARATION OF ASPHALT CEMENT.  Provide a continuous supply of asphalt cement to the asphalt Plant at a uniform temperature, within the allowable mixing temperature range noted in the approved mix design.

408-3.09 PREPARATION OF AGGREGATES. Dry the aggregate so the moisture content of the hot mix asphalt, sampled at the point of acceptance for asphalt cement content, does not exceed 0.5% (by total weight of mix), as determined by WAQTC FOP for AASHTO T 329.

Heat the aggregate for the hot mix asphalt to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Hot mix asphalt containing soot or fuel is considered unacceptable according to subsection 105-1.11.

408-3.10 MIXING.  Combine the aggregate, asphalt cement and additives in the mixer in the amounts required by the Job Mix Design. Mix to obtain 98% coated particles when tested according to AASHTO T 195.

For batch Plants, put the dry aggregate in motion before addition of asphalt cement.

Mix the hot mix asphalt within the temperature range determined by the Job Mix Design.

408-3.11 TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE.  Silo type storage bins may be used, provided that the characteristics of the hot mix asphalt are not altered. Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness, or stiffness of the hot mix asphalt are causes for rejection.

408-3.12 PLACING AND SPREADING.  Place the hot mix asphalt upon the approved surface, spread, strike off, and adjust surface irregularities. Use asphalt pavers to distribute hot mix asphalt concrete mixture, including leveling courses.

During placement, the Engineer may evaluate the hot mix asphalt immediately behind the paver for temperature uniformity.  Areas with temperature differences more than 25oF lower than the surrounding hot mix asphalt are likely to produce areas of low density.  Any thermal images and thermal profile data will become part of the project record and shared with the Contractor.

The Contractor shall immediately adjust his laydown procedures to correct the problem.

Use hand tools to spread, rake, and lute the hot mix asphalt concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.

When the section of roadway being paved is open to traffic, pave adjacent traffic lanes to the same elevation within 24 hours. Place approved material against the outside pavement edge when the drop-off exceeds 2 inches.

When multiple lifts are specified in the Contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, are placed and accepted.

Do not pave against new Portland concrete curbing until it has cured for at least 72 hours.

Place hot mix asphalt over bridge deck membranes according to Section 508 and the manufacturer's specifications.

408-3.13 COMPACTION.  Thoroughly and uniformly compact the hot mix asphalt by rolling. In areas not accessible to large rollers, compact with mechanical tampers or trench rollers.

The target value for density is 94% of the maximum specific gravity (MSG), as determined by WAQTC FOP for AASHTO T 209.  For the first lot of each type of hot mix asphalt, the Job Mix Design will determine the MSG.  For additional lots, the MSG will be determined by the sample from the first sublot of each lot.

Acceptance testing for density will be performed according to WAQTC FOP for AASHTO T 166/T 275 using a 6 inch diameter core. (Acceptance testing for density of leveling course or temporary pavement is not required.)

Do not leave rollers or other equipment standing on hot mix asphalt that has not cooled sufficiently to prevent indentation.

408-3.14 JOINTS. Minimize the number of joints.  Place and compact the hot mix asphalt to ensure a continuous bond, texture, and smoothness between adjacent panels of hot mix asphalt.

Remove to full depth improperly formed joints resulting in surface irregularities, replace with new hot mix asphalt, and thoroughly compact.  Precut pavement removal to a neat line with a power saw or by other method approved by the Engineer.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the layer with a power saw or other method approved by the Engineer, or use a removable bulkhead.

Offset the longitudinal joints in one layer from the joint in the layer immediately below by at least 6 inches.  Align the joints of the top layer at the centerline or lane lines.  Where preformed marking tape striping is required, offset the longitudinal joint in the top layer not more than 6 inches from the edge of the stripe.

Uniformly coat joint surfaces below the final lift with a tack coat conforming to Section 703 before placing any fresh HMA against the joint.

On the final lift, seal the vertical edge of pavement with Crafco Pavement Joint Adhesive No. 34524, Deery Cold Joint Adhesive, or approved equal before completing the longitudinal joint by paving against it. Apply a 1/8 inch, thick band of joint adhesive over the cold mat according to manufacturer’s recommendations.

For the top layer of hot mix asphalt, the minimum specification limit for longitudinal joint density is 91% of the MSG of the panel completing the joint.  Cut one 6 inch, diameter core centered on the longitudinal joint at each location that the panel completing the joint is cored for acceptance density testing.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

In the top layer, seal the longitudinal joints with Asphalt Systems GSB-78, or approved equal, while the hot mix asphalt is clean, free of moisture, and before traffic marking.  Longitudinal joint sealing shall be applied to manufacturer’s recommendations at a rate of 0.15 gallons per square yard.  Apply the sealant at least 12 inches wide centered on the longitudinal joint.

Hot lapped joints formed by paving in echelon must be completed while the mat temperature is over 150° F.  These joints do not need to be tacked and will be measured and evaluated for joint density.

Longitudinal joints will be evaluated for acceptance according to subsection 408-4.05.

408-3.15 SURFACE TOLERANCE.  The Engineer will test the finished surface after final rolling at selected locations using a 10-foot or straightedge.  Correct variations from the testing edge, between any two contacts, greater than 1/4 inch.

The Engineer will measure the surface smoothness of the finished top layer of hot mix asphalt pavement in the driving lanes with an inertial profiler before final acceptance of the project.  Remove and replace, or grind smooth any area of final pavement surface that does not meet tolerances. All costs associated with meeting surface tolerances are subsidiary to the hot mix asphalt pay item.

After completion of corrective work, the Engineer will measure the pavement surface in the driving lanes a second time for a smoothness price adjustment.  No measurements will be taken in turn lanes, lane transitions, or within 25 feet of the existing pavement at the project beginning and end.

Smoothness will be measured in both wheel paths of each lane and reported as profilograph results (PrI) filtered with a 0.2 inch blanking band. Report PrI as a job average for all measured lanes, calculated to the nearest 0.1 inch.

408-3.16 PATCHING DEFECTIVE AREAS.  Remove any hot mix asphalt that becomes contaminated with foreign material, is segregated, or is in any way determined to be defective.  Do not skin patch. Remove defective hot mix asphalt for the full thickness of the course. Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic. Coat edges with a tack coat meeting Section 402 and allow to cure. Place and compact fresh hot mix asphalt according to subsection 408-3.13 to grade and smoothness requirements.

All costs associated with patching defective areas are subsidiary to the Hot Mix Asphalt pay item.

408-4.01 METHOD OF MEASUREMENT. Section 109 and the following:

Hot Mix Asphalt.

a)	By weighing, no deduction will be made for the weight of asphalt cement or anti-stripping additive.

b)	By the area of final hot mix asphalt surface.

Asphalt Price Adjustment. Calculated by quality level analysis under subsection 408-4.03.

Asphalt Cement. By the ton as follows:

1.	Percent of asphalt cement for each sublot multiplied by the total weight represented by that sublot.  ATM 405 or WAQTC FOP for AASHTO T 308 will determine the percent of asphalt cement.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity. If no acceptance testing is required, the percent of asphalt cement is the target value for asphalt cement in the Job Mix Design.

2.	Supplier's invoices minus waste, diversion and remnant. This procedure may be used on projects where deliveries are made in tankers and the asphalt Plant is producing hot mix asphalt for one project only.

The Engineer may direct, at any time, that tankers be weighed in the Engineers presence before and after unloading. If the weight determined at the project varies more than 1% from the invoice amount, payment will be based on the weight determined at the project.

Remnant or diversion will be calculated based on tank stickings or weighing the remaining asphalt cement.  The Engineer will determine the method.  The weight of asphalt cement in waste hot mix asphalt will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Method 1 will be used for determining asphalt cement quantity unless otherwise directed in writing.  The procedure initially used will be the one used for the duration of the project.  No payment will be made for any asphalt cement more than 0.4% above the optimum asphalt cement content specified in the Job Mix Design.

Temporary Pavement. By weighing. No deduction will be made for the weight of asphalt cement or anti-stripping additive.

Anti-Strip Additive.  Based on the number of tons of asphalt cement containing required additive.

Job Mix Design. When specified, Contractor furnished Job Mix Designs will be measured at one per hot mix asphalt class and type.

Longitudinal Joint and Joint Adhesive.  By the lineal foot.

408-4.02 ACCEPTANCE SAMPLING AND TESTING. The quantity of each class and type of hot mix asphalt produced and placed will be divided into lots and the lots evaluated individually for acceptance.

A lot will normally be 5,000 tons.  The lot will be divided into sublots of 500 tons; each randomly sampled and tested for asphalt cement content, density, and gradation according to this subsection.  If the project has more than 1 lot, and less than 8 additional sublots have been sampled at the time a lot is terminated, either due to completion of paving operations or the end of the construction season (winter shutdown), the material in the shortened lot will be included as part of the prior lot. The price adjustment computed, according to subsection 408-4.03, for the prior lot will include the samples from the shortened lot.

If 8 or 9 samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 1,500 tons and 5000 tons, the Contract quantity will be considered 1 lot.  The lot will be divided into sublots of 500 tons and randomly sampled for asphalt cement content, density, and gradation according to this subsection except that a determination for outliers will not be performed.  Hot mix asphalt quantities of less than 300 tons remaining after dividing the Contract quantity into sublots will be included in the last sublot.  Hot mix quantities of 300 tons or greater will be treated as an individual sublot.  The lot will be evaluated for price adjustment according to subsection 408-4.03 except as noted.

For Contract quantity of less than 1,500 tons, (or for temporary pavement), hot mix asphalt will be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the hot mix asphalt to the specified depth and finished surface requirements and tolerances.  The Engineer reserves the right to perform any testing required in order to determine acceptance.  Remove and replace any hot mix asphalt that does not conform to the approved JMD.

Samples collected at the Plant from dry batched aggregates, the conveyor system, or the asphalt cement supply line shall be taken by the Contractor in the presence of the Engineer.  The Engineer will take immediate possession of the samples.

1. 	Asphalt Cement Content. Hot mix asphalt samples taken for the determination of asphalt cement content will be taken randomly from behind the screed before initial compaction, at the end of the auger, or from the windrow according to WAQTC FOP for AASHTO T168 and ATM 403 as directed by the Engineer.  Hot mix asphalt samples taken for the determination of both asphalt cement content and gradation will be taken randomly from behind the screed before initial compaction or from the windrow according to WAQTC FOP for AASHTO T 403.

Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  At the discretion of the Engineer, asphalt cement content will be determined according to ATM 405 or WAQTC FOP for AASHTO T 308.

2.	Aggregate Gradation.

a.	Drum Mix Plants.  Samples taken for the determination of aggregate gradation from drum mix Plants will be from the combined aggregate cold feed conveyor via a diverter device, or from the stopped conveyor belt according to WAQTC FOP  for AASHTO T2, or from the same location as samples for the determination of asphalt cement content.  Locate diverter devices for obtaining aggregate samples from drum mix Plants on the conveyor system delivering combined aggregates into the drum.  Divert aggregate from the full width of the conveyor system and maintain the diverter device to provide a representative sample of aggregate incorporated into the hot mix asphalt.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  The aggregate gradation for samples from the conveyor system will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

- Batch Plants. Samples taken for the determination of aggregate gradation from batch Plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates according to WAQTC FOP for AASHTO T 2.  Two separate samples will be taken, one for acceptance testing and one held in reserve for retesting if applicable.  Dry batched aggregate gradations will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For hot mix asphalt samples, the aggregate gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO T 308) has burned off the asphalt cement.

3.	Density. Cut full depth core samples from the finished hot mix asphalt within 24 hours after final rolling.  Neatly cut one 6 inch diameter core sample with a core drill at each location marked by the Engineer.  Cut 6 inch diameter core samples for assurance testing as directed by the Engineer.  Use a core extractor to prevent damage to the core.  The Engineer will determine the density of the core samples according to WAQTC FOP for AASHTO T 166/T 275.  Do not core hot mix asphalt on bridge decks.  Backfill and compact voids left by coring with new hot mix asphalt within 24 hours.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day. Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day. The accrued amount will be subtracted under Item 401(3), Asphalt Price Adjustment.

Cores for longitudinal joint density shall be centered on the longitudinal joint at each location the panel completing the joint is cored for mat density acceptance testing.

4.	Retesting. A retest of any sample outside the limits specified in Table 408-2 may be requested provided the quality control requirements of 408-2.05 are met.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  The Engineer will mark the sample location for the density retest within a 2 foot radius of the original core.  The original test results will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor. Only one retest per sample is allowed.  Except for the first lot, when gradation or asphalt cement content are determined from the same sample retesting for gradation or asphalt cement content from the first sublot of a lot will include retesting for the MSG; when separate samples are used, retesting for asphalt cement content will include retesting for the MSG.

5.	Asphalt Cement.  The lot size for asphalt cement will normally be 200 tons.  If a project has more than one lot and the remaining asphalt cement quantity is less than 150 tons, it will be added to the previous lot and that total quantity will be evaluated for price adjustment as one lot.  If the remaining asphalt cement quantity is 150 tons or greater, it will be sampled, tested and evaluated as a separate lot.

If the Contract quantity of asphalt cement is between 85 – 199 tons, the contact quantity will be considered as one lot and sampled, tested, and evaluated according to this subsection.  Quantities of asphalt cement less than 85 tons will be accepted based on manufacturer’s certified test reports and certification of compliance.

Asphalt cement will be sampled according to WAQTC FOP for AASHTO T 40, tested for conformance to the specifications in Section 702, and evaluated for price adjustment according to 408-4.03.  Asphalt cement pay reduction factors for each sample will be determined from Table 408-4.  Three separate samples from each lot will be taken, one for acceptance testing, one for Contractor retesting, and one held in reserve for referee testing if applicable.

The total asphalt cement price adjustment is the sum of the individual lot price adjustments and will be subtracted under Item 408(3) Asphalt Price Adjustment.

408-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to each type of Hot Mix Asphalt for which the contract quantity equals or exceeds 1,500 ton, except as defined in subsection 408-4.02.

Acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis method as specified in subsection 106-1.03 to determine the total estimated percent of the lot that is within specification limits.

The price adjustment is based on the lower of two pay factors. The first factor is a composite pay factor for hot mix asphalt that includes gradation and asphalt cement content.  The second factor is for density.

A lot containing hot mix asphalt with less than a 1.00 pay factor will be accepted at an adjusted price, provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing hot mix asphalt that fails to obtain at least a 0.75 pay factor will be considered unacceptable and rejected under subsection 105-1.11.

The Engineer will reject hot mix asphalt that appears to be defective based on visual inspection.  A minimum of two samples will be collected from the rejected hot mix asphalt and tested if requested.  If all test results are within specification limits, payment will be made for hot mix asphalt.  If any of the test results fail to meet specifications, no payment will be made and the cost of the testing will be subtracted under Item 408(3) Asphalt Price Adjustment.  Costs associated with removal and disposal of the rejected hot mix asphalt are subsidiary to the Hot Mix Asphalt pay item.

Outlier Test. Before computing the price adjustment, the validity of the test results will be determined by SP-7, the Standard Practice for Determination of Outlier Test Results. Outlier test results will not be included in the price adjustment calculations.

When gradation and asphalt cement content are determined from the same sample, if a sieve size on a gradation test or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sublot will not be included in the price adjustment. The density test result for that sublot will be included in the price adjustment provided it is not an outlier.  If the density test result is an outlier, the density test result will not be included in the price adjustment, however, the gradation and asphalt cement content results for that sublot will be included provided neither is an outlier.

When gradation and asphalt cement content are determined from separate samples, if any sieve size on the gradation test is an outlier, then the gradation test results for that sample will not be included in the price adjustment.  The asphalt cement content and density test results for that sublot will be included in the price adjustment provided neither is an outlier.  If the asphalt cement content test result is an outlier, it will not be included in the price adjustment but the gradation and density test results for the sublot will be included provided neither is an outlier.  If the density test result is an outlier, it will not be included in the price adjustment but the gradation and asphalt cement content test results will be included provided neither is an outlier.

Quality Level Analysis. Pay factors are computed as follows:

1.	Outliers (determined by SP-7), and any test results on material not incorporated into the work, are eliminated from the quality level analysis.

The arithmetic mean () of the remaining test results is determined:

Where:	= summation of

x = individual test value to xn

n = total number of test values

is rounded to the nearest tenth for density and all sieve sizes except the No. 200 sieve.  is rounded to the nearest hundredth for asphalt cement content and the No. 200 sieve.

2.	The sample standard deviation(s), after the outliers have been excluded, is computed:

Where:	(x2)	=	sum of the squares of individual test values.

(x)2	=	square of the sum of the individual test values.

The sample standard deviation (s) is rounded to the nearest hundredth for density and all sieve sizes except the No. 200 sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt cement content and the No. 200 sieve.

If the computed sample standard deviation (s) is <0.001, then use s = 0.20 for density and all sieves except the No. 200.  Use s = 0.020 for asphalt cement content and the No. 200 sieve.

3.	The USL and LSL are computed.  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances in Table 408-2.  The TV is the specification value specified in the approved Job Mix Design. Specification tolerance limits for the largest sieve specified will be plus 0 and minus 1 when performing PWL calculations. The TV for density is 94% of the maximum specific gravity (MSG), the LSL is 92% of MSG and the USL is 98%.

TABLE 408-2

LOWER SPECIFICATION LIMIT (LSL) &

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 3/4 inch sieve | TV-6.0 | TV+6.0 |
| 1/2 inch sieve | TV-6.0 | TV+6.0 |
| 3/8 inch sieve | TV-6.0 | TV+6.0 |
| No. 4 sieve | TV-6.0 | TV+6.0 |
| No. 8 sieve | TV-6.0 | TV+6.0 |
| No. 16 sieve | TV-5.0 | TV+5.0 |
| No. 30 sieve | TV-4.0 | TV+4.0 |
| No. 50 sieve | TV-4.0 | TV+4.0 |
| No. 100 sieve | TV-3.0 | TV+3.0 |
| No. 200 sieve1 | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.4 | TV+0.4 |
| Density % | 92 | 98 |

Note 1.Tolerances for the No. 200 sieve may not exceed the broadband limits in Table 703-3.

4.	The Upper Quality Index (QU) is computed:	 QU

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	The Lower Quality Index (QL) is computed:	 QL

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	PU (percent within the upper specification limit that corresponds to a given QU) is determined. See subsection 106-1.03.

7.	PL (percent within the lower specification limit that corresponds to a given QL) is determined. See subsection 106-1.03.

8.	The Quality Level (the total percent within specification limits) is determined for aggregate gradation, asphalt cement content, and density.

Quality Level = (PL + PU) - 100

9.	Using the Quality Levels from Step 8, the lot Pay Factor is determined for Density (DPF) and gradation and asphalt cement content pay factors (PF) from Table 106-2. The maximum pay factor for the largest sieve size specification for gradation is 1.00.

10.	The Composite Pay Factor (CPF) for the lot is determined using the following formula:

[f3/4 inch (PF3/4 inch) + f1/2 inch (PF1/2 inch) +....fac (PFac)]

CPF =

f

The CPF is rounded to the nearest hundredth.

Table 408-3 gives the weight factor (f) for each sieve size and asphalt cement content.

TABLE 408-3

WEIGHT FACTORS

| ###### Sieve Size | Type I | Type II | Type III |
| --- | --- | --- | --- |
|  | ###### Factor “f” | Factor “f” | ###### Factor “f” |
| 1 inch sieve | 4 |  |  |
| 3/4 inch sieve | 4 | 4 |  |
| 1/2 inch sieve | 4 | 5 | 4 |
| 3/8 inch sieve | 4 | 5 | 5 |
| No. 4 sieve | 4 | 4 | 5 |
| No. 8 sieve | 4 | 4 | 5 |
| No. 16 sieve | 4 | 4 | 5 |
| No. 30 sieve | 4 | 5 | 6 |
| No. 50 sieve | 4 | 5 | 6 |
| No. 100 sieve | 4 | 4 | 4 |
| No. 200 sieve | 20 | 20 | 20 |
| Asphalt Cement Content, % | 40 | 40 | 40 |

The price adjustment will be based on either the CPF or DPF, whichever is the lowest value. The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1.00] x (tons in lot) x (PAB)

* CPF or DPF, whichever is lower.

PAB = Price Adjustment Base = $92 per ton for Parks Hwy Rehabilitation and Lucille/Nelson Improvements

PAB = Price Adjustment Base = $55 per ton for Crusey Street Improvements

Table 408-4

ASPHALT CEMENT PAY REDUCTION FACTORS

(Use the single, highest pay reduction factor)

|  | #### Spec | Pay Reduction Factor (PRF) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 0 | 0.04 | 0.05 | 0.06 | 0.07 | 0.08 | 0.1 | 0.25 | Reject or Engr Eval |
| ##### Tests On Original Binder |  |  |  |  |  |  |  |  |  |  |
| Viscosity | <3 Pa-s | <3 |  | >3 |  |  |  |  |  |  |
| Dynamic Shear | >1.00 kPa | >1.00 |  | 0.88-0.99 |  |  |  | 0.71-0.87 | 0.50-0.70 | <0.50 |
| Toughness | >110 in-lbs | >93.5 | 90.0-93.4 | 85.0-89.9 | 80.0-84.9 | 75.0-79.9 | 70.0-74.9 |  |  | <70.0 |
| Tenacity | >75 in-lbs | >63.8 | 61.0-63.7 | 58.0-60.9 | 55.0-57.9 | 52.0-54.9 | 48.0-51.9 |  |  | <48.0 |
| ##### Tests On RTFO |  |  |  |  |  |  |  |  |  |  |
| Mass Loss | <1.00 % | <1.00 |  | 1.001-1.092 |  |  |  | 1.093-1.184 | 1.185-1.276 | >1.076 |
| Dynamic Shear | >2.20 kPa | >2.20 |  | 1.816-2.199 |  |  |  | 1.432-1.815 | 1.048-1.431 | <1.048 |
| ##### Test On PAV |  |  |  |  |  |  |  |  |  |  |
| Dynamic Shear | <5000 kPa | <5000 |  | 5001-5289 |  |  |  | 5290-5578 | 5579-5867 | >5867 |
| Creep Stiffness, S | <300 MPa | <300 |  | 301-338 |  |  |  | 339-388 | 389-450 | >450 |
| Creep Stiffness, m-value | >0.300 | >0.300 |  | 0.287-0.299 |  |  |  | 0.274-0.286 | 0.261-0.273 | <0.261 |
| Direct Tension | >1.0 % | >1.0 |  | 0.86-0.99 |  |  |  | 0.71-0.85 | 0.56-0.70 | <0.56 |

# Asphalt Cement Price Adjustment for each sample = 5 x PAB x Qty x PRF

PAB = Price Adjustment Base

Qty = Quantity of asphalt cement represented by asphalt cement sample

PRF = Pay Reduction Factor from Table 401-4

Asphalt Cement Appeal Procedure.  Once notified of a failing test result of an asphalt cement sample, the Contractor has 21 days to issue a written appeal.  The appeal must be accompanied by all of the Contactor’s quality control test results and a test result of Contactor’s sample of this lot tested by an AASHTO accredited asphalt laboratory (accredited in the test procedure in question).  The Engineer will review these test results and using ASTM D3244 determine a test value upon which to base a price reduction.

If the Contractor challenges this value, then the referee sample held by the Engineer will be sent to a mutually agreed upon independent AASHTO accredited laboratory for testing.  This test result will be incorporated into the ASTM D3244 procedure to determine a test value upon which to base a price reduction. If this final value incurs a price adjustment, the Contractor under Item 408(3), Asphalt Price Adjustment, shall pay the cost of testing the referee sample.

The total Asphalt Price Adjustment is the sum of all the price adjustments for each lot and will be included in 401(6) asphalt price adjustment.

408-4.04 EVALUATION OF PAVEMENT FOR SMOOTHNESS.  The top layer of hot mix asphalt will be measured according to 408-3.15 and evaluated for a smoothness price adjustment.  The Engineer will calculate the smoothness price adjustment as follows:

Note to Designer see subsection 408-3.15 before applying Smoothness Price Adjustment

Smoothness Price Adjustment = PAB x PQ x SF

PAB = Price Adjustment Base (408-4.03)

PQ = Final quantity of Hot Mix Asphalt, tons

PrI = Final measured hot mix asphalt smoothness, inches/mile

SF = Smoothness Factor

If the PQ is less than 1,500 tons, the SF = 0

If the PQ is 1,500 to 5,000 tons, the SF = 0.1333 – (0.01666 x PrI)

If the PQ is greater than 5,000 tons, the SF = 0.0666 – (0.0083 x PrI)

The smoothness price adjustment will be applied under Item 408(3), Asphalt Price Adjustment.

408-4.05 EVALUATION OF LONGITUDINAL JOINTS FOR ACCEPTANCE.

Longitudinal joint density price adjustments apply when hot mix asphalt quantities are equal to or greater than 1,500 tons.

A longitudinal joint density price adjustment for the top layer will be based on the averages of the joint densities on a project and determined as follows:

1.	If project average joint density is less than 91% MSG, the following disincentives apply:

Longitudinal joint density price adjustment equal to $3.00 per lineal foot is deducted under Item 408(3) Asphalt Price Adjustment.

2.	If project average joint density is greater than 92% MSG apply the following incentive applies:

Longitudinal joint density price adjustment equal to $1.50 per lineal foot is added under Item 408(3) Asphalt Price Adjustment.

401-5.01 BASIS OF PAYMENT.  Anti-stripping additives, and tack coat are subsidiary to the hot mix asphalt.

Payment for furnishing and installing joint adhesive and sealing pavement adjacent to the joints will be paid as 408(4) Longitudinal Joint Adhesive and Sealing.

The accepted quantity will be paid for at the adjusted contract unit price for the pay item listed below, complete in place.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, and for fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in subsection 408-4.02.

The Engineer will assess a mix design fee of $2,500.00 under Item 408(3) Asphalt Price Adjustment for each mix design subsequent to the first approved Job Mix Design for each Type and Class of Hot Mix Asphalt specified.

Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day. Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day. The accrued amount will be subtracted under Item 408(3) Asphalt Price Adjustment.

Price adjustments will not apply to:

1.	Asphalt Concrete Mixture for leveling course

2.   Temporary Pavement

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 408(1A) Hot Mix Asphalt, Type V | Ton |
| 408(1B) Hot Mix Asphalt, Type VH, Hard Aggregate | Ton |
| 408(2) Asphalt Cement, PG 64-28 | Ton |
| 408(3) Asphalt Price Adjustment | Contingent Sum |
| 408(4) Longitudinal Joint Adhesive and Sealing | Linear Foot |

SECTION 503

REINFORCING STEEL

Special Provisions

503-1.01 DESCRIPTION.  Add the following:  This work will also include the epoxy coating of appropriate reinforcing steel bars.  The reinforcing steel in the exposed vertical face of a retaining wall facing the roadway and as noted on the Plans shall be epoxy coated.  R38 (02/08/96)

503-5.01 BASIS OF PAYMENT.  Add the following:  If epoxy coating the reinforcing steel is required, it will be a subsidiary obligation and no separate payment will be made. R38 (02/08/96)

### SECTION 505

### PILING

Special Provisions

505-3.03  Pile Bearing Values.  Delete the first paragraph of this subsection and substitute the following:  Drive piles, except piles for lighting standards, to the required ultimate bearing capacity.  For lighting standards, install piles of sufficient length to cut the pile at the required cut-off elevation and to provide the minimum installed length shown on the Plans.

505-3.09 Driving Piles.  Add the following:  Sites for the lighting standard foundations can contain subsurface soils that consist of very dense sandy gravel with cobbles and boulders.

When the minimum pile length shown on the Plans can not be installed for a lighting standard foundation, install the pile tip to an elevation established by the Engineer.

505-4.01 Method of Measurement.  Add the following to the second paragraph:

Do not measure piles for lighting standards for payment.

505-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:  Include costs of furnishing and installing piles for lighting standards in Item 660(3), Highway Lighting System Complete.  R65USC04 (04/15/05)

Add the following Section:

SECTION 514

CONCRETE SURFACE TREATMENTS

Special Provisions

514-1.01 DESCRIPTION.  This work consists of providing an aesthetic fascia on the sidewalk type retaining wall using custom concrete form liners.  Install graffiti protection on the retaining wall.

514-2.01 MATERIALS.  Reinforcing steel shall meet the requirements of subsection 709-2.01 Reinforcing Steel.

Provide custom concrete form liners with Birch Trees pattern as shown on the Plans.

Use a two step graffiti protection system designed specifically for this use.  The system shall consist of a single component clear acrylic base coat covered by a clear urethane finish coat.  This material is not a sealer or vapor barrier and no appreciable discoloration is allowed.

Trained personnel shall apply the material according to the manufacturer’s recommendations.

514-3.01 AESTHETIC FASCIA.  Use form liners on retaining wall forms that have exposed surfaces.  The wall dimensions and concrete quantities provided on the Plans are minimum and do not include allowances for the thickness of the form liners and must be accounted for by the Contractor.

The liners will cover the majority of the form with a minimum of 2-inches and a maximum of 12-inches between the edge of liner and the finished top of the wall, pathway or original ground grade at the bottom, and edge or expansion joints of the wall on the sides.  The Engineer shall approve the liner placement on the form before the concrete pour.

514-3.02 GRAFFITI PROTECTION.  Let concrete surfaces set at least 28 days before applying any coatings.  Apply the base coat with a sprayer according to the manufacturer’s recommendations.  Apply two coats of the finish coat after the base coat has cured for 72 hours.  Apply appropriate masking as required.

514-4.01 METHOD OF MEASUREMENT.  Measure aesthetic fascia by the square foot of actual form liner surface in the finished structure.

Measure graffiti protection by the square foot of surface area coated.

514-5.01 BASIS OF PAYMENT.  Payment for retaining wall treatments will be full compensation for the labor, equipment and materials, including reinforcing steel, required to complete the walls according to the Plans and Specifications.  (02/28/01)R41USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 514(1) Aesthetic Fascia | ## Square Foot |
| 514(2) Graffiti Protection | ## Square Foot |

SECTION 603

CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION.  Add the following:  This work shall also consist of installing culvert marker posts.

603-2.01 MATERIALS.  Delete the second paragraph and substitute the following:  When Item 603(17-xx), Pipe, is listed in the bid schedule, furnish either Corrugated Steel Pipe (CSP) or Reinforced Concrete Pipe.  Corrugated Polyethylene Pipe is not allowed.  End Sections for Metal Pipe must be of the same material as the pipe.

Add the following:  Culvert marker posts shall meet the requirements of subsection 730-2.05, Flexible Delineator Posts.  The color shall be blue with no other markings.  The 2.5-inch by 6-foot post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 9 inches.

Add the following subsection:

603-3.06 CULVERT MARKER POSTS.  Culvert marker posts shall be installed on the approach side of storm drain outfalls 30 inches and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer.  Forty-two (42) inches of post shall remain above the ground after driving.

603-4.01 METHOD OF MEASUREMENT.  Add the following:  Culvert marker posts will not be measured for payment.

603-5.01 BASIS OF PAYMENT.  Add the following:  Culvert marker posts will not be

paid for directly, but will be subsidiary to pipe items.  R42USC (08/27/03)

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-1.01 DESCRIPTION. Add the following:  With respect to the Parks Hwy Rehabilitation and Lucille/Nelson Improvements projects, this work shall also consist of cleaning the existing drainage system, including all manholes, catch basins, inlets, culverts inlets and culvert outlets.

For the Crusey Street Improvements project contact the City of Wasilla, Department of Public Works, and the Project Engineer to coordinate a pre-inspection of the sanitary sewer manholes located within the project limits before pavement removal begins and a post-inspection after paving operations are complete. Any deficiencies found during the pre-inspection of the manholes shall be corrected by the City of Wasilla, at no cost to the Department, before the Contractor begins adjusting the facilities.  Any deficiencies found during the post-inspection of the manholes shall be corrected by the Contractor, at the Contractor’s expense.

604-3.01 CONSTRUCTION REQUIREMENTS.  The following modifications apply only to the Crusey Street Improvements project:

Add the following after the first paragraph:  Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 1 inch of concrete or asphalt, as applicable.

Under the sentence “Reconstruct existing manhole by using one or more of the following methods,” add the following:

- Remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab.

Add the following:  Notify the Engineer a minimum of 5 days before removing the frame and grate.  The Engineer will notify DOT&PF M&O (907-338-1466) and have an M&O representative physically identify frames and grates to be salvaged.  Deliver frames and grates designated to be salvaged to the DOT&PF M&O yard located at 5300 East Tudor Road.  Frames and grates not designated for salvage by DOT&PF M&O shall become the Contractor’s property.

When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the Plans and 2 inches larger than the outside diameter of the new pipe.  Then, grout joint with nonshrinking cement mortar.

Curb inlet structures shall have a 3 inch formed hole approximately 2 feet below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation.  Keep the openings functional.  This may require temporary dikes, RMC extensions, etc., as necessary.  Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install before concrete hardens.

Add the following:  Contact the City of Wasilla, Department of Public Works at (907) 373-9010 to establish where to send the written notice.   A minimum of fifteen (15) calendar days notice shall be given to the City of Wasilla for pre and post inspections.  Provide the Engineer a copy of the written notice.  The Contractor shall be responsible for furnishing all required traffic control and personnel to assist the City of Wasilla while locating and performing the pre-construction and post-construction inspections.  Both the Contractor and the Engineer shall witness the condition and location of each sanitary sewer manhole. The Contractor forfeits all right to deny damages done by the Contractor or the Contractors agents during the course of work if the Contractor fails to participate in both inspections

The following modifications apply only to the Parks Hwy Rehabilitation and Lucille St/Nelson Ave projects:

Add the following:  Reconstruct existing 3’x 2.5’ wooden weir by removing 8 square feet of existing 2”x 6”x 24” tongue and grove cedar boards and 11’ of existing 3” x 4” channel bar and replace weir with materials matching existing including all necessary fasteners and/or welding.

Replace existing curb boxes in kind at locations designated on the Plans.

Add the following subsection (applies only to the Parks Hwy Rehabilitation and Lucille St/Nelson Ave projects):

604-3.02 CLEAN DRAINAGE SYSTEM.  Remove debris from catch basins, manholes and inlets regardless of the quantity of debris.  No more than 5%-10% of debris should remain.  Remove debris (sticks, plastic bags) blocking culvert inlets and outlets.  Record the date of inspection and the depth of sediments.

The Contractor shall provide equipment that is capable of cleaning storm drains.  The equipment shall be inspected and accepted by the Engineer before use on this project.  The Contractor shall provide traffic control while cleaning storm drains.

The work shall include disposal of silt, trash, debris and other material removed from the system. This material may be disposed at the Municipality of Anchorage Hazardous Materials Waste Disposal site.

604-4.01 METHOD OF MEASUREMENT.  Add the following:  Frames, grates, and lids will not be measured for payment.

Add the following:  Item 604(20) Clean Drainage System, will be measured in the manner specified in the directive authorizing the work.

604-5.01 BASIS OF PAYMENT.  Add the following:  Frames, grates and lids are subsidiary to the drainage structure. (02/28/05) R43USC04

Add the following:  Item 604(20) Clean Drainage System, payment will be made on a time and materials basis according to subsection 109-1.05, Compensation for Extra Work.  Traffic Control provided to clean storm drains will be paid under the 643 items.

Payment for Replace Existing Curb Box shall be included in item 604(3) Reconstruct Existing Manhole and shall include removal and replacement of adjacent curb and gutter as needed.

Delete Item 604(1) Storm Sewer Manhole.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 604(1A) Storm Drain Manhole, Type I | ## Each |
| 604(1B) Storm Drain Manhole, Type II | ## Each |
| 604(1C) Storm Drain Manhole, Type III | ## Each |
| 604(20) Clean Drainage System | ## Contingent Sum |
| 604(21) Reconstruct Storm Drain Weir | ## Lump Sum |

For information only:  For item 604(20), approximately 90 drainage structures shall be cleaned.

SECTION 606

GUARDRAIL

## Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers.  Use flexible markers with an over all length of 72 inches.  The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 20 square inches of surface area.  Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacturer:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval before ordering the markers.

606-3.01 GENERAL.  Replace the second sentence of the first paragraph with the following:  Conform to these Specifications and the Standard Drawings with the following exception.  Modify Standard Drawing G-20.10 to only allow an offset of 1.5 feet for the ET-2000.  (05/12/04)R266

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL.  Add the following:  Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 50 feet of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed.

606-3.07 REMOVAL AND DISPOSAL OF EXISTING GUARDRAIL.  Delete the last sentence and substitute the following:  Notify the Engineer a minimum of 5 days before removing guardrail for disposal.  The Engineer will notify ADOT&PF M&O (907-338-1466) and have an M&O representative physically identify portions of guardrail to be salvaged.  Deliver guardrail and associated hardware designated to be salvaged to the ADOT&PF M&O yard located at Yard at 289 Inner Springer Loop Road in Palmer, Alaska.  Remaining items removed becomes the Contractor’s property.

(06/12/03)R259M98

Add the following subsection:

606-3.09 FLEXIBLE MARKERS.  For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail.  The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer.

SECTION 607

FENCES

# Special Provisions

607-1.01 DESCRIPTION.  Add the following:  This work also includes the fabrication and installation of Decorative Fence, Banner Posts, and Boundary Fence Panels.  Decorative Fence/Barrier consists of the materials shown on the drawings and all other fittings, and hardware required to construct the fence in the location shown on the Plans.

Decorative fence panels consist of stainless steel plate cut with custom patterns as shown on the Drawings, and all stainless steel hardware necessary for installation.

607-2.01 MATERIALS.  Add the following:

| Steel Components | Section 716 |
| --- | --- |
| Boundary Fence | Section 722 |
| Stainless Steel | Section 722 |
| Polyester material for powder coating | AAMA 605.2 for mechanical, chemical and corrosion resistance |

607-3.01 CONSTRUCTION REQUIREMENTS.  Add the following:

Boundary Fence.

Submit a 4 inch x 4 inch sample of the powdercoat finish to the Engineer for review and approval.

Apply the powder coating through the seven-step (minimum) process below:

a.	Blast clean to SSPC10 with a surface profile of no greater than 1.5mils

b.	Etch surfaces with an iron phosphate treatment to remove foreign material

c.	Rinse with clear water

d.	Rinse with non-chrome seal

e.	Oven drying surfaces before powder coating

f.	Electrostatically apply powdercoat base of zinc rich epoxy primer and partially cure

g.	Electrostatically apply final surface finish of polyester powder to a thickness of 3 mils and bake to proper cure schedule

After the powdercoat finish has been approved, submit one complete Boundary Fence Panel to the Engineer for approval before fabrication of the remainder of Boundary Fence. 

Weld in conformance with subsection 504-3.01.08. Grind all welded connections to a smooth, even finish. Complete all welding before applying powdercoat finish.

Drill or punch steel components as required for attaching hardware or other materials.

Provide fabricated product free of warps, kinks, dents, scrapes and other damage or unsightly condition. Round sharp edges to a uniform radius. Grind all edges and corners smooth and straight.

Package and clearly tag parts and assemblies in a manner that will protect materials from damage, and facilitate identification and field assembly.

Install rail plumb to within a lateral displacement of ¼ inch over the height of the rail.

Allow for erection loads, and for sufficient temporary bracing to maintain true alignment until completion of erection and installation of permanent attachments.

Obtain Engineer’s acceptance before site cutting or making adjustments not scheduled.

Patterned Panels.

Submit one sample section of the decorative panels with complete pattern and surface finish to the Engineer for approval before final fabrication.  If accepted, the finished panel may be used in the installation.

Finish exposed surfaces smooth, uniform, sharp, and true to well-defined lines. Finish all stainless steel plates, strips, and sheets with a #4 surface finish.

Provide fabricated product free of warps, kinks, dents, scrapes and other damage or unsightly condition. Round sharp edges to a uniform radius. Grind smooth all burrs, jagged edges, and surface defects.

Drill or punch metalwork as required for attaching hardware or other materials.

Do not flame cut Patterned materials.

Package and clearly tag parts and assemblies in a manner that will protect materials from damage, and facilitate identification and field assembly.

Install fence panels plumb to within a lateral displacement of ¼ inch over the height of the plate.

Powdercoat banner supports according to modifications the Boundary Fence requirements above.

Add the following subsection:

604-3.02 FABRICATION.

For Bronze Finish. Comply with NAAMM "Metal Finishes Manual" for recommendations relative to application and designations of finishes.  Buff, polish and seal.

607-4.01 METHOD OF MEASUREMENT.  Add the following:

Decorative Fence/Barrier.  By linear foot measured horizontally along the top of the proposed retaining wall.  Changes in elevation will not be measured separately.

Steel Leaves.  Each leaf installed on the fence or the retaining wall.

See Section 622, Rest Area Facilities for measurement of all steel structures associated with the rest area at Tommy Moe Drive and the Parks Highway.

607-5.01 BASIS OF PAYMENT.

Decorative Fence/Barrier.  Payment for Decorative Fence/Barrier will be full compensation for all labor, materials, and equipment required to construct the Fence according to the Plans and Specifications.  Subsidiary items include:  preparing submittals and shop drawings, all steel components, galvanizing, fasteners, and other appurtenances required to construct a complete and functional unit in the location shown on the drawings.

Steel Leaves.  Payment for Steel Leaves will be full compensation for all labor, materials, and equipment to construct the Steel Leaves on the Decorative Fence/Barrier and retaining wall.

Boundary Fence.  Boundary fence panels shall be measured by each 10 foot section of fence, installed as shown.  Support posts and their accessories shall be subsidiary to this item.

Add the following Pay Items:

| Pay Item | Pay Unit |
| --- | --- |
| 607(7) Boundary Fence Panels | ## Each |
| 607(10) Decorative Fence/Barrier | ## Linear Foot |
| 607(11) Steel Leaves | ## Each |

SECTION 608

SIDEWALKS

Special Provisions

608-1.01 description.  Add the following:  This work also consists of constructing asphalt pathway(s) and median(s), curb ramp retrofit, concrete medians, concrete landings, and concrete sidewalk type retaining walls in conformance with the Plans.

608-2.01 MATERIALS.  Delete paragraph number 2 and substitute the following:

2.  	Asphalt Sidewalk and Asphalt Pathway

###### Asphalt Cement, PG 52-28					subsection 702-2.01

Aggregate, Type II or III	subsection 703-2.04

Mix Design Requirements 	ATM T 417

Marshall Stability, pounds, min.				1,000

Percent Voids, Total Mix	2-5

Compaction, Blows/side			50

(02/01/00)R47USC

608-3.01 CONCRETE SIDEWALKS.  Add The Following:  Concrete sidewalks designated on the Plans to be stamped (red) shall be colored full depth with Davis Color 160, Brick Red, at a rate of 5 pounds of color per sack of portland cement.  Stamp pattern shall be Bomanite “Running Bond Brick” or equal.

Standard Modifications

608-3.03 CURB RAMPS.  Delete subsection in its entirety and replace with the following:

Construct curb ramps according to the details and the locations shown on the Plans.  Follow the construction requirements of subsection 608-3.01.  Give the exposed concrete surface a coarse broom finish.  Install detectable warnings.

Add the following new subsection:

608-3.04 DETECTABLE WARNINGS.  Construct detectable warnings according to the details and the locations shown on the Plans.  Install detectable warning tile by embedding tile flanges into cast in place concrete construction so there are no vertical changes in grade exceeding 0.25 inch or horizontal gaps exceeding 0.5 inch.  Align pattern on a square grid in the predominant direction of travel.  Install the same type of detectable warning tile throughout the project.  Install the following:

1.	Armor-Tile ADA-C Series tactile detectable warning tile made of composite materials, safety yellow color, slip resistant surface, full length flanges on bottom, and truncated dome pattern;

2.	Cast iron, yellow polymer soaked or black asphalt dip finish, with slip resistant surface, with handle or flange on bottom, and with truncated dome patter; or

- Approved equal.

Detectable warnings shall be manufactured and installed according to the Americans with Disabilities Act Accessibility Guidelines. E40(1/27/07)

Special Provisions

Add the following subsections:

608-3.05 ASPHALT PATHWAYS AND MEDIANS.  Construct asphalt pathways and medians according to subsection 608-3.02, Asphalt Sidewalks.

608-3.06  SIDEWALK TYPE RETAINING WALLS.   Construct sidewalk type retaining walls according to subsection 608-3.01 Concrete Sidewalks.  Excavation and backfill required for the retaining walls shall be according to Section 204.  Reinforcing steel shall conform to the requirements of Section 503.

608-3.07 CURB RAMP RETROFIT.  Provide labor, materials, and equipment necessary to bring existing curb ramps up to current ADA standards.  This work shall include removal and replacement of existing ramp, curb, sidewalk, and asphalt in the locations shown on the Plans.  Remove and replace additional curb as directed by Engineer to allow for a tie in to the existing curb at the best location.  Once the Contractor begins work on a curb ramp the Contractor shall have 6 days to demolish the existing curb ramp and reconstruct a new curb ramp.  If the Contractor does not complete the work on that curb ramp within 6 days, a price adjustment will be assessed to the Contractor as indicated in subsection 643-3.06 Traffic Price Adjustment.

608-3.08 CONCRETE MEDIANS. The concrete median shall be a cast-in-place, colored, textured and imprinted architectural concrete paving as manufactured by Bomanite Corporation, P.O. Box 599, Madera, California 93639-0599, 559-673-2411, www.bomanite.com. No substitutions will be allowed without prior written approval from the Engineer.

1.	Description.  Imprinted concrete includes:

a.		Materials: Welded wire fabric (WWF), concrete, dry-shake hardener, curing compound, release agent and sealer.

b.	Special imprinting and texturing tools.

c.	Concrete placement and finish.

d.	Color hardener and release agent placement.

e.	Pressure washing to remove excess release agent.

f.	Sealer application.

2.	References and Standards.  Install Bomanite/Bomacron imprinted concrete according to the standards and specifications of Bomanite Corporation and the American Concrete Institute (ACI).

3.	Related Work.

a.	Preparation work, include sub-grade preparation, finish grading, placing and setting screeds, and furnishing and placement of welded wire fabric.

b.	Provide and place concrete with integral color.

c.	Provide and apply color hardener.  Bomanite Color Hardener is a colored dry powder, used to color the concrete surface while promoting increased concrete abrasion resistance and color steadfastness.

d.	Provide and apply liquid release agent.  Bomanite Liquid Release is a clear liquid used to facilitate release of the imprinting tools from concrete surface.

e.	Provide and apply Bomacron imprinting tools.

f.	Provide and apply curing treatment.  Bomanite Con-Shield will help prevent deterioration and spalling from deicing salts used in freeze/thaw conditions.  Bomanite Con-Shield will also increase the abrasion resistance of finished Bomacron surface.

g.	Provide and apply membrane forming sealer.  Bomanite Hydrolock, as membrane forming sealer, meets all EPA VOC Laws and Regulations.

4.	Quality Assurance.

a.		The Bomanite Contractor shall provide a qualified foreman or supervisor who has a minimum of 3 years experience with imprinted and textured concrete, and who has successfully completed at least 5 Bomanite/Bomacron imprinted concrete installations of high quality and similar in scope to that specified herein.  Evidence that the Contractor is qualified to complete the project in a workman like manner as specified herein shall be submitted to and approved by the engineer.

b.	All Bomanite work shall comply with the current specifications and quality standards issued by Bomanite Corporation.

c.	The Bomanite Contractor shall provide a job site sample (referee sample) of 100 square feet minimum to be approved by the engineer before start of construction.  Said sample shall be the standard for the balance of the work installed, and shall be protected against damage until final approval from the engineer.

5.	Concrete Mix Design.

a.	Use Class A concrete that meets the requirements of Section 501, Structural Concrete.

6.	Coloring, Imprinting, Curing and Sealing Materials.

- Bomanite Integral Color:  The concrete shall be colored with the following integral color:  Red Clay.

- Bomacron Color Hardener:  The following Bomacron Color Hardener color shall be applied to all concrete surfaces to be imprinted and textured:  Franciscan Red.

c.	Pattern:  The following Bomacron pattern shall be used: Running Bond Brick.  All imprinting tools used in the execution of this project shall be manufactured by Bomanite Corporation.

d.	Reinforcement:  Use 6X6 W1.4XW1.4 steel welded wire fabric.

e.	Curing and densifier:  The concrete shall receive a cure treatment utilizing Bomanite Con-Shield.

f.	Sealer:  Concrete slabs shall be sealed according to the manufacturer’s recommendations using Bomanite Hydrolock.

7.	Installation Procedures.

a.	The area to receive Bomanite/Bomacron imprinted concrete shall have the sub-grade prepared and compacted according to 608-3.01 Concrete Sidewalks.

b.	Provide and install 6X6 W1.4XW1.4 steel welded wire fabric.

c.	Control joints and/or expansion joints shall be provided according to Section 608, Sidewalks and the guidelines established by the American Concrete Institute.  The Contractor shall advise the engineer to determine the best location for these joints to minimize the visibility of the joints and to minimize unsightly cracking.

d.	The concrete shall be placed and screeded to the finish grade, and floated to a uniform surface using standard finishing techniques.

e.	Bomanite Color Hardener shall be applied evenly to the troweled surface before imprinting.

f.	Bomanite Liquid Release agent shall be applied evenly to the troweled surface before imprinting.

- While the concrete is still in its plastic stage of set, the Bomanite/ Bomacron imprinting tools shall be applied to the surface.

- Bomanite Con-Shield shall be applied to Bomacron after Bomanite Liquid Release  has dissipated.

- After the initial curing period, the surface of the slab shall be sealed.

At times when the air temperature is at or near freezing, the concrete slab shall instead be cured using a suitable curing blanket, and if possible, the slab shall later be sealed with Bomanite Hydrolock when the temperature is safely above freezing.

If, at any time during the curing period, any of the forms are removed, a coat of curing compound shall be applied immediately to the exposed surface.  Additional coats shall be applied if the Engineer determines that the coverage is not adequate.  The concrete shall be cured for the minimum period of time set forth below.

Type I Portland Cement Concrete					5 days

Type III Portland High Early Strength Cement Concrete		3 days

j.	Protect sidewalk, and curb and gutter from color stains.  When directed by the Engineer, remove surface stains caused by the Contractors work to the satisfaction and approval by the Engineer.

608-4.01 METHOD OF MEASUREMENT.    Add the following:

Concrete Median. Exclusive of curb, by the square yard of finished surface, complete in place, including reinforcement.

Asphalt Pathways and Medians.  By the ton of asphalt concrete according to Section 109, Measurement and Payment.  Asphalt cement will not be measured for payment.  Additional asphalt pavement used for matching existing surfaces such as paved parking lots behind a new sidewalk/pathway will be measured and paid under this Section.  R47USC(02/01/00)

Sidewalk Type Retaining Wall.  By the cubic yard of concrete, according to Section 109.

Standard Modifications

Delete fifth paragraph beginning with: “Curb Ramp” and replace with the following:

Curb Ramp.  By each installation, complete in place, including detectable warnings, ramp runs, backing curbs, flares, and landings necessary to provide a single street level access.

E40(01/27/07)

### Special Provisions

608-5.01 BASIS OF PAYMENT.  Add the following:  Asphalt cement for Asphalt Pathway and Asphalt Pathways and Medians will not be paid for separately, but will be subsidiary to respective pay items.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.  R47USC (02/01/00)

Payment for 608(1B) Concrete Sidewalk, 4 inches thick, Stamped (Red), will be full compensation for all labor, equipment, and materials required for construction of full depth colored concrete sidewalk with the surface finished with the specified stamp pattern.

Backing curb will be subsidiary to Item 608(6), Curb Ramp and 608 (6A) Curb Ramp Retrofit.

A concrete landing will be paid for as a Curb Ramp.

The composite detectable warning tiles are subsidiary to Item 608(6), Curb Ramp. (06/11/02)R256USC

Concrete and tactile warning bumps used in the construction of curb ramps are subsidiary to item 608(6A) Retrofit Curb Ramp.

Payment for Item 608(24) Sidewalk Type Retaining Wall will be full compensation for all labor, equipment and materials required for construction of the walls, complete and in-place.  Structural excavation, temporary shoring, reinforcing steel, concrete, porous backfill, backfill, concrete stamping, and concrete finishing will not be paid for separately, but will be subsidiary to Item 608(24) Sidewalk Type Retaining Wall.

The welded wire fabric (WWF) is subsidiary to item 608(25) Concrete Median.

Add the following pay items:

| Pay Item | Pay Unit |
| --- | --- |
| 608(1B) Concrete Sidewalk, 4 inches thick, Stamped (Red) | Square Yard |
| 608(6A) Retrofit Curb Ramp | Each |
| 608(7) Asphalt Pathway | Ton |
| 608(8) Asphalt Pathways and Median | Ton |
| 608(24) Sidewalk Type Retaining Wall | Cubic Yard |
| 608(25) Concrete Median | Square Yard |

SECTION 609

CURBING

Special Provisions

609-3.01 GENERAL. Add the following after the last paragraph:  When casting curbs on top of rutted asphalt or asphalt with depressions, the tops of the curb shall be straight line in an appearance, except when crossing grade changes.

Non-conforming curbs shall be subject to rejection by the Engineer.

609-3.02 CAST-IN-PLACE CONCRETE CURBING.  Add the following to the sixth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 2 inches.  R202USC02 (11/06/02)

Add the following subsection:

609-3.06 BUMPER CURBS.  Bumper Curb shall conform to subsection 609-3.03, Precast Concrete Curb and the Plans.

609-4.01 METHOD OF MEASUREMENT.  Add the following:

Bumper Curb.  By each complete installation.

609-5.01 BASIS OF PAYMENT.  Add the following pay items:

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 609(7) Bumper Curb | Each |

# SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS.  Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit shop drawings for all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication. (11/06/02)R50USC02

Standard Modifications

615-2.01 MATERIALS.  Delete the first paragraph of Item 2, including subitems a., b., and c. and replace with:

2.	Sign Fabrication.  Use Type IV reflective sheeting (for lettering, symbols, borders, and background) on sheet aluminum panels for signs except the following:

a.	Orange Background Signs:  Use either Type II or Type III orange reflective sheeting or use Type VII or Type IX fluorescent orange reflective sheeting.  For temporary installations place reflective sheeting on sheet aluminum, plastic, or plywood panels.

Roll Up Signs: Use 3M series RS 24, Reflexite Marathon Orange, or approved equal (based on durability and reflectivity, as determined by the Engineer).  Use flexible signs with fluorescent reflective sheeting that is Type VI or better.  E41(01/27/07)

b.	Railroad Crossbucks and Vertical Crossbuck Supports: Use white Type VIII or Type IX reflective sheeting for background of sign and strips.

- Non-Illuminated Overhead Signs with White Legends on Green Backgrounds:  Use Type IX reflective sheeting for legends and background.  Create the legend in one of the following ways:

(1)	Cut border and legend from white Type IX reflective sheeting and adhere to a green Type IX background, or

(2)	Cut stencil of border and legend out of green transparent acrylic film and use transparent adhesive to overlay the film on a white Type IX reflective background.

- Fluorescent Yellow-Green School Area Signs:  Use Type VIII or Type IX reflective sheeting for background.

Add the following paragraph:

Reflective Sheeting Warranty.  Supply manufacturer’s warranty for reflective sheeting, including retention of fluorescent yellow-green (measured according to ASTM E 2301) for ten years according to the following criteria:

Minimum Fluorescent Luminance Factor 	YF: 20%

Minimum Total Luminance Factor		YT: 35%

The warranty shall stipulate that: If the sheeting fails to meet the minimum fluorescence values within the first 7 years from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, restore the sign surface to its original effectiveness.  If the reflective sheeting fails to meet the minimum fluorescence values within the 8th through the 10th year from the date of fabrication, the manufacturer shall, at the manufacturer’s expense, provide enough new replacement sign sheeting to the Department to restore the sign surface to its original effectiveness.  E26(1/1/06)

Special Provisions

615-3.01 CONSTRUCTION REQUIREMENTS.  Under item 7 add the following:

Deliver sign panels, posts, and hardware to the State Maintenance Yard at 289 Inner Springer Loop Road in Palmer, Alaska.

615-3.02 SIGN PLACEMENT AND INSTALLATION.  Add the following:  Do not remove existing signs without authorization from the Engineer.

615-5.01 BASIS OF PAYMENT.  Delete the first sentence and substitute the following:  Sign posts, bases, mounting hardware, and concrete used for sign bases are subsidiary.

Add the following:  No separate payment for keeping existing signs in service until they are no longer needed or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1) Standard Sign.

No separate payment for removal of existing sign post foundations or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1) Standard Sign.  R50USC02 (11/06/02)

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION.  Add the following:  Topsoil and seed new or disturbed slopes and other areas directed by the Engineer.  Track the soil and apply seed, mulch, fertilizer, and water.  Provide a living ground cover on slopes as soon as possible.

618-2.01 MATERIALS.  Add the following to the list of material specifications:

Mulch	subsection 727-2.01

618-3.01 SOIL PREPARATION.  Add the following:  Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes.  Cover all slopes to be seeded with topsoil according to Section 620.  Complete slope preparation as soon as topsoil is placed on the slopes.   (1/27/07) R52USC

Standard Modification

618-3.01 SOIL PREPARATION.  Delete the fourth paragraph and replace with the following:

Roughen the surface to be seeded by grooving the soil in a uniform pattern that is perpendicular to the fall of the slope.  Use one or more of the following grooving methods before the application of seed:

- Manual raking with landscaping rakes;

- Mechanical track walking with track equipment; or

- Mechanical raking with a scarifying slope board.  Form one inch wide grooves spaced no more than six inches apart.

Rounding the top and bottom of slopes to facilitate tracking or raking and to create a pleasant appearance is acceptable, but disrupting drainage flow lines is not.

618-3.02 SEEDING SEASONS.  Add the following:  Seed disturbed areas that require seeding within 14 days of the permanent cessation of ground disturbing activities in that area.

Seed between May 15 and August 15, or obtain written approval from the Engineer to seed at a different date.  E42(1/27/07)

Special Provisions

618-3.03 APPLICATION.  Add the following:  Apply seed, mulch, and fertilizer as follows per acre.  Apply seed and mulch in one application if using the hydraulic method.  Apply fertilizer with the hydraulic method.

| Component | Ingredients | Application Rate (per MSF) |
| --- | --- | --- |
| Seed | Slender Wheatgrass (Wainwright) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 1.00lbs. 0.80 lbs. 0.20 lbs. Total = 2.00 lbs |
| Soil Stabilizer Slope ≤ 3:1 Slope >3:1 | Mulch Mulch with tackifier | 46 lbs. 45-58 lbs. |
| Fertilizer | 20-20-10 | 12.0 lbs. |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright) is commercially unavailable.  If this substitution is made, apply at the same application rate.

(1/27/07) R52USC

Take extra precaution when applying the seed mixture.  Do not apply the seed mix within the planting beds.  Wash all surfaces that are over sprayed, including planting beds, asphalt, lights, signs, etc., to remove all unwanted seed within 24-hours of application.

Water and fertilizer required for application are subsidiary to the Seeding bid item.

Standard Modification

Delete subsection 618-3.04 in its entirety, and add the following new subsections:

618-3.04 MAINTENANCE AND WATERING.  Protect seeded areas against traffic by approved warning signs or barricades. Repair surfaces gullied or otherwise damaged following seeding.  Maintain seeded areas in a satisfactory condition until final acceptance of work.

Water and maintain seeded areas.  Water applied by this subsection is a paid Contract item.  If, in the opinion of the Engineer, too much water is being applied, reduce amount of water as directed.

Reseed areas not showing evidence of satisfactory growth within 3 weeks of seeding.  Bare patches of soil more than 10 square feet in area must be reseeded.  Erosion gullies over 4 inches deep must be filled and reseeded.  Fill the entire erosion gully to surrounding grade, even the portions less than 4 inches deep.

Contact ADNR for advice or corrective measures, when seeded areas are not showing evidence of satisfactory growth.  The Contractor is responsible for retracking, reseeding, refertilizing and remulching areas that do not show satisfactory growth, and those actions are subsidiary.

618-3.05 ACCEPTANCE.  During final inspection the Engineer will perform a visual inspection of seeding to determine final stabilization.  During the visual inspection each station and each side of the road will be considered a separate area.  The Engineer will accept seeding that has become a vegetative matt with 70% cover density in the inspection area.

Reseed areas that are not acceptable to the Engineer.

618-3.06 PERIOD OF ESTABLISHMENT.  Establishment periods extend for one complete growing season following acceptable seeding.  Employ possible means to preserve the new vegetative matt in a healthy and vigorous condition to ensure successful establishment.  Reseed areas that do not meet the specifications.  Watering and reseeding after the final inspection are subsidiary.

The Engineer may, but is not required to, determine the Project is complete except for the period of establishment, and issue a letter of final acceptance.  After final acceptance, work or materials due under this subsection during any remaining period of establishment are considered warranty obligations that continue to be due following final acceptance in accordance with subsection 105-1.16.  E42(1/27/07)

Standard Modification

618-4.01 METHOD OF MEASUREMENT.  After Seeding by the Pound, delete text and replace with:  By weight of dry seed acceptably seeded and maintained.  E42(1/27/07)

Add the following:  The amount of mulch, and fertilizer in this work, including any required reseeding, will be subsidiary to seeding and will not be measured separately for payment.

Standard Modification

618-5.01 BASIS OF PAYMENT.  Delete paragraphs beginning: “Seeding buy the Acre” and “Seeding by the Pound” and replace with:

Seeding by the Acre.  Payment is for established vegetative matt.  Soil preparation fertilizer, and water required for hydraulic method are subsidiary.

Seeding by the Pound.  Payment is for established vegetative matt.  Soil preparation fertilizer, and water required for hydraulic method are subsidiary.

Add new pay description:

Water for Seeding.  Water applied for growth of vegetative matt.  Water for hydraulic seeding, fertilizer or mulching is subsidiary.  Water after project completion is subsidiary.

E42(1/27/07)

Partial payments shall be made at 40% upon seeding, 30% at the end of the first growing season in which seeding is done (first season’s maintenance) and 30% upon final acceptance.

SECTION 620

TOPSOIL

# Special Provisions

620-3.01 PLACING. Add the following:  Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer.  The resultant indentations shall be perpendicular to the fall of the slope.  Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

For Landscaping areas:

Topsoil shall be evenly spread to a minimum depth of 4” after settlement on all areas to be seeded as described in Section 618.

Topsoil shall be a minimum depth of 12” after settlement on all areas to be established as Planting beds for trees or shrubs as shown on the Plans or as directed by the Engineer.

Contractor shall achieve settlement by rolling the topsoil with a water-filled drum approved by the Engineer.  The Engineer may direct that topsoil placed on slopes be track-walked perpendicular to the slope with a small track dozer.  Track walking is incidental to this bid item and no separate payment will be made.

620-4.01 METHOD OF MEASUREMENT.  Add the following:  Measurement will be by the square yard regardless of the thickness.

For Landscaping areas:

Measurement of 4”depth topsoil shall be the number of square yard units measured to the nearest unit on the ground surface and seeded. Stockpiling and re-handling of topsoil during stripping operations, or during placement shall not be measured for payment.  Topsoil for Planting beds will not be measured separately for payment and shall be considered subsidiary to Pay Items in Section 621.

620-5.01 BASIS OF PAYMENT.  Add the following:  No additional payment will be made for the work required to prepare topsoil.  Topsoil will not be paid for until spreading and compaction of topsoil is complete.

SECTION 621

## PLANTING TREES AND SHRUBS

- Special Provisions

621-1.01 DESCRIPTION.   Add the following: This work shall also include slavage of existing trees, preparation of Planting beds, and furnishing and installing shredded bark mulch as shown on Plans.

621-2.01 PLANT STOCK.  Add the following:  Refer to 621-3.03 PLANTING for provision of Certified Arborist.

A Certified Arborist or botanist shall certify that Plant species are true to type and name according to the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature.  Variety and species shall be as scheduled on the Contract Drawings.  Trees and shrubs are not to be bare root.

1.   Nursery Stock.

- Delete paragraph in its entirety and substitute the following: Container-grown Plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

Add the following:

- Coniferous trees shall not come from or have the appearance of trees from Christmas tree farms.  Coniferous trees that appear to be too heavily pruned, sheared, or that have their bottom branches removed, or that do not have acceptable root balls shall be rejected.  The Owner’s Representative shall be the sole judge of the Plant material.

621-2.03 LIMESTONE.  Add the following:  Limestone shall be applied at a rate determined by the Engineer, as described in subsection 726-1, and based on the soil analysis tests provided by the Contractor for the topsoil used for this project.

621-2.04 MULCH.   Add the following sentence:  Mulch shall be shredded bark mulch and shall be placed as shown on Plans.

All landscape beds shall be mulched for all surface areas within edging.  Individual Plantings of trees not in beds shall include mulch within the excavated area.

Add the following subsections:

Delete Section 621-2.07 TREE WOUND DRESSING. and replace with the following:

621-2.07 LANDSCAPE EDGING.  Landscape edging shall be galvanized 1/8 inch rolled steel bar 4 inch width meeting Section 716.  Grind top of edging to provide smooth, slightly rounded edges.

621-2.08  BOULDERS.  Boulders shall be of size shown on drawings.  Sectional areas shown on drawings can vary by 8 inches.  Heights can vary by 6 inches.

621-2.10  EDGING.  Edging shall be 1/8 inch rolled steel bar with stainless steel bolt and nut used to close ring.  Grind top of edging to provide smooth, slightly rounded edges.

621-2.11 EXISTING TREES TO BE SALVAGED.   The Contractor shall review and flag all trees to be salvaged in a joint meeting at the site with the Engineer.  It is the Contractors responsibility to review and assess Plant size and health before salvaging Plants.  The Contractor shall identify trees that in his opinion, may not survive being moved.  The Engineer will determine whether questionable trees are to be salvaged or replaced immediately.  Trees that can not be salvaged will be replaced with Replacement Trees.  Replacement trees shall be 3-inch caliper Canada Red (Prunus Virginia) that meet or exceed standards within these specifications.  All replacement trees shall be nursery grown.

CONSTRUCTION REQUIREMENTS

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Before final placement of all Plant materials, after Planting pits have been filled with topsoil, the Contractor shall mark with flags, or by other approved methods, the locations where trees and shrubs are to be installed as shown on the Plans to delineate the Planting areas. The Engineer before Planting shall review the marked locations for shape, size, location, and general layout for approval. The Contractor shall notify the Engineer four (4) working days before Plant location inspection.

621-3.02 ADVANCE PREPARATION AND CLEANUP. Delete the 2nd paragraph and replace with the following:  Areas that receive group Plantings shall be laid out as shown on Plans.  Contractor shall mark these areas individually with flags, or other approved methods to delineate Planting areas.  Engineer shall approve the shape, size, location and general layout of Planting areas before the work may proceed.

621-3.03 PLANTING.

1.	Plant Season.

Delete item 1.  Plant Season, and substitute the following:

1.	Plant Season.

a.	Locally grown:  When native species of locally grown trees and shrubs are furnished for the project, they shall be Planted between June 1 and September 15. Trees and shrubs shall be fully leafed-out before Planting.

- Imported and Nursery Grown: When Plants are shipped in from out-of-state, or have been container grown in a nursery for at least one year, handling shall be according to nursery recommendations.  Plants imported from out-of-state shall be Planted between May 15 and August 1.

Replace paragraphs b-d in Item 2 with the following:

2.	Excavation.

b. Trees and Shrubs shall be Planted as shown on the Plans and with excavation and pits sized accordingly.  Dig Planting holes within the Planting bed areas.

Firmly tamp the base of the Planting hole to assure Plants will not settle to lower than their proper Planting depth.

3.	Pruning.  Delete the last two sentences of paragraph (b.) in their entirety.

5.	Placing Plants.  Add the following to paragraph a.:  Trees and Shrubs shall be Planted as shown on the Plans and as directed on site by the Engineer.

Delete paragraph b and substitute the following: Balled and burlapped Plants, Plants in wire baskets or containers shall be handled by the earth ball, container, or basket and not by the Plant itself.  Wire baskets, and burlap shall be clipped and laid flat on the bottom of the Planting pit as indicated on the Plans.  Containers shall be removed from the site.  The Engineer may reject any Plants whose rootballs collapse, crack, or break during Planting

7.	Wrapping.  Delete this paragraph in its entirety, and substitute the following:

Plant materials shall not be wrapped.

8.	Staking and Guying.  Delete paragraphs a, b, and c in their entirety and add the following:  Contractor shall stake trees as shown on Plans and as directed by the Engineer.  The stakes and guys shall be maintained during construction and the establishment period to prevent damage to the trees.  All stakes and guys shall be removed at the end of the period of establishment.

Add the Following:

9.	Prepare Planting Bed.

a.	Planting beds must be completely prepared before placement of Plants.  Planting bed preparation includes excavation, loosening of sub-grade soils and placement of edging and topsoil.  Planting beds shall be prepared no more than five days before Planting.

b.	Before excavation of Planting areas, ascertain the location of all utilities so that proper precautions may be taken not to disturb or damage any subsurface improvements.  Should obstructions or conflicts be found, promptly notify the Engineer.  Prepare a revised Plan that avoids conflicts with the Utility and meets the intent of the original Plan to the extent possible.  The revised Plan shall be submitted to and approved by the Engineer before construction of the Planting bed.

c.	Excavate Planting beds for trees and shrubs to depth as shown on Plans.  Remove all excess excavated material from the site and disposed according to specifications.

d.	Once excavated, sub-grade shall not be mechanically compacted.  Heavy equipment shall not be use within Planting beds.

e.	Soak Planting beds with water.  Allow water to drain completely.  Notify the Engineer if excavated areas fail to drain.  Only place topsoil in well drained beds.  Place topsoil.  Water Planting beds to moisten topsoil.  Allow water to absorb in throughout Planting bed.  Topsoil backfill shall be moist but not wet, during Planting.  Do not Plant until topsoil has no signs of excess water including pools, puddles, inability to compact or muddiness.   Notify Engineer if Planting beds are not draining properly.

f.	Dig Planting holes within the Planting bed.  Firmly tamp the base of the Planting hole to assure Plants will not settle to lower than their proper Planting depth.  Water Planting holes before Planting if soil appears dry or if Planting bed has not been Planted within 24 hours of initial watering.

10.	Quality Control.  Do not install Plants that do not meet standards, remove all Plants deemed unacceptable from the site.  The Contractor is responsible for quality control.  However the Engineer will monitor quality control efforts and may:

  - inspect Plant materials before installation;

  - be on-site to approve Planting conditions and be present for initial Planting; and

  - inspect Plants during the season.

The Contractor shall inspect Plants before installation to assure they meet the requirements under this section including that they meet ANSI, are disease free, free of wounds, broken branches, missing or double leaders, co-dominant trunks or other defects.

The Department may, at is discretion, retain the services of an arborist certified by the International Society of Arboriculture or American Nursery and Landscape Association.  If pruning is required, the Engineer will notify the Contractor and pruning will be accomplished under the direct supervision of the certified arborist or others as designated by the Engineer.

Provide the Engineer with four working days advance written notification of all proposed work so the Engineer or Arborist can review all Plant materials and their installation.  The arborist will report directly to the Engineer.  The Engineer will notify the Contractor of any deficiencies noted.  The Contractor will remain responsible for the acceptability and continued health of Plant materials regardless of the presence or absence of the Engineer or arborist.

11.	Certified Arborist.  The Contractor shall retain the services of an arborist certified by the International Society of Arboriculture or the American Association of Nurserymen whose experience and qualifications are acceptable to the Engineer.  The arborist’s resume detailing current certifications, memberships in industry organizations, work experience in the industry and references shall be submitted at least 10 calendar days before the delivery of Plant material.  The certified arborist shall oversee quality assurance of trees, their installation and shall inspect trees for health and vigor.  Specifically, the arborist shall carry out the following:

The certified arborist shall inspect Plants for health and vigor before installation, to assure the requirements of Section 621-2.01 for Plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected before installation.  The certified arborist shall also be responsible for the following:

  - Inspect the tree Planting process to assure that Planting techniques meet the specifications of the Contract documents and match standard industry practices.

  - Inspect the Plantings after installation is complete to assure that they are ready to be accepted by the Engineer and ready for the maintenance schedule to begin.

  - Inspect Plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.

  - After acceptance, the arborist shall inspect the trees at least twice during the growing season each year of the Plant Establishment period for any needed maintenance, such as watering, pruning, removal of dead, dying or untreatable diseased trees.

12.	Boulders.  Locations for boulders shall be overexcavated and backfilled with native material to set boulders to achieve arrangements shown on drawings.  Ensure no gaps below springline.  Boulders should be placed so that no more than ½ of the boulder is exposed and no less than 1/3 of the boulder is exposed.

13.	Edging.  Beds shall be edged as shown on the Drawings.  Anchor per manufacturer’s instructions with a minimum of stakes at 3’ O.C.

621-3.04 PERIOD OF ESTABLISHMENT.  Delete the last sentence and substitute the following:  The Plant Establishment Period (PEP) shall be one complete growing season.  The growing season is May 1st  to October 15th.  The PEP shall begin when the maintenance schedule is approved by the Engineer and all required Planting is complete and accepted for payment by the Engineer.  The PEP applies to all Planting beds, trees and shrubs.

Watering is not required between October 15 and May 1st during the PEP.  The Contractor shall deep water all tree root balls and other Plant materials as frequently as necessary to keep the immediate root areas moist at all times during the growing season.   The Contractor shall deep water all evergreen Plants just before freeze-up in order to minimize over-wintering desiccation.  Contractor may also choose to apply anti-desiccants to conifers as approved by the Engineer. Rainfall will not be considered a substitute for deep watering unless permitted by the Engineer.

Trees and shrubs shall be pruned to remove disfigured, damaged, or dead branches.  Damaged trees or those that constitute health or safety hazards shall be pruned at any time of the year as required.  Evergreen trees shall not be pruned without prior approval of the Engineer.

Maintain the Planting beds and grass areas in a weed-free condition.  Weed removal shall be a routine maintenance activity.  Weeds include grasses and other undesirable Plants within Planting beds.

621-3.05 CLEANUP.  Add the following:  Planted and seeded areas shall be kept clean of litter and garbage during the growing season.

621-3.06  PLANT REPLACEMENTS.  Add the following:  Plants shall be replaced following the same details and specifications as used in the original Contract Documents.  Plants that are dead or dying, shall be replaced within 48 hours of notification, June through September.  Plants dead at the end of the growing season shall be replaced at the beginning of the following season.

If Plants are not replaced as required, the Engineer may replace or have replaced the damaged items, and deduct the cost of said repair or replacement from remaining payments.

621-3.07 MAINTENANCE.  Add the following:  The maintenance period for this project for all Plantings, Plant materials, and related items shall be one year.  The maintenance period for seeding is covered under Section 618 Seeding.

The Contractor shall submit a maintenance schedule to the Engineer for approval, ten working days before Plant installation.

Maintenance includes the care of all trees, shrubs, and seeded areas for the duration of the maintenance agreements, including the period of establishment, and the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of Planted areas.  At the end of the growing season, and at the end of the Plant establishment period, the Engineer and the Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of Plantings. Once established, seeded areas shall not be mowed.

1.	Watering.  Deep-water the root balls of all trees and shrubs.  Deep watering shall provide water penetration through the root zone to a depth of the Planting pits with a minimum of runoff.  Rain will not be considered as a substitute for deep watering unless permitted by the Engineer.  Deep water all evergreen Plants just before freeze-up in order to minimize over-winter desiccation.  Apply anti-desiccants to conifers as approved by the Engineer.  Application shall occur while the Engineer is present.  Notify the Engineer in writing four days before application of anti-desiccants.  Written notice shall state the specific date and time of application.

2.	Disease Control.  Apply pesticides, insecticides, or other disease-control methods as necessary to maintain Plant health.  Permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation must be obtained before the application of any regulated products.

3.	Pruning.  Prune all Plant materials, with appropriate pruning techniques, to remove dead or dying wood and to improve the shape and or vigor of the Plants.  Cuts shall not be painted. Pruning of flowering trees shall be scheduled to occur right after flowers drop off or decay.  Damaged trees or those that constitute health or safety hazards shall be pruned as directed by the Engineer at any time of the year.  Evergreens are not to be pruned without the approval of the Engineer.

4.	Fertilizer.  Fertilizer shall be applied to all trees, shrubs, and ground covers in the spring of the following year, before June 15 at the rates shown in Table 621-1.  The fertilizer shall be applied as per manufacturer’s recommendations and thoroughly watered into the ground.   Notify the Engineer in writing 4 working days before applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

TABLE 621-1

MAINTENANCE FERTILIZER SCHEDULE

Plant Type			Fertilizer		Application Rate

Coniferous Trees		16-16-16	4 lbs. for each 3-inch caliper

Deciduous Trees		8-32-16	1 lbs. for each 1-inch caliper

Shrubs and Ground Cover	16-16-16	15 lbs. per 1000 square feet

5.	Weeding.  Keep all Planting beds in a weed free condition during Planting and throughout the PEP.  Weeding shall be accomplished on a weekly basis and as requested by the engineer.  Weeding shall begin immediately after each Plant is installed and continue through the PEP.  Weeds include grasses and other undesirable Plants with Planting beds.

Add the following sub-section:

621-3.08   PLANT SALVAGE.  Plants to be salvaged are shown on Plans.  Salvage includes the assessment, digging, wrapping and moving designated trees to an off-site location in such a manner that trees will be rePlanted by others.  Salvaged trees that can not be moved, are determined unhealthy, or are damaged in the process of transPlanting shall be replaced with Replacement Trees.  Replacement Trees are subsidiary to Salvage Trees and will not be paid for separately.

1.	Digging Salvaged Trees.

- Trees shall be salvaged before beginning of construction within all work areas.

- Trees shall be transported to the City of Wasilla Public Works yard locaed at 191 E. Centaur Avenue.

- Trees shall be transported within the same day they are dug.

- The Contractor and the Engineer shall meet at site to identify Plants that may not survive transPlanting or whose appearance may not be acceptable before any digging of Plants.  Plants to be disposed of instead of transPlanted will be flagged in the field by the Engineer and the Contractor.  The Engineer shall have the final word on Plants to be disposed.

- TransPlanted trees shall be given B-1 transPlanting solution following delivery.  Proof of application will be the responsibility of the Contractor.

- Trees shall be dug with a rootball size as per ANSI.  Immediately following digging trees shall be balled and burlapped following standard and accepted nursery practice.

2.	Replacement Trees.

- Trees that the Engineer determines can not be transPlanted or trees whose  rootballs break during digging or delivery process, trees with damaged branches or  trunks, or trees that are not likely to survive transPlanting shall be replaced by the Contractor.

- Replacement Trees shall be delivered to the above address within seven days of tree salvage operation.

- Replacement trees shall be reviewed and inspected by the Engineer before acceptance.

3.	Acceptance of Salvaged Trees.

- The Engineer shall accept healthy salvaged trees at the location noted above within 24 hours of their transport.  Any trees that are not accepted shall be replaced by the Contractor.

- The Contractor is not responsible for maintenance of Salvaged or Replacement Trees once they have been accepted at the delivery site.

621-4.01 METHOD OF MEASUREMENT. Delete this subsection and substitute the following:

The quantity of trees and shrubs to be paid for shall be the actual number of Plants, alive and healthy at the time of final inspection and in the case of dormant willow Plantings the number of live twigs Planted and as accepted by the Engineer.

Plant Establishment Period will not be measured.

Upon the written approval of the Engineer for the Landscape Inspection, a 70% payment for installation of all landscape work shall be made upon the Contractor’s application for partial payment.  Final payment shall be made upon the Engineer’s written approval of the Final Maintenance Acceptance Inspection.

Furnishing and installing shredded bark, topsoil backfill mix, staking and guying, arborist review, fertilizing, disposal of unsuitable and surplus material, the maintenance period, the water for maintenance of Plant materials, and all work required during the one full growing season period of establishment will be subsidiary.  Water for seeding is covered under Section 618.

Item 621(5) Salvage Tree shall be measured by each tree successfully moved from its initial site to the off-site location or that has been replaced as required.  Replacement Trees will not be paid for separately, but will be subsidiary to Item 621 (5).

Landscape edging will be measured by the linear foot installed with no additional payment for overlaps.  Mulch will not be measured.

621-5.01 BASIS OF PAYMENT.  Delete second sentence and Add the following:  The accepted quantity of all Plant materials Planted will be paid for at up to 70% of the Contract price, per unit of measurement, for Pay Items 621 (1-5) at the time of acceptance.  Payment of the remaining 30% will be made after the Final Maintenance Acceptance Inspection has been conducted at the end of the Plant Establishment Period.

The accepted quantities will be paid for at the contract price, per unit of measurement, for all labor material and equipment required to furnish and install the pay items listed below and appearing in the bid schedule.

If damaged Plants are not replaced as required within 48 hours of written notice, the Engineer may replace or have replaced the damaged items and deduct the cost of said repair or replacement work from remaining payments.  The cost of said repair or replacement work will be based on paid receipts plus 10% administrative markup.

Add the following:  Caliper shall be as measured at 48 inches above the ground (diameter at breast height).  Measurement of edging shall not include overlap.  Boulders used in Rest Area construction will be measured as explained in Section 622 Rest Area Facilities.

Add the following pay items:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 621 (1A) Tree, Paper Birch | Each |
| 621(1B) Tree, European Mountain Ash | Each |
| 621(1C) Tree, Canada, Red Chokecherry | Each |
| 621(1D) Tree, Amur Chokecherry | Each |
| 621(1E) Tree, White Spruce | Each |
| 621(1F) Tree, Canada Red (Prunus virginiana), 2-inch caliper | Each |
| 621(1G) Tree, Chokecherry (Prunus mackii), 2-inch caliper | Each |
| 621(1H) Tree, Spruce- White (Picea glauca), 5-feet tall | Each |
| 621 (2A) Shrub, Mugo Pine | Each |
| 621 (2B) Shrub, Gold-Leaf Rose | Each |
| 621 (2C) Shrub, Goldflame Spirea | Each |
| 621 (2D) Shrub, False Spirea | Each |
| 621 (2E) Shrub, Red-Barked Dogwood | Each |
| 621 (2F) Shrub, Highbush Cranberry (Viburnum opulis), 36-inch tall | Each |
| 621(5) Perennials, Type | Each |
| 621(6) Landscape Edging | Linear Foot |
| 621(7) Mulch Mulch | Lump Sum |
| 621(8) Salvage Tree | Each |

SECTION 622

REST AREA FACILITIES

Special Provisions

622-1.01 DESCRIPTION.  Add the following:  This work also includes the installation of all work associated with the rest area shown on the Drawings at the intersection of the Parks Highway and Tommy Moe Drive, including the following:

1.	Benches

2.	Boulders

3.	Banner Posts

4.	Banners

5.	Boundary Fence

6.	Concrete Pavement

7.	Patterns imprinted into concrete pavement

- 622-2.10 CONCRETE.  Add the following:  Animal track imprints shall be from templates furnished by the Engineer. Contractor to provide a test panel for approval before beginning installation into the Project.  Stain for imprints shall be “Brickform Acid Stain” or approved equal.

Add the following:

622-2.13 BENCHES:  Landscape Forms “Arcata Backed Bench with Arms” (surface mount, silver powdercoat, Polysite seat ) or approved equal.

622-2.14 BOULDERS:  See Section 621, Planting Trees and Shrubs

622-2.15 DECORATIVE FENCE:  See Section 607, Fences

- 622-2.16 BANNERS:  Banners shall be manufactured of rip-stop nylon, patterns to be provided by the Engineer.

- 622-2.17 TRASH RECEPTACLE:  Trash receptacle shall be “Landscape Forms Petoskey Hinged Lid, 30 gallon,” or approved equal, powdercoated metal finish.

- 622-3.08 CONCRETE IMPRINTS: Concrete imprints shall be achieved by sandblasting the imprints from templates that will be provided to the Contractor by the Engineer.  Imprints shall be approximately ¼ inch deep and shall be stained with the colors noted on Plans.

    - METHOD OF MEASUREMENT.  Add the following:  The Rest Area shall be measured lump sum and shall include all work associated with the rest area, excluding Plantings.  This includes but is not limited to concrete, concrete imprints, benches, trash receptacles, boulders, banners, banner posts, and decorative fence.  Plantings will be measured separately as explained in Section 621, Planting Trees and Shrubs.

SECTION 627

WATER SYSTEM

Special Provisions

627-1.01 DESCRIPTION. Add the following to the first paragraph:  In conjunction with working around and/or adjusting the water valve boxes, the Contractor shall exercise due care. Before beginning of work by the Contractor, the City of Wasilla, the Engineer, and the Contractor shall determine the condition and location of the existing valves and valve boxes.  The City of Wasilla, at no cost to the project shall correct any deficiencies found.  Failure to participate in the inspection by the Contractor will result in his forfeiting all rights to deny damages at a later date during the course of the work.  A fifteen (15) calendar day written notice will be provided to the City of Wasilla when a date for the pre-inspection has been set.  Contact the City of Wasilla, Department of Public Works at (907) 373-9010 to coordinate the actual field work.  The Contractor shall furnish a copy of the written notice to the Engineer. The Contractor shall provide all traffic control for the inspection of utilities.

It shall be the Contractor's responsibility to protect and maintain all valves and valve boxes in an operable condition during all phases of construction. If at any time after the inspection as outlined above, and before final acceptance, the Water Utility finds a valve or valve box damaged or rendered inoperable, the Contractor shall repair it at his own expense.  The Contractor forfeit all right to deny damages done by the Contractor or the Contractors agents during the course of work if the Contractor fails to participate in both inspections.

SECTION 635

INSULATION BOARD

635-4.01 METHOD OF MEASUREMENT.  Delete this subsection in its entirety and substitute the following:  By the square foot of insulation board, 4” thick, in its final position, complete and accepted.

Sand blanket material is subsidiary.  R57USC (08/23/00)

635-5.01 BASIS OF PAYMENT.  Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 635(2) Insulation Board (R = 4.5/inch) | Square Foot |

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION.  Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS.  Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION.  Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT.  By the number of driveways and approaches constructed as shown on the Plans or as directed.  Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule.  The contract unit price for driveways and approaches shall be full compensation for furnishing equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.  R58M98(05/09/02)

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. Plan, provide, inspect, and maintain control of erosion, sedimentation, water pollution, and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. Common BMP can be found on the EPA website: National Menu of Storm Water Best Management Practices.  [www.epa.gov/npdes/stormwater/menuofbmps]

- ESCP (Erosion and Sediment Control Plan). The ESCP is a project-specific document that illustrates measures to control erosion and sediment problems on a project.  The ESCP normally consists of a general narrative and a map or site plan.  It is developed by the Department and included in the project plans and specifications.  It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization.  A point in time when ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional.  The stabilized site is protected from erosive forces of raindrop impact and water flow.  Typically,  unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- eNOT. Electronic Notice of Termination of coverage under the NPDES General Permit. Use EPA Form 3510-13 found at www.epa.gov/npdes/stormwater/cgp

- NPDES General Permit. The Storm Water General Permit for Large and Small Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires an approved SWPPP and NOIs listed as active status by the EPA before ground-disturbing activities for the project

- SPCC Plan (Spill Prevention, Control and Countermeasure). The Contractor’s detailed plan for oil spill prevention and control measures, that meets the requirements of 40 CFR 112.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 REFERENCES.

The following websites have up to date information about erosion, sediment and pollution control.

Developing your SWPPP.  EPA.  January 2007.  Includes a SWPPP template in WORD

[www.epa.gov/npdes/swpppguide]

National Menu of Storm Water Best Management Practices.  EPA.

[www.epa.gov/npdes/stormwater/menuofbmps]

International Erosion Control Association website [www.ieca.org/Resources/Resources.asp]

Construction Industry Compliance Assistance Center website

[www.CICAcenter.org/bmps.html]

641-1.04 SUBMITTALS. For all projects submit two copies each of your SWPPP and HMCP to the Engineer for approval. Submit one copy of your SPCC Plan (if required under Subsection 641-2.03) to the Engineer. Sign all submittals. Deliver these documents to the Engineer.

The Department will review the SWPPP and HMCP submittals within 14 calendar days. Submittals will be returned to you as either requiring modification, or as approved by the Department. The approved SWPPP must contain all certifications, and be signed in accordance with the Standard Permit Conditions of the NPDES General Permit. You must receive an approved SWPPP before you submit your eNOI to the EPA.

For projects that disturb five acres or more of ground, submit a copy of your approved and signed SWPPP, with the required permit fee to the Alaska Department of Environmental Conservation (ADEC) Storm Water Coordinator. Transmit proof of this submission to the Engineer.

For projects that disturb one acre or more, submit your signed eNOI to EPA. Submit copies of your signed eNOI receipt to the Engineer and to ADEC. Transmit proof of your ADEC submission to the Engineer. The Department will transmit the Department’s NOI to the EPA. Allow adequate time for state and federal processing, prior to commencing ground-disturbing activities.

The active status NOIs, approved SWPPP, approved HMCP, and submitted SPCC Plan (when required) become the basis of the work required for the project’s erosion, sediment, and pollution control.

Submit your signed eNOT to EPA with a copy to the Engineer when notified by the Engineer that the Project is stabilized. The Department will transmit the Department’s eNOT to the EPA.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Prepare a Storm Water Pollution Prevention Plan for all projects. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMPs. The SWPPP Preparer must visit the project site prior to preparing the SWPPP. The plan must include both erosion control and sediment control measures.  The plan must address first preventing erosion, then minimizing erosion, and finally trapping sediment before it leaves the project site.

Your SWPPP must follow the format presented in Appendix A of Developing Your Storm Water Pollution Prevention Plan  (EPA, January 2007) found at www.epa.gov.npdes/swpppguide

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the project permits.

Specify the line of authority and designate your field representative for implementing SWPPP compliance.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where storage, fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of oil, petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup, and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-2.03 SPILL PREVENTION, CONTROL AND COUNTERMEASURE (SPCC) PLAN REQUIREMENTS.

Control

Prepare and implement a SPCC Plan that is certified by a licensed Professional Engineer, when required by 40 CFR 112, including:

- When oil spills may reach navigable waters; and

- Your total above ground oil storage capacity is greater than 1,320 gallons.

Prevention and Countermeasures

Comply with 40 CFR 112 and address the following issues in your SPCC Plan:

- Operating procedures that prevent oil spills;

- Control measures installed to prevent a spill from reaching navigable waters; and

- Countermeasures to contain, clean up, and mitigate the effects of an oil spill.

641-3.01 CONSTRUCTION REQUIREMENTS. On projects with 1 acre or more of ground disturbing activity, do not begin construction activities until the EPA has acknowledged receipt of your NOI and Department’s NOI, and has listed both of them as active status. The EPA will post the status of the NOIs on the EPA website. On projects with less than 1 acre of ground disturbing activity, where submittal of an eNOI to EPA is not required, do not begin construction activities until authorized by the Engineer.

Postings

Post at the construction site:

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	Name and phone number of your local contact person, and

3.	Location of a SWPPP available for viewing by the public.

The above notices must be posted at publicly accessible locations. At a minimum post notices at the BOP, EOP, near the intersection of the highway with any major side street, and the Project Office.

Comply with requirements of the approved HMCP, the submitted SPCC Plan, and state and federal regulations that pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances.  Contain, clean up, and dispose of discharges of petroleum products and other materials hazardous to the land, air, water, and organic life forms.  Perform fueling operations in a safe and environmentally responsible manner.  Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control. Report oil spills as required by federal, state and local law, and as described in the SPCC Plan.

Comply with requirements of the NPDES General Permit, implement temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.  Maintain l temporary and permanent erosion and sediment control measures in effective operating condition.

Coordinate BMPs with all Utility Companies doing work in the project area.

Inspections

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections.  Prior to start of construction, conduct a joint on-site inspection with the Engineer, the SWPPP Preparer, and the Contractor’s field representative to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every seven days and within 24 hours of the end of a storm exceeding ½ inch in 24 hours (as recorded at or near the project site):

(1)	Disturbed areas that have not been finally stabilized

(2)	Areas used for storage of erodible materials that are exposed to precipitation

(3)	Sediment and erosion control measures

(4)	Locations where vehicles enter or exit the site

(5)	Offsite materials sources and waste sites

(6) Staging and equipment storage areas.

b.	During construction, the SWPPP preparer shall review the Project Site, Materials Sites, Waste Sites, and the SWPPP for conformance with the NPDES General Permit at least once per month and after every major change in earth disturbing activities for compliance with the General Permit.

c.	Before winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

d.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections.  During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 1/2 inch or greater. The Engineer may waive monthly inspection requirements until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports.  Prepare and submit, within three working days of each inspection, a report on the DOT&PF SWPPP Inspection Report Form (February 2007) on state Form 25D-100, with the following.  At a minimum the report will contain the following information:

a.	A summary of the scope of the inspection

b.	Name(s) of personnel making the inspection

c.	The date of the inspection

d.	Observations relating to the implementation of the SWPPP

e.	Any actions taken as the result of the inspection

f.	Incidents of non-compliance

Where a report does not identify any incidents of non-compliance, certify that the facility is in compliance with the SWPPP and NPDES General Permit. The Contractor and the Engineer will sign the report according to the Standard Permit Conditions of the NPDES General Permit.  Include reports as an appendix to the SWPPP.

Record Retention

Keep the SWPPP up to date at all times. The SWPPP shall denote the location, date of installation, date maintenance was performed, and the date of removal for all BMPs. It shall also contain copies of all inspection reports and amendments.

Maintain the following records as part of the SWPPP:

1.	Dates when major grading activities occur;

2.	Dates when construction activities temporarily or permanently cease on a portion of the site; and

3.	Dates when stabilization measures are initiated.

4.	Daily precipitation as measured from an on-site rain gauge.

Provide the Engineer with copies of all SWPPP revisions, updates, records, and inspection reports at least weekly.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least three years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Amendments

Submit amendments to the SWPPP to correct problems identified as a result of:

1.	Storm or other circumstance that threatens water quality, and

2.	Inspection that identifies existing or potential problems.

Submit SWPPP amendments to the Engineer within seven days following the storm or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within seven days.

Stabilize all areas disturbed after the seeding deadline within seven days of the temporary or permanent cessation of ground-disturbing activities.

Notice of Termination

For projects that disturb one acre or more of land, submit your signed eNOT to EPA with a copy to the Engineer when the Engineer notifies you that:

1.	The Project site (including all material sources, disposal sites, etc.) has been finally stabilized and that all storm water discharges from construction activities authorized by this permit have ceased, or

2.	The construction activity operator (as defined in the NPDES General Permit) has changed.

641-4.01 METHOD OF MEASUREMENT. Section 109 and as follows:

Items 641(2) and (4) will be measured as specified in the contract or directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1), (2), and (5) or items 641(1), (3), (4), and (5).

- Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum           price for administration of all work under this Section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

- Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract or as provided in the Directive authorizing the work to install and maintain temporary erosion, sedimentation, and pollution control measures.

- Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain all temporary erosion, sedimentation, and pollution control measures required to complete the project per plan and in accordance with the BMP, the ESCP and the original approved SWPPP and HMCP.

- Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item will be shown as amendments to the original approved SWPPP or HMCP.

- Item 641(5) Erosion and Pollution Control Price Adjustment. The total value of this contract will be adjusted as specified in Subsection 641-3.01. In addition, a price adjustment equivalent to any penalties levied against the Department by the EPA or any other state and/or federal agencies for violations of the Clean Water Act and the NPDES General Permit will be made if the Department is issued a Notice of Violation (NOV) by these agencies. This price adjustment shall be the actual cost of any fines levied against the Department. An amount equal to the maximum fine for the violation will be withheld temporarily until the actual cost of the fine is known. The difference, excluding any price adjustments will be released by the Engineer upon satisfactory completion of the requirements of the NPDES General Permit.  You are responsible for the payment of your own fines.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Work that is paid for directly or indirectly under other pay items will not be measured and paid for under this Section, including but not limited to dewatering, shoring, bailing, installation and removal of temporary work pads, temporary accesses, temporary drainage pipes and structures, diversion channels, etc.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.

Payment will be made under:

| PAY ITEM | PAY UNIT |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |
| 641(3) Temporary Erosion and Pollution Control | Lump Sum |
| 641(4) Temporary Erosion and Pollution Control Amendments | Contingent Sum |
| 641(5) Erosion and Pollution Control Price Adjustment | Contingent Sum |

SECTION 642

CONSTRUCTION SURVEYING & MONUMENTS

Special Provisions

642-1.01 DESCRIPTION.  Delete the sentences that begin "Furnish and install..." and "Adjust existing monuments..."

642-3.01 GENERAL.  Delete the text of item 9.

Delete item 10 and substitute the following:

- Cross sections at retaining wall locations.  Provide the Engineer cross section data, taken at 25 foot intervals, 10 days before ordering retaining wall materials.  The Engineer will verify the Plan quantity and make any necessary adjustments to the wall size, design, or configuration.

- Other surveying and staking necessary to complete the project.

R255USC (11/18/02)

642-3.02 CROSS SECTION SURVEYS.  Delete the text of item 13.

642-3.03 MONUMENTS.  Delete the entire subsection.

Standard Modification

642-3.04 OFFICE ENGINEERING. Delete third sentence and replace with: Perform the work by, or under the responsible charge of, a person registered in the State of Alaska as a Professional Land Surveyor or a Professional Engineer.  E53(5/01/07)

642-3.05 FINAL TRAVERSE.  Delete the entire subsection.

SECTION 643

TRAFFIC MAINTENANCE

Special Provisions

643-1.03 TRAFFIC CONTROL PLAN.  Replace the last paragraph with the following: A waiver may requested of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project in writing.  If the waiver is approved, movements of oversize and overweight vehicles in or near traffic within the project limits will be done according to the provisions of an approved Traffic Control Plan.  Maintain a minimum12-foot lateral separation between the nonstreet legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.

Add the following:  The Contractor shall coordinate with the ARRC to ensure the TCP addresses temporary disconnects and reconnecting the pre-emption system.

Standard Modifications

643-2.01 MATERIALS.  Under Item 16. Flagger Paddles, delete the last sentence with the following:  Use reflective sheeting that meets AASHTO M 268 Type VIII or IX.  Use background colors of fluorescent orange on one side and red on the other side.

E56(5/01/07)

Special Provisions

643-2.01 MATERIALS.  Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.  (12/14/06)R222USC04

Special Provision

Add the following subsection:

643-2.02 WEBSITE SUBMITTAL. Submit a proposed web site design at least 5 working days before the preconstruction conference, for the Engineer's approval.  Following the Engineer's review, if revisions to the Plan are required, do so promptly. The web site must be active within 30 days of the Notice to Proceed.  Meet the requirements set forth below.

Standard Modification

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Immediately notify the Engineer of a traffic related accident that occurs within the project limits as soon as you, an employee, or a subcontractor become aware of the accident.  E56(5/01/07)

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS.  Add the following:  Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity.

Maintain business accesses during flagging operations.

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  Add the following:  Contractor will be allowed to maintain traffic on a milled surface for a maximum of seven days.

Standard Modification

643-3.04 TRAFFIC CONTROL DEVICES.

In the sixth paragraph and also in Item 4.b., delete: “ATTSA” and replace with ATSSA (American Traffic Safety Services Association).

E56(5/01/07)

Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.

Delete the first sentence of the eighth paragraph and substitute the following: Items paid under this Section remain the Contractor’s property unless stated otherwise.

Add the following to item 1. Embankments.:  Close trenches and excavations at the end of each continuous work shift.

Add the following to item 3. Fixed Objects.:  Remove obstructions greater than 4 inches above the nominal foreslope grade at the end of each continuous work shift.

Delete item 4.b. and replace with the following:  Flagger Certification by ATSSA

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where the Contractor’s operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT &PF Maintenance and Operations’ district office, or as directed by the Engineer. (12/14/06)R222USC04

643-3.05 AUTHORITY OF THE ENGINEER.  Replace the first sentence with the following:  When existing conditions adversely affect the public’s safety or convenience, the Contractor will receive an oral notice.  A written notice will follow the oral notice according to subsection 105-1.01 Authority of the Engineer.

Add the following after the second sentence:  In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT.  Add the following:  Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

# CRUSEY STREET ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-5,000 | $30 |
| 5,001+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING.  Delete the last sentence and substitute the following:  Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

# Lane Restrictions

1. 	No lane restrictions between 0530 to 2000 hrs daily, except as

otherwise allowed herein.

2. 	No lane restrictions around any Holiday:

- If a holiday falls on Sunday, Monday, or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day of the holiday.

- If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

- If a holiday falls on a Thursday, Friday, or Saturday, the above stipulations apply from 1200 on the day of the holiday to 0300 on the Monday after the holiday.

3. During the weekends of the Alaska State Fair

# Signalized Intersections

Do not impede traffic in more than one intersection at a time, except as otherwise allowed herein.

# Weekend Closures

The Contractor will be allowed one weekend closure for the intersection of Crusey Street/Westpoint Drive

The Contractor will be allowed two weekend closures for each of the intersections of Bogart Street /Crusey Street and Lucille Street /Nelson Street .

Complete all electrical, storm drain, and bottom lift asphalt concrete during the weekend closures.

Weekend closure shall be from Friday at 2000 hrs to Monday at 0530 hrs.

The Contractor shall provide a minimum of three weeks advance notification of a proposed intersection closure to the Engineer.  In the event that scheduled intersection closure does not occurred, all cost incurred by the Department for public notification shall be born by the Contractor.

# Segment Closures

# PARKS HWY

Parks Hwy Station 401+50 to Station 408+00 will be allowed to operate one time in a two way traffic operation, from 2200hrs Sunday to 1400hrs the following Friday to complete the work.

## A minimum of two 12 foot lanes with two 4 foot shoulders shall be provided at all times.

All excavation, backfill, and bottom lift asphalt concrete shall be completed during the segment closure.

# CRUSEY STREET

Phase One, a full closure of Crusey Street, between Westpoint Drive and USA Circle, will be allowed for 5 calendar days.

Phase Two, a full closure of Crusey Street, between USA Circle and Bogard Road, will be allowed for a 10 calendar days.

Phase one and Phase two shall not be closed concurrently.

No closures of Crusey Street will be allowed while School is in session.

# SCHOOL BUS COORDINATION PLAN

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This Plan shall be submitted as a TCP, to the Engineer for approval before implementation of the school bus Plan.

643-3.09 INTERIM PAVEMENT MARKINGS.  In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Apply final pavement markings according to subsection 670-3.01, Construction Requirements of these Special Provisions.  (02/10/06)R222USC04

Add the following subsection:

643-3.10 LIGHTING OF NIGHT WORK

Illuminate the night work areas specified in Table 643-2 to the light levels specified.

Table 643-2 does not provide a comprehensive list of operations that require lighting.  Provide lighting for other operations when necessary.

| Table 643-2 Night Work Illumination Level and Area of Coverage |  |
| --- | --- |
| Type of Work or Equipment | Lighting Configuration |
| Paving, Milling, Striping, Pavement Marking Removal, Rumble Strip Installation | At least 2 machine mounted balloon lights with a cumulative wattage of at least 4000 watts. Provide additional lights or wattage if necessary to provide complete coverage. |
| Rolling, pavement sweeping | At least 4 sealed beam halogen lamps in the front and four in the back. Each should be at least 55 watts. |
| Flagging | Two balloon lights of at least 2000 watts each located within 30 feet of the normal flagger location. Locate one on the right side of the road beyond the flagger and the other on the left side of the road in front of the flagger. |
| Truck Crossings (meaning where haul vehicles cross or enter a road): 1) with roads with ADTs over 10,000 or 2) that are controlled by portable traffic signals or flaggers | Two balloon lights of at least 2000 watts each, located on the main road, one on the far right side of the intersection, the other on the near left. Locate lights within 30 feet of the edges of the side street. If there is a flagger at the crossing, locate the lights to also meet the requirements for flagging. |

Use balloon lighting as the main light sources.  Do not use floodlights without approval by the Engineer.  When approved, install floodlighting in a manner that minimizes glare for motorists, workers, and residents living along the roadway.  Locate, aim, louver, and/or shield light sources to achieve this goal.

The Engineer shall be the sole judge of when glare is unacceptable, either for traffic or for adjoining residences.  When notified of unacceptable glare, modify the lighting system to eliminate it.

If the Contractor fails to provide required lighting equipment or provides lighting that creates unacceptable glare at any time, the Contractor shall cease the operation that requires illumination until the condition is corrected.

Lighting equipment shall be in good operating condition and comply with applicable OSHA, NEC, and NEMA codes.

Provide suitable brackets and hardware to mount lighting fixtures and generators on machines and equipment.  Design mountings so lights can be aimed and positioned as necessary to reduce glare.  Locate mounting brackets and fixtures so they don’t interfere with the equipment operator or overhead structures.  Connect fixtures securely in a manner that minimizes vibration.

Ensure ground, trailer, and equipment mounted light towers or poles are sturdy and freestanding without the aid of guy wires.  Towers shall be capable of being moved as necessary to keep pace with the construction operation.  Position ground and trailer mounted towers and trailers to minimize the risk of being impacted by traffic on the roadway or by construction traffic or equipment.

Raise trailer or equipment mounted lights to maximum height, except do not exceed the clearance required for overhead objects such as overhead signals, overhead signs, trees, aerial utilities, or bridges.  Aim and adjust lights to provide the required light levels. Provide uniform illumination on the hopper, auger, and screed areas of pavers.  Illuminate the operator’s controls on machines uniformly.

Furnish each side of nonstreet legal equipment with a minimum of 75 square inches high intensity retroreflective sheeting in each corner, so at least 150 square inches of sheeting is visible from each direction.  Provide red sheeting on the rear of the equipment and yellow sheeting elsewhere.

Existing street and highway lighting and conventional vehicle headlights do not eliminate the need for the Contractor to provide lighting meeting the requirements of Table 643-2.

Provide sufficient fuel, spare lamps, spare generators, and qualified personnel to ensure that required lights operate continuously during nighttime operations.  Ensure generators have fuel tanks of sufficient capacity to permit operation of the lighting system for a minimum of 12 hours.  In the event of a failure of the lighting system, discontinue the operation that requires illumination until the required level and quality of illumination is restored.

Maintain a supply of at least twenty emergency flares for use in the event of emergency or unanticipated situations.  Comply with local noise ordinances.

Install post mounted electroliers located within the clear zone, on NCHRP 350 compliant breakaway bases.

Standard Modifications

- Add the following new subsection:

643-3.11 HIGH VISIBILITY GARMENTS.  Ensure all workers within project limits wear outer garments that are highly visible and comply with the following requirements:

- Standards.

Use high visibility garments conforming to the requirements of ANSI/ISEA 107-2004, Class 2 for tops or Class E for bottoms, and Level 2 retroreflective material.

- Labeling.

Use garments labeled in conformance with Section 11.2 of ANSI/ISEA 107-2004; except you may use previously purchased garments labeled in conformance with ANSI/ISEA 107-1999 until 1/1/08.

- Tops.

Wear high visibility vests, jackets, or coverall tops at all times.

- Bottoms.

Wear high visibility pants or coverall bottoms during nighttime work (sunset to sunrise). Worksite traffic supervisors, employees assigned to traffic control duties, and flaggers wear high visibility pants or coverall bottom at all times.

- Outer Raingear.

Wear raingear tops and bottoms conforming to the requirements of this Subsection 643-3.11.

- Exceptions.

When workers are inside an enclosed compartment of a vehicle, they are not required to wear high visibility garments.

- Condition.

Furnish and maintain all vests, jackets, coveralls, rain gear, hard hats, and other apparel in a neat, clean, and presentable condition. Maintain retroreflective material to Level 2 standards.

Payment for high visibility garments for workers is subsidiary to other traffic contract items. E56(5/01/07)

Special Provision

643-3.12 TEMPORARY ELECTROLIERS.

Location.  When the Contract includes Item 643(40) Temporary Electrolier, install temporary electroliers at the following locations:

1.	Along roadway segments that are illuminated when beginning work and the following conditions apply:

a.	Maintaining traffic on the subgrade, portions of the new pavement structure, or on the existing pavement.

b.	The permanent lighting system cannot be operational beforehand.

c.	When, because of grading operations, a vehicle is within 4 inches of ground clearance and 5 feet between the tires would snag on the existing foundations, or the tops of the existing foundations are more than 8 inches below the grade of the surrounding embankment.

2.	At locations specified by the Engineer, including

a.	Along detours and diversions, and

b.	Along traveled ways that transition from one typical section to another, and

3.	At temporary traffic signals.

4.	At the locations shown in the Plans.

Lighting Plan.  The Department will not require lighting from midnight June 7 to midnight July 5.  Make temporary electroliers operational by sunset on the day replacing or retiring the existing system, or open a roadway and/or detour to traffic.

Submit a Plan for each temporary electrolier system to the Engineer for review and approval before implementing.  Allow at least two weeks for review.  Provide temporary electroliers on the far right side of approaches at signalized intersections.  Luminaires and mast arms may be installed on the signal poles when they do not conflict with other overhead utilities.  Along roadways, choose one of the following options for temporary lighting Plan:

1.	When one is included, use the temporary lighting Plan detailed in the Plans.

2.	On roadways with existing lighting, provide new foundations and install poles and mast arms sized to keep the existing luminaires in their existing positions horizontally and vertically over the roadway.  In this case, no lighting design is required.

3.	Design temporary lighting system using the Contractor’s choice of luminaires, including the luminaires of the permanent lighting system.  Use a layout pattern, mounting height, and luminaire offset and spacing that provide a light distribution that conforms to AASHTO’s “An Informational Guide for Roadway Lighting” illuminance method of design.  Design the system for the roadway’s functional class as specified in the Department’s Annual Traffic Volume Report.

Furnish and install materials and miscellaneous hardware required to provide a functional lighting system, including foundations, branch circuitry, and electrical load centers.  Size the branch conductors to provide a maximum 5% voltage drop at the most remote luminaire.  Materials shall conform to the Specifications.  The illumination cables may only be directly buried if the cables are listed for direct burial.

###### Poles.  Use any of the following poles.

1.	Existing light poles found within the project limits that are in suitable condition for reuse as determined by the Engineer and scheduled to be removed.

2.	Poles from the permanent lighting system.

3.	The following new poles may be furnished, if a minimum of 30 feet in elevation between a luminaire and the edge of traveled way is maintained.

a.	ANSI Class 4 wood poles.  Installed outside the clear zone during winter shutdown.  To determine the clear zone, see subsection 1130.02 of the Alaska DOT/PF Highway Preconstruction Manual.

b.	Steel, aluminum, or fiberglass poles that meet design criteria for 80 mile per hour wind speeds according to AASHTO’s 1994 edition of the “Standard Specifications for Structural Supports for Highway Signs, Luminaires, and Traffic Signals”.

c.	Poles that are part of the temporary signal systems.

Furnish temporary electrolier service between October 1 through May 15 and located within the clear zone, with an approved yielding type base.  Approved yielding bases consist of FHWA approved slip bases, transformer bases, or frangible couplings.  Install wood poles and other fixed base poles outside the clear zone or behind guardrail or portable concrete barrier that protects against another hazard.

Install temporary electroliers, in service at any time from May 15 through September and located within the clear zone, with approved yielding bases or with fixed bases shielded by 30 feet of barrier and an FHWA approved end treatment.  Provide 2 feet of clearance between the barrier and pole.  Consider the costs of furnishing the barrier and an end treatment a subsidiary obligation of Item 643(40) Temporary Electrolier.  Replace fixed base poles that are located within the clear zone and that will remain in service after October 1 with yielding base poles at no expense to the State.

Load Centers.

Use any of the following load centers to energize the temporary lighting and signal systems. Provide work needed to modify load centers to provide functional temporary lighting and signal systems according to the NEC.

1.	Permanent load centers installed in the Plan location.

2.	Existing load centers scheduled to remain intact until completion of the project.  Relocate and reuse existing load centers only if approved.

3.	Approved temporary load centers with photoelectrical controlled lighting circuits.  Provide a temporary load center when retiring an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

643-3.13 TEMPORARY SIGNAL SYSTEMS.  Provide temporary traffic signals at the intersections of Parks Highway and Knik-Goosebay Road; Parks Highway and Lucille Street; Parks Highway and Weber Street; Parks Highway and Lucus Street; and Crusey Street and Bogard Road.  Move traffic through these intersections with fully functional traffic signals, except during shutdowns to change from one system to another.  The Engineer will limit temporary signal system shutdowns to the times when traffic restrictions are allowed in subsection 643-3.08, Construction Sequencing.  Use flag-control to control the flow of traffic during these shutdowns.

Traffic Control Plan.  Submit a Traffic Control Plan for each temporary signal system to the Engineer for approval before implementation.  Include the same number of signal heads, signal phases, pedestrian pushbuttons, signs, pavement markings, etc. found in the signal system being replaced or modified in the Plan, plus the following details.

1.	A scale drawing of the intersection that includes lanes, their widths, and auxiliary lane pocket lengths.

2.	The location of signal poles, controller cabinet, and the load center that will feed the temporary signal system.

3.	The location, sizes, and type of each signal head.

Temporary Signal Systems.  May consist of a combination of the existing systems, relocated components of the existing systems, guyed wood poles, and parts of the permanent signal system.

1.	Install temporary controller assemblies on Type III junction boxes.

2.	Suspend traffic signals from messenger cables provided mounted with standard span wire hangers and secure them with a second cable to prevent misalignment in a wind.  Leave sufficient signal cable slack at each pole to provide for drip loops and to allow realignment of each signal head.

3.	Use a minimum of two circuits to energize the signals of each phase that include two or more signal faces.  The Engineer will allow splices only at the terminal blocks in the signal faces.

Whenever temporary signals include a span wire attached to a permanent signal pole, install a guy on the permanent pole and provide protective collars to prevent chafe damage.  Exclude poles with breakaway bases in span wire supported signal systems.

Maintain fully actuated traffic signals during the normal course of construction by installing loop detectors or a video detection system.

643-3.14 REQUIREMENTS AND USE OF THE WEB SITE.

1.	Design.  Shall be simple and useable.

a.	Implemented by professional web site designer.

b.	Provide and pay for domain name.

c.	Answer the question, “How will the construction affect my travel as I am traveling through this construction project?”

d.	Include simple graphic or graphics showing traffic pattern impacts.

e.	Include one section that specifically addresses through traffic on the highway.

f.	Minimize pages and links.

g.	Incorporate Department provided home page format.

2.	Maintenance.  Update as required showing current conditions.  Provide 7 days advance notice for major proposed impacts such as lane restrictions on the Parks and intersection closures.  Provide and pay for hosting.

Special Provision

643-4.01 METHOD OF MEASUREMENT.

Replace the second sentence of Item 2 with the following: Special Construction Signs are measured by the total area of legend bearing sign panel, as determined under subsection 615-4.01 and   compensation for a 24 hour period shall be made under Construction Signs in the Traffic Control Rate Schedule.

Add the following:  No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  Work will be subsidiary to Item 643(1) or 643(2) Traffic Maintenance. (12/14/06)R222USC04

Add the following:  643(30) Contractor Furnished Web Site will not be measured for payment.

Standard Modification

643-5.01 BASIS OF PAYMENT. 	Add the following:  Payment for high visibility clothing for workers is subsidiary to other items.  (3/15/06)E29

Special Provisions

643-5.01 BASIS OF PAYMENT.  Add the following:

16.	Work Zone Illumination.  Payment for work zone illumination and any required adjustments to work zone illumination is subsidiary to other items.  ES14(3/15/06)

17.	Road Closure:  The contract price includes all resources required to prepare the TCP, notify the public, and to provide, install, maintain, move, and remove the required devices for the duration of the road closure.

18.	Intersection Closure:  The contract price includes all resources required to prepare the TCP, notify the public, and to provide, install, maintain, move, and remove the required devices for each weekend the intersection is closed.

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $5.00 |
| Special Construction Sign | Square Foot | $20.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | M-Gallon | $ 20.00 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Foot | $.75 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Foot | $1.15 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Foot | $1.25 |
| Temporary Guardrail | Foot | $21.00 |

The Engineer will pay for Item 643(15) Flagging on a contingent sum basis at the rate of $41/hour.  The Engineer does not require a change order/directive for the flagging pay item.  Flagging associated with Change Order work will be paid at the prices according to subsection 109-1.05 Compensation for Extra Work.  (12/14/06)R222USC04

Add the following: Payment for Item 643(30) will be made on the receipts for authorized tests plus 15 percent, and shall be considered full compensation for labor, equipment and materials required to establish and maintain the Internet web site.

Delete Item 643(15) and substitute the following:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |
| 643(30) Contractor Furnished Web Site | Contingent Sum |
| 643(31) Crusey Phase 1 Road Closure | Lump Sum |
| 643(32) Crusey Phase 2 Road Closure | Lump Sum |
| 643(33) Crusey/Bogard Intersection Closure | Each |
| 643(34) Crusey/Westpoint Intersection Closure | Each |
| 643(40) Temporary Electrolier | Contingent Sum |
| 643(41) Temporary Signal System | Lump Sum |

(02/10/06)R222USC04

SECTION 644

# SERVICES TO BE FURNISHED BY THE CONTRACTOR

Special Provisions

644-2.01 FIELD OFFICE.  Delete this subsection in its entirety and substitute the following:  Furnish and maintain a suitable office for the Engineer, available for occupancy from 2 weeks before beginning work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15.  The following office requirements shall be met:

1.	A minimum of 1,000 square feet of floor area.  The office area shall be divided so that it contains an office room separated by a closable door.  The office room shall have a minimum of 160 square feet of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of 6 electrical outlets.

4.	A minimum of 100 square feet of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four telephone service lines available at the office location.  One of the lines provided is to be available for a facsimile machine/dial-up Internet connection.  Provide Internet connection with send and receive data capability supporting 56 kilobytes per second or higher data transfer rate.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 3 miles of the project.

10.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

11.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture from Anchorage.

644-2.02 FIELD LABORATORY.  Delete subitem g of item 2 and substitute the following:

g.	500 gallon capacity tank with a pressure pump or a commercial pressurized system.

Replace item 6. a. with the following:

- Supply 240 volt, 60 hertz power, a 100 pound propane bottle, and a 500 gallon capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

Add the following:

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment from Anchorage.

644-4.01 BASIS OF PAYMENT.  Add the following:  Long distance calls made by State personnel and the Internet service provider will be paid by the State.  Local calls and connection fees shall be paid by the Contractor.

Electricity, propane, and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.  (01/11/07)R63USC

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 648(8) Vehicle | Each |

# Add the following Section:

SECTION 645

## TRAINING PROGRAM

### Special Provisions

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts before the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A-301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "yellow pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish before contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided.  Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and one or more of the following occurs: contribute to the cost of the training, provide the instruction to the apprentice/trainee, or pay the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Before award of the contract, submit Form 25A-311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Conractor, and approval by the Engineer, of efforts made in good faith that substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved before contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A-310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this Section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the Contractor’s judgment, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A-310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  Submit Form 25A-313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A-310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A-310.  Apprentices in USDOL/BAT training programs shall be paid according to their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A-312.

645-3.03 Subcontracts.  In the event  a portion of the work is subcontracted, the Engineer shall determine how many, if any, of the apprentices/trainees are to be trained by the subContractor.  Any such subcontracts shall include this Section 645, Form 25A-311 and Form 25A-310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor according to subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this Section before the Contractor’s submittal and approval by the Engineer of Form 25A-312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the Contractor’s discretion, graduates early and is employed as a journey worker according to the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of other training program funds the Contractor may receive, unless such other funding sources specifically prohibits the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A-311, may be made only when approved by the Engineer through Change Order.

Noncompliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of training programs approved for the project.  No payment or partial payment will be made if the Contractor fails to do the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	Provide the required hours of training (as shown on the approved Form 25A-311),

2.	Train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A-311), or

3.	Hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation that establishes why the Contractor was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs. S16(10/29/91)

Payment will be made under:

| # Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, __ Trainees/Apprentices | Labor Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Replace this subsection with the following:  Submit a detailed initial CPM Schedule at the preconstruction conference for the Engineer’s acceptance as set forth below.

The construction schedule for the entire Project shall not exceed the specified contract time.  Allow the Engineer fourteen (14) days to review the initial CPM Schedule.  Revise promptly.  The finalized CPM Schedule must be completed and accepted before beginning work on the Project. R261M98 (12/13/02)

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.

Delete item 2.  60-Day Preliminary Schedule.

Delete the first sentence of item 3. Schedule Updates.  and substitute the following:  Hold job site progress meetings with the Engineer for the purpose of updating the CPM Schedule.  Meet with the Engineer monthly or as deemed necessary by the Engineer.  R261M98(12/13/02)

Add the following Section:

## SECTION 647

## EQUIPMENT RENTAL

Special Provisions

647-1.01 DESCRIPTION.  This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer.  Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and operations shall be according to the Engineer's instructions.  The Engineer’s instructions shall be to the Contractor’s supervisory personnel only, not to the operators or laborers.  In no case shall the Engineer’s instructions be construed as making the Department liable for the Contractor’s responsibility to prosecute the work in the safest and expeditious manner.

647-2.01 EQUIPMENT FURNISHED.  In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer.  The operation of equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements.  The number of pieces of equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work.  The equipment shall be used only at such times and places as the Engineer may direct.

Equipment shall be in first-class working condition and capable of full output and production.  The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications.  Alterations will not be considered acceptable in achieving the minimum rating.  Equipment shall be replaced when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operated, that shall include the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL.  Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity.  Personnel furnished by the Contractor shall be, and shall remain during the work hereunder, the Contractor’s employees.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work.  Also, furnish without direct compensation, transportation as appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS.  The performance of the work shall be according to the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall begin, continue, and stop the operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days a week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project.  The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer.  Each day's activity will be recorded on a separate sheet or sheets, that shall be verified and signed by the Contractor’s representative at the end of each shift, and a copy will be provided to the Contractor’s representative.

647-4.01 METHOD OF MEASUREMENT.  The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas according to the direction of the Engineer.  The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment.  Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT.  Payment for Item 647(2) Wide Pad Dozer, 65 HP Minimum and Item 647(3) Hyrdo-Vac Vacuum Truck will be paid at the contract price for the number of hours required to complete the work according to the Engineers direction.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher horsepower than specified will not entitle the Contractor to any extra compensation. R15USC(08/24/05)

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(2) Wide Pad Dozer, 65-HP Minimum | Hour |
| 647(3) Hydro-Vac Vacuum Truck | Hour |

### SECTION 660

### SIGNALS AND LIGHTING

Special Provisions

660-1.02 DEFINITIONS.   Revise the first sentence to read:

Use the definitions in NEMA TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements , Section 1, Definitions, along with the following:

Under item 2 Luminaire. Revise the second sentence to read:

Luminaires consist of hood (including socket, lamp, and ballast), reflector, and glass globe or refractor.

660-2.01 MATERIALS.

1.	Equipment List(s) and Drawings. Delete item a in its entirety and the last sentence in item d and substitute the following:

a.	Materials on the Qualified Products List: The Qualified Products List does not apply to the 660 items.  Provide catalog cuts of materials to the Engineer for review and approval.

d.	Materials Not Requiring Certification: Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

2.	As-Built Plans.  Add the following:

The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

Standard Modification

660-2.01 MATERIALS.  Under Item 1.b. change title by removing:  “Materials Not on the Approved Products List:” and replace with:  Materials Not on the Qualified Products List:

E36(01/27/07)

# CONSTRUCTION REQUIREMENTS

Special Provisions

660-3.01 GENERAL.

1.  Schedule of Work.  Add the following:  Before performing signal related work, the Contractor shall contact the ARRC and DOT&PF Maintenance & Operations office to schedule a coordination meeting.

In Item 2, Safety Precautions. Add the following

Existing circuits listed on the wiring diagrams and Plan sheets were obtained from as-built information and must be verified before work involving those circuits.

Delete items 3 through 8 in their entirety and substitute the following:

- Excavating and Backfilling. Complete excavation and backfill required to install the signal and lighting components embedded in the roadway as shown in the Plans, including foundations, conduits, junction boxes, and loop detectors. Provide traffic control to complete this work according to the requirements of Section 643.  Place excavated materials where it will not interfere with surface drainage.

Support and protect conduits and utilities scheduled to remain in service when encountering them during excavation.

Excavate trenches wide enough to install the number of conduits specified side by side, to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches, and to compact the bedding and backfill materials according to these specifications.

To install conduits, excavate trenches deep enough to allow for 6 inches of bedding material, the depth of the largest conduit, and the minimum burial depth specified between the top of the conduit and finished grade of the ground above the conduit.  Keep the longitudinal profile of trench bottoms free of irregularities that would prevent the assembled conduit run from continuously contacting the top of the bedding material.

Dispose of, according to subsection 203-3.01, excavated materials that remains after completing backfill work and excavated material not meeting the requirements of Selected Material, Type C, as defined in subsection 703-2.07.

Dewater foundation and conduit excavations immediately before and during embedding and backfilling operations.  Backfill excavations with materials that meet the following requirements

a.	Backfill foundations with material that meets the requirements of Selected Material, Type A that passes through a 3 inch sieve.

b.	Within the limits of the typical section, embed conduits and backfill trenches using material that meets the requirements of the lift where it is located, reusing excavated materials if it meets the requirements of the applicable lift,

c.	In other locations, embed conduits and backfill trenches using material that meets the requirements of Selected Material, Type C, reusing excavated materials if it meets this requirement.

d.	Import, when ordered, embedment and backfill materials that satisfy the preceding materials requirements.

Embed conduit(s) between two 6 inch lifts of material gleaned free of rocks exceeding a 1 inch maximum dimension.  Grade and compact the first lift to provide a surface that continuously contacts the assembled conduit run.

Within 6 feet of paved surfaces and around foundations, backfill in uniform layers no more than 6 inches deep and compact each layer according to subsection 203-3.04.  In other locations, compaction may be as approved by the Engineer.

- Welding.  Complete welding according to subsection 504-3.01.8. Welding and approved shop drawings.

Submit shop drawings of the proposed work with the welding plans for approval.  The shop drawings shall include material specifications, component dimensions, the types of welds that will be made, and the proposed type and extent of weld inspection.

Repair the holes, which were used to mount equipment, in reused poles and mast arms by welding in disks flush with the adjoining surface.  For the disk material, use steel that matches the ASTM designation, grade, and thickness of the steel used to fabricate each pole.  Cut disks that match the dimensions of the hole being repaired from pieces of steel plate bent to match the pole’s radius at the hole.  Grind the welds smooth and flush with the adjoining pole and disk surfaces.  Repair the damaged finish according to subsection 660-3.01.8.

5.	Removing and Replacing Improvements.  The Contractor shall complete the following work at the Contractor’s expense.

a.	Remove improvements that block completion of the work detailed in the Plans as specified herein.

b.	Reconstruct with new materials the nonreusable improvements the Contractor removed to complete the work, unless other items in the contract cover the improvements.

c.	Replace with new materials the reusable items damaged by the Contractor, that are specified for reuse.

d.	Reconstruct with new materials improvements that the Contractor damaged or removed, that does not conflict with the work and are not scheduled for removal.

Nonreusable improvements consist of cast in place items, including: asphalt concrete pavement, sidewalks, curb and gutter, lawns, and traffic markings.  Reusable improvements include the items that were made before installation.  Crushed aggregate base material may not be used as backfill in the base course if excavation depth exceeds the thickness of the base course.

Complete reconstruction work, including materials, according to the applicable sections of the Alaska SSHC, and leave the work in a satisfactory and serviceable condition.  In completing the reconstruction work, match the alignments, widths, thicknesses, shapes, sizes, cross sections, and finishes of the existing improvements.

If removing a portion of sidewalk or curb and gutter, remove an entire segment between the weakened plane contraction joints or between an expansion joint and a weakened plane contraction joint.

Before removing a segment of Portland or asphalt cement concrete material, cut completely through the material with a saw along the outline of the area to be removed.  Make cuts neat and true and prevent shatter outside the area removed.

To replace lawns, leave the top of the backfilled excavation low enough to install 4 inches of compacted topsoil.  Match the top of the topsoil with the bottom of the vegetative mat.  Apply seed and keep the seeded areas watered according to Section 618.

Remove, keep alive, and replant trees, shrubs, and plants according to Section 621.  Replace the trees, shrubs, and plants that do not survive with plants of like size and type.

6.	Salvaging and Reusing Electrical Equipment.  When the Plans include existing electrical equipment scheduled for removal or relocation, remove and store the equipment listed in the following paragraph without damaging it.  Deliver removed equipment not scheduled for reuse to the nearest District Maintenance Station or place specified in the Plans or Special Provisions.  Notify the district superintendent or person specified by telephone one-week before planned delivery date.  Contact Kurt Devon at 745-2159.

Salvage the controller assemblies, signal heads, mounting brackets, luminaires, lighting standards, signal posts and poles, mast arms, optical detectors, load centers, light emitting diode optical units, and the lids of junction boxes scheduled for removal and other materials scheduled for relocation.  The Contractor shall replace at the Contractor’s expense salvaged equipment damaged or destroyed before or during delivery or reinstallation.

Controller assemblies and load centers include the cabinet and equipment contained in the cabinet before Contract award.

Remove from the highway right-of-way materials associated with the equipment removed or relocated and not scheduled for reuse, including conduits, junction boxes, conductors, and foundations.  Raze the tops of foundations abandoned in place according to subsection 660-3.02.  Fill the holes left by removing junction boxes and foundations with selected material type A and compact as directed.

With approval, after removing conductors, buried conduits that do not interfere with other construction may be abandoned in place with a credit taken by the Department.  Remove the ends of abandoned conduits from the junction boxes that will remain in service.

Within 15 days of the Notice to Proceed, complete an inventory of the materials that will be salvaged in the presence of the Engineer.  Note the location and condition of the materials.  When material specified for reuse is found in an unserviceable condition, the Engineer will determine whether to repair it or replace it with new material, which will be paid for as extra work under subsection 109-1.05.  Retain a copy of the inventory and give the original documents to the Engineer.

When the Plans specify reinstalling existing equipment at new locations and installing State furnished equipment, complete the following work at the Contractor’s expense.

- For poles, install new foundations, furnishing the new nuts, bolts, washers, and conduits needed to complete the installations.

- For lighting poles, install new illumination tap wires and fused disconnect kits.

- For luminaires, clean the luminaires inside and out and install new lamps of the same wattage.

- For signal heads, furnish and install the mounting brackets needed to complete the relocation, and clean the signal heads inside and out.

- For poles and undisturbed poles from which the Plans specify removing equipment, repair the holes that were made to mount equipment according to subsection 660-3.01.4.  Welding and repair the finishes according to subsection 660-3.01.8.

When ordered, the Engineer will pay for repairing damaged finishes on existing equipment according to subsection 660-3.01.8 as extra work.

If deciding to use new equipment rather than reusing the equipment specified, notify the Engineer of the change and include a submittal according to subsection 660-2.01.1.

7.	Field Tests.  Electrical circuits must pass the following tests before the Engineer will accept the work for payment.  Perform these tests in the presence of the Engineer, and document the results of each test on a per circuit basis.  Retain a copy of test results and give the original documents to the Engineer.  Furnish equipment needed to perform these tests.

Replace or repair at the Contractor’s expense, and in an approved manner, faulty materials and work revealed by these tests.  After making repairs, repeat tests on the repaired circuit and continue this process until circuits have passed required tests.  The Department reserves the right to have the Contractor retest circuits, and to use the retest results to accept or reject individual circuits.

a.	Grounds. Before completing the circuitry and functional tests, physically examine conduits ends, junction box lids, load centers, and the foundations for signal posts and poles, lighting poles, and controller cabinets to ensure the grounding system required by subsections 660-3.06 and 661-3.01 has been installed and splices and connections are mechanically firm.

b.	Continuity.  Test each loop detector circuit for continuity at the roadside junction box before splicing the loop detector to the lead-in cable.  Each loop detector must have a resistance less than 0.5 ohms.

After splicing the loop detectors to the lead-in cables, test each pair at the controller or detector cabinet.  Each pair must have a value less than 5 ohms for single pair lead-in cables and 10 ohms for multipair lead-in cables.  The continuity test ohm reading at the cabinet must be greater than the ohm reading measured for the loop detector at the junction box.

c.	Insulation Resistance (megohm) Test.  Complete this test to verify the integrity of each conductor’s insulation after pulling the conductors and cables into position and before terminating the conductors.  At 500 volts DC, each conductor’s insulation shall measure a minimum resistance of 100 megohms or the minimum specified by the manufacturer.  With single conductors, complete the test between each conductor and ground.  In each multiconductor cable, complete the test between conductors and between each conductor and ground.

After splicing the loops to the shielded pairs in the lead-in cables, measure each pair in the lead-in cables at the controller or detector cabinet between one conductor and the cabinet ground rod.

d.	Inductance Test. Measure each detector loop and lead-in cable system at the controller or detector cabinet.  The inductance must be in the range of 50 to 500 microhenries.

e.	Circuit.  Energize every signal indication circuit with lamps installed before installing the load switches.

f.	Functional.  Perform the following tests on each signal and lighting system after the component circuits have satisfactorily passed the tests for continuity, grounding, insulation integrity, and circuitry.

- 1)	For each new traffic signal system, complete at least 24 hours of flashing operation, followed by not less than 5 days of continuous, satisfactory operation.  The Engineer may decide to omit the flashing portion of the test for modified signal systems and for new signals that replaced existing signals that remained in operation during the construction phase.

If the Engineer omits flashing operation and the system performs unsatisfactorily, correct the condition and repeat the test until the system runs for five days with continuous, satisfactory operation.

Begin the signal functional tests between 9:00 a.m. and 2:00 p.m. on any day, except a Friday, Saturday, Sunday, a legal holiday, or the day before the legal holiday.

Before each system turn on, aim signal faces according to subsection 660-3.08 and ensure equipment specified in the Plans is installed and operable, including: pedestrian signals and push buttons; signal backplates and visors; vehicle detectors; highway lighting; and regulatory, warning, and guide signs.

- 2)	Perform the functional test for each highway lighting system and sign illumination system until the systems burn continuously 5 days without the photocell, followed by a 5 day operational test using the photocell.

- 3)	Perform the functional test for each flashing beacon system for not less than 5 days of continuous, satisfactory operation.

- 4)	Perform a continuous 5 day burning test on each pedestrian overpass and underpass lighting system before final acceptance.

A shut down of the electrical system due to a power interruption does not constitute discontinuity of the functional test if the system functions normally when power is returned.

8.	Repairing Damaged Finishes.  Examine new, reused, and State furnished equipment for damage to its finish before putting the equipment into service.  Repair the damaged finishes found according to the following:

a.	Galvanized.  Repair damaged areas more than 12 inches away from welds and slip fit areas, by applying a minimum 7.8 mils of zinc based alloy applied according to ASTM A780.

If the damaged areas are within 12 inches of welds and slip fit areas, make the repair by applying a minimum 7.8 mils of zinc rich paint applied according to ASTM A780.

b.	Painted.  Repair damage to painted finishes according to the following

- (1)	Wash the equipment with a stiff bristle brush using a solution containing two tablespoons of heavy-duty detergent powder per gallon of water.  After rinsing, wire brush surfaces to remove poorly bonded paint, rust, scale, corrosion, grease, or dirt.  Remove dust or residue remaining after wire brushing before priming.

- (2)	Factory or shop cleaning methods may be used for metals if equal to the methods specified herein.

- (3)	Immediately after cleaning, coat bare metal with pretreatment, vinyl wash primer, followed by 2 prime coats of zinc chromate primer for metal.

- (4)	Give signal equipment, excluding standards, a spot finishing coat on newly primed areas, followed by 1 finishing coat over the entire surface.

- (5)	Give nongalvanized standards 2 spot finish coats on newly primed areas.

Paint coats may be applied either by hand brushing or by approved spraying machines.  Perform the work in a neat and workmanlike manner.  The Engineer reserves the right to require the use of brushes for the application of paint, should the work done by the paint-spraying machine prove unacceptable.

Add the following new item 9:

9.	Regulations and Code. Complete work according to the standards of the NEC, the NESC, and local safety codes as adopted and amended by the authority having jurisdiction.

660-3.02 FOUNDATIONS.  Under item 1.  Cast-in-Place Foundations., add the following to the first paragraph:  Locate the tops of traffic signal post and pole foundations flush with the adjacent finished:  walkway, shoulder, or surrounding ground.

1.	Cast-in-Place Foundations.  In subparagraph f, revise the second sentence to read: Before placing the form or reinforcing steel cage, remove loose material from the bottom of the hole to ensure the foundation rests on firm, undisturbed ground.

In the second sentence of sub-item i delete “before grouting.” and substitute ”before attaching the skirt.”

In the first sentence of sub-item j, delete “concrete pile caps” and substitute “foundations”

Delete item k and add the following new items k and l:

k.	Install the bottoms of the bottom leveling nuts in a level Plane within 1 inch of the top of foundations.  Adjust all nuts until their tops form a level Plane.  Install one washer on top of all leveling nuts and, after setting the pole on these washers, install one washer under all top nuts.

Bring all leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Generously lubricate the bearing surface and internal threads of top nuts with beeswax.  Tighten all top nuts to a “snug” condition.  Use a click-type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts.

After torquing the top nuts, use a hydraulic wrench to rotate all top nuts an additional one sixth (60°) turn, while preventing the leveling nuts from turning.

l.	Attach a 4 AWG, bare, solid copper wire as a grounding electrode conductor to the #4 spiral bar in the reinforcing steel cage.  Use an irreversible compression connector or cadweld to make the attachment.  Protect the attachment during concrete placement.  In foundations that lack reinforcing steel cages, install 21 feet of coiled 4 AWG, bare, solid copper wire as the grounding electrode.  Route the conductor to protrude near the top, center of the foundations.  Slide a minimum 6 inch long, nonmetallic, protective sleeve over the conductor.  Allow 1 inch of the sleeve and 24 inches of conductor to protrude from the foundations.

2.	Pile Foundations. Add the following new item g:

g.	Use no more than one splice per foundation.  Locate the splice at least 7 feet from the top of pile.

Add the following new sub subsection:

4.	High Tower Foundations. Furnish pipe piles that conform to API 5L X 52 and feature the diameter, minimum length and wall thickness shown on the Plans.  Furnish seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Complete welding according to subsection 504-3.01.8 Welding.  Submit a shop drawing of the work with the welding Plan.  Furnish Quality Control inspection to ensure materials and workmanship meet contract requirements.  Visually inspect (VT) 100% of each weld and inspect 100% of full penetration welds by ultrasonic NDE (UT).

Furnish anchor bolts that conform to ASTM F1554, grade 55, and meet the supplementary Charpy V-Notch requirements listed in subsection S4 of the specification.  Furnish each anchor bolt with three nuts and two washers.

Secure the anchor bolts to ensure they do not move during concrete placement.  Replace, with no additional compensation, concrete pile caps with anchor bolts that do not match the base plate of the pole or are out of plumb.  The Department will not allow modification of the anchor bolts or base plate to get the base plate set on the leveling nuts.

Replace subsection 660-3.03 with the following:

660-3.03 CONDUIT.  Electrical conductors shall be installed in conduit, except for overhead wiring, wiring inside poles, and when otherwise specified.  Use rigid metal conduits (RMC) and fittings for raceways, including bored casings, except when the Plans specify using polyethylene conduits.  Install conduits of the sizes specified along the routes detailed on the Plans.  When routing is not shown, route conduits as directed by the Engineer.

1.	Install conduits at least 30 inches below the finished grade of the ground above the conduit, except conduits that will be sealed under a minimum 4 inch thick Portland cement concrete sidewalk may be installed a minimum of 18 inches below the top back of curb or surface above the conduit, whichever is lower.

2.	Install conduits that cross unpaved areas and paved roadways that will be overlaid in excavated trenches.  Excavate, bed conduits, and backfill trenches according to subsection 660-3.01.3, Excavating and Backfilling.

3.	Install conduit(s) under paved roadways and approaches that will not be overlaid by boring or drilling methods.  Jacking conduits into position is allowed.  However, if subsurface conditions prevent the successful completion of the work, install the conduit(s) by boring or drilling methods without additional compensation.

4.	Sweep both rigid metal and polyethylene conduits through the open bottom of junction boxes by installing 90-degree rigid metal elbows on the ends of conduit runs.  To each elbow, install a nipple that terminates 5 to 12 inches above the bottom edge of each junction box.

5.	Install the tails of loop detectors without elbows through the walls of junction boxes at elevations that ensure the loops drain into the box.  Extend the ends a minimum of 2 inches beyond the inside wall of the box.

6.	Drill a 3/8 inch drain hole in the bottom of the lower straight section of elbows and in the bottom of conduits at the low points of conduit runs.  Smooth the edges of the drilled holes on the inside of elbows to prevent scraping the conductors.  Cover the holes with a wrap of approved filter cloth secured with 2 self clinching nylon cable ties.

7.	Keep conduits clean.  Install grounding bushings and approved plastic insert type plugs on the ends of conduit runs before backfilling around the conduit ends.

8.	At the low points of conduit runs, install sumps containing a minimum 2 cubic-feet of coarse concrete aggregate material that conforms to subsection 703-2.02.  Compact the aggregate sumps as directed to prevent settlement of the trench backfill.

9.	Install conduits that must cross existing facilities such as storm drain pipes, duct systems, and other underground utilities at the minimum depths specified, going under the facilities if necessary.  Install additional drains and aggregate sumps at the low spots, if any.

10.	Position conduits in trenches, junction boxes, and foundations to provide clearances of at least 2½ inches around 2 inch conduits and at least 2 inches around conduits larger than 2 inches.

11.	Fabricate rigid metal conduits less than 10 feet long from standard lengths of conduit.  Cut conduits squarely to ensure the threading die starts squarely on the conduit.  Cut the same number of threads as found on the factory threaded ends.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.  Do not use slip joints or pieces of running thread pipe.

12.	Coat drilled holes, shop and field cut threads, and the areas with damaged zinc coating with zinc rich paint.

13.	When standard couplings cannot be used to join conduit components, use approved threaded unions.

14.	Bury a continuous strip of 4 mils thick, 6-inch wide polyethylene marker tape above underground conduit runs.  Install the tape 9 inches (± 3 inches) below finished grade, using two strips side by side to mark road crossings.  Furnish tapes with a black legend on a red background.

15.	If encountering obstructions during jacking or drilling operations, obtain approval and cut small holes in the pavement to clear the obstruction.  Locate the bottom inside face of the bore pit no closer than the catch point of a 1¼ to 1 slope (a horizontal to vertical ratio) from the edge of pavement.  Do not leave these pits unattended until installing an approved means of protection.

16.	When the Plans specify using polyethylene conduit, install RMC in structures and foundations, between type 2 and 3 load centers and the nearest junction box, and on the surfaces of poles and other structures.

17.	In foundations, install 90-degree elbows and conduits of the size and quantity shown on the Plans.  Extend the conduits a maximum of 2 inches above the top of the foundations for posts and poles with breakaway bases and 4 inches above the top of foundations for fixed base structures.

18.	Seal conduits leading to electrical equipment mounted on soffits, walls, and other locations below the grade of the serving junction box with an approved duct-sealing compound.

19.	Install expansion fittings in conduits that cross expansion joints.

20.	Install a polypropylene pull rope with a minimum 200-pound tensile strength in future use or spare conduits, and reinstall the plugs.  Double back at least two feet of pull rope into both ends of each conduit.

21.	The Contractor may install conduits larger than the sizes specified.  If used, it must be for the entire length of the run.  Reducing couplings or bushings are not allowed.  Complete work associated with installing conduits larger than specified without extra compensation.

22.	Clean existing conduits that will remain in service using a heavy-duty air compressor that delivers at least 125 cubic feet of air per minute at a pressure of 110 pounds per square inch.  Clean the conduits before pulling in new cables and after removing cables specified to be removed or replaced as follows:

- a.	When the conduits contain cables that will remain in service, leave the cables in place during the cleaning, and

- b.	Ream empty conduits with a mandrel or cylindrical wire brush before blowing them out with compressed air.

23.	When modifying existing conduit runs, complete the work as required for new installations using the same sizes and types of conduit.  When extending existing conduits, add no more than 90 degrees of horizontal bend to the extension.

24.	When installing a junction box in a continuous run of existing conduit, remove a length of conduit in each conduit run and complete the work of installing the conduits, elbows, and nipples as required for a new installation.

25.	When adjusting existing junction boxes to a new grade, remove cables and replace the nipples as required to provide the clearances specified for new installations.

26.	Remove the ends of abandoned conduits from junction boxes that will remain in service.

27.	When Plans call for connecting polyethylene conduit to RMC use an electrofusion coupler rated for direct bury application.  The coupler must be rated for same wall thickness as the adjoining conduits.  Thread the ends of the RMC with the same number of threads as found on the factory threaded ends of RMC.  Ream the inside of conduit ends cut in the shop or field to remove burrs and sharp edges.

Replace subsection 660-3.04 with the following:

660-3.04 JUNCTION BOXES.  Install precast reinforced concrete junction boxes of the types specified.  For junction boxes that contain traffic signal conductors, furnish cast iron lids with the word TRAFFIC inscribed into them.  For junction boxes that contain lighting conductors exclusively, furnish cast iron lids with the word LIGHTING inscribed into them.

Junction Box Location

When shown, install junction boxes at the station and offset locations specified.  When lateral locations are not specified, install junction boxes 8 feet from the face of curb or edge of pavement.  If the 8 feet offset falls:

      - In a pedestrian facility separated less than 7 feet from the roadway face of curb or edge of pavement, increase the offset and install the junction boxes on the backside of the facility.  When lacking the right of way to install junction boxes outside the pathway, install at locations as directed, avoiding curb ramps, curb ramp landings, and the middle of walkways.

      - In a pedestrian facility separated at least 7 feet from the roadway face of curb or edge of pavement, reduce the offset and install the junction box next to the facility.

      - Outside the right of way, install the boxes just inside the right of way line.

      - In a raised median, install junction boxes near the center of the median.

      - In a ditch bottom or area that collects drainage, install the junction boxes at locations as directed.

      - Behind guardrails that shield slopes steeper than 3:1 (a horizontal to vertical ratio), install junction boxes between posts and at least 5 feet back from the face of rail.

      - On top of underground utilities or storm drains, install the junction boxes at locations as directed.

Longitudinally, install junction boxes adjacent to the loop detectors or pole they serve, except avoid installing type 1A junction boxes in driveways and in locations subject to use by heavy trucks.  When shown near the ends of medians, install junction boxes at least 10 feet from the median end.  When the offsets for electroliers and flashing beacon posts place them near the junction boxes that serve them, install the junction boxes on the side of the electroliers and posts downstream of traffic flow.

## Limitations

Limit the distance between adjacent junction boxes to the following dimensions:

1.	400 feet for conduits that contain signal interconnect cable only.

2.	300 feet for conduits that exclusively contain two loop lead-in cables.

3.	300 feet for conduits that contain a single cable other than signal interconnect.

4.	190 feet for conduits that contains more than one cable.

If the preceding limitations require installing additional junction boxes not shown on the Plans, the Engineer will pay for them as extra work, otherwise, installing additional junction boxes will be at the Contractor’s expense.

After grading the roadside, vertically adjust those junction boxes that do not conform to the following criteria.  In unpaved areas that will not be seeded, in areas adjacent to pedestrian facilities, and in paved medians, install the tops of junction boxes 1 inch below finished grade. In seeded areas, install the tops of junction boxes to 2 inches below the seeded surface.

Bond junction box lids to an equipment grounding conductor according to subsection 660-3.06.  Attach the jumpers to the lids with brass or stainless steel hardware.

Install a stone drain under each junction box.  Drains shall consist of coarse aggregate for concrete that conforms to subsection 703-2.02.  Minimum drain dimensions include an 18” depth and a length and width equal to those of the junction box it drains.  Compact the aggregate material as directed to prevent junction box settlement.

In every new and reused junction box, install an electronic marker that consists of an antenna encapsulated in a 4 inch diameter red polyethylene ball.  Furnish markers that conform to the American Public Works Association standards for locating power.  Markers shall respond to locator devices up to 5 feet away, work at all temperatures, and contain no internal power source.

660-3.05 WIRING.  Delete the second paragraph in its entirety and substitute the following:

## Conditions

Do not pull conductors into conduits until the following conditions are met:

a.	The prescribed clearances around conduit ends are provided,

b.	Crushed rock sumps are installed under junction boxes,

c.	Conduit ends protrude above the bottom of junction boxes within the prescribed range,

d.	New conduits are free of material that became lodged in them during the completion of the work,

- e.	Reused conduits are cleaned according to subsection 660-3.03,

- f.	Junction boxes are set to grade, and

- g.	Grounding bushings are installed on the ends of metallic conduits.

Delete item 3 in its entirety and substitute the following:

3.	Pull, as a unit, the conductors specified to be installed into clean conduits, leaving existing conductors that will remain in service in place.

Add the following line to Table 660-1 under subitem a. of item 9.

| # LOOP DETECTOR NUMBER | # COLORED PAIR |
| --- | --- |
| Usually a spare pair | Orange and Black |

Delete items 11 and 12 in their entirety and substitute the following:

11.	Encapsulate illumination cable splices in rigid 2 piece plastic molds filled with an insulating and sealing epoxy resin.  Furnish molds large enough to complete the splices and encase the cable jackets in the epoxy resin.  Furnish molds rated for 600 volts AC operation and feature fill and vent funnels for epoxy resin.  Fill the splice mold bodies with epoxy resin that is resistant to weather, aromatic and straight chain solvents, and that will not sustain combustion.

When approved by the Engineer, 1 splice may be used in the following cases;

- a.	An in-line splice may be used when a Planned cable run exceeds the length available from the manufacturer on a single spool of cable.

- b.	In a run of 1,000 liner feet or more.

When a cable is spliced it shall occur within an appropriately sized j-box or in the base of an electrolier designed for said splice.

12.	Encapsulate loop lead-in and telemetry cable splices in rigid, transparent, PVC molds filled with re-enterable polyurethane electrical insulating and sealing compound.  Furnish splice kits rated for 1000 volts AC operation and direct burial.

Provide re-useable four piece molds that are held together with stainless steel hose clamps.  Two pieces form a cylinder and two flexible end caps seal the ends and allow the conductor entry.  Use molds with dimensions suitable for the splice made, encase the cable jackets, and have fill and vent funnels.

Insert a loose woven polyester web that allows a full ¼ inch of insulating compound to flow between the splice and the inside of the mold.  Fill the PVC molds with re-enterable polyurethane electrical insulating and sealing compound that cures transparent, is nontoxic, is non-corrosive to copper, and does not support fungi or mold growth.

Add the following items:

18.	Retrofit reused poles with new tap wires, fused disconnect kits, and fuses for both illumination circuits and where applicable festoon outlet circuits.

19.	Whenever conductors can not be terminated as specified in the Plans in circuit breakers due to size, splice a piece of #8 AWG power conductor onto the end of each conductor using an overlap type, irreversible compression connector.  Insulate the splice with heat shrink tubing.  Complete the splice in the space between the top of the load center foundation and the bottom of the cabinet. Limit the length of the #8 AWG conductor to 5 feet.

Replace subsection 660-3.06 with the following:

660-3.06 BONDING AND GROUNDING.  Bond and ground branch circuits according to the NEC and the following requirements.  Make noncurrent carrying but electrically conductive components, including: metal conduits, junction box lids, cabinets, transformer cases, and metal posts and poles, mechanically and electrically secure to an equipment grounding conductor.  Make fixtures mounted on metal poles, including signal components and luminaires, mechanically and electrically secure to the pole.

Install grounding bushings with insulated throats on the ends of metallic conduits.

Install a bare stranded copper wire for the equipment grounding conductor in conduits, except those conduits installed for future use.  Install size 8 AWG conductors, except in those conduits that contain circuit conductors larger than 8 AWG.  In this case, install a wire equal in size to the largest circuit conductor.  Attach the grounding conductors to the grounding bushings, leaving 12 inches of slack between each bushing.  Connect grounding conductors together using irreversible compression type connectors to form a fully interconnected and continuous grounding system.

Retrofit existing spare conduits that will contain new cables exclusively with new grounding bushings.  When the Plans require installation or removal of conductors from existing conduits, retrofit with new grounding conductors sized according to the preceding paragraph.

Bond junction box lids to the grounding conductor using copper braid with a cross sectional area equal to an 8 AWG conductor and eyelets spaced at 6 inch intervals.  Connect bonding jumpers to the grounding conductors using irreversible compression type connectors.  Replace missing or damaged conduit and junction box lid bonding jumpers.

Join the equipment grounding conductors from the conduits to the 4 AWG grounding electrode conductor using irreversible compression connectors at Portland cement concrete foundations.  For pile foundations, attach the equipment grounding conductor from the conduit to the pile cap adapter with a listed mechanical grounding connector.

When installing signal poles, signal posts, and lighting standards with frangible coupling bases, run a 5 feet long grounding conductor from the grounding bushing on the conduit to the grounding lug located in the hand hole of each pole.

Bond slip base type standards and pedestals by using 2 conductors from the conduit, one attached with a ground rod clamp to an anchor bolt and the other connected to the grounding lug located in the hand hole of each pole.

Ground one side of the secondary circuit of a transformer.

Install a ¾ inch by 10 feet copper clad ground rod inside each controller cabinet foundation and a 6 AWG bare stranded copper wire for the grounding electrode conductor.

660-3.07 TRAFFIC CONTROLLER ASSEMBLIES

In the 3rd paragraph revise the first sentence to read: At the time the controller assembly is delivered submit the following for each assembly:  and add the following to the last sentence (1 paper copy and 1 electronic copy in Adobe pdf format)

In the 4th paragraph replace “3.5 inch floppy” with “compact”

Delete 1. Shop Tests. entirely and replace with the following:

- Shop Tests.  The Controller Assembly manufacturer shall conduct a pre-test of the cabinet and controller assembly. The pre-test includes but is not limited to; Ensure the cabinet is free of paint scratches, dents, sharp edges, and any other physical defect. Ensure cabinet hinges, heater, ventilation system, lighting and door locking mechanism function properly. Ensure that there are no shorts between AC+, AC- and GND anywhere in the cabinet. Check that there is no continuity between AC+ and DC+.  Check for continuity between any green wire connection point and GND. Ensure all devices within the cabinet are labeled properly.

The Controller Assembly manufacturer shall conduct a final test of the cabinet and controller assembly. Qualified Cabinet Test Technicians shall conduct the final test.  The final test includes but is not limited to ensuring proper operation of; flash colors & combination, standard controller phasing, pedestrian pushbutton isolation, MMU, circuit breaker/fuse operation, telemetry operation, loop panel/detector rack operation, EVP operation and, proper police & auxiliary panel operation.

Upon completing the final test the cabinet shall be run, “burned-in”, under full loads for a period of not less than 48-hours with a test timing Plan in effect that utilizes full cabinet phases and functionality.

In the course of testing, any component found to function incorrectly or exhibit any physical damage must be replaced with an equivalent new component before delivery. Should the cabinet fail in any manner during burn-in, the cause of said failure must be remedied and the test restarted with another 48-hours of burn-in. The intent of this specification is to meet or exceed the requirements of Econolite test procedure MWI-10-28 Rev. C. With prior approval of the Engineer, other equivalent test procedures may be substituted.

Upon completion of the pre-test, final test and burn-in, the Controller Assembly manufacturer shall issue a letter of certification stating that the required tests have been completed, note any defects found and the remedial action taken. Further, the certification shall state assembly conformance with the NEMA TS 2-2003 v02.06, Traffic Controller Assemblies with NTCIP Requirements, Section 2 Environmental Requirements.  Submit the certification letter and copies of the test results to the Engineer.

The work required in this section shall not be paid for separately but shall be considered subsidiary to item 660(1X) Traffic Signal System Complete and/or 660(17X) Traffic Signal System Modifications.

Replace subsection 660-3.08 with the following:

660-3.08 SIGNAL AND LIGHTING INSTALLATION REQUIREMENTS.  Install signal and lighting equipment according to the details shown on the Plans and the following:

Apply anti-seizing compound to the following fasteners:  frangible couplings, mechanical grounding connectors, bolts that secure hand hole covers and signal mounting hardware to poles and mast arms.  Remove the fasteners from luminaire mounting brackets, fused disconnect kits, grounding bushings, and signal faces that secure the visors, and apply anti-seizing compound to these fasteners before completing the installation.

Before passing conductors through the holes made in posts, poles, and mast arms for wireways, remove the burrs and sharp edges from the inside and outside of these holes.

Until each traffic signal and/or flashing beacon goes into operation, keep the vehicular and pedestrian signal faces covered with beige colored canvas shirts sized to fit the signal faces shown in the Plans.  Each signal shirt shall feature elasticized openings that fit over the visors and at least two straps to secure it to the signal.  Provide shirts with a legend that reads “out of service” and a center section that allows an operator to see the indications during system tests.

When not shown in the Plans, determine the shaft lengths of lighting and signal poles and signal mast arm connector plate locations to provide the Plan mounting heights of luminaires and traffic signal heads.

Furnish work to install foundations for relocated poles, including: conduit, excavation, reinforcing steel, class A concrete, anchor bolts, nuts, and washers.

1.	Electrolier Installation.  Before installing electroliers, check the socket position of each luminaire to verify it matches the position indicated in the instructions for the light distribution type shown on the Plans.

Install electroliers with mast arms with a slight rake by plumbing the side of the pole opposite the mast arm.  After the pole has been plumbed, level the luminaire as recommended by the manufacturer.

Install electroliers without mast arms with the centerline of the pole plumb.

2.	Signal Pole Installation.  Install signal poles with a slight rake by plumbing the side of the pole opposite the mast arm just above the base plate.  Tighten the nuts on the anchor bolts as described in subsection 660-3.02k.

Cover the gap between the foundation and base plate by installing a metal skirt around the base plate, secured with stainless steel sheet metal screws.

3.	Vehicular Signal Head Installation.  With two piece mast arms, do not install signal heads within 12 inches on either side of the slip type field splice.

Attach each side mounted terminal compartment with two ½” x 13 bolts, with washers, threaded into holes tapped into the side of the pole at the location shown on Standard Drawing T-30.  Install the vertical pipe members plumb.

When installing 5 section vertically stacked signal heads on the sides of poles, secure the vertical pipe to the pole using a steel conduit hanger mounted 6 inches below the top horizontal pipe.

Aim through phase vehicular signal faces at a point located a distance from the face as shown in Table 660-2.  If two through signal faces are not visible from this point at a height of 42 inches above finished grade, consult the Engineer for corrective measures.

| TABLE 660-2 |  |
| --- | --- |
| THROUGH PHASE SIGNAL FACE AIMING POINTS |  |
| 85th Percentile Speed (mph) | Minimum Visibility Distance (feet) |
| 20 | 175 |
| 25 | 215 |
| 30 | 270 |
| 35 | 325 |
| 40 | 390 |
| 45 | 460 |
| 50 | 540 |
| 55 | 625 |
| 60 | 715 |

4.	Pedestrian Signal and Push Button Installation.  Orient pedestrian signal faces at the center of the crosswalk on the opposite side of the street.  Attach each clamshell bracket with two ½” x 13 bolts threaded into holes tapped into the side of the pole.  Install a spacer, furnished by the bracket manufacturer, on each bolt.

Install the push button on the crosswalk side of the pole.  Install R10-4B (R or L) push button signs above each push button.  Furnish signs with the arrow pointing in the direction of the appropriate crosswalk.  When channel is used for mounting push button signs, tap the top and bottom sign bolts into the pole.

Install an R10-101 sticker, The Meaning of Pedestrian Signals, on each pole with one or two pedestrian push buttons.  With two pedestrian push buttons on a pole, install the sticker between and above the R10-4B signs.  With one pedestrian push button, install the sticker directly above the R10-4B sign.

5.	High Tower Lighting System Installation. Assemble and install high tower poles according to the written instructions furnished by the manufacturer.  To assemble and install poles other than as recommended, furnish a Plan stamped by a registered professional engineer to the Engineer for approval.  Furnish timbers required to assemble the pole, regardless of the method of assembly.

Position the pole during assembly to avoid moving the pole on the ground when lifting the pole to install it on its foundation.  When conditions around a foundation preclude assembling the pole on site, assemble the pole as close as possible to the foundation and move the pole into position for installation on its foundation.  Before moving a pole, submit a Plan stamped by a register professional engineer for moving poles without damage to the Engineer for approval.

Install the lowering system including masthead assembly, luminaire ring, winch assembly, and cables as instructed by the manufacturer’s on site representative.

Install and level the luminaires according to the manufacturer’s written installation instructions.

Furnish the Engineer an instruction sheet from the manufacturer for orienting reflectors in luminaires that provide an asymmetrical light distribution.  Adjust the luminaire reflectors on each pole according to this sheet until they are oriented in the same direction and distribute light according to the pattern shown on the illumination sheets.

Use steel templates to accurately locate and hold the anchor rods plumb and in proper alignment during concrete placement.  Leave this template in place for at least 24 hours after completing concrete placement.  The Engineer will reject foundations with anchor rods that are out of position or more than 1:40 out of plumb.  The Department does not allow bending of anchor rods to plumb the ends or to move them into position, or altering a pole’s base plate to match the anchor bolts.

Tighten the nuts that secure high tower lighting poles to concrete foundations according to the following procedure.

Thread nuts onto the anchor rods to within 1 inch above the top of the concrete base and adjust them downward, if necessary, to provide a minimum ¼ inch projection of the rod above the top of the top nut in the tightened position.  Adjust nuts until their tops form a level Plane.  Install one washer on top of leveling nuts and, after setting the pole on these washers, install one washer under top nuts.

Bring leveling nuts (bottom nuts) to full bearing on the bottom of the base plate.

Apply beeswax to the top nut bearing face and top nut internal threads before threading it onto the anchor rod.  Tighten top nuts to a “snug” condition.  Use a click type torque wrench to apply 600 foot-pounds of torque to the “snug” top nuts.  Torque the top nuts in the following crisscross pattern.

After torquing the top nuts, use a hydraulic wrench to rotate top nuts an additional one sixth (60o) turn, while preventing the leveling nuts from turning.  Use the crisscross pattern shown above.

6.	Underpass Lighting System Installation.  Mount the luminaires as detailed on the drawings to orient the axis of the lamp perpendicular to the axis of the underpass.

7.	Flashing Beacon Installation.  When the Plans specify using the flasher in a signal controller cabinet to energize beacons, furnish a two pole, fused block with built in fuse pullers and two fuses to protect the flasher.  Furnish and leave 5 feet of cable in the cabinet.  Others will install the fused block and terminate the beacon cables.

8.	Wood Pole Installation.  Place the poles in the ground to at least 6 feet deep.

After setting each pole in the ground, backfill the space around the pole with selected earth or sand, free of rocks 4 inches and larger, or deleterious material. Place the material in layers approximately 4 inches thick and thoroughly compact them with mechanical tampers.

Furnish poles that provide a minimum vertical clearance of 21 feet between the pavement and low point of overhead conductor.

660-3.09 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this subsection in its entirety and substitute the following:  This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract.  The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If the existing lighting systems is not kept fully operational as specified herein, the Engineer will reduce the payments under Item 660(22) Illumination Price Adjustment.

Furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities at the Preconstruction Conference.  Make this person available at times until the date of Acceptance for Traffic and Maintenance and provide labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When beginning work, the Engineer will notify the Contractor and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing equipment damaged before the transfer of maintenance responsibility.  Therefore, before starting work on the project, inventory the condition of the existing equipment with the Engineer and document the damaged and defective equipment.  If beginning work before providing the Engineer with an inventory, the Contractor waives the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep components of the existing and temporary electrical systems operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems.  The Engineer will consider these systems operational when no damaged or defective equipment is found in service, components are clean, located, and aligned as specified herein, and photoelectric controls operate the lighting systems.  The State will pay for electricity used to operate the systems, if the public benefits from their operation.  Furnish replacement equipment compatible with equipment used in the Central Region.

Begin work to repair, replace, adjust, realign, clean, and/or relocate components of an affected system within one hour when ordered by the Engineer.  If work is not complete, the Engineer may have outside forces complete the repairs and deduct the amount billed from monies due the Contractor.

Records.  When working on a traffic signal system, print a record of work performed in the diary found in each controller cabinet.  Make sure each entry includes

1.	The dates and times beginning and completing work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours traffic restrictions allowed in subsection 643-3.08, Construction Sequencing.  During shutdowns, use flag persons to control traffic.  Provide local traffic enforcement and maintenance agencies 24-hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day the Contractor retires the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever reducing clearance from the traveled way to less than 6 feet.

Alignment.  During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches according to the following:

1.	For overhead signals located 53 feet and more from the stop line, maintain 17.5 feet to 21.5 feet of clearance between the traveled way and the bottom of each signal.  For closer signals refer to the MUTCD for maximum clearances.

2.	For side mounted signals, maintain nine feet to 11 feet of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	When the horizontal angle to the side mounted far right signal exceeds 20o, relocate this signal to an overhead location.  Measure the angle 10 feet back from the stop line on the lane line between the two farthest left through lanes.

i.	With two or more through lanes, center one signal head over each lane.

ii.	With one through lane and protected permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane.

iii.	Otherwise, install the relocated signal 8 feet to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 7 to 9 feet between the traveled way and the bottom of each pedestrian signal.

7.	Aim signal heads according to Table 660-2 found in subsection 660-3.08, Signal and Lighting Structures.

When no longer required, salvage original and Department provided equipment according to the Plans and item 6.  Salvaging or Reusing Electrical Equipment found in subsection 660-3.01, and remove other materials used in the temporary systems from the project.

Add the following subsection:

660-3.11 MANUFACTURER ASSISTED STARTUP.

The Contractor shall retain the services of a representative from the controller equipment manufacturer (Manufacturer’s Representative), subject to the approval of the Engineer. The Manufacturer’s Representative shall have previous experience with either the Central Region DOT&PF or Northern Region DOT&PF in assisting with traffic signal controller testing, field testing and turn on.  Submit name(s) and professional credentials at least thirty (30) days before commencing this work.  All work on, and connections to, the controller unit, amplifiers, and related equipment shall be performed by or directly supervised by a qualified person serving as the Manufacturer’s Representative.

Required Credentials of Manufacturer’s Representative

- 10 years experience  working in the traffic controller industry, 5 years of that must have been as a signal technician.

- Previous experience with either Northern Region ADOT or Central Region ADOT assisting with traffic signal controller testing and turn-on.

- Familiarity with both the NEMA TS1 and TS2 specifications

- Experience setting up video detection

- Competent to program the Controller Unit

- Competent to program the MMU permissive card

- Competent to implement and adjust timing Plans

- Competent to read cabinet wiring diagrams and troubleshoot cabinet components

- Competent to troubleshoot interconnect cable

- Competent to test inductive loop detectors and setup detector amplifiers

- Competent to conduct training on installed components

The Manufacturer’s Representative will provide oversight and supervision of on-site controller cabinet preparation. This work includes:

- Loop Detector Wiring.  Contractor and the Manufacturer’s Representative will test and inspect the connection of all paired loop detector conductors to the terminal blocks.

- Control Cable Wiring.  Contractor and the Manufacturer’s Representative will connect all control cables within the controller cabinet to the terminal blocks.

- Interconnect Wiring. Contractor and the Manufacturer’s Representative will test and connect all interconnect wiring to the terminal blocks.

- Labeling.  The Contractor will label all wiring according to these specifications.  The Manufacturer’s Representative will verify and check all labeling before any functional testing of the signal heads.

Upon completion of the controller cabinet preparation the Contractor and Manufacturer’s Repetitive shall submit a schedule for controller programming, detector testing, installation field-testing, signal turn-on and training of Department personnel to the Engineer for approval.  Once approved the Manufacturers Representative shall:

- Review timing Plans provided by the Engineer.  The Manufacturer’s Representative may recommend adjustments to timing to be considered and accepted by the Engineer.

- Program the controller unit based upon the accepted timing Plan.

- Connect the programmed controller unit and electronics accessories in the cabinet as required to make the signal fully operational.

- Oversee field testing. Field testing shall be coordinated with the Engineer to allow participation by Department staff. Field testing shall be scheduled so that the turn-on day is preceded by 1 to 5 days of flashing operations once field testing is satisfactorily completed. Flashing operations can immediately follow acceptable field testing.

- Oversee the change of the signal from flashing operations to fully actuated operations

- Place current timing Plans in the controller cabinet by the close of business the day the signal is turned on.

- Provide intersection diagrams compatible with the Aries software.

- Be available for on site timing adjustments for a minimum of 24 hours after signal turn-on.

Test Reports. Contractor and the Manufacturer’s Representative will provide the Engineer with reports detailing test procedures and results of test. The report will include at a minimum;

- Inductive Loop Test including measured values of Inductance, continuity and insulation resistance.

- Proper signal display illumination

- Proper pedestrian display illumination

- Correct number of signal faces per phase

- Proper signal head alignment

- Proper functioning of pedestrian buttons

- Proper functioning of EVP system

- Flash programming correct

- Ensure ped indication black during flash

- Conflicting traffic control signs removed

Add the following subsection:

660-3.12 TELEPHONE SERVICE.  The contractor shall provide telephone service to the master traffic signal controller cabinet. A master traffic signal controller cabinet is any cabinet in which there is an on-street master traffic signal controller such as the Econolite ASC/2-1000 or Traconex TMM-500. The telephone service shall be active inside the cabinet prior to Manufacturer Assisted Start-up. The contractor is financially responsible for the telephone until 100% completion of the Communication System Pay Item. The Telephone Service will not be paid for directly but will be subsidiary to the Traffic Signal System Complete or Traffic Signal Modifications pay item.

Run 6PR19 telephone wire in 1 inch HDPE conduit between the NID and the cabinet. The telephone service must be terminated inside the master traffic signal controller in an RJ11 telephone jack. The contractor is responsible for coordination with the local telephone company to activate service.

660-4.01 METHOD OF MEASUREMENT.  Add the following:

Item 660(22), Illumination Price Adjustment.  By the mile for each roadway with all or part of its illumination system inoperative.  A divided roadway is considered one roadway.  Ramps are considered a separate roadway.  The Engineer will measure each unlit section less than one mile long as one mile.

660-5.01 BASIS OF PAYMENT.  Add the following:

660(1X) Traffic Signal System Complete Includes all labor, equipment and materials required to provide a fully functional traffic signal including but not limited to:

General Construction Requirements, Foundations, Conduit, Junction Boxes, Wiring, Bonding and Grounding, Signal and Lighting Structures, Maintaining Temporary and Existing Electrical Systems.

Traffic Controller Assemblies, traffic controller assembly testing & preparation, vehicle and pedestrian indications, emergency vehicle preemption systems, auxiliary & test equipment, on-site manufacturer-assisted turn-on, 2-year equipment warranty and, required training.

All equipment must be new and not remanufactured or rebuilt.

660(17X) Traffic Signal System Modifications Includes all labor, equipment and materials required to implement modifications to an existing traffic signal. This item may include any of the items included in the Traffic Signal System Complete item.

The amount bid for an item shall include full compensation for:

- Excavation, bedding, and backfill to install the components shown in the Plans.  Dewatering excavations is subsidiary to completion of the excavation work.

- Removing and repairing existing improvements to complete the work, unless other items in the contract cover the repairs.

- Work associated with installing loop detectors, including:  saw cutting, asphalt removal, aggregate base course, tack coating, and installing new asphalt concrete.

The Engineer will pay for the disposal of surplus and unusable excavation and for imported backfill and bedding material at respective contract unit prices, or as extra work if the contract does not include these items.

The cost of repairing damage to finishes on new equipment is subsidiary.

The cost of maintaining the existing and keeping the temporary electrical system fully operational is subsidiary to 660 items included in the Contract.

For each mile of roadway with existing lighting systems that is not kept fully operational, the Engineer will deduct $1275.00 per day from the payments due the Contractor.

Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 660(1A) Traffic Signal System Complete at Parks Hwy and Lucille St | Lump Sum |
| 660(1B) Traffic Signal System Complete at Parks Hwy and Weber Dr | Lump Sum |
| 660(1C) Traffic Signal System Complete at Lucille St and Nelson Rd | Lump Sum |
| 660(7A) Temporary Signal System Complete at Parks Hwy and Main St | Lump Sum |
| 660(7B) Temporary Signal System Complete at Parks Hwy and Lucus Rd | Lump Sum |
| 660(7C) Temporary Signal System Complete at Parks Hwy and Crusey St | Lump Sum |
| 660(7D) Temporary Signal System Complete at Main St and Nelson Ave | Lump Sum |
| 660(7E) Temporary Signal System Complete at Crusey St and Bogard Rd | Lump Sum |
| 660(17A) Traffic Signal Modifications at Parks Hwy and Main St | Lump Sum |
| 660(17B) Traffic Signal Modifications at Parks Hwy and Lucus Rd | Lump Sum |
| 660(17C) Traffic Signal Modifications at Parks Hwy and Crusey St | Lump Sum |
| 660(17D) Traffic Signal Modifications at Main St and Nelson Ave | Lump Sum |
| 660(17E) Traffic Signal Modifications at Crusey St and Bogard Rd | Lump Sum |
| 660(18) Adjust Junction Box | Each |
| 660(20) Highway Lighting System Modifications | Lump Sum |
| 660(22) Illumination Price Adjustment | Contingent Sum |
| 660(27) Flashing Beacon System Modifications | Lump Sum |
| 660(28) Pedestrian Lighting System Complete | Lump Sum |

- R66USC04(4/04/07)(TS-2 version)

- SECTION 661

- ELECTRICAL LOAD CENTERS

- Special Provisions

- Add the following subsection:

- 661-1.02 EQUIPMENT LIST (S) AND DRAWINGS.  Within 14 days following award of the contract, submit 4 collated copies of a portfolio of equipment and material to be installed.  The Department will review these for approval.  The portfolio(s) shall consist of a table of contents that includes each item’s intended use(s) and the following:

- 1.		For materials on the Approved Products List: a description that includes product name, manufacturer, model or part number, and the conditions listed for approval.

- 2.		For materials not on the Approved Products List:  catalog cuts that include the manufacturer’s name, type of product, size, model number, conformance specifications, and supplemented by other data as may be required, including manufacturer’s maintenance and operations manuals, or sample articles.

- This information may be included in the portfolio for 660 items.

- The Department will not be liable for materials purchased, labor performed, equipment used, or delay to the work before equipment and materials have been reviewed and approved.

- 661-2.01 MATERIALS.  Add the following to the paragraph titled Meters: Furnish meter sockets and landing pads rated for 200-ampere services.

- Add the following: Ground Rods.  Furnish one-piece ¾” diameter by 10 feet long copper clad steel rods.

Ground Rod Clamps.  Furnish one piece bronze clamps with a hex head setscrew, that are suitable for direct burial and for use with copper clad ground rods.

Under Photoelectric Controls, delete the first sentence and substitute the following:

Use three wire photoelectric controls that directly switch a circuit from one conductor to another.  Furnish two-piece photoelectric controls that consist of a plug-in photoelectric control unit and a locking type receptacle set in a cast aluminum adapter.

Furnish photoelectric control units that consist of a light sensitive element connected directly to a normally closed, single-pole, single-throw, control relay free of intermediate amplification.  For highway lighting, use horizontal or zenith type sensing units that:

a.	Operate at voltages between 120 and 277 volts AC, 60 Hz,

b.	Handle loads up to 1,800 volt-amperes

c.	Operate at temperatures from -40 °F to +150 °F

d.	Consume less than 10 watts of power

e.	Feature a 3-prong, EEI-NEMA standard, twist-lock plug

f.	Turn-on between 1 and 5 footcandles and turn-off at light levels between 1.5 and 5 times those at turn-on.

Measurements must meet the procedures in EEI-NEMA Standards for Physical and Electrical Interchangeability of Light-Sensitive Control Devices Used in the Control of Roadway Lighting.

Furnish twist lock type, phenolic resin receptacles set in one of the following cast-aluminum adapters.

a.	For photoelectric controls installed on signal poles and load centers, furnish a mounting adapter with a threaded connection that fits conduit outlet bodies threaded for ½ inch rigid metal conduit, General Electric model MB-PECTL or approved equal.

b.	For photoelectric controls installed atop lighting poles (with mast arms), furnish a pole top adapter:  equipped with a terminal block, made to slip over the ends of poles 3½ to 4½ inches in outside diameter, and secured by set-screws, General Electric model PTA-PECTL or approved equal.

Furnish 3-inch wide screens that reach the top of photoelectric control units to prevent artificial light from interfering with normal photoelectric control operation.  Furnish screens constructed of 0.063-inch minimum thick aluminum meeting ASTM B 209, alloy 3003-H14.

Under Equipment List(s) and Drawings, replace item 1 and the last sentence in item 3 with the following:

- Materials on the Qualified Products List: The Qualified Products List does not apply to the 661 items.  Provide catalog cuts of materials to the Engineer for review and approval.

- Materials Not Requiring Certification: Only submit these materials for review and approval if they are included on the Materials Certification List (MCL).

Standard Modification

661-2.01 MATERIALS.  Under Item 2. change title by removing:  “Materials Not on the Approved Products List:” and replace with:  Materials Not on the Qualified Products List:

E36(01/27/07)

661-3.01 CONSTRUCTION REQUIREMENTS.  Delete the 11th paragraph, and substitute the following:  Install two ground rods at least 6 feet apart at each load center.  Connect the neutral bus to the ground rods with a soft drawn bare copper conductor sized per the NEC, 6 AWG minimum.  Bond all non-current carrying metal parts in each load center to the ground bus.  At Type 1 load centers, install one ground rod inside the base, readily accessible though the removable cover, and the second ground rod outside the base.  Route the grounding electrode conductor to the second ground rod through one of the knockouts.

Delete the 12th paragraph, and substitute the following:  Install photoelectric controls at the locations indicated. Orient photoelectric control units to face the north sky.  Install a screen to prevent artificial light from interfering with normal photoelectric control operation.

For photoelectric controls installed on load centers, install a Myers hub in a cabinet wall shielded from traffic.  To the hub, attach an assembly that consists of a type LB conduit body, a length of conduit, and a type C conduit body.  Fabricate the conduit at least 3 feet long and locate the photoelectric control a foot above the top of the load center.  Mount the photoelectric control adapter on the type C conduit body.  Install a conduit hanger to brace the top of the conduit.

For photoelectric controls installed on signal poles, install a Myers hub in the center of the rain cap.  Attach a type C conduit body to the hub with a close nipple.  Mount the photoelectric control adapter on the conduit body.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

- For photoelectric controls installed on electroliers, install a pole top adapter.  When the photoelectric control is on a lighting standard with a slip base or frangible coupling style base, use an approved breakaway disconnect in the base of the light standard.  Restrain the cable in a similar manner as the illumination cable in the pole base.  Use five conductor 14 AWG wire to connect the photoelectric control to the load center.

- 661-5.01 BASIS OF PAYMENT.  Add the following: Payment of fees required by the local authority for an electrical inspection and the costs of correcting the deficiencies noted during the inspection shall be considered incidental to the Section 661 items.

- Work for Pay Item 661(7) Remove Existing Load Center will also include removal of the existing, adjacent junction box.

- Add the following Pay Item:

| - Pay Item | - Pay Unit |
| --- | --- |
| - 661(7) Remove Existing Load Center | - Each |

- Add the following Section:

## SECTION 662

## SIGNAL INTERCONNECT

# Special Provisions

662-1.01 DESCRIPTION.  This item consists of the work required to furnish and install signal interconnect in conduit between the controller assemblies shown on the Plans along the route indicated or on a route as directed by the Engineer.

662-1.02 REGULATIONS AND CODE.  Complete the work according to these Specifications and Section 660, Signals and Lighting.  The Department requires third-party certification for high-density polyethylene conduit.

662-2.01 MATERIALS.  Submit the materials for review and approval per the requirements of item 1. Equipment List and Drawings. of subsection 660-2.01, Materials.

Furnish a 25 pair #19 telephone cable conforming to REA Specification PE-39 for the interconnect cable.  Install the interconnect cable in a 2-inch polyethylene conduit.

Encapsulate completed splices in waterproof re-enterable type splice kits of the same type used for loop lead-in cable splices.  REA Bulletin 344-2 entitled "Lists of Materials Acceptable for use on Telephone Systems of REA Borrowers" provides a list of acceptable splice materials.

662-2.02 POLYETHYLENE DUCT SYSTEM.  Install a polyethylene duct system in which to pull the interconnect cable.  The Department will not permit the installation of the polyethylene conduit in a plowed trench.

Furnish a Type III polyethylene duct made from ultra high molecular weight, high-density, polyethylene (PE) pipe, with a tensile yield strength of 3,200 psi when tested according to ASTM D 638.

Furnish fittings used in the duct system such as elbows, etc. made from the same type polyethylene as the duct.  Fuse connections using the manufacturer’s recommended procedure and equipment.

- Keep junction boxes and ends of conduit covered unless the Contractor is pulling conductors.

Mark underground conduits with a continuous strip of polyethylene marker taped. Furnish marker tape with a black legend on a red background that is 4 mil thick and 6 inches wide.  Install the tape 6 inches below finished grade.

Use care during compaction operations to prevent damage to the junction boxes and conduits.  Remove and replace items damaged during the backfill and compaction operations at no additional cost to the Department.

After testing and installing the conductors, plug conduit openings with duct seal to prevent water from entering the duct system.

662-2.03 JUNCTION BOX.  Furnish pre-cast, reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  Install junction box lids made of cast iron.

662-3.01 CONSTRUCTION REQUIREMENTS.  The signal interconnect consists of cable, conduit, junction boxes, other necessary hardware required to complete the item, cable splicing, and the termination of conductors on terminal blocks.

- Install the polyethylene conduits at least 30 inches below finished grade.

Install junction boxes at all abrupt changes in conduit alignment and on 300-foot maximum centers.  Angle points and curves with delta angles greater than 45 degrees constitute an abrupt change.  Install Type 1A junction boxes, except when the Contractor needs to splice interconnect cables together.  Complete the interconnect cable splices in Type II or III junction boxes.  Complete the splices according to Rural Electrification Administration (REA) Specification PC-2 for splicing telephone cables.  The Contractor may determine the locations for making signal interconnect splices.  The Engineer, however, will not allow splices to be made at low points in the terrain or the bottom of sag vertical curves.  Keep splices in the interconnect cable to an absolute minimum and get the splice locations approved by the Engineer beforehand.

- Furnish the controller cabinets with terminal blocks for the interconnect cable.

662-3.02 EXCAVATING AND BACKFILLING.  Backfill the excavations according to Section 204.

The Engineer will not allow ripping or plowing for installation of conduit.  Backfill around the polyethylene conduit with a 6-inch lift of material free of rocks exceeding a 1-inch maximum dimension.

662-4.01 METHOD OF MEASUREMENT.  The Engineer will measure signal interconnect by the linear foot from the center of junction box to center of the next junction box, following the slopes of the existing ground.

662-5.01 BASIS OF PAYMENT.  The contract unit price paid per linear foot for signal interconnect constitutes full compensation for furnishing all work required to complete the work specified.  Terminal blocks for the interconnect cable shall be paid under Item 660(1), Traffic Signal System Complete. (11/19/02)R67USC02

Payment will be made under:

| ## Pay Item | ## Pay Unit |
| --- | --- |
| 662(1) Signal Interconnect | Linear Foot |

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-1.01 DESCRIPTION.  Delete this subsection in its entirety and substitute the following:  This work consists of furnishing, preparing and placing pavement markings at the locations shown on the Plans or as directed.  Meet these Specifications and the applicable portions of the Alaska Traffic Manual.

670-3.01 CONSTRUCTION REQUIREMENTS.  Delete all paragraphs under item 4. Methyl Methacrylate Pavement Markings. and substitute the following:

a.	General.  All permanent pavement markings shall be installed between May 1, 2008 and June 30, 2008.  Fifteen days before starting work meet with the Engineer for a prestriping meeting.  At this meeting, do the following:

1.	Furnish a striping schedule showing areas and timing of work, placing materials and the Traffic Control Plans to be used.

2.	Discuss placement of materials, potential problems.

3.	Discuss work Plan at off ramps, on ramps and intersections.

4.	Discuss material handling procedures.

5.	Provide copies of the manufacturer’s installation instructions and copies of the Material Safety Data Sheets.

b.	Manufacturer’s Representative.  Provide the services of a manufacturer’s representative (the “Manufacturer’s Representative”).  Ensure the Manufacturer’s Representative observes the application of the pavement marking materials.  Cooperate with the Manufacturer’s Representative and the Engineer to ensure that the materials are placed according to these Specifications and the manufacturer’s recommended procedures.

c.	Manufacturer Certified Installers.  Install methyl methacrylate pavement markings using only striping installers certified by the marking materials manufacturer for the specific striping material and method.  Submit these certifications to the Engineer at the Preconstruction Conference.

d.	Preparation.  Prepare the roadway surface to receive methyl methacrylate according to these Specifications and the manufacturer’s recommendations.  Clean and dry the roadway surface.  Completely remove contaminants such as dirt, loose asphalt, curing agents, surface oils, or existing road marking materials before applying pavement marking material.

e.	Application.  Apply methyl methacrylate marking material according to these Specifications and the manufacturer’s recommendations.  Use equipment designed and capable of properly mixing at the point and time of application and approved by the manufacturer for the type of product being installed.  Unless specified otherwise all markings shall be surface applied as defined below.

For longitudinal markings use truck mounted automatic extrusion equipment capable of installing a double centerline and a single shoulder line in a single pass.  Use automatic bead applicators that place a uniform layer of beads on the lines.  Hand units will not be allowed.

For Transverse markings legends, symbols, and transverse markings use manual or automatic application equipment.  Stencils or extruders are required to form sharply defined markings

For inlaid applications use grooving equipment that produces a dry cut.  Use vacuum shrouded equipment or other equally effective containment procedures.  Install markings in the same work shift as the grooving operation.

(1)	Longitudinal Markings Surface Applied.  Apply markings for lane lines, edge lines, and centerlines to yield a minimum thickness of 90 mils as measured from the surface of the pavement.  Use Type B material, as specified in subsection 712-2.17.

(2)	Longitudinal Extruded Markings Inlaid.  Apply markings for lane lines, edge lines, and centerlines to yield a thickness of 250 mils as measured from the surface of the pavement.  Groove the area for the inlaid markings to a depth of 250 mils.

(3)	Transverse and Symbol Markings Inlaid.  Apply markings for onlys, arrows, stop bars, gore stripes, railroad symbols, and cross walks to yield a thickness of 250 mils as measured from the surface of the pavement.  Use Type C material, as specified in subsection 712-2.17.  Groove the area for inlaid marking to a depth of 250  mils.

(4)	Traverse and Symbol Markings Surface Applied.  Apply markings for onlys, arrows, stop bars, gore stripes, and cross walks to yield a thickness of 120 mils as measured from the surface of the pavement.  Use Type C material.

f.	Disposal of Waste.  Waste material becomes the Contractor’s property.  This includes grindings and removed marking material.  Do not dispose of or store stripe removal wastes material or asphalt grindings on State property.  Dispose of waste material according to applicable Federal, State, and local regulations.

g.	Sampling.  On the form provided by the Engineer, record the following readings, and the locations where they were taken using project stationing, and submit them to the Engineer within 24 hours for evaluation.  Thickness of material and depth of slot are measured from the surface of the pavement.

(1)	For inlay applications, record the depth of the slot every 300 feet during the grinding operation.

(2)	For other longitudinal applications, measure the thickness of the lines (above the pavement surface), at the time of application, every 300 feet.

(3)	For surface applied transverse markings measure the thickness in three locations for each marking.

(4)	Inspect the markings initially, and again two weeks after placement, to ensure the material has cured properly.  Remove soft spots or abnormally darkened areas and replace with material meeting specifications.

(5)	Measure the retroreflecivity of each transverse marking at three locations, and of each line at intervals not to exceed 1,500 feet.  Take these measurements using a Delta LTL2000 Retrometer, a 100 foot retro-reflectometer, or approved similar device.  Perform testing within 72 hours of curing.

The Engineer may elect to use the Contractors readings or perform additional sampling.

670-3.04 PAVEMENT MARKING REMOVAL.  Add the following:  Coordinate removal work with construction activity.  Remove pavement markings the same day permanent markings are applied, unless otherwise directed.  Use vacuum shrouded equipment or other equally effective containment procedures.

Add the following subsection:

670-3.07 TOLERANCES FOR METHYL METHACRYLATE PAVEMENT MARKINGS.

1.	Length of Stripe.  ± 2 inches.

2.	Width of Stripe.  ± 1/8 inch.

3.	Lane Width. ± 4 inches from the width shown in the Plans.

4.	Stripes on Tangent.  Do not vary more than 1 inch laterally within a distance of 100 feet when using the edge of the stripe as a reference.

5.	Stripes on Curves.  Uniform in alignment with no apparent deviations from the true curvature.

6.	All Stripes.  Keep the center of the stripe within 4 inches from the Planed alignment.

7.	Double Stripes.  ± ¼ inches

8.	Thickness of surface applied.  Minimum specified to a maximum of + 30 mils.

9.	Depth of Inlay Slot.  Minimum 250 mils to a maximum of 290 mils.

10.	Thickness of Inlaid Marking Material.  Fill inlay area completely from the bottom of the inlay to the surface of the pavement.

If it is determined that the material is being placed too thin, or otherwise not to specification, make immediate adjustments to correct the problem.

Methyl methacrylate pavement markings applied by any method will be unacceptable if:

1.	The marking is not straight or wide enough.

2.	The thickness of the line is not uniform or less than specified.

3.	The top of the line is not smooth and uniform.

4.	The material is uncured.

5.	The material blackens or is inconsistent in color.

6.	The inlay slot is not ground to the specified depth.

7.	The inlay slot is not filled to the specified depth.

8.	The edge of the markings are not clear cut and free from overspray.

9.	The reflective elements are not properly embedded.

10.	The markings exhibit poor adhesion.

11.	The retro-reflectivity of the markings is less than specified.

12.	The color is not as specified.

Perform repairs using equipment similar to the equipment initially used to place the materials.  Do not perform repairs in a “patch-work” manner.  If more than one repair is required in a single 300 foot section, grind and repair the entire section.

670-4.01 METHOD OF MEASUREMENT.  Add the following:  Thickness will be measured from the top of the marking to the top of the pavement surface.  Marking material placed in a depression left by pavement line removal will not be included in measuring the thickness of the line.

Delete Items 2 and 3 and replace with the following:

2. 	Square Foot Basis.  Transverse pavement marking lines, stop bars, cross walks and gore stripes will be measured by nominal width times actual length.  This does not include 24” wide lines required for Railroad Markings.

3.	Each. Symbol pavement markings only’s and arrow’s will be measured on a unit basis with each separate word or symbol constituting a unit.  Railroad Markings will be measured by the complete unit shown for each lane of travel.

Add the following:

- Foot Basis: Longitudinal Pavement Markings, surface applied or inlaid, will be measured by the linear foot of 4 inch wide line.  Wider striping will be measured in multiples of 4 inches.

670-5.01 BASIS OF PAYMENT.  Add the following:  There will be no separate or additional payment for the following:

	Over-runs of material caused by the variation of the gradation of the asphalt.

	Additional material required to achieve the thickness specified an open graded pavement.

Milling for installation of the inlaid markings is subsidiary to 670 items.  Payment includes costs associated with this item, including the removal of millings.

Traffic control required for the installation of the permanent and temporary markings is subsidiary to 670 items.

Temporary traffic markings required for all phases of the construction of the roadway is subsidiary to 670 items.

Removal of all pavement markings will be subsidiary to 670 items.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 670(10A) MMA Pavement Markings Longitudinal Surface Applied | Linear Foot |
| 670(10B) MMA Pavement Marking Railroad Symbols Surface Applied | Each |
| 670(10C) MMA Pavement Marking Only and Arrow Surface Applied | Each |
| 670(10D) MMA Pavement Transverse Markings Surface Applied | Square Foot |
| 670(10E) MMA Pavement Markings Longitudinal Inlaid | Linear Foot |
| 670(10F) MMA Pavement Markings Railroad Symbols Inlaid | Each |
| 670(10G) MMA Pavement Markings Only and Arrow Inlaid | Each |
| 670(10H) MMA Transverse Markings Inlaid | Square Foot |

(01/04/06)R246USC04

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

###### TABLE 703-2

AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 1 ½ inch | 100 |  |  |
| 1 inch | 70-100 | 100 | 100 |
| ¾ inch | 60-90 | 70-100 | 70-100 |
| 3/8 inch | 45-75 | 50-79 | 50-85 |
| No. 4 | 30-60 | 35-58 | 35-65 |
| No. 8 | 22-52 | 20-47 | 23-50 |
| No. 30 | 10-33 | 10-26 | 13-31 |
| No. 50 | 6-23 | 6-19 | 10-26 |
| No. 200 | 0-6 | 0-6 | 8-15 |

## R199USC04 (06/07/06)

Replace subsection 703-2.04 with the following:

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.

Coarse Aggregate (retained on the No. 4 sieve). Crushed stone or crushed gravel consisting of sound, tough, durable rock of uniform quality.  Remove natural fines passing a #4 sieve before crushing aggregates for Type V or VH asphalt concrete mixtures.  Free from clay balls, organic matter, and other deleterious material.  Not coated with dirt or other finely divided mineral matter.  Meet the following requirements (note A or B indicate class of mix, see Table 401-1), the Engineer may modify the fracture requirements if the hard aggregate sources stated in 106-1.02 do not meet specifications:

|  |  | Type IIA, IV | Type I, IIB, III | Type V | Type VH |
| --- | --- | --- | --- | --- | --- |
| LA Wear, % max | AASHTO T 96 | 45 | 45 | 45 | 45 |
| Degradation Value, min | ATM 313 | 30 | 30 | 30 | 30 |
| Sodium Sulfate Loss % max (5 cycles) | AASHTO T 104 | 9 | 9 | 9 | 9 |
| Fracture, min % | WAQTC FOP for AASHTO TP61 | 90, 2 face | 80, 1 face | 98, 2 face | 98, 2 face |
| Thin-Elongated Pieces, max % 1:5 1:3 | ATM 306 | 8 20 | 8 - | 3 8 | 3 8 |
| Nordic Abrasion, max.% | ATM 312 |  |  | 12 | 8 |
| Absorption, max. % | AASHTO T85 | 2.0 | 2.0 | 2.0 | 2.0 |

TABLE 703-3

BROAD BAND GRADATIONS FOR ASPHALT CONCRETE PAVEMENT AGGREGATE

Percent Passing by Weight

| SIEVE | GRADATION |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Type I | Type II | Type III | Type IV | Type V, VH |
| 1 inch | 100 |  |  |  |  |
| ¾ inch | 80-90 | 100 |  |  | 100 |
| ½ inch | 60-84 | 75-90 | 100 | 100 | 65-80 |
| 3/8 inch | 48-78 | 60-84 | 80-90 | 80-95 | 48-60 |
| No. 4 | 28-63 | 33-70 | 44-81 | 55-70 | 30-45 |
| No. 8 | 14-55 | 19-56 | 26-70 | 35-50 | 20-30 |
| No. 16 | 9-44 | 10-44 | 16-59 | 20-40 | < 22 |
| No. 30 | 6-34 | 7-34 | 9-49 | 15-30 | < 17 |
| No. 50 | 5-24 | 5-24 | 6-36 | 10-24 | < 14 |
| No. 100 | 4-16 | 4-16 | 4-22 | 5-15 | < 12 |
| No. 200 | 3-8 | 3-8 | 3-8 | 3-8 | 3-8 |

(06/05/06)R199USC04

Fine Aggregate (passing the #4 sieve). Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.

For Type IV, V and VH mixes, remove natural fines passing a #4 sieve before crushing aggregates for this asphalt concrete mixture.  Consist entirely of aggregate produced from aggregate crushing process and be non-plastic as determined by WAQTC FOP for AASHTO T 90, and meets the following:

Property	Test Method	Requirement

Fine Aggregate Angularity		AASHTO T 304			45% min.

For Type IV, V and VH mixes, remove all natural fines passing a #4 sieve before crushing aggregates for this asphalt concrete mixture.  Consist entirely of aggregate produced from aggregate crushing process and be non-plastic as determined by WAQTC FOP for AASHTO T 90, and meets the following:

Property			Test Method			Requirement

Fine Aggregate Angularity	AASHTO T 304		45% min.

(06/02/06)matls

SECTION 707

METAL PIPE

Standard Modification

Delete subsection707-2.07 and replace with the following:

707-2.07 GALVANIZED STEEL WATER CONDUIT.  Meet the following:

Galvanized Pipe	ASTM A 53 or ASTM A 120, galvanized according to AASHTO M 111

Galvanized Fittings     ASTM A 234 galvanized according to AASHTO M 232.

E17(06/30/04)

SECTION 712

MISCELLANEOUS

###### Special Provisions

712-2.06 FRAMES, GRATES, COVERS, AND LADDER RUNGS.  Add the following:

Ductile iron castings			ASTM A536 for grade 60-401.

R78M98 (02/22/00)

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS.  Delete the first and second paragraphs under item 1. Quality Requirements: and substitute with the following:  Use a marking material formulated for the application type specified.  Use a marking material manufactured from new materials and free from dirt and other foreign material.  Use a methyl methacrylate based resin system for part “A”.  Use benzoyl peroxide system for part “B”.

Extruded application:  Material formulated for extruded application with factory intermix beads and anti skid aggregate, and additional surface applied beads.

2.	Performance Properties:  Add the following:

l.	Color:	Yellow, PR-1 chart, 33538 Federal Yellow.  White, minimum daylight reflectance of 84.

712-2.18 GLASS BEADS FOR METHYL METHACRYLATE PAVEMENT MARKINGS.  Delete the bead table and substitute the following:  Use the type and amount of beads specified in writing by the marking material manufacturer necessary to meet the performance requirements.

R246USCO04 (01/04/06)

## SECTION 724

## SEED

# Special Provisions

724-2-02. MATERIALS.  Delete Table 724-1 and substitute with the following:

TABLE 724-1

Seed Requirements

FOR CRUSEY STREET IMPROVEMENTS

| Species | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 70 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

R52USC (11/06/02)

#### Table 724-1

#### Type A Seed: Lawn/Grass Requirements

#### For Parks Highway Rehabilitation & Lucille St @ Nelsen Ave Improvements

| Species |  | % Weight | Sproutable Seed* %, Min. |
| --- | --- | --- | --- |
| Arctagrostis latifolia ‘Alyeska’ | Alyeska Polargrass | 10 | 88 |
| Deschampia caespitosa ‘Nortran’ | Nortran Tufted Hairgrass | 10 | 71 |
| Eschscholzia californica | California Poppy | 5 | 90 |
| Lolium sp. | Annual Ryegrass | 15 | 71 |
| Festuca rubra ‘Arctared’ | Arctared Red Fescue | 24 | 78 |
| Poa pratensis ‘Nugget’ | Kentucky Blue Grass ‘Nugget’ | 18 | 76 |
| Poa alpina‘Gruening’ | Gruening Alpine Bluegrass | 18 | 72 |

* Sproutable Seed is the mathematical product of Germination and Purity.

Delete this Section, except for Table 726-1 and substitute the following:

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL.  Furnish topsoil that is representative of the existing, natural organic blanket of the project area.  Perform a quality test, as defined by ATM 201, on the soil to determine the organic content of the soil.  Supply the results to the Engineer.

Soil with an organic content of 5 percent or more may be reused and spread on the finished slopes where topsoil is noted on the Plans.  Remove roots, stumps, unnatural material, and rocks greater than 3 inches in diameter from the organic material before it is graded onto the finished slope.

Soil with an organic content of less than 5 percent cannot be used as topsoil for the project.  In this case, furnish topsoil consisting of a natural friable surface soil without admixtures of undesirable subsoil, refuse, or foreign materials having an organic content of 5 percent or more, as determined by ATM 201.  The material shall be reasonably free from roots, clods, hard clay, rocks greater than 3 inches in diameter, noxious weeds, tall grass, brush, sticks, stubble or other litter, and shall be free draining and nontoxic.  Notify the Engineer of the location topsoil is to be furnished at least 30 calendar days before delivery of topsoil to the project from that location.  The Engineer will inspect the topsoil and its sources before approval will be granted for its use. R208USC (04/01/05)

SECTION 727

SOIL STABILIZATION MATERIAL

### Special Provisions

727-2.01 MULCH.  Add the following:

- Shredded Bark Mulch.  Shredded bark mulch to be placed throughout Planting beds of all newly Planted trees and shrubs, shall consist of aged spruce, fir, hemlock, birch, or aspen wood and bark that is aged at least one year and has a natural deep, dark brown color.  Mulch shall be comprised of a minimum of 70% bark and shall conform to the following gradation:

Screen Designation			Percent, by loose volume

1-inch					    70

Shredded bark mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to Plant growth.  Mulch shall be reasonably free of sawdust, dirt, and twigs.  Mulch shall not contain foreign matter or refuse and shall have the characteristic to be spread evenly so as to form a uniform consistent mat that inhibits weed growth and that will not blow away.

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS.  Add the following item:

7.	Structural Tubing and W-Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 0.2 inch thick walls.  0.4 inch diameter holes shall be drilled as required to permit mounting of the sign.

b.	W-shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized according to 1.b. of this subsection.  Damaged and abraded tubes and beams shall be repaired according to 1.c. of this subsection.

R81USC04 (06/22/04)

## SECTION 740

### SIGNALS AND LIGHTING MATERIALS

Special Provisions

Replace subsection 740-2.02 with the following:

740-2.02 SIGNAL AND LIGHTING POLES.

1.	Design.  Design and fabricate highway lighting and traffic signal structures with pole shaft lengths to 65 feet long to conform to the 1994 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions.  For the design and fabrication of high tower poles, see subsection 740-2.04.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations sealed by a registered professional engineer in the State of Alaska.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for stresses on the completed structure with hardware in place.

a.	In the stamped calculations, indicate the edition of Standard Specifications that the poles are being designed to and provide the input data used to design each pole and mast arm, including:  design wind speed, cross section shape, projected areas, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide design wind speed and the details for building the poles and mast arms, including:  materials specifications, slip fit joint dimensions, pole component dimensions, welds that will be made, and the welding inspection that will be done.

Submit the mill certifications for the steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design poles for 100 mph winds with a 1.3 gust factor.

Design each electrolier to support a sign with an area of 16 square feet with its centroid located 14 feet above the base of the pole.

2.	Fabrication.  Fabricate signal and lighting structures from tapered steel tubes with a round or 16-sided cross section.  Orient hand holes located near the base of poles to face downstream of traffic flow.

Provide traffic signal poles, lighting poles, and signal mast arms in lengths evenly divisible by 5 feet.

Furnish poles and mast arms up to 40 feet long in one piece.  Poles and mast arms longer than 40 feet may be furnished in one piece or in two segments with a slip type field splice.  For slip type joints, provide a minimum overlap of two feet or 1.5 times the inside diameter of the female section whichever is larger.  In mast arms, locate these splices at least one foot away from the Plan location of signal heads and signs.  In signal poles, locate the edge of the female section at least 6 inches above the top of the signal mast arm connection.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.  Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3.  The Department will not accept structures that contain or are made with laminated steel elements.

Fabricate each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent sections to form continuous straight seams from the base to the top of the pole.

When tenons are needed to install traffic signals and luminaires, make them from two-inch nominal schedules 40 pipe that conforms to ASTM A 53 Grade B.

Fabricate 10 feet long signal posts from 11 US Standard Gage sheet steel.  Fabricate each post with a minimum inside diameter of five inches at the base plate.  Use a 3½-inch long piece of four-inch nominal schedule 40 pipe that conforms to ASTM A 53 Grade B as a post-top adapter.

The Department does not allow holes made for lifting purposes in the ends of tubular segments, except in the free ends of luminaire mast arms.  To add lift points, weld them to the tube opposite the longitudinal seam weld on the outside of female segments and on the inside of male segments.  Before shipment, remove lift points added to the outside of the tubes, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a.  Lift points added to the inside of tubes in place may be left in place.

Hot dip galvanize lighting and signal structures to meet AASHTO M 111 and these specifications.  Completely submerge pole and mast arm segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF. Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove all excess zinc from all drip lines and points and the surfaces of all tube ends that form slip type joints to provide a smooth finish.

The Department will reject poles and mast arms that are:

a.	Not fabricated according to these specifications or the approved shop drawings,

b.	Bowed with sweeps exceeding ¾ inch throughout the length of the pole, mast arm, or segment, if furnishing a 2 piece pole or mast arm,

c.	Out of round.  Sections are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

Fabricate pile cap adapters from grade X42 steel line pipe that conforms to API 5L and from steel plate that conforms to ASTM A 709 Grade 50.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Fabricate the anchor plate to match the base plate of the lighting standard.

3.	Welding.  Perform welding to conform to subsection 504-3.01 8.  Welding and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints, the length of the slip fit joint plus one half the diameter of the female section.

b.	Use partial joint penetration (PJP) welds in longitudinal seams.  PJP welds must provide at least 60% penetration.

c.	Use CJP groove welds to connect base plates to tubes with walls 5/16 inch thick and thicker.  When CJP groove welds are used, the designer may use additional fillet welds when deemed necessary.

d.	Use socket type joints with two fillet welds to connect base plates to tubes with walls less than 5/16 of an inch thick.

e.	On steels 5/16 of an inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

f.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT).  If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.  In steels less than 1/8 inch thick, complete the tests according to AWS D1.3.

g.	Only visually inspect welds made on luminaire mast arms.

4.	Miscellaneous.  Finish the edges of poles and mast arms to conform to the following requirements.  Before hot dip galvanizing, neatly round the following features to the radius specified

a.	On holes through which electrical conductors pass, provide a 1/16 inch radius on both the entrance and exit edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus one half the diameter of the female section grind down welds until they feature a radius concentric with the mating surface and remove material protruding from the two surfaces, and

d.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms.  Grinding seam welds on multisided poles is not required, except in slip type joints.

Provide caps to cover the free ends of poles and mast arms.

Identify critical information for poles and arms with visible permanent aluminum tags that contain the information shown in Table 740-1.  The measurements shown are for illustration purposes only.  Use tags large enough to include required information using ¼ inch high text, 3/8 inch of space between successive lines of text, and at least 3/8 inch of space between the edges of the tag and the text.  Secure the tags with two 1/8 inch blind rivets at the base of poles and the under side of mast arms.  If furnishing a two piece signal mast arm with slip type joint, mark both pieces with the same message.

| TABLE 740-1 |  |  |
| --- | --- | --- |
| POLE MARKINGS |  |  |
| Note: Italic type indicates additional Tag Markings if poles have 2 luminaire or 2 signal mast arms. |  |  |
|  | MEASUREMENTS | TAG MARKINGS |
| Signal Poles |  |  |
| a) Signal mast arm length | 45 ft./55 ft. | SMA 45/SMA 55 |
| b) Luminaire mast arm length | 22 ft./18 ft. | LMA 22/LMA 18 |
| c) Pole height | 36 ft. | PH 36 |
| d) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| e) Sum of signal mast arm moments about centerline of signal pole |  | SM 4000/SM 3200 |
| f) Design wind speed | 100 mph | DWS 100 |
| Light Poles |  |  |
| a) Luminaire mast arm length | 15 ft./15 ft. | LMA 15/LMA 15 |
| b) Pole height | 37 ft. | PH 37 |
| Signal Mast Arm |  |  |
| a) Mast arm length | 40 ft. | SMA 40 |
| b) Intersection number (if more than one) -pole number |  | 1 - P 4 |
| c) Sum of signal mast arm moments about centerline of signal pole |  | SM 3740 |
| d) Design wind speed | 100 mph | DWS 100 |
| Luminaire Mast Arm |  |  |
| a) Mast arm length | 18 ft. | LMA 18 |
| b) Pole number (if unique arm design) |  | P 4 |

Replace subsection 740-2.04 with the following:

740-2.04 HIGH TOWER POLES.

1.	Design.  Design and fabricate high tower lighting poles to conform to the 2001 Edition of AASHTO Standard Specifications for Structural Supports for Highway Signs, Luminaires and Traffic Signals with interim revisions.

A registered professional engineer shall design the structures and provide stamped shop drawings and calculations sealed by a registered professional engineer in the State of Alaska.  Submit the stamped drawings and calculations for each pole to the Engineer for approval.  Design for stresses on the completed structure with hardware in place.

a.	In the stamped calculations, indicate the edition of Standard Specifications that the poles are being designed to and provide the input data used to design each pole, including:  design wind speed, cross section shape, yield strengths of the component materials, dimensions of the pole components, and a summary of the loads used.

b.	On the stamped shop drawings, provide the criteria that the poles are designed to and the details for building the poles, including:  materials specifications, slip fit joint dimensions, dimensions of the tube segments and other components, the total weight of each segment, the welds that will be made, and the welding inspection that will be done.

The pole manufacturer shall submit a pole installation plan that details the work required to assemble each pole, the locations of timber supports during and after pole assembly.  Submit this plan with the stamped plans and calculations.

Submit the mill certifications for steel items (piles, plates, bolts, and other related items) to the Engineer for approval.

Design high tower poles for a 50 year design life and the basic wind speed shown in the 2001 AASHTO Standard Specifications for Structural Supports or for 100 mph, whichever is greater.  Use a gust effect factor of 1.14.

For fatigue design, use fatigue category I importance factors for lighting poles, and design poles that taper less than 0.14 inches of diameter per foot to resist the effects of vortex shedding.

Furnish poles fabricated from tapered steel tubes with a round, 16 sided, or 12 sided cross section.  Use no more than four tapered tube segments with slip type field splices to form each pole.  For the slip type joints, provide a minimum overlap of 24 inches or 1.5 times the inside diameter of the female section whichever is larger.

Furnish poles that allow the luminaire ring to descend within five feet of the base plate.

Design poles to support a load that consists of the lowering device and ten luminaires equipped with light shields.  Use the following values for these components.

Component	Effective Projected Area	Weight

One lowering device	8.6 ft2	309 lbs

Ten luminaires	21.5 ft2	617 lbs

Ten light shields	30.0 ft2	22 lbs

2.	Fabrication.  Provide a reinforced rectangular hand hole that provides an opening large enough to install the winch assembly.

Provide a detachable door over the hand hole frame including hinges, nuts to fasten the door to the frame, and a neoprene gasket to provide a watertight seal around the frame. Provide for a locking mechanism for the hand hole door.

Fabricate the reinforced rectangular hand hole to provide maintenance access to the integral luminaire lowering device with a minimum clearance of 12 inches and a maximum clearance of 18 inches between the top of the base plate and the bottom of the hand hole opening.

Fabricate the base plate to match the bolt circle diameter and the quantity and size of anchor bolts of the foundation detailed on the Plans. The anchor bolts conform to ASTM F 1554, Grade 55 with Supplemental Impact Test Requirements of Section S4. The distance from bottom of the leveling nut to the top of the concrete of the anchor bolts will not exceed one inch.

Install a hook to the left of the hand hole for storing the winch control cable away from the top of the foundation.  Provide a 1 inch wide hook that features rounded edges, a 1½ inch radius, and 3 inches between the low point and free end of the hook.

Fabricate tubes with walls up to ½ inch thick from the prequalified base metals listed in AWS D1.1.  Fabricate elements greater than ½ inch thick from steel that conforms to ASTM A 709 and meets the Fracture Critical Impact Test requirements for zone 3.

Fabricate each tube from no more than 2 pieces of steel.  When using 2 pieces, place the longitudinal welded seams directly opposite one another.  Place the welded seams on adjacent segments to form continuous straight seams from the base to the top of the pole.  The Department will not accept poles and mast arms made with laminated steel elements.

The Department does not allow holes made for lifting purposes in the ends of tubular segments.  To add lift points, weld them at least 12 inches away from welds on the outside of female segments and on the inside of male segments.  Before shipment, remove added lift points, grind the area smooth with the base metal, and hot stick repair the finish according to subsection 660-3.01.8.a.

Provide the mounting brackets needed to install the luminaire ring lowering device, including the winch assembly, associated hardware, and the masthead assembly.

Around the top of each pole, provide a stabilizer system that prevents the luminaire ring from swinging freely when the top of the ring is within 24 inches of being fully docked in the masthead fitting.  The stabilizer system shall consist of at least three crooked F shaped brackets located symmetrically around each pole.  The brackets shall form a tapered bottom section and a parallel top section that restricts ring movement.  Bolt each bracket to two channels welded to the pole shaft. With the Eagle lowering device, locate the brackets between the wheels that line the luminaire ring. Design and fabricate the brackets from stainless steel tubing to withstand the load and wind speed used to design the poles.  The installed brackets shall just fit through a circle two inches smaller in diameter than the inside diameter of the luminaire ring.

Notify the Central Region Traffic Design Engineer, at (907)269-0590 five (5) calendar days before start of fabrication of the poles.

3.	Welding.  Perform welding to conform to subsection 504-3.01 8.  Welding and the following:

a.	Make welds continuous.  Grind exposed welds flush with the base metal at slip fit joints, the length of the slip fit joint plus one half the diameter of the female section.

b.	Use CJP groove welds on longitudinal seams within six inches of CJP circumferential welds.

c.	In the ends of those segments that form a slip type joint, provide CJP longitudinal seam welds at least 12 inches longer than the length of the slip joint plus one half times the diameter of the female section.

d.	Use CJP groove welds to connect base plates to tubes.  When CJP groove welds are used, the designer may use additional fillet welds when deemed necessary.

e.	Use socket type joints with two fillet welds to connect the pole top plates to tubes with walls less than 5/16 inch thick.

f.	Use partial joint penetration (PJP) welds in longitudinal seams between the segments of CJP welds.  PJP welds must provide at least 60% penetration.

g.	Use PJP and fillet welds to attach hand-hole frames to the tube.

h.	On steels 5/16 inch thick and thicker, inspect 100 Percent of CJP welds by either radiography (RT) or ultrasound (UT).

i.	Inspect a random 25 percent of PJP and fillet welds by magnetic particle (MT). If a defect is found, inspect 100% of the PJP and fillet welds made to fill the order.

Weld tags on the ends of segments that form slip type joints to facilitate field assembly.  Locate the tags to ensure segment alignment when the tags are aligned.  Attach the tags at least 12 inches away from the slip type joint.  Include the shop drawing number to which the poles are fabricated and pole length on the tag.

4.	Miscellaneous.  Finish poles to meet the following requirements.  Before they are galvanized, neatly round the following features to the radius specified

a.	On holes that electrical conductors pass through, provide a 1/16-inch radius on both edges,

b.	On pole base plates, provide a 1/8 inch radius on edges along which plate thickness is measured and a smooth finish on all other exposed edges,

c.	On the ends of tubes that form slip type joints, complete the following tasks on the two surfaces that contact one another.  First, provide 1/16 inch radii on the inside and outside edges of the female and male segments, respectively.  Then for the length of the joint plus six inches do two things: grind down welds until a radius concentric is feature with the mating surface and remove material protruding from the two surfaces, and

d.	Grind exposed welds flush with the base metal, except fillet welds and seam welds on top of mast arms.  Grinding seam welds on multisided poles is not required, except in slip type joints.

5.	Rejection.  The Department will reject poles containing segments that

a.	Are not fabricated according to these specifications and the approved shop drawings,

b.	Are bowed with sweeps exceeding ¾ inch throughout the length of the segment,

c.	Are out of round.  Segments are out of round when the diameters of round members or the dimension across the flats of multisided members exceed 2 percent of the dimension specified on the shop drawings.

d.	Do not provide the minimum overlap of 24 inches or 1.5 times the inside diameter of the female section, whichever is larger, in the slip type field splices when the pole is assembled.

6.	Galvanization.  Hot dip galvanize pole segments and attachments to meet AASHTO M 111 and these specifications.  Completely submerge pole segments in one dip in a kettle of concentrated zinc ammonium chloride flux solution heated to 130 oF, then completely submerge in one dip in a separate kettle of prime western grade zinc heated to approximately 825 oF.  Galvanize bolts and fasteners to meet AASHTO M 232.

After the poles and mast arms are galvanized, remove excess zinc from drip lines and points and the surfaces of tube ends that form slip type joints to provide a smooth finish.

740-2.05 CONDUCTORS.  Replace Table 740-2 with the following:

| TABLE 740-2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| CONDUCTOR TERMINATION TABLE |  |  |  |  |
| CONDUCTORS | CIRCUIT | WIRE COLOR | AWG. | BAND |
| PER CABLE |  |  | NO. | LEGEND |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red Arrow | Red | 14 | Head No. |
|  | Vehicle Yellow Arrow | Orange |  |  |
|  | Vehicle Green Arrow | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Spare | Black |  |  |
|  | Spare | Blue |  |  |
| 7 | Vehicle Red | Red | 14 | Head No. |
|  | Vehicle Yellow | Orange |  |  |
|  | Vehicle Green | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | White/Black |  |  |
|  | Vehicle Yellow Arrow | Black |  |  |
|  | Vehicle Green Arrow | Blue |  |  |
| 4 | Pedestrian Don’t Walk | Red | 14 | Head No. |
|  | Pedestrian Walk | Green |  |  |
|  | Common Neutral | White |  |  |
|  | Spare | Black |  |  |
| 4 | Pedestrian Pushbutton | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
|  | Spare | Green |  |  |
| 5 | Photo Electric Control | Black | 14 | PEC |
|  | Load to Contactor | Red |  |  |
|  | Neutral | White |  |  |
|  | Spare | Orange |  |  |
|  | Spare | Green |  |  |
| 3 | Flashing Beacon | Black | 14 | Head No. |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Preemption | Black | 20 | “PRE” |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Preemption Confirmation | Black | 14 | “PRECON” |
|  | Neutral | White |  |  |
|  | Spare | Red |  |  |
| 3 | Highway Luminaire | Black | 8 or 6 | Circuit No. |
|  | Highway Luminaire | Red |  | Circuit No. |
|  | Highway Luminaire Spare | White |  |  |
| 3 | Service to Controller | Black | 6 or 4 | “SIG” |
|  | Neutral | White |  | No Band |
|  | Spare | Red |  | No Band |
| 3 | Sign Luminaire | Black | 8 | SIGN |
|  | Sign Luminaire | Red |  | SIGN |
|  | Sign Spare | White |  |  |

Replace Item 5. with the following:

- Detector Loops.  Use No. 14 AWG conductors for detector inductive loops that meet IMSA Specification 51-3, Type RHW/USE, or IMSA Specification 51-5, when called for on the Plans or specified in the Special Provisions.

Replace “6 twisted pairs” in the second sentence of the 4th subparagraph of Item 6. with the following:”7 twisted pairs”.

Replace subsection 740-2.06 with the following:

740-2.06 ELECTRICAL CONDUIT AND FITTINGS.  Unless specified otherwise, use rigid metal conduit and fittings for raceways.  Furnish galvanized rigid type conduit and elbows that conform to UL-6 and are manufactured of mild steel according to ANSI C80.1.  Furnish third party certified fittings designed for rigid metal conduit.

For loop detectors, use Schedule 80 polyvinyl chloride (PVC) conduit that conforms to UL-651.  Use PVC fittings meeting NEMA TC 3.

When polyethylene conduits are specified in the Plans, use a smooth wall, schedule 40, high-density polyethylene (HDPE) pipe that conforms to UL 651 B.

Furnish insulated throat grounding bushings made of malleable iron or steel with a mechanically galvanized or zinc plated finish.  Grounding lugs shall either be an integral part of the bushing or consist of an attached tin plated copper saddle.  Grounding lugs shall feature a stainless steel screw, the centerline of which falls within 20 degrees of conduit centerline.  The bushings furnished shall also feature a stainless steel or brass mounting screw that locks the bushing onto the conduit end.

Furnish conduit outlet bodies and their covers with a hot dip galvanized finish and stainless steel screws.  For loop detectors, furnish type X bodies and, for photoelectric control installation, furnish types C and LB conduit bodies.

When Myers hubs are specified, furnish rain tight, grounding type hubs made of malleable iron with a hot dip or mechanically galvanized finish.

At expansion joints, provide watertight expansion fittings capable of the following movements without damaging the conduits attached to it or the conductors that pass through it.  The movements include:  axial expansion or contraction to ¾ inch, angular misalignments in any direction to 30 degrees, and parallel misalignment of the conduits to ¾ inch.  The fittings shall also include a braided copper bonding jumper equal to an 8 AWG conductor, bushings to prevent scraping the conductors, and a smooth inner sleeve that maintains a constant diameter regardless of conduit alignment.

Replace subsection 740-2.09 with the following:

740-2.09 CONTROLLER ASSEMBLIES. Provide solid-state, traffic controller assemblies having level 2 conformance with the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements as defined in NTCIP1202.,  Traffic Controller Assemblies must meet or exceed all the Environmental Requirements of Section 2 of the NEMA TS2-2003 V02.06 document.

Use traffic control equipment that is compatible with the existing traffic signal monitoring system.  Compatibility must be 100% at the cabinet level to include all inputs, outputs, telemetry protocol, and block upload and download of all RAM data.

The existing traffic signal monitoring system includes the following equipment:

Econolite ASC2/M Master Controller

Aries Zone Manager (version 3.10) by Econolite

In addition, features of the existing local controllers and controller modules must be functionally duplicated to meet or exceed the performance of the existing equipment.

The existing local controller cabinets at other intersections include the following equipment:

Econolite ASC/2-2100

Econolite ASC/3-2100

Use LED indicators for all electronic devices covered under subsections 740-2.09 through 740-2.13.

Replace subsection 740-2.10 with the following:

740-2.10 CONTROLLER UNIT.   Provide solid-state, type A2N Actuated Controller Units (CU) meeting the requirements of Section 3 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements.

- The CU must meet the referenced National Transportation Communications for ITS Protocol (NTCIP) and comply with publication TS 3.2 the Simple Transportation Management Framework, and shall meet the requirements for Conformance Level 2

- The software shall comply with NEMA TS 3.3, the Class B Profile, and shall include both an EIA/TIA 232-E and an FSK modem interface for NTCIP based communications.

- The CU shall implement conformance groups and optional object groups as defined in NEMA TS 3.4 and TS 3.5 for A2N level 2.

740-2.11 CONTROLLER CABINET. Provide a controller cabinet that meets the requirements of NEMA Standard TS 2-2003 V02.06 Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2), Section 5 Terminals and Facilities and Section 7 Cabinets.

- Standard Features. Supply the following standard features:

  - Materials

      - Unless otherwise designated in the Plans, provide cabinets constructed of sheet Aluminum.

  - Cabinet Dimensions

      - Unless otherwise designated in the Plans, provide a size 6 cabinet as defined in NEMA TS-2 Table 7-1.

  - Doors

      - Provide doors meeting the requirements of NEMA TS-2 Section 7.5. The lock must accept a Best CX series core that will be installed by the State after the contract is complete.

      - Provide a Police Compartment meeting the requirements of NEMA TS-2 Section 7.5.7. The Police Compartment shall house the following switches;

        - “flash/automatic” switch that when placed in the “flash” position causes the intersection displays to go into the flashing mode. When placed in the “automatic” position, the signal system must resume normal operation.

        - “signals on/off” switch that when placed in the “off” position removes power from the signal bus. Do not allow power on the bus when either “automatic” or “flash” operation is selected by any means.

      - Permanently label switches in the Police Compartment.

  - Shelves

      - Provide shelves meeting the requirements of  NEMA TS-2 Section 7.6. Provide additional laptop computer shelf mounted approximately 42” above ground level. The laptop shelf must accommodate a standard 17” computer and be retractable below one of the cabinets’ shelves.

  - Finish and Preparation

      - Unless otherwise designated in the Plans, provide unpainted Aluminum Cabinets with a “natural” brushed appearance.

  - Cabinet Mounting

      - Provide cabinet mounting features as defined NEMA TS-2 Section 7.8.

      - The cabinet manufacturer is responsible for providing a cabinet that will mount without modification on the foundation detailed in Alaska Department of Transportation Standard Drawing T-35.00.

  - Cabinet Ventilation

      - Furnish a cabinet that fully meets the requirements of NEMA TS-2 Section 7.9 and the following;

        - Furnish the fan and cabinet vent with internally mounted metal covers that are fabricated to close off the flow of air during winter operation.

        - Equip the cabinet with a selectable, 750/1500-watt cabinet-heating device. The heating device must have a remote air-sensing thermostat. The contacts must be rated 20 amps, 120 volts, 60 hertz.

            - Construct the thermostat so that contacts close on descending temperature and are adjustable between 0 and 30 °F ±5 °F. The contacts must open on rising temperatures of 15 °F above the closing temperature. The adjustment must have an indicating pointer.

            - Connect the thermostat in series with an electrical resistance heater and blower fan. The blower fan must be rated for continuous duty. The heater and fan must be connected in parallel and rated 120 volts, 60 Hertz. Mount the unit in the horizontal position at a location beneath the lowest shelf.

            - Do not block the air intake or outlet. Provide the unit with a SPST manual override switch that bypasses the thermostat to enable the fan and heater to operate at warmer temperatures.

  - Auxiliary Cabinet Equipment

      - Mount a hooded incandescent light fixture with a 15-inch flexible “goose neck” from the cabinet door.  Use a fixture UL rated to accommodate a 25-watt lamp with an integral “ON-OFF” rotary switch mounted on the lamp hood.  Mount a fluorescent lighting fixture on the inside of the cabinet near the front edge.  Use a fixture rated to accommodate an F15T8 lamp operated from a high power factor UL or ETL listed ballast.  The lamp must be included.  The lighting fixture “ON-Off” switch must be a toggle switch mounted on an inside control panel.  Include in the circuit a door-actuated switch that turns the light ON when the door is open and OFF when the door is closed.

      - Provide a resealable print pouch.  The pouch shall be mounted to the door of the cabinet. The pouch shall be of sufficient size to accommodate one complete set of cabinet prints.

      - Provide two paper sets of complete and accurate cabinet drawings with each cabinet. Make cabinet drawings available electronically in AutoCAD v2004 or later format and deliver with paper set.

      - Provide one paper set of manuals for the controller, Malfunction Management Unit and vehicle detector amplifiers with each cabinet. Make said manuals available in electronic Adobe “pdf” format and deliver with paper set.

  - Cabinet Wiring.

        - Neatly arrange the wiring within controller cabinets to conform to the requirements of subsections 660-3.05 and 740-2.05. Furnish all controller cabinets wired to accommodate configuration #4 in Table 5-2 of the NEMA Standards Publications No. TS 2-2003 V02.06, Traffic Controller Assemblies With NTCIP Requirements with two each type 2 detector racks.

          - Equip the cabinet with all required control and auxiliary equipment connecting cables to operate the phases and detection indicated on the Plans, including future use.

          - Size all wiring, switches, surge protectors, flash relays, flashers, etc., to handle the necessary amperage required under full cabinet use. Use orange colored wires to run from the flash transfer relay used for emergency flash programming.

          - Wire the cabinet to accommodate 6 unique preempt sequences as defined by NEMA TS-2 Section 3.7 and 2 auxiliary preempt sequences.  Configure each detector rack to accommodate 4 unique sequences.

        - Field Terminal Blocks.

Provide Terminals and Facilities meeting the requirements of NEMA TS-2 Section 5, Configuration #4 (Table 5-2) and the following:

          - Provide 2 or more insulated terminal blocks to terminate field conductors. Provide each block with 12 poles with 10-32 screw type terminals. Use a terminal block that is a barrier type with removable shorting bars in each of the 12 positions and with integral-type marking strips. Terminate all conductors to a terminal block.

          - Terminate conductors from the controller unit in ring-type terminal lugs or solder them to a through panel solder lug on the rear side of the terminal. Terminate all other conductors in spade-type terminal lugs.

          - Do not bring more than 3 conductors to any one terminal. Two flat metal jumpers, straight or U shaped, may also be placed under a terminal screw. Fully engage at least 2 full threads of all terminal screws when the screw is tightened. Do not extend live parts beyond the barrier.

          - Terminals must be provided to terminate a future 25 pair interconnect cable with each conductor terminated on individual terminals. Terminate all interconnect cable conductors on individual terminals.

          - On the right side of controller cabinets, install two 16-position bus bars, for terminating the equipment grounding and neutral conductors used inside the cabinets.  On the left side of the controller cabinets, install two 32-position bus bars, for terminating the equipment grounding and neutral conductors from field wiring.

  - Cabinet Accessories.

      - See NEMA Standard TS 2-2003 V02.06, Section 5 Terminals and Facilities, Figure 5-4 Cabinet Power Distribution Schematic for items (1) through (4).

        - Disconnecting Means.

              - Main circuit breaker must be a single pole, 50 ampere, 10,000 amperes interrupting capacity for 8 phase cabinets or a single pole, 30 ampere, 10,000 amperes interrupting capacity for 4 phase cabinets.

              - Auxiliary circuit breaker(s) must be single pole, 20 ampere, 10,000 amperes interrupting capacity to protect fan, heater, light and convenience outlet(s).

                - The rating of the main disconnect means with overcurrent protection must be not less than 125% of the maximum anticipated continuous load. When using disconnecting means, use the “trip-indicating trip-free” type.

(2)	Signal Bus. Connect the signal bus to the incoming AC line through a signal bus mercury contactor and an overcurrent protection device. Energize the signal bus mercury contactor to provide power to the signal bus. The current rating of the signal bus mercury contactor must be at least the current rating of the main overcurrent protection device.

(3)	AC Service Transient Suppression. Connect the transient suppression device for the primary feed of the cabinet on the load side of the cabinet overcurrent protection device. The transient voltage suppression device connected to the controller power circuit must provide protection against voltage abnormalities of 1 cycle or less duration.

        - The suppressor must be solid state high energy circuit containing no spark gap, gas tube, or crow bar component. The current rating of the device must be 15 amps minimum. The device must provide transient protection between neutral and ground, line and ground, as well as line and neutral. If the protection circuits fail, they must fail to an open circuit condition. The device must meet all requirements of UL standard 1449.

        - The suppressed voltage rating must be 600 volts or less when subject to an impulse of 6,000 volt, 3,000 amp source impedance, 8.0/20 microsecond waveform as described in UL 1449. In addition, the device must withstand, without failure or permanent damage, one full cycle at 264 volts RMS.

        - The device must contain circuitry to prevent self-induced regenerative ringing. There must be a failure warning indicator light that must illuminate when the device has failed and is no longer operable. The transient suppression device must withstand a 20,000 ampere surge current with a 8x20 microsecond (time to crest x time to second halfcrest) waveform 20 times at 3-minute intervals between surges without damage or degradation to the suppressor. Output voltage must not exceed 500 volts at any time during the test. Use a device that is a solid state, high-energy circuit with no spark gap, gas tube, or bar component.

      - Radio Interference Suppression. Equip each traffic cabinet, flasher, and other current interrupting device with a suitable radio interference suppressor installed at the input power point. Install the radio interference suppressor after the AC service transient suppression unit described in subsection 740-2.11.1.g.(3). It must provide a minimum attenuation of 50 decibels over a frequency range from 200 kilohertz to 75 megahertz, when used with normal installations.

        - The interference suppressor must be hermetically sealed in a substantial metal case filled with suitable insulating compound. Terminals must be nickel-plated, 10-24 brass studs of sufficient external length to provide space for connecting two No. 8 conductors and must be so mounted that the terminals cannot be turned in the case. Ungrounded terminals must be properly insulated from each other and must maintain a surface leakage distance of not less than 1/4 inch between any exposed current conductor and any other metallic part, with an insulation factor of 100 to 200 megohms dependent on external circuit conditions.

        - The radio interference suppressor must have a minimum current rating equal to the rating of the main disconnect means as specified in subsection 740-2.11.1.g.(1). It must be designed for operation on 120 volts, 60 hertz, single phase circuits and be UL and EIA compliant.

        - Connect the ground connection of the radio interference suppressor only to AC neutral. Do not connect to Earth Ground directly.

      - Communications Transient Suppression. Provide a transient suppressor for the system interface communications lines when used. This suppressor must withstand a 100 ampere 10 x 700 microsecond waveform 20 times at 30 second intervals between surges without damage or degradation to the suppressor. Apply the transient surge both line to line and line to ground. Output voltage must not exceed 8 volts line to line and line to ground. Output voltage must not exceed 8 volts line to line or 250 volts line to ground at any time during the test.

      - Control Panel. Provide and label a control panel assembly that is readily accessible from the front of the cabinet. The control panel assembly must consist of:

        - “controller power” switch to energize the controller while the signal lights are off or are being operated by the flasher. Label and rate the switch for load current.

        - An electrical outlet. It must be a duplex, 3 prong, NEMA Type 5-20R grounding type outlet with independent ground fault circuit protection.

        - “auto/flash” switch that when placed in the “flash” position provides flashing operation without interrupting the controller unit power. When the switch is placed in the “auto” position the controller unit must provide normal operation.

        - “stop time/off/on” switch that when placed in the “stop time” position causes the controller unit to stop time. In the “off” position the controller unit must be active regardless of external commands. In the “on” position the timing must be normal but subject to external command interruptions.

        - “heater by-pass” switch to by-pass the remote heater thermostat.

        - momentary contact test switches to place calls on each vehicle and pedestrian phase. Switches must provide tactile feedback and be rated at 1 ampere, minimum, for a resistive load at 120 volts AC and at 28 volts DC. Contacts must be coin silver or gold plated and be enclosed and labeled as to their function.

- Special Features. Provide special features if called for in the Plans or as specified in the Special Provisions

  - Coordination “Remote/Time of Day/Free” Switch. When the switch is in the “Remote” position, all supervisory functions performed on the controller unit from a master coordinator or central computer must operate normally.

When the switch is in the “Time of Day” position, the local controller must use the local coordinators time of day Plan. When the switch is in the “Free” position it must be possible to remove any or all coordination devices and maintain normal, non-coordinated controller operation without wire jumpers, jumper plugs or other special devices. Provide this switch if a local coordination or system modem/interface unit is shown on the Plans.

Replace subsection 740-2.12 with the following:

740-2.12 STANDARD AUXILIARY EQUIPMENT.

Provide equipment meeting the requirements of Section 6 of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Three-Circuit Solid State Load Switches. Use load switches that conform to NEMA TS-2, Section 6.2 Three Circuit Solid State Load Switches and as a minimum be supplied with Light Emitting Diode indicators on the DC input circuitry. The load switch must have 3 independent switching circuits, each being an individually replaceable solid state module.

- Solid State Flasher. Use a NEMA Type III flasher unit that conforms to NEMA TS-2, Section 6.3 Solid State Flashers.

- Malfunction Management Unit (MMU).

Provide Type 16 MMU to be fully compliant with the requirements of NEMA TS-2, Section 4.  In addition the MMU shall have a full intersection LCD back-lighted signal on the front panel and shall be downward compatible with TS-1 CMUs.

4)	Flash Transfer Relay. Use flash transfer relays that meet the requirements of NEMA TS-2, Section 6.4 Flash Transfer Relays.

Replace subsection 740-2.13 with the following:

740-2.13 SPECIAL AUXILIARY EQUIPMENT. Use the following special auxiliary equipment when called for on the Plans and/or Special Provisions:

Provide equipment meeting the requirements of the cited Sections of the NEMA Standard Publication TS 2-2003 V02.06, Traffic Controller Assemblies with NTCIP Requirements (NEMA TS-2).

- Inductive Loop Detectors Units. Provide inductive loop detectors that conform to the requirements of NEMA TS-2, Section 6.5, Inductive Loop Detector Units.  Unless otherwise called for in the Plans provide 4-Channel Inductive Loop Detectors with audible feedback of detection events. The audible feature must be manually switchable between audible “on” and silent “off”.

- Local Coordination Units. Provide actuated coordination that conforms to the requirements of NEMA TS-2, Section 3.6 Actuated Coordination.

- System Modem/Interface Unit. Supply a system modem/interface unit assembly that is compatible with the existing computerized traffic control system.

- Preemption Units. Provide preemption that conforms to the requirements of NEMA TS-2, Section 3.7 Preemption and the following;

Install the following components of the 3M Company’s Opticom Priority Control System according to 3M’s written installation instructions at the signalized intersections listed on the Plans.

- The system must be capable of sending a signal to the controller when an Opticom signal from a vehicle-mounted “3M OPTICOM Emitter” has been received and maintained for a period of 1.7 seconds.

- Use Opticom Priority Control System Model 792H emitters.

- Unless otherwise shown on the Plan use Opticom Traffic Control Systems Opticom Detector Model 721 preemption detectors.

- Furnish the appropriate number of Opticom Traffic Control Systems 752 Phase Selectors to meet the number of channels of detection for each intersection.  Use rack mounted phase selectors.

- When more than one detector is required per phase, furnish the appropriate number of harnesses for the 752 Phase Selectors to handle the auxiliary detection.

- Install Model 138 Optical detector lead-in cable between the end of each signal mast arm and the controller cabinet. Furnish enough slack in these cables for them to extend 2-feet beyond the end of each signal mast arm and to leave 10-feet of slack in the controller cabinet.  Seal both ends of each lead-in cable with mastic lined, heat shrink tubing end caps.

- The controller, rather than the phase selector or auxiliary logic, must perform all interval timing, signal sequences, and phase skips.

- Mount detectors according to manufacturer recommendations or as approved by the Engineer.  Mount and aim all detectors so as to provide maximum emergency vehicle recognition.  Detector locations shown on the Plans are approximate and subject to change as directed by the Engineer.

- Bus Interface Unit (BIU)

Provide BIU’s that fully meet the requirements of NEMA TS-2 Section 8. Unless otherwise called for in the Plans provide BIU’s that meet the NEMA designation BIU2.

6)	Traffic Logging System.  If called for in the Plans, furnish, and install in the controller cabinet, a stand-alone unit that collects, time stamps, and stores data in an unattended manner.

Replace subsection 740-2.14 with the following:

740-2.14 VEHICULAR SIGNAL HEADS.  LED Signal Heads shall conform to the following publications:

- Circular Indications:  Vehicle Traffic Control Signal Heads: Light Emitting Diode (LED) Circular Signal Supplement, 6/27/05  (ITE Publication ST-052)  This is hereafter referred to as “VTCSH-05”.

- Arrow Indications:  Vehicle Traffic Control Signal Heads – Light Emitting Diode (LED) Vehicle Arrow Traffic Signal Supplement Draft, ITE, 4/3/06.  This is hereafter referred to as “VTCSH-Arrow-06”.

“The applicable ITE Specification”, as used in this specification, means VTCSH-05 for circular LED indications and VTSCH-Arrow-06 for arrow LED indications.

Each signal head must: be an adjustable, vertical type with the number and type of lights specified; provide a light indication in one direction only; be adjustable through 360 degrees about a vertical axis; and be mounted at the location and in the manner shown on the Plans. Except for programmed visibility signal heads, all vehicular signal heads installed at any one intersection must be of the same make and type.

- Signal Heads. Use LED optical units for all red, yellow and green indications.

Provide a removable aluminum tunnel visor with an open slot at the bottom for each optical unit. When indicated on the Plans or in the Special Provisions, construct the visor of polycarbonate resin with the color (black) pigment completely impregnated throughout the resin material.

Factory finish signal heads, signal head mountings, brackets and fittings, and outside of visors with 2 coats of dark olive green enamel. Painting is not required where the color is an integral part of the component material. Factory finish aluminum signal visor interiors with 2 coats of flat black enamel.

- Optical Units. Use LED signal modules that meet the requirements of the applicable ITE Specification.  Use one-piece EPDM (ethylene propylene rubber) gaskets to seal LED modules.

- Lens. Use lenses that meet the requirements of the applicable ITE Specification.

- Photometric Requirements. Meet the requirements of the applicable ITE Specification.

- Markings. Permanently mark the back of each LED signal module with the information listed in  Section 3.6, Identification, of the applicable ITE Specification.  In addition, add a label saying “Manufactured according to the ITE LED Circular Signal Supplement”.

- Electrical. Meet the requirements of the applicable ITE Specification. LED signal modules must be operationally compatible with currently used controller assemblies (solid state load switches, flashers, and conflict monitors).

The catastrophic failure of an individual LED in a circular indication, shall not result in the loss of other LEDs. The catastrophic failure of an individual LED in an arrow or pedestrian signal, shall not result in the loss of more than 5% of other LEDs in that signal.

- Testing Requirements.

Burn-in.  Require the manufacturer to energize each new LED module for a minimum of 24 hours at operating voltage and at a temperature of 140F before shipment, to ensure electronic component reliability.

Production Testing and Inspection.  Require the manufacturer to complete the tests in Section 6.3 of the applicable ITE Specification on each signal module.  Submit a manufacturer’s certification of successful completion of all tests with each signal module.

Design Qualification Testing.   An independent test lab with the requisite expertise shall certify that all tests in Section 6.4 of the applicable ITE Specification have been successfully completed.  Submit one such certification per project for each type of LED signal module to be used.  Successful completion of the tests means the LED signal module has met the requirements of Section 3, Physical and Mechanical Requirements, Section 4, Photometric Requirements, Section 5, Electrical Requirements, as well as the requirements of Section 6.4.

Exceptions:  All indications shall meet or exceed minimum intensities after 60 months of continuous use in a traffic signal system.

g.	Warranty. Provide a manufacturer’s written warranty that covers defects in materials and workmanship for the LED signal modules for a period of 60 months. The warranty period will begin on the date the traffic signal satisfactorily completes the functional test prescribed in subsection 660-3.01.7, Field Tests. The warranty period for modules that replace failed modules will begin on the date installed.

Require the manufacturer to replace failed LED modules with new LED modules at no cost to the Department, including the cost of shipping failed modules. The warranty does not include the cost of removing failed modules from or reinstalling new modules in a traffic signal system. Require the manufacturer, upon notification a module has failed, to send the department, via next day delivery, prepaid authorization to return the failed module.

Require the manufacturer to deliver replacement LED modules, within 5 working days of receiving failed modules, to the location designated by the Department.

Submit all warranty documents before installing the LED modules; including the manufacturer’s toll free telephone number for returning failed LED modules.

- Programmed Visibility Signal Heads.

- All indications shall provide a nominal 12-inch diameter circular or arrow indication. Meet the VTCSH requirements for color and arrow configuration.

- Provide each section with a 1-inch cutaway visor.

- Provide each signal section with an adjustable connection that permits incremental tilting from 0 to 10 degrees above or below the horizontal while maintaining a common vertical axis through couplers and mounting axis in 5-degree increments.

- The signal must be mountable with ordinary tools and capable of being serviced without tools. Preset the adjustment at 4 degrees below the horizontal.

- The visibility of each signal face must be capable of adjustment or programming within the face. When programmed, each signal face’s indication must be visible only in those areas or lanes to be controlled. During dusk and darkness a faint glow to each side will be permissible.

- Program the head as recommended by the manufacturer and as directed by the Engineer.

- Housing.

- All parts of the housing, including the doors and end plates, must be of die cast aluminum meeting ASTM B 85, and all parts must be clean, smooth, and free from flaws, cracks, blow holes, or other imperfections.

- The housing of each signal section must be one piece with integral top, bottom, and sides, with square doors.

- All exposed bolts, screws, hinges, pins, and door-locking devices must be stainless steel. All interior screws and fittings must be stainless steel or approved non-ferrous, corrosion-resistant material.

- The top and bottom of each housing must have an opening to accommodate standard 1-1/2 inch pipe fittings and brackets.

- The top and bottom opening of each housing must have an integral serrated boss that will provide positive positioning of the signal head in 5-degree increments so as to eliminate undesirable rotation or misalignment of the signal head as well as between sections. A total of 72 teeth must be provided in the serrated boss. The teeth must be clean and sharp to provide positive positioning with the grooves of the mating section or framework.

- Fasten together individual signal sections with a cadmium-plated tri-stud connector, lockwashers, and nuts with access holes for the passage of electrical conductors from one section to another.

- Each signal housing must have 2 integral hinge lugs located on the left side for mounting the door.

- Provide 1 or 2 latches on the right side of each signal housing with stainless steel wing nut assemblies to engage the door latches.

- Each signal housing must have a door opening with a one-piece EPDM gasket around the periphery to provide a weather tight seal with the mating door.

- Provide the door of each signal housing with a round opening designed to accommodate any standard traffic signal lens.

- Backplates.

Backplates shall not be louvered.  Install backplates around vehicular signal faces except post-mounted flashers.  Furnish backplates constructed of 0.063 inch minimum thickness aluminum alloy sheet meeting ASTM B 209, alloy 3003-H14.  For those backplates fabricated from 2 or more pieces of sheeting, furnish them fastened together with 3/16” aluminum rivets or bolts peened after assembly.

For traffic signals that consist of all 8 inch or all 12 inch signal sections, furnish 5 or 5½ inch wide backplates regardless of where the signals are installed, i.e. on mast arms, on top of posts, or on the sides of poles.

For traffic signals that consist of combinations of vertically stacked 8 and 12 inch signal sections, furnish backplates with nominal borders of 8 inch for the 8 inch sections and 5 inch for 12 inch sections.

Furnish backplates with the back and front faces factory finished with 2 coats of dark olive green enamel and 2 coats of flat black enamel, respectively.

- Signal Mounting Hardware:  Furnish elevator plumbizers, elbow pipe fittings, and post top adapters (without a terminal compartment) with integral serrated contacts that feature 72 teeth.

Provide signal heads that will be mounted on mast arms or pipe tenons with ferrous or bronze elevator plumbizers.

For signal faces installed on the sides of poles, furnish signal frames that consist of watertight assemblies of 1½ inch nominal diameter standard steel pipe, malleable iron or brass pipe fittings, and bronze terminal compartments.  The side of the terminal compartment opposite the door shall feature a saddle shape for wobble free mounting on round poles and include a cable guide and two holes for mounting the compartment.

Furnish vehicular signal frames with a horizontal dimension between the center of the terminal compartment and the axis of the adjacent signal face of 22 inches in side mounted frames and 11 inches in post top installations.

Post top adapters shall slip fit over 4 inch nominal standard pipe and feature two rows of three cadmium plated steel setscrews.  Furnish post top adapters with terminal compartments, except one way signal heads may be installed on adapters without a terminal compartment provided the adapters include offset openings.  Provide post top adapters without a terminal compartment made of cast iron.

Furnish terminal compartments with a terminal block containing 12 poles, each with two screw type terminals.  Each terminal must accommodate at least three 14 AWG conductors.  Provide terminal compartments with a rain tight door that provide ready access to the terminal block.

For mounting each terminal compartment, furnish two ½” x 13 hot dip galvanized bolts that conform to ASTM A 325 and two ½” hot dip galvanized washers that conform to ASTM F 436.

740-2.15 PEDESTRIAN SIGNALS.  Add the following as item 12:  Furnish pedestrian signals side mounted on poles with a 2 piece, hinge connected, cast aluminum clamshell bracket that mounts directly between the pole and the side of the housing.  The bracket shall fit round poles with outside diameters of 4.5 inches and greater without wobbling and allow a minimum rotation of 15 degrees when mounted on a 4.5 inch O.D. pole.  The bracket shall feature a rain-tight terminal compartment and include a 12 position terminal block.  Installed, the bracket shall take less than three inches of space between the housing and pole.

For mounting each clamshell bracket, furnish two ½” x 13 hot dip galvanized bolts that conform to ASTM A 325 and two spacers provided by the bracket manufacturer to keep the bolt head clear of the recess that holds the nut in a through bolted installation.

Replace subsection 740-2.17 with the following:

740-2.17 FLASHING BEACONS.  Furnish beacons that consist of one or more traffic signal sections meeting the requirements of subsection 740-2.14 Vehicular Signal Heads.  See the Plans for the number, size and color of the signal sections required for each beacon.

Use the flasher in signal controller cabinets to energize beacons that flash continuously and are installed near traffic signals.  Otherwise, each flashing beacon controller assembly consists of the following 120 volt ac equipment housed in a NEMA 3R enclosure:  a circuit breaker, a radio interference suppressor, a transient voltage suppressor, a NEMA type 3 flasher, neutral and ground busses, and terminal blocks.

Controller assemblies for school zone speed limit sign beacons shall also include a time switch and a second 120 volt ac circuit breaker that protects a thermostat and heater.

The NEMA 3R enclosure shall feature a single shelf and a top hinged cover with a hasp and staple for sealing and locking the cabinet door.

The radio interference and transient voltage suppressors shall meet the requirements of subsections 740-2.11.1.d.(3) and (4), respectively.

Use a solid state NEMA Type 3 flasher meeting the requirements of NEMA Standard TS 1-1989, Traffic Control Systems.

Use 20 ampere, 600 volt barrier type phenolic terminal blocks with plated brass screw type terminals and integral strips can be marked with a pen or pencil.

Furnish an RTC Manufacturing model AP41-L time switch complete with wiring harness, or an approved, calendar programmable, solid-state time switch with liquid crystal display, keyboard, input/output port, and wiring harness.  The approved time switch shall:

            - Operate on line voltages from 95 to 135 volts ac, operate in temperatures from -22 F to 165 F, and include a capacitor that provides 48 hours of back up power to retain programming and time when the unit is disconnected from ac voltage.

            - Include a backlit display and provide 2 lines of alphanumeric legend with 16 characters per line.  The display shall automatically prompt the operator while programming the device through the keyboard for ease of use.

            - Include an input/output port and keyboard activated special functions that transfer the program to other units and download the program to a printer for a hard copy record of the program.

            - Automatically compensate for changes in Daylight Savings Time and leap years and include a keyboard activated special function to quickly change the dates for the begin and end of Daylight Savings Time.

            - Provide at least 10 basic plans for daily and/or weekly use and at least 200 program steps that are equally divided amongst the actual number of basic Plans.  Each program step shall be assignable to a single day, weekend, weekday, or every day.  The time switch shall also include 20 plans that activate the basic plans to provide one year of time based control.

            - Include at least 4 single pole double throw, relay controlled outputs rated for 15 amperes of resistive load at 115 volts ac.  Each pole shall be independently activated for steady on or momentary on and be manually switched on through the keyboard.

When a signal controller cabinet flasher is used to energize a beacon, furnish a two pole, fused block with built in fuse pullers to protect the flasher.  Furnish third party certified blocks that hold 13/32” x 1-1/2” midget ferrule fuses, are rated for 30 amperes, and feature tubular screw terminals that accommodate conductors to 8 AWG.  Furnish blocks with two fast acting, 3 ampere (BAF-3) fuses and flat bases that can be directly mounted on a dead panel.

Replace subsection 740-2.18 with the following:

740-2.18 ROADWAY LUMINAIRES.  Furnish luminaires that conform the following specifications and provide the light distributions specified.  When luminaire performance criteria are specified, luminaires shall also:

- Meet or exceed the minimum initial light levels indicated.

- Provide light distribution uniformity ratios and veiling luminance ratios equal to or less than the maximums indicated.

When luminaire performance criteria are specified, submit the following information for each luminaire type and light distribution type specified:  luminaire specifications, the lumen output of the lamps that will be furnished, and current electronic photometric data to the Engineer for approval.  Furnish the photometric data in Illuminating Engineering Society (I.E.S.) format.  The Engineer will use software that calculates light levels and uniformity ratios according to the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8 to verify each luminaire provides the light levels, uniformities, and veiling luminance ratios specified.

When cut off distributions are specified, furnish luminaires with flat glass lenses and a full cutoff light distribution as defined in the American National Standard Practice for Roadway Lighting, A.N.S.I./I.E.S RP-8, dated 2000.

Furnish each luminaire with a high pressure sodium lamp of the wattage specified and matching ballast with an input voltage equal to circuit voltage.  Furnish lamps that feature a rated life of 24,000 hours based on 10 hours per start and ballasts that conform to subsection 740-2.21.

Luminiares General

Install luminaires that feature:

1.	Corrosion resistant enclosures with gray paint finish and space for the ballast.

2.	Third party certification for use in wet locations.

3.	Glass lenses, unless polycarbonate resin refractors are specified.

4.	Terminal blocks for attaching the illumination tap conductors.

5.	Aluminum reflectors with an ALZAK or ALGLAS finish.

6.	Optical components free of substances that affect photometric performance, e.g. paint.

7.	Housings cast with no provision for a photoelectric control receptacle.

8.	Airtight reflector and lens units that breathe through activated charcoal filters and include elastomer gaskets to seal the gap between the two components.  Gasket material must withstand the temperatures involved and be securely held in place.

9.	Plug in starting aids in fixtures with lamps through 400 watts.

# Luminaires – Cobrahead

Each cobrahead luminaire shall also include:

- 1.	An easily removed hinged door used exclusively for mounting the ballast.

- 2.	A second door that frames the lens, hinges on the house side, and fastens on the street side with an automatic type latch.

3.	A four bolt mounting brackets that fit 2-inch nominal diameter standard pipe and feature a center pivot for leveling the luminaire.

Offset luminaires shall also include knuckle style pole top adapters that are sized to fit 2 inch nominal diameter standard pipe and feature a wire way meeting NEC requirements for installing three size 10 AWG conductors between the pole and the terminal block located in the luminaire.

High Tower Luminaire.

1.	A 1,000 watt, high pressure sodium lamp that provide 140,000 minimum initial lumens.

2.	A side entry 4 bolt mounting bracket designed for 2 inch nominal diameter pipe with provision for leveling the luminaire.

3.	A die cast aluminum housing attached to the mounting bracket that provides a weather tight enclosure for the ballast and terminal block and is readily removable without removing the luminaire from the bracket arm.

4.	A cover and reflector that readily detaches from the mounting bracket without removing the luminaire from the bracket arm.

5.	A double fused 480 volt ballast with fuses sized by the luminaire manufacturer.

6.	A hinged lens compatible with add on light shields.

7.	A stainless steel lamp clamp to prevent lamps from loosening, that is separate from the socket.

When the Plans specify shielding areas from illumination, install light shields on luminaires on high tower poles whose templates touch the shielded areas.  Provide shields that limit light levels to 0.1 footcandle or less at the right of way line.  Whenever stock shields fail to limit light levels to the 0.1 footcandle level, hire the luminaire manufacturer to custom design and fabricate shields.  If the first generation of custom fabricated shields fail to limit light levels to the 0.1 footcandle level, the Engineer may waive the 0.1 footcandle requirement.

Lenses.

When polycarbonate resin lenses are specified, furnish lenses the fabricator certifies conforms to the following criteria.

1.	The lenses are molded in a single piece from virgin polycarbonate resin.

2.	The lenses are free from cracks, blisters, burns, and flow lines, and furnished with the natural molded surface.

3.	The lenses are of uniform density throughout and free from air, gas, or moisture pockets, and uncured areas.

4.	The lenses are transparent with a clear bluish tint, produced from ultraviolet stabilized resin to reduce the effects of ultraviolet radiation on their color properties.

5.	The resins used meet the requirements for the self extinguishing classification of ASTM D 635 and feature a minimum impact strength, Izod notched of 12 foot pounds per inch when tested according to ASTM D 256, Method A, using a 1/8 inch by ½ inch bar molded according to ASTM recommended practice.

Delete subsection 740-2.20, Illumination Control, in its entirety.

740-2.22 HIGH TOWER LUMINAIRE LOWERING SYSTEM.  Delete this subsection in its entirety and substitute the following:  Furnish an integral luminaire lowering device that is compatible with the high tower design and consists of a head frame assembly, luminaire ring assembly, and winch assembly complete with electric motor.

Provide a technician employed by the lowering device manufacturer, who has a minimum three years experience installing the lowering device, to

1.	Teach each crew that assembles the lowering device how to complete the work on the first pole,

2.	Oversee the assembly work on the next three poles or until the technician can assure the Engineer the crew can correctly assemble the lowering devices,

3.	Teach each crew how to initially adjust each lowering device on the first pole installed,

4.	Oversee the adjustment work on the next three installed poles or until the technician can assure the Engineer the crew can correctly adjust the lowering devices,

5.	Come back to teach each new crew how to assemble and adjust the lowering system components, if the installation crews change, and

6.	Make intermediate and final adjustments to all lowering devices installed under the contract at three, six, and twelve month intervals after the State has accepted the high tower poles.

Furnish a complete service manual with instructions on installation, operation, and maintenance for each lowering device, winch assembly, and power drive system furnished on the project.

Install one of the following high mast lowering devices wired for a single circuit, rated 480 VAC single phase, on each high tower pole shown on the Plans. Furnish all power cords with four #8 AWG conductors.

Furnish each luminaire ring assembly with guide cones (Millerbernd) or tapered positioning pins (Eagle) painted a safety orange color for their full length.  Use a 2 component, water borne epoxy paint with gloss finish that can be applied to galvanized steel and provides a tough, abrasion resistant coating rated for exterior use.  Complete work according to the paint manufacturer’s written instructions, including: preparing the surfaces and tinting, mixing, and applying the paint.

Manufacturer	Model No.	Options to be furnished

Eagle High Mast Lighting Co.	ELC-XX-GV	Hot dip galvanized masthead assembly and transition plate, and integral motor

Millerbernd Manufacturing	SSLD-2	Integral winch and motor

Assembly

High Tower luminaire lowering systems shall meet third party certification.

The Plans will indicate the number of luminaires on each pole, each pole’s height, and whether FAA approved obstruction lights are required.  (10/25/05)R98USC04 (TS-2 Version)

APPENDIX A

PERMITS

APPENDIX B

PARKS HWY MP 42.1 – MP 44 REHABILIATION:

CRUSEY STREET TO LUCUS ROAD

ESCP

APPENDIX C

CRUSEY STREET IMPROVEMENTS

ESCP

APPENDIX D

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX E

ENSTAR EXCAVATION REQUIREMENTS

APPENDIX F

MATERIALS CERTIFICATION LIST (MCL)

APPENDIX G

SIGN FABRICATION DETAILS

APPENDIX H

TEMPORARY CONSTRUCTION EASEMENTS (TCE)

APPENDIX I

QUALIFIED PRODUCTS LIST