# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

- 2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

e.	Cross-sections.

f.	Boardwalk Foundation Investigation memo.

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

- 4.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

PART 4

STANDARD MODIFICATIONS

AND

SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SECTION 101

DEFINITIONS AND TERMS

## Standard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

## Special Provisions

Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material. (11/29/01)R1M98

# SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

# Standard Modifications

# 103-1.01 CONSIDERATION OF BIDS.

Add the following after item 9.: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State. (10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”. (06/25/99)M 69

SECTION 105

CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: Request locates from all the utilities having facilities in the area. Use the locate Call Center for the following utilities:

Locate Call Center Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar AT&T Alascom, Inc. DOT Street Lights, State of Alaska Matanuska Electric Association Matanuska Telephone Association

Call the following utilities and agencies directly:

### Matanuska-Susitna Borough	  745-9804

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the Plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen- (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen- (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.  (05/31/01)R3M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-2.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-2.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

### Standard Modifications

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.  (03/26/01) M 101

Special Provisions

Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this Subsection.

Take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.02  LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

The Plans show several wetland locations in close proximity to the construction limits.  However, the Plans do not delineate all wetlands.  Wetlands exist sporadically along both sides of the Talkeetna Spur Road.  Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by the Contractor’s operations.  These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Department has received the following permits on the Contractor's behalf:

1.	Corps of Engineers Nationwide Permit 23 (#D-2002-0165), issued 03-25-02.

2.	Matanuska-Susitna Borough Floodplain Development Permit (# FHDP 2002-02), issued 5/6/02.

- Corps of Engineers Nationwide Permit 23 only covers a small amount of wetland fill (between stations 71+268 to 71+295 and 71+498 to 71+520).  No other fill is authorized in wetlands areas.  Tracked vehicles are not permitted to work in any wetlands for this project.  This must be taken into consideration when planning for construction of the boardwalk across the Twister Creek wetlands (station 71+295 to station 71+498).

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion and Pollution Control for requirements for this permit.  (05/21/01)R7M98

# 107-1.08 RAILWAY-HIGHWAY PROVISIONS. Delete this Subsection in its entirety and substitute the following:

# SECTION 1.  DEFINITION OF TERMS

ARRC	Alaska Railroad Corporation, P.O. Box 107500, Anchorage, AK 99510-7500.

ARRC Property	All lands owned or withdrawn for the use of the ARRC, including the ARRC's track right-of-way and communications pole line right-of-way.

Chief Engineer	The person employed by the ARRC as head of its Engineering Department or Branch, or his/her authorized representative.

Contractor	Any agent of the Permittee, including Contractors or subcontractors employed to construct, reconstruct, operate and/or maintain the Facility.  The term "Contractor" shall be synonymous with the term "Permittee" when the Permittee performs the construction, reconstruction, operation and/or maintenance of the Facility with its own personnel.

Director, Real Estate	The person authorized by the ARRC to execute contractual real estate agreements on behalf of the ARRC.

Facility 	Any improvements owned by the Permittee/Contractor which are to be placed on ARRC property in accordance with written permission executed by ARRC and Permittee.

Roadway Worker	Any employee of a railroad, or of a contractor to a railroad, whose duties include inspection, construction, maintenance, or repair of railroad track, bridges, roadway, signal and communication systems, electric traction systems, roadway facilities, or roadway machinery on or near track or with the potential of fouling a track.

Telecommunications Supervisor	The person employed by the ARRC as head of its Telecommunications Department or Branch, or his/her authorized representative.

Permittee/Contractor	The person, company or governmental agency to whom the right to enter upon ARRC Property was given in the form of written permit or contract executed by the ARRC and Permittee/Contractor.

Trackwork	All work on the line from the top of subgrade to the top of rail, including geotextile, when required.

Track Materials	All hardware, excluding signals and controllers, associated with the running of a railroad.

# SECTION 2.  GENERAL REQUIREMENTS

2.1	All construction, reconstruction, operation, and maintenance on ARRC Property shall be performed in compliance with these Standard Specifications for Work on Railroad Property, including all revisions thereto.

2.2	Failure to comply with these Standard Specifications for Work on Railroad Property shall result in the demand of ARRC to suspend all work on ARRC Property.

2.3	All work on or about ARRC Property shall be performed by experienced personnel in a safe and workmanlike manner in keeping with approved ARRC practices, and as specified herein.  ARRC traffic and property shall be protected at all times.

2.4	The safety and continuity of the operation of the traffic of ARRC shall be of first importance and shall be at all times protected and safeguarded.  The Permittee/Contractor and its subcontractors shall be required to perform and arrange their work accordingly.  Whenever, in the opinion of the Chief Engineer or his or her representatives, the work or its performance may affect or involve the safety of ARRC's facilities and/or operation of its railroad, the method of doing such work shall first be submitted by the Permittee/Contractor to the Chief Engineer for his/her approval, without which it shall not be commenced or prosecuted.  The approval of the Chief Engineer, when given, shall not be considered as a release from responsibility or liability for any damage which ARRC may suffer, or for which it may be liable, as a result of the acts or omissions of the Permittee/Contractor, its subcontractors or employees.

2.5	Whenever, in the opinion of the Chief Engineer, the construction may cause a hazard to the safe operation of ARRC, ARRC may, in its discretion, place at the site of the work the required number of qualified employees to protect its operations.  The providing of such employees and such other precautions as may be taken shall not relieve the Permittee/Contractor and its subcontractors from liability for the payment of damages caused by their operations.  ARRC shall be the sole judge of the necessity for, and as to the number and classification of employees required. The Permittee/Contractor shall reimburse ARRC for the cost and expense incurred in providing such employees.

# SECTION 3.  SAFETY REQUIREMENTS

3.1	The safety of personnel, property, rail operations, and the public is of paramount importance in the prosecution of any work on ARRC Property.  The Permittee/Contractor shall comply with all Federal, State and local governmental regulations (e.g. OSHA, NESC, etc.) applicable to the construction, installation, or maintenance of any Facility.

As reinforcement and in furtherance of overall safety measures to be observed by Permittee/Contractor (and not by way of limitation), the following special safety rules shall be followed while working on ARRC Property. Further railroad safety information may be obtained from the ARRC Safety Office at 907-265-2440.  Safety information is also available on the ARRC website at www.akrr.com.

3.2	ARRC flag protection is required before any activity can occur on or near a railroad operating facility such as a track, yard, bridge or shop building.  For subsidiary work, such as surveying or inspection, an ARRC furnished flagman will provide a safety briefing prior to the commencement of the work   For any activity involving a disturbance or potential disturbance to the track, track embankment, or any railroad facility, ARRC may require the Permittee/Contractor to submit a specific Railroad Safety Plan prior to startup.   Projects that involve activities that cross the tracks or are longitudinal to the tracks will require a specific Railroad Safety Plan and a one-hour ARRC provided training course for Permittee/Contractor’s project supervisors prior to the initiation of work on ARRC Property.  Specific information on Railroad Safety Plans may be obtained from the ARRC Safety Office at 907-265-2440.

3.3	The Permittee/Contractor shall arrange for ARRC flag protection when performing any work within 6 meters (20’) of any track.  All work within 6 meters (20’) of the track shall cease when a train passes and all Permittee/Contractor employees shall maintain a distance of at least 6 meters (20’) from the track until the train has safely passed.  In addition, any work that could come within 6 meters (20’) of the track will cease when a train passes.  For example, crane or pile driving activities shall stop when trains pass when the maximum boom and suspended load radius can come within 6 meters (20’) of the tracks.  Pile driving shall not be done when trains are passing the work site.  Vehicles and other construction equipment shall not be operated or parked closer than 6 meters (20’) from any track without ARRC flag protection.

3.4	In the event Permittee/Contractor will be performing construction or other activities on or in close proximity to a railroad track, the Permittee/Contractor shall be responsible for compliance with applicable Federal Railroad Administration’s Roadway Worker Protection (“RWP”) regulations (49 CFR 214, Subpart C) if its employees qualify as “Roadway Workers”.  Under 49 CFR 214, Subpart C, railroad contractors are responsible for the training of their employees on these regulations.  All RWP related Work shall be conducted in strict compliance with the RWP safety standards set forth in 49 CFR 214, Subpart C and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any RWP related Work.

3.5	In the event Permittee/Contractor will be performing construction or other activities on a railroad bridge, the provisions of 49 CFR 214 regarding bridge worker safety shall apply.  All bridge related work shall be conducted in strict compliance with the bridge worker safety standards set forth in 49 CFR 214 and the Permittee/Contractor will be required to submit a Railroad Safety Plan to ARRC to demonstrate compliance with said safety standards prior to beginning any bridge related work.

# SECTION 4.  INSURANCE REQUIREMENTS

4.1      	The Permittee/Contractor shall procure and maintain at all times while performing work on ARRC Property, and be covered by the types of insurance with the minimum limits as specified in Section 4.4.

4.2	Each policy specified in Section 4.4 shall be:  (1) endorsed to include ARRC as an additional named insured with respect to the performance of the work; (2) endorsed whereby the insurance company will notify ARRC of any material change, cancellation, non-renewal or expiration of the insurance policy in writing not less than thirty (30) days prior to the effective date; (3) endorsed with a waiver of subrogation rights in favor of ARRC; and (4) endorsed with the Alaska Suit Endorsement.

Prior to commencement of any work on ARRC Property, the Permittee/Contractor shall deliver to ARRC certificate(s) of insurance showing evidence of the insurance required in Section 4.4.

4.4	Alaska Railroad Corporation Minimum Insurance Requirements.

a.	Commercial General Liability insurance with limits not less than $1,000,000 per occurrence and $1,000,000 aggregate for Bodily Injury and Property Damage, including coverage for Premises and Operations Liability, Products and Completed Operations Liability, Contractual Liability, and Broad Form Property Damage Liability. Coverage shall not contain any exclusions of Explosion, Collapse, Underground, or Rail Operations.

b.	Automobile Liability insurance on all owned, non-owned, hired and rented vehicles with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

c.	Worker's Compensation insurance in accordance with the statutory coverage required by the State of Alaska and, where applicable, insurance in compliance with any other statutory obligations, whether State or Federal, pertaining to the compensation of injured employees assigned to the Work, including but not limited to Voluntary Compensation, Federal Longshoremen and Harbor Workers Act, Maritime and the Outer Continental Shelf's Land Act and the Federal Employers Liability Act.

d.	If any part of the work to be performed on ARRC Property is located in close proximity to a railroad track, then the Permittee/Contractor shall also obtain Railroad Protective Liability insurance (Alaska Railroad Corporation as named insured) with limits of liability of not less than $1,000,000 Combined Single Limit for Bodily Injury and Property Damage per each accident or loss.

# SECTION 5.  NOTICE

5.1	A pre-construction meeting shall be held with ARRC's Chief Engineer and representatives of the Permittee/Contractor and subcontractors prior to the commencement of any work on ARRC Property by the Permittee/Contractor or its subcontractors.

5.2	The Permittee/Contractor shall give written notice to the Chief Engineer not less than ten (10) days in advance of the commencement of any construction, reconstruction or major maintenance activity on ARRC Property, in order that the necessary arrangements may be made for the protection of ARRC's operations.  This notice shall include a description of the proposed work on ARRC Property, schedule of work, and the names of any Permittee/Contractor's subcontractor who may also be working on ARRC Property.

# SECTION 6.  FLAG PROTECTION AND PROTECTION OF ARRC TRAFFIC

6.1	Whenever ARRC flag protection is required, it will be provided by ARRC at Permittee/Contractor's expense.  ARRC flag protection is to insure the safe movement of trains and other rail traffic and shall be done in strict accordance with the ARRC rules on flagging.  A minimum of 48 hours prior notice is required for ARRC to provide flag protection.

6.2	ARRC will, during the progress of the work, utilize as many qualified flag people as in the opinion of the ARRC may be required for the adequate protection of ARRC traffic.  All expense for providing such flagpersons shall be paid by the Permittee/Contractor to ARRC.

6.3	The Permittee/Contractor shall arrange with ARRC to keep itself informed on the time of arrival of all trains and shall stop any of Permittee/Contractor's operations which might be or cause a hazard to the safe passage of the train past the site of the work from ten (10) minutes before the expected arrival of the train until it has safely passed.

6.4	Track outages will only be approved in exceptional cases for limited duration’s.  The only outage of the main track will be for installation of the crossings.  Track outages will be:

- Scheduled 30 days in advance

- No more than 12 hours

- Only on Saturday nights

- With 48 hours notice, ARRC may delay the outage by one week.

Prior to a proposed track outage, the Permittee/Contractor shall submit a closure plan to ARRC.  The plan will describe the work to be accomplished, the equipment, manpower and other resources required, and the work schedule.  Once approved by ARRC, the Permittee/Contractor shall follow the plan.  ARRC reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  Permittee/Contractor shall bear all costs and damages which may result from failure to meet the closure schedule, in addition to the train delay charges provided for herein.

# SECTION 7.  TRAIN DELAYS

7.1	All work on ARRC Property shall be conducted in such a manner as to prevent delays to trains or other rail traffic operated by ARRC.  The ARRC will provide a weekly forecast of train traffic and the ARRC flagmen will provide daily updates of anticipated train traffic.  Under no circumstances will the ARRC be liable in any way for delays to the Contractor’s work created by any changes or deviations from anticipated train schedules.

- ANTICIPATED WORK WINDOWS DURING CONSTRUCTION

- ARRC Track Maintenance Work Window: Section and summer work crews may need access into the work area to perform routine track maintenance work and scheduled summer major track replacement work.  The routine track work is performed as necessary for the safe passage of trains.  Railroad on-track equipment also travels through the project as needed.

- Train Traffic: The track through the project is very active.  The approximate number of trains in a 24 hour period is as follows:

- Summer Season - (May 6 to September 24) Approximate Daily Trains

- 2 to 4 Passenger Trains

- Up to 8 Freight Trains

- 1 Coal Train

- Up to 2 Work Trains

- Shoulder - (April 1 to May 5 and September 25 to October 28) Approximate Daily Trains

- Up to 2 Passenger Trains

- Up to 8 Freight Trains

- 1 Coal Train

- 2 Work Trains

- Off Season - Approximate Daily Trains

- Up to 2 Passenger Trains

- Up to 8 Freight Trains

- 1 Coal Train

- 2 Work Trains

- Tracks out of Service: The work shall be planned to minimize track service outages.

- Prior to track outages, submit a closure plan to the Railroad.  The plan shall establish the work to be accomplished, the equipment, manpower and other resources required, and schedule.  Once agreed to by the Railroad, follow the plan.  The Railroad reserves the right to assume control of the work to reestablish rail service if the schedule is not met.  The Contractor will bear all costs and damages, which may result from failure to meet the closure schedule, in addition to the train delay charges provided for in the contract.

7.2	Should any of the Permittee/Contractor's or its subcontractor's actions or activities cause delays to trains or other rail or water traffic, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor by ARRC.

- Passenger trains each:		$50 per minute of delay, 60-minute minimum charge.

- All other rail traffic:		$50 per minute for each delay over five minutes, 30

- minute minimum charge.

- Rail barges, or other

- connecting carrier vessels:	No charge for delays of one hour or less; $1,000 per hour

- for each hour or any part of an hour thereafter with a

- minimum charge of $6,000.

7.3	Delay time will be taken from the train sheet in ARRC’s Dispatcher's Office, Anchorage (907-265-2504) for all delays and such train sheet shall be the official document by which the length of time a train is delayed will be determined.  If another crew is needed to relieve the original crew, the charge shall also apply to the second crew.  If such delay causes a water carrier to miss a sailing, the liquidated damage computation of time covering the period of time to the next possible sailing time shall be in addition to the length of time determined by said train sheet.

# SECTION 8.  PROTECTION OF ARRC COMMUNICATION LINES

8.1	All work on ARRC Property shall be conducted in such a manner as to protect ARRC's communication facilities at all times from outages resulting directly or indirectly from the Permittee/Contractor's or its subcontractor's operations.

8.2	Should any of the Permittee/Contractor or its subcontractor's operations cause outages to said communications facilities, the agreed amount of liquidated damages shall be at the following rates and shall be collected from the Permittee/Contractor:

- Open wire communication circuits:		$1.00 per minute per circuit

- Communication cable:			$1.00 per minute per cable

8.3	A minimum charge of $250.00 will be made for each outage plus the total repair costs.  The outage time shall be that as established by ARRC's Test Board, Anchorage.

8.4	There shall be no equipment operated or excavation made within 4.6 meters (15’) of any ARRC communication pole guy, anchor, or other communications apparatus unless authorized in advance by the Telecommunications Supervisor.

# SECTION 9.  ROAD CROSSINGS

9.1	Whenever automatic railroad crossing signals are in the work area, these signals must remain in operating condition at all times.  If, as a result of the Permittee/Contractor's or subcontractor's activities the signals become inoperable, the crossing shall be continuously flag protected until the signals are again operable.  See Section 6 for flagging specifications.

9.2	When regular railroad crossings are used as haul routes inside or outside the work area, flagpersons shall be provided by the Permittee/Contractor for said crossings in all situations at the discretion of the ARRC.

9.3	Temporary road crossings may be installed provided the Permittee/Contractor has acquired from ARRC a temporary road crossing permit for said crossing.

9.4	The temporary road crossing shall be constructed to the length and the standards specified in the temporary road crossing permit.  All protective signs required by ARRC shall be provided and properly maintained by the Permittee/Contractor.  The temporary road crossing shall be installed under ARRC flag protection in accordance with Section 6 of these specifications.

9.5	The flange ways of all road crossings used by the Permittee/Contractor or its subcontractor as haul routes or temporary road crossings shall be kept clean and free of gravel at all times and shall otherwise be maintained to the satisfaction of the Chief Engineer.

9.6	When a temporary road crossing is in use, ARRC flag protection shall be provided at all times.  See Section 6 for specifications.

9.7	When a temporary or private road crossing is not in use, the Permittee/Contractor shall provide suitable barricades (gates with padlocks, posts driven into the ground, etc.) to prevent vehicular access to the crossing.

9.8	When not in use during the winter season, the temporary road crossing shall be removed.  Upon completion of the work or termination of the crossing permit, the temporary crossing shall be removed and the area restored to its original condition.

9.9	The Permittee/Contractor agrees that all others using the private road crossing, except ARRC and its employees, shall be considered agents of the Permittee/Contractor.

9.10	Sight Triangles at road crossings shall be maintained by Permittee/Contractor free of vegetation and other obstructions to vision in accordance with the table entitled "Sight Triangle Distance" attached and as otherwise established and revised from time to time by ARRC.

9.11	Temporary public road crossings must be included in a traffic control plan submitted by the Permittee/Contractor to Alaska Department of Transportation (ADOT) for review and approval prior to constructing the crossing.

# SECTION 10.  POWER AND COMMUNICATION LINES

10.1	All power and communication lines shall be designed and constructed in accordance with the current edition of the National Electric Safety Code (NESC).

10.2	Underground power and communication lines shall be installed in accordance with Section 11 of these specifications.  Whenever an underground power or communication line crosses underneath a track, a casing pipe shall be installed for carrying such lines.

10.3	The minimum clearance above the top of rail of ARRC track shall be in accordance with the handbook referenced in Section 11.1, plus 152 mm (6”) to allow for future grade raises.

10.4	The minimum clearance above ARRC communication lines shall be in accordance with the handbook referenced in Section 11.1.

10.5	Additional lines may not be added, or the characteristics of the line(s) changed without the prior written approval of ARRC's Director, Real Estate or Chief Engineer.

10.6	Wires shall be strung across ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

10.7	No wires shall be strung across ARRC's communications lines without first receiving prior written approval from ARRC's Telecommunication Supervisor, and such work must be accomplished only at a time and in a manner prescribed by said Telecommunication Supervisor.

# SECTION 11.  UNDERGROUND UTILITIES

11.1	All underground utilities, including culverts, pipelines, and underground power and communication lines, on ARRC Property shall conform to the current American Railway Engineering Association (AREA) / American Railroad Engineering and Maintenance-of-way Association (AREMA) Specifications.

11.2	Unless the Chief Engineer authorizes another method in advance and in writing, all underground utilities shall be installed under tracks and roads by boring, jacking or tunneling.

11.3	Boring, jacking or tunneling shall be done under ARRC tracks only when ARRC flag protection is provided in accordance with Section 6 of these specifications.

11.4	The proposed plan for boring, jacking or tunneling shall be approved by the Chief Engineer prior to commencing the operation.

11.5	All boring, jacking or tunneling headings shall be continuously protected against any loss of ground material by shoring and/or cribbing as necessary.

# SECTION 12.  OPEN TRENCHING

12.1	Only when authorized in advance and in writing by ARRC shall any portion of the track be removed to allow trenching for installation of the Facility.

12.2	If allowed to open trench, the track may be removed from service only at the time authorized by the Chief Engineer and shall be restored to service within the time period specified by the Chief Engineer.  Should the track not be restored to service within the time period specified, the agreed amount of liquidated damages shall be at the rate specified in the written authorization allowing the open trenching or the liquidated damages in accordance with Section 7 of these specifications, whichever is greater, and shall be collected from the Permittee/Contractor.

12.3	All track work shall be accomplished by qualified track persons.

12.4	Only that portion of the track structure necessary to excavate, stockpile and install the Facility shall be removed.  All track material removed shall be handled, stockpiled and relayed in a manner to avoid damage.  Any material that is damaged shall be replaced by the Permittee/Contractor at its own expense.

12.5	The backfill of the trench under the track and in the road bed prism shall be of the same type of material as taken out, except the top 0.6 meters (2’) shall be clean pit run gravel.  Backfilling and compaction shall be in 0.3 meter (1’) lifts with a compaction of 95% of maximum density in the area affecting the road bed prism.

12.6	The ballast used in replacing the track shall be equal in depth and quality as that which was removed.  The track shall be relayed and brought to original grade in accordance with standard ARRC practices.  The track shall be resurfaced as often as necessary for a period of 12 months after completion of construction to remove any settlement that may have occurred.

# SECTION 13.  EXCAVATIONS

13.1	Unless authorized in advance and in writing by ARRC, the top of any excavation shall not be within 6 meters (20’) of the centerline of any track.

13.2	No water shall be allowed to stand in open excavations in the track area.

13.3	Bridging and shoring shall be adequate to safely carry ARRC traffic and the decision of the Chief Engineer pertaining to same shall be final.

13.4	All open excavations shall be continuously protected by flags, flares, barricades or watchpersons, as directed by ARRC.

13.5	No excavation shall be left open more than three days, unless authorized by the Chief Engineer.

13.6	ARRC embankments and cut slopes shall not be disturbed any more than necessary to accommodate the construction and shall be left in a stabilized condition.

13.7	ARRC ditches, culverts and roadways shall be kept clean and free of rock, gravel, construction debris and equipment at all times.

# SECTION 14.  ARRC INSPECTIONS

14.1	ARRC may furnish an inspector during the periods of construction on ARRC Property.  The ARRC inspector will inspect the removal and replacement of tracks, excavation, backfill, necessary bridging for tracks, shoring, flagging, lighting, clearances, etc., when necessary.  The ARRC inspector will work directly with the representative of the Permittee /Contractor and the decision of the ARRC inspector in matters pertaining to ARRC operations and safety shall be final.  In the event more than one shift is worked, an ARRC inspector will be required for each shift.  Presence or absence of an ARRC inspector shall not relieve the Permittee /Contractor of liability for damage done to property of ARRC, or the property of ARRC lessees or permittees having installations on ARRC Property.  All ARRC cost and expense for furnishing said inspector(s) shall be collected from the Permittee /Contractor.

# SECTION 15.  USE OF EXPLOSIVES

15.1	The use of explosives shall be done in compliance with all applicable Federal, State and local laws and ordinances regarding same.

15.2	No blasting of any kind will be permitted unless the Permittee/Contractor thoroughly safeguards the movement of trains and other rail traffic and personnel in the area where such blasting is being conducted.  Before blasting, ARRC flag protection in accordance with Section 6 of these specifications shall be provided on each side of the blast area by the Permittee/Contractor.  This flag protection shall not be removed until the track is inspected for damage from the blast.

# SECTION 16.  SNOW REMOVAL

16.1	Snow removal operations shall be conducted in such a manner as to not place snow (1) upon the tracks of ARRC; (2) where it interferes with the normal operation of the automatic crossing signals; (3) impairs the visibility of either highway or rail traffic at the crossing.

16.2	Snow removal operations shall be conducted in accordance with Section 3 of these specifications.

# SECTION 17.  CLEAN-UP

17.1	At all times, all work and activities on ARRC Property shall be accomplished in such a manner as to keep the ARRC Property in a neat, orderly and safe condition satisfactory to ARRC.

17.2	Upon completion of Permittee/Contractor’s work, all equipment and unused materials shall be removed and the ARRC Property shall be left in a neat and clean condition satisfactory to ARRC.

17.3	Should the Permittee/Contractor or its subcontractor fail to comply with Section 17.1 and 17.2 above, ARRC may perform the required clean-up.  All ARRC costs and expenses for performing this work shall be collected from the Permittee /Contractor.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Delete the sixth paragraph and substitute the following:  Do not use land from any park, recreation area, wildlife or waterfowl refuge, historical site or wetlands, inside or outside the project limits for excess fill, disposal, staging activities, equipment or material storage, or for any other purposes unless allowed by the Contract.  Equipment fording of fish streams may require permits which shall be obtained by the Contractor in accordance with Section 107-1.02.  All vegetation clearing in wetlands shall be done by hand or by brush clearing vehicles equipped with rubber tires.

Add the following: If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (05/21/01)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Add the following before the last paragraph: Where your operations meet any of the following conditions, advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated within 3 m of an overhead electrical line.

2.	Operations anticipated within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15’) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99)R170M98

Standard Modifications

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

### DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report		Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

(01/22/02)S 80

# SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

Ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

## Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03 Submittals. (01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:  The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(2/15/01)R242M98

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor: Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work. (5/31/00)M90

Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e. (02/08/01)M71

## Special Provisions

Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

###### Standard Modifications

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. You will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor. (02/08/01)M71

Special Provisions

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

###### Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgment to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this Subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this Subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this Subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If you fail to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-3.01 GENERAL. Add the following: The construction of mail box installations shall use new posts and mail boxes. Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 530 mm, minimum width of 200 mm and minimum height of 270 mm. Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground. (4/18/00)R74M98

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.  (3/29/01)R84M98

202-5.01 BASIS OF PAYMENT.  Add the following:  Removing pavement in accordance with Subsection 202.-3.05 shall be subsidiary to Item 203(3)

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION. Add the following: Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer. (9/1/89)R20

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work. (03/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

Add the following:  Compact all embankment within 6 meters of retaining walls full width to 100 percent of the maximum density.  Grade all material used within this zone to pass the 75 mm sieve.

203-4.01 METHOD OF MEASUREMENT. Add the following: Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the meter along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT. Add the following: Payment for ditch linear grading will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavation and shaping necessary to complete the work.  (9/1/89)R20

Grading and placement of material used within 6 meters of retaining walls is subsidiary to Item 203(6A) Borrow, Type A.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(17) Ditch Linear Grading | Meter |

SECTION 205

EXCAVATION, BACKFILL AND FOUNDATION

FILL FOR STRUCTURES

# Special Provisions

205-3.03 BACKFILL. Add the following: All backfill placed within 0.3 m of a structural unit shall be graded to pass the 75 mm sieve.

205-5.01 BASIS OF PAYMENT. Add the following: Grading and placement of material used within 0.3 m of structural units will be subsidiary to Item 203(6A) Borrow, Type A.

(7/24/95)R154M

Add the following Section:

SECTION 240

RAILROAD

240-1.01 GENERAL.  The Contractor shall be responsible for all railroad trackwork and construction items associated with this project to the limits shown.  Construct all work on ARRC property in strict accordance with the requirements contained in Section 107-1.08 RAILWAY PROVISIONS of these specifications.  Unless otherwise specified, all track materials and work methods shall comply with the applicable standards contained herein.

240-1.02 SUMMARY OF WORK.  The work involved in this project consists of, but is not necessarily limited to, the following activities:

1.	Remove existing track to the excavation limits shown.

2.	Install new track as specified on the Plans for the trackwork area.

3.	Surface main line tracks and raise to design line and grade.

4.	Install temporary and permanent grade crossings.

240-1.03 DEFINITIONS.

- ARRC. Alaska Railroad Corporation.

- AREA and AREMA.  American Railway Engineering Association and its successor organization, American Railway Engineering and  Maintenance-of-way Association.

- W.C.L.I.B. West Coast Lumberman’s Inspection Bureau.

- FRA.  Federal Railroad Administration.

240-1.04 REFERENCED STANDARDS.

- ARRC  Standard Plans, Ballast and Trackwork.

- AREA/AREMA Manual for Railway Engineering–Fixed Properties.

- AREA/AREMA Portfolio of Trackwork Plans.

All standards listed in each section of these specifications, but referenced thereafter by a basic designation only i.e. AREA/AREMA, form a part of the specifications to the extent indicated by the reference.  The most recent edition of the standard at the time of advertising shall apply.

240-1.05 REFERENCED DRAWINGS.  Alaska Rail Road Standard Drawings shown on sheet A1 of the Plans.

240-1.06 STORAGE.  The Engineer shall designate areas for storage facilities.

240-1.07 CLEAN-UP.  Clean up and leave the job site in a neat condition at the end of each days work shift.  Clean the entire work area to the satisfaction  of the Engineer before calling for a final inspection.

240-1.08 SURVEYING  Furnish all surveying work necessary for the performance of this project.

240-1.09 OWNERSHIP  All tracks and crossing materials replaced by new materials will become the property of the Contractor.

Add the following Section:	SECTION 241

RAILROAD BALLAST

241-1.01 DESCRIPTION. This work consists of furnishing, placing, tamping & shaping railroad ballast and surfacing & lining new/existing track and turnout, in conformance with the lines, grades and thickness’ shown on the Plans.

241-2.01   MATERIALS.  Subballast shall consist of material meeting the minimum requirements of Subsection 703-2.03, AGGREGATE FOR BASE AND SURFACE COURSE, BASE COURSE, gradation C-1.  Prepared ballast shall be crushed shot rock or crushed pit-run rock, size no. 4A, composed of hard, strong and durable particles, free from injurious amounts of deleterious substances and conforming to the following test standards:

TEST	TEST PROCEDURE	TEST STANDARD

Gradation Tests:

Sampling Aggregates	ASTM D 75

ASTM C 702

Sieves with Square Openings	ASTM E 11

Sieve Analysis	ASTM C 136	See table below

Materials Finer Than 0.075 mm (No. 200)	ASTM C 117	See table below

Material Quality Tests:

Bulk Specific Gravity	ASTM C 127	 2.60 min.

Absorption	ASTM C 127	0.5% max.

Magnesium Sulfate Soundness	ASTM C 88

(Five Cycles)	1.0% max.

Clay Lumps & Friable Particles	ASTM C 142	0.5% max.

Flat and/or Elongated Particles	USACE CRD-C119	5.0% max.

Degradation (LA Abrasion)	ASTM C 535	 35% max.

Mill Abrasion	see description below	   9% max.

Abrasion Number	see description below	    55 max.

Fractured Particles	see description below	 80% min.

TYPE 4A

BALLAST GRADATIONS

| Sieve Size | ### Percent Passing |
| --- | --- |
| 63 mm (2-1/2") | 100 |
| 50 mm (2") | 90-100 |
| 37.5 mm (1-1/2") | 60-95 |
| 25 mm (1") | 10-35 |
| 19 mm (3/4") | 0-10 |
| 9.5 mm (3/8") | 0-3 |
| 0.075 mm (No. 200) | 0-0.3 |

- MILL ABRASION TEST DESCRIPTION

A representative sample is obtained and sized using the current ASTM Methods of Test.  From the coarse aggregate, split a representative portion into a sample consisting of 1.5 kg (3.3 lb.) passing the 37.5 mm (1-1/2”) sieve and retained on the 25 mm (1”) sieve plus 1.5 kg (3.3 lb.) passing the 25 mm (1”) sieve and retained on the 19 mm (3/4”) sieve.  The sample shall be washed and oven dried in accordance with the Los Angeles abrasion procedure.  The sample will then be placed in a 3.79 liter (1 gallon) 229 mm (9”) external diameter porcelain ball mill pot, along with 2.99 kg (6.6 lb.) of distilled water.  The mill shall be rotated at 33 rpm for a total of 10,000 revolutions (five hours).  The sample shall then be wash-sieved through a 0.075 mm (No. 200) sieve and oven dried before weighing.  Mill abrasion shall be calculated as a percentage loss in weight by the following formula:

- Mill Abrasion = (Loss in Weight / Original Weight) x 100

- ABRASION NUMBER

The Abrasion Number is a number calculated with the results of the Los Angeles Abrasion Test and the Mill Abrasion Test given in this specification.  The Abrasion Number shall be calculated by the following formula:

Abrasion Number = LA Abrasion Number + (5 x Mill Abrasion Number)

FRACTURED PARTICLES TEST

A representative sample is obtained and sized using current ASTM methods of Test. From each coarse aggregate fraction representing five percent or more of the submitted sample, split a representative portion into samples of within 10 percent of the weight specified below:

| Sieve Passing | Sieve Passing | Mass in Grams (Lbs.) +/- 10 percent |
| --- | --- | --- |
| 63 mm (2 ½") | 50 mm (2") | 5897 (13.00) |
| 50 mm (2") | 37.5 mm (1 ½") | 5307 (11.70) |
| 37.5 mm (1 ½") | 25 mm (1") | 2064 (4.55) |
| 25 mm (1") | 19 mm (3/4") | 590 (1.30) |
| 19 mm (3/4") | 12.5 mm (½") | 177 (0.39) |
| 9.5 mm (3/8") | 4.75 mm (No. 4) | 59 (0.13) |

Each sample shall then be separated into fractured and non-fractured particles according to the following criteria:

A fractured particle shall be a particle with three or more fractured faces.  Each of the fractured faces on the fractured particle must have a freshly exposed rock surface with a maximum dimension of at least one third the maximum particle dimension and a minimum dimension of at least one quarter of the maximum particle dimension.  The included angle formed by the intersection of the average planes of adjoining fractured faces must be less than 135 degrees for each of the faces to be considered as separate fractured faces.

For example, a particle just retained on the 50 mm (2”) screen (i.e. particle size = 50 mm (2”)) must have at a minimum:

1.	a freshly exposed maximum face of between 17 mm (2/3”) and 50 mm (2”),

2.	a second freshly exposed face with a minimum dimension of 13 mm (1/2”),

3.	a third freshly exposed face ranging in dimension between the other two.

The angle formed between any two of these faces must not exceed 135 degrees.

Particles which do not meet the above criterion will be classified as non fractured faces.

The fractured particles for each sample will be calculated as a percentage by the following formula:

Fractured Particles = Weight of fractured particles x 100

Original Weight

Engage the service of a qualified Professional Civil Engineer registered in the State of Alaska to oversee the performance of the referenced test on the rock source and the processed ballast. The professional engineer, or a qualified and experienced technician working under his/her direction, shall perform all sampling and testing.

Take samples of processed ballast directly off the belt to minimize segregation and contamination. Select a testing laboratory to be approved by the AARC to perform material quality tests.

The frequency of tests shall be as follows:

1.	Pre-Manufacturing Tests: Prior to production of ballast, submit whole and crushed samples of the proposed source rock along with test reports that verify that they conform to these specifications.

2.	Start-up Manufacturing Test: When ballast manufacturing begins another full battery of tests shall be run to verify that the ballast manufactured conforms to these specifications.

3.	Periodic Full Testing: Whenever the nature of the source rock changes significantly such that conformance with the specifications is in doubt as determined by the Engineer, the above tests shall be redone as appropriate to verify conformance and the results submitted for approval.

4.	Periodic Gradation Testing: The gradation tests and visual monitoring of degree of fracture shall be performed during manufacturing on every 750 cubic meters (1,000 cubic yards) of ballast that is produced, but at least daily. A complete fractured particle test shall be run on every 4,000 cubic meters (5,000 cubic yards) of ballast manufactured.

Submit all test reports to the Engineer for approval. The professional civil engineer you hire shall verify that all test reports are accurate and shall indicate whether or not they conform to these specifications.  If any tests fail to conform to the specifications, immediately notify the Engineer and take steps to bring manufacturing into conformance.

#### CONSTRUCTION REQUIREMENTS

241-3.01   GENERAL. Manufacture, handle, stockpile and deliver the ballast in such a manner that it is kept clean and free from segregation.  Stockpiling ballast over firm stable base areas.  Stockpile ballast in horizontal layers to minimize segregation.  Do not dump over the sides of the stockpile.  Keep construction machinery and other vehicles from traveling over the top of the stockpile as much as possible.  Keep ballast dumped on subgrade prior to track or turnout construction free from material tracked in by construction equipment.  Uniformly distribute ballast dumped on skeleton track and turnouts during the dumping operation to minimize the carrying or regulating required to provide the designed ballast section.

241-3.02   BALLAST HANDLING.  Keep ballast clean and free from segregation during handling and placing operations.  Submit your plan for handling and placing ballast.  This plan shall include the following:

- source,

- type of equipment to be used,

- location of stockpiles,

- method of distribution.

241-3.03  PLACEMENT OF INITIAL BALLAST.  At your option, an initial layer, or layers, of ballast may be uniformly distributed over the finished sub-ballast and compacted before tie distribution. Limit the initial layer of ballast to a total compacted depth that will establish the track surface at least 50 mm (2”) below final grade. Subgrade fouled or disturbed by the Contractor's operations shall be repaired by the Contractor at no additional cost to State.

- 1.	Each lift of ballast within the initial layers shall be uniformly spread and compacted with not less than two passes of a vibratory compactor with the following characteristics:

- Gross mass (weight)		2,268 kg (5,000 lbs.) minimum

- Drum width			1,448 mm (57”) minimum

- Drum diameter		1,016 mm (40”) minimum

Each compacted lift within the initial layers shall not exceed a depth of 100 mm (4”).

2.	The vibratory compactor shall be capable of applying a dynamic load of not less than 80 kN (18,000 lbs.) at a frequency between 1,100 to 2,000 vibrations per minute. The compacting equipment you select is subject to inspection and acceptance by the Engineer.

241-3.04   SURFACING OF TRACK.  Place the ballast within the limits shown on the Plans with equipment that will not damage the cross ties or the spiking and anchoring holding capacity.

1.	Use vibratory squeeze-type tampers to compact the ballast after final vertical track alignment has been achieved.  Maintain tools to the manufacturer's specifications.  Pack ballast tightly under and around the tie from a point 450 mm (18”) inside each rail on both sides of the tie to the ends of the tie.  Do not compact ballast around the center of the tie between the above limits.

2.	Prepare a detailed tamping procedure specification covering tamping equipment methods for the Engineer's review and approval. The specification shall include a complete description of equipment to be used and variables that can be adjusted such as:

- Number of insertions of tamping tools per tie.

- Number of passes of tamping machine.

- Depth of penetration.

After tamping is complete, regulate ballast to the design section and remove all ballast from the top of cross ties, tie plates and base of rail.  Prepare a detailed raising, aligning, tamping and regulating procedure for the Engineer's review and approval.

241-4.01  METHOD OF MEASUREMENT. Subballast and ballast placed as shown on the Plans will not be measured.

241-5.01  BASIS OF PAYMENT.  The subballast and ballast required for this project is subsidiary to item 245 (1), Modular Crossing and no separate payment will be made.

Add the following Section:	SECTION 242

# TRACKWORK

242-1.01   DESCRIPTION.   This work consists of furnishing and constructing skeleton track to the alignment and limits shown on the Plans.  This work also includes removing existing track and crossing materials at the proposed road crossings.

242-2.01   MATERIALS.   The material shall conform to the current AREA/AREMA "Manual for Railway Engineering" and as detailed in this specification.

1.	New Standard Carbon Rail: Rail shall be 115# RE Rail Section and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends. Rail shall be end hardened, 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

2.	New High Strength Rail: Rail shall be 115# RE Rail Section and have a Brinell Hardness range of 341-388. Rail may be either head hardened or fully heat treated and conform to the latest revision of the AREA/AREMA Manual, Chapter 4, Rail Specifications for steel rail and the ARRC Standard Plan 3.1. Rail shall be drilled at both ends for 6-hole joint bars. Rail shall be 24.4 m (80’) in length per AREA/AREMA Chapter 4, paragraph 2.1.11.

3.	Track Spikes: Use Pandrol screws or approved screws.

4.	Rail Anchors: Use Pandrol clips or approved rail anchors.

5.	Tie Plates: Use Pandrol plates or approved plates.

6.	Angle Joint Bars: Use new 900 mm (36") angle joint bars  headfree, standard toeless, 6 holes for 115# rail with hole spacing to fit rail drilling per ARRC plan 5.12.  Joint bars shall be quenched or medium carbon steel, rolled steel only, heat #16. Hole diameter shall be 31.75 mm (1-1/4").

7.	Track Bolts, Nuts & Washers: Bolts and nuts shall be new and manufactured in accordance with AREA/AREMA Section 4.1.15. Bolts shall be of the appropriate size for the bolt hole of the rail and bar and sufficient length for a full nut, lockwasher and 1 ½ threads exposed after tightening, but not to exceed a 25 mm (1") exposure after tightening. Lockwashers shall be new per ARRC Plan No. 7 and sized for the bolt diameter.

8.	Cross Ties: Cross ties shall be treated 175 mm x 225 mm x 3.0 m (7” x  9” x 10’-0”) per ARRC Standard Plan 1.13.  Cross ties shall be manufactured in accordance with AREA/AREMA Manual for Railway Engineering, Chapter 3; W.C.L.I.B. Grading Rules #17, paragraph 192b; and this specification.  Hardwood ties shall be used.

- Timber: Cross ties shall be sawn from sound, straight live timber, free from any defect that might impair durability and/or strength. Multiples or combinations will not be accepted. Cross ties shall be cut square at the ends and have all bark that impairs treatablility entirely removed.

b.	Stump Pull: Stump pulls will be graded the same as holes or splits in the end of a tie. Cross ties with a stump pull that goes into the interior more than 127 mm (5") will be rejected.

c.	Wane: Cross ties shall have a minimum 203 mm (8”) face. Minimum face specifications apply to the entire length of the cross tie. All wane shall be free of bark.

d.	Knots: A knot exceeding in diameter 1/4 of the width of the surface on which it appears will be rejected if it occurs in the rail bearing area. Outside the rail bearing area, knots will be accepted up to a diameter of 1/3 of the surface on which they appear. A cluster of knots will be judged as being a large knot in damaging effect. Rail bearing area shall be defined as 508 mm (20") to 1,016 mm (40") from center of tie.

e.	Cross Grain: Any cross tie with cross grain exceeding one in fifteen will be rejected.

f.	Straightness: A cross tie will be considered straight when (1) a straight line along the top from middle of one end to middle of the other end is not closer than 76 mm (3") from either side of tie, and (2) when a straight line along a side from middle on one end to the middle of the other end is everywhere more than 63.5 mm (2 ½") from top or bottom of the tie.

g.	Bark: Any cross tie containing more than a minimal amount of ingrown bark will be rejected.

h.	Saw Kerf: A saw kerf is not required.

i.	Mill of Manufacture Certification: A mill certification is required indicating that inspections have been performed and that the product is in conformance with specifications. The mill certification must also indicate the species of wood. All ties which pass the inspection will be clearly marked and identified as ARRC ties; unmarked ties will not be accepted.

j.	Treatment: All treatment shall meet the specifications of the American Wood Preservers Association Standards Book C6 ant the following guidelines. A treatment report shall be accurately completed for all charges and at a minimum shall contain the following:

i 	Charge number

ii	Date

iii	Wood species and size

iv	Total retort time in hours

v	Conditioning time in hours

vi	Pressing time in hours

vii	Retention in pounds per cubic meter

viii	Average penetration to be shown for oak

ix	Initial air time, if applicable

x	Gauge readings and times

xi	Treating operator's signature

xii	Seasoned condition (dry or green), if green show moisture content.

xiii	Final Vacuum

xiv	Wright of solution at 38° C (100° F)

xv	Work tank number and cylinder number

The preservative shall consist of a mixture of 50 percent by volume of creosote oil and 50 percent by volume of residuum oil, 50/50 coal tar solution may also be used. Final readings shall be entered on the treating report. Treating reports and charts shall become a permanent record maintained by the treating company with open access to ARRC personnel.

- Care of Treated Wood: Use extreme care in handling treated cross ties to avoid damage to the edges of the timbers or breaking through the treated portions and exposing untreated wood. Use peavies, cant hooks, pickaroons, long hooks or pointed tools such that they do not break through the treated portion of the wood. If damage occurs during handling which could potentially impair the longevity of material service life, this material shall be retreated at the vendor's expense. All cost associated with retreatment, including oil, shall be the responsibility of the vendor.

l.	Boring: All cross ties shall be bored and adzed in conformance to the ARRC Standard Tie Boring and Adzing Plan 1.13. Adzing may be deleted if vendor will certify that ties furnished will be flat and provide a uniform bearing surface for the tie plates.

m.	Anti-splitting Devices: All hardwood cross ties shall have steel multi-nail anti-splitting end plates in accordance with AREA/AREMA Manual of Railway Engineering, Chapter 3, Section 1.8 titled "Ties and Wood Preservation", Section 1.9.2.3 titled "Nail Plates", and Section 1.10.3 titled "Nail Plates".

n.	Species:   Acceptable hardwood species are Red Oak, White Oak, Hickory, Black Walnut, Gum, Beech, Ash, White Heart Sycamore, Hackberry and Hard Maple.

242-3.01   CONSTRUCTION REQUIREMENTS.   Perform track construction in accordance with the ARRC Standards, AREA/AREMA Manual for Railway Engineering and as specified herein.  The scope of construction includes, but is not limited to, unloading and distribution of track material, distribution and spacing of cross ties, laying, bolting and spiking rail, field welding of joint rail, placing rail anchors, raising, aligning and tamping track, and shaping ballast to the design section.

Employ construction procedures and methods that keep the railroad sub-ballast and ballast sections from becoming rutted or disturbed.  Immediately stop any operation that causes damage and institute alternate construction methods that do not cause damage.

All existing track material removed will become the property of the Contractor. Remove these materials from the ARRC right-of way.

242-3.02   TRACK ALIGNMENT AND GEOMETRY.   Construct the track to the alignment and profile indicated, or as adjusted by the Engineer, within the tolerances specified. Designate right or left rail, while facing in the direction of increasing stationing, to control the grade of all tangent tracks on a contract-wide basis.  Use profile grade rail for low rail on curves.  Use line rail on high rail on curves.

Maintain track centers between main line and future mainline at 4.572 m (15’-0”) within the project area.

242-3.03   TOLERANCES.   Deviations from indicated gauge, cross level, horizontal line, profile grade, and tie spacing shall conform to the following requirements:

1.	Gage: 1,435 mm (4’-8 ½”) plus or minus 3 mm (1/8”).

2.	Cross Level and Superelevation: Plus or minus 3 mm (1/8”) from level on tangent or design superelevation on curve.

3.	Deviation from Horizontal Alignment: Plus or minus 6 mm (¼”) in a 19 m (62’) chord. Plus or minus 13 mm (½”) total except in road crossings where total deviation shall be plus or minus 6 mm (¼”).

4.	Deviation from Profile Grade: Plus or minus 6 mm (¼”) in 19 m (62’) chord or a total of plus or minus 13 mm (½”).

5.	Tie Spacing: Distance between centerline on adjacent ties shall be 495 mm (19 ½”) and not vary more than plus or minus 25 mm (1”) from the indicated spacing, with the additional requirements that 48 ties shall be installed per 23.8 m (78’) of track.

242-3.04   CROSS TIE DISTRIBUTION.   After receiving the cross ties from the supplier, transport them to the work area in accordance with the AREA/AREMA "Handling of Ties from the Tree into the Track".   Place ties on a smooth, compacted surface as specified herein, space as shown within the specified tolerances, and lay them normal to the centerline of track with heartwood face down. Line the ends of ties uniformly on the right side of track when facing increased stationing.

242-3.05  TIE PLATES AND SCREWS.  Attach tie plates to the cross ties with line and hold-down screws to the indicated patterns. You may pre-plate cross ties prior to distribution. If you choose to pre-plate the cross ties, furnish any additional material required at no added cost to Owner. Use a jig to compensate for fabrication tolerances to achieve track gage tolerances.

242-3.06  RAIL LAYING   Use standard carbon rail on all tangent track and curves up to four degrees. Use high strength rail on curved track over four degrees and through the crossings.  Lay rail in accordance with the details and the following procedures:

1.	Rail Distribution; Distribute rails along the roadbed with the head of the rail up and in such a manner that will prevent damage to them.  Do not drop rails from the sides of railcars or trucks.

2.	Rail Laying: Clean the base of the rail and surface of the tie and tie plate prior to laying.  Lay the rails one at a time without bumping or striking. Bring rail ends squarely together against the expansion shims and bolt completely before spiking.  Lay rails so that the joints in opposite rails are staggered not less than 6 m (20’) apart, plus or minus 610 mm (24”) with the following exception.  Closer joints may be required at turnouts or roadway crossings. Use less than standard length rails to space the joints on curves.  Do not use rails shorter than 4.6 m (15’). Lay or weld rail so that no joints are in grade crossings.

3.	Rail Cutting and Drilling: Cut rails square and clean using rail saws. Use an exact template for precisely marking, center punching and drilling holes for complete bolting of cut rail.  Do not mark or drill through joint bars. Debur all holes. Do not drill new holes between two previously drilled holes.  Do not burn or cut rails or bolt holes by means of an acetylene torch. Bevel and harden all cut rail ends at the head to conform to AREA/AREMA "Manual Specifications for Steel Rails", Supplementary Requirement S1.

4.	Rail Joints: Wire bush the fishing surface of the rails and joint-bars to remove rust before assembly. Use expansion shims between the ends of adjacent rails to allow for rail expansion. Use the following table to determine the proper expansion allowance.  Refer to AREMA chapter 5, paragraph 5.3.1 for shim thickness to use for 12 m (39’) rail.

| Rail Temperature °C (°F) | Shim Thickness in mm (”) for 23.8 m-24.4 m (78’- 80’) rail |
| --- | --- |
| Below 2 (35) | 8 (5/16) |
| 2 to 8 (35-47) | 6.4 (1/4) |
| 9 to 15 (48-60) | 4.8 (3/16) |
| 16 to23 (61-73) | 3.2 (1/8) |
| 24 to 30 (74-85) | 1.6 (1/16) |
| Over 30 (Over 85) | None |

Use proportionate shim thickness for shorter lengths of rail.  Determine the temperature of the rails by the use of an AREA standard rail thermometer, placed on the base of the rails close to the web on the side shaded from the sun. Allow sufficient time to accurately record the temperature. Take care to assure that shims are not squeezed or damaged during installation of shims or rails. Remove shims from between rail ends as soon as the bolts have been tightened and the rail anchors applied. Install all track bolts when the rail is laid and tightened before spiking.

Tighten to a “final bolt tension” of 89 to 133 kN (20,000 and 30,000 lbs.).  Tighten the bolts once, at the time of rail installation. Check and adjust the final tension just prior to final acceptance per AREMA chapter 5, paragraph 5.5.2.

5.	Field Welded Joints: Field weld all rail joints in accordance with the applicable AREA/AREMA specifications for thermite welding of rail joints.  Submit the manufacturer of the thermite kits and the qualification of the welders to the Engineer for approval prior to the Bid Award.

6.	Final Dressing of Trackwork:  Dress the ballast section in such a manner so that the tie cribs are full to the top of the ties after the track has been brought to final grade and alignment.

7.	Rail Anchoring:  Use Pandrol clips or approved rail anchors.

242-4.01 METHOD OF MEASUREMENT. Railroad Trackwork and Trackwork Removal will not be measured.

242-5.01 BASIS OF PAYMENT. If you call for flagmen and, through no fault of the Department or the ARRC, the flagmen are not needed, payment shall be deducted from monies due you. Other flagging, required by your operation, shall be paid for by you.

All traffic control measures required will be paid for separately under their respective pay items.

Trackwork and Trackwork Removal required for this project is subsidiary to item 245(1), Modular Crossing and no separate payment shall be made.  This includes, but is not limited to, grading and shaping of the existing track embankment.

Delete Section 617 in its entirety and add the following Section:

### SECTION 245

# GRADE CROSSINGS

245-1.01  DESCRIPTION. This work consists of furnishing and constructing a concrete modular crossing to the alignment and location shown on the Plans.  Installation of the modular crossing to the design grade lines will require the removal of existing main line to permit excavation of unsuitable subgrade and ballast and complete tie renewal within the limits shown.  All trackwork shall be in accordance with Section 242 of the specifications and shall be scheduled with the ARRC through the Engineer.  No portion of the existing track structure shall be removed prior to the approval of the Engineer which must be requested in writing 7 calendar days in advance of the work.

245-2.01  MATERIALS. Furnish and deliver all new material required to construct the grade crossings. The material shall conform to the current AREA/AREMA specifications and as detailed in this specification.  All standard track material shall conform to Section 242 of these specifications.

- Modular Crossing Panels:  Crossing panels shall be modular reinforced concrete panels specifically designed for railroad crossing applications.  The particular manufacturer shall be regularly engaged in the fabrication of railroad crossing materials and the product must be approved, in writing, by the Engineer.  Panels will be screwed to the ties with ARRC approved lag screws.  Manufacturers of reinforced concrete modular panels shall be one of the following or approved equal:

Century Concrete Crossings			800-527-5232

Omni Grade Crossing Systems		800-203-8034

American Concrete Products Co.		402-331-5775

KSA						412-227-2396

Premier Concrete RR Crossings		800-425-5556

Omega Industries, Inc.			360-694-3221

Magnum Manufacturing Corp.		801-785-9700

The manufacturer’s specifications for reinforced concrete crossing panels shall be submitted to the Engineer for approval.

- Cross Ties:  Cross ties shall be new hardwood as specified in Section 242 except length shall be adjusted to meet installation requirements of modular crossing manufacturer.

- Geotextile Fabric:  Geotextile fabric shall be non woven fabric meeting the requirements of AREMA Chapter 1 and shall be heavy class.  Fabric specifications and sample shall be submitted for review prior to purchase and installation.

- Ballast:  Construction and placement of ballast shall conform to Section 241 of these specifications.

- Sub-ballast:  Construction and placement of sub-ballast shall conform to Section 241 of these specifications.

##### CONSTRUCTION REQUIREMENTS

245-3.01  GENERAL. Grade crossing construction shall be performed in accordance with ARRC standards, AREA/AREMA Manual Part 8 and as specified in this document.  The scope of construction includes but is not limited to, unloading and distribution of crossing materials and installation on prepared subgrade and sub-ballast sections.

The ARRC track at the Talkeetna Spur Road crossing can be closed for construction as follows:

- Closure will be scheduled in late September or October on a Thursday, Friday or Saturday night for a period not to exceed 12 hours.

- Start of the closure will depend on arrival and departure of the last train through the Talkeetna area for that day.  When the last train goes over the crossing, the closure will begin.  This is expected to be late afternoon or evening.

- The ARRC can reasonably project these train operations 48 hours in advance.

- If train schedules do not permit the start of a closure, then the closure will be delayed to the following week.  Contractor will be expected to be ready for the closure.  The crossing reconstruction must be substantially completed in one closure.

Subsequent closures of up to 8 hours will be granted around train schedules to complete the crossing.

245-3.02  EXCAVATION.  The construction of the grade crossings will require the excavation of the existing and future mainline to the bottom of unsuitable material at the locations shown in the Plans.

245-3.04  MODULAR CROSSINGS.  Construct modular crossings in accordance with ARRC Standards shown in standard drawing “Modular Crossing”.  Construct all modular crossings with Pandrol Plates, Pandrol Clips and approved screws or equal.  Use geotextile fabric that conforms to Subsection 245-2.01.

245-3.05    RAIL.  Use unjointed 52 kg RE rail within the road crossing and for at least 6 m on either side of the crossing as specified in Section 242-2.01.

245-4.01   METHOD OF MEASUREMENT.  Item 245(1), Modular Crossing will not be measured.

245-5.01  BASIS OF PAYMENT.   All work associated with constructing the modular crossing is subsidiary to item 245(1), Modular Crossing and no separate payment shall be made.   This includes, but is not limited to, excavation and backfill, geotextile fabric, subballast, ballast, cross ties, trackwork and trackwork removal.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 245(1) Modular Crossing | Lump Sum |

SECTION 301

# AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-1.01 DESCRIPTION.  Add the following:  This work also includes furnishing and placing Aggregate Base Course on the foreslopes to blend the existing foreslopes with the top of finished pavement as directed by the Engineer.

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM. (2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05.

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14  Joints.  Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one minimum diameter 150 mm core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

401-3.15 SURFACE TOLERANCE. Add the following, The Engineer shall measure the surface smoothness in all driving lanes of the project with an inertial profiler before construction begins. The surface profile will be measured in the left wheel path of each lane.   No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or project limits.  A 5 mm blanking band filter will be used in the calculations of the Profilograph results.  The Engineer will report an Initial Average Profile Index Value (Initial PrI) that includes all measured lanes, calculated to the nearest 1 mm per km.

The Engineer shall measure the surface smoothness of the top lift of asphalt in all driving lanes with an inertial profiler before final acceptances of the project and after completion of corrective work.  The surface profile will be measured by the same method completed above.  The Engineer will report a Final Average Profile Index Value (Final PrI) that includes all measured lanes, calculated to the nearest 1 mm per km.  Any portion of final pavement surface having a smoothness PrI greater than 230 mm / km in a 160 meters segment shall be removed and replaced.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One minimum diameter 150 mm core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-1 and applied under Item 401( ), Asphalt Price Adjustment.

Reduction Factor (R) = (Initial PrI-Final PrI)/ Initial PrI

# TABLE 401-1

| Reduction Factor (R) | Adjustment to Item 401( ), Asphalt Price Adjustment, for Pavement Smoothness |
| --- | --- |
| 0.61 to 1 | Add $1000 multiplied by [(R – 0.6)*100] |
| 0.5 to 0.6 | No Adjustment |
| 0 to 0.49 | Deduct $1000 multiplied by [(0.5 - R)*100] but not to exceed $10,000 |

(03/19/02)R199M98

# SECTION 505

PILING

Special Provisions

505-3.13 COATING OF STEEL PILES AND SHELLS.  Delete this Subsection and substitute the following:  Above ground portions of permanent piles shall be completely coated with a brush applied rust inhibitive primer, brown in color, as approved by the Engineer.  If the primer color is not the approved brown, the piles shall be painted with both the rust inhibitive primer and an approved cover coat of brown enamel paint in accordance with Subsection 650-2.09.

Add the following Subsection:

505-3.14 PILE CAPS.  The offset allowance between the center of beam and the center of pile shall not exceed 150 mm.

505-4.01 METHOD OF MEASUREMENT. Add the following:  Pile caps will not be measured.

505-5.01 BASIS OF PAYMENT.  Add the following:  Pile caps are subsidiary to Item 505(6), Drive Structural Steel Piles and no separate payment shall be made.

SECTION 506

TIMBER STRUCTURES

Special Provisions

506-1.01 DESCRIPTION. Add the following: This work shall also include furnishing and installing treated timber bollards as shown on the Plans.

506-4.01 METHOD OF MEASUREMENT. Add the following: Treated timber bollards will be measured by the number of units installed and accepted.

506-5.01 BASIS OF PAYMENT. Add the following: Payment for Item 506(7) Treated Timber Bollards will be full compensation for furnishing all labor, equipment and materials required for installation as shown on the Plans. Excavation and grading necessary to complete the work will not be paid for separately, but will be subsidiary to the item. (10/1/91)R122

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 506(7) Treated Timber Bollards | Each |

SECTION 507

BRIDGE RAILING

507-1.01  DESCRIPTION.  Add the following:  This work also consists of constructing and installing approximately 450 meters of balustrade handrailing on the boardwalk shown on the Plans and described in Section 650 of these specifications.

507-2.01 MATERIALS.  Delete item 2 and substitute the following:

2.	Timber Railing			Section 506 and Section 650.

507-3.01 CONSTRUCTION REQUIREMENTS.  Delete item 3 and substitute the following:

3.	Timber. Fabricate and install timber railing in conformance with Section 506 and Section 650.

Add the following item:

5.	Balustrade Rail.

a.	Wood.  Semi-Transparent Oil Stain

507-4.01  METHOD OF MEASUREMENT.  Add the following:  Balustrade Railing will be measured by the linear meter along the centerline of the rail cap completed and accepted.

507-5.01  BASIS OF PAYMENT.  Add the following:  Payment for Item 507(9) Balustrade Railing will be full compensation for all labor, equipment and materials required for installation, complete and in place.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 507(9) Balustrade Railing | Meter |

# SECTION 603

# CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts. (5/31/96)R42M

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

Delete the third paragraph and substitute the following:  When extending in-place culverts use extensions made of the same material as the existing culverts.  The use of extensions made of a dissimilar material will not be allowed.  Verify the existing culvert lengths and material type prior to ordering the culvert extensions.

In the fourth paragraph, delete the last sentence. (02/08/01)M95

Special Provisions

Add the following: Culvert marker posts shall meet the requirements of Subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm. (5/31/96)R42M

Standard Modifications

603-3.03 JOINING PIPE.

2. Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.” (02/08/01)M95

Special Provisions

Add the following Subsection:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving. (5/31/96)R42M

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.

Thrust blocks shown in the Plans will not be measured.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items.  (5/31/96)R42M

Thrust blocks show on the Plans are subsidiary to the pipe items and no separate payment shall be made.

SECTION 606

GUARDRAIL

# Special Provisions

606-1.01 DESCRIPTION.  Add the following:  This work also consists of supplying and installing wood rail as shown on the Plans.  The intent of the rail is to protect pathway users from guardrail posts.  Substitute rail may be used with prior written approval by the Engineer.

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm. The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag that provides approximately 129 cm2 of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

(10/01/01)R45aM98

Threat wood rail in accordance with Section 714.  Fasten rail to the back of guardrail posts with countersunk galvanized screws.

606-3.01 GENERAL. Replace the second sentence of the first paragraph with the following: Conform with these Specifications and the Standard Drawings with the following exception.  Modify Standard drawing G-20 to only allow an offset of 300 mm (1 foot) for the ET-2000.  (03/22/02)R266M98

606-3.09 FLEXIBLE MARKERS. Add the following Subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer. The flexible markers shall have a minimum of 530 millimeters of marker extending above the top of the guardrail. The reflective tape shall face the nearest oncoming traffic.

606-3.10 LENGTH OF NEED VERIFICATION. Add the following Subsection: After shaping the slopes and staking all proposed guardrail locations, notify the Engineer to field verify the beginning and ends. The Engineer will approve the staked location of the guardrail before installation. The Engineer may determine that additional guardrail is necessary, and comply without delay. (10/01/01)R45aM98

606-4.01 METHOD OF MEASUREMENT.  Add the following:  The wood rail shown in the Plans will not be measured.

606-5.01 BASIS OF PAYMENT. Add the following:  All materials, labor and equipment associated with the wood rail are subsidiary to Item 606(1), W-Beam Guardrail.

## SECTION 608

- SIDEWALKS

### Special Provisions

608-1.01 description. Add the following: This work also consists of constructing asphalt pathway(s) in conformance with the Plans.

608-2.01 MATERIALS. Delete paragraph number 2 and substitute the following:

2.  Asphalt Sidewalk and Asphalt Pathway

Asphalt Cement, PG 52-28	Subsection 702-2.01

Aggregate, Type III	Subsection 703-2.04

Mix Design Requirements (ATM T-17)

Marshall Stability, N, min.				4450

Percent Voids, Total Mix	2-5

Compaction, Blows/side	50

- Add following Subsection:

608-3.04 ASPHALT PATHWAY. Construct asphalt pathway in accordance with Subsection 608-3.02 Asphalt Sidewalks.

608-4.01 METHOD OF MEASUREMENT. Add the following:

Asphalt Pathway. By the megagram of asphalt concrete in accordance with Section 109, Measurement and Payment. Asphalt cement will not be measured for payment.

608-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement for Asphalt Pathway will not be paid for separately, but will be subsidiary to their respective pay items.

Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively. (2/1/00)R47M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 608(7) Asphalt Pathway | Megagram |

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Talkeetna.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

No separate payment shall be made for removing and disposing of existing signs and posts  detailed in Subsection 615-3.01.  This work shall be subsidiary to Item 615(1), Standard Sign.

# SECTION 618

# SEEDING

# Special Provisions

618-1.01 DESCRIPTION. Add the following: Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.

618-3.03 APPLICATION. Add the following: Apply seed, mulch and fertilizer as follows per hectare (ha). Apply seed and mulch in one application if using the hydraulic method. Apply all fertilizer with the hydraulic method.

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Slender Wheatgrass (Wainwright) - Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total = 49.0 kg |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

Do not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Slender Wheatgrass (Wainwright) if Slender Wheatgrass (Wainwright)  is commercially unavailable.  If this substitution is made, apply at the same application rate.

618-4.01 METHOD OF MEASUREMENT. Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items.

618-5.01 BASIS OF PAYMENT. The work described under subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(03/05/02)R52M98

SECTION 620

TOPSOIL

# Special Provisions

620-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Topsoil shall conform to the requirements of Section 726.

620-4.01 METHOD OF MEASUREMENT. Add the following: Limestone, if required, will not be measured for payment, but will be subsidiary to Item 620(1) Topsoil.

(9/11/96)R53

# SECTION 627

# WATER SYSTEM

Special Provisions

627-1.01 DESCRIPTION.  Add the following:  This work also consists of field locating, adjusting and/or replacing thaw wire valve box top sections and covers located approximately at stations 71+770 and 72+030 of the pathway alignment.

627-2.01 MATERIALS. Add the following:  Use a Lug Type covers with the word “WATER” embossed on the top.  If required, install 457 mm (18”) valve box top sections.  Use slip type valve box top sections with a lower flange.  Use covers and valve box top sections manufactured by Inland Foundry Co. Inc., or approved equal.

627-4.01 METHOD OF MEASUREMENT.  Delete Item 5 in its entirety and replace with the following:

5.	Valve Boxes and Covers.  Will not be measured.

627-5.01 BASIS OF PAYMENT.  Delete the first two paragraphs and substitute the following:

The work described in Subsection 627-1.01 is subsidiary to Item 608(7), Asphalt Pathway and no separate payment shall be made.  This includes all materials, labor, excavation, bedding, and backfill required.

# SECTION 635

# INSULATION BOARD

Special Provisions

635-2.01 MATERIALS. Delete the last sentence and substitute the following:  Install insulation board with a minimum R value of 0.88 °C m2/W (5 °F h ft2/BTU) per 25 mm (1 inch) at –3.89 °C (25 °F).

635-3.01 CONSTRUCTION REQUIREMENTS. Add the following: Verify the depth of existing water pipe, for insulation requirements, by pot holing the areas shown in the Plans.  Where insulation is required, install enough to provide a total R value of 2.30 [°K m2/W] (13 [°F h ft2/BTU]) or as directed by the Engineer.

635-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following:  By the square meter of insulation board in its final position, including transitions, regardless of thickness, complete and accepted.

Sand blanket material is subsidiary.

Pot holing is subsidiary.

635-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 635(2) Insulation Board | Square Meter |

(8/23/00)R57M98

SECTION 636

# GABIONS

Special Provisions

636-1.01 DESCRIPTION.  Delete this Subsection and substitute the following: This work consists of the design, construction and installation of gabions at the locations shown on the Plans.  Perform all design calculations and develop detailed shop drawings stamped by a professional civil engineer registered in the State of Alaska.  Furnish, assemble and fill wire gabions in accordance with the details shown in the approved shop drawings and in the Plans.  Conduct work within reasonable conformance of the lines and grades as staked.

Add the following Subsection

636-1.02 SUBMITTALS.  Submit design calculations and shop drawings to the Engineer for review and approval.  Submit design calculations and shop drawings a minimum of 30 days before performing the work.  At a minimum, the shop drawings shall include notes, details, elevation, plan, and cross-section views with sufficient detail to perform the work.

If the Engineer disapproves the design calculations and/or the shop drawings, resubmit them within 15 days.  Do not begin work without approved design calculations and shop drawings.

636-4.01 METHOD OF MEASUREMENT. Add the following:  Developing the required design calculations and shop drawings will not be measured.

636-5.01 BASIS OF PAYMENT.  Add the following:  The work associated with developing design calculations and shop drawings is subsidiary to item 636(1), Gabion and no separate payment shall be made.

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION. Add the following: This work also includes the construction of approaches at locations shown on the Plans.

639-3.01 CONSTRUCTION. Delete the first sentence and substitute the following: Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. Delete the first sentence and substitute the following: By the number of driveways and approaches constructed as shown on the Plans or as directed.

639-5.01 BASIS OF PAYMENT. Add the following: The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified. Excavation or clearing beyond the roadway or pathway clearing in driveways and approaches will not be measured for payment but will be considered subsidiary to 639 items. Selected Material, Type A, Aggregate Base Course, and Asphalt Concrete required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule. Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items.

(12/14/99)R58M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(3) Public Approach | Each |

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modifications

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT. Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 10 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Items 641(1) and 641(3) will not be measured for payment.

Items 641(2) and (4) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT. The Bid Schedule will include either items 641(1) and (2) or items 641(1), (3), and (4)

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

3.	Item 641(3) Temporary Erosion and Pollution Control. At the lump sum price shown on the bid schedule to install and maintain temporary erosion, sedimentation, and pollution control measures in accordance with the original approved SWPPP and HMCP.

4.	Item 641(4) Temporary Erosion and Pollution Control Amendments. At the prices specified in the Directive for extra, additional, or unanticipated work to install and maintain temporary erosion, sedimentation, and pollution control measures. All work paid under this Item shall be shown as amendments to the original approved SWPPP or HMCP.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule.  (08/15/01)M78

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Special Provisions

642-1.01 DESCRIPTION. Add the following:  This work also includes flagging monuments as shown in the Plans.

Standard Modifications

642-3.01 GENERAL.  Delete the seventh paragraph.

(06/25/99)M 79

#### Special Provisions

Add the following:  Verify pathway line and grade at the following locations.

- Spur Road with adjacent pathway locations.

- approach locations

- existing turnout locations.

- Submit survey data to the Engineer.  The Engineer will provide corrected alignment data as necessary to construct the adjacent pathway sections in accordance with the typical sections and to match the pathway with approaches and existing turnouts to avoid excessive cutting and filling.

Add the following after Item 10 on page 355: Prior to any work on the project, stake and reference the construction centerline. Reference the existing centerline at 25 meter intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 meters and shall show the offset distance to centerline and the station from the beginning of the project.

Install a reference sign every 150 meters. These reference signs shall meet the following requirements:

1.	mounted a minimum of 1.5 meters above the shoulder,

2.	located a minimum of 3 meters from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 125 mm high black lettering on an orange background.

Reference the beginning and ending points of the no-passing zones in a separate field book.

Provide centerline and shoulder profiles extending 90 meters beyond the limits of the pavement removal and dig-out areas. The Engineer may require such adjustments to the planned roadway grades. This shall not be considered extra work. Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking or blue topping. (8/29/00)R61M98

Add the following:  Install flags at monument locations identified for flagging in the Plans.

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work. (3/31/00)R252M98

642-4.01 METHOD OF MEASUREMENT.  Add the following:  Re-staking of areas required because of revisions of the profile grade designated by the Engineer shall be measured under item 642(3), Three Person Survey Party.

Flagging monuments as described in Subsection 642-1.01 will not be measured.

642-5.01 BASIS OF PAYMENT. Add the following:

Flagging monuments shall be subsidiary to Item 642(9), Reference Existing Monuments and no separate payment shall be made.

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (01/29/02)R222M98

## Standard Modifications

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. (9/29/00)M 91

## Special Provisions

Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

(01/29/02)R222M98

## Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (9/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (01/29/02)R222M98

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.  Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

- 10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

# ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	During the Moose Dropping Festival  (July 13 - July 14, 2002).

2.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, don’t restrict traffic from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, don’t restrict traffic from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, don’t restrict traffic from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Lane restrictions, if allowed, shall be conducted so that no more than a 20 minute accumulated stopped delay, 40 vehicles, or 0.4 kilometers of traffic is detained, whichever occurs first, before releasing the detained motorists.  During paving operations a 30 minute stopped delay will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate your work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (01/29/02)R222M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | ### Contingent Sum |

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE. Delete this Subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

644-2.05 VEHICLES.  Delete first sentence in the first paragraph and substitute the following: Furnish and maintain full-size four-wheel drive pickup(s) or sport utility vehicle(s) for exclusive use of the Department throughout the project.  Furnish the number of vehicles shown in the Estimate of Quantities.

Add the following: Equip vehicles used by the Department with CB radios and yellow rotating beacons wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

The Contractor is responsible for normal wear and tear, and any other incidental damage including broken windshields, occurring during the Department’s operation and use. The Department is responsible for damage to any vehicle caused by its own negligent during operation. The Department will provide non-owned auto liability insurance providing third party liability coverage for any accident during the Department’s operation and use.

644-3.01 METHOD OF MEASUREMENT. Delete subparagraph “vehicles” and substitute the following:

Vehicle. Per each vehicle provided. If a replacement vehicle is necessary, no additional measurement for payment will be made. (01/28/02)R245M98

Standard Modifications

644-4.01 BASIS OF PAYMENT. . In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Special Provisions

Add the following: Electricity, propane and water supplied for a State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.(9/28/00)R63M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 644(7) Vehicle | Each |

Add the following Section:	SECTION 645

TRAINING PROGRAM

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgment of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.  (10/29/91)S 16

Payment will be made under:

| # Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 1 Trainees/Apprentices | Labor Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Delete this Subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item  2.  60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:	SECTION 647

EQUIPMENT RENTAL

## Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operational, which includes the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 48 kW Minimum will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation. (11/12/98)R15M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 647(1) Wide Pad Dozer, 48 kW Minimum | Contingent Sum |

Add the following Section:	SECTION 650

# BOARDWALK

650-1.01 DESCRIPTION.  This work shall consist of furnishing materials and labor for the construction of a boardwalk system in conformance with the Plans and Special Provisions.   This work consists of furnishing and driving approximately 154 steel pipe piles and constructing approximately 675 square meters of boardwalk.  Balustrade railing shall be attached to the boardwalk.

650-1.02  APPLICABLE ACCESSIBILITY STANDARD.  Americans with Disabilities Act (ADA) Accessibility Guidelines for Buildings and Facilities.

650-1.03 SUBMITTALS AND SUBSTITUTIONS.  Conform to Subsection 106-1.01.

#### MATERIALS

650-2.01 GENERAL.  Use all new materials that conform to the details shown on the Plans or as specified.

650-2.02 BACKFILL.  Selected Material, Type A conforming to Subsection 703-2.07.

650-2.03 STEEL.  Steel plates, beams and angles shall conform to the requirements of ASTM Specification A 36, Standard Specifications for Carbon Structural Steel.

650-2.04 STRUCTURAL STEEL PIPE PILES.  Conform to Sections 715 and 716.

650-2.05 GALVANIZING.  Conform to AASHTO M 111/ASTM A 123 (Standard Specification for Zinc [Hot-Dip Galvanized] Coatings on Iron and Steel Products), or AASHTO M 232/ASTM A 153 (Standard Specification for Zinc Coating [Hot-Dip] on Iron and Steel Hardware).  Repair damaged galvanizing by using low melting point zinc repair rods in conformance with ASTM A 780-00 (Standard Practice for Repair of Damaged and Uncoated Areas of Hot-Dip Galvanized Coatings).

650-2.06 WOOD.  Conform to Section 713.  Wood species shall be Douglas Fir, Western Hemlock or Hem-fir unless otherwise specified.

Dimensional lumber and timbers are shown on the Plans in nominal dimensions, indicating surfaced four sides (S4S) or planed material.  Use classification for light framing shall be Construction Grade.  Use classification for structural joists and planks shall be No. 2 Grade or Better.  Use Dressed (Surfaced) Lumber Manufacturing classification.  Us Nominal Size Designations of Boards, Dimension, and Timbers for size classification.

650-2.07 TREATED WOOD.  Treatment shall be as follows:

1.	Above Ground Applications.  Pressure treat lumber and timber with water borne salts preservative Chromated Copper Arsenate Type C (CCA-C) to a minimum retention of 6.4 kg per cubic meter or to refusal. Treated materials shall be pigmented uniformly brown in color by treater and nonincised.  This type of treated wood is commonly used for residential decks for above ground applications.  Incising may be used on 100x and thicker material to obtain minimum retention.

2.	Ground Contact Applications.  Pressure treat lumber and timber with water borne salts preservative Chromated Copper Arsenate Type C (CCA-C) to a minimum retention of 9.6 kg per cubic meter.  Exposed treated materials shall be pigmented uniformly brown in color by treater.

650-2.08 FASTENERS.  Commercial quality and type of nails and screws as required to securely hold all members in place in accordance with National Design Specifications.  Nails shall be hot dipped galvanized.  All other fasteners shall be corrosion resistant.  Fasteners in pressure treated wood shall be hot dipped galvanized.  Nails and wood screws below grade in pressure treated wood shall be stainless steel.

650-2.09 PAINT.  Unless otherwise specified, use the following paint types and colors, or approved equals:

1.	Solid Oil Stain.  Exterior alkyd flat finish stain, color russet.  Color-Shield 4000 #63-138 Russet as manufactured by Preservative Paint Company, Russet as manufactured by Pittsburgh Paint Company, or Olympic Russet as manufactured by PPG Architectural Finishes, Inc.  Submit color samples of proposed substitutions for approval.

2.	Semi-Transparent Oil Stain.  Exterior alkyd based stain, color to match solid oil stain russet.  Stains for pressure treated wood shall be recommended by manufacturer for use on pressure treated wood.

3.	Clear Oil Stain.  Non-pigmented penetrating exterior alkyd base stain formulated for water repellency.

4.	Metal Primer Paint.  As recommended by enamel paint manufacturer.

5.	Enamel Paint.  Exterior alkyd base gloss enamel.  Color to match solid oil stain color.

6.	Above Ground Wood Preservative.  Brown preservative with active ingredient of minimum 9.08 percent copper naphthenate (equivalent to minimum 1 percent metallic copper).  Color to be approved by Engineer.

7.	Below Ground Wood Preservative. Preservative with active ingredient of minimum 18.16 percent copper naphthenate (equivalent to minimum 2 percent metallic copper).

8.	End Cut Preservative for Treated Wood.  Brown preservative with active ingredient of minimum 16 percent copper naphthenate (equivalent to minimum 2 percent metallic copper).  Color to match preservative pressure treatment color.

Paint that has been frozen or is out of date shall be replaced at no additional cost to the Department.

## CONSTRUCTION REQUIREMENTS

650-3.01  EXCAVATION AND BACKFILL.  Conform to the requirements of Section 204 and the details on the Plans.

650-3.02  WELDING.  Welding operators shall be certified in accordance with the applicable code for the type of welding required for this work.  Structural Steel welding to conform to American Welding Society D1.1.

650-3.03  WOOD.  Employ competent carpenters and construct framing true and exact.  Drive nails and spikes with just enough force to set the heads flush with the wood surface unless otherwise specified.  Locate all non-removable shipping, storage, weathering and erection marks on fabricated lumber hidden from view in the completed work.  Do not use damaged lumber.  Store on-site lumber above the ground and protected from damage and weathering.

Bore holes for machine and carriage bolts with a bit of the same diameter as that of the bolt.  Bore holes for lag screws with a bit not larger than the body of the screw at the root of the thread.

Use USS flat washers with all bolts, heads or nuts that would otherwise be in contact with wood unless otherwise specified.

650-3.04  PAINT.  Deliver in sealed containers with labels legible and intact.  Remove dirt, grease, oil and other construction debris prior to painting.  Insure that surfaces to be painted are even, smooth, sound, clean, dry, and free from defects affecting proper application.  Metal surfaces to receive paint shall be corrosion free.  Apply per manufacturer's recommendations.  Apply paint material evenly without runs, sags, or other defects.  Work each coat into the material being coated at an average rate of coverage recommended by the manufacturer.  Cover surfaces completely to provide uniform color and appearance.  Remove all paint, stain, or other finish material where it has spilled or spattered.

1.	General.  Unless otherwise specified, schedule finishes as follows:

a.	Non-Treated Wood, Surfaced.  Finish surfaces not scheduled to receive stain or clear oil stain with wood preservative.

b.	Treated Wood, Hidden.  Brush coat all dados, cut ends, drilled holes and field cuts in wood materials to saturation with end cut preservative.

c.	Treated Wood, Exposed.  Saturate cut surfaces with scheduled finish. Saturate finish surfaces not scheduled to receive stain with a wood preservative.

d.	Metal.  Prime and paint exposed metal surfaces that are not fabricated of corrosion resistant material or galvanized.

2.	Boardwalk.

a.	Wood, Visible Surfaces and Between Decking.  Semi-Transparent Oil Stain

b.	Metal.  Primer and Enamel Paint

650-3.05 STRUCTURAL STEEL PIPE PILES.  Drive pipe piles to a minimum bearing capacity of 155 kN and a minimum depth of 3 meters.

650-3.06  BOARDWALK.  The boardwalk is a walkway 3 meters wide with balustrade rail. Construct the boardwalk in accordance with the Plans.  Construct beams level and stable.  Install joists parallel to adjacent joists and level or sloped according to the Plans. Install the decking perpendicular to the joists with 6 mm spacing.  Fasten each deck board with three (3) decking screws, spaced evenly, at every joist.  Other members shall be fastened in accordance with the Plans.

650-4.01 METHOD OF MEASUREMENT.  Item 650(12), Boardwalk will be measured by the linear meter along the centerline of the boardwalk completed and accepted.

Balustrade railing will be measured under Section 507.

Excavation and backfill required for facilities paid for under this Section will not be measured. for payment but shall be considered subsidiary to this project.

The retaining walls at the beginning and end of the boardwalk will not be measured.

Structural steel piles and pile caps will not be measured under items in Section 505.

650-5.01 BASIS OF PAYMENT.  Item 650(12), Boardwalk will be paid for at the contract price per linear meter.  Payment shall be full compensation for all the labor, equipment, and materials required.

Balustrade railing will be paid for under item 507(5), Balustrade Railing.

Excavation and backfill required for facilities paid for under this Section are subsidiary to Item 650(12) and no separate payment shall be made.

All materials, labor, and equipment necessary to construct the retaining walls at the beginning and end of the boardwalk are subsidiary to Item 650(12), Boardwalk and no separate payment shall be made.

Structural steel piles and pile caps will be paid for under Section 505.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 650(12) Boardwalk | Meter |

# SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph.  The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS. Delete this Subsection in its entirety and substitute the following: This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract. The work includes: locating, repairing, replacing, adjusting, realigning, cleaning, and relocating components of traffic signals, lighting systems, and flashing beacons to keep them wholly operational and positioned according to the following specifications.

If you fail to maintain the electrical systems as specified herein, the Engineer will adjust payments to you according to subsection 643-3.06, Traffic Price Adjustment.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance and provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time. Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility. Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you. If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems. The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, all components are located and aligned as specified herein, and photoelectric controls operate the lighting systems. The State will pay for all electricity used to operate the systems, if the public benefits from their operation. Furnish replacement equipment compatible with equipment used in the Central Region.

Begin repair work on all systems within one hour of notification by the Engineer. If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you. When you work on a traffic signal system, print a record of all work performed in the diary found in each controller cabinet. Make sure each entry includes

1.	The dates and times you began and completed your work, and the names of the crewmembers completing the work.

2.	The characteristics of the equipment failure or faulty operation evident before repair.

3.	The changes made or corrective actions taken.

4.	The printed name and signature of the person responsible for making the repairs or changes.

The Engineer will limit signal system shutdowns to the hours when traffic restrictions are allowed in Subsection 643-3.08, Construction Sequencing. During the shutdowns, use flag persons to control traffic. Provide local traffic enforcement and maintenance agencies 24 hour notice before shutting down a traffic signal system.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Where roadways remain open to traffic and the work includes modifying the existing lighting systems, energize the modified circuit by sunset on the same day you retire the original circuit.

Relocate or replace signal poles, lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever you reduce their clearance from the traveled way to less than 1.8 meters.

During the various phases of construction, shift the signal heads to keep them aligned horizontally and vertically with the approaches in accordance with the following:

1.	For overhead signals, maintain 5.3 m to 5.8 m of clearance between the traveled way and the bottom of each signal.

2.	For side mounted signals, maintain 2.7 m to 3.4 m of clearance between the traveled way and the bottom of the signal.

3.	Align overhead signals controlling a single lane with the center of the lane.

4.	Align overhead signals controlling two or more lanes with the lane lines separating the lanes.

5.	Check the horizontal angle to the side mounted far right signal from the center of the farthest left through lane at the stop bar. When the angle exceeds 20 degrees, move this signal to an overhead location. With two or more through lanes, center one signal head over each lane. With one through lane and protected-permitted signal phasing, leave the five section signal over the lane line and center the signal to be relocated over the through lane, otherwise install the relocated signal 2.4 meters to the right of the signal centered over the through lane.

6.	For pedestrian signals, maintain 2.1 m to 2.7 m between the traveled way and the bottom of each pedestrian signal.

7.	Aim all signal heads in accordance with subsection 660-3.08, Installation Details.

When no longer required, salvage all original and Department provided equipment in accordance with the plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, and remove all other materials used in the temporary systems from the project.

660-2.01 EXCAVATING AND BACKFILLING. Add the following to the first paragraph: Excavate trenches for installing rigid metal conduit to a depth 150 mm below the bottom of the rigid metal conduit.

In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following to the fourth paragraph: Embed conduits between two 150 mm lifts of material that are free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS.  Delete the Pile Foundations Subsection and substitute the following:

Pile Foundations.  Install all foundations for light poles with shaft lengths less than 18 meters according to the following requirements

- Materials. Furnish pipe piles that feature the diameter, minimum length, and wall thickness shown on the Plans.  Furnish piles that conform to ASTM A252, grade 3.  The Department will only accept seamless piles or piles with a single longitudinal seam that is electric resistance welded.

Furnish pile cap adapters fabricated by the pole manufacturer.

- Construction Requirements. Install the steel pipe piles open ended according to Section 505. Complete all splices and extensions in piles according to Section 505. Attach the pile cap adapter to the pipe pile with a full penetration circumferential weld.

Complete all welding shown on the Plans and as specified herein according to the Structural Welding Code –Steel, AWS D1.1-2000. At least 30 calendar days before you begin welding, submit a welding plan and mill certification reports for the pipe piles and pile caps to the Engineer for approval.  Do not begin welding until the Engineer has returned these items approved in writing.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS),

- Procedure Qualification Record (PQR),

- Welder Performance Qualification Record (WPQR),

- Visual Inspection Form,

- Report of Nondestructive Examination (NDE) of Welds, and

- The name of the Contractor’s Quality Control (QC) manager with documentation of qualifications.

Furnish all Quality Control inspection necessary to ensure the materials meet the requirements of the contract documents and workmanship meets the requirements of AWS D1.1.

- Visually inspect (VT) the entire length of each weld.

- Inspect all full penetration welds by ultrasonic NDE (UT).

Correct all deficiencies in materials and workmanship revealed by QC and Quality Assurance (QA) inspections according to AWS D1.1 without additional compensation.

Furnish all completed QC inspection documents to the Quality Assurance representative designated by the State.

Install the frangible couplings according to the manufacturer’s written installation instructions.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Add the following: Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the Plans in a manner that maintains their existing condition. Replace standards damaged by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas according to Subsection 660-2.15, Galvanizing.

Fabricate pile cap adapters from steel piles that conform to ASTM A252 grade 3 and steel plate that conforms to ASTM A709 grade 50.  Only use seamless piles or piles with a single longitudinal seam that is electric resistance welded.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Furnish the adapters hot dip galvanized according to ASTM A123, except leave the beveled edge free of zinc.  Fabricate the anchor plate to match the base plate of the lighting standard.  See the detail sheet in the Plans for all dimensional information.

Complete all welding design, fabrication, and inspection according to the latest edition of the AWS D1.1, Structural Welding Code-Steel

- Circumferential Welded Splices

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Longitudinal Seam Welds

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Inspect 25% of all PJP welds of longitudinal seams by magnetic particle testing (MT)

- Base Connection Welds

- Inspect 100% of all base connection welds.

- Inspect CJP welds by UT

- Inspect fillet welds by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Quality Assurance (QA) representative for approval.  Do not begin welding until these items have been returned approved in writing by the QA representative.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS)

- Procedure Qualification Record (PQR)

- Welder Performance Qualification Record (WPQR)

- Visual Inspection Form

- Report of Nondestructive Examination (NDE) of Welds according to Annex K, latest edition of AWS D1.1

- NDE personnel qualification records

- The Contractor’s Quality Control (QC) manager with documentation of qualifications

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid and will not allow trenching after you place the final lift of asphalt.

Delete paragraph 17 and add the following: Wherever the plans show reusing existing conduits, clean them using compressed air before pulling in the new cables.  Existing illumination cables that will be reused may be left in the conduits while you clean them.  Use a heavy-duty air compressor that delivers at least 3.540 cubic meters per minute (125 cfm) of air at 0.758 MPa (110 psi).

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Use only pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the Plans.  Use only cast iron junction box lids.

660-2.08 CONDUCTORS. Delete the first paragraph of item 2. Power Conductors and Cables and add the following: Use power conductors and cables manufactured according to ICEA publication S-66-524 and NEMA Publication No. WC7, and which are UL listed and labeled for direct burial and resistance to sunlight. Furnish conductors insulated with chemically cross-linked polyethylene UL listed and labeled as type XHHW-2. Furnish cables rated for 600 volts AC operation and which do not contain an integral ground conductor.

Furnish cables consisting of three #8 AWG conductors with conductor insulation colored black, white, and red. Furnish cables with three conductors larger than #8 AWG with conductor insulation colored black, white, and red, or with all black conductor insulation with printed numbers identifying each conductor per ICEA method 4.

Delete subparagraph “d” of item 2. Power Conductors and Cables and add the following: Furnish highway and sign illumination cables that contain #8AWG conductors with a low density, high molecular weight polyethylene jacket.

660-2.09 WIRING. Delete the first paragraph and add the following: Install signal cables with no splices in them. Install illumination cables without splices, except when adding an electrolier or making a branch in the midst of a circuit. In addition, do not splice conductors within cabinets, poles, signal heads, and luminaires.

Crimp spade type terminals onto all conductors that attach to terminal blocks. When reusing cabinets, replace terminal blocks that lack enough terminals. Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

Delete the first two sentences of paragraph numbered 7 and add the following: To add an electrolier to a circuit, pull two cables through the hand hole in the electrolier, leaving 0.9 m of slack cable in the junction box. Terminate the four current-carrying conductors in the line side half of the fused splice connector. Pull the two cables back into the junction box to position the fused splice connector in the space between the base plate and hand hole of each pole.  When a circuit branches, complete the splice in a junction box at the location shown in the Plans.

660-2.10 FUSED SPLICE CONNECTORS. Add the following: Retrofit reused poles with new tap wires, and fused disconnect kits.

660-2.11 BONDING AND GROUNDING.  Add the following after the first paragraph: Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph: All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a zinc or galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Retrofit all existing spare conduits that will contain new cables exclusively with new grounding bushings. Whenever you reuse an existing conduit that contains no ground conductor, install a bare No. 8 AWG copper wire as the ground conductor. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted. (3/30/00)R215M98

660-4.01 METHOD OF MEASUREMENT. Add the following:  Item 660(17), Replace Luminaire, Lamp and Ballast will be measured by each unit, complete and accepted in place.

660-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 660(17) Replace Luminaire, Lamp and Ballast | Each |

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Under item 4 Methyl Methacrylate Pavement Markings, delete the last sentence in the first paragraph and substitute the following: Do not apply striping to the new asphalt until the asphalt has cured for the duration listed below and at the Engineer’s discretion.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Under item 4 Methyl Methacrylate Pavement Markings. , delete the second paragraph and substitute the following: Apply Methyl Methacrylate marking material with truck mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters  (04/05/02)R246m98

Add the following under item 4. before the third paragraph:  A film test strip will be required at the beginning of each striping shift, and when there is a change in the asphalt type. In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion. (09/04/01)R221M98

Under item 4. Methyl Methacrylate Pavement Markings.,  delete the first sentence of the fifth paragraph

and substitute the following:  Apply markings for lane lines, edge lines, and center lines at a thickness of 2.3 mm (1 liter will yield a 2.3 mm thick stripe 100 mm wide by 4.348 m in length).

Under item 4. Methyl Methacrylate Pavement Markings.,  delete the first two sentences of the sixth paragraph. and substitute the following:  Apply transverse type Methyl Methacrylate pavement markings according to the following:

Pavement Marking Type	Yield Thickness

Onlys and Arrows	3.0 mm

Crosswalks & Stop Bars	3.0 mm

Diagonals & Chevrons	1.5 mm

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15 m longitudinal run from the Plan quantity.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.  The Department will limit the final quantity to 115% of the Plan quantity.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:  All costs associated with the MMAMS are subsidiary to Item 670(10B), Methyl Methacrylate Pavement Markings and no separate payment shall be made.

Add the following: The Department will pay the contract unit price for the volume of Methyl Methacrylate accepted by the Engineer up to a maximum of 115% of the quantity shown in the Plans.  All Methyl Methacrylate material over-runs above 115% of the plan quantity shall be paid for by the Contractor at no expense to the Department.   (04/05/02)R246m98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 670(10B) Methyl Methacrylate Pavement Markings | Liter |

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following.

Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T 53 and ASTM D 5801 assigned to each grade.

.

Performance Graded Asphalt Cement

PG 52-28		PG 58-28		PG 64-28

Softening Point

AASHTO T 53	(none)			49°C			52°C

Toughness min.

ASTM D 5801 	(none)			12.4 N-m		12.4 N-m

Tenacity min.

ASTM D 5801	(none)			8.5 N-m		8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

## TABLE 703-2

## AGGREGATE FOR UNTREATED BASE

## Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.(06/25/99)M 82

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following:

Use the ET-2000 LET.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET	Metric	SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

# English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

(01/22/02)R249

SECTION 712

MISCELLANEOUS

## Special Provisions

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS.

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

## SECTION 724

# SEED

# Special Provisions

724-2-02. MATERIALS. Delete this Subsection in its entirety and substitute the following:

Meet applicable requirements of the State of Alaska Seed Regulations, 11 AAC 34, Article 1 and Article 4.

Furnish “certified seed” or 4 signed copies of a report certifying that each lot of seed has been tested by an approved laboratory within 9 months of date of application. Include: name and address of laboratory, date of test, lot number for each kind of seed, and results of test as to name, percentages of purity and germination, and percentage of weed content for each kind of seed furnished.

Meet or exceed the percentages of sproutable seed specified in Table 724-1.

TABLE 724-1

Seed Requirements

| SPECIES | Sproutable Seed*, %, Min. |
| --- | --- |
| Arctared Red Fescue | 78 |
| Egan American Sloughgrass | 67 |
| Norcoast Bering Hairgrass | 71 |
| Nortran Tufted Hairgrass | 71 |
| Wainwright Slender Wheatgrass | 88 |
| Alyeska Polargrass | 71 |
| Bluejoint | 71 |
| Tilesy Sagebrush | 71 |
| Tundra Glaucous Bluegrass | 76 |
| Gruening Alpine Bluegrass | 72 |
| Nugget Kentucky Bluegrass | 76 |
| Beach Wildrye | 2870 |
| Annual Ryegrass | 76 |
| Perennial Ryegrass | 76 |

* Sproutable Seed is the mathematical product of Germination and Purity.

(03/05/02)R52M98

SECTION 726

TOPSOIL

# Special Provisions

726-2.01 TOPSOIL. Delete this Subsection in its entirety and substitute the following:  The existing natural organic blanket, representative of the project area, shall be reused and spread on the finished slopes where “topsoil” is noted on the Plans.  Prior to reusing the existing organic material, quality tests shall be performed by the Contractor and submitted for approval to the Engineer to demonstrate the organic content is equal to or greater than 5 percent by dry weight as determined by ALASKA FOP for AASHTO T 267.  Roots, stumps, unnatural material, and large rocks shall be removed from the organic material before it is graded onto the finished slope.

Fertilizer and seed shall be applied as per Section 618.

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT.  Under 1. Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2. Reinforcement, replace ‘Separation (high survivability)’ with: ‘Stabilization’.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL.  Under 2. Erosion control, replace ‘Meet AASHTO M 288 for Erosion Control’ with: ‘Meet AASHTO M 288 for Permanent Erosion Control’.

729-2.04 SEDIMENT CONTROL.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with: ‘Meet AASHTO M 288 for Temporary Silt Fence’.

(2/28/00)R229M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B. (2/29/00)R81M

Standard Modifications

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

#### Special Provisions

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this Subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this Subsection.

(2/29/00)R81M

# APPENDIX A

ESCP and PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST