PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publication, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Supervisor, (907) 269-0549.

5.	New DBE Program Requirements

ADOT&PF will fully implement new program elements of its USDOT-approved Disadvantaged Business Enterprise (DBE) Program on August 1, 2000.  Key elements of the new DBE Program are:

A newly revised DBE Program specification, Section 120;

All bidder’s are required to register annually with the ADOT&PF Civil Rights Office;

Apparent low bidder’s will be required to submit a written commitment with each DBE firm proposed for subcontracting; and

Prime Contractors will be required to report to the ADOT&PF Civil Rights Office payments made to DBE firms on a monthly basis.

All information required may be reported on forms available from the ADOT&PF Civil Rights Office or the Regional Contract Compliance Officer.  These forms will also be available soon on the ADOT&PF Civil Rights Office web page in ADOBE Acrobat downloadable format at

www.dot.state.ak.us/external/state_wide/dbe/dbe.html

Any questions about these new provisions may be directed to the Civil Rights Office at 1(800)770-6236 or 269-0851.

6.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

SECTION 101

DEFINITIONS AND TERMS

Standard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

## Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE MATERIAL. Material that contains 6 percent or less passing the 75-mm screen as determined by sieve analysis performed with ATM T-7 on minus 75-mm material. (02/18/00)R1M98

## SECTION 102

## BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modification

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State. (10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”. (06/25/99)M 69

SECTION 105

CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital Anchorage School District ACS Alyeska Cable AT&T Alascom, Inc. Anchorage Water & Waste Water Utility Chugach Electric Association City of Wasilla DOT Street Lights, State of Alaska Enstar Natural Gas Eyecom TV/Interior Telephone GCI Communications Marathon Oil Corporation Matanuska Electric Association Matanuska Telephone Association MFS Technologies, inc. Mukluk Telephone Association Municipality of Anchorage Municipal Light & Power Phillips Petroleum PTI Communications, Inc.

The Contractor shall call the following utilities and agencies directly:

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination.  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen- (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen- (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.  (2/1/00)R3M98

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES. Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

## Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: The Contractor shall obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

The Contractor shall provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual, of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

The Contractor shall provide a copy to the Engineer, of all permits or clearances received prior to Contractor's use of any site outside the project limits. Additionally, the Contractor shall provide the Engineer a written statement that the Contractor has obtained all necessary permits or clearances. The Contractor shall also provide a written statement to the Engineer listing agencies or offices contacted which responded that required no additional action from the Contractor.

The Contractor shall obtain an Endangered and Threatened Species Clearance from the U.S. Fish and Wildlife Service for sites being used outside the project limits.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.

Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (7/30/99)R7M

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99)R170M98

Add the following subsections:

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A301

EEO-1 Certification							Form 25A304

DBE Subcontractable Items						Form 25A324

ADOT&PF Training Program Request				Form 25A310

Training Utilization Report						Form 25A311

Contact Report							Form 25A321A

DBE Utilization Report						Form 25A325C

Summary of Good Faith Effort Documentation			Form 25A332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.

In addition to the reports required in the above references, the Contractor shall submit a copy of Form CC-257 to the Department by the 15th of each month of the current construction season, reflecting the composition of the previous month’s workforce. This information must also be made available, upon request, to the US Department of Labor, Office of Federal Contract Compliance Programs.

(8/13/98)S80

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

## Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

- A draft Storm Water Pollution Prevention Plan, Hazardous Material Control Plan, Notice of Intent, and activities description, as required under Section 641.

(5/16/00)R160M98

108-1.04 LIMITATION OF OPERATION.  Add the following The stone mastic paving for  this project will be completed by the interim Milestone date of August 1, 2001.

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:

The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date. (2/15/01)R242M98

108-1.07 FAILURE TO COMPLETE ON TIME. Add the following: If the stone mastic paving is not completed by the interim Milestone date of August 1, 2001 the Contractor will be assessed milestone liquidated damages in the amount of 100% of the Daily Charge indicated in Table 108-1.

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work.

(5/31/00)M90

1. Labor. Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e.

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor.

(02/08/01)M71

## Special Provisions

Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

Add the following section:

## SECTION 120

## DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

#### REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-1.01 DESCRIPTION. Add the following: This work also consists of pavement planing as specified in this section.

Add the following Subsection:

202-3.06 PAVEMENT PLANING. Remove existing asphalt concrete pavement by cold planing at locations shown on the plans.  The surface of the pavement after planing shall be uniformly rough grooved or ridged.

Remove all planed material from the project immediately after planing.  Deliver all planed material to the Municipal gravel pit located along the Hiland Correctional Road. The Contractor shall notify the Engineer at least 36 hours prior to delivering rotomilled material to the Municipal gravel pit.

Keep the rotomilled material free from base course and other deleterious material.

Steel pavement markers may be encountered within the existing pavement during the planing operation.  These steel pavement markers may not be visible prior to planing.  The Department does not have as-built information identifying where these markers were installed.  The Contractor shall not reduce the planing depth if pavement markers are encountered.

During the planing operation, the Contractor shall concurrently sweep the highway with mechanical sweepers equipped with vacuum and water sprinkling devices to control dust and remove all loosened material from the planed areas.

The Contractor shall not allow traffic to travel on surfaces that have an abrupt longitudinal planed edge greater than 50 millimeters.  In the event that it is necessary to route traffic across such edges, an asphalt concrete transition 0.6 meters in width shall be placed adjacent to the edge and to all gutters.

Maintain a vertical tolerance of 3 millimeters between adjacent passes with the planer.

The planing machine shall be specifically designed for the removal of bituminous pavement without the addition of heat.  The cutting drum shall be a minimum of 2.5 meters wide and shall be equipped with cutting teeth placed in a variable-lacing pattern to produce the desired finish.

The planing machine shall have the following capabilities:

1.	operating speeds from 0 to 12 meters per minute,

2.	self propelled,

3.	able to spray water at the cutting drum to minimize dust,

4.	able to remove material next to the gutter,

5.	designed so that the operator can at all times observe the planing operation without leaving the controls,

6.	adjustable as to slope and depth,

7.	longitudinal grade control automatically actuated by the use of two 9-meter skiis, (use on both sides of the machine) and

8.	able to cut up to 76 millimeters without producing fumes or smoke.

The Contractor shall provide a smaller machine to trim areas that are inaccessible to the larger machine at manholes, valve covers, curb returns, and intersections. (7/30/99)R143M

BASIS OF PAYMENT.  Add the following: No separate payment will be made for removing steel pavement markers.  The cost of locating and removing the steel pavement markers is subsidiary to Item 202(15), Pavement Planing.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

202(15)	Pavement Planing	Square Meter

SECTION 401

## ASPHALT CONCRETE PAVEMENT

## Special Provisions

    - DESCRIPTION. Item 401(9A) work includes the placement of Asphalt Concrete Pavement in blowout, rutted, or other areas as directed by the Engineer for pre-leveling prior to paving the Glenn Highway.

401-2.01 MATERIALS. Materials and construction shall conform to Section 401 and all other portions of the Plans and Specifications. Use Asphalt Concrete Pavement, Type III, Class B material for preleveling the milled sections of the Glenn Highway as directed by the Engineer.

The asphalt cement grade shall be PG 52-28.

If the Engineer determines Base Course is needed, he may approve the use of rotomilled tailings.

No testing is required for the preleveling material.  The Engineer will inspect and accept this material.

401-4.01 METHOD OF MEASUREMENT.  Item 401(9A) will be measured by the megagram.

401-5.01 BASIS OF PAYMENT. Add the following: The tack coat, anti-stripping additive, and asphalt cement required for preleveling the milled surface of the Glenn Highway shall be subsidiary to Item 401(9A), Asphalt Concrete Pavement, Type III, Class B.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

401(9A)	Asphalt Concrete Pavement, 	Megagram

Type III, Class B

Add the following Section:

SECTION 407

## STONE MASTIC ASPHALT CONCRETE PAVEMENT

## Special Provisions

407-1.01  DESCRIPTION.  This work consists of the furnishing and mixing of aggregate, asphalt cement and additives at a mixing plant and the hauling, spreading, and compaction of the Stone Mastic Asphalt (SMA) Concrete mixture on a previously prepared surface, all as specified in the contract and in conformance with the lines, grades and thicknesses shown on the plans.

407-2.01  COMPOSITION OF STONE MASTIC ASPHALT CONCRETE MIXTURES - JOB MIX DESIGN.  Stone Mastic Asphalt Concrete mixture shall be composed of aggregate, asphalt cement, and required additives combined within the limits specified in the contract.

Provide a Stone Mastic Asphalt Concrete mixture that meets the Stone Mastic Asphalt Concrete mix design requirements of Table 407-1.

Submit the following to the Engineer at least 15 calendar days prior to the production of Stone Mastic Asphalt Concrete mixture:

1.	A letter stating the location, size, and type of mixing plant, the proposed gradation for the  Job Mix Design, gradations for individual stockpiles with supporting process control information, and the blend ratio of each aggregate stockpile.  The proposed gradation must meet the requirements of Table 703-9, Stone Mastic Asphalt Concrete Aggregate.  Stone Mastic Asphalt Concrete mixtures produced from different plants shall not be mixed.

2.	Representative samples of each of the aggregates to be blended.  Sample sizes:  45 kilograms of each intermediate and/or coarse aggregate, 90 kilograms of fine aggregate, 10 kilograms of blend sand and/or mineral filler.

3.	A minimum of three 4 liter samples of the asphalt cement proposed for use in the mixture.  Include name of product, manufacturer, test results as required in Section 702, manufacturer's certificate of compliance with Section 702, and a temperature/viscosity curve for the asphalt cement.

4.	A minimum 0.25 liter sample of the anti-strip additive proposed, including name of product, manufacturer, and manufacturer's data sheet, and current Materials Safety Data Sheet (MSDS).

5.	A minimum 2.5 kilogram sample of the stabilizing additive (cellulose or polyolefin) proposed for use in the mixture, including name of product, manufacturer, test results as required in Section 407-2.05 and manufacturer’s certificate of compliance with Section 407-2.05.

The Engineer will then evaluate the material and the proposed gradation using ATM T-17 (version 01/93) and the mix design requirements of Table 407-1 to establish the Job Mix Design.  Approved Job Mix Designs will become a part of the contract and will specify the target value for asphalt cement content, additives, and the allowable mixing temperature range.  Up to10 working days will be required to determine the Job Mix Design after receipt of all items specified above.

TABLE 407-1

STONE MASTIC ASPHALT CONCRETE

MIX DESIGN REQUIREMENTS

| Design Parameters | Requirement |
| --- | --- |
| Stability, newton, min. | 4450 |
| Flow, 0.25 mm | 8-16 |
| Voids in total mix, percent | 3-5 |
| Compaction, number of blows each side of test specimen | 50 |
| Dust-asphalt ratio (the percent of material passing the No. 0.075 mm sieve divided by the percent of asphalt, by weight of mix) | 0.6-1.4 |
| Voids in the mineral aggregate (VMA), min. Voids In Coarse Aggregate (VCA) Of The Mix, % | 17.0 Less Than VCA Of The Coarse Aggregate As Determined By AASHTO T 19 |

Approved Job Mix Designs will have the full tolerances shown in Table 407-4 applied and will not be limited to the broad band listed in Table 703-9.  Tolerances will not be applied to the largest sieve specified.

Submit changes in the Job Mix Design warranted by failure to meet the requirements of Table 407-1, changes in the source of asphalt cement, source of aggregates, aggregate quality, aggregate gradation, or blend ratio in the same manner as the original submittal.  A new Job Mix Design will only apply to Stone Mastic Asphalt Concrete mixture produced after submittal of the changes.

All mix designs after a Job Mix Design has been approved will be assessed a fixed fee of $1,500.00 each.

407-2.02  AGGREGATES.  Aggregates shall be of the type specified in the contract and shall conform to the requirements of Subsection 703-2.13.

407-2.03  ASPHALT MATERIALS.  Provide the grade of asphalt cement specified in the contract.  The asphalt cement shall conform to the applicable requirements of Section 702.  When not specified, the grade of asphalt cement shall be PG 58-28.

Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added

If there is a change in the source of the asphalt cement or if the kinematic viscosity (viscosity at 135 degrees Celsius) of the asphalt cement used on the project changes from the viscosity of the asphalt supplied for the Job Mix Design by a factor of 2 (doubles or halves) or more, then operations shall be suspended until a new Job Mix Design  is submitted and approved.

407-2.04  ANTI-STRIP ADDITIVES.  Use anti-strip agents in the proportions determined by ATM T-14 and included in the approved Job Mix Design.  At least 70 percent of the aggregate shall remain coated when tested in accordance with ATM T-14.

407-2.05  STABILIZING ADDITIVES.  Use cellulose or polyolefin stabilizing additives.  The dosage rate for cellulose is 0.3 percent by weight of the total mix.  The dosage rate for polyolefin is 0.4 percent by weight of the total mix.  The allowable tolerance per megagram shall not exceed  10 percent of the required weight of the stabilizing additive.

The cellulose stabilizing additive shall conform to the properties shown in Table 407-2. The polyolefin stabilizing additive shall conform to the properties shown in Table 407-3.

TABLE 407-2

CELLULOSE STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Sieve Analysis: Method A - Alpine Sieve Analysis(1): Fiber Length Percent passing 0.150 mm sieve Method B - Mesh Screen Analysis(2): Fiber Length Percent passing 0.850 mm sieve Percent passing 0.425 mm sieve Percent passing 0.106 mm sieve | 6.4 mm (max) 60-80 0.9-1.5 mm (avg) 75-95 55-75 10-30 |
| Ash Content(3) | 20% non-volatiles (max) |
| pH(4) | 7.5 +/-1.0 |
| Oil Absorption(5) | 5.0 +/-1.0 times fiber weight |
| Moisture Content(6) | < 5% |
| Bulk Density(7) | 20.0-40.0 kg/m3 |

Notes:

(1)	Method A - Alpine Sieve Analysis.  This test is performed using an Alpine Air Jet Sieve (Type 200 LS).  A representative five gram sample of fiber is sieved for 14 minutes at a controlled vacuum of 0.56 meters (+/- 75 mm) of water.  The portion remaining on the screen is weighed.

(2)	Method B - Mesh Screen Analysis.  This test is performed using 0.850, 0.425, 0.250, 0.180, 0.150 and 0.106 mm sieves, nylon brushes and a shaker.  A representative 10 gram sample of fiber is sieved, using a shaker and two nylon brushes on each screen.  The amount retained on each sieve is weighed and the percentage passing calculated.

(3)	Ash Content.  A representative 2-3 gram sample of fiber is placed in a tared crucible and heated between 593 and 649 C for not less than two hours.  The crucible and ash are cooled in a desiccator and reweighed.

(4)	pH Test.  Five grams of fiber is added to 100 ml of distilled water, stirred and let sit for 30 minutes.  The pH is determined with a probe calibrated with pH 7.0 buffer.

(5)	Oil Absorption Test.  Five grams of fiber is accurately weighed and suspended in an excess of mineral spirits for not less than five minutes to ensure total saturation.  It is then placed in a screen mesh strainer (approximately 0.5 square millimeter hole size) and shaken on a wrist action shaker for ten minutes (approximately 31.75 mm motion at 240 shakes/minute).  The shaken mass is then transferred without touching, to a tared container and weighed.  Results are reported as the amount (number of times its own weight) the fibers are able to absorb.

(6)	Moisture Content.  Ten grams of fiber is weighed and placed in a 121 C forced air oven for two hours.  The sample is then reweighed immediately upon removal from the oven.

(7)	Bulk Density.  Fluff fiber with air or Hobart Mixer, weigh out 25 grams of fiber, place in 100 ml cylinder, tap cylinder and measure volume.

TABLE 407-3

POLYOLEFIN STABILIZING ADDITIVE

| Property | Requirement |
| --- | --- |
| Chemical Property | Ethylene, Propylene, Butane 1, Terpolymer, double bond free with no other functional group. |
| Specific Gravity | 0.86 |
| Size | Approx. 3 mm dia. by 3 mm length |
| Softening Point | 93 C |

407-2.06  PROCESS QUALITY CONTROL.  Sample and test materials for process QC of the Stone Mastic Asphalt Concrete mixture in accordance with Subsection 106-1.03.

Failure to perform process QC forfeits the Contractor's right to retests as provided for in Subsection 407-4.02.

# CONSTRUCTION REQUIREMENTS

407-3.01  WEATHER LIMITATIONS.  Do not place Stone Mastic Asphalt Concrete mixture when it is raining or when rain is imminent, on a wet surface, on an unstable/yielding roadbed, when the base material is frozen, or when weather conditions prevent proper handling or finishing of the mixture.  Do not place Stone Mastic Asphalt Concrete mixture unless the surface temperature is 10 degrees C or warmer, or after September 10 of any year.

407-3.02  EQUIPMENT.  Use equipment in good working order and free of asphalt concrete mix buildup.  Make all equipment available for inspection and demonstration of operation 24 hours prior to placement of asphalt concrete mix.

407-3.03  BITUMINOUS MIXING PLANTS.  Use an asphalt plant designed to dry aggregates, maintain accurate temperature control, and accurately proportion asphalt cement and aggregates.  Calibrate the asphalt plant and furnish copies of the data to the Engineer at least one day prior to Stone Mastic Asphalt Concrete production.    Maintain a current Air Quality Permit issued by the State Of Alaska.

Provide a scalping screen on the asphalt plant to prevent oversize material or debris from being incorporated into the Stone Mastic Asphalt Concrete mixture.  Provide aggregate and asphalt cement sampling locations meeting OSHA safety requirements.

Do not use proportioning (batch) scales for weighing material for payment.  Weigh scales used in conjunction with a storage silo may be used to weigh the final product for payment, provided the scales are certified.

407-3.04  HAULING EQUIPMENT.  Haul Stone Mastic Asphalt Concrete mixture in trucks with tight, clean, smooth metal beds thinly coated with a minimum amount of paraffin oil, lime water solution or other manufactured asphalt release agent included on the Department's Approved Products List.  Do not use any petroleum product (e.g. diesel or fuel oil) as an asphalt release agent.  If truck beds are not satisfactorily cleaned, the Engineer may direct operations to cease.  The Engineer will not allow the operations to resume until measures are in place to insure proper cleaning of hauling units.  Hauling units will be restricted to end dumps only.

Belly dumps will not be allowed as hauling units unless a plan is developed and approved by the Engineer that ensures the following items are satisfactorily adhered to:

- Tracking of asphalt material on the haul route, both on and off the project, shall be eliminated or cleaned.

- Truck beds shall be cleaned and build up of material not allowed.

- Pavement mat temperature behind the screed shall be optimum for compaction.

If the above items are not performed to the Engineer’s satisfaction, the use of belly dumps will be terminated.

Cover the Stone Mastic Asphalt Concrete mixture with a secured watertight canvas cover extending at least 0.3 meters over the sides and end of the truck bed when required by the Engineer.

407-3.05  ASPHALT PAVERS.   Use self-propelled asphalt pavers equipped with a heated vibratory screed. Control grade and cross slope with automatic grade and slope control devices.  Use an erected string line, a mobile string-line (ski) at least 9 meters in length, or other approved grade follower to automatically actuate the paver screed control system. Use grade control on either  a) both the high and low sides or b) grade control on the high side and slope control on the low side.

Equip asphalt pavers with a receiving hopper having sufficient capacity for a uniform spreading operation.  Equip receiving hoppers with a distribution system to place the Stone Mastic Asphalt Concrete mixture uniformly in front of the screed.

Use a screed assembly that produces a finished surface of the required smoothness, thickness and texture without tearing, shoving or displacing the Stone Mastic Asphalt Concrete mixture.  Screed extensions used for paving a constant width shall be heated and vibrated.  Place auger extensions within 0.5 meters of the screed extension on both sides, or per written manufacturer’s recommendations.

The use of a pickup machine to transfer Stone Mastic Asphalt Concrete mixture from a windrow to the paver hopper will be permitted, provided the pickup machine is capable of collecting the windrowed material without damage to the underlying course.  The Engineer will not allow the continued use of the pickup machine if segregation, excessive temperature loss, or any detrimental effects are observed.

407-3.06  ROLLERS.  Supply a minimum of three rollers weighing a minimum of 11 megagrams each to compact the Stone Mastic Asphalt Concrete mixture to the required density while maintaining the pace of the paving operations.  Rollers shall be of the static steel wheel or vibratory steel wheel type.  The roller drums shall be a minimum of 2.1 meters wide.  Use self-propelled rollers specifically designed to compact hot asphalt concrete mixtures and capable of reversing without backlash.  The use of equipment which results in crushing of the aggregate, or pick-up of the Stone Mastic Asphalt Concrete mixture will not be permitted.

407-3.07  PREPARATION OF EXISTING SURFACE.  Prepare existing surfaces in conformance with the plans and specifications.  Clean existing paved surfaces of loose material by sweeping with a power broom, supplemented by hand sweeping, if necessary.

After completion of planing of a section of the roadway, the Engineer shall inspect that section for areas of distress or failure.  Areas requiring repair shall have the remaining pavement removed, and the distressed area shall be excavated to the depth and limits directed by the Engineer.  Backfill the excavated area with aggregate base course material in conformance with the requirements of Section 301, asphalt concrete leveling course, or with Stone Mastic Asphalt Concrete as directed by the Engineer.

Prior to placing Stone Mastic Asphalt Concrete mixture, uniformly coat pavement surfaces and contact surfaces of curbing, gutters, manholes, and other structures with tack coat material conforming to Section 402.

407-3.08  PREPARATION OF ASPHALT.  Provide a continuous supply of the asphalt cement to the mixer at a uniform temperature, within the Job Mix Design mixing temperature range.

407-3.09  PREPARATION OF AGGREGATES.    Provide adequate dry storage for the mineral filler and stabilizing additive.  Dry the aggregate for Stone Mastic Asphalt Concrete so the moisture content of the Stone Mastic Asphalt Concrete mixture, sampled from the windrow, the end of the auger, or from behind the screed prior to compaction, is less than 0.5% (by total weight of mix) as determined by ATM T-25.

Heat the aggregate for Stone Mastic Asphalt Concrete to a temperature compatible with the mix requirements specified.

Adjust the burner on the dryer to avoid damage to the aggregate and to prevent the presence of unburned fuel on the aggregate.  Stone Mastic Asphalt Concrete mixture in which soot or fuel is present is considered unacceptable per Subsection 105-1.11.

407-3.10  MIXING.  Uniformly combine the aggregate, asphalt cement, additives, and stabilizing additives in the amounts required by the Job Mix Design.  Mix the materials such that a complete and uniform coating of the aggregate is obtained.

1.	For batch plants.  Add the stabilizing additive through a separate inlet directly into the weigh hopper above the pugmill.  Time the addition of the stabilizing additive to occur during the hot aggregate charging of the hopper.  Provide adequate dry mixing time to ensure proper blending of the aggregate and fiber stabilizer.

2.	For drum mix plants.  Add cellulose stabilizing additive into the drum mixer at the same point the asphalt cement is added.  Add polyolefin stabilizing additive directly into the drum mixer through the RAP inlet.  Do not use polyolefin stabilizing additive in a drum mix plant without a RAP inlet.  Operate the drum mixer to ensure complete blending of the stabilizing additive into the mix.

Dry mix Stone Mastic Asphalt Concrete with cellulose stabilizing additive a minimum of 15 seconds, and wet mix a minimum of 40 seconds.  Dry mix Stone Mastic Asphalt Concrete with polyolefin a minimum of 4 seconds,  and wet mix a minimum of 30 seconds.  In batch plants, place the dry aggregate in motion immediately prior to the addition of asphalt cement.  Use a wet mixing time adequate to obtain 98% coated particles when tested in accordance with AASHTO T 195.

Mix the Stone Mastic Asphalt Concrete within the temperature range determined by the Job Mix Design.

Proportion the mineral filler into the mixture uniformly and in the desired quantities.  Provide appropriate equipment for accurately proportioning the relatively large amounts of mineral filler required for a Stone Mastic Asphalt Concrete mixture.

407-3.11  TEMPORARY STORAGE OF ASPHALT CONCRETE MIXTURE. Temporary storing or holding Stone Mastic Asphalt Concrete mixture in silo type storage bins is permitted provided that the characteristics of the Stone Mastic Asphalt Concrete mixture are not altered.  Signs of visible segregation, heat loss, changes from the Job Mix Design, change in the characteristics of asphalt cement, lumpiness or stiffness of the mixture will be cause for rejection.

Dispose of rejected Stone Mastic Asphalt Concrete mixture at no cost to the Department.

407-3.12  SPREADING AND PLACING.  Submit a Paving Plan for the Engineer's review a minimum of five working days prior to initiating paving operations.  The plan shall consist of, but not be limited to the following:

1.	Paving schedule to include sequence of operations.

2.	Operational details to include:

a.	Plant operating capacity and target production rate.  Process control testing frequency for gradation, moisture, asphalt cement content, and compaction.

b.	Number and capacity of trucks, cycle time, and delivery rate.

c.	The manufacturer and model of the paver and pickup machine, to include information on grade followers, sensors, operating speed and production rate of the pavers.

d.	Number, type, weight, and operating speed of rollers.

e.	Location and method of constructing longitudinal and transverse joints.

f.	Construction plan for paving intersections and driveways.

Place Stone Mastic Asphalt Concrete mixture upon an approved surface, spread and strike off and compact to the required compacted thickness.  Spread and compact in one layer if the total thickness is 75 mm or less.  Use asphalt pavers to distribute the Stone Mastic Asphalt Concrete mixture in lanes of such widths as to hold to a practical minimum the number of longitudinal joints required, subject to the requirements of subsection 407-3.14.

Use hand tools to spread, rake, and lute the Stone Mastic Asphalt Concrete mixture in areas where irregularities or unavoidable obstacles make the use of mechanical spreading and finishing equipment impracticable.  In such areas, compact the Stone Mastic Asphalt Concrete mixture to the required compacted thickness.

Any Stone Mastic Asphalt Concrete mixture which is contaminated or segregated will be rejected.

Pave adjacent traffic lanes to the same elevation within 24 hours when the section of roadway being paved is open to traffic unless prevented by weather or other factors beyond control.  Place approved material against the outside pavement edge when the drop-off exceeds 50 mm.

When multiple lifts are specified in the contract, do not place the final lift until all lower lifts throughout that section, as defined by the Paving Plan, have been placed and accepted.

Do not pave against new concrete curb until it has cured for at least 72 hours..

407-3.13  COMPACTION.  Immediately after spreading, thoroughly and uniformly compact the Stone Mastic Asphalt Concrete mixture by rolling.

Roll with a minimum of three steel wheel rollers of a minimum weight of  11 megagrams each.  Adjust rolling procedures to provide the specified pavement density.  Operate rollers at a uniform speed not to exceed 5 kilometers/hour and with the drive roller nearest the paver.  Roll until all roller marks are eliminated and the specified pavement density has been obtained.

Prevent adhesion of mixture to the rollers by moistening the wheels with water mixed with detergent or other approved material.  Replace rollers showing evidence of excessive pick-up.

Stop rolling operations once sufficient in-place density has been achieved.  Where migration of asphalt cement and filler to the compacted pavement surface has occurred, remove and replace with fresh Stone Mastic Asphalt Concrete mixture.

The target value for density will be 94% of the maximum specific gravity (MSG) as determined in accordance with AASHTO T 209.  For the first lot of Stone Mastic Asphalt Concrete, the MSG will be determined by the Job Mix Design.  For additional lots, the MSG will be determined by the sample from the first sublot of the lot.  Acceptance testing for field density will be determined in accordance with ATM T-18 except that a minimum 150 mm diameter core is required.  (Acceptance testing for field density of leveling course will not be done.)

Grade with rakes and lutes and compact with mechanical tampers areas not accessible to rollers.  Use a trench roller in depressed areas to achieve the required compaction.

Remove any Stone Mastic Asphalt Concrete mixture that becomes loose and broken, segregated, mixed with dirt, or is any other way defective and replace with fresh Stone Mastic Asphalt Concrete mixture and compact to conform with surrounding areas.  Remove and replace any area showing an excess or deficiency of asphalt cement.

Do not leave rollers, other equipment, or vehicles standing on pavement that has not cooled sufficiently to prevent indentation by wheels.

407-3.14  JOINTS.  Minimize the number of joints and construct to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.

The minimum specification for longitudinal joint density will be 91 percent of the MSG of the panel completing the joint.  Cut one minimum 150 mm diameter core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with ATM T-18.

When joining old existing pavement and new pavement, the old pavement shall be cut in a neat line with a power driven saw.

Remove full depth improperly formed joints resulting in surface irregularities, replace with fresh Stone Mastic Asphalt Concrete mixture, and thoroughly compact.  Do not roll joints after the material has cooled below 65 degrees Celsius.  All pavement removal shall be precut to a neat line with a power driven saw.

Apply a tack coat of asphalt cement or asphalt emulsion on all cold joints and allow to break prior to placing any fresh Stone Mastic Asphalt Concrete mixture against the joint.  Apply the tack coat just prior to paving.

Form transverse joints by saw cutting back on the previous run to expose the full depth of the course or by using a removable bulkhead.  Skew transverse joints between 15-25 degrees.

Offset longitudinal joints in one layer from those in the layer immediately below by at least 150 mm.  Align the joints in the top layer at the centerline or lane lines.  Where pre-formed marking tape striping is required, offset the longitudinal joint in the top layer not more than 150 mm from the edge of the stripe.

407-3.15  SURFACE TOLERANCE.  The surface of the Stone Mastic Asphalt Concrete will be measured after final rolling at selected locations using a 4.8 meter straightedge.  Correct variations of the surface greater than 5 millimeters from the testing edge of the straightedge between any two contacts.

The smoothness of the Stone Mastic Asphalt Concrete Pavement in all driving lanes will be measured by the Engineer with a California-type profilograph within 15 days after mainline paving is completed and all defects are corrected.  No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or matches with an existing pavement.  The profilograph results (PrI) will be reduced within the 15 day period and a price adjustment will be calculated in accordance with Subsection 407-5.01.  Furnish any required traffic control devices or flagging in accordance with Section 643.

407-3.16  PATCHING DEFECTIVE AREAS.  Remove any Stone Mastic Asphalt Concrete mixture that becomes contaminated with foreign material, is segregated, or is in any way defective.  Skin patching is not permitted.  Remove defective materials for the full thickness of the course.  Cut the pavement so that all edges are vertical, the sides are parallel to the direction of traffic and the ends are skewed between 15-25 degrees.  Coat edges with tack coat conforming to Section 402 and allow to cure.  Place and compact fresh Stone Mastic Asphalt Concrete mixture in sufficient quantity so that the finished surface conforms to grade and smoothness requirements.  Compact the Stone Mastic Asphalt Concrete mixture to the density specified.  No payment shall be made for material replacing defective material.  All costs associated with patching defective areas shall be borne by the Contractor.

407-3.17  TEST SECTION.  Place a minimum of 270 megagrams of Stone Mastic Asphalt Concrete mixture in a test section at a location approved by the Engineer 5 days prior to proceeding with Stone Mastic Asphalt Concrete paving.  The test section is used to adjust the Job Mix Design asphalt cement content and also to familiarize the Contractor's personnel with the laydown and compaction of Stone Mastic Asphalt Concrete mixture.

Stone Mastic Asphalt Concrete mixture placed in the test strip that meets specifications will be measured and paid for at contract prices.  No payment will be made for mixture that does not meet specifications.  If the test strip is placed within the project limits and does not meet specifications, it shall be removed at the Contractor's expense.

407-4.01  METHOD OF MEASUREMENT.  Stone Mastic Asphalt Concrete mixture will be measured by the megagram in accordance with Section 109.  The weight used shall be the megagrams used in the accepted pavement and no deduction will be made for the weight of asphalt cement material, anti-stripping agent or any other additive used in the mixture.

A price adjustment, when applicable, will be made based on a quality level analysis under Subsection 407-4.03.

Asphalt cement will be measured by the megagram based on the weight of asphalt cement calculated using the percent of asphalt cement for each sublot as determined by ATM T-23, or AASHTO T 308.  The same tests used for the acceptance testing of the sublot will be used for computation of the asphalt cement quantity.  If the asphalt cement content is determined by ATM T-23, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin.  If the asphalt cement content is determined by AASHTO T 308, the percent of asphalt cement for each sublot will be reduced by 0.4 percent for Stone Mastic Asphalt Concrete containing polyolefin, and by 0.3 percent for Stone Mastic Asphalt Concrete containing cellulose.

The Engineer may direct at any time that tankers be weighed before and after unloading in his presence.  If the weight determined at the project varies more than one percent from the invoice amount, payment will be based on the weight determined at the project.

No payment will be made for any asphalt cement in excess of 0.4 percent above the optimum asphalt cement content specified in the Job Mix Design.

Any leftover, waste, or diversion will be computed in a manner to be determined by the Engineer.  The weight of asphalt cement in waste Stone Mastic Asphalt Concrete will be calculated using the target value for asphalt cement as specified in the Job Mix Design.

Longitudinal joints will be measured by the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

407-4.02  ACCEPTANCE SAMPLING AND TESTING.  The quantity of  Stone Mastic Asphalt Concrete mixture produced and placed shall be divided into lots and the lots evaluated individually for acceptance.  The Department has the exclusive right and responsibility for determining the acceptability of all materials incorporated into the project.  Acceptance sampling and testing shall be performed by the Engineer.  The results of the acceptance testing performed by the Engineer will be made available to the Contractor within seven working days from the date of sampling.

A lot will normally be 4,500 megagrams.  The lot will be divided into sublots of 450 megagrams, each randomly sampled and tested for asphalt cement content, density, and gradation in accordance with this subsection.  If the project has more than one lot and less than eight additional sublots have been sampled at the time a lot is terminated, the material in the shortened lot will be included as part of the prior lot and the price adjustment computed for the prior lot will include the samples from the shortened lot.

If eight or nine samples have been obtained at the time a lot is terminated, they will be considered as a lot and the price adjustment will be based on the actual number of test results (excluding outliers) in the shortened lot.

If the contract quantity is between 900 megagrams and 4,499 megagrams, the contract quantity will be considered one lot.  The lot will be divided into 5 equal sublots and randomly sampled for asphalt cement content, density and gradation in accordance with this subsection.  The Engineer shall select one sample for every 900 megagrams of mix, or majority portion thereof, for testing.  If the test result(s) conform to the specification limits, the lot will be accepted and the weight of asphalt cement for the lot will be calculated from the average of the asphalt cement content tests performed.  If only one asphalt cement content test is performed, the weight of asphalt cement for the lot will be calculated from that one test result.  If any of the test results fail to conform to specification limits, the remaining samples will be tested and the lot evaluated for price adjustment in accordance with subsection 407-4.03 with the exception that the Pay Factor shall not exceed 1.00 for any sieve size, asphalt cement content and density.

If the contract quantity is less than 900 megagrams, Stone Mastic Asphalt Concrete pavement shall be accepted for payment based on the Engineer's approval of a Job Mix Design and the placement and compaction of the Stone Mastic Asphalt Concrete mixture to the specified depth and finished surface requirements and tolerances.  Any area of finished surfacing that is segregated, fails to meet surface tolerance requirements, cools to below 65 degrees C prior to completing compaction, or is any other way defective shall be removed and replaced with fresh Stone Mastic Asphalt Concrete mixture.  Removal and replacement of defective pavement shall be at no additional cost to the Department.

Samples taken for the determination of asphalt cement content will be taken from behind the screed prior to initial compaction.  Asphalt cement content will be determined by ATM T-23, or AASHTO T 308 with the exception that the moisture content will be determined by ATM T-25.

Samples taken for the determination of aggregate gradation will be from the same location as samples taken for asphalt cement content.  Aggregate gradation will be determined in accordance with AASHTO T 30 from the aggregate remaining after the ignition oven (AASHTO T 308) has burned off the asphalt cement.

Cut two full-depth core samples with a minimum diameter of 200 millimeters from the finished lift from each sublot within 24 hours of final rolling.  The first core sample will be used for density acceptance testing in accordance with ATM T-18.  The second core sample will be given to the Department for informational testing.  Neatly cut the core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the cores while removing.  Do not cut core samples from Stone Mastic Asphalt Concrete mats on bridge decks.  Failure to cut core samples within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Backfill all voids left by sampling with fresh Stone Mastic Asphalt Concrete mixture and compact within 24 hours of sampling.  Failure to backfill voids left by sampling within the specified period will result in a deduction of $100.00 per hole per day The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

Samples will be evaluated for acceptance in accordance with Subsection 407-4.03.

A retest of any sample outside the limits specified in Table 407-4 may be requested.  Deliver this request in writing to the Engineer within 7 days of receipt of the initial test result.  Verbal requests with the written request to be delivered after the specified 7 days will not be accepted.  The sample(s) for retesting shall be taken within 24 hours of the notice to the Engineer requesting the retest(s).  The Engineer will mark the sample location for the retest.  Failure to provide the sample(s) for retesting within the specified period forfeits the right for a retest for the affected sample(s).  The original test result will be discarded and the retest result will be used in the price adjustment calculation regardless of whether the retest result gives a higher or lower pay factor.  Only one retest per sample will be allowed.

407-4.03  EVALUATION OF MATERIALS FOR ACCEPTANCE.  The following method of price adjustment will be applied to Stone Mastic Asphalt Concrete mixture when  the contract quantity equals or exceeds 4,500 megagrams except as defined in Subsection 407-4.02.  The longitudinal joint density price adjustment will apply when Stone Mastic Asphalt Concrete quantities are equal to or greater than 900 megagrams.

All acceptance test results for a lot will be analyzed collectively and statistically by the Quality Level Analysis Method as specified in Subsection 106-1.03 to determine the estimated percent of a lot that is within specification limits.

Prior to computing the price adjustment, the validity of the test results shall be ascertained in accordance with SP-7, the Standard Practice for Determination of Outlier Test Results.  Outlier test results shall not be included in the price adjustment calculations.  If any sieve size on a gradation test, or the asphalt cement content is an outlier, then the gradation test results and the asphalt cement content results for that sample will not be included in the price adjustment.  The density test result for that sample will be included in the price adjustment provided it is not an outlier also.

If the density test result is an outlier, the density test result will not be included in the price adjustment but the gradation and asphalt cement content results for that sample will be included provided neither is an outlier.

Quality Level Analysis (Specification Conformance Analysis) is a statistical procedure for estimating the percent compliance to a specification and is affected by shifts in the arithmetic mean  and by the sample standard deviation (s).  Analysis of test results will be based on an Acceptable Quality Level (AQL) of 95.0 percent and a contractor's risk of 5.0 percent unless otherwise specified.  AQL may be viewed as the lowest percent within the specification limits of a material that is acceptable as a process average and receive 100 percent pay.  The contractor's risk is the probability that when the Contractor is producing material at exactly the AQL, the materials will receive less than 1.00 pay factor.

As an incentive to produce quality material, a pay factor greater than 1.00 may be obtained.  The maximum pay factor obtainable is 1.05.  The maximum pay factor for the largest sieve size specification for gradation shall be 1.00.  The price adjustment is based on the lowest of two pay factors.  The first factor is a composite pay factor for Stone Mastic Asphalt Concrete mixture which includes gradation and asphalt cement content.  The second factor is a separate pay factor for density.

A lot containing non-specification material (less than 1.00 pay factor) may be accepted at an adjusted price provided the pay factor is at least 0.75 and there are no isolated defects identified by the Engineer.  A lot containing non-specification material that fails to obtain at least a 0.75 pay factor will be rejected in accordance with Subsection 105-1.11.

The Engineer can reject material that appears to be defective based on visual inspection.  Such rejected material shall not be used in the work. No payment will be made for the materials rejected by the Engineer.

Quality Level Analysis.  Procedures for computation of composite pay factors are as follows:

1.	Eliminate test results found to be outliers by SP-7 (Standard Practice for Determination of Outlier Test Results) and any test results on material not incorporated into the work from the quality level analysis.

Determine the arithmetic mean  of the remaining test results:

Where:	Σ  =  summation of

x  =  individual test value to xn

n  =  total number of test values

is rounded to the nearest tenth for density and all sieve sizes except the 0.075 mm sieve.   is rounded to the nearest hundredth for asphalt content and the 0.075 mm sieve.

2.	Compute the sample standard deviation (s) after the outliers have been excluded:

Where:	Σ(x2)  =  summation of the squares of individual test values.

(Σx)2  =  square of the summation of the individual test values.

The sample standard deviation (s) is rounded to the nearest 0.01 for density and all sieve sizes except the 0.075 mm sieve.  The sample standard deviation (s) is rounded to the nearest 0.001 for asphalt content and the 0.075 mm sieve.

If the computed sample standard deviation (s) is less than 0.001, then use s = 0.20 for density and all sieve sizes except the 0.075 mm sieve.  Use s = 0.020 for the 0.075 mm sieve and asphalt cement content.

3.	Compute the Upper Specification Limit (USL) and Lower Specification Limit (LSL).  For aggregate gradation and asphalt cement content, the Specification Limits (USL and LSL) are equal to the Target Value (TV) plus and minus the allowable tolerances  in Table 407-4.  The tolerances for the largest sieve specified will be plus 0% and minus 1%.  The TV is the specification value defined by the Job Mix Design.  The TV for density is 94 percent of the maximum specific gravity (MSG).  The LSL  for density is 92 percent of MSG and the USL is 96%.

4.	Compute the upper quality index (QU):

Where:	USL = Upper Specification Limit

QU is rounded to the nearest hundredth.

5.	Compute the lower quality index (QL):

Where:	LSL = Lower Specification Limit

QL is rounded to the nearest hundredth.

6.	Determine PU (percent within the upper specification limit that corresponds to a given QU) from Table 106-1.  For negative values of QU, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

7.	Determine PL (percent within the lower specification limit that corresponds to a given QL) from Table 106-1.  For negative values of QL, see 106-1.03, 3.  QUALITY LEVEL ANALYSIS (QLA).

8.	Determine the Quality Level (QL), the total percent within specification limits, for aggregate gradation, asphalt cement content, and density.

QL = (PL + PU) - 100

9.	Using the Quality Levels from step 8, determine the lot Pay Factor for Density (DPF), and gradation and asphalt cement content pay factors (PF) from Table 106-2.

10.	Calculate the lot Stone Mastic Asphalt Concrete mixture Composite Pay Factor (CPF) for asphalt cement content and gradation using the following formula:

Round the Composite Pay Factor (CPF) to the nearest hundredth.

Table 407-5 is used to determine the weight factor (f) for each sieve size and asphalt  cement content.

Table 407-4

LOWER SPECIFICATION LIMIT (LSL) and

UPPER SPECIFICATION LIMIT (USL)

| Measured Characteristics | LSL | USL |
| --- | --- | --- |
| 19.0 mm sieve | TV-5.0 | TV+5.0 |
| 12.5 mm sieve | TV-5.0 | TV+5.0 |
| 9.5 mm sieve | TV-5.0 | TV+5.0 |
| 4.75 mm sieve | TV-4.0 | TV+4.0 |
| 2.36 mm sieve | TV-4.0 | TV+4.0 |
| 1.18 mm sieve | TV-4.0 | TV+4.0 |
| 0.600 mm sieve | TV-4.0 | TV+4.0 |
| 0.300 mm sieve | TV-3.0 | TV+3.0 |
| 0.150 mm sieve | TV-3.0 | TV+3.0 |
| 0.075 mm sieve | TV-2.0 | TV+2.0 |
| Asphalt % | TV-0.40 | TV+0.40 |
| Density | 92% | 96% |

Table 407-5

WEIGHT FACTORS

| Sieve Designation | Factor (f) |
| --- | --- |
| 19.0 mm sieve | 3 |
| 12.5 mm sieve | 5 |
| 9.5 mm sieve | 6 |
| 4.75 mm sieve | 10 |
| 2.36 mm sieve | 4 |
| 1.18 mm sieve | 4 |
| 0.600 mm sieve | 4 |
| 0.300 mm sieve | 6 |
| 0.150 mm sieve | 8 |
| 0.075 mm sieve | 10 |
| Asphalt % | 40 |

407-5.01  BASIS OF PAYMENT.  The accepted quantity will be paid for at the contract unit price for the pay items listed below, complete in place.

Anti-strip additives will be subsidiary to the stone mastic asphalt concrete.

Stabilizing additives will be subsidiary to Item 407(1), Stone Mastic Asphalt Concrete.

A change order/directive is not required for Asphalt Price Adjustment pay item.  The approved Job Mix Design will initiate Anti-Strip Additive at the prescribed rate and the Notice to Proceed shall constitute the notice required to initiate Item 407(4), Asphalt Price Adjustment.

The Asphalt Price Adjustment will be the sum of the price adjustments for each lot, fees accrued for subsequent Job Mix Design evaluations as outlined in Subsection 407-2.01, and fees accrued for failure to cut cores and/or backfill voids left by sampling in the allotted time as outlined in Sub-section 407-4.02.

The Asphalt Price Adjustment will be algebraically added to the Contractor's payment for Stone Mastic Asphalt Concrete.  Individual lot price adjustments will be based on either the Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest value.  The price adjustment for each individual lot will be calculated as follows:

Price Adjustment = [(CPF or DPF)* -1] x (megagrams in lot) x (PAB)

PAB = Price Adjustment Base = $46.00 / Megagram

* Composite Pay Factor (CPF) or Density Pay Factor (DPF), whichever is the lowest    value.

Longitudinal joint densities less than 91 percent of MSG as defined in Subsection 407-3.14 will be measured in accordance with Subsection 407-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 407(4), Asphalt Price Adjustment.

(02/28/01)R163M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

407(1)	Stone Mastic Asphalt Concrete	Megagram

407(2)	Asphalt Cement, PG 58-28	Megagram

407(4)	Asphalt Price Adjustment	Contingent Sum

SECTION 615

## STANDARD SIGNS

## Special Provision

615-1.01 DESCRIPTION. Add the following: Item 615(4) Delineators, Rigid consists of installing 150 mm x 300 mm yellow reflectors on all existing electroliers adjacent to the Glenn Highway from the intersection of Airport Heights to the Artillery Road interchange as directed by the Engineer. Attach using banded couplings of the type described in section 615-2.01.

Item 615(5), Delineators, Flexible consists of installing flexible delineators adjacent to the Glenn Highway along the four curves north of the Fort Richardson interchange and south of the Artillery Road interchange.

615-2.01 MATERIALS. Add the following:

Rigid delineators.   Use materials that conform to the following:

Reflectors	Yellow, high-intensity reflective sheeting meeting the requirements of Subsection 730-2.03

Brackets	ANSI type 304 stainless steel single-bolt flared

(Use Signfix cat. # HPN177 or Bandit cat. # D021)

Bands	19 mm wide, 0.30 mm thick stainless steel

Buckles	Stainless steel

Attaching hardware	6 mm galvanized bolts with nylon washers and

Galvanized self locking nuts

Flexible delineators.  Use white reflective sheeting on one of the following:

- Guardrail Delineator Post manufactured by Carsonite International, 2900 Lockheed Way, Carson City, Nevaday 89701.

- Guardrail Delineator manufactured by Safe-Hit Corporation, 1930 West Winton Avenue, Building 11, Hayward, California 94545.

- Flex-o-Guide, Model EY426 manufactured by Flexible Safety Zoning Company, 4152  Warren Avenue, Hillside, Illinois 60162.

615-3.01 CONSTRUCTION REQUIREMENTS. Add the following:

Rigid delineators: Attach two flared brackets to each reflector.  Attach the brackets to the existing electroliers using bands and buckles.  Tighten each band until it stops moving through the buckle.

Flexible delineators: Install the flexible delineators 2.4 meters from the edge of pavement at the locations described in Section 615-1.01.  Install the delineators according to the manufacture’s recommendations and standard drawing T-05.00[M] with the following spacing:

Curve 1- First curve north of the Fort Richardson interchange

Spacing in advance and beyond curve (A1, A2, & A3)	90 meters

Spacing “SC”		57.96 meters

Curve 2- Second curve north of the Fort Richardson interchange

Spacing in advance and beyond curve (A1, A2, & A3)	90 meters

Spacing “SC”		57.12 meters

Curve 3- Third curve north of the Fort Richardson interchange

Spacing in advance and beyond curve (A1, A2, & A3)	90 meters

Spacing “SC”		60.52 meters

Curve 4- Forth curve north of the Fort Richardson interchange

Spacing in advance and beyond curve (A1, A2, & A3)	90 meters

Spacing “SC”		59.67 meters

There is an existing overhead sign behind guardrail located at the P.C. of the forth curve north of the Fort Richardson interchange.  Attach a yellow reflector to this pole as shown in the Plans and described in the Rigid Delineator Construction Requirements.  Do not install a flexible delineator at this P.C.

Delete Section 641 in its entirety and substitute the following:

## SECTION 641

## TEMPORARY EROSION AND POLLUTION

## CONTROL

## Special Provisions

641-1.01 DESCRIPTION. This work shall consist of temporary control measures as shown on the plans, or ordered during the life of the contract, to control temporary erosion and water pollution. This work shall include preparation of a Temporary Erosion and Pollution Control (TEPC) Plan. Conduct construction activities in accordance with the approved TEPC Plan.

641-1.02 TEMPORARY EROSION AND POLLUTION CONTROL PLAN. Submit a TEPC Plan at least five (5) days prior to the preconstruction conference, for approval by the Department's Environmental Section. The TEPC Plan shall consist of the following:

1.	Methods for clearing and grubbing.

2.	Plan for installation of temporary erosion and sediment control measures, in accordance with the Department's Storm Water Manual, including, but not limited to, the following:

a.	Excavation and embankment construction;

b.	Construction of temporary and permanent drainage features;

c.	Construction in and around waterbodies and wetlands; and

d.	Haul roads and material sites.

e.	List of quantities, types and suppliers of materials to be used.

3.	Disposal of waste material.

4.	Containment, cleanup, and disposal of such substances, as well as the methods to be utilized for disposing of, petroleum products or other hazardous substances generated by construction equipment or activities. The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.

The Department will review the TEPC Plan for approval within five (5) working days. If corrections or modifications are necessary to the plan, resubmit the corrected within five (5) days of receipt of the comments.

641-2.01 CONSTRUCTION REQUIREMENTS. The Contractor shall limit the surface area of erodible earth material exposed by clearing and grubbing, excavation, borrow and fill operations and the Engineer will direct the Engineer to provide immediate permanent or temporary pollution control measures to prevent contamination of adjacent streams, lakes, ponds or other areas of water impoundment. As necessary, such work may involve the construction of temporary berms, dikes, dams, sediment basins, slope drains, and use of temporary mulches, seeding or other control devices or methods as necessary to control erosion. Use temporary pollution control measures to correct conditions that develop during construction that were not foreseen during the design stage, that are needed prior to installation of permanent pollution control features, but are not associated with permanent control features on the project.

The Contractor shall incorporate all permanent erosion control features into the project at the earliest practicable time as outlined in the schedule.

Seed and mulch cut slopes as the excavation proceeds to the extent considered desirable and practicable.

Where erosion is likely to be a problem, schedule and perform clearing and grubbing operations so that grading operations and permanent erosion control features can follow immediately thereafter if the project conditions permit; otherwise temporary erosion control measures may be required between successive construction stages. The surface area of erodible earth material exposed at one time by clearing and grubbing shall not exceed 2.02 hectares without written approval.

The Contractor shall limit the area of excavation, borrow and embankment operations in progress commensurate with the Contractor’s capability and progress in keeping the finish grading, mulching, seeding and other such permanent pollution control measures current in accordance with the accepted schedule. Should seasonal limitations make such coordination unrealistic, take temporary erosion control measures immediately to the extent feasible and justified.

In the event of conflict between these requirements and pollution control laws, rules or regulations of other federal or state or local agencies, the more restrictive laws, rules or regulations shall apply.

The Contractor shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-3.01 METHOD OF MEASUREMENT. The method of measurement shall be as specified in the order authorizing the work.

641-4.01 BASIS OF PAYMENT. Temporary erosion and pollution control work required, which is not attributed to the Contractor’s negligence, carelessness or failure to install permanent controls, will be paid for as specified in the order authorizing the work.

In the event that temporary erosion and pollution control measures are required due to the Contractor’s negligence, carelessness or failure to install permanent controls as a part of the work as scheduled and as ordered, such work shall be performed at the Contractor’s expense.

In case of repeated failures on the Contractor’s part to control erosion, pollution and/or siltation, the Engineer reserves the right to employ outside assistance or to use his own forces to provide the necessary corrective measures. Such incurred direct costs plus project-engineering costs will be charged to the Contractor and the appropriate deductions made to the monthly progress estimate.

Temporary pollution control may include construction work outside the right-of-way where such work is necessary as a result of roadway construction, such as State Furnished Material sources. Temporary erosion and pollution control in connection with contractor furnished material sources shall be at the Contractor’s expense.

Install and acceptably maintain the erosion control.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Temporary Erosion and Pollution Control	Contingent Sum

(3/28/00)R203M98

SECTION 642

#### CONSTRUCTION SURVEYING AND MONUMENTS

Standard Modifications

642-3.01 GENERAL.  Delete the seventh paragraph.

(06/25/99)M 79

#### Special Provisions

642-3.01 GENERAL. Add the following to the third paragraph: Prior to any work on the project, stake and reference the construction centerline. Reference the existing centerline at 25 meter intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 meters and shall show the offset distance to centerline and the station from the beginning of the project.

Install a reference sign every 150 meters. These reference signs shall meet the following requirements:

1.	mounted a minimum of 1.5 meters above the shoulder,

2.	located a minimum of 3 meters from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 125-mm high black lettering on an orange background.

Reference the beginning and ending points of the no-passing zones in a separate field book.

SECTION 643

## TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (03/06/01)R222M98

#### Standard Modifications

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.(9/29/00) M91

## Special Provisions

643-2.01 MATERIALS. Add the following:

17.	Flexible Markers.  Refer to subsection 606-2.01 Materials.

(03/06/01)R222M98

## Standard Modifications

Add the following subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (09/29/00) M91

## Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (03/06/01)R222M98

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Add the following:

The Contractor shall not restrict traffic during the following times:

- Monday through Friday 6:00 AM through 8:00 AM, Southbound only.

- Monday through Thursday 4:00 PM to 6:00 PM, Northbound only.

3.	Friday from 3:00 PM to 9:00 PM, Northbound only.

4.	Sunday from 12:00 (noon) to Sunday at 10:00 PM, Southbound only.

5.	Around any holiday:

- If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 3:00 P.M. on the Friday before the holiday to 3:00 A.M. on the day after the holiday.

- If a holiday falls on Wednesday, the above stipulations apply from 3:00 P.M. on the Tuesday before the holiday to 3:00 A.M. on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 3:00 P.M. on the day before the holiday to 3:00 A.M. on the Monday after the holiday.

- During the Alaska State Fair:

Friday 3:00 P.M. through Sunday 11:59 P.M.

The Contractor shall make every effort not to delay school buses through the construction work zone.

Lane restrictions, if allowed, shall be conducted so that no more than a 5 minute accumulated delay is encountered by a waiting motorist through the entire length of the project, except during paving operations when 10 minutes delay will be allowed for all motorists except school buses. If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

The Contractor will be permitted to allow traffic to run on a milled surface only up to seven days. At the end of a continuous work shift both lanes of traffic in the same direction shall be milled and striped. No pavement lips along the centerline will be left after the work shift has ended.  The Engineer will allow one-lane road operations for asphalt installation. One-lane road operations will be limited to 5 kilometers

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion | Each | $2,500.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Plastic Safety Fence | Meter | $16.40 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.32 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (03/06/01)R222M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)				Flagging		         Contingent Sum

#### SECTION 644

#### SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE. Delete the third fifth and seventh sentences of the first paragraph and the second paragraph in this subsection and substitute the following: Meet the following office requirements:

1.	A minimum of 50 square meters of floor area. Divide the office area so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	A minimum of two electrical outlets.

4.	Adequate parking for a minimum of 10 vehicles, with one disability parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

5.	Provide attached indoor plumbing with sanitary lavatory facilities and potable drinking water.

6.	Three telephone lines available at the project location.

7.	Located in Eagle River or within 20 kilometers south of Eagle River.

8.	Provide one move in and one move out for state office furniture and equipment.

Standard Modifications

644-2.01 FIELD OFFICE.  In the third paragraph, change “the final inspection” to “project completion”.

Standard Modifications

644-4.01 BASIS OF PAYMENT. In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators, “.

(06/25/99)M 81

#### Special Provisions

644-4.01 BASIS OF PAYMENT. Add the following: The Engineer will not pay for electricity, propane and water supplied for the State provided portable asphalt lab separately.  Those items are subsidiary to Item 644(1) Field Office.

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

SECTION 670

## TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Under item 4 Methyl Methacrylate Pavement Markings, delete the last sentence in the first paragraph and substitute the following: Do not apply striping to the new asphalt until the asphalt has cured for the duration listed below and at the Engineer’s discretion.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Under item 4 Methyl Methacrylate Pavement Markings, delete the second paragraph and substitute the following: Apply Methyl Methacrylate marking material with truck mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.

Add the following under item 4. before the third paragraph: A film test stripe will be required at the beginning of each striping shift, and when there is a change in the asphalt type.  Additional film test stripes may be required at the Engineer’s discretion.   (7/28/99)R221M98

Under item 4. Methyl Methacrylate Pavement Markings, delete the first sentence in the fifth paragraph and substitute the following: Apply markings for lane lines, edge lines and centerlines at the thickness shown in the Plans.

Under item 4 Methyl Methacrylate Pavement Markings, delete the first sentence of the sixth paragraph and substitute the following: Apply transverse type pavement at the thickness shown in the Plans.

670-3.04 PAINT REMOVAL. Change the title of this subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15m longitudinal run from the plan quantity. (12/15/00)R246M98

# SECTION 702

## ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following.

Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

Performance Graded Asphalt Cement

PG 52-28		PG 58-28		PG 64-28

Softening Point

AASHTO T-53	(none)			49°C			52°C

Toughness min.

ASTM D5801 	(none)			12.4 N-m		12.4 N-m

Tenacity min.

# ASTM D5801		(none)			8.5 N-m		8.5 N-m

(9/18/00)R244M98

## SECTION 703

## AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

## TABLE 703-2

## AGGREGATE FOR UNTREATED BASE

Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

Coarse Aggregate.  Change the percent fracture: from 80 min. (single face) to 95 min.(double face).

Fine Aggregate.   Add the following: Fine aggregate shall be produced from crushing.  Natural aggregate that is minus #4 shall be removed and stockpiled separately from the crushed fines.

Blended Aggregate.   Add the following: No more than 10 percent natural fines may be added to produce the asphalt job mix aggregate gradation.

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.(06/25/99)M 82

703-2.13 AGGREGATE FOR STONE MASTIC ASPHALT PAVEMENT

Coarse Aggregate (retained on the 4.75 mm sieve).  Crushed stone or crushed gravel consisting of sound, tough, durable rock of uniform quality.

Free from clay balls, vegetative matter or other deleterious matters.  Not coated with dirt or other finely divided mineral matter.  Meet the following requirements:

Property			Test Method		Requirement

Percent of Wear		AASHTO T 96	45 max.

Degradation			ATM T-13		30 min.

Percent Sodium Sulfate Loss	AASHTO T 104	9   max. (5 cycles)

Percent Fracture		ATM T-4

Double Face					90 min.

Flat & Elongated Particles	ATM T-9

3 to 1						25% max.

5 to 1						5%   max.

Absorption			AASHTO T 85	2%   max.

Fine Aggregate (passing the 4.75 mm sieve).  Meet the quality requirements of AASHTO M 29, including S1.1, Sulfate Soundness.  Consist entirely of 100 percent crushed aggregate and be non-plastic as determined by AASHTO T 90.

Mineral Filler.  Meet the requirements of AASHTO M 17.  Contain 3.0 percent or less organic impurities as determined by ATM T-6, and have a plastic index not greater than 4 as determined by AASHTO T 90.  Mineral filler shall be free of  agglomerations and be sufficiently dry to flow freely.

Blended Aggregate.  Blend the aggregate fractions to meet the grading requirements of Table 703-9 as determined by ATM T-7.

## TABLE 703-9

## STONE MASTIC ASPHALT CONCRETE AGGREGATE

Percent Passing by Weight

Sieve Designation			Requirement

19.0 mm			100

12.5 mm			76-88

9.5 mm			57-70

4.75 mm			20-27

2.36 mm			17-23

1.18 mm			14-20

0.6 mm			12-17

0.3 mm			11-15

0.15 mm			10-14

0.075 mm			7-10

SECTION 712

## MISCELLANEOUS

## Special Provisions

712-2.17 METHYL METHACRYLATE PAVEMENT MARKINGS. Add the following subsection:

2.	Performance Properties: Add the following:

k.	Adhesion: To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

(7/28/99)R221M98

APPENDIX A

ERROSION AND SEDIMENT CONTROL PLAN

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST