# SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

2.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

3.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

4.	The Department has approved an environmental document addressing concerns and environmental commitments and is available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

5.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SECTION 101

DEFINITIONS AND TERMS

## Standard ModificationsStandard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

## Special Provisions

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material. (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

103-1.01 CONSIDERATION OF BIDS.

Add the following after item 9.: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State. (10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”. (06/25/99)M 69

SECTION 105

CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Alaska Fiberstar Alaska Native Hospital AT&T Alascom, Inc. Chugach Electric Association Digline - Boise loan to AK ENSTAR Natural Gas, Inc. GCI Marathon Oil Corporation PTI Communications, Inc. Phillips Petroleum Rogers Cable Systems of AK, Inc. Signature Flight Support SOA-DOT/PF Anchorage M&O TelAlaska, Inc. Tesoro Petroleum Co. Unocal Oil & Gas

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations	235-5217

City of Seward	224-4049

Shoreside Petroleum	224-8040

There are various utility appurtenances located within the project limits. Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

Work around those utilities not designated for relocation in the plans and the following utility specific coordination .  The Contractor shall bear the expense for any changes or additional relocation requested for Contractor convenience.

Work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

The Contractor shall bear the responsibility for any changes in contract scheduling that result in the conditions in this specification not being met.  Additional coordination with the applicable utility will be required.

Schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required prior to utility relocation.

Payment will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen (15) calendar days advance written notice for required staking.

Provide the Utility Companies fifteen (15) calendar days advance written notice of the relocations described below to begin.  The Utility Companies will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific coordination requirements for the specific utilities are included below:

CITY OF SEWARD – ELECTRICAL 	The City of Seward owns an overhead and underground electrical distribution system, which crosses the project in several locations conflicting with the proposed storm drain system. At the following locations the City will adjust the existing facilities;

## Port Avenue

Station 5+164 – Two existing 4” conduits at this location require adjustment to avoid the proposed storm drain.  A 6m trench will be required to lower the conduits 254mm.  The adjustment will require one (1) calendar day.

Station 5+235 – Several conduits at this location require adjustment due to conflicts with the proposed storm drain.  Three 4” and two 2” conduits will be lowered 305mm, requiring 5.5m of trench.  Adjustment work will require one (1) calendar day.

Station 5+316 – A 4” and a 2” conduit at this location will be raised 152mm to avoid the proposed storm drain.  A 3.7m trench is needed for the adjustment, which will require one (1) calendar day.

Station 5+420 – Three 2” conduits at this location will be raised 152mm to avoid the proposed storm drain.  The relocation requires a 3.7m trench.  Relocation work will require one (1) calendar day.

Station 5+443 – Existing facilities at this location are in conflict with the proposed storm drain and require adjustment.  Two 4” conduits and a 2” conduit will be raised 406mm, requiring 9.8m of trench.  Work at this location will require one (1) calendar day.

# Fourth Avenue

Station 10+139 Lt. – 10+182 Lt. – To provide power to an existing streetlight, COS will install 45.7m of cable at this location.  Construction will require four (4) calendar days.

Station 10+214 – Due to conflicts with the proposed storm drain, relocation of existing facilities at this location is required.  The relocation consists of lowering two sections of conduit 762mm and installing a new 55.5m run to avoid boat launch ramps.  Relocation work will require five (5) calendar days.

Station 10+309 – An existing 2” conduit will be raised 152mm to avoid a proposed storm drain inlet.  The relocation requires a 3.7m trench and will require one (1) calendar day.

Station 10+280 – Cable supplying power to existing streetlights must be disconnected and removed when the Contractor is ready to refeed.  Work will require one (1) calendar day.

Station 10+383 – The existing electric line at this location is in conflict with a proposed storm drain inlet.  The existing conduit must be moved 610mm east, requiring a 14.6m trench.  Relocation work will require two (2) days.

Station 10+515 – An existing 2” conduit at this location is in conflict with a proposed storm drain inlet.  The conduit will be raised 152mm, requiring a 3.7m trench.  The adjustment will require (1) calendar day.

Station 10+530 – The existing electrical facilities at this location require relocation to avoid a proposed storm drain manhole.  The relocation will require the installation of two new 4” conduits and repulling the existing cable.  Relocation work will require four (4) calendar days.

Station 10+573 – The existing conduit at this location will be lowered 203mm to avoid the new storm drain.  The adjustment will require one (1) calendar day.

Station 10+661 – The existing conduit at this location is in conflict with the proposed storm drain and will be raised 127mm, requiring a 3m trench.  Work at this location will require (1) calendar day.

Station 10+704 – Existing transformers at this location will be relocated and replaced with two new transformers due to conflicts with the proposed sidewalk and to provide service to new lighting.  Relocation work will require five (5) calendar days.

Station 10+724 – An existing 4” conduit at this location is in conflict with the proposed storm drain.  The conduit will be raised 356mm, requiring an 8.5m trench.  Work at this location will require one (1) calendar day.

Station 10+760 – The contractor will need to contact the City of Seward Electrical Department 48 hours in advance of work near the crossing.  The existing electric facilities will need to be supported while installing the crossing.

TELALASKA – TELEPHONE   TelAlaska owns and operates an overhead and underground telephone system, which crosses the project in several locations conflicting with the proposed storm drain system. At the following locations, TelAlaska will adjust the existing facilities:

## Port Avenue

Station 5+235 – TelAlaska’s existing facilities at this location are in conflict with the proposed storm drain and will be relocated.  New conduit will be installed along with a new 61.6m 100-pair  telephone cable.  Relocation work will require four (4) calendar days.

Station 5+320 – An existing 50-pair telephone cable at this location will be relocated due to conflicts with the proposed storm drain.  20m of conduit and a 50-pair cable will be installed and the existing cable and conduit will be removed.  The relocation will require three (3) calendar days.

## Fourth Avenue

Station 10+215 – 10+280 – There are two conflicts between TelAlaska’s facilities and the proposed storm drain at this location.  TelAlaska’s relocation will include installing a new 21.3m length of 4” conduit from the telephone pedestal at Sta. 10+215 Rt. to the existing conduit that runs along the middle of the road.  TelAlaska will also install 24.4m of 4” conduit across the road at MH9 (Sta. 10+276 Lt.).

110m of 50-pair cable will be installed between the pedestal at Sta. 10+215 Rt. and MH9.  81.1m of 200-pair cable will be installed between MH9 and the cross-connect on the east side of the road.  The relocation will require six (6) calendar days.

Station 10+575 – The existing telephone crossing at this location is in conflict with the proposed storm drain and requires relocation.  A new 22.9m section of 6-way duct will be installed across the roadway and connected to the existing duct.  82.9m of new 600-pair and 300-pair telephone cables will be installed between MH12 and MH13.  The relocation work at this location will require six (6) calendar days.

Station 10+730 – The existing service connection at this location is in conflict with the proposed storm drain and requires relocation.  The existing service will be abandoned and reestablished from MH9A.  52.1m of 2” conduit and a 25-pair cable will be installed from MH9A to the NAPA Auto Parts building.  The relocation will require three (3) calendar days.

GCI-Telecommunications.   GCI may have wires that conflict with the storm drain outfall and may require adjustment at the southwest boat harbor ramp.

All traffic control, temporary or permanent asphalt placement and concrete placement will be provided for the companies by the Contractor.

(11/2/99)R3M98

105-1.15 PROJECT COMPLETION. Delete the first sentence and substitute the following:  Upon written notice from the Contractor of presumptive completion of all construction provided for under the Contract, the Engineer and the City of Seward will conduct the final inspection.

Delete the last paragraph and substitute the following:  When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas; and Subsection 621-3.04, Period of Establishment; Subsection 641-1.042.01, Storm Water Pollution Prevention Plan (SWPPP) Requirements and Subsection 641-3.01, Construction Requirements, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04, and 621-3.04, 641-1.042.01 and 641-3.01, and will stop the count of contract time but will not relieve him of any obligations under the Contract. (02/06/02)R237M98

Standard Modifications

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following: Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630. (03/26/01) M 101

Special Provisions

-Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. Comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this subsection.

Take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.02  LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.:  In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to their beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (05/01/02)R262M98

Special Provisions

106-1.03 TESTING AND ACCEPTANCE. Add the following:

When the specifications refer to the following test methods, use the corresponding ‘New Test Method’ shown below.  ATM = Alaska Test Method.  AASHTO = American Association of State Highway and Transportation Officials.  FOP = Field Operating Procedure.  WAQTC = Western Alliance for Quality in Transportation Construction.

Test Method	New Test Method

ATM T-1	Alaska FOP for AASHTO T 87/T 88

ATM T-3	Alaska FOP for AASHTO T 205

ATM T-4	WAQTC TM 1

ATM T-5	WAQTC FOP for AASHTO T 255/T 265

ATM T-6	Alaska FOP for AASHTO T 267

ATM T-7	WAQTC FOP for AASHTO T 27/T 11

ATM T-8	WAQTC FOP for AASHTO T 152

ATM T-11	WAQTC TM 7 and WAQTC FOP for AASHTO T 224

ATM T-18	WAQTC FOP for AASHTO T 166/T 275

ATM T-22	WAQTC TM 8

ATM T-23	WAQTC TM 4

ATM T-25	WAQTC TM 6

AASHTO T 2	WAQTC FOP for AASHTO T 2

AASHTO T 23	WAQTC FOP for AASHTO T 23

AASHTO T 27/T 11	WAQTC FOP for AASHTO T 27/T 11

AASHTO T 30	WAQTC FOP for AASHTO T 30

AASHTO T 40	WAQTC FOP for AASHTO T 40

AASHTO TP 53/T 308	WAQTC FOP for AASHTO TP 53

AASHTO T 85	WAQTC FOP for AASHTO T 85

AASHTO T 87/T 88	WAQTC FOP for AASHTO T 87/T 88

AASHTO T 89	WAQTC FOP for AASHTO T 89

AASHTO T 90	WAQTC FOP for AASHTO T 90

AASHTO T 99/T 180	WAQTC FOP for AASHTO T 99/T 180

AASHTO T 119	WAQTC FOP for AASHTO T 119

AASHTO T 121	WAQTC FOP for AASHTO T 121

AASHTO T 152	WAQTC FOP for AASHTO T 152

AASHTO T 164	WAQTC FOP for AASHTO T 164

AASHTO T 166/T 275	WAQTC FOP for AASHTO T 166/T 275

AASHTO T 168	WAQTC FOP for AASHTO T 168

AASHTO T 176	WAQTC FOP for AASHTO T 176

AASHTO T 182	Alaska FOP for AASHTO T 182

AASHTO T 205	Alaska FOP for AASHTO T 205

AASHTO T 209	WAQTC FOP for AASHTO T 209

AASHTO T 224	WAQTC FOP for AASHTO T 224

AASHTO T 248	WAQTC FOP for AASHTO T 248

AASHTO T 255/T 265	WAQTC FOP for AASHTO T 255/ T 265

AASHTO T 267	Alaska FOP for AASHTO T 267

(07/26/01)S 87

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If you discover cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by your operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Provide all necessary information to comply with the US Environmental Protection Agency National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska to discharge storm water from the construction site. Refer to Section 641, Erosion, Sediment, and Pollution Control for requirements for this permit.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If you require water for any construction purpose from a non-municipal water source, obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (5/29/02)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated to be within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

Provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99)R170M98

Add the following Subsection:

107-1.21 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program	Section 120

Training Program	Section 645

Federal EEO Bid Conditions	Form 25A-301

EEO-1 Certification	Form 25A-304

DBE Subcontractable Items	Form 25A-324

ADOT&PF Training Program Request	Form 25A-310

# Training Utilization Report		Form 25A-311

Contact Report	Form 25A-321A

DBE Utilization Report	Form 25A-325C

Summary of Good Faith Effort Documentation	Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts	Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments.  (01/22/02)S 80

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments. (9/11/01)

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

Ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

## Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under Item 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.03, Submittals.

(01/31/02)R160M98

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:  The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(2/15/01)R242M98

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor:

Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work. (5/31/00)M90

Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e. (02/08/01)M71

## Special Provisions

Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

###### Standard Modifications

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if the work is done by a lower tier subcontractor. (02/08/01)M71

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from you, will release this amount.

Failure to comply with the requirements of the National Pollutant Discharge Elimination System (NPDES) General Permit for Alaska, as indicated under Section 641, Erosion, Sediment, and Pollution Control, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. This amount will be released by the Engineer upon satisfactory completion of the requirements of the permit.

(02/04/02)R137A

###### Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. Carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The determination of CUF is made by the Engineer after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal.The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the quantity of work of a bid item involving a DBE firm is reduced by the Department, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If a DBE replacement is approved by the Engineer, replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. Such an opportunity must be exercised by the bidder within 3 calendar days of notification it has failed to meet the requirements of this subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The decision on reconsideration will be made by the DBE Liaison Officer.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, immediately notify the Engineer of the default and the circumstances surrounding the default.

Take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-3.03 REMOVAL OF BRIDGES, CULVERTS AND OTHER DRAINAGE STRUCTURES. Add the following after the second paragraph: Remove, dispose or salvage storm drain manholes designated for removal by the Plans or as directed by the Engineer.

Remove manhole frame and cover, dustpan, adjusting rings and cone section or reducing slab for existing sanitary sewer manholes designated for removal by the Plans or by the Engineer. Plug all conduits intersecting the manhole and fill the remaining barrel sections of the abandoned manholes with material meeting the requirements of selected material, Type C and compact it to the satisfaction of the Engineer.

Carefully remove and deliver salvaged materials to a site directed by the Engineer. Provide a disposal site for non-salvageable materials.

All existing manhole frames, covers, dustpans, adjusting rings, cone sections and reducing slabs removed but not reinstalled or salvaged under these Special Provisions shall become the property of the Contractor.  Materials may be reused if they are undamaged, of satisfactory quality and approved by the Engineer.  No materials are reused for reinstalled until they have been thoroughly cleaned by the Contractor and inspected by the Engineer. (2/2/00)R18M98

Add the following:  The Seward Parks and Recreation Department will remove the Parking Fee Kiosks.  Contact Karin Sturdy at 224-4053 two weeks before you begin construction to allow for their removal.

The Harbormaster’s Office will remove the Slip Pay Box.  Contact Jim Beckham, Harbormaster, at 224-3138 two weeks before you begin construction activities to allow for its removal.  The Harbormaster’s office will also remove the parking bumpers in front of their office.  Contact Jim Beckham two weeks before they need to be removed to allow for their removal.

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590. (3/29/01)R84M98

Add the following Subsection:

202-3.06 SALVAGING. Notify the Engineer, five (5) days prior to removing manholes and inlets. Upon excavation, the Engineer will physically identify those manholes, inlets or portions thereof to be salvaged.  All manholes, inlets or portions thereof so designated will be delivered to the Department of Transportation Maintenance Yard located in Seward.  All remaining items removed become the property of the Contractor.  (8/30/00)R258M98

202-5.01 BASIS OF PAYMENT.  Delete Item 202(6) Removal of Manholes.

(2/2/00)R18M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 202(6A) Removal of Storm Drain Manholes | Each |

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the Plans call for placement of selected material and excavation is required, the existing material may be left in place at the Engineer’s discretion if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope of Work.  (03/14/02)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (03/14/02)R193M98

203-4.01 METHOD OF MEASUREMENT.  Add the following to item 1.:  No volume reduction will be made for material removed under Items 202(2), 202(3), and 202(9)

Add the following:

6.	Item 203(3B).  No measurement of quantities will be made.

203-5.01 BASIS OF PAYMENT.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 203(3B) Unclassified Excavation | Lump Sum |

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

Add the following after the first paragraph: At your option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

(2/28/01)R176M98

301-3.01 PLACING. Add the following: Base course material used for the sidewalk and pathway foundation shall be placed with a "Layton box" or similar equipment capable of providing a specified depth with a uniform surface. (9/1/89)R26

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-2.01  Composition Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03  Asphalt Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following.

Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09  Preparation Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14  Joints.  Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one minimum diameter 150 mm core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined according to WAQTC FOP for AASHTO T 166/T 275.

401-3.15 SURFACE TOLERANCE. Add the following, The Engineer shall measure the surface smoothness in all driving lanes of the project with an inertial profiler before construction begins. The surface profile will be measured in the left wheel path of each lane.   No measurements will be taken in turn lanes, lane transitions, or within 8 meters of bridge abutments or project limits.  A 5 mm blanking band filter will be used in the calculations of the Profilograph results.  The Engineer will report an Initial Average Profile Index Value (Initial PrI) that includes all measured lanes, calculated to the nearest 1 mm per km.

The Engineer shall measure the surface smoothness of the top lift of asphalt in all driving lanes with an inertial profiler before final acceptances of the project and after completion of corrective work.  The surface profile will be measured by the same method completed above.  The Engineer will report a Final Average Profile Index Value (Final PrI) that includes all measured lanes, calculated to the nearest 1 mm per km.  Any portion of final pavement surface having a smoothness PrI greater than 230 mm / km in a 160 meters segment shall be removed and replaced.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01  Method Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02  Acceptance Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC  TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined according to WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, the gradation will be determined according to WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One minimum diameter 150 mm core is required for acceptance density testing only.  Acceptance density testing will be according to WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

A separate price adjustment for pavement smoothness as measured in accordance with Subsection 401-3.15 will be calculated in accordance with Table 401-1 and applied under Item 401(6), Asphalt Price Adjustment.

Reduction Factor (R) = (Initial PrI-Final PrI)/ Initial PrI

# TABLE 401-1

| Reduction Factor (R) | Adjustment to Item 401(6), Asphalt Price Adjustment, for Pavement Smoothness |
| --- | --- |
| 0.61 to 1 | Add $1000 multiplied by [(R – 0.6)*100] |
| 0.5 to 0.6 | No Adjustment |
| 0 to 0.49 | Deduct $1000 multiplied by [(0.5 - R)*100] but not to exceed $10,000 |

(03/19/02)R199M98

SECTION 603

# CULVERTS AND STORM DRAINS

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence.

603-3.03 JOINING PIPE.

2. 	Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.” (02/08/01)M95

SECTION 604

MANHOLES AND INLETS

Special Provisions

604-2.01 MATERIALS. Add the following:

Aluminum Plate	ASTM B 209

Aluminum Angle	ASTM B 308

604-3.01 CONSTRUCTION REQUIREMENTS. Add the following after the third sentence: Any proposed access manhole that falls within a concrete sidewalk or asphalt pathway must have a lid with a rough cobbled grit surface, or be specifically designed to hold a minimum of 25 mm concrete or asphalt, as applicable.

Under the heading “Reconstruct existing manhole by using one or more of the following methods,” add the following:

6.	Salvage existing frame and grate, remove and dispose of the existing reducing slab and adjustment rings and install a new cover slab (reducing slab without an access hole).  Salvaged frame and grate shall be delivered to the local DOT maintenance station.

Add the following: When installing new pipe in an existing manhole, cleanly cut a hole by approved means at the invert elevation given on the Plans and 50 mm larger than the outside diameter of the new pipe. Then, grout joint with non-shrinking cement mortar.

All curb inlet structures shall have a 75 mm formed hole approximately 600 mm below the top of casting on the project centerline side to provide for direct drainage during subgrade construction to avoid embankment saturation. Keep the openings functional. This may require temporary dikes, RMC extensions, etc., as necessary. Fill these holes with grout upon final paving.

Cast standard drainage structure steps during structure pour or install them before concrete hardens.

604-5.01 BASIS OF PAYMENT. Add the following: Frames, grates and lids are subsidiary to the drainage structure. (9/1/00)R43M98

Delete Item 604(1) Storm Sewer Manhole.  Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 604(1A) Storm Drain Manhole, Type I | Each |
| 604(1B) Storm Drain Manhole, Type II | Each |

## SECTION 608

# SIDEWALKS

### Special Provisions

608-1.01  DESCRIPTION.  Replace this Subsection with the following:  Provide equipment, materials and labor necessary to install cast-in-place P.C.C. sidewalk with exposed aggregate finish in conformance with the Plans and these Special Provisions.

### 608-2.01 MATERIALS. In paragraph number 2 delete “AC-5” and substitute “PG 52-28”.

Add the following:

3.	Concrete Sidewalk, Exposed Aggregate

Bed Course Material 	Subsection 703-2.03

Joint Fillers	Subsection 705-2.01

Joint Sealer	Subsection 705-2.02

Reinforcing Steel	Subsection 709-2.01

Concrete, Class A	Section 501*

* With the following exceptions:

Subsection  501-3.01 under 4. Using Admixtures.  Add the following:  Do not use any curing agents and/or admixtures in concrete slabs which will deter or prevent the final finishing of concrete in any way.

Subsection 501-3.02 under 3. Aggregates. Delete the third paragraph.

# CONSTRUCTION REQUIREMENTS

608-3.04  CONCRETE SIDEWALKS. Add the following:  Place exposed aggregate concrete sidewalks in such a fashion that a uniform appearance and texture is maintained along the length of the sidewalk.  Remove and replace panels as directed by the Engineer if the Engineer determines there is a significant difference in texture or appearance between adjacent concrete panels.

Float and trowel all surfaces to receive the exposed aggregate finish.  Do not seed the surface with aggregate.  Expose surface aggregate using water fog spray and brooms to remove surface matrix after concrete has taken its initial set.  Expose coarse aggregate very lightly, approximately 2 mm, to match the approved sample.  The use of surface retarders may be permitted if application methods are accepted in writing by the Engineer.  Apply a weak acid wash to exposed aggregate surfaces after concrete has taken its final set.  Thoroughly neutralize and flushacid wash from finish surfaces.  Protect other adjacent construction and finishes from damage due to acid wash.

608-3.03 SIDEWALK RAMPS. Delete this Subsection and substitute the following:

608-3.03 CURB RAMPS. Construct curb ramps according to the details and locations shown on the Plans.

Follow the construction requirements of Subsection 608-3.01.  Give the surface a coarse broom finish.

608-4.01 METHOD OF MEASUREMENT. Delete the fourth item “Sidewalk Ramp” and substitute the following:

Curb Ramp. By each installation, complete in place, including construction of the ramp runs, flares, detectable warning tiles, backing curb and landing necessary to provide a single street-level access. (06/11/02)R256M98

Exposed Aggregate Sidewalk  By the square meter of finished surface.

### 608-5.01 BASIS OF PAYMENT. Add the following: Asphalt cement for Asphalt Sidewalk will not be paid for separately, but will be subsidiary to their respective pay items.

### Embankment and bed course materials will be furnished, placed and paid under Sections 203 and 301, respectively.

Backing curb, will be subsidiary to Item 608(6), Curb Ramp.

The detectable warning tiles are subsidiary to Item 608(6) and no separate payment shall be made.

Delete Item 608(6), Sidewalk Ramp.

All costs associated with replacing exposed aggregate concrete sidewalk panels as directed by the Engineer shall be subsidiary to Item 608(16) and no separate payment shall be made.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 608(6) Curb Ramp | Each |
| 608(16) Exposed Aggregate Sidewalk, 100 mm Thick | Square Meter |

SECTION 609

# CURBING

# Special Provisions

609-1.01  DESCRIPTION.  Add the following:  This work also consists of constructing a 0.5 m Landscape Wall as shown in the Plans.  The Landscape Wall also includes transition sections from the 0.5 m high wall down to the Flush Landscape Curb.

Type 4:  Flush Landscape Curb

Type 5:  100 mm High Landscape Curb

Type 6:  0.5 m High Landscape Wall

609-3.02 CAST-IN-PLACE CONCRETE CURBING. Add the following to the fifth paragraph: Concrete placed by the extrusion or slip-form process shall have a slump of less than 50 mm.

(2/1/00)R202M98

609-3.05 CURB RAMPS. Delete this Subsection in its entirety.

609-4.01 METHOD OF MEASUREMENT. Delete the second paragraph.

Add the following:

Curb, Type 4, Flush Landscape Curb will be measured by the meter along the centerline of the top of curb.

Curb, Type 5, 100 mm High Landscape Curb will be measured by the meter along the centerline of the top of curb.

Curb, Type 6, 0.5 m High Landscape Wall will be measured by the meter along the centerline of the top of wall.

609-5.01 BASIS OF PAYMENT. Delete Pay Item 609(3), Curb Ramp. (06/11/02)R256M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 609(1A) Curb, Type 4, Flush Landscape Curb | Meter |
| 609(1B) Curb, Type 5, 100 mm High Landscape Curb | Meter |
| 609(1C) Curb, Type 6, 0.5 m High Landscape Wall | Meter |

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Seward.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign.

(05/16/01)R50M98

SECTION 618

SEEDING

Special Provisions

618-1.01 DESCRIPTION. Add the following: This work shall consist of topsoil preparation, hydraulic application or hand broadcasting of the seed, finishing work including raking seed into the soil, fertilizing and limestone application in conformance with the Plans and Specifications.

Topsoil and seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible.

618-2.01 MATERIALS. Add the following to the list of material specifications:

### Schedule A	Subsection 724-2.02, Table 724-1

### Mulch	Subsection 727-2.01

618-3.01 SOIL PREPARATION. Add the following: Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes. Cover all slopes to be seeded with topsoil in accordance with Section 620. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope. Complete slope preparation as soon as topsoil is placed on the slopes. Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines.

Protect prepared base from damage and prevent erosion if seeding season limitations prohibit application of seed.

618-3.02 SEEDING SEASONS.  Add the following:  All seeding shall be performed between May 15 and August 15.  Submit request for extension of seeding season in writing and provide appropriate guarantee for remedy if seeding proves to be unsuccessful.

Seed germination shall occur in the same growing season as seeding.

618-3.03 APPLICATION. Add the following to Subsection 1. Hydraulic Method:

e.	Seed, mulch and fertilizer for seeding shall be applied adhering to the application rates shown in the following table.

Item	Application Rate (per ha)

Schedule A	Section 724 as modified

Mulch	1710 kg

Fertilizer (16-16-16)	586 kg

618-3.04 MAINTENANCE OF SEEDED AREAS.  Delete second paragraph and replace with the following: Water seeded areas as required for proper germination and growth.

Add the following:

Fertilizing.  Fertilizer shall be reapplied with water twice between May 31 and September 1 at a rate of one-half the initial application to all areas that received Schedule A as shown on Plans during the maintenance period.

- Watering during establishment.  Ensure that the seeded areas stay moist during germination and seedling establishment (as defined by the grass plants attaining a height of approximately 75mm).  Be prepared to water the seeded areas 3 times a day if weather conditions warrant it, until seedlings have become established.

- If you fail to apply adequate moisture during the germination period for 4 consecutive days, or after 2 notices without immediate response, the Engineer may declare all affected seeding unacceptable.  You will be required to reseed areas that have not been kept moist.

- Mowing. To control successional growth of voluntary species all seeded areas shall be mowed once at the end of the growing season after October 1st when plants are dormant.

Maintenance period. The maintenance period for seeded areas shall be one full growing season following their acceptance. One full growing season shall be defined as the period between May 1 and September 30 for the purpose of this Contract. Partial growing seasons will not be counted against the one full growing season requirement.

Repair any damage to seeded areas within their respective maintenance periods upon request by the Engineer.

- Add the following Subsection:

618-3.05 APPLICATION METHOD FOR SCHEDULE A.  Seeding shall be applied to areas indicated on the Plan.  Seeding shall be sown after the first frost or October 1st whichever is later using the dry method and shall not be watered or fertilized.

The seed shall be sown mixed with a topsoil carrier to aid in seed distribution.  The ratio shall be 1 part seed to 4 parts carrier.  The following application rate shall be used per hectare:

Item	Application Rate (per ha)

Seeding	 Section 724 as modified

Carrier	200 kg

618-4.01 METHOD OF MEASUREMENT. Delete full paragraph and substitute the following:  Seeding shall be measured by the Square Meter accepted in place.

The amount of mulch, fertilizer, limestone and water in this work, including any required reseeding, will not be measured.

The work described under subsection 618-3.01 Soil Preparation shall not be measured.

Water required for establishment of seed and maintenance will not be measured.

Maintenance of seeded areas will not be measured.

618-5.01 BASIS OF PAYMENT. Add the following:  Partial payments of up to 70% of full amount may be authorized for seeded areas at the time of acceptance.  The balance shall be paid at the completion of the maintenance period.

The amount of mulch, fertilizer, limestone and water in this work, including any required reseeding is subsidiary to Pay Item 618(5A) and separate payment shall be made.

The work described under subsection 618-3.01 Soil Preparation is subsidiary to Item 618(5A) and no separate payment shall be made.

Water required for establishment of seed and maintenance is subsidiary to Item 618(5A).

Maintenance of seeded areas is subsidiary to Item 618(5A).

- Payment will be made under:

| - Pay Item | - Pay Unit |
| --- | --- |
| - 618(5A) Seeding, Schedule A | - Square Meter |

SECTION 620

TOPSOIL

# Special Provisions

620-1.01 DESCRIPTION. Delete paragraph in its entirety and substitute the following:  This work consists of furnishing and placing topsoil for seed areas and in planting beds.  Work under this Section also consists of providing all operations pertaining to construction of the landscape berms at the locations shown on the Plans or as directed by the Engineer.

620-2.01 MATERIALS.  Add the following:  Planting areas shall be constructed of required topsoil depth and unclassified excavation conforming to Section 203-2.03.  Topsoil placed for seed areas and in planting beds shall conform to Section 726.

620-3.01 PLACING.  Delete this Subsection in its entirety and substitute the following: Spread topsoil evenly to a minimum depth of 100 mm after settlement on all areas to be seeded, as described in Section 618.

Topsoil shall be a minimum depth of 500 mm after settlement on all areas to be established as planting beds for trees or shrubs as shown on the Plans or as directed by the Engineer.

Do not place topsoil in heavy rainfall, snowfall, when the soil is frozen or during other conditions detrimental to the work.  Keep all roadway surfaces clean of topsoil during hauling and spreading operations.

620-4.01 METHOD OF MEASUREMENT. Add the following:  Limestone, if required, will not be measured.

Topsoil placed in concrete planters within the plaza shall not be measured.

620-5.01 BASIS OF PAYMENT. Add the following:  Limestone, if required is subsidiary to Items 620(1A) and 620(1B) and no separate payment will be made.

- Topsoil placed in concrete planters within the plaza shall be subsidiary to Item 622(16) and no separate payment shall be made.

- Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 620(1A) Topsoil (500 mm Depth) | Square Meter |
| 620(1B) Topsoil (100 mm Depth) | Square Meter |

SECTION 621

## PLANTING TREES AND SHRUBS

- Special Provisions

621-1.01 DESCRIPTION.  Delete this Subsection in its entirety and substitute the following: This work shall consist of collecting, furnishing, planting and maintaining trees, shrubs and other plants as shown and scheduled on the Plans.  This work also includes preparation of planting bed areas including furnishing and installing shredded bark mulch and landscape fabric.

621-2.01 PLANT STOCK.  Delete this Subsection in its entirety and substitute the following:  All plants shall be locally grown and shall be true to type and name in accordance with the current edition of Standardized Plant Names, American Joint Committee on Horticultural Nomenclature, except that plant species which are scheduled, but not included in the current edition of Standardized Plant Names, shall be certified by a botanist.  Each bundle, flat, or plant if not bundled, shall be labeled with the scientific name.

Variety and species shall be as scheduled on the Plans.  All trees and shrubs shall be typical of the species or variety and shall, unless otherwise specified, conform to the American Standard for Nursery Stock (ANSI-Z 60.1-1996) of the American Association of Nurserymen (AAN) for type and grade.  Plant stock having severely damaged bark or trunks, broken leaders or main branches, severed main roots, or evidence of disease or injurious insects will be rejected.  Bare root trees and shrubs will also be rejected.

1.	Nursery Stock.

a.  	Trees and shrubs furnished from a nursery shall have a fibrous compact root system suitable for the various species and sizes called for on the Plans.

- Container-grown plants shall be healthy, vigorous, well rooted and established in the container in which they are furnished.  Root mass shall retain its shape and hold together when removed from the container without being root-bound.

2.	Collected Stock.  These materials shall be plants growing under natural conditions in soils and in locations which lend themselves to proper collecting practices.  Obtain any permits required for collection of plant stock from natural areas.  The root system of collected stock shall be at least one-third larger than those specified for nursery grown material.

3.	Balled and Burlapped Plants.

a.	The diameter and depths of balls on balled and burlapped Trees and Shrubs shall be in accordance with ANSI-Z60.1-1996.

- All balled and burlapped Trees and Shrubs shall be furnished with a firm ball of earth from the original and undisturbed soil in which the plant was growing.  The ball shall be wrapped with burlap or similar approved material and tightly laced to hold the ball firm and intact.  Any balled and burlapped designated plant material arriving at the planting site with broken or loose balls or of manufactured earth will be rejected.

- All plants found to be rootbound by the determination of the Engineer will be rejected.

- Substitutions.  No substitutions of plant stock will be permitted without written approval of the Engineer.  Request for substitutions for Trees and Shrubs shall be submitted in writing six (6) months prior to installation.

5.	Storage and Packing.  All plant material shall be handled and packed in accordance with good nursery practices as required by soil and climatic conditions.  Plants that show signs of improper storage or handling will be rejected.

6.	Inspection.

a.	All planting stock shall be available for inspection in a dedicated project nursery or planting stock shall be flagged at the collection field before it is dug.  Furnish complete and detailed information concerning the source of supply for all plant materials not less than 10 days in advance of digging operations.

- Final inspection and acceptance for size of ball or roots, color, absence of defects, and for other requirements will be made at the planting site by the Engineer prior to placing the plants in their permanent positions.

Plant material installed prior to acceptance by the Engineer will be removed, inspected and reinstalled if found acceptable.  If found to be unacceptable, furnish, allow inspection and then install the new material.

621-2.02 FERTILIZER.  Add the following: Deliver fertilizer in moisture-proof containers marked with weight and manufacturer’s guaranteed analysis showing proportions of the chemical ingredients of nitrogen, phosphoric acid, and potassium within a tolerance of +/- 2 percent. A slow release fertilizer 8-32-16 (N-P-K) shall be used with all trees and shrubs early in the first full growing season following installation.  Apply fertilizer for topsoil installation at the rate described in Section 726 or as

directed by the Engineer.  Place the fertilizer near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered immediately after application.

621-2.03 LIMESTONE. Add the following: Apply limestone at the rate described in Subsection 726, in Table 726-1 or as determined by the Engineer.

621-2.04 MULCH.  Replace this Subsection with the following: Mulch shall be shredded bark mulch.  It shall consist of shredded bark and wood.  The maximum length of any individual component shall be 50  mm and a minimum of 75% of the mulch shall pass through a 25 mm sieve.  The mulch shall be free of growth or germination-inhibiting ingredients.  The bark mulch shall have the characteristics of retaining moisture, forming a mat not susceptible to spreading by wind or rain, and providing a good growth medium for plants.  Shredded bark may contain up to 50% shredded wood material.  Wood chips are not acceptable.  Bark mulch containing shredded wood shall be aged for one-year minimum prior to installation.  The mulch shall not contain resin, tannin, or other compounds in quantities that are detrimental to plant life.  Mulch shall be spread evenly in all planting beds as shown on Plans.

621-2.06 STAKES.  Add the following:  Stakes shall be installed as shown on Plans.

Delete Subsection 621-2.07 and replace with the following:

621-2.07 LANDSCAPE FABRIC.  Use landscape fabric that conforms to Section 727.2.02 Matting.

CONSTRUCTION REQUREMENTS

621-3.02 ADVANCE PREPARATION AND CLEANUP. Add the following:  Lay out areas which receive group plantings as shown on Plans.  Mark these areas individually with flags, or other approved methods to delineate planting areas.  The Engineer shall approve the shape, size, location and general layout of planting areas before the work may proceed.

Stake or mark with other approved methods the location of individual trees within each planting area for approval by the Engineer.

621-3.03 PLANTING.  Delete Items 1 and 2 and substitute the following:

1.	Plant Season.

  - Locally grown:  When native species of locally grown trees and shrubs are furnished for the project, they shall be planted between June 1 and September 15.  Trees and shrubs shall be fully leafed-out prior to planting.

  - Imported and Nursery grown:  When plants are shipped in from out of state, or have been container grown in a nursery for at least one year, handling shall be in accordance with nursery recommendations.  Plants imported from out of state shall be planted between May 15 and September 1.

2.	Excavation.

a.	Keep topsoil separate from subsoil and rendered loose and friable.  Separate and dispose of any material detrimental to plant growth at approved locations.

b.	Dig planting holes within the planting bed.  Firmly tamp the base of the planting hole to assure plants will no settle to lower than their proper planting depth.

Delete paragraphs (c.) and (d.)

- Pruning.  Delete the last two sentences of paragraph b in their entirety.

5.	Placing Plants.  Add the following to paragraph a.:  Plant trees and shrubs as shown on the Plans and as directed by the Engineer.

Delete paragraph b and substitute the following: Handle balled and burlapped plants, plants in wire baskets or containers by the earth ball, container, or basket and not by the plant itself.  Clip and lay wire baskets and burlap flat on the bottom of the planting pit as indicated on the Plans.  Removed containers from the site.  The Engineer may reject any plants whose rootballs collapse during planting

7.	Wrapping.  Delete this paragraph in its entirety.

- Staking and Guying.  Delete paragraphs a, b, and c in their entirety and add the following:  Stake trees as shown on Plans and as directed by the Engineer.  Maintain the stakes and wire during construction and the establishment period to prevent damage to the trees.  Remove all stakes and wire at the end of the period of establishment.

Add the following item:

9.	Certified Arborist.  R> RRRrrrrrrrrrrrrrrrooetain the services of an > arborist certified by the International Society of Arboriculture or the > American Association of Nurserymen whose experience and qualifications > are acceptable to the Engineer.  Submit the arborist’s resume > at least 10 calendar days before the delivery of plant material.  The > certified arborist shall oversee quality assurance of trees, their > installation and shall inspect trees for health and vigor.

Specifically, > the arborist shall inspect plants for health and vigor prior to installation, to assure the requirements of Section 621-2.01 for plant stock, including that the materials are disease free, free of wounds, broken branches, double leaders, co-dominant trunks, or other defects.  Plants that do not meet the standards will be rejected prior to installation.  The certified arborist shall also be responsible for the following:

  - Inspect the tree planting process to assure that planting techniques meet the specifications of the Contract documents and match standard industry practices.

  - Provide the Engineer, through the Contractor, written certification that all materials meet the requirements of this Section prior to acceptance.

  - Inspect the plantings after installation is complete to assure that they are ready to be accepted by the Engineer and ready for the maintenance schedule to begin.

  - Inspect plantings twice during the growing season during Plant Establishment Period for any needed maintenance, such as watering, pruning, or removal of dead, dying, or untreatable diseased trees.>

  - After acceptance, inspect the trees at least twice > during the growing season each year of the Plant Establishment period > for any needed maintenance, such as watering, pruning, removal of dead, > dying or untreatable diseased trees.

621-3.04 PERIOD OF ESTABLISHMENT.  Delete the last sentence and substitute the following: The period of establishment for trees and shrubs shall extend to September 15 of the year following planting. The plant establishment period applies to all planting beds, trees and shrubs.

621-3.05 CLEANUP.  Add the following: Planted trees, shrubs, and seeded areas shall be kept clean of litter and garbage during the growing season.

621-3.06 PLANT REPLACEMENTS.  Delete the last sentence and substitute the following:  Replace plants following the same details and specifications used in the original Plans.  Replace plants which are dead or dying immediately during the months of June through September.  Replace plants dead at the end of the growing season at the beginning of the following season.

621-3.07 MAINTENANCE.  Delete the paragraph and substitute with the following:  Maintenance includes the care of all trees and shrubs during the period of establishment, including the non-growing season.  Specific work includes watering, pruning, weeding, pest control, and protection of planted areas.  At the beginning and end of each growing season, the Engineer and Contractor shall undertake a joint inspection to review conditions and document any changes in maintenance or acceptance of plantings.

1.   	Watering. Water all trees and shrubs using the quick coupler system to maintain the plants in a healthy, vigorous growing condition.  Keep the root zone of plants moist at all times.

2.	Disease Control. Apply pesticides, insecticides, or other disease-control methods as necessary to maintain plant health.  Obtain permission of the Engineer and appropriate permits for the application of insecticides from the Alaska Department of Environmental Conservation prior to the application of any regulated products.

3.	Pruning. Prune all plant materials, with appropriate pruning techniques, to remove dead or dying wood and to improve the shape and or vigor of the plants.  Cuts shall not be painted. Schedule pruning of flowering plants to occur immediately after flowers drop off or decay.  Prune damaged plants or those that constitute health or safety hazards as directed by the Engineer at any time of the year.  Do not prune Evergreens without the approval of the Engineer.

4.	Fertilizing.  Apply fertilizer to Trees and Shrubs in accordance with Section 621-2.02 Fertilizer between May 15 and June 15 of each growing season following planting.  Place the fertilizer tablets near the root zone in accordance with the fertilizer manufacturer’s instructions.  Fertilizer shall be well-watered in immediately after application.  Notify the Engineer in writing 4 working days prior to applying any fertilizers.  Written notice shall state the time and location of fertilizer application.

TABLE 621-1

MAINTENANCE FERTILIZER SCHEDULE

Plant Type	Fertilizer	Application Rate

Coniferous Trees	8-32-16	34.2 grams per square meter

Shrubs and Ground Cover	8-32-16	7 grams per square meter.

621-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following: Trees and Shrubs shall be measured by the actual number planted and maintained in accordance with the Plans and Specifications, and as accepted by the Engineer.  Furnishing and installing shredded bark mulch, landscape fabric, additional topsoil backfill mix, staking and guying, arborist review, fertilizing, disposal of unsuitable and surplus material, water used for establishment and maintenance, and all work required during the one full growing season period of establishment shall not be paid for separately, but shall be subsidiary to the individual pay items.

621-5.01 BASIS OF PAYMENT.  Delete second sentence and add the following:   Partial payments of up to 70% of full amount may be authorized for Trees and Shrubs at the time of acceptance. The balance shall be paid at the completion of the period of establishment.

The accepted quantities will be paid for at the contract price, per unit of measurement, for all labor material and equipment required to furnish and install the pay items listed below and appearing in the bid schedule.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 621(1A) Tree (Picea sitchensis - 3 m Ht.) | Each |
| 621(2A) Shrub (Rosa rugosa ‘Hansa’ - 0.75 m Ht.) | Each |
| 621(2B) Shrub (Cornus sericea - 0.6 m Ht.) | Each |

SECTION 622

REST AREA FACILITIES

Special Provisions

622-1.01 DESCRIPTION. Delete this Subsection in its entirety and substitute the following: The work under this Section includes all labor, materials, transportation, testing, maintenance, and service necessary to furnish and install concrete pavers and planters as shown on the Plans and specified herein.

Add the following Subsection:

    - SAMPLES

Provide paver samples.  Provide one sample for each color.

Provide catalog cuts of proposed planter if from manufacturer.  Provide shop drawings of planter if manufactured by you.

MATERIALS

Add the following Subsections:

622-2.13 CONCRETE PAVERS.

Use 101.6 mm x 60 mm x 203 mm red, tan, gray, and black concrete brick pavers meeting the requirements of Section 704.

Construct setting beds and sweep sand grout in between pavers that meet the requirements of Section 703, modified table 703-8.

622-2.14 CONCRETE PLANTERS.  Construct round concrete planters approximately 1.5 meters wide by 0.5 meters deep by 75 mm thick walls.   Provide enough space at the bottom in order to facilitate picking the planters up by fork lift.  Construct the edges with a 10 mm to 20 mm radius.  Use a smooth sacked or smooth form finish.  Ensure that no fins or pockets are evident on areas of the planter not covered by topsoil.  Inset the planters approximately 100mm x 100mm at bottom.  Provide four 25 mm drainage holes, equally spaced, at the bottom of each planter.  The planters are to be manufactured in a shop setting.  All planters are to be identical.

Provide porous backfill material meeting the requirements of Table 703-7 in the bottom of the planters after placing them at the locations shown in the Plans.  Cover the porous backfill completely with separation geotextile fabric meeting the requirements of Subsection 729-2.01.  Use topsoil meeting the requirements of Section 620 for the remainder of the backfill.  Fill to within 50 mm of the planter top.

CONSTRUCTION REQUIREMENTS

Add the following Subsection:

622-3.08 PAVER PLAZA.  Provide a level surface that meets the grades shown in the Plans for placement of setting bed and pavers.  Compact the subgrade to 95% relative density. Provide a sand setting bed and compact with a plate compactor to the lines and grades shown on the Plans.  Construct straight paver courses using a radial pattern, or as shown on the Plans.

Cut pavers as required to provide the pattern shown on the Plans.  All cuts shall be clean.  Pavers with chips larger than 10 mm x 10 mm are unacceptable.  With prior approval by the Engineer, you may use chipped pavers provided they are placed so the chipped surface is not visible.

During the setting process, ensure that all slopes are even and meet the lines and grades shown on the Plans. Remove any unlevel paver sections and reinstall in accordance with the Specifications and Plans or as directed by the Engineer.  Sweep sand into all joints, filling all voids between pavers after final placement.

Manufacture all planters in a shop setting.  Planters manufactured on-site shall not be allowed.

622-4.01 METHOD OF MEASUREMENT.  Add the following:  Item 622(15), Concrete Pavers shall be measured by the square meter installed and accepted in place. All other work associated with constructing the Paver Plaza including excavation, grading, backfilling, compacting, sand setting bed and disposal of useable material shall not be measured for payment.

Concrete Planters shall be measured by the number of planters completed and accepted.

622-5.01 BASIS OF PAYMENT.  Add the following:  Excavation, grading, backfilling, compacting, sand setting bed and disposal of useable material are subsidiary to Item 622(15), Concrete Pavers and no separate payment shall be made.

Payment for Item 622(16) shall be paid at the contract unit price for the number of units completed and accepted.  Payment includes full compensation for all labor and materials required, including porous backfill, separation geotextile fabric and topsoil.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 622(15) Concrete Pavers | Square meter |
| 622(16) Concrete Planter | Each |

SECTION 627

WATER SYSTEM

Special Provisions

CONSTRUCTION REQUIREMENTS

627-3.01 GENERAL.  Add the following before the first sentence:  Contact the City of Seward to coordinate a pre inspection of the water facilities before pavement removal begins and a post inspection after paving operations are complete.

627-4.01 METHOD OF MEASUREMENT. Add the following

6.	Pre-paving and Post-paving Inspections.  Will not be measured.

627-5.01 BASIS OF PAYMENT.  Add the following:  All fees associated with pre and post paving inspections, as specified in Subsection 627-3.01, are subsidiary to Item 401(1A), Asphalt Concrete Pavement, Type II; Class A and no separate payment shall be made.

# SECTION 635

INSULATION BOARD

Special Provisions

635-4.01 METHOD OF MEASUREMENT. Delete this Subsection in its entirety and substitute the following:  By the square meter of insulation board in its final position, including transitions, regardless of thickness, complete and accepted.

Sand blanket material is subsidiary.

635-5.01 BASIS OF PAYMENT. Payment will be made under:

(8/23/00)R57M98

| Pay Item | Pay Unit |
| --- | --- |
| 635(2) Insulation Board | Square Meter |

Delete this Section in its entirety and substitute the following:

SECTION 639

DRIVEWAYS

# Special Provisions

639-1.01 DESCRIPTION. Construct approaches, residential or commercial driveways at the locations shown in the Plans.

639-2.01 MATERIALS. Use materials that conform to the standards for the main roadway.

639-3.01 CONSTRUCTION. Construct driveways and approaches to the dimensions shown on the Plans.

639-4.01 METHOD OF MEASUREMENT. By the number of driveways and approaches constructed as shown on the Plans or as directed. Pavement removal and excavation required beyond the limits of the adjacent mainline will be subsidiary.

639-5.01 BASIS OF PAYMENT.  At the contract unit price shown in the bid schedule. The contract unit price for driveways and approaches shall be full compensation for furnishing all equipment and labor necessary to complete the work as specified.

Materials required to construct driveways and approaches will be paid for separately under the respective items listed in the bid schedule.

Native material meeting the minimum requirements of Selected Material, Type C will not be paid for directly, but will be considered subsidiary to 639 items. (05/09/02)R58M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 639(6) Approach | Each |

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modifications

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Standard Modifications

Delete Section 641 in its entirety and substitute the following:

SECTION 641

EROSION, SEDIMENT, AND POLLUTION CONTROL

641-1.01 DESCRIPTION. This work consists of planning, providing, inspecting and maintaining control of erosion, sedimentation, water pollution and hazardous materials contamination.

641-1.02 DEFINITIONS.

- BMP (Best Management Practices). A wide range of project management practices, schedules, activities, or prohibition of practices, that when used alone or in combination, prevent or reduce erosion, sedimentation, and/or pollution of adjacent water bodies and wetlands. BMP include temporary or permanent structural and non-structural devices and practices. The Department describes common BMP in its Alaska Storm Water Pollution Prevention Plan Guide.

- ESCP (Erosion and Sediment Control Plan). The general plan for control of project-related erosion and sedimentation. The ESCP normally consists of a general narrative and a map or site plan. It is developed by the Department and included in the project plans and specifications. It serves as a resource for bid estimation and a framework from which the Contractor develops the project SWPPP.

- Final Stabilization. A point in time when all ground-disturbing activities are complete and permanent erosion and sediment controls are established and functional. The stabilized site is protected from erosive forces of raindrop impact and water flow. Typically, all unpaved areas except graveled shoulders, crushed aggregate base course, or other areas not covered by permanent structures are protected by either a uniform blanket of perennial vegetation (at least 70% cover density) or equivalent permanent stabilization measures such as riprap, gabions or geotextiles.

- HMCP (Hazardous Material Control Plan). The Contractor's detailed plan for prevention of pollution that stems from the use, containment, cleanup, and disposal of hazardous material, including petroleum products generated by construction activities and equipment.

- NOI. Notice of Intent to commence ground-disturbing activities under the NPDES General Permit.

- NOT. Notice of Termination of coverage under the NPDES General Permit.

- NPDES General Permit. The General Permit for Stormwater Discharges from Construction Activities, issued by the Environmental Protection Agency (EPA) under the National Pollutant Discharge Elimination System (NPDES). It requires a SWPPP prior to ground-disturbing activities for the project.

- SWPPP (Storm Water Pollution Prevention Plan). The Contractor’s plan for erosion and sediment control and storm water management under the NPDES General Permit. The SWPPP is developed by the Contractor and describes site-specific controls and management of issues identified for the project. The approved SWPPP replaces the ESCP.

641-1.03 SUBMITTALS. Submit 3 copies each of your SWPPP and HMCP for approval no less than 5 calendar days prior to the preconstruction conference.

The Department will review the above submittals within 14 calendar days. Submittals that do not meet Department approval will be returned to you for modification.

The approved SWPPP must be signed by you and the Engineer in accordance with the NPDES General Permit.

Submit your signed NOI (use EPA Form 3510-9) to the Engineer no later than 10 working days before you intend to commence ground-disturbing activities.

The approved SWPPP and HMCP become the basis of the work required for the project erosion, sediment and pollution control.

641-2.01 STORM WATER POLLUTION PREVENTION PLAN (SWPPP) REQUIREMENTS. Use the Department's ESCP to develop a SWPPP based on your scheduling, equipment, and use of alternative BMP. Follow the format presented in the Alaska Storm Water Pollution Prevention Plan Guide, for projects disturbing over 2 hectares. The plan must consider first preventing erosion, then minimizing erosion, and finally trapping sediment before it enters waterways.

The plan must address your site-specific controls and management plan for the construction site as well as for all material sites, waste disposal sites, haul roads, and other affected areas, public or private. The plan must also incorporate all the requirements of the Project permits.

Have the SWPPP prepared under the direction of and sealed by a professional engineer currently registered in the State of Alaska. Include all requirements of the NPDES General Permit.

641-2.02 HAZARDOUS MATERIAL CONTROL PLAN (HMCP) REQUIREMENTS. Prepare a HMCP for the handling, storage, cleanup, and disposal of petroleum products and other hazardous substances. (See 40 CFR 117 and 302 for listing of hazardous materials.)

List and give the location of all hazardous materials, including office materials, to be used and/or stored on site, and their estimated quantities. Detail your plan for storing these materials as well as disposing of waste petroleum products and other hazardous materials generated by the project.

Identify the locations where fueling and maintenance activities will take place, describe the maintenance activities, and list all controls to prevent the accidental spillage of petroleum products and other hazardous materials.

Detail your procedures for containment and cleanup of hazardous substances, including a list of the types and quantities of equipment and materials available on site to be used.

Detail your plan for the prevention, containment, cleanup and disposal of soil and water contaminated by accidental spills. Detail your plan for dealing with unexpected contaminated soil and water encountered during construction.

Specify the line of authority and designate your field representative for spill response and one representative for each subcontractor.

641-3.01 CONSTRUCTION REQUIREMENTS.

Do not begin ground-disturbing work until you are notified by the Engineer that 48 hours have passed since the NOIs were mailed to the EPA and DEC.

Post at the construction site, the

1.	NPDES Permit number, if available, and a copy of the NOI,

2.	name and phone number of your local contact person, and

3.	location of a SWPPP available for viewing by the public.

Comply with all requirements of the NPDES General Permit, implement all temporary and permanent erosion and sediment control measures identified in the SWPPP, and ensure that the SWPPP remains current.

Maintain all temporary and permanent erosion and sediment control measures in effective operating condition.

Comply with all requirements of the approved HMCP and all state and federal regulations which pertain to the handling, storage, cleanup, and disposal of petroleum products or other hazardous substances. Contain, clean up, and dispose of all discharges of petroleum products and/or other materials hazardous to the land, air, water, and organic life forms. Perform all fueling operations in a safe and environmentally responsible manner. Comply with the requirements of 18 AAC 75 and AS 46, Oil and Hazardous Substances Pollution Control.

Perform inspections and prepare inspection reports in compliance with the project SWPPP and the NPDES General Permit.

1.	Joint Inspections. Prior to start of construction conduct a joint on-site inspection with the Engineer and the professional engineer who stamped the SWPPP to discuss the implementation of the SWPPP.

Conduct the following additional joint on-site inspections with the Engineer:

a.	During construction, inspect the following at least once every 7 calendar days and within 24 hours of the end of a storm event exceeding 13 mm in 24 hours (as recorded at or near the project site).

(1)	Disturbed areas that have not been finally stabilized.

(2)	Areas used for storage of erodible materials that are exposed to precipitation.

(3)	Sediment and erosion control measures.

(4)	Locations where vehicles enter or exit the site.

b.	Prior to winter shutdown, to ensure that the site has been adequately stabilized and devices are functional.

c.	At project completion, to ensure final stabilization of the project.

2.	Winter Inspections. During winter shutdown, conduct inspections at least once every month and within 24 hours of a storm resulting in rainfall of 13 mm or greater. Monthly inspection requirements may be waived by the Engineer until one month before thawing conditions are expected to result in a discharge, if all of the following requirements are met:

a.	Below-freezing conditions are anticipated to continue for more than one month.

b.	Land disturbance activities have been suspended.

c.	The beginning and ending dates of the waiver period are documented in the SWPPP.

3.	Inspection Reports. Prepare and submit, within 3 calendar days of each inspection, a report with the following information:

a.	A summary of the scope of the inspection.

b.	Name(s) of personnel making the inspection.

c.	The date of the inspection.

d.	Observations relating to the implementation of the SWPPP.

e.	Any actions taken as the result of the inspection.

f.	Incidents of non-compliance.

Where a report does not identify any incidents of non-compliance, include certification that the facility is in compliance with the SWPPP and NPDES General Permit. Sign the report in accordance with Part VI. Standard Permit Conditions of the NPDES General Permit. All certifications shall be included as an appendix to the SWPPP.

Retain copies of the SWPPP, and all other records required by the NPDES General Permit, for at least 3 years from the date of final stabilization.

If unanticipated or emergency conditions threaten water quality, take immediate suitable action to preclude erosion and pollution.

Submit amendments to the SWPPP, to correct problems identified as a result of any

1.	storm event or other circumstance that threatens water quality, and

2.	inspection which identifies existing or potential problems.

Submit SWPPP amendments to the Engineer, within 7 calendar days following the storm event or inspection. Detail additional emergency measures required and taken, to include additional or modified measures. If modifications to existing measures are necessary, complete implementation within 7 days.

Stabilize all areas disturbed after the seeding deadline within 7 calendar days of the temporary or permanent cessation of ground-disturbing activities.

Submit a signed NOT (use EPA Form 3510-7) to the Engineer

1.	when the project site (including all material sources, disposal sites, etc.) has been finally stabilized and all storm water discharges from construction activities authorized by this permit have ceased, or

2.	when the construction activity Operator (as defined in the NPDES General Permit) has changed.

If you fail to coordinate temporary or permanent stabilization measures with the earthwork operations in a manner to effectively control erosion and prevent water pollution, the Engineer may suspend your earthwork operations and withhold monies due on current estimates for such earthwork items until all aspects of the work are coordinated in a satisfactory manner.

If you fail to:

- pursue work required by the approved SWPPP,

- respond to inspection recommendations and/or deficiencies in the SWPPP, or

- implement erosion and sedimentation controls identified by the Engineer,

the Engineer may, after giving you written notice, proceed to perform such work and deduct the cost thereof, including project engineering costs, from your progress payments.

641-4.01 METHOD OF MEASUREMENT. Item 641(1) will not be measured for payment.

Item 641(2) will be measured as specified in the Contract or Directive authorizing the work.

641-5.01 BASIS OF PAYMENT.

1.	Item 641(1) Erosion and Pollution Control Administration. At the contract lump sum price for administration of all work under this section. Includes, but is not limited to, plan preparation, plan amendments and updates, inspections, monitoring, reporting and record keeping.

2.	Item 641(2) Temporary Erosion and Pollution Control. At the prices specified in the Contract to install and maintain all temporary erosion, sedimentation, and pollution control measures.

Temporary erosion and pollution control measures that are required at Contractor-furnished sites are subsidiary.

Perform temporary erosion and pollution control measures that are required due to your negligence, carelessness, or failure to install permanent controls as a part of the work as scheduled or ordered by the Engineer, or for your convenience, at your own expense.

Permanent erosion and pollution control measures will be measured and paid for under other contract items, when shown on the bid schedule. (08/15/01)M78

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 641(1) Erosion and Pollution Control Administration | Lump Sum |
| 641(2) Temporary Erosion and Pollution Control | Contingent Sum |

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Standard Modifications

642-3.01 GENERAL.  Delete the seventh paragraph.

(06/25/99)M 79

#### Special Provisions

Add the following:  Perform cross-sections on 10 meter intervals for the full length of the project.  Cross-sections shall extend from the right-of-way to right-of-way, or to the use permit line, whichever is farthest.  Elevations for centerline, lip of gutter, gutter flow line, top face of curb, top back of curb and back of sidewalk on both sides of the roadway will be included in the cross-sections.  The cross-section information will be provided to the Engineer 14 calendar days prior to pavement, curb and gutter and sidewalk removal operations.  Such adjustments as may be required to the planned roadway grades shall be made by the Engineer and shall not be considered extra work.

Where the Plans call for the Contractor to reference existing curb and gutter, sidewalk and match existing, reference the existing line, grade, and elevations of the curb and gutter, at 2.5 meter intervals, before removal.  Stake the new curb and gutter or sidewalk to original line, grade, and elevation.

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work. (3/31/00)R252M98

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations. (01/29/02)R222M98

## Standard Modifications

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Pedestrian Fence, Type I. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Pedestrian Fence, Type II . Provide connectable, self-supporting chain link wire fence panel approximately 1.8 m high, bordered by a metal tube frame.  Do not use barbed wire on the top of the fence.  Clamp the fence together at the top and provide weights at the base by a method approved by the Engineer and capable of withstanding 50 km/hr wind velocities. Submit the type of weighted base to be used to the Engineer for approval prior to use.  Install OM-3(R or L) object markers at all outside corners that face vehicle traffic.

15.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with no irregularities. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 50 km/h wind velocities to hold temporary surfacing in place.

e.	Cover the entire walking surface with 90 pound mineral surfaced roll roofing material to provide a non-slip surface.

16.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

17.	Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. (9/29/00)M 91

## Special Provisions

Add the following:

18.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

## Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (9/29/00) M91

Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (01/29/02)R222M98

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES. Add the following to 1. Embankments.: Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.: At the end of each continuous work shift remove all obstructions greater than 100 mm above the nominal foreslope grading.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a power broom that can eject them to the shoulder of the road.

Change items 7 and 8 to 8 and 9 respectively.

Add the following:

10.	ET-2000 LET.  The price listed in the Traffic Control Rate Schedule will be full compensation for the purchase, installation, maintenance during construction, removal and salvaging the ET-2000 LET unit(s).  Deliver the salvaged unit(s) to the nearest DOT&PF Maintenance and Operations’ district office, or as directed by the Engineer.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

# ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Add the following:  Coordinate lane closures or restrictions on Port Avenue with Jim Beckham, Harbormaster at 244-3138.  This coordination is required for the Harbormaster’s mobilization of boats on Port Avenue during construction.

Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	Friday from 1500 hours to Sunday 2200 hours

2.	Monday through Friday from 0600 hours to 0800 hours.

3.	Monday through Thursday from 1600 hours to 1800 hours.

4.	During the Seward Silver Salmon Derby, August 10 through August 18.

5.	Around any holiday:

a.	If a holiday falls on Sunday, Monday or Tuesday, the above stipulations apply from 1200 on the Friday before the holiday to 0300 on the day after the holiday.

b.	If a holiday falls on Wednesday, the above stipulations apply from 1200 on the Tuesday before the holiday to 0300 on the Thursday after the holiday.

c.	If a holiday falls on Thursday, Friday or Saturday, the above stipulations apply from 1200 on the day before the holiday to 0300 on the Monday after the holiday.

Lane restrictions, if allowed, shall be conducted so that no more than a 5 minute stopped delay is encountered by waiting motorists through the entire length of the project, except during paving operations when a 10 minute stopped delay will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

Obtain the local school bus schedule and coordinate work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  Make every effort not to delay school buses through the construction work zone.

# Obtain the cruise ship docking schedule and coordinate work efforts to ensure tour buses are not delayed through the construction zone.  Submit a Traffic Control Plan outlining this plan for approval by the Engineer.

# Port Avenue Work

# Provide and maintain safe routes for pedestrians and bicyclists on existing pavement or a hard surface through the work zone on Port Avenue.  Maintain a minimum width of 2.2 meters and keep this route separated from the work zone by Pedestrian Fence, Type I.  Submit a Traffic Control Plan outlining these measures for the Engineer’s approval.

# Fourth Avenue Work Segments.

# Fourth Avenue work has been separated into 3 work segments as shown in the plans.  Maintain traffic on a paved surface at all times on Fourth Avenue, with the exception of locations where storm drain work occurs and during the pulverizing of existing pavement and placement of new pavement.

Pulverize the existing pavement and place the new pavement on Fourth Avenue within 10 consecutive days.

# Sidewalk Entrance Criteria.  Maintain access to businesses at all times, except during sidewalk demolition and replacement.  Contact the effected business owners 14 days prior to beginning work in front of their business.  Coordinate business access closures with the owners 3 days prior to performing any demolition or reconstruction activities.  Demolish and remove sidewalk in front of business entrances in one work shift.  Replace sidewalk in front of business entrances in one work shift.

Complete the work described below within the individual work segments within the duration stated for each segment.  Notify the Engineer in writing as to when they are beginning work on the individual segments.

Segment 1.

Do not begin work on Segment 1 until August 19, 2002, once the Seward Silver Salmon Derby is completed.  Complete all storm drain, curb & gutter, sidewalk, sign foundation, lighting conduit, conductor, junction box and foundation work for Segment 1 in four (4) consecutive weeks.

Segment 2.

Do not begin work on Segment 2 until September 3, 2002. Complete all storm drain, curb & gutter, sidewalk, sign foundation, lighting conduit, conductor, junction box and foundation work for Segment 2 in three (3) consecutive weeks.

Segment 3.

Do not begin work on Segment 3 until August 19, 2002, once the Seward Silver Salmon Derby is completed.  Complete all storm drain, curb & gutter, sidewalk, sign foundation, lighting conduit, conductor, junction box and foundation work for Segment 3 in four (4) consecutive weeks.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following: Apply final pavement markings according to Subsection 670-3.01 CONSTRUCTION REQUIREMENTS of these Special Provisions.

Add the following Subsection:

643-3.10 PUBLIC INFORMATIONAL PROGRAM. Provide a Public Information (PI) professional to accomplish the work outlined in this Subsection. The PI person shall have a minimum of five (5) years demonstrated professional experience in performing similar informational campaigns involving multi-media, ie: television, radio, newspaper and public presentations. S/he shall be responsible for all aspects of this service including coordination; public interaction; preparing graphics; developing mailing lists; supplying updated information; and all labor, equipment, postage, and materials to provide this service. Logos, reports, software, visual aids, graphics and work products developed for this Project shall become the property of the Department, and delivered to the Engineer at the end of the work.

The PI professional's office shall be equipped with a facsimile machine.

This professional shall be responsible for following tasks for the PI Program:

- Mail-outs. Design and distribute three informational mail-outs/flyers each construction season, which will be approved by the Engineer. The mail-outs shall contain most or all of the following:

a.	a brief description and map of the Project,

b.	the Contractor's anticipated construction schedule,

c.	a narrative of the possible delays to the traveling public through the Project,

d.	detailed traffic information such as intersection, lane and/or sidewalk closures, their corresponding detours, and their effective dates,

e.	locations of temporary bus stops,

d.	a description of possible impacts to abutting property accessing the Project,

f.	a listing of locations where current Project information may be obtained,

g.	date and times of Open House meeting as required by the Engineer,

h.	the Contractor's 24-hour message number and office telephone number, and

i.	the Engineer's Project office telephone number, e-mail address, and the web site address containing Project updates, schedules and general narrative information.

The last mail-out shall also contain a questionnaire to aid in preparing the final Report required under Item 5 below.

The mail-outs shall be sent to all addresses within one city block on either side of the Project corridor, and shall be addressed to both the owner of record and the current tenant. It shall be distributed at the following times:

a.	two weeks before construction begins,

b.	at the approximate one-third point of construction season, and

c.	at the approximate two-thirds point of construction season.

2.	Weekly Notices. Write and submit weekly Public Information Notices that identify road closures, restrictions to traffic, and detours. Areas of potential traffic delay shall be emphasized and alternative routes noted. Coordinate this effort with the Engineer and the Department's NAVIGATOR Informational Program. Telephone numbers for further information, and the date and time for the next scheduled public open house meeting shall be provided. The Engineer will approve the Notices. Hand carry or fax the Notices to the local news broadcasting media, emergency services, public service organizations and the major retailers near the Project corridor.

Notices shall also be distributed to the following local officials and transportation organizations, including but not necessarily limited to:

Alaska Carriers Association

Alaska Trucking Association

Alaska State Troopers

Seward Police Department

Seward Fire Department

Local Schools

Local Emergency Medical Services

US Postal Service

The Notices shall be submitted at the following times:

a.	one week prior to the beginning of construction,

b.	on Wednesday of each week during construction, and

c.	prior to any major change or disruption to traffic or local access.

Additionally, the PI professional shall notify business and residents that front the Project or scheduled road closures or of driveway, curb or sidewalk reconstruction, or any other work affecting them. Property owners with the work segment shall receive the Notices a minimum of one week prior to the commencement of the work within their segment. Lastly, provide daily information to those media who do non-paid public service road reports or announcements, and/or "Eye-in-the-Sky" commuter road reporting.

3.	Public Open House Meetings. Prepare presentations for the Engineer's Open House Meetings, and for of each of the Community Councils which represent areas affected the this Project. The Community Council meetings attended shall be the last regularly scheduled meetings prior to the beginning of construction.  Presentation size graphics shall be used to help explain the Project to the general public.

The PI professional shall be the Contractor's representative and spokesman, able to speak for him. The PI professional shall be available to attend additional public meetings, up to five, as requested by the Engineer.

4.	Other Agency Coordination. Coordinate with the city of Seward to take advantage of programs which will help decrease traffic through this Project, such as Park-and-Ride with express bus service, Ride Share, and the car pooling program. Also coordinate any major detours and closures with emergency service providers (police, fire, and ambulance), local school district bus operators, and the postal service.

5.	Final Report. Before Project completion, submit a Report evaluating the Public Informational Program as detailed under this Subsection. The Report shall include an outline of the program, an analysis of the program's effectiveness, and suggestions on how to improve the program's effectiveness, economy, and usefulness on future projects.

6.	Project Progress Meetings. Attend all scheduled or special Project meetings between the Contractor and the Engineer at the field office.

7.	Web Page. Generate an INTERNET web site for the Project containing Project updates, schedules and general narrative information. Add links to the Department's NAVIGATOR Home Page (www.dot.state.ak.us/navigator.html). Update the site weekly.

(8/13/99)R102M98

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.(01/29/02)R222M98

Add the following: Providing mail-outs, notices, displays for open house and public meetings, and providing weekly notices with updates will not be measured for payment. (8/13/99)R102M98

643-5.01 BASIS OF PAYMENT. Add the following:  The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion / ET-2000 LET | Each | $3,000.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Pedestrian Fence, Type I | Meter | $8.00 |
| Pedestrian Fence, Type II | Meter | $12.50 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (01/29/02)R222M98

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 643(15) Flagging | Contingent Sum |
| 643(31) Public Informational Program | Lump Sum |

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE. Delete this Subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Four (4) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Located within 1600 meters of the project.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

644-4.01 BASIS OF PAYMENT. . In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(2) Field Laboratory.

(9/28/00)R63M98

Add the following Section:	SECTION 645

TRAINING PROGRAM

Special Provision

645-1.01 DESCRIPTION.  This Training Special Provision implements 23 CFR 230, Subpart A, Appendix B.

As part of the Equal Employment Opportunity Affirmative Action Program, provide on-the-job training aimed at developing full journey status in the type of trade or job classification involved.  The number of individuals to be trained and the number of hours of training to be provided under this contract will be as shown on the bid schedule.

645-2.01 Objective.  Training and upgrading of minorities and women toward journey status is the primary objective of this program.  Enroll minorities and/or women, where possible, and document good faith efforts prior to the hire of non-minority males in order to demonstrate compliance with this Training Special Provision.  Specific good faith efforts required under this Section for the recruitment and employment of minorities and women are found in the Federal EEO Bid Conditions, Form 25A301, items 7.b, 7.c, 7.d, 7.e, 7.i, 7.j and 7.l, located in the "green pages" of this document.

645-3.01 General.  Determine the distribution of the required number of apprentices/trainees and the required number of hours of training among the various work classifications based upon the type of work to be performed, the size of the workforce in each trade or job classification, and the shortage of minority and female journey workers within a reasonable area of recruitment.

Training will be provided in the skilled construction crafts unless the Contractor can establish prior to contract award that training in the skilled classifications is not possible on a project; if so, the Department may then approve training either in lower level management positions such as office engineers, estimators, and timekeepers, where the training is oriented toward construction applications, or in the unskilled classifications, provided that significant and meaningful training can be provided. Some offsite training is permissible as long as the training is an integral part of an approved training program and does not comprise a significant part of the overall training.

Credit for offsite training hours indicated above may only be made to the Contractor where the apprentices/trainees are concurrently employed on the project and the Contractor does one or more of the following: contributes to the cost of the training, provides the instruction to the apprentice/trainee, or pays the apprentice's/trainee's wages during the offsite training period.

Where feasible, 25 percent of apprentices or trainees in each occupation shall be in their first year of apprenticeship or training.

Prior to award of the contract, submit Form 25A311, Training Utilization Report, indicating the training program to be used, the number of apprentices/trainees to be trained in each selected classification, the number of hours of training to be provided, and the anticipated starting time for training in each of the classifications.

Training must begin within 2 weeks of the anticipated start date(s); unless otherwise authorized by a Directive.  Such authorization will be made only after submission of documentation by the Contractor, and approval by the Engineer, of efforts made in good faith which substantiate the necessity for a change.

Contractors may use a training program approved by the U.S. Department of Labor, Bureau of Apprenticeship & Training (USDOL/BAT), or one developed by the Contractor and approved prior to contract award by the Alaska Department of Transportation and Public facilities (ADOT&PF) Training Program Representative, using Form 25A310.

The minimum length and type of training for each classification will be established in the training program selected by the Contractor.  Training program approval by the Department for use under this section is on a project by project basis.

It is expected that each apprentice/trainee will begin training on the project as soon as feasible after start of work utilizing the skill involved and remain on the project as long as training opportunities exist or until training has been completed.  It is not required that apprentices/trainees be continuously employed for the duration of the contract.

If, in the judgement of the Contractor, an apprentice/trainee becomes proficient enough to qualify as a journey worker before the end of the prescribed training period and the Contractor employs that individual as a journey worker in that classification for as long as work in that area remains, the individual's training program will be considered completed and the balance of training hours required for that apprentice/trainee shall be waived.

Furnish each ADOT&PF training program trainee a copy of the program (Form 25A310) to be followed during training on the project, and with a written certification showing the type and length of training completed on the project.  Existing USDOL/BAT apprentices should already have a copy of their program.  No employee shall be employed for credit as an apprentice/trainee in a classification in which that employee has previously worked at journey status or has previously completed a training course leading to journey status.

Periodically review the training and promotion potential of minority and women employees and shall encourage eligible employees to apply for such training and promotion.

Provide for the maintenance of records and the furnishing of periodic reports documenting the progress of each apprentice/trainee.  The Contractor must submit Form 25A313 by the 15th of each month and provide each ADOT&PF trainee written evaluation reports for each unit of training provided as established on Form 25A310.

645-3.02 Wages.  Trainees in ADOT&PF approved training programs will be paid prevailing Davis-Bacon fringe benefits plus at least 60 (but less than 100) percent of the appropriate minimum journey rate specified in the contract for the first half of the training period, at least 75 (but less than 100) percent for the third quarter of the training period, and at least 90 (but less than 100) percent for the last quarter of the training period.  Trainee wages shall be identified on Form 25A310.  Apprentices in USDOL/BAT training programs shall be paid in accordance with their approved program.  Beginning wages of each trainee/apprentice enrolled in a Section 645 Training Program on the project shall be identified on Form 25A312.

645-3.03 Subcontracts.  In the event the Contractor subcontracts a portion of the work, he shall determine how many, if any, of the apprentices/trainees are to be trained by the subcontractor.  Any such subcontracts shall include this Section 645, Form 25A311 and Form 25A310, where appropriate.  However, the responsibility for meeting these training requirements remains with the Contractor; compliance or non-compliance with these provisions rests with the Contractor and sanctions and/or damages, if any, shall be applied to the Contractor in accordance with subsection 645-5.01, Basis of Payment.

645-4.01 Method of Measurement.  The Contractor will be credited for each approved apprentice/trainee employed on the project and reimbursed on the basis of hours worked, as listed in the certified payrolls.  There shall be no credit for training provided under this section prior to the Contractor's submittal and approval by the Engineer of Form 25A312 for each apprentice/trainee trained under this Section.  Upon completion of each individual training program, no further measurement for payment shall be made.

645-5.01 Basis of Payment.  Payment will be made at the contract unit price for each hour of training credited.  Where a trainee or apprentice, at the discretion of the Contractor, graduates early and is employed as a journey worker in accordance with the provisions of subsection 645-3.01, the Contractor will receive payment only for those hours of training actually provided.

This payment will be made regardless of any other training program funds the Contractor may receive, unless such other funding sources specifically prohibit the Contractor from receiving other reimbursement.

Payment for training in excess of the number of hours specified on the approved Form 25A311, may be made only when approved by the Engineer through Change Order.

Non-compliance with these specifications shall result in the withholding of progress payments until good faith efforts documentation has been submitted and acceptable remedial action has been taken.

Payment will be at the end of the project following the completion of all training programs approved for the project.  No payment or partial payment will be made to the Contractor if he fails to do any of the following and where such failure indicates a lack of good faith in meeting these requirements:

1.	provide the required hours of training (as shown on the approved Form 25A311),

2.	train the required number of trainees/apprentices in each training program (as shown on the approved Form 25A311), or

3.	hire the apprentice/trainee as a journey worker in that classification upon completion of the training program for as long as work in that area remains.

Failure to provide the required training damages the effectiveness and integrity of this affirmative action program and thwarts the Department's federal mandate to bring women and minorities into the construction industry.  Although precise damages to the program are impractical to calculate, they are at a minimum, equivalent to the loss to the individuals who were the intended beneficiaries of the program.  Therefore, where the Contractor has failed, by the end of the project, to provide the required number of hours of training and has failed to submit acceptable good faith efforts documentation which establishes why he was unable to do so, the Contractor will be assessed an amount equal to the following damages to be deducted from the final progress payment:

Number of hours of training not provided, times the journey worker hourly scale plus benefits.  The journey worker scale is that for the classification identified in the approved programs.  (10/29/91)S 16

Payment will be made under:

| # Pay Item | Pay Unit |
| --- | --- |
| 645(1) Training Program, 1 Trainees/Apprentices | Labor Hour |

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Delete this subsection in its entirety and replace with the following:  Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:	SECTION 647

EQUIPMENT RENTAL

## Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operational, which includes the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

Furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

Furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(5) will be paid on a contingent sum basis at the rate of $125/hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation. (11/12/98)R15M98

Payment will be made under:

| # Pay Item | # Pay Unit |
| --- | --- |
| 647(5) Rubber Tired Backhoe, 4WD, 0.75 CM Bucket, 48 kW Minimum | Contingent Sum |

Add the following Section:

SECTION 651

- MISCELLANEOUS METAL FABRICATIONS

Special Provisions

651-1.01 DESCRIPTION.  The work under this Section includes, but is not limited to, all shop drawings, structural calculations, all labor, materials, transportation, testing, maintenance, and service necessary to furnish and install a covered seating structure, ornamental fencing, “Octopus” bike rack, interpretive structures, thematic “Whale’s Tail” benches and standard benches as shown on the Plans, specified herein and with Section 504, Steel Structures.

Recognize that the covered seating structure, the bike rack, interpretive structures, and thematic benches will require preliminary, pre-final and final shop drawings to be submitted for review by the Engineer prior to construction.

You are responsible for the verification of all existing utilities or requesting locates of underground utility lines.

651-1.02 CONTRACTOR QUALIFICATIONS.  Qualification of fabricators and installers shall meet the following:

1.	At least five years of continuous experience in the fabrication of custom products.

- Currently certified by the American Welding Society (AWS).

3.	The “Code for Welding in Building Construction” of the American Welding Society, latest edition.

651-1.03 SUBMITTALS.  Do not begin construction of miscellaneous site fabrications until all submittal requirements are satisfied and approved by the Engineer.  If you deviate from the approved submittals, you must re-submit the changes for approval.  A professional civil engineer registered in the State of Alaska and practicing in the field of structural engineering must stamp the shop drawings.  No adjustments in contract time will be allowed due to incomplete submittals.  Obtain a building permit from the City of Seward and arrange for on site inspections by City inspectors.

The submittal process is as follows:

- Submit preliminary shop drawings of all fabrications to the Engineer.  The shop drawings must clearly show all material, finishes, connections, joining methods, installation locations, field measurements and foundations.  Upon receiving your preliminary submittal, the Engineer shall have 10 days to provide written comments back to you.

- Review the Engineer’s comments for the preliminary shop drawings and prepare pre-final shop drawings that clearly show all materials, finishes, connections, joining methods, installation locations, field measurements and foundations.  Upon receiving your pre-final submittal, the Engineer shall have 10 days to provide written comment back to you.

- Provide catalog cuts of proposed seating for the Engineer’s approval.

- Provide the construction methods for puffins, crab, and octopus to be located in Covered Seating Structure.

- Provide the original or maquette of castings for sign post tops, indicating level of detail.

- Review the Engineer’s comments for the pre-final shop drawings and prepare final shop drawings that clearly show all materials, finishes, connections, joining methods, installation location, field measurements and foundations.  Provide all structural calculations for snow, wind and gravity loads.  These calculations must be done by a professional civil engineer registered in the State of Alaska and practicing in the field of structural engineering. Approved final shop drawings and calculations shall become the basis for acceptance of Work.

- Provide the Engineer a sample of Covered Seating Structure column caps for approval.  If approved, the cap will be returned to you for installation.

- Provide the Engineer 75 mm x 150 mm color chips of specified colors from RAL Standard color chart for approval.

- Provide letter samples “SEWARD ALASKA”.

- Sample of graphic for installation in fence panels.

651-2.01 MATERIALS.

# Concrete 		Section 501, Class A

Reinforcing Steel				Section 503

Paint						Section 708 as modified

Structural Steel and Related Materials		Section 716

Stainless Steel, 308 				Conform to ASTM A 240

Roofing for Covered Seating Structure		24 gauge steel, corrugated 2-1/2” x 9/16” depth, galvanized, meet Section 716.

Silicon Bronze	97% copper 3% silicon  all silicon bronze shall conform to ASTM B 96

Steel Pipe	ASTM A 53, Schedule 40

651-2.02 METAL SILHOUETTES.  Make the silhouettes of puffins, crab, and octopus located within the Covered Seating Structure framework from 6 mm stainless steel plate.  Ensure the silhouettes have a clean edge.  Templates are available from the Engineer.

651-2.03 LETTERING.  Use Schedule 40 stainless steel to construct the Ring displaying “SEWARD ALASKA” lettering.  Use silicon bronze Times New Roman letters.

651-2.04 POST CAPS.  Manufacture post cap birds using a “Lost Wax” casting process.  Construct silicon bronze bird castings approximately ½ size and proportional to the original animals found in the wild as shown on the Plans.  Provide original art pieces for use in the casting process.  Detail the art enough so viewers can easily identify the type of bird represented and differentiate body parts, creases/contours and contrasting patterns/textures/colors in the individual animals.  Individual feather differentiation is not required, but may be gained through use of general textures instead .

Permanently affix the feet of the castings via the casting process (or as directed by the Engineer) to the cap as shown in the Plans.  Attach the casting/cap to the post as shown in the Plans.

651-2.03 SEATING.  Construct seating for “Covered Seating Structure” from steel wire or steel band with a steel support structure.  Construct the seating with back-rests and no arms using contemporary lines.  Provide four individual seats for each side of the structure mounted to tube steel fabricated as part of the Covered Seating Structure.  Install the structure seats according to your submitted and approved shop drawings.

Fabricate sidewalk benches 2 meters in length with straight-backs, arms, 4 legs and a black powder coat finish.  Construct the structure using steel with woven or horizontal straps.  Submit three candidate samples for selection by the Engineer.

Construct the Whale’s Tail Seating from 12 mm plate steel with continuous welded seams.  Provide a black powder coat finish as shown in the Plans.

651-2.06 ETCHED BRONZE PLAQUES.  Fabricate two-color, micro-metal etched bronze plaques with the City of Seward’s logo for the Covered Seating Structure, Fence Panels, and for the sidewalk seating.  Use a bright bronze base material with a dark or black etched finish for the image.  Submit process and sample product for review and approval.  The Engineer shall provide the original/template electronically.  You are responsible for etching. Use 6 mm thick metal.

651-2.07 FINISHES.  Comply with National Association of Architectural Metal Manufacturer’s (NAAMM) Metal Finishes Manual for recommendations on application and designation of metal finishes.

Provide a black powder coat finish for all mild steel fabrications.  Powder coating shall be prepared using the following five-step process to provide an acceptable finish:

- Rinse and clean with clear water

- Phosphate treat to etch surfaces

- Re-rinse with clear water

- Oven dry surfaces prior to powder coating

e.	Application of polyester powder by the electrostatic spray process to a thickness of 0.04 mm.

Provide a natural “yellow” bronze finish for post cap bird shapes.  They will be allowed to weather.

Provide a polished “yellow” bronze, buffed finish for “SEWARD ALASKA” letters and for column caps in the Covered Seating Structure.  These shall be sealed.

Stainless steel pieces shall have a “bright” finish.

Provide bright bronze plaques with black etching for fence and bench installation.  The plaques shall be sealed.

651-2.08 PILE CAPS.  Pile caps for the covered seating structure shall be white polyethylene, cone shaped, sized to provide a snug fit on the exposed pipe ends.  They shall meet the following requirements:

Property	Value	Tests

Density	0.9 g/cm3	ASTM D 1505

Melt Index	8.0 g/10 min.	ASTM D 1238

Tensile Strength at break   	26.2 MPa	ASTM D 638

Elongation at break	970	ASTM D 638

Tensile Impact	1,103 J/cm (3,800 ft*lbs/in)	ASTM D 1822

Low Temperature Brittleness	Less than 76°C	ASTM D 746

651-3.01 CONSTRUCTION REQUIREMENTS.  Assemble metal fabrications as per the approved shop drawings.  Weld in accordance with “Code for Welding in Building Construction” of the American Welding Society, latest edition.

Finish metal fabrications after assembly.

Prepare site for metal assemblies.

Call for inspection at significant steps of the process:  metal fabrication in shop, foundation installation, in-shop metal assembly, on site assembly and installation.

651-4.01 METHOD OF MEASUREMENT.

Items 651(1), 651(3), and 651(5) through 651(7).  The actual number installed and accepted by the Engineer.

Item 651(2) Decorative Fence.  By the meter measured along the top of fence that is installed and accepted by the Engineer.

Item 651(4) Covered Seating Structure.  No measurement of quantities will be made.

651-5.01 BASIS OF PAYMENT.

Payment shall include full compensation for all work and materials required to construct and install the items shown in the bid schedule in accordance with the Specifications.

Items 651(1) Post Top.  At the contract unit price for each item completed and accepted.  Payment will be full compensation for all work and labor required for complete installation according to the Plans and specifications.  This includes post top fabrication, post support, foundation and installation of post top.  There shall be no differentiation between the types of bird used.

651(3) Kiosk.  At the contract unit price for each item completed and accepted.  Sidewalk and pavers shall be paid under their respective pay items.

651(5) Octopus Bicycle Rack.  At the contract unit price for each item completed and accepted.

651(7) Sidewalk Bench.  At the contract unit price for each item completed and accepted.  Bronze plaques shall be subsidiary.

Item 651(2) Decorative Fence.  At the contract unit price of fence installed and accepted.  Bronze plaques shall be subsidiary.

Item 651(4) Covered Seating Structure.  At the lump sum price.  Payment includes full compensation for all labor and material required including all appurtenances such as seating, silhouettes, roof, etc.

Payment will be made under:

| Pay Item | Pay Unit |
| --- | --- |
| 651(1) Post Top | Each |
| 651(2) Decorative Fence | Meter |
| 651(3) Kiosk | Each |
| 651(4) Covered Seating Structure | Lump Sum |
| 651(5) Octopus Bicycle Rack | Each |
| 651(6) Whale’s Tail Seat | Each |
| 651(7) Sidewalk Bench | Each |

SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following:

- Approved Products List: The Approved Products List does not apply to the 660 items. Refer to Appendix of Materials Certification List of required items to submit for approval.

Delete item number 2 that follows the first paragraph, and add the following:

2.  Provide catalog cuts that include the manufacture’s name, type of product, size, model number, conformance specifications, any other data as may be required of all materials to the Engineer for review and approval by the department.

Add the following to the last paragraph:  The Engineer will deliver one copy each as built to:  the  City of Seward Engineering and Electrical department; State Maintenance and Operations; Technical Services; Statewide Materials; and attach the appropriate sheets of the last set either in plastic laminate or in clear plastic envelopes to the inside of each load center or electrical pedestal.

660-1.05 MAINTAINING EXISTING AND TEMPORARY ELECTRICAL SYSTEMS.   Delete this Subsection in its entirety and substitute the following:

This work consists of protecting and maintaining the existing and temporary electrical systems during the life of the contract.  The work includes: repairing, replacing, adjusting, realigning, cleaning, and relocating components of highway lighting systems, and flashing beacons to keep them wholly operational and positioned in accordance with the following specifications.

At the Pre-construction Conference, furnish the Engineer with the name and phone number of the person who will maintain the existing and temporary electrical facilities. Make this person available at all times until the date of Acceptance for Traffic and Maintenance.   Provide all labor, materials, and equipment this person may need to complete repairs ordered by the Engineer.

When you begin work, the Engineer will notify you and the local maintenance agencies in writing of the transfer of maintenance responsibilities, providing an effective date and time.  Maintenance does not include replacing defective equipment or repairing damage before transferring maintenance responsibility.  Therefore, before starting work on the project, you should inventory the condition of the existing equipment and document all damaged and defective equipment, which the Engineer will inspect with you.  If you begin work before providing the Engineer with an inventory, you waive the right to claim extra compensation when the Engineer later finds damaged or defective equipment.

Keep all components of the existing and temporary electrical systems fully operational during the progress of the work, except when the Engineer allows shutdowns to alter or remove the systems.  The Engineer will consider these systems fully operational when he finds no damaged or defective equipment in service, and photoelectric controls operate the lighting systems.  Furnish replacement equipment compatible with equipment used in the Central Region.

Notify the Engineer within one hour of beginning repair work on all systems.  If you do not complete the repairs, the Engineer may have outside forces complete the repairs and deduct the amount billed from any monies due you.

Locate existing conduit runs, buried cables, junction boxes, and all underground utilities before starting work that may damage these facilities or interfere with these systems.

Relocate or replace lighting standards, sign poles, flashing beacon poles, load centers, and controller cabinets whenever their clearance from the traveled way is less than 1.8 meters.

Where roadways are to remain open to traffic and existing lighting systems are to be modified, energize the modified circuit by sunset on the same day the original circuit is retired.

If you fail to maintain the electrical system as specified herein, the Engineer will adjust payments to you according to subsection 643-3.06, Traffic Price Adjustment

When no longer required, salvage all original and Department provided equipment in accordance with the plans and subsection 660-3.21, Salvaging or Reusing Electrical Equipment, remove all other materials used in the temporary systems from the project.

All materials shall conform to the requirements of the plans and specifications.  Use temporary equipment compatible with existing equipment used in the Central Region.  Provide load centers as required in subsection 660-1.05(B), Temporary Illumination Systems.

Add the following paragraphs:

Provide temporary illumination at all locations with existing lighting, along all roadways that transition from one section to another.  Provide this work during the life of the contract on all roadways open to traffic within the project limits.  Make temporary lighting systems operational by sunset on the day you replace or retire a system, or you open a roadway and/or detour to traffic.

Submit a plan for each temporary lighting system to the Engineer for his review and approval before implementing.  Make sure the temporary lighting plans equal the systems being replaced or modified.  At intersections consider the street with the vehicular right-of-way as the main street; four-ways stops, consider both streets main streets.

Furnish and install all materials and miscellaneous hardware required to provide a functional lighting system, including electrical load centers.  All materials shall conform to the requirements of the Plans and specifications, except branch conductors may be triplex aluminum with messenger cable if they are installed overhead.  Install branch conductors in underground electrical conduit when overhead conductor clearances do not conform to the National Electrical Safety Code (NESC).  Size conductors to provide the minimum voltage recommended by the ballast manufacturer at the most remote luminaire.  You may use the existing luminaires or new luminaires with a light distribution compatible with the proposed lighting system configuration.

Use any of the following poles that maintain a minimum 12 m difference in elevation between a luminaire and the edge of traveled way beneath it.

1.	Existing poles if they are not owned by a utility.

2.	Poles from the permanent lighting system.

3.	ANSI Class 4 wood poles that you furnish.

4.	Steel or aluminum poles that meet design criteria for 130 kilometer per hour wind speeds according to AASHTO Standard Specifications for Structural Supports.

Install all light poles with the ends of the mast arms situated over the face of curb.  Retain the breakaway base features, when you relocate existing electroliers.  Provide all other poles installed in the clear zone, except traffic signal poles, with FHWA approved slip bases, transformer bases, or frangible coupling bases.  Install wood poles and all other fixed base poles behind portable concrete barrier; provide a 0.6 meter space between the barrier and the pole.

Use any of the following load centers to energize the temporary lighting.  Provide all work needed to modify load centers to provide functional temporary lighting according to the NEC.

1.	Permanent load centers installed in their plan location.

2.	Existing load centers scheduled to remain intact until completion of the project. You may not relocate and reuse existing load centers.

3.	Approved temporary load centers with photoelectric controlled lighting circuits.  Provide a temporary load center when you retire an existing load center that is not approved, and when approved load centers are unavailable.

Approved load centers include load centers UL labeled as Service Equipment, or UL labeled as Industrial Control Equipment and marked "Suitable for use as service equipment".

660-2.01 EXCAVATING AND BACKFILLING.  In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

660-2.03 FOUNDATIONS.  Delete the Pile Foundations subsection and substitute the following:

Pile Foundations.  Install all foundations for light poles with shaft lengths less than 18 meters according to the following requirements

- Materials. Furnish pipe piles that feature the diameter, minimum length, and wall thickness shown on the Plans.  Furnish piles that conform to ASTM A252, grade 3.  The Department will only accept seamless piles or piles with a single longitudinal seam that is electric resistance welded.

- Furnish pile cap adapters fabricated by the pole manufacturer.

- Construction Requirements. Install the steel pipe piles open ended according to Section 505. Complete all splices and extensions in piles according to Section 505. Attach the pile cap adapter to the pipe pile with a full penetration circumferential weld.

Complete all welding shown on the Plans and as specified herein according to the Structural Welding Code –Steel, AWS D1.1-2000. At least 30 calendar days before you begin welding, submit a welding plan and mill certification reports for the pipe piles and pile caps to the Engineer for approval.  Do not begin welding until the Engineer has returned these items approved in writing.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS),

- Procedure Qualification Record (PQR),

- Welder Performance Qualification Record (WPQR),

- Visual Inspection Form,

- Report of Nondestructive Examination (NDE) of Welds, and

- The name of the Contractor’s Quality Control (QC) manager with documentation of qualifications.

Furnish all Quality Control inspection necessary to ensure the materials meet the requirements of the contract documents and workmanship meets the requirements of AWS D1.1.

- Visually inspect (VT) the entire length of each weld.

- Inspect all full penetration welds by ultrasonic NDE (UT).

Correct all deficiencies in materials and workmanship revealed by QC and Quality Assurance (QA) inspections according to AWS D1.1 without additional compensation.

Furnish all completed QC inspection documents to the Quality Assurance representative designated by the State.

Install the frangible couplings according to the manufacturer’s written installation instructions.

660-2.04 POLES, STEEL PEDESTALS AND POSTS.  Add the following: Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged or destroyed by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas in accordance with subsection 660-2.15, Galvanizing.

Fabricate pile cap adapters from steel piles that conform to ASTM A252 grade 3 and steel plate that conforms to ASTM A709 grade 50.  Only use seamless piles or piles with a single longitudinal seam that is electric resistance welded.  Attach the anchor plate to the pile section with a complete joint penetration (CJP) weld.  Furnish the adapters hot dip galvanized according to ASTM A123, except leave the beveled edge free of zinc.  Fabricate the anchor plate to match the base plate of the lighting standard.  See the detail sheet in the plans for all dimensional information.

Complete all welding design, fabrication, and inspection according to the latest edition of the AWS D1.1, Structural Welding Code-Steel

- Circumferential Welded Splices

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Longitudinal Seam Welds

- Inspect 100% of CJP welds by ultrasonic testing (UT)

- Inspect 25% of all PJP welds of longitudinal seams by magnetic particle testing (MT)

- Base Connection Welds

- Inspect 100% of all base connection welds.

- Inspect CJP welds by UT

- Inspect fillet welds by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Quality Assurance (QA) representative for approval.  Do not begin welding until these items have been returned approved in writing by the QA representative.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS)

- Procedure Qualification Record (PQR)

- Welder Performance Qualification Record (WPQR)

- Visual Inspection Form

- Report of Nondestructive Examination (NDE) of Welds according to Annex K, latest edition of AWS D1.1

- NDE personnel qualification records

- The Contractor’s Quality Control (QC) manager with documentation of qualifications

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT.  Add the following:  The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  After you pave the final asphalt course, however, the Engineer will not allow trenching.

660-2.06 JUNCTION BOXES.  Delete the second paragraph and substitute the following:  Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS.  Delete item 2. Power Conductors and Cables and add the following:

- Power Conductors.  For individual conductors, install general-purpose building wire manufactured according to UL Standard 44, ICEA publication S-66-524, and NEMA Publication No. WC7.  Furnish conductors insulated with cross-linked polyethylene, UL listed as type XHHW-2 and rated for 600 volts AC operation.

- Provide the following markings on the conductor insulation: manufacturer, conductor size, 600V, the symbol of an Approved Independent Testing Laboratory, and XHHW-2 on intervals of 2 feet or less.

- Use size 10 AWG wire for illumination tap conductors.  In an electrolier, the illumination tap conductors run from the fused disconnect kit to the ballast in the luminaire. Furnish conductors with black, red, or white colored insulation as required to identify the two phase and neutral conductors, respectively.

- If conductors in controller cabinets carry the full signal load circuit, use size 10 AWG or larger conductors.  Use orange colored conductors from the flash transfer relay to program emergency flashing operation.

- Illumination Cables.  For cables that consist of three size 6 or 8 AWG conductors, furnish power cables that feature three conductors, each insulated with cross-linked polyethylene, and a black, low density, high molecular weight polyethylene jacket.  Use conductors UL listed as type XHHW-2.  Furnish these cables with one black, one white, and one red colored conductor and no ground conductor. Use cables rated for 600 volts AC operation.

- Use insulated conductors that meet the requirements of ICEA publication S-66-524 and Underwriters Laboratories for Type XHHW.  The jacket shall also meet the requirement of ICEA publication S-66-524.

- Provide the following markings on the jacket:  manufacturer, conductor size, number of conductors, and 600V on intervals of 0.6 meters or less.

- Power Cables.  For cables that consist of three size 4 AWG and larger conductors, furnish tray cables that feature three conductors, each insulated with cross-linked polyethylene, and a PVC jacket.  Furnish these cables with no ground conductor. Use cables manufactured according to ICEA publication S-95-658 and NEMA Publication No. WC70.  Provide cables UL listed for direct burial and resistance to sunlight and rated for 600 volts AC operation.

Furnish these cables with black conductor insulation with one printed number (1, 2, or 3) identifying each conductor. Provide conductors UL listed as type XHHW-2.

Provide the following markings on the jacket: manufacturer, number and size of conductors, TYPE TC, 600V, sunlight resistant, 90oC Dry 75oC Wet, and symbol of an Approved Independent Testing Laboratory on intervals of 0.6 meters or less.

660-2.09 WIRING.  Delete the first paragraph and add the following:  Install illumination cables without splices, except when adding an electrolier to the midst of a circuit.  In addition, do not splice conductors within cabinets, poles, and luminaires.

Crimp spade type terminals onto all conductors that attach to terminal blocks.  When reusing cabinets, replace terminal blocks that lack enough terminals.  Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

Delete the first two sentences of paragraph numbered 7 and add the following:  Pull illumination and power cables through the junction boxes adjacent to electroliers.  If the plans include the electrolier or outlet in a circuit, install illumination cable between the fused splice connectors and electrolier; make a parallel splice in the junction box to join the cables together.

Delete paragraph numbered 14.  Add the following:  Label the cables used in the  illumination systems with the following legends:

For the cables listed in Table 660-1, use the legends included in the same Table.

Furnish the type of identification tags listed below that feature hand written legends.  Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer.  Replace at no expense to the State all identification tags the Engineer deems illegible.

1.	To label all cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear.  Provide tags with a 100 mm by 44 mm minimum size that attach flag style at one corner to a single strap.  Furnish red tags for labeling lighting and feeder cables.

660-2.10 FUSED SPLICE CONNECTORS.

Add the following:  Retrofit reused poles with new fused disconnect kits.

660-2.11 BONDING AND GROUNDING.  Delete the second paragraph and add the following:

Use No. 8 AWG copper conductor with green colored insulation as the grounding conductor in all conduit.  All hardware including insulated throat grounding bushing, ground rods, and clamps shall be UL listed.  Grounding bushing shall be the threaded type.

Where wire is pulled and reinstalled in existing conduits, the  No. 8 AWG green clad copper wire shall also be installed.  Where conduits are installed for future conductors, the above mentioned copper wire may be omitted.

660-3.16 LUMINAIRES.  Add the following:  Furnish high pressure sodium lamps with a rated life of 24,000 hours based on 10 hours per start.

Furnish luminaires that:

1.	Are UL 1572 listed for use in wet location.

2.	Include a terminal block for terminating the illumination tap conductors.

3.	Feature an easily removed hinged door or tray used exclusively for mounting the ballast.

4.	Provide the illumination levels and uniformity specified (or better) in the arrangements listed on the plans when calculated according to the American National Standard Practices for Roadway Lighting, A.N.S.I./I.E.S. RP-8, dated 1983.

5.	Include a lamp-starting aid that plugs into a socket for easy replacement.

6.	Furnish a wire way that meets NEC requirements for installing three #10 AWG conductors with type XHHw-2 insulation between the pole and a terminal block located in the luminaire.

7.	Are free of substances (such as paint) that affect photometric performance.

Furnish the Engineer with the manufacturer’s current electronic photometric data in Illuminating Engineering Society (I.E.S.) format to verify illumination levels and uniformity ratios.

Luminaire Type Definitions:

MC-3:	Mastarm Mounted Medium Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

MS-3:	Mast-arm Mounted Semi Cutoff, Type 3 as defined by the Illuminating Engineering Society (I.E.S.).

Offset:	Pole top mounted luminaires designed to be offset between 6 and 15 meters from the edge of traveled way and angled between 30 and 50 degrees from the horizontal.

660-3.21 SALVAGING OR REUSING ELECTRICAL EQUIPMENT. Add the following:  Transport all illumination equipment from the project, to the City of Seward  Maintenance Yard in Seward.  Allow maintenance personnel to select the equipment they would like to salvage, and the remaining equipment becomes the property of the Contractor to dispose of.  Contact Dave Calvert, City of Seward Engineer, Jeff Estes, at (907)224-     Electrician or George Church, Peninsula District Superintendent, at (907)262-2199; provide one week notice of your intent to deliver salvaged materials.

660-5.01  BASIS OF PAYMENT.  Add the following:  The lump sum prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans. This includes: completing all excavation to install foundations, conduits, retrofitting all existing conduit that will contain new illumination cable with new ground bushings, festoon outlets, fuse disconnects, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The lump sum prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

SECTION 661

ELECTRICAL LOAD CENTERS

Special Provisions

661-2.01 MATERIALS. Add the following paragraph:  Furnish load center cabinets that are fabricated entirely from stainless steel and rated as NEMA Type 3R enclosures.

661-5.01  BASIS OF PAYMENT.  Add the following:  The following work is subsidiary to Items 661(2) Load Center, Type 1A and 661(3), Load Center, Type 2.

1.	Provide all work detailed on the Plans for Pedestal 2 on Fourth Avenue at station F 10+275 left up to the  pedestal.  The City of Seward’s electrician will make the required connect of the new  number 8 AWG circuit for Pedestrian electroliers (illumination cable only) L4-40A and L4-40B.

***Deleted***

2.	Terminate the existing illumination cables that feed the circuits shown in each load center summary.

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.01 CONSTRUCTION REQUIREMENTS. Under item 4 Methyl Methacrylate Pavement Markings, delete the last sentence in the first paragraph and substitute the following: Do not apply striping to the new asphalt until the asphalt has cured for the duration listed below and at the Engineer’s discretion.

Stone Mastic Asphalt Concrete	30 days

All others				15 days

Under item 4 Methyl Methacrylate Pavement Markings. , delete the second paragraph and substitute the following: Apply Methyl Methacrylate marking material with truck mounted equipment designed and capable of properly mixing at the point and time of application according to the manufacturer’s recommendations.

Supply and use a Methyl Methacrylate application monitoring system (MMAMS) that calculates flow throughout the high pressure airless pumps.  The MMAMS shall measure the combined A and B Methyl Methacrylate components and show the total volume applied on a digital readout display.  The digital readout shall display two (2) decimal places and be located on the operator control panel.  The digital readout display shall be selectable to show output volume in liters.

Add the following under item 4. before the third paragraph:  A film test strip will be required at the beginning of each striping shift, and when there is a change in the asphalt type. In addition, measure out one (1) liter of Methyl Methacrylate for field verification of the MMAMS accuracy. Additional film test strips and MMAMS accuracy samples may be required at the Engineer’s discretion. (09/04/01)R221M98

Under item 4. Methyl Methacrylate Pavement Markings.  delete the first sentence in the fifth paragraph and substitute the following:  Apply markings for lane lines, edge lines, and center lines at a yield thickness of 2.3 mm (1 liter will yield a 2.3 mm thick stripe 100 mm wide by 4.348 m in length).

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15 m longitudinal run from the Plan quantity.

670-4.01 METHOD OF MEASUREMENT.  Add the following after Item 4:

5.	Liter Basis:  The Methyl Methacrylate material used to form the pavement markings accepted by the Engineer will be measured in liters.  The Department will limit the final quantity to 115% of the Plan quantity.

670-5.01 BASIS OF PAYMENT.  Add the following to the second paragraph:

All costs associated with the MMAMS are subsidiary to Item 670(10B), Methyl Methacrylate Pavement Markings and no separate payment shall be made.

Add the following: The Department will pay the contract unit price for the volume of Methyl Methacrylate accepted by the Engineer up to a maximum of 115% of the quantity shown in the Plans.  All Methyl Methacrylate material over-runs above 115% of the plan quantity shall be paid for by the Contractor at no expense to the Department.   (04/30/02)R246m98

Payment will be made under:

| #### Pay Item | #### Pay Unit |
| --- | --- |
| 670(10B) Methyl Methacrylate Pavement Markings | Liter |

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following.

Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T-53 and ASTM D5801 assigned to each grade.

.

Performance Graded Asphalt Cement

PG 52-28		PG 58-28		PG 64-28

Softening Point

AASHTO T-53	(none)			49°C			52°C

Toughness min.

ASTM D5801 	(none)			12.4 N-m		12.4 N-m

Tenacity min.

ASTM D5801		(none)			8.5 N-m		8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

# Special Provisions

703-2.02 COARSE AGGREGATE FOR CONCRETE.  Add the following after the first sentence:  Substitute the following gradations in Table 1 of AASHTO M 43 for exposed aggregate concrete only:

| Designated Sizes | 50 mm | 37.5 mm | 25 mm | 19 mm | 13.2 mm | 9.5 mm | 4.75 mm |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 19 mm to 4.75 mm | -- | -- | 100 | 90-100 | -- | 20-26 | 0-10* |
| 37.5 mm to 19 mm | 100 | 90-100 | 20-55 | 0-15 | -- | 0-5 | -- |

*Not more than 5% shall pass the 2.36 mm sieve.  All coarse aggregate shall have a minimum of two fracture faces.

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

## TABLE 703-2

## AGGREGATE FOR UNTREATED BASE

## Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.(06/25/99)M 82

703-2.12 SAND BLANKET. Delete Table 703-8 and replace with the following:

| U.S. Standard Sieve (mm) | Percent by Weight Passing |
| --- | --- |
| 12.5 | 100 |
| 9.5 | 90-100 |
| 4.75 | 80-100 |
| 2.36 | 65-85 |
| 1.18 | 50-75 |
| 0.600 | 40-60 |
| 0.300 | 18-30 |
| 0.150 | 5-15 |
| 0.075 | 4-9 |

SECTION 706

CONCRETE AND PLASTIC PIPE

Special Provisions

706-2.07 CORRUGATED POLYETHYLENE PIPE.  Delete this Subsection in its entirety and substitute the following:  Non-perforated, smooth-wall pipe conforming to the following:

Polyethylene (PE)			AASHTO M 294, Type S

SECTION 708

# PAINTS

Special Provisions

708-2.01 PAINT FOR STEEL.  Add the following:

- Polyester material for powder coating shall meet AAMA 605.2 performance standards.  Material shall be as follows:

Chemical Type:	Polyester

Particle Size:	30-60 microns average

Specific Gravity:	1.2-1.7

Cure Cycle:	400F-10MINS Peak Metal Temperature (TGIC)

400F-15MINS Peak Metal Temperature (Polyurethane)

Gloss @ 60 Degree:	Available from 30-90+ Degrees

Film thickness: 	1.5 mils

Mechanical Specifications ASTM # or AAMA 605.2

Dry Adhesion D3359 7.4.1.1	100% 5b Pass

Wet Adhesion 7.4.1.2	100% 5b Pass

Boiling Water Adhesion 7.4.1.3	100% 5b Pass

Hardness D3363 7.3.1.2H	Pass

Impact Direct D2794-67 7.5.1	Up to 160” Lbs. Pass

Reverse D2795-67 7.5.1 	Up to 160” Lbs. Pass

Abrasion Resistance D968 7.6.1 Coefficient	28 Pass

Chemical Resistance AAMA 605.2

Muriatic Acid 15 Minutes	No effect

Mortar Resistance 24 Hours	No effect

Nitric Acid Resistance 30 Minutes	Less than DE2 Color Change

Corrosion Resistance ASTM # or AAMA 605.2

Humidity D2247 7.8.1 3000 Hours 	Rated “8” Few Blisters

Salt Spray B117 7.8.2 3000 Hours	Less than 1/16” Creepage

SECTION 712

MISCELLANEOUS

## Special Provisions

712-2.17 METHYLMETHACRYLATE PAVEMENT MARKINGS.

2.	Performance Properties: Add the following:

k.	Adhesion: 	To Portland Cement, minimum 13.8 MegaPa, to asphalt, dependent on tensile failure of the substrate.

(09/04/01)R221M98

## SECTION 724

# SEED

Special Provisions

724-2.01 DESCRIPTION.  Add the following:  Each species of seed to be supplied separately and not as mixtures.  Mark each container with the weight and with the manufacturer’s guaranteed analysis of the contents showing the percentage for each ingredient contained therein.

724-2.02 MATERIALS.  Delete Table 724-1 in its entirety and substitute the following tables:

TABLE 724-1

- SEED REQUIREMENTS

Schedule A - Wildflower Mix (Application Rate: 45 kg/ha)

### NAME	GERM PD	PURITY	GERM RATE  RATE/HA

Alaska Carnation

(Dianthus repens)	14 days	90%	85%	1 kg

Canada Goldenrod

(Solidago canadensis)	14 days	85%	85%	1.5 kg

Alyeska Polargrass

(Arctagrostis latifolia)	14 days	90%	90%	7.5 kg

Arctared Fescue

(Festuca rubra)	14 days	95%	85%	10 kg

Blue Flax

(Linum perenne lewisii)	14 days	85%	85%	1.5 kg

Cornflower

(Centurea cyanus)	14 days	85%	85%	1 kg

Plains Coreopsis

(Coreopsis tinctoria)	14 days	85%	85%	1.5 kg

Icelandic poppy

(Papaver nudicaule)	12 days	85%	85%	1 kg

Maltese Cross

(Lychnis chalcedonica)	12 days	85%	85%	1 kg

Nootka Lupine

(Lupinus nootkatensis)	14 days	85%	75%	5.5 kg

Shasta Daisy

(Chrysantheum maximum)	14 days	85%	85%	1 kg

Shirley Poppy

(Papaver rhoeas)	12 days	95%	95%	1 kg

Siberian Aster

(Aster sibiricus)	14 days	85%	80%	1.5 kg

Siberian Wallflower

(Cheiranthus allionii)	12 days	85%	85%	2 kg

Tall Jacob’s Ladder

(Polemonium acutiflorum)	14 days	90%	85%	2 kg

Tall Larkspur

(Delphinium glaucum)	14 days	90%	85%	2 kg

Yarrow

(Achillea millefolium)	14 days	90%	85%	2 kg

Western Columbine

(Aquilegia formosa)	14 days	85%	85%	2 kg

SECTION 726

TOPSOIL

Special Provisions

726-2.01 TOPSOIL.  Replace item (2.) with the following:

2.	Topsoil shall contain not less than 5 percent and no greater than 15 percent organic matter by dry weight as determined by ATM T-6.

Delete the gradation table in the third paragraph and substitute the following:

| Sieve Size (mm) | Percent Passing (by Weight) |
| --- | --- |
| 12.5 | 100 |
| 4.75 | 95-100 |
| 1.18 | 64-90 |
| 0.075 | 30-60 |

Delete last sentence in second paragraph and substitute the following:  Submit a soil analysis for particle size, nutrient content and organic content to the Engineer for acceptance at least 10 days before final placement.  The Engineer may test the topsoil at any time to verify compliance with the topsoil analysis.  If the supplied topsoil does not meet these specifications, supply new topsoil of a quality required to meet the typical sections shown in the Plans.

Delete the fertilizer requirements (not the limestone requirements) of this Subsection and substitute the following:

Nitrogen	50 – 75 kg per hectare

Phosphoric Acid	112 – 165 kg per hectare

Potassium		121 – 200 kg per hectare

SECTION 727

SOIL STABILIZATION MATERIAL

Special Provisions

727-2.01 MULCH. Delete numbered item 1. in its entirety and substitute the following:

- Virgin/Recycled Wood Fiber, Paper Cellulose Fiber Mulch, or Blended Wood-Paper Mulch.

Mulch shall consist of specially prepared wood fiber processed to contain no growth or germination inhibiting factors. The mulch shall be manufactured and processed in such a manner that the fibers will remain in uniform suspension in water under agitation and will blend with grass seed, fertilizer and other additives to form a homogeneous slurry. The mulch shall be of a texture such that it can be applied uniformly to the soil surface. Mulch shall not create a hard crust upon drying and it shall have moisture absorption and retention properties as well as the ability to hold grass seed in contact with the soil.

The mulch shall be shipped in packages of uniform weight (plus or minus 5%) bearing the name of the manufacturer and the air-dry weight content.

The mulch shall be dyed a suitable color to facilitate inspection of the placement of the material.

A commercial tackifier shall be used on all seeded areas where mulch is applied. The amount added will be as recommended by the manufacturer.

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B. (2/29/00)R81M

Standard Modifications

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

#### Special Provisions

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the Plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this subsection.

(2/29/00)R81M

APPENDIX A

PERMITS AND ESCP

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

APPENDIX D

SIGN SHOP DRAWINGS