SPECIAL NOTICE TO BIDDERS

The Department hereby notifies bidders that information to assist in preparing bids is available at 4111 Aviation Avenue for the following:

1.	These items are available upon request in the Anchorage Department of Transportation and Public Facilities Building Plans Room:

a.	Quantity Computations

b.	State of Alaska Department of Transportation and Public Facilities publications, Best Management Practices for Construction Erosion and Sediment Control and Maintenance and Operations Activities and Alaska Storm Water Pollution Prevention Plan Guide, effective October, 2001.

c.	Department of Transportation and Public Facilities - Sign Face Fabrication Requirements

d.	Standard Specifications for Highway Construction 1998 Metric. ($25.00)

2.	Utility agreements pertaining to the disposition of all utility facilities on this project are available for review at the office of the Utilities Engineer, (907) 269-0647.

3.	The Department has approved environmental documents addressing concerns and environmental commitments.  They are available for review in the office of the Preliminary Design and Environmental Coordinator, (907) 269-0534.

4.	The Materials Certification List (MCL) has been included in Appendix C.  This list is provided for the Contractor to determine which materials will require submittal to the Project Engineer for certification of compliance.  The MCL also provides the Project Engineer with the appropriate approving authority.

5.	The CPM schedule submittal requirements have changed.  See Section 646, CPM SCHEDULING of the Special Provisions for details.

6.	Unless directed otherwise by the Engineer, only culvert installation and removal work will be allowed during 2002 for Hatcher Pass and Gold Chord Roads (base course and paving work shall be done in 2003 without the written approval of the Engineer).  Do not interrupt the Contractor on the Hatcher Pass Road Milepost 7 to 14 project.

PART 4

STANDARD MODIFICATIONS

AND SPECIAL PROVISIONS

to the

STATE OF ALASKA

SPECIFICATIONS

FOR

HIGHWAY CONSTRUCTION

(METRIC)

98M

SECTION 101

DEFINITIONS AND TERMS

## Standard Modifications

101-1.03 DEFINITIONS. Add the following:

Interim Work Authorization. A written order by the Engineer initiating changes to the Contract, within its general scope, until a subsequent Change Order is executed. (06/25/99)M 68

## Special Provisions

101-1.03 DEFINITIONS. Add the following definition:

NON-FROST SUSCEPTIBLE. Material that contains 6 percent or less passing the 0.075 mm  screen as determined by sieve analysis performed with WAQTC FOP for AASHTO T 27/T 11 on minus 75 mm  material. (11/29/01)R1M98

SECTION 102

BIDDING REQUIREMENTS AND CONDITIONS

# Special Provisions

102-1.11 ADDENDA REQUIREMENTS. Delete this Subsection in its entirety and substitute the following: Addenda will be issued to the individual or company to whom bidding documents were issued. Addenda may be issued by any reasonable method such as hand delivery, mail, telefacsimile, telegraph, courier, and in special circumstances by phone. Addenda will be issued to the address, telefacsimile number or phone number as stated on the planholder's list unless picked up in person or included with the bid documents. It is the bidder's responsibility to insure that he has received all addenda affecting the Invitation For Bids. No claim or protest will be allowed based on the bidder's allegation that he did not receive all of the addenda for an Invitation For Bids.

All addenda shall be acknowledged on the Proposal or by telegram or telefacsimile prior to the scheduled time of bid opening. If no addenda are received by the bidder, the word "None" should be entered on the Proposal Form. (2/1/00)R171M98

SECTION 103

AWARD AND EXECUTION OF CONTRACT

Standard Modifications

103-1.01 CONSIDERATION OF BIDS.  Add the following after item 9.: In addition to the circumstances described above, the Contractor may request permission from the Contracting Officer to add or replace a listed subcontractor. The request must be made in advance, in writing, specifically detailing the basis for the request, and shall include appropriate supporting documentation. The Contracting Officer will approve the request if it is determined to be in the best interest of the State. (10/28/99) M 84

103-1.02 AWARD OF CONTRACT.  In the third paragraph, change “practical” to “practicable”. (06/25/99)M 69

SECTION 105

CONTROL OF WORK

### Standard Modifications

105-1.02 PLANS AND WORKING DRAWINGS.  Replace the fifth paragraph with the following:

Upon receipt of an approved copy of the shop working drawings, the Contractor shall furnish to the Engineer:

1.	Enough additional copies to provide 8 approved sets of prints.

2.	One set of reproducible transparencies (polyester film).

3.	If requested, an electronic file in AutoCAD drawing interchange format (.DXF).

(09/30/99) M 85

Special Provisions

105-1.06 COOPERATION WITH UTILITIES. Add the following: The Contractor shall request locates from all the utilities having facilities in the area. The Contractor shall use the locate Call Center for the following utilities:

Locate Call Center Anchorage Area 278-3121 Statewide 800-478-3121 who will notify the following:

Enstar Natural Gas Matanuska Electric Association Matanuska Telephone Association GCI Cable, Inc.

The Contractor shall call the following utilities and agencies directly:

DOT/PF Maintenance and Operations (Willow)	495-6286

DOT/PF Maintenance and Operations (Palmer)	745-2159

There are various utility appurtenances located within the project limits.  Utilities scheduled for relocation are addressed in the following utility specific sections.  Cooperate with these utilities and coordinate schedule of work to allow them access to the project for their adjustments and/or relocation.

It shall be the responsibility of the Contractor to work around those utilities not designated for relocation in the plans and the following utility specific coordination. Any changes or additional relocation requested for Contractor convenience shall be at the Contractor’s expense.

The Contractor is required to work around all utility facilities, either existing or relocated, throughout the project unless advised by the utility that the facility is abandoned in place.

Any changes in contract scheduling that result in the conditions in this specification not being met shall be the responsibility of the Contractor and additional coordination with the applicable utility will be required.

It is the Contractor’s responsibility to schedule and coordinate the utility relocations with project construction as set forth in Section 108-1.03, Prosecution and Progress.

Right of Way and/or Construction surveying is required of the Contractor prior to utility relocation. Payment to the Contractor will be made as follows:

- Subsidiary to Item 642(1), Construction Surveying, if the Contractor is required to provide the surveying as part of the contract an/or

- Under Item 642(3), Three Person Survey Party, if the construction or Right of Way staking required by the utility is either in advance of the Contractor’s two (2) week work plan, or not required by the contract.

The utility shall give the Contractor, through the Engineer, fifteen  (15) calendar days advance written notice for required staking.

The Contractor will be required to provide the Utility Company’s fifteen (15) calendar days advance written notice of the relocations described below to begin. The utility Company’s will not be required to work in more than one location at a time, and will be allowed to complete a specific section of work prior to commencing with another section.

Relocation or adjustment of underground utility appurtenances will not normally be performed when the ground is frozen.  In addition, the utility companies may prohibit the Contractor, through the Engineer, from working near the utility’s facilities when the ground is frozen.

Specific Coordination requirements for the specific utilities are included below:

Enstar Natural Gas Company (Enstar) owns and operates an underground gas transmission and distribution system through out the project. None of the lines require relocation for this project.

GCI Cable, Inc. (GCI) owns and operates aerial and underground television cables within the project. GCI will relocate one aerial crossing on Cottle Loop Road that conflicts with the new project grade. The Contractor will allow GCI two (2) calendar days to complete this crossing.

Matanuska Electric Association, Inc. (MEA) has existing overhead electric lines throughout the project. MEA will relocate several aerial crossings to accommodate the grade changes due to the project. MEA anticipates completing the work prior to construction. However, if any crossings require relocation during construction, the Contractor will allow MEA two (2) calendar days to complete each crossing.

MEA will provide a service connect to the new load center being installed by the Contractor for this project,. After the load center has been installed by the Contractor, and inspected and tagged by the Department of Labor, the Contractor will notify MEA by calling Eric Sanford at 761-9274 to schedule the service connect. The Contractor will allow MEA two (2) calendar days to complete the load center connect.

Matanuska Telephone Association, Inc. (MTA) has underground telephone cables requiring adjustment where they conflict with new culverts and lineal ditching. After the Engineer has determined and staked the culverts and lineal ditching and MTA has performed the underground locates, a determination will be made by the Engineer as to the extent of the underground telephone cables requiring adjustment.  The Contractor will allow MTA five (5) calendar days to complete the work at each required location.

105-1.07 COOPERATION BETWEEN CONTRACTORS. Add the following: The following projects will be under construction concurrently with this project:

Projects:	Hatcher Pass Road Milepost 7 to 14 	Palmer-Wasilla Hwy. Rehabilitation

STP-0001(71) / 51204	STP-044-1(4) / 53921

Owners:	DOT&PF	DOT&PF

Contractors:	Summit Roads

7828 Lake Otis Parkway

Anchorage, AK 99507

Coordinate traffic control and construction with the prime contractor of the above project so as to minimize impact on the travelling public, and to minimize conflicts with the work being performed under the other contract.  (2/1/00)R175M98

105-1.15 PROJECT COMPLETION. Delete the last paragraph and substitute the following: When all physical work and cleanup provided for under the contract is found to be complete, except for work specified under Subsection 618-3.04, Maintenance of Seeded Areas and Subsection 621-3.04, Period of Establishment, a letter of project completion will be issued by the Engineer.  Project completion will relieve the Contractor from further maintenance responsibilities, except under Subsections 618-3.04 and 621-3.04 and will stop the count of contract time but will not relieve him of any obligations under the Contract. (7/30/99)R237M98

### Standard Modification

105-1.17 CLAIMS FOR ADJUSTMENT AND DISPUTES.  Delete this Subsection in its entirety and substitute the following:

Notify the Engineer as soon as you become aware of any act or occurrence which may form the basis of a claim for additional compensation or an extension of Contract time or of any dispute regarding a question of fact or interpretation of the Contract.

If the matter is not resolved by agreement within 7 days, submit any Intent to Claim, in writing, within the next 14 days.

If you believe additional compensation or time is warranted, immediately begin keeping complete, accurate, and specific daily records concerning every detail of the potential claim including actual costs incurred.  Give the Engineer access to any such records and furnish the Engineer copies, if requested.  Equipment costs must be based on your internal rates for ownership, depreciation, and operation expenses and not on published rental rates.

Submit any Claim to the Contracting Officer, in writing, within 90 days of the act or occurrence forming the basis of the claim.  The Contracting Officer will acknowledge receipt of the Claim in writing.

You waive any right to claim if the Engineer was not notified properly or afforded the opportunity to inspect conditions or monitor actual costs.

The Claim must include all of the following:

- The act, event, or condition the claim is based on.

- The Contract provisions which apply to the claim and provide relief.

- The item or items of Contract work affected and how they are affected.

- The specific relief requested, including Contract time if applicable, and the basis upon which it was calculated.

- A statement certifying that the claim is made in good faith, that the supporting cost and pricing data are accurate and complete to the best of your knowledge and belief, and that the amount requested accurately reflects the Contract adjustment which you believe is due.

The Claim, in order to be valid, must not only show that you suffered damages or delay but that it was caused by the act, event, or condition complained of and that the Contract provides entitlement to relief for such act, event, or condition.

The Department can make written request to you at any time for additional information relative to the Claim.  Provide the Department such additional information within 30 days of receipt of such a request.  Failure to furnish such information may be regarded as a waiver of the Claim.

You will be furnished the Contracting Officer’s Decision within 90 days, unless additional information is requested by the Contracting Officer.  The Contracting Officer’s Decision is final and conclusive unless, within 14 days of receipt of the decision, you deliver a Notice of Appeal to the Appeals Officer.  Procedures for appeals are covered under AS 36.30.625 and AS 36.30.630.  (03/26/01) M 101

Special Provisions

Add the following Any appeal to the superior court under AS 36.30.685 must be filed in the third judicial district. (3/21/01)R93

SECTION 106

CONTROL OF MATERIAL

## Special Provisions

106-1.01 Source of Supply and Quality Requirements.  Add the following:

Buy America Provision. The Contractor shall comply with the requirements of 23 CFR 635.410, Buy America Requirements, and shall submit a completed Material Origin Certificate, Form 25D-60, prior to award of the contract.

All steel and iron products which are incorporated into the work, shall be manufactured in the United States except that minor amounts of steel and iron products of foreign manufacture may be used, provided the aggregate cost of such does not exceed one tenth of one percent (0.001) of the total contract amount, or $2500, whichever is greater. For the purposes of this paragraph, the cost is the value of the products as they are delivered to the project including freight.

“Manufactured in the United States” means that all manufacturing processes starting with the initial mixing and melting through the final shaping, welding, and coating processes must be undertaken in the United States. The definition of “manufacturing process” is smelting or any subsequent process that alters the material’s physical form, shape or chemical composition. These processes include rolling, extruding, machining, bending, grinding, drilling, etc. The application of coatings, such as epoxy coating, galvanizing, painting or any other coating that protects or enhances the value of steel or iron materials shall also be considered a manufacturing process subject to the “Buy America Requirements.”

Buy America does not apply to raw materials (iron ore), pig iron, and processed, pelletized and reduced iron ore. It also does not apply to temporary steel items (e.g., temporary sheet piling, temporary bridges, steel scaffolding, and falsework). Further, it does not apply to materials that remain in place at the Contractor’s convenience (e.g., sheet pilings, and forms).

The North American Free Trade Agreement (NAFTA) does not apply to the Buy America requirement. There is a specific exemption within NAFTA (article 1001) for grant programs such as the Federal-aid highway program.

When steel and iron products manufactured in the United States are shipped to a foreign country where non steel or iron products are installed on or in them (e.g., electronic components in a steel cabinet), the steel and iron is considered to meet the requirements of this Subsection.

The Contractor shall take whatever steps are necessary to ensure that all manufacturing processes for each covered product comply with this provision. Non-conforming products shall be replaced at no expense to the State. Failure to comply may also subject the Contractor to default and/or debarment. False statements may result in criminal penalties prescribed under Title 18 US Code Section 1001 and 1020. (08/31/99)S 13

106-1.02 LOCAL MATERIAL SOURCES.  Add the following under Item 2. Inspection and Acceptance.: In compliance with 30CFR46.11, have the Operator of your sand and gravel surface mine (materials source) provide Site-specific Hazard Awareness Training for all the Engineer’s personnel (non-miners) prior to beginning any operations in your surface mine.  Offer the training at each surface mine that you will be using to supply processed aggregates.  A competent person must provide the training in accordance with the Operator’s written training plan as approved by the Mine Safety and Health Administration, and covering the following items:

- Site specific health and safety risks.

- Recognition and avoidance of hazards.

- Restricted areas.

- Warning and evacuation signals.

- Other special safety procedures.

- Site tour.

Upon completion of this training, the Engineer’s personnel will sign a Visitor’s Log Book to indicate that training was provided.  (5/7/01)R262M98

SECTION 107

LEGAL RELATIONS AND RESPONSIBILITY TO PUBLIC

# Special Provisions

107-1.02 PERMITS, LICENSES AND TAXES. Add the following: Obtain a written statement from the State Historic Preservation Officer stating that material disposal, extraction, stockpiling or staging, on any off project site, is not expected to impact any cultural resources. The State Historic Preservation Officer is with the Department of Natural Resources in Anchorage, and may be contacted at (907) 269-8715. If the Contractor discovers cultural resources during construction activities, stop work at that site and notify the Engineer.

Provide a wetland specialist able to conduct wetlands determinations and delineations in accordance with the Corps of Engineers 1987 Wetland Delineation Manual.  The wetland specialist shall conduct the determination and delineations of any site outside the project limits or not previously permitted, impacted by the Contractor's operations. These delineations will be subject to Corps of Engineers approval.

Provide the Engineer a copy of all permits or clearances received prior to using any site outside the project limits. Additionally, provide the Engineer a written statement that all necessary permits or clearances have been obtained. Also provide a written statement to the Engineer listing agencies or offices contacted which responded that no additional action is required.

Add the following: The Department has received the following permits on the Contractor's behalf:

1.	Department of the Army, Corps of Engineers, Nationwide Permit 3, No. D-2001-0770, dated July 3, 2001, expires February 11, 2002.

2.	Alaska Department of Fish and Game, Title 16 Permit No. FG01-II-0361, dated June 25, 2001, expires July 15, 2002.

3.	Alaska Department of Fish and Game, Title 16 Permit No. FG01-II-0359, dated June 25, 2001, expires July 15, 2002.

Copies of the permits are located in Appendix A.

107-1.11 PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE. Add the following: If the Contractor requires water for any construction purpose from a non-municipal water source, the Contractor shall obtain a Temporary Water Use Permit from the Water Resource Manager, and provide a copy to the Engineer. The Water Resource Manager is with the Department of Natural Resources in Anchorage and may be contacted at (907) 269-8624. (5/21/01)R7M98

107-1.16 CONTRACTOR'S RESPONSIBILITY FOR UTILITY PROPERTY AND SERVICE.

Add the following before the last paragraph: Where the Contractor's operations meet any of the following conditions, the Contractor shall advise the owning Utility in writing at least 24 hours in advance of the work.

1.	Operations anticipated being within 3 m of an overhead electrical line.

2.	Operations anticipated to be within 0.9 m of an underground electrical line according to locates provided by the owning Utility.

3.	Operations requiring use of equipment which is capable of coming within 3 m of an overhead electrical line.

The notice shall indicate the location and duration of the work.

The Contractor shall provide an attendant whose sole responsibility is to perform as a safety observer while equipment is operating such that any part is capable of reaching within 4.6 m (15 feet) of an overhead line.

Providing a safety observer for overhead electrical facilities, or a cable watch for buried electrical facilities, will be subsidiary to the item(s) of work being performed requiring these services.

(7/30/99)R170M98

Add the following Subsections:

107-1.22 FEDERAL AFFIRMATIVE ACTION. The Federal Equal Employment Opportunity, Disadvantaged Business Enterprise, and On-the-Job Training affirmative action program requirements that are applicable to this Contract are contained in the project Special Provisions and Contract Forms, and may include:

Disadvantaged Business Enterprise (DBE) Program			Section 120

Training Program							Section 645

Federal EEO Bid Conditions						Form 25A-301

EEO-1 Certification							Form 25A-304

DBE Subcontractable Items						Form 25A-324

ADOT&PF Training Program Request				Form 25A-310

Training Utilization Report						Form 25A-311

Contact Report							Form 25A-321A

DBE Utilization Report						Form 25A-325C

Summary of Good Faith Effort Documentation			Form 25A-332A

Required Contract Provisions, Federal-Aid Contracts		Form 25D-55

In addition to the sanctions provided in the above references, non-compliance with these requirements is grounds for withholding of progress payments. (09/11/01)S80

SECTION 108

PROSECUTION AND PROGRESS

# Standard Modifications

108-1.01 SUBLETTING OF CONTRACT.  Delete the last paragraph under Item 4. and add the following to Item 5.:

The Contractor shall ensure that the required prompt payment provisions of AS 36.90.210 are included in all subcontracts. (10/28/99) M 70

## Special Provisions

108-1.03 PROSECUTION IN PROGRESS. Add the following under item no. 1: Use the schedule for coordination and monitoring of all work under the contract including all activity of subcontractors, manufacturers, suppliers, utility companies and review activity of the Department. (4/22/99)R250M98

Delete Items 5 of the first paragraph and substitute the following:

- The submittals identified under Subsection 641-1.02, Temporary Erosion and Pollution Control Plan.

(5/16/00)R160M98

108-1.04  LIMITATION OF OPERATIONS.  Add the following:  No work, except for culvert removal and installation, will be allowed on Hatcher Pass and Gold Chord Roads until May 1, 2003, unless approved in writing by the Engineer.

108-1.06 DETERMINATION AND EXTENSION OF CONTRACT TIME. Delete the 2nd paragraph under item 3 “Suspension and Extension of Contract Time,” and substitute the following:  The count of Contract time shall continue through the suspension of work in the following conditions:

- those instances where the Engineer orders suspension of the work for unsafe conditions,

- for failure by the Contractor to carry out contractual provisions, or

- for failure to carry out orders given by the Engineer within the limits of his contractual authority.

In the instance where the Engineer suspends a controlling item of work due to adverse weather conditions for one or more calendar days, the number of days included in the suspension period shall extend the completion date.

(2/15/01)R242M98

108-1.07 FAILURE TO COMPLETE ON TIME. Add the following to the first paragraph:  Failure to meet the interim completion dates will result in a daily charge for liquidated damages of $1,500 for each calendar day of delay.

Add the following Subsection:

108-1.11 INTERIM COMPLETION DATES.  This project has two interim completion dates.

Complete all culvert work on Hatcher Pass Road and Gold Chord Road by August 31, 2002.

Complete all work on all roads, except for Hatcher Pass Road and Gold Chord Road, by October 15, 2002.

SECTION 109

MEASUREMENT AND PAYMENT

Standard Modifications

109-1.05 COMPENSATION FOR EXTRA WORK. Under item 1. Labor: Delete “(supported by proof of rates)”.

Delete paragraph d., and substitute the following:

d.	plus Workers’ Compensation at 8% of a. The actual net rate will be used only when it exceeds 10% and when proof of rates are submitted within 30 days of the completion of the extra work. (5/31/00)M90

Replace subparagraphs e. and f., with the following:

e.	plus either subsistence and travel allowances, or prorated camp costs

f.	plus 35% of the sum of a, c, d, and e. (02/08/01)M71

## Special Provisions

Under item 3, Equipment, change the first sentence to read ..."Rental Rate Blue Book for Construction Equipment", published by Primedia, 1735 Technology Drive, Suite 410, San Jose, CA 95110-1313.

Under item 3, Equipment, add the following to the second paragraph: The rental rate area adjustment factors for this project shall be as specified on the adjustment maps for the Alaska - South Region. (1/27/00)R14

###### Standard Modifications

Delete item 5. and substitute the following:

5.	Work by a Subcontractor. The Contractor will receive a 5% markup on the total time and materials work defined in 1 through 4 above which is performed by an approved subcontractor or owner-operator. This markup will be for administrative expenses incurred in connection with the work. No percentage will be paid on work covered under bid items in the original Contract. No percentage over the amount covered above will be paid if a lower tier subcontractor does the work. (02/08/01)M71

109-1.06 PROGRESS PAYMENTS. Add the following: Failure to submit schedules in accordance with Subsection 108-1.03, Prosecution and Progress, will result in withholding an amount equal to 5 percent of the total amount earned from all subsequent progress payments. The Engineer, upon receipt of current schedules from the Contractor, will release this amount. (09/05/01)R137

###### Add the following Section:

SECTION 120

DISADVANTAGED BUSINESS ENTERPRISE (DBE) PROGRAM

120-1.01 DESCRIPTION. The work consists of providing Disadvantaged Business Enterprises (DBEs), as defined in Title 49, CFR (Code of Federal Regulations), Part 26, with the opportunity to participate on an equitable basis with other contractors in the performance of contracts financed in whole, or in part, with federal funds. The Contractor or subcontractor shall not discriminate on the basis of race, color, national origin, or sex in the performance of this contract. The Contractor shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of USDOT assisted contracts.

120-1.02 INTERPRETATION. It is the intent of this section to implement the requirements of 49 CFR, Part 26, and the Department's federally approved DBE Program.

120-1.03 ESSENTIAL CONTRACT PROVISION. Failure to comply with the provisions of this section will be considered a material breach of contract, which may result in the termination of this contract or such other remedy as ADOT&PF deems appropriate. The Department also considers failure to comply with this section to be so serious as to justify debarment action as provided in AS 36.30.640(4).

120-1.04 DEFINITIONS AND TERMS. The following definitions will apply.

- Broker. A DBE certified by the Department that arranges for the delivery or provision of creditable materials, supplies, equipment, transportation/hauling, insurance, bonding, etc., within its certified category, that is necessary for the completion of the project. A broker of materials certified in a supply category must be responsible for scheduling the delivery of materials and fully responsible for ensuring that the materials meet specifications before credit will be given.

- Commercially Useful Function (CUF). The execution of the work of the Contract by a DBE carrying out its responsibilities by actually performing, managing, and supervising the work involved using its own employees and equipment. The DBE shall be responsible, with respect to materials and supplies used on the Contract, for negotiating price, determining quality and quantity, ordering the material, and installing (where applicable) and paying for the material itself. To determine whether a DBE is performing a commercially useful function, an evaluation of the amount of work subcontracted, industry practices, whether the amount the firm is to be paid under the Contract is commensurate with the work it is actually performing and the DBE credit claimed for its performance of the work. Other relevant factors will be considered. The Engineer makes the determination of CUF after evaluating the way in which the work was performed during the execution of the Contract.

- Disadvantaged Business Enterprise (DBE). An enterprise which is a for-profit small business concern

- that is at least 51 percent owned by one or more individuals who are both socially and economically disadvantaged or, in the case of a corporation, in which 51 percent of the stock is owned by one or more such individuals;

- whose management and daily business operations are controlled by one or more of the socially and economically disadvantaged individuals who own it; and

- has been certified by the Department in accordance with 49 CFR, Part 26.

- DBE Key Employee. Permanent employees identified by the DBE owner in its certification file in the Department Civil Rights Office.

- DBE Utilization Goal. The percent of work to be performed by certified DBEs that is established by the Department and specified in the Contract.

- Good Faith Efforts. Efforts by the bidder or Contractor to achieve a DBE goal or other requirement of 49 CFR Part 26, by their scope, intensity, and appropriateness to the objective, that can reasonably be expected to fulfill the program requirement.

- Manufacturer. A DBE certified by the Department in a supply category that changes the shape, form, or composition of original material in some way and then provides that altered material to the project and to the general public or the construction industry at large on a regular basis.

- Notification. For purposes of soliciting DBE participation on a project and to count toward a contractor’s Good Faith Efforts, notification shall be by letter or fax transmission, with a return receipt requested or successful transmission report. Telephonic contact with a DBE may be allowed, however it shall be based on the ability of Civil Rights staff to independently verify this contact.

- Regular Dealer. A DBE certified by the Department in a supply category that

- maintains an in-house inventory on a regular basis of the particular product provided to this project; and

- keeps an inventory in an amount appropriate for the type of work using that product; and

- offers that inventory for sale to the general public or construction industry at large (private and public sectors), not just supplied as needed on a project by project basis during the construction season, except where the product requires special or heavy equipment for delivery and the DBE possesses and operates this equipment on a regular basis throughout the construction season in order to deliver the product to the general public or construction industry at large. If the distribution equipment is rented or leased, it must be on a repetitive, seasonal basis; and may additionally

- fabricate (assembles large components) for use on a construction project, consistent with standard industry practice, for delivery to the project.

120-2.01 UTILIZATION GOAL. The DBE Utilization Goal for this contract is shown on Form 25A324 (DBE Subcontractable Items) as a percentage of the total basic bid amount. A DBE may be considered creditable towards meeting the DBE Utilization Goal at time of Contract award, if the DBE is certified by the Department in a category covering the CUF to be performed at the time of listing on Form 25A325C (DBE Utilization Report).

A bidder shall demonstrate the ability to meet the DBE Utilization Goal or perform and document all of the required Good Faith Efforts under Subsection 120-3.02 in order to be eligible for award of this Contract.

If the Department reduces the quantity of work of a bid item involving a DBE firm, the DBE Utilization Goal on Form 25A325C will be reduced proportionately.

120-3.01 DETERMINATION OF COMPLIANCE

- Phase I - Bid. Each bidder must register with the Civil Rights Office annually in accordance with §§26.11 & 26.53(b)(2)(iv) of 49 CFR, Part 26.  No contract may be awarded to a bidder that is not registered.

- Phase II - Award. The apparent low bidder will provide the following within 15 days of receipt of notice of intent to award:

- Written DBE Commitment. Written commitments from DBEs to be used on the project. The written commitment shall contain the following information:

- A description of the work that each DBE will perform;

- The dollar amount of participation by the DBE firm;

- Written documentation of the bidder/offeror’s commitment to use a DBE subcontractor whose participation it submits to meet a contract goal; and

- Written confirmation from the DBE that it is participating in the contract as provided in the prime Contractor’s commitment.

- DBE Utilization Report. Form 25A325C listing the certified DBEs to be used to meet the DBE Utilization Goal.

- Good Faith Effort Documentation. Summary of Good Faith Effort Documentation (Form 25A332A and attachments) and DBE Contact Reports (Form 25A321A) if the Contractor submits less DBE utilization on Form 25A325C than is required to meet the DBE Utilization Goal. If accepted by the Department, this lower DBE utilization becomes the new DBE Utilization Goal. If the bidder cannot demonstrate the ability to meet the DBE Utilization Goal, and can not document the minimum required Good Faith Efforts (as outlined in Subsection 120-3.02 below), the Contracting Officer will determine the bidder to be not responsible.

- Phase III - Construction.

- Designation of DBE/EEO Officer. At the preconstruction conference, the Contractor shall submit, in writing, the designation of a DBE/EEO officer.

- DBE Creditable Work. The CUF work items and creditable dollar amounts shown for a DBE on the DBE Utilization Report (Form 25A325C) shall be included in any subcontract, purchase order or service agreement with that DBE.

- DBE Replacement. If the Engineer approves a DBE replacement, the Contractor shall replace the DBE with another DBE for the same work in order to fulfill its commitment under the DBE Utilization Goal. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer and the Civil Rights Office, both of the following criteria have been met:

- The Contractor has not committed any discriminatory practice in its exercise of good business judgement to replace a DBE.

- If the Contractor is unable to find replacement DBE participation and has adequately performed and documented the Good Faith Effort expended in accordance with Subsection 120-3.02.

- DBE Utilization Goal. The DBE Utilization Goal will be adjusted to reflect only that amount of the DBE's work that can not be replaced.

120-3.02 GOOD FAITH EFFORT

- Good Faith Effort Criteria. The Contracting Officer will use the following criteria to judge if the bidder, who has not met the DBE Utilization Goal, has demonstrated sufficient Good Faith Effort to be eligible for award of the contract.

Failure by the bidder to perform and document all of the following actions constitutes insufficient Good Faith Effort.

- Consideration of all subcontractable items. The bidder shall, at a minimum, seek DBE participation for each of the subcontractable items upon which the DBE goal was established as identified by the Department (on Form 25A324) prior to bid opening. It is the bidder’s responsibility to make the work listed on the subcontractable items list available to DBE firms, to facilitate DBE participation.

- If the bidder can not achieve the DBE Utilization Goal using the list of available DBE firms based on the subcontractable items list, then the bidder may consider other items that could be subcontracted to DBEs.

- Notification to all active DBEs listed for a given region in the Department's most current DBE Directory at least 7 calendar days prior to bid opening. The bidder must give the DBEs no less than five days to respond. The bidder may reject DBE quotes received after the deadline. Such a deadline for bid submission by DBEs will be consistently applied. DBEs certified to perform work items identified on Form 25A324 must be contacted to solicit their interest in participating in the execution of work with the Contractor. Each contact with a DBE firm will be logged on a Contact Report (Form 25A321A).

- Non-competitive DBE quotes may be rejected by the bidder. Allegations of non-competitive DBE quotes must be documented and verifiable. A DBE quote that is more than 10.0% higher than the accepted non-DBE quote will be deemed non-competitive, provided the DBE and non-DBE subcontractor quotes are for the exact same work or service. Bidders must have a non-DBE subcontractor quote for comparison purposes. Such evidence shall be provided in support of the bidder’s allegation. Where the bidder rejects a DBE quote as being non-competitive under this condition, the work must be performed by the non-DBE subcontractor and payments received by the non-DBE subcontractor during the execution of the Contract shall be consistent with the non-DBE's accepted quote. This does not preclude increases as a result of Change documents issued by the Department.

- Provision of assistance to DBEs who need help in obtaining information about bonding or insurance required by the bidder.

- Provision of assistance to DBEs who need help in obtaining information about securing equipment, supplies, materials, or related assistance or services.

- Providing prospective DBEs with adequate information about the requirements of the Contract regarding the specific item of work or service sought from the DBE.

- Follow-up of initial notifications by contacting DBEs to determine whether or not they will be bidding. Failure to submit a bid by the project bid opening or deadline by the bidder is de facto evidence of the DBE’s lack of interest in bidding. Documentation of follow-up contacts shall be logged on the Contact Report (Form 25A321A).

- Items c through h will be utilized to evaluate any request from the Contractor for a reduction in the DBE Utilization Goal due to the default or decertification of a DBE and the Contractor's subsequent inability to obtain additional DBE participation.

- Administrative Reconsideration. Under the provisions of 49 CFR. Part 26.53(d), if it is determined that the apparent successful bidder has failed to meet the requirements of this Subsection, the bidder must indicate whether they would like an opportunity for administrative reconsideration. The bidder must exercise such an opportunity within 3 calendar days of notification it has failed to meet the requirements of this Subsection. As part of this reconsideration, the bidder must provide written documentation or argument concerning the issue of whether it met the goal or made adequate good faith efforts to do so.

- The DBE Liaison Officer will make the decision on reconsideration.

- The bidder will have the opportunity to meet in person with the DBE Liaison Officer to discuss the issue of whether it met the goal or made adequate good faith efforts to do so. If a meeting is desired, the bidder must be ready, willing and able to meet with the DBE Liaison Officer within 4 days of notification that it has failed to meet the requirements of this Subsection.

- The DBE Liaison Officer will render a written decision on reconsideration and provide notification to the bidder. The written decision will explain the basis for finding that the bidder did or did not meet the goal or make adequate good faith efforts to do so.

- The result of the reconsideration process is not administratively appealable to US DOT.

120-3.03 COMMERCIALLY USEFUL FUNCTION (CUF).

- Creditable Work. Measurement of attainment of the DBE Utilization Goal will be based upon the actual amount of money received by the DBEs for creditable CUF work on this project as determined by the Engineer in accordance with this Section. CUF is limited to that of a:

- regular dealer;

- manufacturer;

- broker;

- subcontractor;

- joint-venture; or

- prime contractor.

- Determination of Commercially Useful Function. In order for the CUF work of the DBE to be credited toward the goal, the Contractor will ensure that all of the following requirements are met:

- The CUF performed by a DBE certified in a supply category will be evaluated by the Engineer to determine whether the DBE performed as either a broker, regular dealer, or manufacturer of the product provided to this project.

- A DBE trucking firm certified and performing work in a transportation/hauling category is restricted to credit for work performed with its own trucks and personnel certified with the CRO prior to submitting a bid to a contractor for DBE trucking. The DBE trucking firm must demonstrate that it owns all trucks (proof of title and/or registration) to be credited for work and that all operators are employed by the DBE trucking firm. A DBE trucking firm that does not certify its trucks and personnel that it employs on a job will be considered a broker of trucking services and limited to credit for a broker. (This does not effect the CUF of that same firm, when performance includes the hauling of materials for that work.)

- The DBE is certified in the appropriate category at the time of

- the Engineer's approval of the DBE subcontract, consistent with the written DBE commitment; and

- the issuance of a purchase order or service agreement by the Contractor to a DBE performing as either a manufacturer, regular dealer, or broker (with a copy to the Engineer).

- The Contractor will receive credit for the CUF performed by DBEs as provided in this Section. Contractors are encouraged to contact the Engineer in advance of the execution of the DBE's work or provision of goods or services regarding CUF and potential DBE credit.

- The DBE may perform work in categories for which it is not certified, but only work performed in the DBE's certified category meeting the CUF criteria may be credited toward the DBE Utilization Goal.

- The work of the DBE firm must meet the following criteria when determining when CUF is being performed by the DBE:

- The work performed will be necessary and useful work required for the execution of the Contract.

- The scope of work will be distinct and identifiable with specific contract items of work, bonding, or insurance requirements.

- The work will be performed, controlled, managed, and supervised by employees normally employed by and under the control of the certified DBE. The work will be performed with the DBE’s own equipment. Either the DBE owner or DBE key employee will be at the work site and responsible for the work.

- The manner in which the work is sublet or performed will conform to standard, statewide industry practice within Alaska, as determined by the Department. The work or provision of goods or services will have a market outside of the DBE program (must also be performed by non-DBE firms within the Alaskan construction industry). Otherwise, the work or service will be deemed an unnecessary step in the contracting or purchasing process and no DBE credit will be allowed.

There will be no DBE credit for lower-tier non-DBE subcontract work.

- The cost of the goods and services will be reasonable and competitive with the cost of the goods and services outside the DBE program within Alaska. Materials or supplies needed as a regular course of the Contractor's operations such as fuel, maintenance, office facilities, portable bathrooms, etc. are not creditable.

The cost of materials actually incorporated into the project by a DBE subcontractor is creditable toward the DBE goal only if the DBE is responsible for ordering and scheduling the delivery of creditable materials and fully responsible for ensuring that the materials meet specifications.

- All subcontract work, with the exception of truck hauling, will be sublet by the same unit of measure as is contained in the Bid Schedule unless prior written approval of the Engineer is obtained.

- The DBE will control all business administration, accounting, billing, and payment transactions. The prime contractor will not perform the business, accounting, billing, and similar functions of the DBE. The Engineer may, in accordance with AS 36.30.420(b), inspect the offices of the DBE and audit the records of the DBE to assure compliance.

- On a monthly basis, the Contractor shall report on Form 25A336 (Monthly Summary of DBE Participation) to the Department Civil Rights Office the payments made (canceled checks or bank statements that identify payor, payee, and amount of transfer) for the qualifying work, goods and services provided by DBEs.

- Decertification of a DBE. Should a DBE performing a CUF become decertified during the term of the subcontract, purchase order, or service agreement for reasons beyond the control of and without the fault or negligence of the Contractor, the work remaining under the subcontract, purchase order, or service agreement may be credited toward the DBE Utilization Goal.

Should the DBE be decertified between the time of Contract award and the time of the Engineer's subcontract approval or issuance of a purchase order or service agreement, the work of the decertified firm will not be credited toward the DBE Utilization Goal. The Contractor must still meet the DBE Utilization Goal by either

- withdrawing the subcontract, purchase order or service agreement from the decertified DBE and expending Good Faith Effort (Subsection 120-3.02, Items c through h) to replace it with one from a currently certified DBE for that same work or service through subcontractor substitution (Subsection 103-1.01); or

- continuing with the subcontract, purchase order or service agreement with the decertified firm and expending Good Faith Effort to find other work not already subcontracted out to DBEs in an amount to meet the DBE Utilization Goal through either

- increasing the participation of other DBEs on the project;

- documenting Good Faith Efforts (Subsection 120-3.02, items c through h); or

- by a combination of the above.

- DBE Rebuttal of a Finding of no CUF. Consistent with the provisions of 49 CFR, Part 26.55(c)(4)&(5), before the Engineer makes a final finding that no CUF has been performed by a DBE firm the Engineer will coordinate notification of the presumptive finding through the Civil Rights Office to the Contractor, who will notify the DBE firm.

The Engineer, in cooperation with the Civil Rights Office, may determine that the firm is performing a CUF if the rebuttal information convincingly demonstrates the type of work involved and normal industry practices establishes a CUF was performed by the DBE. Under no circumstances shall the Contractor take any action against the DBE firm until the Engineer has made a final determination. The Engineer’s decisions on CUF matters are not administratively appealable to US DOT.

120-3.04 DEFAULT OF DBE. In the event that a DBE firm under contract or to whom a purchase order or similar agreement has been issued defaults on their work for whatever reason, the Contractor shall immediately notify the Engineer of the default and the circumstances surrounding the default.

The Contractor shall take immediate steps, without any order or direction from the Engineer, to retain the services of other DBEs to perform the defaulted work. In the event that the Contractor cannot obtain replacement DBE participation, the Engineer may adjust the DBE Utilization Goal if, in the opinion of the Engineer, the following criteria have been met:

1.	The Contractor was not at fault or negligent in the default and that the circumstances surrounding the default were beyond the control of the Contractor; and

- The Contractor is unable to find replacement DBE participation at the same level of DBE commitment and has adequately performed and documented the Good Faith Effort expended in accordance with items c through h of Subsection 120-3.02 for the defaulted work; or

- It is too late in the project to provide any real subcontracting opportunities remaining for DBEs.

The DBE Utilization Goal will be adjusted to reflect only that amount of the defaulted DBE's work that can not be replaced.

120-4.01 METHOD OF MEASUREMENT. The Contractor will be entitled to count toward the DBE Utilization Goal those monies actually paid to certified DBEs for CUF work performed by the DBE as determined by the Engineer. The Contractor will receive credit for the utilization of the DBEs, as follows:

- Credit for the CUF of a DBE prime contractor is 100% of the monies actually paid to the DBE under the contract for creditable work and materials in accordance with 49 CFR 26.55.

- Credit for the CUF of a subcontractor is 100% of the monies actually paid to the DBE under the subcontract for creditable work and materials. This shall include DBE trucking firms certified as a subcontractor and not a broker. Trucks leased from another DBE firm shall also qualify for credit and conforms to the provisions of 49 CFR 26.55(d).

- Credit for the CUF of a manufacturer is 100% of the monies paid to the DBE for the creditable materials manufactured.

- Credit for the CUF of a regular dealer of a creditable material, product, or supply is 60% of its value. The value will be the actual cost paid to the DBE but will not exceed the bid price for the item.

- Credit for the CUF of a broker performed by a DBE certified in a supply category for providing a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the procurement contract for the creditable item.

- Credit for the CUF of a broker performed by a DBE certified in the transportation/hauling category for arranging for the delivery of a creditable material, product or supply is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the cost of the hauling subcontract.

- Credit for the CUF of a broker performed by a DBE certified in a bonding or insurance category for arranging for the provision of insurance or bonding is limited to a reasonable brokerage fee. The brokerage fee will not exceed 5% of the premium cost.

- Credit for the CUF of a joint venture (JV) (either as the prime contractor or as a subcontractor) may not exceed the percent of the DBE's participation in the joint venture agreement, as certified for this project by the Department. The DBE joint venture partner will be responsible for performing all of the work as delineated in the certified JV agreement.

120-5.01 BASIS OF PAYMENT. Work under this item is subsidiary to other contract items and no payment will be made for meeting or exceeding the DBE Utilization Goal.

If the Contractor fails to utilize the DBEs listed on Form 25A325C as scheduled or fails to submit required documentation to verify proof of payment or documentation requested by the Department to help in the determination of CUF, the Department will consider this to be unsatisfactory work. If the Contractor fails to utilize Good Faith Efforts to replace a DBE, regardless of fault (except for Subsection 120-3.04 item 3), the Department will also consider this unsatisfactory work.

Unsatisfactory work may result in disqualification of the Contractor from future bidding under Subsection 102-1.13 and withholding of progress payments consistent with Subsection 109-1.06. (11/17/00)S 33

#### SECTION 201

#### CLEARING AND GRUBBING

Special Provisions

201-1.01 DESCRIPTION. Add the following after the last sentence: Item 201(4C) Hand Clearing will be used to improve sight distance and for cleaning and improving the flow of ditches at areas selected by the Engineer.  Prior to removing trees or limbs, the Engineer will define the Right of Way (R.O.W.) using Item 642(1) Construction Surveying.

201-3.01 METHOD OF MEASUREMENT. Add the following: Item 201(4C) will be measured by the hour as directed by the Engineer.  No clearing outside of the R.O.W. will be required.

201-4.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

201(4C)	Hand Clearing	Hour

SECTION 202

REMOVAL OF STRUCTURES AND OBSTRUCTIONS

#### Special Provisions

202-1.01 DESCRIPTION.  Add the following: This work shall also include the construction of mail box turnouts as shown in the Plans.

202-2.01 MATERIALS.  Add the following:

5.  	Borrow.  Meet the requirements of Section 203.

6.  	Aggregate base course.  Meet the requirements of Section 301

7.  	Asphalt concrete and asphalt cement.  Meet the requirements of Section 401.

(3/29/01)R84M98

202-3.01 GENERAL. Add the following: The construction of mail box installations shall use new posts and mail boxes. Mail boxes shall be United States Postal Service approved, either traditional or contemporary design, having a minimum length of 530 mm, minimum width of 200 mm and minimum height of 270 mm. Existing posts and foundations shall be removed with remaining holes backfilled to the level of surrounding ground. (4/18/00)R74M98

202-3.05 REMOVAL OF PAVEMENT, SIDEWALKS AND CURBS. Add the following: Pavement removed may be used for embankment construction if it is not exposed at the completed embankment surface.  The maximum allowable dimension of the broken asphalt pieces is 150 mm.

Obtain a solid waste disposal permit from DEC or use a site previously approved by DEC for disposal of removed asphalt if not using it in the embankment.  A DEC permitting officer in Anchorage may be contacted at 269-7590.

(3/29/01)R84M98

Add the following Section:

202-3.06 MAIL BOX TURNOUTS.  Construct turnouts for grouped boxes as shown on the Plans and according to these Specifications.

202-4.01 METHOD OF MEASUREMENT.  Add the following: Borrow and Aggregate Base course required to construct Item 202(40), Mail Box Turnouts will not be measured.

Asphalt Concrete and Asphalt Cement required to construct Item 202(40), Mail Box Turnouts will be measured by the megagram.

202-5.01 BASIS OF PAYMENT. Add the following: Item 202(40), Mail Box Turnouts will be paid for at the contract lump sum price.  All work associated with supplying, placing and compacting Borrow and Aggregate Base Course for mail box turnouts is subsidiary to Item 202(40), Mail Box Turnouts and no separate payment shall be made.

Asphalt Concrete and Asphalt Cement required to construct mail box turnouts will be paid under Items 401(1B), Asphalt Concrete, Type II; Class B and 401(2) Asphalt Cement, Grade PG 52-28 respectively.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

202(40)	Mail Box Turnouts	Lump Sum

SECTION 203

EXCAVATION AND EMBANKMENT

Special Provisions

203-1.01 DESCRIPTION. Add the following: Ditch linear grading shall consist of the final shaping of designated ditches and slopes for drainage by grading with a small dozer, motor grader, or other suitable means approved by the Engineer. (9/1/89)R20

203-3.02 EMBANKMENT CONSTRUCTION. On page 88, delete the first sentence of the second paragraph, and substitute the following: Place roadway embankment of earth materials in horizontal layers not exceeding 200 mm in thickness measured before compaction. Each layer of classified material shall have its joint offset from the joint below, longitudinally by 300 mm and transversely by 3 m.

Add the following: Where the plans call for placement of selected material and excavation is required, the existing material may be left in place if tests determine that it will meet the appropriate selected material requirements. Any reduction in excavation or Borrow quantities as a result of this condition shall not constitute a basis for adjustment in contract unit prices except as provided for in Section 104 Scope or Work.

The surface of Selected Material, Type D, shall be compacted by coverage of the Contractor’s placement equipment to provide a smooth and firm slope.  The surface of Selected Material, Type D shall be free of surface irregularities, rutting, slope breaks or unconsolidated material. (2/9/00)R23M98

203-3.03 CONSTRUCTION OF EMBANKMENTS WITH MOISTURE AND DENSITY CONTROL.  Delete this Subsection in its entirety and substitute the following: Construct embankments with moisture and density control from specified materials placed and compacted at approximately their optimum moisture content.  Dry or moisten material as required.

Compact embankment material to not less than 95% of the maximum dry density as determined by WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, or ATM T-12.  The Engineer will determine in-place field densities using ALASKA FOP for AASHTO T 205, or WAQTC TM 7 and WAQTC FOP for AASHTO T 224.

The Engineer will determine the maximum dry density of free-draining, non-plastic, cohesionless materials with less than 10% by weight passing the 0.075-mm sieve using ATM T-12.  (For some materials it may be necessary to perform both ATM T-12 and WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, in which case the highest maximum dry density is used.)  For materials with greater than 80% by weight passing the 4.75 mm sieve, WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method A with the plus 4.75 mm material removed and treated as oversize will be used.  WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9, Method D will be used for materials with greater than 60% by weight passing the 19.0 mm sieve with the plus 19.0 mm material removed and treated as oversize.

WAQTC FOP for AASHTO T 99/T 180/WAQTC TM 9 will be performed in accordance with Note 7 (the 12 hour stand time may be waived if the sample has not been dried to less than four percentage points below the optimum moisture content) and modified so that the moisture content of each trial is determined from the complete specimen and reported to the nearest 0.1%.  Section 13 is modified to include: 13.1.6 Bulk Specific Gravity of the oversize material; 13.1.7 Apparent Specific Gravity of the tested material minus the oversize; and 13.1.8 Zero Air Voids Curve calculated and plotted in accordance with ASTM D 1557, Sections 11.2 and 11.5. (11/29/01)R193M98

203-4.01 METHOD OF MEASUREMENT. Add the following: Measurement of ditch linear grading, whether flat bottom or "V" ditch, will be measured for payment by the meter along the center of the ditch for each ditch so designated, constructed and accepted by the Engineer.

203-5.01 BASIS OF PAYMENT. Add the following: Payment for ditch linear grading will be full compensation for furnishing all equipment, labor, tools and incidentals to provide the preparation, excavation and shaping necessary to complete the work.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

203(17)	Ditch Linear Grading	Meter

(9/1/89)R20

SECTION 301

AGGREGATE BASE AND SURFACE COURSE

## Special Provisions

301-1.01 DESCRIPTION.  Add the following:  No base course work will be allowed during 2002 for Hatcher Pass and Gold Chord Roads unless directed otherwise by the Engineer.  Aggregate base course  work shall be done in 2003 for Hatcher Pass and Gold Chord Roads.

301-2.01 MATERIALS. Delete the second sentence of the first paragraph and substitute the following: The gradation of base course material shall conform to the requirements for Grading D-1. (10/1/91)R116

Add the following after the first paragraph: At the Contractor's option, recycled asphalt material (RAM) may be substituted for aggregate base course, millimeter for millimeter, if the following conditions are met:

1.	RAM shall be crushed or processed to 100 percent by weight passing the 37.5 mm sieve and 95-100 percent by weight passing the 25 mm sieve.

2.	The gradation of the extracted aggregate shall meet the following:

| # Sieve | Percent Passing by Weight |
| --- | --- |
| 25 mm | 100 |
| 19 mm | 70-100 |
| 9.5 mm | 42-90 |
| 4.75 mm | 28-78 |
| 1.18 mm | 11-54 |
| 0.300 mm | 5-34 |
| 0.150 mm | 3-22 |
| 0.075 mm | 2-12 |

3.	The asphalt content shall be 2.5 - 5.0 percent by weight of the RAM.

301-3.03 SHAPING AND COMPACTION. Add the following: If recycled asphalt material is substituted for aggregate base course, the following conditions shall be met:

1.	Density acceptance will be based upon a roller pattern. The roller pattern shall be determined by a test strip using a vibratory compactor with a minimum dynamic force of 178,000 newtons. The optimum density will be determined by the Engineer using a nuclear densometer gauge to monitor the test strip. Adequate water shall be added to aid compaction.

2.	After the appropriate coverage with the vibratory compactor, a minimum of 6 passes with a pneumatic tire roller shall be completed. Tires shall be inflated to 550 kPa (±34 kPa), and the roller shall have a minimum operating weight per tire of 1360 kg.

301-5.01 BASIS OF PAYMENT. Add the following: If recycled asphalt material is substituted for aggregate base course, it will be paid for as Item 301(1), Aggregate Base Course at the unit price shown on the bid schedule for that item.

(2/28/01)R176M98

SECTION 303

RECONDITIONING

## Special Provisions

303-1.01 DESCRIPTION. Add the following: This work also consists of all excavation and shaping required to reconstruct superelevations to grade as determined by the Engineer.  Additional excavation, beyond the depth shown on the Plans, may be required in order to reduce the superelevation rate to the proposed rate. (3/28/00)R254M98

Item 303(1B), Reconditioning consists of reconditioning the following six (6) parking areas:

Willow Creek Parkway MP 3.86

Hatcher Pass Road MP 16.0

Hatcher Pass Road MP 16.2

Gold Chord Road MP 0.17

Gold Chord Road MP 1.17

Gold Chord Road MP 1.45

303-3.01 METHOD OF MEASUREMENT. Add the following: Work required to reconstruct superelevation as detailed in Subsection 303-1.01 will not be measured for payment.

Item 303(1B), Reconditioning will be measured by the square meter.

303-4.01 BASIS OF PAYMENT. Add the following: Superelevation reconstruction is subsidiary to item 303(1), Reconditioning and no separate payment shall be made.

Select Material, Type A required to reconstruct superelevations will be paid for as required in Section 203.  (3/28/00)R254M98

Item 303(1B), Reconditioning shall be paid at the contract unit price per square meter completed and accepted.

Add the following Pay Item:

Pay Item No.	Pay Item	Pay Unit

303(1B)	Reconditioning	Square Meter

SECTION 401

ASPHALT CONCRETE PAVEMENT

# Special Provisions

401-1.01 DESCRIPTION. Add the following:  No paving work will be allowed during 2002 for Hatcher Pass and Gold Chord Roads unless directed otherwise by the Engineer.  Paving shall be done in 2003 for Hatcher Pass and Gold Chord Roads.

401-2.01 COMPOSITION Of Mixture - Job Mix Design.  Add the following to the first paragraph after ATM T-17: (version 01/93).

Delete the last sentence of the second paragraph on page 114 and substitute the following: Tolerances will not be applied to the largest sieve specified.

401-2.03 ASPHALT Materials. Change the last sentence of the first paragraph to read: When not specified, the grade of the asphalt cement shall be PG 52-28.

Delete the second paragraph and substitute the following:

Asphalt cement may be conditionally accepted at the source. Each batch of asphalt cement shall be tested for conformance to specifications in Section 702 prior to shipping. Storage tanks used for the batch shall be noted on the test report. Anti-strip additives required by the mix design shall be added to the asphalt cement during load out for delivery to the project. A printed weight ticket of antistrip shall be included with the asphalt cement delivery ticket. The location where antistrip is added may be changed with the approval of the Engineer.

Shipping documents shall include the following:

- Manufacturers certificate of compliance, Subsection 106-1.05

- Conformance test results of the batch, Section 702.

- Manufacturer shall also certify:

- Date and Time of loading

- Batch number and storage tank

- Type, grade, temperature, and quantity of materials loaded

- Type and percent of anti-strip added.

401-3.09 PREPARATION Of Aggregates.  In the first paragraph, delete AASHTO T-110 and substitute the following: WAQTC TM 6.

401-3.14 JOINTS.  Delete the last paragraph.  Delete the first paragraph and substitute the following: Construct the minimum number of joints to ensure a continuous bond, texture, and smoothness between adjacent sections of the pavement.  The minimum specification limit for longitudinal joint density will be 91% of the MSG of the panel completing the joint.  Cut one minimum diameter 150 mm core centered on the longitudinal joint at each location the mat is cored for acceptance density testing in the panel completing the joint.  Density will be determined in accordance with WAQTC FOP for AASHTO T 166/ T 275.

401-3.16 PATCHING DEFECTIVE AREAS.  Add the following: All costs associated with the patching of defective areas shall be borne by the Contractor.

401-4.01 METHOD Of Measurement.  Under Asphalt Cement, 1., add to the end of the second sentence: “... ,or WAQTC FOP for AASHTO TP 53.”

Add the following paragraph to this Subsection: Longitudinal joints.  By the meter.  The distance measured will be in both directions from a longitudinal joint core location to a point equal distant to the next longitudinal joint core.

401-4.02 ACCEPTANCE Sampling And Testing.  Delete the third, fourth, fifth, and sixth full paragraphs on page 122, and substitute the following: Samples taken for the determination of asphalt cement content will be taken from the windrow, at the end of the auger, or from behind the screed prior to compaction.  Asphalt cement content will be determined in accordance with WAQTC TM 4, or WAQTC FOP for AASHTO TP 53 with the exception that the moisture content will be determined in accordance with WAQTC TM 6.

Samples taken for the determination of aggregate gradation from drum mix plants will be from the combined aggregate cold feed conveyor via a sampling device, the stopped conveyor belt, or from asphalt concrete mixture samples taken from the same location as samples for the determination of asphalt cement content.  The aggregate gradation for samples from the conveyor system will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from the aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Maintain cold-feed conveyor sampling devices diverting aggregate from the full width of the conveyor system to provide a representative sample of the aggregate incorporated into the asphalt concrete mixture.

Samples taken for the determination of aggregate gradation from batch plants will be from the same location as samples for the determination of asphalt cement content, or from dry batched aggregates. The dry batched aggregate gradation will be determined in accordance with WAQTC FOP for AASHTO T 27/T 11.  For asphalt concrete mixture samples, or cores, the gradation will be determined in accordance with WAQTC FOP for AASHTO T 30 from aggregate remaining after the ignition oven (WAQTC FOP for AASHTO TP 53) has burned off the asphalt cement.

Within 24 hours of final rolling, neatly cut core samples with a core drill at the randomly selected locations marked by the Engineer.  Use a core extractor to prevent damage to the core while removing.  Do not cut core samples from bridge decks.  One minimum diameter 150 mm core is required for acceptance density testing only.  Acceptance density testing will be in accordance with WAQTC FOP for AASHTO T 166/T 275.

Failure to cut core samples for acceptance testing within the specified period will result in a deduction of $100.00 per sample per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

Backfill and compact all voids left by sampling with new asphalt concrete mixture within 24 hours of sampling.  Failure to backfill voids left by sampling in the specified period will result in a deduction of $100.00 per hole per day.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment.

401-4.03 EVALUATION OF MATERIALS FOR ACCEPTANCE. Add the following: The longitudinal joint density price adjustment will apply when Asphalt Concrete Pavement quantities are equal to or greater than 900 megagrams.

Add the following under item 3.: The tolerances for the largest sieve specified will be plus 0% and minus 1%.

401-5.01 BASIS OF PAYMENT. Add the following to the first paragraph, No payment shall be made for asphalt cement, and asphalt concrete mix made with this cement, if tests of the asphalt cement sampled during production are out of specification.

Add the following: Longitudinal joint densities less than 91 percent of MSG, as defined is Subsection 401-3.14, will be measured in accordance with Subsection 401-4.01 and assessed a price adjustment of $1.00 per meter.  The accrued amount will be subtracted under Item 401(6), Asphalt Price Adjustment. (11/29/01)R199M98

# SECTION 603

# CULVERTS AND STORM DRAINS

# Special Provisions

603-1.01 DESCRIPTION. Add the following: This work shall also consist of installing culvert marker posts. (5/31/96)R42M

This work also consists of locating and exposing buried culvert ends on Hatcher Pass Road at the Engineer’s direction.

Standard Modifications

603-2.01 MATERIALS. In the second paragraph, delete “(900 mm maximum diameter)”.

In the fourth paragraph, delete the last sentence. (02/08/01)M95

Special Provisions

Add the following: Culvert marker posts shall meet the requirements of Subsection 730-2.05 Delineator Posts, for item 2. Flexible Posts. The color shall be blue with no other markings. The 65 mm by 1800 mm post shall be rectangular in cross-section with reinforcing ribs capable of a minimum bending radius of 230 mm. (5/31/96)R42M

Ditch lining required for the 1676 mm x 1295 mm pipe arch shall meet the requirements of Section 610.

CONSTRUCTION REQUIREMENTS

Standard Modifications

603-3.03 JOINING PIPE.

2. 	Metal Pipe. Replace the second sentence with the following: “Use bands that are no more than two nominal sheet thicknesses lighter than the pipe being joined, and in no case lighter than 1.3 mm.” (02/08/01)M95

Special Provisions

Add the following Subsections:

603-3.06 CULVERT MARKER POSTS. Culvert marker posts shall be installed on the approach side of storm drain outfalls 750 mm and smaller, field inlets not in paved parking lots, all end sections to cross culverts, or as directed by the Engineer. 1070 mm of post shall remain above the ground after driving.

603-3.07 CULVERT LOCATION.  Locate and expose each pipe outlet.  After exposing the outlet to allow unobstructed full flow, locate and expose the inlet of the pipe.

603-4.01 METHOD OF MEASUREMENT. Add the following: Culvert marker posts will not be measured for payment.  No measurement will be made for the ditch lining required for item 603(19).

Culvert Location. By the number of culverts located, cleared and accepted by the Engineer.

603-5.01 BASIS OF PAYMENT. Add the following: Culvert marker posts will not be paid for directly, but will be subsidiary to pipe items. (5/31/96) R42M

Ditch lining (approximately 25 m3) required for the 1676 mm x 1295 mm Pipe Arch is subsidiary to Item 603(19) and no separate payment shall be made.

Item 603(31), Culvert Location will be paid at the contract price per culvert located, cleared and accepted by the Engineer.

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

603(31)	Culvert Location	Each

# SECTION 606

# GUARDRAIL

# Special Provisions

606-2.01 MATERIALS.  Delete “Flexible Markers” in its entirety and substitute the following:

Flexible Markers. Use flexible markers with an over all length of 1,800 mm (72”). The marker shaft shall have a coil spring at the bottom and a flag at the top.  The shaft and spring shall be one piece and made from galvanized spring steel.  The flexible marker shall have an orange HDPE flag which provides approximately 129 cm2 (20 in2) of surface area. Use stainless or galvanized steel attaching hardware.  The following is an example of an acceptable flexible marker:

Model:	FF2

Manufacture:	Nordic Fiberglass, Inc.

P.O. Box 27

Highway 75 South

Warren, MN 56762

Phone:	(218) 745-5095

Fax:	(218) 745-4990

E-mail:	www.nordicfiberglass.com

If using another brand, submit specifications to the Engineer for approval prior to ordering the markers.

(10/01/01)R45aM98

Standard Modifications

606-3.01 GENERAL.  Add the following: Treat field cuts to timber posts and blocks according to AWPA standard M 4. (10/19/98)M 67

606-3.05 TERMINAL SECTIONS.  Delete the fourth paragraph (flexible markers) in its entirety and substitute the following:

Attach flexible markers, in a vertical position, to the last post of each guardrail terminal using two pipe bracket holders spaced 300 mm apart. Attach to wooden guardrail posts with wood screws and to steel guardrail posts with hex bolts.

(03/14/00) M 88

# Special Provisions

606-3.06 REMOVAL AND RECONSTRUCTION OF GUARDRAIL. Add the following: Guardrail removed and to be replaced with new guardrail shall have the entire new run installed within 7 calendar days after removal.

Guardrail located within 15 meters of bridge ends shall have the new guardrail installed by the end of the shift in which the existing guardrail is removed. (10/01/01)R45aM98

606-3.07 REMOVAL AND DISPOSAL OF GUARDRAIL. Delete the last sentence and substitute the following: Notify the Engineer, five (5) days prior to removing guard rail for disposal.  At that time, the Engineer will physically identify portions of guardrail to be salvaged.  All guardrail and associated hardware so designated will be delivered to the Department of Transportation Maintenance Yard located in Palmer.  All remaining items removed become the property of the Contractor.  (9/8/00)R259M98

606-3.09 FLEXIBLE MARKERS. Add the following Subsection: For each slotted rail terminal, a flexible marker shall be attached to the extreme piece of rail. The flexible markers shall be attached using hardware and attachment methods recommended by the manufacturer. The flexible markers shall have a minimum of 530 millimeters of marker extending above the top of the guardrail. The reflective tape shall face the nearest oncoming traffic.

606-3.10 LENGTH OF NEED VERIFICATION. Add the following Subsection: After shaping the slopes and staking all proposed guardrail locations, the Contractor shall notify the Engineer to field verify the beginning and ends. The staked location of the guardrail will be approved by the Engineer prior to installation. The Engineer may determine that additional guardrail is necessary, and the Contractor shall comply without delay.

(10/01/01)R45aM98

606-4.01 METHOD OF MEASUREMENT.  Add the following under Terminal section:

4.	Box Beam Terminal.  Per each installation.  Includes all materials from the nose assembly to the breakaway tensile connector including all tubes, spacers, posts, cable assemblies and associated hardware required for a complete installation.

606-5.01 BASIS OF PAYMENT. Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

606(14)	Box Beam Terminal	Each

SECTION 611

RIPRAP

Special Provisions

611-1.01 DESCRIPTION.  Add the following: This work shall also consist of furnishing and placing geotextile liner and excavation associated with placement of riprap as shown on the Plans or as directed by the Engineer.

611-2.01 MATERIALS. Add the following: Geotextile liner shall conform to the requirements of Subsection 729-2.02.

611-3.01 CONSTRUCTION REQUIREMENTS. Add the following: Construct geotextile liner in accordance with Section 631.  Perform all excavation associated with placement of riprap as shown on the Plans or as directed by the Engineer.

611-4.01 METHOD OF MEASUREMENT. Add the following: The geotextile liner and excavation associated with placement of riprap will not be measured.

611-5.01 BASIS OF PAYMENT.  Add the following: The geotextile liner and all excavation associated with placement of riprap is subsidiary to other 611 items and no separate payment shall be made.

SECTION 615

STANDARD SIGNS

# Special Provisions

615-2.01 MATERIALS. Under item 1. delete the first sentence and substitute the following: Unless Shop Drawings have been provided in the Contract, submit all signs that require the use of the Alaska Sign Design Specifications (ASDS), the Department of Transportation and Public Facilities - Sign Face Fabrication Requirements, and the Alaska Traffic Manual, letter width and spacing charts for approval before fabrication.

615-3.01 CONSTRUCTION REQUIREMENTS. Delete item 7 and substitute the following:

- Notify the Engineer five (5) days prior to beginning sign salvage activities. At that time, the Engineer will physically identify those signs to be salvaged.  For each sign so designated, disconnect sign post from panel.  The panels shall then be grouped together in a manner to preclude damage.  Posts shall also be grouped together as with hardware in a workmanlike manner.  Deliver sign panels, posts and hardware to the State Maintenance Yard located in Palmer and Willow.  Do not deliver salvaged materials until they have been inspected and approved by the Engineer.  Replace all panels, posts and hardware damaged during salvaging or delivery with new panels, posts and hardware at no additional cost to the Department.

Remove and dispose of project signs and/or parts designated for removal and not selected for salvage.

Dispose of foundations from salvaged existing signs in a manner approved of by the Engineer (remove and dispose, abandoned in place, or otherwise dispose of). If they are abandoned in place, the tops of the foundations, reinforcing steel, anchor bolts, and conduits shall be removed to a depth of not less than 300 millimeters below roadway subgrade or unimproved ground, whichever applies. All signs and posts at a single installation shall be considered as one unit.

615-3.02 SIGN PLACEMENT AND INSTALLATION. Add the following: Do not remove existing signs without authorization from the Engineer.  Reference existing sign posts that are to be replaced before removing.

615-4.01 METHOD OF MEASUREMENT. Add the following to the second paragraph: Concrete used for sign bases is considered subsidiary to other work under this section.

615-5.01 BASIS OF PAYMENT. Add the following: No separate payment for keeping existing signs in service until they are no longer needed, or temporary relocation of existing signs will be made.  This work is subsidiary to Item 615(1), Standard Sign.

No separate payment for removal of existing sign post foundations, or work required to abandon them in place will be made, but shall be subsidiary to Item 615(1), Standard Sign.

No separate payment for salvaging activities detailed in Subsection 615-3.01 will be made.  This work will be subsidiary to Item 615(1), Standard Sign or Item 615(8), Replace Sign Panels.

(05/16/01)R50M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

615(8)	Replace Sign Panels	Square Meter

Delete this Section in its entirety and substitute the following:

SECTION 618

SEEDING

618-1.01 DESCRIPTION. This work consists of establishing a perennial stand of grass or other specified living vegetative cover in the areas indicated on the Plans and to acceptably maintain the cover for the term of the Contract. (02/08/01)M99

#### Special Provisions

Add the following: Seed all new or disturbed slopes and any other areas directed by the Engineer. Track the soil and apply seed, mulch, fertilizer and water. Provide a living ground cover on all slopes as soon as possible. (08/28/01)R52M98

## Standard Modifications

618-2.01 MATERIALS. Use materials that conform to the Special Provisions and the following:

Seed 	Section 724

Fertilizer (20-20-10)	Section 725

(02/08/01)M99

Special Provisions

Add the following to the list of material specifications:

Mulch	Subsection 727-2.01

(08/28/01)R52M98

Seed mix B will be provided by the Alaska State Plant Material Center.

## Standard Modifications

CONSTRUCTION REQUIREMENTS

618-3.01 SOIL PREPARATION. Clear all areas to be seeded of stones 100 mm in diameter and larger and of all weeds, plant growth, sticks, stumps, and other debris or irregularities that might interfere with the seeding operation, growth of grass, or subsequent maintenance of the grass-covered areas.

Make areas to be seeded reasonably free of ruts, holes, and humps.

(02/08/01)M99

#### Special Provisions

Add the following: Apply seed as detailed in Subsection 618-3.03 immediately after the shaping of the slopes. Prepare slopes for seed by "walking" a dozer transversely up and down the slopes, or by grading with a scarifying slope board, as determined by the Engineer. The resultant indentations shall be perpendicular to the fall of the slope.  Rounding the top and bottom of the slopes is acceptable to facilitate tracking and to create a pleasing appearance, but do not disrupt drainage flow lines. (08/28/01)R52M98

## Standard Modifications

618-3.02 SEEDING SEASONS. Do not seed during windy conditions or when climatic conditions or ground conditions would hinder placement or proper growth.

Special Provisions

Add the following: Type A mixture seeding shall be performed between May 15, 2002 and August 15, 2002.  Type B mixture seeding shall be performed between June 1, 2002 and July 31, 2002.

Standard Modifications

618-3.03 APPLICATION. Apply seed mix at the rate specified in the Special Provisions.

Use the following method:

1.	Hydraulic Method.

a.	Furnish and place a slurry made of seed, fertilizer, water, and other components as required by the Special Provisions.

b.	Use hydraulic seeding equipment that will maintain a continuous agitation and apply a homogeneous mixture through a spray nozzle. The pump must produce enough pressure to maintain a continuous, nonfluctuating spray that will reach the extremities of the seeding area with the pump unit located on the roadbed. Provide enough hose to reach areas not practical to seed from the nozzle unit situated on the roadbed.

c.	If mulch material is required, it may be added to the water slurry in the hydraulic seeder after adding the proportionate amounts of seed and fertilizer. Add seed to the slurry mixture no more than 30 minutes before application.

d.	Mix the slurry and apply it evenly.

(02/08/01)M99

Special Provisions

Add the following: Apply both types of seed mix by the hydraulic method.  For Type A Seed Mix, apply seed, mulch and fertilizer in one application.  For Type B Seed Mix, apply slurry of seed, fertilizer, and hydromatting.

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type A | Seed | Bering Hairgrass (Norcoast) Red Fescue (Arctared) Annual Ryegrass (Lolium) | 24.5 kg 19.5 kg 5.0 kg Total = 49.0 kg |
|  | Soil Stabilizer Slope ≤ 3:1 Slope >3:1 – 2:1 | Mulch Mulch with tackifier | 2240 kg 2800 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

| Seed Mix | Component | Ingredients | Application Rate (per ha) |
| --- | --- | --- | --- |
| Type B | Seed | Poa Alpina Burnet Dwarf Fireweed Lupine Geranium Monkshood Tall Fireweed Bluejoint Alder Mertens Sedge Senecio Arnica Festuca Altacia | 22.6 kg 2.2 kg 2.2 kg 2.2 kg 1.1 kg 1.1 kg 1.1 kg 1.1 kg 1.1 kg 0.4 kg 0.4 kg 0.4 kg 0.4 kg Total = 36.3 kg |
|  | Hydro Matting |  | 3419 kg |
|  | Fertilizer | 20-20-10 | 586 kg |

The Contractor shall not remove the required tags from the seed bags.

Upon the Engineer’s approval, Nortran Tufted Hairgrass may be used as a substitute for Bering Hairgrass if Bering Hairgrass is commercially unavailable.  Substitute Bering Hairgrass with Nortran Tufted Hairgrass at the same application rate. (08/28/01)R52M98

#### Standard Modifications

618-3.04 Plant Establishment AND MAINTENANCE. Protect seeded areas against traffic and erosion.

Promptly repair surfaces that are gullied or otherwise damaged following seeding by regrading, reseeding, and remulching as needed.

Water and maintain seeded areas in a satisfactory condition until final inspection and acceptance of the work. Use equipment that can water all seeded areas without damaging the seed bed.

Reseed any areas not showing evidence of satisfactory growth within 3 weeks of seeding.

618-4.01 METHOD OF MEASUREMENT.

Seeding by the hectare. By the area of ground surface acceptably seeded and maintained. Seed, water, and fertilizer are subsidiary.

Water for seeding. By the kiloliter using calibrated tanks or distributors, accurate water meters, or by weighing. The conversion factor of 1 kilogram per liter will be used to convert weight to volume.

Mulching will be measured and paid for under Section 619.  (02/08/01)M99

#### Special Provisions

Add the following: The amounts of fertilizer, mulch and water for application used in this work, including any required reseeding, are subsidiary to other 618 items. (08/28/01)R52M98

#### Standard Modifications

618-5.01 BASIS OF PAYMENT. At the contract unit price per unit of measurement for the pay items listed below that appear on the bid schedule. (02/08/01)M99

#### Special Provisions

Add the following: The work described under Subsection 618-3.01 Soil Preparation is subsidiary to seeding.

Water required for the hydraulic method of application is subsidiary to seeding.

(08/28/01)R52M98

SECTION 619

SOIL STABILIZATION

Special Provisions

619-1.01 DESCRIPTION. Add the following: This work also includes the furnishing, application and maintenance of hydraulically applied soil stabilization matting.

619-2.01 MATERIALS. Add the following to the first paragraph:

Hydro Matting			727-2.04

Add the following: Hydraulically applied soil stabilization matting shall contain the seed and fertilizer specified in Section 618, Seeding. It shall be applied at the rate of 3,360 kg/ha or in accordance with the manufacturer's written recommendations and application parameters. Where hydro matting is required by the plans on 1V:1½H cut or fill slopes 6 meters or more in height, the slopes shall be stabilized as the faces are exposed, as practical, in accordance with the NPDES Storm Water Pollution Prevention Plan.

Slopes with lateral seeps shall be allowed to dry before treating with hydro matting. Treatment of such areas may be deferred until the end of slope finishing unless there is a risk of a major failure. In such event, the Engineer will direct repairs to be made by redressing and hydro matting, by rock buttressing, or by other means in accordance with Section 641.

619-3.03 MAINTENANCE AND REPAIR. Add the following: Hydraulically applied soil stabilization matting shall be maintained and repaired in accordance with the manufacturer's written recommendations and Subsection 618-3.04, Plant & Establishment and Maintenance, or as directed by the Engineer.

619-4.01 METHOD OF MEASUREMENT. Add the following: The unit price for Item 619(3), Hydro Matting, shall include seed and fertilizer at application rates specified in Section 618.

619-5.01 BASIS OF PAYMENT. Add the following: There shall be no adjustment to price in the event that weather, soil conditions or other conditions preclude the use of hydro matting.

(6/30/97)R223M

Add the following pay item:

Pay Item No.	Pay Item	Pay Unit

619(3)	Hydro Matting	Square Meter

SECTION 640

MOBILIZATION AND DEMOBILIZATION

Standard Modifications

640-2.01 METHOD OF MEASUREMENT.  Delete items 3. and 4. and substitute the following:

3.	The remaining balance of the amount bid for this item will be paid after all submittals required under the Contract are received and approved.

(06/25/99)M 77

Delete Section 641 in its entirety and substitute the following:

SECTION 641

TEMPORARY EROSION AND POLLUTION CONTROL

## Special Provisions

641-1.01 DESCRIPTION. This work shall consist of temporary control measures as shown on the plans, or ordered during the life of the contract, to control temporary erosion and water pollution. This work shall include preparation of a Temporary Erosion and Pollution Control (TEPC) Plan. Conduct construction activities in accordance with the approved TEPC Plan.

641-1.02 TEMPORARY EROSION AND POLLUTION CONTROL PLAN. Submit a TEPC Plan at least five (5) days prior to the preconstruction conference, for approval by the Department's Environmental Section. The TEPC Plan shall consist of the following:

1.	Methods for clearing and grubbing.

2.	Plan for installation of temporary erosion and sediment control measures, in accordance with the Department's Storm Water Manual, including, but not limited to, the following:

a.	Excavation and embankment construction;

b.	Construction of temporary and permanent drainage features;

c.	Construction in and around waterbodies and wetlands; and

d.	Haul roads and material sites.

e.	List of quantities, types and suppliers of materials to be used.

3.	Disposal of waste material.

4.	Containment, cleanup, and disposal of such substances, as well as the methods to be utilized for disposing of, petroleum products or other hazardous substances generated by construction equipment or activities. The plan shall also include a list of the quantities and types of materials available on site to be utilized for hazardous substance containment and cleanup activities.

The Department will review the TEPC Plan for approval within five (5) working days. If corrections or modifications are necessary to the plan, resubmit the corrected within five (5) days of receipt of the comments.

641-2.01 CONSTRUCTION REQUIREMENTS. The Contractor shall limit the surface area of erodible earth material exposed by clearing and grubbing, excavation, borrow and fill operations.  The Contractor shall provide immediate permanent or temporary pollution control measures to prevent contamination of adjacent streams, lakes, ponds or other areas of water impoundment, as directed by the Engineer. As necessary, such work may involve the construction of temporary berms, dikes, dams, sediment basins, slope drains, and use of temporary mulches, seeding or other control devices or methods as necessary to control erosion. Use temporary pollution control measures to correct conditions that develop during construction that were not foreseen during the design stage, that are needed prior to installation of permanent pollution control features, but are not associated with permanent control features on the project.

Incorporate all permanent erosion control features into the project at the earliest practicable time as outlined in the Contractor’s accepted schedule.

Seed and mulch cut slopes as the excavation proceeds to the extent considered desirable and practicable.

Where erosion is likely to be a problem, schedule and perform clearing and grubbing operations so that grading operations and permanent erosion control features can follow immediately thereafter if the project conditions permit; otherwise temporary erosion control measures may be required between successive construction stages. The surface area of erodible earth material exposed at one time by clearing and grubbing shall not exceed 2.02 hectares without written approval.

Based on the Engineer assessment of the Contractor’s ability to meet the approved schedule to construct the project, mulch, seed and implement other permanent pollution control measures, the Engineer may direct the Contractor to limit the area of excavation, borrow and embankment operations in progress. Should seasonal limitations make such coordination unrealistic, the Contractor shall take temporary erosion control measures immediately to the extent feasible and justified.

In the event of conflict between these requirements and pollution control laws, rules or regulations of other federal or state or local agencies, the more restrictive laws, rules or regulations shall apply.

The Contractor’s shall be responsible for the containment, cleanup, and disposal of all construction-related discharges of petroleum fuels, oil, and/or other substances hazardous to the land and water. Performance of this activity shall comply with the requirements of 18 AAC 75 and Title 46 of the Alaska Statutes.

641-3.01 METHOD OF MEASUREMENT. The method of measurement shall be as specified in the order authorizing the work.

641-4.01 BASIS OF PAYMENT. Temporary erosion and pollution control work required, which is not attributed to the Contractor’s negligence, carelessness or failure to install permanent controls, will be paid for as specified in the authorized the work order.

In the event that temporary erosion and pollution control measures are required due to the Contractor’s negligence, carelessness or failure to install permanent controls as a part of the work as scheduled and as ordered, such work shall be performed at the Contractor’s  expense.

In case of repeated failures on the Contractor’s part to control erosion, pollution and/or siltation, the Engineer reserves the right to employ outside assistance or to use the Department’s forces to provide the necessary corrective measures. Such incurred direct costs plus project engineering costs will be charged to the Contractor and appropriate deductions made to the Contractor’s monthly progress estimate.

Temporary pollution control may include construction work outside the right-of-way where such work is necessary as a result of roadway construction, such as State Furnished Material sources. Temporary erosion and pollution control in connection with Contractor furnished material sources shall be at the Contractor’s expense.

Install and acceptably maintain the erosion control.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

641(1)	Temporary Erosion and Pollution Control	Contingent Sum

(3/28/00)R203M98

SECTION 642

CONSTRUCTION SURVEYING AND MONUMENTS

Standard Modifications

642-3.01 GENERAL.  Delete the seventh paragraph.  (06/25/99)M 79

#### Special Provisions

642-3.01 GENERAL. Add the following after Item 10 on page 355: Prior to any work on the project, stake and reference the construction centerline. Reference the existing centerline at 25 meter intervals on tangents, and 12.5 meter intervals on curves, super elevations, transitions and cross-slopes. The reference stake shall be a minimum of 25 mm x 50 mm by 0.6 meters and shall show the offset distance to centerline and the station from the beginning of the project.

Install a reference sign every 150 meters. These reference signs shall meet the following requirements:

1.	mounted a minimum of 1.5 meters above the shoulder,

2.	located a minimum of 3 meters from the edge of shoulder,

3.	marked with the station from the beginning of the project, in 125 mm high black lettering on an orange background.

Reference the beginning and ending points of the no-passing zones in a separate field book.

Provide centerline and shoulder profiles extending 90 meters beyond the limits of the pavement removal and dig-out areas. The Engineer may require such adjustments to the planned roadway grades. This shall not be considered extra work. Provide this profile information to the Engineer (electronically in Excel format) immediately upon its completion, along with checked computations on all level loops, but in no case later than 7 calendar days before slope staking or blue topping. (8/29/00)R61M98

11.	Measuring and documenting the intersection sight triangles for all public approaches in accordance with Figure 1190-1 of the Highway Preconstruction Manual.

642-3.02 CROSS-SECTION SURVEYS Under the heading “The following shall be required of the Contractor:,” delete item 1, and substitute the following:

- Field Books (level, Cross-Section, Slope Stake, etc.).  Hardbound “Rite-in-the-Rain” or similar weather resistant books.  Field books become the property of the Department upon completion of the work. (3/31/00)R252M98

SECTION 643

TRAFFIC MAINTENANCE

# Special Provisions

643-1.03 TRAFFIC CONTROL PLAN. Replace the last paragraph with the following: The Contractor may request, in writing, a waiver of regulation 17 AAC 25 regarding oversize and overweight vehicle movements within this project.  All movements of oversize and overweight vehicles in or near traffic within the project limits will be done in accordance with the provisions of an approved Traffic Control Plan. Maintain a minimum 3.6 meter lateral separation between the non street legal vehicles and the motoring public.  The Traffic Control plan shall specify the traffic control devices required for these operations.   (11/29/01)R222M98

## Standard Modifications

643-2.01 MATERIALS. Delete this Subsection in its entirety and substitute the following: Provide traffic control devices conforming to the following requirements:

1.	Signs. Use signs, including sign supports, that conform to Section 615, the ATM and ASDS.

a.	Construction Signs: Use regulatory, guide, or construction warning signs designated in the ASDS.

b.	Permanent Construction Signs: As designated on the Plans or on an approved TCP.

c.	Special Construction Signs: All other signs are Special Construction Signs. Clearly and neatly mark the size of each sign on the back in 75-mm black numerals.

2.	Portable Sign Supports. Use wind-resistant sign supports with no external ballasting. Use sign supports that can vertically support a 1.2 m X 1.2 m traffic control sign at the height above the adjacent roadway surface required by the ATM.

3.	Barricades and Vertical Panels. Use barricades and vertical panel supports that conform to the ATM. Use Type III Barricades at least 2.4 m long. Use reflective sheeting that meets AASHTO M 268 Type II or III.

4.	Portable Concrete Barriers. Use portable concrete barriers that conform to the Plans. For each direction of traffic, equip barriers with at least two side-mounted retroreflective reflectors or a continuous longitudinal stripe of preformed retroreflective pavement marking tape mounted 150 mm below the top of each barrier section. Use yellow reflectors or tape if you use barriers at centerline. Use white reflectors or tape if you use barriers on the roadway shoulder.

5.	Warning Lights. Use Type A (low intensity flashing), Type B (high intensity flashing) or Type C (steady burn) warning lights that conform to the ATM.

6.	Drums. Use plastic drums that conform to the requirements of the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III.

7.	Traffic Cones and Tubular Markers. Use reflectorized traffic cones and tubular markers that conform to the requirements of the ATM. Use traffic cones and tubular markers at least 710 mm high. Use reflective sheeting that meets AASHTO M 268 Type II or III.

8.	Interim Pavement Markings. Apply markings according to Section 670 and the manufacturer's recommendations. Use either:

a.	Paint conforming to Subsection 708-2.03 with glass beads conforming to Subsection 712-2.08,

b.	Preformed marking tape (removable or non-removable) conforming to Subsection 712-2.14, or

c.	Temporary raised pavement markers conforming to Subsection 712-2.15 or 712-2.16, as appropriate.

9.	High-Level Warning Devices. Use high-level warning devices that conform to the ATM.

10.	Temporary Crash Cushions. Use approved temporary crash cushions conforming to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. Do not use permanent crash cushions as temporary crash cushions. Use sand or water filled crash cushions only when the forecasted temperature during their use is above 5 oC.

11.	Sequential Arrow Panels. Use Type A (610 X 1220 mm), Type B (762 X 1524 mm) or Type C (1220 X 2438 mm) panels that conform to the ATM.

12.	Portable Changeable Message Board Signs. Use truck or trailer mounted portable changeable message board signs with a self contained power supply for the sign and with the following features:

- Message sign panel large enough to display 3 lines of 229 mm high characters.

- Eight character display per message line.

- Fully programmable message module.

- The capacity to create, preview, and display new messages and message sequences.

- A waterproof, lockable cover for the controller keyboard.

- An operator’s manual, a service manual, and a wiring diagram.

- Quick release attachments on the display panel cover.

- Variable flash and sequence rates.

- Manual and automatic dimming capabilities on lamp bulb matrix models.

- Locate the bottom of the sign panel at least 2.1 m above the pavement.

- Operate with a battery pack a minimum of 2 hours under full load.

13.	Plastic Safety Fence. Use 1.2-m high construction orange fence manufactured by one of the following companies, or an approved equal:

a.	“Safety Fence” by Services and Materials Company, Inc., 2200 South “J” Street, Elwood, Indiana, 46036. Phone (800) 428-8185.

b.	“Flexible Safety Fencing” by Carsonite, 1301 Hot Springs Road, Carson City, Nevada, 89706. Phone (800) 648-7974.

c.	“Warning Barrier Fence” by Plastic Safety Systems, Inc. P.O. Box 20140, Cleveland, Ohio, 44120. Phone (800) 662-6338.

14.	Temporary Sidewalk Surfacing. Provide temporary sidewalk surfacing as required by an approved TCP and the following:

a.	Use plywood at least 12 mm thick for areas continuously supported by subgrade. Use plywood at least 25 mm thick for areas that are not continuously supported.

b.	Do not use unsupported 25-mm plywood longer than 750 mm.

c.	Use plywood with regular surfaces. Do not overlap plywood joints higher than 25 mm.

d.	Use a method that will withstand 40 km/h wind velocities to hold temporary surfacing in place.

15.	Temporary Guardrail. Use temporary guardrail that meets Section 606, except that posts may require placement under special conditions, such as in frozen ground.

- Flagger Paddles. Use flagger paddles with 600 mm wide by 600 mm high sign panels, 200 mm Series C lettering (see ASDS for definition of Series C), and otherwise conform to the ATM. Use reflective sheeting that meets AASHTO M 268 Type II or III. (9/29/00)M 91

## Special Provisions

Add the following:

17.	Flexible Markers.  Refer to Subsection 606-2.01 Materials.

(11/29/01)R222M98

## Standard Modifications

Add the following Subsection:

643-2.02 CRASHWORTHINESS. Submit documentation, by the method indicated, that the following devices comply with the requirements of the National Cooperative Highway Research Program (NCHRP) Report 350, (Test Level 3) on the given schedule.

| Work Zone Traffic Control Device Compliance with NCHRP 350 |  |  |  |  |
| --- | --- | --- | --- | --- |
| ## Category | ## Devices | Compliance Required for New Devices* | Full Compliance Required** | Method of Documentation |
| 1 | Cones, candles, drums w/o attachments, delineators | 10/1/98 | 1/1/02 | Manufacturer’s Certification for devices exceeding height and weight limits |
| 2 | Barricades, portable sign supports, drums w/ lights, other devices weighing less than 45 kg but not included in category 1. | 10/1/00 | 1/1/04 | FHWA approval letter. |
| 3 | Truck mounted attenuators and portable crash cushions. | 10/1/98 | 1/1/02 | FHWA approval letter. |
|  | Portable concrete barriers | 10/1/02 | 1/1/08 | FHWA approval letter. |

*  All devices purchased after this date.

**All devices used after this date.

Category 1 devices that exceed the following weights and heights require certification that they meet the evaluation criteria of NCHRP Report 350, Test Level 3. This certification may be a one-page affidavit signed by the vendor.  Documentation supporting the certification (crash tests and/or engineering analysis) must be kept on file by the certifying organization.  No certification is required for devices within the weight and height limitations.

Composition		Weight		Height

Cones		Rubber			 9 kg	 920 mm

Plastic			 9 kg	1220 mm

Candles	Rubber			 6 kg	920 mm

Plastic			 6 kg	920 mm

Drums		Hi Density Plastic	35 kg	920 mm

Lo Density Plastic	35 kg	920 mm

Delineators	Plastic or Fiberglass	 N/A	1220 mm

Category 2 and listed category 3 devices may be documented by submitting an official letter from the Federal Highway Administration stating the device NCHRP 350, Test Level 3 requirements. Letters for many devices may be found on the FHWA’s Work Zone Device web site: (http://safety.fhwa.dot.gov/roadside/know/workzone/index.htm).

Submit documentation of compliance to the Engineer before using devices on the project. (9/29/00) M91

## Special Provisions

643-3.01 GENERAL CONSTRUCTION REQUIREMENTS. Add the following: Whenever construction activity encroaches onto the safe route in a traffic control zone, the Contractor shall station a flagger at the encroachment to assist pedestrians and bicyclists past the construction activity. (11/06/01)R222M98

Standard Modifications

643-3.02 ROADWAY CHARACTERISTICS DURING CONSTRUCTION.  In the fourth paragraph, third sentence, change “crossings” to “closures”.  (06/25/99)M 80

## Special Provisions

643-3.04 TRAFFIC CONTROL DEVICES.  Add the following to 1. Embankments.:  Close all trenches and excavations at the end of each continuous work shift.

Add the following to 3. Fixed Objects.:  Remove all obstructions greater than 100 mm above the nominal foreslope grade at the end of each continuous work shift.

Delete item 6 and replace with the following:

6.	Street Sweeping.  Keep free of loose material all paved portions of the roadway and haul routes open to the public, including sections of roadway off the project where your operations have deposited loose material using a street sweeper that can collect materials rather than eject them to the shoulder of the road.

7.	Power Brooming.  Use a power broom capable of ejecting all loose material to the shoulder of the road.  Remove all loose material from all paved portions of the roadway and haul routes open to the public.  This includes sections of roadway off the project where the Contractor’s operations have deposited loose material.

Change items 7 and 8 to 8 and 9 respectively.

643-3.05 AUTHORITY OF THE ENGINEER. Add the following after the second sentence: In no case shall this time exceed 24 hours.

643-3.06 TRAFFIC PRICE ADJUSTMENT. Add the following: Traffic Price Adjustment will also apply to unacceptable driving conditions, such as severe bumps, “washboarding,” potholes, excessive dust or mud, or dirty or out of place traffic control devices. The Engineer will make the sole determination as to whether the roadway or pedestrian facility is acceptable for full unimpeded use by the public. Failure to maintain an acceptable infrastructure or traffic control plan will result in a price adjustment equal to 100 percent of the applicable rate shown in Table 643-1, for the time that the roadway or pedestrian facility is in an unacceptable condition.

Delete Table 643-1 and substitute the following:

TABLE 643-1

ADJUSTMENT RATES

| Published ADT | Dollars/Minute of Delay/Lane |
| --- | --- |
| 0-4,999 | $10 |
| 5,000-9,999 | $30 |
| 10,000+ | $40 |

643-3.08 CONSTRUCTION SEQUENCING. Delete the last sentence and substitute the following: Unless otherwise determined by the Engineer and on an approved Traffic Control Plan (TCP), do not restrict traffic during the times listed below.

1.	0600 hours to 0800 hours

2.	No work shall begin on Deshka Landing Road, Mishap Road or Gomer Road prior to July 4, 2002.

Lane restrictions, if allowed shall be conducted so that no more than a 10 minute accumulated stopped delay, 40 vehicles, or 0.4 kilometers of traffic is detained, whichever occurs first, before releasing of the detained motorist.  During paving operations a 20 minute stopped delay will be allowed for all motorists except school buses.  If a queue of traffic develops at a stop, the entire queue must be emptied to include the last car that entered the queue at the time the queue was released.

The Contractor shall obtain the local school bus schedule and coordinate his work efforts to ensure the school buses are not delayed through the construction zone.  This plan shall be submitted, as a TCP, to the Engineer for approval before the implementation of the school bus coordination plan.  The Contractor shall make every effort not to delay school buses through the construction work zone.

643-3.09 INTERIM PAVEMENT MARKINGS. In the second paragraph, delete the words “or cover them with black removable preformed marking tape.”

Replace the first sentence in the last paragraph with the following:  Do not place final pavement markings until traffic has traveled over the seal coat or surface treatment for at least 15 days and no more than 21 days, as directed by the Engineer.

643-4.01 METHOD OF MEASUREMENT. Page 376, under item 6 “Interim Pavement Markings,” delete the second paragraph.

Add the following: No measurement required to provide a 24-hour toll free (1-800-###-####) "hotline road report" telephone with a prerecorded message, and weekly notices with daily updates.  All work will be subsidiary to Item 643(1) or 643(2), Traffic Maintenance.

643-5.01 BASIS OF PAYMENT. Add the following:

The Engineer does not require a change order/directive for Item 643(25) Traffic Control.

TRAFFIC CONTROL RATE SCHEDULE

| Traffic Control Device | Pay Unit | Unit Rate |
| --- | --- | --- |
| Construction Signs | Each/Day | $ 5.00 |
| Special Construction Sign | Square Meter | $215.00 |
| Type II Barricade | Each/Day | $ 3.00 |
| Type III Barricade | Each/Day | $ 10.00 |
| Traffic Cone or Tubular Marker | Each/Day | $ 1.00 |
| Drums | Each/Day | $ 3.00 |
| Sequential Arrow Panel | Each/Day | $55.00 |
| Portable Concrete Barrier | Each | $60.00 |
| Temporary Crash Cushion | Each | $2,500.00 |
| Pilot Car | Hour | $65.00 |
| Watering | Kiloliter | $5.25 |
| Street Sweeping | Hour | $150.00 |
| Power Broom | Hour | $75.00 |
| Plastic Safety Fence | Meter | $8.00 |
| Portable Changeable Message Board Sign | Calendar Day | $150.00 |
| Temporary Sidewalk Surfacing | Square Meter | $12.50 |
| Flexible Markers | Each | $50.00 |
| Removal of Pavement Markings | Meter | $4.00 |
| Temporary Guardrail | Meter | $70.00 |
| Interim Pavement Markings Painted Markings Removable Preformed Markings Temporary Raised Pavement Markings Word or Symbol Markings | Meter Meter Meter Each | $0.90 $2.13 $0.24 $40.00 |

Payment for Item 643(15), the Engineer will pay Flagging on a contingent sum basis at the rate of $32.00/hour. The Engineer does not require a change order/directive for the flagging pay item.  (11/29/01)R222M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

643(15)	Flagging	 Contingent Sum

SECTION 644

SERVICES TO BE FURNISHED BY THE CONTRACTOR

#### Special Provisions

644-2.01 FIELD OFFICE. Delete this Subsection in its entirety and substitute the following: Furnish and maintain a suitable office for the Engineer, available for occupancy from two weeks prior to commencing work, through 30 days after issuance of the notice of project completion as defined in Subsection 105-1.15. The following office requirements shall be met:

1.	A minimum of 100 square meters of floor area. The office area shall be divided so that it contains an office room separated by a closable door. The office room shall have a minimum of 15 square meters of floor area.

2.	A thermostatically controlled interior heating system with necessary fuel.

3.	Adequate electrical lighting and 120 volt, 60 hertz power, with a minimum of six (6) electrical outlets.

4.	A minimum of 9 square meters of window area and adequate ventilation.

5.	Adequate parking for a minimum of 16 vehicles, with one handicap parking space meeting the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

6.	Attached indoor plumbing with sanitary lavatory facilities and potable drinking water provided.

7.	Three (3) telephone service lines available at the office location.

8.	If a part of the Contractor's building, it shall be completely partitioned off from the balance of the structure and provided with a separate outside door equipped with a lock.

9.	Centrally located within the Palmer-Wasilla Area.

10.	The Engineer's office shall be accessible by disabled individuals from the designated handicap parking space in accordance with the requirements of Americans with Disabilities Act Accessibility Guidelines (ADAAG).

11.	Weekly janitorial service consisting of emptying trash receptacles, vacuuming office area and cleaning restrooms and counter areas.

12.	Provide one mobilization and one demobilization of the Engineer’s office equipment and furniture.

644-2.02 FIELD LABORATORY. Delete sub-item g on page 380 and substitute the following:

g.	1900 liter capacity tank with a pressure pump or a commercial pressurized system.

Add the following:

- Supply 240 volt, 60 hertz power, a 45 kilogram propane bottle, and a 1900 liter capacity water tank with a pressure pump or a commercial pressurized system for a State provided portable asphalt lab at a location designated by the Engineer.

- Provide one mobilization and one demobilization of the Engineer's laboratory equipment.

644-2.05 VEHICLES. Add the following: Equip vehicles used for Engineering Transportation with a yellow rotating beacon light wired into the vehicle’s system with a dash mounted switch easily accessible to the vehicle operator.

644-4.01 BASIS OF PAYMENT. . In the last full paragraph, beginning with “Furnishing the following is subsidiary”, after “platform scales,” insert “ scale operators.”

(06/25/99)M 81

Add the following: Electricity, propane and water supplied for the State provided portable asphalt lab will not be paid for separately, but will be subsidiary to Item 644(1) Field Office.

(9/28/00)R63M98

644-5.01 BASIS OF PAYMENT.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

644(6A)	Engineering Transportation	Each

SECTION 646

CPM SCHEDULING

Special Provisions

646-2.01 SUBMITTAL OF SCHEDULE.  Delete this Subsection in its entirety and replace with the following: Submit a detailed draft CPM schedule at the preconstruction conference for the Engineer’s approval.   The finalized CPM schedule must be completed and accepted prior to any work being done on the project site.

646-3.01 REQUIREMENTS AND USE OF SCHEDULE.  Delete item 2.   60-Day Preliminary Schedule.

(3/12/01)R261M98

Add the following Section:

SECTION 647

EQUIPMENT RENTAL

## Special Provisions

647-1.01 DESCRIPTION. This item consists of furnishing construction equipment, operated, fueled and maintained, on a rental basis for use in construction of extra or unanticipated work at the direction of the Engineer. Construction equipment is defined as that equipment actually used for performing the items of work specified and shall not include support equipment such as, but not limited to, hand tools, power tools, electric power generators, welders, small air compressors and other shop equipment needed for maintenance of the construction equipment.

The work is to be accomplished under the direction of the Engineer, and the Contractor's operations shall at all times be in accordance with the Engineer's instructions. These instructions by the Engineer shall be to the Contractor's supervisory personnel only, not to the operators or laborers. In no case shall these instructions by the Engineer be construed as making the Department liable for the Contractor's responsibility to prosecute the work in the safest and most expeditious manner.

647-2.01 EQUIPMENT FURNISHED. In the performance of this work, the Contractor shall furnish, operate, maintain, service, and repair equipment of the numbers, kinds, sizes, and capacities set forth on the Bid Schedule or as directed by the Engineer. The operation of all equipment shall be by skilled, experienced operators familiar with the equipment.

The kinds, sizes, capacities, and other requirements set forth shall be understood to be minimum requirements. The number of pieces of each equipment to be furnished and used shall be as the Engineer considers necessary for economical and expeditious performance of the work. The equipment shall be used only at such times and places as the Engineer may direct.

All equipment shall be in first-class working condition and capable of full output and production. The minimum ratings of various types of equipment shall be as manufactured and based on manufacturer's specifications. Alterations will not be considered acceptable in achieving the minimum rating. Equipment shall be replaced at any time when, in the opinion of the Engineer, their condition is below that normal for efficient output and production.

Equipment shall be fully operational, which includes the operators, oilers, tenders, fuel, oil, air hose, lubrication, repairs, maintenance, insurance, and all incidental items and expenses.

647-2.02 EQUIPMENT OPERATORS AND SUPERVISION PERSONNEL. Equipment operators shall be competent and experienced and shall be capable of operating the equipment to its capacity. All personnel furnished by the Contractor shall be, and shall remain during the work hereunder, employees solely of the Contractor.

The Contractor shall furnish, without direct compensation, a job superintendent or Contractor's representative together with such other personnel as are needed for Union, State, or Federal requirements and in servicing, maintaining, repairing and caring for the equipment, tools, supplies, and materials provided by the Contractor and involved in the performance of the work. Also, the Contractor shall furnish, without direct compensation, such transportation as may be appropriate for the personnel.

647-3.01 CONSTRUCTION REQUIREMENTS. The performance of the work shall be in accordance with the instructions of the Engineer, and with recognized standards and efficient methods.

The Contractor shall furnish equipment, tools, labor, and materials in the kinds, number, and at times directed by the Engineer and shall commence, continue, and stop any of the several operations involved in the work only as directed by the Engineer.

Normally, the work is to be done when weather conditions are reasonably favorable, six (6) days per week, Mondays through Saturdays, holidays excepted.

The Engineer will begin recording time for payment each shift when the equipment begins work on the project. The serial number and brief description of each item of equipment listing in the bid schedule and the number of hours, or fractions thereof to the nearest one-quarter hour, during which equipment is actively engaged in construction of the project shall be recorded by the Engineer Each day's activity will be recorded on a separate sheet or sheets, which shall be verified and signed by the Contractor's representative at the end of each shift, and a copy will be provided to the Contractor's representative.

647-4.01 METHOD OF MEASUREMENT. The number of hours of equipment operation to be paid for shall be the actual number of hours each fully operated specified unit of equipment, or each fully operated specified combination of units of equipment, is actually engaged in the performance of the specified work on the designated areas in accordance with the instruction of the Engineer. The pay time will not include idle periods, and no payment will be made for time used in oiling, servicing, or repairing of equipment, or in making changeovers of parts to the equipment. Travel time to or from the project, will not be authorized for payment.

647-5.01 BASIS OF PAYMENT. Payment for Item 647(1), Wide Pad Dozer, 48 kW Minimum will be paid by the hour.  This shall be full compensation for furnishing, operating, maintaining, servicing and repairing the equipment, and for all incidental costs related to the equipment. Furnishing and operating of equipment of heavier type, larger capacity, or higher wattage than specified will not entitle the Contractor to any extra compensation. (11/12/98)R15M98

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

647(1)	Wide Pad Dozer, 48 kW Minimum	Hour

# Add the following Section:

# SECTION 650

PARK FACILITIES

Special Provisions

650-1.01 DESCRIPTION.  This work consists of furnishing, constructing and installing concrete parking bumpers in conformance with the Plans.

650-2.01 MATERIALS.  Present submittals for approval by the Department prior to incorporating materials into the work.

Materials shall be new and conform to the Plans.  The concrete shall conform to Section 501.

650-2.02 CONCRETE PARKING BUMPERS.  Concrete parking bumpers for handicap parking spaces shall be colored blue either by painting with a blue pigmented paint or cast with a blue tinted concrete, as approved by the Engineer.

CONSTRUCTION REQUIREMENTS

650-3.01 GENERAL.  Locations shown on the Plans of park facilities are approximate.  The Engineer will field locate park facilities at the time of construction.

Salvage the existing wood parking bumpers and existing barrier rail at Willow Creek and deliver them to:

Nancy Lake Ranger Station

Mile 1.3 Nancy Lake Parkway

Willow, Alaska 99688

(907) 495-6273

650-4.01 METHOD OF MEASUREMENT.  Measurement of Section 650 bid items shall be for each unit installed and accepted by the Engineer.  Concrete and associated mounting hardware will not be measured.

650-5.01 BASIS OF PAYMENT.  The accepted quantities will be paid for at the Contract price per unit of measurement for each item shown in the Bid Schedule.

Salvaging the existing wood parking bumpers and existing barrier rail are subsidiary to Item 650(17), Concrete Parking Bumper and no separate payment shall be made.

Payment will be made under:

Pay Item No.	Pay Item	Pay Unit

650(17)	Concrete Parking Bumper	Each

# SECTION 660

SIGNALS AND LIGHTING

Special Provisions

660-1.03 EQUIPMENT LIST(S) AND DRAWINGS.  Delete item number 1 that follows the first paragraph, and add the following: The Approved Products List does not apply to the 660 items.  Provide catalog cuts of all materials to the Engineer for review and approval.

Add the following to the last paragraph: The Engineer will deliver one copy each to State Maintenance and Operations; Technical Services; and attach the appropriate sheets of the last set in clear plastic envelopes to the inside of each controller assembly and load center.

660-2.01 EXCAVATING AND BACKFILLING. In the fourth paragraph, change “Subsection 204-3.01" to “Section 204.”

Add the following after the fourth paragraph: Backfill the first 150 mm lift with material free of rocks exceeding a 25 mm maximum dimension.

660-2.03 FOUNDATIONS.  Delete the Pile Foundations subsection and substitute the following:

Pile Foundations.  The use of pile foundations on the project is not permitted.

660-2.04 POLES, STEEL PEDESTALS AND POSTS. Add the following: Furnish back-up calculations stamped by a registered professional engineer.

Relocate existing standards per the plans in a manner that maintains their existing condition. Replace standards damaged or destroyed by your operations at your expense. When you relocate galvanized standards with rusted or scarred surface areas, repair these areas in accordance with Subsection 660-2.15, Galvanizing.

Complete all welding design and fabrication according to the latest edition of the AWS D1.1, Structural Welding Code- Steel

- Circumferential Welded Splices

Inspect 100% of CJP welds by radiography (RT)

- Longitudinal Seam Welds

- Inspect 100% of CJP welds by radiography (RT)

- Inspect 25% of all PJP welds of longitudinal seams by magnetic particle (MT)

- Base Connection Welds

- Inspect 100% of all base connection welds.

- Inspect CJP welds by RT

- Inspect fillet welds by MT

- At least 14 calendar days before welding, submit the welding plan and mill certification reports for all steel to the Quality Assurance (QA) representative for approval.  Do not begin welding until these items have been returned approved in writing by the QA representative.  The welding plan shall consist of the following:

- Welding Procedure Specification (WPS)

- Procedure Qualification Record (PQR)

- Welder Performance Qualification Record (WPQR)

- Visual Inspection Form

- Report of Nondestructive Examination (NDE) of Welds

- The Contractor’s Quality Control (QC) manager with documentation of qualifications

- Furnish all Quality Control inspection necessary to ensure that the materials meet the requirements of the contract documents and that workmanship meets the requirements of AWS D1.1.

- Correct all deficiencies in materials and workmanship revealed by inspection in accordance with AWS D1.1 without additional compensation.

- Furnish all completed QC inspection documents to the QA representative as designated by the State.

660-2.05 CONDUIT. Add the following: The Engineer will only allow trenching to install conduits across roadways scheduled to be paved or overlaid.  After the Contractor paves the final asphalt course, however, the Engineer will not allow trenching.  Trenching will not be permitted when bored casing, as indicated on the Plans, is to be installed.

Use Standard Schedule 40 pipe conforming to ASTM A53 to the sizes and at locations shown on the plans for bored casings.  Diameters indicated are DN Designator.

660-2.06 JUNCTION BOXES. Delete the second paragraph and substitute the following: Only use pre-cast reinforced concrete junction boxes conforming to the sizes and details shown on the plans.  All junction box lids shall be cast iron.

660-2.08 CONDUCTORS. Delete the first paragraph of item 2. Power Conductors and Cables and add the following: Use power conductors and cables manufactured according to ICEA publication S-66-524

and NEMA Publication No. WC7, and which are UL listed and labeled for direct burial and resistance to sunlight. Furnish conductors insulated with chemically cross-linked polyethylene UL listed and labeled as type XHHW-2. Use cables rated for 600 volts AC operation.

Furnish cables consisting of three #8 AWG conductors with conductor insulation colored black, white, and red. Furnish cables with three conductors larger than #8 AWG with conductor insulation colored black, white, and red, or with all black conductor insulation with printed numbers identifying each conductor per ICEA method 4.

Delete subparagraph “d” of item 2. Power Conductors and Cables and add the following: Furnish highway and sign illumination cables with #8AWG conductors with a low density, high molecular weight polyethylene jacket.

660-2.09 WIRING. Delete the first paragraph and add the following: Install flashing beacon cables with no splices in them.

Crimp spade type terminals onto all conductors that attach to terminal blocks. When reusing cabinets, replace terminal blocks that lack enough terminals. Make the wiring within cabinets neat, and cable conductors together with self-clinching nylon ties.

Delete paragraph numbered 14. and add the following: Furnish the two types of identification tags listed below that feature hand written legends. Write the legends specified neatly and legibly, using a black marking pen recommended by the tag manufacturer. Replace at no expense to the State all identification tags the Engineer deems illegible.

1.	Use identification cable ties for labeling loop detector tails and the paired conductors included in each loop lead-in cable in the controller cabinet. Furnish identification cable ties made of nylon that feature a nonmagnetic stainless steel locking device embedded in the head and a tag attached "flag style" to the head. The cable ties shall consist of a single strap with a minimum size tag of 20 mm by 9 mm.

2.	To label all other cables, use cable tags made of nylon reinforced vinyl impervious to the elements and which will not tear. Provide tags with a 100 mm by 44 mm minimum size that attach flag style at one corner to a single strap. Furnish yellow tags for labeling all signal and interconnect cables and red tags for labeling lighting and feeder cables.

660-2.11 BONDING AND GROUNDING.  Add the following after the first paragraph: Install a 19 mm by 3.0 m copper clad ground rod under “P” type controller cabinet foundations.

Add the following after the second paragraph: All hardware, including grounding bushings, ground rods, and ground rod clamps shall be UL listed. Furnish threaded type grounding bushings that are made of malleable iron or steel and feature a mechanically or hot dip galvanized finish.  Bushings shall also feature an insulated throat, a tin-plated copper saddle for attaching the grounding conductors, and stainless steel set screws.

Where wire is pulled and reinstalled in existing conduits, the bare No. 8 AWG copper wire shall also be installed. Where conduits are installed for future conductors, the above mentioned copper wire may be omitted. (3/30/00)R215M98

660-3.07 SHOP TESTS. In the second paragraph, change "6 weeks" to "2 weeks".

660-3.09 SIGNAL HEADS

Change the Subsection titled Optical Units.  to:  Incandescent Optical Units

660-3.11 SIGNAL HEAD MOUNTING. Add the following: Remove all burrs from the inside and outside of all holes made to pass conductors through the walls of posts, poles, and mast arms to prevent scraping of the conductors.

660-5.01 BASIS OF PAYMENT. Add the following: The lump sum prices paid for the items included in the Contract includes full compensation for all work involved in furnishing and installing, assembling, modifying, and removing the components of the systems shown on the plans. This includes: completing all excavation to install foundations, conduits, and junction boxes, backfilling and compacting trenches, removing and replacing improvements, installing sumps under junction boxes, and pulling conductors. The lump sum prices paid also include full compensation for all work specified in the Standard Specifications and Special Provisions. This includes: getting all materials approved; preparing as-built plans, maintaining the electrical systems, adjusting junction boxes to grade, making all splices, labeling all conductors, completing all tests, and delivering salvaged electrical equipment.

SECTION 670

TRAFFIC MARKINGS

## Special Provisions

670-3.04 PAINT REMOVAL. Change the title of this Subsection to "Pavement Markings Removal".

Replace the first sentence of the second paragraph with the following: Remove pavement markings to the fullest extent possible by a method that does not materially damage the surface or texture of the pavement. Painting over existing striping does not meet the requirement for removal. Any method utilizing burning with an open flame shall not be used for the removal of pavement markings on the final paving lift.

670-3.06 TOLERENCES FOR LINE STRIPING. Replace criteria number two with the following:

- Width of Stripe. The width shall not vary more than 6 mm in width in any 15 m longitudinal run from the plan quantity.

SECTION 702

ASPHALT MATERIALS

Special Provisions

702-2.01 ASPHALT CEMENTS. Add the following: Performance Graded Asphalt Binder shall conform to the requirements of AASHTO MP1 and the additional properties defined by AASHTO T 53 and ASTM D 5801 assigned to each grade.

Performance Graded Asphalt Cement

Property	Standard	PG 52-28	PG 58-28	PG 64-28

Softening Point	AASHTO T 53	(none)	49oC	52oC

Toughness (min)	ASTM D 5801	(none)	12.4 N-m	12.4 N-m

Tenacity (min)	ASTM D 5801	(none)	8.5 N-m	8.5 N-m

(9/18/00)R244M98

SECTION 703

AGGREGATES

# Special Provisions

703-2.03 AGGREGATE FOR BASE. Delete Table 703-2 and substitute the following:

## TABLE 703-2

## AGGREGATE FOR UNTREATED BASE

## Percent Passing By Weight

| Sieve Designation | Grading C-1 | Grading D-1 | Grading E-1 |
| --- | --- | --- | --- |
| 37.5 mm | 100 |  |  |
| 25 mm | 70-100 | 100 | 100 |
| 19 mm | 60-90 | 70-100 | 70-100 |
| 9.5 mm | 45-75 | 50-79 | 50-85 |
| 4.75 mm | 30-60 | 35-58 | 35-65 |
| 2.36 mm | 22-52 | 20-47 | 23-50 |
| 0.600 mm | 10-33 | 10-26 | 13-31 |
| 0.300 mm | 6-23 | 6-19 | 10-26 |
| 0.075 mm | 0-6 | 0-6 | 8-15 |

(2/28/00)R117M98

Standard Modifications

703-2.04 AGGREGATE FOR ASPHALT CONCRETE PAVEMENT.  Under Blended Aggregate, delete the last sentence and substitute: “Ensure that the fraction actually retained between any two consecutive sieves larger than the 0.150 mm is not less than 2% of the total."

703-2.07 SELECTED MATERIAL.  Replace the last sentence in both items 1. and 2. with the following: The percent passing the 0.075 mm sieve will be determined on minus 75 mm material.(06/25/99)M 82

SECTION 710

FENCE AND GUARDRAIL

# Special Provisions

710-2.11 GUARDRAIL TERMINALS. Add the following:

The preferred design installation is the ET-2000 LET.  In some cases the SRT-350 will be allowed.

The current guardrail end terminal drawings approved by the Department are as follows:

# Drawing	Original	Latest

# Number	Date	Revision	Comments

# ET-2000 LET	Metric	SS 155M	7/18/00	None	11.4 m, 7 tube, Plus head

# English	SS 155	5/18/00	None	37.5’, 7 tube, Plus head

# SRT-350	Metric	SS 351M	1/19/01	4/14/01	11.4m Straight flare,

# 6 post, 2 HBA

# English	SS 351	12/12/00	4/14/01	37.5’ Straight flare,

# 6 post, 2 HBA

(08/15/01)R249

SECTION 727

SOIL STABILIZATION MATERIAL

Add the following Subsection:

727-2.04 HYDRO MATTING. Hydro matting shall be a hydraulically applied system of long strand fibers joined together by a high-strength adhesive to create a continuous three dimensional blanket that adheres to the soil surface to form a bonded fiber matrix. The system shall be applied to the soil as a viscous mixture, which upon drying, creates a high strength, porous and erosion resistant mat. Upon drying, the matrix shall not inhibit the germination and growth of plants beneath the layer. The matrix shall retain its form despite rewetting.

(6/30/97)R223M

SECTION 729

GEOTEXTILES

Special Provisions

729-2.01 EMBANKMENT SEPARATION AND REINFORCEMENT.  Under 1. Separation, replace ‘(medium survivability)’ with: ‘(Class 3)’.  Under 2. Reinforcement, replace ‘Separation (high survivability)’ with: ‘Stabilization’.

729-2.02 SUBSURFACE DRAINAGE AND EROSION CONTROL.  Under 2. Erosion control, replace ‘Meet AASHTO M 288 for Erosion Control’ with: ‘Meet AASHTO M 288 for Permanent Erosion Control’.

729-2.04 SEDIMENT CONTROL.  Replace ‘Meet AASHTO M 288 for Sediment Control’ with: ‘Meet AASHTO M 288 for Temporary Silt Fence’.

(2/28/00)R229M98

SECTION 730

SIGN MATERIALS

# Special Provisions

730-2.04 SIGN POSTS. Under item 1., Metal Pipe Posts, add the following to paragraph a.: Posts conforming to ASTM A53 shall be either Type E grade B, or Type S grade B. (2/29/00)R81M

Standard Modifications

In item 2. Perforated Steel Posts., paragraph a., first sentence, replace “ASTM A 446” with “ASTM A 653 and ASTM A 924”.

(06/25/99)M 83

#### Special Provisions

Add the following:

5.	Structural Tubing and W Shape Beams.

a.	Structural tubing shall conform to either ASTM A500, grade B, or ASTM A501. The tubing shall be square and of the dimensions called for in the plans with 5 millimeter thick walls. 11 millimeter diameter holes shall be drilled as required to permit mounting of the sign.

b.	W shape beams shall conform to ASTM A36.

c.	Structural tubing and W shape beams shall be hot dip galvanized in accordance with 1.b. of this Subsection. Damaged and abraded tubes and beams shall be repaired in accordance with 1.c. of this Subsection.

(2/29/00)R81M

APPENDIX A

PERMITS

APPENDIX B

CONSTRUCTION SURVEYING REQUIREMENTS

APPENDIX C

MATERIALS CERTIFICATION LIST

APPENDIX D

ESCP